## Document
Document Reference | Document Title | Revision Number | Revision Date | Document Revision Object | Document Client Reference | Discipline | Transmittal Date | Transmittal Reference | Specific Transmittal Number | Required Action | Response Due Date | Actual Response Date | Document Status | Client Transmittal Ref Number | Remarks | Client Transmittal Date
036909C-1012-PID-0021-1245 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Flue Gas | A | 2018-11-15 | IFR | OL1-2G43-1245 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1240 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Burners | A | 2018-11-15 | IFR | OL1-2G43-1240 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1235 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas | A | 2018-11-15 | IFR | OL1-2G43-1235 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1056-MSD-0011-5616 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Sludge Dewatering Package | A | 2018-12-20 | IFA | OL1-2G74-5616 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1056-MSD-0011-5614 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Biotreatment Package | A | 2018-12-20 | IFA | OL1-2G74-5614 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1056-MSD-0011-5613 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - CPI & IGF Packages | A | 2018-12-20 | IFA | OL1-2G74-5613 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1056-MSD-0011-5617 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Slop and Oil Sludge | A | 2018-12-20 | IFA | OL1-2G74-5617 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1051-MSD-0011-5101 | Material Selection Diagram - Olefins Unit 10 - 51 BFW- Steam- Cond Systems - Steam Balance Diagram | A | 2018-12-20 | IFA | OL1-2G74-5101 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1056-MSD-0011-5602 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Surface Runoff Collection | A | 2018-12-20 | IFA | OL1-2G74-5602 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1056-MSD-0011-5603 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Cracker Holding Basin | A | 2018-12-20 | IFA | OL1-2G74-5603 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1055-MSD-0011-5501 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - Flare and Blowdown System | A | 2018-12-20 | IFA | OL1-2G74-5501 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1051-MSD-0011-5104 | Material Selection Diagram - Olefins Unit 10 - 51 BFW Steam Cond Systems - Furnace Blowdown System | A | 2018-12-20 | IFA | OL1-2G74-5104 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1056-MSD-0011-5601 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Oily Wastewater Collection | A | 2018-12-20 | IFA | OL1-2G74-5601 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1055-MSD-0011-5511 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - HP-LLDPE LP Flare | A | 2018-12-20 | IFA | OL1-2G74-5511 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1056-MSD-0011-5612 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Oily Wastewater Equilization Tank | A | 2018-12-20 | IFA | OL1-2G74-5612 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1059-MSD-0011-5911 | Material Selection Diagram - Olefins Unit 10 - 59 Utilities And Auxiliaries Complex U & O Chemical Storage | A | 2018-12-20 | IFA | OL1-2G74-5911 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1056-MSD-0011-5615 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Check Basin | A | 2018-12-20 | IFA | OL1-2G74-5615 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1056-MSD-0011-5604 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Domestic Wastewater Collection | A | 2018-12-20 | IFA | OL1-2G74-5604 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1056-MSD-0011-5611 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - OSBL Oily Wastewater Collection | A | 2018-12-20 | IFA | OL1-2G74-5611 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1056-MSD-0011-5610 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - HP Flare Area SW & Oily WW Collection | A | 2018-12-20 | IFA | OL1-2G74-5610 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1052-PID-0031-5210 | P&ID - Olefins Unit 10 - Fuel System - Fuel Gas Distribution - Sheet 1 | A | 2019-01-30 14:00 | IFR | OL1-2G43-5210 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1052-PID-0031-5211 | P&ID - Olefins Unit 10 - Fuel System - Fuel Gas Distribution - Sheet 2 | A | 2019-01-30 14:00 | IFR | OL1-2G43-5211 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1052-PID-0031-5202 | P&ID - Olefins Unit 10 - Fuel System - Fuel Gas Drum | A | 2019-01-30 14:00 | IFR | OL1-2G43-5202 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1052-PID-0031-5203 | P&ID - Olefins Unit 10 - Fuel System - Pilot Gas Vaporizer | A | 2019-01-30 14:00 | IFR | OL1-2G43-5203 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1052-PID-0031-5201 | P&ID - Olefins Unit 10 - Fuel System - Fuel Gas | A | 2019-01-30 14:00 | IFR | OL1-2G43-5201 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1012-JSS-0127-2004 | Project Specification for Fabrication of Convection Coil for Cracking Furnaces | A | 2019-02-07 | IFR | OL1-2M92-2004 | ME | 2019-02-12 | 036909C-JVD-TRN-00842 | 036909C-JVD-TRN-00842 | IFR | 2019-02-26 | 2019-03-07 | R1-No comments | TPSK-LSPA1-T-ME-00842
036909C-1000-JSS-0910-0001 | ME-010 Centrifugal Pump | 0 | 2019-01-07 | IMP | OL1-2R03-0010 | ME | 2019-01-22 | 036909C-JVD-TRN-00693 | 036909C-JVD-TRN-00693, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 | 2019-02-14 | R1-No comments | TPSK-LSPA1-T-ME-00693
036909C-1000-JSS-1140-0001 | ME-013 Diesel Engine | 0 | 2019-01-07 | IMP | OL1-2R03-0013 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 |  | Transmitted | TPSK-LSPA1-T-ME-00668
036909C-1000-JSS-1160-0001 | ME-022 Special Purpose Gear | 0 | 2019-01-07 | IMP | OL1-2R03-0022 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 |  | Transmitted | TPSK-LSPA1-T-ME-00668
036909C-1000-JSS-1013-0001 | ME-016 Centrifugal Compressor For PA-IA Servise | 0 | 2019-01-07 | IMP | OL1-2R03-0016 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 |  | Transmitted | TPSK-LSPA1-T-ME-00668
036909C-1000-JSS-1011-0001 | ME-014 Centrifugal Compressor | 0 | 2019-01-07 | IMP | OL1-2R03-0014 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 |  | Transmitted | TPSK-LSPA1-T-ME-00668
036909C-1000-JSS-0910-0002 | ME-050 Centrifugal Pump - Non API | 0 | 2019-01-07 | IMP | OL1-2R03-0500 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 |  | Transmitted | TPSK-LSPA1-T-ME-00668
036909C-1056-PFD-0030-5617 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Slop & Oil Sludge | B | 2018-10-09 | IFD | OL1-2G42-5617 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1059-PFD-0030-5911 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Complex U & O Chemical Storage | B | 2018-10-09 | IFD | OL1-2G42-5911 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1059-PFD-0030-5901 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Chemical Storage | B | 2018-10-09 | IFD | OL1-2G42-5901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1056-PFD-0030-5601 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Collection | B | 2018-10-09 | IFD | OL1-2G42-5601 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1055-PFD-0030-5501 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Flare and Blowdown System | B | 2018-10-09 | IFD | OL1-2G42-5501 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1055-PFD-0030-5502 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Process Vent Gas Collection | B | 2018-10-09 | IFD | OL1-2G42-5502 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1055-PFD-0030-5512 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Enclosed Ground Flare | B | 2018-10-09 | IFD | OL1-2G42-5512 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1055-PFD-0030-5511 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - HP - LLDPE LP Flare | B | 2018-10-09 | IFD | OL1-2G42-5511 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1056-PFD-0030-5604 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Domestic Wastewater Collection | B | 2018-10-09 | IFD | OL1-2G42-5604 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1056-PFD-0030-5611 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - OSBL Oily Wastewater Collection | B | 2018-10-09 | IFD | OL1-2G42-5611 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1056-PFD-0030-5610 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - HP Flare Area SW & Oily WW Collection | B | 2018-10-09 | IFD | OL1-2G42-5610 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1054-PFD-0030-5401 | Utility Flow Diagram - Olefins Unit 10 - 54 - Air and Nitrogen System - Plant Air Instrument Air and Nitrogen Systems | B | 2018-10-09 | IFD | OL1-2G42-5401 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1056-PFD-0030-5603 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Cracker Holding Basin | B | 2018-10-09 | IFD | OL1-2G42-5603 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1056-PFD-0030-5602 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Surface Runoff Collection | B | 2018-10-09 | IFD | OL1-2G42-5602 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1030-PFD-0010-3003 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier | B | 2018-10-09 | IFD | OL1-2G41-3003 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1030-PFD-0010-3002 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Evaporation | B | 2018-10-09 | IFD | OL1-2G41-3002 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1030-PFD-0010-3005 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation | B | 2018-10-09 | IFD | OL1-2G41-3005 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1030-PFD-0010-3004 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing | B | 2018-10-09 | IFD | OL1-2G41-3004 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1028-PFD-0010-2803 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | B | 2018-10-09 | IFD | OL1-2G41-2803 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1028-PFD-0010-2802 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | B | 2018-10-09 | IFD | OL1-2G41-2802 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1030-PFD-0010-3001 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation | B | 2018-10-09 | IFD | OL1-2G41-3001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1028-PFD-0010-2804 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | B | 2018-10-09 | IFD | OL1-2G41-2804 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1029-PFD-0010-2901 | Process Flow Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | B | 2018-10-09 | IFD | OL1-2G41-2901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1051-PFD-0030-5104 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Furnace Blowdown System | B | 2018-10-09 | IFD | OL1-2G42-5104 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1051-PFD-0030-5102 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate and Boiler Feedwater Systems | B | 2018-10-09 | IFD | OL1-2G42-5102 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1053-PFD-0030-5311 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Tower | B | 2018-10-09 | IFD | OL1-2G42-5311 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1052-PFD-0030-5201 | Utility Flow Diagram - Olefins Unit 10 - 52 - Fuel System - Fuel Gas System | B | 2018-10-09 | IFD | OL1-2G42-5201 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1053-PFD-0030-5301 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Water Diagram | B | 2018-10-09 | IFD | OL1-2G42-5301 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1031-PFD-0010-3102 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam and Condensate System | B | 2018-10-09 | IFD | OL1-2G41-3102 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1031-PFD-0010-3101 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration | B | 2018-10-09 | IFD | OL1-2G41-3101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1051-PFD-0030-5101 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Steam Balance Diagram | B | 2018-10-09 | IFD | OL1-2G42-5101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1039-PFD-0010-3901 | Process Flow Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage | B | 2018-10-09 | IFD | OL1-2G41-3901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1050-PFD-0030-5001 | Utility Flow Diagram - Olefins Unit 10 - 50 - Water System - Treated Potable and Demin Water Systems | B | 2018-10-09 | IFD | OL1-2G42-5001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1056-PFD-0030-5615 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Check Basin | B | 2018-10-09 | IFD | OL1-2G42-5615 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1056-PFD-0030-5616 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Sludge Dewatering Package | B | 2018-10-09 | IFD | OL1-2G42-5616 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1056-PFD-0030-5612 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Equalization Tank | B | 2018-10-09 | IFD | OL1-2G42-5612 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1056-PFD-0030-5614 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Biotreatment Package | B | 2018-10-09 | IFD | OL1-2G42-5614 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1056-PFD-0030-5613 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - CPI & IGF Packages | B | 2018-10-09 | IFD | OL1-2G42-5613 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1026-PFD-0010-2603 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | B | 2018-10-09 | IFD | OL1-2G41-2603 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1026-PFD-0010-2604 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | B | 2018-10-09 | IFD | OL1-2G41-2604 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1025-PFD-0010-2506 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | B | 2018-10-09 | IFD | OL1-2G41-2506 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1026-PFD-0010-2602 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | B | 2018-10-09 | IFD | OL1-2G41-2602 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1026-PFD-0010-2601 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | B | 2018-10-09 | IFD | OL1-2G41-2601 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1027-PFD-0010-2704 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation | B | 2018-10-09 | IFD | OL1-2G41-2704 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1028-PFD-0010-2801 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | B | 2018-10-09 | IFD | OL1-2G41-2801 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1027-PFD-0010-2701 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Reactor & Depentanizer | B | 2018-10-09 | IFD | OL1-2G41-2701 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1027-PFD-0010-2703 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - Hydrog Reactivation Gas System | B | 2018-10-09 | IFD | OL1-2G41-2703 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1027-PFD-0010-2702 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Rerun Tower | B | 2018-10-09 | IFD | OL1-2G41-2702 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1024-PFD-0010-2404 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | B | 2018-10-09 | IFD | OL1-2G41-2404 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1024-PFD-0010-2405 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | B | 2018-10-09 | IFD | OL1-2G41-2405 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1024-PFD-0010-2401 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | B | 2018-10-09 | IFD | OL1-2G41-2401 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1024-PFD-0010-2403 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | B | 2018-10-09 | IFD | OL1-2G41-2403 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1024-PFD-0010-2402 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | B | 2018-10-09 | IFD | OL1-2G41-2402 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1025-PFD-0010-2504 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | B | 2018-10-09 | IFD | OL1-2G41-2504 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1025-PFD-0010-2505 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | B | 2018-10-09 | IFD | OL1-2G41-2505 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1025-PFD-0010-2501 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | B | 2018-10-09 | IFD | OL1-2G41-2501 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1025-PFD-0010-2503 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | B | 2018-10-09 | IFD | OL1-2G41-2503 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1025-PFD-0010-2502 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | B | 2018-10-09 | IFD | OL1-2G41-2502 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1021-PFD-0010-2102 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | B | 2018-10-09 | IFD | OL1-2G41-2102 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1021-PFD-0010-2101 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | B | 2018-10-09 | IFD | OL1-2G41-2101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1010-PFD-0010-1003 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | B | 2018-10-09 | IFD | OL1-2G41-1003 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1022-PFD-0010-2201 | Process Flow Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | B | 2018-10-09 | IFD | OL1-2G41-2201 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1023-PFD-0010-2305 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | B | 2018-10-09 | IFD | OL1-2G41-2305 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1020-PFD-0010-2002 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | B | 2018-10-09 | IFD | OL1-2G41-2002 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1010-PFD-0010-1001 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | B | 2018-10-09 | IFD | OL1-2G41-1001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00155
036909C-1020-PFD-0010-2001 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | B | 2018-10-09 | IFD | OL1-2G41-2001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1021-PFD-0010-2103 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | B | 2018-10-09 | IFD | OL1-2G41-2103 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1000-PFD-0010-0002 | Process Flow Diagram - Olefins Unit 10 - 00-General - Drawing Index | B | 2018-10-09 | IFD | OL1-2G41-0002 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1019-PFD-0010-1901 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | B | 2018-10-09 | IFD | OL1-2G41-1901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1000-PFD-0010-0010 | Block Flow Diagram - Olefins Unit 10 - 00-General - Overall Plant Scheme | B | 2018-10-09 | IFD | OL1-2G40-0010 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1012-PFD-0010-1201 | Process Flow Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | B | 2018-10-09 | IFD | OL1-2G41-1201 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1023-PFD-0010-2302 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | B | 2018-10-09 | IFD | OL1-2G41-2302 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1011-PFD-0010-1101 | Process Flow Diagram - Olefins Unit 10 - 11 - Furnaces - Recycle Gas Cracking Furnace | B | 2018-10-09 | IFD | OL1-2G41-1101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1023-PFD-0010-2301 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | B | 2018-10-09 | IFD | OL1-2G41-2301 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1019-PFD-0010-1902 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | B | 2018-10-09 | IFD | OL1-2G41-1902 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1000-PFD-0010-0001 | Process Flow Diagram - Olefins Unit 10 - 00-General - Legend & Symbols | B | 2018-10-09 | IFD | OL1-2G41-0001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00155
036909C-1023-PFD-0010-2303 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | B | 2018-10-09 | IFD | OL1-2G41-2303 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1023-PFD-0010-2304 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | B | 2018-10-09 | IFD | OL1-2G41-2304 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1000-DI-0007-0003 | Flare and Blowdown System Design Basis | A | 2018-09-06 | IFA | OL1-2G02-0003 | PE | 2018-09-07 | 036909C-JVD-TRN-00034 | 036909C-JVD-TRN-00034, ROC-TPSK-CECO-T-00001 | IFA | 2018-09-20 | 2018-09-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-00034 |  | 2018-09-07
036909C-1022-DI-0007-2201 | Area Basis of Design - 22-24 Compresssion Train | A | 2018-08-09 | IFA | OL1-2G05-2201 | PE | 2018-08-15 | 036909C-JVD-TRN-00022 | 036909C-JVD-TRN-00022, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-27 | 2018-09-05 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00022 |  | 2018-08-15
036909C-1010-DI-0007-1001 | Area Basis of Design - 10 Feed Preparation | A | 2018-08-06 | IFA | OL1-2G05-1001 | PE | 2018-08-08 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | 2018-08-08
036909C-1055-DI-0007-5501 | Area Basis of Design - 55 Flare System | A | 2018-08-09 | IFA | OL1-2G05-5501 | PE | 2018-08-10 | 036909C-JVD-TRN-00016 | 036909C-JVD-TRN-00016, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-23 | 2018-08-29 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00016 |  | 2018-08-10
036909C-1027-DI-0007-2701 | Area Basis of Design - 270 Gasoline Hydrogenation -GHU-1 | A | 2018-11-09 | IFA | OL1-2G05-2701 | PE | 2018-11-12 | 036909C-JVD-TRN-00307 | 036909C-JVD-TRN-00307, ROC-TPSK-CECO-T-00001 | IFA | 2018-11-26 | 2019-02-04 | A1-Approved without comments | TPSK-LSPA1-T-PE-00307
036909C-101A-DW-0051-0001 | Detail Plot Plan Zone 1A Furnaces | A | 2019-03-06 | IFR | OL1-2P06-0006 | MP | 2019-03-08 | 036909C-JVD-TRN-01003 | 036909C-JVD-TRN-01003, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-MP-01003 |  | 2019-03-08
036909C-1056-PDS-0840-5612 | Process Equipment Datasheet - 10-F-5610 - Hydroblast Filter | A | 2018-12-06 | IFR | OL1-2G30-5612 | PE | 2018-12-10 | 036909C-JVD-TRN-00454 | 036909C-JVD-TRN-00454 | IFR | 2018-12-21 | 2019-03-11 | R1-No comments | TPSK-LSPA1-T-PE-00454
036909C-1056-SP-0910-5625 | Mechanical Equipment Datasheet - East Gate House Septic Tank Pumps | A | 2019-02-08 | IFQ | OL1-2M03-5625 | ME | 2019-02-13 | 036909C-JVD-TRN-00847 | 036909C-JVD-TRN-00847 | IFR | 2019-02-27 | 2019-03-11 | R2-Comments as noted | TPSK-LSPA1-T-ME -00847
036909C-1056-SP-0910-5624 | Mechanical Equipment Datasheet - West Gate House Septic Tank Pumps | A | 2019-02-08 | IFQ | OL1-2M03-5624 | ME | 2019-02-13 | 036909C-JVD-TRN-00847 | 036909C-JVD-TRN-00847 | IFR | 2019-02-27 | 2019-03-11 | R2-Comments as noted | TPSK-LSPA1-T-ME -00847
036909C-1056-SP-0910-5623 | Mechanical Equipment Datasheet - Gate House Septic Tank Pumps | A | 2019-02-08 | IFQ | OL1-2M03-5623 | ME | 2019-02-13 | 036909C-JVD-TRN-00847 | 036909C-JVD-TRN-00847 | IFR | 2019-02-27 | 2019-03-11 | R2-Comments as noted | TPSK-LSPA1-T-ME -00847
036909C-1000-MR-1800-0001 | Material Requisition For Steel Structures | A | 2019-03-04 | IFQ | OL1-2C12-000001 | PL | 2019-03-11 | 036909C-JVD-TRN-01010 | 036909C-JVD-TRN-01010 | IFR | 2019-03-08 |  | Transmitted | TPSK-LSPA1-T-PL-1010 |  | 2019-03-11
036909C-1056-PDS-0840-5612 | Process Equipment Datasheet - 10-F-5610 - Hydroblast Filter | B | 2019-03-07 | IFD | OL1-2G30-5612 | PE | 2019-03-08 | 036909C-JVD-TRN-01009 | 036909C-JVD-TRN-01009 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-PE-01009 |  | 2019-03-08
036909C-102D-DW-1743-0029 | Foundation For 10-E-2576 | A | 2019-03-06 | IFR | OL1-2K34-0122 | CV | 2019-03-08 | 036909C-JVD-TRN-01004 | 036909C-JVD-TRN-01004 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01004 |  | 2019-03-08
036909C-102D-CN-1733-0026 | Calculation Note For Foundation Of 10-E-2576 | A | 2019-03-06 | IFR | OL1-2K13-0115 | CV | 2019-03-08 | 036909C-JVD-TRN-01005 | 036909C-JVD-TRN-01005 | IFA | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01005 |  | 2019-03-08
036909C-102D-DW-1743-0032 | Foundation for 10-E-2515 | A | 2019-02-27 | IFR | OL1-2K34-0125 | CV | 2019-03-08 | 036909C-JVD-TRN-01004 | 036909C-JVD-TRN-01004 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01004 |  | 2019-03-08
036909C-102B-DW-1743-0031 | Foundation For 10-E-2636 | A | 2019-02-22 | IFR | OL1-2K34-0161 | CV | 2019-03-08 | 036909C-JVD-TRN-01004 | 036909C-JVD-TRN-01004 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01004 |  | 2019-03-08
036909C-102B-CN-1733-0014 | Calculation Note for Foundation of 10-E-2630 | A | 2019-02-22 | IFR | OL1-2K13-0072 | CV | 2019-03-08 | 036909C-JVD-TRN-01005 | 036909C-JVD-TRN-01005 | IFA | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01005 |  | 2019-03-08
036909C-102B-DW-1743-0013 | Foundation For 10-E-2630 | A | 2019-02-22 | IFR | OL1-2K34-0076 | CV | 2019-03-08 | 036909C-JVD-TRN-01004 | 036909C-JVD-TRN-01004 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01004 |  | 2019-03-08
036909C-102B-CN-1733-0028 | Calculation Note For Foundation Of 10-E-2636 | A | 2019-02-22 | IFR | OL1-2K13-0155 | CV | 2019-03-08 | 036909C-JVD-TRN-01005 | 036909C-JVD-TRN-01005 | IFA | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01005 |  | 2019-03-08
036909C-102A-DW-1743-0016 | Foundation For 10-E-2166 | A | 2019-03-06 | IFR | OL1-2K34-0023 | CV | 2019-03-08 | 036909C-JVD-TRN-01004 | 036909C-JVD-TRN-01004 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01004 |  | 2019-03-08
036909C-1028-PDS-0600-2853 | Process Equipment Datasheet - 10-E-2853 - C2R Desuperheater No 2 | A | 2018-09-28 | IFA | OL1-2G30-2853 | PE | 2018-10-01 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | 2018-10-01
036909C-1028-PDS-0600-2852 | Process Equipment Datasheet - 10-E-2852 - C2R Desuperheater No 1 | A | 2018-09-28 | IFA | OL1-2G30-2852 | PE | 2018-10-01 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | 2018-10-01
036909C-102A-CN-1733-0012 | Calculation Note For Foundation Of 10-E-2166 | A | 2019-03-06 | IFR | OL1-2K13-0018 | CV | 2019-03-08 | 036909C-JVD-TRN-01005 | 036909C-JVD-TRN-01005 | IFA | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01005 |  | 2019-03-08
036909C-102A-DW-1743-0013 | Foundation For 10-E-2136 | A | 2019-02-28 | IFR | OL1-2K34-0020 | CV | 2019-03-08 | 036909C-JVD-TRN-01004 | 036909C-JVD-TRN-01004 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01004 |  | 2019-03-08
036909C-1028-PDS-0600-2809 | Process Equipment Datasheet - 10-E-2809 - C3 Chiller No 2 | A | 2018-09-28 | IFA | OL1-2G30-2809 | PE | 2018-10-01 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | 2018-10-01
036909C-1028-PDS-0600-2807 | Process Equipment Datasheet - 10-E-2807 - C3 Chiller No 1 | A | 2018-09-28 | IFA | OL1-2G30-2807 | PE | 2018-10-01 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | 2018-10-01
036909C-1021-PDS-0800-2160 | Process Equipment Datasheet - 10-D-2160 - Dilution Steam Generator | A | 2018-09-28 | IFA | OL1-2G30-2160 | PE | 2018-10-01 | 036909C-JVD-TRN-00115 | 036909C-JVD-TRN-00115 | IFA | 2018-10-12 | 2018-11-05 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00115 |  | 2018-10-01
036909C-1028-PDS-0600-2806 | Process Equipment Datasheet - 10-E-2805 - C3 Refrig Condensers | A | 2018-09-28 | IFA | OL1-2G30-2806 | PE | 2018-10-01 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00113 |  | 2018-10-01
036909C-101B-DW-1743-0002 | Foundation For 10-E-5200 | A | 2019-02-19 | IFR | OL1-2K34-0008 | CV | 2019-03-08 | 036909C-JVD-TRN-01004 | 036909C-JVD-TRN-01004 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01004 |  | 2019-03-08
036909C-1000-NM-0001-1011 | Heat & Material Balance - Cooling Water System | A | 2018-09-28 | IFI | OL1-2G44-1011 | PE | 2018-10-02 | 036909C-JVD-TRN-00116 | 036909C-JVD-TRN-00116 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00116 |  | 2018-10-02
036909C-1000-JSS-1800-0001 | Job Supply Specification for Steel Structures | A | 2019-03-04 | IFI | OL1-2R02-0006 | CV | 2019-03-07 | 036909C-JVD-TRN-00995 | 036909C-JVD-TRN-00995 | IFR | 2019-03-21 |  | Transmitted | TPSK-LSPA1-T-CV-00995 |  | 2019-03-07
036909C-1000-STC-1890-080 | Construction Standards For Ladders And Platforms Attached To Pressure Equipment | A | 2018-08-23 | IFR | OL1-2R03-055 | ME | 2018-08-29 | 036909C-JVD-TRN-00027 | 036909C-JVD-TRN-00027 | IFR | 2018-09-10 | 2018-09-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-00027 |  | 2018-08-29
036909C-1025-PDS-1000-2550 | Process Equipment Data Sheet - 10-C-TX-2550 - Residue Gas Expander - Recompressor | A | 2018-08-29 | IFA | OL1-2G30-2550 | PE | 2018-09-03 | 036909C-JVD-TRN-00031 | 036909C-JVD-TRN-00031 | IFA |  | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00031 |  | 2018-09-03
036909C-1019-PDS-1000-1950 | Process Equipment Data Sheet - 10-PK-1950 - Decoke Air Compressor Package | A | 2018-08-29 | IFA | OL1-2G30-1950 | PE | 2018-09-03 | 036909C-JVD-TRN-00031 | 036909C-JVD-TRN-00031 | IFA |  | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00031 |  | 2018-09-03
036909C-1055-PDS-0800-5552 | Process Equipment Datasheet - 10-D-5552 - LPG Storage Drum | A | 2018-12-05 | IFR | OL1-2G30-5552 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00439
036909C-1055-PDS-0180-5560 | Process Equipment Datasheet - 10-PK-5560 - HP - Polyolefins Flare Pkg | A | 2018-11-29 | IFR | OL1-2G30-5560 | PE | 2018-11-29 | 036909C-JVD-TRN-00398 | 036909C-JVD-TRN-00398 | IFR | 2018-12-13 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00398
036909C-1055-SP-1040-5522 | Mechanical Equipment Datasheet - LP Vent Blower | A | 2019-01-10 | IFQ | OL1-2M03-5522 | ME | 2019-01-11 | 036909C-JVD-TRN-00640 | 036909C-JVD-TRN-00640 | IFR | 2019-01-24 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00640
036909C-102D-CN-1733-0029 | Calculation Note For Foundation Of 10-E-2515 | A | 2019-02-26 | IFR | OL1-2K13-0118 | CV | 2019-03-07 | 036909C-JVD-TRN-00992 | 036909C-JVD-TRN-00992 | IFA | 2019-03-21 |  | Transmitted | TPSK-LSPA1-T-CV-00992 |  | 2019-03-07
036909C-1026-SP-0510-2640 | Mechanical Equipment Data Sheet - C3 Tower | C | 2019-03-01 | IFQ | OL1-2M03-2640 | ME | 2019-03-05 | 036909C-JVD-TRN-00981 | 036909C-JVD-TRN-00981 | IFR | 2019-03-19 |  | Transmitted | TPSK-LSPA1-T-ME-00981 |  | 2019-03-05
036909C-1027-PDS-0900-2751 | Process Equipment Datasheet - 10-P-2750 A-B - C4 - C5 Hydrog Feed Pump | B | 2019-02-28 | IFD | OL1-2G30-2751 | PE | 2019-03-04 | 036909C-JVD-TRN-00963 | 036909C-JVD-TRN-00963 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-PE-00963 |  | 2019-03-04
036909C-1031-PDS-0500-3110 | Process Equipment Datasheet - 10-T-3110 - Water Washer | A | 2019-03-01 | IFR | OL1-2G30-3110 | PE | 2019-03-04 | 036909C-JVD-TRN-00973 | 036909C-JVD-TRN-00973 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-PE-00973 |  | 2019-03-04
036909C-102A-CN-1733-0010 | Calculation Note For Foundation Of 10-E-2136 | A | 2019-02-28 | IFR | OL1-2K13-0016 | CV | 2019-03-07 | 036909C-JVD-TRN-00992 | 036909C-JVD-TRN-00992 | IFA | 2019-03-21 |  | Transmitted | TPSK-LSPA1-T-CV-00992 |  | 2019-03-07
036909C-1055-PDS-0180-5570 | Process Equipment Datasheet - 10-PK-5570 - Enclosed Ground Flare Package | A | 2019-02-28 | IFR | OL1-2G30-5570 | PE | 2019-03-04 | 036909C-JVD-TRN-00959 | 036909C-JVD-TRN-00959 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-PE-00959 |  | 2019-03-04
036909C-1030-PDS-0500-3040 | Process Equipment Datasheet - 10-T-3040 - Rectifier | A | 2019-02-12 | IFR | OL1-2G30-3040 | PE | 2019-03-04 | 036909C-JVD-TRN-00958 | 036909C-JVD-TRN-00958 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-PE-00958 |  | 2019-03-04
036909C-1026-PDS-0600-2666 | Process Equipment Datasheet - 10-E-2666 - Debutanizer Bottoms Cooler | A | 2018-09-27 | IFA | OL1-2G30-2666 | PE | 2018-09-28 | 036909C-JVD-TRN-00112 | 036909C-JVD-TRN-00112 | IFA | 2018-10-12 | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00112 |  | 2018-09-28
036909C-1025-SP-0510-2510 | Mechanical Equipment Data Sheet - Demethanizer Prefractionator & Reflux Drum | C | 2019-02-28 | IFQ | OL1-2M03-2510 | ME | 2019-03-04 | 036909C-JVD-TRN-00970 | 036909C-JVD-TRN-00970 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-ME-00970 |  | 2019-03-04
036909C-1025-TDS-0610-2575 | Mechanical Equipment Data Sheet - 10-E-2575 - Deethanizer Reboiler | B | 2019-03-01 | IFQ | OL1-2M03-2575 | ME | 2019-03-04 | 036909C-JVD-TRN-00961 | 036909C-JVD-TRN-00961 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-ME-00961 |  | 2019-03-04
036909C-1026-PDS-0900-2623 | Process Equipment Data Sheet - 10-P-2620 - C3 Hydrog Recycle Pumps | B | 2019-02-28 | IFD | OL1-2G30-2623 | PE | 2019-03-04 | 036909C-JVD-TRN-00963 | 036909C-JVD-TRN-00963 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-PE-00963 |  | 2019-03-04
036909C-1026-SP-0410-2620 | Mechanical Equipment Data Sheet - C3 Hydrog Reactor | B | 2019-03-04 | IFQ | OL1-2M03-2620 | ME | 2019-03-06 | 036909C-JVD-TRN-00990 | 036909C-JVD-TRN-00990 | IFR | 2019-03-20 |  | Transmitted | TPSK-LSPA1-T-ME-00990 |  | 2019-03-06
036909C-1026-SP-0510-2630 | Mechanical Equipment Data Sheet - Secondary Deethanizer | B | 2019-03-01 | IFQ | OL1-2M03-2630 | ME | 2019-03-04 | 036909C-JVD-TRN-00974 | 036909C-JVD-TRN-00974 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-ME-00974 |  | 2019-03-04
036909C-1025-SP-0510-2580 | Mechanical Equipment Data Sheet - C2 Tower | B | 2019-03-01 | IFQ | OL1-2M03-2580 | ME | 2019-03-05 | 036909C-JVD-TRN-00981 | 036909C-JVD-TRN-00981 | IFR | 2019-03-19 |  | Transmitted | TPSK-LSPA1-T-ME-00981 |  | 2019-03-05
036909C-1020-PDS-0900-2091 | Process Equipment Datasheet - 10-P-2090 A-B - Quench Oil Drain Drum Pumps | B | 2019-02-28 | IFD | OL1-2G30-2091 | PE | 2019-03-04 | 036909C-JVD-TRN-00963 | 036909C-JVD-TRN-00963 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-PE-00963 |  | 2019-03-04
036909C-1019-PDS-0900-1914 | Process Equipment Datasheet - 10-P-1912 - DMDS Presulfiding Injection Pump | B | 2019-02-28 | IFD | OL1-2G30-1914 | PE | 2019-03-04 | 036909C-JVD-TRN-00963 | 036909C-JVD-TRN-00963 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-PE-00963 |  | 2019-03-04
036909C-1010-PDS-0600-1020 | Process Equipment Datasheet - 10-E-1020 - Liquid Feed Heater | D | 2019-03-06 | IFD | OL1-2G30-1020 | PE | 2019-03-07 | 036909C-JVD-TRN-00999 | 036909C-JVD-TRN-00999 | IFR | 2019-03-21 |  | Transmitted | TPSK-LSPA1-T-PE-00999 |  | 2019-03-07
036909C-1010-PDS-0600-1006 | Process Equipment Datasheet - 10-E-1006 - LPG Feed Steam Heater | A | 2019-03-06 | IFR | OL1-2G30-1006 | PE | 2019-03-07 | 036909C-JVD-TRN-00998 | 036909C-JVD-TRN-00998 | IFR | 2019-03-21 |  | Transmitted | TPSK-LSPA1-T-PE-00998 |  | 2019-03-07
036909C-1010-PDS-0600-1005 | Process Equipment Datasheet - 10-E-1005 - LPG Feed Heater | C | 2019-03-06 | IFD | OL1-2G30-1005 | PE | 2019-03-07 | 036909C-JVD-TRN-00999 | 036909C-JVD-TRN-00999 | IFR | 2019-03-21 |  | Transmitted | TPSK-LSPA1-T-PE-00999 |  | 2019-03-07
036909C-1010-PDS-0600-1020 | Process Equipment Datasheet - 10-E-1020 - Liquid Feed Heater | A | 2018-10-18 | IFR | OL1-2G30-1020 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00206
036909C-1010-PDS-0600-1020 | Process Equipment Datasheet - 10-E-1020 - Liquid Feed Heater | B | 2018-12-04 | IFD | OL1-2G30-1020 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-00431
036909C-1010-PDS-0600-1005 | Process Equipment Datasheet - 10-E-1005 - LPG Feed Heater | A | 2018-10-15 | IFR | OL1-2G30-1005 | PE | 2018-10-15 | 036909C-JVD-TRN-00176 | 036909C-JVD-TRN-00176 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00176
036909C-1000-DW-1802-0001 | General Notes For Steel Structures | A | 2018-09-19 | IFR | OL1-2K92-0004 | CV | 2019-09-27 | 036909C-JVD-TRN-00086 | 036909C-JVD-TRN-00086 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00086 |  | 2019-09-27
036909C-1026-SP-0410-2620 | Mechanical Equipment Data Sheet - C3 Hydrog Reactor | A | 2019-01-28 | IFQ | OL1-2M03-2620 | ME | 2019-02-06 | 036909C-JVD-TRN-00802 | 036909C-JVD-TRN-00802 | IFR | 2019-02-19 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00802
036909C-1055-PDS-0800-5565 | Process Equipment Datasheet - 10-D-5565 - Polyolefins Flare Knock-Out Drum | A | 2018-12-20 | IFR | OL1-2G30-5565 | PE | 2018-12-20 | 036909C-JVD-TRN-00558 | 036909C-JVD-TRN-00558 | IFR | 2019-01-03 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00558
036909C-1051-PDS-0800-5140 | Process Equipment Datasheet - 10-D-5140 - Intermittent Blowdown Drum | A | 2018-11-15 | IFR | OL1-2G30-5140 | PE | 2018-11-19 | 036909C-JVD-TRN-00331 | 036909C-JVD-TRN-00331 | IFR | 2018-12-03 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00331
036909C-1029-PDS-2600-2906 | Process Equipment Datasheet - 10-PK-2906 - DSG Anti-Foulant Injection Pkg | B | 2019-01-24 | IFD | OL1-2G30-2906 | PE | 2019-01-25 | 036909C-JVD-TRN-00726 | 036909C-JVD-TRN-00726 | IFI |  | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00726
036909C-1029-PDS-2600-2904 | Process Equipment Datasheet - 10-PK-2904 - Process Water Stripper Chem Inj Pkg | B | 2019-01-24 | IFD | OL1-2G30-2904 | PE | 2019-01-25 | 036909C-JVD-TRN-00726 | 036909C-JVD-TRN-00726 | IFI |  | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00726
036909C-1029-PDS-2600-2902 | Process Equipment Datasheet - 10-PK-2902 - Emulsion Breaker Injection Pkg | B | 2019-01-24 | IFD | OL1-2G30-2902 | PE | 2019-01-25 | 036909C-JVD-TRN-00726 | 036909C-JVD-TRN-00726 | IFI |  | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00726
036909C-1010-PDS-0600-1003 | Process Equipment Datasheet - 10-E-1001 - LPG Steam Vaporizer | B | 2019-01-21 | IFD | OL1-2G30-1003 | PE | 2019-01-23 | 036909C-JVD-TRN-00712 | 036909C-JVD-TRN-00712 | IFI |  | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00712
036909C-1056-PDS-0900-5648 | Process Equipment Datasheet - 10-P-5606 A-B - C3 Hydrog Area Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5648 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774
036909C-1056-PDS-0900-5636 | Process Equipment Datasheet - 10-P-5631 A-B - CWWT Area Oily WWater Sump Pumps | B | 2019-01-29 | IFD | OL1-2G30-5636 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774
036909C-1056-PDS-0900-5635 | Process Equipment Datasheet - 10-P-5630 A-B - CT Area Oily WWater Sump Pumps | B | 2019-01-29 | IFD | OL1-2G30-5635 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774
036909C-1056-PDS-0900-5623 | Process Equipment Datasheet - 10-P-5626 A-B - Gate House Septic Tank Pumps | B | 2019-01-29 | IFD | OL1-2G30-5623 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774
036909C-1056-PDS-0900-5616 | Process Equipment Datasheet - 10-P-5615 A-B - Olefins Stormwater Sump Pumps | B | 2019-01-29 | IFD | OL1-2G30-5616 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774
036909C-1056-PDS-0900-5613 | Process Equipment Datasheet - 10-P-5604 A-B - Refrig Area Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5613 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774
036909C-1056-PDS-0900-5609 | Process Equipment Datasheet - 10-P-5603 A-B - CGC Area Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5609 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774
036909C-1056-PDS-0900-5608 | Process Equipment Datasheet - 10-P-5602 A-B - QW Area Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5608 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774
036909C-1056-PDS-0900-5607 | Process Equipment Datasheet - 10-P-5601 A-B - Butadiene Area Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5607 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774
036909C-1059-PDS-0900-5902 | Process Equipment Datasheet - 10-P-5901 A-B - Sulfuric Acid Metering Pumps | B | 2019-01-29 | IFD | OL1-2G30-5902 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00774
036909C-1056-PDS-0900-5625 | Process Equipment Datasheet - 10-P-5628 A-B - East Gate House Septic Tank Pumps | B | 2019-01-29 | IFD | OL1-2G30-5625 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00774
036909C-1056-PDS-0900-5624 | Process Equipment Datasheet - 10-P-5627 A-B - West Gate House Septic Tank Pumps | B | 2019-01-29 | IFD | OL1-2G30-5624 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00774
036909C-1055-PDS-0900-5551 | Process Equipment Datasheet - 10-P-5550 A-B - HP Flare Knock-Out Pumps | B | 2019-01-29 | IFD | OL1-2G30-5551 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00774
036909C-1054-PDS-0800-5400 | Process Equipment Datasheet - 10-D-5400 - Instrument Air Receiver | A | 2018-12-11 | IFR | OL1-2G30-5400 | PE | 2018-12-13 | 036909C-JVD-TRN-00485 | 036909C-JVD-TRN-00485 | IFR | 2018-12-25 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-PE-00485
036909C-1056-PDS-0200-5600 | Process Equipment Datahseet - 10-PIT-5600 - Pygas Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5600 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1056-PDS-0200-5601 | Process Equipment Datasheet - 10-PIT-5601 - Butadiene Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5601 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1056-PDS-0200-5602 | Process Equipment Datasheet - 10-PIT-5602 - QW Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5602 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1056-PDS-0200-5603 | Process Equipment Datasheet - 10-PIT-5603 - CGC Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5603 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1056-PDS-0200-5604 | Process Equipment Datasheet - 10-PIT-5604 - Refrig Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5604 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1056-PDS-0200-5605 | Process Equipment Datasheet - 10-PIT-5605 - Furnace Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5605 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1056-PDS-0200-5630 | Process Equipment Datasheet - 10-PIT-5630 - CT Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5630 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1056-PDS-0200-5631 | Process Equipment Datasheet - 10-PIT-5631 - CWWT Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5631 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1056-PDS-0200-5632 | Process Equipment Datasheet - 10-PIT-5632 - HP Flare Area Oily WW Sump | A | 2019-01-02 | IFR | OL1-2G30-5632 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1056-PDS-0200-5646 | Process Equipment Datasheet - 10-PIT-5606 - C3 Hydrog Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5646 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1056-PDS-0200-5647 | Process Equipment Datasheet - 10-PIT-5607 - Flare KO Drum Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5647 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1025-SP-0510-2580 | Mechanical Equipment Data Sheet - C2 Tower | A | 2018-12-18 | IFQ | OL1-2M03-2580 | ME | 2018-12-20 | 036909C-JVD-TRN-00531 | 036909C-JVD-TRN-00531 | IFR | 2019-01-02 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00531
036909C-1026-SP-0510-2640 | Mechanical Equipment Data Sheet - C3 Tower | A | 2018-11-30 | IFQ | OL1-2M03-2640 | ME | 2018-12-05 | 036909C-JVD-TRN-00415 | 036909C-JVD-TRN-00415 | IFR | 2018-12-18 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00415
036909C-1024-PDS-0800-2410 | Process Equipment Datasheet - 10-D-2410 A-B - Cracked Gas Dryer | A | 2018-12-06 | IFR | OL1-2G30-2410 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00439
036909C-1056-PDS-0900-5614 | Process Equipment Datasheet - 10-P-5605 A-B - Furnace Area Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5614 | PE | 2019-01-31 | 036909C-JVD-TRN-00779 | 036909C-JVD-TRN-00779 | IFI |  | 2019-03-04 | R1-No comments | TPSK-LSPA1-T-PE-00779
036909C-1059-PDS-0900-5901 | Process Equipment Datasheet - 10-P-5900 A-B - Sulfuric Acid Distribution Pumps | A | 2019-01-24 | IFR | OL1-2G30-5901 | PE | 2019-01-28 | 036909C-JVD-TRN-00738 | 036909C-JVD-TRN-00738 | IFR | 2019-02-11 | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00738
036909C-1056-PDS-2600-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg | C | 2019-02-01 | IFD | OL1-2G30-5670 | PE | 2019-02-01 | 036909C-JVD-TRN-00797 | 036909C-JVD-TRN-00797 | IFI |  | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00797
036909C-1056-PDS-2600-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg | C | 2019-02-01 | IFD | OL1-2G30-5650 | PE | 2019-02-01 | 036909C-JVD-TRN-00797 | 036909C-JVD-TRN-00797 | IFI |  | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00797
036909C-1022-SP-0810-2210 | Mechanical Equipment Data Sheet - CG 1st Stage Suction Drum | A | 2018-01-15 | IFQ | OL1-2M03-2210 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685 | IFR | 2019-02-04 | 2019-02-15 | R1-No comments | TPSK-LSPA1-T-ME-00685
036909C-1055-SP-0810-5550 | Mechanical Equipment Data Sheet - HP Flare Knock-Out Drum | A | 2019-01-07 | IFQ | OL1-2M03-5550 | ME | 2019-01-11 | 036909C-JVD-TRN-00629 | 036909C-JVD-TRN-00629 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00629
036909C-1055-SP-0810-5565 | Mechanical Equipment Data Sheet - Polyolefins Flare Knock-Out Drum | A | 2019-01-21 | IFQ | OL1-2M03-5565 | ME | 2019-01-23 | 036909C-JVD-TRN-00709 | 036909C-JVD-TRN-00709 | IFR | 2019-02-05 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00709
036909C-1054-SP-0810-5400 | Mechanical Equipment Data Sheet - Instrument Air Receiver | A | 2019-01-15 | IFQ | OL1-2M03-5400 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685 | IFR | 2019-02-04 | 2019-02-15 | R1-No comments | TPSK-LSPA1-T-ME-00685
036909C-1028-SP-0810-2880 | Mechanical Equipment Data Sheet - C2R 3RD Stage Suction Drum | B | 2019-01-17 | IFQ | OL1-2M03-2880 | ME | 2019-01-23 | 036909C-JVD-TRN-00708 | 036909C-JVD-TRN-00708 | IFR | 2019-02-05 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00708
036909C-1028-SP-0810-2810 | Mechanical Equipment Data Sheet - C3R 1st Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2810 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00483
036909C-1055-SP-0810-5500 | Mechanical Equipment Data Sheet - Hot Flare Drum | A | 2018-12-07 | IFQ | OL1-2M03-5500 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483
036909C-1028-SP-0810-2840 | Mechanical Equipment Data Sheet - C3R 4TH Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2840 | ME | 2018-12-10 | 036909C-JVD-TRN-00460 | 036909C-JVD-TRN-00460 | IFR | 2018-12-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00460
036909C-1021-SP-0810-2160 | Mechanical Equipment Data Sheet - Dilution Steam Generator | A | 2018-12-05 | IFQ | OL1-2M03-2160 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483
036909C-1010-SP-0810-1000 | Mechanical Equipment Data Sheet - LPG Drum | A | 2018-12-05 | IFQ | OL1-2M03-1000 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483
036909C-1010-PDS-0800-1000 | Process Equipment Datasheet - 10-D-1000 - LPG Drum | B | 2018-12-07 | IFD | OL1-2G30-1000 | PE | 2018-12-10 | 036909C-JVD-TRN-00463 | 036909C-JVD-TRN-00463 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00463
036909C-1022-SP-0810-2230 | Mechanical Equipment Data Sheet - CG 3rd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2230 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483
036909C-1022-SP-0810-2220 | Mechanical Equipment Data Sheet - CG 2nd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2220 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483
036909C-1026-SP-0510-2630 | Mechanical Equipment Data Sheet - Secondary Deethanizer | A | 2018-12-05 | IFQ | OL1-2M03-2630 | ME | 2018-12-10 | 036909C-JVD-TRN-00458 | 036909C-JVD-TRN-00458 | IFR | 2018-12-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00458
036909C-1025-TDS-0610-2515 | Mechanical Equipment Data Sheet - 10-E-2515- Demeth Prefrac Reboiler | A | 2018-12-10 | IFQ | OL1-2M03-2515 | ME | 2019-01-03 | 036909C-JVD-TRN-00573 | 036909C-JVD-TRN-00573 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00573
036909C-1025-SP-0510-2510 | Mechanical Equipment Data Sheet - Demethanizer Prefractionator and Reflux Drum | A | 2018-10-29 | IFQ | OL1-2M03-2510 | ME | 2018-10-31 | 036909C-JVD-TRN-00260 | 036909C-JVD-TRN-00260 | IFR | 2018-11-14 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00260
036909C-1025-SP-0510-2510 | Mechanical Equipment Data Sheet - Demethanizer Prefractionator & Reflux Drum | B | 2018-11-30 | IFQ | OL1-2M03-2510 | ME | 2018-12-05 | 036909C-JVD-TRN-00414 | 036909C-JVD-TRN-00414 | IFI |  | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00414
036909C-1026-PDS-4200-2624 | Process Equipment Datasheet - 10-X-2620 - C3 Hydrog Static Mixer | A | 2019-01-15 | IFR | OL1-2G30-2624 | PE | 2019-01-16 | 036909C-JVD-TRN-00664 | 036909C-JVD-TRN-00664 | IFR | 2019-01-29 | 2019-01-31 | R1-No comments | TPSK-LSPA1-T-PE-00664
036909C-1026-PDS-0600-2621 | Process Equipment Datasheet - 10-E-2620 - C3 Hydrog Aftercooler | A | 2019-01-09 | IFR | OL1-2G30-2621 | PE | 2019-01-10 | 036909C-JVD-TRN-00615 | 036909C-JVD-TRN-00615 | IFR | 2019-01-23 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00615
036909C-1021-PDS-0800-2110 | Process Equipment Datasheet - 10-D-2110 - Interception Drum | A | 2018-12-06 | IFR | OL1-2G30-2110 | PE | 2018-12-10 | 036909C-JVD-TRN-00453 | 036909C-JVD-TRN-00453 | IFR | 2018-12-21 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-00453
036909C-1020-PDS-0800-2090 | Process Equipment Datasheet - 10-D-2090 - Quench Oil Drain Drum | A | 2018-11-26 | IFR | OL1-2G30-2090 | PE | 2018-11-27 | 036909C-JVD-TRN-00368 | 036909C-JVD-TRN-00368 | IFR | 2018-12-11 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00368
036909C-1021-PDS-0800-2190 | Process Equipment Datasheet - 10-D-2190 - Quench Water Drain Drum | A | 2018-11-26 | IFR | OL1-2G30-2190 | PE | 2018-11-27 | 036909C-JVD-TRN-00368 | 036909C-JVD-TRN-00368 | IFR | 2018-12-11 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00368
036909C-1000-JSD-0000-03 | JSD for P&ID Preparation | A | 2018-07-31 | IFA | OL1-2G01-0001 | PE | 2018-07-31 | 036909C-JVD-TRN-00006 | 036909C-JVD-TRN-00006 | IFR | 2018-08-13 | 2018-08-21 | Transmitted | TPSK-LSPA1-T-PE-00006 |  | 2018-07-31
036909C-1027-PDS-0900-2764 | Process Equipment Datasheet - 10-P-2760 A-C - C4-C5 Hydrog Recycle Pump | A | 2019-02-01 | IFR | OL1-2G30-2764 | PE | 2019-02-01 | 036909C-JVD-TRN-00788 | 036909C-JVD-TRN-00788 | IFR | 2019-02-15 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00788
036909C-1027-PDS-0900-2751 | Process Equipment Datasheet - 10-P-2750 A-B - C4-C5 Hydrog Feed Pump | A | 2019-02-01 | IFR | OL1-2G30-2751 | PE | 2019-02-01 | 036909C-JVD-TRN-00788 | 036909C-JVD-TRN-00788 | IFR | 2019-02-15 | 2019-02-15 | R1-No comments | TPSK-LSPA1-T-PE-00788
036909C-1026-PDS-0900-2623 | Process Equipment Data Sheet - 10-P-2620 - C3 Hydrog Recycle Pumps | A | 2019-01-04 | IFR | OL1-2G30-2623 | PE | 2019-01-07 | 036909C-JVD-TRN-00587 | 036909C-JVD-TRN-00587 | IFR | 2019-01-21 | 2019-01-31 | R1-No comments | TPSK-LSPA1-T-PE-00587
036909C-1021-PDS-0900-2126 | Process Equipment Datasheet - 10-P-2126 A-B - Distillate Stripper Bottom Pumps | A | 2018-11-26 | IFR | OL1-2G30-2126 | PE | 2018-11-27 | 036909C-JVD-TRN-00371 | 036909C-JVD-TRN-00371 | IFR | 2018-12-11 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00371
036909C-1020-PDS-0900-2091 | Process Equipment Datasheet - 10-P-2090 A-B - Quench Oil Drain Drum Pumps | A | 2018-11-26 | IFR | OL1-2G30-2091 | PE | 2018-11-27 | 036909C-JVD-TRN-00371 | 036909C-JVD-TRN-00371 | IFR | 2018-12-11 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00371
036909C-1019-PDS-0900-1914 | Process Equipment Datasheet - 10-P-1912 - DMDS Presulfiding Injection Pump | A | 2019-01-17 | IFR | OL1-2G30-1914 | PE | 2019-01-22 | 036909C-JVD-TRN-00687 | 036909C-JVD-TRN-00687 | IFR | 2019-02-04 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE--00687
036909C-1019-PDS-0900-1913 | Process Equipment Datasheet - 10-P-1910 A-B - DMDS Feed Injection Pump | A | 2019-01-17 | IFR | OL1-2G30-1913 | PE | 2019-01-22 | 036909C-JVD-TRN-00687 | 036909C-JVD-TRN-00687 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE--00687
036909C-1056-SP-0910-5649 | Mechanical Equipment Datasheet - Flare KO Drum Oily Wastewater Pump | A | 2019-01-18 | IFQ | OL1-2M03-5649 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716
036909C-1056-SP-0910-5648 | Mechanical Equipment Datasheet - C3 Hydrog Area Oily Wastewater Pump | A | 2019-01-18 | IFQ | OL1-2M03-5648 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716
036909C-1056-SP-0910-5616 | Mechanical Equipment Datasheet - Olefins Stormwater Sump Pumps | A | 2019-01-21 | IFQ | OL1-2M03-5616 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716
036909C-1056-SP-0910-5614 | Mechanical Equipment Datasheet - Furnace Area Oily Wastewater Pump | A | 2019-01-18 | IFQ | OL1-2M03-5614 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716
036909C-1056-SP-0910-5613 | Mechanical Equipment Datasheet - Refrig Area Oily Wastewater Pump | A | 2019-01-18 | IFQ | OL1-2M03-5613 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716
036909C-1056-SP-0910-5609 | Mechanical Equipment Datasheet - CGC Area Oily Wastewater Pump | A | 2019-01-18 | IFQ | OL1-2M03-5609 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716
036909C-1056-SP-0910-5608 | Mechanical Equipment Datasheet - QW Area Oily Wastewater Pump | A | 2019-01-18 | IFQ | OL1-2M03-5608 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716
036909C-1056-SP-0910-5607 | Mechanical Equipment Datasheet - Butadiene Area Oily Wastewater Pump | A | 2019-01-18 | IFQ | OL1-2M03-5607 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716
036909C-1025-TDS-0610-2575 | Mechanical Equipment Data Sheet - 10-E-2575 - Deethanizer Reboiler | A | 2019-01-17 | IFQ | OL1-2M03-2575 | ME | 2019-01-22 | 036909C-JVD-TRN-00684 | 036909C-JVD-TRN-00684 | IFR | 2019-02-04 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00684
036909C-1025-TDS-0610-2548 | Mechanical Equipment Data Sheet - 10-E-2548 - Demethanizer Bottoms Vaporizer | A | 2019-01-07 | IFQ | OL1-2M03-2548 | ME | 2019-01-10 | 036909C-JVD-TRN-00617 | 036909C-JVD-TRN-00617 | IFR | 2019-01-23 | 2019-01-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-00617
036909C-1010-TDS-0610-1051 | Mechanical Equipment Data Sheet - 10-E-1050 - C2 Feed Superheater | A | 2018-12-27 | IFQ | OL1-2M03-1051 | ME | 2019-01-03 | 036909C-JVD-TRN-00573 | 036909C-JVD-TRN-00573 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00573
036909C-1056-PDS-0200-5633 | Process Equipment Datasheet - 10-PIT-5633 - HP Flare Area Stormwater Sump | A | 2019-01-10 | IFR | OL1-2G30-5633 | PE | 2019-01-11 | 036909C-JVD-TRN-00636 | 036909C-JVD-TRN-00636 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00636
036909C-1053-PDS-0300-5355 | Process Equipment Data Sheet - 10-PK-5355 - Side Stream Filter Package | A | 2018-09-24 | IFA | OL1-2G30-5355 | PE | 2018-09-25 | 036909C-JVD-TRN-00082 | 036909C-JVD-TRN-00082 | IFA | 2018-10-09 | 2018-10-13 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00082 |  | 2018-09-25
036909C-1053-PDS-0300-5350 | Process Equipment Data Sheet - 10-PK-5350 - Cooling Tower | A | 2018-09-24 | IFA | OL1-2G30-5350 | PE | 2018-09-25 | 036909C-JVD-TRN-00082 | 036909C-JVD-TRN-00082 | IFA | 2018-10-09 | 2018-10-13 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00082 |  | 2018-09-25
036909C-1029-PDS-0900-2911 | Process Equipment Datasheet - 10-P-2910 - Wash Oil Injection Pump | B | 2019-02-26 | IFD | OL1-2G30-2911 | PE | 2019-02-27 | 036909C-JVD-TRN-00939 | 036909C-JVD-TRN-00939 | IFR | 2019-03-13 |  | Transmitted | TPSK-LSPA1-T-PE-00939 |  | 2019-02-27
036909C-1026-SP-0810-2610 | Mechanical Equipment Datasheet - C3 Hydrog Arsine Guard Bed | C | 2019-02-26 | IFQ | OL1-2M03-2610 | ME | 2019-03-01 | 036909C-JVD-TRN-00950 | 036909C-JVD-TRN-00950 | IFR | 2019-03-15 |  | Transmitted | TPSK-LSPA1-T-ME-00950 |  | 2019-03-01
036909C-1026-SP-0810-2600 | Mechanical Equipment Data Sheet - C3 Hydrog Guard Adsorber | C | 2019-02-26 | IFQ | OL1-2M03-2600 | ME | 2019-03-01 | 036909C-JVD-TRN-00954 | 036909C-JVD-TRN-00954 | IFR | 2019-03-15 |  | Transmitted | TPSK-LSPA1-T-ME-00954 |  | 2019-03-01
036909C-1026-PDS-0600-2665 | Process Equipment Datasheet - 10-E-2665 A-B - Debutanizer Reboilers | A | 2018-09-27 | IFA | OL1-2G30-2665 | PE | 2018-09-28 | 036909C-JVD-TRN-00101 | 036909C-JVD-TRN-00101 | IFA | 2018-10-11 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00101 |  | 2018-09-28
036909C-1026-PDS-0600-2661 | Process Equipment Datasheet - 10-E-2660 - Debutanizer Condenser | A | 2018-09-26 | IFA | OL1-2G30-2661 | PE | 2018-09-27 | 036909C-JVD-TRN-00094 | 036909C-JVD-TRN-00094 | IFA | 2018-10-10 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00094 |  | 2018-09-27
036909C-1025-SP-0510-2540 | Mechanical Equipment Data Sheet - Demethanizer Reflux Drum | C | 2019-02-25 | IFQ | OL1-2M03-2540 | ME | 2019-02-28 | 036909C-JVD-TRN-00945 | 036909C-JVD-TRN-00945 | IFR | 2019-03-14 |  | Transmitted | TPSK-LSPA1-T-ME-00945 |  | 2019-02-28
036909C-1025-PDS-0600-2576 | Process Equipment Datasheet - 10-E-2576 - Deethanizer Bottoms Cooler | A | 2018-09-26 | IFA | OL1-2G30-2576 | PE | 2018-09-27 | 036909C-JVD-TRN-00094 | 036909C-JVD-TRN-00094 | IFA | 2018-10-10 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00094 |  | 2018-09-27
036909C-1025-PDS-0600-2575 | Process Equipment Datasheet - 10-E-2575 - Deethanizer Reboiler | A | 2018-09-26 | IFA | OL1-2G30-2575 | PE | 2018-09-27 | 036909C-JVD-TRN-00094 | 036909C-JVD-TRN-00094 | IFA | 2018-10-10 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00094 |  | 2018-09-27
036909C-1025-PDS-0500-2510 | Process Equipment Datasheet - 10-T-2510 and 10-D-2510 - Demethanizer Prefractionator & Reflux Drum | A | 2018-09-26 | IFA | OL1-2G30-2510 | PE | 2018-09-25 | 036909C-JVD-TRN-00092 | 036909C-JVD-TRN-00092 | IFA | 2018-10-09 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00092 |  | 2018-09-25
036909C-1024-SP-0810-2420 | Mechanical Equipment Data Sheet - CG Liquid Dryer | B | 2019-02-26 | IFQ | OL1-2M03-2420 | ME | 2019-03-01 | 036909C-JVD-TRN-00950 | 036909C-JVD-TRN-00950 | IFR | 2019-03-15 |  | Transmitted | TPSK-LSPA1-T-ME-00950 |  | 2019-03-01
036909C-1024-SP-0410-2470 | Mechanical Equipment Data Sheet - C2 Hydrog Reactor | B | 2019-02-26 | IFQ | OL1-2M03-2470 | ME | 2019-03-01 | 036909C-JVD-TRN-00953 | 036909C-JVD-TRN-00953 | IFR | 2019-03-15 |  | Transmitted | TPSK-LSPA1-T-ME-00953 |  | 2019-03-01
036909C-1024-SP-0810-2480 | Mechanical Equipment Data Sheet - CG Secondary Dryer | B | 2019-02-26 | IFQ | OL1-2M03-2480 | ME | 2019-03-01 | 036909C-JVD-TRN-00954 | 036909C-JVD-TRN-00954 | IFR | 2019-03-15 |  | Transmitted | TPSK-LSPA1-T-ME-00954 |  | 2019-03-01
036909C-1024-SP-0810-2411 | Mechanical Equipment Data Sheet - Cracked Gas Mercury Adsorber | B | 2019-02-26 | IFQ | OL1-2M03-2411 | ME | 2019-03-01 | 036909C-JVD-TRN-00954 | 036909C-JVD-TRN-00954 | IFR | 2019-03-15 |  | Transmitted | TPSK-LSPA1-T-ME-00954 |  | 2019-03-01
036909C-1023-PDS-0800-2309 | Process Equipment Datasheet - 10-D-2305 - Yellow Oil Drum | A | 2018-09-27 | IFA | OL1-2G30-2309 | PE | 2018-09-28 | 036909C-JVD-TRN-00102 | 036909C-JVD-TRN-00102 | IFA | 2018-10-11 | 2018-11-14 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00102 |  | 2018-09-28
036909C-1023-PDS-0800-2392 | Process Equipment Datasheet - 10-D-2392 Spent Caustic Drain Drum | A | 2018-09-27 | IFA | OL1-2G30-2392 | PE | 2018-09-28 | 036909C-JVD-TRN-00102 | 036909C-JVD-TRN-00102 | IFA | 2018-10-11 | 2018-11-14 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00102 |  | 2018-09-28
036909C-1023-PDS-0800-2390 | Process Equipment Datasheet - 10-D-2390 - Caustic Drain Drum | A | 2018-09-27 | IFA | OL1-2G30-2390 | PE | 2018-09-28 | 036909C-JVD-TRN-00102 | 036909C-JVD-TRN-00102 | IFA | 2018-10-11 | 2018-11-14 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00102 |  | 2018-09-28
036909C-101B-CN-1733-0002 | Calculation Note For Foundation Of 10-E-5200 | A | 2019-02-19 | IFR | OL1-2K13-0005 | CV | 2019-02-28 | 036909C-JVD-TRN-00943 | 036909C-JVD-TRN-00943 | IFA | 2019-03-14 |  | Transmitted | TPSK-LSPA1-T-CV-00943 |  | 2019-02-28
036909C-1012-PDS-1040-2011 | See document number 036909C-1012-PDS-1040-1211 or OL1-2G30-1211 | A | 2018-09-25 | IFR | OL1-4G30-2011 | PE | 2018-09-27 | 036909C-JVD-TRN-00090 | 036909C-JVD-TRN-00090 | IFR | 2018-10-10 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00090 |  | 2018-09-27
036909C-1012-NM-0022-1201 | Line Designation Table - Liquid Cracking Furnace 10-H-1200 | A | 2019-02-26 | IBD | OL1-2P91-1201 | PE | 2019-02-27 | 036909C-JVD-TRN-00934 | 036909C-JVD-TRN-00934 | IFR | 2019-03-12 |  | Transmitted | TPSK-LSPA1-T-PE-00934 |  | 2019-02-27
036909C-1011-PDS-1040-1011 | See document number 036909C-1011-PDS-1040-1111 or OL1-2G30-1111 | A | 2018-09-25 | IFR | OL1-4G30-1011 | PE | 2018-09-27 | 036909C-JVD-TRN-00090 | 036909C-JVD-TRN-00090 | IFR | 2018-10-10 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00090 |  | 2018-09-27
036909C-1010-TDS-0610-1003 | Mechanical Equipment Data Sheet - 10-E-1001 - LPG Steam Vaporizer | B | 2019-02-25 | IFQ | OL1-2M03-1003 | ME | 2019-02-28 | 036909C-JVD-TRN-00946 | 036909C-JVD-TRN-00946 | IFR | 2019-03-14 |  | Transmitted | TPSK-LSPA1-T-ME-00946 |  | 2019-02-28
036909C-1000-NM-0050-0001 | Battery Limit Summary | A | 2019-02-27 | IFR | OL1-2G60-0001 | PE | 2019-03-01 | 036909C-JVD-TRN-00948 | 036909C-JVD-TRN-00948 | IFR | 2019-03-15 |  | Transmitted | TPSK-LSPA1-T-PE-00948 |  | 2019-03-01
036909C-1000-DW-1702-0001 | General Notes For Concrete Works | A | 2018-09-19 | IFR | OL1-2K92-0003 | CV | 2019-09-27 | 036909C-JVD-TRN-00086 | 036909C-JVD-TRN-00086 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00086 |  | 2019-09-27
036909C-1000-DW-1402-0001 | General Notes For Underground Works | A | 2018-09-18 | IFR | OL1-2K92-0001 | CV | 2019-09-27 | 036909C-JVD-TRN-00086 | 036909C-JVD-TRN-00086 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00086 |  | 2019-09-27
036909C-102B-CN-1733-0013 | Calculation Note for Foundation of 10-D-2305 | A | 2019-02-05 | IFR | OL1-2K13-0071 | CV | 2019-02-08 | 036909C-JVD-TRN-00827 | 036909C-JVD-TRN-00827 | IFA | 2019-02-25 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00827
036909C-102B-CN-1733-0004 | Calculation Note for Foundation of 10-D-2310 | A | 2019-02-05 | IFR | OL1-2K13-0050 | CV | 2019-02-08 | 036909C-JVD-TRN-00827 | 036909C-JVD-TRN-00827 | IFA | 2019-02-25 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00827
036909C-1000-QCP-1760-0001 | Quality Control Plan Civil Works-Grouting | A | 2019-01-21 | IFR | OL1-2Q20-0018 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729
036909C-1000-QCP-1740-0001 | Quality Control Plan Civil Works-Fire Proofing | A | 2019-01-21 | IFR | OL1-2Q20-0017 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729
036909C-1000-QCP-1717-0001 | Quality Control Plan Civil Works-Concrete Structure for Cooling Tower | A | 2019-01-21 | IFR | OL1-2Q20-0016 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729
036909C-1000-QCP-1714-0001 | Quality Control Plan U-G Civil Works-Installation of Concrete Pits Cable Duct Banks Trenches-Ditches Cable Trenches Direct Buried Box Culverts and Lighting Poles Foundations | A | 2019-01-21 | IFR | OL1-2Q20-0015 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729
036909C-1000-QCP-1713-0001 | Quality Control Plan Civil Works-Rigid Paving | A | 2019-01-21 | IFR | OL1-2Q20-0014 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729
036909C-1000-QCP-1710-0005 | Quality Control Plan Above Ground Civil Works- Concrete Elements Installation | A | 2019-01-21 | IFR | OL1-2Q20-0013 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729
036909C-1000-QCP-1710-0004 | Quality Control Plan Civil Works-Tank Rings Foundations | A | 2019-01-21 | IFR | OL1-2Q20-0012 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729
036909C-1000-QCP-1710-0003 | Quality Control Plan Precast Pipe-Rack Erection | A | 2019-01-21 | IFR | OL1-2Q20-0011 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729
036909C-1000-QCP-1710-0002 | Quality Control Plan Civil Works-Prefabrication of Concrete Elements | A | 2019-01-21 | IFR | OL1-2Q20-0010 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729
036909C-1000-QCP-1710-0001 | Quality Control Plan Civil Works-Reinforced Concrete For Foundation-Elevation Structures And Basins | A | 2019-01-21 | IFR | OL1-2Q20-0009 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729
036909C-1026-SP-0910-2623 | Mechanical Equipment Datasheet - C3 Hydrog Recycle Pumps | A | 2019-01-18 | IFQ | OL1-2M03-2623 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716
036909C-1021-SP-0910-2105 | Mechanical Equipment Datasheet - Quench Oil Reflux Pumps | A | 2018-11-23 | IFQ | OL1-2M03-2105 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457 | IFR | 2018-12-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00457
036909C-1023-SP-0910-2304 | Mechanical Equipment Datasheet - Intermediate Caustic Circulating Pump | B | 2018-12-03 | IFQ | OL1-2M03-2304 | ME | 2018-12-05 | 036909C-JVD-TRN-00411 | 036909C-JVD-TRN-00411 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00411
036909C-1023-SP-0910-2306 | Mechanical Equipment Datasheet - Weak Caustic Circulating Pumps | B | 2018-12-03 | IFQ | OL1-2M03-2306 | ME | 2018-12-05 | 036909C-JVD-TRN-00411 | 036909C-JVD-TRN-00411 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00411
036909C-1025-SP-0910-2586 | Mechanical Equipment Datasheet - Ethane Recycle Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2586 | ME | 2018-12-05 | 036909C-JVD-TRN-00413 | 036909C-JVD-TRN-00413 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00413
036909C-1022-SP-0910-2212 | Mechanical Equipment Datasheet - CG 1st Stage Condensate Pumps | A | 2018-12-04 | IFQ | OL1-2M03-2212 | ME | 2018-12-05 | 036909C-JVD-TRN-00413 | 036909C-JVD-TRN-00413 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00413
036909C-1025-SP-0910-2577 | Mechanical Equipment Datasheet - Deethanizer Reboiler Cond Pumps | A | 2018-12-05 | IFQ | OL1-2M03-2577 | ME | 2018-12-13 | 036909C-JVD-TRN-00494 | 036909C-JVD-TRN-00494 | IFR | 2018-12-26 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00494
036909C-1023-SP-0910-2302 | Mechanical Equipment Datasheet - Strong Caustic Circulating Pumps | A | 2018-11-13 | IFQ | OL1-2M03-2302 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320 | IFR | 2018-11-29 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00320
036909C-1020-SP-0910-2091 | Mechanical Equipment Datasheet - Quench Oil Drain Drum Pumps | A | 2018-12-05 | IFQ | OL1-2M03-2091 | ME | 2018-12-13 | 036909C-JVD-TRN-00494 | 036909C-JVD-TRN-00494 | IFR | 2018-12-26 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00494
036909C-1024-SP-0910-2453 | Mechanical Equipment Datasheet - LP Depropanizer Reflux-Product Pump | A | 2018-11-08 | IFQ | OL1-2M03-2453 | ME | 2018-11-08 | 036909C-JVD-TRN-00294 | 036909C-JVD-TRN-00294 | IFR | 2018-11-22 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00294
036909C-1023-SP-0910-2393 | Mechanical Equipment Datasheet - Spent Caustic Drain Drum Pump | A | 2018-12-05 | IFQ | OL1-2M03-2393 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457 | IFR | 2018-12-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00457
036909C-1025-SP-0910-2573 | Mechanical Equipment Datasheet - Deethanizer Reflux Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2573 | ME | 2018-12-20 | 036909C-JVD-TRN-00552 | 036909C-JVD-TRN-00552 | IFR | 2019-01-03 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-ME-00552
036909C-1023-SP-0910-2311 | Mechanical Equipment Datasheet - Wash Oil Circulating Pumps | A | 2018-11-13 | IFQ | OL1-2M03-2311 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320 | IFR | 2018-11-29 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00320
036909C-1021-SP-0910-2191 | Mechanical Equipment Datasheet - Quench Water Drain Drum Pump | A | 2018-11-28 | IFQ | OL1-2M03-2191 | ME | 2018-11-29 | 036909C-JVD-TRN-00400 | 036909C-JVD-TRN-00400 | IFR | 2018-12-13 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00400
036909C-1023-SP-0910-2321 | Mechanical Equipment Datasheet - Spent Caustic Pumps | A | 2018-11-16 | IFQ | OL1-2M03-2321 | ME | 2018-11-19 | 036909C-JVD-TRN-00335 | 036909C-JVD-TRN-00335 | IFR | 2018-12-03 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-ME-00335
036909C-1022-SP-0910-2222 | Mechanical Equipment Datasheet - CG 2nd Stage Condensed HC Pump | A | 2018-11-16 | IFQ | OL1-2M03-2222 | ME | 2018-11-20 | 036909C-JVD-TRN-00343 | 036909C-JVD-TRN-00343 | IFR | 2018-12-04 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00343
036909C-1021-SP-0910-2126 | Mechanical Equipment Datasheet - Distillate Stripper Bottom Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2126 | ME | 2018-12-05 | 036909C-JVD-TRN-00410 | 036909C-JVD-TRN-00410 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00410
036909C-1027-SP-0910-2791 | Mechanical Equipment Datasheet - Light Oil Drain Drum Pump | A | 2018-12-13 | IFQ | OL1-2M03-2791 | ME | 2018-12-17 | 036909C-JVD-TRN-00515 | 036909C-JVD-TRN-00515 | IFR | 2018-12-31 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00515
036909C-1055-SP-0910-5551 | Mechanical Equipment Datasheet - HP Flare Knock-Out Pumps | A | 2019-01-08 | IFQ | OL1-2M03-5551 | ME | 2019-01-10 | 036909C-JVD-TRN-00616 | 036909C-JVD-TRN-00616 | IFR | 2019-01-23 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-ME-00616
036909C-1051-SP-0910-5141 | Mechanical Equipment Datasheet - Intermittent Blowdown Pumps | A | 2018-11-16 | IFQ | OL1-2M03-5141 | ME | 2018-11-19 | 036909C-JVD-TRN-00335 | 036909C-JVD-TRN-00335 | IFR | 2018-12-03 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-ME-00335
036909C-1026-SP-0910-2633 | Mechanical Equipment Data Sheet - Secondary Deeth Reflux Pumps | B | 2018-12-20 | IFQ | OL1-2M03-2633 | ME | 2018-12-20 | 036909C-JVD-TRN-00554 | 036909C-JVD-TRN-00554 | IFR | 2019-01-03 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-ME-00554
036909C-1055-SP-0910-5566 | Mechanical Equipment Datasheet - Polyolefins Flare Knock-Out Pumps | A | 2019-01-14 | IFQ | OL1-2M03-5566 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716
036909C-1056-SP-0910-5611 | Mechanical Equipment Datasheet - Hydroblast Sump Pump | A | 2019-01-15 | IFQ | OL1-2M03-5611 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716
036909C-1026-SP-0910-2646 | Mechanical Equipment Datasheet - Propane Recycle Pumps | A | 2018-12-18 | IFQ | OL1-2M03-2646 | ME | 2018-12-20 | 036909C-JVD-TRN-00543 | 036909C-JVD-TRN-00543 | IFR | 2019-01-02 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-ME-00543
036909C-1000-SL-0000-04 | Subvendor list for Pumps | 0 | 2018-11-16 | IMP | OL1-2C01-0003 | PL | 2018-11-19 | 036909C-JVD-TRN-00333 | 036909C-JVD-TRN-00333 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00333
036909C-1056-SP-0910-5621 | Mechanical Equipment Datasheet - Olefins Holding Basin Skimmed Oil Pump | A | 2019-01-11 | IFQ | OL1-2M03-5621 | ME | 2019-01-28 | 036909C-JVD-TRN-00742 | 036909C-JVD-TRN-00742 | IFR | 2019-02-11 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME -00742
036909C-1056-SP-0910-5622 | Mechanical Equipment Datasheet - Olefins Holding Basin Pumps | A | 2019-01-14 | IFQ | OL1-2M03-5622 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716
036909C-1000-QCP-1470-0001 | Quality Control Plan U-G Civil Works-Sewers | A | 2019-01-07 | IFR | OL1-2Q20-0007 | QM | 2019-01-11 | 036909C-JVD-TRN-00625 | 036909C-JVD-TRN-00625 | IFA | 2019-01-25 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00625
036909C-1000-QCP-1450-0001 | Quality Control Plan Civil Works-Asphalt Roads And Yards | A | 2019-01-07 | IFR | OL1-2Q20-0006 | QM | 2019-01-11 | 036909C-JVD-TRN-00625 | 036909C-JVD-TRN-00625 | IFA | 2019-01-25 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00625
036909C-1000-QCP-1440-0001 | Quality Control Plan Civil Works-Earth Moving | A | 2019-01-07 | IFR | OL1-2Q20-0005 | QM | 2019-01-11 | 036909C-JVD-TRN-00625 | 036909C-JVD-TRN-00625 | IFA | 2019-01-25 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00625
036909C-1000-QCP-1430-0003 | Quality Control Plan Civil Works-Concrete Precast Driven Piles | A | 2019-01-07 | IFR | OL1-2Q20-0004 | QM | 2019-01-11 | 036909C-JVD-TRN-00625 | 036909C-JVD-TRN-00625 | IFA | 2019-01-25 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00625
036909C-1000-QCP-1430-0002 | Quality Control Plan Civil Works-Continuous Flight Auger Piles | A | 2019-01-07 | IFR | OL1-2Q20-0003 | QM | 2019-01-11 | 036909C-JVD-TRN-00625 | 036909C-JVD-TRN-00625 | IFA | 2019-01-25 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00625
036909C-1000-QCP-1430-0001 | Quality Control Plan Civil Works-Bored Cast In Situ Piles | A | 2019-01-07 | IFR | OL1-2Q20-0002 | QM | 2019-01-11 | 036909C-JVD-TRN-00625 | 036909C-JVD-TRN-00625 | IFA | 2019-01-25 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00625
036909C-102B-CN-1733-0026 | Calculation Note For Foundation Of 10-D-2600A-B | A | 2019-02-07 | IFR | OL1-2K13-0150 | CV | 2019-02-11 | 036909C-JVD-TRN-00832 | 036909C-JVD-TRN-00832 | IFA | 2019-02-26 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00832
036909C-102B-CN-1733-0025 | Calculation Note For Foundation Of 10-D-2610 | A | 2019-02-07 | IFR | OL1-2K13-0149 | CV | 2019-02-11 | 036909C-JVD-TRN-00832 | 036909C-JVD-TRN-00832 | IFA | 2019-02-26 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00832
036909C-102B-CN-1733-0003 | Calculation Note for Foundation of 10-D-2455 | A | 2019-02-07 | IFR | OL1-2K13-0044 | CV | 2019-02-11 | 036909C-JVD-TRN-00832 | 036909C-JVD-TRN-00832 | IFA | 2019-02-26 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00832
036909C-1053-DI-0007-5301 | Area Basis of Design - 53 Cooling Tower System | A | 2018-07-25 | IFA | OL1-2G05-5301 | PE | 2018-07-31 | 036909C-JVD-TRN-00003 | 036909C-JVD-TRN-00003 | IFA | 2018-08-13 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00003 |  | 2018-07-31
036909C-1012-PDS-0811-1207 | Process Equipment Datasheet - 10-D-1200-1600 - 132U Cracking Furnace Steam Drum | A | 2018-10-11 | IFR | OL1-2G30-1207 | PE | 2018-10-11 | 036909C-JVD-TRN-00159 | 036909C-JVD-TRN-00159 | IFR | 2018-10-25 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00159
036909C-1011-PDS-0811-1107 | Process Equipment Datasheet - 10-D-1100 - 36M Cracking Furnace Steam Drum | A | 2018-10-11 | IFR | OL1-2G30-1107 | PE | 2018-10-11 | 036909C-JVD-TRN-00159 | 036909C-JVD-TRN-00159 | IFR | 2018-10-25 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00159
036909C-1012-PDS-1542-1213 | Process Equipment Datasheet - 10-M-1201 - 1601 A-F - USC 132U Dilution Steam Mixing Tee | A | 2018-12-04 | IFR | OL1-2G30-1213 | PE | 2018-12-07 | 036909C-JVD-TRN-00434 | 036909C-JVD-TRN-00434 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00434
036909C-1023-PDS-2500-2324 | Process Equipment Datasheet - 10-TK-2300 - Fresh Caustic Day Tank | A | 2018-12-12 | IFR | OL1-2G30-2324 | PE | 2018-12-13 | 036909C-JVD-TRN-00495 | 036909C-JVD-TRN-00495 | IFR | 2018-12-26 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00495
036909C-1026-PDS-0800-2644 | Process Equipment Datasheet - 10-D-2645 - C3 Tower Reboiler Cond Pot | A | 2019-01-16 | IFR | OL1-2G30-2644 | PE | 2019-01-18 | 036909C-JVD-TRN-00677 | 036909C-JVD-TRN-00677 | IFR | 2019-01-31 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-PE-00677
036909C-1029-PDS-0900-2911 | Process Equipment Datasheet - 10-P-2910 - Wash Oil Injection Pump | A | 2019-01-07 | IFR | OL1-2G30-2911 | PE | 2019-01-10 | 036909C-JVD-TRN-00613 | 036909C-JVD-TRN-00613 | IFR | 2019-01-23 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00613
036909C-1010-TDS-0610-1003 | Mechanical Equipment Data Sheet - 10-E-1001 - LPG Steam Vaporizer | A | 2018-12-27 | IFQ | OL1-2M03-1003 | ME | 2019-01-03 | 036909C-JVD-TRN-00573 | 036909C-JVD-TRN-00573 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00573
036909C-1025-SP-0510-2540 | Mechanical Equipment Data Sheet - Demethanizer and Demethanizer Reflux Drum | B | 2018-11-30 | IFQ | OL1-2M03-2540 | ME | 2018-12-05 | 036909C-JVD-TRN-00415 | 036909C-JVD-TRN-00415 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00415
036909C-1025-SP-0510-2540 | Mechanical Equipment Data Sheet - Demethanizer and Demethanizer Reflux Drum | A | 2018-11-09 | IFQ | OL1-2M03-2540 | ME | 2018-11-09 | 036909C-JVD-TRN-00304 | 036909C-JVD-TRN-00304 | IFR | 2018-11-23 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00304
036909C-1000-STC-0490-000 | Construction Standards For Pressure Equipment | A | 2018-08-10 | IFR | OL1-2R03-0054 | ME | 2018-08-13 | 036909C-JVD-TRN-00018 | 036909C-JVD-TRN-00018 | IFR | 2018-08-24 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00018 |  | 2018-08-13
036909C-1000-JSS-0400-01 | Job Specification for Supply of Pressure Vessels | A | 2018-08-10 | IFR | OL1-2R03-0051 | ME | 2018-08-13 | 036909C-JVD-TRN-00021 | 036909C-JVD-TRN-00021 | IFR | 2018-08-27 | 2018-08-27 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-ME-00021 |  | 2018-08-13
036909C-1000-JSD-0400-01 | Job Specification For Design Of Pressure & Atmospheric Static Equipment | A | 2018-08-09 | IFR | OL1-2R03-0050 | ME | 2018-08-13 | 036909C-JVD-TRN-00017 | 036909C-JVD-TRN-00017 | IFR | 2018-08-24 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00017 |  | 2018-08-13
036909C-1026-SP-0810-2600 | Mechanical Equipment Data Sheet - C3 Hydrog Guard Adsorber | B | 2019-01-21 | IFQ | OL1-2M03-2600 | ME | 2019-01-22 | 036909C-JVD-TRN-00701 | 036909C-JVD-TRN-00701 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME -00701
036909C-1026-SP-0810-2600 | Mechanical Equipment Data Sheet - C3 Hydrog Guard Adsorber | A | 2019-01-16 | IFQ | OL1-2M03-2600 | ME | 2019-01-17 | 036909C-JVD-TRN-00672 | 036909C-JVD-TRN-00672 | IFR | 2019-01-30 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00672
036909C-1024-SP-0810-2480 | Mechanical Equipment Data Sheet - CG Secondary Dryer | A | 2019-01-21 | IFQ | OL1-2M03-2480 | ME | 2019-01-22 | 036909C-JVD-TRN-00702 | 036909C-JVD-TRN-00702 | IFR | 2019-02-04 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00702
036909C-1024-SP-0810-2411 | Mechanical Equipment Data Sheet - Cracked Gas Mercury Adsorber | A | 2019-01-10 | IFQ | OL1-2M03-2411 | ME | 2019-01-11 | 036909C-JVD-TRN-00631 | 036909C-JVD-TRN-00631 | IFR | 2019-01-24 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00631
036909C-1024-SP-0410-2470 | Mechanical Equipment Data Sheet - C2 Hydrog Reactor | A | 2019-01-10 | IFQ | OL1-2M03-2470 | ME | 2019-01-11 | 036909C-JVD-TRN-00630 | 036909C-JVD-TRN-00630 | IFR | 2019-01-24 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00630
036909C-1000-JSS-1300-01 | General Supply Specification For Piping Material | A | 2018-08-22 | IFR | OL1-2R04-0006 | MP | 2018-08-29 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-00028 |  | 2018-08-29
036909C-1026-SP-0810-2610 | Mechanical Equipment Datasheet - C3 Hydrog Arsine Guard Bed | B | 2019-01-14 | IFQ | OL1-2M03-2610 | ME | 2019-01-16 | 036909C-JVD-TRN-00658 | 036909C-JVD-TRN-00658 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00658
036909C-1024-SP-0810-2420 | Mechanical Equipment Data Sheet - CG Liquid Dryer | A | 2019-01-21 | IFQ | OL1-2M03-2420 | ME | 2019-01-22 | 036909C-JVD-TRN-00702 | 036909C-JVD-TRN-00702 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00702
036909C-102D-CN-1733-0042 | Calculation Note For Foundation Of 10-E-2582 | A | 2019-02-07 | IFR | OL1-2K13-0132 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843
036909C-102D-CN-1733-0036 | Calculation Note For Foundation Of 10-E-2856 | A | 2019-02-07 | IFR | OL1-2K13-0127 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843
036909C-102D-CN-1733-0031 | Calculation Note For Foundation Of 10-E-2548 | A | 2019-02-01 | IFR | OL1-2K13-0120 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843
036909C-102D-CN-1733-0030 | Calculation Note For Foundation Of 10-E-2546 | A | 2019-02-08 | IFR | OL1-2K13-0119 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843
036909C-102D-CN-1733-0024 | Calculation Note For Foundation Of 10-E-2858 | A | 2019-02-08 | IFR | OL1-2K13-0126 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843
036909C-102D-CN-1733-0022 | Calculation Note For Foundation Of 10-E-2809 | A | 2019-02-07 | IFR | OL1-2K13-0124 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843
036909C-102D-CN-1733-0021 | Calculation Note For Foundation Of 10-D-2865 | A | 2019-02-05 | IFR | OL1-2K13-0109 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843
036909C-102D-CN-1733-0017 | Calculation Note For Foundation Of 10-D-2575 | A | 2019-02-08 | IFR | OL1-2K13-0105 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843
036909C-102D-CN-1733-0016 | Calculation Note For Foundation Of 10-E-2807 | A | 2019-02-06 | IFR | OL1-2K13-0123 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843
036909C-102B-CN-1733-0002 | Calculation Note For Foundation Of 10-T-2330 | A | 2019-02-07 | IFR | OL1-2K13-0037 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843
036909C-102A-CN-1733-0029 | Calculation Note For Foundation Of 10-E-2008A-B-C-D-E | A | 2019-02-05 | IFR | OL1-2K13-0182 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843
036909C-102A-CN-1733-0015 | Calculation Note For Foundation Of 10-E-2026 | A | 2019-02-07 | IFR | OL1-2K13-0021 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843
036909C-102A-CN-1733-0014 | Calculation Note For Foundation Of 10-E-2146 | A | 2019-02-05 | IFR | OL1-2K13-0020 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843
036909C-102A-CN-1733-0004 | Calculation Note For Foundation Of 10-D-5150 | A | 2019-02-05 | IFR | OL1-2K13-0010 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843
036909C-101B-CN-1733-0001 | Calculation Note For Foundation Of 10-D-5200 | A | 2019-02-05 | IFR | OL1-2K13-0004 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843
036909C-1029-PDS-2600-2900 | Process Equipment Datasheet - 10-PK-2900 - PH Ctrl - Corrosion Inhibitor Inj Pkg | B | 2019-01-31 | IFD | OL1-2G30-2900 | PE | 2019-01-31 | 036909C-JVD-TRN-00780 | 036909C-JVD-TRN-00780 | IFI |  | 2019-02-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-00780
036909C-1021-SP-0510-2120 | Mechanical Equipment Data Sheet - Distillate Stripper | B | 2019-02-11 | IFQ | OL1-2M03-2120 | ME | 2019-02-12 | 036909C-JVD-TRN-00840 | 036909C-JVD-TRN-00840 | IFI |  | 2019-02-28 | R1-No comments | TPSK-LSPA1-T-ME-00840
036909C-1059-SP-2510-5950 | Mechanical Equipment Data Sheet - Sodium Hypochlorite Tank | A | 2019-02-07 | IFQ | OL1-2M03-5950 | ME | 2019-02-11 | 036909C-JVD-TRN-00839 | 036909C-JVD-TRN-00839 | IFR | 2019-02-25 | 2019-02-28 | R1-No comments | TPSK-LSPA1-T-ME-00839
036909C-102D-DW-1743-0016 | Foundation For 10-D-2645 | A | 2019-02-05 | IFR | OL1-2K34-0108 | CV | 2019-02-06 | 036909C-JVD-TRN-00807 | 036909C-JVD-TRN-00807 | IFR | 2019-02-20 |  | Transmitted | TPSK-LSPA1-T-CV-00807
036909C-1053-PDS-0900-5352 | Process Equipment Data Sheet - 10-P-5350 A-H - Olefins Cooling Water Pumps | A | 2018-09-20 | IFA | OL1-2G30-5352 | PE | 2018-09-25 | 036909C-JVD-TRN-00075 | 036909C-JVD-TRN-00075 | IFA | 2018-10-08 |  | Transmitted | TPSK-LSPA1-T-PE-00075 |  | 2018-09-25
036909C-1027-SP-0410-2760 | Mechanical Equipment Data Sheet - C4 -C5 Hydrog Reactor | A | 2019-01-28 | IFQ | OL1-2M03-2760 | ME | 2019-02-01 | 036909C-JVD-TRN-00795 | 036909C-JVD-TRN-00795 | IFR | 2019-02-15 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00795
036909C-1053-PDS-0900-5361 | Process Equipment Data Sheet - 10-P-5360 A-C - CTU Cooling Water Pumps | A | 2018-09-20 | IFA | OL1-2G30-5361 | PE | 2018-09-25 | 036909C-JVD-TRN-00075 | 036909C-JVD-TRN-00075 | IFA | 2018-10-08 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00075 |  | 2018-09-25
036909C-1012-MR-0122-2004 | Material Requisition for Radiant Coil Assemblies | A | 2018-09-12 | IFQ | OL1-2M55-2004 | ME | 2018-10-18 | 036909C-JVD-TRN-00063 | 036909C-JVD-TRN-00063 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00063 |  | 2018-10-18
036909C-1021-PDS-0900-2146 | Process Equipment Datasheet 10-P-2146 DSG Feed Pumps | A | 2018-09-20 | IFA | OL1-2G30-2146 | PE | 2018-09-24 | 036909C-JVD-TRN-00069 | 036909C-JVD-TRN-00069 | IFA | 2018-10-04 | 2018-10-09 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00069 |  | 2018-09-24
036909C-1023-PDS-2500-2320 | Process Equipment Data Sheet - 10-TK-2320 - Spent Caustic Storage Tank | A | 2018-09-20 | IFA | OL1-2G30-2320 | PE | 2018-09-24 | 036909C-JVD-TRN-00068 | 036909C-JVD-TRN-00068 | IFA | 2018-10-04 | 2018-10-09 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00068 |  | 2018-09-24
036909C-1023-PDS-0500-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper | A | 2018-09-20 | IFA | OL1-2G30-2330 | PE | 2018-09-25 | 036909C-JVD-TRN-00073 | 036909C-JVD-TRN-00073 | IFA | 2018-10-08 | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00073 |  | 2018-09-25
036909C-1021-PDS-0900-2106 | Process Equipment Datasheet - 10-P-2106 A-C - Quench Water Pumps | A | 2018-09-20 | IFA | OL1-2G30-2106 | PE | 2018-09-24 | 036909C-JVD-TRN-00070 | 036909C-JVD-TRN-00070 | IFA | 2018-10-04 | 2018-10-09 | A1-Approved without comments | TPSK-LSPA1-T-PE-00070 |  | 2018-09-24
036909C-1020-PDS-0900-2006 | Process Equipment Datasheet - 10-P-2006 A-C - Quench Oil Pumps | A | 2018-09-20 | IFA | OL1-2G30-2006 | PE | 2018-09-24 | 036909C-JVD-TRN-00071 | 036909C-JVD-TRN-00071 | IFA | 2018-10-04 | 2018-10-09 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00071 |  | 2018-09-24
036909C-1026-PDS-0600-2636 | Process Equipment Datasheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | A | 2018-09-20 | IFA | OL1-2G30-2636 | PE | 2018-09-25 | 036909C-JVD-TRN-00074 | 036909C-JVD-TRN-00074 | IFA | 2018-10-08 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00074 |  | 2018-09-25
036909C-1012-SP-0122-2004 | Particular Technical Specification For Radiant Coil Assemblies | A | 2018-09-10 | IFI | OL1-2M57-2004 | ME | 2018-10-18 | 036909C-JVD-TRN-00063 | 036909C-JVD-TRN-00063 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00063 |  | 2018-10-18
036909C-1025-PDS-0500-2540 | Process Equipment Datasheet - 10-T-2540 and 10-D-2540 - Demethanizer and Reflux Drum | A | 2018-09-20 | IFA | OL1-2G30-2540 | PE | 2018-09-25 | 036909C-JVD-TRN-00073 | 036909C-JVD-TRN-00073 | IFA | 2018-10-08 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00073 |  | 2018-09-25
036909C-1026-PDS-0600-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler | A | 2018-09-20 | IFA | OL1-2G30-2635 | PE | 2018-09-25 | 036909C-JVD-TRN-00074 | 036909C-JVD-TRN-00074 | IFA | 2018-10-08 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00074 |  | 2018-09-25
036909C-1026-PDS-0600-2631 | Process Equipment Datasheet - 10-E-2630 - Secondary Deeth Condenser | A | 2018-09-20 | IFA | OL1-2G30-2631 | PE | 2018-09-25 | 036909C-JVD-TRN-00074 | 036909C-JVD-TRN-00074 | IFA | 2018-10-08 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00074 |  | 2018-09-25
036909C-102D-CN-1733-0043 | Calculation Note For Foundation Of 10-E-2504 | A | 2019-01-23 | IFR | OL1-2K13-0133 | CV | 2019-01-31 | 036909C-JVD-TRN-00762 | 036909C-JVD-TRN-00762 | IFA | 2019-02-15 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00762 |  | 2019-01-31
036909C-102D-CN-1733-0032 | Calculation Note for Foundation Of 10-E-2545 | A | 2019-01-24 | IFR | OL1-2K13-0121 | CV | 2019-01-31 | 036909C-JVD-TRN-00762 | 036909C-JVD-TRN-00762 | IFA | 2019-02-15 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00762 |  | 2019-01-31
036909C-1000-JSS-1820-01 | Job Specification For Supply Of Equipment Ladders And Platforms | A | 2018-08-09 | IFR | OL1-2R03-0053 | ME | 2018-08-13 | 036909C-JVD-TRN-00017 | 036909C-JVD-TRN-00017 | IFR | 2018-08-24 | 2018-08-27 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-ME-00017 |  | 2018-08-13
036909C-1000-JSS-0570-01 | Job Specification For Supply Of Column Internals | A | 2018-08-09 | IFR | OL1-2R03-0052 | ME | 2018-08-13 | 036909C-JVD-TRN-00017 | 036909C-JVD-TRN-00017 | IFR | 2018-08-24 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00017 |  | 2018-08-13
036909C-1053-PDS-0900-5352 | Process Equipment Datasheet - 10-P-5350 A-H - Olefins Cooling Water Pumps | B | 2018-10-24 | IFD | OL1-2G30-5352 | PE | 2018-10-24 | 036909C-JVD-TRN-00225 | 036909C-JVD-TRN-00225 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00225
036909C-1053-PDS-0900-5361 | Process Equipment Datasheet - 10-P-5360 A-C - CTU Cooling Water Pumps | C | 2018-10-25 | IFD | OL1-2G30-5361 | PE | 2018-10-26 | 036909C-JVD-TRN-00234 | 036909C-JVD-TRN-00234 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00075
036909C-1023-PDS-0500-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper | B | 2018-10-10 | IFA | OL1-2G30-2330 | PE | 2018-10-11 | 036909C-JVD-TRN-00160 | 036909C-JVD-TRN-00160 | IFA | 2018-10-25 | 2019-02-25 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00160
036909C-1051-PFD-0030-5104 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Furnace Blowdown System | A | 2018-08-23 | IFA | OL1-2G42-5104 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1051-PFD-0030-5103 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate Treatment System | A | 2018-08-23 | IFA | OL1-2G42-5103 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1056-PFD-0030-5612 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Equalization Tank | A | 2018-08-23 | IFA | OL1-2G42-5612 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1056-PFD-0030-5613 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - CPI & IGF Packages | A | 2018-08-23 | IFA | OL1-2G42-5613 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1056-PFD-0030-5604 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Domestic Wastewater Collection | A | 2018-08-23 | IFA | OL1-2G42-5604 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1056-PFD-0030-5611 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - OSBL Oily Wastewater Collection | A | 2018-08-23 | IFA | OL1-2G42-5611 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1056-PFD-0030-5610 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - HP Flare Area SW & Oily WW Collection | A | 2018-08-23 | IFA | OL1-2G42-5610 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1056-PFD-0030-5617 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Slop & Oil Sludge | A | 2018-08-23 | IFA | OL1-2G42-5617 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1059-PFD-0030-5911 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Complex U & O Chemical Storage | A | 2018-08-23 | IFA | OL1-2G42-5911 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1059-PFD-0030-5901 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Chemical Storage | A | 2018-08-23 | IFA | OL1-2G42-5901 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1056-PFD-0030-5614 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Biotreatment Package | A | 2018-08-23 | IFA | OL1-2G42-5614 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1056-PFD-0030-5616 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Sludge Dewatering Package | A | 2018-08-23 | IFA | OL1-2G42-5616 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1056-PFD-0030-5615 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Check Basin | A | 2018-08-23 | IFA | OL1-2G42-5615 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1054-PFD-0030-5401 | Utility Flow Diagram - Olefins Unit 10 - 54 - Air and Nitrogen System - Plant Air Instrument Air And Nitrogen Systems | A | 2018-08-23 | IFA | OL1-2G42-5401 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1055-PFD-0030-5501 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Flare And Blowdown System | A | 2018-08-23 | IFA | OL1-2G42-5501 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1052-PFD-0030-5201 | Utility Flow Diagram - Olefins Unit 10 - 52 - Fuel System - Fuel Gas System | A | 2018-08-23 | IFA | OL1-2G42-5201 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1053-PFD-0030-5311 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Tower | A | 2018-08-23 | IFA | OL1-2G42-5311 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1053-PFD-0030-5301 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Water Diagram | A | 2018-08-23 | IFA | OL1-2G42-5301 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1056-PFD-0030-5601 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Collection | A | 2018-08-23 | IFA | OL1-2G42-5601 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1056-PFD-0030-5603 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Cracker Holding Basin | A | 2018-08-23 | IFA | OL1-2G42-5603 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1056-PFD-0030-5602 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Surface Runoff Collection | A | 2018-08-23 | IFA | OL1-2G42-5602 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1055-PFD-0030-5502 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Process Vent Gas Collection | A | 2018-08-23 | IFA | OL1-2G42-5502 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1055-PFD-0030-5512 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Enclosed Ground Flare | A | 2018-08-23 | IFA | OL1-2G42-5512 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1055-PFD-0030-5511 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - HP - LLDPE LP Flare | A | 2018-08-23 | IFA | OL1-2G42-5511 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1030-PFD-0010-3003 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier | A | 2018-08-23 | IFA | OL1-2G41-3003 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1030-PFD-0010-3005 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation | A | 2018-08-23 | IFA | OL1-2G41-3005 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1030-PFD-0010-3004 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing | A | 2018-08-23 | IFA | OL1-2G41-3004 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1029-PFD-0010-2901 | Process Flow Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | A | 2018-08-23 | IFA | OL1-2G41-2901 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1030-PFD-0010-3002 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Evaporation | A | 2018-08-23 | IFA | OL1-2G41-3002 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1030-PFD-0010-3001 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation | A | 2018-08-23 | IFA | OL1-2G41-3001 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1050-PFD-0030-5001 | Utility Flow Diagram - Olefins Unit 10 - 50 - Water System - Treated Potable And Demin Water Systems | A | 2018-08-23 | IFA | OL1-2G42-5001 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1051-PFD-0030-5102 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate And Boiler Feedwater Systems | A | 2018-08-23 | IFA | OL1-2G42-5102 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1051-PFD-0030-5101 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Steam Balance Diagram | A | 2018-08-23 | IFA | OL1-2G42-5101 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1031-PFD-0010-3101 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration | A | 2018-08-23 | IFA | OL1-2G41-3101 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1039-PFD-0010-3901 | Process Flow Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage | A | 2018-08-23 | IFA | OL1-2G41-3901 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1031-PFD-0010-3102 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam And Condensate System | A | 2018-08-23 | IFA | OL1-2G41-3102 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1026-PFD-0010-2603 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | A | 2018-08-23 | IFA | OL1-2G41-2603 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1026-PFD-0010-2604 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | A | 2018-08-23 | IFA | OL1-2G41-2604 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1026-PFD-0010-2601 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | A | 2018-08-23 | IFA | OL1-2G41-2601 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1026-PFD-0010-2602 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | A | 2018-08-23 | IFA | OL1-2G41-2602 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1028-PDS-0600-2857 | Process Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer | A | 2018-09-11 | IFA | OL1-2G30-2857 | PE | 2018-09-12 | 036909C-JVD-TRN-00041 | 036909C-JVD-TRN-00041 | IFA | 2018-09-26 | 2018-10-01 | A1-Approved without comments | TPSK-LSPA1-T-PE-00041 |  | 2018-09-12
036909C-1026-PDS-0600-2645 | Process Equipment Data Sheet - 10-E-2645 - C3 Tower Reboilers | A | 2018-09-11 | IFA | OL1-2G30-2645 | PE | 2018-09-12 | 036909C-JVD-TRN-00041 | 036909C-JVD-TRN-00041 | IFA | 2018-09-26 | 2018-10-01 | A1-Approved without comments | TPSK-LSPA1-T-PE-00041 |  | 2018-09-12
036909C-1028-PDS-0600-2856 | Process Equipment Data Sheet - 10-E-2855 - C2R Condenser | A | 2018-09-10 | IFA | OL1-2G30-2856 | PE | 2018-09-12 | 036909C-JVD-TRN-00039 | 036909C-JVD-TRN-00039 | IFA | 2018-09-25 | 2018-09-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00039 |  | 2018-09-12
036909C-1027-PFD-0010-2701 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Reactor & Depentanizer | A | 2018-08-23 | IFA | OL1-2G41-2701 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1026-PDS-0500-2630 | Process Equipment Data Sheet - 10-T-2630 - Secondary Deethanizer | A | 2018-09-13 | IFA | OL1-2G30-2630 | PE | 2018-09-17 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | 2018-09-17
036909C-1028-PDS-1000-2850 | Process Equipment Data Sheet - 10-C-2850 - Ethylene Refrig Compressor | B | 2018-09-14 | IFD | OL1-2G30-2850 | PE | 2018-09-18 | 036909C-JVD-TRN-00055 | 036909C-JVD-TRN-00055 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00055 |  | 2018-09-18
036909C-1028-PFD-0010-2802 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | A | 2018-08-23 | IFA | OL1-2G41-2802 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1028-PFD-0010-2803 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | A | 2018-08-23 | IFA | OL1-2G41-2803 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1028-PDS-1000-2800 | Process Equipment Data Sheet - 10-C-2800 - Propylene Refrig Compressor | B | 2018-09-14 | IFD | OL1-2G30-2800 | PE | 2018-09-18 | 036909C-JVD-TRN-00055 | 036909C-JVD-TRN-00055 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00055 |  | 2018-09-18
036909C-1028-PFD-0010-2804 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | A | 2018-08-23 | IFA | OL1-2G41-2804 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1027-PFD-0010-2703 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - Hydrog Reactivation Gas System | A | 2018-08-23 | IFA | OL1-2G41-2703 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1027-PFD-0010-2702 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Rerun Tower | A | 2018-08-23 | IFA | OL1-2G41-2702 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1028-PFD-0010-2801 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | A | 2018-08-23 | IFA | OL1-2G41-2801 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1026-PDS-0500-2660 | Process Equipment Data Sheet - 10-T-2660 - Debutanizer | A | 2018-09-13 | IFA | OL1-2G30-2660 | PE | 2018-09-17 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | 2018-09-17
036909C-1027-PFD-0010-2704 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation | A | 2018-08-23 | IFA | OL1-2G41-2704 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1025-PFD-0010-2502 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | A | 2018-08-23 | IFA | OL1-2G41-2502 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1025-PFD-0010-2503 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | A | 2018-08-23 | IFA | OL1-2G41-2503 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1025-PDS-0600-2571 | Process Equipment Data Sheet - 10-E-2570 Deethanizer Condenser | A | 2018-09-07 | IFA | OL1-2G30-2571 | PE | 2018-09-11 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11
036909C-1025-PDS-0600-2502 | Process Equipment Data Sheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | A | 2018-09-07 | IFA | OL1-2G30-2502 | PE | 2018-09-11 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11
036909C-1025-PDS-0600-2503 | Process Equipment Data Sheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | A | 2018-09-07 | IFA | OL1-2G30-2503 | PE | 2018-09-11 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11
036909C-1025-PFD-0010-2501 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | A | 2018-08-23 | IFA | OL1-2G41-2501 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1025-PFD-0010-2506 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | A | 2018-08-23 | IFA | OL1-2G41-2506 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1025-PFD-0010-2504 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | A | 2018-08-23 | IFA | OL1-2G41-2504 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1025-PFD-0010-2505 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | A | 2018-08-23 | IFA | OL1-2G41-2505 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1021-PFD-0010-2103 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | A | 2018-08-23 | IFA | OL1-2G41-2103 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1021-PFD-0010-2101 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | A | 2018-08-23 | IFA | OL1-2G41-2101 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1024-PFD-0010-2402 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | A | 2018-08-23 | IFA | OL1-2G41-2402 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1022-PFD-0010-2201 | Process Flow Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | A | 2018-08-23 | IFA | OL1-2G41-2201 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1024-PFD-0010-2403 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | A | 2018-08-23 | IFA | OL1-2G41-2403 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1024-PDS-0500-2440 | Process Equipment Data Sheet - 10-T-2440 - HP Depropanizer | A | 2018-09-13 | IFA | OL1-2G30-2440 | PE | 2018-09-17 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | 2018-09-17
036909C-1021-PFD-0010-2102 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | A | 2018-08-23 | IFA | OL1-2G41-2102 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1023-PDS-0500-2300 | Process Equipment Data Sheet - 10-T-2300 - Caustic Tower | A | 2018-09-17 | IFA | OL1-2G30-2300 | PE | 2018-09-19 | 036909C-JVD-TRN-00060 | 036909C-JVD-TRN-00060 | IFA | 2018-10-02 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00060 |  | 2018-09-19
036909C-1024-PFD-0010-2404 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | A | 2018-08-23 | IFA | OL1-2G41-2404 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1022-PDS-1000-2200 | Process Equipment Data Sheet - 10-C-2200 - Cracked Gas Compressor | B | 2018-09-14 | IFD | OL1-2G30-2200 | PE | 2018-09-18 | 036909C-JVD-TRN-00055 | 036909C-JVD-TRN-00055 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00055 |  | 2018-09-18
036909C-1024-PFD-0010-2405 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | A | 2018-08-23 | IFA | OL1-2G41-2405 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1023-PFD-0010-2303 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | A | 2018-08-23 | IFA | OL1-2G41-2303 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1023-PFD-0010-2302 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | A | 2018-08-23 | IFA | OL1-2G41-2302 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1023-PFD-0010-2305 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | A | 2018-08-23 | IFA | OL1-2G41-2305 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1023-PFD-0010-2304 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | A | 2018-08-23 | IFA | OL1-2G41-2304 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1024-PDS-0500-2450 | Process Equipment Data Sheet - 10-T-2450 - LP Depropanizer | A | 2018-09-13 | IFA | OL1-2G30-2450 | PE | 2018-09-17 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | 2018-09-17
036909C-1023-PFD-0010-2301 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | A | 2018-08-23 | IFA | OL1-2G41-2301 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1024-PFD-0010-2401 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | A | 2018-08-23 | IFA | OL1-2G41-2401 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1019-SP-1013-1950 | Mechanical Equipment Datasheet for Decoking Air Compressor Package | A | 2018-09-13 | IFA | OL1-2M03-1950 | ME | 2018-09-14 | 036909C-JVD-TRN-00050 | 036909C-JVD-TRN-00050 | IFA | 2018-09-27 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00050 |  | 2018-09-14
036909C-1012-JSS-0000-9999 | General Supply Rules for Supplier Documentation | A | 2018-09-12 | IFI | OL1-2C93-0001 | PL | 2018-09-19 | 036909C-JVD-TRN-00043 | 036909C-JVD-TRN-00043 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00043 |  | 2018-09-19
036909C-1019-PFD-0010-1902 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | A | 2018-08-23 | IFA | OL1-2G41-1902 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1020-PFD-0010-2002 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | A | 2018-08-23 | IFA | OL1-2G41-2002 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1012-PFD-0010-1201 | Process Flow Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | A | 2018-08-23 | IFA | OL1-2G41-1201 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1020-PFD-0010-2001 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | A | 2018-08-23 | IFA | OL1-2G41-2001 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1019-PFD-0010-1901 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | A | 2018-08-23 | IFA | OL1-2G41-1901 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1012-DW-0122-2202 | USC 132U Cracking Furnace Transfer Lines and Clean-Out Details | A | 2018-09-11 | IFR | OL1-2M06-2202 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00062 |  | 2018-10-08
036909C-1012-DW-0122-2203 | USC 132U Cracking Furnace Radiant Coil Tubeskin Thermocouple Details | A | 2018-09-11 | IFR | OL1-2M06-2203 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00062 |  | 2018-10-08
036909C-1010-PFD-0010-1001 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | A | 2018-08-23 | IFA | OL1-2G41-1001 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1011-DW-0122-1202 | USC 36M Recycle Furnace Transfer Line and Clean-Out Details | A | 2018-09-11 | IFR | OL1-2M06-1202 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00062 |  | 2018-10-08
036909C-1012-DW-0122-2201 | USC 132U Furnace Radiant Coil Assembly and Details | A | 2018-09-11 | IFR | OL1-2M06-2201 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00062 |  | 2018-10-08
036909C-1011-DW-0122-1203 | USC 36M Recycle Furnace Radiant Coil Tubeskin Thermocouple Details | A | 2018-09-11 | IFR | OL1-2M06-1203 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00062 |  | 2018-10-08
036909C-1010-PFD-0010-1003 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | A | 2018-08-23 | IFA | OL1-2G41-1003 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1011-DW-0122-1201 | USC 36M Recycle Furnace Radiant Coil Assembly and Details | A | 2018-09-11 | IFR | OL1-2M06-1201 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-21 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00062 |  | 2018-10-08
036909C-1011-PFD-0010-1101 | Process Flow Diagram - Olefins Unit 10 - 11 - Furnaces - Recycle Gas Cracking Furnace | A | 2018-08-23 | IFA | OL1-2G41-1101 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1000-PFD-0010-0010 | Block Flow Diagram - Olefins Unit 10 - 00-General - Overall Plant Scheme | A | 2018-08-23 | IFA | OL1-2G40-0010 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1000-NM-0003-1006 | Cooling Water Balance | A | 2018-09-14 | IFI | OL1-2G62-1006 | PE | 2018-09-18 | 036909C-JVD-TRN-00054 | 036909C-JVD-TRN-00054 | IFI | 2018-10-08 | 2018-10-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-00054 |  | 2018-09-18
036909C-1000-NM-0003-1008 | Fuel Balance | A | 2018-09-12 | IFI | OL1-2G62-1008 | PE | 2018-09-14 | 036909C-JVD-TRN-00049 | 036909C-JVD-TRN-00049 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00049 |  | 2018-09-14
036909C-1000-PFD-0010-0001 | Process Flow Diagram - Olefins Unit 10 - 00-General - Legend & Symbols | A | 2018-08-23 | IFA | OL1-2G41-0001 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1000-PFD-0010-0002 | Process Flow Diagram - Olefins Unit 10 - 00-General - Drawing Index | A | 2018-08-23 | IFA | OL1-2G41-0002 | PE | 2018-08-24 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24
036909C-1027-SP-0410-2700 | Mechanical Equipment Data Sheet - GHU-1 Reactor | A | 2019-01-28 | IFQ | OL1-2M03-2700 | ME | 2019-02-01 | 036909C-JVD-TRN-00795 | 036909C-JVD-TRN-00795 | IFR | 2019-02-15 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00795
036909C-1026-PDS-0400-2620 | Process Equipment Data Sheet - 10-R-2620 - C3 Hydrog Reactor | A | 2019-01-03 | IFR | OL1-2G30-2620 | PE | 2019-01-03 | 036909C-JVD-TRN-00583 | 036909C-JVD-TRN-00583 | IFR | 2019-01-18 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-00583
036909C-1024-SP-0810-2438 | Mechanical Equipment Data Sheet - HP Depropanizer Reflux Drum | A | 2018-12-04 | IFQ | OL1-2M03-2438 | ME | 2018-12-13 | 036909C-JVD-TRN-00484 | 036909C-JVD-TRN-00484 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00484
036909C-1024-PDS-0800-2438 | Process Equipment Datasheet - 10-D-2440 - HP Depropanizer Reflux Drum | B | 2018-12-04 | IFD | OL1-2G30-2438 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  | 2018-12-18 | R1-No comments | TPSK-LSPA1-T-PE-00430
036909C-1000-STD-1380-0001 | Piping Design Standard Drawings | A | 2018-08-07 | IFR | OL1-2P92-0002 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | 2018-08-08
036909C-1051-MSD-0011-5103 | Material Selection Diagram - Olefins Unit 10 - 51 BFW Steam Cond Systems - Condensate Treatment System | A | 2018-12-20 | IFA | OL1-2G74-5103 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1000-JSD-1600-0009 | Document Template | 0 | 2018-12-03 | IMP | OL1-2R05-0036 | EE | 2018-12-05 | 036909C-JVD-TRN-00424 | 036909C-JVD-TRN-00424 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00424
036909C-1028-PDS-1000-2850 | Process Equipment Data Sheet - 10-C-2850 - Ethylene Refrig Compressor | A | 2018-08-22 | IFA | OL1-2G30-2850 | PE | 2018-08-23 | 036909C-JVD-TRN-00025 | 036909C-JVD-TRN-00025 | IFA | 2018-09-05 | 2018-09-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00025 |  | 2018-08-23
036909C-1028-PDS-1000-2800 | Process Equipment Data Sheet - 10-C-2800 - Propylene Refrig Compressor | A | 2018-08-22 | IFA | OL1-2G30-2800 | PE | 2018-08-23 | 036909C-JVD-TRN-00025 | 036909C-JVD-TRN-00025 | IFA | 2018-09-05 | 2018-09-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00025 |  | 2018-08-23
036909C-1022-PDS-1000-2200 | Process Equipment Data Sheet - 10-C-2200 - Cracked Gas Compressor | A | 2018-08-22 | IFA | OL1-2G30-2200 | PE | 2018-08-23 | 036909C-JVD-TRN-00025 | 036909C-JVD-TRN-00025 | IFA | 2018-09-05 | 2018-09-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00025 |  | 2018-08-23
036909C-1025-PDS-0600-2502 | Process Equipment Datasheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | B | 2018-11-01 | IFD | OL1-2G30-2502 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272
036909C-1026-PDS-0600-2645 | Process Equipment Datasheet - 10-E-2645 A-B - C3 Tower Reboilers | B | 2018-11-01 | IFD | OL1-2G30-2645 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272
036909C-1011-PDS-0191-1106 | Process Equipment Datasheet - 10-H-1100 - USC 36M Burner | B | 2019-01-29 | IFD | OL1-2G30-1106 | PE | 2019-01-29 | 036909C-JVD-TRN-00756 | 036909C-JVD-TRN-00756 | IFI |  | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00756
036909C-1012-PDS-1542-1212 | Process Equipment Datasheet - 10-ZZ-1200 - 1600 USC 132U Attemperator | A | 2019-01-24 | IFR | OL1-2G31-1212 | PE | 2019-01-29 | 036909C-JVD-TRN-00757 | 036909C-JVD-TRN-00757 | IFR | 2019-02-13 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00757
036909C-1011-PDS-1542-1112 | Process Equipment Datasheet - 10-ZZ-1100 - USC 36M Attemperator | A | 2019-01-24 | IFR | OL1-2G31-1112 | PE | 2019-01-29 | 036909C-JVD-TRN-00757 | 036909C-JVD-TRN-00757 | IFR | 2019-02-12 | 2019-02-26 | R1-No comments | TPSK-LSPA1-T-PE-00757
036909C-1028-TDS-0610-2856 | Mechanical Equipment Data Sheet - 10-E-2855 - C2R Condenser | B | 2019-01-30 | IFQ | OL1-2M03-2856 | ME | 2019-01-30 | 036909C-JVD-TRN-00773 | 036909C-JVD-TRN-00773 | IFR | 2019-02-15 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00773
036909C-1026-TDS-0610-2645 | Mechanical Equipment Data Sheet - 10-E-2645 - C3 Tower Reboilers | B | 2019-01-30 | IFQ | OL1-2M03-2645 | ME | 2019-01-30 | 036909C-JVD-TRN-00773 | 036909C-JVD-TRN-00773 | IFR | 2019-02-15 | 2019-02-26 | R1-No comments | TPSK-LSPA1-T-ME-00773
036909C-1027-PDS-0900-2729 | Process Equipment Datasheet - 10-P-2721 A-B - Wash Oil Pumps | A | 2019-02-12 | IFR | OL1-2G30-2729 | PE | 2019-02-15 | 036909C-JVD-TRN-00873 | 036909C-JVD-TRN-00873 | IFR | 2019-03-04 | 2019-02-26 | R1-No comments | TPSK-LSPA1-T-PE-00873 |  | 2019-02-15
036909C-1027-PDS-0900-2726 | Process Equipment Datasheet - 10-P-2726 A-B - Pygas Fuel Oil Pumps | A | 2019-02-12 | IFR | OL1-2G30-2726 | PE | 2019-02-15 | 036909C-JVD-TRN-00873 | 036909C-JVD-TRN-00873 | IFR | 2019-03-04 | 2019-02-26 | R1-No comments | TPSK-LSPA1-T-PE-00873 |  | 2019-02-15
036909C-102B-CN-1733-0008 | Calculation Note for Foundation of 10-D-2330 | A | 2019-01-28 | IFR | OL1-2K13-0054 | CV | 2019-02-01 | 036909C-JVD-TRN-00783 | 036909C-JVD-TRN-00783 | IFA | 2019-02-18 | 2019-02-25 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00783 |  | 2019-02-01
036909C-102B-CN-1733-0006 | Calculation Note for Foundation of 10-D-2316 | A | 2019-01-28 | IFR | OL1-2K13-0052 | CV | 2019-02-01 | 036909C-JVD-TRN-00783 | 036909C-JVD-TRN-00783 | IFA | 2019-02-18 | 2019-02-25 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00783 |  | 2019-02-01
036909C-102D-DW-1743-0039 | Foundation For 10-E-2853 | A | 2019-02-07 | IFR | OL1-2K34-0136 | CV | 2019-02-15 | 036909C-JVD-TRN-00868 | 036909C-JVD-TRN-00868 | IFR | 2019-03-04 |  | Transmitted | TPSK-LSPA1-T-CV-00868 |  | 2019-02-15
036909C-1027-PDS-0800-2767 | Process Equipment Datasheet - 10-D-2765 - C4 - C5 Hydrog Coalescer Drum | A | 2019-02-13 | IFR | OL1-2G30-2767 | PE | 2019-02-20 | 036909C-JVD-TRN-00901 | 036909C-JVD-TRN-00901 | IFR | 2019-03-07 |  | Transmitted | TPSK-LSPA1-T-PE--00901 |  | 2019-02-20
036909C-1027-PDS-4100-2717 | Process Equipment Datasheet - 10-PK-2720 - Rerun Tower Liquid Ring Pump | A | 2019-02-18 | IFR | OL1-2G30-2717 | PE | 2019-02-20 | 036909C-JVD-TRN-00902 | 036909C-JVD-TRN-00902 | IFR | 2019-03-07 |  | Transmitted | TPSK-LSPA1-T-PE-00902 |  | 2019-02-20
036909C-1027-PDS-0600-2702 | Process Equipment Datasheet - 10-E-2702 - GHU-1 Start-up Heater | A | 2019-02-18 | IFR | OL1-2G30-2702 | PE | 2019-02-20 | 036909C-JVD-TRN-00899 | 036909C-JVD-TRN-00899 | IFR | 2019-03-07 |  | Transmitted | TPSK-LSPA1-T-PE-00899 |  | 2019-02-20
036909C-1000-STC-1390-0001 | Piping Construction Drawing | A | 2018-08-07 | IFR | OL1-2P92-0003 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | 2018-08-08
036909C-1000-RT-200 | Firefighting basic design report for package A1 | 0 | 2018-08-10 | IFI | OL1-2W90-0001 | PM | 2018-08-13 | 036909C-JVD-TRN-00020 | 036909C-JVD-TRN-00020 | IFI |  | 2018-08-20 | R2-Comments as noted | TPSK-LSPA1-T-PC-00020 |  | 2018-08-13
036909C-1000-PP-1600-003 | Coordination Procedure For ETAP | A | 2018-08-03 | IFI | OL1-2R05-0045 | EE | 2018-08-07 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 |  | 2018-08-07
036909C-1000-PP-1600-001 | Coordination Procedure For Smartplant Electrical | A | 2018-08-03 | IFR | OL1-2R05-0044 | EE | 2018-08-07 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 |  | 2018-08-07
036909C-1000-NM-0001-1013 | Heat and Material Balance - 56 Waste Water Treatment System | 1 | 2019-02-18 | IFI | OL1-2G44-1013 | PE | 2019-02-19 | 036909C-JVD-TRN-00892 | 036909C-JVD-TRN-00892 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00892 |  | 2019-02-19
036909C-1000-NM-0001-1002 | Heat & Material Balance - Design Case 6 | A | 2018-08-30 | IFI | OL1-2G44-1002 | PE | 2018-09-03 | 036909C-JVD-TRN-00032 | 036909C-JVD-TRN-00032 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00032 |  | 2018-09-03
036909C-1000-NM-0001-1003 | Heat & Material Balance - Design Case 8 | A | 2018-08-30 | IFI | OL1-2G44-1003 | PE | 2018-09-03 | 036909C-JVD-TRN-00032 | 036909C-JVD-TRN-00032 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00032 |  | 2018-09-03
036909C-1000-NM-0001-1004 | Heat & Material Balance - Design Case 9 | A | 2018-08-30 | IFI | OL1-2G44-1004 | PE | 2018-09-03 | 036909C-JVD-TRN-00032 | 036909C-JVD-TRN-00032 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00032 |  | 2018-09-03
036909C-1000-MR-0910-0002 | Material Requisition For API Centrifugal Pumps | A | 2019-02-15 | IFQ | OL1-2C13-442000 | PL | 2019-02-19 | 036909C-JVD-TRN-00880 | 036909C-JVD-TRN-00880 | IFR | 2019-03-05 |  | Transmitted | TPSK-LSPA1-T-PL-00880 |  | 2019-02-19
036909C-1000-NM-0001-1001 | Overall Material Balance | A | 2018-08-03 | IFI | OL1-2G44-1001 | PE | 2018-08-07 | 036909C-JVD-TRN-00009 | 036909C-JVD-TRN-00009 | IFI |  | 2018-08-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-00009 |  | 2018-08-07
036909C-1000-MR-0662-0001 | Material Requisition For Heat Recovery System Requisition For Purchase | 0 | 2019-02-20 | IFP | OL1-2C13-143000 | PL | 2019-02-22 | 036909C-JVD-TRN-00906 | 036909C-JVD-TRN-00906 | IFR | 2019-03-08 |  | Transmitted | TPSK-LSPA1-T-PL-00906 |  | 2019-02-22
036909C-1000-JSS-1320-01 | Job Supply Specification For Pipes | A | 2018-08-22 | IFR | OL1-2R04-0011 | MP | 2018-08-29 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-00028 |  | 2018-08-29
036909C-1000-JSS-1350-01 | Job Supply Specification For Flanges | A | 2018-08-24 | IFR | OL1-2R04-0015 | MP | 2018-08-29 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00028 |  | 2018-08-29
036909C-1000-JSS-1330-01 | Job Supply Specification For Butt Welding Fittings | A | 2018-08-22 | IFR | OL1-2R04-0013 | MP | 2018-08-29 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00028 |  | 2018-08-29
036909C-1000-JSD-2200-01 | Job design specification for thermal insulation (hot service) | A | 2018-08-22 | IFR | OL1-2R04-0003 | MP | 2018-08-23 | 036909C-JVD-TRN-00024 | 036909C-JVD-TRN-00024 | IFR | 2018-09-05 | 2018-09-12 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00024 |  | 2018-08-23
036909C-1000-JSS-1340-01 | Job Supply Specification For Forged Fittings | A | 2018-08-22 | IFR | OL1-2R04-0014 | MP | 2018-08-29 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00028 |  | 2018-08-29
036909C-1000-JSD-2300-01 | Job Design Specification For Painting | A | 2018-08-22 | IFR | OL1-2R04-0005 | MP | 2018-08-23 | 036909C-JVD-TRN-00024 | 036909C-JVD-TRN-00024 | IFR | 2018-09-05 | 2018-09-12 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00024 |  | 2018-08-23
036909C-1000-JSD-2200-02 | Job Design Specification For Thermal Insulation (Cold Service) | A | 2018-08-22 | IFR | OL1-2R04-0004 | MP | 2018-08-23 | 036909C-JVD-TRN-00024 | 036909C-JVD-TRN-00024 | IFR | 2018-09-05 | 2018-09-12 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00024 |  | 2018-08-23
036909C-1000-JSD-1600-008 | General Design Rule For Smartplant Electrical | A | 2018-08-03 | IFR | OL1-2R05-0043 | EE | 2018-08-07 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 |  | 2018-08-07
036909C-1000-JSD-1300-0003 | Job Design Specification For Steam Tracing | A | 2018-08-07 | IFR | OL1-2R04-0031 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | 2018-08-08
036909C-1000-JSD-1300-0002 | Piping Design Specification | A | 2018-08-07 | IFR | OL1-2R04-0002 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | 2018-08-08
036909C-1000-DI-0007-0006 | Furnace Process Basis of Design | A | 2018-07-26 | IFA | OL1-2G02-0006 | PE | 2018-07-31 | 036909C-JVD-TRN-00004 | 036909C-JVD-TRN-00004 | IFA | 2018-08-13 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00004 |  | 2018-07-31
036909C-1055-PDS-0800-5520 | Process Equipment Datasheet - 10-D-5520 - Vent Collection Drum | A | 2018-11-16 | IFR | OL1-2G30-5520 | PE | 2018-11-26 | 036909C-JVD-TRN-00365 | 036909C-JVD-TRN-00365 | IFR | 2018-12-10 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00365
036909C-1023-SP-0510-2330 | Mechanical Equipment Data Sheet - Spent Caustic Stripper | A | 2018-12-06 | IFQ | OL1-2M03-2330 | ME | 2018-12-10 | 036909C-JVD-TRN-00462 | 036909C-JVD-TRN-00462 | IFR | 2018-12-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00462
036909C-1024-SP-0810-2460 | Mechanical Equipment Data Sheet - C2 Hydrog Arsine Guard Bed | A | 2019-01-08 | IFQ | OL1-2M03-2460 | ME | 2019-01-16 | 036909C-JVD-TRN-00657 | 036909C-JVD-TRN-00657 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00657
036909C-1025-TDS-0610-2582 | Mechanical Equipment Data Sheet - 10-E-2582 - C2 Tower Reflux Cooler | A | 2019-01-14 | IFQ | OL1-2M03-2582 | ME | 2019-01-16 | 036909C-JVD-TRN-00661 | 036909C-JVD-TRN-00661 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00661
036909C-1026-SP-0510-2660 | Mechanical Equipment Datasheet - Debutanizer | B | 2018-11-07 | IFQ | OL1-2M03-2660 | ME | 2018-11-08 | 036909C-JVD-TRN-00288 | 036909C-JVD-TRN-00288 | IFR | 2018-11-22 | 2018-11-17 | R2-Comments as noted | TPSK-LSPA1-T-ME-00288
036909C-1026-SP-0510-2660 | Mechanical Equipment Datasheet for Debutanizer | A | 2018-10-23 | IFQ | OL1-2M03-2660 | ME | 2018-10-23 | 036909C-JVD-TRN-00215 | 036909C-JVD-TRN-00215 | IFR | 2018-11-06 |  | Transmitted | TPSK-LSPA1-T-ME-00215
036909C-1026-SP-0510-2660 | Mechanical Equipment Datasheet - Debutanizer | C | 2018-11-30 | IFQ | OL1-2M03-2660 | ME | 2018-12-05 | 036909C-JVD-TRN-00415 | 036909C-JVD-TRN-00415 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00415
036909C-1053-PDS-2600-5397 | Process Equipment Datasheet - 10-PK-5397 - Non-oxidizing Biocide Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5397 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00375
036909C-1053-PDS-2600-5394 | Process Equipment Datasheet - 10-PK-5394 - Dispersant Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5394 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00375
036909C-1053-PDS-2600-5390 | Process Equipment Datasheet - 10-PK-5390 - Copper Corrosion Inhibitor Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5390 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00375
036909C-1023-SP-0510-2300 | Mechanical Equipment Data Sheet Caustic Tower 10-T-2300 | A | 2018-10-26 | IFQ | OL1-2M03-2300 | ME | 2018-10-31 | 036909C-JVD-TRN-00246 | 036909C-JVD-TRN-00246 | IFR | 2018-11-13 | 2018-11-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00246
036909C-1024-SP-0510-2450 | Mechanical Equipment Datasheet - LP Depropanizer | B | 2018-11-06 | IFQ | OL1-2M03-2450 | ME | 2018-11-06 | 036909C-JVD-TRN-00283 | 036909C-JVD-TRN-00283 | IFI |  | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-ME-00283
036909C-1024-SP-0510-2450 | Mechanical Equipment Data Sheet - LP Depropanizer | C | 2018-11-30 | IFQ | OL1-2M03-2450 | ME | 2018-12-05 | 036909C-JVD-TRN-00412 | 036909C-JVD-TRN-00412 | IFI |  | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00412
036909C-1024-SP-0510-2450 | Mechanical Equipment Datasheet LP Depropanizer | A | 2018-10-15 | IFQ | OL1-2M03-2450 | ME | 2018-10-16 | 036909C-JVD-TRN-00183 | 036909C-JVD-TRN-00183 | IFR | 2018-10-30 | 2018-11-05 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00183
036909C-1024-SP-0510-2440 | Mechanical Equipment Datasheet for HP Depropanizer | A | 2018-10-23 | IFQ | OL1-2M03-2440 | ME | 2018-10-23 | 036909C-JVD-TRN-00215 | 036909C-JVD-TRN-00215 | IFR | 2018-11-06 | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-ME-00215
036909C-1024-SP-0510-2440 | Mechanical Equipment Datasheet - HP Depropanizer | B | 2018-11-28 | IFQ | OL1-2M03-2440 | ME | 2018-12-05 | 036909C-JVD-TRN-00416 | 036909C-JVD-TRN-00416 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00416
036909C-1053-PDS-2600-5392 | Process Equipment Datasheet - 10-PK-5392 - Mild Steel Corr Inhibitor Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5392 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00375
036909C-1000-NM-0001-1013 | Heat and Material Balance - 56 Waste Water Treatment System | A | 2019-01-02 | IFI | OL1-2G44-1013 | PE | 2019-01-03 | 036909C-JVD-TRN-00581 | 036909C-JVD-TRN-00581 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00581
036909C-1028-PDS-0800-2860 | Process Equipment Datasheet - 10-D-2860 - C2R 1st Stage Suction Drum | B | 2019-02-12 | IFD | OL1-2G30-2860 | PE | 2019-02-12 | 036909C-JVD-TRN-00845 | 036909C-JVD-TRN-00845 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00845
036909C-1027-PDS-0900-2728 | Process Equipment Datasheet - 10-P-2724 A-B - Recycle Wash Oil Pumps | A | 2019-02-11 | IFR | OL1-2G30-2728 | PE | 2019-02-12 | 036909C-JVD-TRN-00841 | 036909C-JVD-TRN-00841 | IFR | 2019-02-26 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00841
036909C-1025-PDS-0600-2505 | Process Equipment Datasheet - 10-E2506 & 10-E-2508 - Demeth Prefrac Feed Cooler No 3 & No 4 | C | 2019-02-04 | IFD | OL1-2G30-2505 | PE | 2019-02-06 | 036909C-JVD-TRN-00811 | 036909C-JVD-TRN-00811 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00811
036909C-1027-PDS-0600-2725 | Process Equipment Datasheet - 10-E-2725 A-B - Rerun Tower Reboiler | A | 2019-02-01 | IFR | OL1-2G30-2725 | PE | 2019-02-11 | 036909C-JVD-TRN-00835 | 036909C-JVD-TRN-00835 | IFR | 2019-02-25 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00835
036909C-1027-PDS-0600-2721 | Process Equipment Datasheet - 10-E-2720 - Rerun Tower Condenser | A | 2019-02-04 | IFR | OL1-2G30-2721 | PE | 2019-02-11 | 036909C-JVD-TRN-00835 | 036909C-JVD-TRN-00835 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00835
036909C-1029-PDS-2600-2931 | Process Equipment Datasheet - 10-PK-2931 - Propanol Injection Pkg | B | 2019-02-12 | IFD | OL1-2G30-2931 | PE | 2019-02-12 | 036909C-JVD-TRN-00846 | 036909C-JVD-TRN-00846 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00846
036909C-1023-PDS-0900-2325 | Process Equipment Datasheet - 10-P-2300 A-B - 10 Percent Caustic Makeup Pump | B | 2019-01-29 | IFD | OL1-2G30-2325 | PE | 2019-01-29 | 036909C-JVD-TRN-00759 | 036909C-JVD-TRN-00759 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00759
036909C-1029-PDS-0900-2934 | Process Equipment Datasheet - 10-P-2930 - Methanol Injection Pump | B | 2019-02-12 | IFD | OL1-2G30-2934 | PE | 2019-02-12 | 036909C-JVD-TRN-00844 | 036909C-JVD-TRN-00844 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00844
036909C-1026-PDS-0900-2633 | Process Equipment Datasheet - 10-P-2630 A-B - Secondary Deeth Reflux Pumps | B | 2019-02-12 | IFD | OL1-2G30-2633 | PE | 2019-02-12 | 036909C-JVD-TRN-00844 | 036909C-JVD-TRN-00844 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00844
036909C-1026-PDS-0900-2646 | Process Equipment Datasheet - 10-P-2646 A-B - Propane Recycle Pumps | B | 2019-02-12 | IFD | OL1-2G30-2646 | PE | 2019-02-12 | 036909C-JVD-TRN-00844 | 036909C-JVD-TRN-00844 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00844
036909C-1027-PDS-0900-2719 | Process Equipment Datasheet - 10-P-2720 A-B - Rerun Tower Reflux - Product Pumps | A | 2019-02-11 | IFR | OL1-2G30-2719 | PE | 2019-02-12 | 036909C-JVD-TRN-00841 | 036909C-JVD-TRN-00841 | IFR | 2019-02-26 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00841
036909C-1021-SP-0510-2100 | Mechanical Equipment Data Sheet - Quench Water Tower | B | 2019-02-04 | IFQ | OL1-2M03-2100 | ME | 2019-02-06 | 036909C-JVD-TRN-00803 | 036909C-JVD-TRN-00803 | IFI |  | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-ME -00803
036909C-1021-SP-0510-2140 | Mechanical Equipment Data Sheet - Process Water Stripper | B | 2019-01-31 | IFQ | OL1-2M03-2140 | ME | 2019-02-06 | 036909C-JVD-TRN-00801 | 036909C-JVD-TRN-00801 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-ME-00801
036909C-1020-SP-0510-2020 | Mechanical Equipment Data Sheet - Light Fuel Oil Stripper Elevation View | B | 2019-01-31 | IFQ | OL1-2M03-2020 | ME | 2019-02-06 | 036909C-JVD-TRN-00801 | 036909C-JVD-TRN-00801 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-ME-00801
036909C-1020-SP-0510-2000 | Mechanical Equipment Data Sheet - Quench Oil Tower | B | 2019-02-04 | IFQ | OL1-2M03-2000 | ME | 2019-02-06 | 036909C-JVD-TRN-00801 | 036909C-JVD-TRN-00801 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-ME-00801
036909C-1000-QCP-1420-0001 | Quality Control Plan Civil Works-Fencing | A | 2018-12-10 | IFR | OL1-2Q20-0001 | QM | 2018-12-13 | 036909C-JVD-TRN-00488 | 036909C-JVD-TRN-00488 | IFA | 2018-12-27 | 2019-02-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00488
036909C-1019-PDS-0800-1912 | Process Equipment Datasheet - 10-D-1912 - DMDS Injection Drum | A | 2019-01-17 | IFR | OL1-2G30-1912 | PE | 2019-01-22 | 036909C-JVD-TRN-00686 | 036909C-JVD-TRN-00686 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00686
036909C-1019-PDS-0800-1911 | Process Equipment Datasheet - 10-D-1910 - DMDS Bulk Storage Drum | A | 2019-01-17 | IFR | OL1-2G30-1911 | PE | 2019-01-22 | 036909C-JVD-TRN-00686 | 036909C-JVD-TRN-00686 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00686
036909C-1055-TDS-0610-5511 | Mechanical Equipment Data Sheet - 10-E-5510 - Cold Flare Blowdown Vaporizer | A | 2019-01-22 | IFQ | OL1-2M03-5511 | ME | 2019-01-29 | 036909C-JVD-TRN-00755 | 036909C-JVD-TRN-00755 | IFR | 2019-02-12 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00755
036909C-1052-TDS-0610-5201 | Mechanical Equipment Data Sheet - 10-E-5200 - MP Ethylene Superheater | A | 2019-01-28 | IFQ | OL1-2M03-5201 | ME | 2019-01-29 | 036909C-JVD-TRN-00755 | 036909C-JVD-TRN-00755 | IFR | 2019-02-12 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00755
036909C-1051-TDS-0610-5113 | Mechanical Equipment Data Sheet - 10-E-5113 - Foul Condensate Cooler | A | 2019-01-25 | IFQ | OL1-2M03-5113 | ME | 2019-01-29 | 036909C-JVD-TRN-00755 | 036909C-JVD-TRN-00755 | IFR | 2019-02-12 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00755
036909C-1051-TDS-0610-5107 | Mechanical Equipment Data Sheet - 10-E-5112 - Suspect Cond Flash Drum Vent Condenser | A | 2019-01-25 | IFQ | OL1-2M03-5107 | ME | 2019-01-29 | 036909C-JVD-TRN-00755 | 036909C-JVD-TRN-00755 | IFR | 2019-02-12 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00755
036909C-1051-TDS-0610-5103 | Mechanical Equipment Data Sheet - 10-E-5100 - Deaerator Vent Condenser | A | 2019-01-24 | IFQ | OL1-2M03-5103 | ME | 2019-01-29 | 036909C-JVD-TRN-00755 | 036909C-JVD-TRN-00755 | IFR | 2019-02-12 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00755
036909C-1051-PDS-0800-5100 | Process Equipment Datasheet - 10-D-5100 - Deaerator | B | 2018-11-14 | IFD | OL1-2G30-5100 | PE | 2018-11-14 | 036909C-JVD-TRN-00318 | 036909C-JVD-TRN-00318 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00318
036909C-1059-SP-2510-5900 | Mechanical Equipment Data Sheet - Sulfuric Acid Tank | A | 2019-01-25 | IFQ | OL1-2M03-5900 | ME | 2019-01-29 | 036909C-JVD-TRN-00754 | 036909C-JVD-TRN-00754 | IFR | 2019-02-12 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00754
036909C-1025-SP-0510-2520 | Mechanical Equipment Data Sheet - Residue Gas Rectifier And Rectifier Reflux Drum | B | 2019-01-30 | IFQ | OL1-2M03-2520 | ME | 2019-02-01 | 036909C-JVD-TRN-00792 | 036909C-JVD-TRN-00792 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00792
036909C-1020-SP-0510-2040 | Mechanical Equipment Data Sheet - Heavy Fuel Oil Stripper | C | 2019-02-06 | IFQ | OL1-2M03-2040 | ME | 2019-02-06 | 036909C-JVD-TRN-00815 | 036909C-JVD-TRN-00815 |  |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00815
036909C-1027-SP-0510-2710 | Mechanical Equipment Data Sheet - Depentanizer | A | 2019-01-30 | IFQ | OL1-2M03-2710 | ME | 2019-02-06 | 036909C-JVD-TRN-00805 | 036909C-JVD-TRN-00805 | IFR | 2019-02-19 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00805
036909C-1019-SP-0810-1912 | Mechanical Equipment Data Sheet - DMDS Injection Drum | A | 2019-01-24 | IFQ | OL1-2M03-1912 | ME | 2019-01-28 | 036909C-JVD-TRN-00744 | 036909C-JVD-TRN-00744 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00744
036909C-1019-SP-0810-1911 | Mechanical Equipment Data Sheet - DMDS Bulk Storage Drum | A | 2019-01-24 | IFQ | OL1-2M03-1911 | ME | 2019-01-28 | 036909C-JVD-TRN-00743 | 036909C-JVD-TRN-00743 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00743
036909C-1027-SP-0510-2720 | Mechanical Equipment Data Sheet - Rerun Tower | A | 2019-01-25 | IFQ | OL1-2M03-2720 | ME | 2019-01-28 | 036909C-JVD-TRN-00741 | 036909C-JVD-TRN-00741 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00741
036909C-1020-PDS-0600-2048 | Process Equipment Datasheet - 10-E-2048 - Heavy Fuel Oil Product Cooler | B | 2019-01-16 | IFD | OL1-2G30-2048 | PE | 2019-01-18 | 036909C-JVD-TRN-00680 | 036909C-JVD-TRN-00680 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00680
036909C-1020-PDS-0600-2026 | Process Equipment Datasheet - 10-E-2026 - FO Product Cooler | B | 2019-01-16 | IFD | OL1-2G30-2026 | PE | 2019-01-18 | 036909C-JVD-TRN-00680 | 036909C-JVD-TRN-00680 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00680
036909C-1051-SP-2510-5120 | Mechanical Equipment Data Sheet - Raw Condensate Tank | A | 2019-01-24 | IFQ | OL1-2M03-5120 | ME | 2019-01-28 | 036909C-JVD-TRN-00746 | 036909C-JVD-TRN-00746 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00746
036909C-1051-SP-2510-5110 | Mechanical Equipment Data Sheet - Condensate Tank | A | 2019-01-24 | IFQ | OL1-2M03-5110 | ME | 2019-01-28 | 036909C-JVD-TRN-00746 | 036909C-JVD-TRN-00746 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00746
036909C-1029-SP-2510-2910 | Mechanical Equipment Data Sheet - Wash Oil Day Tank | A | 2019-01-24 | IFQ | OL1-2M03-2910 | ME | 2019-01-28 | 036909C-JVD-TRN-00745 | 036909C-JVD-TRN-00745 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00745
036909C-1023-SP-2510-2324 | Mechanical Equipment Data Sheet - Fresh Caustic Day Tank | A | 2019-01-24 | IFQ | OL1-2M03-2324 | ME | 2019-01-28 | 036909C-JVD-TRN-00745 | 036909C-JVD-TRN-00745 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00745
036909C-1023-SP-2510-2320 | Mechanical Equipment Data Sheet - Spent Caustic Storage Tank | A | 2019-01-24 | IFQ | OL1-2M03-2320 | ME | 2019-01-28 | 036909C-JVD-TRN-00745 | 036909C-JVD-TRN-00745 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00745
036909C-1021-PDS-0800-2136 | Process Equipment Datasheet - 10-D-2136 - Process Water Feed Coalescer | B | 2019-01-16 | IFD | OL1-2G30-2136 | PE | 2019-01-18 | 036909C-JVD-TRN-00678 | 036909C-JVD-TRN-00678 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00678
036909C-1027-PDS-0800-2712 | Process Equipment Datasheet - 10-D-2710 - Depentanizer Reflux Drum | A | 2019-01-24 | IFR | OL1-2G30-2712 | PE | 2019-02-01 | 036909C-JVD-TRN-00781 | 036909C-JVD-TRN-00781 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00781
036909C-1027-PDS-0800-2706 | Process Equipment Datasheet - 10-D-2706 - GHU-1 Cold Separator | A | 2019-01-28 | IFR | OL1-2G30-2706 | PE | 2019-02-01 | 036909C-JVD-TRN-00781 | 036909C-JVD-TRN-00781 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00781
036909C-1059-SP-0940-5902 | Mechanical Equipment Datasheet - Sulfuric Acid Metering Pumps | A | 2019-01-24 | IFQ | OL1-2M03-5902 | ME | 2019-02-01 | 036909C-JVD-TRN-00787 | 036909C-JVD-TRN-00787 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00787
036909C-1059-SP-0940-5901 | Mechanical Equipment Datasheet - Sulfuric Acid Distribution Pumps | A | 2019-01-30 | IFQ | OL1-2M03-5901 | ME | 2019-02-01 | 036909C-JVD-TRN-00787 | 036909C-JVD-TRN-00787 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00787
036909C-1053-SP-0910-5361 | Mechanical Equipment Data Sheet - CTU Cooling Water Pumps | B | 2018-11-12 | IFQ | OL1-2M03-5361 | ME | 2018-11-14 | 036909C-JVD-TRN-00317 | 036909C-JVD-TRN-00317 | IFR | 2018-11-28 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00317
036909C-1051-SP-0910-5109 | Mechanical Equipment Data Sheet - Condensate Pumps | B | 2018-11-12 | IFQ | OL1-2M03-5109 | ME | 2018-11-14 | 036909C-JVD-TRN-00317 | 036909C-JVD-TRN-00317 | IFR | 2018-11-28 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00317
036909C-1059-SP-0940-5951 | Mechanical Equipment Datasheet - Sodium Hypochlorite Metering Pumps | A | 2019-01-16 | IFQ | OL1-2M03-5951 | ME | 2019-01-28 | 036909C-JVD-TRN-00742 | 036909C-JVD-TRN-00742 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME -00742
036909C-1055-TDS-0610-5513 | Mechanical Equipment Data Sheet - 10-E-5513 - Methanol Vaporizer | A | 2019-01-23 | IFQ | OL1-2M03-5513 | ME | 2019-01-25 | 036909C-JVD-TRN-00723 | 036909C-JVD-TRN-00723 | IFR | 2019-02-07 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00723
036909C-1056-PDS-0200-5610 | Process Equipment Datasheet - 10-PIT-5610 - Hydroblast Sump | A | 2019-01-04 | IFR | OL1-2G30-5610 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1029-SP-0940-2934 | Mechanical Equipment Datasheet - Methanol Injection Pump | A | 2019-01-16 | IFQ | OL1-2M03-2934 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716
036909C-1011-PID-0021-1121 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1121 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1111 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1111 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1108 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1108 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1107 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1107 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1106 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoke Air Header Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1106 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1105 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Dilution Steam Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1105 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1101 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1101 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1250 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas | A | 2018-11-15 | IFR | OL1-2G43-1250 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1231 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Coils | A | 2018-11-15 | IFR | OL1-2G43-1231 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1230 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Boiler Feed Water Supply Export Steam | A | 2018-11-15 | IFR | OL1-2G43-1230 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1229 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Drum-SLE And TLX Risers | A | 2018-11-15 | IFR | OL1-2G43-1229 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1228 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - VHP Steam Drum | A | 2018-11-15 | IFR | OL1-2G43-1228 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1227 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - SLE Drain Header | A | 2018-11-15 | IFR | OL1-2G43-1227 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1226 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Furnace Effluent & Decoke MOV's | A | 2018-11-15 | IFR | OL1-2G43-1226 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1225 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - TLX Exchanger | A | 2018-11-15 | IFR | OL1-2G43-1225 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1221 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1221 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1220 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1220 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1219 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1219 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1218 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1218 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1217 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1217 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1216 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1216 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1215 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Convection Section | A | 2018-11-15 | IFR | OL1-2G43-1215 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1212 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1212 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1211 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1211 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1210 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1210 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1209 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1209 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1208 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1208 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1207 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1207 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1206 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Decoke Air Header Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1206 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1205 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Dilution Steam Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1205 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1202 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Liquid Feed Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1202 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1201 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - C3 LPG Feed Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1201 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1150 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Flue Gas | A | 2018-11-15 | IFR | OL1-2G43-1150 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1145 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoking Effluent | A | 2018-11-15 | IFR | OL1-2G43-1145 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1140 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Burners | A | 2018-11-15 | IFR | OL1-2G43-1140 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1135 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Fuel Gas | A | 2018-11-15 | IFR | OL1-2G43-1135 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1131 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Coils | A | 2018-11-15 | IFR | OL1-2G43-1131 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1130 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Boiler Feed Water Supply Export Steam | A | 2018-11-15 | IFR | OL1-2G43-1130 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1129 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Drum-USX And TLX-1 Risers | A | 2018-11-15 | IFR | OL1-2G43-1129 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1128 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - SHP Steam Drum | A | 2018-11-15 | IFR | OL1-2G43-1128 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1127 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - USX Drain Header | A | 2018-11-15 | IFR | OL1-2G43-1127 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1126 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Furnace Effluent And Decoke MOVs | A | 2018-11-15 | IFR | OL1-2G43-1126 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1125 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - TLX Quench Exchangers | A | 2018-11-15 | IFR | OL1-2G43-1125 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1120 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1120 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1119 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1119 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1118 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1118 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1117 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1117 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1116 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1116 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1115 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Convection Section | A | 2018-11-15 | IFR | OL1-2G43-1115 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1112 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1112 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1110 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed-Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1110 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1011-PID-0021-1109 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1109 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1010-TDS-0610-1020 | Mechanical Equipment Data Sheet - 10-E-1020 - Liquid Feed Heater | A | 2019-01-15 | IFQ | OL1-2M03-1020 | ME | 2019-01-17 | 036909C-JVD-TRN-00671 | 036909C-JVD-TRN-00671 | IFR | 2019-01-30 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00671
036909C-1052-TDS-0610-5210 | Mechanical Equipment Data Sheet - 10-E-5210 - Pilot Gas Vaporizer | A | 2019-01-15 | IFQ | OL1-2M03-5210 | ME | 2019-01-17 | 036909C-JVD-TRN-00673 | 036909C-JVD-TRN-00673 | IFR | 2019-01-30 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00673
036909C-1025-TDS-0610-2546 | Mechanical Equipment Data Sheet - 10-E-2546 - Demethanizer Bottoms Cooler | A | 2019-01-14 | IFQ | OL1-2M03-2546 | ME | 2019-01-16 | 036909C-JVD-TRN-00654 | 036909C-JVD-TRN-00654 | IFR | 2019-01-29 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00654
036909C-1024-TDS-0610-2445 | Mechanical Equipment Data Sheet - 10-E-2445 - HP Depropanizer Reboiler | A | 2019-01-15 | IFQ | OL1-2M03-2445 | ME | 2019-01-17 | 036909C-JVD-TRN-00671 | 036909C-JVD-TRN-00671 | IFR | 2019-01-30 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00671
036909C-1021-TDS-0610-2166 | Mechanical Equipment Data Sheet - 10-E-2166 - DSG Blowdown Cooler | A | 2019-01-18 | IFQ | OL1-2M03-2166 | ME | 2019-01-22 | 036909C-JVD-TRN-00684 | 036909C-JVD-TRN-00684 | IFR | 2019-02-04 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00684
036909C-1055-TDS-0610-5553 | Mechanical Equipment Data Sheet - 10-E-5552 - LPG Vaporizer - Superheater | A | 2019-01-17 | IFQ | OL1-2M03-5553 | ME | 2019-01-22 | 036909C-JVD-TRN-00684 | 036909C-JVD-TRN-00684 | IFR | 2019-02-04 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00684
036909C-1020-TDS-0610-2026 | Mechanical Equipment Data Sheet - 10-E-2026 - FO Product Cooler | A | 2019-01-17 | IFQ | OL1-2M03-2026 | ME | 2019-01-22 | 036909C-JVD-TRN-00683 | 036909C-JVD-TRN-00683 | IFR | 2019-02-04 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00683
036909C-1020-TDS-0610-2048 | Mechanical Equipment Data Sheet - 10-E-2048 - Heavy Fuel Oil Product Cooler | A | 2019-01-17 | IFQ | OL1-2M03-2048 | ME | 2019-01-22 | 036909C-JVD-TRN-00683 | 036909C-JVD-TRN-00683 | IFR | 2019-02-04 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00683
036909C-1021-TDS-0610-2147 | Mechanical Equipment Data Sheet - 10-E-2146 - DSG Feed Heater | A | 2019-01-14 | IFQ | OL1-2M03-2147 | ME | 2019-01-14 | 036909C-JVD-TRN-00650 | 036909C-JVD-TRN-00650 | IFR | 2019-01-28 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00650
036909C-1025-TDS-0610-2576 | Mechanical Equipment Data Sheet - 10-E-2576 - Deethanizer Bottoms Cooler | A | 2019-01-02 | IFQ | OL1-2M03-2576 | ME | 2019-01-03 | 036909C-JVD-TRN-00582 | 036909C-JVD-TRN-00582 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00582
036909C-1026-TDS-0610-2635 | Mechanical Equipment Data Sheet - 10-E-2635 - Secondary Deeth Reboiler | A | 2019-01-02 | IFQ | OL1-2M03-2635 | ME | 2019-01-03 | 036909C-JVD-TRN-00582 | 036909C-JVD-TRN-00582 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00582
036909C-1010-TDS-0610-1005 | Mechanical Equipment Data Sheet - 10-E-1005 - LPG Feed Heater | A | 2018-12-27 | IFQ | OL1-2M03-1005 | ME | 2019-01-03 | 036909C-JVD-TRN-00573 | 036909C-JVD-TRN-00573 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00573
036909C-1021-TDS-0610-2137 | Mechanical Equipment Data Sheet - 10-E-2136 - Process Water Stripper Feed Heater | A | 2018-12-27 | IFQ | OL1-2M03-2137 | ME | 2019-01-03 | 036909C-JVD-TRN-00573 | 036909C-JVD-TRN-00573 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00573
036909C-1021-TDS-0610-2161 | Mechanical Equipment Data Sheet - 10-E-2160 - Dilution Steam Superheater | A | 2019-01-10 | IFQ | OL1-2M03-2161 | ME | 2019-01-11 | 036909C-JVD-TRN-00641 | 036909C-JVD-TRN-00641 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-00641
036909C-1024-TDS-0610-2465 | Mechanical Equipment Data Sheet - 10-E-2465 - C2 Hydrog Feed Heater | A | 2019-01-09 | IFQ | OL1-2M03-2465 | ME | 2019-01-11 | 036909C-JVD-TRN-00641 | 036909C-JVD-TRN-00641 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-00641
036909C-1021-TDS-0610-2125 | Mechanical Equipment Data Sheet - 10-E-2125 - Distillate Stripper Reboiler | A | 2019-01-02 | IFQ | OL1-2M03-2125 | ME | 2019-01-07 | 036909C-JVD-TRN-00584 | 036909C-JVD-TRN-00584 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00584
036909C-1022-TDS-0610-2206 | Mechanical Equipment Data Sheet - 10-E-2206 - Wash Water Cooler | A | 2019-01-03 | IFQ | OL1-2M03-2206 | ME | 2019-01-07 | 036909C-JVD-TRN-00584 | 036909C-JVD-TRN-00584 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00584
036909C-1028-TDS-0610-2807 | Mechanical Equipment Data Sheet - 10-E-2807 - C3 Chiller No 1 | A | 2018-12-12 | IFQ | OL1-2M03-2807 | ME | 2018-12-14 | 036909C-JVD-TRN-00505 | 036909C-JVD-TRN-00505 | IFR | 2018-12-27 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00505
036909C-1028-TDS-0610-2852 | Mechanical Equipment Data Sheet - 10-E-2852 - C2R Desuperheater No 1 | A | 2018-12-13 | IFQ | OL1-2M03-2852 | ME | 2018-12-14 | 036909C-JVD-TRN-00505 | 036909C-JVD-TRN-00505 | IFR | 2018-12-27 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00505
036909C-1028-TDS-0610-2809 | Mechanical Equipment Data Sheet - 10-E-2809 - C3 Chiller No 2 | A | 2018-12-13 | IFQ | OL1-2M03-2809 | ME | 2018-12-14 | 036909C-JVD-TRN-00505 | 036909C-JVD-TRN-00505 | IFR | 2018-12-27 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00505
036909C-1026-TDS-0610-2631 | Mechanical Equipment Data Sheet - 10-E-2630 - Secondary Deeth Condenser | A | 2018-12-06 | IFQ | OL1-2M03-2631 | ME | 2018-12-10 | 036909C-JVD-TRN-00455 | 036909C-JVD-TRN-00455 | IFR | 2018-12-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00455
036909C-1026-TDS-0610-2636 | Mechanical Equipment Data Sheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | A | 2018-12-07 | IFQ | OL1-2M03-2636 | ME | 2018-12-10 | 036909C-JVD-TRN-00465 | 036909C-JVD-TRN-00465 | IFR | 2018-12-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00465
036909C-1026-TDS-0610-2666 | Mechanical Equipment Data Sheet - 10-E-2666 - Debutanizer Bottoms Cooler | A | 2018-12-07 | IFQ | OL1-2M03-2666 | ME | 2018-12-10 | 036909C-JVD-TRN-00468 | 036909C-JVD-TRN-00468 | IFR | 2018-12-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00468
036909C-1026-TDS-0610-2665 | Mechanical Equipment Data Sheet - 10-E-2665 AB - Debutanizer Reboilers | A | 2018-12-07 | IFQ | OL1-2M03-2665 | ME | 2018-12-10 | 036909C-JVD-TRN-00468 | 036909C-JVD-TRN-00468 | IFR | 2018-12-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00468
036909C-1028-TDS-0610-2859 | Mechanical Equipment Data Sheet - 10-E-2856 - Ethylene Product Subcooler | A | 2018-12-18 | IFQ | OL1-2M03-2859 | ME | 2018-12-20 | 036909C-JVD-TRN-00541 | 036909C-JVD-TRN-00541 | IFR | 2019-01-02 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00541
036909C-1028-TDS-0610-2853 | Mechanical Equipment Data Sheet - 10-E-2853 - C2R Desuperheater No 2 | A | 2018-12-18 | IFQ | OL1-2M03-2853 | ME | 2018-12-20 | 036909C-JVD-TRN-00541 | 036909C-JVD-TRN-00541 | IFR | 2019-01-02 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00541
036909C-1012-JSS-0191-2009 | Project Specification for Furnace Burners | 0 | 2019-01-18 | IMP | OL1-2M92-2009 | ME | 2019-01-22 | 036909C-JVD-TRN-00698 | 036909C-JVD-TRN-00698 | IFI |  | 2019-02-14 | R1-No comments | TPSK-LSPA1-T-ME-00698
036909C-1053-MSD-0011-5311 | Material Selection Diagram - Olefins Unit 10 - 53-Cooling Water System Cooling Tower | A | 2018-11-16 | IFA | OL1-2G74-5311 | ME | 2018-11-29 | 036909C-JVD-TRN-00399 | 036909C-JVD-TRN-00399 | IFA | 2018-12-13 | 2019-02-15 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00399
036909C-1053-MSD-0011-5301 | Material Selection Diagram - Olefins Unit 10 - 53 Cooling Water System Cooling Water Diagram | A | 2018-11-16 | IFA | OL1-2G74-5301 | ME | 2018-11-29 | 036909C-JVD-TRN-00399 | 036909C-JVD-TRN-00399 | IFA | 2018-12-13 | 2019-02-15 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00399
036909C-1027-PDS-0500-2720 | Process Equipment Datasheet - 10-T-2720 - Rerun Tower | A | 2019-01-17 | IFR | OL1-2G30-2720 | PE | 2019-01-22 | 036909C-JVD-TRN-00699 | 036909C-JVD-TRN-00699 | IFR | 2019-02-04 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00669
036909C-1027-PDS-0600-2711 | Process Equipment Datasheet - 10-E-2710 - Depentanizer Condenser | A | 2019-01-22 | IFR | OL1-2G30-2711 | PE | 2019-01-25 | 036909C-JVD-TRN-00720 | 036909C-JVD-TRN-00720 | IFR | 2019-02-07 | 2019-02-15 | R1-No comments | TPSK-LSPA1-T-PE-00720
036909C-1027-PDS-0600-2707 | Process Equipment Datasheet - 10-E-2706 - GHU-1 Cooler | A | 2019-01-24 | IFR | OL1-2G30-2707 | PE | 2019-01-25 | 036909C-JVD-TRN-00720 | 036909C-JVD-TRN-00720 | IFR | 2019-02-07 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00720
036909C-1027-PDS-0600-2703 | Process Equipment Datasheet - 10-E-2705 - GHU-1 Recycle Cooler | A | 2019-01-21 | IFR | OL1-2G30-2703 | PE | 2019-01-25 | 036909C-JVD-TRN-00720 | 036909C-JVD-TRN-00720 | IFR | 2019-02-07 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00720
036909C-1051-PDS-0800-5112 | Process Equipment Datasheet - 10-D-5112 - Suspect Condensate Flash Drum | A | 2018-11-05 | IFR | OL1-2G30-5112 | PE | 2018-11-05 | 036909C-JVD-TRN-00274 | 036909C-JVD-TRN-00274 | IFR | 2018-11-21 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00274
036909C-1051-PDS-0200-5125 | Process Equipment Datasheet - 10-PK-5125 - Condensate Polisher Pkg | A | 2018-11-27 | IFR | OL1-2G30-5125 | PE | 2018-11-27 | 036909C-JVD-TRN-00373 | 036909C-JVD-TRN-00373 | IFR | 2018-12-11 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00373
036909C-1024-TDS-0610-2441 | Mechanical Equipment Data Sheet - 10-E-2441 - HP Deprop Reflux Chiller No 2 | A | 2019-01-14 | IFQ | OL1-2M03-2441 | ME | 2019-01-16 | 036909C-JVD-TRN-00663 | 036909C-JVD-TRN-00663 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00663
036909C-1022-TDS-0610-2211 | Mechanical Equipment Data Sheet - 10-E-2210 A-B - CG 1st Stage Aftercoolers | A | 2019-01-15 | IFQ | OL1-2M03-2211 | ME | 2019-01-22 | 036909C-JVD-TRN-00683 | 036909C-JVD-TRN-00683 | IFR | 2019-02-04 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00683
036909C-1028-TDS-0610-2806 | Mechanical Equipment Data Sheet - 10-E-2805A-C - C3 Refrig Condensers | A | 2019-01-15 | IFQ | OL1-2M03-2806 | ME | 2019-01-17 | 036909C-JVD-TRN-00671 | 036909C-JVD-TRN-00671 | IFR | 2019-01-30 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00671
036909C-1010-TDS-0610-1002 | Mechanical Equipment Data Sheet - 10-E-1000 - LPG Vaporizer | A | 2019-01-18 | IFQ | OL1-2M03-1002 | ME | 2019-01-22 | 036909C-JVD-TRN-00684 | 036909C-JVD-TRN-00684 | IFR | 2019-02-04 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00684
036909C-1024-TDS-0610-2439 | Mechanical Equipment Data Sheet - 10-E-2440 - HP Depropanizer Condenser | A | 2019-01-16 | IFQ | OL1-2M03-2439 | ME | 2019-01-22 | 036909C-JVD-TRN-00683 | 036909C-JVD-TRN-00683 | IFR | 2019-02-04 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00683
036909C-1024-TDS-0610-2472 | Mechanical Equipment Data Sheet - 10-E-2472 - C2 Hydrog 2nd Stage Intercooler | A | 2019-01-10 | IFQ | OL1-2M03-2472 | ME | 2019-01-11 | 036909C-JVD-TRN-00641 | 036909C-JVD-TRN-00641 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-00641
036909C-1024-TDS-0610-2471 | Mechanical Equipment Data Sheet - 10-E-2470 - C2 Hydrog 1st Stage Intercooler | A | 2019-01-10 | IFQ | OL1-2M03-2471 | ME | 2019-01-11 | 036909C-JVD-TRN-00641 | 036909C-JVD-TRN-00641 | IFR | 2019-01-24 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00641
036909C-1020-TDS-0610-2015 | Mechanical Equipment Data Sheet - 10-E-2008 - LS2 Steam Generators | A | 2019-01-13 | IFQ | OL1-2M03-2015 | ME | 2019-01-14 | 036909C-JVD-TRN-00643 | 036909C-JVD-TRN-00643 | IFR | 2019-01-28 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-00643
036909C-1024-TDS-0610-2474 | Mechanical Equipment Data Sheet - 10-E-2474 - C2 Hydrog Aftercooler | A | 2019-01-09 | IFQ | OL1-2M03-2474 | ME | 2019-01-11 | 036909C-JVD-TRN-00641 | 036909C-JVD-TRN-00641 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-00641
036909C-1024-TDS-0610-2406 | Mechanical Equipment Data Sheet - 10-E-2405 - Gas Dryer Feed Chiller | A | 2019-01-02 | IFQ | OL1-2M03-2406 | ME | 2019-01-07 | 036909C-JVD-TRN-00584 | 036909C-JVD-TRN-00584 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00584
036909C-1025-TDS-0610-2503 | Mechanical Equipment Data Sheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | A | 2018-11-28 | IFQ | OL1-2M03-2503 | ME | 2018-11-28 | 036909C-JVD-TRN-00389 | 036909C-JVD-TRN-00389 | IFR | 2018-12-12 | 2018-12-13 | R1-No comments | TPSK-LSPA1-T-ME-00389
036909C-1024-TDS-0610-2461 | Mechanical Equipment Data Sheet - 10-E-2460 - C2 Hydrog Feed Cooler | A | 2018-12-26 | IFQ | OL1-2M03-2461 | ME | 2019-01-03 | 036909C-JVD-TRN-00573 | 036909C-JVD-TRN-00573 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00573
036909C-1021-TDS-0610-2165 | Mechanical Equipment Data Sheet - 10-E-2165 A-D - DSG Reboilers | A | 2018-12-22 | IFQ | OL1-2M03-2165 | ME | 2019-01-03 | 036909C-JVD-TRN-00582 | 036909C-JVD-TRN-00582 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00582
036909C-1024-TDS-0610-2412 | Mechanical Equipment Data Sheet - 10-E-2412 - HP Deprop Feed Chiller | A | 2019-01-04 | IFQ | OL1-2M03-2412 | ME | 2019-01-10 | 036909C-JVD-TRN-00617 | 036909C-JVD-TRN-00617 | IFR | 2019-01-23 | 2019-01-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-00617
036909C-1025-TDS-0610-2502 | Mechanical Equipment Data Sheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | A | 2018-12-06 | IFQ | OL1-2M03-2502 | ME | 2018-12-10 | 036909C-JVD-TRN-00461 | 036909C-JVD-TRN-00461 | IFR | 2018-12-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00461
036909C-1022-TDS-0610-2221 | Mechanical Equipment Data Sheet - 10-E-2220 - CG 2nd Stage Aftercooler | A | 2019-01-03 | IFQ | OL1-2M03-2221 | ME | 2019-01-07 | 036909C-JVD-TRN-00588 | 036909C-JVD-TRN-00588 | IFR | 2019-01-21 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00588
036909C-1026-TDS-0610-2661 | Mechanical Equipment Data Sheet - 10-E-2660 - Debutanizer Condenser | A | 2018-12-07 | IFQ | OL1-2M03-2661 | ME | 2018-12-10 | 036909C-JVD-TRN-00465 | 036909C-JVD-TRN-00465 | IFR | 2018-12-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00465
036909C-1024-TDS-0610-2451 | Mechanical Equipment Data Sheet - 10-E-2450 - LP Depropanizer Condenser | A | 2019-01-04 | IFQ | OL1-2M03-2451 | ME | 2019-01-07 | 036909C-JVD-TRN-00588 | 036909C-JVD-TRN-00588 | IFR | 2019-01-21 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00588
036909C-1029-PDS-2600-2931 | Process Equipment Datasheet - 10-PK-2931 - Propanol Injection Pkg | A | 2019-01-17 | IFR | OL1-2G30-2931 | PE | 2019-01-22 | 036909C-JVD-TRN-00689 | 036909C-JVD-TRN-00689 | IFR | 2019-02-04 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00689
036909C-1028-PDS-0800-2860 | Process Equipment Datasheet - 10-D-2860 - C2R 1st Stage Suction Drum | A | 2018-10-22 | IFR | OL1-2G30-2860 | PE | 2018-10-23 | 036909C-JVD-TRN-00208 | 036909C-JVD-TRN-00208 | IFR | 2018-11-06 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00208
036909C-1029-PDS-0900-2934 | Process Equipment Datasheet - 10-P-2930 - Methanol Injection Pump | A | 2019-01-10 | IFR | OL1-2G30-2934 | PE | 2019-01-14 | 036909C-JVD-TRN-00645 | 036909C-JVD-TRN-00645 | IFR | 2019-01-28 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00645
036909C-1026-PDS-0900-2646 | Process Equipment Datasheet - 10-P-2646 A-B - Propane Recycle Pumps | A | 2018-11-05 | IFR | OL1-2G30-2646 | PE | 2018-11-06 | 036909C-JVD-TRN-00277 | 036909C-JVD-TRN-00277 | IFR | 2018-11-20 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00277
036909C-1026-PDS-0900-2633 | Process Equipment Datasheet - 10-P-2630 A-B - Secondary Deeth Reflux Pumps | A | 2018-11-05 | IFR | OL1-2G30-2633 | PE | 2018-11-06 | 036909C-JVD-TRN-00277 | 036909C-JVD-TRN-00277 | IFR | 2018-11-20 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00277
036909C-1021-SP-0510-2120 | Mechanical Equipment Data Sheet - Distillate Stripper | A | 2018-12-18 | IFQ | OL1-2M03-2120 | ME | 2018-12-20 | 036909C-JVD-TRN-00546 | 036909C-JVD-TRN-00546 | IFR | 2019-01-02 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00546
036909C-102B-DW-1743-0003 | Foundation For 10-D-2455 | A | 2019-02-07 | IFR | OL1-2K34-0049 | CV | 2019-02-11 | 036909C-JVD-TRN-00833 | 036909C-JVD-TRN-00833 | IFR | 2019-02-26 |  | Transmitted | TPSK-LSPA1-T-CV-00833
036909C-102B-DW-1743-0028 | Foundation For 10-D-2610 | A | 2019-02-07 | IFR | OL1-2K34-0155 | CV | 2019-02-11 | 036909C-JVD-TRN-00833 | 036909C-JVD-TRN-00833 | IFR | 2019-02-26 |  | Transmitted | TPSK-LSPA1-T-CV-00833
036909C-1000-SP-0570-0004 | Particular Technical Specification for High Efficiency Internals for Columns | B | 2018-11-12 | IMP | OL1-2M57-0075 | ME | 2018-11-14 | 036909C-JVD-TRN-00314 | 036909C-JVD-TRN-00314 | IFR | 2018-11-29 | 2019-02-08 | R1-No comments | TPSK-LSPA1-T-ME-00314
036909C-1000-MR-0570-0004 | Material Requisition for High Efficiency Internals for Columns | B | 2018-11-12 | IMP | OL1-2M55-0075 | ME | 2018-11-14 | 036909C-JVD-TRN-00314 | 036909C-JVD-TRN-00314 | IFR | 2018-11-29 | 2019-02-08 | R1-No comments | TPSK-LSPA1-T-ME-00314
036909C-1056-PDS-0200-5628 | Process Equipment Datasheet - 10-PIT-5628 - East Gate House Septic Tank | A | 2019-01-02 | IFR | OL1-2G30-5628 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1056-PDS-0200-5627 | Process Equipment Datasheet - 10-PIT-5627 - West Gate House Septic Tank | A | 2019-01-02 | IFR | OL1-2G30-5627 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1056-PDS-0200-5626 | Process Equipment Datasheet - 10-PIT-5626 - Gate House Septic Tank | A | 2019-01-02 | IFR | OL1-2G30-5626 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1055-PDS-1000-5522 | Process Equipment Datasheet - 10-C-5520 A-B - LP Vent Blowers | A | 2018-12-17 | IFR | OL1-2G30-5522 | PE | 2018-12-20 | 036909C-JVD-TRN-00528 | 036909C-JVD-TRN-00528 | IFR | 2019-01-02 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00528
036909C-1052-PDS-0800-5211 | Process Equipment Datasheet - 10-D-5210 - Pilot Gas Vaporizer Cond Pot | A | 2019-01-08 | IFR | OL1-2G30-5211 | PE | 2019-01-10 | 036909C-JVD-TRN-00614 | 036909C-JVD-TRN-00614 | IFR | 2019-01-23 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00614
036909C-1052-PDS-0800-5202 | Process Equipment Datasheet - 10-D-5220 - MP Ethylene Superhtr Cond Pot | A | 2019-01-08 | IFR | OL1-2G30-5202 | PE | 2019-01-10 | 036909C-JVD-TRN-00614 | 036909C-JVD-TRN-00614 | IFR | 2019-01-23 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00614
036909C-1020-PDS-0840-2049 | Process Equipment Datasheet - 10-F-2048 A-B - Heavy Fuel Oil Filters | B | 2019-01-16 | IFD | OL1-2G30-2049 | PE | 2019-01-18 | 036909C-JVD-TRN-00676 | 036909C-JVD-TRN-00676 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00676
036909C-1020-PDS-0840-2028 | Process Equipment Datasheet - 10-F-2028 A-B - FO Pump Purge Oil Filter | B | 2019-01-16 | IFD | OL1-2G30-2028 | PE | 2019-01-18 | 036909C-JVD-TRN-00676 | 036909C-JVD-TRN-00676 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00676
036909C-1020-PDS-0840-2025 | Process Equipment Datasheet - 10-F-2026 A-B Cracker Bottoms Product Filter | B | 2019-01-16 | IFD | OL1-2G30-2025 | PE | 2019-01-18 | 036909C-JVD-TRN-00676 | 036909C-JVD-TRN-00676 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00676
036909C-1022-PDS-0600-2206 | Process Equipment Datasheet - 10-E-2206 - Wash Water Cooler | B | 2019-01-14 | IFD | OL1-2G30-2206 | PE | 2019-01-16 | 036909C-JVD-TRN-00655 | 036909C-JVD-TRN-00655 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00655
036909C-1029-PDS-2600-2920 | Process Equipment Datasheet - 10-PK-2920 - Polymerization Inhibitor Inj Pkg | B | 2019-01-24 | IFD | OL1-2G30-2920 | PE | 2019-01-25 | 036909C-JVD-TRN-00726 | 036909C-JVD-TRN-00726 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00726
036909C-1027-PDS-0600-2715 | Process Equipment Datasheet - 10-E-2715 A-B - Depentanizer Reboiler | A | 2019-01-23 | IFR | OL1-2G30-2715 | PE | 2019-01-25 | 036909C-JVD-TRN-00724 | 036909C-JVD-TRN-00724 | IFR | 2019-02-07 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00724
036909C-1027-PDS-0900-2791 | Process Equipment Datasheet - 10-P-2790 - Light Oil Drain Drum Pump | B | 2019-01-23 | IFD | OL1-2G30-2791 | PE | 2019-01-25 | 036909C-JVD-TRN-00722 | 036909C-JVD-TRN-00722 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00722
036909C-1027-PDS-0600-2701 | Process Equipment Datasheet - 10-E-2701 - GHU-1 Feed - Effluent Exchangers | A | 2019-01-21 | IFR | OL1-2G30-2701 | PE | 2019-01-23 | 036909C-JVD-TRN-00710 | 036909C-JVD-TRN-00710 | IFR | 2019-02-05 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00710
036909C-1025-TDS-0610-2571 | Mechanical Equipment Data Sheet - 10-E-2570 - Deethanizer Condenser | A | 2018-11-12 | IFQ | OL1-2M03-2571 | ME | 2018-11-13 | 036909C-JVD-TRN-00310 | 036909C-JVD-TRN-00310 | IFR | 2018-11-27 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00310
036909C-1028-TDS-0610-2857 | Mechanical Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer | A | 2018-11-13 | IFQ | OL1-2M03-2857 | ME | 2018-11-13 | 036909C-JVD-TRN-00312 | 036909C-JVD-TRN-00312 | IFR | 2018-11-27 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00312
036909C-1026-TDS-0610-2645 | Mechanical Equipment Data Sheet - 10-E-2645 - C3 Tower Reboilers | A | 2018-11-19 | IFQ | OL1-2M03-2645 | ME | 2018-11-26 | 036909C-JVD-TRN-00361 | 036909C-JVD-TRN-00361 | IFR | 2018-12-10 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00361
036909C-1025-SP-0810-2525 | Mechanical Equipment Data Sheet - Hydrogen Drum | A | 2018-12-12 | IFQ | OL1-2M03-2525 | ME | 2019-01-16 | 036909C-JVD-TRN-00657 | 036909C-JVD-TRN-00657 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00657
036909C-1011-PDS-0630-1008 | See document number 036909C-1011-PDS-0630-1108 or OL1-2G30-1108 | A | 2018-09-17 | IFR | OL1-4G30-1008 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00066
036909C-1028-SP-0810-2870 | Mechanical Equipment Data Sheet - C2R 2ND Stage Suction Drum | A | 2018-12-24 | IFQ | OL1-2M03-2870 | ME | 2019-01-17 | 036909C-JVD-TRN-00670 | 036909C-JVD-TRN-00670 | IFR | 2019-01-30 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00670
036909C-1026-PDS-0600-2666 | Process Equipment Datasheet - 10-E-2666 - Debutanizer Bottoms Cooler | C | 2019-01-21 | IFD | OL1-2G30-2666 | PE | 2019-01-23 | 036909C-JVD-TRN-00711 | 036909C-JVD-TRN-00711 | IFI |  | 2019-02-11 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00711
036909C-1028-PDS-0600-2859 | Process Equipment Datasheet - 10-E-2856 - Ethylene Product Subcooler | C | 2019-01-21 | IFD | OL1-2G30-2859 | PE | 2019-01-23 | 036909C-JVD-TRN-00711 | 036909C-JVD-TRN-00711 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00711
036909C-1024-PDS-0600-2434 | Process Equipment Datasheet - 10-E-2435 - Regen Gas Effluent Cooler | B | 2019-01-18 | IFD | OL1-2G30-2434 | PE | 2019-01-22 | 036909C-JVD-TRN-00696 | 036909C-JVD-TRN-00696 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00696
036909C-1024-PDS-0600-2430 | Process Equipment Datasheet - 10-E-2430 - Regen Gas Feed Heater | B | 2019-01-18 | IFD | OL1-2G30-2430 | PE | 2019-01-22 | 036909C-JVD-TRN-00696 | 036909C-JVD-TRN-00696 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00696
036909C-1012-SP-4061-2002 | Elevator Data Sheet | A | 2019-01-15 | IFR | OL1-2M03-2002 | ME | 2019-01-18 | 036909C-JVD-TRN-00681 | 036909C-JVD-TRN-00682 | IFR | 2019-02-01 | 2019-02-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-00681
036909C-1000-JSD-1300-0012 | Pipe Support | A | 2018-11-12 | IFR | OL1-2R04-0012 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 | 2018-12-18 | R1-No comments | TPSK-LSPA1-T-MP-00324
036909C-1056-PDS-0200-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg | A | 2018-11-06 | IFR | OL1-2G30-5653 | PE | 2018-11-06 | 036909C-JVD-TRN-00282 | 036909C-JVD-TRN-00282 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00282
036909C-1053-SP-0910-5361 | Mechanical Equipment Data Sheet for CTU Cooling Water Pumps 10-P-5360 A-B-C | A | 2018-10-22 | IFQ | OL1-2M03-5361 | ME | 2018-10-23 | 036909C-JVD-TRN-00210 | 036909C-JVD-TRN-00210 | IFR | 2018-11-06 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00210
036909C-1056-PDS-2600-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg | A | 2018-11-06 | IFR | OL1-2G30-5650 | PE | 2018-11-06 | 036909C-JVD-TRN-00281 | 036909C-JVD-TRN-00281 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00281
036909C-1056-PDS-2600-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg | A | 2018-11-06 | IFR | OL1-2G30-5670 | PE | 2018-11-06 | 036909C-JVD-TRN-00281 | 036909C-JVD-TRN-00281 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00281
036909C-1055-PDS-1000-5521 | Process Equipment Datasheet - 10-PK-5520 - LP Vent Blower Pkg | A | 2018-11-15 | IFR | OL1-2G30-5521 | PE | 2018-11-19 | 036909C-JVD-TRN-00332 | 036909C-JVD-TRN-00332 | IFR | 2018-12-03 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-PE-00332
036909C-1056-PDS-2600-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package | A | 2018-11-06 | IFR | OL1-2G30-5644 | PE | 2018-11-06 | 036909C-JVD-TRN-00281 | 036909C-JVD-TRN-00281 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00281
036909C-1051-SP-0910-5121 | Mechanical Equipment Datasheet - Raw Condensate Pumps | A | 2018-11-20 | IFQ | OL1-2M03-5121 | ME | 2018-11-20 | 036909C-JVD-TRN-00341 | 036909C-JVD-TRN-00341 | IFR | 2018-12-04 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-ME-00341
036909C-1051-SP-0910-5111 | Mechanical Equipment Datasheet - Suspect Condensate Pumps | A | 2018-11-20 | IFQ | OL1-2M03-5111 | ME | 2018-11-20 | 036909C-JVD-TRN-00341 | 036909C-JVD-TRN-00341 | IFR | 2018-12-04 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-ME-00341
036909C-1053-PDS-0900-5352 | Process Equipment Datasheet - 10-P-5350 A-H - Olefins Cooling Water Pumps | C | 2018-10-25 | IFD | OL1-2G30-5352 | PE | 2018-10-26 | 036909C-JVD-TRN-00234 | 036909C-JVD-TRN-00234 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00075
036909C-1053-SP-0910-5352 | Mechanical Equipment Data Sheet for Olefins Cooling Water Pumps 10-P-5350 A-H | A | 2018-10-22 | IFQ | OL1-2M03-5352 | ME | 2018-10-23 | 036909C-JVD-TRN-00210 | 036909C-JVD-TRN-00210 | IFR | 2018-11-06 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00210
036909C-1051-PDS-0900-5101 | Process Equipment Datasheet - 10-P-5100 A-C - SHP BFW Pumps | B | 2018-10-30 | IFD | OL1-2G30-5101 | PE | 2018-10-31 | 036909C-JVD-TRN-00251 | 036909C-JVD-TRN-00251 | IFI |  | 2018-12-13 | R1-No comments | TPSK-LSPA1-T-PE-00251
036909C-1051-PDS-0900-5102 | Process Equipment Datasheet - 10-P-5102 A-B - VLP BFW Pumps | B | 2018-10-30 | IFD | OL1-2G30-5102 | PE | 2018-10-31 | 036909C-JVD-TRN-00251 | 036909C-JVD-TRN-00251 | IFI |  | 2018-12-13 | R1-No comments | TPSK-LSPA1-T-PE-00251
036909C-1051-PDS-0600-5108 | Process Equipment Datasheet - 10-E-5110 - Suspect Condensate Cooler | A | 2018-10-29 | IFR | OL1-2G30-5108 | PE | 2018-10-30 | 036909C-JVD-TRN-00243 | 036909C-JVD-TRN-00243 | IFR | 2018-11-12 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00243
036909C-1051-PDS-0800-5114 | Process Equipment Datasheet - 10-D-5114 - LP Condensate Flash Drum | A | 2018-11-05 | IFR | OL1-2G30-5114 | PE | 2018-11-05 | 036909C-JVD-TRN-00274 | 036909C-JVD-TRN-00274 | IFR | 2018-11-21 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00274
036909C-1051-PDS-0600-5107 | Process Equipment Datasheet - 10-E-5112 - Suspect Cond Flash Drum Vent Condenser | A | 2018-10-26 | IFR | OL1-2G30-5107 | PE | 2018-10-30 | 036909C-JVD-TRN-00243 | 036909C-JVD-TRN-00243 | IFR | 2018-11-12 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00243
036909C-1051-SP-0910-5101 | Mechanical Equipment Data Sheet SHP BFW Pumps - 10-P-5100 A-B-C | A | 2018-10-25 | IFQ | OL1-2M03-5101 | ME | 2018-10-27 | 036909C-JVD-TRN-00236 | 036909C-JVD-TRN-00236 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00236
036909C-1051-PDS-0800-5150 | Process Equipment Datasheet - 10-D-5150 - Continuous Blow Down Flash Drum | A | 2018-11-15 | IFR | OL1-2G30-5150 | PE | 2018-11-19 | 036909C-JVD-TRN-00331 | 036909C-JVD-TRN-00331 | IFR | 2018-12-03 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00331
036909C-1030-PDS-1000-3073 | Process Equipment Data Sheet - 10-C-3070 - BDU Recycle Gas Compressor | A | 2018-11-20 | IFR | OL1-2G30-3073 | PE | 2018-11-20 | 036909C-JVD-TRN-00344 | 036909C-JVD-TRN-00344 | IFR | 2018-12-04 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00344
036909C-1051-SP-0910-5102 | Mechanical Equipment Data Sheet VLP BFW Pumps - 10-P-5102 A-B | A | 2018-10-25 | IFQ | OL1-2M03-5102 | ME | 2018-10-27 | 036909C-JVD-TRN-00236 | 036909C-JVD-TRN-00236 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00236
036909C-1051-PDS-0900-5121 | Process Equipment Datasheet - 10-P-5120 A-B - Raw Condensate Pumps | A | 2018-10-23 | IFR | OL1-2G30-5121 | PE | 2018-10-24 | 036909C-JVD-TRN-00219 | 036909C-JVD-TRN-00219 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00219
036909C-102D-DW-1743-0027 | Foundation For 10-E-2857 | A | 2019-02-04 | IFR | OL1-2K34-0132 | CV | 2019-02-06 | 036909C-JVD-TRN-00807 | 036909C-JVD-TRN-00807 | IFR | 2019-02-20 |  | Transmitted | TPSK-LSPA1-T-CV-00807
036909C-1051-PDS-0900-5111 | Process Equipment Datasheet - 10-P-5112 A-B - Suspect Condensate Pumps | A | 2018-10-23 | IFR | OL1-2G30-5111 | PE | 2018-10-24 | 036909C-JVD-TRN-00219 | 036909C-JVD-TRN-00219 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00219
036909C-1051-PDS-0600-5103 | Process Equipment Datasheet - 10-E-5100 - Deaerator Vent Condenser | A | 2018-10-25 | IFR | OL1-2G30-5103 | PE | 2018-10-25 | 036909C-JVD-TRN-00230 | 036909C-JVD-TRN-00230 | IFR | 2018-11-08 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00230
036909C-1051-SP-0910-5109 | Mechanical Equipment Data Sheet - Condensate Pumps 10-P-5110 A-B | A | 2018-10-25 | IFQ | OL1-2M03-5109 | ME | 2018-10-26 | 036909C-JVD-TRN-00235 | 036909C-JVD-TRN-00235 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00235
036909C-1051-PDS-0600-5113 | Process Equipment Datasheet - 10-E-5113 - Foul Condensate Cooler | A | 2018-10-25 | IFR | OL1-2G30-5113 | PE | 2018-10-25 | 036909C-JVD-TRN-00230 | 036909C-JVD-TRN-00230 | IFR | 2018-11-08 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00230
036909C-102B-DW-1743-0008 | Foundation For 10-D-2330 | A | 2019-01-28 | IFR | OL1-2K34-0059 | CV | 2019-02-06 | 036909C-JVD-TRN-00807 | 036909C-JVD-TRN-00807 | IFR | 2019-02-20 |  | Transmitted | TPSK-LSPA1-T-CV-00807
036909C-102A-DW-1743-0020 | Foundation For 10-E-2048 | A | 2019-02-04 | IFR | OL1-2K34-0027 | CV | 2019-02-06 | 036909C-JVD-TRN-00807 | 036909C-JVD-TRN-00807 | IFR | 2019-02-20 |  | Transmitted | TPSK-LSPA1-T-CV-00807
036909C-1029-MSD-0011-2901 | Material Selection Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | A | 2018-11-02 | IFA | OL1-2G74-2901 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1028-PDS-0900-2801 | Process Equipment Datasheet - 10-P-2805 A-B - Propylene Product Pumps | A | 2018-11-05 | IFR | OL1-2G30-2801 | PE | 2018-11-06 | 036909C-JVD-TRN-00277 | 036909C-JVD-TRN-00277 | IFR | 2018-11-20 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00277
036909C-102B-DW-1743-0006 | Foundation For 10-D-2316 | A | 2019-01-28 | IFR | OL1-2K34-0057 | CV | 2019-02-06 | 036909C-JVD-TRN-00807 | 036909C-JVD-TRN-00807 | IFR | 2019-02-20 |  | Transmitted | TPSK-LSPA1-T-CV-00807
036909C-1029-PDS-2600-2914 | Process Equipment Datasheet - 10-PK-2914 - Neutralization Injection Pkg | A | 2018-10-15 | IFR | OL1-2G30-2914 | PE | 2018-10-16 | 036909C-JVD-TRN-00181 | 036909C-JVD-TRN-00181 | IFR | 2018-10-30 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00181
036909C-102D-CN-1733-0013 | Calculation Note for Foundation of 10-D-2645 | A | 2019-02-01 | IFR | OL1-2K13-0101 | CV | 2019-02-07 | 036909C-JVD-TRN-00816 | 036909C-JVD-TRN-00816 | IFA | 2019-02-22 |  | Transmitted | TPSK-LSPA1-T-CV-00816
036909C-1028-PDS-0800-2870 | Process Equipment Datasheet - 10-D-2870 - C2R 2nd Stage Suction Drum | A | 2018-10-23 | IFR | OL1-2G30-2870 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-00218
036909C-102D-CN-1733-0023 | Calculation Note for Foundation of 10-E-2857 | A | 2019-02-04 | IFR | OL1-2K13-0125 | CV | 2019-02-07 | 036909C-JVD-TRN-00816 | 036909C-JVD-TRN-00816 | IFA | 2019-02-22 |  | Transmitted | TPSK-LSPA1-T-CV-00816
036909C-1028-PDS-0900-2816 | Process Equipment Datasheet - 10-P-2815 - Propylene Refrig Recovery Pump | A | 2018-11-14 | IFR | OL1-2G30-2816 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00340
036909C-102A-CN-1733-0016 | Calculation Note for Foundation of 10-E-2048 | A | 2019-02-04 | IFR | OL1-2K13-0022 | CV | 2019-02-07 | 036909C-JVD-TRN-00816 | 036909C-JVD-TRN-00816 | IFA | 2019-02-22 |  | Transmitted | TPSK-LSPA1-T-CV-00816
036909C-1028-MSD-0011-2803 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | A | 2018-11-02 | IFA | OL1-2G74-2803 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1028-PDS-0600-2857 | Process Equipment Datasheet - 10-E-2857 - HP Ethylene Product Vaporizer | B | 2018-11-01 | IFD | OL1-2G30-2857 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272
036909C-1028-PDS-0600-2809 | Process Equipment Datasheet - 10-E-2809 - C3 Chiller No 2 | B | 2018-11-01 | IFD | OL1-2G30-2809 | PE | 2018-11-05 | 036909C-JVD-TRN-00273 | 036909C-JVD-TRN-00273 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00273
036909C-1028-MSD-0011-2802 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | A | 2018-11-02 | IFA | OL1-2G74-2802 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1028-MSD-0011-2801 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | A | 2018-11-02 | IFA | OL1-2G74-2801 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1028-PDS-0800-2854 | Process Equipment Datasheet - 10-D-2855 - C2R Surge Drum | A | 2018-10-23 | IFR | OL1-2G30-2854 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218
036909C-1028-PDS-0800-2805 | Process Equipment Datasheet - 10-D-2805 - C3R Surge Drum | A | 2018-10-23 | IFR | OL1-2G30-2805 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218
036909C-1028-MSD-0011-2804 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | A | 2018-11-02 | IFA | OL1-2G74-2804 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1026-PDS-0800-2662 | Process Equipment Datasheet - 10-D-2660 - Debutanizer Reflux Drum | A | 2018-11-07 | IFR | OL1-2G30-2662 | PE | 2018-11-07 | 036909C-JVD-TRN-00287 | 036909C-JVD-TRN-00287 | IFR | 2018-11-21 | 2019-01-11 | R1-No comments | TPSK-LSPA1-T-PE-00287
036909C-1026-PDS-0900-2663 | Process Equipment Datasheet - 10-P-2660 A-B - Debutanizer Reflux - Product Pumps | A | 2018-11-14 | IFR | OL1-2G30-2663 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00340
036909C-1026-PDS-0900-2647 | Process Equipment Datasheet - 10-P-2647 - HP Propylene - Off Spec Pumps | A | 2018-11-08 | IFR | OL1-2G30-2647 | PE | 2018-11-09 | 036909C-JVD-TRN-00302 | 036909C-JVD-TRN-00302 | IFR | 2018-11-23 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00302
036909C-1026-PDS-0600-2665 | Process Equipment Datasheet - 10-E-2665 A-B - Debutanizer Reboilers | B | 2018-11-01 | IFD | OL1-2G30-2665 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272
036909C-1026-PDS-0800-2610 | Process Equipment Datasheet - 10-D-2610 - C3 Hydrog Arsine Guard Bed | A | 2018-11-20 | IFR | OL1-2G30-2610 | PE | 2018-11-21 | 036909C-JVD-TRN-00345 | 036909C-JVD-TRN-00345 | IFR | 2018-12-05 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00345
036909C-1026-MSD-0011-2603 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | A | 2018-11-02 | IFA | OL1-2G74-2603 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1026-PDS-0800-2632 | Process Equipment Datasheet - 10-D-2630 - Secondary Deeth Reflux Drum | A | 2018-11-07 | IFR | OL1-2G30-2632 | PE | 2018-11-07 | 036909C-JVD-TRN-00287 | 036909C-JVD-TRN-00287 | IFR | 2018-11-21 | 2019-01-11 | R1-No comments | TPSK-LSPA1-T-PE-00287
036909C-1026-MSD-0011-2604 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | A | 2018-11-02 | IFA | OL1-2G74-2604 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1026-PDS-0500-2640 | Process Equipment Datasheet - 10-T-2640 - C3 Tower | A | 2018-10-18 | IFR | OL1-2G30-2640 | PE | 2018-10-22 | 036909C-JVD-TRN-00201 | 036909C-JVD-TRN-00201 | IFR | 2018-11-05 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00201
036909C-1026-MSD-0011-2602 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | A | 2018-11-02 | IFA | OL1-2G74-2602 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1026-MSD-0011-2601 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | A | 2018-11-02 | IFA | OL1-2G74-2601 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1025-PDS-0800-2551 | Process Equipment Datasheet - 10-D-2550 - Expander Suction Drum | A | 2018-10-23 | IFR | OL1-2G30-2551 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-00218
036909C-1025-PDS-0800-2572 | Process Equipment Datasheet - 10-D-2570 - Deethanizer Reflux Drum | A | 2018-10-24 | IFR | OL1-2G30-2572 | PE | 2018-10-25 | 036909C-JVD-TRN-00227 | 036909C-JVD-TRN-00227 | IFR | 2018-11-08 | 2018-12-05 | R1-No comments | TPSK-LSPA1-T-PE-00227
036909C-1025-PDS-0800-2555 | Process Equipment Datasheet - 10-D-2555 - Expander Discharge Drum | A | 2018-10-23 | IFR | OL1-2G30-2555 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218
036909C-1025-PDS-0600-2582 | Process Equipment Datasheet - 10-E-2582 - C2 Tower Reflux Cooler | A | 2018-11-01 | IFR | OL1-2G30-2582 | PE | 2018-11-01 | 036909C-JVD-TRN-00265 | 036909C-JVD-TRN-00265 | IFR | 2018-11-15 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00265
036909C-1025-PDS-0800-2504 | Process Equipment Datasheet - 10-D-2504 - Demeth Prefrac Feed Separator No 1 | A | 2018-10-23 | IFR | OL1-2G30-2504 | PE | 2018-10-24 | 036909C-JVD-TRN-00217 | 036909C-JVD-TRN-00217 | IFR | 2018-11-07 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-PE-00217
036909C-1025-PDS-0800-2506 | Process Equipment Datasheet - 10-D-2506 - Demeth Prefrac Feed Separator No 2 | A | 2018-10-23 | IFR | OL1-2G30-2506 | PE | 2018-10-24 | 036909C-JVD-TRN-00217 | 036909C-JVD-TRN-00217 | IFR | 2018-11-07 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-PE-00217
036909C-1025-PDS-4100-2560 | Process Equipment Datasheet - 10-PK-2560 - PSA Unit | A | 2018-10-17 | IFR | OL1-2G30-2560 | PE | 2018-10-17 | 036909C-JVD-TRN-00190 | 036909C-JVD-TRN-00190 | IFR | 2018-10-31 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00190
036909C-1025-PDS-0600-2591 | Process Equipment Datasheet - 10-E-2856 - Ethylene Product Subcooler | A | 2018-10-23 | IFR | OL1-2G30-2591 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216 | CHANGE NUMBER - For next revision see 1025-PDS-0600-2859 - OL1-2G30-2859
036909C-1025-PDS-0900-2586 | Process Equipment Datasheet - 10-P-2586 A-B - Ethane Recycle Pumps | A | 2018-11-14 | IFR | OL1-2G30-2586 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00340
036909C-1025-PDS-0900-2573 | Process Equipment Datasheet - 10-P-2570 A-B - Deethanizer Reflux Pumps | A | 2018-11-14 | IFR | OL1-2G30-2573 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00340
036909C-1025-PDS-0800-2508 | Process Equipment Datasheet - 10-D-2508 - Demeth Prefrac Feed Separator No 3 | A | 2018-10-23 | IFR | OL1-2G30-2508 | PE | 2018-10-24 | 036909C-JVD-TRN-00217 | 036909C-JVD-TRN-00217 | IFR | 2018-11-07 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-PE-00217
036909C-1025-PDS-0800-2525 | Process Equipment Datasheet - 10-D-2525 - Hydrogen Drum | A | 2018-10-23 | IFR | OL1-2G30-2525 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218
036909C-1025-PDS-0800-2508 | Process Equipment Datasheet - 10-D-2508 - Demeth Prefrac Feed Separator No 3 | B | 2018-11-08 | IFD | OL1-2G30-2508 | PE | 2018-11-09 | 036909C-JVD-TRN-00303 | 036909C-JVD-TRN-00303 | IFI |  | 2018-11-26 | R1-No comments | TPSK-LSPA1-T-PE-00303
036909C-1025-PDS-0800-2506 | Process Equipment Datasheet - 10-D-2506 - Demeth Prefrac Feed Separator No 2 | B | 2018-11-08 | IFD | OL1-2G30-2506 | PE | 2018-11-09 | 036909C-JVD-TRN-00303 | 036909C-JVD-TRN-00303 | IFI |  | 2018-11-26 | R1-No comments | TPSK-LSPA1-T-PE-00303
036909C-1025-PDS-0600-2515 | Process Equipment Datasheet - 10-E-2515 - Demeth Prefrac Reboiler | A | 2018-10-23 | IFR | OL1-2G30-2515 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216
036909C-1025-MSD-0011-2506 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | A | 2018-11-02 | IFA | OL1-2G74-2506 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1025-PDS-0500-2570 | Process Equipment Datasheet - 10-T-2570 - Deethanizer | A | 2018-10-17 | IFR | OL1-2G30-2570 | PE | 2018-10-17 | 036909C-JVD-TRN-00191 | 036909C-JVD-TRN-00191 | IFR | 2018-10-31 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00191
036909C-1025-PDS-0600-2546 | Process Equipment Datasheet - 10-E-2546 - Demethanizer Bottoms Cooler | A | 2018-10-23 | IFR | OL1-2G30-2546 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216
036909C-1025-PDS-0600-2548 | Process Equipment Datasheet - 10-E-2548 - Demethanizer Bottoms Vaporizer | A | 2018-10-23 | IFR | OL1-2G30-2548 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00216
036909C-1025-PDS-0600-2545 | Process Equipment Datasheet - 10-E-2545 - Demethanizer Reboiler | A | 2018-10-23 | IFR | OL1-2G30-2545 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216
036909C-1024-PDS-0600-2461 | Process Equipment Datasheet - 10-E-2460 - C2 Hydrog Feed Cooler | A | 2018-10-30 | IFR | OL1-2G30-2461 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250
036909C-1025-MSD-0011-2505 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | A | 2018-11-02 | IFA | OL1-2G74-2505 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1025-MSD-0011-2504 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | A | 2018-11-02 | IFA | OL1-2G74-2504 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1025-MSD-0011-2502 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | A | 2018-11-02 | IFA | OL1-2G74-2502 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1025-MSD-0011-2503 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | A | 2018-11-02 | IFA | OL1-2G74-2503 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1025-MSD-0011-2501 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | A | 2018-11-02 | IFA | OL1-2G74-2501 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1024-PDS-0800-2452 | Process Equipment Datasheet - 10-D-2450 - LP Depropanizer Reflux Drum | A | 2018-10-31 | IFR | OL1-2G30-2452 | PE | 2018-11-01 | 036909C-JVD-TRN-00264 | 036909C-JVD-TRN-00264 | IFR | 2018-11-15 | 2018-11-27 | R1-No comments | TPSK-LSPA1-T-PE-00264
036909C-1024-PDS-0800-2405 | Process Equipment Datasheet - 10-D-2405 - Gas Dryer Feed KO Drum | A | 2018-11-13 | IFR | OL1-2G30-2405 | PE | 2018-11-14 | 036909C-JVD-TRN-00315 | 036909C-JVD-TRN-00315 | IFR | 2018-11-28 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00315
036909C-1024-PDS-0800-2438 | Process Equipment Datasheet - 10-D-2440 - HP Depropanizer Reflux Drum | A | 2018-10-31 | IFR | OL1-2G30-2438 | PE | 2018-11-01 | 036909C-JVD-TRN-00264 | 036909C-JVD-TRN-00264 | IFR | 2018-11-15 | 2018-11-27 | R1-No comments | TPSK-LSPA1-T-PE-00264
036909C-1024-PDS-0900-2416 | Process Equipment Datasheet - 10-P-2415 A-B - CG Liquid Dryer Feed Pumps | A | 2018-11-06 | IFR | OL1-2G30-2416 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00285
036909C-1024-PDS-0800-2415 | Process Equipment Datasheet - 10-D-2415 - CG Liquid Dryer Feed Coalescer | A | 2018-11-19 | IFR | OL1-2G30-2415 | PE | 2018-11-20 | 036909C-JVD-TRN-00339 | 036909C-JVD-TRN-00339 | IFR | 2018-12-04 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00339
036909C-1024-PDS-0800-2420 | Process Equipment Datasheet - 10-D-2420 A-B - CG Liquid Dryer | A | 2018-11-08 | IFR | OL1-2G30-2420 | PE | 2018-11-09 | 036909C-JVD-TRN-00301 | 036909C-JVD-TRN-00301 | IFR | 2018-11-23 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00301
036909C-1024-PDS-0900-2453 | Process Equipment Datasheet - 10-P-2450 A-B - LP Depropanizer Reflux-Product Pump | A | 2018-11-06 | IFR | OL1-2G30-2453 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00285
036909C-1024-PDS-0800-2411 | Process Equipment Datasheet - 10-D-2411 - Cracked Gas Mercury Adsorber | A | 2018-11-19 | IFR | OL1-2G30-2411 | PE | 2018-11-20 | 036909C-JVD-TRN-00339 | 036909C-JVD-TRN-00339 | IFR | 2018-12-04 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00339
036909C-1024-PDS-0600-2413 | Process Equipment Datasheet - 10-E-2413 - HP Deprop Feed - Overhead Exchanger | A | 2018-10-30 | IFR | OL1-2G30-2413 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R2-Comments as noted | TPSK-LSPA1-T-PE-00250
036909C-1024-PDS-0600-2412 | Process Equipment Datasheet - 10-E-2412 - HP Depropanizer Feed Chiller | A | 2018-10-26 | IFR | OL1-2G30-2412 | PE | 2018-10-30 | 036909C-JVD-TRN-00239 | 036909C-JVD-TRN-00239 | IFR | 2018-11-12 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00239
036909C-1024-MSD-0011-2403 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | A | 2018-11-02 | IFA | OL1-2G74-2403 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1024-MSD-0011-2402 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | A | 2018-11-02 | IFA | OL1-2G74-2402 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1024-PDS-0600-2406 | Process Equipment Datasheet - 10-E-2405 - Gas Dryer Feed Chiller | A | 2018-10-26 | IFR | OL1-2G30-2406 | PE | 2018-10-30 | 036909C-JVD-TRN-00239 | 036909C-JVD-TRN-00239 | IFR | 2018-11-12 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00239
036909C-1024-MSD-0011-2404 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | A | 2018-11-02 | IFA | OL1-2G74-2404 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1024-MSD-0011-2405 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | A | 2018-11-02 | IFA | OL1-2G74-2405 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1024-PDS-0600-2442 | Process Equipment Datasheet - 10-E-2442 - HP Deprop Reflux Chiller No 1 | A | 2018-10-30 | IFR | OL1-2G30-2442 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250
036909C-1024-PDS-0600-2441 | Process Equipment Datasheet - 10-E-2441 - HP Deprop Reflux Chiller No 2 | A | 2018-10-30 | IFR | OL1-2G30-2441 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250
036909C-1024-PDS-0600-2455 | Process Equipment Datasheet - 10-E-2455 A-B - LP Depropanizer Reboilers | A | 2018-10-24 | IFR | OL1-2G30-2455 | PE | 2018-10-25 | 036909C-JVD-TRN-00228 | 036909C-JVD-TRN-00228 | IFR | 2018-11-08 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00228
036909C-1024-PDS-0600-2446 | Process Equipment Datasheet - 10-E-2446 - LP Depropanizer Feed Cooler | A | 2018-10-30 | IFR | OL1-2G30-2446 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250
036909C-1024-PDS-0600-2451 | Process Equipment Datasheet - 10-E-2450 - LP Depropanizer Condenser | A | 2018-10-31 | IFR | OL1-2G30-2451 | PE | 2018-10-31 | 036909C-JVD-TRN-00259 | 036909C-JVD-TRN-00259 | IFR | 2018-11-14 | 2018-11-20 | R2-Comments as noted | TPSK-LSPA1-T-PE-00259
036909C-1024-PDS-0400-2470 | Process Equipment Datasheet - 10-R-2470 A-C - C2 Hydrog Reactor | A | 2018-11-08 | IFR | OL1-2G30-2470 | PE | 2018-11-09 | 036909C-JVD-TRN-00299 | 036909C-JVD-TRN-00299 | IFR | 2018-11-23 | 2018-11-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-00299
036909C-1024-PDS-0600-2439 | Process Equipment Datasheet - 10-E-2440 - HP Depropanizer Condenser | A | 2018-10-30 | IFR | OL1-2G30-2439 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250
036909C-1024-PDS-0600-2445 | Process Equipment Datasheet - 10-E-2445 A-B - HP Depropanizer Reboilers | A | 2018-11-01 | IFR | OL1-2G30-2445 | PE | 2018-11-01 | 036909C-JVD-TRN-00267 | 036909C-JVD-TRN-00267 | IFR | 2018-11-15 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00267
036909C-1023-PDS-0900-2321 | Process Equipment Datasheet - 10-P-2320 A-B - Spent Caustic Pumps | A | 2018-10-29 | IFR | OL1-2G30-2321 | PE | 2018-10-31 | 036909C-JVD-TRN-00252 | 036909C-JVD-TRN-00252 | IFR | 2018-11-14 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00252
036909C-1024-MSD-0011-2401 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | A | 2018-11-02 | IFA | OL1-2G74-2401 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1023-PDS-0900-2393 | Process Equipment Datasheet - 10-P-2392 - Spent Caustic Drain Drum Pump | A | 2018-10-29 | IFR | OL1-2G30-2393 | PE | 2018-10-31 | 036909C-JVD-TRN-00252 | 036909C-JVD-TRN-00252 | IFR | 2018-11-14 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00252
036909C-1023-PDS-0840-2319 | Process Equipment Datasheet - 10-F-2320 A-B - Spent Caustic Pump Discharge Filters | A | 2018-10-29 | IFR | OL1-2G30-2319 | PE | 2018-10-31 | 036909C-JVD-TRN-00255 | 036909C-JVD-TRN-00255 | IFR | 2018-11-14 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00255
036909C-1023-SP-0910-2304 | Mechanical Equipment Datasheet - Intermediate Caustic Circulating Pump | A | 2018-11-13 | IFQ | OL1-2M03-2304 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320 | IFR | 2018-11-29 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00320
036909C-1023-SP-0910-2306 | Mechanical Equipment Datasheet - Weak Caustic Circulating Pumps | A | 2018-11-13 | IFQ | OL1-2M03-2306 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320 | IFR | 2018-11-29 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00320
036909C-1023-PDS-4100-2350 | Process Equipment Datasheet - 10-PK-2350 - Wet Air Oxidation Pkg | A | 2018-10-15 | IFR | OL1-2G30-2350 | PE | 2018-10-16 | 036909C-JVD-TRN-00180 | 036909C-JVD-TRN-00180 | IFR | 2018-10-30 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00180
036909C-1022-PDS-0800-2245 | Process Equipment Datasheet - 10-D-2245 - CG 4th Stage Discharge Drum | A | 2018-10-31 | IFR | OL1-2G30-2245 | PE | 2018-11-01 | 036909C-JVD-TRN-00264 | 036909C-JVD-TRN-00264 | IFR | 2018-11-15 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00264
036909C-1023-PDS-0840-2307 | Process Equipment Datasheet - 10-F-2306 A-B - Weak Caustic Circulating Filters | A | 2018-10-18 | IFR | OL1-2G30-2307 | PE | 2018-10-22 | 036909C-JVD-TRN-00205 | 036909C-JVD-TRN-00205 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00205
036909C-1023-MSD-0011-2304 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | A | 2018-11-02 | IFA | OL1-2G74-2304 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1023-MSD-0011-2305 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | A | 2018-11-02 | IFA | OL1-2G74-2305 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1022-PDS-0600-2241 | Process Equipment Datasheet - 10-E-2240 A-B - CG 4th Stage Aftercooler | A | 2018-10-18 | IFR | OL1-2G30-2241 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00206
036909C-1023-PDS-0840-2314 | Process Equipment Datasheet - 10-F-2310 A-B - Wash Oil Circulating Filter | A | 2018-10-18 | IFR | OL1-2G30-2314 | PE | 2018-10-22 | 036909C-JVD-TRN-00205 | 036909C-JVD-TRN-00205 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00205
036909C-1022-PDS-0600-2221 | Process Equipment Datasheet - 10-E-2220 A-B - CG 2nd Stage Aftercoolers | A | 2018-10-18 | IFR | OL1-2G30-2221 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00206
036909C-1023-PDS-0600-2305 | Process Equipment Datasheet - 10-E-2305 - Caustic Tower Feed Heater | A | 2018-10-31 | IFR | OL1-2G30-2305 | PE | 2018-10-31 | 036909C-JVD-TRN-00259 | 036909C-JVD-TRN-00259 | IFR | 2018-11-14 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00259
036909C-1022-PDS-0600-2231 | Process Equipment Datasheet - 10-E-2230 A-B - CG 3rd Stage Aftercooler | A | 2018-10-18 | IFR | OL1-2G30-2231 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00206
036909C-1022-MSD-0011-2201 | Material Selection Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | A | 2018-11-02 | IFA | OL1-2G74-2201 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1023-MSD-0011-2301 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | A | 2018-11-02 | IFA | OL1-2G74-2301 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1022-PDS-0600-2211 | Process Equipment Datasheet - 10-E-2210 A-B - CG 1st Stage Aftercoolers | A | 2018-11-01 | IFR | OL1-2G30-2211 | PE | 2018-11-01 | 036909C-JVD-TRN-00266 | 036909C-JVD-TRN-00266 | IFR | 2018-11-15 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00266
036909C-1023-PDS-0800-2310 | Process Equipment Datasheet - 10-D-2310 - Spent Caustic Deoiling Drum | A | 2018-10-29 | IFR | OL1-2G30-2310 | PE | 2018-10-31 | 036909C-JVD-TRN-00254 | 036909C-JVD-TRN-00254 | IFR | 2018-11-14 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00254
036909C-1023-MSD-0011-2303 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | A | 2018-11-02 | IFA | OL1-2G74-2303 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1023-MSD-0011-2302 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | A | 2018-11-02 | IFA | OL1-2G74-2302 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1022-PDS-0900-2222 | Process Equipment Datasheet - 10-P-2220 A-B - CG 2nd Stage Condensed HC Pumps | A | 2018-11-06 | IFR | OL1-2G30-2222 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00285
036909C-1022-PDS-0900-2212 | Process Equipment Datasheet - 10-P-2210 A-B - CG 1st Stage Condensate Pumps | A | 2018-11-06 | IFR | OL1-2G30-2212 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00285
036909C-1021-SP-0910-2106 | Mechanical Equipment Data Sheet - Quench Water Pumps - 10-P-2106 A-B-C | A | 2018-10-25 | IFQ | OL1-2M03-2106 | ME | 2018-10-27 | 036909C-JVD-TRN-00236 | 036909C-JVD-TRN-00236 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00236
036909C-1021-PDS-0500-2100 | Process Equipment Datasheet - 10-T-2100 - Quench Water Tower | A | 2018-10-26 | IFR | OL1-2G30-2100 | PE | 2018-10-29 | 036909C-JVD-TRN-00238 | 036909C-JVD-TRN-00238 | IFR | 2018-11-12 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00238
036909C-1021-PDS-0900-2191 | Process Equipment Datasheet - 10-P-2190- Quench Water Drain Drum Pump | A | 2018-11-20 | IFR | OL1-2G30-2191 | PE | 2018-11-21 | 036909C-JVD-TRN-00346 | 036909C-JVD-TRN-00346 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00346
036909C-1021-PDS-0900-2105 | Process Equipment Datasheet - 10-P-2105 A-B - Quench Oil Reflux Pumps | A | 2018-11-06 | IFR | OL1-2G30-2105 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00285
036909C-1021-PDS-0600-2166 | Process Equipment Datasheet - 10-E-2166 - DSG Blowdown Cooler | A | 2018-10-22 | IFR | OL1-2G30-2166 | PE | 2018-10-23 | 036909C-JVD-TRN-00209 | 036909C-JVD-TRN-00209 | IFR | 2018-11-06 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00209
036909C-1020-SP-0910-2006 | Mechanical Equipment Data Sheet Quench Oil Pump 10-P-2006 A-B-C | A | 2018-10-25 | IFQ | OL1-2M03-2006 | ME | 2018-10-26 | 036909C-JVD-TRN-00235 | 036909C-JVD-TRN-00235 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00235
036909C-1021-PDS-0500-2120 | Process Equipment Datasheet - 10-T-2120 - Distillate Stripper | A | 2018-10-29 | IFR | OL1-2G30-2120 | PE | 2018-10-31 | 036909C-JVD-TRN-00253 | 036909C-JVD-TRN-00253 | IFR | 2018-11-14 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00253
036909C-1021-SP-0910-2146 | Mechanical Equipment Data Sheet - DSG Feed Pumps 10-P-2146 A-B | A | 2018-10-25 | IFQ | OL1-2M03-2146 | ME | 2018-10-26 | 036909C-JVD-TRN-00235 | 036909C-JVD-TRN-00235 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00235
036909C-1021-MSD-0011-2102 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | A | 2018-11-02 | IFA | OL1-2G74-2102 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1021-PDS-0600-2125 | Process Equipment Datasheet - 10-E-2125 - Distillate Stripper Reboiler | A | 2018-11-01 | IFR | OL1-2G30-2125 | PE | 2018-11-01 | 036909C-JVD-TRN-00265 | 036909C-JVD-TRN-00265 | IFR | 2018-11-15 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00265
036909C-1021-MSD-0011-2103 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | A | 2018-11-02 | IFA | OL1-2G74-2103 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1021-PDS-0900-2106 | Process Equipment Datasheet - 10-P-2106 A-C - Quench Water Pumps | B | 2018-10-18 | IFD | OL1-2G30-2106 | PE | 2018-10-22 | 036909C-JVD-TRN-00202 | 036909C-JVD-TRN-00202 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00202
036909C-1020-PDS-0500-2020 | Process Equipment Datasheet - 10-T-2020 - Light Fuel Oil Stripper | A | 2018-10-26 | IFR | OL1-2G30-2020 | PE | 2018-10-29 | 036909C-JVD-TRN-00238 | 036909C-JVD-TRN-00238 | IFR | 2018-11-12 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00238
036909C-1020-MSD-0011-2002 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | A | 2018-11-02 | IFA | OL1-2G74-2002 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1020-PDS-0900-2046 | Process Equipment Datasheet - 10-P-2046 A-B - Heavy Fuel Oil Pumps | A | 2018-11-06 | IFR | OL1-2G30-2046 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00285
036909C-1020-PDS-0600-2015 | Process Equipment Datasheet - 10-E-2008 A-C - LS2 Steam Generators | A | 2018-11-09 | IFR | OL1-2G30-2015 | PE | 2018-11-09 | 036909C-JVD-TRN-00305 | 036909C-JVD-TRN-00305 | IFR | 2018-11-23 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00305
036909C-1019-SP-1013-1950 | Mechanical Equipment Datasheet - Decoking Air Compressor Package | C | 2018-10-31 | IFQ | OL1-2M03-1950 | ME | 2018-11-01 | 036909C-JVD-TRN-00261 | 036909C-JVD-TRN-00261 | IFI |  | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00261
036909C-1020-PDS-4200-2036 | Process Equipment Datasheet - 10-X-2036 - Quench Fitting | A | 2018-11-19 | IFR | OL1-2G30-2036 | PE | 2018-11-20 | 036909C-JVD-TRN-00338 | 036909C-JVD-TRN-00338 | IFR | 2018-12-04 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00338
036909C-1020-PDS-0600-2026 | Process Equipment Datasheet - 10-E-2026 - FO Product Cooler | A | 2018-11-08 | IFR | OL1-2G30-2026 | PE | 2018-11-09 | 036909C-JVD-TRN-00298 | 036909C-JVD-TRN-00298 | IFR | 2018-11-23 | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-PE-00298
036909C-1020-MSD-0011-2001 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | A | 2018-11-02 | IFA | OL1-2G74-2001 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1020-PDS-0600-2048 | Process Equipment Datasheet - 10-E-2048 - Heavy Fuel Oil Product Cooler | A | 2018-11-08 | IFR | OL1-2G30-2048 | PE | 2018-11-09 | 036909C-JVD-TRN-00298 | 036909C-JVD-TRN-00298 | IFR | 2018-11-23 | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-PE-00298
036909C-1019-MSD-0011-1901 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | A | 2018-11-02 | IFA | OL1-2G74-1901 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1019-MSD-0011-1902 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | A | 2018-11-02 | IFA | OL1-2G74-1902 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1020-PDS-0900-2024 | Process Equipment Datasheet - 10-P-2026 A-B - Light Fuel Oil Pumps | A | 2018-11-06 | IFR | OL1-2G30-2024 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00285
036909C-1012-SP-1040-2005 | Particular Technical Specification for Furnace ID Fans | A | 2018-11-01 | IFQ | OL1-2M57-2005 | ME | 2018-11-05 | 036909C-JVD-TRN-00269 | 036909C-JVD-TRN-00269 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00269
036909C-1012-PDS-0853-1212 | Process Equipment Datasheet - 10-M-1200 1600 - USC 132U Attemperator | A | 2018-11-14 | IFR | OL1-2G30-1212 | PE | 2018-11-16 | 036909C-JVD-TRN-00330 | 036909C-JVD-TRN-00330 | IFR | 2018-11-30 | 2018-12-13 | R1-No comments | TPSK-LSPA1-T-PE-00330
036909C-1012-PDS-0191-1206 | Process Equipment Datasheet - 10-H-1200 - 1600 - USC 132U Burner | A | 2018-10-26 | IFR | OL1-2G30-1206 | PE | 2018-10-30 | 036909C-JVD-TRN-00241 | 036909C-JVD-TRN-00241 | IFR | 2018-11-12 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00241
036909C-1012-PDS-0117-1202 | Anticipated Operating Conditions - 10-H-1200/1600 - USC 132U Liquid Cracking Furnace | 0 | 2018-10-24 | IFI | OL1-2G30-1202 | PE | 2018-10-24 | 036909C-JVD-TRN-00224 | 036909C-JVD-TRN-00224 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00224
036909C-1012-PDS-0117-1205 | Process Equipment Datasheet - 10-H-1200/1600 - API Fired Heater Process Datasheet | A | 2019-02-05 | IFR | OL1-2G30-1205 | PE | 2019-02-06 | 036909C-JVD-TRN-00814 | 036909C-JVD-TRN-00814 | IFR | 2019-02-20 |  | Transmitted | TPSK-LSPA1-T-PE-00814
036909C-1012-MSD-0011-1201 | Material Selection Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | A | 2018-11-02 | IFA | OL1-2G74-1201 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1012-PDS-0117-1201 | Process Equipment Datasheet - 10-H-1200 - 132U Cracking Furnace Yields | A | 2018-10-15 | IFR | OL1-2G30-1201 | PE | 2018-10-22 | 036909C-JVD-TRN-00204 | 036909C-JVD-TRN-00204 | IFR | 2018-11-05 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00204
036909C-1012-MR-1040-2005 | Material Requisition for Furnace ID Fans | A | 2018-11-01 | IFQ | OL1-2M55-2005 | ME | 2018-11-05 | 036909C-JVD-TRN-00269 | 036909C-JVD-TRN-00269 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00269
036909C-1012-PDS-0630-1208 | Process Equipment Datasheet - 10-E-1200A-F - 10-E-1600A-F - USC 132U SLE Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1208 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237
036909C-1012-DW-0125-2302 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-2302 | ME | 2018-11-08 | 036909C-JVD-TRN-00289 | 036909C-JVD-TRN-00289 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00289
036909C-1012-JSS-0191-2009 | Project Specification for Furnace Burners | A | 2018-10-15 | IFR | OL1-2M92-2009 | ME | 2018-10-25 | 036909C-JVD-TRN-00231 | 036909C-JVD-TRN-00231 | IFR | 2018-11-08 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00231
036909C-1012-DW-0117-2001 | USC 132U Cracking Furnace General Arrangement Cross Section Elevation | A | 2018-11-15 | IFR | OL1-2M06-2001 | ME | 2018-11-16 | 036909C-JVD-TRN-00328 | 036909C-JVD-TRN-00328 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-ME-00328
036909C-1012-DW-0117-2002 | USC 132U Cracking Furnace General Arrangement Longitudinal Elevation | A | 2018-11-15 | IFR | OL1-2M06-2002 | ME | 2018-11-16 | 036909C-JVD-TRN-00328 | 036909C-JVD-TRN-00328 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-ME-00328
036909C-1011-PDS-0191-1106 | Process Equipment Datasheet - 10-H-1100 - USC 36M Burner | A | 2018-10-26 | IFR | OL1-2G30-1106 | PE | 2018-10-30 | 036909C-JVD-TRN-00241 | 036909C-JVD-TRN-00241 | IFR | 2018-11-12 | 2018-11-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00241
036909C-1011-PDS-0630-1108 | Process Equipment Datasheet - 10-E-1100A1 - F6 - USC 36M USX Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1108 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237
036909C-1011-PDS-0853-1112 | Process Equipment Datasheet - 10-M-1100 - USC 36M Attemperator | A | 2018-11-14 | IFR | OL1-2G30-1112 | PE | 2018-11-16 | 036909C-JVD-TRN-00330 | 036909C-JVD-TRN-00330 | IFR | 2018-11-30 | 2018-12-13 | R1-No comments | TPSK-LSPA1-T-PE-00330
036909C-1011-PDS-0117-1105 | Process Equipment Datasheet - 10-H-1100 - API Fired Heater Process Datasheet | A | 2019-02-05 | IFR | OL1-2G30-1105 | PE | 2019-02-06 | 036909C-JVD-TRN-00814 | 036909C-JVD-TRN-00814 | IFR | 2019-02-20 |  | Transmitted | TPSK-LSPA1-T-PE-00814
036909C-1012-DW-0125-2301 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-2301 | ME | 2018-11-08 | 036909C-JVD-TRN-00289 | 036909C-JVD-TRN-00289 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00289
036909C-1011-PDS-0117-1102 | Anticipated Operating Conditions - 10-H-1100 - USC 36M Gas Cracking Furnace | 0 | 2018-10-24 | IFI | OL1-2G30-1102 | PE | 2018-10-24 | 036909C-JVD-TRN-00224 | 036909C-JVD-TRN-00224 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00224
036909C-1011-DW-0125-1301 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-1301 | ME | 2018-11-07 | 036909C-JVD-TRN-00286 | 036909C-JVD-TRN-00286 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00286
036909C-1011-DW-0125-1302 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-1302 | ME | 2018-11-07 | 036909C-JVD-TRN-00286 | 036909C-JVD-TRN-00286 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00286
036909C-1011-MSD-0011-1101 | Material Selection Diagram - Olefins Unit 10 - 11 - Furnaces - Gas Cracking Furnace | A | 2018-11-02 | IFA | OL1-2G74-1101 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1011-PDS-0117-1101 | Process Equipment Datasheet - 10-H-1100 - 36M Cracking Furnace Yields | A | 2018-10-15 | IFR | OL1-2G30-1101 | PE | 2018-10-22 | 036909C-JVD-TRN-00204 | 036909C-JVD-TRN-00204 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00204
036909C-1011-DW-0117-1002 | USC 36M Recycle Furnace General Arrangement Longitudinal Elevation | A | 2018-11-15 | IFR | OL1-2M06-1002 | ME | 2018-11-16 | 036909C-JVD-TRN-00327 | 036909C-JVD-TRN-00327 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-ME-00327
036909C-1011-DW-0117-1001 | USC 36M Recycle Furnace General Arrangement Cross Section Elevation | A | 2018-11-15 | IFR | OL1-2M06-1001 | ME | 2018-11-16 | 036909C-JVD-TRN-00327 | 036909C-JVD-TRN-00327 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-ME-00327
036909C-1010-PDS-0600-1003 | Process Equipment Datasheet - 10-E-1001 - LPG Steam Vaporizer | A | 2018-10-15 | IFR | OL1-2G30-1003 | PE | 2018-10-16 | 036909C-JVD-TRN-00179 | 036909C-JVD-TRN-00179 | IFR | 2018-10-30 | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00179
036909C-1010-PDS-0800-1000 | Process Equipment Datasheet - 10-D-1000 - LPG Drum | A | 2018-10-25 | IFR | OL1-2G30-1000 | PE | 2018-10-25 | 036909C-JVD-TRN-00227 | 036909C-JVD-TRN-00227 | IFR | 2018-11-08 | 2018-12-05 | R1-No comments | TPSK-LSPA1-T-PE-00227
036909C-1010-PDS-0600-1051 | Process Equipment Datasheet - 10-E-1050 - C2 Feed Superheater | A | 2018-10-18 | IFR | OL1-2G30-1051 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00206
036909C-1010-MSD-0011-1003 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | A | 2018-11-02 | IFA | OL1-2G74-1003 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1010-MSD-0011-1001 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | A | 2018-11-02 | IFA | OL1-2G74-1001 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1010-PDS-0600-1001 | Process Equipment Datasheet - 10-E-1000 - LPG Vaporizer | A | 2018-10-15 | IFR | OL1-2G30-1001 | PE | 2018-10-15 | 036909C-JVD-TRN-00176 | 036909C-JVD-TRN-00176 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00176
036909C-1010-PDS-0600-1015 | Process Equipment Datasheet - 10-E-1015 - LPG Superheater | A | 2018-10-15 | IFR | OL1-2G30-1015 | PE | 2018-10-15 | 036909C-JVD-TRN-00176 | 036909C-JVD-TRN-00176 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00176
036909C-1000-MSD-0011-0001 | Material Selection Diagram - Olefins Unit 10 - Legend & Notes | A | 2018-11-02 | IFA | OL1-2G74-0001 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1012-PDS-0853-1212 | Process Equipment Datasheet - 10-M-1200-1600 - USC 132U Attemperator | B | 2019-01-24 | IFD | OL1-2G30-1212 | PE | 2019-01-29 | 036909C-JVD-TRN-00752 | 036909C-JVD-TRN-00752 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00752
036909C-1011-PDS-0853-1112 | Process Equipment Datasheet - 10-M-1100 - USC 36M Attemperator | B | 2019-01-24 | IFD | OL1-2G30-1112 | PE | 2019-01-29 | 036909C-JVD-TRN-00752 | 036909C-JVD-TRN-00752 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00752
036909C-1028-SP-0910-2816 | Mechanical Equipment Datasheet - Propylene Refrig Recovery Pump | A | 2018-12-18 | IFQ | OL1-2M03-2816 | ME | 2018-12-20 | 036909C-JVD-TRN-00543 | 036909C-JVD-TRN-00543 | IFR | 2019-01-02 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-ME-00543
036909C-1055-SP-0910-5501 | Mechanical Equipment Datasheet - Hot Blowdown Pumps | A | 2019-01-08 | IFQ | OL1-2M03-5501 | ME | 2019-01-10 | 036909C-JVD-TRN-00616 | 036909C-JVD-TRN-00616 | IFR | 2019-01-23 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00616
036909C-1026-SP-0910-2669 | Mechanical Equipment Datasheet - Debutanizer Bottoms Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2669 | ME | 2018-12-04 | 036909C-JVD-TRN-00421 | 036909C-JVD-TRN-00421 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00421
036909C-1023-SP-0910-2391 | Mechanical Equipment Datasheet - Caustic Drain Drum Pump | A | 2018-12-13 | IFQ | OL1-2M03-2391 | ME | 2018-12-17 | 036909C-JVD-TRN-00511 | 036909C-JVD-TRN-00511 | IFR | 2018-12-31 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00511
036909C-1023-SP-0910-2325 | Mechanical Equipment Datasheet for 10 Caustic Makeup Pumps | A | 2018-12-28 | IFQ | OL1-2M03-2325 | ME | 2019-01-03 | 036909C-JVD-TRN-00580 | 036909C-JVD-TRN-00580 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00580
036909C-1021-PDS-0900-2105 | Process Equipment Datasheet - 10-P-2105 A-B - Quench Oil Reflux Pumps | B | 2019-01-07 | IFD | OL1-2G30-2105 | PE | 2019-01-07 | 036909C-JVD-TRN-00603 | 036909C-JVD-TRN-00603 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00603
036909C-1023-PDS-4200-2301 | Process Equipment Datasheet - 10-X-2300 - Caustic Dilution Mixer | C | 2019-01-04 | IFD | OL1-2G30-2301 | PE | 2019-01-07 | 036909C-JVD-TRN-00600 | 036909C-JVD-TRN-00600 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00600
036909C-1021-PDS-0600-2147 | Process Equipment Datasheet - 10-E-2146 - DSG Feed Heater | B | 2019-01-07 | IFD | OL1-2G30-2147 | PE | 2019-01-07 | 036909C-JVD-TRN-00605 | 036909C-JVD-TRN-00605 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00605
036909C-1021-PDS-0600-2145 | Process Equipment Datasheet - 10-E-2145 - Process Water Stripper Reboiler | B | 2019-01-07 | IFD | OL1-2G30-2145 | PE | 2019-01-07 | 036909C-JVD-TRN-00605 | 036909C-JVD-TRN-00605 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00605
036909C-1021-PDS-0900-2191 | Process Equipment Datasheet - 10-P-2190 - Quench Water Drain Drum Pump | B | 2019-01-07 | IFD | OL1-2G30-2191 | PE | 2019-01-07 | 036909C-JVD-TRN-00603 | 036909C-JVD-TRN-00603 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00603
036909C-1020-PDS-0500-2040 | Process Equipment Datasheet - 10-T-2040 - Heavy Fuel Oil Stripper | A | 2018-10-11 | IFR | OL1-2G30-2040 | PE | 2018-10-12 | 036909C-JVD-TRN-00162 | 036909C-JVD-TRN-00162 | IFR | 2018-10-26 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00162
036909C-1028-PDS-0900-2816 | Process Equipment Datasheet - 10-P-2815 - Propylene Refrig Recovery Pump | B | 2018-12-10 | IFD | OL1-2G30-2816 | PE | 2018-12-13 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00481
036909C-1021-PDS-0500-2120 | Process Equipment Datasheet - 10-T-2120 - Distillate Stripper | B | 2018-11-29 | IFD | OL1-2G30-2120 | PE | 2018-11-29 | 036909C-JVD-TRN-00401 | 036909C-JVD-TRN-00401 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00401
036909C-1020-SP-0510-2040 | Mechanical Equipment Data Sheet - Heavy Fuel Oil Stripper | A | 2018-11-28 | IFQ | OL1-2M03-2040 | ME | 2018-11-28 | 036909C-JVD-TRN-00387 | 036909C-JVD-TRN-00387 | IFR | 2018-12-12 | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-ME-00387
036909C-1020-SP-0510-2040 | Mechanical Equipment Data Sheet - Heavy Fuel Oil Stripper | B | 2018-12-04 | IFQ | OL1-2M03-2040 | ME | 2018-12-05 | 036909C-JVD-TRN-00418 | 036909C-JVD-TRN-00418 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00418
036909C-1023-PDS-0840-2307 | Process Equipment Datasheet - 10-F-2306 A-B - Weak Caustic Circulating Filters | B | 2018-12-11 | IFD | OL1-2G30-2307 | PE | 2018-12-13 | 036909C-JVD-TRN-00493 | 036909C-JVD-TRN-00493 | IFI |  | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00493
036909C-1055-PDS-0900-5566 | Process Equipment Datasheet - 10-P-5565 A-B - Polyolefins Flare Knock-out Pumps | A | 2019-01-09 | IFR | OL1-2G30-5566 | PE | 2019-01-10 | 036909C-JVD-TRN-00623 | 036909C-JVD-TRN-00623 | IFR | 2019-01-23 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00623
036909C-1055-PDS-0800-5514 | Process Equipment Datasheet - 10-D-5513 - Methanol Vaporizer Cond Pot | A | 2019-01-08 | IFR | OL1-2G30-5514 | PE | 2019-01-10 | 036909C-JVD-TRN-00614 | 036909C-JVD-TRN-00614 | IFR | 2019-01-23 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00614
036909C-1056-PDS-0900-5622 | Process Equipment Datasheet - 10-P-5620 A-C - Olefins Holding Basin Pumps | A | 2019-01-10 | IFR | OL1-2G30-5622 | PE | 2019-01-11 | 036909C-JVD-TRN-00635 | 036909C-JVD-TRN-00635 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00635
036909C-1055-PDS-0600-5511 | Process Equipment Datasheet - 10-E-5510 - Cold Flare Blowdown Vaporizer | B | 2019-01-09 | IFR | OL1-2G30-5511 | PE | 2019-01-11 | 036909C-JVD-TRN-00626 | 036909C-JVD-TRN-00626 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00626
036909C-1055-PDS-0600-5512 | Process Equipment Datasheet - 10-E-5512 - Cold Flare Superheater | B | 2019-01-09 | IFR | OL1-2G30-5512 | PE | 2019-01-11 | 036909C-JVD-TRN-00626 | 036909C-JVD-TRN-00626 | IFR | 2019-01-24 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00626
036909C-1053-PDS-0300-5355 | Process Equipment Datasheet - 10-PK-5355 - Side Stream Filter Pkg | C | 2019-01-03 | IFD | OL1-2G30-5355 | PE | 2019-01-08 | 036909C-JVD-TRN-00611 | 036909C-JVD-TRN-00611 | IFI |  | 2019-01-24 | A1-Approved without comments | TPSK-LSPA1-T-PE-00611
036909C-1053-SP-0910-5361 | Mechanical Data Sheet - CTU Cooling Water Pumps | D | 2019-01-09 | IFQ | OL1-2M03-5361 | ME | 2019-01-11 | 036909C-JVD-TRN-00627 | 036909C-JVD-TRN-00627 | IFI |  | 2019-01-31 | R1-No comments | TPSK-LSPA1-T-ME-00627
036909C-1029-PDS-0800-2932 | Process Equipment Datasheet - 10-D-2930 - Methanol Drum | A | 2019-01-10 | IFR | OL1-2G30-2932 | PE | 2019-01-14 | 036909C-JVD-TRN-00644 | 036909C-JVD-TRN-00644 | IFR | 2019-01-28 | 2019-01-31 | R1-No comments | TPSK-LSPA-1-T-PE-00644
036909C-1053-PDS-0900-5371 | Process Equipment Datasheet - 10-P-5370 A-B - CW Filter Backwash Pumps | A | 2019-01-09 | IFR | OL1-2G30-5371 | PE | 2019-01-10 | 036909C-JVD-TRN-00623 | 036909C-JVD-TRN-00623 | IFR | 2019-01-23 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00623
036909C-1055-PDS-0600-5513 | Process Equipment Datasheet - 10-E-5513 - Methanol Vaporizer | B | 2019-01-09 | IFR | OL1-2G30-5513 | PE | 2019-01-11 | 036909C-JVD-TRN-00626 | 036909C-JVD-TRN-00626 | IFR | 2019-01-24 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00626
036909C-1028-PDS-0900-2801 | Process Equipment Datasheet - 10-P-2805 A-B - Propylene Product Pumps | B | 2019-01-10 | IFD | OL1-2G30-2801 | PE | 2019-01-14 | 036909C-JVD-TRN-00649 | 036909C-JVD-TRN-00649 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00649
036909C-1028-PDS-0800-2854 | Process Equipment Datasheet - 10-D-2855 - C2R Surge Drum | B | 2019-01-09 | IFD | OL1-2G30-2854 | PE | 2019-01-10 | 036909C-JVD-TRN-00621 | 036909C-JVD-TRN-00621 | IFI |  | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00621
036909C-1024-TDS-0610-2455 | Mechanical Equipment Data Sheet - 10-E-2455 AB - LP Depropanizer Reboilers | A | 2019-01-02 | IFQ | OL1-2M03-2455 | ME | 2019-01-07 | 036909C-JVD-TRN-00584 | 036909C-JVD-TRN-00584 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00584
036909C-1026-PDS-0900-2647 | Process Equipment Datasheet - 10-P-2647 - HP Propylene - Off Spec Pumps | B | 2019-01-10 | IFD | OL1-2G30-2647 | PE | 2019-01-14 | 036909C-JVD-TRN-00649 | 036909C-JVD-TRN-00649 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00649
036909C-1028-PDS-0800-2865 | Process Equipment Datasheet - 10-D-2865 - C2R Drain Drum | B | 2019-01-10 | IFD | OL1-2G30-2865 | PE | 2019-01-11 | 036909C-JVD-TRN-00633 | 036909C-JVD-TRN-00633 | IFI |  | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00633
036909C-1023-PDS-0800-2331 | Process Equipment Datasheet - 10-D-2330 - Spent Caustic Stripper Ovhd Drum | A | 2018-10-12 | IFR | OL1-2G30-2331 | PE | 2018-10-15 | 036909C-JVD-TRN-00175 | 036909C-JVD-TRN-00175 | IFR | 2018-10-29 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00175
036909C-1022-PDS-0800-2240 | Process Equipment Datasheet - 10-D-2240 - CG 4th Stage Suction Drum | A | 2018-10-12 | IFR | OL1-2G30-2240 | PE | 2018-10-15 | 036909C-JVD-TRN-00175 | 036909C-JVD-TRN-00175 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00175
036909C-1023-PDS-0800-2316 | Process Equipment Datasheet - 10-D-2316 - Spent Caustic Degassing Drum | A | 2018-10-12 | IFR | OL1-2G30-2316 | PE | 2018-10-15 | 036909C-JVD-TRN-00175 | 036909C-JVD-TRN-00175 | IFR | 2018-10-29 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00175
036909C-1023-PDS-0900-2302 | Process Equipment Datasheet - 10-P-2302 A-B - Strong Caustic Circulating Pumps | A | 2018-10-12 | IFR | OL1-2G30-2302 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00174
036909C-1023-PDS-0900-2311 | Process Equipment Datasheet - 10-P-2310 A-B - Wash Oil Circulating Pumps | A | 2018-10-12 | IFR | OL1-2G30-2311 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00174
036909C-1023-PDS-0900-2304 | Process Equipment Datasheet - 10-P-2304 - Intermediate Caustic Circulating Pump | A | 2018-10-12 | IFR | OL1-2G30-2304 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00174
036909C-1026-PDS-0900-2663 | Process Equipment Datasheet - 10-P-2660 A-B - Debutanizer Reflux - Product Pumps | C | 2019-01-10 | IFD | OL1-2G30-2663 | PE | 2019-01-14 | 036909C-JVD-TRN-00648 | 036909C-JVD-TRN-00648 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00648
036909C-1028-PDS-0900-2816 | Process Equipment Datasheet - 10-P-2815 - Propylene Refrig Recovery Pump | C | 2019-01-10 | IFD | OL1-2G30-2816 | PE | 2019-01-14 | 036909C-JVD-TRN-00648 | 036909C-JVD-TRN-00648 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00648
036909C-1020-PDS-0900-2024 | Process Equipment Datasheet - 10-P-2026 A-B - Light Fuel Oil Pumps | B | 2019-01-10 | IFD | OL1-2G30-2024 | PE | 2019-01-14 | 036909C-JVD-TRN-00648 | 036909C-JVD-TRN-00648 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00648
036909C-1020-PDS-0900-2046 | Process Equipment Datasheet - 10-P-2046 A-B - Heavy Fuel Oil Pumps | B | 2019-01-10 | IFD | OL1-2G30-2046 | PE | 2019-01-14 | 036909C-JVD-TRN-00648 | 036909C-JVD-TRN-00648 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00648
036909C-1059-PDS-2500-5900 | Process Equipment Datasheet - 10-TK-5900 - Sulfuric Acid Tank | A | 2018-11-16 | IFR | OL1-2G30-5900 | PE | 2018-11-26 | 036909C-JVD-TRN-00364 | 036909C-JVD-TRN-00364 | IFR | 2018-12-10 | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-00364
036909C-1020-SP-0840-2049 | Mechanical Equipment Datasheet -Heavy Fuel Oil Filters | A | 2019-01-10 | IFQ | OL1-2M03-2049 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639
036909C-1021-SP-0840-2138 | Mechanical Equipment Datasheet - Process Water Feed Filters | A | 2019-01-10 | IFQ | OL1-2M03-2138 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639
036909C-1021-SP-0840-2104 | Mechanical Equipment Datasheet - Quench Oil Reflux Filter | A | 2019-01-10 | IFQ | OL1-2M03-2104 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639
036909C-1020-SP-0840-2010 | Mechanical Equipment Data sheet - Quench Oil Filter | A | 2019-01-10 | IFQ | OL1-2M03-2010 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639
036909C-1020-SP-0840-2025 | Mechanical Equipment Datasheet - Cracker Bottoms Product Filter | A | 2019-01-10 | IFQ | OL1-2M03-2025 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639
036909C-1020-SP-0840-2028 | Mechanical Equipment Datasheet- Fo Pump Purge Oil Filter | A | 2019-01-10 | IFQ | OL1-2M03-2028 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639
036909C-1020-SP-0840-2014 | Mechanical Equipment Datasheet - QO Pump Purge Oil Filter | A | 2019-01-10 | IFQ | OL1-2M03-2014 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639
036909C-1023-SP-0840-2319 | Mechanical Equipment Datasheet - Spent Caustic Pump Discharge Filters | A | 2019-01-10 | IFQ | OL1-2M03-2319 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639
036909C-1056-SP-0840-5612 | Mechanical Equipment Datasheet - Hydroblast Filter | A | 2019-01-10 | IFQ | OL1-2M03-5612 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639
036909C-1023-SP-0840-2307 | Mechanical Equipment Datasheet - Weak Caustic Circulating Filters | A | 2019-01-10 | IFQ | OL1-2M03-2307 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639
036909C-1023-SP-0840-2314 | Mechanical Equipment Datasheet - Wash Oil Circulation Filter | A | 2019-01-10 | IFQ | OL1-2M03-2314 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639
036909C-1028-SP-0810-2854 | Mechanical Equipment Data Sheet - C2R Surge Drum | A | 2019-01-10 | IFQ | OL1-2M03-2854 | ME | 2019-01-11 | 036909C-JVD-TRN-00638 | 036909C-JVD-TRN-00638 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00638
036909C-1024-PDS-0800-2480 | Process Equipment Datasheet - 10-D-2480 - CG Secondary Dryer | A | 2018-11-28 | IFR | OL1-2G30-2480 | PE | 2018-11-28 | 036909C-JVD-TRN-00386 | 036909C-JVD-TRN-00386 | IFR | 2018-12-12 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00386
036909C-1028-PDS-0800-2865 | Process Equipment Datasheet - 10-D-2865 - C2R Drain Drum | A | 2018-12-06 | IFR | OL1-2G30-2865 | PE | 2018-12-07 | 036909C-JVD-TRN-00445 | 036909C-JVD-TRN-00445 | IFR | 2018-12-20 | 2019-01-10 | R1-No comments | TPSK-LSPA1-T-PE-00445
036909C-1028-PDS-0800-2815 | Process Equipment Datasheet - 10-D-2815 - C3R Drain Drum | A | 2018-12-04 | IFR | OL1-2G30-2815 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00439
036909C-1055-SP-0810-5510 | Mechanical Equipment Data Sheet - Cold Flare Drum | A | 2019-01-05 | IFQ | OL1-2M03-5510 | ME | 2019-01-11 | 036909C-JVD-TRN-00629 | 036909C-JVD-TRN-00629 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00629
036909C-1052-MSD-0011-5201 | Material Selection Diagram - Olefins Unit 10 - 52 Fuel System - Fuel Gas System | A | 2018-12-20 | IFA | OL1-2G74-5201 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1050-MSD-0011-5001 | Material Selection Diagram - Olefins Unit 10 - 50 Water Systems - Treated -Potable and Demin Water Systems | A | 2018-12-20 | IFA | OL1-2G74-5001 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1051-MSD-0011-5102 | Material Selection Diagram - Olefins Unit 10 - 51 BFW Steam Cond Systems - Condensate and Boiler Feedwater Systems | A | 2018-12-20 | IFA | OL1-2G74-5102 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1055-MSD-0011-5512 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - Enclosed Ground | A | 2018-12-20 | IFA | OL1-2G74-5512 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1059-MSD-0011-5901 | Material Selection Diagram - Olefins Unit 10 - 59 Utilities Aux - Chemical Storage | A | 2018-12-20 | IFA | OL1-2G74-5901 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1054-MSD-0011-5401 | Material Selection Diagram - Olefins Unit 10 - 54 Air and Nitrogen System - Plant Air - Instrument Air and Nitrogen Systems | A | 2018-12-20 | IFA | OL1-2G74-5401 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1055-MSD-0011-5502 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - Process Vent Gas Collection | A | 2018-12-20 | IFA | OL1-2G74-5502 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608
036909C-1025-SP-0810-2555 | Mechanical Equipment Data Sheet - Expander Discharge Drum | A | 2018-12-13 | IFQ | OL1-2M03-2555 | ME | 2019-01-08 | 036909C-JVD-TRN-00607 | 036909C-JVD-TRN-00607 | IFR | 2019-01-22 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-ME-00607
036909C-1028-SP-0810-2865 | Mechanical Equipment Data Sheet - C2R Drain Drum | A | 2018-12-18 | IFQ | OL1-2M03-2865 | ME | 2019-01-08 | 036909C-JVD-TRN-00607 | 036909C-JVD-TRN-00607 | IFR | 2019-01-22 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-ME-00607
036909C-1020-PDS-0840-2010 | Process Equipment Datasheet - 10-F-2008 A-C - Quench Oil Filter | B | 2019-01-07 | IFD | OL1-2G30-2010 | PE | 2019-01-07 | 036909C-JVD-TRN-00606 | 036909C-JVD-TRN-00606 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00606
036909C-1020-PDS-0840-2014 | Process Equipment Datasheet - 10-F-2009 A-B - QO Pump Purge Oil Filter | B | 2019-01-07 | IFD | OL1-2G30-2014 | PE | 2019-01-07 | 036909C-JVD-TRN-00606 | 036909C-JVD-TRN-00606 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00606
036909C-1021-PDS-0600-2147 | Process Equipment Datasheet - 10-E-2146 - DSG Feed Heater | A | 2018-10-17 | IFR | OL1-2G30-2147 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00194
036909C-1021-PDS-0600-2145 | Process Equipment Datasheet - 10-E-2145 - Process Water Stripper Reboiler | A | 2018-10-17 | IFR | OL1-2G30-2145 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00194
036909C-1022-PDS-0900-2212 | Process Equipment Datasheet - 10-P-2210 A-B - CG 1st Stage Condensate Pumps | B | 2019-01-02 | IFD | OL1-2G30-2212 | PE | 2019-01-07 | 036909C-JVD-TRN-00593 | 036909C-JVD-TRN-00593 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00593
036909C-1053-PDS-0900-5361 | Process Equipment Datasheet - 10-P-5360 A-C - CTU Cooling Water Pumps | D | 2019-01-03 | IFD | OL1-2G30-5361 | PE | 2019-01-07 | 036909C-JVD-TRN-00593 | 036909C-JVD-TRN-00593 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00593
036909C-1022-PDS-0900-2222 | Process Equipment Datasheet - 10-P-2220 A-B - CG 2nd Stage Condensed HC Pumps | B | 2019-01-02 | IFD | OL1-2G30-2222 | PE | 2019-01-07 | 036909C-JVD-TRN-00593 | 036909C-JVD-TRN-00593 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00593
036909C-1021-SP-0510-2100 | Mechanical Equipment Data Sheet - Quench Water Tower | A | 2018-12-06 | IFQ | OL1-2M03-2100 | ME | 2018-12-07 | 036909C-JVD-TRN-00443 | 036909C-JVD-TRN-00443 | IFR | 2018-12-20 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00443
036909C-1021-SP-0510-2140 | Mechanical Equipment Data Sheet - Process Water Stripper | A | 2018-12-05 | IFQ | OL1-2M03-2140 | ME | 2018-12-10 | 036909C-JVD-TRN-00458 | 036909C-JVD-TRN-00458 | IFR | 2018-12-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00458
036909C-1020-SP-0510-2020 | Mechanical Equipment Data Sheet - Light Fuel Oil Stripper | A | 2018-12-07 | IFQ | OL1-2M03-2020 | ME | 2018-12-10 | 036909C-JVD-TRN-00447 | 036909C-JVD-TRN-00447 | IFR | 2018-12-21 | 2019-01-27 | R1-No comments | TPSK-LSPA1-T-ME-00447
036909C-1020-SP-0510-2000 | Mechanical Equipment Data Sheet - Quench Oil Tower | A | 2018-12-04 | IFQ | OL1-2M03-2000 | ME | 2018-12-04 | 036909C-JVD-TRN-00420 | 036909C-JVD-TRN-00420 | IFR | 2018-12-18 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00420
036909C-1020-SP-0910-2046 | Mechanical Equipment Datasheet - Heavy Fuel Oil Pumps | A | 2018-11-23 | IFQ | OL1-2M03-2046 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457 | IFR | 2018-12-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00457
036909C-1020-SP-0910-2024 | Mechanical Equipment Datasheet - Light Fuel Oil Pumps | A | 2018-11-23 | IFQ | OL1-2M03-2024 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457 | IFR | 2018-12-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00457
036909C-1029-PDS-2600-2902 | Process Equipment Datasheet - 10-PK-2902 - Emulsion Breaker Injection Pkg | A | 2018-12-18 | IFR | OL1-2G30-2902 | PE | 2018-12-20 | 036909C-JVD-TRN-00533 | 036909C-JVD-TRN-00533 | IFR | 2019-01-02 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00533
036909C-1029-PDS-2600-2900 | Process Equipment Datasheet - 10-PK-2900 - pH Ctrl - Corrosion Inhibitor Inj Pkg | A | 2018-12-18 | IFR | OL1-2G30-2900 | PE | 2018-12-20 | 036909C-JVD-TRN-00532 | 036909C-JVD-TRN-00532 | IFR | 2019-01-02 | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00532
036909C-1029-PDS-2600-2920 | Process Equipment Datasheet - 10-PK-2920 - Polymerization Inhibitor Inj Pkg | A | 2018-12-18 | IFR | OL1-2G30-2920 | PE | 2018-12-20 | 036909C-JVD-TRN-00533 | 036909C-JVD-TRN-00533 | IFR | 2019-01-02 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00533
036909C-1051-SP-0810-5140 | Mechanical Equipment Data Sheet - Intermittent Blowdown Drum | A | 2018-12-18 | IFQ | OL1-2M03-5140 | ME | 2018-12-20 | 036909C-JVD-TRN-00548 | 036909C-JVD-TRN-00548 | IFR | 2019-01-02 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA-T-ME-00548
036909C-1029-PDS-2600-2940 | Process Equipment Datasheet - 10-PK-2940 - C4 Polymer Inhibitor Inj Pkg | A | 2018-12-18 | IFR | OL1-2G30-2940 | PE | 2018-12-20 | 036909C-JVD-TRN-00533 | 036909C-JVD-TRN-00533 | IFR | 2019-01-02 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00533
036909C-1029-PDS-2600-2904 | Process Equipment Datasheet - 10-PK-2904 - Process Water Stripper Chem Inj Pkg | A | 2018-12-18 | IFR | OL1-2G30-2904 | PE | 2018-12-20 | 036909C-JVD-TRN-00533 | 036909C-JVD-TRN-00533 | IFR | 2019-01-02 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00533
036909C-1029-PDS-2600-2912 | Process Equipment Datasheet - 10-PK-2912 - Caustic Tower Anti-Foulant Inj Pkg | A | 2018-12-18 | IFR | OL1-2G30-2912 | PE | 2018-12-20 | 036909C-JVD-TRN-00533 | 036909C-JVD-TRN-00533 | IFR | 2019-01-02 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00533
036909C-1029-PDS-2600-2906 | Process Equipment Datasheet - 10-PK-2906 - DSG Anti-Foulant Injection Pkg | A | 2018-12-18 | IFR | OL1-2G30-2906 | PE | 2018-12-20 | 036909C-JVD-TRN-00533 | 036909C-JVD-TRN-00533 | IFR | 2019-01-02 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00533
036909C-1028-SP-0810-2860 | Mechanical Equipment Data Sheet - C2R 1ST Stage Suction Drum | A | 2018-12-07 | IFQ | OL1-2M03-2860 | ME | 2018-12-20 | 036909C-JVD-TRN-00553 | 036909C-JVD-TRN-00553 | IFR | 2019-01-03 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00553
036909C-1025-SP-0510-2520 | Mechanical Equipment Data Sheet - Residue Gas Rectifier And Rectifier Reflux Drum | A | 2018-12-17 | IFQ | OL1-2M03-2520 | ME | 2018-12-20 | 036909C-JVD-TRN-00535 | 036909C-JVD-TRN-00535 | IFR | 2019-01-02 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00534
036909C-1024-PDS-0800-2435 | Process Equipment Datasheet - 10-D-2435 - Regen Gas Separator | A | 2018-12-20 | IFR | OL1-2G30-2435 | PE | 2018-12-20 | 036909C-JVD-TRN-00559 | 036909C-JVD-TRN-00559 | IFR | 2019-01-03 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00559
036909C-1024-PDS-0500-2450 | Process Equipment Datasheet - 10-T-2450 - LP Depropanizer | B | 2018-10-11 | IFD | OL1-2G30-2450 | PE | 2018-10-12 | 036909C-JVD-TRN-00167 | 036909C-JVD-TRN-00167 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00167
036909C-1025-PDS-0500-2580 | Process Equipment Datasheet - 10-T-2580 - C2 Tower | A | 2018-10-11 | IFR | OL1-2G30-2580 | PE | 2018-10-12 | 036909C-JVD-TRN-00162 | 036909C-JVD-TRN-00162 | IFR | 2018-10-26 | 2018-10-31 | R2-Comments as noted | TPSK-LSPA1-T-PE-00162
036909C-1023-PDS-4200-2313 | Process Equipment Datasheet - 10-X-2312 - Spent Wash Oil Mixer | B | 2018-12-17 | IFD | OL1-2G30-2313 | PE | 2018-12-20 | 036909C-JVD-TRN-00525 | 036909C-JVD-TRN-00525 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00525
036909C-1023-PDS-0900-2311 | Process Equipment Datasheet - 10-P-2310 A-B - Wash Oil Circulating Pumps | B | 2018-12-17 | IFD | OL1-2G30-2311 | PE | 2018-12-20 | 036909C-JVD-TRN-00524 | 036909C-JVD-TRN-00524 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00524
036909C-1023-PDS-0900-2325 | Process Equipment Datasheet - 10-P-2300 A-B - 10 Percent Caustic Makeup Pump | A | 2018-12-17 | IFR | OL1-2G30-2325 | PE | 2018-12-20 | 036909C-JVD-TRN-00526 | 036909C-JVD-TRN-00526 | IFR | 2019-01-02 | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00526
036909C-1023-PDS-4200-2315 | Process Equipment Datasheet - 10-X-2310 - Spent Caustic Mixer | B | 2018-12-17 | IFD | OL1-2G30-2315 | PE | 2018-12-20 | 036909C-JVD-TRN-00525 | 036909C-JVD-TRN-00525 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00525
036909C-1023-PDS-0900-2302 | Process Equipment Datasheet - 10-P-2302 A-B - Strong Caustic Circulating Pumps | B | 2018-12-17 | IFD | OL1-2G30-2302 | PE | 2018-12-20 | 036909C-JVD-TRN-00524 | 036909C-JVD-TRN-00524 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00524
036909C-1024-PDS-0500-2440 | Process Equipment Datasheet - 10-T-2440 - HP Depropanizer | B | 2018-10-11 | IFD | OL1-2G30-2440 | PE | 2018-10-12 | 036909C-JVD-TRN-00167 | 036909C-JVD-TRN-00167 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00167
036909C-1023-PDS-0900-2321 | Process Equipment Datasheet - 10-P-2320 A-B - Spent Caustic Pumps | B | 2019-01-02 | IFD | OL1-2G30-2321 | PE | 2019-01-07 | 036909C-JVD-TRN-00598 | 036909C-JVD-TRN-00598 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00598
036909C-1023-PDS-0900-2393 | Process Equipment Datasheet - 10-P-2392 - Spent Caustic Drain Drum Pump | B | 2019-01-02 | IFD | OL1-2G30-2393 | PE | 2019-01-07 | 036909C-JVD-TRN-00598 | 036909C-JVD-TRN-00598 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00598
036909C-1020-PDS-0500-2000 | Process Equipment Datasheet - 10-T-2000 - Quench Oil Tower | A | 2018-10-11 | IFR | OL1-2G30-2000 | PE | 2018-10-12 | 036909C-JVD-TRN-00162 | 036909C-JVD-TRN-00162 | IFR | 2018-10-26 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00162
036909C-1053-PDS-0300-5370 | Process Equipment Datasheet - 10-PIT-5370 - CW Filter Backwash Sump | A | 2018-12-18 | IFR | OL1-2G30-5370 | PE | 2018-12-20 | 036909C-JVD-TRN-00539 | 036909C-JVD-TRN-00539 | IFR | 2019-01-02 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA-1-T-PE-00539
036909C-1053-PDS-0300-5360 | Process Equipment Datasheet - 10-PIT-5360 A-C - CTU CW Pumps Sump | A | 2018-12-18 | IFR | OL1-2G30-5360 | PE | 2018-12-20 | 036909C-JVD-TRN-00539 | 036909C-JVD-TRN-00539 | IFR | 2019-01-02 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA-1-T-PE-00539
036909C-1053-PDS-0300-5351 | Process Equipment Datasheet - 10-PIT-5351 A-H - Olefins CW Pumps Sump | A | 2018-12-18 | IFR | OL1-2G30-5351 | PE | 2018-12-20 | 036909C-JVD-TRN-00539 | 036909C-JVD-TRN-00539 | IFR | 2019-01-02 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA-1-T-PE-00539
036909C-1020-PDS-0850-2092 | Process Equipment Datasheet - 10-EJ-2090 - Quench Oil Drain Sump Eductor | A | 2019-01-03 | IFD | OL1-2G30-2092 | PE | 2019-01-07 | 036909C-JVD-TRN-00595 | 036909C-JVD-TRN-00595 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00595
036909C-1021-PDS-0850-2192 | Process Equipment Datasheet - 10-EJ-2190 - Quench Water Drain Sump Eductor | A | 2019-01-03 | IFD | OL1-2G30-2192 | PE | 2019-01-07 | 036909C-JVD-TRN-00595 | 036909C-JVD-TRN-00595 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00595
036909C-1023-PDS-0850-2394 | Process Equipment Datasheet - 10-EJ-2392 - Spent Caustic Drain Sump Eductor | A | 2019-01-03 | IFD | OL1-2G30-2394 | PE | 2019-01-07 | 036909C-JVD-TRN-00595 | 036909C-JVD-TRN-00595 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00595
036909C-1027-PDS-0850-2792 | Process Equipment Datasheet - 10-EJ-2790 - Light Oil Drain Sump Eductor | A | 2019-01-03 | IFD | OL1-2G30-2792 | PE | 2019-01-07 | 036909C-JVD-TRN-00595 | 036909C-JVD-TRN-00595 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00595
036909C-1023-PDS-0850-2389 | Process Equipment Datasheet - 10-EJ-2390 - Caustic Drain Sump Eductor | A | 2019-01-03 | IFD | OL1-2G30-2389 | PE | 2019-01-07 | 036909C-JVD-TRN-00595 | 036909C-JVD-TRN-00595 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00595
036909C-1023-PDS-0850-2323 | Process Equipment Datasheet - 10-EJ-2322 - Skim Oil Sump Eductor | A | 2019-01-03 | IFD | OL1-2G30-2323 | PE | 2019-01-07 | 036909C-JVD-TRN-00595 | 036909C-JVD-TRN-00595 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00595
036909C-1026-SP-0910-2633 | Mechanical Equipment Data Sheet - Secondary Deeth Reflux Pumps | A | 2018-11-19 | IFQ | OL1-2M03-2633 | ME | 2018-12-13 | 036909C-JVD-TRN-00487 | 036909C-JVD-TRN-00487 | IFR | 2018-12-25 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-ME-00487
036909C-1025-SP-0810-2506 | Mechanical Equipment Data Sheet - Demeth Prefrac Feed Separator No 2 | A | 2018-12-07 | IFQ | OL1-2M03-2506 | ME | 2018-12-20 | 036909C-JVD-TRN-00551 | 036909C-JVD-TRN-00551 | IFR | 2019-01-03 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00551
036909C-1025-SP-0810-2508 | Mechanical Equipment Data Sheet - Demeth Prefrac Feed Separator No 3 | A | 2018-12-07 | IFQ | OL1-2M03-2508 | ME | 2018-12-20 | 036909C-JVD-TRN-00551 | 036909C-JVD-TRN-00551 | IFR | 2019-01-03 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00551
036909C-1025-SP-0810-2551 | Mechanical Equipment Data Sheet - Expander Suction Drum | A | 2018-12-11 | IFQ | OL1-2M03-2551 | ME | 2018-12-20 | 036909C-JVD-TRN-00551 | 036909C-JVD-TRN-00551 | IFR | 2019-01-03 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00551
036909C-1012-MR-0137-2010 | Material Requisition for MOVs | A | 2018-12-12 | IFQ | OL1-2M55-2010 | ME | 2018-12-18 | 036909C-JVD-TRN-00534 | 036909C-JVD-TRN-00534 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00534
036909C-1024-PDS-0600-2406 | Process Equipment Datasheet - 10-E-2405 - Gas Dryer Feed Chiller | B | 2018-12-17 | IFD | OL1-2G30-2406 | PE | 2018-12-20 | 036909C-JVD-TRN-00523 | 036909C-JVD-TRN-00523 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00523
036909C-1023-PDS-0600-2305 | Process Equipment Datasheet - 10-E-2305 - Caustic Tower Feed Heater | B | 2018-12-17 | IFD | OL1-2G30-2305 | PE | 2018-12-20 | 036909C-JVD-TRN-00523 | 036909C-JVD-TRN-00523 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00523
036909C-1024-PDS-0600-2455 | Process Equipment Datasheet - 10-E-2455 A-B - LP Depropanizer Reboilers | B | 2018-12-17 | IFD | OL1-2G30-2455 | PE | 2018-12-20 | 036909C-JVD-TRN-00523 | 036909C-JVD-TRN-00523 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00523
036909C-1024-PDS-0600-2412 | Process Equipment Datasheet - 10-E-2412 - HP Depropanizer Feed Chiller | B | 2018-12-17 | IFD | OL1-2G30-2412 | PE | 2018-12-20 | 036909C-JVD-TRN-00523 | 036909C-JVD-TRN-00523 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00523
036909C-1012-PDS-1543-1251 | Process Equipment Datasheet 10-MOV-1201 USC 132U Effluent MOV | A | 2018-12-12 | IFR | OL1-2G30-1251 | PE | 2018-12-20 | 036909C-JVD-TRN-00521 | 036909C-JVD-TRN-00521 | IFR | 2019-01-02 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-00521
036909C-1011-PDS-1543-1152 | Process Equipment Datasheet 10-MOV-1102A USC 36M Decoke Effluent MOV | A | 2018-12-12 | IFR | OL1-2G30-1152 | PE | 2018-12-20 | 036909C-JVD-TRN-00521 | 036909C-JVD-TRN-00521 | IFR | 2019-01-02 | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00521
036909C-1011-PDS-1543-1153 | Process Equipment Datasheet 10-MOV-1102B USC 36M Decoke Effluent Bypass MOV | A | 2018-12-12 | IFR | OL1-2G30-1153 | PE | 2018-12-20 | 036909C-JVD-TRN-00521 | 036909C-JVD-TRN-00521 | IFR | 2019-01-02 | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00521
036909C-1011-PDS-1543-1151 | Process Equipment Datasheet 10-MOV-1101 USC 36M Effluent MOV | A | 2018-12-12 | IFR | OL1-2G30-1151 | PE | 2018-12-20 | 036909C-JVD-TRN-00521 | 036909C-JVD-TRN-00521 | IFR | 2019-01-02 | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00521
036909C-1012-PDS-1543-1252 | Process Equipment Datasheet 10-MOV-1202A USC 132U Decoke Effluent MOV | A | 2018-12-12 | IFR | OL1-2G30-1252 | PE | 2018-12-20 | 036909C-JVD-TRN-00521 | 036909C-JVD-TRN-00521 | IFR | 2019-01-02 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-00521
036909C-1012-PDS-1543-1253 | Process Equipment Datasheet 10-MOV-1202B USC 132U Decoke Effluent Bypass MOV | A | 2018-12-12 | IFR | OL1-2G30-1253 | PE | 2018-12-20 | 036909C-JVD-TRN-00521 | 036909C-JVD-TRN-00521 | IFR | 2019-01-02 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-00521
036909C-1051-PDS-0900-5111 | Process Equipment Datasheet - 10-P-5112 A-B - Suspect Condensate Pumps | B | 2018-11-16 | IFD | OL1-2G30-5111 | PE | 2018-11-26 | 036909C-JVD-TRN-00363 | 036909C-JVD-TRN-00363 | IFI |  | 2018-12-13 | R1-No comments | TPSK-LSPA1-T-PE-00363
036909C-1051-PDS-0900-5121 | Process Equipment Datasheet - 10-P-5120 A-B - Raw Condensate Pumps | B | 2018-11-16 | IFD | OL1-2G30-5121 | PE | 2018-11-26 | 036909C-JVD-TRN-00363 | 036909C-JVD-TRN-00363 | IFI |  | 2018-12-13 | R1-No comments | TPSK-LSPA1-T-PE-00363
036909C-1051-PDS-0200-5115 | Process Equipment Datasheet - 10-PK-5115 - Condensate Carbon Filter Pkg | A | 2018-11-16 | IFR | OL1-2G30-5115 | PE | 2018-11-26 | 036909C-JVD-TRN-00362 | 036909C-JVD-TRN-00362 | IFR | 2018-12-10 | 2018-12-18 | R2-Comments as noted | TPSK-LSPA1-T-PE-00362
036909C-1028-PDS-0900-2855 | Process Equipment Datasheet - 10-P-2855 A-B - Ethylene Product Pumps | A | 2018-11-27 | IFR | OL1-2G30-2855 | PE | 2018-11-28 | 036909C-JVD-TRN-00379 | 036909C-JVD-TRN-00379 | IFR | 2018-12-12 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00379
036909C-1027-PDS-0900-2791 | Process Equipment Datasheet - 10-P-2790 - Light Oil Drain Drum Pump | A | 2018-12-12 | IFR | OL1-2G30-2791 | PE | 2018-12-13 | 036909C-JVD-TRN-00496 | 036909C-JVD-TRN-00496 | IFR | 2018-12-26 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00496
036909C-1028-PDS-0600-2859 | Process Equipment Datasheet - 10-E-2856 - Ethylene Product Subcooler | B | 2018-12-11 | IFD | OL1-2G30-2859 | PE | 2018-12-13 | 036909C-JVD-TRN-00492 | 036909C-JVD-TRN-00492 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00492 | CHANGE NUMBER - For revision A see document OL1-2G30-2591 - 1025-PDS-0600-2591
036909C-1026-SP-0910-2647 | Mechanical Equipment Datasheet - HP Propylene - Off Spec Pump | A | 2018-12-12 | IFQ | OL1-2M03-2647 | ME | 2018-12-13 | 036909C-JVD-TRN-00494 | 036909C-JVD-TRN-00494 | IFR | 2018-12-26 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00494
036909C-1026-PDS-0900-2669 | Process Equipment Datasheet - 10-P-2665 A-B - Debutanizer Bottoms Pumps | A | 2018-11-26 | IFR | OL1-2G30-2669 | PE | 2018-11-27 | 036909C-JVD-TRN-00371 | 036909C-JVD-TRN-00371 | IFR | 2018-12-11 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00371
036909C-1025-PDS-0900-2577 | Process Equipment Datasheet - 10-P-2575 A-B - Deethanizer Reboiler Cond Pumps | A | 2018-12-03 | IFR | OL1-2G30-2577 | PE | 2018-12-04 | 036909C-JVD-TRN-00408 | 036909C-JVD-TRN-00408 | IFR | 2018-12-17 | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-00408
036909C-1024-SP-0910-2457 | Mechanical Equipment Datasheet - LP Deprop Reboiler Cond Pump | A | 2018-12-05 | IFQ | OL1-2M03-2457 | ME | 2018-12-13 | 036909C-JVD-TRN-00494 | 036909C-JVD-TRN-00494 | IFR | 2018-12-26 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00494
036909C-1024-SP-0910-2443 | Mechanical Equipment Datasheet - HP Deprop Reboiler Cond Pump | A | 2018-12-05 | IFQ | OL1-2M03-2443 | ME | 2018-12-13 | 036909C-JVD-TRN-00494 | 036909C-JVD-TRN-00494 | IFR | 2018-12-26 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00494
036909C-1024-PDS-0600-2471 | Process Equipment Datasheet - 10-E-2470 - C2 Hydrog 1st Stage Intercooler | A | 2018-11-28 | IFR | OL1-2G30-2471 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00391
036909C-1024-PDS-0600-2465 | Process Equipment Datasheet - 10-E-2465 - C2 Hydrog Feed Heater | A | 2018-11-28 | IFR | OL1-2G30-2465 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00391
036909C-1024-PDS-0600-2472 | Process Equipment Datasheet - 10-E-2472 - C2 Hydrog 2nd Stage Intercooler | A | 2018-11-28 | IFR | OL1-2G30-2472 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00391
036909C-1024-SP-0910-2416 | Mechanical Equipment Datasheet - CG Liquid Dryer Feed Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2416 | ME | 2018-12-05 | 036909C-JVD-TRN-00413 | 036909C-JVD-TRN-00413 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00413
036909C-1024-PDS-0600-2474 | Process Equipment Datasheet - 10-E-2474 - C2 Hydrog Aftercooler | A | 2018-11-28 | IFR | OL1-2G30-2474 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00391
036909C-1024-PDS-0900-2443 | Process Equipment Datasheet - 10-P-2445 A-B - HP Deprop Reboiler Cond Pump | A | 2018-12-03 | IFR | OL1-2G30-2443 | PE | 2018-12-04 | 036909C-JVD-TRN-00408 | 036909C-JVD-TRN-00408 | IFR | 2018-12-17 | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-00408
036909C-1024-PDS-0900-2457 | Process Equipment Datasheet - 10-P-2455 A-B - LP Deprop Reboiler Cond Pump | A | 2018-12-03 | IFR | OL1-2G30-2457 | PE | 2018-12-04 | 036909C-JVD-TRN-00408 | 036909C-JVD-TRN-00408 | IFR | 2018-12-17 | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-00408
036909C-1023-PDS-0600-2326 | Process Equipment Datasheet - 10-E-2326 - Spent Caustic Stripper Feed Heater | A | 2018-11-27 | IFR | OL1-2G30-2326 | PE | 2018-11-28 | 036909C-JVD-TRN-00381 | 036909C-JVD-TRN-00381 | IFR | 2018-12-12 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00381
036909C-1022-PDS-0600-2206 | Process Equipment Datasheet - 10-E-2206 - Wash Water Cooler | A | 2018-11-27 | IFR | OL1-2G30-2206 | PE | 2018-11-28 | 036909C-JVD-TRN-00381 | 036909C-JVD-TRN-00381 | IFR | 2018-12-12 | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00381
036909C-1012-MR-0133-2008 | Material Requisition for Peep Doors | A | 2018-12-06 | IFQ | OL1-2M55-2008 | ME | 2018-12-14 | 036909C-JVD-TRN-00502 | 036909C-JVD-TRN-00502 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00502
036909C-1012-MR-0122-2004 | Material Requisition for Radiant Coil Assemblies | 0 | 2018-12-11 | IFP | OL1-2M55-2004 | ME | 2018-12-14 | 036909C-JVD-TRN-00499 | 036909C-JVD-TRN-00499 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00499
036909C-1023-PDS-0840-2314 | Process Equipment Datasheet - 10-F-2310 A-B - Wash Oil Circulating Filter | B | 2018-12-11 | IFD | OL1-2G30-2314 | PE | 2018-12-13 | 036909C-JVD-TRN-00493 | 036909C-JVD-TRN-00493 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00493
036909C-1023-PDS-0840-2319 | Process Equipment Datasheet - 10-F-2320 A-B - Spent Caustic Pump Discharge Filters | B | 2018-12-11 | IFD | OL1-2G30-2319 | PE | 2018-12-13 | 036909C-JVD-TRN-00493 | 036909C-JVD-TRN-00493 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00493
036909C-1028-PDS-0600-2858 | Process Equipment Datasheet - 10-E-2858 - HP Ethylene Product Superheater | B | 2018-12-11 | IFD | OL1-2G30-2858 | PE | 2018-12-13 | 036909C-JVD-TRN-00492 | 036909C-JVD-TRN-00492 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00492
036909C-1025-PDS-0600-2546 | Process Equipment Datasheet - 10-E-2546 - Demethanizer Bottoms Cooler | B | 2018-12-11 | IFD | OL1-2G30-2546 | PE | 2018-12-13 | 036909C-JVD-TRN-00492 | 036909C-JVD-TRN-00492 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00492
036909C-1025-PDS-0600-2545 | Process Equipment Datasheet - 10-E-2545 - Demethanizer Reboiler | B | 2018-12-11 | IFD | OL1-2G30-2545 | PE | 2018-12-13 | 036909C-JVD-TRN-00492 | 036909C-JVD-TRN-00492 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00492
036909C-1025-PDS-0600-2582 | Process Equipment Datasheet - 10-E-2582 - C2 Tower Reflux Cooler | B | 2018-12-11 | IFD | OL1-2G30-2582 | PE | 2018-12-13 | 036909C-JVD-TRN-00492 | 036909C-JVD-TRN-00492 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00492
036909C-1025-PDS-0600-2515 | Process Equipment Datasheet - 10-E-2515 - Demeth Prefrac Reboiler | B | 2018-12-11 | IFD | OL1-2G30-2515 | PE | 2018-12-13 | 036909C-JVD-TRN-00492 | 036909C-JVD-TRN-00492 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00492
036909C-1024-PDS-0600-2439 | Process Equipment Datasheet - 10-E-2440 - HP Depropanizer Condenser | B | 2018-11-28 | IFD | OL1-2G30-2439 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392
036909C-1024-PDS-0600-2461 | Process Equipment Datasheet - 10-E-2460 - C2 Hydrog Feed Cooler | B | 2018-11-28 | IFD | OL1-2G30-2461 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392
036909C-1024-PDS-0600-2446 | Process Equipment Datasheet - 10-E-2446 - LP Depropanizer Feed Cooler | B | 2018-11-28 | IFD | OL1-2G30-2446 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392
036909C-1024-PDS-0600-2441 | Process Equipment Datasheet - 10-E-2441 - HP Deprop Reflux Chiller No 2 | B | 2018-11-28 | IFD | OL1-2G30-2441 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392
036909C-1024-PDS-0600-2442 | Process Equipment Datasheet - 10-E-2442 - HP Deprop Reflux Chiller No 1 | B | 2018-11-28 | IFD | OL1-2G30-2442 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392
036909C-1026-PDS-0500-2630 | Process Equipment Datasheet - 10-T-2630 - Secondary Deethanizer | C | 2018-11-30 | IFD | OL1-2G30-2630 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-PE-00407
036909C-1021-PDS-0500-2140 | Process Equipment Datasheet - 10-T-2140 - Process Water Stripper | A | 2018-10-17 | IFR | OL1-2G30-2140 | PE | 2018-10-17 | 036909C-JVD-TRN-00189 | 036909C-JVD-TRN-00189 | IFR | 2018-10-31 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00189
036909C-1029-PDS-2600-2922 | Process Equipment Datasheet - 10-PK-2922 - CO Injection Pkg | B | 2019-01-14 | IFD | OL1-2G30-2922 | PE | 2019-01-16 | 036909C-JVD-TRN-00656 | 036909C-JVD-TRN-00656 | IFI |  | 2019-01-31 | R1-No comments | TPSK-LSPA1-T-PE-00656
036909C-1012-CN-0015-1201 | Steam Drum and Superheater PSVs Sizing Calculation | A | 2019-01-23 | IFR | OL1-2G05-1201 | PE | 2019-01-30 | 036909C-JVD-TRN-00769 | 036909C-JVD-TRN-00769 | IFR | 2019-02-15 |  | Transmitted | TPSK-LSPA1-T-PE-00769
036909C-1011-CN-0015-1101 | Steam Drum and Superheater PSVs Sizing Calculation | A | 2019-01-23 | IFR | OL1-2G05-1101 | PE | 2019-01-30 | 036909C-JVD-TRN-00769 | 036909C-JVD-TRN-00769 | IFR | 2019-02-15 |  | Transmitted | TPSK-LSPA1-T-PE-00769
036909C-1028-SP-0810-2880 | Mechanical Equipment Data Sheet - C2R 3RD Stage Suction Drum | A | 2018-12-04 | IFQ | OL1-2M03-2880 | ME | 2018-12-10 | 036909C-JVD-TRN-00460 | 036909C-JVD-TRN-00460 | IFR | 2018-12-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00460
036909C-1027-PDS-0800-2790 | Process Equipment Datasheet - 10-D-2790 - Light Oil Drain Drum | A | 2018-12-10 | IFR | OL1-2G30-2790 | PE | 2018-12-13 | 036909C-JVD-TRN-00482 | 036909C-JVD-TRN-00482 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00482
036909C-1024-PDS-0800-2460 | Process Equipment Datasheet - 10-D-2460 - C2 Hydrog Arsine Guard Bed | A | 2018-12-06 | IFR | OL1-2G30-2460 | PE | 2018-12-10 | 036909C-JVD-TRN-00453 | 036909C-JVD-TRN-00453 | IFR | 2018-12-21 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-00453
036909C-1024-PDS-0800-2456 | Process Equipment Datasheet - 10-D-2455 - LP Deprop Reboiler Cond Pot | A | 2018-12-07 | IFR | OL1-2G30-2456 | PE | 2018-12-11 | 036909C-JVD-TRN-00474 | 036909C-JVD-TRN-00474 | IFR | 2018-12-24 | 2018-12-21 | R1-No comments | TPSK-LSPA1-T-PE-00474
036909C-1025-PDS-0800-2574 | Process Equipment Datasheet - 10-D-2575 - Deethanizer Reboiler Cond Pot | A | 2018-12-07 | IFR | OL1-2G30-2574 | PE | 2018-12-11 | 036909C-JVD-TRN-00474 | 036909C-JVD-TRN-00474 | IFR | 2018-12-24 | 2018-12-21 | R1-No comments | TPSK-LSPA1-T-PE-00474
036909C-1024-PDS-0800-2444 | Process Equipment Datasheet - 10-D-2445 - HP Deprop Reboiler Cond Pot | A | 2018-12-07 | IFR | OL1-2G30-2444 | PE | 2018-12-11 | 036909C-JVD-TRN-00474 | 036909C-JVD-TRN-00474 | IFR | 2018-12-24 | 2018-12-21 | R1-No comments | TPSK-LSPA1-T-PE-00474
036909C-1022-PDS-0600-2211 | Process Equipment Datasheet - 10-E-2210 A-B - CG 1st Stage Aftercoolers | B | 2018-12-10 | IFD | OL1-2G30-2211 | PE | 2018-12-13 | 036909C-JVD-TRN-00479 | 036909C-JVD-TRN-00479 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00479
036909C-1023-PDS-0900-2391 | Process Equipment Datasheet - 10-P-2390 - Caustic Drain Drum Pump | A | 2018-12-06 | IFR | OL1-2G30-2391 | PE | 2018-12-07 | 036909C-JVD-TRN-00444 | 036909C-JVD-TRN-00444 | IFR | 2018-12-20 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-00444
036909C-1021-PDS-0800-2136 | Process Equipment Datasheet - 10-D-2136 - Process Water Feed Coalescer | A | 2018-12-06 | IFR | OL1-2G30-2136 | PE | 2018-12-10 | 036909C-JVD-TRN-00453 | 036909C-JVD-TRN-00453 | IFR | 2018-12-21 | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00453
036909C-1012-MR-0127-2001 | Material Requisition for Convection Tubes | 0 | 2018-12-06 | IFP | OL1-2M55-2001 | ME | 2018-12-10 | 036909C-JVD-TRN-00450 | 036909C-JVD-TRN-00450 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00450
036909C-1012-DW-0130-2554 | USC 132U Cracking Furnace Peep Door Details | 0 | 2018-12-04 | IFI | OL1-2M06-2554 | ME | 2018-12-04 | 036909C-JVD-TRN-00422 | 036909C-JVD-TRN-00422 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00422
036909C-1012-DW-0131-2546 | USC 132U Cracking Furnace Name Plate Details | 0 | 2018-12-04 | IFI | OL1-2K32-2546 | ME | 2018-12-04 | 036909C-JVD-TRN-00423 | 036909C-JVD-TRN-00423 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00423
036909C-1012-DW-0117-2005 | USC 132U Cracking Furnace Dilution Mixing Tee Details | 0 | 2019-01-10 | IFI | OL1-2M06-2207 | ME | 2019-01-23 | 036909C-JVD-TRN-00669 | 036909C-JVD-TRN-00668, 036909C-JVD-TRN-00669 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00669
036909C-1025-PDS-0800-2525 | Process Equipment Datasheet - 10-D-2525 - Hydrogen Drum | B | 2018-12-04 | IFD | OL1-2G30-2525 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  | 2018-12-18 | R1-No comments | TPSK-LSPA1-T-PE-00430
036909C-1022-PDS-0600-2231 | Process Equipment Datasheet - 10-E-2230 A-B - CG 3rd Stage Aftercooler | B | 2018-12-04 | IFD | OL1-2G30-2231 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00431
036909C-1022-PDS-0600-2241 | Process Equipment Datasheet - 10-E-2240 A-B - CG 4th Stage Aftercooler | B | 2018-12-04 | IFD | OL1-2G30-2241 | PE | 2018-12-07 | 036909C-JVD-TRN-00436 | 036909C-JVD-TRN-00436 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00436
036909C-1051-SP-0910-5101 | Mechanical Equipment Data Sheet - SHP BFW Pumps | C | 2018-11-28 | IFQ | OL1-2M03-5101 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00476
036909C-1025-PDS-0900-2573 | Process Equipment Datasheet - 10-P-2570 A-B - Deethanizer Reflux Pumps | B | 2018-12-10 | IFD | OL1-2G30-2573 | PE | 2018-12-13 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00481
036909C-1025-PDS-0900-2586 | Process Equipment Datasheet - 10-P-2586 A-B - Ethane Recycle Pumps | B | 2018-12-10 | IFD | OL1-2G30-2586 | PE | 2018-12-13 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00481
036909C-102D-DW-1743-0023 | Foundation For 10-D-2860 | A | 2019-01-24 | IFR | OL1-2K34-0115 | CV | 2019-01-28 | 036909C-JVD-TRN-00734 | 036909C-JVD-TRN-00734 | IFR | 2019-02-12 |  | Transmitted | TPSK-LSPA1-T-CV-00734
036909C-1000-QCP-1812-0002 | Quality Control Plan Secondary Steel Structures Erection - Ladders Platforms Walkways Handrails Gratings | A | 2019-01-21 | IFR | OL1-2Q22-0002 | QM | 2019-01-28 | 036909C-JVD-TRN-00735 | 036909C-JVD-TRN-00735 | IFA | 2019-02-12 |  | Transmitted | TPSK-LSPA1-T-QM-00735
036909C-102D-CN-1733-0028 | Calculation Note for Foundation of 10-E-2502 | A | 2019-01-17 | IFR | OL1-2K13-0117 | CV | 2019-01-25 | 036909C-JVD-TRN-00682 | 036909C-JVD-TRN-00679 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-CV-00679
036909C-102D-CN-1733-0010 | Calculation Note For Foundation Of 10-D-2815 | A | 2019-01-23 | IFR | OL1-2K13-0098 | CV | 2019-01-28 | 036909C-JVD-TRN-00732 | 036909C-JVD-TRN-00732 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-CV-00732
036909C-102D-DW-1743-0022 | Foundation For 10-D-2870 | A | 2019-01-22 | IFR | OL1-2K34-0114 | CV | 2019-01-28 | 036909C-JVD-TRN-00728 | 036909C-JVD-TRN-00728 | IFR | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-CV-00728
036909C-102D-CN-1733-0020 | Calculation Note For Foundation Of 10-D-2860 | A | 2019-01-22 | IFR | OL1-2K13-0108 | CV | 2019-01-28 | 036909C-JVD-TRN-00732 | 036909C-JVD-TRN-00732 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-CV-00732
036909C-102D-DW-1743-0031 | Foundation for 10-E-2502 | A | 2019-01-17 | IFR | OL1-2K34-0124 | CV | 2019-01-28 | 036909C-JVD-TRN-00728 | 036909C-JVD-TRN-00728 | IFR | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-CV-00728
036909C-102D-CN-1733-0019 | Calculation Note For Foundation of 10-D-2870 | A | 2019-01-22 | IFR | OL1-2K13-0107 | CV | 2019-01-25 | 036909C-JVD-TRN-00682 | 036909C-JVD-TRN-00679 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-CV-00679
036909C-102D-CN-1733-0007 | Calculation Note For Foundation Of 10-T-2520/10-D-2520 | A | 2019-01-23 | IFR | OL1-2K13-0093 | CV | 2019-01-25 | 036909C-JVD-TRN-00682 | 036909C-JVD-TRN-00679 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-CV-00679
036909C-1000-QCP-1761-0001 | Quality Control Plan Concrete Protective Coating | A | 2019-01-21 | IFR | OL1-2Q20-0019 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-QM-00729
036909C-102A-CN-1733-0030 | Calculation Note for Foundation of 10-D-5140 | A | 2019-01-22 | IFR | OL1-2K13-0287 | CV | 2019-01-25 | 036909C-JVD-TRN-00682 | 036909C-JVD-TRN-00679 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-CV-00679
036909C-1000-QCP-2300-0001 | Quality Control Plan Painting | A | 2019-01-21 | IFR | OL1-2Q24-0010 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-QM-00730
036909C-1000-QCP-2200-0001 | Quality Control Plan Insulation | A | 2019-01-21 | IFR | OL1-2Q24-0009 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-QM-00730
036909C-1000-QCP-1812-0001 | Quality Control Plan Steel Structures Erection | A | 2019-01-21 | IFR | OL1-2Q22-0001 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-QM-00729
036909C-102A-DW-1743-0035 | Foundation for 10-D-5140 | A | 2019-01-22 | IFR | OL1-2K34-0306 | CV | 2019-01-28 | 036909C-JVD-TRN-00728 | 036909C-JVD-TRN-00728 | IFR | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-CV-00728
036909C-102A-CN-1733-0005 | Calculation Note For Foundation of 10-D-2160 | A | 2019-01-23 | IFR | OL1-2K13-0011 | CV | 2019-01-28 | 036909C-JVD-TRN-00732 | 036909C-JVD-TRN-00732 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-CV-00732
036909C-1000-QCP-1399-0001 | Quality Control Plan Welders Management | A | 2019-01-22 | IFR | OL1-2Q24-0008 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-QM-00730
036909C-1000-QCP-1310-0001 | Quality Control Plan Piping Prefabrication | A | 2019-01-22 | IFR | OL1-2Q24-0001 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-QM-00730
036909C-1000-QCP-1310-0002 | Quality Control Plan Piping Support Prefabrication | A | 2019-01-22 | IFR | OL1-2Q24-0002 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-QM-00730
036909C-1000-QCP-1320-0002 | Quality Control Plan Piping Support Erection | A | 2019-01-22 | IFR | OL1-2Q24-0004 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-QM-00730
036909C-1000-QCP-1330-0001 | Quality Control Plan Steam Tracing System | A | 2019-01-22 | IFR | OL1-2Q24-0005 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-QM-00730
036909C-1000-QCP-1390-0001 | Quality Control Plan Piping NDE PWHT Management | A | 2019-01-22 | IFR | OL1-2Q24-0007 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-QM-00730
036909C-1000-QCP-1320-0001 | Quality Control Plan Piping Erection - Above & Underground | A | 2019-01-22 | IFR | OL1-2Q24-0003 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-QM-00730
036909C-1000-QCP-1370-0001 | Quality Control Plan Piping Tie-ins | A | 2019-01-22 | IFR | OL1-2Q24-0006 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-QM-00730
036909C-1000-RT-1920-0051 | MSDS for Chemicals and Catalysts | 0 | 2019-01-21 | IFI | OL1-2L60-0051 | SE | 2019-01-23 | 036909C-JVD-TRN-00707 | 036909C-JVD-TRN-00707 | IFI |  |  | Transmitted | TPSK-LSPA1-T-SE-00707
036909C-1024-PDS-0600-2434 | Process Equipment Datasheet - 10-E-2435 - Regen Gas Effluent Cooler | A | 2018-12-27 | IFR | OL1-2G30-2434 | PE | 2019-01-03 | 036909C-JVD-TRN-00574 | 036909C-JVD-TRN-00574 | IFR | 2019-01-15 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00574
036909C-1024-PDS-0600-2432 | Process Equipment Datasheet - 10-E-2432 - Regen Gas Shp Heater | A | 2018-12-27 | IFR | OL1-2G30-2432 | PE | 2019-01-03 | 036909C-JVD-TRN-00574 | 036909C-JVD-TRN-00574 | IFR | 2019-01-15 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00574
036909C-1024-PDS-0600-2430 | Process Equipment Datasheet - 10-E-2430 - Regen Gas Feed Heater | A | 2018-12-27 | IFR | OL1-2G30-2430 | PE | 2019-01-03 | 036909C-JVD-TRN-00574 | 036909C-JVD-TRN-00574 | IFR | 2019-01-15 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00574
036909C-1020-PDS-0840-2049 | Process Equipment Datasheet - 10-F-2048 A-B Heavy Fuel Oil Filters | A | 2018-11-21 | IFR | OL1-2G30-2049 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00350
036909C-1020-PDS-0840-2028 | Process Equipment Datasheet - 10-F-2028 A-B - FO Pump Purge Oil Filter | A | 2018-11-21 | IFR | OL1-2G30-2028 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00350
036909C-1020-PDS-0840-2025 | Process Equipment Datasheet - 10-F-2026 A-B Cracker Bottoms Product Filter | A | 2018-11-21 | IFR | OL1-2G30-2025 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00350
036909C-1011-PDS-0117-1001 | See document number 036909C-1011-PDS-0117-1101 or OL1-2G30-1101 | A | 2018-09-28 | IFR | OL1-4G30-1001 | PE | 2018-10-01 | 036909C-JVD-TRN-00117 | 036909C-JVD-TRN-00117 | IFR | 2018-10-15 |  | Transmitted | TPSK-LSPA1-T-PE-00117
036909C-1012-PDS-0117-2001 | See document number 036909C-1012-PDS-0117-1201 or OL1-2G30-1201 | A | 2018-09-28 | IFR | OL1-4G30-2001 | PE | 2018-10-01 | 036909C-JVD-TRN-00117 | 036909C-JVD-TRN-00117 | IFR | 2018-10-15 |  | Transmitted | TPSK-LSPA1-T-PE-00117
036909C-1000-QCP-1470-0002 | Quality Control Plan Non Metallic Pressure Piping Installation - Above and Underground | A | 2019-01-07 | IFR | OL1-2Q20-0008 | QM | 2019-01-11 | 036909C-JVD-TRN-00625 | 036909C-JVD-TRN-00625 | IFA | 2019-01-25 |  | Transmitted | TPSK-LSPA1-T-QM-00625
036909C-1020-PDS-0840-2014 | Process Equipment Datasheet - 10-F-2009 A-B QO Pump Purge Oil Filter | A | 2018-11-21 | IFR | OL1-2G30-2014 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00350
036909C-1020-PDS-0840-2010 | Process Equipment Datasheet - 10-F-2008 A-C Quench Oil Filter | A | 2018-11-21 | IFR | OL1-2G30-2010 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00350
036909C-1000-JSS-1661-0001 | Substation Monitoring And Control System | 0 | 2018-12-03 | IMP | OL1-2R05-0005 | EE | 2018-12-05 | 036909C-JVD-TRN-00425 | 036909C-JVD-TRN-00425 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00425
036909C-1028-PDS-0600-2858 | Process Equipment Datasheet - 10-E-2858 - HP Ethylene Product Superheater | A | 2018-10-23 | IFR | OL1-2G30-2858 | PE | 2018-10-24 | 036909C-JVD-TRN-00223 | 036909C-JVD-TRN-00223 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00223
036909C-1021-MSD-0011-2101 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | A | 2018-11-02 | IFA | OL1-2G74-2101 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295
036909C-1021-PDS-0600-2165 | Process Equipment Datasheet - 10-E-2165 A-D DSG Reboilers | A | 2018-10-17 | IFR | OL1-2G30-2165 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00194
036909C-1021-PDS-0600-2161 | Process Equipment Datasheet - 10-E-2160 - Dilution Steam Superheater | A | 2018-10-17 | IFR | OL1-2G30-2161 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00194
036909C-1021-PDS-0600-2137 | Process Equipment Datasheet - 10-E-2136 - Process Water Stripper Feed Heater | A | 2018-10-17 | IFR | OL1-2G30-2137 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00194
036909C-1000-SL-0000-03 | Subvendor list for PSA/Deareator/Filter Package | 0 | 2018-11-15 | IMP | OL1-2C01-0002 | PL | 2018-11-19 | 036909C-JVD-TRN-00333 | 036909C-JVD-TRN-00333 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00333
036909C-1000-JSS-1656-0001 | Power Capacitors | 0 | 2018-09-20 | IMP | OL1-2R05-0021 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268
036909C-1011-PDS-0610-1009 | See document number 036909C-1011-PDS-0610-1109 or OL1-2G30-1109 | A | 2018-09-17 | IFR | OL1-4G30-1009 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066
036909C-1011-PDS-0610-1010 | See document number 036909C-1011-PDS-0610-1110 or OL1-2G30-1110 | A | 2018-09-17 | IFR | OL1-4G30-1010 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066
036909C-1000-RT-200 | Fire Fighting Basic Design Report For Package A1 | 1 | 2018-09-28 | IFI | OL1-2W90-0001 | PC | 2018-10-17 | 036909C-JVD-TRN-00187 | 036909C-JVD-TRN-00187 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PM-00187
036909C-1012-PDS-0610-2009 | See document number 036909C-1012-PDS-0610-1209 or OL1-2G30-1209 | A | 2018-09-17 | IFR | OL1-4G30-2009 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066
036909C-1012-PDS-0630-2008 | See document number 036909C-1012-PDS-0630-1208 or OL1-2G30-1208 | A | 2018-09-17 | IFR | OL1-4G30-2008 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066
036909C-1051-PDS-0800-5100 | Process Equipment Data Sheet - 10-D-5100 - Deaerator | A | 2018-10-09 | IFR | OL1-2G30-5100 | PE | 2018-10-10 | 036909C-JVD-TRN-00151 | 036909C-JVD-TRN-00151 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00151 |  | 2018-10-10
036909C-1056-PID-0031-5631 | P&ID - Olefins Unit 10 - Wastewater - Olefins Holding Basin - Sheet 2 | A | 2019-02-13 | IFR | OL1-2G43-5631 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5630 | P&ID - Olefins Unit 10 - Wastewater - Olefins Holding Basin - Sheet 1 | A | 2019-02-13 | IFR | OL1-2G43-5630 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5621 | P&ID - Olefins Unit 10 - Wastewater - HP Flare Area Storm Water Collection | A | 2019-02-13 | IFR | OL1-2G43-5621 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5620 | P&ID - Olefins Unit 10 - Wastewater - Olefins Storm Water Collection | A | 2019-02-13 | IFR | OL1-2G43-5620 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5610 | P&ID - Olefins Unit 10 - Wastewater - Oily Waste Water Collection | A | 2019-02-13 | IFR | OL1-2G43-5610 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5609 | P&ID - Olefins Unit 10 - Wastewater - Flare Kod Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5609 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5608 | P&ID - Olefins Unit 10 - Wastewater - C3 Hydrog Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5608 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5607 | P&ID - Olefins Unit 10 - Wastewater - Hydroblast Sump | A | 2019-02-13 | IFR | OL1-2G43-5607 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00007 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5606 | P&ID - Olefins Unit 10 - Wastewater - Furnace Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5606 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5640 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 1 | A | 2019-02-13 | IFR | OL1-2G43-5640 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5641 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 2 | A | 2019-02-13 | IFR | OL1-2G43-5641 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5642 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 3 | A | 2019-02-13 | IFR | OL1-2G43-5642 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5649 | P&ID - Olefins Unit 10 - Wastewater - HP Flare Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5649 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5650 | P&ID - Olefins Unit 10 - Wastewater - CT Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5650 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5651 | P&ID - Olefins Unit 10 - Wastewater - CWWT Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5651 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5652 | P&ID - Olefins Unit 10 - Wastewater - Cooling Water Blowdown Basin | A | 2019-02-13 | IFR | OL1-2G43-5652 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00007 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5653 | P&ID - Olefins Unit 10 - Wastewater - Oily Waste Water Distribution | A | 2019-02-13 | IFR | OL1-2G43-5653 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00007 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5656 | P&ID - Olefins Unit 10 - Wastewater - Domestic Wastewater Collection | A | 2019-02-13 | IFR | OL1-2G43-5656 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00007 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5654 | P&ID - Olefins Unit 10 - Wastewater - Equalization Tank | A | 2019-02-13 | IFR | OL1-2G43-5654 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00007 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5655 | P&ID - Olefins Unit 10 - Wastewater - Waste Water CPI-IGF Package | A | 2019-02-13 | IFR | OL1-2G43-5655 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00007 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5667 | P&ID - Olefins Unit 10 - Wastewater - Oily Sludge Tank | A | 2019-02-13 | IFR | OL1-2G43-5667 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5666 | P&ID - Olefins Unit 10 - Wastewater - Slop Oil Tank B | A | 2019-02-13 | IFR | OL1-2G43-5666 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5665 | P&ID - Olefins Unit 10 - Wastewater - Slop Oil Tank A | A | 2019-02-13 | IFR | OL1-2G43-5665 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5662 | P&ID - Olefins Unit 10 - Wastewater - Dewatering System | A | 2019-02-13 | IFR | OL1-2G43-5662 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5660 | P&ID - Olefins Unit 10 - Wastewater - Final Check Basin | A | 2019-02-13 | IFR | OL1-2G43-5660 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5658 | P&ID - Olefins Unit 10 - Wastewater - Bio Treatment Package | A | 2019-02-13 | IFR | OL1-2G43-5658 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5657 | P&ID - Olefins Unit 10 - Wastewater - Bio Equalization Pit | A | 2019-02-13 | IFR | OL1-2G43-5657 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00007 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5602 | P&ID - Olefins Unit 10 - Wastewater - Butadiene Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5602 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5603 | P&ID - Olefins Unit 10 - Wastewater - QW Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5603 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5604 | P&ID - Olefins Unit 10 - Wastewater - CGC Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5604 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5605 | P&ID - Olefins Unit 10 - Wastewater - Refrig Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5605 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1056-PID-0031-5601 | P&ID - Olefins Unit 10 - Wastewater - Pygas Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5601 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15
036909C-1000-JSS-6300-05 | Job Specification For Welding And NDE Storage Tanks | A | 2018-08-24 | IFR | OL1-2R03-0004 | MP | 2018-08-29 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | R1-No comments | TPSK-LSPA1-T-ME-00029 |  | 2018-08-29
036909C-1000-JSS-6300-04 | Job Specification For Supply Positive Alloy Material Identification Of Equipment And Piping | A | 2018-08-24 | IFR | OL1-2R03-0003 | MP | 2018-08-29 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | R1-No comments | TPSK-LSPA1-T-ME-00029 |  | 2018-08-29
036909C-1000-JSS-6300-03 | Job Specification For Materials In Sour Services | A | 2018-08-24 | IFR | OL1-2R03-0002 | MP | 2018-08-29 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | R1-No comments | TPSK-LSPA1-T-ME-00029 |  | 2018-08-29
036909C-1000-NM-0005-0001 | Effluent Summary | A | 2019-02-21 | IFR | OL1-2G63-0001 | PE | 2019-02-26 | 036909C-JVD-TRN-00922 | 036909C-JVD-TRN-00922 | IFR | 2019-03-12 |  | Transmitted | TPSK-LSPA1-T-PE-00922 |  | 2019-02-26
036909C-1027-SP-0810-2706 | Mechanical Equipment Data Sheet - GHU-1 Cold Separator | A | 2019-02-22 | IFQ | OL1-2M03-2706 | ME | 2019-02-26 | 036909C-JVD-TRN-00928 | 036909C-JVD-TRN-00928 | IFR | 2019-03-12 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-00928 |  | 2019-02-26
036909C-1021-TDS-0661-2101 | Mechanical Equipment Data Sheet - 10-E-2100 - Quench Water Cooler | 0 | 2019-02-25 | IFP | OL1-2M03-2101 | ME | 2019-02-26 | 036909C-JVD-TRN-00930 | 036909C-JVD-TRN-00930 | IFR | 2019-03-12 |  | Transmitted | TPSK-LSPA1-T-ME -0930 |  | 2019-02-26
036909C-1025-SP-0510-2570 | Mechanical Equipment Data Sheet - Deethanizer | B | 2018-12-17 | IFQ | OL1-2M03-2570 | ME | 2018-12-20 | 036909C-JVD-TRN-00547 | 036909C-JVD-TRN-00547 | IFR | 2019-01-02 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00547
036909C-1025-SP-0510-2570 | Mechanical Equipment Data Sheet - Deethanizer | A | 2018-11-28 | IFQ | OL1-2M03-2570 | ME | 2018-11-29 | 036909C-JVD-TRN-00394 | 036909C-JVD-TRN-00394 | IFR | 2018-12-13 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00394
036909C-1011-NM-0022-1101 | Line Designation Table – Recycle Gas Cracking Furnace 10-H-1100 | A | 2019-02-15 | IBD | OL1-2P91-1101 | PE | 2019-02-27 | 036909C-JVD-TRN-00933 | 036909C-JVD-TRN-00933 | IFR | 2019-03-12 |  | Transmitted | TPSK-LSPA1-T-PE-00933 |  | 2019-02-27
036909C-1021-PDS-0600-2101 | Process Equipment Data Sheet - 10-E-2100 - Quench Water Cooler | A | 2018-09-07 | IFA | OL1-2G30-2101 | PE | 2018-09-11 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11
036909C-1025-PDS-0600-2587 | Process Equipment Data Sheet - 10-E-2587 - C2 Tower Side Reboiler | A | 2018-09-06 | IFA | OL1-2G30-2587 | PE | 2018-09-11 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11
036909C-1025-PDS-0600-2585 | Process Equipment Data Sheet - 10-E-2585 - C2 Tower Bottoms Reboiler | A | 2018-09-06 | IFA | OL1-2G30-2585 | PE | 2018-09-11 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11
036909C-1025-PDS-0600-2541 | Process Equipment Data Sheet - 10-E-2540 - Demethanizer Condenser | A | 2018-09-06 | IFA | OL1-2G30-2541 | PE | 2018-09-11 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11
036909C-1025-PDS-0600-2526 | Process Equipment Data Sheet - 10-E-2525 - Hydrogen Core Exchanger | A | 2018-09-06 | IFA | OL1-2G30-2526 | PE | 2018-09-11 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11
036909C-1000-EL-001 | Item Index | A | 2019-03-15 | IFR | OL1-2M91-0001 | ME | 2019-03-18 | 036909C-JVD-TRN-01080 | 036909C-JVD-TRN-01080 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-ME-01080 |  | 2019-03-18
036909C-1025-PDS-0600-2511 | Process Equipment Data Sheet - 10-E-2510 - Demeth Prefrac Condenser | A | 2018-09-06 | IFA | OL1-2G30-2511 | PE | 2018-09-11 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11
036909C-1012-EL-001 | Item Index Furnace Island | A | 2019-03-15 | IFR | OL1-2M91-0002 | ME | 2019-03-18 | 036909C-JVD-TRN-01080 | 036909C-JVD-TRN-01080 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-ME-01080 |  | 2019-03-18
036909C-1000-JSD-0000-0005 | Plate-Fin Exchanger Design Specification | A | 2018-10-01 | IFR | OL1-2G01-0003 | PE | 2018-10-04 | 036909C-JVD-TRN-00123 | 036909C-JVD-TRN-00123, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-10-17 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00123 |  | 2018-10-04
036909C-1027-TDS-0610-2763 | Mechanical Equipment Data Sheet - 10-E-2760 - C4-C5 Hydro Vent Condenser | A | 2019-03-07 | IFQ | OL1-2M03-2763 | ME | 2019-03-18 | 036909C-JVD-TRN-01075 | 036909C-JVD-TRN-01075 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-ME-01075 |  | 2019-03-18
036909C-1039-PID-0031-3901 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - NMP Storage | A | 2019-03-14 | IFR | OL1-2G43-3901 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1039-PID-0031-3902 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Solvent Inhibitor Injection System | A | 2019-03-14 | IFR | OL1-2G43-3902 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1031-PID-0031-3112 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drain System - Sheet 1 | A | 2019-03-14 | IFR | OL1-2G43-3112 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1031-PID-0031-3113 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drain System - Sheet 2 | A | 2019-03-14 | IFR | OL1-2G43-3113 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3029 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Butadiene Product To B L | A | 2019-03-14 | IFR | OL1-2G43-3029 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3028 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Butadiene Drying Tower And Reboiler | A | 2019-03-14 | IFR | OL1-2G43-3028 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1039-PID-0031-3903 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Product Inhibitor Injection System | A | 2019-03-14 | IFR | OL1-2G43-3903 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1031-PID-0031-3101 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Solvent Regeneration | A | 2019-03-14 | IFR | OL1-2G43-3101 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1031-PID-0031-3102 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Water Washer And Condenser | A | 2019-03-14 | IFR | OL1-2G43-3102 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1031-PID-0031-3105 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Ejector Seal Drum And Waste Water Pumps | A | 2019-03-14 | IFR | OL1-2G43-3105 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1031-PID-0031-3107 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drum | A | 2019-03-14 | IFR | OL1-2G43-3107 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1031-PID-0031-3106 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Blow Down Drum | A | 2019-03-14 | IFR | OL1-2G43-3106 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1031-PID-0031-3104 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Water Washer Accumulator & Solvent Return Pumps | A | 2019-03-14 | IFR | OL1-2G43-3104 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1031-PID-0031-3103 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Regen Steam Ejector Package | A | 2019-03-14 | IFR | OL1-2G43-3103 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1039-PID-0031-3904 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Anti-Foam Agent Injection System | A | 2019-03-14 | IFR | OL1-2G43-3904 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1031-PID-0031-3110 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Heater And Cooler | A | 2019-03-14 | IFR | OL1-2G43-3110 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1031-PID-0031-3111 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - BDU Steam Letdown | A | 2019-03-14 | IFR | OL1-2G43-3111 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1039-PID-0031-3905 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Predistillation Inhibitor System | A | 2019-03-14 | IFR | OL1-2G43-3905 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1031-PID-0031-3108 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Flash Drum | A | 2019-03-14 | IFR | OL1-2G43-3108 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1031-PID-0031-3109 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Drum And Recycle Pumps | A | 2019-03-14 | IFR | OL1-2G43-3109 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3006 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - C4 Vaporizers | A | 2019-03-14 | IFR | OL1-2G43-3006 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3005 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - C4 Vaporization Tower & Heavy End Disch. Pumps | A | 2019-03-14 | IFR | OL1-2G43-3005 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3018 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Direct Cooler Pump & Degasser Bottom Pump | A | 2019-03-14 | IFR | OL1-2G43-3018 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3019 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - HC - Water Separator | A | 2019-03-14 | IFR | OL1-2G43-3019 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3016 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Direct Cooler And NMP Cooler | A | 2019-03-14 | IFR | OL1-2G43-3016 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3017 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Degassing Tower And Reboiler | A | 2019-03-14 | IFR | OL1-2G43-3017 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3023 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Recycle Gas Compressor | A | 2019-03-14 | IFR | OL1-2G43-3023 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3024 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Butadiene Tower | A | 2019-03-14 | IFR | OL1-2G43-3024 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3020 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Acetylene Wash Condenser | A | 2019-03-14 | IFR | OL1-2G43-3020 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3022 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - C4 Acetylene Pumps | A | 2019-03-14 | IFR | OL1-2G43-3022 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3021 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Acetylene Condenser And Accumulator | A | 2019-03-14 | IFR | OL1-2G43-3021 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3009 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Main Washer Bottom Pump & Reflux Pump | A | 2019-03-14 | IFR | OL1-2G43-3009 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3010 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Rectifier | A | 2019-03-14 | IFR | OL1-2G43-3010 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1027-PID-0021-2734 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Reactor | A | 2019-03-14 | IFR | OL1-2G43-2734 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2736 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Separator Drum | A | 2019-03-14 | IFR | OL1-2G43-2736 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1030-PID-0021-3014 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Solvent Heat Exchangers - I | A | 2019-03-14 | IFR | OL1-2G43-3014 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3015 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Solvent Heat Exchanger-II And Solvent Heater | A | 2019-03-14 | IFR | OL1-2G43-3015 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3011 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Rectifier Pump And Degasser Feed Pump | A | 2019-03-14 | IFR | OL1-2G43-3011 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3013 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - After Washer Overhead | A | 2019-03-14 | IFR | OL1-2G43-3013 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3012 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - After Washer | A | 2019-03-14 | IFR | OL1-2G43-3012 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3003 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Predistillation Tower Trim Reboilers | A | 2019-03-14 | IFR | OL1-2G43-3003 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3007 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Main Washer & Solvent Cooler | A | 2019-03-14 | IFR | OL1-2G43-3007 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3004 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Predistillation Tower Overhead | A | 2019-03-14 | IFR | OL1-2G43-3004 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3001 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Predistillation Feed Drum & Feed Pumps | A | 2019-03-14 | IFR | OL1-2G43-3001 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3008 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Main Washer Overhead | A | 2019-03-14 | IFR | OL1-2G43-3008 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3002 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Predistillation Tower & Reboiler | A | 2019-03-14 | IFR | OL1-2G43-3002 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1027-PID-0021-2740 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Light Oil Drain Collection | A | 2019-03-14 | IFR | OL1-2G43-2740 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1030-PID-0021-3025 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Butadiene Tower Reboilers | A | 2019-03-14 | IFR | OL1-2G43-3025 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1027-PID-0021-2738 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Recycle-Product Cooling | A | 2019-03-14 | IFR | OL1-2G43-2738 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2742 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Light Oil Drain Drum | A | 2019-03-14 | IFR | OL1-2G43-2742 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1030-PID-0021-3026 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Butadiene Tower Bottom Pump | A | 2019-03-14 | IFR | OL1-2G43-3026 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1030-PID-0021-3027 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Butadiene Tower Overhead | A | 2019-03-14 | IFR | OL1-2G43-3027 | PE | 2019-03-15 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15
036909C-1027-PID-0021-2701 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Feed Heating | A | 2019-03-14 | IFR | OL1-2G43-2701 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2711 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU Rerun Tower Condenser | A | 2019-03-14 | IFR | OL1-2G43-2711 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2703 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Reactors - Sheet 2 | A | 2019-03-14 | IFR | OL1-2G43-2703 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2702 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Reactors - Sheet 1 | A | 2019-03-14 | IFR | OL1-2G43-2702 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2707 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU C5 Cut Pumps | A | 2019-03-14 | IFR | OL1-2G43-2707 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2710 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Rerun Tower | A | 2019-03-14 | IFR | OL1-2G43-2710 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2708 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Depentanizer Overhead | A | 2019-03-14 | IFR | OL1-2G43-2708 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2704 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Hot Separator | A | 2019-03-14 | IFR | OL1-2G43-2704 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2706 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Depentanizer | A | 2019-03-14 | IFR | OL1-2G43-2706 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2705 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Cold Separator | A | 2019-03-14 | IFR | OL1-2G43-2705 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2722 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Regeneration Decoke Drum | A | 2019-03-14 | IFR | OL1-2G43-2722 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2720 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Reactivation Gas Heating | A | 2019-03-14 | IFR | OL1-2G43-2720 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2732 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Feed Pump | A | 2019-03-14 | IFR | OL1-2G43-2732 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2733 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Feed Heating | A | 2019-03-14 | IFR | OL1-2G43-2733 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2730 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Feed Surge Drum | A | 2019-03-14 | IFR | OL1-2G43-2730 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2715 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Recycle Wash Oil | A | 2019-03-14 | IFR | OL1-2G43-2715 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2712 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU Rerun Tower Reflux-Product Pump | A | 2019-03-14 | IFR | OL1-2G43-2712 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2713 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Product - Wash Oil Pumps | A | 2019-03-14 | IFR | OL1-2G43-2713 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2718 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Anti-Oxidant Injection Package | A | 2019-03-14 | IFR | OL1-2G43-2718 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2716 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Pygas Fuel Oil Product | A | 2019-03-14 | IFR | OL1-2G43-2716 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1027-PID-0021-2717 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Refun Tower Liquid Ring Pump | A | 2019-03-14 | IFR | OL1-2G43-2717 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1026-PID-0021-2608 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Aftercooling | A | 2019-03-14 | IFR | OL1-2G43-2608 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1026-PID-0021-2604 | P&ID - Olefins Unit 10 - Hot Fractionation - Feed Section | A | 2019-03-14 | IFR | OL1-2G43-2604 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1026-PID-0021-2605 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Reactors - Sheet 1 | A | 2019-03-14 | IFR | OL1-2G43-2605 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1026-PID-0021-2630 | P&ID - Olefins Unit 10 - Hot Fractionation - C5-Pygas Surge Drum | B | 2019-03-14 | IFR | OL1-2G43-2630 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1026-PID-0021-2610 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Recycle | A | 2019-03-14 | IFR | OL1-2G43-2610 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1026-PID-0021-2629 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Bottoms Cooling | B | 2019-03-14 | IFR | OL1-2G43-2629 | PE | 2019-03-15 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15
036909C-1001-DW-2054-0003 | Gatehouse A - Architectural Plans Elevations Sections And Schedules | A | 2019-03-04 | IFR | OL1-2K30-0038 | CV | 2019-03-15 | 036909C-JVD-TRN-01064 | 036909C-JVD-TRN-01064 | IFA | 2019-03-29 |  | Transmitted | TPSL-LSPA1-T-CV-01064 |  | 2019-03-15
036909C-1001-DW-2054-0001-03 | Gatehouse A - Architectural Isometric Views | A | 2019-03-04 | IFR | OL1-2K30-0032 | CV | 2019-03-15 | 036909C-JVD-TRN-01064 | 036909C-JVD-TRN-01064 | IFA | 2019-03-29 |  | Transmitted | TPSL-LSPA1-T-CV-01064 |  | 2019-03-15
036909C-1001-DW-2058-0001-03 | Operation Tool Room - Architectural Isometric Views | A | 2019-03-04 | IFR | OL1-2K30-0042 | CV | 2019-03-15 | 036909C-JVD-TRN-01064 | 036909C-JVD-TRN-01064 | IFA | 2019-03-29 |  | Transmitted | TPSL-LSPA1-T-CV-01064 |  | 2019-03-15
036909C-1001-DW-2058-0001-01 | Operation Tool Room - Architectural Plans And Schedules | A | 2019-03-04 | IFR | OL1-2K30-0040 | CV | 2019-03-15 | 036909C-JVD-TRN-01064 | 036909C-JVD-TRN-01064 | IFA | 2019-03-29 |  | Transmitted | TPSL-LSPA1-T-CV-01064 |  | 2019-03-15
036909C-1001-DW-2058-0001-02 | Operation Tool Room - Architectural Elevations And Sections | A | 2019-03-04 | IFR | OL1-2K30-0041 | CV | 2019-03-15 | 036909C-JVD-TRN-01064 | 036909C-JVD-TRN-01064 | IFA | 2019-03-29 |  | Transmitted | TPSL-LSPA1-T-CV-01064 |  | 2019-03-15
036909C-1001-DW-2054-0001-01 | Gatehouse A - Architectural Plans An Schedules | A | 2019-03-04 | IFR | OL1-2K30-0030 | CV | 2019-03-15 | 036909C-JVD-TRN-01064 | 036909C-JVD-TRN-01064 | IFA | 2019-03-29 |  | Transmitted | TPSL-LSPA1-T-CV-01064 |  | 2019-03-15
036909C-105W-DW-0051-0001 | Detail Plot Plan - Zone 5W Waste Water Treatment | A | 2019-02-15 | IFR | OL1-2P06-0017 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15
036909C-105U-DW-0051-0001 | Detail Plot Plan - Zone 5U - Utilities | A | 2019-02-15 | IFR | OL1-2P06-0016 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15
036909C-105T-DW-0051-0001 | Detail Plot Plan - Zone 5T - Cooling Water Unit | A | 2019-02-15 | IFR | OL1-2P06-0015 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15
036909C-103A-DW-0051-0001 | Detail Plot Plan - Zone 3A - Butadiene Extraction Unit | A | 2019-02-15 | IFR | OL1-2P06-0013 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15
036909C-102E-DW-0051-0001 | Detail Plot Plan - Zone 2E - Cracked Gas Compressor | A | 2019-02-15 | IFR | OL1-2P06-0012 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15
036909C-102D-DW-0051-0001 | Detail Plot Plan - Zone 2D - Process Cold Compressor | A | 2019-02-15 | IFR | OL1-2P06-0011 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15
036909C-102C-DW-0051-0001 | Detail Plot Plan - Zone 2C - Hot Fractionation/GHU Unit | A | 2019-02-15 | IFR | OL1-2P06-0010 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15
036909C-102B-DW-0051-0001 | Detail Plot Plan - Zone 2B - C3 Hydrogenation | A | 2019-02-15 | IFR | OL1-2P06-0009 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15
036909C-102A-DW-0051-0001 | Detail Plot Plan - Zone 2A - Quench | A | 2019-02-15 | IFR | OL1-2P06-0008 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15
036909C-101B-DW-0051-0001 | Detail Plot Plan - Zone 1B - Furnaces Utilities | A | 2019-02-15 | IFR | OL1-2P06-0007 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15
036909C-103S-DW-0051-0001 | Detail Plot Plan - Zone 3S - Electrical Sub-Station And Far C | A | 2019-02-15 | IFR | OL1-2P06-0005 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15
036909C-100S-DW-0051-0001 | Detail Plot Plan - Zone 0S - Electrical Sub-Station And Far E | A | 2019-02-15 | IFR | OL1-2P06-0004 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15
036909C-100P-DW-0051-0001 | Unit Plot Plan - Zone 0P - Main Pipe Rack | A | 2019-02-15 | IFR | OL1-2P06-0003 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15
036909C-100M-DW-0051-0001 | Detail Plot Plan - Zone 0M - Metering Station | A | 2019-02-15 | IFR | OL1-2P06-0002 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15
036909C-1000-DW-0051-0001 | General Plot Plan - Draft | A | 2019-02-15 | IFR | OL1-2P06-0001 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15
036909C-1000-JSD-2300-01 | Job Design Specification For Painting | B | 2018-12-18 | IFR | OL1-2R04-0005 | MP | 2018-12-27 | 036909C-JVD-TRN-00562 | 036909C-JVD-TRN-00562, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-01-11 | 2019-01-17 | R2-Comments as noted | TPSK-LSPA1-T-MP-00562
036909C-1000-JSD-2200-01 | Job Design Specification For Thermal Insulation (Hot Service) | B | 2018-12-18 | IFR | OL1-2R04-0003 | MP | 2018-12-27 | 036909C-JVD-TRN-00562 | 036909C-JVD-TRN-00562, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-01-11 | 2019-01-17 | R2-Comments as noted | TPSK-LSPA1-T-MP-00562
036909C-1000-JSD-2200-02 | Job Design Specification For Thermal Insulation (Cold Service) | B | 2018-12-18 | IFR | OL1-2R04-0004 | MP | 2018-12-27 | 036909C-JVD-TRN-00562 | 036909C-JVD-TRN-00562, ROC-TPSK-CECO-T-00003 | IFR | 2019-01-11 | 2019-01-17 | R2-Comments as noted | TPSK-LSPA1-T-MP-00562
036909C-1026-PID-0021-2630 | P&ID - Olefins Unit 10 - Hot Fractionation - C5-Pygas Surge Drum | A | 2019-01-10 | IFR | OL1-2G43-2630 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1026-PID-0021-2629 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Bottoms Cooling | A | 2019-01-10 | IFR | OL1-2G43-2629 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-105F-DW-1920-0001 | Hazardous Area Classification - Zone 5F - HP and Ployolefins Flare Unit | A | 2019-03-07 | IFA | OL1-2L42-0014 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-105T-DW-1920-0001 | Hazardous Area Classification - Zone 5T - Cooling Water Unit | A | 2019-03-07 | IFA | OL1-2L42-0015 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-105W-DW-1920-0001 | Hazardous Area Classification - Zone 5W - Waste Water Treatment | A | 2019-03-07 | IFA | OL1-2L42-0017 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-105U-DW-1920-0001 | Hazardous Area Classification - Zone 5U - Utilities | A | 2019-03-07 | IFA | OL1-2L42-0016 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-103S-DW-1920-0001 | Hazardous Area Classification - Zone 3S -Electrical and Substation and Far C | A | 2019-03-07 | IFA | OL1-2L42-0005 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-103A-DW-1920-0001 | Hazardous Area Classification - Zone 3A - Butadiene Extraction Unit | A | 2019-03-07 | IFA | OL1-2L42-0013 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-102E-DW-1920-0001 | Hazardous Area Classification - Zone 2E - Cracked Gas Compressor | A | 2019-03-07 | IFA | OL1-2L42-0012 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-102D-DW-1920-0001 | Hazardous Area Classification - Zone 2D - Process Cold Compressor | A | 2019-03-07 | IFA | OL1-2L42-0011 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-102B-DW-1920-0001 | Hazardous Area Classification - Zone 2B - C3 Hydrogenation | A | 2019-03-07 | IFA | OL1-2L42-0009 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-102C-DW-1920-0001 | Hazardous Area Classification - Zone 2C - Hot Fractionation - GHU | A | 2019-03-07 | IFA | OL1-2L42-0010 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-102A-DW-1920-0001 | Hazardous Area Classification - Zone 2A - Quench | A | 2019-03-07 | IFA | OL1-2L42-0008 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-1024-SP-0810-2410 | Mechanical Equipment Data Sheet - Cracked Gas Dryer | C | 2019-03-07 | IFQ | OL1-2M03-2410 | ME | 2019-03-12 | 036909C-JVD-TRN-01016 | 036909C-JVD-TRN-01016 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-ME-01016 |  | 2019-03-12
036909C-101B-DW-1920-0001 | Hazardous Area Classification - Zone 1B -Furnaces Utilities | A | 2019-03-07 | IFA | OL1-2L42-0007 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-101A-DW-1920-0001 | Hazardous Area Classification - Zone 1A - Furnaces | A | 2019-03-07 | IFA | OL1-2L42-0006 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-100M-DW-1920-0001 | Hazardous Area Classification - Zone 0M - Metering Station | A | 2019-03-07 | IFA | OL1-2L42-0002 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-100S-DW-1920-0001 | Hazardous Area Classification - Zone 0S - Electrical Substation and Far E | A | 2019-03-07 | IFA | OL1-2L42-0004 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-100P-DW-1920-0001 | Hazardous Area Classification - Zone 0P - Main Pipe Rack | A | 2019-03-07 | IFA | OL1-2L42-0003 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-1000-JSS-1112-0001 | ME-020 Special Purpose Steam Tturbines | 0 | 2019-01-07 | IMP | OL1-2R03-0020 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 |  | Transmitted | TPSK-LSPA1-T-ME-00668
036909C-1000-JSS-1111-0001 | ME-018 General Purpose Steam Turbines | 0 | 2019-01-07 | IMP | OL1-2R03-0018 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 |  | Transmitted | TPSK-LSPA1-T-ME-00668
036909C-1000-JSS-1061-0001 | ME-019 Lube Oil Unit And Seal Oil System | 0 | 2019-01-07 | IMP | OL1-2R03-0019 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 |  | Transmitted | TPSK-LSPA1-T-ME-00668
036909C-1000-DW-1920-0001 | Hazardous Area Classification - Overall | A | 2019-03-07 | IFA | OL1-2L42-0001 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-1000-DW-1920-0002 | Hazardous Area Classification - Details | A | 2019-03-07 | IFA | OL1-2L42-0020 | SE | 2019-03-12 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12
036909C-1024-SP-0810-2452 | Mechanical Equipment Data Sheet - LP Depropanizer Reflux Drum | A | 2018-12-10 | IFQ | OL1-2M03-2452 | ME | 2018-12-17 | 036909C-JVD-TRN-00516 | 036909C-JVD-TRN-00516 | IFR | 2018-12-31 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00516
036909C-1023-SP-0810-2322 | Mechanical Equipment Data Sheet - Skim Oil Drum | A | 2018-12-10 | IFQ | OL1-2M03-2322 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483
036909C-1027-SP-0810-2705 | Mechanical Equipment Data Sheet - GHU-1 Hot Separator | A | 2019-02-14 | IFQ | OL1-2M03-2705 | ME | 2019-02-19 | 036909C-JVD-TRN-00893 | 036909C-JVD-TRN-00893 | IFR | 2019-03-06 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00893 |  | 2019-02-19
036909C-1022-SP-0810-2240 | Mechanical Equipment Data Sheet - CG 4th Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2240 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483
036909C-1025-SP-0810-2572 | Mechanical Equipment Data Sheet - Deethanizer Reflux Drum | A | 2018-12-10 | IFQ | OL1-2M03-2572 | ME | 2018-12-13 | 036909C-JVD-TRN-00484 | 036909C-JVD-TRN-00484 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00484
036909C-1023-SP-0810-2309 | Mechanical Equipment Data Sheet - Yellow Oil Drum | A | 2018-12-10 | IFQ | OL1-2M03-2309 | ME | 2018-12-13 | 036909C-JVD-TRN-00484 | 036909C-JVD-TRN-00484 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00484
036909C-1023-SP-0810-2310 | Mechanical Equipment Data Sheet - Spent Caustic Deoiling Drum | A | 2018-12-10 | IFQ | OL1-2M03-2310 | ME | 2018-12-17 | 036909C-JVD-TRN-00513 | 036909C-JVD-TRN-00513 | IFR | 2018-12-31 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00513
036909C-1023-SP-0810-2390 | Mechanical Equipment Data Sheet - Caustic Drain Drum | A | 2018-12-13 | IFQ | OL1-2M03-2390 | ME | 2018-12-17 | 036909C-JVD-TRN-00514 | 036909C-JVD-TRN-00514 | IFR | 2018-12-31 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00514
036909C-1025-SP-0810-2504 | Mechanical Equipment Data Sheet - Demeth Prefrac Feed Separator No 1 | A | 2018-12-06 | IFQ | OL1-2M03-2504 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483
036909C-1026-SP-0810-2662 | Mechanical Equipment Data Sheet - Debutanizer Reflux Drum | A | 2018-12-04 | IFQ | OL1-2M03-2662 | ME | 2018-12-17 | 036909C-JVD-TRN-00516 | 036909C-JVD-TRN-00516 | IFR | 2018-12-31 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00516
036909C-1028-SP-0810-2830 | Mechanical Equipment Data Sheet - C3R 3rd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2830 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483
036909C-1028-SP-0810-2820 | Mechanical Equipment Data Sheet - C3R 2nd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2820 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483
036909C-1028-SP-0810-2805 | Mechanical Equipment Data Sheet - C3R Surge Drum | A | 2018-12-05 | IFQ | OL1-2M03-2805 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483
036909C-1051-PID-0031-5120 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Carbon Filters | A | 2019-01-23 | IFR | OL1-2G43-5120 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1000-JSD-0001 | Project Design Basis | 0 | 2018-09-26 | IMP | OL1-2R07-0026 | ME | 2018-09-28 | 036909C-JVD-TRN-00110 | 036909C-JVD-TRN-00110 | IFR | 2018-10-11 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00110 |  | 2018-09-28
036909C-1000-JSD-0000-03 | JSD for PID Preparation | 0 | 2019-03-01 | IMP | OL1-2G01-0001 | PE | 2019-03-04 | 036909C-JVD-TRN-00965 | 036909C-JVD-TRN-00965, ROC-TPSK-CECO-T-00003 | IFR | 2019-03-18 |  | Transmitted | TPSK-LSPA1-T-PE-00965 |  | 2019-03-04
036909C-1051-PFD-0030-5103 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate Treatment System | B | 2018-10-09 | IFD | OL1-2G42-5103 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155
036909C-1000-JSD-0001-0002 | Units Of Measurement | 0 | 2018-09-20 | IMP | OL1-2R07-0018 | ME | 2018-09-25 | 036909C-JVD-TRN-00080 | 036909C-JVD-TRN-00080 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00080 |  | 2018-09-25
036909C-1000-DI-0007-0001 | Process Design Basis | A | 2018-07-20 | IFA | OL1-2G02-0001 | PE | 2018-07-29 | 036909C-JVD-TRN-00002 | 036909C-JVD-TRN-00002, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-10 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00002 |  | 2018-07-27
036909C-1000-PID-0090-0002 | P&ID - Olefins Unit 10 - Common - Piping Symbols | A | 2018-11-15 | IFR | OL1-2G43-0002 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323, ROC-TPSK-CECO-T-00010 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1000-PID-0090-0004 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 1 | A | 2018-11-15 | IFR | OL1-2G43-0004 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323, ROC-TPSK-CECO-T-00010 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1000-PID-0090-0003 | P&ID - Olefins Unit 10 - Common - Instrumentation Symbols | A | 2018-11-15 | IFR | OL1-2G43-0003 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323, ROC-TPSK-CECO-T-00010 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1000-PID-0090-0001 | P&ID - Olefins Unit 10 - Common - Abbreviations And Numbering | A | 2018-11-15 | IFR | OL1-2G43-0001 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323, ROC-TPSK-CECO-T-00010 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1000-PID-0090-0005 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 2 | A | 2018-11-15 | IFR | OL1-2G43-0005 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323, ROC-TPSK-CECO-T-00010 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1000-PID-0090-0010 | P&ID - Olefins Unit 10 - Common - Instrument Details | A | 2018-11-15 | IFR | OL1-2G43-0010 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323, ROC-TPSK-CECO-T-00010 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1000-DI-0007-0002 | Equipment Basis Of Design | A | 2018-07-24 | IFA | OL1-2G02-0002 | PE | 2018-07-27 | 036909C-JVD-TRN-00002 | 036909C-JVD-TRN-00002 | IFA | 2018-08-10 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00002 |  | 2018-07-27
036909C-1051-PID-0031-5162 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 3 | A | 2019-01-23 | IFR | OL1-2G43-5162 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00006, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1059-PID-0031-5928 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Lube Oil Pump Turbine B Details | A | 2019-01-28 | IFR | OL1-2G43-5928 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1059-PID-0031-5925 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Pump Turbine Details | A | 2019-01-28 | IFR | OL1-2G43-5925 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1059-PID-0031-5922 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Ctu Cooling Water Pump Turbine Details | A | 2019-01-28 | IFR | OL1-2G43-5922 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1059-PID-0031-5927 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Lube Oil Pump Turbine A Details | A | 2019-01-28 | IFR | OL1-2G43-5927 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1059-PID-0031-5915 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Condensate Pump Turbine Details | A | 2019-01-28 | IFR | OL1-2G43-5915 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1055-PID-0031-5528 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Propylene Blowdown Header - Sheet 2 | A | 2019-01-17 | IFR | OL1-2G43-5528 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5529 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 1 | A | 2019-01-17 | IFR | OL1-2G43-5529 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1059-PID-0031-5908 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Phosphate Injection System | A | 2019-01-28 | IFR | OL1-2G43-5908 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1055-PID-0031-5531 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 2 | A | 2019-01-17 | IFR | OL1-2G43-5531 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1059-PID-0031-5921 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Olefins CW Pump Turbine Details - Sheet 2 | A | 2019-01-28 | IFR | OL1-2G43-5921 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1059-PID-0031-5929 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - VLP BFW Pump Turbine Details | A | 2019-01-28 | IFR | OL1-2G43-5929 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1059-PID-0031-5930 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - VLP BFW Lube Oil Pump Turbine Details | A | 2019-01-28 | IFR | OL1-2G43-5930 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1059-PID-0031-5920 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Olefins CW Pump Turbine Details - Sheet 1 | A | 2019-01-28 | IFR | OL1-2G43-5920 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1059-PID-0031-5904 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - 98 percent Sulfuric Acid Chemical Injection | A | 2018-12-11 | IFR | OL1-2G43-5904 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00006 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1059-PID-0031-5932 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - 98 percent Sulfuric Acid Pumps | A | 2018-12-11 | IFR | OL1-2G43-5932 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00006 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1055-PID-0031-5575 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - HP Flare Package | A | 2019-01-17 | IFR | OL1-2G43-5575 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5553 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - HP Flare Pilot Gas | A | 2019-01-17 | IFR | OL1-2G43-5553 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5555 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Polyolefins Flare | A | 2019-01-17 | IFR | OL1-2G43-5555 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1059-PID-0031-5903 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - CW Hypochlorite Chemical Injection | A | 2018-12-11 | IFR | OL1-2G43-5903 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00006 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1055-PID-0031-5534 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 4 | A | 2019-01-17 | IFR | OL1-2G43-5534 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5533 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 3 | A | 2019-01-17 | IFR | OL1-2G43-5533 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1059-PID-0031-5907 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Oxygen Scavenger Injection System | A | 2019-01-28 | IFR | OL1-2G43-5907 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1055-PID-0031-5519 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - LP Flare Header - Sheet 1 | A | 2019-01-17 | IFR | OL1-2G43-5519 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1059-PID-0031-5905 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Neutralizing Amine Injection System | A | 2019-01-28 | IFR | OL1-2G43-5905 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776
036909C-1055-PID-0031-5545 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Vent Collection System - Sheet 1 | A | 2019-01-17 | IFR | OL1-2G43-5545 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5551 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - HP Flare KO Drum | A | 2019-01-17 | IFR | OL1-2G43-5551 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5546 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Vent Collection System - Sheet 2 | A | 2019-01-17 | IFR | OL1-2G43-5546 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5536 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 2 | A | 2019-01-17 | IFR | OL1-2G43-5536 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5535 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 1 | A | 2019-01-17 | IFR | OL1-2G43-5535 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5542 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 4 | A | 2019-01-17 | IFR | OL1-2G43-5542 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5540 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 3 | A | 2019-01-17 | IFR | OL1-2G43-5540 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1022-PID-0021-2206 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 2nd Stage Suction Drum | A | 2018-12-20 | IFR | OL1-2G43-2206 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1022-PID-0021-2210 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 3rd Stage Suction Drum | A | 2018-12-20 | IFR | OL1-2G43-2210 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1022-PID-0021-2208 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 2nd Stage Aftercooling | A | 2018-12-20 | IFR | OL1-2G43-2208 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1022-PID-0021-2201 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 1st Stage Suction Drum | A | 2018-12-20 | IFR | OL1-2G43-2201 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2138 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Blowdown Cooling | A | 2018-12-20 | IFR | OL1-2G43-2138 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1022-PID-0021-2204 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 1st Stage Aftercooling | A | 2018-12-20 | IFR | OL1-2G43-2204 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1022-PID-0021-2203 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 1st and 2nd Stages | A | 2018-12-20 | IFR | OL1-2G43-2203 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1023-PID-0021-2315 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Caustic Drain Collection | A | 2018-12-20 | IFR | OL1-2G43-2315 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1023-PID-0021-2314 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Drain Collection | A | 2018-12-20 | IFR | OL1-2G43-2314 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1023-PID-0021-2320 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Storage | A | 2018-12-20 | IFR | OL1-2G43-2320 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1023-PID-0021-2316 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Caustic Drain Sump | A | 2018-12-20 | IFR | OL1-2G43-2316 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1022-PID-0021-2212 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 3rd Stage Aftercooling | A | 2018-12-20 | IFR | OL1-2G43-2212 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1022-PID-0021-2211 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 3rd and 4th Stages | A | 2018-12-20 | IFR | OL1-2G43-2211 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1023-PID-0021-2313 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Degassing | A | 2018-12-20 | IFR | OL1-2G43-2313 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1023-PID-0021-2311 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Deoiling | A | 2018-12-20 | IFR | OL1-2G43-2311 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1021-PID-0021-2120 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Distillate Stripper | A | 2018-12-20 | IFR | OL1-2G43-2120 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2123 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Process Water Stripper Feed | A | 2018-12-20 | IFR | OL1-2G43-2123 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2122 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Distillate Stripper Reboiler | A | 2018-12-20 | IFR | OL1-2G43-2122 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1011-PID-0021-1129 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Drum-USX And TLX-1 Risers | B | 2019-02-12 | IBD | OL1-2G43-1129 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1128 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Shp Steam Drum | B | 2019-02-12 | IBD | OL1-2G43-1128 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1131 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Coils | B | 2019-02-12 | IBD | OL1-2G43-1131 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1130 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Boiler Feed Water Supply-Export Steam | B | 2019-02-12 | IBD | OL1-2G43-1130 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1021-PID-0021-2132 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Generator Reboilers - Sheet 1 | A | 2018-12-20 | IFR | OL1-2G43-2132 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2131 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Generator | A | 2018-12-20 | IFR | OL1-2G43-2131 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2137 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Superheating | A | 2018-12-20 | IFR | OL1-2G43-2137 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2134 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Generator Reboilers - Sheet 2 | A | 2018-12-20 | IFR | OL1-2G43-2134 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2126 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Process Water Stripper Reboiler | A | 2018-12-20 | IFR | OL1-2G43-2126 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2125 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Process Water Stripper | A | 2018-12-20 | IFR | OL1-2G43-2125 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2130 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Generator Feed Heating | A | 2018-12-20 | IFR | OL1-2G43-2130 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2127 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Generator Feed Pumps | A | 2018-12-20 | IFR | OL1-2G43-2127 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1012-PID-0021-1206 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Decoke Air Header Distribution Header | B | 2019-02-12 | IBD | OL1-2G43-1206 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1010-PID-0021-1001 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - Liquid Feed Heater | A | 2018-12-20 | IFR | OL1-2G43-1001 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1000-PID-0090-0011 | P&ID - Olefins Unit 10 - Common - EIV Block Valves Typical | A | 2018-11-15 | IFR | OL1-2G43-0011 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323, ROC-TPSK-CECO-T-00010 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323
036909C-1012-PID-0021-1201 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - C3 LPG Feed Distribution Header | B | 2019-02-12 | IBD | OL1-2G43-1201 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1205 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Dilution Steam Distribution Header | B | 2019-02-12 | IBD | OL1-2G43-1205 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1202 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Liquid Feed Distribution Header | B | 2019-02-12 | IBD | OL1-2G43-1202 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1215 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Convection Section | B | 2019-02-12 | IBD | OL1-2G43-1215 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1217 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 2 | B | 2019-02-12 | IBD | OL1-2G43-1217 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1216 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 1 | B | 2019-02-12 | IBD | OL1-2G43-1216 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1209 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 3 | B | 2019-02-12 | IBD | OL1-2G43-1209 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1212 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 6 | B | 2019-02-12 | IBD | OL1-2G43-1212 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1211 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 5 | B | 2019-02-12 | IBD | OL1-2G43-1211 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1125 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - TLX Quench Exchangers | B | 2019-02-12 | IBD | OL1-2G43-1125 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1126 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Furnace Effluent & Decoke MOV'S | B | 2019-02-12 | IBD | OL1-2G43-1126 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1120 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 5 | B | 2019-02-12 | IBD | OL1-2G43-1120 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1121 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 6 | B | 2019-02-12 | IBD | OL1-2G43-1121 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1118 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 3 | B | 2019-02-12 | IBD | OL1-2G43-1118 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1117 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 2 | B | 2019-02-12 | IBD | OL1-2G43-1117 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1140 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Burners | B | 2019-02-12 | IBD | OL1-2G43-1140 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1150 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Flue Gas & Shutdown Logic | B | 2019-02-12 | IBD | OL1-2G43-1150 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1145 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoking Effluent | B | 2019-02-12 | IBD | OL1-2G43-1145 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1119 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 4 | B | 2019-02-12 | IBD | OL1-2G43-1119 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1135 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Fuel Gas | B | 2019-02-12 | IBD | OL1-2G43-1135 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1127 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - USX Drain Header | B | 2019-02-12 | IBD | OL1-2G43-1127 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1010-PID-0021-1035 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - Cracking Furnace Distribution Utility Sheet 1 | A | 2018-12-20 | IFR | OL1-2G43-1035 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1010-PID-0021-1003 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - LPG Drum & LPG Vaporizer | A | 2018-12-20 | IFR | OL1-2G43-1003 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1010-PID-0021-1004 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - LPG Superheater | A | 2018-12-20 | IFR | OL1-2G43-1004 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1010-PID-0021-1036 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - Cracking Furnace Distribution Utility Sheet 2 | A | 2018-12-20 | IFR | OL1-2G43-1036 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1011-PID-0021-1107 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 1 | B | 2019-02-12 | IBD | OL1-2G43-1107 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1010-PID-0021-1002 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - LPG Feed Heater | A | 2018-12-20 | IFR | OL1-2G43-1002 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1011-PID-0021-1111 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 5 | B | 2019-02-12 | IBD | OL1-2G43-1111 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1105 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Dilution Steam Distribution Header | B | 2019-02-12 | IBD | OL1-2G43-1105 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1101 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed Distribution Header | B | 2019-02-12 | IBD | OL1-2G43-1101 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1110 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 4 | B | 2019-02-12 | IBD | OL1-2G43-1110 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1106 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoke Air Header Distribution Header | B | 2019-02-12 | IBD | OL1-2G43-1106 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1010-PID-0021-1030 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - Cracking Furnace Distribution - Sheet 1 | A | 2018-12-20 | IFR | OL1-2G43-1030 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1010-PID-0021-1031 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - Cracking Furnace Distribution - Sheet 2 | A | 2018-12-20 | IFR | OL1-2G43-1031 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1010-PID-0021-1005 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - LPG Steam Vaporizer | A | 2018-12-20 | IFR | OL1-2G43-1005 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1010-PID-0021-1023 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - C2 Feed Superheater | A | 2018-12-20 | IFR | OL1-2G43-1023 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1012-PID-0021-1208 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 2 | B | 2019-02-12 | IBD | OL1-2G43-1208 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1109 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 3 | B | 2019-02-12 | IBD | OL1-2G43-1109 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1108 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 2 | B | 2019-02-12 | IBD | OL1-2G43-1108 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1210 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 4 | B | 2019-02-12 | IBD | OL1-2G43-1210 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1116 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 1 | B | 2019-02-12 | IBD | OL1-2G43-1116 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1112 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 6 | B | 2019-02-12 | IBD | OL1-2G43-1112 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1207 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 1 | B | 2019-02-12 | IBD | OL1-2G43-1207 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1011-PID-0021-1115 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Convection Section | B | 2019-02-12 | IBD | OL1-2G43-1115 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1023-PID-0021-2319 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Skim Oil Drum | A | 2018-12-20 | IFR | OL1-2G43-2319 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1051-PID-0031-5150 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Steam Distribution - Sheet 01 | A | 2019-01-23 | IFR | OL1-2G43-5150 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00006, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5143 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - HP Steam Distribtion - Sheet 1 | A | 2019-01-23 | IFR | OL1-2G43-5143 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00006, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5144 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - HP Steam Distribution - Sheet 02 | A | 2019-01-23 | IFR | OL1-2G43-5144 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00006, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5151 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Steam Distribution - Sheet 2 | A | 2019-01-23 | IFR | OL1-2G43-5151 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00006, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5161 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 2 | A | 2019-01-23 | IFR | OL1-2G43-5161 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00006, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1025-PID-0021-2520 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Feed Cooling | A | 2019-01-08 | IFR | OL1-2G43-2520 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2530 | P&ID - Olefins Unit 10 - Cold Fractionation - Propylene Refrigerant Subcooler - Sheet 1 | A | 2019-01-08 | IFR | OL1-2G43-2530 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2525 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Expander Suction-Discharge Drums | A | 2019-01-08 | IFR | OL1-2G43-2525 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1024-PID-0021-2402 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Caustic Tower Overhead Ko Drum | A | 2018-12-20 | IFR | OL1-2G43-2402 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2414 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Regeneration Gas Cooling | A | 2018-12-20 | IFR | OL1-2G43-2414 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2412 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Regeneration Gas Heating | A | 2018-12-20 | IFR | OL1-2G43-2412 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1025-PID-0021-2517 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Rectifier | A | 2019-01-08 | IFR | OL1-2G43-2517 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2503 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Separator No. 1 | A | 2019-01-08 | IFR | OL1-2G43-2503 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2515 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Rectifier Condenser | A | 2019-01-08 | IFR | OL1-2G43-2515 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2522 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Reboiler | A | 2019-01-08 | IFR | OL1-2G43-2522 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1023-PID-0021-2326 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Stripper | A | 2018-12-20 | IFR | OL1-2G43-2326 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1021-PID-0021-2104 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Oil Fractionator Reflux | A | 2018-12-20 | IFR | OL1-2G43-2104 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1020-PID-0021-2026 | P&ID - Olefins Unit 10 - Quench Oil - Heavy Fuel Oil Pumps | A | 2018-12-20 | IFR | OL1-2G43-2026 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1020-PID-0021-2040 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Drain Collection | A | 2018-12-20 | IFR | OL1-2G43-2040 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1020-PID-0021-2027 | P&ID - Olefins Unit 10 - Quench Oil - Heavy Fuel Oil Product Cooling | A | 2018-12-20 | IFR | OL1-2G43-2027 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2106 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Pumps | A | 2018-12-20 | IFR | OL1-2G43-2106 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2108 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Distribution | A | 2018-12-20 | IFR | OL1-2G43-2108 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1020-PID-0021-2042 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Drain Drum | A | 2018-12-20 | IFR | OL1-2G43-2042 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2101 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Tower | A | 2018-12-20 | IFR | OL1-2G43-2101 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2115 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Drain Collection | A | 2018-12-20 | IFR | OL1-2G43-2115 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2117 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Drain Drum | A | 2018-12-20 | IFR | OL1-2G43-2117 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2110 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Cooling | A | 2018-12-20 | IFR | OL1-2G43-2110 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1021-PID-0021-2102 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Tower Overhead | A | 2018-12-20 | IFR | OL1-2G43-2102 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1012-PID-0021-1229 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Drum-SLE And TLX Risers | B | 2019-02-12 | IBD | OL1-2G43-1229 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1227 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - SLE Drain Header | B | 2019-02-12 | IBD | OL1-2G43-1227 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1228 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Shp Steam Drum | B | 2019-02-12 | IBD | OL1-2G43-1228 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1025-PID-0021-2541 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer | A | 2019-01-08 | IFR | OL1-2G43-2541 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1020-PID-0021-2022 | P&ID - Olefins Unit 10 - Quench Oil - Purge Oil Filtration | A | 2018-12-20 | IFR | OL1-2G43-2022 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1020-PID-0021-2025 | P&ID - Olefins Unit 10 - Quench Oil - Heavy Fuel Oil Stripper | A | 2018-12-20 | IFR | OL1-2G43-2025 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1012-PID-0021-1219 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 4 | B | 2019-02-12 | IBD | OL1-2G43-1219 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1020-PID-0021-2021 | P&ID - Olefins Unit 10 - Quench Oil - Fuel Oil Product Cooling | A | 2018-12-20 | IFR | OL1-2G43-2021 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1012-PID-0021-1218 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 3 | B | 2019-02-12 | IBD | OL1-2G43-1218. | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1225 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - TLX Exchanger | B | 2019-02-12 | IBD | OL1-2G43-1225 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1226 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Furnace Effluent & Decoke MOV'S | B | 2019-02-12 | IBD | OL1-2G43-1226 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1220 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 5 | B | 2019-02-12 | IBD | OL1-2G43-1220 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1221 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 6 | B | 2019-02-12 | IBD | OL1-2G43-1221 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1025-PID-0021-2513 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Reboiler | A | 2019-01-08 | IFR | OL1-2G43-2513 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2511 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Prefractionator | A | 2019-01-08 | IFR | OL1-2G43-2511 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2521 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer | A | 2019-01-08 | IFR | OL1-2G43-2521 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1012-PID-0021-1250 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Flue Gas & Shutdown Logic | B | 2019-02-12 | IBD | OL1-2G43-1250 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1025-PID-0021-2505 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Separator No. 2 | A | 2019-01-08 | IFR | OL1-2G43-2505 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2507 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Separator No. 3 | A | 2019-01-08 | IFR | OL1-2G43-2507 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2527 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Expander-Recompressor | A | 2019-01-08 | IFR | OL1-2G43-2527 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2543 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer Reboiler | A | 2019-01-08 | IFR | OL1-2G43-2543 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2532 | P&ID - Olefins Unit 10 - Cold Fractionation - Pressure Swing Absorption Unit | A | 2019-01-08 | IFR | OL1-2G43-2532 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2546 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer Condenser | A | 2019-01-08 | IFR | OL1-2G43-2546 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2529 | P&ID - Olefins Unit 10 - Cold Fractionation - Hydrogen Recovery | A | 2019-01-08 | IFR | OL1-2G43-2529 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2501 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Chilling | A | 2019-01-08 | IFR | OL1-2G43-2501 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2531 | P&ID - Olefins Unit 10 - Cold Fractionation - Propylene Refrigerant Subcooler - Sheet 2 | A | 2019-01-08 | IFR | OL1-2G43-2531 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1024-PID-0021-2442 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Reactor C | A | 2018-12-20 | IFR | OL1-2G43-2442 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2440 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Reactor B Intercooling | A | 2018-12-20 | IFR | OL1-2G43-2440 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1019-PID-0021-1901 | P&ID - Olefins Unit 10 - Furnace Auxiliaries - Dmds Injection System | A | 2018-12-20 | IFR | OL1-2G43-1901 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1024-PID-0021-2446 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - HP Depropanizer Reflux Chilling | A | 2018-12-20 | IFR | OL1-2G43-2446 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2438 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Reactor A Intercooling | A | 2018-12-20 | IFR | OL1-2G43-2438 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2447 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - HP Depropanizer Reflux | A | 2018-12-20 | IFR | OL1-2G43-2447 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1020-PID-0021-2006 | P&ID - Olefins Unit 10 - Quench Oil - VLP Steam Generation - Sheet 1 | A | 2018-12-20 | IFR | OL1-2G43-2006 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1020-PID-0021-2007 | P&ID - Olefins Unit 10 - Quench Oil - VLP Steam Generation - Sheet 2 | A | 2018-12-20 | IFR | OL1-2G43-2007 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1020-PID-0021-2020 | P&ID - Olefins Unit 10 - Quench Oil - Light Fuel Oil Stripper | A | 2018-12-20 | IFR | OL1-2G43-2020 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1024-PID-0021-2439 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Reactor B | A | 2018-12-20 | IFR | OL1-2G43-2439 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2444 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - CG Secondary Dehydrator | A | 2018-12-20 | IFR | OL1-2G43-2444 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1020-PID-0021-2005 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Filtration | A | 2018-12-20 | IFR | OL1-2G43-2005 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1023-PID-0021-2317 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Yellow Oil Drum | A | 2018-12-20 | IFR | OL1-2G43-2317 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1023-PID-0021-2310 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Fresh Caustic Supply | A | 2018-12-20 | IFR | OL1-2G43-2310 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1012-PID-0021-1231 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Coils | B | 2019-02-12 | IBD | OL1-2G43-1231 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1240 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Burners | B | 2019-02-12 | IBD | OL1-2G43-1240 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1012-PID-0021-1235 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas | B | 2019-02-12 | IBD | OL1-2G43-1235 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1023-PID-0021-2318 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Drain Sump | A | 2018-12-20 | IFR | OL1-2G43-2318 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1012-PID-0021-1230 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Boiler Feed Water Supply-Export Steam | B | 2019-02-12 | IBD | OL1-2G43-1230 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1023-PID-0021-2325 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Stripper Feed Heater Cond. Pot | A | 2018-12-20 | IFR | OL1-2G43-2325 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1022-PID-0021-2215 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 4th Stage Aftercooling | A | 2018-12-20 | IFR | OL1-2G43-2215 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1022-PID-0021-2220 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Wash Water Cooling | A | 2018-12-20 | IFR | OL1-2G43-2220 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1022-PID-0021-2217 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 4th Stage Discharge Drum | A | 2018-12-20 | IFR | OL1-2G43-2217 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1020-PID-0021-2001 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Tower | A | 2018-12-20 | IFR | OL1-2G43-2001 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1020-PID-0021-2003 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Pumps | A | 2018-12-20 | IFR | OL1-2G43-2003 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1022-PID-0021-2214 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 4th Stage Suction Drum | A | 2018-12-20 | IFR | OL1-2G43-2214 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1019-PID-0021-1915 | P&ID - Olefins Unit 10 - Furnace Auxiliaries - Decoke Air Receiver | A | 2018-12-20 | IFR | OL1-2G43-1915 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1022-PID-0021-2222 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Wash Water Injection | A | 2018-12-20 | IFR | OL1-2G43-2222 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1023-PID-0021-2301 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Caustic Tower | A | 2018-12-20 | IFR | OL1-2G43-2301 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1022-PID-0021-2224 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Wash Oil Injection | A | 2018-12-20 | IFR | OL1-2G43-2224 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566
036909C-1023-PID-0021-2305 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Strong Caustic Circulation | A | 2018-12-20 | IFR | OL1-2G43-2305 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1012-PID-0021-1245 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Flue Gas | B | 2019-02-12 | IBD | OL1-2G43-1245 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 |  | Transmitted | TPSK-LSPA1-T-PE-00850
036909C-1023-PID-0021-2303 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Weak & Intermediate Caustic Circulation | A | 2018-12-20 | IFR | OL1-2G43-2303 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1054-PID-0031-5412 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Instrument Air Distribution - Sheet 2 | A | 2019-01-28 | IFR | OL1-2G43-5412 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758
036909C-1028-PID-0021-2804 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Receiver | A | 2019-01-14 | IFR | OL1-2G43-2804 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1054-PID-0031-5410 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Instrument Air Receiver | A | 2019-01-28 | IFR | OL1-2G43-5410 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758
036909C-1028-PID-0021-2801 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 1 | A | 2019-01-14 | IFR | OL1-2G43-2801 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1054-PID-0031-5420 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 1 | A | 2019-01-28 | IFR | OL1-2G43-5420 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758
036909C-1028-PID-0021-2802 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 2 | A | 2019-01-14 | IFR | OL1-2G43-2802 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2803 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Condenser | A | 2019-01-14 | IFR | OL1-2G43-2803 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2812 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 1st Stage Suction | A | 2019-01-14 | IFR | OL1-2G43-2812 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2816 | P&ID - Olefins Unit 10 - Refrigeration System - Propylene Product Pump | A | 2019-01-14 | IFR | OL1-2G43-2816 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2805 | P&ID - Olefins Unit 10 - Refrigeration System - Hp C3 Refrigeration Distribution | A | 2019-01-14 | IFR | OL1-2G43-2805 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2814 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Drain Drum | A | 2019-01-14 | IFR | OL1-2G43-2814 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1054-PID-0031-5411 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Instrument Air Distribution - Sheet 1 | A | 2019-01-28 | IFR | OL1-2G43-5411 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758
036909C-1026-PID-0021-2622 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Tower Bottoms | A | 2019-01-10 | IFR | OL1-2G43-2622 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1026-PID-0021-2627 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Overhead | A | 2019-01-10 | IFR | OL1-2G43-2627 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1026-PID-0021-2625 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer | A | 2019-01-10 | IFR | OL1-2G43-2625 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2808 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 3rd Stage Suction | A | 2019-01-14 | IFR | OL1-2G43-2808 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2806 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 4th Stage Suction | A | 2019-01-14 | IFR | OL1-2G43-2806 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2807 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 3 | A | 2019-01-14 | IFR | OL1-2G43-2807 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2810 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 2nd Stage Suction | A | 2019-01-14 | IFR | OL1-2G43-2810 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2818 | P&ID - Olefins Unit 10 - Refrigeration System - Propylene Product Chilling - Sheet 1 | A | 2019-01-14 | IFR | OL1-2G43-2818 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2824 | P&ID - Olefins Unit 10 - Refrigeration System - C2 Refrigerant Desuperheaters | A | 2019-01-14 | IFR | OL1-2G43-2824 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1051-PID-0031-5105 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Deaerator | A | 2019-01-23 | IFR | OL1-2G43-5105 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5103 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Station - Sheet 3 | A | 2019-01-23 | IFR | OL1-2G43-5103 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5102 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Stations - Sheet 2 | A | 2019-01-23 | IFR | OL1-2G43-5102 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1050-PID-0031-5020 | P&ID - Olefins Unit 10 - Water System Treated - Potable - Demin - Potable Water | A | 2019-01-23 | IFR | OL1-2G43-5020 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1025-PID-0021-2547 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer Overhead | A | 2019-01-08 | IFR | OL1-2G43-2547 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1051-PID-0031-5101 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Stations - Sheet 1 | A | 2019-01-23 | IFR | OL1-2G43-5101 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5111 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Boiler Feedwater Pumps | A | 2019-01-23 | IFR | OL1-2G43-5111 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1026-PID-0021-2616 | P&ID - Olefins Unit 10 - Hot Fractionation - Secondary Deethanizer Overhead | A | 2019-01-10 | IFR | OL1-2G43-2616 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1051-PID-0031-5115 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Suspect Condensate Collection | A | 2019-01-23 | IFR | OL1-2G43-5115 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5113 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP & HP BFW Distribution | A | 2019-01-23 | IFR | OL1-2G43-5113 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5114 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP BFW Distribution | A | 2019-01-23 | IFR | OL1-2G43-5114 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1026-PID-0021-2615 | P&ID - Olefins Unit 10 - Hot Fractionation - Secondary Deethanizer | A | 2019-01-10 | IFR | OL1-2G43-2615 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1026-PID-0021-2603 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Arsine Guard Bed | A | 2019-01-10 | IFR | OL1-2G43-2603 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1051-PID-0031-5110 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP Boiler Feedwater Pumps | A | 2019-01-23 | IFR | OL1-2G43-5110 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1028-PID-0021-2822 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Compressor - Sheet 2 | A | 2019-01-14 | IFR | OL1-2G43-2822 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2821 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Compressor - Sheet 1 | A | 2019-01-14 | IFR | OL1-2G43-2821 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2846 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Drain Drum | A | 2019-01-14 | IFR | OL1-2G43-2846 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1026-PID-0021-2620 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Tower | A | 2019-01-10 | IFR | OL1-2G43-2620 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1025-PID-0021-2554 | P&ID - Olefins Unit 10 - Cold Fractionation - C2 Tower Side Reboiler | A | 2019-01-08 | IFR | OL1-2G43-2554 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1028-PID-0021-2842 | P&ID - Olefins Unit 10 - Refrigeration System - LP Ethylene Product Cooling | A | 2019-01-14 | IFR | OL1-2G43-2842 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1026-PID-0021-2631 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Bottoms Pumps | A | 2019-01-10 | IFR | OL1-2G43-2631 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1025-PID-0021-2552 | P&ID - Olefins Unit 10 - Cold Fractionation - C2 Tower | A | 2019-01-08 | IFR | OL1-2G43-2552 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1025-PID-0021-2553 | P&ID - Olefins Unit 10 - Cold Fractionation - C2 Tower Bottoms Reboiler | A | 2019-01-08 | IFR | OL1-2G43-2553 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1026-PID-0021-2628 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Overhead Product-Reflux | A | 2019-01-10 | IFR | OL1-2G43-2628 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1026-PID-0021-2621 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Tower Reboilers | A | 2019-01-10 | IFR | OL1-2G43-2621 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2828 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Surge Drum | A | 2019-01-14 | IFR | OL1-2G43-2828 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2830 | P&ID - Olefins Unit 10 - Refrigeration System - HP Ethylene Liquid Product Chiller | A | 2019-01-14 | IFR | OL1-2G43-2830 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1050-PID-0031-5001 | P&ID - Olefins Unit 10 - Water System Treated - Potable - Demin - Demineralized Water | A | 2019-01-23 | IFR | OL1-2G43-5001 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1028-PID-0021-2819 | P&ID - Olefins Unit 10 - Refrigeration System - Propylene Product Chilling - Sheet 2 | A | 2019-01-14 | IFR | OL1-2G43-2819 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2825 | P&ID - Olefins Unit 10 - Refrigeration System - C2R Desuperheater And Condenser | A | 2019-01-14 | IFR | OL1-2G43-2825 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2840 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant 1st Stage Suction | A | 2019-01-14 | IFR | OL1-2G43-2840 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1025-PID-0021-2551 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Bottoms | A | 2019-01-08 | IFR | OL1-2G43-2551 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1028-PID-0021-2834 | P&ID - Olefins Unit 10 - Refrigeration System - HP Ethylene Vapor Product | A | 2019-01-14 | IFR | OL1-2G43-2834 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2838 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant 2nd Stage Suction | A | 2019-01-14 | IFR | OL1-2G43-2838 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1028-PID-0021-2836 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant 3rd Stage Suction | A | 2019-01-14 | IFR | OL1-2G43-2836 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1026-PID-0021-2601 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Guard Adsorbers - Sheet 1 | A | 2019-01-10 | IFR | OL1-2G43-2601 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1026-PID-0021-2602 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Guard Adsorbers - Sheet 2 | A | 2019-01-10 | IFR | OL1-2G43-2602 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653
036909C-1024-PID-0021-2420 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - HP Depropanizer Feed Chilling | A | 2018-12-20 | IFR | OL1-2G43-2420 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2419 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Cracked Gas Mercury Adsorber | A | 2018-12-20 | IFR | OL1-2G43-2419 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2423 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - HP Depropanizer Reboiler | A | 2018-12-20 | IFR | OL1-2G43-2423 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2422 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - HP Depropanizer | A | 2018-12-20 | IFR | OL1-2G43-2422 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2407 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Liquid Driers - Sheet 2 | A | 2018-12-20 | IFR | OL1-2G43-2407 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2406 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Liquid Driers - Sheet 1 | A | 2018-12-20 | IFR | OL1-2G43-2406 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2410 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - CG Dehydration - Sheet 2 | A | 2018-12-20 | IFR | OL1-2G43-2410 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2409 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - CG Dehydration - Sheet 1 | A | 2018-12-20 | IFR | OL1-2G43-2409 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2433 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Arsine Guard Removal | A | 2018-12-20 | IFR | OL1-2G43-2433 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2432 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - CG Compressor 5th Stage Aftercooling | A | 2018-12-20 | IFR | OL1-2G43-2432 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2437 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Reactor A | A | 2018-12-20 | IFR | OL1-2G43-2437 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2435 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Feed Heating | A | 2018-12-20 | IFR | OL1-2G43-2435 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2426 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - LP Depropanizer Reboiler | A | 2018-12-20 | IFR | OL1-2G43-2426 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2425 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - LP Depropanizer | A | 2018-12-20 | IFR | OL1-2G43-2425 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2430 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - 5th Stage Cracked Gas Compression | A | 2018-12-20 | IFR | OL1-2G43-2430 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2427 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - LP Depropanizer Overhead | A | 2018-12-20 | IFR | OL1-2G43-2427 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2428 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - LP Depropanizer Product & Reflux Pumps | A | 2018-12-20 | IFR | OL1-2G43-2428 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1023-PID-0021-2328 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Stripper Ovhd Drum | A | 2018-12-20 | IFR | OL1-2G43-2328 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1025-PID-0021-2556 | P&ID - Olefins Unit 10 - Cold Fractionation - Ethane Recycle Pumps | A | 2019-01-08 | IFR | OL1-2G43-2556 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612
036909C-1050-PID-0031-5010 | P&ID - Olefins Unit 10 - Water System Treated Potable Demin - Supporting Utilities Auxiliaries Treated Water | A | 2018-12-11 | IFR | OL1-2G43-5010 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00008 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1024-PID-0021-2404 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Liquid Drier Feed Coalescer | A | 2018-12-20 | IFR | OL1-2G43-2404 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1024-PID-0021-2401 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Caustic Tower Overhead Chilling | A | 2018-12-20 | IFR | OL1-2G43-2401 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1023-PID-0021-2329 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Wet Air Oxidation Package | A | 2018-12-20 | IFR | OL1-2G43-2329 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567
036909C-1051-PID-0031-5130 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Tank | A | 2019-01-23 | IFR | OL1-2G43-5130 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5127 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Polisher - Sheet 1 | A | 2019-01-23 | IFR | OL1-2G43-5127 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5128 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Polisher - Sheet 2 | A | 2019-01-23 | IFR | OL1-2G43-5128 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5152 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Steam Distribution - Sheet 3 | A | 2019-01-23 | IFR | OL1-2G43-5152 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5160 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 1 | A | 2019-01-23 | IFR | OL1-2G43-5160 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5132 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Low Pressure Steam Flash Drum | A | 2019-01-23 | IFR | OL1-2G43-5132 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5140 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP Steam Distribution | A | 2019-01-23 | IFR | OL1-2G43-5140 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5134 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Furnace Blowdown System | A | 2019-01-23 | IFR | OL1-2G43-5134 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1055-PID-0031-5520 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 1 | A | 2019-01-17 | IFR | OL1-2G43-5520 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5521 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 2 | A | 2019-01-17 | IFR | OL1-2G43-5521 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5516 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 5 | A | 2019-01-17 | IFR | OL1-2G43-5516 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5518 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 6 | A | 2019-01-17 | IFR | OL1-2G43-5518 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5526 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Propylene Blowdown Header - Sheet 1 | A | 2019-01-17 | IFR | OL1-2G43-5526 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1051-PID-0031-5125 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Raw Condensate Tank | A | 2019-01-23 | IFR | OL1-2G43-5125 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1055-PID-0031-5523 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 3 | A | 2019-01-17 | IFR | OL1-2G43-5523 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5524 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 4 | A | 2019-01-17 | IFR | OL1-2G43-5524 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5510 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 1 | A | 2019-01-17 | IFR | OL1-2G43-5510 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1054-PID-0031-5424 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 4 | A | 2019-01-28 | IFR | OL1-2G43-5424 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758
036909C-1055-PID-0031-5512 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 3 | A | 2019-01-17 | IFR | OL1-2G43-5512 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1054-PID-0031-5426 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 6 | A | 2019-01-28 | IFR | OL1-2G43-5426 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758
036909C-1054-PID-0031-5425 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 5 | A | 2019-01-28 | IFR | OL1-2G43-5425 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758
036909C-1055-PID-0031-5511 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 2 | A | 2019-01-17 | IFR | OL1-2G43-5511 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1055-PID-0031-5514 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 4 | A | 2019-01-17 | IFR | OL1-2G43-5514 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1053-PID-0031-5351 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Chemical Injection | A | 2018-12-11 | IFR | OL1-2G43-5351 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1054-PID-0031-5421 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 2 | A | 2019-01-28 | IFR | OL1-2G43-5421 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758
036909C-1055-PID-0031-5502 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Drum | A | 2019-01-17 | IFR | OL1-2G43-5502 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1053-PID-0031-5352 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Corrosion Inhibitor Injection | A | 2018-12-11 | IFR | OL1-2G43-5352 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1055-PID-0031-5501 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Flare Drum | A | 2019-01-17 | IFR | OL1-2G43-5501 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1053-PID-0031-5307 | P&ID - Olefins Unit 10 - Cooling Water - CTU Cooling Water Supply Pumps | A | 2018-12-11 | IFR | OL1-2G43-5307 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1053-PID-0031-5310 | P&ID - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply | A | 2018-12-11 | IFR | OL1-2G43-5310 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1053-PID-0031-5326 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 07 | A | 2018-12-11 | IFR | OL1-2G43-5326 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1053-PID-0031-5325 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 06 | A | 2018-12-11 | IFR | OL1-2G43-5325 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1051-PID-0031-5118 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Suspect Condensate Cooling | A | 2019-01-23 | IFR | OL1-2G43-5118 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1053-PID-0031-5302 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 2 | A | 2018-12-11 | IFR | OL1-2G43-5302 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1053-PID-0031-5305 | P&ID - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 1 | A | 2018-12-11 | IFR | OL1-2G43-5305 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1053-PID-0031-5303 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 3 | A | 2018-12-11 | IFR | OL1-2G43-5303 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1054-PID-0031-5422 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 3 | A | 2019-01-28 | IFR | OL1-2G43-5422 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758
036909C-1055-PID-0031-5503 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Methanol Vaporizer | A | 2019-01-17 | IFR | OL1-2G43-5503 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706
036909C-1053-PID-0031-5306 | P&ID - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 2 | A | 2018-12-11 | IFR | OL1-2G43-5306 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1053-PID-0031-5301 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 1 | A | 2018-12-11 | IFR | OL1-2G43-5301 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1051-PID-0031-5178 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 3 | A | 2019-01-23 | IFR | OL1-2G43-5178 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1053-PID-0031-5311 | P&ID - Olefins Unit 10 - Cooling Water - Ctu Cooling Water Supply | A | 2018-12-11 | IFR | OL1-2G43-5311 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1051-PID-0031-5177 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 2 | A | 2019-01-23 | IFR | OL1-2G43-5177 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5176 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 1 | A | 2019-01-23 | IFR | OL1-2G43-5176 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1054-PID-0031-5403 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 3 | A | 2019-01-28 | IFR | OL1-2G43-5403 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758
036909C-1054-PID-0031-5402 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 2 | A | 2019-01-28 | IFR | OL1-2G43-5402 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758
036909C-1051-PID-0031-5179 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Condensate Collection | A | 2019-01-23 | IFR | OL1-2G43-5179 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1054-PID-0031-5404 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 4 | A | 2019-01-28 | IFR | OL1-2G43-5404 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758
036909C-1054-PID-0031-5401 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 1 | A | 2019-01-28 | IFR | OL1-2G43-5401 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758
036909C-1051-PID-0031-5172 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Condensate Collection | A | 2019-01-23 | IFR | OL1-2G43-5172 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5170 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP - HP Condensate Collection | A | 2019-01-23 | IFR | OL1-2G43-5170 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1053-PID-0031-5323 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 04 | A | 2018-12-11 | IFR | OL1-2G43-5323 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1053-PID-0031-5324 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 05 | A | 2018-12-11 | IFR | OL1-2G43-5324 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1051-PID-0031-5164 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 5 | A | 2019-01-23 | IFR | OL1-2G43-5164 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5163 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 4 | A | 2019-01-23 | IFR | OL1-2G43-5163 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5168 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Steam Ls2 Distribution - Sheet 1 | A | 2019-01-23 | IFR | OL1-2G43-5168 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1051-PID-0031-5166 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 6 | A | 2019-01-23 | IFR | OL1-2G43-5166 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718
036909C-1053-PID-0031-5320 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 01 | A | 2018-12-11 | IFR | OL1-2G43-5320 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1053-PID-0031-5315 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Side Stream Filter Package | A | 2018-12-11 | IFR | OL1-2G43-5315 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1053-PID-0031-5317 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Filter Backwash | A | 2018-12-11 | IFR | OL1-2G43-5317 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1053-PID-0031-5322 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 03 | A | 2018-12-11 | IFR | OL1-2G43-5322 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1053-PID-0031-5321 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 02 | A | 2018-12-11 | IFR | OL1-2G43-5321 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491
036909C-1024-SP-0810-2410 | Mechanical Equipment Data Sheet - Cracked Gas Dryer | B | 2019-02-26 | IFQ | OL1-2M03-2410 | ME | 2019-03-04 | 036909C-JVD-TRN-00972 | 036909C-JVD-TRN-00972 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-ME-00972 |  | 2019-03-04
036909C-1024-SP-0810-2410 | Mechanical Equipment Data Sheet - Cracked Gas Dryer | A | 2019-01-21 | IFQ | OL1-2M03-2410 | ME | 2019-01-22 | 036909C-JVD-TRN-00700 | 036909C-JVD-TRN-00700 | IFR | 2019-02-04 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00700
036909C-1012-JSS-0132-2006 | Project Specification for Supply and Installation of Refractory Insulation and Cracking Furnaces | A | 2019-02-04 | IFR | OL1-2M92-2006 | ME | 2019-02-12 | 036909C-JVD-TRN-00842 | 036909C-JVD-TRN-00842 | IFR | 2019-02-26 | 2019-03-07 | R1-No comments | TPSK-LSPA1-T-ME-00842
036909C-1012-JSS-0132-2005 | Project Specification for Supply and Installation of Ceramics Fiber Blanket and Ceramics Fiber Modules | A | 2019-02-04 | IFR | OL1-2M92-2005 | ME | 2019-02-12 | 036909C-JVD-TRN-00842 | 036909C-JVD-TRN-00842 | IFR | 2019-02-26 | 2019-03-07 | R1-No comments | TPSK-LSPA1-T-ME-00842
036909C-1012-DW-0127-2204 | USC 132U Cracking Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill of Material | 0 | 2019-02-11 | IMP | OL1-2M06-2204 | ME | 2019-02-13 | 036909C-JVD-TRN-00848 | 036909C-JVD-TRN-00848 | IFR | 2019-02-27 | 2019-03-07 | R1-No comments | TPSK-LSPA1-T-ME-00848
036909C-1011-DW-0127-1204 | USC 36M Recycle Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill of Material | 0 | 2019-02-11 | IMP | OL1-2M06-1204 | ME | 2019-02-13 | 036909C-JVD-TRN-00848 | 036909C-JVD-TRN-00848 | IFR | 2019-02-27 | 2019-03-07 | R1-No comments | TPSK-LSPA1-T-ME-00848
036909C-1000-STC-1490-0001 | Standard Construction Drawings For Underground Systems - Ex Document Client Reference OL1-2K23-0001 | 0 | 2019-01-30 | IFC | OL1-2K24-0001 | CV | 2019-02-06 | 036909C-JVD-TRN-00806 | 036909C-JVD-TRN-00806, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-20 |  | Transmitted | TPSK-LSPA1-T-CV-00806 | Ex Document Client Reference OL1-2K23-0001
036909C-1000-STC-1890-0001 | Construction Standards For Steel Structures | 0 | 2019-02-27 | IFC | OL1-2K21-0001 | CV | 2019-03-07 | 036909C-JVD-TRN-00996 | 036909C-JVD-TRN-00996, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFA | 2019-03-21 |  | Transmitted | TPSK-LSPA1-T-CV-00996 |  | 2019-03-07
036909C-1000-STC-1790-0001 | Construction Standards For Reinforced Concrete Works | 0 | 2019-02-26 | IFC | OL1-2K20-0001 | CV | 2019-03-07 | 036909C-JVD-TRN-00997 | 036909C-JVD-TRN-00997, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFA | 2019-03-21 |  | Transmitted | TPSK-LSPA1-T-CV-00997 |  | 2019-03-07
036909C-1000-JSD-1600-0007 | Functional and Schematic Diagram | 0 | 2018-09-20 | IMP | OL1-2R05-0029 | EE | 2018-11-05 | 036909C-JVD-TRN-00258 | 036909C-JVD-TRN-00258, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00258
036909C-1000-JSD-1511-0001 | Instrument Cabinet | 0 | 2019-02-27 | IMP | OL1-2R06-0016 | IE | 2019-03-06 | 036909C-JVD-TRN-00986 | 036909C-JVD-TRN-00986, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-03-20 |  | Transmitted | TPSK-LSPA1-T-IE-00986 |  | 2019-03-06
036909C-1000-JSD-1900-0001 | Fire Fighting And Fire Protection | A | 2019-01-30 | IFR | OL1-2L01-0001 | PE | 2019-02-01 | 036909C-JVD-TRN-00782 | 036909C-JVD-TRN-00782, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-18 |  | Transmitted | TPSK-LSPA1-T-PE-00782
036909C-1000-JSD-1515-0001 | General Design Rules For SIS Safety Requirements Specification | A | 2019-01-23 | IFR | OL1-2I61-1102 | IE | 2019-01-25 | 036909C-JVD-TRN-00719 | 036909C-JVD-TRN-00719, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-08 | 2019-03-05 | R2-Comments as noted | TPSK-LSPA1-T-IE-00719
036909C-1000-JSD-1580-0001 | Integrated Turbine And Compressor Control System | 0 | 2018-12-14 | IMP | OL1-2R06-0017 | IE | 2018-12-17 | 036909C-JVD-TRN-00507 | 036909C-JVD-TRN-00507, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-28 | 2018-12-26 | R1-No comments | TPSK-LSPA1-T-IE-00507
036909C-1000-JSD-1600-0006 | Protective Relay And Control Unit | 0 | 2018-12-13 | IMP | OL1-2R05-0004 | EE | 2018-12-20 | 036909C-JVD-TRN-00522 | 036909C-JVD-TRN-00522, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00522
036909C-1000-JSD-1400-0001 | Job Design Specification For Underground Systems | 0 | 2019-03-04 | IMP | OL1-2R02-0001 | CV | 2019-03-07 | 036909C-JVD-TRN-00994 | 036909C-JVD-TRN-00994, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-03-21 |  | Transmitted | TPSK-LSPA1-T-CV-00994 |  | 2019-03-07
036909C-1000-JSD-1522-0001 | Electrical And Instrument Interface Philosophy | 0 | 2018-12-14 | IMP | OL1-2R07-0020 | IE | 2018-12-17 | 036909C-JVD-TRN-00507 | 036909C-JVD-TRN-00507, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-28 | 2018-12-26 | R1-No comments | TPSK-LSPA1-T-IE-00507
036909C-1000-JSD-1511-0002 | Integrated Control And Safety System | A | 2018-11-20 | IFR | OL1-2R06-0015 | IE | 2018-11-26 | 036909C-JVD-TRN-00357 | 036909C-JVD-TRN-00357, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-11 | 2019-02-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-00357
036909C-1000-JSD-1584-0001 | Custody Transfer System | A | 2018-11-20 | IFR | OL1-2R06-3101 | IE | 2018-11-26 | 036909C-JVD-TRN-00357 | 036909C-JVD-TRN-00357, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-11 | 2019-02-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-00357
036909C-1000-JSD-1501-0002 | General Design Rules For SmartPlant Instrumentation Setup | B | 2018-10-24 | IFR | OL1-2R06-0024 | IE | 2018-11-08 | 036909C-JVD-TRN-00291 | 036909C-JVD-TRN-00291, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-11-23 | 2019-02-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-00291
036909C-1000-JSD-1600-0002 | Electrical System Design | 0 | 2018-12-03 | IMP | OL1-2R05-0002 | EE | 2018-12-05 | 036909C-JVD-TRN-00424 | 036909C-JVD-TRN-00424, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00424
036909C-1000-JSD-2000-0001 | Buildings Design And Construction | A | 2018-10-10 | IFR | OL1-2R02-0005 | CV | 2018-10-11 | 036909C-JVD-TRN-00158 | 036909C-JVD-TRN-00158, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-10-25 |  | Transmitted | TPSK-LSPA1-T-CV-00158
036909C-1000-JSD-1580-0002 | Progammable Logic Controller | A | 2018-11-07 | IFR | OL1-2R06-1301 | IE | 2018-11-08 | 036909C-JVD-TRN-00291 | 036909C-JVD-TRN-00291, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-11-23 | 2019-02-01 | R1-No comments | TPSK-LSPA1-T-IE-00291
036909C-1000-JSD-1980-0001 | Fire Proof | A | 2019-01-18 | IFR | OL1-2L01-0002 | PE | 2019-01-29 | 036909C-JVD-TRN-00749 | 036909C-JVD-TRN-00749, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-13 |  | Transmitted | TPSK-LSPA1-T-PE-00749
036909C-1000-JSD-1515-0004 | Machinery Monitoring System | 0 | 2019-02-18 | IMP | OL1-2R06-0013 | IE | 2019-02-19 | 036909C-JVD-TRN-00889 | 036909C-JVD-TRN-00889, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-03-06 | 2019-03-08 | R1-No comments | TPSK-LSPA1-T-IE-00889 |  | 2019-02-19
036909C-1000-JSD-1510-0001 | General Design Rules For Control and Safety Philosophy | A | 2019-01-29 | IFR | OL1-2R06-1025 | IE | 2019-01-29 | 036909C-JVD-TRN-00750 | 036909C-JVD-TRN-00750, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-13 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-IE-00750
036909C-1000-JSD-1300-0008 | JSD For Piping Stress Analysis | 0 | 2019-02-14 | IMP | OL1-2R04-0032 | MP | 2019-02-19 | 036909C-JVD-TRN-00881 | 036909C-JVD-TRN-00881, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-18 |  | Transmitted | TPSK-LSPA1-T-MP-00881 |  | 2019-02-19
036909C-1000-JSD-1300-0003 | A1 Scope Annex C– Ppiping Specification PIP-006 Steam Tracing Piping | 0 | 2019-01-25 | IMP | OL1-2R04-0031 | MP | 2019-01-28 | 036909C-JVD-TRN-00736 | 036909C-JVD-TRN-00736, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-12 | 2019-03-01 | R2-Comments as noted | TPSK-LSPA1-T-MP-00736
036909C-1006-JSS-0117-0024 | ME-024 Elevator For 36M and 132U Furnace | 0 | 2018-12-18 | IMP | OL1-2R03-0024 | ME | 2018-12-20 | 036909C-JVD-TRN-00537 | 036909C-JVD-TRN-00537, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00537
036909C-1006-JSS-0117-0029 | ME-029 Centrifugal Blower for 36M and 132U Furnace | 0 | 2018-10-16 | IMP | OL1-2R03-0029 | ME | 2018-10-17 | 036909C-JVD-TRN-00185 | 036909C-JVD-TRN-00185, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFI |  | 2018-11-05 | Transmitted | TPSK-LSPA1-T-ME-00185
036909C-1006-JSS-0117-3001 | ME-001 Pressure Vessel for 36M and 132U Furnace | 0 | 2018-10-18 | IFE | OL1-2R03-1001 | ME | 2018-11-07 | 036909C-JVD-TRN-00262 | 036909C-JVD-TRN-00262, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00262
036909C-1006-JSS-0117-3004 | ME-004 Shell and Tube Heat Exchangers for 36M and 132U Furnace | 0 | 2018-10-18 | IFI | OL1-2R03-1004 | ME | 2018-10-24 | 036909C-JVD-TRN-00221 | 036909C-JVD-TRN-00221, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00221
036909C-1006-JSS-0117-0005 | ME-005 Double Jacket Pipe Heat Exchangers for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL1-2R03-0005 | ME | 2018-10-23 | 036909C-JVD-TRN-00212 | 036909C-JVD-TRN-00212, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00212
036909C-1000-JSD-1530-0001 | Intercom-Paging-Audible Alarm System | 0 | 2019-02-19 | IMP | OL1-2R05-0013 | EE | 2019-03-06 | 036909C-JVD-TRN-00987 | 036909C-JVD-TRN-00987, ROC-TPSK-CECO-T-00003 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-EE-00987 |  | 2019-03-06
036909C-1000-JSS-1384-0001 | General Supply Rules For Sliding Plates | A | 2019-02-04 | IFR | OL1-2R04-0038 | MP | 2019-02-08 | 036909C-JVD-TRN-00831 | 036909C-JVD-TRN-00831, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 |  | Transmitted | TPSK-LSPA1-T-MP-00831
036909C-1000-JSS-1383-0001 | General Supply Rules For Rod And Spring Hangers | A | 2019-02-04 | IFR | OL1-2R04-0037 | MP | 2019-02-08 | 036909C-JVD-TRN-00831 | 036909C-JVD-TRN-00831, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 |  | Transmitted | TPSK-LSPA1-T-MP-00831
036909C-1000-JSS-1530-0002 | Job Supply Specification For Safety Supervisory System - Ex Document Client Reference OL1-2T92-0002 | B | 2019-02-26 | IFR | OL1-2T01-0002 | EE | 2019-03-07 | 036909C-JVD-TRN-00985 | 036909C-JVD-TRN-00985, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFA | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-EE-00985 | Ex Document Client Reference: OL1-2T92-0002 | 2019-03-06
036909C-1000-JSD-1530-0002 | Safety Supervisory System | 0 | 2019-03-04 | IMP | OL1-2R05-0019 | EE | 2019-03-07 | 036909C-JVD-TRN-00987 | 036909C-JVD-TRN-00987, ROC-TPSK-CECO-T-00003 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-EE-00987 |  | 2019-03-06
036909C-1000-JSS-1382-0001 | General Supply Rules For Polyurethane Piping Supports | A | 2019-02-04 | IFR | OL1-2R04-0036 | MP | 2019-02-08 | 036909C-JVD-TRN-00831 | 036909C-JVD-TRN-00831, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 |  | Transmitted | TPSK-LSPA1-T-MP-00831
036909C-1000-JSS-1530-0001 | Job Supply Specification For Intercom Paging And Audible Alarm System -Ex Document Client Reference OL1-2T92-0001 | 0 | 2019-02-26 | IMP | OL1-2T01-0001 | EE | 2019-03-07 | 036909C-JVD-TRN-00985 | 036909C-JVD-TRN-00985, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFA | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-EE-00985 | Ex Document Client Reference: OL1-2T92-0001 | 2019-03-06
036909C-1000-JSS-1040-0001 | ME-017 Root Blower | 0 | 2018-11-16 | IMP | OL1-2R03-0017 | ME | 2018-11-19 | 036909C-JVD-TRN-00334 | 036909C-JVD-TRN-00334, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00334
036909C-1000-JSS-0184-0001 | ME-021 Flare System | A | 2018-11-29 | IFR | OL1-2R03-0021 | ME | 2018-12-06 | 036909C-JVD-TRN-00429 | 036909C-JVD-TRN-00429, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2018-12-20 | 2018-12-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00429
036909C-1000-JSS-0310-0001 | ME-008 Cooling Water | A | 2018-10-30 | IFQ | OL1-2R03-0104 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2018-11-19 | 2019-02-15 | Transmitted | TPSK-LSPA1-T-ME-00276
036909C-1000-JSS-1386-0001 | General Supply Rules For Dynamic Piping Supports | A | 2019-02-04 | IFR | OL1-2R04-0039 | MP | 2019-02-08 | 036909C-JVD-TRN-00831 | 036909C-JVD-TRN-00831, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 |  | Transmitted | TPSK-LSPA1-T-MP-00831
036909C-1000-JSS-0660-01 | Plate Heat Exchanger | 0 | 2018-09-10 | IMP | OL1-2R03-0006 | ME | 2018-09-13 | 036909C-JVD-TRN-00042 | 036909C-JVD-TRN-00042, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00042 |  | 2018-09-13
036909C-1000-JSS-0900-0001 | ME-028 Mechanical Seal | 0 | 2018-09-14 | IMP | OL1-2R03-0028 | ME | 2018-09-18 | 036909C-JVD-TRN-00057 | 036909C-JVD-TRN-00057, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00057 |  | 2018-09-18
036909C-1000-JSS-1391-0001 | General Supply Rules For Metallic Expansion Joints | A | 2019-02-04 | IFR | OL1-2R04-0040 | MP | 2019-02-08 | 036909C-JVD-TRN-00831 | 036909C-JVD-TRN-00831, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 |  | Transmitted | TPSK-LSPA1-T-MP-00831
036909C-1000-JSD-1300-0010 | JSD For Auxiliary Piping Supports | 0 | 2019-03-06 | IMP | OL1-2R04-0034 | MP | 2019-03-08 | 036909C-JVD-TRN-01002 | 036909C-JVD-TRN-01002, ROC-TPSK-CECO-T-00003 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-MP-01002 |  | 2019-03-08
036909C-1000-JSD-1300-0011 | Piping Flexibility | 0 | 2019-02-04 | IMP | OL1-2R04-0030 | MP | 2019-02-08 | 036909C-JVD-TRN-00828 | 036909C-JVD-TRN-00828, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-MP-00828
036909C-1000-JSD-1300-0009 | JSD for Piping Loads On PRK SLW STR IS | 0 | 2019-02-04 | IMP | OL1-2R04-0033 | MP | 2019-02-08 | 036909C-JVD-TRN-00828 | 036909C-JVD-TRN-00828, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-MP-00828
036909C-1000-JSD-1300-0012 | Pipe Support | 0 | 2019-02-04 | IMP | OL1-2R04-0012 | MP | 2019-02-08 | 036909C-JVD-TRN-00828 | 036909C-JVD-TRN-00828, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-MP-00828
036909C-1000-DW-1702-0001 | General Notes For Concrete Works | 0 | 2019-02-12 | IFC | OL1-2K92-0003 | CV | 2019-02-19 | 036909C-JVD-TRN-00886 | 036909C-JVD-TRN-00886, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFA | 2019-03-06 |  | Transmitted | TPSK-LSPA1-T-CV-00886 |  | 2019-02-19
036909C-1000-DW-1802-0001 | General Notes For Steel Structure | 1 | 2019-03-01 | IFC1 | OL1-2K92-0004 | CV | 2019-03-07 | 036909C-JVD-TRN-00993 | 036909C-JVD-TRN-00993, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFA | 2019-03-21 |  | Transmitted | TPSK-LSPA1-T-CV-00993 |  | 2019-03-07
036909C-1000-DW-1402-0001 | General Notes For Underground Works | 0 | 2019-01-30 | IFC | OL1-2K92-0001 | CV | 2019-02-01 | 036909C-JVD-TRN-00784 | 036909C-JVD-TRN-00784, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-18 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-CV-00784 |  | 2019-02-01
036909C-1011-DW-1514-1001 | Cause and Effect Diagram Cracking Furnaces | A | 2019-01-15 | IFR | OL1-2I72-1001 | IE | 2019-01-17 | 036909C-JVD-TRN-00674 | 036909C-JVD-TRN-00674 | IFR | 2019-01-31 | 2019-03-08 | R1-No comments | TPSK-LSPA1-T-IE-00674
036909C-1020-DI-0007-2001 | Area Basis of Design - 20-21 Quench and Dilution Steam | A | 2018-08-06 | IFA | OL1-2G05-2001 | PE | 2018-08-08 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | 2018-08-08
036909C-1000-DI-0007-0006 | Furnace Process Basis of Design | B | 2018-11-27 | IFD | OL1-2G02-0006 | PE | 2018-11-27 | 036909C-JVD-TRN-00376 | 036909C-JVD-TRN-00376, ROC-TPSK-CECO-T-00001 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00376
036909C-1025-DI-0007-2501 | Area Basis of Design - 25 Cold Fractionation | A | 2018-08-06 | IFA | OL1-2G05-2501 | PE | 2018-08-08 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | 2018-08-08
036909C-1026-DI-0007-2602 | Area Basis of Design - 262 C3 Hydrogenation | A | 2018-11-09 | IFA | OL1-2G05-2602 | PE | 2018-11-12 | 036909C-JVD-TRN-00307 | 036909C-JVD-TRN-00307, ROC-TPSK-CECO-T-00001 | IFA | 2018-11-26 | 2019-02-04 | A1-Approved without comments | TPSK-LSPA1-T-PE-00307
036909C-1028-DI-0007-2801 | Area Basis of Design - 28 Refrigeration | A | 2018-08-09 | IFA | OL1-2G05-2801 | PE | 2018-08-15 | 036909C-JVD-TRN-00022 | 036909C-JVD-TRN-00022, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-27 | 2018-09-05 | A1-Approved without comments | TPSK-LSPA1-T-PE-00022 |  | 2018-08-15
036909C-1026-DI-0007-2601 | Area Basis of Design - 26 Hot Fractionation | A | 2018-08-07 | IFA | OL1-2G05-2601 | PE | 2018-08-09 | 036909C-JVD-TRN-00014 | 036909C-JVD-TRN-00014, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-22 | 2018-08-31 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00014 |  | 2018-08-09
036909C-1023-DI-0007-2301 | Area Basis of Design - 23 Caustic and Spent Caustic Pretreatment | A | 2018-08-08 | IFA | OL1-2G05-2301 | PE | 2018-08-09 | 036909C-JVD-TRN-00014 | 036909C-JVD-TRN-00014, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-22 | 2018-08-31 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00014 |  | 2018-08-09
036909C-1053-DI-0007-5301 | Area Basis of Design - 53 Cooling Tower System | B | 2018-09-24 | IFD | OL1-2G05-5301 | PE | 2018-09-27 | 036909C-JVD-TRN-00093 | 036909C-JVD-TRN-00093, ROC-TPSK-CECO-T-00001 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00003 |  | 2018-09-27
036909C-1027-DI-0007-2702 | Area Basis of Design - Area 275 C4-C5 Hydrogenation | A | 2018-11-09 | IFA | OL1-2G05-2702 | PE | 2018-11-12 | 036909C-JVD-TRN-00307 | 036909C-JVD-TRN-00307, ROC-TPSK-CECO-T-00001 | IFA | 2018-11-26 | 2019-02-04 | A1-Approved without comments | TPSK-LSPA1-T-PE-00307
036909C-1056-PDS-0200-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg | C | 2019-02-01 | IFD | OL1-2G30-5653 | PE | 2019-02-01 | 036909C-JVD-TRN-00798 | 036909C-JVD-TRN-00798 | IFI |  | 2019-03-11 | R1-No comments | TPSK-LSPA1-T-PE-00798
036909C-1000-JSS-1391-0002 | Job Supply Specification For Non Metallic Expansion Joints | A | 2019-03-06 | IFR | OL1-2R04-0042 | MP | 2019-03-08 | 036909C-JVD-TRN-01000 | 036909C-JVD-TRN-01000, ROC-TPSK-CECO-T-00004 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-MP-01000 |  | 2019-03-08
036909C-1000-QCP-6882-0001 | Quality Control Plan Bridge Crane Installation | A | 2019-03-06 | IFR | OL1-2Q23-0022 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-QCP-6880-0002 | Quality Control Plan Skid Mounted Packages | A | 2019-03-05 | IFR | OL1-2Q23-0021 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-QCP-6860-0002 | Quality Control Plan Equipment Internals Installation - Distributors-Grids-Demisters-etc | A | 2019-03-04 | IFR | OL1-2Q23-0017 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-QCP-6880-0001 | Quality Control Plan Packages Installation | A | 2019-03-04 | IFR | OL1-2Q23-0020 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-QCP-6872-0001 | Quality Control Plan Cooling Tower Mechanical Installation | A | 2019-03-04 | IFR | OL1-2Q23-0019 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-QCP-6852-0001 | Quality Control Plan Elevator Installation | A | 2019-03-04 | IFR | OL1-2Q23-0015 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-QCP-6850-0005 | Quality Control Plan Machinery Installation - Mixers and Agitators | A | 2019-03-04 | IFR | OL1-2Q23-0014 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-QCP-6860-0001 | Quality Control Plan Equipment Internals Installation - Trays | A | 2019-03-04 | IFR | OL1-2Q23-0016 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-QCP-6850-0003 | Quality Control Plan Machinery Installation - Centrifugal Compressors | A | 2019-02-28 | IFR | OL1-2Q23-0012 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-QCP-6850-0004 | Quality Control Plan Machinery Installation - Reciprocating Compressors | A | 2019-03-04 | IFR | OL1-2Q23-0013 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-QCP-6850-0002 | Quality Control Plan Machinery Installation - Blower and Fans | A | 2019-03-04 | IFR | OL1-2Q23-0011 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-QCP-6835-0001 | Quality Control Plan Refractory Installation | A | 2019-02-28 | IFR | OL1-2Q23-0009 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-QCP-6833-0001 | Quality Control Plan Flare System Erection | A | 2019-02-28 | IFR | OL1-2Q23-0008 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-QCP-6850-0001 | Quality Control Plan Machinery Installation - Centrifugal and Rotary Pumps | A | 2019-03-04 | IFR | OL1-2Q23-0010 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-QCP-6831-0001 | Quality Control Plan Package Furnace - Site Assembled - Installation | A | 2019-02-28 | IFR | OL1-2Q23-0007 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-QCP-6820-0001 | Quality Control Plan Static Equipment Installation | A | 2019-02-28 | IFR | OL1-2Q23-0006 | QM | 2019-03-11 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11
036909C-1000-DW-1522-0002 | Instrument And Telecom Grounding Philosophy Diagram | A | 2019-03-05 | IFR | OL1-2I48-1001 | IE | 2019-03-11 | 036909C-JVD-TRN-01013 | 036909C-JVD-TRN-01013 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-IE-01013 |  | 2019-03-11
036909C-1000-DW-1512-0001 | Control And Safety Systems Connection Diagram | A | 2019-03-08 | IFR | OL1-2I81-1001 | IE | 2019-03-11 | 036909C-JVD-TRN-01012 | 036909C-JVD-TRN-01012 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-IE-01012 |  | 2019-03-11
036909C-1000-JSD-1572-0003 | Instrument Air Supply | A | 2018-11-20 | IFR | OL1-2R06-0011 | IE | 2018-11-26 | 036909C-JVD-TRN-00357 | 036909C-JVD-TRN-00357 | IFR | 2018-12-11 | 2019-02-01 | R1-No comments | TPSK-LSPA1-T-IE-00357
036909C-1055-PDS-0180-5560 | Process Equipment Datasheet - 10-PK-5560 - HP - Polyolefins Flare Pkg | B | 2019-03-07 | IFD | OL1-2G30-5560 | PE | 2019-03-08 | 036909C-JVD-TRN-01007 | 036909C-JVD-TRN-01007 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-PE-01007 |  | 2019-03-08
036909C-1025-PDS-1000-2550 | Process Equipment Datasheet - 10-TX-2550 - 10-C-2550 - Residue Gas Expander - Recompressor | B | 2018-09-28 | IFD | OL1-2G30-2550 | PE | 2018-10-01 | 036909C-JVD-TRN-00114 | 036909C-JVD-TRN-00114 | IFI |  | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-PE-00114 |  | 2018-10-01
036909C-1019-PDS-1000-1950 | Process Equipment Datasheet - 10-PK-1950 - Decoke Air Compressor Pkg | B | 2018-09-28 | IFD | OL1-2G30-1950 | PE | 2018-10-01 | 036909C-JVD-TRN-00114 | 036909C-JVD-TRN-00114 | IFI |  | 2018-10-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00114 |  | 2018-10-01
036909C-1000-JSD-1554-0001 | TEMPERATURE MEASUREMENT | A | 2018-09-28 | IFR | OL1-2R06-0007 | IE | 2018-10-04 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04
036909C-1000-JSD-1552-0001 | LEVEL MEASUREMENT | A | 2018-09-28 | IFR | OL1-2R06-0005 | IE | 2018-10-04 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04
036909C-1000-JSD-1540-0001 | Instrument General Design | A | 2018-09-28 | IFR | OL1-2R06-0001 | IE | 2018-10-04 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04
036909C-1000-JSD-1553-0001 | PRESSURE MEASUREMENT | A | 2018-09-28 | IFR | OL1-2R06-0006 | IE | 2018-10-04 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04
036909C-1000-JSD-1511-0001 | Instrument Cabinet | A | 2018-09-28 | IFR | OL1-2R06-0016 | IE | 2018-10-04 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04
036909C-1000-JSD-1522-0001 | Electrical And Instrument Interface Philosophy | A | 2018-09-28 | IFR | OL1-2R07-0020 | IE | 2018-10-04 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04
036909C-1000-JSD-1515-0004 | Machinery Monitoring System | A | 2018-09-28 | IFR | OL1-2R06-0013 | IE | 2018-10-04 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04
036909C-1000-CN-1901-0001 | Fire Water Demand Calculation And Hydraulic Study For FW Network | A | 2019-03-06 | IFR | OL1-2L20-0001 | SE | 2019-03-08 | 036909C-JVD-TRN-01006 | 036909C-JVD-TRN-01006 | IFA | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-SE-01006 |  | 2019-03-08
036909C-1000-DW-1512-0002 | Control And Safety Systems Architecture | A | 2019-02-20 | IFR | OL1-2I81-1002 | IE | 2019-02-25 | 036909C-JVD-TRN-00912 | 036909C-JVD-TRN-00912 | IFA | 2019-03-11 | 2019-03-08 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-00912 |  | 2019-02-25
036909C-1000-JSD-1300-0010 | JSD For Auxiliary Piping Supports | A | 2018-11-12 | IFR | OL1-2R04-0034 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 | 2018-12-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-00324
036909C-1000-JSD-1300-0010 | JSD For Auxiliary Piping Supports | B | 2019-02-04 | IFR | OL1-2R04-0034 | MP | 2019-02-08 | 036909C-JVD-TRN-00830 | 036909C-JVD-TRN-00830 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-MP-00830
036909C-1000-JSS-1693-0001 | Low Voltage Variable Voltage Variable Frequency System | 0 | 2018-09-20 | IMP | OL1-2R05-0023 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268
036909C-1000-JSS-1691-0001 | Electrical Motos Up To 300 kW | 0 | 2018-09-20 | IMP | OL1-2R05-0010 | EE | 2018-09-25 | 036909C-JVD-TRN-00079 | 036909C-JVD-TRN-00079 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00079 |  | 2018-09-25
036909C-1055-PDS-0800-5565 | Process Equipment Datasheet - 10-D-5565 - Polyolefins Flare Knock-Out Drum | B | 2019-03-04 | IFD | OL1-2G30-5565 | PE | 2019-03-06 | 036909C-JVD-TRN-00989 | 036909C-JVD-TRN-00989 | IFR | 2019-03-20 |  | Transmitted | TPSK-LSPA1-T-PE-00989 |  | 2019-03-06
036909C-1027-PDS-0900-2764 | Process Equipment Datasheet - 10-P-2760 A-B - C4 - C5 Hydrog Recycle Pump | B | 2019-02-28 | IFD | OL1-2G30-2764 | PE | 2019-03-04 | 036909C-JVD-TRN-00963 | 036909C-JVD-TRN-00963 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-PE-00963 |  | 2019-03-04
036909C-1027-TDS-0610-2765 | Mechanical Equipment Data Sheet - 10-E-2765 - C4 -C5 Hydrog Recycle Cooler | A | 2019-03-04 | IFQ | OL1-2M03-2765 | ME | 2019-03-05 | 036909C-JVD-TRN-00991 | 036909C-JVD-TRN-00991 | IFR | 2019-03-20 |  | Transmitted | TPSK-LSPA1-T-ME-00991
036909C-1025-TDS-0610-2548 | Mechanical Equipment Data Sheet - 10-E-2548 - Demethanizer Bottoms Vaporizer | B | 2019-02-27 | IFQ | OL1-2M03-2548 | ME | 2019-03-04 | 036909C-JVD-TRN-00961 | 036909C-JVD-TRN-00961 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-ME-00961 |  | 2019-03-04
036909C-1025-TDS-0610-2515 | Mechanical Equipment Data Sheet - 10-E-2515- Demeth Prefrac Reboiler | B | 2019-02-28 | IFQ | OL1-2M03-2515 | ME | 2019-03-04 | 036909C-JVD-TRN-00971 | 036909C-JVD-TRN-00971 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-ME-00971 |  | 2019-03-04
036909C-1021-PDS-0900-2126 | Process Equipment Datasheet - 10-P-2126 A-B - Distillate Stripper Bottom Pumps | B | 2019-02-28 | IFD | OL1-2G30-2126 | PE | 2019-03-04 | 036909C-JVD-TRN-00963 | 036909C-JVD-TRN-00963 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-PE-00963 |  | 2019-03-04
036909C-1019-PDS-0900-1913 | Process Equipment Datasheet - 10-P-1910 A-B - DMDS Feed Injection Pump | B | 2019-02-28 | IFD | OL1-2G30-1913 | PE | 2019-03-04 | 036909C-JVD-TRN-00963 | 036909C-JVD-TRN-00963 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-PE-00963 |  | 2019-03-04
036909C-1010-TDS-0610-1051 | Mechanical Equipment Data Sheet - 10-E-1050 - C2 Feed Superheater | B | 2019-02-26 | IFQ | OL1-2M03-1051 | ME | 2019-03-04 | 036909C-JVD-TRN-00961 | 036909C-JVD-TRN-00961 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-ME-00961 |  | 2019-03-04
036909C-1010-TDS-0610-1015 | Mechanical Equipment Data Sheet - 10-E-1015 - LPG Superheater | B | 2019-02-27 | IFQ | OL1-2M03-1015 | ME | 2019-03-04 | 036909C-JVD-TRN-00971 | 036909C-JVD-TRN-00971 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-ME-00971 |  | 2019-03-04
036909C-1000-MR-0811-0001 | Material Requisition For Shop Assembled Large Drums | A | 2019-03-01 | IFI | OL1-2C13-131000 | PL | 2019-03-04 | 036909C-JVD-TRN-00967 | 036909C-JVD-TRN-00967 | IFR | 2019-03-18 |  | Transmitted | TPSK-LSPA1-T-PL-00967 |  | 2019-03-04
036909C-1000-MR-1530-0001 | MATERIAL REQUISITION FOR INTERCOM/PAGING/AUDIBLE ALARM SYSTEM | A | 2019-03-01 | IFQ | OL1-2C16-881000 | PL | 2019-03-05 | 036909C-JVD-TRN-00984 | 036909C-JVD-TRN-00984 | IFR | 2019-03-18 |  | Transmitted | TPSK-LSPA1-T-PL-00984 |  | 2019-03-05
036909C-1000-MR-1530-0002 | MATERIAL REQUISITION FOR SAFETY SUPERVISORY SYSTEM | A | 2019-03-01 | IFQ | OL1-2C16-851000 | PL | 2019-03-05 | 036909C-JVD-TRN-00984 | 036909C-JVD-TRN-00984 | IFR | 2019-03-18 |  | Transmitted | TPSK-LSPA1-T-PL-00984 |  | 2019-03-05
036909C-1000-MR-1329-0002 | Material Requisition For Underground Welded Carbon Steel Pipes | A | 2019-02-27 | IFQ | OL1-2C14-365001 | PL | 2019-03-05 | 036909C-JVD-TRN-00975 | 036909C-JVD-TRN-00975 | IFR | 2019-03-19 |  | Transmitted | TPSK-LSPA1-T-PL-00975 |  | 2019-03-05
036909C-1000-MR-1309-0001 | Material Requisition For Carbon Steel Underground Piping | A | 2019-02-27 | IFI | OL1-2C14-360001 | PL | 2019-03-04 | 036909C-JVD-TRN-00969 | 036909C-JVD-TRN-00969 | IFR | 2019-03-18 |  | Transmitted | TPSK-LSPA1-T-PL-00969 |  | 2019-03-04
036909C-1000-DW-1532-0004 | Telecomm Syst Architecture Of Safety Supervisory System | A | 2019-02-27 | IFR | OL1-2T31-0001 | EE | 2019-03-05 | 036909C-JVD-TRN-00976 | 036909C-JVD-TRN-00976 | IFA | 2019-03-19 |  | Transmitted | TPSK-LSPA1-T-EE-00976 |  | 2019-03-05
036909C-1000-DW-1532-0003 | Telecomm Syst Architecture Of Intercom Paging and Audible Alarm Systems | A | 2019-03-01 | IFR | OL1-2T11-0001 | EE | 2019-03-05 | 036909C-JVD-TRN-00976 | 036909C-JVD-TRN-00976 | IFA | 2019-03-19 |  | Transmitted | TPSK-LSPA1-T-EE-00976 |  | 2019-03-05
036909C-1000-JSS-1530-0002 | Job Supply Specification For Safety Supervisory System | A | 2018-12-21 | IFR | OL1-2T92-0002 | EE | 2019-01-03 | 036909C-JVD-TRN-00577 | 036909C-JVD-TRN-00577 | IFR | 2019-01-17 | 2019-01-23 | R2-Comments as noted | TPSK-LSPA1-T-EE-00577
036909C-1000-JSS-1530-0001 | Job Supply Specification For Intercom Paging Audible Alarm System | A | 2018-12-21 | IFR | OL1-2T92-0001 | EE | 2019-01-03 | 036909C-JVD-TRN-00577 | 036909C-JVD-TRN-00577 | IFR | 2019-01-17 | 2019-01-23 | R2-Comments as noted | TPSK-LSPA1-T-EE-00577
036909C-1000-JSD-1530-0002 | Safety Supervisory System | A | 2018-11-30 | IFR | OL1-2R05-0019 | EE | 2018-12-04 | 036909C-JVD-TRN-00403 | 036909C-JVD-TRN-00403 | IFR | 2018-12-18 | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-EE-00403
036909C-1000-JSD-1530-0001 | Intercom/Paging/Audible Alarm System | A | 2018-11-30 | IFR | OL1-2R05-0013 | EE | 2018-12-04 | 036909C-JVD-TRN-00403 | 036909C-JVD-TRN-00403 | IFR | 2018-12-18 | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-EE-00403
036909C-1000-JSS-1671-0001 | Uninterruptible Power Supplies | 0 | 2018-09-20 | IMP | OL1-2R05-0012 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268
036909C-1000-JSD-1530-0003 | Telecom Numbering | A | 2019-02-19 | IFR | OL1-2R05-0028 | EE | 2019-02-22 | 036909C-JVD-TRN-00905 | 036909C-JVD-TRN-00905 | IFR | 2019-03-08 | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-EE-00905 |  | 2019-02-22
036909C-1012-JSS-0000-9999 | General Supply Rules for Supplier Documentation | C | 2019-01-30 | IFI | OL1-2C93-0001 | PL | 2019-02-06 | 036909C-JVD-TRN-00777 | 036909C-JVD-TRN-00777 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00777
036909C-1000-JSS-1621-0001 | Power Control And Fiber Optic Cables | 0 | 2018-12-03 | IMP | OL1-2R05-0018 | EE | 2018-12-05 | 036909C-JVD-TRN-00425 | 036909C-JVD-TRN-00425 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00425
036909C-1010-PDS-0600-1020 | Process Equipment Datasheet - 10-E-1020 - Liquid Feed Heater | C | 2019-01-16 | IFD | OL1-2G30-1020 | PE | 2019-01-18 | 036909C-JVD-TRN-00680 | 036909C-JVD-TRN-00680 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00680
036909C-1010-PDS-0600-1005 | Process Equipment Datasheet - 10-E-1005 - LPG Feed Heater | B | 2019-01-16 | IFD | OL1-2G30-1005 | PE | 2019-01-18 | 036909C-JVD-TRN-00680 | 036909C-JVD-TRN-00680 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00680
036909C-1000-STC-1790-0001 | Construction Standards for Reinforced Concrete Works | A | 2018-09-19 | IFR | OL1-2K20-0001 | CV | 2018-09-27 | 036909C-JVD-TRN-00088 | 036909C-JVD-TRN-00088 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00088 |  | 2018-09-27
036909C-1000-JSD-1400-0001 | Job Design Specification For Underground Systems | A | 2018-09-18 | IFR | OL1-2R02-0001 | CV | 2019-09-27 | 036909C-JVD-TRN-00087 | 036909C-JVD-TRN-00087 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00087 |  | 2019-09-27
036909C-1051-PDS-0800-5140 | Process Equipment Datasheet - 10-D-5140 - Intermittent Blowdown Drum | B | 2018-12-13 | IFD | OL1-2G30-5140 | PE | 2018-12-14 | 036909C-JVD-TRN-00504 | 036909C-JVD-TRN-00504 | IFI |  | 2019-01-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00504
036909C-1023-PDS-0900-2391 | Process Equipment Datasheet - 10-P-2390 - Caustic Drain Drum Pump | B | 2019-01-18 | IFD | OL1-2G30-2391 | PE | 2019-01-22 | 036909C-JVD-TRN-00695 | 036909C-JVD-TRN-00695 | IFI |  | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00695
036909C-1026-PDS-0600-2666 | Process Equipment Datasheet - 10-E-2666 - Debutanizer Bottoms Cooler | B | 2018-11-26 | IFD | OL1-2G30-2666 | PE | 2018-11-27 | 036909C-JVD-TRN-00370 | 036909C-JVD-TRN-00370 | IFI |  | 2018-12-10 | A1-Approved without comments | TPSK-LSPA1-T-PE-00370
036909C-1056-PDS-0200-5600 | Process Equipment Datahseet - 10-PIT-5600 - Pygas Area Oily Wastewater Sump | B | 2019-02-07 | IFD | OL1-2G30-5600 | PE | 2019-02-11 | 036909C-JVD-TRN-00838 | 036909C-JVD-TRN-00838 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00838
036909C-1056-PDS-0200-5601 | Process Equipment Datasheet - 10-PIT-5601 - Butadiene Area Oily Wastewater Sump | B | 2019-02-06 | IFD | OL1-2G30-5601 | PE | 2019-02-07 | 036909C-JVD-TRN-00819 | 036909C-JVD-TRN-00819 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00819
036909C-1056-PDS-0200-5602 | Process Equipment Datasheet - 10-PIT-5602 - QW Area Oily Wastewater Sump | B | 2019-02-06 | IFD | OL1-2G30-5602 | PE | 2019-02-07 | 036909C-JVD-TRN-00819 | 036909C-JVD-TRN-00819 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00819
036909C-1056-PDS-0200-5603 | Process Equipment Datasheet - 10-PIT-5603 - CGC Area Oily Wastewater Sump | B | 2019-02-06 | IFD | OL1-2G30-5603 | PE | 2019-02-07 | 036909C-JVD-TRN-00819 | 036909C-JVD-TRN-00819 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00819
036909C-1056-PDS-0200-5604 | Process Equipment Datasheet - 10-PIT-5604 - Refrig Area Oily Wastewater Sump | B | 2019-02-06 | IFD | OL1-2G30-5604 | PE | 2019-02-07 | 036909C-JVD-TRN-00819 | 036909C-JVD-TRN-00819 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00819
036909C-1056-PDS-0200-5605 | Process Equipment Datasheet - 10-PIT-5605 - Furnace Area Oily Wastewater Sump | B | 2019-02-06 | IFD | OL1-2G30-5605 | PE | 2019-02-07 | 036909C-JVD-TRN-00819 | 036909C-JVD-TRN-00819 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00819
036909C-1056-PDS-0200-5630 | Process Equipment Datasheet - 10-PIT-5630 - CT Area Oily Wastewater Sump | B | 2019-02-07 | IFD | OL1-2G30-5630 | PE | 2019-02-11 | 036909C-JVD-TRN-00838 | 036909C-JVD-TRN-00838 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00838
036909C-1056-PDS-0200-5631 | Process Equipment Datasheet - 10-PIT-5631 - CWWT Area Oily Wastewater Sump | B | 2019-02-07 | IFD | OL1-2G30-5631 | PE | 2019-02-11 | 036909C-JVD-TRN-00838 | 036909C-JVD-TRN-00838 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00838
036909C-1056-PDS-0200-5632 | Process Equipment Datasheet - 10-PIT-5632 - HP Flare Area Oily WW Sump | B | 2019-02-07 | IFD | OL1-2G30-5632 | PE | 2019-02-11 | 036909C-JVD-TRN-00838 | 036909C-JVD-TRN-00838 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00838
036909C-1056-PDS-0200-5646 | Process Equipment Datasheet - 10-PIT-5606 - C3 Hydrog Area Oily Wastewater Sump | B | 2019-02-06 | IFD | OL1-2G30-5646 | PE | 2019-02-07 | 036909C-JVD-TRN-00819 | 036909C-JVD-TRN-00819 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00819
036909C-1056-PDS-0200-5647 | Process Equipment Datasheet - 10-PIT-5607 - Flare KO Drum Oily Wastewater Sump | B | 2019-02-06 | IFD | OL1-2G30-5647 | PE | 2019-02-07 | 036909C-JVD-TRN-00819 | 036909C-JVD-TRN-00819 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00819
036909C-1024-PDS-0800-2410 | Process Equipment Datasheet - 10-D-2410 A-B - Cracked Gas Dryer | B | 2019-01-15 | IFD | OL1-2G30-2410 | PE | 2019-01-18 | 036909C-JVD-TRN-00678 | 036909C-JVD-TRN-00678 | IFI |  | 2019-01-29 | R1-No comments | TPSK-LSPA1-T-PE-00678
036909C-1056-PDS-0900-5649 | Process Equipment Datasheet - 10-P-5607 A-B - Flare KO Drum Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5649 | PE | 2019-01-31 | 036909C-JVD-TRN-00779 | 036909C-JVD-TRN-00779 | IFI |  | 2019-03-04 | R1-No comments | TPSK-LSPA1-T-PE-00779
036909C-1010-PDS-0600-1001 | Process Equipment Datasheet - 10-E-1000 - LPG Vaporizer | B | 2018-12-06 | IFD | OL1-2G30-1001 | PE | 2018-12-10 | 036909C-JVD-TRN-00451 | 036909C-JVD-TRN-00451 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00451
036909C-1056-PDS-2600-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package | C | 2019-02-01 | IFD | OL1-2G30-5644 | PE | 2019-02-01 | 036909C-JVD-TRN-00797 | 036909C-JVD-TRN-00797 | IFI |  | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00797
036909C-1022-PDS-0800-2220 | Process Equipment Datasheet - 10-D-2220 - CG 2nd Stage Suction Drum | C | 2019-01-16 | IFD | OL1-2G30-2220 | PE | 2019-01-18 | 036909C-JVD-TRN-00678 | 036909C-JVD-TRN-00678 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00678
036909C-1021-PDS-0800-2160 | Process Equipment Datasheet - 10-D-2160 - Dilution System Generator | B | 2019-01-09 | IFD | OL1-2G30-2160 | PE | 2019-01-10 | 036909C-JVD-TRN-00620 | 036909C-JVD-TRN-00620 | IFI |  | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00620
036909C-1022-PDS-0800-2230 | Process Equipment Datasheet - 10-D-2230 - CG 3rd Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2230 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00448
036909C-1028-PDS-0800-2810 | Process Equipment Datasheet - 10-D-2810 - C3R 1st Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2810 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349
036909C-1022-PDS-0800-2210 | Process Equipment Datasheet - 10-D-2210 - CG 1st Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2210 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00448
036909C-1028-PDS-0800-2840 | Process Equipment Datasheet - 10-D-2840 - C3R 4th Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2840 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349
036909C-1021-PDS-0800-2110 | Process Equipment Datasheet - 10-D-2110 - Interception Drum | B | 2019-01-16 | IFD | OL1-2G30-2110 | PE | 2019-01-18 | 036909C-JVD-TRN-00678 | 036909C-JVD-TRN-00678 | IFI |  | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00678
036909C-1027-TDS-0610-2721 | Mechanical Equipment Data Sheet - 10-E-2720 - Rerun Tower Condenser | A | 2019-02-21 | IFQ | OL1-2M03-2721 | ME | 2019-03-01 | 036909C-JVD-TRN-00956 | 036909C-JVD-TRN-00956 | IFR | 2019-03-15 |  | Transmitted | TPSK-LSPA1-T-ME -00956 |  | 2019-03-01
036909C-1000-STC-1490-0001 | Standard Construction Drawings For Underground Systems | A | 2018-09-18 | IFR | OL1-2K23-0001 | CV | 2018-09-27 | 036909C-JVD-TRN-00088 | 036909C-JVD-TRN-00088 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00088 |  | 2018-09-27
036909C-1000-STC-0490-000 | Construction Standards For Pressure Equipment | B | 2018-09-20 | IFR | OL1-2R03-0054 | ME | 2019-09-27 | 036909C-JVD-TRN-00085 | 036909C-JVD-TRN-00085 | IFR | 2018-10-09 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-ME-00084 |  | 2019-09-27
036909C-1000-QCP-2520-0003 | Quality Control Plan Cryogenic Tanks Erection | A | 2019-02-19 | IFR | OL1-2Q23-0003 | QM | 2019-02-28 | 036909C-JVD-TRN-00942 | 036909C-JVD-TRN-00942 | IFA | 2019-03-14 |  | Transmitted | TPSK-LSPA1-T-QM-00942 |  | 2019-02-28
036909C-1000-QCP-2520-0002 | Quality Control Plan Floating Roof Tanks Erection | A | 2019-02-19 | IFR | OL1-2Q23-0002 | QM | 2019-02-28 | 036909C-JVD-TRN-00942 | 036909C-JVD-TRN-00942 | IFA | 2019-03-14 |  | Transmitted | TPSK-LSPA1-T-QM-00942 |  | 2019-02-28
036909C-1000-QCP-2520-0001 | Quality Control Plan Fixed Roof Tanks Erection | A | 2019-02-19 | IFR | OL1-2Q23-0001 | QM | 2019-02-28 | 036909C-JVD-TRN-00942 | 036909C-JVD-TRN-00942 | IFA | 2019-03-14 |  | Transmitted | TPSK-LSPA1-T-QM-00942 |  | 2019-02-28
036909C-1000-MR-0213-0001 | Material Requisition for Condensate Polisher Package | A | 2019-02-26 | IFQ | OL1-2C13-701000 | PL | 2019-02-27 | 036909C-JVD-TRN-00940 | 036909C-JVD-TRN-00940 | IFR | 2019-03-12 |  | Transmitted | TPSK-LSPA1-T-PL-00940 |  | 2019-02-27
036909C-1000-JSS-0400-01 | Job Specification For Supply Of Pressure Vessels | B | 2018-09-20 | IFR | OL1-2R03-0051 | ME | 2019-09-27 | 036909C-JVD-TRN-00084 | 036909C-JVD-TRN-00084 | IFR | 2018-10-09 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-ME-00084 |  | 2019-09-27
036909C-1000-JSD-1700-0001 | Job Design Specification For Foundations And Structures | A | 2018-09-19 | IFR | OL1-2R02-0004 | CV | 2019-09-27 | 036909C-JVD-TRN-00087 | 036909C-JVD-TRN-00087 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00087 |  | 2019-09-27
036909C-1000-JSD-0400-01 | Job Specification For Design Of Pressure & Atmospheric Static Equipment | B | 2018-09-20 | IFR | OL1-2R03-0050 | ME | 2019-09-27 | 036909C-JVD-TRN-00084 | 036909C-JVD-TRN-00084 | IFR | 2018-10-09 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-ME-00084 |  | 2019-09-27
036909C-1000-JSD-1501-0002 | General Design Rules For SmartPlant Instrumentation Setup | A | 2018-09-27 | IFR | OL1-2R06-0024 | IE | 2018-09-28 | 036909C-JVD-TRN-00109 | 036909C-JVD-TRN-00109 | IFR | 2018-10-11 | 2018-10-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-00109 |  | 2018-09-28
036909C-1024-SP-0910-2457 | Mechanical Equipment Datasheet - LP Deprop Reboiler Cond Pump | B | 2019-01-21 | IFQ | OL1-2M03-2457 | ME | 2019-01-30 | 036909C-JVD-TRN-00770 | 036909C-JVD-TRN-00770 | IFR | 2019-02-15 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00770
036909C-1020-SP-0910-2046 | Mechanical Equipment Datasheet - Heavy Fuel Oil Pumps | B | 2019-01-22 | IFQ | OL1-2M03-2046 | ME | 2019-02-01 | 036909C-JVD-TRN-00786 | 036909C-JVD-TRN-00786 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00786
036909C-1023-SP-0910-2391 | Mechanical Equipment Datasheet - Caustic Drain Drum Pump | B | 2019-01-28 | IFQ | OL1-2M03-2391 | ME | 2019-02-07 | 036909C-JVD-TRN-00822 | 036909C-JVD-TRN-00822 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00822
036909C-1020-SP-0910-2024 | Mechanical Equipment Datasheet - Light Fuel Oil Pumps | B | 2019-01-22 | IFQ | OL1-2M03-2024 | ME | 2019-02-01 | 036909C-JVD-TRN-00786 | 036909C-JVD-TRN-00786 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00786
036909C-1024-SP-0910-2443 | Mechanical Equipment Datasheet - HP Deprop Reboiler Cond Pump | B | 2019-01-21 | IFQ | OL1-2M03-2443 | ME | 2019-01-30 | 036909C-JVD-TRN-00770 | 036909C-JVD-TRN-00770 | IFR | 2019-02-15 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00770
036909C-1024-SP-0910-2416 | Mechanical Equipment Datasheet - CG Liquid Dryer Feed Pumps | B | 2019-01-21 | IFQ | OL1-2M03-2416 | ME | 2019-01-30 | 036909C-JVD-TRN-00770 | 036909C-JVD-TRN-00770 | IFR | 2019-02-15 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00770
036909C-1023-SP-0910-2325 | Mechanical Equipment Datasheet - 10 percent Caustic Makeup Pumps | B | 2019-01-31 | IFQ | OL1-2M03-2325 | ME | 2019-02-07 | 036909C-JVD-TRN-00822 | 036909C-JVD-TRN-00822 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00822
036909C-1028-SP-0910-2816 | Mechanical Equipment Datasheet - Propylene Refrig Recovery Pump | B | 2019-01-31 | IFQ | OL1-2M03-2816 | ME | 2019-02-07 | 036909C-JVD-TRN-00822 | 036909C-JVD-TRN-00822 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00822
036909C-1051-SP-0910-5121 | Mechanical Equipment Datasheet - Raw Condensate Pumps | B | 2018-12-18 | IFQ | OL1-2M03-5121 | ME | 2018-12-20 | 036909C-JVD-TRN-00544 | 036909C-JVD-TRN-00544 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00544
036909C-1051-SP-0910-5111 | Mechanical Equipment Datasheet - Suspect Condensate Pumps | B | 2018-12-18 | IFQ | OL1-2M03-5111 | ME | 2018-12-20 | 036909C-JVD-TRN-00544 | 036909C-JVD-TRN-00544 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00544
036909C-1026-SP-0910-2663 | Mechanical Equipment Datasheet - Debutanizer Reflux - Product Pumps | B | 2019-01-30 | IFQ | OL1-2M03-2663 | ME | 2019-02-07 | 036909C-JVD-TRN-00822 | 036909C-JVD-TRN-00822 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00822
036909C-1026-SP-0910-2647 | Mechanical Equipment Datasheet - HP Propylene - Off Spec Pump | B | 2019-01-22 | IFQ | OL1-2M03-2647 | ME | 2019-01-30 | 036909C-JVD-TRN-00770 | 036909C-JVD-TRN-00770 | IFR | 2019-02-15 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00770
036909C-1055-SP-0910-5501 | Mechanical Equipment Datasheet - Hot Blowdown Pumps | B | 2019-01-31 | IFQ | OL1-2M03-5501 | ME | 2019-02-07 | 036909C-JVD-TRN-00822 | 036909C-JVD-TRN-00822 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00822
036909C-1000-MR-4065-0001 | Material Requisition For Bridge Crane | A | 2019-02-20 | IFQ | OL1-2C13-771000 | PL | 2019-02-25 | 036909C-JVD-TRN-00914 | 036909C-JVD-TRN-00914 | IFR | 2019-03-11 |  | Transmitted | TPSK-LSPA1-T-PC-00914 |  | 2019-02-25
036909C-1028-SP-4065-6005 | Mechanical Equipment Datasheet For Ethylene And Propylene Compressor Bridge Crane (10-EL-2800) | A | 2019-02-20 | IFQ | OL1-2M03-6005 | ME | 2019-02-25 | 036909C-JVD-TRN-00913 | 036909C-JVD-TRN-00913 | IFR | 2019-02-22 |  | Transmitted | TPSK-LSPA1-T-ME-00913 |  | 2019-02-25
036909C-1023-SP-4065-6004 | Mechanical Equipment Datasheet For Cracked Gas Compressor Bridge Crane (10-EL-2300) | A | 2019-02-20 | IFQ | OL1-2M03-6004 | ME | 2019-02-25 | 036909C-JVD-TRN-00913 | 036909C-JVD-TRN-00913 | IFR | 2019-02-22 |  | Transmitted | TPSK-LSPA1-T-ME-00913 |  | 2019-02-25
036909C-1000-MR-0610-0002 | Material Requisition For S&T Heat Exchangers - Large - Requisition For Inquiry | A | 2019-02-08 | IFQ | OL1-2C13-272000 | PL | 2019-02-13 | 036909C-JVD-TRN-00849 | 036909C-JVD-TRN-00849 | IFR | 2019-02-28 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-PL-00849
036909C-1012-PDS-0811-1207 | Process Equipment Datasheet - 10-D-1200-1600 - USC 132U Cracking Furnace Steam Drum | B | 2018-12-10 | IFD | OL1-2G30-1207 | PE | 2018-12-12 | 036909C-JVD-TRN-00478 | 036909C-JVD-TRN-00478 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00478
036909C-1011-PDS-0811-1107 | Process Equipment Datasheet - 10-D-1100 - USC 36M Cracking Furnace Steam Drum | B | 2018-12-10 | IFD | OL1-2G30-1107 | PE | 2018-12-12 | 036909C-JVD-TRN-00478 | 036909C-JVD-TRN-00478 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00478
036909C-1023-PDS-2500-2324 | Process Equipment Datasheet - 10-TK-2300 - Fresh Caustic Day Tank | B | 2019-01-29 | IFD | OL1-2G30-2324 | PE | 2019-01-29 | 036909C-JVD-TRN-00760 | 036909C-JVD-TRN-00760 | IFI |  | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00760
036909C-1026-PDS-0800-2644 | Process Equipment Datasheet - 10-D-2645 - C3 Tower Reboiler Cond Pot | B | 2019-02-01 | IFD | OL1-2G30-2644 | PE | 2019-02-01 | 036909C-JVD-TRN-00796 | 036909C-JVD-TRN-00796 | IFI |  | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00796
036909C-1000-STC-0490-000 | Construction Standards For Pressure Equipment | 0 | 2018-10-26 | IMP | OL1-2R03-0054 | ME | 2018-10-31 | 036909C-JVD-TRN-00256 | 036909C-JVD-TRN-00256 | IFR | 2018-11-14 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00256
036909C-1000-JSD-0400-01 | Job Specification For Design Of Pressure & Atmospheric Static Equipment | 0 | 2018-10-26 | IMP | OL1-2R03-0050 | ME | 2018-10-31 | 036909C-JVD-TRN-00245 | 036909C-JVD-TRN-00245 | IFR | 2018-11-14 | 2018-11-26 | Transmitted | TPSK-LSPA1-T-ME-00245
036909C-1053-PDS-0300-5355 | Process Equipment Datasheet - 10-PK-5355 - Side Stream Filter Pkg | B | 2018-10-24 | IFD | OL1-2G30-5355 | PE | 2018-10-24 | 036909C-JVD-TRN-00226 | 036909C-JVD-TRN-00226 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00226
036909C-1000-JSS-1300-01 | General Supply Specification For Piping Material | B | 2018-11-19 | IFR | OL1-2R04-0006 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00342
036909C-1012-SP-0137-2010 | Particular Technical Specification for MOVs | A | 2018-12-12 | IFQ | OL1-2M57-2010 | ME | 2018-12-18 | 036909C-JVD-TRN-00534 | 036909C-JVD-TRN-00534 | IFI |  | 2019-02-28 | R2-Comments as noted | TPSK-LSPA1-T-ME-00534
036909C-1029-PDS-2600-2912 | Process Equipment Datasheet - 10-PK-2912 - Caustic Tower Anti-Foulant Inj Pkg | B | 2019-01-31 | IFD | OL1-2G30-2912 | PE | 2019-01-31 | 036909C-JVD-TRN-00780 | 036909C-JVD-TRN-00780 | IFI |  | 2019-02-28 | R1-No comments | TPSK-LSPA1-T-PE-00780
036909C-1023-PDS-0840-2307 | Process Equipment Datasheet - 10-F-2306 A-B - Weak Caustic Circulating Filters | C | 2019-01-29 | IFD | OL1-2G30-2307 | PE | 2019-01-30 | 036909C-JVD-TRN-00775 | 036909C-JVD-TRN-00775 | IFI |  | 2019-02-28 | R1-No comments | TPSK-LSPA1-T-PE-00775
036909C-102B-DW-1743-0012 | Foundation For 10-D-2305 | A | 2019-02-05 | IFR | OL1-2K34-0074 | CV | 2019-02-08 | 036909C-JVD-TRN-00826 | 036909C-JVD-TRN-00826 | IFR | 2019-02-25 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00826
036909C-102B-DW-1743-0004 | Foundation For 10-D-2310 | A | 2019-02-05 | IFR | OL1-2K34-0055 | CV | 2019-02-08 | 036909C-JVD-TRN-00826 | 036909C-JVD-TRN-00826 | IFR | 2019-02-25 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00826
036909C-1051-SP-0213-0002 | Mechanical Equipment Datasheet for Condensate Polisher Package | A | 2019-02-26 | IFQ | OL1-2M03-5125 | ME | 2019-02-28 | 036909C-JVD-TRN-00941 | 036909C-JVD-TRN-00941 | IFR | 2019-03-13 |  | Transmitted | TPSK-LSPA1-T-ME-00941 |  | 2019-02-28
036909C-1012-JSS-0154-2008 | Project Specification For Transfer Line Exchangers | A | 2018-09-20 | IFR | OL1-4M92-2008 | ME | 2018-09-24 | 036909C-JVD-TRN-00067 | 036909C-JVD-TRN-00067 | IFR | 2018-10-04 | 2018-10-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00067 |  | 2018-09-24
036909C-1012-JSS-0154-2007 | Project Specification For SLE and USX Exchangers | A | 2018-09-20 | IFR | OL1-4M92-2007 | ME | 2018-09-24 | 036909C-JVD-TRN-00067 | 036909C-JVD-TRN-00067 | IFR | 2018-10-04 | 2018-10-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00067 |  | 2018-09-24
036909C-1011-DW-1514-1001 | Cause and Effect Diagram Cracking Furnaces | B | 2019-02-13 | IBD | OL1-2172-1001 | IE | 2019-02-15 | 036909C-JVD-TRN-00860 | 036909C-JVD-TRN-00860 | IFR | 2019-02-28 |  | Transmitted | TPSK-LSPA1-T-IE-00556 |  | 2019-02-15
036909C-1000-MR-0511-0002 | Material Requisition For Shop Assembled Columns | A | 2019-01-18 | IFQ | OL1-2C13-101000 | PL | 2019-01-23 | 036909C-JVD-TRN-00705 | 036909C-JVD-TRN-00705 | IFR | 2019-02-06 |  | Transmitted | TPSK-LSPA1-T-PL-00705
036909C-1000-JSS-0910-0001 | ME-010 Centrifugal Pump | A | 2018-09-20 | IFR | OL1-2R03-0010 | ME | 2018-09-25 | 036909C-JVD-TRN-00078 | 036909C-JVD-TRN-00078 | IFR | 2018-10-08 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-ME-00078 |  | 2018-09-25
036909C-1000-JSS-1682-0001 | Electrical Heat Tracing | 0 | 2018-09-20 | IMP | OL1-2R05-0037 | EE | 2018-09-25 | 036909C-JVD-TRN-00079 | 036909C-JVD-TRN-00079 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00079 |  | 2018-09-25
036909C-1000-JSS-1011-0001 | ME-014 Centrifugal Compressor | A | 2018-09-18 | IFR | OL1-2R03-0014 | ME | 2018-10-19 | 036909C-JVD-TRN-00065 | 036909C-JVD-TRN-00065 | IFR | 2018-10-03 | 2018-10-10 | R1-No comments | TPSK-LSPA1-T-ME-00065 |  | 2018-10-19
036909C-102D-DW-1743-0044 | Foundation For 10-E-2504 | A | 2019-01-25 | IFR | OL1-2K34-0140 | CV | 2019-01-31 | 036909C-JVD-TRN-00763 | 036909C-JVD-TRN-00763 | IFR | 2019-02-15 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00763 |  | 2019-01-31
036909C-102D-DW-1743-0035 | Foundation For 10-E-2545 | A | 2019-01-25 | IFR | OL1-2K34-0128 | CV | 2019-01-31 | 036909C-JVD-TRN-00763 | 036909C-JVD-TRN-00763 | IFR | 2019-02-15 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00763 |  | 2019-01-31
036909C-1012-SP-0191-2006 | Particular Technical Specification for Furnace Burners | A | 2018-11-07 | IFQ | OL1-2M57-2006 | ME | 2018-11-13 | 036909C-JVD-TRN-00313 | 036909C-JVD-TRN-00313 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00313
036909C-1000-MR-0310-0001 | Material Requisition for Cooling Tower | A | 2018-10-30 | IFQ | OL1-2M55-0104 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276 | IFR | 2018-11-19 | 2019-02-15 | R1-No comments | TPSK-LSPA1-T-ME-00276
036909C-1000-SP-0310-0001 | Particular Technical Specification for Cooling Tower | A | 2018-10-30 | IFQ | OL1-2M57-0104 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276 | IFR | 2018-11-19 | 2019-02-15 | R1-No comments | TPSK-LSPA1-T-ME-00276
036909C-1053-SP-0310-0002 | Mechanical Equipment Datasheet for Cooling Tower | B | 2018-10-30 | IFQ | OL1-2M03-5350 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276 | IFR | 2018-11-19 | 2019-02-15 | R1-No comments | TPSK-LSPA1-T-ME-00276
036909C-1000-SP-0610-0001 | Particular Technical Specification For Wieland Tubes (Solo Source) | A | 2018-11-27 | IFQ | OL1-2M57-0058 | ME | 2018-11-28 | 036909C-JVD-TRN-00377 | 036909C-JVD-TRN-00377 | IFR | 2018-12-13 | 2019-02-07 | R1-No comments | TPSK-LSPA1-T-ME-00377
036909C-1012-DW-0127-2204 | USC 132U Cracking Furnace Fabricatin Assembly of Convection Coils Finned Tubes and Bill of Material | A | 2018-10-12 | IFR | OL1-2M06-2204 | ME | 2018-10-16 | 036909C-JVD-TRN-00182 | 036909C-JVD-TRN-00182 | IFR | 2018-10-30 |  | Transmitted | TPSK-LSPA1-T-ME-00182
036909C-1011-DW-0127-1204 | USC 36M Recycle Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill Of Material | A | 2018-10-12 | IFR | OL1-2M06-1204 | ME | 2018-10-16 | 036909C-JVD-TRN-00182 | 036909C-JVD-TRN-00182 | IFR | 2018-10-30 |  | Transmitted | TPSK-LSPA1-T-ME-00182
036909C-1053-PDS-0900-5361 | Process Equipment Datasheet - 10-P-5360 A-C - CTU Cooling Water Pumps | B | 2018-10-24 | IFD | OL1-2G30-5361 | PE | 2018-10-24 | 036909C-JVD-TRN-00225 | 036909C-JVD-TRN-00225 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00225
036909C-1026-PDS-0600-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler | B | 2018-11-01 | IFD | OL1-2G30-2635 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272
036909C-1025-PDS-0500-2540 | Process Equipment Datasheet - 10-T-2540 - 10-D-2540 - Demethanizer & Reflux Drum | B | 2018-11-09 | IFD | OL1-2G30-2540 | PE | 2018-11-09 | 036909C-JVD-TRN-00306 | 036909C-JVD-TRN-00306 | IFI |  | 2018-11-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00306
036909C-1012-DI-1607-2001 | Electrical Basis of Design | A | 2019-01-29 | IFR | OL1-2E01-2001 | EE | 2019-01-30 | 036909C-JVD-TRN-00772 | 036909C-JVD-TRN-00772 | IFR | 2019-02-15 | 2019-02-27 | A4 - Not Approved, re-submit for approval | TPSK-LSPA1-T-EE-00772
036909C-1012-JSS-0122-2001 | Project Specification for Centrifugally Cast Tubes for Radiant Coils and Transfer Lines in Cracking Furnaces | A | 2018-09-10 | IFR | OL1-4M92-2001 | ME | 2018-09-11 | 036909C-JVD-TRN-00037 | 036909C-JVD-TRN-00037 | IFR | 2018-09-24 | 2018-09-25 | R2-Comments as noted | TPSK-LSPA1-T-ME-00037 |  | 2018-09-11
036909C-1012-TEN-0127-2001 | See document number 036909C-1012-SP-0127-2001 or OL1-2M57-2001 | A | 2018-09-06 | IFQ | OL1-4M57-2001 | ME | 2018-09-13 | 036909C-JVD-TRN-00044 | 036909C-JVD-TRN-00044 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00044 |  | 2018-09-13
036909C-1012-MR-0127-2001 | Material Requisition for Convection Tubes | A | 2018-09-06 | IFQ | OL1-4M55-2001 | ME | 2018-09-13 | 036909C-JVD-TRN-00044 | 036909C-JVD-TRN-00044 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00044 |  | 2018-09-13
036909C-1012-JSS-0122-2002 | Project Specification for Statically Cast Fittings for Radiant Coils and Transfer Lines in Cracking Furnaces | A | 2018-09-10 | IFR | OL1-4M92-2002 | ME | 2018-09-11 | 036909C-JVD-TRN-00037 | 036909C-JVD-TRN-00037 | IFR | 2018-09-24 | 2018-09-25 | R2-Comments as noted | TPSK-LSPA1-T-ME-00037 |  | 2018-09-11
036909C-1000-NM-0003-1001 | Steam Balance | A | 2018-09-17 | IFI | OL1-2G62-1001 | PE | 2018-09-18 | 036909C-JVD-TRN-00059 | 036909C-JVD-TRN-00059 | IFI | 2018-10-01 | 2018-10-04 | Transmitted | TPSK-LSPA1-T-PE-00059 |  | 2018-09-18
036909C-1000-JSD-1580-0003 | General Design Rules For Instrumentation And Control Of Packaged Equipment | A | 2018-09-14 | IFR | OL1-2R06-0035 | IE | 2018-09-18 | 036909C-JVD-TRN-00056 | 036909C-JVD-TRN-00056 | IFR | 2018-10-01 | 2018-10-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-00056 |  | 2018-09-18
036909C-1024-PDS-0800-2420 | Process Equipment Datasheet - 10-D-2420 A-B - CG Liquid Dryer | B | 2019-01-04 | IFD | OL1-2G30-2420 | PE | 2019-01-08 | 036909C-JVD-TRN-00610 | 036909C-JVD-TRN-00610 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00610
036909C-1026-PDS-0800-2610 | Process Equipment Datasheet - 10-D-2610 - C3 Hydrog Arsine Guard Bed | B | 2019-01-08 | IFD | OL1-2G30-2610 | PE | 2019-01-10 | 036909C-JVD-TRN-00618 | 036909C-JVD-TRN-00618 | IFI |  | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00618
036909C-1024-PDS-0800-2480 | Process Equipment Datasheet - 10-D-2480 - CG Secondary Dryer | B | 2019-01-10 | IFD | OL1-2G30-2480 | PE | 2019-01-11 | 036909C-JVD-TRN-00637 | 036909C-JVD-TRN-00637 | IFI |  | 2019-01-31 | R1-No comments | TPSK-LSPA1-T-PE-00637
036909C-1024-PDS-0800-2460 | Process Equipment Datasheet - 10-D-2460 - C2 Hydrog Arsine Guard Bed | B | 2019-01-14 | IFD | OL1-2G30-2460 | PE | 2019-01-16 | 036909C-JVD-TRN-00660 | 036909C-JVD-TRN-00660 | IFI |  | 2019-01-29 | R1-No comments | TPSK-LSPA1-T-PE-00660
036909C-1024-PDS-0800-2411 | Process Equipment Datasheet - 10-D-2411 - Cracked Gas Mercury Adsorber | B | 2019-01-04 | IFD | OL1-2G30-2411 | PE | 2019-01-08 | 036909C-JVD-TRN-00610 | 036909C-JVD-TRN-00610 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00610
036909C-1024-PDS-0400-2470 | Process Equipment Datasheet - 10-R-2470 A-C - C2 Hydrog Reactor | B | 2019-01-04 | IFD | OL1-2G30-2470 | PE | 2019-01-08 | 036909C-JVD-TRN-00609 | 036909C-JVD-TRN-00609 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00609
036909C-1000-SP-1691-0100 | Typical Data Sheet for LV Motors | A | 2018-11-16 | IFQ | OL1-2E05-3100 | EE | 2018-11-26 | 036909C-JVD-TRN-00358 | 036909C-JVD-TRN-00358 | IFR | 2018-12-11 | 2019-01-03 | R1-No comments | TPSK-LSPA1-T-EE-00358
036909C-1000-SP-1691-0500 | Typical Data Sheet For Low Voltage Variable Voltage Variable Frequency System | A | 2018-11-16 | IFQ | OL1-2E05-3500 | EE | 2018-11-26 | 036909C-JVD-TRN-00358 | 036909C-JVD-TRN-00358 | IFR | 2018-12-11 | 2019-01-03 | R1-No comments | TPSK-LSPA1-T-EE-00358
036909C-1023-PDS-0500-2300 | Process Equipment Datasheet - 10-T-2300 - Caustic Tower | B | 2018-11-08 | IFD | OL1-2G30-2300 | PE | 2018-11-08 | 036909C-JVD-TRN-00290 | 036909C-JVD-TRN-00290 | IFI |  | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00290
036909C-1019-SP-1013-1950 | Mechanical Equipment Datasheet for Decoke Air Compressor Package | B | 2018-10-10 | IFQ | OL1-2M03-1950 | ME | 2018-10-11 | 036909C-JVD-TRN-00161 | 036909C-JVD-TRN-00161 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00161
036909C-1012-PDS-0191-1206 | Process Equipment Datasheet - 10-H-1200-1600 - USC 132U Burner | B | 2019-01-29 | IFD | OL1-2G30-1206 | PE | 2019-01-29 | 036909C-JVD-TRN-00756 | 036909C-JVD-TRN-00756 | IFI |  | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00756
036909C-1028-TDS-0610-2857 | Mechanical Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer | B | 2019-01-30 | IFQ | OL1-2M03-2857 | ME | 2019-01-30 | 036909C-JVD-TRN-00773 | 036909C-JVD-TRN-00773 | IFR | 2019-02-15 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00773
036909C-1025-TDS-0610-2571 | Mechanical Equipment Data Sheet - 10-E-2570 - Deethanizer Condenser | B | 2019-01-30 | IFQ | OL1-2M03-2571 | ME | 2019-01-30 | 036909C-JVD-TRN-00773 | 036909C-JVD-TRN-00773 | IFR | 2019-02-15 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00773
036909C-1026-PDS-0400-2620 | Process Equipment Data Sheet - 10-R-2620 - C3 Hydrog Reactor | B | 2019-02-20 | IFD | OL1-2G30-2620 | PE | 2019-02-22 | 036909C-JVD-TRN-00910 | 036909C-JVD-TRN-00910 | IFR | 2019-03-08 |  | Transmitted | TPSK-LSPA1-T-PE-00910 |  | 2019-02-22
036909C-1000-STC-1391-0000 | Standard Auxiliary Piping Support Collection | A | 2019-02-11 | IFR | OL1-2P25-0085 | MP | 2019-02-20 | 036909C-JVD-TRN-00896 | 036909C-JVD-TRN-00896 | IFR | 2019-02-20 |  | Transmitted | TPSK-LSPA1-T-MP-00896 |  | 2019-02-20
036909C-1000-MR-0610-0003 | Material Requisition For CS S-T Heat Exchangers Requisition For Inquiry | A | 2019-02-11 | IFQ | OL1-2C13-273000 | PL | 2019-02-15 | 036909C-JVD-TRN-00866 | 036909C-JVD-TRN-00866 | IFR | 2019-03-04 |  | Transmitted | TPSK-LSPA1-T-PL-00866 |  | 2019-02-15
036909C-1000-MR-0610-0004 | Material Requisition For CS Clad SS And LAS S-T Heat Exchangers Requisition For Inquiry | A | 2019-02-15 | IFQ | OL1-2C13-274000 | PL | 2019-02-15 | 036909C-JVD-TRN-00870 | 036909C-JVD-TRN-00870 | IFR | 2019-03-04 |  | Transmitted | TPSK-LSPA1-T-PL-00870 |  | 2019-02-15
036909C-1000-JSS-1692-0001 | Electrical Motors Greater Than 300 kW | 0 | 2018-09-20 | IMP | OL1-2R05-0011 | EE | 2018-11-08 | 036909C-JVD-TRN-00293 | 036909C-JVD-TRN-00293, 036909C-JVD-TRN-00748 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-EE-00748
036909C-1000-JSD-1300-0003 | A1 Scope Annex C– Ppiping Specification PIP-006 Steam Tracing Piping | B | 2018-11-06 | IFR | OL1-2R04-0031 | MP | 2018-11-09 | 036909C-JVD-TRN-00292 | 036909C-JVD-TRN-00292 | IFR | 2018-11-26 | 2019-01-23 | R1-No comments | TPSK-LSPA1-T-MP-00292
036909C-1000-JSD-1300-0002 | Job Specification For Detail Design Piping - Includes ex doc. OL1-2P92-0002 as attachment | B | 2018-11-12 | IFR | OL1-2R04-0002 | MP | 2018-11-16 | 036909C-JVD-TRN-00326 | 036909C-JVD-TRN-00326 | IFR | 2018-12-03 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00012 | Includes ex doc. OL1-2P92-0002 as attachment
036909C-1000-JSD-1300-0008 | JSD For Piping Stress Analysis | A | 2018-11-12 | IFR | OL1-2R04-0032 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 | 2018-12-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-00324
036909C-1023-SP-0510-2300 | Mechanical Equipment Data Sheet - Caustic Tower | B | 2018-12-04 | IFQ | OL1-2M03-2300 | ME | 2018-12-05 | 036909C-JVD-TRN-00419 | 036909C-JVD-TRN-00419 | IFI |  | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00419
036909C-1029-PDS-2500-2910 | Process Equipment Datasheet - 10-TK-2910 - Wash Oil Day Tank | B | 2019-01-29 | IFD | OL1-2G30-2910 | PE | 2019-01-29 | 036909C-JVD-TRN-00760 | 036909C-JVD-TRN-00760 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00760
036909C-1000-MR-0610-0001 | Material Requisition For Wieland Tubes - Solo Source - Requisition For Purchase - Ex Doc. Client Reference OL1-2M57-0058 | 0 | 2019-02-05 | IFP | OL1-2C13-271000 | PL | 2019-02-08 | 036909C-JVD-TRN-00829 | 036909C-JVD-TRN-00829 | IFR | 2019-02-25 |  | Transmitted | TPSK-LSPA1-T-PL-00829 | Ex Doc. Client Reference OL1-2M55-0058 P.A. SOCOTEC-Poggi JeanJacques-Sog.It@socotec-oilandgas.com
036909C-1000-MR-0610-0001 | Material Requisition For Wieland Tubes (Solo Source) Requisition For Inquiry | A | 2018-11-27 | IFQ | OL1-2M55-0058 | ME | 2018-11-28 | 036909C-JVD-TRN-00377 | 036909C-JVD-TRN-00377 | IFR | 2018-12-13 | 2019-02-07 | R1-No comments | TPSK-LSPA1-T-ME-00377
036909C-1055-TDS-0610-5512 | Mechanical Equipment Data Sheet - 10-E-5512 - Cold Flare Superheater | A | 2019-01-28 | IFQ | OL1-2M03-5512 | ME | 2019-01-29 | 036909C-JVD-TRN-00755 | 036909C-JVD-TRN-00755 | IFR | 2019-02-12 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00755
036909C-1051-PDS-0200-5125 | Process Equipment Datasheet - 10-PK-5125 - Condensate Polisher Pkg | B | 2019-01-29 | IFD | OL1-2G30-5125 | PE | 2019-01-31 | 036909C-JVD-TRN-00778 | 036909C-JVD-TRN-00778 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00778
036909C-1051-PDS-0200-5115 | Process Equipment Datasheet - 10-PK-5115 - Condensate Carbon Filter Pkg | B | 2019-01-29 | IFD | OL1-2G30-5115 | PE | 2019-01-31 | 036909C-JVD-TRN-00778 | 036909C-JVD-TRN-00778 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00778
036909C-1024-TDS-0610-2430 | Mechanical Equipment Data Sheet - 10-E-2430 - Regen Gas Feed Heater | A | 2019-01-22 | IFQ | OL1-2M03-2430 | ME | 2019-01-28 | 036909C-JVD-TRN-00740 | 036909C-JVD-TRN-00740 | IFR | 2019-02-11 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00740
036909C-1051-PDS-0600-5108 | Process Equipment Datasheet - 10-E-5110 - Suspect Condensate Cooler | B | 2019-01-14 | IFD | OL1-2G30-5108 | PE | 2019-01-14 | 036909C-JVD-TRN-00652 | 036909C-JVD-TRN-00652 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00652
036909C-1051-PDS-0600-5107 | Process Equipment Datasheet - 10-E-5112 - Suspect Cond Flash Drum Vent Condenser | B | 2019-01-10 | IFD | OL1-2G30-5107 | PE | 2019-01-14 | 036909C-JVD-TRN-00646 | 036909C-JVD-TRN-00646 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00646
036909C-1024-TDS-0610-2434 | Mechanical Equipment Data Sheet - 10-E-2435 - Regen Gas Effluent Cooler | A | 2019-01-24 | IFQ | OL1-2M03-2434 | ME | 2019-01-25 | 036909C-JVD-TRN-00723 | 036909C-JVD-TRN-00723 | IFR | 2019-02-07 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00723
036909C-1012-DW-0117-2005 | USC 132U Cracking Furnace General Arrangement Instrumentation Sections | A | 2019-01-28 | IFR | OL1-2M06-2005 | ME | 2019-01-30 | 036909C-JVD-TRN-00768 | 036909C-JVD-TRN-00768 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00768
036909C-1012-DW-0131-2551 | USC 132U Cracking Furnace Steel Instrument Connection Details | A | 2019-01-28 | IFI | OL1-2K32-2551 | ME | 2019-01-31 | 036909C-JVD-TRN-00767 | 036909C-JVD-TRN-00767 | IFI |  | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00767 |  | 2019-01-31
036909C-1011-DW-0117-1551 | USC 36M Recycle Furnace Steel Instrument Connection Details | A | 2019-01-28 | IFI | OL1-2K32-1551 | ME | 2019-01-31 | 036909C-JVD-TRN-00767 | 036909C-JVD-TRN-00767 | IFI |  | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00767 |  | 2019-01-31
036909C-1012-DW-0117-2004 | USC 132U Cracking Furnace General Arrangement Instrumentation | A | 2019-01-28 | IFR | OL1-2M06-2004 | ME | 2019-01-31 | 036909C-JVD-TRN-00766 | 036909C-JVD-TRN-00766 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00766 |  | 2019-01-31
036909C-1011-DW-0117-1005 | USC 36M Recycle Furnace General Arrangement Instrumentation Sections | A | 2019-01-28 | IFR | OL1-2M06-1005 | ME | 2019-01-31 | 036909C-JVD-TRN-00764 | 036909C-JVD-TRN-00764 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00764 |  | 2019-01-31
036909C-1011-DW-0117-1004 | USC 36M Recycle Furnace General Arrangement Instrumentation | A | 2019-01-09 | IFR | OL1-2M06-1004 | ME | 2019-01-31 | 036909C-JVD-TRN-00764 | 036909C-JVD-TRN-00764 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00764 |  | 2019-01-31
036909C-1028-TDS-0610-2856 | Mechanical Equipment Data Sheet - 10-E-2855 - C2R Condenser | A | 2018-11-14 | IFQ | OL1-2M03-2856 | ME | 2018-11-14 | 036909C-JVD-TRN-00316 | 036909C-JVD-TRN-00316 | IFR | 2018-11-28 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-00316
036909C-1024-TDS-0610-2442 | Mechanical Equipment Data Sheet - 10-E-2442 - HP Deprop Reflux Chiller no 1 | A | 2019-01-14 | IFQ | OL1-2M03-2442 | ME | 2019-01-16 | 036909C-JVD-TRN-00662 | 036909C-JVD-TRN-00662 | IFR | 2019-01-29 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00662
036909C-1025-TDS-0610-2545 | Mechanical Equipment Data Sheet - 10-E-2545 - Demethanizer Reboiler | A | 2019-01-14 | IFQ | OL1-2M03-2545 | ME | 2019-01-14 | 036909C-JVD-TRN-00651 | 036909C-JVD-TRN-00651 | IFR | 2019-01-28 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00651
036909C-1021-TDS-0610-2145 | Mechanical Equipment Data Sheet - 10-E-2145 - Process Water Stripper Reboiler | A | 2019-01-17 | IFQ | OL1-2M03-2145 | ME | 2019-01-22 | 036909C-JVD-TRN-00684 | 036909C-JVD-TRN-00684 | IFR | 2019-02-04 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00684
036909C-1028-TDS-0610-2858 | Mechanical Equipment Data Sheet - 10-E-2858 - HP Ethylene Product Superheater | A | 2019-01-17 | IFQ | OL1-2M03-2858 | ME | 2019-01-22 | 036909C-JVD-TRN-00684 | 036909C-JVD-TRN-00684 | IFR | 2019-02-04 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00684
036909C-1023-TDS-0610-2305 | Mechanical Equipment Data Sheet - 10-E-2305 - Caustic Tower Feed Heater | A | 2019-01-08 | IFQ | OL1-2M03-2305 | ME | 2019-01-10 | 036909C-JVD-TRN-00617 | 036909C-JVD-TRN-00617 | IFR | 2019-01-23 | 2019-01-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-00617
036909C-1012-MR-4061-2009 | Material Requisition for Furnace Elevator | A | 2019-01-16 | IFQ | OL1-2C13-709000 | ME | 2019-01-22 | 036909C-JVD-TRN-00697 | 036909C-JVD-TRN-00697 | IFI |  | 2019-02-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00697
036909C-1011-PDS-0630-1108 | Process Equipment Datasheet - 10-E-1100A1 - F6 - USC 36M USX Exchanger | B | 2018-12-05 | IFD | OL1-2G30-1108 | PE | 2018-12-07 | 036909C-JVD-TRN-00432 | 036909C-JVD-TRN-00432 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00432
036909C-1000-JSS-1657-0001 | Low Voltage Distribution Panel | 0 | 2018-09-20 | IMP | OL1-2R05-0007 | EE | 2018-11-12 | 036909C-JVD-TRN-00309 | 036909C-JVD-TRN-00309 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00309
036909C-1000-STD-1380-0001 | Piping Design Standard Drawings - For next revision see document OL1-2R04-0002 - included as attachment | 0 | 2018-11-12 | CAN | OL1-2P92-0002 | MP | 2018-11-16 | 036909C-JVD-TRN-00325 | 036909C-JVD-TRN-00325 | IFR | 2018-12-03 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00325 | For next revision see document OL1-2R04-0002 - inclueded as attachment
036909C-1024-TDS-0610-2413 | Mechanical Equipment Data Sheet - 10-E-2413 - HP Deprop Feed-Overhead Exchanger | A | 2019-01-07 | IFR | OL1-2M03-2413 | ME | 2019-01-10 | 036909C-JVD-TRN-00617 | 036909C-JVD-TRN-00617 | IFR | 2019-01-23 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00617
036909C-1022-TDS-0610-2241 | Mechanical Equipment Data Sheet - 10-E-2240 - CG 4th Stage Aftercooler | A | 2019-01-07 | IFQ | OL1-2M03-2241 | ME | 2019-01-10 | 036909C-JVD-TRN-00617 | 036909C-JVD-TRN-00617 | IFR | 2019-01-23 | 2019-01-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-00617
036909C-1022-TDS-0610-2231 | Mechanical Equipment Data Sheet - 10-E-2230 - CG 3rd Stage Aftercooler | A | 2019-01-04 | IFQ | OL1-2M03-2231 | ME | 2019-01-07 | 036909C-JVD-TRN-00588 | 036909C-JVD-TRN-00588 | IFR | 2019-01-21 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00588
036909C-1056-PDS-0200-5628 | Process Equipment Datasheet - 10-PIT-5628 - East Gate House Septic Tank | B | 2019-02-07 | IFD | OL1-2G30-5628 | PE | 2019-02-11 | 036909C-JVD-TRN-00838 | 036909C-JVD-TRN-00838 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00838
036909C-1056-PDS-0200-5626 | Process Equipment Datasheet - 10-PIT-5626 - Gate House Septic Tank | B | 2019-02-07 | IFD | OL1-2G30-5626 | PE | 2019-02-11 | 036909C-JVD-TRN-00838 | 036909C-JVD-TRN-00838 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00838
036909C-1056-PDS-0200-5627 | Process Equipment Datasheet - 10-PIT-5627 - West Gate House Septic Tank | B | 2019-02-07 | IFD | OL1-2G30-5627 | PE | 2019-02-11 | 036909C-JVD-TRN-00838 | 036909C-JVD-TRN-00838 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00838
036909C-102B-DW-1743-0029 | Foundation For 10-D-2600 A-B | A | 2019-02-07 | IFR | OL1-2K34-0156 | CV | 2019-02-11 | 036909C-JVD-TRN-00833 | 036909C-JVD-TRN-00833 | IFR | 2019-02-26 |  | Transmitted | TPSK-LSPA1-T-CV-00833
036909C-1000-JSD-0000-0006 | Tray Design Specification | A | 2019-01-07 | IFR | OL1-2G01-0004 | PE | 2019-01-10 | 036909C-JVD-TRN-00624 | 036909C-JVD-TRN-00624 | IFR | 2019-01-25 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00624
036909C-1012-PDS-0630-1208 | Process Equipment Datasheet - 10-E-1200A-F - 10-E-1600A-F - USC 132U SLE Exchanger | B | 2018-12-05 | IFD | OL1-2G30-1208 | PE | 2018-12-07 | 036909C-JVD-TRN-00433 | 036909C-JVD-TRN-00433 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00433
036909C-1020-PDS-0600-2015 | Process Equipment Datasheet - 10-E-2008 A-C - LS2 Steam Generators | B | 2019-01-09 | IFD | OL1-2G30-2015 | PE | 2019-01-11 | 036909C-JVD-TRN-00632 | 036909C-JVD-TRN-00632 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00632
036909C-1000-SP-4111-0001 | Particular Technical Specification For Hydrogen Production Unit | A | 2018-10-26 | IFQ | OL1-2M57-0114 | ME | 2018-11-06 | 036909C-JVD-TRN-00271 | 036909C-JVD-TRN-00271 | IFR | 2018-11-20 | 2019-02-07 | R2-Comments as noted | TPSK-LSPA1-T-ME-00271
036909C-1000-SP-0184-0002 | Mechanical Data Sheet for HP / Polyolefins Flare Package | A | 2019-01-15 | IFQ | OL1-2M03-5560 | ME | 2019-01-17 | 036909C-JVD-TRN-00667 | 036909C-JVD-TRN-00667 | IFR | 2019-01-30 | 2019-02-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-00667
036909C-1000-MR-4100-0001 | Material Requisition for Wet Air Oxidation Package | A | 2018-11-22 | IFQ | OL1-2M55-0103 | ME | 2018-11-27 | 036909C-JVD-TRN-00367 | 036909C-JVD-TRN-00367 | IFR | 2018-12-11 | 2019-02-07 | R1-No comments | TPSK-LSPA1-T-ME-00367
036909C-1000-SP-4100-0001 | Particular Technical Specification for Wet Air Oxidation Package | A | 2018-11-26 | IFQ | OL1-2M57-0103 | ME | 2018-11-29 | 036909C-JVD-TRN-00390 | 036909C-JVD-TRN-00390 | IFR | 2018-12-13 | 2019-02-07 | R1-No comments | TPSK-LSPA1-T-ME-00390
036909C-1023-SP-4100-0002 | Mechanical Equipment Datasheet for Wet Air Oxidation Package | A | 2018-11-27 | IFQ | OL1-2M03-2350 | ME | 2018-11-29 | 036909C-JVD-TRN-00390 | 036909C-JVD-TRN-00390 | IFR | 2018-12-13 | 2019-02-07 | R1-No comments | TPSK-LSPA1-T-ME-00390
036909C-1000-JSD-1300-0011 | Piping Flexibility | A | 2018-11-19 | IFR | OL1-2R04-0030 | MP | 2018-11-20 | 036909C-JVD-TRN-00336 | 036909C-JVD-TRN-00336 | IFR | 2018-12-05 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00336
036909C-1000-JSD-1300-0009 | JSD for piping loads on PRK SLW STR IS | A | 2018-11-12 | IFR | OL1-2R04-0033 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 | 2018-12-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-00324
036909C-1053-PDS-0300-5350 | Process Equipment Datasheet - 10-PK-5350 - Cooling Tower | B | 2018-10-24 | IFD | OL1-2G30-5350 | PE | 2018-10-24 | 036909C-JVD-TRN-00226 | 036909C-JVD-TRN-00226 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00226
036909C-1051-SP-0910-5101 | Mechanical Equipment Data Sheet for SHP BFW Pumps | B | 2018-11-12 | IFQ | OL1-2M03-5101 | ME | 2018-11-15 | 036909C-JVD-TRN-00322 | 036909C-JVD-TRN-00322 | IFR | 2018-11-29 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00322
036909C-1028-PDS-0600-2853 | Process Equipment Datasheet - 10-E-2853 - C2R Desuperheater No 2 | B | 2018-11-01 | IFD | OL1-2G30-2853 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272
036909C-1028-PDS-0600-2852 | Process Equipment Datasheet - 10-E-2852 - C2R Desuperheater No 1 | B | 2018-11-01 | IFD | OL1-2G30-2852 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272
036909C-1028-PDS-0600-2807 | Process Equipment Datasheet - 10-E-2807 - C3 Chiller No 1 | B | 2018-11-01 | IFD | OL1-2G30-2807 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272
036909C-1028-PDS-0600-2856 | Process Equipment Datasheet - 10-E-2855 - C2R Condenser | B | 2018-11-01 | IFD | OL1-2G30-2856 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272
036909C-1028-PDS-0600-2806 | Process Equipment Datasheet - 10-E-2805 A-B - C3 Refrig Condensers | B | 2018-11-01 | IFD | OL1-2G30-2806 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272
036909C-1026-PDS-0600-2636 | Process Equipment Datasheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | B | 2018-11-01 | IFD | OL1-2G30-2636 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272
036909C-1026-PDS-0600-2661 | Process Equipment Datasheet - 10-E-2660 - Debutanizer Condenser | B | 2018-11-01 | IFD | OL1-2G30-2661 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272
036909C-1026-PDS-0600-2631 | Process Equipment Datasheet - 10-E-2630 - Secondary Deeth Condenser | B | 2018-11-01 | IFD | OL1-2G30-2631 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272
036909C-1025-PDS-0600-2576 | Process Equipment Datasheet - 10-E-2576 - Deethanizer Bottoms Cooler | B | 2018-11-01 | IFD | OL1-2G30-2576 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272
036909C-1025-PDS-0600-2571 | Process Equipment Datasheet - 10-E-2570 - Deethanizer Condenser | B | 2018-11-01 | IFD | OL1-2G30-2571 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272
036909C-1025-PDS-0500-2510 | Process Equipment Datasheet - 10-T-2510 - 10-D-2510 - Demethanizer Prefractionator & Reflux Drum | B | 2018-11-09 | IFD | OL1-2G30-2510 | PE | 2018-11-09 | 036909C-JVD-TRN-00306 | 036909C-JVD-TRN-00306 | IFI |  | 2018-11-29 | A1-Approved without comments | TPSK-LSPA1-T-PE-00306
036909C-1025-PDS-0600-2575 | Process Equipment Datasheet - 10-E-2575 - Deethanizer Reboiler | B | 2018-11-01 | IFD | OL1-2G30-2575 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272
036909C-1025-PDS-0600-2503 | Process Equipment Datasheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | B | 2018-11-01 | IFD | OL1-2G30-2503 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272
036909C-1023-PDS-2500-2320 | Process Equipment Datasheet - 10-TK-2320 - Spent Caustic Storage Tank | B | 2018-10-18 | IFD | OL1-2G30-2320 | PE | 2018-10-22 | 036909C-JVD-TRN-00203 | 036909C-JVD-TRN-00203 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00203
036909C-1022-SP-1011-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor | C | 2018-10-31 | IFQ | OL1-2M03-2200 | ME | 2018-11-06 | 036909C-JVD-TRN-00280 | 036909C-JVD-TRN-00280 | IFI |  | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-ME-00280
036909C-1021-PDS-0900-2146 | Process Equipment Datasheet - 10-P-2146 A-B - DSG Feed Pumps | B | 2018-10-18 | IFD | OL1-2G30-2146 | PE | 2018-10-22 | 036909C-JVD-TRN-00202 | 036909C-JVD-TRN-00202 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00202
036909C-1019-PDS-1000-1950 | Process Equipment Datasheet - 10-PK-1950 - Decoke Air Compressor Pkg | C | 2018-10-29 | IFD | OL1-2G30-1950 | PE | 2018-10-30 | 036909C-JVD-TRN-00242 | 036909C-JVD-TRN-00242 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00242
036909C-1020-PDS-0900-2006 | Process Equipment Datasheet - 10-P-2006 A-C - Quench Oil Pumps | B | 2018-10-18 | IFD | OL1-2G30-2006 | PE | 2018-10-22 | 036909C-JVD-TRN-00202 | 036909C-JVD-TRN-00202 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00202
036909C-1020-PDS-0500-2040 | Process Equipment Datasheet - 10-T-2040 - Heavy Fuel Oil Stripper | B | 2018-11-21 | IFD | OL1-2G30-2040 | PE | 2018-11-21 | 036909C-JVD-TRN-00347 | 036909C-JVD-TRN-00347 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00347
036909C-1012-SP-0155-2018 | Particular Technical Specification for Furnace Steam Drums | A | 2018-11-01 | IFQ | OL1-2M57-2018 | ME | 2018-11-01 | 036909C-JVD-TRN-00263 | 036909C-JVD-TRN-00263 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00263
036909C-1012-SP-0125-2007 | Particular Technical Specification for Cast Intermediate Tube Supports | A | 2018-11-12 | IFQ | OL1-2M57-2007 | ME | 2018-11-16 | 036909C-JVD-TRN-00329 | 036909C-JVD-TRN-00329 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00329
036909C-1012-SP-0127-2002 | Particular Technical Specification for Furnace Convection Fittings | A | 2018-10-16 | IFQ | OL1-2M57-2002 | ME | 2018-10-22 | 036909C-JVD-TRN-00207 | 036909C-JVD-TRN-00207 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00207
036909C-1012-MR-0191-2006 | Material Requisition for Furnace Burners | A | 2018-11-07 | IFQ | OL1-2M55-2006 | ME | 2018-11-13 | 036909C-JVD-TRN-00313 | 036909C-JVD-TRN-00313 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00313
036909C-1012-MR-0125-2007 | Material Requisition for Cast Intermediate Tube Supports | A | 2018-11-12 | IFQ | OL1-2M55-2007 | ME | 2018-11-16 | 036909C-JVD-TRN-00329 | 036909C-JVD-TRN-00329 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00329
036909C-1012-MR-0155-2018 | Material Requisition for Furnace Steam Drums | A | 2018-11-01 | IFQ | OL1-2M55-2018 | ME | 2018-11-01 | 036909C-JVD-TRN-00263 | 036909C-JVD-TRN-00263 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00263
036909C-1012-MR-0191-2006 | Material Requisition for Furnace Burners | 0 | 2019-01-31 | IFP | OL1-2C13-306000 | ME | 2019-02-07 | 036909C-JVD-TRN-00820 | 036909C-JVD-TRN-00820 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00820
036909C-1012-MR-0127-2002 | Material Requisition for Furnace Convection Fittings | A | 2018-10-16 | IFQ | OL1-2M55-2002 | ME | 2018-10-22 | 036909C-JVD-TRN-00207 | 036909C-JVD-TRN-00207 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00207
036909C-1006-JSS-0117-1004 | PIP-004 Piping Welding Specification for 36M and 132U Furnace | 0 | 2018-10-15 | IMP | OL1-2R04-1004 | ME | 2018-10-16 | 036909C-JVD-TRN-00184 | 036909C-JVD-TRN-00184 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00184
036909C-1006-JSS-0117-1001 | Approved Vendor List for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL1-2M91-1001 | ME | 2018-10-23 | 036909C-JVD-TRN-00211 | 036909C-JVD-TRN-00211 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00211
036909C-1006-JSS-0117-0009 | SP-009 Painting for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL1-2R07-0009 | ME | 2018-10-23 | 036909C-JVD-TRN-00214 | 036909C-JVD-TRN-00214 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00214
036909C-1006-JSS-0117-0007 | PIP-007 Marking of Piping Material for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL1-2R04-0007 | ME | 2018-10-23 | 036909C-JVD-TRN-00213 | 036909C-JVD-TRN-00213 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00213
036909C-1000-QCP-0000-0001 | Quality Control Plan Material Management and Warehouse | A | 2019-01-31 | IFR | OL1-2Q92-0008 | QM | 2019-02-07 | 036909C-JVD-TRN-00818 | 036909C-JVD-TRN-00818 | IFA | 2019-02-22 |  | Transmitted | TPSK-LSPA1-T-QM-00818
036909C-1000-NM-0014-0001 | Flare Load Summary | A | 2018-10-23 | IFR | OL1-2G22-0001 | PE | 2018-10-25 | 036909C-JVD-TRN-00229 | 036909C-JVD-TRN-00229 | IFR | 2018-11-08 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00229
036909C-1012-MR-0853-2011 | Material Requisition for Attemperators | A | 2019-01-25 | IFQ | OL1-2C13-286000 | PL | 2019-01-30 | 036909C-JVD-TRN-00771 | 036909C-JVD-TRN-00771 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00771
036909C-1026-SP-0910-2663 | Mechanical Equipment Datasheet - Debutanizer Reflux - Product Pumps | A | 2018-12-12 | IFQ | OL1-2M03-2663 | ME | 2018-12-17 | 036909C-JVD-TRN-00511 | 036909C-JVD-TRN-00511 | IFR | 2018-12-31 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00511
036909C-1026-PDS-0900-2663 | Process Equipment Datasheet - 10-P-2660 A-B - Debutanizer Reflux - Product Pumps | B | 2018-12-10 | IFD | OL1-2G30-2663 | PE | 2018-12-13 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00481
036909C-1053-SP-0910-5361 | Mechanical Equipment Data Sheet - CTU Cooling Water Pumps | C | 2018-11-26 | IFQ | OL1-2M03-5361 | ME | 2018-11-28 | 036909C-JVD-TRN-00388 | 036909C-JVD-TRN-00388 | IFI |  | 2018-12-18 | R1-No comments | TPSK-LSPA1-T-ME-00388
036909C-1056-PDS-0200-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg | B | 2018-12-05 | IFD | OL1-2G30-5653 | PE | 2018-12-07 | 036909C-JVD-TRN-00441 | 036909C-JVD-TRN-00441 | IFI |  | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00441
036909C-1056-PDS-2600-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg | B | 2018-12-05 | IFD | OL1-2G30-5670 | PE | 2018-12-07 | 036909C-JVD-TRN-00442 | 036909C-JVD-TRN-00442 | IFI |  | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00442
036909C-1056-PDS-2600-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg | B | 2018-12-05 | IFD | OL1-2G30-5650 | PE | 2018-12-07 | 036909C-JVD-TRN-00442 | 036909C-JVD-TRN-00442 | IFI |  | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00442
036909C-1056-PDS-2600-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package | B | 2018-12-05 | IFD | OL1-2G30-5644 | PE | 2018-12-07 | 036909C-JVD-TRN-00442 | 036909C-JVD-TRN-00442 | IFI |  | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00442
036909C-1025-PDS-0500-2570 | Process Equipment Datasheet - 10-T-2570 - Deethanizer | B | 2018-11-30 | IFD | OL1-2G30-2570 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-00407
036909C-1059-PDS-2500-5900 | Process Equipment Datasheet - 10-TK-5900 - Sulfuric Acid Tank | B | 2019-01-10 | IFD | OL1-2G30-5900 | PE | 2019-01-14 | 036909C-JVD-TRN-00647 | 036909C-JVD-TRN-00647 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00647
036909C-1028-PDS-0900-2855 | Process Equipment Datasheet - 10-P-2855 A-B - Ethylene Product Pumps | B | 2019-01-10 | IFD | OL1-2G30-2855 | PE | 2019-01-14 | 036909C-JVD-TRN-00648 | 036909C-JVD-TRN-00648 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00648
036909C-1026-PDS-0900-2669 | Process Equipment Datasheet - 10-P-2665 A-B - Debutanizer Bottoms Pumps | B | 2019-01-10 | IFD | OL1-2G30-2669 | PE | 2019-01-14 | 036909C-JVD-TRN-00648 | 036909C-JVD-TRN-00648 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00648
036909C-1024-PDS-0600-2471 | Process Equipment Datasheet - 10-E-2470 - C2 Hydrog 1st Stage Intercooler | B | 2019-01-07 | IFD | OL1-2G30-2471 | PE | 2019-01-07 | 036909C-JVD-TRN-00602 | 036909C-JVD-TRN-00602 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00602
036909C-1024-PDS-0600-2465 | Process Equipment Datasheet - 10-E-2465 - C2 Hydrog Feed Heater | B | 2019-01-07 | IFD | OL1-2G30-2465 | PE | 2019-01-07 | 036909C-JVD-TRN-00602 | 036909C-JVD-TRN-00602 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00602
036909C-1024-PDS-0600-2472 | Process Equipment Datasheet - 10-E-2472 - C2 Hydrog 2nd Stage Intercooler | B | 2019-01-07 | IFD | OL1-2G30-2472 | PE | 2019-01-07 | 036909C-JVD-TRN-00602 | 036909C-JVD-TRN-00602 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00602
036909C-1024-PDS-0600-2474 | Process Equipment Datasheet - 10-E-2474 - C2 Hydrog Aftercooler | B | 2019-01-07 | IFD | OL1-2G30-2474 | PE | 2019-01-07 | 036909C-JVD-TRN-00602 | 036909C-JVD-TRN-00602 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00602
036909C-1023-PDS-4200-2301 | Process Equipment Datasheet - 10-X-2300 - Caustic Dilution Mixer | B | 2018-11-27 | IFD | OL1-2G30-2301 | PE | 2018-11-28 | 036909C-JVD-TRN-00383 | 036909C-JVD-TRN-00383 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00383
036909C-1012-SP-0127-2002 | Particular Technical Specification for Furnace Convection Fittings | 0 | 2018-12-19 | IFP | OL1-2M57-2002 | ME | 2019-01-07 | 036909C-JVD-TRN-00592 | 036909C-JVD-TRN-00592 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00592
036909C-1012-MR-0127-2002 | Material Requisition for Furnace Convection Fittings | 0 | 2018-12-19 | IFP | OL1-2M55-2002 | ME | 2019-01-07 | 036909C-JVD-TRN-00592 | 036909C-JVD-TRN-00592 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00592
036909C-1024-PDS-0900-2453 | Process Equipment Datasheet - 10-P-2450 A-B - LP Depropanizer Reflux-Product Pump | B | 2019-01-04 | IFD | OL1-2G30-2453 | PE | 2019-01-07 | 036909C-JVD-TRN-00593 | 036909C-JVD-TRN-00593 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00593
036909C-1024-PDS-0900-2416 | Process Equipment Datasheet - 10-P-2415 A-B - CG Liquid Dryer Feed Pumps | B | 2019-01-04 | IFD | OL1-2G30-2416 | PE | 2019-01-07 | 036909C-JVD-TRN-00593 | 036909C-JVD-TRN-00593 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00593
036909C-1025-PDS-4100-2560 | Process Equipment Datasheet - 10-PK-2560 - PSA Unit | B | 2018-12-18 | IFD | OL1-2G30-2560 | PE | 2018-12-20 | 036909C-JVD-TRN-00530 | 036909C-JVD-TRN-00530 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00530
036909C-1025-PDS-0500-2570 | Process Equipment Datasheet - 10-T-2570 - Deethanizer | C | 2018-12-18 | IFD | OL1-2G30-2570 | PE | 2018-12-20 | 036909C-JVD-TRN-00538 | 036909C-JVD-TRN-00538 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00538
036909C-1024-PDS-0800-2415 | Process Equipment Datasheet - 10-D-2415 - CG Liquid Dryer Feed Coalescer | B | 2019-01-04 | IFD | OL1-2G30-2415 | PE | 2019-01-07 | 036909C-JVD-TRN-00596 | 036909C-JVD-TRN-00596 | IFI |  | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00596
036909C-1023-PDS-0500-2300 | Process Equipment Datasheet - 10-T-2300 - Caustic Tower | C | 2019-01-04 | IFD | OL1-2G30-2300 | PE | 2019-01-07 | 036909C-JVD-TRN-00597 | 036909C-JVD-TRN-00597 | IFI |  | 2019-01-28 | A1-Approved without comments | TPSK-LSPA1-T-PE-00597
036909C-1012-JSS-0125-2003 | Project Specification for Cast Intermediate Tube Supports | 1 | 2018-12-13 | IMP | OL1-2M92-2003 | ME | 2018-12-17 | 036909C-JVD-TRN-00517 | 036909C-JVD-TRN-00517 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00517
036909C-1012-SP-0125-2007 | Particular Technical Specification for Cast Intermediate Tube Supports | 0 | 2018-12-18 | IFP | OL1-2M57-2007 | ME | 2018-12-20 | 036909C-JVD-TRN-00542 | 036909C-JVD-TRN-00542 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00542
036909C-1012-MR-0125-2007 | Material Requisition for Cast Intermediate Tube Supports | 0 | 2018-12-18 | IFP | OL1-2M55-2007 | ME | 2018-12-20 | 036909C-JVD-TRN-00542 | 036909C-JVD-TRN-00542 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00542
036909C-1011-DW-0125-1301 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details | 1 | 2018-12-12 | IMP | OL1-2M06-1301 | ME | 2018-12-17 | 036909C-JVD-TRN-00520 | 036909C-JVD-TRN-00520 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00520
036909C-1011-DW-0125-1302 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details | 1 | 2018-12-12 | IMP | OL1-2M06-1302 | ME | 2018-12-17 | 036909C-JVD-TRN-00520 | 036909C-JVD-TRN-00520 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00520
036909C-1012-DW-0125-2301 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details | 1 | 2018-12-12 | IMP | OL1-2M06-2301 | ME | 2018-12-17 | 036909C-JVD-TRN-00520 | 036909C-JVD-TRN-00520 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00520
036909C-1012-DW-0125-2302 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details | 1 | 2018-12-12 | IMP | OL1-2M06-2302 | ME | 2018-12-17 | 036909C-JVD-TRN-00520 | 036909C-JVD-TRN-00520 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00520
036909C-1012-SP-0155-2018 | Particular Technical Specification for Furnace Steam Drums | 0 | 2018-12-11 | IFP | OL1-2M57-2018 | ME | 2018-12-17 | 036909C-JVD-TRN-00518 | 036909C-JVD-TRN-00518 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00518
036909C-1012-MR-0155-2018 | Material Requisition for Furnace Steam Drums | 0 | 2018-12-12 | IFP | OL1-2M55-2018 | ME | 2018-12-17 | 036909C-JVD-TRN-00518 | 036909C-JVD-TRN-00518 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00518
036909C-1012-JSS-0125-2003 | Project Specification for Cast Intermediate Tube Supports | 0 | 2018-10-15 | IFI | OL1-2M92-2003 | ME | 2018-10-26 | 036909C-JVD-TRN-00232 | 036909C-JVD-TRN-00232 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00232
036909C-1053-SP-0910-5352 | Mechanical Equipment DataSheet - Olefins Cooling Water Pumps | B | 2018-11-26 | IFQ | OL1-2M03-5352 | ME | 2018-11-28 | 036909C-JVD-TRN-00388 | 036909C-JVD-TRN-00388 | IFI |  | 2018-12-18 | R1-No comments | TPSK-LSPA1-T-ME-00388
036909C-1051-PDS-0600-5103 | Process Equipment Datasheet - 10-E-5100 - Deaerator Vent Condenser | B | 2018-11-19 | IFD | OL1-2G30-5103 | PE | 2018-11-26 | 036909C-JVD-TRN-00366 | 036909C-JVD-TRN-00366 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00366
036909C-1051-PDS-0600-5113 | Process Equipment Datasheet - 10-E-5113 - Foul Condensate Cooler | B | 2018-11-19 | IFD | OL1-2G30-5113 | PE | 2018-11-26 | 036909C-JVD-TRN-00366 | 036909C-JVD-TRN-00366 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00366
036909C-1023-PDS-0900-2306 | Process Equipment Datasheet - 10-P-2306 A-B - Weak Caustic Circulating Pumps | B | 2018-11-27 | IFD | OL1-2G30-2306 | PE | 2018-11-28 | 036909C-JVD-TRN-00382 | 036909C-JVD-TRN-00382 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00382
036909C-1023-PDS-4200-2308 | Process Equipment Datasheet - 10-X-2306 - Weak Caustic - Wash Oil Mixer | B | 2018-11-27 | IFD | OL1-2G30-2308 | PE | 2018-11-28 | 036909C-JVD-TRN-00383 | 036909C-JVD-TRN-00383 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00383
036909C-1023-PDS-0500-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper | C | 2018-11-27 | IFD | OL1-2G30-2330 | PE | 2018-11-28 | 036909C-JVD-TRN-00384 | 036909C-JVD-TRN-00384 | IFI |  | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00384
036909C-1023-PDS-0900-2304 | Process Equipment Datasheet - 10-P-2304 - Intermediate Caustic Circulating Pump | B | 2018-11-27 | IFD | OL1-2G30-2304 | PE | 2018-11-28 | 036909C-JVD-TRN-00382 | 036909C-JVD-TRN-00382 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00382
036909C-1021-PDS-0500-2140 | Process Equipment Datasheet - 10-T-2140 - Process Water Stripper | B | 2018-11-29 | IFD | OL1-2G30-2140 | PE | 2018-11-29 | 036909C-JVD-TRN-00401 | 036909C-JVD-TRN-00401 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00401
036909C-1020-PDS-0500-2000 | Process Equipment Datasheet - 10-T-2000 - Quench Oil Tower | B | 2018-11-29 | IFD | OL1-2G30-2000 | PE | 2018-12-04 | 036909C-JVD-TRN-00402 | 036909C-JVD-TRN-00402 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00402
036909C-1012-PDS-0117-1201 | Process Equipment Datasheet - 10-H-1200 - 132U Cracking Furnace Yields | B | 2018-11-27 | IFD | OL1-2G30-1201 | PE | 2018-11-27 | 036909C-JVD-TRN-00372 | 036909C-JVD-TRN-00372 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00372
036909C-1011-PDS-0117-1101 | Process Equipment Datasheet - 10-H-1100 - USM 36M Cracking Furnace Yields | B | 2018-11-15 | IFD | OL1-2G30-1101 | PE | 2018-11-26 | 036909C-JVD-TRN-00360 | 036909C-JVD-TRN-00360 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00360
036909C-1012-SP-0133-2008 | Particular Technical Specification for Peep Doors | A | 2018-12-06 | IFQ | OL1-2M57-2008 | ME | 2018-12-14 | 036909C-JVD-TRN-00502 | 036909C-JVD-TRN-00502 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00502
036909C-1012-SP-0122-2004 | Particular Technical Specification For Radiant Coil Assemblies | 0 | 2018-12-11 | IFP | OL1-2M57-2004 | ME | 2018-12-14 | 036909C-JVD-TRN-00499 | 036909C-JVD-TRN-00499 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00499
036909C-1021-PDS-0600-2125 | Process Equipment Datasheet - 10-E-2125 - Distillate Stripper Reboiler | B | 2018-12-11 | IFD | OL1-2G30-2125 | PE | 2018-12-13 | 036909C-JVD-TRN-00492 | 036909C-JVD-TRN-00492 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00492
036909C-1024-PDS-0600-2451 | Process Equipment Datasheet - 10-E-2450 - LP Depropanizer Condenser | B | 2018-11-28 | IFD | OL1-2G30-2451 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392
036909C-1024-PDS-0600-2413 | Process Equipment Datasheet - 10-E-2413 - HP Deprop Feed - Overhead Exchanger | B | 2018-11-28 | IFD | OL1-2G30-2413 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392
036909C-1026-PDS-0500-2640 | Process Equipment Datasheet - 10-T-2640 - C3 Tower | B | 2018-11-30 | IFD | OL1-2G30-2640 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-PE-00407
036909C-1025-PDS-0500-2580 | Process Equipment Datasheet - 10-T-2580 - C2 Tower | B | 2018-11-30 | IFD | OL1-2G30-2580 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-PE-00407
036909C-1025-PDS-0500-2520 | Process Equipment Datasheet - 10-T-2520 - 10-D2520 - Residue Gas Rectifier & Reflux Drum | B | 2018-11-30 | IFD | OL1-2G30-2520 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-PE-00407
036909C-1025-PDS-0500-2540 | Process Equipment Datasheet - 10-T-2540 - 10-D-2540 - Demethanizer & Reflux Drum | C | 2018-11-30 | IFD | OL1-2G30-2540 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-PE-00407
036909C-1026-PDS-0600-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler | C | 2018-12-04 | IFD | OL1-2G30-2635 | PE | 2018-12-07 | 036909C-JVD-TRN-00438 | 036909C-JVD-TRN-00438 | IFI |  | 2018-12-27 | A1-Approved without comments | TPSK-LSPA1-T-PE-00438
036909C-1026-PDS-0600-2645 | Process Equipment Datasheet - 10-E-2645 A-B - C3 Tower Reboilers | C | 2018-12-04 | IFD | OL1-2G30-2645 | PE | 2018-12-07 | 036909C-JVD-TRN-00438 | 036909C-JVD-TRN-00438 | IFI |  | 2018-11-27 | A1-Approved without comments | TPSK-LSPA1-T-PE-00438
036909C-1025-PDS-0600-2548 | Process Equipment Datasheet - 10-E-2548 - Demethanizer Bottoms Vaporizer | B | 2018-12-07 | IFD | OL1-2G30-2548 | PE | 2018-12-10 | 036909C-JVD-TRN-00464 | 036909C-JVD-TRN-00464 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00464
036909C-1025-PDS-0600-2502 | Process Equipment Datasheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | C | 2018-12-07 | IFD | OL1-2G30-2502 | PE | 2018-12-11 | 036909C-JVD-TRN-00475 | 036909C-JVD-TRN-00475 | IFI |  | 2019-01-10 | A1-Approved without comments | TPSK-LSPA1-T-PE-00475
036909C-1012-SP-0154-2003 | Particular Techanical Specification for Quench Exchangers | 0 | 2018-12-06 | IFP | OL1-2M57-2003 | ME | 2018-12-10 | 036909C-JVD-TRN-00466 | 036909C-JVD-TRN-00466 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00466
036909C-1012-SP-0127-2001 | Particular Technical Specification for Convection Tubes | 0 | 2018-12-04 | IFP | OL1-2M57-2001 | ME | 2018-12-10 | 036909C-JVD-TRN-00450 | 036909C-JVD-TRN-00450 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00450
036909C-1012-SP-0154-2003 | Particular Techanical Specification for Quench Exchangers | A | 2018-10-18 | IFQ | OL1-2M57-2003 | ME | 2018-10-26 | 036909C-JVD-TRN-00233 | 036909C-JVD-TRN-00233 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00233
036909C-1012-MR-0154-2003 | Material Requisition for Quench Exchangers | 0 | 2018-12-07 | IFP | OL1-2M55-2003 | ME | 2018-12-10 | 036909C-JVD-TRN-00466 | 036909C-JVD-TRN-00466 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00466
036909C-1012-MR-0154-2003 | Material Requisition for Quench Exchangers | A | 2018-10-18 | IFQ | OL1-2M55-2003 | ME | 2018-10-26 | 036909C-JVD-TRN-00233 | 036909C-JVD-TRN-00233 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00233
036909C-1012-JSS-0154-2008 | Project Specification For Transfer Line Exchangers | 0 | 2018-11-28 | IMP | OL1-2M92-2008 | ME | 2018-12-05 | 036909C-JVD-TRN-00428 | 036909C-JVD-TRN-00428 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00428
036909C-1012-JSS-0122-2002 | Project Specification for Statically Cast Fittings For Radiant Coils and Transfer Lines in Cracking Furnaces | 0 | 2018-12-07 | IMP | OL1-2M92-2002 | ME | 2018-12-11 | 036909C-JVD-TRN-00471 | 036909C-JVD-TRN-00471 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00471
036909C-1012-JSS-0154-2007 | Project Specification For SLE and USX Exchangers | 0 | 2018-11-28 | IMP | OL1-2M92-2007 | ME | 2018-12-05 | 036909C-JVD-TRN-00427 | 036909C-JVD-TRN-00427 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00427
036909C-1012-JSS-0122-2001 | Project Specification for Centrifugally Cast Tubes for Radiant Coils and Transfer Lines in Cracking Furnaces | 0 | 2018-12-07 | IMP | OL1-2M92-2001 | ME | 2018-12-11 | 036909C-JVD-TRN-00470 | 036909C-JVD-TRN-00470 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00470
036909C-1000-JSS-1310-0001 | Job Supply Specification For Valves (Gate - Globe - Check) | A | 2018-11-20 | IFR | OL1-2R04-0041 | MP | 2018-11-26 | 036909C-JVD-TRN-00356 | 036909C-JVD-TRN-00356 | IFR | 2018-12-11 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00356
036909C-1000-JSS-1310-0008 | Job Supply Specification For Ball Valves | A | 2018-11-20 | IFR | OL1-2R04-0010 | MP | 2018-11-26 | 036909C-JVD-TRN-00352 | 036909C-JVD-TRN-00352 | IFR | 2018-12-11 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00352
036909C-1000-JSS-1310-0006 | Job Supply Specification For Plug Valves | A | 2018-11-20 | IFR | OL1-2R04-0009 | MP | 2018-11-26 | 036909C-JVD-TRN-00352 | 036909C-JVD-TRN-00352 | IFR | 2018-12-11 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00352
036909C-1000-JSS-1310-0004 | Job Supply Specification For Butterfly Valves | A | 2018-11-20 | IFR | OL1-2R04-0008 | MP | 2018-11-26 | 036909C-JVD-TRN-00352 | 036909C-JVD-TRN-00352 | IFR | 2018-12-11 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00352
036909C-1025-PDS-0800-2555 | Process Equipment Datasheet - 10-D-2555 - Expander Discharge Drum | B | 2018-12-04 | IFD | OL1-2G30-2555 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  | 2018-12-18 | R2-Comments as noted | TPSK-LSPA1-T-PE-00430
036909C-1022-PDS-0600-2221 | Process Equipment Datasheet - 10-E-2220 A-B - CG 2nd Stage Aftercooler | B | 2018-12-04 | IFD | OL1-2G30-2221 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00431
036909C-1010-PDS-0600-1015 | Process Equipment Datasheet - 10-E-1015 - LPG Superheater | B | 2018-12-04 | IFD | OL1-2G30-1015 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00431
036909C-1021-PDS-0600-2166 | Process Equipment Datasheet - 10-E-2166 - DSG Blowdown Cooler | B | 2018-12-04 | IFD | OL1-2G30-2166 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00431
036909C-1024-PDS-0600-2445 | Process Equipment Datasheet - 10-E-2445 A-B - HP Depropanizer Reboilers | B | 2018-12-04 | IFD | OL1-2G30-2445 | PE | 2018-12-07 | 036909C-JVD-TRN-00436 | 036909C-JVD-TRN-00436 | IFI |  | 2018-12-18 | R1-No comments | TPSK-LSPA1-T-PE-00436
036909C-1010-PDS-0600-1051 | Process Equipment Datasheet - 10-E-1050 - C2 Feed Superheater | B | 2018-12-04 | IFD | OL1-2G30-1051 | PE | 2018-12-07 | 036909C-JVD-TRN-00436 | 036909C-JVD-TRN-00436 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00436
036909C-1021-PDS-0500-2120 | Process Equipment Datasheet - 10-T-2120 - Distillate Stripper | C | 2018-12-05 | IFD | OL1-2G30-2120 | PE | 2018-12-07 | 036909C-JVD-TRN-00437 | 036909C-JVD-TRN-00437 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00437
036909C-1020-PDS-0500-2020 | Process Equipment Datasheet - 10-T-2020 - Light Fuel Oil Stripper | B | 2018-12-05 | IFD | OL1-2G30-2020 | PE | 2018-12-07 | 036909C-JVD-TRN-00437 | 036909C-JVD-TRN-00437 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00437
036909C-1021-PDS-0500-2100 | Process Equipment Datasheet - 10-T-2100 - Quench Water Tower | B | 2018-12-05 | IFD | OL1-2G30-2100 | PE | 2018-12-07 | 036909C-JVD-TRN-00437 | 036909C-JVD-TRN-00437 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00437
036909C-1025-PDS-0800-2551 | Process Equipment Datasheet - 10-D-2550 - Expander Suction Drum | B | 2018-12-04 | IFD | OL1-2G30-2551 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00440
036909C-1021-PDS-0600-2165 | Process Equipment Datasheet - 10-E-2165 A-D - DSG Reboilers | B | 2018-12-07 | IFD | OL1-2G30-2165 | PE | 2018-12-10 | 036909C-JVD-TRN-00467 | 036909C-JVD-TRN-00467 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00467
036909C-1021-PDS-0600-2137 | Process Equipment Datasheet - 10-E-2136 - Process Water Stripper Feed Heater | B | 2018-12-07 | IFD | OL1-2G30-2137 | PE | 2018-12-10 | 036909C-JVD-TRN-00467 | 036909C-JVD-TRN-00467 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00467
036909C-1021-PDS-0600-2161 | Process Equipment Datasheet - 10-E-2160 - Dilution Steam Superheater | B | 2018-12-07 | IFD | OL1-2G30-2161 | PE | 2018-12-10 | 036909C-JVD-TRN-00467 | 036909C-JVD-TRN-00467 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00467
036909C-1051-SP-0910-5109 | Mechanical Equipment Data Sheet - Condensate Pumps | C | 2018-11-28 | IFQ | OL1-2M03-5109 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00476
036909C-1021-SP-0910-2146 | Mechanical Equipment Data Sheet - DSG Feed Pumps | B | 2018-11-28 | IFQ | OL1-2M03-2146 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00476
036909C-1021-SP-0910-2106 | Mechanical Equipment Data Sheet - Quench Water Pumps | B | 2018-11-28 | IFQ | OL1-2M03-2106 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00476
036909C-1020-SP-0910-2006 | Mechanical Equipment Data Sheet - Quench Oil Pump | B | 2018-11-28 | IFQ | OL1-2M03-2006 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00476
036909C-1051-SP-0910-5102 | Mechanical Equipment Data Sheet - VLP BFW Pumps | B | 2018-11-28 | IFQ | OL1-2M03-5102 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00476
036909C-1012-DW-0122-2202 | USC 132U Cracking Furnace Transfer Lines and Clean-Out Details | 0 | 2018-12-11 | IMP | OL1-2M06-2202 | ME | 2018-12-13 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00486
036909C-1012-DW-0122-2201 | USC 132U Cracking Furnace Radiant Coil Assembly and Details | 0 | 2018-12-11 | IMP | OL1-2M06-2201 | ME | 2018-12-13 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00486
036909C-1012-DW-0122-2203 | USC 132U Cracking Furnace Radiant Coil Tubeskin Thermocouple Details | 0 | 2018-12-11 | IMP | OL1-2M06-2203 | ME | 2018-12-13 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00486
036909C-1011-DW-0122-1201 | USC 36M Recycle Furnace Radiant Coil Assembly and Details | 0 | 2018-12-10 | IMP | OL1-2M06-1201 | ME | 2018-12-13 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00486
036909C-1011-DW-0122-1203 | USC 36M Recycle Furnace Radiant Coil Tubeskin Thermocouple Details | 0 | 2018-12-11 | IMP | OL1-2M06-1203 | ME | 2018-12-13 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00486
036909C-1011-DW-0122-1202 | USC 36M Recycle Furnace Transfer Line And Clean Out Details | 0 | 2018-12-11 | IMP | OL1-2M06-1202 | ME | 2018-12-13 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00486
036909C-102D-DW-1743-0013 | Foundation For 10-D-2815 | A | 2019-01-23 | IFR | OL1-2K34-0105 | CV | 2019-01-28 | 036909C-JVD-TRN-00734 | 036909C-JVD-TRN-00734 | IFR | 2019-02-12 |  | Transmitted | TPSK-LSPA1-T-CV-00734
036909C-102A-DW-1743-0009 | Foundation For 10-D-2160 | A | 2019-01-23 | IFR | OL1-2K34-0016 | CV | 2019-01-28 | 036909C-JVD-TRN-00734 | 036909C-JVD-TRN-00734 | IFR | 2019-02-12 |  | Transmitted | TPSK-LSPA1-T-CV-00734
036909C-1000-MR-0840-0001 | Material Requisition For Filters And Coalescers | A | 2019-01-22 | IFQ | OL1-2C13-152000 | PL | 2019-01-28 | 036909C-JVD-TRN-00737 | 036909C-JVD-TRN-00737 | IFR | 2019-02-12 |  | Transmitted | TPSK-LSPA1-T-PL-00737
036909C-102D-DW-1743-0010 | Foundation for 10-T-2520/10-D-2520 | A | 2019-01-23 | IFR | OL1-2K34-0099 | CV | 2019-01-28 | 036909C-JVD-TRN-00728 | 036909C-JVD-TRN-00728 | IFR | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-CV-00728
036909C-1000-JSS-1694-0001 | Medium Voltage Variable Voltage Variable Frequency System | 0 | 2018-09-20 | IMP | OL1-2R05-0040 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268
036909C-1000-DW-1662-0001 | Medium Voltage Protection Diagram | A | 2018-12-18 | IFR | OL1-2E19-0001 | EE | 2018-12-20 | 036909C-JVD-TRN-00555 | 036909C-JVD-TRN-00555 | IFR | 2019-01-04 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00555
036909C-1000-MR-1031-0001 | Material Requisition for Recycle Gas Compressor | A | 2019-01-23 | IFQ | OL1-2C13-403000 | PL | 2019-01-23 | 036909C-JVD-TRN-00714 | 036909C-JVD-TRN-00714 | IFR | 2019-02-06 |  | Transmitted | TPSK-LSPA1-T-PL-00714
036909C-1000-MR-0511-0001 | Material Requisition For Shop Assembled Large Columns | A | 2019-01-04 | IFQ | OL1-2C13-100000 | ME | 2019-01-07 | 036909C-JVD-TRN-00586 | 036909C-JVD-TRN-00586 | IFR | 2019-01-15 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00586
036909C-1030-PDS-1000-3073 | Process Equipment Data Sheet - 10-C-3070 - BDU Recycle Gas Compressor | B | 2019-01-15 | IFD | OL1-2G30-3073 | PE | 2019-01-18 | 036909C-JVD-TRN-00675 | 036909C-JVD-TRN-00675 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00675
036909C-1000-JSS-1160-0001 | ME-022 Special Purpose Gear | A | 2018-10-12 | IFR | OL1-2R03-0022 | ME | 2018-10-12 | 036909C-JVD-TRN-00166 | 036909C-JVD-TRN-00166 | IFR | 2018-10-26 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-ME-00166
036909C-1000-JSS-1140-0001 | ME-013 Diesel Engine | A | 2018-10-22 | IFR | OL1-2R03-0013 | ME | 2018-10-18 | 036909C-JVD-TRN-00196 | 036909C-JVD-TRN-00196 | IFR | 2018-11-06 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-ME-00196
036909C-1000-JSS-1013-0001 | ME-016 Centrifugal Compressor For PA/IA Servise | A | 2018-10-09 | IFR | OL1-2R03-0016 | ME | 2018-10-12 | 036909C-JVD-TRN-00164 | 036909C-JVD-TRN-00164 | IFR | 2018-10-26 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-ME-00164
036909C-1000-JSS-0910-0002 | ME-050 Centrifugal Pump (Non API) | A | 2018-10-25 | IFR | OL1-2R03-0500 | ME | 2018-11-12 | 036909C-JVD-TRN-00308 | 036909C-JVD-TRN-00308 | IFR | 2018-11-27 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-ME-00308
036909C-1000-JSS-1031-0001 | ME-047 Dry Screw Compressor for Hydrocarbon Services | A | 2018-11-30 | IFR | OL1-2R03-0047 | ME | 2018-12-06 | 036909C-JVD-TRN-00429 | 036909C-JVD-TRN-00429 | IFR | 2018-12-20 | 2018-12-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00429
036909C-1000-SP-1692-0001 | Particular Technical Specification for Medium Voltage Motors Medium Voltage Variable Voltage Variable Frequency System | A | 2018-12-14 | IFQ | OL1-2E57-4100 | EE | 2018-12-20 | 036909C-JVD-TRN-00540 | 036909C-JVD-TRN-00540 | IFR | 2018-12-19 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-EE-00540
036909C-1000-MR-1692-0001 | Material Requisition For Medium Voltage Motors Medium Voltage Variable Voltage Variable Frequency System | A | 2018-12-14 | IFQ | OL1-2E55-4100 | EE | 2018-12-20 | 036909C-JVD-TRN-00540 | 036909C-JVD-TRN-00540 | IFR | 2018-12-19 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-EE-00540
036909C-1000-MR-4234-0001 | Material Requisition for Side Stream Filter Package | A | 2018-10-29 | IFQ | OL1-2M55-0109 | ME | 2018-10-31 | 036909C-JVD-TRN-00248 | 036909C-JVD-TRN-00248 | IFR | 2018-11-16 | 2018-11-27 | R1-No comments | TPSK-LSPA1-T-ME-00248
036909C-1000-MR-1013-0001 | Material Requisition For Integrally Geared Decoking Air Compressors | A | 2018-10-18 | IFQ | OL1-2M55-0014 | ME | 2018-10-19 | 036909C-JVD-TRN-00198 | 036909C-JVD-TRN-00198 | IFR | 2018-11-02 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-ME-00198
036909C-1000-MR-0910-0001 | Material Requisition For API Centrifugal Pumps - LLI | A | 2018-10-30 | IFQ | OL1-2M55-0015 | ME | 2018-10-31 | 036909C-JVD-TRN-00257 | 036909C-JVD-TRN-00257 | IFR | 2018-11-20 | 2018-11-27 | R1-No comments | TPSK-LSPA1-T-ME-00257
036909C-1000-MR-0845-0001 | Material Requisition for Deareator | A | 2018-10-29 | IFQ | OL1-2M55-0108 | ME | 2018-11-06 | 036909C-JVD-TRN-00270 | 036909C-JVD-TRN-00270 | IFR | 2018-11-20 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00270
036909C-1000-MR-0570-0002 | Material Requisition For Ripple Trays And Internals | 0 | 2019-01-07 | IFP | OL1-2C13-243000 | PL | 2019-01-11 | 036909C-JVD-TRN-00628 | 036909C-JVD-TRN-00628 | IFR | 2019-01-25 |  | Transmitted | TPSK-LSPA1-T-PL-00628
036909C-1000-DW-1662-0002 | Low Voltage Protection Diagram | A | 2018-12-18 | IFR | OL1-2E19-0002 | EE | 2018-12-20 | 036909C-JVD-TRN-00555 | 036909C-JVD-TRN-00555 | IFR | 2019-01-04 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00555
036909C-1000-JSD-1600-008 | General Design Rules For Smartplant Electrical - Ex Document Client Reference OL1-2R05-0043 | 0 | 2018-11-09 | IFI | OL1-2E92-0001 | EE | 2018-11-29 | 036909C-JVD-TRN-00396 | 036909C-JVD-TRN-00396 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00396 | Ex Document Client Reference: OL1-2R05-0043
036909C-1000-SP-1661-0001 | Particular Technical Specification for Substation Monitoring & Control System (SMCS) | A | 2018-12-14 | IFQ | OL1-2E57-1800 | EE | 2018-12-17 | 036909C-JVD-TRN-00510 | 036909C-JVD-TRN-00510 | IFR | 2018-12-31 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00510
036909C-1000-MR-1661-0001 | Material Requisition for Substation Monitoring & Control System (SMCS) | A | 2018-12-14 | IFQ | OL1-2E55-1800 | EE | 2018-12-17 | 036909C-JVD-TRN-00510 | 036909C-JVD-TRN-00510 | IFR | 2018-12-31 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00510
036909C-1000-SP-1654-0001 | Particular Technical Specification for Low Voltage Switchgears/MCCs & Busducts | A | 2018-12-11 | IFQ | OL1-2E57-1200 | EE | 2018-12-14 | 036909C-JVD-TRN-00497 | 036909C-JVD-TRN-00497 | IFR | 2018-12-27 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00497
036909C-1000-MR-1654-0001 | Material Requisition for Low Voltage Switchgears/MCCs & Busducts | A | 2018-12-11 | IFQ | OL1-2E55-1200 | EE | 2018-12-14 | 036909C-JVD-TRN-00497 | 036909C-JVD-TRN-00497 | IFR | 2018-12-27 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00497
036909C-1000-SP-1655-1400 | Typical Data Sheet for Low Voltage Bus Ducts | A | 2018-12-11 | IFQ | CL1-2E05-1400 | EE | 2018-12-14 | 036909C-JVD-TRN-00497 | 036909C-JVD-TRN-00497 | IFR | 2018-12-27 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00497
036909C-1000-SP-1654-1200 | Typical Data Sheet for Low Voltage Switchgears/MCCs | A | 2018-12-11 | IFQ | CL1-2E05-1200 | EE | 2018-12-14 | 036909C-JVD-TRN-00497 | 036909C-JVD-TRN-00497 | IFR | 2018-12-27 | 2019-01-07 | R1-No comments | TPSK-LSPA1-T-EE-00497
036909C-1000-SP-1652-1100 | Typical Data Sheet for Medium Voltage Switchgears | A | 2018-12-07 | IFQ | OL1-2E05-1100 | EE | 2018-12-11 | 036909C-JVD-TRN-00477 | 036909C-JVD-TRN-00477 | IFR | 2018-12-25 | 2019-01-07 | R1-No comments | TPSK-LSPA1-T-ME-00476
036909C-1000-MR-1652-0001 | Material Requisition for Medium Voltage Switchgears | A | 2018-12-07 | IFQ | OL1-2E55-1100 | EE | 2018-12-11 | 036909C-JVD-TRN-00477 | 036909C-JVD-TRN-00477 | IFR | 2018-12-25 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-ME-00476
036909C-1000-SP-1652-0001 | Particular Technical Specification for Medium Voltage Switchgears | A | 2018-12-07 | IFQ | OL1-2E57-1100 | EE | 2018-12-11 | 036909C-JVD-TRN-00477 | 036909C-JVD-TRN-00477 | IFR | 2018-12-25 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-ME-00476
036909C-1000-JSD-3400-0001 | Air Conditioning Ventilating And Ducting Design | A | 2018-10-12 | IFR | OL1-2H03-0001 | EE | 2018-10-12 | 036909C-JVD-TRN-00165 | 036909C-JVD-TRN-00165 | IFR | 2018-10-26 | 2018-10-26 | R2-Comments as noted | TPSK-LSPA1-T-EE-00165
036909C-1000-SP-1692-4100 | Typical Data Sheet For MV Motor | A | 2018-12-14 | IFQ | OL1-2E05-4100 | EE | 2018-12-20 | 036909C-JVD-TRN-00529 | 036909C-JVD-TRN-00529 | IFR | 2019-01-02 | 2019-01-03 | R1-No comments | TPSK-LSPA1-T-EE-00529
036909C-1000-SP-1692-1700 | Typical Data Sheet For Medium Voltage Variable Voltage Variable Frequency System | A | 2018-12-14 | IFQ | OL1-2E05-1700 | EE | 2018-12-20 | 036909C-JVD-TRN-00529 | 036909C-JVD-TRN-00529 | IFR | 2019-01-02 | 2019-01-03 | R1-No comments | TPSK-LSPA1-T-EE-00529
036909C-1000-SP-1691-0001 | Particular Technical Specification For Low Voltage Motors Low Voltage Variable Voltage Variable Frequency System | A | 2018-11-16 | IFQ | OL1-2E57-3001 | EE | 2018-11-26 | 036909C-JVD-TRN-00359 | 036909C-JVD-TRN-00359 | IFR | 2018-12-11 | 2019-01-03 | R2-Comments as noted | TPSK-LSPA1-T-EE-00359
036909C-1000-MR-1691-0001 | Material Requisition For Low Voltage Motors Low Voltage Variable Voltage Variable Frequency System | A | 2018-11-16 | IFQ | OL1-2E55-3001 | EE | 2018-11-26 | 036909C-JVD-TRN-00359 | 036909C-JVD-TRN-00359 | IFR | 2018-12-11 | 2019-01-03 | R2-Comments as noted | TPSK-LSPA1-T-EE-00359
036909C-1000-DW-1422-0001 | Soil Investigation Plan | B | 2018-10-10 | IFR | OL1-2K43-0004 | CV | 2018-10-12 | 036909C-JVD-TRN-00163 | 036909C-JVD-TRN-00163 | IFR | 2018-10-26 | 2018-12-24 | R1-No comments | TPSK-LSPA1-T-CV-00163
036909C-1000-STC-1390-0001 | Piping Standard Construction Drawings - For next revision see document OL1-2R04-0001 - included as attachment | 0 | 2018-11-12 | CAN | OL1-2P92-0003 | MP | 2018-11-16 | 036909C-JVD-TRN-00325 | 036909C-JVD-TRN-00325 | IFR | 2018-12-03 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00325 | For next revision see document OL1-2R04-0001 - included as attachment
036909C-1000-JSS-1654-0001 | Low Voltage Switchgear And Motor Control Center | 0 | 2018-09-20 | IFE | OL1-2R05-0008 | EE | 2018-11-12 | 036909C-JVD-TRN-00309 | 036909C-JVD-TRN-00309 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00309
036909C-1000-JSS-1655-0001 | Low Voltage Bus Duct | 0 | 2018-09-20 | IMP | OL1-2R05-0038 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268
036909C-1000-JSS-1641-0002 | Neutral Grounding Resistor | 0 | 2018-12-03 | IMP | OL1-2R05-0027 | EE | 2018-12-05 | 036909C-JVD-TRN-00425 | 036909C-JVD-TRN-00425 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00425
036909C-1000-JSS-1652-0001 | Medium Voltage Switchgear | 0 | 2018-09-20 | IMP | OL1-2R05-0006 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268
036909C-1000-SP-0910-0003 | Particular Technical Specification for Cooling Water Pumps | A | 2018-11-14 | IFQ | OL1-2M57-0003 | ME | 2018-11-15 | 036909C-JVD-TRN-00319 | 036909C-JVD-TRN-00319 | IFR | 2018-11-29 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00319
036909C-1000-MR-0910-0003 | Material Requisition for Cooling Water Pumps | A | 2018-11-14 | IFQ | OL1-2M55-0003 | ME | 2018-11-15 | 036909C-JVD-TRN-00319 | 036909C-JVD-TRN-00319 | IFR | 2018-11-29 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00319
036909C-1028-PDS-0800-2870 | Process Equipment Datasheet - 10-D-2870 - C2R 2nd Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2870 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349
036909C-1000-SP-0570-0001 | Particular Technical Specification For Trays For Columns | A | 2018-11-06 | IFQ | OL1-2M57-0055 | ME | 2018-11-09 | 036909C-JVD-TRN-00300 | 036909C-JVD-TRN-00300 | IFR | 2018-11-26 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-ME-00300
036909C-1000-MR-0570-0001 | Material Requisition For Trays For Columns Requisition For Inquiry | A | 2018-11-06 | IFQ | OL1-2M55-0055 | ME | 2018-11-09 | 036909C-JVD-TRN-00300 | 036909C-JVD-TRN-00300 | IFR | 2018-11-26 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-ME-00300
036909C-1000-PP-1600-003 | Coordination Procedure For ETAP | 0 | 2018-12-03 | IFI | OL1-2E92-0003 | EE | 2018-12-05 | 036909C-JVD-TRN-00426 | 036909C-JVD-TRN-00426 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00426 | Ex Document Client Reference: OL1-2R05-0045
036909C-1000-PP-1600-001 | Coordination Procedure For Smartplant Electrical | 0 | 2018-11-09 | IFI | OL1-2E92-0002 | EE | 2018-11-29 | 036909C-JVD-TRN-00395 | 036909C-JVD-TRN-00395 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00395 | Ex Document Client Reference: OL1-2R05-0044
036909C-1000-SP-0570-0004 | Particular Technical Specification For MD Trays For Columns | A | 2018-10-31 | IFQ | OL1-2M57-0075 | ME | 2018-11-07 | 036909C-JVD-TRN-00278 | 036909C-JVD-TRN-00278 | IFR | 2018-11-21 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00278
036909C-1000-MR-0570-0004 | Material Requisition For MD Trays For Columns Requisition For Inquiry | A | 2018-10-31 | IFQ | OL1-2M55-0075 | ME | 2018-11-07 | 036909C-JVD-TRN-00278 | 036909C-JVD-TRN-00278 | IFR | 2018-11-21 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00278
036909C-1000-SP-1013-0001 | Particular Technical Specification for Integrally Geared Decoking Air Compressors | A | 2018-10-18 | IFQ | OL1-2M57-0014 | ME | 2018-10-19 | 036909C-JVD-TRN-00198 | 036909C-JVD-TRN-00198 | IFR | 2018-11-02 | 2018-11-07 | Transmitted | TPSK-LSPA1-T-ME-00198
036909C-1053-SP-4234-0002 | Mechanical Equipment Datasheet for Side Stream Filter Package | B | 2018-10-29 | IFQ | OL1-2M03-5355 | ME | 2018-10-31 | 036909C-JVD-TRN-00248 | 036909C-JVD-TRN-00248 | IFR | 2018-11-16 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00248
036909C-1000-SP-4234-0001 | Particular Technical Specification for Side Steam Filter Package | A | 2018-10-29 | IFQ | OL1-2M57-0109 | ME | 2018-10-31 | 036909C-JVD-TRN-00248 | 036909C-JVD-TRN-00248 | IFR | 2018-11-16 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00248
036909C-1000-SP-0910-0001 | Particular Technical Specification For API Centrifugal Pumps - LLI | A | 2018-10-30 | IFQ | OL1-2M57-0015 | ME | 2018-10-31 | 036909C-JVD-TRN-00257 | 036909C-JVD-TRN-00257 | IFR | 2018-11-20 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00257
036909C-1000-JSS-4123-0001 | Diesel Engine Generator | 0 | 2018-09-20 | IMP | OL1-2R05-0017 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268
036909C-1000-JSS-1684-0001 | Cathodic Protection | 0 | 2018-09-20 | IMP | OL1-2R05-0016 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268
036909C-1000-JSS-1641-0001 | Oil Filled Distribution Transformer | 0 | 2018-09-20 | IMP | OL1-2R05-0003 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268
036909C-1000-SP-0845-0001 | Particular Technical Specification For Deaerator | A | 2018-10-29 | IFQ | OL1-2M57-0108 | ME | 2018-11-06 | 036909C-JVD-TRN-00270 | 036909C-JVD-TRN-00270 | IFR | 2018-11-20 | 2018-11-29 | Transmitted | TPSK-LSPA1-T-ME-00270
036909C-1000-MS-1422-0001 | Technical Specification for Geotechnical Investigation | B | 2018-10-15 | IFR | OL1-2K43-0002 | CV | 2018-10-17 | 036909C-JVD-TRN-00188 | 036909C-JVD-TRN-00188 | IFR | 2018-11-05 | 2018-11-01 | R1-No comments | TPSK-LSPA1-T-CV-00188
036909C-1000-PS-1422-0001 | Price List for Geotechnical Investigation | B | 2018-10-15 | IFR | OL1-2K43-0003 | CV | 2018-10-17 | 036909C-JVD-TRN-00188 | 036909C-JVD-TRN-00188 | IFR | 2018-11-05 | 2018-11-01 | R1-No comments | TPSK-LSPA1-T-CV-00188
036909C-102D-CN-1733-0003 | Calculation Note For Foundation Of 10-T-2640 | A | 2019-03-13 | IFR | OL1-2K13-0089 | CV | 2019-03-18 | 036909C-JVD-TRN-01071 | 036909C-JVD-TRN-01071 | IFA | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-CV-01071 |  | 2019-03-18
036909C-102D-CN-1733-0027 | Calculation Note For Foundation of 10-E-2645A-B | A | 2019-03-06 | IFR | OL1-2K13-0116 | CV | 2019-03-15 | 036909C-JVD-TRN-01059 | 036909C-JVD-TRN-01059, 036909C-JVD-TRN-01071 | IFA | 2019-03-29 |  | Transmitted | TPSL-LSPA1-T-CV-01059 |  | 2019-03-15
036909C-1027-TDS-0630-2723 | Mechanical Equipment Data Sheet - 10-E-2724 - Wash Oil Condenser | A | 2019-02-21 | IFQ | OL1-2M03-2723 | ME | 2019-02-26 | 036909C-JVD-TRN-00929 | 036909C-JVD-TRN-00929 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00929 |  | 2019-02-26
036909C-1000-MR-0411-0001 | Material Requisition For Reactors And Thicker Vessels Requisition For Iinquiry | A | 2019-02-21 | IFQ | OL1-2C13-111000 | PL | 2019-02-26 | 036909C-JVD-TRN-00918 | 036909C-JVD-TRN-00918 | IFR | 2019-03-12 |  | Transmitted | TPSK-LSPA1-T-PL-00918 |  | 2019-02-26
036909C-1021-TDS-0661-2101 | Mechanical Equipment Data Sheet - 10-E-2100 - Quench Water Cooler | B | 2018-10-09 | IFQ | OL1-2M03-2101 | ME | 2018-10-11 | 036909C-JVD-TRN-00154 | 036909C-JVD-TRN-00154 | IFI |  | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-ME-00154 |  | 2018-10-11
036909C-1000-MR-0662-0002 | Material Requisition For Cold Box And Core Exchangers Requisition For Inquiry | B | 2018-10-09 | IFQ | OL1-2M55-0066 | ME | 2018-10-11 | 036909C-JVD-TRN-00153 | 036909C-JVD-TRN-00153 | IFR | 2018-10-24 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-ME-00153 |  | 2018-10-11
036909C-1000-JSS-6300-04 | Job Specification For Supply Positive Alloy Material Identification Of Equipment And Piping | 0 | 2019-02-21 | IMP | OL1-2R03-0003 | ME | 2019-02-26 | 036909C-JVD-TRN-00921 | 036909C-JVD-TRN-00921 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00921 |  | 2019-02-26
036909C-1000-JSS-6300-02 | Job Specification For Welding And NDE Of Pressure Vessel And Heat Exchanger | 0 | 2019-02-21 | IMP | OL1-2R03-0001 | ME | 2019-02-26 | 036909C-JVD-TRN-00921 | 036909C-JVD-TRN-00921 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00921 |  | 2019-02-26
036909C-1000-JSS-6300-05 | Job Specification For Welding And NDE Storage Tenks | 0 | 2019-02-21 | IMP | OL1-2R03-0004 | ME | 2019-02-26 | 036909C-JVD-TRN-00921 | 036909C-JVD-TRN-00921 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00921 |  | 2019-02-26
036909C-1028-PDS-0600-2882 | Process Equipment Datasheet - 10-E-2882 - LP Ethylene Product Cooler No 1 | B | 2018-10-03 | IFD | OL1-2G30-2882 | PE | 2018-10-05 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05
036909C-1025-PDS-0600-2526 | Process Equipment Datasheet - 10-E-2525 - Hydrogen Core Exchanger | B | 2018-10-03 | IFD | OL1-2G30-2526 | PE | 2018-10-05 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05
036909C-1025-PDS-0600-2585 | Process Equipment Datasheet - 10-E-2585 - C2 Tower Bottoms Reboiler | B | 2018-10-03 | IFD | OL1-2G30-2585 | PE | 2018-10-05 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05
036909C-1025-PDS-0600-2531 | Process Equipment Datasheet - 10-E-2530 - Demeth Feed Cooler | B | 2018-10-03 | IFD | OL1-2G30-2531 | PE | 2018-10-05 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05
036909C-1000-SL-0000-02 | Subvendor List For Compressor And Turboexpander - Abstract From Approved Vendor List | 0 | 2018-10-05 | IMP | OL1-2C01-0001 | PL | 2018-10-05 | 036909C-JVD-TRN-00134 | 036909C-JVD-TRN-00134 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00134 |  | 2018-10-05
036909C-1025-PDS-0600-2511 | Process Equipment Datasheet - 10-E-2510 - Demeth Prefrac Condenser | B | 2018-10-03 | IFD | OL1-2G30-2511 | PE | 2018-10-05 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05
036909C-1000-MR-1011-0001 | Material Requisition For Centrifugal Compressors Steam Turbine Driven | A | 2018-10-04 | IFQ | OL1-2M55-0008 | ME | 2018-10-08 | 036909C-JVD-TRN-00136 | 036909C-JVD-TRN-00136 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-ME-00136 |  | 2018-10-08
036909C-1000-JSD-1501-0001 | Instrument Numbering | A | 2018-10-03 | IFR | OL1-2R06-0022 | IE | 2018-10-05 | 036909C-JVD-TRN-00132 | 036909C-JVD-TRN-00132 | IFR | 2018-10-19 | 2018-10-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05
036909C-1028-SP-1011-2850 | Mechanical Equipment Data Sheet for Ethylene Refrigeration Compressor | B | 2018-10-02 | IFQ | OL1-2M03-2850 | ME | 2018-10-04 | 036909C-JVD-TRN-00127 | 036909C-JVD-TRN-00127 | IFI |  | 2018-10-26 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00127 |  | 2018-10-04
036909C-1000-SP-0662-0002 | Particular Technical Specification For Cold Box And Core Exchangers | A | 2018-10-01 | IFQ | OL1-2M57-0066 | ME | 2018-10-04 | 036909C-JVD-TRN-00125 | 036909C-JVD-TRN-00125 | IFR | 2018-10-17 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00125 |  | 2018-10-04
036909C-1025-PDS-0600-2587 | Process Equipment Datasheet - 10-E-2587 - C2 Tower Side Reboiler | B | 2018-10-03 | IFD | OL1-2G30-2587 | PE | 2018-10-05 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05
036909C-1025-SP-1011-2550 | Mechanical Equipment Datasheet for Residue Gas Expander-Recompressor | B | 2018-10-04 | IFQ | OL1-2M03-2550 | ME | 2018-10-05 | 036909C-JVD-TRN-00130 | 036909C-JVD-TRN-00130 | IFI |  | 2018-10-26 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00130 |  | 2018-10-05
036909C-1025-PDS-0600-2500 | Process Equipment Datasheet - 10-E-2500 - Propylene Refrig Subcooler | B | 2018-10-03 | IFD | OL1-2G30-2500 | PE | 2018-10-05 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05
036909C-1025-PDS-0600-2505 | Process Equipment Datasheet - 10-E2506 and 10-E2508 - Demeth Prefrac Feed Cooler No 3 and No 4 | B | 2018-10-03 | IFD | OL1-2G30-2505 | PE | 2018-10-05 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05
036909C-1028-SP-1011-2800 | Mechanical Equipment Data Sheet for Propylene Refrigeration Compressor | B | 2018-10-02 | IFQ | OL1-2M03-2800 | ME | 2018-10-04 | 036909C-JVD-TRN-00127 | 036909C-JVD-TRN-00127 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00127 |  | 2018-10-04
036909C-1025-PDS-0600-2541 | Process Equipment Datasheet - 10-E-2540 - Demethanizer Condenser | B | 2018-10-03 | IFD | OL1-2G30-2541 | PE | 2018-10-05 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05
036909C-1022-SP-1011-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor | B | 2018-10-02 | IFQ | OL1-2M03-2200 | ME | 2018-10-04 | 036909C-JVD-TRN-00127 | 036909C-JVD-TRN-00127 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00127 |  | 2018-10-04
036909C-1028-PDS-0600-2884 | Process Equipment Datasheet - 10-E-2884 - LP Ethylene Product Cooler No 2 | B | 2018-10-03 | IFD | OL1-2G30-2884 | PE | 2018-10-05 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05
036909C-1052-PDS-0600-5201 | Process Equipment Datasheet - 10-E-5200 - MP Ethylene Superheater | B | 2019-01-29 | IFD | OL1-2G30-5201 | PE | 2019-02-15 | 036909C-JVD-TRN-00853 | 036909C-JVD-TRN-00853 | IFR | 2019-03-01 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00853 |  | 2019-02-15
036909C-1052-PDS-0600-5201 | Process Equipment Datasheet - 10-E-5200 - MP Ethylene Superheater | A | 2018-11-05 | IFR | OL1-2G30-5201 | PE | 2018-11-05 | 036909C-JVD-TRN-00275 | 036909C-JVD-TRN-00275 | IFR | 2018-11-19 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-PE-00275
036909C-102D-DW-1743-0033 | Foundation For 10-E-2546 | A | 2019-02-08 | IFR | OL1-2K34-0126 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15
036909C-102D-DW-1743-0034 | Foundation For 10-E-2548 | A | 2019-02-04 | IFR | OL1-2K34-0127 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15
036909C-102D-DW-1743-0037 | Foundation For 10-E-2856 | A | 2019-02-07 | IFR | OL1-2K34-0134 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15
036909C-102D-DW-1743-0041 | Foundation For 10-E-2858 | A | 2019-02-08 | IFR | OL1-2K34-0133 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15
036909C-102D-DW-1743-0043 | Foundation For 10-E-2582 | A | 2019-02-07 | IFR | OL1-2K34-0139 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15
036909C-102D-DW-1743-0026 | Foundation For 10-E-2809 | A | 2019-02-07 | IFR | OL1-2K34-0131 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15
036909C-102D-DW-1743-0025 | Foundation For 10-E-2807 | A | 2019-02-06 | IFR | OL1-2K34-0130 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15
036909C-102D-DW-1743-0024 | Foundation For 10-D-2865 | A | 2019-02-06 | IFR | OL1-2K34-0116 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15
036909C-102D-DW-1743-0020 | Foundation For 10-D-2575 | A | 2019-02-11 | IFR | OL1-2K34-0112 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15
036909C-102B-DW-1743-0002 | Foundation For 10-T-2330 | A | 2019-02-07 | IFR | OL1-2K34-0042 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15
036909C-102A-DW-1743-0034 | Foundation For 10-E-2008A/B/C/D/E | A | 2019-02-05 | IFR | OL1-2K34-0191 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15
036909C-102A-DW-1743-0019 | Foundation For 10-E-2026 | A | 2019-02-08 | IFR | OL1-2K34-0026 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15
036909C-102A-DW-1743-0017 | Foundation For 10-E-2146 | A | 2019-02-05 | IFR | OL1-2K34-0024 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15
036909C-102A-DW-1743-0008 | Foundation for 10-D-5150 | A | 2019-02-05 | IFR | OL1-2K34-0015 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15
036909C-101B-DW-1743-0001 | Foundation For 10-D-5200 | A | 2019-02-05 | IFR | OL1-2K34-0007 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15
036909C-102D-DW-1743-0043 | Foundation For 10-E-2582 | B | 2019-02-19 | IFR | OL1-2K34-0139 | CV | 2019-02-21 | 036909C-JVD-TRN-00903 | 036909C-JVD-TRN-00903 | IFR | 2019-03-08 |  | Transmitted | TPSK-LSPA1-T-CV-00903 |  | 2019-02-21
036909C-102A-DW-1743-0003 | Foundation For 10-T-2100 | A | 2019-02-05 | IFR | OL1-2K34-1040 | CV | 2019-02-21 | 036909C-JVD-TRN-00903 | 036909C-JVD-TRN-00903 | IFR | 2019-03-08 |  | Transmitted | TPSK-LSPA1-T-CV-00903 |  | 2019-02-21
036909C-1000-MR-0661-0001 | Material Requisition For Plate And Frame Heat Exchangers Requisition For Inquiry | A | 2018-10-01 | IFQ | OL1-2M55-0064 | ME | 2018-10-04 | 036909C-JVD-TRN-00124 | 036909C-JVD-TRN-00124 | IFR | 2018-10-17 | 2018-10-24 | A1-Approved without comments | TPSK-LSPA1-T-ME-00124 |  | 2018-10-04
036909C-1000-MR-0661-0001 | Material Requisition Plate And Frame Heat Exchangers Requisition For Purchase | 0 | 2019-02-25 | IFP | OL1-2C13-142000 | PL | 2019-02-26 | 036909C-JVD-TRN-00916 | 036909C-JVD-TRN-00916 | IFR | 2019-03-12 |  | Transmitted | TPSK-LSPA1-T-PL-00916 |  | 2019-02-26
036909C-1056-DI-0007-5601 | Area Basis of Design - 56 Waste Water Treatment System | C | 2019-02-19 | IFD | OL1-2G05-5601 | PE | 2019-02-26 | 036909C-JVD-TRN-00920 | 036909C-JVD-TRN-00920, ROC-TPSK-CECO-T-00001 | IFR | 2019-03-12 |  | Transmitted | TPSK-LSPA1-T-PE-00920 |  | 2019-02-26
036909C-1056-DI-0007-5601 | Area Basis of Design - 56 Waste Water Treatment System | A | 2018-08-03 | IFA | OL1-2G05-5601 | PE | 2018-08-08 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | 2018-08-08
036909C-1056-DI-0007-5601 | Area Basis of Design - 56 Waste Water Treatment System | B | 2018-09-13 | IFD | OL1-2G05-5601 | PE | 2018-09-27 | 036909C-JVD-TRN-00091 | 036909C-JVD-TRN-00091 | IFI |  | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00091 |  | 2018-09-27
036909C-1000-JSS-6300-03 | Job Specification For Materials In Sour Service | 0 | 2019-02-21 | IMP | OL1-2R03-0002 | ME | 2019-02-26 | 036909C-JVD-TRN-00921 | 036909C-JVD-TRN-00921 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00921 |  | 2019-02-26
036909C-1000-JSS-6300-02 | Jo b Specification For Weldings and NDE Of Pressure Vessels And Heat Exchangers | A | 2018-08-24 | IFR | OL1-2R03-0001 | MP | 2018-08-29 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-ME-00029 |  | 2018-08-29
036909C-1030-PDS-0500-3080 | Process Equipment Datasheet - 10-T-3080 - Butadiene Tower | A | 2019-02-20 | IFR | OL1-2G30-3080 | PE | 2019-02-26 | 036909C-JVD-TRN-00923 | 036909C-JVD-TRN-00923 | IFR | 2019-03-12 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00923 |  | 2019-02-26
036909C-1030-PDS-0500-3060 | Process Equipment Datasheet - 10-T-3060 - C4 Acetylene Washer | A | 2019-02-20 | IFR | OL1-2G30-3060 | PE | 2019-02-26 | 036909C-JVD-TRN-00923 | 036909C-JVD-TRN-00923 | IFR | 2019-03-12 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00923 |  | 2019-02-26
036909C-1030-PDS-0500-3010 | Process Equipment Datasheet - 10-T-3010 - C4 Vaporization Tower | A | 2019-02-08 | IFR | OL1-2G30-3010 | PE | 2019-02-26 | 036909C-JVD-TRN-00923 | 036909C-JVD-TRN-00923 | IFR | 2019-03-12 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00923 |  | 2019-02-26
036909C-1030-PDS-0500-3000 | Process Equipment Datasheet - 10-T-3000 - Predistillation Tower | A | 2019-02-12 | IFR | OL1-2G30-3000 | PE | 2019-02-26 | 036909C-JVD-TRN-00923 | 036909C-JVD-TRN-00923 | IFR | 2019-03-12 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00923 |  | 2019-02-26
036909C-1027-PDS-0600-2755 | Process Equipment Datasheet - 10-E-2755 - C4 - C5 Hydrog Start-up Heater | A | 2019-02-21 | IFR | OL1-2G30-2755 | PE | 2019-02-26 | 036909C-JVD-TRN-00924 | 036909C-JVD-TRN-00924 | IFR | 2019-03-12 |  | Transmitted | TPSK-LSPA1-T-PE-00924 |  | 2019-02-26
036909C-1029-SP-0940-2911 | Mechanical Equipment Datasheet - Wash Oil Injection Pump | A | 2019-02-20 | IFQ | OL1-2M03-2911 | ME | 2019-02-26 | 036909C-JVD-TRN-00925 | 036909C-JVD-TRN-00925 | IFR | 2019-03-12 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00925 |  | 2019-02-26
036909C-1056-SP-2510-5640 | Mechanical Equipment Data Sheet - Oily Wastewater Tank | A | 2019-02-22 | IFQ | OL1-2M03-5640 | ME | 2019-02-26 | 036909C-JVD-TRN-00926 | 036909C-JVD-TRN-00926 | IFR | 2019-03-12 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-00926 |  | 2019-02-26
036909C-1027-TDS-0610-2707 | Mechanical Equipment Data Sheet - 10-E-2706 - GHU-1 Cooler | A | 2019-02-21 | IFQ | OL1-2M03-2707 | ME | 2019-02-26 | 036909C-JVD-TRN-00927 | 036909C-JVD-TRN-00927 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00927 |  | 2019-02-26
036909C-1026-TDS-0610-2621 | Mechanical Equipment Data Sheet - 10-E-2620 - C3 Hydrog Aftercooler | A | 2019-02-21 | IFQ | OL1-2M03-2621 | ME | 2019-02-26 | 036909C-JVD-TRN-00929 | 036909C-JVD-TRN-00929 | IFR | 2019-03-12 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-00929 |  | 2019-02-26
036909C-1051-TDS-0661-5108 | Mechanical Equipment Data Sheet - 10-E-5110 - Suspect Condensate Cooler | 0 | 2019-02-21 | IFP | OL1-2M03-5108 | ME | 2019-02-26 | 036909C-JVD-TRN-00930 | 036909C-JVD-TRN-00930 | IFR | 2019-03-12 |  | Transmitted | TPSK-LSPA1-T-ME-00930 |  | 2019-02-26
036909C-1051-TDS-0661-5108 | Mechanical Equipment Data Sheet - 10-E-5110 - Suspect Condensate Cooler | A | 2019-01-23 | IFQ | OL1-2M03-5108 | ME | 2019-01-25 | 036909C-JVD-TRN-00723 | 036909C-JVD-TRN-00723 | IFR | 2019-02-07 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00723
036909C-1021-TDS-0661-2101 | Mechanical Data Sheet - 10-E-2100 - Quench Water Cooler | A | 2018-09-14 | IFA | OL1-2M03-2101 | ME | 2018-09-18 | 036909C-JVD-TRN-00058 | 036909C-JVD-TRN-00058 | IFA | 2018-10-01 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00058 |  | 2018-09-18
036909C-1025-SP-0510-2570 | Mechanical Equipment Data Sheet - Deethanizer | C | 2019-02-19 | IFQ | OL1-2M03-2570 | ME | 2019-02-27 | 036909C-JVD-TRN-00931 | 036909C-JVD-TRN-00931 | IFR | 2019-03-13 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-00931 |  | 2019-02-27
036909C-1030-PDS-0500-3020 | Process Equipment Datasheet - 10-T-3020 - Main Washer | A | 2019-02-26 | IFR | OL1-2G30-3020 | PE | 2019-02-27 | 036909C-JVD-TRN-00932 | 036909C-JVD-TRN-00932 | IFR | 2019-03-13 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00932 |  | 2019-02-27
036909C-1030-PDS-0500-3090 | Process Equipment Datasheet - 10-T-3090 - Butadiene Drying Tower | A | 2019-02-26 | IFR | OL1-2G30-3090 | PE | 2019-02-27 | 036909C-JVD-TRN-00932 | 036909C-JVD-TRN-00932 | IFR | 2019-03-13 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00932 |  | 2019-02-27
036909C-1000-MR-0662-0002 | Material Requisition For Cold Box And Core Exchangers Requisition For Inquiry | A | 2018-10-01 | IFQ | OL1-2M55-0066 | ME | 2018-10-04 | 036909C-JVD-TRN-00125 | 036909C-JVD-TRN-00125 | IFR | 2018-10-17 | 2018-10-24 | A1-Approved without comments | TPSK-LSPA1-T-ME-00125 |  | 2018-10-04
036909C-1030-DI-0007-3001 | Area Basis of Design - 30 BDU | A | 2018-10-09 | IFA | OL1-2G05-3001 | PE | 2018-10-10 | 036909C-JVD-TRN-00150 | 036909C-JVD-TRN-00150, ROC-TPSK-CECO-T-00001 | IFA | 2018-10-23 |  | Transmitted | TPSK-LSPA1-T-PE-00150 |  | 2018-10-10
036909C-1000-JSD-1580-0001 | Integrated Turbine And Compressor Control System | A | 2018-10-08 | IFR | OL1-2R06-0017 | IE | 2018-10-09 | 036909C-JVD-TRN-00148 | 036909C-JVD-TRN-00148 | IFR | 2018-10-24 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-IE-00148 |  | 2018-10-09
036909C-1000-PS-1422-0001 | Price List For Geotechnical Investigation | A | 2018-10-04 | IFR | OL1-2K43-0003 | CV | 2018-10-09 | 036909C-JVD-TRN-00147 | 036909C-JVD-TRN-00147 | IFR | 2018-10-24 | 2018-12-24 | R1-No comments | TPSK-LSPA1-T-CV-00147 |  | 2018-10-09
036909C-1000-MS-1422-0001 | Technical Specification For Geotechnical Investigation | A | 2018-10-04 | IFR | OL1-2K43-0002 | CV | 2018-10-09 | 036909C-JVD-TRN-00147 | 036909C-JVD-TRN-00147 | IFR | 2018-10-24 | 2018-12-24 | R1-No comments | TPSK-LSPA1-T-CV-00147 |  | 2018-10-09
036909C-1000-DW-1422-0001 | Soil Investigation Plan | A | 2018-10-04 | IFR | OL1-2K43-0004 | CV | 2018-10-09 | 036909C-JVD-TRN-00145 | 036909C-JVD-TRN-00145 | IFR | 2018-10-24 | 2018-12-24 | R1-No comments | TPSK-LSPA1-T-CV-00145 |  | 2018-10-09
036909C-1028-PDS-0800-2840 | Process Equipment Datasheet - 10-D-2840 - C3R 4th Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2840 | PE | 2018-10-08 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | 2018-10-08
036909C-1028-PDS-0800-2830 | Process Equipment Datasheet - 10-D-2830 - C3R 3rd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2830 | PE | 2018-10-08 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | 2018-10-08
036909C-1028-PDS-0800-2820 | Process Equipment Datasheet - 10-D-2820 - C3R 2nd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2820 | PE | 2018-10-08 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | 2018-10-08
036909C-1028-PDS-0800-2810 | Process Equipment Datasheet - 10-D-2810 - C3R 1st Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2810 | PE | 2018-10-08 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | 2018-10-08
036909C-1022-PDS-0800-2230 | Process Equipment Datasheet - 10-D-2230 - CG 3rd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2230 | PE | 2018-10-08 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | 2018-10-08
036909C-1022-PDS-0800-2220 | Process Equipment Datasheet - 10-D-2220 - CG 2nd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2220 | PE | 2018-10-08 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | 2018-10-08
036909C-1022-PDS-0800-2220 | Process Equipment Datasheet - 10-D-2220 - CG 2nd Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2220 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-00448
036909C-1022-PDS-0800-2210 | Process Equipment Datasheet - 10-D-2210 - CG 1st Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2210 | PE | 2018-10-08 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | 2018-10-08
036909C-1021-PDS-0600-2101 | Process Equipment Datasheet - 10-E-2100 A-F - Quench Water Cooler | B | 2018-10-04 | IFD | OL1-2G30-2101 | PE | 2018-10-07 | 036909C-JVD-TRN-00143 | 036909C-JVD-TRN-00143 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00143 |  | 2018-10-07
036909C-1055-PDS-0800-5550 | Process Equipment Datasheet - 10-D-5550 - HP Flare Knock-Out Drum | B | 2018-12-05 | IFD | OL1-2G30-5550 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00440
036909C-1055-PDS-0800-5550 | Process Equipment Datasheet - 10-D-5550 - HP Flare Knock-Out Drum | A | 2018-10-04 | IFR | OL1-2G30-5550 | PE | 2018-10-08 | 036909C-JVD-TRN-00142 | 036909C-JVD-TRN-00142 | IFR | 2018-10-22 | 2018-10-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00142 |  | 2018-10-07
036909C-1051-PDS-0900-5109 | Process Equipment Datasheet - 10-P-5110 A-B - Condensate Pumps | B | 2018-10-30 | IFD | OL1-2G30-5109 | PE | 2018-10-31 | 036909C-JVD-TRN-00251 | 036909C-JVD-TRN-00251 | IFI |  | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00251
036909C-1051-PDS-0900-5109 | Process Equipment Datasheet - 10-P-5110 A-B - Condensate Pumps | A | 2018-10-04 | IFR | OL1-2G30-5109 | PE | 2018-10-09 | 036909C-JVD-TRN-00141 | 036909C-JVD-TRN-00141 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-PE-00141 |  | 2018-10-09
036909C-1051-PDS-0900-5102 | Process Equipment Datasheet - 10-P-5102 A-B - VLP BFW Pumps | A | 2018-10-04 | IFR | OL1-2G30-5102 | PE | 2018-10-09 | 036909C-JVD-TRN-00141 | 036909C-JVD-TRN-00141 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-PE-00141 |  | 2018-10-09
036909C-1051-PDS-0900-5101 | Process Equipment Datasheet - 10-P-5100 A-C - SHP BFW Pumps | A | 2018-10-04 | IFR | OL1-2G30-5101 | PE | 2018-10-09 | 036909C-JVD-TRN-00141 | 036909C-JVD-TRN-00141 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-PE-00141 |  | 2018-10-09
036909C-1000-MR-1130-0001 | Material Requisition For Residue Gas Expander/Recompressor | A | 2018-10-05 | IFQ | OL1-2M55-0012 | ME | 2018-10-07 | 036909C-JVD-TRN-00139 | 036909C-JVD-TRN-00139 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-ME-00139 |  | 2018-10-07
036909C-1000-DW-1702-0002 | General Notes For Precast Concrete Works | A | 2018-10-04 | IFR | OL1-2K92-0002 | CV | 2018-10-08 | 036909C-JVD-TRN-00137 | 036909C-JVD-TRN-00137, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2018-10-22 | 2018-12-24 | R1-No comments | TPSK-LSPA1-T-CV-00137 |  | 2018-10-08
036909C-1028-PDS-0600-2884 | Process Equipment Data Sheet - 10-E-2884 - LP Ethylene Product Cooler No 2 | A | 2018-09-06 | IFA | OL1-2G30-2884 | PE | 2018-09-11 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11
036909C-1028-PDS-0600-2882 | Process Equipment Data Sheet - 10-E-2882 - LP Ethylene Product Cooler No 1 | A | 2018-09-06 | IFA | OL1-2G30-2882 | PE | 2018-09-11 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11
036909C-1020-SP-1513-2002 | Instrument Interlock Descriptions Area 20 - Quench Oil | A | 2019-03-15 | IFR | OL1-2I30-2002 | IE | 2019-03-18 | 036909C-JVD-TRN-01088 | 036909C-JVD-TRN-01088 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-IE-01088 |  | 2019-03-18
036909C-1059-SP-1513-5902 | Instrument Interlock Descriptions Area 59 - Supporting Utilities Auxiliaries | A | 2019-03-15 | IFR | OL1-2I30-5902 | IE | 2019-03-18 | 036909C-JVD-TRN-01088 | 036909C-JVD-TRN-01088 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-IE-01088 |  | 2019-03-18
036909C-1059-DW-1514-5901 | Cause and Effect Diagram Area 59 - Supporting Utilities Auxiliaries | A | 2019-03-15 | IFR | OL1-2I30-5901 | IE | 2019-03-18 | 036909C-JVD-TRN-01087 | 036909C-JVD-TRN-01087 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-IE-01087 |  | 2019-03-18
036909C-1020-DW-1514-2001 | Cause and Effect Diagram Area 20 - Quench Oil | A | 2019-03-15 | IFR | OL1-2I30-2001 | IE | 2019-03-18 | 036909C-JVD-TRN-01087 | 036909C-JVD-TRN-01087 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-IE-01087 |  | 2019-03-18
036909C-1019-SP-0940-1913 | Mechanical Equipment Datasheet - DMDS Feed Injection Pump | B | 2019-03-07 | IFQ | OL1-2M03-1913 | ME | 2019-03-18 | 036909C-JVD-TRN-01086 | 036909C-JVD-TRN-01086 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-ME-01086 |  | 2019-03-18
036909C-1019-SP-0940-1913 | Mechanical Equipment Datasheet - DMDS Feed Injection Pump | A | 2019-01-28 | IFQ | OL1-2M03-1913 | ME | 2019-02-01 | 036909C-JVD-TRN-00787 | 036909C-JVD-TRN-00787 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00787
036909C-1019-SP-0940-1914 | Mechanical Equipment Datasheet - DMDS Presulfiding Injection Pump | A | 2019-01-28 | IFQ | OL1-2M03-1914 | ME | 2019-02-01 | 036909C-JVD-TRN-00787 | 036909C-JVD-TRN-00787 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00787
036909C-1019-SP-0940-1914 | Mechanical Equipment Datasheet - DMDS Presulfiding Injection Pump | B | 2019-03-07 | IFQ | OL1-2M03-1914 | ME | 2019-03-18 | 036909C-JVD-TRN-01086 | 036909C-JVD-TRN-01086 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-ME-01086 |  | 2019-03-18
036909C-1025-PDS-0600-2531 | Process Equipment Data Sheet - 10-E-2530 - Demeth Feed Cooler | A | 2018-09-06 | IFA | OL1-2G30-2531 | PE | 2018-09-11 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11
036909C-1012-MR-0126-2012 | Material Requisition for Furnace Convection Finnings | 0 | 2019-03-07 | IFP | OL1-2C13-281000 | PL | 2019-03-18 | 036909C-JVD-TRN-01085 | 036909C-JVD-TRN-01085 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01085 |  | 2019-03-18
036909C-1012-MR-0126-2012 | Material Requisition for Furnace Convection Finnings | A | 2019-01-16 | IFQ | OL1-2C13-281000 | PL | 2019-01-23 | 036909C-JVD-TRN-00713 | 036909C-JVD-TRN-00713 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00713
036909C-1012-SP-0117-1205 | API Fired Heater Datasheet 10-H-1200_1600 | A | 2019-03-01 | IFR | OL1-2M03-1205 | ME | 2019-03-18 | 036909C-JVD-TRN-01084 | 036909C-JVD-TRN-01084 | IFR | 2019-03-30 |  | Transmitted | TPSK-LSPA1-T-ME-01084 |  | 2019-03-18
036909C-1011-SP-0117-1105 | API Fired Heater Datasheet 10-H-1100 | A | 2019-03-07 | IFR | OL1-2M03-1105 | ME | 2019-03-18 | 036909C-JVD-TRN-01084 | 036909C-JVD-TRN-01084 | IFR | 2019-03-30 |  | Transmitted | TPSK-LSPA1-T-ME-01084 |  | 2019-03-18
036909C-1025-PDS-0600-2521 | Process Equipment Datasheet - 10-E-2520 - Rectifier Condenser | B | 2018-10-03 | IFD | OL1-2G30-2521 | PE | 2018-10-05 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05
036909C-1025-PDS-0600-2521 | Process Equipment Data Sheet - 10-E-2520 - Rectifier Condenser | A | 2018-09-06 | IFA | OL1-2G30-2521 | PE | 2018-09-11 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11
036909C-1027-PDS-0900-2714 | Process Equipment Datasheet - 10-P-2714 A-B - C5 Cut Pumps | B | 2019-03-15 | IFD | OL1-2G30-2714 | PE | 2019-03-18 | 036909C-JVD-TRN-01083 | 036909C-JVD-TRN-01083 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-PE-01083 |  | 2019-03-18
036909C-1027-PDS-0900-2714 | Process Equipment Datasheet - 10-P-2714 A-B - C5 Cut Pumps | A | 2019-02-11 | IFR | OL1-2G30-2714 | PE | 2019-02-12 | 036909C-JVD-TRN-00841 | 036909C-JVD-TRN-00841 | IFR | 2019-02-26 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00841
036909C-1027-PDS-0500-2710 | Process Equipment Datasheet - 10-T-2710 Depentanizer | B | 2019-03-15 | IFD | OL1-2G30-2710 | PE | 2019-03-18 | 036909C-JVD-TRN-01082 | 036909C-JVD-TRN-01082 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-PE-01082 |  | 2019-03-18
036909C-1027-PDS-0500-2710 | Process Equipment Datasheet - 10-T-2710 Depentanizer | A | 2019-01-18 | IFR | OL1-2G30-2710 | PE | 2019-01-22 | 036909C-JVD-TRN-00688 | 036909C-JVD-TRN-00688 | IFR | 2019-02-04 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00688
036909C-1027-PDS-0400-2700 | Process Equipment Datasheet - 10-R-2700 A-B - GHU-1 Reactor | A | 2019-01-14 | IFR | OL1-2G30-2700 | PE | 2019-01-16 | 036909C-JVD-TRN-00659 | 036909C-JVD-TRN-00659 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00659
036909C-1027-PDS-0400-2700 | Process Equipment Datasheet - 10-R-2700 A-B - GHU-1 Reactor | B | 2019-03-15 | IFD | OL1-2G30-2700 | PE | 2019-03-18 | 036909C-JVD-TRN-01081 | 036909C-JVD-TRN-01081 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-PE-01081 |  | 2019-03-18
036909C-1025-PDS-0600-2505 | Process Equipment Data Sheet - 10-E-2506 & 2508 - Demeth Prefrac Feed Cooler No 3 & No 4 | A | 2018-09-06 | IFA | OL1-2G30-2505 | PE | 2018-09-11 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11
036909C-1025-PDS-0600-2500 | Process Equipment Data Sheet - 10-E-2500 - Propylene Refrig Subcooler | A | 2018-09-10 | IFA | OL1-2G30-2500 | PE | 2018-09-12 | 036909C-JVD-TRN-00039 | 036909C-JVD-TRN-00039 | IFA | 2018-09-25 | 2018-09-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00039 |  | 2018-09-12
036909C-1025-SP-1011-2550 | Mechanical Equipment Datasheet for Residue Gas Expander-Recompressor | A | 2018-09-13 | IFA | OL1-2M03-2550 | ME | 2018-09-14 | 036909C-JVD-TRN-00050 | 036909C-JVD-TRN-00050 | IFA | 2018-09-27 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00050 |  | 2018-09-14
036909C-1012-PDS-1040-1211 | Process Equipment Datasheet - 10-C-1200_1600 - USC 132U Induced Draft Fan | C | 2019-03-13 | IFD | OL1-2G30-1211 | PE | 2019-03-18 | 036909C-JVD-TRN-01079 | 036909C-JVD-TRN-01079 | IFR | 2019-03-30 |  | Transmitted | TPSK-LSPA1-T-PE-01079 |  | 2019-03-18
036909C-1012-PDS-1040-1211 | Process Equipment Datasheet - 10-C-1200 1600 - USC 132U Induced Draft Fan | B | 2018-10-23 | IFD | OL1-2G30-1211 | PE | 2018-10-24 | 036909C-JVD-TRN-00222 | 036909C-JVD-TRN-00222 | IFI | 2018-11-08 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00222
036909C-1011-PDS-1040-1111 | Process Equipment Datasheet - 10-C-1100 - USC 36M Induced Draft Fan | B | 2018-10-23 | IFD | OL1-2G30-1111 | PE | 2018-10-24 | 036909C-JVD-TRN-00222 | 036909C-JVD-TRN-00222 | IFI | 2018-11-08 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00222
036909C-1011-PDS-1040-1111 | Process Equipment Datasheet - 10-C-1100 - USC 36M Induced Draft Fan | C | 2019-03-13 | IFD | OL1-2G30-1111 | PE | 2019-03-18 | 036909C-JVD-TRN-01079 | 036909C-JVD-TRN-01079 | IFR | 2019-03-30 |  | Transmitted | TPSK-LSPA1-T-PE-01079 |  | 2019-03-18
036909C-1000-NM-0001-1010 | Heat and Material Balance - ISBL Supporting Utilities | A | 2018-10-03 | IFI | OL1-2G44-1010 | PE | 2018-10-04 | 036909C-JVD-TRN-00128 | 036909C-JVD-TRN-00128 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00128 |  | 2018-10-04
036909C-1028-SP-1011-2850 | Mechanical Equipment Data Sheet for Ethylene Refrigeration Compressor | A | 2018-09-06 | IFA | OL1-2M03-2850 | ME | 2018-09-11 | 036909C-JVD-TRN-00038 | 036909C-JVD-TRN-00038 | IFA | 2018-09-24 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00038 |  | 2018-09-11
036909C-1011-PDS-0610-1109 | Process Equipment Datasheet - 10-E-1110 - USC 36M TLX-1 Quench Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1109 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237
036909C-1011-PDS-0610-1109 | Process Equipment Datasheet - 10-E-1110 - USC 36M TLX-1 Quench Exchanger | C | 2019-03-14 | IFD | OL1-2G30-1109 | PE | 2019-03-18 | 036909C-JVD-TRN-01078 | 036909C-JVD-TRN-01078 | IFR | 2019-03-30 |  | Transmitted | TPSK-LSPA1-T-PE-01078 |  | 2019-03-18
036909C-1011-PDS-0610-1109 | Process Equipment Datasheet - 10-E-1110 - USC 36M TLX-1 Quench Exchanger | B | 2018-12-06 | IFD | OL1-2G30-1109 | PE | 2018-12-10 | 036909C-JVD-TRN-00459 | 036909C-JVD-TRN-00459 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00459
036909C-1028-SP-1011-2800 | Mechanical Equipment Data Sheet for Propylene Refrigeration Compressor | A | 2018-09-06 | IFA | OL1-2M03-2800 | ME | 2018-09-11 | 036909C-JVD-TRN-00038 | 036909C-JVD-TRN-00038 | IFA | 2018-09-24 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00038 |  | 2018-09-11
036909C-1011-PDS-0610-1110 | Process Equipment Datasheet - 10-E-1120 - USC 36M TLX-2 Quench Exchanger | B | 2018-12-06 | IFD | OL1-2G30-1110 | PE | 2018-12-10 | 036909C-JVD-TRN-00459 | 036909C-JVD-TRN-00459 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00459
036909C-1011-PDS-0610-1110 | Process Equipment Datasheet - 10-E-1120 - USC 36M TLX-2 Quench Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1110 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237
036909C-1011-PDS-0610-1110 | Process Equipment Datasheet - 10-E-1120 - USC 36M TLX-2 Quench Exchanger | C | 2019-03-14 | IFD | OL1-2G30-1110 | PE | 2019-03-18 | 036909C-JVD-TRN-01078 | 036909C-JVD-TRN-01078 | IFR | 2019-03-30 |  | Transmitted | TPSK-LSPA1-T-PE-01078 |  | 2019-03-18
036909C-1022-SP-1011-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor | A | 2018-09-06 | IFA | OL1-2M03-2200 | ME | 2018-09-11 | 036909C-JVD-TRN-00038 | 036909C-JVD-TRN-00038 | IFA | 2018-09-24 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00038 |  | 2018-09-11
036909C-1000-JSD-1600-003 | General Design Rule For Package Equipment Electrical System - Client code for next revision will be OL1-2E04-6000 | A | 2018-08-03 | IFR | OL1-2R05-0042 | EE | 2018-08-07 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 |  | 2018-08-07
036909C-1012-PDS-0610-1209 | Process Equipment Datasheet - 10-E-1210_10-E-1610 - USC 132U TLX Quench Exchanger | C | 2019-03-14 | IFD | OL1-2G30-1209 | PE | 2019-03-18 | 036909C-JVD-TRN-01078 | 036909C-JVD-TRN-01078 | IFR | 2019-03-30 |  | Transmitted | TPSK-LSPA1-T-PE-01078 |  | 2019-03-18
036909C-1012-PDS-0610-1209 | Process Equipment Datasheet - 10-E-1210 - 10-E-1610 - USC 132U TLX Quench Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1209 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237
036909C-1012-PDS-0610-1209 | Process Equipment Datasheet - 10-E-1210 - 10-E-1610 - USC 132U TLX Quench Exchanger | B | 2018-12-06 | IFD | OL1-2G30-1209 | PE | 2018-12-10 | 036909C-JVD-TRN-00449 | 036909C-JVD-TRN-00449 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00449
036909C-1000-JSD-0000-0004 | Cold Box Design Specification | A | 2018-10-01 | IFR | OL1-2G01-0002 | PE | 2018-10-04 | 036909C-JVD-TRN-00123 | 036909C-JVD-TRN-00123, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-10-17 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00123 |  | 2018-10-04
036909C-1000-SP-0661-0001 | Particular Technical Specification For Plate And Frame Heat Exchangers | A | 2018-10-01 | IFQ | OL1-2M57-0064 | ME | 2018-10-04 | 036909C-JVD-TRN-00124 | 036909C-JVD-TRN-00124 | IFR | 2018-10-17 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00124 |  | 2018-10-04
036909C-1021-PDS-0840-2104 | Process Equipment Datasheet - 10-F-2105 A-B Quench Oil Reflux Filter | A | 2018-11-21 | IFR | OL1-2G30-2104 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00350
036909C-1021-PDS-0840-2104 | Process Equipment Datasheet - 10-F-2105 A-B - Quench Oil Reflux Filter | B | 2019-01-07 | IFD | OL1-2G30-2104 | PE | 2019-01-07 | 036909C-JVD-TRN-00606 | 036909C-JVD-TRN-00606 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00606
036909C-1021-PDS-0840-2104 | Process Equipment Datasheet - 10-F-2105 A-B - Quench Oil Reflux Filter | C | 2019-03-14 | IFD | OL1-2G30-2104 | PE | 2019-03-18 | 036909C-JVD-TRN-01072 | 036909C-JVD-TRN-01072 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-PE-01072 |  | 2019-03-18
036909C-1021-PDS-0840-2138 | Process Equipment Datasheet - 10-F-2136 A-B - Process Water Feed Filters | C | 2019-03-14 | IFD | OL1-2G30-2138 | PE | 2019-03-18 | 036909C-JVD-TRN-01072 | 036909C-JVD-TRN-01072 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-PE-01072 |  | 2019-03-18
036909C-1021-PDS-0840-2138 | Process Equipment Datasheet - 10-F-2136 A-B - Process Water Feed Filters | B | 2019-01-07 | IFD | OL1-2G30-2138 | PE | 2019-01-07 | 036909C-JVD-TRN-00606 | 036909C-JVD-TRN-00606 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00606
036909C-1021-PDS-0840-2138 | Process Equipment Datasheet - 10-F-2136 A-B Process Water Feed Filters | A | 2018-11-21 | IFR | OL1-2G30-2138 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00350
036909C-1000-DW-1442-0001 | Major Underground Networks | A | 2019-03-13 | IFR | OL1-2K36-1000 | CV | 2019-03-18 | 036909C-JVD-TRN-01073 | 036909C-JVD-TRN-01073 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-CV-01073 |  | 2019-03-18
036909C-1000-DW-1425-0001 | Roads Paving And Finishing Layout | A | 2019-03-13 | IFR | OL1-2K27-0001 | CV | 2019-03-18 | 036909C-JVD-TRN-01074 | 036909C-JVD-TRN-01074 | IFA | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-CV-01074 |  | 2019-03-18
036909C-1000-MR-2630-0003 | Material Requisition For Molecular And HG Sieves | A | 2019-03-15 | IMP | OL1-2C18-263000 | PL | 2019-03-18 | 036909C-JVD-TRN-01076 | 036909C-JVD-TRN-01076 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-PL-01076 |  | 2019-03-18
036909C-1000-MR-2630-0005 | Material Requisition For Molecular Sieves | A | 2019-03-12 | IMP | OL1-2C18-265000 | PL | 2019-03-18 | 036909C-JVD-TRN-01077 | 036909C-JVD-TRN-01077 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-PL-01077 |  | 2019-03-18
036909C-1027-PDS-0600-2730 | Process Equipment Datasheet - 10-E-2730 - Regen Gas Electric Heater | A | 2019-03-13 | IFR | OL1-2G30-2730 | PE | 2019-03-18 | 036909C-JVD-TRN-01070 | 036909C-JVD-TRN-01070 | IFR | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-PE-01070 |  | 2019-03-18
036909C-1059-PDS-2600-5914 | Process Equipment Datasheet - 10-PK-5914 - Phosphate Injection Pkg | C | 2019-03-14 | IFD | OL1-2G30-5914 | PE | 2019-03-15 | 036909C-JVD-TRN-01063 | 036909C-JVD-TRN-01063 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01063 |  | 2019-03-15
036909C-1051-PDS-0900-5141 | Process Equipment Datasheet - 10-P-5140 A-B - Intermittent Blowdown Pumps | B | 2019-03-13 | IFD | OL1-2G30-5141 | PE | 2019-03-15 | 036909C-JVD-TRN-01051 | 036909C-JVD-TRN-01051 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01051 |  | 2019-03-15
036909C-1056-PDS-0900-5611 | Process Equipment Datasheet - 10-P-5610 - Hydroblast Sump Pump | B | 2019-03-13 | IFD | OL1-2G30-5611 | PE | 2019-03-15 | 036909C-JVD-TRN-01051 | 036909C-JVD-TRN-01051 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01051 |  | 2019-03-15
036909C-1056-PDS-0900-5606 | Process Equipment Datasheet - 10-P-5600 A-B - Pygas Area Oily Wastewater Pump | C | 2019-03-13 | IFD | OL1-2G30-5606 | PE | 2019-03-15 | 036909C-JVD-TRN-01051 | 036909C-JVD-TRN-01051 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01051 |  | 2019-03-15
036909C-1055-PDS-0600-5553 | Process Equipment Datasheet - 10-E-5552 - LPG Vaporizer - Superheater | B | 2019-03-13 | IFD | OL1-2G30-5553 | PE | 2019-03-15 | 036909C-JVD-TRN-01054 | 036909C-JVD-TRN-01054 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01054 |  | 2019-03-15
036909C-1030-SP-1031-3073 | Mechanical Equipment Datasheet - BDU Recycle Gas Compressor | B | 2019-03-13 | IFQ | OL1-2M03-3073 | ME | 2019-03-15 | 036909C-JVD-TRN-01066 | 036909C-JVD-TRN-01066 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-ME-01066 |  | 2019-03-15
036909C-1051-PDS-0900-5109 | Process Equipment Datasheet - 10-P-5110 A-B-C - Condensate Pumps | C | 2019-03-13 | IFD | OL1-2G30-5109 | PE | 2019-03-15 | 036909C-JVD-TRN-01051 | 036909C-JVD-TRN-01051 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01051 |  | 2019-03-15
036909C-1052-PDS-0600-5210 | Process Equipment Datasheet - 10-E-5210 - Pilot Gas Vaporizer | B | 2019-03-13 | IFD | OL1-2G30-5210 | PE | 2019-03-15 | 036909C-JVD-TRN-01054 | 036909C-JVD-TRN-01054 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01054 |  | 2019-03-15
036909C-1059-PDS-2500-5950 | Process Equipment Datasheet - 10-TK-5950 - Sodium Hypochlorite Tank | B | 2019-03-13 | IFD | OL1-2G30-5950 | PE | 2019-03-15 | 036909C-JVD-TRN-01055 | 036909C-JVD-TRN-01055 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01055 |  | 2019-03-15
036909C-1055-PDS-0800-5515 | Process Equipment Datasheet - 10-D-5515 - Methanol Makeup Drum | B | 2019-03-13 | IFD | OL1-2G30-5515 | PE | 2019-03-15 | 036909C-JVD-TRN-01052 | 036909C-JVD-TRN-01052 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01052 |  | 2019-03-15
036909C-1056-PDS-0200-5615 | Process Equipment Datasheet - 10-PIT-5615 - Olefins Stormwater Sump | C | 2019-03-14 | IFD | OL1-2G30-5615 | PE | 2019-03-15 | 036909C-JVD-TRN-01068 | 036909C-JVD-TRN-01068 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01068 |  | 2019-03-15
036909C-1051-PDS-2500-5120 | Process Equipment Datasheet - 10-TK-5120 - Raw Condensate Tank | B | 2019-03-13 | IFD | OL1-2G30-5120 | PE | 2019-03-15 | 036909C-JVD-TRN-01055 | 036909C-JVD-TRN-01055 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01055 |  | 2019-03-15
036909C-1056-PDS-0200-5620 | Process Equipment Datasheet - 10-PIT-5620 A-C - Olefins Holding Basin | C | 2019-03-14 | IFD | OL1-2G30-5620 | PE | 2019-03-15 | 036909C-JVD-TRN-01068 | 036909C-JVD-TRN-01068 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01068 |  | 2019-03-15
036909C-1059-PDS-2600-5910 | Process Equipment Datasheet - 10-PK-5910 - Oxygen Scavenger Inj Pkg | C | 2019-03-14 | IFD | OL1-2G30-5910 | PE | 2019-03-15 | 036909C-JVD-TRN-01063 | 036909C-JVD-TRN-01063 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01063 |  | 2019-03-15
036909C-1059-PDS-2600-5912 | Process Equipment Datasheet - 10-PK-5912 - Neutralization Amine Inhibitor Inj Pkg | C | 2019-03-14 | IFD | OL1-2G30-5912 | PE | 2019-03-15 | 036909C-JVD-TRN-01063 | 036909C-JVD-TRN-01063 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PE-01063 |  | 2019-03-15
036909C-1012-HOM-0154-2003 | Hand-Over Meeting Report - Quench Exchanger and Steam D | 0 | 2019-02-20 | IFI | OL1-2C95-140000 | PL | 2019-03-12 | 036909C-JVD-TRN-01026 | 036909C-JVD-TRN-01026 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01026 |  | 2019-03-12
036909C-1012-DW-0132-2103 | USC 132U Cracking Furnace Refractory and Insulation Installation Details | A | 2019-02-22 | IFR | OL1-2M06-2103 | ME | 2019-03-15 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15
036909C-1012-DW-0132-2101 | USC 132U Cracking Furnace Refractory and Insulation Radiant Section Details | A | 2019-02-22 | IFR | OL1-2M06-2101 | ME | 2019-03-15 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15
036909C-1012-DW-0132-2102 | USC 132U Cracking Furnace Refractory and Insulation Convection Section Details | A | 2019-02-22 | IFR | OL1-2M06-2102 | ME | 2019-03-15 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15
036909C-1012-DW-0132-2106 | USC 132U Cracking Furnace Peep Door Insert Details | A | 2019-02-20 | IFR | OL1-2M06-2106 | ME | 2019-03-15 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15
036909C-1012-DW-0132-2108 | USC 132U Cracking Furnace Decoke Nozzle Details | A | 2019-02-22 | IFR | OL1-2M06-2108 | ME | 2019-03-15 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15
036909C-1012-DW-0132-2104 | USC 132U Cracking Furnace Refractory and Insulation Anchor Details | A | 2019-02-22 | IFR | OL1-2M06-2104 | ME | 2019-03-15 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15
036909C-1012-DW-0132-2105 | USC 132U Cracking Furnace Insulation Details at Radiant Floor Burners | A | 2019-02-22 | IFR | OL1-2M06-2105 | ME | 2019-03-15 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15
036909C-1011-DW-0132-1101 | USC 36M Recycle Furnace Refractory and Insulation Radiant Section Details | A | 2019-02-22 | IFR | OL1-2M06-1101 | ME | 2019-03-15 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15
036909C-1011-DW-0132-1102 | USC 36M Recycle Furnace Refractory and Insulation Convection Section Details | A | 2019-02-22 | IFR | OL1-2M06-1102 | ME | 2019-03-15 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15
036909C-1011-DW-0132-1108 | USC 36M Recycle Furnace Decoke Nozzle Details | A | 2019-02-22 | IFR | OL1-2M06-1108 | ME | 2019-03-15 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15
036909C-1011-DW-0132-1103 | USC 36M Recycle Furnace Refractory and Insulation Installation Details | A | 2019-02-22 | IFR | OL1-2M06-1103 | ME | 2019-03-15 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15
036909C-1011-DW-0132-1104 | USC 36M Recycle Furnace Refractory and Insulation Anchor Details | A | 2019-02-22 | IFR | OL1-2M06-1104 | ME | 2019-03-15 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15
036909C-1011-DW-0132-1106 | USC 36M Recycle Furnace Peep Door Insert Details | A | 2019-02-22 | IFR | OL1-2M06-1106 | ME | 2019-03-15 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15
036909C-1001-DW-2054-0001-02 | Gatehouse A - Architectural Elevations And Sections | A | 2019-03-04 | IFR | OL1-2K30-0031 | CV | 2019-03-15 | 036909C-JVD-TRN-01064 | 036909C-JVD-TRN-01064 | IFA | 2019-03-29 |  | Transmitted | TPSL-LSPA1-T-CV-01064 |  | 2019-03-15
036909C-1011-DW-0132-1105 | USC 36M Recycle Furnace Insulation Details at Radiant Floor Burners | A | 2019-02-22 | IFR | OL1-2M06-1105 | ME | 2019-03-15 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15
036909C-1000-DW-1576-0005 | Instr Supports Typical Mount Details | A | 2019-03-12 | IFR | OL1-2I31-0001 | IE | 2019-03-15 | 036909C-JVD-TRN-01058 | 036909C-JVD-TRN-01058 | IFA | 2019-03-29 |  | Transmitted | TPSL-LSPA1-T-IE-01058 |  | 2019-03-15
036909C-1056-SP-0910-5649 | Mechanical Equipment Datasheet - Flare KO Drum Oily Wastewater Pump | B | 2019-02-13 | IFQ | OL1-2M03-5649 | ME | 2019-03-04 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04
036909C-1056-SP-0910-5648 | Mechanical Equipment Datasheet - C3 Hydrog Area Oily Wastewater Pump | B | 2019-02-13 | IFQ | OL1-2M03-5648 | ME | 2019-03-04 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04
036909C-1056-SP-0910-5616 | Mechanical Equipment Datasheet - Olefins Stormwater Sump Pumps | B | 2019-02-11 | IFQ | OL1-2M03-5616 | ME | 2019-03-04 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04
036909C-1056-SP-0910-5614 | Mechanical Equipment Datasheet - Furnace Area Oily Wastewater Pump | B | 2019-02-13 | IFQ | OL1-2M03-5614 | ME | 2019-03-04 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04
036909C-1056-SP-0910-5613 | Mechanical Equipment Datasheet - Refrig Area Oily Wastewater Pump | B | 2019-02-13 | IFQ | OL1-2M03-5613 | ME | 2019-03-04 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04
036909C-1056-SP-0910-5609 | Mechanical Equipment Datasheet - CGC Area Oily Wastewater Pump | B | 2019-02-13 | IFQ | OL1-2M03-5609 | ME | 2019-03-04 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04
036909C-1056-SP-0910-5608 | Mechanical Equipment Datasheet - QW Area Oily Wastewater Pump | B | 2019-02-13 | IFQ | OL1-2M03-5608 | ME | 2019-03-04 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04
036909C-1056-SP-0910-5607 | Mechanical Equipment Datasheet - Butadiene Area Oily Wastewater Pump | B | 2019-02-13 | IFQ | OL1-2M03-5607 | ME | 2019-03-04 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04
036909C-1026-SP-0910-2669 | Mechanical Equipment Datasheet - Debutanizer Bottoms Pumps | B | 2019-01-31 | IFQ | OL1-2M03-2669 | ME | 2019-02-07 | 036909C-JVD-TRN-00823 | 036909C-JVD-TRN-00823 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00823
036909C-1056-SP-0910-5638 | Mechanical Equipment Datasheet - HP Flare Area SW Sump Pumps | A | 2019-02-06 | IFQ | OL1-2M03-5638 | ME | 2019-02-07 | 036909C-JVD-TRN-00817 | 036909C-JVD-TRN-00817 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00817
036909C-1056-SP-0910-5637 | Mechanical Equipment Datasheet - HP Flare Area Oily Wastewater Sump Pumps | A | 2019-02-06 | IFQ | OL1-2M03-5637 | ME | 2019-02-07 | 036909C-JVD-TRN-00817 | 036909C-JVD-TRN-00817 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00817
036909C-1056-SP-0910-5636 | Mechanical Equipment Datasheet - CWWT Area Oily Wastewater Sump Pumps | A | 2019-02-06 | IFQ | OL1-2M03-5636 | ME | 2019-02-07 | 036909C-JVD-TRN-00817 | 036909C-JVD-TRN-00817 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00817
036909C-1056-SP-0910-5635 | Mechanical Equipment Datasheet - CT Area Oily Wastewater Sump Pumps | A | 2019-02-06 | IFQ | OL1-2M03-5635 | ME | 2019-02-07 | 036909C-JVD-TRN-00817 | 036909C-JVD-TRN-00817 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00817
036909C-1056-SP-0910-5606 | Mechanical Equipment Datasheet - Pygas Area Oily Wastewater Pumps | A | 2019-02-06 | IFQ | OL1-2M03-5606 | ME | 2019-02-07 | 036909C-JVD-TRN-00817 | 036909C-JVD-TRN-00817 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00817
036909C-1027-SP-0910-2764 | Mechanical Equipment Datasheet - C4-C5 Hydrog Recycle Pump | A | 2019-02-06 | IFQ | OL1-2M03-2764 | ME | 2019-02-07 | 036909C-JVD-TRN-00817 | 036909C-JVD-TRN-00817 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00817
036909C-1027-SP-0910-2751 | Mechanical Equipment Datasheet - C4-C5 Hydrog Feed Pump | A | 2019-02-06 | IFQ | OL1-2M03-2751 | ME | 2019-02-07 | 036909C-JVD-TRN-00817 | 036909C-JVD-TRN-00817 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00817
036909C-1051-PDS-0800-5140 | Process Equipment Datasheet - 10-D-5140 - Intermittent Blowdown Drum | C | 2019-03-04 | IFD | OL1-2G30-5140 | PE | 2019-03-06 | 036909C-JVD-TRN-00988 | 036909C-JVD-TRN-00988 | IFR | 2019-03-20 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-PE-00988 |  | 2019-03-06
036909C-1000-JSS-6300-0008 | Job Specification For Axens Standard Material Specifications For Wet H2S Service | A | 2019-02-21 | IFR | OL1-2R03-0009 | ME | 2019-02-22 | 036909C-JVD-TRN-00909 | 036909C-JVD-TRN-00909 | IFR | 2019-03-08 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00909 |  | 2019-02-22
036909C-1000-JSS-6300-0007 | Job Specification For Axens Standard Material Specifications - Low Alloyed Steels For Pressure Vessels | A | 2019-02-21 | IFR | OL1-2R03-0008 | ME | 2019-02-22 | 036909C-JVD-TRN-00909 | 036909C-JVD-TRN-00909 | IFR | 2019-03-08 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00909 |  | 2019-02-22
036909C-1000-JSS-6300-0006 | Job Specification for AXENS Standard Material Specifications - Carbon Steels For Pressure Service | A | 2019-02-21 | IFR | OL1-2R03-0007 | ME | 2019-02-22 | 036909C-JVD-TRN-00909 | 036909C-JVD-TRN-00909 | IFR | 2019-03-08 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00909 |  | 2019-02-22
036909C-1056-PDS-2500-5676 | Process Equipment Datasheet - 10-TK-5676 - Oily Sludge Tank | A | 2019-02-05 | IFR | OL1-2G30-5676 | PE | 2019-02-06 | 036909C-JVD-TRN-00809 | 036909C-JVD-TRN-00809 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00809
036909C-1056-PDS-2500-5675 | Process Equipment Datasheet - 10-TK-5675 A-B - Slop Oil Tanks | A | 2019-02-05 | IFR | OL1-2G30-5675 | PE | 2019-02-06 | 036909C-JVD-TRN-00809 | 036909C-JVD-TRN-00809 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00809
036909C-1056-PDS-2500-5640 | Process Equipment Datasheet - 10-TK-5640 - Oily Wastewater Tank | A | 2019-02-05 | IFR | OL1-2G30-5640 | PE | 2019-02-06 | 036909C-JVD-TRN-00809 | 036909C-JVD-TRN-00809 | IFR | 2019-02-19 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-PE-00809
036909C-1012-PDS-1542-1213 | Process Equipment Datasheet - 10-X-1200_1600 A-F - USC 132U Dilution Steam Mixing Tee | B | 2019-02-25 | IFD | OL1-2G30-1213 | PE | 2019-02-27 | 036909C-JVD-TRN-00936 | 036909C-JVD-TRN-00936 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-PE-00936 |  | 2019-02-27
036909C-1012-PDS-0811-1207 | Process Equipment Datasheet - 10-D-1200_1600 - USC 132U Cracking Furnace Steam Drum | C | 2019-02-26 | IFD | OL1-2G30-1207 | PE | 2019-02-27 | 036909C-JVD-TRN-00935 | 036909C-JVD-TRN-00935 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-PE-00935 |  | 2019-02-27
036909C-1011-PDS-0811-1107 | Process Equipment Datasheet - 10-D-1100 - USC 36M Cracking Furnace Steam Drum | C | 2019-02-26 | IFD | OL1-2G30-1107 | PE | 2019-02-27 | 036909C-JVD-TRN-00935 | 036909C-JVD-TRN-00935 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-PE-00935 |  | 2019-02-27
036909C-1023-PDS-2500-2324 | Process Equipment Datasheet - 10-TK-2300 - Fresh Caustic Day Tank | C | 2019-02-26 | IFD | OL1-2G30-2324 | PE | 2019-02-27 | 036909C-JVD-TRN-00937 | 036909C-JVD-TRN-00937 | IFR | 2019-03-13 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-PE-00937 |  | 2019-02-27
036909C-1056-PDS-0900-5645 | Process Equipment Datasheet - 10-P-5640 A-B - Oily Wastewater EQ Tank Pumps | A | 2019-02-05 | IFR | OL1-2G30-5645 | PE | 2019-02-06 | 036909C-JVD-TRN-00810 | 036909C-JVD-TRN-00810 | IFR | 2019-02-19 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-PE-00810
036909C-1056-PDS-0900-5677 | Process Equipment Datasheet - 10-P-5676 - Oily Sludge Transfer Pump | A | 2019-02-05 | IFR | OL1-2G30-5677 | PE | 2019-02-06 | 036909C-JVD-TRN-00810 | 036909C-JVD-TRN-00810 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00810
036909C-1056-PDS-0900-5674 | Process Equipment Datasheet - 10-P-5675 - Slop Oil Transfer Pump | A | 2019-02-05 | IFR | OL1-2G30-5674 | PE | 2019-02-06 | 036909C-JVD-TRN-00810 | 036909C-JVD-TRN-00810 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00810
036909C-1056-PDS-0900-5657 | Process Equipment Datasheet - 10-P-5656 A-B - Final Check Basin Pumps | A | 2019-02-05 | IFR | OL1-2G30-5657 | PE | 2019-02-06 | 036909C-JVD-TRN-00810 | 036909C-JVD-TRN-00810 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00810
036909C-1056-PDS-0900-5654 | Process Equipment Datasheet - 10-P-5655 A-B - Equalization Pit Pumps | A | 2019-02-05 | IFR | OL1-2G30-5654 | PE | 2019-02-06 | 036909C-JVD-TRN-00810 | 036909C-JVD-TRN-00810 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00810
036909C-1056-PDS-0900-5643 | Process Equipment Datasheet - 10-P-5642 A-B - Cooling Water BD Basin Pumps | A | 2019-02-05 | IFR | OL1-2G30-5643 | PE | 2019-02-06 | 036909C-JVD-TRN-00810 | 036909C-JVD-TRN-00810 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00810
036909C-1056-PDS-0900-5641 | Process Equipment Datasheet - 10-P-5641 - Wastewater EQ Tank Skimmed Oil Pumps | A | 2019-02-05 | IFR | OL1-2G30-5641 | PE | 2019-02-06 | 036909C-JVD-TRN-00810 | 036909C-JVD-TRN-00810 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00810
036909C-1000-JSD-0400-01 | Job Specification For Design Of Pressure And Atmospheric Static Equipment | 1 | 2019-02-18 | IMP | OL1-2R03-0050 | ME | 2019-02-19 | 036909C-JVD-TRN-00888 | 036909C-JVD-TRN-00888, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-03-06 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00888 |  | 2019-02-19
036909C-1056-PDS-0200-5656 | Process Equipment Datasheet - 10-PIT-5656 - Final Check Basin | A | 2019-02-05 | IFR | OL1-2G30-5656 | PE | 2019-02-06 | 036909C-JVD-TRN-00808 | 036909C-JVD-TRN-00808 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00808
036909C-1056-PDS-0200-5655 | Process Equipment Datasheet - 10-PIT-5655 - Bio Equalization Pit | A | 2019-02-05 | IFR | OL1-2G30-5655 | PE | 2019-02-06 | 036909C-JVD-TRN-00808 | 036909C-JVD-TRN-00808 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00808
036909C-1056-PDS-0200-5642 | Process Equipment Datasheet - 10-PIT-5642 - Cooling Water Blowdown Basin | A | 2019-02-05 | IFR | OL1-2G30-5642 | PE | 2019-02-06 | 036909C-JVD-TRN-00808 | 036909C-JVD-TRN-00808 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00808
036909C-1030-PDS-0500-3070 | Process Equipment Datasheet - 10-T-3070 - Direct Cooler Tower | A | 2019-02-28 | IFR | OL1-2G30-3070 | PE | 2019-03-01 | 036909C-JVD-TRN-00955 | 036909C-JVD-TRN-00955 | IFR | 2019-03-15 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00955 |  | 2019-03-01
036909C-1030-PDS-0500-3050 | Process Equipment Datasheet - 10-T-3050 - Degasser | A | 2019-02-28 | IFR | OL1-2G30-3050 | PE | 2019-03-01 | 036909C-JVD-TRN-00955 | 036909C-JVD-TRN-00955 | IFR | 2019-03-15 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00955 |  | 2019-03-01
036909C-1030-PDS-0500-3030 | Process Equipment Datasheet - 10-T-3030 - After Washer | A | 2019-02-28 | IFR | OL1-2G30-3030 | PE | 2019-03-01 | 036909C-JVD-TRN-00955 | 036909C-JVD-TRN-00955 | IFR | 2019-03-15 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00955 |  | 2019-03-01
036909C-1000-MR-0630-0001 | Material Requisition For Hairpin Heat Exchangers Requisition For Inquiry | A | 2019-03-12 | IFQ | OL1-2C13-145000 | PL | 2019-03-14 | 036909C-JVD-TRN-01046 | 036909C-JVD-TRN-01046 | IFR | 2019-03-28 |  | Transmitted | TPSK-LSPA1-T-PL-01046 |  | 2019-03-14
036909C-1027-TDS-0630-2727 | Mechanical Equipment Data Sheet - 10-E-2726 - Pygas Fuel Oil Cooler | A | 2019-02-19 | IFQ | OL1-2M03-2727 | ME | 2019-02-20 | 036909C-JVD-TRN-00897 | 036909C-JVD-TRN-00897 | IFR | 2019-03-07 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00897 |  | 2019-02-20
036909C-1027-PDS-0600-2723 | Process Equipment Datasheet - 10-E-2724 - Wash Oil Condenser | A | 2019-02-05 | IFR | OL1-2G30-2723 | PE | 2019-02-11 | 036909C-JVD-TRN-00835 | 036909C-JVD-TRN-00835 | IFR | 2019-02-25 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00835
036909C-1027-TDS-0630-2716 | Mechanical Equipment Data Sheet - 10-E-2714 - C5 Cut Cooler | A | 2019-02-12 | IFQ | OL1-2M03-2716 | ME | 2019-02-15 | 036909C-JVD-TRN-00872 | 036909C-JVD-TRN-00872 | IFR | 2019-03-04 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00872 |  | 2019-02-15
036909C-1027-PDS-0600-2727 | Process Equipment Datasheet - 10-E-2726 - Pygas Fuel Oil Cooler | A | 2019-02-08 | IFR | OL1-2G30-2727 | PE | 2019-02-11 | 036909C-JVD-TRN-00835 | 036909C-JVD-TRN-00835 | IFR | 2019-02-25 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00835
036909C-1024-PDS-0600-2432 | Process Equipment Datasheet - 10-E-2432 - Regen Gas Shp Heater | B | 2019-01-18 | IFD | OL1-2G30-2432 | PE | 2019-01-22 | 036909C-JVD-TRN-00696 | 036909C-JVD-TRN-00696 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00696
036909C-1027-PDS-0600-2716 | Process Equipment Datasheet - 10-E-2714 - C5 Cut Cooler | A | 2019-01-22 | IFR | OL1-2G30-2716 | PE | 2019-01-25 | 036909C-JVD-TRN-00720 | 036909C-JVD-TRN-00720 | IFR | 2019-02-07 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00720
036909C-1023-PDS-0600-2326 | Process Equipment Datasheet - 10-E-2326 - Spent Caustic Stripper Feed Heater | B | 2019-01-17 | IFD | OL1-2G30-2326 | PE | 2019-01-22 | 036909C-JVD-TRN-00690 | 036909C-JVD-TRN-00690 | IFI |  | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00690
036909C-1023-TDS-0630-2326 | Mechanical Equipment Data Sheet - 10-E-2326 - Spent Caustic Stripper Feed Heater | A | 2019-01-22 | IFQ | OL1-2M03-2326 | ME | 2019-01-28 | 036909C-JVD-TRN-00740 | 036909C-JVD-TRN-00740 | IFR | 2019-02-11 | 2019-02-28 | R2-Comments as noted | TPSK-LSPA1-T-ME-00740
036909C-1024-TDS-0630-2432 | Mechanical Equipment Data Sheet - 10-E-2432 - Regen Gas SHP Heater | A | 2019-01-24 | IFQ | OL1-2M03-2432 | ME | 2019-01-29 | 036909C-JVD-TRN-00751 | 036909C-JVD-TRN-00751 | IFR | 2019-02-12 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00751
036909C-1000-JSS-0400-02 | Marking For Vessel & Heat Exchanger | 0 | 2018-09-10 | IMP | OL1-2R03-0102 | ME | 2018-09-13 | 036909C-JVD-TRN-00042 | 036909C-JVD-TRN-00042 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00042 |  | 2018-09-13
036909C-1000-JSS-0400-01 | Job Specification For Supply Of Pressure Vessels | 0 | 2018-10-26 | IMP | OL1-2R03-0051 | ME | 2018-10-31 | 036909C-JVD-TRN-00249 | 036909C-JVD-TRN-00249, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2018-11-14 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00249
036909C-1000-STC-0490-000 | Construction Standards For Pressure Equipment | 1 | 2019-02-15 | IMP | OL1-2R03-0054 | ME | 2019-02-19 | 036909C-JVD-TRN-00876 | 036909C-JVD-TRN-00876, ROC-TPSK-CECO-T-00004 | IFR | 2019-03-05 | 2019-03-11 | R1-No comments | TPSK-LSPA1-T-ME-00876 |  | 2019-02-19
036909C-1056-PDS-0200-5615 | Process Equipment Datasheet - 10-PIT-5615 - Olefins Stormwater Sump | A | 2019-01-10 | IFR | OL1-2G30-5615 | PE | 2019-01-11 | 036909C-JVD-TRN-00636 | 036909C-JVD-TRN-00636 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00636
036909C-1056-PDS-0200-5615 | Process Equipment Datasheet - 10-PIT-5615 - Olefins Stormwater Sump | B | 2019-02-28 | IFD | OL1-2G30-5615 | PE | 2019-03-04 | 036909C-JVD-TRN-00960 | 036909C-JVD-TRN-00960 | IFR | 2019-03-16 | 2019-03-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00960 |  | 2019-03-04
036909C-1056-PDS-0200-5620 | Process Equipment Datasheet - 10-PIT-5620 A-C - Olefins Holding Basin | A | 2019-01-02 | IFR | OL1-2G30-5620 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589
036909C-1056-PDS-0200-5620 | Process Equipment Datasheet - 10-PIT-5620 A-C - Olefins Holding Basin | B | 2019-02-28 | IFD | OL1-2G30-5620 | PE | 2019-03-04 | 036909C-JVD-TRN-00960 | 036909C-JVD-TRN-00960 | IFR | 2019-03-16 | 2019-03-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00960 |  | 2019-03-04
036909C-1030-SP-1031-3073 | Mechanical Equipment Datasheet - BDU Recycle Gas Compressor | A | 2019-01-17 | IFQ | OL1-2M03-3073 | ME | 2019-01-22 | 036909C-JVD-TRN-00692 | 036909C-JVD-TRN-00692 | IFR | 2019-02-04 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00692
036909C-1059-PDS-2600-5912 | Process Equipment Datasheet - 10-PK-5912 - Neutralization Amine Inhibitor Inj Pkg | B | 2019-01-24 | IFD | OL1-2G30-5912 | PE | 2019-01-25 | 036909C-JVD-TRN-00727 | 036909C-JVD-TRN-00727 | IFI |  | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00727
036909C-1059-PDS-2600-5912 | Process Equipment Datasheet - 10-PK-5912 - Neutralization Amine Inhibitor Inj Pkg | A | 2018-12-07 | IFR | OL1-2G30-5912 | PE | 2018-12-10 | 036909C-JVD-TRN-00456 | 036909C-JVD-TRN-00456 | IFR | 2018-12-21 | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00456
036909C-1059-PDS-2600-5910 | Process Equipment Datasheet - 10-PK-5910 - Oxygen Scavenger Inj Pkg | A | 2018-12-07 | IFR | OL1-2G30-5910 | PE | 2018-12-10 | 036909C-JVD-TRN-00456 | 036909C-JVD-TRN-00456 | IFR | 2018-12-21 | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00456
036909C-1059-PDS-2600-5910 | Process Equipment Datasheet - 10-PK-5910 - Oxygen Scavenger Inj Pkg | B | 2019-01-24 | IFD | OL1-2G30-5910 | PE | 2019-01-25 | 036909C-JVD-TRN-00727 | 036909C-JVD-TRN-00727 | IFI |  | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00727
036909C-1059-PDS-2600-5914 | Process Equipment Datasheet - 10-PK-5914 - Phosphate Injection Pkg | B | 2019-01-24 | IFD | OL1-2G30-5914 | PE | 2019-01-28 | 036909C-JVD-TRN-00739 | 036909C-JVD-TRN-00739 | IFI |  | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00739
036909C-1059-PDS-2600-5914 | Process Equipment Datasheet - 10-PK-5914 - Phosphate Injection Pkg | A | 2018-12-07 | IFR | OL1-2G30-5914 | PE | 2018-12-10 | 036909C-JVD-TRN-00456 | 036909C-JVD-TRN-00456 | IFR | 2018-12-21 | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00456
036909C-1059-PDS-2500-5950 | Process Equipment Datasheet - 10-TK-5950 - Sodium Hypochlorite Tank | A | 2018-11-29 | IFR | OL1-2G30-5950 | PE | 2018-12-04 | 036909C-JVD-TRN-00406 | 036909C-JVD-TRN-00406 | IFR | 2018-12-17 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00406
036909C-1051-PDS-2500-5120 | Process Equipment Datasheet - 10-TK-5120 - Raw Condensate Tank | A | 2018-11-16 | IFR | OL1-2G30-5120 | PE | 2018-11-26 | 036909C-JVD-TRN-00364 | 036909C-JVD-TRN-00364 | IFR | 2018-12-10 | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-00364
036909C-1055-PDS-0600-5553 | Process Equipment Datasheet - 10-E-5552 - LPG Vaporizer - Superheater | A | 2019-01-09 | IFR | OL1-2G30-5553 | PE | 2019-01-10 | 036909C-JVD-TRN-00622 | 036909C-JVD-TRN-00622 | IFR | 2019-01-23 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00622
036909C-1052-PDS-0600-5210 | Process Equipment Datasheet - 10-E-5210 - Pilot Gas Vaporizer | A | 2018-11-14 | IFR | OL1-2G30-5210 | PE | 2018-11-15 | 036909C-JVD-TRN-00321 | 036909C-JVD-TRN-00321 | IFR | 2018-11-29 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00321
036909C-1055-PDS-0800-5515 | Process Equipment Datasheet - 10-D-5515 - Methanol Makeup Drum | A | 2018-12-17 | IFR | OL1-2G30-5515 | PE | 2018-12-20 | 036909C-JVD-TRN-00527 | 036909C-JVD-TRN-00527 | IFR | 2019-01-02 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00527
036909C-1056-PDS-0900-5606 | Process Equipment Datasheet - 10-P-5600 A-B - Pygas Area Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5606 | PE | 2019-01-31 | 036909C-JVD-TRN-00779 | 036909C-JVD-TRN-00779 | IFI |  | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00779
036909C-1051-PDS-0900-5141 | Process Equipment Datasheet - 10-P-5140 A-B - Intermittent Blowdown Pumps | A | 2018-10-23 | IFR | OL1-2G30-5141 | PE | 2018-10-24 | 036909C-JVD-TRN-00219 | 036909C-JVD-TRN-00219 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00219
036909C-1056-PDS-0900-5611 | Process Equipment Datasheet - 10-P-5610 - Hydroblast Sump Pump | A | 2019-01-03 | IFR | OL1-2G30-5611 | PE | 2019-01-07 | 036909C-JVD-TRN-00590 | 036909C-JVD-TRN-00590 | IFR | 2019-01-21 | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00590
036909C-1056-PDS-0900-5638 | Process Equipment Datasheet - 10-P-5633 A-B - HP Flare Area SW Sump Pumps | B | 2019-03-09 | IFD | OL1-2G30-5638 | PE | 2019-03-12 | 036909C-JVD-TRN-01019 | 036909C-JVD-TRN-01019 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01019 |  | 2019-03-12
036909C-1056-PDS-0900-5637 | Process Equipment Datasheet - 10-P-5632 A-B - HP Flare Area Oily WW Sump Pumps | B | 2019-03-09 | IFD | OL1-2G30-5637 | PE | 2019-03-12 | 036909C-JVD-TRN-01019 | 036909C-JVD-TRN-01019 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01019 |  | 2019-03-12
036909C-1056-PDS-0900-5621 | Process Equipment Datasheet - 10-P-5621 - Olefins Holding Basin Skimmed Oil Pump | C | 2019-03-09 | IFD | OL1-2G30-5621 | PE | 2019-03-12 | 036909C-JVD-TRN-01022 | 036909C-JVD-TRN-01022 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01022 |  | 2019-03-12
036909C-105F-DW-0051-0001 | Detail Plot Plan - Zone 5F HP And Polyolefins Flares Unit | A | 2019-03-11 | IFR | OL1-2P06-0014 | MP | 2019-03-13 | 036909C-JVD-TRN-01031 | 036909C-JVD-TRN-01031 | IFA | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-MP-01031 |  | 2019-03-13
036909C-1055-PDS-0800-5555 | Process Equipment Datasheet - 10-D-5553 - LPG Vaporizer - Superhtr Cond Pot | B | 2019-03-09 | IFD | OL1-2G30-5555 | PE | 2019-03-12 | 036909C-JVD-TRN-01018 | 036909C-JVD-TRN-01018 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01018 |  | 2019-03-12
036909C-1055-PDS-0800-5510 | Process Equipment Datasheet - 10-D-5510 - Cold Flare Drum | B | 2019-03-09 | IFD | OL1-2G30-5510 | PE | 2019-03-12 | 036909C-JVD-TRN-01018 | 036909C-JVD-TRN-01018 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01018 |  | 2019-03-12
036909C-1053-SP-1513-5301 | Complex Loop Narratives - Area 53 - Cooling Water System | A | 2019-03-11 | IFR | OL1-2I71-5301 | IE | 2019-03-13 | 036909C-JVD-TRN-01037 | 036909C-JVD-TRN-01037 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-IE-01037 |  | 2019-03-13
036909C-1053-SP-0910-5371 | Mechanical Equipment Datasheet - CW Filter Backwash Pumps | B | 2019-03-05 | IFQ | OL1-2M03-5371 | ME | 2019-03-13 | 036909C-JVD-TRN-01038 | 036909C-JVD-TRN-01038 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-ME-01038 |  | 2019-03-13
036909C-1053-SP-1513-5302 | Instrument Interlock Descriptions - Area 53- Cooling Water System | A | 2019-03-11 | IFR | OL1-2I30-5302 | IE | 2019-03-13 | 036909C-JVD-TRN-01037 | 036909C-JVD-TRN-01037 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-IE-01037 |  | 2019-03-13
036909C-1055-PDS-0800-5550 | Process Equipment Datasheet - 10-D-5550 - HP Flare Knock-Out Drum | C | 2019-03-09 | IFD | OL1-2G30-5550 | PE | 2019-03-12 | 036909C-JVD-TRN-01020 | 036909C-JVD-TRN-01020 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01020 |  | 2019-03-12
036909C-1055-PDS-0800-5500 | Process Equipment Datasheet - 10-D-5500 - Hot Flare Drum | C | 2019-03-09 | IFD | OL1-2G30-5500 | PE | 2019-03-12 | 036909C-JVD-TRN-01020 | 036909C-JVD-TRN-01020 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01020 |  | 2019-03-12
036909C-1055-PDS-0900-5501 | Process Equipment Datasheet - 10-P-5500 A-B - Hot Blowdown Pumps | C | 2019-03-09 | IFD | OL1-2G30-5501 | PE | 2019-03-12 | 036909C-JVD-TRN-01022 | 036909C-JVD-TRN-01022 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01022 |  | 2019-03-12
036909C-1053-DW-1514-5301 | Cause and Effect Diagram - Area 53 - Cooling Water System | A | 2019-03-11 | IFR | OL1-2I30-5301 | IE | 2019-03-13 | 036909C-JVD-TRN-01036 | 036909C-JVD-TRN-01036 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-IE-01036 |  | 2019-03-13
036909C-1052-PDS-0800-5200 | Process Equipment Datasheet - 10-D-5200 - Fuel Gas Drum | B | 2018-12-05 | IFD | OL1-2G30-5200 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00440
036909C-1051-PDS-2500-5110 | Process Equipment Datasheet - 10-TK-5110 - Condensate Tank | B | 2019-03-09 | IFD | OL1-2G30-5110 | PE | 2019-03-12 | 036909C-JVD-TRN-01017 | 036909C-JVD-TRN-01017 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01017 |  | 2019-03-12
036909C-1051-SP-0214-0002 | Mechanical Equipment Datasheet For Condensate Carbon Filter Package | A | 2019-03-11 | IFQ | OL1-2M03-5115 | ME | 2019-03-13 | 036909C-JVD-TRN-01040 | 036909C-JVD-TRN-01040 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-ME-01040 |  | 2019-03-13
036909C-102E-DW-1743-0009 | Foundation For 10-D-2220 | A | 2019-03-07 | IFR | OL1-2K34-0050 | CV | 2019-03-13 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13
036909C-102E-DW-1743-0007 | Foundation For 10-D-2245 | A | 2019-03-06 | IFR | OL1-2K34-0047 | CV | 2019-03-13 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13
036909C-102E-DW-1743-0008 | Foundation For 10-D-2445 | A | 2019-03-07 | IFR | OL1-2K34-0048 | CV | 2019-03-13 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13
036909C-102E-DW-1743-0004 | Foundation For 10-D-2435 | A | 2019-03-07 | IFR | OL1-2K34-0044 | CV | 2019-03-13 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13
036909C-102E-DW-1743-0006 | Foundation For 10-D-2240 | A | 2019-03-06 | IFR | OL1-2K34-0046 | CV | 2019-03-13 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13
036909C-102E-CN-1733-0009 | Calculation Note For Foundation Of 10-D-2220 | A | 2019-03-07 | IFR | OL1-2K13-0045 | CV | 2019-03-13 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033 | IFA | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13
036909C-102E-DW-1743-0003 | Foundation For 10-D-2410 A/B/C | A | 2019-03-07 | IFR | OL1-2K34-0043 | CV | 2019-03-13 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13
036909C-102E-CN-1733-0007 | Calculation Note For Foundation Of 10-D-2245 | A | 2019-03-11 | IFR | OL1-2K13-0042 | CV | 2019-03-13 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033 | IFA | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13
036909C-102E-CN-1733-0006 | Calculation Note For Foundation Of 10-D-2240 | A | 2019-03-07 | IFR | OL1-2K13-0041 | CV | 2019-03-13 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033 | IFA | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13
036909C-102E-CN-1733-0008 | Calculation Note For Foundation Of 10-D-2445 | A | 2019-03-07 | IFR | OL1-2K13-0043 | CV | 2019-03-13 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033 | IFA | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13
036909C-102D-DW-1743-0040 | Foundation For 10-E-2852 | A | 2019-03-08 | IFR | OL1-2K34-0137 | CV | 2019-03-13 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13
036909C-102E-CN-1733-0004 | Calculation Note For Foundation Of 10-D-2435 | A | 2019-03-11 | IFR | OL1-2K13-0039 | CV | 2019-03-13 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033 | IFA | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13
036909C-102E-CN-1733-0003 | Calculation Note For Foundation Of 10-D-2410 A/B/C | A | 2019-03-11 | IFR | OL1-2K13-0038 | CV | 2019-03-13 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033 | IFA | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13
036909C-102D-DW-1743-0030 | Foundation for 10-E-2645A/B | A | 2019-03-07 | IFR | OL1-2K34-0123 | CV | 2019-03-14 | 036909C-JVD-TRN-01042 | 036909C-JVD-TRN-01042 | IFR | 2019-03-28 |  | Transmitted | TPSK-LSPA1-T-CV-01042 |  | 2019-03-14
036909C-102D-CN-1733-0039 | Calculation Note For Foundation Of 10-E-2852 | A | 2019-03-08 | IFR | OL1-2K13-0130 | CV | 2019-03-13 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033 | IFA | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13
036909C-102B-DW-1743-0043 | Foundation For 10-E-1015 | A | 2019-03-05 | IFR | OL1-2K34-0168 | CV | 2019-03-13 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13
036909C-102B-CN-1733-0019 | Calculation Note For Foundation Of 10-E-2620 | A | 2019-03-05 | IFR | OL1-2K13-0140 | CV | 2019-03-13 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033 | IFA | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13
036909C-102B-CN-1733-0043 | Calculation Note For Foundation Of 10-E-1015 | A | 2019-03-05 | IFR | OL1-2K13-0162 | CV | 2019-03-13 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033 | IFA | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13
036909C-102B-DW-1743-0041 | Foundation For 10-E-1001 | A | 2019-03-05 | IFR | OL1-2K34-0169 | CV | 2019-03-13 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13
036909C-102B-CN-1733-0041 | Calculation Note For Foundation Of 10-E-1001 | A | 2019-03-05 | IFR | OL1-2K13-0163 | CV | 2019-03-13 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033 | IFA | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13
036909C-102B-DW-1743-0022 | Foundation For 10-E-2620 | A | 2019-03-05 | IFR | OL1-2K34-0146 | CV | 2019-03-13 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13
036909C-1027-PDS-0900-2704 | Process Equipment Datasheet - 10-P-2705 A-B - GHU-1 Recycle Pump | B | 2019-03-08 | IFD | OL1-2G30-2704 | PE | 2019-03-12 | 036909C-JVD-TRN-01025 | 036909C-JVD-TRN-01025 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01025 |  | 2019-03-12
036909C-1027-PDS-0800-2735 | Process Equipment Datasheet - 10-D-2735 - Regen Hydrog Drum | A | 2019-03-13 | IFR | OL1-2G30-2735 | PE | 2019-03-14 | 036909C-JVD-TRN-01049 | 036909C-JVD-TRN-01049 | IFR | 2019-03-28 |  | Transmitted | TPSK-LSPA1-T-PE-01049 |  | 2019-03-14
036909C-1027-PDS-0900-2713 | Process Equipment Datasheet - 10-P-2710 A-B - Depentanizer Reflux Pump | B | 2019-03-08 | IFD | OL1-2G30-2713 | PE | 2019-03-12 | 036909C-JVD-TRN-01025 | 036909C-JVD-TRN-01025 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01025 |  | 2019-03-12
036909C-1028-PDS-0800-2880 | Process Equipment Datasheet - 10-D-2880 - C2R 3rd Stage Suction Drum | B | 2019-02-12 | IFD | OL1-2G30-2880 | PE | 2019-02-12 | 036909C-JVD-TRN-00845 | 036909C-JVD-TRN-00845 | IFI |  | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00845
036909C-1027-PDS-0800-2762 | Process Equipment Datasheet - 10-D-2760 - C4-C5 Hydrog Recycle Drum | B | 2019-03-06 | IFD | OL1-2G30-2762 | PE | 2019-03-12 | 036909C-JVD-TRN-01023 | 036909C-JVD-TRN-01023 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01023 |  | 2019-03-12
036909C-1028-SP-0910-2855 | Mechanical Equipment Datasheet - Ethylene Product Pumps | B | 2019-01-31 | IFQ | OL1-2M03-2855 | ME | 2019-03-13 | 036909C-JVD-TRN-01035 | 036909C-JVD-TRN-01035 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-ME-01035 |  | 2019-03-13
036909C-1028-SP-0910-2801 | Mechanical Equipment Datasheet - Propylene Product Pumps | B | 2019-01-31 | IFQ | OL1-2M03-2801 | ME | 2019-03-13 | 036909C-JVD-TRN-01035 | 036909C-JVD-TRN-01035 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-ME-01035 |  | 2019-03-13
036909C-1027-PDS-0800-2750 | Process Equipment Datasheet - 10-D-2750 - C4-C5 Hydrog Surge Drum | B | 2019-03-04 | IFD | OL1-2G30-2750 | PE | 2019-03-12 | 036909C-JVD-TRN-01023 | 036909C-JVD-TRN-01023 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01023 |  | 2019-03-12
036909C-1027-PDS-0400-2760 | Process Equipment Datasheet - 10-R-2760 - C4-C5 Hydrog Reactor | B | 2019-03-07 | IFD | OL1-2G30-2760 | PE | 2019-03-12 | 036909C-JVD-TRN-01030 | 036909C-JVD-TRN-01030 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01030 |  | 2019-03-12
036909C-1027-PDS-0600-2765 | Process Equipment Datasheet - 10-E-2765 - C4-C5 Hydrog Recycle Cooler | B | 2019-03-07 | IFD | OL1-2G30-2765 | PE | 2019-03-12 | 036909C-JVD-TRN-01027 | 036909C-JVD-TRN-01027 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01027 |  | 2019-03-12
036909C-1027-PDS-0600-2763 | Process Equipment Datasheet - 10-E-2760 - C4-C5 Hydrog Vent Condenser | B | 2019-03-04 | IFD | OL1-2G30-2763 | PE | 2019-03-12 | 036909C-JVD-TRN-01027 | 036909C-JVD-TRN-01027 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01027 |  | 2019-03-12
036909C-1026-PDS-0800-2622 | Process Equipment Datasheet - 10-D-2620 - C3 Hydrog Recycle Drum | B | 2019-03-08 | IFD | OL1-2G30-2622 | PE | 2019-03-12 | 036909C-JVD-TRN-01023 | 036909C-JVD-TRN-01023 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01023 |  | 2019-03-12
036909C-1026-PDS-0900-2668 | Process Equipment Datasheet - 10-P-2666 A-B - C5 - Pygas Pumps | B | 2019-03-08 | IFD | OL1-2G30-2668 | PE | 2019-03-12 | 036909C-JVD-TRN-01025 | 036909C-JVD-TRN-01025 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01025 |  | 2019-03-12
036909C-1026-PDS-0800-2600 | Process Equipment Datasheet - 10-D-2600 A-B - C3 Hydrog Guard Adsorber | C | 2019-03-13 | IFD | OL1-2G30-2600 | PE | 2019-03-14 | 036909C-JVD-TRN-01049 | 036909C-JVD-TRN-01049 | IFR | 2019-03-28 |  | Transmitted | TPSK-LSPA1-T-PE-01049 |  | 2019-03-14
036909C-1026-PDS-0840-2664 | Process Equipment Datasheet - 10-F-2666 A-B - C5 - Pygas Feed Filters | B | 2019-03-08 | IFD | OL1-2G30-2664 | PE | 2019-03-12 | 036909C-JVD-TRN-01024 | 036909C-JVD-TRN-01024 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01024 |  | 2019-03-12
036909C-101B-DW-1743-0003 | Foundation For 10-E-5210 | A | 2019-03-08 | IFR | OL1-2K34-0009 | CV | 2019-03-13 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13
036909C-101B-CN-1733-0003 | Calculation Note For Foundation Of 10-E-5210 | A | 2019-03-11 | IFR | OL1-2K13-0006 | CV | 2019-03-13 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033 | IFA | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13
036909C-1012-SP-1040-2001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 132U | 0 | 2019-03-06 | IMP | OL1-2M03-2001 | ME | 2019-03-12 | 036909C-JVD-TRN-01021 | 036909C-JVD-TRN-01021 | IFR |  |  | Transmitted | TPSK-LSPA1-T-ME-01021 |  | 2019-03-12
036909C-1012-PDS-1545-1203 | USC 132U Superheater Outlet PSV Datasheet - 10-PSV-1244 | A | 2019-03-07 | IFR | OL1-2G32-1203 | PE | 2019-03-12 | 036909C-JVD-TRN-01029 | 036909C-JVD-TRN-01029 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01029 |  | 2019-03-12
036909C-1012-PDS-1545-1202 | USC 132U Steam Drum PSV Datasheet - 10-PSV-1242B | A | 2019-03-07 | IFR | OL1-2G32-1202 | PE | 2019-03-12 | 036909C-JVD-TRN-01029 | 036909C-JVD-TRN-01029 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01029 |  | 2019-03-12
036909C-1012-PDS-1545-1201 | USC 132U Steam Drum PSV Datasheet - 10-PSV-1242A | A | 2019-03-07 | IFR | OL1-2G32-1201 | PE | 2019-03-12 | 036909C-JVD-TRN-01029 | 036909C-JVD-TRN-01029 | IFR | 2019-03-26 |  | Transmitted | TPSK-LSPA1-T-PE-01029 |  | 2019-03-12
036909C-1011-SP-1040-1001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 36M | 0 | 2019-03-06 | IMP | OL1-2M03-1001 | ME | 2019-03-12 | 036909C-JVD-TRN-01021 | 036909C-JVD-TRN-01021 | IFR |  |  | Transmitted | TPSK-LSPA1-T-ME-01021 |  | 2019-03-12
036909C-1011-SP-1552-1005 | USC 36M and USC 132U Instrument Datasheets for Level Gauge | A | 2019-03-07 | IFR | OL1-2I20-1005 | IE | 2019-03-14 | 036909C-JVD-TRN-01047 | 036909C-JVD-TRN-01047 | IFR | 2019-03-28 |  | Transmitted | TPSK-LSPA1-T-IE-01047 |  | 2019-03-14
036909C-1010-DW-1514-1001 | Cause and Effect Diagram - Area 10 - Feed Preparation and Feed Preheat | A | 2019-03-13 | IFR | OL1-2I30-1001 | IE | 2019-03-14 | 036909C-JVD-TRN-01043 | 036909C-JVD-TRN-01043 | IFR | 2019-03-28 |  | Transmitted | TPSK-LSPA1-T-IE-01043 |  | 2019-03-14
036909C-1011-PDS-1545-1101 | USC 36M Steam Drum PSV Datasheet - 10-PSV-1142A | A | 2019-03-07 | IFR | OL1-2G32-1101 | PE | 2019-03-12 | 036909C-JVD-TRN-01028 | 036909C-JVD-TRN-01028 | IFR | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-PE-01028 |  | 2019-03-12
036909C-1011-PDS-1545-1102 | USC 36M Steam Drum PSV Datasheet - 10-PSV-1142B | A | 2019-03-07 | IFR | OL1-2G32-1102 | PE | 2019-03-12 | 036909C-JVD-TRN-01028 | 036909C-JVD-TRN-01028 | IFR | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-PE-01028 |  | 2019-03-12
036909C-1011-PDS-1545-1103 | USC 36M Superheater Outlet PSV Datasheet - 10-PSV-1144 | A | 2019-03-07 | IFR | OL1-2G32-1103 | PE | 2019-03-12 | 036909C-JVD-TRN-01028 | 036909C-JVD-TRN-01028 | IFR | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-PE-01028 |  | 2019-03-12
036909C-1010-SP-1513-1002 | Instrument Interlock Descriptions - Area 10 - Feed Preparation and Feed Preheat | A | 2019-03-13 | IFR | OL1-2I30-1002 | IE | 2019-03-14 | 036909C-JVD-TRN-01045 | 036909C-JVD-TRN-01045 | IFR | 2019-03-28 |  | Transmitted | TPSK-LSPA1-T-IE-01045 |  | 2019-03-14
036909C-1000-MR-0811-0002 | Material Requisition For Shop Assembled CS Drums | A | 2019-03-08 | IFQ | OL1-2C13-132000 | PL | 2019-03-13 | 036909C-JVD-TRN-01032 | 036909C-JVD-TRN-01032 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-PL-01032 |  | 2019-03-13
036909C-1000-MR-0214-0001 | Material Requisition For Condensate Carbon Filter Package | A | 2019-03-11 | IFQ | OL1-2C13-151000 | PL | 2019-03-13 | 036909C-JVD-TRN-01039 | 036909C-JVD-TRN-01039 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-PL-01039 |  | 2019-03-13
036909C-1000-JSD-1560-0001 | Process On-Line Analyzer And Analyzer Housing | 0 | 2019-03-08 | IMP | OL1-2R06-2003 | IE | 2019-03-14 | 036909C-JVD-TRN-01044 | 036909C-JVD-TRN-01044 | IFR | 2019-03-28 |  | Transmitted | TPSK-LSPA1-T-IE-01044 |  | 2019-03-14
036909C-1026-PDS-0800-2644 | Process Equipment Datasheet - 10-D-2645 - C3 Tower Reboiler Cond Pot | C | 2019-02-26 | IFD | OL1-2G30-2644 | PE | 2019-02-27 | 036909C-JVD-TRN-00938 | 036909C-JVD-TRN-00938 | IFR | 2019-03-13 | 2019-03-14 | R1-No comments | TPSK-LSPA1-T-PE-00938 |  | 2019-02-27
036909C-1056-PDS-2600-5691 | Process Equipment Datasheet - 10-PK-5691 - Slop Tank Acid Injection Pkg | A | 2019-02-07 | IFR | OL1-2G30-5691 | PE | 2019-02-07 | 036909C-JVD-TRN-00821 | 036909C-JVD-TRN-00821 | IFR | 2019-02-21 | 2019-03-14 | R1-No comments | TPSK-LSPA1-T-PE-00821
036909C-1056-PDS-2600-5690 | Process Equipment Datasheet - 10-PK-5690 - Slop Tank Polymer Injection Pkg | A | 2019-02-07 | IFR | OL1-2G30-5690 | PE | 2019-02-07 | 036909C-JVD-TRN-00821 | 036909C-JVD-TRN-00821 | IFR | 2019-02-21 | 2019-03-14 | R1-No comments | TPSK-LSPA1-T-PE-00821
036909C-1029-PDS-2600-2940 | Process Equipment Datasheet - 10-PK-2940 - C4 Polymer Inhibitor Inj Pkg | B | 2019-01-24 | IFD | OL1-2G30-2940 | PE | 2019-01-25 | 036909C-JVD-TRN-00726 | 036909C-JVD-TRN-00726 | IFI |  | 2019-03-14 | R1-No comments | TPSK-LSPA1-T-PE-00726
036909C-1056-PDS-0200-5633 | Process Equipment Datasheet - 10-PIT-5633 - HP Flare Area Stormwater Sump | B | 2019-02-28 | IFD | OL1-2G30-5633 | PE | 2019-03-04 | 036909C-JVD-TRN-00960 | 036909C-JVD-TRN-00960 | IFR | 2019-03-16 | 2019-03-14 | R1-No comments | TPSK-LSPA1-T-PE-00960 |  | 2019-03-04
036909C-1022-PDS-0800-2245 | Process Equipment Datasheet - 10-D-2245 - CG 4th Stage Discharge Drum | B | 2018-12-10 | IFD | OL1-2G30-2245 | PE | 2018-12-13 | 036909C-JVD-TRN-00480 | 036909C-JVD-TRN-00480 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00480
036909C-1024-PDS-0800-2452 | Process Equipment Datasheet - 10-D-2450 - LP Depropanizer Reflux Drum | B | 2018-12-04 | IFD | OL1-2G30-2452 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  | 2018-12-18 | R1-No comments | TPSK-LSPA1-T-PE-00430
036909C-1023-PDS-0800-2322 | Process Equipment Datasheet - 10-D-2322 - Skim Oil Drum | A | 2018-09-27 | IFA | OL1-2G30-2322 | PE | 2018-09-28 | 036909C-JVD-TRN-00111 | 036909C-JVD-TRN-00111 | IFA | 2018-10-12 | 2019-02-25 | A1-Approved without comments | TPSK-LSPA1-T-PE-00111 |  | 2018-09-28
036909C-1024-PDS-0800-2405 | Process Equipment Datasheet - 10-D-2405 - Gas Dryer Feed KO Drum | B | 2018-12-10 | IFD | OL1-2G30-2405 | PE | 2018-12-13 | 036909C-JVD-TRN-00480 | 036909C-JVD-TRN-00480 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00480
036909C-1023-PDS-0800-2392 | Process Equipment Datasheet - 10-D-2392 - Spent Caustic Drain Drum | B | 2018-11-26 | IFD | OL1-2G30-2392 | PE | 2018-11-27 | 036909C-JVD-TRN-00369 | 036909C-JVD-TRN-00369 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00369
036909C-1022-PDS-0800-2240 | Process Equipment Datasheet - 10-D-2240 - CG 4th Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2240 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00448
036909C-1023-PDS-0800-2316 | Process Equipment Datasheet - 10-D-2316 - Spent Caustic Degassing Drum | B | 2019-01-10 | IFD | OL1-2G30-2316 | PE | 2019-01-11 | 036909C-JVD-TRN-00634 | 036909C-JVD-TRN-00634 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00634
036909C-1023-PDS-0800-2331 | Process Equipment Datasheet - 10-D-2330 - Spent Caustic Stripper Ovhd Drum | B | 2019-01-10 | IFD | OL1-2G30-2331 | PE | 2019-01-11 | 036909C-JVD-TRN-00634 | 036909C-JVD-TRN-00634 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00634
036909C-1024-PDS-0800-2435 | Process Equipment Datasheet - 10-D-2435 - Regen Gas Separator | B | 2019-01-24 | IFD | OL1-2G30-2435 | PE | 2019-01-25 | 036909C-JVD-TRN-00725 | 036909C-JVD-TRN-00725 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00725
036909C-1023-PDS-0800-2309 | Process Equipment Datasheet - 10-D-2305 - Yellow Oil Drum | B | 2019-01-10 | IFD | OL1-2G30-2309 | PE | 2019-01-11 | 036909C-JVD-TRN-00634 | 036909C-JVD-TRN-00634 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00634
036909C-1023-PDS-0800-2310 | Process Equipment Datasheet - 10-D-2310 - Spent Caustic Deoiling Drum | B | 2019-01-02 | IFD | OL1-2G30-2310 | PE | 2019-01-07 | 036909C-JVD-TRN-00599 | 036909C-JVD-TRN-00599 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00599
036909C-1021-PDS-0800-2110 | Process Equipment Datasheet - 10-D-2110 - Interception Drum | C | 2019-02-28 | IFD | OL1-2G30-2110 | PE | 2019-03-04 | 036909C-JVD-TRN-00964 | 036909C-JVD-TRN-00964 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-PE-00964 |  | 2019-03-04
036909C-1021-PDS-0800-2190 | Process Equipment Datasheet - 10-D-2190 - Quench Water Drain Drum | B | 2019-02-28 | IFD | OL1-2G30-2190 | PE | 2019-03-04 | 036909C-JVD-TRN-00964 | 036909C-JVD-TRN-00964 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-PE-00964 |  | 2019-03-04
036909C-1025-PDS-0800-2504 | Process Equipment Datasheet - 10-D-2504 - Demeth Prefrac Feed Separator No 1 | B | 2018-11-08 | IFD | OL1-2G30-2504 | PE | 2018-11-09 | 036909C-JVD-TRN-00303 | 036909C-JVD-TRN-00303 | IFI |  | 2018-11-26 | R1-No comments | TPSK-LSPA1-T-PE-00303
036909C-1023-PDS-0800-2390 | Process Equipment Datasheet - 10-D-2390 - Caustic Drain Drum | B | 2018-11-26 | IFD | OL1-2G30-2390 | PE | 2018-11-27 | 036909C-JVD-TRN-00369 | 036909C-JVD-TRN-00369 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00369
036909C-1025-PDS-0800-2572 | Process Equipment Datasheet - 10-D-2570 - Deethanizer Reflux Drum | B | 2018-12-06 | IFD | OL1-2G30-2572 | PE | 2018-12-07 | 036909C-JVD-TRN-00446 | 036909C-JVD-TRN-00446 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00446
036909C-1020-PDS-0800-2090 | Process Equipment Datasheet - 10-D-2090 - Quench Oil Drain Drum | B | 2019-02-28 | IFD | OL1-2G30-2090 | PE | 2019-03-04 | 036909C-JVD-TRN-00964 | 036909C-JVD-TRN-00964 | IFR | 2019-03-16 |  | Transmitted | TPSK-LSPA1-T-PE-00964 |  | 2019-03-04
036909C-1026-PDS-0800-2632 | Process Equipment Datasheet - 10-D-2630 - Secondary Deeth Reflux Drum | B | 2018-11-29 | IFD | OL1-2G30-2632 | PE | 2019-01-11 | 036909C-JVD-TRN-00633 | 036909C-JVD-TRN-00633 | IFI |  | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00633
036909C-1027-PDS-0800-2718 | Process Equipment Datasheet - 10-D-2720 - Rerun Tower Reflux Drum | A | 2019-01-28 | IFR | OL1-2G30-2718 | PE | 2019-02-01 | 036909C-JVD-TRN-00781 | 036909C-JVD-TRN-00781 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00781
036909C-1027-PDS-0800-2790 | Process Equipment Datasheet - 10-D-2790 - Light Oil Drain Drum | B | 2019-01-23 | IFD | OL1-2G30-2790 | PE | 2019-01-25 | 036909C-JVD-TRN-00721 | 036909C-JVD-TRN-00721 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00721
036909C-1027-PDS-0800-2724 | Process Equipment Datasheet - 10-D-2724 - Wash Oil Degrassing Drum | A | 2019-01-28 | IFR | OL1-2G30-2724 | PE | 2019-02-01 | 036909C-JVD-TRN-00781 | 036909C-JVD-TRN-00781 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00781
036909C-1026-PDS-0800-2667 | Process Equipment Datasheet - 10-D-2666 - C5 - Pygas Surge Drum | A | 2019-01-28 | IFR | OL1-2G30-2667 | PE | 2019-02-01 | 036909C-JVD-TRN-00781 | 036909C-JVD-TRN-00781 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00781
036909C-1028-PDS-0800-2805 | Process Equipment Datasheet - 10-D-2805 - C3R Surge Drum | B | 2018-11-21 | IFD | OL1-2G30-2805 | PE | 2018-11-21 | 036909C-JVD-TRN-00348 | 036909C-JVD-TRN-00348 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00348
036909C-1027-PDS-0800-2705 | Process Equipment Datasheet - 10-D-2705 - GHU-1 Hot Separator | A | 2019-01-28 | IFR | OL1-2G30-2705 | PE | 2019-02-01 | 036909C-JVD-TRN-00781 | 036909C-JVD-TRN-00781 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00781
036909C-1026-PDS-0800-2662 | Process Equipment Datasheet - 10-D-2660 - Debutanizer Reflux Drum | B | 2019-01-14 | IFD | OL1-2G30-2662 | PE | 2019-01-16 | 036909C-JVD-TRN-00660 | 036909C-JVD-TRN-00660 | IFI |  | 2019-01-29 | R1-No comments | TPSK-LSPA1-T-PE-00660
036909C-1055-PDS-0800-5514 | Process Equipment Datasheet - 10-D-5513 - Methanol Vaporizer Cond Pot | B | 2019-01-29 | IFD | OL1-2G30-5514 | PE | 2019-02-01 | 036909C-JVD-TRN-00785 | 036909C-JVD-TRN-00785 | IFI |  | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00785
036909C-1052-PDS-0800-5202 | Process Equipment Datasheet - 10-D-5220 - MP Ethylene Superhtr Cond Pot | B | 2019-02-10 | IFD | OL1-2G30-5202 | PE | 2019-02-11 | 036909C-JVD-TRN-00836 | 036909C-JVD-TRN-00836 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE--00836
036909C-1022-SP-0810-2245 | Mechanical Equipment Data Sheet - CG 4th Stage Discharge Drum | A | 2018-12-24 | IFQ | OL1-2M03-2245 | ME | 2019-01-16 | 036909C-JVD-TRN-00657 | 036909C-JVD-TRN-00657 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00657
036909C-1028-PDS-0800-2830 | Process Equipment Datasheet - 10-D-2830 - C3R 3rd Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2830 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349
036909C-1028-PDS-0800-2820 | Process Equipment Datasheet - 10-D-2820 - C3R 2nd Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2820 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349
036909C-1052-PDS-0800-5211 | Process Equipment Datasheet - 10-D-5210 - Pilot Gas Vaporizer Cond Pot | B | 2019-02-10 | IFD | OL1-2G30-5211 | PE | 2019-02-11 | 036909C-JVD-TRN-00836 | 036909C-JVD-TRN-00836 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE--00836
036909C-1027-SP-0810-2750 | Mechanical Equipment Data Sheet - C4-C5 Hydrog Surge Drum | A | 2019-02-08 | IFQ | OL1-2M03-2750 | ME | 2019-02-15 | 036909C-JVD-TRN-00869 | 036909C-JVD-TRN-00869 | IFR | 2019-03-04 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00869 |  | 2019-02-15
036909C-1025-SP-0810-2574 | Mechanical Equipment Data Sheet - Deethanizer Reboilder Cond Pot | A | 2018-12-20 | IFQ | OL1-2M03-2574 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00685
036909C-1028-PDS-0800-2815 | Process Equipment Datasheet - 10-D-2815 - C3R Drain Drum | B | 2019-01-09 | IFD | OL1-2G30-2815 | PE | 2019-01-11 | 036909C-JVD-TRN-00633 | 036909C-JVD-TRN-00633 | IFI |  | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00633
036909C-1029-PDS-0800-2932 | Process Equipment Datasheet - 10-D-2930 - Methanol Drum | B | 2019-02-01 | IFD | OL1-2G30-2932 | PE | 2019-02-01 | 036909C-JVD-TRN-00796 | 036909C-JVD-TRN-00796 | IFI |  | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00796
036909C-1026-SP-0810-2644 | Mechanical Equipment Data Sheet - C3 Tower Reboilder Cond Pot | A | 2019-01-25 | IFQ | OL1-2M03-2644 | ME | 2019-01-29 | 036909C-JVD-TRN-00753 | 036909C-JVD-TRN-00753 | IFR | 2019-02-12 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00753
036909C-1027-SP-0810-2724 | Mechanical Equipment Data Sheet - Wash Oil Degassing Drum | A | 2019-02-14 | IFQ | OL1-2M03-2724 | ME | 2019-02-15 | 036909C-JVD-TRN-00869 | 036909C-JVD-TRN-00869 | IFR | 2019-03-04 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00869 |  | 2019-02-15
036909C-1024-SP-0810-2444 | Mechanical Equipment Data Sheet - HP Deprop Reboiler Cond Pot | A | 2019-01-05 | IFQ | OL1-2M03-2444 | ME | 2019-01-11 | 036909C-JVD-TRN-00629 | 036909C-JVD-TRN-00629 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00629
036909C-1055-PDS-0800-5552 | Process Equipment Datasheet - 10-D-5552 - LPG Storage Drum | B | 2019-03-07 | IFD | OL1-2G30-5552 | PE | 2019-03-08 | 036909C-JVD-TRN-01008 | 036909C-JVD-TRN-01008 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-PE-01008 |  | 2019-03-08
036909C-1024-SP-0810-2405 | Mechanical Equipment Data Sheet - Gas Dryer Feed KO Drum | A | 2019-01-05 | IFQ | OL1-2M03-2405 | ME | 2019-01-11 | 036909C-JVD-TRN-00629 | 036909C-JVD-TRN-00629 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00629
036909C-1026-SP-0810-2622 | Mechanical Equipment Data Sheet - C3 Hydrog Recycle Drum | A | 2019-01-15 | IFQ | OL1-2M03-2622 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00685
036909C-1055-PDS-0800-5520 | Process Equipment Datasheet - 10-D-5520 - Vent Collection Drum | B | 2019-01-29 | IFD | OL1-2G30-5520 | PE | 2019-02-15 | 036909C-JVD-TRN-00856 | 036909C-JVD-TRN-00856 | IFR | 2019-03-01 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00856 |  | 2019-02-15
036909C-1026-SP-0810-2632 | Mechanical Equipment Data Sheet - Secondary Deeth Reflux Drum | A | 2019-01-05 | IFQ | OL1-2M03-2632 | ME | 2019-01-11 | 036909C-JVD-TRN-00629 | 036909C-JVD-TRN-00629 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00629
036909C-1020-PDS-4200-2036 | Process Equipment Datasheet - 10-X-2036 - Quench Fitting | B | 2019-01-07 | IFD | OL1-2G30-2036 | PE | 2019-01-07 | 036909C-JVD-TRN-00604 | 036909C-JVD-TRN-00604 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00604
036909C-1051-PDS-0800-5150 | Process Equipment Datasheet - 10-D-5150 - Continuous Blow Down Flash Drum | B | 2018-12-05 | IFD | OL1-2G30-5150 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  | 2019-03-11 | R1-No comments | TPSK-LSPA1-T-PE-00440
036909C-1051-PDS-0800-5114 | Process Equipment Datasheet - 10-D-5114 - LP Condensate Flash Drum | B | 2018-12-12 | IFD | OL1-2G30-5114 | PE | 2018-12-14 | 036909C-JVD-TRN-00498 | 036909C-JVD-TRN-00498 | IFI |  | 2019-01-10 | R1-No comments | TPSK-LSPA1-T-PE-00498
036909C-1051-PDS-0800-5112 | Process Equipment Datasheet - 10-D-5112 - Suspect Condensate Flash Drum | B | 2018-12-12 | IFD | OL1-2G30-5112 | PE | 2018-12-14 | 036909C-JVD-TRN-00498 | 036909C-JVD-TRN-00498 | IFI |  | 2019-01-10 | R1-No comments | TPSK-LSPA1-T-PE-00498
036909C-1021-SP-0810-2110 | Mechanical Equipment Data Sheet - Interception Drum | A | 2019-01-17 | IFQ | OL1-2M03-2110 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685 | IFR | 2019-02-04 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-00685
036909C-1027-SP-0810-2718 | Mechanical Equipment Data Sheet - Rerun Tower Reflux Drum | A | 2019-02-06 | IFQ | OL1-2M03-2718 | ME | 2019-02-15 | 036909C-JVD-TRN-00869 | 036909C-JVD-TRN-00869 | IFR | 2019-03-04 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00869 |  | 2019-02-15
036909C-1026-SP-0810-2667 | Mechanical Equipment Data Sheet - C5-Pygas Surge Drum | A | 2019-02-08 | IFQ | OL1-2M03-2667 | ME | 2019-02-15 | 036909C-JVD-TRN-00869 | 036909C-JVD-TRN-00869 | IFR | 2019-03-04 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00869 |  | 2019-02-15
036909C-1023-SP-0810-2392 | Mechanical Equipment Data Sheet - Spent Caustic Drain Drum | A | 2019-01-11 | IFQ | OL1-2M03-2392 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685 | IFR | 2019-02-04 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-00685
036909C-1021-SP-0810-2190 | Mechanical Equipment Data Sheet - Quench Water Drain Drum | A | 2019-01-10 | IFQ | OL1-2M03-2190 | ME | 2019-01-11 | 036909C-JVD-TRN-00638 | 036909C-JVD-TRN-00638 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00638
036909C-1024-SP-0810-2456 | Mechanical Equipment Data Sheet - LP Deprop Reboilder Cond Pot | A | 2019-01-17 | IFQ | OL1-2M03-2456 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00685
036909C-1020-SP-0810-2090 | Mechanical Equipment Data Sheet - Quench Oil Drain Drum | A | 2019-01-10 | IFQ | OL1-2M03-2090 | ME | 2019-01-11 | 036909C-JVD-TRN-00638 | 036909C-JVD-TRN-00638 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00638
036909C-1023-SP-0810-2316 | Mechanical Equipment Data Sheet - Spent Caustic Degassing Drum | A | 2018-12-10 | IFQ | OL1-2M03-2316 | ME | 2019-01-07 | 036909C-JVD-TRN-00601 | 036909C-JVD-TRN-00601 | IFR | 2019-01-21 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00601
036909C-1024-SP-0810-2435 | Mechanical Equipment Data Sheet - Regen Gas Separator | A | 2019-01-17 | IFQ | OL1-2M03-2435 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00685
036909C-1023-SP-0810-2331 | Mechanical Equipment Data Sheet - Spent Caustic Stripper OVHD Drum | A | 2019-01-10 | IFQ | OL1-2M03-2331 | ME | 2019-01-11 | 036909C-JVD-TRN-00638 | 036909C-JVD-TRN-00638 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00638
036909C-1055-SP-0810-5515 | Mechanical Equipment Data Sheet - C3R Drain Drum | A | 2018-12-21 | IFQ | OL1-2M03-5515 | ME | 2019-01-08 | 036909C-JVD-TRN-00607 | 036909C-JVD-TRN-00607 | IFR | 2019-01-22 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-ME-00607
036909C-1027-SP-0810-2762 | Mechanical Equipment Data Sheet - C4-C5 Hydrog Recycle Drum | A | 2019-02-14 | IFQ | OL1-2M03-2762 | ME | 2019-02-15 | 036909C-JVD-TRN-00869 | 036909C-JVD-TRN-00869 | IFR | 2019-03-04 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00869 |  | 2019-02-15
036909C-1029-SP-0810-2932 | Mechanical Equipment Data Sheet - Methanol Drum | A | 2019-01-18 | IFQ | OL1-2M03-2932 | ME | 2019-01-23 | 036909C-JVD-TRN-00709 | 036909C-JVD-TRN-00709 | IFR | 2019-02-05 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00709
036909C-1028-SP-0810-2815 | Mechanical Equipment Data Sheet - C3R Drain Drum | A | 2018-12-18 | IFQ | OL1-2M03-2815 | ME | 2019-01-08 | 036909C-JVD-TRN-00607 | 036909C-JVD-TRN-00607 | IFR | 2019-01-22 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-ME-00607
036909C-1027-SP-0810-2790 | Mechanical Equipment Data Sheet - Light Oil Drain Drum | A | 2018-12-20 | IFQ | OL1-2M03-2790 | ME | 2019-01-08 | 036909C-JVD-TRN-00607 | 036909C-JVD-TRN-00607 | IFR | 2019-01-22 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-ME-00607
036909C-1051-SP-0810-5114 | Mechanical Equipment Data Sheet - LP Condensate Flash Drum | A | 2019-01-10 | IFQ | OL1-2M03-5114 | ME | 2019-01-16 | 036909C-JVD-TRN-00657 | 036909C-JVD-TRN-00657 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00657
036909C-1052-SP-0810-5200 | Mechanical Equipment Data Sheet - Fuel Gas Drum | A | 2019-01-09 | IFQ | OL1-2M03-5200 | ME | 2019-01-11 | 036909C-JVD-TRN-00629 | 036909C-JVD-TRN-00629 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00629
036909C-1051-SP-0810-5112 | Mechanical Equipment Data Sheet - Suspect Condensate Flash Drum | A | 2019-01-05 | IFQ | OL1-2M03-5112 | ME | 2019-01-16 | 036909C-JVD-TRN-00657 | 036909C-JVD-TRN-00657 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00657
036909C-1051-SP-0810-5140 | Mechanical Equipment Data Sheet - Intermittent Blowdown Drum | B | 2019-01-10 | IFQ | OL1-2M03-5140 | ME | 2019-01-11 | 036909C-JVD-TRN-00638 | 036909C-JVD-TRN-00638 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00638
036909C-1055-SP-0810-5520 | Mechanical Equipment Data Sheet - Vent Collection Drum | A | 2019-01-10 | IFQ | OL1-2M03-5520 | ME | 2019-01-11 | 036909C-JVD-TRN-00638 | 036909C-JVD-TRN-00638 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00638
036909C-1052-SP-0810-5202 | Mechanical Equipment Data Sheet - MP Ethylene Superhtr Cond Pot | A | 2019-01-17 | IFQ | OL1-2M03-5202 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685 | IFR | 2019-02-04 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-00685
036909C-1055-SP-0810-5514 | Mechanical Equipment Data Sheet - Methanol Vaporizer Cond Pot | A | 2019-01-22 | IFQ | OL1-2M03-5514 | ME | 2019-01-23 | 036909C-JVD-TRN-00709 | 036909C-JVD-TRN-00709 | IFR | 2019-02-05 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00709
036909C-1051-SP-0810-5150 | Mechanical Equipment Data Sheet - Continuous Blow Down Flash Drum | A | 2019-01-05 | IFQ | OL1-2M03-5150 | ME | 2019-01-11 | 036909C-JVD-TRN-00629 | 036909C-JVD-TRN-00629 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00629
036909C-1052-SP-0810-5211 | Mechanical Equipment Data Sheet - Pilot Gas Vaporizer Cond Pot | A | 2019-01-18 | IFQ | OL1-2M03-5211 | ME | 2019-01-23 | 036909C-JVD-TRN-00709 | 036909C-JVD-TRN-00709 | IFR | 2019-02-05 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00709
036909C-1055-SP-0810-5552 | Mechanical Equipment Data Sheet - LPG Storage Drum | A | 2018-12-18 | IFQ | OL1-2M03-5552 | ME | 2019-01-11 | 036909C-JVD-TRN-00638 | 036909C-JVD-TRN-00638 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00638
036909C-1000-JSS-0570-01 | Job Specification For Supply Of Column Internals | 0 | 2018-09-20 | IMP | OL1-2R03-0052 | ME | 2018-09-25 | 036909C-JVD-TRN-00081 | 036909C-JVD-TRN-00081, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00081 |  | 2018-09-25
036909C-1000-JSS-1820-01 | Job Specification For Supply Of Equipment Ladders And Platforms | 0 | 2018-09-20 | IFR | OL1-2R03-0053 | ME | 2018-09-25 | 036909C-JVD-TRN-00081 | 036909C-JVD-TRN-00081 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00081 |  | 2018-09-25
036909C-1055-SP-0810-5555 | Mechanical Equipment Data Sheet - LPG Vaporizer-Superhtr Cond Pot | A | 2019-01-15 | IFQ | OL1-2M03-5555 | ME | 2019-01-23 | 036909C-JVD-TRN-00709 | 036909C-JVD-TRN-00709 | IFR | 2019-02-05 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00709
036909C-1026-PDS-0800-2600 | Process Equipment Datasheet - 10-D-2600 A-B - C3 Hydrog Guard Adsorber | B | 2019-01-08 | IFD | OL1-2G30-2600 | PE | 2019-01-10 | 036909C-JVD-TRN-00618 | 036909C-JVD-TRN-00618 | IFI |  | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00618
036909C-1026-PDS-0800-2600 | Process Equipment Datasheet - 10-D-2600 A-B - C3 Hydrog Guard Adsorber | A | 2018-12-05 | IFR | OL1-2G30-2600 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00439
036909C-1000-JSD-1560-0001 | Process On-Line Analyzer And Analyzer Housing | A | 2019-01-31 | IFR | OL1-2R06-2003 | IE | 2019-02-08 | 036909C-JVD-TRN-00825 | 036909C-JVD-TRN-00825, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-25 | 2019-03-08 | R1-No comments | TPSK-LSPA1-T-IE-00825
036909C-1027-PDS-0800-2762 | Process Equipment Datasheet - 10-D-2760 - C4-C5 Hydrog Recycle Drum | A | 2019-01-31 | IFR | OL1-2G30-2762 | PE | 2019-02-01 | 036909C-JVD-TRN-00794 | 036909C-JVD-TRN-00794 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00794
036909C-1027-PDS-0800-2750 | Process Equipment Datasheet - 10-D-2750 - C4-C5 Hydrog Surge Drum | A | 2019-01-31 | IFR | OL1-2G30-2750 | PE | 2019-02-01 | 036909C-JVD-TRN-00794 | 036909C-JVD-TRN-00794 | IFR | 2019-02-15 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00794
036909C-1055-PDS-0800-5555 | Process Equipment Datasheet - 10-D-5553 - LPG Vaporizer - Superhtr Cond Pot | A | 2019-01-09 | IFR | OL1-2G30-5555 | PE | 2019-01-10 | 036909C-JVD-TRN-00619 | 036909C-JVD-TRN-00619 | IFR | 2019-01-23 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00619
036909C-1056-PDS-0200-5647 | Process Equipment Datasheet - 10-PIT-5607 - Flare KO Drum Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5647 | PE | 2019-03-05 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05
036909C-1056-PDS-0200-5646 | Process Equipment Datasheet - 10-PIT-5606 - C3 Hydrog Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5646 | PE | 2019-03-05 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05
036909C-1056-PDS-0200-5632 | Process Equipment Datasheet - 10-PIT-5632 - HP Flare Area Oily WW Sump | C | 2019-03-04 | IFD | OL1-2G30-5632 | PE | 2019-03-05 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05
036909C-1056-PDS-0200-5631 | Process Equipment Datasheet - 10-PIT-5631 - CWWT Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5631 | PE | 2019-03-05 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05
036909C-1056-PDS-0200-5630 | Process Equipment Datasheet - 10-PIT-5630 - CT Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5630 | PE | 2019-03-05 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05
036909C-1056-PDS-0200-5605 | Process Equipment Datasheet - 10-PIT-5605 - Furnace Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5605 | PE | 2019-03-05 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05
036909C-1056-PDS-0200-5604 | Process Equipment Datasheet - 10-PIT-5604 - Refrig Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5604 | PE | 2019-03-05 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05
036909C-1056-PDS-0200-5603 | Process Equipment Datasheet - 10-PIT-5603 - CGC Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5603 | PE | 2019-03-05 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05
036909C-1056-PDS-0200-5602 | Process Equipment Datasheet - 10-PIT-5602 - QW Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5602 | PE | 2019-03-05 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05
036909C-1056-PDS-0200-5601 | Process Equipment Datasheet - 10-PIT-5601 - Butadiene Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5601 | PE | 2019-03-05 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05
036909C-1056-PDS-0200-5600 | Process Equipment Datahseet - 10-PIT-5600 - Pygas Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5600 | PE | 2019-03-05 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05
036909C-1055-PDS-1000-5522 | Process Equipment Datasheet - 10-C-5520 A-B - LP Vent Blowers | B | 2019-01-29 | IFD | OL1-2G30-5522 | PE | 2019-02-11 | 036909C-JVD-TRN-00837 | 036909C-JVD-TRN-00837 | IFI |  | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00837
036909C-1054-PDS-0800-5400 | Process Equipment Datasheet - 10-D-5400 - Instrument Air Receiver | B | 2019-01-29 | IFD | OL1-2G30-5400 | PE | 2019-02-06 | 036909C-JVD-TRN-00800 | 036909C-JVD-TRN-00800 | IFI |  | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00800
036909C-1000-JSS-1112-0001 | ME-020 Special Purpose Steam Tturbines | A | 2018-09-20 | IFR | OL1-2R03-0020 | ME | 2018-09-25 | 036909C-JVD-TRN-00078 | 036909C-JVD-TRN-00078 | IFR | 2018-10-08 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-ME-00078 |  | 2018-09-25
036909C-1000-JSS-1061-0001 | ME-019 Lube Oil Unit And Seal Oil System | A | 2018-09-18 | IFR | OL1-2R03-0019 | ME | 2018-10-19 | 036909C-JVD-TRN-00065 | 036909C-JVD-TRN-00065 | IFR | 2018-10-03 | 2018-10-10 | R1-No comments | TPSK-LSPA1-T-ME-00065 |  | 2018-10-19
036909C-1000-JSS-1111-0001 | ME-018 General Purpose Steam Turbines | A | 2018-09-20 | IFR | OL1-2R03-0018 | ME | 2018-09-25 | 036909C-JVD-TRN-00078 | 036909C-JVD-TRN-00078 | IFR | 2018-10-08 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-ME-00078 |  | 2018-09-25
036909C-1024-PDS-0800-2410 | Process Equipment Datasheet - 10-D-2410 A-B - Cracked Gas Dryer | C | 2019-03-02 | IFD | OL1-2G30-2410 | PE | 2019-03-05 | 036909C-JVD-TRN-00980 | 036909C-JVD-TRN-00980 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00980 |  | 2019-03-05
036909C-1026-PDS-4200-2624 | Process Equipment Datasheet - 10-X-2620 - C3 Hydrog Static Mixer | B | 2019-02-28 | IFD | OL1-2G30-2624 | PE | 2019-03-04 | 036909C-JVD-TRN-00968 | 036909C-JVD-TRN-00968 | IFR | 2019-03-16 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00968 |  | 2019-03-04
036909C-1026-PDS-0600-2621 | Process Equipment Datasheet - 10-E-2620 - C3 Hydrog Aftercooler | B | 2019-02-28 | IFD | OL1-2G30-2621 | PE | 2019-03-04 | 036909C-JVD-TRN-00966 | 036909C-JVD-TRN-00966 | IFR | 2019-03-16 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00966 |  | 2019-03-04
036909C-1054-PDS-0800-5400 | Process Equipment Datasheet - 10-D-5400 - Instrument Air Receiver | C | 2019-03-04 | IFD | OL1-2G30-5400 | PE | 2019-03-05 | 036909C-JVD-TRN-00983 | 036909C-JVD-TRN-00983 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00983 |  | 2019-03-05
036909C-1053-PDS-0300-5370 | Process Equipment Datasheet - 10-PIT-5370 - CW Filter Backwash Sump | B | 2019-01-31 | IFD | OL1-2G30-5370 | PE | 2019-02-01 | 036909C-JVD-TRN-00791 | 036909C-JVD-TRN-00791 | IFI |  | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00791
036909C-1053-PDS-0300-5360 | Process Equipment Datasheet - 10-PIT-5360 A-C - CTU CW Pumps Sump | B | 2019-01-31 | IFD | OL1-2G30-5360 | PE | 2019-02-01 | 036909C-JVD-TRN-00791 | 036909C-JVD-TRN-00791 | IFI |  | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00791
036909C-1053-PDS-0300-5351 | Process Equipment Datasheet - 10-PIT-5351 A-H - Olefins CW Pumps Sump | B | 2019-01-31 | IFD | OL1-2G30-5351 | PE | 2019-02-01 | 036909C-JVD-TRN-00791 | 036909C-JVD-TRN-00791 | IFI |  | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00791
036909C-1053-PDS-2600-5392 | Process Equipment Datasheet - 10-PK-5392 - Mild Steel Coor Inhibitor Inj Pkg | B | 2019-02-15 | IFD | OL1-2G30-5392 | PE | 2019-02-19 | 036909C-JVD-TRN-00890 | 036909C-JVD-TRN-00890 | IFR | 2019-03-06 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00890 |  | 2019-02-19
036909C-1053-PDS-2600-5397 | Process Equipment Datasheet - 10-PK-5397 - Non-oxidizing Biocide Inj Pkg | B | 2019-02-08 | IFD | OL1-2G30-5397 | PE | 2019-02-19 | 036909C-JVD-TRN-00877 | 036909C-JVD-TRN-00877 | IFR | 2019-03-05 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00877 |  | 2019-02-19
036909C-1053-PDS-2600-5394 | Process Equipment Datasheet - 10-PK-5394 - Dispersant Inj Pkg | B | 2019-02-15 | IFD | OL1-2G30-5394 | PE | 2019-02-19 | 036909C-JVD-TRN-00877 | 036909C-JVD-TRN-00877 | IFR | 2019-03-05 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00877 |  | 2019-02-19
036909C-1053-PDS-2600-5390 | Process Equipment Datasheet - 10-PK-5390 - Copper Corrosion Inhibitor Inj Pkg | B | 2019-02-15 | IFD | OL1-2G30-5390 | PE | 2019-02-19 | 036909C-JVD-TRN-00877 | 036909C-JVD-TRN-00877 | IFR | 2019-03-05 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00877 |  | 2019-02-19
036909C-1000-JSD-1572-0003 | Instrument Air Supply | 0 | 2019-02-28 | IMP | OL1-2R06-0011 | IE | 2019-03-11 | 036909C-JVD-TRN-01014 | 036909C-JVD-TRN-01014, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-IE-01014 |  | 2019-03-11
036909C-1050-DI-0007-5001 | Area Basis of Design - 50 ISBL Supporting Utilities | A | 2018-07-25 | IFA | OL1-2G05-5001 | PE | 2018-07-31 | 036909C-JVD-TRN-00003 | 036909C-JVD-TRN-00003, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-13 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00003 |  | 2018-07-31
036909C-1000-JSD-1600-0001 | General Electrical Design | 0 | 2018-12-03 | IMP | OL1-2R05-0001 | EE | 2018-12-05 | 036909C-JVD-TRN-00424 | 036909C-JVD-TRN-00424, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00424
036909C-1000-JSD-1553-0001 | Pressure Measurement | 0 | 2018-12-14 | IMP | OL1-2R06-0006 | IE | 2018-12-17 | 036909C-JVD-TRN-00507 | 036909C-JVD-TRN-00507, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-28 | 2018-12-26 | R1-No comments | TPSK-LSPA1-T-IE-00507
036909C-1000-JSD-1554-0001 | Temperature Measurement | 0 | 2018-12-14 | IMP | OL1-2R06-0007 | IE | 2018-12-17 | 036909C-JVD-TRN-00507 | 036909C-JVD-TRN-00507, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-28 | 2018-12-26 | R1-No comments | TPSK-LSPA1-T-IE-00507
036909C-1000-JSD-1600-0010 | Earthing And Lightning Protection | 0 | 2018-09-20 | IMP | OL1-2R05-0015 | EE | 2018-11-05 | 036909C-JVD-TRN-00258 | 036909C-JVD-TRN-00258, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00258
036909C-1000-JSD-1552-0001 | Level Measurement | 0 | 2018-12-14 | IMP | OL1-2R06-0005 | IE | 2018-12-17 | 036909C-JVD-TRN-00507 | 036909C-JVD-TRN-00507, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-28 | 2018-12-26 | R1-No comments | TPSK-LSPA1-T-IE-00507
036909C-1000-JSD-1540-0001 | Instrument General Design | 0 | 2018-12-14 | IMP | OL1-2R06-0001 | IE | 2018-12-17 | 036909C-JVD-TRN-00507 | 036909C-JVD-TRN-00507, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-28 | 2018-12-26 | R1-No comments | TPSK-LSPA1-T-IE-00507
036909C-1000-JSD-1600-0004 | LIGHTING SYSTEM | 0 | 2018-09-20 | IMP | OL1-2R05-0014 | EE | 2018-11-05 | 036909C-JVD-TRN-00258 | 036909C-JVD-TRN-00258, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00258
036909C-1000-JSS-1622-0001 | Miscellaneous Equipment | 0 | 2018-09-20 | IMP | OL1-2R05-0022 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268
036909C-1000-JSD-1547-0001 | Flow Measurement | 0 | 2018-09-28 | IMP | OL1-2R06-0003 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122
036909C-1000-JSD-1545-0001 | Pressure Safety Valve | 0 | 2018-09-28 | IMP | OL1-2R06-0021 | IE | 2018-10-04 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | 2018-10-04
036909C-1000-JSD-1572-0001 | Instrument Construction Material | 0 | 2018-09-28 | IMP | OL1-2R06-0010 | IE | 2018-10-04 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | 2018-10-04
036909C-1000-JSD-1572-0004 | Instrument Installation | 0 | 2018-09-28 | IMP | OL1-2R08-0003 | IE | 2018-10-04 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | 2018-10-04
036909C-1000-JSD-1501-0003 | Instrument Inspection And Test Plan | 0 | 2018-09-28 | IMP | OL1-2R06-0023 | IE | 2018-10-04 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | 2018-10-04
036909C-1000-JSD-1541-0001 | Final Control Element | A | 2018-09-28 | IFR | OL1-2R06-0008 | IE | 2018-10-04 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04
036909C-1000-JSD-1572-0005 | Grounding System for Instrument | 0 | 2018-12-14 | IMP | OL1-2R06-0012 | IE | 2018-12-17 | 036909C-JVD-TRN-00508 | 036909C-JVD-TRN-00508, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00508
036909C-1000-JSD-1300-0001 | Piping Class Summary And Piping Classes - Includes ex doc. OL1-2P92-0003 as attachment | A | 2018-12-20 | IFR | OL1-2R04-0001 | MP | 2018-12-27 | 036909C-JVD-TRN-00562 | 036909C-JVD-TRN-00562, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-01-11 | 2019-01-17 | R2-Comments as noted | TPSK-LSPA1-T-MP-00562 | Includes ex doc. OL1-2P92-0003 as attachment
036909C-1000-JSD-6200-0001 | Environmental Protection Design Criteria | A | 2018-12-05 | IFR | OL1-2S08-0001 | ES | 2018-12-11 | 036909C-JVD-TRN-00473 | 036909C-JVD-TRN-00473 | IFR | 2018-12-27 |  | Transmitted | TPSK-LSPA1-T-ES-00473
036909C-1000-JSD-6000-0001 | Noise Control | A | 2018-12-05 | IFR | OL1-2L10-0001 | SE | 2018-12-11 | 036909C-JVD-TRN-00472 | 036909C-JVD-TRN-00472 | IFR | 2018-12-27 |  | Transmitted | TPSK-LSPA1-T-SE-00472
036909C-1000-JSD-1300-0002 | Job Specification For Detail Design Piping | 0 | 2019-01-25 | IMP | OL1-2R04-0002 | MP | 2019-01-28 | 036909C-JVD-TRN-00736 | 036909C-JVD-TRN-00736, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-12 | 2019-03-01 | R2-Comments as noted | TPSK-LSPA1-T-MP-00736
036909C-1000-JSS-1350-01 | Job Supply Specification For Flanges | B | 2018-11-19 | IFR | OL1-2R04-0015 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00342
036909C-1000-JSD-1700-0001 | Job Design Specification For Foundations And Structures | 0 | 2019-02-14 | IMP | OL1-2R02-0004 | CV | 2019-02-19 | 036909C-JVD-TRN-00887 | 036909C-JVD-TRN-00887, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-03-06 |  | Transmitted | TPSK-LSPA1-T-CV-00887 |  | 2019-02-19
036909C-1000-JSS-1320-01 | Job Supply Specification For Pipes | B | 2018-11-19 | IFR | OL1-2R04-0011 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00342
036909C-1000-DW-1802-0001 | General Notes For Steel Structure | 0 | 2019-02-14 | IFC | OL1-2K92-0004 | CV | 2019-02-15 | 036909C-JVD-TRN-00867 | 036909C-JVD-TRN-00867 | IFA | 2019-03-04 |  | Transmitted | TPSK-LSPA1-T-CV-00867 |  | 2019-02-15
036909C-1000-JSS-1340-01 | Job Supply Specification For Forged Fittings | B | 2018-11-19 | IFR | OL1-2R04-0014 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00342
036909C-1000-JSS-1330-01 | Job Supply Specification For Buttwelding Fittings | B | 2018-11-19 | IFR | OL1-2R04-0013 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00342
036909C-1000-JSS-1300-01 | General Supply Specification For Piping Material | 0 | 2019-02-27 | IMP | OL1-2R04-0006 | MP | 2019-03-01 | 036909C-JVD-TRN-00951 | 036909C-JVD-TRN-00951 | IFR | 2019-03-15 |  | Transmitted | TPSK-LSPA1-T-MP-00951 |  | 2019-03-01
036909C-1000-STC-1890-0001 | Construction Standards For Steel Structures | A | 2018-09-19 | IFR | OL1-2K21-0001 | CV | 2018-09-27 | 036909C-JVD-TRN-00088 | 036909C-JVD-TRN-00088 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00088 |  | 2018-09-27
036909C-1053-SP-0910-5371 | Mechanical Equipment Datasheet - CW Filter Backwash Pumps | A | 2019-01-18 | IFQ | OL1-2M03-5371 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716
036909C-1028-SP-0910-2801 | Mechanical Equipment Datasheet - Propylene Product Pumps | A | 2018-12-18 | IFQ | OL1-2M03-2801 | ME | 2018-12-20 | 036909C-JVD-TRN-00543 | 036909C-JVD-TRN-00543 | IFR | 2019-01-02 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-ME-00543
036909C-1028-SP-0910-2855 | Mechanical Equipment Datasheet - Ethylene Product Pumps | A | 2018-12-05 | IFQ | OL1-2M03-2855 | ME | 2018-12-13 | 036909C-JVD-TRN-00494 | 036909C-JVD-TRN-00494 | IFR | 2018-12-26 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00494
036909C-1052-PDS-0800-5200 | Process Equipment Datasheet - 10-D-5200 - Fuel Gas Drum | A | 2018-11-15 | IFR | OL1-2G30-5200 | PE | 2018-11-19 | 036909C-JVD-TRN-00331 | 036909C-JVD-TRN-00331 | IFR | 2018-12-03 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00331
036909C-1028-PDS-0800-2880 | Process Equipment Datasheet - 10-D-2880 - C2R 3rd Stage Suction Drum | A | 2018-10-22 | IFR | OL1-2G30-2880 | PE | 2018-10-23 | 036909C-JVD-TRN-00208 | 036909C-JVD-TRN-00208 | IFR | 2018-11-06 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00208
036909C-1027-SP-0910-2728 | Mechanical Equipment Datasheet - Recycle Wash Oil Pumps | A | 2019-02-13 | IFQ | OL1-2M03-2728 | ME | 2019-02-19 | 036909C-JVD-TRN-00891 | 036909C-JVD-TRN-00891 | IFR | 2019-03-06 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00891 |  | 2019-02-19
036909C-102D-CN-1733-0042 | Calculation Note For Foundation of 10-E-2582 | B | 2019-02-19 | IFR | OL1-2K13-0132 | CV | 2019-02-22 | 036909C-JVD-TRN-00904 | 036909C-JVD-TRN-00904 | IFA | 2019-03-08 | 2019-03-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00904 |  | 2019-02-22
036909C-1027-SP-0910-2719 | Mechanical Equipment Datasheet - Rerun Tower Reflux - Product Pumps | A | 2019-02-13 | IFQ | OL1-2M03-2719 | ME | 2019-02-19 | 036909C-JVD-TRN-00891 | 036909C-JVD-TRN-00891 | IFR | 2019-03-06 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00891 |  | 2019-02-19
036909C-1027-SP-0910-2714 | Mechanical Equipment Datasheet - C5 Cut Pumps | A | 2019-02-13 | IFQ | OL1-2M03-2714 | ME | 2019-02-19 | 036909C-JVD-TRN-00891 | 036909C-JVD-TRN-00891 | IFR | 2019-03-06 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00891 |  | 2019-02-19
036909C-102A-CN-1733-0034 | Calculation Note For Foundation of 10-T-2100 | A | 2019-02-14 | IFR | OL1-2K13-0324 | CV | 2019-02-22 | 036909C-JVD-TRN-00904 | 036909C-JVD-TRN-00904 | IFA | 2019-03-08 | 2019-03-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00904 |  | 2019-02-22
036909C-1027-SP-0910-2713 | Mechanical Equipment Datasheet - Depentanizer Reflux Pump | A | 2019-02-13 | IFQ | OL1-2M03-2713 | ME | 2019-02-19 | 036909C-JVD-TRN-00891 | 036909C-JVD-TRN-00891 | IFR | 2019-03-06 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00891 |  | 2019-02-19
036909C-1027-SP-0910-2704 | Mechanical Equipment Datasheet - GHU-1 Recycle Pump | A | 2019-02-12 | IFQ | OL1-2M03-2704 | ME | 2019-02-19 | 036909C-JVD-TRN-00891 | 036909C-JVD-TRN-00891 | IFR | 2019-03-06 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00891 |  | 2019-02-19
036909C-1024-SP-0910-2453 | Mechanical Equipment Datasheet - LP Depropanizer Reflux - Product Pump | B | 2019-02-27 | IFQ | OL1-2M03-2453 | ME | 2019-02-28 | 036909C-JVD-TRN-00944 | 036909C-JVD-TRN-00944 | IFR | 2019-03-14 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00944 |  | 2019-02-28
036909C-1027-SP-0910-2726 | Mechanical Equipment Datasheet - Pygas Fuel Oil Pumps | A | 2019-02-19 | IFQ | OL1-2M03-2726 | ME | 2019-02-20 | 036909C-JVD-TRN-00898 | 036909C-JVD-TRN-00898 | IFR | 2019-03-07 | 2019-03-19 | R1-No comments | TPSK-LSPA1-T-ME-00898 |  | 2019-02-20
036909C-1026-SP-0910-2668 | Mechanical Equipment Datasheet - C5 - Pygas Pumps | A | 2019-02-19 | IFQ | OL1-2M03-2668 | ME | 2019-02-20 | 036909C-JVD-TRN-00898 | 036909C-JVD-TRN-00898 | IFR | 2019-03-07 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00898 |  | 2019-02-20
036909C-1027-SP-0940-2729 | Mechanical Equipment Datasheet -Wash Oil Pumps | A | 2019-02-19 | IFQ | OL1-2M03-2729 | ME | 2019-02-20 | 036909C-JVD-TRN-00898 | 036909C-JVD-TRN-00898 | IFR | 2019-03-07 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00898 |  | 2019-02-20
036909C-1027-TDS-0610-2715 | Mechanical Equipment Data Sheet - 10-E-2715 A-B - Depentanizer Reboiler | A | 2019-02-13 | IFQ | OL1-2M03-2715 | ME | 2019-02-22 | 036909C-JVD-TRN-00908 | 036909C-JVD-TRN-00908 | IFR | 2019-03-08 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00908 |  | 2019-02-22
036909C-1027-TDS-0610-2711 | Mechanical Equipment Data Sheet - 10-E-2710 - Depentanizer Condenser | A | 2019-02-08 | IFQ | OL1-2M03-2711 | ME | 2019-02-22 | 036909C-JVD-TRN-00908 | 036909C-JVD-TRN-00908 | IFR | 2019-03-08 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00908 |  | 2019-02-22
036909C-1027-TDS-0610-2703 | Mechanical Equipment Data Sheet - 10-E-2705 - GHU-1 Recycle Cooler | A | 2019-02-18 | IFQ | OL1-2M03-2703 | ME | 2019-02-19 | 036909C-JVD-TRN-00895 | 036909C-JVD-TRN-00895 | IFR | 2019-03-06 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00895 |  | 2019-02-19
036909C-1026-SP-0510-2640 | Mechanical Equipment Data Sheet - C3 Tower | B | 2019-02-13 | IFQ | OL1-2M03-2640 | ME | 2019-02-19 | 036909C-JVD-TRN-00885 | 036909C-JVD-TRN-00885 | IFR | 2019-03-05 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00885 |  | 2019-02-19
036909C-1024-SP-0510-2450 | Mechanical Equipment Data Sheet - LP Depropanizer | D | 2019-02-15 | IFQ | OL1-2M03-2450 | ME | 2019-02-19 | 036909C-JVD-TRN-00884 | 036909C-JVD-TRN-00884 | IFR | 2019-03-05 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00884 |  | 2019-02-19
036909C-1024-SP-0510-2440 | Mechanical Equipment Datasheet - HP Depropanizer | C | 2019-02-15 | IFQ | OL1-2M03-2440 | ME | 2019-02-19 | 036909C-JVD-TRN-00884 | 036909C-JVD-TRN-00884 | IFR | 2019-03-05 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00884 |  | 2019-02-19
036909C-1023-SP-0510-2300 | Mechanical Equipment Data Sheet - Caustic Tower | C | 2019-02-15 | IFQ | OL1-2M03-2300 | ME | 2019-02-19 | 036909C-JVD-TRN-00883 | 036909C-JVD-TRN-00883 | IFR | 2019-03-05 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME -00883 |  | 2019-02-19
036909C-1027-SP-0810-2712 | Mechanical Equipment Data Sheet - Depentanizer Reflux Drum | A | 2019-02-06 | IFQ | OL1-2M03-2712 | ME | 2019-02-15 | 036909C-JVD-TRN-00874 | 036909C-JVD-TRN-00874 | IFR | 2019-03-04 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00874 |  | 2019-02-15
036909C-1026-SP-0510-2660 | Mechanical Equipment Datasheet - Debutanizer | D | 2019-02-13 | IFQ | OL1-2M03-2660 | ME | 2019-02-15 | 036909C-JVD-TRN-00861 | 036909C-JVD-TRN-00861 | IFR | 2019-03-04 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00861 |  | 2019-02-15
036909C-1025-TDS-0610-2582 | Mechanical Equipment Data Sheet - 10-E-2582 - C2 Tower Reflux Cooler | B | 2019-02-13 | IFQ | OL1-2M03-2582 | ME | 2019-02-15 | 036909C-JVD-TRN-00859 | 036909C-JVD-TRN-00859 | IFR | 2019-03-01 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00859 |  | 2019-02-15
036909C-1024-SP-0810-2460 | Mechanical Equipment Data Sheet - C2 Hydrog Arsine Guard Bed | B | 2019-02-13 | IFQ | OL1-2M03-2460 | ME | 2019-02-15 | 036909C-JVD-TRN-00858 | 036909C-JVD-TRN-00858 | IFR | 2019-03-01 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME -00858 |  | 2019-02-15
036909C-1023-SP-0510-2330 | Mechanical Equipment Data Sheet - Spent Caustic Stripper | B | 2019-02-13 | IFQ | OL1-2M03-2330 | ME | 2019-02-15 | 036909C-JVD-TRN-00857 | 036909C-JVD-TRN-00857 | IFR | 2019-03-01 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00857 |  | 2019-02-15
036909C-102D-CN-1733-0038 | Calculation Note For Foundation Of 10-E-2853 | A | 2019-02-06 | IFR | OL1-2K13-0129 | CV | 2019-02-19 | 036909C-JVD-TRN-00878 | 036909C-JVD-TRN-00878 | IFA | 2019-03-05 | 2019-03-11 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00878 |  | 2019-02-19
036909C-1029-PID-0021-2930 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - CG Compressor Auxiliaries - Sheet 1 | A | 2019-01-30 | IFR | OL1-2G43-2930 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2924 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - DSG Feed Pump Turbine Details | A | 2019-01-30 | IFR | OL1-2G43-2924 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2976 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C2R Lube Oil Pump Turbine Details | A | 2019-01-30 | IFR | OL1-2G43-2976 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2932 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - CG Compressor Auxiliaries - Sheet 2 | A | 2019-01-30 | IFR | OL1-2G43-2932 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2934 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - CGC Lube Oil Pump Turbine Details | A | 2019-01-30 | IFR | OL1-2G43-2934 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2909 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Methanol Injection System | A | 2019-01-30 | IFR | OL1-2G43-2909 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2908 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Neutralization Injection | A | 2019-01-30 | IFR | OL1-2G43-2908 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2922 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Quench Water Pump Turbine Details | A | 2019-01-30 | IFR | OL1-2G43-2922 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2915 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Wash Oil Storage | A | 2019-01-30 | IFR | OL1-2G43-2915 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2920 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Quench Oil Pump Turbine Details | A | 2019-01-30 | IFR | OL1-2G43-2920 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2902 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Emulsion Breaker Injection System | A | 2019-01-30 | IFR | OL1-2G43-2902 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2904 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - DSG Anti Foulant Injection Package | A | 2019-01-30 | IFR | OL1-2G43-2904 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1027-PDS-0400-2760 | Process Equipment Datasheet - 10-R-2760 - C4-C5 Hydrog Reactor | A | 2019-01-15 | IFR | OL1-2G30-2760 | PE | 2019-01-16 | 036909C-JVD-TRN-00659 | 036909C-JVD-TRN-00659 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00659
036909C-1027-PDS-0600-2763 | Process Equipment Datasheet - 10-E-2760 - C4-C5 Hydrog Vent Condenser | A | 2019-02-01 | IFR | OL1-2G30-2763 | PE | 2019-02-01 | 036909C-JVD-TRN-00793 | 036909C-JVD-TRN-00793 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00793
036909C-1027-PDS-0600-2765 | Process Equipment Datasheet - 10-E-2765 - C4-C5 Hydrog Recycle Cooler | A | 2019-02-01 | IFR | OL1-2G30-2765 | PE | 2019-02-01 | 036909C-JVD-TRN-00793 | 036909C-JVD-TRN-00793 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00793
036909C-1027-PDS-0900-2713 | Process Equipment Datasheet - 10-P-2710 A-B - Depentanizer Reflux Pump | A | 2019-02-11 | IFR | OL1-2G30-2713 | PE | 2019-02-11 | 036909C-JVD-TRN-00834 | 036909C-JVD-TRN-00834 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00834
036909C-1027-PDS-0900-2704 | Process Equipment Datasheet - 10-P-2705 A-B - GHU-1 Recycle Pump | A | 2019-02-11 | IFR | OL1-2G30-2704 | PE | 2019-02-11 | 036909C-JVD-TRN-00834 | 036909C-JVD-TRN-00834 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00834
036909C-1026-PDS-0900-2668 | Process Equipment Datasheet - 10-P-2666 A-B - C5 - Pygas Pumps | A | 2019-02-08 | IFR | OL1-2G30-2668 | PE | 2019-02-11 | 036909C-JVD-TRN-00834 | 036909C-JVD-TRN-00834 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00834
036909C-1026-PDS-0840-2664 | Process Equipment Datasheet - 10-F-2666 A-B - C5 - Pygas Feed Filters | A | 2019-02-18 | IFR | OL1-2G30-2664 | PE | 2019-02-20 | 036909C-JVD-TRN-00900 | 036909C-JVD-TRN-00900 | IFR | 2019-03-07 | 2019-02-26 | R1-No comments | TPSK-LSPA1-T-PE-0900 |  | 2019-02-20
036909C-1026-PDS-0800-2622 | Process Equipment Datasheet - 10-D-2620 - C3 Hydrog Recycle Drum | A | 2019-01-07 | IFR | OL1-2G30-2622 | PE | 2019-01-10 | 036909C-JVD-TRN-00614 | 036909C-JVD-TRN-00614 | IFR | 2019-01-23 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00614
036909C-1056-PDS-0900-5621 | Process Equipment Datasheet - 10-P-5621 - Olefins Holding Basin Skimmed Oil Pump | B | 2019-01-29 | IFD | OL1-2G30-5621 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00774
036909C-1055-PDS-0900-5501 | Process Equipment Datasheet - 10-P-5500 A-B - Hot Blowdown Pumps | B | 2019-01-29 | IFD | OL1-2G30-5501 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774
036909C-1011-SP-1040-1001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 36M | A | 2018-10-30 | IFR | OL1-2M03-1001 | ME | 2018-10-31 | 036909C-JVD-TRN-00247 | 036909C-JVD-TRN-00247 | IFR | 2018-11-13 |  | Transmitted | TPSK-LSPA1-T-ME-00247
036909C-1012-SP-1040-2001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 132U | A | 2018-10-29 | IFR | OL1-2M03-2001 | ME | 2018-10-31 | 036909C-JVD-TRN-00247 | 036909C-JVD-TRN-00247 | IFR | 2018-11-13 |  | Transmitted | TPSK-LSPA1-T-ME-00247
036909C-1055-PDS-0800-5500 | Process Equipment Datasheet - 10-D-5500 - Hot Flare Drum | B | 2018-12-04 | IFD | OL1-2G30-5500 | PE | 2018-12-05 | 036909C-JVD-TRN-00417 | 036909C-JVD-TRN-00417 | IFI |  | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00417
036909C-1055-PDS-0800-5510 | Process Equipment Datasheet - 10-D-5510 - Cold Flare Drum | A | 2018-11-29 | IFR | OL1-2G30-5510 | PE | 2018-11-29 | 036909C-JVD-TRN-00397 | 036909C-JVD-TRN-00397 | IFR | 2018-12-13 | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00397
036909C-1051-PDS-2500-5110 | Process Equipment Datasheet - 10-TK-5110 - Condensate Tank | A | 2018-11-27 | IFR | OL1-2G30-5110 | PE | 2018-11-27 | 036909C-JVD-TRN-00374 | 036909C-JVD-TRN-00374 | IFR | 2018-12-11 | 2018-12-18 | R2-Comments as noted | TPSK-LSPA1-T-PE-00374
036909C-1000-JSD-3400-0001 | Air Conditioning Ventilating And Ducting Design - Ex Document Client Reference: OL1-2H03-0001 - | 0 | 2019-01-02 | IMP | OL1-2E05-0020 | EE | 2019-01-07 | 036909C-JVD-TRN-00585 | 036909C-JVD-TRN-00585, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-01-15 | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-EE-00585 | Ex Document Client Reference: OL1-2H03-0001
036909C-1000-JSS-1031-0001 | ME-047 Dry Screw Compressor for Hydrocarbon Services | 0 | 2019-01-16 | IMP | OL1-2R03-0047 | ME | 2019-01-17 | 036909C-JVD-TRN-00666 | 036909C-JVD-TRN-00666, ROC-TPSK-CECO-T-00004, ROC-TPSK-CECO-T-00003 | IFR | 2019-01-30 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-ME-00666
036909C-1000-MR-1040-0001 | Material Requisition For Vent Gas Blower | A | 2019-03-04 | IFQ | OL1-2C13-451000 | PL | 2019-03-08 | 036909C-JVD-TRN-01001 | 036909C-JVD-TRN-01001 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-PL-01001 |  | 2019-03-08
036909C-1010-TDS-0610-1015 | Mechanical Equipment Data Sheet - 10-E-1015 - LPG Superheater | A | 2018-12-18 | IFQ | OL1-2M03-1015 | ME | 2018-12-27 | 036909C-JVD-TRN-00571 | 036909C-JVD-TRN-00571 | IFR | 2019-01-11 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00571
036909C-1000-MR-0950-0001 | Material Requisition For API Mechanical Seals and Seal System | A | 2019-02-22 | IFQ | OL1-2C13-251000 | PL | 2019-03-01 | 036909C-JVD-TRN-00949 | 036909C-JVD-TRN-00949 | IFR | 2019-03-08 |  | Transmitted | TPSK-LSPA1-T-PL-00949 |  | 2019-03-01
036909C-1026-SP-0810-2610 | Mechanical Equipment Datasheet - C3 Hydrog Arsine Guard Bed | A | 2018-12-20 | IFQ | OL1-2M03-2610 | ME | 2018-12-27 | 036909C-JVD-TRN-00570 | 036909C-JVD-TRN-00570 | IFR | 2019-01-11 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00570
036909C-1000-MR-0232-0001 | Material Requisition For Complex Waste Water Treatment Package | A | 2019-02-15 | IFQ | OL1-2C13-702000 | PL | 2019-02-15 | 036909C-JVD-TRN-00862 | 036909C-JVD-TRN-00862 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-PL-00862 |  | 2019-02-15
036909C-1026-PDS-0500-2630 | Process Equipment Datasheet - 10-T-2630 - Secondary Deethanizer | B | 2018-10-12 | IFD | OL1-2G30-2630 | PE | 2018-10-12 | 036909C-JVD-TRN-00169 | 036909C-JVD-TRN-00169 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00169
036909C-1056-SP-0232-0002 | Mechanical Equipment Datasheet For Complex Waste Water Treatment Package | A | 2019-02-15 | IFQ | OL1-2M03-5644 | ME | 2019-02-15 | 036909C-JVD-TRN-00863 | 036909C-JVD-TRN-00863 | IFR | 2019-03-01 |  | Transmitted | TPSK-LSPA1-T-ME-00863 |  | 2019-02-15
036909C-1024-TDS-0610-2446 | Mechanical Equipment Data Sheet - 10-E-2446 - LP Depropanizer Feed Cooler | A | 2018-12-20 | IFQ | OL1-2M03-2446 | ME | 2018-12-27 | 036909C-JVD-TRN-00565 | 036909C-JVD-TRN-00565 | IFR | 2019-01-11 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00565
036909C-1000-MR-4111-0001 | Material Requisition for Hydrogen Production Unit | A | 2018-10-26 | IFQ | OL1-2M55-0114 | ME | 2018-11-06 | 036909C-JVD-TRN-00271 | 036909C-JVD-TRN-00271 | IFR | 2018-11-20 | 2019-02-07 | R1-No comments | TPSK-LSPA1-T-ME-00271
036909C-1023-PDS-4200-2301 | Process Equipment Datasheet - 10-X-2300 - Caustic Dilution Mixer | A | 2018-10-12 | IFR | OL1-2G30-2301 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00173
036909C-1056-PDS-0900-5616 | Process Equipment Datasheet - 10-P-5615 A-B - Olefins Stormwater Sump Pumps | A | 2018-12-28 | IFR | OL1-2G30-5616 | PE | 2019-01-03 | 036909C-JVD-TRN-00576 | 036909C-JVD-TRN-00576 | IFR | 2019-01-15 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00576
036909C-1056-PDS-0900-5649 | Process Equipment Datasheet - 10-P-5607 A-B - Flare KO Drum Oily Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5649 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00572
036909C-1056-PDS-0900-5648 | Process Equipment Datasheet - 10-P-5606 A-B - C3 Hydrog Area Oily Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5648 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572
036909C-1056-PDS-0900-5636 | Process Equipment Datasheet - 10-P-5631 A-B - CWWT Area Oily WWater Sump Pumps | A | 2018-12-26 | IFR | OL1-2G30-5636 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572
036909C-1056-PDS-0900-5635 | Process Equipment Datasheet - 10-P-5630 A-B - CT Area Oily WWater Sump Pumps | A | 2018-12-26 | IFR | OL1-2G30-5635 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572
036909C-1056-PDS-0900-5625 | Process Equipment Datasheet - 10-P-5628 A-B - East Gate House Septic Tank Pumps | A | 2018-12-26 | IFR | OL1-2G30-5625 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572
036909C-1056-PDS-0900-5624 | Process Equipment Datasheet - 10-P-5627 A-B - West Gate House Septic Tank Pumps | A | 2018-12-26 | IFR | OL1-2G30-5624 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572
036909C-1056-PDS-0900-5623 | Process Equipment Datasheet - 10-P-5626 A-B - Gate House Septic Tank Pumps | A | 2018-12-26 | IFR | OL1-2G30-5623 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572
036909C-1056-PDS-0900-5614 | Process Equipment Datasheet - 10-P-5605 A-B - Furnace Area Oily Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5614 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572
036909C-1056-PDS-0900-5613 | Process Equipment Datasheet - 10-P-5604 A-B - Refrig Area Oily Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5613 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572
036909C-1056-PDS-0900-5609 | Process Equipment Datasheet - 10-P-5603 A-B - CGC Area Oily Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5609 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572
036909C-1056-PDS-0900-5608 | Process Equipment Datasheet - 10-P-5602 A-B - QW Area Oily Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5608 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572
036909C-1056-PDS-0900-5607 | Process Equipment Datasheet - 10-P-5601 A-B - Butadiene Area Oily Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5607 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572
036909C-1059-PDS-0900-5951 | Process Equipment Datasheet - 10-P-5950 A-B - Sodium Hypochlorite Metering Pumps | A | 2018-12-21 | IFR | OL1-2G30-5951 | PE | 2018-12-27 | 036909C-JVD-TRN-00569 | 036909C-JVD-TRN-00569 | IFR | 2019-01-11 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00569
036909C-1059-PDS-0900-5902 | Process Equipment Datasheet - 10-P-5901 A-B - Sulfuric Acid Metering Pumps | A | 2018-12-21 | IFR | OL1-2G30-5902 | PE | 2018-12-27 | 036909C-JVD-TRN-00569 | 036909C-JVD-TRN-00569 | IFR | 2019-01-11 | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00569
036909C-1055-PDS-0900-5551 | Process Equipment Datasheet - 10-P-5550 A-B - HP Flare Knock-Out Pumps | A | 2018-12-21 | IFR | OL1-2G30-5551 | PE | 2018-12-27 | 036909C-JVD-TRN-00569 | 036909C-JVD-TRN-00569 | IFR | 2019-01-11 | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00569
036909C-1025-PDS-0900-2577 | Process Equipment Datasheet - 10-P-2575 A-B - Deethanizer Reboiler Cond Pumps | B | 2018-12-21 | IFD | OL1-2G30-2577 | PE | 2018-12-27 | 036909C-JVD-TRN-00568 | 036909C-JVD-TRN-00568 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00568
036909C-1024-PDS-0900-2457 | Process Equipment Datasheet - 10-P-2455 A-B - LP Deprop Reboiler Cond Pump | B | 2018-12-21 | IFD | OL1-2G30-2457 | PE | 2018-12-27 | 036909C-JVD-TRN-00568 | 036909C-JVD-TRN-00568 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00568
036909C-1024-PDS-0900-2443 | Process Equipment Datasheet - 10-P-2445 A-B - HP Deprop Reboiler Cond Pump | B | 2018-12-21 | IFD | OL1-2G30-2443 | PE | 2018-12-27 | 036909C-JVD-TRN-00568 | 036909C-JVD-TRN-00568 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00568
036909C-1023-PDS-4200-2315 | Process Equipment Datasheet - 10-X-2310 - Spent Caustic Mixer | A | 2018-10-12 | IFR | OL1-2G30-2315 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00173
036909C-1029-PDS-2500-2910 | Process Equipment Datasheet - 10-TK-2910 - Wash Oil Day Tank | A | 2018-12-20 | IFR | OL1-2G30-2910 | PE | 2018-12-27 | 036909C-JVD-TRN-00561 | 036909C-JVD-TRN-00561 | IFR | 2019-01-11 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-00561
036909C-1029-PDS-2600-2922 | Process Equipment Datasheet - 10-PK-2922 - Co Injection Pkg | A | 2018-12-20 | IFR | OL1-2G30-2922 | PE | 2018-12-20 | 036909C-JVD-TRN-00560 | 036909C-JVD-TRN-00560 | IFR | 2019-01-03 | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00560
036909C-1023-PDS-4200-2313 | Process Equipment Datasheet - 10-X-2312 - Spent Wash Oil Mixer | A | 2018-10-12 | IFR | OL1-2G30-2313 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00173
036909C-1023-PDS-0900-2306 | Process Equipment Datasheet - 10-P-2306 A-B - Weak Caustic Circulating Pumps | A | 2018-10-12 | IFR | OL1-2G30-2306 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00174
036909C-1023-PDS-4200-2308 | Process Equipment Datasheet - 10-X-2306 - Weak Caustic - Wash Oil Mixer | A | 2018-10-12 | IFR | OL1-2G30-2308 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00173
036909C-1025-PDS-0500-2520 | Process Equipment Datasheet - 10-T-2520 and 10-D-2520 - Residue Gas Rectifier & Reflux Drum | A | 2018-10-12 | IFR | OL1-2G30-2520 | PE | 2018-10-15 | 036909C-JVD-TRN-00172 | 036909C-JVD-TRN-00172 | IFR | 2018-10-29 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00172
036909C-1026-PDS-0500-2660 | Process Equipment Datasheet - 10-T-2660 - Debutanizer | B | 2018-10-12 | IFD | OL1-2G30-2660 | PE | 2018-10-12 | 036909C-JVD-TRN-00169 | 036909C-JVD-TRN-00169 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00169
036909C-1000-MR-0184-0001 | MR for HP / Polyolefins Flare Package | A | 2019-01-15 | IFQ | OL1-2C13-708000 | PL | 2019-01-17 | 036909C-JVD-TRN-00665 | 036909C-JVD-TRN-00665 | IFR | 2019-01-30 |  | Transmitted | TPSK-LSPA1-T-PL-00665
036909C-1000-SP-1130-0001 | Particular Technical Specification For Residue Gas Expander/Recompressor | A | 2018-10-05 | IFQ | OL1-2M57-0012 | ME | 2018-10-09 | 036909C-JVD-TRN-00139 | 036909C-JVD-TRN-00139 | IFR | 2018-10-22 | 2018-10-26 | Transmitted | TPSK-LSPA1-T-ME-00139 |  | 2018-10-07
036909C-1000-JSD-1600-003 | General Design Rule for Package Equipment Electrical System - Ex Client code OL1-2R05-0042 | B | 2018-09-20 | IFR | OL1-2E04-6000 | EE | 2018-10-04 | 036909C-JVD-TRN-00126 | 036909C-JVD-TRN-00126, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-10-18 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-EE-00126 | Ex Document Client Reference OL1-2R05-0042 | 2018-10-04
036909C-1000-SP-1011-0001 | Particular Technical Specification For Centrifugal Compressors Steam Turbine Driven | A | 2018-10-04 | IFQ | OL1-2M57-0008 | ME | 2018-10-08 | 036909C-JVD-TRN-00136 | 036909C-JVD-TRN-00136 | IFR | 2018-10-22 | 2018-10-26 | Transmitted | TPSK-LSPA1-T-ME-00136 |  | 2018-10-08
036909C-1000-MS-1320-0051 | Construction Specification For Piping Prefabrication Erection And Non Destructive Examination | A | 2019-02-21 | IFR | OL1-2P92-0007 | MP | 2019-02-26 | 036909C-JVD-TRN-00917 | 036909C-JVD-TRN-00917 | IFR | 2019-03-12 |  | Transmitted | TPSK-LSPA1-T-MP-00917 |  | 2019-02-26
036909C-1056-PDS-0900-5606 | Process Equipment Datasheet - 10-P-5600 A-B - Pygas Area Only Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5606 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00572
036909C-1025-PDS-0800-2574 | Process Equipment Datasheet - 10-D-2575 - Deethanizer Reboiler Cond Pot | B | 2018-12-21 | IFD | OL1-2G30-2574 | PE | 2018-12-27 | 036909C-JVD-TRN-00563 | 036909C-JVD-TRN-00563 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00563
036909C-1024-PDS-0800-2456 | Process Equipment Datasheet - 10-D-2455 - LP Deprop Reboiler Cond Pot | B | 2018-12-21 | IFD | OL1-2G30-2456 | PE | 2018-12-27 | 036909C-JVD-TRN-00563 | 036909C-JVD-TRN-00563 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00563
036909C-1024-PDS-0800-2444 | Process Equipment Datasheet - 10-D-2445 - HP Deprop Reboiler Cond Pot | B | 2018-12-21 | IFD | OL1-2G30-2444 | PE | 2018-12-27 | 036909C-JVD-TRN-00563 | 036909C-JVD-TRN-00563 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00563
036909C-1000-STC-1890-080 | Construction Standards For Ladders & Platforms Attached To Pressure Equipment | 0 | 2018-10-01 | IMP | OL1-2R03-0055 | ME | 2018-10-04 | 036909C-JVD-TRN-00120 | 036909C-JVD-TRN-00120, ROC-TPSK-CECO-T-00004 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00120 |  | 2018-10-04
036909C-1055-PDS-0600-5513 | Process Equipment Datasheet - 10-E-5513 - Methanol Vaporizer | A | 2018-12-28 | IFR | OL1-2G30-5513 | PE | 2019-01-03 | 036909C-JVD-TRN-00575 | 036909C-JVD-TRN-00575 | IFR | 2019-01-15 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00575
036909C-1055-PDS-0600-5512 | Process Equipment Datasheet - 10-E-5512 - Cold Flare Superheater | A | 2018-12-28 | IFR | OL1-2G30-5512 | PE | 2019-01-03 | 036909C-JVD-TRN-00575 | 036909C-JVD-TRN-00575 | IFR | 2019-01-15 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00575
036909C-1055-PDS-0600-5511 | Process Equipment Datasheet - 10-E-5510 - Cold Flare Blowdown Vaporizer | A | 2018-12-28 | IFR | OL1-2G30-5511 | PE | 2019-01-03 | 036909C-JVD-TRN-00575 | 036909C-JVD-TRN-00575 | IFR | 2019-01-15 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00575
036909C-1000-JSD-1580-0003 | General Design Rules For Instrumentation And Control Of Packaged Equipment | 0 | 2018-11-29 | IMP | OL1-2R06-0035 | IE | 2018-11-29 | 036909C-JVD-TRN-00393 | 036909C-JVD-TRN-00393, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-14 | 2018-12-13 | Transmitted | TPSK-LSPA1-T-IE-00393
036909C-1029-PID-0021-2965 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C3R Compressor Lube Oil Pump Turbine Details | A | 2019-01-30 | IFR | OL1-2G43-2965 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2960 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C3R Refrig Compressor Turbine Details - Sheet 2 | A | 2019-01-30 | IFR | OL1-2G43-2960 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2975 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C2R Compressor Auxiliaries Details - Sheet 2 | A | 2019-01-30 | IFR | OL1-2G43-2975 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2970 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C2R Compressor Auxiliaries - Sheet 1 | A | 2019-01-30 | IFR | OL1-2G43-2970 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2903 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Process Water Stripping Chemical Injection Pkg | A | 2019-01-30 | IFR | OL1-2G43-2903 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2955 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C3 Refrig Compressor Turbine Details - Sheet 1 | A | 2019-01-30 | IFR | OL1-2G43-2955 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2901 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - pH Control - Corrosion Injection System | A | 2019-01-30 | IFR | OL1-2G43-2901 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2907 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Caustic Tower Anti Foulant Injection System | A | 2019-01-30 | IFR | OL1-2G43-2907 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2906 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C4 Polymer Inhibitor Injection Package | A | 2019-01-30 | IFR | OL1-2G43-2906 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1029-PID-0021-2905 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Polymerization Inhibitor Injection | A | 2019-01-30 | IFR | OL1-2G43-2905 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799
036909C-1056-PDS-0900-5621 | Process Equipment Datasheet - 10-P-5621 - Olefins Holding Basin Skimmed Oil Pump | A | 2018-12-28 | IFR | OL1-2G30-5621 | PE | 2019-01-03 | 036909C-JVD-TRN-00576 | 036909C-JVD-TRN-00576 | IFR | 2019-01-15 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00576
036909C-1055-PDS-0900-5501 | Process Equipment Datasheet - 10-P-5500 A-B - Hot Blowdown Pumps | A | 2018-12-21 | IFR | OL1-2G30-5501 | PE | 2018-12-27 | 036909C-JVD-TRN-00569 | 036909C-JVD-TRN-00569 | IFR | 2019-01-11 | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00569
036909C-1055-PDS-0800-5500 | Process Equipment Datasheet - 10-D-5500 - Hot Flare Drum | A | 2018-10-12 | IFR | OL1-2G30-5500 | PE | 2018-10-12 | 036909C-JVD-TRN-00168 | 036909C-JVD-TRN-00168 | IFR | 2018-10-26 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00168
036909C-1056-PDS-0900-5637 | Process Equipment Datasheet - 10-P-5632 A-B - HP Flare Area Oily WW Sump Pumps | A | 2018-12-28 | IFR | OL1-2G30-5637 | PE | 2019-01-03 | 036909C-JVD-TRN-00576 | 036909C-JVD-TRN-00576 | IFR | 2019-01-15 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00576
036909C-1056-PDS-0900-5638 | Process Equipment Datasheet - 10-P-5633 A-B - HP Flare Area SW Sump Pumps | A | 2018-12-28 | IFR | OL1-2G30-5638 | PE | 2019-01-03 | 036909C-JVD-TRN-00576 | 036909C-JVD-TRN-00576 | IFR | 2019-01-15 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00576