## Document
Document Reference | Document Client Reference | Document Title | Revision Number | Document Revision Object | Client Transmittal Ref Number | Transmittal Date | Document Status | Actual Response Date | Response Due Date | Revision Date | Required Action | Current/History | Document Origin | Discipline | Document Class
036909C-1000-PP-102 | OL1-2W92-0001 | Coordination Procedure | A | IFR | TPSK-LSPA1-T-PM-00001 | 2018-07-30 | R2-Comments as noted | 2018-08-22 | 2018-08-10 | 2018-07-26 | IFR | C | ROC | PC | 2
036909C-1000-PP-106 | OL1-2R07-0001 | Tagging Procedure | A | IFR | TPSK-LSPA1-T-PM-00001 | 2018-07-30 | A4 - Not approve | 2018-08-22 | 2018-08-10 | 2018-07-26 | IFR | H | ROC | ME | 2
036909C-1000-PP-107 | OL1-2W92-0003 | Project Document Coding | A | IFR | TPSK-LSPA1-T-PM-00001 | 2018-07-30 | A4 - Not approve | 2018-08-22 | 2018-08-10 | 2018-07-26 | IFR | H | ROC | PM | 2
036909C-1000-DI-0007-0001 | OL1-2G02-0001 | Process Design Basis | A | IFA | TPSK-LSPA1-T-PE-00002 | 2018-07-30 | A3-Not Approve Re-Submit For Re-Approval | 2018-08-17 | 2018-08-10 | 2018-07-20 | IFA | C | ROC | PE | 1
036909C-1000-DI-0007-0002 | OL1-2G02-0002 | Equipment Basis Of Design | A | IFA | TPSK-LSPA1-T-PE-00002 | 2018-07-30 | A3-Not Approve Re-Submit For Re-Approval | 2018-08-17 | 2018-08-10 | 2018-07-24 | IFA | C | ROC | PE | 1
036909C-1050-DI-0007-5001 | OL1-2G05-5001 | Area Basis of Design - 50 ISBL Supporting Utilities | A | IFA | TPSK-LSPA1-T-PE-00003 | 2018-07-31 | A3-Not Approve Re-Submit For Re-Approval | 2018-08-17 | 2018-08-13 | 2018-07-25 | IFA | C | HOC | PE | 1
036909C-1053-DI-0007-5301 | OL1-2G05-5301 | Area Basis of Design - 53 Cooling Tower System | A | IFA | TPSK-LSPA1-T-PE-00003 | 2018-07-31 | A3-Not Approve Re-Submit For Re-Approval | 2018-08-17 | 2018-08-13 | 2018-07-25 | IFA | H | HOC | PE | 1
036909C-1000-DI-0007-0006 | OL1-2G02-0006 | Furnace Process Basis of Design | A | IFA | TPSK-LSPA1-T-PE-00004 | 2018-07-31 | A3-Not Approve Re-Submit For Re-Approval | 2018-08-17 | 2018-08-13 | 2018-07-26 | IFA | C | HOC | PE | 1
036909C-LSPA1-TPSK-MOM-0001 | LSPA1-TPSK-M-0001 | LNTP Works Kick Off Meeting - General & Coordination | 0 | IFI | TPSK-LSPA1-T-PM-00005 | 2018-07-31 | Transmitted |  |  | 2018-07-13 | IFI | C | ROC | PM | 3
036909C-LSPA1-TPSK-MOM-0002 | LSPA1-TPSK-M-0002 | LNTP Works Kick Off Meeting - FURNACE ISLAND | 0 | IFI | TPSK-LSPA1-T-PM-00005 | 2018-07-31 | Transmitted |  |  | 2018-07-12 | IFI | C | ROC | PM | 3
036909C-LSPA1-TPSK-MOM-0003 | LSPA1-TPSK-M-0003 | Package A1 Kick Off Meeting | 0 | IFI | TPSK-LSPA1-T-PM-00005 | 2018-07-31 | Transmitted |  |  | 2018-07-10 | IFI | C | ROC | PM | 3
036909C-1000-JSD-0000-03 | OL1-2G01-0001 | JSD for P&ID Preparation | A | IFA | TPSK-LSPA1-T-PE-00006 | 2018-07-31 | Transmitted | 2018-08-21 | 2018-08-13 | 2018-07-31 | IFR | C | ROC | PE | 2
036909C-LSPA1-TPSK-MOM-0004 | LSPA1-TPSK-M-0004 | Package A1 Kick Off Meeting | 0 | IFI | TPSK-LSPA1-T-PM-00007 | 2018-08-02 | Transmitted |  |  | 2018-02-08 | IFI | C | ROC | PM | 3
036909C-1000-JSD-1600-003 | OL1-2R05-0042 | General Design Rule For Package Equipment Electrical System | A | IFR | TPSK-LSPA1-T-EE-00008 | 2018-08-06 | A3-Approved with comments, re-submit for review. | 2018-08-24 | 2018-08-20 | 2018-08-03 | IFR | H | ROC | EE | 2
036909C-1000-JSD-1600-008 | OL1-2R05-0043 | General Design Rule For Smartplant Electrical | A | IFR | TPSK-LSPA1-T-EE-00008 | 2018-08-06 | A3-Approved with comments, re-submit for review. | 2018-08-24 | 2018-08-20 | 2018-08-03 | IFR | C | ROC | EE | 3
036909C-1000-PP-1600-001 | OL1-2R05-0044 | Coordination Procedure For Smartplant Electrical | A | IFR | TPSK-LSPA1-T-EE-00008 | 2018-08-06 | A3-Approved with comments, re-submit for review. | 2018-08-24 | 2018-08-20 | 2018-08-03 | IFR | C | ROC | EE | 3
036909C-1000-PP-1600-003 | OL1-2R05-0045 | Coordination Procedure For ETAP | A | IFI | TPSK-LSPA1-T-EE-00008 | 2018-08-06 | A3-Approved with comments, re-submit for review. | 2018-08-24 | 2018-08-20 | 2018-08-03 | IFR | C | ROC | EE | 3
036909C-1000-NM-0001-1001 | OL1-2G44-1001 | Overall Material Balance | A | IFI | TPSK-LSPA1-T-PE-00009 | 2018-08-06 | R2-Comments as noted | 2018-08-23 |  | 2018-08-03 | IFI | C | HOC | PE | 3
036909C-1000-PP-100 | OL1-2W92-0006 | TPSK Project Directorate Organization Chart | 0 | IFI | TPSK-LSPA1-T-PC-00010 | 2018-08-06 | Transmitted |  |  | 2018-08-06 | IFI | C | JVD | PC | 3
036909C-1000-PP-308 |  | Personnel assignment authorization form and time sheet preparation procedure for tpsk directorate | 0 | IMP | 036909C-JVD-TRN-INTERNAL-00001 | 2018-08-07 | Transmitted |  |  | 2018-08-07 | IFI | C | ROC | PC | Internal Doc
036909C-1056-DI-0007-5601 | OL1-2G05-5601 | Area Basis of Design - 56 Waste Water Treatment System | A | IFA | TPSK-LSPA1-T-PE-00011 | 2018-08-07 | A3-Approved with comments, re-submit for review. | 2018-08-27 | 2018-08-21 | 2018-08-03 | IFA | H | HOC | PE | 1
036909C-1010-DI-0007-1001 | OL1-2G05-1001 | Area Basis of Design - 10 Feed Preparation | A | IFA | TPSK-LSPA1-T-PE-00011 | 2018-08-07 | A3-Approved with comments, re-submit for review. | 2018-08-27 | 2018-08-21 | 2018-08-06 | IFA | C | HOC | PE | 1
036909C-1020-DI-0007-2001 | OL1-2G05-2001 | Area Basis of Design - 20-21 Quench and Dilution Steam | A | IFA | TPSK-LSPA1-T-PE-00011 | 2018-08-07 | A3-Approved with comments, re-submit for review. | 2018-08-27 | 2018-08-21 | 2018-08-06 | IFA | C | HOC | PE | 1
036909C-1025-DI-0007-2501 | OL1-2G05-2501 | Area Basis of Design - 25 Cold Fractionation | A | IFA | TPSK-LSPA1-T-PE-00011 | 2018-08-07 | A3-Approved with comments, re-submit for review. | 2018-08-27 | 2018-08-21 | 2018-08-06 | IFA | C | HOC | PE | 1
036909C-1000-STD-1380-0001 | OL1-2P92-0002 | Piping Design Standard Drawings | A | IFR | TPSK-LSPA1-T-MP-00012 | 2018-08-08 | A4-Not Approved, re-submit for approval | 2018-09-26 | 2018-08-22 | 2018-08-07 | IFR | H | ROC | MP | 2
036909C-1000-STC-1390-0001 | OL1-2P92-0003 | Piping Construction Drawing | A | IFR | TPSK-LSPA1-T-MP-00012 | 2018-08-08 | A4-Not Approved, re-submit for approval | 2018-09-26 | 2018-08-22 | 2018-08-07 | IFR | H | ROC | MP | 2
036909C-1000-JSD-1300-0002 | OL1-2R04-0002 | Piping Design Specification | A | IFR | TPSK-LSPA1-T-MP-00012 | 2018-08-08 | A4-Not Approved, re-submit for approval | 2018-09-26 | 2018-08-22 | 2018-08-07 | IFR | H | ROC | MP | 2
036909C-1000-JSD-1300-0003 | OL1-2R04-0031 | Job Design Specification For Steam Tracing | A | IFR | TPSK-LSPA1-T-MP-00012 | 2018-08-08 | A4-Not Approved, re-submit for approval | 2018-09-26 | 2018-08-22 | 2018-08-07 | IFR | H | ROC | MP | 2
036909C-1000-PP-110 | OL1-2W92-0004 | Document management procedure | A | IFR | TPSK-LSPA1-T-PC-00013 | 2018-08-08 | R2-Comments as noted | 2018-08-29 | 2018-08-22 | 2018-08-08 | IFR | C | ROC | PC | 2
036909C-1000-PP-130 |  | Travel procedure | 0 | IMP | 036909C-JVD-TRN-INTERNAL-00002 | 2018-08-08 | Transmitted |  |  | 2018-08-08 | IMP | C | ROC | PC | Internal Doc
036909C-1023-DI-0007-2301 | OL1-2G05-2301 | Area Basis of Design - 23 Caustic and Spent Caustic Pretreatment | A | IFA | TPSK-LSPA1-T-PE-00014 | 2018-08-08 | A3-Approved with comments, re-submit for review. | 2018-08-31 | 2018-08-22 | 2018-08-08 | IFA | C | HOC | PE | 1
036909C-1026-DI-0007-2601 | OL1-2G05-2601 | Area Basis of Design - 26 Hot Fractionation | A | IFA | TPSK-LSPA1-T-PE-00014 | 2018-08-08 | A3-Approved with comments, re-submit for review. | 2018-08-31 | 2018-08-22 | 2018-08-07 | IFA | C | HOC | PE | 1
036909C-1000-PLG-103 | OL1-2W01-0002 | Work Breakdown Structure | A | IFR | TPSK-LSPA1-T-PC-00015 | 2018-08-09 | A4 - Not approve | 2018-08-17 | 2018-08-23 | 2018-07-30 | IFR | H | ROC | PC | 2
036909C-1000-JSS-1820-01 | OL1-2R03-0053 | Job Specification For Supply Of Equipment Ladders And Platforms | A | IFR | TPSK-LSPA1-T-ME-00017 | 2018-08-10 | A4-Not Approved, re-submit for approval | 2018-08-27 | 2018-08-24 | 2018-08-09 | IFR | H | ROC | ME | 2
036909C-1000-JSD-0400-01 | OL1-2R03-0050 | Job Specification For Design Of Pressure & Atmospheric Static Equipment | A | IFR | TPSK-LSPA1-T-ME-00017 | 2018-08-10 | A3-Approved with comments, re-submit for review. | 2018-08-27 | 2018-08-24 | 2018-08-09 | IFR | H | ROC | ME | 2
036909C-1000-JSS-0570-01 | OL1-2R03-0052 | Job Specification For Supply Of Column Internals | A | IFR | TPSK-LSPA1-T-ME-00017 | 2018-08-10 | A3-Approved with comments, re-submit for review. | 2018-08-27 | 2018-08-24 | 2018-08-09 | IFR | H | ROC | ME | 2
036909C-1055-DI-0007-5501 | OL1-2G05-5501 | Area Basis of Design - 55 Flare System | A | IFA | TPSK-LSPA1-T-PE-00016 | 2018-08-09 | A3-Not Approve Re-Submit For Re-Approval | 2018-08-29 | 2018-08-23 | 2018-08-09 | IFA | C | HOC | PE | 1
036909C-1000-STC-0490-000 | OL1-2R03-0054 | Construction Standards For Pressure Equipment | A | IFR | TPSK-LSPA1-T-ME-00018 | 2018-08-10 | A3-Approved with comments, re-submit for review. | 2018-08-27 | 2018-08-24 | 2018-08-10 | IFR | H | ROC | ME | 2
036909C-1000-PLG-102 | OL1-2W01-0001 | Plant and section codes | A | IFR | TPSK-LSPA1-T-PC-00019 | 2018-08-10 | A2-Approved with comments, re-submit is not required. | 2018-08-22 | 2018-08-24 | 2018-08-10 | IFR | H | ROC | PM | 2
036909C-1000-RT-200 | OL1-2W90-0001 | Firefighting basic design report for package A1 | 0 | IFI | TPSK-LSPA1-T-PC-00020 | 2018-08-10 | R2-Comments as noted | 2018-08-20 |  | 2018-08-10 | IFI | H | ROC | PM | 3
036909C-1000-JSS-0400-01 | OL1-2R03-0051 | Job Specification for Supply of Pressure Vessels | A | IFR | TPSK-LSPA1-T-ME-00021 | 2018-08-13 | A4-Not Approved, re-submit for approval | 2018-08-27 | 2018-08-27 | 2018-08-10 | IFR | H | ROC | ME | 2
036909C-1022-DI-0007-2201 | OL1-2G05-2201 | Area Basis of Design - 22-24 Compresssion Train | A | IFA | TPSK-LSPA1-T-PE-00022 | 2018-08-13 | A3-Approved with comments, re-submit for review. | 2018-09-05 | 2018-08-27 | 2018-08-09 | IFA | C | HOC | PE | 1
036909C-1028-DI-0007-2801 | OL1-2G05-2801 | Area Basis of Design - 28 Refrigeration | A | IFA | TPSK-LSPA1-T-PE-00022 | 2018-08-13 | A1-Approved without comments | 2018-09-05 | 2018-08-27 | 2018-08-09 | IFA | C | HOC | PE | 1
036909C-1000-PP-401 | OL1-2X01-0001 | Payment And Invoicing Procedure | 0 | IFR | TPSK-LSPA1-T-PC-00023 | 2018-08-17 | Transmitted |  | 2018-08-30 | 2018-08-15 | IFR | C | ROC | PC | 2
036909C-1000-JSD-2200-01 | OL1-2R04-0003 | Job design specification for thermal insulation (hot service) | A | IFR | TPSK-LSPA1-T-MP-00024 | 2018-08-22 | A4-Not Approved, re-submit for approval | 2018-09-12 | 2018-09-05 | 2018-08-22 | IFR | C | ROC | MP | 2
036909C-1000-JSD-2200-02 | OL1-2R04-0004 | Job Design Specification For Thermal Insulation (Cold Service) | A | IFR | TPSK-LSPA1-T-MP-00024 | 2018-08-22 | A4-Not Approved, re-submit for approval | 2018-09-12 | 2018-09-05 | 2018-08-22 | IFR | C | ROC | MP | 2
036909C-1000-JSD-2300-01 | OL1-2R04-0005 | Job Design Specification For Painting | A | IFR | TPSK-LSPA1-T-MP-00024 | 2018-08-22 | A4-Not Approved, re-submit for approval | 2018-09-12 | 2018-09-05 | 2018-08-22 | IFR | C | ROC | MP | 2
036909C-1022-PDS-1000-2200 | OL1-2G30-2200 | Process Equipment Data Sheet - 10-C-2200 - Cracked Gas Compressor | A | IFA | TPSK-LSPA1-T-PE-00025 | 2018-08-22 | A3-Approved with comments, re-submit for review. | 2018-09-11 | 2018-09-05 | 2018-08-22 | IFA | H | HOC | PE | 1
036909C-1028-PDS-1000-2800 | OL1-2G30-2800 | Process Equipment Data Sheet - 10-C-2800 - Propylene Refrig Compressor | A | IFA | TPSK-LSPA1-T-PE-00025 | 2018-08-22 | A3-Approved with comments, re-submit for review. | 2018-09-11 | 2018-09-05 | 2018-08-22 | IFA | H | HOC | PE | 1
036909C-1028-PDS-1000-2850 | OL1-2G30-2850 | Process Equipment Data Sheet - 10-C-2850 - Ethylene Refrig Compressor | A | IFA | TPSK-LSPA1-T-PE-00025 | 2018-08-22 | A3-Approved with comments, re-submit for review. | 2018-09-11 | 2018-09-05 | 2018-08-22 | IFA | H | HOC | PE | 1
036909C-1000-JSD-0600-0001 |  | Basis of Design for Heat Exchangers | A | IFI | 036909C-JVD-TRN-INTERNAL-00004 | 2018-08-22 | Transmitted |  |  | 2018-08-21 | IFI | H | HOC | PE
036909C-1000-JSS-1300-01 | OL1-2R04-0006 | General Supply Specification For Piping Material | A | IFR | TPSK-LSPA1-T-MP-00028 | 2018-08-27 | R2-Comments as noted | 2018-09-18 | 2018-09-10 | 2018-08-22 | IFR | C | ROC | MP | 2
036909C-1000-JSS-1320-01 | OL1-2R04-0011 | Job Supply Specification For Pipes | A | IFR | TPSK-LSPA1-T-MP-00028 | 2018-08-27 | R2-Comments as noted | 2018-09-18 | 2018-09-10 | 2018-08-22 | IFR | C | ROC | MP | 2
036909C-1000-JSS-1330-01 | OL1-2R04-0013 | Job Supply Specification For Butt Welding Fittings | A | IFR | TPSK-LSPA1-T-MP-00028 | 2018-08-27 | A4-Not Approved, re-submit for approval | 2018-09-18 | 2018-09-10 | 2018-08-22 | IFR | C | ROC | MP | 2
036909C-1000-JSS-1340-01 | OL1-2R04-0014 | Job Supply Specification For Forged Fittings | A | IFR | TPSK-LSPA1-T-MP-00028 | 2018-08-27 | A4-Not Approved, re-submit for approval | 2018-09-18 | 2018-09-10 | 2018-08-22 | IFR | C | ROC | MP | 2
036909C-1000-PFD-0010-0010 | OL1-2G40-0010 | Block Flow Diagram - Olefins Unit 10 - 00-General - Overall Plant Scheme | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1000-PFD-0010-0001 | OL1-2G41-0001 | Process Flow Diagram - Olefins Unit 10 - 00-General - Legend & Symbols | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1000-PFD-0010-0002 | OL1-2G41-0002 | Process Flow Diagram - Olefins Unit 10 - 00-General - Drawing Index | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1010-PFD-0010-1001 | OL1-2G41-1001 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1010-PFD-0010-1003 | OL1-2G41-1003 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1011-PFD-0010-1101 | OL1-2G41-1101 | Process Flow Diagram - Olefins Unit 10 - 11 - Furnaces - Recycle Gas Cracking Furnace | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1012-PFD-0010-1201 | OL1-2G41-1201 | Process Flow Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1019-PFD-0010-1901 | OL1-2G41-1901 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1019-PFD-0010-1902 | OL1-2G41-1902 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1020-PFD-0010-2001 | OL1-2G41-2001 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1020-PFD-0010-2002 | OL1-2G41-2002 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1021-PFD-0010-2101 | OL1-2G41-2101 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1021-PFD-0010-2102 | OL1-2G41-2102 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1021-PFD-0010-2103 | OL1-2G41-2103 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1022-PFD-0010-2201 | OL1-2G41-2201 | Process Flow Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1023-PFD-0010-2301 | OL1-2G41-2301 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1023-PFD-0010-2302 | OL1-2G41-2302 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1023-PFD-0010-2303 | OL1-2G41-2303 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1023-PFD-0010-2304 | OL1-2G41-2304 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1023-PFD-0010-2305 | OL1-2G41-2305 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1024-PFD-0010-2401 | OL1-2G41-2401 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1024-PFD-0010-2402 | OL1-2G41-2402 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1024-PFD-0010-2403 | OL1-2G41-2403 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1024-PFD-0010-2404 | OL1-2G41-2404 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1024-PFD-0010-2405 | OL1-2G41-2405 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1025-PFD-0010-2501 | OL1-2G41-2501 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1025-PFD-0010-2502 | OL1-2G41-2502 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1025-PFD-0010-2503 | OL1-2G41-2503 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1025-PFD-0010-2504 | OL1-2G41-2504 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1025-PFD-0010-2505 | OL1-2G41-2505 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1025-PFD-0010-2506 | OL1-2G41-2506 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1026-PFD-0010-2601 | OL1-2G41-2601 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1026-PFD-0010-2602 | OL1-2G41-2602 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1026-PFD-0010-2603 | OL1-2G41-2603 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1026-PFD-0010-2604 | OL1-2G41-2604 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1027-PFD-0010-2701 | OL1-2G41-2701 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Reactor & Depentanizer | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1027-PFD-0010-2702 | OL1-2G41-2702 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Rerun Tower | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1027-PFD-0010-2703 | OL1-2G41-2703 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - Hydrog Reactivation Gas System | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1027-PFD-0010-2704 | OL1-2G41-2704 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1028-PFD-0010-2801 | OL1-2G41-2801 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1028-PFD-0010-2802 | OL1-2G41-2802 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1028-PFD-0010-2803 | OL1-2G41-2803 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1028-PFD-0010-2804 | OL1-2G41-2804 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1029-PFD-0010-2901 | OL1-2G41-2901 | Process Flow Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1030-PFD-0010-3001 | OL1-2G41-3001 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1030-PFD-0010-3002 | OL1-2G41-3002 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Evaporation | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1030-PFD-0010-3003 | OL1-2G41-3003 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1030-PFD-0010-3004 | OL1-2G41-3004 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1030-PFD-0010-3005 | OL1-2G41-3005 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1031-PFD-0010-3101 | OL1-2G41-3101 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1031-PFD-0010-3102 | OL1-2G41-3102 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam And Condensate System | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1039-PFD-0010-3901 | OL1-2G41-3901 | Process Flow Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1050-PFD-0030-5001 | OL1-2G42-5001 | Utility Flow Diagram - Olefins Unit 10 - 50 - Water System - Treated Potable And Demin Water Systems | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1051-PFD-0030-5101 | OL1-2G42-5101 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Steam Balance Diagram | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1051-PFD-0030-5102 | OL1-2G42-5102 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate And Boiler Feedwater Systems | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1051-PFD-0030-5103 | OL1-2G42-5103 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate Treatment System | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1051-PFD-0030-5104 | OL1-2G42-5104 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Furnace Blowdown System | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1052-PFD-0030-5201 | OL1-2G42-5201 | Utility Flow Diagram - Olefins Unit 10 - 52 - Fuel System - Fuel Gas System | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1053-PFD-0030-5301 | OL1-2G42-5301 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Water Diagram | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1053-PFD-0030-5311 | OL1-2G42-5311 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Tower | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1054-PFD-0030-5401 | OL1-2G42-5401 | Utility Flow Diagram - Olefins Unit 10 - 54 - Air and Nitrogen System - Plant Air Instrument Air And Nitrogen Systems | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1055-PFD-0030-5501 | OL1-2G42-5501 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Flare And Blowdown System | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1055-PFD-0030-5502 | OL1-2G42-5502 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Process Vent Gas Collection | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1055-PFD-0030-5511 | OL1-2G42-5511 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - HP - LLDPE LP Flare | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1055-PFD-0030-5512 | OL1-2G42-5512 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Enclosed Ground Flare | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5601 | OL1-2G42-5601 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Collection | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5602 | OL1-2G42-5602 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Surface Runoff Collection | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5603 | OL1-2G42-5603 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Cracker Holding Basin | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5604 | OL1-2G42-5604 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Domestic Wastewater Collection | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5610 | OL1-2G42-5610 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - HP Flare Area SW & Oily WW Collection | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5611 | OL1-2G42-5611 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - OSBL Oily Wastewater Collection | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5612 | OL1-2G42-5612 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Equalization Tank | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5613 | OL1-2G42-5613 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - CPI & IGF Packages | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5614 | OL1-2G42-5614 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Biotreatment Package | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5615 | OL1-2G42-5615 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Check Basin | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5616 | OL1-2G42-5616 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Sludge Dewatering Package | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5617 | OL1-2G42-5617 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Slop & Oil Sludge | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1059-PFD-0030-5901 | OL1-2G42-5901 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Chemical Storage | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1059-PFD-0030-5911 | OL1-2G42-5911 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Complex U & O Chemical Storage | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1000-JSS-1350-01 | OL1-2R04-0015 | Job Supply Specification For Flanges | A | IFR | TPSK-LSPA1-T-MP-00028 | 2018-08-27 | A4-Not Approved, re-submit for approval | 2018-09-18 | 2018-09-10 | 2018-08-24 | IFR | C | ROC | MP | 2
036909C-1000-JSS-6300-02 | OL1-2R03-0001 | Jo b Specification For Weldings and NDE Of Pressure Vessels And Heat Exchangers | A | IFR | TPSK-LSPA1-T-ME-00029 | 2018-08-27 | A4-Not Approved, re-submit for approval | 2018-09-19 | 2018-09-10 | 2018-08-24 | IFR | C | ROC | MP | 2
036909C-1000-JSS-6300-03 | OL1-2R03-0002 | Job Specification For Materials In Sour Services | A | IFR | TPSK-LSPA1-T-ME-00029 | 2018-08-27 | R1-No comments | 2018-09-19 | 2018-09-10 | 2018-08-24 | IFR | C | ROC | MP | 2
036909C-1000-JSS-6300-04 | OL1-2R03-0003 | Job Specification For Supply Positive Alloy Material Identification Of Equipment And Piping | A | IFR | TPSK-LSPA1-T-ME-00029 | 2018-08-27 | R1-No comments | 2018-09-19 | 2018-09-10 | 2018-08-24 | IFR | C | ROC | MP | 2
036909C-1000-JSS-6300-05 | OL1-2R03-0004 | Job Specification For Welding And NDE Storage Tanks | A | IFR | TPSK-LSPA1-T-ME-00029 | 2018-08-27 | R1-No comments | 2018-09-19 | 2018-09-10 | 2018-08-24 | IFR | C | ROC | MP | 2
036909C-1000-STC-1890-080 | OL1-2R03-055 | Construction Standards For Ladders And Platforms Attached To Pressure Equipment | A | IFR | TPSK-LSPA1-T-ME-00027 | 2018-08-27 | R2-Comments as noted | 2018-09-18 | 2018-09-10 | 2018-08-23 | IFR | H | ROC | ME | 2
036909C-1000-PP-123 | OL1-2W92-0009 | Criticality Rating Procedure | A | IFR | TPSK-LSPA1-T-PC-00033 | 2018-09-05 | R2-Comments as noted | 2018-10-01 | 2018-09-19 | 2018-08-22 | IFR | C | ROC | PC | 2
036909C-1000-PP-131 | OL1-2W92-0007 | TPSK Roc Organization Chart | A | IFI | TPSK-LSPA1-T-PC-00030 | 2018-08-27 | Transmitted |  |  | 2018-08-24 | IFI | C | ROC | PC | 3
036909C-1000-PP-104 |  | Coordination Procedure Among TPSK TPGM TPIT SKEC and TPSW | 0 | IMP | 036909C-JVD-TRN-INTERNAL-00007 | 2018-09-20 | Transmitted |  |  | 2018-08-24 | IMP | C | ROC | PM | Internal Doc
036909C-1019-PDS-1000-1950 | OL1-2G30-1950 | Process Equipment Data Sheet - 10-PK-1950 - Decoke Air Compressor Package | A | IFA | TPSK-LSPA1-T-PE-00031 | 2018-08-29 | A3-Approved with comments, re-submit for review. | 2018-09-28 |  | 2018-08-29 | IFA | H | HOC | PE | 1
036909C-1025-PDS-1000-2550 | OL1-2G30-2550 | Process Equipment Data Sheet - 10-C-TX-2550 - Residue Gas Expander - Recompressor | A | IFA | TPSK-LSPA1-T-PE-00031 | 2018-08-29 | A3-Approved with comments, re-submit for review. | 2018-09-28 |  | 2018-08-29 | IFA | H | HOC | PE | 1
036909C-1000-NM-0001-1002 | OL1-2G44-1002 | Heat & Material Balance - Design Case 6 | A | IFI | TPSK-LSPA1-T-PE-00032 | 2018-08-31 | Transmitted |  |  | 2018-08-30 | IFI | C | HOC | PE | 3
036909C-1000-NM-0001-1003 | OL1-2G44-1003 | Heat & Material Balance - Design Case 8 | A | IFI | TPSK-LSPA1-T-PE-00032 | 2018-08-31 | Transmitted |  |  | 2018-08-30 | IFI | C | HOC | PE | 3
036909C-1000-NM-0001-1004 | OL1-2G44-1004 | Heat & Material Balance - Design Case 9 | A | IFI | TPSK-LSPA1-T-PE-00032 | 2018-08-31 | Transmitted |  |  | 2018-08-30 | IFI | C | HOC | PE | 3
036909C-1000-DI-0007-0003 | OL1-2G02-0003 | Flare and Blowdown System Design Basis | A | IFA | TPSK-LSPA1-T-PE-00034 | 2018-09-06 | R2-Comments as noted | 2018-09-28 | 2018-09-20 | 2018-09-06 | IFA | C | HOC | PE | 1
036909C-1000-PP-307 | OL1-2A92-0001 | Variation Order Procedure | A | IFR | TPSK-LSPA1-T-CO-00035 | 2018-09-10 | Transmitted |  | 2018-09-24 | 2018-09-05 | IFR | C | ROC | PC | 2
036909C-1000-PP-312 |  | Lumpsum & Reimbursable Services Invoicing Procedure | 0 | IMP | 036909C-JVD-TRN-INTERNAL-00006 | 2018-09-10 | Transmitted |  |  | 2018-09-05 | IMP | C | ROC | PC | Internal Doc
036909C-1021-PDS-0600-2101 | OL1-2G30-2101 | Process Equipment Data Sheet - 10-E-2100 - Quench Water Cooler | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-07 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2502 | OL1-2G30-2502 | Process Equipment Data Sheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-07 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2503 | OL1-2G30-2503 | Process Equipment Data Sheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-07 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2505 | OL1-2G30-2505 | Process Equipment Data Sheet - 10-E-2506 & 2508 - Demeth Prefrac Feed Cooler No 3 & No 4 | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2511 | OL1-2G30-2511 | Process Equipment Data Sheet - 10-E-2510 - Demeth Prefrac Condenser | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2521 | OL1-2G30-2521 | Process Equipment Data Sheet - 10-E-2520 - Rectifier Condenser | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2526 | OL1-2G30-2526 | Process Equipment Data Sheet - 10-E-2525 - Hydrogen Core Exchanger | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2531 | OL1-2G30-2531 | Process Equipment Data Sheet - 10-E-2530 - Demeth Feed Cooler | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2541 | OL1-2G30-2541 | Process Equipment Data Sheet - 10-E-2540 - Demethanizer Condenser | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2571 | OL1-2G30-2571 | Process Equipment Data Sheet - 10-E-2570 Deethanizer Condenser | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-24 | 2018-09-07 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2585 | OL1-2G30-2585 | Process Equipment Data Sheet - 10-E-2585 - C2 Tower Bottoms Reboiler | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2587 | OL1-2G30-2587 | Process Equipment Data Sheet - 10-E-2587 - C2 Tower Side Reboiler | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2882 | OL1-2G30-2882 | Process Equipment Data Sheet - 10-E-2882 - LP Ethylene Product Cooler No 1 | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2884 | OL1-2G30-2884 | Process Equipment Data Sheet - 10-E-2884 - LP Ethylene Product Cooler No 2 | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1012-JSS-0122-2001 | OL1-4M92-2001 | Project Specification for Centrifugally Cast Tubes for Radiant Coils and Transfer Lines in Cracking Furnaces | A | IFR | TPSK-LSPA1-T-ME-00037 | 2018-09-10 | R2-Comments as noted | 2018-09-25 | 2018-09-24 | 2018-09-10 | IFR | C | HOC | ME | 2
036909C-1012-JSS-0122-2002 | OL1-4M92-2002 | Project Specification for Statically Cast Fittings for Radiant Coils and Transfer Lines in Cracking Furnaces | A | IFR | TPSK-LSPA1-T-ME-00037 | 2018-09-10 | R2-Comments as noted | 2018-09-25 | 2018-09-24 | 2018-09-10 | IFR | C | HOC | ME | 2
036909C-1022-SP-1011-2200 | OL1-2M03-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor | A | IFA | TPSK-LSPA1-T-ME-00038 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-09-28 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | ME | 1
036909C-1028-SP-1011-2800 | OL1-2M03-2800 | Mechanical Equipment Data Sheet for Propylene Refrigeration Compressor | A | IFA | TPSK-LSPA1-T-ME-00038 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-09-28 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | ME | 1
036909C-1028-SP-1011-2850 | OL1-2M03-2850 | Mechanical Equipment Data Sheet for Ethylene Refrigeration Compressor | A | IFA | TPSK-LSPA1-T-ME-00038 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-09-28 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | ME | 1
036909C-1025-PDS-0600-2500 | OL1-2G30-2500 | Process Equipment Data Sheet - 10-E-2500 - Propylene Refrig Subcooler | A | IFA | TPSK-LSPA1-T-PE-00039 | 2018-09-11 | A2-Approved with comments, re-submit is not required. | 2018-09-28 | 2018-09-25 | 2018-09-10 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2856 | OL1-2G30-2856 | Process Equipment Data Sheet - 10-E-2855 - C2R Condenser | A | IFA | TPSK-LSPA1-T-PE-00039 | 2018-09-11 | A2-Approved with comments, re-submit is not required. | 2018-09-28 | 2018-09-25 | 2018-09-10 | IFA | H | HOC | PE | 1
036909C-1000-PP-830 | OL1-2J92-0002 | Employee Grievance Management Plan | 0 | IFI | TPSK-LSPA1-T-HR-00040 | 2018-09-12 | Transmitted |  |  | 2018-09-12 | IFI | C | SK | HR | 3
036909C-1000-PP-831 | OL1-2J93-0004 | Human Resource Policy And Procedures | 0 | IFI | TPSK-LSPA1-T-HR-00040 | 2018-09-12 | Transmitted |  |  | 2018-09-12 | IFI | C | SK | HR | 3
036909C-1000-PP-832 | OL1-2J94-0002 | Worker Code Of Conduct Declaration Form | 0 | IFI | TPSK-LSPA1-T-HR-00040 | 2018-09-12 | Transmitted |  |  | 2018-09-12 | IFI | C | SK | HR | 3
036909C-1000-PP-833 | OL1-2J94-0004 | Child Labor Risk Assessment Checklist | 0 | IFI | TPSK-LSPA1-T-HR-00040 | 2018-09-12 | Transmitted |  |  | 2018-09-12 | IFI | C | SK | HR | 3
036909C-1000-PP-834 | OL1-2J94-0005 | Forced Labor Risk Assessment Checklist | 0 | IFI | TPSK-LSPA1-T-HR-00040 | 2018-09-12 | Transmitted |  |  | 2018-09-12 | IFI | C | SK | HR | 3
036909C-1026-PDS-0600-2645 | OL1-2G30-2645 | Process Equipment Data Sheet - 10-E-2645 - C3 Tower Reboilers | A | IFA | TPSK-LSPA1-T-PE-00041 | 2018-09-12 | A1-Approved without comments | 2018-10-01 | 2018-09-26 | 2018-09-11 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2857 | OL1-2G30-2857 | Process Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer | A | IFA | TPSK-LSPA1-T-PE-00041 | 2018-09-12 | A1-Approved without comments | 2018-10-01 | 2018-09-26 | 2018-09-11 | IFA | H | HOC | PE | 1
036909C-1000-JSS-0400-02 | OL1-2R03-0102 | Marking For Vessel & Heat Exchanger | 0 | IMP | TPSK-LSPA1-T-ME-00042 | 2018-09-12 | Transmitted |  |  | 2018-09-10 | IFI | C | ROC | ME | 3
036909C-1000-JSS-0660-01 | OL1-2R03-0006 | Plate Heat Exchanger | 0 | IMP | TPSK-LSPA1-T-ME-00042 | 2018-09-12 | Transmitted |  |  | 2018-09-10 | IFI | C | ROC | ME | 3
036909C-1012-JSS-0000-9999 | OL1-2C93-0001 | General Supply Rules for Supplier Documentation | A | IFI | TPSK-LSPA1-T-PL-00043 | 2018-09-12 | Transmitted |  |  | 2018-09-12 | IFI | C | HOC | PL | 3
036909C-1012-TEN-0127-2001 | OL1-4M57-2001 | Technical Notes for Convection Tubes Material Requisition | A | IFQ | TPSK-LSPA1-T-ME-00044 | 2018-09-12 | Transmitted |  |  | 2018-09-06 | IFI | C | HOC | ME | 3
036909C-1012-SR-0127-2001 | OL1-4M56-2001 | Material Requisition Scope of Supply for Convection Tubes | A | IFQ | TPSK-LSPA1-T-ME-00044 | 2018-09-12 | Transmitted |  |  | 2018-09-06 | IFI | C | HOC | ME | 3
036909C-1012-MR-0127-2001 | OL1-4M55-2001 | Material Requisition for Convection Tubes | A | IFQ | TPSK-LSPA1-T-ME-00044 | 2018-09-12 | Transmitted |  |  | 2018-09-06 | IFI | C | HOC | ME | 3
036909C-1012-ITP-0127-2001 | OL1-4M07-2001 | Inspection and Test Plan for Convection Tubes | A | IFQ | TPSK-LSPA1-T-ME-00044 | 2018-09-12 | Transmitted | 2018-11-05 |  | 2018-09-06 | IFI | C | HOC | ME | 3
036909C-1000-PP-602 | OL1-2C92-0002 | Project QCS Coordination Procedure | A | IFR | TPSK-LSPA1-T-PL-00046 | 2018-09-13 | R2-Comments as noted | 2018-10-01 | 2018-09-28 | 2018-09-11 | IFR | H | JVD | PL | 2
036909C-1000-PP-605 | OL1-2C92-0005 | Project QCS Requirements For Suppliers | A | IFR | TPSK-LSPA1-T-PL-00046 | 2018-09-13 | R2-Comments as noted | 2018-10-01 | 2018-09-28 | 2018-09-11 | IFR | H | JVD | PL | 2
036909C-1000-PP-608 | OL1-2C92-0008 | Project QCS Expediting Procedure | A | IFR | TPSK-LSPA1-T-PL-00046 | 2018-09-13 | Transmitted |  | 2018-09-28 | 2018-09-11 | IFR | H | ROC | PL | 2
036909C-1000-PP-609 | OL1-2C92-0009 | Project QCS Inspection Procedure | A | IFR | TPSK-LSPA1-T-PL-00046 | 2018-09-13 | R2-Comments as noted | 2018-10-01 | 2018-09-28 | 2018-09-11 | IFR | H | JVD | PL | 2
036909C-1000-PP-614 | OL1-2C92-0014 | Project Expediting And Inspection Level Definition | A | IFR | TPSK-LSPA1-T-PL-00046 | 2018-09-13 | R2-Comments as noted | 2018-10-01 | 2018-09-28 | 2018-09-11 | IFR | H | JVD | PL | 2
036909C-1000-PP-015 | OL1-2W92-0015 | Prescriptions For Preparation Of Manufacturing Data Record Book | A | IFR | TPSK-LSPA1-T-PC-00047 | 2018-09-13 | Transmitted |  | 2018-09-28 | 2018-09-11 | IFR | H | ROC | PC | 2
036909C-1000-PP-301 | OL1-2B92-0001 | Planning Scheduling And Progress Measurement Procedure | A | IFR | TPSK-LSPA1-T-PC-00045 | 2018-09-13 | R2-Comments as noted | 2018-11-05 | 2018-09-28 | 2018-09-11 | IFR | C | ROC | PC | 2
036909C-1000-PP-607 | OL1-2C92-0007 | Prescriptions For Preparation Of Documentation Package For Transportation | A | IFR | TPSK-LSPA1-T-PL-00048 | 2018-09-13 | R2-Comments as noted | 2018-10-01 | 2018-09-28 | 2018-08-22 | IFR | H | ROC | PL | 2
036909C-1000-PP-615 | OL1-2C92-0015 | Transport Plan | A | IFR | TPSK-LSPA1-T-PL-00048 | 2018-09-13 | R2-Comments as noted | 2018-10-01 | 2018-09-28 | 2018-08-31 | IFR | H | ROC | PL | 2
036909C-1000-PP-616 | OL1-2C92-0016 | Parking Marking And Shipping Instructions | A | IFR | TPSK-LSPA1-T-PL-00048 | 2018-09-13 | R2-Comments as noted | 2018-10-01 | 2018-09-28 | 2018-08-28 | IFR | H | ROC | PL | 2
036909C-1000-NM-0003-1008 | OL1-2G62-1008 | Fuel Balance | A | IFI | TPSK-LSPA1-T-PE-00049 | 2018-09-13 | Transmitted |  |  | 2018-09-12 | IFI | C | HOC | PE | 3
036909C-1019-SP-1013-1950 | OL1-2M03-1950 | Mechanical Equipment Datasheet for Decoking Air Compressor Package | A | IFA | TPSK-LSPA1-T-ME-00050 | 2018-09-13 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-27 | 2018-09-13 | IFA | H | HOC | ME | 1
036909C-1025-SP-1011-2550 | OL1-2M03-2550 | Mechanical Equipment Datasheet for Residue Gas Expander-Recompressor | A | IFA | TPSK-LSPA1-T-ME-00050 | 2018-09-13 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-27 | 2018-09-13 | IFA | H | HOC | ME | 1
036909C-1000-PP-601 | OL1-2C92-0001 | Project Procurement Execution Plan | A | IFR | TPSK-LSPA1-T-PC-00051 | 2018-09-14 | Transmitted |  | 2018-09-28 | 2018-09-13 | IFR | C | ROC | PC | 2
036909C-1000-PP-617 | OL1-2C92-0017 | Project Site Services Conditions For Supplier Specialists | A | IFR | TPSK-LSPA1-T-PL-00051 | 2018-09-14 | R2-Comments as noted | 2018-10-04 | 2018-09-28 | 2018-09-12 | IFR | H | JVD | PL | 2
036909C-1024-PDS-0500-2440 | OL1-2G30-2440 | Process Equipment Data Sheet - 10-T-2440 - HP Depropanizer | A | IFA | TPSK-LSPA1-T-PE-00053 | 2018-09-14 | A3-Approved with comments, re-submit for review. | 2018-10-03 | 2018-09-28 | 2018-09-13 | IFA | H | HOC | PE | 1
036909C-1024-PDS-0500-2450 | OL1-2G30-2450 | Process Equipment Data Sheet - 10-T-2450 - LP Depropanizer | A | IFA | TPSK-LSPA1-T-PE-00053 | 2018-09-14 | A3-Approved with comments, re-submit for review. | 2018-10-03 | 2018-09-28 | 2018-09-13 | IFA | H | HOC | PE | 1
036909C-1026-PDS-0500-2630 | OL1-2G30-2630 | Process Equipment Data Sheet - 10-T-2630 - Secondary Deethanizer | A | IFA | TPSK-LSPA1-T-PE-00053 | 2018-09-14 | A3-Approved with comments, re-submit for review. | 2018-10-03 | 2018-09-28 | 2018-09-13 | IFA | H | HOC | PE | 1
036909C-1026-PDS-0500-2660 | OL1-2G30-2660 | Process Equipment Data Sheet - 10-T-2660 - Debutanizer | A | IFA | TPSK-LSPA1-T-PE-00053 | 2018-09-14 | A3-Approved with comments, re-submit for review. | 2018-10-03 | 2018-09-28 | 2018-09-13 | IFA | H | HOC | PE | 1
036909C-1000-NM-0003-1006 | OL1-2G62-1006 | Cooling Water Balance | A | IFI | TPSK-LSPA1-T-PE-00054 | 2018-09-17 | R2-Comments as noted | 2018-10-09 | 2018-10-08 | 2018-09-14 | IFI | C | HOC | PE | 3
036909C-1000-JSS-0900-0001 | OL1-2R03-0028 | ME-028 Mechanical Seal | 0 | IMP | TPSK-LSPA1-T-ME-00057 | 2018-09-17 | Transmitted |  |  | 2018-09-14 | IFI | C | ROC | ME | 3
036909C-1000-JSD-1580-0003 | OL1-2R06-0035 | General Design Rules For Instrumentation And Control Of Packaged Equipment | A | IFR | TPSK-LSPA1-T-IE-00056 | 2018-09-17 | R2-Comments as noted | 2018-10-02 | 2018-10-01 | 2018-09-14 | IFR | C | ROC | IE | 2
036909C-1028-PDS-1000-2800 | OL1-2G30-2800 | Process Equipment Data Sheet - 10-C-2800 - Propylene Refrig Compressor | B | IFD | TPSK-LSPA1-T-PE-00055 | 2018-09-17 | Transmitted |  |  | 2018-09-14 | IFI | C | HOC | PE | 3
036909C-1028-PDS-1000-2850 | OL1-2G30-2850 | Process Equipment Data Sheet - 10-C-2850 - Ethylene Refrig Compressor | B | IFD | TPSK-LSPA1-T-PE-00055 | 2018-09-17 | Transmitted |  |  | 2018-09-14 | IFI | C | HOC | PE | 3
036909C-1022-PDS-1000-2200 | OL1-2G30-2200 | Process Equipment Data Sheet - 10-C-2200 - Cracked Gas Compressor | B | IFD | TPSK-LSPA1-T-PE-00055 | 2018-09-17 | Transmitted |  |  | 2018-09-14 | IFI | C | HOC | PE | 3
036909C-1021-TDS-0661-2101 | OL1-2M03-2101 | Mechanical Data Sheet - 10-E-2100 - Quench Water Cooler | A | IFA | TPSK-LSPA1-T-ME-00058 | 2018-09-17 | A3-Approved with comments, re-submit for review. | 2018-09-28 | 2018-10-01 | 2018-09-14 | IFA | H | HOC | ME | 1
036909C-1000-NM-0003-1001 | OL1-2G62-1001 | Steam Balance | A | IFI | TPSK-LSPA1-T-PE-00059 | 2018-09-17 | Transmitted | 2018-10-04 | 2018-10-01 | 2018-09-17 | IFI | C | HOC | PE | 3
036909C-1023-PDS-0500-2300 | OL1-2G30-2300 | Process Equipment Data Sheet - 10-T-2300 - Caustic Tower | A | IFA | TPSK-LSPA1-T-PE-00060 | 2018-09-18 | A3-Approved with comments, re-submit for review. | 2018-10-24 | 2018-10-02 | 2018-09-17 | IFA | H | HOC | PE | 1
036909C-LSPA1-TPSK-MOM-0011 | LSPA1-TPSK-M-0011 | Process Flow Diagrams Review | 0 | IFI | TPSK-LSPA1-T-PM-00061 | 2018-09-18 | Transmitted |  |  | 2018-09-18 | IFI | C | HOC | PE | 3
036909C-1012-SR-0122-2004 | OL1-2M56-2004 | Scope of Supply for Radiant Coil Assemblies | A | IFQ | TPSK-LSPA1-T-ME-00063 | 2018-09-18 | Transmitted |  |  | 2018-09-10 | IFI | C | HOC | ME | 3
036909C-1012-MR-0122-2004 | OL1-2M55-2004 | Material Requisition for Radiant Coil Assemblies | A | IFQ | TPSK-LSPA1-T-ME-00063 | 2018-09-18 | Transmitted |  |  | 2018-09-12 | IFI | C | HOC | ME | 3
036909C-1012-ITP-0122-2004 | OL1-2M07-2004 | Inspection and Test Plan for Radiant Coil Assemblies | A | IFQ | TPSK-LSPA1-T-ME-00063 | 2018-09-18 | Transmitted |  |  | 2018-09-10 | IFI | C | HOC | ME | 3
036909C-1011-DW-0122-1201 | OL1-2M06-1201 | USC 36M Recycle Furnace Radiant Coil Assembly and Details | A | IFR | TPSK-LSPA1-T-ME-00062 | 2018-10-08 | Transmitted |  | 2018-10-22 | 2018-09-11 | IFR | C | HOC | ME | 2
036909C-1011-DW-0122-1202 | OL1-2M06-1202 | USC 36M Recycle Furnace Transfer Line and Clean-Out Details | A | IFR | TPSK-LSPA1-T-ME-00062 | 2018-10-08 | Transmitted |  | 2018-10-22 | 2018-09-11 | IFR | C | HOC | ME | 2
036909C-1011-DW-0122-1203 | OL1-2M06-1203 | USC 36M Recycle Furnace Radiant Coil Tubeskin Thermocouple Details | A | IFR | TPSK-LSPA1-T-ME-00062 | 2018-10-08 | Transmitted |  | 2018-10-22 | 2018-09-11 | IFR | C | HOC | ME | 2
036909C-1012-DW-0122-2201 | OL1-2M06-2201 | USC 132U Furnace Radiant Coil Assembly and Details | A | IFR | TPSK-LSPA1-T-ME-00062 | 2018-10-08 | Transmitted |  | 2018-10-22 | 2018-09-11 | IFR | C | HOC | ME | 2
036909C-1012-DW-0122-2202 | OL1-2M06-2202 | USC 132U Cracking Furnace Transfer Lines and Clean-Out Details | A | IFR | TPSK-LSPA1-T-ME-00062 | 2018-10-08 | Transmitted |  | 2018-10-22 | 2018-09-11 | IFR | C | HOC | ME | 2
036909C-1012-DW-0122-2203 | OL1-2M06-2203 | USC 132U Cracking Furnace Radiant Coil Tubeskin Thermocouple Details | A | IFR | TPSK-LSPA1-T-ME-00062 | 2018-10-08 | Transmitted |  | 2018-10-22 | 2018-09-11 | IFR | C | HOC | ME | 2
036909C-1000-PP-613 | OL1-2C92-0013 | Spare Parts & Specials Tools Instruction | A | IFR | TPSK-LSPA1-T-PL-00064 | 2018-09-19 | R2-Comments as noted | 2018-09-25 | 2018-10-03 | 2018-09-14 | IFR | H | ROC | PL | 2
036909C-1000-JSS-1011-0001 | OL1-2R03-0014 | ME-014 Centrifugal Compressor | A | IFR | TPSK-LSPA1-T-ME-00065 | 2018-09-18 | R1-No comments | 2018-10-10 | 2018-10-03 | 2018-09-18 | IFR | C | ROC | ME | 2
036909C-1000-JSS-1061-0001 | OL1-2R03-0019 | ME-019 Lube Oil Unit And Seal Oil System | A | IFR | TPSK-LSPA1-T-ME-00065 | 2018-09-18 | R1-No comments | 2018-10-10 | 2018-10-03 | 2018-09-18 | IFR | C | ROC | ME | 2
036909C-1011-PDS-0610-1009 | OL1-4G30-1009 | See document number 036909C-1011-PDS-0610-1109 or OL1-2G30-1109 | A | IFR | TPSK-LSPA1-T-PE-00066 | 2018-09-19 | Transmitted |  |  | 2018-09-17 | IFR | C | HOC | PE | 2
036909C-1011-PDS-0610-1010 | OL1-4G30-1010 | See document number 036909C-1011-PDS-0610-1110 or OL1-2G30-1110 | A | IFR | TPSK-LSPA1-T-PE-00066 | 2018-09-19 | Transmitted |  |  | 2018-09-17 | IFR | C | HOC | PE | 2
036909C-1011-PDS-0630-1008 | OL1-4G30-1008 | See document number 036909C-1011-PDS-0630-1108 or OL1-2G30-1108 | A | IFR | TPSK-LSPA1-T-PE-00066 | 2018-09-19 | Transmitted |  |  | 2018-09-17 | IFR | C | HOC | PE | 2
036909C-1012-PDS-0610-2009 | OL1-4G30-2009 | See document number 036909C-1012-PDS-0610-1209 or OL1-2G30-1209 | A | IFR | TPSK-LSPA1-T-PE-00066 | 2018-09-19 | Transmitted |  |  | 2018-09-17 | IFR | C | HOC | PE | 2
036909C-1012-PDS-0630-2008 | OL1-4G30-2008 | See document number 036909C-1012-PDS-0630-1208 or OL1-2G30-1208 | A | IFR | TPSK-LSPA1-T-PE-00066 | 2018-09-19 | Transmitted |  |  | 2018-09-17 | IFR | C | HOC | PE | 2
036909C-1012-JSS-0154-2007 | OL1-4M92-2007 | Project Specification For SLE and USX Exchangers | A | IFR | TPSK-LSPA1-T-ME-00067 | 2018-09-20 | R2-Comments as noted | 2018-10-12 | 2018-10-04 | 2018-09-20 | IFR | C | HOC | ME | 2
036909C-1012-JSS-0154-2008 | OL1-4M92-2008 | Project Specification For Transfer Line Exchangers | A | IFR | TPSK-LSPA1-T-ME-00067 | 2018-09-20 | R2-Comments as noted | 2018-10-12 | 2018-10-04 | 2018-09-20 | IFR | C | HOC | ME | 2
036909C-1023-PDS-2500-2320 | OL1-2G30-2320 | Process Equipment Data Sheet - 10-TK-2320 - Spent Caustic Storage Tank | A | IFA | TPSK-LSPA1-T-PE-00068 | 2018-09-20 | A3-Approved with comments, re-submit for review. | 2018-10-09 | 2018-10-04 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1021-PDS-0900-2146 | OL1-2G30-2146 | Process Equipment Datasheet 10-P-2146 DSG Feed Pumps | A | IFA | TPSK-LSPA1-T-PE-00069 | 2018-09-20 | A3-Approved with comments, re-submit for review. | 2018-10-09 | 2018-10-04 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1021-PDS-0900-2106 | OL1-2G30-2106 | Process Equipment Datasheet - 10-P-2106 A-C - Quench Water Pumps | A | IFA | TPSK-LSPA1-T-PE-00070 | 2018-09-20 | A1-Approved without comments | 2018-10-09 | 2018-10-04 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1020-PDS-0900-2006 | OL1-2G30-2006 | Process Equipment Datasheet - 10-P-2006 A-C - Quench Oil Pumps | A | IFA | TPSK-LSPA1-T-PE-00071 | 2018-09-20 | A3-Approved with comments, re-submit for review. | 2018-10-09 | 2018-10-04 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-LSPA1-TPSK-MOM-0007 | LSPA1-TPSK-M-0007 | Clarification Meeting - Buildings Specifications Review | 0 | IFI | TPSK-LSPA1-T-CV-00099 | 2018-09-27 | Transmitted |  |  | 2018-09-10 | IFI | C | JVD | CV | 3
036909C-LSPA1-TPSK-MOM-0008 | LSPA1-TPSK-M-0008 | Clarification Meeting - Procurement | 0 | IFI | TPSK-LSPA1-T-PL-00104 | 2018-09-28 | Transmitted |  |  | 2018-09-12 | IFI | C | JVD | PL | 3
036909C-LSPA1-TPSK-MOM-0009 | LSPA1-TPSK-M-0009 | Clarification Meeting - Project Control | 0 | IFI | TPSK-LSPA1-T-PC-00103 | 2018-09-28 | Transmitted |  |  | 2018-09-18 | IFI | C | JVD | PC | 3
036909C-LSPA1-TPSK-MOM-0010 | LSPA1-TPSK-M-0010 | Clarification Meeting - Reporting Meeting With LSP | 0 | IFI | TPSK-LSPA1-T-PC-00103 | 2018-09-28 | Transmitted |  |  | 2018-09-06 | IFI | C | JVD | PC | 3
036909C-LSPA1-TPSK-MOM-0012 | LSPA1-TPSK-M-0012 | Clarification Meeting - Civil Design | 0 | IFI | TPSK-LSPA1-T-CV-00099 | 2018-09-27 | Transmitted |  |  | 2018-09-10 | IFI | C | JVD | CV | 3
036909C-LSPA1-TPSK-MOM-0013 | LSPA1-TPSK-M-0013 | Clarification Meeting - Piping Design | 0 | IFI | TPSK-LSPA1-T-MP-00100 | 2018-09-27 | Transmitted |  |  | 2018-09-14 | IFI | C | JVD | MP | 3
036909C-LSPA1-TPSK-MOM-0014 | LSPA1-TPSK-M-0014 | Clarification Meeting - Piping Stress | 0 | IFI | TPSK-LSPA1-T-MP-00100 | 2018-09-27 | Transmitted |  |  | 2018-08-28 | IFI | C | JVD | MP | 3
036909C-LSPA1-TPSK-MOM-0015 | LSPA1-TPSK-M-0015 | Clarification Meeting - Piping Material | 0 | IFI | TPSK-LSPA1-T-MP-00100 | 2018-09-27 | Transmitted |  |  | 2018-09-14 | IFI | C | JVD | MP | 3
036909C-LSPA1-TPSK-MOM-0016 | LSPA1-TPSK-M-0016 | Clarification Meeting - Piping Stress | 0 | IFI | TPSK-LSPA1-T-MP-00100 | 2018-09-27 | Transmitted |  |  | 2018-09-07 | IFI | C | JVD | MP | 3
036909C-LSPA1-TPSK-MOM-0017 | LSPA1-TPSK-M-0017 | Clarification Meeting - Document Control | 0 | IFI | TPSK-LSPA1-T-PM-00097 | 2018-09-27 | Transmitted |  |  | 2018-09-03 | IFI | C | JVD | PM | 3
036909C-1000-PLG-102 | OL1-2W01-0001 | Plant And Section Codes | 0 | IMP | TPSK-LSPA1-T-PC-00076 | 2018-09-24 | Transmitted |  |  | 2018-09-17 | IFI | C | ROC | PC | 3
036909C-LSPA1-TPSK-MOM-0018 | LSPA1-TPSK-M-0018 | Clarification Meeting - Engineering Data Interfacing Work | 0 | IFI | TPSK-LSPA1-T-PM-00097 | 2018-09-27 | Transmitted |  |  | 2018-09-14 | IFI | C | JVD | PM | 3
036909C-1000-PLG-103 | OL1-2W01-0002 | Plant And Zone Codes | B | IFR | TPSK-LSPA1-T-PC-00077 | 2018-09-24 | R2-Comments as noted | 2018-10-17 | 2018-10-08 | 2018-09-17 | IFR | C | ROC | PC | 2
036909C-LSPA1-TPSK-MOM-0019 | LSPA1-TPSK-M-0019 | Clarification Meeting - Construction Permit Preliminary Schedule | 0 | IFI | TPSK-LSPA1-T-PM-00097 | 2018-09-27 | Transmitted |  |  | 2018-09-07 | IFI | C | JVD | PM | 3
036909C-LSPA1-TPSK-MOM-0020 | LSPA1-TPSK-M-0020 | Clarification Meeting - Noise Control Specification And Firefighting Basic Design Report | 0 | IFI | TPSK-LSPA1-T-PM-00097 | 2018-09-27 | Transmitted |  |  | 2018-09-07 | IFI | C | JVD | PM | 3
036909C-LSPA1-TPSK-MOM-0021 | LSPA1-TPSK-M-0021 | Clarification Meeting - Instrument | 0 | IFI | TPSK-LSPA1-T-IE-00105 | 2018-09-28 | Transmitted |  |  | 2018-09-14 | IFI | C | JVD | IE | 3
036909C-LSPA1-TPSK-MOM-0022 | LSPA1-TPSK-M-0022 | Clarification Meeting - Electrical | 0 | IFI | TPSK-LSPA1-T-EE-00106 | 2018-09-28 | Transmitted |  |  | 2018-09-14 | IFI | C | JVD | EE | 3
036909C-LSPA1-TPSK-MOM-0023 | LSPA1-TPSK-M-0023 | Clarification Meeting - Quality | 0 | IFI | TPSK-LSPA1-T-QM-00107 | 2018-09-28 | Transmitted |  |  | 2018-09-13 | IFI | C | JVD | QM | 3
036909C-LSPA1-TPSK-MOM-0024 | LSPA1-TPSK-M-0024 | Clarification Meeting - 2D Drafting (New Procedure) And 3D Model (Comments To SP-021) By TPSK | 0 | IFI | TPSK-LSPA1-T-PM-00097 | 2018-09-27 | Transmitted |  |  | 2018-09-04 | IFI | C | JVD | PM | 3
036909C-LSPA1-TPSK-MOM-0025 | LSPA1-TPSK-M-0025 | Clarification Meeting - Project Management | 0 | IFI | TPSK-LSPA1-T-PM-00097 | 2018-09-27 | Transmitted |  |  | 2018-09-18 | IFI | C | JVD | PM | 3
036909C-LSPA1-TPSK-MOM-0026 | LSPA1-TPSK-M-0026 | LLDPE Flare And EGF Proposals | 0 | IFI | TPSK-LSPA1-T-PM-00097 | 2018-09-27 | Transmitted |  |  | 2018-09-18 | IFI | C | JVD | PM | 3
036909C-LSPA1-TPSK-MOM-0027 | LSPA1-TPSK-M-0027 | Vendor List Status and PQ Process | 0 | IFI | TPSK-LSPA1-T-PM-00097 | 2018-09-27 | Transmitted |  |  | 2018-09-18 | IFI | C | JVD | PM | 3
036909C-LSPA1-TPSK-MOM-0005 | LSPA1-TPSK-M-0005 | Clarification Meeting - PV&HE & Welding KOM With Client | 0 | IFI | TPSK-LSPA1-T-MP-00097 | 2018-09-27 | Transmitted |  |  | 2018-09-18 | IFI | C | JVD | MP | 3
036909C-LSPA1-TPSK-MOM-0006 | LSPA1-TPSK-M-0006 | Clarification Meeting - Review Of Client Mechanical Specification For Centrifugal Compressors Steam Turbine Lube Oil System | 0 | IFI | TPSK-LSPA1-T-MP-00097 | 2018-09-27 | Transmitted |  |  | 2018-08-31 | IFI | C | JVD | ME | 3
036909C-1000-PP-500 | OL1-2Q92-0001 | Overall Project Quality Plan | A | IFR | TPSK-LSPA1-T-QM-00072 | 2018-09-24 | R2-Comments as noted | 2018-10-12 | 2018-10-05 | 2018-09-17 | IFR | C | ROC | QM | 2
036909C-1023-PDS-0500-2330 | OL1-2G30-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper | A | IFA | TPSK-LSPA1-T-PE-00073 | 2018-09-24 | A3-Approved with comments, re-submit for review. | 2018-10-12 | 2018-10-08 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0500-2540 | OL1-2G30-2540 | Process Equipment Datasheet - 10-T-2540 and 10-D-2540 - Demethanizer and Reflux Drum | A | IFA | TPSK-LSPA1-T-PE-00073 | 2018-09-24 | A3-Approved with comments, re-submit for review. | 2018-10-24 | 2018-10-08 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1026-PDS-0600-2631 | OL1-2G30-2631 | Process Equipment Datasheet - 10-E-2630 - Secondary Deeth Condenser | A | IFA | TPSK-LSPA1-T-PE-00074 | 2018-09-24 | A2-Approved with comments, re-submit is not required. | 2018-10-12 | 2018-10-08 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1026-PDS-0600-2635 | OL1-2G30-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler | A | IFA | TPSK-LSPA1-T-PE-00074 | 2018-09-24 | A2-Approved with comments, re-submit is not required. | 2018-10-12 | 2018-10-08 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1026-PDS-0600-2636 | OL1-2G30-2636 | Process Equipment Datasheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | A | IFA | TPSK-LSPA1-T-PE-00074 | 2018-09-24 | A2-Approved with comments, re-submit is not required. | 2018-10-12 | 2018-10-08 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1053-PDS-0900-5352 | OL1-2G30-5352 | Process Equipment Data Sheet - 10-P-5350 A-H - Olefins Cooling Water Pumps | A | IFA | TPSK-LSPA1-T-PE-00075 | 2018-09-24 | Transmitted |  | 2018-10-08 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1000-JSD-0001-0002 | OL1-2R07-0018 | Units Of Measurement | 0 | IMP | TPSK-LSPA1-T-ME-00080 | 2018-09-24 | Transmitted | 2018-10-24 |  | 2018-09-20 | IFI | C | ROC | ME | 3
036909C-1053-PDS-0900-5361 | OL1-2G30-5361 | Process Equipment Data Sheet - 10-P-5360 A-C - CTU Cooling Water Pumps | A | IFA | TPSK-LSPA1-T-PE-00075 | 2018-09-24 | A3-Approved with comments, re-submit for review. | 2018-10-24 | 2018-10-08 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1000-JSS-0910-0001 | OL1-2R03-0010 | ME-010 Centrifugal Pump | A | IFR | TPSK-LSPA1-T-ME-00078 | 2018-09-24 | R1-No comments | 2018-10-12 | 2018-10-08 | 2018-09-20 | IFR | C | ROC | ME | 2
036909C-1000-JSS-1111-0001 | OL1-2R03-0018 | ME-018 General Purpose Steam Turbines | A | IFR | TPSK-LSPA1-T-ME-00078 | 2018-09-24 | R1-No comments | 2018-10-12 | 2018-10-08 | 2018-09-20 | IFR | C | ROC | ME | 2
036909C-1000-JSS-1112-0001 | OL1-2R03-0020 | ME-020 Special Purpose Steam Tturbines | A | IFR | TPSK-LSPA1-T-ME-00078 | 2018-09-24 | R1-No comments | 2018-10-12 | 2018-10-08 | 2018-09-20 | IFR | C | ROC | ME | 2
036909C-1000-JSS-1682-0001 | OL1-2R05-0037 | Electrical Heat Tracing | 0 | IMP | TPSK-LSPA1-T-EE-00079 | 2018-09-24 | Transmitted |  |  | 2018-09-20 | IFI | C | ROC | EE | 3
036909C-1000-JSS-1691-0001 | OL1-2R05-0010 | Electrical Motos Up To 300 kW | 0 | IMP | TPSK-LSPA1-T-EE-00079 | 2018-09-24 | Transmitted |  |  | 2018-09-20 | IFI | C | ROC | EE | 3
036909C-1000-JSS-0570-01 | OL1-2R03-0052 | Job Specification For Supply Of Column Internals | 0 | IMP | TPSK-LSPA1-T-ME-00081 | 2018-09-24 | Transmitted | 2018-10-24 |  | 2018-09-20 | IFI | C | ROC | ME | 3
036909C-1000-JSS-1820-01 | OL1-2R03-0053 | Job Specification For Supply Of Equipment Ladders And Platforms | 0 | IFR | TPSK-LSPA1-T-ME-00081 | 2018-09-24 | Transmitted | 2018-10-24 |  | 2018-09-20 | IFI | C | ROC | ME | 3
036909C-1000-JSD-0400-01 | OL1-2R03-0050 | Job Specification For Design Of Pressure & Atmospheric Static Equipment | B | IFR | TPSK-LSPA1-T-ME-00084 | 2018-09-25 | R1-No comments | 2018-10-24 | 2018-10-09 | 2018-09-20 | IFR | H | ROC | ME | 2
036909C-1000-JSS-0400-01 | OL1-2R03-0051 | Job Specification For Supply Of Pressure Vessels | B | IFR | TPSK-LSPA1-T-ME-00084 | 2018-09-25 | R1-No comments | 2018-10-24 | 2018-10-09 | 2018-09-20 | IFR | H | ROC | ME | 2
036909C-1053-PDS-0300-5350 | OL1-2G30-5350 | Process Equipment Data Sheet - 10-PK-5350 - Cooling Tower | A | IFA | TPSK-LSPA1-T-PE-00082 | 2018-09-25 | A3-Approved with comments, re-submit for review. | 2018-10-13 | 2018-10-09 | 2018-09-24 | IFA | H | HOC | PE | 1
036909C-1053-PDS-0300-5355 | OL1-2G30-5355 | Process Equipment Data Sheet - 10-PK-5355 - Side Stream Filter Package | A | IFA | TPSK-LSPA1-T-PE-00082 | 2018-09-25 | A3-Approved with comments, re-submit for review. | 2018-10-13 | 2018-10-09 | 2018-09-24 | IFA | H | HOC | PE | 1
036909C-1000-PP-111 | OL1-2W92-0016 | Reporting Procedure | A | IFR | TPSK-LSPA1-T-PC-00083 | 2018-09-25 | Transmitted |  | 2018-10-08 | 2018-09-21 | IFR | C | JVD | PC | 2
036909C-1000-STC-0490-000 | OL1-2R03-0054 | Construction Standards For Pressure Equipment | B | IFR | TPSK-LSPA1-T-ME-00084 | 2018-09-25 | R1-No comments | 2018-10-24 | 2018-10-09 | 2018-09-20 | IFR | H | ROC | ME | 2
036909C-1000-DW-1402-0001 | OL1-2K92-0001 | General Notes For Underground Works | A | IFR | TPSK-LSPA1-T-CV-00086 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-18 | IFR | C | ROC | CV | 2
036909C-1000-DW-1702-0001 | OL1-2K92-0003 | General Notes For Concrete Works | A | IFR | TPSK-LSPA1-T-CV-00086 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-19 | IFR | C | ROC | CV | 2
036909C-1000-DW-1802-0001 | OL1-2K92-0004 | General Notes For Steel Structures | A | IFR | TPSK-LSPA1-T-CV-00086 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-19 | IFR | C | ROC | CV | 2
036909C-1000-JSD-1400-0001 | OL1-2R02-0001 | Job Design Specification For Underground Systems | A | IFR | TPSK-LSPA1-T-CV-00087 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-18 | IFR | C | ROC | CV | 2
036909C-1000-JSD-1700-0001 | OL1-2R02-0004 | Job Design Specification For Foundations And Structures | A | IFR | TPSK-LSPA1-T-CV-00087 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-19 | IFR | C | ROC | CV | 2
036909C-1000-STC-1790-0001 | OL1-2K20-0001 | Construction Standards for Reinforced Concrete Works | A | IFR | TPSK-LSPA1-T-CV-00088 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-19 | IFR | C | ROC | CV | 2
036909C-1000-STC-1890-0001 | OL1-2K21-0001 | Construction Standards For Steel Structures | A | IFR | TPSK-LSPA1-T-CV-00088 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-19 | IFR | C | ROC | CV | 2
036909C-1000-PP-259 | OL1-2R07-0023 | Drafting Procedure For 2D Drawings | A | IFR | TPSK-LSPA1-T-ME-00089 | 2018-09-25 | R2-Comments as noted | 2018-10-24 | 2018-10-09 | 2018-09-18 | IFR | C | ROC | ME | 2
036909C-1000-STC-1490-0001 | OL1-2K23-0001 | Standard Construction Drawings For Underground Systems | A | IFR | TPSK-LSPA1-T-CV-00088 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-18 | IFR | C | ROC | CV | 2
036909C-1011-PDS-1040-1011 | OL1-4G30-1011 | Process Equipment Datasheet - 10-C-1100 - USC 36M Induced Draft Fan | A | IFR | TPSK-LSPA1-T-PE-00090 | 2018-09-26 | R1-No comments | 2018-10-12 | 2018-10-10 | 2018-09-25 | IFR | C | HOC | PE | 2
036909C-1012-PDS-1040-2011 | OL1-4G30-2011 | Process Equipment Data sheet - 10-C-1200-1600 - USC 132U Induced Draft Fan | A | IFR | TPSK-LSPA1-T-PE-00090 | 2018-09-26 | R1-No comments | 2018-10-12 | 2018-10-10 | 2018-09-25 | IFR | C | HOC | PE | 2
036909C-1056-DI-0007-5601 | OL1-2G05-5601 | Area Basis of Design - 56 Waste Water Treatment System | B | IFD | TPSK-LSPA1-T-PE-00011 | 2018-09-26 | A3-Approved with comments, re-submit for review. | 2018-10-12 |  | 2018-09-13 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0500-2510 | OL1-2G30-2510 | Process Equipment Datasheet - 10-T-2510 and 10-D-2510 - Demethanizer Prefractionator & Reflux Drum | A | IFA | TPSK-LSPA1-T-PE-00092 | 2018-09-26 | A3-Approved with comments, re-submit for review. | 2018-10-24 | 2018-10-09 | 2018-09-26 | IFA | H | HOC | PE | 1
036909C-1053-DI-0007-5301 | OL1-2G05-5301 | Area Basis of Design - 53 Cooling Tower System | B | IFD | TPSK-LSPA1-T-PE-00003 | 2018-09-26 | Transmitted |  |  | 2018-09-24 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0600-2575 | OL1-2G30-2575 | Process Equipment Datasheet - 10-E-2575 - Deethanizer Reboiler | A | IFA | TPSK-LSPA1-T-PE-00094 | 2018-09-26 | A2-Approved with comments, re-submit is not required. | 2018-10-12 | 2018-10-10 | 2018-09-26 | IFA | H | HOC | PE | 1
036909C-1026-PDS-0600-2661 | OL1-2G30-2661 | Process Equipment Datasheet - 10-E-2660 - Debutanizer Condenser | A | IFA | TPSK-LSPA1-T-PE-00094 | 2018-09-26 | A2-Approved with comments, re-submit is not required. | 2018-10-12 | 2018-10-10 | 2018-09-26 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2576 | OL1-2G30-2576 | Process Equipment Datasheet - 10-E-2576 - Deethanizer Bottoms Cooler | A | IFA | TPSK-LSPA1-T-PE-00094 | 2018-09-26 | A2-Approved with comments, re-submit is not required. | 2018-10-12 | 2018-10-10 | 2018-09-26 | IFA | H | HOC | PE | 1
036909C-1000-PP-908 | OL1-2O92-0001 | Instructions To Supplier For Filling-Up Of Spare Parts And Interchangeability Record (SPIR Form) | A | IFR | TPSK-LSPA1-T-PE-00095 | 2018-09-27 | Transmitted |  | 2018-10-11 | 2018-09-24 | IFR | C | ROC | PE | 2
036909C-1000-PLG-313 | OL1-2B91-0001 | Six (6) Week Look-Head Schedule | 0 | IFI | TPSK-LSPA1-T-PC-00096 | 2018-09-27 | Transmitted |  |  | 2018-09-26 | IFI | C | JVD | PC | 3
036909C-1000-PP-261 | OL1-2R07-0025 | Requirements For Eqipment Supplier 3D Model | 0 | IMP | TPSK-LSPA1-T-ME-00108 | 2018-09-28 | Transmitted | 2018-10-24 |  | 2018-09-27 | IFI | C | ROC | ME | 3
036909C-1000-JSD-0001 | OL1-2R07-0026 | Project Design Basis | 0 | IMP | TPSK-LSPA1-T-ME-00110 | 2018-09-28 | Transmitted | 2018-10-24 | 2018-10-11 | 2018-09-26 | IFR | C | ROC | ME | 2
036909C-1000-JSD-1501-0002 | OL1-2R06-0024 | General Design Rules For SmartPlant Instrumentation Setup | A | IFR | TPSK-LSPA1-T-IE-00109 | 2018-09-28 | R2-Comments as noted | 2018-10-09 | 2018-10-11 | 2018-09-27 | IFR | H | ROC | IE | 2
036909C-1026-PDS-0600-2665 | OL1-2G30-2665 | Process Equipment Datasheet - 10-E-2665 A-B - Debutanizer Reboilers | A | IFA | TPSK-LSPA1-T-PE-00101 | 2018-09-27 | A1-Approved without comments | 2018-10-12 | 2018-10-11 | 2018-09-27 | IFA | H | HOC | PE | 1
036909C-1023-PDS-0800-2309 | OL1-2G30-2309 | Process Equipment Datasheet - 10-D-2305 - Yellow Oil Drum | A | IFA | TPSK-LSPA1-T-PE-00102 | 2018-09-27 | A3-Approved with comments, re-submit for review. | 2018-11-14 | 2018-10-11 | 2018-09-27 | IFA | C | HOC | PE | 1
036909C-1023-PDS-0800-2390 | OL1-2G30-2390 | Process Equipment Datasheet - 10-D-2390 - Caustic Drain Drum | A | IFA | TPSK-LSPA1-T-PE-00102 | 2018-09-27 | A3-Approved with comments, re-submit for review. | 2018-11-14 | 2018-10-11 | 2018-09-27 | IFA | C | HOC | PE | 1
036909C-1023-PDS-0800-2392 | OL1-2G30-2392 | Process Equipment Datasheet - 10-D-2392 Spent Caustic Drain Drum | A | IFA | TPSK-LSPA1-T-PE-00102 | 2018-09-27 | A3-Approved with comments, re-submit for review. | 2018-11-14 | 2018-10-11 | 2018-09-27 | IFA | C | HOC | PE | 1
036909C-1023-PDS-0800-2322 | OL1-2G30-2322 | Process Equipment Datasheet - 10-D-2322 - Skim Oil Drum | A | IFA | TPSK-LSPA1-T-PE-00111 | 2018-09-28 | Transmitted |  | 2018-10-12 | 2018-09-27 | IFA | C | HOC | PE | 1
036909C-1026-PDS-0600-2666 | OL1-2G30-2666 | Process Equipment Datasheet - 10-E-2666 - Debutanizer Bottoms Cooler | A | IFA | TPSK-LSPA1-T-PE-00112 | 2018-09-28 | A3-Approved with comments, re-submit for review. | 2018-10-12 | 2018-10-12 | 2018-09-27 | IFA | C | HOC | PE | 1
036909C-1028-PDS-0600-2806 | OL1-2G30-2806 | Process Equipment Datasheet - 10-E-2805 - C3 Refrig Condensers | A | IFA | TPSK-LSPA1-T-PE-00113 | 2018-09-28 | A3-Approved with comments, re-submit for review. | 2018-10-12 | 2018-10-12 | 2018-09-28 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2807 | OL1-2G30-2807 | Process Equipment Datasheet - 10-E-2807 - C3 Chiller No 1 | A | IFA | TPSK-LSPA1-T-PE-00113 | 2018-09-28 | A1-Approved without comments | 2018-10-12 | 2018-10-12 | 2018-09-28 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2809 | OL1-2G30-2809 | Process Equipment Datasheet - 10-E-2809 - C3 Chiller No 2 | A | IFA | TPSK-LSPA1-T-PE-00113 | 2018-09-28 | A1-Approved without comments | 2018-10-12 | 2018-10-12 | 2018-09-28 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2852 | OL1-2G30-2852 | Process Equipment Datasheet - 10-E-2852 - C2R Desuperheater No 1 | A | IFA | TPSK-LSPA1-T-PE-00113 | 2018-09-28 | A1-Approved without comments | 2018-10-12 | 2018-10-12 | 2018-09-28 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2853 | OL1-2G30-2853 | Process Equipment Datasheet - 10-E-2853 - C2R Desuperheater No 2 | A | IFA | TPSK-LSPA1-T-PE-00113 | 2018-09-28 | A1-Approved without comments | 2018-10-12 | 2018-10-12 | 2018-09-28 | IFA | H | HOC | PE | 1
036909C-1019-PDS-1000-1950 | OL1-2G30-1950 | Process Equipment Datasheet - 10-PK-1950 - Decoke Air Compressor Pkg | B | IFD | TPSK-LSPA1-T-PE-00114 | 2018-09-28 | R2-Comments as noted | 2018-10-24 |  | 2018-09-28 | IFI | H | HOC | PE | 3
036909C-1025-PDS-1000-2550 | OL1-2G30-2550 | Process Equipment Datasheet - 10-TX-2550 - 10-C-2550 - Residue Gas Expander - Recompressor | B | IFD | TPSK-LSPA1-T-PE-00114 | 2018-09-28 | R1-No comments | 2018-10-24 |  | 2018-09-28 | IFI | C | HOC | PE | 3
036909C-1021-PDS-0800-2160 | OL1-2G30-2160 | Process Equipment Datasheet - 10-D-2160 - Dilution Steam Generator | A | IFA | TPSK-LSPA1-T-PE-00115 | 2018-09-28 | A3-Approved with comments, re-submit for review. | 2018-11-05 | 2018-10-12 | 2018-09-28 | IFA | C | HOC | PE | 1
036909C-TPTI-TPSW-MOM-0001 |  | Coordnation Meeting Between PVHE Operating Centers (ROC-HOC) | 0 | IFI | 036909C-JVD-TRN-INTERNAL-00008 | 2018-10-01 | Transmitted |  |  | 2018-09-27 | IFI | C | JVD | ME | 3
036909C-1000-NM-0001-1011 | OL1-2G44-1011 | Heat & Material Balance - Cooling Water System | A | IFI | TPSK-LSPA1-T-PE-00116 | 2018-10-01 | Transmitted |  |  | 2018-09-28 | IFI | C | HOC | PE | 3
036909C-1012-PDS-0117-2001 | OL1-4G30-2001 | Process Equipment Datasheet - USC 132U Cracking Furnace Yields | A | IFR | TPSK-LSPA1-T-PE-00117 | 2018-10-01 | Transmitted |  | 2018-10-15 | 2018-09-28 | IFR | C | HOC | PE | 2
036909C-1011-PDS-0117-1001 | OL1-4G30-1001 | Process Equipment Datasheet - USC 36M Cracking Furnace Yields | A | IFR | TPSK-LSPA1-T-PE-00117 | 2018-10-01 | Transmitted |  | 2018-10-15 | 2018-09-28 | IFR | C | HOC | PE | 2
036909C-TPTI-TPSW-MOM-0002 |  | Montly Meeting - PDP Progress Review | 0 | IFI | 036909C-JVD-TRN-INTERNAL-00009 | 2018-10-02 | Transmitted |  |  | 2018-09-28 | IFI | C | ROC | PM | 3
036909C-1000-PP-101 | OL1-2W92-0013 | Project Execution Plan | 0 | IFI | TPSK-LSPA1-T-PC-00118 | 2018-10-02 | Transmitted |  |  | 2018-09-28 | IFI | C | JVD | PC | 3
036909C-1000-PP-613 | OL1-2C92-0013 | Spare Parts & Special Tools Instructions | 0 | IMP | TPSK-LSPA1-T-PL-00119 | 2018-10-02 | Transmitted |  |  | 2018-10-01 | IFI | C | JVD | PL | 3
036909C-1000-JSD-0000-0004 | OL1-2G01-0002 | Cold Box Design Specification | A | IFR | TPSK-LSPA1-T-PE-00123 | 2018-10-03 | R1-No comments | 2018-10-12 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | PE | 2
036909C-1000-JSD-1540-0001 | OL1-2R06-0001 | Instrument General Design | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-ITP-0662-0002 | OL1-2M07-0066 | Inspection And Test Plan For Cold Box And Core Exchangers | A | IFQ | TPSK-LSPA1-T-ME-00125 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-DL-0662-0002 | OL1-2M58-0066 | Deviation List For Cold Box And Core Exchangers | A | IFQ | TPSK-LSPA1-T-ME-00125 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-SP-0662-0002 | OL1-2M57-0066 | Particular Technical Specification For Cold Box And Core Exchangers | A | IFQ | TPSK-LSPA1-T-ME-00125 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-SR-0662-0002 | OL1-2M56-0066 | Scope Of Supply For Cold Box And Core Exchangers | A | IFQ | TPSK-LSPA1-T-ME-00125 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-STC-1890-080 | OL1-2R03-0055 | Construction Standards For Ladders & Platforms Attached To Pressure Equipment | 0 | IMP | TPSK-LSPA1-T-ME-00120 | 2018-10-03 | Transmitted | 2018-10-24 |  | 2018-10-01 | IFI | C | ROC | ME | 3
036909C-1000-ITP-0661-0001 | OL1-2M07-0064 | Inspection And Test Plan For Plate And Frame Heat Exchangers | A | IFQ | TPSK-LSPA1-T-ME-00124 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-DL-0661-0001 | OL1-2M58-0064 | Deviation List For Plate And Frame Heat Exchangers | A | IFQ | TPSK-LSPA1-T-ME-00124 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-SP-0661-0001 | OL1-2M57-0064 | Particular Technical Specification For Plate And Frame Heat Exchangers | A | IFQ | TPSK-LSPA1-T-ME-00124 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-SR-0661-0001 | OL1-2M56-0064 | Scope Of Supply For Plate And Frame Heat Exchangers | A | IFQ | TPSK-LSPA1-T-ME-00124 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-JSD-1552-0001 | OL1-2R06-0005 | LEVEL MEASUREMENT | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1553-0001 | OL1-2R06-0006 | PRESSURE MEASUREMENT | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1554-0001 | OL1-2R06-0007 | TEMPERATURE MEASUREMENT | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1501-0003 | OL1-2R06-0023 | Instrument Inspection And Test Plan | 0 | IMP | TPSK-LSPA1-T-IE-00122 | 2018-10-03 | Transmitted |  |  | 2018-09-28 | IFI | C | ROC | IE | 3
036909C-1000-JSD-1511-0001 | OL1-2R06-0016 | Instrument Cabinet | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1515-0004 | OL1-2R06-0013 | Machinery Monitoring System | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1522-0001 | OL1-2R07-0020 | Electrical And Instrument Interface Philosophy | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1541-0001 | OL1-2R06-0008 | Final Control Element | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1545-0001 | OL1-2R06-0021 | Pressure Safety Valve | 0 | IMP | TPSK-LSPA1-T-IE-00122 | 2018-10-03 | Transmitted |  |  | 2018-09-28 | IFI | C | ROC | IE | 3
036909C-1000-JSD-1547-0001 | OL1-2R06-0003 | Flow Measurement | 0 | IMP | TPSK-LSPA1-T-IE-00122 | 2018-10-03 | Transmitted |  |  | 2018-09-28 | IFI | C | ROC | IE | 3
036909C-1000-JSD-1572-0001 | OL1-2R06-0010 | Instrument Construction Material | 0 | IMP | TPSK-LSPA1-T-IE-00122 | 2018-10-03 | Transmitted |  |  | 2018-09-28 | IFI | C | ROC | IE | 3
036909C-1000-JSD-1572-0004 | OL1-2R08-0003 | Instrument Installation | 0 | IMP | TPSK-LSPA1-T-IE-00122 | 2018-10-03 | Transmitted |  |  | 2018-09-28 | IFI | C | ROC | IE | 3
036909C-1000-JSD-0000-0005 | OL1-2G01-0003 | Plate-Fin Exchanger Design Specification | A | IFR | TPSK-LSPA1-T-PE-00123 | 2018-10-03 | R1-No comments | 2018-10-12 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | PE | 2
036909C-1028-SP-1011-2850 | OL1-2M03-2850 | Mechanical Equipment Data Sheet for Ethylene Refrigeration Compressor | B | IFQ | TPSK-LSPA1-T-ME-00127 | 2018-10-03 | A3-Approved with comments, re-submit for review. | 2018-10-26 |  | 2018-10-02 | IFI | C | HOC | ME | 3
036909C-1000-MR-0661-0001 | OL1-2M55-0064 | Material Requisition For Plate And Frame Heat Exchangers Requisition For Inquiry | A | IFQ | TPSK-LSPA1-T-ME-00124 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-MR-0662-0002 | OL1-2M55-0066 | Material Requisition For Cold Box And Core Exchangers Requisition For Inquiry | A | IFQ | TPSK-LSPA1-T-ME-00125 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | H | ROC | ME | 2
036909C-1000-JSD-1600-003 | OL1-2E04-6000 | General Design Rule for Package Equipment Electrical System | B | IFR | TPSK-LSPA1-T-EE-00126 | 2018-10-04 | R1-No comments | 2018-10-12 | 2018-10-18 | 2018-10-20 | IFR | C | ROC | EE | 2
036909C-1028-SP-1011-2800 | OL1-2M03-2800 | Mechanical Equipment Data Sheet for Propylene Refrigeration Compressor | B | IFQ | TPSK-LSPA1-T-ME-00127 | 2018-10-03 | Transmitted |  |  | 2018-10-02 | IFI | C | HOC | ME | 3
036909C-1022-SP-1011-2200 | OL1-2M03-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor | B | IFQ | TPSK-LSPA1-T-ME-00127 | 2018-10-03 | Transmitted |  |  | 2018-10-02 | IFI | H | HOC | ME | 3
036909C-1000-NM-0001-1010 | OL1-2G44-1010 | Heat and Material Balance - ISBL Supporting Utilities | A | IFI | TPSK-LSPA1-T-PE-00128 | 2018-10-03 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1000-PP-551 | OL1-2S92-0001 | Project HSSE Plan | A | IFR | TPSK-LSPA1-T-ES-00129 | 2018-10-04 | Transmitted |  | 2018-10-18 | 2018-10-02 | IFR | C | ROC | ES | 2
036909C-1025-SP-1011-2550 | OL1-2M03-2550 | Mechanical Equipment Datasheet for Residue Gas Expander-Recompressor | B | IFQ | TPSK-LSPA1-T-ME-00130 | 2018-10-05 | A3-Approved with comments, re-submit for review. | 2018-10-26 |  | 2018-10-04 | IFI | C | HOC | ME | 3
036909C-1025-PDS-0600-2500 | OL1-2G30-2500 | Process Equipment Datasheet - 10-E-2500 - Propylene Refrig Subcooler | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0600-2505 | OL1-2G30-2505 | Process Equipment Datasheet - 10-E2506 and 10-E2508 - Demeth Prefrac Feed Cooler No 3 and No 4 | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0600-2541 | OL1-2G30-2541 | Process Equipment Datasheet - 10-E-2540 - Demethanizer Condenser | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0600-2587 | OL1-2G30-2587 | Process Equipment Datasheet - 10-E-2587 - C2 Tower Side Reboiler | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0600-2521 | OL1-2G30-2521 | Process Equipment Datasheet - 10-E-2520 - Rectifier Condenser | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0600-2526 | OL1-2G30-2526 | Process Equipment Datasheet - 10-E-2525 - Hydrogen Core Exchanger | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0600-2585 | OL1-2G30-2585 | Process Equipment Datasheet - 10-E-2585 - C2 Tower Bottoms Reboiler | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1028-PDS-0600-2882 | OL1-2G30-2882 | Process Equipment Datasheet - 10-E-2882 - LP Ethylene Product Cooler No 1 | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0600-2531 | OL1-2G30-2531 | Process Equipment Datasheet - 10-E-2530 - Demeth Feed Cooler | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0600-2511 | OL1-2G30-2511 | Process Equipment Datasheet - 10-E-2510 - Demeth Prefrac Condenser | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1028-PDS-0600-2884 | OL1-2G30-2884 | Process Equipment Datasheet - 10-E-2884 - LP Ethylene Product Cooler No 2 | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1000-DW-1702-0002 | OL1-2K92-0002 | General Notes For Precast Concrete Works | A | IFR | TPSK-LSPA1-T-CV-00137 | 2018-10-08 | Transmitted |  | 2018-10-22 | 2018-10-04 | IFR | C | ROC | CV | 2
036909C-1000-SL-0000-02 | OL1-2C01-0001 | Subvendor List For Compressor And Turboexpander - Abstract From Approved Vendor List | 0 | IMP | TPSK-LSPA1-T-PL-00134 | 2018-10-05 | Transmitted |  |  | 2018-10-05 | IFI | C | ROC | PL | 3
036909C-1000-JSD-1501-0001 | OL1-2R06-0022 | Instrument Numbering | A | IFR | TPSK-LSPA1-T-PE-00131 | 2018-10-05 | R2-Comments as noted | 2018-10-24 | 2018-10-19 | 2018-10-03 | IFR | C | ROC | IE | 2
036909C-1000-PLG-302 | OL1-2B92-0002 | 90 Days Look-Head Schedule | A | IFR | TPSK-LSPA1-T-PC-00133 | 2018-10-05 | R2-Comments as noted | 2018-10-26 | 2018-10-19 | 2018-10-04 | IFR | C | JVD | PC | 2
036909C-1000-SP-1011-0001 | OL1-2M57-0008 | Particular Technical Specification For Centrifugal Compressors Steam Turbine Driven | A | IFQ | TPSK-LSPA1-T-ME-00136 | 2018-10-08 | R2-Comments as noted | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFQ | C | ROC | ME | 2
036909C-1000-MR-1011-0001 | OL1-2M55-0008 | Material Requisition For Centrifugal Compressors Steam Turbine Driven | A | IFQ | TPSK-LSPA1-T-ME-00136 | 2018-10-08 | R1-No comments | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFQ | C | ROC | ME | 2
036909C-1000-ITP-1011-0001 | OL1-2M07-0008 | Inspection And Test Plan For Centrifugal Compressors Steam Turbine Driven | A | IFQ | TPSK-LSPA1-T-ME-00136 | 2018-10-08 | R2-Comments as noted | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFQ | C | ROC | ME | 2
036909C-1000-DL-1011-0001 | OL1-2M58-0008 | Deviation List For Centrifugal Compressors Steam Turbine Driven | A | IFQ | TPSK-LSPA1-T-ME-00136 | 2018-10-08 | R1-No comments | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFQ | C | ROC | ME | 2
036909C-1000-SR-1011-0001 | OL1-2M56-0008 | Scope Of Supply For Centrifugal Compressors Steam Turbine Driven | A | IFQ | TPSK-LSPA1-T-ME-00136 | 2018-10-08 | R2-Comments as noted | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFQ | C | ROC | ME | 2
036909C-1000-PLG-305 | OL1-2B01-0001 | Engineering And Procurement Level 3 Schedule | A | IFR | TPSK-LSPA1-T-PC-00135 | 2018-10-05 | A3-Approved with comments, re-submit for review. | 2018-10-26 | 2018-10-19 | 2018-10-05 | IFR | C | JVD | PC | 2
036909C-TPTI-TPSW-MOM-0003 |  | Monthly Meeting - Furnace Island Progress Review | 0 | IFQ | 036909C-JVD-TRN-INTERNAL-00010 | 2018-10-05 | Transmitted |  |  | 2018-09-25 | IFI | C | ROC | ME | Internal Doc
036909C-1000-PP-119 | OL1-2V92-0014 | Interface Management Plan | A | IFR | TPSK-LSPA1-T-IF-00138 | 2018-10-08 | R2-Comments as noted | 2018-10-25 | 2018-10-22 | 2018-09-20 | IFR | C | SK | IF | 2
036909C-1000-DL-1130-0001 | OL1-2M58-0012 | Deviation List For Residue Gas Expander/Recompressor | A | IFQ | TPSK-LSPA1-T-ME-00139 | 2018-10-09 | R1-No comments | 2018-10-26 | 2018-10-22 | 2018-10-05 | IFQ | C | ROC | ME | 2
036909C-1000-ITP-1130-0001 | OL1-2M07-0012 | Inspection And Test Plan For Residue Gas Expander/Recompressor | A | IFQ | TPSK-LSPA1-T-ME-00139 | 2018-10-09 | R2-Comments as noted | 2018-10-26 | 2018-10-22 | 2018-10-05 | IFQ | C | ROC | ME | 2
036909C-1000-SP-1130-0001 | OL1-2M57-0012 | Particular Technical Specification For Residue Gas Expander/Recompressor | A | IFQ | TPSK-LSPA1-T-ME-00139 | 2018-10-09 | R2-Comments as noted | 2018-10-26 | 2018-10-22 | 2018-10-05 | IFQ | C | ROC | ME | 2
036909C-1000-SR-1130-0001 | OL1-2M56-0012 | Scope Of Supply For Residue Gas Expander/Recompressor | A | IFQ | TPSK-LSPA1-T-ME-00139 | 2018-10-09 | R2-Comments as noted | 2018-10-26 | 2018-10-22 | 2018-10-05 | IFQ | C | ROC | ME | 2
036909C-1000-MR-1130-0001 | OL1-2M55-0012 | Material Requisition For Residue Gas Expander/Recompressor | A | IFQ | TPSK-LSPA1-T-ME-00139 | 2018-10-09 | R1-No comments | 2018-10-26 | 2018-10-22 | 2018-10-05 | IFQ | C | ROC | ME | 2
036909C-1000-PP-607 | OL1-2C92-0007 | Prescriptions For Preparation Of Documentation Package For Transportation | 0 | IMP | TPSK-LSPA1-T-PL-00140 | 2018-10-08 | R2-Comments as noted | 2018-10-30 | 2018-10-22 | 2018-10-05 | IMP | C | ROC | PL | 2
036909C-1000-PP-616 | OL1-2C92-0016 | Parking Marking And Shipping Instructions | 0 | IMP | TPSK-LSPA1-T-PL-00140 | 2018-10-08 | R2-Comments as noted | 2018-10-30 | 2018-10-22 | 2018-10-05 | IMP | C | ROC | PL | 2
036909C-1051-PDS-0900-5101 | OL1-2G30-5101 | Process Equipment Datasheet - 10-P-5100 A-C - SHP BFW Pumps | A | IFR | TPSK-LSPA1-T-PE-00141 | 2018-10-08 | R1-No comments | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFR | H | HOC | PE | 2
036909C-1051-PDS-0900-5102 | OL1-2G30-5102 | Process Equipment Datasheet - 10-P-5102 A-B - VLP BFW Pumps | A | IFR | TPSK-LSPA1-T-PE-00141 | 2018-10-08 | R1-No comments | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFR | H | HOC | PE | 2
036909C-1051-PDS-0900-5109 | OL1-2G30-5109 | Process Equipment Datasheet - 10-P-5110 A-B - Condensate Pumps | A | IFR | TPSK-LSPA1-T-PE-00141 | 2018-10-08 | R1-No comments | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFR | H | HOC | PE | 2
036909C-1055-PDS-0800-5550 | OL1-2G30-5550 | Process Equipment Datasheet - 10-D-5550 - HP Flare Knock-Out Drum | A | IFR | TPSK-LSPA1-T-PE-00142 | 2018-10-08 | R2-Comments as noted | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0600-2101 | OL1-2G30-2101 | Process Equipment Datasheet - 10-E-2100 A-F - Quench Water Cooler | B | IFD | TPSK-LSPA1-T-PE-00143 | 2018-10-08 | Transmitted |  |  | 2018-10-04 | IFI | C | HOC | PE | 3
036909C-1022-PDS-0800-2210 | OL1-2G30-2210 | Process Equipment Datasheet - 10-D-2210 - CG 1st Stage Suction Drum | A | IFR | TPSK-LSPA1-T-PE-00144 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-08 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0800-2220 | OL1-2G30-2220 | Process Equipment Datasheet - 10-D-2220 - CG 2nd Stage Suction Drum | A | IFR | TPSK-LSPA1-T-PE-00144 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-08 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0800-2230 | OL1-2G30-2230 | Process Equipment Datasheet - 10-D-2230 - CG 3rd Stage Suction Drum | A | IFR | TPSK-LSPA1-T-PE-00144 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-08 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2810 | OL1-2G30-2810 | Process Equipment Datasheet - 10-D-2810 - C3R 1st Stage Suction Drum | A | IFR | TPSK-LSPA1-T-PE-00144 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-08 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2820 | OL1-2G30-2820 | Process Equipment Datasheet - 10-D-2820 - C3R 2nd Stage Suction Drum | A | IFR | TPSK-LSPA1-T-PE-00144 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-08 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2830 | OL1-2G30-2830 | Process Equipment Datasheet - 10-D-2830 - C3R 3rd Stage Suction Drum | A | IFR | TPSK-LSPA1-T-PE-00144 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-08 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2840 | OL1-2G30-2840 | Process Equipment Datasheet - 10-D-2840 - C3R 4th Stage Suction Drum | A | IFR | TPSK-LSPA1-T-PE-00144 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-08 | IFR | C | HOC | PE | 2
036909C-1000-PP-133 | OL1-2W92-0011 | TPSK HOC Organization Chart | 0 | IFI | TPSK-LSPA1-T-PM-00146 | 2018-10-09 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PC | 3
036909C-1000-DW-1422-0001 | OL1-2K43-0004 | Soil Investigation Plan | A | IFR | TPSK-LSPA1-T-CV-00145 | 2018-10-10 | Transmitted |  | 2018-10-24 | 2018-10-04 | IFR | H | ROC | CV | 2
036909C-1000-MS-1422-0001 | OL1-2K43-0002 | Technical Specification For Geotechnical Investigation | A | IFR | TPSK-LSPA1-T-CV-00147 | 2018-10-10 | Transmitted |  | 2018-10-24 | 2018-10-04 | IFR | H | ROC | CV | 2
036909C-1000-PS-1422-0001 | OL1-2K43-0003 | Price List For Geotechnical Investigation | A | IFR | TPSK-LSPA1-T-CV-00147 | 2018-10-10 | Transmitted |  | 2018-10-24 | 2018-10-04 | IFR | H | ROC | CV | 2
036909C-1000-JSD-1580-0001 | OL1-2R06-0017 | Integrated Turbine And Compressor Control System | A | IFR | TPSK-LSPA1-T-IE-00148 | 2018-10-10 | R1-No comments | 2018-10-24 | 2018-10-24 | 2018-10-08 | IFR | C | ROC | IE | 2
036909C-1000-PP-923 | OL1-2R07-0010 | Equipment Preservation | 0 | IMP | TPSK-LSPA1-T-PE-00149 | 2018-10-09 | Transmitted |  |  | 2018-10-09 | IMP | C | ROC | ME | 3
036909C-1030-DI-0007-3001 | OL1-2G05-3001 | Area Basis of Design - 30 BDU | A | IFA | TPSK-LSPA1-T-PE-00150 | 2018-10-09 | Transmitted |  | 2018-10-23 | 2018-10-09 | IFA | C | HOC | PE | 1
036909C-1051-PDS-0800-5100 | OL1-2G30-5100 | Process Equipment Data Sheet - 10-D-5100 - Deaerator | A | IFR | TPSK-LSPA1-T-PE-00151 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-09 | IFR | H | HOC | PE | 2
036909C-1000-PP-552 | OL1-2S92-0002 | Incident Investigation And Reporting Procedure | A | IFR | TPSK-LSPA1-T-ES-00152 | 2018-10-10 | Transmitted |  | 2018-10-24 | 2018-10-05 | IFR | C | JVD | ES | 2
036909C-1000-MR-0662-0002 | OL1-2M55-0066 | Material Requisition For Cold Box And Core Exchangers Requisition For Inquiry | B | IFQ | TPSK-LSPA1-T-ME-00153 | 2018-10-10 | R1-No comments | 2018-11-02 | 2018-10-24 | 2018-10-09 | IFQ | C | ROC | ME | 2
036909C-1000-JSD-0600-0001 |  | Basis of Design for Heat Exchangers | B | IFI | 036909C-JVD-TRN-INTERNAL-00011 | 2018-10-10 | Transmitted |  |  | 2018-10-08 | IFI | C | HOC | ME | Internal Doc
036909C-1021-TDS-0661-2101 | OL1-2M03-2101 | Mechanical Equipment Data Sheet - 10-E-2100 - Quench Water Cooler | B | IFQ | TPSK-LSPA1-T-ME-00154 | 2018-10-10 | R1-No comments | 2018-11-07 |  | 2018-10-09 | IFI | C | HOC | ME | 3
036909C-1000-PFD-0010-0010 | OL1-2G40-0010 | Block Flow Diagram - Olefins Unit 10 - 00-General - Overall Plant Scheme | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1000-PFD-0010-0001 | OL1-2G41-0001 | Process Flow Diagram - Olefins Unit 10 - 00-General - Legend & Symbols | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1000-PFD-0010-0002 | OL1-2G41-0002 | Process Flow Diagram - Olefins Unit 10 - 00-General - Drawing Index | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1010-PFD-0010-1001 | OL1-2G41-1001 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1010-PFD-0010-1003 | OL1-2G41-1003 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1011-PFD-0010-1101 | OL1-2G41-1101 | Process Flow Diagram - Olefins Unit 10 - 11 - Furnaces - Recycle Gas Cracking Furnace | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1012-PFD-0010-1201 | OL1-2G41-1201 | Process Flow Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1019-PFD-0010-1901 | OL1-2G41-1901 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1019-PFD-0010-1902 | OL1-2G41-1902 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1020-PFD-0010-2001 | OL1-2G41-2001 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1020-PFD-0010-2002 | OL1-2G41-2002 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1021-PFD-0010-2101 | OL1-2G41-2101 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1021-PFD-0010-2102 | OL1-2G41-2102 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1021-PFD-0010-2103 | OL1-2G41-2103 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1022-PFD-0010-2201 | OL1-2G41-2201 | Process Flow Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1023-PFD-0010-2301 | OL1-2G41-2301 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1023-PFD-0010-2302 | OL1-2G41-2302 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1023-PFD-0010-2303 | OL1-2G41-2303 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1023-PFD-0010-2304 | OL1-2G41-2304 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1023-PFD-0010-2305 | OL1-2G41-2305 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1024-PFD-0010-2401 | OL1-2G41-2401 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1024-PFD-0010-2402 | OL1-2G41-2402 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1024-PFD-0010-2403 | OL1-2G41-2403 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1024-PFD-0010-2404 | OL1-2G41-2404 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1024-PFD-0010-2405 | OL1-2G41-2405 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1025-PFD-0010-2501 | OL1-2G41-2501 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1025-PFD-0010-2502 | OL1-2G41-2502 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1025-PFD-0010-2503 | OL1-2G41-2503 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1025-PFD-0010-2504 | OL1-2G41-2504 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1025-PFD-0010-2505 | OL1-2G41-2505 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1025-PFD-0010-2506 | OL1-2G41-2506 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1026-PFD-0010-2601 | OL1-2G41-2601 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1026-PFD-0010-2602 | OL1-2G41-2602 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1026-PFD-0010-2603 | OL1-2G41-2603 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1026-PFD-0010-2604 | OL1-2G41-2604 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1027-PFD-0010-2701 | OL1-2G41-2701 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Reactor & Depentanizer | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1027-PFD-0010-2702 | OL1-2G41-2702 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Rerun Tower | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1027-PFD-0010-2703 | OL1-2G41-2703 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - Hydrog Reactivation Gas System | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1027-PFD-0010-2704 | OL1-2G41-2704 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1028-PFD-0010-2801 | OL1-2G41-2801 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1028-PFD-0010-2802 | OL1-2G41-2802 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1028-PFD-0010-2803 | OL1-2G41-2803 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1028-PFD-0010-2804 | OL1-2G41-2804 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1029-PFD-0010-2901 | OL1-2G41-2901 | Process Flow Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1030-PFD-0010-3001 | OL1-2G41-3001 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1030-PFD-0010-3002 | OL1-2G41-3002 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Evaporation | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1030-PFD-0010-3003 | OL1-2G41-3003 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1030-PFD-0010-3004 | OL1-2G41-3004 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1030-PFD-0010-3005 | OL1-2G41-3005 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1031-PFD-0010-3101 | OL1-2G41-3101 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1031-PFD-0010-3102 | OL1-2G41-3102 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam and Condensate System | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1039-PFD-0010-3901 | OL1-2G41-3901 | Process Flow Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1050-PFD-0030-5001 | OL1-2G42-5001 | Utility Flow Diagram - Olefins Unit 10 - 50 - Water System - Treated Potable and Demin Water Systems | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1051-PFD-0030-5101 | OL1-2G42-5101 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Steam Balance Diagram | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1051-PFD-0030-5102 | OL1-2G42-5102 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate and Boiler Feedwater Systems | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1051-PFD-0030-5103 | OL1-2G42-5103 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate Treatment System | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1051-PFD-0030-5104 | OL1-2G42-5104 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Furnace Blowdown System | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1052-PFD-0030-5201 | OL1-2G42-5201 | Utility Flow Diagram - Olefins Unit 10 - 52 - Fuel System - Fuel Gas System | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1053-PFD-0030-5301 | OL1-2G42-5301 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Water Diagram | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1053-PFD-0030-5311 | OL1-2G42-5311 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Tower | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1054-PFD-0030-5401 | OL1-2G42-5401 | Utility Flow Diagram - Olefins Unit 10 - 54 - Air and Nitrogen System - Plant Air Instrument Air and Nitrogen Systems | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1055-PFD-0030-5501 | OL1-2G42-5501 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Flare and Blowdown System | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1055-PFD-0030-5502 | OL1-2G42-5502 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Process Vent Gas Collection | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1055-PFD-0030-5511 | OL1-2G42-5511 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - HP - LLDPE LP Flare | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1055-PFD-0030-5512 | OL1-2G42-5512 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Enclosed Ground Flare | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5601 | OL1-2G42-5601 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Collection | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5602 | OL1-2G42-5602 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Surface Runoff Collection | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5603 | OL1-2G42-5603 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Cracker Holding Basin | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5604 | OL1-2G42-5604 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Domestic Wastewater Collection | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5610 | OL1-2G42-5610 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - HP Flare Area SW & Oily WW Collection | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5611 | OL1-2G42-5611 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - OSBL Oily Wastewater Collection | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5612 | OL1-2G42-5612 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Equalization Tank | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5613 | OL1-2G42-5613 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - CPI & IGF Packages | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5614 | OL1-2G42-5614 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Biotreatment Package | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 3
036909C-1056-PFD-0030-5615 | OL1-2G42-5615 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Check Basin | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5616 | OL1-2G42-5616 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Sludge Dewatering Package | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5617 | OL1-2G42-5617 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Slop & Oil Sludge | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1059-PFD-0030-5901 | OL1-2G42-5901 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Chemical Storage | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1059-PFD-0030-5911 | OL1-2G42-5911 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Complex U & O Chemical Storage | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1000-PP-125 | OL1-2W92-0019 | Project Control Procedure | 0 | IMP | TPSK-LSPA1-T-PC-00156 | 2018-10-11 | Transmitted |  |  | 2018-10-05 | IMP | C | JVD | PC | 3
036909C-1000-PP-134 | OL1-2W92-0020 | TPSK SOC Organization Chart | 0 | IFI | TPSK-LSPA1-T-PC-00157 | 2018-10-11 | Transmitted |  |  | 2018-10-11 | IFI | C | SK | PC | 3
036909C-1000-JSS-1013-0001 | OL1-2R03-0016 | ME-016 Centrifugal Compressor For PA/IA Servise | A | IFR | TPSK-LSPA1-T-ME-00164 | 2018-10-12 | R1-No comments | 2018-11-07 | 2018-10-26 | 2018-10-09 | IFR | C | ROC | ME | 2
036909C-1000-DW-1422-0001 | OL1-2K43-0004 | Soil Investigation Plan | B | IFR | TPSK-LSPA1-T-CV-00163 | 2018-10-12 | Transmitted |  | 2018-10-26 | 2018-10-10 | IFR | C | ROC | CV | 2
036909C-1000-JSD-2000-0001 | OL1-2R02-0005 | Buildings Design And Construction | A | IFR | TPSK-LSPA1-T-CV-00158 | 2018-10-11 | Transmitted |  | 2018-10-25 | 2018-10-10 | IFR | C | ROC | CV | 2
036909C-1011-PDS-0811-1107 | OL1-2G30-1107 | Process Equipment Datasheet - 10-D-1100 - 36M Cracking Furnace Steam Drum | A | IFR | TPSK-LSPA1-T-PE-00159 | 2018-10-11 | R2-Comments as noted | 2018-11-05 | 2018-10-25 | 2018-10-11 | IFR | C | HOC | PE | 2
036909C-1012-PDS-0811-1207 | OL1-2G30-1207 | Process Equipment Datasheet - 10-D-1200-1600 - 132U Cracking Furnace Steam Drum | A | IFR | TPSK-LSPA1-T-PE-00159 | 2018-10-11 | R2-Comments as noted | 2018-11-05 | 2018-10-25 | 2018-10-11 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0500-2330 | OL1-2G30-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper | B | IFA | TPSK-LSPA1-T-PE-00160 | 2018-10-11 | Transmitted |  | 2018-10-25 | 2018-10-10 | IFA | C | HOC | PE | 1
036909C-1019-SP-1013-1950 | OL1-2M03-1950 | Mechanical Equipment Datasheet for Decoke Air Compressor Package | B | IFQ | TPSK-LSPA1-T-ME-00161 | 2018-10-11 | Transmitted |  |  | 2018-10-10 | IFI | H | HOC | ME | 3
036909C-1020-PDS-0500-2000 | OL1-2G30-2000 | Process Equipment Datasheet - 10-T-2000 - Quench Oil Tower | A | IFR | TPSK-LSPA1-T-PE-00162 | 2018-10-12 | R2-Comments as noted | 2018-11-05 | 2018-10-26 | 2018-10-11 | IFR | C | HOC | PE | 2
036909C-1020-PDS-0500-2040 | OL1-2G30-2040 | Process Equipment Datasheet - 10-T-2040 - Heavy Fuel Oil Stripper | A | IFR | TPSK-LSPA1-T-PE-00162 | 2018-10-12 | R2-Comments as noted | 2018-11-05 | 2018-10-26 | 2018-10-11 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0500-2580 | OL1-2G30-2580 | Process Equipment Datasheet - 10-T-2580 - C2 Tower | A | IFR | TPSK-LSPA1-T-PE-00162 | 2018-10-12 | R2-Comments as noted | 2018-10-31 | 2018-10-26 | 2018-10-11 | IFR | C | HOC | PE | 2
036909C-1000-JSD-3400-0001 | OL1-2H03-0001 | Air Conditioning Ventilating And Ducting Design | A | IFR | TPSK-LSPA1-T-EE-00165 | 2018-10-12 | R2-Comments as noted | 2018-10-26 | 2018-10-26 | 2018-10-12 | IFR | C | ROC | EE | 2
036909C-1000-JSS-1160-0001 | OL1-2R03-0022 | ME-022 Special Purpose Gear | A | IFR | TPSK-LSPA1-T-ME-00166 | 2018-10-12 | R1-No comments | 2018-11-07 | 2018-10-26 | 2018-10-12 | IFR | C | ROC | ME | 2
036909C-1024-PDS-0500-2440 | OL1-2G30-2440 | Process Equipment Datasheet - 10-T-2440 - HP Depropanizer | B | IFD | TPSK-LSPA1-T-PE-00167 | 2018-10-12 | Transmitted |  |  | 2018-10-11 | IFI | C | HOC | PE | 3
036909C-1024-PDS-0500-2450 | OL1-2G30-2450 | Process Equipment Datasheet - 10-T-2450 - LP Depropanizer | B | IFD | TPSK-LSPA1-T-PE-00167 | 2018-10-12 | Transmitted |  |  | 2018-10-11 | IFI | C | HOC | PE | 3
036909C-1055-PDS-0800-5500 | OL1-2G30-5500 | Process Equipment Datasheet - 10-D-5500 - Hot Flare Drum | A | IFR | TPSK-LSPA1-T-PE-00168 | 2018-10-12 | R2-Comments as noted | 2018-11-14 | 2018-10-26 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1026-PDS-0500-2630 | OL1-2G30-2630 | Process Equipment Datasheet - 10-T-2630 - Secondary Deethanizer | B | IFD | TPSK-LSPA1-T-PE-00169 | 2018-10-12 | Transmitted |  |  | 2018-10-12 | IFI | C | HOC | PE | 3
036909C-1026-PDS-0500-2660 | OL1-2G30-2660 | Process Equipment Datasheet - 10-T-2660 - Debutanizer | B | IFD | TPSK-LSPA1-T-PE-00169 | 2018-10-12 | Transmitted |  |  | 2018-10-12 | IFI | C | HOC | PE | 3
036909C-1000-PP-124 | OL1-2W92-0018 | Engineering Execution Plan | 0 | IFI | TPSK-LSPA1-T-PM-00170 | 2018-10-15 | Transmitted |  |  | 2018-10-12 | IFI | C | ROC | PC | 3
036909C-1000-PP-132 | OL1-2W92-0021 | TPSK KLOC Organization Chart | 0 | IFI | TPSK-LSPA1-T-PC-00171 | 2018-10-15 | Transmitted |  |  | 2018-10-15 | IFI | C | KLOC | PC | 3
036909C-1025-PDS-0500-2520 | OL1-2G30-2520 | Process Equipment Datasheet - 10-T-2520 and 10-D-2520 - Residue Gas Rectifier & Reflux Drum | A | IFR | TPSK-LSPA1-T-PE-00172 | 2018-10-15 | R2-Comments as noted | 2018-11-05 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-4200-2301 | OL1-2G30-2301 | Process Equipment Datasheet - 10-X-2300 - Caustic Dilution Mixer | A | IFR | TPSK-LSPA1-T-PE-00173 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-4200-2308 | OL1-2G30-2308 | Process Equipment Datasheet - 10-X-2306 - Weak Caustic - Wash Oil Mixer | A | IFR | TPSK-LSPA1-T-PE-00173 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-4200-2313 | OL1-2G30-2313 | Process Equipment Datasheet - 10-X-2312 - Spent Wash Oil Mixer | A | IFR | TPSK-LSPA1-T-PE-00173 | 2018-10-15 | R1-No comments | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-4200-2315 | OL1-2G30-2315 | Process Equipment Datasheet - 10-X-2310 - Spent Caustic Mixer | A | IFR | TPSK-LSPA1-T-PE-00173 | 2018-10-15 | R1-No comments | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0900-2302 | OL1-2G30-2302 | Process Equipment Datasheet - 10-P-2302 A-B - Strong Caustic Circulating Pumps | A | IFR | TPSK-LSPA1-T-PE-00174 | 2018-10-15 | R1-No comments | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0900-2304 | OL1-2G30-2304 | Process Equipment Datasheet - 10-P-2304 - Intermediate Caustic Circulating Pump | A | IFR | TPSK-LSPA1-T-PE-00174 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0900-2306 | OL1-2G30-2306 | Process Equipment Datasheet - 10-P-2306 A-B - Weak Caustic Circulating Pumps | A | IFR | TPSK-LSPA1-T-PE-00174 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0900-2311 | OL1-2G30-2311 | Process Equipment Datasheet - 10-P-2310 A-B - Wash Oil Circulating Pumps | A | IFR | TPSK-LSPA1-T-PE-00174 | 2018-10-15 | R1-No comments | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0800-2331 | OL1-2G30-2331 | Process Equipment Datasheet - 10-D-2330 - Spent Caustic Stripper Ovhd Drum | A | IFR | TPSK-LSPA1-T-PE-00175 | 2018-10-15 | Transmitted |  | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0800-2316 | OL1-2G30-2316 | Process Equipment Datasheet - 10-D-2316 - Spent Caustic Degassing Drum | A | IFR | TPSK-LSPA1-T-PE-00175 | 2018-10-15 | Transmitted |  | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0800-2240 | OL1-2G30-2240 | Process Equipment Datasheet - 10-D-2240 - CG 4th Stage Suction Drum | A | IFR | TPSK-LSPA1-T-PE-00175 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1010-PDS-0600-1015 | OL1-2G30-1015 | Process Equipment Datasheet - 10-E-1015 - LPG Superheater | A | IFR | TPSK-LSPA1-T-PE-00176 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1010-PDS-0600-1005 | OL1-2G30-1005 | Process Equipment Datasheet - 10-E-1005 - LPG Feed Heater | A | IFR | TPSK-LSPA1-T-PE-00176 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1010-PDS-0600-1001 | OL1-2G30-1001 | Process Equipment Datasheet - 10-E-1000 - LPG Vaporizer | A | IFR | TPSK-LSPA1-T-PE-00176 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1000-PP-615 | OL1-2C92-0015 | Transportation Plan | 0 | IMP | TPSK-LSPA1-T-PL-00177 | 2018-10-16 | R2-Comments as noted | 2018-10-30 | 2018-10-30 | 2018-10-16 | IMP | C | JVD | PL | 2
036909C-LSPA1-TPSK-MOM-0028 | LSPA1-TPSK-M-0028 | Project KOM | 0 | IFI | TPSK-LSPA1-T-PM-00178 | 2018-10-16 | Transmitted |  |  | 2018-10-11 | IFI | C | JVD | PM | 3
036909C-LSPA1-TPSK-MOM-0029 | LSPA1-TPSK-M-0029 | Flare System | 0 | IFI | TPSK-LSPA1-T-PM-00178 | 2018-10-16 | Transmitted |  |  | 2018-10-09 | IFI | C | JVD | PM | 3
036909C-1010-PDS-0600-1003 | OL1-2G30-1003 | Process Equipment Datasheet - 10-E-1001 - LPG Steam Vaporizer | A | IFR | TPSK-LSPA1-T-PE-00179 | 2018-10-16 | Transmitted |  | 2018-10-30 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1023-PDS-4100-2350 | OL1-2G30-2350 | Process Equipment Datasheet - 10-PK-2350 - Wet Air Oxidation Pkg | A | IFR | TPSK-LSPA1-T-PE-00180 | 2018-10-16 | Transmitted |  | 2018-10-30 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1029-PDS-2600-2914 | OL1-2G30-2914 | Process Equipment Datasheet - 10-PK-2914 - Neutralization Injection Pkg | A | IFR | TPSK-LSPA1-T-PE-00181 | 2018-10-16 | Transmitted |  | 2018-10-30 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1011-DW-0127-1204 | OL1-2M06-1204 | USC 36M Recycle Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill Of Material | A | IFR | TPSK-LSPA1-T-ME-00182 | 2018-10-16 | Transmitted |  | 2018-10-30 | 2018-10-12 | IFR | C | HOC | ME | 2
036909C-1012-DW-0127-2204 | OL1-2M06-2204 | USC 132U Cracking Furnace Fabricatin Assembly of Convection Coils Finned Tubes and Bill of Material | A | IFR | TPSK-LSPA1-T-ME-00182 | 2018-10-16 | Transmitted |  | 2018-10-30 | 2018-10-12 | IFR | C | HOC | ME | 2
036909C-1006-JSS-0117-0029 | OL1-2R03-0029 | ME-029 Centrifugal Blower for 36M and 132U Furnace | 0 | IMP | TPSK-LSPA1-T-ME-00185 | 2018-10-17 | R1-No comments | 2018-11-05 | 2018-10-31 | 2018-10-16 | IMP | C | HOC | ME | 3
036909C-1024-SP-0510-2450 | OL1-2M03-2450 | Mechanical Equipment Datasheet LP Depropanizer | A | IFQ | TPSK-LSPA1-T-ME-00183 | 2018-10-16 | A3-Approved with comments, re-submit for review. | 2018-11-05 | 2018-10-30 | 2018-10-15 | IFR | H | HOC | ME | 2
036909C-1006-JSS-0117-1004 | OL1-2R04-1004 | PIP-004 Piping Welding Specification for 36M and 132U Furnace | 0 | IMP | TPSK-LSPA1-T-ME-00184 | 2018-10-16 | Transmitted |  |  | 2018-10-15 | IFE | C | HOC | ME | 3
036909C-1000-NM-107 | OL1-2W91-0001 | Master Document Index (MDI) | 0 | IFI | TPSK-LSPA1-T-PM-00186 | 2018-10-17 | Transmitted |  |  | 2018-10-16 | IFI | C | ROC | PC | 3
036909C-1000-RT-200 | OL1-2W90-0001 | Fire Fighting Basic Design Report For Package A1 | 1 | IFI | TPSK-LSPA1-T-PM-00187 | 2018-10-17 | Transmitted |  |  | 2018-09-28 | IFI | C | ROC | PC | 3
036909C-1012-SP-0122-2004 | OL1-2M57-2004 | Particular Technical Specification For Radiant Coil Assemblies | A | IFI | TPSK-LSPA1-T-ME-00063 | 2018-09-18 | Transmitted |  |  | 2018-09-10 | IFI | C | HOC | ME | 3
036909C-1021-PDS-0500-2140 | OL1-2G30-2140 | Process Equipment Datasheet - 10-T-2140 - Process Water Stripper | A | IFR | TPSK-LSPA1-T-PE-00189 | 2018-10-17 | Transmitted |  | 2018-10-31 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1025-PDS-4100-2560 | OL1-2G30-2560 | Process Equipment Datasheet - 10-PK-2560 - PSA Unit | A | IFR | TPSK-LSPA1-T-PE-00190 | 2018-10-17 | R2-Comments as noted | 2018-11-05 | 2018-10-31 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0500-2570 | OL1-2G30-2570 | Process Equipment Datasheet - 10-T-2570 - Deethanizer | A | IFR | TPSK-LSPA1-T-PE-00191 | 2018-10-17 | R2-Comments as noted | 2018-11-05 | 2018-10-31 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1000-PP-313 | OL1-2A92-0002 | Car & Third Party Insurance Claim Procedure | 0 | IFI | TPSK-LSPA1-T-CO-00192 | 2018-10-18 | R2-Comments as noted | 2018-10-26 |  | 2018-10-18 | IFI | C | JVD | CO | 3
036909C-1000-PP-703 | OL1-2D92-0001 | Construction Subcontracting Plan | A | IFR | TPSK-LSPA1-T-CM-00193 | 2018-10-18 | Transmitted |  | 2018-11-01 | 2018-10-18 | IFR | C | SK | CM | 2
036909C-1021-PDS-0600-2137 | OL1-2G30-2137 | Process Equipment Datasheet - 10-E-2136 - Process Water Stripper Feed Heater | A | IFR | TPSK-LSPA1-T-PE-00194 | 2018-10-18 | Transmitted |  | 2018-11-01 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0600-2145 | OL1-2G30-2145 | Process Equipment Datasheet - 10-E-2145 - Process Water Stripper Reboiler | A | IFR | TPSK-LSPA1-T-PE-00194 | 2018-10-18 | Transmitted |  | 2018-11-01 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0600-2147 | OL1-2G30-2147 | Process Equipment Datasheet - 10-E-2146 - DSG Feed Heater | A | IFR | TPSK-LSPA1-T-PE-00194 | 2018-10-18 | Transmitted |  | 2018-11-01 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0600-2161 | OL1-2G30-2161 | Process Equipment Datasheet - 10-E-2160 - Dilution Steam Superheater | A | IFR | TPSK-LSPA1-T-PE-00194 | 2018-10-18 | Transmitted |  | 2018-11-01 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0600-2165 | OL1-2G30-2165 | Process Equipment Datasheet - 10-E-2165 A-D DSG Reboilers | A | IFR | TPSK-LSPA1-T-PE-00194 | 2018-10-18 | Transmitted |  | 2018-11-01 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1000-PP-117 | OL1-2W92-0012 | ITC Plan | A | IFR | TPSK-LSPA1-T-PM-00197 | 2018-10-19 | Transmitted |  | 2018-11-02 | 2018-10-15 | IFR | C | JVD | PC | 2
036909C-1000-MR-1013-0001 | OL1-2M55-0014 | Material Requisition For Integrally Geared Decoking Air Compressors | A | IFQ | TPSK-LSPA1-T-ME-00198 | 2018-10-19 | R1-No comments | 2018-11-07 | 2018-11-02 | 2018-10-18 | IFQ | C | ROC | ME | 2
036909C-1000-ITP-1013-0001 | OL1-2M07-0014 | Inspection And Test Plan For Integrally Geared Decoking Air Compressors | A | IFQ | TPSK-LSPA1-T-ME-00198 | 2018-10-19 | R2-Comments as noted | 2018-11-07 | 2018-11-02 | 2018-10-18 | IFQ | C | ROC | ME | 2
036909C-1000-SP-1013-0001 | OL1-2M57-0014 | Particular Technical Specification for Integrally Geared Decoking Air Compressors | A | IFQ | TPSK-LSPA1-T-ME-00198 | 2018-10-19 | R1-No comments | 2018-11-07 | 2018-11-02 | 2018-10-18 | IFQ | C | ROC | ME | 2
036909C-1000-DL-1013-0001 | OL1-2M58-0014 | Deviation List For Integrally Geared Decoking Air Compressors | A | IFQ | TPSK-LSPA1-T-ME-00198 | 2018-10-19 | R1-No comments | 2018-11-07 | 2018-11-02 | 2018-10-18 | IFQ | C | ROC | ME | 2
036909C-1000-SR-1013-0001 | OL1-2M56-0014 | Scope Of Supply For Integrally Geared Decoking Air Compressors | A | IFQ | TPSK-LSPA1-T-ME-00198 | 2018-10-19 | R1-No comments | 2018-11-07 | 2018-11-02 | 2018-10-18 | IFQ | C | ROC | ME | 2
036909C-1000-PP-502 | OL1-2Q92-0002 | Confidentiality Plan | A | IFR | TPSK-LSPA1-T-QM-00199 | 2018-10-19 | Transmitted |  | 2018-11-02 | 2018-10-18 | IFR | C | JVD | QM | 2
036909C-1000-MS-1422-0001 | OL1-2K43-0002 | Technical Specification for Geotechnical Investigation | B | IFR | TPSK-LSPA1-T-CV-00188 | 2018-10-17 | R1-No comments | 2018-11-01 | 2018-11-05 | 2018-10-15 | IFR | C | ROC | CV | 2
036909C-1000-PS-1422-0001 | OL1-2K43-0003 | Price List for Geotechnical Investigation | B | IFR | TPSK-LSPA1-T-CV-00188 | 2018-10-17 | R1-No comments | 2018-11-01 | 2018-11-05 | 2018-10-15 | IFR | C | ROC | CV | 2
036909C-LSPA1-TPSK-MOM-0030 | LSPA1-TPSK-M-0030 | Technical Item Discussion | 0 | IFI | TPSK-LSPA1-T-PM-00200 | 2018-10-22 | Transmitted |  |  | 2018-10-12 | IFI | C | JVD | PM | 3
036909C-1020-PDS-0900-2006 | OL1-2G30-2006 | Process Equipment Datasheet - 10-P-2006 A-C - Quench Oil Pumps | B | IFD | TPSK-LSPA1-T-PE-00202 | 2018-10-22 | Transmitted |  |  | 2018-10-18 | IFI | C | HOC | PE | 1
036909C-1021-PDS-0900-2106 | OL1-2G30-2106 | Process Equipment Datasheet - 10-P-2106 A-C - Quench Water Pumps | B | IFD | TPSK-LSPA1-T-PE-00202 | 2018-10-22 | Transmitted |  |  | 2018-10-18 | IFI | C | HOC | PE | 1
036909C-1021-PDS-0900-2146 | OL1-2G30-2146 | Process Equipment Datasheet - 10-P-2146 A-B - DSG Feed Pumps | B | IFD | TPSK-LSPA1-T-PE-00202 | 2018-10-22 | Transmitted |  |  | 2018-10-18 | IFI | C | HOC | PE | 1
036909C-1026-PDS-0500-2640 | OL1-2G30-2640 | Process Equipment Datasheet - 10-T-2640 - C3 Tower | A | IFR | TPSK-LSPA1-T-PE-00201 | 2018-10-22 | R2-Comments as noted | 2018-11-05 | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1000-RR-5000 | OL1-2W95-5000 | Monthly Progress Report As Of October 15th 2018 | 0 | IFI | TPSK-LSPA1-T-PC-00195 | 2018-10-22 | Transmitted |  | 2018-11-07 | 2018-10-22 | IFI | C | JVD | PC | 2
036909C-1023-PDS-2500-2320 | OL1-2G30-2320 | Process Equipment Datasheet - 10-TK-2320 - Spent Caustic Storage Tank | B | IFD | TPSK-LSPA1-T-PE-00203 | 2018-10-22 | Transmitted |  |  | 2018-10-18 | IFI | C | HOC | PE | 1
036909C-1012-PDS-0117-1201 | OL1-2G30-1201 | Process Equipment Datasheet - 10-H-1200 - 132U Cracking Furnace Yields | A | IFR | TPSK-LSPA1-T-PE-00204 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1011-PDS-0117-1101 | OL1-2G30-1101 | Process Equipment Datasheet - 10-H-1100 - 36M Cracking Furnace Yields | A | IFR | TPSK-LSPA1-T-PE-00204 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0840-2307 | OL1-2G30-2307 | Process Equipment Datasheet - 10-F-2306 A-B - Weak Caustic Circulating Filters | A | IFR | TPSK-LSPA1-T-PE-00205 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0840-2314 | OL1-2G30-2314 | Process Equipment Datasheet - 10-F-2310 A-B - Wash Oil Circulating Filter | A | IFR | TPSK-LSPA1-T-PE-00205 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1010-PDS-0600-1020 | OL1-2G30-1020 | Process Equipment Datasheet - 10-E-1020 - Liquid Feed Heater | A | IFR | TPSK-LSPA1-T-PE-00206 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0600-2221 | OL1-2G30-2221 | Process Equipment Datasheet - 10-E-2220 A-B - CG 2nd Stage Aftercoolers | A | IFR | TPSK-LSPA1-T-PE-00206 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1010-PDS-0600-1051 | OL1-2G30-1051 | Process Equipment Datasheet - 10-E-1050 - C2 Feed Superheater | A | IFR | TPSK-LSPA1-T-PE-00206 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0600-2231 | OL1-2G30-2231 | Process Equipment Datasheet - 10-E-2230 A-B - CG 3rd Stage Aftercooler | A | IFR | TPSK-LSPA1-T-PE-00206 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0600-2241 | OL1-2G30-2241 | Process Equipment Datasheet - 10-E-2240 A-B - CG 4th Stage Aftercooler | A | IFR | TPSK-LSPA1-T-PE-00206 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1012-MR-0127-2002 | OL1-2M55-2002 | Material Requisition for Furnace Convection Fittings | A | IFQ | TPSK-LSPA1-T-ME-00207 | 2018-10-22 | Transmitted |  |  | 2018-10-16 | IFQ | C | HOC | ME | 3
036909C-1012-ITP-0127-2002 | OL1-2M07-2002 | Inspection and Test Plan For Furnace Convection Fittings | A | IFQ | TPSK-LSPA1-T-ME-00207 | 2018-10-22 | Transmitted |  |  | 2018-10-18 | IFQ | C | HOC | ME | 3
036909C-1012-SR-0127-2002 | OL1-2M56-2002 | Scope of Supply for Furnace Convection Fittings | A | IFQ | TPSK-LSPA1-T-ME-00207 | 2018-10-22 | Transmitted |  |  | 2018-10-16 | IFQ | C | HOC | ME | 3
036909C-1012-SP-0127-2002 | OL1-2M57-2002 | Particular Technical Specification for Furnace Convection Fittings | A | IFQ | TPSK-LSPA1-T-ME-00207 | 2018-10-22 | Transmitted |  |  | 2018-10-16 | IFQ | C | HOC | ME | 3
036909C-1000-JSS-1140-0001 | OL1-2R03-0013 | ME-013 Diesel Engine | A | IFR | TPSK-LSPA1-T-ME-00196 | 2018-10-18 | R1-No comments | 2018-11-02 | 2018-11-06 | 2018-10-22 | IFR | C | ROC | ME | 2
036909C-1021-PDS-0600-2166 | OL1-2G30-2166 | Process Equipment Datasheet - 10-E-2166 - DSG Blowdown Cooler | A | IFR | TPSK-LSPA1-T-PE-00209 | 2018-10-23 | Transmitted |  | 2018-11-06 | 2018-10-22 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2860 | OL1-2G30-2860 | Process Equipment Datasheet - 10-D-2860 - C2R 1st Stage Suction Drum | A | IFR | TPSK-LSPA1-T-PE-00208 | 2018-10-23 | Transmitted |  | 2018-11-06 | 2018-10-22 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2880 | OL1-2G30-2880 | Process Equipment Datasheet - 10-D-2880 - C2R 3rd Stage Suction Drum | A | IFR | TPSK-LSPA1-T-PE-00208 | 2018-10-23 | Transmitted |  | 2018-11-06 | 2018-10-22 | IFR | C | HOC | PE | 2
036909C-1006-JSS-0117-0005 | OL1-2R03-0005 | ME-005 Double Jacket Pipe Heat Exchangers for 36M and 132U Furnace | 0 | IMP | TPSK-LSPA1-T-ME-00212 | 2018-10-23 | Transmitted |  |  | 2018-10-18 | IMP | C | HOC | ME | 3
036909C-1053-SP-0910-5352 | OL1-2M03-5352 | Mechanical Equipment Data Sheet for Olefins Cooling Water Pumps 10-P-5350 A-H | A | IFQ | TPSK-LSPA1-T-ME-00210 | 2018-10-23 | R2-Comments as noted | 2018-11-14 | 2018-11-06 | 2018-10-22 | IFR | C | HOC | ME | 2
036909C-1053-SP-0910-5361 | OL1-2M03-5361 | Mechanical Equipment Data Sheet for CTU Cooling Water Pumps 10-P-5360 A-B-C | A | IFQ | TPSK-LSPA1-T-ME-00210 | 2018-10-23 | R2-Comments as noted | 2018-11-14 | 2018-11-06 | 2018-10-22 | IFR | H | HOC | ME | 2
036909C-1006-JSS-0117-0007 | OL1-2R04-0007 | PIP-007 Marking of Piping Material for 36M and 132U Furnace | 0 | IMP | TPSK-LSPA1-T-ME-00213 | 2018-10-23 | Transmitted |  |  | 2018-10-18 | IMP | C | HOC | ME | 3
036909C-1006-JSS-0117-0009 | OL-2R07-0009 | SP-009 Painting for 36M and 132U Furnace | 0 | IMP | TPSK-LSPA1-T-ME-00214 | 2018-10-23 | Transmitted |  |  | 2018-10-18 | IMP | C | HOC | ME | 3
036909C-1006-JSS-0117-1001 | OL1-2M91-1001 | Approved Vendor List for 36M and 132U Furnace | 0 | IMP | TPSK-LSPA1-T-ME-00211 | 2018-10-23 | Transmitted |  |  | 2018-10-18 | IMP | C | HOC | ME | 3
036909C-1024-SP-0510-2440 | OL1-2M03-2440 | Mechanical Equipment Datasheet for HP Depropanizer | A | IFQ | TPSK-LSPA1-T-ME-00215 | 2018-10-23 | Transmitted |  | 2018-11-06 | 2018-10-23 | IFR | C | HOC | ME | 2
036909C-1026-SP-0510-2660 | OL1-2M03-2660 | Mechanical Equipment Datasheet for Debutanizer | A | IFQ | TPSK-LSPA1-T-ME-00215 | 2018-10-23 | Transmitted |  | 2018-11-06 | 2018-10-23 | IFR | H | HOC | ME | 2
036909C-1025-PDS-0600-2515 | OL1-2G30-2515 | Process Equipment Datasheet - 10-E-2515 - Demeth Prefrac Reboiler | A | IFR | TPSK-LSPA1-T-PE-00216 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0600-2545 | OL1-2G30-2545 | Process Equipment Datasheet - 10-E-2545 - Demethanizer Reboiler | A | IFR | TPSK-LSPA1-T-PE-00216 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0600-2546 | OL1-2G30-2546 | Process Equipment Datasheet - 10-E-2546 - Demethanizer Bottoms Cooler | A | IFR | TPSK-LSPA1-T-PE-00216 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0600-2548 | OL1-2G30-2548 | Process Equipment Datasheet - 10-E-2548 - Demethanizer Bottoms Vaporizer | A | IFR | TPSK-LSPA1-T-PE-00216 | 2018-10-24 | R2-Comments as noted | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0600-2591 | OL1-2G30-2591 | Process Equipment Datasheet - 10-E-2856 - Ethylene Product Subcooler | A | IFR | TPSK-LSPA1-T-PE-00216 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0800-2504 | OL1-2G30-2504 | Process Equipment Datasheet - 10-D-2504 - Demeth Prefrac Feed Separator No 1 | A | IFR | TPSK-LSPA1-T-PE-00217 | 2018-10-24 | R1-No comments | 2018-11-07 | 2018-11-07 | 2018-10-23 | IFR | H | HOC | PE | 2
036909C-1025-PDS-0800-2506 | OL1-2G30-2506 | Process Equipment Datasheet - 10-D-2506 - Demeth Prefrac Feed Separator No 2 | A | IFR | TPSK-LSPA1-T-PE-00217 | 2018-10-24 | R1-No comments | 2018-11-07 | 2018-11-07 | 2018-10-23 | IFR | H | HOC | PE | 2
036909C-1025-PDS-0800-2508 | OL1-2G30-2508 | Process Equipment Datasheet - 10-D-2508 - Demeth Prefrac Feed Separator No 3 | A | IFR | TPSK-LSPA1-T-PE-00217 | 2018-10-24 | R1-No comments | 2018-11-07 | 2018-11-07 | 2018-10-23 | IFR | H | HOC | PE | 2
036909C-1025-PDS-0800-2525 | OL1-2G30-2525 | Process Equipment Datasheet - 10-D-2525 - Hydrogen Drum | A | IFR | TPSK-LSPA1-T-PE-00218 | 2018-10-24 | R1-No comments | 2018-11-09 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0800-2551 | OL1-2G30-2551 | Process Equipment Datasheet - 10-D-2550 - Expander Suction Drum | A | IFR | TPSK-LSPA1-T-PE-00218 | 2018-10-24 | R2-Comments as noted | 2018-11-09 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0800-2555 | OL1-2G30-2555 | Process Equipment Datasheet - 10-D-2555 - Expander Discharge Drum | A | IFR | TPSK-LSPA1-T-PE-00218 | 2018-10-24 | R1-No comments | 2018-11-09 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2805 | OL1-2G30-2805 | Process Equipment Datasheet - 10-D-2805 - C3R Surge Drum | A | IFR | TPSK-LSPA1-T-PE-00218 | 2018-10-24 | R1-No comments | 2018-11-09 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2854 | OL1-2G30-2854 | Process Equipment Datasheet - 10-D-2855 - C2R Surge Drum | A | IFR | TPSK-LSPA1-T-PE-00218 | 2018-10-24 | R1-No comments | 2018-11-09 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2870 | OL1-2G30-2870 | Process Equipment Datasheet - 10-D-2870 - C2R 2nd Stage Suction Drum | A | IFR | TPSK-LSPA1-T-PE-00218 | 2018-10-24 | R2-Comments as noted | 2018-11-09 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0900-5111 | OL1-2G30-5111 | Process Equipment Datasheet - 10-P-5112 A-B - Suspect Condensate Pumps | A | IFR | TPSK-LSPA1-T-PE-00219 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0900-5121 | OL1-2G30-5121 | Process Equipment Datasheet - 10-P-5120 A-B - Raw Condensate Pumps | A | IFR | TPSK-LSPA1-T-PE-00219 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0900-5141 | OL1-2G30-5141 | Process Equipment Datasheet - 10-P-5140 A-B - Intermittent Blowdown Pumps | A | IFR | TPSK-LSPA1-T-PE-00219 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1012-PP-122 | OL1-2W92-2122 | Project Engineering Plan - Package A1 - Furnaces - Houston Scope (Internal Only) | 0 | IFI | TPSK-LSPA1-T-PM-00220 | 2018-10-24 | Transmitted |  |  | 2018-10-22 | IFI | C | HOC | PC | 3
036909C-1006-JSS-0117-3004 | OL1-2R03-1004 | ME-004 Shell and Tube Heat Exchangers for 36M and 132U Furnace | 0 | IFI | TPSK-LSPA1-T-ME-00221 | 2018-10-24 | Transmitted |  |  | 2018-10-18 | IMP | C | HOC | ME | 3
036909C-1011-PDS-1040-1111 | OL1-2G30-1011 | Process Equipment Datasheet - 10-C-1100 - USC 36M Induced Draft Fan | B | IFD | TPSK-LSPA1-T-PE-00222 | 2018-10-24 | Transmitted |  |  | 2018-10-23 | IFD | C | HOC | PE | 2
036909C-1012-PDS-1040-1211 | OL1-2G30-1211 | Process Equipment Datasheet - 10-C-1200 1600 - USC 132U Induced Draft Fan | B | IFD | TPSK-LSPA1-T-PE-00222 | 2018-10-24 | Transmitted |  |  | 2018-10-23 | IFD | C | HOC | PE | 2
036909C-1028-PDS-0600-2858 | OL1-2G30-2858 | Process Equipment Datasheet - 10-E-2858 - HP Ethylene Product Superheater | A | IFR | TPSK-LSPA1-T-PE-00223 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1053-PDS-0300-5350 | OL1-2G30-5350 | Process Equipment Datasheet - 10-PK-5350 - Cooling Tower | B | IFD | TPSK-LSPA1-T-PE-00226 | 2018-10-24 | A1-Approved without comments | 2018-11-14 |  | 2018-10-24 | IFI | C | HOC | PE | 1
036909C-1053-PDS-0900-5352 | OL1-2G30-5352 | Process Equipment Datasheet - 10-P-5350 A-H - Olefins Cooling Water Pumps | B | IFD | TPSK-LSPA1-T-PE-00225 | 2018-10-24 | A1-Approved without comments | 2018-11-14 |  | 2018-10-24 | IFI | H | HOC | PE | 1
036909C-1053-PDS-0300-5355 | OL1-2G30-5355 | Process Equipment Datasheet - 10-PK-5355 - Side Stream Filter Pkg | B | IFD | TPSK-LSPA1-T-PE-00226 | 2018-10-24 | A1-Approved without comments | 2018-11-14 |  | 2018-10-24 | IFI | C | HOC | PE | 1
036909C-1053-PDS-0900-5361 | OL1-2G30-5361 | Process Equipment Datasheet - 10-P-5360 A-C - CTU Cooling Water Pumps | B | IFD | TPSK-LSPA1-T-PE-00225 | 2018-10-24 | A1-Approved without comments | 2018-11-14 |  | 2018-10-24 | IFI | H | HOC | PE | 1
036909C-1011-PDS-0117-1102 | OL1-2G30-1102 | Anticipated Operating Conditions - 10-H-1100 - USC 36M Gas Cracking Furnace | 0 | IFI | TPSK-LSPA1-T-PE-00224 | 2018-10-24 | Transmitted |  |  | 2018-10-24 | IFI | C | HOC | PE | 3
036909C-1012-PDS-0117-1202 | OL1-2G30-1202 | Anticipated Operating Conditions - 10-H-1200/1600 - USC 132U Liquid Cracking Furnace | 0 | IFI | TPSK-LSPA1-T-PE-00224 | 2018-10-24 | Transmitted |  |  | 2018-10-24 | IFI | C | HOC | PE | 3
036909C-1010-PDS-0800-1000 | OL1-2G30-1000 | Process Equipment Datasheet - 10-D-1000 - LPG Drum | A | IFR | TPSK-LSPA1-T-PE-00227 | 2018-10-25 | Transmitted |  | 2018-11-08 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0800-2572 | OL1-2G30-2572 | Process Equipment Datasheet - 10-D-2570 - Deethanizer Reflux Drum | A | IFR | TPSK-LSPA1-T-PE-00227 | 2018-10-25 | Transmitted |  | 2018-11-08 | 2018-10-24 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2455 | OL1-2G30-2455 | Process Equipment Datasheet - 10-E-2455 A-B - LP Depropanizer Reboilers | A | IFR | TPSK-LSPA1-T-PE-00228 | 2018-10-25 | R1-No comments | 2018-11-14 | 2018-11-08 | 2018-10-24 | IFR | C | HOC | PE | 2
036909C-1000-NM-0014-0001 | OL1-2G22-0001 | Flare Load Summary | A | IFR | TPSK-LSPA1-T-PE-00229 | 2018-10-25 | R2-Comments as noted | 2018-11-14 | 2018-11-08 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0600-5113 | OL1-2G30-5113 | Process Equipment Datasheet - 10-E-5113 - Foul Condensate Cooler | A | IFR | TPSK-LSPA1-T-PE-00230 | 2018-10-25 | R2-Comments as noted | 2018-11-14 | 2018-11-08 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0600-5103 | OL1-2G30-5103 | Process Equipment Datasheet - 10-E-5100 - Deaerator Vent Condenser | A | IFR | TPSK-LSPA1-T-PE-00230 | 2018-10-25 | R2-Comments as noted | 2018-11-14 | 2018-11-08 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-1012-JSS-0191-2009 | OL1-2M92-2009 | Project Specification for Furnace Burners | A | IFR | TPSK-LSPA1-T-PE-00231 | 2018-10-25 | R1-No comments | 2018-11-14 | 2018-11-08 | 2018-10-15 | IFR | C | HOC | ME | 2
036909C-1012-JSS-0125-2003 | OL1-2M92-2003 | Project Specification for Cast Intermediate Tube Supports | 0 | IFI | TPSK-LSPA1-T-ME-00232 | 2018-10-26 | Transmitted |  |  | 2018-10-15 | IFI | C | HOC | ME | 3
036909C-1012-MR-0154-2003 | OL1-2M55-2003 | Material Requisition for Quench Exchangers | A | IFQ | TPSK-LSPA1-T-ME-00233 | 2018-10-26 | Transmitted |  |  | 2018-10-18 | IFQ | C | HOC | ME | 3
036909C-1012-SR-0154-2003 | OL1-2M56-2003 | Scope of Supply for Quench Exchangers | A | IFQ | TPSK-LSPA1-T-ME-00233 | 2018-10-26 | Transmitted |  |  | 2018-10-18 | IFQ | C | HOC | ME | 3
036909C-1012-ITP-0154-2003 | OL1-2M07-2003 | Inspection and Test Plan for Quench Exchangers | A | IFQ | TPSK-LSPA1-T-ME-00233 | 2018-10-26 | Transmitted |  |  | 2018-10-18 | IFQ | C | HOC | ME | 3
036909C-1012-SP-0154-2003 | OL1-2M57-2003 | Particular Techanical Specification for Quench Exchangers | A | IFQ | TPSK-LSPA1-T-ME-00233 | 2018-10-26 | Transmitted |  |  | 2018-10-18 | IFQ | C | HOC | ME | 3
036909C-1053-PDS-0900-5352 | OL1-2G30-5352 | Process Equipment Datasheet - 10-P-5350 A-H - Olefins Cooling Water Pumps | C | IFD | TPSK-LSPA1-T-PE-00075 | 2018-10-26 | A1-Approved without comments | 2018-11-14 |  | 2018-10-25 | IFI | C | HOC | PE | 1
036909C-1053-PDS-0900-5361 | OL1-2G30-5361 | Process Equipment Datasheet - 10-P-5360 A-C - CTU Cooling Water Pumps | C | IFD | TPSK-LSPA1-T-PE-00075 | 2018-10-26 | A1-Approved without comments | 2018-11-14 |  | 2018-10-25 | IFI | C | HOC | PE | 1
036909C-1051-SP-0910-5109 | OL1-2M03-5109 | Mechanical Equipment Data Sheet - Condensate Pumps 10-P-5110 A-B | A | IFQ | TPSK-LSPA1-T-ME-00235 | 2018-10-26 | Transmitted |  | 2018-11-09 | 2018-10-25 | IFR | H | HOC | ME | 2
036909C-1021-SP-0910-2146 | OL1-2M03-2146 | Mechanical Equipment Data Sheet - DSG Feed Pumps 10-P-2146 A-B | A | IFQ | TPSK-LSPA1-T-ME-00235 | 2018-10-26 | Transmitted |  | 2018-11-09 | 2018-10-25 | IFR | C | HOC | ME | 2
036909C-1020-SP-0910-2006 | OL1-2M03-2006 | Mechanical Equipment Data Sheet Quench Oil Pump 10-P-2006 A-B-C | A | IFQ | TPSK-LSPA1-T-ME-00235 | 2018-10-26 | Transmitted |  | 2018-11-09 | 2018-10-25 | IFR | C | HOC | ME | 2
036909C-1021-SP-0910-2106 | OL1-2M03-2106 | Mechanical Equipment Data Sheet - Quench Water Pumps - 10-P-2106 A-B-C | A | IFQ | TPSK-LSPA1-T-ME-00236 | 2018-10-27 | Transmitted |  | 2018-11-09 | 2018-10-25 | IFR | C | HOC | ME | 2
036909C-1051-SP-0910-5101 | OL1-2M03-5101 | Mechanical Equipment Data Sheet SHP BFW Pumps - 10-P-5100 A-B-C | A | IFQ | TPSK-LSPA1-T-ME-00236 | 2018-10-27 | Transmitted |  | 2018-11-09 | 2018-10-25 | IFR | H | HOC | ME | 2
036909C-1051-SP-0910-5102 | OL1-2M03-5102 | Mechanical Equipment Data Sheet VLP BFW Pumps - 10-P-5102 A-B | A | IFQ | TPSK-LSPA1-T-ME-00236 | 2018-10-27 | Transmitted |  | 2018-11-09 | 2018-10-25 | IFR | C | HOC | ME | 2
036909C-1011-PDS-0610-1109 | OL1-2G30-1109 | Process Equipment Datasheet - 10-E-1110 - USC 36M TLX-1 Quench Exchanger | A | IFR | TPSK-LSPA1-T-PE-00237 | 2018-10-29 | Transmitted |  | 2018-11-12 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-1011-PDS-0610-1110 | OL1-2G30-1110 | Process Equipment Datasheet - 10-E-1120 - USC 36M TLX-2 Quench Exchanger | A | IFR | TPSK-LSPA1-T-PE-00237 | 2018-10-29 | Transmitted |  | 2018-11-12 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-1011-PDS-0630-1108 | OL1-2G30-1108 | Process Equipment Datasheet - 10-E-1100A1 - F6 - USC 36M USX Exchanger | A | IFR | TPSK-LSPA1-T-PE-00237 | 2018-10-29 | Transmitted |  | 2018-11-12 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-1012-PDS-0610-1209 | OL1-2G30-1209 | Process Equipment Datasheet - 10-E-1210 - 10-E-1610 - USC 132U TLX Quench Exchanger | A | IFR | TPSK-LSPA1-T-PE-00237 | 2018-10-29 | Transmitted |  | 2018-11-12 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-1012-PDS-0630-1208 | OL1-2G30-1208 | Process Equipment Datasheet - 10-E-1200A-F - 10-E-1600A-F - USC 132U SLE Exchanger | A | IFR | TPSK-LSPA1-T-PE-00237 | 2018-10-29 | Transmitted |  | 2018-11-12 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-TPSK-SKEC-MOM-0001 |  | Subcontracting And Construction Review Meeting | A | IFI | 036909C-JVD-TRN-INTERNAL-00012 | 2018-10-29 | Transmitted |  |  | 2018-10-26 | IFI | C | ROC | PM | 1
036909C-1020-PDS-0500-2020 | OL1-2G30-2020 | Process Equipment Datasheet - 10-T-2020 - Light Fuel Oil Stripper | A | IFR | TPSK-LSPA1-T-PE-00238 | 2018-10-29 | Transmitted |  | 2018-11-12 | 2018-10-26 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0500-2100 | OL1-2G30-2100 | Process Equipment Datasheet - 10-T-2100 - Quench Water Tower | A | IFR | TPSK-LSPA1-T-PE-00238 | 2018-10-29 | Transmitted |  | 2018-11-12 | 2018-10-26 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2406 | OL1-2G30-2406 | Process Equipment Datasheet - 10-E-2405 - Gas Dryer Feed Chiller | A | IFR | TPSK-LSPA1-T-PE-00239 | 2018-10-30 | R1-No comments | 2018-11-14 | 2018-11-12 | 2018-10-26 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2412 | OL1-2G30-2412 | Process Equipment Datasheet - 10-E-2412 - HP Depropanizer Feed Chiller | A | IFR | TPSK-LSPA1-T-PE-00239 | 2018-10-30 | R1-No comments | 2018-11-14 | 2018-11-12 | 2018-10-26 | IFR | C | HOC | PE | 2
036909C-1000-PP-107 | OL1-2W92-0003 | Project Document Coding | 0 | IMP | TPSK-LSPA1-T-PC-00240 | 2018-10-30 | Transmitted |  | 2018-11-13 | 2018-10-24 | IMP | C | ROC | PC | 2
036909C-1011-PDS-0191-1106 | OL1-2G30-1106 | Process Equipment Datasheet - 10-H-1100 - USC 36M Burner | A | IFR | TPSK-LSPA1-T-PE-00241 | 2018-10-30 | Transmitted |  | 2018-11-12 | 2018-10-26 | IFR | C | HOC | PE | 2
036909C-1012-PDS-0191-1206 | OL1-2G30-1206 | Process Equipment Datasheet - 10-H-1200 - 1600 - USC 132U Burner | A | IFR | TPSK-LSPA1-T-PE-00241 | 2018-10-30 | Transmitted |  | 2018-11-12 | 2018-10-26 | IFR | C | HOC | PE | 2
036909C-1019-PDS-1000-1950 | OL1-2G30-1950 | Process Equipment Datasheet - 10-PK-1950 - Decoke Air Compressor Pkg | C | IFD | TPSK-LSPA1-T-PE-00242 | 2018-10-30 | Transmitted |  |  | 2018-10-29 | IFI | C | HOC | PE | 1
036909C-1051-PDS-0600-5108 | OL1-2G30-5108 | Process Equipment Datasheet - 10-E-5110 - Suspect Condensate Cooler | A | IFR | TPSK-LSPA1-T-PE-00243 | 2018-10-30 | R2-Comments as noted | 2018-11-14 | 2018-11-12 | 2018-10-29 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0600-5107 | OL1-2G30-5107 | Process Equipment Datasheet - 10-E-5112 - Suspect Cond Flash Drum Vent Condenser | A | IFR | TPSK-LSPA1-T-PE-00243 | 2018-10-30 | R2-Comments as noted | 2018-11-14 | 2018-11-12 | 2018-10-26 | IFR | C | HOC | PE | 2
036909C-1000-PP-602 | OL1-2C92-0002 | Project QCS Coordination Procedure | 0 | IMP | TPSK-LSPA1-T-PL-00244 | 2018-10-30 | Transmitted |  | 2018-11-15 | 2018-10-29 | IMP | C | JVD | PL | 2
036909C-1000-PP-605 | OL1-2C92-0005 | Project QCS Requirements For Suppliers | 0 | IMP | TPSK-LSPA1-T-PL-00244 | 2018-10-30 | Transmitted |  | 2018-11-15 | 2018-10-29 | IMP | C | JVD | PL | 2
036909C-1000-PP-609 | OL1-2C92-0009 | Project QCS Inspection Procedure | 0 | IMP | TPSK-LSPA1-T-PL-00244 | 2018-10-30 | Transmitted |  | 2018-11-15 | 2018-10-29 | IMP | C | ROC | PL | 2
036909C-1000-PP-614 | OL1-2C92-0014 | Project Expediting And Inspection Level Definition | 0 | IMP | TPSK-LSPA1-T-PL-00244 | 2018-10-30 | Transmitted |  | 2018-11-15 | 2018-10-29 | IMP | C | JVD | PL | 2
036909C-1000-JSD-0400-01 | OL1-2R03-0050 | Job Specification For Design Of Pressure & Atmospheric Static Equipment | 0 | IMP | TPSK-LSPA1-T-ME-00245 | 2018-10-31 | Transmitted |  |  | 2018-10-26 | IMP | C | ROC | ME | 2
036909C-1000-JSS-0400-01 | OL1-2R03-0051 | Job Specification For Supply Of Pressure Vessels | 0 | IMP | TPSK-LSPA1-T-ME-00249 | 2018-10-31 | Transmitted |  |  | 2018-10-26 | IMP | C | ROC | ME | 2
036909C-1000-STC-0490-000 | OL1-2R03-0054 | Construction Standards For Pressure Equipment | 0 | IMP | TPSK-LSPA1-T-ME-00256 | 2018-10-31 | Transmitted |  |  | 2018-10-26 | IMP | C | ROC | ME | 2
036909C-1023-SP-0510-2300 | OL1-2M03-2300 | Mechanical Equipment Data Sheet Caustic Tower 10-T-2300 | A | IFQ | TPSK-LSPA1-T-ME-00246 | 2018-10-31 | Transmitted |  | 2018-11-13 | 2018-10-26 | IFR | C | HOC | ME | 2
036909C-1012-PP-121 | OL1-2W92-2121 | Project Execution Plan Furnaces | 0 | IFI |  | 2018-10-30 | Transmitted |  |  | 2018-10-23 | IFI | C | HOC | PC | 3
036909C-1000-PP-9905 |  | Project Health Safety Environmental and Security Plan - Package A1- Olefins - Houston Scope | 0 | IFI |  | 2018-10-30 | Transmitted |  |  | 2018-10-30 | IFI | C | HOC | PM
036909C-1011-SP-1040-1001 | OL1-2M03-1001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 36M | A | IFR | TPSK-LSPA1-T-ME-00247 | 2018-10-31 | Transmitted |  | 2018-11-13 | 2018-10-30 | IFR | C | HOC | ME | 2
036909C-1012-SP-1040-2001 | OL1-2M03-2001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 132U | A | IFR | TPSK-LSPA1-T-ME-00247 | 2018-10-31 | Transmitted |  | 2018-11-13 | 2018-10-29 | IFR | C | HOC | ME | 2
036909C-1000-DL-4234-0001 | OL1-2M58-0109 | Deviation List for Side Stream Filter Package | A | IFQ | TPSK-LSPA1-T-ME-00248 | 2018-10-31 | Transmitted |  | 2018-11-16 | 2018-10-29 | IFQ | C | KLOC | ME | 2
036909C-1000-ITP-4234-0001 | OL1-2M7-0109 | Inspection Test Plan for Side Stream Filter Package | A | IFQ | TPSK-LSPA1-T-ME-00248 | 2018-10-31 | Transmitted |  | 2018-11-16 | 2018-10-29 | IFQ | C | KLOC | ME | 2
036909C-1000-MR-4234-0001 | OL1-2M55-0109 | Material Requisition for Side Stream Filter Package | A | IFQ | TPSK-LSPA1-T-ME-00248 | 2018-10-31 | Transmitted |  | 2018-11-16 | 2018-10-29 | IFQ | C | KLOC | ME | 2
036909C-1000-SP-4234-0001 | OL1-2M57-0109 | Particular Technical Specification for Side Steam Filter Package | A | IFQ | TPSK-LSPA1-T-ME-00248 | 2018-10-31 | Transmitted |  | 2018-11-16 | 2018-10-29 | IFQ | C | KLOC | ME | 2
036909C-1000-SR-4234-0001 | OL1-2M56-0109 | Scope of Supply for Side Stream Filter Package | A | IFQ | TPSK-LSPA1-T-ME-00248 | 2018-10-31 | Transmitted |  | 2018-11-16 | 2018-10-29 | IFQ | C | KLOC | ME | 2
036909C-1053-SP-4234-0002 | OL1-2M03-5355 | Mechanical Equipment Datasheet for Side Stream Filter Package | B | IFQ | TPSK-LSPA1-T-ME-00248 | 2018-10-31 | Transmitted |  | 2018-11-16 | 2018-10-29 | IFQ | C | KLOC | ME | 2
036909C-1000-DL-0910-0001 | OL1-2M58-0015 | Deviation List For API Centrifugal Pumps - LLI | A | IFQ | TPSK-LSPA1-T-ME-00257 | 2018-10-31 | Transmitted |  | 2018-11-20 | 2018-10-30 | IMP | C | ROC | ME | 2
036909C-1000-ITP-0910-0001 | OL1-2M07-0015 | Inspection And Test Plan For API Centrifugal Pumps - LLI | A | IFQ | TPSK-LSPA1-T-ME-00257 | 2018-10-31 | Transmitted |  | 2018-11-20 | 2018-10-30 | IMP | C | ROC | ME | 2
036909C-1000-SP-0910-0001 | OL1-2M57-0015 | Particular Technical Specification For API Centrifugal Pumps - LLI | A | IFQ | TPSK-LSPA1-T-ME-00257 | 2018-10-31 | Transmitted |  | 2018-11-20 | 2018-10-30 | IMP | C | ROC | ME | 2
036909C-1000-SR-0910-0001 | OL1-2M56-0015 | Scope Of Supply For API Centrifugal Pumps - LLI | A | IFQ | TPSK-LSPA1-T-ME-00257 | 2018-10-31 | Transmitted |  | 2018-11-20 | 2018-10-30 | IMP | C | ROC | ME | 2
036909C-1024-PDS-0600-2413 | OL1-2G30-2413 | Process Equipment Datasheet - 10-E-2413 - HP Deprop Feed - Overhead Exchanger | A | IFR | TPSK-LSPA1-T-PE-00250 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-30 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2439 | OL1-2G30-2439 | Process Equipment Datasheet - 10-E-2440 - HP Depropanizer Condenser | A | IFR | TPSK-LSPA1-T-PE-00250 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-30 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2441 | OL1-2G30-2441 | Process Equipment Datasheet - 10-E-2441 - HP Deprop Reflux Chiller No 2 | A | IFR | TPSK-LSPA1-T-PE-00250 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-30 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2442 | OL1-2G30-2442 | Process Equipment Datasheet - 10-E-2442 - HP Deprop Reflux Chiller No 1 | A | IFR | TPSK-LSPA1-T-PE-00250 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-30 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2446 | OL1-2G30-2446 | Process Equipment Datasheet - 10-E-2446 - LP Depropanizer Feed Cooler | A | IFR | TPSK-LSPA1-T-PE-00250 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-30 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2461 | OL1-2G30-2461 | Process Equipment Datasheet - 10-E-2460 - C2 Hydrog Feed Cooler | A | IFR | TPSK-LSPA1-T-PE-00250 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-30 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0900-2321 | OL1-2G30-2321 | Process Equipment Datasheet - 10-P-2320 A-B - Spent Caustic Pumps | A | IFR | TPSK-LSPA1-T-PE-00252 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-29 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0900-2393 | OL1-2G30-2393 | Process Equipment Datasheet - 10-P-2392 - Spent Caustic Drain Drum Pump | A | IFR | TPSK-LSPA1-T-PE-00252 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-29 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0900-5101 | OL1-2G30-5101 | Process Equipment Datasheet - 10-P-5100 A-C - SHP BFW Pumps | B | IFD | TPSK-LSPA1-T-PE-00251 | 2018-10-31 | Transmitted |  |  | 2018-10-30 | IFI | C | HOC | PE | 2
036909C-1051-PDS-0900-5102 | OL1-2G30-5102 | Process Equipment Datasheet - 10-P-5102 A-B - VLP BFW Pumps | B | IFD | TPSK-LSPA1-T-PE-00251 | 2018-10-31 | Transmitted |  |  | 2018-10-30 | IFI | C | HOC | PE | 2
036909C-1051-PDS-0900-5109 | OL1-2G30-5109 | Process Equipment Datasheet - 10-P-5110 A-B - Condensate Pumps | B | IFD | TPSK-LSPA1-T-PE-00251 | 2018-10-31 | Transmitted |  |  | 2018-10-30 | IFI | C | HOC | PE | 2
036909C-1021-PDS-0500-2120 | OL1-2G30-2120 | Process Equipment Datasheet - 10-T-2120 - Distillate Stripper | A | IFR | TPSK-LSPA1-T-PE-00253 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-29 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0800-2310 | OL1-2G30-2310 | Process Equipment Datasheet - 10-D-2310 - Spent Caustic Deoiling Drum | A | IFR | TPSK-LSPA1-T-PE-00254 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-29 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0840-2319 | OL1-2G30-2319 | Process Equipment Datasheet - 10-F-2320 A-B - Spent Caustic Pump Discharge Filters | A | IFR | TPSK-LSPA1-T-PE-00255 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-29 | IFR | C | HOC | PE | 2
036909C-1000-DL-0845-0001 | OL1-2M58-0108 | Deviation List For Deaerator | A | IFQ | TPSK-LSPA1-T-ME-00270 | 2018-11-06 | Transmitted |  |  | 2018-10-29 | IFQ | C | ROC | ME | 2
036909C-1000-SP-0845-0001 | OL1-2M57-0108 | Particular Technical Specification For Deaerator | A | IFQ | TPSK-LSPA1-T-ME-00270 | 2018-11-06 | Transmitted |  |  | 2018-10-29 | IFQ | C | ROC | ME | 2
036909C-1000-SR-0845-0001 | OL1-2M56-0108 | Scope Of Supply For Deareator | A | IFQ | TPSK-LSPA1-T-ME-00270 | 2018-11-06 | Transmitted |  |  | 2018-10-29 | IFQ | C | ROC | ME | 2
036909C-1000-SR-4111-0001 | OL1-2M56-0114 | Scope Of Supply For Hydrogen Production Unit | A | IFQ |  | 2018-11-06 | Transmitted |  |  | 2018-10-26 | IFQ | C | ROC | ME | 2
036909C-1000-JSD-1600-0004 | OL1-2R05-0014 | LIGHTING SYSTEM | 0 | IMP | TPSK-LSPA1-T-EE-00258 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-MR-0910-0001 | OL1-2M55-0015 | Material Requisition For API Centrifugal Pumps - LLI | A | IFQ | TPSK-LSPA1-T-ME-00257 | 2018-10-31 | Transmitted |  | 2018-11-20 | 2018-10-30 | IMP | C | ROC | ME | 2
036909C-1000-JSD-1600-0007 | OL1-2R05-0029 | Functional and Schematic Diagram | 0 | IMP | TPSK-LSPA1-T-EE-00258 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSD-1600-0010 | OL1-2R05-0015 | Earthing And Lightning Protection | 0 | IMP | TPSK-LSPA1-T-EE-00258 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1023-PDS-0600-2305 | OL1-2G30-2305 | Process Equipment Datasheet - 10-E-2305 - Caustic Tower Feed Heater | A | IFR | TPSK-LSPA1-T-PE-00259 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-31 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2451 | OL1-2G30-2451 | Process Equipment Datasheet - 10-E-2450 - LP Depropanizer Condenser | A | IFR | TPSK-LSPA1-T-PE-00259 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-31 | IFR | C | HOC | PE | 2
036909C-1025-SP-0510-2510 | OL1-2M03-2510 | Mechanical Equipment Data Sheet - Demethanizer Prefractionator and Reflux Drum | A | IFQ | TPSK-LSPA1-T-ME-00260 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-29 | IFR | C | HOC | ME | 2
036909C-1019-SP-1013-1950 | OL1-2M03-1950 | Mechanical Equipment Datasheet - Decoke Air Compressor Package | C | IFQ | TPSK-LSPA1-T-ME-00261 | 2018-11-01 | Transmitted |  |  | 2018-10-31 | IFI | C | HOC | ME | 1
036909C-1006-JSS-0117-3001 | OL1-2R03-1001 | ME-001 Pressure Vessel for 36M and 132U Furnace | 0 | IFE | TPSK-LSPA1-T-ME-00262 | 2018-11-07 | Transmitted |  |  | 2018-10-18 | IMP | C | HOC | ME | 3
036909C-1012-MR-0155-2018 | OL1-2M55-2018 | Material Requisition for Furnace Steam Drums | A | IFQ | TPSK-LSPA1-T-ME-00263 | 2018-11-01 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1012-SR-0155-2018 | OL1-2M56-2018 | Scope of Supply for Furnace Steam Drums | A | IFQ |  | 2018-11-01 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1012-ITP-0155-2018 | OL1-2M07-2018 | Inspection and Test Plan for Furnace Steam Drums | A | IFQ | TPSK-LSPA1-T-ME-00263 | 2018-11-01 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1012-SP-0155-2018 | OL1-2M57-2018 | Particular Technical Specification for Furnace Steam Drums | A | IFQ |  | 2018-11-01 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1022-PDS-0800-2245 | OL1-2G30-2245 | Process Equipment Datasheet - 10-D-2245 - CG 4th Stage Discharge Drum | A | IFR | TPSK-LSPA1-T-PE-00264 | 2018-11-01 | Transmitted |  | 2018-11-15 | 2018-10-31 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0800-2438 | OL1-2G30-2438 | Process Equipment Datasheet - 10-D-2440 - HP Depropanizer Reflux Drum | A | IFR | TPSK-LSPA1-T-PE-00264 | 2018-11-01 | Transmitted |  | 2018-11-15 | 2018-10-31 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0600-2125 | OL1-2G30-2125 | Process Equipment Datasheet - 10-E-2125 - Distillate Stripper Reboiler | A | IFR | TPSK-LSPA1-T-PE-00265 | 2018-11-01 | Transmitted |  | 2018-11-15 | 2018-11-01 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0800-2452 | OL1-2G30-2452 | Process Equipment Datasheet - 10-D-2450 - LP Depropanizer Reflux Drum | A | IFR | TPSK-LSPA1-T-PE-00264 | 2018-11-01 | Transmitted |  | 2018-11-15 | 2018-10-31 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0600-2582 | OL1-2G30-2582 | Process Equipment Datasheet - 10-E-2582 - C2 Tower Reflux Cooler | A | IFR | TPSK-LSPA1-T-PE-00265 | 2018-11-01 | Transmitted |  | 2018-11-15 | 2018-11-01 | IFR | C | HOC | PE | 2
036909C-1012-PP-126 | OL1-2C92-2126 | Project Procurement Plan - Furnace Island | 0 | IFI |  | 2018-11-01 | Transmitted |  |  | 2018-10-30 | IFI | C | HOC | PL | 3
036909C-1022-PDS-0600-2211 | OL1-2G30-2211 | Process Equipment Datasheet - 10-E-2210 A-B - CG 1st Stage Aftercoolers | A | IFR | TPSK-LSPA1-T-PE-00266 | 2018-11-01 | Transmitted |  | 2018-11-15 | 2018-11-01 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2445 | OL1-2G30-2445 | Process Equipment Datasheet - 10-E-2445 A-B - HP Depropanizer Reboilers | A | IFR | TPSK-LSPA1-T-PE-00267 | 2018-11-01 | Transmitted |  | 2018-11-15 | 2018-11-01 | IFR | C | HOC | PE | 2
036909C-1000-JSS-1622-0001 | OL1-2R05-0022 | Miscellaneous Equipment | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1641-0001 | OL1-2R05-0003 | Oil Filled Distribution Transformer | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1652-0001 | OL1-2R05-0006 | Medium Voltage Switchgear | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1655-0001 | OL1-2R05-0038 | Low Voltage Bus Duct | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-DL-4111-0001 | OL1-2M58-0114 | Deviation List For Hydrogen Production Unit | A | IFQ |  | 2018-11-06 | Transmitted |  |  | 2018-10-26 | IFQ | C | ROC | ME | 2
036909C-1000-JSS-1656-0001 | OL1-2R05-0021 | Power Capacitors | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1671-0001 | OL1-2R05-0012 | Uninterruptible Power Supplies | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-ITP-4111-0001 | OL1-2M07-0114 | Inspection And Test Plan For Hydrogen Production Unit | A | IFQ |  | 2018-11-06 | Transmitted |  |  | 2018-10-26 | IFQ | C | ROC | ME | 2
036909C-1000-SP-4111-0001 | OL1-2M57-0114 | Particular Technical Specification For Hydrogen Production Unit | A | IFQ |  | 2018-11-06 | Transmitted |  |  | 2018-10-26 | IFQ | C | ROC | ME | 2
036909C-1000-ITP-0845-0001 | OL1-2M07-0108 | Inspection And Test Plan For Deareator | A | IFQ | TPSK-LSPA1-T-ME-00270 | 2018-11-06 | Transmitted |  |  | 2018-10-29 | IFQ | C | ROC | ME | 2
036909C-1000-JSS-1684-0001 | OL1-2R05-0016 | Cathodic Protection | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1693-0001 | OL1-2R05-0023 | Low Voltage Variable Voltage Variable Frequency System | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1694-0001 | OL1-2R05-0040 | Medium Voltage Variable Voltage Variable Frequency System | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-4123-0001 | OL1-2R05-0017 | Diesel Engine Generator | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-DL-0570-0004 | OL1-2M58-0075 | Deviation List For MD Trays For Columns | A | IFQ | TPSK-LSPA1-T-ME-00278 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-10-31 | IFR | H | ROC | ME | 2
036909C-1000-ITP-0570-0004 | OL1-2M07-0075 | Inspection And Test Plan For MD Trays For Columns | A | IFQ | TPSK-LSPA1-T-ME-00278 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-10-31 | IFR | H | ROC | ME | 2
036909C-1000-SP-0570-0004 | OL1-2M57-0075 | Particular Technical Specification For MD Trays For Columns | A | IFQ | TPSK-LSPA1-T-ME-00278 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-10-31 | IFR | H | ROC | ME | 2
036909C-1000-SR-0570-0004 | OL1-2M56-0075 | Scope Of Supply For MD Trays For Columns | A | IFQ | TPSK-LSPA1-T-ME-00278 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-10-31 | IFR | H | ROC | ME | 2
036909C-1012-DL-1040-2005 | OL1-2M58-2005 | Deviation List for Furnace ID Fans | A | IFQ | TPSK-LSPA1-T-ME-00269 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1012-ITP-1040-2005 | OL1-2M07-2005 | Inspection and Test Plan for Furnace ID Fans | A | IFQ | TPSK-LSPA1-T-ME-00269 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1012-SR-1040-2005 | OL1-2M56-2005 | Scope of Supply for Furnace ID Fans | A | IFQ | TPSK-LSPA1-T-ME-00269 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1012-MR-1040-2005 | OL1-2M55-2005 | Material Requisition for Furnace ID Fans | A | IFQ | TPSK-LSPA1-T-ME-00269 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1012-SP-1040-2005 | OL1-2M57-2005 | Particular Technical Specification for Furnace ID Fans | A | IFQ | TPSK-LSPA1-T-ME-00269 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1000-MR-4111-0001 | OL1-2M55-0114 | Material Requisition for Hydrogen Production Unit | A | IFQ |  | 2018-11-06 | Transmitted |  |  | 2018-10-26 | IFQ | C | ROC | ME | 2
036909C-1000-MR-0845-0001 | OL1-2M55-0108 | Material Requisition for Deareator | A | IFQ | TPSK-LSPA1-T-ME-00270 | 2018-11-06 | Transmitted |  |  | 2018-10-29 | IFQ | C | ROC | ME | 2
036909C-1028-PDS-0600-2856 | OL1-2G30-2856 | Process Equipment Datasheet - 10-E-2855 - C2R Condenser | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1028-PDS-0600-2853 | OL1-2G30-2853 | Process Equipment Datasheet - 10-E-2853 - C2R Desuperheater No 2 | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1028-PDS-0600-2857 | OL1-2G30-2857 | Process Equipment Datasheet - 10-E-2857 - HP Ethylene Product Vaporizer | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1028-PDS-0600-2852 | OL1-2G30-2852 | Process Equipment Datasheet - 10-E-2852 - C2R Desuperheater No 1 | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1028-PDS-0600-2807 | OL1-2G30-2807 | Process Equipment Datasheet - 10-E-2807 - C3 Chiller No 1 | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1028-PDS-0600-2806 | OL1-2G30-2806 | Process Equipment Datasheet - 10-E-2805 A-B - C3 Refrig Condensers | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1026-PDS-0600-2665 | OL1-2G30-2665 | Process Equipment Datasheet - 10-E-2665 A-B - Debutanizer Reboilers | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1026-PDS-0600-2661 | OL1-2G30-2661 | Process Equipment Datasheet - 10-E-2660 - Debutanizer Condenser | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1026-PDS-0600-2645 | OL1-2G30-2645 | Process Equipment Datasheet - 10-E-2645 A-B - C3 Tower Reboilers | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1026-PDS-0600-2636 | OL1-2G30-2636 | Process Equipment Datasheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1026-PDS-0600-2635 | OL1-2G30-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1026-PDS-0600-2631 | OL1-2G30-2631 | Process Equipment Datasheet - 10-E-2630 - Secondary Deeth Condenser | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1025-PDS-0600-2576 | OL1-2G30-2576 | Process Equipment Datasheet - 10-E-2576 - Deethanizer Bottoms Cooler | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1025-PDS-0600-2575 | OL1-2G30-2575 | Process Equipment Datasheet - 10-E-2575 - Deethanizer Reboiler | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1025-PDS-0600-2571 | OL1-2G30-2571 | Process Equipment Datasheet - 10-E-2570 - Deethanizer Condenser | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1025-PDS-0600-2503 | OL1-2G30-2503 | Process Equipment Datasheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1025-PDS-0600-2502 | OL1-2G30-2502 | Process Equipment Datasheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1028-PDS-0600-2809 | OL1-2G30-2809 | Process Equipment Datasheet - 10-E-2809 - C3 Chiller No 2 | B | IFD | TPSK-LSPA1-T-PE-00273 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1051-PDS-0800-5112 | OL1-2G30-5112 | Process Equipment Datasheet - 10-D-5112 - Suspect Condensate Flash Drum | A | IFR | TPSK-LSPA1-T-PE-00274 | 2018-11-05 | Transmitted |  | 2018-11-21 | 2018-11-05 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0800-5114 | OL1-2G30-5114 | Process Equipment Datasheet - 10-D-5114 - LP Condensate Flash Drum | A | IFR | TPSK-LSPA1-T-PE-00274 | 2018-11-05 | Transmitted |  | 2018-11-21 | 2018-11-05 | IFR | C | HOC | PE | 2
036909C-1052-PDS-0600-5201 | OL1-2G30-5201 | Process Equipment Datasheet - 10-E-5200 - MP Ethylene Superheater | A | IFR | TPSK-LSPA1-T-PE-00275 | 2018-11-05 | Transmitted |  | 2018-11-19 | 2018-11-05 | IFR | C | HOC | PE | 2
036909C-1000-DL-0310-0001 | OL1-2M58-0104 | Deviation List | A | IFQ | TPSK-LSPA1-T-ME-00276 | 2018-11-06 | Transmitted |  | 2018-11-19 | 2018-10-30 | IFR | C | KLOC | ME | 2
036909C-1000-ITP-0310-0001 | OL1-2M07-0104 | Inspection and Test Plan for Cooling Tower | A | IFQ | TPSK-LSPA1-T-ME-00276 | 2018-11-06 | Transmitted |  | 2018-11-19 | 2018-10-30 | IFR | C | KLOC | ME | 2
036909C-1000-JSS-0310-0001 | OL1-2R03-0104 | ME-008 Cooling Water | A | IFQ | TPSK-LSPA1-T-ME-00276 | 2018-11-06 | Transmitted |  | 2018-11-19 | 2018-10-30 | IFR | C | KLOC | ME | 2
036909C-1000-MR-0310-0001 |  | Material Requisition for Cooling Tower | A | IFQ | TPSK-LSPA1-T-ME-00276 | 2018-11-06 | Transmitted |  | 2018-11-19 | 2018-10-30 | IFR | C | KLOC | ME | 2
036909C-1000-SP-0310-0001 | OL1-2M57-0104 | Particular Technical Specification for Cooling Tower | A | IFQ | TPSK-LSPA1-T-ME-00276 | 2018-11-06 | Transmitted |  | 2018-11-19 | 2018-10-30 | IFR | C | KLOC | ME | 2
036909C-1000-SR-0310-0001 | OL1-2M56-0104 | Scope of Supply for Cooling Tower | A | IFQ | TPSK-LSPA1-T-ME-00276 | 2018-11-06 | Transmitted |  | 2018-11-19 | 2018-10-30 | IFR | C | KLOC | ME | 2
036909C-1053-SP-0310-0002 | OL1-2M03-5350 | Mechanical Equipment Datasheet for Cooling Tower | B | IFQ | TPSK-LSPA1-T-ME-00276 | 2018-11-06 | Transmitted |  | 2018-11-19 | 2018-10-30 | IFR | C | KLOC | ME | 2
036909C-1026-PDS-0900-2633 | OL1-2G30-2633 | Process Equipment Datasheet - 10-P-2630 A-B - Secondary Deeth Reflux Pumps | A | IFR | TPSK-LSPA1-T-PE-00277 | 2018-11-06 | Transmitted |  | 2018-11-20 | 2018-11-05 | IFR | C | HOC | PE | 2
036909C-1026-PDS-0900-2646 | OL1-2G30-2646 | Process Equipment Datasheet - 10-P-2646 A-B - Propane Recycle Pumps | A | IFR | TPSK-LSPA1-T-PE-00277 | 2018-11-06 | Transmitted |  | 2018-11-20 | 2018-11-05 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0900-2801 | OL1-2G30-2801 | Process Equipment Datasheet - 10-P-2805 A-B - Propylene Product Pumps | A | IFR | TPSK-LSPA1-T-PE-00277 | 2018-11-06 | Transmitted |  | 2018-11-20 | 2018-11-05 | IFR | C | HOC | PE | 2
036909C-1000-MR-0570-0004 | OL1-2M55-0075 | Material Requisition For MD Trays For Columns Requisition For Inquiry | A | IFQ | TPSK-LSPA1-T-ME-00278 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-10-31 | IFR | H | ROC | ME | 2
036909C-1000-PP-106 | OL1-2R07-0001 | Tagging Procedure | 0 | IMP | TPSK-LSPA1-T-ME-00279 | 2018-11-07 | Transmitted |  |  | 2018-10-29 | IFI | C | ROC | ME | 2
036909C-1022-SP-1011-2200 | OL1-2M03-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor | C | IFQ | TPSK-LSPA1-T-ME-00280 | 2018-11-06 | Transmitted |  |  | 2018-10-31 | IFI | C | HOC | ME | 2
036909C-1056-PDS-2600-5644 | OL1-2G30-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package | A | IFR | TPSK-LSPA1-T-PE-00281 | 2018-11-06 | Transmitted |  | 2018-11-20 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1056-PDS-2600-5650 | OL1-2G30-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg | A | IFR | TPSK-LSPA1-T-PE-00281 | 2018-11-06 | Transmitted |  | 2018-11-20 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1056-PDS-0200-5653 | OL1-2G30-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg | A | IFR | TPSK-LSPA1-T-PE-00282 | 2018-11-06 | Transmitted |  | 2018-11-20 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1056-PDS-2600-5670 | OL1-2G30-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg | A | IFR | TPSK-LSPA1-T-PE-00281 | 2018-11-06 | Transmitted |  | 2018-11-20 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1024-SP-0510-2450 | OL1-2M03-2450 | Mechanical Equipment Datasheet - LP Depropanizer | B | IFQ | TPSK-LSPA1-T-ME-00283 | 2018-11-06 | Transmitted |  |  | 2018-11-06 | IFI | C | HOC | ME | 2
036909C-1000-PP-617 | OL1-2C92-0017 | Project Site Services Conditions For Supplier Specialists | 0 | IMP | TPSK-LSPA1-T-PL-00284 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-05 | IFR | C | JVD | PL | 2
036909C-1000-ITP-0570-0001 | OL1-2M07-0055 | Inspection And Test Plan For Trays For Columns | A | IFQ | TPSK-LSPA1-T-ME-00300 | 2018-11-09 | Transmitted |  | 2018-11-26 | 2018-11-06 | IFR | C | ROC | ME | 2
036909C-1000-DL-0570-0001 | OL1-2M58-0055 | Deviation List For Trays For Column | A | IFQ | TPSK-LSPA1-T-ME-00300 | 2018-11-09 | Transmitted |  | 2018-11-26 | 2018-11-06 | IFR | C | ROC | ME | 2
036909C-1000-SP-0570-0001 | OL1-2M57-0055 | Particular Technical Specification For Trays For Columns | A | IFQ | TPSK-LSPA1-T-ME-00300 | 2018-11-09 | Transmitted |  | 2018-11-26 | 2018-11-06 | IFR | C | ROC | ME | 2
036909C-1000-SR-0570-0001 | OL1-2M56-0055 | Scope Of Supply For Trays For Columns | A | IFQ | TPSK-LSPA1-T-ME-00300 | 2018-11-09 | Transmitted |  | 2018-11-26 | 2018-11-06 | IFR | C | ROC | ME | 2
036909C-1020-PDS-0900-2024 | OL1-2G30-2024 | Process Equipment Datasheet - 10-P-2026 A-B - Light Fuel Oil Pumps | A | IFR | TPSK-LSPA1-T-PE-00285 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1020-PDS-0900-2046 | OL1-2G30-2046 | Process Equipment Datasheet - 10-P-2046 A-B - Heavy Fuel Oil Pumps | A | IFR | TPSK-LSPA1-T-PE-00285 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0900-2105 | OL1-2G30-2105 | Process Equipment Datasheet - 10-P-2105 A-B - Quench Oil Reflux Pumps | A | IFR | TPSK-LSPA1-T-PE-00285 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0900-2212 | OL1-2G30-2212 | Process Equipment Datasheet - 10-P-2210 A-B - CG 1st Stage Condensate Pumps | A | IFR | TPSK-LSPA1-T-PE-00285 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0900-2222 | OL1-2G30-2222 | Process Equipment Datasheet - 10-P-2220 A-B - CG 2nd Stage Condensed HC Pumps | A | IFR | TPSK-LSPA1-T-PE-00285 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0900-2416 | OL1-2G30-2416 | Process Equipment Datasheet - 10-P-2415 A-B - CG Liquid Dryer Feed Pumps | A | IFR | TPSK-LSPA1-T-PE-00285 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0900-2453 | OL1-2G30-2453 | Process Equipment Datasheet - 10-P-2450 A-B - LP Depropanizer Reflux-Product Pump | A | IFR | TPSK-LSPA1-T-PE-00285 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1000-MSD-0011-0001 | OL1-2G74-0001 | Material Selection Diagram - Olefins Unit 10 - Legend & Notes | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1010-MSD-0011-1001 | OL1-2G74-1001 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1010-MSD-0011-1003 | OL1-2G74-1003 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1011-MSD-0011-1101 | OL1-2G74-1101 | Material Selection Diagram - Olefins Unit 10 - 11 - Furnaces - Gas Cracking Furnace | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1012-MSD-0011-1201 | OL1-2G74-1201 | Material Selection Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1019-MSD-0011-1901 | OL1-2G74-1901 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1019-MSD-0011-1902 | OL1-2G74-1902 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1020-MSD-0011-2001 | OL1-2G74-2001 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1020-MSD-0011-2002 | OL1-2G74-2002 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1021-MSD-0011-2101 | OL1-2G74-2101 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1021-MSD-0011-2102 | OL1-2G74-2102 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1021-MSD-0011-2103 | OL1-2G74-2103 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1022-MSD-0011-2201 | OL1-2G74-2201 | Material Selection Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1023-MSD-0011-2301 | OL1-2G74-2301 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1023-MSD-0011-2302 | OL1-2G74-2302 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1023-MSD-0011-2303 | OL1-2G74-2303 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1023-MSD-0011-2304 | OL1-2G74-2304 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1023-MSD-0011-2305 | OL1-2G74-2305 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1024-MSD-0011-2401 | OL1-2G74-2401 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1024-MSD-0011-2402 | OL1-2G74-2402 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1024-MSD-0011-2403 | OL1-2G74-2403 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1024-MSD-0011-2404 | OL1-2G74-2404 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1024-MSD-0011-2405 | OL1-2G74-2405 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1025-MSD-0011-2501 | OL1-2G74-2501 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1025-MSD-0011-2502 | OL1-2G74-2502 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1025-MSD-0011-2503 | OL1-2G74-2503 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1025-MSD-0011-2504 | OL1-2G74-2504 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1025-MSD-0011-2505 | OL1-2G74-2505 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1025-MSD-0011-2506 | OL1-2G74-2506 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1026-MSD-0011-2601 | OL1-2G74-2601 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1026-MSD-0011-2602 | OL1-2G74-2602 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1026-MSD-0011-2603 | OL1-2G74-2603 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1026-MSD-0011-2604 | OL1-2G74-2604 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1028-MSD-0011-2801 | OL1-2G74-2801 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1028-MSD-0011-2802 | OL1-2G74-2802 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1028-MSD-0011-2803 | OL1-2G74-2803 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1028-MSD-0011-2804 | OL1-2G74-2804 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1029-MSD-0011-2901 | OL1-2G74-2901 | Material Selection Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | A | IFA |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-02 | IFA | C | HOC | ME | 1
036909C-1011-DW-0125-1301 | OL1-2M06-1301 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details | 0 | IFI | TPSK-LSPA1-T-ME-00286 | 2018-11-07 | Transmitted |  |  | 2018-11-06 | IFI | C | HOC | ME | 3
036909C-1011-DW-0125-1302 | OL1-2M06-1302 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details | 0 | IFI | TPSK-LSPA1-T-ME-00286 | 2018-11-07 | Transmitted |  |  | 2018-11-06 | IFI | C | HOC | ME | 3
036909C-1026-PDS-0800-2662 | OL1-2G30-2662 | Process Equipment Datasheet - 10-D-2660 - Debutanizer Reflux Drum | A | IFR | TPSK-LSPA1-T-PE-00287 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-07 | IFR | C | HOC | PE | 2
036909C-1026-PDS-0800-2632 | OL1-2G30-2632 | Process Equipment Datasheet - 10-D-2630 - Secondary Deeth Reflux Drum | A | IFR | TPSK-LSPA1-T-PE-00287 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-07 | IFR | C | HOC | PE | 2
036909C-1026-SP-0510-2660 | OL1-2M03-2660 | Mechanical Equipment Datasheet - Debutanizer | B | IFQ | TPSK-LSPA1-T-ME-00288 | 2018-11-08 | Transmitted |  | 2018-11-22 | 2018-11-07 | IFR | C | HOC | ME | 2
036909C-1012-DW-0125-2302 | OL1-2M06-2302 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details | 0 | IFI | TPSK-LSPA1-T-ME-00289 | 2018-11-08 | Transmitted |  |  | 2018-11-06 | IFI | C | HOC | ME | 3
036909C-1012-DW-0125-2301 | OL1-2M06-2301 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details | 0 | IFI | TPSK-LSPA1-T-ME-00289 | 2018-11-08 | Transmitted |  |  | 2018-11-06 | IFI | C | HOC | ME | 3
036909C-1023-PDS-0500-2300 | OL1-2G30-2300 | Process Equipment Datasheet - 10-T-2300 - Caustic Tower | B | IFD | TPSK-LSPA1-T-PE-00290 | 2018-11-08 | Transmitted |  |  | 2018-11-08 | IFI | C | HOC | PE | 1
036909C-1000-JSD-1580-0002 | OL1-2R06-1301 | Progammable Logic Controller | A | IFR | TPSK-LSPA1-T-IE-00291 | 2018-11-08 | Transmitted |  | 2018-11-23 | 2018-11-07 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1501-0002 | OL1-2R06-0024 | General Design Rules For SmartPlant Instrumentation Setup | B | IFR | TPSK-LSPA1-T-IE-00291 | 2018-11-08 | Transmitted |  | 2018-11-23 | 2018-10-24 | IFR | C | ROC | IE | 2
036909C-1000-JSS-1692-0001 | OL1-2R05-0011 | Electrical Motors Greater Than 300 kW | 0 | IMP | TPSK-LSPA1-T-EE-00293 | 2018-11-08 | Transmitted |  |  | 2018-09-20 | IFI | C | ROC | EE | 3
036909C-1000-MR-0570-0001 | OL1-2M55-0055 | Material Requisition For Trays For Columns Requisition For Inquiry | A | IFQ | TPSK-LSPA1-T-ME-00300 | 2018-11-09 | Transmitted |  | 2018-11-26 | 2018-11-06 | IFR | C | ROC | ME | 2
036909C-1024-SP-0910-2453 | OL1-2M03-2453 | Mechanical Equipment Datasheet - LP Depropanizer Reflux-Product Pump | A | IFQ | TPSK-LSPA1-T-ME-00294 | 2018-11-08 | Transmitted |  | 2018-11-22 | 2018-11-08 | IFR | C | HOC | ME | 2
036909C-1000-JSD-1300-0003 | OL1-2R04-0031 | A1 Scope Annex C– Ppiping Specification PIP-006 Steam Tracing Piping | B | IFR |  | 2018-11-09 | Transmitted |  | 2018-11-26 | 2018-11-06 | IFR | C | ROC | MP | 2
036909C-1000-PP-608 | OL1-2C92-0008 | Project QCS Expediting Procedure | 0 | IMP |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-10-29 | IFR | C | ROC | PL | 2
036909C-1000-PP-015 | OL1-2W92-0015 | Prescriptions For Preparation Of Manufacturing Data Record Book | 0 | IMP |  | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-10-29 | IFR | C | ROC | PC | 2
036909C-1020-PDS-0600-2026 | OL1-2G30-2026 | Process Equipment Datasheet - 10-E-2026 - FO Product Cooler | A | IFR | TPSK-LSPA1-T-PE-00298 | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-08 | IFR | C | HOC | PE | 2
036909C-1020-PDS-0600-2048 | OL1-2G30-2048 | Process Equipment Datasheet - 10-E-2048 - Heavy Fuel Oil Product Cooler | A | IFR | TPSK-LSPA1-T-PE-00298 | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-08 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0400-2470 | OL1-2G30-2470 | Process Equipment Datasheet - 10-R-2470 A-C - C2 Hydrog Reactor | A | IFR | TPSK-LSPA1-T-PE-00299 | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-08 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0800-2420 | OL1-2G30-2420 | Process Equipment Datasheet - 10-D-2420 A-B - CG Liquid Dryer | A | IFR | TPSK-LSPA1-T-PE-00301 | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-08 | IFR | C | HOC | PE | 2
036909C-1026-PDS-0900-2647 | OL1-2G30-2647 | Process Equipment Datasheet - 10-P-2647 - HP Propylene - Off Spec Pumps | A | IFR | TPSK-LSPA1-T-PE-00302 | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-08 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0800-2504 | OL1-2G30-2504 | Process Equipment Datasheet - 10-D-2504 - Demeth Prefrac Feed Separator No 1 | B | IFD | TPSK-LSPA1-T-PE-00303 | 2018-11-09 | Transmitted |  |  | 2018-11-08 | IFI | C | HOC | PE | 2
036909C-1025-PDS-0800-2506 | OL1-2G30-2506 | Process Equipment Datasheet - 10-D-2506 - Demeth Prefrac Feed Separator No 2 | B | IFD | TPSK-LSPA1-T-PE-00303 | 2018-11-09 | Transmitted |  |  | 2018-11-08 | IFI | C | HOC | PE | 2
036909C-1025-PDS-0800-2508 | OL1-2G30-2508 | Process Equipment Datasheet - 10-D-2508 - Demeth Prefrac Feed Separator No 3 | B | IFD | TPSK-LSPA1-T-PE-00303 | 2018-11-09 | Transmitted |  |  | 2018-11-08 | IFI | C | HOC | PE | 2
036909C-1025-SP-0510-2540 | OL1-2M03-2540 | Mechanical Equipment Data Sheet - Demethanizer and Demethanizer Reflux Drum | A | IFQ | TPSK-LSPA1-T-ME-00304 | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-09 | IFR | C | HOC | ME | 2
036909C-1020-PDS-0600-2015 | OL1-2G30-2015 | Process Equipment Datasheet - 10-E-2008 A-C - LS2 Steam Generators | A | IFR | TPSK-LSPA1-T-PE-00305 | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-09 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0500-2510 | OL1-2G30-2510 | Process Equipment Datasheet - 10-T-2510 - 10-D-2510 - Demethanizer Prefractionator & Reflux Drum | B | IFD | TPSK-LSPA1-T-PE-00306 | 2018-11-09 | Transmitted |  |  | 2018-11-09 | IFI | C | HOC | PE | 1
036909C-1025-PDS-0500-2540 | OL1-2G30-2540 | Process Equipment Datasheet - 10-T-2540 - 10-D-2540 - Demethanizer & Reflux Drum | B | IFD | TPSK-LSPA1-T-PE-00306 | 2018-11-09 | Transmitted |  |  | 2018-11-09 | IFI | C | HOC | PE | 1
036909C-1026-DI-0007-2602 | OL1-2G05-2602 | Area Basis of Design - 262 C3 Hydrogenation | A | IFA | TPSK-LSPA1-T-PE-00307 | 2018-11-12 | Transmitted |  | 2018-11-26 | 2018-11-09 | IFA | C | HOC | PE | 1
036909C-1027-DI-0007-2702 | OL1-2G05-2702 | Area Basis of Design - Area 275 C4-C5 Hydrogenation | A | IFA | PSK-LSPA1-T-PE-00307 | 2018-11-12 | Transmitted |  | 2018-11-26 | 2018-11-09 | IFA | C | HOC | PE | 1
036909C-1027-DI-0007-2701 | OL1-2G05-2701 | Area Basis of Design - 270 Gasoline Hydrogenation -GHU-1 | A | IFA | PSK-LSPA1-T-PE-00307 | 2018-11-12 | Transmitted |  | 2018-11-26 | 2018-11-09 | IFA | C | HOC | PE | 1
036909C-1000-JSS-0910-0002 | OL1-2R03-0500 | ME-050 Centrifugal Pump (Non API) | A | IFR | TPSK-LSPA1-T-ME-00308 | 2018-11-12 | Transmitted |  | 2018-11-27 | 2018-10-25 | IFR | C | ROC | ME | 2
036909C-1000-JSS-1654-0001 | OL1-2R05-0008 | Low Voltage Switchgear And Motor Control Center | 0 | IFE | TPSK-LSPA1-T-EE-00309 | 2018-11-12 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1657-0001 | OL1-2R05-0007 | Low Voltage Distribution Panel | 0 | IMP | TPSK-LSPA1-T-EE-00309 | 2018-11-12 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1025-TDS-0610-2571 | OL1-2M03-2571 | Mechanical Equipment Data Sheet - 10-E-2570 - Deethanizer Condenser | A | IFQ | TPSK-LSPA1-T-ME-00310 | 2018-11-13 | Transmitted |  | 2018-11-27 | 2018-11-12 | IFR | C | HOC | ME | 2
036909C-1000-PP-255 | OL1-2R07-0027 | 3D Modeling Procedure For Piping Designers | A | IFR |  | 2018-11-13 | Transmitted |  | 2018-11-28 | 2018-06-06 | IFR | C | ROC | ME | 2
036909C-1051-SP-0910-5101 | OL1-2M03-5101 | Mechanical Equipment Data Sheet for SHP BFW Pumps | B | IFQ | TPSK-LSPA1-T-ME-00236 | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-12 | IFR | C | HOC | ME | 2
036909C-1051-SP-0910-5109 | OL1-2M03-5109 | Mechanical Equipment Data Sheet - Condensate Pumps | B | IFQ |  | 2018-11-14 | Transmitted |  | 2018-11-28 | 2018-11-12 | IFR | C | HOC | ME | 2
036909C-1053-SP-0910-5361 | OL1-2M03-5361 | Mechanical Equipment Data Sheet - CTU Cooling Water Pumps | B | IFQ |  | 2018-11-14 | Transmitted |  | 2018-11-28 | 2018-11-12 | IFR | C | HOC | ME | 2
036909C-1028-TDS-0610-2857 | OL1-2M03-2857 | Mechanical Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer | A | IFQ |  | 2018-11-13 | Transmitted |  | 2018-11-27 | 2018-11-13 | IFR | C | HOC | ME | 2
036909C-1012-SR-0191-2006 | OL1-2M56-2006 | Scope of Supply for Furnace Burners | A | IFQ |  | 2018-11-13 | Transmitted |  |  | 2018-11-07 | IFQ | C | HOC | ME | 3
036909C-1012-MR-0191-2006 | OL1-2M55-2006 | Material Requisition for Furnace Burners | A | IFQ |  | 2018-11-13 | Transmitted |  |  | 2018-11-07 | IFQ | C | HOC | ME | 3
036909C-1012-DL-0191-2006 | OL1-2M58-2006 | Deviation List for Furnace Burners | A | IFQ |  | 2018-11-13 | Transmitted |  |  | 2018-11-07 | IFQ | C | HOC | ME | 3
036909C-1012-ITP-0191-2006 | OL1-2M07-2006 | Inspection and Test Plan for Furnace Burners | A | IFQ |  | 2018-11-13 | Transmitted |  |  | 2018-11-07 | IFQ | C | HOC | ME | 3
036909C-1012-SP-0191-2006 | OL1-2M57-2006 | Particular Technical Specification for Furnace Burners | A | IFQ |  | 2018-11-13 | Transmitted |  |  | 2018-11-07 | IFQ | C | HOC | ME | 3
036909C-1000-ITP-0570-0004 | OL1-2M07-0075 | Inspection and Test Plan for High Efficiency Internals for Columns | B | IMP |  | 2018-11-14 | Transmitted |  | 2018-11-29 | 2018-11-12 | IFR | C | ROC | ME | 2
036909C-1000-MR-0570-0004 | OL1-2M55-0075 | Material Requisition for High Efficiency Internals for Columns | B | IMP |  | 2018-11-14 | Transmitted |  | 2018-11-29 | 2018-11-12 | IFR | C | ROC | ME | 2
036909C-1000-SR-0570-0004 | OL1-2M56-0075 | Scope of Supply for High Efficiency Internals for Columns | B | IMP |  | 2018-11-14 | Transmitted |  | 2018-11-29 | 2018-11-12 | IFR | C | ROC | ME | 2
036909C-1000-SP-0570-0004 | OL1-2M57-0075 | Particular Technical Specification for High Efficiency Internals for Columns | B | IMP |  | 2018-11-14 | Transmitted |  | 2018-11-29 | 2018-11-12 | IFR | C | ROC | ME | 2
036909C-1000-DL-0570-0004 | OL1-2M58-0075 | Deviation List for High Efficiency Internals for Columns | B | IMP |  | 2018-11-14 | Transmitted |  | 2018-11-29 | 2018-11-12 | IFR | C | ROC | ME | 2
036909C-1024-PDS-0800-2405 | OL1-2G30-2405 | Process Equipment Datasheet - 10-D-2405 - Gas Dryer Feed KO Drum | A | IFR |  | 2018-11-14 | Transmitted |  | 2018-11-28 | 2018-11-13 | IFR | C | HOC | PE | 2
036909C-1028-TDS-0610-2856 | OL1-2M03-2856 | Mechanical Equipment Data Sheet - 10-E-2855 - C2R Condenser | A | IFQ |  | 2018-11-14 | Transmitted |  | 2018-11-28 | 2018-11-14 | IFR | C | HOC | ME | 2
036909C-1051-PDS-0800-5100 | OL1-2G30-5100 | Process Equipment Datasheet - 10-D-5100 - Deaerator | B | IFD | TPSK-LSPA1-T-PE-00151 | 2018-11-14 | Transmitted |  |  | 2018-11-14 | IFI | C | HOC | PE | 2
036909C-1023-SP-0910-2302 | OL1-2M03-2302 | Mechanical Equipment Datasheet - Strong Caustic Circulating Pumps | A | IFQ |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-13 | IFR | C | HOC | ME | 2
036909C-1023-SP-0910-2304 | OL1-2M03-2304 | Mechanical Equipment Datasheet - Intermediate Caustic Circulating Pump | A | IFQ |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-13 | IFR | C | HOC | ME | 2
036909C-1023-SP-0910-2306 | OL1-2M03-2306 | Mechanical Equipment Datasheet - Weak Caustic Circulating Pumps | A | IFQ |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-13 | IFR | C | HOC | ME | 2
036909C-1023-SP-0910-2311 | OL1-2M03-2311 | Mechanical Equipment Datasheet - Wash Oil Circulating Pumps | A | IFQ |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-13 | IFR | C | HOC | ME | 2
036909C-1000-ITP-0910-0003 | OL1-2M07-0003 | Inspection and Test Plan for Cooling Water Pumps | A | IFQ |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-14 | IFR | C | KLOC | ME | 2
036909C-1000-MR-0910-0003 | OL1-2M55-0003 | Material Requisition for Cooling Water Pumps | A | IFQ |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-14 | IFR | C | KLOC | ME | 2
036909C-1000-SP-0910-0003 | OL1-2M57-0003 | Particular Technical Specification for Cooling Water Pumps | A | IFQ |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-14 | IFR | C | KLOC | ME | 2
036909C-1000-PP-135 |  | TPSK Project Directorate Table of Delegations | 0 | IMP |  | 2018-11-15 | Transmitted |  |  | 2018-11-15 | IFI | C | JVD | PM
036909C-1000-DL-0910-0003 | OL1-2M58-0003 | Deviation List for Cooling Water Pumps | A | IFQ |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-14 | IFR | C | KLOC | ME | 2
036909C-1000-SR-0910-0003 | OL1-2M56-0003 | Scope of Supply for Cooling Water Pumps | A | IFQ |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-14 | IFR | C | KLOC | ME | 2
036909C-1052-PDS-0600-5210 | OL1-2G30-5210 | Process Equipment Datasheet - 10-E-5210 - Pilot Gas Vaporizer | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-14 | IFR | C | HOC | PE | 2
036909C-1000-PID-0090-0001 | OL1-2G43-0001 | P&ID - Olefins Unit 10 - Common - Abbreviations And Numbering | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1000-PID-0090-0002 | OL1-2G43-0002 | P&ID - Olefins Unit 10 - Common - Piping Symbols | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1000-PID-0090-0003 | OL1-2G43-0003 | P&ID - Olefins Unit 10 - Common - Instrumentation Symbols | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1000-PID-0090-0004 | OL1-2G43-0004 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 1 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1000-PID-0090-0005 | OL1-2G43-0005 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 2 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1000-PID-0090-0010 | OL1-2G43-0010 | P&ID - Olefins Unit 10 - Common - Instrument Details | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1000-PID-0090-0011 | OL1-2G43-0011 | P&ID - Olefins Unit 10 - Common - EIV Block Valves Typical | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1101 | OL1-2G43-1101 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed Distribution Header | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1105 | OL1-2G43-1105 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Dilution Steam Distribution Header | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1106 | OL1-2G43-1106 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoke Air Header Distribution Header | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1107 | OL1-2G43-1107 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 1 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1108 | OL1-2G43-1108 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 2 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1109 | OL1-2G43-1109 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 3 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1110 | OL1-2G43-1110 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed-Sheet 4 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1111 | OL1-2G43-1111 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 5 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1112 | OL1-2G43-1112 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 6 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1115 | OL1-2G43-1115 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Convection Section | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1116 | OL1-2G43-1116 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 1 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1117 | OL1-2G43-1117 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 2 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1118 | OL1-2G43-1118 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 3 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1119 | OL1-2G43-1119 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 4 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1120 | OL1-2G43-1120 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 5 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1121 | OL1-2G43-1121 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 6 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1125 | OL1-2G43-1125 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - TLX Quench Exchangers | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1126 | OL1-2G43-1126 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Furnace Effluent And Decoke MOVs | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1127 | OL1-2G43-1127 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - USX Drain Header | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1128 | OL1-2G43-1128 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - SHP Steam Drum | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1129 | OL1-2G43-1129 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Drum-USX And TLX-1 Risers | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1130 | OL1-2G43-1130 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Boiler Feed Water Supply Export Steam | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1131 | OL1-2G43-1131 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Coils | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1135 | OL1-2G43-1135 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Fuel Gas | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1140 | OL1-2G43-1140 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Burners | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1145 | OL1-2G43-1145 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoking Effluent | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1011-PID-0021-1150 | OL1-2G43-1150 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Flue Gas | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1201 | OL1-2G43-1201 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - C3 LPG Feed Distribution Header | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1202 | OL1-2G43-1202 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Liquid Feed Distribution Header | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1205 | OL1-2G43-1205 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Dilution Steam Distribution Header | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1206 | OL1-2G43-1206 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Decoke Air Header Distribution Header | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1207 | OL1-2G43-1207 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 1 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1208 | OL1-2G43-1208 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 2 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1209 | OL1-2G43-1209 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 3 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1210 | OL1-2G43-1210 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 4 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1211 | OL1-2G43-1211 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 5 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1212 | OL1-2G43-1212 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 6 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1215 | OL1-2G43-1215 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Convection Section | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1216 | OL1-2G43-1216 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 1 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1217 | OL1-2G43-1217 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 2 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1218 | OL1-2G43-1218 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 3 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1219 | OL1-2G43-1219 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 4 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1220 | OL1-2G43-1220 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 5 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1221 | OL1-2G43-1221 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 6 | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1225 | OL1-2G43-1225 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - TLX Exchanger | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1226 | OL1-2G43-1226 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Furnace Effluent & Decoke MOV's | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1227 | OL1-2G43-1227 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - SLE Drain Header | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1228 | OL1-2G43-1228 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - VHP Steam Drum | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1229 | OL1-2G43-1229 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Drum-SLE And TLX Risers | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1230 | OL1-2G43-1230 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Boiler Feed Water Supply Export Steam | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1231 | OL1-2G43-1231 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Coils | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1235 | OL1-2G43-1235 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1240 | OL1-2G43-1240 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Burners | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1245 | OL1-2G43-1245 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Flue Gas | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 14:00 | IFR | C | HOC | PE | 2
036909C-1012-PID-0021-1250 | OL1-2G43-1250 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas | A | IFR |  | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-15 | IFR | C | HOC | PE | 2
036909C-1000-JSD-1300-0008 | OL1-2R04-0032 | JSD For Piping Stress Analysis | A | IFR |  | 2018-11-16 | Transmitted |  | 2018-12-03 | 2018-11-12 | IFR | C | ROC | MP | 2
036909C-1000-JSD-1300-0009 | OL1-2R04-0033 | JSD for piping loads on PRK, SLW, STR, IS | A | IFR |  | 2018-11-16 | Transmitted |  | 2018-12-03 | 2018-11-12 | IFR | C | ROC | MP | 2
036909C-1000-JSD-1300-0010 | OL1-2R04-0034 | JSD For Auxiliary Piping Supports | A | IFR |  | 2018-11-16 | Transmitted |  | 2018-12-03 | 2018-11-12 | IFR | C | ROC | MP | 2
036909C-1000-JSD-1300-0012 | OL1-2R04-0012 | Pipe Support | A | IFR |  | 2018-11-16 | Transmitted |  | 2018-12-03 | 2018-11-12 | IFR | C | ROC | MP | 2
036909C-1000-STC-1390-0001 | OL1-2P92-0003 | Piping Standard Construction Drawings | 0 | CAN |  | 2018-11-16 | Transmitted |  | 2018-12-03 | 2018-11-12 | IFR | C | ROC | MP | 2
036909C-1000-STD-1380-0001 | OL1-2P92-0002 | Piping Design Standard Drawings | 0 | CAN |  | 2018-11-16 | Transmitted |  | 2018-12-03 | 2018-11-12 | IFR | C | ROC | MP | 2
036909C-TPIT-TPGM-MOM-0002 |  | Package A1 Olefins Plant KLOC And ROC Instrument & Telecom Deliverables - Scope Split And Alignment Meeting | 0 | IFI |  | 2018-11-16 | Transmitted |  |  | 2018-11-15 | IFI | C | ROC | IE
036909C-TPIT-TPGM-MOM-0003 |  | Long Son Project KLOC And ROC E & I Alignment Meeting | 0 | IFI |  | 2018-11-16 | Transmitted |  |  | 2018-11-15 | IFI | C | ROC | EE
036909C-TPIT-TPSW-MOM-0004 |  | Package A1 Olefins Plant Meeting | 0 | IFI |  | 2018-11-16 | Transmitted |  |  | 2018-10-04 | IFI | C | ROC | IE
036909C-1000-JSD-1300-0002 | OL1-2R04-0002 | Job Specification For Detail Design Piping | B | IFR | TPSK-LSPA1-T-MP-00012 | 2018-11-16 | Transmitted |  | 2018-12-03 | 2018-11-12 | IFR | C | ROC | ROC Piping | 2

## FILTER
Document Reference | Document Client Reference | Client Reference | Document Title | Revision Number | Document Revision Object | Client Transmittal Ref Number | Transmittal Date | Document Status | Actual Response Date | Response Due Date | Revision Date | Required Action | Current/History | Document Origin | Discipline | Document Class
036909C-1000-PP-307 | OL1-2A92-0001 | OL1-2A92-0001 | VARIATION ORDER PROCEDURE | A | IFR | TPSK-LSPA1-T-CO-00035 | 2018-09-10 | Transmitted |  | 2018-09-24 | 2018-09-05 | IFR | C | ROC | PC | 2
036909C-1000-PP-313 | OL1-2A92-0002 | OL1-2A92-0002 | CAR & THIRD PARTY INSURANCE CLAIM PROCEDURE | 0 | IFI | TPSK-LSPA1-T-CO-00192 | 2018-10-18 | R2-Comments as noted | 2018-10-26 |  | 2018-10-18 | IFI | C | JVD | CO | 3
036909C-1000-PLG-305 | OL1-2B01-0001 | OL1-2B01-0001 | ENGINEERING AND PROCUREMENT LEVEL 3 SCHEDULE | A | IFR | TPSK-LSPA1-T-PC-00135 | 2018-10-05 | A3-Approved with comments, re-submit for review. | 2018-10-26 | 2018-10-19 | 2018-10-05 | IFR | C | JVD | PC | 2
036909C-1000-PLG-313 | OL1-2B91-0001 | OL1-2B91-0001 | SIX (6) WEEK LOOK-HEAD SCHEDULE | 0 | IFI | TPSK-LSPA1-T-PC-00096 | 2018-09-27 | Transmitted |  |  | 2018-09-26 | IFI | C | JVD | PC | 3
036909C-1000-PP-301 | OL1-2B92-0001 | OL1-2B92-0001 | PLANNING SCHEDULING AND PROGRESS MEASUREMENT PROCEDURE | A | IFR | TPSK-LSPA1-T-PC-00045 | 2018-09-13 | R2-Comments as noted | 2018-11-05 | 2018-09-28 | 2018-09-11 | IFR | C | ROC | PC | 2
036909C-1000-PLG-302 | OL1-2B92-0002 | OL1-2B92-0002 | 90 DAYS LOOK-HEAD SCHEDULE | A | IFR | TPSK-LSPA1-T-PC-00133 | 2018-10-05 | R2-Comments as noted | 2018-10-26 | 2018-10-19 | 2018-10-04 | IFR | C | JVD | PC | 2
036909C-1000-SL-0000-02 | OL1-2C01-0001 | OL1-2C01-0001 | SUBVENDOR LIST FOR COMPRESSOR AND TURBOEXPANDER - ABSTRACT FROM APPROVED VENDOR LIST | 0 | IMP | TPSK-LSPA1-T-PL-00134 | 2018-10-05 | Transmitted |  |  | 2018-10-05 | IFI | C | ROC | PL | 3
036909C-1000-PP-601 | OL1-2C92-0001 | OL1-2C92-0001 | PROJECT PROCUREMENT EXECUTION PLAN | A | IFR | TPSK-LSPA1-T-PC-00051 | 2018-09-14 | Transmitted |  | 2018-09-28 | 2018-09-13 | IFR | C | ROC | PC | 2
036909C-1000-PP-602 | OL1-2C92-0002 | OL1-2C92-0002 | PROJECT QCS COORDINATION PROCEDURE | A | IFR | TPSK-LSPA1-T-PL-00046 | 2018-09-13 | R2-Comments as noted | 2018-10-01 | 2018-09-28 | 2018-09-11 | IFR | H | JVD | PL | 2
036909C-1000-PP-602 | OL1-2C92-0002 | OL1-2C92-0002 | PROJECT QCS COORDINATION PROCEDURE | 0 | IMP | TPSK-LSPA1-T-PL-00244 | 2018-10-30 | Transmitted |  | 2018-11-15 | 2018-10-29 | IMP | C | JVD | PL | 2
036909C-1000-PP-605 | OL1-2C92-0005 | OL1-2C92-0005 | PROJECT QCS REQUIREMENTS FOR SUPPLIERS | A | IFR | TPSK-LSPA1-T-PL-00046 | 2018-09-13 | R2-Comments as noted | 2018-10-01 | 2018-09-28 | 2018-09-11 | IFR | H | JVD | PL | 2
036909C-1000-PP-605 | OL1-2C92-0005 | OL1-2C92-0005 | PROJECT QCS REQUIREMENTS FOR SUPPLIERS | 0 | IMP | TPSK-LSPA1-T-PL-00244 | 2018-10-30 | Transmitted |  | 2018-11-15 | 2018-10-29 | IMP | C | JVD | PL | 2
036909C-1000-PP-607 | OL1-2C92-0007 | OL1-2C92-0007 | PRESCRIPTIONS FOR PREPARATION OF DOCUMENTATION PACKAGE FOR TRANSPORTATION | A | IFR | TPSK-LSPA1-T-PL-00048 | 2018-09-13 | R2-Comments as noted | 2018-10-01 | 2018-09-28 | 2018-08-22 | IFR | H | ROC | PL | 2
036909C-1000-PP-607 | OL1-2C92-0007 | OL1-2C92-0007 | PRESCRIPTIONS FOR PREPARATION OF DOCUMENTATION PACKAGE FOR TRANSPORTATION | 0 | IMP | TPSK-LSPA1-T-PL-00140 | 2018-10-08 | R2-Comments as noted | 2018-10-30 | 2018-10-22 | 2018-10-05 | IMP | C | ROC | PL | 2
036909C-1000-PP-608 | OL1-2C92-0008 | OL1-2C92-0008 | PROJECT QCS EXPEDITING PROCEDURE | A | IFR | TPSK-LSPA1-T-PL-00046 | 2018-09-13 | Transmitted |  | 2018-09-28 | 2018-09-11 | IFR | H | ROC | PL | 2
036909C-1000-PP-609 | OL1-2C92-0009 | OL1-2C92-0009 | PROJECT QCS INSPECTION PROCEDURE | A | IFR | TPSK-LSPA1-T-PL-00046 | 2018-09-13 | R2-Comments as noted | 2018-10-01 | 2018-09-28 | 2018-09-11 | IFR | H | JVD | PL | 2
036909C-1000-PP-609 | OL1-2C92-0009 | OL1-2C92-0009 | PROJECT QCS INSPECTION PROCEDURE | 0 | IMP | TPSK-LSPA1-T-PL-00244 | 2018-10-30 | Transmitted |  | 2018-11-15 | 2018-10-29 | IMP | C | ROC | PL | 2
036909C-1000-PP-613 | OL1-2C92-0013 | OL1-2C92-0013 | SPARE PARTS & SPECIALS TOOLS INSTRUCTION | A | IFR | TPSK-LSPA1-T-PL-00064 | 2018-09-19 | R2-Comments as noted | 2018-09-25 | 2018-10-03 | 2018-09-14 | IFR | H | ROC | PL | 2
036909C-1000-PP-613 | OL1-2C92-0013 | OL1-2C92-0013 | SPARE PARTS & SPECIAL TOOLS INSTRUCTIONS | 0 | IMP | TPSK-LSPA1-T-PL-00119 | 2018-10-02 | Transmitted |  |  | 2018-10-01 | IFI | C | JVD | PL | 3
036909C-1000-PP-614 | OL1-2C92-0014 | OL1-2C92-0014 | PROJECT EXPEDITING AND INSPECTION LEVEL DEFINITION | A | IFR | TPSK-LSPA1-T-PL-00046 | 2018-09-13 | R2-Comments as noted | 2018-10-01 | 2018-09-28 | 2018-09-11 | IFR | H | JVD | PL | 2
036909C-1000-PP-614 | OL1-2C92-0014 | OL1-2C92-0014 | PROJECT EXPEDITING AND INSPECTION LEVEL DEFINITION | 0 | IMP | TPSK-LSPA1-T-PL-00244 | 2018-10-30 | Transmitted |  | 2018-11-15 | 2018-10-29 | IMP | C | JVD | PL | 2
036909C-1000-PP-615 | OL1-2C92-0015 | OL1-2C92-0015 | TRANSPORT PLAN | A | IFR | TPSK-LSPA1-T-PL-00048 | 2018-09-13 | R2-Comments as noted | 2018-10-01 | 2018-09-28 | 2018-08-31 | IFR | H | ROC | PL | 2
036909C-1000-PP-615 | OL1-2C92-0015 | OL1-2C92-0015 | TRANSPORTATION PLAN | 0 | IMP | TPSK-LSPA1-T-PL-00177 | 2018-10-16 | R2-Comments as noted | 2018-10-30 | 2018-10-30 | 2018-10-16 | IMP | C | JVD | PL | 2
036909C-1000-PP-616 | OL1-2C92-0016 | OL1-2C92-0016 | PARKING MARKING AND SHIPPING INSTRUCTIONS | A | IFR | TPSK-LSPA1-T-PL-00048 | 2018-09-13 | R2-Comments as noted | 2018-10-01 | 2018-09-28 | 2018-08-28 | IFR | H | ROC | PL | 2
036909C-1000-PP-616 | OL1-2C92-0016 | OL1-2C92-0016 | PARKING MARKING AND SHIPPING INSTRUCTIONS | 0 | IMP | TPSK-LSPA1-T-PL-00140 | 2018-10-08 | R2-Comments as noted | 2018-10-30 | 2018-10-22 | 2018-10-05 | IMP | C | ROC | PL | 2
036909C-1000-PP-617 | OL1-2C92-0017 | OL1-2C92-0017 | PROJECT SITE SERVICES CONDITIONS FOR SUPPLIER SPECIALISTS | A | IFR | TPSK-LSPA1-T-PL-00051 | 2018-09-14 | R2-Comments as noted | 2018-10-04 | 2018-09-28 | 2018-09-12 | IFR | H | JVD | PL | 2
036909C-1000-PP-617 | OL1-2C92-0017 | OL1-2C92-0017 | PROJECT SITE SERVICES CONDITIONS FOR SUPPLIER SPECIALISTS | 0 | IMP | TPSK-LSPA1-T-PL-00284 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-05 | IFR | C | JVD | PL | 2
036909C-1012-JSS-0000-9999 | OL1-2C93-0001 | OL1-2C93-0001 | GENERAL SUPPLY RULES FOR SUPPLIER DOCUMENTATION | A | IFI | TPSK-LSPA1-T-PL-00043 | 2018-09-12 | Transmitted |  |  | 2018-09-12 | IFI | C | HOC | PL | 3
036909C-1000-PP-703 | OL1-2D92-0001 | OL1-2D92-0001 | CONSTRUCTION SUBCONTRACTING PLAN | A | IFR | TPSK-LSPA1-T-CM-00193 | 2018-10-18 | Transmitted |  | 2018-11-01 | 2018-10-18 | IFR | C | SK | CM | 2
036909C-1000-JSD-1600-003 | OL1-2E04-6000 | OL1-2E04-6000 | GENERAL DESIGN RULE FOR PACKAGE EQUIPMENT ELECTRICAL SYSTEM | B | IFR | TPSK-LSPA1-T-EE-00126 | 2018-10-04 | R1-No comments | 2018-10-12 | 2018-10-18 | 2018-10-20 | IFR | C | ROC | EE | 2
036909C-1000-JSD-0000-03 | OL1-2G01-0001 | OL1-2G01-0001 | JSD FOR P&ID PREPARATION | A | IFA | TPSK-LSPA1-T-PE-00006 | 2018-07-31 | Transmitted | 2018-08-21 | 2018-08-13 | 2018-07-31 | IFR | C | ROC | PE | 2
036909C-1000-JSD-0000-0004 | OL1-2G01-0002 | OL1-2G01-0002 | COLD BOX DESIGN SPECIFICATION | A | IFR | TPSK-LSPA1-T-PE-00123 | 2018-10-03 | R1-No comments | 2018-10-12 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | PE | 2
036909C-1000-JSD-0000-0005 | OL1-2G01-0003 | OL1-2G01-0003 | PLATE-FIN EXCHANGER DESIGN SPECIFICATION | A | IFR | TPSK-LSPA1-T-PE-00123 | 2018-10-03 | R1-No comments | 2018-10-12 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | PE | 2
036909C-1000-DI-0007-0001 | OL1-2G02-0001 | OL1-2G02-0001 | PROCESS DESIGN BASIS | A | IFA | TPSK-LSPA1-T-PE-00002 | 2018-07-30 | A3-Not Approve Re-Submit For Re-Approval | 2018-08-17 | 2018-08-10 | 2018-07-20 | IFA | C | ROC | PE | 1
036909C-1000-DI-0007-0002 | OL1-2G02-0002 | OL1-2G02-0002 | EQUIPMENT BASIS OF DESIGN | A | IFA | TPSK-LSPA1-T-PE-00002 | 2018-07-30 | A3-Not Approve Re-Submit For Re-Approval | 2018-08-17 | 2018-08-10 | 2018-07-24 | IFA | C | ROC | PE | 1
036909C-1000-DI-0007-0003 | OL1-2G02-0003 | OL1-2G02-0003 | FLARE AND BLOWDOWN SYSTEM DESIGN BASIS | A | IFA | TPSK-LSPA1-T-PE-00034 | 2018-09-06 | R2-Comments as noted | 2018-09-28 | 2018-09-20 | 2018-09-06 | IFA | C | HOC | PE | 1
036909C-1000-DI-0007-0006 | OL1-2G02-0006 | OL1-2G02-0006 | FURNACE PROCESS BASIS OF DESIGN | A | IFA | TPSK-LSPA1-T-PE-00004 | 2018-07-31 | A3-Not Approve Re-Submit For Re-Approval | 2018-08-17 | 2018-08-13 | 2018-07-26 | IFA | C | HOC | PE | 1
036909C-1010-DI-0007-1001 | OL1-2G05-1001 | OL1-2G05-1001 | AREA BASIS OF DESIGN - 10 FEED PREPARATION | A | IFA | TPSK-LSPA1-T-PE-00011 | 2018-08-07 | A3-Approved with comments, re-submit for review. | 2018-08-27 | 2018-08-21 | 2018-08-06 | IFA | C | HOC | PE | 1
036909C-1020-DI-0007-2001 | OL1-2G05-2001 | OL1-2G05-2001 | AREA BASIS OF DESIGN - 20-21 QUENCH AND DILUTION STEAM | A | IFA | TPSK-LSPA1-T-PE-00011 | 2018-08-07 | A3-Approved with comments, re-submit for review. | 2018-08-27 | 2018-08-21 | 2018-08-06 | IFA | C | HOC | PE | 1
036909C-1022-DI-0007-2201 | OL1-2G05-2201 | OL1-2G05-2201 | AREA BASIS OF DESIGN - 22-24 COMPRESSSION TRAIN | A | IFA | TPSK-LSPA1-T-PE-00022 | 2018-08-13 | A3-Approved with comments, re-submit for review. | 2018-09-05 | 2018-08-27 | 2018-08-09 | IFA | C | HOC | PE | 1
036909C-1023-DI-0007-2301 | OL1-2G05-2301 | OL1-2G05-2301 | AREA BASIS OF DESIGN - 23 CAUSTIC AND SPENT CAUSTIC PRETREATMENT | A | IFA | TPSK-LSPA1-T-PE-00014 | 2018-08-08 | A3-Approved with comments, re-submit for review. | 2018-08-31 | 2018-08-22 | 2018-08-08 | IFA | C | HOC | PE | 1
036909C-1025-DI-0007-2501 | OL1-2G05-2501 | OL1-2G05-2501 | AREA BASIS OF DESIGN - 25 COLD FRACTIONATION | A | IFA | TPSK-LSPA1-T-PE-00011 | 2018-08-07 | A3-Approved with comments, re-submit for review. | 2018-08-27 | 2018-08-21 | 2018-08-06 | IFA | C | HOC | PE | 1
036909C-1026-DI-0007-2601 | OL1-2G05-2601 | OL1-2G05-2601 | AREA BASIS OF DESIGN - 26 HOT FRACTIONATION | A | IFA | TPSK-LSPA1-T-PE-00014 | 2018-08-08 | A3-Approved with comments, re-submit for review. | 2018-08-31 | 2018-08-22 | 2018-08-07 | IFA | C | HOC | PE | 1
036909C-1026-DI-0007-2602 | OL1-2G05-2602 | OL1-2G05-2602 | AREA BASIS OF DESIGN - 262 C3 HYDROGENATION | A | IFA | TPSK-LSPA1-T-PE-00307 | 2018-11-12 | Transmitted |  | 2018-11-26 | 2018-11-09 | IFA | C | HOC | PE | 1
036909C-1028-DI-0007-2801 | OL1-2G05-2801 | OL1-2G05-2801 | AREA BASIS OF DESIGN - 28 REFRIGERATION | A | IFA | TPSK-LSPA1-T-PE-00022 | 2018-08-13 | A1-Approved without comments | 2018-09-05 | 2018-08-27 | 2018-08-09 | IFA | C | HOC | PE | 1
036909C-1030-DI-0007-3001 | OL1-2G05-3001 | OL1-2G05-3001 | AREA BASIS OF DESIGN - 30 BDU | A | IFA | TPSK-LSPA1-T-PE-00150 | 2018-10-09 | Transmitted |  | 2018-10-23 | 2018-10-09 | IFA | C | HOC | PE | 1
036909C-1050-DI-0007-5001 | OL1-2G05-5001 | OL1-2G05-5001 | AREA BASIS OF DESIGN - 50 ISBL SUPPORTING UTILITIES | A | IFA | TPSK-LSPA1-T-PE-00003 | 2018-07-31 | A3-Not Approve Re-Submit For Re-Approval | 2018-08-17 | 2018-08-13 | 2018-07-25 | IFA | C | HOC | PE | 1
036909C-1053-DI-0007-5301 | OL1-2G05-5301 | OL1-2G05-5301 | AREA BASIS OF DESIGN - 53 COOLING TOWER SYSTEM | A | IFA | TPSK-LSPA1-T-PE-00003 | 2018-07-31 | A3-Not Approve Re-Submit For Re-Approval | 2018-08-17 | 2018-08-13 | 2018-07-25 | IFA | H | HOC | PE | 1
036909C-1053-DI-0007-5301 | OL1-2G05-5301 | OL1-2G05-5301 | AREA BASIS OF DESIGN - 53 COOLING TOWER SYSTEM | B | IFD | TPSK-LSPA1-T-PE-00003 | 2018-09-26 | Transmitted |  |  | 2018-09-24 | IFI | C | HOC | PE | 3
036909C-1055-DI-0007-5501 | OL1-2G05-5501 | OL1-2G05-5501 | AREA BASIS OF DESIGN - 55 FLARE SYSTEM | A | IFA | TPSK-LSPA1-T-PE-00016 | 2018-08-09 | A3-Not Approve Re-Submit For Re-Approval | 2018-08-29 | 2018-08-23 | 2018-08-09 | IFA | C | HOC | PE | 1
036909C-1056-DI-0007-5601 | OL1-2G05-5601 | OL1-2G05-5601 | AREA BASIS OF DESIGN - 56 WASTE WATER TREATMENT SYSTEM | A | IFA | TPSK-LSPA1-T-PE-00011 | 2018-08-07 | A3-Approved with comments, re-submit for review. | 2018-08-27 | 2018-08-21 | 2018-08-03 | IFA | H | HOC | PE | 1
036909C-1056-DI-0007-5601 | OL1-2G05-5601 | OL1-2G05-5601 | AREA BASIS OF DESIGN - 56 WASTE WATER TREATMENT SYSTEM | B | IFD | TPSK-LSPA1-T-PE-00011 | 2018-09-26 | A3-Approved with comments, re-submit for review. | 2018-10-12 |  | 2018-09-13 | IFI | C | HOC | PE | 3
036909C-1000-NM-0014-0001 | OL1-2G22-0001 | OL1-2G22-0001 | FLARE LOAD SUMMARY | A | IFR | TPSK-LSPA1-T-PE-00229 | 2018-10-25 | R2-Comments as noted | 2018-11-14 | 2018-11-08 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1010-PDS-0800-1000 | OL1-2G30-1000 | OL1-2G30-1000 | PROCESS EQUIPMENT DATASHEET - 10-D-1000 - LPG DRUM | A | IFR | TPSK-LSPA1-T-PE-00227 | 2018-10-25 | Transmitted |  | 2018-11-08 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-1010-PDS-0600-1001 | OL1-2G30-1001 | OL1-2G30-1001 | PROCESS EQUIPMENT DATASHEET - 10-E-1000 - LPG VAPORIZER | A | IFR | TPSK-LSPA1-T-PE-00176 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1010-PDS-0600-1003 | OL1-2G30-1003 | OL1-2G30-1003 | PROCESS EQUIPMENT DATASHEET - 10-E-1001 - LPG STEAM VAPORIZER | A | IFR | TPSK-LSPA1-T-PE-00179 | 2018-10-16 | Transmitted |  | 2018-10-30 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1010-PDS-0600-1005 | OL1-2G30-1005 | OL1-2G30-1005 | PROCESS EQUIPMENT DATASHEET - 10-E-1005 - LPG FEED HEATER | A | IFR | TPSK-LSPA1-T-PE-00176 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1011-PDS-1040-1111 | OL1-2G30-1011 | OL1-2G30-1011 | PROCESS EQUIPMENT DATASHEET - 10-C-1100 - USC 36M INDUCED DRAFT FAN | B | IFD | TPSK-LSPA1-T-PE-00222 | 2018-10-24 | Transmitted |  |  | 2018-10-23 | IFD | C | HOC | PE | 2
036909C-1010-PDS-0600-1015 | OL1-2G30-1015 | OL1-2G30-1015 | PROCESS EQUIPMENT DATASHEET - 10-E-1015 - LPG SUPERHEATER | A | IFR | TPSK-LSPA1-T-PE-00176 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1010-PDS-0600-1020 | OL1-2G30-1020 | OL1-2G30-1020 | PROCESS EQUIPMENT DATASHEET - 10-E-1020 - LIQUID FEED HEATER | A | IFR | TPSK-LSPA1-T-PE-00206 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1010-PDS-0600-1051 | OL1-2G30-1051 | OL1-2G30-1051 | PROCESS EQUIPMENT DATASHEET - 10-E-1050 - C2 FEED SUPERHEATER | A | IFR | TPSK-LSPA1-T-PE-00206 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1011-PDS-0117-1101 | OL1-2G30-1101 | OL1-2G30-1101 | PROCESS EQUIPMENT DATASHEET - 10-H-1100 - 36M CRACKING FURNACE YIELDS | A | IFR | TPSK-LSPA1-T-PE-00204 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1011-PDS-0117-1102 | OL1-2G30-1102 | OL1-2G30-1102 | ANTICIPATED OPERATING CONDITIONS - 10-H-1100 - USC 36M GAS CRACKING FURNACE | 0 | IFI | TPSK-LSPA1-T-PE-00224 | 2018-10-24 | Transmitted |  |  | 2018-10-24 | IFI | C | HOC | PE | 3
036909C-1011-PDS-0191-1106 | OL1-2G30-1106 | OL1-2G30-1106 | PROCESS EQUIPMENT DATASHEET - 10-H-1100 - USC 36M BURNER | A | IFR | TPSK-LSPA1-T-PE-00241 | 2018-10-30 | Transmitted |  | 2018-11-12 | 2018-10-26 | IFR | C | HOC | PE | 2
036909C-1011-PDS-0811-1107 | OL1-2G30-1107 | OL1-2G30-1107 | PROCESS EQUIPMENT DATASHEET - 10-D-1100 - 36M CRACKING FURNACE STEAM DRUM | A | IFR | TPSK-LSPA1-T-PE-00159 | 2018-10-11 | R2-Comments as noted | 2018-11-05 | 2018-10-25 | 2018-10-11 | IFR | C | HOC | PE | 2
036909C-1011-PDS-0630-1108 | OL1-2G30-1108 | OL1-2G30-1108 | PROCESS EQUIPMENT DATASHEET - 10-E-1100A1 - F6 - USC 36M USX EXCHANGER | A | IFR | TPSK-LSPA1-T-PE-00237 | 2018-10-29 | Transmitted |  | 2018-11-12 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-1011-PDS-0610-1109 | OL1-2G30-1109 | OL1-2G30-1109 | PROCESS EQUIPMENT DATASHEET - 10-E-1110 - USC 36M TLX-1 QUENCH EXCHANGER | A | IFR | TPSK-LSPA1-T-PE-00237 | 2018-10-29 | Transmitted |  | 2018-11-12 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-1011-PDS-0610-1110 | OL1-2G30-1110 | OL1-2G30-1110 | PROCESS EQUIPMENT DATASHEET - 10-E-1120 - USC 36M TLX-2 QUENCH EXCHANGER | A | IFR | TPSK-LSPA1-T-PE-00237 | 2018-10-29 | Transmitted |  | 2018-11-12 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-1012-PDS-0117-1201 | OL1-2G30-1201 | OL1-2G30-1201 | PROCESS EQUIPMENT DATASHEET - 10-H-1200 - 132U CRACKING FURNACE YIELDS | A | IFR | TPSK-LSPA1-T-PE-00204 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1012-PDS-0117-1202 | OL1-2G30-1202 | OL1-2G30-1202 | ANTICIPATED OPERATING CONDITIONS - 10-H-1200/1600 - USC 132U LIQUID CRACKING FURNACE | 0 | IFI | TPSK-LSPA1-T-PE-00224 | 2018-10-24 | Transmitted |  |  | 2018-10-24 | IFI | C | HOC | PE | 3
036909C-1012-PDS-0191-1206 | OL1-2G30-1206 | OL1-2G30-1206 | PROCESS EQUIPMENT DATASHEET - 10-H-1200 - 1600 - USC 132U BURNER | A | IFR | TPSK-LSPA1-T-PE-00241 | 2018-10-30 | Transmitted |  | 2018-11-12 | 2018-10-26 | IFR | C | HOC | PE | 2
036909C-1012-PDS-0811-1207 | OL1-2G30-1207 | OL1-2G30-1207 | PROCESS EQUIPMENT DATASHEET - 10-D-1200-1600 - 132U CRACKING FURNACE STEAM DRUM | A | IFR | TPSK-LSPA1-T-PE-00159 | 2018-10-11 | R2-Comments as noted | 2018-11-05 | 2018-10-25 | 2018-10-11 | IFR | C | HOC | PE | 2
036909C-1012-PDS-0630-1208 | OL1-2G30-1208 | OL1-2G30-1208 | PROCESS EQUIPMENT DATASHEET - 10-E-1200A-F - 10-E-1600A-F - USC 132U SLE EXCHANGER | A | IFR | TPSK-LSPA1-T-PE-00237 | 2018-10-29 | Transmitted |  | 2018-11-12 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-1012-PDS-0610-1209 | OL1-2G30-1209 | OL1-2G30-1209 | PROCESS EQUIPMENT DATASHEET - 10-E-1210 - 10-E-1610 - USC 132U TLX QUENCH EXCHANGER | A | IFR | TPSK-LSPA1-T-PE-00237 | 2018-10-29 | Transmitted |  | 2018-11-12 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-1012-PDS-1040-1211 | OL1-2G30-1211 | OL1-2G30-1211 | PROCESS EQUIPMENT DATASHEET - 10-C-1200 1600 - USC 132U INDUCED DRAFT FAN | B | IFD | TPSK-LSPA1-T-PE-00222 | 2018-10-24 | Transmitted |  |  | 2018-10-23 | IFD | C | HOC | PE | 2
036909C-1019-PDS-1000-1950 | OL1-2G30-1950 | OL1-2G30-1950 | PROCESS EQUIPMENT DATA SHEET - 10-PK-1950 - DECOKE AIR COMPRESSOR PACKAGE | A | IFA | TPSK-LSPA1-T-PE-00031 | 2018-08-29 | A3-Approved with comments, re-submit for review. | 2018-09-28 |  | 2018-08-29 | IFA | H | HOC | PE | 1
036909C-1019-PDS-1000-1950 | OL1-2G30-1950 | OL1-2G30-1950 | PROCESS EQUIPMENT DATASHEET - 10-PK-1950 - DECOKE AIR COMPRESSOR PKG | B | IFD | TPSK-LSPA1-T-PE-00114 | 2018-09-28 | R2-Comments as noted | 2018-10-24 |  | 2018-09-28 | IFI | H | HOC | PE | 3
036909C-1019-PDS-1000-1950 | OL1-2G30-1950 | OL1-2G30-1950 | PROCESS EQUIPMENT DATASHEET - 10-PK-1950 - DECOKE AIR COMPRESSOR PKG | C | IFD | TPSK-LSPA1-T-PE-00242 | 2018-10-30 | Transmitted |  |  | 2018-10-29 | IFI | C | HOC | PE | 1
036909C-1020-PDS-0500-2000 | OL1-2G30-2000 | OL1-2G30-2000 | PROCESS EQUIPMENT DATASHEET - 10-T-2000 - QUENCH OIL TOWER | A | IFR | TPSK-LSPA1-T-PE-00162 | 2018-10-12 | R2-Comments as noted | 2018-11-05 | 2018-10-26 | 2018-10-11 | IFR | C | HOC | PE | 2
036909C-1020-PDS-0900-2006 | OL1-2G30-2006 | OL1-2G30-2006 | PROCESS EQUIPMENT DATASHEET - 10-P-2006 A-C - QUENCH OIL PUMPS | A | IFA | TPSK-LSPA1-T-PE-00071 | 2018-09-20 | A3-Approved with comments, re-submit for review. | 2018-10-09 | 2018-10-04 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1020-PDS-0900-2006 | OL1-2G30-2006 | OL1-2G30-2006 | PROCESS EQUIPMENT DATASHEET - 10-P-2006 A-C - QUENCH OIL PUMPS | B | IFD | TPSK-LSPA1-T-PE-00202 | 2018-10-22 | Transmitted |  |  | 2018-10-18 | IFI | C | HOC | PE | 1
036909C-1020-PDS-0600-2015 | OL1-2G30-2015 | OL1-2G30-2015 | PROCESS EQUIPMENT DATASHEET - 10-E-2008 A-C - LS2 STEAM GENERATORS | A | IFR | TPSK-LSPA1-T-PE-00305 | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-09 | IFR | C | HOC | PE | 2
036909C-1020-PDS-0500-2020 | OL1-2G30-2020 | OL1-2G30-2020 | PROCESS EQUIPMENT DATASHEET - 10-T-2020 - LIGHT FUEL OIL STRIPPER | A | IFR | TPSK-LSPA1-T-PE-00238 | 2018-10-29 | Transmitted |  | 2018-11-12 | 2018-10-26 | IFR | C | HOC | PE | 2
036909C-1020-PDS-0900-2024 | OL1-2G30-2024 | OL1-2G30-2024 | PROCESS EQUIPMENT DATASHEET - 10-P-2026 A-B - LIGHT FUEL OIL PUMPS | A | IFR | TPSK-LSPA1-T-PE-00285 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1020-PDS-0600-2026 | OL1-2G30-2026 | OL1-2G30-2026 | PROCESS EQUIPMENT DATASHEET - 10-E-2026 - FO PRODUCT COOLER | A | IFR | TPSK-LSPA1-T-PE-00298 | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-08 | IFR | C | HOC | PE | 2
036909C-1020-PDS-0500-2040 | OL1-2G30-2040 | OL1-2G30-2040 | PROCESS EQUIPMENT DATASHEET - 10-T-2040 - HEAVY FUEL OIL STRIPPER | A | IFR | TPSK-LSPA1-T-PE-00162 | 2018-10-12 | R2-Comments as noted | 2018-11-05 | 2018-10-26 | 2018-10-11 | IFR | C | HOC | PE | 2
036909C-1020-PDS-0900-2046 | OL1-2G30-2046 | OL1-2G30-2046 | PROCESS EQUIPMENT DATASHEET - 10-P-2046 A-B - HEAVY FUEL OIL PUMPS | A | IFR | TPSK-LSPA1-T-PE-00285 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1020-PDS-0600-2048 | OL1-2G30-2048 | OL1-2G30-2048 | PROCESS EQUIPMENT DATASHEET - 10-E-2048 - HEAVY FUEL OIL PRODUCT COOLER | A | IFR | TPSK-LSPA1-T-PE-00298 | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-08 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0500-2100 | OL1-2G30-2100 | OL1-2G30-2100 | PROCESS EQUIPMENT DATASHEET - 10-T-2100 - QUENCH WATER TOWER | A | IFR | TPSK-LSPA1-T-PE-00238 | 2018-10-29 | Transmitted |  | 2018-11-12 | 2018-10-26 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0600-2101 | OL1-2G30-2101 | OL1-2G30-2101 | PROCESS EQUIPMENT DATA SHEET - 10-E-2100 - QUENCH WATER COOLER | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-07 | IFA | H | HOC | PE | 1
036909C-1021-PDS-0600-2101 | OL1-2G30-2101 | OL1-2G30-2101 | PROCESS EQUIPMENT DATASHEET - 10-E-2100 A-F - QUENCH WATER COOLER | B | IFD | TPSK-LSPA1-T-PE-00143 | 2018-10-08 | Transmitted |  |  | 2018-10-04 | IFI | C | HOC | PE | 3
036909C-1021-PDS-0900-2105 | OL1-2G30-2105 | OL1-2G30-2105 | PROCESS EQUIPMENT DATASHEET - 10-P-2105 A-B - QUENCH OIL REFLUX PUMPS | A | IFR | TPSK-LSPA1-T-PE-00285 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0900-2106 | OL1-2G30-2106 | OL1-2G30-2106 | PROCESS EQUIPMENT DATASHEET - 10-P-2106 A-C - QUENCH WATER PUMPS | A | IFA | TPSK-LSPA1-T-PE-00070 | 2018-09-20 | A1-Approved without comments | 2018-10-09 | 2018-10-04 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1021-PDS-0900-2106 | OL1-2G30-2106 | OL1-2G30-2106 | PROCESS EQUIPMENT DATASHEET - 10-P-2106 A-C - QUENCH WATER PUMPS | B | IFD | TPSK-LSPA1-T-PE-00202 | 2018-10-22 | Transmitted |  |  | 2018-10-18 | IFI | C | HOC | PE | 1
036909C-1021-PDS-0500-2120 | OL1-2G30-2120 | OL1-2G30-2120 | PROCESS EQUIPMENT DATASHEET - 10-T-2120 - DISTILLATE STRIPPER | A | IFR | TPSK-LSPA1-T-PE-00253 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-29 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0600-2125 | OL1-2G30-2125 | OL1-2G30-2125 | PROCESS EQUIPMENT DATASHEET - 10-E-2125 - DISTILLATE STRIPPER REBOILER | A | IFR | TPSK-LSPA1-T-PE-00265 | 2018-11-01 | Transmitted |  | 2018-11-15 | 2018-11-01 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0600-2137 | OL1-2G30-2137 | OL1-2G30-2137 | PROCESS EQUIPMENT DATASHEET - 10-E-2136 - PROCESS WATER STRIPPER FEED HEATER | A | IFR | TPSK-LSPA1-T-PE-00194 | 2018-10-18 | Transmitted |  | 2018-11-01 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0500-2140 | OL1-2G30-2140 | OL1-2G30-2140 | PROCESS EQUIPMENT DATASHEET - 10-T-2140 - PROCESS WATER STRIPPER | A | IFR | TPSK-LSPA1-T-PE-00189 | 2018-10-17 | Transmitted |  | 2018-10-31 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0600-2145 | OL1-2G30-2145 | OL1-2G30-2145 | PROCESS EQUIPMENT DATASHEET - 10-E-2145 - PROCESS WATER STRIPPER REBOILER | A | IFR | TPSK-LSPA1-T-PE-00194 | 2018-10-18 | Transmitted |  | 2018-11-01 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0900-2146 | OL1-2G30-2146 | OL1-2G30-2146 | PROCESS EQUIPMENT DATASHEET 10-P-2146 DSG FEED PUMPS | A | IFA | TPSK-LSPA1-T-PE-00069 | 2018-09-20 | A3-Approved with comments, re-submit for review. | 2018-10-09 | 2018-10-04 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1021-PDS-0900-2146 | OL1-2G30-2146 | OL1-2G30-2146 | PROCESS EQUIPMENT DATASHEET - 10-P-2146 A-B - DSG FEED PUMPS | B | IFD | TPSK-LSPA1-T-PE-00202 | 2018-10-22 | Transmitted |  |  | 2018-10-18 | IFI | C | HOC | PE | 1
036909C-1021-PDS-0600-2147 | OL1-2G30-2147 | OL1-2G30-2147 | PROCESS EQUIPMENT DATASHEET - 10-E-2146 - DSG FEED HEATER | A | IFR | TPSK-LSPA1-T-PE-00194 | 2018-10-18 | Transmitted |  | 2018-11-01 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0800-2160 | OL1-2G30-2160 | OL1-2G30-2160 | PROCESS EQUIPMENT DATASHEET - 10-D-2160 - DILUTION STEAM GENERATOR | A | IFA | TPSK-LSPA1-T-PE-00115 | 2018-09-28 | A3-Approved with comments, re-submit for review. | 2018-11-05 | 2018-10-12 | 2018-09-28 | IFA | C | HOC | PE | 1
036909C-1021-PDS-0600-2161 | OL1-2G30-2161 | OL1-2G30-2161 | PROCESS EQUIPMENT DATASHEET - 10-E-2160 - DILUTION STEAM SUPERHEATER | A | IFR | TPSK-LSPA1-T-PE-00194 | 2018-10-18 | Transmitted |  | 2018-11-01 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0600-2165 | OL1-2G30-2165 | OL1-2G30-2165 | PROCESS EQUIPMENT DATASHEET - 10-E-2165 A-D DSG REBOILERS | A | IFR | TPSK-LSPA1-T-PE-00194 | 2018-10-18 | Transmitted |  | 2018-11-01 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1021-PDS-0600-2166 | OL1-2G30-2166 | OL1-2G30-2166 | PROCESS EQUIPMENT DATASHEET - 10-E-2166 - DSG BLOWDOWN COOLER | A | IFR | TPSK-LSPA1-T-PE-00209 | 2018-10-23 | Transmitted |  | 2018-11-06 | 2018-10-22 | IFR | C | HOC | PE | 2
036909C-1022-PDS-1000-2200 | OL1-2G30-2200 | OL1-2G30-2200 | PROCESS EQUIPMENT DATA SHEET - 10-C-2200 - CRACKED GAS COMPRESSOR | A | IFA | TPSK-LSPA1-T-PE-00025 | 2018-08-22 | A3-Approved with comments, re-submit for review. | 2018-09-11 | 2018-09-05 | 2018-08-22 | IFA | H | HOC | PE | 1
036909C-1022-PDS-1000-2200 | OL1-2G30-2200 | OL1-2G30-2200 | PROCESS EQUIPMENT DATA SHEET - 10-C-2200 - CRACKED GAS COMPRESSOR | B | IFD | TPSK-LSPA1-T-PE-00055 | 2018-09-17 | Transmitted |  |  | 2018-09-14 | IFI | C | HOC | PE | 3
036909C-1022-PDS-0800-2210 | OL1-2G30-2210 | OL1-2G30-2210 | PROCESS EQUIPMENT DATASHEET - 10-D-2210 - CG 1ST STAGE SUCTION DRUM | A | IFR | TPSK-LSPA1-T-PE-00144 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-08 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0600-2211 | OL1-2G30-2211 | OL1-2G30-2211 | PROCESS EQUIPMENT DATASHEET - 10-E-2210 A-B - CG 1ST STAGE AFTERCOOLERS | A | IFR | TPSK-LSPA1-T-PE-00266 | 2018-11-01 | Transmitted |  | 2018-11-15 | 2018-11-01 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0900-2212 | OL1-2G30-2212 | OL1-2G30-2212 | PROCESS EQUIPMENT DATASHEET - 10-P-2210 A-B - CG 1ST STAGE CONDENSATE PUMPS | A | IFR | TPSK-LSPA1-T-PE-00285 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0800-2220 | OL1-2G30-2220 | OL1-2G30-2220 | PROCESS EQUIPMENT DATASHEET - 10-D-2220 - CG 2ND STAGE SUCTION DRUM | A | IFR | TPSK-LSPA1-T-PE-00144 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-08 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0600-2221 | OL1-2G30-2221 | OL1-2G30-2221 | PROCESS EQUIPMENT DATASHEET - 10-E-2220 A-B - CG 2ND STAGE AFTERCOOLERS | A | IFR | TPSK-LSPA1-T-PE-00206 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0900-2222 | OL1-2G30-2222 | OL1-2G30-2222 | PROCESS EQUIPMENT DATASHEET - 10-P-2220 A-B - CG 2ND STAGE CONDENSED HC PUMPS | A | IFR | TPSK-LSPA1-T-PE-00285 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0800-2230 | OL1-2G30-2230 | OL1-2G30-2230 | PROCESS EQUIPMENT DATASHEET - 10-D-2230 - CG 3RD STAGE SUCTION DRUM | A | IFR | TPSK-LSPA1-T-PE-00144 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-08 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0600-2231 | OL1-2G30-2231 | OL1-2G30-2231 | PROCESS EQUIPMENT DATASHEET - 10-E-2230 A-B - CG 3RD STAGE AFTERCOOLER | A | IFR | TPSK-LSPA1-T-PE-00206 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0800-2240 | OL1-2G30-2240 | OL1-2G30-2240 | PROCESS EQUIPMENT DATASHEET - 10-D-2240 - CG 4TH STAGE SUCTION DRUM | A | IFR | TPSK-LSPA1-T-PE-00175 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0600-2241 | OL1-2G30-2241 | OL1-2G30-2241 | PROCESS EQUIPMENT DATASHEET - 10-E-2240 A-B - CG 4TH STAGE AFTERCOOLER | A | IFR | TPSK-LSPA1-T-PE-00206 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1022-PDS-0800-2245 | OL1-2G30-2245 | OL1-2G30-2245 | PROCESS EQUIPMENT DATASHEET - 10-D-2245 - CG 4TH STAGE DISCHARGE DRUM | A | IFR | TPSK-LSPA1-T-PE-00264 | 2018-11-01 | Transmitted |  | 2018-11-15 | 2018-10-31 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0500-2300 | OL1-2G30-2300 | OL1-2G30-2300 | PROCESS EQUIPMENT DATA SHEET - 10-T-2300 - CAUSTIC TOWER | A | IFA | TPSK-LSPA1-T-PE-00060 | 2018-09-18 | A3-Approved with comments, re-submit for review. | 2018-10-24 | 2018-10-02 | 2018-09-17 | IFA | H | HOC | PE | 1
036909C-1023-PDS-0500-2300 | OL1-2G30-2300 | OL1-2G30-2300 | PROCESS EQUIPMENT DATASHEET - 10-T-2300 - CAUSTIC TOWER | B | IFD | TPSK-LSPA1-T-PE-00290 | 2018-11-08 | Transmitted |  |  | 2018-11-08 | IFI | C | HOC | PE | 1
036909C-1023-PDS-4200-2301 | OL1-2G30-2301 | OL1-2G30-2301 | PROCESS EQUIPMENT DATASHEET - 10-X-2300 - CAUSTIC DILUTION MIXER | A | IFR | TPSK-LSPA1-T-PE-00173 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0900-2302 | OL1-2G30-2302 | OL1-2G30-2302 | PROCESS EQUIPMENT DATASHEET - 10-P-2302 A-B - STRONG CAUSTIC CIRCULATING PUMPS | A | IFR | TPSK-LSPA1-T-PE-00174 | 2018-10-15 | R1-No comments | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0900-2304 | OL1-2G30-2304 | OL1-2G30-2304 | PROCESS EQUIPMENT DATASHEET - 10-P-2304 - INTERMEDIATE CAUSTIC CIRCULATING PUMP | A | IFR | TPSK-LSPA1-T-PE-00174 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0600-2305 | OL1-2G30-2305 | OL1-2G30-2305 | PROCESS EQUIPMENT DATASHEET - 10-E-2305 - CAUSTIC TOWER FEED HEATER | A | IFR | TPSK-LSPA1-T-PE-00259 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-31 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0900-2306 | OL1-2G30-2306 | OL1-2G30-2306 | PROCESS EQUIPMENT DATASHEET - 10-P-2306 A-B - WEAK CAUSTIC CIRCULATING PUMPS | A | IFR | TPSK-LSPA1-T-PE-00174 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0840-2307 | OL1-2G30-2307 | OL1-2G30-2307 | PROCESS EQUIPMENT DATASHEET - 10-F-2306 A-B - WEAK CAUSTIC CIRCULATING FILTERS | A | IFR | TPSK-LSPA1-T-PE-00205 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1023-PDS-4200-2308 | OL1-2G30-2308 | OL1-2G30-2308 | PROCESS EQUIPMENT DATASHEET - 10-X-2306 - WEAK CAUSTIC - WASH OIL MIXER | A | IFR | TPSK-LSPA1-T-PE-00173 | 2018-10-15 | R2-Comments as noted | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0800-2309 | OL1-2G30-2309 | OL1-2G30-2309 | PROCESS EQUIPMENT DATASHEET - 10-D-2305 - YELLOW OIL DRUM | A | IFA | TPSK-LSPA1-T-PE-00102 | 2018-09-27 | A3-Approved with comments, re-submit for review. | 2018-11-14 | 2018-10-11 | 2018-09-27 | IFA | C | HOC | PE | 1
036909C-1023-PDS-0800-2310 | OL1-2G30-2310 | OL1-2G30-2310 | PROCESS EQUIPMENT DATASHEET - 10-D-2310 - SPENT CAUSTIC DEOILING DRUM | A | IFR | TPSK-LSPA1-T-PE-00254 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-29 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0900-2311 | OL1-2G30-2311 | OL1-2G30-2311 | PROCESS EQUIPMENT DATASHEET - 10-P-2310 A-B - WASH OIL CIRCULATING PUMPS | A | IFR | TPSK-LSPA1-T-PE-00174 | 2018-10-15 | R1-No comments | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-4200-2313 | OL1-2G30-2313 | OL1-2G30-2313 | PROCESS EQUIPMENT DATASHEET - 10-X-2312 - SPENT WASH OIL MIXER | A | IFR | TPSK-LSPA1-T-PE-00173 | 2018-10-15 | R1-No comments | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0840-2314 | OL1-2G30-2314 | OL1-2G30-2314 | PROCESS EQUIPMENT DATASHEET - 10-F-2310 A-B - WASH OIL CIRCULATING FILTER | A | IFR | TPSK-LSPA1-T-PE-00205 | 2018-10-22 | Transmitted |  | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1023-PDS-4200-2315 | OL1-2G30-2315 | OL1-2G30-2315 | PROCESS EQUIPMENT DATASHEET - 10-X-2310 - SPENT CAUSTIC MIXER | A | IFR | TPSK-LSPA1-T-PE-00173 | 2018-10-15 | R1-No comments | 2018-11-14 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0800-2316 | OL1-2G30-2316 | OL1-2G30-2316 | PROCESS EQUIPMENT DATASHEET - 10-D-2316 - SPENT CAUSTIC DEGASSING DRUM | A | IFR | TPSK-LSPA1-T-PE-00175 | 2018-10-15 | Transmitted |  | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0840-2319 | OL1-2G30-2319 | OL1-2G30-2319 | PROCESS EQUIPMENT DATASHEET - 10-F-2320 A-B - SPENT CAUSTIC PUMP DISCHARGE FILTERS | A | IFR | TPSK-LSPA1-T-PE-00255 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-29 | IFR | C | HOC | PE | 2
036909C-1023-PDS-2500-2320 | OL1-2G30-2320 | OL1-2G30-2320 | PROCESS EQUIPMENT DATA SHEET - 10-TK-2320 - SPENT CAUSTIC STORAGE TANK | A | IFA | TPSK-LSPA1-T-PE-00068 | 2018-09-20 | A3-Approved with comments, re-submit for review. | 2018-10-09 | 2018-10-04 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1023-PDS-2500-2320 | OL1-2G30-2320 | OL1-2G30-2320 | PROCESS EQUIPMENT DATASHEET - 10-TK-2320 - SPENT CAUSTIC STORAGE TANK | B | IFD | TPSK-LSPA1-T-PE-00203 | 2018-10-22 | Transmitted |  |  | 2018-10-18 | IFI | C | HOC | PE | 1
036909C-1023-PDS-0900-2321 | OL1-2G30-2321 | OL1-2G30-2321 | PROCESS EQUIPMENT DATASHEET - 10-P-2320 A-B - SPENT CAUSTIC PUMPS | A | IFR | TPSK-LSPA1-T-PE-00252 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-29 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0800-2322 | OL1-2G30-2322 | OL1-2G30-2322 | PROCESS EQUIPMENT DATASHEET - 10-D-2322 - SKIM OIL DRUM | A | IFA | TPSK-LSPA1-T-PE-00111 | 2018-09-28 | Transmitted |  | 2018-10-12 | 2018-09-27 | IFA | C | HOC | PE | 1
036909C-1023-PDS-0500-2330 | OL1-2G30-2330 | OL1-2G30-2330 | PROCESS EQUIPMENT DATASHEET - 10-T-2330 - SPENT CAUSTIC STRIPPER | A | IFA | TPSK-LSPA1-T-PE-00073 | 2018-09-24 | A3-Approved with comments, re-submit for review. | 2018-10-12 | 2018-10-08 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1023-PDS-0500-2330 | OL1-2G30-2330 | OL1-2G30-2330 | PROCESS EQUIPMENT DATASHEET - 10-T-2330 - SPENT CAUSTIC STRIPPER | B | IFA | TPSK-LSPA1-T-PE-00160 | 2018-10-11 | Transmitted |  | 2018-10-25 | 2018-10-10 | IFA | C | HOC | PE | 1
036909C-1023-PDS-0800-2331 | OL1-2G30-2331 | OL1-2G30-2331 | PROCESS EQUIPMENT DATASHEET - 10-D-2330 - SPENT CAUSTIC STRIPPER OVHD DRUM | A | IFR | TPSK-LSPA1-T-PE-00175 | 2018-10-15 | Transmitted |  | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1023-PDS-4100-2350 | OL1-2G30-2350 | OL1-2G30-2350 | PROCESS EQUIPMENT DATASHEET - 10-PK-2350 - WET AIR OXIDATION PKG | A | IFR | TPSK-LSPA1-T-PE-00180 | 2018-10-16 | Transmitted |  | 2018-10-30 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1023-PDS-0800-2390 | OL1-2G30-2390 | OL1-2G30-2390 | PROCESS EQUIPMENT DATASHEET - 10-D-2390 - CAUSTIC DRAIN DRUM | A | IFA | TPSK-LSPA1-T-PE-00102 | 2018-09-27 | A3-Approved with comments, re-submit for review. | 2018-11-14 | 2018-10-11 | 2018-09-27 | IFA | C | HOC | PE | 1
036909C-1023-PDS-0800-2392 | OL1-2G30-2392 | OL1-2G30-2392 | PROCESS EQUIPMENT DATASHEET - 10-D-2392 SPENT CAUSTIC DRAIN DRUM | A | IFA | TPSK-LSPA1-T-PE-00102 | 2018-09-27 | A3-Approved with comments, re-submit for review. | 2018-11-14 | 2018-10-11 | 2018-09-27 | IFA | C | HOC | PE | 1
036909C-1023-PDS-0900-2393 | OL1-2G30-2393 | OL1-2G30-2393 | PROCESS EQUIPMENT DATASHEET - 10-P-2392 - SPENT CAUSTIC DRAIN DRUM PUMP | A | IFR | TPSK-LSPA1-T-PE-00252 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-29 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2406 | OL1-2G30-2406 | OL1-2G30-2406 | PROCESS EQUIPMENT DATASHEET - 10-E-2405 - GAS DRYER FEED CHILLER | A | IFR | TPSK-LSPA1-T-PE-00239 | 2018-10-30 | R1-No comments | 2018-11-14 | 2018-11-12 | 2018-10-26 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2412 | OL1-2G30-2412 | OL1-2G30-2412 | PROCESS EQUIPMENT DATASHEET - 10-E-2412 - HP DEPROPANIZER FEED CHILLER | A | IFR | TPSK-LSPA1-T-PE-00239 | 2018-10-30 | R1-No comments | 2018-11-14 | 2018-11-12 | 2018-10-26 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2413 | OL1-2G30-2413 | OL1-2G30-2413 | PROCESS EQUIPMENT DATASHEET - 10-E-2413 - HP DEPROP FEED - OVERHEAD EXCHANGER | A | IFR | TPSK-LSPA1-T-PE-00250 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-30 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0900-2416 | OL1-2G30-2416 | OL1-2G30-2416 | PROCESS EQUIPMENT DATASHEET - 10-P-2415 A-B - CG LIQUID DRYER FEED PUMPS | A | IFR | TPSK-LSPA1-T-PE-00285 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0800-2420 | OL1-2G30-2420 | OL1-2G30-2420 | PROCESS EQUIPMENT DATASHEET - 10-D-2420 A-B - CG LIQUID DRYER | A | IFR | TPSK-LSPA1-T-PE-00301 | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-08 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0800-2438 | OL1-2G30-2438 | OL1-2G30-2438 | PROCESS EQUIPMENT DATASHEET - 10-D-2440 - HP DEPROPANIZER REFLUX DRUM | A | IFR | TPSK-LSPA1-T-PE-00264 | 2018-11-01 | Transmitted |  | 2018-11-15 | 2018-10-31 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2439 | OL1-2G30-2439 | OL1-2G30-2439 | PROCESS EQUIPMENT DATASHEET - 10-E-2440 - HP DEPROPANIZER CONDENSER | A | IFR | TPSK-LSPA1-T-PE-00250 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-30 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0500-2440 | OL1-2G30-2440 | OL1-2G30-2440 | PROCESS EQUIPMENT DATA SHEET - 10-T-2440 - HP DEPROPANIZER | A | IFA | TPSK-LSPA1-T-PE-00053 | 2018-09-14 | A3-Approved with comments, re-submit for review. | 2018-10-03 | 2018-09-28 | 2018-09-13 | IFA | H | HOC | PE | 1
036909C-1024-PDS-0500-2440 | OL1-2G30-2440 | OL1-2G30-2440 | PROCESS EQUIPMENT DATASHEET - 10-T-2440 - HP DEPROPANIZER | B | IFD | TPSK-LSPA1-T-PE-00167 | 2018-10-12 | Transmitted |  |  | 2018-10-11 | IFI | C | HOC | PE | 3
036909C-1024-PDS-0600-2441 | OL1-2G30-2441 | OL1-2G30-2441 | PROCESS EQUIPMENT DATASHEET - 10-E-2441 - HP DEPROP REFLUX CHILLER NO 2 | A | IFR | TPSK-LSPA1-T-PE-00250 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-30 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2442 | OL1-2G30-2442 | OL1-2G30-2442 | PROCESS EQUIPMENT DATASHEET - 10-E-2442 - HP DEPROP REFLUX CHILLER NO 1 | A | IFR | TPSK-LSPA1-T-PE-00250 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-30 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2445 | OL1-2G30-2445 | OL1-2G30-2445 | PROCESS EQUIPMENT DATASHEET - 10-E-2445 A-B - HP DEPROPANIZER REBOILERS | A | IFR | TPSK-LSPA1-T-PE-00267 | 2018-11-01 | Transmitted |  | 2018-11-15 | 2018-11-01 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2446 | OL1-2G30-2446 | OL1-2G30-2446 | PROCESS EQUIPMENT DATASHEET - 10-E-2446 - LP DEPROPANIZER FEED COOLER | A | IFR | TPSK-LSPA1-T-PE-00250 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-30 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0500-2450 | OL1-2G30-2450 | OL1-2G30-2450 | PROCESS EQUIPMENT DATA SHEET - 10-T-2450 - LP DEPROPANIZER | A | IFA | TPSK-LSPA1-T-PE-00053 | 2018-09-14 | A3-Approved with comments, re-submit for review. | 2018-10-03 | 2018-09-28 | 2018-09-13 | IFA | H | HOC | PE | 1
036909C-1024-PDS-0500-2450 | OL1-2G30-2450 | OL1-2G30-2450 | PROCESS EQUIPMENT DATASHEET - 10-T-2450 - LP DEPROPANIZER | B | IFD | TPSK-LSPA1-T-PE-00167 | 2018-10-12 | Transmitted |  |  | 2018-10-11 | IFI | C | HOC | PE | 3
036909C-1024-PDS-0600-2451 | OL1-2G30-2451 | OL1-2G30-2451 | PROCESS EQUIPMENT DATASHEET - 10-E-2450 - LP DEPROPANIZER CONDENSER | A | IFR | TPSK-LSPA1-T-PE-00259 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-31 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0800-2452 | OL1-2G30-2452 | OL1-2G30-2452 | PROCESS EQUIPMENT DATASHEET - 10-D-2450 - LP DEPROPANIZER REFLUX DRUM | A | IFR | TPSK-LSPA1-T-PE-00264 | 2018-11-01 | Transmitted |  | 2018-11-15 | 2018-10-31 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0900-2453 | OL1-2G30-2453 | OL1-2G30-2453 | PROCESS EQUIPMENT DATASHEET - 10-P-2450 A-B - LP DEPROPANIZER REFLUX-PRODUCT PUMP | A | IFR | TPSK-LSPA1-T-PE-00285 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2455 | OL1-2G30-2455 | OL1-2G30-2455 | PROCESS EQUIPMENT DATASHEET - 10-E-2455 A-B - LP DEPROPANIZER REBOILERS | A | IFR | TPSK-LSPA1-T-PE-00228 | 2018-10-25 | R1-No comments | 2018-11-14 | 2018-11-08 | 2018-10-24 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0600-2461 | OL1-2G30-2461 | OL1-2G30-2461 | PROCESS EQUIPMENT DATASHEET - 10-E-2460 - C2 HYDROG FEED COOLER | A | IFR | TPSK-LSPA1-T-PE-00250 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-30 | IFR | C | HOC | PE | 2
036909C-1024-PDS-0400-2470 | OL1-2G30-2470 | OL1-2G30-2470 | PROCESS EQUIPMENT DATASHEET - 10-R-2470 A-C - C2 HYDROG REACTOR | A | IFR | TPSK-LSPA1-T-PE-00299 | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-08 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0600-2500 | OL1-2G30-2500 | OL1-2G30-2500 | PROCESS EQUIPMENT DATA SHEET - 10-E-2500 - PROPYLENE REFRIG SUBCOOLER | A | IFA | TPSK-LSPA1-T-PE-00039 | 2018-09-11 | A2-Approved with comments, re-submit is not required. | 2018-09-28 | 2018-09-25 | 2018-09-10 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2500 | OL1-2G30-2500 | OL1-2G30-2500 | PROCESS EQUIPMENT DATASHEET - 10-E-2500 - PROPYLENE REFRIG SUBCOOLER | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0600-2502 | OL1-2G30-2502 | OL1-2G30-2502 | PROCESS EQUIPMENT DATA SHEET - 10-E-2502 - DEMETH PREFRAC FEED COOLER NO 1 | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-07 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2502 | OL1-2G30-2502 | OL1-2G30-2502 | PROCESS EQUIPMENT DATASHEET - 10-E-2502 - DEMETH PREFRAC FEED COOLER NO 1 | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1025-PDS-0600-2503 | OL1-2G30-2503 | OL1-2G30-2503 | PROCESS EQUIPMENT DATA SHEET - 10-E-2504 - DEMETH PREFRAC FEED COOLER NO 2 | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-07 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2503 | OL1-2G30-2503 | OL1-2G30-2503 | PROCESS EQUIPMENT DATASHEET - 10-E-2504 - DEMETH PREFRAC FEED COOLER NO 2 | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1025-PDS-0800-2504 | OL1-2G30-2504 | OL1-2G30-2504 | PROCESS EQUIPMENT DATASHEET - 10-D-2504 - DEMETH PREFRAC FEED SEPARATOR NO 1 | A | IFR | TPSK-LSPA1-T-PE-00217 | 2018-10-24 | R1-No comments | 2018-11-07 | 2018-11-07 | 2018-10-23 | IFR | H | HOC | PE | 2
036909C-1025-PDS-0800-2504 | OL1-2G30-2504 | OL1-2G30-2504 | PROCESS EQUIPMENT DATASHEET - 10-D-2504 - DEMETH PREFRAC FEED SEPARATOR NO 1 | B | IFD | TPSK-LSPA1-T-PE-00303 | 2018-11-09 | Transmitted |  |  | 2018-11-08 | IFI | C | HOC | PE | 2
036909C-1025-PDS-0600-2505 | OL1-2G30-2505 | OL1-2G30-2505 | PROCESS EQUIPMENT DATA SHEET - 10-E-2506 & 2508 - DEMETH PREFRAC FEED COOLER NO 3 & NO 4 | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2505 | OL1-2G30-2505 | OL1-2G30-2505 | PROCESS EQUIPMENT DATASHEET - 10-E2506 AND 10-E2508 - DEMETH PREFRAC FEED COOLER NO 3 AND NO 4 | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0800-2506 | OL1-2G30-2506 | OL1-2G30-2506 | PROCESS EQUIPMENT DATASHEET - 10-D-2506 - DEMETH PREFRAC FEED SEPARATOR NO 2 | A | IFR | TPSK-LSPA1-T-PE-00217 | 2018-10-24 | R1-No comments | 2018-11-07 | 2018-11-07 | 2018-10-23 | IFR | H | HOC | PE | 2
036909C-1025-PDS-0800-2506 | OL1-2G30-2506 | OL1-2G30-2506 | PROCESS EQUIPMENT DATASHEET - 10-D-2506 - DEMETH PREFRAC FEED SEPARATOR NO 2 | B | IFD | TPSK-LSPA1-T-PE-00303 | 2018-11-09 | Transmitted |  |  | 2018-11-08 | IFI | C | HOC | PE | 2
036909C-1025-PDS-0800-2508 | OL1-2G30-2508 | OL1-2G30-2508 | PROCESS EQUIPMENT DATASHEET - 10-D-2508 - DEMETH PREFRAC FEED SEPARATOR NO 3 | A | IFR | TPSK-LSPA1-T-PE-00217 | 2018-10-24 | R1-No comments | 2018-11-07 | 2018-11-07 | 2018-10-23 | IFR | H | HOC | PE | 2
036909C-1025-PDS-0800-2508 | OL1-2G30-2508 | OL1-2G30-2508 | PROCESS EQUIPMENT DATASHEET - 10-D-2508 - DEMETH PREFRAC FEED SEPARATOR NO 3 | B | IFD | TPSK-LSPA1-T-PE-00303 | 2018-11-09 | Transmitted |  |  | 2018-11-08 | IFI | C | HOC | PE | 2
036909C-1025-PDS-0500-2510 | OL1-2G30-2510 | OL1-2G30-2510 | PROCESS EQUIPMENT DATASHEET - 10-T-2510 AND 10-D-2510 - DEMETHANIZER PREFRACTIONATOR & REFLUX DRUM | A | IFA | TPSK-LSPA1-T-PE-00092 | 2018-09-26 | A3-Approved with comments, re-submit for review. | 2018-10-24 | 2018-10-09 | 2018-09-26 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0500-2510 | OL1-2G30-2510 | OL1-2G30-2510 | PROCESS EQUIPMENT DATASHEET - 10-T-2510 - 10-D-2510 - DEMETHANIZER PREFRACTIONATOR & REFLUX DRUM | B | IFD | TPSK-LSPA1-T-PE-00306 | 2018-11-09 | Transmitted |  |  | 2018-11-09 | IFI | C | HOC | PE | 1
036909C-1025-PDS-0600-2511 | OL1-2G30-2511 | OL1-2G30-2511 | PROCESS EQUIPMENT DATA SHEET - 10-E-2510 - DEMETH PREFRAC CONDENSER | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2511 | OL1-2G30-2511 | OL1-2G30-2511 | PROCESS EQUIPMENT DATASHEET - 10-E-2510 - DEMETH PREFRAC CONDENSER | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0600-2515 | OL1-2G30-2515 | OL1-2G30-2515 | PROCESS EQUIPMENT DATASHEET - 10-E-2515 - DEMETH PREFRAC REBOILER | A | IFR | TPSK-LSPA1-T-PE-00216 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0500-2520 | OL1-2G30-2520 | OL1-2G30-2520 | PROCESS EQUIPMENT DATASHEET - 10-T-2520 AND 10-D-2520 - RESIDUE GAS RECTIFIER & REFLUX DRUM | A | IFR | TPSK-LSPA1-T-PE-00172 | 2018-10-15 | R2-Comments as noted | 2018-11-05 | 2018-10-29 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0600-2521 | OL1-2G30-2521 | OL1-2G30-2521 | PROCESS EQUIPMENT DATA SHEET - 10-E-2520 - RECTIFIER CONDENSER | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2521 | OL1-2G30-2521 | OL1-2G30-2521 | PROCESS EQUIPMENT DATASHEET - 10-E-2520 - RECTIFIER CONDENSER | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0800-2525 | OL1-2G30-2525 | OL1-2G30-2525 | PROCESS EQUIPMENT DATASHEET - 10-D-2525 - HYDROGEN DRUM | A | IFR | TPSK-LSPA1-T-PE-00218 | 2018-10-24 | R1-No comments | 2018-11-09 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0600-2526 | OL1-2G30-2526 | OL1-2G30-2526 | PROCESS EQUIPMENT DATA SHEET - 10-E-2525 - HYDROGEN CORE EXCHANGER | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2526 | OL1-2G30-2526 | OL1-2G30-2526 | PROCESS EQUIPMENT DATASHEET - 10-E-2525 - HYDROGEN CORE EXCHANGER | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0600-2531 | OL1-2G30-2531 | OL1-2G30-2531 | PROCESS EQUIPMENT DATA SHEET - 10-E-2530 - DEMETH FEED COOLER | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2531 | OL1-2G30-2531 | OL1-2G30-2531 | PROCESS EQUIPMENT DATASHEET - 10-E-2530 - DEMETH FEED COOLER | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0500-2540 | OL1-2G30-2540 | OL1-2G30-2540 | PROCESS EQUIPMENT DATASHEET - 10-T-2540 AND 10-D-2540 - DEMETHANIZER AND REFLUX DRUM | A | IFA | TPSK-LSPA1-T-PE-00073 | 2018-09-24 | A3-Approved with comments, re-submit for review. | 2018-10-24 | 2018-10-08 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0500-2540 | OL1-2G30-2540 | OL1-2G30-2540 | PROCESS EQUIPMENT DATASHEET - 10-T-2540 - 10-D-2540 - DEMETHANIZER & REFLUX DRUM | B | IFD | TPSK-LSPA1-T-PE-00306 | 2018-11-09 | Transmitted |  |  | 2018-11-09 | IFI | C | HOC | PE | 1
036909C-1025-PDS-0600-2541 | OL1-2G30-2541 | OL1-2G30-2541 | PROCESS EQUIPMENT DATA SHEET - 10-E-2540 - DEMETHANIZER CONDENSER | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2541 | OL1-2G30-2541 | OL1-2G30-2541 | PROCESS EQUIPMENT DATASHEET - 10-E-2540 - DEMETHANIZER CONDENSER | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0600-2545 | OL1-2G30-2545 | OL1-2G30-2545 | PROCESS EQUIPMENT DATASHEET - 10-E-2545 - DEMETHANIZER REBOILER | A | IFR | TPSK-LSPA1-T-PE-00216 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0600-2546 | OL1-2G30-2546 | OL1-2G30-2546 | PROCESS EQUIPMENT DATASHEET - 10-E-2546 - DEMETHANIZER BOTTOMS COOLER | A | IFR | TPSK-LSPA1-T-PE-00216 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0600-2548 | OL1-2G30-2548 | OL1-2G30-2548 | PROCESS EQUIPMENT DATASHEET - 10-E-2548 - DEMETHANIZER BOTTOMS VAPORIZER | A | IFR | TPSK-LSPA1-T-PE-00216 | 2018-10-24 | R2-Comments as noted | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1025-PDS-1000-2550 | OL1-2G30-2550 | OL1-2G30-2550 | PROCESS EQUIPMENT DATA SHEET - 10-C-TX-2550 - RESIDUE GAS EXPANDER - RECOMPRESSOR | A | IFA | TPSK-LSPA1-T-PE-00031 | 2018-08-29 | A3-Approved with comments, re-submit for review. | 2018-09-28 |  | 2018-08-29 | IFA | H | HOC | PE | 1
036909C-1025-PDS-1000-2550 | OL1-2G30-2550 | OL1-2G30-2550 | PROCESS EQUIPMENT DATASHEET - 10-TX-2550 - 10-C-2550 - RESIDUE GAS EXPANDER - RECOMPRESSOR | B | IFD | TPSK-LSPA1-T-PE-00114 | 2018-09-28 | R1-No comments | 2018-10-24 |  | 2018-09-28 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0800-2551 | OL1-2G30-2551 | OL1-2G30-2551 | PROCESS EQUIPMENT DATASHEET - 10-D-2550 - EXPANDER SUCTION DRUM | A | IFR | TPSK-LSPA1-T-PE-00218 | 2018-10-24 | R2-Comments as noted | 2018-11-09 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0800-2555 | OL1-2G30-2555 | OL1-2G30-2555 | PROCESS EQUIPMENT DATASHEET - 10-D-2555 - EXPANDER DISCHARGE DRUM | A | IFR | TPSK-LSPA1-T-PE-00218 | 2018-10-24 | R1-No comments | 2018-11-09 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1025-PDS-4100-2560 | OL1-2G30-2560 | OL1-2G30-2560 | PROCESS EQUIPMENT DATASHEET - 10-PK-2560 - PSA UNIT | A | IFR | TPSK-LSPA1-T-PE-00190 | 2018-10-17 | R2-Comments as noted | 2018-11-05 | 2018-10-31 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0500-2570 | OL1-2G30-2570 | OL1-2G30-2570 | PROCESS EQUIPMENT DATASHEET - 10-T-2570 - DEETHANIZER | A | IFR | TPSK-LSPA1-T-PE-00191 | 2018-10-17 | R2-Comments as noted | 2018-11-05 | 2018-10-31 | 2018-10-17 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0600-2571 | OL1-2G30-2571 | OL1-2G30-2571 | PROCESS EQUIPMENT DATA SHEET - 10-E-2570 DEETHANIZER CONDENSER | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-24 | 2018-09-07 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2571 | OL1-2G30-2571 | OL1-2G30-2571 | PROCESS EQUIPMENT DATASHEET - 10-E-2570 - DEETHANIZER CONDENSER | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1025-PDS-0800-2572 | OL1-2G30-2572 | OL1-2G30-2572 | PROCESS EQUIPMENT DATASHEET - 10-D-2570 - DEETHANIZER REFLUX DRUM | A | IFR | TPSK-LSPA1-T-PE-00227 | 2018-10-25 | Transmitted |  | 2018-11-08 | 2018-10-24 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0600-2575 | OL1-2G30-2575 | OL1-2G30-2575 | PROCESS EQUIPMENT DATASHEET - 10-E-2575 - DEETHANIZER REBOILER | A | IFA | TPSK-LSPA1-T-PE-00094 | 2018-09-26 | A2-Approved with comments, re-submit is not required. | 2018-10-12 | 2018-10-10 | 2018-09-26 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2575 | OL1-2G30-2575 | OL1-2G30-2575 | PROCESS EQUIPMENT DATASHEET - 10-E-2575 - DEETHANIZER REBOILER | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1025-PDS-0600-2576 | OL1-2G30-2576 | OL1-2G30-2576 | PROCESS EQUIPMENT DATASHEET - 10-E-2576 - DEETHANIZER BOTTOMS COOLER | A | IFA | TPSK-LSPA1-T-PE-00094 | 2018-09-26 | A2-Approved with comments, re-submit is not required. | 2018-10-12 | 2018-10-10 | 2018-09-26 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2576 | OL1-2G30-2576 | OL1-2G30-2576 | PROCESS EQUIPMENT DATASHEET - 10-E-2576 - DEETHANIZER BOTTOMS COOLER | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1025-PDS-0500-2580 | OL1-2G30-2580 | OL1-2G30-2580 | PROCESS EQUIPMENT DATASHEET - 10-T-2580 - C2 TOWER | A | IFR | TPSK-LSPA1-T-PE-00162 | 2018-10-12 | R2-Comments as noted | 2018-10-31 | 2018-10-26 | 2018-10-11 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0600-2582 | OL1-2G30-2582 | OL1-2G30-2582 | PROCESS EQUIPMENT DATASHEET - 10-E-2582 - C2 TOWER REFLUX COOLER | A | IFR | TPSK-LSPA1-T-PE-00265 | 2018-11-01 | Transmitted |  | 2018-11-15 | 2018-11-01 | IFR | C | HOC | PE | 2
036909C-1025-PDS-0600-2585 | OL1-2G30-2585 | OL1-2G30-2585 | PROCESS EQUIPMENT DATA SHEET - 10-E-2585 - C2 TOWER BOTTOMS REBOILER | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2585 | OL1-2G30-2585 | OL1-2G30-2585 | PROCESS EQUIPMENT DATASHEET - 10-E-2585 - C2 TOWER BOTTOMS REBOILER | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0600-2587 | OL1-2G30-2587 | OL1-2G30-2587 | PROCESS EQUIPMENT DATA SHEET - 10-E-2587 - C2 TOWER SIDE REBOILER | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A1-Approved without comments | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1025-PDS-0600-2587 | OL1-2G30-2587 | OL1-2G30-2587 | PROCESS EQUIPMENT DATASHEET - 10-E-2587 - C2 TOWER SIDE REBOILER | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1025-PDS-0600-2591 | OL1-2G30-2591 | OL1-2G30-2591 | PROCESS EQUIPMENT DATASHEET - 10-E-2856 - ETHYLENE PRODUCT SUBCOOLER | A | IFR | TPSK-LSPA1-T-PE-00216 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1026-PDS-0500-2630 | OL1-2G30-2630 | OL1-2G30-2630 | PROCESS EQUIPMENT DATA SHEET - 10-T-2630 - SECONDARY DEETHANIZER | A | IFA | TPSK-LSPA1-T-PE-00053 | 2018-09-14 | A3-Approved with comments, re-submit for review. | 2018-10-03 | 2018-09-28 | 2018-09-13 | IFA | H | HOC | PE | 1
036909C-1026-PDS-0500-2630 | OL1-2G30-2630 | OL1-2G30-2630 | PROCESS EQUIPMENT DATASHEET - 10-T-2630 - SECONDARY DEETHANIZER | B | IFD | TPSK-LSPA1-T-PE-00169 | 2018-10-12 | Transmitted |  |  | 2018-10-12 | IFI | C | HOC | PE | 3
036909C-1026-PDS-0600-2631 | OL1-2G30-2631 | OL1-2G30-2631 | PROCESS EQUIPMENT DATASHEET - 10-E-2630 - SECONDARY DEETH CONDENSER | A | IFA | TPSK-LSPA1-T-PE-00074 | 2018-09-24 | A2-Approved with comments, re-submit is not required. | 2018-10-12 | 2018-10-08 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1026-PDS-0600-2631 | OL1-2G30-2631 | OL1-2G30-2631 | PROCESS EQUIPMENT DATASHEET - 10-E-2630 - SECONDARY DEETH CONDENSER | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1026-PDS-0800-2632 | OL1-2G30-2632 | OL1-2G30-2632 | PROCESS EQUIPMENT DATASHEET - 10-D-2630 - SECONDARY DEETH REFLUX DRUM | A | IFR | TPSK-LSPA1-T-PE-00287 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-07 | IFR | C | HOC | PE | 2
036909C-1026-PDS-0900-2633 | OL1-2G30-2633 | OL1-2G30-2633 | PROCESS EQUIPMENT DATASHEET - 10-P-2630 A-B - SECONDARY DEETH REFLUX PUMPS | A | IFR | TPSK-LSPA1-T-PE-00277 | 2018-11-06 | Transmitted |  | 2018-11-20 | 2018-11-05 | IFR | C | HOC | PE | 2
036909C-1026-PDS-0600-2635 | OL1-2G30-2635 | OL1-2G30-2635 | PROCESS EQUIPMENT DATASHEET - 10-E-2635 - SECONDARY DEETH REBOILER | A | IFA | TPSK-LSPA1-T-PE-00074 | 2018-09-24 | A2-Approved with comments, re-submit is not required. | 2018-10-12 | 2018-10-08 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1026-PDS-0600-2635 | OL1-2G30-2635 | OL1-2G30-2635 | PROCESS EQUIPMENT DATASHEET - 10-E-2635 - SECONDARY DEETH REBOILER | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1026-PDS-0600-2636 | OL1-2G30-2636 | OL1-2G30-2636 | PROCESS EQUIPMENT DATASHEET - 10-E-2636 - SECONDARY DEETH BOTTOMS COOLER | A | IFA | TPSK-LSPA1-T-PE-00074 | 2018-09-24 | A2-Approved with comments, re-submit is not required. | 2018-10-12 | 2018-10-08 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1026-PDS-0600-2636 | OL1-2G30-2636 | OL1-2G30-2636 | PROCESS EQUIPMENT DATASHEET - 10-E-2636 - SECONDARY DEETH BOTTOMS COOLER | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1026-PDS-0500-2640 | OL1-2G30-2640 | OL1-2G30-2640 | PROCESS EQUIPMENT DATASHEET - 10-T-2640 - C3 TOWER | A | IFR | TPSK-LSPA1-T-PE-00201 | 2018-10-22 | R2-Comments as noted | 2018-11-05 | 2018-11-05 | 2018-10-18 | IFR | C | HOC | PE | 2
036909C-1026-PDS-0600-2645 | OL1-2G30-2645 | OL1-2G30-2645 | PROCESS EQUIPMENT DATA SHEET - 10-E-2645 - C3 TOWER REBOILERS | A | IFA | TPSK-LSPA1-T-PE-00041 | 2018-09-12 | A1-Approved without comments | 2018-10-01 | 2018-09-26 | 2018-09-11 | IFA | H | HOC | PE | 1
036909C-1026-PDS-0600-2645 | OL1-2G30-2645 | OL1-2G30-2645 | PROCESS EQUIPMENT DATASHEET - 10-E-2645 A-B - C3 TOWER REBOILERS | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1026-PDS-0900-2646 | OL1-2G30-2646 | OL1-2G30-2646 | PROCESS EQUIPMENT DATASHEET - 10-P-2646 A-B - PROPANE RECYCLE PUMPS | A | IFR | TPSK-LSPA1-T-PE-00277 | 2018-11-06 | Transmitted |  | 2018-11-20 | 2018-11-05 | IFR | C | HOC | PE | 2
036909C-1026-PDS-0900-2647 | OL1-2G30-2647 | OL1-2G30-2647 | PROCESS EQUIPMENT DATASHEET - 10-P-2647 - HP PROPYLENE - OFF SPEC PUMPS | A | IFR | TPSK-LSPA1-T-PE-00302 | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-08 | IFR | C | HOC | PE | 2
036909C-1026-PDS-0500-2660 | OL1-2G30-2660 | OL1-2G30-2660 | PROCESS EQUIPMENT DATA SHEET - 10-T-2660 - DEBUTANIZER | A | IFA | TPSK-LSPA1-T-PE-00053 | 2018-09-14 | A3-Approved with comments, re-submit for review. | 2018-10-03 | 2018-09-28 | 2018-09-13 | IFA | H | HOC | PE | 1
036909C-1026-PDS-0500-2660 | OL1-2G30-2660 | OL1-2G30-2660 | PROCESS EQUIPMENT DATASHEET - 10-T-2660 - DEBUTANIZER | B | IFD | TPSK-LSPA1-T-PE-00169 | 2018-10-12 | Transmitted |  |  | 2018-10-12 | IFI | C | HOC | PE | 3
036909C-1026-PDS-0600-2661 | OL1-2G30-2661 | OL1-2G30-2661 | PROCESS EQUIPMENT DATASHEET - 10-E-2660 - DEBUTANIZER CONDENSER | A | IFA | TPSK-LSPA1-T-PE-00094 | 2018-09-26 | A2-Approved with comments, re-submit is not required. | 2018-10-12 | 2018-10-10 | 2018-09-26 | IFA | H | HOC | PE | 1
036909C-1026-PDS-0600-2661 | OL1-2G30-2661 | OL1-2G30-2661 | PROCESS EQUIPMENT DATASHEET - 10-E-2660 - DEBUTANIZER CONDENSER | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1026-PDS-0800-2662 | OL1-2G30-2662 | OL1-2G30-2662 | PROCESS EQUIPMENT DATASHEET - 10-D-2660 - DEBUTANIZER REFLUX DRUM | A | IFR | TPSK-LSPA1-T-PE-00287 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-11-07 | IFR | C | HOC | PE | 2
036909C-1026-PDS-0600-2665 | OL1-2G30-2665 | OL1-2G30-2665 | PROCESS EQUIPMENT DATASHEET - 10-E-2665 A-B - DEBUTANIZER REBOILERS | A | IFA | TPSK-LSPA1-T-PE-00101 | 2018-09-27 | A1-Approved without comments | 2018-10-12 | 2018-10-11 | 2018-09-27 | IFA | H | HOC | PE | 1
036909C-1026-PDS-0600-2665 | OL1-2G30-2665 | OL1-2G30-2665 | PROCESS EQUIPMENT DATASHEET - 10-E-2665 A-B - DEBUTANIZER REBOILERS | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1026-PDS-0600-2666 | OL1-2G30-2666 | OL1-2G30-2666 | PROCESS EQUIPMENT DATASHEET - 10-E-2666 - DEBUTANIZER BOTTOMS COOLER | A | IFA | TPSK-LSPA1-T-PE-00112 | 2018-09-28 | A3-Approved with comments, re-submit for review. | 2018-10-12 | 2018-10-12 | 2018-09-27 | IFA | C | HOC | PE | 1
036909C-1028-PDS-1000-2800 | OL1-2G30-2800 | OL1-2G30-2800 | PROCESS EQUIPMENT DATA SHEET - 10-C-2800 - PROPYLENE REFRIG COMPRESSOR | A | IFA | TPSK-LSPA1-T-PE-00025 | 2018-08-22 | A3-Approved with comments, re-submit for review. | 2018-09-11 | 2018-09-05 | 2018-08-22 | IFA | H | HOC | PE | 1
036909C-1028-PDS-1000-2800 | OL1-2G30-2800 | OL1-2G30-2800 | PROCESS EQUIPMENT DATA SHEET - 10-C-2800 - PROPYLENE REFRIG COMPRESSOR | B | IFD | TPSK-LSPA1-T-PE-00055 | 2018-09-17 | Transmitted |  |  | 2018-09-14 | IFI | C | HOC | PE | 3
036909C-1028-PDS-0900-2801 | OL1-2G30-2801 | OL1-2G30-2801 | PROCESS EQUIPMENT DATASHEET - 10-P-2805 A-B - PROPYLENE PRODUCT PUMPS | A | IFR | TPSK-LSPA1-T-PE-00277 | 2018-11-06 | Transmitted |  | 2018-11-20 | 2018-11-05 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2805 | OL1-2G30-2805 | OL1-2G30-2805 | PROCESS EQUIPMENT DATASHEET - 10-D-2805 - C3R SURGE DRUM | A | IFR | TPSK-LSPA1-T-PE-00218 | 2018-10-24 | R1-No comments | 2018-11-09 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0600-2806 | OL1-2G30-2806 | OL1-2G30-2806 | PROCESS EQUIPMENT DATASHEET - 10-E-2805 - C3 REFRIG CONDENSERS | A | IFA | TPSK-LSPA1-T-PE-00113 | 2018-09-28 | A3-Approved with comments, re-submit for review. | 2018-10-12 | 2018-10-12 | 2018-09-28 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2806 | OL1-2G30-2806 | OL1-2G30-2806 | PROCESS EQUIPMENT DATASHEET - 10-E-2805 A-B - C3 REFRIG CONDENSERS | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1028-PDS-0600-2807 | OL1-2G30-2807 | OL1-2G30-2807 | PROCESS EQUIPMENT DATASHEET - 10-E-2807 - C3 CHILLER NO 1 | A | IFA | TPSK-LSPA1-T-PE-00113 | 2018-09-28 | A1-Approved without comments | 2018-10-12 | 2018-10-12 | 2018-09-28 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2807 | OL1-2G30-2807 | OL1-2G30-2807 | PROCESS EQUIPMENT DATASHEET - 10-E-2807 - C3 CHILLER NO 1 | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1028-PDS-0600-2809 | OL1-2G30-2809 | OL1-2G30-2809 | PROCESS EQUIPMENT DATASHEET - 10-E-2809 - C3 CHILLER NO 2 | A | IFA | TPSK-LSPA1-T-PE-00113 | 2018-09-28 | A1-Approved without comments | 2018-10-12 | 2018-10-12 | 2018-09-28 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2809 | OL1-2G30-2809 | OL1-2G30-2809 | PROCESS EQUIPMENT DATASHEET - 10-E-2809 - C3 CHILLER NO 2 | B | IFD | TPSK-LSPA1-T-PE-00273 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1028-PDS-0800-2810 | OL1-2G30-2810 | OL1-2G30-2810 | PROCESS EQUIPMENT DATASHEET - 10-D-2810 - C3R 1ST STAGE SUCTION DRUM | A | IFR | TPSK-LSPA1-T-PE-00144 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-08 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2820 | OL1-2G30-2820 | OL1-2G30-2820 | PROCESS EQUIPMENT DATASHEET - 10-D-2820 - C3R 2ND STAGE SUCTION DRUM | A | IFR | TPSK-LSPA1-T-PE-00144 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-08 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2830 | OL1-2G30-2830 | OL1-2G30-2830 | PROCESS EQUIPMENT DATASHEET - 10-D-2830 - C3R 3RD STAGE SUCTION DRUM | A | IFR | TPSK-LSPA1-T-PE-00144 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-08 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2840 | OL1-2G30-2840 | OL1-2G30-2840 | PROCESS EQUIPMENT DATASHEET - 10-D-2840 - C3R 4TH STAGE SUCTION DRUM | A | IFR | TPSK-LSPA1-T-PE-00144 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-08 | IFR | C | HOC | PE | 2
036909C-1028-PDS-1000-2850 | OL1-2G30-2850 | OL1-2G30-2850 | PROCESS EQUIPMENT DATA SHEET - 10-C-2850 - ETHYLENE REFRIG COMPRESSOR | A | IFA | TPSK-LSPA1-T-PE-00025 | 2018-08-22 | A3-Approved with comments, re-submit for review. | 2018-09-11 | 2018-09-05 | 2018-08-22 | IFA | H | HOC | PE | 1
036909C-1028-PDS-1000-2850 | OL1-2G30-2850 | OL1-2G30-2850 | PROCESS EQUIPMENT DATA SHEET - 10-C-2850 - ETHYLENE REFRIG COMPRESSOR | B | IFD | TPSK-LSPA1-T-PE-00055 | 2018-09-17 | Transmitted |  |  | 2018-09-14 | IFI | C | HOC | PE | 3
036909C-1028-PDS-0600-2852 | OL1-2G30-2852 | OL1-2G30-2852 | PROCESS EQUIPMENT DATASHEET - 10-E-2852 - C2R DESUPERHEATER NO 1 | A | IFA | TPSK-LSPA1-T-PE-00113 | 2018-09-28 | A1-Approved without comments | 2018-10-12 | 2018-10-12 | 2018-09-28 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2852 | OL1-2G30-2852 | OL1-2G30-2852 | PROCESS EQUIPMENT DATASHEET - 10-E-2852 - C2R DESUPERHEATER NO 1 | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1028-PDS-0600-2853 | OL1-2G30-2853 | OL1-2G30-2853 | PROCESS EQUIPMENT DATASHEET - 10-E-2853 - C2R DESUPERHEATER NO 2 | A | IFA | TPSK-LSPA1-T-PE-00113 | 2018-09-28 | A1-Approved without comments | 2018-10-12 | 2018-10-12 | 2018-09-28 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2853 | OL1-2G30-2853 | OL1-2G30-2853 | PROCESS EQUIPMENT DATASHEET - 10-E-2853 - C2R DESUPERHEATER NO 2 | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1028-PDS-0800-2854 | OL1-2G30-2854 | OL1-2G30-2854 | PROCESS EQUIPMENT DATASHEET - 10-D-2855 - C2R SURGE DRUM | A | IFR | TPSK-LSPA1-T-PE-00218 | 2018-10-24 | R1-No comments | 2018-11-09 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0600-2856 | OL1-2G30-2856 | OL1-2G30-2856 | PROCESS EQUIPMENT DATA SHEET - 10-E-2855 - C2R CONDENSER | A | IFA | TPSK-LSPA1-T-PE-00039 | 2018-09-11 | A2-Approved with comments, re-submit is not required. | 2018-09-28 | 2018-09-25 | 2018-09-10 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2856 | OL1-2G30-2856 | OL1-2G30-2856 | PROCESS EQUIPMENT DATASHEET - 10-E-2855 - C2R CONDENSER | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1028-PDS-0600-2857 | OL1-2G30-2857 | OL1-2G30-2857 | PROCESS EQUIPMENT DATA SHEET - 10-E-2857 - HP ETHYLENE PRODUCT VAPORIZER | A | IFA | TPSK-LSPA1-T-PE-00041 | 2018-09-12 | A1-Approved without comments | 2018-10-01 | 2018-09-26 | 2018-09-11 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2857 | OL1-2G30-2857 | OL1-2G30-2857 | PROCESS EQUIPMENT DATASHEET - 10-E-2857 - HP ETHYLENE PRODUCT VAPORIZER | B | IFD | TPSK-LSPA1-T-PE-00272 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFI | C | HOC | PE | 1
036909C-1028-PDS-0600-2858 | OL1-2G30-2858 | OL1-2G30-2858 | PROCESS EQUIPMENT DATASHEET - 10-E-2858 - HP ETHYLENE PRODUCT SUPERHEATER | A | IFR | TPSK-LSPA1-T-PE-00223 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2860 | OL1-2G30-2860 | OL1-2G30-2860 | PROCESS EQUIPMENT DATASHEET - 10-D-2860 - C2R 1ST STAGE SUCTION DRUM | A | IFR | TPSK-LSPA1-T-PE-00208 | 2018-10-23 | Transmitted |  | 2018-11-06 | 2018-10-22 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2870 | OL1-2G30-2870 | OL1-2G30-2870 | PROCESS EQUIPMENT DATASHEET - 10-D-2870 - C2R 2ND STAGE SUCTION DRUM | A | IFR | TPSK-LSPA1-T-PE-00218 | 2018-10-24 | R2-Comments as noted | 2018-11-09 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0800-2880 | OL1-2G30-2880 | OL1-2G30-2880 | PROCESS EQUIPMENT DATASHEET - 10-D-2880 - C2R 3RD STAGE SUCTION DRUM | A | IFR | TPSK-LSPA1-T-PE-00208 | 2018-10-23 | Transmitted |  | 2018-11-06 | 2018-10-22 | IFR | C | HOC | PE | 2
036909C-1028-PDS-0600-2882 | OL1-2G30-2882 | OL1-2G30-2882 | PROCESS EQUIPMENT DATA SHEET - 10-E-2882 - LP ETHYLENE PRODUCT COOLER NO 1 | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2882 | OL1-2G30-2882 | OL1-2G30-2882 | PROCESS EQUIPMENT DATASHEET - 10-E-2882 - LP ETHYLENE PRODUCT COOLER NO 1 | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1028-PDS-0600-2884 | OL1-2G30-2884 | OL1-2G30-2884 | PROCESS EQUIPMENT DATA SHEET - 10-E-2884 - LP ETHYLENE PRODUCT COOLER NO 2 | A | IFA | TPSK-LSPA1-T-PE-00036 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | PE | 1
036909C-1028-PDS-0600-2884 | OL1-2G30-2884 | OL1-2G30-2884 | PROCESS EQUIPMENT DATASHEET - 10-E-2884 - LP ETHYLENE PRODUCT COOLER NO 2 | B | IFD | TPSK-LSPA1-T-PE-00131 | 2018-10-04 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1029-PDS-2600-2914 | OL1-2G30-2914 | OL1-2G30-2914 | PROCESS EQUIPMENT DATASHEET - 10-PK-2914 - NEUTRALIZATION INJECTION PKG | A | IFR | TPSK-LSPA1-T-PE-00181 | 2018-10-16 | Transmitted |  | 2018-10-30 | 2018-10-15 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0800-5100 | OL1-2G30-5100 | OL1-2G30-5100 | PROCESS EQUIPMENT DATA SHEET - 10-D-5100 - DEAERATOR | A | IFR | TPSK-LSPA1-T-PE-00151 | 2018-10-09 | R2-Comments as noted | 2018-11-05 | 2018-10-23 | 2018-10-09 | IFR | H | HOC | PE | 2
036909C-1051-PDS-0800-5100 | OL1-2G30-5100 | OL1-2G30-5100 | PROCESS EQUIPMENT DATASHEET - 10-D-5100 - DEAERATOR | B | IFD | TPSK-LSPA1-T-PE-00151 | 2018-11-14 | Transmitted |  |  | 2018-11-14 | IFI | C | HOC | PE | 2
036909C-1051-PDS-0900-5101 | OL1-2G30-5101 | OL1-2G30-5101 | PROCESS EQUIPMENT DATASHEET - 10-P-5100 A-C - SHP BFW PUMPS | A | IFR | TPSK-LSPA1-T-PE-00141 | 2018-10-08 | R1-No comments | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFR | H | HOC | PE | 2
036909C-1051-PDS-0900-5101 | OL1-2G30-5101 | OL1-2G30-5101 | PROCESS EQUIPMENT DATASHEET - 10-P-5100 A-C - SHP BFW PUMPS | B | IFD | TPSK-LSPA1-T-PE-00251 | 2018-10-31 | Transmitted |  |  | 2018-10-30 | IFI | C | HOC | PE | 2
036909C-1051-PDS-0900-5102 | OL1-2G30-5102 | OL1-2G30-5102 | PROCESS EQUIPMENT DATASHEET - 10-P-5102 A-B - VLP BFW PUMPS | A | IFR | TPSK-LSPA1-T-PE-00141 | 2018-10-08 | R1-No comments | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFR | H | HOC | PE | 2
036909C-1051-PDS-0900-5102 | OL1-2G30-5102 | OL1-2G30-5102 | PROCESS EQUIPMENT DATASHEET - 10-P-5102 A-B - VLP BFW PUMPS | B | IFD | TPSK-LSPA1-T-PE-00251 | 2018-10-31 | Transmitted |  |  | 2018-10-30 | IFI | C | HOC | PE | 2
036909C-1051-PDS-0600-5103 | OL1-2G30-5103 | OL1-2G30-5103 | PROCESS EQUIPMENT DATASHEET - 10-E-5100 - DEAERATOR VENT CONDENSER | A | IFR | TPSK-LSPA1-T-PE-00230 | 2018-10-25 | R2-Comments as noted | 2018-11-14 | 2018-11-08 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0600-5107 | OL1-2G30-5107 | OL1-2G30-5107 | PROCESS EQUIPMENT DATASHEET - 10-E-5112 - SUSPECT COND FLASH DRUM VENT CONDENSER | A | IFR | TPSK-LSPA1-T-PE-00243 | 2018-10-30 | R2-Comments as noted | 2018-11-14 | 2018-11-12 | 2018-10-26 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0600-5108 | OL1-2G30-5108 | OL1-2G30-5108 | PROCESS EQUIPMENT DATASHEET - 10-E-5110 - SUSPECT CONDENSATE COOLER | A | IFR | TPSK-LSPA1-T-PE-00243 | 2018-10-30 | R2-Comments as noted | 2018-11-14 | 2018-11-12 | 2018-10-29 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0900-5109 | OL1-2G30-5109 | OL1-2G30-5109 | PROCESS EQUIPMENT DATASHEET - 10-P-5110 A-B - CONDENSATE PUMPS | A | IFR | TPSK-LSPA1-T-PE-00141 | 2018-10-08 | R1-No comments | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFR | H | HOC | PE | 2
036909C-1051-PDS-0900-5109 | OL1-2G30-5109 | OL1-2G30-5109 | PROCESS EQUIPMENT DATASHEET - 10-P-5110 A-B - CONDENSATE PUMPS | B | IFD | TPSK-LSPA1-T-PE-00251 | 2018-10-31 | Transmitted |  |  | 2018-10-30 | IFI | C | HOC | PE | 2
036909C-1051-PDS-0900-5111 | OL1-2G30-5111 | OL1-2G30-5111 | PROCESS EQUIPMENT DATASHEET - 10-P-5112 A-B - SUSPECT CONDENSATE PUMPS | A | IFR | TPSK-LSPA1-T-PE-00219 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0800-5112 | OL1-2G30-5112 | OL1-2G30-5112 | PROCESS EQUIPMENT DATASHEET - 10-D-5112 - SUSPECT CONDENSATE FLASH DRUM | A | IFR | TPSK-LSPA1-T-PE-00274 | 2018-11-05 | Transmitted |  | 2018-11-21 | 2018-11-05 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0600-5113 | OL1-2G30-5113 | OL1-2G30-5113 | PROCESS EQUIPMENT DATASHEET - 10-E-5113 - FOUL CONDENSATE COOLER | A | IFR | TPSK-LSPA1-T-PE-00230 | 2018-10-25 | R2-Comments as noted | 2018-11-14 | 2018-11-08 | 2018-10-25 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0800-5114 | OL1-2G30-5114 | OL1-2G30-5114 | PROCESS EQUIPMENT DATASHEET - 10-D-5114 - LP CONDENSATE FLASH DRUM | A | IFR | TPSK-LSPA1-T-PE-00274 | 2018-11-05 | Transmitted |  | 2018-11-21 | 2018-11-05 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0900-5121 | OL1-2G30-5121 | OL1-2G30-5121 | PROCESS EQUIPMENT DATASHEET - 10-P-5120 A-B - RAW CONDENSATE PUMPS | A | IFR | TPSK-LSPA1-T-PE-00219 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1051-PDS-0900-5141 | OL1-2G30-5141 | OL1-2G30-5141 | PROCESS EQUIPMENT DATASHEET - 10-P-5140 A-B - INTERMITTENT BLOWDOWN PUMPS | A | IFR | TPSK-LSPA1-T-PE-00219 | 2018-10-24 | R1-No comments | 2018-11-14 | 2018-11-07 | 2018-10-23 | IFR | C | HOC | PE | 2
036909C-1052-PDS-0600-5201 | OL1-2G30-5201 | OL1-2G30-5201 | PROCESS EQUIPMENT DATASHEET - 10-E-5200 - MP ETHYLENE SUPERHEATER | A | IFR | TPSK-LSPA1-T-PE-00275 | 2018-11-05 | Transmitted |  | 2018-11-19 | 2018-11-05 | IFR | C | HOC | PE | 2
036909C-1053-PDS-0300-5350 | OL1-2G30-5350 | OL1-2G30-5350 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5350 - COOLING TOWER | A | IFA | TPSK-LSPA1-T-PE-00082 | 2018-09-25 | A3-Approved with comments, re-submit for review. | 2018-10-13 | 2018-10-09 | 2018-09-24 | IFA | H | HOC | PE | 1
036909C-1053-PDS-0300-5350 | OL1-2G30-5350 | OL1-2G30-5350 | PROCESS EQUIPMENT DATASHEET - 10-PK-5350 - COOLING TOWER | B | IFD | TPSK-LSPA1-T-PE-00226 | 2018-10-24 | A1-Approved without comments | 2018-11-14 |  | 2018-10-24 | IFI | C | HOC | PE | 1
036909C-1053-PDS-0900-5352 | OL1-2G30-5352 | OL1-2G30-5352 | PROCESS EQUIPMENT DATA SHEET - 10-P-5350 A-H - OLEFINS COOLING WATER PUMPS | A | IFA | TPSK-LSPA1-T-PE-00075 | 2018-09-24 | Transmitted |  | 2018-10-08 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1053-PDS-0900-5352 | OL1-2G30-5352 | OL1-2G30-5352 | PROCESS EQUIPMENT DATASHEET - 10-P-5350 A-H - OLEFINS COOLING WATER PUMPS | B | IFD | TPSK-LSPA1-T-PE-00225 | 2018-10-24 | A1-Approved without comments | 2018-11-14 |  | 2018-10-24 | IFI | H | HOC | PE | 1
036909C-1053-PDS-0900-5352 | OL1-2G30-5352 | OL1-2G30-5352 | PROCESS EQUIPMENT DATASHEET - 10-P-5350 A-H - OLEFINS COOLING WATER PUMPS | C | IFD | TPSK-LSPA1-T-PE-00075 | 2018-10-26 | A1-Approved without comments | 2018-11-14 |  | 2018-10-25 | IFI | C | HOC | PE | 1
036909C-1053-PDS-0300-5355 | OL1-2G30-5355 | OL1-2G30-5355 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5355 - SIDE STREAM FILTER PACKAGE | A | IFA | TPSK-LSPA1-T-PE-00082 | 2018-09-25 | A3-Approved with comments, re-submit for review. | 2018-10-13 | 2018-10-09 | 2018-09-24 | IFA | H | HOC | PE | 1
036909C-1053-PDS-0300-5355 | OL1-2G30-5355 | OL1-2G30-5355 | PROCESS EQUIPMENT DATASHEET - 10-PK-5355 - SIDE STREAM FILTER PKG | B | IFD | TPSK-LSPA1-T-PE-00226 | 2018-10-24 | A1-Approved without comments | 2018-11-14 |  | 2018-10-24 | IFI | C | HOC | PE | 1
036909C-1053-PDS-0900-5361 | OL1-2G30-5361 | OL1-2G30-5361 | PROCESS EQUIPMENT DATA SHEET - 10-P-5360 A-C - CTU COOLING WATER PUMPS | A | IFA | TPSK-LSPA1-T-PE-00075 | 2018-09-24 | A3-Approved with comments, re-submit for review. | 2018-10-24 | 2018-10-08 | 2018-09-20 | IFA | H | HOC | PE | 1
036909C-1053-PDS-0900-5361 | OL1-2G30-5361 | OL1-2G30-5361 | PROCESS EQUIPMENT DATASHEET - 10-P-5360 A-C - CTU COOLING WATER PUMPS | B | IFD | TPSK-LSPA1-T-PE-00225 | 2018-10-24 | A1-Approved without comments | 2018-11-14 |  | 2018-10-24 | IFI | H | HOC | PE | 1
036909C-1053-PDS-0900-5361 | OL1-2G30-5361 | OL1-2G30-5361 | PROCESS EQUIPMENT DATASHEET - 10-P-5360 A-C - CTU COOLING WATER PUMPS | C | IFD | TPSK-LSPA1-T-PE-00075 | 2018-10-26 | A1-Approved without comments | 2018-11-14 |  | 2018-10-25 | IFI | C | HOC | PE | 1
036909C-1055-PDS-0800-5500 | OL1-2G30-5500 | OL1-2G30-5500 | PROCESS EQUIPMENT DATASHEET - 10-D-5500 - HOT FLARE DRUM | A | IFR | TPSK-LSPA1-T-PE-00168 | 2018-10-12 | R2-Comments as noted | 2018-11-14 | 2018-10-26 | 2018-10-12 | IFR | C | HOC | PE | 2
036909C-1055-PDS-0800-5550 | OL1-2G30-5550 | OL1-2G30-5550 | PROCESS EQUIPMENT DATASHEET - 10-D-5550 - HP FLARE KNOCK-OUT DRUM | A | IFR | TPSK-LSPA1-T-PE-00142 | 2018-10-08 | R2-Comments as noted | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFR | C | HOC | PE | 2
036909C-1056-PDS-2600-5644 | OL1-2G30-5644 | OL1-2G30-5644 | PROCESS EQUIPMENT DATASHEET - 10-PK-5644 - WASTEWATER CPI - IGF PACKAGE | A | IFR | TPSK-LSPA1-T-PE-00281 | 2018-11-06 | Transmitted |  | 2018-11-20 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1056-PDS-2600-5650 | OL1-2G30-5650 | OL1-2G30-5650 | PROCESS EQUIPMENT DATASHEET - 10-PK-5650 - BIO TREATMENT PKG | A | IFR | TPSK-LSPA1-T-PE-00281 | 2018-11-06 | Transmitted |  | 2018-11-20 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1056-PDS-0200-5653 | OL1-2G30-5653 | OL1-2G30-5653 | PROCESS EQUIPMENT DATASHEET - 10-PK-5653 - WASTEWATER DUAL MEDIA FILTERS PKG | A | IFR | TPSK-LSPA1-T-PE-00282 | 2018-11-06 | Transmitted |  | 2018-11-20 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1056-PDS-2600-5670 | OL1-2G30-5670 | OL1-2G30-5670 | PROCESS EQUIPMENT DATASHEET - 10-PK-5670 - DEWATERING PKG | A | IFR | TPSK-LSPA1-T-PE-00281 | 2018-11-06 | Transmitted |  | 2018-11-20 | 2018-11-06 | IFR | C | HOC | PE | 2
036909C-1000-PFD-0010-0010 | OL1-2G40-0010 | OL1-2G40-0010 | BLOCK FLOW DIAGRAM - OLEFINS UNIT 10 - 00-GENERAL - OVERALL PLANT SCHEME | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1000-PFD-0010-0010 | OL1-2G40-0010 | OL1-2G40-0010 | BLOCK FLOW DIAGRAM - OLEFINS UNIT 10 - 00-GENERAL - OVERALL PLANT SCHEME | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1000-PFD-0010-0001 | OL1-2G41-0001 | OL1-2G41-0001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 00-GENERAL - LEGEND & SYMBOLS | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1000-PFD-0010-0001 | OL1-2G41-0001 | OL1-2G41-0001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 00-GENERAL - LEGEND & SYMBOLS | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1000-PFD-0010-0002 | OL1-2G41-0002 | OL1-2G41-0002 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 00-GENERAL - DRAWING INDEX | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1000-PFD-0010-0002 | OL1-2G41-0002 | OL1-2G41-0002 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 00-GENERAL - DRAWING INDEX | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1010-PFD-0010-1001 | OL1-2G41-1001 | OL1-2G41-1001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 10 - FEED PREPARATION - FEED PREHEAT | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1010-PFD-0010-1001 | OL1-2G41-1001 | OL1-2G41-1001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 10 - FEED PREPARATION - FEED PREHEAT | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1010-PFD-0010-1003 | OL1-2G41-1003 | OL1-2G41-1003 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 10 - FEED PREPARATION - FEEDSTOCK DISTRIBUTION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1010-PFD-0010-1003 | OL1-2G41-1003 | OL1-2G41-1003 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 10 - FEED PREPARATION - FEEDSTOCK DISTRIBUTION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1011-PFD-0010-1101 | OL1-2G41-1101 | OL1-2G41-1101 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 11 - FURNACES - RECYCLE GAS CRACKING FURNACE | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1011-PFD-0010-1101 | OL1-2G41-1101 | OL1-2G41-1101 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 11 - FURNACES - RECYCLE GAS CRACKING FURNACE | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1012-PFD-0010-1201 | OL1-2G41-1201 | OL1-2G41-1201 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 12 - FURNACES - LIQUID CRACKING FURNACES | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1012-PFD-0010-1201 | OL1-2G41-1201 | OL1-2G41-1201 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 12 - FURNACES - LIQUID CRACKING FURNACES | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1019-PFD-0010-1901 | OL1-2G41-1901 | OL1-2G41-1901 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 19 - CRACKING FURNACE UNIT AUX - DECOKE AIR COMPRESSOR | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1019-PFD-0010-1901 | OL1-2G41-1901 | OL1-2G41-1901 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 19 - CRACKING FURNACE UNIT AUX - DECOKE AIR COMPRESSOR | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1019-PFD-0010-1902 | OL1-2G41-1902 | OL1-2G41-1902 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 19 - CRACKING FURNACE UNIT AUX - CHEMICAL STORAGE | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1019-PFD-0010-1902 | OL1-2G41-1902 | OL1-2G41-1902 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 19 - CRACKING FURNACE UNIT AUX - CHEMICAL STORAGE | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1020-PFD-0010-2001 | OL1-2G41-2001 | OL1-2G41-2001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 20 - QUENCH OIL - QUENCH OIL TOWER | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1020-PFD-0010-2001 | OL1-2G41-2001 | OL1-2G41-2001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 20 - QUENCH OIL - QUENCH OIL TOWER | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1020-PFD-0010-2002 | OL1-2G41-2002 | OL1-2G41-2002 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 20 - QUENCH OIL - HEAVY FUEL OIL STRIPPER | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1020-PFD-0010-2002 | OL1-2G41-2002 | OL1-2G41-2002 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 20 - QUENCH OIL - HEAVY FUEL OIL STRIPPER | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1021-PFD-0010-2101 | OL1-2G41-2101 | OL1-2G41-2101 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 21 - QUENCH WATER - DILUTION STEAM - QUENCH WATER TOWER | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1021-PFD-0010-2101 | OL1-2G41-2101 | OL1-2G41-2101 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 21 - QUENCH WATER - DILUTION STEAM - QUENCH WATER TOWER | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1021-PFD-0010-2102 | OL1-2G41-2102 | OL1-2G41-2102 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 21 - QUENCH WATER - DILUTION STEAM - QUENCH WATER CIRCUIT | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1021-PFD-0010-2102 | OL1-2G41-2102 | OL1-2G41-2102 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 21 - QUENCH WATER - DILUTION STEAM - QUENCH WATER CIRCUIT | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1021-PFD-0010-2103 | OL1-2G41-2103 | OL1-2G41-2103 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 21 - QUENCH WATER - DILUTION STEAM - DILUTION STEAM GENERATION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1021-PFD-0010-2103 | OL1-2G41-2103 | OL1-2G41-2103 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 21 - QUENCH WATER - DILUTION STEAM - DILUTION STEAM GENERATION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1022-PFD-0010-2201 | OL1-2G41-2201 | OL1-2G41-2201 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 22 - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1022-PFD-0010-2201 | OL1-2G41-2201 | OL1-2G41-2201 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 22 - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1023-PFD-0010-2301 | OL1-2G41-2301 | OL1-2G41-2301 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 - CAUSTIC & SPENT CAUSTIC TREATMENT - CAUSTIC TOWER | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1023-PFD-0010-2301 | OL1-2G41-2301 | OL1-2G41-2301 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 - CAUSTIC & SPENT CAUSTIC TREATMENT - CAUSTIC TOWER | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1023-PFD-0010-2302 | OL1-2G41-2302 | OL1-2G41-2302 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC HANDLING | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1023-PFD-0010-2302 | OL1-2G41-2302 | OL1-2G41-2302 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC HANDLING | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1023-PFD-0010-2303 | OL1-2G41-2303 | OL1-2G41-2303 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STORAGE | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1023-PFD-0010-2303 | OL1-2G41-2303 | OL1-2G41-2303 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STORAGE | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1023-PFD-0010-2304 | OL1-2G41-2304 | OL1-2G41-2304 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC TREATMENT | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1023-PFD-0010-2304 | OL1-2G41-2304 | OL1-2G41-2304 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC TREATMENT | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1023-PFD-0010-2305 | OL1-2G41-2305 | OL1-2G41-2305 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 - CAUSTIC & SPENT CAUSTIC TREATMENT - WET AIR OXIDATION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1023-PFD-0010-2305 | OL1-2G41-2305 | OL1-2G41-2305 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 - CAUSTIC & SPENT CAUSTIC TREATMENT - WET AIR OXIDATION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1024-PFD-0010-2401 | OL1-2G41-2401 | OL1-2G41-2401 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 - DEHYDRATION - REGEN - DEPROP - C2 HYDROG - CG DEHYDRATION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1024-PFD-0010-2401 | OL1-2G41-2401 | OL1-2G41-2401 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 - DEHYDRATION - REGEN - DEPROP - C2 HYDROG - CG DEHYDRATION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1024-PFD-0010-2402 | OL1-2G41-2402 | OL1-2G41-2402 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 - DEHYDRATION - REGEN - DEPROP - C2 HYDROG - REGENERATION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1024-PFD-0010-2402 | OL1-2G41-2402 | OL1-2G41-2402 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 - DEHYDRATION - REGEN - DEPROP - C2 HYDROG - REGENERATION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1024-PFD-0010-2403 | OL1-2G41-2403 | OL1-2G41-2403 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 - DEHYDRATION - REGEN - DEPROP - C2 HYDROG - HP DEPROPANIZER | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1024-PFD-0010-2403 | OL1-2G41-2403 | OL1-2G41-2403 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 - DEHYDRATION - REGEN - DEPROP - C2 HYDROG - HP DEPROPANIZER | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1024-PFD-0010-2404 | OL1-2G41-2404 | OL1-2G41-2404 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 - DEHYDRATION - REGEN - DEPROP - C2 HYDROG - C2 HYDROGENATION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1024-PFD-0010-2404 | OL1-2G41-2404 | OL1-2G41-2404 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 - DEHYDRATION - REGEN - DEPROP - C2 HYDROG - C2 HYDROGENATION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1024-PFD-0010-2405 | OL1-2G41-2405 | OL1-2G41-2405 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 - DEHYDRATION - REGEN - DEPROP - C2 HYDROG - LP DEPROPANIZER | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1024-PFD-0010-2405 | OL1-2G41-2405 | OL1-2G41-2405 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 - DEHYDRATION - REGEN - DEPROP - C2 HYDROG - LP DEPROPANIZER | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1025-PFD-0010-2501 | OL1-2G41-2501 | OL1-2G41-2501 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1025-PFD-0010-2501 | OL1-2G41-2501 | OL1-2G41-2501 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1025-PFD-0010-2502 | OL1-2G41-2502 | OL1-2G41-2502 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - RESIDUE GAS SYSTEM | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1025-PFD-0010-2502 | OL1-2G41-2502 | OL1-2G41-2502 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - RESIDUE GAS SYSTEM | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1025-PFD-0010-2503 | OL1-2G41-2503 | OL1-2G41-2503 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - DEMETHANIZER | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1025-PFD-0010-2503 | OL1-2G41-2503 | OL1-2G41-2503 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - DEMETHANIZER | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1025-PFD-0010-2504 | OL1-2G41-2504 | OL1-2G41-2504 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - DEETHANIZER | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1025-PFD-0010-2504 | OL1-2G41-2504 | OL1-2G41-2504 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - DEETHANIZER | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1025-PFD-0010-2505 | OL1-2G41-2505 | OL1-2G41-2505 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - ETHYLENE FRACTIONATION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1025-PFD-0010-2505 | OL1-2G41-2505 | OL1-2G41-2505 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - ETHYLENE FRACTIONATION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1025-PFD-0010-2506 | OL1-2G41-2506 | OL1-2G41-2506 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - HYDROGEN PURIFICATION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1025-PFD-0010-2506 | OL1-2G41-2506 | OL1-2G41-2506 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - HYDROGEN PURIFICATION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1026-PFD-0010-2601 | OL1-2G41-2601 | OL1-2G41-2601 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 - HOT FRACTIONATION - C3 HYDROGENATION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1026-PFD-0010-2601 | OL1-2G41-2601 | OL1-2G41-2601 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 - HOT FRACTIONATION - C3 HYDROGENATION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1026-PFD-0010-2602 | OL1-2G41-2602 | OL1-2G41-2602 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 - HOT FRACTIONATION - SECONDARY DEETHANIZER | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1026-PFD-0010-2602 | OL1-2G41-2602 | OL1-2G41-2602 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 - HOT FRACTIONATION - SECONDARY DEETHANIZER | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1026-PFD-0010-2603 | OL1-2G41-2603 | OL1-2G41-2603 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 - HOT FRACTIONATION - PROPYLENE FRACTIONATION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1026-PFD-0010-2603 | OL1-2G41-2603 | OL1-2G41-2603 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 - HOT FRACTIONATION - PROPYLENE FRACTIONATION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1026-PFD-0010-2604 | OL1-2G41-2604 | OL1-2G41-2604 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 - HOT FRACTIONATION - DEBUTANIZER | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1026-PFD-0010-2604 | OL1-2G41-2604 | OL1-2G41-2604 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 - HOT FRACTIONATION - DEBUTANIZER | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1027-PFD-0010-2701 | OL1-2G41-2701 | OL1-2G41-2701 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 - GHU & C4-C5 HYDROG - GHU-1 REACTOR & DEPENTANIZER | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1027-PFD-0010-2701 | OL1-2G41-2701 | OL1-2G41-2701 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 - GHU & C4-C5 HYDROG - GHU-1 REACTOR & DEPENTANIZER | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1027-PFD-0010-2702 | OL1-2G41-2702 | OL1-2G41-2702 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 - GHU & C4-C5 HYDROG - GHU-1 RERUN TOWER | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1027-PFD-0010-2702 | OL1-2G41-2702 | OL1-2G41-2702 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 - GHU & C4-C5 HYDROG - GHU-1 RERUN TOWER | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1027-PFD-0010-2703 | OL1-2G41-2703 | OL1-2G41-2703 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 - GHU & C4-C5 HYDROG - HYDROG REACTIVATION GAS SYSTEM | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1027-PFD-0010-2703 | OL1-2G41-2703 | OL1-2G41-2703 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 - GHU & C4-C5 HYDROG - HYDROG REACTIVATION GAS SYSTEM | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1027-PFD-0010-2704 | OL1-2G41-2704 | OL1-2G41-2704 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 - GHU & C4-C5 HYDROG - C4-C5 HYDROGENATION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1027-PFD-0010-2704 | OL1-2G41-2704 | OL1-2G41-2704 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 - GHU & C4-C5 HYDROG - C4-C5 HYDROGENATION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1028-PFD-0010-2801 | OL1-2G41-2801 | OL1-2G41-2801 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 - REFRIGERATION SYSTEM - PROPYLENE REFRIGERATION 1 | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1028-PFD-0010-2801 | OL1-2G41-2801 | OL1-2G41-2801 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 - REFRIGERATION SYSTEM - PROPYLENE REFRIGERATION 1 | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1028-PFD-0010-2802 | OL1-2G41-2802 | OL1-2G41-2802 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 - REFRIGERATION SYSTEM - PROPYLENE REFRIGERATION 2 | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1028-PFD-0010-2802 | OL1-2G41-2802 | OL1-2G41-2802 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 - REFRIGERATION SYSTEM - PROPYLENE REFRIGERATION 2 | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1028-PFD-0010-2803 | OL1-2G41-2803 | OL1-2G41-2803 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 - REFRIGERATION SYSTEM - ETHYLENE REFRIGERATION 1 | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1028-PFD-0010-2803 | OL1-2G41-2803 | OL1-2G41-2803 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 - REFRIGERATION SYSTEM - ETHYLENE REFRIGERATION 1 | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1028-PFD-0010-2804 | OL1-2G41-2804 | OL1-2G41-2804 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 - REFRIGERATION SYSTEM - ETHYLENE REFRIGERATION 2 | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1028-PFD-0010-2804 | OL1-2G41-2804 | OL1-2G41-2804 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 - REFRIGERATION SYSTEM - ETHYLENE REFRIGERATION 2 | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1029-PFD-0010-2901 | OL1-2G41-2901 | OL1-2G41-2901 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 29 - OLEFINS RECOVERY UNIT AUX - CHEMICAL STORAGE | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1029-PFD-0010-2901 | OL1-2G41-2901 | OL1-2G41-2901 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 29 - OLEFINS RECOVERY UNIT AUX - CHEMICAL STORAGE | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1030-PFD-0010-3001 | OL1-2G41-3001 | OL1-2G41-3001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 - C4 UNIT BDU - PREDISTILLATION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1030-PFD-0010-3001 | OL1-2G41-3001 | OL1-2G41-3001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 - C4 UNIT BDU - PREDISTILLATION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1030-PFD-0010-3002 | OL1-2G41-3002 | OL1-2G41-3002 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 - C4 UNIT BDU - EVAPORATION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1030-PFD-0010-3002 | OL1-2G41-3002 | OL1-2G41-3002 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 - C4 UNIT BDU - EVAPORATION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1030-PFD-0010-3003 | OL1-2G41-3003 | OL1-2G41-3003 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 - C4 UNIT BDU - RECTIFIER | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1030-PFD-0010-3003 | OL1-2G41-3003 | OL1-2G41-3003 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 - C4 UNIT BDU - RECTIFIER | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1030-PFD-0010-3004 | OL1-2G41-3004 | OL1-2G41-3004 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 - C4 UNIT BDU - DEGASSING | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1030-PFD-0010-3004 | OL1-2G41-3004 | OL1-2G41-3004 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 - C4 UNIT BDU - DEGASSING | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1030-PFD-0010-3005 | OL1-2G41-3005 | OL1-2G41-3005 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 - C4 UNIT BDU - FRACTIONATION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1030-PFD-0010-3005 | OL1-2G41-3005 | OL1-2G41-3005 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 - C4 UNIT BDU - FRACTIONATION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1031-PFD-0010-3101 | OL1-2G41-3101 | OL1-2G41-3101 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 31 - C4 UNIT BDU UTILITIES - SOLVENT REGENERATION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1031-PFD-0010-3101 | OL1-2G41-3101 | OL1-2G41-3101 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 31 - C4 UNIT BDU UTILITIES - SOLVENT REGENERATION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1031-PFD-0010-3102 | OL1-2G41-3102 | OL1-2G41-3102 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 31 - C4 UNIT BDU UTILITIES - STEAM AND CONDENSATE SYSTEM | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1031-PFD-0010-3102 | OL1-2G41-3102 | OL1-2G41-3102 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 31 - C4 UNIT BDU UTILITIES - STEAM AND CONDENSATE SYSTEM | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1039-PFD-0010-3901 | OL1-2G41-3901 | OL1-2G41-3901 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 39 - C4 UNIT AUX - BDU CHEMICAL STORAGE | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1039-PFD-0010-3901 | OL1-2G41-3901 | OL1-2G41-3901 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 39 - C4 UNIT AUX - BDU CHEMICAL STORAGE | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1050-PFD-0030-5001 | OL1-2G42-5001 | OL1-2G42-5001 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 50 - WATER SYSTEM - TREATED POTABLE AND DEMIN WATER SYSTEMS | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1050-PFD-0030-5001 | OL1-2G42-5001 | OL1-2G42-5001 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 50 - WATER SYSTEM - TREATED POTABLE AND DEMIN WATER SYSTEMS | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1051-PFD-0030-5101 | OL1-2G42-5101 | OL1-2G42-5101 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 - BFW STEAM AND CONDENSATE SYSTEM - STEAM BALANCE DIAGRAM | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1051-PFD-0030-5101 | OL1-2G42-5101 | OL1-2G42-5101 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 - BFW STEAM AND CONDENSATE SYSTEM - STEAM BALANCE DIAGRAM | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1051-PFD-0030-5102 | OL1-2G42-5102 | OL1-2G42-5102 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 - BFW STEAM AND CONDENSATE SYSTEM - CONDENSATE AND BOILER FEEDWATER SYSTEMS | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1051-PFD-0030-5102 | OL1-2G42-5102 | OL1-2G42-5102 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 - BFW STEAM AND CONDENSATE SYSTEM - CONDENSATE AND BOILER FEEDWATER SYSTEMS | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1051-PFD-0030-5103 | OL1-2G42-5103 | OL1-2G42-5103 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 - BFW STEAM AND CONDENSATE SYSTEM - CONDENSATE TREATMENT SYSTEM | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1051-PFD-0030-5103 | OL1-2G42-5103 | OL1-2G42-5103 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 - BFW STEAM AND CONDENSATE SYSTEM - CONDENSATE TREATMENT SYSTEM | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1051-PFD-0030-5104 | OL1-2G42-5104 | OL1-2G42-5104 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 - BFW STEAM AND CONDENSATE SYSTEM - FURNACE BLOWDOWN SYSTEM | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1051-PFD-0030-5104 | OL1-2G42-5104 | OL1-2G42-5104 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 - BFW STEAM AND CONDENSATE SYSTEM - FURNACE BLOWDOWN SYSTEM | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1052-PFD-0030-5201 | OL1-2G42-5201 | OL1-2G42-5201 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 52 - FUEL SYSTEM - FUEL GAS SYSTEM | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1052-PFD-0030-5201 | OL1-2G42-5201 | OL1-2G42-5201 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 52 - FUEL SYSTEM - FUEL GAS SYSTEM | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1053-PFD-0030-5301 | OL1-2G42-5301 | OL1-2G42-5301 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 53 - COOLING WATER SYSTEM - COOLING WATER DIAGRAM | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1053-PFD-0030-5301 | OL1-2G42-5301 | OL1-2G42-5301 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 53 - COOLING WATER SYSTEM - COOLING WATER DIAGRAM | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1053-PFD-0030-5311 | OL1-2G42-5311 | OL1-2G42-5311 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 53 - COOLING WATER SYSTEM - COOLING TOWER | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1053-PFD-0030-5311 | OL1-2G42-5311 | OL1-2G42-5311 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 53 - COOLING WATER SYSTEM - COOLING TOWER | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1054-PFD-0030-5401 | OL1-2G42-5401 | OL1-2G42-5401 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 54 - AIR AND NITROGEN SYSTEM - PLANT AIR INSTRUMENT AIR AND NITROGEN SYSTEMS | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1054-PFD-0030-5401 | OL1-2G42-5401 | OL1-2G42-5401 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 54 - AIR AND NITROGEN SYSTEM - PLANT AIR INSTRUMENT AIR AND NITROGEN SYSTEMS | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1055-PFD-0030-5501 | OL1-2G42-5501 | OL1-2G42-5501 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 - VENT GAS AND FLARE SYSTEM - FLARE AND BLOWDOWN SYSTEM | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1055-PFD-0030-5501 | OL1-2G42-5501 | OL1-2G42-5501 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 - VENT GAS AND FLARE SYSTEM - FLARE AND BLOWDOWN SYSTEM | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1055-PFD-0030-5502 | OL1-2G42-5502 | OL1-2G42-5502 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 - VENT GAS AND FLARE SYSTEM - PROCESS VENT GAS COLLECTION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1055-PFD-0030-5502 | OL1-2G42-5502 | OL1-2G42-5502 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 - VENT GAS AND FLARE SYSTEM - PROCESS VENT GAS COLLECTION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1055-PFD-0030-5511 | OL1-2G42-5511 | OL1-2G42-5511 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 - VENT GAS AND FLARE SYSTEM - HP - LLDPE LP FLARE | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1055-PFD-0030-5511 | OL1-2G42-5511 | OL1-2G42-5511 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 - VENT GAS AND FLARE SYSTEM - HP - LLDPE LP FLARE | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1055-PFD-0030-5512 | OL1-2G42-5512 | OL1-2G42-5512 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 - VENT GAS AND FLARE SYSTEM - ENCLOSED GROUND FLARE | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1055-PFD-0030-5512 | OL1-2G42-5512 | OL1-2G42-5512 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 - VENT GAS AND FLARE SYSTEM - ENCLOSED GROUND FLARE | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5601 | OL1-2G42-5601 | OL1-2G42-5601 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - OILY WASTEWATER COLLECTION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5601 | OL1-2G42-5601 | OL1-2G42-5601 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - OILY WASTEWATER COLLECTION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5602 | OL1-2G42-5602 | OL1-2G42-5602 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - SURFACE RUNOFF COLLECTION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5602 | OL1-2G42-5602 | OL1-2G42-5602 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - SURFACE RUNOFF COLLECTION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5603 | OL1-2G42-5603 | OL1-2G42-5603 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - CRACKER HOLDING BASIN | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5603 | OL1-2G42-5603 | OL1-2G42-5603 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - CRACKER HOLDING BASIN | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5604 | OL1-2G42-5604 | OL1-2G42-5604 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - DOMESTIC WASTEWATER COLLECTION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5604 | OL1-2G42-5604 | OL1-2G42-5604 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - DOMESTIC WASTEWATER COLLECTION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5610 | OL1-2G42-5610 | OL1-2G42-5610 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - HP FLARE AREA SW & OILY WW COLLECTION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5610 | OL1-2G42-5610 | OL1-2G42-5610 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - HP FLARE AREA SW & OILY WW COLLECTION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5611 | OL1-2G42-5611 | OL1-2G42-5611 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - OSBL OILY WASTEWATER COLLECTION | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5611 | OL1-2G42-5611 | OL1-2G42-5611 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - OSBL OILY WASTEWATER COLLECTION | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5612 | OL1-2G42-5612 | OL1-2G42-5612 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - OILY WASTEWATER EQUALIZATION TANK | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5612 | OL1-2G42-5612 | OL1-2G42-5612 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - OILY WASTEWATER EQUALIZATION TANK | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5613 | OL1-2G42-5613 | OL1-2G42-5613 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - CPI & IGF PACKAGES | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5613 | OL1-2G42-5613 | OL1-2G42-5613 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - CPI & IGF PACKAGES | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5614 | OL1-2G42-5614 | OL1-2G42-5614 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - BIOTREATMENT PACKAGE | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5614 | OL1-2G42-5614 | OL1-2G42-5614 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - BIOTREATMENT PACKAGE | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 3
036909C-1056-PFD-0030-5615 | OL1-2G42-5615 | OL1-2G42-5615 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - CHECK BASIN | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5615 | OL1-2G42-5615 | OL1-2G42-5615 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - CHECK BASIN | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5616 | OL1-2G42-5616 | OL1-2G42-5616 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - SLUDGE DEWATERING PACKAGE | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5616 | OL1-2G42-5616 | OL1-2G42-5616 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - SLUDGE DEWATERING PACKAGE | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1056-PFD-0030-5617 | OL1-2G42-5617 | OL1-2G42-5617 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - SLOP & OIL SLUDGE | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1056-PFD-0030-5617 | OL1-2G42-5617 | OL1-2G42-5617 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - SLOP & OIL SLUDGE | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1059-PFD-0030-5901 | OL1-2G42-5901 | OL1-2G42-5901 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 59 - UTILITIES AUXILLIARIES - CHEMICAL STORAGE | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1059-PFD-0030-5901 | OL1-2G42-5901 | OL1-2G42-5901 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 59 - UTILITIES AUXILLIARIES - CHEMICAL STORAGE | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1059-PFD-0030-5911 | OL1-2G42-5911 | OL1-2G42-5911 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 59 - UTILITIES AUXILLIARIES - COMPLEX U & O CHEMICAL STORAGE | A | IFA | TPSK-LSPA1-T-PE-00026 | 2018-08-23 | A3-Approved with comments, re-submit for review. | 2018-10-29 | 2018-09-06 | 2018-08-23 | IFA | H | HOC | PE | 1
036909C-1059-PFD-0030-5911 | OL1-2G42-5911 | OL1-2G42-5911 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 59 - UTILITIES AUXILLIARIES - COMPLEX U & O CHEMICAL STORAGE | B | IFD | TPSK-LSPA1-T-PE-00155 | 2018-10-10 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PE | 1
036909C-1000-NM-0001-1001 | OL1-2G44-1001 | OL1-2G44-1001 | OVERALL MATERIAL BALANCE | A | IFI | TPSK-LSPA1-T-PE-00009 | 2018-08-06 | R2-Comments as noted | 2018-08-23 |  | 2018-08-03 | IFI | C | HOC | PE | 3
036909C-1000-NM-0001-1002 | OL1-2G44-1002 | OL1-2G44-1002 | HEAT & MATERIAL BALANCE - DESIGN CASE 6 | A | IFI | TPSK-LSPA1-T-PE-00032 | 2018-08-31 | Transmitted |  |  | 2018-08-30 | IFI | C | HOC | PE | 3
036909C-1000-NM-0001-1003 | OL1-2G44-1003 | OL1-2G44-1003 | HEAT & MATERIAL BALANCE - DESIGN CASE 8 | A | IFI | TPSK-LSPA1-T-PE-00032 | 2018-08-31 | Transmitted |  |  | 2018-08-30 | IFI | C | HOC | PE | 3
036909C-1000-NM-0001-1004 | OL1-2G44-1004 | OL1-2G44-1004 | HEAT & MATERIAL BALANCE - DESIGN CASE 9 | A | IFI | TPSK-LSPA1-T-PE-00032 | 2018-08-31 | Transmitted |  |  | 2018-08-30 | IFI | C | HOC | PE | 3
036909C-1000-NM-0001-1010 | OL1-2G44-1010 | OL1-2G44-1010 | HEAT AND MATERIAL BALANCE - ISBL SUPPORTING UTILITIES | A | IFI | TPSK-LSPA1-T-PE-00128 | 2018-10-03 | Transmitted |  |  | 2018-10-03 | IFI | C | HOC | PE | 3
036909C-1000-NM-0001-1011 | OL1-2G44-1011 | OL1-2G44-1011 | HEAT & MATERIAL BALANCE - COOLING WATER SYSTEM | A | IFI | TPSK-LSPA1-T-PE-00116 | 2018-10-01 | Transmitted |  |  | 2018-09-28 | IFI | C | HOC | PE | 3
036909C-1000-NM-0003-1001 | OL1-2G62-1001 | OL1-2G62-1001 | STEAM BALANCE | A | IFI | TPSK-LSPA1-T-PE-00059 | 2018-09-17 | Transmitted | 2018-10-04 | 2018-10-01 | 2018-09-17 | IFI | C | HOC | PE | 3
036909C-1000-NM-0003-1006 | OL1-2G62-1006 | OL1-2G62-1006 | COOLING WATER BALANCE | A | IFI | TPSK-LSPA1-T-PE-00054 | 2018-09-17 | R2-Comments as noted | 2018-10-09 | 2018-10-08 | 2018-09-14 | IFI | C | HOC | PE | 3
036909C-1000-NM-0003-1008 | OL1-2G62-1008 | OL1-2G62-1008 | FUEL BALANCE | A | IFI | TPSK-LSPA1-T-PE-00049 | 2018-09-13 | Transmitted |  |  | 2018-09-12 | IFI | C | HOC | PE | 3
036909C-1000-JSD-3400-0001 | OL1-2H03-0001 | OL1-2H03-0001 | AIR CONDITIONING VENTILATING AND DUCTING DESIGN | A | IFR | TPSK-LSPA1-T-EE-00165 | 2018-10-12 | R2-Comments as noted | 2018-10-26 | 2018-10-26 | 2018-10-12 | IFR | C | ROC | EE | 2
036909C-1000-PP-830 | OL1-2J92-0002 | OL1-2J92-0002 | EMPLOYEE GRIEVANCE MANAGEMENT PLAN | 0 | IFI | TPSK-LSPA1-T-HR-00040 | 2018-09-12 | Transmitted |  |  | 2018-09-12 | IFI | C | SK | HR | 3
036909C-1000-PP-831 | OL1-2J93-0004 | OL1-2J93-0004 | HUMAN RESOURCE POLICY AND PROCEDURES | 0 | IFI | TPSK-LSPA1-T-HR-00040 | 2018-09-12 | Transmitted |  |  | 2018-09-12 | IFI | C | SK | HR | 3
036909C-1000-PP-832 | OL1-2J94-0002 | OL1-2J94-0002 | WORKER CODE OF CONDUCT DECLARATION FORM | 0 | IFI | TPSK-LSPA1-T-HR-00040 | 2018-09-12 | Transmitted |  |  | 2018-09-12 | IFI | C | SK | HR | 3
036909C-1000-PP-833 | OL1-2J94-0004 | OL1-2J94-0004 | CHILD LABOR RISK ASSESSMENT CHECKLIST | 0 | IFI | TPSK-LSPA1-T-HR-00040 | 2018-09-12 | Transmitted |  |  | 2018-09-12 | IFI | C | SK | HR | 3
036909C-1000-PP-834 | OL1-2J94-0005 | OL1-2J94-0005 | FORCED LABOR RISK ASSESSMENT CHECKLIST | 0 | IFI | TPSK-LSPA1-T-HR-00040 | 2018-09-12 | Transmitted |  |  | 2018-09-12 | IFI | C | SK | HR | 3
036909C-1000-STC-1790-0001 | OL1-2K20-0001 | OL1-2K20-0001 | CONSTRUCTION STANDARDS FOR REINFORCED CONCRETE WORKS | A | IFR | TPSK-LSPA1-T-CV-00088 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-19 | IFR | C | ROC | CV | 2
036909C-1000-STC-1890-0001 | OL1-2K21-0001 | OL1-2K21-0001 | CONSTRUCTION STANDARDS FOR STEEL STRUCTURES | A | IFR | TPSK-LSPA1-T-CV-00088 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-19 | IFR | C | ROC | CV | 2
036909C-1000-STC-1490-0001 | OL1-2K23-0001 | OL1-2K23-0001 | STANDARD CONSTRUCTION DRAWINGS FOR UNDERGROUND SYSTEMS | A | IFR | TPSK-LSPA1-T-CV-00088 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-18 | IFR | C | ROC | CV | 2
036909C-1000-MS-1422-0001 | OL1-2K43-0002 | OL1-2K43-0002 | TECHNICAL SPECIFICATION FOR GEOTECHNICAL INVESTIGATION | A | IFR | TPSK-LSPA1-T-CV-00147 | 2018-10-10 | Transmitted |  | 2018-10-24 | 2018-10-04 | IFR | H | ROC | CV | 2
036909C-1000-MS-1422-0001 | OL1-2K43-0002 | OL1-2K43-0002 | TECHNICAL SPECIFICATION FOR GEOTECHNICAL INVESTIGATION | B | IFR | TPSK-LSPA1-T-CV-00188 | 2018-10-17 | R1-No comments | 2018-11-01 | 2018-11-05 | 2018-10-15 | IFR | C | ROC | CV | 2
036909C-1000-PS-1422-0001 | OL1-2K43-0003 | OL1-2K43-0003 | PRICE LIST FOR GEOTECHNICAL INVESTIGATION | A | IFR | TPSK-LSPA1-T-CV-00147 | 2018-10-10 | Transmitted |  | 2018-10-24 | 2018-10-04 | IFR | H | ROC | CV | 2
036909C-1000-PS-1422-0001 | OL1-2K43-0003 | OL1-2K43-0003 | PRICE LIST FOR GEOTECHNICAL INVESTIGATION | B | IFR | TPSK-LSPA1-T-CV-00188 | 2018-10-17 | R1-No comments | 2018-11-01 | 2018-11-05 | 2018-10-15 | IFR | C | ROC | CV | 2
036909C-1000-DW-1422-0001 | OL1-2K43-0004 | OL1-2K43-0004 | SOIL INVESTIGATION PLAN | A | IFR | TPSK-LSPA1-T-CV-00145 | 2018-10-10 | Transmitted |  | 2018-10-24 | 2018-10-04 | IFR | H | ROC | CV | 2
036909C-1000-DW-1422-0001 | OL1-2K43-0004 | OL1-2K43-0004 | SOIL INVESTIGATION PLAN | B | IFR | TPSK-LSPA1-T-CV-00163 | 2018-10-12 | Transmitted |  | 2018-10-26 | 2018-10-10 | IFR | C | ROC | CV | 2
036909C-1000-DW-1402-0001 | OL1-2K92-0001 | OL1-2K92-0001 | GENERAL NOTES FOR UNDERGROUND WORKS | A | IFR | TPSK-LSPA1-T-CV-00086 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-18 | IFR | C | ROC | CV | 2
036909C-1000-DW-1702-0002 | OL1-2K92-0002 | OL1-2K92-0002 | GENERAL NOTES FOR PRECAST CONCRETE WORKS | A | IFR | TPSK-LSPA1-T-CV-00137 | 2018-10-08 | Transmitted |  | 2018-10-22 | 2018-10-04 | IFR | C | ROC | CV | 2
036909C-1000-DW-1702-0001 | OL1-2K92-0003 | OL1-2K92-0003 | GENERAL NOTES FOR CONCRETE WORKS | A | IFR | TPSK-LSPA1-T-CV-00086 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-19 | IFR | C | ROC | CV | 2
036909C-1000-DW-1802-0001 | OL1-2K92-0004 | OL1-2K92-0004 | GENERAL NOTES FOR STEEL STRUCTURES | A | IFR | TPSK-LSPA1-T-CV-00086 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-19 | IFR | C | ROC | CV | 2
036909C-1011-SP-1040-1001 | OL1-2M03-1001 | OL1-2M03-1001 | MECHANICAL EQUIPMENT DATASHEET FOR FURNACE ID FAN USC 36M | A | IFR | TPSK-LSPA1-T-ME-00247 | 2018-10-31 | Transmitted |  | 2018-11-13 | 2018-10-30 | IFR | C | HOC | ME | 2
036909C-1019-SP-1013-1950 | OL1-2M03-1950 | OL1-2M03-1950 | MECHANICAL EQUIPMENT DATASHEET FOR DECOKING AIR COMPRESSOR PACKAGE | A | IFA | TPSK-LSPA1-T-ME-00050 | 2018-09-13 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-27 | 2018-09-13 | IFA | H | HOC | ME | 1
036909C-1019-SP-1013-1950 | OL1-2M03-1950 | OL1-2M03-1950 | MECHANICAL EQUIPMENT DATASHEET FOR DECOKE AIR COMPRESSOR PACKAGE | B | IFQ | TPSK-LSPA1-T-ME-00161 | 2018-10-11 | Transmitted |  |  | 2018-10-10 | IFI | H | HOC | ME | 3
036909C-1019-SP-1013-1950 | OL1-2M03-1950 | OL1-2M03-1950 | MECHANICAL EQUIPMENT DATASHEET - DECOKE AIR COMPRESSOR PACKAGE | C | IFQ | TPSK-LSPA1-T-ME-00261 | 2018-11-01 | Transmitted |  |  | 2018-10-31 | IFI | C | HOC | ME | 1
036909C-1012-SP-1040-2001 | OL1-2M03-2001 | OL1-2M03-2001 | MECHANICAL EQUIPMENT DATASHEET FOR FURNACE ID FAN USC 132U | A | IFR | TPSK-LSPA1-T-ME-00247 | 2018-10-31 | Transmitted |  | 2018-11-13 | 2018-10-29 | IFR | C | HOC | ME | 2
036909C-1020-SP-0910-2006 | OL1-2M03-2006 | OL1-2M03-2006 | MECHANICAL EQUIPMENT DATA SHEET QUENCH OIL PUMP 10-P-2006 A-B-C | A | IFQ | TPSK-LSPA1-T-ME-00235 | 2018-10-26 | Transmitted |  | 2018-11-09 | 2018-10-25 | IFR | C | HOC | ME | 2
036909C-1021-TDS-0661-2101 | OL1-2M03-2101 | OL1-2M03-2101 | MECHANICAL DATA SHEET - 10-E-2100 - QUENCH WATER COOLER | A | IFA | TPSK-LSPA1-T-ME-00058 | 2018-09-17 | A3-Approved with comments, re-submit for review. | 2018-09-28 | 2018-10-01 | 2018-09-14 | IFA | H | HOC | ME | 1
036909C-1021-TDS-0661-2101 | OL1-2M03-2101 | OL1-2M03-2101 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2100 - QUENCH WATER COOLER | B | IFQ | TPSK-LSPA1-T-ME-00154 | 2018-10-10 | R1-No comments | 2018-11-07 |  | 2018-10-09 | IFI | C | HOC | ME | 3
036909C-1021-SP-0910-2106 | OL1-2M03-2106 | OL1-2M03-2106 | MECHANICAL EQUIPMENT DATA SHEET - QUENCH WATER PUMPS - 10-P-2106 A-B-C | A | IFQ | TPSK-LSPA1-T-ME-00236 | 2018-10-27 | Transmitted |  | 2018-11-09 | 2018-10-25 | IFR | C | HOC | ME | 2
036909C-1021-SP-0910-2146 | OL1-2M03-2146 | OL1-2M03-2146 | MECHANICAL EQUIPMENT DATA SHEET - DSG FEED PUMPS 10-P-2146 A-B | A | IFQ | TPSK-LSPA1-T-ME-00235 | 2018-10-26 | Transmitted |  | 2018-11-09 | 2018-10-25 | IFR | C | HOC | ME | 2
036909C-1022-SP-1011-2200 | OL1-2M03-2200 | OL1-2M03-2200 | MECHANICAL EQUIPMENT DATA SHEET FOR CRACKED GAS COMPRESSOR | A | IFA | TPSK-LSPA1-T-ME-00038 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-09-28 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | ME | 1
036909C-1022-SP-1011-2200 | OL1-2M03-2200 | OL1-2M03-2200 | MECHANICAL EQUIPMENT DATA SHEET FOR CRACKED GAS COMPRESSOR | B | IFQ | TPSK-LSPA1-T-ME-00127 | 2018-10-03 | Transmitted |  |  | 2018-10-02 | IFI | H | HOC | ME | 3
036909C-1022-SP-1011-2200 | OL1-2M03-2200 | OL1-2M03-2200 | MECHANICAL EQUIPMENT DATA SHEET FOR CRACKED GAS COMPRESSOR | C | IFQ | TPSK-LSPA1-T-ME-00280 | 2018-11-06 | Transmitted |  |  | 2018-10-31 | IFI | C | HOC | ME | 2
036909C-1023-SP-0510-2300 | OL1-2M03-2300 | OL1-2M03-2300 | MECHANICAL EQUIPMENT DATA SHEET CAUSTIC TOWER 10-T-2300 | A | IFQ | TPSK-LSPA1-T-ME-00246 | 2018-10-31 | Transmitted |  | 2018-11-13 | 2018-10-26 | IFR | C | HOC | ME | 2
036909C-1024-SP-0510-2440 | OL1-2M03-2440 | OL1-2M03-2440 | MECHANICAL EQUIPMENT DATASHEET FOR HP DEPROPANIZER | A | IFQ | TPSK-LSPA1-T-ME-00215 | 2018-10-23 | Transmitted |  | 2018-11-06 | 2018-10-23 | IFR | C | HOC | ME | 2
036909C-1024-SP-0510-2450 | OL1-2M03-2450 | OL1-2M03-2450 | MECHANICAL EQUIPMENT DATASHEET LP DEPROPANIZER | A | IFQ | TPSK-LSPA1-T-ME-00183 | 2018-10-16 | A3-Approved with comments, re-submit for review. | 2018-11-05 | 2018-10-30 | 2018-10-15 | IFR | H | HOC | ME | 2
036909C-1024-SP-0510-2450 | OL1-2M03-2450 | OL1-2M03-2450 | MECHANICAL EQUIPMENT DATASHEET - LP DEPROPANIZER | B | IFQ | TPSK-LSPA1-T-ME-00283 | 2018-11-06 | Transmitted |  |  | 2018-11-06 | IFI | C | HOC | ME | 2
036909C-1024-SP-0910-2453 | OL1-2M03-2453 | OL1-2M03-2453 | MECHANICAL EQUIPMENT DATASHEET - LP DEPROPANIZER REFLUX-PRODUCT PUMP | A | IFQ | TPSK-LSPA1-T-ME-00294 | 2018-11-08 | Transmitted |  | 2018-11-22 | 2018-11-08 | IFR | C | HOC | ME | 2
036909C-1025-SP-0510-2510 | OL1-2M03-2510 | OL1-2M03-2510 | MECHANICAL EQUIPMENT DATA SHEET - DEMETHANIZER PREFRACTIONATOR AND REFLUX DRUM | A | IFQ | TPSK-LSPA1-T-ME-00260 | 2018-10-31 | Transmitted |  | 2018-11-14 | 2018-10-29 | IFR | C | HOC | ME | 2
036909C-1025-SP-0510-2540 | OL1-2M03-2540 | OL1-2M03-2540 | MECHANICAL EQUIPMENT DATA SHEET - DEMETHANIZER AND DEMETHANIZER REFLUX DRUM | A | IFQ | TPSK-LSPA1-T-ME-00304 | 2018-11-09 | Transmitted |  | 2018-11-23 | 2018-11-09 | IFR | C | HOC | ME | 2
036909C-1025-SP-1011-2550 | OL1-2M03-2550 | OL1-2M03-2550 | MECHANICAL EQUIPMENT DATASHEET FOR RESIDUE GAS EXPANDER-RECOMPRESSOR | A | IFA | TPSK-LSPA1-T-ME-00050 | 2018-09-13 | A3-Approved with comments, re-submit for review. | 2018-10-02 | 2018-09-27 | 2018-09-13 | IFA | H | HOC | ME | 1
036909C-1025-SP-1011-2550 | OL1-2M03-2550 | OL1-2M03-2550 | MECHANICAL EQUIPMENT DATASHEET FOR RESIDUE GAS EXPANDER-RECOMPRESSOR | B | IFQ | TPSK-LSPA1-T-ME-00130 | 2018-10-05 | A3-Approved with comments, re-submit for review. | 2018-10-26 |  | 2018-10-04 | IFI | C | HOC | ME | 3
036909C-1025-TDS-0610-2571 | OL1-2M03-2571 | OL1-2M03-2571 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2570 - DEETHANIZER CONDENSER | A | IFQ | TPSK-LSPA1-T-ME-00310 | 2018-11-13 | Transmitted |  | 2018-11-27 | 2018-11-12 | IFR | C | HOC | ME | 2
036909C-1026-SP-0510-2660 | OL1-2M03-2660 | OL1-2M03-2660 | MECHANICAL EQUIPMENT DATASHEET FOR DEBUTANIZER | A | IFQ | TPSK-LSPA1-T-ME-00215 | 2018-10-23 | Transmitted |  | 2018-11-06 | 2018-10-23 | IFR | H | HOC | ME | 2
036909C-1026-SP-0510-2660 | OL1-2M03-2660 | OL1-2M03-2660 | MECHANICAL EQUIPMENT DATASHEET - DEBUTANIZER | B | IFQ | TPSK-LSPA1-T-ME-00288 | 2018-11-08 | Transmitted |  | 2018-11-22 | 2018-11-07 | IFR | C | HOC | ME | 2
036909C-1028-SP-1011-2800 | OL1-2M03-2800 | OL1-2M03-2800 | MECHANICAL EQUIPMENT DATA SHEET FOR PROPYLENE REFRIGERATION COMPRESSOR | A | IFA | TPSK-LSPA1-T-ME-00038 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-09-28 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | ME | 1
036909C-1028-SP-1011-2800 | OL1-2M03-2800 | OL1-2M03-2800 | MECHANICAL EQUIPMENT DATA SHEET FOR PROPYLENE REFRIGERATION COMPRESSOR | B | IFQ | TPSK-LSPA1-T-ME-00127 | 2018-10-03 | Transmitted |  |  | 2018-10-02 | IFI | C | HOC | ME | 3
036909C-1028-SP-1011-2850 | OL1-2M03-2850 | OL1-2M03-2850 | MECHANICAL EQUIPMENT DATA SHEET FOR ETHYLENE REFRIGERATION COMPRESSOR | A | IFA | TPSK-LSPA1-T-ME-00038 | 2018-09-10 | A3-Approved with comments, re-submit for review. | 2018-09-28 | 2018-09-24 | 2018-09-06 | IFA | H | HOC | ME | 1
036909C-1028-SP-1011-2850 | OL1-2M03-2850 | OL1-2M03-2850 | MECHANICAL EQUIPMENT DATA SHEET FOR ETHYLENE REFRIGERATION COMPRESSOR | B | IFQ | TPSK-LSPA1-T-ME-00127 | 2018-10-03 | A3-Approved with comments, re-submit for review. | 2018-10-26 |  | 2018-10-02 | IFI | C | HOC | ME | 3
036909C-1051-SP-0910-5101 | OL1-2M03-5101 | OL1-2M03-5101 | MECHANICAL EQUIPMENT DATA SHEET SHP BFW PUMPS - 10-P-5100 A-B-C | A | IFQ | TPSK-LSPA1-T-ME-00236 | 2018-10-27 | Transmitted |  | 2018-11-09 | 2018-10-25 | IFR | H | HOC | ME | 2
036909C-1051-SP-0910-5101 | OL1-2M03-5101 | OL1-2M03-5101 | MECHANICAL EQUIPMENT DATA SHEET FOR SHP BFW PUMPS | B | IFQ | TPSK-LSPA1-T-ME-00236 | 2018-11-15 | Transmitted |  | 2018-11-29 | 2018-11-12 | IFR | C | HOC | ME | 2
036909C-1051-SP-0910-5102 | OL1-2M03-5102 | OL1-2M03-5102 | MECHANICAL EQUIPMENT DATA SHEET VLP BFW PUMPS - 10-P-5102 A-B | A | IFQ | TPSK-LSPA1-T-ME-00236 | 2018-10-27 | Transmitted |  | 2018-11-09 | 2018-10-25 | IFR | C | HOC | ME | 2
036909C-1051-SP-0910-5109 | OL1-2M03-5109 | OL1-2M03-5109 | MECHANICAL EQUIPMENT DATA SHEET - CONDENSATE PUMPS 10-P-5110 A-B | A | IFQ | TPSK-LSPA1-T-ME-00235 | 2018-10-26 | Transmitted |  | 2018-11-09 | 2018-10-25 | IFR | H | HOC | ME | 2
036909C-1053-SP-0310-0002 | OL1-2M03-5350 | OL1-2M03-5350 | MECHANICAL EQUIPMENT DATASHEET FOR COOLING TOWER | B | IFQ | TPSK-LSPA1-T-ME-00276 | 2018-11-06 | Transmitted |  | 2018-11-19 | 2018-10-30 | IFR | C | KLOC | ME | 2
036909C-1053-SP-0910-5352 | OL1-2M03-5352 | OL1-2M03-5352 | MECHANICAL EQUIPMENT DATA SHEET FOR OLEFINS COOLING WATER PUMPS 10-P-5350 A-H | A | IFQ | TPSK-LSPA1-T-ME-00210 | 2018-10-23 | R2-Comments as noted | 2018-11-14 | 2018-11-06 | 2018-10-22 | IFR | C | HOC | ME | 2
036909C-1053-SP-4234-0002 | OL1-2M03-5355 | OL1-2M03-5355 | MECHANICAL EQUIPMENT DATASHEET FOR SIDE STREAM FILTER PACKAGE | B | IFQ | TPSK-LSPA1-T-ME-00248 | 2018-10-31 | Transmitted |  | 2018-11-16 | 2018-10-29 | IFQ | C | KLOC | ME | 2
036909C-1053-SP-0910-5361 | OL1-2M03-5361 | OL1-2M03-5361 | MECHANICAL EQUIPMENT DATA SHEET FOR CTU COOLING WATER PUMPS 10-P-5360 A-B-C | A | IFQ | TPSK-LSPA1-T-ME-00210 | 2018-10-23 | R2-Comments as noted | 2018-11-14 | 2018-11-06 | 2018-10-22 | IFR | H | HOC | ME | 2
036909C-1011-DW-0122-1201 | OL1-2M06-1201 | OL1-2M06-1201 | USC 36M RECYCLE FURNACE RADIANT COIL ASSEMBLY AND DETAILS | A | IFR | TPSK-LSPA1-T-ME-00062 | 2018-10-08 | Transmitted |  | 2018-10-22 | 2018-09-11 | IFR | C | HOC | ME | 2
036909C-1011-DW-0122-1202 | OL1-2M06-1202 | OL1-2M06-1202 | USC 36M RECYCLE FURNACE TRANSFER LINE AND CLEAN-OUT DETAILS | A | IFR | TPSK-LSPA1-T-ME-00062 | 2018-10-08 | Transmitted |  | 2018-10-22 | 2018-09-11 | IFR | C | HOC | ME | 2
036909C-1011-DW-0122-1203 | OL1-2M06-1203 | OL1-2M06-1203 | USC 36M RECYCLE FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS | A | IFR | TPSK-LSPA1-T-ME-00062 | 2018-10-08 | Transmitted |  | 2018-10-22 | 2018-09-11 | IFR | C | HOC | ME | 2
036909C-1011-DW-0127-1204 | OL1-2M06-1204 | OL1-2M06-1204 | USC 36M RECYCLE FURNACE FABRICATION ASSEMBLY OF CONVECTION COILS FINNED TUBES AND BILL OF MATERIAL | A | IFR | TPSK-LSPA1-T-ME-00182 | 2018-10-16 | Transmitted |  | 2018-10-30 | 2018-10-12 | IFR | C | HOC | ME | 2
036909C-1011-DW-0125-1301 | OL1-2M06-1301 | OL1-2M06-1301 | USC 36M RECYCLE FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS | 0 | IFI | TPSK-LSPA1-T-ME-00286 | 2018-11-07 | Transmitted |  |  | 2018-11-06 | IFI | C | HOC | ME | 3
036909C-1011-DW-0125-1302 | OL1-2M06-1302 | OL1-2M06-1302 | USC 36M RECYCLE FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS | 0 | IFI | TPSK-LSPA1-T-ME-00286 | 2018-11-07 | Transmitted |  |  | 2018-11-06 | IFI | C | HOC | ME | 3
036909C-1012-DW-0122-2201 | OL1-2M06-2201 | OL1-2M06-2201 | USC 132U FURNACE RADIANT COIL ASSEMBLY AND DETAILS | A | IFR | TPSK-LSPA1-T-ME-00062 | 2018-10-08 | Transmitted |  | 2018-10-22 | 2018-09-11 | IFR | C | HOC | ME | 2
036909C-1012-DW-0122-2202 | OL1-2M06-2202 | OL1-2M06-2202 | USC 132U CRACKING FURNACE TRANSFER LINES AND CLEAN-OUT DETAILS | A | IFR | TPSK-LSPA1-T-ME-00062 | 2018-10-08 | Transmitted |  | 2018-10-22 | 2018-09-11 | IFR | C | HOC | ME | 2
036909C-1012-DW-0122-2203 | OL1-2M06-2203 | OL1-2M06-2203 | USC 132U CRACKING FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS | A | IFR | TPSK-LSPA1-T-ME-00062 | 2018-10-08 | Transmitted |  | 2018-10-22 | 2018-09-11 | IFR | C | HOC | ME | 2
036909C-1012-DW-0127-2204 | OL1-2M06-2204 | OL1-2M06-2204 | USC 132U CRACKING FURNACE FABRICATIN ASSEMBLY OF CONVECTION COILS FINNED TUBES AND BILL OF MATERIAL | A | IFR | TPSK-LSPA1-T-ME-00182 | 2018-10-16 | Transmitted |  | 2018-10-30 | 2018-10-12 | IFR | C | HOC | ME | 2
036909C-1012-DW-0125-2301 | OL1-2M06-2301 | OL1-2M06-2301 | USC 132U CRACKING FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS | 0 | IFI | TPSK-LSPA1-T-ME-00289 | 2018-11-08 | Transmitted |  |  | 2018-11-06 | IFI | C | HOC | ME | 3
036909C-1012-DW-0125-2302 | OL1-2M06-2302 | OL1-2M06-2302 | USC 132U CRACKING FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS | 0 | IFI | TPSK-LSPA1-T-ME-00289 | 2018-11-08 | Transmitted |  |  | 2018-11-06 | IFI | C | HOC | ME | 3
036909C-1000-ITP-1011-0001 | OL1-2M07-0008 | OL1-2M07-0008 | INSPECTION AND TEST PLAN FOR CENTRIFUGAL COMPRESSORS STEAM TURBINE DRIVEN | A | IFQ | TPSK-LSPA1-T-ME-00136 | 2018-10-08 | R2-Comments as noted | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFQ | C | ROC | ME | 2
036909C-1000-ITP-1130-0001 | OL1-2M07-0012 | OL1-2M07-0012 | INSPECTION AND TEST PLAN FOR RESIDUE GAS EXPANDER/RECOMPRESSOR | A | IFQ | TPSK-LSPA1-T-ME-00139 | 2018-10-09 | R2-Comments as noted | 2018-10-26 | 2018-10-22 | 2018-10-05 | IFQ | C | ROC | ME | 2
036909C-1000-ITP-1013-0001 | OL1-2M07-0014 | OL1-2M07-0014 | INSPECTION AND TEST PLAN FOR INTEGRALLY GEARED DECOKING AIR COMPRESSORS | A | IFQ | TPSK-LSPA1-T-ME-00198 | 2018-10-19 | R2-Comments as noted | 2018-11-07 | 2018-11-02 | 2018-10-18 | IFQ | C | ROC | ME | 2
036909C-1000-ITP-0910-0001 | OL1-2M07-0015 | OL1-2M07-0015 | INSPECTION AND TEST PLAN FOR API CENTRIFUGAL PUMPS - LLI | A | IFQ | TPSK-LSPA1-T-ME-00257 | 2018-10-31 | Transmitted |  | 2018-11-20 | 2018-10-30 | IMP | C | ROC | ME | 2
036909C-1000-ITP-0570-0001 | OL1-2M07-0055 | OL1-2M07-0055 | INSPECTION AND TEST PLAN FOR TRAYS FOR COLUMNS | A | IFQ | TPSK-LSPA1-T-ME-00300 | 2018-11-09 | Transmitted |  | 2018-11-26 | 2018-11-06 | IFR | C | ROC | ME | 2
036909C-1000-ITP-0661-0001 | OL1-2M07-0064 | OL1-2M07-0064 | INSPECTION AND TEST PLAN FOR PLATE AND FRAME HEAT EXCHANGERS | A | IFQ | TPSK-LSPA1-T-ME-00124 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-ITP-0662-0002 | OL1-2M07-0066 | OL1-2M07-0066 | INSPECTION AND TEST PLAN FOR COLD BOX AND CORE EXCHANGERS | A | IFQ | TPSK-LSPA1-T-ME-00125 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-ITP-0570-0004 | OL1-2M07-0075 | OL1-2M07-0075 | INSPECTION AND TEST PLAN FOR MD TRAYS FOR COLUMNS | A | IFQ | TPSK-LSPA1-T-ME-00278 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-10-31 | IFR | H | ROC | ME | 2
036909C-1000-ITP-0310-0001 | OL1-2M07-0104 | OL1-2M07-0104 | INSPECTION AND TEST PLAN FOR COOLING TOWER | A | IFQ | TPSK-LSPA1-T-ME-00276 | 2018-11-06 | Transmitted |  | 2018-11-19 | 2018-10-30 | IFR | C | KLOC | ME | 2
036909C-1000-ITP-0845-0001 | OL1-2M07-0108 | OL1-2M07-0108 | INSPECTION AND TEST PLAN FOR DEAREATOR | A | IFQ | TPSK-LSPA1-T-ME-00270 | 2018-11-06 | Transmitted |  |  | 2018-10-29 | IFQ | C | ROC | ME | 2
036909C-1012-ITP-0127-2002 | OL1-2M07-2002 | OL1-2M07-2002 | INSPECTION AND TEST PLAN FOR FURNACE CONVECTION FITTINGS | A | IFQ | TPSK-LSPA1-T-ME-00207 | 2018-10-22 | Transmitted |  |  | 2018-10-18 | IFQ | C | HOC | ME | 3
036909C-1012-ITP-0154-2003 | OL1-2M07-2003 | OL1-2M07-2003 | INSPECTION AND TEST PLAN FOR QUENCH EXCHANGERS | A | IFQ | TPSK-LSPA1-T-ME-00233 | 2018-10-26 | Transmitted |  |  | 2018-10-18 | IFQ | C | HOC | ME | 3
036909C-1012-ITP-0122-2004 | OL1-2M07-2004 | OL1-2M07-2004 | INSPECTION AND TEST PLAN FOR RADIANT COIL ASSEMBLIES | A | IFQ | TPSK-LSPA1-T-ME-00063 | 2018-09-18 | Transmitted |  |  | 2018-09-10 | IFI | C | HOC | ME | 3
036909C-1012-ITP-1040-2005 | OL1-2M07-2005 | OL1-2M07-2005 | INSPECTION AND TEST PLAN FOR FURNACE ID FANS | A | IFQ | TPSK-LSPA1-T-ME-00269 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1012-ITP-0155-2018 | OL1-2M07-2018 | OL1-2M07-2018 | INSPECTION AND TEST PLAN FOR FURNACE STEAM DRUMS | A | IFQ | TPSK-LSPA1-T-ME-00263 | 2018-11-01 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1000-MR-1011-0001 | OL1-2M55-0008 | OL1-2M55-0008 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSORS STEAM TURBINE DRIVEN | A | IFQ | TPSK-LSPA1-T-ME-00136 | 2018-10-08 | R1-No comments | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFQ | C | ROC | ME | 2
036909C-1000-MR-1130-0001 | OL1-2M55-0012 | OL1-2M55-0012 | MATERIAL REQUISITION FOR RESIDUE GAS EXPANDER/RECOMPRESSOR | A | IFQ | TPSK-LSPA1-T-ME-00139 | 2018-10-09 | R1-No comments | 2018-10-26 | 2018-10-22 | 2018-10-05 | IFQ | C | ROC | ME | 2
036909C-1000-MR-1013-0001 | OL1-2M55-0014 | OL1-2M55-0014 | MATERIAL REQUISITION FOR INTEGRALLY GEARED DECOKING AIR COMPRESSORS | A | IFQ | TPSK-LSPA1-T-ME-00198 | 2018-10-19 | R1-No comments | 2018-11-07 | 2018-11-02 | 2018-10-18 | IFQ | C | ROC | ME | 2
036909C-1000-MR-0910-0001 | OL1-2M55-0015 | OL1-2M55-0015 | MATERIAL REQUISITION FOR API CENTRIFUGAL PUMPS - LLI | A | IFQ | TPSK-LSPA1-T-ME-00257 | 2018-10-31 | Transmitted |  | 2018-11-20 | 2018-10-30 | IMP | C | ROC | ME | 2
036909C-1000-MR-0570-0001 | OL1-2M55-0055 | OL1-2M55-0055 | MATERIAL REQUISITION FOR TRAYS FOR COLUMNS REQUISITION FOR INQUIRY | A | IFQ | TPSK-LSPA1-T-ME-00300 | 2018-11-09 | Transmitted |  | 2018-11-26 | 2018-11-06 | IFR | C | ROC | ME | 2
036909C-1000-MR-0661-0001 | OL1-2M55-0064 | OL1-2M55-0064 | MATERIAL REQUISITION FOR PLATE AND FRAME HEAT EXCHANGERS REQUISITION FOR INQUIRY | A | IFQ | TPSK-LSPA1-T-ME-00124 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-MR-0662-0002 | OL1-2M55-0066 | OL1-2M55-0066 | MATERIAL REQUISITION FOR COLD BOX AND CORE EXCHANGERS REQUISITION FOR INQUIRY | A | IFQ | TPSK-LSPA1-T-ME-00125 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | H | ROC | ME | 2
036909C-1000-MR-0662-0002 | OL1-2M55-0066 | OL1-2M55-0066 | MATERIAL REQUISITION FOR COLD BOX AND CORE EXCHANGERS REQUISITION FOR INQUIRY | B | IFQ | TPSK-LSPA1-T-ME-00153 | 2018-10-10 | R1-No comments | 2018-11-02 | 2018-10-24 | 2018-10-09 | IFQ | C | ROC | ME | 2
036909C-1000-MR-0570-0004 | OL1-2M55-0075 | OL1-2M55-0075 | MATERIAL REQUISITION FOR MD TRAYS FOR COLUMNS REQUISITION FOR INQUIRY | A | IFQ | TPSK-LSPA1-T-ME-00278 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-10-31 | IFR | H | ROC | ME | 2
036909C-1000-MR-0845-0001 | OL1-2M55-0108 | OL1-2M55-0108 | MATERIAL REQUISITION FOR DEAREATOR | A | IFQ | TPSK-LSPA1-T-ME-00270 | 2018-11-06 | Transmitted |  |  | 2018-10-29 | IFQ | C | ROC | ME | 2
036909C-1000-MR-4234-0001 | OL1-2M55-0109 | OL1-2M55-0109 | MATERIAL REQUISITION FOR SIDE STREAM FILTER PACKAGE | A | IFQ | TPSK-LSPA1-T-ME-00248 | 2018-10-31 | Transmitted |  | 2018-11-16 | 2018-10-29 | IFQ | C | KLOC | ME | 2
036909C-1012-MR-0127-2002 | OL1-2M55-2002 | OL1-2M55-2002 | MATERIAL REQUISITION FOR FURNACE CONVECTION FITTINGS | A | IFQ | TPSK-LSPA1-T-ME-00207 | 2018-10-22 | Transmitted |  |  | 2018-10-16 | IFQ | C | HOC | ME | 3
036909C-1012-MR-0154-2003 | OL1-2M55-2003 | OL1-2M55-2003 | MATERIAL REQUISITION FOR QUENCH EXCHANGERS | A | IFQ | TPSK-LSPA1-T-ME-00233 | 2018-10-26 | Transmitted |  |  | 2018-10-18 | IFQ | C | HOC | ME | 3
036909C-1012-MR-0122-2004 | OL1-2M55-2004 | OL1-2M55-2004 | MATERIAL REQUISITION FOR RADIANT COIL ASSEMBLIES | A | IFQ | TPSK-LSPA1-T-ME-00063 | 2018-09-18 | Transmitted |  |  | 2018-09-12 | IFI | C | HOC | ME | 3
036909C-1012-MR-1040-2005 | OL1-2M55-2005 | OL1-2M55-2005 | MATERIAL REQUISITION FOR FURNACE ID FANS | A | IFQ | TPSK-LSPA1-T-ME-00269 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1012-MR-0155-2018 | OL1-2M55-2018 | OL1-2M55-2018 | MATERIAL REQUISITION FOR FURNACE STEAM DRUMS | A | IFQ | TPSK-LSPA1-T-ME-00263 | 2018-11-01 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1000-SR-1011-0001 | OL1-2M56-0008 | OL1-2M56-0008 | SCOPE OF SUPPLY FOR CENTRIFUGAL COMPRESSORS STEAM TURBINE DRIVEN | A | IFQ | TPSK-LSPA1-T-ME-00136 | 2018-10-08 | R2-Comments as noted | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFQ | C | ROC | ME | 2
036909C-1000-SR-1130-0001 | OL1-2M56-0012 | OL1-2M56-0012 | SCOPE OF SUPPLY FOR RESIDUE GAS EXPANDER/RECOMPRESSOR | A | IFQ | TPSK-LSPA1-T-ME-00139 | 2018-10-09 | R2-Comments as noted | 2018-10-26 | 2018-10-22 | 2018-10-05 | IFQ | C | ROC | ME | 2
036909C-1000-SR-1013-0001 | OL1-2M56-0014 | OL1-2M56-0014 | SCOPE OF SUPPLY FOR INTEGRALLY GEARED DECOKING AIR COMPRESSORS | A | IFQ | TPSK-LSPA1-T-ME-00198 | 2018-10-19 | R1-No comments | 2018-11-07 | 2018-11-02 | 2018-10-18 | IFQ | C | ROC | ME | 2
036909C-1000-SR-0910-0001 | OL1-2M56-0015 | OL1-2M56-0015 | SCOPE OF SUPPLY FOR API CENTRIFUGAL PUMPS - LLI | A | IFQ | TPSK-LSPA1-T-ME-00257 | 2018-10-31 | Transmitted |  | 2018-11-20 | 2018-10-30 | IMP | C | ROC | ME | 2
036909C-1000-SR-0570-0001 | OL1-2M56-0055 | OL1-2M56-0055 | SCOPE OF SUPPLY FOR TRAYS FOR COLUMNS | A | IFQ | TPSK-LSPA1-T-ME-00300 | 2018-11-09 | Transmitted |  | 2018-11-26 | 2018-11-06 | IFR | C | ROC | ME | 2
036909C-1000-SR-0661-0001 | OL1-2M56-0064 | OL1-2M56-0064 | SCOPE OF SUPPLY FOR PLATE AND FRAME HEAT EXCHANGERS | A | IFQ | TPSK-LSPA1-T-ME-00124 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-SR-0662-0002 | OL1-2M56-0066 | OL1-2M56-0066 | SCOPE OF SUPPLY FOR COLD BOX AND CORE EXCHANGERS | A | IFQ | TPSK-LSPA1-T-ME-00125 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-SR-0570-0004 | OL1-2M56-0075 | OL1-2M56-0075 | SCOPE OF SUPPLY FOR MD TRAYS FOR COLUMNS | A | IFQ | TPSK-LSPA1-T-ME-00278 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-10-31 | IFR | H | ROC | ME | 2
036909C-1000-SR-0310-0001 | OL1-2M56-0104 | OL1-2M56-0104 | SCOPE OF SUPPLY FOR COOLING TOWER | A | IFQ | TPSK-LSPA1-T-ME-00276 | 2018-11-06 | Transmitted |  | 2018-11-19 | 2018-10-30 | IFR | C | KLOC | ME | 2
036909C-1000-SR-0845-0001 | OL1-2M56-0108 | OL1-2M56-0108 | SCOPE OF SUPPLY FOR DEAREATOR | A | IFQ | TPSK-LSPA1-T-ME-00270 | 2018-11-06 | Transmitted |  |  | 2018-10-29 | IFQ | C | ROC | ME | 2
036909C-1000-SR-4234-0001 | OL1-2M56-0109 | OL1-2M56-0109 | SCOPE OF SUPPLY FOR SIDE STREAM FILTER PACKAGE | A | IFQ | TPSK-LSPA1-T-ME-00248 | 2018-10-31 | Transmitted |  | 2018-11-16 | 2018-10-29 | IFQ | C | KLOC | ME | 2
036909C-1012-SR-0127-2002 | OL1-2M56-2002 | OL1-2M56-2002 | SCOPE OF SUPPLY FOR FURNACE CONVECTION FITTINGS | A | IFQ | TPSK-LSPA1-T-ME-00207 | 2018-10-22 | Transmitted |  |  | 2018-10-16 | IFQ | C | HOC | ME | 3
036909C-1012-SR-0154-2003 | OL1-2M56-2003 | OL1-2M56-2003 | SCOPE OF SUPPLY FOR QUENCH EXCHANGERS | A | IFQ | TPSK-LSPA1-T-ME-00233 | 2018-10-26 | Transmitted |  |  | 2018-10-18 | IFQ | C | HOC | ME | 3
036909C-1012-SR-0122-2004 | OL1-2M56-2004 | OL1-2M56-2004 | SCOPE OF SUPPLY FOR RADIANT COIL ASSEMBLIES | A | IFQ | TPSK-LSPA1-T-ME-00063 | 2018-09-18 | Transmitted |  |  | 2018-09-10 | IFI | C | HOC | ME | 3
036909C-1012-SR-1040-2005 | OL1-2M56-2005 | OL1-2M56-2005 | SCOPE OF SUPPLY FOR FURNACE ID FANS | A | IFQ | TPSK-LSPA1-T-ME-00269 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1000-SP-1011-0001 | OL1-2M57-0008 | OL1-2M57-0008 | PARTICULAR TECHNICAL SPECIFICATION FOR CENTRIFUGAL COMPRESSORS STEAM TURBINE DRIVEN | A | IFQ | TPSK-LSPA1-T-ME-00136 | 2018-10-08 | R2-Comments as noted | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFQ | C | ROC | ME | 2
036909C-1000-SP-1130-0001 | OL1-2M57-0012 | OL1-2M57-0012 | PARTICULAR TECHNICAL SPECIFICATION FOR RESIDUE GAS EXPANDER/RECOMPRESSOR | A | IFQ | TPSK-LSPA1-T-ME-00139 | 2018-10-09 | R2-Comments as noted | 2018-10-26 | 2018-10-22 | 2018-10-05 | IFQ | C | ROC | ME | 2
036909C-1000-SP-1013-0001 | OL1-2M57-0014 | OL1-2M57-0014 | PARTICULAR TECHNICAL SPECIFICATION FOR INTEGRALLY GEARED DECOKING AIR COMPRESSORS | A | IFQ | TPSK-LSPA1-T-ME-00198 | 2018-10-19 | R1-No comments | 2018-11-07 | 2018-11-02 | 2018-10-18 | IFQ | C | ROC | ME | 2
036909C-1000-SP-0910-0001 | OL1-2M57-0015 | OL1-2M57-0015 | PARTICULAR TECHNICAL SPECIFICATION FOR API CENTRIFUGAL PUMPS - LLI | A | IFQ | TPSK-LSPA1-T-ME-00257 | 2018-10-31 | Transmitted |  | 2018-11-20 | 2018-10-30 | IMP | C | ROC | ME | 2
036909C-1000-SP-0570-0001 | OL1-2M57-0055 | OL1-2M57-0055 | PARTICULAR TECHNICAL SPECIFICATION FOR TRAYS FOR COLUMNS | A | IFQ | TPSK-LSPA1-T-ME-00300 | 2018-11-09 | Transmitted |  | 2018-11-26 | 2018-11-06 | IFR | C | ROC | ME | 2
036909C-1000-SP-0661-0001 | OL1-2M57-0064 | OL1-2M57-0064 | PARTICULAR TECHNICAL SPECIFICATION FOR PLATE AND FRAME HEAT EXCHANGERS | A | IFQ | TPSK-LSPA1-T-ME-00124 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-SP-0662-0002 | OL1-2M57-0066 | OL1-2M57-0066 | PARTICULAR TECHNICAL SPECIFICATION FOR COLD BOX AND CORE EXCHANGERS | A | IFQ | TPSK-LSPA1-T-ME-00125 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-SP-0570-0004 | OL1-2M57-0075 | OL1-2M57-0075 | PARTICULAR TECHNICAL SPECIFICATION FOR MD TRAYS FOR COLUMNS | A | IFQ | TPSK-LSPA1-T-ME-00278 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-10-31 | IFR | H | ROC | ME | 2
036909C-1000-SP-0310-0001 | OL1-2M57-0104 | OL1-2M57-0104 | PARTICULAR TECHNICAL SPECIFICATION FOR COOLING TOWER | A | IFQ | TPSK-LSPA1-T-ME-00276 | 2018-11-06 | Transmitted |  | 2018-11-19 | 2018-10-30 | IFR | C | KLOC | ME | 2
036909C-1000-SP-0845-0001 | OL1-2M57-0108 | OL1-2M57-0108 | PARTICULAR TECHNICAL SPECIFICATION FOR DEAERATOR | A | IFQ | TPSK-LSPA1-T-ME-00270 | 2018-11-06 | Transmitted |  |  | 2018-10-29 | IFQ | C | ROC | ME | 2
036909C-1000-SP-4234-0001 | OL1-2M57-0109 | OL1-2M57-0109 | PARTICULAR TECHNICAL SPECIFICATION FOR SIDE STEAM FILTER PACKAGE | A | IFQ | TPSK-LSPA1-T-ME-00248 | 2018-10-31 | Transmitted |  | 2018-11-16 | 2018-10-29 | IFQ | C | KLOC | ME | 2
036909C-1012-SP-0127-2002 | OL1-2M57-2002 | OL1-2M57-2002 | PARTICULAR TECHNICAL SPECIFICATION FOR FURNACE CONVECTION FITTINGS | A | IFQ | TPSK-LSPA1-T-ME-00207 | 2018-10-22 | Transmitted |  |  | 2018-10-16 | IFQ | C | HOC | ME | 3
036909C-1012-SP-0154-2003 | OL1-2M57-2003 | OL1-2M57-2003 | PARTICULAR TECHANICAL SPECIFICATION FOR QUENCH EXCHANGERS | A | IFQ | TPSK-LSPA1-T-ME-00233 | 2018-10-26 | Transmitted |  |  | 2018-10-18 | IFQ | C | HOC | ME | 3
036909C-1012-SP-0122-2004 | OL1-2M57-2004 | OL1-2M57-2004 | PARTICULAR TECHNICAL SPECIFICATION FOR RADIANT COIL ASSEMBLIES | A | IFI | TPSK-LSPA1-T-ME-00063 | 2018-09-18 | Transmitted |  |  | 2018-09-10 | IFI | C | HOC | ME | 3
036909C-1012-SP-1040-2005 | OL1-2M57-2005 | OL1-2M57-2005 | PARTICULAR TECHNICAL SPECIFICATION FOR FURNACE ID FANS | A | IFQ | TPSK-LSPA1-T-ME-00269 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1000-DL-1011-0001 | OL1-2M58-0008 | OL1-2M58-0008 | DEVIATION LIST FOR CENTRIFUGAL COMPRESSORS STEAM TURBINE DRIVEN | A | IFQ | TPSK-LSPA1-T-ME-00136 | 2018-10-08 | R1-No comments | 2018-10-26 | 2018-10-22 | 2018-10-04 | IFQ | C | ROC | ME | 2
036909C-1000-DL-1130-0001 | OL1-2M58-0012 | OL1-2M58-0012 | DEVIATION LIST FOR RESIDUE GAS EXPANDER/RECOMPRESSOR | A | IFQ | TPSK-LSPA1-T-ME-00139 | 2018-10-09 | R1-No comments | 2018-10-26 | 2018-10-22 | 2018-10-05 | IFQ | C | ROC | ME | 2
036909C-1000-DL-1013-0001 | OL1-2M58-0014 | OL1-2M58-0014 | DEVIATION LIST FOR INTEGRALLY GEARED DECOKING AIR COMPRESSORS | A | IFQ | TPSK-LSPA1-T-ME-00198 | 2018-10-19 | R1-No comments | 2018-11-07 | 2018-11-02 | 2018-10-18 | IFQ | C | ROC | ME | 2
036909C-1000-DL-0910-0001 | OL1-2M58-0015 | OL1-2M58-0015 | DEVIATION LIST FOR API CENTRIFUGAL PUMPS - LLI | A | IFQ | TPSK-LSPA1-T-ME-00257 | 2018-10-31 | Transmitted |  | 2018-11-20 | 2018-10-30 | IMP | C | ROC | ME | 2
036909C-1000-DL-0570-0001 | OL1-2M58-0055 | OL1-2M58-0055 | DEVIATION LIST FOR TRAYS FOR COLUMN | A | IFQ | TPSK-LSPA1-T-ME-00300 | 2018-11-09 | Transmitted |  | 2018-11-26 | 2018-11-06 | IFR | C | ROC | ME | 2
036909C-1000-DL-0661-0001 | OL1-2M58-0064 | OL1-2M58-0064 | DEVIATION LIST FOR PLATE AND FRAME HEAT EXCHANGERS | A | IFQ | TPSK-LSPA1-T-ME-00124 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-DL-0662-0002 | OL1-2M58-0066 | OL1-2M58-0066 | DEVIATION LIST FOR COLD BOX AND CORE EXCHANGERS | A | IFQ | TPSK-LSPA1-T-ME-00125 | 2018-10-03 | Transmitted | 2018-10-24 | 2018-10-17 | 2018-10-01 | IFR | C | ROC | ME | 2
036909C-1000-DL-0570-0004 | OL1-2M58-0075 | OL1-2M58-0075 | DEVIATION LIST FOR MD TRAYS FOR COLUMNS | A | IFQ | TPSK-LSPA1-T-ME-00278 | 2018-11-07 | Transmitted |  | 2018-11-21 | 2018-10-31 | IFR | H | ROC | ME | 2
036909C-1000-DL-0310-0001 | OL1-2M58-0104 | OL1-2M58-0104 | DEVIATION LIST | A | IFQ | TPSK-LSPA1-T-ME-00276 | 2018-11-06 | Transmitted |  | 2018-11-19 | 2018-10-30 | IFR | C | KLOC | ME | 2
036909C-1000-DL-0845-0001 | OL1-2M58-0108 | OL1-2M58-0108 | DEVIATION LIST FOR DEAERATOR | A | IFQ | TPSK-LSPA1-T-ME-00270 | 2018-11-06 | Transmitted |  |  | 2018-10-29 | IFQ | C | ROC | ME | 2
036909C-1000-DL-4234-0001 | OL1-2M58-0109 | OL1-2M58-0109 | DEVIATION LIST FOR SIDE STREAM FILTER PACKAGE | A | IFQ | TPSK-LSPA1-T-ME-00248 | 2018-10-31 | Transmitted |  | 2018-11-16 | 2018-10-29 | IFQ | C | KLOC | ME | 2
036909C-1012-DL-1040-2005 | OL1-2M58-2005 | OL1-2M58-2005 | DEVIATION LIST FOR FURNACE ID FANS | A | IFQ | TPSK-LSPA1-T-ME-00269 | 2018-11-05 | Transmitted |  |  | 2018-11-01 | IFQ | C | HOC | ME | 3
036909C-1000-ITP-4234-0001 | OL1-2M7-0109 | OL1-2M7-0109 | INSPECTION TEST PLAN FOR SIDE STREAM FILTER PACKAGE | A | IFQ | TPSK-LSPA1-T-ME-00248 | 2018-10-31 | Transmitted |  | 2018-11-16 | 2018-10-29 | IFQ | C | KLOC | ME | 2
036909C-1006-JSS-0117-1001 | OL1-2M91-1001 | OL1-2M91-1001 | APPROVED VENDOR LIST FOR 36M AND 132U FURNACE | 0 | IMP | TPSK-LSPA1-T-ME-00211 | 2018-10-23 | Transmitted |  |  | 2018-10-18 | IMP | C | HOC | ME | 3
036909C-1012-JSS-0125-2003 | OL1-2M92-2003 | OL1-2M92-2003 | PROJECT SPECIFICATION FOR CAST INTERMEDIATE TUBE SUPPORTS | 0 | IFI | TPSK-LSPA1-T-ME-00232 | 2018-10-26 | Transmitted |  |  | 2018-10-15 | IFI | C | HOC | ME | 3
036909C-1012-JSS-0191-2009 | OL1-2M92-2009 | OL1-2M92-2009 | PROJECT SPECIFICATION FOR FURNACE BURNERS | A | IFR | TPSK-LSPA1-T-PE-00231 | 2018-10-25 | R1-No comments | 2018-11-14 | 2018-11-08 | 2018-10-15 | IFR | C | HOC | ME | 2
036909C-1000-PP-908 | OL1-2O92-0001 | OL1-2O92-0001 | INSTRUCTIONS TO SUPPLIER FOR FILLING-UP OF SPARE PARTS AND INTERCHANGEABILITY RECORD (SPIR FORM) | A | IFR | TPSK-LSPA1-T-PE-00095 | 2018-09-27 | Transmitted |  | 2018-10-11 | 2018-09-24 | IFR | C | ROC | PE | 2
036909C-1000-STD-1380-0001 | OL1-2P92-0002 | OL1-2P92-0002 | PIPING DESIGN STANDARD DRAWINGS | A | IFR | TPSK-LSPA1-T-MP-00012 | 2018-08-08 | A4-Not Approved, re-submit for approval | 2018-09-26 | 2018-08-22 | 2018-08-07 | IFR | H | ROC | MP | 2
036909C-1000-STC-1390-0001 | OL1-2P92-0003 | OL1-2P92-0003 | PIPING CONSTRUCTION DRAWING | A | IFR | TPSK-LSPA1-T-MP-00012 | 2018-08-08 | A4-Not Approved, re-submit for approval | 2018-09-26 | 2018-08-22 | 2018-08-07 | IFR | H | ROC | MP | 2
036909C-1000-PP-500 | OL1-2Q92-0001 | OL1-2Q92-0001 | OVERALL PROJECT QUALITY PLAN | A | IFR | TPSK-LSPA1-T-QM-00072 | 2018-09-24 | R2-Comments as noted | 2018-10-12 | 2018-10-05 | 2018-09-17 | IFR | C | ROC | QM | 2
036909C-1000-PP-502 | OL1-2Q92-0002 | OL1-2Q92-0002 | CONFIDENTIALITY PLAN | A | IFR | TPSK-LSPA1-T-QM-00199 | 2018-10-19 | Transmitted |  | 2018-11-02 | 2018-10-18 | IFR | C | JVD | QM | 2
036909C-1000-JSD-1400-0001 | OL1-2R02-0001 | OL1-2R02-0001 | JOB DESIGN SPECIFICATION FOR UNDERGROUND SYSTEMS | A | IFR | TPSK-LSPA1-T-CV-00087 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-18 | IFR | C | ROC | CV | 2
036909C-1000-JSD-1700-0001 | OL1-2R02-0004 | OL1-2R02-0004 | JOB DESIGN SPECIFICATION FOR FOUNDATIONS AND STRUCTURES | A | IFR | TPSK-LSPA1-T-CV-00087 | 2018-09-25 | R1-No comments | 2018-11-02 | 2018-10-09 | 2018-09-19 | IFR | C | ROC | CV | 2
036909C-1000-JSD-2000-0001 | OL1-2R02-0005 | OL1-2R02-0005 | BUILDINGS DESIGN AND CONSTRUCTION | A | IFR | TPSK-LSPA1-T-CV-00158 | 2018-10-11 | Transmitted |  | 2018-10-25 | 2018-10-10 | IFR | C | ROC | CV | 2
036909C-1000-JSS-6300-02 | OL1-2R03-0001 | OL1-2R03-0001 | JO B SPECIFICATION FOR WELDINGS AND NDE OF PRESSURE VESSELS AND HEAT EXCHANGERS | A | IFR | TPSK-LSPA1-T-ME-00029 | 2018-08-27 | A4-Not Approved, re-submit for approval | 2018-09-19 | 2018-09-10 | 2018-08-24 | IFR | C | ROC | MP | 2
036909C-1000-JSS-6300-03 | OL1-2R03-0002 | OL1-2R03-0002 | JOB SPECIFICATION FOR MATERIALS IN SOUR SERVICES | A | IFR | TPSK-LSPA1-T-ME-00029 | 2018-08-27 | R1-No comments | 2018-09-19 | 2018-09-10 | 2018-08-24 | IFR | C | ROC | MP | 2
036909C-1000-JSS-6300-04 | OL1-2R03-0003 | OL1-2R03-0003 | JOB SPECIFICATION FOR SUPPLY POSITIVE ALLOY MATERIAL IDENTIFICATION OF EQUIPMENT AND PIPING | A | IFR | TPSK-LSPA1-T-ME-00029 | 2018-08-27 | R1-No comments | 2018-09-19 | 2018-09-10 | 2018-08-24 | IFR | C | ROC | MP | 2
036909C-1000-JSS-6300-05 | OL1-2R03-0004 | OL1-2R03-0004 | JOB SPECIFICATION FOR WELDING AND NDE STORAGE TANKS | A | IFR | TPSK-LSPA1-T-ME-00029 | 2018-08-27 | R1-No comments | 2018-09-19 | 2018-09-10 | 2018-08-24 | IFR | C | ROC | MP | 2
036909C-1006-JSS-0117-0005 | OL1-2R03-0005 | OL1-2R03-0005 | ME-005 DOUBLE JACKET PIPE HEAT EXCHANGERS FOR 36M AND 132U FURNACE | 0 | IMP | TPSK-LSPA1-T-ME-00212 | 2018-10-23 | Transmitted |  |  | 2018-10-18 | IMP | C | HOC | ME | 3
036909C-1000-JSS-0660-01 | OL1-2R03-0006 | OL1-2R03-0006 | PLATE HEAT EXCHANGER | 0 | IMP | TPSK-LSPA1-T-ME-00042 | 2018-09-12 | Transmitted |  |  | 2018-09-10 | IFI | C | ROC | ME | 3
036909C-1000-JSS-0910-0001 | OL1-2R03-0010 | OL1-2R03-0010 | ME-010 CENTRIFUGAL PUMP | A | IFR | TPSK-LSPA1-T-ME-00078 | 2018-09-24 | R1-No comments | 2018-10-12 | 2018-10-08 | 2018-09-20 | IFR | C | ROC | ME | 2
036909C-1000-JSS-1140-0001 | OL1-2R03-0013 | OL1-2R03-0013 | ME-013 DIESEL ENGINE | A | IFR | TPSK-LSPA1-T-ME-00196 | 2018-10-18 | R1-No comments | 2018-11-02 | 2018-11-06 | 2018-10-22 | IFR | C | ROC | ME | 2
036909C-1000-JSS-1011-0001 | OL1-2R03-0014 | OL1-2R03-0014 | ME-014 CENTRIFUGAL COMPRESSOR | A | IFR | TPSK-LSPA1-T-ME-00065 | 2018-09-18 | R1-No comments | 2018-10-10 | 2018-10-03 | 2018-09-18 | IFR | C | ROC | ME | 2
036909C-1000-JSS-1013-0001 | OL1-2R03-0016 | OL1-2R03-0016 | ME-016 CENTRIFUGAL COMPRESSOR FOR PA/IA SERVISE | A | IFR | TPSK-LSPA1-T-ME-00164 | 2018-10-12 | R1-No comments | 2018-11-07 | 2018-10-26 | 2018-10-09 | IFR | C | ROC | ME | 2
036909C-1000-JSS-1111-0001 | OL1-2R03-0018 | OL1-2R03-0018 | ME-018 GENERAL PURPOSE STEAM TURBINES | A | IFR | TPSK-LSPA1-T-ME-00078 | 2018-09-24 | R1-No comments | 2018-10-12 | 2018-10-08 | 2018-09-20 | IFR | C | ROC | ME | 2
036909C-1000-JSS-1061-0001 | OL1-2R03-0019 | OL1-2R03-0019 | ME-019 LUBE OIL UNIT AND SEAL OIL SYSTEM | A | IFR | TPSK-LSPA1-T-ME-00065 | 2018-09-18 | R1-No comments | 2018-10-10 | 2018-10-03 | 2018-09-18 | IFR | C | ROC | ME | 2
036909C-1000-JSS-1112-0001 | OL1-2R03-0020 | OL1-2R03-0020 | ME-020 SPECIAL PURPOSE STEAM TTURBINES | A | IFR | TPSK-LSPA1-T-ME-00078 | 2018-09-24 | R1-No comments | 2018-10-12 | 2018-10-08 | 2018-09-20 | IFR | C | ROC | ME | 2
036909C-1000-JSS-1160-0001 | OL1-2R03-0022 | OL1-2R03-0022 | ME-022 SPECIAL PURPOSE GEAR | A | IFR | TPSK-LSPA1-T-ME-00166 | 2018-10-12 | R1-No comments | 2018-11-07 | 2018-10-26 | 2018-10-12 | IFR | C | ROC | ME | 2
036909C-1000-JSS-0900-0001 | OL1-2R03-0028 | OL1-2R03-0028 | ME-028 MECHANICAL SEAL | 0 | IMP | TPSK-LSPA1-T-ME-00057 | 2018-09-17 | Transmitted |  |  | 2018-09-14 | IFI | C | ROC | ME | 3
036909C-1006-JSS-0117-0029 | OL1-2R03-0029 | OL1-2R03-0029 | ME-029 CENTRIFUGAL BLOWER FOR 36M AND 132U FURNACE | 0 | IMP | TPSK-LSPA1-T-ME-00185 | 2018-10-17 | R1-No comments | 2018-11-05 | 2018-10-31 | 2018-10-16 | IMP | C | HOC | ME | 3
036909C-1000-JSD-0400-01 | OL1-2R03-0050 | OL1-2R03-0050 | JOB SPECIFICATION FOR DESIGN OF PRESSURE & ATMOSPHERIC STATIC EQUIPMENT | A | IFR | TPSK-LSPA1-T-ME-00017 | 2018-08-10 | A3-Approved with comments, re-submit for review. | 2018-08-27 | 2018-08-24 | 2018-08-09 | IFR | H | ROC | ME | 2
036909C-1000-JSD-0400-01 | OL1-2R03-0050 | OL1-2R03-0050 | JOB SPECIFICATION FOR DESIGN OF PRESSURE & ATMOSPHERIC STATIC EQUIPMENT | B | IFR | TPSK-LSPA1-T-ME-00084 | 2018-09-25 | R1-No comments | 2018-10-24 | 2018-10-09 | 2018-09-20 | IFR | H | ROC | ME | 2
036909C-1000-JSD-0400-01 | OL1-2R03-0050 | OL1-2R03-0050 | JOB SPECIFICATION FOR DESIGN OF PRESSURE & ATMOSPHERIC STATIC EQUIPMENT | 0 | IMP | TPSK-LSPA1-T-ME-00245 | 2018-10-31 | Transmitted |  |  | 2018-10-26 | IMP | C | ROC | ME | 2
036909C-1000-JSS-0400-01 | OL1-2R03-0051 | OL1-2R03-0051 | JOB SPECIFICATION FOR SUPPLY OF PRESSURE VESSELS | A | IFR | TPSK-LSPA1-T-ME-00021 | 2018-08-13 | A4-Not Approved, re-submit for approval | 2018-08-27 | 2018-08-27 | 2018-08-10 | IFR | H | ROC | ME | 2
036909C-1000-JSS-0400-01 | OL1-2R03-0051 | OL1-2R03-0051 | JOB SPECIFICATION FOR SUPPLY OF PRESSURE VESSELS | B | IFR | TPSK-LSPA1-T-ME-00084 | 2018-09-25 | R1-No comments | 2018-10-24 | 2018-10-09 | 2018-09-20 | IFR | H | ROC | ME | 2
036909C-1000-JSS-0400-01 | OL1-2R03-0051 | OL1-2R03-0051 | JOB SPECIFICATION FOR SUPPLY OF PRESSURE VESSELS | 0 | IMP | TPSK-LSPA1-T-ME-00249 | 2018-10-31 | Transmitted |  |  | 2018-10-26 | IMP | C | ROC | ME | 2
036909C-1000-JSS-0570-01 | OL1-2R03-0052 | OL1-2R03-0052 | JOB SPECIFICATION FOR SUPPLY OF COLUMN INTERNALS | A | IFR | TPSK-LSPA1-T-ME-00017 | 2018-08-10 | A3-Approved with comments, re-submit for review. | 2018-08-27 | 2018-08-24 | 2018-08-09 | IFR | H | ROC | ME | 2
036909C-1000-JSS-0570-01 | OL1-2R03-0052 | OL1-2R03-0052 | JOB SPECIFICATION FOR SUPPLY OF COLUMN INTERNALS | 0 | IMP | TPSK-LSPA1-T-ME-00081 | 2018-09-24 | Transmitted | 2018-10-24 |  | 2018-09-20 | IFI | C | ROC | ME | 3
036909C-1000-JSS-1820-01 | OL1-2R03-0053 | OL1-2R03-0053 | JOB SPECIFICATION FOR SUPPLY OF EQUIPMENT LADDERS AND PLATFORMS | A | IFR | TPSK-LSPA1-T-ME-00017 | 2018-08-10 | A4-Not Approved, re-submit for approval | 2018-08-27 | 2018-08-24 | 2018-08-09 | IFR | H | ROC | ME | 2
036909C-1000-JSS-1820-01 | OL1-2R03-0053 | OL1-2R03-0053 | JOB SPECIFICATION FOR SUPPLY OF EQUIPMENT LADDERS AND PLATFORMS | 0 | IFR | TPSK-LSPA1-T-ME-00081 | 2018-09-24 | Transmitted | 2018-10-24 |  | 2018-09-20 | IFI | C | ROC | ME | 3
036909C-1000-STC-0490-000 | OL1-2R03-0054 | OL1-2R03-0054 | CONSTRUCTION STANDARDS FOR PRESSURE EQUIPMENT | A | IFR | TPSK-LSPA1-T-ME-00018 | 2018-08-10 | A3-Approved with comments, re-submit for review. | 2018-08-27 | 2018-08-24 | 2018-08-10 | IFR | H | ROC | ME | 2
036909C-1000-STC-0490-000 | OL1-2R03-0054 | OL1-2R03-0054 | CONSTRUCTION STANDARDS FOR PRESSURE EQUIPMENT | B | IFR | TPSK-LSPA1-T-ME-00084 | 2018-09-25 | R1-No comments | 2018-10-24 | 2018-10-09 | 2018-09-20 | IFR | H | ROC | ME | 2
036909C-1000-STC-0490-000 | OL1-2R03-0054 | OL1-2R03-0054 | CONSTRUCTION STANDARDS FOR PRESSURE EQUIPMENT | 0 | IMP | TPSK-LSPA1-T-ME-00256 | 2018-10-31 | Transmitted |  |  | 2018-10-26 | IMP | C | ROC | ME | 2
036909C-1000-STC-1890-080 | OL1-2R03-0055 | OL1-2R03-0055 | CONSTRUCTION STANDARDS FOR LADDERS & PLATFORMS ATTACHED TO PRESSURE EQUIPMENT | 0 | IMP | TPSK-LSPA1-T-ME-00120 | 2018-10-03 | Transmitted | 2018-10-24 |  | 2018-10-01 | IFI | C | ROC | ME | 3
036909C-1000-JSS-0400-02 | OL1-2R03-0102 | OL1-2R03-0102 | MARKING FOR VESSEL & HEAT EXCHANGER | 0 | IMP | TPSK-LSPA1-T-ME-00042 | 2018-09-12 | Transmitted |  |  | 2018-09-10 | IFI | C | ROC | ME | 3
036909C-1000-JSS-0310-0001 | OL1-2R03-0104 | OL1-2R03-0104 | ME-008 COOLING WATER | A | IFQ | TPSK-LSPA1-T-ME-00276 | 2018-11-06 | Transmitted |  | 2018-11-19 | 2018-10-30 | IFR | C | KLOC | ME | 2
036909C-1000-JSS-0910-0002 | OL1-2R03-0500 | OL1-2R03-0500 | ME-050 CENTRIFUGAL PUMP (NON API) | A | IFR | TPSK-LSPA1-T-ME-00308 | 2018-11-12 | Transmitted |  | 2018-11-27 | 2018-10-25 | IFR | C | ROC | ME | 2
036909C-1000-STC-1890-080 | OL1-2R03-055 | OL1-2R03-055 | CONSTRUCTION STANDARDS FOR LADDERS AND PLATFORMS ATTACHED TO PRESSURE EQUIPMENT | A | IFR | TPSK-LSPA1-T-ME-00027 | 2018-08-27 | R2-Comments as noted | 2018-09-18 | 2018-09-10 | 2018-08-23 | IFR | H | ROC | ME | 2
036909C-1006-JSS-0117-3001 | OL1-2R03-1001 | OL1-2R03-1001 | ME-001 PRESSURE VESSEL FOR 36M AND 132U FURNACE | 0 | IFE | TPSK-LSPA1-T-ME-00262 | 2018-11-07 | Transmitted |  |  | 2018-10-18 | IMP | C | HOC | ME | 3
036909C-1006-JSS-0117-3004 | OL1-2R03-1004 | OL1-2R03-1004 | ME-004 SHELL AND TUBE HEAT EXCHANGERS FOR 36M AND 132U FURNACE | 0 | IFI | TPSK-LSPA1-T-ME-00221 | 2018-10-24 | Transmitted |  |  | 2018-10-18 | IMP | C | HOC | ME | 3
036909C-1000-JSD-1300-0002 | OL1-2R04-0002 | OL1-2R04-0002 | PIPING DESIGN SPECIFICATION | A | IFR | TPSK-LSPA1-T-MP-00012 | 2018-08-08 | A4-Not Approved, re-submit for approval | 2018-09-26 | 2018-08-22 | 2018-08-07 | IFR | H | ROC | MP | 2
036909C-1000-JSD-1300-0002 | OL1-2R04-0002 | OL1-2R04-0002 | JOB SPECIFICATION FOR DETAIL DESIGN PIPING | B | IFR | TPSK-LSPA1-T-MP-00012 | 2018-11-16 | Transmitted |  | 2018-12-03 | 2018-11-12 | IFR | C | ROC | ROC Piping | 2
036909C-1000-JSD-2200-01 | OL1-2R04-0003 | OL1-2R04-0003 | JOB DESIGN SPECIFICATION FOR THERMAL INSULATION (HOT SERVICE) | A | IFR | TPSK-LSPA1-T-MP-00024 | 2018-08-22 | A4-Not Approved, re-submit for approval | 2018-09-12 | 2018-09-05 | 2018-08-22 | IFR | C | ROC | MP | 2
036909C-1000-JSD-2200-02 | OL1-2R04-0004 | OL1-2R04-0004 | JOB DESIGN SPECIFICATION FOR THERMAL INSULATION (COLD SERVICE) | A | IFR | TPSK-LSPA1-T-MP-00024 | 2018-08-22 | A4-Not Approved, re-submit for approval | 2018-09-12 | 2018-09-05 | 2018-08-22 | IFR | C | ROC | MP | 2
036909C-1000-JSD-2300-01 | OL1-2R04-0005 | OL1-2R04-0005 | JOB DESIGN SPECIFICATION FOR PAINTING | A | IFR | TPSK-LSPA1-T-MP-00024 | 2018-08-22 | A4-Not Approved, re-submit for approval | 2018-09-12 | 2018-09-05 | 2018-08-22 | IFR | C | ROC | MP | 2
036909C-1000-JSS-1300-01 | OL1-2R04-0006 | OL1-2R04-0006 | GENERAL SUPPLY SPECIFICATION FOR PIPING MATERIAL | A | IFR | TPSK-LSPA1-T-MP-00028 | 2018-08-27 | R2-Comments as noted | 2018-09-18 | 2018-09-10 | 2018-08-22 | IFR | C | ROC | MP | 2
036909C-1006-JSS-0117-0007 | OL1-2R04-0007 | OL1-2R04-0007 | PIP-007 MARKING OF PIPING MATERIAL FOR 36M AND 132U FURNACE | 0 | IMP | TPSK-LSPA1-T-ME-00213 | 2018-10-23 | Transmitted |  |  | 2018-10-18 | IMP | C | HOC | ME | 3
036909C-1000-JSS-1320-01 | OL1-2R04-0011 | OL1-2R04-0011 | JOB SUPPLY SPECIFICATION FOR PIPES | A | IFR | TPSK-LSPA1-T-MP-00028 | 2018-08-27 | R2-Comments as noted | 2018-09-18 | 2018-09-10 | 2018-08-22 | IFR | C | ROC | MP | 2
036909C-1000-JSS-1330-01 | OL1-2R04-0013 | OL1-2R04-0013 | JOB SUPPLY SPECIFICATION FOR BUTT WELDING FITTINGS | A | IFR | TPSK-LSPA1-T-MP-00028 | 2018-08-27 | A4-Not Approved, re-submit for approval | 2018-09-18 | 2018-09-10 | 2018-08-22 | IFR | C | ROC | MP | 2
036909C-1000-JSS-1340-01 | OL1-2R04-0014 | OL1-2R04-0014 | JOB SUPPLY SPECIFICATION FOR FORGED FITTINGS | A | IFR | TPSK-LSPA1-T-MP-00028 | 2018-08-27 | A4-Not Approved, re-submit for approval | 2018-09-18 | 2018-09-10 | 2018-08-22 | IFR | C | ROC | MP | 2
036909C-1000-JSS-1350-01 | OL1-2R04-0015 | OL1-2R04-0015 | JOB SUPPLY SPECIFICATION FOR FLANGES | A | IFR | TPSK-LSPA1-T-MP-00028 | 2018-08-27 | A4-Not Approved, re-submit for approval | 2018-09-18 | 2018-09-10 | 2018-08-24 | IFR | C | ROC | MP | 2
036909C-1000-JSD-1300-0003 | OL1-2R04-0031 | OL1-2R04-0031 | JOB DESIGN SPECIFICATION FOR STEAM TRACING | A | IFR | TPSK-LSPA1-T-MP-00012 | 2018-08-08 | A4-Not Approved, re-submit for approval | 2018-09-26 | 2018-08-22 | 2018-08-07 | IFR | H | ROC | MP | 2
036909C-1006-JSS-0117-1004 | OL1-2R04-1004 | OL1-2R04-1004 | PIP-004 PIPING WELDING SPECIFICATION FOR 36M AND 132U FURNACE | 0 | IMP | TPSK-LSPA1-T-ME-00184 | 2018-10-16 | Transmitted |  |  | 2018-10-15 | IFE | C | HOC | ME | 3
036909C-1000-JSS-1641-0001 | OL1-2R05-0003 | OL1-2R05-0003 | OIL FILLED DISTRIBUTION TRANSFORMER | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1652-0001 | OL1-2R05-0006 | OL1-2R05-0006 | MEDIUM VOLTAGE SWITCHGEAR | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1657-0001 | OL1-2R05-0007 | OL1-2R05-0007 | LOW VOLTAGE DISTRIBUTION PANEL | 0 | IMP | TPSK-LSPA1-T-EE-00309 | 2018-11-12 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1654-0001 | OL1-2R05-0008 | OL1-2R05-0008 | LOW VOLTAGE SWITCHGEAR AND MOTOR CONTROL CENTER | 0 | IFE | TPSK-LSPA1-T-EE-00309 | 2018-11-12 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1691-0001 | OL1-2R05-0010 | OL1-2R05-0010 | ELECTRICAL MOTOS UP TO 300 KW | 0 | IMP | TPSK-LSPA1-T-EE-00079 | 2018-09-24 | Transmitted |  |  | 2018-09-20 | IFI | C | ROC | EE | 3
036909C-1000-JSS-1692-0001 | OL1-2R05-0011 | OL1-2R05-0011 | ELECTRICAL MOTORS GREATER THAN 300 KW | 0 | IMP | TPSK-LSPA1-T-EE-00293 | 2018-11-08 | Transmitted |  |  | 2018-09-20 | IFI | C | ROC | EE | 3
036909C-1000-JSS-1671-0001 | OL1-2R05-0012 | OL1-2R05-0012 | UNINTERRUPTIBLE POWER SUPPLIES | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSD-1600-0004 | OL1-2R05-0014 | OL1-2R05-0014 | LIGHTING SYSTEM | 0 | IMP | TPSK-LSPA1-T-EE-00258 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSD-1600-0010 | OL1-2R05-0015 | OL1-2R05-0015 | EARTHING AND LIGHTNING PROTECTION | 0 | IMP | TPSK-LSPA1-T-EE-00258 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1684-0001 | OL1-2R05-0016 | OL1-2R05-0016 | CATHODIC PROTECTION | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-4123-0001 | OL1-2R05-0017 | OL1-2R05-0017 | DIESEL ENGINE GENERATOR | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1656-0001 | OL1-2R05-0021 | OL1-2R05-0021 | POWER CAPACITORS | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1622-0001 | OL1-2R05-0022 | OL1-2R05-0022 | MISCELLANEOUS EQUIPMENT | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1693-0001 | OL1-2R05-0023 | OL1-2R05-0023 | LOW VOLTAGE VARIABLE VOLTAGE VARIABLE FREQUENCY SYSTEM | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSD-1600-0007 | OL1-2R05-0029 | OL1-2R05-0029 | FUNCTIONAL AND SCHEMATIC DIAGRAM | 0 | IMP | TPSK-LSPA1-T-EE-00258 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1682-0001 | OL1-2R05-0037 | OL1-2R05-0037 | ELECTRICAL HEAT TRACING | 0 | IMP | TPSK-LSPA1-T-EE-00079 | 2018-09-24 | Transmitted |  |  | 2018-09-20 | IFI | C | ROC | EE | 3
036909C-1000-JSS-1655-0001 | OL1-2R05-0038 | OL1-2R05-0038 | LOW VOLTAGE BUS DUCT | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSS-1694-0001 | OL1-2R05-0040 | OL1-2R05-0040 | MEDIUM VOLTAGE VARIABLE VOLTAGE VARIABLE FREQUENCY SYSTEM | 0 | IMP | TPSK-LSPA1-T-EE-00268 | 2018-11-05 | Transmitted |  |  | 2018-09-20 | IMP | C | ROC | EE | 3
036909C-1000-JSD-1600-003 | OL1-2R05-0042 | OL1-2R05-0042 | GENERAL DESIGN RULE FOR PACKAGE EQUIPMENT ELECTRICAL SYSTEM | A | IFR | TPSK-LSPA1-T-EE-00008 | 2018-08-06 | A3-Approved with comments, re-submit for review. | 2018-08-24 | 2018-08-20 | 2018-08-03 | IFR | H | ROC | EE | 2
036909C-1000-JSD-1600-008 | OL1-2R05-0043 | OL1-2R05-0043 | GENERAL DESIGN RULE FOR SMARTPLANT ELECTRICAL | A | IFR | TPSK-LSPA1-T-EE-00008 | 2018-08-06 | A3-Approved with comments, re-submit for review. | 2018-08-24 | 2018-08-20 | 2018-08-03 | IFR | C | ROC | EE | 3
036909C-1000-PP-1600-001 | OL1-2R05-0044 | OL1-2R05-0044 | COORDINATION PROCEDURE FOR SMARTPLANT ELECTRICAL | A | IFR | TPSK-LSPA1-T-EE-00008 | 2018-08-06 | A3-Approved with comments, re-submit for review. | 2018-08-24 | 2018-08-20 | 2018-08-03 | IFR | C | ROC | EE | 3
036909C-1000-PP-1600-003 | OL1-2R05-0045 | OL1-2R05-0045 | COORDINATION PROCEDURE FOR ETAP | A | IFI | TPSK-LSPA1-T-EE-00008 | 2018-08-06 | A3-Approved with comments, re-submit for review. | 2018-08-24 | 2018-08-20 | 2018-08-03 | IFR | C | ROC | EE | 3
036909C-1000-JSD-1540-0001 | OL1-2R06-0001 | OL1-2R06-0001 | INSTRUMENT GENERAL DESIGN | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1547-0001 | OL1-2R06-0003 | OL1-2R06-0003 | FLOW MEASUREMENT | 0 | IMP | TPSK-LSPA1-T-IE-00122 | 2018-10-03 | Transmitted |  |  | 2018-09-28 | IFI | C | ROC | IE | 3
036909C-1000-JSD-1552-0001 | OL1-2R06-0005 | OL1-2R06-0005 | LEVEL MEASUREMENT | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1553-0001 | OL1-2R06-0006 | OL1-2R06-0006 | PRESSURE MEASUREMENT | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1554-0001 | OL1-2R06-0007 | OL1-2R06-0007 | TEMPERATURE MEASUREMENT | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1541-0001 | OL1-2R06-0008 | OL1-2R06-0008 | FINAL CONTROL ELEMENT | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1572-0001 | OL1-2R06-0010 | OL1-2R06-0010 | INSTRUMENT CONSTRUCTION MATERIAL | 0 | IMP | TPSK-LSPA1-T-IE-00122 | 2018-10-03 | Transmitted |  |  | 2018-09-28 | IFI | C | ROC | IE | 3
036909C-1000-JSD-1515-0004 | OL1-2R06-0013 | OL1-2R06-0013 | MACHINERY MONITORING SYSTEM | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1511-0001 | OL1-2R06-0016 | OL1-2R06-0016 | INSTRUMENT CABINET | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1580-0001 | OL1-2R06-0017 | OL1-2R06-0017 | INTEGRATED TURBINE AND COMPRESSOR CONTROL SYSTEM | A | IFR | TPSK-LSPA1-T-IE-00148 | 2018-10-10 | R1-No comments | 2018-10-24 | 2018-10-24 | 2018-10-08 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1545-0001 | OL1-2R06-0021 | OL1-2R06-0021 | PRESSURE SAFETY VALVE | 0 | IMP | TPSK-LSPA1-T-IE-00122 | 2018-10-03 | Transmitted |  |  | 2018-09-28 | IFI | C | ROC | IE | 3
036909C-1000-JSD-1501-0001 | OL1-2R06-0022 | OL1-2R06-0022 | INSTRUMENT NUMBERING | A | IFR | TPSK-LSPA1-T-PE-00131 | 2018-10-05 | R2-Comments as noted | 2018-10-24 | 2018-10-19 | 2018-10-03 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1501-0003 | OL1-2R06-0023 | OL1-2R06-0023 | INSTRUMENT INSPECTION AND TEST PLAN | 0 | IMP | TPSK-LSPA1-T-IE-00122 | 2018-10-03 | Transmitted |  |  | 2018-09-28 | IFI | C | ROC | IE | 3
036909C-1000-JSD-1501-0002 | OL1-2R06-0024 | OL1-2R06-0024 | GENERAL DESIGN RULES FOR SMARTPLANT INSTRUMENTATION SETUP | A | IFR | TPSK-LSPA1-T-IE-00109 | 2018-09-28 | R2-Comments as noted | 2018-10-09 | 2018-10-11 | 2018-09-27 | IFR | H | ROC | IE | 2
036909C-1000-JSD-1501-0002 | OL1-2R06-0024 | OL1-2R06-0024 | GENERAL DESIGN RULES FOR SMARTPLANT INSTRUMENTATION SETUP | B | IFR | TPSK-LSPA1-T-IE-00291 | 2018-11-08 | Transmitted |  | 2018-11-23 | 2018-10-24 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1580-0003 | OL1-2R06-0035 | OL1-2R06-0035 | GENERAL DESIGN RULES FOR INSTRUMENTATION AND CONTROL OF PACKAGED EQUIPMENT | A | IFR | TPSK-LSPA1-T-IE-00056 | 2018-09-17 | R2-Comments as noted | 2018-10-02 | 2018-10-01 | 2018-09-14 | IFR | C | ROC | IE | 2
036909C-1000-JSD-1580-0002 | OL1-2R06-1301 | OL1-2R06-1301 | PROGAMMABLE LOGIC CONTROLLER | A | IFR | TPSK-LSPA1-T-IE-00291 | 2018-11-08 | Transmitted |  | 2018-11-23 | 2018-11-07 | IFR | C | ROC | IE | 2
036909C-1000-PP-106 | OL1-2R07-0001 | OL1-2R07-0001 | TAGGING PROCEDURE | A | IFR | TPSK-LSPA1-T-PM-00001 | 2018-07-30 | A4 - Not approve | 2018-08-22 | 2018-08-10 | 2018-07-26 | IFR | H | ROC | ME | 2
036909C-1000-PP-106 | OL1-2R07-0001 | OL1-2R07-0001 | TAGGING PROCEDURE | 0 | IMP | TPSK-LSPA1-T-ME-00279 | 2018-11-07 | Transmitted |  |  | 2018-10-29 | IFI | C | ROC | ME | 2
036909C-1000-PP-923 | OL1-2R07-0010 | OL1-2R07-0010 | EQUIPMENT PRESERVATION | 0 | IMP | TPSK-LSPA1-T-PE-00149 | 2018-10-09 | Transmitted |  |  | 2018-10-09 | IMP | C | ROC | ME | 3
036909C-1000-JSD-0001-0002 | OL1-2R07-0018 | OL1-2R07-0018 | UNITS OF MEASUREMENT | 0 | IMP | TPSK-LSPA1-T-ME-00080 | 2018-09-24 | Transmitted | 2018-10-24 |  | 2018-09-20 | IFI | C | ROC | ME | 3
036909C-1000-JSD-1522-0001 | OL1-2R07-0020 | OL1-2R07-0020 | ELECTRICAL AND INSTRUMENT INTERFACE PHILOSOPHY | A | IFR | TPSK-LSPA1-T-IE-00121 | 2018-10-03 | R1-No comments | 2018-10-09 | 2018-10-17 | 2018-09-28 | IFR | C | ROC | IE | 2
036909C-1000-PP-259 | OL1-2R07-0023 | OL1-2R07-0023 | DRAFTING PROCEDURE FOR 2D DRAWINGS | A | IFR | TPSK-LSPA1-T-ME-00089 | 2018-09-25 | R2-Comments as noted | 2018-10-24 | 2018-10-09 | 2018-09-18 | IFR | C | ROC | ME | 2
036909C-1000-PP-261 | OL1-2R07-0025 | OL1-2R07-0025 | REQUIREMENTS FOR EQIPMENT SUPPLIER 3D MODEL | 0 | IMP | TPSK-LSPA1-T-ME-00108 | 2018-09-28 | Transmitted | 2018-10-24 |  | 2018-09-27 | IFI | C | ROC | ME | 3
036909C-1000-JSD-0001 | OL1-2R07-0026 | OL1-2R07-0026 | PROJECT DESIGN BASIS | 0 | IMP | TPSK-LSPA1-T-ME-00110 | 2018-09-28 | Transmitted | 2018-10-24 | 2018-10-11 | 2018-09-26 | IFR | C | ROC | ME | 2
036909C-1000-JSD-1572-0004 | OL1-2R08-0003 | OL1-2R08-0003 | INSTRUMENT INSTALLATION | 0 | IMP | TPSK-LSPA1-T-IE-00122 | 2018-10-03 | Transmitted |  |  | 2018-09-28 | IFI | C | ROC | IE | 3
036909C-1000-PP-551 | OL1-2S92-0001 | OL1-2S92-0001 | PROJECT HSSE PLAN | A | IFR | TPSK-LSPA1-T-ES-00129 | 2018-10-04 | Transmitted |  | 2018-10-18 | 2018-10-02 | IFR | C | ROC | ES | 2
036909C-1000-PP-552 | OL1-2S92-0002 | OL1-2S92-0002 | INCIDENT INVESTIGATION AND REPORTING PROCEDURE | A | IFR | TPSK-LSPA1-T-ES-00152 | 2018-10-10 | Transmitted |  | 2018-10-24 | 2018-10-05 | IFR | C | JVD | ES | 2
036909C-1000-PP-119 | OL1-2V92-0014 | OL1-2V92-0014 | INTERFACE MANAGEMENT PLAN | A | IFR | TPSK-LSPA1-T-IF-00138 | 2018-10-08 | R2-Comments as noted | 2018-10-25 | 2018-10-22 | 2018-09-20 | IFR | C | SK | IF | 2
036909C-1000-PLG-102 | OL1-2W01-0001 | OL1-2W01-0001 | PLANT AND SECTION CODES | A | IFR | TPSK-LSPA1-T-PC-00019 | 2018-08-10 | A2-Approved with comments, re-submit is not required. | 2018-08-22 | 2018-08-24 | 2018-08-10 | IFR | H | ROC | PM | 2
036909C-1000-PLG-102 | OL1-2W01-0001 | OL1-2W01-0001 | PLANT AND SECTION CODES | 0 | IMP | TPSK-LSPA1-T-PC-00076 | 2018-09-24 | Transmitted |  |  | 2018-09-17 | IFI | C | ROC | PC | 3
036909C-1000-PLG-103 | OL1-2W01-0002 | OL1-2W01-0002 | WORK BREAKDOWN STRUCTURE | A | IFR | TPSK-LSPA1-T-PC-00015 | 2018-08-09 | A4 - Not approve | 2018-08-17 | 2018-08-23 | 2018-07-30 | IFR | H | ROC | PC | 2
036909C-1000-PLG-103 | OL1-2W01-0002 | OL1-2W01-0002 | PLANT AND ZONE CODES | B | IFR | TPSK-LSPA1-T-PC-00077 | 2018-09-24 | R2-Comments as noted | 2018-10-17 | 2018-10-08 | 2018-09-17 | IFR | C | ROC | PC | 2
036909C-1000-RT-200 | OL1-2W90-0001 | OL1-2W90-0001 | FIREFIGHTING BASIC DESIGN REPORT FOR PACKAGE A1 | 0 | IFI | TPSK-LSPA1-T-PC-00020 | 2018-08-10 | R2-Comments as noted | 2018-08-20 |  | 2018-08-10 | IFI | H | ROC | PM | 3
036909C-1000-RT-200 | OL1-2W90-0001 | OL1-2W90-0001 | FIRE FIGHTING BASIC DESIGN REPORT FOR PACKAGE A1 | 1 | IFI | TPSK-LSPA1-T-PM-00187 | 2018-10-17 | Transmitted |  |  | 2018-09-28 | IFI | C | ROC | PC | 3
036909C-1000-NM-107 | OL1-2W91-0001 | OL1-2W91-0001 | MASTER DOCUMENT INDEX (MDI) | 0 | IFI | TPSK-LSPA1-T-PM-00186 | 2018-10-17 | Transmitted |  |  | 2018-10-16 | IFI | C | ROC | PC | 3
036909C-1000-PP-102 | OL1-2W92-0001 | OL1-2W92-0001 | COORDINATION PROCEDURE | A | IFR | TPSK-LSPA1-T-PM-00001 | 2018-07-30 | R2-Comments as noted | 2018-08-22 | 2018-08-10 | 2018-07-26 | IFR | C | ROC | PC | 2
036909C-1000-PP-107 | OL1-2W92-0003 | OL1-2W92-0003 | PROJECT DOCUMENT CODING | A | IFR | TPSK-LSPA1-T-PM-00001 | 2018-07-30 | A4 - Not approve | 2018-08-22 | 2018-08-10 | 2018-07-26 | IFR | H | ROC | PM | 2
036909C-1000-PP-107 | OL1-2W92-0003 | OL1-2W92-0003 | PROJECT DOCUMENT CODING | 0 | IMP | TPSK-LSPA1-T-PC-00240 | 2018-10-30 | Transmitted |  | 2018-11-13 | 2018-10-24 | IMP | C | ROC | PC | 2
036909C-1000-PP-110 | OL1-2W92-0004 | OL1-2W92-0004 | DOCUMENT MANAGEMENT PROCEDURE | A | IFR | TPSK-LSPA1-T-PC-00013 | 2018-08-08 | R2-Comments as noted | 2018-08-29 | 2018-08-22 | 2018-08-08 | IFR | C | ROC | PC | 2
036909C-1000-PP-100 | OL1-2W92-0006 | OL1-2W92-0006 | TPSK PROJECT DIRECTORATE ORGANIZATION CHART | 0 | IFI | TPSK-LSPA1-T-PC-00010 | 2018-08-06 | Transmitted |  |  | 2018-08-06 | IFI | C | JVD | PC | 3
036909C-1000-PP-131 | OL1-2W92-0007 | OL1-2W92-0007 | TPSK ROC ORGANIZATION CHART | A | IFI | TPSK-LSPA1-T-PC-00030 | 2018-08-27 | Transmitted |  |  | 2018-08-24 | IFI | C | ROC | PC | 3
036909C-1000-PP-123 | OL1-2W92-0009 | OL1-2W92-0009 | CRITICALITY RATING PROCEDURE | A | IFR | TPSK-LSPA1-T-PC-00033 | 2018-09-05 | R2-Comments as noted | 2018-10-01 | 2018-09-19 | 2018-08-22 | IFR | C | ROC | PC | 2
036909C-1000-PP-133 | OL1-2W92-0011 | OL1-2W92-0011 | TPSK HOC ORGANIZATION CHART | 0 | IFI | TPSK-LSPA1-T-PM-00146 | 2018-10-09 | Transmitted |  |  | 2018-10-09 | IFI | C | HOC | PC | 3
036909C-1000-PP-117 | OL1-2W92-0012 | OL1-2W92-0012 | ITC PLAN | A | IFR | TPSK-LSPA1-T-PM-00197 | 2018-10-19 | Transmitted |  | 2018-11-02 | 2018-10-15 | IFR | C | JVD | PC | 2
036909C-1000-PP-101 | OL1-2W92-0013 | OL1-2W92-0013 | PROJECT EXECUTION PLAN | 0 | IFI | TPSK-LSPA1-T-PC-00118 | 2018-10-02 | Transmitted |  |  | 2018-09-28 | IFI | C | JVD | PC | 3
036909C-1000-PP-015 | OL1-2W92-0015 | OL1-2W92-0015 | PRESCRIPTIONS FOR PREPARATION OF MANUFACTURING DATA RECORD BOOK | A | IFR | TPSK-LSPA1-T-PC-00047 | 2018-09-13 | Transmitted |  | 2018-09-28 | 2018-09-11 | IFR | H | ROC | PC | 2
036909C-1000-PP-111 | OL1-2W92-0016 | OL1-2W92-0016 | REPORTING PROCEDURE | A | IFR | TPSK-LSPA1-T-PC-00083 | 2018-09-25 | Transmitted |  | 2018-10-08 | 2018-09-21 | IFR | C | JVD | PC | 2
036909C-1000-PP-124 | OL1-2W92-0018 | OL1-2W92-0018 | ENGINEERING EXECUTION PLAN | 0 | IFI | TPSK-LSPA1-T-PM-00170 | 2018-10-15 | Transmitted |  |  | 2018-10-12 | IFI | C | ROC | PC | 3
036909C-1000-PP-125 | OL1-2W92-0019 | OL1-2W92-0019 | PROJECT CONTROL PROCEDURE | 0 | IMP | TPSK-LSPA1-T-PC-00156 | 2018-10-11 | Transmitted |  |  | 2018-10-05 | IMP | C | JVD | PC | 3
036909C-1000-PP-134 | OL1-2W92-0020 | OL1-2W92-0020 | TPSK SOC ORGANIZATION CHART | 0 | IFI | TPSK-LSPA1-T-PC-00157 | 2018-10-11 | Transmitted |  |  | 2018-10-11 | IFI | C | SK | PC | 3
036909C-1000-PP-132 | OL1-2W92-0021 | OL1-2W92-0021 | TPSK KLOC ORGANIZATION CHART | 0 | IFI | TPSK-LSPA1-T-PC-00171 | 2018-10-15 | Transmitted |  |  | 2018-10-15 | IFI | C | KLOC | PC | 3
036909C-1012-PP-122 | OL1-2W92-2122 | OL1-2W92-2122 | PROJECT ENGINEERING PLAN - PACKAGE A1 - FURNACES - HOUSTON SCOPE (INTERNAL ONLY) | 0 | IFI | TPSK-LSPA1-T-PM-00220 | 2018-10-24 | Transmitted |  |  | 2018-10-22 | IFI | C | HOC | PC | 3
036909C-1000-RR-5000 | OL1-2W95-5000 | OL1-2W95-5000 | MONTHLY PROGRESS REPORT AS OF OCTOBER 15TH 2018 | 0 | IFI | TPSK-LSPA1-T-PC-00195 | 2018-10-22 | Transmitted |  | 2018-11-07 | 2018-10-22 | IFI | C | JVD | PC | 2
036909C-1000-PP-401 | OL1-2X01-0001 | OL1-2X01-0001 | PAYMENT AND INVOICING PROCEDURE | 0 | IFR | TPSK-LSPA1-T-PC-00023 | 2018-08-17 | Transmitted |  | 2018-08-30 | 2018-08-15 | IFR | C | ROC | PC | 2
036909C-1011-PDS-0117-1001 | OL1-4G30-1001 | OL1-2G30-1001 | PROCESS EQUIPMENT DATASHEET - USC 36M CRACKING FURNACE YIELDS | A | IFR | TPSK-LSPA1-T-PE-00117 | 2018-10-01 | Transmitted |  | 2018-10-15 | 2018-09-28 | IFR | C | HOC | PE | 2
036909C-1011-PDS-0630-1008 | OL1-4G30-1008 | OL1-2G30-1008 | SEE DOCUMENT NUMBER 036909C-1011-PDS-0630-1108 OR OL1-2G30-1108 | A | IFR | TPSK-LSPA1-T-PE-00066 | 2018-09-19 | Transmitted |  |  | 2018-09-17 | IFR | C | HOC | PE | 2
036909C-1011-PDS-0610-1009 | OL1-4G30-1009 | OL1-2G30-1009 | SEE DOCUMENT NUMBER 036909C-1011-PDS-0610-1109 OR OL1-2G30-1109 | A | IFR | TPSK-LSPA1-T-PE-00066 | 2018-09-19 | Transmitted |  |  | 2018-09-17 | IFR | C | HOC | PE | 2
036909C-1011-PDS-0610-1010 | OL1-4G30-1010 | OL1-2G30-1010 | SEE DOCUMENT NUMBER 036909C-1011-PDS-0610-1110 OR OL1-2G30-1110 | A | IFR | TPSK-LSPA1-T-PE-00066 | 2018-09-19 | Transmitted |  |  | 2018-09-17 | IFR | C | HOC | PE | 2
036909C-1011-PDS-1040-1011 | OL1-4G30-1011 | OL1-2G30-1011 | PROCESS EQUIPMENT DATASHEET - 10-C-1100 - USC 36M INDUCED DRAFT FAN | A | IFR | TPSK-LSPA1-T-PE-00090 | 2018-09-26 | R1-No comments | 2018-10-12 | 2018-10-10 | 2018-09-25 | IFR | C | HOC | PE | 2
036909C-1012-PDS-0117-2001 | OL1-4G30-2001 | OL1-2G30-2001 | PROCESS EQUIPMENT DATASHEET - USC 132U CRACKING FURNACE YIELDS | A | IFR | TPSK-LSPA1-T-PE-00117 | 2018-10-01 | Transmitted |  | 2018-10-15 | 2018-09-28 | IFR | C | HOC | PE | 2
036909C-1012-PDS-0630-2008 | OL1-4G30-2008 | OL1-2G30-2008 | SEE DOCUMENT NUMBER 036909C-1012-PDS-0630-1208 OR OL1-2G30-1208 | A | IFR | TPSK-LSPA1-T-PE-00066 | 2018-09-19 | Transmitted |  |  | 2018-09-17 | IFR | C | HOC | PE | 2
036909C-1012-PDS-0610-2009 | OL1-4G30-2009 | OL1-2G30-2009 | SEE DOCUMENT NUMBER 036909C-1012-PDS-0610-1209 OR OL1-2G30-1209 | A | IFR | TPSK-LSPA1-T-PE-00066 | 2018-09-19 | Transmitted |  |  | 2018-09-17 | IFR | C | HOC | PE | 2
036909C-1012-PDS-1040-2011 | OL1-4G30-2011 | OL1-2G30-2011 | PROCESS EQUIPMENT DATA SHEET - 10-C-1200-1600 - USC 132U INDUCED DRAFT FAN | A | IFR | TPSK-LSPA1-T-PE-00090 | 2018-09-26 | R1-No comments | 2018-10-12 | 2018-10-10 | 2018-09-25 | IFR | C | HOC | PE | 2
036909C-1012-ITP-0127-2001 | OL1-4M07-2001 | OL1-2M07-2001 | INSPECTION AND TEST PLAN FOR CONVECTION TUBES | A | IFQ | TPSK-LSPA1-T-ME-00044 | 2018-09-12 | Transmitted | 2018-11-05 |  | 2018-09-06 | IFI | C | HOC | ME | 3
036909C-1012-MR-0127-2001 | OL1-4M55-2001 | OL1-2M55-2001 | MATERIAL REQUISITION FOR CONVECTION TUBES | A | IFQ | TPSK-LSPA1-T-ME-00044 | 2018-09-12 | Transmitted |  |  | 2018-09-06 | IFI | C | HOC | ME | 3
036909C-1012-SR-0127-2001 | OL1-4M56-2001 | OL1-2M56-2001 | MATERIAL REQUISITION SCOPE OF SUPPLY FOR CONVECTION TUBES | A | IFQ | TPSK-LSPA1-T-ME-00044 | 2018-09-12 | Transmitted |  |  | 2018-09-06 | IFI | C | HOC | ME | 3
036909C-1012-TEN-0127-2001 | OL1-4M57-2001 | OL1-2M57-2001 | TECHNICAL NOTES FOR CONVECTION TUBES MATERIAL REQUISITION | A | IFQ | TPSK-LSPA1-T-ME-00044 | 2018-09-12 | Transmitted |  |  | 2018-09-06 | IFI | C | HOC | ME | 3
036909C-1012-JSS-0122-2001 | OL1-4M92-2001 | OL1-2M92-2001 | PROJECT SPECIFICATION FOR CENTRIFUGALLY CAST TUBES FOR RADIANT COILS AND TRANSFER LINES IN CRACKING FURNACES | A | IFR | TPSK-LSPA1-T-ME-00037 | 2018-09-10 | R2-Comments as noted | 2018-09-25 | 2018-09-24 | 2018-09-10 | IFR | C | HOC | ME | 2
036909C-1012-JSS-0122-2002 | OL1-4M92-2002 | OL1-2M92-2002 | PROJECT SPECIFICATION FOR STATICALLY CAST FITTINGS FOR RADIANT COILS AND TRANSFER LINES IN CRACKING FURNACES | A | IFR | TPSK-LSPA1-T-ME-00037 | 2018-09-10 | R2-Comments as noted | 2018-09-25 | 2018-09-24 | 2018-09-10 | IFR | C | HOC | ME | 2
036909C-1012-JSS-0154-2007 | OL1-4M92-2007 | OL1-2M92-2007 | PROJECT SPECIFICATION FOR SLE AND USX EXCHANGERS | A | IFR | TPSK-LSPA1-T-ME-00067 | 2018-09-20 | R2-Comments as noted | 2018-10-12 | 2018-10-04 | 2018-09-20 | IFR | C | HOC | ME | 2
036909C-1012-JSS-0154-2008 | OL1-4M92-2008 | OL1-2M92-2008 | PROJECT SPECIFICATION FOR TRANSFER LINE EXCHANGERS | A | IFR | TPSK-LSPA1-T-ME-00067 | 2018-09-20 | R2-Comments as noted | 2018-10-12 | 2018-10-04 | 2018-09-20 | IFR | C | HOC | ME | 2