## CPY_Format
|  |  |  | Master Document Index (MDI) |  | ABBREVIATION | [10 empty] | DOCUMENT NO. | REV.
[6 empty] | **Revision Purpose of Issued Document |  |  |  | *Owner Feedback (Comment) |  |  |  |  | ***Classification
[6 empty] | IFR = Issue For Review |  | IFF = Issue For Final |  | A1 = App. w/o comments |  |  | R1 = No comments |  | Class 1 = For Approval |  | LSP-2W91-0001 | A
[6 empty] | IFA = Issue For Approval |  | ASB = Issue For As-Built |  | A2 = App. with comments, re-submit not required |  |  | R2 = Comments as noted |  | Class 2 = For Review
[6 empty] | IFC = Issue For Construction |  | AFC = Approved for Construction |  | A3 = App. with comments, re-submit for review |  |  |  |  | Class 3 = For Information
Owner: |  | Long Son Pterochemicals C0., Ltd. |  | Plant Name: PACKAGE A1: OLEFINS PLANT |  | IFI = Issue For Information |  | IMP = Issue for Implementation |  | A4 = Not App., re-submit for approval | [6 empty] | Issue Date
|  |  |  | Att. To OL1-2W91-0001 036909C-1000-NM-107 |  | IFP = Issue For Planning |  | / Execution
Document Code : | [5 empty] | IFD = Issue For Design |  | CAN = Issue for Cancellation |  | Period for Company's comment |  |  |  |  | __________ | Working Days
Item | Org. | Document No. | Document Name |  | Classification
Category Code: =Index!B30 =Index!C30
Category Code: A03 Technology transfer dossiers
Category Code: A04 Confidentiality Agreements
Category Code: A05 Laws and Regulations
Category Code: A06 Local content
Category Code: A09 Arbitration and Dispute Resolution
Category Code: A10 Guarantee of Labour Payment Affidavit
Category Code: A11 Termination or Amendment of Contracts
Category Code: A12 Liquidation Contract
Category Code: A13 Claim & Complaint from contractors
Category Code: A14 Claim & Complaint to contractors
Category Code: A15 Variation Change Notice
Category Code: A16 ITC - Instruction to Contractor
Category Code: A17 Contract Variation Form
Category Code: A18 License Agreement
Category Code: A19 Supplement Dossier
Category Code: A20 Certificates
Category Code: A21 Approval Letter
Category Code: A30 Certificate of Work Completion
Category Code: A41 Power of Attorney
Category Code: A42 Power of Attorney
Category Code: A43 Power of Attorney
Category Code: A44 Power of Attorney
Category Code: A51 Contract Document of Consultancy Service
Category Code: A52 Contract Document of EPC Contractor
Category Code: A53 Contract Document of Vendor/Supplier
Category Code: A61 Records of Management of Change (before final investment decision)
Category Code: A62 Records of Management of Change (after final investment decision)
Category Code: A71 Appraisal Report for Consultancy Service
Category Code: A72 Appraisal Report for EPC Contractor Work
Category Code: A73 Appraisal Report for Vendor/Supplier
Category Code: A91 Index/List
Category Code: A92 Procedures & Standards
Category Code: A93 Policy , Guidelines & Memo
Category Code: A94 Forms & Templates
Category Code: A95 Progress/Status Reports
Category Code: B01 Project Schedule
Category Code: B71 Appraisal Report for Consultancy Service
Category Code: B72 Appraisal Report for EPC Contractor Work
Category Code: B73 Appraisal Report for Vendor/Supplier
Category Code: B91 Index/List
Category Code: B92 Procedures & Standards
Category Code: B93 Policy , Guidelines & Memo
Category Code: B94 Forms & Templates
Category Code: B95 Progress/Status Reports
Category Code: C01 Subvendor List
| PL | OL1-2C01-0001 | Subvendor List For Compressor And Turboexpander - Abstract From Approved Vendor List |  |  | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00134
Return Date
Owner Cmmt*
| PL | OL1-2C01-0002 | Subvendor list for PSA/Deareator/Filter Package |  |  | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00333
Return Date
Owner Cmmt*
| PL | OL1-2C01-0003 | Subvendor list for Pumps |  |  | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00333
Return Date
Owner Cmmt*
| PL | OL1-2C01-0004 | Sub Vendor List For Mechanical Packages |  |  | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PL-01633
Return Date
Owner Cmmt*
Category Code: C10 Request for Quotation (RFQ) for Civil work (Engineering and Procurement)
Category Code: C11 Request for Quotation (RFQ) for Building work (Engineering and Procurement)
Category Code: C12 Request for Quotation (RFQ) for Steel Structure work (Engineering and Procurement)
| PL | OL1-2C12-000001 | Material Requisition For Steel Structures |  | Class Final | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-1010
Return Date
Owner Cmmt*
| PL | OL1-2C12-301000 | Material Requisition for Radiant Steel Panel |  | Class Final | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01229
Return Date
Owner Cmmt*
Category Code: C13 Request for Quotation (RFQ) for Mechanical work (Engineering and Procurement)
| ME | OL1-2C13-100000 | Material Requisition For Shop Assembled Large Columns |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-05-15 | 2019-09-26
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00586 | TPSK-LSPA1-T-PL-01526
[6 empty] | Return Date | 2019-01-24
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C13-101000 | Material Requisition For Shop Assembled Columns |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-15 | 2019-09-26
Revised Plan
[6 empty] | Issue Actual | 2019-01-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00705
Return Date
Owner Cmmt*
| PL | OL1-2C13-102000 | Material Requisition For Shop Assembled Columns (C4 Unit) |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-15 | 2019-09-26
Revised Plan
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01623
Return Date
Owner Cmmt*
| PL | OL1-2C13-111000 | Material Requisition For Reactors And Thicker Vessels Requisition For Iinquiry |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-22 | 2019-06-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00918
Return Date
Owner Cmmt*
| PL | OL1-2C13-120000 | Material Requisition for Deaerator D-5100 |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-11-06 | 2019-02-15
Revised Plan
[6 empty] | Issue Actual |  | 2019-04-01
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01210
Return Date
Owner Cmmt*
| PL | OL1-2C13-131000 | Material Requisition For Shop Assembled Large Drums |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
Revised Plan
[6 empty] | Issue Actual | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00967
Return Date
Owner Cmmt*
| PL | OL1-2C13-132000 | Material Requisition For Shop Assembled CS Drums |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
Revised Plan
[6 empty] | Issue Actual | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01032
Return Date
Owner Cmmt*
| PL | OL1-2C13-133000 | Material Requisition For Shop Assembled CS Cladded And SS Vessels |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
Revised Plan
[6 empty] | Issue Actual | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01156
Return Date
Owner Cmmt*
| PL | OL1-2C13-140000 | Material Requisition for Quench Exchangers |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 1
[6 empty] | Issue Plan | 2018-10-26 | 2018-12-17
Revised Plan
[6 empty] | Issue Actual |  | 2019-04-01
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01221
Return Date
Owner Cmmt*
| PL | OL1-2C13-142000 | Material Requisition Plate And Frame Heat Exchangers Requisition For Purchase |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-10-08 | 2019-02-14
Revised Plan
[6 empty] | Issue Actual |  | 2019-02-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-00916
Return Date
Owner Cmmt*
| PL | OL1-2C13-143000 | Material Requisition For Heat Recovery System Requisition For Purchase |  | Class Final | Purpose** | IFP | IFP
[6 empty] | Rev. | 0 | 1
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-21 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00906 | TPSK-LSPA1-T-PL-01452
Return Date
Owner Cmmt*
| PL | OL1-2C13-144000 | Material Requisition For Cold Box And Core Exchangers Requisition For Purchase |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-10-15 | 2019-02-21
Revised Plan
[6 empty] | Issue Actual |  | 2019-04-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-1351
Return Date
Owner Cmmt*
| PL | OL1-2C13-145000 | Material Requisition For Hairpin Heat Exchangers Requisition For Inquiry |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-30 | 2019-05-10
[6 empty] | Revised Plan |  | 2019-06-28
[6 empty] | Issue Actual | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01046
Return Date
Owner Cmmt*
| PL | OL1-2C13-151000 | Material Requisition For Condensate Carbon Filter Package |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-19 | 2019-07-16
Revised Plan
[6 empty] | Issue Actual | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01039
Return Date
Owner Cmmt*
| PL | OL1-2C13-152000 | Material Requisition For Filters And Coalescers |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-24 | 2019-05-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00737
Return Date
Owner Cmmt*
| PL | OL1-2C13-202000 | MATERIAL REQUISITION FOR FRP TANK |  | Class Final | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01646
Return Date
Owner Cmmt*
| PL | OL1-2C13-242000 | Material Requisition For Trays For Columns |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-12-17 | 2019-04-10
Revised Plan
[6 empty] | Issue Actual |  | 2019-04-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01352
Return Date
Owner Cmmt*
| PL | OL1-2C13-243000 | Material Requisition For Ripple Trays And Internals |  | Class Final | Purpose** | IFP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-01-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00628
Return Date
Owner Cmmt*
| PL | OL1-2C13-244000 | MATERIAL REQUISITION FOR TRAYS FOR COLUMNS |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-27 | 2019-07-09
Revised Plan
[6 empty] | Issue Actual | 2019-04-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01268
Return Date
Owner Cmmt*
| PL | OL1-2C13-246000 | Material Requisition for Packing of Columns (C4 Unit) |  | Class Final | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01182
Return Date
Owner Cmmt*
| PL | OL1-2C13-251000 | Material Requisition For API Mechanical Seals and Seal System |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-17 | 2019-05-01
[6 empty] | Revised Plan |  | 2019-06-28
[6 empty] | Issue Actual | 2019-02-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00949
Return Date
Owner Cmmt*
| PL | OL1-2C13-271000 | Material Requisition For Wieland Tubes - Solo Source - Requisition For Purchase - Ex Doc. Client Reference OL1-2M57-0058 |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
Revised Plan
[6 empty] | Issue Actual |  | 2019-02-08
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-00829
Return Date
Owner Cmmt*
| PL | OL1-2C13-272000 | Material Requisition For S&T Heat Exchangers - Large - Requisition For Inquiry |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00849
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C13-273000 | Material Requisition For CS S-T Heat Exchangers Requisition For Inquiry |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00866
Return Date
Owner Cmmt*
| PL | OL1-2C13-274000 | Material Requisition For CS Clad SS And LAS S-T Heat Exchangers Requisition For Inquiry |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00870
Return Date
Owner Cmmt*
| PL | OL1-2C13-281000 | Material Requisition for Furnace Convection Finnings |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-21 | 2019-03-20
Revised Plan
[6 empty] | Issue Actual | 2019-01-23 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00713 | TPSK-LSPA1-T-PL-01085
Return Date
Owner Cmmt*
| PL | OL1-2C13-282000 | Material Requisition for Convection Fabrication |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-16 | 2019-10-21
Revised Plan
[6 empty] | Issue Actual | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01316
Return Date
Owner Cmmt*
| PL | OL1-2C13-283000 | Material Requisition for Radiant Refractory |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-02-07 | 2019-04-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-20 | 2019-05-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01108 | TPSK-LSPA1-T-PL-01657
Return Date
Owner Cmmt*
| PL | OL1-2C13-284000 | Material Requisition for Peep Doors |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-12-10 | 2019-04-03
Revised Plan
[6 empty] | Issue Actual |  | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01181
Return Date
Owner Cmmt*
| PL | OL1-2C13-285000 | Material Requisition for MOVs |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-12-18 | 2019-03-19
Revised Plan
[6 empty] | Issue Actual |  | 2019-04-01
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01219
Return Date
Owner Cmmt*
| PL | OL1-2C13-286000 | Material Requisition for Attemperators |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-16 | 2019-04-03
Revised Plan
[6 empty] | Issue Actual | 2019-01-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00771
Return Date
Owner Cmmt*
| PL | OL1-2C13-300000 | Material Requisition for Radiant Coil Assemblies |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 1
[6 empty] | Issue Plan | 2018-09-19 | 2019-02-14
Revised Plan
[6 empty] | Issue Actual |  | 2019-03-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| PL | OL1-2C13-301000 | Material Requisition for Furnace ID Fans |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-11-05 | 2019-01-17
Revised Plan
[6 empty] | Issue Actual |  | 2019-03-20
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01109
Return Date
Owner Cmmt*
| PL | OL1-2C13-302000 | Material Requisition for Cast Intermediate Tube Supports |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 1
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28
Revised Plan
[6 empty] | Issue Actual |  | 2019-03-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| PL | OL1-2C13-303000 | Material Requisition for Convection Tubes |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 1
[6 empty] | Issue Plan | 2019-07-16 | 2019-10-21
Revised Plan
[6 empty] | Issue Actual |  | 2019-03-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| PL | OL1-2C13-304000 | Material Requisition for Furnace Convection Fittings |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 1
[6 empty] | Issue Plan | 2018-10-22 | 2018-12-21
Revised Plan
[6 empty] | Issue Actual |  | 2019-03-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| PL | OL1-2C13-305000 | Material Requisition for Furnace Steam Drums |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 1
[6 empty] | Issue Plan | 2018-10-26 | 2018-12-17
Revised Plan
[6 empty] | Issue Actual |  | 2019-03-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| ME | OL1-2C13-306000 | Material Requisition for Furnace Burners |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-11-13 | 2019-01-23
Revised Plan
[6 empty] | Issue Actual |  | 2019-02-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00820
Return Date
Owner Cmmt*
| PL | OL1-2C13-311000 | Material Requisition for Cooling Tower |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-10-31 | 2019-03-26
Revised Plan
[6 empty] | Issue Actual |  | 2019-04-24
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01460
Return Date
Owner Cmmt*
| PL | OL1-2C13-321001 | Material Requisition For Ladders And Platforms For Equipment Requisition For Inquiry |  | Class Final | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01593
Return Date
Owner Cmmt*
| PL | OL1-2C13-401000 | Material Requisition For Centrifugal Compressors Steam Turbine Driven - Ex Document Cliet Reference OL1-2M55-0008 |  | Class Final | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 1
[6 empty] | Issue Plan | 2018-10-04 | 2019-04-03 | 2019-04-03
Revised Plan
[6 empty] | Issue Actual |  | 2019-03-21 | 2019-04-19
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01124 | TPSK-LSPA1-T-PL-01420
Return Date
Owner Cmmt*
| PL | OL1-2C13-403000 | Material Requisition for Recycle Gas Compressor |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-25 | 2019-07-22
Revised Plan
[6 empty] | Issue Actual | 2019-01-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00714
Return Date
Owner Cmmt*
| PL | OL1-2C13-421000 | Material Requisition For Residue Gas Expander/Recompressor |  | Class Final | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 1
[6 empty] | Issue Plan | 2018-10-05 | 2019-04-05 | 2019-04-05
Revised Plan
[6 empty] | Issue Actual |  | 2019-03-21 | 2019-04-23
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01118 | TPSK-LSPA1-T-PL-01443
Return Date
Owner Cmmt*
| PL | OL1-2C13-442000 | Material Requisition For API Centrifugal Pumps |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-31 | 2019-05-23
Revised Plan
[6 empty] | Issue Actual | 2019-02-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00880
Return Date
Owner Cmmt*
| PL | OL1-2C13-451000 | Material Requisition For Vent Gas Blower |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-21 | 2019-04-30
[6 empty] | Revised Plan |  | 2019-07-19
[6 empty] | Issue Actual | 2019-03-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01001
[6 empty] | Return Date | 2019-03-27
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C13-700000 | Material Requisition For Electric Heater |  | Class Final | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01409
Return Date
Owner Cmmt*
| PL | OL1-2C13-701000 | Material Requisition for Condensate Polisher Package |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-22 | 2019-06-10
Revised Plan
[6 empty] | Issue Actual | 2019-02-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00940
Return Date
Owner Cmmt*
| PL | OL1-2C13-702000 | Material Requisition For Complex Waste Water Treatment Package |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-25 | 2019-05-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00862
Return Date
Owner Cmmt*
| PL | OL1-2C13-704000 | Material Requisition for Wet Air Oxidation Package |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-11-30 | 2019-04-15
Revised Plan
[6 empty] | Issue Actual |  | 2019-05-08
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01611
Return Date
Owner Cmmt*
| PL | OL1-2C13-705000 | Material Requisition For Hydrogen Production Unit PK-2560 |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-11-14 | 2019-02-15
Revised Plan
[6 empty] | Issue Actual |  | 2019-05-06
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01580
Return Date
Owner Cmmt*
| PL | OL1-2C13-706000 | Material Requisition for Side Stream Filter Package |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-11-07 | 2019-04-05
Revised Plan
[6 empty] | Issue Actual |  | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01165
Return Date
Owner Cmmt*
| PL | OL1-2C13-707000 | Material Requisition For Chemical Dosing System |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2019-07-02
Revised Plan
[6 empty] | Issue Actual | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01491
Return Date
Owner Cmmt*
| PL | OL1-2C13-708000 | MR for HP / Polyolefins Flare Package |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-06-21
Revised Plan
[6 empty] | Issue Actual | 2019-01-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00665
Return Date
Owner Cmmt*
| ME | OL1-2C13-709000 | Material Requisition for Furnace Elevator |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-19 | 2019-02-19
[6 empty] | Revised Plan |  | 2019-05-24
[6 empty] | Issue Actual | 2019-01-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00697
[6 empty] | Return Date | 2019-02-14
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C13-771000 | Material Requisition For Bridge Crane |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00914
Return Date
Owner Cmmt*
| PL | OL1-2C13-801000 | Material Requisition For Ejectors And Static Mixers |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-05 | 2019-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01408
Return Date
Owner Cmmt*
Category Code: C14 Request for Quotation (RFQ) Piping work (Engineering and Procurement)
| PL | OL1-2C14-100001 | Material Requisition For Gate Globe And Check Forged Valves |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-10-15
Revised Plan
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01567
Return Date
Owner Cmmt*
| PL | OL1-2C14-110001 | Material Requisition For Gate Globe And Check Cast Valves Low Pressure |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01
Revised Plan
[6 empty] | Issue Actual | 2019-05-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01574
Return Date
Owner Cmmt*
| PL | OL1-2C14-115001 | Material Requisition For Gate Globe Check Cast Valves High Pressure |  | Class Final | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01579
Return Date
Owner Cmmt*
| PL | OL1-2C14-120001 | Material Requisition For Butterfly Valves Low Pressure Category A |  | Class Final | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01592
Return Date
Owner Cmmt*
| PL | OL1-2C14-125001 | Material Requisition For Butterfly Valves High Performance (Category B) |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01
Revised Plan
[6 empty] | Issue Actual | 2019-05-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01575
Return Date
Owner Cmmt*
| PL | OL1-2C14-130001 | Material Requisition For Plug Valves |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01
Revised Plan
[6 empty] | Issue Actual | 2019-05-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01576
Return Date
Owner Cmmt*
| PL | OL1-2C14-140001 | Material Requisition For Ball Valves |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01
Revised Plan
[6 empty] | Issue Actual | 2019-05-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01577
Return Date
Owner Cmmt*
| PL | OL1-2C14-150001 | Material Requisition For Dual Plate Check Valves |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01
Revised Plan
[6 empty] | Issue Actual | 2019-05-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01578
Return Date
Owner Cmmt*
| PL | OL1-2C14-210001 | Material Requisition For Carbon Steel Seamless Pipe |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15
Revised Plan
[6 empty] | Issue Actual | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01525
Return Date
Owner Cmmt*
| PL | OL1-2C14-215001 | Material Requisition For Carbon Steel Welded Pipe |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-06-17
Revised Plan
[6 empty] | Issue Actual | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01527
Return Date
Owner Cmmt*
| PL | OL1-2C14-220001 | Material Requisition For Alloy Steel Seamless Pipe |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-06-17
Revised Plan
[6 empty] | Issue Actual | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01528
Return Date
Owner Cmmt*
| PL | OL1-2C14-225001 | Material Requisition For Alloy Steel Welded Pipe |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-06-17
Revised Plan
[6 empty] | Issue Actual | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01529
Return Date
Owner Cmmt*
| PL | OL1-2C14-230001 | Material Requisition For Stainless Steel Seamless Pipe |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15
Revised Plan
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01553
Return Date
Owner Cmmt*
| PL | OL1-2C14-235001 | Material Requisition For Stainless Steel Welded Pipe |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15
Revised Plan
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01555
Return Date
Owner Cmmt*
| PL | OL1-2C14-250001 | Material Requisition For Buttwelding Fittings |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15
Revised Plan
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01557
Return Date
Owner Cmmt*
| PL | OL1-2C14-260001 | Material Requisition For Forged Fittings |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15
Revised Plan
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01559
Return Date
Owner Cmmt*
| PL | OL1-2C14-270001 | Material Requisition For Flanges Blinds And Drip Rings |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15
Revised Plan
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01558
Return Date
Owner Cmmt*
| PL | OL1-2C14-360001 | Material Requisition For Carbon Steel Underground Piping |  | Class Final | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00969
Return Date
Owner Cmmt*
| PL | OL1-2C14-365001 | Material Requisition For Underground Welded Carbon Steel Pipes |  | Class Final | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00975
Return Date
Owner Cmmt*
Category Code: C15 Request for Quotation (RFQ) for Fire Fighting work (Engineering and Procurement)
Category Code: C16 Request for Quotation (RFQ) for Electrical and HVAC work (Engineering and Procurement)
| PL | OL1-2C16-851000 | MATERIAL REQUISITION FOR SAFETY SUPERVISORY SYSTEM |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-04 | 2020-01-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00984
[6 empty] | Return Date | 2019-04-05
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C16-881000 | MATERIAL REQUISITION FOR INTERCOM/PAGING/AUDIBLE ALARM SYSTEM |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-04 | 2020-01-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00984
[6 empty] | Return Date | 2019-04-10
[6 empty] | Owner Cmmt* | R2
Category Code: C17 Request for Quotation (RFQ) for Instrumentation work (Engineering and Procurement)
| PL | OL1-2C17-022005 | Material Requisition for Level Gauges |  | Class Final | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-26 | 2019-06-26
Revised Plan
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01393
Return Date
Owner Cmmt*
| PL | OL1-2C17-032010-ATT2 | Instrument Datasheets for Temperature Elements for Furnace Profile |  | Class Final | Purpose** | IFR | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-11-05
Revised Plan
[6 empty] | Issue Actual | 2019-05-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01542
Return Date
Owner Cmmt*
| PL | OL1-2C17-052001 | Material Requistion for Control Valves |  | Class Final | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01482
Return Date
Owner Cmmt*
| PL | OL1-2C17-072002 | Material Requisition for Pressure Relief Valves |  | Class Final | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01427
Return Date
Owner Cmmt*
Category Code: C18 Request for Quotation (RFQ) for Chemicals (Engineering and Procurement)
| PL | OL1-2C18-263000 | Material Requisition For Molecular And HG Sieves |  | Class Final | Purpose** | IMP
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01076
[6 empty] | Return Date | 2019-04-01
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C18-264000 | Material Requisition For Adsorbents |  | Class Final | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01295
Return Date
Owner Cmmt*
| PL | OL1-2C18-265000 | Material Requisition For Molecular Sieves |  | Class Final | Purpose** | IMP
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01077
[6 empty] | Return Date | 2019-04-01
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C18-266000 | Material Requisition For Adsorbents |  | Class Final | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01299
Return Date
Owner Cmmt*
| PL | OL1-2C18-267000 | Material Requisition For Hg Sieves |  | Class Final | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01296
Return Date
Owner Cmmt*
| PL | OL1-2C18-268000 | Material Requisition For Support Balls |  | Class Final | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01297
Return Date
Owner Cmmt*
Category Code: C20 Technical Bid Evaluation for Civil work (Engineering and Procurement)
Category Code: C21 Technical Bid Evaluation for Building work (Engineering and Procurement)
Category Code: C22 Technical Bid Evaluation for Steel Structure work (Engineering and Procurement)
Category Code: C23 Technical Bid Evaluation for Mechanical work (Engineering and Procurement)
Category Code: C24 Technical Bid Evaluation for Piping work (Engineering and Procurement)
Category Code: C25 Technical Bid Evaluation for Fire Fighting work (Engineering and Procurement)
Category Code: C26 Technical Bid Evaluation for Electrical and HVAC work (Engineering and Procurement)
Category Code: C27 Technical Bid Evaluation for Instrumentation work (Engineering and Procurement)
Category Code: C28 Technical Bid Evaluation for Chemicals (Engineering and Procurement)
Category Code: C30 Scope of Supply (SR) for Mechanical Work
Category Code: C31 Scope of Supply (SR) for Piping Work
Category Code: C32 Scope of Supply (SR) for Electrical work
Category Code: C33 Scope of Supply (SR) for Instrumentation work
Category Code: C34 Scope of Supply (SR) for Civil,Structure and Architecture.
Category Code: C35 Extend of Supply (SP) Mechanical Work
Category Code: C36 Extend of Supply (SP) for Piping Work
Category Code: C37 Extend of Supply (SP) for Electrical work
Category Code: C38 Extend of Supply (SP) for Instrumentation work
Category Code: C39 Extend of Supply (SP) for Civil,Structure and Architecture
Category Code: C40 Deviation List (DL) for Mechanical Work
Category Code: C41 Deviation List (DL) for Piping Work |  |  |  |  | Class Final | Purpose**
Category Code: C42 Deviation List (DL) for Electrical work | [5 empty] | Rev.
Category Code: C43 Deviation List (DL) for Instrumentation work | [5 empty] | Issue Plan
Category Code: C44 Deviation List (DL) for Civil,Structure and Architecture | [5 empty] | Revised Plan
Category Code: C50 Purchase Order (PO) for Civil work, Building work, Steel Structure work | [5 empty] | Issue Actual
Category Code: C51 Purchase Order (PO) for Mechanical work | [5 empty] | Transmittal no.
| PL | OL1-2C51-0001 | Vendor s Acknowledgment of Purchase Order For Wieland Tubes -Sole Source - MR 0610-0001 Rev 0 |  | Class Final | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
Return Date
Owner Cmmt*
| PL | OL1-2C51-0002 | Vendor s Acknowledgment of Purchase Order For Residue Gas Expander Recompressor – MR 1130-0001 Rev 0 |  | Class Final | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
Return Date
Owner Cmmt*
| PL | OL1-2C51-0003 | Vendor s Acknowledgment of Purchase Order For Steam Turbine Drive Centrifugal Compressor – MR 1011-0001 Rev 0 |  | Class Final | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
Return Date
Owner Cmmt*
| PL | OL1-2C51-0004 | Vendor s Acknowledgment of Purchase Order For Centrifugal Compressor Steam Turbine Driven Site Services |  | Class Final | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
Return Date
Owner Cmmt*
| PL | OL1-2C51-0005 | Vendor s Acknowledgment of Purchase Order For Deareator MR-0845-0001 |  | Class Final | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
Return Date
Owner Cmmt*
| PL | OL1-2C51-0006 | Vendor s Acknowledgment of Purchase Order For Plate And Frame Heat Exchangers – MR 0661-0001 Rev 0 |  | Class Final | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
Return Date
Owner Cmmt*
| PL | OL1-2C51-0008 | Vendor s Acknowledgment of Purchase Order For Cold Box And Core Exchangers – MR 0662-0002 Rev 0 |  | Class Final | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
Return Date
Owner Cmmt*
Category Code: C52 Purchase Order (PO) for Piping work
Category Code: C53 Purchase Order (PO) for Fire Fighting work
Category Code: C54 Purchase Order (PO) for Electrical and HVAC work
Category Code: C55 Purchase Order (PO) for Instrumentation work
Category Code: C56 Purchase Order (PO) for Chemicals
Category Code: C71 Appraisal Report for Consultancy Service
Category Code: C72 Appraisal Report for EPC Contractor Work
Category Code: C73 Appraisal Report for Vendor/Supplier
Category Code: C91 Index/List
Category Code: C92 Procedures & Standards
Category Code: C93 Policy , Guidelines & Memo
| PL | OL1-2C93-0001 | General Supply Rules for Supplier Documentation |  | Class Final | Purpose** | IFI | IFI
[6 empty] | Rev. | A | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12 | 2019-02-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00043 | TPSK-LSPA1-T-PL-00777
Return Date
Owner Cmmt*
Category Code: C94 Forms & Templates
Category Code: C95 Progress/Status Reports
| PL | OL1-2C95-0001 | Expediting Execution Plan |  | Class Final | Purpose** | IFI | IFI
[6 empty] | Rev. | 0 | 1
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-22 | 2019-04-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01134 | TPSK-LSPA1-T-PL-01419
Return Date
Owner Cmmt*
| PL | OL1-2C95-0002 | Monthly Complete Expediting Report |  | Class Final | Purpose** | IFI | IFI
[6 empty] | Rev. | 0 | 1
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-22 | 2019-04-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01134 | TPSK-LSPA1-T-PL-01419
Return Date
Owner Cmmt*
| PL | OL1-2C95-140000 | Hand-Over Meeting Report - Quench Exchanger and Steam D |  | Class Final | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01026
Return Date
Owner Cmmt*
| PL | OL1-2C95-300000 | Hand-Over Meeting Report - Radiant Coils |  | Class Final | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01194
Return Date
Owner Cmmt*
| PL | OL1-2C95-302000 | Pre-Inspection Meeting Report - Intermediate Tube Supports |  | Class Final | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01359
Return Date
Owner Cmmt*
Category Code: Code Information
Category Code: D01 Construction Permits/License/Permit Plan
Category Code: D03 Security Plan
Category Code: D04 Transportation Program
Category Code: D05 Office & Construction Camp Plan
Category Code: D06 Work Change Proposal
Category Code: D71 Appraisal Report for Consultancy Service
Category Code: D72 Appraisal Report for EPC Contractor Work
Category Code: D73 Appraisal Report for Vendor/Supplier
Category Code: D91 Index/List
Category Code: D92 Procedures & Standards
Category Code: D93 Policy , Guidelines & Memo
Category Code: D94 Forms & Templates
Category Code: D95 Progress/Status Reports
Category Code: D96 Hydrostatic leak testing for piping systems
Category Code: E01 Electrical design basis
| EE | OL1-2E01-2001 | ELECTRICAL BASIS OF FURNACE DETAILED DESIGN |  | Class 1 | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-24 | 2019-03-28 | 2019-03-28
[6 empty] | Revised Plan |  | 2019-05-16 | 2019-05-16
[6 empty] | Issue Actual | 2019-01-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00772
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A4
Category Code: E02 Abbreviation and standard symbols
| EE | OL1-2E02-0001 | ELECTRICAL DRAWINGS LEGEND AND SYMBOLS |  | Class 2 | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-30
Revised Plan
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01411
Return Date
Owner Cmmt*
Category Code: E03 Project electrical specification
| EE | OL1-2E03-0035 | TYPICAL INSTALLATION STANDARDS FOR ELECTRICAL EQUIPMENT |  | Class 2 | Purpose** | IFR | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-10-07 | 2020-02-14
Revised Plan
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01193
[6 empty] | Return Date | 2019-05-07
[6 empty] | Owner Cmmt* | A3
Category Code: E04 Electrical requirement for package unit
| EE | OL1-2E04-6000 | GENERAL DEIGN RULES FOR ELECTRICAL SYSTEM OF PACKAGED EQUIPMENT |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | B
[6 empty] | Issue Plan | 2018-10-14 | 2019-01-30
Revised Plan
[6 empty] | Issue Actual | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00126
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
Category Code: E05 Electrical Equipment datasheets
| EE | CL1-2E05-1200 | Typical Data Sheet for Low Voltage Switchgears/MCCs |  | Class As Built | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00497
[6 empty] | Return Date | 2019-01-07
[6 empty] | Owner Cmmt* | R1
| EE | CL1-2E05-1400 | Typical Data Sheet for Low Voltage Bus Ducts |  | Class As Built | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00497
[6 empty] | Return Date | 2019-01-07
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E05-0020 | Air Conditioning Ventilating And Ducting Design - Ex Document Client Reference: OL1-2H03-0001 - |  | Class As Built | Purpose** | IFR | IMP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-10-12 | 2019-01-15
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00585
[6 empty] | Return Date |  | 2019-01-16
[6 empty] | Owner Cmmt* |  | R1
| EE | OL1-2E05-1100 | Typical Data Sheet for Medium Voltage Switchgears |  | Class As Built | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00476
[6 empty] | Return Date | 2019-01-07
[6 empty] | Owner Cmmt* | R1
| EE | OL1-2E05-1111 | Data Sheet for Medium Voltage Switchgear |  | Class As Built | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E05-1211 | Data Sheet for 690V Switchgear And MCC |  | Class As Built | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E05-1311 | Data Sheet for 400V SwitchgearAndMCC |  | Class As Built | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E05-1501 | Data Sheet for Distribution Transformer |  | Class As Built | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E05-1700 | Typical Data Sheet For Medium Voltage Variable Voltage Variable Frequency System |  | Class As Built | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00529
[6 empty] | Return Date | 2019-01-03
[6 empty] | Owner Cmmt* | R1
| EE | OL1-2E05-2001 | Data Sheet for AC UPS |  | Class As Built | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E05-2101 | Data Sheet For DC UPS |  | Class As Built | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E05-3100 | Typical Data Sheet for LV Motors |  | Class As Built | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00358
[6 empty] | Return Date | 2019-01-03
[6 empty] | Owner Cmmt* | R1
| EE | OL1-2E05-3500 | Typical Data Sheet For Low Voltage Variable Voltage Variable Frequency System |  | Class As Built | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00358
[6 empty] | Return Date | 2019-01-03
[6 empty] | Owner Cmmt* | R1
| EE | OL1-2E05-4100 | Typical Data Sheet For MV Motor |  | Class As Built | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00529
[6 empty] | Return Date | 2019-01-03
[6 empty] | Owner Cmmt* | R1
Category Code: E10 Power system studies
| EE | OL1-2E10-0001 | ELECTRICAL CABLE SIZING CALCULATION NOTES |  | Class 2 | Purpose** | IFR | IDD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-10-15 | 2020-01-15
Revised Plan
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01438
Return Date
Owner Cmmt*
| EE | OL1-2E10-0002 | ELECTRICAL POWER BALANCE |  | Class 2 | Purpose** | IDD | IDD1 | IFF
Rev.
[6 empty] | Issue Plan | 2019-05-18 | 2019-10-21 | 2020-01-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0003 | LIGHTING SYSTEM CALCULATION NOTES |  | Class 2 | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0004 | SHORT CIRCUIT ANALYSIS |  | Class 2 | Purpose** | IFR | IDD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
Revised Plan
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01438
Return Date
Owner Cmmt*
| EE | OL1-2E10-0005 | LOAD FLOW AND VOLTAGE DROP ANALYSIS |  | Class 2 | Purpose** | IFR | IDD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
Revised Plan
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01438
Return Date
Owner Cmmt*
| EE | OL1-2E10-0006 | MOTOR STARTING ANALYSIS |  | Class 2 | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0007 | REACCELERATION STUDY |  | Class 2 | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0008 | HARMONIC ANALYSIS |  | Class 2 | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0009 | EMC STUDY |  | Class 2 | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0010 | ELECTRICAL RELIABILITY ANALYSIS |  | Class 2 | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0011 | INSULATION COORDINATION STUDY |  | Class 2 | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E11 Arc flash studies
| EE | OL1-2E11-0001 | FLASH PROTECTION STUDY |  | Class 2 | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E12 Protective relay selection and coordination study
| EE | OL1-2E12-0001 | PROTECTIVE RELAY SELECTIVITY STUDY |  | Class 2 | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2020-10-21 | 2020-11-21 | 2020-12-21
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E13 Electrical equipment sizing
| EE | OL1-2E13-0001 | POWER FACTOR IMPROVEMENT SYSTEM SIZING |  | Class 2 | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E13-0002 | AC UPS SYSTEM SIZING |  | Class 2 | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-11 | 2020-03-15 | 2020-05-21
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E13-0003 | DC SYSTEM SIZING |  | Class 2 | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-11 | 2020-03-15 | 2020-05-21
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E14 Single line diagram
| EE | OL1-2E14-0001 | KEY SINGLE LINE DIAGRAM |  | Class 2 | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-11-07 | 2020-04-17
Revised Plan
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01412
Return Date
Owner Cmmt*
| EE | OL1-2E14-0002 | INTERLOCKING SYSTEM PHYLOSOPHY DRAWING |  | Class 2 | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2019-06-03 | 2019-11-07 | 2020-04-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E14-0003 | SUBSTATION E SINGLE LINE DIAGRAM (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-11-07 | 2020-04-17 | 2020-07-17
Revised Plan
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01211
[6 empty] | Return Date | 2019-04-25
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E14-0004 | SUBSTATION C SINGLE LINE DIAGRAM (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-11-07 | 2020-04-17 | 2020-07-17
Revised Plan
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01211
[6 empty] | Return Date | 2019-04-25
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E14-0005 | SATELLITE SUBSTATION SINGLE LINE DIAGRAM (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-11-07 | 2020-04-17 | 2020-07-17
Revised Plan
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01211
[6 empty] | Return Date | 2019-04-25
[6 empty] | Owner Cmmt* | A3
Category Code: E15 Electrical load schedule |  |  |  |  | Class 3 | Purpose**
| EE | OL1-2E15-0001 | PRELIMINARY ELECTRICAL LOAD SCHEDULE - OLEFINS UNIT |  | Class 3 | Purpose** | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-05-03 | 2020-03-17
[6 empty] | Revised Plan | 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-0002 | ELECTRICAL EQUIPMENT LIST |  | Class 2 | Purpose** | IDD | IDD1 | IFF
Rev.
[6 empty] | Issue Plan | 2019-06-03 | 2019-11-07 | 2020-04-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-0003 | EX-EQUIPMENT REGISTER LIST |  | Class 2 | Purpose** | IF1T | IF2T
Rev.
[6 empty] | Issue Plan | 2020-04-14 | 2020-10-19
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-0004 | ELECTRICAL CONSUMERS LIST |  | Class 2 | Purpose** | IFR | IFI
Rev.
[6 empty] | Issue Plan | 2019-03-19 | 2019-04-23
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-1001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-10 | 2019-10-08 | 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-2001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-10 | 2019-10-08 | 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-3001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-4001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-5001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-6001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E16 Emergency power supply load schedule
Category Code: E17 Motor list
| EE | OL1-2E17-1001 | PRELIMINARY MOTOR LIST - OLEFINS UNIT |  |  | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-02-18 | 2019-04-23
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E18 Control and Signal List
| EE | OL1-2E18-0001 | SUBSTATION MONITORING AND CONTROL SYSTEM BLOCK DIAGRAM FOR SUBSTATION E |  | Class 2 | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-07-14 | 2019-11-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E18-0002 | SUBSTATION MONITORING AND CONTROL SYSTEM BLOCK DIAGRAM FOR SUBSTATION C |  | Class 2 | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-07-14 | 2019-11-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E18-0003 | SUBSTATION MONITORING AND CONTROL SYSTEM BLOCK DIAGRAM FOR SATELLITE SUBSTATION |  | Class 2 | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-07-14 | 2019-11-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E19 Control schematic and control logic diagrams
| EE | OL1-2E19-0001 | MEDIUM VOLTAGE PROTECTION DIAGRAMS |  | Class 2 | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-09-07 | 2019-11-12
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E19-0002 | LOW VOLTAGE PROTECTION DIAGRAMS |  | Class 2 | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-09-07 | 2019-11-12
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E20 Substation equipment layout
| EE | OL1-2E20-0001 | SUBSTATION E EQUIPMENT LAYOUT |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-08 | 2020-04-17 | 2020-06-17
Revised Plan
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01212
[6 empty] | Return Date | 2019-04-08
[6 empty] | Owner Cmmt* | CA
| EE | OL1-2E20-0002 | SUBSTATION C EQUIPMENT LAYOUT |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-08 | 2020-04-17 | 2020-06-17
Revised Plan
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01212
[6 empty] | Return Date | 2019-05-07
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E20-0003 | SATELLITE ELECTRICAL / INSTRUMENT EQUIPMENT LAYOUT |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-08 | 2020-04-17 | 2020-06-17
Revised Plan
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01212
Return Date
Owner Cmmt*
Category Code: E21 Layout of busduct for substation
Category Code: E22 Cable tray layout for substation
| EE | OL1-2E22-0001 | SUBSTATION E CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E22-0002 | SUBSTATION C CABLE ROUTING LAYOUT (N…) |  | Class 2 | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E22-0003 | SATELLITE SUBSTATION CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E23 Wiring drawing for substation system
Category Code: E24 Diesel engine generator equipment layout
Category Code: E25 Motor Auto restart for power dift.
Category Code: E31 Power equipment layout
| EE | OL1-2E31-0001 | OVERALL ELECTRICAL MAIN CABLE ROUTING LAYOUT |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0002 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0003 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0004 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0005 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0006 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0007 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0008 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0009 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0010 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0011 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0012 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0013 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0014 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0015 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0016 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0017 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-1001 | USC 36M FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-1002 | USC 36M FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-1003 | USC 36M FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-2001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-2002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-2003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-3001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-3002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-3003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-4001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-4002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-4003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-5001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-5002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-5003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-6001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-6002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-6003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E32 Main cable route layout
| EE | OL1-2E32-0001 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0002 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0003 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0004 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0005 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0006 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0007 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0008 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0009 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0010 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0011 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0012 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0013 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0014 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0015 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0016 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1001 | USC 36M FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1002 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1003 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1004 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1005 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1006 | USC 36M FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1007 | USC 36M FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1008 | USC 36M FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1009 | USC 36M FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E33 Power and control wiring layout
Category Code: E34 Power and control cable arrangement drawing
| EE | OL1-2E34-0001 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0002 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0003 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0004 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0005 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0006 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0007 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0008 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0009 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0010 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0011 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0012 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0013 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0014 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0015 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0016 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E40 Lighting illumination level calculation
Category Code: E41 Voltage drop calculation for lighting system
Category Code: E42 Lighting and receptacle panel board circuit schedule
| EE | OL1-2E42-0001 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0002 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0003 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0004 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0005 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0006 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0007 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0008 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0009 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0010 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0011 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0012 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0013 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0014 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0015 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0016 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-1001 | USC 36M FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-1002 | USC 36M FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-1003 | USC 36M FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-2001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-2002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-2003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-3001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-3002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-3003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-4001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-4002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-4003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-5001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-5002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-5003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-6001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-6002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-6003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E43 Lighting and receptacle system layout
| EE | OL1-2E43-0001 | STREET LIGHTING SYSTEM LAYOUT |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0005 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0006 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IFA | IDD | IFC1 | IFC2
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-05-19 |  | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
[6 empty] | Issue Actual |  | 2019-04-23
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-01437
Return Date
Owner Cmmt*
| EE | OL1-2E43-0007 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0008 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0009 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0010 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0011 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0012 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0013 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
[6 empty] | Issue Actual | 2019-04-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01423
Return Date
Owner Cmmt*
| EE | OL1-2E43-0014 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
[6 empty] | Issue Actual | 2019-04-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01423
Return Date
Owner Cmmt*
| EE | OL1-2E43-0015 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
[6 empty] | Issue Actual | 2019-04-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01423
Return Date
Owner Cmmt*
| EE | OL1-2E43-0016 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
[6 empty] | Issue Actual | 2019-04-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01423
Return Date
Owner Cmmt*
| EE | OL1-2E43-0017 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
[6 empty] | Issue Actual | 2019-04-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01423
Return Date
Owner Cmmt*
| EE | OL1-2E43-0018 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
[6 empty] | Issue Actual | 2019-04-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01423
Return Date
Owner Cmmt*
| EE | OL1-2E43-0019 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0020 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1001 | USC 36M FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1002 | USC 36M FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1003 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1004 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1005 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1006 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1007 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1008 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1009 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1010 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1011 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1012 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1013 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1014 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1015 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2016 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2017 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2018 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2019 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2020 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3016 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3017 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4016 | ELECTRICAL LIGHTING FOR ELEVATOR LANDINGS ASSOCIATED WITH FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4017 | ELECTRICAL LIGHTING FOR ELEVATOR LANDINGS ASSOCIATED WITH FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4018 | ELECTRICAL LIGHTING FOR ELEVATOR LANDINGS ASSOCIATED WITH FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4019 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4020 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5016 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5017 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6016 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6017 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6018 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6019 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6020 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E44 Lighting and receptacle system wiring layout
| EE | OL1-2E44-0001 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0002 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0003 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0004 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0005 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0006 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0007 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0008 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0009 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0010 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0011 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0012 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0013 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0014 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0015 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0016 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E45 POWER BLOCK DIAGRAM (WELDING AND RECEPACLES)
Category Code: E50 Grounding and lightning network calculation
| EE | OL1-2E50-0001 | EARTHING AND LIGHTNING SYSTEM CALCULATION |  | Class 2 | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-04-19 | 2019-10-15 | 2020-07-08
[6 empty] | Revised Plan | 2019-07-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E51 Protective zone for lightning system
Category Code: E52 Grounding and lightning system layout
| EE | OL1-2E52-0001 | OVERALL EARTHING LAYOUT |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0002 | OVERALL LIGHTNING PROTECTION LAYOUT |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0003 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0004 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0005 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0006 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0007 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0008 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0009 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0010 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0011 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0012 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0013 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0014 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0015 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0016 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0017 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0018 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0021 | SUBSTATION E EARTHING LAYOUT |  | Class 2 | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0022 | SUBSTATION C EARTHING LAYOUT |  | Class 2 | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0023 | SATELLITE SUBSTATION EARTHING LAYOUT |  | Class 2 | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-1001 | USC 36M FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-02-03 | 2020-02-03
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-1002 | USC 36M FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-02-03 | 2020-02-03
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-1003 | USC 36M FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-02-03 | 2020-02-03
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-2001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-2002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-2003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-3001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-3002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-3003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-4001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-4002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-4003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-5001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-5002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-5003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-6001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-6002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-6003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E53 Wiring drawing for grounding and lightning system
Category Code: E54 Layout of grounding lug
Category Code: E55 Request for Quotation (RFQ) for Electrical
| EE | OL1-2E55-1100 | MR FOR MV SWITCHGEARS (> 1 KV, = 52 KV) |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00476
[6 empty] | Return Date | 2019-01-07
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E55-1200 | MR FOR LV SWITCHGEARS AND LV BUS DUCTS (= 1 KV) |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00497
[6 empty] | Return Date | 2019-01-07
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E55-1800 | MR FOR SMCS SYSTEM |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00510
[6 empty] | Return Date | 2019-01-07
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E55-3001 | MR FOR LV ELECTRIC MOTORS AND LV VVVF |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00359
[6 empty] | Return Date | 2019-01-03
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E55-4100 | Material Requisition For Medium Voltage Motors Medium Voltage Variable Voltage Variable Frequency System |  |  | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00540
[6 empty] | Return Date | 2019-01-14
[6 empty] | Owner Cmmt* | R2
Category Code: E60 Cable drum schedule |  |  |  |  | Class 2 | Purpose**
| EE | OL1-2E60-0001 | ELECTRICAL CABLE DRUM SCHEDULE |  | Class 2 | Purpose** | IF1T | IF2T
Rev.
[6 empty] | Issue Plan | 2020-04-14 | 2020-10-19
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E61 Cable schedule
| EE | OL1-2E61-0001 | ELECTRICAL CABLE SCHEDULE - SUBSTATION - E |  | Class 2 | Purpose** | IDD | IF1T | IF2T | IFF
Rev.
[6 empty] | Issue Plan | 2019-08-10 | 2019-11-15 | 2020-02-15 | 2020-05-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E61-0002 | ELECTRICAL CABLE SCHEDULE - SUBSTATION - C |  | Class 2 | Purpose** | IDD | IF1T | IF2T | IFF
Rev.
[6 empty] | Issue Plan | 2019-08-10 | 2019-11-15 | 2020-02-15 | 2020-05-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E61-0003 | ELECTRICAL CABLE SCHEDULE - SATELLITE SUBSTATION |  | Class 2 | Purpose** | IDD | IF1T | IF2T | IFF
Rev.
[6 empty] | Issue Plan | 2019-08-10 | 2019-11-15 | 2020-02-15 | 2020-05-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E62 Connection List
Category Code: E63 Construction material and Bill of quantities
| EE | OL1-2E63-0002 | TECHNICAL SPECIFICATION FOR ELECTRICAL INSTALLATION |  | Class 2 | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-02-20 | 2020-05-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-0003 | JOB QC SPECIFICATION FOR ELECTRICAL INSTALLATION |  | Class 2 | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-02-20 | 2020-05-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-1001 | ELECTRICAL BULK MATERIAL |  | Class 3 | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-10-22 | 2020-02-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-2001 | ELECTRICAL BULK MATERIAL |  | Class 3 | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-10-22 | 2020-02-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-3001 | ELECTRICAL BULK MATERIAL |  | Class 3 | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-10-22 | 2020-02-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-4001 | ELECTRICAL BULK MATERIAL |  | Class 3 | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-10-22 | 2020-02-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-5001 | ELECTRICAL BULK MATERIAL |  | Class 3 | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-10-22 | 2020-02-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-6001 | ELECTRICAL BULK MATERIAL |  | Class 3 | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-10-22 | 2020-02-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E64 Typical drawing
Category Code: E70 Cathodic Protection system schematic diagram
Category Code: E71 Cathodic Protection system layout
Category Code: E72 Cathodic Protection calculation
Category Code: E80 SMCS and PMS system equipment data sheets
Category Code: E81 SMCS and PMS system schematic diagram
Category Code: E82 SMCS and PMS system layout
Category Code: E86 Appraisal Report for Consultancy Service
Category Code: E87 Appraisal Report for EPC Contractor Work
Category Code: E88 Appraisal Report for Vendor/Supplier
Category Code: E90 Vendor documents
Category Code: E91 Index/List
Category Code: E92 Procedures & Standards
| EE | OL1-2E92-0001 | GENERAL DESIGN RULES FOR FOR SMART PLAN ELECTRICAL |  | Class 2 | Purpose** | IFR | IFI | IMP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-10-14 |  | 2019-01-30
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00396
Return Date
Owner Cmmt*
| EE | OL1-2E92-0002 | Coordination Procedure For Smartplant Electrical |  | Class Final | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00395
Return Date
Owner Cmmt*
| EE | OL1-2E92-0003 | Coordination Procedure For ETAP |  | Class Final | Purpose** | IFR | IFI | IMP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-10-14 |  | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00426
Return Date
Owner Cmmt*
Category Code: E93 Policy , Guidelines & Memo
Category Code: E94 Forms & Templates
Category Code: E95 Progress/Status Reports
Category Code: F26 Hydraulic Calculation for Fixed FF Systems
Category Code: F30 Fire Fighting Layout
Category Code: F40 Fire and Gas Layout
| FF | OL1-2F40-5002 | FIRE & GAS DEVICES LAYOUT METERING |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 | 2019-06-15 | 2020-01-25 | 2020-05-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01119 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F40-5003 | FIRE & GAS DEVICES LAYOUT MAIN PIPE RACK |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 | 2019-06-15 | 2020-01-25 | 2020-05-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01119 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F40-5004 | FIRE & GAS DEVICES LAYOUT AREA SUBSTATION E & FAR E |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 | 2019-06-15 | 2020-01-25 | 2020-05-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F40-5005 | FIRE & GAS DEVICES LAYOUT AREA SUBSTATION C & FAR C |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 | 2019-06-15 | 2020-01-25 | 2020-05-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F40-5006 | FIRE & GAS DEVICES LAYOUT FURNACES UTILITY |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 | 2019-06-15 | 2020-01-25 | 2020-05-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F40-5007 | FIRE & GAS DEVICES LAYOUT QUENCH |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 | 2019-06-15 | 2020-01-25 | 2020-05-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F40-5008 | FIRE & GAS DEVICES LAYOUT PROCESS 20B |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 | 2019-06-15 | 2020-01-25 | 2020-05-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F40-5009 | FIRE & GAS DEVICES LAYOUT PROCESS 20C |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 | 2019-06-15 | 2020-01-25 | 2020-05-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F40-5010 | FIRE & GAS DEVICES LAYOUT PROCESS COLD COMPRESSORS |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 | 2019-06-15 | 2020-01-25 | 2020-05-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F40-5011 | FIRE & GAS DEVICES LAYOUT PROCESS CGC |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 | 2019-06-15 | 2020-01-25 | 2020-05-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F40-5012 | FIRE & GAS DEVICES LAYOUT BUTADIENE |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 | 2019-06-15 | 2020-01-25 | 2020-05-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F40-5013 | FIRE & GAS DEVICES LAYOUT COOLING WATER UNIT |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 | 2019-06-15 | 2020-01-25 | 2020-05-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F40-5014 | FIRE & GAS DEVICES LAYOUT UTILITIES |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 | 2019-06-15 | 2020-01-25 | 2020-05-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F40-5015 | FIRE & GAS DEVICES LAYOUT WASTE WATER TREATMENT |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 | 2019-06-15 | 2020-01-25 | 2020-05-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F40-5016 | FIRE & GAS DEVICES LAYOUT FLARE AREA |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 | 2019-06-15 | 2020-01-25 | 2020-05-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
Category Code: F41 Fire and Gas Detector C&E
| FF | OL1-2F41-5001 | FIRE AND GAS CAUSE & EFFECT CHART FAR-E SYSTEM |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-06-07 | 2020-09-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F41-5002 | FIRE AND GAS CAUSE & EFFECT CHART FAR-C SYSTEM |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-06-07 | 2020-09-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F41-5003 | FIRE AND GAS CAUSE & EFFECT CHART CCB SYSTEM |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-06-07 | 2020-09-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: F71 Appraisal Report for Consultancy Service
Category Code: F72 Appraisal Report for EPC Contractor Work
Category Code: F73 Appraisal Report for Vendor/Supplier
Category Code: F75 Escape Ways Drawing
| FF | OL1-2F75-0001 | Life Saving Equipment and Escape Route Layout - Zone 0S Electrical Sub-station and Far E |  | Class Final | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F75-0002 | Life Saving Equipment and Escape Route Layout - Zone 3S Electrical Sub-station and Far C |  | Class Final | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F75-0003 | Life Saving Equipment and Escape Route Layout - Zone 5T Cooling Water Unit |  | Class Final | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F75-0004 | Life Saving Equipment and Escape Route Layout - Zone 5W Waste Water Treatment |  | Class Final | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F75-0005 | Life Saving Equipment and Escape Route Layout - Zone 5U Utilities |  | Class Final | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F75-0006 | Life Saving Equipment and Escape Route Layout - Zone 5F HP & Polyoleffins Flares Unit |  | Class Final | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F75-0007 | Life Saving Equipment and Escape Route Layout - Zone 0M Metering Station |  | Class Final | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F75-0009 | Life Saving Equipment and Escape Route Layout - - Zone 1B Furnaces Utility |  | Class Final | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F75-0010 | Life Saving Equipment and Escape Route Layout - Zone 2A Quench |  | Class Final | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F75-0011 | Life Saving Equipment and Escape Route Layout - Zone 2B C3 Hydrogenation |  | Class Final | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F75-0012 | Life Saving Equipment and Escape Route Layout - Zone 2D Process Cold Compressor |  | Class Final | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F75-0013 | Life Saving Equipment and Escape Route Layout - Zone 2E Cracked Gas Compressor |  | Class Final | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F75-0014 | Life Saving Equipment and Escape Route Layout - Zone 3A Butadiene Extraction Unit |  | Class Final | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| FF | OL1-2F75-0015 | Life Saving Equipment and Escape Route Layout - Zone 2C Hot Fractionation/GHU Unit |  | Class Final | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
Category Code: F90 Vendor Document
Category Code: F91 Index/List
Category Code: F92 Procedures & Standards
| FF | OL1-2F92-0001 | Fire And Gas Detection |  | Class Final | Purpose** | IFR | IMP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-18 | 2019-02-15
[6 empty] | Revised Plan |  | 2019-05-16
[6 empty] | Issue Actual | 2019-03-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01125
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R1
Category Code: F93 Policy , Guidelines & Memo
Category Code: F94 Forms & Templates
Category Code: F95 Progress/Status Reports |  |  |  |  | Class 2 | Purpose**
Category Code: G01 All Project Philosophies and Process design standard and All Project Studies Records | [5 empty] | Rev.
| PE | OL1-2G01-0001 | JSD FOR P & ID PREPARATION |  |  | Purpose** | IFR | IFA | IMP
[6 empty] | Rev. |  | A | 0
[6 empty] | Issue Plan | 2018-07-31 |  | 2019-03-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-07-31 | 2019-03-01
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00006 | TPSK-LSPA1-T-PE-00965
[6 empty] | Return Date |  | 2018-08-21 | 2019-04-05
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G01-0002 | Cold Box Design Specification |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00123
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G01-0003 | Plate-Fin Exchanger Design Specification |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00123
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G01-0004 | Tray Design Specification |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-01-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00624
[6 empty] | Return Date | 2019-02-04
[6 empty] | Owner Cmmt* | R1
Category Code: G02 Design Basis
| PE | OL1-2G02-0001 | PROCESS BASIS OF DESIGN |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-07-30 | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00002 | TPSK-LSPA1-T-PE-01154
[6 empty] | Return Date |  | 2018-08-17
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G02-0002 | EQUIPMENT BASIS OF DESIGN |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-07-30 | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00002 | TPSK-LSPA1-T-PE-01154
[6 empty] | Return Date |  | 2018-08-17
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G02-0003 | FLARE AND BLOWDOWN SYSTEM BASIS OF DESIGN |  | Class 2 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2018-09-04 |  | 2019-06-13
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-06
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00034
[6 empty] | Return Date |  | 2018-09-28
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G02-0006 | FURNACE BASIS OF DESIGN |  | Class 3 | Purpose** | IFR | IFA | IFF
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2018-07-31 |  | 2018-11-27
Revised Plan
[6 empty] | Issue Actual |  | 2018-07-31
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00004
[6 empty] | Return Date |  | 2018-08-17
[6 empty] | Owner Cmmt* |  | A3
Category Code: G03 Conceptual Design
Category Code: G04 Process Design Package
Category Code: G05 Equipment and Unit Functional Design
| PE | OL1-2G05-1001 | AREA BASIS OF DESIGN - 10 FEED |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-07 | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-01154
[6 empty] | Return Date |  | 2018-08-27 | 2019-04-22
[6 empty] | Owner Cmmt* |  | A3 | A1
| PE | OL1-2G05-1101 | SIZING OF STEAM DRUM & SUPERHEATER PSVS |  | Class 2 | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-10
[6 empty] | Revised Plan |  | 2019-10-15
[6 empty] | Issue Actual | 2019-01-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00769
[6 empty] | Return Date | 2019-03-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G05-1201 | Steam Drum and Superheater PSVs Sizing Calculation |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-01-30 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00769 | TPSK-LSPA1-T-PE-01513
[6 empty] | Return Date | 2019-03-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G05-2001 | AREA BASIS OF DESIGN - 20/21 QUENCH |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-07 | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-01224
[6 empty] | Return Date |  | 2018-08-27
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G05-2101 | SIZING OF STEAM DRUM & SUPERHEATER PSVS |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-10
[6 empty] | Revised Plan |  | 2019-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G05-2201 | AREA BASIS OF DESIGN - 22/24 COMPRESSION |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-13 | 2019-04-08
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00022 | TPSK-LSPA1-T-PE-01272
[6 empty] | Return Date |  | 2018-09-05
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G05-2301 | AREA BASIS OF DESIGN - 23 CAUSTIC |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-08 | 2019-04-11
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00014 | TPSK-LSPA1-T-PE-01317
[6 empty] | Return Date |  | 2018-08-31
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G05-2501 | AREA BASIS OF DESIGN - 25 COLD FRACTIONATION |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-07 | 2019-04-08
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-01276
[6 empty] | Return Date |  | 2018-08-27
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G05-2601 | AREA BASIS OF DESIGN - 26 HOT FRACTIONATION |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-08 | 2019-04-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00014 | TPSK-LSPA1-T-PE-01249
[6 empty] | Return Date |  | 2018-08-31
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G05-2602 | AREA BASIS OF DESIGN - 262 C3 HYDROGENATION |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-12 | 2019-04-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00307 | TPSK-LSPA1-T-PE-01510
[6 empty] | Return Date |  | 2019-02-04
[6 empty] | Owner Cmmt* |  | A1
| PE | OL1-2G05-2701 | AREA BASIS OF DESIGN - 270 GHU-1 |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-12 | 2019-04-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00307 | TPSK-LSPA1-T-PE-01510
[6 empty] | Return Date |  | 2019-02-04
[6 empty] | Owner Cmmt* |  | A1
| PE | OL1-2G05-2702 | AREA BASIS OF DESIGN - 275 C4/C5 HYDROGENATION |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-12 | 2019-05-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00307 | TPSK-LSPA1-T-PE-01667
[6 empty] | Return Date |  | 2019-02-04
[6 empty] | Owner Cmmt* |  | A1
| PE | OL1-2G05-2801 | AREA BASIS OF DESIGN - 28 REFRIG |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-13 | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00022 | TPSK-LSPA1-T-PE-01224
[6 empty] | Return Date |  | 2018-09-05
[6 empty] | Owner Cmmt* |  | A1
| PE | OL1-2G05-3001 | AREA BASIS OF DESIGN - 30 BDU |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  |  | 2019-05-16
[6 empty] | Issue Actual |  | 2018-10-09
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00150
[6 empty] | Return Date |  | 2019-04-02
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G05-5001 | AREA BASIS OF DESIGN - 50 ISBL SUPPORTING UTILITIES |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  |  | 2019-05-16
[6 empty] | Issue Actual |  | 2018-07-31
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00003
[6 empty] | Return Date |  | 2018-08-17
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G05-5301 | AREA BASIS OF DESIGN - 53 COOLING WATER TOWER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-08-09 |  | 2019-03-21
[6 empty] | Revised Plan |  |  | 2019-06-03
[6 empty] | Issue Actual |  | 2018-07-31 | 2018-09-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00003 | TPSK-LSPA1-T-PE-00003
[6 empty] | Return Date |  | 2018-08-17
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G05-5501 | AREA BASIS OF DESIGN - 55 FLARE SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2018-08-09 |  | 2019-03-21
[6 empty] | Revised Plan |  |  | 2019-06-03
[6 empty] | Issue Actual |  | 2018-08-09
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00016
[6 empty] | Return Date |  | 2018-08-29
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G05-5601 | AREA BASIS OF DESIGN - 56 WASTEWATER TREATMENT SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-09 |  | 2019-03-21 | 2019-03-21
[6 empty] | Revised Plan |  |  | 2019-06-03 | 2019-06-03
[6 empty] | Issue Actual |  | 2018-08-07 | 2018-09-26 | 2019-02-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-00091 | TPSK-LSPA1-T-PE-00920
[6 empty] | Return Date |  | 2018-08-27 | 2018-10-12 | 2019-03-29
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1
Category Code: G06 Process simulation model |  |  |  |  | Class 2 | Purpose**
Category Code: G20 Design calculations | [5 empty] | Rev.
Category Code: G21 Hydraulic Calculation | [5 empty] | Issue Plan
| PE | OL1-2G21-12XX | HYDRAULICS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G21-13XX | HYDRAULICS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G21-14XX | HYDRAULICS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G21-15XX | HYDRAULICS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G21-16XX | HYDRAULICS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G22 Flare Calculation
| PE | OL1-2G22-0001 | FLARE LOAD SUMMARY |  | Class 2 | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-10-25 | 2019-06-20 | 2019-10-10
Revised Plan
[6 empty] | Issue Actual | 2018-10-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00229
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
Category Code: G23 Sizing data for the relief and blowdown systems
| PE | OL1-2G23-1001 | PSV-1001 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-1002 | PSV-1002 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380
Return Date
Owner Cmmt*
| PE | OL1-2G23-1003 | PSV-1003 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380
Return Date
Owner Cmmt*
| PE | OL1-2G23-1004 | PSV-1004 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380
Return Date
Owner Cmmt*
| PE | OL1-2G23-1006 | PSV-1006 and PSV-1009 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-1007 | PSV-1007 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-1008 | PSV-1008 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380
Return Date
Owner Cmmt*
| PE | OL1-2G23-1010 | PSV-1010 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-1011 | PSV-1011 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380
Return Date
Owner Cmmt*
| PE | OL1-2G23-1012 | PSV-1012 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-1015 | PSV-1015 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-1016 | PSV-1016 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380
Return Date
Owner Cmmt*
| PE | OL1-2G23-1901 | PSV-1911 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488
Return Date
Owner Cmmt*
| PE | OL1-2G23-1902 | PSV-1912 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488
Return Date
Owner Cmmt*
| PE | OL1-2G23-2201 | PSV-2201 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-2202 | PSV-2210 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-2203 | PSV-2225 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-2204 | PSV-2230 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-2205 | PSV-2235 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-2206 | PSV-2246 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01475
Return Date
Owner Cmmt*
| PE | OL1-2G23-2207 | PSV-2255 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-2208 | PSV-2260 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-2209 | PSV-2265 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-2210 | PSV-2266 A-B Sizing Calulation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01475
Return Date
Owner Cmmt*
| PE | OL1-2G23-2303 | PSV-2316 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01530
Return Date
Owner Cmmt*
| PE | OL1-2G23-2304 | PSV-2322 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2305 | PSV-2327 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2306 | PSV-2332 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2307 | PSV-2335 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2401 | PSV-2401 Sizing Calculaiton |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-2402 | PSV-2403 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-2403 | PSV-2405 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-2404 | PSV-2407 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-2405 | PSV-2408 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
Return Date
Owner Cmmt*
| PE | OL1-2G23-2406 | PSV-2410 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435
Return Date
Owner Cmmt*
| PE | OL1-2G23-2407 | PSV-2411 Sizing Calcuation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435
Return Date
Owner Cmmt*
| PE | OL1-2G23-2408 | PSV-2414 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508
Return Date
Owner Cmmt*
| PE | OL1-2G23-2409 | PSV-2415 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01530
Return Date
Owner Cmmt*
| PE | OL1-2G23-2410 | PSV-2416 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508
Return Date
Owner Cmmt*
| PE | OL1-2G23-2412 | PSV-2419 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488
Return Date
Owner Cmmt*
| PE | OL1-2G23-2413 | PSV-2422 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2414 | PSV-2423 A-B-C Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2415 | PSV-2425 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2416 | PSV-2426 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2417 | PSV-2428 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2418 | PSV-2429 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01530
Return Date
Owner Cmmt*
| PE | OL1-2G23-2419 | PSV-2431 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2420 | PSV-2432 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2422 | PSV-2435 A-D Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2423 | PSV-2436 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2424 | PSV-2437 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2427 | PSV-2443 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2428 | PSV-2444 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2429 | PSV-2445 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2430 | PSV-2446 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2431 | PSV-2447 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2432 | PSV-2448 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2433 | PSV-2449 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2434 | PSV-2450 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488
Return Date
Owner Cmmt*
| PE | OL1-2G23-2435 | PSV-2440 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
Return Date
Owner Cmmt*
| PE | OL1-2G23-2436 | PSV-2413 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01530
Return Date
Owner Cmmt*
| PE | OL1-2G23-2501 | PSV-2504 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488
Return Date
Owner Cmmt*
| PE | OL1-2G23-2503 | PSV-2514 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488
Return Date
Owner Cmmt*
| PE | OL1-2G23-2504 | PSV-2517 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435
Return Date
Owner Cmmt*
| PE | OL1-2G23-2506 | PSV-2522 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01382
Return Date
Owner Cmmt*
| PE | OL1-2G23-2507 | PSV-2524 Sizing Calculation |  | Class Final | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-25 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488 | TPSK-LSPA1-T-PE-01530
Return Date
Owner Cmmt*
| PE | OL1-2G23-2508 | PSV-2525 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01382
Return Date
Owner Cmmt*
| PE | OL1-2G23-2509 | PSV-2530 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395
Return Date
Owner Cmmt*
| PE | OL1-2G23-2510 | PSV-2531 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01382
Return Date
Owner Cmmt*
| PE | OL1-2G23-2511 | PSV-2535 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395
Return Date
Owner Cmmt*
| PE | OL1-2G23-2512 | PSV-2539 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435
Return Date
Owner Cmmt*
| PE | OL1-2G23-2513 | PSV-2540 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395
Return Date
Owner Cmmt*
| PE | OL1-2G23-2514 | PSV-2544 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435
Return Date
Owner Cmmt*
| PE | OL1-2G23-2515 | PSV-2545 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435
Return Date
Owner Cmmt*
| PE | OL1-2G23-2517 | PSV-2548 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395
Return Date
Owner Cmmt*
| PE | OL1-2G23-2519 | PSV-2551 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488
Return Date
Owner Cmmt*
| PE | OL1-2G23-2520 | PSV-2555 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395
Return Date
Owner Cmmt*
| PE | OL1-2G23-2521 | PSV-2553 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435
Return Date
Owner Cmmt*
| PE | OL1-2G23-2522 | PSV-2560 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395
Return Date
Owner Cmmt*
| PE | OL1-2G23-2524 | PSV-2556 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395
Return Date
Owner Cmmt*
| PE | OL1-2G23-2801 | PSV-2810 A-C Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508
Return Date
Owner Cmmt*
| PE | OL1-2G23-2802 | PSV-2815 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508
Return Date
Owner Cmmt*
| PE | OL1-2G23-2803 | PSV-2820 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508
Return Date
Owner Cmmt*
| PE | OL1-2G23-2804 | PSV-2805 A-D Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508
Return Date
Owner Cmmt*
| PE | OL1-2G23-2805 | PSV-2806 A-D Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508
Return Date
Owner Cmmt*
| PE | OL1-2G23-2806 | PSV-2823 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2807 | PSV-2826 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2808 | PSV-2829 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2810 | PSV-2835 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2811 | PSV-2836 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2813 | PSV-2838 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2814 | PSV-2839 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2815 | PSV-2841 A-D Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2816 | PSV-2842 A-B Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2817 | PSV-2843 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2818 | PSV-2845 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2819 | PSV-2846 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2820 | PSV-2847 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2821 | PSV-2851 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2822 | PSV-2852 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2823 | PSV-2854 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2825 | PSV-2856 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2901 | PSV-2925 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2902 | PSV-2926 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2903 | PSV-2928 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2904 | PSV-2929 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2905 | PSV-2930 Sizing Calulation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2906 | PSV-2931 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
| PE | OL1-2G23-2907 | PSV-2932 Sizing Calculation |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
Return Date
Owner Cmmt*
Category Code: G30 Process Equipment Data Sheets
| PE | OL1-2G30-1000 | PROCESS EQUIPMENT DATA SHEET - 10-D-1000 - LPG FEED DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-25 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00227 | TPSK-LSPA1-T-PE-00463
[6 empty] | Return Date | 2018-12-05 | 2019-01-16
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-1001 | PROCESS EQUIPMENT DATA SHEET - 10-E-1000 - LPG VAPORIZER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00176 | TPSK-LSPA1-T-PE-00451
[6 empty] | Return Date | 2018-11-14 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1003 | PROCESS EQUIPMENT DATA SHEET - 10-E-1001 - LPG STEAM VAPORIZER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-16 | 2019-01-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00179 | TPSK-LSPA1-T-PE-00712
[6 empty] | Return Date | 2019-01-28 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-1005 | PROCESS EQUIPMENT DATA SHEET - 10-E-1005 - LPG FEED HEATER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2019-01-18 | 2019-03-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00176 | TPSK-LSPA1-T-PE-00680 | TPSK-LSPA1-T-PE-00999
[6 empty] | Return Date | 2018-11-14 | 2019-02-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1006 | Process Equipment Datasheet - 10-E-1006 - LPG Feed Steam Heater |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-06 | 2019-04-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00998 | TPSK-LSPA1-T-PE-01261
Return Date
Owner Cmmt*
| PE | OL1-2G30-1015 | PROCESS EQUIPMENT DATA SHEET - 10-E-1015 - LPG SUPERHEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00176 | TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-11-14 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1020 | PROCESS EQUIPMENT DATA SHEET - 10-E-1020 - LIQUID FEED HEATER |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-07 | 2019-01-18 | 2019-03-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00431 | TPSK-LSPA1-T-PE-00680 | TPSK-LSPA1-T-PE-00999
[6 empty] | Return Date | 2018-11-30 | 2019-01-16 | 2019-02-21
[6 empty] | Owner Cmmt* | R1 | R2 | R1
| PE | OL1-2G30-1051 | PROCESS EQUIPMENT DATA SHEET - 10-E-1050 - C2 FEED SUPERHEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00436
[6 empty] | Return Date | 2018-11-30 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1101 | PROCESS DATA SHEETS YIELDS FOR 36M FURNACE |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-08-15 | 2018-08-15
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00204 | TPSK-LSPA1-T-PE-00360
[6 empty] | Return Date | 2018-11-30 | 2018-12-27
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-1102 | AOCS PDS (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFI | IFD | IFF
[6 empty] | Rev. |  | 0 | 1
[6 empty] | Issue Plan | 2019-01-09 |  | 2019-03-06 | 2019-09-30
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-24 | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00224 | TPSK-LSPA1-T-PE-01232
Return Date
Owner Cmmt*
| PE | OL1-2G30-1105 | API FIRED HEATER DATA SHEET (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-09 | 2019-03-06 | 2019-09-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00814 | TPSK-LSPA1-T-PE-01322
Return Date
Owner Cmmt*
| PE | OL1-2G30-1106 | BURNERS PDS (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-10-30 | 2019-01-16 | 2019-01-16
Revised Plan
[6 empty] | Issue Actual | 2018-10-30 | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00241 | TPSK-LSPA1-T-PE-00756
[6 empty] | Return Date | 2018-11-27 | 2019-02-26
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-1107 | STEAM DRUM PDS (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-10-11 | 2018-12-03 | 2018-12-03 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2018-10-11 | 2018-12-12 | 2019-02-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00159 | TPSK-LSPA1-T-PE-00478 | TPSK-LSPA1-T-PE-00935
[6 empty] | Return Date | 2018-11-05 | 2019-02-11 | 2019-03-15
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-1108 | USX QUENCH EXCHANGERS PDS (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-09-19 | 2018-12-10 | 2018-12-10
Revised Plan
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00432
[6 empty] | Return Date | 2018-11-30 | 2019-02-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1109 | TLX 1 QUENCH EXCHANGER PDS (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-09-19 | 2018-12-10 | 2018-12-10 | 2018-12-10
Revised Plan
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-10 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00459 | TPSK-LSPA1-T-PE-01078
[6 empty] | Return Date | 2018-11-30 | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-1110 | TLX 2 QUENCH EXCHANGER PDS (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-09-19 | 2018-12-10 | 2018-12-10 | 2018-12-10
Revised Plan
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-10 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00459 | TPSK-LSPA1-T-PE-01078
[6 empty] | Return Date | 2018-11-30 | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-1111 | ID FAN DATA SHEET (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFD | IFF
[6 empty] | Rev. |  | B | C
[6 empty] | Issue Plan | 2018-09-26 | 2018-11-17 | 2018-11-17 | 2018-11-17
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-24 | 2019-03-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00222 | TPSK-LSPA1-T-PE-01079
[6 empty] | Return Date |  | 2018-11-30 | 2019-04-10
[6 empty] | Owner Cmmt* |  | R1 | R1
| PE | OL1-2G30-1112 | ATTEMPERATOR DATA SHEET (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-03-13 | 2019-03-13
Revised Plan
[6 empty] | Issue Actual | 2018-11-16 | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00330 | TPSK-LSPA1-T-PE-00752
[6 empty] | Return Date | 2018-12-13 | 2019-03-21
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-1151 | USC 36M EFFLUENT MOV - DATA SHEET |  | Class 2 | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-20 | 2019-03-05
Revised Plan
[6 empty] | Issue Actual | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521
[6 empty] | Return Date | 2019-01-28
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-1152 | USC 36M DECOKE MOV - DATA SHEET |  | Class 2 | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-20 | 2019-03-05
Revised Plan
[6 empty] | Issue Actual | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521
[6 empty] | Return Date | 2019-01-28
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-1153 | Process Equipment Datasheet 10-MOV-1102B USC 36M Decoke Effluent Bypass MOV |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521 | TPSK-LSPA1-T-PE-01195
[6 empty] | Return Date | 2019-01-28 | 2019-04-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-1201 | PROCESS DATA SHEETS YIELDS FOR 132 U FURNACE |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-08-15 | 2018-08-15
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00204 | TPSK-LSPA1-T-PE-00372
[6 empty] | Return Date | 2018-11-30 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1202 | AOCS PDS (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFI | IFD | IFF
[6 empty] | Rev. |  | 0 | 1
[6 empty] | Issue Plan | 2019-01-09 |  | 2019-03-06 | 2019-09-30
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-24 | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00224 | TPSK-LSPA1-T-PE-01232
Return Date
Owner Cmmt*
| PE | OL1-2G30-1205 | Process Equipment Datasheet - 10-H-1200/1600 - API Fired Heater Process Datasheet |  | Class Final | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-09 | 2019-03-06 | 2019-09-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00814 | TPSK-LSPA1-T-PE-01322
Return Date
Owner Cmmt*
| PE | OL1-2G30-1206 | BURNERS PDS (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-10-30 | 2019-01-16 | 2019-01-16
Revised Plan
[6 empty] | Issue Actual | 2018-10-30 | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00241 | TPSK-LSPA1-T-PE-00756
[6 empty] | Return Date | 2018-12-27 | 2019-02-26
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-1207 | STEAM DRUM PDS (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-10-11 | 2018-12-03 | 2018-12-03 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2018-10-11 | 2018-12-12 | 2019-02-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00159 | TPSK-LSPA1-T-PE-00478 | TPSK-LSPA1-T-PE-00935
[6 empty] | Return Date | 2018-11-05 | 2019-02-11 | 2019-03-15
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-1208 | SLE QUENCH EXCHANGERS PDS (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-09-19 | 2018-12-10 | 2018-12-10
Revised Plan
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00433
[6 empty] | Return Date | 2018-11-30 | 2019-02-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1209 | TLX QUENCH EXCHANGER PDS (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-09-19 | 2018-12-10 | 2018-12-10 | 2018-12-10
Revised Plan
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-10 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00449 | TPSK-LSPA1-T-PE-01078
[6 empty] | Return Date | 2018-11-30 | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-1211 | ID FAN DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFD | IFF
[6 empty] | Rev. |  | B | C
[6 empty] | Issue Plan | 2018-09-26 | 2018-11-17 | 2018-11-17 | 2018-11-17
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-24 | 2019-03-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00222 | TPSK-LSPA1-T-PE-01079
[6 empty] | Return Date |  | 2018-11-30 | 2019-04-10
[6 empty] | Owner Cmmt* |  | R1 | R1
| PE | OL1-2G30-1212 | ATTEMPERATOR DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-11-16 | 2019-03-13 | 2019-03-13 | 2019-03-13
Revised Plan
[6 empty] | Issue Actual | 2018-11-16 | 2019-01-29 | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00330 | TPSK-LSPA1-T-PE-00752 | TPSK-LSPA1-T-PE-01220
[6 empty] | Return Date | 2018-12-13 | 2019-03-21
[6 empty] | Owner Cmmt* | R1 | R2
| PE | OL1-2G30-1213 | MIXING TEE PDS (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-09 | 2019-01-09
Revised Plan
[6 empty] | Issue Actual | 2018-12-07 | 2019-02-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00434 | TPSK-LSPA1-T-PE-00936
[6 empty] | Return Date |  | 2019-03-15
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-1251 | USC 132SU EFFLUENT MOV - DATA SHEET |  | Class 2 | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-20 | 2019-03-05
Revised Plan
[6 empty] | Issue Actual | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521
[6 empty] | Return Date | 2019-01-28
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1252 | USC 132SU DECOKE MOV - DATA SHEET |  | Class 2 | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-20 | 2019-03-05
Revised Plan
[6 empty] | Issue Actual | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521
[6 empty] | Return Date | 2019-01-28
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1253 | Process Equipment Datasheet 10-MOV-1202B USC 132U Decoke Effluent Bypass MOV |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521 | TPSK-LSPA1-T-PE-01195
[6 empty] | Return Date | 2019-01-28 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1911 | Process Equipment Datasheet - 10-D-1910 - DMDS Bulk Storage Drum |  | Class Final | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22 | 2019-03-19 | 2019-04-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00686 | TPSK-LSPA1-T-PE-01096 | TPSK-LSPA1-T-PE--01280
[6 empty] | Return Date | 2019-02-21 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1912 | Process Equipment Datasheet - 10-D-1912 - DMDS Injection Drum |  | Class Final | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22 | 2019-03-19 | 2019-04-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00686 | TPSK-LSPA1-T-PE-01096 | TPSK-LSPA1-T-PE-01280
[6 empty] | Return Date | 2019-02-21 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1913 | Process Equipment Datasheet - 10-P-1910 A-B - DMDS Feed Injection Pump |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22 | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE--00687 | TPSK-LSPA1-T-PE-00963
[6 empty] | Return Date | 2019-02-21 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1914 | Process Equipment Datasheet - 10-P-1912 - DMDS Presulfiding Injection Pump |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22 | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE--00687 | TPSK-LSPA1-T-PE-00963
[6 empty] | Return Date | 2019-02-21 | 2019-03-21
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-1950 | PROCESS EQUIPMENT DATA SHEET - 10-PK-1950 - DECOKE AIR COMPRESSOR PACKAGE |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-29 | 2018-09-28 | 2018-10-30
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00031 | TPSK-LSPA1-T-PE-00114 | TPSK-LSPA1-T-PE-00242
[6 empty] | Return Date |  | 2018-09-28 | 2018-10-24 | 2018-11-30
[6 empty] | Owner Cmmt* |  | A3 | R2 | A1
| PE | OL1-2G30-2000 | PROCESS EQUIPMENT DATA SHEET - 10-T-2000 - QUENCH OIL TOWER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-12 | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00162 | TPSK-LSPA1-T-PE-00402
[6 empty] | Return Date | 2018-11-05 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2006 | PROCESS EQUIPMENT DATA SHEET - 10-P-2006 - QUENCH OIL PUMP |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-20 | 2018-10-22 | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00071 | TPSK-LSPA1-T-PE-00202 | TPSK-LSPA1-T-PE-01159
[6 empty] | Return Date |  | 2018-10-09 | 2018-11-30 | 2019-04-12
[6 empty] | Owner Cmmt* |  | A3 | A1 | R1
| PE | OL1-2G30-2010 | PROCESS EQUIPMENT DATA SHEET - 10-F-2008 - QUENCH OIL FILTER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00606
[6 empty] | Return Date | 2018-12-27 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2014 | PROCESS EQUIPMENT DATA SHEET - 10-F-2009 - QO PUMP PURGE OIL FILTER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00606
[6 empty] | Return Date | 2018-12-27 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2015 | PROCESS EQUIPMENT DATA SHEET - 10-E-2008 - VLP STEAM GENERATORS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-09 | 2019-01-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00305 | TPSK-LSPA1-T-PE-00632
[6 empty] | Return Date | 2018-12-13 | 2019-02-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2020 | PROCESS EQUIPMENT DATA SHEET - 10-T-2020 - LIGHT FUEL OIL STRIPPER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00238 | TPSK-LSPA1-T-PE-00437
[6 empty] | Return Date | 2018-12-04 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2024 | PROCESS EQUIPMENT DATA SHEET - 10-P-2026 - LIGHT FUEL OIL PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00648
[6 empty] | Return Date | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2025 | PROCESS EQUIPMENT DATA SHEET - 10-F-2026 - CRACKER BOTTOMS PRODUCT FILTER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00676
[6 empty] | Return Date | 2018-12-27 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2026 | PROCESS EQUIPMENT DATA SHEET - 10-E-2026 - FUEL OIL PRODUCT COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-09 | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00298 | TPSK-LSPA1-T-PE-00680
[6 empty] | Return Date | 2018-12-17 | 2019-02-21
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2028 | PROCESS EQUIPMENT DATA SHEET - 10-F-2028 - FO PUMP PURGE OIL FILTER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00676
[6 empty] | Return Date | 2018-12-27 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2036 | PROCESS EQUIPMENT DATA SHEET - 10-X-2036 - QUENCH FITTING |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2018-11-20 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00338 | TPSK-LSPA1-T-PE-00604
[6 empty] | Return Date | 2018-12-27 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2040 | PROCESS EQUIPMENT DATA SHEET - 10-T-2040 - HEAVY FUEL OIL STRIPPER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-12 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00162 | TPSK-LSPA1-T-PE-00347
[6 empty] | Return Date | 2018-11-05 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2046 | PROCESS EQUIPMENT DATA SHEET - 10-P-2046 - HEAVY FUEL OIL PUMP |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-14 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00648 | TPSK-LPSA1-T-PE-01402
[6 empty] | Return Date | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2048 | PROCESS EQUIPMENT DATA SHEET - 10-E-2048 - HEAVY FUEL OIL PRODUCT COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-09 | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00298 | TPSK-LSPA1-T-PE-00680
[6 empty] | Return Date | 2018-12-17 | 2019-02-21
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2049 | PROCESS EQUIPMENT DATA SHEET - 10-F-2048 - HEAVY FUEL OIL FILTERS |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-18 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00676 | TPSK-LSPA1-T-PE-01401
[6 empty] | Return Date | 2018-12-27 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2090 | PROCESS EQUIPMENT DATA SHEET - 10-D-2090 - QUENCH OIL DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-27 | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00368 | TPSK-LSPA1-T-PE-00964
[6 empty] | Return Date | 2019-02-25 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2091 | PROCESS EQUIPMENT DATA SHEET - 10-P-2090 - QUENCH OIL DRAIN DRUM PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-27 | 2019-03-01 | 2019-03-26 | 2019-04-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00371 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-01159 | TPSK-LSPA1-T-PE-01255
[6 empty] | Return Date | 2019-02-25 | 2019-03-21 | 2019-04-12
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2092 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2090 - QUENCH OIL DRAIN SUMP EDUCTOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date |  | 2019-01-28
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-2100 | PROCESS EQUIPMENT DATA SHEET - 10-T-2100 - QUENCH WATER TOWER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-07 | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00238 | TPSK-LSPA1-T-PE-00437 | TPSK-LSPA1-T-PE-01184
[6 empty] | Return Date | 2018-12-04 | 2019-01-16 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2101 | PROCESS EQUIPMENT DATA SHEET - 10-E-2100 - QUENCH WATER COOLER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-10-08 | 2019-04-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00143 | TPSK-LSPA1-T-PE-01261
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A1
| PE | OL1-2G30-2104 | PROCESS EQUIPMENT DATA SHEET - 10-F-2105 - QUENCH OIL REFLUX FILTER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-07 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00606 | TPSK-LSPA1-T-PE-01072
[6 empty] | Return Date | 2018-12-27 | 2019-02-04 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2105 | PROCESS EQUIPMENT DATA SHEET - 10-P-2105 - QUENCH OIL REFLUX PUMP |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-07 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00603 | TPSK-LSPA1-T-PE-01159
[6 empty] | Return Date | 2018-12-27 | 2019-02-04 | 2019-04-12
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2106 | PROCESS EQUIPMENT DATA SHEET - 10-P-2106 - QUENCH WATER PUMP |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-20 | 2018-10-22 | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00070 | TPSK-LSPA1-T-PE-00202 | TPSK-LSPA1-T-PE-01159
[6 empty] | Return Date |  | 2018-10-09 | 2018-11-30 | 2019-04-12
[6 empty] | Owner Cmmt* |  | A1 | A1 | R1
| PE | OL1-2G30-2110 | PROCESS EQUIPMENT DATA SHEET - 10-D-2110 - INTERCEPTION DRUM |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-10 | 2019-01-18 | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00453 | TPSK-LSPA1-T-PE-00678 | TPSK-LSPA1-T-PE-00964
[6 empty] | Return Date | 2019-01-16 | 2019-02-21 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-2120 | PROCESS EQUIPMENT DATA SHEET - 10-T-2120 - DISTILLTATE STRIPPER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00253 | TPSK-LSPA1-T-PE-00401 | TPSK-LSPA1-T-PE-00437
[6 empty] | Return Date | 2018-12-04 | 2019-01-14 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2125 | PROCESS EQUIPMENT DATA SHEET - 10-E-2125 - DISTILLATE STRIPPER REBOILER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00265 | TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-12-10 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2126 | PROCESS EQUIPMENT DATA SHEET - 10-P-2126 - DISTILLATE STRIPPER BOTTOMS PUMP |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-27 | 2019-03-01 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00371 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-01383
[6 empty] | Return Date | 2019-02-25 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2136 | PROCESS EQUIPMENT DATA SHEET - 10-D-2136 - PROCESS WATER FEED COALESCER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-10 | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00453 | TPSK-LSPA1-T-PE-00678
[6 empty] | Return Date | 2019-01-16 | 2019-02-21
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2137 | PROCESS EQUIPMENT DATA SHEET - 10-E-2136 - PROCESS WATER STRIPPER FEED HEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-18 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194 | TPSK-LSPA1-T-PE-00467
[6 empty] | Return Date | 2018-11-26 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2138 | PROCESS EQUIPMENT DATA SHEET - 10-F-2136 - PROCESS WATER FEED FILTER |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02 | 2019-01-02 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-07 | 2019-03-15 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00606 | TPSK-LSPA1-T-PE-01072 | TPSK-LSPA1-T-PE-01401
[6 empty] | Return Date | 2018-12-27 | 2019-02-04 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2139 | Process Equipment Datasheet - 10-F-2137 A-B - Process Water Coalescer Prefilters |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01401
Return Date
Owner Cmmt*
| PE | OL1-2G30-2140 | PROCESS EQUIPMENT DATA SHEET - 10-T-2140 - PROCESS WATER STRIPPER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-17 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00189 | TPSK-LSPA1-T-PE-00401
[6 empty] | Return Date | 2018-11-26 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2145 | PROCESS EQUIPMENT DATA SHEET - 10-E-2145 - PROCESS WATER STRIPPER REBOILER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-18 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194 | TPSK-LSPA1-T-PE-00605
[6 empty] | Return Date | 2018-12-27 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2146 | PROCESS EQUIPMENT DATA SHEET - 10-P-2146 - DSG FEED PUMP |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-20 | 2018-10-22
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00069 | TPSK-LSPA1-T-PE-00202
[6 empty] | Return Date |  | 2018-10-09 | 2018-11-30
[6 empty] | Owner Cmmt* |  | A3 | A1
| PE | OL1-2G30-2147 | PROCESS EQUIPMENT DATA SHEET - 10-E-2146 - DSG FEED HEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-18 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194 | TPSK-LSPA1-T-PE-00605
[6 empty] | Return Date | 2018-12-27 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2160 | PROCESS EQUIPMENT DATA SHEET - 10-D-2160 - DILUTION STEAM GENERATOR |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-28 | 2019-01-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00115 | TPSK-LSPA1-T-PE-00620
[6 empty] | Return Date |  | 2018-11-05 | 2019-02-11
[6 empty] | Owner Cmmt* |  | A3 | R2
| PE | OL1-2G30-2161 | PROCESS EQUIPMENT DATA SHEET - 10-E-2160 - DILUTION STEAM SUPERHEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-18 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194 | TPSK-LSPA1-T-PE-00467
[6 empty] | Return Date | 2018-11-26 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2165 | PROCESS EQUIPMENT DATA SHEET - 10-E-2165 - DSG REBOILER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-18 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194 | TPSK-LSPA1-T-PE-00467
[6 empty] | Return Date | 2018-11-26 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2166 | PROCESS EQUIPMENT DATA SHEET - 10-E-2166 - DSG BLOWDOWN COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-23 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00209 | TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-11-30 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2190 | PROCESS EQUIPMENT DATA SHEET - 10-D-2190 - QUENCH WATER DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-27 | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00368 | TPSK-LSPA1-T-PE-00964
[6 empty] | Return Date | 2019-02-25 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2191 | PROCESS EQUIPMENT DATA SHEET - 10-P-2190 - QUENCH WATER DRAIN DRUM PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00346 | TPSK-LSPA1-T-PE-00603
[6 empty] | Return Date | 2018-12-27 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2192 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2190 - QUENCH WATER DRAING SUMP EDUCTOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date |  | 2019-01-28
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-2200 | PROCESS EQUIPMENT DATA SHEET - 10-C-2200 - CRACKED GAS COMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-22 | 2018-09-17
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00055
[6 empty] | Return Date |  | 2018-09-11
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2206 | PROCESS EQUIPMENT DATA SHEET - 10-E-2206 - WASH WATER COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-28 | 2019-01-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00381 | TPSK-LSPA1-T-PE-00655
[6 empty] | Return Date | 2019-01-14 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2210 | PROCESS EQUIPMENT DATA SHEET - 10-D-2210 - CG 1ST STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00448
[6 empty] | Return Date | 2018-11-05 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2211 | PROCESS EQUIPMENT DATA SHEET - 10-E-2210 - CG 1ST STAGE AFTERCOOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00266 | TPSK-LSPA1-T-PE-00479
[6 empty] | Return Date | 2018-12-10 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2212 | PROCESS EQUIPMENT DATA SHEET - 10-P-2210 - CG 1ST STAGE CONDENSATE PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00593
[6 empty] | Return Date | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2220 | PROCESS EQUIPMENT DATA SHEET - 10-D-2220 - CG 2ND STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-12-10 | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00448 | TPSK-LSPA1-T-PE-00678
[6 empty] | Return Date | 2018-11-05 | 2019-01-16 | 2019-02-21
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-2221 | PROCESS EQUIPMENT DATA SHEET - 10-E-2220 - CG 2ND STAGE AFTERCOOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-11-30 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2222 | PROCESS EQUIPMENT DATA SHEET - 10-P-2220 - CG 2ND STAGE CONDENSED HC PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00593
[6 empty] | Return Date | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2230 | PROCESS EQUIPMENT DATA SHEET - 10-D-2230 - CG 3RD STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00448
[6 empty] | Return Date | 2018-11-05 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2231 | PROCESS EQUIPMENT DATA SHEET - 10-E-2230 - CG 3RD STAGE AFTERCOOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-11-30 | 2019-01-16
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2240 | PROCESS EQUIPMENT DATA SHEET - 10-D-2240 - CG 4TH STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00175 | TPSK-LSPA1-T-PE-00448
[6 empty] | Return Date | 2018-11-14 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2241 | PROCESS EQUIPMENT DATA SHEET - 10-E-2240 - CG 4TH STAGE AFTERCOOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00436
[6 empty] | Return Date | 2018-11-30 | 2019-01-16
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2245 | PROCESS EQUIPMENT DATA SHEET - 10-D-2245 - CG 4TH STAGE DISCHARGE DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00264 | TPSK-LSPA1-T-PE-00480
[6 empty] | Return Date | 2018-12-10 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2300 | PROCESS EQUIPMENT DATA SHEET - 10-T-2300 - CAUSTIC TOWER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-18 | 2018-11-08 | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00060 | TPSK-LSPA1-T-PE-00290 | TPSK-LSPA1-T-PE-00597
[6 empty] | Return Date |  | 2018-10-24 | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* |  | A3 | R2 | A1
| PE | OL1-2G30-2301 | PROCESS EQUIPMENT DATA SHEET - 10-X-2300 - CAUSTIC DILUENT MIXER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-11-28 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00383 | TPSK-LSPA1-T-PE-00600
[6 empty] | Return Date | 2018-11-14 | 2019-01-14 | 2019-02-04
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2302 | PROCESS EQUIPMENT DATA SHEET - 10-P-2302 - STRONG CAUSTIC CIRCULATING PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174 | TPSK-LSPA1-T-PE-00524
[6 empty] | Return Date | 2018-11-14 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2304 | PROCESS EQUIPMENT DATA SHEET - 10-P-2304 - INTERMEDIATE CAUSTIC CIRCULATING PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174 | TPSK-LSPA1-T-PE-00382
[6 empty] | Return Date | 2018-11-14 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2305 | PROCESS EQUIPMENT DATA SHEET - 10-E-2305 - CAUSTIC TOWER FEED HEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00259 | TPSK-LSPA1-T-PE-00523
[6 empty] | Return Date | 2018-12-10 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2306 | PROCESS EQUIPMENT DATA SHEET - 10-P-2306 - WEAK CAUSTIC CIRCULATING PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174 | TPSK-LSPA1-T-PE-00382
[6 empty] | Return Date | 2018-11-14 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2307 | PROCESS EQUIPMENT DATA SHEET - 10-F-2306 - WEAK CAUSTIC STRAINER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-13 | 2019-01-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00205 | TPSK-LSPA1-T-PE-00493 | TPSK-LSPA1-T-PE-00775
[6 empty] | Return Date | 2018-11-30 | 2019-01-22 | 2019-02-28
[6 empty] | Owner Cmmt* | R1 | R2 | R1
| PE | OL1-2G30-2308 | PROCESS EQUIPMENT DATA SHEET - 10-X-2306 - WEAK CAUSTIC / WASH OIL MIXER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00383
[6 empty] | Return Date | 2018-11-14 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2309 | PROCESS EQUIPMENT DATA SHEET - 10-D-2305 - YELLOW OIL DRUM |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-27 | 2019-01-11 | 2019-04-04 | 2019-04-16
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00102 | TPSK-LSPA1-T-PE-00634 | TPSK-LSPA1-T-PE-01260 | TPSK-LSPA1-T-PE-01377
[6 empty] | Return Date |  | 2018-11-14 | 2019-02-11
[6 empty] | Owner Cmmt* |  | A3 | R1
| PE | OL1-2G30-2310 | PROCESS EQUIPMENT DATA SHEET - 10-D-2310 - SPENT CAUSTIC DEOILING DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00254 | TPSK-LSPA1-T-PE-00599
[6 empty] | Return Date | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2311 | PROCESS EQUIPMENT DATA SHEET - 10-P-2310 - WASH OIL CIRCULATING PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174 | TPSK-LSPA1-T-PE-00524
[6 empty] | Return Date | 2018-11-14 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2313 | PROCESS EQUIPMENT DATA SHEET - 10-X-2312 - SPENT WASH OIL MIXER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00525
[6 empty] | Return Date | 2018-11-14 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2314 | PROCESS EQUIPMENT DATA SHEET - 10-F-2310 - WASH OIL CIRCULATION FILTER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00205 | TPSK-LSPA1-T-PE-00493
[6 empty] | Return Date | 2018-11-30 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2315 | PROCESS EQUIPMENT DATA SHEET - 10-X-2310 - SPENT CAUSTIC MIXER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00525
[6 empty] | Return Date | 2018-11-14 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2316 | PROCESS EQUIPMENT DATA SHEET - 10-D-2316 - SPENT CAUSTIC DEGASSING DRUM |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2019-01-11 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00175 | TPSK-LSPA1-T-PE-00634 | TPSK-LSPA1-T-PE-01377
[6 empty] | Return Date | 2018-11-26 | 2019-02-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2319 | PROCESS EQUIPMENT DATA SHEET - 10-F-2320 - SPENT CAUSTIC PUMP DISCHARGE FILTER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00255 | TPSK-LSPA1-T-PE-00493
[6 empty] | Return Date | 2018-12-10 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2320 | PROCESS EQUIPMENT DATA SHEET - 10-TK-2320 - SPENT CAUSTIC STORAGE TANK |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-20 | 2018-10-22
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00068 | TPSK-LSPA1-T-PE-00203
[6 empty] | Return Date |  | 2018-10-09 | 2018-11-30
[6 empty] | Owner Cmmt* |  | A3 | A1
| PE | OL1-2G30-2321 | PROCESS EQUIPMENT DATA SHEET - 10-P-2320 - SPENT CAUSTIC PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00252 | TPSK-LSPA1-T-PE-00598
[6 empty] | Return Date | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2322 | PROCESS EQUIPMENT DATA SHEET - 10-D-2322 - SKIM OIL DRUM |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-28 | 2019-03-25 | 2019-04-16 | 2019-05-13
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00111 | TPSK-LSPA1-T-PE-01142 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01652
[6 empty] | Return Date |  | 2019-02-25 | 2019-04-22
[6 empty] | Owner Cmmt* |  | A1 | TP
| PE | OL1-2G30-2323 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2322 - SKIM OIL SUMP EDUCTOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date |  | 2019-01-28
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-2324 | Process Equipment Datasheet - 10-TK-2300 - Fresh Caustic Day Tank |  | Class Final | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-13 | 2019-01-29 | 2019-02-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00495 | TPSK-LSPA1-T-PE-00760 | TPSK-LSPA1-T-PE-00937
[6 empty] | Return Date | 2019-01-22 | 2019-02-25 | 2019-03-15
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-2325 | Process Equipment Datasheet - 10-P-2300 A-B - 10 Percent Caustic Makeup Pump |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00526 | TPSK-LSPA1-T-PE-00759
[6 empty] | Return Date | 2019-01-28 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2326 | PROCESS EQUIPMENT DATA SHEET - 10-E-2326 - SPENT CAUSTIC STRIPPER FEED HEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-28 | 2019-01-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00381 | TPSK-LSPA1-T-PE-00690
[6 empty] | Return Date | 2019-01-14 | 2019-03-05
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2327 | PROCESS EQUIPMENT DATA SHEET - 10-D-2326 - SPENT CAUSTIC STRIPPER FEED HTR COND POT |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-25 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01152 | TPSK-LSPA1-T-PE-01517
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2330 | PROCESS EQUIPMENT DATA SHEET - 10-T-2330 - SPENT CAUSTIC STRIPPER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-01-21 |  |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-10-11 | 2018-11-28
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00073 | TPSK-LSPA1-T-PE-00160 | TPSK-LSPA1-T-PE-00384
[6 empty] | Return Date |  | 2018-10-12 | 2019-02-25 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A2 | TP
| PE | OL1-2G30-2331 | PROCESS EQUIPMENT DATA SHEET - 10-D-2330 - SPENT CAUSTIC STRIPPER OVERHEAD DRUM |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2019-01-11 | 2019-04-11 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00175 | TPSK-LSPA1-T-PE-00634 | TPSK-LSPA1-T-PE-01327 | TPSK-LSPA1-T-PE-01377
[6 empty] | Return Date | 2018-11-26 | 2019-02-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2350 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2350 - WET AIR OXIDATION PACKAGE |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2018-10-16 | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00180 | TPSK-LSPA1-T-PE-01328
[6 empty] | Return Date | 2019-02-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2389 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2390 - CAUSTIC DRAIN SUMP EDUCTOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date |  | 2019-01-28
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-2390 | PROCESS EQUIPMENT DATA SHEET - 10-D-2390 - CAUSTIC DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-27 | 2018-11-27 | 2019-04-16 | 2019-05-13
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00102 | TPSK-LSPA1-T-PE-00369 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01652
[6 empty] | Return Date |  | 2018-11-14 | 2019-01-14
[6 empty] | Owner Cmmt* |  | A3 | R1
| PE | OL1-2G30-2391 | PROCESS EQUIPMENT DATA SHEET - 10-P-2390 - CAUSTIC DRAIN DRUM PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-07 | 2019-01-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00444 | TPSK-LSPA1-T-PE-00695
[6 empty] | Return Date | 2019-01-16 | 2019-03-05
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2392 | PROCESS EQUIPMENT DATA SHEET - 10-D-2392 - SPENT CAUSTIC DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-27 | 2018-11-27 | 2019-04-16 | 2019-05-13
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00102 | TPSK-LSPA1-T-PE-00369 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01652
[6 empty] | Return Date |  | 2018-11-14 | 2019-01-14
[6 empty] | Owner Cmmt* |  | A3 | R1
| PE | OL1-2G30-2393 | PROCESS EQUIPMENT DATA SHEET - 10-P-2392 - SPENT CAUSTIC DRAIN DRUM PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00252 | TPSK-LSPA1-T-PE-00598
[6 empty] | Return Date | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2394 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2392 - SPENT CAUSTIC DRAIN SUMP EDUCTOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date |  | 2019-01-28
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-2405 | PROCESS EQUIPMENT DATA SHEET - 10-D-2405 - GAS DRYER FEED KO DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-14 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00315 | TPSK-LSPA1-T-PE-00480
[6 empty] | Return Date | 2018-12-10 | 2018-12-27
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2406 | PROCESS EQUIPMENT DATA SHEET - 10-E-2405 - GAS DRYER FEED CHILLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-30 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00239 | TPSK-LSPA1-T-PE-00523
[6 empty] | Return Date | 2018-11-14 | 2019-01-14
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2410 | PROCESS EQUIPMENT DATA SHEET - 10-D-2410 - CRACKED GAS DRYER |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-07 | 2019-01-18 | 2019-03-04 | 2019-04-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-00678 | TPSK-LSPA1-T-PE-00980 | TPSK-LSPA1-T-PE-01310
[6 empty] | Return Date | 2018-12-27 | 2019-01-29 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2411 | PROCESS EQUIPMENT DATA SHEET - 10-D-2411 - CRACKED GAS MERCURY ADSORBER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-20 | 2019-01-08 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00339 | TPSK-LSPA1-T-PE-00610 | TPSK-LSPA1-T-PE-01089
[6 empty] | Return Date | 2018-12-13 | 2019-01-22 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2412 | PROCESS EQUIPMENT DATA SHEET - 10-E-2412 - HP DEPROPANIZER FEED CHILLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-30 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00239 | TPSK-LSPA1-T-PE-00523
[6 empty] | Return Date | 2018-11-14 | 2019-01-14
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2413 | PROCESS EQUIPMENT DATA SHEET - 10-E-2413 - HP DEPROP FEED / OVERHEAD EXCHANGER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2415 | PROCESS EQUIPMENT DATA SHEET - 10-D-2415 - CG LIQUID DRYER FEED COALESCER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-20 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00339 | TPSK-LSPA1-T-PE-00596
[6 empty] | Return Date | 2018-12-13 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-2416 | PROCESS EQUIPMENT DATA SHEET - 10-P-2415 - CG LIQUID DRYER FEED PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00593
[6 empty] | Return Date | 2018-12-27 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2420 | PROCESS EQUIPMENT DATA SHEET - 10-D-2420 - CG LIQUID DRYER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-09 | 2019-01-08 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00301 | TPSK-LSPA1-T-PE-00610 | TPSK-LSPA1-T-PE-01089
[6 empty] | Return Date | 2018-11-30 | 2019-01-22 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G30-2430 | PROCESS EQUIPMENT DATA SHEET - 10-E-2430 - REGEN GAS FEED HEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00574 | TPSK-LSPA1-T-PE-00696
[6 empty] | Return Date | 2019-01-22 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2432 | PROCESS EQUIPMENT DATA SHEET - 10-E-2432 - REGEN GAS SHP HEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00574 | TPSK-LSPA1-T-PE-00696
[6 empty] | Return Date | 2019-01-22 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2434 | PROCESS EQUIPMENT DATA SHEET - 10-E-2435 - REGEN GAS EFFLUENT COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00574 | TPSK-LSPA1-T-PE-00696
[6 empty] | Return Date | 2019-01-22 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2435 | PROCESS EQUIPMENT DATA SHEET - 10-D-2435 - REGEN GAS SEPARATOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00559 | TPSK-LSPA1-T-PE-00725
[6 empty] | Return Date | 2019-01-22 | 2019-02-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2438 | PROCESS EQUIPMENT DATA SHEET - 10-D-2440 - HP DEPROPANIZER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00264 | TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-11-27 | 2018-12-18
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2439 | PROCESS EQUIPMENT DATA SHEET - 10-E-2440 - HP DEPROPANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2440 | PROCESS EQUIPMENT DATA SHEET - 10-T-2440 - HP DEPROPANIZER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-14 | 2018-10-12
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00167
[6 empty] | Return Date |  | 2018-10-03
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2441 | PROCESS EQUIPMENT DATA SHEET - 10-E-2441 - HP DEPROP REFLUX CHILLER NO. 2 |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2442 | PROCESS EQUIPMENT DATA SHEET - 10-E-2442 - HP DEPROP REFLUX CHILLER NO. 1 |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2443 | PROCESS EQUIPMENT DATA SHEET - 10-P-2445 - HP DEPROPANIZER COND PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-04 | 2018-12-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00408 | TPSK-LSPA1-T-PE-00568
[6 empty] | Return Date | 2018-12-17 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2444 | PROCESS EQUIPMENT DATA SHEET - 10-D-2445 - HP DEPROP REBOILER COND POT |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-11 | 2018-12-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00474 | TPSK-LSPA1-T-PE-00563
[6 empty] | Return Date | 2018-12-21 | 2019-01-14
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2445 | PROCESS EQUIPMENT DATA SHEET - 10-E-2445 - HP DEPROPANIZER REBOILER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00267 | TPSK-LSPA1-T-PE-00436
[6 empty] | Return Date | 2018-11-26 | 2018-12-18
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2446 | PROCESS EQUIPMENT DATA SHEET - 10-E-2446 - LP DEPROPANIZER FEED COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2450 | PROCESS EQUIPMENT DATA SHEET - 10-T-2450 - LP DEPROPANIZER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-14 | 2018-10-12
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00167
[6 empty] | Return Date |  | 2018-10-03
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2451 | PROCESS EQUIPMENT DATA SHEET - 10-E-2450 - LP DEPROPANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00259 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2452 | PROCESS EQUIPMENT DATA SHEET - 10-D-2450 - LP DEPROPANIZER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00264 | TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-11-27 | 2018-12-18
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2453 | PROCESS EQUIPMENT DATA SHEET - 10-P-2450 - LP DEPROPANIZER REFLUX / PRODUCT PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00593
[6 empty] | Return Date | 2018-12-27 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2455 | PROCESS EQUIPMENT DATA SHEET - 10-E-2455 - LP DEPROPANIZER REBOILER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-25 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00228 | TPSK-LSPA1-T-PE-00523
[6 empty] | Return Date | 2018-11-14 | 2019-01-14
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2456 | PROCESS EQUIPMENT DATA SHEET - 10-D-2455 - LP DEPROP REBOILER COND POT |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-11 | 2018-12-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00474 | TPSK-LSPA1-T-PE-00563
[6 empty] | Return Date | 2018-12-21 | 2019-01-14
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2457 | PROCESS EQUIPMENT DATA SHEET - 10-P-2455 - LP DEPROPANIZER COND PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-04 | 2018-12-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00408 | TPSK-LSPA1-T-PE-00568
[6 empty] | Return Date | 2018-12-17 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2460 | PROCESS EQUIPMENT DATA SHEET - 10-D-2460 - C2 HYDROG ARSINE GUARD BED |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-10 | 2019-01-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00453 | TPSK-LSPA1-T-PE-00660
[6 empty] | Return Date | 2019-01-16 | 2019-01-29
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2461 | PROCESS EQUIPMENT DATA SHEET - 10-E-2460 - C2 HYDROG FEED COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2465 | PROCESS EQUIPMENT DATA SHEET - 10-E-2465 - C2 HYDROG FEED HEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-29 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00391 | TPSK-LSPA1-T-PE-00602
[6 empty] | Return Date | 2018-12-13 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2470 | PROCESS EQUIPMENT DATA SHEET - 10-R-2470 - C2 HYDROG REACTOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-16 | 2019-02-06
Revised Plan
[6 empty] | Issue Actual | 2018-11-09 | 2019-01-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00299 | TPSK-LSPA1-T-PE-00609
[6 empty] | Return Date | 2018-11-29 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2471 | PROCESS EQUIPMENT DATA SHEET - 10-E-2470 - C2 HYDROG 1ST STAGE INTERCOOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-29 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00391 | TPSK-LSPA1-T-PE-00602
[6 empty] | Return Date | 2018-12-13 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2472 | PROCESS EQUIPMENT DATA SHEET - 10-E-2472 - C2 HYDROG 2ND STAGE INTERCOOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-29 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00391 | TPSK-LSPA1-T-PE-00602
[6 empty] | Return Date | 2018-12-13 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2474 | PROCESS EQUIPMENT DATA SHEET - 10-E-2474 - C2 HYDROG AFTERCOOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-29 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00391 | TPSK-LSPA1-T-PE-00602
[6 empty] | Return Date | 2018-12-13 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2480 | PROCESS EQUIPMENT DATA SHEET - 10-D-2480 - CG SECONDARY DRYER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-28 | 2019-01-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00386 | TPSK-LSPA1-T-PE-00637
[6 empty] | Return Date | 2018-12-13 | 2019-01-31
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2500 | PROCESS EQUIPMENT DATA SHEET - 10-E-2500 - PROPYLENE REFRIG SUBCOOLER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-10-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00039 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-09-28
[6 empty] | Owner Cmmt* |  | A2
| PE | OL1-2G30-2502 | PROCESS EQUIPMENT DATA SHEET - 10-E-2502 - DEMETH PREFRAC FEED COOLER NO. 1 |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-11-05 | 2018-12-11
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00475
[6 empty] | Return Date |  | 2018-10-02 | 2018-11-26 | 2019-01-10
[6 empty] | Owner Cmmt* |  | A1 | A2 | A1
| PE | OL1-2G30-2503 | PROCESS EQUIPMENT DATA SHEET - 10-E-2504 - DEMETH PREFRAC FEED COOLER NO. 2 |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-02 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A2
| PE | OL1-2G30-2504 | PROCESS EQUIPMENT DATA SHEET - 10-D-2504 - DEMETH PREFRAC FEED SEPARATOR NO. 1 |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00217 | TPSK-LSPA1-T-PE-00303
[6 empty] | Return Date | 2018-11-07 | 2018-11-26
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2505 | PROCESS EQUIPMENT DATA SHEET - 10-E-2506 - DEMETH PREFRAC FEED COOLER NO. 3 |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-10-04 | 2019-02-06
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-PE-00811
[6 empty] | Return Date |  | 2018-10-02 |  | 2019-02-25
[6 empty] | Owner Cmmt* |  | A3 |  | R1
| PE | OL1-2G30-2506 | PROCESS EQUIPMENT DATA SHEET - 10-D-2506 - DEMETH PREFRAC FEED SEPARATOR NO. 2 |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00217 | TPSK-LSPA1-T-PE-00303
[6 empty] | Return Date | 2018-11-07 | 2018-11-26
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2508 | PROCESS EQUIPMENT DATA SHEET - 10-D-2508 - DEMETH PREFRAC FEED SEPARATOR NO. 3 |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00217 | TPSK-LSPA1-T-PE-00303
[6 empty] | Return Date | 2018-11-07 | 2018-11-26
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2510 | PROCESS EQUIPMENT DATA SHEET - 10-T-2510 - DEMETHANIZER PREFRACTIONATOR |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-26 | 2018-11-09
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00092 | TPSK-LSPA1-T-PE-00306
[6 empty] | Return Date |  | 2018-10-24 | 2018-11-29
[6 empty] | Owner Cmmt* |  | A3 | A1
| PE | OL1-2G30-2511 | PROCESS EQUIPMENT DATA SHEET - 10-E-2510 - DEMETH PREFRAC CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A1
| PE | OL1-2G30-2515 | PROCESS EQUIPMENT DATA SHEET - 10-E-2515 - DEMETH PREFRACTIONATOR REBOILER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216 | TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-11-14 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2520 | PROCESS EQUIPMENT DATA SHEET - 10-T-2520 - RESIDUE GAS RECTIFIER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00172 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-11-05 | 2018-12-17
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2521 | PROCESS EQUIPMENT DATA SHEET - 10-E-2520 - RECTIFIER CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2525 | PROCESS EQUIPMENT DATA SHEET - 10-D-2525 - HYDROGEN DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-11-09 | 2018-12-18
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2526 | PROCESS EQUIPMENT DATA SHEET - 10-E-2525 - HYDROGEN CORE EXCHANGER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A1
| PE | OL1-2G30-2531 | PROCESS EQUIPMENT DATA SHEET - 10-E-2530 - DEMETH FEED COOLER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2540 | PROCESS EQUIPMENT DATA SHEET - 10-T-2540 - DEMETHANIZER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-11-09 | 2018-12-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00073 | TPSK-LSPA1-T-PE-00306 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date |  | 2018-10-24 | 2018-11-29 | 2018-12-17
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1
| PE | OL1-2G30-2541 | PROCESS EQUIPMENT DATA SHEET - 10-E-2540 - DEMETHANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A1
| PE | OL1-2G30-2545 | PROCESS EQUIPMENT DATA SHEET - 10-E-2545 - DEMETHANIZER REBOILER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216 | TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-11-14 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2546 | PROCESS EQUIPMENT DATA SHEET - 10-E-2546 - DEMETHANIZER BOTTOMS COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216 | TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-11-14 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2548 | PROCESS EQUIPMENT DATA SHEET - 10-E-2548 - DEMETHANIZER BOTTOMS VAPORIZER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216 | TPSK-LSPA1-T-PE-00464
[6 empty] | Return Date | 2018-11-14 | 2018-12-27
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2550 | PROCESS EQUIPMENT DATA SHEET - 10-C-2550 - RESIDUE GAS EXPANDER / RECOMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-29 | 2018-09-28
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00031 | TPSK-LSPA1-T-PE-00114
[6 empty] | Return Date |  | 2018-09-28 | 2018-10-24
[6 empty] | Owner Cmmt* |  | A3 | R1
| PE | OL1-2G30-2551 | PROCESS EQUIPMENT DATA SHEET - 10-D-2550 - EXPANDER SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00440
[6 empty] | Return Date | 2018-11-09 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2555 | PROCESS EQUIPMENT DATA SHEET - 10-D-2555 - EXPANDER DISCHARGE DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-11-09 | 2018-12-18
[6 empty] | Owner Cmmt* | R1 | em
| PE | OL1-2G30-2560 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2560 - PSA UNIT |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2018-10-17 | 2018-12-20 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00190 | TPSK-LSPA1-T-PE-00530 | TPSK-LSPA1-T-PE-01485
[6 empty] | Return Date | 2018-11-05 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2570 | PROCESS EQUIPMENT DATA SHEET - 10-T-2570 - DEETHANIZER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-17 | 2018-12-04 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00191 | TPSK-LSPA1-T-PE-00407 | TPSK-LSPA1-T-PE-00538
[6 empty] | Return Date | 2018-11-05 | 2018-12-17 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-2571 | PROCESS EQUIPMENT DATA SHEET - 10-E-2570 - DEETHANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-02 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A3 | A2
| PE | OL1-2G30-2572 | PROCESS EQUIPMENT DATA SHEET - 10-D-2570 - DEETHANIZER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-25 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00227 | TPSK-LSPA1-T-PE-00446
[6 empty] | Return Date | 2018-12-05 | 2018-12-27
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2573 | PROCESS EQUIPMENT DATA SHEET - 10-P-2570 - DEETHANIZER REFLUX PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-20 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00481
[6 empty] | Return Date | 2018-12-10 | 2018-12-27
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2574 | PROCESS EQUIPMENT DATA SHEET - 10-D-2575 - DEETHANIZER REBOILER COND POT |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-11 | 2018-12-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00474 | TPSK-LSPA1-T-PE-00563
[6 empty] | Return Date | 2018-12-21 | 2019-01-14
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2575 | PROCESS EQUIPMENT DATA SHEET - 10-E-2575 - DEETHANIZER REBOILER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-26 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00094 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A2 | A1
| PE | OL1-2G30-2576 | PROCESS EQUIPMENT DATA SHEET - 10-E-2576 - DEETHANIZER BOTTOMS COOLER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-26 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00094 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A2 | A1
| PE | OL1-2G30-2577 | PROCESS EQUIPMENT DATA SHEET - 10-P-2575 - DEETHANIZER REBOILER COND PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-04 | 2018-12-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00408 | TPSK-LSPA1-T-PE-00568
[6 empty] | Return Date | 2018-12-17 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2580 | PROCESS EQUIPMENT DATA SHEET - 10-T-2580 - C2 TOWER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-12 | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00162 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-10-31 | 2018-12-17
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2582 | PROCESS EQUIPMENT DATA SHEET - 10-E-2582 - C2 TOWER REFLUX COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00265 | TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-11-20 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2585 | PROCESS EQUIPMENT DATA SHEET - 10-E-2585 - C2 TOWER BOTTOMS REBOILER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-10-04 | 2019-04-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-PE-01261
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A1
| PE | OL1-2G30-2586 | PROCESS EQUIPMENT DATA SHEET - 10-P-2586 - ETHANE RECYCLE PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-20 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00481
[6 empty] | Return Date | 2018-12-10 | 2018-12-27
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2587 | PROCESS EQUIPMENT DATA SHEET - 10-E-2587 - C2 TOWER SIDE REBOILER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-10-04 | 2019-04-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-PE-01261
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A1
| PE | OL1-2G30-2591 | PROCESS EQUIPMENT DATA SHEET - 10-E-2856 - ETHYLENE PRODUCT SUBCOOLER |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2600 | PROCESS EQUIPMENT DATA SHEET - 10-D-2600 - C3 HYDROG GUARD ADSORBER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-07 | 2019-01-10 | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-00618 | TPSK-LSPA1-T-PE-01049
[6 empty] | Return Date | 2018-12-27 | 2019-01-24 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2610 | PROCESS EQUIPMENT DATA SHEET - 10-D-2610 - C3 HYDROG ARSINE GUARD BED |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00345 | TPSK-LSPA1-T-PE-00618
[6 empty] | Return Date | 2018-12-13 | 2019-01-24
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2620 | PROCESS EQUIPMENT DATA SHEET - 10-R-2620 - C3 HYDROG REACTOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-16 | 2019-02-06
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-02-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00583 | TPSK-LSPA1-T-PE-00910
[6 empty] | Return Date | 2019-01-16 | 2019-03-19
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-2621 | PROCESS EQUIPMENT DATA SHEET - 10-E-2620 - C3 HYDROG AFTERCOOLER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-10 | 2019-03-01 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00615 | TPSK-LSPA1-T-PE-00966 | TPSK-LSPA1-T-PE-01609
[6 empty] | Return Date | 2019-01-24 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2622 | PROCESS EQUIPMENT DATA SHEET - 10-D-2620 - C3 HYDROG RECYCLE DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-10 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00614 | TPSK-LSPA1-T-PE-01023
[6 empty] | Return Date | 2019-01-24 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2623 | PROCESS EQUIPMENT DATA SHEET - 10-P-2620 - C3 HYDROG RECYCLE PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00587 | TPSK-LSPA1-T-PE-00963
[6 empty] | Return Date | 2019-01-31 | 2019-03-21
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2624 | Process Equipment Datasheet - 10-X-2620 - C3 Hydrog Static Mixer |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2019-01-16 | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00664 | TPSK-LSPA1-T-PE-00968
[6 empty] | Return Date | 2019-01-31 | 2019-03-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2630 | PROCESS EQUIPMENT DATA SHEET - 10-T-2630 - SECONDARY DEETHANIZER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-14 | 2018-10-12 | 2018-12-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00169 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date |  | 2018-10-03 |  | 2018-12-17
[6 empty] | Owner Cmmt* |  | A3 |  | R1
| PE | OL1-2G30-2631 | PROCESS EQUIPMENT DATA SHEET - 10-E-2630 - SECONDARY DEETH CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00074 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A2 | A2
| PE | OL1-2G30-2632 | PROCESS EQUIPMENT DATA SHEET - 10-D-2630 - SECONDARY DEETH REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00287 | TPSK-LSPA1-T-PE-00633
[6 empty] | Return Date | 2019-01-11 | 2019-01-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2633 | PROCESS EQUIPMENT DATA SHEET - 10-P-2630 - SECONDARY DEETH REFLUX PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-06 | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00277 | TPSK-LSPA1-T-PE-00844
[6 empty] | Return Date | 2019-02-04 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2635 | PROCESS EQUIPMENT DATA SHEET - 10-E-2635 - SECONDARY DEETH REBOILER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-11-05 | 2018-12-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00074 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00438
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A2 | A2 | A1
| PE | OL1-2G30-2636 | PROCESS EQUIPMENT DATA SHEET - 10-E-2636 - SECONDARY DEETH BOTTOMS COOLER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00074 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A2 | A1
| PE | OL1-2G30-2640 | PROCESS EQUIPMENT DATA SHEET - 10-T-2640 - C3 TOWER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00201 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-11-05 | 2018-12-17
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2644 | PROCESS EQUIPMENT DATA SHEET - 10-D-2645 - C3 TOWER REBOILER COND POT |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-18 | 2019-02-01 | 2019-02-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00677 | TPSK-LSPA1-T-PE-00796 | TPSK-LSPA1-T-PE-00938
[6 empty] | Return Date | 2019-01-31 | 2019-02-21 | 2019-03-14
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-2645 | PROCESS EQUIPMENT DATA SHEET - 10-E-2645 - C3 TOWER REBOILER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-12 | 2018-11-05 | 2018-12-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00041 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00438
[6 empty] | Return Date |  | 2018-10-01 | 2018-11-26 | 2018-11-27
[6 empty] | Owner Cmmt* |  | A1 | A2 | A1
| PE | OL1-2G30-2646 | PROCESS EQUIPMENT DATA SHEET - 10-P-2646 - PROPANE RECYCLE PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-06 | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00277 | TPSK-LSPA1-T-PE-00844
[6 empty] | Return Date | 2019-02-04 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2647 | PROCESS EQUIPMENT DATA SHEET - 10-P-2647 - HP PROPYLENE / OFF SPEC PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-09 | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00302 | TPSK-LSPA1-T-PE-00649
[6 empty] | Return Date | 2019-02-04 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2660 | PROCESS EQUIPMENT DATA SHEET - 10-T-2660 - DEBUTANIZER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-14 | 2018-10-12
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00169
[6 empty] | Return Date |  | 2018-10-03
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2661 | PROCESS EQUIPMENT DATA SHEET - 10-E-2660 - DEBUTANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-26 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00094 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A2 | A1
| PE | OL1-2G30-2662 | PROCESS EQUIPMENT DATA SHEET - 10-D-2660 - DEBUTANIZER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00287 | TPSK-LSPA1-T-PE-00660
[6 empty] | Return Date | 2019-01-11 | 2019-01-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2663 | PROCESS EQUIPMENT DATA SHEET - 10-P-2660 - DEBUTANIZER REFLUX / PRODUCT PUMP |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-20 | 2018-12-13 | 2019-01-14 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00481 | TPSK-LSPA1-T-PE-00648 | TPSK-LSPA1-T-PE-01383
[6 empty] | Return Date | 2018-12-10 | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2664 | Process Equipment Datasheet - 10-F-2666 A-B - C5 - Pygas Feed Filters |  | Class Final | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2019-02-20 | 2019-03-11 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-0900 | TPSK-LSPA1-T-PE-01024 | TPSK-LSPA1-T-PE-01601
[6 empty] | Return Date | 2019-02-26 | 2019-03-29
[6 empty] | Owner Cmmt* | R1 | R2
| PE | OL1-2G30-2665 | PROCESS EQUIPMENT DATA SHEET - 10-E-2665 - DEBUTANIZER REBOILER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-27 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00101 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A1
| PE | OL1-2G30-2666 | PROCESS EQUIPMENT DATA SHEET - 10-E-2666 - DEBUTANIZER BOTTOMS COOLER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-11-27 | 2019-01-23 | 2019-04-17
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00112 | TPSK-LSPA1-T-PE-00370 | TPSK-LSPA1-T-PE-00711 | TPSK-LSPA1-T-PE-01387
[6 empty] | Return Date |  | 2018-10-12 | 2018-12-10 | 2019-02-11
[6 empty] | Owner Cmmt* |  | A3 | A1 | A2
| PE | OL1-2G30-2667 | PROCESS EQUIPMENT DATA SHEET - 10-D-2666 - C5 / PYGAS SURGE DRUM |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-03-20 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01106 | TPSK-LSPA1-T-PE-01600
[6 empty] | Return Date | 2019-02-21 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2668 | PROCESS EQUIPMENT DATA SHEET - 10-P-2666 - C5 / PYGAS PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-11 | 2019-03-11 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00834 | TPSK-LSPA1-T-PE-01025 | TPSK-LSPA1-T-PE-01339
[6 empty] | Return Date | 2019-02-25 | 2019-03-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2669 | Process Equipment Datasheet - 10-P-2665 A-B - Debutanizer Bottoms Pumps |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-27 | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00371 | TPSK-LSPA1-T-PE-00648
[6 empty] | Return Date | 2018-12-13 | 2019-01-28
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2700 | PROCESS EQUIPMENT DATA SHEET - 10-R-2700 - GHU-1 REACTOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-16 | 2019-02-06
Revised Plan
[6 empty] | Issue Actual | 2019-01-16 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00659 | TPSK-LSPA1-T-PE-01081
[6 empty] | Return Date | 2019-02-11 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2701 | PROCESS EQUIPMENT DATA SHEET - 10-E-2701 - GHU-1 FEED / EFFLUENT EXCHANGERS |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-23 | 2019-03-20 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00710 | TPSK-LSPA1-T-PE-01107 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2702 | PROCESS EQUIPMENT DATA SHEET - 10-E-2702 - GHU-1 S/U HEATER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-20 | 2019-04-04 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00899 | TPSK-LSPA1-T-PE-01250 | TPSK-LSPA1-T-PE-01371
[6 empty] | Return Date | 2019-03-19
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2703 | PROCESS EQUIPMENT DATA SHEET - 10-E-2705 - GHU-1 RECYCLE COOLER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-25 | 2019-03-28 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-01187 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2704 | PROCESS EQUIPMENT DATA SHEET - 10-P-2705 - GHU-1 RECYCLE PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-11 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00834 | TPSK-LSPA1-T-PE-01025
[6 empty] | Return Date | 2019-02-25 | 2019-03-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2705 | PROCESS EQUIPMENT DATA SHEET - 10-D-2705 - GHU-1 HOT SEPARATOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01188
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2706 | PROCESS EQUIPMENT DATA SHEET - 10-D-2706 - GHU-1 COLD SEPARATOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01188
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2707 | PROCESS EQUIPMENT DATA SHEET - 10-E-2706 - GHU-1 COOLER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-25 | 2019-03-28 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-01187 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2710 | PROCESS EQUIPMENT DATA SHEET - 10-T-2710 - DEPENTANIZER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00688 | TPSK-LSPA1-T-PE-01082
[6 empty] | Return Date | 2019-02-15 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2711 | PROCESS EQUIPMENT DATA SHEET - 10-E-2710 -DEPENTANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-25 | 2019-03-20 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-01107 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-15 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2712 | PROCESS EQUIPMENT DATA SHEET - 10-D-2710 - DEPENTANIZER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-03-20 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01106 | TPSK-LSPA1-T-PE-01600
[6 empty] | Return Date | 2019-02-21 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2713 | PROCESS EQUIPMENT DATA SHEET - 10-P-2710 - DEPENTANIZER REFLUX PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-11 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00834 | TPSK-LSPA1-T-PE-01025
[6 empty] | Return Date | 2019-02-25 | 2019-03-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2714 | PROCESS EQUIPMENT DATA SHEET - 10-P-2714 - C5 CUT PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-12 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00841 | TPSK-LSPA1-T-PE-01083
[6 empty] | Return Date | 2019-02-25 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2715 | PROCESS EQUIPMENT DATA SHEET - 10-E-2715 - DEPENTANIZER REBOILER |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-25 | 2019-03-20 | 2019-04-26 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00724 | TPSK-LSPA1-T-PE-01107 | TPSK-LSPA1-T-PE-01507 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2716 | PROCESS EQUIPMENT DATA SHEET - 10-E-2714 - C5 CUT COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-25 | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-01187
[6 empty] | Return Date | 2019-02-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2717 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2720 - RERUN TOWER EDUCTOR PKG |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2019-02-20 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00902 | TPSK-LSPA1-T-PE-01403
[6 empty] | Return Date | 2019-03-19
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2718 | PROCESS EQUIPMENT DATA SHEET - 10-D-2720 - RERUN TOWER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01342
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2719 | PROCESS EQUIPMENT DATA SHEET - 10-P-2720 - RERUN TOWER REFLUX / PRODUCT PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-12 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00841 | TPSK-LSPA1-T-PE-01404
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2720 | PROCESS EQUIPMENT DATA SHEET - 10-T-2720 - RERUN TOWER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00669 | TPSK-LSPA1-T-PE-01340
[6 empty] | Return Date | 2019-02-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2721 | PROCESS EQUIPMENT DATA SHEET - 10-E-2720 - RERUN TOWER CONDENSER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-11 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-01341
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2723 | PROCESS EQUIPMENT DATA SHEET - 10-E-2724 - WASH OIL CONDENSER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-11 | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-01353
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2724 | PROCESS EQUIPMENT DATA SHEET - 10-D-2724 - WASH OIL DEGASSING DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01354
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2725 | PROCESS EQUIPMENT DATA SHEET - 10-E-2725 - RERUN TOWER REBOILER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-11 | 2019-04-17 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-01405 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2726 | PROCESS EQUIPMENT DATA SHEET - 10-P-2726 - PYGAS FUEL OIL PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00873 | TPSK-LSPA1-T-PE-01432
[6 empty] | Return Date | 2019-02-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2727 | PROCESS EQUIPMENT DATA SHEET - 10-E-2726 - PYGAS FUEL OIL COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-11 | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-01431
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2728 | PROCESS EQUIPMENT DATA SHEET - 10-P-2724 - RECYCLE WASH OIL PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-12 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00841 | TPSK-LSPA1-T-PE-01458
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2729 | Process Equipment Datasheet - 10-P-2721 A-B - Wash Oil Pumps |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00873 | TPSK-LSPA1-T-PE-01458
[6 empty] | Return Date | 2019-02-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2730 | PROCESS EQUIPMENT DATA SHEET - 10-E-2730 - HYDROG REGEN HEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01070 | TPSK-LSPA1-T-PE-01586
[6 empty] | Return Date | 2019-04-02
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2735 | PROCESS EQUIPMENT DATA SHEET - 10-D-2735 - REGEN HYDROG DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-03-13 | 2019-04-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01049 | TPSK-LSPA1-T-PE-01277
[6 empty] | Return Date | 2019-04-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2750 | PROCESS EQUIPMENT DATA SHEET - 10-D-2750 - C4 / C5 HYDROG SURGE DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00794 | TPSK-LSPA1-T-PE-01023
[6 empty] | Return Date | 2019-02-21 | 2019-03-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2751 | PROCESS EQUIPMENT DATA SHEET - 10-P-2750 - C4 / C5 HYDROG FEED PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-03-01 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00788 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-01610
[6 empty] | Return Date | 2019-02-15 | 2019-03-21
[6 empty] | Owner Cmmt* | R1 | R2
| PE | OL1-2G30-2755 | PROCESS EQUIPMENT DATA SHEET - 10-E-2755 - C4 / C5 HYDROG S/U HEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-25 | 2019-03-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00924 | TPSK-LSPA1-T-PE-01148
[6 empty] | Return Date | 2019-03-19
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2760 | PROCESS EQUIPMENT DATA SHEET - 10-R-2760 - C4 / C5 HYDROG REACTOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-16 | 2019-02-06
Revised Plan
[6 empty] | Issue Actual | 2019-01-16 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00659 | TPSK-LSPA1-T-PE-01030
[6 empty] | Return Date | 2019-02-11 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2762 | PROCESS EQUIPMENT DATA SHEET - 10-D-2760 - C4 / C5 HYDROG RECYCLE DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00794 | TPSK-LSPA1-T-PE-01023
[6 empty] | Return Date | 2019-02-21 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2763 | PROCESS EQUIPMENT DATA SHEET - 10-E-2760 - C4 / C5 HYDROG VENT CONDENSER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-03-11 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00793 | TPSK-LSPA1-T-PE-01027 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-21 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2764 | PROCESS EQUIPMENT DATA SHEET - 10-P-2760 - C4 / C5 HYDROG RECYCLE PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00788 | TPSK-LSPA1-T-PE-00963
[6 empty] | Return Date | 2019-02-15 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2765 | PROCESS EQUIPMENT DATA SHEET - 10-E-2765 - C4 / C5 HYDROG RECYCLE COOLER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-03-11 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00793 | TPSK-LSPA1-T-PE-01027 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-21 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2767 | Process Equipment Datasheet - 10-D-2765 - C4 - C5 Hydrog Coalescer Drum |  | Class Final | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-20 | 2019-03-25 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE--00901 | TPSK-LSPA1-T-PE-01145 | TPSK-LSPA1-T-PE-01600
[6 empty] | Return Date | 2019-03-19
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2790 | PROCESS EQUIPMENT DATA SHEET - 10-D-2790 - LIGHT OIL DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-13 | 2019-01-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00482 | TPSK-LSPA1-T-PE-00721
[6 empty] | Return Date | 2019-01-22 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2791 | PROCESS EQUIPMENT DATA SHEET - 10-P-2790 - LIGHT OIL DRAIN DRUM PUMP |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-13 | 2019-01-25 | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00496 | TPSK-LSPA1-T-PE-00722 | TPSK-LSPA1-T-PE-01434
[6 empty] | Return Date | 2019-01-22 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2792 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2790 - LIGHT OIL DRAIN SUMP EDUCTOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date |  | 2019-01-22
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-2800 | PROCESS EQUIPMENT DATA SHEET - 10-C-2800 - PROPYLENE REFRIG COMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-22 | 2018-09-17
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00055
[6 empty] | Return Date |  | 2018-09-11
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2801 | PROCESS EQUIPMENT DATA SHEET - 10-P-2805 - PROPYLENE PRODUCT PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-06 | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00277 | TPSK-LSPA1-T-PE-00649
[6 empty] | Return Date | 2019-02-04 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2805 | PROCESS EQUIPMENT DATA SHEET - 10-D-2805 - C3R SURGE DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00348
[6 empty] | Return Date | 2018-11-09 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2806 | PROCESS EQUIPMENT DATA SHEET - 10-E-2805 - C3R CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A3 | A1
| PE | OL1-2G30-2807 | PROCESS EQUIPMENT DATA SHEET - 10-E-2807 - C3 CHILLER NO. 1 |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A2
| PE | OL1-2G30-2809 | PROCESS EQUIPMENT DATA SHEET - 10-E-2809 - C3 CHILLER NO. 2 |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00273
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A1
| PE | OL1-2G30-2810 | PROCESS EQUIPMENT DATA SHEET - 10-D-2810 - C3R 1ST STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2815 | PROCESS EQUIPMENT DATA SHEET - 10-D-2815 - C3R DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-07 | 2019-01-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-00633
[6 empty] | Return Date | 2018-12-27 | 2019-01-24
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2816 | PROCESS EQUIPMENT DATA SHEET - 10-P-2815 - PROPYLENE REFRIG RECOVERY PUMP |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-20 | 2018-12-13 | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00481 | TPSK-LSPA1-T-PE-00648
[6 empty] | Return Date | 2018-12-10 | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2820 | PROCESS EQUIPMENT DATA SHEET - 10-D-2820 - C3R 2ND STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2830 | PROCESS EQUIPMENT DATA SHEET - 10-D-2830 - C3R 3RD STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2840 | PROCESS EQUIPMENT DATA SHEET - 10-D-2840 - C3R 4TH STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2850 | PROCESS EQUIPMENT DATA SHEET - 10-C-2850 - ETHYLENE REFRIG COMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-22 | 2018-09-17
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00055
[6 empty] | Return Date |  | 2018-09-11
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2852 | PROCESS EQUIPMENT DATA SHEET - 10-E-2852 - C2R DESUPERHEATER NO. 1 |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A2
| PE | OL1-2G30-2853 | PROCESS EQUIPMENT DATA SHEET - 10-E-2852 - C2R DESUPERHEATER NO. 2 |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A2
| PE | OL1-2G30-2854 | PROCESS EQUIPMENT DATA SHEET - 10-D-2855 - C2R SURGE DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2019-01-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00621
[6 empty] | Return Date | 2018-11-09 | 2019-01-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2855 | PROCESS EQUIPMENT DATA SHEET - 10-P-2855 - ETHYLENE PRODUCT PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-28 | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00379 | TPSK-LSPA1-T-PE-00648
[6 empty] | Return Date | 2018-12-13 | 2019-01-28
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2856 | PROCESS EQUIPMENT DATA SHEET - 10-E-2855 - C2R CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00039 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-09-28 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A2 | A1
| PE | OL1-2G30-2857 | PROCESS EQUIPMENT DATA SHEET - 10-E-2857 - HP ETHYLENE PRODUCT VAPORIZER |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-12 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00041 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-01 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A1
| PE | OL1-2G30-2858 | PROCESS EQUIPMENT DATA SHEET - 10-E-2858 - HP ETHYLENE PRODUCT SUPERHEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00223 | TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-11-14 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2859 | Process Equipment Datasheet - 10-E-2856 - Ethylene Product Subcooler |  | Class Final | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. |  | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-01-23
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00492 | TPSK-LSPA1-T-PE-00711
[6 empty] | Return Date |  | 2019-01-22 | 2019-02-11
[6 empty] | Owner Cmmt* |  | R1 | R1
| PE | OL1-2G30-2860 | PROCESS EQUIPMENT DATA SHEET - 10-D-2860 - C2R 1ST STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-23 | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00208 | TPSK-LSPA1-T-PE-00845
[6 empty] | Return Date | 2019-02-04 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2865 | PROCESS EQUIPMENT DATA SHEET - 10-D-2865 - C2R DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-07 | 2019-01-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00445 | TPSK-LSPA1-T-PE-00633
[6 empty] | Return Date | 2019-01-10 | 2019-01-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2870 | PROCESS EQUIPMENT DATA SHEET - 10-D-2870 - C2R 2ND STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-09 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2880 | PROCESS EQUIPMENT DATA SHEET - 10-D-2880 - C2R 3RD STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-23 | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00208 | TPSK-LSPA1-T-PE-00845
[6 empty] | Return Date | 2019-02-04 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | TP
| PE | OL1-2G30-2882 | PROCESS EQUIPMENT DATA SHEET - 10-E-2882 - LP ETHYLENE PRODUCT COOLER NO. 1 |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2884 | PROCESS EQUIPMENT DATA SHEET - 10-E-2884 - LP ETHYLENE PRODUCT COOLER NO. 2 |  | Class 1 | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2900 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2900 - PH CTRL / CORROSION INHIBITOR INJ PKG |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-31 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00532 | TPSK-LSPA1-T-PE-00780 | TPSK-LSPA1-T-PE-01103
[6 empty] | Return Date | 2019-01-28 | 2019-02-28 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R2 | R1
| PE | OL1-2G30-2902 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2902 - EMULSION BREAKER INJ PKG |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-25 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-01103
[6 empty] | Return Date | 2019-01-22 | 2019-03-05 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2904 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2904 - WATER STRIPPER CHEMICAL INJ PKG |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-25 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-01103
[6 empty] | Return Date | 2019-01-22 | 2019-03-05 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2906 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2906 - DSG ANTI-FOULANT INJ PKG |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-25 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-01103
[6 empty] | Return Date | 2019-01-22 | 2019-03-05 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2910 | PROCESS EQUIPMENT DATA SHEET - 10-TK-2910 - WASH OIL DAY TANK |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00561 | TPSK-LSPA1-T-PE-00760
[6 empty] | Return Date | 2019-01-28 | 2019-02-25
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2911 | PROCESS EQUIPMENT DATA SHEET - 10-P-2910 - WASH OIL INJECTION PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-10 | 2019-02-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00613 | TPSK-LSPA1-T-PE-00939
[6 empty] | Return Date | 2019-02-04 | 2019-03-21
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2912 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2912 - CAUSTIC TOWER ANTI-FOULANT INJ PKG |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-31 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00780 | TPSK-LSPA1-T-PE-01103
[6 empty] | Return Date | 2019-01-22 | 2019-02-28 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2914 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2914 - NEUTRALIZATION INJECTION PKG |  | Class 1 | Purpose** | IFR | CAN
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-16 | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00181 | TPSK-LSPA1-T-PE-01329
[6 empty] | Return Date | 2019-02-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2920 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2920 - POLYMERIZATION INHIBITOR INJ PKG |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-25 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-01103
[6 empty] | Return Date | 2019-01-22 | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2922 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2922 - CO INJECTION PACKAGE |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00560 | TPSK-LSPA1-T-PE-00656
[6 empty] | Return Date | 2019-01-14 | 2019-01-31
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2931 | Process Equipment Datasheet - 10-PK-2931 - Propanol Injection Pkg |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2019-01-22 | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00689 | TPSK-LSPA1-T-PE-00846
[6 empty] | Return Date | 2019-02-11 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2932 | Process Equipment Datasheet - 10-D-2930 - Methanol Drum |  | Class Final | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-14 | 2019-02-01 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA-1-T-PE-00644 | TPSK-LSPA1-T-PE-00796 | TPSK-LSPA1-T-PE-01162
[6 empty] | Return Date | 2019-01-31 | 2019-02-21
[6 empty] | Owner Cmmt* | R1 | R2
| PE | OL1-2G30-2934 | Process Equipment Datasheet - 10-P-2930 - Methanol Injection Pump |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-14 | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00645 | TPSK-LSPA1-T-PE-00844
[6 empty] | Return Date | 2019-02-04 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2940 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2940 - C4 POLYMER INHIBITOR INJECTION PKG |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-25 | 2019-03-20 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-01384
[6 empty] | Return Date | 2019-01-22 | 2019-03-14 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2945 | Process Equipment Datasheet - 10-PK-2945 - Anti-Oxidant Injection Package |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01617
Return Date
Owner Cmmt*
| PE | OL1-2G30-3000 | PROCESS EQUIPMENT DATA SHEET - 10-T-3000 - PREDISTILLATION TOWER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00923
[6 empty] | Return Date | 2019-03-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3001 | PROCESS EQUIPMENT DATA SHEET - 10-E-3000 - PREDISTILLATION CONDENSER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-03-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01148
[6 empty] | Return Date | 2019-04-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3002 | PROCESS EQUIPMENT DATA SHEET - 10-P-3002 - PREDISTILLATION FEED PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3003 | PROCESS EQUIPMENT DATA SHEET - 10-P-3000 - PREDISTILLATION REFLUX PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3004 | PROCESS EQUIPMENT DATA SHEET - 10-E-3004 - PREDISTILLATION TRIM REBOILER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-03-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01148
[6 empty] | Return Date | 2019-04-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3005 | PROCESS EQUIPMENT DATA SHEET - 10-E-3005 - PREDISTILLATION REBOILER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-03-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01148
[6 empty] | Return Date | 2019-04-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3006 | PROCESS EQUIPMENT DATA SHEET - 10-D-3000 - PREDISTILLATION REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3007 | PROCESS EQUIPMENT DATA SHEET - 10-D-3002 - PREDISTILLATION FEED DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3010 | PROCESS EQUIPMENT DATA SHEET - 10-D-3010 - C4 FEED DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00923
[6 empty] | Return Date | 2019-03-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3014 | PROCESS EQUIPMENT DATA SHEET - 10-E-3014 - C4 SOLVENT VAPORIZER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01148
[6 empty] | Return Date | 2019-04-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3015 | PROCESS EQUIPMENT DATA SHEET - 10-E-3015 - C4 VAPORIZER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3016 | PROCESS EQUIPMENT DATA SHEET - 10-P-3016 - HEAVY END DISCHARGE PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3018 | PROCESS EQUIPMENT DATA SHEET - 10-E-3018 - SOLVENT COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01214
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3020 | PROCESS EQUIPMENT DATA SHEET - 10-T-3020 - MAIN WASHER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00932
[6 empty] | Return Date | 2019-03-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3021 | PROCESS EQUIPMENT DATA SHEET - 10-D-3020 - MAIN WASHER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01214
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3022 | PROCESS EQUIPMENT DATA SHEET - 10-P-3020 - MAIN WASHER REFLUX PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3023 | PROCESS EQUIPMENT DATA SHEET - 10-E-3020 - MAIN WASHER CONDENSER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3026 | PROCESS EQUIPMENT DATA SHEET - 10-P-3026 - MAIN WASHER BOTTOM PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3030 | PROCESS EQUIPMENT DATA SHEET - 10-T-3030 - AFTER WASHER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00955
[6 empty] | Return Date | 2019-03-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3031 | PROCESS EQUIPMENT DATA SHEET - 10-E-3030 - AFTER WASHER CONDENSER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01214
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3032 | PROCESS EQUIPMENT DATA SHEET - 10-P-3030 - AFTER WASHER REFLUX PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3033 | PROCESS EQUIPMENT DATA SHEET - 10-D-3030 - AFTER WASHER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3036 | PROCESS EQUIPMENT DATA SHEET - 10-P-3036 - AFTER WASHER BOTTOM PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3040 | PROCESS EQUIPMENT DATA SHEET - 10-T-3040 - RECTIFIER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00958
[6 empty] | Return Date | 2019-04-02
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3044 | PROCESS EQUIPMENT DATA SHEET - 10-E-3044 - SOLVENT HEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01214
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3045 | PROCESS EQUIPMENT DATA SHEET - 10-E-3045 - SOLVENT HEAT EXCHANGER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01214
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3046 | PROCESS EQUIPMENT DATA SHEET - 10-P-3046 - DEGASSER FEED PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3047 | PROCESS EQUIPMENT DATA SHEET - 10-P-3045 - RECTIFIER PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3050 | PROCESS EQUIPMENT DATA SHEET - 10-T-3050 - DEGASSER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00955
[6 empty] | Return Date | 2019-03-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3055 | PROCESS EQUIPMENT DATA SHEET - 10-E-3055 - DEGASSER REBOILER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3056 | PROCESS EQUIPMENT DATA SHEET - 10-P-3056 - DEGASSER BOTTOM PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3060 | PROCESS EQUIPMENT DATA SHEET - 10-T-3060 - ACETYLENE WASHER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00923
[6 empty] | Return Date | 2019-03-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3061 | PROCESS EQUIPMENT DATA SHEET - 10-E-3060 - ACETYLENE WASHER CONDENSER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3062 | PROCESS EQUIPMENT DATA SHEET - 10-E-3062 - ACETYLENE CONDENSER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3063 | PROCESS EQUIPMENT DATA SHEET - 10-P-3060 - WWASTE WATER PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3064 | PROCESS EQUIPMENT DATA SHEET - 10-P-3062 - C4 ACETYLENE PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3065 | PROCESS EQUIPMENT DATA SHEET - 10-P-3061 - WASTE HC PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3066 | PROCESS EQUIPMENT DATA SHEET - 10-D-3062 - ACETYLENE ACCUMULATOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3067 | PROCESS EQUIPMENT DATA SHEET - 10-D-3060 - C4 FEED DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3070 | PROCESS EQUIPMENT DATA SHEET - 10-T-3070 - DIRECT COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00955
[6 empty] | Return Date | 2019-03-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3071 | PROCESS EQUIPMENT DATA SHEET - 10-E-3070 - WATER / NMP COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3072 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-3070 - RECYCLE GAS STEAM EJECTOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan |  | 2019-05-16
[6 empty] | Issue Actual | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01283
Return Date
Owner Cmmt*
| PE | OL1-2G30-3073 | PROCESS EQUIPMENT DATA SHEET - 10-C-3070 - RECYCLE GAS COMPRESSOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-11-20 | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00344 | TPSK-LSPA1-T-PE-00675
[6 empty] | Return Date | 2018-12-13 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3076 | PROCESS EQUIPMENT DATA SHEET - 10-P-3076 - DIRECT COOLER PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3080 | PROCESS EQUIPMENT DATA SHEET - 10-T-3080 - BUTADIENE TOWER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00923
[6 empty] | Return Date | 2019-03-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3081 | PROCESS EQUIPMENT DATA SHEET - 10-D-3080 - BUTADIENE TOWER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3082 | PROCESS EQUIPMENT DATA SHEET - 10-E-3080 - BUTADIENE TOWER CONDENSER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3083 | Process Equipment Data Sheet - 10-P-3080 A-B Butadiene Tower Reflux Pumps |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3084 | PROCESS EQUIPMENT DATA SHEET - 10-E-3084 - BUTADIENE TOWER TRIM REBOILER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3085 | PROCESS EQUIPMENT DATA SHEET - 10-E-3085 - BUTADIENE TOWER REBOILER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3086 | PROCESS EQUIPMENT DATA SHEET - 10-P-3086 - C4 / C5 HC PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3087 | PROCESS EQUIPMENT DATA SHEET - 10-P-3080 - BUTADIENE TOWER REFLUX PUMPS |  | Class 1 | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3090 | PROCESS EQUIPMENT DATA SHEET - 10-T-3090 - BUTADIENE DRYING TOWER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00932
[6 empty] | Return Date | 2019-03-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3095 | PROCESS EQUIPMENT DATA SHEET - 10-E-3095 - BUTADIENE DRYING TOWER REBOILER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3097 | PROCESS EQUIPMENT DATA SHEET - 10-P-3096 - BUTADIENE PRODUCT PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3098 | PROCESS EQUIPMENT DATA SHEET - 10-E-3098 - BUTADIENE PRODUCT SUBCOOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3100 | PROCESS EQUIPMENT DATA SHEET - 10-D-3100 - SOLVENT REGEN DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3101 | PROCESS EQUIPMENT DATA SHEET - 10-A-3100 - SOLVENT REGEN AGITATOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan |  | 2019-05-16
[6 empty] | Issue Actual | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01319
Return Date
Owner Cmmt*
| PE | OL1-2G30-3110 | PROCESS EQUIPMENT DATA SHEET - 10-T-3110 - WATER WASHER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00973
[6 empty] | Return Date | 2019-04-02
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3111 | PROCESS EQUIPMENT DATA SHEET - 10-D-3110 - WATER WASHER ACCUMULATOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3112 | PROCESS EQUIPMENT DATA SHEET - 10-E-3110 - WATER WASHER CONDENSER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3113 | PROCESS EQUIPMENT DATA SHEET - 10-P-3110 - SOLVENT RETURN PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3123 | PROCESS EQUIPMENT DATA SHEET - 10-PK-3120 - REGEN STEAM EJECTOR PKG |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan |  | 2019-05-16
[6 empty] | Issue Actual | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01284
Return Date
Owner Cmmt*
| PE | OL1-2G30-3126 | PROCESS EQUIPMENT DATA SHEET - 10-D-3126 - EJECTOR SEAL DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3127 | PROCESS EQUIPMENT DATA SHEET - 10-P-3126 - WASTE WATER RETURN PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3150 | PROCESS EQUIPMENT DATA SHEET - 10-E-3150 - CONDENSATE HEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01214
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3151 | PROCESS EQUIPMENT DATA SHEET - 10-D-3150 - CONDENSATE FLASH DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3160 | PROCESS EQUIPMENT DATA SHEET - 10-E-3160 - CONDENSATE COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-29
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01214
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3161 | PROCESS EQUIPMENT DATA SHEET - 10-D-3160 - CONDENSATE DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3162 | PROCESS EQUIPMENT DATA SHEET - 10-P-3160 - CONDENSATE RECYCLE PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3180 | PROCESS EQUIPMENT DATA SHEET - 10-D-3180 - BLOWDOWN DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3190 | PROCESS EQUIPMENT DATA SHEET - 10-D-3190 - NMP SLOP DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3191 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-3190 - NMP SLOP SUMP EDUCTOR |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265
Return Date
Owner Cmmt*
| PE | OL1-2G30-3192 | PROCESS EQUIPMENT DATA SHEET - 10-P-3190 - SOLVENT SLOP PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual |  | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01160
[6 empty] | Return Date |  | 2019-04-11
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G30-3900 | PROCESS EQUIPMENT DATA SHEET - 10-TK-3900 - NMP STORAGE TANK |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01318
Return Date
Owner Cmmt*
| PE | OL1-2G30-3901 | PROCESS EQUIPMENT DATA SHEET - 10-P-3900 - NMP STORAGE PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA-1-PE-01285
Return Date
Owner Cmmt*
| PE | OL1-2G30-3902 | PROCESS EQUIPMENT DATA SHEET - 10-P-3902 - SOLVENT INHIBITOR DOSING PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3903 | PROCESS EQUIPMENT DATA SHEET - 10-D-3902 - SOLVENT INHIBITOR DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA-1-PE-01285
Return Date
Owner Cmmt*
| PE | OL1-2G30-3904 | PROCESS EQUIPMENT DATA SHEET - 10-D-3904 - PRODUCT INHIBITOR DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3905 | PROCESS EQUIPMENT DATA SHEET - 10-P-3904 - PRODUCT INHIBITOR DOSING PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA-1-PE-01285
Return Date
Owner Cmmt*
| PE | OL1-2G30-3906 | PROCESS EQUIPMENT DATA SHEET - 10-D-3906 - ANTI FOAM AGENT DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3907 | PROCESS EQUIPMENT DATA SHEET - 10-P-3906 - ANTIFOAM DOSING PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA-1-PE-01285
Return Date
Owner Cmmt*
| PE | OL1-2G30-3908 | PROCESS EQUIPMENT DATA SHEET - 10-D-3908 - PREDISTILLATION INHIBITOR DRUM |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA-1-PE-01285
Return Date
Owner Cmmt*
| PE | OL1-2G30-3909 | PROCESS EQUIPMENT DATA SHEET - 10-P-3908 - PREDISTILLATION INHIBITOR DOSING PUMP |  | Class 1 | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2019-05-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3910 | Process Equipment Data Sheet - 10-D-3908 - Predistillation Inhibitor Drum |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan |  | 2019-05-20
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5100 | PROCESS EQUIPMENT DATA SHEET - 10-D-5100 - DEAERATOR |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-11-14 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00151 | TPSK-LSPA1-T-PE-00318 | TPSK-LSPA1-T-PE-01174
[6 empty] | Return Date | 2018-11-05 | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5101 | PROCESS EQUIPMENT DATA SHEET - 10-P-5100 - SHP BFW PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-31 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00251 | TPSK-LSPA1-T-PE-01483
[6 empty] | Return Date | 2018-10-26 | 2018-12-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5102 | PROCESS EQUIPMENT DATA SHEET - 10-P-5102 - BFW PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-31 | 2019-03-29 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00251 | TPSK-LSPA1-T-PE-01196 | TPSK-LSPA1-T-PE-01484
[6 empty] | Return Date | 2018-10-26 | 2018-12-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5103 | PROCESS EQUIPMENT DATA SHEET - 10-E-5100 - DEARATOR VENT CONDENSER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-25 | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00230 | TPSK-LSPA1-T-PE-00366
[6 empty] | Return Date | 2018-11-14 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5107 | PROCESS EQUIPMENT DATA SHEET - 10-E-5112 - SUSPECT CONDENSATE FLASH DRUM VENT CONDENSER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-30 | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00243 | TPSK-LSPA1-T-PE-00646
[6 empty] | Return Date | 2018-11-14 | 2019-02-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5108 | PROCESS EQUIPMENT DATA SHEET - 10-E-5110 - SUSPECT CONDENSATE COOLER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-30 | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00243 | TPSK-LSPA1-T-PE-00652
[6 empty] | Return Date | 2018-11-14 | 2019-02-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5109 | PROCESS EQUIPMENT DATA SHEET - 10-P-5110 - CONDENSATE PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-31 | 2019-03-14 | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00251 | TPSK-LSPA1-T-PE-01051 | TPSK-LSAP1-T-PE-01189
[6 empty] | Return Date | 2018-10-26 | 2018-12-13 | 2019-04-02 | 2019-05-09
[6 empty] | Owner Cmmt* | R1 | R2 | R2 | R2
| PE | OL1-2G30-5110 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5110 - CONDENSATE TANK |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-27 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00374 | TPSK-LSPA1-T-PE-01017
[6 empty] | Return Date | 2018-12-18 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5111 | PROCESS EQUIPMENT DATA SHEET - 10-P-5112 - SUSPECT CONDENSATE PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00219 | TPSK-LSPA1-T-PE-00363
[6 empty] | Return Date | 2018-11-14 | 2018-12-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5112 | PROCESS EQUIPMENT DATA SHEET - 10-D-5112 - SUSPECT CONDENSATE FLASH DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-05 | 2018-12-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00274 | TPSK-LSPA1-T-PE-00498
[6 empty] | Return Date | 2018-12-10 | 2019-01-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5113 | PROCESS EQUIPMENT DATA SHEET - 10-E-5113 - FOUL CONDENSATE COOLER |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-25 | 2018-11-26 | 2019-04-08 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00230 | TPSK-LSPA1-T-PE-00366 | TPSK-LSPA1-T-PE-01278 | TPSK-LSPA1-T-PE-01406
[6 empty] | Return Date | 2018-11-14 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5114 | PROCESS EQUIPMENT DATA SHEET - 10-D-5114 - LP CONDENSATE FLASH DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-05 | 2018-12-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00274 | TPSK-LSPA1-T-PE-00498
[6 empty] | Return Date | 2018-12-10 | 2019-01-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5115 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5115 - CONDENSATE CARBON FILTERS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2018-11-26 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00362 | TPSK-LSPA1-T-PE-00778
[6 empty] | Return Date | 2018-12-18 | 2019-02-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5120 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5120 - RAW CONDENSATE TANK |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-26 | 2019-03-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00364 | TPSK-LSPA1-T-PE-01055
[6 empty] | Return Date | 2018-12-17 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5121 | PROCESS EQUIPMENT DATA SHEET - 10-P-5120 - RAW CONDENSATE PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00219 | TPSK-LSPA1-T-PE-00363
[6 empty] | Return Date | 2018-11-14 | 2018-12-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5125 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5125 - CONDENSATE POLISHER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2018-11-27 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00373 | TPSK-LSPA1-T-PE-00778
[6 empty] | Return Date | 2018-12-13 | 2019-02-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5140 | PROCESS EQUIPMENT DATA SHEET - 10-D-5140 - INTERMITTENT BLOWDOWN DRUM |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-19 | 2018-12-14 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00331 | TPSK-LSPA1-T-PE-00504 | TPSK-LSPA1-T-PE-00988
[6 empty] | Return Date | 2018-12-04 | 2019-01-10 | 2019-03-15
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5141 | PROCESS EQUIPMENT DATA SHEET - 10-P-5140 - INTERMITTENT BLOWDOWN PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2019-03-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00219 | TPSK-LSPA1-T-PE-01051
[6 empty] | Return Date | 2018-11-14 | 2019-04-02
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5150 | PROCESS EQUIPMENT DATA SHEET - 10-D-5150 - CONTINUOUS BLOWDOWN FLASH DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-19 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00331 | TPSK-LSPA1-T-PE-00440
[6 empty] | Return Date | 2018-12-04 | 2019-03-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5200 | PROCESS EQUIPMENT DATA SHEET - 10-D-5200 - FUEL GAS DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-19 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00331 | TPSK-LSPA1-T-PE-00440
[6 empty] | Return Date | 2018-12-04 | 2019-01-04
[6 empty] | Owner Cmmt* | R2 | TP
| PE | OL1-2G30-5201 | PROCESS EQUIPMENT DATA SHEET - 10-E-5200 - MP ETHYLENE SUPERHEATER |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-05 | 2019-02-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00275 | TPSK-LSPA1-T-PE-00853
[6 empty] | Return Date | 2018-11-29 | 2019-03-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5202 | Process Equipment Datasheet - 10-D-5220 - MP Ethylene Superhtr Cond Pot |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-10 | 2019-02-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00614 | TPSK-LSPA1-T-PE--00836
[6 empty] | Return Date | 2019-01-24 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5210 | PROCESS EQUIPMENT DATA SHEET - 10-E-5210 - PILOT GAS VAPORIZER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-14 | 2019-04-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00321 | TPSK-LSPA1-T-PE-01054 | TPSK-LSPA1-T-PE-01278
[6 empty] | Return Date | 2018-12-13 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5211 | PROCESS EQUIPMENT DATA SHEET - 10-D-5210 - PILOT GAS VAPORIZER COND POT |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-10 | 2019-02-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00614 | TPSK-LSPA1-T-PE--00836
[6 empty] | Return Date | 2019-01-24 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5350 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5350 - COOLING TOWER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-12-03 |  | 2018-12-26 | 2018-12-26
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-25 | 2018-10-24 | 2019-03-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00082 | TPSK-LSPA1-T-PE-00226 | TPSK-LSPA1-T-PE-01150
[6 empty] | Return Date |  | 2018-10-13 | 2018-11-14 | 2019-04-12
[6 empty] | Owner Cmmt* |  | A3 | A1 | R2
| PE | OL1-2G30-5351 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5351 - OLEFINS CW PUMPS SUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-03 | 2018-12-26
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-02-01
[6 empty] | Transmittal no. | TPSK-LSPA-1-T-PE-00539 | TPSK-LSPA1-T-PE-00791
[6 empty] | Return Date | 2019-01-16 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5352 | PROCESS EQUIPMENT DATA SHEET - 10-P-5350 - OLEFINS COOLING WATER PUMPS |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-10-24 | 2018-10-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00225 | TPSK-LSPA1-T-PE-00075
[6 empty] | Return Date |  | 2019-04-22 | 2018-11-14 | 2018-11-14
[6 empty] | Owner Cmmt* |  | A1 | A1 | A1
| PE | OL1-2G30-5355 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5355 - SIDE STREAM FILTER PKG |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-12-03 |  | 2018-12-26 | 2018-12-26
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-25 | 2018-10-24 | 2019-01-08
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00082 | TPSK-LSPA1-T-PE-00226 | TPSK-LSPA1-T-PE-00611
[6 empty] | Return Date |  | 2018-10-13 | 2018-11-14 | 2019-01-24
[6 empty] | Owner Cmmt* |  | A3 | A1 | A1
| PE | OL1-2G30-5360 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5360 - CTU CW PUMPS SUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-03 | 2018-12-26
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-02-01
[6 empty] | Transmittal no. | TPSK-LSPA-1-T-PE-00539 | TPSK-LSPA1-T-PE-00791
[6 empty] | Return Date | 2019-01-16 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5361 | PROCESS EQUIPMENT DATA SHEET - 10-P-5360 - CTU COOLING WATER PUMPS |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-10-24 | 2018-10-26 | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00225 | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00593
[6 empty] | Return Date |  | 2018-10-24 | 2018-11-14 | 2018-11-14 | 2019-02-04
[6 empty] | Owner Cmmt* |  | A3 | A1 | A1 | R1
| PE | OL1-2G30-5370 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5370 - CW FILTER BACKWASH SUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-03 | 2018-12-26
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-02-01
[6 empty] | Transmittal no. | TPSK-LSPA-1-T-PE-00539 | TPSK-LSPA1-T-PE-00791
[6 empty] | Return Date | 2019-01-16 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5371 | PROCESS EQUIPMENT DATA SHEET - 10-P-5370 - CW FILTER BACKWASH PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-10 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00623 | TPSK-LSPA1-T-PE-01366
[6 empty] | Return Date | 2019-02-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5390 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5390 - COPPER CORROSION INHIBITOR INJ PKG |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-11-27 | 2019-02-19 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00877 | TPSK-LSPA1-T-PE-01111
[6 empty] | Return Date | 2018-12-13 | 2019-03-13 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5392 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5392 - MILD STEEL CORROSION INHIBITOR INJ PKG |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-11-27 | 2019-02-19 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00890 | TPSK-LSPA1-T-PE-01111
[6 empty] | Return Date | 2018-12-13 | 2019-03-13 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5394 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5394 - DISPERSANT INJ PKG |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-11-27 | 2019-02-19 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00877 | TPSK-LSPA1-T-PE-01111
[6 empty] | Return Date | 2018-12-13 | 2019-03-13 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5397 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5397 - NON-OXIDIZING BIOCIDE INJ PKG |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-11-27 | 2019-02-19 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00877 | TPSK-LSPA1-T-PE-01111
[6 empty] | Return Date | 2018-12-13 | 2019-03-13 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5400 | PROCESS EQUIPMENT DATA SHEET - 10-D-5400 - INSTRUMENT AIR RECEIVER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-13 | 2019-02-06 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00485 | TPSK-LSPA1-T-PE-00800 | TPSK-LSPA1-T-PE-00983
[6 empty] | Return Date | 2019-01-07 | 2019-03-13 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5500 | PROCESS EQUIPMENT DATA SHEET - 10-D-5500 - WARM FLARE DRUM |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-12 | 2018-12-05 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00168 | TPSK-LSPA1-T-PE-00417 | TPSK-LSPA1-T-PE-01020
[6 empty] | Return Date | 2018-11-14 | 2019-01-04 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5501 | PROCESS EQUIPMENT DATA SHEET - 10-P-5500 - HOT BLOWDOWN PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-01-30 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01022
[6 empty] | Return Date | 2019-01-24 | 2019-03-05 | 2019-03-27
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-5510 | PROCESS EQUIPMENT DATA SHEET - 10-D-5510 - COLD FLARE DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-29 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00397 | TPSK-LSPA1-T-PE-01018
[6 empty] | Return Date | 2019-01-04 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5511 | PROCESS EQUIPMENT DATA SHEET - 10-E-5510 - COLD FLARE BLOWDOWN VAPORIZER |  | Class 1 | Purpose** | IFR | IFR | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-11 | 2019-04-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00575 | TPSK-LSPA1-T-PE-00626 | TPSK-LSPA1-T-PE-01261
[6 empty] | Return Date | 2019-03-13 | 2019-02-04 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G30-5512 | PROCESS EQUIPMENT DATA SHEET - 10-E-5512 - COLD FLARE SUPERHEATER |  | Class 1 | Purpose** | IFR | IFR | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-11 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00575 | TPSK-LSPA1-T-PE-00626 | TPSK-LSPA1-T-PE-01161
[6 empty] | Return Date | 2019-03-13 | 2019-02-04 | 2019-04-11
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-5513 | PROCESS EQUIPMENT DATA SHEET - 10-E-5513 - METHANOL VAPORIZER |  | Class 1 | Purpose** | IFR | IFR | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-11 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00575 | TPSK-LSPA1-T-PE-00626 | TPSK-LSPA1-T-PE-01161
[6 empty] | Return Date | 2019-03-13 | 2019-02-04 | 2019-04-11
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5514 | PROCESS EQUIPMENT DATA SHEET - 10-D-5513 - METHANOL VAPROIZER COND POT |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-10 | 2019-02-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00614 | TPSK-LSPA1-T-PE-00785
[6 empty] | Return Date | 2019-01-24 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5515 | PROCESS EQUIPMENT DATA SHEET - 10-D-5515 - METHANOL MAKE-UP DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-03-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00527 | TPSK-LSPA1-T-PE-01052
[6 empty] | Return Date | 2019-01-24 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5520 | PROCESS EQUIPMENT DATA SHEET - 10-D-5520 - VENT COLLECTION DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-11-26 | 2019-02-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00365 | TPSK-LSPA1-T-PE-00856
[6 empty] | Return Date | 2018-12-13 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5521 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5520 - LP VENT BLOWER PKG |  | Class 1 | Purpose** | IFR | CAN
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-19 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00332 | TPSK-LSPA1-T-PE-01112
[6 empty] | Return Date | 2018-12-06 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5522 | Process Equipment Datasheet - 10-C-5520 A-B - LP Vent Blowers |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-02-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00528 | TPSK-LSPA1-T-PE-00837
[6 empty] | Return Date | 2019-01-24 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5550 | PROCESS EQUIPMENT DATA SHEET - 10-D-5550 - HP FLARE KNOCK OUT DRUM |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-12-07 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00142 | TPSK-LSPA1-T-PE-00440 | TPSK-LSPA1-T-PE-01020
[6 empty] | Return Date | 2018-10-26 | 2019-01-04 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5551 | PROCESS EQUIPMENT DATA SHEET - 10-P-5550 - HP FLARE KNOCK OUT DRUM PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-01-30 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01366
[6 empty] | Return Date | 2019-01-24 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R2
| PE | OL1-2G30-5552 | PROCESS EQUIPMENT DATA SHEET - 10-D-5552 - LPG STORAGE DRUM |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-07 | 2019-03-07 | 2019-04-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-01008 | TPSK-LSPA1-T-PE-01260
[6 empty] | Return Date | 2018-12-27 | 2019-03-27 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G30-5553 | PROCESS EQUIPMENT DATA SHEET - 10-E-5552 - LPG VAPORIZER / SUPERHEATER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-10 | 2019-03-14 | 2019-05-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00622 | TPSK-LSPA1-T-PE-01054 | TPSK-LSPA1-T-PE-01589
[6 empty] | Return Date | 2019-02-04 | 2019-03-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5555 | Process Equipment Datasheet - 10-D-5553 - LPG Vaporizer - Superhtr Cond Pot |  | Class Final | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-10 | 2019-03-11 | 2019-05-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00619 | TPSK-LSPA1-T-PE-01018 | TPSK-LSPA1-T-PE-01590
[6 empty] | Return Date | 2019-02-04 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5560 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5560 - HP/LLDPE LP FLARE PACKAGE |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-11-29 | 2019-03-07 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00398 | TPSK-LSPA1-T-PE-01007 | TPSK-LSPA1-T-PE-01506
[6 empty] | Return Date | 2018-12-13 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5565 | PROCESS EQUIPMENT DATA SHEET- 10-D-5565 - LLDPE LP FLARE KNOCK OUT DRUM |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-20 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00558 | TPSK-LSPA1-T-PE-00989
[6 empty] | Return Date | 2019-01-22 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5566 | Process Equipment Datasheet - 10-P-5565 A-B - Polyolefins Flare Knock-out Pumps |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-10 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00623 | TPSK-LSPA1-T-PE-01366
[6 empty] | Return Date | 2019-02-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5570 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5570 - ENCLOSED GROUND FLARE PACKAGE |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2019-03-01 | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00959 | TPSK-LSPA1-T-PE-01326
[6 empty] | Return Date | 2019-03-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5600 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5600 - PYGAS AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-11 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5601 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5601 - BUTADIENE AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-07 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5602 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5602 - QW AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-07 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5603 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5603 - CGC AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-07 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5604 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5604 - REFRIG AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-07 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5605 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5605 - FURNACE AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-07 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5606 | PROCESS EQUIPMENT DATA SHEET - 10-P-5600 - PYGAS AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-31 | 2019-03-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00779 | TPSK-LSPA1-T-PE-01051
[6 empty] | Return Date | 2019-01-22 | 2019-03-04 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5607 | PROCESS EQUIPMENT DATA SHEET - 10-P-5601 - BUTADIENE AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5608 | PROCESS EQUIPMENT DATA SHEET - 10-P-5602 - QW AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5609 | PROCESS EQUIPMENT DATA SHEET - 10-P-5603 - CGC AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5610 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5610 - HYDROBLAST SUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-04-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-01281
[6 empty] | Return Date | 2019-02-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5611 | PROCESS EQUIPMENT DATA SHEET - 10-P-5610 - HYDROBLAST PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-03-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00590 | TPSK-LSPA1-T-PE-01051
[6 empty] | Return Date | 2019-01-24 | 2019-04-02
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5612 | PROCESS EQUIPMENT DATA SHEET - 10-F-5610 - HYDROBLAST FILTER |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02 | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-12-10 | 2019-03-07 | 2019-04-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00454 | TPSK-LSPA1-T-PE-01009 | TPSK-LSPA1-T-PE-01259
[6 empty] | Return Date | 2019-03-11 | 2019-03-27 | 2019-05-09
[6 empty] | Owner Cmmt* | R1 | R2 | R2
| PE | OL1-2G30-5613 | PROCESS EQUIPMENT DATA SHEET - 10-P-5604 - REFRIG AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5614 | PROCESS EQUIPMENT DATA SHEET - 10-P-5605 - FURNACE AREA OILY WATER PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00779
[6 empty] | Return Date | 2019-01-22 | 2019-03-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5615 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5615 - OLEFINS STORMWATER SUMP |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-11 | 2019-03-01 | 2019-03-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00636 | TPSK-LSPA1-T-PE-00960 | TPSK-LSPA1-T-PE-01068
[6 empty] | Return Date | 2019-02-04 | 2019-03-14 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5616 | PROCESS EQUIPMENT DATA SHEET - 10-P-5615 - OLEFINS STORMWATER SUMP PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00576 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5620 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5620 - OLEFINS HOLDING BASIN |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-03-01 | 2019-03-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00960 | TPSK-LSPA1-T-PE-01068
[6 empty] | Return Date | 2019-02-04 | 2019-03-14 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5621 | PROCESS EQUIPMENT DATA SHEET - 10-P-5621 - OLEFINS HOLDING BASIN SKIM OIL PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-30 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00576 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01022
[6 empty] | Return Date | 2019-01-22 | 2019-03-05 | 2019-03-27
[6 empty] | Owner Cmmt* | R1 | R2 | R1
| PE | OL1-2G30-5622 | PROCESS EQUIPMENT DATA SHEET - 10-P-5620 - OLEFINS HOLDING BASIN PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-11 | 2019-04-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00635 | TPSK-LSPA1-T-PE-01255
[6 empty] | Return Date | 2019-02-04 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5623 | Process Equipment Datasheet - 10-P-5626 A-B - Gate House Septic Tank Pumps |  | Class Final | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-30 | 2019-03-25 | 2019-04-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01152 | TPSK-LSPA1-T-PE-01255
[6 empty] | Return Date | 2019-01-22 | 2019-03-05 | 2019-04-12
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-5624 | Process Equipment Datasheet - 10-P-5627 A-B - West Gate House Septic Tank Pumps |  | Class Final | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-30 | 2019-03-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-01-22 | 2019-03-05 | 2019-04-12
[6 empty] | Owner Cmmt* | R1 | R2 | R1
| PE | OL1-2G30-5625 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5625 - SANITARY LIFT STATION IFAR 1 |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-30 | 2019-03-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-01-22 | 2019-03-05 | 2019-04-12
[6 empty] | Owner Cmmt* | R1 | R2 | R1
| PE | OL1-2G30-5626 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5626 - SANITARY LIFT STATION IFAR 2 |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-11 | 2019-04-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-01257
[6 empty] | Return Date | 2019-02-04 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5627 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5627 - SANITARY LIFT STATION WEST GATE HOUSE |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-11 | 2019-04-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-01257
[6 empty] | Return Date | 2019-02-04 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5628 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5628 - SANITARY LIFT STATION EAST GATE HOUSE |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-11 | 2019-04-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-01257
[6 empty] | Return Date | 2019-02-04 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5630 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5630 - CT AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-11 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5631 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5631 - CWWT AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-11 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5632 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5632 - HP FLARE AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-11 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5633 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5633 - HP FLARE AREA STORMWATER SUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-11 | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00636 | TPSK-LSPA1-T-PE-00960
[6 empty] | Return Date | 2019-02-04 | 2019-03-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5635 | PROCESS EQUIPMENT DATA SHEET - 10-P-5630 - CT AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5636 | PROCESS EQUIPMENT DATA SHEET - 10-P-5631 - CWWT AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5637 | PROCESS EQUIPMENT DATA SHEET - 10-P-5632 - HP FLARE AREA OILY WASTEWATER SUMP PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00576 | TPSK-LSPA1-T-PE-01019
[6 empty] | Return Date | 2019-01-22 | 2019-03-27
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5638 | PROCESS EQUIPMENT DATA SHEET - 10-P-5633 - HP FLARE AREA STORMWATER SUMP PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00576 | TPSK-LSPA1-T-PE-01019
[6 empty] | Return Date | 2019-01-22 | 2019-03-27
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5640 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5640 - OILY WASTEWATER EQUALIZATION TANKS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00809 | TPSK-LSPA1-T-PE-01176
[6 empty] | Return Date | 2019-03-15 | 2019-04-22
[6 empty] | Owner Cmmt* | R1 | R2
| PE | OL1-2G30-5641 | PROCESS EQUIPMENT DATA SHEET - 10-P-5641 - WASTEWATER EQ TANK SKIMMED OIL PUMP |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-03-15 | 2019-04-12
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5642 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5642 - COOLING WATER BLOWDOWN BASIS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00808 | TPSK-LSPA1-T-PE-01511
[6 empty] | Return Date | 2019-03-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5643 | PROCESS EQUIPMENT DATA SHEET - 10-P-5642 - COOLING WATER BD BASIN PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-05-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01543
[6 empty] | Return Date | 2019-03-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5644 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5644 - WASTE WATER CPI / IGF PACKAGE |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-11-06 | 2018-12-07 | 2019-02-01 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00281 | TPSK-LSPA1-T-PE-00442 | TPSK-LSPA1-T-PE-00797 | TPSK-LSPA1-T-PE-01606
[6 empty] | Return Date | 2018-11-26 | 2019-01-04 | 2019-03-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G30-5645 | PROCESS EQUIPMENT DATA SHEET - 10-P-5640 - OILY WASTEWATER EQ TANK PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01177
[6 empty] | Return Date | 2019-03-15
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5646 | Process Equipment Datasheet - 10-PIT-5606 - C3 Hydrog Area Oily Wastewater Sump |  | Class Final | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-07 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5647 | Process Equipment Datasheet - 10-PIT-5607 - Flare KO Drum Oily Wastewater Sump |  | Class Final | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-07 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5648 | Process Equipment Datasheet - 10-P-5606 A-B - C3 Hydrog Area Oily Wastewater Pump |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5649 | Process Equipment Datasheet - 10-P-5607 A-B - Flare KO Drum Oily Wastewater Pump |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00779
[6 empty] | Return Date | 2019-01-22 | 2019-03-04
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5650 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5650 - BIO TREATMENT UNIT |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-11-06 | 2018-12-07 | 2019-02-01 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00281 | TPSK-LSPA1-T-PE-00442 | TPSK-LSPA1-T-PE-00797 | TPSK-LSPA1-T-PE-01606
[6 empty] | Return Date | 2018-11-26 | 2019-01-04 | 2019-03-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G30-5653 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5655 - WASTEWATER DUAL MEDIA FILTERS PKG |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07 | 2019-01-07 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2018-11-06 | 2018-12-07 | 2019-02-01 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00282 | TPSK-LSPA1-T-PE-00441 | TPSK-LSPA1-T-PE-00798 | TPSK-LSPA1-T-PE-01607
[6 empty] | Return Date | 2018-11-26 | 2019-01-04 | 2019-03-11
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5654 | PROCESS EQUIPMENT DATA SHEET - 10-P-5655 - EQUALIZATION PIT PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-03-15 | 2019-04-12
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5655 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5655 - EQUALIZATION PIT |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00808 | TPSK-LSPA1-T-PE-01178
[6 empty] | Return Date | 2019-03-15 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5656 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5656 - FINAL CHECK BASIN |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00808 | TPSK-LSPA1-T-PE-01178
[6 empty] | Return Date | 2019-03-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5657 | PROCESS EQUIPMENT DATA SHEET - 10-P-5656 - FINAL CHECK BASIN PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01512
[6 empty] | Return Date | 2019-03-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5670 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5670 - DEWATERING PACKAGE |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-11-06 | 2018-12-07 | 2019-02-01 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00281 | TPSK-LSPA1-T-PE-00442 | TPSK-LSPA1-T-PE-00797 | TPSK-LSPA1-T-PE-01606
[6 empty] | Return Date | 2018-11-26 | 2019-01-04 | 2019-03-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G30-5674 | PROCESS EQUIPMENT DATA SHEET - 10-P-5675 - SLOP OIL TRANSFER PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-03-15 | 2019-04-12
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5675 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5675 - SLOP OIL TANKS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00809 | TPSK-LSPA1-T-PE-01176
[6 empty] | Return Date | 2019-03-15 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5676 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5676 - OILY SLUDGE TANK |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00809 | TPSK-LSPA1-T-PE-01176
[6 empty] | Return Date | 2019-03-15 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5677 | PROCESS EQUIPMENT DATA SHEET - 10-P-5676 - OILY SLUDGE TRANSFER PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-03-15 | 2019-04-12
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5690 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5690 - SLOP TANK POLYMER INJECTION PKG |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2019-02-07 | 2019-04-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00821 | TPSK-LSPA1-T-PE-01274
[6 empty] | Return Date | 2019-03-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5691 | Process Equipment Datasheet - 10-PK-5691 - Slop Tank Acid Injection Pkg |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2019-02-07 | 2019-04-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00821 | TPSK-LSPA1-T-PE-01274
[6 empty] | Return Date | 2019-03-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5692 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5692 - SLOP OIL TANK ACID INJECTION PKG |  | Class 1 | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5695 | Process Equipment Datasheet - 10-PK-5695 - Bio Treat Sulfuric Acid Inj Pkg |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01629
Return Date
Owner Cmmt*
| PE | OL1-2G30-5698 | Process Equipment Datasheet - 10-PK-5698 - Bio Treat Caustic Inj Pkg |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01629
Return Date
Owner Cmmt*
| PE | OL1-2G30-5900 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5900 - SULFURIC ACID TANK |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-11-26 | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00364 | TPSK-LSPA1-T-PE-00647
[6 empty] | Return Date | 2018-12-17 | 2019-02-04
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5901 | PROCESS EQUIPMENT DATA SHEET - 10-P-5900 - SULFURIC ACID PUMPS |  | Class 1 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-28 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00738 | TPSK-LSPA1-T-PE-01177
[6 empty] | Return Date | 2019-03-04 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5902 | Process Equipment Datasheet - 10-P-5901 A-B - Sulfuric Acid Metering Pumps |  | Class Final | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-01-30 | 2019-03-21 | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01129 | TPSK-LSPA1-T-PE-01323
[6 empty] | Return Date | 2019-01-24 | 2019-03-05 | 2019-04-04
[6 empty] | Owner Cmmt* | R1 | R2 | R2
| PE | OL1-2G30-5905 | Process Equipment Datasheet - 10-P-5905 A-B - CTU Sulfuric Acid Metering Pumps |  | Class Final | Purpose** | IFD | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01129 | TPSK-LSPA1-T-PE-01323
[6 empty] | Return Date | 2019-04-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5910 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5910 - OXYGEN SCAVENGER INJ PKG |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-12-10 | 2019-01-25 | 2019-03-14 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00456 | TPSK-LSPA1-T-PE-00727 | TPSK-LSPA1-T-PE-01063 | TPSK-LSPA1-T-PE-01111
[6 empty] | Return Date | 2019-01-04 | 2019-03-04 | 2019-04-02 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R1
| PE | OL1-2G30-5912 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5912 - NEUTRALIZING AMINE INHIBITOR INJ PKG |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-12-10 | 2019-01-25 | 2019-03-14 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00456 | TPSK-LSPA1-T-PE-00727 | TPSK-LSPA1-T-PE-01063 | TPSK-LSPA1-T-PE-01111
[6 empty] | Return Date | 2019-01-04 | 2019-03-04 | 2019-04-02 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R1
| PE | OL1-2G30-5914 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5914 - PHOSPHATE INJECTION PACKAGE |  | Class 1 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10 | 2019-01-10 | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2018-12-10 | 2019-01-28 | 2019-03-14 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00456 | TPSK-LSPA1-T-PE-00739 | TPSK-LSPA1-T-PE-01063 | TPSK-LSPA1-T-PE-01111
[6 empty] | Return Date | 2019-01-04 | 2019-03-04 | 2019-04-02 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R1
| PE | OL1-2G30-5950 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5950 - SODIUM HYPOCHLORITE TANK |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18 | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-04 | 2019-03-14 | 2019-04-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00406 | TPSK-LSPA1-T-PE-01055 | TPSK-LSPA1-T-PE-01258
[6 empty] | Return Date | 2019-01-22 | 2019-03-29 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G30-5951 | PROCESS EQUIPMENT DATA SHEET - 10-P-5950 - SODIUM HYPOCHLORITE METERING PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01 | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-21 | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-01129 | TPSK-LSPA1-T-PE-01323
[6 empty] | Return Date | 2019-01-24 | 2019-04-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5955 | Process Equipment Datasheet - 10-P-5955 A-B - CTU NaOCL Metering Pumps |  | Class Final | Purpose** | IFD | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-21 | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01129 | TPSK-LSPA1-T-PE-01323
[6 empty] | Return Date | 2019-04-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-4G30-1001 | See document number 036909C-1011-PDS-0117-1101 or OL1-2G30-1101 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00117
Return Date
Owner Cmmt*
| PE | OL1-4G30-1008 | See document number 036909C-1011-PDS-0630-1108 or OL1-2G30-1108 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
[6 empty] | Return Date | 2019-02-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-4G30-1009 | See document number 036909C-1011-PDS-0610-1109 or OL1-2G30-1109 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-1010 | See document number 036909C-1011-PDS-0610-1110 or OL1-2G30-1110 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-1011 | See document number 036909C-1011-PDS-1040-1111 or OL1-2G30-1111 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00090
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
| PE | OL1-4G30-2001 | See document number 036909C-1012-PDS-0117-1201 or OL1-2G30-1201 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00117
Return Date
Owner Cmmt*
| PE | OL1-4G30-2008 | See document number 036909C-1012-PDS-0630-1208 or OL1-2G30-1208 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-2009 | See document number 036909C-1012-PDS-0610-1209 or OL1-2G30-1209 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-2011 | See document number 036909C-1012-PDS-1040-1211 or OL1-2G30-1211 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00090
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
Category Code: G31 Process Instrument Data sheets
| PE | OL1-2G31-1001 | Process Data Sheet For Analyzers Feed Preparation - Area 10 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01634
Return Date
Owner Cmmt*
| PE | OL1-2G31-1101 | Process Data Sheet For Analyzers Recycle Gas Furnace - Area 11 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01634
Return Date
Owner Cmmt*
| PE | OL1-2G31-1112 | ATTEMPERATOR DATA SHEET |  | Class 2 | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-14 | 2019-03-27
Revised Plan
[6 empty] | Issue Actual | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00757
[6 empty] | Return Date | 2019-02-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G31-11YY | RESTRICTION ORIFICE DATA SHEETS |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-05-16 | 2019-06-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-1201 | Process Data Sheet For Analyzers Liquid Cracking Furnace - Area 12 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01634
Return Date
Owner Cmmt*
| PE | OL1-2G31-1212 | ATTEMPERATOR DATA SHEET |  | Class 2 | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-14 | 2019-03-27
Revised Plan
[6 empty] | Issue Actual | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00757
[6 empty] | Return Date | 2019-02-26
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-12YY | RESTRICTION ORIFICE DATA SHEETS |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-05-16 | 2019-06-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-13YY | RESTRICTION ORIFICE DATA SHEETS |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-05-16 | 2019-06-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-14YY | RESTRICTION ORIFICE DATA SHEETS |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-05-16 | 2019-06-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-15YY | RESTRICTION ORIFICE DATA SHEETS |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-05-16 | 2019-06-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-16YY | RESTRICTION ORIFICE DATA SHEETS |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-05-16 | 2019-06-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-2001 | Process Data Sheet For Analyzers Quench Oil - Area 20 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01634
Return Date
Owner Cmmt*
| PE | OL1-2G31-2101 | Process Data Sheet For Analyzer Quench Water - Dilution Steam - Area 21 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01634
Return Date
Owner Cmmt*
| PE | OL1-2G31-2301 | Process Data Sheet For Analyzers Caustic - Area 23 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01637
Return Date
Owner Cmmt*
| PE | OL1-2G31-2401 | Data Sheet For Analyzers Dehydration - Regen - Deprop - C2 Hydrog - Area 24 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01664
Return Date
Owner Cmmt*
| PE | OL1-2G31-2501 | Data Sheet For Analyzers Cold Fractionation - Area 25 |  | Class Final | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01664
Return Date
Owner Cmmt*
| PE | OL1-2G31-XXXA | AREA 30 RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16
[6 empty] | Revised Plan | 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-XXXB | AREA 53 RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16
[6 empty] | Revised Plan | 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-XXXC | AREA 55 RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16
[6 empty] | Revised Plan | 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-XXXD | AREA 56 RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16
[6 empty] | Revised Plan | 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-XXXX | RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16
[6 empty] | Revised Plan | 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G32 Process Safety Valve Data sheets
| PE | OL1-2G32-1101 | USC 36M Steam Drum PSV Datasheet - 10-PSV-1142A |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-11 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01028 | TPSK-LSPA1-T-PE-01602
[6 empty] | Return Date | 2019-04-02
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G32-1102 | USC 36M Steam Drum PSV Datasheet - 10-PSV-1142B |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-11 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01028 | TPSK-LSPA1-T-PE-01602
[6 empty] | Return Date | 2019-04-02
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G32-1103 | USC 36M Superheater Outlet PSV Datasheet - 10-PSV-1144 |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-11 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01028 | TPSK-LSPA1-T-PE-01602
[6 empty] | Return Date | 2019-04-02
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G32-11XX | PRESSURE RELIEF VALVE DATA SHEETS |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-01-18 | 2019-06-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-1201 | USC 132U Steam Drum PSV Datasheet - 10-PSV-1242A |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-11 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01029 | TPSK-LSPA1-T-PE-01603
[6 empty] | Return Date | 2019-04-02
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G32-1202 | USC 132U Steam Drum PSV Datasheet - 10-PSV-1242B |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-11 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01029 | TPSK-LSPA1-T-PE-01603
[6 empty] | Return Date | 2019-04-02
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G32-1203 | USC 132U Superheater Outlet PSV Datasheet - 10-PSV-1244 |  | Class Final | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-03-11 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01029 | TPSK-LSPA1-T-PE-01603
[6 empty] | Return Date | 2019-04-02
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G32-12XX | PRESSURE RELIEF VALVE DATA SHEETS |  | Class 2 | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-01-18 | 2019-06-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-XXXA | AREA 30 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-05-06 | 2019-09-15 | 2020-04-15
[6 empty] | Revised Plan | 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-XXXB | AREA 53 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-05-06 | 2019-09-15 | 2020-04-15
[6 empty] | Revised Plan | 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-XXXC | AREA 55 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-05-06 | 2019-09-15 | 2020-04-15
[6 empty] | Revised Plan | 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-XXXD | AREA 56 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-05-06 | 2019-09-15 | 2020-04-15
[6 empty] | Revised Plan | 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-XXXE | PSV DATA SHEETS & INDEX & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-05-06 | 2019-09-15 | 2020-04-15
[6 empty] | Revised Plan | 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G40 Block Flow Diagram
| PE | OL1-2G40-0010 | BLOCK FLOW DIAGRAM - OLEFINS UNIT 10 - OVERALL PLANT SCHEME |  | Class 2 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2018-10-10 | 2018-10-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
Category Code: G41 Process Flow Diagrams
| PE | OL1-2G41-0001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - GENERAL - LEGENDS & SYMBOLS |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-0002 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - GENERAL - DRAWING INDEX |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-1001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 10 FEED PREPARATION - FEED PREHEAT |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-1003 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 10 FEED PREPARATION - FEEDSTOCK DISTRIBUTION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-1101 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 11 FURNACES - RECYCLE GAS CRACKING FURNACE |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-1201 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 12 FURNACES - LIQUID CRACKING FURNACE |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-1901 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 19 FEED PREPARATION & FURNACES AUX - DECOKE AIR COMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-1902 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 19 FEED PREPARATION & FURNACES AUX - CHEMICAL STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 20 QUENCH OIL - QUENCH OIL TOWER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2002 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 20 QUENCH OIL - HEAVY FUEL OIL STRIPPER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2101 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 21 QUENCH WATER / DILUTION STEAM - QUENCH WATER TOWER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2102 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 21 QUENCH WATER / DILUTION STEAM - QUENCH WATER CIRCUIT |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2103 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 21 QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2201 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 22 CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2301 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - CAUSTIC TOWER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2302 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC HANDLING |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2303 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2304 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC TREATMENT |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2305 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - WET AIR OXIDATION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2401 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CG DEHYDRATION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2402 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - REGENERATION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2403 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2404 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2405 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2501 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2502 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - RESIDUE GAS SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2503 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - DEMETHANIZER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2504 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - DEETHANIZER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2505 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - ETHYLENE FRACTIONATION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2506 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - HYDROGEN PURIFICATION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2601 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - C3 HYDROGENATION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2602 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - SECONDARY DEETHANIZER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2603 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - PROPYLENE FRACTIONATION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2604 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - DEBUTANIZER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2701 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - GHU-1 REACTOR & DEPENTANIZER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2702 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - GHU-1 RERUN TOWER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-11 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2703 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - HYDROG REACTIVATION GAS SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2704 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2801 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - PROPYLENE REFRIGERATION 1 |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2802 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - PROPYLENE REFRIGERATION 2 |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2803 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - ETHYLENE REFRIGERATION 1 |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2804 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - ETHYLENE REFRIGERATION 2 |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-2901 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 29 OLEFINS RECOVERY AUX - CHEMICAL STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-3001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU PREDISTILLATION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-3002 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU EVAPORATION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-3003 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU RECTIFIER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-3004 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU DEGASSING |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-3005 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU FRACTIONATION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-3101 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 31 C4 UNIT UTILITIES - BDU SOLVENT REGENERATION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-3102 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 31 C4 UNIT UTILITIES - BDU STEAM AND CONDENSATE SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G41-3901 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 39 C4 UNIT AUX - BDU CHEMICAL STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
Category Code: G42 Utility Flow Diagrams
| PE | OL1-2G42-5001 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 50 WATER SYSTEMS - TREATED, POTABLE, AND DEMIN WATER SYSTEMS |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5101 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - STEAM BALANCE DIAGRAM |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5102 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - CONDENSATE AND BOILER FEEDWATER SYSTEMS |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5103 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - CONDENSATE TREATMENT SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5104 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - FURNACE BLOWDOWN SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5201 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 52 FUEL SYSTEM - FUEL GAS SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5301 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 53 COOLING WATER SYSTEM - COOLING WATER DIAGRAM |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5311 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 53 COOLING WATER SYSTEM - COOLING TOWER |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5401 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 54 AIR AND NITROGEN SYSTEM - PLANT AIR, INSTRUMENT AIR, AND NITROGEN SYSTEMS |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5501 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - FLARE AND BLOWDOWN SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5502 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - PROCESS VENT GAS COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5511 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - HP AND LLDPE LP FLARE |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5512 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - ENCLOSED GROUND FLARE |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5601 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OILY WASTEWATER COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5602 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SURFACE RUNOFF COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5603 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CRACKER HOLDING BASIN |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5604 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - DOMESTIC WASTEWATER COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5610 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - HP FLARE AREA STORMWATER AND OILY WASTEWATER COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5611 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OSBL OILY WASTEWATER COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5612 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OILY WASTEWATER EQUILIZATION TANK |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5613 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CPI & IGF PACKAGES |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5614 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - BIOTREATMENT PACKAGE |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5615 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CHECK BASIN |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5616 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SLUDGE DEWATERING PACKAGE |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5617 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SLOP AND OIL SLUDGE |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5901 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 59 UTILITIES AUX - CHEMICAL STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G42-5911 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 59 UTILITIES AUX - COMPLEX U & O CHEMICAL STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20 | 2019-06-20
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-10-10 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A3 | A3
Category Code: G43 Process and Instrument Diagrams (P&ID)
| PE | OL1-2G43-0001 | P&ID - Olefins Unit 10 - Common - Abbreviations And Numbering |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-05-16 | 2019-05-16 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-0002 | P&ID - Olefins Unit 10 - Common - Piping Symbols |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-05-16 | 2019-05-16 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-0003 | P&ID - Olefins Unit 10 - Common - Instrumentation Symbols |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-05-16 | 2019-05-16 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-0004 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 1 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-05-16 | 2019-05-16 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-0005 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 2 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-05-16 | 2019-05-16 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-0010 | P&ID - Olefins Unit 10 - Common - Instrument Details |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-05-16 | 2019-05-16 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-0011 | P&ID - Olefins Unit 10 - Common - EIV Block Valves Typical |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-05-16 | 2019-05-16 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-1001 | P&ID - FEED PREPARATION - FURNACE LIQUID FEED |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1002 | P&ID - FEED PREPARATION - FURNACE LPG FEED HEATER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1003 | P&ID - FEED PREPARATION - FURNACE LPG FEED VAPORIZER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1004 | P&ID - FEED PREPARATION - FURNACE LPG FEED SUPERHEATER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1005 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - LPG Steam Vaporizer |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1006 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - LPG Feed Steam Heater |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual |  | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date |  | 2019-05-05
[6 empty] | Owner Cmmt* |  | CA
| PE | OL1-2G43-1023 | P&ID - FEED PREPARATION - C2 FEED SUPERHEATER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1030 | P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1031 | P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1035 | P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION (UTILITY) - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1036 | P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION (UTILITY) - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1101 | P&ID - RECYCLE GAS CRACKING FURNACE - ETHANE FEED DISTRIBUTION HEADER |  | Class 2 | Purpose** | IFR | IBD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1105 | P&ID - RECYCLE GAS CRACKING FURNACE - DILUTION STEAM DISTRIBUTION HEADER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1106 | P&ID - RECYCLE GAS CRACKING FURNACE - DECOKE AIR HEADER DISTRIBUTION HEADER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1107 | P&ID - RECYCLE GAS CRACKING FURNACE - FEED- SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1108 | P&ID - RECYCLE GAS CRACKING FURNACE - FEED- SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1109 | P&ID - RECYCLE GAS CRACKING FURNACE - FEED- SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1110 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed-Sheet 4 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1111 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 5 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1112 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 6 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1115 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 CONVECTION SECTION |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1116 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1117 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1118 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1119 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 RADIANT SECTION CELL A - SHEET 4 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1120 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 RADIANT SECTION CELL B - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1121 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 RADIANT SECTION CELL B - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1125 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 TLX EXCHANGER |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1126 | P&ID - RECYCLE GAS CRACKING FURNACE - FURNACE EFFLUENT AND DECOKE MOVS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1127 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1128 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 VHP STEAM DRUM |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1129 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1130 | P&ID - RECYCLE GAS CRACKING FURNACE - BOILER FEED WATER SUPPLY/EXPORT STEAM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1131 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 STEAM COILS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1135 | P&ID - RECYCLE GAS CRACKING FURNACE - FUEL GAS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1140 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 BURNERS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1145 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 DECOKING EFFLUENT |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1150 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 FLUE GAS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1201 | P&ID - LIQUID FEED CRACKING FURNACE -C3 LPG FEED DISTRIBUTION HEADER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1202 | P&ID - LIQUID FEED CRACKING FURNACE -LIQUID FEED DISTRIBUTION HEADER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1205 | P&ID - LIQUID FEED CRACKING FURNACE - DILUTION STEAM DISTRIBUTION HEADER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1206 | P&ID - LIQUID FEED CRACKING FURNACE -DECOKE AIR HEADER DISTRIBUTION HEADER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1207 | P&ID - LIQUID FEED CRACKING FURNACE - FEED- SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1208 | P&ID - LIQUID FEED CRACKING FURNACE - FEED - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1209 | P&ID - LIQUID FEED CRACKING FURNACE - FEED - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1210 | P&ID - LIQUID FEED CRACKING FURNACE - FEED- SHEET 4 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1211 | P&ID - LIQUID FEED CRACKING FURNACE - FEED - SHEET 5 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1212 | P&ID - LIQUID FEED CRACKING FURNACE - FEED - SHEET 6 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1215 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 CONVECTION SECTION |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1216 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1217 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1218 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
[6 empty] | Return Date | 2019-02-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-1218. | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 3 |  | Class As built | Purpose** | IBD
[6 empty] | Rev. | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-04-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-1219 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 RADIANT SECTION CELL B - SHEET 4 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1220 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 RADIANT SECTION CELL B - SHEET 5 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1221 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 RADIANT SECTION CELL B - SHEET 6 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1225 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 TLX EXCHANGER |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1226 | P&ID - LIQUID FEED CRACKING FURNACE -FURNACE EFFLUENT & DECOKE MOVS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1227 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1228 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 VHP STEAM DRUM |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1229 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1230 | P&ID - LIQUID FEED CRACKING FURNACE -BOILER FEED WATER SUPPLY/EXPORT STEAM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1231 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 STEAM COILS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1235 | P&ID - LIQUID FEED CRACKING FURNACE -FUEL GAS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1240 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 BURNERS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1245 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 DECOKING EFFLUENT |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1250 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 FLUE GAS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1315 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 CONVECTION SECTION |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1316 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1317 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1318 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1319 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL B - SHEET 4 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1320 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL B - SHEET 5 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1321 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL B - SHEET 6 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1325 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 TLX EXCHANGER |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1327 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1328 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 VHP STEAM DRUM |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1329 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1331 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 STEAM COILS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1340 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 BURNERS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1345 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 DECOKING EFFLUENT |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1350 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 FLUE GAS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1360 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 UTILITY STATION |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1361 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 UTILITY DISTRIBUTION |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1415 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 CONVECTION SECTION |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1416 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1417 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1418 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1419 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL B - SHEET 4 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1420 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL B - SHEET 5 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1421 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL B - SHEET 6 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1425 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 TLX EXCHANGER |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1427 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1428 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 VHP STEAM DRUM |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1429 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1431 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 STEAM COILS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1440 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 BURNERS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1445 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 DECOKING EFFLUENT |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1450 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 FLUE GAS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1460 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 UTILITY STATION |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1461 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 UTILITY DISTRIBUTION |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1515 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 CONVECTION SECTION |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1516 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1517 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1518 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1519 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL B - SHEET 4 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1520 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL B - SHEET 5 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1521 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL B - SHEET 6 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1525 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 TLX EXCHANGER |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1527 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1528 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 VHP STEAM DRUM |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1529 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1531 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 STEAM COILS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1540 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 BURNERS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1545 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 DECOKING EFFLUENT |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1550 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 FLUE GAS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1560 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 UTILITY STATION |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1561 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 UTILITY DISTRIBUTION |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1615 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 CONVECTION SECTION |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1616 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1617 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1618 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1619 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL B - SHEET 4 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1620 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL B - SHEET 5 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1621 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL B - SHEET 6 |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1625 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 TLX EXCHANGER |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1627 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1628 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 VHP STEAM DRUM |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1629 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1631 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 STEAM COILS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1640 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 BURNERS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1645 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 DECOKING EFFLUENT |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1650 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 FLUE GAS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1660 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 UTILITY STATION |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1661 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 UTILITY DISTRIBUTION |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2019-06-28 | 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1901 | P&ID - FEED PREPARATION & FURNACES AUX - DMDS INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1915 | P&ID - FEED PREPARATION & FURNACES AUX - DECOKE AIR RECEIVER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2001 | P&ID - QUENCH OIL - QUENCH OIL FRACTIONATOR |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2003 | P&ID - QUENCH OIL - QUENCH OIL CIRCULATING PUMPS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2005 | P&ID - QUENCH OIL - QUENCH OIL FILTRATION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2006 | P&ID - QUENCH OIL - VLP STEAM GENERATION - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2007 | P&ID - QUENCH OIL - VLP STEAM GENERATION - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2008 | P&ID - Olefins Unit 10 - Quench Oil - VLP Steam Generation - Sheet 3 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual |  | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date |  | 2019-04-05
[6 empty] | Owner Cmmt* |  | CA
| PE | OL1-2G43-2020 | P&ID - QUENCH OIL - LIGHT FUEL OIL STRIPPER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2021 | P&ID - QUENCH OIL - FUEL OIL PRODUCT COOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2022 | P&ID - QUENCH OIL - FUEL OIL FILTRATION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2025 | P&ID - QUENCH OIL - HEAVY FUEL OIL STRIPPER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2026 | P&ID - QUENCH OIL - HEAVY FUEL OIL PUMPS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2027 | P&ID - QUENCH OIL - HEAVY FUEL OIL PRODUCT COOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2040 | P&ID - QUENCH OIL DRAIN COLLECTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2042 | P&ID - QUENCH OIL DRAIN DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2101 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER TOWER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2102 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER TOWER OVERHEAD |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2104 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH OIL FRACTIONATOR REFLUX |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2106 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER PUMPS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2108 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER DISTRIBUTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2110 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER COOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2115 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER DRAIN DISTRIBUTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2117 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER DRAIN DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2120 | P&ID - QUENCH WATER / DILUTION STEAM - DISTILLATE STRIPPER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2122 | P&ID - QUENCH WATER / DILUTION STEAM - DISTILLATE STRIPPER REBOILER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2123 | P&ID - QUENCH WATER / DILUTION STEAM - PROCESS WATER STRIPPER FEED |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2125 | P&ID - QUENCH WATER / DILUTION STEAM - PROCESS WATER STRIPPER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2126 | P&ID - QUENCH WATER / DILUTION STEAM - PRCOESS WATER STRIPPER REBOILER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2127 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR FEED PUMPS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2130 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR FEED HEATING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2131 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2132 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR REBOILERS - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2134 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR REBOILERS - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2137 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM SUPERHEATING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2138 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM BLOWDOWN COOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2201 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS 1ST STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2203 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 1ST AND 2ND STAGES |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2204 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 1ST STAGE AFTERCOOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2206 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 2ND STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2208 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 2ND STAGE AFTERCOOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2210 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 3RD STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2211 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 3RD AND 4TH STAGES |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2212 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 3RD STAGE AFTERCOOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2214 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 4TH STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2215 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 4TH STAGE AFTERCOOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2217 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 4TH STAGE DISCHARGE DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2220 | P&ID - CRACKED GAS COMPRESSION - WASH WATER COOLER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2222 | P&ID - CRACKED GAS COMPRESSION - WASH WATER INJECTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2224 | P&ID - CRACKED GAS COMPRESSION - WASH OIL INJECTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2301 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - CAUSTIC TOWER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2303 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - WEAK/INTERMEDIATE CAUSTIC CIRCULATION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2305 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - STRONG CAUSTIC CIRCULATION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2310 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - FRESH CAUSTIC STORAGE |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2311 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC DEOILING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2313 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC DEGASSING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2314 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Drain Collection |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2315 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT WASH OIL DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2316 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - CAUSTIC DRAIN SUMP |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2317 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Yellow Oil Drum |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2318 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC DRAIN SUMP |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2319 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SKIM OIL DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2320 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STORAGE |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2325 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STRIPPER FEED HEATING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2326 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STRIPPER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2328 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STRIPPER OVERHEAD |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2329 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - WAO PACKAGE |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2401 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CAUSTIC TOWER OVERHEAD CHILLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2402 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CAUSTIC TOWER OVERHEAD KO DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2404 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LIQUID DRIER FEED COALESCER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2406 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LIQUID DRIERS - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2407 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LIQUID DRIERS - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2409 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS DEHYDRATION - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2410 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS DEHYDRATION - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2412 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - REGENERATION GAS HEATING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2414 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - REGENERATION GAS COOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2419 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS MERCURY ABSORBER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2420 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER FEED CHILLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2422 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2423 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER REBOILER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2425 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2426 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER REBOILER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2427 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER OVERHEAD |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2428 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER PRODUCT/REFLUX PUMPS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2430 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - 5TH STAGE CRACKED GAS COMPRESSION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2432 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS COMPRESSOR 5TH STAGE AFTERCOOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2433 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION FEED ARSINE REMOVAL |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2435 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION FEED HEATING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2437 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR A |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2438 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR A INTERCOOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2439 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR B |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2440 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR B INTERCOOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2442 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR C |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2444 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CG SECONDARY DEHYDRATOR |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2446 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER REFLUX CHILLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2447 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER REFLUX |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-21 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2501 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED CHILLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2503 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED SEPARATOR NO. 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2505 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED SEPARATOR NO. 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2507 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED SEPARATOR NO. 3 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2511 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2513 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR REBOILER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2515 | P&ID - COLD FRACTIONATION - RESIDUE GAS RECTIFIER CONDENSER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2517 | P&ID - COLD FRACTIONATION - RESIDUE GAS RECTIFIER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2520 | P&ID - COLD FRACTIONATION - DEMETHANIZER FEED COOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2521 | P&ID - COLD FRACTIONATION - DEMETHANIZER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2522 | P&ID - COLD FRACTIONATION - DEMETHANIZER REBOILER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2525 | P&ID - COLD FRACTIONATION - RESIDUE GAS EXPANDER SUCTION/DISCHARGE DRUMS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2527 | P&ID - COLD FRACTIONATION - RESIDUE GAS EXPANDER/RECOMPRESSOR |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2529 | P&ID - COLD FRACTIONATION - HYDROGEN RECOVERY |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2530 | P&ID - COLD FRACTIONATION - PROPYLENE REFRIGERANT SUBCOOLER SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2531 | P&ID - COLD FRACTIONATION - PROPYLENE REFRIGERANT SUBCOOLER SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2532 | P&ID - COLD FRACTIONATION - PRESSURE SWING ABSORPTION UNIT |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2541 | P&ID - COLD FRACTIONATION - DEETHANIZER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2543 | P&ID - COLD FRACTIONATION - DEETHANIZER REBOILER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2546 | P&ID - COLD FRACTIONATION - DEETHANIZER CONDENSER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2547 | P&ID - COLD FRACTIONATION - DEETHANIZER OVERHEAD |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2551 | P&ID - COLD FRACTIONATION - DEMETHANIZER BOTTOMS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2552 | P&ID - COLD FRACTIONATION - C2 SPLITTER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2553 | P&ID - COLD FRACTIONATION - C2 SPLITTER BOTTOMS REBOILER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2554 | P&ID - COLD FRACTIONATION - C2 SPLITTER INTER-REBOILER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2556 | P&ID - COLD FRACTIONATION - ETHANE RECYCLE PUMPS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-02-25 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-2601 | P&ID - HOT FRACTIONATION - C3 HYDROGENATION ARSINE GUARD BED |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2602 | P&ID - HOT FRACTIONATION - C3 GUARD ADSORBERS - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2603 | P&ID - HOT FRACTIONATION - C3 GUARD ADSORBERS - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2604 | P&ID - Olefins Unit 10 - Hot Fractionation - Feed Section |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-03-14 | 2019-05-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2605 | P&ID - HOT FRACTIONATION - C3 HYDROGENATION REACTORS - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-03-14 | 2019-05-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2608 | P&ID - HOT FRACTIONATION - C3 HYDROGENATION AFTERCOOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-03-14 | 2019-05-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2610 | P&ID - HOT FRACTIONATION - C3 HYDROGENATION RECYCLE |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-03-14 | 2019-05-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2615 | P&ID - HOT FRACTIONATION - SECONDARY DEETHANIZER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2616 | P&ID - HOT FRACTIONATION - SECONDARY DEETHANIZER OVERHEAD |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2620 | P&ID - HOT FRACTIONATION - C3 SPLITTER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2621 | P&ID - HOT FRACTIONATION - C3 SPLITTER REBOILERS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2622 | P&ID - HOT FRACTIONATION - C3 SPLITTER BOTTOMS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2625 | P&ID - HOT FRACTIONATION - DEBUTANIZER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2627 | P&ID - HOT FRACTIONATION - DEBUTANIZER OVERHEAD |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2628 | P&ID - HOT FRACTIONATION - DEBUTANIZER OVERHEAD PRODUCT/REFLUX |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-2629 | P&ID - HOT FRACTIONATION - DEBUTANIZER BOTTOMS COOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-03-14; 2019-03-29: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-03-29: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-25; 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| PE | OL1-2G43-2630 | P&ID - HOT FRACTIONATION - C5/PYGAS SURGE DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: B; 2019-03-29: C
[6 empty] | Issue Plan | 2019-02-20 | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-03-14; 2019-03-29: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-03-29: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-25; 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| PE | OL1-2G43-2631 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Bottoms Pumps |  | Class As built | Purpose** | 2019-02-20: IFR; 2019-02-20: CAN
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01298
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2701 | P&ID - GHU & C4/C5 HYDROG - GHU-1 FEED HEATING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2702 | P&ID - GHU & C4/C5 HYDROG - GHU-1 REACTORS - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2703 | P&ID - GHU & C4/C5 HYDROG - GHU-1 REACTORS - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2704 | P&ID - GHU & C4/C5 HYDROG - GHU-1 HOT SEPARATOR |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2705 | P&ID - GHU & C4/C5 HYDROG - GHU-1 COLD SEPARATOR |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2706 | P&ID - GHU & C4/C5 HYDROG - GHU-1 DEPENTANIZER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2707 | P&ID - GHU & C4/C5 HYDROG - GHU C5 CUT PUMPS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2708 | P&ID - GHU & C4/C5 HYDROG - GHU-1 DEPENTANIZER OVERHEAD |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2710 | P&ID - GHU & C4/C5 HYDROG - GHU RERUN TOWER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2711 | P&ID - GHU & C4/C5 HYDROG - GHU RERUN TOWER CONDENSER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2712 | P&ID - GHU & C4/C5 HYDROG - GHU RERUN TOWER REFLUX/PRODUCT PUMP |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2713 | P&ID - GHU & C4/C5 HYDROG - GHU-1 PRODUCT COOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2715 | P&ID - GHU & C4/C5 HYDROG - GHU-1 RECYCLE WASH OIL |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2716 | P&ID - GHU & C4/C5 HYDROG - PYGAS FUEL OIL PRODUCT |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2717 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Refun Tower Liquid Ring Pump |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2718 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Anti-Oxidant Injection Package |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2720 | P&ID - GHU & C4/C5 HYDROG - REACTIVATION GAS HEATING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2722 | P&ID - GHU & C4/C5 HYDROG - REGENERATION DECOKE DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2730 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION FEED SURGE DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2732 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION FEED PUMP |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2733 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION FEED HEATING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2734 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION REACTOR |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2736 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION RECYCLE DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2738 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION RECYCLE/PRODUCT COOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2740 | P&ID - GHU & C4/C5 HYDROG - LIGHT OIL DRAIN DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2742 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Light Oil Drain Drum |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01061; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2801 | P&ID - REFRIGERATION - C3 REFRIGERANT COMPRESSOR SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2802 | P&ID - REFRIGERATION - C3 REFRIGERANT COMPRESSOR SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2803 | P&ID - REFRIGERATION - C3 REFRIGERANT CONDENSER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2804 | P&ID - REFRIGERATION - C3 REFRIGERANT RECEIVER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2805 | P&ID - REFRIGERATION - HP C3 REFRIGERATION DISTRIBUTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2806 | P&ID - REFRIGERATION - C3 REFRIGERANT 4TH STAGE SUCTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2807 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 3 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2808 | P&ID - REFRIGERATION - C3 REFRIGERANT 3RD STAGE SUCTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2810 | P&ID - REFRIGERATION - C3 REFRIGERANT 2ND STAGE SUCTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2812 | P&ID - REFRIGERATION - C3 REFRIGERANT 1ST STAGE SUCTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2814 | P&ID - REFRIGERATION - C3 REFRIGERANT DRAIN DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2816 | P&ID - REFRIGERATION - PROPYLENE PRODUCT PUMP |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2818 | P&ID - REFRIGERATION - PROPYLENE PRODUCT CHILLING SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2819 | P&ID - REFRIGERATION - PROPYLENE PRODUCT CHILLING SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2821 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT COMPRESSOR SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2822 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT COMPRESSOR SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2823 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Compressor - Sheet 3 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01345
Return Date
Owner Cmmt*
| PE | OL1-2G43-2824 | P&ID - REFRIGERATION - C2 REFRIGERANT DESUPERHEATERS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2825 | P&ID - REFRIGERATION - C2 REFRIGERANT DESUPERHEATERS AND CONDENSING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2828 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT SURGE DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2830 | P&ID - REFRIGERATION - HP ETHYLENE LIQUID PRODUCT CHILLER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2834 | P&ID - REFRIGERATION - HP ETHYLENE VAPOR PRODUCT |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2836 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT 3RD STAGE SUCTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2838 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT 2ND STAGE SUCTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2840 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT 1ST STAGE SUCTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2842 | P&ID - REFRIGERATION - LP ETHYLENE PRODUCT COOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2846 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT DRAIN DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-16; 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00653; 2019-02-20: TPSK-LSPA1-T-PE-01345
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2901 | P&ID - OLEFINS RECOVERY AUXILLARY - EMULSION BREAKER INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2902 | P&ID - OLEFINS RECOVERY AUXILLARY - PH CONTROL INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2903 | P&ID - OLEFINS RECOVERY AUXILLARY - POLYMERIZATION INHIBITOR INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2904 | P&ID - OLEFINS RECOVERY AUXILLARY - PROCESS WATER STRIPPER CHEMICAL INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2905 | P&ID - OLEFINS RECOVERY AUXILLARY - CORROSION INHIBITOR INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2906 | P&ID - OLEFINS RECOVERY AUXILLARY - DSG ANTI-FOULANT INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2907 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Caustic Tower Anti Foulant Injection System |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2908 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Neutralization Injection |  | Class As built | Purpose** | 2019-02-20: IFR; 2019-02-20: CAN
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2909 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Methanol Injection System |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2915 | P&ID - OLEFINS RECOVERY AUXILLARY - WASH OIL STORAGE |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2920 | P&ID - OLEFINS RECOVERY AUXILLARY - QUENCH OIL PUMP TURBINE DETAILS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2922 | P&ID - OLEFINS RECOVERY AUXILLARY - QUENCH WATER PUMP TURBINE DETAILS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2924 | P&ID - OLEFINS RECOVERY AUXILLARY - DSG FEED PUMP TURBINE DETAILS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2930 | P&ID - OLEFINS RECOVERY AUXILLARY - CG COMP. TURBINE DETAILS - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2932 | P&ID - OLEFINS RECOVERY AUXILLARY - CG COMP. TURBINE DETAILS - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2934 | P&ID - OLEFINS RECOVERY AUXILLARY - CG COMP. TURBINE DETAILS - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2955 | P&ID - OLEFINS RECOVERY AUXILLARY - C3 REFRIGERANT COMP. TURBINE DETAILS - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2960 | P&ID - OLEFINS RECOVERY AUXILLARY - C3 REFRIGERANT COMP. TURBINE DETAILS - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2965 | P&ID - OLEFINS RECOVERY AUXILLARY - C3 REFRIGERANT COMP. TURBINE DETAILS - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2970 | P&ID - OLEFINS RECOVERY AUXILLARY - C2 REFRIGERANT COMP. TURBINE DETAILS - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2975 | P&ID - OLEFINS RECOVERY AUXILLARY - C2 REFRIGERANT COMP. TURBINE DETAILS - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-2976 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C2R Lube Oil Pump Turbine Details |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-04; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00799; 2019-02-20: TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3001 | P&ID - C4 UNIT - PREDISTILLATION FEED DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3002 | P&ID - C4 UNIT - PREDISTILLATION FEED PUMPS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3003 | P&ID - C4 UNIT - PREDISTILLATION TOWER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3004 | P&ID - C4 UNIT - PREDISTILLATION TOWER REBOILERS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3005 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - C4 Vaporization Tower & Heavy End Disch. Pumps |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3006 | P&ID - C4 UNIT - PREDISTILLATION TOWER OVERHEAD |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3007 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Main Washer & Solvent Cooler |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3008 | P&ID - C4 UNIT - FEED VAPORIZER DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3009 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Main Washer Bottom Pump & Reflux Pump |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3010 | P&ID - C4 UNIT - C4 EVAPORATORS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3011 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Rectifier Pump And Degasser Feed Pump |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3012 | P&ID - C4 UNIT - MAIN WASHER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3013 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - After Washer Overhead |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3014 | P&ID - C4 UNIT - MAIN WASHER OVERHEAD |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3015 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Solvent Heat Exchanger-II And Solvent Heater |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3016 | P&ID - C4 UNIT - RECTIFIER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3017 | P&ID - C4 UNIT - RECTIFIER BOTTOMS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3018 | P&ID - C4 UNIT - AFTERWASHER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3019 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - HC - Water Separator |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3020 | P&ID - C4 UNIT - AFTERWASHER OVERHEAD |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3021 | P&ID - C4 UNIT - SOLVENT HEAT EXCHANGERS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3022 | P&ID - C4 UNIT - SOLVENT HEATING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3023 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Recycle Gas Compressor |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3024 | P&ID - C4 UNIT - SOLVENT COOLING/DEGASSING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3025 | P&ID - C4 UNIT - DEGASSING TOWER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3026 | P&ID - C4 UNIT - DEGASSING TOWER REBOILERS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3027 | P&ID - C4 UNIT - ACETYLENE WASHER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3028 | P&ID - C4 UNIT - ACETYLENE CONDENSING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3029 | P&ID - C4 UNIT - HC/WATER SEPARATOR |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3101 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Solvent Regeneration |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3102 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Water Washer And Condenser |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3103 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Regen Steam Ejector Package |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3104 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Water Washer Accumulator & Solvent Return Pumps |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3105 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Ejector Seal Drum And Waste Water Pumps |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3106 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Blow Down Drum |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3107 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drum |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3108 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Flash Drum |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3109 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Drum And Recycle Pumps |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3110 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Heater And Cooler |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-30
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3111 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - BDU Steam Letdown |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-30
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3112 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drain System - Sheet 1 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-30
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3113 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drain System - Sheet 2 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-30
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3901 | P&ID - C4 UNIT - SOLVENT STORAGE |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-30
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3902 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Solvent Inhibitor Injection System |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-30
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3903 | P&ID - C4 UNIT - SOLVENT INHIBITOR INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-30
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3904 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Anti-Foam Agent Injection System |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-30
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-3905 | P&ID - C4 UNIT - PRODUCT INHIBITOR INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01067
[6 empty] | Return Date | 2019-02-20: 2019-03-30
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5001 | P&ID - UTILITY SYSTEMS - DEMINERALIZATION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5010 | P&ID - UTILITY SYSTEMS - TREATED WATER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5020 | P&ID - UTILITY SYSTEMS - POTABLE WATER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5101 | P&ID - UTILITY SYSTEMS - STEAM LETDOWN STATIONS - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5102 | P&ID - UTILITY SYSTEMS - STEAM LETDOWN STATIONS - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5103 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Station - Sheet 3 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5105 | P&ID - UTILITY SYSTEMS - DEAERATOR |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5110 | P&ID - UTILITY SYSTEMS - SHP BOILER FEEDWATER PUMPS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5111 | P&ID - UTILITY SYSTEMS - BOILER FEEDWATER PUMPS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5113 | P&ID - UTILITY SYSTEMS - SHP BOILER FEEDWATER DISTRIBUTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5114 | P&ID - UTILITY SYSTEMS - BOILER FEEDWATER DISTRIBUTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5115 | P&ID - UTILITY SYSTEMS - SUSPECT CONDENSATE FLASH DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5118 | P&ID - UTILITY SYSTEMS - SUSPECT CONDENSATE COOLING |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5120 | P&ID - UTILITY SYSTEMS - CONDENSATE CARBON FILTERS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5125 | P&ID - UTILITY SYSTEMS - RAW CONDENSATE TANK |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5127 | P&ID - UTILITY SYSTEMS - CONDENSATE POLISHER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5128 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Polisher - Sheet 2 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5130 | P&ID - UTILITY SYSTEMS - CONDENSATE TANK |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5132 | P&ID - UTILITY SYSTEMS - LOW PRESSURE CONDENSATE FLASH DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5134 | P&ID - UTILITY SYSTEMS - INTERMITTENT FURNACE BLOWDOWN DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5140 | P&ID - UTILITY SYSTEMS - SHP STEAM DISTRIBUTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5143 | P&ID - UTILITY SYSTEMS - HP STEAM DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5144 | P&ID - UTILITY SYSTEMS - HP STEAM DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5150 | P&ID - UTILITY SYSTEMS - MP STEAM DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5151 | P&ID - UTILITY SYSTEMS - MP STEAM DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5152 | P&ID - UTILITY SYSTEMS - MP STEAM DISTRIBUTION - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5160 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5161 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5162 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5163 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 4 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5164 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 5 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5166 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 6 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5168 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Steam Ls2 Distribution - Sheet 1 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5170 | P&ID - UTILITY SYSTEMS - SHP/HP CONDENSATE COLLECTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5172 | P&ID - UTILITY SYSTEMS - MP CONDENSATE COLLECTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5176 | P&ID - UTILITY SYSTEMS - LP CONDENSATE COLLECTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5177 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 2 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5178 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 3 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5179 | P&ID - UTILITY SYSTEMS - VLP CONDENSATE COLLECTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00718; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5201 | P&ID - UTILITY SYSTEMS - FUEL GAS SYSTEM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5202 | P&ID - Olefins Unit 10 - Fuel System - Fuel Gas Drum |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5203 | P&ID - UTILITY SYSTEMS - PILOT GAS VAPORIZER AND SUPERHEATER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5210 | P&ID - UTILITY SYSTEMS - FUEL GAS DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5211 | P&ID - UTILITY SYSTEMS - FUEL GAS DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5301 | P&ID - COOLING WATER TOWER - COOLING TOWER - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5302 | P&ID - UTILITY SYSTEMS - COOLING TOWER - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5303 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 3 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5305 | P&ID - UTILITY SYSTEMS - COOLING WATER SUPPLY PUMPS - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5306 | P&ID - UTILITY SYSTEMS - COOLING WATER SUPPLY PUMPS - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5307 | P&ID - UTILITY SYSTEMS - CTU COOLING WATER SUPPY PUMPS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5310 | P&ID - UTILITY SYSTEMS - COOLING WATER SUPPY |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5311 | P&ID - UTILITY SYSTEMS - CTU COOLING WATER SUPPY |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5315 | P&ID - UTILITY SYSTEMS - COOLING WATER SIDE STREAM FILTER PACKAGE |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5317 | P&ID - UTILITY SYSTEMS - COOLING WATER FILTER BACKWASH |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5320 | P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5321 | P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5322 | P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5323 | P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 4 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5324 | P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 5 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5325 | P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 6 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: CAN
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5326 | P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 7 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5351 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Chemical Injection |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5352 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Corrosion Inhibitor Injection |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5401 | P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-29; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00758; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5402 | P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-29; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00758; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5403 | P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-29; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00758; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5404 | P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 4 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-29; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00758; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5410 | P&ID - UTILITY SYSTEMS - INSTRUMENT AIR RECEIVER |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-29; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00758; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5411 | P&ID - UTILITY SYSTEMS - INSTRUMENT AIR DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-29; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00758; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5412 | P&ID - UTILITY SYSTEMS - INSTRUMENT AIR DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-29; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00758; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5420 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-29; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00758; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5421 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-29; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00758; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5422 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-29; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00758; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5424 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 5 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-29; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00758; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5425 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 6 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-29; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00758; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5426 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 6 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-29; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00758; 2019-02-20: TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5501 | P&ID - UTILITY SYSTEMS - HOT FLARE KO DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5502 | P&ID - UTILITY SYSTEMS - COLD FLARE KO DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5503 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Methanol Vaporizer |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5510 | P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5511 | P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5512 | P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5514 | P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 5 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5516 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 5 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5518 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 6 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5519 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - LP Flare Header - Sheet 1 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5520 | P&ID - UTILITY SYSTEMS - COLD FLARE HEADER - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5521 | P&ID - UTILITY SYSTEMS - COLD FLARE HEADER - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5523 | P&ID - UTILITY SYSTEMS - COLD FLARE HEADER - SHEET 4 - DELETED |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5524 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 4 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5526 | P&ID - UTILITY SYSTEMS - PROPYLENE BLOWDOWN HEADER - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5528 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Propylene Blowdown Header - Sheet 2 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5529 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 1 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5531 | P&ID - UTILITY SYSTEMS - HOT BLOWDOWN HEADER - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5533 | P&ID - UTILITY SYSTEMS - HOT BLOWDOWN HEADER - SHEET 4 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5534 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 4 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5535 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 1 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5536 | P&ID - UTILITY SYSTEMS - COLD BLOWDOWN HEADER - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5540 | P&ID - UTILITY SYSTEMS - VOC VENT COLLECTION SYSTEM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5542 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 4 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5545 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Vent Collection System - Sheet 1 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5546 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Vent Collection System - Sheet 2 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5551 | P&ID - UTILITY SYSTEMS - HP FLARE KO DRUM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5553 | P&ID - UTILITY SYSTEMS - HP FLARE PILOT GAS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5555 | P&ID - UTILITY SYSTEMS - HP FLARE |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5575 | P&ID - UTILITY SYSTEMS - LLDPE FLARE |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23; 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00706; 2019-02-20: TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5601 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5602 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5603 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5604 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 4 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5605 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 5 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5606 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 6 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5607 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 7 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5608 | P&ID - Olefins Unit 10 - Wastewater - C3 Hydrog Area Oily Wastewater Sump |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5609 | P&ID - Olefins Unit 10 - Wastewater - Flare Kod Area Oily Wastewater Sump |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5610 | P&ID - Olefins Unit 10 - Wastewater - Oily Waste Water Collection |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5620 | P&ID - UTILITY SYSTEMS - OLEFINS STORM WATER COLLECTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5621 | P&ID - Olefins Unit 10 - Wastewater - HP Flare Area Storm Water Collection |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5630 | P&ID - UTILITY SYSTEMS - OLEFINS HOLDING BASIN |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5631 | P&ID - Olefins Unit 10 - Wastewater - Olefins Holding Basin - Sheet 2 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5640 | P&ID - UTILITY SYSTEMS - SANITARY LIFT STATION - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5641 | P&ID - UTILITY SYSTEMS - SANITARY LIFT STATION - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5642 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 3 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5649 | P&ID - Olefins Unit 10 - Wastewater - HP Flare Area Oily Wastewater Sump |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5650 | P&ID - Olefins Unit 10 - Wastewater - CT Area Oily Wastewater Sump |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5651 | P&ID - UTILITY SYSTEMS - OSBL OILY WATER COLLECTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5652 | P&ID - UTILITY SYSTEMS - OSBL OILY WATER COLLECTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5653 | P&ID - UTILITY SYSTEMS - OSBL OILY WATER COLLECTION - SHEET 3 |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5654 | P&ID - Olefins Unit 10 - Wastewater - Equalization Tank |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5655 | P&ID - Olefins Unit 10 - Wastewater - Waste Water CPI-IGF Package |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5656 | P&ID - Olefins Unit 10 - Wastewater - Domestic Wastewater Collection |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5657 | P&ID - Olefins Unit 10 - Wastewater - Bio Equalization Pit |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5658 | P&ID - Olefins Unit 10 - Wastewater - Bio Treatment Package |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5660 | P&ID - Olefins Unit 10 - Wastewater - Final Check Basin |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5662 | P&ID - Olefins Unit 10 - Wastewater - Dewatering System |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5665 | P&ID - Olefins Unit 10 - Wastewater - Slop Oil Tank A |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5666 | P&ID - Olefins Unit 10 - Wastewater - Slop Oil Tank B |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5667 | P&ID - Olefins Unit 10 - Wastewater - Oily Sludge Tank |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00855; 2019-02-20: TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-02-20: 2019-03-13
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5903 | P&ID - UTILITY SYSTEMS - COOLING WATER HYPOCHLORIDE AND ACID INJECTION |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5904 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - 98 percent Sulfuric Acid Chemical Injection |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5905 | P&ID - UTILITY SYSTEMS - NEUTRALIZING AMINE INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5907 | P&ID - UTILITY SYSTEMS - OXYGEN SCAVENGER INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5908 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Phosphate Injection System |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5915 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Condensate Pump Turbine Details |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5920 | P&ID - UTILITY SYSTEMS - COOLING WATER SUPPLY PUMP TURBINES |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5921 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Olefins CW Pump Turbine Details - Sheet 2 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5922 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Ctu Cooling Water Pump Turbine Details |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5925 | P&ID - UTILITY SYSTEMS - SHP BFW PUMP TURBINE DETAILS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5927 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Lube Oil Pump Turbine A Details |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5928 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Lube Oil Pump Turbine B Details |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5929 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - VLP BFW Pump Turbine Details |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5930 | P&ID - UTILITY SYSTEMS - SHP BFW LUBE OIL PUMP TURBINE DETAILS |  | Class 2 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-31; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00776; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-26
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5932 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - 98 percent Sulfuric Acid Pumps |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13; 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00491; 2019-02-20: TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G43-5933 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sulfuric Acid Chemical Injection - Sheet 3 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01425
Return Date
Owner Cmmt*
| PE | OL1-2G43-5934 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sodium Hypochlorite Chemical Injection - Sheet 2 |  | Class As built | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01425
Return Date
Owner Cmmt*
Category Code: G44 Heat and Material Balance
| PE | OL1-2G44-1001 | OVERALL MATERIAL BALANCE |  | Class 3 | Purpose** | 2019-02-20: IFI; 2019-02-20: IFI
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-21; 2019-02-20: 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-06; 2019-02-20: 2019-03-29
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00009; 2019-02-20: TPSK-LSPA1-T-PE-01199
[6 empty] | Return Date | 2019-02-20: 2018-08-23; 2019-02-20: 2019-04-22
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| PE | OL1-2G44-1002 | HEAT & MATERIAL BALANCE - DESIGN CASE 6 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-31
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00032
Return Date
Owner Cmmt*
| PE | OL1-2G44-1003 | HEAT & MATERIAL BALANCE - DESIGN CASE 8 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-31
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00032
Return Date
Owner Cmmt*
| PE | OL1-2G44-1004 | HEAT & MATERIAL BALANCE - DESIGN CASE 9 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-31
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00032
Return Date
Owner Cmmt*
| PE | OL1-2G44-1010 | HEAT & MATERIAL BALANCE - ISBL SUPPORTING UTILITIES |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00128
Return Date
Owner Cmmt*
| PE | OL1-2G44-1011 | HEAT & MATERIAL BALANCE - AREA-53 (COOLING WATER SYSTEM) |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00116
Return Date
Owner Cmmt*
| PE | OL1-2G44-1012 | HEAT & MATERIAL BALANCE - AREA-55 (FLARE SYSTEM) |  | Class 3 | Purpose** | 2019-02-20: IFI
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01492
Return Date
Owner Cmmt*
| PE | OL1-2G44-1013 | HEAT & MATERIAL BALANCE - AREA-56 (WWT SYSTEM) |  | Class 3 | Purpose** | 2019-02-20: IFI; 2019-02-20: IFI
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-21; 2019-02-20: 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-03; 2019-02-20: 2019-02-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00581; 2019-02-20: TPSK-LSPA1-T-PE-00892
Return Date
Owner Cmmt*
Category Code: G50 Interlocking Description/Cause and Effect Diagrams
| PE | OL1-2G50-1001 | SHUTDOWN INTERLOCK NARRATIVE (36M FURNACE) |  | Class 2 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G50-1101 | Instrument Interlock Descriptions Area 11 - 10-H-1100 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IBD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-04-11; 2019-03-29: 2019-10-22; 2019-08-06: 2019-10-28
[6 empty] | Revised Plan | 2019-02-20: 2019-05-23
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01367
Return Date
Owner Cmmt*
| IE | OL1-2G50-1201 | Instrument Interlock Descriptions Area 12-16 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IBD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-04-11; 2019-03-29: 2019-10-22; 2019-08-06: 2019-10-28
[6 empty] | Revised Plan | 2019-02-20: 2019-05-23
[6 empty] | Issue Actual | 2019-02-20: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01561
Return Date
Owner Cmmt*
| PE | OL1-2G50-2001 | SHUTDOWN INTERLOCK NARRATIVE |  | Class 2 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G50-2101 | Cause and Effect Diagram - Area 21 - Quench Water - Dilution Steam |  | Class Final | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01137
[6 empty] | Return Date | 2019-02-20: 2019-04-22
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G50-2102 | Instrument Interlock Descriptions - Area 21 - Quench Water - Dilution Steam |  | Class Final | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01149
[6 empty] | Return Date | 2019-02-20: 2019-04-22
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G50-2201 | Cause and Effect Diagram - Area 22 - Cracked Gas Compressor |  | Class Final | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 |  |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-28; 2019-03-29: 2019-03-29
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01183; 2019-03-29: TPSK-LSPA1-T-PE--01204
Return Date
Owner Cmmt*
| PE | OL1-2G50-2202 | Instrument Interlock Descriptions - Area 22 - Cracked Gas Compressor |  | Class Final | Purpose** | 2019-02-20: IFI; 2019-02-20: IFR; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-07-05; 2019-03-29: 2019-12-20; 2019-08-06: 2020-04-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-29
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01203
Return Date
Owner Cmmt*
| PE | OL1-2G50-2301 | Cause and Effect Diagram - Area 23 - Caustic and Spent Caustic Treatment |  | Class Final | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01183
[6 empty] | Return Date | 2019-02-20: 2019-04-06
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G50-2302 | Instrument Interlock Descriptions - Area 23 - Caustic and Spent Caustic Treatment |  | Class Final | Purpose** | 2019-02-20: IFI; 2019-02-20: IFR; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-07-05; 2019-03-29: 2019-12-20; 2019-08-06: 2020-04-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01185
Return Date
Owner Cmmt*
| PE | OL1-2G50-2401 | Cause and Effect Diagram - Area 24 - Dehydration - Regen - Deprop- C2 Hydrog |  | Class Final | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01267
[6 empty] | Return Date | 2019-02-20: 2019-05-09
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G50-2402 | Instrument Interlock Descriptions - Area 24 - Dehydration - Regen - Deprop- C2 Hydrog |  | Class Final | Purpose** | 2019-02-20: IFI; 2019-02-20: IFR; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-07-05; 2019-03-29: 2019-12-20; 2019-08-06: 2020-04-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01266
[6 empty] | Return Date | 2019-02-20: 2019-05-09
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G50-2501 | Cause and Effect Diagram - Area 25 - Cold Fractionation "CAUSE AND EFFECT DIAGRAM AREA 25: COLD FRACTIONATION" |  | Class Final | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01133
[6 empty] | Return Date | 2019-02-20: 2019-04-11
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G50-2502 | Instrument Interlock Descriptions - Area 25 - Cold Fractionation |  | Class Final | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01225
Return Date
Owner Cmmt*
| PE | OL1-2G50-2601 | Cause and Effect Diagram - Area 26 - Hot Fractionation |  | Class Final | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01429
Return Date
Owner Cmmt*
| PE | OL1-2G50-2701 | Cause and Effect Diagram - Area 27 - GHU & C4-C5 Hydrog |  | Class Final | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01481
Return Date
Owner Cmmt*
| PE | OL1-2G50-2801 | Cause and Effect Diagram Area 28 - Refrigeration System |  | Class Final | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01540
Return Date
Owner Cmmt*
| PE | OL1-2G50-2901 | Cause and Effect Diagram - Area 29 - Ethylene Auxiliaries |  | Class Final | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01539
Return Date
Owner Cmmt*
| PE | OL1-2G50-5101 | Cause and Effect Diagram - Area 51 - BFW- Steam - Steam Condensate System |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01471
Return Date
Owner Cmmt*
| PE | OL1-2G50-5102 | Instrument Interlock Descriptions - Area 51 - BFW-Steam - Steam Condensate System |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01573
Return Date
Owner Cmmt*
| PE | OL1-2G50-5201 | Cause and Effect Diagram - Area 52 - Fuel System |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01480
Return Date
Owner Cmmt*
| PE | OL1-2G50-5202 | Instrument Interlock Descriptions - Area 52 - Fuel System |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01573
Return Date
Owner Cmmt*
| PE | OL1-2G50-5501 | Cause and Effect Diagram - Area 55 - Vent Gas and Flare System |  | Class Final | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01429
Return Date
Owner Cmmt*
| PE | OL1-2G50-5502 | Instrument Interlock Descriptions Area 55 - Vent Gas and Flare System |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01523
Return Date
Owner Cmmt*
| PE | OL1-2G50-5601 | Cause and Effect Diagram - Area 56 - Wastewater |  | Class Final | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 |  |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24; 2019-03-29: 2019-05-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01462; 2019-03-29: TPSK-LSPA1-T-PE-01537
Return Date
Owner Cmmt*
| PE | OL1-2G50-5602 | Instrument Interlock Descriptions - Area 56 - Wastewater |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01538
Return Date
Owner Cmmt*
Category Code: G51 Sequence of Operation |  |  |  |  | Class 2 | Purpose**
| PE | OL1-2G51-2403 | Sequence Narratives - Area 24 - Dehydration - Regen - Deprop - C2 Hydrog |  | Class Final | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01374
Return Date
Owner Cmmt*
Category Code: G60 Battery Limit and Tie-in
| PE | OL1-2G60-0001 | BATTERY LIMIT SUMMARY |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-04-12; 2019-02-20: 2019-11-15; 2019-03-29: 2020-08-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00948
[6 empty] | Return Date | 2019-02-20: 2019-04-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G60-1101 | TIE-IN SUMMARY - FURNACE AREA 10-H-1100 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-24; 2019-02-20: 2019-06-24; 2019-03-29: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G60-1201 | TIE-IN SUMMARY - FURNACE AREA 10-H-1200 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-24; 2019-02-20: 2019-06-24; 2019-03-29: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G60-1301 | TIE-IN SUMMARY - FURNACE AREA 10-H-1300 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-24; 2019-02-20: 2019-06-24; 2019-03-29: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G60-1401 | TIE-IN SUMMARY - FURNACE AREA 10-H-1400 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-24; 2019-02-20: 2019-06-24; 2019-03-29: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G60-1501 | TIE-IN SUMMARY - FURNACE AREA 10-H-1500 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-24; 2019-02-20: 2019-06-24; 2019-03-29: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G60-1601 | TIE-IN SUMMARY - FURNACE AREA 10-H-1600 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-24; 2019-02-20: 2019-06-24; 2019-03-29: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G61 Equipment List
| PE | OL1-2G61-9001 | EQUIPMENT LIST - OLEFINS UNIT 10 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-02-21
[6 empty] | Revised Plan | 2019-02-20: 2019-05-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G62 Utility Summary
| PE | OL1-2G62-1001 | STEAM BALANCE - DESIGN CASES |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00059
[6 empty] | Return Date | 2019-02-20: 2018-10-04
Owner Cmmt*
| PE | OL1-2G62-1006 | COOLING WATER BALANCE - DESIGN CASES |  | Class 3 | Purpose** | 2019-02-20: IFI; 2019-02-20: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-09-12; 2019-02-20: 2020-04-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00054
[6 empty] | Return Date | 2019-02-20: 2018-10-09
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G62-1008 | FUEL BALANCE - DESIGN CASES |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00049
Return Date
Owner Cmmt*
| PE | OL1-2G62-1010 | AIR & NITROGEN BALANCES |  | Class 3 | Purpose** | 2019-02-20: IFI
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01644
Return Date
Owner Cmmt*
| PE | OL1-2G62-1011 | ELECTRICAL LOAD SUMMARY |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-04
[6 empty] | Revised Plan | 2019-02-20: 2019-07-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G63 Plant Efffluent Summary
| PE | OL1-2G63-0001 | Effluent Summary |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IDD; 2019-08-06: IFF
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-02-21; 2019-02-20: 2019-03-14; 2019-03-29: 2019-12-03; 2019-08-06: 2020-03-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-25; 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00922; 2019-02-20: TPSK-LSPA1-T-PE-01639
[6 empty] | Return Date | 2019-02-20: 2019-03-21
Owner Cmmt* | bar: 2019-02-20
Category Code: G64 Catalyst, Adsobent, and Chemicals Summary |  |  |  |  | Class 1 | Purpose**
| PE | OL1-2G64-1002 | Catalyst & Chemicals Summary |  | Class Final | Purpose** | 2019-02-20: IFI; 2019-02-20: IFI; 2019-03-29: IFF
[6 empty] | Rev. | 2019-02-20: 0; 2019-02-20: 1
[6 empty] | Issue Plan | 2019-02-20: 2019-02-07; 2019-02-20: 2019-02-07; 2019-03-29: 2019-12-13
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25; 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01143; 2019-02-20: TPSK-LSPA1-T-PE-01659
[6 empty] | Return Date | 2019-02-20: 2019-04-22
Owner Cmmt* | bar: 2019-02-20
Category Code: G70 Materials specification and; Utilities specfication and; Catalyst, Adsobent,; and Chemicals specification and ; Fluid and Solid properties
Category Code: G71 Effluent and Waste specification
Category Code: G72 Standard and Specification
Category Code: G73 Guide to Safe Handling of Material
Category Code: G74 Material Selection Guideline
| ME | OL1-2G74-0001 | Material Selection Diagram - Olefins Unit 10 - Legend & Notes |  | Class Final | Purpose** | 2019-02-20: IFA
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-1001 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 10 FEED PREPARATION - FEED PREHEAT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-1003 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 10 FEED PREPARATION - FEEDSTOCK DISTRIBUTION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-1101 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 11 FURNACES - RECYCLE GAS CRACKING FURNACE |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-1201 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 12 FURNACES - LIQUID CRACKING FURNACE |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-1901 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 19 FEED PREPARATION & FURNACES AUX - DECOKE AIR COMPRESSOR |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-1902 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 19 FEED PREPARATION & FURNACES AUX - CHEMICAL STORAGE |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2001 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 20 QUENCH OIL - QUENCH OIL TOWER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2002 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 20 QUENCH OIL - HEAVY FUEL OIL STRIPPER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2101 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 21 QUENCH WATER / DILUTION STEAM - QUENCH WATER TOWER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2102 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 21 QUENCH WATER / DILUTION STEAM - QUENCH WATER CIRCUIT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2103 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 21 QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2201 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 22 CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2301 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - CAUSTIC TOWER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2302 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC HANDLING |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2303 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STORAGE |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2304 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC TREATMENT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2305 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - WET AIR OXIDATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2401 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CG DEHYDRATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2402 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - REGENERATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2403 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2404 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2405 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2501 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2502 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - RESIDUE GAS SYSTEM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2503 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - DEMETHANIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2504 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - DEETHANIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2505 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - ETHYLENE FRACTIONATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2506 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - HYDROGEN PURIFICATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2601 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - C3 HYDROGENATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2602 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - SECONDARY DEETHANIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2603 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - PROPYLENE FRACTIONATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2604 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - DEBUTANIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2701 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - GHU-1 REACTOR & DEPENTANIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-02-20: 2019-06-15; 2019-03-29: 2019-09-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-2702 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - GHU-1 RERUN TOWER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-02-20: 2019-06-15; 2019-03-29: 2019-09-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-2703 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - HYDROG REACTIVATION GAS SYSTEM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-02-20: 2019-06-15; 2019-03-29: 2019-09-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-2704 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-02-20: 2019-06-15; 2019-03-29: 2019-09-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-2801 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - PROPYLENE REFRIGERATION 1 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2802 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - PROPYLENE REFRIGERATION 2 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2803 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - ETHYLENE REFRIGERATION 1 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2804 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - ETHYLENE REFRIGERATION 2 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-2901 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 29 OLEFINS RECOVERY AUX - CHEMICAL STORAGE |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-09; 2019-03-29: 2019-04-08; 2019-08-06: 2019-09-15
[6 empty] | Revised Plan | 2019-03-29: 2019-07-31
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-3001 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU PREDISTILLATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-02-20: 2019-06-15; 2019-03-29: 2019-09-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-3002 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU EVAPORATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-02-20: 2019-06-15; 2019-03-29: 2019-09-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-3003 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU RECTIFIER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-02-20: 2019-06-15; 2019-03-29: 2019-09-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-3004 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU DEGASSING |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-02-20: 2019-06-15; 2019-03-29: 2019-09-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-3005 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU FRACTIONATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-02-20: 2019-06-15; 2019-03-29: 2019-09-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-3101 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 31 C4 UNIT UTILITIES - BDU SOLVENT REGENERATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-02-20: 2019-06-15; 2019-03-29: 2019-09-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-3102 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 31 C4 UNIT UTILITIES - BDU STEAM AND CONDENSATE SYSTEM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-02-20: 2019-06-15; 2019-03-29: 2019-09-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-3901 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 39 C4 UNIT AUX - BDU CHEMICAL STORAGE |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-02-20: 2019-06-15; 2019-03-29: 2019-09-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5001 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 50 WATER SYSTEMS - TREATED, POTABLE, AND DEMIN WATER SYSTEMS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5101 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - STEAM BALANCE DIAGRAM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5102 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - CONDENSATE AND BOILER FEEDWATER SYSTEMS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5103 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - CONDENSATE TREATMENT SYSTEM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5104 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - FURNACE BLOWDOWN SYSTEM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5201 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 52 FUEL SYSTEM - FUEL GAS SYSTEM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5301 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 53 COOLING WATER SYSTEM - COOLING WATER DIAGRAM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-29
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00399
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-5311 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 53 COOLING WATER SYSTEM - COOLING TOWER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-29
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00399
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| PE | OL1-2G74-5401 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 54 AIR AND NITROGEN SYSTEM - PLANT AIR, INSTRUMENT AIR, AND NITROGEN SYSTEMS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5501 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - FLARE AND BLOWDOWN SYSTEM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5502 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - PROCESS VENT GAS COLLECTION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5511 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - HP FLARE |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5512 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - HP FLARE AREA |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5601 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OILY WASTEWATER COLLECTION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5602 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SURFACE RUNOFF COLLECTION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5603 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CRACKER HOLDING BASIN |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5604 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - DOMESTIC WASTEWATER COLLECTION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| ME | OL1-2G74-5610 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - HP Flare Area SW & Oily WW Collection |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5611 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OSBL OILY WASTEWATER COLLECTION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5612 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OILY WASTEWATER EQUILIZATION TANK |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5613 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CPI & IGF PACKAGES |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5614 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - BIOTREATMENT PACKAGE |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5615 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CHECK BASIN |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5616 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SLUDGE DEWATERING PACKAGE |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5617 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SLOP AND OIL SLUDGE |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5901 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 59 UTILITIES AUX - CHEMICAL STORAGE |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
| PE | OL1-2G74-5911 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 59 UTILITIES AUX - COMPLEX U & O CHEMICAL STORAGE |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-03-29: 2019-06-15; 2019-08-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00608
Return Date
Owner Cmmt*
Category Code: G75 Engineering Procedure
Category Code: G76 Supervisory Level Operating Procedures for all Process/Utility System(s). (Shall include Steady State, Stat-Up, Shutdown & transient Operations
| PE | OL1-2G76-1002 | BALANCE OF PLANT SUPERVISORY OPERATING MANUAL |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19; 2019-02-20: 2019-08-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G77 APC Functional specification
Category Code: G81 Appraisal Report for Consultancy Service
Category Code: G82 Appraisal Report for EPC Contractor Work
Category Code: G83 Appraisal Report for Vendor/Supplier
Category Code: G90 Vendor Document/drawings
Category Code: G91 Index/List
| PE | OL1-2G91-1001 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 10 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1002 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 10 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1003 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 10 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1101 | PIPING SPECIALTY ITEM INDEX |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-10; 2019-02-20: 2019-02-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-18
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01642
Return Date
Owner Cmmt*
| PE | OL1-2G91-1201 | PIPING SPECIALTY ITEM INDEX |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-10; 2019-02-20: 2019-02-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-18
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01642
Return Date
Owner Cmmt*
| PE | OL1-2G91-1301 | PIPING SPECIALTY ITEM INDEX |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-10; 2019-02-20: 2019-02-20
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1401 | PIPING SPECIALTY ITEM INDEX |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-10; 2019-02-20: 2019-02-20
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1501 | PIPING SPECIALTY ITEM INDEX |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-10; 2019-02-20: 2019-02-20
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1601 | PIPING SPECIALTY ITEM INDEX |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-10; 2019-02-20: 2019-02-20
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2001 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 20 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2002 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 20 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2003 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 20 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2101 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 21 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2102 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 21 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2103 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 21 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2201 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 22 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2202 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 22 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2203 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 22 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2301 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 23 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2302 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 23 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2303 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 23 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2401 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 24 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2402 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 24 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2403 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 24 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2501 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 25 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2502 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 25 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2503 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 25 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2601 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 26 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2602 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 26 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2603 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 26 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2701 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 27 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2702 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 27 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2703 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 27 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2801 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 28 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2802 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 28 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2803 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 28 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2901 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 29 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2902 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 29 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2903 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 29 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-3001 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 30 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-3002 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 30 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-3003 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 30 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5001 | PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 50 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5002 | PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 50 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5003 | RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 50 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5301 | PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 53 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5302 | PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 53 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5303 | RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 53 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5501 | PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 55 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5502 | PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 55 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5503 | RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 55 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5601 | PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 56 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16; 2019-03-29: 2020-08-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5602 | PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 56 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-06-13
[6 empty] | Revised Plan | 2019-02-20: 2019-06-11
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5603 | RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 56 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-12-03; 2019-03-29: 2020-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G92 Procedures & Standards
Category Code: G93 Policy , Guidelines & Memo
Category Code: G94 Forms & Templates
Category Code: G95 Progress/Status Reports
Category Code: H01 Design basis
Category Code: H02 Abbreviation and standard symbols
Category Code: H03 Project HVAC specification
| EE | OL1-2H03-0001 | Air Conditioning Ventilating And Ducting Design |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00165
[6 empty] | Return Date | 2019-02-20: 2018-10-26
Owner Cmmt* | bar: 2019-02-20
| EE | OL1-2H03-0002 | JOB SUPPLY SPEC. FOR HVAC SYSTEMS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-30; 2019-02-20: 2019-07-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: H04 Equipment, material specification
Category Code: H05 Equipment datasheet
Category Code: H10 Calculation
| EE | OL1-2H10-0001 | HVAC THERMAL CALC. - ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-06-30; 2019-02-20: 2019-07-29
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-01442
Return Date
Owner Cmmt*
| EE | OL1-2H10-0002 | HVAC THERMAL CALC. - ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-06-30; 2019-02-20: 2019-07-29
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-01446
Return Date
Owner Cmmt*
| EE | OL1-2H10-0003 | HVAC THERMAL CALC. - GATEHOUSE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-05-02; 2019-02-20: 2019-06-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-01273
[6 empty] | Return Date | 2019-02-20: 2019-05-07
Owner Cmmt* | bar: 2019-02-20
| EE | OL1-2H10-0004 | HVAC THERMAL CALC. - OPERATION TOOL ROOM |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-05-02; 2019-02-20: 2019-06-01
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
[6 empty] | Issue Actual | 2019-02-20: 2019-04-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-01273
[6 empty] | Return Date | 2019-02-20: 2019-05-07
Owner Cmmt* | bar: 2019-02-20
| EE | OL1-2H10-0005 | Electrical SUB-F & FAR-F – HVAC Thermal Calculation |  | Class As Built | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-01446
Return Date
Owner Cmmt*
Category Code: H20 System schematic diagram
| EE | OL1-2H20-0001 | HVAC PROCESS FLOW DIAGRAM - ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-06-30; 2019-02-20: 2019-07-29
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-18
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-01416
Return Date
Owner Cmmt*
| EE | OL1-2H20-0003 | HVAC PROCESS FLOW DIAGRAM - ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-06-30; 2019-02-20: 2019-07-29
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-01454
Return Date
Owner Cmmt*
| EE | OL1-2H20-0005 | HVAC PROCESS FLOW DIAGRAM - GATEHOUSE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-30; 2019-02-20: 2019-07-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2H20-0007 | HVAC PROCESS FLOW DIAGRAM - OPERATION TOOL ROOM |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-30; 2019-02-20: 2019-07-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2H20-0010 | Electrical Sub-F- And Far-F - HVAC Process Flow Diagram |  | Class As Built | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-01454
Return Date
Owner Cmmt*
Category Code: H21 Arrangement drawing
| EE | OL1-2H21-0001 | HVAC LAYOUT- ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-06-30; 2019-02-20: 2019-07-29
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-18
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-01417
Return Date
Owner Cmmt*
| EE | OL1-2H21-0005 | HVAC LAYOUT- ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-06-30; 2019-02-20: 2019-07-29
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-01453
Return Date
Owner Cmmt*
| EE | OL1-2H21-0010 | HVAC LAYOUT- GATEHOUSE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-05-02; 2019-02-20: 2019-06-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-04
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-1238
Return Date
Owner Cmmt*
| EE | OL1-2H21-0011 | Prefabricated Gatehouse - HVAC Layout And Process Flow Diagram |  | Class As Built | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-04
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-1238
Return Date
Owner Cmmt*
| EE | OL1-2H21-0015 | HVAC LAYOUT- OPERATION TOOL ROOM |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-05-02; 2019-02-20: 2019-06-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-04
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-1238
Return Date
Owner Cmmt*
| EE | OL1-2H21-0020 | Electrical Sub-F- And Far-F - HVAC Layout |  | Class As Built | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-01453
Return Date
Owner Cmmt*
Category Code: H22 Electrical and control drawing/ document
Category Code: H60 Cable drum schedule
Category Code: H61 Cable schedule
Category Code: H62 Connection list
Category Code: H63 Construction material and Bill of quantities
Category Code: H64 Typical installation drawing
Category Code: H71 Appraisal Report for Consultancy Service
Category Code: H72 Appraisal Report for EPC Contractor Work
Category Code: H73 Appraisal Report for Vendor/Supplier
Category Code: H90 Vendor documents
Category Code: H91 Index/List
Category Code: H92 Procedures & Standards
Category Code: H93 Policy , Guidelines & Memo
Category Code: H94 Forms & Templates
Category Code: H95 Progress/Status Reports
Category Code: I10 MAC FEED Document
Category Code: I20 Instrument datasheet
| IE | OL1-2I20-0101 | D/S MECHANICAL RESTRICTION ORIFICE AND ORIFICE |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-02-09; 2019-02-20: 2019-09-04
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0102 | DATA SHEET FOR PITOT TUBE |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-02-09; 2019-02-20: 2019-09-04
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0103 | D/S MECHANICAL ELECTROMAGNETIC FLOW METER |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-02-09; 2019-02-20: 2019-09-04
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0104 | D/S MECHANICAL ROTAMETERS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-02-09; 2019-02-20: 2019-09-04
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0106 | D/S MECHANICAL MASS FLOW MET.CORIOLIS EFFECT |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-02-09; 2019-02-20: 2019-09-04
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0107 | D/S MECHANICAL VENTURI |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-02-09; 2019-02-20: 2019-09-04
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0108 | D/S MECHANICAL ULTRASONIC FLOW METER |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-02-09; 2019-02-20: 2019-09-04
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0111 | D/S MECHANICAL TURBINE METER |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-02-09; 2019-02-20: 2019-09-04
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0112 | D/S MECHANICAL VORTEX METER |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-02-09; 2019-02-20: 2019-09-04
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0120 | DATA SHEET FOR CUSTODY TRANSFER METERING |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-26; 2019-02-20: 2019-11-30
[6 empty] | Revised Plan | 2019-02-20: 2019-07-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0202 | D/S MECHANICAL MAGNETIC LEVEL GAUGE |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-20; 2019-02-20: 2020-07-12
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0203 | D/S MECHANICAL RADAR LEVEL INSTRUMENTS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-20; 2019-02-20: 2020-07-12
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0211 | D/S MECHANICAL SPECIAL LEVEL TRANSMITTERS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-20; 2019-02-20: 2020-07-12
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0212 | D/S MECHANICAL LEVEL GLASS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-20; 2019-02-20: 2020-07-12
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0301 | D/S MECHANICAL PRESSURE & DIFFER.PRESS.GAUGE |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-05; 2019-02-20: 2020-09-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0302 | DATA SHEET FOR THERMOCOUPLE/RTD WITH WELL |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-05; 2019-02-20: 2020-05-26
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0304 | D/S MECHANICAL THERMOMETER WITH WELL |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-05; 2019-02-20: 2020-05-26
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0305 | DATA SHEET FOR MULTIPLE THERMOCOUPLE / RTD |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-05; 2019-02-20: 2020-05-26
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0501 | D/S MECHANICAL CONTROL VALVES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0503 | D/S MECHANICAL SPECIAL CONTROL VALVE |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0504 | D/S MECHANICAL SEVERE SERVICE CONTROL VALVE |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0505 | D/S ANTISURGE VALVES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0506 | D/S MECHANICAL DESUPERHEATER VALVES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0606 | D/S MECHANICAL PNEUMATIC ON OFF VALVES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0608 | D/S MECHANICAL SPECIAL ON OFF VALVES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0609 | D/S MECHANICAL ELECTRIC OPERATED VALVES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0701 | D/S MECHANICAL SAFETY RELIEF VALVE & RUPTURE DISKS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-31; 2019-02-20: 2019-10-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0801 | D/S MECHANICAL ELECTRONIC TRANSMITTER |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-05; 2019-02-20: 2020-09-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1001 | CONTROL VALVE DATASHEETS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFQ; 2019-08-06: IFP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-02-25; 2019-03-29: 2019-04-03; 2019-08-06: 2019-05-10
[6 empty] | Revised Plan | 2019-03-29: 2019-05-16; 2019-08-06: 2019-07-17
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01130
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I20-1003 | VENTURI TUBE DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-11; 2019-02-20: 2019-04-17; 2019-03-29: 2019-05-24
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1004 | ORIFICE PLATE DATASHEET |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-11; 2019-02-20: 2019-04-17; 2019-03-29: 2019-05-24
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1005 | INSTRUMENT LEVEL GAUGE DATASHEET |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01047
[6 empty] | Return Date | 2019-02-20: 2019-03-27
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I20-1006 | D/P LEVEL TRANSMITTERS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01288
[6 empty] | Return Date | 2019-02-20: 2019-05-13
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I20-1007 | DATA SHEET FOR PRESSURE GAUGES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-01; 2019-02-20: 2019-08-14; 2019-03-29: 2019-09-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1008 | DATA SHEET FOR DRAFT PRESSURE GAUGES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-01; 2019-02-20: 2019-08-14; 2019-03-29: 2019-09-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1009 | PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-01; 2019-02-20: 2019-08-14; 2019-03-29: 2019-09-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1010 | TEMPERATURE ELEMENTS FOR FURNACE PROFILE DATA SHEET |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01658
Return Date
Owner Cmmt*
| IE | OL1-2I20-1011 | TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01309
Return Date
Owner Cmmt*
| IE | OL1-2I20-1012 | TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01660
Return Date
Owner Cmmt*
| IE | OL1-2I20-1013 | TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1014 | TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1015 | INSTRUMENT PH AND CONDUCTIVITY ANALYZER DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01131
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I20-1016 | O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-09; 2019-02-20: 2019-06-22; 2019-03-29: 2019-08-05
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1022 | Instrument Datasheets for Flow Element -Orifice - Area 10 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01660
Return Date
Owner Cmmt*
| IE | OL1-2I20-1101 | Instrument Datasheets for Control Valve -Globe Type- Area 11 -BOP |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01581
Return Date
Owner Cmmt*
| IE | OL1-2I20-1106 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 11 -BOP |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01594
Return Date
Owner Cmmt*
| IE | OL1-2I20-1111 | Instrument Datasheets for ON-OFF Valve Ball Type - Area 11 BOP |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01594
Return Date
Owner Cmmt*
| IE | OL1-2I20-1112 | Instrument Datasheets for ON-OFF Valve Butterfly Type - Area 11 BOP |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01594
Return Date
Owner Cmmt*
| IE | OL1-2I20-1122 | Instrument Datasheets for Flow Element Orifice- Area 11 -BOP |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01615
Return Date
Owner Cmmt*
| IE | OL1-2I20-1127 | Instrument Datasheets for Flow Instrument -Vortex-Area 11 -BOP |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01594
Return Date
Owner Cmmt*
| IE | OL1-2I20-1201 | Instrument Datasheets for Control Valve - Globe Type Area 12 -BOP |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01594
Return Date
Owner Cmmt*
| IE | OL1-2I20-1206 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 12 - BOP |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01594
Return Date
Owner Cmmt*
| IE | OL1-2I20-1211 | Instrument Datasheets for ON-OFF Valve -Ball Type -Area 12 -BOP |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01615
Return Date
Owner Cmmt*
| IE | OL1-2I20-1212 | Instrument Datasheets for ON-OFF Valve -Butterfly Type - Area 12 -BOP |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01615
Return Date
Owner Cmmt*
| IE | OL1-2I20-1222 | Instrument Datasheets for Flow Element -Orifice- Area 12 -BOP |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01594
Return Date
Owner Cmmt*
| IE | OL1-2I20-1227 | Instrument Datasheets for Flow Instrument -Vortex - Area 12 - BOP |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01615
Return Date
Owner Cmmt*
| IE | OL1-2I20-1911 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 19 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01660
Return Date
Owner Cmmt*
| IE | OL1-2I20-2001 | CONTROL VALVE DATASHEETS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-02-25; 2019-02-20: 2019-04-03; 2019-03-29: 2019-05-10
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-03-29: 2019-07-17
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01650
Return Date
Owner Cmmt*
| IE | OL1-2I20-2002 | INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01625
Return Date
Owner Cmmt*
| IE | OL1-2I20-2003 | VENTURI TUBE DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-11; 2019-02-20: 2019-04-17; 2019-03-29: 2019-05-24
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2004 | ORIFICE PLATE DATASHEET |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-11; 2019-02-20: 2019-04-17; 2019-03-29: 2019-05-24
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2005 | INSTRUMENT LEVEL GAUGE DATASHEET |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2006 | D/P LEVEL TRANSMITTERS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01625
Return Date
Owner Cmmt*
| IE | OL1-2I20-2007 | DATA SHEET FOR PRESSURE GAUGES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2008 | DATA SHEET FOR DRAFT PRESSURE GAUGES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2009 | PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2011 | TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01625
Return Date
Owner Cmmt*
| IE | OL1-2I20-2012 | TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01625
Return Date
Owner Cmmt*
| IE | OL1-2I20-2013 | TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2014 | TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2015 | INSTRUMENT PH AND CONDUCTIVITY ANALYZER DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2016 | O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2022 | Instrument Datasheets for Flow Element - Orifice - Area 20 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01650
Return Date
Owner Cmmt*
| IE | OL1-2I20-2024 | Instrument Datasheets for Flow Element -Flow Nozzle -Area 20 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01650
Return Date
Owner Cmmt*
| IE | OL1-2I20-2026 | Instrument Datasheets for Flow Element -Wedge Type-Area 20 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01650
Return Date
Owner Cmmt*
| IE | OL1-2I20-2028 | Instrument Datasheets for Flow Element - Rotameter - Area 20 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01660
Return Date
Owner Cmmt*
| IE | OL1-2I20-2032 | Instrument Datasheets for Flow Element -Integral Orifice- Area 20 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01650
Return Date
Owner Cmmt*
| IE | OL1-2I20-2101 | D/S CEMS / O2 FLUE GAS (MULTICOMPONENTS ANALYZER) |  |  | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01660
Return Date
Owner Cmmt*
| IE | OL1-2I20-2102 | Instrument Datasheets for Control Valve - Butterfly Type- Area 21 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01660
Return Date
Owner Cmmt*
| IE | OL1-2I20-2106 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 21 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01625
Return Date
Owner Cmmt*
| IE | OL1-2I20-2111 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 21 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01625
Return Date
Owner Cmmt*
| IE | OL1-2I20-2112 | Instrument Datasheets for ON-OFF Valve - Butterfly Type -Area 21 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01650
Return Date
Owner Cmmt*
| IE | OL1-2I20-2122 | Instrument Datasheets for Flow Element -Orifice -Area 21 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01660
Return Date
Owner Cmmt*
| IE | OL1-2I20-2201 | D/S MECHANICAL O2 PROCESS ANALYSER |  |  | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01301
Return Date
Owner Cmmt*
| IE | OL1-2I20-2211 | Instrument Datasheets for On-Off Vales - Ball Type - Area 22 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01301
Return Date
Owner Cmmt*
| IE | OL1-2I20-2213 | Instrument Datasheets for Motor Operated Valve - MOV - Area 22 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01301
Return Date
Owner Cmmt*
| IE | OL1-2I20-2301 | D/S MECHANICAL MOISTURE ANALYSER |  |  | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01548
Return Date
Owner Cmmt*
| IE | OL1-2I20-2306 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 23 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01548
Return Date
Owner Cmmt*
| IE | OL1-2I20-2311 | Instrument Datasheets - ON-OFF Valve - Ball Type - Area 23 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01550
Return Date
Owner Cmmt*
| IE | OL1-2I20-2313 | Instrument Datasheets for Motor Operated Valve Area 23 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01550
Return Date
Owner Cmmt*
| IE | OL1-2I20-2322 | Instrument Datasheets for Flow Element -Orifice -Area 23 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01581
Return Date
Owner Cmmt*
| IE | OL1-2I20-2329 | Instrument Datasheets for Flow transmitter - Electromagnetic - Area 23 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01581
Return Date
Owner Cmmt*
| IE | OL1-2I20-2332 | Instrument Datasheets for Flow Element - Integral Orifice- Area 23 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01581
Return Date
Owner Cmmt*
| IE | OL1-2I20-2401 | D/S MECHANICAL PH / CONDUCTIVITY / TURBIDITY / SILICA / ORP / TSS / MLSS METER |  |  | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01550
Return Date
Owner Cmmt*
| IE | OL1-2I20-2402 | Instrument Datasheets for Control Valve - Butterfly Type - Area 24 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01550
Return Date
Owner Cmmt*
| IE | OL1-2I20-2411 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 24 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01581
Return Date
Owner Cmmt*
| IE | OL1-2I20-2412 | Instrument Datasheets for On-Off Valve - Butterfly Type - Area 24 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01548
Return Date
Owner Cmmt*
| IE | OL1-2I20-2413 | Instrument Datasheets for Motor Operated Valve - Area 24 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01550
Return Date
Owner Cmmt*
| IE | OL1-2I20-2422 | Instrument Datasheets for Flow Element -Orifice- Area 24 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01548
Return Date
Owner Cmmt*
| IE | OL1-2I20-2423 | Instrument Datasheets for Flow Element - Venturi - Area 24 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01428
Return Date
Owner Cmmt*
| IE | OL1-2I20-2425 | Instrument Datasheets for Flow Element -Pitot - Area 24 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01428
Return Date
Owner Cmmt*
| IE | OL1-2I20-2428 | Instrument Datasheets for Flow Element - Rotameter- Area 24 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01428
Return Date
Owner Cmmt*
| IE | OL1-2I20-2501 | Instrument Datasheets for Control Valve - Globe Type -Area 25 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01464
Return Date
Owner Cmmt*
| IE | OL1-2I20-2502 | Instrument Datasheets for Control Valve - Butterfly Type- Area 25 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01464
Return Date
Owner Cmmt*
| IE | OL1-2I20-2511 | Instrument Datasheets - ON-OFF Valve - Ball Type - Area 25 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01376
Return Date
Owner Cmmt*
| IE | OL1-2I20-2512 | Instrument Datasheets - ON-OFF Valve - Butterfly Type - Area 25 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01376
Return Date
Owner Cmmt*
| IE | OL1-2I20-2513 | Instrument Datasheets for Motor Operated Valve Area 25 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01660
Return Date
Owner Cmmt*
| IE | OL1-2I20-2522 | Instrument Datasheets for Flow Element - Orifice - Area 25 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01338
Return Date
Owner Cmmt*
| IE | OL1-2I20-2523 | Instrument Datasheets for Flow Element -Venturi - Area 25 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01388
Return Date
Owner Cmmt*
| IE | OL1-2I20-2528 | Instrument Datasheets for Flow Element - Rotameter - Area 25 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01338
Return Date
Owner Cmmt*
| IE | OL1-2I20-2601 | DATA SHEET FOR FIRE AND GAS DEVICES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-20; 2019-02-20: 2020-07-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2801 | D/S MECHANICAL CALORIMETER |  |  | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01464
Return Date
Owner Cmmt*
| IE | OL1-2I20-2802 | D/S MECHANICAL HC INFRARED ANALYSER |  |  | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01464
Return Date
Owner Cmmt*
| IE | OL1-2I20-2806 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 28 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01338
Return Date
Owner Cmmt*
| IE | OL1-2I20-2811 | Instrument Datasheets - ON-OFF Valve - Ball Type - Area 28 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01376
Return Date
Owner Cmmt*
| IE | OL1-2I20-2812 | Instrument Datasheets - ON-OFF Valve - Butterfly Type- Area 28 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01376
Return Date
Owner Cmmt*
| IE | OL1-2I20-2813 | Instrument Datasheets for Motor Operated Valve Area 28 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01464
Return Date
Owner Cmmt*
| IE | OL1-2I20-2822 | Instrument Datasheet for Flow Element -Orifice- Area 28 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01360
Return Date
Owner Cmmt*
| IE | OL1-2I20-2823 | Instrument Datasheets for Flow Element -Venturi- Area 28 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01360
Return Date
Owner Cmmt*
| IE | OL1-2I20-2830 | Instrument Datasheets for Flow Element - Coriolis - Area 28 |  | Class As-built | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01360
Return Date
Owner Cmmt*
| IE | OL1-2I20-3003 | VENTURI TUBE DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-11; 2019-02-20: 2019-04-17; 2019-03-29: 2019-05-24
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3004 | ORIFICE PLATE DATASHEET |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-11; 2019-02-20: 2019-04-17; 2019-03-29: 2019-05-24
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3006 | D/P LEVEL TRANSMITTERS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3007 | DATA SHEET FOR PRESSURE GAUGES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3008 | DATA SHEET FOR DRAFT PRESSURE GAUGES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3009 | PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3012 | TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3013 | TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3014 | TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3016 | O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4003 | VENTURI TUBE DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-11; 2019-02-20: 2019-04-17; 2019-03-29: 2019-05-24
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4004 | ORIFICE PLATE DATASHEET |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-11; 2019-02-20: 2019-04-17; 2019-03-29: 2019-05-24
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4006 | D/P LEVEL TRANSMITTERS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4007 | DATA SHEET FOR PRESSURE GAUGES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4008 | DATA SHEET FOR DRAFT PRESSURE GAUGES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4009 | PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4012 | TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4013 | TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4014 | TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4016 | O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5003 | VENTURI TUBE DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-11; 2019-02-20: 2019-04-17; 2019-03-29: 2019-05-24
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5004 | ORIFICE PLATE DATASHEET |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-11; 2019-02-20: 2019-04-17; 2019-03-29: 2019-05-24
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5006 | D/P LEVEL TRANSMITTERS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5007 | DATA SHEET FOR PRESSURE GAUGES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5008 | DATA SHEET FOR DRAFT PRESSURE GAUGES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5009 | PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5012 | TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5013 | TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5014 | TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5016 | O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6003 | VENTURI TUBE DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-11; 2019-02-20: 2019-04-17; 2019-03-29: 2019-05-24
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6004 | ORIFICE PLATE DATASHEET |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-11; 2019-02-20: 2019-04-17; 2019-03-29: 2019-05-24
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6006 | D/P LEVEL TRANSMITTERS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6007 | DATA SHEET FOR PRESSURE GAUGES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6008 | DATA SHEET FOR DRAFT PRESSURE GAUGES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6009 | PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6012 | TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6013 | TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6014 | TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6016 | O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-09-20; 2019-03-29: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I21 Instrument Calculation sheet |  |  |  |  | Class 2 | Purpose**
| IE | OL1-2I21-1001 | INTRINSIC SAFETY LOOP CALCULATION |  |  | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I30 Interlock Logic and Sequence Diagram
| IE | OL1-2I30-1001 | CAUSE AND EFFECT DIAGRAMS - AREA 10 |  | Class 3 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01043
Return Date
Owner Cmmt*
| IE | OL1-2I30-1002 | Instrument Interlock Descriptions - Area 10 - Feed Preparation and Feed Preheat |  | Class As-built | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01045
[6 empty] | Return Date | 2019-02-20: 2019-04-10
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I30-1101 | DCS INTERLOCK AND SEQUENCES DIAGRAMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-29; 2019-02-20: 2020-03-21; 2019-03-29: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-1102 | ESD INTERLOCK LOGIC DIAGRAMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-29; 2019-02-20: 2020-03-21; 2019-03-29: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2001 | CAUSE AND EFFECT DIAGRAMS - AREA 20 |  | Class 3 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01087
[6 empty] | Return Date | 2019-02-20: 2019-04-10
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I30-2002 | Instrument Interlock Descriptions Area 20 - Quench Oil |  | Class As-built | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01088
[6 empty] | Return Date | 2019-02-20: 2019-04-10
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I30-2203 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 22 |  | Class 3 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2303 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 23 |  | Class 3 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2603 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 26 |  | Class 3 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2703 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 27 |  | Class 3 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2803 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 28 |  | Class 3 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2903 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 29 |  | Class 3 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-3001 | CAUSE AND EFFECT DIAGRAMS - AREA 30 |  | Class 3 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-3003 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 30 |  | Class 3 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-5001 | CAUSE AND EFFECT DIAGRAMS - AREA 50 |  | Class 3 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-5003 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 50 |  | Class 3 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-5301 | CAUSE AND EFFECT DIAGRAMS - AREA 53 |  | Class 3 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01036
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I30-5302 | Instrument Interlock Descriptions - Area 53- Cooling Water System |  | Class As-built | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01037
[6 empty] | Return Date | 2019-02-20: 2019-03-29
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I30-5503 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 55 |  | Class 3 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-5603 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 56 |  | Class 3 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-5901 | Cause and Effect Diagram Area 59 - Supporting Utilities Auxiliaries |  | Class As-built | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01087
[6 empty] | Return Date | 2019-02-20: 2019-04-10
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I30-5902 | Instrument Interlock Descriptions Area 59 - Supporting Utilities Auxiliaries |  | Class As-built | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01088
[6 empty] | Return Date | 2019-02-20: 2019-04-10
Owner Cmmt* | bar: 2019-02-20
Category Code: I31 Typical installation / fabrication drawing
| IE | OL1-2I31-0001 | INSTR.SUPPORTS TYPICAL MOUNT.DETAILS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-12-31; 2019-02-20: 2019-12-31; 2019-03-29: 2020-05-25; 2019-08-06: 2020-09-29
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSL-LSPA1-T-IE-01058; 2019-02-20: TPSK-LPSA1-T-IE-01391
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I31-0200 | LEVEL INSTRUMENT DESIGN, ISBL UNITS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-06-15; 2019-03-29: 2019-12-15
[6 empty] | Revised Plan | 2019-02-20: 2019-07-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-0201 | LEVEL INSTRUMENT DESIGN, OSBL UNITS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-06-15; 2019-03-29: 2019-12-15
[6 empty] | Revised Plan | 2019-02-20: 2019-07-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-0203 | Level Instrument Design Quench ISBL |  | Class As-built | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-06-15; 2019-03-29: 2019-12-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-18
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01413
Return Date
Owner Cmmt*
| IE | OL1-2I31-1003 | FLOW TRANSMITTER - VENTURI STEAM LIQUID SERVICE - 900 AND ABOVE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1005 | PRESSURE TRANSMITTER - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1012 | PRESSURE GAUGE - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1019 | FLOW TRANSMITTER - LIQUID SERVICE 900 AND ABOVE W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1020 | PRESSURE TRANSMITTER - STEAM SVC 1500 W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1021 | LEVEL TRANSMITTER - STEAM LIQ 900 AND ABOVE W ELECT TRACE INSTALLATION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1022 | PRESSURE GAUGE - STEAM SRV 1500 REMOTE MTD W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2001 | O2 COMBUSTIBLE ANALYZER PROCESS CONNECTION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2002 | O2 COMBUSTIBLE ANALYZER INSTRUMENT ELECTRICAL CONNECTION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2003 | FLOW TRANSMITTER - VENTURI STEAM LIQUID SERVICE - 900 AND ABOVE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2004 | PRESSURE GAUGE - GAS SERVICE DRAFT REMOTE MOUNTING |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2005 | PRESSURE TRANSMITTER - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2006 | EYE-HYE LEVEL COMPONENTS ON STEAM DRUM ELECTRICAL CONNECTION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2007 | COT INSERTION WELL T-C CONNECTION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2008 | INSTRUMENT SUPPORT DETAIL EYE-HYE LEVEL CONTROL UNIT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2009 | INSTRUMENT PROCESS DETAILS DRAFT D-P TRANSMITTER GAS SERVICE REMOTE MOUNTED |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2010 | INSTRUMENT SUPPORT DETAILS DUAL STAND 4FT-4IN OUTSIDE HANDRAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2011 | INSTRUMENT SUPPORT DETAILS TRIPLE STAND 4FT-4IN OUTSIDE HANDRAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2012 | PRESSURE GAUGE - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2013 | THERMOCOUPLE HEAD ELECTRICAL CONNECTION DETAIL 3-4IN CONDUIT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2014 | TEMPERATURE TRANSMITTER ELECTRICAL CONNECTION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2015 | LUBE OIL VENDOR JUNCTION BOX TO FIE CHARM BOX ELECTRICAL CONNECTION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2016 | INSTRUMENT SUPPORT DETAIL EYE-HYE MINIATURE LEVEL INDICATOR |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2017 | PH CONDUCTIVITY ANALYZER SAMPLING SYTEM PROCESS CONNECTION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2018 | PH CONDUCTIVITY ANALYZER SAMPLING SYTEM PROCESS CONNECTION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2019 | FLOW TRANSMITTER - LIQUID SERVICE 900 AND ABOVE W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2020 | PRESSURE TRANSMITTER - STEAM SVC 1500 W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2021 | LEVEL TRANSMITTER - STEAM LIQ 900 AND ABOVE W ELECT TRACE INSTALLATION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2022 | PRESSURE GAUGE - STEAM SRV 1500 REMOTE MTD W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2023 | LEVEL GAUGE - STEAM SERVICE DIRECT MTD W ELECTRIC TRACED |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-19; 2019-02-20: 2020-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I32 Instrument installation key plan drawing
Category Code: I33 Instrument cable trays and support layout
Category Code: I34 Instrument main cable layout
| IE | OL1-2I34-0001 | INSTR.MAIN CABLE ROUTING COMMON AREA |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0002 | INSTR.MAIN CABLE ROUTING METERING |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0003 | INSTR.MAIN CABLE ROUTING MAIN PIPE RACK |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0004 | INSTR.MAIN CABLE ROUTING AREA SUBSTATION E & FAR E |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0005 | INSTR.MAIN CABLE ROUTING AREA SUBSTATION C & FAR C |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0006 | INSTR.MAIN CABLE ROUTING FURNACES UTILITY |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0007 | INSTR.MAIN CABLE ROUTING QUENCH |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0008 | INSTR.MAIN CABLE ROUTING PROCESS 20B |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0009 | INSTR.MAIN CABLE ROUTING PROCESS 20C |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0010 | INSTR.MAIN CABLE ROUTING PROCESS COLD COMPRESSORS |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0011 | INSTR.MAIN CABLE ROUTING PROCESS CGC |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0012 | INSTR.MAIN CABLE ROUTING BUTADIENE |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0013 | INSTR.MAIN CABLE ROUTING COOLING WATER UNIT |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0014 | INSTR.MAIN CABLE ROUTING UTILITIES |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0015 | INSTR.MAIN CABLE ROUTING WASTE WATER TREATMENT |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0016 | INSTR.MAIN CABLE ROUTING FLARE AREA |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0017 | INSTR.OVERALL CABLE ROUTING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-11; 2019-02-20: 2019-07-11; 2019-03-29: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I35 Instrument, Junction box and instrument air supply station plot plan drawing
| IE | OL1-2I35-0001 | INSTRUMENT LAYOUT COMMON AREA |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0002 | INSTRUMENT LAYOUT METERING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0003 | INSTRUMENT LAYOUT MAIN PIPE RACK |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0004 | INSTRUMENT LAYOUT AREA SUBSTATION E & FAR E |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0005 | INSTRUMENT LAYOUT AREA SUBSTATION E & FAR C |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0006 | INSTRUMENT LAYOUT FURNACES UTILITY |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0007 | INSTRUMENT LAYOUT QUENCH |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0008 | INSTRUMENT LAYOUT PROCESS 20B |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0009 | INSTRUMENT LAYOUT PROCESS 20C |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0010 | INSTRUMENT LAYOUT PROCESS COLD COMPRESSORS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0011 | INSTRUMENT LAYOUT PROCESS CGC |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0012 | INSTRUMENT LAYOUT BUTADIENE |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0013 | INSTRUMENT LAYOUT COOLING WATER UNIT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0014 | INSTRUMENT LAYOUT UTILITIES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0015 | INSTRUMENT LAYOUT WASTE WATER TREATMENT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0016 | INSTRUMENT LAYOUT FLARE AREA |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0020 | INSTRUMENT AIR DISTRIBUTION LAYOUT COMMON AREA |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0021 | INSTRUMENT AIR DISTRIBUTION LAYOUT METERING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0022 | INSTRUMENT AIR DISTRIBUTION LAYOUT MAIN PIPE RACK |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0023 | INSTRUMENT AIR DISTRIBUTION LAYOUT AREA SUBSTATION E & FAR E |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0024 | INSTRUMENT AIR DISTRIBUTION LAYOUT AREA SUBSTATION C & FAR C |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0025 | INSTRUMENT AIR DISTRIBUTION LAYOUT FURNACES UTILITY |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0026 | INSTRUMENT AIR DISTRIBUTION LAYOUT QUENCH |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0027 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS 20B |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0028 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS 20C |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0029 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS COLD COMPRESSORS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0030 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS CGC |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0031 | INSTRUMENT AIR DISTRIBUTION LAYOUT BUTADIENE |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0032 | INSTRUMENT AIR DISTRIBUTION LAYOUT COOLING WATER UNIT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0033 | INSTRUMENT AIR DISTRIBUTION LAYOUT UTILITIES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0034 | INSTRUMENT AIR DISTRIBUTION LAYOUT WASTE WATER TREATMENT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0035 | INSTRUMENT AIR DISTRIBUTION LAYOUT FLARE AREA |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I36 Local panel plot plan drawing
Category Code: I37 Local panel arrangement drawing
Category Code: I38 Layout of inst wiring (grounding)
Category Code: I39 Instrument air piping and tubing drawing
Category Code: I40 Instrument utilities tubing layout drawing
Category Code: I41 Instrument wiring connection list
Category Code: I42 Junction box Arrangement Drawing
| IE | OL1-2I42-0001 | INSTRUMENT AND F&G WIRING DRAWINGS FOR FAR-E SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-28; 2019-02-20: 2020-06-15; 2019-03-29: 2020-10-31; 2019-08-06: 2021-02-26
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-0002 | INSTRUMENT AND F&G WIRING DRAWINGS FOR FAR-C SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-28; 2019-02-20: 2020-06-15; 2019-03-29: 2020-10-31; 2019-08-06: 2021-02-26
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-0003 | INSTRUMENT AND F&G WIRING DRAWINGS FOR FAR FL SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-28; 2019-02-20: 2020-06-15; 2019-03-29: 2020-10-31; 2019-08-06: 2021-02-26
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-0004 | INSTRUMENT AND F&G WIRING DRAWINGS FOR CCB AND OTHER BUILDINGS SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-28; 2019-02-20: 2020-06-15; 2019-03-29: 2020-10-31; 2019-08-06: 2021-02-26
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT GRADE TO EL AAFT-AIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1100 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1100 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT GRADE TO EL AAFT-AIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1200 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1200 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT GRADE TO EL AAFT-AIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1300 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1300 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT GRADE TO EL AAFT-AIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1400 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1400 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT GRADE TO EL AAFT-AIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1500 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1500 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT GRADE TO EL AAFT-AIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1600 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1600 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-16; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I43 Instrument cable list and cable cutting plan
| IE | OL1-2I43-0001 | INSTRUMENT CABLE LIST FOR FAR C SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-08-15; 2019-03-29: 2020-11-15; 2019-08-06: 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0002 | INSTRUMENT CABLE LIST FOR FAR E SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-08-15; 2019-03-29: 2020-11-15; 2019-08-06: 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0003 | INSTRUMENT CABLE LIST FOR FAR FL SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-08-15; 2019-03-29: 2020-11-15; 2019-08-06: 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0004 | INSTRUMENT CABLE LIST FOR CCB AND OTHER BULDINGS SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-08-15; 2019-03-29: 2020-11-15; 2019-08-06: 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0011 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FOR FAR C SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-09-15; 2019-03-29: 2020-12-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0012 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FOR FAR E SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-09-15; 2019-03-29: 2020-12-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0013 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FOR FAR FL SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-09-15; 2019-03-29: 2020-12-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0014 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FORCCB AND OTHER BULDINGS SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-15; 2019-02-20: 2020-09-15; 2019-03-29: 2020-12-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I44 Power Supply Distribution Drawing
| IE | OL1-2I44-1001 | INST.POW.SUP.DISTRIBUTION FOR CCB |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-22; 2019-02-20: 2020-01-29; 2019-03-29: 2020-06-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I44-1002 | INST.POW.SUP.DISTRIBUTION FOR FAR C |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-22; 2019-02-20: 2020-01-29; 2019-03-29: 2020-06-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I44-1003 | INST.POW.SUP.DISTRIBUTION FOR FAR E |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-22; 2019-02-20: 2020-01-29; 2019-03-29: 2020-06-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I44-1004 | INST.POW.SUP.DISTRIBUTION FOR FAR FL |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-22; 2019-02-20: 2020-01-29; 2019-03-29: 2020-06-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I45 Control Room and Rack Room Drawings
Category Code: I46 Layout of instrument cabinets / panels in Control Room and Rack Room
| IE | OL1-2I46-1001 | CONTROL & TECH.ROOM LAYOUT, CENTRAL CONTROL BUILDING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-04-30; 2019-03-29: 2020-08-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I46-1002 | FAR C INSTRUMENT EQUIPMENT LAYOUT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-04-30; 2019-03-29: 2020-08-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01153
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I46-1003 | FAR E INSTRUMENT EQUIPMENT LAYOUT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-04-30; 2019-03-29: 2020-08-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01153
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I46-1004 | FAR FL INSTRUMENT EQUIPMENT LAYOUT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-04-30; 2019-03-29: 2020-08-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01153
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I46-1005 | MAINTENANCE BUILDING INSTRUMENT EQUIPMENT LAYOUT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-04-30; 2019-03-29: 2020-08-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I46-1006 | EMERGENCY CENTER BUILDING INSTRUMENT EQUIPMENT LAYOUT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-04-30; 2019-03-29: 2020-08-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I47 Layout of instrument main and secondary cable route in Control Room and Rack Room
| IE | OL1-2I47-1001 | FAR E INSTRUMENT CABLE ROUTING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-28; 2019-02-20: 2020-07-31; 2019-03-29: 2020-11-15; 2019-08-06: 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1002 | FAR C INSTRUMENT CABLE ROUTING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-28; 2019-02-20: 2020-07-31; 2019-03-29: 2020-11-15; 2019-08-06: 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1003 | FAR FL INSTRUMENT CABLE ROUTING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-28; 2019-02-20: 2020-07-31; 2019-03-29: 2020-11-15; 2019-08-06: 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1004 | INSTRUMENT CABLE ROUTING CENTRAL CONTROL BUILDING AND OTHER BUILDINGS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-28; 2019-02-20: 2020-07-31; 2019-03-29: 2020-11-15; 2019-08-06: 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1005 | CCB INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT PACKAGE A1 |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-15; 2019-02-20: 2020-07-15; 2019-03-29: 2020-12-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1006 | FAR E INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-15; 2019-02-20: 2020-07-15; 2019-03-29: 2020-12-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1007 | FAR C INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-15; 2019-02-20: 2020-07-15; 2019-03-29: 2020-12-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1008 | FAR FL INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-15; 2019-02-20: 2020-07-15; 2019-03-29: 2020-12-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1021 | TELECOM LOCATION AND CABLE ROUTING FAR E |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-31; 2019-02-20: 2020-02-28; 2019-03-29: 2020-08-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1022 | TELECOM LOCATION AND CABLE ROUTING FAR C |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-31; 2019-02-20: 2020-02-28; 2019-03-29: 2020-08-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1023 | TELECOM LOCATION AND CABLE ROUTING FAR FL |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-31; 2019-02-20: 2020-02-28; 2019-03-29: 2020-08-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1024 | TELECOM LOCATION AND CABLE ROUTING CENTRAL CONTROL BUILDING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-31; 2019-02-20: 2020-02-28; 2019-03-29: 2020-08-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1050 | SUB E INSTRUMENT CABLE ROUTING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-28; 2019-02-20: 2020-07-31; 2019-03-29: 2020-11-15; 2019-08-06: 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1051 | SUB C INSTRUMENT CABLE ROUTING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-28; 2019-02-20: 2020-07-31; 2019-03-29: 2020-11-15; 2019-08-06: 2021-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I48 Layout of instrument grounding wiring in Control Room and Rack Room
| IE | OL1-2I48-1001 | INSTRUMENT & TELECOM GROUNDING PHILOSOPHY DIAGRAM |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-02-14; 2019-02-20: 2019-03-14; 2019-03-29: 2019-04-14
[6 empty] | Revised Plan | 2019-02-20: 2019-06-06; 2019-03-29: 2019-07-05
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01013
Return Date
Owner Cmmt*
| IE | OL1-2I48-1002 | INSTRUMENT / TELECOM EARTHING LAYOUT CENTRAL CONTROL BUILDING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-31; 2019-02-20: 2020-05-30; 2019-03-29: 2020-09-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I48-1003 | INSTRUMENT / TELECOM EARTHING LAYOUT FAR E AND SUB E |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-31; 2019-02-20: 2020-05-30; 2019-03-29: 2020-09-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I48-1004 | INSTRUMENT / TELECOM EARTHING LAYOUT FAR C AND SUB C |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-31; 2019-02-20: 2020-05-30; 2019-03-29: 2020-09-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I48-1005 | INSTRUMENT / TELECOM EARTHING LAYOUT FAR FL |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-31; 2019-02-20: 2020-05-30; 2019-03-29: 2020-09-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I48-1006 | INSTRUMENT / TELECOM EARTHING LAYOUT OTHER BUILDINGS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-31; 2019-02-20: 2020-05-30; 2019-03-29: 2020-09-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I49 Instrument Hook-up Drawing
| IE | OL1-2I49-4101 | INSTRUMENT/TELECOM AND FIBRE OPTIC CABLES MATERIALTAKE-OFF |  |  | Purpose** | 2019-02-20: IF1T; 2019-02-20: IF2T; 2019-03-29: IF3T; 2019-08-06: IF4T
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-15; 2019-02-20: 2020-02-15; 2019-03-29: 2020-06-15; 2019-08-06: 2020-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4201 | CABLE TRAY & ACCESSORIES MAT.TAKE-OFF |  |  | Purpose** | 2019-02-20: IF1T; 2019-02-20: IF2T; 2019-03-29: IF3T; 2019-08-06: IF4T
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-30; 2019-02-20: 2020-08-30; 2019-03-29: 2020-11-30; 2019-08-06: 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4203 | SECONDARY CABLE TRAY & ACCESSORIES MAT.TAKE-OFF |  |  | Purpose** | 2019-02-20: IF1T; 2019-02-20: IF2T; 2019-03-29: IF3T; 2019-08-06: IF4T
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-30; 2019-02-20: 2020-08-30; 2019-03-29: 2020-11-30; 2019-08-06: 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4301 | JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES MATERIAL TAKE-OFF |  |  | Purpose** | 2019-02-20: IF1T; 2019-02-20: IF2T; 2019-03-29: IF3T; 2019-08-06: IF4T
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-24; 2019-02-20: 2020-06-01; 2019-03-29: 2020-08-15; 2019-08-06: 2020-10-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4303 | CABLE GLANDS MAT.TAKE-OFF |  |  | Purpose** | 2019-02-20: IF1T; 2019-02-20: IF2T
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-10-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4304 | MAIN CABLE TRANSIT (MCT) & ACCESSORIES MATERIAL TAKE OFF |  |  | Purpose** | 2019-02-20: IF1T; 2019-02-20: IF2T
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-10-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I50 Hook-up drawing for process lead piping for each instrument
| IE | OL1-2I50-0001 | INSTRUMENT HOOK-UP DRAWINGS ISBL UNITS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-31; 2019-02-20: 2020-05-25; 2019-03-29: 2020-09-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I51 Hook-up drawing for IA and pneumatic
| IE | OL1-2I51-0001 | INSTRUMENT TYPICAL HOOK -UP |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-12-31; 2019-02-20: 2020-05-25; 2019-03-29: 2020-09-29
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-04
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-1254
[6 empty] | Return Date | 2019-02-20: 2019-05-09
Owner Cmmt* | bar: 2019-02-20
Category Code: I52 Hook-up drawing for Steam tracing
| IE | OL1-2I52-0001 | INSTRUMENT HOOK-UP DRAWINGS OSBL UNITS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-31; 2019-02-20: 2020-05-25; 2019-03-29: 2020-09-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I53 Instrument loop drawing diagram
| IE | OL1-2I53-0001 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - FURNACES UTILITY |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-02-15; 2019-02-20: 2021-04-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0002 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - QUENCH |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-02-15; 2019-02-20: 2021-04-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0003 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS 20B |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-02-15; 2019-02-20: 2021-04-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0004 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS 20C |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-02-15; 2019-02-20: 2021-04-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0005 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS COLD COMPRESSORS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-02-15; 2019-02-20: 2021-04-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0006 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS CGC |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-02-15; 2019-02-20: 2021-04-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0007 | INSTRUMENT LOOP DRAWINGS FAR-E- METERING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-02-15; 2019-02-20: 2021-04-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0008 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - SUBSTATION E & FAR E |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-02-15; 2019-02-20: 2021-04-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0009 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - SUBSTATION C & FAR C |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-02-15; 2019-02-20: 2021-04-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0010 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - BUTADIENE |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-02-15; 2019-02-20: 2021-04-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0011 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - COOLING WATER UNIT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-02-15; 2019-02-20: 2021-04-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0012 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - UTILITIES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-02-15; 2019-02-20: 2021-04-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0013 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - WASTE WATER TREATMENT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-02-15; 2019-02-20: 2021-04-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0014 | INSTRUMENT LOOP DRAWINGS FAR-FL DCS, ESD, FGS - FLARE |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-02-15; 2019-02-20: 2021-04-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I54 Bill of bulk materials take-off
| IE | OL1-2I54-1001 | INSTRUMENT MTO 10-H-1100 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I54-2001 | INSTRUMENT MTO 10-H-1200 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I54-3001 | INSTRUMENT MTO 10-H-1300 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I54-4001 | INSTRUMENT MTO 10-H-1400 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I54-5001 | INSTRUMENT MTO 10-H-1500 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I54-6001 | INSTRUMENT MTO 10-H-1600 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I55 In-line & On equipment
| IE | OL1-2I55-0101 | MR ORIFICE AND RESTRICTION ORIFICE |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-04; 2019-02-20: 2019-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0102 | MR PITOT TUBE |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-04; 2019-02-20: 2019-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0103 | MR ELECTROMAGNETIC FLOW METER |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-04; 2019-02-20: 2019-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0104 | MR ROTAMETERS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-04; 2019-02-20: 2019-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0106 | MR MASS FLOW MET.CORIOLIS EFFECT |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-04; 2019-02-20: 2019-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0107 | MR VENTURI |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-04; 2019-02-20: 2019-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0108 | MR ULTRASONIC FLOW METER |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-04; 2019-02-20: 2019-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0111 | MR TURBINE METER |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-04; 2019-02-20: 2019-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0112 | MR VORTEX METER |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-04; 2019-02-20: 2019-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0120 | MR CUSTODY TRANSFER SYSTEM |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-26; 2019-02-20: 2019-11-30
[6 empty] | Revised Plan | 2019-02-20: 2019-07-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0202 | MR MAGNETIC LEVEL GAUGE |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-20; 2019-02-20: 2020-06-12
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0203 | MR RADAR LEVEL INSTRUMENTS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-20; 2019-02-20: 2020-06-12
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0211 | MR SPECIAL LEVEL TRANSMITTERS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-20; 2019-02-20: 2020-06-12
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0212 | MR LEVEL GLASS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-20; 2019-02-20: 2020-06-12
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0213 | MR LEVEL GLASS FOR STEAM DRUM |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-20; 2019-02-20: 2020-06-12
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0302 | MR THERMOCOUPLE/RTD WITH WELL |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-05; 2019-02-20: 2020-07-03
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0304 | MR THERMOMETER WITH WELL |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-05; 2019-02-20: 2020-07-03
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0305 | MR MULTIPLE THERMOCOUPLE / RTD |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-05; 2019-02-20: 2020-07-03
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0402 | MR PRESSURE & DIFFER.PRESS.GAUGE |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-05; 2019-02-20: 2020-08-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0501 | MR CONTROL VALVES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0503 | MR SPECIAL CONTROL VALVE |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0504 | MR SEVERE SERVICE CONTROL VALVE |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0505 | MR ANTISURGE VALVES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0506 | MR DESUPERHEATER VALVES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0606 | MR PNEUMATIC ON OFF VALVE |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0608 | MR SPECIAL ON OFF VALVES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0609 | MR ELECTRIC OPERATED VALVES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-11-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0610 | MR FOR PNEUMATIC ACTUATORS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-10-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0701 | MR SAFETY RELIEF VALVE & RUPTURE DISKS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-31; 2019-02-20: 2019-10-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0801 | MR ELECTRONIC TRANSMITTER |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-05; 2019-02-20: 2020-08-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-1001 | MR INTEGRATED CONTROL AND SAFETY SYSTEMS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-06; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-1701 | MR MACHINE MONITORING SYSTEM |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-21; 2019-02-20: 2020-06-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2001 | MR ANALYSER HOUSE PACKAGE |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-30; 2019-02-20: 2019-10-30
[6 empty] | Revised Plan | 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2002 | MR CEMS / O2 FLUE GAS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-06; 2019-02-20: 2019-10-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2004 | INLINE INSTRUMENT REQUISITION - VORTEX FLOW ELEMENT |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-25; 2019-02-20: 2019-07-01
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2201 | INLINE INSTRUMENT REQUISITION - CONTROL VALVES |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-25; 2019-02-20: 2019-07-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2202 | INLINE INSTRUMENT REQUISITION - PRESSURE & SAFETY RELIEF VAVLE |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-28; 2019-02-20: 2019-06-14
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2203 | INLINE INSTRUMENT REQUISITION - RESTRICTION ORIFICE |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-09; 2019-02-20: 2019-07-30
[6 empty] | Revised Plan | 2019-02-20: 2019-06-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2207 | OFFLINE INSTRUMENT REQUISITION - LEVEL TRANSMITTER |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-26; 2019-02-20: 2019-06-26
[6 empty] | Revised Plan | 2019-02-20: 2019-08-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2208 | OFFLINE INSTRUMENT REQUISITION - O2 & COMBUSTIBLE ANALYZER |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-23; 2019-02-20: 2019-08-26
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2209 | OFFLINE INSTRUMENT REQUISITION - PH/CONDUCTIVITY ANALYZER |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-27; 2019-02-20: 2019-12-03
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2210 | OFFLINE INSTRUMENT REQUISITION - PRESSURE & DIFF PRESSURE TRANSMITTER |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-23; 2019-02-20: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2211 | OFFLINE INSTRUMENT REQUISITION - PRESSURE GAUGES/DRAFT GAUGES |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-23; 2019-02-20: 2019-11-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2212 | OFFLINE INSTRUMENT REQUISITION - TEMPERATURE TRANSMITTER |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-27; 2019-02-20: 2019-12-03
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2213 | OFFLINE INSTRUMENT REQUISITION - THERMOCOUPLE FOR FURNACE PROFILE |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-27; 2019-02-20: 2019-12-03
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2214 | OFFLINE INSTRUMENT REQUISITION - THERMOCOUPLE TYPE K / RTD WITH WELL |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-27; 2019-02-20: 2019-12-03
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2215 | OFFLINE INSTRUMENT REQUISITION - THERMOCOUPLE WITH COT |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-27; 2019-02-20: 2019-12-03
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2301 | MR SIMPLE SPECIFIC COMPONENT AND PROPERTY ANALYZERS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-06; 2019-02-20: 2019-10-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2401 | MR WATER ANALYZERS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-30; 2019-02-20: 2020-02-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2601 | MR FIRE AND GAS DEVICES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-20; 2019-02-20: 2020-06-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4101 | MR INSTRUMENT / TELECOM AND FIBRE OPTIC CABLES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-04; 2019-02-20: 2020-11-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4201 | MR CABLE TRAY AND ACCESSORIES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-11; 2019-02-20: 2020-11-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4301 | MR FOR JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-01; 2019-02-20: 2020-12-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4302 | MR CABLE GLANDS |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-01; 2019-02-20: 2020-12-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4501 | MR MOUNTING ACCESSORIES (TUBING & FITTINGS) |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-11; 2019-02-20: 2020-11-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4502 | MR SUNSHADES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-01; 2019-02-20: 2020-12-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4503 | MOUNTING ACCESSORIES (TUBING & FITTINGS) MATERIALTAKE-OFF |  |  | Purpose** | 2019-02-20: IF1T; 2019-02-20: IF2T; 2019-03-29: IF3T; 2019-08-06: IF4T
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-30; 2019-02-20: 2020-06-15; 2019-03-29: 2020-09-15; 2019-08-06: 2020-11-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4505 | MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) TAKE-OFF |  |  | Purpose** | 2019-02-20: IF1T; 2019-02-20: IF2T; 2019-03-29: IF3T; 2019-08-06: IF4T
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-30; 2019-02-20: 2020-06-15; 2019-03-29: 2020-09-15; 2019-08-06: 2020-11-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4507 | STEAM & ELECTRICALTRACING MAT.TAKE-OFF |  |  | Purpose** | 2019-02-20: IF1T; 2019-02-20: IF2T
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-28; 2019-02-20: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4510 | MR MAIN CABLE TRANSIT (MCT) & ACCESSORIES |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-06-01; 2019-02-20: 2020-12-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4511 | MR FOR MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-11; 2019-02-20: 2020-11-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I61 SIL Study Document
| IE | OL1-2I61-1101 | SIS IMPLEMENTATION CALCULATION NOTES |  |  | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-30; 2019-02-20: 2020-03-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I61-1102 | GENERAL SIS SAFETY REQUIREMENTS SPECIFICATION |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-07-30; 2019-02-20: 2020-03-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00719; 2019-02-20: TPSK-LSPA1-T-IE-01392
[6 empty] | Return Date | 2019-02-20: 2019-03-05
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I61-1103 | PARTICULAR SIS SAFETY REQUIREMENTS SPECIFICATION |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-30; 2019-02-20: 2020-03-05
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I62 FAT Punch Lists
Category Code: I63 SAT Punch Lists
Category Code: I64 Operation and maintenance spare part for 2 years list
Category Code: I65 Initial Spare part list
Category Code: I66 Special tools book
Category Code: I70 Instruction Manual of Instrument
Category Code: I71 Control narative for complex loop
| IE | OL1-2I71-1001 | COMPLEX LOOP NARRATIVES - AREA 10 |  | Class 3 | Purpose** | 2019-02-20: IFI; 2019-02-20: IFR
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01128
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I71-1201 | COMPLEX CONTROL NARRATIVES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IBD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-03-19; 2019-03-29: 2019-03-19; 2019-08-06: 2019-10-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01289
Return Date
Owner Cmmt*
| IE | OL1-2I71-2001 | COMPLEX LOOP NARRATIVES - AREA 20 |  | Class 3 | Purpose** | 2019-02-20: IFI; 2019-02-20: IFR
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01132
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I71-2101 | COMPLEX LOOP NARRATIVES - AREA 21 |  | Class 3 | Purpose** | 2019-02-20: IFI; 2019-02-20: IFR
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01147
Return Date
Owner Cmmt*
| IE | OL1-2I71-2201 | COMPLEX LOOP NARRATIVES - AREA 22 |  | Class 3 | Purpose** | 2019-02-20: IFI; 2019-02-20: IFR
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01544
Return Date
Owner Cmmt*
| IE | OL1-2I71-2301 | COMPLEX LOOP NARRATIVES - AREA 23 |  | Class 3 | Purpose** | 2019-02-20: IFI; 2019-02-20: IFR
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01358
Return Date
Owner Cmmt*
| IE | OL1-2I71-2401 | COMPLEX LOOP NARRATIVES - AREA 24 |  | Class 3 | Purpose** | 2019-02-20: IFI; 2019-02-20: IFR
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01605
Return Date
Owner Cmmt*
| IE | OL1-2I71-2501 | COMPLEX LOOP NARRATIVES - AREA 25 |  | Class 3 | Purpose** | 2019-02-20: IFI; 2019-02-20: IFR
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01358
Return Date
Owner Cmmt*
| IE | OL1-2I71-2601 | COMPLEX LOOP NARRATIVES - AREA 26 |  | Class 3 | Purpose** | 2019-02-20: IFI; 2019-02-20: IFR
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01662
Return Date
Owner Cmmt*
| IE | OL1-2I71-2701 | COMPLEX LOOP NARRATIVES - AREA 27 |  | Class 3 | Purpose** | 2019-02-20: IFI; 2019-02-20: IFR
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01662
Return Date
Owner Cmmt*
| IE | OL1-2I71-2801 | COMPLEX LOOP NARRATIVES - AREA 28 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2901 | COMPLEX LOOP NARRATIVES - AREA 29 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-3001 | COMPLEX LOOP NARRATIVES - AREA 30 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-5001 | COMPLEX LOOP NARRATIVES - AREA 50 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-5101 | Complex Loop Narratives - Area 51 - BFW-Steam -Steam Condensate System |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01614
Return Date
Owner Cmmt*
| IE | OL1-2I71-5201 | Complex Loop Narratives Area 52 - Fuel System |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01632
Return Date
Owner Cmmt*
| IE | OL1-2I71-5301 | COMPLEX LOOP NARRATIVES - AREA 53 |  | Class 3 | Purpose** | 2019-02-20: IFI; 2019-02-20: IFR
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01037
Return Date
Owner Cmmt*
| IE | OL1-2I71-5501 | COMPLEX LOOP NARRATIVES - AREA 55 |  | Class 3 | Purpose** | 2019-02-20: IFI; 2019-02-20: IFR
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01564
Return Date
Owner Cmmt*
| IE | OL1-2I71-5601 | COMPLEX LOOP NARRATIVES - AREA 56 |  | Class 3 | Purpose** | 2019-02-20: IFI; 2019-02-20: IFR
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01544
Return Date
Owner Cmmt*
| IE | OL1-2I71-5901 | Complex Loop Narratives - Area 59 - Supporting Utilities Auxiliaries |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01140
Return Date
Owner Cmmt*
Category Code: I76 Appraisal Report for Consultancy Service |  |  |  |  | Class 2 | Purpose**
Category Code: I77 Appraisal Report for EPC Contractor Work | [5 empty] | Rev.
Category Code: I78 Appraisal Report for Vendor/Supplier | [5 empty] | Issue Plan
Category Code: I81 DCS System Document | [5 empty] | Revised Plan
| IE | OL1-2I81-1001 | CTRL & SAFETY SYST.CONNECTION DIAG. |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-24; 2019-02-20: 2019-05-21; 2019-03-29: 2019-10-04; 2019-08-06: 2019-10-04
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01012
Return Date
Owner Cmmt*
| IE | OL1-2I81-1002 | CTRL & SAFETY SYST.ARCHITECTURE |  |  | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-01-24 | 2019-01-24 | 2019-05-21 | 2019-10-04 | 2019-10-04
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-22; 2019-02-20: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00912; 2019-02-20: TPSK-LSPA1-T-IE-01551
[6 empty] | Return Date | 2019-02-20: 2019-03-08
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I81-1003 | ELECTRIC.INSTRUMENT INTERF. |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-28; 2019-02-20: 2019-12-13; 2019-03-29: 2020-06-01
[6 empty] | Revised Plan | 2019-02-20: 2019-09-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I81-1004 | GRAPHIC DISLAYS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-29; 2019-02-20: 2020-03-21; 2019-03-29: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I81-1005 | OPERATOR TREND DISPLAY DEFINITION |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-29; 2019-02-20: 2020-03-21; 2019-03-29: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I82 ESD system Document
Category Code: I83 FGS system Document
Category Code: I84 Analyzer system Document
| IE | OL1-2I84-2001 | ANALYZER SYST.BLOCK DIAGRAM |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-18; 2019-02-20: 2020-05-18; 2019-03-29: 2020-11-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I84-2002 | ANALYZER SHELTER LAYOUT |  |  | Purpose** | 2019-02-20: IBD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04
[6 empty] | Revised Plan | 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I84-2003 | ANALYZER SAMPLE LOOP ARRANGEMENT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-17; 2019-02-20: 2020-06-17; 2019-03-29: 2020-12-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I85 Custody meter Document
Category Code: I86 Tank gauging Document
Category Code: I87 Pelletizing system Document
Category Code: I90 Vendor documents of Instrument
Category Code: I91 Index/List
| IE | OL1-2I91-0001 | INSTRUMENT LIST |  |  | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-29
[6 empty] | Revised Plan | 2019-02-20: 2019-06-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0002 | INSTRUMENT LIST - SUBSTATION E & FAR E |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0003 | INSTRUMENT LIST - SUBSTATION C & FAR C |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0004 | INSTRUMENT LIST - FURNACES UTILITY |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0005 | INSTRUMENT LIST - QUENCH |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0006 | INSTRUMENT LIST - PROCESS 20B |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0007 | INSTRUMENT LIST - PROCESS 20C |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0008 | INSTRUMENT LIST - PROCESS COLD COMPRESSORS |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0009 | INSTRUMENT LIST - PROCESS CGC |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0010 | INSTRUMENT LIST - BUTADIENE |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0011 | INSTRUMENT LIST - COOLING WATER UNIT |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0012 | INSTRUMENT LIST - UTILITIES |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0013 | INSTRUMENT LIST - WASTE WATER TREATMENT |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0014 | INSTRUMENT LIST - FLARE |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0020 | INSTRUMENT CLASSES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-19; 2019-02-20: 2020-06-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0100 | INSTRUMENT CONTROL SYSTEMS EQUIPMENT LIST |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30; 2019-02-20: 2020-08-30; 2019-03-29: 2020-12-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0102 | ICSS DATA BASE |  |  | Purpose** | 2019-02-20: IBD; 2019-02-20: IDD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2020-01-29; 2019-03-29: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0103 | INSTRUMENT RANGE, ALARM & TRIP LIST |  |  | Purpose** | 2019-02-20: IDD; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-30; 2019-02-20: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0104 | INSTRUMENT LIST - METERING |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1001 | IN/OUT SUMMARY |  |  | Purpose** | 2019-02-20: IBD; 2019-02-20: IDD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2020-01-29; 2019-03-29: 2020-06-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1002 | INSTRUMENT INDEX |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IFD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-04; 2019-02-20: 2019-06-13; 2019-03-29: 2019-06-24; 2019-08-06: 2019-10-28
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1003 | FURNACE ANALYZER LIST |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-10; 2019-02-20: 2019-07-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1004 | CONTROLLER AND SPLIT-RANGE LIST OSBL |  |  | Purpose** | 2019-02-20: IDD; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-30; 2019-02-20: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1005 | CONTROLLER AND SPLIT-RANGE LIST ISBL |  |  | Purpose** | 2019-02-20: IDD; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-30; 2019-02-20: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-2000 | ANALYZER LIST |  |  | Purpose** | 2019-02-20: IBD; 2019-02-20: IDD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-30; 2019-02-20: 2020-02-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-2002 | INSTRUMENT INDEX |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IFD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-04; 2019-02-20: 2019-06-13; 2019-03-29: 2019-06-24; 2019-08-06: 2019-10-28
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-2003 | FURNACE ANALYZER LIST - FURNACES 10-H-1200 - 10-H-1500 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-10; 2019-02-20: 2019-07-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-3002 | INSTRUMENT INDEX |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IFD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-04; 2019-02-20: 2019-06-13; 2019-03-29: 2019-06-24; 2019-08-06: 2019-10-28
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-3003 | FURNACE ANALYZER LIST - FURNACES 10-H-1300 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-10; 2019-02-20: 2019-07-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-4002 | INSTRUMENT INDEX |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IFD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-04; 2019-02-20: 2019-06-13; 2019-03-29: 2019-06-24; 2019-08-06: 2019-10-28
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-4003 | FURNACE ANALYZER LIST - FURNACES 10-H-1400 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-10; 2019-02-20: 2019-07-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-5002 | INSTRUMENT INDEX |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IFD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-04; 2019-02-20: 2019-06-13; 2019-03-29: 2019-06-24; 2019-08-06: 2019-10-28
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-5003 | FURNACE ANALYZER LIST - FURNACES 10-H-1500 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-10; 2019-02-20: 2019-07-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-6002 | INSTRUMENT INDEX |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IFD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-04; 2019-02-20: 2019-06-13; 2019-03-29: 2019-06-24; 2019-08-06: 2019-10-28
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-6003 | FURNACE ANALYZER LIST - FURNACES 10-H-1600 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-10; 2019-02-20: 2019-07-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I92 Procedures & Standards
| IE | OL1-2I92-0050 | JSS FOR ANALYSER SYSTEMS & HOUSES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-04-02; 2019-02-20: 2019-09-06
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01332
[6 empty] | Return Date | 2019-02-20: 2019-05-09
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2I92-0051 | JSS MOUNTING ACCESSORIES (TUBING & FITTINGS) |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-01; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0052 | JSS CABLE TRAY AND ACCESSORIES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-01; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0053 | JSS FOR INSTRUMENT / TELECOM AND FIBRE OPTIC CABLES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-15
[6 empty] | Revised Plan | 2019-02-20: 2019-05-17; 2019-02-20: 2019-05-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0054 | JSS FOR JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-01; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0055 | JSS FOR CABLE GLANDS AND ACCESSORIES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-01; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0056 | JSS FOR SUNSHADES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-01; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0057 | JSS FOR CUSTODY TRANSFER SYSTEM |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-08
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-05-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0058 | JSS FOR MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-01; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0059 | JSS FOR MAIN CABLE TRANSIT & ACCESSORIES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-01; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0060 | JSS FOR FIRE AND GAS DEVICES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-17; 2019-02-20: 2020-01-16
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0100 | JSS FOR FLOW METER |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-15
[6 empty] | Revised Plan | 2019-02-20: 2019-05-17; 2019-02-20: 2019-05-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0101 | JSS DIFFERENTIAL PRESSURE FLOW ELEMENTS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-17; 2019-02-20: 2020-01-16
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0200 | JSS LEVEL INSTRUMENTS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-17; 2019-02-20: 2020-01-16
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0201 | JSS FOR SURGE PROTECTION DEVICES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-01; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0300 | JSS TEMPERATURE INSTRUMENTS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-17; 2019-02-20: 2020-01-16
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0301 | JSS FOR PRESSURE & DIFF.PRESSURE INSTRUMENTS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-17; 2019-02-20: 2020-01-16
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0404 | JSS ANTISURGE VALVES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-08
[6 empty] | Revised Plan | 2019-02-20: 2019-07-22; 2019-02-20: 2019-08-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0405 | JSS DESUPERHEATERS VALVES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-08
[6 empty] | Revised Plan | 2019-02-20: 2019-07-22; 2019-02-20: 2019-08-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0501 | JSS CONTROL VALVES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-08
[6 empty] | Revised Plan | 2019-02-20: 2019-08-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0503 | JSS SPECIAL CONTROL VALVE |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-08
[6 empty] | Revised Plan | 2019-02-20: 2019-07-22; 2019-02-20: 2019-08-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0504 | JSS SEVERE SERVICE CONTROL VALVE |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-08
[6 empty] | Revised Plan | 2019-02-20: 2019-07-22; 2019-02-20: 2019-08-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0602 | JSS FOR ELECTRIC OPERATED VALVES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-08
[6 empty] | Revised Plan | 2019-02-20: 2019-06-10; 2019-02-20: 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0603 | JSS FOR SPECIAL ON OFF VALVES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-08
[6 empty] | Revised Plan | 2019-02-20: 2019-06-10; 2019-02-20: 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0604 | JSS FOR ACTUATORS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-08
[6 empty] | Revised Plan | 2019-02-20: 2019-05-17; 2019-02-20: 2019-05-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0606 | JSS FOR PNEUMATIC ON OFF VALVES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-08
[6 empty] | Revised Plan | 2019-02-20: 2019-06-10; 2019-02-20: 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0701 | JSS FOR SAFETY RELIEF VALVE & RUPTURE DISKS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-11; 2019-02-20: 2019-05-11
[6 empty] | Revised Plan | 2019-02-20: 2019-06-10; 2019-02-20: 2019-06-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0801 | JSS ELECTRONIC TRANSMITER |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-17; 2019-02-20: 2020-01-16
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-1701 | JSS FOR MACHINE MONITORING SYST. |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-17; 2019-02-20: 2019-05-17
[6 empty] | Revised Plan | 2019-02-20: 2019-06-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I93 Policy , Guidelines & Memo
Category Code: I94 SPARE NUMBER
Category Code: I94 Forms & Templates
Category Code: I95 SPARE NUMBER
Category Code: I95 Progress/Status Reports
Category Code: I96 SPARE NUMBER
Category Code: I97 SPARE NUMBER
Category Code: I98 SPARE NUMBER
Category Code: I99 SPARE NUMBER
Category Code: J71 Appraisal Report for Consultancy Service
Category Code: J72 Appraisal Report for EPC Contractor Work
Category Code: J73 Appraisal Report for Vendor/Supplier
Category Code: J91 Index/List
Category Code: J92 Procedures & Standards
Category Code: J93 Policy , Guidelines & Memo
Category Code: J94 Forms & Templates
Category Code: J95 Progress/Status Reports
Category Code: K01 Design Basis Reports
Category Code: K02 Design Verification Reports
Category Code: K03 Master Plan Document
Category Code: K04 Cadastal Map
Category Code: K08 Material Take Off UG
Category Code: K11 Design calculation for pile (including pile driven design)
| CV | OL1-2K11-0001 | CALCULATION NOTES FOR PILES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-04-01
[6 empty] | Revised Plan | 2019-02-20: 2019-05-30
[6 empty] | Issue Actual | 2019-02-20: 2019-03-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
Category Code: K12 Design calculation for paving
| CV | OL1-2K12-0001 | CALCULATION NOTES FOR ROAD AND PAVING THICKNESS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-30; 2019-02-20: 2020-09-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K13 Design calculation for foundations
| CV | OL1-2K13-0001 | CALCULATION NOTE FOR FOUNDATION OF 10-H-1100 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0002 | CALCULATION NOTE FOR FOUNDATION OF 10-H-1200/1600 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0004 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5200 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0005 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5200 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00943
[6 empty] | Return Date | 2019-02-20: 2019-03-28
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0006 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5210 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0007 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2120 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0008 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2140 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0009 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2110 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0010 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5150 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0011 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2160 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00732
[6 empty] | Return Date | 2019-02-20: 2019-03-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0013 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2136 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0014 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2160 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0015 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2125A |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0016 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2136 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00992
[6 empty] | Return Date | 2019-02-20: 2019-03-28
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0017 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2165A/D |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0018 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2166 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01005
[6 empty] | Return Date | 2019-02-20: 2019-03-28
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0019 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2145 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0020 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2146 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0021 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2026 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0022 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2048 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00816
[6 empty] | Return Date | 2019-02-20: 2019-03-18
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0023 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5102A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0024 | CALCULATION NOTE FOR FOUNDATION PUMPS 10-P-2026A/B, 10-P-2126A/B, 10-P-2046A/B, 10-P-5140A/B, 10-P-2146A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0025 | CALCULATION NOTE FOR FOUNDATION OF 10-P-2105A/B AND 10-P-2006A/B/C |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0026 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2105A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0027 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2009A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0028 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2008A/B/C |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0029 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2026A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0030 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2028A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0031 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2136A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0033 | CALCULATION NOTE FOR FOUNDATION OF ANALYZER HOUSE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0034 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2440 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0035 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2450 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0037 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2330 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0038 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2410A/B/C |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0039 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2435 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0041 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2240 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0042 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2245 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0043 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2445 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0044 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2455 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00832
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0045 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2220 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0046 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2210 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0047 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2230 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0048 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2405 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0049 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2415 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0050 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2310 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00827
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0052 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2316 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00783
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0054 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2330 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00783
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0055 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2411 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0056 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-2910 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0058 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2230A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01372
Return Date
Owner Cmmt*
| CV | OL1-2K13-0059 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2412 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01333
[6 empty] | Return Date | 2019-02-20: 2019-05-09
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0060 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2413 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0061 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2432 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0062 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2445A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0063 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2446 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01372
Return Date
Owner Cmmt*
| CV | OL1-2K13-0065 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2450 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01348
[6 empty] | Return Date | 2019-02-20: 2019-04-23
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0066 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2470 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0067 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2206 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01207
Return Date
Owner Cmmt*
| CV | OL1-2K13-0068 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2210A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01372
Return Date
Owner Cmmt*
| CV | OL1-2K13-0069 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2220A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01372
Return Date
Owner Cmmt*
| CV | OL1-2K13-0070 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2240A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01372
Return Date
Owner Cmmt*
| CV | OL1-2K13-0071 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2305 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00827
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0072 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2630 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01005
[6 empty] | Return Date | 2019-02-20: 2019-03-28
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0073 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2326 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0074 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2320A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0075 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2310A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0076 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2306A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0077 | CALCULATION NOTE FOR FOUNDATION OF ANALYZER HOUSE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0078 | CALCULATION NOTE FOR FOUNDATION OF ANALYZER HOUSE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0079 | CALCULATION NOTE FOR FOUNDATION FOR PUMPS 10-P-5112A/B, 10-P-2714A/B, 10-P-2710A/B, 10-P-2720A/B, 10-P-2721A/B, 10-P-2910 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0080 | CALCULATION NOTE FOR FOUNDATION FOR PUMPS 10-P-2724A/B, 10-P-2726A/B, 10-P-2750A/B, 10-P-2760A/B/C, 10-P-2705A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0081 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5100A/B/C |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0082 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2900/2902/2906 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0083 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2920 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0084 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-1920 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0085 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2350 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0086 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5555 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0087 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2048A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0088 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2580 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0089 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2640 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01071
Return Date
Owner Cmmt*
| CV | OL1-2K13-0090 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2570 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0091 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2510, 10-D-2510 AND 10-E-2510 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0093 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2520 AND 10-D-2520 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00679
Return Date
Owner Cmmt*
| CV | OL1-2K13-0094 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2480A |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0096 | Calculation Note For Foundation Of 10-D-2420A-B |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0098 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2815 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00732
[6 empty] | Return Date | 2019-02-20: 2019-03-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0101 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2645 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00816
[6 empty] | Return Date | 2019-02-20: 2019-03-18
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0102 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2555 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0103 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2550 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0104 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5628, 10-PIT-5628, P-10-5628A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0105 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2575 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0106 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2880 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0107 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2870 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00679
Return Date
Owner Cmmt*
| CV | OL1-2K13-0108 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2860 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00732
[6 empty] | Return Date | 2019-02-20: 2019-03-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0109 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2865 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0110 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5632 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0111 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2587 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01207
Return Date
Owner Cmmt*
| CV | OL1-2K13-0113 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2305 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01372
Return Date
Owner Cmmt*
| CV | OL1-2K13-0114 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2575 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0115 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2576 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01005
[6 empty] | Return Date | 2019-02-20: 2019-03-28
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0116 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2645A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSL-LSPA1-T-CV-01059
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0117 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2502 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00679
Return Date
Owner Cmmt*
| CV | OL1-2K13-0118 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2515 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00992
[6 empty] | Return Date | 2019-02-20: 2019-03-28
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0119 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2546 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0120 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2548 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0121 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2545 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00762
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0122 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2805A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0123 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2807 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0124 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2809 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0125 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2857 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00816
[6 empty] | Return Date | 2019-02-20: 2019-03-18
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0126 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2858 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0127 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2856 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0128 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2855 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01126
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0129 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2853 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00878
[6 empty] | Return Date | 2019-02-20: 2019-03-11
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0130 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2852 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0132 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2582 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IFC
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-05-02; 2019-03-29: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12; 2019-02-20: 2019-02-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00843; 2019-02-20: TPSK-LSPA1-T-CV-00904
[6 empty] | Return Date | 2019-02-20: 2019-02-27; 2019-02-20: 2019-03-12
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| CV | OL1-2K13-0133 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2504 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00762
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0134 | CALCULATION NOTE FOR FOUNDATION OF PSA PACKAGE 10-PK-2560, 10-D-2560A/F, 10-D-2565 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0135 | CALCULATION NOTE FOR PUMPS 10-P-2570A/B, 10-P-2575A/B, 10-P-2586A/B, 10-P-2647, 10-P-2646A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0136 | CALCULATION NOTE FOR PUMPS 10-P-2802A/B, 10-P-2805A/B, 10-P-2815, 10-P-2855A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0137 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2930, 10-D-2930 AND 10-P-2930 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0138 | CALCULATION NOTE FOR FOUNDATION OF 10-R-2700A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0139 | CALCULATION NOTE FOR FOUNDATION OF 10-R-2760 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0140 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2620 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0141 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2666 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0142 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2665A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0143 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2660 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01469
Return Date
Owner Cmmt*
| CV | OL1-2K13-0144 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2710 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0145 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2720 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0146 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2660 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0147 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2630 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01372
Return Date
Owner Cmmt*
| CV | OL1-2K13-0148 | CALCULATION NOTE FOR FOUNDATION OF 10-R-2470A/B/C |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0149 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2610 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00832
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0150 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2600A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00832
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0151 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2460 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0152 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2440 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0153 | CALCULATION NOTE FOR FOUNDATION OF 10-D-1000 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01372
Return Date
Owner Cmmt*
| CV | OL1-2K13-0154 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2635 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01348
[6 empty] | Return Date | 2019-02-20: 2019-04-23
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0155 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2636 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01005
[6 empty] | Return Date | 2019-02-20: 2019-03-28
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0156 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2472 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0157 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2474 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01372
Return Date
Owner Cmmt*
| CV | OL1-2K13-0158 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2465 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01372
Return Date
Owner Cmmt*
| CV | OL1-2K13-0159 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2460 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01372
Return Date
Owner Cmmt*
| CV | OL1-2K13-0160 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2440/2441/2442 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01333
[6 empty] | Return Date | 2019-02-20: 2019-05-09
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0161 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1020 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01207
Return Date
Owner Cmmt*
| CV | OL1-2K13-0162 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1015 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0163 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1001A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0164 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1000 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01348
[6 empty] | Return Date | 2019-02-20: 2019-04-23
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0165 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1005 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01348
[6 empty] | Return Date | 2019-02-20: 2019-04-23
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0166 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2912 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0167 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2922 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0168 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2940 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0169 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2705 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01521
Return Date
Owner Cmmt*
| CV | OL1-2K13-0170 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2706 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0171 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2735 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-18
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01415
Return Date
Owner Cmmt*
| CV | OL1-2K13-0172 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2724 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0173 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2730 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0175 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2755 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0176 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2725A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0177 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2726 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0179 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2702 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0180 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2701 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01456
Return Date
Owner Cmmt*
| CV | OL1-2K13-0181 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2706 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0182 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2008A/B/C |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0185 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2720 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0186 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2724 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0187 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2714 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0188 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2882 AND 10-D-2882 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01207
Return Date
Owner Cmmt*
| CV | OL1-2K13-0190 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2715A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0191 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2100A/B/C/D/E/F |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0192 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2705 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01521
Return Date
Owner Cmmt*
| CV | OL1-2K13-0193 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-2320 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0194 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1050 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01207
Return Date
Owner Cmmt*
| CV | OL1-2K13-0195 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-1910 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01469
Return Date
Owner Cmmt*
| CV | OL1-2K13-0196 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5910 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0197 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5914 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0198 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5912 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0199 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2914 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0200 | CALCULATION NOTE FOR FOUNDATION OF IGNITION SYSTEM |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0201 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION FOR 10-C-3070 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0202 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-3900 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0203 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3000 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0204 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3040 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0205 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3020 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0206 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3010 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0207 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3030 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0208 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3050 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0209 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3060 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0210 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3080 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0211 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3090 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0212 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3070 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0213 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3100, 10-A-3100 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0214 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3126 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0215 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3908 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0216 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3902 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0217 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3904 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0218 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3906 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0219 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3180 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0220 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3110 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0221 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3004A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0222 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3014A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0223 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3015 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0224 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3084 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0225 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3085A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0226 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3095 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0227 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3096 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0228 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3098 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0229 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3055A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0230 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3045A/B/C/D |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0231 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3044 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0232 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2585 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01207
Return Date
Owner Cmmt*
| CV | OL1-2K13-0233 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3150 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0234 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3160 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0235 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3005 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0236 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3070 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0237 | CALCULATION FOR FOUNDATION OF METERING STATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0238 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2765 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01521
Return Date
Owner Cmmt*
| CV | OL1-2K13-0239 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5560 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0240 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5560 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0241 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5394 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0242 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5398 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0243 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5355 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0244 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5392 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0245 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5390 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0246 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5396 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0247 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5550 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0248 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5500 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0249 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5510 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01647
Return Date
Owner Cmmt*
| CV | OL1-2K13-0250 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5513 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01647
Return Date
Owner Cmmt*
| CV | OL1-2K13-0251 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5515 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01647
Return Date
Owner Cmmt*
| CV | OL1-2K13-0252 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5520 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01647
Return Date
Owner Cmmt*
| CV | OL1-2K13-0253 | CALCULATION NOTE FOR FOUNDATION OF 10-C-5520A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0254 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5510 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0255 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5513 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0256 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5640 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0257 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5675A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0258 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5676 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0259 | CALCULATION NOTE FOR FOUNDATION OF 10-TX/C-2550 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0260 | CALCULATION NOTE FOR FOUNDATION OF 10-C-5650A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0261 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-C-2800, 10-E-2800 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0262 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-C-2850, 10-E-2850 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0263 | CALCULATION NOTE FOR FOUNDATION OF 10-C-2200, 10-E-2200 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0264 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5627, 10-PIT-5627, P-10-5627A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0265 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5397 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0266 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5692 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0267 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5693 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0268 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5694 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0269 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5671 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0270 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5672 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0271 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5697 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0272 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5690 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0273 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5691 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0274 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5670 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0275 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5670A/B, 10-P-5671A/B, 10-P-5644A/B, 10-P-5645A/B, 10-P-5646A/B, 10-P-5647A/B, 10-P-5675 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0276 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5646 AND 10-X-5646 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0277 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5644 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0278 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5644 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0279 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5653 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0280 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5650 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0281 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5110 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0282 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5120 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0283 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5130 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0284 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5552 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0285 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5565 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0286 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-1950, 10-C-1950A/B, 10-E-1951A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0287 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5140 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00679
Return Date
Owner Cmmt*
| CV | OL1-2K13-0288 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5400 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01521
Return Date
Owner Cmmt*
| CV | OL1-2K13-0289 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5114 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01456
Return Date
Owner Cmmt*
| CV | OL1-2K13-0290 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5112, 10-E-5112 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01456
Return Date
Owner Cmmt*
| CV | OL1-2K13-0291 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5520 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0292 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5113 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0294 | CALCULATION NOTE FOR FOUNDATION OF 10-F-5610 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0295 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5552 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0296 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5110 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0297 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5191 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0298 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5192 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0299 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5115, 10-F-5115A/B/C |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0300 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5125, 10-D-5125A/B, 10-F-5125A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0301 | CALCULATION NOTE FOR FOUNDATION OF 10-P-2106A/B/C |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0302 | CALCULATION NOTE FOR SKID 10-P-2201A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0303 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5360A/B/C |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0304 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5670 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0305 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5695 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0306 | CALCULATION NOTE FOR PUMPS 10-P-5900A/B, 10-P-5950A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0307 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5350 A/B/C/D/E/F/G/H |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0308 | CALCULATION NOTE FOR PUMPS 10-P-3080A/B, 10-P-3030A/B, 10-P-3000A/B, 10-P-3020A/B, 10-P-3061A/B, 10-P-3060A/B, 10-P-3062A/B, 10- |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0309 | CALCULATION NOTE FOR PUMPS 10-P-3096A/B, 10-P-3086A/B, 10-P-3036A/B, 10-P-3016A/B, 10-P-3900, 10-P-3160A/B, 10-P-3076A/B, 10-P-3 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0310 | CALCULATION NOTE FOR PUMPS 10-P-3046A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0311 | CALCULATION NOTE FOR PUMPS 10-P-3045A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0312 | CALCULATION NOTE FOR PUMPS 10-P-3026A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0313 | CALCULATION NOTE FOR PUMPS 10-P-3056A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0314 | CALCULATION NOTE FOR FOUNDATION OF 10-R-2620A |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01372
Return Date
Owner Cmmt*
| CV | OL1-2K13-0315 | CALCULATION NOTE FOR FOUNDATION PUMPS FOR 10-P-2450A/B, 10-P-2455A/B, 10-P-2620A/B, 10-P-2666A/B, 10-P-2660A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0316 | CALCULATION NOTE FOR FOUNDATION PUMPS FOR 10-P-2630A/B, 10-P-2310A/B, 10-P-2316A/B, 10-P-2326A/B, 10-P-2320A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0317 | CALCULATION NOTE FOR PUMPS 10-P-2302A/B, 10-P-2415A/B, 10-P-2445A/B, 10-P-2304, 10-P-2306A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0318 | CALCULATION NOTE FOR PUMPS 10-P-2200A/B, 10-P-2220A/B, 10-P-2210A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0319 | CALCULATION NOTE FOR PUMPS 10-P-5620A/B/C,10-P-5621,10-P-5650A/B, 10-P-5651A/B, 10-P-5640A/B, 10-P-5641 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0320 | CALCULATION NOTE FOR PUMPS 10-P-5550A/B, 10-P-5552 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0321 | CALCULATION NOTE FOR PUMPS 10-P-5110A/B, 10-P-5120A/B, 10-P-5130A/B, 10-P-5500A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0322 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2000 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0323 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2020 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0324 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2100 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IFC
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-05-02; 2019-03-29: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-21; 2019-02-20: 2019-03-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00904; 2019-02-20: TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | 2019-02-20: 2019-03-12; 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| CV | OL1-2K13-0325 | CALCULATION NOTE FOR CONCRETE STRUCTURE OF 10-T-2040 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0326 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5605 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0327 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5610 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0328 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2390 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0329 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5603 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0330 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5604 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0331 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2090 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01303
[6 empty] | Return Date | 2019-02-20: 2019-05-09
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0332 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2190 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0333 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2790 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0335 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-3190 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0336 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5601 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0337 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5600 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0338 | CALCULATION OF BASIN FOR COOLING TOWER 10-PIT-5350 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-12; 2019-02-20: 2020-01-02; 2019-03-29: 2020-01-23; 2019-08-06: 2020-03-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0339 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5370 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0340 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5602 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0341 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2392 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0342 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5658 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0343 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5615 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0344 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5656 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0345 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5620A/B/C |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0346 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5630 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0347 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5633 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0348 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5631 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0349 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5671 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0350 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5650A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0351 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5655 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0352 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5696 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0353 | CALCULATION NOTE FOR FOUNDATION OF CLARIFIER 10-TK-5651A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0356 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0357 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0358 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0359 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0360 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0361 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0362 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0363 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0364 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0365 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0366 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-5900 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0367 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-5950 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0368 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-2320 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0369 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-2910 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0370 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-3900 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0371 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-PK-1910 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0372 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS FLARE UNIT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0373 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0374 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0375 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0376 | CALCULATION FOR FOUNDATION OF SUPPORTS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0377 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0378 | CALCULATION NOTE FOR 10-SLW-5T02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0379 | CALCULATION NOTE FOR 10-SLW-5T01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0380 | CALCULATION NOTE FOR 10-SLW-0C01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0381 | CALCULATION NOTE FOR 10-SLW-5W01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0382 | CALCULATION NOTE FOR 10-SLW-5F01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0383 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0384 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0385 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0386 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0387 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0388 | CALCULATION FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0389 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0391 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0393 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5900 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01647
Return Date
Owner Cmmt*
| CV | OL1-2K13-0394 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5950 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0396 | CALCULATION NOTE FOR SKID 10-P-2801A/B |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0398 | CALCULATION FOR BASIN 10-PIT-5642 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-30; 2019-02-20: 2020-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0399 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2904 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0401 | Calculation Note For Foundation Of 10-E-2441 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01333
[6 empty] | Return Date | 2019-02-20: 2019-05-09
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K13-0402 | Calculation Note For Foundation Of 10-E-2442 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01372
Return Date
Owner Cmmt*
| CV | OL1-2K13-0403 | Calculation Note For Foundation Of 10-E-2405 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0404 | Calculation Note For Foundation Of 10-D-1912 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01469
Return Date
Owner Cmmt*
Category Code: K14 Design calculation for concrete structure (including reinforcement detail)
| CV | OL1-2K14-0001 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-0P01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0002 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-0P01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0003 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-0P02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0004 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-0P02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0005 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-3A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0006 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-3A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0007 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-5U01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0008 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-5U01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0009 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2D01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0010 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-2D01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0011 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2E01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0012 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-2E01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0013 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0014 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-2A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0015 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0016 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-2B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0017 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2C01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0018 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-2C01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0019 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-5T01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0020 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-0P03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0021 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-5F01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0022 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-5F01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0023 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2E01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0024 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0025 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0026 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0027 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0028 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A06 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0029 | CALCULATION NOTE FOR FOUNDATION AND ELEVATIONOF 10-STR-3A03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0030 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A05 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0031 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0032 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0033 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0034 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-3A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0035 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-5T01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0036 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-5T02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0037 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-5U01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0038 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0039 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E02, 10-D-2420A/B AND 10-E-2430 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0040 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0041 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0042 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D05 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0043 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-0P01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0044 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0045 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2A02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0046 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2A03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0047 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0048 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0049 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0050 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0051 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B05 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0052 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B06 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0053 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2D01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0054 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2D02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0055 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0056 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0057 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0058 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0059 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C05 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0060 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0061 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-1B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0062 | CALCULATION NOTE FOR FOUNDATION OF WASTE STORAGE BUILDING |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0063 | CALCULATION NOTE FOR FOUNDATION OF LUBRIFICATION OIL & GREASE STORAGE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0064 | CALCULATION NOTE FOR FOUNDATION OF GAS CYLINDER STORAGE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0065 | CALCULATION NOTE FOR FOUNDATION OF TOOL ROOM OPERATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0066 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-0P03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0067 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2B02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0068 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-2B02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0070 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-5T03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0071 | CALCULATION NOTE FOR FOUNDATION OF STORAGE SHELTER FOR CHENICALS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-04-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0073 | CALCULATION NOTE FOR FOUNDATION OF 10-STR-1B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-08; 2019-02-20: 2019-11-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K15 Design calculation for steel structure (including connection joint) |  |  |  |  | Class 2 | Purpose**
| CV | OL1-2K15-0001 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-0P01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-15; 2019-02-20: 2020-04-15; 2019-03-29: 2020-05-16; 2019-08-06: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0002 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-0P02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-15; 2019-02-20: 2020-04-15; 2019-03-29: 2020-05-16; 2019-08-06: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0003 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-3A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-15; 2019-02-20: 2020-04-15; 2019-03-29: 2020-05-16; 2019-08-06: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0004 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-5U01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-15; 2019-02-20: 2020-04-15; 2019-03-29: 2020-05-16; 2019-08-06: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0005 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2D01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-15; 2019-02-20: 2020-04-15; 2019-03-29: 2020-05-16; 2019-08-06: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0006 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2E01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-15; 2019-02-20: 2020-04-15; 2019-03-29: 2020-05-16; 2019-08-06: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0007 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-15; 2019-02-20: 2020-04-15; 2019-03-29: 2020-05-16; 2019-08-06: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0008 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-15; 2019-02-20: 2020-04-15; 2019-03-29: 2020-05-16; 2019-08-06: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0009 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2C01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-15; 2019-02-20: 2020-04-15; 2019-03-29: 2020-05-16; 2019-08-06: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0010 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-5T01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-15; 2019-02-20: 2020-04-15; 2019-03-29: 2020-05-16; 2019-08-06: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0011 | CALCULATION NOTES FOR STEEL 10-PRK-5F01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-15; 2019-02-20: 2020-04-15; 2019-03-29: 2020-05-16; 2019-08-06: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0012 | CALCULATION NOTE FOR STEEL OF 10-SHT-2E01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0013 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0014 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0015 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0016 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0017 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D05 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0018 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0019 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0020 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0021 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0022 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B05 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0023 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B06 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0024 | CALCULATION NOTE FOR STEEL STRUCTURE 10-SHT-2D01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0025 | CALCULATION NOTE FOR STEEL STRUCTURE 10-SHT-2D02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0026 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0027 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0028 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0029 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0030 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C05 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0032 | CALCULATION NOTE FOR STEEL STRUCTURE 10-SHT-1B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0033 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-0P01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0034 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0035 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2A02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0036 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2A03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0037 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0038 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0039 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0040 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0041 | CALCULATION NOTE FOR STEEL FOR WASTE STORAGE BUILDING |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0042 | CALCULATION NOTE FOR STEEL FOR LUBRIFICATION OIL & GREASE STORAGE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0043 | CALCULATION NOTE FOR STEEL FOR GAS CYLINDER STORAGE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0044 | CALCULATION NOTE FOR STEEL FOR TOOL ROOM OPERATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0045 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-0P03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-15; 2019-02-20: 2020-04-15; 2019-03-29: 2020-05-16; 2019-08-06: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0046 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A06 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0047 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0048 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A05 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0049 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0050 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0051 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0052 | CALCULATION FOR STEEL STRUCTURE 10-SHT-3A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0053 | CALCULATION FOR STEEL STRUCTURE 10-SHT-5T01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0054 | CALCULATION FOR STEEL STRUCTURE 10-SHT-5T02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0055 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-5U01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0056 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2B02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-15; 2019-02-20: 2020-04-15; 2019-03-29: 2020-05-16; 2019-08-06: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0058 | CALCULATION NOTE FOR STEEL FOR STORAGE SHELTER FOR CHENICALS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0059 | CALCULATION FOR STEEL STRUCTURE 10-SHT-5T03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-13; 2019-02-20: 2020-05-14; 2019-03-29: 2020-07-21; 2019-08-06: 2020-09-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0060 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-1B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-06; 2019-02-20: 2019-11-06; 2019-03-29: 2020-06-09; 2019-08-06: 2020-07-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K16 Design calculation for all drainage systems (including roof gutter, down spout, and grating cover)
| CV | OL1-2K16-0001 | UNDERGROUND CALCULATION NOTES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-06-18; 2019-02-20: 2019-12-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01239
Return Date
Owner Cmmt*
Category Code: K17 Design calculation for all blast material i.e. door,wall
Category Code: K20 Standard drawing for civil work
| CV | OL1-2K20-0001 | CONSTR.STDS.FOR CONCRETE WORKS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-25; 2019-02-20: 2019-01-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-25; 2019-02-20: 2019-03-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00088; 2019-02-20: TPSK-LSPA1-T-CV-00997
[6 empty] | Return Date | 2019-02-20: 2018-11-02; 2019-02-20: 2019-03-28
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
Category Code: K21 Standard drawing for steel structure work
| CV | OL1-2K21-0001 | CONSTR.STD.STEEL STRUCTURES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-25; 2019-02-20: 2019-01-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-25; 2019-02-20: 2019-03-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00088; 2019-02-20: TPSK-LSPA1-T-CV-00996
[6 empty] | Return Date | 2019-02-20: 2018-11-02; 2019-02-20: 2019-03-31
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
Category Code: K22 Standard drawing for architecture work
Category Code: K23 Land Developmemt Drawing
| CV | OL1-2K23-0001 | Standard Construction Drawings For Underground Systems |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00088
[6 empty] | Return Date | 2019-02-20: 2018-11-02
Owner Cmmt* | bar: 2019-02-20
Category Code: K25 Plant Layouts
| CV | OL1-2K25-0001 | KEY PLAN FOR INSTALLATION DWGS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-08-01; 2019-02-20: 2019-10-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01271
Return Date
Owner Cmmt*
| CV | OL1-2K25-0002 | KEY PLAN FOR STRUCTURES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-05-06; 2019-02-20: 2019-08-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01171
Return Date
Owner Cmmt*
Category Code: K26 Underground communication Layouts
Category Code: K27 Road and Drainage Layouts
| CV | OL1-2K27-0001 | ROADS, PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-09-29
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01074
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K27-0002 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-09-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0003 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-09-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0004 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-09-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0005 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-09-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0006 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-09-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0007 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-09-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0008 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-09-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0009 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-09-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0010 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-09-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0011 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-07-10; 2019-02-20: 2020-09-01; 2019-03-29: 2020-10-01; 2019-08-06: 2020-10-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0012 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-09-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0013 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-09-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K28 Fireproofing Plan
Category Code: K30 General Arrangement for Architectural drawings of Buildings
| CV | OL1-2K30-0001 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - ARCHITECTURAL CONSTR. DWGS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-29; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0002 | Electrical SUB-E And FAR-1 - Architectural Ground Floor Plan |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01122
Return Date
Owner Cmmt*
| CV | OL1-2K30-0003 | Electrical SUB-E And FAR-1 - Architectural First Floor Plan |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01122
Return Date
Owner Cmmt*
| CV | OL1-2K30-0004 | Electrical SUB-E And FAR-1 - Architectural First Floor Plan |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01122
Return Date
Owner Cmmt*
| CV | OL1-2K30-0005 | Electrical SUB-E And FAR-1 - Architectural Sections |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01122
Return Date
Owner Cmmt*
| CV | OL1-2K30-0006 | Electrical SUB-E And FAR-1 - Architectural Section D And Elevation 1 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01122
Return Date
Owner Cmmt*
| CV | OL1-2K30-0007 | Electrical SUB-E And FAR-1 - Architectural Elevations |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01122
Return Date
Owner Cmmt*
| CV | OL1-2K30-0010 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - PLUMBING DWGS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-29; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0015 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - ARCHITECTURAL CONSTR. DWGS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-03-29; 2019-02-20: 2020-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01122
Return Date
Owner Cmmt*
| CV | OL1-2K30-0016 | Electrical SUB-C And FAR-2 - Architectural First Floor Plan |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01122
Return Date
Owner Cmmt*
| CV | OL1-2K30-0017 | Electrical SUB-C And FAR-2 - Architectural Roof Floor Plan |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01122
Return Date
Owner Cmmt*
| CV | OL1-2K30-0018 | Electrical SUB-C And FAR-2 - Architectural Sections |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01122
Return Date
Owner Cmmt*
| CV | OL1-2K30-0019 | Electrical SUB-C And FAR-2 - Architectural Elevations |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01122
Return Date
Owner Cmmt*
| CV | OL1-2K30-0025 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - PLUMBING DWGS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-29; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0030 | GATEHOUSE - ARCHITECTURAL CONSTR. DWGS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-11-28; 2019-02-20: 2020-01-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSL-LSPA1-T-CV-01064
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K30-0031 | Gatehouse A - Architectural Elevations And Sections |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSL-LSPA1-T-CV-01064
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K30-0032 | Gatehouse A - Architectural Isometric Views |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSL-LSPA1-T-CV-01064
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K30-0035 | GATEHOUSE - PLUMBING |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-28; 2019-02-20: 2020-01-28
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0038 | Gatehouse A - Architectural Plans Elevations Sections And Schedules |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSL-LSPA1-T-CV-01064
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K30-0040 | OPERATION TOOL ROOM - ARCHITECTURAL CONSTR. DWGS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-12-16; 2019-02-20: 2020-02-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSL-LSPA1-T-CV-01064
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K30-0041 | Operation Tool Room - Architectural Elevations And Sections |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSL-LSPA1-T-CV-01064
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K30-0042 | Operation Tool Room - Architectural Isometric Views |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSL-LSPA1-T-CV-01064
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K30-0045 | OPERATION TOOL ROOM - PLUMBING |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-16; 2019-02-20: 2020-02-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0050 | Electrical SUB-F And FAR-F - Architectural Plans And Schedules |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01122
Return Date
Owner Cmmt*
| CV | OL1-2K30-0051 | Electrical SUB-F And FAR-F - Architectural Sections And Elevations |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01122
Return Date
Owner Cmmt*
Category Code: K31 General Arrangement for Civil Concrete Works drawings
| CV | OL1-2K31-0004 | Foundation For 10-E-2765 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01522
Return Date
Owner Cmmt*
| CV | OL1-2K31-0005 | Foundation For 10-E-2585 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01206
Return Date
Owner Cmmt*
| CV | OL1-2K31-0051 | Foundation For 10-D-2210 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K31-0052 | Foundation For 10-D-2230 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K31-0053 | Foundation for 10-D-2405 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K31-0062 | Foundation For 10-E-2230A-B |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0063 | Foundation For 10-E-2412 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01334
Return Date
Owner Cmmt*
| CV | OL1-2K31-0064 | Foundation for 10-E-2413 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01470
Return Date
Owner Cmmt*
| CV | OL1-2K31-0066 | Foundation For 10-E-2446 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0068 | Foundation For 10-E-2450 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01349
[6 empty] | Return Date | 2019-02-20: 2019-04-23
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K31-0070 | Foundation For 10-E-2206 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01206
Return Date
Owner Cmmt*
| CV | OL1-2K31-0071 | Foundation For 10-E-2210AB |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0072 | Foundation For 10-E-2220A-B |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0073 | Foundation For 10-E-2240A-B |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0075 | Foundation For 10-E-2305 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0094 | Foundation For 10-T-2580 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K31-0096 | Foundation For 10-T-2570 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K31-0097 | Foundation For 10-T-2510 And 10-T-2540 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01241
Return Date
Owner Cmmt*
| CV | OL1-2K31-0098 | Foundation For 10-T-2510 And 10-T-2540 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01241
Return Date
Owner Cmmt*
| CV | OL1-2K31-0100 | Foundation For 10-D-2411 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K31-0101 | Foundation Vor 10-D-2480A |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K31-0106 | Foundation For 10-D-2420A-B |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01663
Return Date
Owner Cmmt*
| CV | OL1-2K31-0117 | Foundation For 10-E-2587 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01206
Return Date
Owner Cmmt*
| CV | OL1-2K31-0143 | Foundation For 10-R-2700A-B |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01663
Return Date
Owner Cmmt*
| CV | OL1-2K31-0144 | Foundation For 10-R-2620 A |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0147 | Foundation For 10-E-2666 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01663
Return Date
Owner Cmmt*
| CV | OL1-2K31-0149 | Foundation For 10-E-2660 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01470
Return Date
Owner Cmmt*
| CV | OL1-2K31-0153 | Foundation for 10-T-2630 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0154 | Foundation For 10-R-2470A-B-C |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01663
Return Date
Owner Cmmt*
| CV | OL1-2K31-0157 | Foundation For 10-D-2460 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K31-0158 | Foundation For 10-D-2440 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K31-0159 | Foundation for 10-D-1000 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0160 | Foundation For 10-E-2635 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01349
[6 empty] | Return Date | 2019-02-20: 2019-04-23
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K31-0163 | Foundation for 10-E-2474 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0164 | Foundation For 10-E-2465 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0165 | Foundation For 10-E-2460 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0166 | Foundation For 10-E-2440 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01334
Return Date
Owner Cmmt*
| CV | OL1-2K31-0170 | Foundation For 10-E-1000 A/B |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01349
[6 empty] | Return Date | 2019-02-20: 2019-04-23
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K31-0171 | Foundation For 10-E-1005 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01349
[6 empty] | Return Date | 2019-02-20: 2019-04-23
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K31-0177 | Foundation For 10-D-2705 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01522
Return Date
Owner Cmmt*
| CV | OL1-2K31-0178 | Foundation For 10-E-2705 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01522
Return Date
Owner Cmmt*
| CV | OL1-2K31-0180 | Foundation For 10-D-2735 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-18
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01414
Return Date
Owner Cmmt*
| CV | OL1-2K31-0184 | Foundation For 10-E-2755 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01663
Return Date
Owner Cmmt*
| CV | OL1-2K31-0189 | Foundation For 10-E-2701 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01455
Return Date
Owner Cmmt*
| CV | OL1-2K31-0190 | Foundation For 10-E-2706 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01663
Return Date
Owner Cmmt*
| CV | OL1-2K31-0198 | Foundation For 10-E-2882 And 10-E-2884 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01206
Return Date
Owner Cmmt*
| CV | OL1-2K31-0203 | Foundation For 10-D-1910 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01470
Return Date
Owner Cmmt*
| CV | OL1-2K31-0307 | Foundation For 10-D-5400 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01522
Return Date
Owner Cmmt*
| CV | OL1-2K31-0308 | Foundation For 10-D-5114 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01455
Return Date
Owner Cmmt*
| CV | OL1-2K31-0309 | Foundation For 10-D-5112 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01455
Return Date
Owner Cmmt*
| CV | OL1-2K31-0313 | Foundation For 10-E-5113 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01663
Return Date
Owner Cmmt*
| CV | OL1-2K31-0338 | Foundation For 10-E-2441 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01334
Return Date
Owner Cmmt*
| CV | OL1-2K31-0339 | Foundation for 10-E-2442 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0340 | Foundation For 10-E-2405 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01663
Return Date
Owner Cmmt*
| CV | OL1-2K31-0341 | Foundation For 10-D-1912 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01470
Return Date
Owner Cmmt*
| CV | OL1-2K31-1000 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-0P01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1020 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-0P01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1040 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-0P02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1060 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-0P02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1080 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-0P03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1100 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-0P03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1120 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-3A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1140 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-3A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1160 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-5U01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1180 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-5U01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1200 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2D01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1220 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2D01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1240 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2E01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1260 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2E01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1280 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1300 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1320 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1340 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2B02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1360 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1380 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2B02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1400 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2C01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1440 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2C01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1500 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-5T01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1520 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-5F01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18; 2019-03-29: 2019-12-18; 2019-08-06: 2020-01-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1540 | FOUNDATION FOR 10-PRK-5F01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-18; 2019-02-20: 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1560 | FOUNDATION AND ELEVATION FOR 10-STR-2E01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1580 | FOUNDATION AND ELEVATION FOR 10-STR-2E02, 10-D-2420A/B AND 10-E-2430 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1600 | FOUNDATION AND ELEVATION FOR 10-STR-2E03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1620 | FOUNDATION AND ELEVATION FOR 10-STR-2E04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1640 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D05 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1660 | FOUNDATION AND ELEVATION FOR 10-STR-2B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1680 | FOUNDATION AND ELEVATION FOR 10-STR-2B02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1700 | FOUNDATION AND ELEVATION FOR 10-STR-2B03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1720 | FOUNDATION AND ELEVATION FOR 10-STR-2B04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1740 | FOUNDATION AND ELEVATION FOR 10-STR-2B05 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1760 | FOUNDATION AND ELEVATION FOR 10-STR-2B06 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1780 | FOUNDATION AND ELEVATION FOR 10-SHT-2D01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1800 | FOUNDATION AND ELEVATION FOR 10-SHT-2D02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1820 | FOUNDATION AND ELEVATION FOR 10-STR-2C01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1840 | FOUNDATION AND ELEVATION FOR 10-STR-2C02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1860 | FOUNDATION AND ELEVATION FOR 10-STR-2C03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1880 | FOUNDATION AND ELEVATION FOR 10-STR-2C04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1900 | FOUNDATION AND ELEVATION FOR 10-STR-2C05 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1920 | FOUNDATION AND ELEVATION FOR 10-SHT-2B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1940 | FOUNDATION AND ELEVATION FOR 10-SHT-1B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1960 | FOUNDATION AND ELEVATION FOR 10-STR-0P01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1980 | FOUNDATION AND ELEVATION FOR 10-STR-2A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2000 | FOUNDATION AND ELEVATION FOR 10-STR-2A02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2020 | FOUNDATION AND ELEVATION FOR 10-STR-2A03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2040 | FOUNDATION AND ELEVATION FOR WASTE STORAGE BUILDING |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2060 | FOUNDATION AND ELEVATION FOR STORAGE SHELTER FOR CHENICALS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2080 | FOUNDATION AND ELEVATION FOR LUBRIFICATION OIL & GREASE STORAGE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2100 | FOUNDATION AND ELEVATION FOR GAS CYLINDER STORAGE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2120 | FOUNDATION AND ELEVATION FOR TOOL ROOM OPERATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2140 | FOUNDATION FOR 10-SHT-2E01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2160 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2180 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2200 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2220 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2240 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A06 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2260 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2280 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A05 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2300 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2320 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2340 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2360 | FOUNDATION FOR STRUCTURE 10-SHT-3A01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2380 | FOUNDATION FOR STRUCTURE 10-SHT-5T01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2400 | FOUNDATION FOR STRUCTURE 10-SHT-5T02 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2420 | FOUNDATION FOR STRUCTURE 10-SHT-5T03 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2440 | FOUNDATION AND ELEVATION FOR 10-STR-5U01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-12; 2019-02-20: 2020-05-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2520 | Concrete Basin 10-PIT-2090 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-12-24; 2019-02-20: 2020-01-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01304
[6 empty] | Return Date | 2019-02-20: 2019-05-09
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K31-2521 | Concrete Basin 10-PIT-2090 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01304
[6 empty] | Return Date | 2019-02-20: 2019-05-09
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K31-3000 | FOUNDATION FOR 10-STR-1B01 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-02; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-4060 | Zone 2A - Piling Plan |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-10-15; 2019-02-20: 2019-12-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01170
Return Date
Owner Cmmt*
| CV | OL1-2K31-4120 | Zone 2D - Piling Plan |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-10-15; 2019-02-20: 2019-12-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01170
Return Date
Owner Cmmt*
Category Code: K32 General Arrangement for Steel Structure drawings
| CV | OL1-2K32-1060 | STEEL FOR PIPE RACK 10-PRK-3A01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-28; 2019-02-20: 2020-02-01; 2019-03-29: 2020-03-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1080 | STEEL FOR PIPE RACK 10-PRK-5U01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-28; 2019-02-20: 2020-02-01; 2019-03-29: 2020-03-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1100 | STEEL FOR PIPE RACK 10-PRK-2D01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-28; 2019-02-20: 2020-02-01; 2019-03-29: 2020-03-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1120 | STEEL FOR PIPE RACK 10-PRK-2E01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-28; 2019-02-20: 2020-02-01; 2019-03-29: 2020-03-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1140 | STEEL FOR PIPE RACK 10-PRK-2A01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-28; 2019-02-20: 2020-02-01; 2019-03-29: 2020-03-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1160 | STEEL FOR PIPE RACK 10-PRK-2B01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-28; 2019-02-20: 2020-02-01; 2019-03-29: 2020-03-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1180 | STEEL FOR PIPE RACK 10-PRK-2B02 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-28; 2019-02-20: 2020-02-01; 2019-03-29: 2020-03-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1200 | STEEL FOR PIPE RACK 10-PRK-2C01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-28; 2019-02-20: 2020-02-01; 2019-03-29: 2020-03-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1240 | STEEL FOR PIPE RACK 10-PRK-5T01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-28; 2019-02-20: 2020-02-01; 2019-03-29: 2020-03-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1260 | STEEL FOR 10-PRK-5F01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-28; 2019-02-20: 2020-02-01; 2019-03-29: 2020-03-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1280 | STEEL FOR 10-SHT-2E01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1300 | STEEL FOR STRUCTURE 10-STR-2E01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1304 | FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-20; 2019-03-29: 2019-04-10
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01321
Return Date
Owner Cmmt*
| CV | OL1-2K32-1320 | STEEL FOR STRUCTURE 10-STR-2E02 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1340 | STEEL FOR STRUCTURE 10-STR-2E03 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1360 | STEEL FOR STRUCTURE 10-STR-2E04 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1380 | STEEL FOR STRUCTURE 10-STR-2D05 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1400 | STEEL FOR STRUCTURE 10-STR-2B01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1420 | STEEL FOR STRUCTURE 10-STR-2B02 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1440 | STEEL FOR STRUCTURE 10-STR-2B03 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1460 | STEEL FOR STRUCTURE 10-STR-2B04 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1480 | STEEL FOR STRUCTURE 10-STR-2B05 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1500 | STEEL FOR STRUCTURE 10-STR-2B06 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1511 | USC 36M FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1512 | USC 36M FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1513 | USC 36M FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1514 | USC 36M FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1515 | USC 36M FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1516 | USC 36M FURNACE STEEL SHADOW BOX DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1517 | USC 36M FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1518 | USC 36M FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1519 | USC 36M FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1520 | USC 36M FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01308
Return Date
Owner Cmmt*
| CV | OL1-2K32-1521 | USC 36M FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01308
Return Date
Owner Cmmt*
| CV | OL1-2K32-1522 | USC 36M FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148-2 1/2 & EL 221-10 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1523 | USC 36M FURNACE STEEL END WALL TUBE SHEET ELEVATION |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1524 | USC 36M FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1525 | USC 36M FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1526 | USC 36M FURNACE STEEL CONVECTION SECTION HEADER BOX ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1527 | USC 36M FURNACE STEEL CONVECTION SECTION HEADER BOX DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1528 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE A2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1529 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE B2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1530 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE C2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1531 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1532 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D0 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1533 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1534 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1535 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1536 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1537 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1538 | USC 36M FURNACE STEEL CONVECTION SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1539 | USC 36M FURNACE STEEL CROSSOVER LIMIT STOP DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1540 | USC 36M FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1541 | USC 36M FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1542 | USC 36M FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1543 | USC 36M FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1544 | USC 36M FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1545 | USC 36M FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1546 | USC 36M FURNACE STEEL NAME PLATE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1550 | USC 36M FURNACE STEEL STACK AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1551 | USC 36M FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00767
[6 empty] | Return Date | 2019-02-20: 2019-02-21
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K32-1552 | USC 36M FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-09-18; 2019-03-29: 2018-12-07; 2019-08-06: 2019-01-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1553 | USC 36M FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1555 | USC 36M Recycle Furnace Steel Inspection Door Lance Door and Access Door Details |  | Class Final | Purpose** | 2019-02-20: IFI
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1560 | USC 36M FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1561 | USC 36M FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1580 | USC 36M FURNACE STEEL BREECHING PLAN AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1581 | USC 36M FURNACE STEEL BREECHING SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1582 | USC 36M FURNACE STEEL DUCT PLAN AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1583 | USC 36M FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1584 | USC 36M FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1585 | USC 36M FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1586 | USC 36M FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1587 | USC 36M FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1600 | STEEL FOR STRUCTURE 10-STR-2C03 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1601 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01584
Return Date
Owner Cmmt*
| CV | OL1-2K32-1602 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01584
Return Date
Owner Cmmt*
| CV | OL1-2K32-1603 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01584
Return Date
Owner Cmmt*
| CV | OL1-2K32-1604 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1605 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1606 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1607 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1608 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1609 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1610 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1611 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1612 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1613 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1614 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1615 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1616 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1617 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1618 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1619 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1620 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1621 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1622 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1623 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1631 | USC 36M FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1632 | USC 36M FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1640 | STEEL FOR STRUCTURE 10-STR-2C05 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1641 | USC 36M FURNACE STEEL ID FAN BOLTING PLAN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1651 | USC 36M FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1660 | STEEL FOR STRUCTURE 10-SHT-2B01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1680 | STEEL FOR STRUCTURE 10-SHT-1B01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1700 | STEEL FOR STRUCTURE 10-STR-0P01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1701 | USC 36M FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1702 | USC 36M FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1703 | USC 36M FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1704 | USC 36M FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1705 | USC 36M FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1706 | USC 36M FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1707 | USC 36M FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1708 | USC 36M FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1720 | STEEL FOR STRUCTURE 10-STR-2A01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1740 | STEEL FOR STRUCTURE 10-STR-2A02 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1760 | STEEL FOR STRUCTURE 10-STR-2A03 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1780 | STEEL FOR STRUCTURE 10-STR-2D01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1800 | STEEL FOR STRUCTURE 10-STR-2D02 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1820 | STEEL FOR STRUCTURE 10-STR-2D03 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1840 | STEEL FOR STRUCTURE 10-STR-2D04 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1860 | STEEL FOR WASTE STORAGE BUILDING |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1880 | STEEL FOR STORAGE SHELTER FOR CHEMICALS |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1900 | STEEL FOR LUBRIFICATION OIL & GREASE STORAGE |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1901 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1902 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1903 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1904 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1905 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1906 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1907 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1908 | USC 36M FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1909 | USC 36M FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1910 | USC 36M FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1911 | USC 36M FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1912 | USC 36M FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1913 | USC 36M FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1914 | USC 36M FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1920 | STEEL FOR GAS CYLINDER STORAGE |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1940 | STEEL FOR TOOL ROOM OPERATION |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1960 | STEEL FOR STRUCTURE 10-STR-3A06 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1980 | STEEL FOR STRUCTURE 10-STR-3A03 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2000 | STEEL FOR STRUCTURE 10-STR-3A05 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2020 | STEEL FOR STRUCTURE 10-STR-3A04 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2040 | STEEL FOR STRUCTURE 10-STR-3A02 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2060 | STEEL FOR STRUCTURE 10-STR-3A01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2080 | STEEL FOR STRUCTURE 10-SHT-3A01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2100 | STEEL FOR STRUCTURE 10-SHT-2D01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2120 | STEEL FOR STRUCTURE 10-SHT-2D02 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2140 | STEEL FOR STRUCTURE 10-STR-2C01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2160 | STEEL FOR STRUCTURE 10-STR-2C02 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2161 | FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2162 | FURNACE STEEL MOMENT CONNECTION DETAIL AND MISCELLANEOUS DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2163 | FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2164 | FURNACE STEEL STANDARD FLOOR - TOE PLATE DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2180 | STEEL FOR STRUCTURE 10-STR-2C04 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2304 | FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-20; 2019-03-29: 2019-04-10
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01321
Return Date
Owner Cmmt*
| CV | OL1-2K32-2500 | USC 132U & 36M FURNACE GENERAL NOTES & ABBREVIATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2501 | USC 132U & 36M FURNACE STEEL FOUNDATION PLAN & LOADING DIAGRAM |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFD; 2019-08-06: IFF
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-05-07; 2019-03-29: 2019-06-05; 2019-08-06: 2019-06-05
[6 empty] | Revised Plan | 2019-02-20: 2019-05-23
[6 empty] | Issue Actual | 2019-02-20: 2019-05-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01618
Return Date
Owner Cmmt*
| CV | OL1-2K32-2502 | USC 132U & 36M FURNACE STEEL BASE PLATE DETAILS |  | Class 3 | Purpose** | IFR | IFI | IFD | IFF | IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-11-11: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-05-07; 2019-03-29: 2019-06-05; 2019-08-06: 2019-06-05
[6 empty] | Revised Plan | 2019-02-20: 2019-05-23
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01; 2019-11-11: 2019-05-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222; 2019-11-11: TPSK-LSPA1-T-CV-01616
Return Date
Owner Cmmt*
| CV | OL1-2K32-2503 | USC 132U & 36M FURNACE STEEL MISCELLANEOUS FOUNDATION PLAN & LOADING DIAGRAM |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-07; 2019-02-20: 2019-06-05; 2019-03-29: 2019-06-05
[6 empty] | Revised Plan | 2019-02-20: 2019-05-23
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2504 | USC 132U & 36M FURNACE STEEL MISCELLANEOUS FOUNDATION PLAN & LOADING DIAGRAM |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-07; 2019-02-20: 2019-06-05; 2019-03-29: 2019-06-05
[6 empty] | Revised Plan | 2019-02-20: 2019-05-23
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2511 | USC 132U FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2512 | USC 132U FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2513 | USC 132U FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2514 | USC 132U FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2515 | USC 132U FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2516 | USC 132U FURNACE STEEL SHADOW BOX DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2517 | USC 132U FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2518 | USC 132U FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2519 | USC 132U FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2520 | USC 132U FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2521 | USC 132U FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2522 | USC 132U FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148-2 1/2 & EL 221-10 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2523 | USC 132U FURNACE STEEL END WALL TUBE SHEET ELEVATION |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2524 | USC 132U FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2525 | USC 132U FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2526 | USC 132U FURNACE STEEL CONVECTION SECTION HEADER BOX ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2527 | USC 132U FURNACE STEEL CONVECTION SECTION HEADER BOX DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2528 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE A2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2529 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE B2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2530 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE C2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2531 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2532 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D0 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2533 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2534 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2535 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2536 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2537 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2538 | USC 132U FURNACE STEEL CONVECTION SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2539 | USC 132U FURNACE STEEL CROSSOVER LIMIT STOP DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2540 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2541 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01308
Return Date
Owner Cmmt*
| CV | OL1-2K32-2542 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2543 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2544 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2545 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2546 | USC 132U FURNACE STEEL NAME PLATE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-04
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00423
Return Date
Owner Cmmt*
| CV | OL1-2K32-2550 | USC 132U FURNACE STEEL STACK AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2551 | USC 132U FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00767
[6 empty] | Return Date | 2019-02-20: 2019-02-21
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K32-2552 | USC 132U FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-09-18; 2019-03-29: 2018-12-07; 2019-08-06: 2019-01-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2553 | USC 132U FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2555 | USC 132U Cracking Furnace Steel Inspection Door Lance Door and Access Door Details |  | Class Final | Purpose** | 2019-02-20: IFI
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01308
Return Date
Owner Cmmt*
| CV | OL1-2K32-2560 | USC 132U FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2561 | USC 132U FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2580 | USC 132U FURNACE STEEL BREECHING PLAN AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2581 | USC 132U FURNACE STEEL BREECHING SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2582 | USC 132U FURNACE STEEL DUCT PLAN AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2583 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2584 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2585 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2586 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2587 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2601 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01584
Return Date
Owner Cmmt*
| CV | OL1-2K32-2602 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01584
Return Date
Owner Cmmt*
| CV | OL1-2K32-2603 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-03-29: 2019-10-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01584
Return Date
Owner Cmmt*
| CV | OL1-2K32-2604 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2605 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2606 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2607 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2608 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2609 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2610 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2611 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2612 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2613 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2614 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2615 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2616 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2617 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2618 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2619 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2620 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2621 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2622 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2623 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2631 | USC 132U FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2632 | USC 132U FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2641 | USC 132U FURNACE STEEL ID FAN BOLTING PLAN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2651 | USC 132U FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2659 | USC 132U & 36M FURNACE STEEL MOMENT CONNECTION DETAIL & MISCELLANEOUS DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2660 | USC 132U & 36M FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2661 | USC 36M Recycle Furnace and 132U Cracking Furnaces Steel Platform and TOE Details |  | Class Final | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01585
Return Date
Owner Cmmt*
| CV | OL1-2K32-2701 | USC 132U FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2702 | USC 132U FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2703 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2704 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2705 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2706 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2707 | USC 132U FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2708 | USC 132U FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2801 | USC FURNACE STEEL ELEVATOR ACCESS PLATFORM |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2802 | USC FURNACE STEEL ELEVATOR PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2803 | USC FURNACE STEEL ELEVATOR PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2804 | USC FURNACE STEEL ELEVATOR PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2805 | USC FURNACE STEEL ELEVATOR PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2901 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2902 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2903 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2904 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2905 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2906 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2907 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2908 | USC 132U FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2909 | USC 132U FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2910 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2911 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2912 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2913 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2914 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3000 | STEEL FOR STRUCTURE 10-SHT-5T01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3020 | STEEL FOR STRUCTURE 10-SHT-5T02 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3040 | STEEL FOR STRUCTURE 10-SHT-5T03 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3060 | STEEL FOR STRUCTURE 10-STR-5U01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3080 | STEEL FOR STRUCTURE 10-STR-1B01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-25; 2019-02-20: 2020-07-24; 2019-03-29: 2020-09-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3515 | USC 132U FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3520 | USC 132U FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3521 | USC 132U FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3522 | USC 132U FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148-2 1/2 & EL 221-10 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3523 | USC 132U FURNACE STEEL END WALL TUBE SHEET ELEVATION |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3524 | USC 132U FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3525 | USC 132U FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3526 | USC 132U FURNACE STEEL CONVECTION SECTION HEADER BOX ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3527 | USC 132U FURNACE STEEL CONVECTION SECTION HEADER BOX DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3528 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE A2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3529 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE B2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3530 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE C2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3531 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3532 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D0 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3533 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3534 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3535 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3536 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3537 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3538 | USC 132U FURNACE STEEL CONVECTION SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3539 | USC 132U FURNACE STEEL CROSSOVER LIMIT STOP DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3540 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3541 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3542 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3543 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3544 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3545 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3546 | USC 132U FURNACE STEEL NAME PLATE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3550 | USC 132U FURNACE STEEL STACK AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3551 | USC 132U FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3560 | USC 132U FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3561 | USC 132U FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3580 | USC 132U FURNACE STEEL BREECHING PLAN AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3581 | USC 132U FURNACE STEEL BREECHING SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3582 | USC 132U FURNACE STEEL DUCT PLAN AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3583 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3584 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3585 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3586 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3587 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3601 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3602 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3603 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3604 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3605 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3606 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3607 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3608 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3609 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3610 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3611 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3612 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3613 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3614 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3615 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3616 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3617 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3618 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3619 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3620 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3621 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3622 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3623 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3631 | USC 132U FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3632 | USC 132U FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3641 | USC 132U FURNACE STEEL ID FAN BOLTING PLAN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3651 | USC 132U FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3701 | USC 132U FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3702 | USC 132U FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3703 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3704 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3705 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3706 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3707 | USC 132U FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3708 | USC 132U FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3901 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3902 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3903 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3904 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3905 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3906 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3907 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3908 | USC 132U FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3909 | USC 132U FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3910 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3911 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3912 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3913 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3914 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4515 | USC 132U FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4521 | USC 132U FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4522 | USC 132U FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148-2 1/2 & EL 221-10 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4523 | USC 132U FURNACE STEEL END WALL TUBE SHEET ELEVATION |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4524 | USC 132U FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4525 | USC 132U FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4526 | USC 132U FURNACE STEEL CONVECTION SECTION HEADER BOX ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4527 | USC 132U FURNACE STEEL CONVECTION SECTION HEADER BOX DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4528 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE A2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4529 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE B2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4530 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE C2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4531 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4532 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D0 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4533 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4534 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4535 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4536 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4537 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4538 | USC 132U FURNACE STEEL CONVECTION SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4539 | USC 132U FURNACE STEEL CROSSOVER LIMIT STOP DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4540 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4541 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4542 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4543 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4544 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4545 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4546 | USC 132U FURNACE STEEL NAME PLATE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4550 | USC 132U FURNACE STEEL STACK AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4551 | USC 132U FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4560 | USC 132U FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4561 | USC 132U FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4580 | USC 132U FURNACE STEEL BREECHING PLAN AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4581 | USC 132U FURNACE STEEL BREECHING SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4582 | USC 132U FURNACE STEEL DUCT PLAN AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4583 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4584 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4585 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4586 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4587 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4601 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4602 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4603 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4604 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4605 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4606 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4607 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4608 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4609 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4610 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4611 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4612 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4613 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4614 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4615 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4616 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4617 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4618 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4619 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4620 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4621 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4622 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4623 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4631 | USC 132U FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4632 | USC 132U FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4641 | USC 132U FURNACE STEEL ID FAN BOLTING PLAN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4651 | USC 132U FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4701 | USC 132U FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4702 | USC 132U FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4703 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4704 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4705 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4706 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4707 | USC 132U FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4708 | USC 132U FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4901 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4902 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4903 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4904 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4905 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4906 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4907 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4908 | USC 132U FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4909 | USC 132U FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4910 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4911 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4912 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4913 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4914 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5515 | USC 132U FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5520 | USC 132U FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5521 | USC 132U FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5522 | USC 132U FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148-2 1/2 & EL 221-10 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5523 | USC 132U FURNACE STEEL END WALL TUBE SHEET ELEVATION |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5524 | USC 132U FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5525 | USC 132U FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5526 | USC 132U FURNACE STEEL CONVECTION SECTION HEADER BOX ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5527 | USC 132U FURNACE STEEL CONVECTION SECTION HEADER BOX DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5528 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE A2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5529 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE B2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5530 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE C2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5531 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5532 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D0 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5533 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5534 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5535 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5536 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5537 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5538 | USC 132U FURNACE STEEL CONVECTION SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5539 | USC 132U FURNACE STEEL CROSSOVER LIMIT STOP DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5540 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5541 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5542 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5543 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5544 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5545 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5546 | USC 132U FURNACE STEEL NAME PLATE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5550 | USC 132U FURNACE STEEL STACK AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5551 | USC 132U FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5560 | USC 132U FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5561 | USC 132U FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5580 | USC 132U FURNACE STEEL BREECHING PLAN AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5581 | USC 132U FURNACE STEEL BREECHING SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5582 | USC 132U FURNACE STEEL DUCT PLAN AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5583 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5584 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5585 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5586 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5587 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5601 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5602 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5603 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5604 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5605 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5606 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5607 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5608 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5609 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5610 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5611 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5612 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5613 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5614 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5615 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5616 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5617 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5618 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5619 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5620 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5621 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5622 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5623 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5631 | USC 132U FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5632 | USC 132U FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5641 | USC 132U FURNACE STEEL ID FAN BOLTING PLAN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5651 | USC 132U FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5701 | USC 132U FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5702 | USC 132U FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5703 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5704 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5705 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5706 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5707 | USC 132U FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5708 | USC 132U FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5901 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5902 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5903 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5904 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5905 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5906 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5907 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5908 | USC 132U FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5909 | USC 132U FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5910 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5911 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5912 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5913 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5914 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6515 | USC 132U FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6520 | USC 132U FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6521 | USC 132U FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6522 | USC 132U FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148-2 1/2 & EL 221-10 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6523 | USC 132U FURNACE STEEL END WALL TUBE SHEET ELEVATION |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6524 | USC 132U FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6525 | USC 132U FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6526 | USC 132U FURNACE STEEL CONVECTION SECTION HEADER BOX ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6527 | USC 132U FURNACE STEEL CONVECTION SECTION HEADER BOX DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6528 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE A2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6529 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE B2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6530 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE C2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6531 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6532 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D0 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6533 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6534 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6535 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6536 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6537 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6538 | USC 132U FURNACE STEEL CONVECTION SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6539 | USC 132U FURNACE STEEL CROSSOVER LIMIT STOP DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6540 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6541 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6542 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6543 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6544 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6545 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6546 | USC 132U FURNACE STEEL NAME PLATE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6550 | USC 132U FURNACE STEEL STACK AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6551 | USC 132U FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6560 | USC 132U FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6561 | USC 132U FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6580 | USC 132U FURNACE STEEL BREECHING PLAN AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6581 | USC 132U FURNACE STEEL BREECHING SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6582 | USC 132U FURNACE STEEL DUCT PLAN AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6583 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6584 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6585 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6586 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6587 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6601 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6602 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6603 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6604 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6605 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6606 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6607 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6608 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6609 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6610 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6611 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6612 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6613 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6614 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6615 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6616 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6617 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6618 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6619 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6620 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6621 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6622 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6623 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6631 | USC 132U FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6632 | USC 132U FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6641 | USC 132U FURNACE STEEL ID FAN BOLTING PLAN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6651 | USC 132U FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6701 | USC 132U FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6702 | USC 132U FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6703 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6704 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6705 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6706 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6707 | USC 132U FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6708 | USC 132U FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6901 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6902 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6903 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6904 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6905 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6906 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6907 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6908 | USC 132U FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6909 | USC 132U FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6910 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6911 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6912 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6913 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6914 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-02; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7000 | STEEL FOR PIPE RACK 10-PRK-0P01 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-28; 2019-02-20: 2020-02-01; 2019-03-29: 2020-03-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7100 | STEEL FOR PIPE RACK 10-PRK-0P02 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-28; 2019-02-20: 2020-02-01; 2019-03-29: 2020-03-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7200 | STEEL FOR PIPE RACK 10-PRK-0P03 |  | Class 2 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-28; 2019-02-20: 2020-02-01; 2019-03-29: 2020-03-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K33 Shop Detail Drawings
Category Code: K34 Foundation for equipment, basin, cooling tower, supports and miscellaneous
| CV | OL1-2K34-0007 | FOUNDATION FOR 10-D-5200 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0008 | FOUNDATION FOR 10-E-5200 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0009 | FOUNDATION FOR 10-E-5210 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01034
Return Date
Owner Cmmt*
| CV | OL1-2K34-0015 | FOUNDATION FOR 10-D-5150 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0016 | FOUNDATION FOR 10-D-2160 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00734
[6 empty] | Return Date | 2019-02-20: 2019-03-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0020 | FOUNDATION FOR 10-E-2136 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0023 | FOUNDATION FOR 10-E-2166 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0024 | FOUNDATION FOR 10-E-2146 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0026 | FOUNDATION FOR 10-E-2026 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0027 | FOUNDATION FOR 10-E-2048 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00807
[6 empty] | Return Date | 2019-02-20: 2019-03-18
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0042 | FOUNDATION FOR 10-T-2330 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0043 | FOUNDATION FOR 10-D-2410A/B/C |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01034
Return Date
Owner Cmmt*
| CV | OL1-2K34-0044 | FOUNDATION FOR 10-D-2435 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01034
Return Date
Owner Cmmt*
| CV | OL1-2K34-0046 | FOUNDATION FOR 10-D-2240 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01034
Return Date
Owner Cmmt*
| CV | OL1-2K34-0047 | FOUNDATION FOR 10-D-2245 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01034
Return Date
Owner Cmmt*
| CV | OL1-2K34-0048 | FOUNDATION FOR 10-D-2445 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01034
Return Date
Owner Cmmt*
| CV | OL1-2K34-0049 | FOUNDATION FOR 10-D-2455 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00833
Return Date
Owner Cmmt*
| CV | OL1-2K34-0050 | FOUNDATION FOR 10-D-2220 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01034
Return Date
Owner Cmmt*
| CV | OL1-2K34-0055 | FOUNDATION FOR 10-D-2310 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00826
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0057 | FOUNDATION FOR 10-D-2316 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00807
[6 empty] | Return Date | 2019-02-20: 2019-03-18
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0059 | FOUNDATION FOR 10-D-2330 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00807
[6 empty] | Return Date | 2019-02-20: 2019-03-18
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0074 | FOUNDATION FOR 10-D-2305 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00826
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0076 | FOUNDATION FOR 10-E-2630 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0095 | FOUNDATION FOR 10-T-2640 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-20
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01105
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0099 | FOUNDATION FOR 10-T-2520 AND 10-D-2520 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00728
[6 empty] | Return Date | 2019-02-20: 2019-03-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0105 | FOUNDATION FOR 10-D-2815 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00734
[6 empty] | Return Date | 2019-02-20: 2019-03-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0108 | FOUNDATION FOR 10-D-2645 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00807
[6 empty] | Return Date | 2019-02-20: 2019-03-18
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0109 | FOUNDATION FOR 10-D-2555 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-20
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0110 | FOUNDATION FOR 10-D-2550 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-20
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0112 | FOUNDATION FOR 10-D-2575 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0114 | FOUNDATION FOR 10-D-2870 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00728
[6 empty] | Return Date | 2019-02-20: 2019-03-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0115 | FOUNDATION FOR 10-D-2860 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00734
[6 empty] | Return Date | 2019-02-20: 2019-03-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0116 | FOUNDATION FOR 10-D-2865 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0122 | FOUNDATION FOR 10-E-2576 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0123 | FOUNDATION FOR 10-E-2645A/B |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01042
Return Date
Owner Cmmt*
| CV | OL1-2K34-0124 | FOUNDATION FOR 10-E-2502 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00728
[6 empty] | Return Date | 2019-02-20: 2019-03-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0125 | FOUNDATION FOR 10-E-2515 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0126 | FOUNDATION FOR 10-E-2546 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0127 | FOUNDATION FOR 10-E-2548 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0128 | FOUNDATION FOR 10-E-2545 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00763
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0130 | FOUNDATION FOR 10-E-2807 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0131 | FOUNDATION FOR 10-E-2809 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0132 | FOUNDATION FOR 10-E-2857 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00807
[6 empty] | Return Date | 2019-02-20: 2019-03-18
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0133 | FOUNDATION FOR 10-E-2858 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0134 | FOUNDATION FOR 10-E-2856 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0135 | FOUNDATION FOR 10-E-2855 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-20
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0136 | FOUNDATION FOR 10-E-2853 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00868
Return Date
Owner Cmmt*
| CV | OL1-2K34-0137 | FOUNDATION FOR 10-E-2852 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01034
Return Date
Owner Cmmt*
| CV | OL1-2K34-0139 | FOUNDATION FOR 10-E-2582 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR
Rev. | bar: 2019-02-20 to 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15; 2019-02-20: 2019-02-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00854; 2019-02-20: TPSK-LSPA1-T-CV-00903
[6 empty] | Return Date | 2019-02-20: 2019-04-12; 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| CV | OL1-2K34-0140 | FOUNDATION FOR 10-E-2504 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00763
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0146 | FOUNDATION FOR 10-E-2620 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01034
Return Date
Owner Cmmt*
| CV | OL1-2K34-0155 | FOUNDATION FOR 10-D-2610 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00833
Return Date
Owner Cmmt*
| CV | OL1-2K34-0156 | FOUNDATION FOR 10-D-2600A/B |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00833
Return Date
Owner Cmmt*
| CV | OL1-2K34-0161 | FOUNDATION FOR 10-E-2636 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0167 | FOUNDATION FOR 10-E-1020 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01208
Return Date
Owner Cmmt*
| CV | OL1-2K34-0168 | FOUNDATION FOR 10-E-1015 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01034
Return Date
Owner Cmmt*
| CV | OL1-2K34-0169 | FOUNDATION FOR 10-E-1001A/B |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01034
Return Date
Owner Cmmt*
| CV | OL1-2K34-0191 | FOUNDATION FOR 10-E-2008A/B/C |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0202 | FOUNDATION FOR 10-E-1050 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01208
Return Date
Owner Cmmt*
| CV | OL1-2K34-0269 | FOUNDATION FOR 10-D-5510 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01647
Return Date
Owner Cmmt*
| CV | OL1-2K34-0270 | FOUNDATION FOR 10-D-5513 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01647
Return Date
Owner Cmmt*
| CV | OL1-2K34-0271 | FOUNDATION FOR 10-D-5515 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01647
Return Date
Owner Cmmt*
| CV | OL1-2K34-0272 | FOUNDATION FOR 10-D-5520 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01647
Return Date
Owner Cmmt*
| CV | OL1-2K34-0306 | FOUNDATION FOR 10-D-5140 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00728
[6 empty] | Return Date | 2019-02-20: 2019-03-27
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-0323 | FOUNDATION FOR 10-TK-5900 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01647
Return Date
Owner Cmmt*
| CV | OL1-2K34-1001 | Foundation for 10-T-2000 |  |  | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-20
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-1020 | FOUNDATION FOR 10-T-2020 |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-20
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K34-1040 | FOUNDATION FOR 10-T-2100 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR
Rev. | bar: 2019-02-20 to 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-21; 2019-02-20: 2019-03-20
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00903; 2019-02-20: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | 2019-02-20: 2019-04-12; 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
Category Code: K36 Major UG networks (Nuovo codice richiesto dal Cliente K26/K27) |  |  |  |  | Class 2 | Purpose**
| CV | OL1-2K36-0001 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01138
Return Date
Owner Cmmt*
| CV | OL1-2K36-0002 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01138
Return Date
Owner Cmmt*
| CV | OL1-2K36-0003 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01138
Return Date
Owner Cmmt*
| CV | OL1-2K36-0004 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01138
Return Date
Owner Cmmt*
| CV | OL1-2K36-0005 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01138
Return Date
Owner Cmmt*
| CV | OL1-2K36-0006 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01138
Return Date
Owner Cmmt*
| CV | OL1-2K36-0007 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01138
Return Date
Owner Cmmt*
| CV | OL1-2K36-0008 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01138
Return Date
Owner Cmmt*
| CV | OL1-2K36-0009 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01138
Return Date
Owner Cmmt*
| CV | OL1-2K36-0010 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01138
Return Date
Owner Cmmt*
| CV | OL1-2K36-0011 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01138
Return Date
Owner Cmmt*
| CV | OL1-2K36-0012 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K36-0013 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01240
Return Date
Owner Cmmt*
| CV | OL1-2K36-1000 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01073
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
Category Code: K40 Topographic survey report
Category Code: K41 Hydrological survey report
Category Code: K42 Bathymetric survey report
Category Code: K43 Soil investigation & resisitivity report
| CV | OL1-2K43-0002 | TECHNICAL SPECIFICATION FOR GEOTECHNICAL INVESTIGATION |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IMP
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-10-08; 2019-02-20: 2018-10-08; 2019-03-29: 2019-12-17
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-10; 2019-02-20: 2018-10-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00147; 2019-02-20: TPSK-LSPA1-T-CV-00188
[6 empty] | Return Date | 2019-02-20: 2018-12-24; 2019-02-20: 2018-11-01
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| CV | OL1-2K43-0003 | Price List For Geotechnical Investigation |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR
Rev. | bar: 2019-02-20 to 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-10; 2019-02-20: 2018-10-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00147; 2019-02-20: TPSK-LSPA1-T-CV-00188
[6 empty] | Return Date | 2019-02-20: 2018-12-24; 2019-02-20: 2018-11-01
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| CV | OL1-2K43-0004 | SOIL INVESTIGATION LAYOUT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IMP
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-10-08; 2019-02-20: 2018-10-08; 2019-03-29: 2019-12-17
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-10; 2019-02-20: 2018-10-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00145; 2019-02-20: TPSK-LSPA1-T-CV-00163
[6 empty] | Return Date | 2019-02-20: 2018-12-24; 2019-02-20: 2018-12-24
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
Category Code: K50 Concrete Test Results
Category Code: K71 Appraisal Report for Consultancy Service
Category Code: K72 Appraisal Report for EPC Contractor Work
Category Code: K73 Appraisal Report for Vendor/Supplier
Category Code: K90 Vendor Document/drawings
Category Code: K91 Index/List
Category Code: K92 Procedures & Standards
| CV | OL1-2K92-0001 | GENERAL NOTES FOR UNDERGROUND WORKS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-24; 2019-02-20: 2019-02-10
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-25; 2019-02-20: 2019-02-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00086; 2019-02-20: TPSK-LSPA1-T-CV-00784
[6 empty] | Return Date | 2019-02-20: 2018-11-02; 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| CV | OL1-2K92-0002 | GENERAL NOTES FOR PRECAST CONCRETE WORKS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-10-05; 2019-02-20: 2019-01-30
[6 empty] | Revised Plan | 2019-02-20: 2019-06-18
[6 empty] | Issue Actual | 2019-02-20: 2018-10-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00137
[6 empty] | Return Date | 2019-02-20: 2018-12-24
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2K92-0003 | GENERAL NOTES FOR CONCRETE WORKS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-24; 2019-02-20: 2019-01-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-25; 2019-02-20: 2019-02-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00086; 2019-02-20: TPSK-LSPA1-T-CV-00886
[6 empty] | Return Date | 2019-02-20: 2018-11-02; 2019-02-20: 2019-03-27
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| CV | OL1-2K92-0004 | GENERAL NOTES FOR STEEL STRUCTURE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-24; 2019-02-20: 2019-01-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-25; 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00086; 2019-02-20: TPSK-LSPA1-T-CV-00867
[6 empty] | Return Date | 2019-02-20: 2018-11-02; 2019-02-20: 2019-03-27
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| CV | OL1-2K92-0005 | GENERAL NOTES FOR PILES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-04-01
[6 empty] | Revised Plan | 2019-02-20: 2019-06-07
[6 empty] | Issue Actual | 2019-02-20: 2019-03-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01093
[6 empty] | Return Date | 2019-02-20: 2019-04-12
Owner Cmmt* | bar: 2019-02-20
Category Code: K93 Policy , Guidelines & Memo
Category Code: K94 Forms & Templates
Category Code: K95 Progress/Status Reports
Category Code: K97 Technical Specification/Price list for Architectural Works (Nuovo codice richiesto dal Cliente R02)
| CV | OL1-2K97-0001 | JOB CONST.SPEC.FOR BUILDINGS |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-21
[6 empty] | Transmittal no. | 2019-02-20: 1117-TPSK-LSPA1-T-CV-01117
Return Date
Owner Cmmt*
Category Code: L01 Passive & Active Fire Protection Philosophy
| SE | OL1-2L01-0001 | FIREFIGHTING SYSTEM SPECIFICATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-16; 2019-02-20: 2019-02-13
[6 empty] | Revised Plan | 2019-02-20: 2019-05-20
[6 empty] | Issue Actual | 2019-02-20: 2019-02-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00782
[6 empty] | Return Date | 2019-02-20: 2019-03-18
Owner Cmmt* | bar: 2019-02-20
| SE | OL1-2L01-0002 | PASSIVE FIRE PROTECTION SPECIFICATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-18; 2019-02-20: 2019-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
[6 empty] | Issue Actual | 2019-02-20: 2019-01-29
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00749
[6 empty] | Return Date | 2019-02-20: 2019-04-04
Owner Cmmt* | bar: 2019-02-20
| SE | OL1-2L01-0003 | Clean Agent Fire Extinguishing System |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-16; 2019-02-20: 2019-02-13
[6 empty] | Revised Plan | 2019-02-20: 2019-05-20
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01441
Return Date
Owner Cmmt*
Category Code: L02 Active Fire Protection System
Category Code: L03 Firefighting equipment data sheet |  |  |  |  | Class 2 | Purpose**
Category Code: L08 Noise General Specification | [5 empty] | Rev.
Category Code: L09 Noise Map | [5 empty] | Issue Plan
Category Code: L10 Acoustic Calculation Note | [5 empty] | Revised Plan
| SE | OL1-2L10-0001 | PLANT/EQUIPMENT NOISE CONTROL SPECIFICATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-02-04; 2019-02-20: 2019-02-28
[6 empty] | Revised Plan | 2019-02-20: 2019-05-20
[6 empty] | Issue Actual | 2019-02-20: 2018-12-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-00472
Return Date
Owner Cmmt*
| SE | OL1-2L10-0003 | ACUSTIC INSULATION SPECIFICATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-02-04; 2019-02-20: 2019-02-28
[6 empty] | Revised Plan | 2019-02-20: 2019-05-20
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01461
Return Date
Owner Cmmt*
Category Code: L11 Noise Rep
| SE | OL1-2L11-0001 | NOISE STUDY (NOISE MAP) |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-31; 2019-02-20: 2019-09-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L20 Fire system calculation
| SE | OL1-2L20-0001 | FIRE WATER DEMAND CALCULATION AND HYDRAULIC STUDY FOR FW NETWORK |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-17; 2019-02-20: 2020-03-06
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01006
[6 empty] | Return Date | 2019-02-20: 2019-04-09
Owner Cmmt* | bar: 2019-02-20
Category Code: L40 Active Fire Fighting Systems |  |  |  |  | Class 2 | Purpose**
| SE | OL1-2L40-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - SUBSTATION & FAR E |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-1000 | OVERALL FIRE WATER NETWORK DRAWING |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-02-08; 2019-02-20: 2019-05-08
[6 empty] | Revised Plan | 2019-02-20: 2019-05-22
[6 empty] | Issue Actual | 2019-02-20: 2019-03-29
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01198
Return Date
Owner Cmmt*
| SE | OL1-2L40-5701 | P&ID - FIRE WATER NETWORK (1/6) |  | Class As built | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30; 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520; 2019-02-20: TPSK-LSPA1-T-SE-01622
Return Date
Owner Cmmt*
| SE | OL1-2L40-5702 | P&ID - FIRE WATER NETWORK (2/6) |  | Class As built | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30; 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520; 2019-02-20: TPSK-LSPA1-T-SE-01622
Return Date
Owner Cmmt*
| SE | OL1-2L40-5703 | P&ID - FIRE WATER NETWORK (3/6) |  | Class As built | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30; 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520; 2019-02-20: TPSK-LSPA1-T-SE-01622
Return Date
Owner Cmmt*
| SE | OL1-2L40-5704 | P&ID - FIRE WATER NETWORK (4/6) |  | Class As built | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30; 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520; 2019-02-20: TPSK-LSPA1-T-SE-01622
Return Date
Owner Cmmt*
| SE | OL1-2L40-5705 | P&ID - FIRE WATER NETWORK (5/6) |  | Class As built | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30; 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520; 2019-02-20: TPSK-LSPA1-T-SE-01622
Return Date
Owner Cmmt*
| SE | OL1-2L40-5706 | P&ID - FIRE WATER NETWORK (6/6) |  | Class As built | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30; 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520; 2019-02-20: TPSK-LSPA1-T-SE-01622
Return Date
Owner Cmmt*
| SE | OL1-2L40-5707 | P&ID - DRY RISER SYSTEM |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5708 | P&ID - TYPICAL INSTALLATION OF FIRE PROTECTION EQUIPMENT |  | Class As built | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30; 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520; 2019-02-20: TPSK-LSPA1-T-SE-01622
Return Date
Owner Cmmt*
| SE | OL1-2L40-5709 | P&ID - AUTOMATIC PNEUMATIC & ELECTRIC OPERATED DELUGE SYSTEM |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5710 | P&ID - AUTOMATIC ELECTRIC OPERATED DELUGE SYSTEM |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5711 | P&ID - MANUAL ELECTRIC OPERATED DELUGE SYSTEM |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5712 | P&ID - PRE-ACTION DOUBLE INTERLOCK SPRINKLER SYSTEM |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5713 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 0S |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5714 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2A |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5715 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2B |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5716 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2C (1/2) |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5717 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2C (2/2) |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5718 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2D (1/3) |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5719 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2D (2/3) |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5720 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2D (3/3) |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5721 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2E |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5722 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 3A (1/2) |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5723 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 3A (2/2) |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5724 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 3S |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5725 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 5F |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5726 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 5U |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5727 | P&ID - FIRE WATER CURTAIN SYSTEM - ZONE 1B |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5728 | P&ID - SPRINKLER SYSTEM - SUBSTATION E CABLE CELLAR |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5729 | P&ID - SPRINKLER SYSTEM - SUBSTATION C CABLE CELLAR |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
| SE | OL1-2L40-5730 | P&ID - SPRINKLER SYSTEM - SUBSTATION F CABLE CELLAR |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01520
Return Date
Owner Cmmt*
Category Code: L41 Passive Fire Protection Drawings
Category Code: L42 Hazardous Area Classification |  |  |  |  | Class 2 | Purpose**
| SE | OL1-2L42-0001 | Hazardous Area Classification - Overall |  | Class As built | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01015
[6 empty] | Return Date | 2019-02-20: 2019-03-25
Owner Cmmt* | bar: 2019-02-20
| SE | OL1-2L42-0002 | HAZARDOUS AREA CLASSIFICATION DRAWING, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-17; 2019-02-20: 2020-05-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0003 | HAZARDOUS AREA CLASSIFICATION DRAWING |  | Class 2 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-17; 2019-02-20: 2020-05-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0004 | Hazardous Area Classification - Zone 0S - Electrical Substation and Far E |  | Class As built | Purpose** | 2019-02-20: IFA
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01015
[6 empty] | Return Date | 2019-02-20: 2019-03-25
Owner Cmmt* | bar: 2019-02-20
| SE | OL1-2L42-0005 | HAZARDOUS AREA CLASSIFICATION DRAWING - COOLING WATER UNIT |  | Class 2 | Purpose** | 2019-02-20: IFA
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01015
[6 empty] | Return Date | 2019-02-20: 2019-03-25
Owner Cmmt* | bar: 2019-02-20
| SE | OL1-2L42-0006 | HAZARDOUS AREA CLASSIFICATION DRAWING - WASTE WATER TREATMENT UNIT |  | Class 2 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-17; 2019-02-20: 2020-05-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0007 | HAZARDOUS AREA CLASSIFICATION DRAWING - UTILITIES |  | Class 2 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-17; 2019-02-20: 2020-05-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0008 | HAZARDOUS AREA CLASSIFICATION DRAWING - FLARE UNIT |  | Class 2 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-17; 2019-02-20: 2020-05-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0009 | HAZARDOUS AREA CLASSIFICATION DRAWING - METERING STATION |  | Class 2 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-17; 2019-02-20: 2020-05-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0010 | HAZARDOUS AREA CLASSIFICATION DRAWING - FURNACES |  | Class 2 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-17; 2019-02-20: 2020-05-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0011 | HAZARDOUS AREA CLASSIFICATION DRAWING - FURNACES AND AUXILIARIES |  | Class 2 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-17; 2019-02-20: 2020-05-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0012 | HAZARDOUS AREA CLASSIFICATION DRAWING - QUENCH |  | Class 2 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-17; 2019-02-20: 2020-05-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0013 | HAZARDOUS AREA CLASSIFICATION DRAWING - C3 HYDROGENATION |  | Class 2 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-17; 2019-02-20: 2020-05-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0014 | HAZARDOUS AREA CLASSIFICATION DRAWING - PROCESS COLD COMPRESSORS |  | Class 2 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-17; 2019-02-20: 2020-05-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0015 | HAZARDOUS AREA CLASSIFICATION DRAWING - CRACKED GAS COMPRESSOR / DE-PROPANIZER / C2 HYDROGENATION |  | Class 2 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-17; 2019-02-20: 2020-05-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0016 | HAZARDOUS AREA CLASSIFICATION DRAWING - BUTADIENE EXTRACT UNIT |  | Class 2 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-17; 2019-02-20: 2020-05-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0017 | HAZARDOUS AREA CLASSIFICATION DRAWING - HOT FRACTIONATION / GHU UNIT |  | Class 2 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-17; 2019-02-20: 2020-05-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0018 | HAZARDOUS AREA CLASSIFICATION DRAWING |  | Class 2 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-17; 2019-02-20: 2020-05-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0020 | Hazardous Area Classification - Details |  | Class As built | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-01015
[6 empty] | Return Date | 2019-02-20: 2019-03-25
Owner Cmmt* | bar: 2019-02-20
Category Code: L43 Risk Matrix
Category Code: L44 Life saving Equip & Escape Route Drawing
Category Code: L60 All project study and Report pertain to Loss control and Safety Process safety report; HAZOP Report; LOPA Report; PSSR Reports; Risk analysis dossiers; and and Project Response; |  |  |  |  | Class 2 | Purpose**
| SE | OL1-2L60-0001 | HAZARD & OPERABILITY STUDY (FEED) REPORT |  | Class 3 | Purpose** | 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-21
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L60-0051 | MSDS for Chemicals and Catalysts |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-SE-00707
Return Date
Owner Cmmt*
| SE | OL1-2L60-1001 | HAZARD & OPERABILITY STUDY (DETAIL DESIGN) REPORT |  | Class 3 | Purpose** | 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L60-2001 | HAZARD & OPERABILITY STUDY (DETAIL DESIGN) REPORT |  | Class 3 | Purpose** | 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L60-3001 | SIL CLASSIFICATION REPORT |  | Class 2 | Purpose** | 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-10
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L60-4001 | SIL CLASSIFICATION REPORT |  | Class 2 | Purpose** | 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-03-10
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L62 Recommendation Monitoring System
| SE | OL1-2L62-0001 | HAZARD & OPERABILITY STUDY (FEED) CLOSEOUT REPORT |  | Class 2 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-10
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L62-1001 | HAZARD & OPERABILITY STUDY (DETAIL DESIGN) CLOSEOUT REPORT |  | Class 2 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-10
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L62-2001 | HAZARD & OPERABILITY STUDY (DETAIL DESIGN) CLOSEOUT REPORT |  | Class 2 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-10
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L63 Record of Survey
Category Code: L64 Report of audit
Category Code: L65 Hazardous Source Data
Category Code: L66 Register of Safety Devices |  |  |  |  | Class 2 | Purpose**
| SE | OL1-2L66-0001 | BILL OF MATERIAL FOR FIREFIGHTING AND SAFETY EQUIPMENT |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-05; 2019-02-20: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L67 Equipment Failure Information
Category Code: L70 Emergency Procedures Manual
Category Code: L71 Test Procedures
Category Code: L72 Loss Control and Safety procedure
Category Code: L81 Appraisal Report for Consultancy Service
Category Code: L82 Appraisal Report for EPC Contractor Work
Category Code: L83 Appraisal Report for Vendor/Supplier
Category Code: L90 Vendor Document/drawings
Category Code: L91 Index/List
Category Code: L92 Procedures & Standards
Category Code: L93 Policy , Guidelines & Memo
Category Code: L94 Forms & Templates
Category Code: L95 Progress/Status Reports
Category Code: M03 Mechanical datasheet
| ME | OL1-2M03-1000 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-1000 - LPG FEED DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13; 2019-08-06: 2019-04-23
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00483; 2019-08-06: TPSK-LSPA1-T-ME-01448
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-1001 | MECHANICAL DATASHEET FOR API 560 INDUCED DRAFT FAN (36M FURNACE) |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-31; 2019-02-20: 2018-11-05; 2019-03-29: 2019-01-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-31; 2019-08-06: 2019-03-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00247; 2019-08-06: TPSK-LSPA1-T-ME-01021
[6 empty] | Return Date | 2019-08-06: 2019-03-29
Owner Cmmt* | bar: 2019-08-06
| ME | OL1-2M03-1002 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1000 - LPG VAPORIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00684
[6 empty] | Return Date | 2019-03-29: 2019-02-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-1003 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1001 - LPG STEAM VAPORIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-03; 2019-08-06: 2019-02-27
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00573; 2019-08-06: TPSK-LSPA1-T-ME-00946
[6 empty] | Return Date | 2019-03-29: 2019-01-24; 2019-08-06: 2019-03-25
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-1005 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1005 - LPG FEED HEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-03; 2019-08-06: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00573; 2019-08-06: TPSK-LSPA1-T-ME-01230
[6 empty] | Return Date | 2019-03-29: 2019-01-24; 2019-08-06: 2019-05-09
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-1006 | Mechanical Equipment Data Sheet - 10-E-1006 - LPG Feed Steam Heater |  | Class Final | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFQ
Rev. | bar: 2019-02-20 to 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-19; 2019-02-20: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01095; 2019-02-20: TPSK-LSPA1-T-ME-01362
[6 empty] | Return Date | 2019-02-20: 2019-04-11
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M03-1015 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1015 - LPG SUPERHEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-27; 2019-08-06: 2019-03-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00571; 2019-08-06: TPSK-LSPA1-T-ME-00971
[6 empty] | Return Date | 2019-03-29: 2019-01-22; 2019-08-06: 2019-03-29
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-1020 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1020 - LIQUID FEED HEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-17; 2019-08-06: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00671; 2019-08-06: TPSK-LSPA1-T-ME-01230
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-05-09
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-1051 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1050 - C2 FEED SUPERHEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-03; 2019-08-06: 2019-03-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00573; 2019-08-06: TPSK-LSPA1-T-ME-00961
[6 empty] | Return Date | 2019-03-29: 2019-01-24; 2019-08-06: 2019-03-29
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-1105 | API Fired Heater Datasheet 10-H-1100 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-15; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01084; 2019-02-20: TPSK-LSPA1-T-ME-01486
Return Date
Owner Cmmt*
| ME | OL1-2M03-1205 | API Fired Heater Datasheet 10-H-1200_1600 |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-15; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01084; 2019-02-20: TPSK-LSPA1-T-ME-01486
Return Date
Owner Cmmt*
| ME | OL1-2M03-1911 | Mechanical Equipment Data Sheet - DMDS Bulk Storage Drum |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-28; 2019-08-06: 2019-04-12
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00743; 2019-08-06: TPSK-LSPA1-T-ME-01347
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-1912 | Mechanical Equipment Data Sheet - DMDS Injection Drum |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-28; 2019-08-06: 2019-04-12
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00744; 2019-08-06: TPSK-LSPA1-T-ME-01347
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-1913 | Mechanical Equipment Datasheet - DMDS Feed Injection Pump |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2018-12-27; 2019-02-20: 2019-01-17
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-01; 2019-08-06: 2019-03-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00787; 2019-08-06: TPSK-LSPA1-T-ME-01086
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-04-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-1914 | Mechanical Equipment Datasheet - DMDS Presulfiding Injection Pump |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2018-12-27; 2019-02-20: 2019-01-17
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-01; 2019-08-06: 2019-03-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00787; 2019-08-06: TPSK-LSPA1-T-ME-01086
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-04-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-1950 | MECHANICAL EQUIPMENT DATA SHEET - 10-PK-1950 - DECOKE AIR COMPRESSOR PACKAGE |  | Class 1 | Purpose** | IFR | IFA | IFD | IFQ | IFQ
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2018-09-13; 2019-03-29: 2018-10-11
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-13; 2019-08-06: 2018-10-11; 2019-11-11: 2018-11-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00050; 2019-08-06: TPSK-LSPA1-T-ME-00161; 2019-11-11: TPSK-LSPA1-T-ME-00261
[6 empty] | Return Date | 2019-02-20: 2018-10-02; 2019-11-11: 2018-11-29
Owner Cmmt* | bar: 2019-02-20; 2019-11-11
| ME | OL1-2M03-2000 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2000 - QUENCH OIL TOWER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-04; 2019-08-06: 2019-02-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00420; 2019-08-06: TPSK-LSPA1-T-ME-00801
[6 empty] | Return Date | 2019-03-29: 2018-12-27; 2019-08-06: 2019-02-25
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2001 | MECHANICAL DATASHEET FOR API 560 INDUCED DRAFT FAN (132SU FURNACE) |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-31; 2019-02-20: 2018-11-05; 2019-03-29: 2019-01-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-31; 2019-08-06: 2019-03-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00247; 2019-08-06: TPSK-LSPA1-T-ME-01021
[6 empty] | Return Date | 2019-08-06: 2019-03-29
Owner Cmmt* | bar: 2019-08-06
| ME | OL1-2M03-2002 | ELEVATOR DATA SHEET |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-12-19; 2019-02-20: 2018-12-19; 2019-03-29: 2019-02-19
[6 empty] | Revised Plan | 2019-03-29: 2019-05-24
[6 empty] | Issue Actual | 2019-02-20: 2019-01-18
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00681
[6 empty] | Return Date | 2019-02-20: 2019-02-08
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M03-2006 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2006 - QUENCH OIL PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-10-26; 2019-08-06: 2018-12-11; 2019-11-11: 2019-03-27
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00235; 2019-08-06: TPSK-LSPA1-T-ME-00476; 2019-11-11: TPSK-LSPA1-T-ME-01173
[6 empty] | Return Date | 2019-03-29: 2018-11-19; 2019-08-06: 2019-01-16; 2019-11-11: 2019-04-22
Owner Cmmt* | bar: 2019-03-29 to 2019-11-11
| ME | OL1-2M03-2010 | Mechanical Equipment Data sheet - Quench Oil Filter |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-25; 2019-02-20: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00639
[6 empty] | Return Date | 2019-03-29: 2019-01-30
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2014 | Mechanical Equipment Datasheet - QO Pump Purge Oil Filter |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-25; 2019-02-20: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00639
[6 empty] | Return Date | 2019-03-29: 2019-01-30
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2015 | Mechanical Equipment Data Sheet - 10-E-2008 - LS2 Steam Generators |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-14; 2019-08-06: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00643; 2019-08-06: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | 2019-03-29: 2019-02-04; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2020 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2020 - LIGHT FUEL OIL STRIPPER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10; 2019-08-06: 2019-02-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00447; 2019-08-06: TPSK-LSPA1-T-ME-00801
[6 empty] | Return Date | 2019-03-29: 2019-01-27; 2019-08-06: 2019-02-25
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2024 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2026 - LIGHT FUEL OIL PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10; 2019-08-06: 2019-02-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00457; 2019-08-06: TPSK-LSPA1-T-ME-00786
[6 empty] | Return Date | 2019-03-29: 2018-12-27; 2019-08-06: 2019-02-21
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2025 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2026 - CRACKER BOTTOMS PRODUCT FILTER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-25; 2019-02-20: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-03-25
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00639; 2019-08-06: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | 2019-03-29: 2019-01-30; 2019-08-06: 2019-04-11
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2026 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2026 - FUEL OIL PRODUCT COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22; 2019-08-06: 2019-04-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00683; 2019-08-06: TPSK-LSPA1-T-ME-01307
[6 empty] | Return Date | 2019-03-29: 2019-02-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2028 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2028 - FO PUMP PURGE OIL FILTER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-25; 2019-02-20: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-03-25
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00639; 2019-08-06: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | 2019-03-29: 2019-01-30; 2019-08-06: 2019-04-11
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2040 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2040 - HEAVY FUEL OIL STRIPPER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-28; 2019-08-06: 2018-12-05; 2019-11-11: 2019-02-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00387; 2019-08-06: TPSK-LSPA1-T-ME-00418; 2019-11-11: TPSK-LSPA1-T-ME-00815
[6 empty] | Return Date | 2019-03-29: 2018-12-17; 2019-08-06: 2018-12-27; 2019-11-11: 2019-02-21
Owner Cmmt* | bar: 2019-03-29 to 2019-11-11
| ME | OL1-2M03-2046 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2046 - HEAVY FUEL OIL PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10; 2019-08-06: 2019-02-01; 2019-11-11: 2019-04-26
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00457; 2019-08-06: TPSK-LSPA1-T-ME-00786; 2019-11-11: TPSK-LSPA1-T-ME-01493
[6 empty] | Return Date | 2019-03-29: 2018-12-27; 2019-08-06: 2019-02-21
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2048 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2048 - HEAVY FUEL OIL PRODUCT COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22; 2019-08-06: 2019-04-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00683; 2019-08-06: TPSK-LSPA1-T-ME-01324
[6 empty] | Return Date | 2019-03-29: 2019-02-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2049 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2048 - HEAVY FUEL OIL FILTERS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-25; 2019-02-20: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-03-26
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00639; 2019-08-06: TPSK-LSPA1-T-ME-01157
[6 empty] | Return Date | 2019-03-29: 2019-01-30; 2019-08-06: 2019-04-11
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2090 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2090 - QUENCH OIL DRAIN DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-01-21; 2019-02-20: 2019-02-08
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00638; 2019-08-06: TPSK-LSPA1-T-ME -1226
[6 empty] | Return Date | 2019-03-29: 2019-01-31
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2091 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2090 - QUENCH OIL DRAIN DRUM PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13; 2019-08-06: 2019-04-02; 2019-11-11: 2019-04-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00494; 2019-08-06: TPSK-LSPA1-T-ME-01227; 2019-11-11: TPSK-LSPA1-T-ME-01363
[6 empty] | Return Date | 2019-03-29: 2019-01-14
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2100 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2100 - QUENCH WATER TOWER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-07; 2019-08-06: 2019-02-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00443; 2019-08-06: TPSK-LSPA1-T-ME -00803
[6 empty] | Return Date | 2019-03-29: 2018-12-27; 2019-08-06: 2019-02-25
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2101 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2100 - QUENCH WATER COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFQ
Rev. | bar: 2019-02-20; 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2018-10-20; 2019-03-29: 2018-10-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-17; 2019-08-06: 2018-10-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00058; 2019-08-06: TPSK-LSPA1-T-ME-00154
[6 empty] | Return Date | 2019-02-20: 2018-09-28; 2019-08-06: 2018-11-07
Owner Cmmt* | bar: 2019-02-20; 2019-08-06
| ME | OL1-2M03-2104 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2105 - QUENCH OIL REFLUX FILTER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-25; 2019-02-20: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-03-25
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00639; 2019-08-06: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | 2019-03-29: 2019-01-30; 2019-08-06: 2019-04-11
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2105 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2105 - QUENCH OIL REFLUX PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10; 2019-08-06: 2019-04-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00457; 2019-08-06: TPSK-LSPA1-T-ME-01279
[6 empty] | Return Date | 2019-03-29: 2018-12-27
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2106 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2106 - QUENCH WATER PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-10-27; 2019-08-06: 2018-12-11; 2019-11-11: 2019-03-27
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00236; 2019-08-06: TPSK-LSPA1-T-ME-00476; 2019-11-11: TPSK-LSPA1-T-ME-01173
[6 empty] | Return Date | 2019-03-29: 2018-11-19; 2019-08-06: 2019-01-16; 2019-11-11: 2019-04-22
Owner Cmmt* | bar: 2019-03-29 to 2019-11-11
| ME | OL1-2M03-2110 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2110 - INTERCEPTION DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00685
[6 empty] | Return Date | 2019-03-29: 2019-02-15
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2120 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2120 - DISTILLTATE STRIPPER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-20; 2019-08-06: 2019-02-12
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00546; 2019-08-06: TPSK-LSPA1-T-ME-00840
[6 empty] | Return Date | 2019-03-29: 2019-01-22; 2019-08-06: 2019-02-28
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2125 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2125 - DISTILLATE STRIPPER REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-07; 2019-08-06: 2019-04-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00584; 2019-08-06: TPSK-LSPA1-T-ME-01302
[6 empty] | Return Date | 2019-03-29: 2019-01-24
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2126 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2126 - DISTILLATE STRIPPER BOTTOMS PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-05; 2019-08-06: 2019-03-20; 2019-11-11: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00410; 2019-08-06: TPSK-LSPA1-T-ME-01102; 2019-11-11: TPSK-LSPA1-T-ME-01426
[6 empty] | Return Date | 2019-03-29: 2018-12-27; 2019-08-06: 2019-04-10
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2137 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2136 - PROCESS WATER STRIPPER FEED HEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-03; 2019-08-06: 2019-04-04
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00573; 2019-08-06: TPSK-LSPA1-T-ME -01251
[6 empty] | Return Date | 2019-03-29: 2019-01-24
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2138 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2136 - PROCESS WATER FEED FILTER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-25; 2019-02-20: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-03-25
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00639; 2019-08-06: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | 2019-03-29: 2019-01-30; 2019-08-06: 2019-04-11
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2139 | Mechanical Equipment Datasheet - Process Water Coalescer Prefilters |  | Class Final | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10; 2019-02-20: 2019-05-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01641; 2019-02-20: TPSK-LSPA1-T-ME-01669
Return Date
Owner Cmmt*
| ME | OL1-2M03-2140 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2140 - PROCESS WATER STRIPPER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10; 2019-08-06: 2019-02-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00458; 2019-08-06: TPSK-LSPA1-T-ME-00801
[6 empty] | Return Date | 2019-03-29: 2018-12-27; 2019-08-06: 2019-02-25
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2145 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2145 - PROCESS WATER STRIPPER REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22; 2019-08-06: 2019-04-16
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00684; 2019-08-06: TPSK-LSPA1-T-ME-01357
[6 empty] | Return Date | 2019-03-29: 2019-02-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2146 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2146 - DSG FEED PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-10-26; 2019-08-06: 2018-12-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00235; 2019-08-06: TPSK-LSPA1-T-ME-00476
[6 empty] | Return Date | 2019-03-29: 2018-11-19; 2019-08-06: 2019-01-16
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2147 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2146 - DSG FEED HEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-14; 2019-08-06: 2019-04-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00650; 2019-08-06: TPSK-LSPA1-T-ME-01302
[6 empty] | Return Date | 2019-03-29: 2019-01-31
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2160 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2160 - DILUTION STEAM GENERATOR |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-01-21; 2019-02-20: 2019-02-08
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00483
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2161 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2160 - DILUTION STEAM SUPERHEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00641; 2019-08-06: TPSK-LSPA1-T-ME-01230
[6 empty] | Return Date | 2019-03-29: 2019-02-04; 2019-08-06: 2019-05-09
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2165 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2165 - DSG REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-03; 2019-08-06: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00582; 2019-08-06: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | 2019-03-29: 2019-01-24; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2166 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2166 - DSG BLOWDOWN COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22; 2019-08-06: 2019-04-03
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00684; 2019-08-06: TPSK-LSPA1-T-ME-01248
[6 empty] | Return Date | 2019-03-29: 2019-02-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2190 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2190 - QUENCH WATER DRAIN DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00638; 2019-08-06: TPSK-LSPA1-T-ME -1226
[6 empty] | Return Date | 2019-03-29: 2019-01-31
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2191 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2190 - QUENCH WATER DRAIN DRUM PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00400
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2200 | MECHANICAL EQUIPMENT DATA SHEET - 10-C-2200 - CRACKED GAS COMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | IFD | IFQ | IFQ
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2018-09-13; 2019-03-29: 2018-10-04
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-10; 2019-08-06: 2018-10-03; 2019-11-11: 2018-11-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00038; 2019-08-06: TPSK-LSPA1-T-ME-00127; 2019-11-11: TPSK-LSPA1-T-ME-00280
[6 empty] | Return Date | 2019-02-20: 2018-09-28; 2019-11-11: 2018-11-30
Owner Cmmt* | bar: 2019-02-20; 2019-11-11
| ME | OL1-2M03-2206 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2206 - WASH WATER COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-07; 2019-08-06: 2019-03-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00584; 2019-08-06: TPSK-LSPA1-T-ME-01110
[6 empty] | Return Date | 2019-03-29: 2019-01-24; 2019-08-06: 2019-04-11
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2210 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2210 - CG 1ST STAGE SUCTION DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22; 2019-08-06: 2019-04-23
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00685; 2019-08-06: TPSK-LSPA1-T-ME-01448
[6 empty] | Return Date | 2019-03-29: 2019-02-15
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2211 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2210 - CG 1ST STAGE AFTERCOOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22; 2019-08-06: 2019-03-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00683; 2019-08-06: TPSK-LSPA1-T-ME-01110
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-04-11
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2212 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2210 - CG 1ST STAGE CONDENSATE PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-05
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00413
[6 empty] | Return Date | 2019-03-29: 2018-12-27
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2220 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2220 - CG 2ND STAGE SUCTION DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13; 2019-08-06: 2019-03-28
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00483; 2019-08-06: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | 2019-03-29: 2019-01-22; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2221 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2220 - CG 2ND STAGE AFTERCOOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-07; 2019-08-06: 2019-03-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00588; 2019-08-06: TPSK-LSPA1-T-ME-01110
[6 empty] | Return Date | 2019-03-29: 2019-01-30; 2019-08-06: 2019-04-11
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2222 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2220 - CG 2ND STAGE CONDENSED HC PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00343
[6 empty] | Return Date | 2019-03-29: 2019-02-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2230 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2230 - CG 3RD STAGE SUCTION DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13; 2019-08-06: 2019-03-28
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00483; 2019-08-06: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | 2019-03-29: 2019-01-22; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2231 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2230 - CG 3RD STAGE AFTERCOOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-07; 2019-08-06: 2019-03-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00588; 2019-08-06: TPSK-LSPA1-T-ME-01110
[6 empty] | Return Date | 2019-03-29: 2019-01-30; 2019-08-06: 2019-04-11
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2240 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2240 - CG 4TH STAGE SUCTION DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13; 2019-08-06: 2019-03-28
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00483; 2019-08-06: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | 2019-03-29: 2019-01-22; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2241 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2240 - CG 4TH STAGE AFTERCOOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-10; 2019-08-06: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00617; 2019-08-06: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | 2019-03-29: 2019-01-29; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2245 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2245 - CG 4TH STAGE DISCHARGE DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-16; 2019-08-06: 2019-04-12
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00657; 2019-08-06: TPSK-LSPA1-T-ME-01347
[6 empty] | Return Date | 2019-03-29: 2019-02-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2300 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2300 - CAUSTIC TOWER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-10-31; 2019-08-06: 2018-12-05; 2019-11-11: 2019-02-19
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00246; 2019-08-06: TPSK-LSPA1-T-ME-00419; 2019-11-11: TPSK-LSPA1-T-ME -00883
[6 empty] | Return Date | 2019-03-29: 2018-11-27; 2019-08-06: 2018-12-27; 2019-11-11: 2019-03-12
Owner Cmmt* | bar: 2019-03-29 to 2019-11-11
| ME | OL1-2M03-2302 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2302 - STRONG CAUSTIC CIRCULATING PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00320
[6 empty] | Return Date | 2019-03-29: 2018-12-10
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2304 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2304 - INTERMEDIATE CAUSTIC CIRCULATING PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-15; 2019-08-06: 2018-12-05
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00320; 2019-08-06: TPSK-LSPA1-T-ME-00411
[6 empty] | Return Date | 2019-03-29: 2018-12-10; 2019-08-06: 2018-12-27
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2305 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2305 - CAUSTIC TOWER FEED HEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-10; 2019-08-06: 2019-04-26
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00617; 2019-08-06: TPSK-LSPA1-T-ME-01503
[6 empty] | Return Date | 2019-03-29: 2019-01-29
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2306 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2306 - WEAK CAUSTIC CIRCULATING PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-15; 2019-08-06: 2018-12-05
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00320; 2019-08-06: TPSK-LSPA1-T-ME-00411
[6 empty] | Return Date | 2019-03-29: 2018-12-10; 2019-08-06: 2018-12-27
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2307 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2306 - WEAK CAUSTIC STRAINER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-25; 2019-02-20: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-03-25
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00639; 2019-08-06: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | 2019-03-29: 2019-01-30; 2019-08-06: 2019-04-11
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2309 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2305 - YELLOW OIL DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13; 2019-08-06: 2019-05-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00484; 2019-08-06: TPSK-LSPA1-T-ME-01571
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2310 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2310 - SPENT CAUSTIC DEOILING DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-17; 2019-08-06: 2019-04-23
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00513; 2019-08-06: TPSK-LSPA1-T-ME-01448
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2311 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2310 - WASH OIL CIRCULATING PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00320
[6 empty] | Return Date | 2019-03-29: 2018-12-10
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2314 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2310 - WASH OIL CIRCULATION FILTER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-25; 2019-02-20: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00639
[6 empty] | Return Date | 2019-03-29: 2019-01-30
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2316 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2316 - SPENT CAUSTIC DEGASSING DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-07
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00601
[6 empty] | Return Date | 2019-03-29: 2019-01-30
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2319 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2320 - SPENT CAUSTIC PUMP DISCHARGE FILTER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-25; 2019-02-20: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00639
[6 empty] | Return Date | 2019-03-29: 2019-01-30
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2320 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-2320 - SPENT CAUSTIC STORAGE TANK |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-18; 2019-02-20: 2019-02-26
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-28
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00745
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2321 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2320 - SPENT CAUSTIC PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-19
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00335
[6 empty] | Return Date | 2019-03-29: 2018-12-13
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2322 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2322 - SKIM OIL DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00483
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2324 | Mechanical Equipment Data Sheet - Fresh Caustic Day Tank |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-18; 2019-02-20: 2019-02-26
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-28
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00745
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2325 | Mechanical Equipment Datasheet - 10 percent Caustic Makeup Pumps |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-03; 2019-08-06: 2019-02-07
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00580; 2019-08-06: TPSK-LSPA1-T-ME-00822
[6 empty] | Return Date | 2019-03-29: 2019-01-24; 2019-08-06: 2019-02-21
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2326 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2326 - SPENT CAUSTIC STRIPPER FEED HEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-01-29; 2019-02-20: 2019-01-29
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-28
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00740
[6 empty] | Return Date | 2019-03-29: 2019-02-28
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2327 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2326 - SPENT CAUSTIC STRIPPER FEED HTR COND POT |  | Class 1 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01524
Return Date
Owner Cmmt*
| ME | OL1-2M03-2330 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2330 - SPENT CAUSTIC STRIPPER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10; 2019-08-06: 2019-02-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00462; 2019-08-06: TPSK-LSPA1-T-ME-00857
[6 empty] | Return Date | 2019-03-29: 2018-12-27; 2019-08-06: 2019-03-12
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2331 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2330 - SPENT CAUSTIC STRIPPER OVERHEAD DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-05-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00638; 2019-08-06: TPSK-LSPA1-T-ME-01536
[6 empty] | Return Date | 2019-03-29: 2019-01-31
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2350 | Mechanical Equipment Datasheet for Wet Air Oxidation Package |  | Class Final | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-29; 2019-02-20: 2019-05-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00390; 2019-02-20: TPSK-LSPA1-T-PL-01611
[6 empty] | Return Date | 2019-02-20: 2019-02-07
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M03-2390 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2390 - CAUSTIC DRAIN DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-17; 2019-08-06: 2019-03-28
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00514; 2019-08-06: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | 2019-03-29: 2019-01-22; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2391 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2390 - CAUSTIC DRAIN DRUM PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-17; 2019-08-06: 2019-02-07
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00511; 2019-08-06: TPSK-LSPA1-T-ME-00822
[6 empty] | Return Date | 2019-03-29: 2019-01-14; 2019-08-06: 2019-02-21
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2392 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2392 - SPENT CAUSTIC DRAIN DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22; 2019-08-06: 2019-04-03
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00685; 2019-08-06: TPSK-LSPA1-T-ME-01244
[6 empty] | Return Date | 2019-03-29: 2019-02-15
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2393 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2392 - SPENT CAUSTIC DRAIN DRUM PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00457
[6 empty] | Return Date | 2019-03-29: 2018-12-27
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2405 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2405 - GAS DRYER FEED KO DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-04-30
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00629; 2019-08-06: TPSK-LSPA1-T-ME-01533
[6 empty] | Return Date | 2019-03-29: 2019-01-31
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2406 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2405 - GAS DRYER FEED CHILLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-07; 2019-08-06: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00584; 2019-08-06: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | 2019-03-29: 2019-01-24; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2410 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2410 - CRACKED GAS DRYER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C; 2020-02-07: D
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22; 2019-08-06: 2019-03-01; 2019-11-11: 2019-03-11; 2020-02-07: 2019-04-12
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00700; 2019-08-06: TPSK-LSPA1-T-ME-00972; 2019-11-11: TPSK-LSPA1-T-ME-01016; 2020-02-07: TPSK-LSPA1-T-ME-01347
[6 empty] | Return Date | 2019-03-29: 2019-04-01; 2019-08-06: 2019-03-29; 2019-11-11: 2019-04-02
Owner Cmmt* | bar: 2019-03-29 to 2019-11-11
| ME | OL1-2M03-2411 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2411 - CRACKED GAS MERCURY ADSORBER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-02-28; 2019-11-11: 2019-04-16
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00631; 2019-08-06: TPSK-LSPA1-T-ME-00954; 2019-11-11: TPSK-LSPA1-T-ME-01378
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-03-25
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2412 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2412 - HP DEPROPANIZER FEED CHILLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-10; 2019-08-06: 2019-03-27
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00617; 2019-08-06: TPSK-LSPA1-T-ME-01179
[6 empty] | Return Date | 2019-03-29: 2019-01-29; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2413 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2413 - HP DEPROP FEED / OVERHEAD EXCHANGER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-02-20; 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-10; 2019-03-29: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00617; 2019-03-29: TPSK-LSPA1-T-ME-01179
[6 empty] | Return Date | 2019-02-20: 2019-02-11; 2019-03-29: 2019-05-02
Owner Cmmt* | bar: 2019-02-20; 2019-03-29
| ME | OL1-2M03-2416 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2415 - CG LIQUID DRYER FEED PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-05; 2019-08-06: 2019-01-30
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00413; 2019-08-06: TPSK-LSPA1-T-ME-00770
[6 empty] | Return Date | 2019-03-29: 2018-12-27; 2019-08-06: 2019-02-21
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2420 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2420 - CG LIQUID DRYER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22; 2019-08-06: 2019-02-28; 2019-11-11: 2019-04-16
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00702; 2019-08-06: TPSK-LSPA1-T-ME-00950; 2019-11-11: TPSK-LSPA1-T-ME-01378
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-04-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2430 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2430 - REGEN GAS FEED HEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-28; 2019-08-06: 2019-04-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00740; 2019-08-06: TPSK-LSPA1-T-ME-01315
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2432 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2432 - REGEN GAS SHP HEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-01-29; 2019-02-20: 2019-01-29
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00751
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2434 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2435 - REGEN GAS EFFLUENT COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-25; 2019-08-06: 2019-04-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00723; 2019-08-06: TPSK-LSPA1-T-ME-01218
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-05-09
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2435 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2435 - REGEN GAS SEPARATOR |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00685
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2438 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2440 - HP DEPROPANIZER REFLUX DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13; 2019-08-06: 2019-04-16
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00484; 2019-08-06: TPSK-LSPA1-T-ME-01378
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2439 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2440 - HP DEPROPANIZER CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22; 2019-08-06: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00683; 2019-08-06: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2440 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2440 - HP DEPROPANIZER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-10-23; 2019-08-06: 2018-12-05; 2019-11-11: 2019-02-19
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00215; 2019-08-06: TPSK-LSPA1-T-ME-00416; 2019-11-11: TPSK-LSPA1-T-ME-00884
[6 empty] | Return Date | 2019-03-29: 2018-12-17; 2019-08-06: 2018-12-27; 2019-11-11: 2019-03-12
Owner Cmmt* | bar: 2019-03-29 to 2019-11-11
| ME | OL1-2M03-2441 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2441 - HP DEPROP REFLUX CHILLER NO. 2 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-16; 2019-08-06: 2019-04-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00663; 2019-08-06: TPSK-LSPA1-T-ME -01216
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-05-09
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2442 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2442 - HP DEPROP REFLUX CHILLER NO. 1 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-16; 2019-08-06: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00662; 2019-08-06: TPSK-LSPA1-T-ME-01231
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-05-09
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2443 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2445 - HP DEPROPANIZER COND PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13; 2019-08-06: 2019-01-30
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00494; 2019-08-06: TPSK-LSPA1-T-ME-00770
[6 empty] | Return Date | 2019-03-29: 2019-01-14; 2019-08-06: 2019-02-21
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2444 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2445 - HP DEPROP REBOILER COND POT |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-04-10; 2019-11-11: 2019-05-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00629; 2019-08-06: TPSK-LSPA1-T-ME -01314; 2019-11-11: TPSK-LSPA1-T-ME-01670
[6 empty] | Return Date | 2019-03-29: 2019-01-31
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2445 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2445 - HP DEPROPANIZER REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-17; 2019-08-06: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00671; 2019-08-06: TPSK-LSPA1-T-ME-01231
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-05-09
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2446 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2446 - LP DEPROPANIZER FEED COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-27; 2019-08-06: 2019-04-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00565; 2019-08-06: TPSK-LSPA1-T-ME-01218
[6 empty] | Return Date | 2019-03-29: 2019-01-22; 2019-08-06: 2019-05-09
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2450 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2450 - LP DEPROPANIZER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C; 2020-02-07: D
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-10-16; 2019-08-06: 2018-11-06; 2019-11-11: 2018-12-05; 2020-02-07: 2019-02-19
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00183; 2019-08-06: TPSK-LSPA1-T-ME-00283; 2019-11-11: TPSK-LSPA1-T-ME-00412; 2020-02-07: TPSK-LSPA1-T-ME-00884
[6 empty] | Return Date | 2019-03-29: 2018-11-05; 2019-08-06: 2018-11-30; 2019-11-11: 2018-12-27; 2020-02-07: 2019-03-12
[6 empty] | Owner Cmmt* | 2019-03-29: A3; 2019-08-06: R1; 2019-11-11: R2; 2020-02-07: R2
| ME | OL1-2M03-2451 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2450 - LP DEPROPANIZER CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-07; 2019-08-06: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00588; 2019-08-06: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | 2019-03-29: 2019-01-30; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2452 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2450 - LP DEPROPANIZER REFLUX DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-17; 2019-08-06: 2019-04-30
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00516; 2019-08-06: TPSK-LSPA1-T-ME-01533
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2453 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2450 - LP DEPROPANIZER REFLUX / PRODUCT PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-08; 2019-08-06: 2019-02-27
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00294; 2019-08-06: TPSK-LSPA1-T-ME-00944
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-03-12
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2455 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2455 - LP DEPROPANIZER REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-07; 2019-08-06: 2019-03-27
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00584; 2019-08-06: TPSK-LSPA1-T-ME-01179
[6 empty] | Return Date | 2019-03-29: 2019-01-24; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2456 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2455 - LP DEPROP REBOILER COND POT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00685
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2457 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2455 - LP DEPROPANIZER COND PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13; 2019-08-06: 2019-01-30
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00494; 2019-08-06: TPSK-LSPA1-T-ME-00770
[6 empty] | Return Date | 2019-03-29: 2019-01-14; 2019-08-06: 2019-02-21
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2460 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2460 - C2 HYDROG ARSINE GUARD BED |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-16; 2019-08-06: 2019-02-15; 2019-11-11: 2019-04-16
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00657; 2019-08-06: TPSK-LSPA1-T-ME -00858; 2019-11-11: TPSK-LSPA1-T-ME-01378
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-03-12
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2461 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2460 - C2 HYDROG FEED COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-03; 2019-08-06: 2019-03-27
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00573; 2019-08-06: TPSK-LSPA1-T-ME-01179
[6 empty] | Return Date | 2019-03-29: 2019-01-24; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2465 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2465 - C2 HYDROG FEED HEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00641; 2019-08-06: TPSK-LSPA1-T-ME-01230
[6 empty] | Return Date | 2019-03-29: 2019-02-04; 2019-08-06: 2019-05-09
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2470 | MECHANICAL EQUIPMENT DATA SHEET - 10-R-2470 - C2 HYDROG REACTOR |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-02-16; 2019-02-20: 2019-02-16
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-02-28; 2019-11-11: 2019-04-16
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00630; 2019-08-06: TPSK-LSPA1-T-ME-00953; 2019-11-11: TPSK-LSPA1-T-ME-01379
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-03-25
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2471 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2470 - C2 HYDROG 1ST STAGE INTERCOOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00641; 2019-08-06: TPSK-LSPA1-T-ME-01231
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-05-09
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2472 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2472 - C2 HYDROG 2ND STAGE INTERCOOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00641; 2019-08-06: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | 2019-03-29: 2019-02-04; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2474 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2474 - C2 HYDROG AFTERCOOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00641; 2019-08-06: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | 2019-03-29: 2019-02-04; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2480 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2480 - CG SECONDARY DRYER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22; 2019-08-06: 2019-02-28; 2019-11-11: 2019-04-16
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00702; 2019-08-06: TPSK-LSPA1-T-ME-00954; 2019-11-11: TPSK-LSPA1-T-ME-01378
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-03-25
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2502 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2502 - DEMETH PREFRAC FEED COOLER NO. 1 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10; 2019-08-06: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00461; 2019-08-06: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | 2019-03-29: 2018-12-27; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2503 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2504 - DEMETH PREFRAC FEED COOLER NO. 2 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-28; 2019-08-06: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00389; 2019-08-06: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | 2019-03-29: 2018-12-13; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2504 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2504 - DEMETH PREFRAC FEED SEPARATOR NO. 1 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13; 2019-08-06: 2019-04-30
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00483; 2019-08-06: TPSK-LPSA1-T-ME-01534
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2506 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2506 - DEMETH PREFRAC FEED SEPARATOR NO. 2 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-20; 2019-08-06: 2019-05-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00551; 2019-08-06: TPSK-LSPA1-T-ME-01583
[6 empty] | Return Date | 2019-03-29: 2019-01-24
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2508 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2508 - DEMETH PREFRAC FEED SEPARATOR NO. 3 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-20; 2019-08-06: 2019-05-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00551; 2019-08-06: TPSK-LSPA1-T-ME-01583
[6 empty] | Return Date | 2019-03-29: 2019-01-24
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2510 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2510 - DEMETHANIZER PREFRACTIONATOR |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-10-31; 2019-08-06: 2018-12-05; 2019-11-11: 2019-03-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00260; 2019-08-06: TPSK-LSPA1-T-ME-00414; 2019-11-11: TPSK-LSPA1-T-ME-00970
[6 empty] | Return Date | 2019-03-29: 2018-11-29; 2019-08-06: 2018-12-27; 2019-11-11: 2019-03-29
Owner Cmmt* | bar: 2019-03-29 to 2019-11-11
| ME | OL1-2M03-2515 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2515 - DEMETH PREFRACTIONATOR REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-03; 2019-08-06: 2019-03-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00573; 2019-08-06: TPSK-LSPA1-T-ME-00971
[6 empty] | Return Date | 2019-03-29: 2019-01-24; 2019-08-06: 2019-03-29
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2520 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2520 - RESIDUE GAS RECTIFIER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-20; 2019-08-06: 2019-02-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00534; 2019-08-06: TPSK-LSPA1-T-ME-00792
[6 empty] | Return Date | 2019-03-29: 2019-01-22; 2019-08-06: 2019-02-21
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2525 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2525 - HYDROGEN DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-16; 2019-08-06: 2019-05-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00657; 2019-08-06: TPSK-LSPA1-T-ME-01583
[6 empty] | Return Date | 2019-03-29: 2019-02-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2540 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2540 - DEMETHANIZER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-09; 2019-08-06: 2018-12-05; 2019-11-11: 2019-02-27
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00304; 2019-08-06: TPSK-LSPA1-T-ME-00415; 2019-11-11: TPSK-LSPA1-T-ME-00945
[6 empty] | Return Date | 2019-03-29: 2018-12-10; 2019-08-06: 2018-12-27; 2019-11-11: 2019-03-25
Owner Cmmt* | bar: 2019-03-29 to 2019-11-11
| ME | OL1-2M03-2545 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2545 - DEMETHANIZER REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-14; 2019-08-06: 2019-03-21
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00651; 2019-08-06: TPSK-LSPA1-T-ME-01123
[6 empty] | Return Date | 2019-03-29: 2019-01-31; 2019-08-06: 2019-04-11
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2546 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2546 - DEMETHANIZER BOTTOMS COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-16; 2019-08-06: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00654; 2019-08-06: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | 2019-03-29: 2019-01-31; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2548 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2548 - DEMETHANIZER BOTTOMS VAPORIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-10; 2019-08-06: 2019-03-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00617; 2019-08-06: TPSK-LSPA1-T-ME-00961
[6 empty] | Return Date | 2019-03-29: 2019-01-29; 2019-08-06: 2019-03-29
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2550 | MECHANICAL EQUIPMENT DATA SHEET - 10-C-2550 - RESIDUE GAS EXPANDER / RECOMPRESSOR |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFQ
Rev. | bar: 2019-02-20; 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2018-09-13; 2019-03-29: 2018-10-04
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-13; 2019-08-06: 2018-10-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00050; 2019-08-06: TPSK-LSPA1-T-ME-00130
[6 empty] | Return Date | 2019-02-20: 2018-10-02; 2019-08-06: 2018-10-26
Owner Cmmt* | bar: 2019-02-20; 2019-08-06
| ME | OL1-2M03-2551 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2550 - EXPANDER SUCTION DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00551
[6 empty] | Return Date | 2019-03-29: 2019-01-24
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2555 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2555 - EXPANDER DISCHARGE DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00607
[6 empty] | Return Date | 2019-03-29: 2019-01-28
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2570 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2570 - DEETHANIZER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-29; 2019-08-06: 2018-12-20; 2019-11-11: 2019-02-26
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00394; 2019-08-06: TPSK-LSPA1-T-ME-00547; 2019-11-11: TPSK-LSPA1-T-ME-00931
[6 empty] | Return Date | 2019-03-29: 2018-12-27; 2019-08-06: 2019-01-22; 2019-11-11: 2019-03-15
Owner Cmmt* | bar: 2019-03-29 to 2019-11-11
| ME | OL1-2M03-2571 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2570 - DEETHANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-13; 2019-08-06: 2019-01-30; 2019-11-11: 2019-04-03
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00310; 2019-08-06: TPSK-LSPA1-T-ME-00773; 2019-11-11: TPSK-LSPA1-T-ME-01245
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-02-26
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2572 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2570 - DEETHANIZER REFLUX DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00484
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2573 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2570 - DEETHANIZER REFLUX PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00552
[6 empty] | Return Date | 2019-03-29: 2019-01-16
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2574 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2575 - DEETHANIZER REBOILER COND POT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00685
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2575 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2575 - DEETHANIZER REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22; 2019-08-06: 2019-03-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00684; 2019-08-06: TPSK-LSPA1-T-ME-00961
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-03-29
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2576 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2576 - DEETHANIZER BOTTOMS COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-03; 2019-08-06: 2019-03-21
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00582; 2019-08-06: TPSK-LSPA1-T-ME-01123
[6 empty] | Return Date | 2019-03-29: 2019-01-24; 2019-08-06: 2019-04-11
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2577 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2575 - DEETHANIZER REBOILER COND PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00494
[6 empty] | Return Date | 2019-03-29: 2019-01-14
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2580 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2580 - C2 TOWER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-20; 2019-08-06: 2019-03-04
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00531; 2019-08-06: TPSK-LSPA1-T-ME-00981
[6 empty] | Return Date | 2019-03-29: 2019-01-22; 2019-08-06: 2019-03-29
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2582 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2582 - C2 TOWER REFLUX COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-16; 2019-08-06: 2019-02-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00661; 2019-08-06: TPSK-LSPA1-T-ME-00859
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-03-12
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2586 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2586 - ETHANE RECYCLE PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-05
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00413
[6 empty] | Return Date | 2019-03-29: 2018-12-27
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2600 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2600 - C3 HYDROG GUARD ADSORBER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C; 2020-02-07: D
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-17; 2019-08-06: 2019-01-22; 2019-11-11: 2019-02-28; 2020-02-07: 2019-04-16
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00672; 2019-08-06: TPSK-LSPA1-T-ME -00701; 2019-11-11: TPSK-LSPA1-T-ME-00954; 2020-02-07: TPSK-LSPA1-T-ME -01381
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-02-21; 2019-11-11: 2019-03-25
Owner Cmmt* | bar: 2019-03-29 to 2019-11-11
| ME | OL1-2M03-2610 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2610 - C3 HYDROG ARSINE GUARD BED |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C; 2020-02-07: D
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-27; 2019-08-06: 2019-01-16; 2019-11-11: 2019-02-28; 2020-02-07: 2019-04-16
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00570; 2019-08-06: TPSK-LSPA1-T-ME-00658; 2019-11-11: TPSK-LSPA1-T-ME-00950; 2020-02-07: TPSK-LSPA1-T-ME-01381
[6 empty] | Return Date | 2019-03-29: 2019-01-24; 2019-08-06: 2019-02-11; 2019-11-11: 2019-04-01
Owner Cmmt* | bar: 2019-03-29 to 2019-11-11
| ME | OL1-2M03-2620 | MECHANICAL EQUIPMENT DATA SHEET - 10-R-2620 - C3 HYDROG REACTOR |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-02-16; 2019-02-20: 2019-02-16
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-06; 2019-08-06: 2019-03-05; 2019-11-11: 2019-04-12
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00802; 2019-08-06: TPSK-LSPA1-T-ME-00990; 2019-11-11: TPSK-LSPA1-T-ME-01346
[6 empty] | Return Date | 2019-03-29: 2019-02-26; 2019-08-06: 2019-03-29
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2621 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2620 - C3 HYDROG AFTERCOOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-25; 2019-08-06: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00929; 2019-08-06: TPSK-LSPA1-T-ME-01233
[6 empty] | Return Date | 2019-03-29: 2019-03-15; 2019-08-06: 2019-05-09
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2622 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2620 - C3 HYDROG RECYCLE DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00685
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2623 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2620 - C3 HYDROG RECYCLE PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-24; 2019-08-06: 2019-03-26
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00716; 2019-08-06: TPSK-LSPA1-T-ME-01158
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-04-10
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2630 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2630 - SECONDARY DEETHANIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10; 2019-08-06: 2019-03-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00458; 2019-08-06: TPSK-LSPA1-T-ME-00974
[6 empty] | Return Date | 2019-03-29: 2018-12-27; 2019-08-06: 2019-03-29
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2631 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2630 - SECONDARY DEETH CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10; 2019-08-06: 2019-04-03
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00455; 2019-08-06: TPSK-LSPA1-T-ME-01243
[6 empty] | Return Date | 2019-03-29: 2018-12-27
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2632 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2630 - SECONDARY DEETH REFLUX DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-04-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00629; 2019-08-06: TPSK-LSPA1-T-ME -01314
[6 empty] | Return Date | 2019-03-29: 2019-01-31
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2633 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2630 - SECONDARY DEETH REFLUX PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13; 2019-08-06: 2018-12-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00487; 2019-08-06: TPSK-LSPA1-T-ME-00554
[6 empty] | Return Date | 2019-03-29: 2019-01-16; 2019-08-06: 2019-01-16
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2635 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2635 - SECONDARY DEETH REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-03; 2019-08-06: 2019-04-30
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00582; 2019-08-06: TPSK-LSPA1-T-ME-01532
[6 empty] | Return Date | 2019-03-29: 2019-01-24
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2636 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2636 - SECONDARY DEETH BOTTOMS COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10; 2019-08-06: 2019-04-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00465; 2019-08-06: TPSK-LSPA1-T-ME -01313
[6 empty] | Return Date | 2019-03-29: 2018-12-27
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2640 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2640 - C3 TOWER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-05; 2019-08-06: 2019-02-19; 2019-11-11: 2019-03-04
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00415; 2019-08-06: TPSK-LSPA1-T-ME-00885; 2019-11-11: TPSK-LSPA1-T-ME-00981
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-03-12; 2019-11-11: 2019-03-29
Owner Cmmt* | bar: 2019-03-29 to 2019-11-11
| ME | OL1-2M03-2644 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2645 - C3 TOWER REBOILER COND POT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00753
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2645 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2645 - C3 TOWER REBOILER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-26; 2019-08-06: 2019-01-30; 2019-11-11: 2019-04-09
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00361; 2019-08-06: TPSK-LSPA1-T-ME-00773; 2019-11-11: TPSK-LSPA1-T-ME-01286
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-02-26
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2646 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2646 - PROPANE RECYCLE PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00543
[6 empty] | Return Date | 2019-03-29: 2019-01-16
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2647 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2647 - HP PROPYLENE / OFF SPEC PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13; 2019-08-06: 2019-01-30
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00494; 2019-08-06: TPSK-LSPA1-T-ME-00770
[6 empty] | Return Date | 2019-03-29: 2019-01-14; 2019-08-06: 2019-02-21
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2660 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2660 - DEBUTANIZER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C; 2020-02-07: D
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-10-23; 2019-08-06: 2018-11-08; 2019-11-11: 2018-12-05; 2020-02-07: 2019-02-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00215; 2019-08-06: TPSK-LSPA1-T-ME-00288; 2019-11-11: TPSK-LSPA1-T-ME-00415; 2020-02-07: TPSK-LSPA1-T-ME-00861
[6 empty] | Return Date | 2019-08-06: 2018-11-17; 2019-11-11: 2018-12-27; 2020-02-07: 2019-03-12
Owner Cmmt* | bar: 2019-08-06 to 2020-02-07
| ME | OL1-2M03-2661 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2660 - DEBUTANIZER CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10; 2019-08-06: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00465; 2019-08-06: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | 2019-03-29: 2018-12-27; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2662 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2660 - DEBUTANIZER REFLUX DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-17; 2019-08-06: 2019-04-30
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00516; 2019-08-06: TPSK-LSPA1-T-ME-01535
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2663 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2660 - DEBUTANIZER REFLUX / PRODUCT PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-17; 2019-08-06: 2019-02-07; 2019-11-11: 2019-04-25
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00511; 2019-08-06: TPSK-LSPA1-T-ME-00822; 2019-11-11: TPSK-LSPA1-T-ME-01479
[6 empty] | Return Date | 2019-03-29: 2019-01-14; 2019-08-06: 2019-02-21
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2664 | Mechanical Equipment Datasheet - C5 - Pygas Feed Filters |  | Class Final | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25; 2019-02-20: 2019-05-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01141; 2019-02-20: TPSK-LSPA1-T-ME-01669
[6 empty] | Return Date | 2019-02-20: 2019-04-11
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M03-2665 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2665 - DEBUTANIZER REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10; 2019-08-06: 2019-04-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00468; 2019-08-06: TPSK-LSPA1-T-ME -01313
[6 empty] | Return Date | 2019-03-29: 2018-12-27
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2666 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2666 - DEBUTANIZER BOTTOMS COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10; 2019-08-06: 2019-04-12
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00468; 2019-08-06: TPSK-LSPA1-T-ME-01344
[6 empty] | Return Date | 2019-03-29: 2018-12-27
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2667 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2666 - C5 / PYGAS SURGE DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00869
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2668 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2666 - C5 / PYGAS PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-20; 2019-08-06: 2019-03-20; 2019-11-11: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00898; 2019-08-06: TPSK-LSPA1-T-ME-01102; 2019-11-11: TPSK-LSPA1-T-ME-01426
[6 empty] | Return Date | 2019-03-29: 2019-03-12; 2019-08-06: 2019-04-10
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2669 | Mechanical Equipment Datasheet - Debutanizer Bottoms Pumps |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-04; 2019-08-06: 2019-02-07
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00421; 2019-08-06: TPSK-LSPA1-T-ME-00823
[6 empty] | Return Date | 2019-08-06: 2019-03-15
Owner Cmmt* | bar: 2019-08-06
| ME | OL1-2M03-2700 | MECHANICAL EQUIPMENT DATA SHEET - 10-R-2700 - GHU-1 REACTOR |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-16; 2019-02-20: 2019-02-16
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-01; 2019-08-06: 2019-04-12
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00795; 2019-08-06: TPSK-LSPA1-T-ME-01346
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2701 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2701 - GHU-1 FEED / EFFLUENT EXCHANGERS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-03-20; 2019-08-06: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01100; 2019-08-06: TPSK-LSPA1-T-ME-01230
[6 empty] | Return Date | 2019-08-06: 2019-05-09
Owner Cmmt* | bar: 2019-08-06
| ME | OL1-2M03-2702 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2702 - GHU-1 S/U HEATER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-03-19; 2019-08-06: 2019-05-02; 2019-11-11: 2019-05-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01095; 2019-08-06: TPSK-LSPA1-T-ME-01566; 2019-11-11: TPSK-LSPA1-T-ME-01569
[6 empty] | Return Date | 2019-03-29: 2019-04-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2703 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2705 - GHU-1 RECYCLE COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-19; 2019-08-06: 2019-04-16
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00895; 2019-08-06: TPSK-LSPA1-T-ME-01357
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2704 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2705 - GHU-1 RECYCLE PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-19; 2019-08-06: 2019-03-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00891; 2019-08-06: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date | 2019-03-29: 2019-03-12; 2019-08-06: 2019-04-10
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2705 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2705 - GHU-1 HOT SEPARATOR |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-19
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00893
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2706 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2706 - GHU-1 COLD SEPARATOR |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-25
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00928
[6 empty] | Return Date | 2019-03-29: 2019-03-15
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2707 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2706 - GHU-1 COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-25; 2019-08-06: 2019-04-24
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00927; 2019-08-06: TPSK-LSPA1-T-ME -01467
[6 empty] | Return Date | 2019-03-29: 2019-03-15
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2710 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2710 - DEPENTANIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-06; 2019-08-06: 2019-05-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00805; 2019-08-06: TPSK-LSPA1-T-ME -01588
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2711 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2710 -DEPENTANIZER CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-21; 2019-08-06: 2019-04-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00908; 2019-08-06: TPSK-LSPA1-T-ME-01362
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2712 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2710 - DEPENTANIZER REFLUX DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00874
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2713 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2710 - DEPENTANIZER REFLUX PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-19; 2019-08-06: 2019-03-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00891; 2019-08-06: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date | 2019-03-29: 2019-03-12; 2019-08-06: 2019-04-10
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2714 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2714 - C5 CUT PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-19; 2019-08-06: 2019-04-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00891; 2019-08-06: TPSK-LSPA1-T-ME-01279
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2715 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2715 - DEPENTANIZER REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-21; 2019-08-06: 2019-04-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00908; 2019-08-06: TPSK-LSPA1-T-ME-01362
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2716 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2714 - C5 CUT COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00872
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2718 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2720 - RERUN TOWER REFLUX DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00869
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2719 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2720 - RERUN TOWER REFLUX / PRODUCT PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-19; 2019-08-06: 2019-04-26
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00891; 2019-08-06: TPSK-LSPA1-T-ME-01493
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2720 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2720 - RERUN TOWER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-28; 2019-08-06: 2019-04-17
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00741; 2019-08-06: TPSK-LSPA1-T-ME-01399
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2721 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2720 - RERUN TOWER CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-28
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME -00956
[6 empty] | Return Date | 2019-03-29: 2019-03-25
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2723 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2724 - WASH OIL CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-25
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00929
[6 empty] | Return Date | 2019-03-29: 2019-03-15
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2724 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2724 - WASH OIL DEGASSING DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00869
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2725 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2725 - RERUN TOWER REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2726 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2726 - PYGAS FUEL OIL PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-20; 2019-08-06: 2019-04-30
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00898; 2019-08-06: TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date | 2019-03-29: 2019-03-19
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2727 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2726 - PYGAS FUEL OIL COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00897
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2728 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2724 - RECYCLE WASH OIL PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-19; 2019-08-06: 2019-04-30
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00891; 2019-08-06: TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2729 | Mechanical Equipment Datasheet - Wash Oil Pumps |  | Class Final | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2018-12-27; 2019-02-20: 2019-01-17
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-20; 2019-08-06: 2019-04-09; 2019-11-11: 2019-04-30
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00898; 2019-08-06: TPSK-LSPA1-T-ME-01287; 2019-11-11: TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2730 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2730 - HYDROG REGEN HEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-18
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01410
Return Date
Owner Cmmt*
| ME | OL1-2M03-2735 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2735 - REGEN HYDROG DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-04
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01253
Return Date
Owner Cmmt*
| ME | OL1-2M03-2750 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2750 - C4 / C5 HYDROG SURGE DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00869
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2751 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2750 - C4 / C5 HYDROG FEED PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-07; 2019-08-06: 2019-03-20; 2019-11-11: 2019-05-09
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00817; 2019-08-06: TPSK-LSPA1-T-ME-01102; 2019-11-11: TPSK-LSPA1-T-ME-01626
[6 empty] | Return Date | 2019-03-29: 2019-03-15; 2019-08-06: 2019-04-10
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2755 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2755 - C4 / C5 HYDROG S/U HEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-03-19; 2019-08-06: 2019-04-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01095; 2019-08-06: TPSK-LSPA1-T-ME-01514
[6 empty] | Return Date | 2019-03-29: 2019-04-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2760 | MECHANICAL EQUIPMENT DATA SHEET - 10-R-2760 - C4 / C5 HYDROG REACTOR |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-16; 2019-02-20: 2019-02-16
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-01; 2019-08-06: 2019-04-12
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00795; 2019-08-06: TPSK-LSPA1-T-ME -01346
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2762 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2760 - C4 / C5 HYDROG RECYCLE DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00869
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2763 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2760 - C4 / C5 HYDROG VENT CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-03-15; 2019-08-06: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01075; 2019-08-06: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | 2019-03-29: 2019-05-02; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2764 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2760 - C4 / C5 HYDROG RECYCLE PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-07; 2019-08-06: 2019-03-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00817; 2019-08-06: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date | 2019-03-29: 2019-03-15; 2019-08-06: 2019-04-10
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2765 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2765 - C4 / C5 HYDROG RECYCLE COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-03-05; 2019-08-06: 2019-04-03
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00991; 2019-08-06: TPSK-LSPA1-T-ME -01242
[6 empty] | Return Date | 2019-03-29: 2019-03-29
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2790 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2790 - LIGHT OIL DRAIN DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00607
[6 empty] | Return Date | 2019-03-29: 2019-01-28
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2791 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2790 - LIGHT OIL DRAIN DRUM PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-17; 2019-08-06: 2019-04-26
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00515; 2019-08-06: TPSK-LSPA1-T-ME-01493
[6 empty] | Return Date | 2019-03-29: 2019-01-14
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2800 | MECHANICAL EQUIPMENT DATA SHEET - 10-C-2800 - PROPYLENE REFRIG COMPRESSOR |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFQ
Rev. | bar: 2019-02-20; 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2018-09-13; 2019-03-29: 2018-10-04
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-10; 2019-08-06: 2018-10-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00038; 2019-08-06: TPSK-LSPA1-T-ME-00127
[6 empty] | Return Date | 2019-02-20: 2018-09-28
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M03-2801 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2805 - PROPYLENE PRODUCT PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-20; 2019-08-06: 2019-03-12
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00543; 2019-08-06: TPSK-LSPA1-T-ME-01035
[6 empty] | Return Date | 2019-03-29: 2019-01-16; 2019-08-06: 2019-03-29
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2805 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2805 - C3R SURGE DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13; 2019-08-06: 2019-03-28
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00483; 2019-08-06: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | 2019-03-29: 2019-01-22; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2806 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2805 - C3R CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-17; 2019-08-06: 2019-03-21
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00671; 2019-08-06: TPSK-LSPA1-T-ME-01123
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-04-11
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2807 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2807 - C3 CHILLER NO. 1 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-14; 2019-08-06: 2019-04-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00505; 2019-08-06: TPSK-LSPA1-T-ME-01324
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2809 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2809 - C3 CHILLER NO. 2 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-14; 2019-08-06: 2019-04-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00505; 2019-08-06: TPSK-LSPA1-T-ME-01324
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2810 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2810 - C3R 1ST STAGE SUCTION DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00483
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2815 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2815 - C3R DRAIN DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00607
[6 empty] | Return Date | 2019-03-29: 2019-01-28
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2816 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2815 - PROPYLENE REFRIG RECOVERY PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-20; 2019-08-06: 2019-02-07
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00543; 2019-08-06: TPSK-LSPA1-T-ME-00822
[6 empty] | Return Date | 2019-03-29: 2019-01-16; 2019-08-06: 2019-02-21
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2820 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2820 - C3R 2ND STAGE SUCTION DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00483
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2830 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2830 - C3R 3RD STAGE SUCTION DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00483
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2840 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2840 - C3R 4TH STAGE SUCTION DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00460
[6 empty] | Return Date | 2019-03-29: 2018-12-27
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2850 | MECHANICAL EQUIPMENT DATA SHEET - 10-C-2850 - ETHYLENE REFRIG COMPRESSOR |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFA; 2019-03-29: IFD; 2019-08-06: IFQ
Rev. | bar: 2019-02-20; 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2018-09-13; 2019-03-29: 2018-10-04
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-10; 2019-08-06: 2018-10-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00038; 2019-08-06: TPSK-LSPA1-T-ME-00127
[6 empty] | Return Date | 2019-02-20: 2018-09-28; 2019-08-06: 2018-10-26
Owner Cmmt* | bar: 2019-02-20; 2019-08-06
| ME | OL1-2M03-2852 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2852 - C2R DESUPERHEATER NO. 1 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-14; 2019-08-06: 2019-04-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00505; 2019-08-06: TPSK-LSPA1-T-ME-01311
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2853 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2852 - C2R DESUPERHEATER NO. 2 |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-20; 2019-08-06: 2019-04-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00541; 2019-08-06: TPSK-LSPA1-T-ME -01313
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2854 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2855 - C2R SURGE DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00638
[6 empty] | Return Date | 2019-03-29: 2019-01-31
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2855 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2855 - ETHYLENE PRODUCT PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13; 2019-08-06: 2019-03-12
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00494; 2019-08-06: TPSK-LSPA1-T-ME-01035
[6 empty] | Return Date | 2019-03-29: 2019-01-14; 2019-08-06: 2019-03-29
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2856 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2855 - C2R CONDENSER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-14; 2019-08-06: 2019-01-30; 2019-11-11: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00316; 2019-08-06: TPSK-LSPA1-T-ME-00773; 2019-11-11: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | 2019-03-29: 2019-02-04; 2019-08-06: 2019-02-26; 2019-11-11: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-11-11
| ME | OL1-2M03-2857 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2857 - HP ETHYLENE PRODUCT VAPORIZER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-13; 2019-08-06: 2019-01-30; 2019-11-11: 2019-04-03
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00312; 2019-08-06: TPSK-LSPA1-T-ME-00773; 2019-11-11: TPSK-LSPA1-T-ME-01246
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-02-26
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2858 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2858 - HP ETHYLENE PRODUCT SUPERHEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22; 2019-08-06: 2019-04-04
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00684; 2019-08-06: TPSK-LSPA1-T-ME-01256
[6 empty] | Return Date | 2019-03-29: 2019-02-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2859 | Mechanical Equipment Data Sheet - 10-E-2856 - Ethylene Product Subcooler |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-16; 2019-02-20: 2019-02-16
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-20; 2019-08-06: 2019-04-03
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00541; 2019-08-06: TPSK-LSPA1-T-ME -01234
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-05-09
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2860 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2860 - C2R 1ST STAGE SUCTION DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00553
[6 empty] | Return Date | 2019-03-29: 2019-01-24
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2865 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2865 - C2R DRAIN DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00607
[6 empty] | Return Date | 2019-03-29: 2019-01-28
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2870 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2870 - C2R 2ND STAGE SUCTION DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-17; 2019-08-06: 2019-03-28
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00670; 2019-08-06: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | 2019-03-29: 2019-02-11; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2880 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2880 - C2R 3RD STAGE SUCTION DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-10; 2019-08-06: 2019-01-23
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00460; 2019-08-06: TPSK-LSPA1-T-ME-00708
[6 empty] | Return Date | 2019-03-29: 2018-12-27; 2019-08-06: 2019-02-21
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2900 | MECHANICAL EQUIPMENT DATASHEET FOR pH CTRL / CORROSION INHIBITOR INJECTION PACKAGE TAG: 10-PK-2900 |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01490
Return Date
Owner Cmmt*
| ME | OL1-2M03-2902 | MECHANICAL EQUIPMENT DATASHEET FOR EMULSION BREAKER INJECTION PACKAGE TAG: 10-PK-2902 |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01490
Return Date
Owner Cmmt*
| ME | OL1-2M03-2904 | MECHANICAL EQUIPMENT DATASHEET FOR PROCESS WATER STRIPPER CHEMICAL INJECTION PACKAGE TAG: 10-PK-2904 |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01490
Return Date
Owner Cmmt*
| ME | OL1-2M03-2906 | MECHANICAL EQUIPMENT DATASHEET FOR DSG ANTI-FOULANT INJECTION PACKAGE TAG: 10-PK-2906 |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01490
Return Date
Owner Cmmt*
| ME | OL1-2M03-2910 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-2910 - WASH OIL DAY TANK |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-18; 2019-02-20: 2019-02-26
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-28; 2019-08-06: 2019-04-23
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00745; 2019-08-06: TPSK-LSPA1-T-ME-01449
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2911 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2910 - WASH OIL INJECTION PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2018-12-27; 2019-02-20: 2019-01-17
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-25; 2019-08-06: 2019-04-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00925; 2019-08-06: TPSK-LSPA1-T-ME-01279
[6 empty] | Return Date | 2019-03-29: 2019-03-12
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2912 | MECHANICAL EQUIPMENT DATASHEET FOR CAUSTIC TOWER ANTI-FOULANT INJECTION PACKAGE TAG: 10-PK-2912 |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01490
Return Date
Owner Cmmt*
| ME | OL1-2M03-2920 | MECHANICAL EQUIPMENT DATASHEET FOR POLYMERIZATION INHIBITOR INJECTION PACKAGE TAG: 10-PK-2920 |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01490
Return Date
Owner Cmmt*
| ME | OL1-2M03-2931 | MECHANICAL EQUIPMENT DATASHEET FOR PROPANOL INJECTION PACKAGE TAG: 10-PK-2931 |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01490
Return Date
Owner Cmmt*
| ME | OL1-2M03-2932 | Mechanical Equipment Data Sheet - Methanol Drum |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-23
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00709
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-2934 | Mechanical Equipment Datasheet - Methanol Injection Pump |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2018-12-27; 2019-02-20: 2019-01-17
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-24; 2019-08-06: 2019-03-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00716; 2019-08-06: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-04-10
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-2940 | MECHANICAL EQUIPMENT DATASHEET FOR C4 POLYMER INHIBITOR INJECTION PACKAGE TAG: 10-PK-2940 |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01490
Return Date
Owner Cmmt*
| ME | OL1-2M03-3000 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3000 - PREDISTILLATION TOWER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01275
Return Date
Owner Cmmt*
| ME | OL1-2M03-3001 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3000 - PREDISTILLATION CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3002 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3002 - PREDISTILLATION FEED PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
[6 empty] | Issue Actual | 2019-03-29: 2019-05-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME -01645
Return Date
Owner Cmmt*
| ME | OL1-2M03-3003 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3000 - PREDISTILLATION REFLUX PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
[6 empty] | Issue Actual | 2019-03-29: 2019-05-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME -01645
Return Date
Owner Cmmt*
| ME | OL1-2M03-3004 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3004 - PREDISTILLATION TRIM REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3005 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3005 - PREDISTILLATION REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3006 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3000 - PREDISTILLATION REFLUX DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-16
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01370
Return Date
Owner Cmmt*
| ME | OL1-2M03-3007 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3002 - PREDISTILLATION FEED DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01363
Return Date
Owner Cmmt*
| ME | OL1-2M03-3010 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3010 - C4 FEED DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
[6 empty] | Issue Actual | 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01275
Return Date
Owner Cmmt*
| ME | OL1-2M03-3014 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3014 - C4 TRIM VAPORIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3015 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3015 - C4 VAPORIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3016 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3016 - HEAVY END DISCHARGE PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-23
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01451
Return Date
Owner Cmmt*
| ME | OL1-2M03-3018 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3018 - SOLVENT COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3020 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3020 - MAIN WASHER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01275
Return Date
Owner Cmmt*
| ME | OL1-2M03-3021 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3020 - MAIN WASHER REFLUX DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3022 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3020 - MAIN WASHER CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-03-29: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME -01645
Return Date
Owner Cmmt*
| ME | OL1-2M03-3023 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3020 - MAIN WASHER REFLUX PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01363
Return Date
Owner Cmmt*
| ME | OL1-2M03-3026 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3026 - MAIN WASHER BOTTOM PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME -01562
Return Date
Owner Cmmt*
| ME | OL1-2M03-3030 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3030 - AFTER WASHER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01325
Return Date
Owner Cmmt*
| ME | OL1-2M03-3031 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3030 - AFTER WASHER CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3032 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3030 - AFTER WASHER REFLUX PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
[6 empty] | Issue Actual | 2019-03-29: 2019-05-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME -01645
Return Date
Owner Cmmt*
| ME | OL1-2M03-3033 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3030 - AFTER WASHER REFLUX DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-16
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01370
Return Date
Owner Cmmt*
| ME | OL1-2M03-3036 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3036 - AFTER WASHER BOTTOM PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-16
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01370
Return Date
Owner Cmmt*
| ME | OL1-2M03-3040 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3040 - RECTIFIER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01275
Return Date
Owner Cmmt*
| ME | OL1-2M03-3044 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3044 - SOLVENT HEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3045 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3045 - SOLVENT HEAT EXCHANGER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3046 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3046 - DEGASSER FEED PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-17
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01398
Return Date
Owner Cmmt*
| ME | OL1-2M03-3047 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3045 - RECTIFIER PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-17
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01398
Return Date
Owner Cmmt*
| ME | OL1-2M03-3050 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3050 - DEGASSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01325
Return Date
Owner Cmmt*
| ME | OL1-2M03-3055 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3055 - DEGASSER REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3056 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3056 - DEGASSER BOTTOM PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01582
Return Date
Owner Cmmt*
| ME | OL1-2M03-3060 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3060 - ACETYLENE WASHER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01275
Return Date
Owner Cmmt*
| ME | OL1-2M03-3061 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3060 - ACETYLENE WASHER CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2018-12-27; 2019-02-20: 2019-01-17
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01570
Return Date
Owner Cmmt*
| ME | OL1-2M03-3062 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3062 - ACETYLENE CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3063 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3060 - WASTE WATER PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3064 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3062 - C4 ACETYLENE PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
[6 empty] | Issue Actual | 2019-03-29: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01654
Return Date
Owner Cmmt*
| ME | OL1-2M03-3065 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3061 - WASTE HC PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
[6 empty] | Issue Actual | 2019-03-29: 2019-05-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME -01645
Return Date
Owner Cmmt*
| ME | OL1-2M03-3066 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3062 - ACETYLENE ACCUMULATOR |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01563
Return Date
Owner Cmmt*
| ME | OL1-2M03-3067 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3060 - C4 FEED DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01570
Return Date
Owner Cmmt*
| ME | OL1-2M03-3070 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3070 - DIRECT COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01275
Return Date
Owner Cmmt*
| ME | OL1-2M03-3071 | MECHANICAL EQUIPMENT DATA SHEET - 10-C-3070 - RECYCLE GAS COMPRESSOR |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3073 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3070 - WATER / NMP COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-01-10; 2019-02-20: 2019-01-31
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22; 2019-08-06: 2019-03-14
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00692; 2019-08-06: TPSK-LSPA1-T-ME-01066
[6 empty] | Return Date | 2019-03-29: 2019-02-26; 2019-08-06: 2019-04-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-3076 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3076 - DIRECT COOLER PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01563
Return Date
Owner Cmmt*
| ME | OL1-2M03-3080 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3080 - BUTADIENE TOWER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01275
Return Date
Owner Cmmt*
| ME | OL1-2M03-3081 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3080 - BUTADIENE TOWER REFLUX DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3082 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3080 - BUTADIENE TOWER CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
[6 empty] | Issue Actual | 2019-03-29: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01654
Return Date
Owner Cmmt*
| ME | OL1-2M03-3083 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3080 - BUTADIENE TOWER REFLUX PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01563
Return Date
Owner Cmmt*
| ME | OL1-2M03-3084 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3084 - BUTADIENE TOWER TRIM REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LPSA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3085 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3085 - BUTADIENE TOWER REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3086 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3086 - C4 / C5 HC PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01570
Return Date
Owner Cmmt*
| ME | OL1-2M03-3090 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3090 - BUTADIENE DRYING TOWER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-10
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01312
Return Date
Owner Cmmt*
| ME | OL1-2M03-3095 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3095 - BUTADIENE DRYING TOWER REBOILER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3097 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3096 - BUTADIENE PRODUCT PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01570
Return Date
Owner Cmmt*
| ME | OL1-2M03-3098 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3098 - BUTADIENE PRODUCT SUBCOOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3100 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3100 - SOLVENT REGEN DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01654
Return Date
Owner Cmmt*
| ME | OL1-2M03-3110 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3110 - WATER WASHER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-03-14; 2019-02-20: 2019-04-11
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01275
Return Date
Owner Cmmt*
| ME | OL1-2M03-3111 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3110 - WATER WASHER ACCUMULATOR |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3112 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3110 - WATER WASHER CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01654
Return Date
Owner Cmmt*
| ME | OL1-2M03-3113 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3110 - SOLVENT RETURN PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01563
Return Date
Owner Cmmt*
| ME | OL1-2M03-3126 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3126 - EJECTOR SEAL DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01654
Return Date
Owner Cmmt*
| ME | OL1-2M03-3127 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3126 - WASTE WATER RETURN PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01563
Return Date
Owner Cmmt*
| ME | OL1-2M03-3150 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3150 - CONDENSATE HEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3151 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3150 - CONDENSATE FLASH DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01654
Return Date
Owner Cmmt*
| ME | OL1-2M03-3160 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3160 - CONDENSATE COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01565
Return Date
Owner Cmmt*
| ME | OL1-2M03-3161 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3160 - CONDENSATE DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-01-18; 2019-02-20: 2019-02-08
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
[6 empty] | Issue Actual | 2019-03-29: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01654
Return Date
Owner Cmmt*
| ME | OL1-2M03-3162 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3160 - CONDENSATE RECYCLE PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01563
Return Date
Owner Cmmt*
| ME | OL1-2M03-3180 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3180 - BLOWDOWN DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01654
Return Date
Owner Cmmt*
| ME | OL1-2M03-3190 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3190 - NMP SLOP DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01654
Return Date
Owner Cmmt*
| ME | OL1-2M03-3191 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3190 - SOLVENT SLOP PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01570
Return Date
Owner Cmmt*
| ME | OL1-2M03-3900 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-3900 - NMP STORAGE TANK |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-25; 2019-02-20: 2019-04-22
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
[6 empty] | Issue Actual | 2019-03-29: 2019-04-23
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01449
Return Date
Owner Cmmt*
| ME | OL1-2M03-3901 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3900 - NMP STORAGE PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-30
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01524
Return Date
Owner Cmmt*
| ME | OL1-2M03-3902 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3902 - SOLVENT INHIBITOR DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01654
Return Date
Owner Cmmt*
| ME | OL1-2M03-3903 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3902 - SOLVENT INHIBITOR DOSING PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2018-12-27; 2019-02-20: 2019-01-17
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-23
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01451
Return Date
Owner Cmmt*
| ME | OL1-2M03-3904 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3904 - PRODUCT INHIBITOR DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01654
Return Date
Owner Cmmt*
| ME | OL1-2M03-3905 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3904 - PRODUCT INHIBITOR DOSING PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2018-12-27; 2019-02-20: 2019-01-17
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-23
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01451
Return Date
Owner Cmmt*
| ME | OL1-2M03-3906 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3906 - ANTI FOAM AGENT DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01654
Return Date
Owner Cmmt*
| ME | OL1-2M03-3907 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3906 - ANTIFOAM DOSING PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2018-12-27; 2019-02-20: 2019-01-17
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-23
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01451
Return Date
Owner Cmmt*
| ME | OL1-2M03-3908 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3908 - PREDISTILLATION INHIBITOR DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-17
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01389
Return Date
Owner Cmmt*
| ME | OL1-2M03-3909 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3908 - PREDISTILLATION INHIBITOR DOSING PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2018-12-27; 2019-02-20: 2019-01-17
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-23
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01451
Return Date
Owner Cmmt*
| ME | OL1-2M03-5100 | Mechanical Equipment Datasheet for Deaerator D-5100 |  | Class Final | Purpose** | 2019-02-20: IFP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01209
Return Date
Owner Cmmt*
| ME | OL1-2M03-5101 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5100 - SHP BFW PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C; 2020-02-07: D
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-10-27; 2019-08-06: 2018-11-15; 2019-11-11: 2018-12-11; 2020-02-07: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00236; 2019-08-06: TPSK-LSPA1-T-ME-00322; 2019-11-11: TPSK-LSPA1-T-ME-00476; 2020-02-07: TPSK-LSPA1-T-ME-01433
[6 empty] | Return Date | 2019-03-29: 2018-11-19; 2019-08-06: 2018-12-10; 2019-11-11: 2019-01-16
Owner Cmmt* | bar: 2019-03-29 to 2019-11-11
| ME | OL1-2M03-5102 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5102 - BFW PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C; 2020-02-07: D
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-10-27; 2019-08-06: 2018-12-11; 2019-11-11: 2019-04-02; 2020-02-07: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00236; 2019-08-06: TPSK-LSPA1-T-ME-00476; 2019-11-11: TPSK-LSPA1-T-ME-01227; 2020-02-07: TPSK-LSPA1-T-ME-01433
[6 empty] | Return Date | 2019-03-29: 2018-11-19; 2019-08-06: 2019-01-16
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5103 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5100 - DEARATOR VENT CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00755
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5107 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5112 - SUSPECT CONDENSATE FLASH DRUM VENT CONDENSER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-29; 2019-08-06: 2019-04-18
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00755; 2019-08-06: TPSK-LSPA1-T-ME-01396
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5108 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5110 - SUSPECT CONDENSATE COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2018-10-20; 2019-02-20: 2018-10-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-25
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00723
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5109 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5110 - CONDENSATE PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | B | C | D | E
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-10-26 | 2018-11-14 | 2018-12-11 | 2019-03-25 | 2019-03-29
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00235 | TPSK-LSPA1-T-ME-00317 | TPSK-LSPA1-T-ME-00476 | TPSK-LSPA1-T-ME-01151 | TPSK-LSPA1-T-ME-01197
[6 empty] | Return Date | 2019-03-29: 2018-11-19; 2019-08-06: 2019-02-21; 2019-11-11: 2019-01-16; 2020-02-07: 2019-04-10
Owner Cmmt* | bar: 2019-03-29 to 2020-02-07
| ME | OL1-2M03-5110 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5110 - CONDENSATE TANK |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-18; 2019-02-20: 2019-02-26
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-28; 2019-08-06: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00746; 2019-08-06: TPSK-LSPA1-T-ME-01430
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5111 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5112 - SUSPECT CONDENSATE PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-20; 2019-08-06: 2018-12-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00341; 2019-08-06: TPSK-LSPA1-T-ME-00544
[6 empty] | Return Date | 2019-03-29: 2018-12-13; 2019-08-06: 2019-01-16
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5112 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5112 - SUSPECT CONDENSATE FLASH DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-16
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00657
[6 empty] | Return Date | 2019-03-29: 2019-02-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5113 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5113 - FOUL CONDENSATE COOLER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-29; 2019-08-06: 2019-05-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00755; 2019-08-06: TPSK-LSPA1-T-ME-01545
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5114 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5114 - LP CONDENSATE FLASH DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-16
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00657
[6 empty] | Return Date | 2019-03-29: 2019-02-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5115 | Mechanical Equipment Datasheet For Condensate Carbon Filter Package |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01040
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M03-5120 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5120 - RAW CONDENSATE TANK |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-18; 2019-02-20: 2019-02-26
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-28
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00746
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5121 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5120 - RAW CONDENSATE PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-20; 2019-08-06: 2018-12-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00341; 2019-08-06: TPSK-LSPA1-T-ME-00544
[6 empty] | Return Date | 2019-03-29: 2018-12-13; 2019-08-06: 2019-01-16
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5125 | Mechanical Equipment Datasheet for Condensate Polisher Package |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00941
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M03-5140 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5140 - INTERMITTENT BLOWDOWN DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-20; 2019-08-06: 2019-01-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA-T-ME-00548; 2019-08-06: TPSK-LSPA1-T-ME-00638
[6 empty] | Return Date | 2019-03-29: 2019-01-24; 2019-08-06: 2019-01-31
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5141 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5140 - INTERMITTENT BLOWDOWN PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-11-19
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00335
[6 empty] | Return Date | 2019-03-29: 2018-12-13
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5150 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5150 - CONTINUOUS BLOWDOWN FLASH DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00629
[6 empty] | Return Date | 2019-03-29: 2019-01-31
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5200 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5200 - FUEL GAS DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00629
[6 empty] | Return Date | 2019-03-29: 2019-01-31
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5201 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5200 - MP ETHYLENE SUPERHEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-29; 2019-08-06: 2019-04-12
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00755; 2019-08-06: TPSK-LSPA1-T-ME-01344
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5202 | Mechanical Equipment Data Sheet - MP Ethylene Superhtr Cond Pot |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00685
[6 empty] | Return Date | 2019-03-29: 2019-02-15
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5210 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5210 - PILOT GAS VAPORIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-17; 2019-08-06: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00673; 2019-08-06: TPSK-LSPA1-T-ME-01436
[6 empty] | Return Date | 2019-03-29: 2019-02-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5211 | Mechanical Equipment Data Sheet - Pilot Gas Vaporizer Cond Pot |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-23; 2019-08-06: 2019-03-28
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00709; 2019-08-06: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5350 | Mechanical Equipment Datasheet for Cooling Tower |  | Class Final | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
[6 empty] | Rev. | 2019-02-20: B; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-06; 2019-02-20: 2019-04-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00276; 2019-02-20: TPSK-LSPA1-T-ME-01476
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M03-5352 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5350 - OLEFINS COOLING WATER PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-10-23; 2019-08-06: 2018-11-28
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00210; 2019-08-06: TPSK-LSPA1-T-ME-00388
[6 empty] | Return Date | 2019-03-29: 2018-11-14; 2019-08-06: 2018-12-18
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5355 | Mechanical Equipment Datasheet for Side Stream Filter Package |  | Class Final | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
[6 empty] | Rev. | 2019-02-20: B; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-31; 2019-02-20: 2019-03-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00248; 2019-02-20: TPSK-LSPA1-T-ME-01164
[6 empty] | Return Date | 2019-02-20: 2018-11-27; 2019-02-20: 2019-04-25
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M03-5361 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5360 - CTU COOLING WATER PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C; 2020-02-07: D
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-10-23; 2019-08-06: 2018-11-14; 2019-11-11: 2018-11-28; 2020-02-07: 2019-01-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00210; 2019-08-06: TPSK-LSPA1-T-ME-00317; 2019-11-11: TPSK-LSPA1-T-ME-00388; 2020-02-07: TPSK-LSPA1-T-ME-00627
[6 empty] | Return Date | 2019-03-29: 2018-11-14; 2019-08-06: 2019-02-21; 2019-11-11: 2018-12-18; 2020-02-07: 2019-01-31
Owner Cmmt* | bar: 2019-03-29 to 2020-02-07
| ME | OL1-2M03-5371 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5370 - CW FILTER BACKWASH PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-24; 2019-08-06: 2019-03-12; 2019-11-11: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00716; 2019-08-06: TPSK-LSPA1-T-ME-01038; 2019-11-11: TPSK-LSPA1-T-ME-01426
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-03-29
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5390 | MECHANICAL EQUIPMENT DATASHEET FOR COPPER CORROSION INHIBITOR INJECTION PACKAGE TAG: 10-PK-5390 |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01490
Return Date
Owner Cmmt*
| ME | OL1-2M03-5392 | MECHANICAL EQUIPMENT DATASHEET FOR MILD STEEL CORROSION INHIBITOR INJECTION PACKAGE TAG: 10-PK-5392 |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01490
Return Date
Owner Cmmt*
| ME | OL1-2M03-5394 | MECHANICAL EQUIPMENT DATASHEET FOR DISPERSANT INJECTION PACKAGE TAG: 10-PK-5394 |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01490
Return Date
Owner Cmmt*
| ME | OL1-2M03-5397 | MECHANICAL EQUIPMENT DATASHEET FOR NON-OXIDIZING BIOCIDE INJECTION PACKAGE TAG: 10-PK-5397 |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01490
Return Date
Owner Cmmt*
| ME | OL1-2M03-5400 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5400 - INSTRUMENT AIR RECEIVER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00685
[6 empty] | Return Date | 2019-03-29: 2019-02-15
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5500 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5500 - WARM FLARE DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2018-12-13; 2019-08-06: 2019-04-30
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00483; 2019-08-06: TPSK-LSPA1-T-ME-01535
[6 empty] | Return Date | 2019-03-29: 2019-01-22
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5501 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5500 - HOT BLOWDOWN PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-10; 2019-08-06: 2019-02-07; 2019-11-11: 2019-03-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00616; 2019-08-06: TPSK-LSPA1-T-ME-00822; 2019-11-11: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date | 2019-03-29: 2019-01-30; 2019-08-06: 2019-02-21; 2019-11-11: 2019-04-10
Owner Cmmt* | bar: 2019-03-29 to 2019-11-11
| ME | OL1-2M03-5510 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5510 - COLD FLARE DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00629
[6 empty] | Return Date | 2019-03-29: 2019-01-31
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5511 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5510 - COLD FLARE BLOWDOWN VAPORIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-29; 2019-08-06: 2019-04-26
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00755; 2019-08-06: TPSK-LSPA1-T-ME-01495
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5512 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5512 - COLD FLARE SUPERHEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-29; 2019-08-06: 2019-04-03
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00755; 2019-08-06: TPSK-LSPA1-T-ME-01247
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5513 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5513 - METHANOL VAPORIZER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-25; 2019-08-06: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00723; 2019-08-06: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5514 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5513 - METHANOL VAPROIZER COND POT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-23; 2019-08-06: 2019-03-28
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00709; 2019-08-06: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5515 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5515 - METHANOL MAKE-UP DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00607
[6 empty] | Return Date | 2019-03-29: 2019-01-28
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5520 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5520 - VENT COLLECTION DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00638
[6 empty] | Return Date | 2019-03-29: 2019-01-31
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5522 | Mechanical Equipment Datasheet - LP Vent Blower |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-18; 2019-02-20: 2019-02-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00640
[6 empty] | Return Date | 2019-03-29: 2019-02-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5550 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5550 - HP FLARE KNOCK OUT DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-03-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00629; 2019-08-06: TPSK-LSPA1-T-ME-01114
[6 empty] | Return Date | 2019-03-29: 2019-01-31
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5551 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5550 - HP FLARE KNOCK OUT DRUM PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-10; 2019-08-06: 2019-04-30
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00616; 2019-08-06: TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date | 2019-03-29: 2019-01-30
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5552 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5552 - LPG STORAGE DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00638
[6 empty] | Return Date | 2019-03-29: 2019-01-31
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5553 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5552 - LPG VAPORIZER / SUPERHEATER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-20
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-22; 2019-08-06: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00684; 2019-08-06: TPSK-LSPA1-T-ME-01436
[6 empty] | Return Date | 2019-03-29: 2019-02-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5555 | Mechanical Equipment Data Sheet - LPG Vaporizer-Superhtr Cond Pot |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-23; 2019-08-06: 2019-03-28
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00709; 2019-08-06: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-05-02
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5560 | Mechanical Data Sheet for HP / Polyolefins Flare Package |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00667
[6 empty] | Return Date | 2019-02-20: 2019-02-08
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M03-5565 | MECHANICAL EQUIPMENT DATA SHEET- 10-D-5565 - LLDPE LP FLARE KNOCK OUT DRUM |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-04-08; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-23
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00709
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5566 | Mechanical Equipment Datasheet - Polyolefins Flare Knock-Out Pumps |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-24; 2019-08-06: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00716; 2019-08-06: TPSK-LSPA1-T-ME-01426
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5606 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5600 - PYGAS AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-07; 2019-08-06: 2019-04-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00817; 2019-08-06: TPSK-LSPA1-T-ME-01279
[6 empty] | Return Date | 2019-03-29: 2019-03-15
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5607 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5601 - BUTADIENE AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-24; 2019-08-06: 2019-03-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00716; 2019-08-06: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-03-15
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5608 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5602 - QW AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-24; 2019-08-06: 2019-03-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00716; 2019-08-06: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-03-15
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5609 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5603 - CGC AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-24; 2019-08-06: 2019-03-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00716; 2019-08-06: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-03-15
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5611 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5610 - HYDROBLAST PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-24; 2019-08-06: 2019-04-08
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00716; 2019-08-06: TPSK-LSPA1-T-ME-01279
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5612 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-5610 - HYDROBLAST FILTER |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-25; 2019-02-20: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-11; 2019-08-06: 2019-03-25
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00639; 2019-08-06: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | 2019-03-29: 2019-01-30; 2019-08-06: 2019-04-11
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5613 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5604 - REFRIG AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-24; 2019-08-06: 2019-03-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00716; 2019-08-06: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-03-15
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5614 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5605 - FURNACE AREA OILY WATER PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-24; 2019-08-06: 2019-03-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00716; 2019-08-06: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-03-15
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5616 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5615 - OLEFINS STORMWATER SUMP PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-24; 2019-08-06: 2019-03-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00716; 2019-08-06: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-03-15
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5621 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5621 - OLEFINS HOLDING BASIN SKIM OIL PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-28; 2019-08-06: 2019-03-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME -00742; 2019-08-06: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-04-10
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5622 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5620 - OLEFINS HOLDING BASIN PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-24; 2019-08-06: 2019-04-17
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00716; 2019-08-06: TPSK-LSPA1-T-ME-01390
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5623 | Mechanical Equipment Datasheet - Gate House Septic Tank Pumps |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-13; 2019-08-06: 2019-04-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME -00847; 2019-08-06: TPSK-LSPA1-T-ME-01363
[6 empty] | Return Date | 2019-03-29: 2019-03-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5624 | Mechanical Equipment Datasheet - West Gate House Septic Tank Pumps |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-13; 2019-08-06: 2019-04-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME -00847; 2019-08-06: TPSK-LSPA1-T-ME-01363
[6 empty] | Return Date | 2019-03-29: 2019-03-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5625 | Mechanical Equipment Datasheet - East Gate House Septic Tank Pumps |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-13; 2019-08-06: 2019-04-15
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME -00847; 2019-08-06: TPSK-LSPA1-T-ME-01363
[6 empty] | Return Date | 2019-03-29: 2019-03-11
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5635 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5630 - CT AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-07
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00817
[6 empty] | Return Date | 2019-03-29: 2019-03-15
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5636 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5631 - CWWT AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-07
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00817
[6 empty] | Return Date | 2019-03-29: 2019-03-15
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5637 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5632 - HP FLARE AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-07; 2019-08-06: 2019-03-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00817; 2019-08-06: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date | 2019-03-29: 2019-03-15; 2019-08-06: 2019-04-10
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5638 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5633 - HP FLARE AREA STORMWATER SUMP PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-07; 2019-08-06: 2019-03-20
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00817; 2019-08-06: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date | 2019-03-29: 2019-03-15; 2019-08-06: 2019-04-10
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5640 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5640 - OILY WASTEWATER EQUALIZATION TANKS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-18; 2019-02-20: 2019-02-26
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-26
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00926
[6 empty] | Return Date | 2019-03-29: 2019-03-15
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5641 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5641 - WASTEWATER EQ TANK SKIMMED OIL PUMP |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-09
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01292
Return Date
Owner Cmmt*
| ME | OL1-2M03-5643 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5642 - COOLING WATER BD BASIN PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-05-06
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01582
Return Date
Owner Cmmt*
| ME | OL1-2M03-5644 | Mechanical Equipment Datasheet For Complex Waste Water Treatment Package |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00863
Return Date
Owner Cmmt*
| ME | OL1-2M03-5645 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5640 - OILY WASTEWATER EQ TANK PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-04-09
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-01292
Return Date
Owner Cmmt*
| ME | OL1-2M03-5648 | Mechanical Equipment Datasheet - C3 Hydrog Area Oily Wastewater Pump |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-24; 2019-08-06: 2019-03-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00716; 2019-08-06: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-03-15
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5649 | Mechanical Equipment Datasheet - Flare KO Drum Oily Wastewater Pump |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ; 2019-08-06: IFQ
Rev. | bar: 2019-03-29 to 2019-08-06
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-05-07
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-24; 2019-08-06: 2019-03-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00716; 2019-08-06: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | 2019-03-29: 2019-02-21; 2019-08-06: 2019-03-15
Owner Cmmt* | bar: 2019-03-29 to 2019-08-06
| ME | OL1-2M03-5900 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5900 - SULFURIC ACID TANK |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-18; 2019-02-20: 2019-02-26
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-29
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00754
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5901 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5900 - SULFURIC ACID PUMPS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2018-12-27; 2019-02-20: 2019-01-17
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-01
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00787
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5902 | Mechanical Equipment Datasheet - Sulfuric Acid Metering Pumps |  | Class Final | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2018-12-27; 2019-02-20: 2019-01-17
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-01; 2019-08-06: 2019-04-08; 2019-11-11: 2019-04-17
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00787; 2019-08-06: TPSK-LSPA1-T-ME-01279; 2019-11-11: TPSK-LSPA1-T-ME-01390
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5903 | Mechanical Equipment Datasheet - Sulfuric Acid Distribution Pumps |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01363
Return Date
Owner Cmmt*
| ME | OL1-2M03-5905 | Mechanical Equipment Datasheet - CTU Sulfuric Acid Metering Pumps |  | Class Final | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFQ
Rev. | bar: 2019-02-20 to 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01292; 2019-02-20: TPSK-LSPA1-T-ME-01390
Return Date
Owner Cmmt*
| ME | OL1-2M03-5910 | MECHANICAL EQUIPMENT DATASHEET FOR OXYGEN SCAVENGER INJECTION PACKAGE TAG: 10-PK-5910 |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01490
Return Date
Owner Cmmt*
| ME | OL1-2M03-5912 | MECHANICAL EQUIPMENT DATASHEET FOR NEUTRALIZATION AMINE INHIBITOR INJECTION PACKAGE TAG: 10-PK-5912 |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01490
Return Date
Owner Cmmt*
| ME | OL1-2M03-5914 | MECHANICAL EQUIPMENT DATASHEET FOR PHOSPHATE INJECTION PACKAGE TAG: 10-PK-5914 |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01490
Return Date
Owner Cmmt*
| ME | OL1-2M03-5950 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5950 - SODIUM HYPOCHLORITE TANK |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFQ
Rev. | bar: 2019-03-29
[6 empty] | Issue Plan | 2019-02-20: 2019-02-18; 2019-02-20: 2019-02-26
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-02-11
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME-00839
[6 empty] | Return Date | 2019-03-29: 2019-02-28
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5951 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5950 - SODIUM HYPOCHLORITE METERING PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | 2019-03-29: A; 2019-08-06: B; 2019-11-11: C
[6 empty] | Issue Plan | 2019-02-20: 2018-12-27; 2019-02-20: 2019-01-17
Revised Plan
[6 empty] | Issue Actual | 2019-03-29: 2019-01-28; 2019-08-06: 2019-04-08; 2019-11-11: 2019-04-17
[6 empty] | Transmittal no. | 2019-03-29: TPSK-LSPA1-T-ME -00742; 2019-08-06: TPSK-LSPA1-T-ME-01279; 2019-11-11: TPSK-LSPA1-T-ME-01390
[6 empty] | Return Date | 2019-03-29: 2019-02-21
Owner Cmmt* | bar: 2019-03-29
| ME | OL1-2M03-5955 | Mechanical Equipment Datasheet - CTU NaCOl Metering Pumps |  | Class Final | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFQ
Rev. | bar: 2019-02-20 to 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09; 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01292; 2019-02-20: TPSK-LSPA1-T-ME-01390
Return Date
Owner Cmmt*
| ME | OL1-2M03-6004 | Mechanical Equipment Datasheet For Cracked Gas Compressor Bridge Crane (10-EL-2300) |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00913
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M03-6005 | Mechanical Equipment Datasheet For Ethylene And Propylene Compressor Bridge Crane (10-EL-2800) |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00913
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
Category Code: M04 Mechanical design basic / philosophy / logic diagram
Category Code: M05 Mechanical calculation sheet / report
Category Code: M06 Mechanical equipment drawing
| ME | OL1-2M06-1001 | USC 36M FURNACE GENERAL ARRANGEMENT CROSS SECTION ELEVATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-08; 2019-02-20: 2019-03-13; 2019-03-29: 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-16; 2019-08-06: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00327; 2019-08-06: TPSK-LSPA1-T-ME-01361
Return Date
Owner Cmmt*
| ME | OL1-2M06-1002 | USC 36M FURNACE GENERAL ARRANGEMENT LONGITUDINAL ELEVATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-08; 2019-02-20: 2019-03-13; 2019-03-29: 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-16; 2019-08-06: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00327; 2019-08-06: TPSK-LSPA1-T-ME-01361
Return Date
Owner Cmmt*
| ME | OL1-2M06-1004 | USC 36M FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-08; 2019-02-20: 2019-03-13; 2019-03-29: 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-30; 2019-08-06: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00764; 2019-08-06: TPSK-LSPA1-T-ME-01500
[6 empty] | Return Date | 2019-02-20: 2019-02-21
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-1005 | USC 36M Recycle Furnace General Arrangement Instrumentation Sections |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-30; 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00764; 2019-02-20: TPSK-LSPA1-T-ME-01500
[6 empty] | Return Date | 2019-02-20: 2019-02-21
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-1101 | USC 36M FURNACE REFRACTORY & INSULATION RADIANT SECTION DETAILS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-23; 2019-02-20: 2019-02-20; 2019-03-29: 2019-02-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-08-06: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01065; 2019-08-06: TPSK-LSPA1-T-ME-01653
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-1102 | USC 36M FURNACE REFRACTORY & INSULATION CONVECTION SECTION DETAILS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-23; 2019-02-20: 2019-02-20; 2019-03-29: 2019-02-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-08-06: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01065; 2019-08-06: TPSK-LSPA1-T-ME-01653
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-1103 | USC 36M FURNACE INSULATION INSTALLATION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-1104 | USC 36M FURNACE REFRACTORY AND INSULATION ANCHOR DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-23; 2019-02-20: 2019-02-20; 2019-03-29: 2019-02-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-08-06: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01065; 2019-08-06: TPSK-LSPA1-T-ME-01653
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-1105 | USC 36M FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-1106 | USC 36M FURNACE PEEP DOOR INSERT DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-1107 | USC 36M FURNACE USX ASSEMBLY INSULATION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-28; 2019-02-20: 2019-02-25
[6 empty] | Revised Plan | 2019-02-20: 2019-06-10
[6 empty] | Issue Actual | 2019-02-20: 2019-05-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01619
Return Date
Owner Cmmt*
| ME | OL1-2M06-1108 | USC 36M FURNACE DECOKE NOZZLE DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-1109 | USC 36M FURNACE SEAL BOOT DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-03-29: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01368
Return Date
Owner Cmmt*
| ME | OL1-2M06-1110 | USC 36M FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1201 | USC 36M FURNACE RADIANT COIL ASSEMBLY AND DETAILS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-18; 2019-02-20: 2018-12-07; 2019-03-29: 2019-01-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-08; 2019-08-06: 2018-12-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00062; 2019-08-06: TPSK-LSPA1-T-ME-00486
[6 empty] | Return Date | 2019-02-20: 2019-02-21; 2019-08-06: 2019-01-16
Owner Cmmt* | bar: 2019-02-20; 2019-08-06
| ME | OL1-2M06-1202 | USC 36M FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00062
[6 empty] | Return Date | 2019-02-20: 2019-02-21
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-1203 | USC 36M FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-18; 2019-02-20: 2018-12-07; 2019-03-29: 2019-01-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-08; 2019-08-06: 2018-12-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00062; 2019-08-06: TPSK-LSPA1-T-ME-00486
[6 empty] | Return Date | 2019-02-20: 2019-02-21; 2019-08-06: 2019-01-16
Owner Cmmt* | bar: 2019-02-20; 2019-08-06
| ME | OL1-2M06-1204 | USC 36M FURNACE FABRICATION ASSEMBLY OF CONVECTION COILS, FINNED TUBES, AND BILL OF MATERIAL |  | Class 2 | Purpose** | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0; 2019-11-11: 1
[6 empty] | Issue Plan | 2019-02-20: 2018-10-16; 2019-02-20: 2018-12-17; 2019-03-29: 2019-03-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-16; 2019-08-06: 2019-02-13; 2019-11-11: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00182; 2019-08-06: TPSK-LSPA1-T-ME-00848; 2019-11-11: TPSK-LSPA1-T-ME-01356
[6 empty] | Return Date | 2019-08-06: 2019-03-07
Owner Cmmt* | bar: 2019-08-06
| ME | OL1-2M06-1206 | USC 36M CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2018-09-18; 2019-02-20: 2018-12-07; 2019-03-29: 2019-01-31
[6 empty] | Revised Plan | 2019-02-20: 2019-05-31; 2019-02-20: 2019-05-31; 2019-03-29: 2019-05-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1301 | USC 36M FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORTS AND DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-12-17; 2019-03-29: 2019-01-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00286
Return Date
Owner Cmmt*
| ME | OL1-2M06-1302 | USC 36M FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-12-17; 2019-03-29: 2019-01-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00286
Return Date
Owner Cmmt*
| ME | OL1-2M06-1303 | USC 36M FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-12-17; 2019-03-29: 2019-01-28
[6 empty] | Revised Plan | 2019-03-29: 2019-05-17
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01290
Return Date
Owner Cmmt*
| ME | OL1-2M06-2001 | USC 132SU FURNACE GENERAL ARRANGEMENT CROSS SECTION ELEVATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-08; 2019-02-20: 2019-03-13; 2019-03-29: 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-16; 2019-08-06: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00328; 2019-08-06: TPSK-LSPA1-T-ME-01369
Return Date
Owner Cmmt*
| ME | OL1-2M06-2002 | USC 132SU FURNACE GENERAL ARRANGEMENT LONGITUDINAL ELEVATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-08; 2019-02-20: 2019-03-13; 2019-03-29: 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-16; 2019-08-06: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00328; 2019-08-06: TPSK-LSPA1-T-ME-01369
Return Date
Owner Cmmt*
| ME | OL1-2M06-2004 | USC 132SU FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-08; 2019-02-20: 2019-03-13; 2019-03-29: 2019-10-14
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-30; 2019-08-06: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00766; 2019-08-06: TPSK-LSPA1-T-ME-01500
[6 empty] | Return Date | 2019-02-20: 2019-02-21
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-2005 | USC 132U Cracking Furnace General Arrangement Instrumentation Sections |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00768
[6 empty] | Return Date | 2019-02-20: 2019-02-21
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-2019 | USC 132U Cracking Furnace Seal Boot Details |  | Class Final | Purpose** | 2019-02-20: IFI
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01368
Return Date
Owner Cmmt*
| ME | OL1-2M06-2101 | USC 132U FURNACE REFRACTORY & INSULATION RADIANT SECTION DETAILS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-23; 2019-02-20: 2019-02-20; 2019-03-29: 2019-02-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-08-06: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01065; 2019-08-06: TPSK-LSPA1-T-ME-01653
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-2102 | USC 132U FURNACE REFRACTORY & INSULATION CONVECTION SECTION DETAILS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-23; 2019-02-20: 2019-02-20; 2019-03-29: 2019-02-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-08-06: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01065; 2019-08-06: TPSK-LSPA1-T-ME-01653
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-2103 | USC 132U FURNACE INSULATION INSTALLATION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-2104 | USC 132U FURNACE REFRACTORY AND INSULATION ANCHOR DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-23; 2019-02-20: 2019-02-20; 2019-03-29: 2019-02-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14; 2019-08-06: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01065; 2019-08-06: TPSK-LSPA1-T-ME-01653
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-2105 | USC 132U FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-2106 | USC 132U FURNACE PEEP DOOR INSERT DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-2107 | USC 132U FURNACE USX ASSEMBLY INSULATION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-28; 2019-02-20: 2019-02-25
[6 empty] | Revised Plan | 2019-02-20: 2019-06-10
[6 empty] | Issue Actual | 2019-02-20: 2019-05-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01619
Return Date
Owner Cmmt*
| ME | OL1-2M06-2108 | USC 132U FURNACE DECOKE NOZZLE DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | 2019-02-20: 2019-04-02
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-2109 | USC 132U FURNACE SEAL BOOT DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2110 | USC 132U FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2201 | USC 132U FURNACE RADIANT COIL ASSEMBLY AND DETAILS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-18; 2019-02-20: 2018-12-07; 2019-03-29: 2019-01-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-08; 2019-08-06: 2018-12-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00062; 2019-08-06: TPSK-LSPA1-T-ME-00486
[6 empty] | Return Date | 2019-02-20: 2019-02-21; 2019-08-06: 2019-01-16
Owner Cmmt* | bar: 2019-02-20; 2019-08-06
| ME | OL1-2M06-2202 | USC 132U FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00062
[6 empty] | Return Date | 2019-02-20: 2019-02-21
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M06-2203 | USC 132U FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-18; 2019-02-20: 2018-12-07; 2019-03-29: 2019-01-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-08; 2019-08-06: 2018-12-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00062; 2019-08-06: TPSK-LSPA1-T-ME-00486
[6 empty] | Return Date | 2019-02-20: 2019-02-21; 2019-08-06: 2019-01-16
Owner Cmmt* | bar: 2019-02-20; 2019-08-06
| ME | OL1-2M06-2204 | USC 132U FURNACE FABRICATION ASSEMBLY OF CONVECTION COILS, FINNED TUBES, AND BILL OF MATERIAL |  | Class 2 | Purpose** | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0; 2019-11-11: 1
[6 empty] | Issue Plan | 2019-02-20: 2018-10-16; 2019-02-20: 2018-12-17; 2019-03-29: 2019-03-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-16; 2019-08-06: 2019-02-13; 2019-11-11: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00182; 2019-08-06: TPSK-LSPA1-T-ME-00848; 2019-11-11: TPSK-LSPA1-T-ME-01356
[6 empty] | Return Date | 2019-08-06: 2019-03-07
Owner Cmmt* | bar: 2019-08-06
| ME | OL1-2M06-2206 | USC 132U CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2018-09-18; 2019-02-20: 2018-12-07; 2019-03-29: 2019-01-31
[6 empty] | Revised Plan | 2019-02-20: 2019-05-31; 2019-02-20: 2019-05-31; 2019-03-29: 2019-05-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2207 | DILUTION STEAM MIXING TEE DRAWING |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFD
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-12-21; 2019-03-29: 2019-01-23
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00669
Return Date
Owner Cmmt*
| ME | OL1-2M06-2207- | USC 132U Cracking Furnace Dilution Mixing Tee Details |  | Class Final | Purpose** | 2019-02-20: IMP
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01509
Return Date
Owner Cmmt*
| ME | OL1-2M06-2301 | USC 132SU FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT & DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-12-17; 2019-03-29: 2019-01-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00289
Return Date
Owner Cmmt*
| ME | OL1-2M06-2302 | USC 132SU FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-12-17; 2019-03-29: 2019-01-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00289
Return Date
Owner Cmmt*
| ME | OL1-2M06-2303 | USC 132SU FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-12-17; 2019-03-29: 2019-01-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01291
Return Date
Owner Cmmt*
| ME | OL1-2M06-2554 | FURNACE PEEP DOOR DETAILS (RIGHT HAND) |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFI; 2019-03-29: IFC
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-29; 2019-03-29: 2019-03-27
[6 empty] | Revised Plan | 2019-03-29: 2019-05-16
[6 empty] | Issue Actual | 2019-02-20: 2018-12-04
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00422
Return Date
Owner Cmmt*
| ME | OL1-2M06-3103 | USC 132U FURNACE INSULATION INSTALLATION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3105 | USC 132U FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3106 | USC 132U FURNACE PEEP DOOR INSERT DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3107 | USC 132U FURNACE USX ASSEMBLY INSULATION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-28; 2019-02-20: 2019-02-25
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3108 | USC 132U FURNACE DECOKE NOZZLE DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3109 | USC 132U FURNACE SEAL BOOT DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3110 | USC 132U FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3202 | USC 132U FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4103 | USC 132U FURNACE INSULATION INSTALLATION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4105 | USC 132U FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4106 | USC 132U FURNACE PEEP DOOR INSERT DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4107 | USC 132U FURNACE USX ASSEMBLY INSULATION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-28; 2019-02-20: 2019-02-25
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4108 | USC 132U FURNACE DECOKE NOZZLE DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4109 | USC 132U FURNACE SEAL BOOT DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4110 | USC 132U FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4202 | USC 132U FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5103 | USC 132U FURNACE INSULATION INSTALLATION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5105 | USC 132U FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5106 | USC 132U FURNACE PEEP DOOR INSERT DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5107 | USC 132U FURNACE USX ASSEMBLY INSULATION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-28; 2019-02-20: 2019-02-25
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5108 | USC 132U FURNACE DECOKE NOZZLE DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5109 | USC 132U FURNACE SEAL BOOT DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5110 | USC 132U FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5202 | USC 132U FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6103 | USC 132U FURNACE INSULATION INSTALLATION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6105 | USC 132U FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6106 | USC 132U FURNACE PEEP DOOR INSERT DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6107 | USC 132U FURNACE USX ASSEMBLY INSULATION DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-28; 2019-02-20: 2019-02-25
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-06-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6108 | USC 132U FURNACE DECOKE NOZZLE DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6109 | USC 132U FURNACE SEAL BOOT DETAILS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6110 | USC 132U FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6202 | USC 132U FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-01; 2019-02-20: 2019-09-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: M07 Mechanical certification, inspection and test record |  |  |  |  | Class 3 | Purpose**
Category Code: M20 Static Equipment Datasheet | [5 empty] | Rev.
Category Code: M21 Rotating Machinery Datasheet | [5 empty] | Issue Plan
Category Code: M22 Package Unit-Datasheet | [5 empty] | Revised Plan
Category Code: M55 Request for Quotation (RFQ) for Mechanical work | [5 empty] | Issue Actual
| ME | OL1-2M55-0003 | MR COOLING WATER PUMPS |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00319
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M55-0008 | MR CENTRIFUGAL COMPRESSORS STEAM TURBINE DRIVEN |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00136
[6 empty] | Return Date | 2019-02-20: 2018-10-26
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M55-0012 | MR RESIDUE GAS TURBOEXPANDER/COMPRESSOR |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00139
[6 empty] | Return Date | 2019-02-20: 2018-10-26
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M55-0014 | MR INTEGRALLY GEARED COMPRESSORS |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00198
[6 empty] | Return Date | 2019-02-20: 2018-11-07
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M55-0015 | MR API CENTRIFUGAL PUMPS - LLI |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-31
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00257
[6 empty] | Return Date | 2019-02-20: 2018-11-27
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M55-0055 | MR FOR COLUMNS TRAYS & INTERN. (OPEN SOURCE ITEMS) |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00300
[6 empty] | Return Date | 2019-02-20: 2018-12-06
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M55-0058 | WIELAND TUBES (SOLO SOURCE) |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00377
[6 empty] | Return Date | 2019-02-20: 2019-02-07
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M55-0064 | MR FOR PLATE & FRAME H.E. |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00124
[6 empty] | Return Date | 2019-02-20: 2018-10-24
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M55-0066 | MR FOR COLD BOX AND CORE EXCHANGERS |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFQ
Rev. | bar: 2019-02-20 to 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03; 2019-02-20: 2018-10-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00125; 2019-02-20: TPSK-LSPA1-T-ME-00153
[6 empty] | Return Date | 2019-02-20: 2018-10-24; 2019-02-20: 2018-11-02
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2M55-0075 | MR FOR COLUMNS TRAYS & INTERN. (UOP MD TRAYS FOR COLUMNS) |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IMP
Rev. | bar: 2019-02-20 to 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-07; 2019-02-20: 2018-11-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00278; 2019-02-20: TPSK-LSPA1-T-ME-00314
[6 empty] | Return Date | 2019-02-20: 2018-11-29; 2019-02-20: 2019-02-08
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2M55-0103 | MR WET AIR OXIDATION PACKAGE. |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00367
[6 empty] | Return Date | 2019-02-20: 2019-02-07
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M55-0104 | MR COOLING TOWERS |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00276
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M55-0108 | MR DEAREATORS & DEGASIFIERS |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00270
[6 empty] | Return Date | 2019-02-20: 2018-11-29
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M55-0109 | MR SIDE STREAM FILTERS |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-31
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00248
[6 empty] | Return Date | 2019-02-20: 2018-11-27
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M55-0114 | MR HYDROGEN PRODUC./PURIF.UNITS |  | Class 2 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00271
[6 empty] | Return Date | 2019-02-20: 2019-02-07
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M55-2001 | MATERIAL REQUISITION FOR CONVECTION TUBES |  | Class 3 | Purpose** | 2019-02-20: IFP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00450
Return Date
Owner Cmmt*
| ME | OL1-2M55-2002 | MATERIAL REQUISITION FOR CONVECTION FITTING |  | Class 3 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-22; 2019-02-20: 2019-01-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00207; 2019-02-20: TPSK-LSPA1-T-ME-00592
Return Date
Owner Cmmt*
| ME | OL1-2M55-2003 | MATERIAL REQUISITION FOR QUENCH SYSTEM |  | Class 3 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-26; 2019-02-20: 2018-12-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00233; 2019-02-20: TPSK-LSPA1-T-ME-00466
Return Date
Owner Cmmt*
| ME | OL1-2M55-2004 | MATERIAL REQUISITION FOR RADIANT COILS |  | Class 3 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-18; 2019-02-20: 2018-12-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00063; 2019-02-20: TPSK-LSPA1-T-ME-00499
Return Date
Owner Cmmt*
| ME | OL1-2M55-2005 | MATERIAL REQUISITION FOR ID FAN |  | Class 3 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00269
Return Date
Owner Cmmt*
| ME | OL1-2M55-2006 | MATERIAL REQUISITION FOR BURNERS |  | Class 3 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00313
Return Date
Owner Cmmt*
| ME | OL1-2M55-2007 | MATERIAL REQUISITION FOR ITS |  | Class 3 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-16; 2019-02-20: 2018-12-20
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00329; 2019-02-20: TPSK-LSPA1-T-ME-00542
[6 empty] | Return Date | 2019-02-20: 2018-12-10
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M55-2008 | MATERIAL REQUISITION FOR PEEP DOOR |  | Class 3 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-14
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00502
Return Date
Owner Cmmt*
| ME | OL1-2M55-2010 | MATERIAL REQUISITION FOR MOV |  | Class 3 | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-18
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00534
Return Date
Owner Cmmt*
| ME | OL1-2M55-2018 | DILUTION STEAM MIXING TEE MR |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-01; 2019-02-20: 2018-12-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00263; 2019-02-20: TPSK-LSPA1-T-ME-00518
Return Date
Owner Cmmt*
Category Code: M71 Appraisal Report for Consultancy Service |  |  |  |  | Class 3 | Purpose**
Category Code: M72 Appraisal Report for EPC Contractor Work | [5 empty] | Rev.
Category Code: M73 Appraisal Report for Vendor/Supplier | [5 empty] | Issue Plan
Category Code: M90 Vendor Document/drawings | [5 empty] | Revised Plan
Category Code: M91 Index/List | [5 empty] | Issue Actual
| ME | OL1-2M91-0001 | Item Index |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01080
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M91-0002 | Item Index Furnace Island |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01080
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M91-1001 | Approved Vendor List for 36M and 132U Furnace |  | Class Final | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00211
Return Date
Owner Cmmt*
Category Code: M92 Procedures & Standards
| ME | OL1-2M92-2001 | SPECIFICATION FOR CENTRIFUGALLY CAST TUBE FOR RADIANT AND TRANSFER LINES |  | Class 2 | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00470
Return Date
Owner Cmmt*
| ME | OL1-2M92-2002 | SPECIFICATION FOR STATICALLY CAST FITTINGS FOR RADIANT COILS AND TRANSFER LINES IN CRACKING FURNACES |  | Class 2 | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00471
Return Date
Owner Cmmt*
| ME | OL1-2M92-2003 | SPECIFICATION FOR CAST INTERMEDIATE TUBE SUPPORTS |  | Class 3 | Purpose** | IFR | IFI | IFQ | IFP | IMP
[6 empty] | Rev. | 2019-02-20: 0; 2019-11-11: 1
[6 empty] | Issue Plan | 2019-02-20: 2018-10-26; 2019-03-29: 2018-10-26; 2019-08-06: 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-26; 2019-11-11: 2018-12-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00232; 2019-11-11: TPSK-LSPA1-T-ME-00517
Return Date
Owner Cmmt*
| ME | OL1-2M92-2004 | SPECIFICATION FOR FABRICATION OF CONVECTION COILS FOR CRACKING FURNACES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-07; 2019-02-20: 2018-09-19; 2019-03-29: 2018-12-13
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12; 2019-08-06: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00842; 2019-08-06: TPSK-LSPA1-T-ME -01640
[6 empty] | Return Date | 2019-02-20: 2019-03-07
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M92-2005 | SPECIFICATION FOR SUPPLY & INSTALLATION OF CERAMIC FIBER BLANKET & CF MODULE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-31; 2019-02-20: 2019-02-07; 2019-03-29: 2019-04-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12; 2019-08-06: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00842; 2019-08-06: TPSK-LSPA1-T-ME -01640
[6 empty] | Return Date | 2019-02-20: 2019-03-07
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M92-2006 | SPECIFICATION FOR SUPPLY & INSTALLATION OF REFRACTORY INSULATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-31; 2019-02-20: 2019-02-07; 2019-03-29: 2019-04-09
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-12; 2019-08-06: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00842; 2019-08-06: TPSK-LSPA1-T-ME -01640
[6 empty] | Return Date | 2019-02-20: 2019-03-07
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2M92-2007 | SPECIFICATION FOR SLE / USX QUENCH EXCHANGERS |  | Class 2 | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00427
Return Date
Owner Cmmt*
| ME | OL1-2M92-2008 | SPECIFICATION FOR TLX EXCHANGERS |  | Class 2 | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00428
Return Date
Owner Cmmt*
| ME | OL1-2M92-2009 | SPECIFICATION FOR BURNERS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-08-06: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-25; 2019-02-20: 2018-10-25; 2019-03-29: 2019-01-23
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-25; 2019-08-06: 2019-01-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00231; 2019-08-06: TPSK-LSPA1-T-ME-00698
[6 empty] | Return Date | 2019-02-20: 2018-11-14; 2019-08-06: 2019-02-14
Owner Cmmt* | bar: 2019-02-20; 2019-08-06
| ME | OL1-4M92-2001 | Project Specification for Centrifugally Cast Tubes for Radiant Coils and Transfer Lines in Cracking Furnaces |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-10-26; 2019-02-20: 2018-10-26; 2019-03-29: 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00037
[6 empty] | Return Date | 2019-02-20: 2018-09-25
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-4M92-2002 | Project Specification for Statically Cast Fittings for Radiant Coils and Transfer Lines in Cracking Furnaces |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-10-26; 2019-02-20: 2018-10-26; 2019-03-29: 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00037
[6 empty] | Return Date | 2019-02-20: 2018-09-25
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-4M92-2007 | Project Specification For SLE and USX Exchangers |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-09-20; 2019-02-20: 2018-10-26; 2019-03-29: 2018-12-10
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-20
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00067
[6 empty] | Return Date | 2019-02-20: 2018-10-12
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-4M92-2008 | Project Specification For Transfer Line Exchangers |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFQ; 2019-03-29: IFP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-09-20; 2019-02-20: 2018-10-26; 2019-03-29: 2018-12-10
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-20
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00067
[6 empty] | Return Date | 2019-02-20: 2018-10-12
Owner Cmmt* | bar: 2019-02-20
Category Code: M93 Policy , Guidelines & Memo
Category Code: M94 Forms & Templates
Category Code: M95 Progress/Status Reports
Category Code: M96 Spare part list for construction/precommissioning/commissioning
Category Code: M97 Spare Part List for Maintenance During First Two Years Operation
Category Code: M98 Special tools books
Category Code: M99 Other
Category Code: O01 Precommissioning Plan and Schedule
Category Code: O02 Commissioning Plan and Schedule |  |  |  |  | Class 2 | Purpose**
Category Code: O03 Startup Plan and Schedule | [5 empty] | Rev.
Category Code: O04 Performance Test Plan and Schedule | [5 empty] | Issue Plan
| PE | OL1-2O04-1004 | PERFORMANCE TEST PROCEDURE |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O05 Production Plan
Category Code: O06 Operating Manuals
| PE | OL1-2O06-0001 | CUO 107 - OPERATING MANUALS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-12-15; 2019-02-20: 2021-06-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O07 Startup Lists
| PE | OL1-2O07-0002 | CUO 110 - PLANT MAINTENANCE MANUAL - OFFSITES - S04 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-15; 2019-02-20: 2019-12-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O07-0003 | CUO 110 - PLANT MAINTENANCE MANUAL - WASTE WATER TREATMENT - S05 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-09-15; 2019-02-20: 2020-10-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O07-0004 | CUO 110 - PLANT MAINTENANCE MANUAL - FURNACES - S06 |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-12-01; 2019-02-20: 2021-01-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O08 Startup Philosophy |  |  |  |  | Class 2 | Purpose**
| PE | OL1-2O08-0001 | START-UP DELIVERABLE LIST |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-01; 2019-02-20: 2019-12-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O08-0002 | START-UP PACKAGE LIST |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-10-30; 2019-02-20: 2021-12-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O09 Scope of Work |  |  |  |  | Class 2 | Purpose**
| PE | OL1-2O09-0001 | RESPONSABILITY MATRIX - DEFINITION OF MECHANICAL COMPLET./PRE-COMMISSIONING TPIT-SUBCONTRACTOR |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-15; 2019-02-20: 2020-01-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O09-0002 | DEFINITION OF SCOPE OF WORK - TPIT - SPECIALIZED COMPANY |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-15; 2019-02-20: 2020-01-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O10 Maintenance Manuals
| PE | OL1-2O10-0002 | CUO 110 - MAINTENANCE PHILOSOPHY DURING INTERIM MAINTENANCE MANAGEMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-09-16; 2019-02-20: 2021-11-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O11 Operating Condition Calculation
Category Code: O12 Product Quality Calculation
Category Code: O13 Training Schedule
Category Code: O20 Precommissioning Form and Checksheet
| PE | OL1-2O20-0001 | PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - PIPING - (from 51 to 99 ) |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-01; 2019-02-20: 2019-10-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O20-0002 | PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - INSTRUMENTATION - (from 51 to 99 ) |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-01; 2019-02-20: 2019-10-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O20-0003 | PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - ELECTRICAL - (from 51 to 99 ) |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-01; 2019-02-20: 2019-10-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O20-0004 | PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - MECHANICAL - (from 51 to 99 ) |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-08-01; 2019-02-20: 2019-10-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O21 Commissioning Form and Checksheet
Category Code: O22 Operation Form and Checksheet
Category Code: O23 Equipment Patrol Checksheet
Category Code: O51 Appraisal Report for Consultancy Service
Category Code: O52 Appraisal Report for EPC Contractor Work
Category Code: O53 Appraisal Report for Vendor/Supplier
Category Code: O60 Precommissioning Record and Report
Category Code: O61 Commissioning Record and Report
Category Code: O62 Startup, Shutdown and Emergency Shutdown Record and Report
Category Code: O63 Plant performance Test and record
Category Code: O64 Operation Record and Report Production Record,Report
Category Code: O65 Troubleshooting Record, Report
Category Code: O66 Modification Record,Report
Category Code: O67 List of set point and controller parameter
| PE | OL1-2O67-1001 | ALARM & SETPOINT SUMMARY |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IFD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-04; 2019-02-20: 2019-06-13; 2019-03-29: 2019-06-24; 2019-08-06: 2019-10-28
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O67-2001 | ALARM & SETPOINT SUMMARY |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IFD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-04; 2019-02-20: 2019-06-13; 2019-03-29: 2019-06-24; 2019-08-06: 2019-10-28
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O67-3001 | ALARM & SETPOINT SUMMARY |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IFD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-04; 2019-02-20: 2019-06-13; 2019-03-29: 2019-06-24; 2019-08-06: 2019-10-28
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O67-4001 | ALARM & SETPOINT SUMMARY |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IFD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-04; 2019-02-20: 2019-06-13; 2019-03-29: 2019-06-24; 2019-08-06: 2019-10-28
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O67-5001 | ALARM & SETPOINT SUMMARY |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IFD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-04; 2019-02-20: 2019-06-13; 2019-03-29: 2019-06-24; 2019-08-06: 2019-10-28
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O67-6001 | ALARM & SETPOINT SUMMARY |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IFD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-04; 2019-02-20: 2019-06-13; 2019-03-29: 2019-06-24; 2019-08-06: 2019-10-28
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O70 Precommissioning Procedure
Category Code: O71 Commissioning Procedure
| PE | OL1-2O71-0001 | JOB START UP SPECIFICATION FOR WATER FLUSHING OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0002 | JOB START UP SPECIFICATION FOR AIR BLOWING OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0003 | JOB START UP SPECIFICATION FOR DRYING OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0004 | JOB START UP SPECIFICATION FOR GROSS LEAK TEST |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0005 | JOB START UP SPECIFICATION FOR TIGHTNESS TEST |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0006 | JOB START UP SPECIFICATION FOR STEAM BLOWING OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0007 | JOB START UP SPECIFICATION FOR CHEMICAL CLEANING OF CS OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0008 | JOB START UP SPECIFICATION FOR CHEMICAL CLEANING OF SS OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0009 | JOB START UP SPECIFICATION FOR NITROGEN PURGING OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0010 | JOB START UP SPECIFICATION FOR HYDRO-JETTING OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0011 | JOB START UP SPECIFICATION FOR OIL FLUSHING |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0012 | JOB START UP SPECIFICATION FOR MANUAL CLEANING FOR LARGE BORE PIPING PROCEDURE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0013 | JOB START UP SPECIFICATION FOR PIPING INSPECTION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0014 | JOB START UP SPECIFICATION FOR RELIEF VALVE MANAGEMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0015 | JOB START UP SPECIFICATION FOR SPRING HANGER SETTING |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0016 | JOB START UP SPECIFICATION FOR TIGHTNESS TEST WITH NITROGEN & HELIUM |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0017 | JOB START UP SPECIFICATION FOR LOOP CHECK MANAGEMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-15; 2019-02-20: 2019-10-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0018 | JOB START UP SPECIFICATION FOR LOOP FOLDER MANAGEMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-15; 2019-02-20: 2019-10-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0019 | JOB START UP SPECIFICATION FOR ELECTRICAL MOTOR SOLO RUN |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-01; 2019-02-20: 2020-06-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0020 | JOB START UP SPECIFICATION FOR ELECTRICAL SUBSTATION ENERGIZATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-01-15; 2019-02-20: 2020-02-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0021 | JOB START UP SPECIFICATION FOR PUMP ALIGNMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-15; 2019-02-20: 2019-10-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0022 | JOB START UP SPECIFICATION FOR VESSELS/EQUIPMENT INSPECTION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-15; 2019-02-20: 2019-10-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0023 | CUO 110 - JOB START UP SPECIF.FOR MTL PRESERVATION DURING CONSTRUCTION, PRECOMM., COMMISS. AND STARTUP |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-31; 2019-02-20: 2019-05-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-18
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01090
Return Date
Owner Cmmt*
| PE | OL1-2O71-1001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 1 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-2001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 1 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-3001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 1 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-4001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 1 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-5001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 1 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-6001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 1 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-12-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O72 Startup, Shutdown and Emergency Shutdown Procedure
Category Code: O73 Plant performance Test procedure
Category Code: O74 Tag-in Tag-out/Lock-out Tag-out Procedure
Category Code: O75 Operation Work instruction
| PE | OL1-2O75-0001 | OPERATIONAL TEST PROCEDURE (OTP) |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-03-01; 2019-02-20: 2021-07-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-1001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-11; 2019-02-20: 2019-12-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-2001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-11; 2019-02-20: 2019-12-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-3001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-11; 2019-02-20: 2019-12-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-4001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-11; 2019-02-20: 2019-12-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-5001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-11; 2019-02-20: 2019-12-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-6001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-11; 2019-02-20: 2019-12-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O80 Lab, Product QA and QC
| PE | OL1-2O80-1003 | SAMPLING AND ANALYTICAL MANUAL |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-19; 2019-02-20: 2019-08-16; 2019-03-29: 2020-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O91 Index/List
Category Code: O92 Procedures & Standards
Category Code: O93 Policy , Guidelines & Memo
Category Code: O94 Forms & Templates
Category Code: O95 Progress/Status Reports
Category Code: P03 Piping datasheet
| MP | OL1-2P03-1101 | PIPING SPECIALTY ITEM - DATA SHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-22; 2019-02-20: 2019-05-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1102 | Piping Specialty Item Datasheet - T- Type Filter - Crossover Line - 10-SP-11002 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1104 | Piping Specialty Item Datasheet - Vent Silencer - PSV-1142 A-B Outlet - 10- SP-11004 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1105 | Piping Specialty Item Datasheet - T-Type Filter - Fuel Gas Line - 10 SP-11005 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1107 | Piping Specialty Item Datasheet - Special Tee Fitting 30 inches - 10-SP-11007 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1108 | Piping Specialty Item Datasheet - Special Tee Fitting 20 inches - 10-SP-11008 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1109 | Piping Specialty Item Datasheet - Special Tee Fitting 16 inches - 10-SP-11009 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1110 | Piping Specialty Item Datasheet - Special Tee Fitting 12 inches - 10-SP-11010 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1111 | Piping Specialty Item Datasheet - Stop Check Valve - 10-SP-11011 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| PE | OL1-2P03-1112 | Piping Specialty Item Datasheet - 10-SP-11012 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01457
Return Date
Owner Cmmt*
| MP | OL1-2P03-1113 | Piping Specialty Item Datasheet - Vent Silencer - PSV-1144 Outlet - 10-SP-11013 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1114 | Piping Specialty Item Datasheet - Vent Silencer - Start up - 10-SP-11014 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| PE | OL1-2P03-1151 | Piping Specialty Item Datasheet - 10-BDV-11001 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01457
Return Date
Owner Cmmt*
| MP | OL1-2P03-1201 | PIPING SPECIALTY ITEM - DATA SHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-22; 2019-02-20: 2019-05-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1202 | SP/RO DATASHEETS - MIXING T |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1203 | SP/RO DATASHEETS - ANGLE VALVES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-22; 2019-02-20: 2019-05-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1204 | SP/RO DATASHEETS - SAMPLE COOLER |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-05-22; 2019-02-20: 2019-05-22
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1205 | SP/RO DATASHEETS - ISOKINETIC NOZZLE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-05-22; 2019-02-20: 2019-05-22
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1206 | SP/RO DATASHEETS - SILENCER |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-05-22; 2019-02-20: 2019-05-22
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1207 | Piping Specialty Item Datasheet - Special Tee Fitting 30 inches - 10-SP-12007-16007 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1208 | Piping Specialty Item Datasheet - Special Tee Fitting 20 inches - 10-SP-12008-16008 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1209 | Piping Specialty Item Datasheet - Special Tee Fitting 16 inches - 10-SP-12009-16009 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1211 | Piping Specialty Item Datasheet - Stop Check Valve - 10-SP-12011-16011 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| PE | OL1-2P03-1212 | Piping Specialty Item Datasheet - 10-SP-12012-16012 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01457
Return Date
Owner Cmmt*
| MP | OL1-2P03-1213 | Piping Specialty Item Datasheet - Vent Silencer - PSV-1244 Outlet - 10-SP-12013-16013 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| MP | OL1-2P03-1214 | Piping Specialty Item Datasheet - Vent Silencer - Start up - 10-SP-12014-16014 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01643
Return Date
Owner Cmmt*
| PE | OL1-2P03-1251 | Piping Specialty Item Datasheet - 10-BDV-12001-16001 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-01457
Return Date
Owner Cmmt*
| MP | OL1-2P03-1301 | PIPING SPECIALTY ITEM - DATA SHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-22; 2019-02-20: 2019-05-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1401 | PIPING SPECIALTY ITEM - DATA SHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-22; 2019-02-20: 2019-05-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1501 | PIPING SPECIALTY ITEM - DATA SHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-22; 2019-02-20: 2019-05-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1601 | PIPING SPECIALTY ITEM - DATA SHEETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-22; 2019-02-20: 2019-05-22
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-XXXA | AREA 30 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-XXXB | AREA 53 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-XXXC | AREA 55 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-XXXD | AREA 56 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-XXXX | SP ITEM DATA SHEETS, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-18; 2019-02-20: 2019-05-16
[6 empty] | Revised Plan | 2019-02-20: 2019-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P04 Piping design basic / philosophy / logic diagram
Category Code: P05 Piping calculation sheet / report
| MP | OL1-2P05-0002 | CRITICAL LINE LIST - COOLING WATER UNIT |  | Class 3 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-30; 2019-02-20: 2020-04-10
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0003 | CRITICAL LINE LIST - MAIN PIPE RACK |  | Class 3 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-30; 2019-02-20: 2020-04-10
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0004 | CRITICAL LINE LIST - OFF-SITES |  | Class 3 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-30; 2019-02-20: 2020-04-10
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0005 | CRITICAL LINE LIST - WASTE WATER TREATMENT |  | Class 3 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-30; 2019-02-20: 2020-04-10
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0006 | CRITICAL LINE LIST - FURNACES UTILITIES |  | Class 3 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-30; 2019-02-20: 2020-04-10
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0007 | CRITICAL LINE LIST - FRACTIONATION 1 & 2 |  | Class 3 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-30; 2019-02-20: 2020-04-10
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0008 | CRITICAL LINE LIST - FRACTIONATION 3 & BUTADIENE EXTRACTION |  | Class 3 | Purpose** | 2019-02-20: IDD; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-09-30; 2019-02-20: 2020-04-10
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0041 | Loads On Rack 10-PRK-0P01 |  | Class Final | Purpose** | 2019-02-20: IBD
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01228
[6 empty] | Return Date | 2019-02-20: 2019-04-26
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P05-0042 | Loads On Rack 10-PRK-0P02 |  | Class Final | Purpose** | 2019-02-20: IBD
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01439
Return Date
Owner Cmmt*
| MP | OL1-2P05-0043 | Loads On Rack 10-PRK-0P03 |  | Class Final | Purpose** | 2019-02-20: IBD
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01439
Return Date
Owner Cmmt*
| MP | OL1-2P05-1101 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1102 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1103 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1104 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1105 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1106 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1107 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1108 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1109 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1110 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1111 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1112 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1113 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1114 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1115 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1116 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1117 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1118 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1119 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1120 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1121 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1122 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1123 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1124 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1201 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1202 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1203 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1204 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1205 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1206 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1207 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1208 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1209 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1210 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1211 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1212 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1213 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1214 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1215 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1216 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1217 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1218 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1219 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1220 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1221 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1222 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1223 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1224 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1301 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1302 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1303 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1304 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1305 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1306 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1307 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1308 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1309 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1310 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1311 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1312 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1313 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1314 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1315 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1316 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1317 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1318 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1319 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1320 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1321 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1322 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1323 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1324 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1401 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1402 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1403 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1404 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1405 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1406 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1407 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1408 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1409 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1410 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1411 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1412 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1413 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1414 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1415 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1416 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1417 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1418 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1419 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1420 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1421 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1422 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1423 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1424 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1501 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1502 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1503 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1504 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1505 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1506 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1507 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1508 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1509 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1510 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1511 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1512 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1513 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1514 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1515 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1516 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1517 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1518 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1519 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1520 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1521 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1522 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1523 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1524 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1601 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1602 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1603 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1604 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1605 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1606 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1607 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1608 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1609 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1610 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1611 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1612 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1613 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1614 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1615 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1616 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1617 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1618 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1619 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1620 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1621 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1622 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1623 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1624 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-2001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 0C |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-03-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-2501 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5T |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-03-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-3001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 0P |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-03-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-4001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5R |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-03-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-4501 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5F |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-03-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-5001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5W |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-03-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-6001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 1B |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-03-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2A |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-03-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7201 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2B |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-03-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7401 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2D |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-03-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7601 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2E |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-03-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7801 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5U |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-03-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-8001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2C |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-03-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-8501 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 3A |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-03-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P06 Piping drawing
| MP | OL1-2P06-0001 | GENERAL PLOT PLAN |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-10
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0002 | DETAIL PLOT PLAN METERING STATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
[6 empty] | Revised Plan | 2019-02-20: 2019-05-28
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0003 | DETAIL PLOT-PLAN MAIN PIPE RACK |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0004 | DETAIL PLOT-PLAN ELECTRICAL SUB-STATION & FAR E |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
[6 empty] | Revised Plan | 2019-02-20: 2019-05-28
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0005 | DETAIL PLOT PLAN FURNACES |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
[6 empty] | Revised Plan | 2019-02-20: 2019-05-28
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0006 | DETAIL PLOT PLAN FURNACES AND AUXILIARIES |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01003
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0007 | DETAIL PLOT PLAN QUENCH |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0008 | DETAIL PLOT PLAN C3 HYDROGENATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0009 | DETAIL PLOT PLAN HOT FRACTIONATION / GHU UNIT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0010 | DETAIL PLOT PLAN PROCESS COLD COMPRESSORS |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0011 | DETAIL PLOT PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0012 | DETAIL PLOT PLAN BUTADIENE EXTRACTION UNIT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0013 | DETAIL PLOT-PLAN ELECTRICAL SUB-STATION & FAR C |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
[6 empty] | Revised Plan | 2019-02-20: 2019-05-28
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0014 | DETAIL PLOT PLAN FLARE UNIT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
[6 empty] | Revised Plan | 2019-02-20: 2019-05-28
[6 empty] | Issue Actual | 2019-02-20: 2019-03-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01031
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0015 | DETAIL PLOT PLAN COOLING WATER UNIT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0016 | DETAIL PLOT PLAN UTILITIES |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0017 | DETAIL PLOT PLAN WASTE WATER TREATMENT UNIT |  | Class 1 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-19; 2019-02-20: 2019-05-02; 2019-03-29: 2019-09-17; 2019-08-06: 2020-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P06-0020 | GENERAL KEY-PLAN |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0021 | DETAIL KEY-PLAN METERING STATION |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-15
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01468
Return Date
Owner Cmmt*
| MP | OL1-2P06-0022 | DETAIL KEY-PLAN MAIN PIPE RACK |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0023 | DETAIL KEY-PLAN ELECTRICAL SUB-STATION & FAR E |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-05-31; 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0024 | DETAIL KEY-PLAN FURNACES |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0025 | DETAIL KEY-PLAN FURNACES AUXILIARIES |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0026 | DETAIL KEY-PLAN QUENCH |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0027 | DETAIL KEY-PLAN C3 HYDROGENATION |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0028 | DETAIL KEY-PLAN HOT FRACTIONATION / GHU DETAIL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0029 | DETAIL KEY-PLAN COLD COMPRESSORS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0030 | DETAIL KEY-PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0031 | DETAIL KEY-PLAN BUTADIENE EXTRACTION DETAIL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-05-31; 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0032 | DETAIL KEY-PLAN ELECTRICAL SUB-STATION & FAR C |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-05-31; 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0033 | DETAIL KEY-PLAN FLARE DETAIL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-05-31; 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0034 | DETAIL KEY-PLAN COOLING WATER DETAIL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0035 | DETAIL KEY-PLAN UTILITIES |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0036 | DETAIL KEY-PLAN WASTE WATER TREATMENT DETAIL |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IDD; 2019-08-06: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-29; 2019-02-20: 2019-05-09; 2019-03-29: 2019-09-30; 2019-08-06: 2020-04-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0040 | UTILITY STATION PLOT PLAN MAIN PIPE RACK |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0041 | UTILITY STATION PLOT PLAN FURNACES AUXILIARIES |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0042 | UTILITY STATION PLOT PLAN QUENCH |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0043 | UTILITY STATION PLOT PLAN C3 HYDROGENATION |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0044 | UTILITY STATION PLOT PLAN HOT FRACTIONATION / GHU UNIT |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0045 | UTILITY STATION PLOT PLAN COLD COMPRESSORS |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0046 | UTILITY STATION PLOT PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0047 | UTILITY STATION PLOT PLAN BUTADIENE EXTRACTION UNIT |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0048 | UTILITY STATION PLOT PLAN FLARE UNIT |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0049 | UTILITY STATION PLOT PLAN COOLING WATER UNIT |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0050 | UTILITY STATION PLOT PLAN UTILITIES |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0051 | UTILITY STATION PLOT PLAN WASTE WATER TREATMENT UNIT |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0060 | STEAM TRACING MANIFOLDS LOCATION PLAN MAIN PIPE RACK |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-09-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0061 | STEAM TRACING MANIFOLDS LOCATION PLAN QUENCH |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-09-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0062 | STEAM TRACING MANIFOLDS LOCATION PLAN C3 HYDROGENATION |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-09-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0063 | STEAM TRACING MANIFOLDS LOCATION PLAN HOT FRACTIONATION / GHU UNIT |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-09-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0064 | STEAM TRACING MANIFOLDS LOCATION PLAN COLD COMPRESSORS |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-09-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0065 | STEAM TRACING MANIFOLDS LOCATION PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-09-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0066 | STEAM TRACING MANIFOLDS LOCATION PLAN BUTADIENE EXTRACTION UNIT |  | Class 3 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-09-01
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0070 | GAD KEY-PLAN MAIN PIPE RACK |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LPSA1-T-MP-01394
Return Date
Owner Cmmt*
| MP | OL1-2P06-0071 | GAD KEY-PLAN METERING STATION |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0072 | GAD KEY-PLAN ELECTRICAL SUB-STATION & FAR E |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0073 | GAD KEY-PLAN FURNACES AUXILIARIES |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LPSA1-T-MP-01394
Return Date
Owner Cmmt*
| MP | OL1-2P06-0074 | GAD KEY-PLAN QUENCH |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LPSA1-T-MP-01394
Return Date
Owner Cmmt*
| MP | OL1-2P06-0075 | GAD KEY-PLAN C3 HYDROGENATION |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LPSA1-T-MP-01394
Return Date
Owner Cmmt*
| MP | OL1-2P06-0076 | GAD KEY-PLAN HOT FRACTIONATION / GHU UNIT |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LPSA1-T-MP-01394
Return Date
Owner Cmmt*
| MP | OL1-2P06-0077 | GAD KEY-PLAN COLD COMPRESSORS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LPSA1-T-MP-01394
Return Date
Owner Cmmt*
| MP | OL1-2P06-0078 | GAD KEY-PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LPSA1-T-MP-01394
Return Date
Owner Cmmt*
| MP | OL1-2P06-0079 | GAD KEY-PLAN BUTADIENE EXTRACTION UNIT |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LPSA1-T-MP-01394
Return Date
Owner Cmmt*
| MP | OL1-2P06-0080 | GAD KEY-PLAN ELECTRICAL SUB-STATION & FAR C |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0081 | GAD KEY-PLAN FLARE UNIT |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LPSA1-T-MP-01394
Return Date
Owner Cmmt*
| MP | OL1-2P06-0082 | GAD KEY-PLAN FLARE LINES ROUTING |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0083 | GAD KEY-PLAN COOLING WATER UNIT |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LPSA1-T-MP-01394
Return Date
Owner Cmmt*
| MP | OL1-2P06-0084 | GAD KEY-PLAN UTILITIES |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LPSA1-T-MP-01394
Return Date
Owner Cmmt*
| MP | OL1-2P06-0085 | STD.AUX.PIPE SUPPORTS COLLECTION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2020-11-20; 2019-02-20: 2021-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LPSA1-T-MP-01394
Return Date
Owner Cmmt*
| MP | OL1-2P06-0086 | GAD KEY-PLAN WASTE WATER TREATMENT UNIT |  | Class 3 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LPSA1-T-MP-01394
Return Date
Owner Cmmt*
| MP | OL1-2P06-2000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 0C |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-2500 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5T |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-2901 | MISC ENGINEERED SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-19; 2019-02-20: 2019-12-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-2902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  | Class 3 | Purpose** | 2019-02-20: IFD; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-09; 2019-02-20: 2019-08-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-3000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 0P |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-3901 | MISC ENGINEERED SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-19; 2019-02-20: 2019-12-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-3902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  | Class 3 | Purpose** | 2019-02-20: IFD; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-09; 2019-02-20: 2019-08-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-4500 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5F |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-4901 | MISC ENGINEERED SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-19; 2019-02-20: 2019-12-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-4902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  | Class 3 | Purpose** | 2019-02-20: IFD; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-09; 2019-02-20: 2019-08-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2C |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5500 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 3A |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5901 | MISC ENGINEERED SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-19; 2019-02-20: 2019-12-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  | Class 3 | Purpose** | 2019-02-20: IFD; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-09; 2019-02-20: 2019-08-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-6000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 1B |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-6901 | MISC ENGINEERED SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-19; 2019-02-20: 2019-12-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-6902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  | Class 3 | Purpose** | 2019-02-20: IFD; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-09; 2019-02-20: 2019-08-06
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2A |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7200 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2B |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7400 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2D |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7600 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2E |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7800 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5U |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-8000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5W |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P07 Piping certification, inspection and test record |  |  |  |  | Class 1 | Purpose**
Category Code: P08 Piping Material Take-off (MTO) | [5 empty] | Rev.
Category Code: P09 Painting Material Take-off (MTO) | [5 empty] | Issue Plan
Category Code: P10 Insulation Material Take-off (MTO) | [5 empty] | Revised Plan
| MP | OL1-2P10-10XX | FURNACE 10-H-1100 LARGE BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1100 LARGE BORE ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-10YY | FURNACE 10-H-1100 SMALL BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1100 SMALL BORE ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-20XX | FURNACE 10-H-1200 LARGE BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1200 LARGE BORE ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-20YY | FURNACE 10-H-1200 SMALL BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1200 SMALL BORE ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-30XX | FURNACE 10-H-1300 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1300 ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-40XX | FURNACE 10-H-1400 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1400 ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-50XX | FURNACE 10-H-1500 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1500 ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-60XX | FURNACE 10-H-1600 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1600 ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | 2019-02-20: IFI
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAA | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAB | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAC | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAD | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAE | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAF | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAG | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAH | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAI | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAJ | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAK | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAL | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAM | ISO.SKETCHES PIPE-RACK |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXA | ISO.SKETCHES |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXB | ISO.SKETCHES |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXC | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXD | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXE | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXF | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXG | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXH | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXI | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXJ | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXK | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXL | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXM | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXN | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXO | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXP | ISO.SKETCHES CWR HEADER |  | Class 3 | Purpose** | 2019-02-20: IFC1; 2019-02-20: IFC2; 2019-03-29: IFC3; 2019-08-06: IFC4
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-08-30; 2019-02-20: 2020-10-08; 2019-03-29: 2020-11-16; 2019-08-06: 2021-02-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P20 Aboveground Piping General Arrangement Drawings
| MP | OL1-2P20-0100 | GAD (N...) |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0101 | GAD BATTERY LIMIT OL1-A |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0200 | GAD (N...) |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0300 | GAD (N...) |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0400 | GAD (N...) |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-1000 | GAD (N...) |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2200 | GAD (N...) |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2300 | GAD (N...) |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2301 | GAD BATTERY LIMIT OU1-A |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2400 | GAD (N...) |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2500 | GAD (N...) |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-3000 | GAD (N...) |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5100 | GAD (N...) |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5200 | GAD (N...) |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5300 | GAD (N...) |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5400 | GAD (N...) |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5500 | GAD (N...) |  | Class 3 | Purpose** | 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P21 Underground Piping General Arrangement Drawings
Category Code: P22 Aboveground Piping Isometric Drawings
Category Code: P23 Underground Piping Isometric Drawings
Category Code: P25 Pipe support drawing
| MP | OL1-2P25-0085 | Standard Auxiliary Piping Support Collection |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-31; 2019-02-20: 2019-02-28
[6 empty] | Revised Plan | 2019-02-20: 2019-05-31
[6 empty] | Issue Actual | 2019-02-20: 2019-02-20
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00896
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
Category Code: P30 3D Model Review File
| MP | OL1-2P30-0014 | Model Review Report Furnace Island Action List 30 Percent |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01331
Return Date
Owner Cmmt*
| MP | OL1-P30-0002 | AUX.PIPE SUPP.LIST & BILL OF MTL - COOLING WATER UNIT |  | Class 3 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2; 2019-08-06: IFC3
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-P30-0003 | AUX.PIPE SUPP.LIST & BILL OF MTL - MAIN PIPE RACK |  | Class 3 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2; 2019-08-06: IFC3
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-P30-0004 | AUX.PIPE SUPP.LIST & BILL OF MTL - OFF-SITES |  | Class 3 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2; 2019-08-06: IFC3
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-P30-0005 | AUX.PIPE SUPP.LIST & BILL OF MTL - WASTE WATER TREATMENT |  | Class 3 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2; 2019-08-06: IFC3
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-P30-0006 | AUX.PIPE SUPP.LIST & BILL OF MTL - FURNACES UTILITIES |  | Class 3 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2; 2019-08-06: IFC3
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-P30-0007 | AUX.PIPE SUPP.LIST & BILL OF MTL - FRACTIONATION 1 & 2 |  | Class 3 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2; 2019-08-06: IFC3
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-P30-0008 | AUX.PIPE SUPP.LIST & BILL OF MTL - FRACTIONATION 3 & BUTADIENE EXTRACTION |  | Class 3 | Purpose** | 2019-02-20: IFC; 2019-02-20: IFC1; 2019-03-29: IFC2; 2019-08-06: IFC3
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-21; 2019-02-20: 2020-07-29; 2019-03-29: 2020-11-16; 2019-08-06: 2021-03-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P40 Piping Generic Lists
| MP | OL1-2P40-0007 | TIE-INS / INTERFACE POINTS LIST |  | Class 2 | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-20 | 2019-08-06 | 2019-11-12 | 2020-02-07 | 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P40-0008 | STEAM TRACING MANIFOLD LIST |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-12; 2019-02-20: 2020-03-20; 2019-03-29: 2020-04-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P71 Appraisal Report for Consultancy Service
Category Code: P72 Appraisal Report for EPC Contractor Work
Category Code: P73 Appraisal Report for Vendor/Supplier
Category Code: P90 Vendor Document/drawings
Category Code: P91 Index/List
| MP | OL1-2P91-1001 | LINE LIST - OLEFINS PROCESS AREA 10 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-01
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01541
Return Date
Owner Cmmt*
| MP | OL1-2P91-1101 | LINE DESIGNATION TABLE - FURNACE AREA |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-10; 2019-02-20: 2019-02-15; 2019-03-29: 2019-06-10; 2019-08-06: 2019-09-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00933
Return Date
Owner Cmmt*
| MP | OL1-2P91-1201 | LINE DESIGNATION TABLE - FURNACE AREA |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD; 2019-03-29: IFD; 2019-08-06: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-10; 2019-02-20: 2019-02-15; 2019-03-29: 2019-06-10; 2019-08-06: 2019-09-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00934
Return Date
Owner Cmmt*
| MP | OL1-2P91-1301 | LINE DESIGNATION TABLE - FURNACE AREA |  | Class 2 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-1401 | LINE DESIGNATION TABLE - FURNACE AREA |  | Class 2 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-1501 | LINE DESIGNATION TABLE - FURNACE AREA |  | Class 2 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-1601 | LINE DESIGNATION TABLE - FURNACE AREA |  | Class 2 | Purpose** | 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-24
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-1901 | Line Designation Table - Furnace Auxiliaries |  | Class Final | Purpose** | 2019-02-20: IBD
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP -01375
Return Date
Owner Cmmt*
| MP | OL1-2P91-2001 | LINE LIST - OLEFINS PROCESS AREA 20 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01450
Return Date
Owner Cmmt*
| MP | OL1-2P91-2101 | LINE LIST - OLEFINS PROCESS AREA 21 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01497
Return Date
Owner Cmmt*
| MP | OL1-2P91-2201 | LINE LIST - OLEFINS PROCESS AREA 22 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP -01375
Return Date
Owner Cmmt*
| MP | OL1-2P91-2301 | LINE LIST - OLEFINS PROCESS AREA 23 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP -01375
Return Date
Owner Cmmt*
| MP | OL1-2P91-2401 | LINE LIST - OLEFINS PROCESS AREA 24 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-30
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01531
Return Date
Owner Cmmt*
| MP | OL1-2P91-2501 | LINE LIST - OLEFINS PROCESS AREA 25 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01466
Return Date
Owner Cmmt*
| MP | OL1-2P91-2601 | LINE LIST - OLEFINS PROCESS AREA 26 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-04-04 | 2019-04-25 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-05-28
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01651
Return Date
Owner Cmmt*
| MP | OL1-2P91-2701 | LINE LIST - OLEFINS PROCESS AREA 27 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-04-04 | 2019-04-25 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-05-28
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP -01656
Return Date
Owner Cmmt*
| MP | OL1-2P91-2801 | LINE LIST - OLEFINS PROCESS AREA 28 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01497
Return Date
Owner Cmmt*
| MP | OL1-2P91-2901 | LINE LIST - OLEFINS PROCESS AREA 29 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01620
Return Date
Owner Cmmt*
| MP | OL1-2P91-3001 | LINE LIST - OLEFINS PROCESS AREA 30 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-04-04 | 2019-04-25 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-05-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-5001 | LINE LIST - OLEFINS UTILITY AREA 50 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-04-04 | 2019-04-25 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-05-28
[6 empty] | Issue Actual | 2019-02-20: 2019-05-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01620
Return Date
Owner Cmmt*
| MP | OL1-2P91-5101 | Line Designation Table - BFW - Steam - Steam Condensate System |  | Class Final | Purpose** | 2019-02-20: IBD
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP -01656
Return Date
Owner Cmmt*
| MP | OL1-2P91-5201 | Line Designation Table - Fuel System |  | Class Final | Purpose** | 2019-02-20: IBD
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01627
Return Date
Owner Cmmt*
| MP | OL1-2P91-5301 | LINE LIST - OLEFINS UTILITY AREA 53 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-04-04 | 2019-04-25 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-05-28
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP -01656
Return Date
Owner Cmmt*
| MP | OL1-2P91-5401 | Line Designation Table - Plant Air - Instrument Air - Nitrogen |  | Class Final | Purpose** | 2019-02-20: IBD
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01627
Return Date
Owner Cmmt*
| MP | OL1-2P91-5501 | LINE LIST - OLEFINS UTILITY AREA 55 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-04-04 | 2019-04-25 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-05-28
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP -01648
Return Date
Owner Cmmt*
| MP | OL1-2P91-5601 | LINE LIST - OLEFINS UTILITY AREA 56 |  | Class 3 | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-04-04 | 2019-04-25 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-05-28
[6 empty] | Issue Actual | 2019-02-20: 2019-05-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP -01656
Return Date
Owner Cmmt*
| MP | OL1-2P91-5901 | Line Designation Table - Supporting Utilities Auxiliaries |  | Class Final | Purpose** | 2019-02-20: IBD
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01620
Return Date
Owner Cmmt*
Category Code: P92 Procedures & Standards
| MP | OL1-2P92-0001 | PIPING STANDARD ASSEMBLY COLLECTION |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-02-28; 2019-02-20: 2019-03-17
[6 empty] | Revised Plan | 2019-02-20: 2019-05-28; 2019-02-20: 2019-06-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P92-0002 | Piping Design Standard Drawings |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: CAN
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-08; 2019-02-20: 2018-11-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00012; 2019-02-20: TPSK-LSPA1-T-MP-00325
[6 empty] | Return Date | 2019-02-20: 2018-09-26; 2019-02-20: 2018-12-07
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2P92-0003 | Piping Construction Drawing |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: CAN
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-08; 2019-02-20: 2018-11-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00012; 2019-02-20: TPSK-LSPA1-T-MP-00325
[6 empty] | Return Date | 2019-02-20: 2018-09-26; 2019-02-20: 2018-12-07
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2P92-0004 | JOB CONSTRUCTION SPECIFICATION FOR BOLTED FLANGED JOINT ASSEMBLY |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-04-06; 2019-02-20: 2019-05-06
[6 empty] | Revised Plan | 2019-02-20: 2019-08-06
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01635
Return Date
Owner Cmmt*
| MP | OL1-2P92-0007 | CONSTRUCTION SPECIFICATION FOR PIPING PREFABRICATION, ERECTION AND NON DESTRUCTIVE TESTING |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-04-16; 2019-02-20: 2019-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00917
[6 empty] | Return Date | 2019-02-20: 2019-05-07
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P92-0008 | HYDROSTATIC LEAK TESTING FOR PIPING SYSTEMS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-04-16; 2019-02-20: 2019-06-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01136
[6 empty] | Return Date | 2019-02-20: 2019-04-11
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2P92-0012 | SPECIAL TECH.SPEC.PIP.PREFAB. & ERE. |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-30; 2019-02-20: 2019-03-15
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P93 Policy , Guidelines & Memo
Category Code: P94 Forms & Templates
Category Code: P95 Progress/Status Reports
Category Code: Q07 Quality Audit Reports
Category Code: Q10 QC Record and Report for Civil work (Engineerig and Procurement)
Category Code: Q11 QC Record and Report for Building work (Engineerig and Procurement)
Category Code: Q12 QC Record and Report for Steel Structure work (Engineerig and Procurement)
Category Code: Q13 QC Record and Report for Mechanical work (Engineerig and Procurement)
Category Code: Q14 QC Record and Report for Piping work (Engineerig and Procurement)
Category Code: Q15 QC Record and Report for Fire Fighting work (Engineerig and Procurement)
Category Code: Q16 QC Record and Report for Electrical work (Engineerig and Procurement)
Category Code: Q17 QC Record and Report for Instrumentation work (Engineerig and Procurement)
Category Code: Q20 QC Record and Report for Civil work (construction)
| QM | OL1-2Q20-0001 | Quality Control Plan Civil Works-Fencing |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00488
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0002 | Quality Control Plan Civil Works-Bored Cast In Situ Piles |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0003 | Quality Control Plan Civil Works-Continuous Flight Auger Piles |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0004 | Quality Control Plan Civil Works-Concrete Precast Driven Piles |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0005 | Quality Control Plan Civil Works-Earth Moving |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0006 | Quality Control Plan Civil Works-Asphalt Roads And Yards |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0007 | Quality Control Plan U-G Civil Works-Sewers |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0008 | Quality Control Plan Non Metallic Pressure Piping Installation - Above and Underground |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00625
Return Date
Owner Cmmt*
| QM | OL1-2Q20-0009 | Quality Control Plan Civil Works-Reinforced Concrete For Foundation-Elevation Structures And Basins |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0010 | Quality Control Plan Civil Works-Prefabrication of Concrete Elements |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0011 | Quality Control Plan Precast Pipe-Rack Erection |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0012 | Quality Control Plan Civil Works-Tank Rings Foundations |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0013 | Quality Control Plan Above Ground Civil Works- Concrete Elements Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0014 | Quality Control Plan Civil Works-Rigid Paving |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0015 | Quality Control Plan U-G Civil Works-Installation of Concrete Pits Cable Duct Banks Trenches-Ditches Cable Trenches Direct Buried Box Culverts and Lighting Poles Foundations |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0016 | Quality Control Plan Civil Works-Concrete Structure for Cooling Tower |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0017 | Quality Control Plan Civil Works-Fire Proofing |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0018 | Quality Control Plan Civil Works-Grouting |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q20-0019 | Quality Control Plan Concrete Protective Coating |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
Category Code: Q21 QC Record and Report for Building work (construction)
| QM | OL1-2Q21-0001 | Quality Control Plan Building -Concrete And Masonry- |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01596
Return Date
Owner Cmmt*
Category Code: Q22 QC Record and Report for Steel Structure work (construction)
| QM | OL1-2Q22-0001 | Quality Control Plan Steel Structures Erection |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q22-0002 | Quality Control Plan Secondary Steel Structures Erection - Ladders Platforms Walkways Handrails Gratings |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00735
[6 empty] | Return Date | 2019-02-20: 2019-03-18
Owner Cmmt* | bar: 2019-02-20
Category Code: Q23 QC Record and Report for Mechanical work (construction)
| QM | OL1-2Q23-0001 | Quality Control Plan Fixed Roof Tanks Erection |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00942
Return Date
Owner Cmmt*
| QM | OL1-2Q23-0002 | Quality Control Plan Floating Roof Tanks Erection |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00942
Return Date
Owner Cmmt*
| QM | OL1-2Q23-0003 | Quality Control Plan Cryogenic Tanks Erection |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00942
Return Date
Owner Cmmt*
| QM | OL1-2Q23-0006 | Quality Control Plan Static Equipment Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q23-0007 | Quality Control Plan Package Furnace - Site Assembled - Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q23-0008 | Quality Control Plan Flare System Erection |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q23-0009 | Quality Control Plan Refractory Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q23-0010 | Quality Control Plan Machinery Installation - Centrifugal and Rotary Pumps |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q23-0011 | Quality Control Plan Machinery Installation - Blower and Fans |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q23-0012 | Quality Control Plan Machinery Installation - Centrifugal Compressors |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q23-0013 | Quality Control Plan Machinery Installation - Reciprocating Compressors |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q23-0014 | Quality Control Plan Machinery Installation - Mixers and Agitators |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q23-0015 | Quality Control Plan Elevator Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q23-0016 | Quality Control Plan Equipment Internals Installation - Trays |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
Return Date
Owner Cmmt*
| QM | OL1-2Q23-0017 | Quality Control Plan Equipment Internals Installation - Distributors-Grids-Demisters-etc |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q23-0018 | Quality Control Plan Air Coolers Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01091
Return Date
Owner Cmmt*
| QM | OL1-2Q23-0019 | Quality Control Plan Cooling Tower Mechanical Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q23-0020 | Quality Control Plan Packages Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q23-0021 | Quality Control Plan Skid Mounted Packages |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q23-0022 | Quality Control Plan Bridge Crane Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | 2019-02-20: 2019-04-01
Owner Cmmt* | bar: 2019-02-20
Category Code: Q24 QC Dossier for Piping work (construction)
| QM | OL1-2Q24-0001 | Quality Control Plan Piping Prefabrication |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q24-0002 | Quality Control Plan Piping Support Prefabrication |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q24-0003 | Quality Control Plan Piping Erection - Above & Underground |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q24-0004 | Quality Control Plan Piping Support Erection |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q24-0005 | Quality Control Plan Steam Tracing System |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q24-0006 | Quality Control Plan Piping Tie-ins |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q24-0007 | Quality Control Plan Piping NDE PWHT Management |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q24-0008 | Quality Control Plan Welders Management |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q24-0009 | Quality Control Plan Insulation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
| QM | OL1-2Q24-0010 | Quality Control Plan Painting |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20
Category Code: Q25 QC Record and Report for Fire Fighting work (construction)
| QM | OL1-2Q25-0001 | Quality Control Plan Fire Fighting System Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01596
Return Date
Owner Cmmt*
Category Code: Q26 QC Record and Report for Electrical work (construction)
| QM | OL1-2Q26-0009 | Quality Control Plan Building HVAC -Heating Ventilation And Air Conditioning- System Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01596
Return Date
Owner Cmmt*
Category Code: Q27 QC Record and Report for Instrumentation work (construction)
| QM | OL1-2Q27-0001 | Quality Control Plan - Instrumentation And Communication System - Installation Works In Control Room |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01636
Return Date
Owner Cmmt*
| QM | OL1-2Q27-0002 | Quality Control Plan - Instrumentation And Communication System Installation - Instrument Cables Junction Boxes And Local Panels Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01636
Return Date
Owner Cmmt*
| QM | OL1-2Q27-0003 | Quality Control Plan - Instrumentation And Communication System Installation - Field Instrumentation Works |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01636
Return Date
Owner Cmmt*
| QM | OL1-2Q27-0004 | Quality Control Plan - Instrumentation And Communication System Installation - Analyzer Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01636
Return Date
Owner Cmmt*
| QM | OL1-2Q27-0005 | Quality Control Plan - Instrumentation And Communication System Installation - Telecommunication Systems Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01636
Return Date
Owner Cmmt*
| QM | OL1-2Q27-0006 | Quality Control Plan - Instrumentation And Communication System Installation - Package Instrumentation Test |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01636
Return Date
Owner Cmmt*
Category Code: Q30 Shop Inspection Notice (Civil)
Category Code: Q31 Shop Inspection Notice (Mechanical)
Category Code: Q32 Shop Inspection Notice (Piping)
Category Code: Q33 Shop Inspection Notice (Electrical)
Category Code: Q34 Shop Inspection Notice (Instrumentation)
Category Code: Q35 Mechanical certification (Civil)
Category Code: Q36 Mechanical certification (Static)
Category Code: Q37 Mechanical certification (Rotating)
Category Code: Q38 Mechanical certification (Piping))
Category Code: Q40 Site Inspection Notice (Civil)
Category Code: Q41 Site Inspection Notice (Mechanical)
Category Code: Q42 Site Inspection Notice (Piping)
Category Code: Q43 Site Inspection Notice (Electrical)
Category Code: Q44 Site Inspection Notice (Instrumentation)
Category Code: Q60 Inspection and Test Plan (ITP) for Mechanical Work
Category Code: Q61 Inspection and Test Plan (ITP) for Piping Work
Category Code: Q62 Inspection and Test Plan (ITP) for Electrical work
Category Code: Q63 Inspection and Test Plan (ITP)for Instrumentation work
Category Code: Q64 Inspection and Test Plan (ITP) for Civil,Structure and Architecture.
Category Code: Q65 Inspection and Test Plan (ITP) for Mechanical Work (Construction)
Category Code: Q66 Inspection and Test Plan (ITP) for Piping Work (Construction)
Category Code: Q67 Inspection and Test Plan (ITP) for Electrical work (Construction)
Category Code: Q68 Inspection and Test Plan (ITP)for Instrumentation work (Construction)
Category Code: Q69 Inspection and Test Plan (ITP) for Civil,Structure and Architecture (Construction)
Category Code: Q71 Appraisal Report for Consultancy Service
Category Code: Q72 Appraisal Report for EPC Contractor Work
Category Code: Q73 Appraisal Report for Vendor/Supplier
Category Code: Q90 Vendor Document/drawings
Category Code: Q91 Index/List
Category Code: Q92 Procedures & Standards
| QM | OL1-2Q92-0008 | Quality Control Plan Material Management and Warehouse |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-00818
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0011 | Job Construction Specification For Welders Management |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01236
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0012 | Job Construction Specification For Welding Activities Management |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01236
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0013 | Job Construction Specification For Piping Material Traceability |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01236
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0014 | Job Construction Specification For Bolted Flange Joint Assembly Management During Construction Precommissioning And Commissioning |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01306
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0017 | Job Construction Specification For Material Receiving And Warehousting |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01597
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0018 | Job Construction Specification For Static Equipment and Trays-Internals Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01237
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0019 | Job Construction Specification For Machinery And Air Coolers Installation |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-10
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-QM-01305
Return Date
Owner Cmmt*
Category Code: Q93 Policy , Guidelines,& Memo
Category Code: Q94 Forms & Templates
Category Code: Q95 Progress/Status Reports
Category Code: Q96 Quality Audit Reports
Category Code: Q97 Non-Conformance Record
Category Code: Q98 Addition Vendors/Subcontractors Assessment and Prequalification Report
Category Code: R01 Process Specification (PE)
Category Code: R02 Civil Specification (CV)
| CV | OL1-2R02-0001 | JOB DES.SPEC.FOR UNDERG.SYSTEM |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-24; 2019-02-20: 2019-03-16
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-25; 2019-02-20: 2019-03-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00087; 2019-02-20: TPSK-LSPA1-T-CV-00994
[6 empty] | Return Date | 2019-02-20: 2018-11-02; 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| CV | OL1-2R02-0002 | JOB DESIGN SPECIFICATION FOR GEOTECHNICAL RECOMMENDATIONS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-02-15; 2019-02-20: 2019-10-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01598
Return Date
Owner Cmmt*
| CV | OL1-2R02-0004 | JSD FOR FOUNDATION & STRUCT. |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-25; 2019-02-20: 2019-01-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-25; 2019-02-20: 2019-02-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00087; 2019-02-20: TPSK-LSPA1-T-CV-00887
[6 empty] | Return Date | 2019-02-20: 2018-11-02; 2019-02-20: 2019-03-18
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| CV | OL1-2R02-0005 | AMENDMENT - CV-012 - BUILDING DESIGN AND CONSTRUCTION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-10-10; 2019-02-20: 2019-01-15
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
[6 empty] | Issue Actual | 2019-02-20: 2018-10-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-00158
[6 empty] | Return Date | 2019-02-20: 2019-03-18
Owner Cmmt* | bar: 2019-02-20
| CV | OL1-2R02-0006 | JOB SUPPLY SPEC.FOR STEEL STRUCT. |  | Class 2 | Purpose** | 2019-02-20: IFQ; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-10-16
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2R02-0011 | Geotechnical Factual Report |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-02-15; 2019-02-20: 2019-10-08
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LPSA1-T-CV-01549
Return Date
Owner Cmmt*
| CV | OL1-2R02-0101 | Technical Specification For Piles |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-15; 2019-02-20: 2019-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2R02-0102 | Technical Specification for Civil Works |  | Class Final | Purpose** | 2019-02-20: IFQ; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-06-14; 2019-02-20: 2019-07-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01666
Return Date
Owner Cmmt*
| CV | OL1-2R02-0103 | Technical Specification for Precast Concrete Pipe-Racks |  | Class Final | Purpose** | 2019-02-20: IFQ; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-04-30; 2019-02-20: 2019-08-31
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01666
Return Date
Owner Cmmt*
| CV | OL1-2R02-0104 | Technical Specification For Steel Structures Erection |  | Class Final | Purpose** | 2019-02-20: IFQ; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-10-16
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-CV-01666
Return Date
Owner Cmmt*
Category Code: R03 Mechanical Specification (ME)
| ME | OL1-2R03-0001 | WELDING AND NDE FOR PRESSURE VESSELS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-04-06; 2019-02-20: 2019-05-06
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-27; 2019-02-20: 2019-02-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00029; 2019-02-20: TPSK-LSPA1-T-ME-00921
[6 empty] | Return Date | 2019-02-20: 2018-09-19; 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-0002 | JOB SUPPLY SPECIFICATION FOR MATERIAL IN SOUR SERVICE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-04-06; 2019-02-20: 2019-05-06
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14
[6 empty] | Issue Actual | 2019-02-20: 2018-08-27; 2019-02-20: 2019-02-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00029; 2019-02-20: TPSK-LSPA1-T-ME-00921
[6 empty] | Return Date | 2019-02-20: 2018-09-19; 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-0003 | JOB SUPPLY SPECIFICATION FOR POSITIVE MATERIAL IDENTIFICATION ON EQUIPMENT & PIPING |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-04-06; 2019-02-20: 2019-05-06
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-27; 2019-02-20: 2019-02-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00029; 2019-02-20: TPSK-LSPA1-T-ME-00921
[6 empty] | Return Date | 2019-02-20: 2018-09-19; 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-0004 | WELDING AND NDE FOR TANKS STORAGE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-04-06; 2019-02-20: 2019-05-06
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-27; 2019-02-20: 2019-02-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00029; 2019-02-20: TPSK-LSPA1-T-ME-00921
[6 empty] | Return Date | 2019-02-20: 2018-09-19; 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-0005 | ME-005 Double Jacket Pipe Heat Exchangers for 36M and 132U Furnace |  | Class Final | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00212
Return Date
Owner Cmmt*
| ME | OL1-2R03-0006 | PLATE HEAT EXCHANGER |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-10; 2019-02-20: 2018-09-24
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00042
Return Date
Owner Cmmt*
| ME | OL1-2R03-0007 | Job Specification for AXENS Standard Material Specifications - Carbon Steels For Pressure Service |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00909
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2R03-0008 | Job Specification For Axens Standard Material Specifications - Low Alloyed Steels For Pressure Vessels |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00909
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2R03-0009 | Job Specification For Axens Standard Material Specifications For Wet H2S Service |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00909
[6 empty] | Return Date | 2019-02-20: 2019-03-15
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2R03-0010 | ME-010 Centrifugal Pump |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-24; 2019-02-20: 2019-01-22
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00078; 2019-02-20: TPSK-LSPA1-T-ME-00693
[6 empty] | Return Date | 2019-02-20: 2018-10-12; 2019-02-20: 2019-02-14
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-0011 | ME-011 RECIPROCATING PUMP |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01459
Return Date
Owner Cmmt*
| ME | OL1-2R03-0013 | ME-013 Diesel Engine |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-18; 2019-02-20: 2019-01-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00196; 2019-02-20: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | 2019-02-20: 2018-11-02; 2019-02-20: 2019-04-25
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-0014 | ME-014 Centrifugal Compressor |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-18; 2019-02-20: 2019-01-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00065; 2019-02-20: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | 2019-02-20: 2018-10-10; 2019-02-20: 2019-04-25
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-0016 | ME-016 Centrifugal Compressor For PA-IA Servise |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-12; 2019-02-20: 2019-01-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00164; 2019-02-20: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | 2019-02-20: 2018-11-07; 2019-02-20: 2019-04-25
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-0017 | ME-017 Root Blower |  | Class Final | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00334
Return Date
Owner Cmmt*
| ME | OL1-2R03-0018 | ME-018 General Purpose Steam Turbines |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-24; 2019-02-20: 2019-01-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00078; 2019-02-20: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | 2019-02-20: 2018-10-12; 2019-02-20: 2019-04-25
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-0019 | ME-019 Lube Oil Unit And Seal Oil System |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-18; 2019-02-20: 2019-01-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00065; 2019-02-20: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | 2019-02-20: 2018-10-10; 2019-02-20: 2019-04-25
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-0020 | ME-020 Special Purpose Steam Tturbines |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-24; 2019-02-20: 2019-01-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00078; 2019-02-20: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | 2019-02-20: 2018-10-12; 2019-02-20: 2019-04-25
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-0021 | ME-021 Flare System |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00429
[6 empty] | Return Date | 2019-02-20: 2018-12-26
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2R03-0022 | ME-022 Special Purpose Gear |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-12; 2019-02-20: 2019-01-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00166; 2019-02-20: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | 2019-02-20: 2018-11-07; 2019-02-20: 2019-04-25
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-0024 | ME-024 Elevator For 36M and 132U Furnace |  | Class Final | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-20
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00537
Return Date
Owner Cmmt*
| ME | OL1-2R03-0028 | ME-028 Mechanical Seal |  | Class Final | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00057
Return Date
Owner Cmmt*
| ME | OL1-2R03-0029 | ME-029 Centrifugal Blower for 36M and 132U Furnace |  | Class Final | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00185
[6 empty] | Return Date | 2019-02-20: 2018-11-05
Owner Cmmt*
| MP | OL1-2R03-0030 | Job Sprcification For Supply And Fabrication Of Grade 91 Alloy Steel Piping |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01465
Return Date
Owner Cmmt*
| ME | OL1-2R03-0047 | ME-047 Dry Screw Compressor for Hydrocarbon Services |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-06; 2019-02-20: 2019-01-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00429; 2019-02-20: TPSK-LSPA1-T-ME-00666
[6 empty] | Return Date | 2019-02-20: 2018-12-26; 2019-02-20: 2019-02-04
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-0050 | JOB SPEC. FOR DESIGN OF PRESSURE & ATMOSPHERIC EQUIPMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IMP; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: B; 2019-03-29: 0; 2019-08-06: 1
[6 empty] | Issue Plan | 2019-02-20: 2018-08-10; 2019-02-20: 2018-08-10; 2019-03-29: 2018-09-20; 2019-08-06: 2018-09-20
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-10; 2019-02-20: 2018-09-25; 2019-03-29: 2018-10-31; 2019-08-06: 2019-02-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00017; 2019-02-20: TPSK-LSPA1-T-ME-00084; 2019-03-29: TPSK-LSPA1-T-ME-00245; 2019-08-06: TPSK-LSPA1-T-ME-00888
[6 empty] | Return Date | 2019-02-20: 2018-08-27; 2019-02-20: 2018-10-24; 2019-03-29: 2018-11-26; 2019-08-06: 2019-03-15
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20; 2019-08-06
| ME | OL1-2R03-0051 | JOB SPEC. FOR SUPPLY OF PRESSURE VESSELS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IMP; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: B; 2019-03-29: 0; 2019-08-06: 1
[6 empty] | Issue Plan | 2019-02-20: 2018-09-10; 2019-02-20: 2018-09-10; 2019-03-29: 2018-09-22; 2019-08-06: 2018-09-22
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-13; 2019-02-20: 2018-09-25; 2019-03-29: 2018-10-31; 2019-08-06: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00021; 2019-02-20: TPSK-LSPA1-T-ME-00084; 2019-03-29: TPSK-LSPA1-T-ME-00249; 2019-08-06: TPSK-LSPA1-T-ME-01350
[6 empty] | Return Date | 2019-02-20: 2018-08-27; 2019-02-20: 2018-10-24; 2019-03-29: 2018-11-27
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-0052 | JOB SPEC. FOR SUPPLY OF COLUMN INTERNALS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-08-10; 2019-02-20: 2018-09-23
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-10; 2019-02-20: 2018-09-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00017; 2019-02-20: TPSK-LSPA1-T-ME-00081
[6 empty] | Return Date | 2019-02-20: 2018-08-27; 2019-02-20: 2018-10-24
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2R03-0053 | JOB SPEC. FOR SUPPLY OF EQUIPMENT LADDERS AND PLATFORMS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-08-10; 2019-02-20: 2018-08-10; 2019-03-29: 2018-09-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-10; 2019-02-20: 2018-09-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00017; 2019-02-20: TPSK-LSPA1-T-ME-00081
[6 empty] | Return Date | 2019-02-20: 2018-08-27; 2019-02-20: 2018-10-24
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2R03-0054 | CONST.STANDARDS FOR PRESS. EQUIP. |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IFC
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-08-10; 2019-02-20: 2018-08-10; 2019-03-29: 2018-10-19
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-10; 2019-02-20: 2018-09-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00018; 2019-02-20: TPSK-LSPA1-T-ME-00084
[6 empty] | Return Date | 2019-02-20: 2018-08-27; 2019-02-20: 2018-10-24
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-0055 | CONST.STANDARDS FOR LADDERS AND PLATFORMS ATTACHED TO PRESSURE EQUIPMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2018-10-23; 2019-02-20: 2018-12-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2R03-0102 | MARKING FOR VESSEL & HEAT EXCHANGER |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-10; 2019-02-20: 2018-09-22
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00042
Return Date
Owner Cmmt*
| ME | OL1-2R03-0104 | ME-008 Cooling Water |  | Class Final | Purpose** | 2019-02-20: IFQ
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00276
[6 empty] | Return Date | 2019-02-20: 2019-02-15
Owner Cmmt*
| ME | OL1-2R03-0500 | ME-050 Centrifugal Pump - Non API |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-12; 2019-02-20: 2019-01-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00308; 2019-02-20: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | 2019-02-20: 2018-12-06; 2019-02-20: 2019-04-25
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R03-055 | Construction Standards For Ladders And Platforms Attached To Pressure Equipment |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00027
[6 empty] | Return Date | 2019-02-20: 2018-09-18
Owner Cmmt* | bar: 2019-02-20
| ME | OL1-2R03-1001 | ME-001 Pressure Vessel for 36M and 132U Furnace |  | Class Final | Purpose** | 2019-02-20: IFE
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00262
Return Date
Owner Cmmt*
| ME | OL1-2R03-1004 | ME-004 Shell and Tube Heat Exchangers for 36M and 132U Furnace |  | Class Final | Purpose** | 2019-02-20: IFI
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00221
Return Date
Owner Cmmt*
| ME | OL1-2R03-1005 | Job Specification for Axens General Statement about Selection of Materials for Equipment and Piping |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01505
Return Date
Owner Cmmt*
| ME | OL1-2R03-1006 | Job Specification for Air Liquide-Design Rules- Codes and Standards for Columns and Column Internals |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-04-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-01504
Return Date
Owner Cmmt*
Category Code: R04 Piping Specification (PIP)
| MP | OL1-2R04-0001 | PIPING CLASSES SUMMARY & PIPING CLASSES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-12-19; 2019-02-20: 2020-10-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-27; 2019-02-20: 2019-04-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00562; 2019-02-20: 1262-TPSK-LSPA1-T-MP-01262
[6 empty] | Return Date | 2019-02-20: 2019-01-17
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2R04-0002 | JOB DES.SPEC.FOR PIPING AND STD |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IFC
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-13; 2019-02-20: 2018-11-13; 2019-03-29: 2019-02-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-08; 2019-02-20: 2018-11-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00012; 2019-02-20: TPSK-LSPA1-T-MP-00012
[6 empty] | Return Date | 2019-02-20: 2018-09-26; 2019-02-20: 2018-12-07
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0003 | JOB DESIGN SPECIFICATION FOR THERMAL INSULATION (HOT SERVICE) |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IMP
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-04-29; 2019-02-20: 2019-04-29; 2019-03-29: 2019-08-27
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-22; 2019-02-20: 2018-12-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00024; 2019-02-20: TPSK-LSPA1-T-MP-00562
[6 empty] | Return Date | 2019-02-20: 2018-09-12; 2019-02-20: 2019-01-17
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0004 | JOB DESIGN SPECIFICATION FOR THERMAL INSULATION (COLD SERVICE) |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IFR; 2019-08-06: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: B; 2019-03-29: C
[6 empty] | Issue Plan | 2019-02-20: 2019-04-29; 2019-02-20: 2019-04-29; 2019-03-29: 2019-04-29; 2019-08-06: 2019-08-27
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-22; 2019-02-20: 2018-12-27; 2019-03-29: 2019-05-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00024; 2019-02-20: TPSK-LSPA1-T-MP-00562; 2019-03-29: TPSK-LSPA1-T-MP-01665
[6 empty] | Return Date | 2019-02-20: 2018-09-12; 2019-02-20: 2019-01-17
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0005 | JOB DESIGN SPECIFICATION FOR PAINTING |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IMP
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-04-29; 2019-02-20: 2019-04-29; 2019-03-29: 2019-08-27
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-22; 2019-02-20: 2018-12-27
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00024; 2019-02-20: TPSK-LSPA1-T-MP-00562
[6 empty] | Return Date | 2019-02-20: 2018-09-12; 2019-02-20: 2019-01-17
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0006 | JOB SUPPLY SPECIFICATION FOR PIPING MATERIAL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: B; 2019-03-29: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-04-06; 2019-02-20: 2019-04-06; 2019-03-29: 2019-05-06
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-27; 2019-02-20: 2018-11-20; 2019-03-29: 2019-02-28
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00028; 2019-02-20: TPSK-LSPA1-T-MP-00342; 2019-03-29: TPSK-LSPA1-T-MP-00951
[6 empty] | Return Date | 2019-02-20: 2018-09-18; 2019-02-20: 2019-01-30; 2019-03-29: 2019-04-01
Owner Cmmt* | bar: 2019-02-20 to 2019-03-29
| ME | OL1-2R04-0007 | PIP-007 Marking of Piping Material for 36M and 132U Furnace |  | Class Final | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00213
Return Date
Owner Cmmt*
| MP | OL1-2R04-0008 | JOB SUPPLY SPECIFICATION FOR BUTTERFLY VALVES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-04-13; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-26; 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00352; 2019-02-20: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-02-20: 2019-01-30
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2R04-0009 | JOB SUPPLY SPECIFICATION FOR PLUG VALVES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-04-13; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-26; 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00352; 2019-02-20: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-02-20: 2019-01-30
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2R04-0010 | JOB SUPPLY SPECIFICATION FOR BALL VALVES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-04-13; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-26; 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00352; 2019-02-20: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-02-20: 2019-01-30
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2R04-0011 | JOB SUPPLY SPECIFICATION FOR PIPES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: B; 2019-03-29: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-04-06; 2019-02-20: 2019-04-06; 2019-03-29: 2019-05-06
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-27; 2019-02-20: 2018-11-20; 2019-03-29: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00028; 2019-02-20: TPSK-LSPA1-T-MP-00342; 2019-03-29: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-02-20: 2018-09-18; 2019-02-20: 2019-01-30
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0012 | Pipe Support |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-16; 2019-02-20: 2019-02-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00324; 2019-02-20: TPSK-LSPA1-T-MP-00828
[6 empty] | Return Date | 2019-02-20: 2018-12-18; 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0013 | JOB SUPPLY SPECIFICATION FOR BUTTWELDING FITTINGS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: B; 2019-03-29: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-04-06; 2019-02-20: 2019-04-06; 2019-03-29: 2019-05-06
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-27; 2019-02-20: 2018-11-20; 2019-03-29: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00028; 2019-02-20: TPSK-LSPA1-T-MP-00342; 2019-03-29: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-02-20: 2018-09-18; 2019-02-20: 2019-01-30
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0014 | JOB SUPPLY SPECIFICATION FOR FORGED FITTINGS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: B; 2019-03-29: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-04-06; 2019-02-20: 2019-04-06; 2019-03-29: 2019-05-06
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-27; 2019-02-20: 2018-11-20; 2019-03-29: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00028; 2019-02-20: TPSK-LSPA1-T-MP-00342; 2019-03-29: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-02-20: 2018-09-18; 2019-02-20: 2019-01-30
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0015 | JOB SUPPLY SPECIFICATION FOR FLANGES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: B; 2019-03-29: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-04-06; 2019-02-20: 2019-04-06; 2019-03-29: 2019-05-06
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-27; 2019-02-20: 2018-11-20; 2019-03-29: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00028; 2019-02-20: TPSK-LSPA1-T-MP-00342; 2019-03-29: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-02-20: 2018-09-18; 2019-02-20: 2019-01-30
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0016 | JOB SUPPLY SPECIFICATION FOR GASKETS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-20; 2019-02-20: 2019-05-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2R04-0017 | JOB SUPPLY SPECIFICATION FOR BOLTING |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-20; 2019-02-20: 2019-05-20
[6 empty] | Revised Plan | 2019-02-20: 2019-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2R04-0018 | JOB SUPPLY SPECIFICATION FOR REINFORCED THERMOSETTING RESIN PLASTIC PIPING |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-04-06; 2019-02-20: 2019-05-06
[6 empty] | Revised Plan | 2019-02-20: 2019-07-31; 2019-02-20: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2R04-0030 | Piping Flexibility |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-20; 2019-02-20: 2019-02-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00336; 2019-02-20: TPSK-LSPA1-T-MP-00828
[6 empty] | Return Date | 2019-02-20: 2018-12-07; 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0031 | JOB DES.SPEC.FOR STEAM TRACING |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IFC
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-13; 2019-02-20: 2018-11-13; 2019-03-29: 2019-02-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-08; 2019-02-20: 2018-11-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00012; 2019-02-20: TPSK-LSPA1-T-MP-00292
[6 empty] | Return Date | 2019-02-20: 2018-09-26; 2019-02-20: 2019-01-23
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0032 | JSD FOR PIPING STRESS ANALYSIS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-11-12; 2019-02-20: 2019-02-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-16; 2019-02-20: 2019-02-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00324; 2019-02-20: TPSK-LSPA1-T-MP-00881
[6 empty] | Return Date | 2019-02-20: 2018-12-18; 2019-02-20: 2019-03-21
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0033 | JSD FOR PIPING LOADS ON PIPERACKS (PRK), SLEEPER WAYS (SLW), STRUCTURES (STR), ISOLATED SUPPORTS (IS) |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-11-12; 2019-02-20: 2019-02-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-16; 2019-02-20: 2019-02-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00324; 2019-02-20: TPSK-LSPA1-T-MP-00828
[6 empty] | Return Date | 2019-02-20: 2018-12-18; 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0034 | JSD AUXILIARY STD PIPE SUPPORTS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: B; 2019-03-29: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-11-12; 2019-02-20: 2018-11-12; 2019-03-29: 2019-02-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-16; 2019-02-20: 2019-02-08; 2019-03-29: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00324; 2019-02-20: TPSK-LSPA1-T-MP-00830; 2019-03-29: TPSK-LSPA1-T-MP-01002
[6 empty] | Return Date | 2019-02-20: 2018-12-18; 2019-02-20: 2019-02-25; 2019-03-29: 2019-04-01
Owner Cmmt* | bar: 2019-02-20 to 2019-03-29
| MP | OL1-2R04-0036 | JSS CRYOGENIC SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-31; 2019-02-20: 2019-02-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-08; 2019-02-20: 2019-04-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00831; 2019-02-20: TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | 2019-02-20: 2019-03-21; 2019-02-20: 2019-04-26
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0037 | JSS FOR ROD & SPRING HANGERS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-31; 2019-02-20: 2019-02-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-08; 2019-02-20: 2019-04-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00831; 2019-02-20: TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | 2019-02-20: 2019-03-21; 2019-02-20: 2019-04-26
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0038 | JSS SLIDING PLATES |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-31; 2019-02-20: 2019-02-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-08; 2019-02-20: 2019-04-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00831; 2019-02-20: TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | 2019-02-20: 2019-03-21; 2019-02-20: 2019-04-26
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0039 | JSS DYNAMIC PIPING SUPPORTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-31; 2019-02-20: 2019-02-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-08; 2019-02-20: 2019-04-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00831; 2019-02-20: TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | 2019-02-20: 2019-03-21; 2019-02-20: 2019-04-26
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0040 | JSS METALLIC EXPANSION JOINTS |  | Class 3 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-31; 2019-02-20: 2019-02-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-08; 2019-02-20: 2019-04-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00831; 2019-02-20: TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | 2019-02-20: 2019-03-21; 2019-02-20: 2019-04-26
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| MP | OL1-2R04-0041 | JOB SUPPLY SPECIFICATION FOR VALVE (GATE,GLOBE,CHECK) |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-04-13; 2019-02-20: 2019-05-13
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-26; 2019-02-20: 2019-04-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-00356; 2019-02-20: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-02-20: 2019-01-30
Owner Cmmt* | bar: 2019-02-20
| MP | OL1-2R04-0042 | Job Supply Specification For Non Metallic Expansion Joints |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-31; 2019-02-20: 2019-02-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07; 2019-02-20: 2019-04-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-MP-01000; 2019-02-20: TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | 2019-02-20: 2019-04-01; 2019-02-20: 2019-04-26
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R04-1004 | PIP-004 Piping Welding Specification for 36M and 132U Furnace |  | Class Final | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-16
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00184
Return Date
Owner Cmmt*
Category Code: R05 Electrical Specification (EE)
| EE | OL1-2R05-0001 | GENERAL ELECTRICAL DESIGN SPECIFICATION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2019-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00424
Return Date
Owner Cmmt*
| EE | OL1-2R05-0002 | ELECTRICAL SYSTEM DESIGN |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2019-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00424
Return Date
Owner Cmmt*
| EE | OL1-2R05-0003 | OIL FILLED DISTRIBUTION TRANSFORMER |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0004 | PROTECTIVE RELAY AND CONTROL UNIT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2019-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-20
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00522
Return Date
Owner Cmmt*
| EE | OL1-2R05-0005 | SUBSTATION MONITORING AND CONTROL SYSTEM |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00425
Return Date
Owner Cmmt*
| EE | OL1-2R05-0006 | MEDIUM VOLTAGE SWITCHGEAR |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0007 | LOW VOLTAGE DISTRIBUTION PANEL |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-12
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00309
Return Date
Owner Cmmt*
| EE | OL1-2R05-0008 | LOW VOLTAGE SWITCHGEAR AND MOTOR CONTROL CENTER |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| TS | OL1-2R05-0009 | SMCS I/O LIST |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-06-15; 2019-02-20: 2019-08-17
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2R05-0010 | ELECTRICAL MOTORS UP TO 300 KW |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00079
Return Date
Owner Cmmt*
| EE | OL1-2R05-0011 | ELECTRICAL MOTORS GREATER THAN TO 300 KW |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00748
[6 empty] | Return Date | 2019-02-20: 2019-02-25
Owner Cmmt* | bar: 2019-02-20
| EE | OL1-2R05-0012 | UNINTERRUPTIBLE POWER SUPPLIES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0013 | INTERCOM/PAGING/AUDIBLE ALARM SYSTEM |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-21; 2019-02-20: 2019-02-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-04; 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00403; 2019-02-20: TPSK-LSPA1-T-EE-00987
[6 empty] | Return Date | 2019-02-20: 2018-12-17; 2019-02-20: 2019-03-21
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| EE | OL1-2R05-0014 | LIGHTING SYSTEM |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2019-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00258
Return Date
Owner Cmmt*
| EE | OL1-2R05-0015 | EARTHING AND LIGHTING PROTECTION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2019-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00258
Return Date
Owner Cmmt*
| EE | OL1-2R05-0016 | CATHODIC PROTECTION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP; 2019-03-29: IMP
[6 empty] | Rev. | 2019-02-20: 0; 2019-03-29: 1
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03; 2019-03-29: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-05; 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00268; 2019-03-29: TPSK-LSPA1-T-EE-01556
Return Date
Owner Cmmt*
| EE | OL1-2R05-0017 | DIESEL ENGINE GENERATOR |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0018 | POWER, CONTROL, AND FIBER OPTIC CABLES |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00425
Return Date
Owner Cmmt*
| EE | OL1-2R05-0019 | SAFETY SUPERVISORY SYSTEM |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-21; 2019-02-20: 2019-02-15
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-04; 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00403; 2019-02-20: TPSK-LSPA1-T-EE-00987
[6 empty] | Return Date | 2019-02-20: 2018-12-17; 2019-02-20: 2019-03-21
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| EE | OL1-2R05-0021 | POWER CAPACITORS |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0022 | MISCELLANEOUS EQUIPMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0023 | LOW VOLTAGE VARIABLE VOLTAGE VARIABLE FREQUENCY SYSTEM |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0024 | SUBSTATION DESIGN |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2019-01-30
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14; 2019-02-20: 2019-07-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2R05-0027 | NEUTRAL GROUNDING RESISTOR |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00425
Return Date
Owner Cmmt*
| EE | OL1-2R05-0028 | TELECOM NUMBERING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-21; 2019-02-20: 2019-02-15
[6 empty] | Revised Plan | 2019-02-20: 2019-05-20
[6 empty] | Issue Actual | 2019-02-20: 2019-02-21
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00905
[6 empty] | Return Date | 2019-02-20: 2019-03-04
Owner Cmmt* | bar: 2019-02-20
| EE | OL1-2R05-0029 | FUNCTIONAL AND SCHEMATIC DIAGRAM |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2019-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00258
Return Date
Owner Cmmt*
| EE | OL1-2R05-0036 | DOCUMENT TEMPLATE |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2019-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00424
Return Date
Owner Cmmt*
| EE | OL1-2R05-0037 | ELECTRICAL HEAT TRACING SYSTEM |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00079
Return Date
Owner Cmmt*
| EE | OL1-2R05-0038 | LOW VOLTAGE BUS DUCT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0040 | MEDIUM VOLTAGE VARIABLE VOLTAGE VARIABLE FREQUENCY (VVVF) SYSTEM |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0041 | NUMBERING SYSTEM FOR ELECTRICAL EQUIPMENT |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2019-01-30
[6 empty] | Revised Plan | 2019-02-20: 2019-06-14; 2019-02-20: 2019-07-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2R05-0042 | General Design Rule For Package Equipment Electrical System - Client code for next revision will be OL1-2E04-6000 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | 2019-02-20: 2018-08-24
Owner Cmmt* | bar: 2019-02-20
| EE | OL1-2R05-0043 | General Design Rule For Smartplant Electrical |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | 2019-02-20: 2018-08-24
Owner Cmmt* | bar: 2019-02-20
| EE | OL1-2R05-0044 | Coordination Procedure For Smartplant Electrical |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-10-14; 2019-02-20: 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | 2019-02-20: 2018-08-24
Owner Cmmt* | bar: 2019-02-20
| EE | OL1-2R05-0045 | Coordination Procedure For ETAP |  | Class Final | Purpose** | 2019-02-20: IFI
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-08-06
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | 2019-02-20: 2018-08-24
Owner Cmmt* | bar: 2019-02-20
Category Code: R06 Instrument Specification (INS)
| IE | OL1-2R06-0001 | NSTRUMENT GENERAL DESIGN |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-28; 2019-02-20: 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03; 2019-02-20: 2018-12-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00121; 2019-02-20: TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | 2019-02-20: 2018-10-09; 2019-02-20: 2018-12-26
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| IE | OL1-2R06-0003 | FLOW MEASUREMENT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-28; 2019-02-20: 2018-09-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0005 | LEVEL MEASUREMENT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-28; 2019-02-20: 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03; 2019-02-20: 2018-12-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00121; 2019-02-20: TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | 2019-02-20: 2018-10-09; 2019-02-20: 2018-12-26
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| IE | OL1-2R06-0006 | PRESSURE MEASUREMENT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-28; 2019-02-20: 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03; 2019-02-20: 2018-12-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00121; 2019-02-20: TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | 2019-02-20: 2018-10-09; 2019-02-20: 2018-12-26
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| IE | OL1-2R06-0007 | TEMPERATURE MEASUREMENT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-28; 2019-02-20: 2018-12-21
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03; 2019-02-20: 2018-12-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00121; 2019-02-20: TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | 2019-02-20: 2018-10-09; 2019-02-20: 2018-12-26
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| IE | OL1-2R06-0008 | FINAL CONTROL ELEMENT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-09-28; 2019-02-20: 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2019-02-20: 2018-10-09
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2R06-0010 | INSTRUMENT CONSTRUCTION MATERIAL |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-02-15; 2019-02-20: 2019-09-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0011 | INSTRUMENT AIR SUPPLY |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-02-15; 2019-02-20: 2019-09-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-26; 2019-02-20: 2019-03-08
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00357; 2019-02-20: TPSK-LSPA1-T-IE-01014
[6 empty] | Return Date | 2019-02-20: 2019-02-01; 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| IE | OL1-2R06-0012 | GROUNDING SYSTEM FOR INSTRUMENT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-02-15; 2019-02-20: 2019-09-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00508
Return Date
Owner Cmmt*
| IE | OL1-2R06-0013 | MACHINE MONITORING SYSTEM |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-07-30; 2019-02-20: 2020-03-05
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03; 2019-02-20: 2019-02-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00121; 2019-02-20: TPSK-LSPA1-T-IE-00889
[6 empty] | Return Date | 2019-02-20: 2018-10-09; 2019-02-20: 2019-03-08
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| IE | OL1-2R06-0015 | INTEGRATED CONTROL AND SAFETY SYSTEM (ICSS) |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2018-11-20; 2019-02-20: 2019-02-02
[6 empty] | Revised Plan | 2019-02-20: 2019-05-30
[6 empty] | Issue Actual | 2019-02-20: 2018-11-26
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00357
[6 empty] | Return Date | 2019-02-20: 2019-02-01
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2R06-0016 | INSTRUMENT CABINETS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-11-20; 2019-02-20: 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03; 2019-02-20: 2019-03-05
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00121; 2019-02-20: TPSK-LSPA1-T-IE-00986
[6 empty] | Return Date | 2019-02-20: 2018-10-09
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2R06-0017 | INTEGRATED TURBINE AND COMPRESSOR CONTROL SYSTEM (ITCC) |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-11-07; 2019-02-20: 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-10; 2019-02-20: 2018-12-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00148; 2019-02-20: TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | 2019-02-20: 2018-10-24; 2019-02-20: 2018-12-26
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| IE | OL1-2R06-0021 | PRESSURE SAFETY VALVE |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-28; 2019-02-20: 2018-09-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0022 | INSTRUMENT NUMBERING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-03; 2019-02-20: 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-05; 2019-02-20: 2019-04-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-PE-00131; 2019-02-20: TPSK-LSPA1-T-IE-01320
[6 empty] | Return Date | 2019-02-20: 2018-10-24; 2019-02-20: 2019-05-09
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| IE | OL1-2R06-0023 | INSTRUMENT INSPECTION AND TEST PLAN |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-03; 2019-02-20: 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0024 | JSD FOR SMART PLANT INSTRUMENTATION SET UP |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: B; 2019-03-29: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-10-03; 2019-02-20: 2018-10-03; 2019-03-29: 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-28; 2019-02-20: 2018-11-08; 2019-03-29: 2019-03-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00109; 2019-02-20: TPSK-LSPA1-T-IE-00291; 2019-03-29: TPSK-LSPA1-T-IE-01094
[6 empty] | Return Date | 2019-02-20: 2018-10-09; 2019-02-20: 2019-02-01; 2019-03-29: 2019-04-05
Owner Cmmt* | bar: 2019-02-20 to 2019-03-29
| IE | OL1-2R06-0026 | JSD For Automation System Availability |  | Class Final | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-21; 2019-02-20: 2019-02-21
[6 empty] | Revised Plan | 2019-02-20: 2019-06-07
[6 empty] | Issue Actual | 2019-02-20: 2019-04-15
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-01355
[6 empty] | Return Date | 2019-02-20: 2019-05-07
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2R06-0035 | JSD FOR INSTRUMENTATION AND CONTROL OF PACKAGED EQUIPMENT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP; 2019-03-29: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0; 2019-03-29: 1
[6 empty] | Issue Plan | 2019-02-20: 2018-11-07; 2019-02-20: 2019-02-02; 2019-03-29: 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-17; 2019-02-20: 2018-11-29; 2019-03-29: 2019-04-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00056; 2019-02-20: TPSK-LSPA1-T-IE-00393; 2019-03-29: TPSK-LSPA1-T-IE-01320
[6 empty] | Return Date | 2019-02-20: 2018-10-02; 2019-02-20: 2018-12-13; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-02-20 to 2019-03-29
| IE | OL1-2R06-1002 | SPEC. FOR ALARM MANAGEMENT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-03; 2019-02-20: 2019-04-02
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-05-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2R06-1025 | JSD FOR CTRL & SAFETY PHILOSOPHY |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-21; 2019-02-20: 2019-02-21
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-01-29
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00750
[6 empty] | Return Date | 2019-02-20: 2019-02-27
Owner Cmmt* | bar: 2019-02-20
| IE | OL1-2R06-1301 | PROGRAMMABLE LOGIC CONTROLLER (PLC) |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-11-07; 2019-02-20: 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-08; 2019-02-20: 2019-03-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00291; 2019-02-20: TPSK-LSPA1-T-IE-01094
[6 empty] | Return Date | 2019-02-20: 2019-02-01; 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| IE | OL1-2R06-2003 | PROCESS ONLINE ANALYZER AND ANALYZER HOUSING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-01-10; 2019-02-20: 2019-02-10
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-02-08; 2019-02-20: 2019-03-13
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00825; 2019-02-20: TPSK-LSPA1-T-IE-01044
[6 empty] | Return Date | 2019-02-20: 2019-03-08; 2019-02-20: 2019-05-09
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| IE | OL1-2R06-3101 | CUSTODY TRANSFER SYSTEM |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-11-20; 2019-02-20: 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-11-26; 2019-02-20: 2019-03-19
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00357; 2019-02-20: TPSK-LSPA1-T-IE-01094
[6 empty] | Return Date | 2019-02-20: 2019-02-01; 2019-02-20: 2019-04-05
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
Category Code: R07 Project Specification (SP)
| ME | OL1-2R07-0009 | SP-009 Painting for 36M and 132U Furnace |  | Class Final | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-23
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00214
Return Date
Owner Cmmt*
| ME | OL1-2R07-0018 | Units Of Measurement |  | Class Final | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-24
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00080
[6 empty] | Return Date | 2019-02-20: 2018-10-24
Owner Cmmt*
| ME | OL1-2R07-0020 | ELETRICAL AND INTRUMENT INTERFACE PHILOSOPHY |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: A; 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2018-09-28; 2019-02-20: 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03; 2019-02-20: 2018-12-17
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00121; 2019-02-20: TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | 2019-02-20: 2018-10-09; 2019-02-20: 2018-12-26
Owner Cmmt* | bar: 2019-02-20 to 2019-02-20
| ME | OL1-2R07-0026 | Project Design Basis |  | Class Final | Purpose** | 2019-02-20: IMP; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0; 2019-02-20: 1
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-09-28; 2019-02-20: 2019-05-02
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ME-00110; 2019-02-20: TPSK-LSPA1-T-ME-01547
[6 empty] | Return Date | 2019-02-20: 2018-10-24
Owner Cmmt*
Category Code: R08 Construction Specification (CON)
| CON | OL1-2R08-0001 | SPECIAL TEC.SP.FOR ERECT |  |  | Purpose** | 2019-02-20: IFQ; 2019-02-20: IFP
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-01-27; 2019-02-20: 2019-03-27
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16; 2019-02-20: 2019-07-19
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CON | OL1-2R08-0003 | INSTRUMENT INSTALLATION |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
[6 empty] | Issue Plan | 2019-02-20: 2019-02-15; 2019-02-20: 2019-09-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-10-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
Category Code: R91 Index/List
Category Code: R92 Procedures & Standards
Category Code: R93 Policy , Guidelines & Memo
| CON | OL1-2R93-2001 | GUIDELINE FOR CRACKING FURNACE CONSTRUCTION / ERECTION |  | Class 2 | Purpose** | 2019-02-20: IFR; 2019-02-20: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-07-30; 2019-02-20: 2019-09-03; 2019-03-29: 2019-10-08
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: R94 Forms & Templates
Category Code: R95 Progress/Status Reports
Category Code: Request for Quotation (RFQ) for Mechanical work Request for Quotation (RFQ) for Mechanical work
Category Code: S01 Environmental Management Plan and program;
Category Code: S02 Waste Material Management
Category Code: S03 Health/Social Management and Program; Community Affairs Management
Category Code: S04 Environmental Management Report
Category Code: S05 Health/Social Management Report
Category Code: S06 ESIA Report
Category Code: S07 ESIA Database
Category Code: S08 Environmental Specification (nuovo codice richiesto dal cliente S82)
| ES | OL1-2S08-0001 | ENVIRONMENTAL JOB SPECIFICATION FOR DESIGN |  | Class 2 | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2018-12-11
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ES-00473
Return Date
Owner Cmmt*
Category Code: S63 EH&S Monitoring report
Category Code: S64 OSHE Review/Audit Report
Category Code: S71 Appraisal Report for Consultancy Service
Category Code: S72 Appraisal Report for EPC Contractor Work
Category Code: S73 Appraisal Report for Vendor/Supplier
Category Code: S81 CSR Procedure & Standard
Category Code: S82 CSR Policy, Guideline & Memo
Category Code: S83 CSR Template & Form
Category Code: S84 CSR Report
Category Code: S85 CSR Audit Report
Category Code: S90 Vendor Document/drawings
Category Code: S91 Index/List
Category Code: S92 Procedures & Standards
Category Code: S93 Policy , Guidelines & Memo
Category Code: S94 Forms & Templates
Category Code: S95 Progress/Status Reports
| ES | OL1-2S95-0210 | Furnace Section HAZOP Report |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-20
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ES-01113
[6 empty] | Return Date | 2019-02-20: 2019-04-22
Owner Cmmt* | bar: 2019-02-20
| ES | OL1-2S95-0230 | Furnace Section SIL Classification Report |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-25
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-ES-01146
[6 empty] | Return Date | 2019-02-20: 2019-04-22
Owner Cmmt* | bar: 2019-02-20
Category Code: T01 Design basis
| EE | OL1-2T01-0001 | Job Supply Specification For Intercom Paging And Audible Alarm System -Ex Document Client Reference OL1-2T92-0001 |  | Class Final | Purpose** | 2019-02-20: IMP
[6 empty] | Rev. | 2019-02-20: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00985
[6 empty] | Return Date | 2019-02-20: 2019-03-21
Owner Cmmt* | bar: 2019-02-20
| EE | OL1-2T01-0002 | Job Supply Specification For Safety Supervisory System - Ex Document Client Reference OL1-2T92-0002 |  | Class Final | Purpose** | 2019-02-20: IFR
Rev. | bar: 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-07
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00985
[6 empty] | Return Date | 2019-02-20: 2019-03-21
Owner Cmmt* | bar: 2019-02-20
Category Code: T02 Abbreviation and standard symbols
Category Code: T03 Project Communication, IT, and Safety Supervisory System specification
Category Code: T04 System philosophy
Category Code: T05 Equipment datasheets
Category Code: T10 Intercom/Paging/Audible Alarm system equipment data sheets
Category Code: T11 Intercom/Paging/Audible Alarm system schematic diagram
| EE | OL1-2T11-0001 | TELECOMM.SYST ARCHITECTURE OF INTERCOM, PAGING AND AUDIBLE ALARM SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFR; 2019-03-29: IBD; 2019-08-06: IDD
Rev. | bar: 2019-02-20 to 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-01-09; 2019-02-20: 2019-01-09; 2019-03-29: 2019-01-09; 2019-08-06: 2019-02-28
[6 empty] | Revised Plan | 2019-03-29: 2019-05-30; 2019-08-06: 2019-06-28
[6 empty] | Issue Actual | 2019-02-20: 2019-03-04; 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00976; 2019-02-20: TPSK-LSPA1-T-EE-01624
[6 empty] | Return Date | 2019-02-20: 2019-03-21
Owner Cmmt* | bar: 2019-02-20
Category Code: T12 Intercom/Paging/Audible Alarm aystem layout
| EE | OL1-2T12-0002 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT COMMON AREA |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0003 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT METERING |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0004 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT MAIN PIPE RACK |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0005 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT AREA SUBSTATION E & FAR E |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0006 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT AREA SUBSTATION C & FAR C |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0007 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT FURNACES UTILITY |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0008 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT QUENCH |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0009 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS 20B |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0010 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS 20C |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0011 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS COLD COMPRESSORS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0012 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS CGC |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0013 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT BUTADIENE |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0014 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT COOLING WATER UNIT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0015 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT UTILITIES |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0016 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT WASTE WATER TREATMENT |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0017 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT FLARE AREA |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-01-31; 2019-03-29: 2020-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T13 Intercom/Paging/Audible Alarm aystem wiring layout
| EE | OL1-2T13-1001 | TELECOM WIRING DRAWINGS FOR FAR-E SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-28; 2019-02-20: 2020-02-28; 2019-03-29: 2020-08-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T13-1002 | TELECOM WIRING DRAWINGS FOR FAR-C SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-28; 2019-02-20: 2020-02-28; 2019-03-29: 2020-08-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T13-1003 | TELECOM WIRING DRAWINGS FOR FAR-FL SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-28; 2019-02-20: 2020-02-28; 2019-03-29: 2020-08-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T13-1004 | TELECOM WIRING DRAWINGS FOR CCB SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-02-28; 2019-02-20: 2020-02-28; 2019-03-29: 2020-08-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T14 Cable drum schedule for Intercom/Paging/Audible Alarm aystem
Category Code: T15 Cable schedule for Intercom/Paging/Audible Alarm aystem
Category Code: T16 Connection List for Intercom/Paging/Audible Alarm aystem
| EE | OL1-2T16-1001 | TELECOM CABLE LIST FOR FAR C SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-08-15; 2019-03-29: 2020-11-15; 2019-08-06: 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T16-1002 | TELECOM CABLE LIST FOR FAR E SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-08-15; 2019-03-29: 2020-11-15; 2019-08-06: 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T16-1003 | TELECOM CABLE LIST FOR FAR FL SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-08-15; 2019-03-29: 2020-11-15; 2019-08-06: 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T16-1004 | TELECOM CABLE LIST FOR CCB AND OTHER BULDINGS SYSTEMS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC1; 2019-08-06: IFC2
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2020-05-15; 2019-02-20: 2020-08-15; 2019-03-29: 2020-11-15; 2019-08-06: 2021-01-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T17 Bill of quantities for Intercom/Paging/Audible Alarm aystem
| EE | OL1-2T17-0001 | TELECOMM. & SUPERVISORY SYSTEMS EQUIPMENT LIST |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-02-20: 2020-02-28; 2019-03-29: 2020-08-30
[6 empty] | Revised Plan | 2019-02-20: 2019-12-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T17-0002 | TELECOMM. & SUPERVISORY SYSTEMS EQUIPMENT LIST FOR OTHER CONTRACTORS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-03-04; 2019-02-20: 2020-02-28; 2019-03-29: 2020-08-30
[6 empty] | Revised Plan | 2019-02-20: 2019-12-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T18 Typical drawing for Intercom/Paging/Audible Alarm aystem
Category Code: T20 Computer Network (LAN) and Telephone system equipment data sheets
Category Code: T21 Computer Network (LAN) and Telephone system schematic diagram
Category Code: T22 Computer Network (LAN) and Telephone system layout
Category Code: T23 Computer Network (LAN) and Telephone system wiring layout
Category Code: T24 Cable drum schedule for Computer Network (LAN) and Telephone system
Category Code: T25 Cable schedule for Computer Network (LAN) and Telephone system
Category Code: T26 Connection List for Computer Network (LAN) and Telephone system
| EE | OL1-2T26-0001 | FIBRE OPTIC TERMINATION DRAWINGS |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IDD; 2019-03-29: IFC
Rev.
[6 empty] | Issue Plan | 2019-02-20: 2019-11-30; 2019-02-20: 2020-02-28; 2019-03-29: 2020-08-31
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T27 Bill of quantities for Computer Network (LAN) and Telephone system
Category Code: T28 Typical drawing for Computer Network (LAN) and Telephone system
Category Code: T30 CCTV, Access Control, and Intrusion Alarm system equipment data sheets
Category Code: T31 CCTV, Access Control, and Intrusion Alarm system schematic diagram
| EE | OL1-2T31-0001 | Telecomm Syst Architecture Of Safety Supervisory System |  | Class As Built | Purpose** | 2019-02-20: IFR; 2019-02-20: IBD
Rev. | bar: 2019-02-20 to 2019-02-20
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2019-02-20: 2019-03-04; 2019-02-20: 2019-05-09
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00976; 2019-02-20: TPSK-LSPA1-T-EE-01624
[6 empty] | Return Date | 2019-02-20: 2019-03-21
Owner Cmmt* | bar: 2019-02-20
Category Code: T32 CCTV, Access Control, and Intrusion Alarm system layout
Category Code: T33 CCTV, Access Control, and Intrusion Alarm system wiring layout
Category Code: T34 Cable drum schedule for CCTV, Access Control, and Intrusion Alarm system
Category Code: T35 Cable schedule for CCTV, Access Control, and Intrusion Alarm system
Category Code: T36 Connection List for CCTV, Access Control, and Intrusion Alarm system
Category Code: T37 Bill of quantities for CCTV, Access Control, and Intrusion Alarm system
Category Code: T38 Typical drawing for CCTV, Access Control, and Intrusion Alarm system
Category Code: T40 Fire Alarm system equipment data sheets
Category Code: T41 Fire Alarm system schematic diagram
Category Code: T42 Fire alarm system layout
Category Code: T43 Fire alarm system wiring layout
Category Code: T44 Cable drum schedule for Fire alarm system
Category Code: T45 Cable schedule for Fire alarm system
Category Code: T46 Connection List for Fire alarm system
Category Code: T47 Bill of quantities forFire alarm system
Category Code: T48 Typical drawing for Fire alarm system
Category Code: T60 Application software system
Category Code: T61 Application software Procedure
Category Code: T71 Appraisal Report for Consultancy Service
Category Code: T72 Appraisal Report for EPC Contractor Work
Category Code: T73 Appraisal Report for Vendor/Supplier
Category Code: T90 Vendor documents
Category Code: T91 Index/List
Category Code: T92 Procedures & Standards
| EE | OL1-2T92-0001 | JSS FOR INTERCOM/PAGING/AUDIBLE ALARM SYSTEM |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-15
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
[6 empty] | Issue Actual | 2019-02-20: 2019-01-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00577
[6 empty] | Return Date | 2019-02-20: 2019-01-23
Owner Cmmt* | bar: 2019-02-20
| EE | OL1-2T92-0002 | JSS FOR SAFETY SUPERVISORY SYSTEM |  |  | Purpose** | 2019-02-20: IFR; 2019-02-20: IFF
Rev. | bar: 2019-02-20
[6 empty] | Issue Plan | 2019-02-20: 2019-04-15; 2019-02-20: 2019-05-15
[6 empty] | Revised Plan | 2019-02-20: 2019-05-16
[6 empty] | Issue Actual | 2019-02-20: 2019-01-03
[6 empty] | Transmittal no. | 2019-02-20: TPSK-LSPA1-T-EE-00577
[6 empty] | Return Date | 2019-02-20: 2019-01-23
Owner Cmmt* | bar: 2019-02-20
Category Code: T93 Policy , Guidelines & Memo
Category Code: T94 Forms & Templates
Category Code: T95 Progress/Status Reports
Category Code: U02 Finance Reports
Category Code: U03 Certification(Finance)
Category Code: U07 Bond and other financial security for Consultancy Service
Category Code: U08 Bond and other financial security for EPC Contractor
Category Code: U09 Bond and other financial security for Vendor/Supplier
Category Code: U11 Certificates of Insurance
Category Code: U12 Insurance Policies and Guarantees
Category Code: U71 Appraisal Report for Consultancy Service
Category Code: U72 Appraisal Report for EPC Contractor Work
Category Code: U73 Appraisal Report for Vendor/Supplier
Category Code: U91 Index/List
Category Code: U92 Procedures & Standards
Category Code: U93 Policy , Guidelines & Memo
Category Code: U94 Forms & Templates
Category Code: U95 Progress/Status Reports
Category Code: V04 Interface Matrix (Responsibility Matrix)
Category Code: V71 Appraisal Report for Consultancy Service
Category Code: V72 Appraisal Report for EPC Contractor Work
Category Code: V73 Appraisal Report for Vendor/Supplier
Category Code: V91 Index/List
Category Code: V92 Procedures & Standards
Category Code: V93 Policy , Guidelines & Memo
Category Code: V94 Forms & Templates
Category Code: V95 Progress/Status Reports
Category Code: W71 Appraisal Report for Consultancy Service
Category Code: W72 Appraisal Report for EPC Contractor Work
Category Code: W73 Appraisal Report for Vendor/Supplier
Category Code: W90 Technical Report
Category Code: W91 Index/List
Category Code: W92 Procedures & Standards
Category Code: W93 Policy , Guidelines & Memo
Category Code: W94 Forms & Templates
Category Code: W95 Progress/Status Reports
Category Code: X71 Appraisal Report for Consultancy Service
Category Code: X72 Appraisal Report for EPC Contractor Work
Category Code: X73 Appraisal Report for Vendor/Supplier
Category Code: X91 Index/List
Category Code: X92 Procedures & Standards
Category Code: X93 Policy , Guidelines & Memo
Category Code: X94 Forms & Templates
Category Code: X95 Progress/Status Reports
Category Code: Y01 Bidding Guideline
Category Code: Y02 Bidding Committee Assignment
Category Code: Y03 Bidding Policy
Category Code: Y04 Pre-Qualification Document
Category Code: Y05 List of qualified Bidders
Category Code: Y06 Bidding Evaluation Criteria for Consultancy Service
Category Code: Y07 Bidding Evaluation Criteria for EPC Contractor
Category Code: Y08 Bidding Evaluation Criteria for Vendor/Supplier
Category Code: Y09 Contractor Selection Plan
Category Code: Y13 ITB Structure
Category Code: Y21 Tender or ITB Document for Consultancy service
Category Code: Y22 Tender or ITB Document for EPC Contractor
Category Code: Y23 Tender or ITB Document for Vendor/Supplier
Category Code: Y31 Tender or ITB clarification records for Consultancy service
Category Code: Y32 Tender or ITB clarification records for EPC Contractor
Category Code: Y33 Tender or ITB clarification records for Vendor/Supplier
Category Code: Y41 Proposal Document of Consultancy service bidding
Category Code: Y42 Proposal Document of EPC Contractor bidding
Category Code: Y43 Proposal Document of Vendor/Supplier bidding
Category Code: Y51 Proposal clarification records for Consultancy service
Category Code: Y52 Proposal clarification records for EPC Contractor
Category Code: Y53 Proposal clarification records for Vendor/Supplier
Category Code: Y61 Un-Priced Commerical proposals evaluation report
Category Code: Y62 Priced Commercial proposals evaluation report
Category Code: Y63 Bid Evaluation Report (Technical & Un-priced Commercial proposal )
Category Code: Y64 Bid Evaluation report (Executive Summary)
Category Code: Y65 Nomination of successful bidder for approval
Category Code: Y66 EPC Contract Negotiation, Compliance Report
Category Code: Y71 Appraisal Report for Consultancy Service
Category Code: Y72 Appraisal Report for EPC Contractor Work
Category Code: Y73 Appraisal Report for Vendor/Supplier
Category Code: Y81 Consultancy Service Bidding Records
Category Code: Y82 EPC Contractor Bidding Records
Category Code: Y83 Vendor/Supplier Bidding Records