## Document
Document Reference | Document Title | Revision Number | Revision Date | Document Revision Object | Document Client Reference | Discipline | Transmittal Date | Transmittal Reference | Specific Transmittal Number | Required Action | Response Due Date | Actual Response Date | Document Status | Client Transmittal Ref Number | Remarks | Client Transmittal Date | Document Class
036909C-1012-PID-0021-1260 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1200 - Utility Stations | A | 2019-09-04 | IDD1 | OL1-2G43-1260 | PE | 2019-09-05 | 036909C-JVD-TRN-02578 | 036909C-JVD-TRN-02578 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02578 |  | 2019-09-10 | 2
036909C-1012-PID-0021-1265 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1200 - MOV Purge Details | A | 2019-09-04 | IDD1 | OL1-2G43-1265 | PE | 2019-09-05 | 036909C-JVD-TRN-02578 | 036909C-JVD-TRN-02578 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02578 |  | 2019-09-10 | 2
036909C-1012-PID-0021-1275 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1200 - Cooling Water Supply and Return | A | 2019-09-04 | IDD1 | OL1-2G43-1275 | PE | 2019-09-05 | 036909C-JVD-TRN-02578 | 036909C-JVD-TRN-02578 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02578 |  | 2019-09-10 | 2
036909C-1012-PID-0021-1270 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1200 - Instrument Air Distribution | A | 2019-09-04 | IDD1 | OL1-2G43-1270 | PE | 2019-09-05 | 036909C-JVD-TRN-02578 | 036909C-JVD-TRN-02578 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02578 |  | 2019-09-10 | 2
036909C-1011-PID-0021-1170 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Instrument Air Distribution | A | 2019-09-04 | IDD1 | OL1-2G43-1170 | PE | 2019-09-05 | 036909C-JVD-TRN-02578 | 036909C-JVD-TRN-02578 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02578 |  | 2019-09-10 | 2
036909C-1011-PID-0021-1175 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Cooling Water Supply and Return | A | 2019-09-04 | IDD1 | OL1-2G43-1175 | PE | 2019-09-05 | 036909C-JVD-TRN-02578 | 036909C-JVD-TRN-02578 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02578 |  | 2019-09-10 | 2
036909C-1011-PID-0021-1160 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Utility Stations | A | 2019-09-04 | IDD1 | OL1-2G43-1160 | PE | 2019-09-05 | 036909C-JVD-TRN-02578 | 036909C-JVD-TRN-02578 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02578 |  | 2019-09-10 | 2
036909C-1011-PID-0021-1165 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - MOV Purge Details | A | 2019-09-04 | IDD1 | OL1-2G43-1165 | PE | 2019-09-05 | 036909C-JVD-TRN-02578 | 036909C-JVD-TRN-02578 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02578 |  | 2019-09-10 | 2
036909C-1039-PID-0031-3901 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - NMP Storage | B | 2019-05-20 | IBD | OL1-2G43-3901 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-105F-ML-251 | Model Review Report Flare Unit Action List 30 Per Cent | 0 | 2019-07-11 | IFI | OL1-2P30-0029 | MP | 2019-07-12 | 036909C-JVD-TRN-02145 | 036909C-JVD-TRN-02145 | IFR | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-MP-02145 |  | 2019-07-15 | 2
036909C-105T-ML-251 | Model Review Report Cooling Water Unit Action List 30 Per Cent | 0 | 2019-07-11 | IFI | OL1-2P30-0030 | MP | 2019-07-12 | 036909C-JVD-TRN-02145 | 036909C-JVD-TRN-02145 | IFR | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-MP-02145 |  | 2019-07-15 | 2
036909C-105U-ML-251 | Model Review Report Utilities And Flare KO Drum Action List 30 Per Cent | 0 | 2019-07-11 | IFI | OL1-2P30-0031 | MP | 2019-07-12 | 036909C-JVD-TRN-02145 | 036909C-JVD-TRN-02145 | IFR | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-MP-02145 |  | 2019-07-15 | 2
036909C-103A-ML-251 | Model Review Report Butadeine Extraction Unit Action List 30 Per Cent | 0 | 2019-07-11 | IFI | OL1-2P30-0028 | MP | 2019-07-12 | 036909C-JVD-TRN-02145 | 036909C-JVD-TRN-02145 | IFR | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-MP-02145 |  | 2019-07-15 | 2
036909C-102D-ML-251 | Model Review Report Cold Compression Action List 30 Per Cent | 0 | 2019-07-11 | IFI | OL1-2P30-0026 | MP | 2019-07-12 | 036909C-JVD-TRN-02145 | 036909C-JVD-TRN-02145 | IFR | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-MP-02145 |  | 2019-07-15 | 2
036909C-102E-ML-251 | Model Review Report Cracked Gas Compressor Action List 30 Per Cent | 0 | 2019-07-11 | IFI | OL1-2P30-0027 | MP | 2019-07-12 | 036909C-JVD-TRN-02145 | 036909C-JVD-TRN-02145 | IFR | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-MP-02145 |  | 2019-07-15 | 2
036909C-102C-ML-251 | Model Review Report Hot Fractioning Action List 30 Per Cent | 0 | 2019-07-11 | IFI | OL1-2P30-0025 | MP | 2019-07-12 | 036909C-JVD-TRN-02145 | 036909C-JVD-TRN-02145 | IFR | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-MP-02145 |  | 2019-07-15 | 2
036909C-102B-ML-251 | Model Review Report C3 Hydrogenation Action List 30 Per Cent | 0 | 2019-07-11 | IFI | OL1-2P30-0024 | MP | 2019-07-12 | 036909C-JVD-TRN-02145 | 036909C-JVD-TRN-02145 | IFR | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-MP-02145 |  | 2019-07-15 | 2
036909C-101B-ML-251 | Model Review Report Furnace Utilities And Action List 30 Per Cent | 0 | 2019-07-11 | IFI | OL1-2P30-0022 | MP | 2019-07-12 | 036909C-JVD-TRN-02145 | 036909C-JVD-TRN-02145 | IFR | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-MP-02145 |  | 2019-07-15 | 2
036909C-100M-ML-251 | Model Review Report Metering Station And General Action List 30 Per Cent | 0 | 2019-07-11 | IFI | OL1-2P30-0020 | MP | 2019-07-12 | 036909C-JVD-TRN-02145 | 036909C-JVD-TRN-02145 | IFR | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-MP-02145 |  | 2019-07-15 | 2
036909C-105W-ML-251 | Model Review Report Waste Water Treatment Unit Action List 30 Per Cent | 0 | 2019-07-11 | IFI | OL1-2P30-0032 | MP | 2019-07-12 | 036909C-JVD-TRN-02145 | 036909C-JVD-TRN-02145 | IFR | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-MP-02145 |  | 2019-07-15 | 2
036909C-1056-MSD-0011-5617 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Slop and Oil Sludge | A | 2018-12-20 | IFA | OL1-2G74-5617 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1056-MSD-0011-5615 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Check Basin | A | 2018-12-20 | IFA | OL1-2G74-5615 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1056-MSD-0011-5614 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Biotreatment Package | A | 2018-12-20 | IFA | OL1-2G74-5614 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1056-MSD-0011-5613 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - CPI & IGF Packages | A | 2018-12-20 | IFA | OL1-2G74-5613 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1056-MSD-0011-5603 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Cracker Holding Basin | A | 2018-12-20 | IFA | OL1-2G74-5603 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1056-MSD-0011-5602 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Surface Runoff Collection | A | 2018-12-20 | IFA | OL1-2G74-5602 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1056-MSD-0011-5601 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Oily Wastewater Collection | A | 2018-12-20 | IFA | OL1-2G74-5601 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1055-MSD-0011-5511 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - HP-LLDPE LP Flare | A | 2018-12-20 | IFA | OL1-2G74-5511 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1051-MSD-0011-5101 | Material Selection Diagram - Olefins Unit 10 - 51 BFW- Steam- Cond Systems - Steam Balance Diagram | A | 2018-12-20 | IFA | OL1-2G74-5101 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1012-PID-0021-1245 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Flue Gas | C | 2019-05-23 | IDD1 | OL1-2G43-1245 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1012-PID-0021-1240 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Burners | C | 2019-05-23 | IDD1 | OL1-2G43-1240 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1012-PID-0021-1231 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Coils | C | 2019-05-23 | IDD1 | OL1-2G43-1231 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-PO-036909C001P61 | Vendor s Acknowledgment of Purchase Order For LLI API Centrifugal Pumps Rev 0 – MR 0910-0001 Rev 0 | 0 | 2019-09-10 | IFI | OL1-2C51-0019 | PL | 2019-09-10 | 036909C-JVD-TRN-02634 | 036909C-JVD-TRN-02634 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02634 |  | 2019-09-13 | 3
036909C-PO-036909C001P88 | Vendor s Acknowledgment of Purchase Order For API Centrifugal Pumps Rev 0 – MR 0910-0008 Rev. 0 | 0 | 2019-09-12 | IFI | OL1-2C51-0021 | PL | 2019-09-12 | 036909C-JVD-TRN-02637 | 036909C-JVD-TRN-02637 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02637 |  | 2019-09-13 | 3
036909C-PO-036909C001P48 | Vendor s Acknowledgment of Purchase Order For Shop Assembled Columns Rev 0 – MR 0511-0002 Rev. 0 | 0 | 2019-09-12 | IFI | OL1-2C51-0020 | PL | 2019-09-12 | 036909C-JVD-TRN-02637 | 036909C-JVD-TRN-02637 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02637 |  | 2019-09-13 | 3
036909C-1059-PID-0031-5932 | PID- Olefins Unit 10 - Supporting Utilities Auxiliaries - Sulfuric Acid Chehical Injection Sheet-2 | C | 2019-09-09 | IDD1 | OL1-2G43-5932 | PE | 2019-09-12 | 036909C-JVD-TRN-02633 | 036909C-JVD-TRN-02633 | IFR | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-PE-02633 |  | 2019-09-13 | 2
036909C-1059-PID-0031-5934 | PID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sodium Hypochlorite Chemical Injection - Sheet 2 | C | 2019-09-09 | IDD1 | OL1-2G43-5934 | PE | 2019-09-12 | 036909C-JVD-TRN-02633 | 036909C-JVD-TRN-02633 | IFR | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-PE-02633 |  | 2019-09-13 | 2
036909C-1059-PID-0031-5905 | PID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Neutralizing Amine Injection System | C | 2019-09-09 | IDD1 | OL1-2G43-5905 | PE | 2019-09-12 | 036909C-JVD-TRN-02633 | 036909C-JVD-TRN-02633 | IFR | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-PE-02633 |  | 2019-09-13 | 2
036909C-1059-PID-0031-5933 | PID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sulfuric Acid Chemical Injection - Sheet 3 | C | 2019-09-09 | IDD1 | OL1-2G43-5933 | PE | 2019-09-12 | 036909C-JVD-TRN-02633 | 036909C-JVD-TRN-02633 | IFR | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-PE-02633 |  | 2019-09-13 | 2
036909C-1059-PID-0031-5903 | PID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sodium Hypochlorite Chemical Injection - Sheet 1 | C | 2019-09-09 | IDD1 | OL1-2G43-5903 | PE | 2019-09-12 | 036909C-JVD-TRN-02633 | 036909C-JVD-TRN-02633 | IFR | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-PE-02633 |  | 2019-09-13 | 2
036909C-1059-PID-0031-5904 | PID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sulfuric Acid Chemical Injection - Sheet - 1 | C | 2019-09-09 | IDD1 | OL1-2G43-5904 | PE | 2019-09-12 | 036909C-JVD-TRN-02633 | 036909C-JVD-TRN-02633 | IFR | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-PE-02633 |  | 2019-09-13 | 2
036909C-1031-PID-0031-3111 | PID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - BDU Steam Letdown | C | 2019-08-30 | IDD1 | OL1-2G43-3111 | PE | 2019-09-12 | 036909C-JVD-TRN-02633 | 036909C-JVD-TRN-02633 | IFR | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-PE-02633 |  | 2019-09-13 | 2
036909C-1026-DI-0007-2602 | Area Basis of Design - 262 C3 Hydrogenation | C | 2019-09-12 | IFD | OL1-2G05-2602 | PE | 2019-09-12 | 036909C-JVD-TRN-02638 | 036909C-JVD-TRN-02638 | IFA | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-PE-02638 |  | 2019-09-13 | 1
036909C-1026-DI-0007-2601 | Area Basis of Design - 26 Hot Fractionation | C | 2019-09-12 | IFD | OL1-2G05-2601 | PE | 2019-09-12 | 036909C-JVD-TRN-02638 | 036909C-JVD-TRN-02638 | IFA | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-PE-02638 |  | 2019-09-13 | 1
036909C-1059-PID-0031-5934 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sodium Hypochlorite Chemical Injection - Sheet 2 | A | 2019-04-18 | IBD | OL1-2G43-5934 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00049 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5933 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sulfuric Acid Chemical Injection - Sheet 3 | A | 2019-04-18 | IBD | OL1-2G43-5933 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00049 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5932 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - 98 percent Sulfuric Acid Pumps | A | 2018-12-11 | IFR | OL1-2G43-5932 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00006 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1059-PID-0031-5932 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sulfuric Acid Chehical Injection Sheet-2 | B | 2019-04-18 | IBD | OL1-2G43-5932 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5905 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Neutralizing Amine Injection System | A | 2019-01-28 | IFR | OL1-2G43-5905 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1059-PID-0031-5905 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Neutralizing Amine Injection System | B | 2019-04-18 | IBD | OL1-2G43-5905 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5904 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - 98 percent Sulfuric Acid Chemical Injection | A | 2018-12-11 | IFR | OL1-2G43-5904 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00006 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1059-PID-0031-5904 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sulfuric Acid Chemical Injection - Sheet - 1 | B | 2019-04-18 | IBD | OL1-2G43-5904 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5903 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - CW Hypochlorite Chemical Injection | A | 2018-12-11 | IFR | OL1-2G43-5903 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00006 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1059-PID-0031-5903 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sodium Hypochlorite Chemical Injection - Sheet 1 | B | 2019-04-18 | IBD | OL1-2G43-5903 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1031-PID-0031-3111 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - BDU Steam Letdown | A | 2019-03-14 | IFR | OL1-2G43-3111 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-30 | CA3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1031-PID-0031-3111 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - BDU Steam Letdown | B | 2019-05-20 | IBD | OL1-2G43-3111 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1026-DI-0007-2602 | Area Basis of Design - 262 C3 Hydrogenation | A | 2018-11-09 | IFA | OL1-2G05-2602 | PE | 2018-11-12 | 036909C-JVD-TRN-00307 | 036909C-JVD-TRN-00307, ROC-TPSK-CECO-T-00001 | IFA | 2018-11-26 | 2019-02-04 | A1-Approved without comments | TPSK-LSPA1-T-PE-00307 |  | 2018-11-12 | 1
036909C-1026-DI-0007-2602 | Area Basis of Design - 262 C3 Hydrogenation | B | 2019-04-25 | IFD | OL1-2G05-2602 | PE | 2019-04-26 | 036909C-JVD-TRN-01510 | 036909C-JVD-TRN-01510 | IFA | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01510 |  | 2019-04-29 | 1
036909C-1026-DI-0007-2601 | Area Basis of Design - 26 Hot Fractionation | A | 2018-08-07 | IFA | OL1-2G05-2601 | PE | 2018-08-08 | 036909C-JVD-TRN-00014 | 036909C-JVD-TRN-00014, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-22 | 2018-08-31 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00014 |  | 2018-08-09 | 1
036909C-1027-DI-0007-2701 | Area Basis of Design - 270 Gasoline Hydrogenation - GHU-1 | B | 2019-04-25 | IFD | OL1-2G05-2701 | PE | 2019-04-26 | 036909C-JVD-TRN-01510 | 036909C-JVD-TRN-01510 | IFA | 2019-05-13 | 2019-05-29 | Response to Client Comments emailed Sept-12-2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01510 |  | 2019-04-29 | 1
036909C-PO-036909C001P95 | Vendor s Acknowledgment of Purchase Order For Carbon Steel Underground Piping Rev 0 – MR 1309-0001 Rev. 0 | 0 | 2019-09-10 | IFI | OL1-2C52-0002 | PL | 2019-09-10 | 036909C-JVD-TRN-02610 | 036909C-JVD-TRN-02610 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02610 |  | 2019-09-12 | 3
036909C-PO-036909C001P94 | Vendor s Acknowledgment of Purchase Order For Underground Welded Carbon Steel Pipes Rev 0 – MR 1329-0002 Rev. 0 | 0 | 2019-09-10 | IFI | OL1-2C52-0001 | PL | 2019-09-10 | 036909C-JVD-TRN-02610 | 036909C-JVD-TRN-02610 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02610 |  | 2019-09-12 | 3
036909C-1030-SP-0510-3050 | Mechanical Equipment Data Sheet Degasser | 0 | 2019-09-04 | IFP | OL1-2M03-3050 | ME | 2019-09-10 | 036909C-JVD-TRN-02613 | 036909C-JVD-TRN-02613 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-ME-02613 |  | 2019-09-12 | 2
036909C-1030-SP-0510-3090 | Mechanical Equipment Data Sheet Butadiene Drying Tower | 0 | 2019-09-03 | IFP | OL1-2M03-3090 | ME | 2019-09-10 | 036909C-JVD-TRN-02613 | 036909C-JVD-TRN-02613 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-ME-02613 |  | 2019-09-12 | 2
036909C-1030-SP-0510-3070 | Mechanical Equipment Data Sheet Direct Cooler Tower | 0 | 2019-09-04 | IFP | OL1-2M03-3070 | ME | 2019-09-10 | 036909C-JVD-TRN-02613 | 036909C-JVD-TRN-02613 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-ME-02613 |  | 2019-09-12 | 2
036909C-1030-SP-0510-3080 | Mechanical Equipment Data Sheet Butadiene Tower | 0 | 2019-09-05 | IFP | OL1-2M03-3080 | ME | 2019-09-10 | 036909C-JVD-TRN-02613 | 036909C-JVD-TRN-02613 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-ME-02613 |  | 2019-09-12 | 2
036909C-1030-SP-0510-3010 | Mechanical Equipment Data Sheet C4 Vaporization Tower | 0 | 2019-09-02 | IFP | OL1-2M03-3010 | ME | 2019-09-10 | 036909C-JVD-TRN-02613 | 036909C-JVD-TRN-02613 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-ME-02613 |  | 2019-09-12 | 2
036909C-1030-SP-0510-3030 | Mechanical Equipment Data Sheet After Washer | 0 | 2019-09-05 | IFP | OL1-2M03-3030 | ME | 2019-09-10 | 036909C-JVD-TRN-02613 | 036909C-JVD-TRN-02613 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-ME-02613 |  | 2019-09-12 | 2
036909C-1030-SP-0510-3040 | Mechanical Equipment Data Sheet Rectifier | 0 | 2019-09-10 | IFP | OL1-2M03-3040 | ME | 2019-09-10 | 036909C-JVD-TRN-02613 | 036909C-JVD-TRN-02613 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-ME-02613 |  | 2019-09-12 | 2
036909C-1030-SP-0510-3000 | Mechanical Equipment Data Sheet Predistillation Tower | 0 | 2019-09-04 | IFP | OL1-2M03-3000 | ME | 2019-09-10 | 036909C-JVD-TRN-02613 | 036909C-JVD-TRN-02613 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-ME-02613 |  | 2019-09-12 | 2
036909C-1012-DW-0117-2001 | USC 132U Cracking Furnace General Arrangement Cross Section Elevation | 2 | 2019-09-09 | IMP | OL1-2M06-2001 | ME | 2019-09-11 | 036909C-JVD-TRN-02629 | 036909C-JVD-TRN-02629 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-ME-02629 |  | 2019-09-12 | 2
036909C-1012-DW-0122-2203 | USC 132U Cracking Furnace Radiant Coil Tubeskin Thermocouple Details | 1 | 2019-09-09 | IMP | OL1-2M06-2203 | ME | 2019-09-11 | 036909C-JVD-TRN-02625 | 036909C-JVD-TRN-02625 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-ME-02625 |  | 2019-09-12 | 2
036909C-1011-DW-0117-1001 | USC 36M Recycle Furnace General Arrangement Cross Section Elevation | 2 | 2019-09-09 | IMP | OL1-2M06-1001 | ME | 2019-09-11 | 036909C-JVD-TRN-02626 | 036909C-JVD-TRN-02626 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-ME-02626 |  | 2019-09-12 | 2
036909C-1011-DW-0131-1550 | USC 36M Cracking Furnace Steel Stack Sections and Details | 1 | 2019-08-26 | IMP | OL1-2K32-1550 | CV | 2019-09-10 | 036909C-JVD-TRN-02606 | 036909C-JVD-TRN-02606 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02606 |  | 2019-09-10 | 3
036909C-1000-PP-808 | Site Hand Over Procedure | A | 2019-09-05 | IFR | OL1-2D92-0005 | CM | 2019-09-11 | 036909C-JVD-TRN-02620 | 036909C-JVD-TRN-02620 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CM-02620 |  | 2019-09-12 | 2
036909C-1000-DW-1430-0001-001 | General Notes for Bored Piles | 0 | 2019-09-09 | IFC | OL1-2K92-0005 | CV | 2019-09-11 | 036909C-JVD-TRN-02621 | 036909C-JVD-TRN-02621 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02621 |  | 2019-09-12 | 1
036909C-1000-DW-1430-0002-001 | General Notes For Spun Piles | A | 2019-09-10 | IFR | OL1-2K92-0006 | CV | 2019-09-11 | 036909C-JVD-TRN-02621 | 036909C-JVD-TRN-02621 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02621 |  | 2019-09-12 | 1
036909C-1055-PID-0031-5575 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - HP Flare Package | C | 2019-08-26 | IDD1 | OL1-2G43-5575 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1055-PID-0031-5555 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Polyolefins Flare | C | 2019-08-26 | IDD1 | OL1-2G43-5555 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1059-PID-0031-5908 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Phosphate Injection System | C | 2019-08-26 | IDD1 | OL1-2G43-5908 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1059-PID-0031-5907 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Oxygen Scavenger Injection System | C | 2019-08-26 | IDD1 | OL1-2G43-5907 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1055-PID-0021-5590 | P&ID- Olefins Unit 10- Vent Gas And Flare System- Flare No1-No2-No3- Relief And Flare Pilot Gas BL | A | 2019-08-26 | IDD1 | OL1-2G43-5590 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1055-PID-0021-5592 | P&ID- Olefins Unit 10- Vent Gas And Flare System- Oily Waste Water-Potable-Treated Water BL | A | 2019-08-26 | IDD1 | OL1-2G43-5592 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1055-PID-0021-5591 | P&ID- Olefins Unit 10- Vent Gas Flare System- MP-LP Steam-MP Nitrogen-Plant Air-Instr Air BL | A | 2019-08-26 | IDD1 | OL1-2G43-5591 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1030-PID-0021-3008 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Main Washer Overhead | C | 2019-08-26 | IDD1 | OL1-2G43-3008 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1030-PID-0021-3007 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Main Washer & Solvent Cooler | C | 2019-08-26 | IDD1 | OL1-2G43-3007 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1030-PID-0021-3016 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Direct Cooler And NMP Cooler | C | 2019-08-26 | IDD1 | OL1-2G43-3016 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1030-PID-0021-3009 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Main Washer Bottom Pump & Reflux Pump | C | 2019-08-26 | IDD1 | OL1-2G43-3009 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1055-PID-0031-5503 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Methanol Vaporizer | C | 2019-08-26 | IDD1 | OL1-2G43-5503 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1055-PID-0031-5502 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Drum | C | 2019-08-26 | IDD1 | OL1-2G43-5502 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1055-PID-0031-5553 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - HP Flare Pilot Gas | C | 2019-08-26 | IDD1 | OL1-2G43-5553 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1055-PID-0031-5551 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - HP Flare KO Drum | C | 2019-08-26 | IDD1 | OL1-2G43-5551 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1055-PID-0021-5594 | P&ID- Olefins Unit 10- Vent Gas And flare System- HP Flare- Flare No1- Interconnecting | A | 2019-08-26 | IDD1 | OL1-2G43-5594 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1055-PID-0021-5593 | P&ID- Olefins Unit 10- Vent Gas And Flare System- Others Units HP-Polyolefins Flare Relief BL | A | 2019-08-26 | IDD1 | OL1-2G43-5593 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1055-PID-0031-5501 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Flare Drum | C | 2019-08-26 | IDD1 | OL1-2G43-5501 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1055-PID-0021-5595 | P&ID- Olefins Unit 10- Vent gas And Flare System- Polyolefins Flare- Flare No2- Interconnecting | A | 2019-08-26 | IDD1 | OL1-2G43-5595 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1030-PID-0021-3003 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Predistillation Tower Trim Reboilers | C | 2019-08-26 | IDD1 | OL1-2G43-3003 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1030-PID-0021-3004 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Predistillation Tower Overhead | C | 2019-08-26 | IDD1 | OL1-2G43-3004 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1030-PID-0021-3001 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Predistillation Feed Drum & Feed Pumps | C | 2019-08-26 | IDD1 | OL1-2G43-3001 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1030-PID-0021-3002 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Predistillation Tower & Reboiler | C | 2019-08-26 | IDD1 | OL1-2G43-3002 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1030-PID-0021-3006 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - C4 Vaporizers | C | 2019-08-26 | IDD1 | OL1-2G43-3006 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1030-PID-0021-3005 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - C4 Vaporization Tower & Heavy End Disch Pumps | C | 2019-08-26 | IDD1 | OL1-2G43-3005 | PE | 2019-08-30 | 036909C-JVD-TRN-02555 | 036909C-JVD-TRN-02555 | IFR | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-PE-02555 |  | 2019-09-03 | 2
036909C-1051-PID-0031-5111 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Boiler Feedwater Pumps | C | 2019-08-26 | IDD1 | OL1-2G43-5111 | PE | 2019-09-03 | 036909C-JVD-TRN-02564 | 036909C-JVD-TRN-02564 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02564 |  | 2019-09-04 | 2
036909C-1051-PID-0031-5120 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Carbon Filters | C | 2019-08-26 | IDD1 | OL1-2G43-5120 | PE | 2019-09-03 | 036909C-JVD-TRN-02564 | 036909C-JVD-TRN-02564 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02564 |  | 2019-09-04 | 2
036909C-1051-PID-0031-5118 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Suspect Condensate Cooling | C | 2019-08-26 | IDD1 | OL1-2G43-5118 | PE | 2019-09-03 | 036909C-JVD-TRN-02564 | 036909C-JVD-TRN-02564 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02564 |  | 2019-09-04 | 2
036909C-1051-PID-0031-5186 | P&ID- Olefins Unit 10- BFW- Steam Condensate System- VLP BFW Lube Oil Pump Turbine Details | A | 2019-08-26 | IDD1 | OL1-2G43-5186 | PE | 2019-09-03 | 036909C-JVD-TRN-02564 | 036909C-JVD-TRN-02564 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02564 |  | 2019-09-04 | 2
036909C-1051-PID-0031-5110 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP Boiler Feedwater Pumps | C | 2019-08-26 | IDD1 | OL1-2G43-5110 | PE | 2019-09-03 | 036909C-JVD-TRN-02564 | 036909C-JVD-TRN-02564 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02564 |  | 2019-09-04 | 2
036909C-1051-PID-0031-5105 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Deaerator | C | 2019-08-26 | IDD1 | OL1-2G43-5105 | PE | 2019-09-03 | 036909C-JVD-TRN-02564 | 036909C-JVD-TRN-02564 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02564 |  | 2019-09-04 | 2
036909C-1051-PID-0031-5180 | P&ID- Olefins Unit 10- BFW-Steam- Steam Condensate System- SHP BFW Lube Oil Pump Turbine A Details | A | 2019-08-26 | IDD1 | OL1-2G43-5180 | PE | 2019-09-03 | 036909C-JVD-TRN-02564 | 036909C-JVD-TRN-02564 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02564 |  | 2019-09-04 | 2
036909C-1051-PID-0031-5183 | P&ID- Olefins Unit 10- BFW- Steam- Steam Condensate System- SHP BFW Lube Oil Pump Turbine B Details | A | 2019-08-26 | IDD1 | OL1-2G43-5183 | PE | 2019-09-03 | 036909C-JVD-TRN-02564 | 036909C-JVD-TRN-02564 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02564 |  | 2019-09-04 | 2
036909C-1051-PID-0031-5145 | P&ID- Olefins Unit 10- BFW- Steam- Steam Condensate System- VLP BFW Pump Turbine Details | A | 2019-08-26 | IDD1 | OL1-2G43-5145 | PE | 2019-09-03 | 036909C-JVD-TRN-02564 | 036909C-JVD-TRN-02564 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02564 |  | 2019-09-04 | 2
036909C-1051-PID-0031-5153 | P&ID- Olefins Unit 10-BFW- Steam- Steam Condensate System- SHP BFW Pump Turbine Details | A | 2019-08-26 | IDD1 | OL1-2G43-5153 | PE | 2019-09-03 | 036909C-JVD-TRN-02564 | 036909C-JVD-TRN-02564 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02564 |  | 2019-09-04 | 2
036909C-1051-PID-0031-5132 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Low Pressure Steam Flash Drum | C | 2019-08-26 | IDD1 | OL1-2G43-5132 | PE | 2019-09-03 | 036909C-JVD-TRN-02564 | 036909C-JVD-TRN-02564 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02564 |  | 2019-09-04 | 2
036909C-1051-PID-0031-5127 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Polisher - Sheet 1 | C | 2019-08-26 | IDD1 | OL1-2G43-5127 | PE | 2019-09-03 | 036909C-JVD-TRN-02564 | 036909C-JVD-TRN-02564 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02564 |  | 2019-09-04 | 2
036909C-1051-PID-0031-5128 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Polisher - Sheet 2 | C | 2019-08-26 | IDD1 | OL1-2G43-5128 | PE | 2019-09-03 | 036909C-JVD-TRN-02564 | 036909C-JVD-TRN-02564 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02564 |  | 2019-09-04 | 2
036909C-1051-PID-0031-5135 | P&ID- Olefins Unit 10- BFW-Steam- Steam Condensate System- Condensate Pump Turbine Details | A | 2019-08-26 | IDD1 | OL1-2G43-5135 | PE | 2019-09-03 | 036909C-JVD-TRN-02564 | 036909C-JVD-TRN-02564 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02564 |  | 2019-09-04 | 2
036909C-1051-PID-0031-5134 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Furnace Blowdown System | C | 2019-08-26 | IDD1 | OL1-2G43-5134 | PE | 2019-09-03 | 036909C-JVD-TRN-02564 | 036909C-JVD-TRN-02564 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02564 |  | 2019-09-04 | 2
036909C-1030-PID-0021-3017 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Degassing Tower And Reboiler | C | 2019-08-26 | IDD1 | OL1-2G43-3017 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3018 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Direct Cooler Pump & Degasser Bottom Pump | C | 2019-08-26 | IDD1 | OL1-2G43-3018 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3020 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Acetylene Wash Condenser | C | 2019-08-26 | IDD1 | OL1-2G43-3020 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3019 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - HC - Water Separator | C | 2019-08-26 | IDD1 | OL1-2G43-3019 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3027 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Tower Overhead | C | 2019-08-26 | IDD1 | OL1-2G43-3027 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3026 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Tower Bottom Pump | C | 2019-08-26 | IDD1 | OL1-2G43-3026 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3029 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Product To B L | C | 2019-08-26 | IDD1 | OL1-2G43-3029 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3028 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Drying Tower And Reboiler | C | 2019-08-26 | IDD1 | OL1-2G43-3028 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3023 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Recycle Gas Compressor | C | 2019-08-26 | IDD1 | OL1-2G43-3023 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3011 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Rectifier Pump And Degasser Feed Pump | C | 2019-08-26 | IDD1 | OL1-2G43-3011 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3025 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Tower Reboilers | C | 2019-08-26 | IDD1 | OL1-2G43-3025 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3024 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Tower | C | 2019-08-26 | IDD1 | OL1-2G43-3024 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3014 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Solvent Heat Exchangers - I | C | 2019-08-26 | IDD1 | OL1-2G43-3014 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3013 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - After Washer Overhead | C | 2019-08-26 | IDD1 | OL1-2G43-3013 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3021 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Acetylene Condenser And Accumulator | C | 2019-08-26 | IDD1 | OL1-2G43-3021 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3015 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Solvent Heat Exchanger-II And Solvent Heater | C | 2019-08-26 | IDD1 | OL1-2G43-3015 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3022 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - C4 Acetylene Pumps | C | 2019-08-26 | IDD1 | OL1-2G43-3022 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3090 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - C4 - Butadiene - OFF-SPEC 1-3 BD Battery Limit | A | 2019-08-26 | IDD1 | OL1-2G43-3090 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3012 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - After Washer | C | 2019-08-26 | IDD1 | OL1-2G43-3012 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1030-PID-0021-3010 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Rectifier | C | 2019-08-26 | IDD1 | OL1-2G43-3010 | PE | 2019-09-05 | 036909C-JVD-TRN-02574 | 036909C-JVD-TRN-02574 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-PE-02574 |  | 2019-09-10 | 2
036909C-1054-PID-0031-5403 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 3 | C | 2019-08-30 | IDD1 | OL1-2G43-5403 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1054-PID-0031-5404 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 4 | C | 2019-08-30 | IDD1 | OL1-2G43-5404 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1054-PID-0021-5490 | P&ID- Olefins Unit 10- Plant Air- Instrument Air- Nitrogen- Plant Air- Instrument Air- MP Nitrogen BL | A | 2019-08-30 | IDD1 | OL1-2G43-5490 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1054-PID-0031-5402 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 2 | C | 2019-08-30 | IDD1 | OL1-2G43-5402 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1054-PID-0031-5401 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 1 | C | 2019-08-30 | IDD1 | OL1-2G43-5401 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1054-PID-0031-5424 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 4 | C | 2019-08-30 | IDD1 | OL1-2G43-5424 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1054-PID-0031-5426 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 6 | C | 2019-08-30 | IDD1 | OL1-2G43-5426 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1054-PID-0031-5425 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 5 | C | 2019-08-30 | IDD1 | OL1-2G43-5425 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1054-PID-0031-5420 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 1 | C | 2019-08-30 | IDD1 | OL1-2G43-5420 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1054-PID-0031-5422 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 3 | C | 2019-08-30 | IDD1 | OL1-2G43-5422 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1054-PID-0031-5421 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 2 | C | 2019-08-30 | IDD1 | OL1-2G43-5421 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1051-PID-0021-5190 | P&ID- Olefins Unit 10- BFW- Steam- Steam Condensate System- Return Condensate-HP Steam- HBFW BL | A | 2019-08-30 | IDD1 | OL1-2G43-5190 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1050-PID-0031-5010 | P&Id - Olefins Unit 10 - Water System - Treated - Potable - Demin - Supporting Utilities Auxiliaries Treated Water | C | 2019-08-30 | IDD1 | OL1-2G43-5010 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1050-PID-0031-5020 | P&Id - Olefins Unit 10 - Water System -Treated - Potable - Demin - Potable Water | C | 2019-08-30 | IDD1 | OL1-2G43-5020 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1051-PID-0031-5140 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP Steam Distribution | C | 2019-08-30 | IDD1 | OL1-2G43-5140 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1051-PID-0031-5125 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Raw Condensate Tank | C | 2019-08-30 | IDD1 | OL1-2G43-5125 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1051-PID-0031-5130 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Tank | C | 2019-08-30 | IDD1 | OL1-2G43-5130 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1050-PID-0031-5001 | P&Id - Olefins Unit 10 - Water System - Treated - Potable - Demin - Demineralized Water | C | 2019-08-30 | IDD1 | OL1-2G43-5001 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1050-PID-0021-5090 | P&ID- Olefins Unit 10- Water System -Treated Potable Demin- Demin- Potable- Treated Water Battery Limit | A | 2019-08-30 | IDD1 | OL1-2G43-5090 | PE | 2019-09-09 | 036909C-JVD-TRN-02588 | 036909C-JVD-TRN-02588 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-PE-02588 |  | 2019-09-10 | 2
036909C-1031-PID-0031-3107 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drum | C | 2019-08-30 | IDD1 | OL1-2G43-3107 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1031-PID-0031-3108 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Water Washer Accumulator & Solvent Return Pumps | C | 2019-08-30 | IDD1 | OL1-2G43-3108 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1039-PID-0031-3904 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Anti-Foam Agent Injection System | C | 2019-08-30 | IDD1 | OL1-2G43-3904 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1031-PID-0031-3106 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Regen Steam Ejector Package | C | 2019-08-30 | IDD1 | OL1-2G43-3106 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1031-PID-0031-3112 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drum | C | 2019-08-30 | IDD1 | OL1-2G43-3112 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1031-PID-0031-3110 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Ejector Seal Drum And Waste Water Pumps | C | 2019-08-30 | IDD1 | OL1-2G43-3110 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1031-PID-0031-3109 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Drum And Recycle Pumps | C | 2019-08-30 | IDD1 | OL1-2G43-3109 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1031-PID-0031-3113 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drain System - Sheet 2 | C | 2019-08-30 | IDD1 | OL1-2G43-3113 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1039-PID-0031-3905 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Predistillation Inhibitor System | C | 2019-08-30 | IDD1 | OL1-2G43-3905 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1031-PID-0031-3101 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Solvent Regeneration | C | 2019-08-30 | IDD1 | OL1-2G43-3101 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1039-PID-0031-3901 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - NMP Storage | C | 2019-08-30 | IDD1 | OL1-2G43-3901 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1039-PID-0031-3902 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Solvent Inhibitor Injection System | C | 2019-08-30 | IDD1 | OL1-2G43-3902 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1031-PID-0031-3105 | P&ID- Olefins Unit 10- Butadiene Extraction Unit Utilities- Ejector Seal Drum And Waste Water Pumps | C | 2019-08-30 | IDD1 | OL1-2G43-3105 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1039-PID-0031-3903 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Product Inhibitor Injection System | C | 2019-08-30 | IDD1 | OL1-2G43-3903 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1031-PID-0031-3102 | P&ID- Olefins Unit 10- Butadiene Extraction Unit Utlities- Water Washer And Condenser | C | 2019-08-30 | IDD1 | OL1-2G43-3102 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1031-PID-0031-3104 | P&ID- Olefins Unit 10- Butadiene Extraction Unit Utlities- Water Washer Accumulator & Solvent Return Pumps | C | 2019-08-30 | IDD1 | OL1-2G43-3104 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1031-PID-0031-3103 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Water Washer And Condenser | C | 2019-08-30 | IDD1 | OL1-2G43-3103 | PE | 2019-09-10 | 036909C-JVD-TRN-02602 | 036909C-JVD-TRN-02602 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02602 |  | 2019-09-10 | 2
036909C-1053-PID-0031-5321 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 2 | C | 2019-09-09 | IDD1 | OL1-2G43-5321 | PE | 2019-09-10 | 036909C-JVD-TRN-02609 | 036909C-JVD-TRN-02609 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02609 |  | 2019-09-11 | 2
036909C-1051-PID-0031-5115 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Suspect Condensate Collection | C | 2019-09-09 | IDD1 | OL1-2G43-5115 | PE | 2019-09-10 | 036909C-JVD-TRN-02609 | 036909C-JVD-TRN-02609 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02609 |  | 2019-09-11 | 2
036909C-1056-PID-0031-5660 | P&ID - Olefins Unit 10 - Wastewater - Final Check Basin | C | 2019-09-09 | IDD1 | OL1-2G43-5660 | PE | 2019-09-10 | 036909C-JVD-TRN-02609 | 036909C-JVD-TRN-02609 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02609 |  | 2019-09-11 | 2
036909C-1053-PID-0031-5323 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 4 | C | 2019-09-09 | IDD1 | OL1-2G43-5323 | PE | 2019-09-10 | 036909C-JVD-TRN-02609 | 036909C-JVD-TRN-02609 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02609 |  | 2019-09-11 | 2
036909C-1031-SP-0510-3110 | Mechanical Equipment Datasheet - Water Washer | A | 2019-04-02 | IFQ | OL1-2M03-3110 | ME | 2019-04-08 | 036909C-JVD-TRN-01275 | 036909C-JVD-TRN-01275 | IFR | 2019-04-23 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME-01275 |  | 2019-04-09 | 2
036909C-1031-SP-0510-3110 | Mechanical Equipment Datasheet - Water Washer | B | 2019-06-18 | IFQ | OL1-2M03-3110 | ME | 2019-06-18 | 036909C-JVD-TRN-01916 | 036909C-JVD-TRN-01916 | IFR | 2019-07-03 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-01916 |  | 2019-06-19 | 2
036909C-1030-SP-0510-3090 | Mechanical Equipment Datasheet - Butadiene Drying Tower | A | 2019-04-09 | IFQ | OL1-2M03-3090 | ME | 2019-04-10 | 036909C-JVD-TRN-01312 | 036909C-JVD-TRN-01312 | IFR | 2019-04-25 |  | Transmitted | TPSK-LSPA1-T-ME-01312 |  | 2019-04-11 | 2
036909C-1030-SP-0510-3090 | Mechanical Equipment Datasheet - Butadiene Drying Tower | B | 2019-06-13 | IFQ | OL1-2M03-3090 | ME | 2019-06-13 | 036909C-JVD-TRN-01893 | 036909C-JVD-TRN-01893 | IFR | 2019-06-28 |  | Transmitted | TPSK-LSPA1-T-ME-01893 |  | 2019-06-14 | 2
036909C-1030-SP-0510-3080 | Mechanical Equipment Datasheet - Butadiene Tower | A | 2019-04-03 | IFQ | OL1-2M03-3080 | ME | 2019-04-08 | 036909C-JVD-TRN-01275 | 036909C-JVD-TRN-01275 | IFR | 2019-04-23 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME-01275 |  | 2019-04-09 | 2
036909C-1030-SP-0510-3080 | Mechanical Equipment Data Sheet - Butadiene Tower | B | 2019-06-13 | IFQ | OL1-2M03-3080 | ME | 2019-06-13 | 036909C-JVD-TRN-01893 | 036909C-JVD-TRN-01893 | IFR | 2019-06-28 |  | Transmitted | TPSK-LSPA1-T-ME-01893 |  | 2019-06-14 | 2
036909C-1030-SP-0510-3070 | Mechanical Equipment Datasheet - Direct Cooler Tower | B | 2019-06-12 | IFQ | OL1-2M03-3070 | ME | 2019-06-13 | 036909C-JVD-TRN-01893 | 036909C-JVD-TRN-01893 | IFR | 2019-06-28 |  | Transmitted | TPSK-LSPA1-T-ME-01893 |  | 2019-06-14 | 2
036909C-1030-SP-0510-3070 | Mechanical Equipment Datasheet - Direct Cooler Tower | A | 2019-04-02 | IFQ | OL1-2M03-3070 | ME | 2019-04-08 | 036909C-JVD-TRN-01275 | 036909C-JVD-TRN-01275 | IFR | 2019-04-23 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME-01275 |  | 2019-04-09 | 2
036909C-1030-SP-0510-3060 | Mechanical Equipment Datasheet - C4 Acetylene Washer | A | 2019-04-02 | IFQ | OL1-2M03-3060 | ME | 2019-04-08 | 036909C-JVD-TRN-01275 | 036909C-JVD-TRN-01275 | IFR | 2019-04-23 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME-01275 |  | 2019-04-09 | 2
036909C-1030-SP-0510-3060 | Mechanical Equipment Datasheet - C4 Acetylene Washer | B | 2019-06-11 | IFQ | OL1-2M03-3060 | ME | 2019-06-11 | 036909C-JVD-TRN-01870 | 036909C-JVD-TRN-01870 | IFR | 2019-06-26 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-01870 |  | 2019-06-11 | 2
036909C-1030-SP-0510-3050 | Mechanical Equipment Datasheet - Degasser | B | 2019-06-13 | IFQ | OL1-2M03-3050 | ME | 2019-06-13 | 036909C-JVD-TRN-01893 | 036909C-JVD-TRN-01893 | IFR | 2019-06-28 |  | Transmitted | TPSK-LSPA1-T-ME-01893 |  | 2019-06-14 | 2
036909C-1030-SP-0510-3050 | Mechanical Equipment Datasheet - Degasser | A | 2019-04-04 | IFQ | OL1-2M03-3050 | ME | 2019-04-11 | 036909C-JVD-TRN-01325 | 036909C-JVD-TRN-01325 | IFR | 2019-04-26 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME-01325 |  | 2019-04-12 | 2
036909C-1030-SP-0510-3040 | Mechanical Equipment Datasheet - Rectifier | A | 2019-04-04 | IFQ | OL1-2M03-3040 | ME | 2019-04-08 | 036909C-JVD-TRN-01275 | 036909C-JVD-TRN-01275 | IFR | 2019-04-23 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME-01275 |  | 2019-04-09 | 2
036909C-1030-SP-0510-3040 | Mechanical Datasheet Rectifier | B | 2019-06-13 | IFQ | OL1-2M03-3040 | ME | 2019-06-13 | 036909C-JVD-TRN-01893 | 036909C-JVD-TRN-01893 | IFR | 2019-06-28 |  | Transmitted | TPSK-LSPA1-T-ME-01893 |  | 2019-06-14 | 2
036909C-1030-SP-0510-3030 | Mechanical Equipment Datasheet - After Washer | A | 2019-04-11 | IFQ | OL1-2M03-3030 | ME | 2019-04-11 | 036909C-JVD-TRN-01325 | 036909C-JVD-TRN-01325 | IFR | 2019-04-26 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME-01325 |  | 2019-04-12 | 2
036909C-1030-SP-0510-3030 | Mechanical Equipment Data Sheet - After Washer | B | 2019-06-12 | IFQ | OL1-2M03-3030 | ME | 2019-06-13 | 036909C-JVD-TRN-01893 | 036909C-JVD-TRN-01893 | IFR | 2019-06-28 |  | Transmitted | TPSK-LSPA1-T-ME-01893 |  | 2019-06-14 | 2
036909C-1030-SP-0510-3010 | Mechanical Equipment Datasheet - C4 Vaporization Tower | A | 2019-04-02 | IFQ | OL1-2M03-3010 | ME | 2019-04-08 | 036909C-JVD-TRN-01275 | 036909C-JVD-TRN-01275 | IFR | 2019-04-23 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME-01275 |  | 2019-04-08 | 2
036909C-1030-SP-0510-3010 | Mechanical Equipment DataSheet - C4 Vaporization Tower | B | 2019-06-06 | IFQ | OL1-2M03-3010 | ME | 2019-06-06 | 036909C-JVD-TRN-01818 | 036909C-JVD-TRN-01818 | IFR | 2019-06-21 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-01818 |  | 2019-06-10 | 2
036909C-1030-SP-0510-3010 | Mechanical Equipment Datasheet - C4 Vaporization Tower | C | 2019-06-14 | IFQ | OL1-2M03-3010 | ME | 2019-06-17 | 036909C-JVD-TRN-01909 | 036909C-JVD-TRN-01909 | IFR | 2019-07-02 |  | Transmitted | TPSK-LSPA1-T-ME-01909 |  | 2019-06-18 | 2
036909C-1030-SP-0510-3000 | Mechanical Equipment Datasheet - Predistillation Tower | C | 2019-06-14 | IFQ | OL1-2M03-3000 | ME | 2019-06-17 | 036909C-JVD-TRN-01909 | 036909C-JVD-TRN-01909 | IFR | 2019-07-02 |  | Transmitted | TPSK-LSPA1-T-ME-01909 |  | 2019-06-18 | 2
036909C-1030-SP-0510-3000 | Mechanical Equipment Datasheet - Predistillation Tower | A | 2019-03-29 | IFQ | OL1-2M03-3000 | ME | 2019-04-08 | 036909C-JVD-TRN-01275 | 036909C-JVD-TRN-01275 | IFR | 2019-04-23 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME-01275 |  | 2019-04-09 | 2
036909C-1030-SP-0510-3000 | Mechanical Equipment Datasheet - Predistillation Tower | B | 2019-06-07 | IFQ | OL1-2M03-3000 | ME | 2019-06-11 | 036909C-JVD-TRN-01870 | 036909C-JVD-TRN-01870 | IFR | 2019-06-26 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-01870 |  | 2019-06-11 | 2
036909C-1030-SP-0510-3020 | Mechanical Equipment Datasheet - Main Washer | B | 2019-06-07 | IFQ | OL1-2M03-3020 | ME | 2019-06-11 | 036909C-JVD-TRN-01870 | 036909C-JVD-TRN-01870 | IFR | 2019-06-26 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-01870 |  | 2019-06-11 | 2
036909C-1030-SP-0510-3020 | Mechanical Equipment Datasheet - Main Washer | A | 2019-04-02 | IFQ | OL1-2M03-3020 | ME | 2019-04-08 | 036909C-JVD-TRN-01275 | 036909C-JVD-TRN-01275 | IFR | 2019-04-23 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME-01275 |  | 2019-04-09 | 2
036909C-1000-DW-1422-0003-001 | Olefins Plant - Additional Ground Investigation Phase 2 Platform At 6-7m HDD - Layout Of Site Investigations | B | 2019-06-06 | IFR | OL1-2K43-0008 | CV | 2019-06-11 | 036909C-JVD-TRN-01853 | 036909C-JVD-TRN-01853 |  | 2019-06-26 |  | Transmitted |  |  | 2019-06-11 | 2
036909C-1000-DW-1430-0001-001 | General Notes For Piles | A | 2019-03-15 | IFR | OL1-2K92-0005 | CV | 2019-03-19 | 036909C-JVD-TRN-01093 | 036909C-JVD-TRN-01093, ROC-TPSK-CECO-T-00021 | IFR | 2019-04-03 | 2019-04-12 | A1-Approved without comments | TPSK-LSPA1-T-CV-01093 |  | 2019-03-20 | 1
036909C-1012-DW-0122-2203 | USC 132U Cracking Furnace Radiant Coil Tubeskin Thermocouple Details | 0 | 2018-12-11 | IMP | OL1-2M06-2203 | ME | 2018-12-13 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00486 |  | 2018-12-13 | 2
036909C-1012-DW-0122-2203 | USC 132U Cracking Furnace Radiant Coil Tubeskin Thermocouple Details | A | 2018-09-11 | IFR | OL1-2M06-2203 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00062 |  | 2018-10-08 | 2
036909C-1011-DW-0117-1004 | USC 36M Recycle Furnace General Arrangement Instrumentation | A | 2019-01-09 | IFR | OL1-2M06-1004 | ME | 2019-01-30 | 036909C-JVD-TRN-00764 | 036909C-JVD-TRN-00764 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00764 |  | 2019-01-31 | 2
036909C-1011-DW-0117-1001 | USC 36M Recycle Furnace General Arrangement Cross Section Elevation | A | 2018-11-15 | IFR | OL1-2M06-1001 | ME | 2018-11-16 | 036909C-JVD-TRN-00327 | 036909C-JVD-TRN-00327 | IFR | 2018-11-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-ME-00327 |  | 2018-11-16 | 2
036909C-1011-DW-0117-1001 | USC 36M Recycle Furnace General Arrangement Cross Section Elevation | 0 | 2019-04-12 | IMP | OL1-2M06-1001 | ME | 2019-04-15 | 036909C-JVD-TRN-01361 | 036909C-JVD-TRN-01361 | IFR | 2019-04-30 |  | Transmitted | TPSK-LSPA1-T-ME-01361 |  | 2019-04-16 | 2
036909C-1012-DW-0117-2001 | USC 132U Cracking Furnace General Arrangement Cross Section Elevation | A | 2018-11-15 | IFR | OL1-2M06-2001 | ME | 2018-11-16 | 036909C-JVD-TRN-00328 | 036909C-JVD-TRN-00328 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-ME-00328 |  | 2018-11-16 | 2
036909C-1012-DW-0117-2001 | USC 132U Cracking Furnace General Arrangement Cross Section Elevation | 0 | 2019-04-12 | IMP | OL1-2M06-2001 | ME | 2019-04-16 | 036909C-JVD-TRN-01369 | 036909C-JVD-TRN-01369 | IFR | 2019-05-01 |  | Transmitted | TPSK-LSPA1-T-ME-01369 |  | 2019-04-17 | 2
036909C-1039-CN-0014-3954 | PSV-3954 PSV-3955 PSV-3956 PSV-3957 PSV-3958 PSV-3959 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3954 | PE | 2019-08-02 | 036909C-JVD-TRN-02337 | 036909C-JVD-TRN-02337 | IFR | 2019-08-17 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02337 |  | 2019-08-05 | 2
036909C-1031-PDS-1390-3102 | Piping Specialty Item – T-Type Filter - P-3160A/B Suction SRT-31001 | A | 2019-08-08 | IFR | OL1-2P03-3102 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-11 | R1-No comments | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-PO-036909C001P87 | Vendor s Acknowledgment of Purchase Order For API Centrifugal Pumps Rev 0 – MR 0910-0002 Rev. 0 | 0 | 2019-09-10 | IFI | OL1-2C51-0018 | PL | 2019-09-10 | 036909C-JVD-TRN-02611 | 036909C-JVD-TRN-02611 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02611 |  | 2019-09-11 | 3
036909C-1051-PDS-1390-5108 | SP Item Data Sheet - SHP - HP Letdown Desuperheater - SP-51008 - For next revision see OL1-2G31-5151 | 0 | 2019-09-09 | CAN | OL1-2G31-5151 | MP | 2019-09-10 | 036909C-JVD-TRN-02604 | 036909C-JVD-TRN-02604 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-MP-02604 | For next revision see OL1-2G31-5151 | 2019-09-11 | 2
036909C-1051-PDS-1390-5107 | SP Item Data Sheet - HP - MP Letdown Desuperheater - SP-51007 - For next revision see OL1-2G31-5102 | 0 | 2019-09-09 | CAN | OL1-2G31-5102 | MP | 2019-09-10 | 036909C-JVD-TRN-02604 | 036909C-JVD-TRN-02604 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-MP-02604 | For next revision see OL1-2G31-5102 | 2019-09-11 | 2
036909C-1051-PDS-1390-5105 | SP Item Data Sheet - LP LS1 VLP LS2 Letdown Desuperheater - SP-51005 - For next revision see OL1-2G31-5104 | 0 | 2019-09-09 | CAN | OL1-2G31-5104 | MP | 2019-09-10 | 036909C-JVD-TRN-02604 | 036909C-JVD-TRN-02604 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-MP-02604 | For next revision see OL1-2G31-5104 | 2019-09-11 | 2
036909C-1051-PDS-1390-5106 | SP Item Data Sheet - MP - LP LS1 Letdown Desuperheater - SP-51006 - For next revision see OL1-2G31-5103 | 0 | 2019-09-09 | CAN | OL1-2G31-5103 | MP | 2019-09-10 | 036909C-JVD-TRN-02604 | 036909C-JVD-TRN-02604 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-MP-02604 | For next revision see OL1-2G31-5103 | 2019-09-11 | 2
036909C-102A-CN-1733-0007 | Calculation Note For Foundation Of 10-D-2136 | A | 2019-09-04 | IFR | OL1-2K13-0013 | CV | 2019-09-06 | 036909C-JVD-TRN-02583 | 036909C-JVD-TRN-02583 | IFA | 2019-09-23 |  | Transmitted | TPSK-LSPA1-T-CV-02583 |  | 2019-09-10 | 1
036909C-1000-MTO-1639-0002 | Lighting System Material Take-Off (OSBL Units) | A | 2019-09-05 | IF1T | OL1-2E63-0008 | EE | 2019-09-10 | 036909C-JVD-TRN-02600 | 036909C-JVD-TRN-02600 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-EE-02600 |  | 2019-09-11 | 2
036909C-1000-ML-1007 | Butadiene Unit BDU Operating Manual | 0 | 2019-09-10 | IFI | OL1-2G76-1007 | PE | 2019-09-10 | 036909C-JVD-TRN-02614 | 036909C-JVD-TRN-02614 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02614 |  | 2019-09-11 | 3
036909C-1000-ML-1006 | C4 & C5 Hydrogenation Unit Operating Manual | 0 | 2019-09-10 | IFI | OL1-2G76-1006 | PE | 2019-09-10 | 036909C-JVD-TRN-02614 | 036909C-JVD-TRN-02614 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02614 |  | 2019-09-11 | 3
036909C-1000-MTO-1629-0002 | Power System Material Take-Off (OSBL Units) | A | 2019-09-06 | IF1T | OL1-2E63-0006 | EE | 2019-09-10 | 036909C-JVD-TRN-02600 | 036909C-JVD-TRN-02600 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-EE-02600 |  | 2019-09-11 | 2
036909C-1000-ML-1004 | Gasoline Hydrogenation Unit GHU Operating Manual | 0 | 2019-09-10 | IFI | OL1-2G76-1004 | PE | 2019-09-10 | 036909C-JVD-TRN-02614 | 036909C-JVD-TRN-02614 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02614 |  | 2019-09-11 | 3
036909C-1000-JSD-1600-0005 | Substation Design | A | 2019-09-06 | IFR | OL1-2R05-0024 | EE | 2019-09-10 | 036909C-JVD-TRN-02603 | 036909C-JVD-TRN-02603 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-EE-02603 |  | 2019-09-11 | 2
036909C-PO-036909C001P90 | Vendor s Acknowledgment of Purchase Order For Hairpin Heat Exchangers Rev. 0 MR-0630-0001 Rev. 0 | 0 | 2019-08-29 | IFI | OL1-2C51-0017 | PL | 2019-08-29 | 036909C-JVD-TRN-02536 | 036909C-JVD-TRN-02536 | IFI |  | 2019-09-05 | R1-No comments | TPSK-LSPA1-T-PL-02536 |  | 2019-08-30 | 3
036909C-1056-PID-0031-5660 | P&ID - Olefins Unit 10 - Wastewater - Final Check Basin | A | 2019-02-13 | IFR | OL1-2G43-5660 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5660 | P&ID - Olefins Unit 10 - Wastewater - Final Check Basin | B | 2019-04-26 | IBD | OL1-2G43-5660 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1053-PID-0031-5323 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 4 | B | 2019-04-18 | IBD | OL1-2G43-5323 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5323 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 04 | A | 2018-12-11 | IFR | OL1-2G43-5323 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5321 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 02 | A | 2018-12-11 | IFR | OL1-2G43-5321 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5321 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 2 | B | 2019-04-18 | IBD | OL1-2G43-5321 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1051-PID-0031-5115 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Suspect Condensate Collection | B | 2019-04-24 | IBD | OL1-2G43-5115 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5115 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Suspect Condensate Collection | A | 2019-01-23 | IFR | OL1-2G43-5115 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PDS-1390-5108 | SP Item Data Sheet - SHP - HP Letdown Desuperheater - SP-51008 | A | 2019-07-25 | IFR | OL1-2P03-5108 | MP | 2019-08-01 | 036909C-JVD-TRN-02317 | 036909C-JVD-TRN-02317 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02317 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5107 | SP Item Data Sheet - HP - MP Letdown Desuperheater - SP-51007 | A | 2019-07-25 | IFR | OL1-2P03-5107 | MP | 2019-08-01 | 036909C-JVD-TRN-02317 | 036909C-JVD-TRN-02317 | IFR | 2019-08-16 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-MP-02317 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5106 | SP Item Data Sheet - MP - LP LS1 Letdown Desuperheater - SP-51006 | A | 2019-07-25 | IFR | OL1-2P03-5106 | MP | 2019-08-01 | 036909C-JVD-TRN-02317 | 036909C-JVD-TRN-02317 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02317 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5105 | SP Item Data Sheet - LP LS1 VLP LS2 Letdown Desuperheater - SP-51005 | A | 2019-07-25 | IFR | OL1-2P03-5105 | MP | 2019-08-01 | 036909C-JVD-TRN-02317 | 036909C-JVD-TRN-02317 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02317 |  | 2019-08-05 | 2
036909C-1054-PID-0031-5426 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 6 | A | 2019-01-28 | IFR | OL1-2G43-5426 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758 |  | 2019-01-29 | 2
036909C-1054-PID-0031-5426 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 6 | B | 2019-04-24 | IBD | OL1-2G43-5426 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1054-PID-0031-5425 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 5 | B | 2019-04-24 | IBD | OL1-2G43-5425 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1054-PID-0031-5425 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 5 | A | 2019-01-28 | IFR | OL1-2G43-5425 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758 |  | 2019-01-29 | 2
036909C-1054-PID-0031-5424 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 4 | A | 2019-01-28 | IFR | OL1-2G43-5424 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758 |  | 2019-01-29 | 2
036909C-1054-PID-0031-5424 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 4 | B | 2019-04-24 | IBD | OL1-2G43-5424 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1054-PID-0031-5422 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 3 | B | 2019-04-24 | IBD | OL1-2G43-5422 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1054-PID-0031-5422 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 3 | A | 2019-01-28 | IFR | OL1-2G43-5422 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758 |  | 2019-01-29 | 2
036909C-1054-PID-0031-5421 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 2 | A | 2019-01-28 | IFR | OL1-2G43-5421 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758 |  | 2019-01-29 | 2
036909C-1054-PID-0031-5421 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 2 | B | 2019-04-24 | IBD | OL1-2G43-5421 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1054-PID-0031-5420 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 1 | B | 2019-04-24 | IBD | OL1-2G43-5420 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1054-PID-0031-5420 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 1 | A | 2019-01-28 | IFR | OL1-2G43-5420 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758 |  | 2019-01-29 | 2
036909C-1054-PID-0031-5404 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 4 | A | 2019-01-28 | IFR | OL1-2G43-5404 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758 |  | 2019-01-29 | 2
036909C-1054-PID-0031-5404 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 4 | B | 2019-04-24 | IBD | OL1-2G43-5404 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1054-PID-0031-5403 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 3 | B | 2019-04-24 | IBD | OL1-2G43-5403 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1054-PID-0031-5403 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 3 | A | 2019-01-28 | IFR | OL1-2G43-5403 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758 |  | 2019-01-29 | 2
036909C-1054-PID-0031-5402 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 2 | B | 2019-04-24 | IBD | OL1-2G43-5402 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1054-PID-0031-5402 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 2 | A | 2019-01-28 | IFR | OL1-2G43-5402 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758 |  | 2019-01-29 | 2
036909C-1054-PID-0031-5401 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 1 | B | 2019-04-24 | IBD | OL1-2G43-5401 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1054-PID-0031-5401 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 1 | A | 2019-01-28 | IFR | OL1-2G43-5401 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758 |  | 2019-01-29 | 2
036909C-1051-PID-0031-5140 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP Steam Distribution | A | 2019-01-23 | IFR | OL1-2G43-5140 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5140 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP Steam Distribution | B | 2019-04-24 | IBD | OL1-2G43-5140 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5130 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Tank | A | 2019-01-23 | IFR | OL1-2G43-5130 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5130 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Tank | B | 2019-04-24 | IBD | OL1-2G43-5130 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5125 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Raw Condensate Tank | B | 2019-04-24 | IBD | OL1-2G43-5125 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5125 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Raw Condensate Tank | A | 2019-01-23 | IFR | OL1-2G43-5125 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1050-PID-0031-5020 | P&ID - Olefins Unit 10 - Water System Treated - Potable - Demin - Potable Water | A | 2019-01-23 | IFR | OL1-2G43-5020 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1050-PID-0031-5020 | P&Id - Olefins Unit 10 - Water System -Treated - Potable - Demin - Potable Water | B | 2019-04-18 | IBD | OL1-2G43-5020 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1050-PID-0031-5010 | P&Id - Olefins Unit 10 - Water System - Treated - Potable - Demin - Supporting Utilities Auxiliaries Treated Water | B | 2019-04-18 | IBD | OL1-2G43-5010 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1050-PID-0031-5010 | P&ID - Olefins Unit 10 - Water System Treated Potable Demin - Supporting Utilities Auxiliaries Treated Water | A | 2018-12-11 | IFR | OL1-2G43-5010 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00008 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1050-PID-0031-5001 | P&ID - Olefins Unit 10 - Water System Treated - Potable - Demin - Demineralized Water | A | 2019-01-23 | IFR | OL1-2G43-5001 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1050-PID-0031-5001 | P&Id - Olefins Unit 10 - Water System - Treated - Potable - Demin - Demineralized Water | B | 2019-04-18 | IBD | OL1-2G43-5001 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1051-PDS-1390-5124 | Piping Specialty Item- Datasheet Vent Silencer - PV-5158 Outlet 10-SP-51024 | B | 2019-09-06 | IFD | OL1-2P03-5124 | MP | 2019-09-09 | 036909C-JVD-TRN-02594 | 036909C-JVD-TRN-02594 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-MP-02594 |  | 2019-09-10 | 2
036909C-1051-PDS-1390-5130 | Piping Specialty Item - Datasheet - Vent Silencer - PSV-5150 A-B-C-D Outlet - 10-SP-51030 | 0 | 2019-09-06 | CAN | OL1-2P03-5130 | MP | 2019-09-09 | 036909C-JVD-TRN-02594 | 036909C-JVD-TRN-02594 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-MP-02594 |  | 2019-09-10 | 2
036909C-1051-PDS-1390-5123 | Piping Specialty Item- Datasheet Vent Silencer - PV-5155 Outlet 10-SP-51023 | B | 2019-09-06 | IFD | OL1-2P03-5123 | MP | 2019-09-09 | 036909C-JVD-TRN-02594 | 036909C-JVD-TRN-02594 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-MP-02594 |  | 2019-09-10 | 2
036909C-1051-PDS-1390-5122 | Piping Specialty Item- Datasheet Vent Silencer - PV-5147 Outlet 10-SP-51022 | B | 2019-09-06 | IFD | OL1-2P03-5122 | MP | 2019-09-09 | 036909C-JVD-TRN-02594 | 036909C-JVD-TRN-02594 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-MP-02594 |  | 2019-09-10 | 2
036909C-1051-PDS-1390-5121 | Piping Specialty Item - Datasheet - Vent Silencer -PV-5143 Outlet - 10-SP-51021 | 0 | 2019-09-06 | CAN | OL1-2P03-5121 | MP | 2019-09-09 | 036909C-JVD-TRN-02594 | 036909C-JVD-TRN-02594 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-MP-02594 |  | 2019-09-10 | 2
036909C-1051-PDS-1390-5126 | Piping Specialty Item - Datasheet - Vent Silencer - PSV-5134 A-H- Outlet - 10-SP-51026 | 0 | 2019-09-06 | CAN | OL1-2P06-5126 | MP | 2019-09-09 | 036909C-JVD-TRN-02594 | 036909C-JVD-TRN-02594 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-MP-02594 |  | 2019-09-10 | 2
036909C-1051-PDS-1390-5125 | Piping Specialty Item- Datasheet Vent Silencer - PV-5161 Outlet 10-SP-51025 | B | 2019-09-06 | IFD | OL1-2P03-5125 | MP | 2019-09-09 | 036909C-JVD-TRN-02594 | 036909C-JVD-TRN-02594 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-MP-02594 |  | 2019-09-10 | 2
036909C-1000-CN-1621-0001 | Electrical Cable Sizing Criteria | A | 2019-04-16 | IFR | OL1-2E10-0001 | EE | 2019-04-23 | 036909C-JVD-TRN-01438 | 036909C-JVD-TRN-01438, ROC-TPSK-CECO-T-00048 |  | 2019-05-08 | 2019-05-15 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-01438 |  | 2019-04-24 | 1
036909C-1039-PID-0031-3905 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Predistillation Inhibitor System | A | 2019-03-14 | IFR | OL1-2G43-3905 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-30 | CA2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1039-PID-0031-3905 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Predistillation Inhibitor System | B | 2019-05-20 | IBD | OL1-2G43-3905 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1039-PID-0031-3902 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Solvent Inhibitor Injection System | A | 2019-03-14 | IFR | OL1-2G43-3902 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-30 | CA2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1039-PID-0031-3902 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Solvent Inhibitor Injection System | B | 2019-05-20 | IBD | OL1-2G43-3902 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1039-PID-0031-3901 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - NMP Storage | A | 2019-03-14 | IFR | OL1-2G43-3901 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-30 | CA2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1031-PID-0031-3113 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drain System - Sheet 2 | B | 2019-05-20 | IBD | OL1-2G43-3113 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1031-PID-0031-3113 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drain System - Sheet 2 | A | 2019-03-14 | IFR | OL1-2G43-3113 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-30 | CA3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1031-PID-0031-3112 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drain System - Sheet 1 | A | 2019-03-14 | IFR | OL1-2G43-3112 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-30 | CA3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1031-PID-0031-3112 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drain System - Sheet 1 | B | 2019-05-20 | IBD | OL1-2G43-3112 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1031-PID-0031-3110 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Heater And Cooler | A | 2019-03-14 | IFR | OL1-2G43-3110 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-30 | CA2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1031-PID-0031-3110 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Heater And Cooler | B | 2019-05-20 | IBD | OL1-2G43-3110 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1031-PID-0031-3109 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Drum And Recycle Pumps | B | 2019-05-20 | IBD | OL1-2G43-3109 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1031-PID-0031-3109 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Drum And Recycle Pumps | A | 2019-03-14 | IFR | OL1-2G43-3109 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1031-PID-0031-3107 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drum | B | 2019-05-20 | IBD | OL1-2G43-3107 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1031-PID-0031-3107 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drum | A | 2019-03-14 | IFR | OL1-2G43-3107 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1031-PID-0031-3106 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Blow Down Drum | A | 2019-03-14 | IFR | OL1-2G43-3106 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1031-PID-0031-3108 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Flash Drum | A | 2019-03-14 | IFR | OL1-2G43-3108 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1031-PID-0031-3108 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Flash Drum | B | 2019-05-20 | IBD | OL1-2G43-3108 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1039-PID-0031-3903 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Product Inhibitor Injection System | B | 2019-05-20 | IBD | OL1-2G43-3903 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1039-PID-0031-3903 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Product Inhibitor Injection System | A | 2019-03-14 | IFR | OL1-2G43-3903 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-30 | CA2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1039-PID-0031-3904 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Anti-Foam Agent Injection System | A | 2019-03-14 | IFR | OL1-2G43-3904 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-30 | CA2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1039-PID-0031-3904 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Anti-Foam Agent Injection System | B | 2019-05-20 | IBD | OL1-2G43-3904 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1031-PID-0031-3102 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Water Washer And Condenser | A | 2019-03-14 | IFR | OL1-2G43-3102 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1031-PID-0031-3102 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Water Washer And Condenser | B | 2019-05-20 | IBD | OL1-2G43-3102 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1031-PID-0031-3105 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Ejector Seal Drum And Waste Water Pumps | B | 2019-05-20 | IBD | OL1-2G43-3105 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1031-PID-0031-3105 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Ejector Seal Drum And Waste Water Pumps | A | 2019-03-14 | IFR | OL1-2G43-3105 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1031-PID-0031-3104 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Water Washer Accumulator & Solvent Return Pumps | A | 2019-03-14 | IFR | OL1-2G43-3104 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1031-PID-0031-3104 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Water Washer Accumulator & Solvent Return Pumps | B | 2019-05-20 | IBD | OL1-2G43-3104 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1031-PID-0031-3103 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Regen Steam Ejector Package | A | 2019-03-14 | IFR | OL1-2G43-3103 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1031-PID-0031-3103 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Regen Steam Ejector Package | B | 2019-05-20 | IBD | OL1-2G43-3103 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1031-PID-0031-3101 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Solvent Regeneration | B | 2019-05-20 | IBD | OL1-2G43-3101 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1031-PID-0031-3101 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Solvent Regeneration | A | 2019-03-14 | IFR | OL1-2G43-3101 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1016-DW-0131-6601 | USC 132U Cracking Furnace Steel Partial Platform Plan at TOS EL 103350 107100 and 113000 | 0 | 2019-08-30 | IMP | OL1-2K32-6601 | CV | 2019-09-05 | 036909C-JVD-TRN-02577 | 036909C-JVD-TRN-02577 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02577 |  | 2019-09-10 | 3
036909C-1012-DW-0131-2603 | USC 132U Cracking Furnace Steel Platform Plan at TOS EL 113000 | 1 | 2019-08-30 | IMP | OL1-2K32-2603 | CV | 2019-09-05 | 036909C-JVD-TRN-02577 | 036909C-JVD-TRN-02577 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02577 |  | 2019-09-10 | 3
036909C-1012-DW-0131-2602 | USC 132U Cracking Furnace Steel Platform Plan at TOS EL 107100 | 1 | 2019-08-30 | IMP | OL1-2K32-2602 | CV | 2019-09-05 | 036909C-JVD-TRN-02577 | 036909C-JVD-TRN-02577 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02577 |  | 2019-09-10 | 3
036909C-1012-DW-0131-2542 | USC 132U Cracking Furnace Steel Sections and Details | 0 | 2019-08-30 | IMP | OL1-2K32-2542 | CV | 2019-09-05 | 036909C-JVD-TRN-02577 | 036909C-JVD-TRN-02577 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02577 |  | 2019-09-10 | 3
036909C-1011-DW-0117-1601 | USC 36M Recycle Furnace Steel Platform Plan at TOS EL 103360 | 1 | 2019-08-30 | IMP | OL1-2K32-1601 | CV | 2019-09-05 | 036909C-JVD-TRN-02577 | 036909C-JVD-TRN-02577 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02577 |  | 2019-09-10 | 3
036909C-1011-DW-0131-1542 | USC 36M Recycle Furnace Steel Sections and Details | 0 | 2019-08-30 | IMP | OL1-2K32-1542 | CV | 2019-09-05 | 036909C-JVD-TRN-02577 | 036909C-JVD-TRN-02577 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02577 |  | 2019-09-10 | 3
036909C-1011-DW-0117-1603 | USC 36M Recycle Furnace Steel Platform Plan at TOS El 110000 | 1 | 2019-08-30 | IMP | OL1-2K32-1603 | CV | 2019-09-05 | 036909C-JVD-TRN-02577 | 036909C-JVD-TRN-02577 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02577 |  | 2019-09-10 | 3
036909C-1011-DW-0117-1602 | USC 36M Recycle Furnace Steel Platform Plan at TOS El 107100 | 1 | 2019-08-30 | IMP | OL1-2K32-1602 | CV | 2019-09-05 | 036909C-JVD-TRN-02577 | 036909C-JVD-TRN-02577 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02577 |  | 2019-09-10 | 3
036909C-1026-PID-0021-2690 | P&ID - Olefins Unit 10 - Hot Fractionation - RAW C4S - PYGAS - OFF-SPEC PROPYLENE BATTERY LIMIT | A | 2019-08-07 | IDD1 | OL1-2G43-2690 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2630 | P&ID - Olefins Unit 10 - Hot Fractionation - C5-Pygas Surge Drum | D | 2019-08-07 | IDD1 | OL1-2G43-2630 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2629 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Bottoms Cooling | D | 2019-08-07 | IDD1 | OL1-2G43-2629 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2628 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Overhead Product-Reflux | C | 2019-08-07 | IDD1 | OL1-2G43-2628 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2627 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Overhead | C | 2019-08-07 | IDD1 | OL1-2G43-2627 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2625 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer | C | 2019-08-07 | IDD1 | OL1-2G43-2625 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2622 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Tower Bottoms | C | 2019-08-07 | IDD1 | OL1-2G43-2622 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2621 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Tower Reboilers | C | 2019-08-07 | IDD1 | OL1-2G43-2621 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2620 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Tower | C | 2019-08-07 | IDD1 | OL1-2G43-2620 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2616 | P&ID - Olefins Unit 10 - Hot Fractionation - Secondary Deethanizer Overhead | C | 2019-08-07 | IDD1 | OL1-2G43-2616 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2615 | P&ID - Olefins Unit 10 - Hot Fractionation - Secondary Deethanizer | C | 2019-08-07 | IDD1 | OL1-2G43-2615 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2610 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Recycle | C | 2019-08-07 | IDD1 | OL1-2G43-2610 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2608 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Aftercooling | C | 2019-08-07 | IDD1 | OL1-2G43-2608 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2605 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Reactor | C | 2019-08-07 | IDD1 | OL1-2G43-2605 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2604 | P&ID - Olefins Unit 10 - Hot Fractionation - Feed Section | C | 2019-08-07 | IDD1 | OL1-2G43-2604 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2603 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Arsine Guard Bed | C | 2019-08-07 | IDD1 | OL1-2G43-2603 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2602 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Guard Adsorbers - Sheet 2 | C | 2019-08-07 | IDD1 | OL1-2G43-2602 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1026-PID-0021-2601 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Guard Adsorbers - Sheet 1 | C | 2019-08-07 | IDD1 | OL1-2G43-2601 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2909 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Methanol Injection System | C | 2019-08-07 | IDD1 | OL1-2G43-2909 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2976 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - C2R Lube Oil Pump Turbine Details | C | 2019-08-07 | IDD1 | OL1-2G43-2976 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2975 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - C2R Compressor Auxiliaries Details - Sheet 2 | C | 2019-08-07 | IDD1 | OL1-2G43-2975 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2970 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - C2R Compressor Auxiliaries - Sheet 1 | C | 2019-08-07 | IDD1 | OL1-2G43-2970 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2965 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - C3R Compressor Lube Oil Pump Turbine Details | C | 2019-08-07 | IDD1 | OL1-2G43-2965 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2960 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - C3R Refrig Compressor Turbine Details - Sheet 2 | C | 2019-08-07 | IDD1 | OL1-2G43-2960 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2955 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - C3 Refrig Compressor Turbine Details - Sheet 1 | C | 2019-08-07 | IDD1 | OL1-2G43-2955 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2906 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - C4 Polymer Inhibitor Injection Package | C | 2019-08-07 | IDD1 | OL1-2G43-2906 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2905 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Polymerization Inhibitor Injection | C | 2019-08-07 | IDD1 | OL1-2G43-2905 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1030-PID-0021-3029 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Butadiene Product To B L | A | 2019-03-14 | IFR | OL1-2G43-3029 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3029 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Product To B L | B | 2019-05-20 | IBD | OL1-2G43-3029 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3028 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Butadiene Drying Tower And Reboiler | A | 2019-03-14 | IFR | OL1-2G43-3028 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3028 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Drying Tower And Reboiler | B | 2019-05-20 | IBD | OL1-2G43-3028 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3027 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Tower Overhead | B | 2019-05-20 | IBD | OL1-2G43-3027 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3027 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Butadiene Tower Overhead | A | 2019-03-14 | IFR | OL1-2G43-3027 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3026 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Tower Bottom Pump | B | 2019-05-20 | IBD | OL1-2G43-3026 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3026 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Butadiene Tower Bottom Pump | A | 2019-03-14 | IFR | OL1-2G43-3026 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3025 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Butadiene Tower Reboilers | A | 2019-03-14 | IFR | OL1-2G43-3025 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3025 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Tower Reboilers | B | 2019-05-20 | IBD | OL1-2G43-3025 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3024 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Tower | B | 2019-05-20 | IBD | OL1-2G43-3024 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3024 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Butadiene Tower | A | 2019-03-14 | IFR | OL1-2G43-3024 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3023 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Recycle Gas Compressor | B | 2019-05-20 | IBD | OL1-2G43-3023 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3023 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Recycle Gas Compressor | A | 2019-03-14 | IFR | OL1-2G43-3023 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3022 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - C4 Acetylene Pumps | A | 2019-03-14 | IFR | OL1-2G43-3022 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3022 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - C4 Acetylene Pumps | B | 2019-05-20 | IBD | OL1-2G43-3022 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3021 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Acetylene Condenser And Accumulator | B | 2019-05-20 | IBD | OL1-2G43-3021 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3021 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Acetylene Condenser And Accumulator | A | 2019-03-14 | IFR | OL1-2G43-3021 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3020 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Acetylene Wash Condenser | A | 2019-03-14 | IFR | OL1-2G43-3020 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3020 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Acetylene Wash Condenser | B | 2019-05-20 | IBD | OL1-2G43-3020 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3019 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - HC - Water Separator | A | 2019-03-14 | IFR | OL1-2G43-3019 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3019 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - HC - Water Separator | B | 2019-05-20 | IBD | OL1-2G43-3019 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3018 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Direct Cooler Pump & Degasser Bottom Pump | B | 2019-05-20 | IBD | OL1-2G43-3018 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3018 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Direct Cooler Pump & Degasser Bottom Pump | A | 2019-03-14 | IFR | OL1-2G43-3018 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3017 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Degassing Tower And Reboiler | B | 2019-05-20 | IBD | OL1-2G43-3017 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3017 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Degassing Tower And Reboiler | A | 2019-03-14 | IFR | OL1-2G43-3017 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3015 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Solvent Heat Exchanger-II And Solvent Heater | A | 2019-03-14 | IFR | OL1-2G43-3015 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3015 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Solvent Heat Exchanger-Ii And Solvent Heater | B | 2019-05-20 | IBD | OL1-2G43-3015 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3014 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Solvent Heat Exchangers - I | A | 2019-03-14 | IFR | OL1-2G43-3014 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3014 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Solvent Heat Exchangers - I | B | 2019-05-20 | IBD | OL1-2G43-3014 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3013 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - After Washer Overhead | B | 2019-05-20 | IBD | OL1-2G43-3013 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3013 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - After Washer Overhead | A | 2019-03-14 | IFR | OL1-2G43-3013 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3012 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - After Washer | B | 2019-05-20 | IBD | OL1-2G43-3012 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3012 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - After Washer | A | 2019-03-14 | IFR | OL1-2G43-3012 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3011 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Rectifier Pump And Degasser Feed Pump | A | 2019-03-14 | IFR | OL1-2G43-3011 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3011 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Rectifier Pump And Degasser Feed Pump | B | 2019-05-20 | IBD | OL1-2G43-3011 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3010 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Rectifier | B | 2019-05-20 | IBD | OL1-2G43-3010 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3010 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Rectifier | A | 2019-03-14 | IFR | OL1-2G43-3010 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1012-DW-0131-2603 | USC 132U Cracking Furnace Steel Platform Plan at TOS EL 103360 | 0 | 2019-04-30 | IFI | OL1-2K32-2603 | CV | 2019-05-06 | 036909C-JVD-TRN-01584 | 036909C-JVD-TRN-01584 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01584 |  | 2019-05-07 | 3
036909C-1012-DW-0131-2602 | USC 132U Cracking Furnace Steel Platform Plan at TOS EL 107100 | 0 | 2019-04-30 | IFI | OL1-2K32-2602 | CV | 2019-05-06 | 036909C-JVD-TRN-01584 | 036909C-JVD-TRN-01584 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01584 |  | 2019-05-06 | 3
036909C-1012-DW-0131-2500 | USC 36M Recycle and 132U Cracking Furnaces Steel General Notes and Abbreviations | A | 2019-03-29 | IFI | OL1-2K32-2500 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1011-DW-0117-1603 | USC 36M Recycle Furnace Steel Platform Plan at TOS EL 110000 | 0 | 2019-04-30 | IFI | OL1-2K32-1603 | CV | 2019-05-06 | 036909C-JVD-TRN-01584 | 036909C-JVD-TRN-01584 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01584 |  | 2019-05-07 | 3
036909C-1011-DW-0117-1602 | USC 36M Recycle Furnace Steel Platform Plan at TOS EL 107100 | 0 | 2019-04-30 | IFI | OL1-2K32-1602 | CV | 2019-05-06 | 036909C-JVD-TRN-01584 | 036909C-JVD-TRN-01584 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01584 |  | 2019-05-07 | 3
036909C-1011-DW-0117-1601 | USC 36M Recycle Furnace Steel Platform at TOS EL 103360 | 0 | 2019-04-30 | IFI | OL1-2K32-1601 | CV | 2019-05-06 | 036909C-JVD-TRN-01584 | 036909C-JVD-TRN-01584 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01584 |  | 2019-05-07 | 3
036909C-1000-NM-0003-1006 | Cooling Water Balance | A | 2018-09-14 | IFI | OL1-2G62-1006 | PE | 2018-09-17 | 036909C-JVD-TRN-00054 | 036909C-JVD-TRN-00054, ROC-TPSK-CECO-T-00012 | IFI | 2018-10-08 | 2018-10-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-00054 |  | 2018-09-18 | 3
036909C-1057-PID-0031-5704 | P&ID - FIRE WATER NETWORK (4/6) | B | 2019-05-08 | IFR | OL1-2L40-5704 | SE | 2019-05-09 | 036909C-JVD-TRN-01622 | 036909C-JVD-TRN-01622 | IFR | 2019-05-23 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-SE-01622 |  | 2019-05-09 | 2
036909C-103S-CN-3442-0001 | Electrical SUB-C & FAR-C – HVAC Thermal Calculation | C | 2019-08-22 | IDD | OL1-2H10-0002 | EE | 2019-08-23 | 036909C-JVD-TRN-02481 | 036909C-JVD-TRN-02481 | IFA | 2019-09-09 | 2019-09-03 | A4 - Not Approved, re-submit for approval | TPSK-LSPA1-T-EE-02481 |  | 2019-08-26 | 1
036909C-100S-DW-2052-0001-05 | Electrical SUB-E And FAR-E - Architectural Sections B - C- Ex Section D and Elevation 1 View | B | 2019-09-02 | IFR | OL1-2K30-0006 | CV | 2019-09-04 | 036909C-JVD-TRN-02567 | 036909C-JVD-TRN-02567 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-CV-02567 |  | 2019-09-05 | 1
036909C-100S-DW-2052-0001-06 | Electrical SUB-E And FAR-E - Architectural Elevations 1 And 2 -Ex Elevations View | B | 2019-09-02 | IFR | OL1-2K30-0007 | CV | 2019-09-04 | 036909C-JVD-TRN-02567 | 036909C-JVD-TRN-02567 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-CV-02567 |  | 2019-09-05 | 1
036909C-100S-DW-2052-0001-03 | Electrical SUB-E And FAR-E - Architectural Roff Floor Keyplan -Ex Roof Floor Plan | B | 2019-09-02 | IFR | OL1-2K30-0004 | CV | 2019-09-04 | 036909C-JVD-TRN-02567 | 036909C-JVD-TRN-02567 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-CV-02567 |  | 2019-09-05 | 1
036909C-100S-DW-2052-0001-04 | Electrical SUB-E And FAR-E - Architectural Sections A - D -Ex Sections View | B | 2019-09-02 | IFR | OL1-2K30-0005 | CV | 2019-09-04 | 036909C-JVD-TRN-02567 | 036909C-JVD-TRN-02567 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-CV-02567 |  | 2019-09-05 | 1
036909C-100S-DW-2052-0001-02 | Electrical SUB-E And FAR-E - Architectural First Floor Keyplan- Ex First Floor Plan | B | 2019-09-02 | IFR | OL1-2K30-0003 | CV | 2019-09-04 | 036909C-JVD-TRN-02567 | 036909C-JVD-TRN-02567 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-CV-02567 |  | 2019-09-05 | 1
036909C-100S-DW-2052-0001-013 | Electrical SUB-E And FAR-E - Architectural Roof Floor Plan Part 2 of 2 | A | 2019-09-02 | IFR | OL1-2K30-0014 | CV | 2019-09-04 | 036909C-JVD-TRN-02567 | 036909C-JVD-TRN-02567 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-CV-02567 |  | 2019-09-05 | 1
036909C-100S-DW-2052-0001-012 | Electrical SUB-E And FAR-E - Architectural Roof Floor Plan Part 1 of 2 | A | 2019-09-02 | IFR | OL1-2K30-0013 | CV | 2019-09-04 | 036909C-JVD-TRN-02567 | 036909C-JVD-TRN-02567 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-CV-02567 |  | 2019-09-05 | 1
036909C-100S-DW-2052-0001-010 | Electrical SUB-E And FAR-E - Architectural First Floor Plan Part 1 of 2 | A | 2019-09-02 | IFR | OL1-2K30-0011 | CV | 2019-09-04 | 036909C-JVD-TRN-02567 | 036909C-JVD-TRN-02567 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-CV-02567 |  | 2019-09-05 | 1
036909C-100S-DW-2052-0001-011 | Electrical SUB-E And FAR-E - Architectural First Floor Plan Part 2 of 2 | A | 2019-09-02 | IFR | OL1-2K30-0012 | CV | 2019-09-04 | 036909C-JVD-TRN-02567 | 036909C-JVD-TRN-02567 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-CV-02567 |  | 2019-09-05 | 1
036909C-100S-DW-2052-0001-01 | Electrical SUB-E And FAR-E - Architectural Ground Floor Keyplan- Ex Ground Floor Plan | B | 2019-09-02 | IFR | OL1-2K30-0002 | CV | 2019-09-04 | 036909C-JVD-TRN-02567 | 036909C-JVD-TRN-02567 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-CV-02567 |  | 2019-09-05 | 1
036909C-100S-DW-2052-0001-009 | Electrical SUB-E And FAR-E - Architectural Ground Floor Plan Part 2 of 2 | A | 2019-08-29 | IFR | OL1-2K30-0010 | CV | 2019-09-04 | 036909C-JVD-TRN-02567 | 036909C-JVD-TRN-02567 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-CV-02567 |  | 2019-09-05 | 1
036909C-100S-DW-2052-0001-008 | Electrical SUB-E And FAR-E - Architectural Ground Floor Plan Part 1 of 2 | A | 2019-09-02 | IFR | OL1-2K30-0009 | CV | 2019-09-04 | 036909C-JVD-TRN-02567 | 036909C-JVD-TRN-02567 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-CV-02567 |  | 2019-09-05 | 1
036909C-100S-DW-2052-0001-007 | Electrical SUB-E And FAR-E - Architectural Elevations 3 And 4 | A | 2019-09-02 | IFR | OL1-2K30-0008 | CV | 2019-09-04 | 036909C-JVD-TRN-02567 | 036909C-JVD-TRN-02567 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-CV-02567 |  | 2019-09-05 | 1
036909C-1000-SL-0000-102 | BD AND TD DOSSIER FOR PACKAGE A1 LSP | 0 | 2019-06-18 | IFR | OL1-2A19-0002 | CO | 2019-09-05 | 036909C-JVD-TRN-01902 | 036909C-JVD-TRN-01902 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CO-01902 | 102- is the first submission to MOIT for review and check | 2019-09-05 | 2
036909C-1000-SL-0000-101 | BD AND TD DOSSIER FOR PACKAGE A1 LSP | 0 | 2019-05-08 | IFI | OL1-2A19-0001 | CO | 2019-09-05 | 036909C-JVD-TRN-01546 | 036909C-JVD-TRN-01546 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CO-01546 | 101- is the first submission to verification consultant | 2019-09-05 | 3
036909C-100S-DW-2052-0001-06 | Electrical SUB-E And FAR-1 - Architectural Elevations | A | 2019-03-15 | IFR | OL1-2K30-0007 | CV | 2019-03-21 | 036909C-JVD-TRN-01122 | 036909C-JVD-TRN-01122, ROC-TPSK-CECO-T-00021 | IFA | 2019-04-05 | 2019-05-30 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01122 |  | 2019-03-22 | 1
036909C-100S-DW-2052-0001-05 | Electrical SUB-E And FAR-1 - Architectural Section D And Elevation 1 | A | 2019-03-15 | IFR | OL1-2K30-0006 | CV | 2019-03-21 | 036909C-JVD-TRN-01122 | 036909C-JVD-TRN-01122, ROC-TPSK-CECO-T-00021 | IFA | 2019-04-05 | 2019-05-30 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01122 |  | 2019-03-22 | 1
036909C-100S-DW-2052-0001-04 | Electrical SUB-E And FAR-1 - Architectural Sections | A | 2019-03-15 | IFR | OL1-2K30-0005 | CV | 2019-03-21 | 036909C-JVD-TRN-01122 | 036909C-JVD-TRN-01122, ROC-TPSK-CECO-T-00021 | IFA | 2019-04-05 | 2019-05-30 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01122 |  | 2019-03-22 | 1
036909C-100S-DW-2052-0001-03 | Electrical SUB-E And FAR-1 - Architectural First Floor Plan | A | 2019-03-15 | IFR | OL1-2K30-0004 | CV | 2019-03-21 | 036909C-JVD-TRN-01122 | 036909C-JVD-TRN-01122, ROC-TPSK-CECO-T-00021 | IFA | 2019-04-05 | 2019-05-30 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01122 |  | 2019-03-22 | 1
036909C-100S-DW-2052-0001-02 | Electrical SUB-E And FAR-1 - Architectural First Floor Plan | A | 2019-03-15 | IFR | OL1-2K30-0003 | CV | 2019-03-21 | 036909C-JVD-TRN-01122 | 036909C-JVD-TRN-01122, ROC-TPSK-CECO-T-00021 | IFA | 2019-04-05 | 2019-05-30 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01122 |  | 2019-03-22 | 1
036909C-100S-DW-2052-0001-01 | Electrical SUB-E And FAR-1 - Architectural Ground Floor Plan | A | 2019-03-15 | IFR | OL1-2K30-0002 | CV | 2019-03-21 | 036909C-JVD-TRN-01122 | 036909C-JVD-TRN-01122, ROC-TPSK-CECO-T-00021 | IFA | 2019-04-05 | 2019-05-30 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01122 |  | 2019-03-22 | 1
036909C-1000-PO-036909C004P9103947-47 | Vendor Acknowledgment of Purchase Order for Cold Box | 0 | 2019-06-22 | IFI | OL1-2C51-0216 | PL | 2019-08-22 | 036909C-JVD-TRN-02469 | 036909C-JVD-TRN-02469 | IFI |  | 2019-09-04 | R1-No comments | TPSK-LSPA1-T-PL-02469 |  | 2019-08-22 | 3
036909C-1012-PO-036909C004P9103769-69 | Vendor Acknowledgment of Purchase Order for Furnace ID Fans | 0 | 2019-04-10 | IFI | OL1-2C51-0210 | PL | 2019-08-21 | 036909C-JVD-TRN-02469 | 036909C-JVD-TRN-02469 | IFI |  | 2019-09-04 | R1-No comments | TPSK-LSPA1-T-PL-02469 |  | 2019-08-21 | 3
036909C-1012-PO-036909C004P9103761-61 | Vendor Acknowledgment of Purchase Order for Peep Doors | 0 | 2019-04-01 | IFI | OL1-2C51-0208 | PL | 2019-08-21 | 036909C-JVD-TRN-02469 | 036909C-JVD-TRN-02469 | IFI |  | 2019-09-04 | R1-No comments | TPSK-LSPA1-T-PL-02469 |  | 2019-08-21 | 3
036909C-1012-PO-036909C004P9103643-43 | Vendor Acknowledgment of Purchase Order for Furnace Burners | 0 | 2019-02-17 | IFI | OL1-2C51-0207 | PL | 2019-08-21 | 036909C-JVD-TRN-02469 | 036909C-JVD-TRN-02469 | IFI |  | 2019-09-04 | R1-No comments | TPSK-LSPA1-T-PL-02469 |  | 2019-08-21 | 3
036909C-1023-PDS-1390-2325 | Piping Specialty Item - Datasheet - Sight Glass - SGT-23001 | A | 2019-07-18 | IFR | OL1-2P03-2325 | MP | 2019-07-23 | 036909C-JVD-TRN-02254 | 036909C-JVD-TRN-02254 | IFR | 2019-08-07 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-MP-02254 |  | 2019-07-24 | 2
036909C-1039-CN-0014-3947 | PSV-3947 & PSV-3948 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3947 | PE | 2019-08-02 | 036909C-JVD-TRN-02337 | 036909C-JVD-TRN-02337 | IFR | 2019-08-17 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-02337 |  | 2019-08-05 | 2
036909C-1039-CN-0014-3945 | PSV-3945 & PSV-3946 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3945 | PE | 2019-08-02 | 036909C-JVD-TRN-02337 | 036909C-JVD-TRN-02337 | IFR | 2019-08-17 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-02337 |  | 2019-08-05 | 2
036909C-1039-CN-0014-3944 | PSV-3944 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3944 | PE | 2019-08-02 | 036909C-JVD-TRN-02337 | 036909C-JVD-TRN-02337 | IFR | 2019-08-17 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-02337 |  | 2019-08-05 | 2
036909C-1031-CN-0014-3169 | PSV-3169 Sizing Calculation | A | 2019-07-31 | IFR | OL1-2G23-3169 | PE | 2019-08-02 | 036909C-JVD-TRN-02337 | 036909C-JVD-TRN-02337 | IFR | 2019-08-17 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-02337 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3001 | PSV-3001 A-B Sizing Calculation | A | 2019-07-30 | IFR | OL1-2G23-3001 | PE | 2019-08-02 | 036909C-JVD-TRN-02337 | 036909C-JVD-TRN-02337 | IFR | 2019-08-17 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-02337 |  | 2019-08-05 | 2
036909C-1053-PDS-0300-5350 | Process Equipment Datasheet - 10-PK-5350 - Cooling Tower | C | 2019-03-21 | IFD | OL1-2G30-5350 | PE | 2019-03-25 | 036909C-JVD-TRN-01150 | 036909C-JVD-TRN-01150, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-09 | 2019-04-12 | Response to Clients Comments emailed Sept-4-2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01150 |  | 2019-03-26 | 2
036909C-1027-PDS-1390-2723 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - R-2760 ILK-27006 | A | 2019-08-31 | IFR | OL1-2P03-2723 | MP | 2019-09-03 | 036909C-JVD-TRN-02566 | 036909C-JVD-TRN-02566 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-MP-02566 |  | 2019-09-04 | 2
036909C-1026-PDS-1390-2620 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - R-2620 ILK-26010 | A | 2019-08-31 | IFR | OL1-2P03-2620 | MP | 2019-09-03 | 036909C-JVD-TRN-02566 | 036909C-JVD-TRN-02566 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-MP-02566 |  | 2019-09-04 | 2
036909C-1000-PP-852 | Site Hazard Identification Plan | A | 2019-08-23 | IFR | OL1-2S92-0008 | ES | 2019-09-03 | 036909C-JVD-TRN-02561 | 036909C-JVD-TRN-02561 | IFR | 2019-09-17 |  | Transmitted | TPSK-LSPA1-T-ES-02561 |  | 2019-09-04 | 2
036909C-100P-DW-1572-0003 | Instrument Main Cable Routing Main Pipe Rack | A | 2019-08-08 | IFR | OL1-2I34-0003 | IE | 2019-08-09 | 036909C-JVD-TRN-02407 | 036909C-JVD-TRN-02407 | IFA | 2019-08-26 | 2019-08-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02407 |  | 2019-08-14 | 1
036909C-103A-CN-1733-0020 | Calculation Note For Foundation Of 10-D-3180 | A | 2019-07-01 | IFR | OL1-2K13-0219 | CV | 2019-07-03 | 036909C-JVD-TRN-02064 | 036909C-JVD-TRN-02064 | IFR | 2019-07-17 | 2019-09-03 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02064 |  | 2019-07-03 | 1
036909C-1051-PID-0031-5134 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Furnace Blowdown System | B | 2019-04-24 | IBD | OL1-2G43-5134 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5134 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Furnace Blowdown System | A | 2019-01-23 | IFR | OL1-2G43-5134 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5132 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Low Pressure Steam Flash Drum | B | 2019-04-24 | IBD | OL1-2G43-5132 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5132 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Low Pressure Steam Flash Drum | A | 2019-01-23 | IFR | OL1-2G43-5132 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5128 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Polisher - Sheet 2 | B | 2019-04-24 | IBD | OL1-2G43-5128 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5128 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Polisher - Sheet 2 | A | 2019-01-23 | IFR | OL1-2G43-5128 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5127 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Polisher - Sheet 1 | B | 2019-04-24 | IBD | OL1-2G43-5127 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5127 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Polisher - Sheet 1 | A | 2019-01-23 | IFR | OL1-2G43-5127 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5120 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Carbon Filters | B | 2019-04-24 | IBD | OL1-2G43-5120 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5120 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Carbon Filters | A | 2019-01-23 | IFR | OL1-2G43-5120 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5118 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Suspect Condensate Cooling | B | 2019-04-24 | IBD | OL1-2G43-5118 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5118 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Suspect Condensate Cooling | A | 2019-01-23 | IFR | OL1-2G43-5118 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5111 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Boiler Feedwater Pumps | B | 2019-04-24 | IBD | OL1-2G43-5111 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5111 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Boiler Feedwater Pumps | A | 2019-01-23 | IFR | OL1-2G43-5111 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5110 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP Boiler Feedwater Pumps | B | 2019-04-24 | IBD | OL1-2G43-5110 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5110 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP Boiler Feedwater Pumps | A | 2019-01-23 | IFR | OL1-2G43-5110 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5105 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Deaerator | A | 2019-01-23 | IFR | OL1-2G43-5105 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5105 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Deaerator | B | 2019-04-24 | IBD | OL1-2G43-5105 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1059-PID-0031-5908 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Phosphate Injection System | B | 2019-04-18 | IBD | OL1-2G43-5908 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5908 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Phosphate Injection System | A | 2019-01-28 | IFR | OL1-2G43-5908 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1059-PID-0031-5907 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Oxygen Scavenger Injection System | B | 2019-04-18 | IBD | OL1-2G43-5907 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5907 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Oxygen Scavenger Injection System | A | 2019-01-28 | IFR | OL1-2G43-5907 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1055-PID-0031-5575 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - HP Flare Package | A | 2019-01-17 | IFR | OL1-2G43-5575 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5575 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - HP Flare Package | B | 2019-05-06 | IBD | OL1-2G43-5575 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5555 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Polyolefins Flare | B | 2019-05-06 | IBD | OL1-2G43-5555 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5555 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Polyolefins Flare | A | 2019-01-17 | IFR | OL1-2G43-5555 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5553 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - HP Flare Pilot Gas | A | 2019-01-17 | IFR | OL1-2G43-5553 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5553 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - HP Flare Pilot Gas | B | 2019-05-06 | IBD | OL1-2G43-5553 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5551 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - HP Flare KO Drum | A | 2019-01-17 | IFR | OL1-2G43-5551 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5551 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - HP Flare KO Drum | B | 2019-05-06 | IBD | OL1-2G43-5551 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5503 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Methanol Vaporizer | A | 2019-01-17 | IFR | OL1-2G43-5503 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5503 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Methanol Vaporizer | B | 2019-05-06 | IBD | OL1-2G43-5503 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5502 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Drum | B | 2019-05-06 | IBD | OL1-2G43-5502 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5502 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Drum | A | 2019-01-17 | IFR | OL1-2G43-5502 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5501 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Flare Drum | B | 2019-05-06 | IBD | OL1-2G43-5501 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5501 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Flare Drum | A | 2019-01-17 | IFR | OL1-2G43-5501 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1030-PID-0021-3016 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Direct Cooler And NMP Cooler | B | 2019-05-20 | IBD | OL1-2G43-3016 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3016 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Direct Cooler And NMP Cooler | A | 2019-03-14 | IFR | OL1-2G43-3016 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3009 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Main Washer Bottom Pump & Reflux Pump | A | 2019-03-14 | IFR | OL1-2G43-3009 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3009 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Main Washer Bottom Pump & Reflux Pump | B | 2019-05-20 | IBD | OL1-2G43-3009 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3008 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Main Washer Overhead | B | 2019-05-20 | IBD | OL1-2G43-3008 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3008 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Main Washer Overhead | A | 2019-03-14 | IFR | OL1-2G43-3008 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3007 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Main Washer & Solvent Cooler | B | 2019-05-20 | IBD | OL1-2G43-3007 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3007 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Main Washer & Solvent Cooler | A | 2019-03-14 | IFR | OL1-2G43-3007 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3006 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - C4 Vaporizers | B | 2019-05-20 | IBD | OL1-2G43-3006 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3006 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - C4 Vaporizers | A | 2019-03-14 | IFR | OL1-2G43-3006 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3005 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - C4 Vaporization Tower & Heavy End Disch. Pumps | A | 2019-03-14 | IFR | OL1-2G43-3005 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3005 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - C4 Vaporization Tower & Heavy End Disch. Pumps | B | 2019-05-20 | IBD | OL1-2G43-3005 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3004 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Predistillation Tower Overhead | B | 2019-05-20 | IBD | OL1-2G43-3004 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3004 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Predistillation Tower Overhead | A | 2019-03-14 | IFR | OL1-2G43-3004 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3003 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Predistillation Tower Trim Reboilers | A | 2019-03-14 | IFR | OL1-2G43-3003 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3003 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Predistillation Tower Trim Reboilers | B | 2019-05-20 | IBD | OL1-2G43-3003 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3002 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Predistillation Tower & Reboiler | A | 2019-03-14 | IFR | OL1-2G43-3002 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-1030-PID-0021-3002 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Predistillation Tower & Reboiler | B | 2019-05-20 | IBD | OL1-2G43-3002 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1031-PDS-1390-3121 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3165A/B ILK-31004 | A | 2019-08-08 | IFR | OL1-2P03-3121 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1031-PDS-1390-3107 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3164A/B ILK-31003 | A | 2019-08-08 | IFR | OL1-2P03-3107 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1031-PDS-1390-3106 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3162A/B ILK-31002 | A | 2019-08-08 | IFR | OL1-2P03-3106 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1031-PDS-1390-3101 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3163A/B ILK-31001 | A | 2019-08-08 | IFR | OL1-2P03-3101 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1030-PDS-1390-3040 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3042A/B ILK-30010 | A | 2019-08-08 | IFR | OL1-2P03-3040 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1030-PDS-1390-3039 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3031A/B ILK-30009 | A | 2019-08-08 | IFR | OL1-2P03-3039 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1030-PDS-1390-3038 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3039A/B ILK-30008 | A | 2019-08-08 | IFR | OL1-2P03-3038 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1030-PDS-1390-3037 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3033 A/B ILK-30007 | A | 2019-08-08 | IFR | OL1-2P03-3037 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1030-PDS-1390-3036 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3028 A/B ILK-30006 | A | 2019-08-08 | IFR | OL1-2P03-3036 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1030-PDS-1390-3025 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3026 A/B ILK-30005 | A | 2019-08-08 | IFR | OL1-2P03-3025 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1030-PDS-1390-3007 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3005 A/B ILK-30002 | A | 2019-08-08 | IFR | OL1-2P03-3007 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1030-PDS-1390-3006 | Piping Specialty Item – Data Sheet Double-Keyed Interlocked Locking Device - PSV-3001 A/B ILK-30001 | A | 2019-08-08 | IFR | OL1-2P03-3006 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1039-PDS-1390-3901 | Piping Specialty Item – T-Type Filter - P-3900 Suction SRT-39001 | A | 2019-08-08 | IFR | OL1-2P03-3901 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R1-No comments | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1031-PDS-1390-3104 | Piping Specialty Item – T-Type Filter - P-3126A/B Suction SRT-31003 | A | 2019-08-08 | IFR | OL1-2P03-3104 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R1-No comments | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1031-PDS-1390-3103 | Piping Specialty Item – T-Type Filter - P-3110A/B Suction SRT-31002 | A | 2019-08-08 | IFR | OL1-2P03-3103 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R1-No comments | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1059-PDS-1390-5913 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5103 A- Inlet - SRT-51030 | A | 2019-08-08 | IFR | OL1-2P03-5913 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-03 | R1-No comments | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-105F-DW-2052-0001-01 | Electrical SUB-F And FAR-FL - Architectural Plans And Schedules | B | 2019-08-29 | IFR | OL1-2K30-0050 | CV | 2019-09-02 | 036909C-JVD-TRN-02560 | 036909C-JVD-TRN-02560 | IFA | 2019-09-17 |  | Transmitted | TPSK-LSPA1-T-CV-02560 |  | 2019-09-03 | 1
036909C-105F-DW-2052-0001-02 | Electrical SUB-F and FAR-FL - Architectural Sections and Elevations | B | 2019-08-29 | IFR | OL1-2K30-0051 | ROC Civil | 2019-09-02 | 036909C-JVD-TRN-02560 | 036909C-JVD-TRN-02560 | IFA | 2019-09-17 |  | Transmitted | TPSK-LSPA1-T-CV-02560 |  | 2019-09-03 | 1
036909C-1031-TDS-0610-3111 | Mechanical Equipment Data Sheet - 10-E-3110 - Water Washer Condenser | B | 2019-08-26 | IFQ | OL1-2M03-3111 | ME | 2019-08-28 | 036909C-JVD-TRN-02520 | 036909C-JVD-TRN-02520 | IFR | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-ME-02520 |  | 2019-08-29 | 2
036909C-1031-TDS-0610-3111 | Mechanical Equipment Data Sheet - 10-E-3110 - Water Washer Condenser | A | 2019-04-29 | IFQ | OL1-2M03-3111 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-105F-DW-2052-0001-02 | Electrical SUB-F And FAR-F - Architectural Sections And Elevations | A | 2019-03-15 | IFR | OL1-2K30-0051 | CV | 2019-03-21 | 036909C-JVD-TRN-01122 | 036909C-JVD-TRN-01122, ROC-TPSK-CECO-T-00021 | IFA | 2019-04-05 | 2019-05-30 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01122 |  | 2019-03-22 | 1
036909C-105F-DW-2052-0001-01 | Electrical SUB-F And FAR-F - Architectural Plans And Schedules | A | 2019-03-15 | IFR | OL1-2K30-0050 | CV | 2019-03-21 | 036909C-JVD-TRN-01122 | 036909C-JVD-TRN-01122, ROC-TPSK-CECO-T-00021 | IFA | 2019-04-05 | 2019-05-30 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01122 |  | 2019-03-22 | 1
036909C-1030-PID-0021-3001 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Predistillation Feed Drum & Feed Pumps | B | 2019-05-20 | IBD | OL1-2G43-3001 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1030-PID-0021-3001 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Predistillation Feed Drum & Feed Pumps | A | 2019-03-14 | IFR | OL1-2G43-3001 | PE | 2019-03-14 | 036909C-JVD-TRN-01067 | 036909C-JVD-TRN-01067, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01067 |  | 2019-03-15 | 2
036909C-102A-CN-1833-0001 | Calculation Note For Steel Structure Of 10-T-2040 | A | 2019-06-24 | IFR | OL1-2K15-0065 | CV | 2019-06-28 | 036909C-JVD-TRN-02030 | 036909C-JVD-TRN-02030 | IFA | 2019-07-15 | 2019-08-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02030 |  | 2019-07-01 | 1
036909C-102D-CN-1733-0018 | Calculation Note For Foundation Of 10-D-2880 | A | 2019-06-26 | IFR | OL1-2K13-0106 | CV | 2019-06-28 | 036909C-JVD-TRN-02030 | 036909C-JVD-TRN-02030 | IFA | 2019-07-15 | 2019-08-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02030 |  | 2019-07-01 | 1
036909C-1059-PID-0031-5991 | P&ID- Olefins Unit 10- Supporting Utilities Auxiliaries- Treated Water Meter | A | 2019-08-26 | IDD1 | OL1-2G43-5991 | PE | 2019-08-29 | 036909C-JVD-TRN-02542 | 036909C-JVD-TRN-02542 | IFR | 2019-09-13 |  | Transmitted | TPSK-LSPA1-T-PE-02542 |  | 2019-08-30 | 2
036909C-1059-PID-0031-5990 | P&ID- Olefins Unit 10- Supporting Utilities Auxiliaries- HP Propane and Hydrogen Meters | A | 2019-08-26 | IDD1 | OL1-2G43-5990 | PE | 2019-08-29 | 036909C-JVD-TRN-02542 | 036909C-JVD-TRN-02542 | IFR | 2019-09-13 |  | Transmitted | TPSK-LSPA1-T-PE-02542 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5330 | P&Id - Olefins Unit 10 - Cooling Water - Olefins CW Pump Turbine Sheet 1 | A | 2019-08-26 | IDD1 | OL1-2G43-5330 | PE | 2019-08-29 | 036909C-JVD-TRN-02542 | 036909C-JVD-TRN-02542 | IFR | 2019-09-13 |  | Transmitted | TPSK-LSPA1-T-PE-02542 |  | 2019-08-30 | 2
036909C-102A-DW-1743-0027-001 | Foundation For 10-F-2026-A-B | A | 2019-08-28 | IFR | OL1-2K31-0034 | CV | 2019-08-29 | 036909C-JVD-TRN-02532 | 036909C-JVD-TRN-02532 | IFA | 2019-09-13 |  | Transmitted | TPSK-LSPA1-T-CV-02532 |  | 2019-08-30 | 1
036909C-102A-CN-1733-0037 | Calculation Note For Foundation Of 10-F-2137-A-B | A | 2019-08-27 | IFR | OL1-2K13-4590 | CV | 2019-08-29 | 036909C-JVD-TRN-02539 | 036909C-JVD-TRN-02539 | IFA | 2019-09-13 |  | Transmitted | TPSK-LSPA1-T-CV-02539 |  | 2019-08-30 | 1
036909C-102A-CN-1733-0022 | Calculation Note For Foundation Of 10-F-2026-A-B | A | 2019-08-27 | IFR | OL1-2K13-0029 | CV | 2019-08-29 | 036909C-JVD-TRN-02533 | 036909C-JVD-TRN-02533 | IFA | 2019-09-13 |  | Transmitted | TPSK-LSPA1-T-CV-02533 |  | 2019-08-30 | 1
036909C-1000-PP-260 | 3D Modeling | A | 2018-12-04 | IFR | OL1-2R07-0024 | ME | 2018-12-10 | 036909C-JVD-TRN-00452 | 036909C-JVD-TRN-00452 | IFR | 2018-12-24 | 2019-01-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00452 |  | 2018-12-10 | 2
036909C-1012-MS-6800-0001 | Special Technical Specification For Furnace Island Erection | A | 2019-07-22 | IFQ | OL1-2M92-0002 | ME | 2019-07-23 | 036909C-JVD-TRN-02247 | 036909C-JVD-TRN-02247 | IFR | 2019-08-07 | 2019-08-23 | R1-No comments | TPSK-LSPA1-T-ME-02247 |  | 2019-07-24 | 2
036909C-1012-EL-001 | Item Index Furnace Island | E | 2019-08-10 | IDD1 | OL1-2M91-0002 | ME | 2019-08-12 | 036909C-JVD-TRN-02411 | 036909C-JVD-TRN-02411 | IFR | 2019-08-27 | 2019-08-23 | R1-No comments | TPSK-LSPA1-T-ME-02411 |  | 2019-08-14 | 2
036909C-105U-DW-0051-0001 | Detail Plot Plan - Zone 5U - Utilities | C | 2019-07-16 | IBD | OL1-2P06-0016 | MP | 2019-07-22 | 036909C-JVD-TRN-02219 | 036909C-JVD-TRN-02219 | IFR | 2019-08-06 | 2019-08-22 | R2-Comments as noted | TPSK-LSPA1-T-MP-02219 |  | 2019-07-23 | 2
036909C-1000-PP-261 | Requirements For Eqipment Supplier 3D Model | 0 | 2018-09-27 | IMP | OL1-2R07-0025 | ME | 2018-09-28 | 036909C-JVD-TRN-00108 | 036909C-JVD-TRN-00108 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00108 |  | 2018-09-28 | 3
036909C-1000-JSS-0910-0001 | ME-010 Centrifugal Pump | 0 | 2019-01-07 | IMP | OL1-2R03-0010 | ME | 2019-01-22 | 036909C-JVD-TRN-00693 | 036909C-JVD-TRN-00693, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 | 2019-02-14 | R1-No comments | TPSK-LSPA1-T-ME-00693 |  | 2019-01-22 | 2
036909C-1000-JSD-6000-0003 | Noise Insulation | A | 2019-04-19 | IFR | OL1-2L10-0003 | SE | 2019-04-24 | 036909C-JVD-TRN-01461 | 036909C-JVD-TRN-01461 | IFR | 2019-05-09 | 2019-06-25 | R2-Comments as noted | TPSK-LSPA1-T-SE-01461 |  | 2019-04-25 | 2
036909C-1000-JSS-0910-0002 | ME-050 Centrifugal Pump - Non API | 0 | 2019-01-07 | IMP | OL1-2R03-0500 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 | 2019-04-25 | R1-No comments | TPSK-LSPA1-T-ME-00668 |  | 2019-01-23 | 2
036909C-1000-JSD-6000-0001 | Noise Control | A | 2018-12-05 | IFR | OL1-2L10-0001 | SE | 2018-12-11 | 036909C-JVD-TRN-00472 | 036909C-JVD-TRN-00472 | IFR | 2018-12-27 | 2019-06-07 | R2-Comments as noted | TPSK-LSPA1-T-SE-00472 |  | 2018-12-11 | 2
036909C-1000-JSD-1600-0009 | Document Template | 0 | 2018-12-03 | IMP | OL1-2R05-0036 | EE | 2018-12-05 | 036909C-JVD-TRN-00424 | 036909C-JVD-TRN-00424 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00424 |  | 2018-12-05 | 3
036909C-1000-JSD-0000-03 | JSD for PID Preparation | 0 | 2019-03-01 | IMP | OL1-2G01-0001 | PE | 2019-03-01 | 036909C-JVD-TRN-00965 | 036909C-JVD-TRN-00965, ROC-TPSK-CECO-T-00012 | IFR | 2019-03-18 | 2019-04-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00965 |  | 2019-03-04 | 2
036909C-1054-PID-0031-5412 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Instrument Air Distribution - Sheet 2 | A | 2019-01-28 | IFR | OL1-2G43-5412 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758 |  | 2019-01-29 | 2
036909C-1054-PID-0031-5412 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Instrument Air Distribution - Sheet 2 | B | 2019-04-24 | IBD | OL1-2G43-5412 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1054-PID-0031-5411 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Instrument Air Distribution - Sheet 1 | A | 2019-01-28 | IFR | OL1-2G43-5411 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758 |  | 2019-01-29 | 2
036909C-1054-PID-0031-5411 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Instrument Air Distribution - Sheet 1 | B | 2019-04-24 | IBD | OL1-2G43-5411 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1054-PID-0031-5410 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Instrument Air Receiver | A | 2019-01-28 | IFR | OL1-2G43-5410 | PE | 2019-01-29 | 036909C-JVD-TRN-00758 | 036909C-JVD-TRN-00758, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-12 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00758 |  | 2019-01-29 | 2
036909C-1054-PID-0031-5410 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Instrument Air Receiver | B | 2019-04-24 | IBD | OL1-2G43-5410 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1053-PID-0031-5352 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Corrosion Inhibitor Injection | A | 2018-12-11 | IFR | OL1-2G43-5352 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5352 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Corrosion Inhibitor Injection | B | 2019-04-18 | IBD | OL1-2G43-5352 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5351 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Chemical Injection | B | 2019-04-18 | IBD | OL1-2G43-5351 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5351 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Chemical Injection | A | 2018-12-11 | IFR | OL1-2G43-5351 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5326 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 7 | B | 2019-04-18 | IBD | OL1-2G43-5326 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5326 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 07 | A | 2018-12-11 | IFR | OL1-2G43-5326 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5324 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 5 | B | 2019-04-18 | IBD | OL1-2G43-5324 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5324 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 05 | A | 2018-12-11 | IFR | OL1-2G43-5324 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5322 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 3 | B | 2019-04-18 | IBD | OL1-2G43-5322 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5322 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 03 | A | 2018-12-11 | IFR | OL1-2G43-5322 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5320 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 01 | A | 2018-12-11 | IFR | OL1-2G43-5320 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5320 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 1 | B | 2019-04-18 | IBD | OL1-2G43-5320 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5317 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Filter Backwash | B | 2019-04-18 | IBD | OL1-2G43-5317 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5317 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Filter Backwash | A | 2018-12-11 | IFR | OL1-2G43-5317 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5315 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Side Stream Filter Package | A | 2018-12-11 | IFR | OL1-2G43-5315 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5315 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Side Stream Filter Package | B | 2019-04-18 | IBD | OL1-2G43-5315 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5311 | P&ID - Olefins Unit 10 - Cooling Water - Ctu Cooling Water Supply | A | 2018-12-11 | IFR | OL1-2G43-5311 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5311 | P&Id - Olefins Unit 10 - Cooling Water - CTU Cooling Water Supply | B | 2019-04-18 | IBD | OL1-2G43-5311 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5310 | P&Id - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Suppy | B | 2019-04-18 | IBD | OL1-2G43-5310 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5310 | P&ID - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply | A | 2018-12-11 | IFR | OL1-2G43-5310 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5307 | P&ID - Olefins Unit 10 - Cooling Water - CTU Cooling Water Supply Pumps | A | 2018-12-11 | IFR | OL1-2G43-5307 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5307 | P&Id - Olefins Unit 10 - Cooling Water - CTU Cooling Water Supply Pumps | B | 2019-04-18 | IBD | OL1-2G43-5307 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5306 | P&Id - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 2 | B | 2019-04-18 | IBD | OL1-2G43-5306 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5306 | P&ID - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 2 | A | 2018-12-11 | IFR | OL1-2G43-5306 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5305 | P&Id - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 1 | B | 2019-04-18 | IBD | OL1-2G43-5305 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5305 | P&ID - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 1 | A | 2018-12-11 | IFR | OL1-2G43-5305 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5303 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Tower - Sheet 3 | B | 2019-04-18 | IBD | OL1-2G43-5303 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5303 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 3 | A | 2018-12-11 | IFR | OL1-2G43-5303 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5302 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 2 | A | 2018-12-11 | IFR | OL1-2G43-5302 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1053-PID-0031-5302 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Tower - Sheet 2 | B | 2019-04-18 | IBD | OL1-2G43-5302 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5301 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Tower - Sheet 1 | B | 2019-04-18 | IBD | OL1-2G43-5301 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1053-PID-0031-5301 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 1 | A | 2018-12-11 | IFR | OL1-2G43-5301 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-105U-CN-1733-0001 | Calculation Note For Foundation Of 10-D-5500 | A | 2019-08-27 | IFR | OL1-2K13-0248 | CV | 2019-08-29 | 036909C-JVD-TRN-02497 | 036909C-JVD-TRN-02497 | IFA | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-CV-02497 |  | 2019-08-29 | 1
036909C-1030-TDS-0610-3095 | Mechanical Equipment Data Sheet - 10-E-3095 - Butadiene Drying Tower Reboiler | B | 2019-08-26 | IFQ | OL1-2M03-3095 | ME | 2019-08-28 | 036909C-JVD-TRN-02520 | 036909C-JVD-TRN-02520 | IFR | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-ME-02520 |  | 2019-08-29 | 2
036909C-1031-TDS-0610-3150 | Mechanical Equipment Data Sheet - 10-E-3150 - BDU Condensate Heater | B | 2019-08-26 | IFQ | OL1-2M03-3150 | ME | 2019-08-28 | 036909C-JVD-TRN-02520 | 036909C-JVD-TRN-02520 | IFR | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-ME-02520 |  | 2019-08-29 | 2
036909C-102A-DW-1743-0026-001 | Foundation For 10-F-2008-A-B-C | A | 2019-08-28 | IFR | OL1-2K31-0033 | CV | 2019-08-28 | 036909C-JVD-TRN-02519 | 036909C-JVD-TRN-02519 | IFA | 2019-09-12 |  | Transmitted |  |  | 2019-08-28 | 1
036909C-1025-PID-0021-2563 | P&ID- Olefins Unit 10- Cold Fractionation- Residue Gas Expander-Compressor | A | 2019-08-26 | IDD1 | OL1-2G43-2563 | PE | 2019-08-28 | 036909C-JVD-TRN-02516 | 036909C-JVD-TRN-02516 | IFR | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-PE-02516 |  | 2019-08-29 | 2
036909C-102A-CN-1733-0021 | Calculation Note For Foundation Of 10-F-2008-A-B-C | A | 2019-08-27 | IFR | OL1-2K13-0028 | CV | 2019-08-28 | 036909C-JVD-TRN-02518 | 036909C-JVD-TRN-02518 | IFA | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-CV-02518 |  | 2019-08-29 | 1
036909C-102A-CN-1733-0019 | Calculation Note For Foundation Of 10-F-2105-A-B | A | 2019-08-27 | IFR | OL1-2K13-0026 | CV | 2019-08-28 | 036909C-JVD-TRN-02521 | 036909C-JVD-TRN-02521 | IFA | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-CV-02521 |  | 2019-08-29 | 1
036909C-102A-DW-1743-0024-001 | Foundation For 10-F-2105-A-B | A | 2019-08-28 | IFR | OL1-2K31-0031 | CV | 2019-08-28 | 036909C-JVD-TRN-02522 | 036909C-JVD-TRN-02522 | IFA | 2019-09-12 |  | Transmitted |  |  | 2019-08-28 | 1
036909C-102A-CN-1733-0025 | Calculation Note For Foundation Of 10-F-2048-A-B | A | 2019-08-27 | IFR | OL1-2K13-0087 | CV | 2019-08-28 | 036909C-JVD-TRN-02518 | 036909C-JVD-TRN-02518 | IFA | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-CV-02518 |  | 2019-08-29 | 1
036909C-102A-DW-1743-0030-001 | Foundation For 10-F-2048-A-B | A | 2019-08-28 | IFR | OL1-2K31-0093 | CV | 2019-08-28 | 036909C-JVD-TRN-02519 | 036909C-JVD-TRN-02519 | IFA | 2019-09-12 |  | Transmitted |  |  | 2019-08-28 | 1
036909C-1000-JSD-6000-0003 | Noise Insulation | 0 | 2019-08-26 | IMP | OL1-2L10-0003 | SE | 2019-08-28 | 036909C-JVD-TRN-02523 | 036909C-JVD-TRN-02523 | IFR | 2019-08-28 |  | Transmitted | TPSK-LSPA1-T-SE-02523 |  | 2019-08-29 | 2
036909C-1025-PID-0021-2561 | P&ID- Olefins Unit 10- Cold Fractionation- Seal Gas Expander | A | 2019-08-26 | IDD1 | OL1-2G43-2561 | PE | 2019-08-28 | 036909C-JVD-TRN-02516 | 036909C-JVD-TRN-02516 | IFR | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-PE-02516 |  | 2019-08-29 | 2
036909C-1025-PID-0021-2562 | P&ID- Olefins Unit 10- Cold Fractionation- Residue Gas Expander-Compressor | A | 2019-08-26 | IDD1 | OL1-2G43-2562 | PE | 2019-08-28 | 036909C-JVD-TRN-02516 | 036909C-JVD-TRN-02516 | IFR | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-PE-02516 |  | 2019-08-29 | 2
036909C-1023-PDS-0900-2325 | Process Equipment Datasheet - 10-P-2300 A-B - 10 Percent Caustic Makeup Pump | B | 2019-01-29 | IFD | OL1-2G30-2325 | PE | 2019-01-29 | 036909C-JVD-TRN-00759 | 036909C-JVD-TRN-00759 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00759 |  | 2019-01-29 | 2
036909C-1059-SP-0910-5903 | Mechanical Equipment Datasheet - Sulfuric Acid Distribution Pumps | B | 2019-05-20 | IFQ | OL1-2M03-5903 | ME | 2019-05-21 | 036909C-JVD-TRN-01710 | 036909C-JVD-TRN-01710 | IFR | 2019-06-05 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01710 |  | 2019-05-23 | 2
036909C-1000-SL-0000-04 | Subvendor list for Pumps | 0 | 2018-11-16 | IMP | OL1-2C01-0003 | PL | 2018-11-19 | 036909C-JVD-TRN-00333 | 036909C-JVD-TRN-00333 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00333 |  | 2018-11-19 | 3
036909C-100P-DW-1624-0001 | Electrical Cable Routing Cross Sections - Zone-OP | A | 2019-07-25 | IFR | OL1-2E34-0002 | EE | 2019-07-29 | 036909C-JVD-TRN-02276 | 036909C-JVD-TRN-02276 | IFR | 2019-08-13 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-EE-02276 |  | 2019-07-30 | 2
036909C-100P-DW-1622-0201 | Power Layout - Zone-0P | A | 2019-07-25 | IFR | OL1-2E32-0002 | EE | 2019-07-29 | 036909C-JVD-TRN-02275 | 036909C-JVD-TRN-02275 | IFA | 2019-08-13 | 2019-08-26 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02275 |  | 2019-07-30 | 1
036909C-103S-DW-3432-0001 | Electrical Sub-C- And Far-2 - HVAC Layout | B | 2019-07-30 | IDD | OL1-2H21-0005 | EE | 2019-08-07 | 036909C-JVD-TRN-02370 | 036909C-JVD-TRN-02370 | IFA | 2019-08-22 | 2019-08-19 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02370 |  | 2019-08-08 | 1
036909C-1059-PID-0031-5930 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - VLP BFW Lube Oil Pump Turbine Details | A | 2019-01-28 | IFR | OL1-2G43-5930 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1059-PID-0031-5930 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - VLP BFW Lube Oil Pump Turbine Details | B | 2019-04-18 | IBD | OL1-2G43-5930 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5929 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - VLP BFW Pump Turbine Details | A | 2019-01-28 | IFR | OL1-2G43-5929 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1059-PID-0031-5929 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - VLP BFW Pump Turbine Details | B | 2019-04-18 | IBD | OL1-2G43-5929 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5928 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Lube Oil Pump Turbine B Details | B | 2019-04-18 | IBD | OL1-2G43-5928 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5928 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Lube Oil Pump Turbine B Details | A | 2019-01-28 | IFR | OL1-2G43-5928 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1059-PID-0031-5927 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Lube Oil Pump Turbine A Details | A | 2019-01-28 | IFR | OL1-2G43-5927 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1059-PID-0031-5927 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Lube Oil Pump Turbine A Details | B | 2019-04-18 | IBD | OL1-2G43-5927 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5925 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Pump Turbine Details | B | 2019-04-18 | IBD | OL1-2G43-5925 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5925 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Pump Turbine Details | A | 2019-01-28 | IFR | OL1-2G43-5925 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1059-PID-0031-5922 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - CTU Cooling Water Pump Turbine Details | B | 2019-04-18 | IBD | OL1-2G43-5922 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5922 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Ctu Cooling Water Pump Turbine Details | A | 2019-01-28 | IFR | OL1-2G43-5922 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1059-PID-0031-5921 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Olefins CW Pump Turbine Details - Sheet 2 | B | 2019-04-18 | IBD | OL1-2G43-5921 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5921 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Olefins CW Pump Turbine Details - Sheet 2 | A | 2019-01-28 | IFR | OL1-2G43-5921 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1059-PID-0031-5920 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Olefins CW Pump Turbine Details - Sheet 1 | A | 2019-01-28 | IFR | OL1-2G43-5920 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1059-PID-0031-5920 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Olefins CW Pump Turbine Details - Sheet 1 | B | 2019-04-18 | IBD | OL1-2G43-5920 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5915 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Condensate Pump Turbine Details | B | 2019-04-18 | IBD | OL1-2G43-5915 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1059-PID-0031-5915 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Condensate Pump Turbine Details | A | 2019-01-28 | IFR | OL1-2G43-5915 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1056-PID-0031-5642 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 3 | B | 2019-04-26 | IBD | OL1-2G43-5642 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5642 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 3 | A | 2019-02-13 | IFR | OL1-2G43-5642 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1030-TDS-0610-3085 | Mechanical Equipment Data Sheet - 10-E-3085 - Butadiene Tower Reboiler | A | 2019-05-01 | IFQ | OL1-2M03-3085 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1031-TDS-0610-3160 | Mechanical Equipment Data Sheet - 10-E-3160 - BDU Condensate Cooler | A | 2019-05-02 | IFQ | OL1-2M03-3160 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1031-TDS-0610-3150 | Mechanical Equipment Data Sheet - 10-E-3150 - BDU Condensate Heater | A | 2019-04-29 | IFQ | OL1-2M03-3150 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3098 | Mechanical Equipment Data Sheet - 10-E-3098 - Butadiene Product Subcooler | A | 2019-05-01 | IFQ | OL1-2M03-3098 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3095 | Mechanical Equipment Data Sheet - 10-E-3095 - Butadiene Drying Tower Reboiler | A | 2019-04-29 | IFQ | OL1-2M03-3095 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1000-DW-1920-0002 | Hazardous Area Classification - Details | A | 2019-03-07 | IFA | OL1-2L42-0020 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015, ROC-TPSK-CECO-T-00013_1 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-1027-PDS-1390-2729 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2771 A-B - ILK-27008 | A | 2019-08-01 | IFR | OL1-2P03-2729 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1039-CN-0014-3943 | PSV-3943 Sizing Calculation | A | 2019-07-30 | IFR | OL1-2G23-3943 | PE | 2019-08-02 | 036909C-JVD-TRN-02337 | 036909C-JVD-TRN-02337 | IFR | 2019-08-17 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-02337 |  | 2019-08-05 | 2
036909C-1031-CN-0014-3166 | PSV-3166 Sizing Calculation | A | 2019-07-31 | IFR | OL1-2G23-3166 | PE | 2019-08-02 | 036909C-JVD-TRN-02337 | 036909C-JVD-TRN-02337 | IFR | 2019-08-17 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-02337 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3031 | PSV-3031 A-B Sizing Calculation | A | 2019-07-31 | IFR | OL1-2G23-3031 | PE | 2019-08-02 | 036909C-JVD-TRN-02337 | 036909C-JVD-TRN-02337 | IFR | 2019-08-17 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-02337 |  | 2019-08-05 | 2
036909C-1030-TDS-0610-3015 | Mechanical Equipment Data Sheet - 10-E-3015 - C4 Trim Vaporizer | B | 2019-08-26 | IFQ | OL1-2M03-3015 | ME | 2019-08-27 | 036909C-JVD-TRN-02510 | 036909C-JVD-TRN-02510 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02510 |  | 2019-08-28 | 2
036909C-1030-TDS-0610-3005 | Mechanical Equipment Data Sheet - 10-E-3005- Predistillation Tower Reboiler | B | 2019-08-26 | IFQ | OL1-2M03-3005 | ME | 2019-08-27 | 036909C-JVD-TRN-02510 | 036909C-JVD-TRN-02510 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02510 |  | 2019-08-28 | 2
036909C-103A-CN-1733-0031 | Calculation Note For Foundation Of 10-E-3045 A/B/C/D | A | 2019-08-16 | IFR | OL1-2K13-0230 | CV | 2019-08-27 | 036909C-JVD-TRN-02494 | 036909C-JVD-TRN-02494 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02494 |  | 2019-08-27 | 1
036909C-1030-TDS-0610-3014 | Mechanical Equipment Data Sheet - 10-E-3014 - C4 Solvent Vaporizer | B | 2019-08-26 | IFQ | OL1-2M03-3014 | ME | 2019-08-27 | 036909C-JVD-TRN-02510 | 036909C-JVD-TRN-02510 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02510 |  | 2019-08-28 | 2
036909C-1030-TDS-0610-3084 | Mechanical Equipment Data Sheet - 10-E-3084 - Butadiene Tower Trim Reboiler | A | 2019-05-01 | IFQ | OL1-2M03-3084 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LPSA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3063 | Mechanical Equipment Data Sheet - 10-E-3060 - C4 Acetylene Washer Condenser | A | 2019-04-25 | IFQ | OL1-2M03-3063 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3044 | Mechanical Equipment Data Sheet - 10-E-3044 - Solvent Heater | A | 2019-04-25 | IFQ | OL1-2M03-3044 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3021 | Mechanical Equipment Data Sheet - 10-E-3020 - Main Washer Condenser | A | 2019-04-24 | IFQ | OL1-2M03-3021 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3015 | Mechanical Equipment Data Sheet - 10-E-3015 - C4 Trim Vaporizer | A | 2019-04-23 | IFQ | OL1-2M03-3015 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3014 | Mechanical Equipment Data Sheet - 10-E-3014 - C4 Trim Vaporizer | A | 2019-04-26 | IFQ | OL1-2M03-3014 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3005 | Mechanical Equipment Data Sheet - 10-E-3005- Predistillation Tower Reboiler | A | 2019-04-22 | IFQ | OL1-2M03-3005 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3081 | Mechanical Equipment Data Sheet - 10-E-3080 - Butadiene Tower Condenser | A | 2019-04-26 | IFQ | OL1-2M03-3081 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3071 | Mechanical Equipment Data Sheet - 10-E-3070 - Water - NMP Cooler | A | 2019-04-26 | IFQ | OL1-2M03-3071 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3062 | Mechanical Equipment Data Sheet - 10-E-3062 - C4 Acetylene Condenser | A | 2019-04-29 | IFQ | OL1-2M03-3062 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3055 | Mechanical Equipment Data Sheet - 10-E-3055 - Degasser Reboiler | A | 2019-04-26 | IFQ | OL1-2M03-3055 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3045 | Mechanical Equipment Data Sheet - 10-E-3045 A-D- Solvent Heat Exchanger | A | 2019-04-24 | IFQ | OL1-2M03-3045 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3031 | Mechanical Equipment Data Sheet - 10-E-3030 -After Washer Condenser | A | 2019-04-25 | IFQ | OL1-2M03-3031 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3018 | Mechanical Equipment Data Sheet - 10-E-3018 - Solvent Cooler | A | 2019-04-26 | IFQ | OL1-2M03-3018 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3004 | Mechanical Equipment Data Sheet - 10-E-3004 - Predistillation Tower Trim Reboiler | A | 2019-04-18 | IFQ | OL1-2M03-3004 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1030-TDS-0610-3001 | Mechanical Equipment Data Sheet - 10-E-3000 - Predistillation Tower Condenser | A | 2019-04-24 | IFQ | OL1-2M03-3001 | ME | 2019-05-02 | 036909C-JVD-TRN-01565 | 036909C-JVD-TRN-01565 | IFR | 2019-05-17 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01565 |  | 2019-05-03 | 2
036909C-1056-PID-0031-5607 | P&ID - Olefins Unit 10 - Wastewater - Hydroblast Sump | B | 2019-04-26 | IBD | OL1-2G43-5607 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5607 | P&ID - Olefins Unit 10 - Wastewater - Hydroblast Sump | A | 2019-02-13 | IFR | OL1-2G43-5607 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00007 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1000-JSD-1980-0001 | Fire Proof | A | 2019-01-18 | IFR | OL1-2L01-0002 | PE | 2019-01-29 | 036909C-JVD-TRN-00749 | 036909C-JVD-TRN-00749, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-13 | 2019-04-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00749 |  | 2019-01-29 | 2
036909C-1000-JSS-1140-0001 | ME-013 Diesel Engine | 0 | 2019-01-07 | IMP | OL1-2R03-0013 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 | 2019-04-25 | R1-No comments | TPSK-LSPA1-T-ME-00668 |  | 2019-01-23 | 2
036909C-1023-SP-0510-2300 | Mechanical Equipment Data Sheet - Caustic Tower | 0 | 2019-04-26 | IFP | OL1-2M03-2300 | ME | 2019-04-29 | 036909C-JVD-TRN-01515 | 036909C-JVD-TRN-01515 | IFR | 2019-05-14 | 2019-06-03 | Response to Client comments - sent Aug-27-2019 R2-Comments as noted | TPSK-LSPA1-T-ME -01515 |  | 2019-04-30 | 2
036909C-1039-CN-0014-3960 | PSV-3960 & PSV-3961 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3960 | PE | 2019-08-02 | 036909C-JVD-TRN-02337 | 036909C-JVD-TRN-02337 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02337 |  | 2019-08-05 | 2
036909C-1039-CN-0014-3953 | PSV-3953 & PSV-3970 Sizing Calculation | A | 2019-07-30 | IFR | OL1-2G23-3953 | PE | 2019-08-02 | 036909C-JVD-TRN-02337 | 036909C-JVD-TRN-02337 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02337 |  | 2019-08-05 | 2
036909C-1031-CN-0014-3176 | PSV-3176 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3176 | PE | 2019-08-02 | 036909C-JVD-TRN-02332 | 036909C-JVD-TRN-02332 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02332 |  | 2019-08-05 | 2
036909C-1031-CN-0014-3168 | PSV-3168 Sizing Calculation | A | 2019-07-31 | IFR | OL1-2G23-3168 | PE | 2019-08-02 | 036909C-JVD-TRN-02337 | 036909C-JVD-TRN-02337 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02337 |  | 2019-08-05 | 2
036909C-1031-CN-0014-3167 | PSV-3167 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3167 | PE | 2019-08-02 | 036909C-JVD-TRN-02332 | 036909C-JVD-TRN-02332 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02332 |  | 2019-08-05 | 2
036909C-1031-CN-0014-3165 | PSV-3165 A-B Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3165 | PE | 2019-08-02 | 036909C-JVD-TRN-02332 | 036909C-JVD-TRN-02332 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02332 |  | 2019-08-05 | 2
036909C-1031-CN-0014-3164 | PSV-3164 A-B Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3164 | PE | 2019-08-02 | 036909C-JVD-TRN-02332 | 036909C-JVD-TRN-02332 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02332 |  | 2019-08-05 | 2
036909C-1031-CN-0014-3163 | PSV-3163 A-B Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3163 | PE | 2019-08-02 | 036909C-JVD-TRN-02332 | 036909C-JVD-TRN-02332 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02332 |  | 2019-08-05 | 2
036909C-1031-CN-0014-3162 | PSV-3162 A-B Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3162 | PE | 2019-08-02 | 036909C-JVD-TRN-02332 | 036909C-JVD-TRN-02332 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02332 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3152 | PSV-3152 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3152 | PE | 2019-08-02 | 036909C-JVD-TRN-02332 | 036909C-JVD-TRN-02332 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02332 |  | 2019-08-05 | 2
036909C-1031-CN-0014-3151 | PSV-3151 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3151 | PE | 2019-08-02 | 036909C-JVD-TRN-02332 | 036909C-JVD-TRN-02332 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02332 |  | 2019-08-05 | 2
036909C-1031-CN-0014-3150 | PSV-3150 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3150 | PE | 2019-08-02 | 036909C-JVD-TRN-02332 | 036909C-JVD-TRN-02332 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02332 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3140 | PSV-3140 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3140 | PE | 2019-08-02 | 036909C-JVD-TRN-02332 | 036909C-JVD-TRN-02332 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02332 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3102 | PSV-3102 & PSV-3103 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3102 | PE | 2019-08-02 | 036909C-JVD-TRN-02332 | 036909C-JVD-TRN-02332 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02332 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3077 | PSV-3077 & PSV-3078 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3077 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3074 | PSV-3074 & PSV-3075 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3074 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3072 | PSV-3072 & PSV-3073 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3072 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3049 | PSV-3049 Sizing Calculation | A | 2019-07-31 | IFR | OL1-2G23-3049 | PE | 2019-08-02 | 036909C-JVD-TRN-02337 | 036909C-JVD-TRN-02337 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02337 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3042 | PSV-3042 A-B Sizing Calculation | A | 2019-07-31 | IFR | OL1-2G23-3042 | PE | 2019-08-02 | 036909C-JVD-TRN-02337 | 036909C-JVD-TRN-02337 | IFR | 2019-08-17 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02337 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3041 | PSV-3041 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3041 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3039 | PSV-3039 A-B Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3039 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3037 | PSV-3037 & PSV-3038 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3037 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3035 | PSV-3035 & PSV-3036 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3035 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3034 | PSV-3034 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3034 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3033 | PSV-3033 A-B Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3033 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3032 | PSV-3032 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3032 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3028 | PSV-3028 A-B Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3028 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3027 | PSV-3027 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3027 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3026 | PSV-3026 A-B Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3026 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3019 | PSV-3019 - PSV-3021 - PSV-3023 - PSV-3024 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3019 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3018 | PSV-3018 - PSV-3020 - PSV-3022 - PSV-3025 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3018 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3017 | PSV-3017 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3017 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3016 | PSV-3016 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3016 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3015 | PSV-3015 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3015 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3014 | PSV-3014 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3014 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3011 | PSV-3011 & PSV-3013 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3011 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3010 | PSV-3010 & PSV-3012 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3010 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3007 | PSV-3007 & PSV-3008 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3007 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3006 | PSV-3006 A-B Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3006 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3005 | PSV-3005 A-B Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3005 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3004 | PSV-3004 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3004 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1056-PDS-2500-5640 | Process Equipment Datasheet - 10-TK-5640 - Oily Wastewater Tank | D | 2019-08-01 | IFD | OL1-2G30-5640 | PE | 2019-08-07 | 036909C-JVD-TRN-02378 | 036909C-JVD-TRN-02378 | IFR | 2019-08-22 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02378 |  | 2019-08-08 | 2
036909C-103A-CN-1733-0032 | Calculation Note For Foundation Of 10-E-3044 | A | 2019-08-16 | IFR | OL1-2K13-0231 | CV | 2019-08-27 | 036909C-JVD-TRN-02494 | 036909C-JVD-TRN-02494 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02494 |  | 2019-08-27 | 1
036909C-103A-CN-1733-0044 | Calculation Note For Foundation Of 10-E-3018 A/B | A | 2019-08-16 | IFR | OL1-2K13-0406 | CV | 2019-08-27 | 036909C-JVD-TRN-02494 | 036909C-JVD-TRN-02494 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02494 |  | 2019-08-27
036909C-103A-CN-1733-0037 | Calculation Note For Foundation Of 10-E-3070 | A | 2019-08-16 | IFR | OL1-2K13-0236 | CV | 2019-08-27 | 036909C-JVD-TRN-02494 | 036909C-JVD-TRN-02494 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02494 |  | 2019-08-27 | 1
036909C-1001-DW-2054-0001-03 | Gatehouse A - Architectural Isometric Views | B | 2019-08-22 | IFR | OL1-2K30-0032 | CV | 2019-08-26 | 036909C-JVD-TRN-02484 | 036909C-JVD-TRN-02484 | IFA | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02484 |  | 2019-08-27 | 1
036909C-1001-DW-2054-0001-02 | Gatehouse A- Archiotectural Elevations And Sections | B | 2019-08-22 | IFR | OL1-2K30-0031 | CV | 2019-08-26 | 036909C-JVD-TRN-02484 | 036909C-JVD-TRN-02484 | IFA | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02484 |  | 2019-08-27 | 1
036909C-1001-DW-2054-0001-01 | Gatehouse A - Architectural Plans And Schedules | B | 2019-08-22 | IFR | OL1-2K30-0030 | CV | 2019-08-26 | 036909C-JVD-TRN-02484 | 036909C-JVD-TRN-02484 | IFA | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02484 |  | 2019-08-27 | 1
036909C-1056-SP-2510-5640 | Mechanical Equipment Data Sheet - Oily Wastewater Tank | A | 2019-02-22 | IFQ | OL1-2M03-5640 | ME | 2019-02-26 | 036909C-JVD-TRN-00926 | 036909C-JVD-TRN-00926, ROC-TPSK-CECO-T-00016 | IFR | 2019-03-12 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-00926 |  | 2019-02-26 | 2
036909C-1012-ML-210 | Furnace Section HAZOP Report | A | 2019-03-19 | IFR | OL1-2S95-0210 | ES | 2019-03-20 | 036909C-JVD-TRN-01113 | 036909C-JVD-TRN-01113 | IFR | 2019-04-04 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-ES-01113 |  | 2019-03-21 | 2
036909C-1025-PID-0021-2520 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Feed Cooling | A | 2019-01-08 | IFR | OL1-2G43-2520 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2520 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Feed Cooling | B | 2019-04-04 | IBD | OL1-2G43-2520 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2521 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer | B | 2019-04-04 | IBD | OL1-2G43-2521 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2521 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer | A | 2019-01-08 | IFR | OL1-2G43-2521 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2522 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Reboiler | B | 2019-04-04 | IBD | OL1-2G43-2522 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2522 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Reboiler | A | 2019-01-08 | IFR | OL1-2G43-2522 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2525 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Expander Suction-Discharge Drums | A | 2019-01-08 | IFR | OL1-2G43-2525 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2525 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Expander Suction-Discharge Drums | B | 2019-04-04 | IBD | OL1-2G43-2525 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2527 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Expander-Recompressor | A | 2019-01-08 | IFR | OL1-2G43-2527 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2527 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Expander-Recompressor | B | 2019-04-04 | IBD | OL1-2G43-2527 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2529 | P&ID - Olefins Unit 10 - Cold Fractionation - Hydrogen Recovery | A | 2019-01-08 | IFR | OL1-2G43-2529 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2529 | P&ID - Olefins Unit 10 - Cold Fractionation - Hydrogen Recovery | B | 2019-04-04 | IBD | OL1-2G43-2529 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2530 | P&ID - Olefins Unit 10 - Cold Fractionation - Propylene Refrigerant Subcooler - Sheet 1 | B | 2019-04-04 | IBD | OL1-2G43-2530 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2530 | P&ID - Olefins Unit 10 - Cold Fractionation - Propylene Refrigerant Subcooler - Sheet 1 | A | 2019-01-08 | IFR | OL1-2G43-2530 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2531 | P&ID - Olefins Unit 10 - Cold Fractionation - Propylene Refrigerant Subcooler - Sheet 2 | B | 2019-04-04 | IBD | OL1-2G43-2531 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2531 | P&ID - Olefins Unit 10 - Cold Fractionation - Propylene Refrigerant Subcooler - Sheet 2 | A | 2019-01-08 | IFR | OL1-2G43-2531 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2532 | P&ID - Olefins Unit 10 - Cold Fractionation - Pressure Swing Absorption Unit | A | 2019-01-08 | IFR | OL1-2G43-2532 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2532 | P&ID - Olefins Unit 10 - Cold Fractionation - Pressure Swing Absorption Unit | B | 2019-04-04 | IBD | OL1-2G43-2532 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2541 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer | B | 2019-04-04 | IBD | OL1-2G43-2541 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2541 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer | A | 2019-01-08 | IFR | OL1-2G43-2541 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2543 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer Reboiler | A | 2019-01-08 | IFR | OL1-2G43-2543 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2543 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer Reboiler | B | 2019-04-04 | IBD | OL1-2G43-2543 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2546 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer Condenser | A | 2019-01-08 | IFR | OL1-2G43-2546 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2546 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer Condenser | B | 2019-04-04 | IBD | OL1-2G43-2546 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2547 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer Overhead | A | 2019-01-08 | IFR | OL1-2G43-2547 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2547 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer Overhead | B | 2019-04-04 | IBD | OL1-2G43-2547 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2551 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Bottoms | B | 2019-04-04 | IBD | OL1-2G43-2551 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2551 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Bottoms | A | 2019-01-08 | IFR | OL1-2G43-2551 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2552 | P&ID - Olefins Unit 10 - Cold Fractionation - C2 Tower | B | 2019-04-04 | IBD | OL1-2G43-2552 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2552 | P&ID - Olefins Unit 10 - Cold Fractionation - C2 Tower | A | 2019-01-08 | IFR | OL1-2G43-2552 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2553 | P&ID - Olefins Unit 10 - Cold Fractionation - C2 Tower Bottoms Reboiler | A | 2019-01-08 | IFR | OL1-2G43-2553 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2553 | P&ID - Olefins Unit 10 - Cold Fractionation - C2 Tower Bottoms Reboiler | B | 2019-04-04 | IBD | OL1-2G43-2553 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2554 | P&ID - Olefins Unit 10 - Cold Fractionation - C2 Tower Side Reboiler | B | 2019-04-04 | IBD | OL1-2G43-2554 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2554 | P&ID - Olefins Unit 10 - Cold Fractionation - C2 Tower Side Reboiler | A | 2019-01-08 | IFR | OL1-2G43-2554 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2556 | P&ID - Olefins Unit 10 - Cold Fractionation - Ethane Recycle Pumps | B | 2019-04-04 | IBD | OL1-2G43-2556 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2556 | P&ID - Olefins Unit 10 - Cold Fractionation - Ethane Recycle Pumps | A | 2019-01-08 | IFR | OL1-2G43-2556 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2517 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Rectifier | B | 2019-04-04 | IBD | OL1-2G43-2517 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2517 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Rectifier | A | 2019-01-08 | IFR | OL1-2G43-2517 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2515 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Rectifier Condenser | B | 2019-04-04 | IBD | OL1-2G43-2515 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2515 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Rectifier Condenser | A | 2019-01-08 | IFR | OL1-2G43-2515 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2513 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Reboiler | A | 2019-01-08 | IFR | OL1-2G43-2513 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2513 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Reboiler | B | 2019-04-04 | IBD | OL1-2G43-2513 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2511 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Prefractionator | B | 2019-04-04 | IBD | OL1-2G43-2511 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2511 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Prefractionator | A | 2019-01-08 | IFR | OL1-2G43-2511 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2507 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Separator No 3 | B | 2019-04-04 | IBD | OL1-2G43-2507 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2507 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Separator No. 3 | A | 2019-01-08 | IFR | OL1-2G43-2507 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2505 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Separator No 2 | B | 2019-04-04 | IBD | OL1-2G43-2505 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2505 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Separator No. 2 | A | 2019-01-08 | IFR | OL1-2G43-2505 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2503 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Separator No. 1 | A | 2019-01-08 | IFR | OL1-2G43-2503 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2503 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Separator No 1 | B | 2019-04-04 | IBD | OL1-2G43-2503 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1025-PID-0021-2501 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Chilling | A | 2019-01-08 | IFR | OL1-2G43-2501 | PE | 2019-01-08 | 036909C-JVD-TRN-00612 | 036909C-JVD-TRN-00612, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-23 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00612 |  | 2019-01-08 | 2
036909C-1025-PID-0021-2501 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Chilling | B | 2019-04-04 | IBD | OL1-2G43-2501 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-103S-DW-3432-0001 | Electrical Sub-C- And Far-2 - HVAC Layout | A | 2019-04-17 | IFR | OL1-2H21-0005 | EE | 2019-04-23 | 036909C-JVD-TRN-01453 | 036909C-JVD-TRN-01453, ROC-TPSK-CECO-T-00050 | IFA | 2019-05-08 | 2019-05-17 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01453 |  | 2019-04-24 | 1
036909C-103S-PFD-3410-0001 | Electrical Sub-C- And Far-C - HVAC Process Flow Diagram | B | 2019-07-30 | IDD | OL1-2H20-0003 | EE | 2019-08-07 | 036909C-JVD-TRN-02371 | 036909C-JVD-TRN-02371 | IFA | 2019-08-22 | 2019-08-21 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02371 |  | 2019-08-08 | 1
036909C-103S-PFD-3410-0001 | Electrical Sub-C- And Far-2 - HVAC Process Flow Diagram | A | 2019-04-17 | IFR | OL1-2H20-0003 | EE | 2019-04-23 | 036909C-JVD-TRN-01454 | 036909C-JVD-TRN-01454, ROC-TPSK-CECO-T-00050 | IFA | 2019-05-08 | 2019-05-17 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01454 |  | 2019-04-24 | 1
036909C-1001-DW-2058-0001-03 | Operation Tool Room - Architectural Isometric Views | A | 2019-03-04 | IFR | OL1-2K30-0042 | CV | 2019-03-14 | 036909C-JVD-TRN-01064 | 036909C-JVD-TRN-01064, ROC-TPSK-CECO-T-00041 | IFA | 2019-03-29 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSL-LSPA1-T-CV-01064 |  | 2019-03-15 | 1
036909C-1001-DW-2058-0001-02 | Operation Tool Room - Architectural Elevations And Sections | A | 2019-03-04 | IFR | OL1-2K30-0041 | CV | 2019-03-14 | 036909C-JVD-TRN-01064 | 036909C-JVD-TRN-01064, ROC-TPSK-CECO-T-00041 | IFA | 2019-03-29 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSL-LSPA1-T-CV-01064 |  | 2019-03-15 | 1
036909C-1001-DW-2058-0001-01 | Operation Tool Room - Architectural Plans And Schedules | A | 2019-03-04 | IFR | OL1-2K30-0040 | CV | 2019-03-14 | 036909C-JVD-TRN-01064 | 036909C-JVD-TRN-01064, ROC-TPSK-CECO-T-00041 | IFA | 2019-03-29 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSL-LSPA1-T-CV-01064 |  | 2019-03-15 | 1
036909C-1001-DW-2054-0003 | Gatehouse A - Architectural Plans Elevations Sections And Schedules | A | 2019-03-04 | IFR | OL1-2K30-0038 | CV | 2019-03-14 | 036909C-JVD-TRN-01064 | 036909C-JVD-TRN-01064, ROC-TPSK-CECO-T-00041 | IFA | 2019-03-29 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSL-LSPA1-T-CV-01064 |  | 2019-03-15 | 1
036909C-1001-DW-2054-0001-03 | Gatehouse A - Architectural Isometric Views | A | 2019-03-04 | IFR | OL1-2K30-0032 | CV | 2019-03-14 | 036909C-JVD-TRN-01064 | 036909C-JVD-TRN-01064, ROC-TPSK-CECO-T-00041 | IFA | 2019-03-29 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSL-LSPA1-T-CV-01064 |  | 2019-03-15 | 1
036909C-1001-DW-2054-0001-01 | Gatehouse A - Architectural Plans An Schedules | A | 2019-03-04 | IFR | OL1-2K30-0030 | CV | 2019-03-14 | 036909C-JVD-TRN-01064 | 036909C-JVD-TRN-01064, ROC-TPSK-CECO-T-00041 | IFA | 2019-03-29 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSL-LSPA1-T-CV-01064 |  | 2019-03-15 | 1
036909C-1056-PID-0031-5667 | P&ID - Olefins Unit 10 - Wastewater - Oily Sludge Tank | A | 2019-02-13 | IFR | OL1-2G43-5667 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5667 | P&ID - Olefins Unit 10 - Wastewater - Oily Sludge Tank | B | 2019-04-26 | IBD | OL1-2G43-5667 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5666 | P&ID - Olefins Unit 10 - Wastewater - Slop Oil Tank B | B | 2019-04-26 | IBD | OL1-2G43-5666 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5666 | P&ID - Olefins Unit 10 - Wastewater - Slop Oil Tank B | A | 2019-02-13 | IFR | OL1-2G43-5666 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5665 | P&ID - Olefins Unit 10 - Wastewater - Slop Oil Tank A | A | 2019-02-13 | IFR | OL1-2G43-5665 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5665 | P&ID - Olefins Unit 10 - Wastewater - Slop Oil Tank A | B | 2019-04-26 | IBD | OL1-2G43-5665 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5662 | P&ID - Olefins Unit 10 - Wastewater - Dewatering System | B | 2019-04-26 | IBD | OL1-2G43-5662 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5662 | P&ID - Olefins Unit 10 - Wastewater - Dewatering System | A | 2019-02-13 | IFR | OL1-2G43-5662 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5658 | P&ID - Olefins Unit 10 - Wastewater - Bio Treatment Package | A | 2019-02-13 | IFR | OL1-2G43-5658 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5658 | P&ID - Olefins Unit 10 - Wastewater - Bio Treatment Package | B | 2019-04-26 | IBD | OL1-2G43-5658 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5657 | P&ID - Olefins Unit 10 - Wastewater - Bio Equalization Pit | B | 2019-04-26 | IBD | OL1-2G43-5657 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5657 | P&ID - Olefins Unit 10 - Wastewater - Bio Equalization Pit | A | 2019-02-13 | IFR | OL1-2G43-5657 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00007 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5655 | P&ID - Olefins Unit 10 - Wastewater - Waste Water Cpi - Igf Package | B | 2019-04-26 | IBD | OL1-2G43-5655 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5655 | P&ID - Olefins Unit 10 - Wastewater - Waste Water CPI-IGF Package | A | 2019-02-13 | IFR | OL1-2G43-5655 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00007 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5651 | P&ID - Olefins Unit 10 - Wastewater - CWWT Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5651 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5651 | P&ID - Olefins Unit 10 - Wastewater - CWWT Area Oily Wastewater Sump | B | 2019-04-26 | IBD | OL1-2G43-5651 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5650 | P&ID - Olefins Unit 10 - Wastewater - CT Area Oily Wastewater Sump | B | 2019-04-26 | IBD | OL1-2G43-5650 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5650 | P&ID - Olefins Unit 10 - Wastewater - CT Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5650 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5641 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 2 | A | 2019-02-13 | IFR | OL1-2G43-5641 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5641 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 2 | B | 2019-04-26 | IBD | OL1-2G43-5641 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5640 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 1 | B | 2019-04-26 | IBD | OL1-2G43-5640 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5640 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 1 | A | 2019-02-13 | IFR | OL1-2G43-5640 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5610 | P&ID - Olefins Unit 10 - Wastewater - Oily Waste Water Collection | B | 2019-04-26 | IBD | OL1-2G43-5610 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5610 | P&ID - Olefins Unit 10 - Wastewater - Oily Waste Water Collection | A | 2019-02-13 | IFR | OL1-2G43-5610 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5609 | P&ID - Olefins Unit 10 - Wastewater - Flare Kod Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5609 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5609 | P&ID - Olefins Unit 10 - Wastewater - Flare Kod Area Oily Wastewater Sump | B | 2019-04-26 | IBD | OL1-2G43-5609 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5608 | P&ID - Olefins Unit 10 - Wastewater - C3 Hydrog Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5608 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5608 | P&ID - Olefins Unit 10 - Wastewater - C3 Hydrog Area Oily Wastewater Sump | B | 2019-04-26 | IBD | OL1-2G43-5608 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5606 | P&ID - Olefins Unit 10 - Wastewater - Furnace Area Oily Wastewater Sump | B | 2019-04-26 | IBD | OL1-2G43-5606 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5606 | P&ID - Olefins Unit 10 - Wastewater - Furnace Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5606 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5605 | P&ID - Olefins Unit 10 - Wastewater - Refrig Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5605 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5605 | P&ID - Olefins Unit 10 - Wastewater - Refrig Area Oily Wastewater Sump | B | 2019-04-26 | IBD | OL1-2G43-5605 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5604 | P&ID - Olefins Unit 10 - Wastewater - CGC Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5604 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5604 | P&ID - Olefins Unit 10 - Wastewater - CGC Area Oily Wastewater Sump | B | 2019-04-26 | IBD | OL1-2G43-5604 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5603 | P&ID - Olefins Unit 10 - Wastewater - QW Area Oily Wastewater Sump | B | 2019-04-26 | IBD | OL1-2G43-5603 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5603 | P&ID - Olefins Unit 10 - Wastewater - QW Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5603 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5602 | P&ID - Olefins Unit 10 - Wastewater - Butadiene Area Oily Wastewater Sump | B | 2019-04-26 | IBD | OL1-2G43-5602 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5602 | P&ID - Olefins Unit 10 - Wastewater - Butadiene Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5602 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1053-PDS-0300-5360 | Process Data Sheet for 10-PIT-5360 | C | 2019-08-01 | IFD | OL1-2G30-5360 | PE | 2019-08-02 | 036909C-JVD-TRN-02323 | 036909C-JVD-TRN-02323 | IFR | 2019-08-01 | 2019-08-23 | R1-No comments | TPSK-LSPA1-T-PE-02323 |  | 2019-08-05 | 2
036909C-1053-PDS-0300-5302 | Process Data Sheet for 10-S-5302 A-B | A | 2019-08-01 | IFR | OL1-2G30-5302 | PE | 2019-08-02 | 036909C-JVD-TRN-02323 | 036909C-JVD-TRN-02323 | IFR | 2019-08-01 | 2019-08-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02323 |  | 2019-08-05 | 2
036909C-1053-PDS-0300-5301 | Process Data Sheet for 10-S-5301 A-H | A | 2019-08-01 | IFR | OL1-2G30-5301 | PE | 2019-08-02 | 036909C-JVD-TRN-02323 | 036909C-JVD-TRN-02323 | IFR | 2019-08-01 | 2019-08-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02323 |  | 2019-08-05 | 2
036909C-1023-PDS-1390-2311 | SP Item Data Sheet - Desuperheater - SP-23011 | A | 2019-07-18 | IFR | OL1-2P03-2311 | MP | 2019-07-23 | 036909C-JVD-TRN-02253 | 036909C-JVD-TRN-02253 | IFR | 2019-08-07 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02253 |  | 2019-07-24 | 2
036909C-1030-PDS-0500-3050 | Process Equipment Datasheet - 10-T-3050 - Degasser | C | 2019-07-25 | IFD | OL1-2G30-3050 | PE | 2019-07-25 | 036909C-JVD-TRN-02266 | 036909C-JVD-TRN-02266 | IFR | 2019-08-09 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PE-02266 |  | 2019-07-29 | 2
036909C-1030-PDS-0500-3040 | Process Equipment Datasheet - 10-T-3040 - Rectifier | C | 2019-07-25 | IFD | OL1-2G30-3040 | PE | 2019-07-25 | 036909C-JVD-TRN-02266 | 036909C-JVD-TRN-02266 | IFR | 2019-08-09 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PE-02266 |  | 2019-07-29 | 2
036909C-1030-PDS-0500-3020 | Process Equipment Datasheet - 10-T-3020 - Main Washer | C | 2019-07-25 | IFD | OL1-2G30-3020 | PE | 2019-07-25 | 036909C-JVD-TRN-02266 | 036909C-JVD-TRN-02266 | IFR | 2019-08-09 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PE-02266 |  | 2019-07-29 | 2
036909C-1021-SP-0510-2140 | Mechanical Equipment Data Sheet - Process Water Stripper | 0 | 2019-05-21 | IFP | OL1-2M03-2140 | ME | 2019-05-22 | 036909C-JVD-TRN-01721 | 036909C-JVD-TRN-01721 | IFR | 2019-06-06 | 2019-06-21 | Response to Client Comments sent Aug 26-2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01721 |  | 2019-05-23 | 2
036909C-1024-PDS-1390-2412 | Piping Specialty Item - Datasheet - Desuperheater - SP-24012 | A | 2019-07-18 | IFR | OL1-2P03-2412 | MP | 2019-07-24 | 036909C-JVD-TRN-02259 | 036909C-JVD-TRN-02259 | IFR | 2019-08-08 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02259 |  | 2019-07-25 | 2
036909C-1024-PDS-1390-2409 | Piping Specialty Item - Datasheet - Desuperheater - SP-24009 | A | 2019-07-18 | IFR | OL1-2P03-2409 | MP | 2019-07-24 | 036909C-JVD-TRN-02259 | 036909C-JVD-TRN-02259 | IFR | 2019-08-08 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02259 |  | 2019-07-25 | 2
036909C-1021-SP-0510-2120 | Mechanical Equipment Data Sheet - Distillate Stripper | 0 | 2019-05-21 | IFP | OL1-2M03-2120 | ME | 2019-05-22 | 036909C-JVD-TRN-01721 | 036909C-JVD-TRN-01721 | IFR | 2019-06-06 | 2019-06-21 | Response to Client Comments sent Aug-26-2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01721 |  | 2019-05-23 | 2
036909C-1020-SP-0510-2000 | Mechanical Equipment Data Sheet - Quench Oil Tower | 0 | 2019-04-24 | IFP | OL1-2M03-2000 | ME | 2019-04-25 | 036909C-JVD-TRN-01487 | 036909C-JVD-TRN-01487 | IFR | 2019-05-10 | 2019-05-29 | Response to Clients Comments sent Aug-26-2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01487 |  | 2019-04-26 | 2
036909C-105W-DW-0051-0001 | Detail Plot Plan - Zone 5W Waste Water Treatment | C | 2019-07-19 | IBD | OL1-2P06-0017 | MP | 2019-07-22 | 036909C-JVD-TRN-02219 | 036909C-JVD-TRN-02219 | IFR | 2019-08-06 | 2019-08-22 | R2-Comments as noted | TPSK-LSPA1-T-MP-02219 |  | 2019-07-23 | 2
036909C-105T-DW-0051-0001 | Detail Plot Plan - Zone 5T - Cooling Water Unit | C | 2019-07-16 | IBD | OL1-2P06-0015 | MP | 2019-07-22 | 036909C-JVD-TRN-02219 | 036909C-JVD-TRN-02219 | IFR | 2019-08-06 | 2019-08-22 | R2-Comments as noted | TPSK-LSPA1-T-MP-02219 |  | 2019-07-23 | 2
036909C-103A-DW-0051-0001 | Detail Plot Plan - Zone 3A - Butadiene Extraction Unit | C | 2019-07-16 | IBD | OL1-2P06-0013 | MP | 2019-07-22 | 036909C-JVD-TRN-02219 | 036909C-JVD-TRN-02219 | IFR | 2019-08-06 | 2019-08-22 | R2-Comments as noted | TPSK-LSPA1-T-MP-02219 |  | 2019-07-23 | 2
036909C-102E-DW-0051-0001 | Detail Plot Plan - Zone 2E - Cracked Gas Compressor | C | 2019-07-16 | IBD | OL1-2P06-0012 | MP | 2019-07-22 | 036909C-JVD-TRN-02219 | 036909C-JVD-TRN-02219 | IFR | 2019-08-06 | 2019-08-22 | R2-Comments as noted | TPSK-LSPA1-T-MP-02219 |  | 2019-07-23 | 2
036909C-102D-DW-0051-0001 | Detail Plot Plan - Zone 2D - Process Cold Compressor | C | 2019-07-16 | IBD | OL1-2P06-0011 | MP | 2019-07-22 | 036909C-JVD-TRN-02219 | 036909C-JVD-TRN-02219 | IFR | 2019-08-06 | 2019-08-22 | R2-Comments as noted | TPSK-LSPA1-T-MP-02219 |  | 2019-07-23 | 2
036909C-102C-DW-0051-0001 | Detail Plot Plan - Zone 2C - Hot Fractionation-GHU Unit | C | 2019-07-16 | IBD | OL1-2P06-0010 | MP | 2019-07-22 | 036909C-JVD-TRN-02219 | 036909C-JVD-TRN-02219 | IFR | 2019-08-06 | 2019-08-22 | R2-Comments as noted | TPSK-LSPA1-T-MP-02219 |  | 2019-07-23 | 2
036909C-102B-DW-0051-0001 | Detail Plot Plan - Zone 2B - C3 Hydrogenation | C | 2019-07-16 | IBD | OL1-2P06-0009 | MP | 2019-07-22 | 036909C-JVD-TRN-02219 | 036909C-JVD-TRN-02219 | IFR | 2019-08-06 | 2019-08-22 | R2-Comments as noted | TPSK-LSPA1-T-MP-02219 |  | 2019-07-23 | 2
036909C-102A-DW-0051-0001 | Detail Plot Plan - Zone 2A - Quench | C | 2019-07-16 | IBD | OL1-2P06-0008 | MP | 2019-07-22 | 036909C-JVD-TRN-02219 | 036909C-JVD-TRN-02219 | IFR | 2019-08-06 | 2019-08-22 | R2-Comments as noted | TPSK-LSPA1-T-MP-02219 |  | 2019-07-23 | 2
036909C-1051-PDS-1390-5109 | SP Item Data Sheet - SHP - HP Letdown Desuperheater - SP-51009 | A | 2019-07-25 | IFR | OL1-2P03-5109 | MP | 2019-08-01 | 036909C-JVD-TRN-02317 | 036909C-JVD-TRN-02317 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02317 |  | 2019-08-05 | 2
036909C-1012-SP-4061-2002 | Elevator Data Sheet | 1 | 2019-07-19 | IMP | OL1-2M03-2002 | ME | 2019-07-23 | 036909C-JVD-TRN-02246 | 036909C-JVD-TRN-02246 | IFR | 2019-08-07 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-02246 |  | 2019-07-24 | 2
036909C-1026-CN-0014-2622 | PSV 2616 Sizing Calculation | A | 2019-07-26 | IFR | OL1-2G23-2622 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1027-PDS-1546-2790 | Process Datasheet for Restriction Orifice - Unit 27 | A | 2019-07-31 | IFR | OL1-2G31-2790 | PE | 2019-08-02 | 036909C-JVD-TRN-02338 | 036909C-JVD-TRN-02338 | IFR | 2019-08-17 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PE-02338 |  | 2019-08-05 | 2
036909C-101B-DW-0051-0001 | Detail Plot Plan - Zone 1B - Furnaces Utilities | C | 2019-07-16 | IBD | OL1-2P06-0007 | MP | 2019-07-22 | 036909C-JVD-TRN-02219 | 036909C-JVD-TRN-02219 | IFR | 2019-08-06 | 2019-08-22 | R2-Comments as noted | TPSK-LSPA1-T-MP-02219 |  | 2019-07-23 | 2
036909C-1026-PDS-1546-2690 | Process Datasheet for Restriction Orifice - Unit 26 | A | 2019-07-29 | IFR | OL1-2G31-2690 | PE | 2019-08-02 | 036909C-JVD-TRN-02338 | 036909C-JVD-TRN-02338 | IFR | 2019-08-17 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PE-02338 |  | 2019-08-05 | 2
036909C-100P-DW-0051-0001 | Unit Plot Plan - Zone 0P - Main Pipe Rack | C | 2019-07-18 | IBD | OL1-2P06-0003 | MP | 2019-07-22 | 036909C-JVD-TRN-02219 | 036909C-JVD-TRN-02219 | IFR | 2019-08-06 | 2019-08-22 | R2-Comments as noted | TPSK-LSPA1-T-MP-02219 |  | 2019-07-23 | 2
036909C-1000-DW-0051-0001 | General Plot Plan | C | 2019-07-19 | IBD | OL1-2P06-0001 | MP | 2019-07-22 | 036909C-JVD-TRN-02219 | 036909C-JVD-TRN-02219 | IFR | 2019-08-06 | 2019-08-22 | R2-Comments as noted | TPSK-LSPA1-T-MP-02219 |  | 2019-07-23 | 2
036909C-1023-PDS-0800-2310 | Process Equipment Datasheet - 10-D-2310 - Spent Caustic Deoiling Drum | D | 2019-07-16 | IFD | OL1-2G30-2310 | PE | 2019-07-16 | 036909C-JVD-TRN-02168 | 036909C-JVD-TRN-02168 | IFR | 2019-07-31 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PE-02168 |  | 2019-07-17 | 2
036909C-100M-DW-0051-0001 | Detail Plot Plan - Zone 0M - Metering Station | A | 2019-02-15 | IFR | OL1-2P06-0002 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15 | 1
036909C-102E-CN-1734-0002 | Calculation Note For Foundation Of Lifting Station 10-PIT-5603 | A | 2019-06-14 | IFR | OL1-2K13-0329 | CV | 2019-06-26 | 036909C-JVD-TRN-02003 | 036909C-JVD-TRN-02003 | IFA | 2019-07-11 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02003 |  | 2019-06-27 | 1
036909C-103S-CN-3442-0001 | Electrical SUB-C & FAR-2 – HVAC Thermal Calculation | A | 2019-04-17 | IFR | OL1-2H10-0002 | EE | 2019-04-23 | 036909C-JVD-TRN-01446 | 036909C-JVD-TRN-01446, ROC-TPSK-CECO-T-00050 | IFA | 2019-05-08 | 2019-05-17 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01446 |  | 2019-04-24 | 1
036909C-103S-CN-3442-0001 | Electrical SUB-C & FAR-2 – HVAC Thermal Calculation | B | 2019-07-30 | IDD | OL1-2H10-0002 | EE | 2019-08-07 | 036909C-JVD-TRN-02369 | 036909C-JVD-TRN-02369 | IFA | 2019-08-22 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-02369 |  | 2019-08-08 | 1
036909C-102C-CN-1733-0031 | Calculation Note For Foundation Of 10-E-2702 | A | 2019-06-20 | IFR | OL1-2K13-0179 | CV | 2019-06-26 | 036909C-JVD-TRN-02003 | 036909C-JVD-TRN-02003 | IFA | 2019-07-11 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02003 |  | 2019-06-27 | 1
036909C-1056-PID-0031-5601 | P&ID - Olefins Unit 10 - Wastewater - Pygas Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5601 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5601 | P&ID - Olefins Unit 10 - Wastewater - Pygas Area Oily Wastewater Sump | B | 2019-04-26 | IBD | OL1-2G43-5601 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1022-PID-0021-2224 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Wash Oil Injection | B | 2019-03-29 | IBD | OL1-2G43-2224 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1022-PID-0021-2224 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Wash Oil Injection | A | 2018-12-20 | IFR | OL1-2G43-2224 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1022-PID-0021-2222 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Wash Water Injection | B | 2019-03-29 | IBD | OL1-2G43-2222 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1022-PID-0021-2222 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Wash Water Injection | A | 2018-12-20 | IFR | OL1-2G43-2222 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1022-PID-0021-2220 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Wash Water Cooling | B | 2019-03-29 | IBD | OL1-2G43-2220 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1022-PID-0021-2220 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Wash Water Cooling | A | 2018-12-20 | IFR | OL1-2G43-2220 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1022-PID-0021-2217 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 4th Stage Discharge Drum | A | 2018-12-20 | IFR | OL1-2G43-2217 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1022-PID-0021-2217 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 4th Stage Discharge Drum | B | 2019-03-29 | IBD | OL1-2G43-2217 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1022-PID-0021-2215 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 4th Stage Aftercooling | B | 2019-03-29 | IBD | OL1-2G43-2215 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1022-PID-0021-2215 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 4th Stage Aftercooling | A | 2018-12-20 | IFR | OL1-2G43-2215 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1022-PID-0021-2214 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 4th Stage Suction Drum | B | 2019-03-29 | IBD | OL1-2G43-2214 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1022-PID-0021-2214 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 4th Stage Suction Drum | A | 2018-12-20 | IFR | OL1-2G43-2214 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1022-PID-0021-2212 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 3rd Stage Aftercooling | A | 2018-12-20 | IFR | OL1-2G43-2212 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1022-PID-0021-2212 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 3rd Stage Aftercooling | B | 2019-03-29 | IBD | OL1-2G43-2212 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1022-PID-0021-2211 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 3rd and 4th Stages | A | 2018-12-20 | IFR | OL1-2G43-2211 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1022-PID-0021-2211 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 3rd And 4th Stages | B | 2019-03-29 | IBD | OL1-2G43-2211 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1022-PID-0021-2210 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 3rd Stage Suction Drum | B | 2019-03-29 | IBD | OL1-2G43-2210 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1022-PID-0021-2210 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 3rd Stage Suction Drum | A | 2018-12-20 | IFR | OL1-2G43-2210 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1022-PID-0021-2208 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 2nd Stage Aftercooling | B | 2019-03-29 | IBD | OL1-2G43-2208 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1022-PID-0021-2208 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 2nd Stage Aftercooling | A | 2018-12-20 | IFR | OL1-2G43-2208 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1022-PID-0021-2206 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 2nd Stage Suction Drum | A | 2018-12-20 | IFR | OL1-2G43-2206 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1022-PID-0021-2206 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 2nd Stage Suction Drum | B | 2019-03-29 | IBD | OL1-2G43-2206 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1022-PID-0021-2204 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 1st Stage Aftercooling | B | 2019-03-29 | IBD | OL1-2G43-2204 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1022-PID-0021-2204 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 1st Stage Aftercooling | A | 2018-12-20 | IFR | OL1-2G43-2204 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1022-PID-0021-2203 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 1st And 2nd Stages | B | 2019-03-29 | IBD | OL1-2G43-2203 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1022-PID-0021-2203 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 1st and 2nd Stages | A | 2018-12-20 | IFR | OL1-2G43-2203 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1022-PID-0021-2201 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 1st Stage Suction Drum | A | 2018-12-20 | IFR | OL1-2G43-2201 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1022-PID-0021-2201 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 1st Stage Suction Drum | B | 2019-03-29 | IBD | OL1-2G43-2201 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1023-PID-0021-2329 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Wet Air Oxidation Package | B | 2019-04-02 | IBD | OL1-2G43-2329 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2329 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Wet Air Oxidation Package | A | 2018-12-20 | IFR | OL1-2G43-2329 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2328 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Stripper Ovhd Drum | A | 2018-12-20 | IFR | OL1-2G43-2328 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2328 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Stripper Ovhd Drum | B | 2019-04-02 | IBD | OL1-2G43-2328 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2326 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Stripper | B | 2019-04-02 | IBD | OL1-2G43-2326 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2326 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Stripper | A | 2018-12-20 | IFR | OL1-2G43-2326 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2325 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Stripper Feed Heater | B | 2019-04-02 | IBD | OL1-2G43-2325 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2325 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Stripper Feed Heater Cond. Pot | A | 2018-12-20 | IFR | OL1-2G43-2325 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2320 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Storage | B | 2019-04-02 | IBD | OL1-2G43-2320 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2320 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Storage | A | 2018-12-20 | IFR | OL1-2G43-2320 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2319 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Skim Oil Drum | A | 2018-12-20 | IFR | OL1-2G43-2319 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2319 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Skim Oil Drum | B | 2019-04-02 | IBD | OL1-2G43-2319 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2318 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Drain Sump | A | 2018-12-20 | IFR | OL1-2G43-2318 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2318 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Drain Sump | B | 2019-04-02 | IBD | OL1-2G43-2318 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2317 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Yellow Oil Drum | B | 2019-04-02 | IBD | OL1-2G43-2317 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2317 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Yellow Oil Drum | A | 2018-12-20 | IFR | OL1-2G43-2317 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2316 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Caustic Drain Sump | B | 2019-04-02 | IBD | OL1-2G43-2316 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2316 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Caustic Drain Sump | A | 2018-12-20 | IFR | OL1-2G43-2316 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2315 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Caustic Drain Collection | B | 2019-04-02 | IBD | OL1-2G43-2315 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2315 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Caustic Drain Collection | A | 2018-12-20 | IFR | OL1-2G43-2315 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2314 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Drain Collection | A | 2018-12-20 | IFR | OL1-2G43-2314 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2314 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Drain Collection | B | 2019-04-02 | IBD | OL1-2G43-2314 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2313 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Degassing | B | 2019-04-02 | IBD | OL1-2G43-2313 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2313 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Degassing | A | 2018-12-20 | IFR | OL1-2G43-2313 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2311 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Deoiling | A | 2018-12-20 | IFR | OL1-2G43-2311 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2311 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Deoiling | B | 2019-04-02 | IBD | OL1-2G43-2311 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2310 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Fresh Caustic Supply | B | 2019-04-02 | IBD | OL1-2G43-2310 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2310 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Fresh Caustic Supply | A | 2018-12-20 | IFR | OL1-2G43-2310 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2305 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Strong Caustic Circulation | B | 2019-04-02 | IBD | OL1-2G43-2305 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2305 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Strong Caustic Circulation | A | 2018-12-20 | IFR | OL1-2G43-2305 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2303 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Weak & Intermediate Caustic Circulation | A | 2018-12-20 | IFR | OL1-2G43-2303 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2303 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Weak-Intermediate Caustic Circulation | B | 2019-04-02 | IBD | OL1-2G43-2303 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1023-PID-0021-2301 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Caustic Tower | A | 2018-12-20 | IFR | OL1-2G43-2301 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1023-PID-0021-2301 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Caustic Tower | B | 2019-04-02 | IBD | OL1-2G43-2301 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-22 |  | Transmitted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1028-SP-4065-6005 | Mechanical Equipment Datasheet for Ethylene and Propylene Compressor Bridge Crane | 0 | 2019-08-05 | IFP | OL1-2M03-6005 | ME | 2019-08-06 | 036909C-JVD-TRN-02360 | 036909C-JVD-TRN-02360 | IFR | 2019-08-21 | 2019-08-21 | R1-No comments | TPSK-LSPA1-T-ME-02360 |  | 2019-08-07 | 2
036909C-1023-SP-4065-6004 | Mechanical Equipment Datasheet for Cracked Gas Compressor Bridge Crane | 0 | 2019-08-05 | IFP | OL1-2M03-6004 | ME | 2019-08-06 | 036909C-JVD-TRN-02360 | 036909C-JVD-TRN-02360 | IFR | 2019-08-21 | 2019-08-21 | R1-No comments | TPSK-LSPA1-T-ME-02360 |  | 2019-08-07 | 2
036909C-1000-MR-4065-0001 | Material Requisition For Bridge Crane | 0 | 2019-08-05 | IFP | OL1-2C13-771000 | PL | 2019-08-06 | 036909C-JVD-TRN-02361 | 036909C-JVD-TRN-02361 | IFR | 2019-08-21 | 2019-08-21 | R1-No comments | TPSK-LSPA1-T-PL-02361 |  | 2019-08-07 | 2
036909C-1021-SP-0510-2100 | Mechanical Equipment Data Sheet Quench Water Tower | 2 | 2019-08-22 | IFP | OL1-2M03-2100 | ME | 2019-08-22 | 036909C-JVD-TRN-02475 | 036909C-JVD-TRN-02475 | IFR | 2019-09-06 |  | Transmitted | TPSK-LSPA1-T-ME-02475 |  | 2019-08-22 | 2
036909C-102D-DW-1622-0201 | Power Layout - Zone-2D | A | 2019-07-24 | IFR | OL1-2E32-0013 | EE | 2019-07-29 | 036909C-JVD-TRN-02275 | 036909C-JVD-TRN-02275 | IFA | 2019-08-13 | 2019-08-21 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02275 |  | 2019-07-30 | 1
036909C-102B-DW-1622-0201 | Power Layout - Zone-2B | A | 2019-07-24 | IFR | OL1-2E32-0011 | EE | 2019-07-29 | 036909C-JVD-TRN-02275 | 036909C-JVD-TRN-02275 | IFA | 2019-08-13 | 2019-08-21 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02275 |  | 2019-07-30 | 1
036909C-102A-DW-1622-0201 | Power Layout - Zone-2A | A | 2019-07-24 | IFR | OL1-2E32-0010 | EE | 2019-07-29 | 036909C-JVD-TRN-02275 | 036909C-JVD-TRN-02275 | IFA | 2019-08-13 | 2019-08-21 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02275 |  | 2019-07-30 | 1
036909C-101B-DW-1622-0201 | Power Layout - Zone-1B | A | 2019-07-24 | IFR | OL1-2E32-0009 | EE | 2019-07-29 | 036909C-JVD-TRN-02275 | 036909C-JVD-TRN-02275 | IFA | 2019-08-13 | 2019-08-21 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02275 |  | 2019-07-30 | 1
036909C-102B-CN-1734-0003 | Calculation Note for Foundation of 10-PIT-2392 | A | 2019-06-07 | IFR | OL1-2K13-0341 | CV | 2019-06-21 | 036909C-JVD-TRN-01961 | 036909C-JVD-TRN-01961 | IFA | 2019-06-21 | 2019-08-20 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01961 |  | 2019-06-24 | 1
036909C-1053-PDS-0300-5351 | Process Data Sheet for 10-PIT-5351 | C | 2019-08-01 | IFD | OL1-2G30-5351 | PE | 2019-08-05 | 036909C-JVD-TRN-02339 | 036909C-JVD-TRN-02339 | IFR | 2019-08-16 | 2019-08-22 | R1-No comments | TPSK-LSPA1-T-PE-02339 |  | 2019-08-06 | 2
036909C-105F-DW-0051-0001 | Detail Plot Plan - Zone 5F HP And Polyolefins Flares Unit | A | 2019-03-11 | IFR | OL1-2P06-0014 | MP | 2019-03-12 | 036909C-JVD-TRN-01031 | 036909C-JVD-TRN-01031 | IFA | 2019-03-27 | 2019-04-01 | R2-Comments as noted | TPSK-LSPA1-T-MP-01031 |  | 2019-03-13 | 1
036909C-1021-SP-0510-2100 | Mechanical Equipment Data Sheet - Quench Water Tower | A | 2018-12-06 | IFQ | OL1-2M03-2100 | ME | 2018-12-07 | 036909C-JVD-TRN-00443 | 036909C-JVD-TRN-00443 | IFR | 2018-12-20 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00443 |  | 2018-12-07 | 2
036909C-1021-SP-0510-2100 | Mechanical Equipment Data Sheet - Quench Water Tower | B | 2019-02-04 | IFQ | OL1-2M03-2100 | ME | 2019-02-06 | 036909C-JVD-TRN-00803 | 036909C-JVD-TRN-00803, ROC-TPSK-CECO-T-00014 | IFI |  | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-ME -00803 |  | 2019-02-06 | 2
036909C-1021-SP-0510-2100 | Mechanical Equipment Data Sheet - Quench Water Tower | 1 | 2019-05-20 | IFP | OL1-2M03-2100 | ME | 2019-05-20 | 036909C-JVD-TRN-01701 | 036909C-JVD-TRN-01701 | IFR | 2019-06-04 |  | Transmitted | TPSK-LSPA1-T-ME-01701 |  | 2019-05-21 | 2
036909C-1021-SP-0510-2100 | Mechanical Equipment Data Sheet - Quench Water Tower | 0 | 2019-04-25 | IFP | OL1-2M03-2100 | ME | 2019-04-25 | 036909C-JVD-TRN-01487 | 036909C-JVD-TRN-01487 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01487 |  | 2019-04-26 | 2
036909C-1051-SP-2510-5120 | Mechanical Equipment Data Sheet - Raw Condensate Tank | A | 2019-01-24 | IFQ | OL1-2M03-5120 | ME | 2019-01-28 | 036909C-JVD-TRN-00746 | 036909C-JVD-TRN-00746, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00746 |  | 2019-01-28 | 2
036909C-1051-SP-2510-5110 | Mechanical Equipment Data Sheet - Condensate Tank | B | 2019-04-16 | IFQ | OL1-2M03-5110 | ME | 2019-04-22 | 036909C-JVD-TRN-01430 | 036909C-JVD-TRN-01430 | IFR | 2019-05-07 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01430 |  | 2019-04-23 | 2
036909C-1051-SP-2510-5110 | Mechanical Equipment Data Sheet - Condensate Tank | A | 2019-01-24 | IFQ | OL1-2M03-5110 | ME | 2019-01-28 | 036909C-JVD-TRN-00746 | 036909C-JVD-TRN-00746, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00746 |  | 2019-01-28 | 2
036909C-1021-PID-0021-2138 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Blowdown Cooling | B | 2019-03-29 | IBD | OL1-2G43-2138 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2138 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Blowdown Cooling | A | 2018-12-20 | IFR | OL1-2G43-2138 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2137 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Superheating | A | 2018-12-20 | IFR | OL1-2G43-2137 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2137 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Superheating | B | 2019-03-29 | IBD | OL1-2G43-2137 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2134 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Generator Reboilers - Sheet 2 | A | 2018-12-20 | IFR | OL1-2G43-2134 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2134 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Generator Reboilers - Sheet 2 | B | 2019-03-29 | IBD | OL1-2G43-2134 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2132 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Generator Reboilers - Sheet 1 | A | 2018-12-20 | IFR | OL1-2G43-2132 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2132 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Generator Reboilers - Sheet 1 | B | 2019-03-29 | IBD | OL1-2G43-2132 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2131 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Generator | B | 2019-03-29 | IBD | OL1-2G43-2131 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2131 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Generator | A | 2018-12-20 | IFR | OL1-2G43-2131 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2130 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Generator Feed Heating | B | 2019-03-29 | IBD | OL1-2G43-2130 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2130 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Generator Feed Heating | A | 2018-12-20 | IFR | OL1-2G43-2130 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2127 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Generator Feed Pumps | B | 2019-03-29 | IBD | OL1-2G43-2127 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2127 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Generator Feed Pumps | A | 2018-12-20 | IFR | OL1-2G43-2127 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2126 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Process Water Stripper Reboiler | B | 2019-03-29 | IBD | OL1-2G43-2126 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2126 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Process Water Stripper Reboiler | A | 2018-12-20 | IFR | OL1-2G43-2126 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2125 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Process Water Stripper | A | 2018-12-20 | IFR | OL1-2G43-2125 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2125 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Process Water Stripper | B | 2019-03-29 | IBD | OL1-2G43-2125 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2123 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Process Water Stripper Feed | B | 2019-03-29 | IBD | OL1-2G43-2123 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2123 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Process Water Stripper Feed | A | 2018-12-20 | IFR | OL1-2G43-2123 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2122 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Distillate Stripper Reboiler | A | 2018-12-20 | IFR | OL1-2G43-2122 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2122 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Distillate Stripper Reboiler | B | 2019-03-29 | IBD | OL1-2G43-2122 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2120 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Distillate Stripper | A | 2018-12-20 | IFR | OL1-2G43-2120 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2120 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Distillate Stripper | B | 2019-03-29 | IBD | OL1-2G43-2120 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2117 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Drain Drum | A | 2018-12-20 | IFR | OL1-2G43-2117 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2117 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Water Drain Drum | B | 2019-03-29 | IBD | OL1-2G43-2117 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2115 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Drain Collection | A | 2018-12-20 | IFR | OL1-2G43-2115 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2115 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Water Drain Collection | B | 2019-03-29 | IBD | OL1-2G43-2115 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2110 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Water Cooling | B | 2019-03-29 | IBD | OL1-2G43-2110 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2110 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Cooling | A | 2018-12-20 | IFR | OL1-2G43-2110 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2108 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Water Distribution | B | 2019-03-29 | IBD | OL1-2G43-2108 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2108 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Distribution | A | 2018-12-20 | IFR | OL1-2G43-2108 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2106 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Pumps | A | 2018-12-20 | IFR | OL1-2G43-2106 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2106 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Water Pumps | B | 2019-03-29 | IBD | OL1-2G43-2106 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2104 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Oil Fractionator Reflux | B | 2019-03-29 | IBD | OL1-2G43-2104 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2104 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Oil Fractionator Reflux | A | 2018-12-20 | IFR | OL1-2G43-2104 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2102 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Water Tower Overhead | B | 2019-03-29 | IBD | OL1-2G43-2102 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-1021-PID-0021-2102 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Tower Overhead | A | 2018-12-20 | IFR | OL1-2G43-2102 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2101 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Tower | A | 2018-12-20 | IFR | OL1-2G43-2101 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1021-PID-0021-2101 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Water Tower | B | 2019-03-29 | IBD | OL1-2G43-2101 | PE | 2019-03-29 | 036909C-JVD-TRN-01201 | 036909C-JVD-TRN-01201, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-15 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01201 |  | 2019-04-01 | 2
036909C-103S-DW-2052-0001-04 | Electrical SUB-C & FAR-C - Architectural Sections | B | 2019-08-12 | IFR | OL1-2K30-0018 | CV | 2019-08-21 | 036909C-JVD-TRN-02465 | 036909C-JVD-TRN-02465 | IFA | 2019-09-05 |  | Transmitted | TPSK-LPSA1-T-CV-02465 |  | 2019-08-22 | 1
036909C-1000-MS-1593-0003 | Job Specification For Functional Test Execution | A | 2019-08-19 | IFR | OL1-2O71-0029 | PE | 2019-08-21 | 036909C-JVD-TRN-02464 | 036909C-JVD-TRN-02464 | IFR | 2019-09-05 |  | Transmitted |  |  | 2019-08-22 | 2
036909C-1027-PID-0021-2742 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Light Oil Drain Drum | A | 2019-03-14 | IFR | OL1-2G43-2742 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2742 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Light Oil Drain Drum | B | 2019-05-06 | IBD | OL1-2G43-2742 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2740 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Light Oil Drain Collection | A | 2019-03-14 | IFR | OL1-2G43-2740 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2740 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Light Oil Drain Collection | B | 2019-05-06 | IBD | OL1-2G43-2740 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2738 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Recycle-Product Cooling | A | 2019-03-14 | IFR | OL1-2G43-2738 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2738 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Recycle-Product Cooling | B | 2019-05-06 | IBD | OL1-2G43-2738 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2736 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Separator Drum | A | 2019-03-14 | IFR | OL1-2G43-2736 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2736 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Separator Drum | B | 2019-05-06 | IBD | OL1-2G43-2736 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2734 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Reactor | B | 2019-05-06 | IBD | OL1-2G43-2734 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2734 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Reactor | A | 2019-03-14 | IFR | OL1-2G43-2734 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2733 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Feed Heating | B | 2019-05-06 | IBD | OL1-2G43-2733 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2733 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Feed Heating | A | 2019-03-14 | IFR | OL1-2G43-2733 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2732 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Feed Pump | A | 2019-03-14 | IFR | OL1-2G43-2732 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2732 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Feed Pump | B | 2019-05-06 | IBD | OL1-2G43-2732 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2730 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Feed Surge Drum | A | 2019-03-14 | IFR | OL1-2G43-2730 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2730 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Feed Surge Drum | B | 2019-05-06 | IBD | OL1-2G43-2730 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2722 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Regeneration Decoke Drum | A | 2019-03-14 | IFR | OL1-2G43-2722 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2722 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Regen Hydrog Drum | B | 2019-05-06 | IBD | OL1-2G43-2722 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2720 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Reactivation Gas Heating | A | 2019-03-14 | IFR | OL1-2G43-2720 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2720 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Regen Gas Electric Heater | B | 2019-05-06 | IBD | OL1-2G43-2720 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2718 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Anti-Oxidant Injection Package | A | 2019-03-14 | IFR | OL1-2G43-2718 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2718 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Anti-Oxidant Injection Package | B | 2019-05-06 | IBD | OL1-2G43-2718 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2717 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Refun Tower Liquid Ring Pump | A | 2019-03-14 | IFR | OL1-2G43-2717 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2717 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Rerun Tower Liquid Ring Pump | B | 2019-05-06 | IBD | OL1-2G43-2717 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2716 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Pygas Fuel Oil Product | B | 2019-05-06 | IBD | OL1-2G43-2716 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2716 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Pygas Fuel Oil Product | A | 2019-03-14 | IFR | OL1-2G43-2716 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2715 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Recycle Wash Oil | A | 2019-03-14 | IFR | OL1-2G43-2715 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2715 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Recycle Wash Oil | B | 2019-05-06 | IBD | OL1-2G43-2715 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2713 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Product - Wash Oil Pumps | A | 2019-03-14 | IFR | OL1-2G43-2713 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2713 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Product - Wash Oil Pumps | B | 2019-05-06 | IBD | OL1-2G43-2713 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2712 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU Rerun Tower Reflux-Product Pump | A | 2019-03-14 | IFR | OL1-2G43-2712 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2712 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU Rerun Tower Reflux-Product Pump | B | 2019-05-06 | IBD | OL1-2G43-2712 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2711 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU Rerun Tower Condenser | A | 2019-03-14 | IFR | OL1-2G43-2711 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2711 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU Rerun Tower Condenser | B | 2019-05-06 | IBD | OL1-2G43-2711 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2710 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Rerun Tower | A | 2019-03-14 | IFR | OL1-2G43-2710 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2710 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Rerun Tower | B | 2019-05-06 | IBD | OL1-2G43-2710 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2708 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Depentanizer Overhead | A | 2019-03-14 | IFR | OL1-2G43-2708 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2708 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Depentanizer Overhead | B | 2019-05-06 | IBD | OL1-2G43-2708 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2707 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU C5 Cut Pumps | B | 2019-05-06 | IBD | OL1-2G43-2707 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00066 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2707 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU C5 Cut Pumps | A | 2019-03-14 | IFR | OL1-2G43-2707 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2706 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Depentanizer | B | 2019-05-06 | IBD | OL1-2G43-2706 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00066 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2706 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Depentanizer | A | 2019-03-14 | IFR | OL1-2G43-2706 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2705 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Cold Separator | B | 2019-05-06 | IBD | OL1-2G43-2705 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00066 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2705 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Cold Separator | A | 2019-03-14 | IFR | OL1-2G43-2705 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2704 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Hot Separator | A | 2019-03-14 | IFR | OL1-2G43-2704 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2704 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Hot Separator | B | 2019-05-06 | IBD | OL1-2G43-2704 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00066 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2703 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Reactors - Sheet 2 | B | 2019-05-06 | IBD | OL1-2G43-2703 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00066 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2703 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Reactors - Sheet 2 | A | 2019-03-14 | IFR | OL1-2G43-2703 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2702 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Reactors - Sheet 1 | B | 2019-05-06 | IBD | OL1-2G43-2702 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00066 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1027-PID-0021-2702 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Reactors - Sheet 1 | A | 2019-03-14 | IFR | OL1-2G43-2702 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2701 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Feed Heating | A | 2019-03-14 | IFR | OL1-2G43-2701 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1027-PID-0021-2701 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Feed Heating | B | 2019-05-06 | IBD | OL1-2G43-2701 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00066 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1056-DI-0007-5601 | Area Basis of Design - 56 Waste Water Treatment System | C | 2019-02-19 | IFD | OL1-2G05-5601 | PE | 2019-02-25 | 036909C-JVD-TRN-00920 | 036909C-JVD-TRN-00920, ROC-TPSK-CECO-T-00001 | IFR | 2019-03-12 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-PE-00920 |  | 2019-02-26 | 2
036909C-1056-DI-0007-5601 | Area Basis of Design - 56 Waste Water Treatment System | A | 2018-08-03 | IFA | OL1-2G05-5601 | PE | 2018-08-07 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | 2018-08-08 | 1
036909C-1055-DI-0007-5501 | Area Basis of Design - 55 Flare System | A | 2018-08-09 | IFA | OL1-2G05-5501 | PE | 2018-08-09 | 036909C-JVD-TRN-00016 | 036909C-JVD-TRN-00016, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-23 | 2018-08-29 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00016 |  | 2018-08-10 | 1
036909C-1039-SP-2510-3900 | Mechanical Equipment Data Sheet - NMP Storage Tank | A | 2019-04-19 | IFQ | OL1-2M03-3900 | ME | 2019-04-23 | 036909C-JVD-TRN-01449 | 036909C-JVD-TRN-01449 | IFR | 2019-05-08 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01449 |  | 2019-04-24 | 2
036909C-103S-DW-2052-0001-05 | Electrical SUB-C And FAR-2 - Architectural Elevations | A | 2019-03-15 | IFR | OL1-2K30-0019 | CV | 2019-03-21 | 036909C-JVD-TRN-01122 | 036909C-JVD-TRN-01122, ROC-TPSK-CECO-T-00021 | IFA | 2019-04-05 | 2019-05-30 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01122 |  | 2019-03-22 | 1
036909C-103S-DW-2052-0001-04 | Electrical SUB-C And FAR-2 - Architectural Sections | A | 2019-03-15 | IFR | OL1-2K30-0018 | CV | 2019-03-21 | 036909C-JVD-TRN-01122 | 036909C-JVD-TRN-01122, ROC-TPSK-CECO-T-00021 | IFA | 2019-04-05 | 2019-05-30 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01122 |  | 2019-03-22 | 1
036909C-103S-DW-2052-0001-03 | Electrical SUB-C And FAR-2 - Architectural Roof Floor Plan | A | 2019-03-15 | IFR | OL1-2K30-0017 | CV | 2019-03-21 | 036909C-JVD-TRN-01122 | 036909C-JVD-TRN-01122, ROC-TPSK-CECO-T-00021 | IFA | 2019-04-05 | 2019-05-30 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01122 |  | 2019-03-22 | 1
036909C-103S-DW-2052-0001-02 | Electrical SUB-C And FAR-2 - Architectural First Floor Plan | A | 2019-03-15 | IFR | OL1-2K30-0016 | CV | 2019-03-21 | 036909C-JVD-TRN-01122 | 036909C-JVD-TRN-01122, ROC-TPSK-CECO-T-00021 | IFA | 2019-04-05 | 2019-05-30 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01122 |  | 2019-03-22 | 1
036909C-103S-DW-2052-0001-01 | Electrical SUB-C And FAR-2 - Architectural Ground Floor Plan | A | 2019-03-15 | IFR | OL1-2K30-0015 | CV | 2019-03-21 | 036909C-JVD-TRN-01122 | 036909C-JVD-TRN-01122, ROC-TPSK-CECO-T-00021 | IFA | 2019-04-05 | 2019-05-30 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01122 |  | 2019-03-22 | 1
036909C-1000-PO-036909C001P41-041 | Vendor s Acknowledgment of Purchase Order For Wet Air Oxidation - MR 4100-0001 Rev. 0 | 0 | 2019-06-11 | IFI | OL1-2C51-0103 | PL | 2019-06-11 | 036909C-JVD-TRN-01856 | 036909C-JVD-TRN-01856 | IFI | 2019-06-25 | 2019-06-28 | R1-No comments | TPSK-LSPA1-T-PL-01856 |  | 2019-06-11 | 3
036909C-1023-SP-2510-2320 | Mechanical Equipment Data Sheet For Spent Caustic Storage Tank | B | 2019-08-16 | IFQ | OL1-2M03-2320 | ME | 2019-08-19 | 036909C-JVD-TRN-02453 | 036909C-JVD-TRN-02453 | IFR | 2019-09-03 |  | Transmitted | TPSK-LSPA1-T-ME-02453 |  | 2019-08-21 | 2
036909C-102D-CN-1733-0009 | Calculation Note for Foundation of 10-D-2525 | A | 2019-06-15 | IFR | OL1-2K13-0099 | CV | 2019-06-17 | 036909C-JVD-TRN-01903 | 036909C-JVD-TRN-01903 | IFA | 2019-07-02 | 2019-08-16 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01903 |  | 2019-06-18 | 1
036909C-102B-CN-1733-0034 | Calculation Note For Foundation Of 10-D-2322 | A | 2019-06-07 | IFR | OL1-2K13-0405 | CV | 2019-06-11 | 036909C-JVD-TRN-01857 | 036909C-JVD-TRN-01857 | IFA | 2019-06-26 | 2019-08-16 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01857 |  | 2019-06-11 | 1
036909C-102E-CN-1733-0046 | Calculation Note For Foundation Of 10-T-2300 | A | 2019-06-03 | IFR | OL1-2K13-0036 | CV | 2019-06-11 | 036909C-JVD-TRN-01857 | 036909C-JVD-TRN-01857 | IFA | 2019-06-26 | 2019-08-16 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01857 |  | 2019-06-11 | 1
036909C-1030-PDS-0600-3098 | Process Equipment Datasheet - 10-E-3098 - Butadiene Product Subcooler | A | 2019-03-29 | IFR | OL1-2G30-3098 | PE | 2019-03-29 | 036909C-JVD-TRN-01202 | 036909C-JVD-TRN-01202 | IFR | 2019-04-15 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01202 |  | 2019-04-01 | 2
036909C-1030-PDS-0600-3085 | Process Equipment Datasheet - 10-E-3085 A-B - Butadiene Tower Reboiler | A | 2019-03-29 | IFR | OL1-2G30-3085 | PE | 2019-03-29 | 036909C-JVD-TRN-01202 | 036909C-JVD-TRN-01202 | IFR | 2019-04-15 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01202 |  | 2019-04-01 | 2
036909C-1030-PDS-0600-3084 | Process Equipment Datasheet - 10-E-3084 - Butadiene Tower Trim Reboiler | A | 2019-03-29 | IFR | OL1-2G30-3084 | PE | 2019-03-29 | 036909C-JVD-TRN-01202 | 036909C-JVD-TRN-01202 | IFR | 2019-04-15 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01202 |  | 2019-04-01 | 2
036909C-1030-PDS-0600-3081 | Process Equipment Datasheet - 10-E-3080 A-B - Butadiene Tower Condenser | A | 2019-03-29 | IFR | OL1-2G30-3081 | PE | 2019-03-29 | 036909C-JVD-TRN-01202 | 036909C-JVD-TRN-01202 | IFR | 2019-04-15 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01202 |  | 2019-04-01 | 2
036909C-1030-PDS-0600-3071 | Process Equipment Datasheet - 10-E-3070 - Water - NMP Cooler | A | 2019-03-29 | IFR | OL1-2G30-3071 | PE | 2019-03-29 | 036909C-JVD-TRN-01202 | 036909C-JVD-TRN-01202 | IFR | 2019-04-15 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01202 |  | 2019-04-01 | 2
036909C-1030-PDS-0600-3063 | Process Equipment Datasheet - 10-E-3060 - C4 Acetylene Washer Condenser | A | 2019-03-28 | IFR | OL1-2G30-3063 | PE | 2019-03-29 | 036909C-JVD-TRN-01202 | 036909C-JVD-TRN-01202 | IFR | 2019-04-15 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01202 |  | 2019-04-01 | 2
036909C-1030-PDS-0600-3062 | Process Equipment Datasheet - 10-E-3062 - C4 Acetylene Condenser | A | 2019-03-29 | IFR | OL1-2G30-3062 | PE | 2019-03-29 | 036909C-JVD-TRN-01202 | 036909C-JVD-TRN-01202 | IFR | 2019-04-15 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01202 |  | 2019-04-01 | 2
036909C-1030-PDS-0600-3031 | Process Equipment Datasheet - 10-E-3030 - After Washer Condenser | A | 2019-03-28 | IFR | OL1-2G30-3031 | PE | 2019-04-01 | 036909C-JVD-TRN-01214 | 036909C-JVD-TRN-01214 | IFR | 2019-04-16 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01214 |  | 2019-04-02 | 2
036909C-1030-PDS-0600-3021 | Process Equipment Datasheet - 10-E-3020 - Main Washer Condenser | A | 2019-03-28 | IFR | OL1-2G30-3021 | PE | 2019-04-01 | 036909C-JVD-TRN-01214 | 036909C-JVD-TRN-01214 | IFR | 2019-04-16 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01214 |  | 2019-04-02 | 2
036909C-1030-PDS-0600-3018 | Process Equipment Datasheet - 10-E-3018 A-B - Solvent Cooler | A | 2019-03-29 | IFR | OL1-2G30-3018 | PE | 2019-04-01 | 036909C-JVD-TRN-01214 | 036909C-JVD-TRN-01214 | IFR | 2019-04-16 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01214 |  | 2019-04-02 | 2
036909C-1030-PDS-0600-3015 | Process Equipment Datasheet - 10-E-3015 - C4 Trim Vaporizer | A | 2019-03-28 | IFR | OL1-2G30-3015 | PE | 2019-03-29 | 036909C-JVD-TRN-01202 | 036909C-JVD-TRN-01202 | IFR | 2019-04-15 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01202 |  | 2019-04-01 | 2
036909C-1030-PDS-0600-3014 | Process Equipment Datasheet - 10-E-3014 A-B - C4 Trim Vaporizer | A | 2019-03-18 | IFR | OL1-2G30-3014 | PE | 2019-03-25 | 036909C-JVD-TRN-01148 | 036909C-JVD-TRN-01148 | IFR | 2019-04-09 | 2019-04-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01148 |  | 2019-03-26 | 2
036909C-1030-PDS-0600-3005 | Process Equipment Datasheet - 10-E-3005 - Predistillation Tower Reboiler | A | 2019-03-18 | IFR | OL1-2G30-3005 | PE | 2019-03-25 | 036909C-JVD-TRN-01148 | 036909C-JVD-TRN-01148 | IFR | 2019-04-09 | 2019-04-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01148 |  | 2019-03-26 | 2
036909C-1030-PDS-0600-3004 | Process Equipment Datasheet - 10-E-3004 A-B - Predistillation Tower Trim Reboiler | A | 2019-03-18 | IFR | OL1-2G30-3004 | PE | 2019-03-25 | 036909C-JVD-TRN-01148 | 036909C-JVD-TRN-01148 | IFR | 2019-04-09 | 2019-04-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01148 |  | 2019-03-26 | 2
036909C-1030-PDS-0600-3001 | Process Equipment Datasheet - 10-E-3000 - Predistillation Tower Condenser | A | 2019-03-18 | IFR | OL1-2G30-3001 | PE | 2019-03-25 | 036909C-JVD-TRN-01148 | 036909C-JVD-TRN-01148 | IFR | 2019-04-09 | 2019-04-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01148 |  | 2019-03-26 | 2
036909C-1024-PID-0021-2447 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer Reflux | B | 2019-04-04 | IBD | OL1-2G43-2447 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2447 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - HP Depropanizer Reflux | A | 2018-12-20 | IFR | OL1-2G43-2447 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2446 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer Reflux Chilling | B | 2019-04-04 | IBD | OL1-2G43-2446 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2446 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - HP Depropanizer Reflux Chilling | A | 2018-12-20 | IFR | OL1-2G43-2446 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2444 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - CG Secondary Dehydrator | A | 2018-12-20 | IFR | OL1-2G43-2444 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2444 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - CG Secondary Dehydrator | B | 2019-04-04 | IBD | OL1-2G43-2444 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2442 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Reactor C | B | 2019-04-04 | IBD | OL1-2G43-2442 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2442 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Reactor C | A | 2018-12-20 | IFR | OL1-2G43-2442 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2440 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Reactor B Intercooling | B | 2019-04-04 | IBD | OL1-2G43-2440 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2440 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Reactor B Intercooling | A | 2018-12-20 | IFR | OL1-2G43-2440 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2439 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Reactor B | A | 2018-12-20 | IFR | OL1-2G43-2439 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2439 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Reactor B | B | 2019-04-04 | IBD | OL1-2G43-2439 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2438 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Reactor A Intercooling | B | 2019-04-04 | IBD | OL1-2G43-2438 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2438 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Reactor A Intercooling | A | 2018-12-20 | IFR | OL1-2G43-2438 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2437 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Reactor A | A | 2018-12-20 | IFR | OL1-2G43-2437 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2437 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Reactor A | B | 2019-04-04 | IBD | OL1-2G43-2437 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2435 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Feed Heating | A | 2018-12-20 | IFR | OL1-2G43-2435 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2435 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Feed Heating | B | 2019-04-04 | IBD | OL1-2G43-2435 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2433 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Arsine Guard Removal | A | 2018-12-20 | IFR | OL1-2G43-2433 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2433 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Arsine Guard Removal | B | 2019-04-04 | IBD | OL1-2G43-2433 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2432 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - CG Compressor 5th Stage Aftercooling | B | 2019-04-04 | IBD | OL1-2G43-2432 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2432 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - CG Compressor 5th Stage Aftercooling | A | 2018-12-20 | IFR | OL1-2G43-2432 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2430 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - 5th Stage Cracked Gas Compression | A | 2018-12-20 | IFR | OL1-2G43-2430 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2430 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - 5th Stage Cracked Gas Compression | B | 2019-04-04 | IBD | OL1-2G43-2430 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2428 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - LP Depropanizer Product & Reflux Pumps | A | 2018-12-20 | IFR | OL1-2G43-2428 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2428 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer Product-Reflux Pumps | B | 2019-04-04 | IBD | OL1-2G43-2428 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2427 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - LP Depropanizer Overhead | A | 2018-12-20 | IFR | OL1-2G43-2427 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2427 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer Overhead | B | 2019-04-04 | IBD | OL1-2G43-2427 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2426 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - LP Depropanizer Reboiler | A | 2018-12-20 | IFR | OL1-2G43-2426 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2426 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer Reboiler | B | 2019-04-04 | IBD | OL1-2G43-2426 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2425 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | B | 2019-04-04 | IBD | OL1-2G43-2425 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2425 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - LP Depropanizer | A | 2018-12-20 | IFR | OL1-2G43-2425 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2423 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - HP Depropanizer Reboiler | A | 2018-12-20 | IFR | OL1-2G43-2423 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2423 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer Reboiler | B | 2019-04-04 | IBD | OL1-2G43-2423 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2422 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | B | 2019-04-04 | IBD | OL1-2G43-2422 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2422 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - HP Depropanizer | A | 2018-12-20 | IFR | OL1-2G43-2422 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2420 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer Feed Chilling | B | 2019-04-04 | IBD | OL1-2G43-2420 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2420 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - HP Depropanizer Feed Chilling | A | 2018-12-20 | IFR | OL1-2G43-2420 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2419 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Cracked Gas Mercury Adsorber | A | 2018-12-20 | IFR | OL1-2G43-2419 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2419 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Cracked Gas Mercury Adsorber | B | 2019-04-04 | IBD | OL1-2G43-2419 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2414 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration Gas Cooling | B | 2019-04-04 | IBD | OL1-2G43-2414 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2414 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Regeneration Gas Cooling | A | 2018-12-20 | IFR | OL1-2G43-2414 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2412 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Regeneration Gas Heating | A | 2018-12-20 | IFR | OL1-2G43-2412 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2412 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration Gas Heating | B | 2019-04-04 | IBD | OL1-2G43-2412 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2410 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration - Sheet 2 | B | 2019-04-04 | IBD | OL1-2G43-2410 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2410 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - CG Dehydration - Sheet 2 | A | 2018-12-20 | IFR | OL1-2G43-2410 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2409 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - CG Dehydration - Sheet 1 | A | 2018-12-20 | IFR | OL1-2G43-2409 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2409 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration - Sheet 1 | B | 2019-04-04 | IBD | OL1-2G43-2409 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2407 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Liquid Driers - Sheet 2 | A | 2018-12-20 | IFR | OL1-2G43-2407 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2407 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Liquid Driers - Sheet 2 | B | 2019-04-04 | IBD | OL1-2G43-2407 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2406 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Liquid Driers - Sheet 1 | A | 2018-12-20 | IFR | OL1-2G43-2406 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2406 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Liquid Driers - Sheet 1 | B | 2019-04-04 | IBD | OL1-2G43-2406 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2404 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Liquid Drier Feed Coalescer | A | 2018-12-20 | IFR | OL1-2G43-2404 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2404 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Liquid Drier Feed Coalescer | B | 2019-04-04 | IBD | OL1-2G43-2404 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2402 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Caustic Tower Overhead KO Drum | B | 2019-04-04 | IBD | OL1-2G43-2402 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2402 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Caustic Tower Overhead Ko Drum | A | 2018-12-20 | IFR | OL1-2G43-2402 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1024-PID-0021-2401 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Caustic Tower Overhead Chilling | B | 2019-04-04 | IBD | OL1-2G43-2401 | PE | 2019-04-05 | 036909C-JVD-TRN-01264 | 036909C-JVD-TRN-01264, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01264 |  | 2019-04-08 | 2
036909C-1024-PID-0021-2401 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Caustic Tower Overhead Chilling | A | 2018-12-20 | IFR | OL1-2G43-2401 | PE | 2018-12-27 | 036909C-JVD-TRN-00567 | 036909C-JVD-TRN-00567, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00567 |  | 2018-12-27 | 2
036909C-1059-SP-2510-5900 | Mechanical Equipment Data Sheet - Sulfuric Acid Tank | A | 2019-01-25 | IFQ | OL1-2M03-5900 | ME | 2019-01-29 | 036909C-JVD-TRN-00754 | 036909C-JVD-TRN-00754, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-12 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00754 |  | 2019-01-29 | 2
036909C-1039-SP-0810-3904 | Mechanical Equipment Data Sheet - BDU Product Inhibitor Drum | A | 2019-05-13 | IFQ | OL1-2M03-3904 | ME | 2019-05-13 | 036909C-JVD-TRN-01654 | 036909C-JVD-TRN-01654 | IFR | 2019-05-28 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01654 |  | 2019-05-14 | 2
036909C-1039-SP-0810-3902 | Mechanical Equipment Data Sheet - BDU Solvent Inhibitor Drum | A | 2019-05-10 | IFQ | OL1-2M03-3902 | ME | 2019-05-13 | 036909C-JVD-TRN-01654 | 036909C-JVD-TRN-01654 | IFR | 2019-05-28 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01654 |  | 2019-05-14 | 2
036909C-1039-SP-0810-3906 | Mechanical Equipment Data Sheet - BDU Anti Form Agent Drum | A | 2019-05-10 | IFQ | OL1-2M03-3906 | ME | 2019-05-13 | 036909C-JVD-TRN-01654 | 036909C-JVD-TRN-01654 | IFR | 2019-05-28 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01654 |  | 2019-05-14 | 2
036909C-1031-SP-0810-3180 | Mechanical Equipment Data Sheet - BDU Knock-Out Drum | A | 2019-05-10 | IFQ | OL1-2M03-3180 | ME | 2019-05-13 | 036909C-JVD-TRN-01654 | 036909C-JVD-TRN-01654 | IFR | 2019-05-28 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01654 |  | 2019-05-14 | 2
036909C-1031-SP-0810-3151 | Mechanical Equipment Data Sheet - BDU Condensate Flash Drum | A | 2019-05-10 | IFQ | OL1-2M03-3151 | ME | 2019-05-13 | 036909C-JVD-TRN-01654 | 036909C-JVD-TRN-01654 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-ME-01654 |  | 2019-05-14 | 2
036909C-1030-SP-0810-3003 | Mechanical Equipment Data Sheet - Predistillation Tower Reflux Drum | A | 2019-05-10 | IFQ | OL1-2M03-3003 | ME | 2019-05-10 | 036909C-JVD-TRN-01645 | 036909C-JVD-TRN-01645 | IFR | 2019-05-28 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME -01645 |  | 2019-05-13 | 2
036909C-1023-SP-2510-2320 | Mechanical Equipment Data Sheet - Spent Caustic Storage Tank | A | 2019-01-24 | IFQ | OL1-2M03-2320 | ME | 2019-01-28 | 036909C-JVD-TRN-00745 | 036909C-JVD-TRN-00745, ROC-TPSK-CECO-T-00014 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00745 |  | 2019-01-28 | 2
036909C-1012-PDS-1546-1290 | Process Datasheet for Restriction Orifice Furnace Area 10-H-1200_1600 | A | 2019-05-23 | IFR | OL1-2G31-1290 | PE | 2019-05-30 | 036909C-JVD-TRN-01781 | 036909C-JVD-TRN-01781 | IFR | 2019-06-14 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01781 |  | 2019-05-31 | 2
036909C-1011-PDS-1546-1190 | Process Datasheet for Restriction Orifice Furnace Area 10-H-1100 | A | 2019-05-30 | IFR | OL1-2G31-1190 | PE | 2019-06-07 | 036909C-JVD-TRN-01830 | 036909C-JVD-TRN-01829 | IFR | 2019-06-22 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01830 |  | 2019-06-10 | 2
036909C-1053-DI-0007-5301 | Area Basis of Design - 53 Cooling Tower System | A | 2018-07-25 | IFA | OL1-2G05-5301 | PE | 2018-07-31 | 036909C-JVD-TRN-00003 | 036909C-JVD-TRN-00003 | IFA | 2018-08-13 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00003 |  | 2018-07-31 | 1
036909C-1027-TDS-0610-2721 | Mechanical Equipment Data Sheet - 10-E-2720 - Rerun Tower Condenser | 0 | 2019-07-12 | Issue for Purchase | OL1-2M03-2721 | ME | 2019-07-22 | 036909C-JVD-TRN-02235 | 036909C-JVD-TRN-02235 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02235 |  | 2019-07-23 | 2
036909C-1020-TDS-0610-2026 | Mechanical Equipment Data Sheet - 10-E-2026 - FO Product Cooler | 0 | 2019-07-16 | Issue for Purchase | OL1-2M03-2026 | ME | 2019-07-22 | 036909C-JVD-TRN-02231 | 036909C-JVD-TRN-02231 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02231 |  | 2019-07-23 | 2
036909C-1052-SP-0810-5200 | Mechanical Equipment Data Sheet For Fuel Gas Drum | 0 | 2019-07-05 | IFP | OL1-2M03-5200 | ME | 2019-07-17 | 036909C-JVD-TRN-02177 | 036909C-JVD-TRN-02177 | IFR | 2019-08-01 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02177 |  | 2019-07-17 | 2
036909C-1051-SP-0810-5140 | Mechanical Equipment Data Sheet for Intermittent Blowdown Drum | 0 | 2019-07-05 | IFP | OL1-2M03-5140 | ME | 2019-07-17 | 036909C-JVD-TRN-02177 | 036909C-JVD-TRN-02177 | IFR | 2019-08-01 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02177 |  | 2019-07-17 | 2
036909C-1011-DW-0131-1511 | USC 36M Recycle Furnace Steel Radiant Floor and Radiant Arch Plans | 1 | 2019-06-04 | IMP | OL1-2K32-1511 | CV | 2019-06-12 | 036909C-JVD-TRN-01877 | 036909C-JVD-TRN-01877 | IFI |  | 2019-08-20 | R1-No comments | TPSK-LSPA1-T-CV-01877 |  | 2019-06-14 | 3
036909C-1020-SP-0910-2006 | Mechanical Equipment Data Sheet For Quench Oil Pump | 0 | 2019-07-05 | IFP | OL1-2M03-2006 | ME | 2019-07-08 | 036909C-JVD-TRN-02094 | 036909C-JVD-TRN-02094 | IFR | 2019-07-23 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02094 |  | 2019-07-09 | 2
036909C-1012-DW-0131-2511 | USC 132U Cracking Furnace Steel Radiant Floor And Radiant Arch Plans | 1 | 2019-06-04 | IMP | OL1-2K32-2511 | CV | 2019-06-12 | 036909C-JVD-TRN-01877 | 036909C-JVD-TRN-01877 | IFI |  | 2019-08-20 | R1-No comments | TPSK-LSPA1-T-CV-01877 |  | 2019-06-14 | 3
036909C-102E-NM-1350-0041 | Loads On Structures 10-STR-2E01-2E | A | 2019-07-29 | IBD | OL1-2P05-0153 | MP | 2019-08-02 | 036909C-JVD-TRN-02322 | 036909C-JVD-TRN-02322 | IFR | 2019-08-19 | 2019-08-13 | R1-No comments | TPSK-LSPA1-T-MP-02322 |  | 2019-08-05 | 2
036909C-102D-NM-1350-0030 | Loads On Rack 10-PRK-2D01 | A | 2019-07-12 | IBD | OL1-2P05-0131 | MP | 2019-08-02 | 036909C-JVD-TRN-02322 | 036909C-JVD-TRN-02322 | IFR | 2019-08-19 | 2019-08-13 | R1-No comments | TPSK-LSPA1-T-MP-02322 |  | 2019-08-05 | 2
036909C-102C-NM-1350-0043 | Loads On Structures 10-STR-2C03-2C | A | 2019-07-29 | IBD | OL1-2P05-0113 | MP | 2019-08-02 | 036909C-JVD-TRN-02322 | 036909C-JVD-TRN-02322 | IFR | 2019-08-19 | 2019-08-13 | R1-No comments | TPSK-LSPA1-T-MP-02322 |  | 2019-08-05 | 2
036909C-102C-NM-1350-0041 | Loads On structures 10-STR-2C01-2C | A | 2019-07-29 | IDB | OL1-2P05-0112 | MP | 2019-08-02 | 036909C-JVD-TRN-02322 | 036909C-JVD-TRN-02322 | IFR | 2019-08-19 | 2019-08-13 | R1-No comments | TPSK-LSPA1-T-MP-02322 |  | 2019-08-05 | 2
036909C-102A-NM-1350-0042 | Loads On Structure 10-STR-2A02 | A | 2019-07-29 | IBD | OL1-2P05-0073 | MP | 2019-08-02 | 036909C-JVD-TRN-02322 | 036909C-JVD-TRN-02322 | IFR | 2019-08-19 | 2019-08-13 | R1-No comments | TPSK-LSPA1-T-MP-02322 |  | 2019-08-05 | 2
036909C-1020-SP-0910-2006 | Mechanical Equipment Data Sheet Quench Oil Pump 10-P-2006 A-B-C | A | 2018-10-25 | IFQ | OL1-2M03-2006 | ME | 2018-10-26 | 036909C-JVD-TRN-00235 | 036909C-JVD-TRN-00235 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00235 |  | 2018-10-26 | 2
036909C-1020-SP-0910-2006 | Mechanical Equipment Data Sheet - Quench Oil Pump | C | 2019-03-26 | IFQ | OL1-2M03-2006 | ME | 2019-03-27 | 036909C-JVD-TRN-01173 | 036909C-JVD-TRN-01173 | IFR | 2019-04-11 | 2019-04-22 | R1-No comments | TPSK-LSPA1-T-ME-01173 |  | 2019-03-28 | 2
036909C-1029-SP-2510-2910 | Mechanical Equipment Data Sheet - Wash Oil Day Tank | B | 2019-04-19 | IFQ | OL1-2M03-2910 | ME | 2019-04-23 | 036909C-JVD-TRN-01449 | 036909C-JVD-TRN-01449 | IFR | 2019-05-08 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01449 |  | 2019-04-23 | 2
036909C-1029-SP-2510-2910 | Mechanical Equipment Data Sheet - Wash Oil Day Tank | A | 2019-01-24 | IFQ | OL1-2M03-2910 | ME | 2019-01-28 | 036909C-JVD-TRN-00745 | 036909C-JVD-TRN-00745, ROC-TPSK-CECO-T-00015 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00745 |  | 2019-01-28 | 2
036909C-1023-SP-2510-2324 | Mechanical Equipment Data Sheet - Fresh Caustic Day Tank | A | 2019-01-24 | IFQ | OL1-2M03-2324 | ME | 2019-01-28 | 036909C-JVD-TRN-00745 | 036909C-JVD-TRN-00745, ROC-TPSK-CECO-T-00014 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00745 |  | 2019-01-28 | 2
036909C-1011-PDS-1390-1104 | Piping Specialty Item – Datasheet Vent Silencer – PSV-1142A-B Outlet SP-11004 | B | 2019-07-15 | IFD | OL1-2P03-1104 | MP | 2019-07-16 | 036909C-JVD-TRN-02162 | 036909C-JVD-TRN-02162 | IFR | 2019-07-31 | 2019-08-16 | R1-No comments | TPSK-LSPA1-T-MP-02162 |  | 2019-07-17 | 2
036909C-1056-SP-0910-5648 | MECHANICAL EQUIPMENT DATASHEET - C3 Hydrog Area Oily Wastewater Pump | 0 | 2019-08-09 | IFP | OL1-2M03-5648 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1056-SP-0910-5635 | MECHANICAL EQUIPMENT DATASHEET - CT Area Oily Wastewater Sump Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-5635 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1056-SP-0910-5636 | MECHANICAL EQUIPMENT DATASHEET - CWWT Area Oily Wastewater Sump Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-5636 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1056-SP-0910-5624 | Mechanical Equipment Datasheet for Gate 4 Septic Tank Pumps | 0 | 2019-08-13 | CAN | OL1-2M03-5624 | ME | 2019-08-14 | 036909C-JVD-TRN-02435 | 036909C-JVD-TRN-02435 | CAN |  |  | Transmitted | TPSK-LSPA1-T-ME-02435 |  | 2019-08-15 | 2
036909C-1056-SP-0910-5608 | MECHANICAL EQUIPMENT DATASHEET - QW Area Oily Wastewater Pump | 0 | 2019-08-09 | IFP | OL1-2M03-5608 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1056-SP-0910-5623 | Mechanical Equipment Datasheet for FAR C Septic Tank Pumps | 0 | 2019-08-13 | CAN | OL1-2M03-5623 | ME | 2019-08-14 | 036909C-JVD-TRN-02435 | 036909C-JVD-TRN-02435 | CAN |  |  | Transmitted | TPSK-LSPA1-T-ME-02435 |  | 2019-08-15 | 2
036909C-1056-SP-0910-5613 | MECHANICAL EQUIPMENT DATASHEET - Refrig Area Oily Wastewater Pump | 0 | 2019-08-09 | IFP | OL1-2M03-5613 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1056-SP-0910-5609 | MECHANICAL EQUIPMENT DATASHEET - CGC Area Oily Wastewater Pump | 0 | 2019-08-09 | IFP | OL1-2M03-5609 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1056-SP-0910-5607 | MECHANICAL EQUIPMENT DATASHEET - Butadiene Area Oily Wastewater Pump | 0 | 2019-08-09 | IFP | OL1-2M03-5607 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1056-SP-0910-5606 | MECHANICAL EQUIPMENT DATASHEET - Pygas Area Oily Wastewater Pump | 0 | 2019-08-09 | IFP | OL1-2M03-5606 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1055-SP-0910-5501 | MECHANICAL EQUIPMENT DATASHEET - Hot Blowdown Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-5501 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1051-SP-0910-5121 | MECHANICAL EQUIPMENT DATASHEET - Raw Condensate Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-5121 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1051-SP-0910-5111 | MECHANICAL EQUIPMENT DATASHEET - Suspect Condensate Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-5111 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1051-SP-0910-5141 | MECHANICAL EQUIPMENT DATASHEET - Intermittent Blowdown Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-5141 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1039-PDS-1546-3990 | Process Datasheet for Restriction Orifice Unit 39 | A | 2019-08-14 | IFR | OL1-2G31-3990 | PE | 2019-08-14 | 036909C-JVD-TRN-02436 | 036909C-JVD-TRN-02436 | IFR | 2019-08-29 |  | Transmitted | TPSK-LSPA1-T-PE-02436 |  | 2019-08-15 | 2
036909C-1031-PDS-1390-3125 | Piping Specialty Item - Datasheet - Y-Type Filter - PK-3120 MP Steam Inlet - SRY-31007 | A | 2019-08-09 | IFR | OL1-2P03-3125 | MP | 2019-08-12 | 036909C-JVD-TRN-02415 | 036909C-JVD-TRN-02415 | IFR | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-MP-02415 |  | 2019-08-14 | 2
036909C-1039-PDS-1390-3905 | Piping Specialty Item - Datasheet - Y-Type Filter - P-3904 A-B Suction - SRY-39004 | A | 2019-08-09 | IFR | OL1-2P03-3905 | MP | 2019-08-12 | 036909C-JVD-TRN-02419 | 036909C-JVD-TRN-02419 | IFR | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-MP-02419 |  | 2019-08-14 | 2
036909C-1039-PDS-1390-3903 | Piping Specialty Item - Datasheet - Y-Type Filter - P-3906 A-B - Suction - SRY-39002 | A | 2019-08-09 | IFR | OL1-2P03-3903 | MP | 2019-08-12 | 036909C-JVD-TRN-02419 | 036909C-JVD-TRN-02419 | IFR | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-MP-02419 |  | 2019-08-14 | 2
036909C-1039-PDS-1390-3904 | Piping Specialty Item - Datasheet - Y-Type Filter - P-3908 A-B Suction - SRY-39003 | A | 2019-08-09 | IFR | OL1-2P03-3904 | MP | 2019-08-12 | 036909C-JVD-TRN-02419 | 036909C-JVD-TRN-02419 | IFR | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-MP-02419 |  | 2019-08-14 | 2
036909C-1039-PDS-1390-3902 | Piping Specialty Item - Datasheet - Y-Type Filter - P-3902 A-B Suction - SRY-39001 | A | 2019-08-09 | IFR | OL1-2P03-3902 | MP | 2019-08-12 | 036909C-JVD-TRN-02419 | 036909C-JVD-TRN-02419 | IFR | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-MP-02419 |  | 2019-08-14 | 2
036909C-1031-PDS-1546-3190 | Process Datasheet for Restriction Orifice Unit 31 | A | 2019-08-14 | IFR | OL1-2G31-3190 | PE | 2019-08-14 | 036909C-JVD-TRN-02436 | 036909C-JVD-TRN-02436 | IFR | 2019-08-29 |  | Transmitted | TPSK-LSPA1-T-PE-02436 |  | 2019-08-15 | 2
036909C-1030-PDS-1546-3090 | Process Datasheet for Restriction Orifice Unit 30 | A | 2019-08-13 | IFR | OL1-2G31-3090 | PE | 2019-08-14 | 036909C-JVD-TRN-02436 | 036909C-JVD-TRN-02436 | IFR | 2019-08-29 |  | Transmitted | TPSK-LSPA1-T-PE-02436 |  | 2019-08-15 | 2
036909C-102B-DW-1842-0003-002 | Steel For Structure 10-STR-2B03 | A | 2019-07-30 | IFR | OL1-2K32-8261 | CV | 2019-08-13 | 036909C-JVD-TRN-02423 | 036909C-JVD-TRN-02423 | IFA | 2019-08-28 |  | Transmitted | TPSK-LSPA1-T-CV-02423 |  | 2019-08-15 | 1
036909C-102B-DW-1842-0003-001 | Steel For Structure 10-STR-2B03 | A | 2019-07-30 | IFR | OL1-2K32-8260 | CV | 2019-08-13 | 036909C-JVD-TRN-02423 | 036909C-JVD-TRN-02423 | IFA | 2019-08-28 |  | Transmitted | TPSK-LSPA1-T-CV-02423 |  | 2019-08-15 | 1
036909C-102B-DW-1743-0034 | Foundation For 10-TK-2320 | A | 2019-07-30 | IFR | OL1-2K31-0201 | CV | 2019-08-12 | 036909C-JVD-TRN-02409 | 036909C-JVD-TRN-02409 | IFA | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-CV-02409 |  | 2019-08-14 | 1
036909C-102B-CN-1733-0017 | Calculation Note For Foundation Of 10-F-2310A-B | A | 2019-08-09 | IFR | OL1-2K13-0075 | CV | 2019-08-12 | 036909C-JVD-TRN-02410 | 036909C-JVD-TRN-02410 | IFA | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-CV-02410 |  | 2019-08-14 | 1
036909C-102B-CN-1733-0016 | Calculation Note For Foundation Of 10-F-2320A-B | A | 2019-08-09 | IFR | OL1-2K13-0074 | CV | 2019-08-12 | 036909C-JVD-TRN-02410 | 036909C-JVD-TRN-02410 | IFA | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-CV-02410 |  | 2019-08-14 | 1
036909C-102B-CN-1732-0003 | Calculation Note for Foundation and Elevation of 10-STR-2B03 | A | 2019-07-30 | IFR | OL1-2K14-0018 | CV | 2019-08-13 | 036909C-JVD-TRN-02425 | 036909C-JVD-TRN-02426, 036909C-JVD-TRN-02425 | IFA | 2019-08-28 |  | Transmitted | TPSK-LSPA1-T-CV-02425 |  | 2019-08-15 | 1
036909C-1028-SP-0910-2816 | MECHANICAL EQUIPMENT DATASHEET - PROPYLENE REFRIG RECOVERY PUMP | 0 | 2019-08-09 | IFP | OL1-2M03-2816 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1028-SP-0910-2801 | MECHANICAL EQUIPMENT DATASHEET - Propylene Product Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2801 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1028-SP-0910-2855 | MECHANICAL EQUIPMENT DATASHEET - Ethylene Product Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2855 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1027-SP-0910-2713 | MECHANICAL EQUIPMENT DATASHEET - Depentanizer Reflux Pump | 0 | 2019-08-09 | IFP | OL1-2M03-2713 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1027-SP-0910-2714 | MECHANICAL EQUIPMENT DATASHEET - C5 Cut Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2714 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1027-SP-0910-2764 | MECHANICAL EQUIPMENT DATASHEET - C4-C5 Hydrog Recycle Pump | 0 | 2019-08-09 | IFP | OL1-2M03-2764 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1027-SP-0910-2791 | MECHANICAL EQUIPMENT DATASHEET - Light Oil Drain Drum Pump | 0 | 2019-08-09 | IFP | OL1-2M03-2791 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1027-SP-0910-2728 | MECHANICAL EQUIPMENT DATASHEET - Recycle Wash Oil Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2728 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1027-SP-0910-2719 | MECHANICAL EQUIPMENT DATASHEET - Return Tower Reflux-Product Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2719 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1027-SP-0910-2726 | MECHANICAL EQUIPMENT DATASHEET - Pygas Fuel Oil Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2726 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1026-SP-0910-2647 | MECHANICAL EQUIPMENT DATASHEET - HP Propylene -Off Spec Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2647 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1026-SP-0910-2623 | MECHANICAL EQUIPMENT DATASHEET - C3 Hydrog Recycle Pump | 0 | 2019-08-09 | IFP | OL1-2M03-2623 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1026-SP-0910-2663 | MECHANICAL EQUIPMENT DATASHEET - Debutanizer Reflux-Product Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2663 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1026-SP-0910-2668 | MECHANICAL EQUIPMENT DATASHEET - C5-Pygas Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2668 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1026-SP-0910-2646 | MECHANICAL EQUIPMENT DATASHEET - Propane Recycle Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2646 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1027-SP-0910-2704 | MECHANICAL EQUIPMENT DATASHEET - GHU-1 Recycle Pump | 0 | 2019-08-09 | IFP | OL1-2M03-2704 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1027-PDS-1390-2710 | SP Item Datasheet - Desuperheater - HP Steam to E-2715 A-B & E-2725 A-C - SP-27010 | A | 2019-08-11 | IFR | OL1-2P03-2710 | MP | 2019-08-12 | 036909C-JVD-TRN-02419 | 036909C-JVD-TRN-02419 | IFR | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-MP-02419 |  | 2019-08-14 | 2
036909C-1025-SP-0910-2573 | MECHANICAL EQUIPMENT DATASHEET - Deethanizer Reflux Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2573 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1025-SP-0910-2577 | MECHANICAL EQUIPMENT DATASHEET - Deethanizer Reboiler Cond Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2577 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1025-SP-0910-2586 | MECHANICAL EQUIPMENT DATASHEET - Ethane Recycle Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2586 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1023-DI-0007-2301 | Area Basis of Design - 23 Caustic and Spent Caustic Pretreatment | C | 2019-08-13 | IFD | OL1-2G05-2301 | PE | 2019-08-13 | 036909C-JVD-TRN-02431 | 036909C-JVD-TRN-02431 | IFA | 2019-08-28 |  | Transmitted | TPSK-LSPA1-T-PE-02431 |  | 2019-08-15 | 1
036909C-1024-SP-0910-2457 | MECHANICAL EQUIPMENT DATASHEET - LP Deprop Reboiler Cond Pump | 0 | 2019-08-09 | IFP | OL1-2M03-2457 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1022-SP-0910-2222 | MECHANICAL EQUIPMENT DATASHEET - CG 2nd Stage Condensed HC Pump | 0 | 2019-08-09 | IFP | OL1-2M03-2222 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1021-SP-0910-2105 | MECHANICAL EQUIPMENT DATASHEET - Quench Oil Reflux Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2105 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2970 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - C2R Compressor Auxiliaries - Sheet 1 | B | 2019-04-16 | IBD | OL1-2G43-2970 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2970 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C2R Compressor Auxiliaries - Sheet 1 | A | 2019-01-30 | IFR | OL1-2G43-2970 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2976 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - C2R Lube Oil Pump Turbine Details | B | 2019-04-16 | IBD | OL1-2G43-2976 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2976 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C2R Lube Oil Pump Turbine Details | A | 2019-01-30 | IFR | OL1-2G43-2976 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2975 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - C2R Compressor Auxiliaries Details - Sheet 2 | B | 2019-04-16 | IBD | OL1-2G43-2975 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2975 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C2R Compressor Auxiliaries Details - Sheet 2 | A | 2019-01-30 | IFR | OL1-2G43-2975 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2909 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Methanol Injection System | A | 2019-01-30 | IFR | OL1-2G43-2909 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2909 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Methanol Injection System | B | 2019-04-16 | IBD | OL1-2G43-2909 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2907 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Caustic Tower Anti Foulant Injection System | A | 2019-01-30 | IFR | OL1-2G43-2907 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2907 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Caustic Tower Anti Foulant Injection System | B | 2019-04-16 | IBD | OL1-2G43-2907 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2906 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C4 Polymer Inhibitor Injection Package | A | 2019-01-30 | IFR | OL1-2G43-2906 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2906 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - C4 Polymer Inhibitor Injection Package | B | 2019-04-16 | IBD | OL1-2G43-2906 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2905 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Polymerization Inhibitor Injection | A | 2019-01-30 | IFR | OL1-2G43-2905 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2905 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Polymerization Inhibitor Injection | B | 2019-04-16 | IBD | OL1-2G43-2905 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2904 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - DSG Anti Foulant Injection Package | A | 2019-01-30 | IFR | OL1-2G43-2904 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2904 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - DSG Anti Foulant Injection Package | B | 2019-04-16 | IBD | OL1-2G43-2904 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2903 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Process Water Stripping Chemical Injection Pkg | A | 2019-01-30 | IFR | OL1-2G43-2903 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2903 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Process Water Stripping Chemical Injection Pkg. | B | 2019-04-16 | IBD | OL1-2G43-2903 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2902 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Emulsion Breaker Injection System | A | 2019-01-30 | IFR | OL1-2G43-2902 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2902 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Emulsion Breaker Injection System | B | 2019-04-16 | IBD | OL1-2G43-2902 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2901 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - pH Control - Corrosion Injection System | A | 2019-01-30 | IFR | OL1-2G43-2901 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2901 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - PH Control - Corrosion Injection System | B | 2019-04-16 | IBD | OL1-2G43-2901 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1019-PID-0021-1915 | P&ID - Olefins Unit 10 - Furnace Auxiliaries - Decoke Air Receiver | A | 2018-12-20 | IFR | OL1-2G43-1915 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1019-PID-0021-1915 | P&ID - Olefins Unit 10 - Furnace Auxiliaries - Decoke Air Compressor | B | 2019-03-26 | IBD | OL1-2G43-1915 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1019-PID-0021-1901 | P&ID - Olefins Unit 10 - Furnace Auxiliaries - DMDS Injection System | B | 2019-03-26 | IBD | OL1-2G43-1901 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1019-PID-0021-1901 | P&ID - Olefins Unit 10 - Furnace Auxiliaries - Dmds Injection System | A | 2018-12-20 | IFR | OL1-2G43-1901 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1012-PID-0021-1235 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas | B | 2019-02-12 | IBD | OL1-2G43-1235 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1235 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas | A | 2018-11-15 | IFR | OL1-2G43-1235 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1226 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Furnace Effluent & Decoke MOV's | A | 2018-11-15 | IFR | OL1-2G43-1226 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1226 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Furnace Effluent & Decoke MOV'S | B | 2019-02-12 | IBD | OL1-2G43-1226 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1212 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1212 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1212 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 6 | B | 2019-02-12 | IBD | OL1-2G43-1212 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1211 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 5 | B | 2019-02-12 | IBD | OL1-2G43-1211 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1211 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1211 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1210 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1210 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1210 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 4 | B | 2019-02-12 | IBD | OL1-2G43-1210 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1209 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 3 | B | 2019-02-12 | IBD | OL1-2G43-1209 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1209 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1209 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1208 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 2 | B | 2019-02-12 | IBD | OL1-2G43-1208 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1208 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1208 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1207 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1207 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1207 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 1 | B | 2019-02-12 | IBD | OL1-2G43-1207 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1206 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Decoke Air Header Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1206 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1206 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Decoke Air Header Distribution Header | B | 2019-02-12 | IBD | OL1-2G43-1206 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1205 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Dilution Steam Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1205 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1205 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Dilution Steam Distribution Header | B | 2019-02-12 | IBD | OL1-2G43-1205 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1202 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Liquid Feed Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1202 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1202 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Liquid Feed Distribution Header | B | 2019-02-12 | IBD | OL1-2G43-1202 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1108 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1108 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1108 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 2 | B | 2019-02-12 | IBD | OL1-2G43-1108 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1109 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1109 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1109 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 3 | B | 2019-02-12 | IBD | OL1-2G43-1109 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1110 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 4 | B | 2019-02-12 | IBD | OL1-2G43-1110 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1110 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed-Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1110 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1111 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1111 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1111 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 5 | B | 2019-02-12 | IBD | OL1-2G43-1111 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1112 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 6 | B | 2019-02-12 | IBD | OL1-2G43-1112 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1112 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1112 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1126 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Furnace Effluent And Decoke MOVs | A | 2018-11-15 | IFR | OL1-2G43-1126 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1126 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Furnace Effluent & Decoke MOV'S | B | 2019-02-12 | IBD | OL1-2G43-1126 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1135 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Fuel Gas | A | 2018-11-15 | IFR | OL1-2G43-1135 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1135 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Fuel Gas | B | 2019-02-12 | IBD | OL1-2G43-1135 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1201 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - C3 LPG Feed Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1201 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1201 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - C3 LPG Feed Distribution Header | B | 2019-02-12 | IBD | OL1-2G43-1201 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1010-PID-0021-1004 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - LPG Superheater | B | 2019-03-26 | IBD | OL1-2G43-1004 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1010-PID-0021-1004 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - LPG Superheater | A | 2018-12-20 | IFR | OL1-2G43-1004 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1010-PID-0021-1003 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - LPG Drum & LPG Vaporizer | B | 2019-03-26 | IBD | OL1-2G43-1003 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1010-PID-0021-1003 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - LPG Drum & LPG Vaporizer | A | 2018-12-20 | IFR | OL1-2G43-1003 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1010-PID-0021-1002 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - LPG Feed Heater | A | 2018-12-20 | IFR | OL1-2G43-1002 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1010-PID-0021-1002 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - LPG Feed Heater | B | 2019-03-26 | IBD | OL1-2G43-1002 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1010-PID-0021-1001 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - Liquid Feed Heater | A | 2018-12-20 | IFR | OL1-2G43-1001 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1010-PID-0021-1001 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Liquid Feed Heater | B | 2019-03-26 | IBD | OL1-2G43-1001 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1056-SP-0910-5648 | Mechanical Equipment Datasheet - C3 Hydrog Area Oily Wastewater Pump | A | 2019-01-18 | IFQ | OL1-2M03-5648 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716 |  | 2019-01-24 | 2
036909C-1056-SP-0910-5645 | Mechanical Equipment Datasheet - Oily Wastewater EQ Tank Pumps | A | 2019-04-05 | IFQ | OL1-2M03-5645 | ME | 2019-04-09 | 036909C-JVD-TRN-01292 | 036909C-JVD-TRN-01292 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-ME-01292 |  | 2019-04-10 | 2
036909C-1056-SP-0910-5641 | Mechanical Equipment Datasheet - Wastewater EQ Tank Skimmed Oil Pump | A | 2019-04-05 | IFQ | OL1-2M03-5641 | ME | 2019-04-09 | 036909C-JVD-TRN-01292 | 036909C-JVD-TRN-01292 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-ME-01292 |  | 2019-04-10 | 2
036909C-1056-SP-0910-5636 | Mechanical Equipment Datasheet - CWWT Area Oily Wastewater Sump Pumps | A | 2019-02-06 | IFQ | OL1-2M03-5636 | ME | 2019-02-07 | 036909C-JVD-TRN-00817 | 036909C-JVD-TRN-00817, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00817 |  | 2019-02-07 | 2
036909C-1056-SP-0910-5635 | Mechanical Equipment Datasheet - CT Area Oily Wastewater Sump Pumps | A | 2019-02-06 | IFQ | OL1-2M03-5635 | ME | 2019-02-07 | 036909C-JVD-TRN-00817 | 036909C-JVD-TRN-00817, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00817 |  | 2019-02-07 | 2
036909C-1056-SP-0910-5613 | Mechanical Equipment Datasheet - Refrig Area Oily Wastewater Pump | A | 2019-01-18 | IFQ | OL1-2M03-5613 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716 |  | 2019-01-24 | 2
036909C-1056-SP-0910-5609 | Mechanical Equipment Datasheet - CGC Area Oily Wastewater Pump | A | 2019-01-18 | IFQ | OL1-2M03-5609 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716 |  | 2019-01-24 | 2
036909C-1029-PID-0021-2965 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - C3R Compressor Lube Oil Pump Turbine Details | B | 2019-04-16 | IBD | OL1-2G43-2965 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2965 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C3R Compressor Lube Oil Pump Turbine Details | A | 2019-01-30 | IFR | OL1-2G43-2965 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2960 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - C3R Refrig Compressor Turbine Details - Sheet 2 | B | 2019-04-16 | IBD | OL1-2G43-2960 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2960 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C3R Refrig Compressor Turbine Details - Sheet 2 | A | 2019-01-30 | IFR | OL1-2G43-2960 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2955 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C3 Refrig Compressor Turbine Details - Sheet 1 | A | 2019-01-30 | IFR | OL1-2G43-2955 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2955 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - C3 Refrig Compressor Turbine Details - Sheet 1 | B | 2019-04-16 | IBD | OL1-2G43-2955 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2934 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - CGC Lube Oil Pump Turbine Details | A | 2019-01-30 | IFR | OL1-2G43-2934 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2934 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - CGC Lube Oil Pump Turbine Details | B | 2019-04-16 | IBD | OL1-2G43-2934 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2932 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - CG Compressor Auxiliaries - Sheet 2 | B | 2019-04-16 | IBD | OL1-2G43-2932 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2932 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - CG Compressor Auxiliaries - Sheet 2 | A | 2019-01-30 | IFR | OL1-2G43-2932 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2924 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - DSG Feed Pump Turbine Details | B | 2019-04-16 | IBD | OL1-2G43-2924 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2924 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - DSG Feed Pump Turbine Details | A | 2019-01-30 | IFR | OL1-2G43-2924 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2922 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Quench Water Pump Turbine Details | B | 2019-04-16 | IBD | OL1-2G43-2922 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2922 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Quench Water Pump Turbine Details | A | 2019-01-30 | IFR | OL1-2G43-2922 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2920 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Quench Oil Pump Turbine Details | B | 2019-04-16 | IBD | OL1-2G43-2920 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2915 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Wash Oil Storage | B | 2019-04-16 | IBD | OL1-2G43-2915 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1029-PID-0021-2915 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Wash Oil Storage | A | 2019-01-30 | IFR | OL1-2G43-2915 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1056-SP-0910-5608 | Mechanical Equipment Datasheet - QW Area Oily Wastewater Pump | A | 2019-01-18 | IFQ | OL1-2M03-5608 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716 |  | 2019-01-24 | 2
036909C-1056-SP-0910-5607 | Mechanical Equipment Datasheet - Butadiene Area Oily Wastewater Pump | A | 2019-01-18 | IFQ | OL1-2M03-5607 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716 |  | 2019-01-24 | 2
036909C-1056-SP-0910-5606 | Mechanical Equipment Datasheet - Pygas Area Oily Wastewater Pumps | B | 2019-03-26 | IFQ | OL1-2M03-5606 | ME | 2019-04-08 | 036909C-JVD-TRN-01279 | 036909C-JVD-TRN-01279 | IFR | 2019-04-23 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-ME-01279 |  | 2019-04-09 | 2
036909C-1056-SP-0910-5606 | Mechanical Equipment Datasheet - Pygas Area Oily Wastewater Pumps | A | 2019-02-06 | IFQ | OL1-2M03-5606 | ME | 2019-02-07 | 036909C-JVD-TRN-00817 | 036909C-JVD-TRN-00817, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00817 |  | 2019-02-07 | 2
036909C-1055-SP-0910-5566 | Mechanical Equipment Datasheet - Polyolefins Flare Knock-Out Pumps | A | 2019-01-14 | IFQ | OL1-2M03-5566 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716 |  | 2019-01-24 | 2
036909C-1055-SP-0910-5551 | Mechanical Equipment Datasheet - HP Flare Knock-Out Pumps | A | 2019-01-08 | IFQ | OL1-2M03-5551 | ME | 2019-01-10 | 036909C-JVD-TRN-00616 | 036909C-JVD-TRN-00616, ROC-TPSK-CECO-T-00016 | IFR | 2019-01-23 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-ME-00616 |  | 2019-01-10 | 2
036909C-1055-SP-0910-5551 | Mechanical Equipment Datasheet - HP Flare Knock-Out Pumps | B | 2019-04-25 | IFQ | OL1-2M03-5551 | ME | 2019-04-30 | 036909C-JVD-TRN-01524 | 036909C-JVD-TRN-01524 | IFR | 2019-05-15 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01524 |  | 2019-05-02 | 2
036909C-1055-SP-0910-5501 | Mechanical Equipment Datasheet - Hot Blowdown Pumps | A | 2019-01-08 | IFQ | OL1-2M03-5501 | ME | 2019-01-10 | 036909C-JVD-TRN-00616 | 036909C-JVD-TRN-00616 | IFR | 2019-01-23 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00616 |  | 2019-01-10 | 2
036909C-1055-SP-0910-5501 | Mechanical Equipment Datasheet - Hot Blowdown Pumps | C | 2019-03-13 | IFQ | OL1-2M03-5501 | ME | 2019-03-20 | 036909C-JVD-TRN-01102 | 036909C-JVD-TRN-01102, ROC-TPSK-CECO-T-00016 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-ME-01102 |  | 2019-03-21 | 2
036909C-1051-SP-0910-5121 | Mechanical Equipment Datasheet - Raw Condensate Pumps | A | 2018-11-20 | IFQ | OL1-2M03-5121 | ME | 2018-11-20 | 036909C-JVD-TRN-00341 | 036909C-JVD-TRN-00341 | IFR | 2018-12-04 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-ME-00341 |  | 2018-11-20 | 2
036909C-1051-SP-0910-5111 | Mechanical Equipment Datasheet - Suspect Condensate Pumps | A | 2018-11-20 | IFQ | OL1-2M03-5111 | ME | 2018-11-20 | 036909C-JVD-TRN-00341 | 036909C-JVD-TRN-00341 | IFR | 2018-12-04 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-ME-00341 |  | 2018-11-20 | 2
036909C-1028-SP-0910-2855 | Mechanical Equipment Datasheet - Ethylene Product Pumps | A | 2018-12-05 | IFQ | OL1-2M03-2855 | ME | 2018-12-13 | 036909C-JVD-TRN-00494 | 036909C-JVD-TRN-00494 | IFR | 2018-12-26 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00494 |  | 2018-12-13 | 2
036909C-1028-SP-0910-2816 | Mechanical Equipment Datasheet - Propylene Refrig Recovery Pump | A | 2018-12-18 | IFQ | OL1-2M03-2816 | ME | 2018-12-20 | 036909C-JVD-TRN-00543 | 036909C-JVD-TRN-00543 | IFR | 2019-01-02 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-ME-00543 |  | 2018-12-20 | 2
036909C-1028-SP-0910-2801 | Mechanical Equipment Datasheet - Propylene Product Pumps | A | 2018-12-18 | IFQ | OL1-2M03-2801 | ME | 2018-12-20 | 036909C-JVD-TRN-00543 | 036909C-JVD-TRN-00543 | IFR | 2019-01-02 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-ME-00543 |  | 2018-12-20 | 2
036909C-1027-SP-0910-2791 | Mechanical Equipment Datasheet - Light Oil Drain Drum Pump | A | 2018-12-13 | IFQ | OL1-2M03-2791 | ME | 2018-12-17 | 036909C-JVD-TRN-00515 | 036909C-JVD-TRN-00515, ROC-TPSK-CECO-T-00015 | IFR | 2018-12-31 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00515 |  | 2018-12-17 | 2
036909C-1027-SP-0910-2764 | Mechanical Equipment Datasheet - C4-C5 Hydrog Recycle Pump | B | 2019-03-18 | IFQ | OL1-2M03-2764 | ME | 2019-03-20 | 036909C-JVD-TRN-01102 | 036909C-JVD-TRN-01102, ROC-TPSK-CECO-T-00015 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-ME-01102 |  | 2019-03-21 | 2
036909C-1027-SP-0910-2764 | Mechanical Equipment Datasheet - C4-C5 Hydrog Recycle Pump | C | 2019-06-07 | IFQ | OL1-2M03-2764 | ME | 2019-06-12 | 036909C-JVD-TRN-01880 | 036909C-JVD-TRN-01880 | IFR | 2019-06-27 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-01880 |  | 2019-06-14 | 2
036909C-1027-SP-0910-2764 | Mechanical Equipment Datasheet - C4-C5 Hydrog Recycle Pump | A | 2019-02-06 | IFQ | OL1-2M03-2764 | ME | 2019-02-07 | 036909C-JVD-TRN-00817 | 036909C-JVD-TRN-00817 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00817 |  | 2019-02-07 | 2
036909C-1027-SP-0910-2728 | Mechanical Equipment Datasheet - Recycle Wash Oil Pumps | A | 2019-02-13 | IFQ | OL1-2M03-2728 | ME | 2019-02-19 | 036909C-JVD-TRN-00891 | 036909C-JVD-TRN-00891, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-06 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00891 |  | 2019-02-19 | 2
036909C-1027-SP-0910-2728 | Mechanical Equipment Datasheet - Recycle Wash Oil Pumps | B | 2019-04-26 | IFQ | OL1-2M03-2728 | ME | 2019-04-30 | 036909C-JVD-TRN-01524 | 036909C-JVD-TRN-01524 | IFR | 2019-05-15 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01524 |  | 2019-05-02 | 2
036909C-1027-SP-0910-2726 | Mechanical Equipment Datasheet - Pygas Fuel Oil Pumps | A | 2019-02-19 | IFQ | OL1-2M03-2726 | ME | 2019-02-20 | 036909C-JVD-TRN-00898 | 036909C-JVD-TRN-00898, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-07 | 2019-03-19 | R1-No comments | TPSK-LSPA1-T-ME-00898 |  | 2019-02-20 | 2
036909C-1027-SP-0910-2726 | Mechanical Equipment Datasheet - Pygas Fuel Oil Pumps | B | 2019-04-26 | IFQ | OL1-2M03-2726 | ME | 2019-04-30 | 036909C-JVD-TRN-01524 | 036909C-JVD-TRN-01524 | IFR | 2019-05-15 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01524 |  | 2019-05-02 | 2
036909C-1027-SP-0910-2719 | Mechanical Equipment Datasheet - Rerun Tower Reflux - Product Pumps | A | 2019-02-13 | IFQ | OL1-2M03-2719 | ME | 2019-02-19 | 036909C-JVD-TRN-00891 | 036909C-JVD-TRN-00891, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-06 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00891 |  | 2019-02-19 | 2
036909C-1027-SP-0910-2719 | Mechanical Equipment Datasheet - Rerun Tower Reflux - Product Pumps | B | 2019-04-25 | IFQ | OL1-2M03-2719 | ME | 2019-04-26 | 036909C-JVD-TRN-01493 | 036909C-JVD-TRN-01493 | IFR | 2019-05-13 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01493 |  | 2019-04-29 | 2
036909C-1027-SP-0910-2714 | Mechanical Equipment Datasheet - C5 Cut Pumps | B | 2019-03-27 | IFQ | OL1-2M03-2714 | ME | 2019-04-08 | 036909C-JVD-TRN-01279 | 036909C-JVD-TRN-01279 | IFR | 2019-04-23 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-ME-01279 |  | 2019-04-09 | 2
036909C-1027-SP-0910-2714 | Mechanical Equipment Datasheet - C5 Cut Pumps | A | 2019-02-13 | IFQ | OL1-2M03-2714 | ME | 2019-02-19 | 036909C-JVD-TRN-00891 | 036909C-JVD-TRN-00891, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-06 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00891 |  | 2019-02-19 | 2
036909C-1027-SP-0910-2713 | Mechanical Equipment Datasheet - Depentanizer Reflux Pump | B | 2019-03-12 | IFQ | OL1-2M03-2713 | ME | 2019-03-20 | 036909C-JVD-TRN-01102 | 036909C-JVD-TRN-01102, ROC-TPSK-CECO-T-00015 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-ME-01102 |  | 2019-03-21 | 2
036909C-1027-SP-0910-2713 | Mechanical Equipment Datasheet - Depentanizer Reflux Pump | A | 2019-02-13 | IFQ | OL1-2M03-2713 | ME | 2019-02-19 | 036909C-JVD-TRN-00891 | 036909C-JVD-TRN-00891 | IFR | 2019-03-06 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00891 |  | 2019-02-19 | 2
036909C-1027-SP-0910-2704 | Mechanical Equipment Datasheet - GHU-1 Recycle Pump | C | 2019-05-30 | IFQ | OL1-2M03-2704 | ME | 2019-06-12 | 036909C-JVD-TRN-01880 | 036909C-JVD-TRN-01880 | IFR | 2019-06-27 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-01880 |  | 2019-06-14 | 2
036909C-1027-SP-0910-2704 | Mechanical Equipment Datasheet - GHU-1 Recycle Pump | A | 2019-02-12 | IFQ | OL1-2M03-2704 | ME | 2019-02-19 | 036909C-JVD-TRN-00891 | 036909C-JVD-TRN-00891 | IFR | 2019-03-06 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00891 |  | 2019-02-19 | 2
036909C-1027-SP-0910-2704 | Mechanical Equipment Datasheet - GHU-1 Recycle Pump | B | 2019-03-12 | IFQ | OL1-2M03-2704 | ME | 2019-03-20 | 036909C-JVD-TRN-01102 | 036909C-JVD-TRN-01102, ROC-TPSK-CECO-T-00015 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-ME-01102 |  | 2019-03-21 | 2
036909C-1026-SP-0910-2668 | Mechanical Equipment Datasheet C5 - Pygas Pumps | C | 2019-04-18 | IFQ | OL1-2M03-2668 | ME | 2019-04-22 | 036909C-JVD-TRN-01426 | 036909C-JVD-TRN-01426 | IFR | 2019-05-07 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01426 |  | 2019-04-23 | 2
036909C-1026-SP-0910-2668 | Mechanical Equipment Datasheet - C5 - Pygas Pumps | A | 2019-02-19 | IFQ | OL1-2M03-2668 | ME | 2019-02-20 | 036909C-JVD-TRN-00898 | 036909C-JVD-TRN-00898 | IFR | 2019-03-07 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00898 |  | 2019-02-20 | 2
036909C-1026-SP-0910-2668 | Mechanical Equipment Datasheet - C5 - Pygas Pumps | B | 2019-03-12 | IFQ | OL1-2M03-2668 | ME | 2019-03-20 | 036909C-JVD-TRN-01102 | 036909C-JVD-TRN-01102, ROC-TPSK-CECO-T-00015 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-ME-01102 |  | 2019-03-21 | 2
036909C-1026-SP-0910-2663 | Mechanical Equipment Datasheet - Debutanizer Reflux - Product Pumps | A | 2018-12-12 | IFQ | OL1-2M03-2663 | ME | 2018-12-17 | 036909C-JVD-TRN-00511 | 036909C-JVD-TRN-00511 | IFR | 2018-12-31 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00511 |  | 2018-12-17 | 2
036909C-1026-SP-0910-2663 | Mechanical Equipment Datasheet - Debutanizer Reflux - Product Pumps | C | 2019-04-18 | IFQ | OL1-2M03-2663 | ME | 2019-04-25 | 036909C-JVD-TRN-01479 | 036909C-JVD-TRN-01479 | IFR | 2019-05-10 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01479 |  | 2019-04-26 | 2
036909C-1026-SP-0910-2647 | Mechanical Equipment Datasheet - HP Propylene - Off Spec Pump | A | 2018-12-12 | IFQ | OL1-2M03-2647 | ME | 2018-12-13 | 036909C-JVD-TRN-00494 | 036909C-JVD-TRN-00494 | IFR | 2018-12-26 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00494 |  | 2018-12-13 | 2
036909C-1026-SP-0910-2633 | Mechanical Equipment Data Sheet - Secondary Deeth Reflux Pumps | A | 2018-11-19 | IFQ | OL1-2M03-2633 | ME | 2018-12-13 | 036909C-JVD-TRN-00487 | 036909C-JVD-TRN-00487 | IFR | 2018-12-25 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-ME-00487 |  | 2018-12-13 | 2
036909C-1026-SP-0910-2623 | Mechanical Equipment Datasheet - C3 Hydrog Recycle Pumps | A | 2019-01-18 | IFQ | OL1-2M03-2623 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716, ROC-TPSK-CECO-T-00015 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716 |  | 2019-01-24 | 2
036909C-1026-SP-0910-2623 | Mechanical Equipment Datasheet - C3 Hydrog Recycle Pumps | C | 2019-05-30 | IFQ | OL1-2M03-2623 | ME | 2019-06-12 | 036909C-JVD-TRN-01880 | 036909C-JVD-TRN-01880 | IFR | 2019-06-27 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-01880 |  | 2019-06-14 | 2
036909C-1024-SP-0910-2457 | Mechanical Equipment Datasheet - LP Deprop Reboiler Cond Pump | A | 2018-12-05 | IFQ | OL1-2M03-2457 | ME | 2018-12-13 | 036909C-JVD-TRN-00494 | 036909C-JVD-TRN-00494 | IFR | 2018-12-26 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00494 |  | 2018-12-13 | 2
036909C-1011-PID-0021-1107 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 1 | B | 2019-02-12 | IBD | OL1-2G43-1107 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1107 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1107 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1106 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoke Air Header Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1106 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1106 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoke Air Header Distribution Header | B | 2019-02-12 | IBD | OL1-2G43-1106 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1105 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Dilution Steam Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1105 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1105 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Dilution Steam Distribution Header | B | 2019-02-12 | IBD | OL1-2G43-1105 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1101 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed Distribution Header | B | 2019-02-12 | IBD | OL1-2G43-1101 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1101 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1101 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1010-PID-0021-1031 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - Cracking Furnace Distribution - Sheet 2 | A | 2018-12-20 | IFR | OL1-2G43-1031 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1010-PID-0021-1031 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Cracking Furnace Distribution - Sheet 2 | B | 2019-03-26 | IBD | OL1-2G43-1031 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1010-PID-0021-1030 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Cracking Furnace Distribution - Sheet 1 | B | 2019-03-26 | IBD | OL1-2G43-1030 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1010-PID-0021-1030 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - Cracking Furnace Distribution - Sheet 1 | A | 2018-12-20 | IFR | OL1-2G43-1030 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1010-PID-0021-1023 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - C2 Feed Superheater | A | 2018-12-20 | IFR | OL1-2G43-1023 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1010-PID-0021-1023 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - C2 Feed Superheater | B | 2019-03-26 | IBD | OL1-2G43-1023 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1010-PID-0021-1006 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - LPG Feed Steam Heater | A | 2019-03-26 | IBD | OL1-2G43-1006 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00030 | IFR | 2019-04-11 | 2019-05-05 | CA3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1010-PID-0021-1005 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - LPG Steam Vaporizer | A | 2018-12-20 | IFR | OL1-2G43-1005 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1010-PID-0021-1005 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - LPG Steam Vaporizer | B | 2019-03-26 | IBD | OL1-2G43-1005 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1021-SP-0910-2191 | Mechanical Equipment Datasheet - Quench Water Drain Drum Pump | A | 2018-11-28 | IFQ | OL1-2M03-2191 | ME | 2018-11-29 | 036909C-JVD-TRN-00400 | 036909C-JVD-TRN-00400, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-13 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00400 |  | 2018-11-29 | 2
036909C-1021-SP-0910-2126 | Mechanical Equipment Datasheet - Distillate Stripper Bottom Pumps | C | 2019-04-18 | IFQ | OL1-2M03-2126 | ME | 2019-04-22 | 036909C-JVD-TRN-01426 | 036909C-JVD-TRN-01426 | IFR | 2019-05-07 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01426 |  | 2019-04-23 | 2
036909C-1021-SP-0910-2126 | Mechanical Equipment Datasheet - Distillate Stripper Bottom Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2126 | ME | 2018-12-05 | 036909C-JVD-TRN-00410 | 036909C-JVD-TRN-00410 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00410 |  | 2018-12-05 | 2
036909C-1029-PID-0021-2930 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - CG Compressor Auxiliaries - Sheet 1 | A | 2019-01-30 | IFR | OL1-2G43-2930 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1029-PID-0021-2930 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - CG Compressor Auxiliaries - Sheet 1 | B | 2019-04-16 | IBD | OL1-2G43-2930 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1026-PID-0021-2630 | P&ID - Olefins Unit 10 - Hot Fractionation - C5-Pygas Surge Drum | A | 2019-01-10 | IFR | OL1-2G43-2630 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1026-PID-0021-2630 | P&ID - Olefins Unit 10 - Hot Fractionation - C5-Pygas Surge Drum | C | 2019-05-06 | IBD | OL1-2G43-2630 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00066 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1026-PID-0021-2629 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Bottoms Cooling | B | 2019-03-14 | IFR | OL1-2G43-2629 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1026-PID-0021-2629 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Bottoms Cooling | A | 2019-01-10 | IFR | OL1-2G43-2629 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1026-PID-0021-2629 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Bottoms Cooling | C | 2019-05-06 | IBD | OL1-2G43-2629 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00066 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1026-PID-0021-2628 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Overhead Product-Reflux | A | 2019-01-10 | IFR | OL1-2G43-2628 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1026-PID-0021-2628 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Overhead Product-Reflux | B | 2019-04-09 | IBD | OL1-2G43-2628 | PE | 2019-04-09 | 036909C-JVD-TRN-01294 | 036909C-JVD-TRN-01294, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01294 |  | 2019-04-10 | 2
036909C-1026-PID-0021-2627 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Overhead | A | 2019-01-10 | IFR | OL1-2G43-2627 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1026-PID-0021-2627 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Overhead | B | 2019-04-09 | IBD | OL1-2G43-2627 | PE | 2019-04-09 | 036909C-JVD-TRN-01294 | 036909C-JVD-TRN-01294, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01294 |  | 2019-04-10 | 2
036909C-1026-PID-0021-2625 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer | A | 2019-01-10 | IFR | OL1-2G43-2625 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1026-PID-0021-2625 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer | B | 2019-04-09 | IBD | OL1-2G43-2625 | PE | 2019-04-09 | 036909C-JVD-TRN-01294 | 036909C-JVD-TRN-01294, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01294 |  | 2019-04-10 | 2
036909C-1026-PID-0021-2622 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Tower Bottoms | A | 2019-01-10 | IFR | OL1-2G43-2622 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1026-PID-0021-2622 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Tower Bottoms | B | 2019-04-09 | IBD | OL1-2G43-2622 | PE | 2019-04-09 | 036909C-JVD-TRN-01294 | 036909C-JVD-TRN-01294, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01294 |  | 2019-04-10 | 2
036909C-1026-PID-0021-2621 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Tower Reboilers | B | 2019-04-09 | IBD | OL1-2G43-2621 | PE | 2019-04-09 | 036909C-JVD-TRN-01294 | 036909C-JVD-TRN-01294, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01294 |  | 2019-04-10 | 2
036909C-1026-PID-0021-2621 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Tower Reboilers | A | 2019-01-10 | IFR | OL1-2G43-2621 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1026-PID-0021-2620 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Tower | A | 2019-01-10 | IFR | OL1-2G43-2620 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1026-PID-0021-2620 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Tower | B | 2019-04-09 | IBD | OL1-2G43-2620 | PE | 2019-04-09 | 036909C-JVD-TRN-01294 | 036909C-JVD-TRN-01294, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01294 |  | 2019-04-10 | 2
036909C-1026-PID-0021-2616 | P&ID - Olefins Unit 10 - Hot Fractionation - Secondary Deethanizer Overhead | B | 2019-04-09 | IBD | OL1-2G43-2616 | PE | 2019-04-09 | 036909C-JVD-TRN-01294 | 036909C-JVD-TRN-01294, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01294 |  | 2019-04-10 | 2
036909C-1026-PID-0021-2616 | P&ID - Olefins Unit 10 - Hot Fractionation - Secondary Deethanizer Overhead | A | 2019-01-10 | IFR | OL1-2G43-2616 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1026-PID-0021-2615 | P&ID - Olefins Unit 10 - Hot Fractionation - Secondary Deethanizer | A | 2019-01-10 | IFR | OL1-2G43-2615 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1026-PID-0021-2615 | P&ID - Olefins Unit 10 - Hot Fractionation - Secondary Deethanizer | B | 2019-04-09 | IBD | OL1-2G43-2615 | PE | 2019-04-09 | 036909C-JVD-TRN-01294 | 036909C-JVD-TRN-01294, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01294 |  | 2019-04-10 | 2
036909C-1026-PID-0021-2610 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Recycle | B | 2019-05-06 | IBD | OL1-2G43-2610 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00066 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1026-PID-0021-2610 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Recycle | A | 2019-03-14 | IFR | OL1-2G43-2610 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1026-PID-0021-2608 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Aftercooling | B | 2019-05-06 | IBD | OL1-2G43-2608 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00066 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1026-PID-0021-2608 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Aftercooling | A | 2019-03-14 | IFR | OL1-2G43-2608 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1026-PID-0021-2605 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Reactor | B | 2019-05-06 | IBD | OL1-2G43-2605 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00066 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1026-PID-0021-2605 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Reactors - Sheet 1 | A | 2019-03-14 | IFR | OL1-2G43-2605 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1026-PID-0021-2604 | P&ID - Olefins Unit 10 - Hot Fractionation - Feed Section | B | 2019-05-06 | IBD | OL1-2G43-2604 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00066 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1026-PID-0021-2604 | P&ID - Olefins Unit 10 - Hot Fractionation - Feed Section | A | 2019-03-14 | IFR | OL1-2G43-2604 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061, ROC-TPSK-CECO-T-00011 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1026-PID-0021-2603 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Arsine Guard Bed | B | 2019-04-09 | IBD | OL1-2G43-2603 | PE | 2019-04-09 | 036909C-JVD-TRN-01294 | 036909C-JVD-TRN-01294, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01294 |  | 2019-04-10 | 2
036909C-1026-PID-0021-2603 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Arsine Guard Bed | A | 2019-01-10 | IFR | OL1-2G43-2603 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1026-PID-0021-2602 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Guard Adsorbers - Sheet 2 | B | 2019-04-09 | IBD | OL1-2G43-2602 | PE | 2019-04-09 | 036909C-JVD-TRN-01294 | 036909C-JVD-TRN-01294, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01294 |  | 2019-04-10 | 2
036909C-1026-PID-0021-2602 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Guard Adsorbers - Sheet 2 | A | 2019-01-10 | IFR | OL1-2G43-2602 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1026-PID-0021-2601 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Guard Adsorbers - Sheet 1 | A | 2019-01-10 | IFR | OL1-2G43-2601 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1026-PID-0021-2601 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Guard Adsorbers - Sheet 1 | B | 2019-04-09 | IBD | OL1-2G43-2601 | PE | 2019-04-09 | 036909C-JVD-TRN-01294 | 036909C-JVD-TRN-01294, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01294 |  | 2019-04-10 | 2
036909C-1012-PID-0021-1230 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Boiler Feed Water Supply Export Steam | A | 2018-11-15 | IFR | OL1-2G43-1230 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1230 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Boiler Feed Water Supply-Export Steam | B | 2019-02-12 | IBD | OL1-2G43-1230 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1130 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Boiler Feed Water Supply Export Steam | A | 2018-11-15 | IFR | OL1-2G43-1130 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1130 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Boiler Feed Water Supply-Export Steam | B | 2019-02-12 | IBD | OL1-2G43-1130 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1010-PID-0021-1036 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - Cracking Furnace Distribution Utility Sheet 2 | A | 2018-12-20 | IFR | OL1-2G43-1036 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1010-PID-0021-1036 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Cracking Furnace Distribution Utility Sheet 2 | B | 2019-03-26 | IBD | OL1-2G43-1036 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1010-PID-0021-1035 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Cracking Furnace Distribution Utility Sheet 1 | B | 2019-03-26 | IBD | OL1-2G43-1035 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1010-PID-0021-1035 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - Cracking Furnace Distribution Utility Sheet 1 | A | 2018-12-20 | IFR | OL1-2G43-1035 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00010 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1012-EL-001 | Item Index Furnace Island | C | 2019-07-07 | IBD | OL1-2M91-0002 | ME | 2019-07-07 | 036909C-JVD-TRN-02122 | 036909C-JVD-TRN-02122 | IFR | 2019-07-25 | 2019-07-19 | R1-No comments | TPSK-LSPA1-T-ME-02122 |  | 2019-07-11 | 2
036909C-1012-EL-001 | Item Index Furnace Island | D | 2019-07-19 | IBD | OL1-2M91-0002 | ME | 2019-07-22 | 036909C-JVD-TRN-02232 | 036909C-JVD-TRN-02232 | IFR | 2019-08-06 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02226 |  | 2019-07-23 | 2
036909C-1012-EL-001 | Item Index Furnace Island | B | 2019-05-28 | IBD | OL1-2M91-0002 | ME | 2019-05-30 | 036909C-JVD-TRN-01766 | 036909C-JVD-TRN-01766 | IFR | 2019-06-14 |  | Transmitted | TPSK-LSPA1-T-ME-01766 |  | 2019-05-31 | 2
036909C-1012-EL-001 | Item Index Furnace Island | A | 2019-03-15 | IFR | OL1-2M91-0002 | ME | 2019-03-15 | 036909C-JVD-TRN-01080 | 036909C-JVD-TRN-01080, ROC-TPSK-CECO-T-00013, ROC-TPSK-CECO-T-00013_1 | IFR | 2019-04-01 | 2019-04-05 | R1-No comments | TPSK-LSPA1-T-ME-01080 |  | 2019-03-18 | 2
036909C-1012-DW-0130-2554 | USC 132U Cracking Furnace Peep Door Details | 0 | 2018-12-04 | IFI | OL1-2M06-2554 | ME | 2018-12-04 | 036909C-JVD-TRN-00422 | 036909C-JVD-TRN-00422 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00422 |  | 2018-12-04 | 3
036909C-1012-DW-0130-2554 | USC 132U Cracking Furnace Peep Door Details | 1 | 2019-07-17 | IMP | OL1-2M06-2554 | ME | 2019-07-22 | 036909C-JVD-TRN-02220 | 036909C-JVD-TRN-02220 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-02220 |  | 2019-07-23 | 3
036909C-1039-PDS-0800-3910 | Process Equipment Data Sheet - 10-D-3908 - Predistillation Inhibitor Drum | A | 2019-04-04 | IFR | OL1-2G30-3910 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1039-PDS-0800-3906 | Process Equipment Data Sheet - 10-D-3906 - BDU Anti Foam Agent Drum | A | 2019-04-04 | IFR | OL1-2G30-3906 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1039-PDS-0800-3904 | Process Equipment Data Sheet - 10-D-3904 - BDU Product Inhibitor Drum | A | 2019-04-04 | IFR | OL1-2G30-3904 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1039-PDS-0800-3902 | Process Equipment Data Sheet - 10-D-3902 - BDU Solvent Inhibitor Drum | A | 2019-04-04 | IFR | OL1-2G30-3902 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1031-PDS-0800-3151 | Process Equipment Data Sheet - 10-D-3150 - BDU Condensate Flash Drum | A | 2019-04-04 | IFR | OL1-2G30-3151 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1059-MSD-0011-5911 | Material Selection Diagram - Olefins Unit 10 - 59 Utilities And Auxiliaries Complex U & O Chemical Storage | A | 2018-12-20 | IFA | OL1-2G74-5911 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1059-MSD-0011-5901 | Material Selection Diagram - Olefins Unit 10 - 59 Utilities Aux - Chemical Storage | A | 2018-12-20 | IFA | OL1-2G74-5901 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1056-MSD-0011-5616 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Sludge Dewatering Package | A | 2018-12-20 | IFA | OL1-2G74-5616 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1056-MSD-0011-5612 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Oily Wastewater Equilization Tank | A | 2018-12-20 | IFA | OL1-2G74-5612 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1056-MSD-0011-5611 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - OSBL Oily Wastewater Collection | A | 2018-12-20 | IFA | OL1-2G74-5611 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1056-MSD-0011-5610 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - HP Flare Area SW & Oily WW Collection | A | 2018-12-20 | IFA | OL1-2G74-5610 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1056-MSD-0011-5604 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Domestic Wastewater Collection | A | 2018-12-20 | IFA | OL1-2G74-5604 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1055-MSD-0011-5512 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - Enclosed Ground | A | 2018-12-20 | IFA | OL1-2G74-5512 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1055-MSD-0011-5502 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - Process Vent Gas Collection | A | 2018-12-20 | IFA | OL1-2G74-5502 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1055-MSD-0011-5501 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - Flare and Blowdown System | A | 2018-12-20 | IFA | OL1-2G74-5501 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1054-MSD-0011-5401 | Material Selection Diagram - Olefins Unit 10 - 54 Air and Nitrogen System - Plant Air - Instrument Air and Nitrogen Systems | A | 2018-12-20 | IFA | OL1-2G74-5401 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1053-MSD-0011-5311 | Material Selection Diagram - Olefins Unit 10 - 53-Cooling Water System Cooling Tower | A | 2018-11-16 | IFA | OL1-2G74-5311 | ME | 2018-11-29 | 036909C-JVD-TRN-00399 | 036909C-JVD-TRN-00399 | IFA | 2018-12-13 | 2019-02-15 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00399 |  | 2018-11-29 | 1
036909C-1053-MSD-0011-5301 | Material Selection Diagram - Olefins Unit 10 - 53 Cooling Water System Cooling Water Diagram | A | 2018-11-16 | IFA | OL1-2G74-5301 | ME | 2018-11-29 | 036909C-JVD-TRN-00399 | 036909C-JVD-TRN-00399 | IFA | 2018-12-13 | 2019-02-15 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00399 |  | 2018-11-29 | 1
036909C-1052-MSD-0011-5201 | Material Selection Diagram - Olefins Unit 10 - 52 Fuel System - Fuel Gas System | A | 2018-12-20 | IFA | OL1-2G74-5201 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1051-MSD-0011-5104 | Material Selection Diagram - Olefins Unit 10 - 51 BFW Steam Cond Systems - Furnace Blowdown System | A | 2018-12-20 | IFA | OL1-2G74-5104 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608, TPSK-LSPA1-T-PE-02428, TPSK-LSPA1-T-PE-02428 |  | 2019-01-08 | 3
036909C-1051-MSD-0011-5103 | Material Selection Diagram - Olefins Unit 10 - 51 BFW Steam Cond Systems - Condensate Treatment System | A | 2018-12-20 | IFA | OL1-2G74-5103 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608, TPSK-LSPA1-T-PE-02428, TPSK-LSPA1-T-PE-02428 |  | 2019-01-08 | 3
036909C-1051-MSD-0011-5102 | Material Selection Diagram - Olefins Unit 10 - 51 BFW Steam Cond Systems - Condensate and Boiler Feedwater Systems | A | 2018-12-20 | IFA | OL1-2G74-5102 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608, TPSK-LSPA1-T-PE-02428, TPSK-LSPA1-T-PE-02428 |  | 2019-01-08 | 3
036909C-1050-MSD-0011-5001 | Material Selection Diagram - Olefins Unit 10 - 50 Water Systems - Treated -Potable and Demin Water Systems | A | 2018-12-20 | IFA | OL1-2G74-5001 | ME | 2019-01-08 | 036909C-JVD-TRN-00608 | 036909C-JVD-TRN-00608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00608 |  | 2019-01-08 | 3
036909C-1029-MSD-0011-2901 | Material Selection Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | A | 2018-11-02 | IFA | OL1-2G74-2901 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1028-MSD-0011-2804 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | A | 2018-11-02 | IFA | OL1-2G74-2804 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1028-MSD-0011-2803 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | A | 2018-11-02 | IFA | OL1-2G74-2803 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1028-MSD-0011-2802 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | A | 2018-11-02 | IFA | OL1-2G74-2802 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1028-MSD-0011-2801 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | A | 2018-11-02 | IFA | OL1-2G74-2801 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1026-MSD-0011-2604 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | A | 2018-11-02 | IFA | OL1-2G74-2604 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1026-MSD-0011-2603 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | A | 2018-11-02 | IFA | OL1-2G74-2603 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1026-MSD-0011-2602 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | A | 2018-11-02 | IFA | OL1-2G74-2602 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1026-MSD-0011-2601 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | A | 2018-11-02 | IFA | OL1-2G74-2601 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1025-MSD-0011-2506 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | A | 2018-11-02 | IFA | OL1-2G74-2506 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1025-MSD-0011-2505 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | A | 2018-11-02 | IFA | OL1-2G74-2505 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1025-MSD-0011-2504 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | A | 2018-11-02 | IFA | OL1-2G74-2504 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1025-MSD-0011-2503 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | A | 2018-11-02 | IFA | OL1-2G74-2503 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1025-MSD-0011-2502 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | A | 2018-11-02 | IFA | OL1-2G74-2502 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1025-MSD-0011-2501 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | A | 2018-11-02 | IFA | OL1-2G74-2501 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1024-MSD-0011-2405 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | A | 2018-11-02 | IFA | OL1-2G74-2405 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1024-MSD-0011-2404 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | A | 2018-11-02 | IFA | OL1-2G74-2404 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1024-MSD-0011-2403 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | A | 2018-11-02 | IFA | OL1-2G74-2403 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1024-MSD-0011-2402 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | A | 2018-11-02 | IFA | OL1-2G74-2402 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1024-MSD-0011-2401 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | A | 2018-11-02 | IFA | OL1-2G74-2401 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1023-MSD-0011-2305 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | A | 2018-11-02 | IFA | OL1-2G74-2305 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1023-MSD-0011-2304 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | A | 2018-11-02 | IFA | OL1-2G74-2304 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1023-MSD-0011-2303 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | A | 2018-11-02 | IFA | OL1-2G74-2303 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1023-MSD-0011-2302 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | A | 2018-11-02 | IFA | OL1-2G74-2302 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1023-MSD-0011-2301 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | A | 2018-11-02 | IFA | OL1-2G74-2301 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1022-MSD-0011-2201 | Material Selection Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | A | 2018-11-02 | IFA | OL1-2G74-2201 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1021-MSD-0011-2103 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | A | 2018-11-02 | IFA | OL1-2G74-2103 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1021-MSD-0011-2102 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | A | 2018-11-02 | IFA | OL1-2G74-2102 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1021-MSD-0011-2101 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | A | 2018-11-02 | IFA | OL1-2G74-2101 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1020-MSD-0011-2002 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | A | 2018-11-02 | IFA | OL1-2G74-2002 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1020-MSD-0011-2001 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | A | 2018-11-02 | IFA | OL1-2G74-2001 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1019-MSD-0011-1902 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | A | 2018-11-02 | IFA | OL1-2G74-1902 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1019-MSD-0011-1901 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | A | 2018-11-02 | IFA | OL1-2G74-1901 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1012-MSD-0011-1201 | Material Selection Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | A | 2018-11-02 | IFA | OL1-2G74-1201 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1011-MSD-0011-1101 | Material Selection Diagram - Olefins Unit 10 - 11 - Furnaces - Gas Cracking Furnace | A | 2018-11-02 | IFA | OL1-2G74-1101 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1010-MSD-0011-1003 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | A | 2018-11-02 | IFA | OL1-2G74-1003 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1010-MSD-0011-1001 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | A | 2018-11-02 | IFA | OL1-2G74-1001 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1000-MSD-0011-0001 | Material Selection Diagram - Olefins Unit 10 - Legend & Notes | A | 2018-11-02 | IFA | OL1-2G74-0001 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | 2018-11-09 | 1
036909C-1028-PID-0021-2846 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Drain Drum | A | 2019-01-14 | IFR | OL1-2G43-2846 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2846 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Drain Drum | B | 2019-04-12 | IBD | OL1-2G43-2846 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2842 | P&ID - Olefins Unit 10 - Refrigeration System - LP Ethylene Product Cooling | B | 2019-04-12 | IBD | OL1-2G43-2842 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2842 | P&ID - Olefins Unit 10 - Refrigeration System - LP Ethylene Product Cooling | A | 2019-01-14 | IFR | OL1-2G43-2842 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2840 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant 1st Stage Suction | B | 2019-04-12 | IBD | OL1-2G43-2840 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2840 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant 1st Stage Suction | A | 2019-01-14 | IFR | OL1-2G43-2840 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2838 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant 2nd Stage Suction | A | 2019-01-14 | IFR | OL1-2G43-2838 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2838 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant 2nd Stage Suction | B | 2019-04-12 | IBD | OL1-2G43-2838 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2836 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant 3rd Stage Suction | B | 2019-04-12 | IBD | OL1-2G43-2836 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2836 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant 3rd Stage Suction | A | 2019-01-14 | IFR | OL1-2G43-2836 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2834 | P&ID - Olefins Unit 10 - Refrigeration System - HP Ethylene Vapor Product | A | 2019-01-14 | IFR | OL1-2G43-2834 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2834 | P&ID - Olefins Unit 10 - Refrigeration System - HP Ethylene Vapor Product | B | 2019-04-12 | IBD | OL1-2G43-2834 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2830 | P&ID - Olefins Unit 10 - Refrigeration System - HP Ethylene Liquid Product Chiller | A | 2019-01-14 | IFR | OL1-2G43-2830 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2830 | P&ID - Olefins Unit 10 - Refrigeration System - HP Ethylene Liquid Product Chiller | B | 2019-04-12 | IBD | OL1-2G43-2830 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2828 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Surge Drum | A | 2019-01-14 | IFR | OL1-2G43-2828 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2828 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Surge Drum | B | 2019-04-12 | IBD | OL1-2G43-2828 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2825 | P&ID - Olefins Unit 10 - Refrigeration System - C2R Desuperheater And Condenser | B | 2019-04-12 | IBD | OL1-2G43-2825 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2825 | P&ID - Olefins Unit 10 - Refrigeration System - C2R Desuperheater And Condenser | A | 2019-01-14 | IFR | OL1-2G43-2825 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2824 | P&ID - Olefins Unit 10 - Refrigeration System - C2 Refrigerant Desuperheaters | B | 2019-04-12 | IBD | OL1-2G43-2824 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2824 | P&ID - Olefins Unit 10 - Refrigeration System - C2 Refrigerant Desuperheaters | A | 2019-01-14 | IFR | OL1-2G43-2824 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2823 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Compressor - Sheet 3 | A | 2019-04-12 | IBD | OL1-2G43-2823 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00047 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2822 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Compressor - Sheet 2 | A | 2019-01-14 | IFR | OL1-2G43-2822 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2822 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Compressor - Sheet 2 | B | 2019-04-12 | IBD | OL1-2G43-2822 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2821 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Compressor - Sheet 1 | B | 2019-04-12 | IBD | OL1-2G43-2821 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2821 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Compressor - Sheet 1 | A | 2019-01-14 | IFR | OL1-2G43-2821 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2819 | P&ID - Olefins Unit 10 - Refrigeration System - Propylene Product Chilling - Sheet 2 | B | 2019-04-12 | IBD | OL1-2G43-2819 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2819 | P&ID - Olefins Unit 10 - Refrigeration System - Propylene Product Chilling - Sheet 2 | A | 2019-01-14 | IFR | OL1-2G43-2819 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2818 | P&ID - Olefins Unit 10 - Refrigeration System - Propylene Product Chilling - Sheet 1 | B | 2019-04-12 | IBD | OL1-2G43-2818 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2818 | P&ID - Olefins Unit 10 - Refrigeration System - Propylene Product Chilling - Sheet 1 | A | 2019-01-14 | IFR | OL1-2G43-2818 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2816 | P&ID - Olefins Unit 10 - Refrigeration System - Propylene Product Pump | B | 2019-04-12 | IBD | OL1-2G43-2816 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2816 | P&ID - Olefins Unit 10 - Refrigeration System - Propylene Product Pump | A | 2019-01-14 | IFR | OL1-2G43-2816 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2814 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Drain Drum | A | 2019-01-14 | IFR | OL1-2G43-2814 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2814 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Drain Drum | B | 2019-04-12 | IBD | OL1-2G43-2814 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2812 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 1st Stage Suction | A | 2019-01-14 | IFR | OL1-2G43-2812 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2812 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 1st Stage Suction | B | 2019-04-12 | IBD | OL1-2G43-2812 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2810 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 2nd Stage Suction | B | 2019-04-12 | IBD | OL1-2G43-2810 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2810 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 2nd Stage Suction | A | 2019-01-14 | IFR | OL1-2G43-2810 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2808 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 3rd Stage Suction | A | 2019-01-14 | IFR | OL1-2G43-2808 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2808 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 3rd Stage Suction | B | 2019-04-12 | IBD | OL1-2G43-2808 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2807 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 3 | B | 2019-04-12 | IBD | OL1-2G43-2807 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2807 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 3 | A | 2019-01-14 | IFR | OL1-2G43-2807 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2806 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 4th Stage Suction | B | 2019-04-12 | IBD | OL1-2G43-2806 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2806 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 4th Stage Suction | A | 2019-01-14 | IFR | OL1-2G43-2806 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2805 | P&ID - Olefins Unit 10 - Refrigeration System - Hp C3 Refrigeration Distribution | A | 2019-01-14 | IFR | OL1-2G43-2805 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2805 | P&ID - Olefins Unit 10 - Refrigeration System - Hp C3 Refrigeration Distribution | B | 2019-04-12 | IBD | OL1-2G43-2805 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2804 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Receiver | B | 2019-04-12 | IBD | OL1-2G43-2804 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2804 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Receiver | A | 2019-01-14 | IFR | OL1-2G43-2804 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2803 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Condenser | A | 2019-01-14 | IFR | OL1-2G43-2803 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2803 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Condenser | B | 2019-04-12 | IBD | OL1-2G43-2803 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2802 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 2 | A | 2019-01-14 | IFR | OL1-2G43-2802 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1028-PID-0021-2802 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 2 | B | 2019-04-12 | IBD | OL1-2G43-2802 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2801 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 1 | B | 2019-04-12 | IBD | OL1-2G43-2801 | PE | 2019-04-12 | 036909C-JVD-TRN-01345 | 036909C-JVD-TRN-01345, ROC-TPSK-CECO-T-00067 | IFR | 2019-04-29 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01345 |  | 2019-04-15 | 2
036909C-1028-PID-0021-2801 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 1 | A | 2019-01-14 | IFR | OL1-2G43-2801 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1020-PID-0021-2042 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Drain Drum | B | 2019-03-26 | IBD | OL1-2G43-2042 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1020-PID-0021-2042 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Drain Drum | A | 2018-12-20 | IFR | OL1-2G43-2042 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1020-PID-0021-2040 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Drain Collection | A | 2018-12-20 | IFR | OL1-2G43-2040 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1020-PID-0021-2040 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Drain Collection | B | 2019-03-26 | IBD | OL1-2G43-2040 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1020-PID-0021-2027 | P&ID - Olefins Unit 10 - Quench Oil - Heavy Fuel Oil Product Cooling | A | 2018-12-20 | IFR | OL1-2G43-2027 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1020-PID-0021-2027 | P&ID - Olefins Unit 10 - Quench Oil - Heavy Fuel Oil Product Cooling | B | 2019-03-26 | IBD | OL1-2G43-2027 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1020-PID-0021-2026 | P&ID - Olefins Unit 10 - Quench Oil - Heavy Fuel Oil Pumps | A | 2018-12-20 | IFR | OL1-2G43-2026 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1020-PID-0021-2026 | P&ID - Olefins Unit 10 - Quench Oil - Heavy Fuel Oil Pumps | B | 2019-03-26 | IBD | OL1-2G43-2026 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1020-PID-0021-2025 | P&ID - Olefins Unit 10 - Quench Oil - Heavy Fuel Oil Stripper | B | 2019-03-26 | IBD | OL1-2G43-2025 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1020-PID-0021-2025 | P&ID - Olefins Unit 10 - Quench Oil - Heavy Fuel Oil Stripper | A | 2018-12-20 | IFR | OL1-2G43-2025 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1020-PID-0021-2022 | P&ID - Olefins Unit 10 - Quench Oil - Purge Oil Filtration | B | 2019-03-26 | IBD | OL1-2G43-2022 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1020-PID-0021-2022 | P&ID - Olefins Unit 10 - Quench Oil - Purge Oil Filtration | A | 2018-12-20 | IFR | OL1-2G43-2022 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1020-PID-0021-2021 | P&ID - Olefins Unit 10 - Quench Oil - Fuel Oil Product Cooling | B | 2019-03-26 | IBD | OL1-2G43-2021 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1020-PID-0021-2021 | P&ID - Olefins Unit 10 - Quench Oil - Fuel Oil Product Cooling | A | 2018-12-20 | IFR | OL1-2G43-2021 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1020-PID-0021-2020 | P&ID - Olefins Unit 10 - Quench Oil - Light Fuel Oil Stripper | A | 2018-12-20 | IFR | OL1-2G43-2020 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1020-PID-0021-2020 | P&ID - Olefins Unit 10 - Quench Oil - Light Fuel Oil Stripper | B | 2019-03-26 | IBD | OL1-2G43-2020 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1020-PID-0021-2008 | P&ID - Olefins Unit 10 - Quench Oil - VLP Steam Generation - Sheet 3 | A | 2019-03-26 | IBD | OL1-2G43-2008 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00030 | IFR | 2019-04-11 | 2019-04-05 | CA3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1020-PID-0021-2007 | P&ID - Olefins Unit 10 - Quench Oil - VLP Steam Generation - Sheet 2 | A | 2018-12-20 | IFR | OL1-2G43-2007 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1020-PID-0021-2007 | P&ID - Olefins Unit 10 - Quench Oil - VLP Steam Generation - Sheet 2 | B | 2019-03-26 | IBD | OL1-2G43-2007 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1020-PID-0021-2006 | P&ID - Olefins Unit 10 - Quench Oil - VLP Steam Generation - Sheet 1 | A | 2018-12-20 | IFR | OL1-2G43-2006 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1020-PID-0021-2006 | P&ID - Olefins Unit 10 - Quench Oil - VLP Steam Generation - Sheet 1 | B | 2019-03-26 | IBD | OL1-2G43-2006 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1020-PID-0021-2005 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Filtration | B | 2019-03-26 | IBD | OL1-2G43-2005 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1020-PID-0021-2005 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Filtration | A | 2018-12-20 | IFR | OL1-2G43-2005 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1020-PID-0021-2003 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Pumps | A | 2018-12-20 | IFR | OL1-2G43-2003 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1020-PID-0021-2003 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Pumps | B | 2019-03-26 | IBD | OL1-2G43-2003 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1020-PID-0021-2001 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Tower | B | 2019-03-26 | IBD | OL1-2G43-2001 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1020-PID-0021-2001 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Tower | A | 2018-12-20 | IFR | OL1-2G43-2001 | PE | 2018-12-27 | 036909C-JVD-TRN-00566 | 036909C-JVD-TRN-00566, ROC-TPSK-CECO-T-00009 | IFR | 2019-01-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00566 |  | 2018-12-27 | 2
036909C-1028-SP-0810-2870 | Mechanical Equipment Data Sheet for C2R 2ND Stage Suction Drum | 0 | 2019-07-17 | Issue for Purchase | OL1-2M03-2870 | ME | 2019-07-22 | 036909C-JVD-TRN-02207 | 036909C-JVD-TRN-02207 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02207 |  | 2019-07-23 | 2
036909C-1027-SP-0810-2712 | Mechanical Equipment Data Sheet For Depentanizer Reflux Drum | 0 | 2019-07-16 | Issue for Purchase | OL1-2M03-2712 | ME | 2019-07-22 | 036909C-JVD-TRN-02207 | 036909C-JVD-TRN-02207 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02207 |  | 2019-07-23 | 2
036909C-1026-TDS-0610-2636 | Mechanical Equipment Data Sheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | 0 | 2019-06-25 | Issue for Purchase | OL1-2M03-2636 | ME | 2019-07-18 | 036909C-JVD-TRN-02185 | 036909C-JVD-TRN-02185 | IFR | 2019-08-02 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02185 |  | 2019-07-19 | 2
036909C-1026-TDS-0610-2631 | Mechanical Equipment Data Sheet - 10-E-2630 - Secondary Deeth Condenser | 0 | 2019-06-25 | IFP | OL1-2M03-2631 | ME | 2019-07-18 | 036909C-JVD-TRN-02185 | 036909C-JVD-TRN-02185 | IFR | 2019-08-02 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02185 |  | 2019-07-19 | 2
036909C-1025-TDS-0610-2576 | Mechanical Equipment Data Sheet - 10-E-2576 - Deethanizer Bottoms Cooler | 0 | 2019-07-16 | Issue for Purchase | OL1-2M03-2576 | ME | 2019-07-22 | 036909C-JVD-TRN-02231 | 036909C-JVD-TRN-02231 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02231 |  | 2019-07-23 | 2
036909C-1025-SP-0810-2555 | Mechanical Equipment Data Sheet - Expander Discharge Drum | 0 | 2019-07-17 | Issue for Purchase | OL1-2M03-2555 | ME | 2019-07-22 | 036909C-JVD-TRN-02207 | 036909C-JVD-TRN-02207 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02207 |  | 2019-07-23 | 2
036909C-1024-SP-0810-2405 | Mechanical Equipment Data Sheet For Gas Dryer Feed KO Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2405 | ME | 2019-07-16 | 036909C-JVD-TRN-02167 | 036909C-JVD-TRN-02167 | IFR | 2019-07-31 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02167 |  | 2019-07-17 | 2
036909C-1023-SP-0810-2392 | Mechanical Equipment Data Sheet for Spent Caustic Drain Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2392 | ME | 2019-07-16 | 036909C-JVD-TRN-02167 | 036909C-JVD-TRN-02167 | IFR | 2019-07-31 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02167 |  | 2019-07-17 | 2
036909C-1023-SP-0810-2390 | Mechanical Equipment Data Sheet Caustic Drain Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2390 | ME | 2019-07-16 | 036909C-JVD-TRN-02167 | 036909C-JVD-TRN-02167 | IFR | 2019-07-31 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02167 |  | 2019-07-17 | 2
036909C-1023-SP-0810-2309 | Mechanical Equipment Data Sheet Yellow Oil Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2309 | HOC Mech | 2019-07-16 | 036909C-JVD-TRN-02166 | 036909C-JVD-TRN-02166 | IFR | 2019-07-31 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02166 |  | 2019-07-16 | 2
036909C-1022-SP-0810-2245 | Mechanical Equipment Data Sheet for CG 4th Stage Discharge Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2245 | HOC Mech | 2019-07-16 | 036909C-JVD-TRN-02166 | 036909C-JVD-TRN-02166 | IFR | 2019-07-31 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02166 |  | 2019-07-16 | 2
036909C-1022-SP-0810-2240 | Mechanical Equipment Data Sheet CG 4th Stage Suction Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2240 | HOC Mech | 2019-07-16 | 036909C-JVD-TRN-02166 | 036909C-JVD-TRN-02166 | IFR | 2019-07-31 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02166 |  | 2019-07-16 | 2
036909C-1021-SP-0810-2110 | Mechanical Equipment Data Sheet for Interception Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2110 | ME | 2019-07-16 | 036909C-JVD-TRN-02166 | 036909C-JVD-TRN-02166 | IFR | 2019-07-31 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02166 |  | 2019-07-17 | 2
036909C-1010-TDS-0610-1006 | Mechanical Equipment Data Sheet - 10-E-1006 - LPG Feed Steam Heater | 0 | 2019-07-16 | IFP | OL1-2M03-1006 | ME | 2019-07-17 | 036909C-JVD-TRN-02175 | 036909C-JVD-TRN-02175 | IFR | 2019-08-01 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02175 |  | 2019-07-17 | 2
036909C-1056-PDS-2600-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg | E | 2019-07-18 | IFD | OL1-2G30-5670 | PE | 2019-07-22 | 036909C-JVD-TRN-02214 | 036909C-JVD-TRN-02214 | IFR | 2019-08-06 | 2019-08-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-02214 |  | 2019-07-23 | 2
036909C-1056-PDS-2600-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg | E | 2019-07-18 | IFD | OL1-2G30-5650 | PE | 2019-07-22 | 036909C-JVD-TRN-02214 | 036909C-JVD-TRN-02214 | IFR | 2019-08-06 | 2019-08-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-02214 |  | 2019-07-23 | 2
036909C-1012-TBT-1545-2202 | Technical Bid Tabulation For Pressure Relief Valves | 0 | 2019-07-22 | IFI | OL1-2C23-2202 | PL | 2019-07-23 | 036909C-JVD-TRN-02243 | 036909C-JVD-TRN-02243 | IFI |  | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-PL-02243 |  | 2019-07-24 | 3
036909C-1012-MR-4061-2009 | Material Requisition for Furnace Elevator | 0 | 2019-07-22 | IFP | OL1-2C13-709000 | PL | 2019-07-24 | 036909C-JVD-TRN-02260 | 036909C-JVD-TRN-02260 | IFI |  | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-PL-02260 |  | 2019-07-25 | 3
036909C-1031-SP-0810-3190 | Mechanical Equipment Data Sheet - NMP Slop Drum | A | 2019-05-10 | IFQ | OL1-2M03-3190 | ME | 2019-05-13 | 036909C-JVD-TRN-01654 | 036909C-JVD-TRN-01654 | IFR | 2019-05-28 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01654 |  | 2019-05-14 | 2
036909C-1031-SP-0810-3161 | Mechanical Equipment Data Sheet - BDU Condensate Drum | A | 2019-05-13 | IFQ | OL1-2M03-3161 | ME | 2019-05-13 | 036909C-JVD-TRN-01654 | 036909C-JVD-TRN-01654 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-ME-01654 |  | 2019-05-14 | 2
036909C-1031-SP-0810-3100 | Mechanical Equipment Data Sheet - Solvent Regen Drum | A | 2019-05-10 | IFQ | OL1-2M03-3100 | ME | 2019-05-13 | 036909C-JVD-TRN-01654 | 036909C-JVD-TRN-01654 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-ME-01654 |  | 2019-05-07 | 2
036909C-1030-SP-0810-3082 | Mechanical Equipment Data Sheet - Butadiene Tower Reflux Drum | A | 2019-05-10 | IFQ | OL1-2M03-3082 | ME | 2019-05-13 | 036909C-JVD-TRN-01654 | 036909C-JVD-TRN-01654 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-ME-01654 |  | 2019-05-14 | 2
036909C-1030-SP-0810-3065 | Mechanical Equipment Data Sheet - C4 Acetylene Accumulator | A | 2019-05-10 | IFQ | OL1-2M03-3065 | ME | 2019-05-10 | 036909C-JVD-TRN-01645 | 036909C-JVD-TRN-01645 | IFR | 2019-05-28 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME -01645 |  | 2019-05-13 | 2
036909C-1030-SP-0810-3064 | Mechanical Equipment Data Sheet - BDU HC-Water Separator | A | 2019-05-10 | IFQ | OL1-2M03-3064 | ME | 2019-05-13 | 036909C-JVD-TRN-01654 | 036909C-JVD-TRN-01654 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-ME-01654 |  | 2019-05-14 | 2
036909C-1030-SP-0810-3032 | Mechanical Equipment Data Sheet - After Washer Reflux Drum | A | 2019-05-10 | IFQ | OL1-2M03-3032 | ME | 2019-05-10 | 036909C-JVD-TRN-01645 | 036909C-JVD-TRN-01645 | IFR | 2019-05-28 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME -01645 |  | 2019-05-13 | 2
036909C-1030-SP-0810-3022 | Mechanical Equipment Data Sheet - Main Washer Reflux Drum | A | 2019-05-10 | IFI | OL1-2M03-3022 | ME | 2019-05-10 | 036909C-JVD-TRN-01645 | 036909C-JVD-TRN-01645 | IFR | 2019-05-28 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME -01645 |  | 2019-05-13 | 2
036909C-1030-SP-0810-3002 | Mechanical Equipment Data Sheet - Predistillation Feed Drum | A | 2019-05-10 | IFQ | OL1-2M03-3002 | ME | 2019-05-10 | 036909C-JVD-TRN-01645 | 036909C-JVD-TRN-01645 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-ME -01645 |  | 2019-05-13 | 2
036909C-1056-SP-0910-5624 | Mechanical Equipment Datasheet - West Gate House Septic Tank Pumps | A | 2019-02-08 | IFQ | OL1-2M03-5624 | ME | 2019-02-13 | 036909C-JVD-TRN-00847 | 036909C-JVD-TRN-00847, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-27 | 2019-03-11 | R2-Comments as noted | TPSK-LSPA1-T-ME -00847 |  | 2019-02-13 | 2
036909C-1056-SP-0910-5623 | Mechanical Equipment Datasheet - Gate House Septic Tank Pumps | A | 2019-02-08 | IFQ | OL1-2M03-5623 | ME | 2019-02-13 | 036909C-JVD-TRN-00847 | 036909C-JVD-TRN-00847, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-27 | 2019-03-11 | R2-Comments as noted | TPSK-LSPA1-T-ME -00847 |  | 2019-02-13 | 2
036909C-1031-PDS-0800-3190 | Process Equipment Data Sheet - 10-D-3190 - NMP Slop Drum | A | 2019-04-04 | IFR | OL1-2G30-3190 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1031-PDS-0800-3190 | Process Equipment Data Sheet - 10-D-3190 - NMP Slop Drum | B | 2019-06-05 | IFD | OL1-2G30-3190 | PE | 2019-06-06 | 036909C-JVD-TRN-01820 | 036909C-JVD-TRN-01820 | IFR | 2019-06-21 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01820 |  | 2019-06-10 | 2
036909C-1031-PFD-0010-3102 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam And Condensate System | A | 2018-08-23 | IFA | OL1-2G41-3102 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1031-PFD-0010-3102 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam and Condensate System | C | 2019-04-26 | IFD | OL1-2G41-3102 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1031-PFD-0010-3102 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam and Condensate System | B | 2018-10-09 | IFD | OL1-2G41-3102 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1039-PFD-0010-3901 | Process Flow Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage | A | 2018-08-23 | IFA | OL1-2G41-3901 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1039-PFD-0010-3901 | Process Flow Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage | C | 2019-04-26 | IFD | OL1-2G41-3901 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1039-PFD-0010-3901 | Process Flow Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage | B | 2018-10-09 | IFD | OL1-2G41-3901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1050-PFD-0030-5001 | Utility Flow Diagram - Olefins Unit 10 - 50 - Water System - Treated Potable and Demin Water Systems | C | 2019-04-26 | IFD | OL1-2G42-5001 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1050-PFD-0030-5001 | Utility Flow Diagram - Olefins Unit 10 - 50 - Water System - Treated Potable And Demin Water Systems | A | 2018-08-23 | IFA | OL1-2G42-5001 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1050-PFD-0030-5001 | Utility Flow Diagram - Olefins Unit 10 - 50 - Water System - Treated Potable and Demin Water Systems | B | 2018-10-09 | IFD | OL1-2G42-5001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1051-PFD-0030-5101 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Steam Balance Diagram | C | 2019-04-26 | IFD | OL1-2G42-5101 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1051-PFD-0030-5101 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Steam Balance Diagram | B | 2018-10-09 | IFD | OL1-2G42-5101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1051-PFD-0030-5101 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Steam Balance Diagram | A | 2018-08-23 | IFA | OL1-2G42-5101 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1051-PFD-0030-5102 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate And Boiler Feedwater Systems | A | 2018-08-23 | IFA | OL1-2G42-5102 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1051-PFD-0030-5102 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate and Boiler Feedwater Systems | C | 2019-04-26 | IFD | OL1-2G42-5102 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1051-PFD-0030-5102 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate and Boiler Feedwater Systems | B | 2018-10-09 | IFD | OL1-2G42-5102 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1051-PFD-0030-5103 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate Treatment System | A | 2018-08-23 | IFA | OL1-2G42-5103 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1051-PFD-0030-5103 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate Treatment System | B | 2018-10-09 | IFD | OL1-2G42-5103 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1051-PFD-0030-5103 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate Treatment System | C | 2019-04-26 | IFD | OL1-2G42-5103 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1051-PFD-0030-5104 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Furnace Blowdown System | A | 2018-08-23 | IFA | OL1-2G42-5104 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1051-PFD-0030-5104 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Furnace Blowdown System | C | 2019-04-26 | IFD | OL1-2G42-5104 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1051-PFD-0030-5104 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Furnace Blowdown System | B | 2018-10-09 | IFD | OL1-2G42-5104 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1052-PFD-0030-5201 | Utility Flow Diagram - Olefins Unit 10 - 52 - Fuel System - Fuel Gas System | A | 2018-08-23 | IFA | OL1-2G42-5201 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1052-PFD-0030-5201 | Utility Flow Diagram - Olefins Unit 10 - 52 - Fuel System - Fuel Gas System | B | 2018-10-09 | IFD | OL1-2G42-5201 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1052-PFD-0030-5201 | Utility Flow Diagram - Olefins Unit 10 - 52 - Fuel System - Fuel Gas System | C | 2019-04-26 | IFD | OL1-2G42-5201 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1053-PFD-0030-5301 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Water Diagram | C | 2019-04-26 | IFD | OL1-2G42-5301 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1053-PFD-0030-5301 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Water Diagram | A | 2018-08-23 | IFA | OL1-2G42-5301 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1053-PFD-0030-5301 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Water Diagram | B | 2018-10-09 | IFD | OL1-2G42-5301 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1053-PFD-0030-5311 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Tower | A | 2018-08-23 | IFA | OL1-2G42-5311 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1053-PFD-0030-5311 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Tower | B | 2018-10-09 | IFD | OL1-2G42-5311 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1053-PFD-0030-5311 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Tower | C | 2019-04-26 | IFD | OL1-2G42-5311 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1054-PFD-0030-5401 | Utility Flow Diagram - Olefins Unit 10 - 54 - Air and Nitrogen System - Plant Air Instrument Air and Nitrogen Systems | B | 2018-10-09 | IFD | OL1-2G42-5401 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1054-PFD-0030-5401 | Utility Flow Diagram - Olefins Unit 10 - 54 - Air and Nitrogen System - Plant Air Instrument Air and Nitrogen Systems | C | 2019-04-26 | IFD | OL1-2G42-5401 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1054-PFD-0030-5401 | Utility Flow Diagram - Olefins Unit 10 - 54 - Air and Nitrogen System - Plant Air Instrument Air And Nitrogen Systems | A | 2018-08-23 | IFA | OL1-2G42-5401 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1055-PFD-0030-5501 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Flare And Blowdown System | A | 2018-08-23 | IFA | OL1-2G42-5501 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1055-PFD-0030-5501 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Flare and Blowdown System | C | 2019-04-26 | IFD | OL1-2G42-5501 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1055-PFD-0030-5501 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Flare and Blowdown System | B | 2018-10-09 | IFD | OL1-2G42-5501 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1055-PFD-0030-5502 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Process Vent Gas Collection | C | 2019-04-26 | IFD | OL1-2G42-5502 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1055-PFD-0030-5502 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Process Vent Gas Collection | A | 2018-08-23 | IFA | OL1-2G42-5502 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1055-PFD-0030-5502 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Process Vent Gas Collection | B | 2018-10-09 | IFD | OL1-2G42-5502 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1055-PFD-0030-5511 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - HP - LLDPE LP Flare | A | 2018-08-23 | IFA | OL1-2G42-5511 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1055-PFD-0030-5511 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - HP - LLDPE LP Flare | C | 2019-04-26 | IFD | OL1-2G42-5511 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1055-PFD-0030-5511 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - HP - LLDPE LP Flare | B | 2018-10-09 | IFD | OL1-2G42-5511 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1055-PFD-0030-5512 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Enclosed Ground Flare | B | 2018-10-09 | IFD | OL1-2G42-5512 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1055-PFD-0030-5512 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Enclosed Ground Flare | A | 2018-08-23 | IFA | OL1-2G42-5512 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1055-PFD-0030-5512 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Enclosed Ground Flare | C | 2019-04-26 | IFD | OL1-2G42-5512 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1056-PFD-0030-5601 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Collection | B | 2018-10-09 | IFD | OL1-2G42-5601 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1056-PFD-0030-5601 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Collection | C | 2019-04-26 | IFD | OL1-2G42-5601 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1056-PFD-0030-5601 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Collection | A | 2018-08-23 | IFA | OL1-2G42-5601 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1056-PFD-0030-5602 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Surface Runoff Collection | C | 2019-04-26 | IFD | OL1-2G42-5602 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1056-PFD-0030-5602 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Surface Runoff Collection | B | 2018-10-09 | IFD | OL1-2G42-5602 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1056-PFD-0030-5602 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Surface Runoff Collection | A | 2018-08-23 | IFA | OL1-2G42-5602 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1056-PFD-0030-5603 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Cracker Holding Basin | A | 2018-08-23 | IFA | OL1-2G42-5603 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1056-PFD-0030-5603 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Cracker Holding Basin | B | 2018-10-09 | IFD | OL1-2G42-5603 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1056-PFD-0030-5603 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Cracker Holding Basin | C | 2019-04-26 | IFD | OL1-2G42-5603 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1056-PFD-0030-5604 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Domestic Wastewater Collection | C | 2019-04-26 | IFD | OL1-2G42-5604 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1056-PFD-0030-5604 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Domestic Wastewater Collection | A | 2018-08-23 | IFA | OL1-2G42-5604 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1056-PFD-0030-5604 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Domestic Wastewater Collection | B | 2018-10-09 | IFD | OL1-2G42-5604 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1056-PFD-0030-5610 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - HP Flare Area SW & Oily WW Collection | B | 2018-10-09 | IFD | OL1-2G42-5610 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1056-PFD-0030-5610 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - HP Flare Area SW & Oily WW Collection | C | 2019-04-26 | IFD | OL1-2G42-5610 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1056-PFD-0030-5610 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - HP Flare Area SW & Oily WW Collection | A | 2018-08-23 | IFA | OL1-2G42-5610 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1056-PFD-0030-5611 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - OSBL Oily Wastewater Collection | C | 2019-04-26 | IFD | OL1-2G42-5611 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1056-PFD-0030-5611 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - OSBL Oily Wastewater Collection | A | 2018-08-23 | IFA | OL1-2G42-5611 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1056-PFD-0030-5611 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - OSBL Oily Wastewater Collection | B | 2018-10-09 | IFD | OL1-2G42-5611 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1056-PFD-0030-5612 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Equalization Tank | A | 2018-08-23 | IFA | OL1-2G42-5612 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1056-PFD-0030-5612 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Equalization Tank | B | 2018-10-09 | IFD | OL1-2G42-5612 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1056-PFD-0030-5612 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Equalization Tank | C | 2019-04-26 | IFD | OL1-2G42-5612 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1056-PFD-0030-5613 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - CPI & IGF Packages | B | 2018-10-09 | IFD | OL1-2G42-5613 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1056-PFD-0030-5613 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - CPI & IGF Packages | A | 2018-08-23 | IFA | OL1-2G42-5613 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1056-PFD-0030-5613 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - CPI & IGF Packages | C | 2019-04-26 | IFD | OL1-2G42-5613 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1056-PFD-0030-5614 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Biotreatment Package | C | 2019-04-26 | IFD | OL1-2G42-5614 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1056-PFD-0030-5614 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Biotreatment Package | B | 2018-10-09 | IFD | OL1-2G42-5614 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 3
036909C-1056-PFD-0030-5614 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Biotreatment Package | A | 2018-08-23 | IFA | OL1-2G42-5614 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1056-PFD-0030-5615 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Check Basin | A | 2018-08-23 | IFA | OL1-2G42-5615 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1056-PFD-0030-5615 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Check Basin | B | 2018-10-09 | IFD | OL1-2G42-5615 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1056-PFD-0030-5615 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Check Basin | C | 2019-04-26 | IFD | OL1-2G42-5615 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1056-PFD-0030-5616 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Sludge Dewatering Package | B | 2018-10-09 | IFD | OL1-2G42-5616 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1056-PFD-0030-5616 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Sludge Dewatering Package | A | 2018-08-23 | IFA | OL1-2G42-5616 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1056-PFD-0030-5616 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Sludge Dewatering Package | C | 2019-04-26 | IFD | OL1-2G42-5616 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1056-PFD-0030-5617 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Slop & Oil Sludge | A | 2018-08-23 | IFA | OL1-2G42-5617 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1056-PFD-0030-5617 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Slop & Oil Sludge | C | 2019-04-26 | IFD | OL1-2G42-5617 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1056-PFD-0030-5617 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Slop & Oil Sludge | B | 2018-10-09 | IFD | OL1-2G42-5617 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1059-PFD-0030-5901 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Chemical Storage | A | 2018-08-23 | IFA | OL1-2G42-5901 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1059-PFD-0030-5901 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Chemical Storage | C | 2019-04-26 | IFD | OL1-2G42-5901 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1059-PFD-0030-5901 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Chemical Storage | B | 2018-10-09 | IFD | OL1-2G42-5901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1059-PFD-0030-5911 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Complex U & O Chemical Storage | B | 2018-10-09 | IFD | OL1-2G42-5911 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1059-PFD-0030-5911 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Complex U & O Chemical Storage | C | 2019-04-26 | IFD | OL1-2G42-5911 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1059-PFD-0030-5911 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Complex U & O Chemical Storage | A | 2018-08-23 | IFA | OL1-2G42-5911 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1031-PFD-0010-3101 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration | C | 2019-04-26 | IFD | OL1-2G41-3101 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1031-PFD-0010-3101 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration | A | 2018-08-23 | IFA | OL1-2G41-3101 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1031-PFD-0010-3101 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration | B | 2018-10-09 | IFD | OL1-2G41-3101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1030-PFD-0010-3005 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation | B | 2018-10-09 | IFD | OL1-2G41-3005 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1030-PFD-0010-3005 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation | C | 2019-04-26 | IFD | OL1-2G41-3005 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1030-PFD-0010-3005 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation | A | 2018-08-23 | IFA | OL1-2G41-3005 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1030-PFD-0010-3004 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing | C | 2019-04-26 | IFD | OL1-2G41-3004 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1030-PFD-0010-3004 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing | B | 2018-10-09 | IFD | OL1-2G41-3004 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1030-PFD-0010-3004 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing | A | 2018-08-23 | IFA | OL1-2G41-3004 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1030-PFD-0010-3003 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier | B | 2018-10-09 | IFD | OL1-2G41-3003 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1030-PFD-0010-3003 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier | A | 2018-08-23 | IFA | OL1-2G41-3003 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1030-PFD-0010-3003 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier | C | 2019-04-26 | IFD | OL1-2G41-3003 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1030-PFD-0010-3002 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Evaporation | C | 2019-04-26 | IFD | OL1-2G41-3002 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1030-PFD-0010-3002 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Evaporation | B | 2018-10-09 | IFD | OL1-2G41-3002 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1030-PFD-0010-3002 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Evaporation | A | 2018-08-23 | IFA | OL1-2G41-3002 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1030-PFD-0010-3001 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation | A | 2018-08-23 | IFA | OL1-2G41-3001 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1030-PFD-0010-3001 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation | B | 2018-10-09 | IFD | OL1-2G41-3001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1030-PFD-0010-3001 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation | C | 2019-04-26 | IFD | OL1-2G41-3001 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1029-PFD-0010-2901 | Process Flow Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | A | 2018-08-23 | IFA | OL1-2G41-2901 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1029-PFD-0010-2901 | Process Flow Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | B | 2018-10-09 | IFD | OL1-2G41-2901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1029-PFD-0010-2901 | Process Flow Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | C | 2019-04-26 | IFD | OL1-2G41-2901 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1028-PFD-0010-2804 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | A | 2018-08-23 | IFA | OL1-2G41-2804 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1028-PFD-0010-2804 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | C | 2019-04-26 | IFD | OL1-2G41-2804 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1028-PFD-0010-2804 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | B | 2018-10-09 | IFD | OL1-2G41-2804 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1028-PFD-0010-2803 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | A | 2018-08-23 | IFA | OL1-2G41-2803 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1028-PFD-0010-2803 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | B | 2018-10-09 | IFD | OL1-2G41-2803 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1028-PFD-0010-2803 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | C | 2019-04-26 | IFD | OL1-2G41-2803 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1028-PFD-0010-2802 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | B | 2018-10-09 | IFD | OL1-2G41-2802 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1028-PFD-0010-2802 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | C | 2019-04-26 | IFD | OL1-2G41-2802 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1028-PFD-0010-2802 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | A | 2018-08-23 | IFA | OL1-2G41-2802 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1028-PFD-0010-2801 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | A | 2018-08-23 | IFA | OL1-2G41-2801 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1028-PFD-0010-2801 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | B | 2018-10-09 | IFD | OL1-2G41-2801 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1028-PFD-0010-2801 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | C | 2019-04-26 | IFD | OL1-2G41-2801 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1027-PFD-0010-2704 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation | C | 2019-04-26 | IFD | OL1-2G41-2704 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1027-PFD-0010-2704 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation | B | 2018-10-09 | IFD | OL1-2G41-2704 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1027-PFD-0010-2704 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation | A | 2018-08-23 | IFA | OL1-2G41-2704 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1027-PFD-0010-2703 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - Hydrog Reactivation Gas System | A | 2018-08-23 | IFA | OL1-2G41-2703 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1027-PFD-0010-2703 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - Hydrog Reactivation Gas System | B | 2018-10-09 | IFD | OL1-2G41-2703 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1027-PFD-0010-2703 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - Hydrog Reactivation Gas System | C | 2019-04-26 | IFD | OL1-2G41-2703 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1027-PFD-0010-2702 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Rerun Tower | C | 2019-04-26 | IFD | OL1-2G41-2702 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1027-PFD-0010-2702 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Rerun Tower | B | 2018-10-09 | IFD | OL1-2G41-2702 | PE | 2018-10-11 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1027-PFD-0010-2702 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Rerun Tower | A | 2018-08-23 | IFA | OL1-2G41-2702 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1027-PFD-0010-2701 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Reactor & Depentanizer | A | 2018-08-23 | IFA | OL1-2G41-2701 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1027-PFD-0010-2701 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Reactor & Depentanizer | C | 2019-04-26 | IFD | OL1-2G41-2701 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1027-PFD-0010-2701 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Reactor & Depentanizer | B | 2018-10-09 | IFD | OL1-2G41-2701 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1026-PFD-0010-2604 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | C | 2019-04-26 | IFD | OL1-2G41-2604 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1026-PFD-0010-2604 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | A | 2018-08-23 | IFA | OL1-2G41-2604 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1026-PFD-0010-2604 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | B | 2018-10-09 | IFD | OL1-2G41-2604 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1026-PFD-0010-2603 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | C | 2019-04-26 | IFD | OL1-2G41-2603 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1026-PFD-0010-2603 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | A | 2018-08-23 | IFA | OL1-2G41-2603 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1026-PFD-0010-2603 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | B | 2018-10-09 | IFD | OL1-2G41-2603 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1026-PFD-0010-2602 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | A | 2018-08-23 | IFA | OL1-2G41-2602 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1026-PFD-0010-2602 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | C | 2019-04-26 | IFD | OL1-2G41-2602 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1026-PFD-0010-2602 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | B | 2018-10-09 | IFD | OL1-2G41-2602 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1026-PFD-0010-2601 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | C | 2019-04-26 | IFD | OL1-2G41-2601 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1026-PFD-0010-2601 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | A | 2018-08-23 | IFA | OL1-2G41-2601 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1026-PFD-0010-2601 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | B | 2018-10-09 | IFD | OL1-2G41-2601 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1025-PFD-0010-2506 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | C | 2019-04-26 | IFD | OL1-2G41-2506 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1025-PFD-0010-2506 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | A | 2018-08-23 | IFA | OL1-2G41-2506 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1025-PFD-0010-2506 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | B | 2018-10-09 | IFD | OL1-2G41-2506 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1025-PFD-0010-2505 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | B | 2018-10-09 | IFD | OL1-2G41-2505 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1025-PFD-0010-2505 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | A | 2018-08-23 | IFA | OL1-2G41-2505 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1025-PFD-0010-2505 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | C | 2019-04-26 | IFD | OL1-2G41-2505 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1025-PFD-0010-2504 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | C | 2019-04-26 | IFD | OL1-2G41-2504 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1025-PFD-0010-2504 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | B | 2018-10-09 | IFD | OL1-2G41-2504 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1025-PFD-0010-2504 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | A | 2018-08-23 | IFA | OL1-2G41-2504 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1025-PFD-0010-2503 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | A | 2018-08-23 | IFA | OL1-2G41-2503 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1025-PFD-0010-2503 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | B | 2018-10-09 | IFD | OL1-2G41-2503 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1025-PFD-0010-2503 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | C | 2019-04-26 | IFD | OL1-2G41-2503 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1025-PFD-0010-2502 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | A | 2018-08-23 | IFA | OL1-2G41-2502 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1025-PFD-0010-2502 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | C | 2019-04-26 | IFD | OL1-2G41-2502 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1025-PFD-0010-2502 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | B | 2018-10-09 | IFD | OL1-2G41-2502 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1025-PFD-0010-2501 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | B | 2018-10-09 | IFD | OL1-2G41-2501 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1025-PFD-0010-2501 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | C | 2019-04-26 | IFD | OL1-2G41-2501 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1025-PFD-0010-2501 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | A | 2018-08-23 | IFA | OL1-2G41-2501 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1024-PFD-0010-2405 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | B | 2018-10-09 | IFD | OL1-2G41-2405 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1024-PFD-0010-2405 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | A | 2018-08-23 | IFA | OL1-2G41-2405 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1024-PFD-0010-2405 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | C | 2019-04-26 | IFD | OL1-2G41-2405 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1024-PFD-0010-2404 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | A | 2018-08-23 | IFA | OL1-2G41-2404 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1024-PFD-0010-2404 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | B | 2018-10-09 | IFD | OL1-2G41-2404 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1024-PFD-0010-2404 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | C | 2019-04-26 | IFD | OL1-2G41-2404 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1024-PFD-0010-2403 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | C | 2019-04-26 | IFD | OL1-2G41-2403 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1024-PFD-0010-2403 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | A | 2018-08-23 | IFA | OL1-2G41-2403 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1024-PFD-0010-2403 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | B | 2018-10-09 | IFD | OL1-2G41-2403 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1024-PFD-0010-2402 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | A | 2018-08-23 | IFA | OL1-2G41-2402 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1024-PFD-0010-2402 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | B | 2018-10-09 | IFD | OL1-2G41-2402 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1024-PFD-0010-2402 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | C | 2019-04-26 | IFD | OL1-2G41-2402 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1024-PFD-0010-2401 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | B | 2018-10-09 | IFD | OL1-2G41-2401 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1024-PFD-0010-2401 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | A | 2018-08-23 | IFA | OL1-2G41-2401 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1024-PFD-0010-2401 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | C | 2019-04-26 | IFD | OL1-2G41-2401 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1023-PFD-0010-2305 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | A | 2018-08-23 | IFA | OL1-2G41-2305 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1023-PFD-0010-2305 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | B | 2018-10-09 | IFD | OL1-2G41-2305 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1023-PFD-0010-2305 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | C | 2019-04-26 | IFD | OL1-2G41-2305 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1023-PFD-0010-2304 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | B | 2018-10-09 | IFD | OL1-2G41-2304 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1023-PFD-0010-2304 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | A | 2018-08-23 | IFA | OL1-2G41-2304 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1023-PFD-0010-2303 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | C | 2019-04-26 | IFD | OL1-2G41-2303 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1023-PFD-0010-2303 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | B | 2018-10-09 | IFD | OL1-2G41-2303 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1023-PFD-0010-2303 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | A | 2018-08-23 | IFA | OL1-2G41-2303 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1023-PFD-0010-2302 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | C | 2019-04-26 | IFD | OL1-2G41-2302 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1023-PFD-0010-2302 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | A | 2018-08-23 | IFA | OL1-2G41-2302 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1023-PFD-0010-2302 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | B | 2018-10-09 | IFD | OL1-2G41-2302 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1023-PFD-0010-2301 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | C | 2019-04-26 | IFD | OL1-2G41-2301 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1023-PFD-0010-2301 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | B | 2018-10-09 | IFD | OL1-2G41-2301 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1023-PFD-0010-2301 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | A | 2018-08-23 | IFA | OL1-2G41-2301 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1022-PFD-0010-2201 | Process Flow Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | C | 2019-04-26 | IFD | OL1-2G41-2201 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1022-PFD-0010-2201 | Process Flow Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | A | 2018-08-23 | IFA | OL1-2G41-2201 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1022-PFD-0010-2201 | Process Flow Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | B | 2018-10-09 | IFD | OL1-2G41-2201 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1021-PFD-0010-2103 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | A | 2018-08-23 | IFA | OL1-2G41-2103 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1021-PFD-0010-2103 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | C | 2019-04-26 | IFD | OL1-2G41-2103 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1021-PFD-0010-2103 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | B | 2018-10-09 | IFD | OL1-2G41-2103 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1021-PFD-0010-2102 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | B | 2018-10-09 | IFD | OL1-2G41-2102 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1021-PFD-0010-2102 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | A | 2018-08-23 | IFA | OL1-2G41-2102 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1021-PFD-0010-2102 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | C | 2019-04-26 | IFD | OL1-2G41-2102 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1021-PFD-0010-2101 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | A | 2018-08-23 | IFA | OL1-2G41-2101 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1021-PFD-0010-2101 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | C | 2019-04-26 | IFD | OL1-2G41-2101 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1021-PFD-0010-2101 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | B | 2018-10-09 | IFD | OL1-2G41-2101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1020-PFD-0010-2002 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | A | 2018-08-23 | IFA | OL1-2G41-2002 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1020-PFD-0010-2002 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | C | 2019-04-26 | IFD | OL1-2G41-2002 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1020-PFD-0010-2002 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | B | 2018-10-09 | IFD | OL1-2G41-2002 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1020-PFD-0010-2001 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | A | 2018-08-23 | IFA | OL1-2G41-2001 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1020-PFD-0010-2001 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | C | 2019-04-26 | IFD | OL1-2G41-2001 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1020-PFD-0010-2001 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | B | 2018-10-09 | IFD | OL1-2G41-2001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1019-PFD-0010-1902 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | B | 2018-10-09 | IFD | OL1-2G41-1902 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1019-PFD-0010-1902 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | C | 2019-04-26 | IFD | OL1-2G41-1902 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1019-PFD-0010-1902 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | A | 2018-08-23 | IFA | OL1-2G41-1902 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1019-PFD-0010-1901 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | B | 2018-10-09 | IFD | OL1-2G41-1901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1019-PFD-0010-1901 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | C | 2019-04-26 | IFD | OL1-2G41-1901 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1019-PFD-0010-1901 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | A | 2018-08-23 | IFA | OL1-2G41-1901 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1012-PFD-0010-1201 | Process Flow Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | B | 2018-10-09 | IFD | OL1-2G41-1201 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1012-PFD-0010-1201 | Process Flow Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | C | 2019-04-26 | IFD | OL1-2G41-1201 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1012-PFD-0010-1201 | Process Flow Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | A | 2018-08-23 | IFA | OL1-2G41-1201 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1011-PFD-0010-1101 | Process Flow Diagram - Olefins Unit 10 - 11 - Furnaces - Recycle Gas Cracking Furnace | B | 2018-10-09 | IFD | OL1-2G41-1101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1011-PFD-0010-1101 | Process Flow Diagram - Olefins Unit 10 - 11 - Furnaces - Recycle Gas Cracking Furnace | A | 2018-08-23 | IFA | OL1-2G41-1101 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1011-PFD-0010-1101 | Process Flow Diagram - Olefins Unit 10 - 11 - Furnaces - Recycle Gas Cracking Furnace | C | 2019-04-26 | IFD | OL1-2G41-1101 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1010-PFD-0010-1003 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | A | 2018-08-23 | IFA | OL1-2G41-1003 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1010-PFD-0010-1003 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | B | 2018-10-09 | IFD | OL1-2G41-1003 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1010-PFD-0010-1003 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | C | 2019-04-26 | IFD | OL1-2G41-1003 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1010-PFD-0010-1001 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | C | 2019-04-26 | IFD | OL1-2G41-1001 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1010-PFD-0010-1001 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | B | 2018-10-09 | IFD | OL1-2G41-1001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1010-PFD-0010-1001 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | A | 2018-08-23 | IFA | OL1-2G41-1001 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1000-PFD-0010-0010 | Block Flow Diagram - Olefins Unit 10 - 00-General - Overall Plant Scheme | A | 2018-08-23 | IFA | OL1-2G40-0010 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1000-PFD-0010-0010 | Block Flow Diagram - Olefins Unit 10 - 00-General - Overall Plant Scheme | C | 2019-04-26 | IFD | OL1-2G40-0010 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516 | IFA | 2019-05-14 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1000-PFD-0010-0010 | Block Flow Diagram - Olefins Unit 10 - 00-General - Overall Plant Scheme | B | 2018-10-09 | IFD | OL1-2G40-0010 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1000-PFD-0010-0002 | Process Flow Diagram - Olefins Unit 10 - 00-General - Drawing Index | B | 2018-10-09 | IFD | OL1-2G41-0002 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1000-PFD-0010-0002 | Process Flow Diagram - Olefins Unit 10 - 00-General - Drawing Index | C | 2019-04-26 | IFD | OL1-2G41-0002 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1000-PFD-0010-0002 | Process Flow Diagram - Olefins Unit 10 - 00-General - Drawing Index | A | 2018-08-23 | IFA | OL1-2G41-0002 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1000-PFD-0010-0001 | Process Flow Diagram - Olefins Unit 10 - 00-General - Legend & Symbols | A | 2018-08-23 | IFA | OL1-2G41-0001 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | 2018-08-24 | 1
036909C-1000-PFD-0010-0001 | Process Flow Diagram - Olefins Unit 10 - 00-General - Legend & Symbols | C | 2019-04-26 | IFD | OL1-2G41-0001 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1000-PFD-0010-0001 | Process Flow Diagram - Olefins Unit 10 - 00-General - Legend & Symbols | B | 2018-10-09 | IFD | OL1-2G41-0001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155, ROC-TPSK-CECO-T-00002 | IFI |  | 2018-12-27 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00155 |  | 2018-10-11 | 1
036909C-1024-SP-0910-2453 | Mechanical Equipment Datasheet - LP Depropanizer Reflux-Product Pump | 0 | 2019-08-09 | IFP | OL1-2M03-2453 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-13 | 2
036909C-1024-SP-0910-2416 | MECHANICAL EQUIPMENT DATASHEET - CG Liquid Dryer Feed Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2416 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-13 | 2
036909C-1024-SP-0910-2443 | MECHANICAL EQUIPMENT DATASHEET - HP Deprop Reboiler Cond Pump | 0 | 2019-08-09 | IFP | OL1-2M03-2443 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-13 | 2
036909C-1023-SP-0910-2302 | MECHANICAL EQUIPMENT DATASHEET - Strong Caustic Circulating Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2302 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-13 | 2
036909C-1023-SP-0910-2306 | MECHANICAL EQUIPMENT DATASHEET - Weak Caustic Circulating Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2306 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-13 | 2
036909C-1023-SP-0910-2304 | MECHANICAL EQUIPMENT DATASHEET - Intermediate Caustic Circulating Pump | 0 | 2019-08-09 | IFP | OL1-2M03-2304 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-13 | 2
036909C-1023-SP-0910-2321 | MECHANICAL EQUIPMENT DATASHEET - Spent Caustic Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2321 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-13 | 2
036909C-1023-SP-0910-2393 | MECHANICAL EQUIPMENT DATASHEET - Spent Caustic Drain Drum Pump | 0 | 2019-08-09 | IFP | OL1-2M03-2393 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-13 | 2
036909C-1023-SP-0910-2391 | Mechanical Equipment Datasheet - Caustic Drain Drum Pump | 0 | 2019-08-09 | IFP | OL1-2M03-2391 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-13 | 2
036909C-1023-SP-0910-2311 | MECHANICAL EQUIPMENT DATASHEET - Wash Oil Circulating Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2311 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-13 | 2
036909C-1000-JSD-2200-01 | Job Design Specification For Thermal Insulation (Hot Service) | B | 2018-12-18 | IFR | OL1-2R04-0003 | MP | 2018-12-27 | 036909C-JVD-TRN-00562 | 036909C-JVD-TRN-00562, ROC-TPSK-CECO-T-00004 | IFR | 2019-01-11 | 2019-01-17 | R2-Comments as noted | TPSK-LSPA1-T-MP-00562 |  | 2018-12-27 | 2
036909C-1000-DW-1920-0001 | Hazardous Area Classification - Overall | A | 2019-03-07 | IFA | OL1-2L42-0001 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015, ROC-TPSK-CECO-T-00013_1 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-105W-DW-1920-0001 | Hazardous Area Classification - Zone 5W - Waste Water Treatment | A | 2019-03-07 | IFA | OL1-2L42-0017 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-1056-PDS-2600-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg | F | 2019-08-01 | IFD | OL1-2G30-5650 | PE | 2019-08-02 | 036909C-JVD-TRN-02327 | 036909C-JVD-TRN-02327 | IFR | 2019-08-17 |  | Transmitted | TPSK-LSPA1-T-PE-02327 |  | 2019-08-05 | 2
036909C-1056-PDS-2600-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package | F | 2019-08-01 | IFD | OL1-2G30-5644 | PE | 2019-08-02 | 036909C-JVD-TRN-02327 | 036909C-JVD-TRN-02327 | IFR | 2019-08-17 |  | Transmitted | TPSK-LSPA1-T-PE-02327 |  | 2019-08-05 | 2
036909C-1056-PDS-2600-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg | F | 2019-08-01 | IFD | OL1-2G30-5670 | PE | 2019-08-02 | 036909C-JVD-TRN-02327 | 036909C-JVD-TRN-02327 | IFR | 2019-08-17 |  | Transmitted | TPSK-LSPA1-T-PE-02327 |  | 2019-08-05 | 2
036909C-1056-PDS-0200-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg | F | 2019-08-01 | IFD | OL1-2G30-5653 | PE | 2019-08-02 | 036909C-JVD-TRN-02327 | 036909C-JVD-TRN-02327 | IFR | 2019-08-17 |  | Transmitted | TPSK-LSPA1-T-PE-02327 |  | 2019-08-05 | 2
036909C-1024-SP-0910-2453 | Mechanical Equipment Datasheet - LP Depropanizer Reflux-Product Pump | A | 2018-11-08 | IFQ | OL1-2M03-2453 | ME | 2018-11-08 | 036909C-JVD-TRN-00294 | 036909C-JVD-TRN-00294 | IFR | 2018-11-22 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00294 |  | 2018-11-08 | 2
036909C-1024-SP-0910-2443 | Mechanical Equipment Datasheet - HP Deprop Reboiler Cond Pump | A | 2018-12-05 | IFQ | OL1-2M03-2443 | ME | 2018-12-13 | 036909C-JVD-TRN-00494 | 036909C-JVD-TRN-00494 | IFR | 2018-12-26 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00494 |  | 2018-12-13 | 2
036909C-1024-SP-0910-2416 | Mechanical Equipment Datasheet - CG Liquid Dryer Feed Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2416 | ME | 2018-12-05 | 036909C-JVD-TRN-00413 | 036909C-JVD-TRN-00413 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00413 |  | 2018-12-05 | 2
036909C-1023-SP-0910-2391 | Mechanical Equipment Datasheet - Caustic Drain Drum Pump | A | 2018-12-13 | IFQ | OL1-2M03-2391 | ME | 2018-12-17 | 036909C-JVD-TRN-00511 | 036909C-JVD-TRN-00511 | IFR | 2018-12-31 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00511 |  | 2018-12-17 | 2
036909C-1023-SP-0910-2306 | Mechanical Equipment Datasheet - Weak Caustic Circulating Pumps | A | 2018-11-13 | IFQ | OL1-2M03-2306 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320 | IFR | 2018-11-29 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00320 |  | 2018-11-15 | 2
036909C-1023-SP-0910-2304 | Mechanical Equipment Datasheet - Intermediate Caustic Circulating Pump | A | 2018-11-13 | IFQ | OL1-2M03-2304 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320 | IFR | 2018-11-29 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00320 |  | 2018-11-15 | 2
036909C-1022-TDS-0610-2241 | Mechanical Equipment Data Sheet - 10-E-2240 - CG 4th Stage Aftercooler | 0 | 2019-06-24 | IFP | OL1-2M03-2241 | ME | 2019-07-16 | 036909C-JVD-TRN-02163 | 036909C-JVD-TRN-02163 | IFR | 2019-07-31 | 2019-08-12 | R1-No comments | TPSK-LSPA1-T-ME-02163 |  | 2019-07-17 | 2
036909C-1021-TDS-0610-2165 | Mechanical Equipment Data Sheet - 10-E-2165 A-D - LPG Feed Heater | 0 | 2019-06-24 | IFQ | OL1-2M03-2165 | ME | 2019-07-16 | 036909C-JVD-TRN-02163 | 036909C-JVD-TRN-02163 | IFR | 2019-07-31 | 2019-08-12 | R1-No comments | TPSK-LSPA1-T-ME-02163 |  | 2019-07-17 | 2
036909C-103S-DW-0051-0001 | Detail Plot Plan- Zone 3S - Electrical Sub-Station & Far C | B | 2019-08-06 | IBD | OL1-2P06-0005 | MP | 2019-08-08 | 036909C-JVD-TRN-02386 | 036909C-JVD-TRN-02386 | IFR | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-MP-02386 |  | 2019-08-09 | 2
036909C-102B-DW-1743-0033 | Foundation For 10-E-2100 | A | 2019-08-06 | IFR | OL1-2K31-0200 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-013 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Beams | A | 2019-08-02 | IFR | OL1-2K31-1312 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-012 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Beams | A | 2019-08-02 | IFR | OL1-2K31-1311 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-002 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Plans | A | 2019-08-02 | IFR | OL1-2K31-1301 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0001-002 | Piperack 10-PRK-2A01 Foundation (Formwork and Reinforcement) | A | 2019-08-02 | IFR | OL1-2K31-1281 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-003 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Plans | A | 2019-08-02 | IFR | OL1-2K31-1302 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-014 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Beams | A | 2019-08-02 | IFR | OL1-2K31-1313 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-015 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Beams | A | 2019-08-02 | IFR | OL1-2K31-1314 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0001-001 | Piperack 10-PRK-2A01 Foundation (Formwork and Reinforcement) | A | 2019-08-02 | IFR | OL1-2K31-1280 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-100S-DW-0051-0001 | Detail Plot Plan- Zone 0S - Electrical Sub-Station & Far E | B | 2019-08-06 | IBD | OL1-2P06-0004 | MP | 2019-08-08 | 036909C-JVD-TRN-02386 | 036909C-JVD-TRN-02386 | IFR | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-MP-02386 |  | 2019-08-09 | 2
036909C-1000-MS-1430-0001 | Technical Specification For Piles | 0 | 2019-08-02 | IFP | OL1-2R02-0101 | CV | 2019-08-08 | 036909C-JVD-TRN-02385 | 036909C-JVD-TRN-02385 | IFR | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02385 |  | 2019-08-09 | 2
036909C-1000-DW-0051-0001 | General Plot Plan | D | 2019-08-06 | IBD | OL1-2P06-0001 | MP | 2019-08-08 | 036909C-JVD-TRN-02386 | 036909C-JVD-TRN-02386 | IFR | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-MP-02386 |  | 2019-08-09 | 2
036909C-1028-SP-1513-2801 | Complex Loop Narratives - Area 28 - Refrigeration System | A | 2019-05-30 | IFR | OL1-2I71-2801 | IE | 2019-05-30 | 036909C-JVD-TRN-01778 | 036909C-JVD-TRN-01778 | IFR | 2019-06-14 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-IE-01778 |  | 2019-05-31 | 2
036909C-105U-DW-1920-0001 | Hazardous Area Classification - Zone 5U - Utilities | A | 2019-03-07 | IFA | OL1-2L42-0016 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-1000-JSD-2200-02 | Job Design Specification For Thermal Insulation (Cold Service) | B | 2018-12-18 | IFR | OL1-2R04-0004 | MP | 2018-12-27 | 036909C-JVD-TRN-00562 | 036909C-JVD-TRN-00562, ROC-TPSK-CECO-T-00003 | IFR | 2019-01-11 | 2019-01-17 | R2-Comments as noted | TPSK-LSPA1-T-MP-00562 |  | 2018-12-27 | 2
036909C-1000-JSD-2200-02 | Job Design Specification For Thermal Insulation (Cold Service) | A | 2018-08-22 | IFR | OL1-2R04-0004 | MP | 2018-08-22 | 036909C-JVD-TRN-00024 | 036909C-JVD-TRN-00024 | IFR | 2018-09-05 | 2018-09-12 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00024 |  | 2018-08-23 | 2
036909C-1000-JSD-2200-01 | Job design specification for thermal insulation (hot service) | A | 2018-08-22 | IFR | OL1-2R04-0003 | MP | 2018-08-22 | 036909C-JVD-TRN-00024 | 036909C-JVD-TRN-00024 | IFR | 2018-09-05 | 2018-09-12 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00024 |  | 2018-08-23 | 2
036909C-1000-JSD-1300-0001 | Piping Class Summary And Piping Classes - Includes ex doc. OL1-2P92-0003 as attachment | A | 2018-12-20 | IFR | OL1-2R04-0001 | MP | 2018-12-27 | 036909C-JVD-TRN-00562 | 036909C-JVD-TRN-00562, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-01-11 | 2019-01-17 | R2-Comments as noted | TPSK-LSPA1-T-MP-00562 | Includes ex doc. OL1-2P92-0003 as attachment | 2018-12-27 | 2
036909C-103S-DW-0051-0001 | Detail Plot Plan - Zone 3S - Electrical Sub-Station And Far C | A | 2019-02-15 | IFR | OL1-2P06-0005 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15 | 1
036909C-100S-DW-0051-0001 | Detail Plot Plan - Zone 0S - Electrical Sub-Station And Far E | A | 2019-02-15 | IFR | OL1-2P06-0004 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15 | 1
036909C-1000-DW-0051-0001 | General Plot Plan - Draft | A | 2019-02-15 | IFR | OL1-2P06-0001 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15 | 1
036909C-102B-CN-1834-0001 | Calculation For Steel Platform For 10-PIT-2190 | A | 2019-07-31 | IFR | OL1-2K15-0094 | CV | 2019-08-01 | 036909C-JVD-TRN-02312 | 036909C-JVD-TRN-02312 | IFA | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-CV-02312 |  | 2019-08-05 | 1
036909C-1027-TDS-0630-2727 | Mechanical Equipment Data Sheet - 10-E-2726 - Pygas Fuel Oil Cooler | B | 2019-05-20 | IFQ | OL1-2M03-2727 | ME | 2019-05-24 | 036909C-JVD-TRN-01743 | 036909C-JVD-TRN-01743 | IFR | 2019-06-10 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01743 |  | 2019-05-27 | 2
036909C-1027-TDS-0630-2723 | Mechanical Equipment Data Sheet - 10-E-2724 - Wash Oil Condenser | B | 2019-05-20 | IFQ | OL1-2M03-2723 | ME | 2019-05-24 | 036909C-JVD-TRN-01743 | 036909C-JVD-TRN-01743 | IFR | 2019-06-10 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01743 |  | 2019-05-27 | 2
036909C-1027-TDS-0630-2716 | Mechanical Equipment Data Sheet - 10-E-2714 - C5 Cut Cooler | B | 2019-05-17 | IFQ | OL1-2M03-2716 | ME | 2019-05-24 | 036909C-JVD-TRN-01743 | 036909C-JVD-TRN-01743 | IFR | 2019-06-10 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01743 |  | 2019-05-27 | 2
036909C-1023-TDS-0630-2326 | Mechanical Equipment Data Sheet - 10-E-2326 - Spent Caustic Stripper Feed Heater | A | 2019-01-22 | IFQ | OL1-2M03-2326 | ME | 2019-01-28 | 036909C-JVD-TRN-00740 | 036909C-JVD-TRN-00740, ROC-TPSK-CECO-T-00017 | IFR | 2019-02-11 | 2019-02-28 | R2-Comments as noted | TPSK-LSPA1-T-ME-00740 |  | 2019-01-28 | 2
036909C-1056-PDS-2500-5640 | Process Equipment Datasheet - 10-TK-5640 - Oily Wastewater Tank | B | 2019-03-26 | IFD | OL1-2G30-5640 | PE | 2019-03-27 | 036909C-JVD-TRN-01176 | 036909C-JVD-TRN-01176 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01176 |  | 2019-03-28 | 2
036909C-1056-PDS-2500-5640 | Process Equipment Datasheet - 10-TK-5640 - Oily Wastewater Tank | A | 2019-02-05 | IFR | OL1-2G30-5640 | PE | 2019-02-06 | 036909C-JVD-TRN-00809 | 036909C-JVD-TRN-00809 | IFR | 2019-02-19 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-PE-00809 |  | 2019-02-06 | 2
036909C-1056-PDS-2500-5676 | Process Equipment Datasheet - 10-TK-5676 - Oily Sludge Tank | A | 2019-02-05 | IFR | OL1-2G30-5676 | PE | 2019-02-06 | 036909C-JVD-TRN-00809 | 036909C-JVD-TRN-00809, ROC-TPSK-CECO-T-00020 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00809 |  | 2019-02-06 | 2
036909C-1056-PDS-2500-5675 | Process Equipment Datasheet - 10-TK-5675 A-B - Slop Oil Tanks | A | 2019-02-05 | IFR | OL1-2G30-5675 | PE | 2019-02-06 | 036909C-JVD-TRN-00809 | 036909C-JVD-TRN-00809, ROC-TPSK-CECO-T-00020 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00809 |  | 2019-02-06 | 2
036909C-1056-PDS-0900-5652 | Process Equipment Datasheet - 10-P-5653 - Bio Equalization Pit Sludge Pump | A | 2019-05-29 | IFR | OL1-2G30-5652 | PE | 2019-05-30 | 036909C-JVD-TRN-01775 | 036909C-JVD-TRN-01775 | IFR | 2019-06-14 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE--01775 |  | 2019-05-31 | 2
036909C-1056-PDS-0900-5643 | Process Equipment Datasheet - 10-P-5642 A-B - Cooling Water BD Basin Pumps | A | 2019-02-05 | IFR | OL1-2G30-5643 | PE | 2019-02-06 | 036909C-JVD-TRN-00810 | 036909C-JVD-TRN-00810, ROC-TPSK-CECO-T-00020 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00810 |  | 2019-02-06 | 2
036909C-1050-PDS-1390-5001 | Piping Specialty Item - Datasheet - Safety Shower and Eye Station - Area 50 - SS-50001 | A | 2019-07-27 | IFR | OL1-2P03-5001 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 |  | Transmitted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1022-SP-0810-2230 | Mechanical Equipment Data Sheet CG 3rd Stage Suction Drum | 0 | 2019-07-03 | IFP | OL1-2M03-2230 | ME | 2019-07-08 | 036909C-JVD-TRN-02102 | 036909C-JVD-TRN-02102 | IFR | 2019-07-23 | 2019-08-07 | R1-No comments | TPSK-LSPA1-T-ME-02102 |  | 2019-07-08 | 2
036909C-1022-SP-0810-2220 | Mechanical Equipment Data Sheet CG 2nd Stage Suction Drum | 0 | 2019-07-03 | IFP | OL1-2M03-2220 | ME | 2019-07-08 | 036909C-JVD-TRN-02102 | 036909C-JVD-TRN-02102 | IFR | 2019-07-23 | 2019-08-07 | R1-No comments | TPSK-LSPA1-T-ME-02102 |  | 2019-07-09 | 2
036909C-1057-PID-0031-5706 | P&ID - FIRE WATER NETWORK (6/6) | B | 2019-05-08 | IFR | OL1-2L40-5706 | SE | 2019-05-09 | 036909C-JVD-TRN-01622 | 036909C-JVD-TRN-01622 | IFR | 2019-05-23 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-SE-01622 |  | 2019-05-09 | 2
036909C-1057-PID-0031-5705 | P&ID - FIRE WATER NETWORK (5/6) | B | 2019-05-08 | IFR | OL1-2L40-5705 | SE | 2019-05-09 | 036909C-JVD-TRN-01622 | 036909C-JVD-TRN-01622 | IFR | 2019-05-23 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-SE-01622 |  | 2019-05-09 | 2
036909C-1057-PID-0031-5703 | P&ID - FIRE WATER NETWORK (3/6) | B | 2019-05-08 | IFR | OL1-2L40-5703 | SE | 2019-05-09 | 036909C-JVD-TRN-01622 | 036909C-JVD-TRN-01622 | IFR | 2019-05-23 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-SE-01622 |  | 2019-05-09 | 2
036909C-1000-NM-0050-0001 | Battery limit Summary | C | 2019-07-01 | IFD | OL1-2G60-0001 | PE | 2019-07-03 | 036909C-JVD-TRN-02069 | 036909C-JVD-TRN-02069 | IFR | 2019-07-18 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-PE-02069 |  | 2019-07-04 | 2
036909C-1057-PID-0031-5702 | P&ID - FIRE WATER NETWORK (2/6) | B | 2019-05-08 | IFR | OL1-2L40-5702 | SE | 2019-05-09 | 036909C-JVD-TRN-01622 | 036909C-JVD-TRN-01622 | IFR | 2019-05-23 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-SE-01622 |  | 2019-05-09 | 2
036909C-1057-PID-0031-5701 | P&ID - FIRE WATER NETWORK (1/6) | B | 2019-05-08 | IFR | OL1-2L40-5701 | SE | 2019-05-09 | 036909C-JVD-TRN-01622 | 036909C-JVD-TRN-01622 | IFR | 2019-05-23 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-SE-01622 |  | 2019-05-09 | 2
036909C-1028-SP-0810-2840 | Mechanical Equipment Data Sheet C3R 4TH Stage Suction Drum | 0 | 2019-07-03 | IFP | OL1-2M03-2840 | ME | 2019-07-08 | 036909C-JVD-TRN-02102 | 036909C-JVD-TRN-02102 | IFR | 2019-07-23 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02102 |  | 2019-07-08 | 2
036909C-1055-SP-0810-5565 | Mechanical Equipment Data Sheet for Polyolefins Flare Knock-Out Drum | 0 | 2019-07-11 | IFP | OL1-2M03-5565 | ME | 2019-07-11 | 036909C-JVD-TRN-02138 | 036909C-JVD-TRN-02138 | IFR | 2019-07-26 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02138 |  | 2019-07-15 | 2
036909C-1027-TDS-0610-2763 | Mechanical Equipment Data Sheet - 10-E-2760 - C4/C5 HYDRO VENT CONDENSER | 0 | 2019-06-25 | IFP | OL1-2M03-2763 | ME | 2019-07-11 | 036909C-JVD-TRN-02140 | 036909C-JVD-TRN-02140 | IFR | 2019-07-26 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02140 |  | 2019-07-15 | 2
036909C-1028-SP-0810-2805 | Mechanical Equipment Data Sheet C3R Surge Drum | 0 | 2019-07-12 | IFP | OL1-2M03-2805 | HOC Mech | 2019-07-16 | 036909C-JVD-TRN-02166 | 036909C-JVD-TRN-02166 | IFR | 2019-07-31 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02166 |  | 2019-07-16 | 2
036909C-1027-SP-0810-2762 | Mechanical Equipment Data Sheet For C4 C5 hydrog Recycle Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2762 | ME | 2019-07-17 | 036909C-JVD-TRN-02177 | 036909C-JVD-TRN-02177 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02177 |  | 2019-07-18 | 2
036909C-1027-SP-0810-2724 | Mechanical Equipment Data Sheet For Wash Oil Degassing Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2724 | ME | 2019-07-17 | 036909C-JVD-TRN-02176 | 036909C-JVD-TRN-02176 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02176 |  | 2019-07-17 | 2
036909C-1027-SP-0810-2718 | Mechanical Equipment Data Sheet For Rerun Tower Reflux Drum | 0 | 2019-07-12 | IFP | OL1-2M03-2718 | HOC Mech | 2019-07-16 | 036909C-JVD-TRN-02166 | 036909C-JVD-TRN-02166 | IFR | 2019-07-31 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02166 |  | 2019-07-16 | 2
036909C-1026-SP-0810-2662 | Mechanical Equipment Data Sheet Debutanizer Reflux Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2662 | ME | 2019-07-17 | 036909C-JVD-TRN-02176 | 036909C-JVD-TRN-02176 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02176 |  | 2019-07-17 | 2
036909C-1026-SP-0810-2632 | Mechanical Equipment Data Sheet For Secondary Deeth Reflux Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2632 | ME | 2019-07-17 | 036909C-JVD-TRN-02173 | 036909C-JVD-TRN-02173 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02173 |  | 2019-07-18 | 2
036909C-1026-SP-0810-2622 | Mechanical Equipment Data Sheet for C3 Hydrog Recycle Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2622 | ME | 2019-07-17 | 036909C-JVD-TRN-02173 | 036909C-JVD-TRN-02173 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02173 |  | 2019-07-18 | 2
036909C-1025-SP-0810-2504 | Mechanical Equipment Data Sheet Demeth Prefrac Feed Separator No. 1 | 0 | 2019-07-12 | IFP | OL1-2M03-2504 | HOC Mech | 2019-07-16 | 036909C-JVD-TRN-02166 | 036909C-JVD-TRN-02166 | IFR | 2019-07-31 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02166 |  | 2019-07-16 | 2
036909C-1027-SP-0810-2735 | Mechanical Equipment Data Sheet For Regen Hydrog Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2735 | ME | 2019-07-17 | 036909C-JVD-TRN-02176 | 036909C-JVD-TRN-02176 | IFR | 2019-08-01 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02176 |  | 2019-07-18 | 2
036909C-1059-SP-2510-5950 | Mechanical Equipment Data Sheet For Sodium Hypochlorite Tank | B | 2019-06-28 | IFQ | OL1-2M03-5950 | ME | 2019-07-05 | 036909C-JVD-TRN-02086 | 036909C-JVD-TRN-02086 | IFR | 2019-07-20 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02086 |  | 2019-07-08 | 2
036909C-1029-SP-0810-2932 | Mechanical Equipment Data Sheet for Methanol Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2932 | ME | 2019-07-16 | 036909C-JVD-TRN-02167 | 036909C-JVD-TRN-02167 | IFR | 2019-07-31 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02167 |  | 2019-07-17 | 2
036909C-1028-TDS-0610-2856 | Mechanical Equipment Data Sheet - 10-E-2855 - C2R Condenser | 0 | 2019-06-26 | IFP | OL1-2M03-2856 | ME | 2019-07-15 | 036909C-JVD-TRN-02153 | 036909C-JVD-TRN-02153 | IFR | 2019-07-30 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02153 |  | 2019-07-16 | 2
036909C-1028-TDS-0610-2806 | Mechanical Equipment Data Sheet - 10-E-2805A-C - C3 Refrig Condensers | 0 | 2019-06-24 | IFP | OL1-2M03-2806 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-18 | 2
036909C-1027-TDS-0610-2707 | Mechanical Equipment Data Sheet - 10-E-2706 - GHU-1 Cooler | 0 | 2019-07-02 | IFP | OL1-2M03-2707 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-17 | 2
036909C-1026-TDS-0610-2661 | Mechanical Equipment Data Sheet - 10-E-2660 - Debutanizer Condenser | 0 | 2019-06-25 | IFP | OL1-2M03-2661 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-18 | 2
036909C-1026-TDS-0610-2645 | Mechanical Equipment Data Sheet - 10-E-2645 - C3 Tower Reboilers | 0 | 2019-06-26 | IFP | OL1-2M03-2645 | ME | 2019-07-15 | 036909C-JVD-TRN-02153 | 036909C-JVD-TRN-02153 | IFR | 2019-07-30 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02153 |  | 2019-07-16 | 2
036909C-1025-TDS-0610-2548 | Mechanical Equipment Data Sheet - 10-E-2548 - Demethanizer Bottoms Vaporizer | 0 | 2019-07-03 | IFP | OL1-2M03-2548 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-17 | 2
036909C-1025-TDS-0610-2545 | Mechanical Equipment Data Sheet - 10-E-2545 - Demethanizer Reboiler | 0 | 2019-06-25 | IFP | OL1-2M03-2545 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-17 | 2
036909C-1025-TDS-0610-2515 | Mechanical Equipment Data Sheet - 10-E-2515- Demeth Prefrac Reboiler | 0 | 2019-06-25 | IFP | OL1-2M03-2515 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-17 | 2
036909C-1025-TDS-0610-2503 | Mechanical Equipment Data Sheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | 0 | 2019-06-24 | IFP | OL1-2M03-2503 | ME | 2019-07-16 | 036909C-JVD-TRN-02163 | 036909C-JVD-TRN-02163 | IFR | 2019-07-31 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02163 |  | 2019-07-17 | 2
036909C-1025-TDS-0610-2502 | Mechanical Equipment Data Sheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | 0 | 2019-06-24 | IFP | OL1-2M03-2502 | ME | 2019-07-16 | 036909C-JVD-TRN-02163 | 036909C-JVD-TRN-02163 | IFR | 2019-07-31 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02163 |  | 2019-07-17 | 2
036909C-1024-SP-0810-2456 | Mechanical Equipment Data Sheet for LP Deprop Reboilder Cond Pot | 0 | 2019-07-05 | IFP | OL1-2M03-2456 | ME | 2019-07-16 | 036909C-JVD-TRN-02167 | 036909C-JVD-TRN-02167 | IFR | 2019-07-31 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02167 |  | 2019-07-17 | 2
036909C-1024-SP-0810-2452 | Mechanical Equipment Data Sheet LP Depropanizer Reflux Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2452 | ME | 2019-07-16 | 036909C-JVD-TRN-02167 | 036909C-JVD-TRN-02167 | IFR | 2019-07-31 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02167 |  | 2019-07-17 | 2
036909C-1024-TDS-0610-2406 | Mechanical Equipment Data Sheet - 10-E-2405 - Gas Dryer Feed Chiller | 0 | 2019-06-24 | IFP | OL1-2M03-2406 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-18 | 2
036909C-1021-SP-0910-2146 | Mechanical Equipment Data Sheet For DGS Feed Pumps | 0 | 2019-07-05 | IFP | OL1-2M03-2146 | ME | 2019-07-08 | 036909C-JVD-TRN-02094 | 036909C-JVD-TRN-02094 | IFR | 2019-07-23 | 2019-08-01 | R2-Comments as noted | TPSK-LSPA1-T-ME-02094 |  | 2019-07-09 | 2
036909C-1021-SP-0910-2106 | Mechanical Equipment Data Sheet For Quench Water Pump | 0 | 2019-07-05 | IFP | OL1-2M03-2106 | ME | 2019-07-08 | 036909C-JVD-TRN-02094 | 036909C-JVD-TRN-02094 | IFR | 2019-07-23 | 2019-08-01 | R2-Comments as noted | TPSK-LSPA1-T-ME-02094 |  | 2019-07-09 | 2
036909C-1021-SP-1111-0001 | Mechanical Data Sheet For General Purpose Steam Turbines PT-2106 A Quench Water Pump Turbne | 0 | 2019-07-05 | IMP | OL1-2M03-2170 | ME | 2019-07-11 | 036909C-JVD-TRN-02130 | 036909C-JVD-TRN-02130 | IFR | 2019-07-26 | 2019-08-01 | R2-Comments as noted | TPSK-LSPA1-T-ME-02130 |  | 2019-07-15 | 2
036909C-1051-SP-0910-5109 | Mechanical Equipment Data Sheet For Condensate Pumps | 0 | 2019-07-05 | IFP | OL1-2M03-5109 | ME | 2019-07-08 | 036909C-JVD-TRN-02094 | 036909C-JVD-TRN-02094 | IFR | 2019-07-23 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02094 |  | 2019-07-09 | 2
036909C-1051-SP-0910-5102 | mechanical Equipment Datasheet For VLP BFW Pumps | 0 | 2019-07-05 | IMP | OL1-2M03-5102 | ME | 2019-07-08 | 036909C-JVD-TRN-02094 | 036909C-JVD-TRN-02094 | IFR | 2019-07-23 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02094 |  | 2019-07-09 | 2
036909C-1051-SP-0910-5101 | Mechanical Equipment Data Sheet For SHP BFW Pumps | 0 | 2019-07-05 | IFP | OL1-2M03-5101 | ME | 2019-07-08 | 036909C-JVD-TRN-02094 | 036909C-JVD-TRN-02094 | IFR | 2019-07-23 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02094 |  | 2019-07-09 | 2
036909C-1000-JSS-1656-0001 | Power Capacitors | 0 | 2018-09-20 | IMP | OL1-2R05-0021 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | 2018-11-05 | 3
036909C-1051-PDS-0600-5107 | Process Equipment Datasheet - 10-E-5112 - Suspect Cond Flash Drum Vent Condenser | A | 2018-10-26 | IFR | OL1-2G30-5107 | PE | 2018-10-30 | 036909C-JVD-TRN-00243 | 036909C-JVD-TRN-00243 | IFR | 2018-11-12 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00243 |  | 2018-10-30 | 2
036909C-1031-PDS-0800-3180 | Process Equipment Data Sheet - 10-D-3180 - BDU Knock Out Drum | A | 2019-04-04 | IFR | OL1-2G30-3180 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1031-PDS-0800-3161 | Process Equipment Data Sheet - 10-D-3160 - BDU Condensate Drum | A | 2019-04-04 | IFR | OL1-2G30-3161 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1031-PDS-0800-3126 | Process Equipment Data Sheet - 10-D-3126 - Ejector Seal Drum | A | 2019-04-04 | IFR | OL1-2G30-3126 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1031-PDS-0800-3112 | Process Equipment Data Sheet - 10-D-3110 - Water Washer Accumulator | A | 2019-04-04 | IFR | OL1-2G30-3112 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1031-PDS-0800-3100 | Process Equipment Data Sheet - 10-D-3100 - Solvent Regen Drum | A | 2019-04-04 | IFR | OL1-2G30-3100 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1030-PDS-0800-3082 | Process Equipment Data Sheet - 10-D-3080 - Butadiene Tower Reflux Drum | A | 2019-04-04 | IFR | OL1-2G30-3082 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1030-PDS-0800-3065 | Process Equipment Data Sheet - 10-D-3062 - C4 Acetylene Accumulator | A | 2019-04-04 | IFR | OL1-2G30-3065 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1030-PDS-0800-3064 | Process Equipment Data Sheet - 10-D-3060 - BDU HC-Water Separator | A | 2019-04-04 | IFR | OL1-2G30-3064 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1030-PDS-0800-3032 | Process Equipment Data Sheet - 10-D-3030 - After Washer Reflux Drum | A | 2019-04-04 | IFR | OL1-2G30-3032 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1030-PDS-0800-3022 | Process Equipment Data Sheet - 10-D-3020 - Main Washer Reflux Drum | A | 2019-04-04 | IFR | OL1-2G30-3022 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1030-PDS-0800-3003 | Process Equipment Data Sheet - 10-D-3000 - Predistillation Tower Reflux Drum | A | 2019-04-04 | IFR | OL1-2G30-3003 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1030-PDS-0800-3002 | Process Equipment Data Sheet - 10-D-3002 - Predistillation Feed Drum | A | 2019-04-04 | IFR | OL1-2G30-3002 | PE | 2019-04-05 | 036909C-JVD-TRN-01263 | 036909C-JVD-TRN-01263 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01263 |  | 2019-04-08 | 2
036909C-1053-PDS-0300-5351 | Process Equipment Datasheet - 10-PIT-5351 A-H - Olefins CW Pumps Sump | A | 2018-12-18 | IFR | OL1-2G30-5351 | PE | 2018-12-20 | 036909C-JVD-TRN-00539 | 036909C-JVD-TRN-00539 | IFR | 2019-01-02 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA-1-T-PE-00539 |  | 2018-12-20 | 2
036909C-1055-SP-0810-5520 | Mechanical Equipment Data Sheet for Vent Collection Drum | 0 | 2019-07-10 | IFP | OL1-2M03-5520 | ME | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1039-SP-0810-3908 | Mechanical Equipment Data Sheet for Predistillation Inhibitor Drum | 0 | 2019-07-10 | IFP | OL1-2M03-3908 | ME | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1028-SP-0810-2830 | Mechanical Equipment Data Sheet C3R 3rd Stage Suction Drum | 0 | 2019-07-10 | IFP | OL1-2M03-2830 | ME | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1027-SP-0810-2750 | Mechanical Equipment Data Sheet For C4/C5 Hydrog Surge Drum | 0 | 2019-07-10 | IFP | OL1-2M03-2750 | ME | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1027-SP-0810-2705 | Mechanical Equipment Data Sheet GHU-1 Hot Separator | 0 | 2019-07-10 | IFP | OL1-2M03-2705 | ME | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1026-SP-0810-2667 | Mechanical Equipment Data Sheet For C5/Pygas Surge Drum | 0 | 2019-07-10 | IFP | OL1-2M03-2667 | ME | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1025-SP-0810-2574 | Mechanical Equipment Data Sheet for Deethanizer Reboilder Cond Pot | 0 | 2019-07-10 | IFP | OL1-2M03-2574 | ME | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1025-SP-0810-2572 | Mechanical Equipment Data Sheet Deethanizer Reflux Drum | 0 | 2019-07-10 | IFP | OL1-2M03-2572 | ME | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1025-TDS-0610-2571 | Mechanical Equipment Data Sheet - 10-E-2570 - Deethanizer Condenser | 0 | 2019-06-26 | IFP | OL1-2M03-2571 | ME | 2019-07-15 | 036909C-JVD-TRN-02153 | 036909C-JVD-TRN-02153 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-02153 |  | 2019-07-16 | 2
036909C-1024-SP-0810-2444 | Mechanical Equipment Data Sheet For HP Deprop Reboiler Cond Pot | 0 | 2019-07-10 | IFP | OL1-2M03-2444 | ME | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1024-SP-0810-2435 | Mechanical Equipment Data Sheet for Regen Gas Separator | 0 | 2019-07-10 | IFP | OL1-2M03-2435 | ME | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1027-PDS-0800-2718 | Process Equipment Datasheet - 10-D-2720 - Rerun Tower Reflux Drum | C | 2019-07-01 | IFD | OL1-2G30-2718 | PE | 2019-07-02 | 036909C-JVD-TRN-02056 | 036909C-JVD-TRN-02056 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02056 |  | 2019-07-03 | 2
036909C-102E-CN-1734-0001 | Calculation Note For Foundation Of Basin 10-PIT-2390 | A | 2019-07-22 | IFR | OL1-2K13-0328 | CV | 2019-08-01 | 036909C-JVD-TRN-02312 | 036909C-JVD-TRN-02312 | IFA | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-CV-02312 |  | 2019-08-05 | 1
036909C-1000-NM-0001-1001 | Overall Material Balance | 1 | 2019-08-01 | IFI | OL1-2G44-1001 | PE | 2019-08-02 | 036909C-JVD-TRN-02336 | 036909C-JVD-TRN-02336 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02336 |  | 2019-08-05 | 3
036909C-1056-PDS-0200-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg | D | 2019-05-07 | IFD | OL1-2G30-5653 | PE | 2019-05-07 | 036909C-JVD-TRN-01607 | 036909C-JVD-TRN-01607 | IFR | 2019-05-22 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-01607 |  | 2019-05-08 | 2
036909C-1012-PDS-1390-1254 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-12002 | A | 2019-06-05 | IFR | OL1-2P03-1254 | MP | 2019-06-07 | 036909C-JVD-TRN-01829 |  | IFR | 2019-06-22 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-01829 |  | 2019-06-10 | 2
036909C-1012-PDS-1390-1253 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-12001 | A | 2019-06-05 | IFR | OL1-2P03-1253 | MP | 2019-06-07 | 036909C-JVD-TRN-01829 |  | IFR | 2019-06-22 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-01829 |  | 2019-06-10 | 2
036909C-1011-PDS-1390-1154 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-11002 | A | 2019-06-05 | IFR | OL1-2P03-1154 | MP | 2019-06-07 | 036909C-JVD-TRN-01829 |  | IFR | 2019-06-22 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-01829 |  | 2019-06-10 | 2
036909C-1011-PDS-1390-1153 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-11001 | A | 2019-06-05 | IFR | OL1-2P03-1153 | MP | 2019-06-07 | 036909C-JVD-TRN-01829 |  | IFR | 2019-06-22 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-MP-01829 |  | 2019-06-10 | 2
036909C-1053-PDS-0300-5360 | Process Equipment Datasheet - 10-PIT-5360 A-C - CTU CW Pumps Sump | A | 2018-12-18 | IFR | OL1-2G30-5360 | PE | 2018-12-20 | 036909C-JVD-TRN-00539 | 036909C-JVD-TRN-00539 | IFR | 2019-01-02 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA-1-T-PE-00539 |  | 2018-12-20 | 2
036909C-1056-PDS-0900-5624 | Process Equipment Datasheet - 10-P-5627 A-B - Gate 4 Septic Tank Pumps | 0 | 2019-07-29 | CAN | OL1-2G30-5624 | PE | 2019-08-01 | 036909C-JVD-TRN-02321 | 036909C-JVD-TRN-02321 | IFR | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-PE-02321 |  | 2019-08-05 | 2
036909C-1056-PDS-0900-5623 | Process Equipment Datasheet - 10-P-5626 A-B - Far C Septic Tank Pumps | 0 | 2019-07-29 | CAN | OL1-2G30-5623 | PE | 2019-08-01 | 036909C-JVD-TRN-02321 | 036909C-JVD-TRN-02321 | IFR | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-PE-02321 |  | 2019-08-05 | 2
036909C-1056-PDS-0200-5627 | Process Equipment Datasheet - 10-PIT-5627 - Gate 4 Septic Tank | 0 | 2019-07-29 | CAN | OL1-2G30-5627 | PE | 2019-08-01 | 036909C-JVD-TRN-02321 | 036909C-JVD-TRN-02321 | IFR | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-PE-02321 |  | 2019-08-05 | 2
036909C-1056-PDS-0200-5626 | Process Equipment Datasheet - 10-PIT-5626 - Far C Septic Tank | 0 | 2019-07-29 | CAN | OL1-2G30-5626 | PE | 2019-08-01 | 036909C-JVD-TRN-02321 | 036909C-JVD-TRN-02321 | IFR | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-PE-02321 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3029 | PSV-3029 Sizing Calculation | A | 2019-07-25 | IFR | OL1-2G23-3029 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1030-CN-0014-3046 | PSV-3046 Sizing Calculation | A | 2019-07-22 | IFR | OL1-2G23-3046 | PE | 2019-08-01 | 036909C-JVD-TRN-02320 | 036909C-JVD-TRN-02320 | IFR | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-PE-02320 |  | 2019-08-05 | 2
036909C-1056-PDS-0900-5624 | Process Equipment Datasheet - 10-P-5627 A-B - West Gate House Septic Tank Pumps | B | 2019-01-29 | IFD | OL1-2G30-5624 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00774 |  | 2019-01-31 | 2
036909C-1056-PDS-0900-5623 | Process Equipment Datasheet - 10-P-5626 A-B - Far C Septic Tank Pumps | D | 2019-04-03 | IFD | OL1-2G30-5623 | PE | 2019-04-04 | 036909C-JVD-TRN-01255 | 036909C-JVD-TRN-01255 | IFR | 2019-04-19 |  | Transmitted | TPSK-LSPA1-T-PE-01255 |  | 2019-04-05 | 2
036909C-1056-PDS-0900-5623 | Process Equipment Datasheet - 10-P-5626 A-B - Gate House Septic Tank Pumps | C | 2019-03-21 | IFD | OL1-2G30-5623 | PE | 2019-03-25 | 036909C-JVD-TRN-01152 | 036909C-JVD-TRN-01152 | IFR | 2019-04-09 | 2019-04-12 | R1-No comments | TPSK-LSPA1-T-PE-01152 |  | 2019-03-26 | 2
036909C-1056-PDS-0900-5623 | Process Equipment Datasheet - 10-P-5626 A-B - Gate House Septic Tank Pumps | B | 2019-01-29 | IFD | OL1-2G30-5623 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774 |  | 2019-01-31 | 2
036909C-1056-PDS-0200-5627 | Process Equipment Datasheet - 10-PIT-5627 - West Gate House Septic Tank | A | 2019-01-02 | IFR | OL1-2G30-5627 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1056-PDS-0200-5626 | Process Equipment Datasheet - 10-PIT-5626 - Gate House Septic Tank | A | 2019-01-02 | IFR | OL1-2G30-5626 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1000-JSD-2300-01 | Job Design Specification For Painting | B | 2018-12-18 | IFR | OL1-2R04-0005 | MP | 2018-12-27 | 036909C-JVD-TRN-00562 | 036909C-JVD-TRN-00562, ROC-TPSK-CECO-T-00004 | IFR | 2019-01-11 | 2019-01-17 | R2-Comments as noted | TPSK-LSPA1-T-MP-00562 |  | 2018-12-27 | 2
036909C-PO-036909C001P4_1 | Vendor s Acknowledgment of Purchase Order For Residue Gas Expander Recompressor Amd 1 – MR 1130-0001 Rev 1 | 0 | 2019-07-17 | IFI | OL1-2C51-0016 | PL | 2019-07-18 | 036909C-JVD-TRN-02187 | 036909C-JVD-TRN-02187 | IFI |  | 2019-07-31 | R1-No comments | TPSK-LSPA1-T-PL-02187 |  | 2019-07-19 | 3
036909C-PO-036909C001P47 | Vendor s Acknowledgment of Purchase Order For Reactors and Thicker Vessels Rev. 0 MR-0411-0001 Rev. 0 | 0 | 2019-07-16 | IFI | OL1-2C51-0015 | PL | 2019-07-16 | 036909C-JVD-TRN-02159 | 036909C-JVD-TRN-02159 | IFI |  | 2019-07-31 | R1-No comments | TPSK-LSPA1-T-PL-02159 |  | 2019-07-17 | 3
036909C-1000-JSS-3480-0001 | ROC - Job Supply Specification For HVAC Systems | A | 2019-07-12 | IFR | OL1-2H03-0002 | EE | 2019-07-12 | 036909C-JVD-TRN-02147 | 036909C-JVD-TRN-02147 | IFR | 2019-07-29 | 2019-07-31 | R1-No comments | TPSK-LSPA1-T-EE-02147 |  | 2019-07-15 | 2
036909C-1000-PP-107 | Project Document Coding | 1 | 2019-03-11 | IMP | OL1-2W92-0003 | PC | 2019-03-13 | 036909C-JVD-TRN-01041 | 036909C-JVD-TRN-01041 | IFR | 2019-03-28 |  | Transmitted | TPSK-LSPA1-T-PC-01041 |  | 2019-03-14 | 2
036909C-1056-SP-0910-5643 | Mechanical Equipment Datasheet - Cooling Water BD Basin Pumps | A | 2019-05-03 | IFQ | OL1-2M03-5643 | ME | 2019-05-06 | 036909C-JVD-TRN-01582 | 036909C-JVD-TRN-01582 | IFR | 2019-05-21 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01582 |  | 2019-05-07 | 2
036909C-1051-TDS-0610-5107 | Mechanical Equipment Data Sheet - 10-E-5112 - Suspect Cond Flash Drum Vent Condenser | A | 2019-01-25 | IFQ | OL1-2M03-5107 | ME | 2019-01-29 | 036909C-JVD-TRN-00755 | 036909C-JVD-TRN-00755, ROC-TPSK-CECO-T-00018 | IFR | 2019-02-12 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00755 |  | 2019-01-29 | 2
036909C-1051-TDS-0610-5107 | Mechanical Equipment Data Sheet - 10-E-5112 - Suspect Cond Flash Drum Vent Condenser | B | 2019-04-15 | IFQ | OL1-2M03-5107 | ME | 2019-04-18 | 036909C-JVD-TRN-01396 | 036909C-JVD-TRN-01396 | IFR | 2019-05-02 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01396 |  | 2019-04-18 | 2
036909C-1012-PDS-1390-1214 | Piping Specialty Item Datasheet - Vent Silencer - Start up - 10-SP-12014-16014 | A | 2019-05-08 | IFR | OL1-2P03-1214 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1012-PDS-1390-1213 | Piping Specialty Item Datasheet - Vent Silencer - PSV-1244 Outlet - 10-SP-12013-16013 | A | 2019-05-08 | IFR | OL1-2P03-1213 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1012-PDS-1390-1205 | Piping Specialty Item Datasheet - T-Type Filter - Fuel Gas Line - 10-SP-12005-16005 | A | 2019-05-07 | IFR | OL1-2P03-1205 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1012-PDS-1390-1203 | Piping Specialty Item Datasheet - Exhaust Head - 10-SP-12003-16003 | A | 2019-05-13 | IFR | OL1-2P03-1203 | MP | 2019-05-16 | 036909C-JVD-TRN-01683 | 036909C-JVD-TRN-01683 | IFR | 2019-05-31 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-MP-01683 |  | 2019-05-17 | 2
036909C-1011-PDS-1390-1114 | Piping Specialty Item Datasheet - Vent Silencer - Start up - 10-SP-11014 | A | 2019-05-08 | IFR | OL1-2P03-1114 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1011-PDS-1390-1105 | Piping Specialty Item Datasheet - T-Type Filter - Fuel Gas Line - 10 SP-11005 | A | 2019-05-07 | IFR | OL1-2P03-1105 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1011-PDS-1390-1103 | Piping Specialty Item Datasheet - Exhaust Head - 10-SP-11003 | A | 2019-05-13 | IFR | OL1-2P03-1103 | MP | 2019-05-16 | 036909C-JVD-TRN-01683 | 036909C-JVD-TRN-01683 | IFR | 2019-05-31 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-MP-01683 |  | 2019-05-17 | 2
036909C-1053-PDS-2600-5397 | Process Equipment Datasheet - 10-PK-5397 - Non-oxidizing Biocide Inj Pkg | C | 2019-03-20 | IFD | OL1-2G30-5397 | PE | 2019-03-20 | 036909C-JVD-TRN-01111 | 036909C-JVD-TRN-01111, ROC-TPSK-CECO-T-00020 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01111 |  | 2019-03-21 | 2
036909C-1029-PDS-2600-2920 | Process Equipment Datasheet - 10-PK-2920 - Polymerization Inhibitor Inj Pkg | A | 2018-12-18 | IFR | OL1-2G30-2920 | PE | 2018-12-20 | 036909C-JVD-TRN-00533 | 036909C-JVD-TRN-00533 | IFR | 2019-01-02 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00533 |  | 2018-12-20 | 2
036909C-1029-PDS-2600-2920 | Process Equipment Datasheet - 10-PK-2920 - Polymerization Inhibitor Inj Pkg | B | 2019-01-24 | IFD | OL1-2G30-2920 | PE | 2019-01-25 | 036909C-JVD-TRN-00726 | 036909C-JVD-TRN-00726 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00726 |  | 2019-01-25 | 2
036909C-1029-PDS-2600-2920 | Process Equipment Datasheet - 10-PK-2920 - Polymerization Inhibitor Inj Pkg | D | 2019-05-15 | IFD | OL1-2G30-2920 | PE | 2019-05-16 | 036909C-JVD-TRN-01686 | 036909C-JVD-TRN-01686 | IFR | 2019-05-31 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01686 |  | 2019-05-17 | 2
036909C-1029-PDS-2600-2920 | Process Equipment Datasheet - 10-PK-2920 - Polymerization Inhibitor Inj Pkg | C | 2019-03-19 | IFD | OL1-2G30-2920 | PE | 2019-03-20 | 036909C-JVD-TRN-01103 | 036909C-JVD-TRN-01103, ROC-TPSK-CECO-T-00019 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01103 |  | 2019-03-21 | 2
036909C-1029-PDS-2600-2900 | Process Equipment Datasheet - 10-PK-2900 - pH Ctrl - Corrosion Inhibitor Inj Pkg | A | 2018-12-18 | IFR | OL1-2G30-2900 | PE | 2018-12-20 | 036909C-JVD-TRN-00532 | 036909C-JVD-TRN-00532 | IFR | 2019-01-02 | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00532 |  | 2018-12-20 | 2
036909C-1029-PDS-2600-2900 | Process Equipment Datasheet - 10-PK-2900 - PH Ctrl - Corrosion Inhibitor Inj Pkg | B | 2019-01-31 | IFD | OL1-2G30-2900 | PE | 2019-01-31 | 036909C-JVD-TRN-00780 | 036909C-JVD-TRN-00780 | IFI |  | 2019-02-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-00780 |  | 2019-02-01 | 2
036909C-102C-CN-1734-0002 | Calculation Note For Foundation Of Lifting Station 10-PIT-5600 | A | 2019-07-19 | IFR | OL1-2K13-0337 | CV | 2019-07-29 | 036909C-JVD-TRN-02273 | 036909C-JVD-TRN-02273 | IFA | 2019-08-13 |  | Transmitted | TPSK-LSPA1-T-CV-02273 |  | 2019-07-30 | 1
036909C-102C-CN-1734-0001 | Calculation Note For Foundation Of Basin 10-PIT-2790 | A | 2019-07-19 | IFR | OL1-2K13-0333 | CV | 2019-07-29 | 036909C-JVD-TRN-02273 | 036909C-JVD-TRN-02273 | IFA | 2019-08-13 |  | Transmitted | TPSK-LSPA1-T-CV-02273 |  | 2019-07-30 | 1
036909C-1000-SL-0000-05 | Sub Vendor List For Mechanical Packages | 0 | 2018-11-27 | IFI | OL1-2C91-0004 | PL | 2019-05-10 | 036909C-JVD-TRN-01633 | 036909C-JVD-TRN-01633 | IFA | 2019-05-24 | 2019-06-20 | R2-Comments as noted | TPSK-LPSA1-T-PL-01633 |  | 2019-05-13 | 3
036909C-1031-PDS-0500-3110 | Process Equipment Datasheet - 10-T-3110 - Water Washer | A | 2019-03-01 | IFR | OL1-2G30-3110 | PE | 2019-03-01 | 036909C-JVD-TRN-00973 | 036909C-JVD-TRN-00973, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-16 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-00973 |  | 2019-03-04 | 2
036909C-1030-PDS-0500-3090 | Process Equipment Datasheet - 10-T-3090 - Butadiene Drying Tower | A | 2019-02-26 | IFR | OL1-2G30-3090 | PE | 2019-02-26 | 036909C-JVD-TRN-00932 | 036909C-JVD-TRN-00932, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-13 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00932 |  | 2019-02-27 | 2
036909C-1030-PDS-0500-3080 | Process Equipment Datasheet - 10-T-3080 - Butadiene Tower | A | 2019-02-20 | IFR | OL1-2G30-3080 | PE | 2019-02-25 | 036909C-JVD-TRN-00923 | 036909C-JVD-TRN-00923, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-12 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00923 |  | 2019-02-26 | 2
036909C-1030-PDS-0500-3070 | Process Equipment Datasheet - 10-T-3070 - Direct Cooler Tower | A | 2019-02-28 | IFR | OL1-2G30-3070 | PE | 2019-02-28 | 036909C-JVD-TRN-00955 | 036909C-JVD-TRN-00955, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-15 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00955 |  | 2019-03-01 | 2
036909C-1030-PDS-0500-3060 | Process Equipment Datasheet - 10-T-3060 - C4 Acetylene Washer | A | 2019-02-20 | IFR | OL1-2G30-3060 | PE | 2019-02-25 | 036909C-JVD-TRN-00923 | 036909C-JVD-TRN-00923, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-12 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00923 |  | 2019-02-26 | 2
036909C-1030-PDS-0500-3050 | Process Equipment Datasheet - 10-T-3050 - Degasser | A | 2019-02-28 | IFR | OL1-2G30-3050 | PE | 2019-02-28 | 036909C-JVD-TRN-00955 | 036909C-JVD-TRN-00955, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-15 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00955 |  | 2019-03-01 | 2
036909C-1030-PDS-0500-3040 | Process Equipment Datasheet - 10-T-3040 - Rectifier | A | 2019-02-12 | IFR | OL1-2G30-3040 | PE | 2019-03-01 | 036909C-JVD-TRN-00958 | 036909C-JVD-TRN-00958, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-16 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-00958 |  | 2019-03-04 | 2
036909C-1030-PDS-0500-3030 | Process Equipment Datasheet - 10-T-3030 - After Washer | A | 2019-02-28 | IFR | OL1-2G30-3030 | PE | 2019-02-28 | 036909C-JVD-TRN-00955 | 036909C-JVD-TRN-00955, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-15 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00955 |  | 2019-03-01 | 2
036909C-1030-PDS-0500-3020 | Process Equipment Datasheet - 10-T-3020 - Main Washer | A | 2019-02-26 | IFR | OL1-2G30-3020 | PE | 2019-02-26 | 036909C-JVD-TRN-00932 | 036909C-JVD-TRN-00932, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-13 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00932 |  | 2019-02-27 | 2
036909C-1030-PDS-0500-3010 | Process Equipment Datasheet - 10-T-3010 - C4 Vaporization Tower | A | 2019-02-08 | IFR | OL1-2G30-3010 | PE | 2019-02-25 | 036909C-JVD-TRN-00923 | 036909C-JVD-TRN-00923, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-12 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00923 |  | 2019-02-26 | 2
036909C-1030-PDS-0500-3000 | Process Equipment Datasheet - 10-T-3000 - Predistillation Tower | A | 2019-02-12 | IFR | OL1-2G30-3000 | PE | 2019-02-25 | 036909C-JVD-TRN-00923 | 036909C-JVD-TRN-00923, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-12 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00923 |  | 2019-02-26 | 2
036909C-1026-TDS-0610-2631 | Mechanical Equipment Data Sheet - 10-E-2630 - Secondary Deeth Condenser | A | 2018-12-06 | IFQ | OL1-2M03-2631 | ME | 2018-12-10 | 036909C-JVD-TRN-00455 | 036909C-JVD-TRN-00455, ROC-TPSK-CECO-T-00018 | IFR | 2018-12-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00455 |  | 2018-12-10 | 2
036909C-1001-DW-3438-0001 | Operation Tool Room - Hvac Layout And Section | B | 2019-07-01 | IDD | OL1-2H21-0015 | EE | 2019-07-02 | 036909C-JVD-TRN-02053 | 036909C-JVD-TRN-02053 | IFA | 2019-07-17 | 2019-07-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-02053 |  | 2019-07-03 | 1
036909C-1001-DW-3434-0002 | Prefabricated Gatehouse - Hvac Layout And Process Flow Diagram | B | 2019-07-01 | IDD | OL1-2H21-0011 | EE | 2019-07-02 | 036909C-JVD-TRN-02053 | 036909C-JVD-TRN-02053 | IFA | 2019-07-17 | 2019-07-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-02053 |  | 2019-07-03 | 1
036909C-1001-DW-3434-0001 | Gatehouse A - Hvac Layout And Process Flow Diagram | B | 2019-07-01 | IDD | OL1-2H21-0010 | EE | 2019-07-02 | 036909C-JVD-TRN-02053 | 036909C-JVD-TRN-02053 | IFA | 2019-07-17 | 2019-07-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-02053 |  | 2019-07-03 | 1
036909C-1025-PDS-0800-2506 | Process Equipment Datasheet - 10-D-2506 - Demeth Prefrac Feed Separator No 2 | C | 2019-06-27 | IFD | OL1-2G30-2506 | PE | 2019-07-01 | 036909C-JVD-TRN-02040 | 036909C-JVD-TRN-02040 | IFR | 2019-07-16 | 2019-07-17 | R1-No comments | TPSK-LSPA1-T-PE-02040 |  | 2019-07-02 | 2
036909C-1019-PDS-0800-1912 | Process Equipment Datasheet - 10-D-1912 - DMDS Injection Drum | C | 2019-04-05 | IFD | OL1-2G30-1912 | PE | 2019-04-08 | 036909C-JVD-TRN-01280 | 036909C-JVD-TRN-01280 | IFR | 2019-04-23 |  | Transmitted | TPSK-LSPA1-T-PE-01280 |  | 2019-04-09 | 2
036909C-1027-PDS-0800-2712 | Process Equipment Datasheet - 10-D-2710 - Depentanizer Reflux Drum | C | 2019-05-03 | IFD | OL1-2G30-2712 | PE | 2019-05-07 | 036909C-JVD-TRN-01600 | 036909C-JVD-TRN-01600 | IFR | 2019-05-22 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-PE-01600 |  | 2019-05-08 | 2
036909C-1019-PDS-0800-1911 | Process Equipment Datasheet - 10-D-1910 - DMDS Bulk Storage Drum | C | 2019-04-05 | IFD | OL1-2G30-1911 | PE | 2019-04-08 | 036909C-JVD-TRN-01280 | 036909C-JVD-TRN-01280 | IFR | 2019-04-23 |  | Transmitted | TPSK-LSPA1-T-PE--01280 |  | 2019-04-09 | 2
036909C-1028-PDS-0800-2860 | Process Equipment Datasheet - 10-D-2860 - C2R 1st Stage Suction Drum | B | 2019-02-12 | IFD | OL1-2G30-2860 | PE | 2019-02-12 | 036909C-JVD-TRN-00845 | 036909C-JVD-TRN-00845 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00845 |  | 2019-02-12 | 2
036909C-1028-PDS-0800-2854 | Process Equipment Datasheet - 10-D-2855 - C2R Surge Drum | B | 2019-01-09 | IFD | OL1-2G30-2854 | PE | 2019-01-10 | 036909C-JVD-TRN-00621 | 036909C-JVD-TRN-00621 | IFI |  | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00621 |  | 2019-01-10 | 2
036909C-1028-PDS-0800-2865 | Process Equipment Datasheet - 10-D-2865 - C2R Drain Drum | B | 2019-01-10 | IFD | OL1-2G30-2865 | PE | 2019-01-11 | 036909C-JVD-TRN-00633 | 036909C-JVD-TRN-00633 | IFI |  | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00633 |  | 2019-01-11 | 2
036909C-1010-TDS-0610-1051 | Mechanical Equipment Data Sheet - 10-E-1050 - C2 Feed Superheater | 0 | 2019-07-12 | Issue for Purchase | OL1-2M03-1051 | ME | 2019-07-22 | 036909C-JVD-TRN-02235 | 036909C-JVD-TRN-02235 | IFR | 2019-08-06 |  | Transmitted | TPSK-LSPA1-T-ME-02235 |  | 2019-07-23 | 2
036909C-1010-TDS-0610-1020 | Mechanical Equipment Data Sheet - 10-E-1020 - Liquid Feed Heater | 0 | 2019-07-08 | IFP | OL1-2M03-1020 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 |  | Transmitted | TPSK-LSPA1-T-ME-02174 |  | 2019-07-17 | 2
036909C-1010-TDS-0610-1003 | Mechanical Equipment Data Sheet - 10-E-1001 - LPG Steam Vaporizer | 0 | 2019-06-25 | IFP | OL1-2M03-1003 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 |  | Transmitted | TPSK-LSPA1-T-ME-02174 |  | 2019-07-18 | 2
036909C-1000-DW-0053-0001 | General Key Plan | A | 2019-05-24 | IFR | OL1-2P06-0020 | MP | 2019-05-30 | 036909C-JVD-TRN-01767 | 036909C-JVD-TRN-01767 | IFR | 2019-06-14 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01767 |  | 2019-05-31 | 2
036909C-1022-SP-1543-2201 | Instrument Datasheets for On-Off Vales - Ball Type - Area 22 | A | 2019-04-10 | IFQ | OL1-2I20-2211 | IE | 2019-04-23 | 036909C-JVD-TRN-01301 | 036909C-JVD-TRN-01301 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01301 |  | 2019-04-23 | 3
036909C-1025-SP-1543-2501 | Instrument Datasheets - ON-OFF Valve - Ball Type - Area 25 | A | 2019-04-15 | IFQ | OL1-2I20-2511 | IE | 2019-04-23 | 036909C-JVD-TRN-01376 | 036909C-JVD-TRN-01376 | IFI |  | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-01376 |  | 2019-04-23 | 3
036909C-1028-SP-1543-2804 | Instrument Datasheets - ON-OFF Valve - Butterfly Type- Area 28 | A | 2019-04-15 | IFQ | OL1-2I20-2812 | IE | 2019-04-23 | 036909C-JVD-TRN-01376 | 036909C-JVD-TRN-01376, ROC-TPSK-CECO-T-00056 | IFI |  | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-IE-01376 |  | 2019-04-23 | 3
036909C-1023-SP-1543-2301 | Instrument Datasheets - ON-OFF Valve - Ball Type - Area 23 | A | 2019-04-26 | IFQ | OL1-2I20-2311 | IE | 2019-05-02 13:00 | 036909C-JVD-TRN-01550 | 036909C-JVD-TRN-01550 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01550 |  | 2019-05-03 | 3
036909C-1025-SP-1543-2504 | Instrument Datasheets - ON-OFF Valve - Butterfly Type - Area 25 | A | 2019-04-15 | IFQ | OL1-2I20-2512 | IE | 2019-04-23 | 036909C-JVD-TRN-01376 | 036909C-JVD-TRN-01376 | IFI |  | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-IE-01376 |  | 2019-04-23 | 3
036909C-1028-SP-1543-2801 | Instrument Datasheets - ON-OFF Valve - Ball Type - Area 28 | A | 2019-04-15 | IFQ | OL1-2I20-2811 | IE | 2019-04-23 | 036909C-JVD-TRN-01376 | 036909C-JVD-TRN-01376, ROC-TPSK-CECO-T-00056 | IFI |  | 2019-06-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-01376 |  | 2019-04-23 | 3
036909C-1000-MR-1547-0004 | MR For Venturi | A | 2019-07-01 | IFQ | OL1-2C17-010701 | PL | 2019-07-04 | 036909C-JVD-TRN-02077 | 036909C-JVD-TRN-02077 | IFR | 2019-07-19 | 2019-07-18 | R2-Comments as noted | TPSK-LSPA1-T-PL-02077 |  | 2019-07-05 | 2
036909C-1039-SP-0940-3909 | Mechanical Equipment Datasheet for BDU Predistillation Inhibitor Dosing Pumps | B | 2019-07-03 | Issue for Inquiry | OL1-2M03-3909 | ME | 2019-07-23 | 036909C-JVD-TRN-02251 | 036909C-JVD-TRN-02251 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02251 |  | 2019-07-24 | 2
036909C-1039-SP-0940-3903 | Mechanical Equipment Datasheet for BDU Solvent Inhibitor Dosing Pumps | B | 2019-07-03 | Issue for Inquiry | OL1-2M03-3903 | ME | 2019-07-23 | 036909C-JVD-TRN-02251 | 036909C-JVD-TRN-02251 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02251 |  | 2019-07-24 | 2
036909C-1039-SP-0940-3905 | Mechanical Equipment Datasheet for BDU Product Inhibitor Dosing Pumps | B | 2019-07-03 | Issue for Inquiry | OL1-2M03-3905 | ME | 2019-07-23 | 036909C-JVD-TRN-02251 | 036909C-JVD-TRN-02251 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02251 |  | 2019-07-24 | 2
036909C-1039-SP-0940-3907 | Mechanical Equipment Datasheet for BDU Anti-Foam Dosing Pumps | B | 2019-07-12 | Issue for Inquiry | OL1-2M03-3907 | ME | 2019-07-23 | 036909C-JVD-TRN-02251 | 036909C-JVD-TRN-02251 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02251 |  | 2019-07-24 | 2
036909C-1039-SP-0910-3901 | Mechanical Equipment Datasheet for NMP Storage Pump | B | 2019-07-03 | Issue for Inquiry | OL1-2M03-3901 | ME | 2019-07-23 | 036909C-JVD-TRN-02251 | 036909C-JVD-TRN-02251 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02251 |  | 2019-07-24 | 2
036909C-1030-SP-0910-3023 | Mechanical Equipment Datasheet for Main Washer Reflux C4 Raffinate-I Pumps | B | 2019-07-03 | Issue for Inquiry | OL1-2M03-3023 | ME | 2019-07-23 | 036909C-JVD-TRN-02241 | 036909C-JVD-TRN-02241 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02241 |  | 2019-07-24 | 2
036909C-1030-SP-0910-3046 | Mechanical Equipment Datasheet for Degasser Feed Pumps | B | 2019-07-12 | Issue for Inquiry | OL1-2M03-3046 | ME | 2019-07-23 | 036909C-JVD-TRN-02241 | 036909C-JVD-TRN-02241 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02241 |  | 2019-07-24 | 2
036909C-102B-CN-1734-0004 | Calculation Note For Foundation Of 10-PIT-5606 | A | 2019-07-16 | IFR | OL1-2K13-0100 | CV | 2019-07-23 | 036909C-JVD-TRN-02238 | 036909C-JVD-TRN-02238 | IFA | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-CV-02238 |  | 2019-07-24 | 1
036909C-102B-CN-1733-0048 | Calculation Note For Foundation Of 10-TK-2300 | A | 2019-07-16 | IFR | OL1-2K13-0400 | CV | 2019-07-23 | 036909C-JVD-TRN-02238 | 036909C-JVD-TRN-02238 | IFA | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-CV-02238 |  | 2019-07-24 | 1
036909C-102B-CN-1733-0047 | Calculation Note For Foundation Of 10-TK-2910 | A | 2019-07-16 | IFR | OL1-2K13-0056 | CV | 2019-07-23 | 036909C-JVD-TRN-02238 | 036909C-JVD-TRN-02238 | IFA | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-CV-02238 |  | 2019-07-24 | 1
036909C-1039-SP-0940-3909 | Mechanical Equipment Datasheet - BDU Predistillation Inhibitor Dosing Pumps | A | 2019-04-18 | IFQ | OL1-2M03-3909 | ME | 2019-04-23 | 036909C-JVD-TRN-01451 | 036909C-JVD-TRN-01451 | IFR | 2019-05-08 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01451 |  | 2019-04-24 | 2
036909C-1039-SP-0940-3907 | Mechanical Equipment Datasheet - BDU Anti-Foam Dosing Pumps | A | 2019-04-18 | IFQ | OL1-2M03-3907 | ME | 2019-04-23 | 036909C-JVD-TRN-01451 | 036909C-JVD-TRN-01451 | IFR | 2019-05-08 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01451 |  | 2019-04-24 | 2
036909C-1039-SP-0940-3905 | Mechanical Equipment Datasheet - BDU Product Inhibitor Dosing Pumps | A | 2019-04-23 | IFQ | OL1-2M03-3905 | ME | 2019-04-23 | 036909C-JVD-TRN-01451 | 036909C-JVD-TRN-01451 | IFR | 2019-05-08 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01451 |  | 2019-04-24 | 2
036909C-1039-SP-0940-3903 | Mechanical Equipment Datasheet - BDU Solvent Inhibitor Dosing Pumps | A | 2019-04-18 | IFQ | OL1-2M03-3903 | ME | 2019-04-23 | 036909C-JVD-TRN-01451 | 036909C-JVD-TRN-01451 | IFR | 2019-05-08 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01451 |  | 2019-04-24 | 2
036909C-1039-SP-0910-3901 | Mechanical Equipment Datasheet - NMP Storage Pump | A | 2019-04-25 | IFQ | OL1-2M03-3901 | ME | 2019-04-30 | 036909C-JVD-TRN-01524 | 036909C-JVD-TRN-01524 | IFR | 2019-05-15 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01524 |  | 2019-05-02 | 2
036909C-1030-SP-0910-3097 | Mechanical Equipment Datasheet - Butadiene Product Pumps | A | 2019-05-02 | IFQ | OL1-2M03-3097 | ME | 2019-05-06 | 036909C-JVD-TRN-01570 | 036909C-JVD-TRN-01570 | IFR | 2019-05-21 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01570 |  | 2019-05-07 | 2
036909C-1031-SP-0910-3113 | Mechanical Equipment Datasheet - Solvent Return Pumps | A | 2019-05-02 | IFQ | OL1-2M03-3113 | ME | 2019-05-02 | 036909C-JVD-TRN-01563 | 036909C-JVD-TRN-01563 | IFR | 2019-05-17 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-01563 |  | 2019-05-03 | 2
036909C-1031-SP-0910-3127 | Mechanical Equipment Datasheet - BDU Ejector Seal Drum Pumps | A | 2019-05-02 | IFQ | OL1-2M03-3127 | ME | 2019-05-02 | 036909C-JVD-TRN-01563 | 036909C-JVD-TRN-01563 | IFR | 2019-05-17 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-01563 |  | 2019-05-03 | 2
036909C-1031-SP-0910-3162 | Mechanical Equipment Datasheet - BDU Condensate Recycle Pumps | A | 2019-05-02 | IFQ | OL1-2M03-3162 | ME | 2019-05-02 | 036909C-JVD-TRN-01563 | 036909C-JVD-TRN-01563 | IFR | 2019-05-17 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-01563 |  | 2019-05-03 | 2
036909C-1031-SP-0910-3191 | Mechanical Equipment Datasheet - Solvent Slop Pump | A | 2019-05-03 | IFQ | OL1-2M03-3191 | ME | 2019-05-06 | 036909C-JVD-TRN-01570 | 036909C-JVD-TRN-01570 | IFR | 2019-05-21 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01570 |  | 2019-05-07 | 2
036909C-1012-SP-4061-2002 | Elevator Data Sheet | A | 2019-01-15 | IFR | OL1-2M03-2002 | ME | 2019-01-18 | 036909C-JVD-TRN-00681 | 036909C-JVD-TRN-00682 | IFR | 2019-02-01 | 2019-02-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-00681 |  | 2019-01-18 | 2
036909C-105U-DW-0053-0001 | Detail Key Plan - Zone 5U - Utilities | A | 2019-05-24 | IFR | OL1-2P06-0035 | MP | 2019-05-30 | 036909C-JVD-TRN-01767 | 036909C-JVD-TRN-01767 | IFR | 2019-06-14 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01767 |  | 2019-05-31 | 2
036909C-102A-DW-0053-0001 | Detail Key Plan - Zone 2A - Quench | A | 2019-05-24 | IFR | OL1-2P06-0026 | MP | 2019-05-30 | 036909C-JVD-TRN-01767 | 036909C-JVD-TRN-01767 | IFR | 2019-06-14 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01767 |  | 2019-05-31 | 2
036909C-101A-DW-0053-0001 | Detail Key Plan - Zone 1A - Furnaces | A | 2019-05-24 | IFR | OL1-2P06-0024 | MP | 2019-05-30 | 036909C-JVD-TRN-01767 | 036909C-JVD-TRN-01767 | IFR | 2019-06-14 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01767 |  | 2019-05-31 | 2
036909C-1030-SP-0910-3066 | Mechanical Equipment Datasheet - Wastewater Pumps | A | 2019-05-02 | IFQ | OL1-2M03-3066 | ME | 2019-05-02 | 036909C-JVD-TRN-01563 | 036909C-JVD-TRN-01563 | IFR | 2019-05-17 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-01563 |  | 2019-05-03 | 2
036909C-1030-SP-0910-3056 | Mechanical Equipment Datasheet - Degasser Bottom Pumps | A | 2019-05-06 | IFQ | OL1-2M03-3056 | ME | 2019-05-06 | 036909C-JVD-TRN-01582 | 036909C-JVD-TRN-01582 | IFR | 2019-05-21 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01582 |  | 2019-05-07 | 2
036909C-1030-SP-0910-3046 | Mechanical Equipment Datasheet - Degasser Feed Pumps | A | 2019-04-16 | IFQ | OL1-2M03-3046 | ME | 2019-04-17 | 036909C-JVD-TRN-01398 | 036909C-JVD-TRN-01398 | IFR | 2019-05-02 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01398 |  | 2019-04-18 | 2
036909C-1030-SP-0910-3026 | Mechanical Equipment Datasheet - Main Washer Bottom Pumps | A | 2019-05-02 | IFQ | OL1-2M03-3026 | ME | 2019-05-02 | 036909C-JVD-TRN-01562 | 036909C-JVD-TRN-01562 | IFR | 2019-05-17 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME -01562 |  | 2019-05-03 | 2
036909C-1030-SP-0910-3023 | Mechanical Equipment Datasheet - Main Washer Reflux-C4 Raffinate-I Pumps | A | 2019-04-11 | IFQ | OL1-2M03-3023 | ME | 2019-04-15 | 036909C-JVD-TRN-01363 | 036909C-JVD-TRN-01363 | IFR | 2019-04-30 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-ME-01363 |  | 2019-04-16 | 2
036909C-1030-SP-0940-3061 | Mechanical Equipment Datasheet - Dimer Pumps | A | 2019-05-03 | IFQ | OL1-2M03-3061 | ME | 2019-05-06 | 036909C-JVD-TRN-01570 | 036909C-JVD-TRN-01570 | IFR | 2019-05-21 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01570 |  | 2019-05-07 | 2
036909C-1030-SP-0910-3086 | Mechanical Equipment Datasheet - Butadiene Tower Bottom Pumps | A | 2019-05-02 | IFQ | OL1-2M03-3086 | ME | 2019-05-06 | 036909C-JVD-TRN-01570 | 036909C-JVD-TRN-01570 | IFR | 2019-05-21 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01570 |  | 2019-05-07 | 2
036909C-1030-SP-0910-3083 | Mechanical Equipment Datasheet - Butadiene Tower Refllux Pumps | A | 2019-05-02 | IFQ | OL1-2M03-3083 | ME | 2019-05-02 | 036909C-JVD-TRN-01563 | 036909C-JVD-TRN-01563 | IFR | 2019-05-17 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-01563 |  | 2019-05-03 | 2
036909C-1030-SP-0910-3076 | Mechanical Equipment Datasheet - Direct Cooler Pumps | A | 2019-05-02 | IFQ | OL1-2M03-3076 | ME | 2019-05-02 | 036909C-JVD-TRN-01563 | 036909C-JVD-TRN-01563 | IFR | 2019-05-17 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-01563 |  | 2019-05-03 | 2
036909C-1030-SP-0910-3067 | Mechanical Equipment Datasheet - C4 Acetylene Pumps | A | 2019-05-02 | IFQ | OL1-2M03-3067 | ME | 2019-05-06 | 036909C-JVD-TRN-01570 | 036909C-JVD-TRN-01570 | IFR | 2019-05-21 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01570 |  | 2019-05-07 | 2
036909C-1028-TDS-0610-2852 | Mechanical Equipment Data Sheet - 10-E-2852 - C2R Desuperheater No 1 | A | 2018-12-13 | IFQ | OL1-2M03-2852 | ME | 2018-12-14 | 036909C-JVD-TRN-00505 | 036909C-JVD-TRN-00505, ROC-TPSK-CECO-T-00018 | IFR | 2018-12-27 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00505 |  | 2018-12-14 | 2
036909C-1028-TDS-0610-2852 | Mechanical Equipment Data Sheet - 10-E-2852 - C2R Desuperheater No 1 | B | 2019-04-10 | IFQ | OL1-2M03-2852 | ME | 2019-04-10 | 036909C-JVD-TRN-01311 | 036909C-JVD-TRN-01311 | IFR | 2019-04-25 |  | Transmitted | TPSK-LSPA1-T-ME-01311 |  | 2019-04-11 | 2
036909C-1028-TDS-0610-2807 | Mechanical Equipment Data Sheet - 10-E-2807 - C3 Chiller No 1 | A | 2018-12-12 | IFQ | OL1-2M03-2807 | ME | 2018-12-14 | 036909C-JVD-TRN-00505 | 036909C-JVD-TRN-00505, ROC-TPSK-CECO-T-00018 | IFR | 2018-12-27 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00505 |  | 2018-12-14 | 2
036909C-1025-TDS-0610-2575 | Mechanical Equipment Data Sheet - 10-E-2575 - Deethanizer Reboiler | A | 2019-01-17 | IFQ | OL1-2M03-2575 | ME | 2019-01-22 | 036909C-JVD-TRN-00684 | 036909C-JVD-TRN-00684 | IFR | 2019-02-04 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00684 |  | 2019-01-22 | 2
036909C-1021-TDS-0610-2147 | Mechanical Equipment Data Sheet - 10-E-2146 - DSG Feed Heater | A | 2019-01-14 | IFQ | OL1-2M03-2147 | ME | 2019-01-14 | 036909C-JVD-TRN-00650 | 036909C-JVD-TRN-00650, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-28 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00650 |  | 2019-01-14 | 2
036909C-1021-TDS-0610-2137 | Mechanical Equipment Data Sheet - 10-E-2136 - Process Water Stripper Feed Heater | A | 2018-12-27 | IFQ | OL1-2M03-2137 | ME | 2019-01-03 | 036909C-JVD-TRN-00573 | 036909C-JVD-TRN-00573, ROC-TPSK-CECO-T-00017 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00573 |  | 2019-01-03 | 2
036909C-1010-TDS-0610-1051 | Mechanical Equipment Data Sheet - 10-E-1050 - C2 Feed Superheater | A | 2018-12-27 | IFQ | OL1-2M03-1051 | ME | 2019-01-03 | 036909C-JVD-TRN-00573 | 036909C-JVD-TRN-00573 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00573 |  | 2019-01-03 | 2
036909C-1010-TDS-0610-1005 | Mechanical Equipment Data Sheet - 10-E-1005 - LPG Feed Heater | B | 2019-03-21 | IFQ | OL1-2M03-1005 | ME | 2019-04-02 | 036909C-JVD-TRN-01230 | 036909C-JVD-TRN-01230 | IFR | 2019-04-17 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-01230 |  | 2019-04-03 | 2
036909C-1010-TDS-0610-1005 | Mechanical Equipment Data Sheet - 10-E-1005 - LPG Feed Heater | A | 2018-12-27 | IFQ | OL1-2M03-1005 | ME | 2019-01-03 | 036909C-JVD-TRN-00573 | 036909C-JVD-TRN-00573, ROC-TPSK-CECO-T-00017 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00573 |  | 2019-01-03 | 2
036909C-1027-PDS-0900-2726 | Process Equipment Datasheet - 10-P-2726 A-B - Pygas Fuel Oil Pumps | B | 2019-04-17 | IFD | OL1-2G30-2726 | PE | 2019-04-22 | 036909C-JVD-TRN-01432 | 036909C-JVD-TRN-01432 | IFR | 2019-05-07 | 2019-06-17 | Response to Comments sent July 23, 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01432 |  | 2019-04-23 | 2
036909C-1039-MSD-0011-3901 | Material Selection Diagram - Olefins Unit 10 - 39 - C4 Unit BDU Aux - BDU Chemical Storage | A | 2019-06-21 | IFA | OL1-2G74-3901 | PE | 2019-06-26 | 036909C-JVD-TRN-02013 | 036909C-JVD-TRN-02013 | IFI |  | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02013 |  | 2019-06-27 | 3
036909C-1031-MSD-0011-3102 | Material Selection Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam And Condensate System | A | 2019-06-21 | IFA | OL1-2G74-3102 | PE | 2019-06-26 | 036909C-JVD-TRN-02013 | 036909C-JVD-TRN-02013 | IFI |  | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02013 |  | 2019-06-27 | 3
036909C-1031-MSD-0011-3101 | Material Selection Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration | A | 2019-06-21 | IFA | OL1-2G74-3101 | PE | 2019-06-26 | 036909C-JVD-TRN-02013 | 036909C-JVD-TRN-02013 | IFI |  | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02013 |  | 2019-06-27 | 3
036909C-1030-MSD-0011-3005 | Material Selection Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation | A | 2019-06-21 | IFA | OL1-2G74-3005 | PE | 2019-06-26 | 036909C-JVD-TRN-02013 | 036909C-JVD-TRN-02013 | IFI |  | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02013 |  | 2019-06-27 | 3
036909C-1030-MSD-0011-3004 | Material Selection Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing | A | 2019-06-21 | IFA | OL1-2G74-3004 | PE | 2019-06-26 | 036909C-JVD-TRN-02013 | 036909C-JVD-TRN-02013 | IFI |  | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02013 |  | 2019-06-27 | 3
036909C-1030-MSD-0011-3003 | Material Selection Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier | A | 2019-06-21 | IFA | OL1-2G74-3003 | PE | 2019-06-26 | 036909C-JVD-TRN-02013 | 036909C-JVD-TRN-02013 | IFI |  | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02013 |  | 2019-06-27 | 3
036909C-1030-MSD-0011-3002 | Material Selection Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation | A | 2019-06-21 | IFA | OL1-2G74-3002 | PE | 2019-06-26 | 036909C-JVD-TRN-02013 | 036909C-JVD-TRN-02013 | IFI |  | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02013 |  | 2019-06-27 | 3
036909C-1030-MSD-0011-3001 | Material Selection Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation | A | 2019-06-21 | IFA | OL1-2G74-3001 | PE | 2019-06-26 | 036909C-JVD-TRN-02013 | 036909C-JVD-TRN-02013 | IFI |  | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02013 |  | 2019-06-27 | 3
036909C-1027-MSD-0011-2703 | Material Selection Diagram - Olefins Unit 10 - 27 - GHU & C4/C5 Hydrog - Hydrog Reactivation Gas System | A | 2019-06-21 | IFA | OL1-2G74-2703 | PE | 2019-06-26 | 036909C-JVD-TRN-02013 | 036909C-JVD-TRN-02013 | IFI |  | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02013 |  | 2019-06-27 | 3
036909C-1027-MSD-0011-2702 | Material Selection Diagram - Olefins Unit 10 - 27 - GHU & C4/C5 Hydrog - GHU-1 Rerun Tower | A | 2019-06-21 | IFA | OL1-2G74-2702 | PE | 2019-06-26 | 036909C-JVD-TRN-02007 | 036909C-JVD-TRN-02007 | IFI |  | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-ME-02007 |  | 2019-06-27 | 3
036909C-1027-MSD-0011-2701 | Material Selection Diagram - Olefins Unit 10 - 27 - GHU & C4/C5 Hydrog GHU-1 Reactor & Depentanizer | A | 2019-06-21 | IFA | OL1-2G74-2701 | PE | 2019-06-26 | 036909C-JVD-TRN-02007 | 036909C-JVD-TRN-02007 | IFI |  | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02007 |  | 2019-06-27 | 3
036909C-1054-NM-0007-5401 | Piping Specialty Item - Datasheet Index - Plant Air-Instrument Air-Nitrogen - Area 54 | A | 2019-06-25 | IFR | OL1-2G91-5401 | PE | 2019-07-02 | 036909C-JVD-TRN-02055 | 036909C-JVD-TRN-02055 | IFR | 2019-07-17 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02055 |  | 2019-07-03 | 2
036909C-1052-NM-0007-5201 | Piping Specialty Item - Datasheet Index - Fuel Gas System - Area 52 | A | 2019-06-27 | IFR | OL1-2G91-5201 | PE | 2019-07-02 | 036909C-JVD-TRN-02055 | 036909C-JVD-TRN-02055 | IFR | 2019-07-17 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02055 |  | 2019-07-03 | 2
036909C-1050-NM-0007-5001 | Piping Specialty Item - Datasheet Index - Water System-Treated Potable Demin - Area 50 | A | 2019-06-28 | IFR | OL1-2G91-5001 | PE | 2019-07-02 | 036909C-JVD-TRN-02055 | 036909C-JVD-TRN-02055 | IFR | 2019-07-17 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02055 |  | 2019-07-03 | 2
036909C-1029-NM-0007-2901 | Piping Specialty Item - Datasheet Index - Ethylene Auxiliaries - Area 29 | A | 2019-06-25 | IFR | OL1-2G91-2901 | PE | 2019-06-27 | 036909C-JVD-TRN-02020 | 036909C-JVD-TRN-02020 | IFR | 2019-07-12 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02020 |  | 2019-06-28 | 2
036909C-1026-NM-0007-2601 | Piping Specialty Item - Datasheet Index - Hot Fractionation - Area 26 | A | 2019-06-26 | IFR | OL1-2G91-2601 | PE | 2019-06-27 | 036909C-JVD-TRN-02020 | 036909C-JVD-TRN-02020 | IFR | 2019-07-12 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02020 |  | 2019-06-28 | 2
036909C-1025-NM-0007-2501 | Piping Specialty Item - Datasheet Index - Cold Fractionation - Area 25 | A | 2019-06-26 | IFR | OL1-2G91-2501 | PE | 2019-06-27 | 036909C-JVD-TRN-02020 | 036909C-JVD-TRN-02020 | IFR | 2019-07-12 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02020 |  | 2019-06-28 | 2
036909C-1021-NM-0007-2101 | Piping Specialty Item - Datasheet Index - Quench Water-Dilution Steam - Area 21 | A | 2019-06-28 | IFR | OL1-2G91-2101 | PE | 2019-07-02 | 036909C-JVD-TRN-02055 | 036909C-JVD-TRN-02055 | IFR | 2019-07-17 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02055 |  | 2019-07-03 | 2
036909C-1020-NM-0007-2001 | Piping Specialty Item - Datasheet Index - Quench Oil - Area 20 | A | 2019-06-28 | IFR | OL1-2G91-2001 | PE | 2019-07-02 | 036909C-JVD-TRN-02055 | 036909C-JVD-TRN-02055 | IFR | 2019-07-17 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02055 |  | 2019-07-03 | 2
036909C-1019-NM-0007-1901 | Piping Specialty Item - Datasheet Index - Furnace Auxiliaries - Area 19 | A | 2019-06-26 | IFR | OL1-2G91-1901 | PE | 2019-06-27 | 036909C-JVD-TRN-02020 | 036909C-JVD-TRN-02020 | IFR | 2019-07-12 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02020 |  | 2019-06-28 | 2
036909C-1010-NM-0007-1001 | Piping Specialty Item - Datasheet Index - Feed Preparation and Furnaces - Area 10 | A | 2019-06-26 | IFR | OL1-2G91-1001 | PE | 2019-06-27 | 036909C-JVD-TRN-02020 | 036909C-JVD-TRN-02020 | IFR | 2019-07-12 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02020 |  | 2019-06-28 | 2
036909C-1053-NM-0007-5301 | Piping Specialty Item - Datasheet Index - Cooling Water - Area 53 | A | 2019-06-21 | IFR | OL1-2G91-5301 | PE | 2019-07-02 | 036909C-JVD-TRN-02055 | 036909C-JVD-TRN-02055 | IFR | 2019-07-17 | 2019-07-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02055 |  | 2019-07-03 | 2
036909C-1028-NM-0007-2801 | Piping Specialty Item - Datasheet Index - Refrigeration System - Area 28 | A | 2019-06-27 | IFR | OL1-2G91-2801 | PE | 2019-07-02 | 036909C-JVD-TRN-02055 | 036909C-JVD-TRN-02055 | IFR | 2019-07-17 | 2019-07-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02055 |  | 2019-07-03 | 2
036909C-1027-NM-0007-2701 | Piping Specialty Item - Datasheet Index - GHU and C4-C5 Hydrog - Area 27 | A | 2019-06-27 | IFR | OL1-2G91-2701 | PE | 2019-07-02 | 036909C-JVD-TRN-02055 | 036909C-JVD-TRN-02055 | IFR | 2019-07-17 | 2019-07-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02055 |  | 2019-07-03 | 2
036909C-1001-CN-3444-0001 | Gatehouse A HVAC Thermal Calculation | B | 2019-07-01 | IDD | OL1-2H10-0003 | EE | 2019-07-03 | 036909C-JVD-TRN-02068 | 036909C-JVD-TRN-02068 | IFA | 2019-07-18 | 2019-07-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-02068 |  | 2019-07-04 | 1
036909C-1051-PDS-1546-5190 | Process Datasheet for Restriction Orifice - Area 51 | A | 2019-06-27 | IFR | OL1-2G31-5190 | PE | 2019-07-01 | 036909C-JVD-TRN-02044 | 036909C-JVD-TRN-02044 | IFR | 2019-07-16 | 2019-07-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02044 |  | 2019-07-02 | 2
036909C-1059-PDS-1546-5990 | Process Datasheet for Restriction Orifice Area 59 | A | 2019-06-25 | IFR | OL1-2G31-5990 | PE | 2019-06-27 | 036909C-JVD-TRN-02019 | 036909C-JVD-TRN-02019 | IFR | 2019-07-12 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02019 |  | 2019-06-28 | 2
036909C-1055-PDS-1546-5590 | Process Datasheet for Restriction Orifice - Area 55 | A | 2019-06-28 | IFR | OL1-2G31-5590 | PE | 2019-07-01 | 036909C-JVD-TRN-02044 | 036909C-JVD-TRN-02044 | IFR | 2019-07-16 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02044 |  | 2019-07-02 | 2
036909C-1056-PDS-1546-5690 | Process Datasheet for Restriction Orifice Area 56 | A | 2019-06-20 | IFR | OL1-2G31-5690 | PE | 2019-06-27 | 036909C-JVD-TRN-02018 | 036909C-JVD-TRN-02018 | IFR | 2019-07-12 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02018 |  | 2019-06-28 | 2
036909C-1053-PDS-1546-5390 | Process Datasheet for Restriction Orifice Area 53 | A | 2019-06-26 | IFR | OL1-2G31-5390 | PE | 2019-06-27 | 036909C-JVD-TRN-02018 | 036909C-JVD-TRN-02018 | IFR | 2019-07-12 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02018 |  | 2019-06-28 | 2
036909C-1029-PDS-1546-2990 | Process Datasheet for Restriction Orifice Unit 29 | A | 2019-06-26 | IFR | OL1-2G31-2990 | PE | 2019-06-27 | 036909C-JVD-TRN-02018 | 036909C-JVD-TRN-02018 | IFR | 2019-07-12 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02018 |  | 2019-06-28 | 2
036909C-1025-PDS-1546-2590 | Process Datasheet for Restriction Orifice Unit 25 | A | 2019-06-26 | IFR | OL1-2G31-2590 | PE | 2019-06-27 | 036909C-JVD-TRN-02018 | 036909C-JVD-TRN-02018 | IFR | 2019-07-12 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02018 |  | 2019-06-28 | 2
036909C-1021-PDS-1546-2190 | Process Datasheet for Restriction Orifice - Area 21 | A | 2019-06-26 | IFR | OL1-2G31-2190 | PE | 2019-07-01 | 036909C-JVD-TRN-02044 | 036909C-JVD-TRN-02044 | IFR | 2019-07-16 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02044 |  | 2019-07-02 | 2
036909C-1020-PDS-1546-2090 | Process Datasheet for Restriction Orifice - Area 20 | A | 2019-07-01 | IFR | OL1-2G31-2090 | PE | 2019-07-02 | 036909C-JVD-TRN-02061 | 036909C-JVD-TRN-02061 | IFR | 2019-07-17 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02061 |  | 2019-07-03 | 2
036909C-1059-NM-0007-5901 | Piping Specialty Item - Datasheet Index - Supporting Utilities Auxiliaries - Area 59 | A | 2019-06-28 | IFR | OL1-2G91-5901 | PE | 2019-07-02 | 036909C-JVD-TRN-02055 | 036909C-JVD-TRN-02055 | IFR | 2019-07-17 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02055 |  | 2019-07-03 | 2
036909C-1056-NM-0007-5601 | Piping Specialty Item - Datasheet Index - WasteWater - Area 56 | A | 2019-06-28 | IFR | OL1-2G91-5601 | PE | 2019-07-02 | 036909C-JVD-TRN-02055 | 036909C-JVD-TRN-02055 | IFR | 2019-07-17 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02055 |  | 2019-07-03 | 2
036909C-1055-NM-0007-5501 | Piping Specialty Item - Datasheet Index - Vent Gas and Flare System - Area 55 | A | 2019-06-28 | IFR | OL1-2G91-5501 | PE | 2019-07-02 | 036909C-JVD-TRN-02055 | 036909C-JVD-TRN-02055 | IFR | 2019-07-17 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02055 |  | 2019-07-03 | 2
036909C-1039-NM-0007-3901 | Piping Specialty Item - Datasheet Index - Butadiene Extraction Unit Auxiliaries - Area 39 | A | 2019-07-03 | IFR | OL1-2G91-3901 | PE | 2019-07-05 | 036909C-JVD-TRN-02085 | 036909C-JVD-TRN-02085 | IFR | 2019-07-20 | 2019-07-23 | R1-No comments | TPSK-LSPA1-T-PE-02085 |  | 2019-07-08 | 2
036909C-1051-NM-0007-5101 | Piping Specialty Item - Datasheet Index - BFW-Steam-Steam Condensation System - Area 51 | A | 2019-06-28 | IFR | OL1-2G91-5101 | PE | 2019-07-02 | 036909C-JVD-TRN-02055 | 036909C-JVD-TRN-02055 | IFR | 2019-07-17 | 2019-07-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02055 |  | 2019-07-03 | 2
036909C-1031-NM-0007-3101 | Piping Specialty Item - Datasheet Index - Butadiene Extraction Unit Utilities - Area 31 | A | 2019-07-03 | IFR | OL1-2G91-3101 | PE | 2019-07-05 | 036909C-JVD-TRN-02085 | 036909C-JVD-TRN-02085 | IFR | 2019-07-20 | 2019-07-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02085 |  | 2019-07-08 | 2
036909C-1030-NM-0007-3001 | Piping Specialty Item - Datasheet Index - Butadiene Extraction Unit - Area 30 | A | 2019-07-03 | IFR | OL1-2G91-3001 | PE | 2019-07-05 | 036909C-JVD-TRN-02085 | 036909C-JVD-TRN-02085 | IFR | 2019-07-20 | 2019-07-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02085 |  | 2019-07-08 | 2
036909C-1012-DW-0131-2582 | USC 132U Cracking Furnace Steel Duct Plan and Elevations | 0 | 2019-07-17 | IMP | OL1-2K32-2582 | CV | 2019-07-22 | 036909C-JVD-TRN-02228 | 036909C-JVD-TRN-02228 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02228 |  | 2019-07-23 | 3
036909C-1012-DW-0131-2581 | USC 132U Cracking Furnace Steel Breeching Sections and Details | 1 | 2019-07-17 | IMP | OL1-2K32-2581 | CV | 2019-07-22 | 036909C-JVD-TRN-02228 | 036909C-JVD-TRN-02228 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02228 |  | 2019-07-23 | 3
036909C-1012-DW-0131-2512 | USC 132U Cracking Furnace Steel Radiant Side Wall at COL Line A2 And D2 | 1 | 2019-07-17 | IMP | OL1-2K32-2512 | CV | 2019-07-22 | 036909C-JVD-TRN-02228 | 036909C-JVD-TRN-02228 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02228 |  | 2019-07-23 | 3
036909C-1012-DW-0117-2562 | USC 132U Cracking Furnace Steel Access Door Davit Details | 0 | 2019-07-17 | IMP | OL1-2K32-2562 | CV | 2019-07-22 | 036909C-JVD-TRN-02236 | 036909C-JVD-TRN-02236 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02236 |  | 2019-07-23 | 3
036909C-1011-DW-0117-1582 | USC 36M Recycle Furnace Steel Duct Plan and Elevations | 0 | 2019-07-17 | IMP | OL1-2K32-1582 | CV | 2019-07-22 | 036909C-JVD-TRN-02227 | 036909C-JVD-TRN-02227 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02227 |  | 2019-07-23 | 3
036909C-1011-DW-0117-1562 | USC 36M Recycle Furnace Steel Access Door Davit Details | 0 | 2019-07-17 | IMP | OL1-2K32-1562 | CV | 2019-07-22 | 036909C-JVD-TRN-02227 | 036909C-JVD-TRN-02227 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02227 |  | 2019-07-23 | 3
036909C-1011-DW-0131-1511 | USC 36M Recycle Furnace Steel Radiant Floor and Radiant Arch Plans | 2 | 2019-07-17 | IMP | OL1-2K23-1511 | CV | 2019-07-22 | 036909C-JVD-TRN-02229 | 036909C-JVD-TRN-02229 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02229 |  | 2019-07-23 | 3
036909C-1011-DW-0131-1512 | USC 36M Recycle Furnace Steel Radiant Side Wall at Col Line A1 and D1 | 1 | 2019-07-17 | IMP | OL1-2K32-1512 | CV | 2019-07-22 | 036909C-JVD-TRN-02229 | 036909C-JVD-TRN-02229 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02229 |  | 2019-07-23 | 3
036909C-1025-TDS-0610-2576 | Mechanical Equipment Data Sheet - 10-E-2576 - Deethanizer Bottoms Cooler | A | 2019-01-02 | IFQ | OL1-2M03-2576 | ME | 2019-01-03 | 036909C-JVD-TRN-00582 | 036909C-JVD-TRN-00582 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00582 |  | 2019-01-03 | 2
036909C-1020-TDS-0610-2048 | Mechanical Equipment Data Sheet - 10-E-2048 - Heavy Fuel Oil Product Cooler | A | 2019-01-17 | IFQ | OL1-2M03-2048 | ME | 2019-01-22 | 036909C-JVD-TRN-00683 | 036909C-JVD-TRN-00683, ROC-TPSK-CECO-T-00017 | IFR | 2019-02-04 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00683 |  | 2019-01-22 | 2
036909C-1020-TDS-0610-2026 | Mechanical Equipment Data Sheet - 10-E-2026 - FO Product Cooler | B | 2019-03-27 | IFQ | OL1-2M03-2026 | ME | 2019-04-10 | 036909C-JVD-TRN-01307 | 036909C-JVD-TRN-01307 | IFR | 2019-04-25 |  | Transmitted | TPSK-LSPA1-T-ME-01307 |  | 2019-04-11 | 2
036909C-1011-DW-0131-1512 | USC 36M Recycle Furnace Steel Radiant Side Wall at Col Line A1 and D1 | A | 2019-03-29 | IFI | OL1-2K32-1512 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1011-DW-0131-1512 | USC 36M Recycle Furnace Steel Radiant Side Wall at Col Line A1 and D1 | 0 | 2019-05-15 | IMP | OL1-2K32-1512 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1011-DW-0131-1511 | USC 36M Recycle Furnace Steel Radiant Floor and Radiant Arch Plans | A | 2019-03-29 | IFI | OL1-2K32-1511 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222, TPSK-LSPA1-T-CV-01702, TPSK-LSPA1-T-CV-01702 |  | 2019-04-02 | 3
036909C-1011-DW-0131-1511 | USC 36M Recycle Furnace Steel Radiant Floor and Radiant Arch Plans | 0 | 2019-05-15 | IMP | OL1-2K32-1511 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1011-DW-0117-1552 | USC 36M Recycle Furnace Steel Radiant Coil Removal Access Door Details | A | 2019-03-29 | IFI | OL1-2K32-1552 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1012-DW-0131-2582 | USC 132U Cracking Furnace Steel Duct Plan and Elevations | A | 2019-04-05 | IFI | OL1-2K32-2582 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1012-DW-0131-2581 | USC 132U Cracking Furnace Steel Breeching Sections and Details | A | 2019-04-08 | IFI | OL1-2K32-2581 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1012-DW-0131-2581 | USC 132U Cracking Furnace Steel Breeching Sections and Details | 0 | 2019-05-24 | IMP | OL1-2K32-2581 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1012-DW-0131-2518 | USC 132U Cracking Furnace Steel Radiant Sections And Details | A | 2019-03-29 | IFI | OL1-2K32-2518 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1012-DW-0131-2512 | USC 132U Cracking Furnace Steel Radiant Side Wall at COL Line A2 And D2 | 0 | 2019-05-15 | IMP | OL1-2K32-2512 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-25 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1012-DW-0131-2512 | USC 132U Cracking Furnace Steel Radiant Side Wall at COL Line A2 And D2 | A | 2019-03-29 | IFI | OL1-2K32-2512 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1011-DW-0131-1518 | USC 36M Recycle Furnace Steel Radiant Sections and Details | A | 2019-03-29 | IFI | OL1-2K32-1518 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1012-DW-0117-2552 | USC 132U Cracking Furnace Steel Radiant Coil Removal_Access Door Details | A | 2019-03-29 | IFI | OL1-2K32-2552 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-105W-DW-0051-0001 | Detail Plot Plan - Zone 5W Waste Water Treatment | A | 2019-02-15 | IFR | OL1-2P06-0017 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15 | 1
036909C-105U-DW-0051-0001 | Detail Plot Plan - Zone 5U - Utilities | A | 2019-02-15 | IFR | OL1-2P06-0016 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15 | 1
036909C-105T-DW-0051-0001 | Detail Plot Plan - Zone 5T - Cooling Water Unit | A | 2019-02-15 | IFR | OL1-2P06-0015 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15 | 1
036909C-103A-DW-0051-0001 | Detail Plot Plan - Zone 3A - Butadiene Extraction Unit | A | 2019-02-15 | IFR | OL1-2P06-0013 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15 | 1
036909C-102E-DW-0051-0001 | Detail Plot Plan - Zone 2E - Cracked Gas Compressor | A | 2019-02-15 | IFR | OL1-2P06-0012 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15 | 1
036909C-102D-DW-0051-0001 | Detail Plot Plan - Zone 2D - Process Cold Compressor | A | 2019-02-15 | IFR | OL1-2P06-0011 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15 | 1
036909C-102C-DW-0051-0001 | Detail Plot Plan - Zone 2C - Hot Fractionation/GHU Unit | A | 2019-02-15 | IFR | OL1-2P06-0010 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15 | 1
036909C-102B-DW-0051-0001 | Detail Plot Plan - Zone 2B - C3 Hydrogenation | A | 2019-02-15 | IFR | OL1-2P06-0009 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15 | 1
036909C-102A-DW-0051-0001 | Detail Plot Plan - Zone 2A - Quench | A | 2019-02-15 | IFR | OL1-2P06-0008 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15 | 1
036909C-101B-DW-0051-0001 | Detail Plot Plan - Zone 1B - Furnaces Utilities | A | 2019-02-15 | IFR | OL1-2P06-0007 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15 | 1
036909C-100P-DW-0051-0001 | Unit Plot Plan - Zone 0P - Main Pipe Rack | A | 2019-02-15 | IFR | OL1-2P06-0003 | MP | 2019-02-15 | 036909C-JVD-TRN-00871 | 036909C-JVD-TRN-00871, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-04 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-00871 |  | 2019-02-15 | 1
036909C-1056-PDS-2600-5690 | Process Equipment Datasheet - 10-PK-5690 - Slop Tank Polymer Injection Pkg | B | 2019-04-04 | IFD | OL1-2G30-5690 | PE | 2019-04-08 | 036909C-JVD-TRN-01274 | 036909C-JVD-TRN-01274 | IFR | 2019-04-23 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01274 |  | 2019-04-09 | 2
036909C-1056-PDS-2600-5690 | Process Equipment Datasheet - 10-PK-5690 - Slop Tank Polymer Injection Pkg | A | 2019-02-07 | IFR | OL1-2G30-5690 | PE | 2019-02-07 | 036909C-JVD-TRN-00821 | 036909C-JVD-TRN-00821, ROC-TPSK-CECO-T-00020 | IFR | 2019-02-21 | 2019-03-14 | R1-No comments | TPSK-LSPA1-T-PE-00821 |  | 2019-02-07 | 2
036909C-1026-TDS-0610-2666 | Mechanical Equipment Data Sheet - 10-E-2666 - Debutanizer Bottoms Cooler | A | 2018-12-07 | IFQ | OL1-2M03-2666 | ME | 2018-12-10 | 036909C-JVD-TRN-00468 | 036909C-JVD-TRN-00468, ROC-TPSK-CECO-T-00018 | IFR | 2018-12-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00468 |  | 2018-12-10 | 2
036909C-1024-TDS-0610-2455 | Mechanical Equipment Data Sheet - 10-E-2455 AB - LP Depropanizer Reboilers | A | 2019-01-02 | IFQ | OL1-2M03-2455 | ME | 2019-01-07 | 036909C-JVD-TRN-00584 | 036909C-JVD-TRN-00584, ROC-TPSK-CECO-T-00017 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00584 |  | 2019-01-07 | 2
036909C-1024-TDS-0610-2445 | Mechanical Equipment Data Sheet - 10-E-2445 - HP Depropanizer Reboiler | A | 2019-01-15 | IFQ | OL1-2M03-2445 | ME | 2019-01-17 | 036909C-JVD-TRN-00671 | 036909C-JVD-TRN-00671, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-30 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00671 |  | 2019-01-17 | 2
036909C-1021-TDS-0610-2145 | Mechanical Equipment Data Sheet - 10-E-2145 - Process Water Stripper Reboiler | B | 2019-04-14 | IFQ | OL1-2M03-2145 | ME | 2019-04-16 | 036909C-JVD-TRN-01357 | 036909C-JVD-TRN-01357 | IFR | 2019-05-01 |  | Transmitted | TPSK-LSPA1-T-ME-01357 |  | 2019-04-17 | 2
036909C-1021-TDS-0610-2125 | Mechanical Equipment Data Sheet - 10-E-2125 - Distillate Stripper Reboiler | A | 2019-01-02 | IFQ | OL1-2M03-2125 | ME | 2019-01-07 | 036909C-JVD-TRN-00584 | 036909C-JVD-TRN-00584, ROC-TPSK-CECO-T-00017 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00584 |  | 2019-01-07 | 2
036909C-1028-SP-0810-2854 | Mechanical Equipment Data Sheet - C2R Surge Drum | A | 2019-01-10 | IFQ | OL1-2M03-2854 | ME | 2019-01-11 | 036909C-JVD-TRN-00638 | 036909C-JVD-TRN-00638, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00638 |  | 2019-01-11 | 2
036909C-1027-SP-0810-2712 | Mechanical Equipment Data Sheet - Depentanizer Reflux Drum | A | 2019-02-06 | IFQ | OL1-2M03-2712 | ME | 2019-02-15 | 036909C-JVD-TRN-00874 | 036909C-JVD-TRN-00874, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-04 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00874 |  | 2019-02-15 | 2
036909C-1027-SP-0810-2712 | Mechanical Equipment Data Sheet - Depentanizer Reflux Drum | B | 2019-06-07 | IFQ | OL1-2M03-2712 | ME | 2019-06-10 | 036909C-JVD-TRN-01850 | 036909C-JVD-TRN-01850 | IFR | 2019-06-25 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01850 |  | 2019-06-11 | 2
036909C-1027-SP-0810-2706 | Mechanical Equipment Data Sheet - GHU-1 Cold Separator | A | 2019-02-22 | IFQ | OL1-2M03-2706 | ME | 2019-02-25 | 036909C-JVD-TRN-00928 | 036909C-JVD-TRN-00928, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-12 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-00928 |  | 2019-02-26 | 2
036909C-1025-SP-0810-2555 | Mechanical Equipment Data Sheet - Expander Discharge Drum | B | 2019-05-25 | IFQ | OL1-2M03-2555 | ME | 2019-05-28 | 036909C-JVD-TRN-01760 | 036909C-JVD-TRN-01760 | IFR | 2019-06-12 | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-ME-01760 |  | 2019-05-29 | 2
036909C-1025-SP-0810-2551 | Mechanical Equipment Data Sheet - Expander Suction Drum | B | 2019-05-23 | IFQ | OL1-2M03-2551 | ME | 2019-05-29 | 036909C-JVD-TRN-01764 | 036909C-JVD-TRN-01764 | IFR | 2019-06-13 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01764 |  | 2019-05-30 | 2
036909C-1025-SP-0810-2551 | Mechanical Equipment Data Sheet - Expander Suction Drum | A | 2018-12-11 | IFQ | OL1-2M03-2551 | ME | 2018-12-20 | 036909C-JVD-TRN-00551 | 036909C-JVD-TRN-00551, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-03 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00551 |  | 2018-12-20 | 2
036909C-1025-SP-0810-2508 | Mechanical Equipment Data Sheet - Demeth Prefrac Feed Separator No 3 | A | 2018-12-07 | IFQ | OL1-2M03-2508 | ME | 2018-12-20 | 036909C-JVD-TRN-00551 | 036909C-JVD-TRN-00551, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-03 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00551 |  | 2018-12-20 | 2
036909C-1025-SP-0810-2506 | Mechanical Equipment Data Sheet - Demeth Prefrac Feed Separator No 2 | A | 2018-12-07 | IFQ | OL1-2M03-2506 | ME | 2018-12-20 | 036909C-JVD-TRN-00551 | 036909C-JVD-TRN-00551, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-03 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00551 |  | 2018-12-20 | 2
036909C-1019-SP-0810-1912 | Mechanical Equipment Data Sheet - DMDS Injection Drum | B | 2019-04-11 | IFQ | OL1-2M03-1912 | ME | 2019-04-12 | 036909C-JVD-TRN-01347 | 036909C-JVD-TRN-01347 | IFR | 2019-04-29 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-01347 |  | 2019-04-15 | 2
036909C-1019-SP-0810-1912 | Mechanical Equipment Data Sheet - DMDS Injection Drum | A | 2019-01-24 | IFQ | OL1-2M03-1912 | ME | 2019-01-28 | 036909C-JVD-TRN-00744 | 036909C-JVD-TRN-00744, ROC-TPSK-CECO-T-00014 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00744 |  | 2019-01-28 | 2
036909C-1019-SP-0810-1911 | Mechanical Equipment Data Sheet - DMDS Bulk Storage Drum | B | 2019-04-11 | IFQ | OL1-2M03-1911 | ME | 2019-04-12 | 036909C-JVD-TRN-01347 | 036909C-JVD-TRN-01347 | IFR | 2019-04-29 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-01347 |  | 2019-04-15 | 2
036909C-1019-SP-0810-1911 | Mechanical Equipment Data Sheet - DMDS Bulk Storage Drum | A | 2019-01-24 | IFQ | OL1-2M03-1911 | ME | 2019-01-28 | 036909C-JVD-TRN-00743 | 036909C-JVD-TRN-00743, ROC-TPSK-CECO-T-00014 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00743 |  | 2019-01-28 | 2
036909C-1028-SP-0810-2870 | Mechanical Equipment Data Sheet - C2R 2ND Stage Suction Drum | B | 2019-03-25 | IFQ | OL1-2M03-2870 | ME | 2019-03-28 | 036909C-JVD-TRN-01186 | 036909C-JVD-TRN-01186 | IFR | 2019-04-12 | 2019-05-02 | R1-No comments | TPSK-LSPA1-T-ME-01186 |  | 2019-03-29 | 2
036909C-1028-SP-0810-2870 | Mechanical Equipment Data Sheet - C2R 2ND Stage Suction Drum | A | 2018-12-24 | IFQ | OL1-2M03-2870 | ME | 2019-01-17 | 036909C-JVD-TRN-00670 | 036909C-JVD-TRN-00670, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-30 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00670 |  | 2019-01-17 | 2
036909C-1028-SP-0810-2865 | Mechanical Equipment Data Sheet - C2R Drain Drum | A | 2018-12-18 | IFQ | OL1-2M03-2865 | ME | 2019-01-08 | 036909C-JVD-TRN-00607 | 036909C-JVD-TRN-00607, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-22 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-ME-00607 |  | 2019-01-08 | 2
036909C-1028-SP-0810-2865 | Mechanical Equipment Data Sheet - C2R Drain Drum | B | 2019-05-27 | IFQ | OL1-2M03-2865 | ME | 2019-05-30 | 036909C-JVD-TRN-01783 | 036909C-JVD-TRN-01783 | IFR | 2019-06-14 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01783 |  | 2019-05-31 | 2
036909C-1028-SP-0810-2860 | Mechanical Equipment Data Sheet - C2R 1ST Stage Suction Drum | A | 2018-12-07 | IFQ | OL1-2M03-2860 | ME | 2018-12-20 | 036909C-JVD-TRN-00553 | 036909C-JVD-TRN-00553, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-03 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00553 |  | 2018-12-20 | 2
036909C-102D-CN-1733-0050 | Calculation Note for Foundation Of 10-TX-C-2550 | A | 2019-07-18 | IFR | OL1-2K13-0259 | CV | 2019-07-19 | 036909C-JVD-TRN-02202 | 036909C-JVD-TRN-02202 | IFA | 2019-08-05 |  | Transmitted | TPSK-LSPA1-T-CV-02202 |  | 2019-07-22 | 1
036909C-1025-SP-0810-2525 | Mechanical Equipment Data Sheet - Hydrogen Drum | B | 2019-05-02 | IFQ | OL1-2M03-2525 | ME | 2019-05-06 | 036909C-JVD-TRN-01583 | 036909C-JVD-TRN-01583 | IFR | 2019-05-21 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01583 |  | 2019-05-07 | 2
036909C-1025-SP-0810-2525 | Mechanical Equipment Data Sheet - Hydrogen Drum | A | 2018-12-12 | IFQ | OL1-2M03-2525 | ME | 2019-01-16 | 036909C-JVD-TRN-00657 | 036909C-JVD-TRN-00657, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00657 |  | 2019-01-16 | 2
036909C-1059-PDS-2600-5914 | Process Equipment Datasheet - 10-PK-5914 - Phosphate Injection Pkg | D | 2019-03-19 | IFD | OL1-2G30-5914 | PE | 2019-03-20 | 036909C-JVD-TRN-01111 | 036909C-JVD-TRN-01111, ROC-TPSK-CECO-T-00020 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01111 |  | 2019-03-21 | 2
036909C-1059-PDS-2600-5914 | Process Equipment Datasheet - 10-PK-5914 - Phosphate Injection Pkg | A | 2018-12-07 | IFR | OL1-2G30-5914 | PE | 2018-12-10 | 036909C-JVD-TRN-00456 | 036909C-JVD-TRN-00456 | IFR | 2018-12-21 | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00456 |  | 2018-12-10 | 2
036909C-1059-PDS-2600-5912 | Process Equipment Datasheet - 10-PK-5912 - Neutralization Amine Inhibitor Inj Pkg | A | 2018-12-07 | IFR | OL1-2G30-5912 | PE | 2018-12-10 | 036909C-JVD-TRN-00456 | 036909C-JVD-TRN-00456 | IFR | 2018-12-21 | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00456 |  | 2018-12-10 | 2
036909C-1059-PDS-2600-5912 | Process Equipment Datasheet - 10-PK-5912 - Neutralization Amine Inhibitor Inj Pkg | D | 2019-03-19 | IFD | OL1-2G30-5912 | PE | 2019-03-20 | 036909C-JVD-TRN-01111 | 036909C-JVD-TRN-01111, ROC-TPSK-CECO-T-00020 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01111 |  | 2019-03-21 | 2
036909C-1059-PDS-2600-5910 | Process Equipment Datasheet - 10-PK-5910 - Oxygen Scavenger Inj Pkg | A | 2018-12-07 | IFR | OL1-2G30-5910 | PE | 2018-12-10 | 036909C-JVD-TRN-00456 | 036909C-JVD-TRN-00456 | IFR | 2018-12-21 | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00456 |  | 2018-12-10 | 2
036909C-1059-PDS-2600-5910 | Process Equipment Datasheet - 10-PK-5910 - Oxygen Scavenger Inj Pkg | D | 2019-03-19 | IFD | OL1-2G30-5910 | PE | 2019-03-20 | 036909C-JVD-TRN-01111 | 036909C-JVD-TRN-01111, ROC-TPSK-CECO-T-00020 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01111 |  | 2019-03-21 | 2
036909C-1053-PDS-2600-5394 | Process Equipment Datasheet - 10-PK-5394 - Dispersant Inj Pkg | C | 2019-03-19 | IFD | OL1-2G30-5394 | PE | 2019-03-20 | 036909C-JVD-TRN-01111 | 036909C-JVD-TRN-01111, ROC-TPSK-CECO-T-00020 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01111 |  | 2019-03-21 | 2
036909C-1053-PDS-2600-5392 | Process Equipment Datasheet - 10-PK-5392 - Mild Steel Corr Inhibitor Inj Pkg | C | 2019-03-19 | IFD | OL1-2G30-5392 | PE | 2019-03-20 | 036909C-JVD-TRN-01111 | 036909C-JVD-TRN-01111, ROC-TPSK-CECO-T-00020 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01111 |  | 2019-03-21 | 2
036909C-1053-PDS-2600-5390 | Process Equipment Datasheet - 10-PK-5390 - Copper Corrosion Inhibitor Inj Pkg | C | 2019-03-19 | IFD | OL1-2G30-5390 | PE | 2019-03-20 | 036909C-JVD-TRN-01111 | 036909C-JVD-TRN-01111, ROC-TPSK-CECO-T-00020 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01111 |  | 2019-03-21 | 2
036909C-103A-CN-1733-0003 | Calculation Note For Foundation Of 10-TK-3900 | A | 2019-07-16 | IFR | OL1-2K13-0202 | CV | 2019-07-19 | 036909C-JVD-TRN-02194 | 036909C-JVD-TRN-02194 | IFR | 2019-08-02 |  | Transmitted | TPSK-LSPA1-T-CV-02194 |  | 2019-07-19 | 1
036909C-1000-MR-2630-0005 | Material Requisition For Molecular Sieves | 0 | 2019-07-17 | CAN | OL1-2C18-265000 | PL | 2019-07-18 | 036909C-JVD-TRN-02186 | 036909C-JVD-TRN-02186 | IFR | 2019-08-02 |  | Transmitted | TPSK-LSPA1-T-PL-02186 |  | 2019-07-19 | 2
036909C-1000-PP-204 | SIL Study Procedure | 2 | 2019-07-15 | Issued for Execution | OL1-2S92-0007 | ES | 2019-07-18 | 036909C-JVD-TRN-02192 | 036909C-JVD-TRN-02192 | IFR | 2019-08-02 |  | Transmitted | TPSK-LSPA1-T-ES-02192 |  | 2019-07-19 | 2
036909C-1012-TBT-4061-2009 | Technical Bid Tabulation For Elevator | 0 | 2019-07-15 | IFI | OL1-2C23-2009 | PL | 2019-07-18 | 036909C-JVD-TRN-02190 | 036909C-JVD-TRN-02190 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02190 |  | 2019-07-19 | 3
036909C-1021-SP-0810-2190 | Mechanical Equipment Data Sheet for Quench Water Drain Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2190 | HOC Mech | 2019-07-16 | 036909C-JVD-TRN-02166 | 036909C-JVD-TRN-02166 | IFR | 2019-07-31 |  | Transmitted | TPSK-LSPA1-T-ME-02166 |  | 2019-07-16 | 2
036909C-1023-PDS-0800-2390 | Process Equipment Datasheet - 10-D-2390 - Caustic Drain Drum | D | 2019-05-10 | IFD | OL1-2G30-2390 | PE | 2019-05-13 | 036909C-JVD-TRN-01652 | 036909C-JVD-TRN-01652 | IFR | 2019-05-28 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01652 |  | 2019-05-14 | 2
036909C-1020-SP-0810-2090 | Mechanical Equipment Data Sheet for Quench Oil Drain Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2090 | ME | 2019-07-16 | 036909C-JVD-TRN-02166 | 036909C-JVD-TRN-02166 | IFR | 2019-07-31 |  | Transmitted | TPSK-LSPA1-T-ME-02166 |  | 2019-07-17 | 2
036909C-1027-PDS-0800-2735 | Process Equipment Datasheet - 10-D-2735 - Regen Hydrog Drum | B | 2019-04-05 | IFD | OL1-2G30-2735 | PE | 2019-04-08 | 036909C-JVD-TRN-01277 | 036909C-JVD-TRN-01277 | IFR | 2019-04-23 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01277 |  | 2019-04-09 | 2
036909C-1026-PDS-0800-2667 | Process Equipment Datasheet - 10-D-2666 - C5 - Pygas Surge Drum | C | 2019-05-03 | IFD | OL1-2G30-2667 | PE | 2019-05-07 | 036909C-JVD-TRN-01600 | 036909C-JVD-TRN-01600 | IFR | 2019-05-22 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-PE-01600 |  | 2019-05-08 | 2
036909C-1023-PDS-0800-2309 | Process Equipment Datasheet - 10-D-2305 - Yellow Oil Drum | D | 2019-04-15 | IFD | OL1-2G30-2309 | PE | 2019-04-16 | 036909C-JVD-TRN-01377 | 036909C-JVD-TRN-01377 | IFR | 2019-05-01 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-01377 |  | 2019-04-17 | 2
036909C-1023-PDS-0800-2322 | Process Equipment Datasheet - 10-D-2322 - Skim Oil Drum | D | 2019-05-10 | IFD | OL1-2G30-2322 | PE | 2019-05-13 | 036909C-JVD-TRN-01652 | 036909C-JVD-TRN-01652 | IFR | 2019-05-28 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01652 |  | 2019-05-14 | 2
036909C-1023-PDS-0800-2392 | Process Equipment Datasheet - 10-D-2392 - Spent Caustic Drain Drum | D | 2019-05-10 | IFD | OL1-2G30-2392 | PE | 2019-05-13 | 036909C-JVD-TRN-01652 | 036909C-JVD-TRN-01652 | IFR | 2019-05-28 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01652 |  | 2019-05-14 | 2
036909C-1026-PDS-0800-2662 | Process Equipment Datasheet - 10-D-2660 - Debutanizer Reflux Drum | B | 2019-01-14 | IFD | OL1-2G30-2662 | PE | 2019-01-16 | 036909C-JVD-TRN-00660 | 036909C-JVD-TRN-00660 | IFI |  | 2019-01-29 | R1-No comments | TPSK-LSPA1-T-PE-00660 |  | 2019-01-16 | 2
036909C-1051-PDS-0800-5114 | Process Equipment Datasheet - 10-D-5114 - LP Condensate Flash Drum | B | 2018-12-12 | IFD | OL1-2G30-5114 | PE | 2018-12-14 | 036909C-JVD-TRN-00498 | 036909C-JVD-TRN-00498 | IFI |  | 2019-01-10 | R1-No comments | TPSK-LSPA1-T-PE-00498 |  | 2018-12-14 | 2
036909C-1027-PDS-0800-2790 | Process Equipment Datasheet - 10-D-2790 - Light Oil Drain Drum | B | 2019-01-23 | IFD | OL1-2G30-2790 | PE | 2019-01-25 | 036909C-JVD-TRN-00721 | 036909C-JVD-TRN-00721 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00721 |  | 2019-01-25 | 2
036909C-1051-PDS-0800-5140 | Process Equipment Datasheet - 10-D-5140 - Intermittent Blowdown Drum | C | 2019-03-04 | IFD | OL1-2G30-5140 | PE | 2019-03-05 | 036909C-JVD-TRN-00988 | 036909C-JVD-TRN-00988 | IFR | 2019-03-20 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-PE-00988 |  | 2019-03-06 | 2
036909C-1027-PDS-0800-2750 | Process Equipment Datasheet - 10-D-2750 - C4-C5 Hydrog Surge Drum | B | 2019-03-04 | IFD | OL1-2G30-2750 | PE | 2019-03-11 | 036909C-JVD-TRN-01023 | 036909C-JVD-TRN-01023 | IFR | 2019-03-26 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-PE-01023 |  | 2019-03-12 | 2
036909C-1026-PDS-0800-2622 | Process Equipment Datasheet - 10-D-2620 - C3 Hydrog Recycle Drum | B | 2019-03-08 | IFD | OL1-2G30-2622 | PE | 2019-03-11 | 036909C-JVD-TRN-01023 | 036909C-JVD-TRN-01023 | IFR | 2019-03-26 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-PE-01023 |  | 2019-03-12 | 2
036909C-1020-TDS-0610-2015 | Mechanical Equipment Data Sheet - 10-E-2008 - LS2 Steam Generators | 0 | 2019-06-25 | IFP | OL1-2M03-2015 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 |  | Transmitted | TPSK-LSPA1-T-ME-02174 |  | 2019-07-17 | 2
036909C-1012-NM-0007-1201 | Piping Specialty Item Datasheet Index - Liquid Cracking Furnace Areas 12-16 | A | 2019-05-09 | IFR | OL1-2G91-1201 | PE | 2019-05-10 | 036909C-JVD-TRN-01642 | 036909C-JVD-TRN-01642 | IFR | 2019-05-28 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01642 |  | 2019-05-13 | 2
036909C-1011-NM-0007-1101 | Piping Specialty Item Datasheet Index - Recycle Gas Furnace Area 11 | A | 2019-05-09 | IFR | OL1-2G91-1101 | PE | 2019-05-10 | 036909C-JVD-TRN-01642 | 036909C-JVD-TRN-01642 | IFR | 2019-05-28 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01642 |  | 2019-05-13 | 2
036909C-1000-PP-204 | SIL Study Procedure | A | 2019-02-15 | IFR | OL1-2L72-0002 | SE | 2019-02-19 | 036909C-JVD-TRN-00894 | 036909C-JVD-TRN-00894 | IFR | 2019-03-06 | 2019-03-21 | R2-Comments as noted | TPSK-LSPA1-T-SE-00894 |  | 2019-02-19 | 2
036909C-1026-TDS-0610-2635 | Mechanical Equipment Data Sheet - 10-E-2635 - Secondary Deeth Reboiler | A | 2019-01-02 | IFQ | OL1-2M03-2635 | ME | 2019-01-03 | 036909C-JVD-TRN-00582 | 036909C-JVD-TRN-00582, ROC-TPSK-CECO-T-00018 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00582 |  | 2019-01-03 | 2
036909C-1024-TDS-0610-2430 | Mechanical Equipment Data Sheet - 10-E-2430 - Regen Gas Feed Heater | B | 2019-04-04 | IFQ | OL1-2M03-2430 | ME | 2019-04-10 | 036909C-JVD-TRN-01315 | 036909C-JVD-TRN-01315 | IFR | 2019-04-25 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-ME-01315 |  | 2019-04-11 | 2
036909C-1023-SP-0810-2322 | Mechanical Equipment Data Sheet - Skim Oil Drum | B | 2019-05-27 | IFQ | OL1-2M03-2322 | ME | 2019-05-30 | 036909C-JVD-TRN-01783 | 036909C-JVD-TRN-01783 | IFR | 2019-06-14 | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-ME-01783 |  | 2019-05-31 | 2
036909C-1023-SP-0810-2322 | Mechanical Equipment Data Sheet - Skim Oil Drum | A | 2018-12-10 | IFQ | OL1-2M03-2322 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483 |  | 2018-12-13 | 2
036909C-1023-SP-0810-2310 | Mechanical Equipment Data Sheet - Spent Caustic Deoiling Drum | A | 2018-12-10 | IFQ | OL1-2M03-2310 | ME | 2018-12-17 | 036909C-JVD-TRN-00513 | 036909C-JVD-TRN-00513, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-31 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00513 |  | 2018-12-17 | 2
036909C-1023-SP-0810-2310 | Mechanical Equipment Data Sheet - Spent Caustic Deoiling Drum | B | 2019-03-22 | IFQ | OL1-2M03-2310 | ME | 2019-04-23 | 036909C-JVD-TRN-01448 | 036909C-JVD-TRN-01448 | IFR | 2019-05-08 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01448 |  | 2019-04-24 | 2
036909C-1051-TDS-0610-5113 | Mechanical Equipment Data Sheet - 10-E-5113 - Foul Condensate Cooler | A | 2019-01-25 | IFQ | OL1-2M03-5113 | ME | 2019-01-29 | 036909C-JVD-TRN-00755 | 036909C-JVD-TRN-00755, ROC-TPSK-CECO-T-00018 | IFR | 2019-02-12 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00755 |  | 2019-01-29 | 2
036909C-1028-TDS-0610-2853 | Mechanical Equipment Data Sheet - 10-E-2853 - C2R Desuperheater No 2 | A | 2018-12-18 | IFQ | OL1-2M03-2853 | ME | 2018-12-20 | 036909C-JVD-TRN-00541 | 036909C-JVD-TRN-00541, ROC-TPSK-CECO-T-00018 | IFR | 2019-01-02 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00541 |  | 2018-12-20 | 2
036909C-1026-TDS-0610-2636 | Mechanical Equipment Data Sheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | A | 2018-12-07 | IFQ | OL1-2M03-2636 | ME | 2018-12-10 | 036909C-JVD-TRN-00465 | 036909C-JVD-TRN-00465, ROC-TPSK-CECO-T-00018 | IFR | 2018-12-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00465 |  | 2018-12-10 | 2
036909C-1029-PDS-2600-2945 | Process Equipment Datasheet - 10-PK-2945 - Anti-Oxidant Injection Package | A | 2019-05-07 | IFR | OL1-2G30-2945 | PE | 2019-05-08 | 036909C-JVD-TRN-01617 | 036909C-JVD-TRN-01617 | IFR | 2019-05-23 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-PE-01617 |  | 2019-05-09 | 2
036909C-1029-PDS-2600-2945 | Process Equipment Datasheet - 10-PK-2945 - Anti-Oxidant Injection Package | B | 2019-06-19 | IFD | OL1-2G30-2945 | PE | 2019-06-19 | 036909C-JVD-TRN-01930 | 036909C-JVD-TRN-01930 | IFR | 2019-07-04 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01930 |  | 2019-06-20 | 2
036909C-1029-PDS-2600-2940 | Process Equipment Datasheet - 10-PK-2940 - C4 Polymer Inhibitor Inj Pkg | C | 2019-03-19 | IFD | OL1-2G30-2940 | PE | 2019-03-20 | 036909C-JVD-TRN-01103 | 036909C-JVD-TRN-01103, ROC-TPSK-CECO-T-00019 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01103 |  | 2019-03-21 | 2
036909C-1029-PDS-2600-2940 | Process Equipment Datasheet - 10-PK-2940 - C4 Polymer Inhibitor Inj Pkg | D | 2019-04-15 | IFD | OL1-2G30-2940 | PE | 2019-04-16 | 036909C-JVD-TRN-01384 | 036909C-JVD-TRN-01384 | IFR | 2019-05-01 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-01384 |  | 2019-04-17 | 2
036909C-1029-PDS-2600-2940 | Process Equipment Datasheet - 10-PK-2940 - C4 Polymer Inhibitor Inj Pkg | B | 2019-01-24 | IFD | OL1-2G30-2940 | PE | 2019-01-25 | 036909C-JVD-TRN-00726 | 036909C-JVD-TRN-00726 | IFI |  | 2019-03-14 | R1-No comments | TPSK-LSPA1-T-PE-00726 |  | 2019-01-25 | 2
036909C-1029-PDS-2600-2940 | Process Equipment Datasheet - 10-PK-2940 - C4 Polymer Inhibitor Inj Pkg | A | 2018-12-18 | IFR | OL1-2G30-2940 | PE | 2018-12-20 | 036909C-JVD-TRN-00533 | 036909C-JVD-TRN-00533 | IFR | 2019-01-02 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00533 |  | 2018-12-20 | 2
036909C-1029-PDS-2600-2912 | Process Equipment Datasheet - 10-PK-2912 - Caustic Tower Anti-Foulant Inj Pkg | C | 2019-03-19 | IFD | OL1-2G30-2912 | PE | 2019-03-20 | 036909C-JVD-TRN-01103 | 036909C-JVD-TRN-01103, ROC-TPSK-CECO-T-00019 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01103 |  | 2019-03-21 | 2
036909C-1029-PDS-2600-2912 | Process Equipment Datasheet - 10-PK-2912 - Caustic Tower Anti-Foulant Inj Pkg | A | 2018-12-18 | IFR | OL1-2G30-2912 | PE | 2018-12-20 | 036909C-JVD-TRN-00533 | 036909C-JVD-TRN-00533 | IFR | 2019-01-02 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00533 |  | 2018-12-20 | 2
036909C-1029-PDS-2600-2906 | Process Equipment Datasheet - 10-PK-2906 - DSG Anti-Foulant Injection Pkg | A | 2018-12-18 | IFR | OL1-2G30-2906 | PE | 2018-12-20 | 036909C-JVD-TRN-00533 | 036909C-JVD-TRN-00533 | IFR | 2019-01-02 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00533 |  | 2018-12-20 | 2
036909C-1029-PDS-2600-2906 | Process Equipment Datasheet - 10-PK-2906 - DSG Anti-Foulant Injection Pkg | B | 2019-01-24 | IFD | OL1-2G30-2906 | PE | 2019-01-25 | 036909C-JVD-TRN-00726 | 036909C-JVD-TRN-00726 | IFI |  | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00726 |  | 2019-01-25 | 2
036909C-1029-PDS-2600-2906 | Process Equipment Datasheet - 10-PK-2906 - DSG Anti-Foulant Injection Pkg | C | 2019-03-19 | IFD | OL1-2G30-2906 | PE | 2019-03-20 | 036909C-JVD-TRN-01103 | 036909C-JVD-TRN-01103, ROC-TPSK-CECO-T-00019 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01103 |  | 2019-03-21 | 2
036909C-1029-PDS-2600-2904 | Process Equipment Datasheet - 10-PK-2904 - Process Water Stripper Chem Inj Pkg | A | 2018-12-18 | IFR | OL1-2G30-2904 | PE | 2018-12-20 | 036909C-JVD-TRN-00533 | 036909C-JVD-TRN-00533 | IFR | 2019-01-02 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00533 |  | 2018-12-20 | 2
036909C-1029-PDS-2600-2904 | Process Equipment Datasheet - 10-PK-2904 - Process Water Stripper Chem Inj Pkg | B | 2019-01-24 | IFD | OL1-2G30-2904 | PE | 2019-01-25 | 036909C-JVD-TRN-00726 | 036909C-JVD-TRN-00726 | IFI |  | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00726 |  | 2019-01-25 | 2
036909C-1029-PDS-2600-2904 | Process Equipment Datasheet - 10-PK-2904 - Process Water Stripper Chem Inj Pkg | C | 2019-03-19 | IFD | OL1-2G30-2904 | PE | 2019-03-20 | 036909C-JVD-TRN-01103 | 036909C-JVD-TRN-01103, ROC-TPSK-CECO-T-00019 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01103 |  | 2019-03-21 | 2
036909C-1029-PDS-2600-2902 | Process Equipment Datasheet - 10-PK-2902 - Emulsion Breaker Injection Pkg | B | 2019-01-24 | IFD | OL1-2G30-2902 | PE | 2019-01-25 | 036909C-JVD-TRN-00726 | 036909C-JVD-TRN-00726 | IFI |  | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00726 |  | 2019-01-25 | 2
036909C-1029-PDS-2600-2902 | Process Equipment Datasheet - 10-PK-2902 - Emulsion Breaker Injection Pkg | C | 2019-03-19 | IFD | OL1-2G30-2902 | PE | 2019-03-20 | 036909C-JVD-TRN-01103 | 036909C-JVD-TRN-01103, ROC-TPSK-CECO-T-00019 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01103 |  | 2019-03-21 | 2
036909C-1029-PDS-2600-2902 | Process Equipment Datasheet - 10-PK-2902 - Emulsion Breaker Injection Pkg | A | 2018-12-18 | IFR | OL1-2G30-2902 | PE | 2018-12-20 | 036909C-JVD-TRN-00533 | 036909C-JVD-TRN-00533 | IFR | 2019-01-02 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00533 |  | 2018-12-20 | 2
036909C-1055-SP-0810-5515 | Mechanical Equipment Data Sheet - Methanol Makeup Drum | B | 2019-05-29 | IFQ | OL1-2M03-5515 | ME | 2019-06-04 | 036909C-JVD-TRN-01803 | 036909C-JVD-TRN-01803 | IFR | 2019-06-19 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-01803 |  | 2019-06-10 | 2
036909C-1055-SP-0810-5515 | Mechanical Equipment Data Sheet - Methanol Makeup Drum | A | 2018-12-21 | IFQ | OL1-2M03-5515 | ME | 2019-01-08 | 036909C-JVD-TRN-00607 | 036909C-JVD-TRN-00607, ROC-TPSK-CECO-T-00016 | IFR | 2019-01-22 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-ME-00607 |  | 2019-01-08 | 2
036909C-1000-PP-132 | TPSK KLOC Organization Chart | 1 | 2019-01-30 | IFI | OL1-2W92-0021 | PC | 2019-01-30 | 036909C-JVD-TRN-00761 | 036909C-JVD-TRN-00761 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PC-00761 |  | 2019-01-31 | 3
036909C-1027-MSD-0011-2704 | Material Selection Diagram - Olefins Unit 10 - 27 - GHU & C4/C5 Hydrog - C4/C5 Hydrogenation | A | 2019-06-21 | IFA | OL1-2G74-2704 | PE | 2019-06-26 | 036909C-JVD-TRN-02013 | 036909C-JVD-TRN-02013 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02013 |  | 2019-06-27 | 3
036909C-1026-SP-0810-2610 | Mechanical Equipment Datasheet - C3 Hydrog Arsine Guard Bed | 0 | 2019-06-20 | IFP | 0L1-2M03-2610 | ME | 2019-06-21 | 036909C-JVD-TRN-01966 | 036909C-JVD-TRN-01966 | IFA | 2019-07-06 | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-ME-01966 |  | 2019-06-24 | 2
036909C-1027-SP-0410-2760 | Mechanical Equipment Data Sheet C4/C5 Hydrog Reactor | 0 | 2019-06-20 | IFP | OL1-2M03-2760 | ME | 2019-06-21 | 036909C-JVD-TRN-01966 | 036909C-JVD-TRN-01966 | IFA | 2019-07-06 | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-ME-01966 |  | 2019-06-24 | 2
036909C-1026-SP-0810-2600 | Mechanical Equipment Data Sheet C3 Hydrog Guard Adsorber | 0 | 2019-06-20 | IFP | OL1-2M03-2600 | ME | 2019-06-21 | 036909C-JVD-TRN-01966 | 036909C-JVD-TRN-01966 | IFA | 2019-07-06 | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-ME-01966 |  | 2019-06-24 | 2
036909C-1027-SP-0410-2700 | Mechanical Equipment Data Sheet GHU-1 Reactor | 0 | 2019-06-20 | IFP | OL1-2M03-2700 | ME | 2019-06-21 | 036909C-JVD-TRN-01966 | 036909C-JVD-TRN-01966 | IFA | 2019-07-06 | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-ME-01966 |  | 2019-06-24 | 2
036909C-1027-SP-0510-2710 | Mechanical Equipment Data Sheet Depentanizer | 1 | 2019-06-20 | IFP | OL1-2M03-2710 | ME | 2019-06-21 | 036909C-JVD-TRN-01966 | 036909C-JVD-TRN-01966 | IFA | 2019-07-06 |  | Transmitted | TPSK-LSPA1-T-ME-01966 |  | 2019-06-24 | 2
036909C-1026-SP-0410-2620 | Mechanical Equipment Data Sheet C3 Hydrog Reactor | 0 | 2019-06-20 | IFP | OL1-2M03-2620 | ME | 2019-06-21 | 036909C-JVD-TRN-01966 | 036909C-JVD-TRN-01966 | IFA | 2019-07-06 | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-ME-01966 |  | 2019-06-24 | 2
036909C-1024-SP-0810-2480 | Mechanical Equipment Data Sheet CG Secondary Dryer | 0 | 2019-06-20 | IFP | OL1-2M03-2480 | ME | 2019-06-21 | 036909C-JVD-TRN-01966 | 036909C-JVD-TRN-01966 | IFA | 2019-07-06 | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-ME-01966 |  | 2019-06-24 | 2
036909C-1024-SP-0810-2420 | Mechanical Equipment Data Sheet CG Liquid Dryer | 0 | 2019-06-20 | IFP | OL1-2M03-2420 | ME | 2019-06-21 | 036909C-JVD-TRN-01966 | 036909C-JVD-TRN-01966 | IFA | 2019-07-06 | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-ME-01966 |  | 2019-06-24 | 2
036909C-1024-SP-0810-2438 | Mechanical Equipment Data Sheet HP Depropanizer Reflux Drum | 0 | 2019-06-20 | IFP | OL1-2M03-2438 | ME | 2019-06-21 | 036909C-JVD-TRN-01966 | 036909C-JVD-TRN-01966 | IFA | 2019-07-06 | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-ME-01966 |  | 2019-06-24 | 2
036909C-1024-SP-0810-2460 | Mechanical Equipment Data Sheet for C2 Hydrog Arsine Guard Bed | 0 | 2019-06-20 | IFP | OL1-2M03-2460 | ME | 2019-06-21 | 036909C-JVD-TRN-01966 | 036909C-JVD-TRN-01966 | IFA | 2019-07-06 | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-ME-01966 |  | 2019-06-24 | 2
036909C-1024-SP-0810-2411 | Mechanical Equipment Data Sheet Cracked Gas Mercury Adsorber | 0 | 2019-06-20 | IFP | OL1-2M03-2411 | ME | 2019-06-21 | 036909C-JVD-TRN-01966 | 036909C-JVD-TRN-01966 | IFA | 2019-07-06 | 2019-07-16 | R2-Comments as noted | TPSK-LSPA1-T-ME-01966 |  | 2019-06-24 | 2
036909C-1024-SP-0810-2410 | Mechanical Equipment Data Sheet Cracked Gas Dryer | 0 | 2019-06-20 | IFP | OL1-2M03-2410 | ME | 2019-06-21 | 036909C-JVD-TRN-01966 | 036909C-JVD-TRN-01966 | IFA | 2019-07-06 | 2019-07-16 | R2-Comments as noted | TPSK-LSPA1-T-ME-01966 |  | 2019-06-24 | 2
036909C-1024-SP-0410-2470 | Mechanical Equipment Data Sheet C2 Hydrog Reactor | 0 | 2019-06-20 | IFP | OL1-2M03-2470 | ME | 2019-06-21 | 036909C-JVD-TRN-01966 | 036909C-JVD-TRN-01966 | IFA | 2019-07-06 | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-ME-01966 |  | 2019-06-24 | 2
036909C-1057-PID-0031-5726 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 5U | A | 2019-04-26 | IFR | OL1-2L40-5726 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5720 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2D (3/3) | A | 2019-04-26 | IFR | OL1-2L40-5720 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5714 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2A | A | 2019-04-26 | IFR | OL1-2L40-5714 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5716 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2C (1/2) | A | 2019-04-26 | IFR | OL1-2L40-5716 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5713 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 0S | A | 2019-04-26 | IFR | OL1-2L40-5713 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5715 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2B | A | 2019-04-26 | IFR | OL1-2L40-5715 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5730 | P&ID - SPRINKLER SYSTEM - SUBSTATION F CABLE CELLAR | A | 2019-04-26 | IFR | OL1-2L40-5730 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5725 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 5F | A | 2019-04-26 | IFR | OL1-2L40-5725 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5728 | P&ID - SPRINKLER SYSTEM - SUBSTATION E CABLE CELLAR | A | 2019-04-26 | IFR | OL1-2L40-5728 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5722 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 3A (1/2) | A | 2019-04-26 | IFR | OL1-2L40-5722 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5723 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 3A (2/2) | A | 2019-04-26 | IFR | OL1-2L40-5723 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5727 | P&ID - FIRE WATER CURTAIN SYSTEM - ZONE 1B | A | 2019-04-26 | IFR | OL1-2L40-5727 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5717 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2C (2/2) | A | 2019-04-26 | IFR | OL1-2L40-5717 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5718 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2D (1/3) | A | 2019-04-26 | IFR | OL1-2L40-5718 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5719 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2D (2/3) | A | 2019-04-26 | IFR | OL1-2L40-5719 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5729 | P&ID - SPRINKLER SYSTEM - SUBSTATION C CABLE CELLAR | A | 2019-04-26 | IFR | OL1-2L40-5729 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5724 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 3S | A | 2019-04-26 | IFR | OL1-2L40-5724 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5721 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2E | A | 2019-04-26 | IFR | OL1-2L40-5721 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5707 | P&ID - DRY RISER SYSTEM | A | 2019-04-26 | IFR | OL1-2L40-5707 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5704 | P&ID - FIRE WATER NETWORK (4/6) | A | 2019-04-26 | IFR | OL1-2L40-5704 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5706 | P&ID - FIRE WATER NETWORK (6/6) | A | 2019-04-26 | IFR | OL1-2L40-5706 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5705 | P&ID - FIRE WATER NETWORK (5/6) | A | 2019-04-26 | IFR | OL1-2L40-5705 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5701 | P&ID - FIRE WATER NETWORK (1/6) | A | 2019-04-26 | IFR | OL1-2L40-5701 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5702 | P&ID - FIRE WATER NETWORK (2/6) | A | 2019-04-26 | IFR | OL1-2L40-5702 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5703 | P&ID - FIRE WATER NETWORK (3/6) | A | 2019-04-26 | IFR | OL1-2L40-5703 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1021-TDS-0610-2161 | Mechanical Equipment Data Sheet - 10-E-2160 - Dilution Steam Superheater | A | 2019-01-10 | IFQ | OL1-2M03-2161 | ME | 2019-01-11 | 036909C-JVD-TRN-00641 | 036909C-JVD-TRN-00641, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-00641 |  | 2019-01-11 | 2
036909C-1021-TDS-0610-2161 | Mechanical Equipment Data Sheet - 10-E-2160 - Dilution Steam Superheater | B | 2019-03-27 | IFQ | OL1-2M03-2161 | ME | 2019-04-02 | 036909C-JVD-TRN-01230 | 036909C-JVD-TRN-01230 | IFR | 2019-04-17 | 2019-05-09 | R1-No comments | TPSK-LSPA1-T-ME-01230 |  | 2019-04-03 | 2
036909C-1021-SP-0810-2190 | Mechanical Equipment Data Sheet - Quench Water Drain Drum | A | 2019-01-10 | IFQ | OL1-2M03-2190 | ME | 2019-01-11 | 036909C-JVD-TRN-00638 | 036909C-JVD-TRN-00638, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00638 |  | 2019-01-11 | 2
036909C-1021-SP-0810-2190 | Mechanical Equipment Data Sheet - Quench Water Drain Drum | B | 2019-04-01 | IFQ | OL1-2M03-2190 | ME | 2019-04-02 | 036909C-JVD-TRN-01226 | 036909C-JVD-TRN-01226 | IFR | 2019-04-17 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-ME -1226 |  | 2019-04-03 | 2
036909C-1021-SP-0810-2160 | Mechanical Equipment Data Sheet - Dilution Steam Generator | A | 2018-12-05 | IFQ | OL1-2M03-2160 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483 |  | 2018-12-13 | 2
036909C-1021-SP-0810-2160 | Mechanical Equipment Data Sheet - Dilution Steam Generator | B | 2019-05-23 | IFQ | OL1-2M03-2160 | ME | 2019-05-28 | 036909C-JVD-TRN-01760 | 036909C-JVD-TRN-01760 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01760 |  | 2019-05-29 | 2
036909C-1021-SP-0810-2110 | Mechanical Equipment Data Sheet - Interception Drum | A | 2019-01-17 | IFQ | OL1-2M03-2110 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685, ROC-TPSK-CECO-T-00014 | IFR | 2019-02-04 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-00685 |  | 2019-01-22 | 2
036909C-1021-SP-0810-2110 | Mechanical Equipment Data Sheet - Interception Drum | B | 2019-06-10 | IFQ | OL1-2M03-2110 | ME | 2019-06-10 | 036909C-JVD-TRN-01850 | 036909C-JVD-TRN-01850 | IFR | 2019-06-25 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01850 |  | 2019-06-11 | 2
036909C-1020-TDS-0610-2015 | Mechanical Equipment Data Sheet - 10-E-2008 - LS2 Steam Generators | A | 2019-01-13 | IFQ | OL1-2M03-2015 | ME | 2019-01-14 | 036909C-JVD-TRN-00643 | 036909C-JVD-TRN-00643, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-28 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-00643 |  | 2019-01-14 | 2
036909C-1020-SP-0810-2090 | Mechanical Equipment Data Sheet - Quench Oil Drain Drum | B | 2019-04-01 | IFQ | OL1-2M03-2090 | ME | 2019-04-02 | 036909C-JVD-TRN-01226 | 036909C-JVD-TRN-01226 | IFR | 2019-04-17 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-ME -1226 |  | 2019-04-03 | 2
036909C-1020-SP-0810-2090 | Mechanical Equipment Data Sheet - Quench Oil Drain Drum | A | 2019-01-10 | IFQ | OL1-2M03-2090 | ME | 2019-01-11 | 036909C-JVD-TRN-00638 | 036909C-JVD-TRN-00638, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00638 |  | 2019-01-11 | 2
036909C-1010-TDS-0610-1020 | Mechanical Equipment Data Sheet - 10-E-1020 - Liquid Feed Heater | A | 2019-01-15 | IFQ | OL1-2M03-1020 | ME | 2019-01-17 | 036909C-JVD-TRN-00671 | 036909C-JVD-TRN-00671, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-30 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00671 |  | 2019-01-17 | 2
036909C-1010-TDS-0610-1020 | Mechanical Equipment Data Sheet - 10-E-1020 - Liquid Feed Heater | B | 2019-03-21 | IFQ | OL1-2M03-1020 | ME | 2019-04-02 | 036909C-JVD-TRN-01230 | 036909C-JVD-TRN-01230 | IFR | 2019-04-17 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-01230 |  | 2019-04-03 | 2
036909C-1010-TDS-0610-1003 | Mechanical Equipment Data Sheet - 10-E-1001 - LPG Steam Vaporizer | A | 2018-12-27 | IFQ | OL1-2M03-1003 | ME | 2019-01-03 | 036909C-JVD-TRN-00573 | 036909C-JVD-TRN-00573 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00573 |  | 2019-01-03 | 2
036909C-1010-TDS-0610-1002 | Mechanical Equipment Data Sheet - 10-E-1000 - LPG Vaporizer | A | 2019-01-18 | IFQ | OL1-2M03-1002 | ME | 2019-01-22 | 036909C-JVD-TRN-00684 | 036909C-JVD-TRN-00684, ROC-TPSK-CECO-T-00017 | IFR | 2019-02-04 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00684 |  | 2019-01-22 | 2
036909C-1010-SP-0810-1000 | Mechanical Equipment Data Sheet - LPG Drum | B | 2019-03-20 | IFQ | OL1-2M03-1000 | ME | 2019-04-23 | 036909C-JVD-TRN-01448 | 036909C-JVD-TRN-01448 | IFR | 2019-05-08 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01448 |  | 2019-04-24 | 2
036909C-1010-SP-0810-1000 | Mechanical Equipment Data Sheet - LPG Drum | A | 2018-12-05 | IFQ | OL1-2M03-1000 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483 |  | 2018-12-13 | 2
036909C-1052-SP-0810-5200 | Mechanical Equipment Data Sheet - Fuel Gas Drum | A | 2019-01-09 | IFQ | OL1-2M03-5200 | ME | 2019-01-11 | 036909C-JVD-TRN-00629 | 036909C-JVD-TRN-00629, ROC-TPSK-CECO-T-00016 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00629 |  | 2019-01-11 | 2
036909C-1051-SP-0810-5150 | Mechanical Equipment Data Sheet - Continuous Blow Down Flash Drum | A | 2019-01-05 | IFQ | OL1-2M03-5150 | ME | 2019-01-11 | 036909C-JVD-TRN-00629 | 036909C-JVD-TRN-00629, ROC-TPSK-CECO-T-00016 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00629 |  | 2019-01-11 | 2
036909C-1051-SP-0810-5140 | Mechanical Equipment Data Sheet - Intermittent Blowdown Drum | B | 2019-01-10 | IFQ | OL1-2M03-5140 | ME | 2019-01-11 | 036909C-JVD-TRN-00638 | 036909C-JVD-TRN-00638, ROC-TPSK-CECO-T-00016 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00638 |  | 2019-01-11 | 2
036909C-1051-SP-0810-5140 | Mechanical Equipment Data Sheet - Intermittent Blowdown Drum | C | 2019-05-28 | IFQ | OL1-2M03-5140 | ME | 2019-05-28 | 036909C-JVD-TRN-01760 | 036909C-JVD-TRN-01760 | IFR | 2019-06-12 | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-ME-01760 |  | 2019-05-29 | 2
036909C-1051-SP-0810-5140 | Mechanical Equipment Data Sheet - Intermittent Blowdown Drum | A | 2018-12-18 | IFQ | OL1-2M03-5140 | ME | 2018-12-20 | 036909C-JVD-TRN-00548 | 036909C-JVD-TRN-00548 | IFR | 2019-01-02 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA-T-ME-00548 |  | 2018-12-20 | 2
036909C-1027-SP-0810-2762 | Mechanical Equipment Data Sheet - C4-C5 Hydrog Recycle Drum | A | 2019-02-14 | IFQ | OL1-2M03-2762 | ME | 2019-02-15 | 036909C-JVD-TRN-00869 | 036909C-JVD-TRN-00869, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-04 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00869 |  | 2019-02-15 | 2
036909C-1027-SP-0810-2762 | Mechanical Equipment Data Sheet - C4-C5 Hydrog Recycle Drum | B | 2019-06-06 | IFQ | OL1-2M03-2762 | ME | 2019-06-06 | 036909C-JVD-TRN-01817 | 036909C-JVD-TRN-01817 | IFR | 2019-06-21 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01817 |  | 2019-06-10 | 2
036909C-1027-SP-0810-2735 | Mechanical Equipment Data Sheet - Regen Hydrog Drum | A | 2019-03-19 | IFQ | OL1-2M03-2735 | ME | 2019-04-04 | 036909C-JVD-TRN-01253 | 036909C-JVD-TRN-01253 | IFR | 2019-04-19 | 2019-06-05 | R1-No comments | TPSK-LSPA1-T-ME-01253 |  | 2019-04-05 | 2
036909C-1027-SP-0810-2724 | Mechanical Equipment Data Sheet - Wash Oil Degassing Drum | A | 2019-02-14 | IFQ | OL1-2M03-2724 | ME | 2019-02-15 | 036909C-JVD-TRN-00869 | 036909C-JVD-TRN-00869, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-04 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00869 |  | 2019-02-15 | 2
036909C-1027-SP-0810-2724 | Mechanical Equipment Data Sheet - Wash Oil Degassing Drum | B | 2019-06-04 | IFQ | OL1-2M03-2724 | ME | 2019-06-04 | 036909C-JVD-TRN-01803 | 036909C-JVD-TRN-01803 | IFR | 2019-06-19 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01803 |  | 2019-06-10 | 2
036909C-1026-SP-0810-2662 | Mechanical Equipment Data Sheet - Debutanizer Reflux Drum | B | 2019-03-22 | IFQ | OL1-2M03-2662 | ME | 2019-04-30 | 036909C-JVD-TRN-01535 | 036909C-JVD-TRN-01535 | IFR | 2019-05-15 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01535 |  | 2019-05-02 | 2
036909C-1026-SP-0810-2662 | Mechanical Equipment Data Sheet - Debutanizer Reflux Drum | A | 2018-12-04 | IFQ | OL1-2M03-2662 | ME | 2018-12-17 | 036909C-JVD-TRN-00516 | 036909C-JVD-TRN-00516, ROC-TPSK-CECO-T-00015 | IFR | 2018-12-31 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00516 |  | 2018-12-17 | 2
036909C-1026-SP-0810-2644 | Mechanical Equipment Data Sheet - C3 Tower Reboilder Cond Pot | A | 2019-01-25 | IFQ | OL1-2M03-2644 | ME | 2019-01-29 | 036909C-JVD-TRN-00753 | 036909C-JVD-TRN-00753, ROC-TPSK-CECO-T-00015 | IFR | 2019-02-12 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00753 |  | 2019-01-29 | 2
036909C-1028-TDS-0610-2806 | Mechanical Equipment Data Sheet - 10-E-2805A-C - C3 Refrig Condensers | A | 2019-01-15 | IFQ | OL1-2M03-2806 | ME | 2019-01-17 | 036909C-JVD-TRN-00671 | 036909C-JVD-TRN-00671 | IFR | 2019-01-30 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00671 |  | 2019-01-17 | 2
036909C-1027-TDS-0610-2707 | Mechanical Equipment Data Sheet - 10-E-2706 - GHU-1 Cooler | B | 2019-04-22 | IFQ | OL1-2M03-2707 | ME | 2019-04-24 | 036909C-JVD-TRN-01467 | 036909C-JVD-TRN-01467 | IFR | 2019-05-09 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME -01467 |  | 2019-04-25 | 2
036909C-1026-TDS-0610-2665 | Mechanical Equipment Data Sheet - 10-E-2665 AB - Debutanizer Reboilers | A | 2018-12-07 | IFQ | OL1-2M03-2665 | ME | 2018-12-10 | 036909C-JVD-TRN-00468 | 036909C-JVD-TRN-00468, ROC-TPSK-CECO-T-00018 | IFR | 2018-12-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00468 |  | 2018-12-10 | 2
036909C-1026-TDS-0610-2661 | Mechanical Equipment Data Sheet - 10-E-2660 - Debutanizer Condenser | A | 2018-12-07 | IFQ | OL1-2M03-2661 | ME | 2018-12-10 | 036909C-JVD-TRN-00465 | 036909C-JVD-TRN-00465, ROC-TPSK-CECO-T-00018 | IFR | 2018-12-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00465 |  | 2018-12-10 | 2
036909C-1026-TDS-0610-2661 | Mechanical Equipment Data Sheet - 10-E-2660 - Debutanizer Condenser | B | 2019-03-29 | IFQ | OL1-2M03-2661 | ME | 2019-03-29 | 036909C-JVD-TRN-01205 | 036909C-JVD-TRN-01205 | IFR | 2019-04-15 | 2019-05-02 | R1-No comments | TPSK-LSPA1-T-ME-01205 |  | 2019-04-01 | 2
036909C-1025-TDS-0610-2548 | Mechanical Equipment Data Sheet - 10-E-2548 - Demethanizer Bottoms Vaporizer | A | 2019-01-07 | IFQ | OL1-2M03-2548 | ME | 2019-01-10 | 036909C-JVD-TRN-00617 | 036909C-JVD-TRN-00617 | IFR | 2019-01-23 | 2019-01-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-00617 |  | 2019-01-10 | 2
036909C-1025-TDS-0610-2546 | Mechanical Equipment Data Sheet - 10-E-2546 - Demethanizer Bottoms Cooler | A | 2019-01-14 | IFQ | OL1-2M03-2546 | ME | 2019-01-16 | 036909C-JVD-TRN-00654 | 036909C-JVD-TRN-00654, ROC-TPSK-CECO-T-00018 | IFR | 2019-01-29 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00654 |  | 2019-01-16 | 2
036909C-1025-TDS-0610-2546 | Mechanical Equipment Data Sheet - 10-E-2546 - Demethanizer Bottoms Cooler | B | 2019-03-29 | IFQ | OL1-2M03-2546 | ME | 2019-03-29 | 036909C-JVD-TRN-01205 | 036909C-JVD-TRN-01205 | IFR | 2019-04-15 | 2019-05-02 | R1-No comments | TPSK-LSPA1-T-ME-01205 |  | 2019-04-01 | 2
036909C-1025-TDS-0610-2545 | Mechanical Equipment Data Sheet - 10-E-2545 - Demethanizer Reboiler | A | 2019-01-14 | IFQ | OL1-2M03-2545 | ME | 2019-01-14 | 036909C-JVD-TRN-00651 | 036909C-JVD-TRN-00651 | IFR | 2019-01-28 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00651 |  | 2019-01-14 | 2
036909C-1025-TDS-0610-2515 | Mechanical Equipment Data Sheet - 10-E-2515- Demeth Prefrac Reboiler | A | 2018-12-10 | IFQ | OL1-2M03-2515 | ME | 2019-01-03 | 036909C-JVD-TRN-00573 | 036909C-JVD-TRN-00573 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00573 |  | 2019-01-03 | 2
036909C-1024-TDS-0610-2465 | Mechanical Equipment Data Sheet - 10-E-2465 - C2 Hydrog Feed Heater | A | 2019-01-09 | IFQ | OL1-2M03-2465 | ME | 2019-01-11 | 036909C-JVD-TRN-00641 | 036909C-JVD-TRN-00641, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-00641 |  | 2019-01-11 | 2
036909C-1024-TDS-0610-2451 | Mechanical Equipment Data Sheet - 10-E-2450 - LP Depropanizer Condenser | A | 2019-01-04 | IFQ | OL1-2M03-2451 | ME | 2019-01-07 | 036909C-JVD-TRN-00588 | 036909C-JVD-TRN-00588, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-21 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00588 |  | 2019-01-07 | 2
036909C-1024-TDS-0610-2441 | Mechanical Equipment Data Sheet - 10-E-2441 - HP Deprop Reflux Chiller No 2 | A | 2019-01-14 | IFQ | OL1-2M03-2441 | ME | 2019-01-16 | 036909C-JVD-TRN-00663 | 036909C-JVD-TRN-00663, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00663 |  | 2019-01-16 | 2
036909C-1024-TDS-0610-2439 | Mechanical Equipment Data Sheet - 10-E-2440 - HP Depropanizer Condenser | A | 2019-01-16 | IFQ | OL1-2M03-2439 | ME | 2019-01-22 | 036909C-JVD-TRN-00683 | 036909C-JVD-TRN-00683, ROC-TPSK-CECO-T-00017 | IFR | 2019-02-04 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00683 |  | 2019-01-22 | 2
036909C-1024-TDS-0610-2406 | Mechanical Equipment Data Sheet - 10-E-2405 - Gas Dryer Feed Chiller | A | 2019-01-02 | IFQ | OL1-2M03-2406 | ME | 2019-01-07 | 036909C-JVD-TRN-00584 | 036909C-JVD-TRN-00584, ROC-TPSK-CECO-T-00017 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00584 |  | 2019-01-07 | 2
036909C-1026-SP-0810-2622 | Mechanical Equipment Data Sheet - C3 Hydrog Recycle Drum | A | 2019-01-15 | IFQ | OL1-2M03-2622 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685, ROC-TPSK-CECO-T-00015 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00685 |  | 2019-01-22 | 2
036909C-1026-SP-0810-2632 | Mechanical Equipment Data Sheet - Secondary Deeth Reflux Drum | A | 2019-01-05 | IFQ | OL1-2M03-2632 | ME | 2019-01-11 | 036909C-JVD-TRN-00629 | 036909C-JVD-TRN-00629, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00629 |  | 2019-01-11 | 2
036909C-1026-SP-0810-2632 | Mechanical Equipment Data Sheet - Secondary Deeth Reflux Drum | B | 2019-04-09 | IFQ | OL1-2M03-2632 | ME | 2019-04-10 | 036909C-JVD-TRN-01314 | 036909C-JVD-TRN-01314 | IFR | 2019-04-25 | 2019-06-05 | R1-No comments | TPSK-LSPA1-T-ME -01314 |  | 2019-04-11 | 2
036909C-1012-PDS-1390-1204 | Piping Specialty Item Datasheet - Vent Silencer - PSV-1242 A-B Outlet - 10-SP-12004-16004 | A | 2019-05-08 | IFR | OL1-2P03-1204 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1011-PDS-1390-1104 | Piping Specialty Item Datasheet - Vent Silencer - PSV-1142 A-B Outlet - 10- SP-11004 | A | 2019-05-08 | IFR | OL1-2P03-1104 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1011-PDS-1390-1102 | Piping Specialty Item Datasheet - T- Type Filter - Crossover Line - 10-SP-11002 | A | 2019-05-07 | IFR | OL1-2P03-1102 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1055-PDS-0800-5514 | Process Equipment Datasheet - 10-D-5513 - Methanol Vaporizer Cond Pot | 0 | 2019-06-28 | IFC | OL1-2G30-5514 | PE | 2019-07-01 | 036909C-JVD-TRN-02042 | 036909C-JVD-TRN-02042 | IFR | 2019-07-16 | 2019-07-17 | R1-No comments | TPSK-LSPA1-T-PE-02042 |  | 2019-07-02 | 2
036909C-1052-PDS-0800-5211 | Process Equipment Datasheet - 10-D-5210 - Pilot Gas Vaporizer Cond Pot | 0 | 2019-06-28 | IFC | OL1-2G30-5211 | PE | 2019-07-01 | 036909C-JVD-TRN-02041 | 036909C-JVD-TRN-02041 | IFR | 2019-07-16 | 2019-07-17 | R1-No comments | TPSK-LSPA1-T-PE-02041 |  | 2019-07-02 | 2
036909C-1052-PDS-0800-5202 | Process Equipment Datasheet - 10-D-5220 - MP Ethylene Superhtr Cond Pot | 0 | 2019-06-28 | IFC | OL1-2G30-5202 | PE | 2019-07-01 | 036909C-JVD-TRN-02042 | 036909C-JVD-TRN-02042 | IFR | 2019-07-16 | 2019-07-17 | R1-No comments | TPSK-LSPA1-T-PE-02042 |  | 2019-07-02 | 2
036909C-1027-PDS-0600-2716 | Process Equipment Datasheet - 10-E-2714 - C5 Cut Cooler | C | 2019-06-24 | IFD | OL1-2G30-2716 | PE | 2019-06-25 | 036909C-JVD-TRN-01990 | 036909C-JVD-TRN-01990 | IFR | 2019-07-10 | 2019-07-17 | R1-No comments | TPSK-LSPA1-T-PE-01990 |  | 2019-06-26 | 2
036909C-1055-PDS-0800-5555 | Process Equipment Datasheet - 10-D-5553 - LPG Vaporizer - Superhtr Cond Pot | 0 | 2019-06-28 | IFC | OL1-2G30-5555 | PE | 2019-07-01 | 036909C-JVD-TRN-02042 | 036909C-JVD-TRN-02042 | IFR | 2019-07-16 | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02042 |  | 2019-07-02 | 2
036909C-1027-CN-0014-2729 | PSV-2767 Sizing Calculation | A | 2019-06-19 | IFR | OL1-2G23-2729 | PE | 2019-06-25 | 036909C-JVD-TRN-01988 | 036909C-JVD-TRN-01988 | IFR | 2019-07-10 | 2019-07-17 | R1-No comments | TPSK-LSPA1-T-PE-01988 |  | 2019-06-26 | 2
036909C-1027-CN-0014-2736 | PSV-2768 Sizing Calculation | A | 2019-06-24 | IFR | OL1-2G23-2736 | PE | 2019-06-26 | 036909C-JVD-TRN-02002 | 036909C-JVD-TRN-02002 | IFR | 2019-07-11 | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02002 |  | 2019-06-27 | 2
036909C-1027-CN-0014-2713 | PSV-2733 A-B-C-D-E Sizing Calculation | A | 2019-06-24 | IFR | OL1-2G23-2713 | PE | 2019-06-26 | 036909C-JVD-TRN-02002 | 036909C-JVD-TRN-02002 | IFR | 2019-07-11 | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02002 |  | 2019-06-27 | 2
036909C-PO-036909C001P10_1 | Vendor s Acknowledgment of Purchase Order For Cold Box And Core Exchangers Rev. 0 – MR 0662-0002 Rev 1 | 0 | 2019-07-03 | IFI | OL1-2C51-0010 | PL | 2019-07-03 | 036909C-JVD-TRN-02073 | 036909C-JVD-TRN-02073 | IFI |  | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-PL-02073 |  | 2019-07-05 | 3
036909C-1011-PDS-1390-1112 | Piping Specialty Item – Datasheet Isokinetic Sampling Nozzle SP-11012 | B | 2019-07-15 | IFD | OL1-2P03-1112 | MP | 2019-07-16 | 036909C-JVD-TRN-02160 | 036909C-JVD-TRN-02160 | IFR | 2019-07-31 |  | Transmitted | TPSK-LSPA1-T-MP-02160 |  | 2019-07-17 | 2
036909C-1027-SP-0510-2710 | Mechanical Equipment Data Sheet - Depentanizer | B | 2019-05-06 | IFQ | OL1-2M03-2710 | ME | 2019-05-06 | 036909C-JVD-TRN-01588 | 036909C-JVD-TRN-01588 | IFR | 2019-05-21 | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-ME -01588 |  | 2019-05-07 | 2
036909C-1054-PDS-0800-5400 | Process Equipment Datasheet - 10-D-5400 - Instrument Air Receiver | C | 2019-03-04 | IFD | OL1-2G30-5400 | PE | 2019-03-04 | 036909C-JVD-TRN-00983 | 036909C-JVD-TRN-00983 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00983 |  | 2019-03-05 | 2
036909C-1000-PP-017 | Computerized Maintenance Management System CMMS | A | 2018-12-21 | IFR | OL1-2W92-0022 | PC | 2019-01-03 | 036909C-JVD-TRN-00578 | 036909C-JVD-TRN-00578 | IFR | 2019-01-17 |  | Transmitted | TPSK-LSPA1-T-PC-00578 |  | 2019-01-03 | 2
036909C-1010-PDS-0800-1000 | Process Equipment Datasheet - 10-D-1000 - LPG Drum | B | 2018-12-07 | IFD | OL1-2G30-1000 | PE | 2018-12-10 | 036909C-JVD-TRN-00463 | 036909C-JVD-TRN-00463 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00463 |  | 2018-12-10 | 2
036909C-1024-SP-0810-2405 | Mechanical Equipment Data Sheet - Gas Dryer Feed KO Drum | A | 2019-01-05 | IFQ | OL1-2M03-2405 | ME | 2019-01-11 | 036909C-JVD-TRN-00629 | 036909C-JVD-TRN-00629, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00629 |  | 2019-01-11 | 2
036909C-1024-SP-0810-2405 | Mechanical Equipment Data Sheet - Gas Dryer Feed KO Drum | B | 2019-04-22 | IFQ | OL1-2M03-2405 | ME | 2019-04-30 | 036909C-JVD-TRN-01533 | 036909C-JVD-TRN-01533 | IFR | 2019-05-15 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01533 |  | 2019-05-02 | 2
036909C-1023-SP-0810-2390 | Mechanical Equipment Data Sheet - Caustic Drain Drum | A | 2018-12-13 | IFQ | OL1-2M03-2390 | ME | 2018-12-17 | 036909C-JVD-TRN-00514 | 036909C-JVD-TRN-00514, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-31 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00514 |  | 2018-12-17 | 2
036909C-1023-SP-0810-2390 | Mechanical Equipment Data Sheet - Caustic Drain Drum | C | 2019-05-30 | IFQ | OL1-2M03-2390 | ME | 2019-05-30 | 036909C-JVD-TRN-01783 | 036909C-JVD-TRN-01783 | IFR | 2019-06-14 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-ME-01783 |  | 2019-05-31 | 2
036909C-1023-SP-0810-2390 | Mechanical Equipment Data Sheet - Caustic Drain Drum | B | 2019-03-18 | IFQ | OL1-2M03-2390 | ME | 2019-03-28 | 036909C-JVD-TRN-01186 | 036909C-JVD-TRN-01186 | IFR | 2019-04-12 | 2019-05-02 | R2-Comments as noted | TPSK-LSPA1-T-ME-01186 |  | 2019-03-29 | 2
036909C-1023-SP-0810-2392 | Mechanical Equipment Data Sheet - Spent Caustic Drain Drum | C | 2019-05-30 | IFQ | OL1-2M03-2392 | ME | 2019-05-30 | 036909C-JVD-TRN-01783 | 036909C-JVD-TRN-01783 | IFR | 2019-06-14 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-ME-01783 |  | 2019-05-31 | 2
036909C-1023-SP-0810-2392 | Mechanical Equipment Data Sheet - Spent Caustic Drain Drum | A | 2019-01-11 | IFQ | OL1-2M03-2392 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685, ROC-TPSK-CECO-T-00014 | IFR | 2019-02-04 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-00685 |  | 2019-01-22 | 2
036909C-1023-SP-0810-2392 | Mechanical Equipment Data Sheet - Spent Caustic Drain Drum | B | 2019-04-03 | IFQ | OL1-2M03-2392 | ME | 2019-04-03 | 036909C-JVD-TRN-01244 | 036909C-JVD-TRN-01244 | IFR | 2019-04-18 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-01244 |  | 2019-04-04 | 2
036909C-1023-PDS-0800-2310 | Process Equipment Datasheet - 10-D-2310 - Spent Caustic Deoiling Drum | B | 2019-01-02 | IFD | OL1-2G30-2310 | PE | 2019-01-07 | 036909C-JVD-TRN-00599 | 036909C-JVD-TRN-00599 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00599 |  | 2019-01-07 | 2
036909C-1023-PDS-0800-2310 | Process Equipment Datasheet - 10-D-2310 - Spent Caustic Deoiling Drum | C | 2019-07-01 | IFD | OL1-2G30-2310 | PE | 2019-07-01 | 036909C-JVD-TRN-02043 | 036909C-JVD-TRN-02043 | IFR | 2019-07-16 |  | Transmitted | TPSK-LSPA1-T-PE-02043 |  | 2019-07-02 | 2
036909C-1029-SP-0810-2932 | Mechanical Equipment Data Sheet - Methanol Drum | A | 2019-01-18 | IFQ | OL1-2M03-2932 | ME | 2019-01-23 | 036909C-JVD-TRN-00709 | 036909C-JVD-TRN-00709, ROC-TPSK-CECO-T-00015 | IFR | 2019-02-05 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00709 |  | 2019-01-23 | 2
036909C-1024-SP-0810-2456 | Mechanical Equipment Data Sheet - LP Deprop Reboilder Cond Pot | A | 2019-01-17 | IFQ | OL1-2M03-2456 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685, ROC-TPSK-CECO-T-00014 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00685 |  | 2019-01-22 | 2
036909C-1024-SP-0810-2452 | Mechanical Equipment Data Sheet - LP Depropanizer Reflux Drum | A | 2018-12-10 | IFQ | OL1-2M03-2452 | ME | 2018-12-17 | 036909C-JVD-TRN-00516 | 036909C-JVD-TRN-00516, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-31 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00516 |  | 2018-12-17 | 2
036909C-1024-SP-0810-2452 | Mechanical Equipment Data Sheet - LP Depropanizer Reflux Drum | B | 2019-03-22 | IFQ | OL1-2M03-2452 | ME | 2019-04-30 | 036909C-JVD-TRN-01533 | 036909C-JVD-TRN-01533 | IFR | 2019-05-15 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01533 |  | 2019-05-02 | 2
036909C-1055-TDS-0610-5511 | Mechanical Equipment Data Sheet - 10-E-5510 - Cold Flare Blowdown Vaporizer | B | 2019-04-25 | IFQ | OL1-2M03-5511 | ME | 2019-04-26 | 036909C-JVD-TRN-01495 | 036909C-JVD-TRN-01495 | IFR | 2019-05-13 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01495 |  | 2019-04-29 | 2
036909C-1055-TDS-0610-5511 | Mechanical Equipment Data Sheet - 10-E-5510 - Cold Flare Blowdown Vaporizer | A | 2019-01-22 | IFQ | OL1-2M03-5511 | ME | 2019-01-29 | 036909C-JVD-TRN-00755 | 036909C-JVD-TRN-00755, ROC-TPSK-CECO-T-00018 | IFR | 2019-02-12 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00755 |  | 2019-01-29 | 2
036909C-1028-TDS-0610-2859 | Mechanical Equipment Data Sheet - 10-E-2856 - Ethylene Product Subcooler | A | 2018-12-18 | IFQ | OL1-2M03-2859 | ME | 2018-12-20 | 036909C-JVD-TRN-00541 | 036909C-JVD-TRN-00541, ROC-TPSK-CECO-T-00018 | IFR | 2019-01-02 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00541 |  | 2018-12-20 | 2
036909C-PO-036909C001P6_1 | Vendor s Acknowledgment of Purchase Order For Centrifugal Compressor Steam Turbine Driven Site Services Rev 1 | 0 | 2019-07-04 | IFI | OL1-2C51-0014 | PL | 2019-07-04 | 036909C-JVD-TRN-02076 | 036909C-JVD-TRN-02076 | IFI |  | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-PL-02076 |  | 2019-07-05 | 3
036909C-1028-TDS-0610-2809 | Mechanical Equipment Data Sheet - 10-E-2809 - C3 Chiller No 2 | A | 2018-12-13 | IFQ | OL1-2M03-2809 | ME | 2018-12-14 | 036909C-JVD-TRN-00505 | 036909C-JVD-TRN-00505, ROC-TPSK-CECO-T-00018 | IFR | 2018-12-27 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00505 |  | 2018-12-14 | 2
036909C-1025-TDS-0610-2582 | Mechanical Equipment Data Sheet - 10-E-2582 - C2 Tower Reflux Cooler | A | 2019-01-14 | IFQ | OL1-2M03-2582 | ME | 2019-01-16 | 036909C-JVD-TRN-00661 | 036909C-JVD-TRN-00661 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00661 |  | 2019-01-16 | 2
036909C-1025-TDS-0610-2503 | Mechanical Equipment Data Sheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | B | 2019-03-19 | IFQ | OL1-2M03-2503 | ME | 2019-03-29 | 036909C-JVD-TRN-01205 | 036909C-JVD-TRN-01205 | IFR | 2019-04-15 | 2019-05-02 | R1-No comments | TPSK-LSPA1-T-ME-01205 |  | 2019-04-01 | 2
036909C-1025-TDS-0610-2502 | Mechanical Equipment Data Sheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | B | 2019-03-19 | IFQ | OL1-2M03-2502 | ME | 2019-03-29 | 036909C-JVD-TRN-01205 | 036909C-JVD-TRN-01205 | IFR | 2019-04-15 | 2019-05-02 | R1-No comments | TPSK-LSPA1-T-ME-01205 |  | 2019-04-01 | 2
036909C-1025-TDS-0610-2502 | Mechanical Equipment Data Sheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | A | 2018-12-06 | IFQ | OL1-2M03-2502 | ME | 2018-12-10 | 036909C-JVD-TRN-00461 | 036909C-JVD-TRN-00461, ROC-TPSK-CECO-T-00017 | IFR | 2018-12-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00461 |  | 2018-12-10 | 2
036909C-1021-TDS-0610-2165 | Mechanical Equipment Data Sheet - 10-E-2165 A-D - DSG Reboilers | A | 2018-12-22 | IFQ | OL1-2M03-2165 | ME | 2019-01-03 | 036909C-JVD-TRN-00582 | 036909C-JVD-TRN-00582, ROC-TPSK-CECO-T-00017 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00582 |  | 2019-01-03 | 2
036909C-PO-036909C001P5_1 | Vendor s Acknowledgment of Purchase Order For Steam Turbine Drive Centrifugal Compressor Rev 1 – MR 1011-0001 Rev 1 | 0 | 2019-07-04 | IFI | OL1-2C51-0013 | PL | 2019-07-04 | 036909C-JVD-TRN-02076 | 036909C-JVD-TRN-02076 | IFI |  | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-PL-02076 |  | 2019-07-05 | 3
036909C-1012-PDS-1390-1251 | Piping Specialty Item Datasheet - 10-BDV-12001-16001 | A | 2019-04-17 | IFR | OL1-2P03-1251 | PE | 2019-04-23 | 036909C-JVD-TRN-01457 | 036909C-JVD-TRN-01457 | IFR | 2019-05-08 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-01457 |  | 2019-04-24 | 2
036909C-1012-PDS-1390-1212 | Piping Specialty Item Datasheet - 10-SP-12012-16012 | A | 2019-04-17 | IFR | OL1-2P03-1212 | MP | 2019-04-23 | 036909C-JVD-TRN-01457 | 036909C-JVD-TRN-01457 | IFR | 2019-05-08 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-01457 |  | 2019-04-24 | 2
036909C-1011-PDS-1390-1151 | Piping Specialty Item Datasheet - 10-BDV-11001 | A | 2019-04-17 | IFR | OL1-2P03-1151 | PE | 2019-04-23 | 036909C-JVD-TRN-01457 | 036909C-JVD-TRN-01457 | IFR | 2019-05-08 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-01457 |  | 2019-04-24 | 2
036909C-1011-PDS-1390-1112 | Piping Specialty Item Datasheet - 10-SP-11012 | A | 2019-04-23 | IFR | OL1-2P03-1112 | PE | 2019-04-23 | 036909C-JVD-TRN-01457 | 036909C-JVD-TRN-01457 | IFR | 2019-05-08 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-PE-01457 |  | 2019-04-24 | 2
036909C-1000-CN-1431-0001 | Calculation Note For Piles | A | 2019-03-15 | IFR | OL1-2K11-0001 | CV | 2019-03-19 | 036909C-JVD-TRN-01092 | 036909C-JVD-TRN-01092, ROC-TPSK-CECO-T-00021, ROC-TPSK-CECO-T-00034 | IFA | 2019-04-03 | 2019-04-12 | A2 - Approved with comments re-submit is not required | TPSK-LSPA1-T-CV-01092 |  | 2019-03-20 | 1
036909C-1051-SP-0810-5114 | Mechanical Equipment Data Sheet - LP Condensate Flash Drum | A | 2019-01-10 | IFQ | OL1-2M03-5114 | ME | 2019-01-16 | 036909C-JVD-TRN-00657 | 036909C-JVD-TRN-00657, ROC-TPSK-CECO-T-00016 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00657 |  | 2019-01-16 | 2
036909C-1051-SP-0810-5112 | Mechanical Equipment Data Sheet - Suspect Condensate Flash Drum | A | 2019-01-05 | IFQ | OL1-2M03-5112 | ME | 2019-01-16 | 036909C-JVD-TRN-00657 | 036909C-JVD-TRN-00657, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00657 |  | 2019-01-16 | 2
036909C-1028-SP-0810-2805 | Mechanical Equipment Data Sheet - C3R Surge Drum | A | 2018-12-05 | IFQ | OL1-2M03-2805 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483, ROC-TPSK-CECO-T-00015 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483 |  | 2018-12-13 | 2
036909C-1028-SP-0810-2805 | Mechanical Equipment Data Sheet - C3R Surge Drum | B | 2019-03-25 | IFQ | OL1-2M03-2805 | ME | 2019-03-28 | 036909C-JVD-TRN-01186 | 036909C-JVD-TRN-01186 | IFR | 2019-04-12 | 2019-05-02 | R1-No comments | TPSK-LSPA1-T-ME-01186 |  | 2019-03-29 | 2
036909C-1027-SP-0810-2790 | Mechanical Equipment Data Sheet - Light Oil Drain Drum | A | 2018-12-20 | IFQ | OL1-2M03-2790 | ME | 2019-01-08 | 036909C-JVD-TRN-00607 | 036909C-JVD-TRN-00607, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-22 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-ME-00607 |  | 2019-01-08 | 2
036909C-1027-SP-0810-2790 | Mechanical Equipment Data Sheet - Light Oil Drain Drum | B | 2019-05-29 | IFQ | OL1-2M03-2790 | ME | 2019-05-30 | 036909C-JVD-TRN-01780 | 036909C-JVD-TRN-01780 | IFR | 2019-06-14 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01780 |  | 2019-05-31 | 2
036909C-1027-SP-0810-2718 | Mechanical Equipment Data Sheet - Rerun Tower Reflux Drum | A | 2019-02-06 | IFQ | OL1-2M03-2718 | ME | 2019-02-15 | 036909C-JVD-TRN-00869 | 036909C-JVD-TRN-00869, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-04 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00869 |  | 2019-02-15 | 2
036909C-1027-SP-0810-2718 | Mechanical Equipment Data Sheet - Rerun Tower Reflux Drum | B | 2019-06-04 | IFQ | OL1-2M03-2718 | ME | 2019-06-04 | 036909C-JVD-TRN-01803 | 036909C-JVD-TRN-01803 | IFR | 2019-06-19 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01803 |  | 2019-06-10 | 2
036909C-1025-SP-0810-2504 | Mechanical Equipment Data Sheet - Demeth Prefrac Feed Separator No 1 | A | 2018-12-06 | IFQ | OL1-2M03-2504 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483, ROC-TPSK-CECO-T-00015 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483 |  | 2018-12-13 | 2
036909C-1025-SP-0810-2504 | Mechanical Equipment Data Sheet - Demeth Prefrac Feed Separator No 1 | B | 2019-03-22 | IFQ | OL1-2M03-2504 | ME | 2019-04-30 | 036909C-JVD-TRN-01534 | 036909C-JVD-TRN-01534 | IFR | 2019-05-15 | 2019-06-18 | R1-No comments | TPSK-LPSA1-T-ME-01534 |  | 2019-05-02 | 2
036909C-1023-SP-0810-2309 | Mechanical Equipment Data Sheet - Yellow Oil Drum | B | 2019-05-02 | IFQ | OL1-2M03-2309 | ME | 2019-05-06 | 036909C-JVD-TRN-01571 | 036909C-JVD-TRN-01571 | IFR | 2019-05-21 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-ME-01571 |  | 2019-05-07 | 2
036909C-1023-SP-0810-2309 | Mechanical Equipment Data Sheet - Yellow Oil Drum | A | 2018-12-10 | IFQ | OL1-2M03-2309 | ME | 2018-12-13 | 036909C-JVD-TRN-00484 | 036909C-JVD-TRN-00484, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00484 |  | 2018-12-13 | 2
036909C-1022-SP-0810-2245 | Mechanical Equipment Data Sheet - CG 4th Stage Discharge Drum | A | 2018-12-24 | IFQ | OL1-2M03-2245 | ME | 2019-01-16 | 036909C-JVD-TRN-00657 | 036909C-JVD-TRN-00657, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00657 |  | 2019-01-16 | 2
036909C-1022-SP-0810-2245 | Mechanical Equipment Data Sheet - CG 4th Stage Discharge Drum | B | 2019-04-11 | IFQ | OL1-2M03-2245 | ME | 2019-04-12 | 036909C-JVD-TRN-01347 | 036909C-JVD-TRN-01347 | IFR | 2019-04-29 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME-01347 |  | 2019-04-15 | 2
036909C-1022-SP-0810-2240 | Mechanical Equipment Data Sheet - CG 4th Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2240 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483 |  | 2018-12-13 | 2
036909C-1022-SP-0810-2240 | Mechanical Equipment Data Sheet - CG 4th Stage Suction Drum | B | 2019-03-18 | IFQ | OL1-2M03-2240 | ME | 2019-03-28 | 036909C-JVD-TRN-01186 | 036909C-JVD-TRN-01186 | IFR | 2019-04-12 | 2019-05-02 | R1-No comments | TPSK-LSPA1-T-ME-01186 |  | 2019-03-29 | 2
036909C-PO-036909C001P45 | Vendor s Acknowledgment of Purchase Order For Hydrogen Production Unit - MR 4111-0001 Rev 0 | 0 | 2019-07-04 | IFI | OL1-2C51-0012 | PL | 2019-07-04 | 036909C-JVD-TRN-02076 | 036909C-JVD-TRN-02076 | IFI |  | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-PL-02076 |  | 2019-07-05 | 3
036909C-PO-036909C001P44_1 | Vendor s Acknowledgment of Purchase Order For Integrally Geared Decoking Air Compressor Rev 1 – MR 1013-0001 Rev 0 | 0 | 2019-07-04 | IFI | OL1-2C51-0011 | PL | 2019-07-04 | 036909C-JVD-TRN-02074 | 036909C-JVD-TRN-02074 | IFI |  | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-PL-02074 |  | 2019-07-05 | 3
036909C-1024-TDS-0610-2412 | Mechanical Equipment Data Sheet - 10-E-2412 - HP Deprop Feed Chiller | A | 2019-01-04 | IFQ | OL1-2M03-2412 | ME | 2019-01-10 | 036909C-JVD-TRN-00617 | 036909C-JVD-TRN-00617, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-23 | 2019-01-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-00617 |  | 2019-01-10 | 2
036909C-1055-SP-0810-5552 | Mechanical Equipment Data Sheet - LPG Storage Drum | B | 2019-05-27 | IFQ | OL1-2M03-5552 | ME | 2019-05-30 | 036909C-JVD-TRN-01783 | 036909C-JVD-TRN-01783 | IFR | 2019-06-14 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01783 |  | 2019-05-31 | 2
036909C-1055-SP-0810-5520 | Mechanical Equipment Data Sheet - Vent Collection Drum | A | 2019-01-10 | IFQ | OL1-2M03-5520 | ME | 2019-01-11 | 036909C-JVD-TRN-00638 | 036909C-JVD-TRN-00638, ROC-TPSK-CECO-T-00016 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00638 |  | 2019-01-11 | 2
036909C-1055-SP-0810-5520 | Mechanical Equipment Data Sheet - Vent Collection Drum | B | 2019-05-27 | IFQ | OL1-2M03-5520 | ME | 2019-05-30 | 036909C-JVD-TRN-01783 | 036909C-JVD-TRN-01783 | IFR | 2019-06-14 | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-ME-01783 |  | 2019-05-31 | 2
036909C-1039-SP-0810-3908 | Mechanical Equipment Data Sheet - Predistillation Inhibitor Drum | A | 2019-04-17 | IFQ | OL1-2M03-3908 | ME | 2019-04-17 | 036909C-JVD-TRN-01389 | 036909C-JVD-TRN-01389 | IFR | 2019-05-02 |  | Transmitted | TPSK-LSPA1-T-ME-01389 |  | 2019-04-18 | 2
036909C-1028-SP-0810-2830 | Mechanical Equipment Data Sheet - C3R 3rd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2830 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483, ROC-TPSK-CECO-T-00015 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483 |  | 2018-12-13 | 2
036909C-1028-SP-0810-2820 | Mechanical Equipment Data Sheet - C3R 2nd Stage Suction Drum | B | 2019-05-31 | IFQ | OL1-2M03-2820 | ME | 2019-06-04 | 036909C-JVD-TRN-01803 | 036909C-JVD-TRN-01803 | IFR | 2019-06-19 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-01803 |  | 2019-06-10 | 2
036909C-1028-SP-0810-2820 | Mechanical Equipment Data Sheet - C3R 2nd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2820 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483, ROC-TPSK-CECO-T-00015 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483 |  | 2018-12-13 | 2
036909C-1028-SP-0810-2815 | Mechanical Equipment Data Sheet - C3R Drain Drum | B | 2019-05-30 | IFQ | OL1-2M03-2815 | ME | 2019-05-30 | 036909C-JVD-TRN-01783 | 036909C-JVD-TRN-01783 | IFR | 2019-06-14 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01783 |  | 2019-05-31 | 2
036909C-1028-SP-0810-2815 | Mechanical Equipment Data Sheet - C3R Drain Drum | A | 2018-12-18 | IFQ | OL1-2M03-2815 | ME | 2019-01-08 | 036909C-JVD-TRN-00607 | 036909C-JVD-TRN-00607, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-22 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-ME-00607 |  | 2019-01-08 | 2
036909C-1027-SP-0810-2750 | Mechanical Equipment Data Sheet - C4-C5 Hydrog Surge Drum | B | 2019-06-06 | IFQ | OL1-2M03-2750 | ME | 2019-06-06 | 036909C-JVD-TRN-01817 | 036909C-JVD-TRN-01817 | IFR | 2019-06-21 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01817 |  | 2019-06-10 | 2
036909C-1027-SP-0810-2750 | Mechanical Equipment Data Sheet - C4-C5 Hydrog Surge Drum | A | 2019-02-08 | IFQ | OL1-2M03-2750 | ME | 2019-02-15 | 036909C-JVD-TRN-00869 | 036909C-JVD-TRN-00869, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-04 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00869 |  | 2019-02-15 | 2
036909C-1027-SP-0810-2705 | Mechanical Equipment Data Sheet - GHU-1 Hot Separator | B | 2019-06-04 | IFQ | OL1-2M03-2705 | ME | 2019-06-04 | 036909C-JVD-TRN-01803 | 036909C-JVD-TRN-01803 | IFR | 2019-06-19 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01803 |  | 2019-06-10 | 2
036909C-1027-SP-0810-2705 | Mechanical Equipment Data Sheet - GHU-1 Hot Separator | A | 2019-02-14 | IFQ | OL1-2M03-2705 | ME | 2019-02-19 | 036909C-JVD-TRN-00893 | 036909C-JVD-TRN-00893, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-06 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00893 |  | 2019-02-19 | 2
036909C-1026-SP-0810-2667 | Mechanical Equipment Data Sheet - C5-Pygas Surge Drum | A | 2019-02-08 | IFQ | OL1-2M03-2667 | ME | 2019-02-15 | 036909C-JVD-TRN-00869 | 036909C-JVD-TRN-00869, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-04 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00869 |  | 2019-02-15 | 2
036909C-1026-SP-0810-2667 | Mechanical Equipment Data Sheet For C5-Pygas Surge Drum | B | 2019-06-04 | IFQ | OL1-2M03-2667 | ME | 2019-06-04 | 036909C-JVD-TRN-01803 | 036909C-JVD-TRN-01803 | IFR | 2019-06-19 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01803 |  | 2019-06-10 | 2
036909C-1025-SP-0810-2574 | Mechanical Equipment Data Sheet - Deethanizer Reboilder Cond Pot | A | 2018-12-20 | IFQ | OL1-2M03-2574 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685, ROC-TPSK-CECO-T-00015 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00685 |  | 2019-01-22 | 2
036909C-1025-SP-0810-2572 | Mechanical Equipment Data Sheet - Deethanizer Reflux Drum | A | 2018-12-10 | IFQ | OL1-2M03-2572 | ME | 2018-12-13 | 036909C-JVD-TRN-00484 | 036909C-JVD-TRN-00484, ROC-TPSK-CECO-T-00015 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00484 |  | 2018-12-13 | 2
036909C-1024-SP-0810-2444 | Mechanical Equipment Data Sheet - HP Deprop Reboiler Cond Pot | B | 2019-04-09 | IFQ | OL1-2M03-2444 | ME | 2019-04-10 | 036909C-JVD-TRN-01314 | 036909C-JVD-TRN-01314 | IFR | 2019-04-25 | 2019-06-05 | R1-No comments | TPSK-LSPA1-T-ME -01314 |  | 2019-04-11 | 2
036909C-1024-SP-0810-2444 | Mechanical Equipment Data Sheet - HP Deprop Reboiler Cond Pot | C | 2019-04-23 | IFQ | OL1-2M03-2444 | ME | 2019-05-15 | 036909C-JVD-TRN-01670 | 036909C-JVD-TRN-01670 | IFR | 2019-05-30 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-ME-01670 |  | 2019-05-16 | 2
036909C-1024-SP-0810-2444 | Mechanical Equipment Data Sheet - HP Deprop Reboiler Cond Pot | A | 2019-01-05 | IFQ | OL1-2M03-2444 | ME | 2019-01-11 | 036909C-JVD-TRN-00629 | 036909C-JVD-TRN-00629, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00629 |  | 2019-01-11 | 2
036909C-1024-SP-0810-2435 | Mechanical Equipment Data Sheet - Regen Gas Separator | A | 2019-01-17 | IFQ | OL1-2M03-2435 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685, ROC-TPSK-CECO-T-00014 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00685 |  | 2019-01-22 | 2
036909C-1023-SP-0810-2331 | Mechanical Equipment Data Sheet - Spent Caustic Stripper OVHD Drum | B | 2019-04-12 | IFQ | OL1-2M03-2331 | ME | 2019-05-01 | 036909C-JVD-TRN-01536 | 036909C-JVD-TRN-01536 | IFR | 2019-05-16 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01536 |  | 2019-05-02 | 2
036909C-1023-SP-0810-2331 | Mechanical Equipment Data Sheet - Spent Caustic Stripper OVHD Drum | A | 2019-01-10 | IFQ | OL1-2M03-2331 | ME | 2019-01-11 | 036909C-JVD-TRN-00638 | 036909C-JVD-TRN-00638, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00638 |  | 2019-01-11 | 2
036909C-1023-SP-0810-2316 | Mechanical Equipment Data Sheet - Spent Caustic Degassing Drum | A | 2018-12-10 | IFQ | OL1-2M03-2316 | ME | 2019-01-07 | 036909C-JVD-TRN-00601 | 036909C-JVD-TRN-00601, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-21 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00601 |  | 2019-01-07 | 2
036909C-1028-TDS-0610-2856 | Mechanical Equipment Data Sheet - 10-E-2855 - C2R Condenser | B | 2019-01-30 | IFQ | OL1-2M03-2856 | ME | 2019-01-30 | 036909C-JVD-TRN-00773 | 036909C-JVD-TRN-00773, ROC-TPSK-CECO-T-00018 | IFR | 2019-02-15 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00773 |  | 2019-01-31 | 2
036909C-1027-TDS-0610-2702 | Mechanical Equipment Data Sheet - 10-E-2702 - GHU-1 Start-Up Heater | B | 2019-06-03 | IFQ | OL1-2M03-2702 | ME | 2019-06-04 | 036909C-JVD-TRN-01806 | 036909C-JVD-TRN-01806 | IFR | 2019-06-19 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-ME -01806 |  | 2019-06-10 | 2
036909C-1026-TDS-0610-2645 | Mechanical Equipment Data Sheet - 10-E-2645 - C3 Tower Reboilers | B | 2019-01-30 | IFQ | OL1-2M03-2645 | ME | 2019-01-30 | 036909C-JVD-TRN-00773 | 036909C-JVD-TRN-00773, ROC-TPSK-CECO-T-00018 | IFR | 2019-02-15 | 2019-02-26 | R1-No comments | TPSK-LSPA1-T-ME-00773 |  | 2019-01-31 | 2
036909C-1030-SP-0910-3033 | Mechanical Equipment Datasheet for After Washer Reflux-Crude Butadiene Pumps | B | 2019-06-13 | IFQ | OL1-2M03-3033 | ME | 2019-06-17 | 036909C-JVD-TRN-01910 | 036909C-JVD-TRN-01910 | IFR | 2019-07-02 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-01910 |  | 2019-06-18 | 2
036909C-1030-SP-0910-3006 | Mechanical Equipment Datasheet for Predistallation Tower Feed Pumps | B | 2019-06-13 | IFQ | OL1-2M03-3006 | ME | 2019-06-17 | 036909C-JVD-TRN-01910 | 036909C-JVD-TRN-01910 | IFR | 2019-07-02 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-01910 |  | 2019-06-18 | 2
036909C-1030-SP-0910-3007 | Mechanical Equipment Datasheet for Predistillation Tower Reflux Pumps | B | 2019-06-13 | IFQ | OL1-2M03-3007 | ME | 2019-06-17 | 036909C-JVD-TRN-01910 | 036909C-JVD-TRN-01910 | IFR | 2019-07-02 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-01910 |  | 2019-06-18 | 2
036909C-1030-SP-0910-3016 | Mechanical Equipment Datasheet for Heavy Ends Discharge Pumps | B | 2019-06-13 | IFQ | OL1-2M03-3016 | ME | 2019-06-17 | 036909C-JVD-TRN-01910 | 036909C-JVD-TRN-01910 | IFR | 2019-07-02 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-01910 |  | 2019-06-18 | 2
036909C-1030-SP-0910-3036 | Mechanical Equipment Datasheet for After Washer Bottom Pumps | B | 2019-06-12 | IFQ | OL1-2M03-3036 | ME | 2019-06-17 | 036909C-JVD-TRN-01910 | 036909C-JVD-TRN-01910 | IFR | 2019-07-02 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-01910 |  | 2019-06-18 | 2
036909C-1030-SP-0910-3047 | Mechanical Equipment Datasheet for Rectifier Pumps | B | 2019-06-12 | IFQ | OL1-2M03-3047 | ME | 2019-06-17 | 036909C-JVD-TRN-01910 | 036909C-JVD-TRN-01910 | IFR | 2019-07-02 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-01910 |  | 2019-06-18 | 2
036909C-1012-TBT-0132-2013 | Technical Bid Tabulation for Radiant Refractory | 0 | 2019-05-06 | IFI | OL1-2C23-2013 | PL | 2019-05-07 | 036909C-JVD-TRN-01608 | 036909C-JVD-TRN-01608 | IFI |  | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-01608 |  | 2019-05-08 | 3
036909C-1021-CN-0014-2108 | PSV-2131 Sizing Calculation | A | 2019-06-07 | IFR | OL1-2G23-2108 | PE | 2019-06-07 | 036909C-JVD-TRN-01834 | 036909C-JVD-TRN-01834 | IFR | 2019-06-24 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-01834 |  | 2019-06-10 | 2
036909C-1001-CN-3444-0001 | GATEHOUSE A – HVAC Thermal Calculation | A | 2019-04-01 | IFR | OL1-2H10-0003 | EE | 2019-04-08 | 036909C-JVD-TRN-01273 | 036909C-JVD-TRN-01273, ROC-TPSK-CECO-T-00050 | IFA | 2019-04-23 | 2019-05-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-01273 |  | 2019-04-09 | 1
036909C-1001-CN-3444-0002 | PREFABRICATED GATEHOUSE – HVAC Thermal Calculation | A | 2019-04-01 | IFR | OL1-2H10-0004 | EE | 2019-04-08 | 036909C-JVD-TRN-01273 | 036909C-JVD-TRN-01273, ROC-TPSK-CECO-T-00050 | IFA | 2019-04-23 | 2019-05-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-01273 |  | 2019-04-09 | 1
036909C-1022-TDS-0610-2231 | Mechanical Equipment Data Sheet - 10-E-2230 - CG 3rd Stage Aftercooler | A | 2019-01-04 | IFQ | OL1-2M03-2231 | ME | 2019-01-07 | 036909C-JVD-TRN-00588 | 036909C-JVD-TRN-00588 | IFR | 2019-01-21 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00588 |  | 2019-01-07 | 2
036909C-1055-TDS-0610-5513 | Mechanical Equipment Data Sheet - 10-E-5513 - Methanol Vaporizer | B | 2019-03-27 | IFQ | OL1-2M03-5513 | ME | 2019-03-29 | 036909C-JVD-TRN-01205 | 036909C-JVD-TRN-01205 | IFR | 2019-04-15 | 2019-05-02 | TPSK-LSPA1-E-00190 May 09 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01205 |  | 2019-04-01 | 2
036909C-1027-TDS-0610-2765 | Mechanical Equipment Data Sheet - 10-E-2765 - C4 - C5 Hydrog Recycle Cooler | C | 2019-05-20 | IFQ | OL1-2M03-2765 | ME | 2019-05-21 | 036909C-JVD-TRN-01712 | 036909C-JVD-TRN-01712 | IFR | 2019-06-05 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01712 |  | 2019-05-23 | 2
036909C-1027-TDS-0610-2763 | Mechanical Equipment Data Sheet - 10-E-2760 - C4-C5 Hydro Vent Condenser | B | 2019-03-29 | IFQ | OL1-2M03-2763 | ME | 2019-03-29 | 036909C-JVD-TRN-01205 | 036909C-JVD-TRN-01205 | IFR | 2019-04-15 | 2019-05-02 | R1-No comments | TPSK-LSPA1-T-ME-01205 |  | 2019-04-01 | 2
036909C-1027-TDS-0610-2703 | Mechanical Equipment Data Sheet - 10-E-2705 - GHU-1 Recycle Cooler | B | 2019-04-12 | IFQ | OL1-2M03-2703 | ME | 2019-04-16 | 036909C-JVD-TRN-01357 | 036909C-JVD-TRN-01357 | IFR | 2019-05-01 |  | Transmitted | TPSK-LSPA1-T-ME-01357 |  | 2019-04-16 | 2
036909C-1027-TDS-0610-2703 | Mechanical Equipment Data Sheet - 10-E-2705 - GHU-1 Recycle Cooler | C | 2019-05-20 | IFQ | OL1-2M03-2703 | ME | 2019-05-21 | 036909C-JVD-TRN-01712 | 036909C-JVD-TRN-01712 | IFR | 2019-06-05 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01712 |  | 2019-05-23 | 2
036909C-1027-TDS-0610-2701 | Mechanical Equipment Data Sheet - 10-E-2701 - GHU-1 Feed Effluent Exchanger | B | 2019-04-01 | IFQ | OL1-2M03-2701 | ME | 2019-04-02 | 036909C-JVD-TRN-01230 | 036909C-JVD-TRN-01230 | IFR | 2019-04-17 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-01230 |  | 2019-04-03 | 2
036909C-1027-TDS-0610-2701 | Mechanical Equipment Data Sheet - 10-E-2701 - GHU-1 Feed - Effluent Exchanger | A | 2019-03-18 | IFQ | OL1-2M03-2701 | ME | 2019-03-20 | 036909C-JVD-TRN-01100 | 036909C-JVD-TRN-01100 | IFR | 2019-04-04 |  | Transmitted | TPSK-LSPA1-T-ME-01100 |  | 2019-03-21 | 2
036909C-1024-TDS-0610-2472 | Mechanical Equipment Data Sheet - 10-E-2472 - C2 Hydrog 2nd Stage Intercooler | A | 2019-01-10 | IFQ | OL1-2M03-2472 | ME | 2019-01-11 | 036909C-JVD-TRN-00641 | 036909C-JVD-TRN-00641, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-00641 |  | 2019-01-11 | 2
036909C-1024-TDS-0610-2471 | Mechanical Equipment Data Sheet - 10-E-2470 - C2 Hydrog 1st Stage Intercooler | A | 2019-01-10 | IFQ | OL1-2M03-2471 | ME | 2019-01-11 | 036909C-JVD-TRN-00641 | 036909C-JVD-TRN-00641, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-24 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00641 |  | 2019-01-11 | 2
036909C-1024-TDS-0610-2461 | Mechanical Equipment Data Sheet - 10-E-2460 - C2 Hydrog Feed Cooler | A | 2018-12-26 | IFQ | OL1-2M03-2461 | ME | 2019-01-03 | 036909C-JVD-TRN-00573 | 036909C-JVD-TRN-00573, ROC-TPSK-CECO-T-00017 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00573 |  | 2019-01-03 | 2
036909C-1024-TDS-0610-2474 | Mechanical Equipment Data Sheet - 10-E-2474 - C2 Hydrog Aftercooler | A | 2019-01-09 | IFQ | OL1-2M03-2474 | ME | 2019-01-11 | 036909C-JVD-TRN-00641 | 036909C-JVD-TRN-00641, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-00641 |  | 2019-01-11 | 2
036909C-1024-TDS-0610-2474 | Mechanical Equipment Data Sheet - 10-E-2474 - C2 Hydrog Aftercooler | C | 2019-05-15 | IFQ | OL1-2M03-2474 | ME | 2019-05-21 | 036909C-JVD-TRN-01714 | 036909C-JVD-TRN-01714 | IFR | 2019-06-05 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01714 |  | 2019-05-23 | 2
036909C-1024-TDS-0610-2474 | Mechanical Equipment Data Sheet - 10-E-2474 - C2 Hydrog Aftercooler | B | 2019-03-21 | IFQ | OL1-2M03-2474 | ME | 2019-03-29 | 036909C-JVD-TRN-01205 | 036909C-JVD-TRN-01205 | IFR | 2019-04-15 | 2019-05-02 | R2-Comments as noted | TPSK-LSPA1-T-ME-01205 |  | 2019-04-01 | 2
036909C-1022-TDS-0610-2221 | Mechanical Equipment Data Sheet - 10-E-2220 - CG 2nd Stage Aftercooler | A | 2019-01-03 | IFQ | OL1-2M03-2221 | ME | 2019-01-07 | 036909C-JVD-TRN-00588 | 036909C-JVD-TRN-00588 | IFR | 2019-01-21 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00588 |  | 2019-01-07 | 2
036909C-1022-TDS-0610-2211 | Mechanical Equipment Data Sheet - 10-E-2210 A-B - CG 1st Stage Aftercoolers | A | 2019-01-15 | IFQ | OL1-2M03-2211 | ME | 2019-01-22 | 036909C-JVD-TRN-00683 | 036909C-JVD-TRN-00683 | IFR | 2019-02-04 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00683 |  | 2019-01-22 | 2
036909C-1055-SP-0810-5565 | Mechanical Equipment Data Sheet - Polyolefins Flare Knock-Out Drum | B | 2019-05-31 | IFQ | OL1-2M03-5565 | ME | 2019-06-04 | 036909C-JVD-TRN-01803 | 036909C-JVD-TRN-01803 | IFR | 2019-06-19 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01803 |  | 2019-06-10 | 2
036909C-1055-SP-0810-5565 | Mechanical Equipment Data Sheet - Polyolefins Flare Knock-Out Drum | A | 2019-01-21 | IFQ | OL1-2M03-5565 | ME | 2019-01-23 | 036909C-JVD-TRN-00709 | 036909C-JVD-TRN-00709, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-05 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00709 |  | 2019-01-23 | 2
036909C-1055-SP-0810-5550 | Mechanical Equipment Data Sheet - HP Flare Knock-Out Drum | A | 2019-01-07 | IFQ | OL1-2M03-5550 | ME | 2019-01-11 | 036909C-JVD-TRN-00629 | 036909C-JVD-TRN-00629 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00629 |  | 2019-01-11 | 2
036909C-1055-SP-0810-5550 | Mechanical Equipment Data Sheet - HP Flare Knock-Out Drum | C | 2019-05-23 | IFQ | OL1-2M03-5550 | ME | 2019-05-29 | 036909C-JVD-TRN-01764 | 036909C-JVD-TRN-01764 | IFR | 2019-06-13 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01764 |  | 2019-05-30 | 2
036909C-1055-SP-0810-5550 | Mechanical Equipment Data Sheet - HP Flare Knock-Out Drum | B | 2019-03-15 | IFQ | OL1-2M03-5550 | ME | 2019-03-20 | 036909C-JVD-TRN-01114 | 036909C-JVD-TRN-01114, ROC-TPSK-CECO-T-00016 | IFR | 2019-04-04 |  | Transmitted | TPSK-LSPA1-T-ME-01114 |  | 2019-03-21 | 2
036909C-1055-SP-0810-5510 | Mechanical Equipment Data Sheet - Cold Flare Drum | A | 2019-01-05 | IFQ | OL1-2M03-5510 | ME | 2019-01-11 | 036909C-JVD-TRN-00629 | 036909C-JVD-TRN-00629, ROC-TPSK-CECO-T-00016 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00629 |  | 2019-01-11 | 2
036909C-1055-SP-0810-5500 | Mechanical Equipment Data Sheet - Hot Flare Drum | A | 2018-12-07 | IFQ | OL1-2M03-5500 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483, ROC-TPSK-CECO-T-00016 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483 |  | 2018-12-13 | 2
036909C-1055-SP-0810-5500 | Mechanical Equipment Data Sheet - Hot Flare Drum | B | 2019-03-22 | IFQ | OL1-2M03-5500 | ME | 2019-04-30 | 036909C-JVD-TRN-01535 | 036909C-JVD-TRN-01535 | IFR | 2019-05-15 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01535 |  | 2019-05-02 | 2
036909C-1054-SP-0810-5400 | Mechanical Equipment Data Sheet - Instrument Air Receiver | B | 2019-05-22 | IFQ | OL1-2M03-5400 | ME | 2019-05-22 | 036909C-JVD-TRN-01723 | 036909C-JVD-TRN-01723 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01723 |  | 2019-05-23 | 2
036909C-1054-SP-0810-5400 | Mechanical Equipment Data Sheet - Instrument Air Receiver | A | 2019-01-15 | IFQ | OL1-2M03-5400 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-04 | 2019-02-15 | R1-No comments | TPSK-LSPA1-T-ME-00685 |  | 2019-01-22 | 2
036909C-1051-PDS-0600-5108 | Process Equipment Datasheet - 10-E-5110 - Suspect Condensate Cooler | C | 2019-06-18 | IFD | OL1-2G30-5108 | PE | 2019-06-18 | 036909C-JVD-TRN-01918 | 036909C-JVD-TRN-01918, 036909C-JVD-TRN-01920 | IFR | 2019-07-03 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01918 |  | 2019-06-19 | 2
036909C-1055-CN-0014-5510 | PSV-5532 A-B Sizing Calculation | A | 2019-06-14 | IFR | OL1-2G23-5510 | PE | 2019-06-17 | 036909C-JVD-TRN-01912 | 036909C-JVD-TRN-01912 | IFR | 2019-07-02 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01912 |  | 2019-06-18 | 2
036909C-1055-CN-0014-5509 | PSV-5531 A-B Sizing Calculation | A | 2019-06-14 | IFR | OL1-2G23-5509 | PE | 2019-06-17 | 036909C-JVD-TRN-01912 | 036909C-JVD-TRN-01912 | IFR | 2019-07-02 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01912 |  | 2019-06-18 | 2
036909C-1055-CN-0014-5503 | PSV-5509 Sizing Calculation | A | 2019-06-13 | IFR | OL1-2G23-5503 | PE | 2019-06-17 | 036909C-JVD-TRN-01912 | 036909C-JVD-TRN-01912 | IFR | 2019-07-02 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01912 |  | 2019-06-18 | 2
036909C-1027-CN-0014-2732 | PSV-2752 Sizing Calculation | A | 2019-06-18 | IFR | OL1-2G23-2732 | PE | 2019-06-25 | 036909C-JVD-TRN-01983 | 036909C-JVD-TRN-01983 | IFR | 2019-07-09 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01983 |  | 2019-06-26 | 2
036909C-1027-CN-0014-2728 | PSV-2766 Sizing Calculation | A | 2019-06-13 | IFR | OL1-2G23-2728 | PE | 2019-06-17 | 036909C-JVD-TRN-01911 | 036909C-JVD-TRN-01911 | IFR | 2019-07-02 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01911 |  | 2019-06-18 | 2
036909C-1027-CN-0014-2727 | PSV-2761 A-B Sizing Calculation | A | 2019-06-19 | IFR | OL1-2G23-2727 | PE | 2019-06-25 | 036909C-JVD-TRN-01983 | 036909C-JVD-TRN-01983 | IFR | 2019-07-09 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01983 |  | 2019-06-26 | 2
036909C-1027-CN-0014-2720 | PSV-2748 Sizing Calculation | A | 2019-06-14 | IFR | OL1-2G23-2720 | PE | 2019-06-17 | 036909C-JVD-TRN-01911 | 036909C-JVD-TRN-01911 | IFR | 2019-07-02 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01911 |  | 2019-06-18 | 2
036909C-1027-CN-0014-2719 | PSV-2747 Sizing Calculation | A | 2019-06-16 | IFR | OL2-2G23-2719 | PE | 2019-06-17 | 036909C-JVD-TRN-01911 | 036909C-JVD-TRN-01911 | IFR | 2019-07-02 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01911 |  | 2019-06-18 | 2
036909C-1027-CN-0014-2718 | PSV-2744 Sizing Calculation | A | 2019-06-13 | IFR | OL1-2G23-2718 | PE | 2019-06-17 | 036909C-JVD-TRN-01911 | 036909C-JVD-TRN-01911 | IFR | 2019-07-02 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01911 |  | 2019-06-18 | 2
036909C-1027-CN-0014-2717 | PSV-2741 Sizing Calculation | A | 2019-06-13 | IFR | OL1-2G23-2717 | PE | 2019-06-17 | 036909C-JVD-TRN-01911 | 036909C-JVD-TRN-01911 | IFR | 2019-07-02 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01911 |  | 2019-06-18 | 2
036909C-1027-CN-0014-2715 | PSV-2737 Sizing Calculation | A | 2019-06-13 | IFR | OL1-2G23-2715 | PE | 2019-06-17 | 036909C-JVD-TRN-01911 | 036909C-JVD-TRN-01911 | IFR | 2019-07-02 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01911 |  | 2019-06-18 | 2
036909C-1027-CN-0014-2712 | PSV-2729 Sizing Calculation | A | 2019-06-12 | IFR | OL1-2G23-2712 | PE | 2019-06-17 | 036909C-JVD-TRN-01911 | 036909C-JVD-TRN-01911 | IFR | 2019-07-02 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01911 |  | 2019-06-18 | 2
036909C-1027-CN-0014-2711 | PSV-2726 Sizing Calculation | A | 2019-06-12 | IFR | OL1-2G23-2711 | PE | 2019-06-17 | 036909C-JVD-TRN-01911 | 036909C-JVD-TRN-01911 | IFR | 2019-07-02 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01911 |  | 2019-06-18 | 2
036909C-1022-CN-0014-2201 | PSV-2201 A-B-C Sizing Calculation | B | 2019-05-28 | IFR | OL1-2G23-2201 | PE | 2019-06-07 | 036909C-JVD-TRN-01831 | 036909C-JVD-TRN-01831 | IFR | 2019-06-24 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01831 |  | 2019-06-10 | 2
036909C-1023-NM-0007-2301 | Piping Specialty Item - Datasheet Index - Caustic and Spent Caustic Treatment - Area 23 | A | 2019-06-25 | IFR | OL1-2G91-2301 | PE | 2019-06-25 | 036909C-JVD-TRN-01992 | 036909C-JVD-TRN-01992 | IFR | 2019-07-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01992 |  | 2019-06-26 | 2
036909C-1022-NM-0007-2201 | Piping Specialty Item - Datasheet Index - Cracked Gas Compression - Area 22 | A | 2019-06-24 | IFR | OL1-2G91-2201 | PE | 2019-06-25 | 036909C-JVD-TRN-01991 | 036909C-JVD-TRN-01991 | IFR | 2019-07-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01991 |  | 2019-06-26 | 2
036909C-1024-PDS-1546-2490 | Process Datasheet for Restriction Orifice - Area 24 | A | 2019-06-18 | IFR | OL1-2G23-2490 | PE | 2019-06-19 | 036909C-JVD-TRN-01929 | 036909C-JVD-TRN-01929 | IFR | 2019-07-04 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01929 |  | 2019-06-20 | 2
036909C-1027-CN-0014-2730 | PSV-2771 Calculation | A | 2019-06-20 | IFR | OL1-2G23-2730 | PE | 2019-06-25 | 036909C-JVD-TRN-01983 | 036909C-JVD-TRN-01983 | IFR | 2019-07-09 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01983 |  | 2019-06-26 | 2
036909C-1027-CN-0014-2725 | PSV-2755 Calculation | A | 2019-06-18 | IFR | OL1-2G23-2725 | PE | 2019-06-25 | 036909C-JVD-TRN-01983 | 036909C-JVD-TRN-01983 | IFR | 2019-07-09 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01983 |  | 2019-06-26 | 2
036909C-1027-CN-0014-2724 | PSV-2751 Sizing Calculation | A | 2019-06-18 | IFR | OL1-2G23-2724 | PE | 2019-06-25 | 036909C-JVD-TRN-01983 | 036909C-JVD-TRN-01983 | IFR | 2019-07-09 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01983 |  | 2019-06-26 | 2
036909C-1024-CN-0014-2437 | PSV-2452 Sizing Calculation | A | 2019-04-26 | IFR | OL1-2G23-2437 | PE | 2019-06-19 | 036909C-JVD-TRN-01924 | 036909C-JVD-TRN-01924 | IFR | 2019-07-04 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01924 |  | 2019-06-20 | 2
036909C-1021-CN-0014-2101 | PSV-2105 A-O Sizing Calculation | A | 2019-06-07 | IFR | OL1-2G23-2101 | PE | 2019-06-07 | 036909C-JVD-TRN-01834 | 036909C-JVD-TRN-01834 | IFR | 2019-06-24 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01834 |  | 2019-06-10 | 2
036909C-1027-CN-0014-2726 | PSV-2760 Sizing Calculation | A | 2019-06-13 | IFR | OL1-2G23-2726 | PE | 2019-06-17 | 036909C-JVD-TRN-01911 | 036909C-JVD-TRN-01911 | IFR | 2019-07-02 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01911 |  | 2019-06-18 | 2
036909C-1027-CN-0014-2723 | PSV-2750 Sizing Calculation | A | 2019-06-17 | IFR | OL1-2G23-2723 | PE | 2019-06-17 | 036909C-JVD-TRN-01911 | 036909C-JVD-TRN-01911 | IFR | 2019-07-02 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01911 |  | 2019-06-18 | 2
036909C-1027-CN-0014-2722 | PSV-2749 Sizing Calculation | A | 2019-06-17 | IFR | OL1-2G23-2722 | PE | 2019-06-17 | 036909C-JVD-TRN-01911 | 036909C-JVD-TRN-01911 | IFR | 2019-07-02 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01911 |  | 2019-06-18 | 2
036909C-1027-CN-0014-2721 | PSV-2746 Sizing Calculation | A | 2019-06-16 | IFR | OL1-2G23-2721 | PE | 2019-06-17 | 036909C-JVD-TRN-01911 | 036909C-JVD-TRN-01911 | IFR | 2019-07-02 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01911 |  | 2019-06-18 | 2
036909C-1027-CN-0014-2708 | PSV-2719 Sizing Calculation | A | 2019-06-12 | IFR | OL1-2G23-2708 | PE | 2019-06-17 | 036909C-JVD-TRN-01911 | 036909C-JVD-TRN-01911 | IFR | 2019-07-02 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01911 |  | 2019-06-18 | 2
036909C-1022-CN-0014-2210 | PSV-2266 A-B Sizing Calulation | B | 2019-06-03 | IFR | OL1-2G23-2210 | PE | 2019-06-07 | 036909C-JVD-TRN-01831 | 036909C-JVD-TRN-01831 | IFR | 2019-06-24 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01831 |  | 2019-06-10 | 2
036909C-1022-CN-0014-2204 | PSV-2230 A-B Sizing Calculation | B | 2019-06-04 | IFR | OL1-2G23-2204 | PE | 2019-06-07 | 036909C-JVD-TRN-01831 | 036909C-JVD-TRN-01831 | IFR | 2019-06-24 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01831 |  | 2019-06-10 | 2
036909C-102D-CN-1734-0001 | Calculation Note For Concrete Basin 10-PIT-5604 | A | 2019-07-04 | IFR | OL1-2K13-0330 | CV | 2019-07-10 | 036909C-JVD-TRN-02118 | 036909C-JVD-TRN-02118 | IFR | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02118 |  | 2019-07-11 | 1
036909C-102A-CN-1734-0002 | Calculation Note For Foundation Of Basin 10-PIT-5602 | A | 2019-07-02 | IFR | OL1-2K13-0340 | CV | 2019-07-10 | 036909C-JVD-TRN-02118 | 036909C-JVD-TRN-02118 | IFR | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02118 |  | 2019-07-11 | 1
036909C-102B-CN-1734-0001 | Calculation Note For Foundation Of 10-PIT-2190 | A | 2019-07-02 | IFR | OL1-2K13-0332 | CV | 2019-07-10 | 036909C-JVD-TRN-02118 | 036909C-JVD-TRN-02118 | IFR | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02118 |  | 2019-07-11 | 1
036909C-101B-CN-1734-0002 | Calculatoin Note For Foundation Of Lifting Station 10-PIT-5610 | A | 2019-07-04 | IFR | OL1-2K13-0327 | CV | 2019-07-10 | 036909C-JVD-TRN-02118 | 036909C-JVD-TRN-02118 | IFR | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02118 |  | 2019-07-11 | 1
036909C-1000-NM-0005-0001 | Effluent Summary | C | 2019-07-09 | IFD | OL1-2G63-0001 | PE | 2019-07-10 | 036909C-JVD-TRN-02123 | 036909C-JVD-TRN-02123 | IFR | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-PE-02123 |  | 2019-07-10 | 2
036909C-1000-JSS-1061-0001 | ME-019 Lube Oil Unit And Seal Oil System | 0 | 2019-01-07 | IMP | OL1-2R03-0019 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 | 2019-04-25 | R1-No comments | TPSK-LSPA1-T-ME-00668 |  | 2019-01-23 | 2
036909C-1000-JSS-1111-0001 | ME-018 General Purpose Steam Turbines | 0 | 2019-01-07 | IMP | OL1-2R03-0018 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 | 2019-04-25 | R1-No comments | TPSK-LSPA1-T-ME-00668 |  | 2019-01-23 | 2
036909C-1053-SP-0910-5361 | Mechanical Data Sheet - CTU Cooling Water Pumps | D | 2019-01-09 | IFQ | OL1-2M03-5361 | ME | 2019-01-11 | 036909C-JVD-TRN-00627 | 036909C-JVD-TRN-00627, ROC-TPSK-CECO-T-00016 | IFI |  | 2019-01-31 | R1-No comments | TPSK-LSPA1-T-ME-00627 |  | 2019-01-11 | 2
036909C-1023-PDS-0800-2331 | Process Equipment Datasheet - 10-D-2330 - Spent Caustic Stripper Ovhd Drum | C | 2019-04-11 | IFD | OL1-2G30-2331 | PE | 2019-04-11 | 036909C-JVD-TRN-01327 | 036909C-JVD-TRN-01327 | IFR | 2019-04-26 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01327 |  | 2019-04-12 | 2
036909C-1023-PDS-0800-2331 | Process Equipment Datasheet - 10-D-2330 - Spent Caustic Stripper Ovhd Drum | D | 2019-04-15 | IFD | OL1-2G30-2331 | PE | 2019-04-16 | 036909C-JVD-TRN-01377 | 036909C-JVD-TRN-01377 | IFR | 2019-05-01 |  | Transmitted | TPSK-LSPA1-T-PE-01377 |  | 2019-04-17 | 2
036909C-1011-NM-0022-1101 | Line Designation Table – Recycle Gas Cracking Furnace 10-H-1100 | B | 2019-06-20 | IDD1 | OL1-2P91-1101 | MP | 2019-06-21 | 036909C-JVD-TRN-01967 | 036909C-JVD-TRN-01967 | IFR |  | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-MP-01967 |  | 2019-06-24 | 2
036909C-1012-NM-0022-1201 | Line Designation Table - Liquid Cracking Furnace 10-H-1200 | B | 2019-06-20 | IDD1 | OL1-2P91-1201 | MP | 2019-06-21 | 036909C-JVD-TRN-01967 | 036909C-JVD-TRN-01967 | IFR |  | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-MP-01967 |  | 2019-06-24 | 2
036909C-1000-NM-0005-0001 | Effluent Summary | A | 2019-02-21 | IFR | OL1-2G63-0001 | PE | 2019-02-25 | 036909C-JVD-TRN-00922 | 036909C-JVD-TRN-00922, ROC-TPSK-CECO-T-00022 | IFR | 2019-03-12 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-PE-00922 |  | 2019-02-26 | 2
036909C-1000-NM-0005-0001 | Effluent Summary | B | 2019-05-09 | IFD | OL1-2G63-0001 | PE | 2019-05-10 | 036909C-JVD-TRN-01639 | 036909C-JVD-TRN-01639 | IFR | 2019-05-28 | 2019-05-31 | R2-Comments as noted | TPSK-LSPA1-T-PE-01639 |  | 2019-05-13 | 2
036909C-101A-ML-251 | Model Review Report Furnace Island Action List 30 | C | 2019-07-08 | IFR | OL1-2P30-0014 | MP | 2019-07-09 | 036909C-JVD-TRN-02107 | 036909C-JVD-TRN-02107 | IFR | 2019-07-24 |  | Transmitted | TPSK-LSPA1-T-MP-02107 |  | 2019-07-10 | 2
036909C-101A-ML-251 | Model Review Report Furnace Island Action List 30 Percent | B | 2019-05-30 | IFR | OL1-2P30-0014 | MP | 2019-05-30 | 036909C-JVD-TRN-01782 | 036909C-JVD-TRN-01782 | IFR | 2019-06-14 |  | Transmitted | TPSK-LSPA1-T-MP-01782 |  | 2019-05-31 | 2
036909C-1030-SP-1031-3073 | Mechanical Equipment Datasheet - BDU Recycle Gas Compressor | A | 2019-01-17 | IFQ | OL1-2M03-3073 | ME | 2019-01-22 | 036909C-JVD-TRN-00692 | 036909C-JVD-TRN-00692 | IFR | 2019-02-04 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00692 |  | 2019-01-22 | 2
036909C-1023-PDS-1390-2303 | Piping Specialty Item - T-Type Filter - P-2304 Suction - 10-SP-23003 | A | 2019-06-06 | IFR | OL1-2P03-2303 | MP | 2019-06-12 | 036909C-JVD-TRN-01884 | 036909C-JVD-TRN-01884 | IFR | 2019-06-27 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01884 |  | 2019-06-14 | 2
036909C-1021-CN-0014-2112 | PSV-2146 A-B & 2152 A-B Sizing Calculation | A | 2019-06-06 | IFR | OL1-2G23-2112 | PE | 2019-06-07 | 036909C-JVD-TRN-01831 | 036909C-JVD-TRN-01831 | IFR | 2019-06-24 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01831 |  | 2019-06-10 | 2
036909C-1021-CN-0014-2120 | PSV-2113 A-B Sizing Calculation | A | 2019-06-04 | IFR | OL1-2G23-2120 | PE | 2019-06-05 | 036909C-JVD-TRN-01811 | 036909C-JVD-TRN-01811 | IFR | 2019-06-20 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01811 |  | 2019-06-10 | 2
036909C-1021-CN-0014-2119 | PSV-2126 A-B Sizing Calculation | A | 2019-06-04 | IFR | OL1-2G23-2119 | PE | 2019-06-05 | 036909C-JVD-TRN-01811 | 036909C-JVD-TRN-01811 | IFR | 2019-06-20 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01811 |  | 2019-06-10 | 2
036909C-1021-CN-0014-2118 | PSV-2132 Sizing Calculation | A | 2019-06-04 | IFR | OL1-2G23-2118 | PE | 2019-06-05 | 036909C-JVD-TRN-01811 | 036909C-JVD-TRN-01811 | IFR | 2019-06-20 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01811 |  | 2019-06-10 | 2
036909C-1021-CN-0014-2109 | PSV-2130 Sizing Calculation | A | 2019-06-04 | IFR | OL1-2G23-2109 | PE | 2019-06-05 | 036909C-JVD-TRN-01811 | 036909C-JVD-TRN-01811 | IFR | 2019-06-20 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01811 |  | 2019-06-10 | 2
036909C-1021-CN-0014-2116 | PSV-2165 Sizing Calculation | A | 2019-06-07 | IFR | OL1-2G23-2116 | PE | 2019-06-07 | 036909C-JVD-TRN-01834 | 036909C-JVD-TRN-01834 | IFR | 2019-06-24 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01834 |  | 2019-06-10 | 2
036909C-1021-CN-0014-2110 | PSV-2135 Sizing Calculation | A | 2019-06-04 | IFR | OL1-2G23-2110 | PE | 2019-06-05 | 036909C-JVD-TRN-01811 | 036909C-JVD-TRN-01811 | IFR | 2019-06-20 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-PE-01811 |  | 2019-06-10 | 2
036909C-1021-CN-0014-2106 | PSV-2125 A-B Sizing Calculation | A | 2019-06-04 | IFR | OL1-2G23-2106 | PE | 2019-06-05 | 036909C-JVD-TRN-01811 | 036909C-JVD-TRN-01811 | IFR | 2019-06-20 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-PE-01811 |  | 2019-06-10 | 2
036909C-1021-CN-0014-2103 | PSV-2111 A-B Sizing Calculation | A | 2019-06-04 | IFR | OL1-2G23-2103 | PE | 2019-06-05 | 036909C-JVD-TRN-01811 | 036909C-JVD-TRN-01811 | IFR | 2019-06-20 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-PE-01811 |  | 2019-06-10 | 2
036909C-1021-CN-0014-2102 | PSV-2108 A-B Sizing Calculation | A | 2019-06-04 | IFR | OL1-2G23-2102 | PE | 2019-06-05 | 036909C-JVD-TRN-01811 | 036909C-JVD-TRN-01811 | IFR | 2019-06-20 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-PE-01811 |  | 2019-06-10 | 2
036909C-1051-TDS-0661-5108 | Mechanical Equipment Data Sheet - 10-E-5110 - Suspect Condensate Cooler | 1 | 2019-06-12 | IFP | OL1-2M03-5108 | ME | 2019-06-12 | 036909C-JVD-TRN-01882 | 036909C-JVD-TRN-01882 | IFR | 2019-06-27 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-01882 |  | 2019-06-14 | 2
036909C-1051-CN-0014-5104 | PSV-5140 A-B Sizing Calculation | A | 2019-06-05 | IFR | OL1-2G23-5104 | PE | 2019-06-07 | 036909C-JVD-TRN-01834 | 036909C-JVD-TRN-01834 | IFR | 2019-06-24 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01834 |  | 2019-06-10 | 2
036909C-1028-SP-0810-2880 | Mechanical Equipment Data Sheet - C2R 3RD Stage Suction Drum | B | 2019-01-17 | IFQ | OL1-2M03-2880 | ME | 2019-01-23 | 036909C-JVD-TRN-00708 | 036909C-JVD-TRN-00708, ROC-TPSK-CECO-T-00015 | IFR | 2019-02-05 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00708 |  | 2019-01-23 | 2
036909C-1028-SP-0810-2880 | Mechanical Equipment Data Sheet - C2R 3RD Stage Suction Drum | A | 2018-12-04 | IFQ | OL1-2M03-2880 | ME | 2018-12-10 | 036909C-JVD-TRN-00460 | 036909C-JVD-TRN-00460 | IFR | 2018-12-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00460 |  | 2018-12-10 | 2
036909C-1028-SP-0810-2880 | Mechanical Equipment Data Sheet - C2R 3RD Stage Suction Drum | C | 2019-05-22 | IFQ | OL1-2M03-2880 | ME | 2019-05-22 | 036909C-JVD-TRN-01723 | 036909C-JVD-TRN-01723 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01723 |  | 2019-05-23 | 2
036909C-1028-SP-0810-2840 | Mechanical Equipment Data Sheet - C3R 4TH Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2840 | ME | 2018-12-10 | 036909C-JVD-TRN-00460 | 036909C-JVD-TRN-00460, ROC-TPSK-CECO-T-00015 | IFR | 2018-12-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00460 |  | 2018-12-10 | 2
036909C-1028-SP-0810-2810 | Mechanical Equipment Data Sheet - C3R 1st Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2810 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483, ROC-TPSK-CECO-T-00015 | IFR | 2018-12-25 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00483 |  | 2018-12-13 | 2
036909C-1028-SP-0810-2810 | Mechanical Equipment Data Sheet - C3R 1st Stage Suction Drum | B | 2019-06-04 | IFQ | OL1-2M03-2810 | ME | 2019-06-04 | 036909C-JVD-TRN-01803 | 036909C-JVD-TRN-01803 | IFR | 2019-06-19 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-01803 |  | 2019-06-10 | 2
036909C-1022-SP-0810-2230 | Mechanical Equipment Data Sheet - CG 3rd Stage Suction Drum | B | 2019-03-18 | IFQ | OL1-2M03-2230 | ME | 2019-03-28 | 036909C-JVD-TRN-01186 | 036909C-JVD-TRN-01186 | IFR | 2019-04-12 | 2019-05-02 | R1-No comments | TPSK-LSPA1-T-ME-01186 |  | 2019-03-29 | 2
036909C-1022-SP-0810-2230 | Mechanical Equipment Data Sheet - CG 3rd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2230 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483 |  | 2018-12-13 | 2
036909C-1022-SP-0810-2220 | Mechanical Equipment Data Sheet - CG 2nd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2220 | ME | 2018-12-13 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00483 |  | 2018-12-13 | 2
036909C-1022-SP-0810-2220 | Mechanical Equipment Data Sheet - CG 2nd Stage Suction Drum | B | 2019-03-18 | IFQ | OL1-2M03-2220 | ME | 2019-03-28 | 036909C-JVD-TRN-01186 | 036909C-JVD-TRN-01186 | IFR | 2019-04-12 | 2019-05-02 | R1-No comments | TPSK-LSPA1-T-ME-01186 |  | 2019-03-29 | 2
036909C-1022-SP-0810-2210 | Mechanical Equipment Data Sheet - CG 1st Stage Suction Drum | B | 2019-03-20 | IFQ | OL1-2M03-2210 | ME | 2019-04-23 | 036909C-JVD-TRN-01448 | 036909C-JVD-TRN-01448 | IFR | 2019-05-08 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01448 |  | 2019-04-24 | 2
036909C-1022-SP-0810-2210 | Mechanical Equipment Data Sheet - CG 1st Stage Suction Drum | A | 2018-01-15 | IFQ | OL1-2M03-2210 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685, ROC-TPSK-CECO-T-00014 | IFR | 2019-02-04 | 2019-02-15 | R1-No comments | TPSK-LSPA1-T-ME-00685 |  | 2019-01-22 | 2
036909C-1051-SP-0910-5109 | Mechanical Equipment Data Sheet - Condensate Pumps | D | 2019-03-25 | IFQ | OL1-2M03-5109 | ME | 2019-03-25 | 036909C-JVD-TRN-01151 | 036909C-JVD-TRN-01151 | IFR | 2019-04-09 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-ME-01151 |  | 2019-03-26 | 2
036909C-1051-SP-0910-5109 | Mechanical Equipment Data Sheet - Condensate Pumps | E | 2019-03-29 | IFQ | OL1-2M03-5109 | ME | 2019-03-29 | 036909C-JVD-TRN-01197 | 036909C-JVD-TRN-01197 | IFR | 2019-04-15 |  | Transmitted | TPSK-LSPA1-T-ME-01197 |  | 2019-04-01 | 2
036909C-1051-SP-0910-5102 | Mechanical Equipment Data Sheet - VLP BFW Pumps | D | 2019-04-22 | IFQ | OL1-2M03-5102 | ME | 2019-04-22 | 036909C-JVD-TRN-01433 | 036909C-JVD-TRN-01433 | IFR | 2019-05-07 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01433 |  | 2019-04-23 | 2
036909C-1051-SP-0910-5102 | Mechanical Equipment Data Sheet - VLP BFW Pumps | C | 2019-04-01 | IFQ | OL1-2M03-5102 | ME | 2019-04-02 | 036909C-JVD-TRN-01227 | 036909C-JVD-TRN-01227 | IFR | 2019-04-17 |  | Transmitted | TPSK-LSPA1-T-ME-01227 |  | 2019-04-03 | 2
036909C-1051-SP-0910-5101 | Mechanical Equipment Data Sheet - SHP BFW Pumps | D | 2019-04-22 | IFQ | OL1-2M03-5101 | ME | 2019-04-22 | 036909C-JVD-TRN-01433 | 036909C-JVD-TRN-01433 | IFR | 2019-05-07 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01433 |  | 2019-04-23 | 2
036909C-1051-SP-0910-5101 | Mechanical Equipment Data Sheet - SHP BFW Pumps | C | 2018-11-28 | IFQ | OL1-2M03-5101 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476, ROC-TPSK-CECO-T-00016 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00476 |  | 2018-12-11 | 2
036909C-1021-SP-0910-2106 | Mechanical Equipment Data Sheet - Quench Water Pumps | C | 2019-03-26 | IFQ | OL1-2M03-2106 | ME | 2019-03-27 | 036909C-JVD-TRN-01173 | 036909C-JVD-TRN-01173 | IFR | 2019-04-11 | 2019-04-22 | R1-No comments | TPSK-LSPA1-T-ME-01173 |  | 2019-03-28 | 2
036909C-1021-PDS-0840-2139 | Process Equipment Datasheet - 10-F-2137 A-B - Process Water Coalescer Prefilters | B | 2019-06-04 | IFD | OL1-2G30-2139 | PE | 2019-06-04 | 036909C-JVD-TRN-01804 | 036909C-JVD-TRN-01804 | IFR | 2019-06-19 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01804 |  | 2019-06-10 | 2
036909C-1023-PDS-0500-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper | D | 2019-06-04 | IFD | OL1-2G30-2330 | PE | 2019-06-05 | 036909C-JVD-TRN-01808 | 036909C-JVD-TRN-01808 | IFR | 2019-06-20 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01808 |  | 2019-06-10 | 2
036909C-1052-CN-0014-5204 | PSV-5209 A-B Sizing Calculation | A | 2019-06-10 | IFR | OL1-2G23-5204 | PE | 2019-06-10 | 036909C-JVD-TRN-01851 | 036909C-JVD-TRN-01851 | IFR | 2019-06-25 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01851 |  | 2019-06-11 | 2
036909C-1021-CN-0014-2117 | PSV-2166 Sizing Calculation | A | 2019-06-05 | IFR | OL1-2G23-2117 | PE | 2019-06-06 | 036909C-JVD-TRN-01822 | 036909C-JVD-TRN-01822 | IFR | 2019-06-21 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01822 |  | 2019-06-10 | 2
036909C-1021-CN-0014-2105 | PSV-2120 A-B Sizing Calculation | A | 2019-06-05 | IFR | OL1-2G23-2105 | PE | 2019-06-06 | 036909C-JVD-TRN-01822 | 036909C-JVD-TRN-01822 | IFR | 2019-06-21 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01822 |  | 2019-06-10 | 2
036909C-1021-CN-0014-2104 | PSV-2115 A-E Sizing Calculation | A | 2019-06-05 | IFR | OL1-2G23-2104 | PE | 2019-06-06 | 036909C-JVD-TRN-01822 | 036909C-JVD-TRN-01822 | IFR | 2019-06-21 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01822 |  | 2019-06-10 | 2
036909C-1051-CN-0014-5106 | PSV-5150 A-D Sizing Calculation | A | 2019-06-06 | IFR | OL1-2G23-5106 | PE | 2019-06-07 | 036909C-JVD-TRN-01834 | 036909C-JVD-TRN-01834 | IFR | 2019-06-24 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01834 |  | 2019-06-10 | 2
036909C-1055-CN-0014-5504 | PSV-5510 A-B Sizing Calculation | A | 2019-06-10 | IFR | OL1-2G23-5504 | PE | 2019-06-10 | 036909C-JVD-TRN-01851 | 036909C-JVD-TRN-01851 | IFR | 2019-06-25 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01851 |  | 2019-06-11 | 2
036909C-1051-CN-0014-5105 | PSV-5143 A-K Sizing Calculation | A | 2019-06-07 | IFR | OL1-2G23-5105 | PE | 2019-06-10 | 036909C-JVD-TRN-01851 | 036909C-JVD-TRN-01851 | IFR | 2019-06-25 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01851 |  | 2019-06-11 | 2
036909C-1054-CN-0014-5401 | PSV-5401 Sizing Calculation | A | 2019-06-05 | IFR | OL1-2G23-5401 | PE | 2019-06-06 | 036909C-JVD-TRN-01822 | 036909C-JVD-TRN-01822 | IFR | 2019-06-21 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01822 |  | 2019-06-10 | 2
036909C-1051-CN-0014-5103 | PSV-5120 Sizing Calculation | A | 2019-06-04 | IFR | OL1-2G23-5103 | PE | 2019-06-06 | 036909C-JVD-TRN-01822 | 036909C-JVD-TRN-01822 | IFR | 2019-06-21 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01822 |  | 2019-06-10 | 2
036909C-1051-CN-0014-5102 | PSV-5113 Sizing Calculation | A | 2019-06-04 | IFR | OL1-2G23-5102 | PE | 2019-06-06 | 036909C-JVD-TRN-01822 | 036909C-JVD-TRN-01822 | IFR | 2019-06-21 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01822 |  | 2019-06-10 | 2
036909C-1052-CN-0014-5203 | PSV-5208 Sizing Calculation | A | 2019-06-07 | IFR | OL1-2G23-5203 | PE | 2019-06-07 | 036909C-JVD-TRN-01834 | 036909C-JVD-TRN-01834 | IFR | 2019-06-24 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01834 |  | 2019-06-10 | 2
036909C-1052-CN-0014-5201 | PSV-5201 Sizing Calculation | A | 2019-06-07 | IFR | OL1-2G23-5201 | PE | 2019-06-07 | 036909C-JVD-TRN-01834 | 036909C-JVD-TRN-01834 | IFR | 2019-06-24 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01834 |  | 2019-06-10 | 2
036909C-1051-CN-0014-5107 | PSV-5153 A-D Sizing Calculation | A | 2019-06-07 | IFR | OL1-2G23-5107 | PE | 2019-06-07 | 036909C-JVD-TRN-01834 | 036909C-JVD-TRN-01834 | IFR | 2019-06-24 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01834 |  | 2019-06-10 | 2
036909C-1020-CN-0014-2007 | PSV-2030 A-B Sizing Calculation | A | 2019-06-04 | IFR | OL1-2G23-2007 | PE | 2019-06-05 | 036909C-JVD-TRN-01811 | 036909C-JVD-TRN-01811 | IFR | 2019-06-20 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01811 |  | 2019-06-10 | 2
036909C-1027-SP-0510-2720 | Mechanical Equipment Data Sheet - Rerun Tower | 0 | 2019-06-04 | IFP | OL1-2M03-2720 | ME | 2019-06-05 | 036909C-JVD-TRN-01810 | 036909C-JVD-TRN-01810 | IFR | 2019-06-20 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-01810 |  | 2019-06-10 | 2
036909C-1027-SP-0510-2710 | Mechanical Equipment Data Sheet - Depentanizer | 0 | 2019-06-05 | IFP | OL1-2M03-2710 | ME | 2019-06-05 | 036909C-JVD-TRN-01810 | 036909C-JVD-TRN-01810 | IFR | 2019-06-20 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-01810 |  | 2019-06-10 | 2
036909C-1024-SP-0510-2440 | Mechanical Equipment Datasheet - HP Depropanizer | 1 | 2019-06-04 | IFP | OL1-2M03-2440 | ME | 2019-06-05 | 036909C-JVD-TRN-01812 | 036909C-JVD-TRN-01812 | IFR | 2019-06-20 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-01812 |  | 2019-06-10 | 2
036909C-1000-MR-1541-0003 | Material Requisition for Special Control Valves | A | 2019-06-13 | IFQ | OL1-2C17-050401 | PL | 2019-06-13 | 036909C-JVD-TRN-01891 | 036909C-JVD-TRN-01891 | IFR | 2019-07-01 | 2019-06-28 | R2-Comments as noted | TPSK-LSPA1-T-PL-01891 |  | 2019-06-13 | 2
036909C-1000-MR-1511-0001 | Material Requisition for Integrated Control And Safety Systems - ICSS | A | 2019-06-12 | IFQ | OL1-2C17-101001 | PL | 2019-06-13 | 036909C-JVD-TRN-01892 | 036909C-JVD-TRN-01892 | IFA | 2019-07-01 | 2019-06-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PL-01892 |  | 2019-06-13 | 1
036909C-1027-CN-0014-2703 | PSV-2706 Sizing Calculation | A | 2019-06-07 | IFR | OL1-2G23-2703 | PE | 2019-06-07 | 036909C-JVD-TRN-01834 | 036909C-JVD-TRN-01834 | IFR | 2019-06-24 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01834 |  | 2019-06-10 | 2
036909C-1020-CN-0014-2010 | PSV-2027 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2010 | PE | 2019-06-05 | 036909C-JVD-TRN-01811 | 036909C-JVD-TRN-01811 | IFR | 2019-06-20 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01811 |  | 2019-06-10 | 2
036909C-1020-CN-0014-2012 | PSV-2018 Sizing Calculation | A | 2019-06-04 | IFR | OL1-2G23-2012 | PE | 2019-06-05 | 036909C-JVD-TRN-01811 | 036909C-JVD-TRN-01811 | IFR | 2019-06-20 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01811 |  | 2019-06-10 | 2
036909C-1020-CN-0014-2011 | PSV-2011 A-B-C-D-E Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2011 | PE | 2019-06-05 | 036909C-JVD-TRN-01811 | 036909C-JVD-TRN-01811 | IFR | 2019-06-20 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01811 |  | 2019-06-10 | 2
036909C-1020-CN-0014-2009 | PSV-2028 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2009 | PE | 2019-06-05 | 036909C-JVD-TRN-01811 | 036909C-JVD-TRN-01811 | IFR | 2019-06-20 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01811 |  | 2019-06-10 | 2
036909C-1012-PDS-1040-1211 | Process Equipment Datasheet - 10-C-1200_1600 - USC 132U Induced Draft Fan | D | 2019-05-29 | IFD | OL1-2G30-1211 | PE | 2019-06-04 | 036909C-JVD-TRN-01797 | 036909C-JVD-TRN-01797 | IFR | 2019-06-19 | 2019-07-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01797 |  | 2019-06-10 | 2
036909C-1011-PDS-1040-1111 | Process Equipment Datasheet - 10-C-1100 - USC 36M Induced Draft Fan | D | 2019-05-24 | IFD | OL1-2G30-1111 | PE | 2019-06-04 | 036909C-JVD-TRN-01797 | 036909C-JVD-TRN-01797 | IFR | 2019-06-19 | 2019-07-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01797 |  | 2019-06-10 | 2
036909C-1028-SP-1546-2805 | Instrument Datasheets for Flow Element -Venturi- Area 28 | A | 2019-04-10 | IFQ | OL1-2I20-2823 | IE | 2019-04-23 | 036909C-JVD-TRN-01360 | 036909C-JVD-TRN-01360, ROC-TPSK-CECO-T-00056 | IFI |  | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-01360 |  | 2019-04-23 | 3
036909C-1025-SP-1546-2505 | Instrument Datasheets for Flow Element -Venturi - Area 25 | A | 2019-04-08 | IFQ | OL1-2I20-2523 | IE | 2019-04-23 | 036909C-JVD-TRN-01388 | 036909C-JVD-TRN-01388 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01388 |  | 2019-04-23 | 3
036909C-1011-PDS-0117-1105 | Process Equipment Datasheet - 10-H-1100 - API Fired Heater Process Datasheet | B | 2019-04-10 | IFD | OL1-2G30-1105 | PE | 2019-04-11 | 036909C-JVD-TRN-01322 | 036909C-JVD-TRN-01322 | IFR | 2019-04-26 | 2019-05-15 | R1-No comments | TPSK-LSPA1-T-PE-01322 |  | 2019-04-12 | 2
036909C-1011-CN-0015-1101 | Steam Drum and Superheater PSVs Sizing Calculation | B | 2019-04-25 | IFD | OL1-2G05-1101 | PE | 2019-04-26 | 036909C-JVD-TRN-01513 | 036909C-JVD-TRN-01513 | IFR | 2019-05-11 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-PE-01513 |  | 2019-04-29 | 2
036909C-102B-CN-1733-0046 | Calculation Note For Foundation Of 10-E-1006 | A | 2019-05-21 | IFR | OL1-2K13-0097 | CV | 2019-05-27 | 036909C-JVD-TRN-01749 | 036909C-JVD-TRN-01749 | IFA | 2019-06-11 | 2019-06-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01749 |  | 2019-05-28 | 1
036909C-1000-JSS-1800-0001 | Job Supply Specification for Steel Structures | A | 2019-03-04 | IFI | OL1-2R02-0006 | CV | 2019-03-06 | 036909C-JVD-TRN-00995 | 036909C-JVD-TRN-00995 | IFR | 2019-03-21 | 2019-03-31 | R2-Comments as noted | TPSK-LSPA1-T-CV-00995 |  | 2019-03-07 | 2
036909C-1000-NM-0050-0001 | Battery Limit Summary | A | 2019-02-27 | IFR | OL1-2G60-0001 | PE | 2019-02-28 | 036909C-JVD-TRN-00948 | 036909C-JVD-TRN-00948, ROC-TPSK-CECO-T-00022 | IFR | 2019-03-15 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00948 |  | 2019-03-01 | 2
036909C-1027-PDS-0500-2710 | Process Equipment Datasheet - 10-T-2710 Depentanizer | C | 2019-05-17 | IFD | OL1-2G30-2710 | PE | 2019-05-21 | 036909C-JVD-TRN-01708 | 036909C-JVD-TRN-01708 | IFR | 2019-06-05 | 2019-06-12 | CLIENT-COMMENT-TRN-01488-04 July 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01708 |  | 2019-05-23 | 2
036909C-PO-036909C001P10 | Vendor s Acknowledgment of Purchase Order For Cold Box And Core Exchangers – MR 0662-0002 Rev 0 | 0 | 2019-05-07 | IFI | OL1-2C51-0008 | PL | 2019-05-08 | 036909C-JVD-TRN-01613 | 036909C-JVD-TRN-01613 | IFI |  | 2019-05-22 | R1-No comments | TPSK-LSPA1-T-PL-01613 | 036909C-1000-MR-0662-0002_0 | 2019-05-09 | 3
036909C-1027-PDS-0800-2718 | Process Equipment Datasheet - 10-D-2720 - Rerun Tower Reflux Drum | A | 2019-01-28 | IFR | OL1-2G30-2718 | PE | 2019-02-01 | 036909C-JVD-TRN-00781 | 036909C-JVD-TRN-00781 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00781 |  | 2019-02-01 | 2
036909C-1000-DW-1802-0001 | General Notes For Steel Structure | 0 | 2019-02-14 | IFC | OL1-2K92-0004 | CV | 2019-02-15 | 036909C-JVD-TRN-00867 | 036909C-JVD-TRN-00867 | IFA | 2019-03-04 | 2019-03-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00867 |  | 2019-02-15 | 1
036909C-1001-DW-3438-0001 | Operation Tool Room - HVAC Layout And Section | A | 2019-04-01 | IFR | OL1-2H21-0015 | EE | 2019-04-04 | 036909C-JVD-TRN-01238 | 036909C-JVD-TRN-01238, ROC-TPSK-CECO-T-00050 | IFA | 2019-04-19 |  | Transmitted | TPSK-LSPA1-T-EE-1238 |  | 2019-04-05 | 1
036909C-1001-DW-3434-0002 | Prefabricated Gatehouse - HVAC Layout And Process Flow Diagram | A | 2019-04-01 | IFR | OL1-2H21-0011 | EE | 2019-04-04 | 036909C-JVD-TRN-01238 | 036909C-JVD-TRN-01238, ROC-TPSK-CECO-T-00050 | IFA | 2019-04-19 |  | Transmitted | TPSK-LSPA1-T-EE-1238 |  | 2019-04-05 | 1
036909C-1001-DW-3434-0001 | Gatehouse A - HVAC Layout And Process Flow Diagram | A | 2019-04-01 | IFR | OL1-2H21-0010 | EE | 2019-04-04 | 036909C-JVD-TRN-01238 | 036909C-JVD-TRN-01238, ROC-TPSK-CECO-T-00050 | IFA | 2019-04-19 |  | Transmitted | TPSK-LSPA1-T-EE-1238 |  | 2019-04-05 | 1
036909C-1011-PDS-0117-1105 | Process Equipment Datasheet - 10-H-1100 - API Fired Heater Process Datasheet | A | 2019-02-05 | IFR | OL1-2G30-1105 | PE | 2019-02-06 | 036909C-JVD-TRN-00814 | 036909C-JVD-TRN-00814 | IFR | 2019-02-20 |  | Transmitted | TPSK-LSPA1-T-PE-00814 |  | 2019-02-06 | 2
036909C-1011-CN-0015-1101 | Steam Drum and Superheater PSVs Sizing Calculation | A | 2019-01-23 | IFR | OL1-2G05-1101 | PE | 2019-01-30 | 036909C-JVD-TRN-00769 | 036909C-JVD-TRN-00769 | IFR | 2019-02-15 | 2019-03-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00769 |  | 2019-01-31 | 2
036909C-1000-PP-614 | Project Expediting And Inspection Level Definition | 1 | 2019-04-18 | IMP | OL1-2C92-0014 | PL | 2019-04-25 | 036909C-JVD-TRN-01477 | 036909C-JVD-TRN-01477 | IFR | 2019-05-09 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PL-01473 |  | 2019-04-25 | 2
036909C-1024-SP-1543-2403 | Instrument Datasheets for Control Valve - Butterfly Type - Area 24 | A | 2019-04-30 | IFQ | OL1-2I20-2402 | IE | 2019-05-02 13:00 | 036909C-JVD-TRN-01550 | 036909C-JVD-TRN-01550 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01550 |  | 2019-05-03 | 3
036909C-1024-SP-1543-2414 | Instrument Datasheets for Motor Operated Valve - Area 24 | A | 2019-04-30 | IFQ | OL1-2I20-2413 | IE | 2019-05-02 13:00 | 036909C-JVD-TRN-01550 | 036909C-JVD-TRN-01550 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01550 |  | 2019-05-03 | 3
036909C-1024-SP-1541-2401 | Instrument Datasheets for Control Valve - Globe Type - Area 24 | A | 2019-04-27 | IFQ | OL1-2I20-2401 | IE | 2019-05-02 13:00 | 036909C-JVD-TRN-01550 | 036909C-JVD-TRN-01550 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01550 |  | 2019-05-03 | 3
036909C-1023-SP-1543-2314 | Instrument Datasheets for Motor Operated Valve Area 23 | A | 2019-04-25 | IFQ | OL1-2I20-2313 | IE | 2019-05-02 13:00 | 036909C-JVD-TRN-01550 | 036909C-JVD-TRN-01550 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01550 |  | 2019-05-03 | 3
036909C-1022-SP-1543-2214 | Instrument Datasheets for Motor Operated Valve - MOV - Area 22 | A | 2019-04-10 | IFQ | OL1-2I20-2213 | IE | 2019-04-23 | 036909C-JVD-TRN-01301 | 036909C-JVD-TRN-01301 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01301 |  | 2019-04-23 | 3
036909C-1022-SP-1541-2201 | Instrument Datasheets for Control Valve - Globe Type- Area 22 | A | 2019-04-10 | IFQ | OL1-2I20-2201 | IE | 2019-04-23 | 036909C-JVD-TRN-01301 | 036909C-JVD-TRN-01301 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01301 |  | 2019-04-23 | 3
036909C-1051-PDS-0900-5109 | Process Equipment Datasheet - 10-P-5110 A-B - Condensate Pumps | D | 2019-03-28 | IFD | OL1-2G30-5109 | PE | 2019-03-28 | 036909C-JVD-TRN-01189 | 036909C-JVD-TRN-01189 | IFR | 2019-04-12 | 2019-05-09 | Response to Client Comments sent July 02 2019 R2-Comments as noted | TPSK-LSAP1-T-PE-01189 |  | 2019-03-29 | 2
036909C-1059-CN-0014-5906 | PSV-5924 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-5906 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1028-SP-1547-2806 | Instrument Datasheets for Flow Element - Coriolis - Area 28 | A | 2019-04-10 | IFQ | OL1-2I20-2830 | IE | 2019-04-23 | 036909C-JVD-TRN-01360 | 036909C-JVD-TRN-01360, ROC-TPSK-CECO-T-00056 | IFI |  | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-01360 |  | 2019-04-23 | 3
036909C-1027-CN-0014-2709 | PSV-2723 A-B-C-D Sizing Calculation | A | 2019-06-07 | IFR | OL1-2G23-2709 | PE | 2019-06-07 | 036909C-JVD-TRN-01834 | 036909C-JVD-TRN-01834 | IFR | 2019-06-24 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01834 |  | 2019-06-10 | 2
036909C-1027-CN-0014-2704 | PSV-2716 A-B Sizing Calculation | A | 2019-06-07 | IFR | OL1-2G23-2704 | PE | 2019-06-07 | 036909C-JVD-TRN-01834 | 036909C-JVD-TRN-01834 | IFR | 2019-06-24 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01834 |  | 2019-06-10 | 2
036909C-1027-CN-0014-2701 | PSV-2703 Sizing Calculation | A | 2019-06-06 | IFR | OL1-2G23-2701 | PE | 2019-06-07 | 036909C-JVD-TRN-01831 | 036909C-JVD-TRN-01831 | IFR | 2019-06-24 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01831 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5919 | PSV-5965 B Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-5919 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5918 | PSV-5965 A Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-5918 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5917 | PSV-5962 B Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-5917 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5916 | PSV-5962 A Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-5916 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5915 | PSV-5956 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-5915 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5914 | PSV-5952 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-5914 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5913 | PSV-5948 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-5913 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5912 | PSV-5944 Sizing Calculation | A | 2019-06-01 | IFR | OL1-2G23-5912 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5911 | PSV-5940 Sizing Calculation | A | 2019-06-01 | IFR | OL1-2G23-5911 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5910 | PSV-5938 Sizing Calculation | A | 2019-06-01 | IFR | OL1-2G23-5910 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5909 | PSV-5934 Sizing Calculation | A | 2019-06-01 | IFR | OL1-2G23-5909 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5908 | PSV-5930 Sizing Calculation | A | 2019-06-01 | IFR | OL1-2G23-5908 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5907 | PSV-5926 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-5907 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5905 | PSV-5920 Sizing Calculation | A | 2019-06-01 | IFR | OL1-2G23-5905 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5904 | PSV-5908 B Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-5904 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5903 | PSV-5908 A Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-5903 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5902 | PSV-5901 B Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-5902 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1059-CN-0014-5901 | PSV-5901 A Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-5901 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1054-CN-0014-5402 | PSV-5404 A-B Sizing Calculation | A | 2019-06-04 | IFR | OL1-2G23-5402 | PE | 2019-06-05 | 036909C-JVD-TRN-01811 | 036909C-JVD-TRN-01811 | IFR | 2019-06-20 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01811 |  | 2019-06-10 | 2
036909C-1028-CN-0014-2832 | PSV-2833 Sizing Calculation | A | 2019-06-06 | IFR | OL1-2G23-2832 | PE | 2019-06-07 | 036909C-JVD-TRN-01834 | 036909C-JVD-TRN-01834 | IFR | 2019-06-24 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01834 |  | 2019-06-10 | 2
036909C-1027-CN-0014-2702 | PSV-2704 Sizing Calculation | A | 2019-06-06 | IFR | OL1-2G23-2702 | PE | 2019-06-07 | 036909C-JVD-TRN-01831 | 036909C-JVD-TRN-01831 | IFR | 2019-06-24 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01831 |  | 2019-06-10 | 2
036909C-1020-CN-0014-2006 | PSV-2025 A-B Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2006 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1020-CN-0014-2005 | PSV-2020 A-B Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2005 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1020-CN-0014-2003 | PSV-2010 A-E Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2003 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1020-CN-0014-2002 | PSV-2006 A-C Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2002 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1020-CN-0014-2008 | PSV-2017 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2008 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1020-CN-0014-2004 | PSV-2016 A-B Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2004 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1020-CN-0014-2001 | PSV-2005 A-B Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2001 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1000-NM-0004-1002 | Catalyst & Chemicals Summary | 2 | 2019-06-27 | IFI | OL1-2G64-1002 | PE | 2019-07-01 | 036909C-JVD-TRN-02039 | 036909C-JVD-TRN-02039 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02039 |  | 2019-07-02 | 3
036909C-1055-PDS-0800-5555 | Process Equipment Datasheet - 10-D-5553 - LPG Vaporizer - Superhtr Cond Pot | C | 2019-05-06 | IFD | OL1-2G30-5555 | PE | 2019-05-06 | 036909C-JVD-TRN-01590 | 036909C-JVD-TRN-01590 | IFR | 2019-05-21 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-PE-01590 |  | 2019-05-07 | 2
036909C-1055-PDS-0800-5555 | Process Equipment Datasheet - 10-D-5553 - LPG Vaporizer - Superhtr Cond Pot | A | 2019-01-09 | IFR | OL1-2G30-5555 | PE | 2019-01-10 | 036909C-JVD-TRN-00619 | 036909C-JVD-TRN-00619 | IFR | 2019-01-23 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00619 |  | 2019-01-10 | 2
036909C-1055-PDS-0800-5514 | Process Equipment Datasheet - 10-D-5513 - Methanol Vaporizer Cond Pot | A | 2019-01-08 | IFR | OL1-2G30-5514 | PE | 2019-01-10 | 036909C-JVD-TRN-00614 | 036909C-JVD-TRN-00614 | IFR | 2019-01-23 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00614 |  | 2019-01-10 | 2
036909C-1052-PDS-0800-5202 | Process Equipment Datasheet - 10-D-5220 - MP Ethylene Superhtr Cond Pot | A | 2019-01-08 | IFR | OL1-2G30-5202 | PE | 2019-01-10 | 036909C-JVD-TRN-00614 | 036909C-JVD-TRN-00614 | IFR | 2019-01-23 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00614 |  | 2019-01-10 | 2
036909C-1052-PDS-0800-5211 | Process Equipment Datasheet - 10-D-5210 - Pilot Gas Vaporizer Cond Pot | A | 2019-01-08 | IFR | OL1-2G30-5211 | PE | 2019-01-10 | 036909C-JVD-TRN-00614 | 036909C-JVD-TRN-00614 | IFR | 2019-01-23 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00614 |  | 2019-01-10 | 2
036909C-1000-NM-0004-1002 | Catalyst & Chemicals Summary | 0 | 2019-03-25 | IFI | OL1-2G64-1002 | PE | 2019-03-25 | 036909C-JVD-TRN-01143 | 036909C-JVD-TRN-01143, ROC-TPSK-CECO-T-00027 | IFI |  | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01143 |  | 2019-03-26 | 3
036909C-1000-NM-0004-1002 | Catalyst & Chemicals Summary | 1 | 2019-05-13 | IFI | OL1-2G64-1002 | PE | 2019-05-14 | 036909C-JVD-TRN-01659 | 036909C-JVD-TRN-01659 | IFI |  | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01659 |  | 2019-05-15 | 3
036909C-1026-CN-0014-2620 | PSV-2646 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2620 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2619 | PSV-2631 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2619 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2618 | PSV-2625 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2618 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2615 | PSV-2650 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2615 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2614 | PSV-2645 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2614 | PE | 2019-06-04 | 036909C-JVD-TRN-01805 | 036909C-JVD-TRN-01805 | IFR | 2019-06-19 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-PE-01805 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2611 | PSV-2630 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2611 | PE | 2019-06-04 | 036909C-JVD-TRN-01805 | 036909C-JVD-TRN-01805 | IFR | 2019-06-19 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-PE-01805 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2610 | PSV-2624 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2610 | PE | 2019-06-04 | 036909C-JVD-TRN-01805 | 036909C-JVD-TRN-01805 | IFR | 2019-06-19 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-PE-01805 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2607 | PSV-2614 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2607 | PE | 2019-06-04 | 036909C-JVD-TRN-01805 | 036909C-JVD-TRN-01805 | IFR | 2019-06-19 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-PE-01805 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2606 | PSV-2610 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2606 | PE | 2019-06-04 | 036909C-JVD-TRN-01805 | 036909C-JVD-TRN-01805 | IFR | 2019-06-19 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-PE-01805 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2605 | PSV-2605 Sizinig Calculation | A | 2019-06-03 | IFR | OL1-2G23-2605 | PE | 2019-06-04 | 036909C-JVD-TRN-01805 | 036909C-JVD-TRN-01805 | IFR | 2019-06-19 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-PE-01805 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2604 | PSV-2601 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2604 | PE | 2019-06-04 | 036909C-JVD-TRN-01805 | 036909C-JVD-TRN-01805 | IFR | 2019-06-19 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-PE-01805 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2602 | PSV-2639 A-B Sizing Calculation | A | 2019-05-30 | IFR | OL1-2G23-2602 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2601 | PSV-2626 A-B Sizing Calculation | A | 2019-05-30 | IFR | OL1-2G23-2601 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1025-CN-0014-2518 | PSV-2550 A-B-C Sizing Calculation | A | 2019-05-24 | IFR | OL1-2G23-2518 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2617 | PSV-2655 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2617 | PE | 2019-06-04 | 036909C-JVD-TRN-01805 | 036909C-JVD-TRN-01805 | IFR | 2019-06-19 | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-01805 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2616 | PSV-2652 A-B Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2616 | PE | 2019-06-04 | 036909C-JVD-TRN-01805 | 036909C-JVD-TRN-01805 | IFR | 2019-06-19 | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-01805 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2613 | PSV-2638 A-B Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2613 | PE | 2019-06-04 | 036909C-JVD-TRN-01805 | 036909C-JVD-TRN-01805 | IFR | 2019-06-19 | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-01805 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2612 | PSV-2637 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2612 | PE | 2019-06-04 | 036909C-JVD-TRN-01805 | 036909C-JVD-TRN-01805 | IFR | 2019-06-19 | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-01805 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2609 | PSV-2620 A-B Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2609 | PE | 2019-06-04 | 036909C-JVD-TRN-01805 | 036909C-JVD-TRN-01805 | IFR | 2019-06-19 | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-01805 |  | 2019-06-10 | 2
036909C-1026-CN-0014-2608 | PSV-2615 Sizing Calculation | A | 2019-06-03 | IFR | OL1-2G23-2608 | PE | 2019-06-04 | 036909C-JVD-TRN-01805 | 036909C-JVD-TRN-01805 | IFR | 2019-06-19 | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-01805 |  | 2019-06-10 | 2
036909C-1025-CN-0014-2505 | PSV-2520 Sizing Calculation | A | 2019-05-28 | IFR | OL1-2G23-2505 | PE | 2019-06-04 | 036909C-JVD-TRN-01801 | 036909C-JVD-TRN-01801 | IFR | 2019-06-19 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-PE-01801 |  | 2019-06-10 | 2
036909C-1051-PDS-1390-5141 | Piping Specialty Item - Datasheet - Exhaust Head - 10-SP-51041 | A | 2019-06-03 | IFR | OL1-2P03-5141 | MP | 2019-06-05 | 036909C-JVD-TRN-01809 | 036909C-JVD-TRN-01809 | IFR | 2019-06-20 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-MP-01809 |  | 2019-06-10 | 2
036909C-1031-SP-0810-3112 | Mechanical Equipment Data Sheet - Water Washer Accumulator | A | 2019-05-10 | IFQ | OL1-2M03-3112 | ME | 2019-05-13 | 036909C-JVD-TRN-01654 | 036909C-JVD-TRN-01654 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-ME-01654 |  | 2019-05-14 | 2
036909C-1031-SP-0810-3126 | Mechanical Equipment Data Sheet - Ejector Seal Drum | A | 2019-05-10 | IFQ | OL1-2M03-3126 | ME | 2019-05-13 | 036909C-JVD-TRN-01654 | 036909C-JVD-TRN-01654 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-ME-01654 |  | 2019-05-14 | 2
036909C-1025-SP-1541-2503 | Instrument Datasheets for Control Valve - Butterfly Type- Area 25 | A | 2019-04-17 | IFQ | OL1-2I20-2502 | IE | 2019-04-24 | 036909C-JVD-TRN-01464 | 036909C-JVD-TRN-01464 | IFI |  | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-IE-01464 |  | 2019-04-25 | 3
036909C-1039-PDS-0900-3905 | Process Equipment Datasheet - 10-P-3904 A-B - BDU Product Inhibitor Dosing Pump | B | 2019-06-20 | IFR | OL1-2G30-3905 | PE | 2019-06-24 | 036909C-JVD-TRN-01978 | 036909C-JVD-TRN-01978 | IFR | 2019-07-08 |  | Transmitted | TPSK-LSPA1-T-PE-01978 |  | 2019-06-25 | 2
036909C-1039-PDS-0900-3907 | Process Equipment Datasheet - 10-P-3906 A-B - BDU Anti-Foam Dosing Pump | B | 2019-06-20 | IFR | OL1-2G30-3907 | PE | 2019-06-24 | 036909C-JVD-TRN-01978 | 036909C-JVD-TRN-01978 | IFR | 2019-07-08 |  | Transmitted | TPSK-LSPA1-T-PE-01978 |  | 2019-06-25 | 2
036909C-1025-SP-1541-2501 | Instrument Datasheets for Control Valve - Globe Type -Area 25 | A | 2019-04-17 | IFQ | OL1-2I20-2501 | IE | 2019-04-24 | 036909C-JVD-TRN-01464 | 036909C-JVD-TRN-01464 | IFI |  | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-IE-01464 |  | 2019-04-25 | 3
036909C-1051-PDS-1390-5119 | Piping Specialty Item - Datasheet - Exhaust Head - 10-SP-51019 | A | 2019-06-03 | IFR | OL1-2P03-5119 | MP | 2019-06-05 | 036909C-JVD-TRN-01809 | 036909C-JVD-TRN-01809 | IFR | 2019-06-20 | 2019-06-27 | R1-No comments | TPSK-LSPA1-T-MP-01809 |  | 2019-06-10 | 2
036909C-1000-PP-501 | NON CONFORMITY MANAGEMENT PROCEDURE | A | 2019-01-22 | IFR | OL1-2Q92-0003 | QM | 2019-01-28 | 036909C-JVD-TRN-00733 | 036909C-JVD-TRN-00733 | IFR | 2019-02-08 | 2019-03-11 | R2-Comments as noted | TPSK-LSPA1-T-QM-00733 |  | 2019-01-28 | 2
036909C-1012-DW-0117-2002 | USC 132U Cracking Furnace General Arrangement Longitudinal Elevation | 0 | 2019-04-12 | IMP | OL1-2M06-2002 | ME | 2019-04-16 | 036909C-JVD-TRN-01369 | 036909C-JVD-TRN-01369 | IFR | 2019-05-01 |  | Transmitted | TPSK-LSPA1-T-ME-01369 |  | 2019-04-17 | 2
036909C-1011-DW-0117-1002 | USC 36M Recycle Furnace General Arrangement Longitudinal Elevation | 0 | 2019-04-12 | IMP | OL1-2M06-1002 | ME | 2019-04-15 | 036909C-JVD-TRN-01361 | 036909C-JVD-TRN-01361 | IFR | 2019-04-30 |  | Transmitted | TPSK-LSPA1-T-ME-01361 |  | 2019-04-16 | 2
036909C-1027-PDS-0600-2716 | Process Equipment Datasheet - 10-E-2714 - C5 Cut Cooler | A | 2019-01-22 | IFR | OL1-2G30-2716 | PE | 2019-01-25 | 036909C-JVD-TRN-00720 | 036909C-JVD-TRN-00720 | IFR | 2019-02-07 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00720 |  | 2019-01-25 | 2
036909C-1025-SP-0510-2510 | Mechanical Equipment Data Sheet - Demethanizer Prefractionator & Reflux Drum | 0 | 2019-04-26 | IFP | OL1-2M03-2510 | ME | 2019-04-29 | 036909C-JVD-TRN-01515 | 036909C-JVD-TRN-01515 | IFR | 2019-05-14 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME -01515 |  | 2019-04-30 | 2
036909C-1012-DW-0131-2546 | USC 132U Cracking Furnace Name Plate Details | 1 | 2019-05-24 | IMP | OL1-2K32-2546 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1012-DW-0131-2522 | USC 132U Cracking Furnace Steel Match Bolting Plans For Field Splice At EL 118240 and 135270 | 0 | 2019-05-15 | IMP | OL1-2K32-2522 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1012-DW-0015-2601 | USC 132U Cracking Furnace Steel Platform Plan at TOS EL 103360 | 0 | 2019-04-30 | IFI | OL1-2K32-2601 | CV | 2019-05-06 | 036909C-JVD-TRN-01584 | 036909C-JVD-TRN-01584 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01584 |  | 2019-05-07 | 3
036909C-1012-DW-0131-2516 | USC 132U Cracking Furnace Steel Shadow Box Details | 0 | 2019-05-15 | IMP | OL1-2K32-2516 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1012-DW-0131-2515 | USC 132U Cracking Furnace Steel Transition Floor Plan And Sections | 0 | 2019-05-15 | IMP | OL1-2K32-2515 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1012-DW-0131-2513 | USC 132U Cracking Furnace Steel Radiant Side Wall At COL Line B2 And C2 | 0 | 2019-05-15 | IMP | OL1-2K32-2513 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1011-DW-0117-1581 | USC 36M Recycle Furnace Steel Breeching Sections and Details | 0 | 2019-05-24 | IMP | OL1-2K32-1581 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1011-DW-0117-1580 | USC 36M Recycle Furnace Steel Breeching Plan and Elevations | 0 | 2019-05-24 | IMP | OL1-2K32-1580 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-102A-DW-1331-0001 | GAD KEY PLAN - ZONE 2A - QUENCH | A | 2019-04-16 | IFR | OL1-2P06-0074 | MP | 2019-04-17 | 036909C-JVD-TRN-01394 | 036909C-JVD-TRN-01394, ROC-TPSK-CECO-T-00052 | IFR | 2019-05-02 | 2019-06-14 | R1-No comments | TPSK-LPSA1-T-MP-01394 |  | 2019-04-18 | 2
036909C-1021-CN-0014-2113 | PSV-2146 A-B Sizing Calculation | A | 2019-05-27 | IFR | OL1-2G23-2113 | PE | 2019-05-29 | 036909C-JVD-TRN-01763 | 036909C-JVD-TRN-01763 | IFR | 2019-06-13 | 2019-06-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-01763 |  | 2019-05-30 | 2
036909C-1021-CN-0014-2111 | PSV-2136 Sizing Calculation | A | 2019-05-27 | IFR | OL1-2G23-2111 | PE | 2019-05-29 | 036909C-JVD-TRN-01763 | 036909C-JVD-TRN-01763 | IFR | 2019-06-13 | 2019-06-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-01763 |  | 2019-05-30 | 2
036909C-101B-DW-1331-0001 | GAD KEY PLAN - ZONE 1B - FURNACES UTILITIES | A | 2019-04-16 | IFR | OL1-2P06-0073 | MP | 2019-04-17 | 036909C-JVD-TRN-01394 | 036909C-JVD-TRN-01394, ROC-TPSK-CECO-T-00052 | IFR | 2019-05-02 | 2019-06-14 | R1-No comments | TPSK-LPSA1-T-MP-01394 |  | 2019-04-18 | 2
036909C-1056-PDS-2600-5691 | Process Equipment Datasheet - 10-PK-5691 - Slop Tank Acid Injection Pkg | 0 | 2019-05-09 | CAN | OL1-2G30-5691 | PE | 2019-05-09 | 036909C-JVD-TRN-01628 | 036909C-JVD-TRN-01628 | IFR | 2019-05-24 | 2019-06-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-01628 |  | 2019-05-10 | 2
036909C-1039-PDS-0900-3908 | Process Equipment Datasheet - 10-P-3908 A-B - BDU Predistillation Inhibitor Dosing Pump | A | 2019-04-08 | IFR | OL1-2G30-3908 | PE | 2019-04-09 | 036909C-JVD-TRN-01285 | 036909C-JVD-TRN-01285 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA-1-PE-01285 |  | 2019-04-10 | 2
036909C-1039-PDS-0900-3907 | Process Equipment Datasheet - 10-P-3906 A-B - BDU Anti-Foam Dosing Pump | A | 2019-04-08 | IFR | OL1-2G30-3907 | PE | 2019-04-09 | 036909C-JVD-TRN-01285 | 036909C-JVD-TRN-01285 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA-1-PE-01285 |  | 2019-04-10 | 2
036909C-1039-PDS-0900-3905 | Process Equipment Datasheet - 10-P-3904 A-B - BDU Product Inhibitor Dosing Pump | A | 2019-04-08 | IFR | OL1-2G30-3905 | PE | 2019-04-09 | 036909C-JVD-TRN-01285 | 036909C-JVD-TRN-01285 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA-1-PE-01285 |  | 2019-04-10 | 2
036909C-1056-PDS-0200-5655 | Process Equipment Datasheet - 10-PIT-5655 - Bio Equalization Pit | A | 2019-02-05 | IFR | OL1-2G30-5655 | PE | 2019-02-06 | 036909C-JVD-TRN-00808 | 036909C-JVD-TRN-00808, ROC-TPSK-CECO-T-00020 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00808 |  | 2019-02-06 | 2
036909C-1027-SP-0510-2710 | Mechanical Equipment Data Sheet - Depentanizer | A | 2019-01-30 | IFQ | OL1-2M03-2710 | ME | 2019-02-06 | 036909C-JVD-TRN-00805 | 036909C-JVD-TRN-00805, ROC-TPSK-CECO-T-00015 | IFR | 2019-02-19 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00805 |  | 2019-02-06 | 2
036909C-1027-SP-0410-2760 | Mechanical Equipment Data Sheet - C4-C5 Hydrog Reactor | B | 2019-04-11 | IFQ | OL1-2M03-2760 | ME | 2019-04-12 | 036909C-JVD-TRN-01346 | 036909C-JVD-TRN-01346 | IFR | 2019-04-29 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME -01346 |  | 2019-04-12 | 2
036909C-1027-SP-0410-2760 | Mechanical Equipment Data Sheet - C4 -C5 Hydrog Reactor | A | 2019-01-28 | IFQ | OL1-2M03-2760 | ME | 2019-02-01 | 036909C-JVD-TRN-00795 | 036909C-JVD-TRN-00795, ROC-TPSK-CECO-T-00015 | IFR | 2019-02-15 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00795 |  | 2019-02-04 | 2
036909C-1027-SP-0410-2700 | Mechanical Equipment Data Sheet - GHU-1 Reactor | B | 2019-04-11 | IFQ | OL1-2M03-2700 | ME | 2019-04-12 | 036909C-JVD-TRN-01346 | 036909C-JVD-TRN-01346 | IFR | 2019-04-29 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME-01346 |  | 2019-04-12 | 2
036909C-1027-SP-0410-2700 | Mechanical Equipment Data Sheet - GHU-1 Reactor | A | 2019-01-28 | IFQ | OL1-2M03-2700 | ME | 2019-02-01 | 036909C-JVD-TRN-00795 | 036909C-JVD-TRN-00795, ROC-TPSK-CECO-T-00015 | IFR | 2019-02-15 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00795 |  | 2019-02-04 | 2
036909C-1026-SP-0810-2610 | Mechanical Equipment Datasheet - C3 Hydrog Arsine Guard Bed | B | 2019-01-14 | IFQ | OL1-2M03-2610 | ME | 2019-01-16 | 036909C-JVD-TRN-00658 | 036909C-JVD-TRN-00658 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00658 |  | 2019-01-16 | 2
036909C-1026-SP-0810-2610 | Mechanical Equipment Datasheet - C3 Hydrog Arsine Guard Bed | D | 2019-04-15 | IFQ | OL1-2M03-2610 | ME | 2019-04-16 | 036909C-JVD-TRN-01381 | 036909C-JVD-TRN-01381 | IFR | 2019-05-01 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-ME-01381 |  | 2019-04-17 | 2
036909C-1026-SP-0810-2610 | Mechanical Equipment Datasheet - C3 Hydrog Arsine Guard Bed | C | 2019-02-26 | IFQ | OL1-2M03-2610 | ME | 2019-02-28 | 036909C-JVD-TRN-00950 | 036909C-JVD-TRN-00950, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-15 | 2019-04-01 | R1-No comments | TPSK-LSPA1-T-ME-00950 |  | 2019-03-01 | 2
036909C-1026-SP-0810-2600 | Mechanical Equipment Data Sheet - C3 Hydrog Guard Adsorber | A | 2019-01-16 | IFQ | OL1-2M03-2600 | ME | 2019-01-17 | 036909C-JVD-TRN-00672 | 036909C-JVD-TRN-00672 | IFR | 2019-01-30 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00672 |  | 2019-01-17 | 2
036909C-1026-SP-0810-2600 | Mechanical Equipment Data Sheet - C3 Hydrog Guard Adsorber | B | 2019-01-21 | IFQ | OL1-2M03-2600 | ME | 2019-01-22 | 036909C-JVD-TRN-00701 | 036909C-JVD-TRN-00701 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME -00701 |  | 2019-01-22 | 2
036909C-1026-SP-0810-2600 | Mechanical Equipment Data Sheet - C3 Hydrog Guard Adsorber | D | 2019-04-15 | IFQ | OL1-2M03-2600 | ME | 2019-04-16 | 036909C-JVD-TRN-01381 | 036909C-JVD-TRN-01381 | IFR | 2019-05-01 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-ME -01381 |  | 2019-04-17 | 2
036909C-1026-SP-0810-2600 | Mechanical Equipment Data Sheet - C3 Hydrog Guard Adsorber | C | 2019-02-26 | IFQ | OL1-2M03-2600 | ME | 2019-02-28 | 036909C-JVD-TRN-00954 | 036909C-JVD-TRN-00954, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-15 | 2019-03-25 | R1-No comments | TPSK-LSPA1-T-ME-00954 |  | 2019-03-01 | 2
036909C-1026-SP-0410-2620 | Mechanical Equipment Data Sheet - C3 Hydrog Reactor | C | 2019-04-12 | IFQ | OL1-2M03-2620 | ME | 2019-04-12 | 036909C-JVD-TRN-01346 | 036909C-JVD-TRN-01346 | IFR | 2019-04-29 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME-01346 |  | 2019-04-12 | 2
036909C-1026-SP-0410-2620 | Mechanical Equipment Data Sheet - C3 Hydrog Reactor | B | 2019-03-04 | IFQ | OL1-2M03-2620 | ME | 2019-03-05 | 036909C-JVD-TRN-00990 | 036909C-JVD-TRN-00990, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-20 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-00990 |  | 2019-03-06 | 2
036909C-1026-SP-0410-2620 | Mechanical Equipment Data Sheet - C3 Hydrog Reactor | A | 2019-01-28 | IFQ | OL1-2M03-2620 | ME | 2019-02-06 | 036909C-JVD-TRN-00802 | 036909C-JVD-TRN-00802 | IFR | 2019-02-19 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00802 |  | 2019-02-06 | 2
036909C-1024-SP-0810-2480 | Mechanical Equipment Data Sheet - CG Secondary Dryer | C | 2019-04-15 | IFQ | OL1-2M03-2480 | ME | 2019-04-16 | 036909C-JVD-TRN-01378 | 036909C-JVD-TRN-01378 | IFR | 2019-05-01 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-01378 |  | 2019-04-17 | 2
036909C-1024-SP-0810-2480 | Mechanical Equipment Data Sheet - CG Secondary Dryer | B | 2019-02-26 | IFQ | OL1-2M03-2480 | ME | 2019-02-28 | 036909C-JVD-TRN-00954 | 036909C-JVD-TRN-00954, ROC-TPSK-CECO-T-00014 | IFR | 2019-03-15 | 2019-03-25 | R1-No comments | TPSK-LSPA1-T-ME-00954 |  | 2019-03-01 | 2
036909C-1024-SP-0810-2480 | Mechanical Equipment Data Sheet - CG Secondary Dryer | A | 2019-01-21 | IFQ | OL1-2M03-2480 | ME | 2019-01-22 | 036909C-JVD-TRN-00702 | 036909C-JVD-TRN-00702 | IFR | 2019-02-04 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00702 |  | 2019-01-22 | 2
036909C-1024-SP-0810-2460 | Mechanical Equipment Data Sheet - C2 Hydrog Arsine Guard Bed | C | 2019-04-15 | IFQ | OL1-2M03-2460 | ME | 2019-04-16 | 036909C-JVD-TRN-01378 | 036909C-JVD-TRN-01378 | IFR | 2019-05-01 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-01378 |  | 2019-04-17 | 2
036909C-1024-SP-0810-2460 | Mechanical Equipment Data Sheet - C2 Hydrog Arsine Guard Bed | A | 2019-01-08 | IFQ | OL1-2M03-2460 | ME | 2019-01-16 | 036909C-JVD-TRN-00657 | 036909C-JVD-TRN-00657 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00657 |  | 2019-01-16 | 2
036909C-1024-SP-0810-2460 | Mechanical Equipment Data Sheet - C2 Hydrog Arsine Guard Bed | B | 2019-02-13 | IFQ | OL1-2M03-2460 | ME | 2019-02-15 | 036909C-JVD-TRN-00858 | 036909C-JVD-TRN-00858, ROC-TPSK-CECO-T-00014 | IFR | 2019-03-01 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME -00858 |  | 2019-02-15 | 2
036909C-1024-SP-0810-2438 | Mechanical Equipment Data Sheet - HP Depropanizer Reflux Drum | A | 2018-12-04 | IFQ | OL1-2M03-2438 | ME | 2018-12-13 | 036909C-JVD-TRN-00484 | 036909C-JVD-TRN-00484, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-ME-00484 |  | 2018-12-13 | 2
036909C-1024-SP-0810-2438 | Mechanical Equipment Data Sheet - HP Depropanizer Reflux Drum | B | 2019-03-22 | IFQ | OL1-2M03-2438 | ME | 2019-04-16 | 036909C-JVD-TRN-01378 | 036909C-JVD-TRN-01378 | IFR | 2019-05-01 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-01378 |  | 2019-04-17 | 2
036909C-1024-SP-0810-2420 | Mechanical Equipment Data Sheet - CG Liquid Dryer | C | 2019-04-15 | IFQ | OL1-2M03-2420 | ME | 2019-04-16 | 036909C-JVD-TRN-01378 | 036909C-JVD-TRN-01378 | IFR | 2019-05-01 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-01378 |  | 2019-04-17 | 2
036909C-1024-SP-0810-2420 | Mechanical Equipment Data Sheet - CG Liquid Dryer | B | 2019-02-26 | IFQ | OL1-2M03-2420 | ME | 2019-02-28 | 036909C-JVD-TRN-00950 | 036909C-JVD-TRN-00950, ROC-TPSK-CECO-T-00014 | IFR | 2019-03-15 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-00950 |  | 2019-03-01 | 2
036909C-1024-SP-0810-2420 | Mechanical Equipment Data Sheet - CG Liquid Dryer | A | 2019-01-21 | IFQ | OL1-2M03-2420 | ME | 2019-01-22 | 036909C-JVD-TRN-00702 | 036909C-JVD-TRN-00702 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00702 |  | 2019-01-22 | 2
036909C-1024-SP-0810-2411 | Mechanical Equipment Data Sheet - Cracked Gas Mercury Adsorber | A | 2019-01-10 | IFQ | OL1-2M03-2411 | ME | 2019-01-11 | 036909C-JVD-TRN-00631 | 036909C-JVD-TRN-00631 | IFR | 2019-01-24 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00631 |  | 2019-01-11 | 2
036909C-1024-SP-0810-2411 | Mechanical Equipment Data Sheet - Cracked Gas Mercury Adsorber | C | 2019-04-15 | IFQ | OL1-2M03-2411 | ME | 2019-04-16 | 036909C-JVD-TRN-01378 | 036909C-JVD-TRN-01378 | IFR | 2019-05-01 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-01378 |  | 2019-04-17 | 2
036909C-1024-SP-0810-2411 | Mechanical Equipment Data Sheet - Cracked Gas Mercury Adsorber | B | 2019-02-26 | IFQ | OL1-2M03-2411 | ME | 2019-02-28 | 036909C-JVD-TRN-00954 | 036909C-JVD-TRN-00954, ROC-TPSK-CECO-T-00014 | IFR | 2019-03-15 | 2019-03-25 | R2-Comments as noted | TPSK-LSPA1-T-ME-00954 |  | 2019-03-01 | 2
036909C-1024-SP-0810-2410 | Mechanical Equipment Data Sheet - Cracked Gas Dryer | D | 2019-04-11 | IFQ | OL1-2M03-2410 | ME | 2019-04-12 | 036909C-JVD-TRN-01347 | 036909C-JVD-TRN-01347 | IFR | 2019-04-29 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-01347 |  | 2019-04-15 | 2
036909C-1024-SP-0810-2410 | Mechanical Equipment Data Sheet - Cracked Gas Dryer | A | 2019-01-21 | IFQ | OL1-2M03-2410 | ME | 2019-01-22 | 036909C-JVD-TRN-00700 | 036909C-JVD-TRN-00700 | IFR | 2019-02-04 | 2019-04-01 | R2-Comments as noted | TPSK-LSPA1-T-ME-00700 |  | 2019-01-22 | 2
036909C-1024-SP-0810-2410 | Mechanical Equipment Data Sheet - Cracked Gas Dryer | B | 2019-02-26 | IFQ | OL1-2M03-2410 | ME | 2019-03-01 | 036909C-JVD-TRN-00972 | 036909C-JVD-TRN-00972 | IFR | 2019-03-16 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-00972 |  | 2019-03-04 | 2
036909C-1024-SP-0810-2410 | Mechanical Equipment Data Sheet - Cracked Gas Dryer | C | 2019-03-07 | IFQ | OL1-2M03-2410 | ME | 2019-03-11 | 036909C-JVD-TRN-01016 | 036909C-JVD-TRN-01016, ROC-TPSK-CECO-T-00014 | IFR | 2019-03-26 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-ME-01016 |  | 2019-03-12 | 2
036909C-1024-SP-0410-2470 | Mechanical Equipment Data Sheet - C2 Hydrog Reactor | C | 2019-04-15 | IFQ | OL1-2M03-2470 | ME | 2019-04-16 | 036909C-JVD-TRN-01379 | 036909C-JVD-TRN-01379 | IFR | 2019-05-01 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-ME-01379 |  | 2019-04-17 | 2
036909C-1024-SP-0410-2470 | Mechanical Equipment Data Sheet - C2 Hydrog Reactor | A | 2019-01-10 | IFQ | OL1-2M03-2470 | ME | 2019-01-11 | 036909C-JVD-TRN-00630 | 036909C-JVD-TRN-00630 | IFR | 2019-01-24 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00630 |  | 2019-01-11 | 2
036909C-1011-NM-0022-1101 | Line Designation Table – Recycle Gas Cracking Furnace 10-H-1100 | A | 2019-02-15 | IBD | OL1-2P91-1101 | PE | 2019-02-26 | 036909C-JVD-TRN-00933 | 036909C-JVD-TRN-00933, ROC-TPSK-CECO-T-00012 | IFR | 2019-03-12 | 2019-05-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00933 |  | 2019-02-27 | 2
036909C-1012-NM-0022-1201 | Line Designation Table - Liquid Cracking Furnace 10-H-1200 | A | 2019-02-26 | IBD | OL1-2P91-1201 | PE | 2019-02-26 | 036909C-JVD-TRN-00934 | 036909C-JVD-TRN-00934, ROC-TPSK-CECO-T-00012 | IFR | 2019-03-12 | 2019-05-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00934 |  | 2019-02-27 | 2
036909C-1026-SP-0510-2660 | Mechanical Equipment Data Sheet - Debutanizer | 0 | 2019-05-21 | IFP | OL1-2M03-2660 | ME | 2019-05-22 | 036909C-JVD-TRN-01721 | 036909C-JVD-TRN-01721 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01721 |  | 2019-05-23 | 2
036909C-1026-SP-0510-2630 | Mechanical Equipment Data Sheet - Secondary Deethanizer | 0 | 2019-05-21 | IFP | OL1-2M03-2630 | ME | 2019-05-22 | 036909C-JVD-TRN-01721 | 036909C-JVD-TRN-01721 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01721 |  | 2019-05-23 | 2
036909C-1020-SP-0510-2020 | Mechanical Equipment Data Sheet - Light Fuel Oil Stripper | 0 | 2019-05-20 | IFP | OL1-2M03-2020 | ME | 2019-05-22 | 036909C-JVD-TRN-01721 | 036909C-JVD-TRN-01721 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01721 |  | 2019-05-23 | 2
036909C-1055-SP-0810-5555 | Mechanical Equipment Data Sheet - LPG Vaporizer-Superhtr Cond Pot | C | 2019-05-30 | IFQ | OL1-2M03-5555 | ME | 2019-05-30 | 036909C-JVD-TRN-01783 | 036909C-JVD-TRN-01783 | IFR | 2019-06-14 | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-ME-01783 |  | 2019-05-31 | 2
036909C-1052-SP-0810-5202 | Mechanical Equipment Data Sheet - MP Ethylene Superhtr Cond Pot | B | 2019-05-29 | IFQ | OL1-2M03-5202 | ME | 2019-05-30 | 036909C-JVD-TRN-01780 | 036909C-JVD-TRN-01780 | IFR | 2019-06-14 | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-ME-01780 |  | 2019-05-31 | 2
036909C-1011-DW-0131-1546 | USC 36M Recycle Furnace Steel Name Plate Details | 0 | 2019-05-24 | IMP | OL1-2K32-1546 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1011-DW-0131-1522 | USC 36M Recycle Furnace Steel Match Bolting Plans for Field Splice at El 115022 and 132470 | 0 | 2019-05-15 | IMP | OL1-2K32-1522 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1011-DW-0131-1516 | USC 36M Recycle Furnace Steel Shadow Box Details | 0 | 2019-05-15 | IMP | OL1-2K32-1516 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1011-DW-0131-1515 | USC 36M Recycle Furnace Steel Transition Floor Plan and Sections | 0 | 2019-05-15 | IMP | OL1-2K32-1515 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1011-DW-0131-1513 | USC 36M Recycle Furnace Steel Radiant Side Wall at Col Line B1 and C1 | 0 | 2019-05-15 | IMP | OL1-2K32-1513 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1029-CN-0014-2927 | PSV-2988 Sizing Calculation | A | 2019-05-25 | IFR | OL1-2G23-2927 | PE | 2019-05-28 | 036909C-JVD-TRN-01759 | 036909C-JVD-TRN-01759 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01759 |  | 2019-05-29 | 2
036909C-1029-CN-0014-2922 | PSV-2976 Sizing Calculation | A | 2019-05-22 | IFR | OL1-2G23-2922 | PE | 2019-05-28 | 036909C-JVD-TRN-01759 | 036909C-JVD-TRN-01759 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01759 |  | 2019-05-29 | 2
036909C-1029-CN-0014-2921 | PSV-2974 Sizing Calculation | A | 2019-05-24 | IFR | OL1-2G23-2921 | PE | 2019-05-28 | 036909C-JVD-TRN-01759 | 036909C-JVD-TRN-01759 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01759 |  | 2019-05-29 | 2
036909C-1029-CN-0014-2916 | PSV-2962 Sizing Calculation | A | 2019-05-24 | IFR | OL1-2G23-2916 | PE | 2019-05-28 | 036909C-JVD-TRN-01759 | 036909C-JVD-TRN-01759 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01759 |  | 2019-05-29 | 2
036909C-1029-CN-0014-2911 | PSV-2951 Sizing Calculation | A | 2019-05-22 | IFR | OL1-2G23-2911 | PE | 2019-05-28 | 036909C-JVD-TRN-01759 | 036909C-JVD-TRN-01759 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01759 |  | 2019-05-29 | 2
036909C-1029-CN-0014-2910 | PSV-2938 Sizing Calculation | A | 2019-05-24 | IFR | OL1-2G23-2910 | PE | 2019-05-28 | 036909C-JVD-TRN-01759 | 036909C-JVD-TRN-01759 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01759 |  | 2019-05-29 | 2
036909C-1029-CN-0014-2909 | PSV-2936 Sizing Calculation | A | 2019-05-24 | IFR | OL1-2G23-2909 | PE | 2019-05-28 | 036909C-JVD-TRN-01759 | 036909C-JVD-TRN-01759 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01759 |  | 2019-05-29 | 2
036909C-1029-CN-0014-2908 | PSV-2934 Sizing Calculation | A | 2019-05-24 | IFR | OL1-2G23-2908 | PE | 2019-05-28 | 036909C-JVD-TRN-01759 | 036909C-JVD-TRN-01759 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01759 |  | 2019-05-29 | 2
036909C-1026-CN-0014-2603 | PSV-2633 A-B-C-D-E Sizing Calculation | A | 2019-05-27 | IFR | OL1-2G23-2603 | PE | 2019-05-28 | 036909C-JVD-TRN-01759 | 036909C-JVD-TRN-01759 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01759 |  | 2019-05-29 | 2
036909C-1025-CN-0014-2523 | PSV-2565 Sizing Calculation | A | 2019-05-24 | IFR | OL1-2G23-2523 | PE | 2019-05-28 | 036909C-JVD-TRN-01759 | 036909C-JVD-TRN-01759 | IFR | 2019-06-12 | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-PE-01759 |  | 2019-05-29 | 2
036909C-1023-CN-0014-2302 | PSV-2310 Sizing Calculation | A | 2019-05-01 | IFR | OL1-2G23-2302 | PE | 2019-05-28 | 036909C-JVD-TRN-01759 | 036909C-JVD-TRN-01759 | IFR | 2019-06-12 | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-PE-01759 |  | 2019-05-29 | 2
036909C-1039-NM-0022-3901 | Line Designation Table - C4 Unit Auxiliaries | A | 2019-06-03 | IBD | OL1-2P91-3901 | MP | 2019-06-03 | 036909C-JVD-TRN-01795 | 036909C-JVD-TRN-01795 | IFR | 2019-06-18 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-MP-01795 |  | 2019-06-10 | 2
036909C-1031-NM-0022-3101 | Line Designation Table - Butadiene Extraction Unit Utilities | A | 2019-06-03 | IBD | OL1-2P91-3101 | MP | 2019-06-03 | 036909C-JVD-TRN-01795 | 036909C-JVD-TRN-01795 | IFR | 2019-06-18 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-MP-01795 |  | 2019-06-10 | 2
036909C-1030-NM-0022-3001 | Line Designation Table - Butadiene Extraction Unit | A | 2019-06-03 | IBD | OL1-2P91-3001 | MP | 2019-06-03 | 036909C-JVD-TRN-01795 | 036909C-JVD-TRN-01795 | IFR | 2019-06-18 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-MP-01795 |  | 2019-06-10 | 2
036909C-1023-PDS-1546-2390 | Process Datasheet for Restriction Orifice - Unit 23 | A | 2019-06-17 | IFR | OL1-2G23-2390 | PE | 2019-06-19 | 036909C-JVD-TRN-01929 | 036909C-JVD-TRN-01929 | IFR | 2019-07-04 |  | Transmitted | TPSK-LSPA1-T-PE-01929 |  | 2019-06-20 | 2
036909C-1039-PDS-0900-3903 | Process Equipment Datasheet - 10-P-3902 A-B - BDU Solvent Inhibitor Dosing Pump | A | 2019-04-09 | IFR | OL1-2G30-3903 | PE | 2019-04-09 | 036909C-JVD-TRN-01285 | 036909C-JVD-TRN-01285 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA-1-PE-01285 |  | 2019-04-10 | 2
036909C-1039-PDS-0900-3901 | Process Equipment Datasheet - 10-P-3900 - NMP Storage Pump | A | 2019-04-08 | IFR | OL1-2G30-3901 | PE | 2019-04-09 | 036909C-JVD-TRN-01285 | 036909C-JVD-TRN-01285 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA-1-PE-01285 |  | 2019-04-10 | 2
036909C-1030-PDS-0900-3066 | Process Equipment Data Sheet - 10-P-3060 A-B Wastewater Pump | A | 2019-04-04 | IFR | OL1-2G30-3066 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1030-PDS-0900-3056 | Process Equipment Data Sheet - 10-P-3056 A-B Degasser Bottom Pump | A | 2019-04-04 | IFR | OL1-2G30-3056 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1030-PDS-0900-3046 | Process Equipment Data Sheet - 10-P-3046 A-B Degasser Feed Pump | A | 2019-04-04 | IFR | OL1-2G30-3046 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1030-PDS-0900-3026 | Process Equipment Data Sheet - 10-P-3026 A-B Main Washer Bottom Pump | A | 2019-04-04 | IFR | OL1-2G30-3026 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1030-PDS-0900-3023 | Process Equipment Data Sheet - 10-P-3020 A-B Main Washer Reflux -C4 Raffinate-I-Pump | A | 2019-04-04 | IFR | OL1-2G30-3023 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1031-PDS-0900-3162 | Process Equipment Data Sheet - 10-P-3160 BDU Condensate Recycle Pump | A | 2019-04-04 | IFR | OL1-2G30-3162 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1031-PDS-0900-3127 | Process Equipment Data Sheet - 10-P-3126 A-B BDU Ejector Seal Drum Pump | A | 2019-04-04 | IFR | OL1-2G30-3127 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1031-PDS-0900-3113 | Process Equipment Data Sheet - 10-P-3110 A-B Solvent Return Pump | A | 2019-04-04 | IFR | OL1-2G30-3113 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1030-PDS-0900-3097 | Process Equipment Data Sheet - 10-P-3096 A-B Butadiene Product Pumps | A | 2019-04-04 | IFR | OL1-2G30-3097 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1030-PDS-0900-3086 | Process Equipment Data Sheet - 10-P-3086 A-B Butadiene Tower Bottom Pump | A | 2019-04-04 | IFR | OL1-2G30-3086 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1030-PDS-0900-3083 | Process Equipment Data Sheet - 10-P-3080 A-B Butadiene Tower Reflux Pumps | A | 2019-04-04 | IFR | OL1-2G30-3083 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1030-PDS-0900-3076 | Process Equipment Data Sheet - 10-P-3076 A-B - Direct Cooler Pump | A | 2019-04-04 | IFR | OL1-2G30-3076 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1031-PDS-0900-3191 | Process Equipment Data Sheet - 10-P-3190 Solvent Slop Pump | A | 2019-04-04 | IFR | OL1-2G30-3191 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1030-PDS-0900-3067 | Process Equipment Data Sheet - 10-P-3062 A-B - C4 Acetylene Pump | A | 2019-04-04 | IFR | OL1-2G30-3067 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1030-PDS-0900-3061 | Process Equipment Data Sheet - 10-P-3061 A-B - Dimer Pump | A | 2019-04-04 | IFR | OL1-2G30-3061 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1052-CN-0014-5202 | PSV-5204 A-D Sizing Calculation | A | 2019-06-17 | IFR | OL1-2G23-5202 | PE | 2019-06-18 | 036909C-JVD-TRN-01921 | 036909C-JVD-TRN-01921 | IFR | 2019-07-03 |  | Transmitted | TPSK-LSPA1-T-PE-01921 |  | 2019-06-19 | 2
036909C-1051-CN-0014-5105 | PSV-5143 A-H Sizing Calculation | B | 2019-06-18 | IFR | OL1-2G23-5105 | PE | 2019-06-18 | 036909C-JVD-TRN-01921 | 036909C-JVD-TRN-01921 | IFR | 2019-07-03 |  | Transmitted | TPSK-LSPA1-T-PE-01921 |  | 2019-06-19 | 2
036909C-1051-CN-0014-5107 | PSV-5153 A-D Sizing Calculation | B | 2019-06-17 | IFR | OL1-2G23-5107 | PE | 2019-06-18 | 036909C-JVD-TRN-01921 | 036909C-JVD-TRN-01921 | IFR | 2019-07-03 |  | Transmitted | TPSK-LSPA1-T-PE-01921 |  | 2019-06-19 | 2
036909C-1051-CN-0014-5106 | PSV-5150 A-D Sizing Calculation | B | 2019-06-15 | IFR | OL1-2G23-5106 | PE | 2019-06-18 | 036909C-JVD-TRN-01921 | 036909C-JVD-TRN-01921 | IFR | 2019-07-03 |  | Transmitted | TPSK-LSPA1-T-PE-01921 |  | 2019-06-19 | 2
036909C-1026-PDS-1390-2606 | Piping Specialty Item - Datasheet - T-Type Filter - P-2660 A-B Suction - 10-SP-26006 | A | 2019-06-13 | IFR | OL1-2P03-2606 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1026-PDS-1390-2608 | Piping Specialty Item - Datasheet - T-Type Filter - P-2647 Suction - 10-SP-26008 | A | 2019-06-13 | IFR | OL1-2P03-2608 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1026-PDS-1390-2607 | Piping Specialty Item - Datasheet - T-Type Filter - P-2646 A-B Suction - 10-SP-26007 | A | 2019-06-13 | IFR | OL1-2P03-2607 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1026-PDS-1390-2603 | Piping Specialty Item - Datasheet - T-Type Filter - P-2666 A-B Suction - 10-SP-26003 | A | 2019-06-13 | IFR | OL1-2P03-2603 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1026-PDS-1390-2602 | Piping Specialty Item - Datasheet - T-Type Filter - P-2630 A-B Suction - 10-SP-26002 | A | 2019-06-13 | IFR | OL1-2P03-2602 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1025-PDS-1390-2532 | Piping Specialty Item - Datasheet - Basket-Type Filter - C3R To E-2500 - 10-SP-25032 | B | 2019-06-13 | IFR | OL1-2P03-2532 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1025-PDS-1390-2522 | Piping Specialty Item - Datasheet - T-Type Filter - TX-2550 Residue Gas Expander Suction - 10-SP-25022 | A | 2019-06-12 | IFR | OL1-2P03-2522 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1025-PDS-1390-2536 | Piping Specialty Item - Datasheet - T-Type Filter - P-2570 A-B Suction - 10-SP-25036 | A | 2019-06-12 | IFR | OL1-2P03-2536 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1025-PDS-1390-2544 | Piping Specialty Item - Datasheet - T-Type Filter - P-2575 A-b Suction - 10-SP-25044 | A | 2019-06-13 | IFR | OL1-2P03-2544 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1025-PDS-1390-2538 | Piping Specialty Item - Datasheet - T-Type Filter - P-2586 A-B Suction - 10-SP-25038 | A | 2019-06-12 | IFR | OL1-2P03-2538 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1026-PDS-1390-2601 | Piping Specialty Item - Datasheet - T-Type Filter - 2-2620 A-B Suction - 10-SP-26001 | A | 2019-06-13 | IFR | OL1-2P03-2601 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1020-PDS-1390-2001 | Piping Specialty Item - Datasheet - Basket-Type Filter - Quench Oil Pump Suction - 10-SP-20001 | A | 2019-06-12 | IFR | OL1-2P03-2001 | MP | 2019-06-17 | 036909C-JVD-TRN-01913 | 036909C-JVD-TRN-01913 | IFR | 2019-07-02 |  | Transmitted | TPSK-LSPA1-T-MP-01913 |  | 2019-06-18 | 2
036909C-1020-PDS-1390-2004 | Piping Specialty Item - Basket-Type Filter - Heavy Fuel Oil Pump Suction - 10-SP-20004 | A | 2019-06-12 | IFR | OL1-2P03-2004 | MP | 2019-06-17 | 036909C-JVD-TRN-01913 | 036909C-JVD-TRN-01913 | IFR | 2019-07-02 |  | Transmitted | TPSK-LSPA1-T-MP-01913 |  | 2019-06-18 | 2
036909C-1024-PDS-0800-2420 | Process Equipment Datasheet - 10-D-2420 A-B - CG Liquid Dryer | C | 2019-03-16 | IFD | OL1-2G30-2420 | PE | 2019-03-18 | 036909C-JVD-TRN-01089 | 036909C-JVD-TRN-01089 | IFR | 2019-04-02 | 2019-04-02 | CLIENT-COMMENT-TRN-01310- June 18 2019 - R2-Comments as noted | TPSK-LSPA1-T-PE-01089 |  | 2019-03-19 | 2
036909C-1026-PDS-0600-2621 | Process Equipment Datasheet - 10-E-2620 - C3 Hydrog Aftercooler | C | 2019-05-06 | IFD | OL1-2G30-2621 | PE | 2019-05-07 | 036909C-JVD-TRN-01609 | 036909C-JVD-TRN-01609 | IFR | 2019-05-22 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-PE-01609 |  | 2019-05-08 | 2
036909C-1021-SP-0840-2136 | Mechanical Equipment Data Sheet 10-D-2136 Process Water Feed Coalescer | 0 | 2019-05-15 | IFP | OL1-2M03-7002 | ME | 2019-05-16 | 036909C-JVD-TRN-01682 | 036909C-JVD-TRN-01682 | IFR | 2019-05-31 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-ME-01682 |  | 2019-05-17 | 2
036909C-1027-SP-0840-2767 | Mechanical Equipment Data Sheet 10-D-765 C4-C5 Hydrog Coalescer Drum | 0 | 2019-05-15 | IFP | OL1-2M03-7001 | ME | 2019-05-16 | 036909C-JVD-TRN-01682 | 036909C-JVD-TRN-01682 | IFR | 2019-05-31 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-ME-01682 |  | 2019-05-17 | 2
036909C-1024-SP-0840-2415 | Mechanical Equipment Data Sheet 10-d-D-2415 CG Liquid Dryer Feed Coalescer | 0 | 2019-05-15 | IFP | OL1-2M03-7000 | ME | 2019-05-16 | 036909C-JVD-TRN-01682 | 036909C-JVD-TRN-01682 | IFR | 2019-05-31 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-ME-01682 |  | 2019-05-17 | 2
036909C-1026-SP-0840-2664 | Mechanical Equipment Datasheet - C5-Pygas Feed Filters | 0 | 2019-05-13 | IFP | OL1-2M03-2664 | ME | 2019-05-15 | 036909C-JVD-TRN-01669 | 036909C-JVD-TRN-01669 | IFR | 2019-05-30 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-ME-01669 |  | 2019-05-16 | 2
036909C-1023-SP-0840-2319 | Mechanical Equipment Datasheet - Spent Caustic Pump Discharge Filters | 0 | 2019-05-13 | IFP | OL1-2M03-2319 | ME | 2019-05-15 | 036909C-JVD-TRN-01669 | 036909C-JVD-TRN-01669 | IFR | 2019-05-30 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-01669 |  | 2019-05-16 | 2
036909C-1023-SP-0840-2314 | Mechanical Equipment Datasheet - Wash Oil Circulation Filter | 0 | 2019-05-13 | IFP | OL1-2M03-2314 | ME | 2019-05-15 | 036909C-JVD-TRN-01669 | 036909C-JVD-TRN-01669 | IFR | 2019-05-30 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-ME-01669 |  | 2019-05-16 | 2
036909C-1023-SP-0840-2307 | Mechanical Equipment Datasheet - Weak Caustic Circulating Filters | 0 | 2019-05-13 | IFP | OL1-2M03-2307 | ME | 2019-05-15 | 036909C-JVD-TRN-01669 | 036909C-JVD-TRN-01669 | IFR | 2019-05-30 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-ME-01669 |  | 2019-05-16 | 2
036909C-1021-SP-0840-2138 | Mechanical Equipment Datasheet - Process Water Feed Filters | 0 | 2019-05-13 | IFP | OL1-2M03-2138 | ME | 2019-05-15 | 036909C-JVD-TRN-01669 | 036909C-JVD-TRN-01669 | IFR | 2019-05-30 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-ME-01669 |  | 2019-05-16 | 2
036909C-1059-SP-0940-5955 | Mechanical Equipment Datasheet - CTU NaOCl Metering Pumps | B | 2019-04-17 | IFQ | OL1-2M03-5955 | ME | 2019-04-17 | 036909C-JVD-TRN-01390 | 036909C-JVD-TRN-01390 | IFR | 2019-05-02 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01390 |  | 2019-04-18 | 2
036909C-1059-SP-0940-5951 | Mechanical Equipment Datasheet - Olefins NaOCl Metering Pumps | C | 2019-04-17 | IFQ | OL1-2M03-5951 | ME | 2019-04-17 | 036909C-JVD-TRN-01390 | 036909C-JVD-TRN-01390 | IFR | 2019-05-02 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01390 |  | 2019-04-18 | 2
036909C-1059-SP-0940-5905 | Mechanical Equipment Datasheet - CTU Sulfuric Acid Metering Pumps | B | 2019-04-16 | IFQ | OL1-2M03-5905 | ME | 2019-04-17 | 036909C-JVD-TRN-01390 | 036909C-JVD-TRN-01390 | IFR | 2019-05-02 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01390 |  | 2019-04-18 | 2
036909C-1059-SP-0940-5902 | Mechanical Equipment Datasheet - Olefins Sulfuric Acid Metering Pumps | C | 2019-04-17 | IFQ | OL1-2M03-5902 | ME | 2019-04-17 | 036909C-JVD-TRN-01390 | 036909C-JVD-TRN-01390 | IFR | 2019-05-02 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01390 |  | 2019-04-18 | 2
036909C-1026-SP-0510-2640 | Mechanical Equipment Data Sheet - C3 Tower | 0 | 2019-04-26 | IFP | OL1-2M03-2640 | ME | 2019-04-29 | 036909C-JVD-TRN-01515 | 036909C-JVD-TRN-01515 | IFR | 2019-05-14 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME -01515 |  | 2019-04-30 | 2
036909C-1024-SP-0510-2450 | Mechanical Equipment Data Sheet - LP Depropanizer | 0 | 2019-04-25 | IFP | OL1-2M03-2450 | ME | 2019-04-26 | 036909C-JVD-TRN-01498 | 036909C-JVD-TRN-01498 | IFR | 2019-05-13 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME -01498 |  | 2019-04-29 | 2
036909C-1020-SP-0910-2046 | Mechanical Equipment Datasheet - Heavy Fuel Oil Pumps | C | 2019-04-25 | IFQ | OL1-2M03-2046 | ME | 2019-04-26 | 036909C-JVD-TRN-01493 | 036909C-JVD-TRN-01493 | IFR | 2019-05-13 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01493 |  | 2019-04-29 | 2
036909C-1020-SP-0510-2040 | Mechanical Equipment Data Sheet - Heavy Fuel Oil Stripper | 0 | 2019-04-24 | IFP | OL1-2M03-2040 | ME | 2019-04-24 | 036909C-JVD-TRN-01472 | 036909C-JVD-TRN-01472 | IFR | 2019-05-09 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01472 |  | 2019-04-25 | 2
036909C-1056-SP-0910-5649 | Mechanical Equipment Datasheet - Flare KO Drum Oily Wastewater Pump | 0 | 2019-05-10 | CAN | OL1-2M03-5649 | ME | 2019-05-13 | 036909C-JVD-TRN-01655 | 036909C-JVD-TRN-01655 | IFR | 2019-05-28 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01655 |  | 2019-05-14 | 2
036909C-1056-SP-0910-5614 | Mechanical Equipment Datasheet - Furnace Area Oily Wastewater Pump | 0 | 2019-05-10 | CAN | OL1-2M03-5614 | ME | 2019-05-13 | 036909C-JVD-TRN-01655 | 036909C-JVD-TRN-01655 | IFR | 2019-05-28 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01655 |  | 2019-05-14 | 2
036909C-1053-SP-0910-5371 | Mechanical Equipment Datasheet - CW Filter Backwash Pumps | C | 2019-04-18 | IFQ | OL1-2M03-5371 | ME | 2019-04-22 | 036909C-JVD-TRN-01426 | 036909C-JVD-TRN-01426 | IFR | 2019-05-07 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01426 |  | 2019-04-23 | 2
036909C-1030-SP-0910-3047 | Mechanical Equipment Datasheet - Rectifier Pumps | A | 2019-04-16 | IFQ | OL1-2M03-3047 | ME | 2019-04-17 | 036909C-JVD-TRN-01398 | 036909C-JVD-TRN-01398 | IFR | 2019-05-02 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01398 |  | 2019-04-18 | 2
036909C-1030-SP-0910-3016 | Mechanical Equipment Datasheet - Heavy Ends Discharge Pumps | A | 2019-04-09 | IFQ | OL1-2M03-3016 | ME | 2019-04-23 | 036909C-JVD-TRN-01451 | 036909C-JVD-TRN-01451 | IFR | 2019-05-08 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01451 |  | 2019-04-24 | 2
036909C-1027-SP-0910-2751 | Mechanical Equipment Datasheet for C4-C5 Hydrog Feed Pump | C | 2019-05-09 | IFQ | OL1-2M03-2751 | ME | 2019-05-09 | 036909C-JVD-TRN-01626 | 036909C-JVD-TRN-01626 | IFR | 2019-05-24 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01626 |  | 2019-05-10 | 2
036909C-1027-SP-0940-2729 | Mechanical Equipment Datasheet - Wash Oil Pumps | C | 2019-04-26 | IFQ | OL1-2M03-2729 | ME | 2019-04-30 | 036909C-JVD-TRN-01524 | 036909C-JVD-TRN-01524 | IFR | 2019-05-15 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01524 |  | 2019-05-02 | 2
036909C-1025-SP-0510-2580 | Mechanical Equipment Data Sheet - C2 Tower | 0 | 2019-04-26 | IFP | OL1-2M03-2580 | ME | 2019-04-26 | 036909C-JVD-TRN-01502 | 036909C-JVD-TRN-01502 | IFR | 2019-05-13 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01502 |  | 2019-04-29 | 2
036909C-1025-SP-0510-2570 | Mechanical Equipment Data Sheet - Deethanizer | 0 | 2019-04-25 | IFP | OL1-2M03-2570 | ME | 2019-04-26 | 036909C-JVD-TRN-01494 | 036909C-JVD-TRN-01494 | IFR | 2019-05-13 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01494 |  | 2019-04-29 | 2
036909C-1025-SP-0510-2520 | Mechanical Equipment Data Sheet - Residue Gas Rectifier Reflux Drum | 0 | 2019-05-08 | IFP | OL1-2M03-2520 | ME | 2019-05-15 | 036909C-JVD-TRN-01671 | 036909C-JVD-TRN-01671 | IFR | 2019-05-30 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01671 |  | 2019-05-16 | 2
036909C-1021-SP-0840-2104 | Mechanical Equipment Datasheet - Quench Oil Reflux Filter | 0 | 2019-05-13 | IFP | OL1-2M03-2104 | ME | 2019-05-15 | 036909C-JVD-TRN-01669 | 036909C-JVD-TRN-01669 | IFR | 2019-05-30 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01669 |  | 2019-05-16 | 2
036909C-1020-SP-0840-2049 | Mechanical Equipment Datasheet - Heavy Fuel Oil Filters | 0 | 2019-05-13 | IFP | OL1-2M03-2049 | ME | 2019-05-15 | 036909C-JVD-TRN-01669 | 036909C-JVD-TRN-01669 | IFR | 2019-05-30 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01669 |  | 2019-05-16 | 2
036909C-1020-SP-0840-2025 | Mechanical Equipment Datasheet - Cracker Bottoms Product Filter | 0 | 2019-05-13 | IFP | OL1-2M03-2025 | ME | 2019-05-15 | 036909C-JVD-TRN-01669 | 036909C-JVD-TRN-01669 | IFR | 2019-05-30 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01669 |  | 2019-05-16 | 2
036909C-1020-SP-0840-2010 | Mechanical Equipment Data sheet - Quench Oil Filter | 0 | 2019-05-13 | IFP | OL1-2M03-2010 | ME | 2019-05-15 | 036909C-JVD-TRN-01669 | 036909C-JVD-TRN-01669 | IFR | 2019-05-30 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01669 |  | 2019-05-16 | 2
036909C-1030-SP-0910-3036 | Mechanical Equipment Datasheet - After Washer Bottom Pumps | A | 2019-04-11 | IFQ | OL1-2M03-3036 | ME | 2019-04-16 | 036909C-JVD-TRN-01370 | 036909C-JVD-TRN-01370 | IFR | 2019-05-01 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-ME-01370 |  | 2019-04-17 | 2
036909C-1030-SP-0910-3033 | Mechanical Equipment Datasheet - After Washer Reflux-Crude Butadiene Pumps | A | 2019-04-11 | IFQ | OL1-2M03-3033 | ME | 2019-04-16 | 036909C-JVD-TRN-01370 | 036909C-JVD-TRN-01370 | IFR | 2019-05-01 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-ME-01370 |  | 2019-04-17 | 2
036909C-1030-SP-0910-3007 | Mechanical Equipment Datasheet - Predistillation Tower Reflux Pumps | A | 2019-04-11 | IFQ | OL1-2M03-3007 | ME | 2019-04-15 | 036909C-JVD-TRN-01363 | 036909C-JVD-TRN-01363 | IFR | 2019-04-30 |  | Transmitted | TPSK-LSPA1-T-ME-01363 |  | 2019-04-16 | 2
036909C-1030-SP-0910-3006 | Mechanical Equipment Datasheet - Predistallation Tower Feed Pumps | A | 2019-04-10 | IFQ | OL1-2M03-3006 | ME | 2019-04-16 | 036909C-JVD-TRN-01370 | 036909C-JVD-TRN-01370 | IFR | 2019-05-01 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-ME-01370 |  | 2019-04-17 | 2
036909C-1023-CN-0014-2308 | PSV-2341 Sizing Calculation | A | 2019-05-08 | IFR | OL1-2G23-2308 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1059-SP-0940-5901 | Mechanical Equipment Datasheet - Sulfuric Acid Distribution Pumps | 0 | 2019-04-12 | CAN | OL1-2M03-5901 | ME | 2019-04-15 | 036909C-JVD-TRN-01363 | 036909C-JVD-TRN-01363 | IFR | 2019-04-30 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-ME-01363 |  | 2019-04-16 | 2
036909C-1051-PDS-0900-5102 | Process Equipment Datasheet - 10-P-5102 A-B - VLP BFW Pumps | D | 2019-04-24 | IFD | OL1-2G30-5102 | PE | 2019-04-25 | 036909C-JVD-TRN-01484 | 036909C-JVD-TRN-01484 | IFR | 2019-05-10 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-PE-01484 |  | 2019-04-26 | 2
036909C-1051-PDS-0900-5101 | Process Equipment Datasheet - 10-P-5100 A-C - SHP BFW Pumps | C | 2019-04-24 | IFD | OL1-2G30-5101 | PE | 2019-04-25 | 036909C-JVD-TRN-01483 | 036909C-JVD-TRN-01483 | IFR | 2019-05-10 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-PE-01483 |  | 2019-04-26 | 2
036909C-1027-PDS-0900-2791 | Process Equipment Datasheet - 10-P-2790 - Light Oil Drain Drum Pump | C | 2019-04-17 | IFD | OL1-2G30-2791 | PE | 2019-04-22 | 036909C-JVD-TRN-01434 | 036909C-JVD-TRN-01434 | IFR | 2019-05-07 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01434 |  | 2019-04-23 | 2
036909C-1027-PDS-0800-2767 | Process Equipment Datasheet - 10-D-2765 - C4 - C5 Hydrog Coalescer Drum | C | 2019-05-03 | IFD | OL1-2G30-2767 | PE | 2019-05-07 | 036909C-JVD-TRN-01600 | 036909C-JVD-TRN-01600 | IFR | 2019-05-22 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01600 |  | 2019-05-08 | 2
036909C-1027-PDS-0600-2765 | Process Equipment Datasheet - 10-E-2765 - C4-C5 Hydrog Recycle Cooler | C | 2019-05-03 | IFD | OL1-2G30-2765 | PE | 2019-05-07 | 036909C-JVD-TRN-01604 | 036909C-JVD-TRN-01604 | IFR | 2019-05-22 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-PE-01604 |  | 2019-05-08 | 2
036909C-1027-PDS-0600-2763 | Process Equipment Datasheet - 10-E-2760 - C4-C5 Hydrog Vent Condenser | C | 2019-05-05 | IFD | OL1-2G30-2763 | PE | 2019-05-07 | 036909C-JVD-TRN-01604 | 036909C-JVD-TRN-01604 | IFR | 2019-05-22 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-PE-01604 |  | 2019-05-08 | 2
036909C-1027-PDS-0600-2715 | Process Equipment Datasheet - 10-E-2715 - Depentanizer Reboiler | C | 2019-04-24 | IFD | OL1-2G30-2715 | PE | 2019-04-26 | 036909C-JVD-TRN-01507 | 036909C-JVD-TRN-01507 | IFR | 2019-05-13 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-PE-01507 |  | 2019-04-29 | 2
036909C-1027-PDS-0600-2711 | Process Equipment Datasheet - 10-E-2710 - Depentanizer Condenser | C | 2019-05-06 | IFD | OL1-2G30-2711 | PE | 2019-05-07 | 036909C-JVD-TRN-01604 | 036909C-JVD-TRN-01604 | IFR | 2019-05-22 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-PE-01604 |  | 2019-05-08 | 2
036909C-1027-PDS-0600-2707 | Process Equipment Datasheet - 10-E-2706 - GHU-1 Cooler | C | 2019-05-03 | IFD | OL1-2G30-2707 | PE | 2019-05-07 | 036909C-JVD-TRN-01604 | 036909C-JVD-TRN-01604 | IFR | 2019-05-22 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-PE-01604 |  | 2019-05-08 | 2
036909C-1027-PDS-0600-2703 | Process Equipment Datasheet - 10-E-2705 - GHU-1 Recycle Cooler | C | 2019-05-03 | IFD | OL1-2G30-2703 | PE | 2019-05-07 | 036909C-JVD-TRN-01604 | 036909C-JVD-TRN-01604 | IFR | 2019-05-22 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-PE-01604 |  | 2019-05-08 | 2
036909C-1027-PDS-0600-2701 | Process Equipment Datasheet - 10-E-2701 - GHU-1 Feed - Effluent Exchangers | C | 2019-05-03 | IFD | OL1-2G30-2701 | PE | 2019-05-07 | 036909C-JVD-TRN-01604 | 036909C-JVD-TRN-01604 | IFR | 2019-05-22 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-PE-01604 |  | 2019-05-08 | 2
036909C-1055-CN-0001-5501 | PSV-5507 Sizing Calculation | A | 2019-06-10 | IFR | OL1-2G23-5501 | PE | 2019-06-11 | 036909C-JVD-TRN-01873 | 036909C-JVD-TRN-01873 | IFR | 2019-06-26 |  | Transmitted | TPSK-LSPA1-T-PE-01873 |  | 2019-06-11 | 2
036909C-1055-CN-0014-5508 | PSV-5530 Sizing Calculation | A | 2019-06-11 | IFR | OL1-2G23-5508 | PE | 2019-06-12 | 036909C-JVD-TRN-01883 | 036909C-JVD-TRN-01883 | IFR | 2019-06-27 |  | Transmitted | TPSK-LSPA1-T-PE-01883 |  | 2019-06-14 | 2
036909C-1055-CN-0014-5507 | PSV-5521 Sizing Calculation | A | 2019-06-11 | IFR | OL1-2G23-5507 | PE | 2019-06-11 | 036909C-JVD-TRN-01873 | 036909C-JVD-TRN-01873 | IFR | 2019-06-26 |  | Transmitted | TPSK-LSPA1-T-PE-01873 |  | 2019-06-11 | 2
036909C-1055-CN-0014-5506 | PSV-5520 Sizing Calculation | A | 2019-06-11 | IFR | OL1-2G23-5506 | PE | 2019-06-11 | 036909C-JVD-TRN-01873 | 036909C-JVD-TRN-01873 | IFR | 2019-06-26 |  | Transmitted | TPSK-LSPA1-T-PE-01873 |  | 2019-06-11 | 2
036909C-1055-CN-0014-5502 | PSV-5506 Sizing Calculation | A | 2019-06-11 | IFR | OL1-2G23-5502 | PE | 2019-06-11 | 036909C-JVD-TRN-01873 | 036909C-JVD-TRN-01873 | IFR | 2019-06-26 |  | Transmitted | TPSK-LSPA1-T-PE-01873 |  | 2019-06-11 | 2
036909C-1027-CN-0014-2710 | PSV-2721 Sizing Calculation | A | 2019-06-10 | IFR | OL1-2G23-2710 | PE | 2019-06-11 | 036909C-JVD-TRN-01873 | 036909C-JVD-TRN-01873 | IFR | 2019-06-26 |  | Transmitted | TPSK-LSPA1-T-PE-01873 |  | 2019-06-11 | 2
036909C-1027-CN-0014-2733 | PSV-2707 AB Sizing Calculation | A | 2019-06-10 | IFR | OL1-2G23-2733 | PE | 2019-06-11 | 036909C-JVD-TRN-01873 | 036909C-JVD-TRN-01873 | IFR | 2019-06-26 |  | Transmitted | TPSK-LSPA1-T-PE-01873 |  | 2019-06-11 | 2
036909C-1027-CN-0014-2705 | PSV-2705 Sizing Calculation | A | 2019-06-12 | IFR | OL1-2G23-2705 | PE | 2019-06-12 | 036909C-JVD-TRN-01883 | 036909C-JVD-TRN-01883 | IFR | 2019-06-27 |  | Transmitted | TPSK-LSPA1-T-PE-01883 |  | 2019-06-14 | 2
036909C-1027-CN-0014-2707 | PSV-2715 Sizing Calculation | A | 2019-06-12 | IFR | OL1-2G23-2707 | PE | 2019-06-12 | 036909C-JVD-TRN-01883 | 036909C-JVD-TRN-01883 | IFR | 2019-06-27 |  | Transmitted | TPSK-LSPA1-T-PE-01883 |  | 2019-06-14 | 2
036909C-1027-CN-0014-2731 | PSV-2720 A-B-C Sizing Calculation | A | 2019-06-10 | IFR | OL1-2G23-2731 | PE | 2019-06-11 | 036909C-JVD-TRN-01873 | 036909C-JVD-TRN-01873 | IFR | 2019-06-26 |  | Transmitted | TPSK-LSPA1-T-PE-01873 |  | 2019-06-11 | 2
036909C-1027-CN-0014-2735 | PSV-2745 Sizing Calculation | A | 2019-06-12 | IFR | OL1-2G23-2735 | PE | 2019-06-12 | 036909C-JVD-TRN-01883 | 036909C-JVD-TRN-01883 | IFR | 2019-06-27 |  | Transmitted | TPSK-LSPA1-T-PE-01883 |  | 2019-06-14 | 2
036909C-1027-CN-0014-2734 | PSV-2714 Sizing Calculation | A | 2019-06-10 | IFR | OL1-2G23-2734 | PE | 2019-06-11 | 036909C-JVD-TRN-01873 | 036909C-JVD-TRN-01873 | IFR | 2019-06-26 |  | Transmitted | TPSK-LSPA1-T-PE-01873 |  | 2019-06-11 | 2
036909C-1027-CN-0014-2714 | PSV-2734 A-B-C Sizing Calculation | A | 2019-06-11 | IFR | OL1-2G23-2714 | PE | 2019-06-11 | 036909C-JVD-TRN-01873 | 036909C-JVD-TRN-01873 | IFR | 2019-06-26 |  | Transmitted | TPSK-LSPA1-T-PE-01873 |  | 2019-06-11 | 2
036909C-1027-CN-0014-2716 | PSV-2738 A-B Sizing Calculation | A | 2019-06-12 | IFR | OL1-2G23-2716 | PE | 2019-06-12 | 036909C-JVD-TRN-01883 | 036909C-JVD-TRN-01883 | IFR | 2019-06-27 |  | Transmitted | TPSK-LSPA1-T-PE-01883 |  | 2019-06-14 | 2
036909C-1026-CN-0014-2621 | PSV-2651 Sizing Calculation | A | 2019-06-12 | IFR | OL1-2G23-2621 | PE | 2019-06-12 | 036909C-JVD-TRN-01883 | 036909C-JVD-TRN-01883 | IFR | 2019-06-27 |  | Transmitted | TPSK-LSPA1-T-PE-01883 |  | 2019-06-14 | 2
036909C-1026-CN-0014-2603 | PSV-2633 A-B Sizing Calculation | B | 2019-06-12 | IFR | OL1-2G23-2603 | PE | 2019-06-12 | 036909C-JVD-TRN-01883 | 036909C-JVD-TRN-01883 | IFR | 2019-06-27 |  | Transmitted | TPSK-LSPA1-T-PE-01883 |  | 2019-06-14 | 2
036909C-1021-CN-0014-2118 | PSV-2132 Sizing Calculation | B | 2019-06-11 | IFR | OL1-2G23-2118 | PE | 2019-06-12 | 036909C-JVD-TRN-01883 | 036909C-JVD-TRN-01883 | IFR | 2019-06-27 |  | Transmitted | TPSK-LSPA1-T-PE-01883 |  | 2019-06-14 | 2
036909C-1021-CN-0014-2112 | PSV-2145 A-B-C-D Sizing Calculation | B | 2019-06-11 | IFR | OL1-2G23-2112 | PE | 2019-06-11 | 036909C-JVD-TRN-01873 | 036909C-JVD-TRN-01873 | IFR | 2019-06-26 |  | Transmitted | TPSK-LSPA1-T-PE-01873 |  | 2019-06-11 | 2
036909C-1021-CN-0014-2106 | PSV-2125 A-B Sizing Calculation | B | 2019-06-11 | IFR | OL1-2G23-2106 | PE | 2019-06-11 | 036909C-JVD-TRN-01873 | 036909C-JVD-TRN-01873 | IFR | 2019-06-26 |  | Transmitted | TPSK-LSPA1-T-PE-01873 |  | 2019-06-11 | 2
036909C-1021-CN-0014-2111 | PSV-2136 Sizing Calculation | B | 2019-06-11 | IFR | OL1-2G23-2111 | PE | 2019-06-11 | 036909C-JVD-TRN-01873 | 036909C-JVD-TRN-01873 | IFR | 2019-06-26 |  | Transmitted | TPSK-LSPA1-T-PE-01873 |  | 2019-06-11 | 2
036909C-1000-PP-256 | 3D Modeling Procedure For Civil Designers | 0 | 2019-04-09 | IMP | OL1-2R02-0010 | CV | 2019-04-12 | 036909C-JVD-TRN-01335 | 036909C-JVD-TRN-01335 | IFR | 2019-04-29 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01335 |  | 2019-04-15 | 2
036909C-102D-CN-1733-0041 | Calculation Note For Foundation Of 10-E-2585 | A | 2019-03-21 | IFR | OL1-2K13-0232 | CV | 2019-04-01 | 036909C-JVD-TRN-01207 | 036909C-JVD-TRN-01207, ROC-TPSK-CECO-T-00034 | IFA | 2019-04-16 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01207 |  | 2019-04-02 | 1
036909C-102B-CN-1733-0045 | Calculation Note For Foundation Of 10-E-1050 | A | 2019-03-28 | IFR | OL1-2K13-0194 | CV | 2019-04-01 | 036909C-JVD-TRN-01207 | 036909C-JVD-TRN-01207, ROC-TPSK-CECO-T-00034 | IFA | 2019-04-16 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01207 |  | 2019-04-02 | 1
036909C-102B-CN-1733-0044 | Calculation Note for Foundation of 10-E-1020 | A | 2019-03-28 | IFR | OL1-2K13-0161 | CV | 2019-04-01 | 036909C-JVD-TRN-01207 | 036909C-JVD-TRN-01207, ROC-TPSK-CECO-T-00034 | IFA | 2019-04-16 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01207 |  | 2019-04-02 | 1
036909C-102D-CN-1733-0040 | Calculation Note For Foundation Of 10-E-2587 | A | 2019-03-21 | IFR | OL1-2K13-0111 | CV | 2019-04-01 | 036909C-JVD-TRN-01207 | 036909C-JVD-TRN-01207, ROC-TPSK-CECO-T-00034 | IFA | 2019-04-16 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01207 |  | 2019-04-02 | 1
036909C-102E-CN-1733-0022 | Calculation Note For Foundation Of 10-E-2206 | A | 2019-03-28 | IFR | OL1-2K13-0067 | CV | 2019-04-01 | 036909C-JVD-TRN-01207 | 036909C-JVD-TRN-01207, ROC-TPSK-CECO-T-00034 | IFA | 2019-04-16 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01207 |  | 2019-04-02 | 1
036909C-1051-TDS-0661-5108 | Mechanical Equipment Data Sheet - 10-E-5110 - Suspect Condensate Cooler | 0 | 2019-02-21 | IFP | OL1-2M03-5108 | ME | 2019-02-25 | 036909C-JVD-TRN-00930 | 036909C-JVD-TRN-00930, ROC-TPSK-CECO-T-00018 | IFR | 2019-03-12 | 2019-03-25 | R1-No comments | TPSK-LSPA1-T-ME-00930 |  | 2019-02-26 | 2
036909C-1051-TDS-0661-5108 | Mechanical Equipment Data Sheet - 10-E-5110 - Suspect Condensate Cooler | A | 2019-01-23 | IFQ | OL1-2M03-5108 | ME | 2019-01-25 | 036909C-JVD-TRN-00723 | 036909C-JVD-TRN-00723 | IFR | 2019-02-07 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00723 |  | 2019-01-25 | 2
036909C-1012-DW-0131-2511 | USC 132U Cracking Furnace Steel Radiant Floor And Radiant Arch Plans | A | 2019-03-29 | IFI | OL1-2K32-2511 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1012-DW-0131-2511 | USC 132U Cracking Furnace Steel Radiant Floor And Radiant Arch Plans | 0 | 2019-05-15 | IMP | OL1-2K32-2511 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1012-DW-0132-2108 | USC 132U Cracking Furnace Decoke Nozzle Details | A | 2019-02-22 | IFR | OL1-2M06-2108 | ME | 2019-03-14 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15 | 2
036909C-1011-DW-0132-1108 | USC 36M Recycle Furnace Decoke Nozzle Details | A | 2019-02-22 | IFR | OL1-2M06-1108 | ME | 2019-03-14 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15 | 2
036909C-1027-PDS-0900-2704 | Process Equipment Datasheet - 10-P-2705 A-B - GHU-1 Recycle Pump | C | 2019-05-24 | IFD | OL1-2G30-2704 | PE | 2019-05-24 | 036909C-JVD-TRN-01739 | 036909C-JVD-TRN-01739 | IFR | 2019-06-10 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01739 |  | 2019-05-27 | 2
036909C-1027-PDS-0900-2764 | Process Equipment Datasheet - 10-P-2760 A-B - C4 - C5 Hydrog Recycle Pump | C | 2019-05-24 | IFD | OL1-2G30-2764 | PE | 2019-05-24 | 036909C-JVD-TRN-01739 | 036909C-JVD-TRN-01739 | IFR | 2019-06-10 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01739 |  | 2019-05-27 | 2
036909C-1026-PDS-0900-2668 | Process Equipment Datasheet - 10-P-2666 A-B - C5 - Pygas Pumps | D | 2019-05-24 | IFD | OL1-2G30-2668 | PE | 2019-05-24 | 036909C-JVD-TRN-01739 | 036909C-JVD-TRN-01739 | IFR | 2019-06-10 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01739 |  | 2019-05-24 | 2
036909C-1026-PDS-0900-2623 | Process Equipment Data Sheet - 10-P-2620 A-B - C3 Hydrog Recycle Pumps | C | 2019-05-24 | IFD | OL1-2G30-2623 | PE | 2019-05-24 | 036909C-JVD-TRN-01739 | 036909C-JVD-TRN-01739 | IFR | 2019-06-10 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01739 |  | 2019-05-27 | 2
036909C-1029-CN-0014-2930 | PSV-2989 Sizing Calculation | A | 2019-05-20 | IFR | OL1-2G23-2930 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1029-CN-0014-2929 | PSV-2975 Sizing Calculation | A | 2019-05-20 | IFR | OL1-2G23-2929 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1029-CN-0014-2923 | PSV-2981 Sizing Calculation | A | 2019-05-20 | IFR | OL1-2G23-2923 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1029-CN-0014-2919 | PSV-2967 Sizing Calcuation | A | 2019-05-20 | IFR | OL1-2G23-2919 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1029-CN-0014-2918 | PSV-2966 Sizing Calculation | A | 2019-05-20 | IFR | OL1-2G23-2918 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1024-CN-0014-2426 | PSV-2441 Sizing Calculation | A | 2019-04-24 | IFR | OL1-2G23-2426 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1024-CN-0014-2409 | PSV-2415 A-B Sizing Calculation | B | 2019-05-21 | IFR | OL1-2G23-2409 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1024-CN-0014-2408 | PSV-2414 A-B Sizing Calculation | B | 2019-05-20 | IFR | OL1-2G23-2408 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1029-CN-0014-2928 | PSV-2963 Sizing Caluclation | A | 2019-05-20 | IFR | OL1-2G23-2928 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1029-CN-0014-2925 | PSV-2986 Sizing Calculation | A | 2019-05-20 | IFR | OL1-2G23-2925 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1029-CN-0014-2924 | PSV-2985 Sizing Calucation | A | 2019-05-20 | IFR | OL1-2G23-2924 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1029-CN-0014-2917 | PSV-2965 Sizing Calculation | A | 2019-05-20 | IFR | OL1-2G23-2917 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1029-CN-0014-2914 | PSV-2959 Sizing Calculation | A | 2019-05-20 | IFR | OL1-2G23-2914 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1029-CN-0014-2913 | PSV-2958 Sizing Calculation | A | 2019-05-20 | IFR | OL1-2G23-2913 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1029-CN-0014-2912 | PSV-2956 Sizing Calculation | A | 2019-05-15 | IFR | OL1-2G23-2912 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1024-CN-0014-2425 | PSV-2438 Sizing Calculation | A | 2019-05-01 | IFR | OL1-2G23-2425 | PE | 2019-05-24 | 036909C-JVD-TRN-01737 | 036909C-JVD-TRN-01737 | IFR | 2019-06-10 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01737 |  | 2019-05-27 | 2
036909C-1023-PDS-0800-2392 | Process Equipment Datasheet - 10-D-2392 - Spent Caustic Drain Drum | C | 2019-04-15 | IFD | OL1-2G30-2392 | PE | 2019-04-16 | 036909C-JVD-TRN-01377 | 036909C-JVD-TRN-01377 | IFR | 2019-05-01 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01377 |  | 2019-04-17 | 2
036909C-1023-PDS-0800-2390 | Process Equipment Datasheet - 10-D-2390 - Caustic Drain Drum | C | 2019-04-15 | IFD | OL1-2G30-2390 | PE | 2019-04-16 | 036909C-JVD-TRN-01377 | 036909C-JVD-TRN-01377 | IFR | 2019-05-01 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01377 |  | 2019-04-17 | 2
036909C-1023-PDS-0800-2322 | Process Equipment Datasheet - 10-D-2322 - Skim Oil Drum | C | 2019-04-15 | IFD | OL1-2G30-2322 | PE | 2019-04-16 | 036909C-JVD-TRN-01377 | 036909C-JVD-TRN-01377 | IFR | 2019-05-01 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01377 |  | 2019-04-17 | 2
036909C-1030-PDS-0900-3047 | Process Equipment Data Sheet - 10-P-3045 A-B - Rectifier Pump | A | 2019-04-04 | IFR | OL1-2G30-3047 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1030-PDS-0900-3036 | Process Equipment Data Sheet - 10-P-3036 A-B After Washer Bottom Pump | A | 2019-04-04 | IFR | OL1-2G30-3036 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1000-MR-0662-0001 | Material Requisition For Heat Recovery System Requisition For Purchase | 0 | 2019-02-20 | IFP | OL1-2C13-143000 | PL | 2019-02-21 | 036909C-JVD-TRN-00906 | 036909C-JVD-TRN-00906 | IFR | 2019-03-08 | 2019-06-06 | R2-Comments as noted | TPSK-LSPA1-T-PL-00906 |  | 2019-02-22 | 2
036909C-1012-DW-0117-2207 | USC 132U Cracking Furnace Dilution Mixing Tee Details | 1 | 2019-04-26 | IMP | OL1-2M06-2207- | ME | 2019-04-26 | 036909C-JVD-TRN-01509 | 036909C-JVD-TRN-01509 | IFI |  | 2019-05-31 | R1-No comments | TPSK-LSPA1-T-ME-01509 |  | 2019-04-29 | 3
036909C-1030-PDS-0900-3033 | Process Equipment Data Sheet - 10-P-3030 A-B After Washer Reflux - Crude Butadiene Pump | A | 2019-04-04 | IFR | OL1-2G30-3033 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1030-PDS-0900-3016 | Process Equipment Data Sheet - 10-P-3016 A-B Heavy End Discharge Pump | A | 2019-04-04 | IFR | OL1-2G30-3016 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1030-PDS-0900-3007 | Process Equipment Data Sheet - 10-P-3000 A-B Predistillation Tower Reflux Pump | A | 2019-04-01 | IFR | OL1-2G30-3007 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1030-PDS-0900-3006 | Process Equipment Data Sheet - 10-P-3002 A-B - Predistillation Tower Feed Pump | A | 2019-04-01 | IFR | OL1-2G30-3006 | PE | 2019-04-05 | 036909C-JVD-TRN-01265 | 036909C-JVD-TRN-01265 | IFR | 2019-04-22 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01265 |  | 2019-04-08 | 2
036909C-1022-CN-0014-2210 | PSV-2266 A-B Sizing Calulation | A | 2019-04-23 | IFR | OL1-2G23-2210 | PE | 2019-04-24 | 036909C-JVD-TRN-01475 | 036909C-JVD-TRN-01475 | IFR | 2019-05-09 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01475 |  | 2019-04-25 | 2
036909C-1022-CN-0014-2204 | PSV-2230 Sizing Calculation | A | 2019-04-16 | IFR | OL1-2G23-2204 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1022-CN-0014-2201 | PSV-2201 Sizing Calculation | A | 2019-04-11 | IFR | OL1-2G23-2201 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1030-PDS-0850-3072 | Process Equipment Datasheet - 10-EJ-3070 - BDU Recycle Gas Ejector | A | 2019-04-08 | IFR | OL1-2G30-3072 | PE | 2019-04-09 | 036909C-JVD-TRN-01283 | 036909C-JVD-TRN-01283 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01283 |  | 2019-04-10 | 2
036909C-1039-PDS-2500-3900 | Process Equipment Datasheet - 10-TK-3900 - NMP Storage Tank | A | 2019-04-10 | IFR | OL1-2G30-3900 | PE | 2019-04-11 | 036909C-JVD-TRN-01318 | 036909C-JVD-TRN-01318 | IFR | 2019-04-26 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01318 |  | 2019-04-12 | 2
036909C-1031-PDS-4260-3101 | Process Equipment Datasheet - 10-A-3100 - Solvent Regen Agitator | A | 2019-04-10 | IFR | OL1-2G30-3101 | PE | 2019-04-11 | 036909C-JVD-TRN-01319 | 036909C-JVD-TRN-01319 | IFR | 2019-04-26 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01319 |  | 2019-04-12 | 2
036909C-1031-PDS-4100-3123 | Process Equipment Datasheet - 10-PK-3120 - Regeneration Steam Ejector Package Unit | A | 2019-04-08 | IFR | OL1-2G30-3123 | PE | 2019-04-09 | 036909C-JVD-TRN-01284 | 036909C-JVD-TRN-01284 | IFR | 2019-04-24 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01284 |  | 2019-04-10 | 2
036909C-1024-SP-0510-2440 | Mechanical Equipment Datasheet - HP Depropanizer | 0 | 2019-04-25 | IFP | OL1-2M03-2440 | ME | 2019-04-25 | 036909C-JVD-TRN-01489 | 036909C-JVD-TRN-01489 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01489 |  | 2019-04-26 | 2
036909C-1024-SP-0510-2440 | Mechanical Equipment Datasheet - HP Depropanizer | C | 2019-02-15 | IFQ | OL1-2M03-2440 | ME | 2019-02-19 | 036909C-JVD-TRN-00884 | 036909C-JVD-TRN-00884, ROC-TPSK-CECO-T-00014 | IFR | 2019-03-05 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00884 |  | 2019-02-19 | 2
036909C-1027-SP-0510-2720 | Mechanical Equipment Data Sheet - Rerun Tower | B | 2019-04-17 | IFQ | OL1-2M03-2720 | ME | 2019-04-17 | 036909C-JVD-TRN-01399 | 036909C-JVD-TRN-01399 | IFR | 2019-05-02 |  | Transmitted | TPSK-LSPA1-T-ME-01399 |  | 2019-04-18 | 2
036909C-1027-SP-0510-2720 | Mechanical Equipment Data Sheet - Rerun Tower | A | 2019-01-25 | IFQ | OL1-2M03-2720 | ME | 2019-01-28 | 036909C-JVD-TRN-00741 | 036909C-JVD-TRN-00741, ROC-TPSK-CECO-T-00015 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00741 |  | 2019-01-28 | 2
036909C-1021-PDS-0840-2139 | Process Equipment Datasheet - 10-F-2137 A-B - Process Water Coalescer Prefilters | A | 2019-04-17 | IFR | OL1-2G30-2139 | PE | 2019-04-17 | 036909C-JVD-TRN-01401 | 036909C-JVD-TRN-01401 | IFR |  | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01401 |  | 2019-04-18 | 2
036909C-1031-PDS-0600-3160 | Process Equipment Datasheet - 10-E-3160 - BDU Condensate Cooler | A | 2019-03-29 | IFR | OL1-2G30-3160 | PE | 2019-04-01 | 036909C-JVD-TRN-01214 | 036909C-JVD-TRN-01214 | IFR | 2019-04-16 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01214 |  | 2019-04-02 | 2
036909C-1031-PDS-0600-3150 | Process Equipment Datasheet - 10-E-3150 - BDU Condensate Heater | A | 2019-03-29 | IFR | OL1-2G30-3150 | PE | 2019-04-01 | 036909C-JVD-TRN-01214 | 036909C-JVD-TRN-01214 | IFR | 2019-04-16 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01214 |  | 2019-04-02 | 2
036909C-1030-PDS-0600-3095 | Process Equipment Datasheet - 10-E-3095 - Butadiene Drying Tower Reboiler | A | 2019-03-29 | IFR | OL1-2G30-3095 | PE | 2019-03-29 | 036909C-JVD-TRN-01202 | 036909C-JVD-TRN-01202 | IFR | 2019-04-15 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01202 |  | 2019-04-01 | 2
036909C-1051-PDS-0900-5102 | Process Equipment Datasheet - 10-P-5102 A-B - VLP BFW Pumps | C | 2019-03-28 | IFD | OL1-2G30-5102 | PE | 2019-03-29 | 036909C-JVD-TRN-01196 | 036909C-JVD-TRN-01196 | IFR | 2019-04-15 | 2019-06-07 | R1-No comments | TPSK-LSPA1-T-PE-01196 |  | 2019-04-01 | 2
036909C-1027-PDS-0600-2702 | Process Equipment Datasheet - 10-E-2702 - GHU-1 Start-up Heater | C | 2019-04-15 | IFD | OL1-2G30-2702 | PE | 2019-04-16 | 036909C-JVD-TRN-01371 | 036909C-JVD-TRN-01371 | IFR | 2019-05-01 | 2019-06-07 | R1-No comments | TPSK-LSPA1-T-PE-01371 |  | 2019-04-17 | 2
036909C-1052-PDS-0600-5210 | Process Equipment Datasheet - 10-E-5210 - Pilot Gas Vaporizer | C | 2019-04-04 | IFD | OL1-2G30-5210 | PE | 2019-04-08 | 036909C-JVD-TRN-01278 | 036909C-JVD-TRN-01278 | IFR | 2019-04-23 | 2019-06-07 | R1-No comments | TPSK-LSPA1-T-PE-01278 |  | 2019-04-09 | 2
036909C-1051-PDS-0600-5113 | Process Equipment Datasheet - 10-E-5113 - Foul Condensate Cooler | C | 2019-04-04 | IFD | OL1-2G30-5113 | PE | 2019-04-08 | 036909C-JVD-TRN-01278 | 036909C-JVD-TRN-01278 | IFR | 2019-04-23 | 2019-06-07 | R1-No comments | TPSK-LSPA1-T-PE-01278 |  | 2019-04-09 | 2
036909C-1025-PDS-0600-2587 | Process Equipment Datasheet - 10-E-2587 - C2 Tower Side Reboiler | C | 2019-04-03 | IFD | OL1-2G30-2587 | PE | 2019-04-04 | 036909C-JVD-TRN-01261 | 036909C-JVD-TRN-01261, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-19 | 2019-06-07 | R1-No comments | TPSK-LSPA1-T-PE-01261 |  | 2019-04-05 | 2
036909C-1025-PDS-0600-2585 | Process Equipment Datasheet - 10-E-2585 - C2 Tower Bottoms Reboiler | C | 2019-04-03 | IFD | OL1-2G30-2585 | PE | 2019-04-04 | 036909C-JVD-TRN-01261 | 036909C-JVD-TRN-01261, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-19 | 2019-06-07 | R1-No comments | TPSK-LSPA1-T-PE-01261 |  | 2019-04-05 | 2
036909C-102A-CN-1733-0030 | Calculation Note for Foundation of 10-D-5140 | A | 2019-01-22 | IFR | OL1-2K13-0287 | CV | 2019-01-25 | 036909C-JVD-TRN-00682 | 036909C-JVD-TRN-00679, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-11 | 2019-06-03 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00679 |  | 2019-01-25 | 1
036909C-102D-CN-1733-0028 | Calculation Note for Foundation of 10-E-2502 | A | 2019-01-17 | IFR | OL1-2K13-0117 | CV | 2019-01-25 | 036909C-JVD-TRN-00682 | 036909C-JVD-TRN-00679, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-11 | 2019-06-03 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00679 |  | 2019-01-25 | 1
036909C-102D-CN-1733-0019 | Calculation Note For Foundation of 10-D-2870 | A | 2019-01-22 | IFR | OL1-2K13-0107 | CV | 2019-01-25 | 036909C-JVD-TRN-00682 | 036909C-JVD-TRN-00679, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-11 | 2019-06-03 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00679 |  | 2019-01-25 | 1
036909C-102D-CN-1733-0007 | Calculation Note For Foundation Of 10-T-2520/10-D-2520 | A | 2019-01-23 | IFR | OL1-2K13-0093 | CV | 2019-01-25 | 036909C-JVD-TRN-00682 | 036909C-JVD-TRN-00679, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-11 | 2019-06-03 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00679 |  | 2019-01-25 | 1
036909C-1029-PID-0021-2908 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Neutralization Injection | 0 | 2019-04-16 | CAN | OL1-2G43-2908 | PE | 2019-04-17 | 036909C-JVD-TRN-01397 | 036909C-JVD-TRN-01397, ROC-TPSK-CECO-T-00067 | IFR | 2019-05-02 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01397 |  | 2019-04-18 | 2
036909C-1053-PID-0031-5325 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 6 | 0 | 2019-04-18 | CAN | OL1-2G43-5325 | PE | 2019-04-22 | 036909C-JVD-TRN-01425 | 036909C-JVD-TRN-01425, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-07 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01425 |  | 2019-04-23 | 2
036909C-1010-CN-0014-1015 | PSV-1015 Sizing Calculation | A | 2019-04-18 | IFR | OL1-2G23-1015 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1010-CN-0014-1006 | PSV-1006 and PSV-1009 Sizing Calculation | A | 2019-04-16 | IFR | OL1-2G23-1006 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1010-CN-0014-1001 | PSV-1001 Sizing Calculation | A | 2019-04-15 | IFR | OL1-2G23-1001 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1025-CN-0014-2514 | PSV-2544 Sizing Calculation | A | 2019-03-26 | IFR | OL1-2G23-2514 | PE | 2019-04-22 | 036909C-JVD-TRN-01435 | 036909C-JVD-TRN-01435 | IFR | 2019-05-07 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01435 |  | 2019-04-23 | 2
036909C-1025-CN-0014-2504 | PSV-2517 Sizing Calculation | A | 2019-03-25 | IFR | OL1-2G23-2504 | PE | 2019-04-22 | 036909C-JVD-TRN-01435 | 036909C-JVD-TRN-01435 | IFR | 2019-05-07 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01435 |  | 2019-04-23 | 2
036909C-1024-CN-0014-2407 | PSV-2411 Sizing Calcuation | A | 2019-04-17 | IFR | OL1-2G23-2407 | PE | 2019-04-22 | 036909C-JVD-TRN-01435 | 036909C-JVD-TRN-01435 | IFR | 2019-05-07 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01435 |  | 2019-04-23 | 2
036909C-1024-CN-0014-2406 | PSV-2410 Sizing Calculation | A | 2019-04-17 | IFR | OL1-2G23-2406 | PE | 2019-04-22 | 036909C-JVD-TRN-01435 | 036909C-JVD-TRN-01435 | IFR | 2019-05-07 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01435 |  | 2019-04-23 | 2
036909C-1051-PDS-0600-5113 | Process Equipment Datasheet - 10-E-5113 - Foul Condensate Cooler | D | 2019-04-17 | IFD | OL1-2G30-5113 | PE | 2019-04-17 | 036909C-JVD-TRN-01406 | 036909C-JVD-TRN-01406 | IFR | 2019-05-02 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01406 |  | 2019-04-18 | 2
036909C-1027-PDS-0900-2719 | Process Equipment Datasheet - 10-P-2720 A-B - Rerun Tower Reflux - Product Pumps | B | 2019-04-17 | IFD | OL1-2G30-2719 | PE | 2019-04-17 | 036909C-JVD-TRN-01404 | 036909C-JVD-TRN-01404 | IFR | 2019-05-02 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01404 |  | 2019-04-18 | 2
036909C-1027-PDS-0900-2729 | Process Equipment Datasheet - 10-P-2721 A-B - Wash Oil Pumps | B | 2019-04-22 | IFD | OL1-2G30-2729 | PE | 2019-04-23 | 036909C-JVD-TRN-01458 | 036909C-JVD-TRN-01458 | IFR | 2019-05-08 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01458 |  | 2019-04-24 | 2
036909C-1020-PDS-0900-2046 | Process Equipment Datasheet - 10-P-2046 A-B - Heavy Fuel Oil Pumps | C | 2019-04-17 | IFD | OL1-2G30-2046 | PE | 2019-04-17 | 036909C-JVD-TRN-01402 | 036909C-JVD-TRN-01402 | IFR | 2019-05-02 | 2019-06-04 | R1-No comments | TPSK-LPSA1-T-PE-01402 |  | 2019-04-18 | 2
036909C-1021-PDS-0840-2138 | Process Equipment Datasheet - 10-F-2136 A-B - Process Water Feed Filters | D | 2019-04-17 | IFD | OL1-2G30-2138 | PE | 2019-04-17 | 036909C-JVD-TRN-01401 | 036909C-JVD-TRN-01401 | IFR |  | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01401 |  | 2019-04-18 | 2
036909C-1020-PDS-0840-2049 | Process Equipment Datasheet - 10-F-2048 A-B - Heavy Fuel Oil Filters | C | 2019-04-17 | IFD | OL1-2G30-2049 | PE | 2019-04-17 | 036909C-JVD-TRN-01401 | 036909C-JVD-TRN-01401 | IFR | 2019-05-02 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01401 |  | 2019-04-18 | 2
036909C-1000-PP-126 | Lsp Document Coding | A | 2019-05-10 | IFR | OL1-2W92-0023 | PC | 2019-05-16 | 036909C-JVD-TRN-01674 | 036909C-JVD-TRN-01674 | IFR | 2019-05-31 | 2019-05-30 | R2-Comments as noted | TPSK-LSPA1-T-PC-01674 |  | 2019-05-17 | 2
036909C-1010-CN-0014-1007 | PSV-1007 Sizing Calculation | A | 2019-04-16 | IFR | OL1-2G23-1007 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1022-CN-0014-2209 | PSV-2265 Sizing Calculation | A | 2019-04-17 | IFR | OL1-2G23-2209 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1022-CN-0014-2208 | PSV-2260 Sizing Calculation | A | 2019-04-16 | IFR | OL1-2G23-2208 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1022-CN-0014-2207 | PSV-2255 A-B Sizing Calculation | A | 2019-04-11 | IFR | OL1-2G23-2207 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1022-CN-0014-2205 | PSV-2235 Sizing Calculation | A | 2019-04-16 | IFR | OL1-2G23-2205 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1022-CN-0014-2203 | PSV-2225 Sizing Calculation | A | 2019-04-16 | IFR | OL1-2G23-2203 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1022-CN-0014-2202 | PSV-2210 Sizing Calculation | A | 2019-04-16 | IFR | OL1-2G23-2202 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1024-CN-0014-2405 | PSV-2408 Sizing Calculation | A | 2019-04-16 | IFR | OL1-2G23-2405 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1024-CN-0014-2404 | PSV-2407 Sizing Calculation | A | 2019-04-16 | IFR | OL1-2G23-2404 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1024-CN-0014-2403 | PSV-2405 Sizing Calculation | A | 2019-04-16 | IFR | OL1-2G23-2403 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1024-CN-0014-2402 | PSV-2403 A-B Sizing Calculation | A | 2019-04-15 | IFR | OL1-2G23-2402 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1024-CN-0014-2401 | PSV-2401 Sizing Calculaiton | A | 2019-04-16 | IFR | OL1-2G23-2401 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1010-CN-0014-1012 | PSV-1012 Sizing Calculation | A | 2019-04-22 | IFR | OL1-2G23-1012 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1010-CN-0014-1010 | PSV-1010 Sizing Calculation | A | 2019-04-17 | IFR | OL1-2G23-1010 | PE | 2019-04-24 | 036909C-JVD-TRN-01474 | 036909C-JVD-TRN-01474 | IFR | 2019-05-09 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01474 |  | 2019-04-25 | 2
036909C-1025-CN-0014-2521 | PSV-2553 A-B Sizing Calculation | A | 2019-03-15 | IFR | OL1-2G23-2521 | PE | 2019-04-22 | 036909C-JVD-TRN-01435 | 036909C-JVD-TRN-01435 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01435 |  | 2019-04-23 | 2
036909C-1025-CN-0014-2515 | PSV-2545 Sizing Calculation | A | 2019-03-27 | IFR | OL1-2G23-2515 | PE | 2019-04-22 | 036909C-JVD-TRN-01435 | 036909C-JVD-TRN-01435 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01435 |  | 2019-04-23 | 2
036909C-1025-CN-0014-2512 | PSV-2539 Sizing Calculation | A | 2019-03-16 | IFR | OL1-2G23-2512 | PE | 2019-04-22 | 036909C-JVD-TRN-01435 | 036909C-JVD-TRN-01435 | IFR | 2019-05-07 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01435 |  | 2019-04-23 | 2
036909C-1023-PDS-0900-2327 | Process Equipment Datasheet - 10-P-2322 - Skim Oil Pump | B | 2019-04-12 | IFD | OL1-2G30-2327 | PE | 2019-04-29 | 036909C-JVD-TRN-01517 | 036909C-JVD-TRN-01517 | IFR | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01517 |  | 2019-04-30 | 2
036909C-1028-CN-0014-2811 | PSV-2836 Sizing Calculation | A | 2019-05-10 | IFR | OL1-2G23-2811 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LPSA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1029-CN-0014-2906 | PSV-2931 Sizing Calculation | A | 2019-05-15 | IFR | OL1-2G23-2906 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2820 | PSV-2847 Sizing Calculation | A | 2019-05-13 | IFR | OL1-2G23-2820 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1029-CN-0014-2907 | PSV-2932 Sizing Calculation | A | 2019-05-15 | IFR | OL1-2G23-2907 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1029-CN-0014-2905 | PSV-2930 Sizing Calulation | A | 2019-05-15 | IFR | OL1-2G23-2905 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2807 | PSV-2826 Sizing Calculation | A | 2019-05-10 | IFR | OL1-2G23-2807 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LPSA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2817 | PSV-2843 Sizing Calculation | A | 2019-05-13 | IFR | OL1-2G23-2817 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2810 | PSV-2835 Sizing Calculation | A | 2019-05-10 | IFR | OL1-2G23-2810 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LPSA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2816 | PSV-2842 A-B Sizing Calculation | A | 2019-05-13 | IFR | OL1-2G23-2816 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2819 | PSV-2846 Sizing Calculation | A | 2019-05-13 | IFR | OL1-2G23-2819 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2808 | PSV-2829 Sizing Calculation | A | 2019-05-10 | IFR | OL1-2G23-2808 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LPSA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2825 | PSV-2856 Sizing Calculation | A | 2019-05-15 | IFR | OL1-2G23-2825 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2823 | PSV-2854 Sizing Calculation | A | 2019-05-15 | IFR | OL1-2G23-2823 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1029-CN-0014-2902 | PSV-2926 Sizing Calculation | A | 2019-05-15 | IFR | OL1-2G23-2902 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2822 | PSV-2852 Sizing Calculation | A | 2019-05-15 | IFR | OL1-2G23-2822 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2806 | PSV-2823 A-B Sizing Calculation | A | 2019-05-10 | IFR | OL1-2G23-2806 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R1-No comments | TPSK-LPSA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1029-CN-0014-2904 | PSV-2929 Sizing Calculation | A | 2019-05-15 | IFR | OL1-2G23-2904 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1029-CN-0014-2903 | PSV-2928 Sizing Calculation | A | 2019-05-15 | IFR | OL1-2G23-2903 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1029-CN-0014-2901 | PSV-2925 Sizing Calculation | A | 2019-05-15 | IFR | OL1-2G23-2901 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2821 | PSV-2851 Sizing Calculation | A | 2019-05-15 | IFR | OL1-2G23-2821 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2818 | PSV-2845 Sizing Calculation | A | 2019-05-13 | IFR | OL1-2G23-2818 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R2-Comments as noted | TPSK-LPSA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2815 | PSV-2841 A-D Sizing Calculation | A | 2019-05-10 | IFR | OL1-2G23-2815 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2813 | PSV-2838 Sizing Calculation | A | 2019-05-10 | IFR | OL1-2G23-2813 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R2-Comments as noted | TPSK-LPSA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1028-CN-0014-2814 | PSV-2839 Sizing Calculation | A | 2019-05-10 | IFR | OL1-2G23-2814 | PE | 2019-05-15 | 036909C-JVD-TRN-01672 | 036909C-JVD-TRN-01672 | IFR | 2019-05-30 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01672 |  | 2019-05-16 | 2
036909C-1031-PDS-0600-3111 | Process Equipment Datasheet - 10-E-3110 - Water Washer Condenser | A | 2019-03-29 | IFR | OL1-2G30-3111 | PE | 2019-03-29 | 036909C-JVD-TRN-01202 | 036909C-JVD-TRN-01202 | IFR | 2019-04-15 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01202 |  | 2019-04-01 | 2
036909C-1023-PDS-0800-2316 | Process Equipment Datasheet - 10-D-2316 - Spent Caustic Degassing Drum | C | 2019-04-15 | IFD | OL1-2G30-2316 | PE | 2019-04-16 | 036909C-JVD-TRN-01377 | 036909C-JVD-TRN-01377 | IFR | 2019-05-01 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-01377 |  | 2019-04-17 | 2
036909C-1023-SP-0510-2330 | Mechanical Equipment Data Sheet - Spent Caustic Stripper | B | 2019-02-13 | IFQ | OL1-2M03-2330 | ME | 2019-02-15 | 036909C-JVD-TRN-00857 | 036909C-JVD-TRN-00857, ROC-TPSK-CECO-T-00014 | IFR | 2019-03-01 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00857 |  | 2019-02-15 | 2
036909C-1023-SP-0510-2330 | Mechanical Equipment Data Sheet - Spent Caustic Stripper | A | 2018-12-06 | IFQ | OL1-2M03-2330 | ME | 2018-12-10 | 036909C-JVD-TRN-00462 | 036909C-JVD-TRN-00462 | IFR | 2018-12-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00462 |  | 2018-12-10 | 2
036909C-1052-SP-0810-5202 | Mechanical Equipment Data Sheet - MP Ethylene Superhtr Cond Pot | A | 2019-01-17 | IFQ | OL1-2M03-5202 | ME | 2019-01-22 | 036909C-JVD-TRN-00685 | 036909C-JVD-TRN-00685, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-04 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-00685 |  | 2019-01-22 | 2
036909C-1030-PDS-0600-3044 | Process Equipment Datasheet - 10-E-3044 - Solvent Heater | A | 2019-03-29 | IFR | OL1-2G30-3044 | PE | 2019-04-01 | 036909C-JVD-TRN-01214 | 036909C-JVD-TRN-01214 | IFR | 2019-04-16 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01214 |  | 2019-04-02 | 2
036909C-1030-PDS-0600-3045 | Process Equipment Datasheet - 10-E-3045 A-D - Solvent Heat Exchanger | A | 2019-03-28 | IFR | OL1-2G30-3045 | PE | 2019-04-01 | 036909C-JVD-TRN-01214 | 036909C-JVD-TRN-01214 | IFR | 2019-04-16 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01214 |  | 2019-04-02 | 2
036909C-1030-PDS-0600-3055 | Process Equipment Datasheet - 10-E-3055 A-B - Degasser Reboiler | A | 2019-03-28 | IFR | OL1-2G30-3055 | PE | 2019-03-29 | 036909C-JVD-TRN-01202 | 036909C-JVD-TRN-01202 | IFR | 2019-04-15 | 2019-04-12 | R2-Comments as noted | TPSK-LSAP1-T-PE-01202 |  | 2019-04-01 | 2
036909C-1056-PDS-0200-5647 | Process Equipment Datasheet - 10-PIT-5607 - Flare KO Drum Oily Wastewater Sump | 0 | 2019-05-08 | CAN | OL1-2G30-5647 | PE | 2019-05-09 | 036909C-JVD-TRN-01630 | 036909C-JVD-TRN-01630 | IFR | 2019-05-24 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01630 |  | 2019-05-10 | 2
036909C-1056-PDS-0200-5605 | Process Equipment Datasheet - 10-PIT-5605 - Furnace Area Oily Wastewater Sump | 0 | 2019-05-08 | CAN | OL1-2G30-5605 | PE | 2019-05-09 | 036909C-JVD-TRN-01630 | 036909C-JVD-TRN-01630 | IFR | 2019-05-24 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01630 |  | 2019-05-10 | 2
036909C-1056-PDS-2600-5698 | Process Equipment Datasheet - 10-PK-5698 - Bio Treat Caustic Inj Pkg | A | 2019-05-09 | IFR | OL1-2G30-5698 | PE | 2019-05-09 | 036909C-JVD-TRN-01629 | 036909C-JVD-TRN-01629 | IFR | 2019-05-24 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01629 |  | 2019-05-10 | 2
036909C-1056-PDS-2600-5695 | Process Equipment Datasheet - 10-PK-5695 - Bio Treat Sulfuric Acid Inj Pkg | A | 2019-05-09 | IFR | OL1-2G30-5695 | PE | 2019-05-09 | 036909C-JVD-TRN-01629 | 036909C-JVD-TRN-01629 | IFR | 2019-05-24 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01629 |  | 2019-05-10 | 2
036909C-1056-PDS-0900-5649 | Process Equipment Datasheet - 10-P-5607 A-B - Flare KO Drum Oily Wastewater Pump | 0 | 2019-05-08 | CAN | OL1-2G30-5649 | PE | 2019-05-09 | 036909C-JVD-TRN-01631 | 036909C-JVD-TRN-01631 | IFR | 2019-05-24 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01631 |  | 2019-05-10 | 2
036909C-1056-PDS-0900-5614 | Process Equipment Datasheet - 10-P-5605 A-B - Furnace Area Oily Wastewater Pump | 0 | 2019-05-08 | CAN | OL1-2G30-5614 | PE | 2019-05-09 | 036909C-JVD-TRN-01631 | 036909C-JVD-TRN-01631 | IFR | 2019-05-24 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01631 |  | 2019-05-10 | 2
036909C-PO-036909C001P40 | Vendor s Acknowledgment of Purchase Order For Trays For Shop Assembled Large Columns – MR 0511-0001 Rev 0 | 0 | 2019-05-21 | IFI | OL1-2C51-0009 | PL | 2019-05-21 | 036909C-JVD-TRN-01707 | 036909C-JVD-TRN-01707 | IFI |  | 2019-05-30 | R1-No comments | TPSK-LSPA1-T-PL-01707 | 036909C-1000-MR-0511-0001_0 | 2019-05-23 | 3
036909C-1024-CN-0014-2409 | PSV-2415 Sizing Calculation | A | 2019-04-25 | IFR | OL1-2G23-2409 | PE | 2019-04-30 | 036909C-JVD-TRN-01530 | 036909C-JVD-TRN-01530 | IFR | 2019-05-15 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01530 |  | 2019-05-02 | 2
036909C-1024-CN-0014-2408 | PSV-2414 Sizing Calculation | A | 2019-04-23 | IFR | OL1-2G23-2408 | PE | 2019-04-26 | 036909C-JVD-TRN-01508 | 036909C-JVD-TRN-01508 | IFR | 2019-05-13 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01508 |  | 2019-04-29 | 2
036909C-PO-036909C001P7 | Vendor s Acknowledgment of Purchase Order For Trays For Columns – MR 0570-0001 Rev 0 | 0 | 2019-05-21 | IFI | OL1-2C51-0007 | PL | 2019-05-21 | 036909C-JVD-TRN-01707 | 036909C-JVD-TRN-01707 | IFI |  | 2019-05-30 | R1-No comments | TPSK-LSPA1-T-PL-01707 | 036909C-1000-MR-0570-0001_0 | 2019-05-23 | 3
036909C-1000-NM-0003-1010 | Air & Nitrogen Balances | 0 | 2019-05-07 | IFI | OL1-2G62-1010 | PE | 2019-05-10 | 036909C-JVD-TRN-01644 | 036909C-JVD-TRN-01644 | IFI |  | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01644 |  | 2019-05-13 | 3
036909C-1023-CN-0014-2301 | PSV-2301 Sizing Calculation | A | 2019-05-01 | IFR | OL1-2G23-2301 | PE | 2019-05-28 | 036909C-JVD-TRN-01759 | 036909C-JVD-TRN-01759 | IFR | 2019-06-12 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01759 |  | 2019-05-29 | 2
036909C-1021-SP-0840-2139 | Mechanical Equipment Datasheet - Process Water Coalescer Prefilters | A | 2019-05-09 | IFQ | OL1-2M03-2139 | ME | 2019-05-10 | 036909C-JVD-TRN-01641 | 036909C-JVD-TRN-01641 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-ME-01641 |  | 2019-05-13 | 2
036909C-1023-SP-0932-2327 | Mechanical Equipment Datasheet - Skim Oil Pump | A | 2019-04-26 | IFQ | OL1-2M03-2327 | ME | 2019-04-30 | 036909C-JVD-TRN-01524 | 036909C-JVD-TRN-01524 | IFR | 2019-05-15 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-ME-01524 |  | 2019-05-02 | 2
036909C-1000-MR-1800-0001 | Material Requisition For Steel Structures | A | 2019-03-04 | IFQ | OL1-2C12-000001 | PL | 2019-03-08 | 036909C-JVD-TRN-01010 | 036909C-JVD-TRN-01010 | IFR | 2019-03-08 | 2019-05-07 | R1-No comments | TPSK-LSPA1-T-PL-1010 |  | 2019-03-11 | 2
036909C-1000-PP-259 | Drafting Procedure For 2D Drawings | 0 | 2019-04-12 | IMP | OL1-2R07-0023 | ME | 2019-04-17 | 036909C-JVD-TRN-01386 | 036909C-JVD-TRN-01386 | IFR | 2019-05-02 | 2019-05-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01386 |  | 2019-04-18 | 2
036909C-102C-CN-1733-0044 | Calculation Note For Foundation Of 10-D-5400 | A | 2019-04-24 | IFR | OL1-2K13-0288 | CV | 2019-04-30 | 036909C-JVD-TRN-01521 | 036909C-JVD-TRN-01521, ROC-TPSK-CECO-T-00056 | IFA | 2019-05-15 | 2019-05-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01521 |  | 2019-05-02 | 1
036909C-102C-CN-1733-0027 | Calculation Note For Foundation Of 10-E-2765 | A | 2019-04-24 | IFR | OL1-2K13-0238 | CV | 2019-04-30 | 036909C-JVD-TRN-01521 | 036909C-JVD-TRN-01521, ROC-TPSK-CECO-T-00056 | IFA | 2019-05-15 | 2019-05-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01521 |  | 2019-05-02 | 1
036909C-102C-CN-1733-0040 | Calculation Note For Foundation Of 10-D-2705 | A | 2019-04-24 | IFR | OL1-2K13-0192 | CV | 2019-04-30 | 036909C-JVD-TRN-01521 | 036909C-JVD-TRN-01521, ROC-TPSK-CECO-T-00056 | IFA | 2019-05-15 | 2019-05-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01521 |  | 2019-05-02 | 1
036909C-102C-CN-1733-0021 | Calculation Note For Foundation Of 10-E-2705 | A | 2019-04-24 | IFR | OL1-2K13-0169 | CV | 2019-04-30 | 036909C-JVD-TRN-01521 | 036909C-JVD-TRN-01521, ROC-TPSK-CECO-T-00056 | IFA | 2019-05-15 | 2019-05-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01521 |  | 2019-05-02 | 1
036909C-102C-CN-1733-0046 | Calculation Note For Foundation Of 10-D-5112 | A | 2019-04-17 | IFR | OL1-2K13-0290 | CV | 2019-04-23 | 036909C-JVD-TRN-01456 | 036909C-JVD-TRN-01456, ROC-TPSK-CECO-T-00051 | IFA | 2019-05-08 | 2019-05-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01456 |  | 2019-04-24 | 1
036909C-102C-CN-1733-0045 | Calculation Note For Foundation Of 10-D-5114 | A | 2019-04-17 | IFR | OL1-2K13-0289 | CV | 2019-04-23 | 036909C-JVD-TRN-01456 | 036909C-JVD-TRN-01456, ROC-TPSK-CECO-T-00051 | IFA | 2019-05-08 | 2019-05-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01456 |  | 2019-04-24 | 1
036909C-102C-CN-1733-0032 | Calculation Note For Foundation Of 10-E-2701 | A | 2019-04-17 | IFR | OL1-2K13-0180 | CV | 2019-04-23 | 036909C-JVD-TRN-01456 | 036909C-JVD-TRN-01456, ROC-TPSK-CECO-T-00051 | IFA | 2019-05-08 | 2019-05-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01456 |  | 2019-04-24 | 1
036909C-105F-PFD-3410-0001 | Electrical Sub-F- And Far-F - HVAC Process Flow Diagram | A | 2019-04-19 | IFR | OL1-2H20-0010 | EE | 2019-04-23 | 036909C-JVD-TRN-01454 | 036909C-JVD-TRN-01454, ROC-TPSK-CECO-T-00050 | IFA | 2019-05-08 | 2019-05-17 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01454 |  | 2019-04-24 | 1
036909C-100S-PFD-3410-0001 | Electrical Sub-e- And Far-1-HVAC Process Flow Diagram | A | 2019-04-12 | IFR | OL1-2H20-0001 | EE | 2019-04-18 | 036909C-JVD-TRN-01416 | 036909C-JVD-TRN-01416, ROC-TPSK-CECO-T-00050 | IFA | 2019-05-03 | 2019-05-17 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01416 |  | 2019-04-19 | 1
036909C-105F-DW-3432-0001 | Electrical Sub-F- And Far-F - HVAC Layout | A | 2019-04-19 | IFR | OL1-2H21-0020 | EE | 2019-04-23 | 036909C-JVD-TRN-01453 | 036909C-JVD-TRN-01453, ROC-TPSK-CECO-T-00050 | IFA | 2019-05-08 | 2019-05-17 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01453 |  | 2019-04-24 | 1
036909C-100S-DW-3432-0001 | Electrical Sub-e- And Far-1-HVAC Layout | A | 2019-04-12 | IFR | OL1-2H21-0001 | EE | 2019-04-18 | 036909C-JVD-TRN-01417 | 036909C-JVD-TRN-01417, ROC-TPSK-CECO-T-00050 | IFA | 2019-05-03 | 2019-05-17 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01417 |  | 2019-04-19 | 1
036909C-100S-CN-3442-0001 | Electrical SUB-E And FAR-1 – HVAC Thermal Calculation | A | 2019-04-12 | IFR | OL1-2H10-0001 | EE | 2019-04-23 | 036909C-JVD-TRN-01442 | 036909C-JVD-TRN-01442, ROC-TPSK-CECO-T-00050 | IFA | 2019-05-08 | 2019-05-17 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01442 |  | 2019-04-24 | 1
036909C-105F-CN-3442-0001 | Electrical SUB-F & FAR-F – HVAC Thermal Calculation | A | 2019-04-19 | IFR | OL1-2H10-0005 | EE | 2019-04-23 | 036909C-JVD-TRN-01446 | 036909C-JVD-TRN-01446, ROC-TPSK-CECO-T-00050 | IFA | 2019-05-08 | 2019-05-17 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01446 |  | 2019-04-24 | 1
036909C-1055-SP-0810-5555 | Mechanical Equipment Data Sheet - LPG Vaporizer-Superhtr Cond Pot | A | 2019-01-15 | IFQ | OL1-2M03-5555 | ME | 2019-01-23 | 036909C-JVD-TRN-00709 | 036909C-JVD-TRN-00709, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-05 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00709 |  | 2019-01-23 | 2
036909C-1055-SP-0810-5555 | Mechanical Equipment Data Sheet - LPG Vaporizer- Superhtr Cond Pot | B | 2019-03-19 | IFQ | OL1-2M03-5555 | ME | 2019-03-28 | 036909C-JVD-TRN-01186 | 036909C-JVD-TRN-01186 | IFR | 2019-04-12 | 2019-05-02 | R1-No comments | TPSK-LSPA1-T-ME-01186 |  | 2019-03-29 | 2
036909C-1056-PID-0031-5621 | P&ID - Olefins Unit 10 - Wastewater - HP Flare Area Storm Water Collection | B | 2019-04-26 | IBD | OL1-2G43-5621 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-PO-036909C001P3 | Vendor s Acknowledgment of Purchase Order For Plate And Frame Heat Exchangers – MR 0661-0001 Rev 0 | 0 | 2019-05-07 | IFI | OL1-2C51-0006 | PL | 2019-05-08 | 036909C-JVD-TRN-01613 | 036909C-JVD-TRN-01613 | IFI |  | 2019-05-22 | R1-No comments | TPSK-LSPA1-T-PL-01613 | Transmittal TPSK-LSPA-1-PL-01167 withdrawn - Document updated with correct template 036909C-1000-MR-0661-0001_0 | 2019-05-09 | 3
036909C-PO-036909C001P9 | Vendor s Acknowledgment of Purchase Order For Deareator MR-0845-0001 | 0 | 2019-05-07 | IFI | OL1-2C51-0005 | PL | 2019-05-08 | 036909C-JVD-TRN-01613 | 036909C-JVD-TRN-01613 | IFI |  | 2019-05-22 | R1-No comments | TPSK-LSPA1-T-PL-01613 | Transmittal TPSK-LSPA-1-PL-01365 withdrawn - Document updated with correct template 036909C-1000-MR-0845-0001_0 | 2019-05-09 | 3
036909C-PO-036909C001P6 | Vendor s Acknowledgment of Purchase Order For Centrifugal Compressor Steam Turbine Driven Site Services | 0 | 2019-05-07 | IFI | OL1-2C51-0004 | PL | 2019-05-08 | 036909C-JVD-TRN-01613 | 036909C-JVD-TRN-01613 | IFI |  | 2019-05-22 | R1-No comments | TPSK-LSPA1-T-PL-01613 | Transmittal TPSK-LSPA-1-PL-01337 withdrawn - Document updated with correct template | 2019-05-09 | 3
036909C-PO-036909C001P5 | Vendor s Acknowledgment of Purchase Order For Steam Turbine Drive Centrifugal Compressor – MR 1011-0001 Rev 0 | 0 | 2019-05-07 | IFI | OL1-2C51-0003 | PL | 2019-05-08 | 036909C-JVD-TRN-01613 | 036909C-JVD-TRN-01613 | IFI |  | 2019-05-22 | R1-No comments | TPSK-LSPA1-T-PL-01613 | Transmittal TPSK-LSPA-1-PL-01336 withdravn - Document updated with correct template 036909C-1000-MR-1011-0001_0 | 2019-05-09 | 3
036909C-PO-036909C001P4 | Vendor s Acknowledgment of Purchase Order For Residue Gas Expander Recompressor – MR 1130-0001 Rev 0 | 0 | 2019-05-07 | IFI | OL1-2C51-0002 | PL | 2019-05-08 | 036909C-JVD-TRN-01613 | 036909C-JVD-TRN-01613 | IFI |  | 2019-05-22 | R1-No comments | TPSK-LSPA1-T-PL-01613 | Transmittal TPSK-LSPA-T-PL-01300 withdrawn - Document updated with correct template 036909C-1000-MR-1130-0001_0 | 2019-04-11 | 3
036909C-PO-036909C001P2 | Vendor s Acknowledgment of Purchase Order For Wieland Tubes -Sole Source - MR 0610-0001 Rev 0 | 0 | 2019-05-07 | IFI | OL1-2C51-0001 | PL | 2019-05-08 | 036909C-JVD-TRN-01613 | 036909C-JVD-TRN-01613 | IFI |  | 2019-05-22 | R1-No comments | TPSK-LSPA1-T-PL-01613 | Transmittal TPSK-LSPA-1-PL-01060 withdravn - Document updated with correct template 036909C-1000-MR-0610-0001_0 | 2019-05-09 | 3
036909C-1025-CN-0014-2507 | PSV-2524 Sizing Calculation | B | 2019-04-30 | IFR | OL1-2G23-2507 | PE | 2019-04-30 | 036909C-JVD-TRN-01530 | 036909C-JVD-TRN-01530 | IFR | 2019-05-15 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01530 |  | 2019-05-02 | 2
036909C-1024-CN-0014-2436 | PSV-2413 Sizing Calculation | A | 2019-04-24 | IFR | OL1-2G23-2436 | PE | 2019-04-30 | 036909C-JVD-TRN-01530 | 036909C-JVD-TRN-01530 | IFR | 2019-05-15 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01530 |  | 2019-05-02 | 2
036909C-1024-CN-0014-2418 | PSV-2429 Sizing Calculation | A | 2019-04-29 | IFR | OL1-2G23-2418 | PE | 2019-04-30 | 036909C-JVD-TRN-01530 | 036909C-JVD-TRN-01530 | IFR | 2019-05-15 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01530 |  | 2019-05-02 | 2
036909C-1023-CN-0014-2303 | PSV-2316 A-B Sizing Calculation | A | 2019-04-26 | IFR | OL1-2G23-2303 | PE | 2019-04-30 | 036909C-JVD-TRN-01530 | 036909C-JVD-TRN-01530 | IFR | 2019-05-15 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01530 |  | 2019-05-02 | 2
036909C-1022-CN-0014-2206 | PSV-2246 A-B Sizing Calculation | A | 2019-04-16 | IFR | OL1-2G23-2206 | PE | 2019-04-24 | 036909C-JVD-TRN-01475 | 036909C-JVD-TRN-01475 | IFR | 2019-05-09 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01475 |  | 2019-04-25 | 2
036909C-1024-CN-0014-2410 | PSV-2416 Sizing Calculation | A | 2019-04-24 | IFR | OL1-2G23-2410 | PE | 2019-04-26 | 036909C-JVD-TRN-01508 | 036909C-JVD-TRN-01508 | IFR | 2019-05-13 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-PE-01508 |  | 2019-04-29 | 2
036909C-1025-CN-0014-2519 | PSV-2551 Sizing Calculation | A | 2019-04-22 | IFR | OL1-2G23-2519 | PE | 2019-04-25 | 036909C-JVD-TRN-01488 | 036909C-JVD-TRN-01488 | IFR | 2019-05-10 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-PE-01488 |  | 2019-04-26 | 2
036909C-1025-CN-0014-2503 | PSV-2514 Sizing Calculation | A | 2019-04-22 | IFR | OL1-2G23-2503 | PE | 2019-04-25 | 036909C-JVD-TRN-01488 | 036909C-JVD-TRN-01488 | IFR | 2019-05-10 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-PE-01488 |  | 2019-04-26 | 2
036909C-1025-CN-0014-2501 | PSV-2504 Sizing Calculation | A | 2019-04-22 | IFR | OL1-2G23-2501 | PE | 2019-04-25 | 036909C-JVD-TRN-01488 | 036909C-JVD-TRN-01488 | IFR | 2019-05-10 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-PE-01488 |  | 2019-04-26 | 2
036909C-1024-CN-0014-2434 | PSV-2450 Sizing Calculation | A | 2019-04-17 | IFR | OL1-2G23-2434 | PE | 2019-04-25 | 036909C-JVD-TRN-01488 | 036909C-JVD-TRN-01488 | IFR | 2019-05-10 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-PE-01488 |  | 2019-04-26 | 2
036909C-1024-CN-0014-2412 | PSV-2419 Sizing Calculation | A | 2019-04-24 | IFR | OL1-2G23-2412 | PE | 2019-04-25 | 036909C-JVD-TRN-01488 | 036909C-JVD-TRN-01488 | IFR | 2019-05-10 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-PE-01488 |  | 2019-04-26 | 2
036909C-1019-CN-0014-1902 | PSV-1912 Sizing Calculation | A | 2019-04-23 | IFR | OL1-2G23-1902 | PE | 2019-04-25 | 036909C-JVD-TRN-01488 | 036909C-JVD-TRN-01488 | IFR | 2019-05-10 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-PE-01488 |  | 2019-04-26 | 2
036909C-1019-CN-0014-1901 | PSV-1911 Sizing Calculation | A | 2019-04-23 | IFR | OL1-2G23-1901 | PE | 2019-04-25 | 036909C-JVD-TRN-01488 | 036909C-JVD-TRN-01488 | IFR | 2019-05-10 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-PE-01488 |  | 2019-04-26 | 2
036909C-1028-CN-0014-2805 | PSV-2806 A-D Sizing Calculation | A | 2019-04-24 | IFR | OL1-2G23-2805 | PE | 2019-04-26 | 036909C-JVD-TRN-01508 | 036909C-JVD-TRN-01508 | IFR | 2019-05-13 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-PE-01508 |  | 2019-04-29 | 2
036909C-1028-CN-0014-2804 | PSV-2805 A-D Sizing Calculation | A | 2019-04-24 | IFR | OL1-2G23-2804 | PE | 2019-04-26 | 036909C-JVD-TRN-01508 | 036909C-JVD-TRN-01508 | IFR | 2019-05-13 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-PE-01508 |  | 2019-04-29 | 2
036909C-1028-CN-0014-2803 | PSV-2820 A-B Sizing Calculation | A | 2019-04-24 | IFR | OL1-2G23-2803 | PE | 2019-04-26 | 036909C-JVD-TRN-01508 | 036909C-JVD-TRN-01508 | IFR | 2019-05-13 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-PE-01508 |  | 2019-04-29 | 2
036909C-1028-CN-0014-2802 | PSV-2815 Sizing Calculation | A | 2019-04-24 | IFR | OL1-2G23-2802 | PE | 2019-04-26 | 036909C-JVD-TRN-01508 | 036909C-JVD-TRN-01508 | IFR | 2019-05-13 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-PE-01508 |  | 2019-04-29 | 2
036909C-1028-CN-0014-2801 | PSV-2810 A-C Sizing Calculation | A | 2019-04-24 | IFR | OL1-2G23-2801 | PE | 2019-04-26 | 036909C-JVD-TRN-01508 | 036909C-JVD-TRN-01508 | IFR | 2019-05-13 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-PE-01508 |  | 2019-04-29 | 2
036909C-102E-CN-1733-0016 | Calculation Note For Foundation of 10-E-2230A-B | A | 2019-04-11 | IFR | OL1-2K13-0058 | CV | 2019-04-16 | 036909C-JVD-TRN-01372 | 036909C-JVD-TRN-01372, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-18 | R1-No comments | TPSK-LSPA1-T-CV-01372 |  | 2019-04-17 | 1
036909C-1011-DW-0117-1581 | USC 36M Recycle Furnace Steel Breeching Sections and Details | A | 2019-04-08 | IFI | OL1-2K32-1581 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1011-DW-0117-1580 | USC 36M Recycle Furnace Steel Breeching Plan and Elevations | A | 2019-04-08 | IFI | OL1-2K32-1580 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1025-SP-0510-2540 | Mechanical Equipment Data Sheet - Demethanizer & Reflux Drum | 0 | 2019-04-24 | IFP | OL1-2M03-2540 | ME | 2019-04-25 | 036909C-JVD-TRN-01487 | 036909C-JVD-TRN-01487 | IFR | 2019-05-10 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-ME-01487 |  | 2019-04-26 | 2
036909C-1000-NM-0001-1012 | Heat & Material Balance Area 55 - Flare System | 0 | 2019-04-25 | IFI | OL1-2G44-1012 | PE | 2019-04-26 | 036909C-JVD-TRN-01492 | 036909C-JVD-TRN-01492 | IFI |  | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01492 |  | 2019-04-29 | 3
036909C-1028-SP-1546-2802 | Instrument Datasheet for Flow Element -Orifice- Area 28 | A | 2019-04-10 | IFQ | OL1-2I20-2822 | IE | 2019-04-23 | 036909C-JVD-TRN-01360 | 036909C-JVD-TRN-01360 | IFI |  | 2019-05-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-01360 |  | 2019-04-23 | 3
036909C-1010-CN-0014-1002 | PSV-1002 A-B Sizing Calculation | A | 2019-02-25 | IFR | OL1-2G23-1002 | PE | 2019-04-16 | 036909C-JVD-TRN-01380 | 036909C-JVD-TRN-01380 | IFR | 2019-05-01 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-01380 |  | 2019-04-17 | 2
036909C-1010-CN-0014-1003 | PSV-1003 Sizing Calculation | A | 2019-03-04 | IFR | OL1-2G23-1003 | PE | 2019-04-16 | 036909C-JVD-TRN-01380 | 036909C-JVD-TRN-01380 | IFR | 2019-05-01 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-01380 |  | 2019-04-17 | 2
036909C-1010-CN-0014-1004 | PSV-1004 A-B Sizing Calculation | A | 2019-03-06 | IFR | OL1-2G23-1004 | PE | 2019-04-16 | 036909C-JVD-TRN-01380 | 036909C-JVD-TRN-01380 | IFR | 2019-05-01 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-01380 |  | 2019-04-17 | 2
036909C-1010-CN-0014-1008 | PSV-1008 Sizing Calculation | A | 2019-03-11 | IFR | OL1-2G23-1008 | PE | 2019-04-16 | 036909C-JVD-TRN-01380 | 036909C-JVD-TRN-01380 | IFR | 2019-05-01 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-01380 |  | 2019-04-17 | 2
036909C-1010-CN-0014-1011 | PSV-1011 A-B Sizing Calculation | A | 2019-03-14 | IFR | OL1-2G23-1011 | PE | 2019-04-16 | 036909C-JVD-TRN-01380 | 036909C-JVD-TRN-01380 | IFR | 2019-05-01 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-01380 |  | 2019-04-17 | 2
036909C-1010-CN-0014-1016 | PSV-1016 Sizing Calculation | A | 2019-02-27 | IFR | OL1-2G23-1016 | PE | 2019-04-16 | 036909C-JVD-TRN-01380 | 036909C-JVD-TRN-01380 | IFR | 2019-05-01 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-01380 |  | 2019-04-17 | 2
036909C-102A-CN-1733-0028 | Calculation Note For Foundation Of 10-D-2735 | A | 2019-04-16 | IFR | OL1-2K13-0171 | CV | 2019-04-18 | 036909C-JVD-TRN-01415 | 036909C-JVD-TRN-01415, ROC-TPSK-CECO-T-00047 | IFA | 2019-05-03 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01415 |  | 2019-04-19 | 1
036909C-1012-CN-0015-1201 | Steam Drum and Superheater PSVs Sizing Calculation | B | 2019-04-25 | IFD | OL1-2G05-1201 | PE | 2019-04-26 | 036909C-JVD-TRN-01513 | 036909C-JVD-TRN-01513 | IFR | 2019-05-11 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-PE-01513 |  | 2019-04-29 | 2
036909C-101B-CN-1733-0009 | Calculation Note For Foundation Of 10-D-1912 | A | 2019-04-22 | IFR | OL1-2K13-0404 | CV | 2019-04-24 | 036909C-JVD-TRN-01469 | 036909C-JVD-TRN-01469, ROC-TPSK-CECO-T-00053 | IFA | 2019-05-09 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01469 |  | 2019-04-25 | 1
036909C-101B-CN-1733-0006 | Calculation Note for Foundation of 10-D-1910 | A | 2019-04-22 | IFR | OL1-2K13-0195 | CV | 2019-04-24 | 036909C-JVD-TRN-01469 | 036909C-JVD-TRN-01469, ROC-TPSK-CECO-T-00053 | IFA | 2019-05-09 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01469 |  | 2019-04-25 | 1
036909C-102C-CN-1733-0015 | Calculation Note For Foundation Of 10-E-2660 | A | 2019-04-17 | IFR | OL1-2K13-0143 | CV | 2019-04-24 | 036909C-JVD-TRN-01469 | 036909C-JVD-TRN-01469, ROC-TPSK-CECO-T-00053 | IFA | 2019-05-09 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01469 |  | 2019-04-25 | 1
036909C-102E-CN-1733-0038 | Calculation Note For Foundation Of 10-E-2460 | A | 2019-04-11 | IFR | OL1-2K13-0159 | CV | 2019-04-16 | 036909C-JVD-TRN-01372 | 036909C-JVD-TRN-01372, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-CV-01372 |  | 2019-04-17 | 1
036909C-102E-CN-1733-0048 | Calculation Note For Foundation Of 10-E-2442 | A | 2019-04-15 | IFR | OL1-2K13-0402 | CV | 2019-04-16 | 036909C-JVD-TRN-01372 | 036909C-JVD-TRN-01372, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-CV-01372 |  | 2019-04-17 | 1
036909C-102B-CN-1733-0035 | Calculation Note For Foundation Of 10-R-2620A | A | 2019-04-09 | IFR | OL1-2K13-0314 | CV | 2019-04-16 | 036909C-JVD-TRN-01372 | 036909C-JVD-TRN-01372, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-CV-01372 |  | 2019-04-17 | 1
036909C-102E-CN-1733-0037 | Calculation Note For Foundation Of 10-E-2465 | A | 2019-04-05 | IFR | OL1-2K13-0158 | CV | 2019-04-16 | 036909C-JVD-TRN-01372 | 036909C-JVD-TRN-01372, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-CV-01372 |  | 2019-04-17 | 1
036909C-102E-CN-1733-0036 | Calculation Note for Foundation of 10-E-2474 | A | 2019-04-11 | IFR | OL1-2K13-0157 | CV | 2019-04-16 | 036909C-JVD-TRN-01372 | 036909C-JVD-TRN-01372, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-CV-01372 |  | 2019-04-17 | 1
036909C-102B-CN-1733-0039 | Calculation Note For Foundation Of 10-D-1000 | A | 2019-04-09 | IFR | OL1-2K13-0153 | CV | 2019-04-16 | 036909C-JVD-TRN-01372 | 036909C-JVD-TRN-01372, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-CV-01372 |  | 2019-04-17 | 1
036909C-102B-CN-1733-0024 | Calculation Note For Foundation Of 10-T-2630 | A | 2019-04-09 | IFR | OL1-2K13-0147 | CV | 2019-04-16 | 036909C-JVD-TRN-01372 | 036909C-JVD-TRN-01372, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-CV-01372 |  | 2019-04-17 | 1
036909C-102E-CN-1733-0031 | Calculation Note for Foundation of 10-E-2305 | A | 2019-04-11 | IFR | OL1-2K13-0113 | CV | 2019-04-16 | 036909C-JVD-TRN-01372 | 036909C-JVD-TRN-01372, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-CV-01372 |  | 2019-04-17 | 1
036909C-102E-CN-1733-0025 | Calculation Note For Foundation of 10-E-2240A-B | A | 2019-04-15 | IFR | OL1-2K13-0070 | CV | 2019-04-16 | 036909C-JVD-TRN-01372 | 036909C-JVD-TRN-01372, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-CV-01372 |  | 2019-04-17 | 1
036909C-102E-CN-1733-0024 | Calculation Note For Foundation Of 10-E-2220AB | A | 2019-04-15 | IFR | OL1-2K13-0069 | CV | 2019-04-16 | 036909C-JVD-TRN-01372 | 036909C-JVD-TRN-01372, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-CV-01372 |  | 2019-04-17 | 1
036909C-102E-CN-1733-0023 | Calculation Note For Foundation Of 10-E-2210AB | A | 2019-04-11 | IFR | OL1-2K13-0068 | CV | 2019-04-16 | 036909C-JVD-TRN-01372 | 036909C-JVD-TRN-01372, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-CV-01372 |  | 2019-04-17 | 1
036909C-102E-CN-1733-0020 | Calculation Note For Foundation Of 10-E-2446 | A | 2019-04-11 | IFR | OL1-2K13-0063 | CV | 2019-04-16 | 036909C-JVD-TRN-01372 | 036909C-JVD-TRN-01372, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-CV-01372 |  | 2019-04-17 | 1
036909C-101A-DW-0051-0001 | Detail Plot Plan Zone 1A Furnaces | A | 2019-03-06 | IFR | OL1-2P06-0006 | MP | 2019-03-07 | 036909C-JVD-TRN-01003 | 036909C-JVD-TRN-01003, ROC-TPSK-CECO-T-00005 | IFA | 2019-03-22 | 2019-04-01 | R2-Comments as noted | TPSK-LSPA1-T-MP-01003 |  | 2019-03-08 | 1
036909C-1026-PDS-0900-2663 | Process Equipment Datasheet - 10-P-2660 A-B - Debutanizer Reflux - Product Pumps | D | 2019-04-15 | IFD | OL1-2G30-2663 | PE | 2019-04-16 | 036909C-JVD-TRN-01383 | 036909C-JVD-TRN-01383 | IFR | 2019-05-01 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-01383 |  | 2019-04-17 | 2
036909C-1021-PDS-0900-2126 | Process Equipment Datasheet - 10-P-2126 A-B - Distillate Stripper Bottom Pumps | C | 2019-04-15 | IFD | OL1-2G30-2126 | PE | 2019-04-16 | 036909C-JVD-TRN-01383 | 036909C-JVD-TRN-01383 | IFR | 2019-05-01 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-01383 |  | 2019-04-17 | 2
036909C-1025-CN-0014-2522 | PSV-2560 Sizing Calculation | A | 2019-04-01 | IFR | OL1-2G23-2522 | PE | 2019-04-17 | 036909C-JVD-TRN-01395 | 036909C-JVD-TRN-01395 | IFR | 2019-05-02 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-01395 |  | 2019-04-18 | 2
036909C-1025-CN-0014-2520 | PSV-2555 Sizing Calculation | A | 2019-03-19 | IFR | OL1-2G23-2520 | PE | 2019-04-17 | 036909C-JVD-TRN-01395 | 036909C-JVD-TRN-01395 | IFR | 2019-05-02 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-01395 |  | 2019-04-18 | 2
036909C-1025-CN-0014-2524 | PSV-2556 A-B Sizing Calculation | A | 2019-03-20 | IFR | OL1-2G23-2524 | PE | 2019-04-17 | 036909C-JVD-TRN-01395 | 036909C-JVD-TRN-01395 | IFR | 2019-05-02 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-01395 |  | 2019-04-18 | 2
036909C-1025-CN-0014-2513 | PSV-2540 A-B Sizing Calculation | A | 2019-03-27 | IFR | OL1-2G23-2513 | PE | 2019-04-17 | 036909C-JVD-TRN-01395 | 036909C-JVD-TRN-01395 | IFR | 2019-05-02 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-01395 |  | 2019-04-18 | 2
036909C-1025-CN-0014-2511 | PSV-2535 Sizing Calculation | A | 2019-03-27 | IFR | OL1-2G23-2511 | PE | 2019-04-17 | 036909C-JVD-TRN-01395 | 036909C-JVD-TRN-01395 | IFR | 2019-05-02 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-01395 |  | 2019-04-18 | 2
036909C-1025-CN-0014-2517 | PSV-2548 A-B Sizing Calculation | A | 2019-03-27 | IFR | OL1-2G23-2517 | PE | 2019-04-17 | 036909C-JVD-TRN-01395 | 036909C-JVD-TRN-01395 | IFR | 2019-05-02 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-01395 |  | 2019-04-18 | 2
036909C-1025-CN-0014-2509 | PSV-2530 Sizing Calculation | A | 2019-03-14 | IFR | OL1-2G23-2509 | PE | 2019-04-17 | 036909C-JVD-TRN-01395 | 036909C-JVD-TRN-01395 | IFR | 2019-05-02 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-01395 |  | 2019-04-18 | 2
036909C-1025-CN-0014-2510 | PSV-2531 Sizing Calculation | A | 2019-03-27 | IFR | OL1-2G23-2510 | PE | 2019-04-16 | 036909C-JVD-TRN-01382 | 036909C-JVD-TRN-01382 | IFR | 2019-05-01 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-01382 |  | 2019-04-17 | 2
036909C-1025-CN-0014-2508 | PSV-2525 Sizing Calculation | A | 2019-03-18 | IFR | OL1-2G23-2508 | PE | 2019-04-16 | 036909C-JVD-TRN-01382 | 036909C-JVD-TRN-01382 | IFR | 2019-05-01 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-01382 |  | 2019-04-17 | 2
036909C-1025-CN-0014-2506 | PSV-2522 Sizing Calculation | A | 2019-03-08 | IFR | OL1-2G23-2506 | PE | 2019-04-16 | 036909C-JVD-TRN-01382 | 036909C-JVD-TRN-01382 | IFR | 2019-05-01 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-01382 |  | 2019-04-17 | 2
036909C-1024-CN-0014-2417 | PSV-2428 A-B Sizing Calculation | A | 2019-04-11 | IFR | OL1-2G23-2417 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2430 | PSV-2446 Sizing Calculation | A | 2019-03-28 | IFR | OL1-2G23-2430 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2427 | PSV-2443 Sizing Calculation | A | 2019-03-28 | IFR | OL1-2G23-2427 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2435 | PSV-2440 Sizing Calculation | A | 2019-04-02 | IFR | OL1-2G23-2435 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2433 | PSV-2449 Sizing Calculation | A | 2019-03-27 | IFR | OL1-2G23-2433 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2432 | PSV-2448 Sizing Calculation | A | 2019-04-01 | IFR | OL1-2G23-2432 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2431 | PSV-2447 Sizing Calculation | A | 2019-03-27 | IFR | OL1-2G23-2431 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2429 | PSV-2445 Sizing Calculation | A | 2019-03-27 | IFR | OL1-2G23-2429 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2428 | PSV-2444 Sizing Calculation | A | 2019-04-02 | IFR | OL1-2G23-2428 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2424 | PSV-2437 Sizing Calculation | A | 2019-04-01 | IFR | OL1-2G23-2424 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2423 | PSV-2436 Sizing Calculation | A | 2019-04-01 | IFR | OL1-2G23-2423 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2422 | PSV-2435 A-D Sizing Calculation | A | 2019-03-28 | IFR | OL1-2G23-2422 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2420 | PSV-2432 A-B Sizing Calculation | A | 2019-03-27 | IFR | OL1-2G23-2420 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2419 | PSV-2431 A-B Sizing Calculation | A | 2019-04-15 | IFR | OL1-2G23-2419 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2416 | PSV-2426 A-B Sizing Calculation | A | 2019-03-25 | IFR | OL1-2G23-2416 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2415 | PSV-2425 A-B Sizing Calculation | A | 2019-03-18 | IFR | OL1-2G23-2415 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2414 | PSV-2423 A-B-C Sizing Calculation | A | 2019-04-11 | IFR | OL1-2G23-2414 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1024-CN-0014-2413 | PSV-2422 Sizing Calculation | A | 2019-03-15 | IFR | OL1-2G23-2413 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1023-CN-0014-2307 | PSV-2335 A-B Sizing Calculation | A | 2019-03-25 | IFR | OL1-2G23-2307 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1023-CN-0014-2306 | PSV-2332 A-B Sizing Calculation | A | 2019-03-21 | IFR | OL1-2G23-2306 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1023-CN-0014-2305 | PSV-2327 Sizing Calculation | A | 2019-03-21 | IFR | OL1-2G23-2305 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1023-CN-0014-2304 | PSV-2322 A-B Sizing Calculation | A | 2019-03-21 | IFR | OL1-2G23-2304 | PE | 2019-04-15 | 036909C-JVD-TRN-01364 | 036909C-JVD-TRN-01364 | IFR | 2019-04-30 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-001364 |  | 2019-04-16 | 2
036909C-1029-NM-0022-2901 | Line Designation Table - Ethylene Auxiliaries | A | 2019-05-07 | IBD | OL1-2P91-2901 | MP | 2019-05-08 | 036909C-JVD-TRN-01620 | 036909C-JVD-TRN-01620, ROC-TPSK-CECO-T-00061 | IFR | 2019-05-23 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-MP-01620 |  | 2019-05-09 | 2
036909C-1059-NM-0022-5901 | Line Designation Table - Supporting Utilities Auxiliaries | A | 2019-05-08 | IBD | OL1-2P91-5901 | MP | 2019-05-08 | 036909C-JVD-TRN-01620 | 036909C-JVD-TRN-01620, ROC-TPSK-CECO-T-00063 | IFR | 2019-05-23 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP-01620 |  | 2019-05-09 | 2
036909C-1050-NM-0022-5001 | Line Designation Table - Water System - Treated - Potable - Demin | A | 2019-05-08 | IBD | OL1-2P91-5001 | MP | 2019-05-08 | 036909C-JVD-TRN-01620 | 036909C-JVD-TRN-01620, ROC-TPSK-CECO-T-00061 | IFR | 2019-05-23 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP-01620 |  | 2019-05-09 | 2
036909C-1056-NM-0022-5601 | Line Designation Table - Wastewater | A | 2019-05-13 | IBD | OL1-2P91-5601 | MP | 2019-05-13 | 036909C-JVD-TRN-01656 | 036909C-JVD-TRN-01656, ROC-TPSK-CECO-T-00071 | IFR | 2019-05-28 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP -01656 |  | 2019-05-14 | 2
036909C-1053-NM-0022-5301 | Line Designation Table - Cooling Water | A | 2019-05-13 | IBD | OL1-2P91-5301 | MP | 2019-05-13 | 036909C-JVD-TRN-01656 | 036909C-JVD-TRN-01656 , ROC-TPSK-CECO-T-00071 | IFR | 2019-05-28 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP -01656 |  | 2019-05-14 | 2
036909C-1000-MR-1324-0001 | Material Requisition For Stainless Steel Seamless Pipe | A | 2019-04-17 | IFQ | OL1-2C14-230001 | PL | 2019-05-02 | 036909C-JVD-TRN-01553 | 036909C-JVD-TRN-01553 | IFR | 2019-05-17 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01553 |  | 2019-05-03 | 2
036909C-1024-SP-0510-2450 | Mechanical Equipment Data Sheet - LP Depropanizer | D | 2019-02-15 | IFQ | OL1-2M03-2450 | ME | 2019-02-19 | 036909C-JVD-TRN-00884 | 036909C-JVD-TRN-00884, ROC-TPSK-CECO-T-00014 | IFR | 2019-03-05 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00884 |  | 2019-02-19 | 2
036909C-102E-CN-1733-0049 | Calculation Note For Foundation Of 10-E-2405 | A | 2019-05-06 | IFR | OL1-2K13-0403 | CV | 2019-05-14 | 036909C-JVD-TRN-01661 | 036909C-JVD-TRN-01661, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 |  | Transmitted | TPSK-LSPA1-T-CV-01661 | Correct document class modified on document - Document replaced in Aconex and PDB on 27-05-2019 | 2019-05-15 | 1
036909C-1012-PID-0021-1250 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Flue Gas & Shutdown Logic | C | 2019-05-23 | IDD1 | OL1-2G43-1250 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1012-PID-0021-1229 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Drum-Sle And TLX Risers | C | 2019-05-23 | IDD1 | OL1-2G43-1229 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1012-PID-0021-1227 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Sle Drain Header | C | 2019-05-23 | IDD1 | OL1-2G43-1227 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1012-PID-0021-1228 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - SHP Steam Drum | C | 2019-05-23 | IDD1 | OL1-2G43-1228 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1012-PID-0021-1220 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 5 | C | 2019-05-23 | IDD1 | OL1-2G43-1220 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1012-PID-0021-1218 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 3 | C | 2019-05-23 | IDD1 | OL1-2G43-1218 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1012-PID-0021-1216 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 1 | C | 2019-05-23 | IDD1 | OL1-2G43-1216 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1012-PID-0021-1217 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 2 | C | 2019-05-23 | IDD1 | OL1-2G43-1217 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1012-PID-0021-1215 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Convection Section | C | 2019-05-23 | IDD1 | OL1-2G43-1215 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1012-PID-0021-1219 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 4 | C | 2019-05-23 | IDD1 | OL1-2G43-1219 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1012-PID-0021-1225 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - TLX Exchanger | C | 2019-05-23 | IDD1 | OL1-2G43-1225 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1012-PID-0021-1221 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 6 | C | 2019-05-23 | IDD1 | OL1-2G43-1221 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1011-PID-0021-1140 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Burners | C | 2019-05-23 | IDD1 | OL1-2G43-1140 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1011-PID-0021-1127 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - USX Drain Header | C | 2019-05-23 | IDD1 | OL1-2G43-1127 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1011-PID-0021-1131 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Coils | C | 2019-05-23 | IDD1 | OL1-2G43-1131 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1011-PID-0021-1120 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 5 | C | 2019-05-23 | IDD1 | OL1-2G43-1120 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1011-PID-0021-1117 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 2 | C | 2019-05-23 | IDD1 | OL1-2G43-1117 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1011-PID-0021-1118 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 3 | C | 2019-05-23 | IDD1 | OL1-2G43-1118 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1011-PID-0021-1150 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Flue Gas & Shutdown Logic | C | 2019-05-23 | IDD1 | OL1-2G43-1150 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1011-PID-0021-1119 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 4 | C | 2019-05-23 | IDD1 | OL1-2G43-1119 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1011-PID-0021-1115 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Convection Section | C | 2019-05-23 | IDD1 | OL1-2G43-1115 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1011-PID-0021-1121 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 6 | C | 2019-05-23 | IDD1 | OL1-2G43-1121 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1011-PID-0021-1129 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Drum-USX And TLX-1 Risers | C | 2019-05-23 | IDD1 | OL1-2G43-1129 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1011-PID-0021-1125 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - TLX Quench Exchangers | C | 2019-05-23 | IDD1 | OL1-2G43-1125 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1011-PID-0021-1145 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoking Effluent | C | 2019-05-23 | IDD1 | OL1-2G43-1145 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1011-PID-0021-1128 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - SHP Steam Drum | C | 2019-05-23 | IDD1 | OL1-2G43-1128 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1011-PID-0021-1116 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 1 | C | 2019-05-23 | IDD1 | OL1-2G43-1116 | PE | 2019-05-24 | 036909C-JVD-TRN-01742 | 036909C-JVD-TRN-01742 | IFR | 2019-06-08 |  | Transmitted | TPSK-LSPA1-T-PE-01742 |  | 2019-05-27 | 2
036909C-1000-MR-2630-0008 | Material Requisition For Support Balls | A | 2019-04-03 | IFQ | OL1-2C18-268000 | PL | 2019-04-10 | 036909C-JVD-TRN-01297 | 036909C-JVD-TRN-01297 | IFR | 2019-04-25 |  | Transmitted | TPSK-LSPA1-T-PL-01297 |  | 2019-04-11 | 2
036909C-1000-MR-2630-0007 | Material Requisition For Hg Sieves | A | 2019-04-03 | IFQ | OL1-2C18-267000 | PL | 2019-04-10 | 036909C-JVD-TRN-01296 | 036909C-JVD-TRN-01296 | IFR | 2019-04-25 |  | Transmitted | TPSK-LSPA1-T-PL-01296 |  | 2019-04-11 | 2
036909C-1000-MR-2630-0006 | Material Requisition For Adsorbents | A | 2019-04-03 | IFQ | OL1-2C18-266000 | PL | 2019-04-10 | 036909C-JVD-TRN-01299 | 036909C-JVD-TRN-01299 | IFR | 2019-04-25 |  | Transmitted | TPSK-LSPA1-T-PL-01299 |  | 2019-04-11 | 2
036909C-1000-MR-2630-0004 | Material Requisition For Adsorbents | A | 2019-04-03 | IFQ | OL1-2C18-264000 | PL | 2019-04-10 | 036909C-JVD-TRN-01295 | 036909C-JVD-TRN-01295 | IFR | 2019-04-25 |  | Transmitted | TPSK-LSPA1-T-PL-01295 |  | 2019-04-11 | 2
036909C-1011-PID-0021-1140 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Burners | B | 2019-02-12 | IBD | OL1-2G43-1140 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1131 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Coils | B | 2019-02-12 | IBD | OL1-2G43-1131 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1129 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Drum-USX And TLX-1 Risers | B | 2019-02-12 | IBD | OL1-2G43-1129 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1128 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Shp Steam Drum | B | 2019-02-12 | IBD | OL1-2G43-1128 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1127 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - USX Drain Header | B | 2019-02-12 | IBD | OL1-2G43-1127 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1125 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - TLX Quench Exchangers | B | 2019-02-12 | IBD | OL1-2G43-1125 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1121 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 6 | B | 2019-02-12 | IBD | OL1-2G43-1121 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1120 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 5 | B | 2019-02-12 | IBD | OL1-2G43-1120 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1119 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 4 | B | 2019-02-12 | IBD | OL1-2G43-1119 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1118 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 3 | B | 2019-02-12 | IBD | OL1-2G43-1118 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1117 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 2 | B | 2019-02-12 | IBD | OL1-2G43-1117 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1116 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 1 | B | 2019-02-12 | IBD | OL1-2G43-1116 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1150 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Flue Gas & Shutdown Logic | B | 2019-02-12 | IBD | OL1-2G43-1150 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1215 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Convection Section | B | 2019-02-12 | IBD | OL1-2G43-1215 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1216 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 1 | B | 2019-02-12 | IBD | OL1-2G43-1216 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1217 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 2 | B | 2019-02-12 | IBD | OL1-2G43-1217 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1218 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 3 | B | 2019-02-12 | IBD | OL1-2G43-1218. | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1219 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 4 | B | 2019-02-12 | IBD | OL1-2G43-1219 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1220 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 5 | B | 2019-02-12 | IBD | OL1-2G43-1220 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1221 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 6 | B | 2019-02-12 | IBD | OL1-2G43-1221 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1250 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Flue Gas & Shutdown Logic | B | 2019-02-12 | IBD | OL1-2G43-1250 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1115 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Convection Section | B | 2019-02-12 | IBD | OL1-2G43-1115 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1229 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Drum-SLE And TLX Risers | B | 2019-02-12 | IBD | OL1-2G43-1229 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1227 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - SLE Drain Header | B | 2019-02-12 | IBD | OL1-2G43-1227 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1225 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - TLX Exchanger | B | 2019-02-12 | IBD | OL1-2G43-1225 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1228 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Shp Steam Drum | B | 2019-02-12 | IBD | OL1-2G43-1228 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1011-PID-0021-1145 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoking Effluent | B | 2019-02-12 | IBD | OL1-2G43-1145 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00010 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1231 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Coils | B | 2019-02-12 | IBD | OL1-2G43-1231 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1240 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Burners | B | 2019-02-12 | IBD | OL1-2G43-1240 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1012-PID-0021-1245 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Flue Gas | B | 2019-02-12 | IBD | OL1-2G43-1245 | PE | 2019-02-13 | 036909C-JVD-TRN-00850 | 036909C-JVD-TRN-00850, ROC-TPSK-CECO-T-00009 | IFR | 2019-02-27 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00850 |  | 2019-02-13 | 2
036909C-1027-PDS-0900-2704 | Process Equipment Datasheet - 10-P-2705 A-B - GHU-1 Recycle Pump | A | 2019-02-11 | IFR | OL1-2G30-2704 | PE | 2019-02-11 | 036909C-JVD-TRN-00834 | 036909C-JVD-TRN-00834 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00834 |  | 2019-02-11 | 2
036909C-1027-PDS-0900-2704 | Process Equipment Datasheet - 10-P-2705 A-B - GHU-1 Recycle Pump | B | 2019-03-08 | IFD | OL1-2G30-2704 | PE | 2019-03-11 | 036909C-JVD-TRN-01025 | 036909C-JVD-TRN-01025 | IFR | 2019-03-26 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-PE-01025 |  | 2019-03-12 | 2
036909C-1027-PDS-0900-2764 | Process Equipment Datasheet - 10-P-2760 A-C - C4-C5 Hydrog Recycle Pump | A | 2019-02-01 | IFR | OL1-2G30-2764 | PE | 2019-02-01 | 036909C-JVD-TRN-00788 | 036909C-JVD-TRN-00788 | IFR | 2019-02-15 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00788 |  | 2019-02-04 | 2
036909C-1026-PDS-0900-2668 | Process Equipment Datasheet - 10-P-2666 A-B - C5 - Pygas Pumps | B | 2019-03-08 | IFD | OL1-2G30-2668 | PE | 2019-03-11 | 036909C-JVD-TRN-01025 | 036909C-JVD-TRN-01025 | IFR | 2019-03-26 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-PE-01025 |  | 2019-03-12 | 2
036909C-1026-PDS-0900-2668 | Process Equipment Datasheet - 10-P-2666 A-B - C5 - Pygas Pumps | C | 2019-04-11 | IFD | OL1-2G30-2668 | PE | 2019-04-12 | 036909C-JVD-TRN-01339 | 036909C-JVD-TRN-01339 | IFR | 2019-04-29 |  | Transmitted | TPSK-LSPA1-T-PE-01339 |  | 2019-04-15 | 2
036909C-1026-PDS-0900-2668 | Process Equipment Datasheet - 10-P-2666 A-B - C5 - Pygas Pumps | A | 2019-02-08 | IFR | OL1-2G30-2668 | PE | 2019-02-11 | 036909C-JVD-TRN-00834 | 036909C-JVD-TRN-00834 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00834 |  | 2019-02-11 | 2
036909C-1026-PDS-0900-2623 | Process Equipment Data Sheet - 10-P-2620 - C3 Hydrog Recycle Pumps | B | 2019-02-28 | IFD | OL1-2G30-2623 | PE | 2019-03-01 | 036909C-JVD-TRN-00963 | 036909C-JVD-TRN-00963 | IFR | 2019-03-16 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-PE-00963 |  | 2019-03-04 | 2
036909C-1026-PDS-0900-2623 | Process Equipment Data Sheet - 10-P-2620 - C3 Hydrog Recycle Pumps | A | 2019-01-04 | IFR | OL1-2G30-2623 | PE | 2019-01-07 | 036909C-JVD-TRN-00587 | 036909C-JVD-TRN-00587 | IFR | 2019-01-21 | 2019-01-31 | R1-No comments | TPSK-LSPA1-T-PE-00587 |  | 2019-01-07 | 2
036909C-1028-SP-1542-2803 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 28 | A | 2019-04-11 | IFQ | OL1-2I20-2806 | IE | 2019-04-23 | 036909C-JVD-TRN-01338 | 036909C-JVD-TRN-01338, ROC-TPSK-CECO-T-00056 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-01338 |  | 2019-04-23 | 3
036909C-1051-NM-0022-5101 | Line Designation Table - BFW - Steam - Steam Condensate System | A | 2019-05-13 | IBD | OL1-2P91-5101 | MP | 2019-05-13 | 036909C-JVD-TRN-01656 | 036909C-JVD-TRN-01656, ROC-TPSK-CECO-T-00071 | IFR | 2019-05-28 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP -01656 |  | 2019-05-14 | 2
036909C-1027-NM-0022-2701 | Line Designation Table - GHU & C4-C5 Hydrog | A | 2019-05-13 | IBD | OL1-2P91-2701 | MP | 2019-05-13 | 036909C-JVD-TRN-01656 | 036909C-JVD-TRN-01656, ROC-TPSK-CECO-T-00071 | IFR | 2019-05-28 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP -01656 |  | 2019-05-14 | 2
036909C-1055-NM-0022-5501 | Line Designation Table - Vent Gas and Flare System | A | 2019-05-10 | IBD | OL1-2P91-5501 | MP | 2019-05-13 | 036909C-JVD-TRN-01648 | 036909C-JVD-TRN-01648, ROC-TPSK-CECO-T-00071 | IFR | 2019-05-28 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP -01648 |  | 2019-05-14 | 2
036909C-1026-NM-0022-2601 | Line Designation Table - Hot Fractionation | A | 2019-05-13 | IBD | OL1-2P91-2601 | MP | 2019-05-13 | 036909C-JVD-TRN-01651 | 036909C-JVD-TRN-01651, ROC-TPSK-CECO-T-00071 | IFR | 2019-05-28 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP-01651 |  | 2019-05-14 | 2
036909C-1054-NM-0022-5401 | Line Designation Table - Plant Air - Instrument Air - Nitrogen | A | 2019-05-09 | IBD | OL1-2P91-5401 | MP | 2019-05-09 | 036909C-JVD-TRN-01627 | 036909C-JVD-TRN-01627, ROC-TPSK-CECO-T-00063 | IFR | 2019-05-24 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP-01627 |  | 2019-05-10 | 2
036909C-1052-NM-0022-5201 | Line Designation Table - Fuel System | A | 2019-05-09 | IBD | OL1-2P91-5201 | MP | 2019-05-09 | 036909C-JVD-TRN-01627 | 036909C-JVD-TRN-01627, ROC-TPSK-CECO-T-00063 | IFR | 2019-05-24 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP-01627 |  | 2019-05-10 | 2
036909C-1010-NM-0022-1001 | Line Designation Table - Feed Preparation and Furnaces | A | 2019-04-30 | IBD | OL1-2P91-1001 | MP | 2019-05-01 | 036909C-JVD-TRN-01541 | 036909C-JVD-TRN-01541, ROC-TPSK-CECO-T-00056 | IFR | 2019-05-16 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP-01541 |  | 2019-05-02 | 2
036909C-1028-NM-0022-2801 | Line Designation Table - Refrigeration System | A | 2019-04-25 | IBD | OL1-2P91-2801 | MP | 2019-04-26 | 036909C-JVD-TRN-01497 | 036909C-JVD-TRN-01497, ROC-TPSK-CECO-T-00054 | IFR | 2019-05-13 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP-01497 |  | 2019-04-29 | 2
036909C-1021-NM-0022-2101 | Line Designation Table - Quench Water - Dilution Steam | A | 2019-04-25 | IBD | OL1-2P91-2101 | MP | 2019-04-26 | 036909C-JVD-TRN-01497 | 036909C-JVD-TRN-01497, ROC-TPSK-CECO-T-00054 | IFR | 2019-05-13 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP-01497 |  | 2019-04-29 | 2
036909C-1024-NM-0022-2401 | Line Designation Table - Dehydration - Regen -Deprop - C2 Hydrog | A | 2019-04-30 | IBD | OL1-2P91-2401 | MP | 2019-04-30 | 036909C-JVD-TRN-01531 | 036909C-JVD-TRN-01531, ROC-TPSK-CECO-T-00056 | IFR | 2019-05-15 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP-01531 |  | 2019-05-02 | 2
036909C-1020-NM-0022-2001 | Line Designation Table - Quench Oil | A | 2019-04-22 | IBD | OL1-2P91-2001 | MP | 2019-04-23 | 036909C-JVD-TRN-01450 | 036909C-JVD-TRN-01450, ROC-TPSK-CECO-T-00051 | IFR | 2019-05-08 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP-01450 |  | 2019-04-24 | 2
036909C-1023-NM-0022-2301 | Line Designation Table - Caustic and Spent Caustic Treatment | A | 2019-04-15 | IBD | OL1-2P91-2301 | MP | 2019-04-16 | 036909C-JVD-TRN-01375 | 036909C-JVD-TRN-01375, ROC-TPSK-CECO-T-00045 | IFR | 2019-05-01 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP -01375 |  | 2019-04-17 | 2
036909C-1022-NM-0022-2201 | Line Designation Table - Cracked Gas Compression | A | 2019-04-15 | IBD | OL1-2P91-2201 | MP | 2019-04-16 | 036909C-JVD-TRN-01375 | 036909C-JVD-TRN-01375, ROC-TPSK-CECO-T-00045 | IFR | 2019-05-01 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-MP -01375 |  | 2019-04-17 | 2
036909C-1019-NM-0022-1901 | Line Designation Table - Furnace Auxiliaries | A | 2019-04-15 | IBD | OL1-2P91-1901 | MP | 2019-04-16 | 036909C-JVD-TRN-01375 | 036909C-JVD-TRN-01375, ROC-TPSK-CECO-T-00053 | IFR | 2019-05-01 | 2019-05-24 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-MP -01375 |  | 2019-04-17 | 2
036909C-1025-NM-0022-2501 | Line Designation Table - Cold Fractionation | A | 2019-04-24 | IBD | OL1-2P91-2501 | MP | 2019-04-24 | 036909C-JVD-TRN-01466 | 036909C-JVD-TRN-01466, ROC-TPSK-CECO-T-00053 | IFR | 2019-05-09 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-MP-01466 |  | 2019-04-25 | 2
036909C-1028-CN-0014-2831 | PSV-2870 Sizing Calculation | A | 2019-05-16 | IFR | OL1-2G23-2831 | PE | 2019-05-20 | 036909C-JVD-TRN-01698 | 036909C-JVD-TRN-01698 | IFR | 2019-06-04 |  | Transmitted | TPSK-LSPA1-T-PE-01698 |  | 2019-05-21 | 2
036909C-1028-CN-0014-2826 | PSV-2857 Sizing Calculation | A | 2019-05-16 | IFR | OL1-2G23-2826 | PE | 2019-05-20 | 036909C-JVD-TRN-01698 | 036909C-JVD-TRN-01698 | IFR | 2019-06-04 |  | Transmitted | TPSK-LSPA1-T-PE-01698 |  | 2019-05-21 | 2
036909C-1028-CN-0014-2830 | PSV-2867 Sizing Calculation | A | 2019-05-16 | IFR | OL1-2G23-2830 | PE | 2019-05-20 | 036909C-JVD-TRN-01698 | 036909C-JVD-TRN-01698 | IFR | 2019-06-04 |  | Transmitted | TPSK-LSPA1-T-PE-01698 |  | 2019-05-21 | 2
036909C-1028-CN-0014-2828 | PSV-2861 Sizing Calculation | A | 2019-05-16 | IFR | OL1-2G23-2828 | PE | 2019-05-20 | 036909C-JVD-TRN-01698 | 036909C-JVD-TRN-01698 | IFR | 2019-06-04 |  | Transmitted | TPSK-LSPA1-T-PE-01698 |  | 2019-05-21 | 2
036909C-1028-CN-0014-2829 | PSV-2864 Sizing Calculation | A | 2019-05-16 | IFR | OL1-2G23-2829 | PE | 2019-05-20 | 036909C-JVD-TRN-01698 | 036909C-JVD-TRN-01698 | IFR | 2019-06-04 |  | Transmitted | TPSK-LSPA1-T-PE-01698 |  | 2019-05-21 | 2
036909C-1028-CN-0014-2827 | PSV-2858 Sizing Calculation | A | 2019-05-16 | IFR | OL1-2G23-2827 | PE | 2019-05-20 | 036909C-JVD-TRN-01698 | 036909C-JVD-TRN-01698 | IFR | 2019-06-04 |  | Transmitted | TPSK-LSPA1-T-PE-01698 |  | 2019-05-21 | 2
036909C-1023-CN-0014-2303 | PSV-2316 A-B Sizing Calculations | B | 2019-05-15 | IFR | OL1-2G23-2303 | PE | 2019-05-20 | 036909C-JVD-TRN-01698 | 036909C-JVD-TRN-01698 | IFR | 2019-06-04 |  | Transmitted | TPSK-LSPA1-T-PE-01698 |  | 2019-05-21 | 2
036909C-1023-CN-0014-2309 | PSV-2343 A-B Sizing Calculation | B | 2019-05-15 | IFR | OL1-2G23-2309 | PE | 2019-05-20 | 036909C-JVD-TRN-01698 | 036909C-JVD-TRN-01698 | IFR | 2019-06-04 |  | Transmitted | TPSK-LSPA1-T-PE-01698 |  | 2019-05-21 | 2
036909C-1011-PDS-1543-1153 | Process Equipment Datasheet 10-MOV-1102B USC 36M Decoke Effluent Bypass MOV | B | 2019-03-28 | IFD | OL1-2G30-1153 | PE | 2019-03-29 | 036909C-JVD-TRN-01195 | 036909C-JVD-TRN-01195 | IFR |  | 2019-04-22 | R1-No comments | TPSK-LSPA1-T-PE-01195 |  | 2019-04-01 | 2
036909C-1011-PDS-1543-1151 | Process Equipment Datasheet 10-MOV-1101 USC 36M Effluent MOV | B | 2019-03-28 | IFD | OL1-2G30-1151 | PE | 2019-03-29 | 036909C-JVD-TRN-01195 | 036909C-JVD-TRN-01195 | IFR |  | 2019-04-22 | R1-No comments | TPSK-LSPA1-T-PE-01195 |  | 2019-04-01 | 2
036909C-1011-PDS-1542-1112 | Process Equipment Datasheet - 10-ZZ-1100 - USC 36M Attemperator | B | 2019-04-01 | IFD | OL1-2G31-1112 | PE | 2019-04-11 | 036909C-JVD-TRN-01330 | 036909C-JVD-TRN-01330 | IFR | 2019-04-26 | 2019-05-15 | R1-No comments | TPSK-LSPA1-T-PE-01330 |  | 2019-04-12 | 2
036909C-1011-PDS-0117-1102 | Anticipated Operating Conditions - 10-H-1100 - USC 36M Gas Cracking Furnace | 1 | 2019-03-28 | IFD | OL1-2G30-1102 | PE | 2019-04-02 | 036909C-JVD-TRN-01232 | 036909C-JVD-TRN-01232 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-01232 |  | 2019-04-03 | 3
036909C-1011-DW-0132-1109 | USC 36M Recycle Furnace Seal Boot Details | 0 | 2019-04-15 | IFI | OL1-2M06-1109 | ME | 2019-04-16 | 036909C-JVD-TRN-01368 | 036909C-JVD-TRN-01368 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-01368 |  | 2019-04-17 | 3
036909C-1011-DW-0125-1302 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details | 1 | 2018-12-12 | IMP | OL1-2M06-1302 | ME | 2018-12-17 | 036909C-JVD-TRN-00520 | 036909C-JVD-TRN-00520 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00520 |  | 2018-12-17 | 3
036909C-100S-DW-1920-0001 | Hazardous Area Classification - Zone 0S - Electrical Substation and Far E | A | 2019-03-07 | IFA | OL1-2L42-0004 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-103S-DW-1920-0001 | Hazardous Area Classification - Zone 3S -Electrical and Substation and Far C | A | 2019-03-07 | IFA | OL1-2L42-0005 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-100M-DW-1920-0001 | Hazardous Area Classification - Zone 0M - Metering Station | A | 2019-03-07 | IFA | OL1-2L42-0002 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015, ROC-TPSK-CECO-T-00013 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-101B-DW-1920-0001 | Hazardous Area Classification - Zone 1B -Furnaces Utilities | A | 2019-03-07 | IFA | OL1-2L42-0007 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-102A-DW-1920-0001 | Hazardous Area Classification - Zone 2A - Quench | A | 2019-03-07 | IFA | OL1-2L42-0008 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-101A-DW-1920-0001 | Hazardous Area Classification - Zone 1A - Furnaces | A | 2019-03-07 | IFA | OL1-2L42-0006 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-100P-DW-1920-0001 | Hazardous Area Classification - Zone 0P - Main Pipe Rack | A | 2019-03-07 | IFA | OL1-2L42-0003 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-103A-DW-1920-0001 | Hazardous Area Classification - Zone 3A - Butadiene Extraction Unit | A | 2019-03-07 | IFA | OL1-2L42-0013 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-105F-DW-1920-0001 | Hazardous Area Classification - Zone 5F - HP and Ployolefins Flare Unit | A | 2019-03-07 | IFA | OL1-2L42-0014 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-102C-DW-1920-0001 | Hazardous Area Classification - Zone 2C - Hot Fractionation - GHU | A | 2019-03-07 | IFA | OL1-2L42-0010 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-102B-DW-1920-0001 | Hazardous Area Classification - Zone 2B - C3 Hydrogenation | A | 2019-03-07 | IFA | OL1-2L42-0009 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-102E-DW-1920-0001 | Hazardous Area Classification - Zone 2E - Cracked Gas Compressor | A | 2019-03-07 | IFA | OL1-2L42-0012 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-105T-DW-1920-0001 | Hazardous Area Classification - Zone 5T - Cooling Water Unit | A | 2019-03-07 | IFA | OL1-2L42-0015 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-102D-DW-1920-0001 | Hazardous Area Classification - Zone 2D - Process Cold Compressor | A | 2019-03-07 | IFA | OL1-2L42-0011 | SE | 2019-03-11 | 036909C-JVD-TRN-01015 | 036909C-JVD-TRN-01015 | IFA | 2019-03-26 | 2019-03-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01015 |  | 2019-03-12 | 1
036909C-1025-SP-1547-2502 | Instrument Datasheets for Flow Element - Rotameter - Area 25 | A | 2019-04-08 | IFQ | OL1-2I20-2528 | IE | 2019-04-23 | 036909C-JVD-TRN-01338 | 036909C-JVD-TRN-01338, ROC-TPSK-CECO-T-00056 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-01338 |  | 2019-04-15 | 3
036909C-1021-SP-0840-2139 | Mechanical Equipment Datasheet - Process Water Coalescer Prefilters | 0 | 2019-05-13 | IFP | OL1-2M03-2139 | ME | 2019-05-15 | 036909C-JVD-TRN-01669 | 036909C-JVD-TRN-01669 | IFR | 2019-05-30 |  | Transmitted | TPSK-LSPA1-T-ME-01669 |  | 2019-05-16 | 2
036909C-1012-DW-0117-2207 | USC 132U Cracking Furnace Dilution Mixing Tee Details | 0 | 2019-01-10 | IFI | OL1-2M06-2207 | ME | 2019-01-23 | 036909C-JVD-TRN-00669 | 036909C-JVD-TRN-00668, 036909C-JVD-TRN-00669 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00669 |  | 2019-01-23 | 3
036909C-1026-SP-0510-2630 | Mechanical Equipment Data Sheet - Secondary Deethanizer | A | 2018-12-05 | IFQ | OL1-2M03-2630 | ME | 2018-12-10 | 036909C-JVD-TRN-00458 | 036909C-JVD-TRN-00458 | IFR | 2018-12-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00458 |  | 2018-12-10 | 2
036909C-1026-SP-0510-2630 | Mechanical Equipment Data Sheet - Secondary Deethanizer | B | 2019-03-01 | IFQ | OL1-2M03-2630 | ME | 2019-03-01 | 036909C-JVD-TRN-00974 | 036909C-JVD-TRN-00974, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-16 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-ME-00974 |  | 2019-03-04 | 2
036909C-1021-SP-0510-2140 | Mechanical Equipment Data Sheet - Process Water Stripper | B | 2019-01-31 | IFQ | OL1-2M03-2140 | ME | 2019-02-06 | 036909C-JVD-TRN-00801 | 036909C-JVD-TRN-00801, ROC-TPSK-CECO-T-00014 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-ME-00801 |  | 2019-02-06 | 2
036909C-1021-SP-0510-2140 | Mechanical Equipment Data Sheet - Process Water Stripper | A | 2018-12-05 | IFQ | OL1-2M03-2140 | ME | 2018-12-10 | 036909C-JVD-TRN-00458 | 036909C-JVD-TRN-00458 | IFR | 2018-12-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00458 |  | 2018-12-10 | 2
036909C-1021-SP-0510-2120 | Mechanical Equipment Data Sheet - Distillate Stripper | A | 2018-12-18 | IFQ | OL1-2M03-2120 | ME | 2018-12-20 | 036909C-JVD-TRN-00546 | 036909C-JVD-TRN-00546 | IFR | 2019-01-02 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00546 |  | 2018-12-20 | 2
036909C-1021-SP-0510-2120 | Mechanical Equipment Data Sheet - Distillate Stripper | B | 2019-02-11 | IFQ | OL1-2M03-2120 | ME | 2019-02-12 | 036909C-JVD-TRN-00840 | 036909C-JVD-TRN-00840, ROC-TPSK-CECO-T-00014 | IFI |  | 2019-02-28 | R1-No comments | TPSK-LSPA1-T-ME-00840 |  | 2019-02-12 | 2
036909C-1020-SP-0510-2020 | Mechanical Equipment Data Sheet - Light Fuel Oil Stripper Elevation View | B | 2019-01-31 | IFQ | OL1-2M03-2020 | ME | 2019-02-06 | 036909C-JVD-TRN-00801 | 036909C-JVD-TRN-00801, ROC-TPSK-CECO-T-00014 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-ME-00801 |  | 2019-02-06 | 2
036909C-1012-DW-0131-2522 | USC 132U Cracking Furnace Steel Match Bolting Plans For Field Splice At EL 118240 and 135270 | A | 2019-03-29 | IFI | OL1-2K32-2522 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1012-DW-0131-2519 | USC 132U Cracking Furnace Steel Radiant Sections And Details | A | 2019-03-29 | IFI | OL1-2K32-2519 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1012-DW-0131-2517 | USC 132U Cracking Furnace Steel Radiant Sections And Details | A | 2019-03-29 | IFI | OL1-2K32-2517 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1012-DW-0131-2516 | USC 132U Cracking Furnace Steel Shadow Box Details | A | 2019-03-29 | IFI | OL1-2K32-2516 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1012-DW-0131-2515 | USC 132U Cracking Furnace Steel Transition Floor Plan And Sections | A | 2019-03-29 | IFI | OL1-2K32-2515 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1012-DW-0131-2513 | USC 132U Cracking Furnace Steel Radiant Side Wall At COL Line B2 And C2 | A | 2019-03-29 | IFI | OL1-2K32-2513 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1012-DW-0117-2553 | USC 132U Cracking Furnace Steel Radiant Coil Tube Pulling Panel Detail | A | 2019-03-29 | IFI | OL1-2K32-2553 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1011-DW-0131-1522 | USC 36M Recycle Furnace Steel Match Bolting Plans for Field Splice at El 115022 and 132470 | A | 2019-03-29 | IFI | OL1-2K32-1522 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1011-DW-0117-1553 | USC 36M Recycle Furnace Steel Radiant Coil Tube Pulling Panel Details | A | 2019-03-29 | IFI | OL1-2K32-1553 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1011-DW-0131-1513 | USC 36M Recycle Furnace Steel Radiant Side Wall at Col Line B1 and C1 | A | 2019-03-29 | IFI | OL1-2K32-1513 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1011-DW-0131-1519 | USC 36M Recycle Furnace Steel Radiant Sections and Details | A | 2019-03-29 | IFI | OL1-2K32-1519 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1011-DW-0131-1517 | USC 36M Recycle Furnace Steel Radiant Sections and Details | A | 2019-03-29 | IFI | OL1-2K32-1517 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1011-DW-0131-1516 | USC 36M Recycle Furnace Steel Shadow Box Details | A | 2019-03-29 | IFI | OL1-2K32-1516 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1011-DW-0131-1515 | USC 36M Recycle Furnace Steel Transition Floor Plan and Sections | A | 2019-03-29 | IFI | OL1-2K32-1515 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1027-PDS-0500-2710 | Process Equipment Datasheet - 10-T-2710 Depentanizer | A | 2019-01-18 | IFR | OL1-2G30-2710 | PE | 2019-01-22 | 036909C-JVD-TRN-00688 | 036909C-JVD-TRN-00688 | IFR | 2019-02-04 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00688 |  | 2019-01-22 | 2
036909C-1027-PDS-0500-2710 | Process Equipment Datasheet - 10-T-2710 Depentanizer | B | 2019-03-15 | IFD | OL1-2G30-2710 | PE | 2019-03-15 | 036909C-JVD-TRN-01082 | 036909C-JVD-TRN-01082 | IFR | 2019-04-01 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-PE-01082 |  | 2019-03-18 | 2
036909C-1021-TDS-0661-2101 | Mechanical Equipment Data Sheet - 10-E-2100 - Quench Water Cooler | 1 | 2019-04-11 | IFP | OL1-2M03-2101 | ME | 2019-04-12 | 036909C-JVD-TRN-01343 | 036909C-JVD-TRN-01343 | IFR | 2019-04-29 | 2019-05-20 | R1-No comments | TPSK-LSAP1-T-ME-01343 |  | 2019-04-15 | 2
036909C-1012-HOM-0154-2003 | Hand-Over Meeting Report - Quench Exchanger and Steam D | 0 | 2019-02-20 | IFI | OL1-2C95-140000 | PL | 2019-03-11 | 036909C-JVD-TRN-01026 | 036909C-JVD-TRN-01026 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01026 |  | 2019-03-12 | 3
036909C-1012-DL-1040-2005 | Deviation List for Furnace ID Fans | B | 2019-02-27 | IFR | OL1-2C40-301000 | PL | 2019-03-04 | 036909C-JVD-TRN-00978 | 036909C-JVD-TRN-00978 | IFR | 2019-03-18 |  | Transmitted | TPSK-LSPA1-T-PL-00978 |  | 2019-03-05 | 3
036909C-1012-HOM-0122-2004 | Hand-Over Meeting Report - Radiant Coils | 0 | 2019-03-29 | IFI | OL1-2C95-300000 | PL | 2019-03-29 | 036909C-JVD-TRN-01194 | 036909C-JVD-TRN-01194 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01194 |  | 2019-04-01 | 3
036909C-1024-PDS-0800-2410 | Process Equipment Datasheet - 10-D-2410 A-B - Cracked Gas Dryer | D | 2019-04-08 | IFD | OL1-2G30-2410 | PE | 2019-04-10 | 036909C-JVD-TRN-01310 | 036909C-JVD-TRN-01310 | IFR | 2019-04-25 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01310 |  | 2019-04-11 | 2
036909C-1011-PDS-1543-1151 | Process Equipment Datasheet 10-MOV-1101 USC 36M Effluent MOV | A | 2018-12-12 | IFR | OL1-2G30-1151 | PE | 2018-12-20 | 036909C-JVD-TRN-00521 | 036909C-JVD-TRN-00521 | IFR | 2019-01-02 | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00521 |  | 2018-12-20 | 2
036909C-1011-PDS-1543-1153 | Process Equipment Datasheet 10-MOV-1102B USC 36M Decoke Effluent Bypass MOV | A | 2018-12-12 | IFR | OL1-2G30-1153 | PE | 2018-12-20 | 036909C-JVD-TRN-00521 | 036909C-JVD-TRN-00521 | IFR | 2019-01-02 | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00521 |  | 2018-12-20 | 2
036909C-1011-PDS-1542-1112 | Process Equipment Datasheet - 10-ZZ-1100 - USC 36M Attemperator | A | 2019-01-24 | IFR | OL1-2G31-1112 | PE | 2019-01-29 | 036909C-JVD-TRN-00757 | 036909C-JVD-TRN-00757 | IFR | 2019-02-12 | 2019-02-26 | R1-No comments | TPSK-LSPA1-T-PE-00757 |  | 2019-01-29 | 2
036909C-1011-DW-0132-1106 | USC 36M Recycle Furnace Peep Door Insert Details | A | 2019-02-22 | IFR | OL1-2M06-1106 | ME | 2019-03-14 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15 | 2
036909C-1011-SP-0117-1105 | API Fired Heater Datasheet 10-H-1100 | A | 2019-03-07 | IFR | OL1-2M03-1105 | ME | 2019-03-15 | 036909C-JVD-TRN-01084 | 036909C-JVD-TRN-01084 | IFR | 2019-03-30 |  | Transmitted | TPSK-LSPA1-T-ME-01084 |  | 2019-03-18 | 2
036909C-1028-CN-0014-2824 | PSV-2855 Sizing Calculation | A | 2019-05-15 | IFR | OL1-2G23-2824 | PE | 2019-05-16 | 036909C-JVD-TRN-01680 | 036909C-JVD-TRN-01680 | IFR | 2019-05-31 |  | Transmitted | TPSK-LSPA1-T-PE-01680 |  | 2019-05-17 | 2
036909C-1028-CN-0014-2812 | PSV-2837 Sizing Calculation | A | 2019-05-10 | IFR | OL1-2G23-2812 | PE | 2019-05-16 | 036909C-JVD-TRN-01680 | 036909C-JVD-TRN-01680 | IFR | 2019-05-31 |  | Transmitted | TPSK-LSPA1-T-PE-01680 |  | 2019-05-17 | 2
036909C-1028-CN-0014-2809 | PSV-2832 Sizing Calculation | A | 2019-05-10 | IFR | OL1-2G23-2809 | PE | 2019-05-16 | 036909C-JVD-TRN-01680 | 036909C-JVD-TRN-01680 | IFR | 2019-05-31 |  | Transmitted | TPSK-LSPA1-T-PE-01680 |  | 2019-05-17 | 2
036909C-1024-CN-0014-2415 | PSV-2425 A-B Sizing Calculation | B | 2019-05-09 | IFR | OL1-2G23-2415 | PE | 2019-05-16 | 036909C-JVD-TRN-01680 | 036909C-JVD-TRN-01680 | IFR | 2019-05-31 |  | Transmitted | TPSK-LSPA1-T-PE-01680 |  | 2019-05-17 | 2
036909C-1024-CN-0014-2419 | PSV-2431 A-B Sizing Calculation | B | 2019-05-13 | IFR | OL1-2G23-2419 | PE | 2019-05-16 | 036909C-JVD-TRN-01680 | 036909C-JVD-TRN-01680 | IFR | 2019-05-31 |  | Transmitted | TPSK-LSPA1-T-PE-01680 |  | 2019-05-17 | 2
036909C-1024-CN-0014-2411 | PSV-2418 A-D Sizing Calculation | A | 2019-05-10 | IFR | OL1-2G23-2411 | PE | 2019-05-16 | 036909C-JVD-TRN-01680 | 036909C-JVD-TRN-01680 | IFR | 2019-05-31 |  | Transmitted | TPSK-LSPA1-T-PE-01680 |  | 2019-05-17 | 2
036909C-1059-PDS-0900-5901 | Process Equipment Datasheet - 10-P-5900 A-B - Sulfuric Acid Distribution Pumps | A | 2019-01-24 | IFR | OL1-2G30-5901 | PE | 2019-01-28 | 036909C-JVD-TRN-00738 | 036909C-JVD-TRN-00738 | IFR | 2019-02-11 | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00738 |  | 2019-01-28 | 2
036909C-1026-PID-0021-2631 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Bottoms Pumps | 0 | 2019-04-10 | CAN | OL1-2G43-2631 | PE | 2019-04-10 | 036909C-JVD-TRN-01298 | 036909C-JVD-TRN-01298, ROC-TPSK-CECO-T-00066 | IFR | 2019-04-25 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01298 |  | 2019-04-11 | 2
036909C-1029-PDS-2600-2914 | Process Equipment Datasheet - 10-PK-2914 - Neutralization Injection Pkg | 0 | 2019-04-11 | CAN | OL1-2G30-2914 | PE | 2019-04-11 | 036909C-JVD-TRN-01329 | 036909C-JVD-TRN-01329 | IFR | 2019-04-26 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01329 |  | 2019-04-12 | 2
036909C-1056-PDS-2600-5691 | Process Equipment Datasheet - 10-PK-5691 - Slop Tank Acid Injection Pkg | B | 2019-04-04 | IFD | OL1-2G30-5691 | PE | 2019-04-08 | 036909C-JVD-TRN-01274 | 036909C-JVD-TRN-01274 | IFR | 2019-04-23 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01274 |  | 2019-04-09 | 2
036909C-1025-SP-0510-2520 | Mechanical Equipment Data Sheet - Residue Gas Rectifier And Rectifier Reflux Drum | B | 2019-01-30 | IFQ | OL1-2M03-2520 | ME | 2019-02-01 | 036909C-JVD-TRN-00792 | 036909C-JVD-TRN-00792, ROC-TPSK-CECO-T-00015 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00792 |  | 2019-02-04 | 2
036909C-1025-SP-0510-2520 | Mechanical Equipment Data Sheet - Residue Gas Rectifier And Rectifier Reflux Drum | A | 2018-12-17 | IFQ | OL1-2M03-2520 | ME | 2018-12-20 | 036909C-JVD-TRN-00535 | 036909C-JVD-TRN-00535 | IFR | 2019-01-02 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00534 |  | 2018-12-20 | 2
036909C-1026-SP-0840-2664 | Mechanical Equipment Datasheet - C5 - Pygas Feed Filters | A | 2019-03-19 | IFQ | OL1-2M03-2664 | ME | 2019-03-25 | 036909C-JVD-TRN-01141 | 036909C-JVD-TRN-01141 | IFR | 2019-04-09 | 2019-04-11 | R1-No comments | TPSK-LSPA1-T-ME-01141 |  | 2019-03-26 | 2
036909C-1023-SP-0840-2319 | Mechanical Equipment Datasheet - Spent Caustic Pump Discharge Filters | A | 2019-01-10 | IFQ | OL1-2M03-2319 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639 |  | 2019-01-11 | 2
036909C-1023-SP-0840-2314 | Mechanical Equipment Datasheet - Wash Oil Circulation Filter | A | 2019-01-10 | IFQ | OL1-2M03-2314 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639 |  | 2019-01-11 | 2
036909C-1023-SP-0840-2307 | Mechanical Equipment Datasheet - Weak Caustic Circulating Filters | A | 2019-01-10 | IFQ | OL1-2M03-2307 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639 |  | 2019-01-11 | 2
036909C-1023-SP-0840-2307 | Mechanical Equipment Datasheet - Weak Caustic Circulating Filters | B | 2019-03-14 | IFQ | OL1-2M03-2307 | ME | 2019-03-25 | 036909C-JVD-TRN-01141 | 036909C-JVD-TRN-01141 | IFR | 2019-04-09 | 2019-04-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-01141 |  | 2019-03-26 | 2
036909C-1021-SP-0840-2138 | Mechanical Equipment Datasheet - Process Water Feed Filters | B | 2019-03-18 | IFQ | OL1-2M03-2138 | ME | 2019-03-25 | 036909C-JVD-TRN-01141 | 036909C-JVD-TRN-01141 | IFR | 2019-04-09 | 2019-04-11 | R1-No comments | TPSK-LSPA1-T-ME-01141 |  | 2019-03-26 | 2
036909C-1021-SP-0840-2138 | Mechanical Equipment Datasheet - Process Water Feed Filters | A | 2019-01-10 | IFQ | OL1-2M03-2138 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639 |  | 2019-01-11 | 2
036909C-1021-SP-0840-2104 | Mechanical Equipment Datasheet - Quench Oil Reflux Filter | A | 2019-01-10 | IFQ | OL1-2M03-2104 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639 |  | 2019-01-11 | 2
036909C-1021-SP-0840-2104 | Mechanical Equipment Datasheet - Quench Oil Reflux Filter | B | 2019-03-18 | IFQ | OL1-2M03-2104 | ME | 2019-03-25 | 036909C-JVD-TRN-01141 | 036909C-JVD-TRN-01141 | IFR | 2019-04-09 | 2019-04-11 | R1-No comments | TPSK-LSPA1-T-ME-01141 |  | 2019-03-26 | 2
036909C-1020-SP-0840-2049 | Mechanical Equipment Datasheet -Heavy Fuel Oil Filters | A | 2019-01-10 | IFQ | OL1-2M03-2049 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639 |  | 2019-01-11 | 2
036909C-1020-SP-0840-2049 | Mechanical Equipment Datasheet - Heavy Fuel Oil Filters | B | 2019-03-26 | IFQ | OL1-2M03-2049 | ME | 2019-03-26 | 036909C-JVD-TRN-01157 | 036909C-JVD-TRN-01157 | IFR | 2019-04-10 | 2019-04-11 | R1-No comments | TPSK-LSPA1-T-ME-01157 |  | 2019-03-27 | 2
036909C-1020-SP-0840-2025 | Mechanical Equipment Datasheet - Cracker Bottoms Product Filter | B | 2019-03-14 | IFQ | OL1-2M03-2025 | ME | 2019-03-25 | 036909C-JVD-TRN-01141 | 036909C-JVD-TRN-01141 | IFR | 2019-04-09 | 2019-04-11 | R1-No comments | TPSK-LSPA1-T-ME-01141 |  | 2019-03-26 | 2
036909C-1020-SP-0840-2025 | Mechanical Equipment Datasheet - Cracker Bottoms Product Filter | A | 2019-01-10 | IFQ | OL1-2M03-2025 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639 |  | 2019-01-11 | 2
036909C-1020-SP-0840-2010 | Mechanical Equipment Data sheet - Quench Oil Filter | A | 2019-01-10 | IFQ | OL1-2M03-2010 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639 |  | 2019-01-11 | 2
036909C-102E-CN-1733-0032 | Calculation Note For Foundation Of 10-R-2470A-B-C | A | 2019-05-13 | IFR | OL1-2K13-0148 | CV | 2019-05-14 | 036909C-JVD-TRN-01661 | 036909C-JVD-TRN-01661, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 |  | Transmitted | TPSK-LSPA1-T-CV-01661 |  | 2019-05-15 | 1
036909C-102E-CN-1733-0026 | Calculation Note For Foundation Of 10-D-2420A-B | A | 2019-05-13 | IFR | OL1-2K13-0096 | CV | 2019-05-14 | 036909C-JVD-TRN-01661 | 036909C-JVD-TRN-01661, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 |  | Transmitted | TPSK-LSPA1-T-CV-01661 |  | 2019-05-15 | 1
036909C-102C-CN-1733-0011 | Calculation Note For Foundation Of 10-R-2700A-B | A | 2019-05-13 | IFR | OL1-2K13-0138 | CV | 2019-05-14 | 036909C-JVD-TRN-01661 | 036909C-JVD-TRN-01661, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 |  | Transmitted | TPSK-LSPA1-T-CV-01661 |  | 2019-05-15 | 1
036909C-102C-CN-1733-0033 | Calculation Note For Foundation Of 10-E-2706 | A | 2019-05-08 | IFR | OL1-2K13-0181 | CV | 2019-05-14 | 036909C-JVD-TRN-01661 | 036909C-JVD-TRN-01661, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 |  | Transmitted | TPSK-LSPA1-T-CV-01661 |  | 2019-05-15 | 1
036909C-102C-CN-1733-0026 | Calculation Note For Foundation Of 10-E-2755 | A | 2019-05-13 | IFR | OL1-2K13-0175 | CV | 2019-05-14 | 036909C-JVD-TRN-01661 | 036909C-JVD-TRN-01661, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 |  | Transmitted | TPSK-LSPA1-T-CV-01661 |  | 2019-05-15 | 1
036909C-102C-CN-1733-0016 | Calculation Note For Foundation Of 10-E-2666 | A | 2019-05-07 | IFR | OL1-2K13-0141 | CV | 2019-05-14 | 036909C-JVD-TRN-01661 | 036909C-JVD-TRN-01661, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 |  | Transmitted | TPSK-LSPA1-T-CV-01661 |  | 2019-05-15 | 1
036909C-102C-CN-1733-0002 | Calculation Note For Foundation Of 10-E-5113 | A | 2019-05-13 | IFR | OL1-2K13-0292 | CV | 2019-05-14 | 036909C-JVD-TRN-01661 | 036909C-JVD-TRN-01661, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 |  | Transmitted | TPSK-LSPA1-T-CV-01661 |  | 2019-05-15 | 1
036909C-1056-SP-0910-5649 | Mechanical Equipment Datasheet - Flare KO Drum Oily Wastewater Pump | A | 2019-01-18 | IFQ | OL1-2M03-5649 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716 |  | 2019-01-24 | 2
036909C-1056-SP-0910-5614 | Mechanical Equipment Datasheet - Furnace Area Oily Wastewater Pump | A | 2019-01-18 | IFQ | OL1-2M03-5614 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716 |  | 2019-01-24 | 2
036909C-1012-DW-0132-2106 | USC 132U Cracking Furnace Peep Door Insert Details | A | 2019-02-20 | IFR | OL1-2M06-2106 | ME | 2019-03-14 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15 | 2
036909C-102E-CN-1733-0047 | Calculation Note For Foundation Of 10-E-2441 | A | 2019-04-04 | IFR | OL1-2K13-0401 | CV | 2019-04-12 | 036909C-JVD-TRN-01333 | 036909C-JVD-TRN-01333, ROC-TPSK-CECO-T-00044 | IFA | 2019-04-29 | 2019-05-09 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01333 |  | 2019-04-15 | 1
036909C-102E-CN-1733-0039 | Calculation Note For Foundation Of 10-E-2440 | A | 2019-04-04 | IFR | OL1-2K13-0160 | CV | 2019-04-12 | 036909C-JVD-TRN-01333 | 036909C-JVD-TRN-01333, ROC-TPSK-CECO-T-00044 | IFA | 2019-04-29 | 2019-05-09 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01333 |  | 2019-04-15 | 1
036909C-102E-CN-1733-0017 | Calculation Note For Foundation Of 10-E-2412 | A | 2019-04-04 | IFR | OL1-2K13-0059 | CV | 2019-04-12 | 036909C-JVD-TRN-01333 | 036909C-JVD-TRN-01333, ROC-TPSK-CECO-T-00044 | IFA | 2019-04-29 | 2019-05-09 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01333 |  | 2019-04-15 | 1
036909C-102A-CN-1734-0001 | Calculation Note For Foundation of 10-PIT-2090 | A | 2019-04-04 | IFR | OL1-2K13-0331 | CV | 2019-04-10 | 036909C-JVD-TRN-01303 | 036909C-JVD-TRN-01303, ROC-TPSK-CECO-T-00050 | IFA | 2019-04-25 | 2019-05-09 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01303 |  | 2019-04-11 | 1
036909C-1021-PDS-0500-2100 | Process Equipment Datasheet - 10-T-2100 - Quench Water Tower | C | 2019-03-27 | IFD | OL1-2G30-2100 | PE | 2019-03-28 | 036909C-JVD-TRN-01184 | 036909C-JVD-TRN-01184 | IFR | 2019-04-12 | 2019-04-22 | R1-No comments | TPSK-LSPA1-T-PE-01184 |  | 2019-03-29 | 2
036909C-1055-PDS-0600-5553 | Process Equipment Datasheet - 10-E-5552 - LPG Vaporizer - Superheater | C | 2019-05-06 | IFD | OL1-2G30-5553 | PE | 2019-05-06 | 036909C-JVD-TRN-01589 | 036909C-JVD-TRN-01589 | IFR | 2019-05-21 |  | Transmitted | TPSK-LSPA1-T-PE-01589 |  | 2019-05-07 | 2
036909C-1027-PDS-0600-2725 | Process Equipment Datasheet - 10-E-2725 A-B - Rerun Tower Reboiler | C | 2019-05-03 | IFD | OL1-2G30-2725 | PE | 2019-05-07 | 036909C-JVD-TRN-01604 | 036909C-JVD-TRN-01604 | IFR | 2019-05-22 |  | Transmitted | TPSK-LSPA1-T-PE-01604 |  | 2019-05-08 | 2
036909C-1027-PDS-0600-2715 | Process Equipment Datasheet - 10-E-2715 - Depentanizer Reboiler | D | 2019-05-03 | IFD | OL1-2G30-2715 | PE | 2019-05-07 | 036909C-JVD-TRN-01604 | 036909C-JVD-TRN-01604 | IFR | 2019-05-22 |  | Transmitted | TPSK-LSPA1-T-PE-01604 |  | 2019-05-08 | 2
036909C-1056-PDS-0900-5614 | Process Equipment Datasheet - 10-P-5605 A-B - Furnace Area Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5614 | PE | 2019-01-31 | 036909C-JVD-TRN-00779 | 036909C-JVD-TRN-00779 | IFI |  | 2019-03-04 | R1-No comments | TPSK-LSPA1-T-PE-00779 |  | 2019-02-01 | 2
036909C-1056-PDS-0200-5647 | Process Equipment Datasheet - 10-PIT-5607 - Flare KO Drum Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5647 | PE | 2019-03-04 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05 | 2
036909C-1056-PDS-0200-5647 | Process Equipment Datasheet - 10-PIT-5607 - Flare KO Drum Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5647 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1056-PDS-0200-5605 | Process Equipment Datasheet - 10-PIT-5605 - Furnace Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5605 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1056-PDS-0200-5605 | Process Equipment Datasheet - 10-PIT-5605 - Furnace Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5605 | PE | 2019-03-04 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05 | 2
036909C-1056-PDS-2600-5691 | Process Equipment Datasheet - 10-PK-5691 - Slop Tank Acid Injection Pkg | A | 2019-02-07 | IFR | OL1-2G30-5691 | PE | 2019-02-07 | 036909C-JVD-TRN-00821 | 036909C-JVD-TRN-00821, ROC-TPSK-CECO-T-00020 | IFR | 2019-02-21 | 2019-03-14 | R1-No comments | TPSK-LSPA1-T-PE-00821 |  | 2019-02-07 | 2
036909C-1027-SP-0910-2751 | Mechanical Equipment Datasheet - C4-C5 Hydrog Feed Pump | B | 2019-03-07 | IFQ | OL1-2M03-2751 | ME | 2019-03-20 | 036909C-JVD-TRN-01102 | 036909C-JVD-TRN-01102, ROC-TPSK-CECO-T-00015 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-ME-01102 |  | 2019-03-21 | 2
036909C-1027-SP-0910-2751 | Mechanical Equipment Datasheet - C4-C5 Hydrog Feed Pump | A | 2019-02-06 | IFQ | OL1-2M03-2751 | ME | 2019-02-07 | 036909C-JVD-TRN-00817 | 036909C-JVD-TRN-00817 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00817 |  | 2019-02-07 | 2
036909C-1000-PP-257 | 3D Modeling Procedure For Electrical Designers | 0 | 2019-03-11 | IMP | OL1-2R05-0060 | EE | 2019-04-01 | 036909C-JVD-TRN-01217 | 036909C-JVD-TRN-01217 | IFR | 2019-04-16 | 2019-05-07 | R1-No comments | TPSK-LSPA1-T-EE-01217 |  | 2019-04-02 | 2
036909C-1027-PDS-0900-2751 | Process Equipment Datasheet - 10-P-2750 A-B - C4 - C5 Hydrog Feed Pump | B | 2019-02-28 | IFD | OL1-2G30-2751 | PE | 2019-03-01 | 036909C-JVD-TRN-00963 | 036909C-JVD-TRN-00963 | IFR | 2019-03-16 | 2019-03-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00963 |  | 2019-03-04 | 2
036909C-1027-PDS-0900-2751 | Process Equipment Datasheet - 10-P-2750 A-B - C4-C5 Hydrog Feed Pump | A | 2019-02-01 | IFR | OL1-2G30-2751 | PE | 2019-02-01 | 036909C-JVD-TRN-00788 | 036909C-JVD-TRN-00788 | IFR | 2019-02-15 | 2019-02-15 | R1-No comments | TPSK-LSPA1-T-PE-00788 |  | 2019-02-04 | 2
036909C-1026-PDS-0600-2621 | Process Equipment Datasheet - 10-E-2620 - C3 Hydrog Aftercooler | A | 2019-01-09 | IFR | OL1-2G30-2621 | PE | 2019-01-10 | 036909C-JVD-TRN-00615 | 036909C-JVD-TRN-00615 | IFR | 2019-01-23 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00615 |  | 2019-01-10 | 2
036909C-1027-PDS-0600-2765 | Process Equipment Datasheet - 10-E-2765 - C4-C5 Hydrog Recycle Cooler | A | 2019-02-01 | IFR | OL1-2G30-2765 | PE | 2019-02-01 | 036909C-JVD-TRN-00793 | 036909C-JVD-TRN-00793 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00793 |  | 2019-02-04 | 2
036909C-1027-PDS-0600-2765 | Process Equipment Datasheet - 10-E-2765 - C4-C5 Hydrog Recycle Cooler | B | 2019-03-07 | IFD | OL1-2G30-2765 | PE | 2019-03-11 | 036909C-JVD-TRN-01027 | 036909C-JVD-TRN-01027 | IFR | 2019-03-26 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-PE-01027 |  | 2019-03-12 | 2
036909C-1027-PDS-0600-2763 | Process Equipment Datasheet - 10-E-2760 - C4-C5 Hydrog Vent Condenser | A | 2019-02-01 | IFR | OL1-2G30-2763 | PE | 2019-02-01 | 036909C-JVD-TRN-00793 | 036909C-JVD-TRN-00793 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00793 |  | 2019-02-04 | 2
036909C-1027-PDS-0600-2725 | Process Equipment Datasheet - 10-E-2725 A-B - Rerun Tower Reboiler | A | 2019-02-01 | IFR | OL1-2G30-2725 | PE | 2019-02-11 | 036909C-JVD-TRN-00835 | 036909C-JVD-TRN-00835, ROC-TPSK-CECO-T-00019 | IFR | 2019-02-25 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00835 |  | 2019-02-11 | 2
036909C-1027-PDS-0600-2715 | Process Equipment Datasheet - 10-E-2715 A-B - Depentanizer Reboiler | B | 2019-03-20 | IFD | OL1-2G30-2715 | PE | 2019-03-20 | 036909C-JVD-TRN-01107 | 036909C-JVD-TRN-01107 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01107 |  | 2019-03-21 | 2
036909C-1027-PDS-0600-2715 | Process Equipment Datasheet - 10-E-2715 A-B - Depentanizer Reboiler | A | 2019-01-23 | IFR | OL1-2G30-2715 | PE | 2019-01-25 | 036909C-JVD-TRN-00724 | 036909C-JVD-TRN-00724 | IFR | 2019-02-07 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00724 |  | 2019-01-25 | 2
036909C-1027-PDS-0600-2711 | Process Equipment Datasheet - 10-E-2710 - Depentanizer Condenser | A | 2019-01-22 | IFR | OL1-2G30-2711 | PE | 2019-01-25 | 036909C-JVD-TRN-00720 | 036909C-JVD-TRN-00720 | IFR | 2019-02-07 | 2019-02-15 | R1-No comments | TPSK-LSPA1-T-PE-00720 |  | 2019-01-25 | 2
036909C-1027-PDS-0600-2711 | Process Equipment Datasheet - 10-E-2710 - Depentanizer Condenser | B | 2019-03-20 | IFD | OL1-2G30-2711 | PE | 2019-03-20 | 036909C-JVD-TRN-01107 | 036909C-JVD-TRN-01107 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01107 |  | 2019-03-21 | 2
036909C-1027-PDS-0600-2707 | Process Equipment Datasheet - 10-E-2706 - GHU-1 Cooler | A | 2019-01-24 | IFR | OL1-2G30-2707 | PE | 2019-01-25 | 036909C-JVD-TRN-00720 | 036909C-JVD-TRN-00720 | IFR | 2019-02-07 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00720 |  | 2019-01-25 | 2
036909C-1027-PDS-0600-2703 | Process Equipment Datasheet - 10-E-2705 - GHU-1 Recycle Cooler | A | 2019-01-21 | IFR | OL1-2G30-2703 | PE | 2019-01-25 | 036909C-JVD-TRN-00720 | 036909C-JVD-TRN-00720 | IFR | 2019-02-07 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00720 |  | 2019-01-25 | 2
036909C-1027-PDS-0600-2701 | Process Equipment Datasheet - 10-E-2701 - GHU-1 Feed - Effluent Exchangers | A | 2019-01-21 | IFR | OL1-2G30-2701 | PE | 2019-01-23 | 036909C-JVD-TRN-00710 | 036909C-JVD-TRN-00710 | IFR | 2019-02-05 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00710 |  | 2019-01-23 | 2
036909C-1012-PDS-1545-1203 | USC 132U Superheater Outlet PSV Datasheet - 10-PSV-1244 | A | 2019-03-07 | IFR | OL1-2G32-1203 | PE | 2019-03-11 | 036909C-JVD-TRN-01029 | 036909C-JVD-TRN-01029 | IFR | 2019-03-26 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01029 |  | 2019-03-12 | 2
036909C-1012-PDS-1545-1202 | USC 132U Steam Drum PSV Datasheet - 10-PSV-1242B | A | 2019-03-07 | IFR | OL1-2G32-1202 | PE | 2019-03-11 | 036909C-JVD-TRN-01029 | 036909C-JVD-TRN-01029 | IFR | 2019-03-26 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01029 |  | 2019-03-12 | 2
036909C-1012-PDS-1545-1201 | USC 132U Steam Drum PSV Datasheet - 10-PSV-1242A | A | 2019-03-07 | IFR | OL1-2G32-1201 | PE | 2019-03-11 | 036909C-JVD-TRN-01029 | 036909C-JVD-TRN-01029 | IFR | 2019-03-26 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01029 |  | 2019-03-12 | 2
036909C-1011-PDS-1545-1103 | USC 36M Superheater Outlet PSV Datasheet - 10-PSV-1144 | A | 2019-03-07 | IFR | OL1-2G32-1103 | PE | 2019-03-11 | 036909C-JVD-TRN-01028 | 036909C-JVD-TRN-01028 | IFR | 2019-03-25 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01028 |  | 2019-03-12 | 2
036909C-1011-PDS-1545-1101 | USC 36M Steam Drum PSV Datasheet - 10-PSV-1142A | A | 2019-03-07 | IFR | OL1-2G32-1101 | PE | 2019-03-11 | 036909C-JVD-TRN-01028 | 036909C-JVD-TRN-01028 | IFR | 2019-03-25 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01028 |  | 2019-03-12 | 2
036909C-1011-PDS-1545-1102 | USC 36M Steam Drum PSV Datasheet - 10-PSV-1142B | A | 2019-03-07 | IFR | OL1-2G32-1102 | PE | 2019-03-11 | 036909C-JVD-TRN-01028 | 036909C-JVD-TRN-01028 | IFR | 2019-03-25 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01028 |  | 2019-03-12 | 2
036909C-1026-PDS-0840-2664 | Process Equipment Datasheet - 10-F-2666 A-B - C5 - Pygas Feed Filters | A | 2019-02-18 | IFR | OL1-2G30-2664 | PE | 2019-02-20 | 036909C-JVD-TRN-00900 | 036909C-JVD-TRN-00900 | IFR | 2019-03-07 | 2019-02-26 | R1-No comments | TPSK-LSPA1-T-PE-0900 |  | 2019-02-20 | 2
036909C-1026-PDS-0840-2664 | Process Equipment Datasheet - 10-F-2666 A-B - C5 - Pygas Feed Filters | B | 2019-03-08 | IFD | OL1-2G30-2664 | PE | 2019-03-11 | 036909C-JVD-TRN-01024 | 036909C-JVD-TRN-01024, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-26 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01024 |  | 2019-03-12 | 2
036909C-1027-PDS-0800-2767 | Process Equipment Datasheet - 10-D-2765 - C4 - C5 Hydrog Coalescer Drum | A | 2019-02-13 | IFR | OL1-2G30-2767 | PE | 2019-02-20 | 036909C-JVD-TRN-00901 | 036909C-JVD-TRN-00901, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-07 | 2019-03-19 | R2-Comments as noted | TPSK-LSPA1-T-PE--00901 |  | 2019-02-20 | 2
036909C-1027-PDS-0800-2712 | Process Equipment Datasheet - 10-D-2710 - Depentanizer Reflux Drum | A | 2019-01-24 | IFR | OL1-2G30-2712 | PE | 2019-02-01 | 036909C-JVD-TRN-00781 | 036909C-JVD-TRN-00781 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00781 |  | 2019-02-01 | 2
036909C-1026-PDS-0800-2667 | Process Equipment Datasheet - 10-D-2666 - C5 - Pygas Surge Drum | A | 2019-01-28 | IFR | OL1-2G30-2667 | PE | 2019-02-01 | 036909C-JVD-TRN-00781 | 036909C-JVD-TRN-00781 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00781 |  | 2019-02-01 | 2
036909C-1055-PDS-0600-5553 | Process Equipment Datasheet - 10-E-5552 - LPG Vaporizer - Superheater | B | 2019-03-13 | IFD | OL1-2G30-5553 | PE | 2019-03-14 | 036909C-JVD-TRN-01054 | 036909C-JVD-TRN-01054 | IFR | 2019-03-29 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-PE-01054 |  | 2019-03-15 | 2
036909C-1055-PDS-0600-5553 | Process Equipment Datasheet - 10-E-5552 - LPG Vaporizer - Superheater | A | 2019-01-09 | IFR | OL1-2G30-5553 | PE | 2019-01-10 | 036909C-JVD-TRN-00622 | 036909C-JVD-TRN-00622 | IFR | 2019-01-23 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00622 |  | 2019-01-10 | 2
036909C-1027-PDS-0600-2730 | Process Equipment Datasheet - 10-E-2730 - Regen Gas Electric Heater | A | 2019-03-13 | IFR | OL1-2G30-2730 | PE | 2019-03-15 | 036909C-JVD-TRN-01070 | 036909C-JVD-TRN-01070 | IFR | 2019-04-01 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01070 |  | 2019-03-18 | 2
036909C-1025-SP-1546-2502 | Instrument Datasheets for Flow Element - Orifice - Area 25 | A | 2019-04-08 | IFQ | OL1-2I20-2522 | IE | 2019-04-23 | 036909C-JVD-TRN-01338 | 036909C-JVD-TRN-01338, ROC-TPSK-CECO-T-00056 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-01338 |  | 2019-04-23 | 3
036909C-1055-SP-0810-5514 | Mechanical Equipment Data Sheet - Methanol Vaporizer Cond Pot | B | 2019-03-19 | IFQ | OL1-2M03-5514 | ME | 2019-03-28 | 036909C-JVD-TRN-01186 | 036909C-JVD-TRN-01186 | IFR | 2019-04-12 | 2019-05-02 | R1-No comments | TPSK-LSPA1-T-ME-01186 |  | 2019-03-29 | 2
036909C-1052-SP-0810-5211 | Mechanical Equipment Data Sheet - Pilot Gas Vaporizer Cond Pot | B | 2019-03-19 | IFQ | OL1-2M03-5211 | ME | 2019-03-28 | 036909C-JVD-TRN-01186 | 036909C-JVD-TRN-01186 | IFR | 2019-04-12 | 2019-05-02 | R1-No comments | TPSK-LSPA1-T-ME-01186 |  | 2019-03-29 | 2
036909C-102D-CN-1733-0015 | Calculation Note For Foundation Of 10-D-2550 | A | 2019-03-15 | IFR | OL1-2K13-0103 | CV | 2019-03-19 | 036909C-JVD-TRN-01092 | 036909C-JVD-TRN-01092, ROC-TPSK-CECO-T-00024 | IFA | 2019-04-03 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01092 |  | 2019-03-20 | 1
036909C-102B-CN-1733-0042 | Calculation Note For Foundation Of 10-E-1005 | A | 2019-04-03 | IFR | OL1-2K13-0165 | CV | 2019-04-15 | 036909C-JVD-TRN-01348 | 036909C-JVD-TRN-01348, ROC-TPSK-CECO-T-00046 | IFA | 2019-04-30 | 2019-04-23 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01348 |  | 2019-04-16 | 1
036909C-102B-CN-1733-0027 | Calculation Note For Foundation Of 10-E-2635 | A | 2019-04-05 | IFR | OL1-2K13-0154 | CV | 2019-04-15 | 036909C-JVD-TRN-01348 | 036909C-JVD-TRN-01348, ROC-TPSK-CECO-T-00046 | IFA | 2019-04-30 | 2019-04-23 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01348 |  | 2019-04-16 | 1
036909C-102B-CN-1733-0012 | Calculation Note For Foundation of 10-E-2450 | A | 2019-04-09 | IFR | OL1-2K13-0065 | CV | 2019-04-15 | 036909C-JVD-TRN-01348 | 036909C-JVD-TRN-01348, ROC-TPSK-CECO-T-00046 | IFA | 2019-04-30 | 2019-04-23 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01348 |  | 2019-04-16 | 1
036909C-1000-JSS-1160-0001 | ME-022 Special Purpose Gear | 0 | 2019-01-07 | IMP | OL1-2R03-0022 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 | 2019-04-25 | R1-No comments | TPSK-LSPA1-T-ME-00668 |  | 2019-01-23 | 2
036909C-1000-JSS-1112-0001 | ME-020 Special Purpose Steam Tturbines | 0 | 2019-01-07 | IMP | OL1-2R03-0020 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 | 2019-04-25 | R1-No comments | TPSK-LSPA1-T-ME-00668 |  | 2019-01-23 | 2
036909C-1000-JSS-1013-0001 | ME-016 Centrifugal Compressor For PA-IA Servise | 0 | 2019-01-07 | IMP | OL1-2R03-0016 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 | 2019-04-25 | R1-No comments | TPSK-LSPA1-T-ME-00668 |  | 2019-01-23 | 2
036909C-1000-JSS-1011-0001 | ME-014 Centrifugal Compressor | 0 | 2019-01-07 | IMP | OL1-2R03-0014 | ME | 2019-01-23 | 036909C-JVD-TRN-00668 | 036909C-JVD-TRN-00668, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-05 | 2019-04-25 | R1-No comments | TPSK-LSPA1-T-ME-00668 |  | 2019-01-23 | 2
036909C-1056-PDS-0900-5645 | Process Equipment Datasheet - 10-P-5640 A-B - Oily Wastewater EQ Tank Pumps | B | 2019-03-26 | IFD | OL1-2G30-5645 | PE | 2019-03-27 | 036909C-JVD-TRN-01177 | 036909C-JVD-TRN-01177, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-11 |  | Transmitted | TPSK-LSPA1-T-PE-01177 |  | 2019-03-28 | 2
036909C-1025-CN-0014-2507 | PSV-2524 Sizing Calculation | A | 2019-04-22 | IFR | OL1-2G23-2507 | PE | 2019-04-25 | 036909C-JVD-TRN-01488 | 036909C-JVD-TRN-01488 | IFR | 2019-05-10 |  | Transmitted | TPSK-LSPA1-T-PE-01488 |  | 2019-04-26 | 2
036909C-1027-SP-0940-2729 | Mechanical Equipment Datasheet -Wash Oil Pumps | A | 2019-02-19 | IFQ | OL1-2M03-2729 | ME | 2019-02-20 | 036909C-JVD-TRN-00898 | 036909C-JVD-TRN-00898, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-07 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00898 |  | 2019-02-20 | 2
036909C-1023-PDS-0900-2327 | Process Equipment Datasheet - 10-P-2322 - Skim Oil Pump | A | 2019-03-21 | IFR | OL1-2G30-2327 | PE | 2019-03-25 | 036909C-JVD-TRN-01152 | 036909C-JVD-TRN-01152 | IFR | 2019-04-09 | 2019-04-12 | R1-No comments | TPSK-LSPA1-T-PE-01152 |  | 2019-03-26 | 2
036909C-1026-SP-0510-2640 | Mechanical Equipment Data Sheet - C3 Tower | B | 2019-02-13 | IFQ | OL1-2M03-2640 | ME | 2019-02-19 | 036909C-JVD-TRN-00885 | 036909C-JVD-TRN-00885 | IFR | 2019-03-05 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00885 |  | 2019-02-19 | 2
036909C-1023-SP-0510-2300 | Mechanical Equipment Data Sheet - Caustic Tower | C | 2019-02-15 | IFQ | OL1-2M03-2300 | ME | 2019-02-19 | 036909C-JVD-TRN-00883 | 036909C-JVD-TRN-00883, ROC-TPSK-CECO-T-00014 | IFR | 2019-03-05 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME -00883 |  | 2019-02-19 | 2
036909C-1012-CN-0015-1201 | Steam Drum and Superheater PSVs Sizing Calculation | A | 2019-01-23 | IFR | OL1-2G05-1201 | PE | 2019-01-30 | 036909C-JVD-TRN-00769 | 036909C-JVD-TRN-00769 | IFR | 2019-02-15 | 2019-03-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00769 |  | 2019-01-31 | 2
036909C-1056-PDS-0900-5657 | Process Equipment Datasheet - 10-P-5656 A-B - Final Check Basin Pumps | A | 2019-02-05 | IFR | OL1-2G30-5657 | PE | 2019-02-06 | 036909C-JVD-TRN-00810 | 036909C-JVD-TRN-00810, ROC-TPSK-CECO-T-00020 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00810 |  | 2019-02-06 | 2
036909C-1025-SP-0510-2580 | Mechanical Equipment Data Sheet - C2 Tower | B | 2019-03-01 | IFQ | OL1-2M03-2580 | ME | 2019-03-04 | 036909C-JVD-TRN-00981 | 036909C-JVD-TRN-00981, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-19 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-00981 |  | 2019-03-05 | 2
036909C-1025-SP-0510-2580 | Mechanical Equipment Data Sheet - C2 Tower | A | 2018-12-18 | IFQ | OL1-2M03-2580 | ME | 2018-12-20 | 036909C-JVD-TRN-00531 | 036909C-JVD-TRN-00531 | IFR | 2019-01-02 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00531 |  | 2018-12-20 | 2
036909C-1056-PID-0031-5621 | P&ID - Olefins Unit 10 - Wastewater - HP Flare Area Storm Water Collection | A | 2019-02-13 | IFR | OL1-2G43-5621 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1025-SP-0510-2570 | Mechanical Equipment Data Sheet - Deethanizer | B | 2018-12-17 | IFQ | OL1-2M03-2570 | ME | 2018-12-20 | 036909C-JVD-TRN-00547 | 036909C-JVD-TRN-00547 | IFR | 2019-01-02 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00547 |  | 2018-12-20 | 2
036909C-1020-SP-0910-2046 | Mechanical Equipment Datasheet - Heavy Fuel Oil Pumps | A | 2018-11-23 | IFQ | OL1-2M03-2046 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457 | IFR | 2018-12-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00457 |  | 2018-12-10 | 2
036909C-1000-PP-117 | ITC Plan | 0 | 2019-04-11 | IMP | OL1-2W92-0012 | PC | 2019-04-23 | 036909C-JVD-TRN-01444 | 036909C-JVD-TRN-01444 | IFR | 2019-05-08 |  | Transmitted | TPSK-LSPA1-T-PC-01444 |  | 2019-04-24 | 2
036909C-1025-SP-0510-2540 | Mechanical Equipment Data Sheet - Demethanizer Reflux Drum | C | 2019-02-25 | IFQ | OL1-2M03-2540 | ME | 2019-02-27 | 036909C-JVD-TRN-00945 | 036909C-JVD-TRN-00945, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-14 | 2019-03-25 | R1-No comments | TPSK-LSPA1-T-ME-00945 |  | 2019-02-28 | 2
036909C-1020-SP-0510-2000 | Mechanical Equipment Data Sheet - Quench Oil Tower | B | 2019-02-04 | IFQ | OL1-2M03-2000 | ME | 2019-02-06 | 036909C-JVD-TRN-00801 | 036909C-JVD-TRN-00801, ROC-TPSK-CECO-T-00014 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-ME-00801 |  | 2019-02-06 | 2
036909C-1020-SP-0510-2040 | Mechanical Equipment Data Sheet - Heavy Fuel Oil Stripper | C | 2019-02-06 | IFQ | OL1-2M03-2040 | ME | 2019-02-06 | 036909C-JVD-TRN-00815 | 036909C-JVD-TRN-00815, ROC-TPSK-CECO-T-00014 |  |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00815 |  | 2019-02-06 | 2
036909C-1027-PDS-0900-2729 | Process Equipment Datasheet - 10-P-2721 A-B - Wash Oil Pumps | A | 2019-02-12 | IFR | OL1-2G30-2729 | PE | 2019-02-15 | 036909C-JVD-TRN-00873 | 036909C-JVD-TRN-00873 | IFR | 2019-03-04 | 2019-02-26 | R1-No comments | TPSK-LSPA1-T-PE-00873 |  | 2019-02-15 | 2
036909C-1027-PDS-0900-2728 | Process Equipment Datasheet - 10-P-2724 A-B - Recycle Wash Oil Pumps | A | 2019-02-11 | IFR | OL1-2G30-2728 | PE | 2019-02-12 | 036909C-JVD-TRN-00841 | 036909C-JVD-TRN-00841 | IFR | 2019-02-26 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00841 |  | 2019-02-12 | 2
036909C-1020-PDS-0840-2049 | Process Equipment Datasheet - 10-F-2048 A-B - Heavy Fuel Oil Filters | B | 2019-01-16 | IFD | OL1-2G30-2049 | PE | 2019-01-18 | 036909C-JVD-TRN-00676 | 036909C-JVD-TRN-00676 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00676 |  | 2019-01-18 | 2
036909C-1027-PDS-0900-2791 | Process Equipment Datasheet - 10-P-2790 - Light Oil Drain Drum Pump | B | 2019-01-23 | IFD | OL1-2G30-2791 | PE | 2019-01-25 | 036909C-JVD-TRN-00722 | 036909C-JVD-TRN-00722 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00722 |  | 2019-01-25 | 2
036909C-1027-PDS-0900-2791 | Process Equipment Datasheet - 10-P-2790 - Light Oil Drain Drum Pump | A | 2018-12-12 | IFR | OL1-2G30-2791 | PE | 2018-12-13 | 036909C-JVD-TRN-00496 | 036909C-JVD-TRN-00496 | IFR | 2018-12-26 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00496 |  | 2018-12-13 | 2
036909C-1027-PDS-0900-2726 | Process Equipment Datasheet - 10-P-2726 A-B - Pygas Fuel Oil Pumps | A | 2019-02-12 | IFR | OL1-2G30-2726 | PE | 2019-02-15 | 036909C-JVD-TRN-00873 | 036909C-JVD-TRN-00873 | IFR | 2019-03-04 | 2019-02-26 | R1-No comments | TPSK-LSPA1-T-PE-00873 |  | 2019-02-15 | 2
036909C-1027-PDS-0600-2727 | Process Equipment Datasheet - 10-E-2726 - Pygas Fuel Oil Cooler | A | 2019-02-08 | IFR | OL1-2G30-2727 | PE | 2019-02-11 | 036909C-JVD-TRN-00835 | 036909C-JVD-TRN-00835 | IFR | 2019-02-25 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00835 |  | 2019-02-11 | 2
036909C-1053-SP-0910-5371 | Mechanical Equipment Datasheet - CW Filter Backwash Pumps | A | 2019-01-18 | IFQ | OL1-2M03-5371 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716 |  | 2019-01-24 | 2
036909C-1053-PID-0031-5325 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 06 | A | 2018-12-11 | IFR | OL1-2G43-5325 | PE | 2018-12-13 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491, ROC-TPSK-CECO-T-00007 | IFR | 2018-12-26 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00491 |  | 2018-12-13 | 2
036909C-1011-PDS-1543-1152 | Process Equipment Datasheet 10-MOV-1102A USC 36M Decoke Effluent MOV | B | 2019-03-28 | IFD | OL1-2G30-1152 | PE | 2019-03-29 | 036909C-JVD-TRN-01195 | 036909C-JVD-TRN-01195 | IFR |  | 2019-04-22 | R1-No comments | TPSK-LSPA1-T-PE-01195 |  | 2019-04-01 | 2
036909C-1051-PDS-0800-5100 | Process Equipment Datasheet - 10-D-5100 - Deaerator | C | 2019-03-26 | IFD | OL1-2G30-5100 | PE | 2019-03-27 | 036909C-JVD-TRN-01174 | 036909C-JVD-TRN-01174 | IFR | 2019-04-11 | 2019-04-22 | R1-No comments | TPSK-LSPA1-T-PE-01174 |  | 2019-03-28 | 2
036909C-1012-PDS-1542-1212 | Process Equipment Datasheet - 10-ZZ-1200 - 1600 USC 132U Attemperator | A | 2019-01-24 | IFR | OL1-2G31-1212 | PE | 2019-01-29 | 036909C-JVD-TRN-00757 | 036909C-JVD-TRN-00757 | IFR | 2019-02-13 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00757 |  | 2019-01-29 | 2
036909C-1031-PDS-0850-3192 | Process Equipment Datasheet - 10-EJ-3190 - NMP Slop Sump Eductor | A | 2019-03-26 | IFD | OL1-2G30-3192 | PE | 2019-03-26 | 036909C-JVD-TRN-01160 | 036909C-JVD-TRN-01160 | IFR | 2019-04-10 | 2019-04-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01160 |  | 2019-03-27 | 2
036909C-1020-PDS-0850-2092 | Process Equipment Datasheet - 10-EJ-2090 - Quench Oil Drain Sump Eductor | A | 2019-01-03 | IFD | OL1-2G30-2092 | PE | 2019-01-07 | 036909C-JVD-TRN-00595 | 036909C-JVD-TRN-00595, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00595 |  | 2019-01-07 | 2
036909C-1023-PDS-4200-2313 | Process Equipment Datasheet - 10-X-2312 - Spent Wash Oil Mixer | B | 2018-12-17 | IFD | OL1-2G30-2313 | PE | 2018-12-20 | 036909C-JVD-TRN-00525 | 036909C-JVD-TRN-00525, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00525 |  | 2018-12-20 | 2
036909C-1027-PDS-0850-2792 | Process Equipment Datasheet - 10-EJ-2790 - Light Oil Drain Sump Eductor | A | 2019-01-03 | IFD | OL1-2G30-2792 | PE | 2019-01-07 | 036909C-JVD-TRN-00595 | 036909C-JVD-TRN-00595, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00595 |  | 2019-01-07 | 2
036909C-1021-PDS-0850-2192 | Process Equipment Datasheet - 10-EJ-2190 - Quench Water Drain Sump Eductor | A | 2019-01-03 | IFD | OL1-2G30-2192 | PE | 2019-01-07 | 036909C-JVD-TRN-00595 | 036909C-JVD-TRN-00595, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00595 |  | 2019-01-07 | 2
036909C-1023-PDS-0850-2389 | Process Equipment Datasheet - 10-EJ-2390 - Caustic Drain Sump Eductor | A | 2019-01-03 | IFD | OL1-2G30-2389 | PE | 2019-01-07 | 036909C-JVD-TRN-00595 | 036909C-JVD-TRN-00595, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00595 |  | 2019-01-07 | 2
036909C-1023-PDS-0850-2394 | Process Equipment Datasheet - 10-EJ-2392 - Spent Caustic Drain Sump Eductor | A | 2019-01-03 | IFD | OL1-2G30-2394 | PE | 2019-01-07 | 036909C-JVD-TRN-00595 | 036909C-JVD-TRN-00595, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00595 |  | 2019-01-07 | 2
036909C-1023-PDS-4200-2315 | Process Equipment Datasheet - 10-X-2310 - Spent Caustic Mixer | B | 2018-12-17 | IFD | OL1-2G30-2315 | PE | 2018-12-20 | 036909C-JVD-TRN-00525 | 036909C-JVD-TRN-00525, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00525 |  | 2018-12-20 | 2
036909C-1000-QCP-1320-0001 | Quality Control Plan Piping Erection - Above & Underground | A | 2019-01-22 | IFR | OL1-2Q24-0003 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 | 2019-04-05 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00730 |  | 2019-01-28 | 1
036909C-1023-PDS-4200-2301 | Process Equipment Datasheet - 10-X-2300 - Caustic Dilution Mixer | C | 2019-01-04 | IFD | OL1-2G30-2301 | PE | 2019-01-07 | 036909C-JVD-TRN-00600 | 036909C-JVD-TRN-00600, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00600 |  | 2019-01-07 | 2
036909C-1027-PDS-0900-2719 | Process Equipment Datasheet - 10-P-2720 A-B - Rerun Tower Reflux - Product Pumps | A | 2019-02-11 | IFR | OL1-2G30-2719 | PE | 2019-02-12 | 036909C-JVD-TRN-00841 | 036909C-JVD-TRN-00841 | IFR | 2019-02-26 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00841 |  | 2019-02-12 | 2
036909C-1027-PDS-4100-2717 | Process Equipment Datasheet - 10-PK-2720 - Rerun Tower Liquid Ring Pump | A | 2019-02-18 | IFR | OL1-2G30-2717 | PE | 2019-02-20 | 036909C-JVD-TRN-00902 | 036909C-JVD-TRN-00902, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-07 | 2019-03-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-00902 |  | 2019-02-20 | 2
036909C-1020-PDS-0900-2046 | Process Equipment Datasheet - 10-P-2046 A-B - Heavy Fuel Oil Pumps | B | 2019-01-10 | IFD | OL1-2G30-2046 | PE | 2019-01-14 | 036909C-JVD-TRN-00648 | 036909C-JVD-TRN-00648 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00648 |  | 2019-01-14 | 2
036909C-1021-PDS-0840-2138 | Process Equipment Datasheet - 10-F-2136 A-B - Process Water Feed Filters | C | 2019-03-14 | IFD | OL1-2G30-2138 | PE | 2019-03-15 | 036909C-JVD-TRN-01072 | 036909C-JVD-TRN-01072 | IFR | 2019-04-01 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01072 |  | 2019-03-18 | 2
036909C-1021-PDS-0840-2138 | Process Equipment Datasheet - 10-F-2136 A-B - Process Water Feed Filters | B | 2019-01-07 | IFD | OL1-2G30-2138 | PE | 2019-01-07 | 036909C-JVD-TRN-00606 | 036909C-JVD-TRN-00606 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00606 |  | 2019-01-07 | 2
036909C-1029-PID-0021-2908 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Neutralization Injection | A | 2019-01-30 | IFR | OL1-2G43-2908 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-05 | 2
036909C-1059-SP-0940-5955 | Mechanical Equipment Datasheet - CTU NaCOl Metering Pumps | A | 2019-04-04 | IFQ | OL1-2M03-5955 | ME | 2019-04-09 | 036909C-JVD-TRN-01292 | 036909C-JVD-TRN-01292 | IFR | 2019-04-24 |  | Transmitted | TPSK-LSPA1-T-ME-01292 |  | 2019-04-10 | 2
036909C-1059-SP-0940-5951 | Mechanical Equipment Datasheet - Sodium Hypochlorite Metering Pumps | A | 2019-01-16 | IFQ | OL1-2M03-5951 | ME | 2019-01-28 | 036909C-JVD-TRN-00742 | 036909C-JVD-TRN-00742, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-11 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME -00742 |  | 2019-01-28 | 2
036909C-1059-SP-0940-5905 | Mechanical Equipment Datasheet - CTU Sulfuric Acid Metering Pumps | A | 2019-04-04 | IFQ | OL1-2M03-5905 | ME | 2019-04-09 | 036909C-JVD-TRN-01292 | 036909C-JVD-TRN-01292 | IFR | 2019-04-24 |  | Transmitted | TPSK-LSPA1-T-ME-01292 |  | 2019-04-10 | 2
036909C-1059-SP-0940-5902 | Mechanical Equipment Datasheet - Sulfuric Acid Metering Pumps | A | 2019-01-24 | IFQ | OL1-2M03-5902 | ME | 2019-02-01 | 036909C-JVD-TRN-00787 | 036909C-JVD-TRN-00787, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00787 |  | 2019-02-04 | 2
036909C-1056-SP-0910-5622 | Mechanical Equipment Datasheet - Olefins Holding Basin Pumps | A | 2019-01-14 | IFQ | OL1-2M03-5622 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716 |  | 2019-01-24 | 2
036909C-1026-PDS-0600-2666 | Process Equipment Datasheet - 10-E-2666 - Debutanizer Bottoms Cooler | C | 2019-01-21 | IFD | OL1-2G30-2666 | PE | 2019-01-23 | 036909C-JVD-TRN-00711 | 036909C-JVD-TRN-00711 | IFI |  | 2019-02-11 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00711 |  | 2019-01-23 | 1
036909C-1012-DW-0132-2019 | USC 132U Cracking Furnace Seal Boot Details | 0 | 2019-04-12 | IFI | OL1-2M06-2019 | ME | 2019-04-16 | 036909C-JVD-TRN-01368 | 036909C-JVD-TRN-01368 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-01368 |  | 2019-04-17 | 3
036909C-1026-PDS-0900-2663 | Process Equipment Datasheet - 10-P-2660 A-B - Debutanizer Reflux - Product Pumps | C | 2019-01-10 | IFD | OL1-2G30-2663 | PE | 2019-01-14 | 036909C-JVD-TRN-00648 | 036909C-JVD-TRN-00648 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00648 |  | 2019-01-14 | 2
036909C-1023-PDS-0800-2309 | Process Equipment Datasheet - 10-D-2305 - Yellow Oil Drum | C | 2019-04-03 | IFD | OL1-2G30-2309 | PE | 2019-04-04 | 036909C-JVD-TRN-01260 | 036909C-JVD-TRN-01260 | IFR | 2019-04-19 |  | Transmitted | TPSK-LSPA1-T-PE-01260 |  | 2019-04-05 | 2
036909C-1027-PDS-0600-2702 | Process Equipment Datasheet - 10-E-2702 - GHU-1 Start-up Heater | A | 2019-02-18 | IFR | OL1-2G30-2702 | PE | 2019-02-20 | 036909C-JVD-TRN-00899 | 036909C-JVD-TRN-00899, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-07 | 2019-03-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-00899 |  | 2019-02-20 | 2
036909C-1055-PDS-0900-5566 | Process Equipment Datasheet - 10-P-5565 A-B - Polyolefins Flare Knock-out Pumps | A | 2019-01-09 | IFR | OL1-2G30-5566 | PE | 2019-01-10 | 036909C-JVD-TRN-00623 | 036909C-JVD-TRN-00623 | IFR | 2019-01-23 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00623 |  | 2019-01-10 | 2
036909C-1055-PDS-0900-5551 | Process Equipment Datasheet - 10-P-5550 A-B - HP Flare Knock-Out Pumps | B | 2019-01-29 | IFD | OL1-2G30-5551 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00774 |  | 2019-01-31 | 2
036909C-1053-PDS-0900-5371 | Process Equipment Datasheet - 10-P-5370 A-B - CW Filter Backwash Pumps | A | 2019-01-09 | IFR | OL1-2G30-5371 | PE | 2019-01-10 | 036909C-JVD-TRN-00623 | 036909C-JVD-TRN-00623 | IFR | 2019-01-23 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00623 |  | 2019-01-10 | 2
036909C-1020-SP-0910-2091 | Mechanical Equipment Datasheet - Quench Oil Drain Drum Pumps | C | 2019-04-15 | IFQ | OL1-2M03-2091 | ME | 2019-04-15 | 036909C-JVD-TRN-01363 | 036909C-JVD-TRN-01363 | IFR | 2019-04-30 |  | Transmitted | TPSK-LSPA1-T-ME-01363 |  | 2019-04-16 | 2
036909C-1059-SP-0940-5901 | Mechanical Equipment Datasheet - Sulfuric Acid Distribution Pumps | A | 2019-01-30 | IFQ | OL1-2M03-5901 | ME | 2019-02-01 | 036909C-JVD-TRN-00787 | 036909C-JVD-TRN-00787, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00787 |  | 2019-02-04 | 2
036909C-1056-SP-0910-5625 | Mechanical Equipment Datasheet - East Gate House Septic Tank Pumps | A | 2019-02-08 | IFQ | OL1-2M03-5625 | ME | 2019-02-13 | 036909C-JVD-TRN-00847 | 036909C-JVD-TRN-00847, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-27 | 2019-03-11 | R2-Comments as noted | TPSK-LSPA1-T-ME -00847 |  | 2019-02-13 | 2
036909C-1027-PDS-0800-2724 | Process Equipment Datasheet - 10-D-2724 - Wash Oil Degrassing Drum | A | 2019-01-28 | IFR | OL1-2G30-2724 | PE | 2019-02-01 | 036909C-JVD-TRN-00781 | 036909C-JVD-TRN-00781 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00781 |  | 2019-02-01 | 2
036909C-1027-PDS-0600-2723 | Process Equipment Datasheet - 10-E-2724 - Wash Oil Condenser | A | 2019-02-05 | IFR | OL1-2G30-2723 | PE | 2019-02-11 | 036909C-JVD-TRN-00835 | 036909C-JVD-TRN-00835 | IFR | 2019-02-25 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00835 |  | 2019-02-11 | 2
036909C-102E-CN-1733-0034 | Calculation Note For Foundation Of 10-D-2440 | A | 2019-03-25 | IFR | OL1-2K13-0152 | CV | 2019-03-27 | 036909C-JVD-TRN-01168 | 036909C-JVD-TRN-01168, ROC-TPSK-CECO-T-00028 | IFA | 2019-04-11 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01168 |  | 2019-03-28 | 1
036909C-102E-CN-1733-0033 | Calculation Note For Foundation Of 10-D-2460 | A | 2019-03-25 | IFR | OL1-2K13-0151 | CV | 2019-03-27 | 036909C-JVD-TRN-01168 | 036909C-JVD-TRN-01168, ROC-TPSK-CECO-T-00028 | IFA | 2019-04-11 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01168 |  | 2019-03-28 | 1
036909C-102E-CN-1733-0029 | Calculation Note For Foundation Of 10-D-2480A | A | 2019-03-25 | IFR | OL1-2K13-0094 | CV | 2019-03-27 | 036909C-JVD-TRN-01168 | 036909C-JVD-TRN-01168, ROC-TPSK-CECO-T-00028 | IFA | 2019-04-11 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01168 |  | 2019-03-28 | 1
036909C-102E-CN-1733-0014 | Calculation Note For Foundation Of 10-D-2411 | A | 2019-03-25 | IFR | OL1-2K13-0055 | CV | 2019-03-27 | 036909C-JVD-TRN-01168 | 036909C-JVD-TRN-01168, ROC-TPSK-CECO-T-00028 | IFA | 2019-04-11 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01168 |  | 2019-03-28 | 1
036909C-102E-CN-1733-0012 | Calculation Note For Foundation Of 10-D-2405 | A | 2019-03-25 | IFR | OL1-2K13-0048 | CV | 2019-03-27 | 036909C-JVD-TRN-01168 | 036909C-JVD-TRN-01168, ROC-TPSK-CECO-T-00028 | IFA | 2019-04-11 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01168 |  | 2019-03-28 | 1
036909C-102E-CN-1733-0011 | Calculation Note For Foundation Of 10-D-2230 | A | 2019-03-25 | IFR | OL1-2K13-0047 | CV | 2019-03-27 | 036909C-JVD-TRN-01168 | 036909C-JVD-TRN-01168, ROC-TPSK-CECO-T-00028 | IFA | 2019-04-11 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01168 |  | 2019-03-28 | 1
036909C-102E-CN-1733-0010 | Calculation Note For Foundation Of 10-D-2210 | A | 2019-03-25 | IFR | OL1-2K13-0046 | CV | 2019-03-27 | 036909C-JVD-TRN-01168 | 036909C-JVD-TRN-01168, ROC-TPSK-CECO-T-00028 | IFA | 2019-04-11 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01168 |  | 2019-03-28 | 1
036909C-102D-CN-1733-0004 | Calculation Note For Foundation Of 10-T-2570 | A | 2019-03-21 | IFR | OL1-2K13-0090 | CV | 2019-03-27 | 036909C-JVD-TRN-01168 | 036909C-JVD-TRN-01168, ROC-TPSK-CECO-T-00028 | IFA | 2019-04-11 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01168 |  | 2019-03-28 | 1
036909C-102D-CN-1733-0002 | Calculation Note For Foundation Of 10-T-2580 | A | 2019-03-22 | IFR | OL1-2K13-0088 | CV | 2019-03-27 | 036909C-JVD-TRN-01168 | 036909C-JVD-TRN-01168, ROC-TPSK-CECO-T-00028 | IFA | 2019-04-11 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01168 |  | 2019-03-28 | 1
036909C-102D-CN-1733-0037 | Calculation Note For Foundation of 10-E-2855 | A | 2019-03-19 | IFR | OL1-2K13-0128 | CV | 2019-03-21 | 036909C-JVD-TRN-01126 | 036909C-JVD-TRN-01126, ROC-TPSK-CECO-T-00024 | IFA | 2019-04-05 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01126 |  | 2019-03-22 | 1
036909C-102D-DW-1743-0006 | Foundation For 10-T-2640 | A | 2019-03-13 | IFR | OL1-2K34-0095 | CV | 2019-03-20 | 036909C-JVD-TRN-01105 | 036909C-JVD-TRN-01105, ROC-TPSK-CECO-T-00023 | IFR | 2019-04-04 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01105 |  | 2019-03-20 | 2
036909C-1027-PDS-0600-2721 | Process Equipment Datasheet - 10-E-2720 - Rerun Tower Condenser | B | 2019-04-12 | IFD | OL1-2G30-2721 | PE | 2019-04-12 | 036909C-JVD-TRN-01341 | 036909C-JVD-TRN-01341 | IFR | 2019-04-29 |  | Transmitted | TPSK-LSPA1-T-PE-01341 |  | 2019-04-15 | 2
036909C-102D-CN-1733-0014 | Calculation Note For Foundation Of 10-D-2555 | A | 2019-03-15 | IFR | OL1-2K13-0102 | CV | 2019-03-19 | 036909C-JVD-TRN-01092 | 036909C-JVD-TRN-01092, ROC-TPSK-CECO-T-00024 | IFA | 2019-04-03 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01092 |  | 2019-03-20 | 1
036909C-102A-CN-1733-0033 | Calculation Note For Foundation Of 10-T-2020 | A | 2019-03-18 | IFR | OL1-2K13-0323 | CV | 2019-03-19 | 036909C-JVD-TRN-01092 | 036909C-JVD-TRN-01092, ROC-TPSK-CECO-T-00024 | IFA | 2019-04-03 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01092 |  | 2019-03-20 | 1
036909C-102A-CN-1733-0032 | Calculation Note For Foundation of 10-T-2000 | A | 2019-03-18 | IFR | OL1-2K13-0322 | CV | 2019-03-19 | 036909C-JVD-TRN-01092 | 036909C-JVD-TRN-01092, ROC-TPSK-CECO-T-00024 | IFA | 2019-04-03 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01092 |  | 2019-03-20 | 1
036909C-102D-CN-1733-0027 | Calculation Note For Foundation of 10-E-2645A-B | A | 2019-03-06 | IFR | OL1-2K13-0116 | CV | 2019-03-14 | 036909C-JVD-TRN-01059 | 036909C-JVD-TRN-01059, 036909C-JVD-TRN-01071 | IFA | 2019-03-29 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSL-LSPA1-T-CV-01059 |  | 2019-03-15 | 1
036909C-102E-CN-1733-0009 | Calculation Note For Foundation Of 10-D-2220 | A | 2019-03-07 | IFR | OL1-2K13-0045 | CV | 2019-03-12 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-27 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13 | 1
036909C-102E-CN-1733-0008 | Calculation Note For Foundation Of 10-D-2445 | A | 2019-03-07 | IFR | OL1-2K13-0043 | CV | 2019-03-12 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-27 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13 | 1
036909C-102E-CN-1733-0007 | Calculation Note For Foundation Of 10-D-2245 | A | 2019-03-11 | IFR | OL1-2K13-0042 | CV | 2019-03-12 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-27 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13 | 1
036909C-102E-CN-1733-0006 | Calculation Note For Foundation Of 10-D-2240 | A | 2019-03-07 | IFR | OL1-2K13-0041 | CV | 2019-03-12 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-27 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13 | 1
036909C-102E-CN-1733-0004 | Calculation Note For Foundation Of 10-D-2435 | A | 2019-03-11 | IFR | OL1-2K13-0039 | CV | 2019-03-12 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-27 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13 | 1
036909C-102E-CN-1733-0003 | Calculation Note For Foundation Of 10-D-2410 A/B/C | A | 2019-03-11 | IFR | OL1-2K13-0038 | CV | 2019-03-12 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-27 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13 | 1
036909C-102D-CN-1733-0039 | Calculation Note For Foundation Of 10-E-2852 | A | 2019-03-08 | IFR | OL1-2K13-0130 | CV | 2019-03-12 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-27 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13 | 1
036909C-102B-CN-1733-0043 | Calculation Note For Foundation Of 10-E-1015 | A | 2019-03-05 | IFR | OL1-2K13-0162 | CV | 2019-03-12 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-27 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13 | 1
036909C-102B-CN-1733-0041 | Calculation Note For Foundation Of 10-E-1001 | A | 2019-03-05 | IFR | OL1-2K13-0163 | CV | 2019-03-12 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-27 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13 | 1
036909C-102B-CN-1733-0019 | Calculation Note For Foundation Of 10-E-2620 | A | 2019-03-05 | IFR | OL1-2K13-0140 | CV | 2019-03-12 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-27 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13 | 1
036909C-101B-CN-1733-0003 | Calculation Note For Foundation Of 10-E-5210 | A | 2019-03-11 | IFR | OL1-2K13-0006 | CV | 2019-03-12 | 036909C-JVD-TRN-01033 | 036909C-JVD-TRN-01033, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-27 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01033 |  | 2019-03-13 | 1
036909C-102A-DW-1743-0003 | Foundation For 10-T-2100 | A | 2019-02-05 | IFR | OL1-2K34-1040 | CV | 2019-02-21 | 036909C-JVD-TRN-00903 | 036909C-JVD-TRN-00903 | IFR | 2019-03-08 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00903 |  | 2019-02-21 | 2
036909C-102D-DW-1743-0043 | Foundation For 10-E-2582 | A | 2019-02-07 | IFR | OL1-2K34-0139 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854 | IFR | 2019-03-01 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15 | 2
036909C-1021-TDS-0661-2101 | Mechanical Equipment Data Sheet - 10-E-2100 - Quench Water Cooler | 0 | 2019-02-25 | IFP | OL1-2M03-2101 | ME | 2019-02-25 | 036909C-JVD-TRN-00930 | 036909C-JVD-TRN-00930, ROC-TPSK-CECO-T-00017 | IFR | 2019-03-12 | 2019-03-25 | R1-No comments | TPSK-LSPA1-T-ME -0930 |  | 2019-02-26 | 2
036909C-1027-PDS-0600-2721 | Process Equipment Datasheet - 10-E-2720 - Rerun Tower Condenser | A | 2019-02-04 | IFR | OL1-2G30-2721 | PE | 2019-02-11 | 036909C-JVD-TRN-00835 | 036909C-JVD-TRN-00835 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00835 |  | 2019-02-11 | 2
036909C-1027-PDS-0500-2720 | Process Equipment Datasheet - 10-T-2720 - Rerun Tower | A | 2019-01-17 | IFR | OL1-2G30-2720 | PE | 2019-01-22 | 036909C-JVD-TRN-00699 | 036909C-JVD-TRN-00699 | IFR | 2019-02-04 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00669 |  | 2019-01-22 | 2
036909C-1021-PDS-0900-2106 | Process Equipment Datasheet - 10-P-2106 A-C - Quench Water Pumps | C | 2019-03-26 | IFD | OL1-2G30-2106 | PE | 2019-03-26 | 036909C-JVD-TRN-01159 | 036909C-JVD-TRN-01159 | IFR | 2019-04-10 | 2019-04-12 | R1-No comments | TPSK-LSPA1-T-PE-01159 |  | 2019-03-27 | 2
036909C-1021-PDS-0900-2105 | Process Equipment Datasheet - 10-P-2105 A-B - Quench Oil Reflux Pumps | C | 2019-03-26 | IFD | OL1-2G30-2105 | PE | 2019-03-26 | 036909C-JVD-TRN-01159 | 036909C-JVD-TRN-01159 | IFR | 2019-04-10 | 2019-04-12 | R1-No comments | TPSK-LSPA1-T-PE-01159 |  | 2019-03-27 | 2
036909C-1020-PDS-0900-2091 | Process Equipment Datasheet - 10-P-2090 A-B - Quench Oil Drain Drum Pumps | C | 2019-03-26 | IFD | OL1-2G30-2091 | PE | 2019-03-26 | 036909C-JVD-TRN-01159 | 036909C-JVD-TRN-01159 | IFR | 2019-04-10 | 2019-04-12 | R1-No comments | TPSK-LSPA1-T-PE-01159 |  | 2019-03-27 | 2
036909C-1020-PDS-0900-2006 | Process Equipment Datasheet - 10-P-2006 A-C - Quench Oil Pumps | C | 2019-03-26 | IFD | OL1-2G30-2006 | PE | 2019-03-26 | 036909C-JVD-TRN-01159 | 036909C-JVD-TRN-01159 | IFR | 2019-04-10 | 2019-04-12 | R1-No comments | TPSK-LSPA1-T-PE-01159 |  | 2019-03-27 | 2
036909C-1000-PP-255 | 3D Modeling Procedure For Piping Designers | 0 | 2019-03-11 | IMP | OL1-2R07-0027 | ME | 2019-03-21 | 036909C-JVD-TRN-01127 | 036909C-JVD-TRN-01127 |  | 2019-04-05 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-01127 |  | 2019-03-22 | 2
036909C-1012-PDS-0117-1205 | Process Equipment Datasheet - 10-H-1200/1600 - API Fired Heater Process Datasheet | A | 2019-02-05 | IFR | OL1-2G30-1205 | PE | 2019-02-06 | 036909C-JVD-TRN-00814 | 036909C-JVD-TRN-00814 | IFR | 2019-02-20 |  | Transmitted | TPSK-LSPA1-T-PE-00814 |  | 2019-02-06 | 2
036909C-1055-PDS-0180-5570 | Process Equipment Datasheet - 10-PK-5570 - Enclosed Ground Flare Package | A | 2019-02-28 | IFR | OL1-2G30-5570 | PE | 2019-03-01 | 036909C-JVD-TRN-00959 | 036909C-JVD-TRN-00959, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-16 | 2019-03-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00959 |  | 2019-03-04 | 2
036909C-1059-PDS-0900-5955 | Process Equipment Datasheet - 10-P-5955 A-B - CTU NaOCL Metering Pumps | A | 2019-03-20 | IFD | OL1-2G30-5955 | PE | 2019-03-21 | 036909C-JVD-TRN-01129 | 036909C-JVD-TRN-01129 | IFR | 2019-04-05 | 2019-04-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01129 |  | 2019-03-22 | 2
036909C-1059-PDS-0900-5905 | Process Equipment Datasheet - 10-P-5905 A-B - CTU Sulfuric Acid Metering Pumps | A | 2019-03-20 | IFD | OL1-2G30-5905 | PE | 2019-03-21 | 036909C-JVD-TRN-01129 | 036909C-JVD-TRN-01129 | IFR | 2019-04-05 | 2019-04-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01129 |  | 2019-03-22 | 2
036909C-1059-PDS-0900-5902 | Process Equipment Datasheet - 10-P-5901 A-B - Sulfuric Acid Metering Pumps | B | 2019-01-29 | IFD | OL1-2G30-5902 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00774 |  | 2019-01-31 | 2
036909C-1012-PDS-1543-1253 | Process Equipment Datasheet 10-MOV-1202B USC 132U Decoke Effluent Bypass MOV | A | 2018-12-12 | IFR | OL1-2G30-1253 | PE | 2018-12-20 | 036909C-JVD-TRN-00521 | 036909C-JVD-TRN-00521 | IFR | 2019-01-02 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-00521 |  | 2018-12-20 | 2
036909C-1012-PDS-1543-1251 | Process Equipment Datasheet 10-MOV-1201 USC 132U Effluent MOV | A | 2018-12-12 | IFR | OL1-2G30-1251 | PE | 2018-12-20 | 036909C-JVD-TRN-00521 | 036909C-JVD-TRN-00521 | IFR | 2019-01-02 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-00521 |  | 2018-12-20 | 2
036909C-1012-PDS-1543-1252 | Process Equipment Datasheet 10-MOV-1202A USC 132U Decoke Effluent MOV | A | 2018-12-12 | IFR | OL1-2G30-1252 | PE | 2018-12-20 | 036909C-JVD-TRN-00521 | 036909C-JVD-TRN-00521 | IFR | 2019-01-02 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-00521 |  | 2018-12-20 | 2
036909C-1055-PDS-0600-5513 | Process Equipment Datasheet - 10-E-5513 - Methanol Vaporizer | C | 2019-03-26 | IFD | OL1-2G30-5513 | PE | 2019-03-26 | 036909C-JVD-TRN-01161 | 036909C-JVD-TRN-01161 | IFR | 2019-04-10 | 2019-04-11 | R1-No comments | TPSK-LSPA1-T-PE-01161 |  | 2019-03-27 | 2
036909C-1055-PDS-0600-5512 | Process Equipment Datasheet - 10-E-5512 - Cold Flare Superheater | C | 2019-03-26 | IFD | OL1-2G30-5512 | PE | 2019-03-26 | 036909C-JVD-TRN-01161 | 036909C-JVD-TRN-01161 | IFR | 2019-04-10 | 2019-04-11 | R1-No comments | TPSK-LSPA1-T-PE-01161 |  | 2019-03-27 | 2
036909C-1020-SP-0840-2028 | Mechanical Equipment Datasheet - FO Pump Purge Oil Filter | B | 2019-03-14 | IFQ | OL1-2M03-2028 | ME | 2019-03-25 | 036909C-JVD-TRN-01141 | 036909C-JVD-TRN-01141 | IFR | 2019-04-09 | 2019-04-11 | R1-No comments | TPSK-LSPA1-T-ME-01141 |  | 2019-03-26 | 2
036909C-1056-SP-0840-5612 | Mechanical Equipment Datasheet - Hydroblast Filter | B | 2019-03-18 | IFQ | OL1-2M03-5612 | ME | 2019-03-25 | 036909C-JVD-TRN-01141 | 036909C-JVD-TRN-01141 | IFR | 2019-04-09 | 2019-04-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-01141 |  | 2019-03-26 | 2
036909C-1024-PDS-0800-2410 | Process Equipment Datasheet - 10-D-2410 A-B - Cracked Gas Dryer | C | 2019-03-02 | IFD | OL1-2G30-2410 | PE | 2019-03-04 | 036909C-JVD-TRN-00980 | 036909C-JVD-TRN-00980 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00980 |  | 2019-03-05 | 2
036909C-1026-PID-0021-2631 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Bottoms Pumps | A | 2019-01-10 | IFR | OL1-2G43-2631 | PE | 2019-01-16 | 036909C-JVD-TRN-00653 | 036909C-JVD-TRN-00653, ROC-TPSK-CECO-T-00008 | IFR | 2019-01-29 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00653 |  | 2019-01-16 | 2
036909C-1026-PDS-0900-2669 | Process Equipment Datasheet - 10-P-2665 A-B - Debutanizer Bottoms Pumps | 0 | 2019-03-18 | CAN | OL1-2G30-2669 | PE | 2019-03-19 | 036909C-JVD-TRN-01099 | 036909C-JVD-TRN-01099 | IFR | 2019-04-03 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01099 |  | 2019-03-20 | 2
036909C-1023-PDS-0850-2323 | Process Equipment Datasheet - 10-EJ-2322 - Skim Oil Sump Eductor | 0 | 2019-03-18 | CAN | OL1-2G30-2323 | PE | 2019-03-19 | 036909C-JVD-TRN-01098 | 036909C-JVD-TRN-01098, ROC-TPSK-CECO-T-00019 | IFR | 2019-04-03 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01098 |  | 2019-03-20 | 2
036909C-1055-PDS-1000-5521 | Process Equipment Datasheet - 10-PK-5520 - LP Vent Blower Pkg | 0 | 2019-03-19 | CAN | OL1-2G30-5521 | PE | 2019-03-20 | 036909C-JVD-TRN-01112 | 036909C-JVD-TRN-01112 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01112 |  | 2019-03-21 | 2
036909C-1011-PDS-0610-1110 | Process Equipment Datasheet - 10-E-1120 - USC 36M TLX-2 Quench Exchanger | C | 2019-03-14 | IFD | OL1-2G30-1110 | PE | 2019-03-15 | 036909C-JVD-TRN-01078 | 036909C-JVD-TRN-01078 | IFR | 2019-03-30 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01078 |  | 2019-03-18 | 2
036909C-1056-SP-0910-5638 | Mechanical Equipment Datasheet - HP Flare Area SW Sump Pumps | B | 2019-03-12 | IFQ | OL1-2M03-5638 | ME | 2019-03-20 | 036909C-JVD-TRN-01102 | 036909C-JVD-TRN-01102, ROC-TPSK-CECO-T-00016 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-ME-01102 |  | 2019-03-21 | 2
036909C-1011-PDS-0610-1109 | Process Equipment Datasheet - 10-E-1110 - USC 36M TLX-1 Quench Exchanger | C | 2019-03-14 | IFD | OL1-2G30-1109 | PE | 2019-03-15 | 036909C-JVD-TRN-01078 | 036909C-JVD-TRN-01078 | IFR | 2019-03-30 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01078 |  | 2019-03-18 | 2
036909C-1021-PDS-0840-2104 | Process Equipment Datasheet - 10-F-2105 A-B - Quench Oil Reflux Filter | C | 2019-03-14 | IFD | OL1-2G30-2104 | PE | 2019-03-15 | 036909C-JVD-TRN-01072 | 036909C-JVD-TRN-01072 | IFR | 2019-04-01 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01072 |  | 2019-03-18 | 2
036909C-1000-QCP-2300-0001 | Quality Control Plan Painting | A | 2019-01-21 | IFR | OL1-2Q24-0010 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 | 2019-04-05 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00730 |  | 2019-01-28 | 1
036909C-1000-QCP-2200-0001 | Quality Control Plan Insulation | A | 2019-01-21 | IFR | OL1-2Q24-0009 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 | 2019-04-05 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00730 |  | 2019-01-28 | 1
036909C-1000-QCP-1399-0001 | Quality Control Plan Welders Management | A | 2019-01-22 | IFR | OL1-2Q24-0008 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 | 2019-04-05 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00730 |  | 2019-01-28 | 1
036909C-1000-QCP-1390-0001 | Quality Control Plan Piping NDE PWHT Management | A | 2019-01-22 | IFR | OL1-2Q24-0007 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 | 2019-04-05 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00730 |  | 2019-01-28 | 1
036909C-1000-QCP-1370-0001 | Quality Control Plan Piping Tie-ins | A | 2019-01-22 | IFR | OL1-2Q24-0006 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 | 2019-04-05 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00730 |  | 2019-01-28 | 1
036909C-1000-QCP-1330-0001 | Quality Control Plan Steam Tracing System | A | 2019-01-22 | IFR | OL1-2Q24-0005 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 | 2019-04-05 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00730 |  | 2019-01-28 | 1
036909C-1000-QCP-1320-0002 | Quality Control Plan Piping Support Erection | A | 2019-01-22 | IFR | OL1-2Q24-0004 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 | 2019-04-05 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00730 |  | 2019-01-28 | 1
036909C-1000-QCP-1310-0002 | Quality Control Plan Piping Support Prefabrication | A | 2019-01-22 | IFR | OL1-2Q24-0002 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 | 2019-04-05 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00730 |  | 2019-01-28 | 1
036909C-1000-QCP-1310-0001 | Quality Control Plan Piping Prefabrication | A | 2019-01-22 | IFR | OL1-2Q24-0001 | QM | 2019-01-28 | 036909C-JVD-TRN-00730 | 036909C-JVD-TRN-00730 | IFA | 2019-02-11 | 2019-04-05 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00730 |  | 2019-01-28 | 1
036909C-1056-PDS-0200-5610 | Process Equipment Datasheet - 10-PIT-5610 - Hydroblast Sump | A | 2019-01-04 | IFR | OL1-2G30-5610 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589, ROC-TPSK-CECO-T-00020 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1019-PDS-0800-1912 | Process Equipment Datasheet - 10-D-1912 - DMDS Injection Drum | A | 2019-01-17 | IFR | OL1-2G30-1912 | PE | 2019-01-22 | 036909C-JVD-TRN-00686 | 036909C-JVD-TRN-00686 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00686 |  | 2019-01-22 | 2
036909C-1019-PDS-0800-1911 | Process Equipment Datasheet - 10-D-1910 - DMDS Bulk Storage Drum | A | 2019-01-17 | IFR | OL1-2G30-1911 | PE | 2019-01-22 | 036909C-JVD-TRN-00686 | 036909C-JVD-TRN-00686 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00686 |  | 2019-01-22 | 2
036909C-1056-SP-0910-5611 | Mechanical Equipment Datasheet - Hydroblast Sump Pump | A | 2019-01-15 | IFQ | OL1-2M03-5611 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716 |  | 2019-01-24 | 2
036909C-1029-SP-0940-2911 | Mechanical Equipment Datasheet - Wash Oil Injection Pump | A | 2019-02-20 | IFQ | OL1-2M03-2911 | ME | 2019-02-25 | 036909C-JVD-TRN-00925 | 036909C-JVD-TRN-00925, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-12 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00925 |  | 2019-02-26 | 2
036909C-1027-PDS-0800-2735 | Process Equipment Datasheet - 10-D-2735 - Regen Hydrog Drum | A | 2019-03-13 | IFR | OL1-2G30-2735 | PE | 2019-03-13 | 036909C-JVD-TRN-01049 | 036909C-JVD-TRN-01049 | IFR | 2019-03-28 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-PE-01049 |  | 2019-03-14 | 2
036909C-1021-PDS-0600-2165 | Process Equipment Datasheet - 10-E-2165 A-D - DSG Reboilers | B | 2018-12-07 | IFD | OL1-2G30-2165 | PE | 2018-12-10 | 036909C-JVD-TRN-00467 | 036909C-JVD-TRN-00467 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00467 |  | 2018-12-10 | 2
036909C-1051-TDS-0610-5103 | Mechanical Equipment Data Sheet - 10-E-5100 - Deaerator Vent Condenser | 0 | 2019-03-29 | CAN | OL1-2M03-5103 | ME | 2019-04-04 | 036909C-JVD-TRN-01252 | 036909C-JVD-TRN-01252 | IFR | 2019-04-19 |  | Transmitted | TPSK-LSPA1-T-ME-01252 |  | 2019-04-05 | 2
036909C-1020-PDS-0900-2091 | Process Equipment Datasheet - 10-P-2090 A-B - Quench Oil Drain Drum Pumps | D | 2019-04-03 | IFD | OL1-2G30-2091 | PE | 2019-04-04 | 036909C-JVD-TRN-01255 | 036909C-JVD-TRN-01255 | IFR | 2019-04-19 |  | Transmitted | TPSK-LSPA1-T-PE-01255 |  | 2019-04-05 | 2
036909C-1021-PDS-0600-2101 | Process Equipment Datasheet - 10-E-2100 A-E - Quench Water Cooler | C | 2019-04-03 | IFD | OL1-2G30-2101 | PE | 2019-04-04 | 036909C-JVD-TRN-01261 | 036909C-JVD-TRN-01261 | IFR | 2019-04-19 |  | Transmitted | TPSK-LSPA1-T-PE-01261 |  | 2019-04-05 | 2
036909C-1000-PP-258 | 3D Modeling Procedure for Instrumentation Designers | A | 2018-12-18 | IFR | OL1-2R06-0040 | IE | 2018-12-20 | 036909C-JVD-TRN-00556 | 036909C-JVD-TRN-00556 | IFR | 2018-12-20 | 2019-01-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-00556 |  | 2018-12-20 | 2
036909C-1056-PDS-0840-5612 | Process Equipment Datasheet - 10-F-5610 - Hydroblast Filter | B | 2019-03-07 | IFD | OL1-2G30-5612 | PE | 2019-03-07 | 036909C-JVD-TRN-01009 | 036909C-JVD-TRN-01009 | IFR | 2019-03-22 | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-01009 |  | 2019-03-08 | 2
036909C-1056-PDS-0840-5612 | Process Equipment Datasheet - 10-F-5610 - Hydroblast Filter | A | 2018-12-06 | IFR | OL1-2G30-5612 | PE | 2018-12-10 | 036909C-JVD-TRN-00454 | 036909C-JVD-TRN-00454 | IFR | 2018-12-21 | 2019-03-11 | R1-No comments | TPSK-LSPA1-T-PE-00454 |  | 2018-12-10 | 2
036909C-1055-PDS-0600-5511 | Process Equipment Datasheet - 10-E-5510 - Cold Flare Blowdown Vaporizer | B | 2019-01-09 | IFR | OL1-2G30-5511 | PE | 2019-01-11 | 036909C-JVD-TRN-00626 | 036909C-JVD-TRN-00626 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00626 |  | 2019-01-11 | 2
036909C-1010-PDS-0600-1006 | Process Equipment Datasheet - 10-E-1006 - LPG Feed Steam Heater | A | 2019-03-06 | IFR | OL1-2G30-1006 | PE | 2019-03-06 | 036909C-JVD-TRN-00998 | 036909C-JVD-TRN-00998 | IFR | 2019-03-21 |  | Transmitted | TPSK-LSPA1-T-PE-00998 |  | 2019-03-07 | 2
036909C-1056-PDS-0200-5628 | Process Equipment Datasheet - 10-PIT-5628 - East Gate House Septic Tank | A | 2019-01-02 | IFR | OL1-2G30-5628 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1056-PDS-0900-5622 | Process Equipment Datasheet - 10-P-5620 A-C - Olefins Holding Basin Pumps | A | 2019-01-10 | IFR | OL1-2G30-5622 | PE | 2019-01-11 | 036909C-JVD-TRN-00635 | 036909C-JVD-TRN-00635 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00635 |  | 2019-01-11 | 2
036909C-1020-PDS-0900-2091 | Process Equipment Datasheet - 10-P-2090 A-B - Quench Oil Drain Drum Pumps | B | 2019-02-28 | IFD | OL1-2G30-2091 | PE | 2019-03-01 | 036909C-JVD-TRN-00963 | 036909C-JVD-TRN-00963 | IFR | 2019-03-16 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-PE-00963 |  | 2019-03-04 | 2
036909C-1051-TDS-0610-5103 | Mechanical Equipment Data Sheet - 10-E-5100 - Deaerator Vent Condenser | A | 2019-01-24 | IFQ | OL1-2M03-5103 | ME | 2019-01-29 | 036909C-JVD-TRN-00755 | 036909C-JVD-TRN-00755 | IFR | 2019-02-12 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00755 |  | 2019-01-29 | 2
036909C-1011-PDS-1543-1152 | Process Equipment Datasheet 10-MOV-1102A USC 36M Decoke Effluent MOV | A | 2018-12-12 | IFR | OL1-2G30-1152 | PE | 2018-12-20 | 036909C-JVD-TRN-00521 | 036909C-JVD-TRN-00521 | IFR | 2019-01-02 | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00521 |  | 2018-12-20 | 2
036909C-1012-PDS-0117-1202 | Anticipated Operating Conditions - 10-H-1200_1600 - USC 132U Liquid Cracking Furnace | 1 | 2019-03-28 | IFD | OL1-2G30-1202 | PE | 2019-04-02 | 036909C-JVD-TRN-01232 | 036909C-JVD-TRN-01232 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-01232 |  | 2019-04-03 | 3
036909C-1012-PDS-0853-1212 | Process Equipment Datasheet - 10-ZZ-1200_1600 - USC 132U Attemperator | C | 2019-03-26 | IFD | OL1-2G30-1212 | PE | 2019-04-01 | 036909C-JVD-TRN-01220 | 036909C-JVD-TRN-01220 | IFR | 2019-04-16 |  | Transmitted | TPSK-LSPA1-T-PE-01220 |  | 2019-04-02 | 2
036909C-1000-PP-804 | Construction Management Plan | A | 2019-03-26 | IFR | OL1-2D01-0001 | CM | 2019-03-27 | 036909C-JVD-TRN-01166 | 036909C-JVD-TRN-01166 | IFR | 2019-04-09 |  | Transmitted | TPSK-LSPA1-T-CM-01166 |  | 2019-03-27 | 1
036909C-1024-PDS-0800-2411 | Process Equipment Datasheet - 10-D-2411 - Cracked Gas Mercury Adsorber | C | 2019-03-16 | IFD | OL1-2G30-2411 | PE | 2019-03-18 | 036909C-JVD-TRN-01089 | 036909C-JVD-TRN-01089 | IFR | 2019-04-02 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-PE-01089 |  | 2019-03-19 | 2
036909C-1027-PDS-0900-2714 | Process Equipment Datasheet - 10-P-2714 A-B - C5 Cut Pumps | B | 2019-03-15 | IFD | OL1-2G30-2714 | PE | 2019-03-15 | 036909C-JVD-TRN-01083 | 036909C-JVD-TRN-01083 | IFR | 2019-04-01 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-PE-01083 |  | 2019-03-18 | 2
036909C-1027-PDS-0400-2700 | Process Equipment Datasheet - 10-R-2700 A-B - GHU-1 Reactor | B | 2019-03-15 | IFD | OL1-2G30-2700 | PE | 2019-03-15 | 036909C-JVD-TRN-01081 | 036909C-JVD-TRN-01081 | IFR | 2019-04-01 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-PE-01081 |  | 2019-03-18 | 2
036909C-1026-PDS-0800-2600 | Process Equipment Datasheet - 10-D-2600 A-B - C3 Hydrog Guard Adsorber | C | 2019-03-13 | IFD | OL1-2G30-2600 | PE | 2019-03-13 | 036909C-JVD-TRN-01049 | 036909C-JVD-TRN-01049 | IFR | 2019-03-28 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-PE-01049 |  | 2019-03-14 | 2
036909C-1051-PDS-0600-5103 | Process Equipment Datasheet - 10-E-5100 - Deaerator Vent Condenser | 0 | 2019-03-18 | CAN | OL1-2G30-5103 | PE | 2019-03-19 | 036909C-JVD-TRN-01097 | 036909C-JVD-TRN-01097 | IFR | 2019-04-03 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-PE-01097 |  | 2019-03-20 | 2
036909C-1056-PDS-0900-5611 | Process Equipment Datasheet - 10-P-5610 - Hydroblast Sump Pump | B | 2019-03-13 | IFD | OL1-2G30-5611 | PE | 2019-03-14 | 036909C-JVD-TRN-01051 | 036909C-JVD-TRN-01051 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-PE-01051 |  | 2019-03-15 | 2
036909C-1051-PDS-0900-5141 | Process Equipment Datasheet - 10-P-5140 A-B - Intermittent Blowdown Pumps | B | 2019-03-13 | IFD | OL1-2G30-5141 | PE | 2019-03-14 | 036909C-JVD-TRN-01051 | 036909C-JVD-TRN-01051 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-PE-01051 |  | 2019-03-15 | 2
036909C-1012-PDS-0853-1212 | Process Equipment Datasheet - 10-M-1200-1600 - USC 132U Attemperator | B | 2019-01-24 | IFD | OL1-2G30-1212 | PE | 2019-01-29 | 036909C-JVD-TRN-00752 | 036909C-JVD-TRN-00752 | IFI |  | 2019-03-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00752 |  | 2019-01-29 | 2
036909C-1000-PP-257 | 3D Modeling Procedure For Electrical Designers | A | 2019-01-02 | IFR | OL1-2R05-0060 | EE | 2019-01-03 | 036909C-JVD-TRN-00579 | 036909C-JVD-TRN-00579 | IFR | 2019-01-17 | 2019-01-23 | R1-No comments | TPSK-LSPA1-T-EE-00579 |  | 2019-01-03 | 2
036909C-1012-SR-0122-2004 | Scope of Supply for Radiant Coil Assemblies | 0 | 2018-12-10 | IFP | OL1-2M56-2004 | ME | 2018-12-14 | 036909C-JVD-TRN-00499 | 036909C-JVD-TRN-00499 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00499 |  | 2018-12-14 | 3
036909C-1012-SP-0122-2004 | Particular Technical Specification For Radiant Coil Assemblies | 0 | 2018-12-11 | IFP | OL1-2M57-2004 | ME | 2018-12-14 | 036909C-JVD-TRN-00499 | 036909C-JVD-TRN-00499 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00499 |  | 2018-12-14 | 3
036909C-1012-SR-0137-2010 | Scope of Supply for MOVs | A | 2018-12-12 | IFQ | OL1-2M56-2010 | ME | 2018-12-18 | 036909C-JVD-TRN-00534 | 036909C-JVD-TRN-00534 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00534 |  | 2018-12-18 | 3
036909C-1027-PDS-0400-2760 | Process Equipment Datasheet - 10-R-2760 - C4-C5 Hydrog Reactor | B | 2019-03-07 | IFD | OL1-2G30-2760 | PE | 2019-03-11 | 036909C-JVD-TRN-01030 | 036909C-JVD-TRN-01030 | IFR | 2019-03-26 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-PE-01030 |  | 2019-03-12 | 2
036909C-1027-PDS-0900-2713 | Process Equipment Datasheet - 10-P-2710 A-B - Depentanizer Reflux Pump | B | 2019-03-08 | IFD | OL1-2G30-2713 | PE | 2019-03-11 | 036909C-JVD-TRN-01025 | 036909C-JVD-TRN-01025 | IFR | 2019-03-26 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-PE-01025 |  | 2019-03-12 | 2
036909C-102A-CN-1733-0014 | Calculation Note For Foundation Of 10-E-2146 | A | 2019-02-05 | IFR | OL1-2K13-0020 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843 |  | 2019-02-12 | 1
036909C-102D-CN-1733-0026 | Calculation Note For Foundation Of 10-E-2576 | A | 2019-03-06 | IFR | OL1-2K13-0115 | CV | 2019-03-07 | 036909C-JVD-TRN-01005 | 036909C-JVD-TRN-01005, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-22 | 2019-03-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01005 |  | 2019-03-08 | 1
036909C-102B-CN-1733-0028 | Calculation Note For Foundation Of 10-E-2636 | A | 2019-02-22 | IFR | OL1-2K13-0155 | CV | 2019-03-07 | 036909C-JVD-TRN-01005 | 036909C-JVD-TRN-01005, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-22 | 2019-03-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01005 |  | 2019-03-08 | 1
036909C-102B-CN-1733-0014 | Calculation Note for Foundation of 10-E-2630 | A | 2019-02-22 | IFR | OL1-2K13-0072 | CV | 2019-03-07 | 036909C-JVD-TRN-01005 | 036909C-JVD-TRN-01005, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-22 | 2019-03-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01005 |  | 2019-03-08 | 1
036909C-102A-CN-1733-0012 | Calculation Note For Foundation Of 10-E-2166 | A | 2019-03-06 | IFR | OL1-2K13-0018 | CV | 2019-03-07 | 036909C-JVD-TRN-01005 | 036909C-JVD-TRN-01005, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-22 | 2019-03-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01005 |  | 2019-03-08 | 1
036909C-102D-CN-1733-0029 | Calculation Note For Foundation Of 10-E-2515 | A | 2019-02-26 | IFR | OL1-2K13-0118 | CV | 2019-03-06 | 036909C-JVD-TRN-00992 | 036909C-JVD-TRN-00992, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-21 | 2019-03-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00992 |  | 2019-03-07 | 1
036909C-102A-CN-1733-0010 | Calculation Note For Foundation Of 10-E-2136 | A | 2019-02-28 | IFR | OL1-2K13-0016 | CV | 2019-03-06 | 036909C-JVD-TRN-00992 | 036909C-JVD-TRN-00992, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-21 | 2019-03-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00992 |  | 2019-03-07 | 1
036909C-101B-CN-1733-0002 | Calculation Note For Foundation Of 10-E-5200 | A | 2019-02-19 | IFR | OL1-2K13-0005 | CV | 2019-02-27 | 036909C-JVD-TRN-00943 | 036909C-JVD-TRN-00943, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-14 | 2019-03-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00943 |  | 2019-02-28 | 1
036909C-1027-PDS-0800-2706 | Process Equipment Datasheet - 10-D-2706 - GHU-1 Cold Separator | A | 2019-01-28 | IFR | OL1-2G30-2706 | PE | 2019-02-01 | 036909C-JVD-TRN-00781 | 036909C-JVD-TRN-00781 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00781 |  | 2019-02-01 | 2
036909C-1027-PDS-0800-2705 | Process Equipment Datasheet - 10-D-2705 - GHU-1 Hot Separator | A | 2019-01-28 | IFR | OL1-2G30-2705 | PE | 2019-02-01 | 036909C-JVD-TRN-00781 | 036909C-JVD-TRN-00781 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00781 |  | 2019-02-01 | 2
036909C-1055-SP-0810-5514 | Mechanical Equipment Data Sheet - Methanol Vaporizer Cond Pot | A | 2019-01-22 | IFQ | OL1-2M03-5514 | ME | 2019-01-23 | 036909C-JVD-TRN-00709 | 036909C-JVD-TRN-00709, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-05 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00709 |  | 2019-01-23 | 2
036909C-1052-SP-0810-5211 | Mechanical Equipment Data Sheet - Pilot Gas Vaporizer Cond Pot | A | 2019-01-18 | IFQ | OL1-2M03-5211 | ME | 2019-01-23 | 036909C-JVD-TRN-00709 | 036909C-JVD-TRN-00709, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-05 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00709 |  | 2019-01-23 | 2
036909C-1000-PP-553 | Construction Environmental And Social Management Plan (CESMP) | A | 2019-03-26 | IFR | OL1-2S92-0005 | ES | 2019-03-27 | 036909C-JVD-TRN-01163 | 036909C-JVD-TRN-01163 | IFR | 2019-04-09 |  | Transmitted | TPSK-LSPA1-T-ES-01163 |  | 2019-03-27 | 1
036909C-1056-PDS-0200-5656 | Process Equipment Datasheet - 10-PIT-5656 - Final Check Basin | A | 2019-02-05 | IFR | OL1-2G30-5656 | PE | 2019-02-06 | 036909C-JVD-TRN-00808 | 036909C-JVD-TRN-00808, ROC-TPSK-CECO-T-00020 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00808 |  | 2019-02-06 | 2
036909C-1056-PDS-0900-5645 | Process Equipment Datasheet - 10-P-5640 A-B - Oily Wastewater EQ Tank Pumps | A | 2019-02-05 | IFR | OL1-2G30-5645 | PE | 2019-02-06 | 036909C-JVD-TRN-00810 | 036909C-JVD-TRN-00810, ROC-TPSK-CECO-T-00020 | IFR | 2019-02-19 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-PE-00810 |  | 2019-02-06 | 2
036909C-1000-PP-202 | HAZOP Procedure | A | 2019-02-15 | IFR | OL1-2L72-0001 | SE | 2019-02-19 | 036909C-JVD-TRN-00882 | 036909C-JVD-TRN-00882 | IFR | 2019-03-05 | 2019-03-21 | R2-Comments as noted | TPSK-LSPA1-T-SE-00882 |  | 2019-02-19 | 2
036909C-1012-SR-0133-2008 | Scope of Supply for Peep Doors | A | 2018-12-06 | IFQ | OL1-2M56-2008 | ME | 2018-12-14 | 036909C-JVD-TRN-00502 | 036909C-JVD-TRN-00502 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00502 |  | 2018-12-14 | 3
036909C-1012-SP-0133-2008 | Particular Technical Specification for Peep Doors | A | 2018-12-06 | IFQ | OL1-2M57-2008 | ME | 2018-12-14 | 036909C-JVD-TRN-00502 | 036909C-JVD-TRN-00502 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00502 |  | 2018-12-14 | 3
036909C-1055-PDS-0900-5501 | Process Equipment Datasheet - 10-P-5500 A-B - Hot Blowdown Pumps | C | 2019-03-09 | IFD | OL1-2G30-5501 | PE | 2019-03-11 | 036909C-JVD-TRN-01022 | 036909C-JVD-TRN-01022 | IFR | 2019-03-26 | 2019-03-27 | R1-No comments | TPSK-LSPA1-T-PE-01022 |  | 2019-03-12 | 2
036909C-1056-PDS-0900-5638 | Process Equipment Datasheet - 10-P-5633 A-B - HP Flare Area SW Sump Pumps | B | 2019-03-09 | IFD | OL1-2G30-5638 | PE | 2019-03-11 | 036909C-JVD-TRN-01019 | 036909C-JVD-TRN-01019 | IFR | 2019-03-26 | 2019-03-27 | R1-No comments | TPSK-LSPA1-T-PE-01019 |  | 2019-03-12 | 2
036909C-1056-PDS-0900-5637 | Process Equipment Datasheet - 10-P-5632 A-B - HP Flare Area Oily WW Sump Pumps | B | 2019-03-09 | IFD | OL1-2G30-5637 | PE | 2019-03-11 | 036909C-JVD-TRN-01019 | 036909C-JVD-TRN-01019 | IFR | 2019-03-26 | 2019-03-27 | R1-No comments | TPSK-LSPA1-T-PE-01019 |  | 2019-03-12 | 2
036909C-102D-CN-1733-0020 | Calculation Note For Foundation Of 10-D-2860 | A | 2019-01-22 | IFR | OL1-2K13-0108 | CV | 2019-01-28 | 036909C-JVD-TRN-00732 | 036909C-JVD-TRN-00732, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-11 | 2019-03-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00732 |  | 2019-01-28 | 1
036909C-102D-CN-1733-0010 | Calculation Note For Foundation Of 10-D-2815 | A | 2019-01-23 | IFR | OL1-2K13-0098 | CV | 2019-01-28 | 036909C-JVD-TRN-00732 | 036909C-JVD-TRN-00732, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-11 | 2019-03-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00732 |  | 2019-01-28 | 1
036909C-102A-CN-1733-0005 | Calculation Note For Foundation of 10-D-2160 | A | 2019-01-23 | IFR | OL1-2K13-0011 | CV | 2019-01-28 | 036909C-JVD-TRN-00732 | 036909C-JVD-TRN-00732, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-11 | 2019-03-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00732 |  | 2019-01-28 | 1
036909C-1029-PDS-0800-2932 | Process Equipment Datasheet - 10-D-2930 - Methanol Drum | B | 2019-02-01 | IFD | OL1-2G30-2932 | PE | 2019-02-01 | 036909C-JVD-TRN-00796 | 036909C-JVD-TRN-00796 | IFI |  | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00796 |  | 2019-02-04 | 2
036909C-1029-PDS-0800-2932 | Process Equipment Datasheet - 10-D-2930 - Methanol Drum | A | 2019-01-10 | IFR | OL1-2G30-2932 | PE | 2019-01-14 | 036909C-JVD-TRN-00644 | 036909C-JVD-TRN-00644 | IFR | 2019-01-28 | 2019-01-31 | R1-No comments | TPSK-LSPA-1-T-PE-00644 |  | 2019-01-14 | 2
036909C-1055-PDS-0600-5512 | Process Equipment Datasheet - 10-E-5512 - Cold Flare Superheater | B | 2019-01-09 | IFR | OL1-2G30-5512 | PE | 2019-01-11 | 036909C-JVD-TRN-00626 | 036909C-JVD-TRN-00626 | IFR | 2019-01-24 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00626 |  | 2019-01-11 | 2
036909C-1055-PDS-0600-5513 | Process Equipment Datasheet - 10-E-5513 - Methanol Vaporizer | B | 2019-01-09 | IFR | OL1-2G30-5513 | PE | 2019-01-11 | 036909C-JVD-TRN-00626 | 036909C-JVD-TRN-00626 | IFR | 2019-01-24 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00626 |  | 2019-01-11 | 2
036909C-1021-PDS-0900-2105 | Process Equipment Datasheet - 10-P-2105 A-B - Quench Oil Reflux Pumps | B | 2019-01-07 | IFD | OL1-2G30-2105 | PE | 2019-01-07 | 036909C-JVD-TRN-00603 | 036909C-JVD-TRN-00603 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00603 |  | 2019-01-07 | 2
036909C-1056-PDS-0900-5625 | Process Equipment Datasheet - 10-P-5628 A-B - East Gate House Septic Tank Pumps | B | 2019-01-29 | IFD | OL1-2G30-5625 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00774 |  | 2019-01-31 | 2
036909C-1056-PDS-0900-5641 | Process Equipment Datasheet - 10-P-5641 - Wastewater EQ Tank Skimmed Oil Pumps | A | 2019-02-05 | IFR | OL1-2G30-5641 | PE | 2019-02-06 | 036909C-JVD-TRN-00810 | 036909C-JVD-TRN-00810, ROC-TPSK-CECO-T-00020 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00810 |  | 2019-02-06 | 2
036909C-1056-PDS-0900-5654 | Process Equipment Datasheet - 10-P-5655 A-B - Equalization Pit Pumps | A | 2019-02-05 | IFR | OL1-2G30-5654 | PE | 2019-02-06 | 036909C-JVD-TRN-00810 | 036909C-JVD-TRN-00810, ROC-TPSK-CECO-T-00020 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00810 |  | 2019-02-06 | 2
036909C-1056-PDS-0900-5674 | Process Equipment Datasheet - 10-P-5675 - Slop Oil Transfer Pump | A | 2019-02-05 | IFR | OL1-2G30-5674 | PE | 2019-02-06 | 036909C-JVD-TRN-00810 | 036909C-JVD-TRN-00810, ROC-TPSK-CECO-T-00020 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00810 |  | 2019-02-06 | 2
036909C-1056-PDS-0900-5677 | Process Equipment Datasheet - 10-P-5676 - Oily Sludge Transfer Pump | A | 2019-02-05 | IFR | OL1-2G30-5677 | PE | 2019-02-06 | 036909C-JVD-TRN-00810 | 036909C-JVD-TRN-00810, ROC-TPSK-CECO-T-00020 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00810 |  | 2019-02-06 | 2
036909C-1027-PDS-0600-2755 | Process Equipment Datasheet - 10-E-2755 - C4 - C5 Hydrog Start-up Heater | A | 2019-02-21 | IFR | OL1-2G30-2755 | PE | 2019-02-25 | 036909C-JVD-TRN-00924 | 036909C-JVD-TRN-00924, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-12 | 2019-03-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-00924 |  | 2019-02-26 | 2
036909C-1020-SP-0840-2028 | Mechanical Equipment Datasheet- Fo Pump Purge Oil Filter | A | 2019-01-10 | IFQ | OL1-2M03-2028 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639 |  | 2019-01-11 | 2
036909C-1056-SP-0840-5612 | Mechanical Equipment Datasheet - Hydroblast Filter | A | 2019-01-10 | IFQ | OL1-2M03-5612 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639, ROC-TPSK-CECO-T-00016 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639 |  | 2019-01-11 | 2
036909C-102D-DW-1743-0027 | Foundation For 10-E-2857 | A | 2019-02-04 | IFR | OL1-2K34-0132 | CV | 2019-02-06 | 036909C-JVD-TRN-00807 | 036909C-JVD-TRN-00807, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-20 | 2019-03-18 | R2-Comments as noted | TPSK-LSPA1-T-CV-00807 |  | 2019-02-06 | 2
036909C-102D-DW-1743-0029 | Foundation For 10-E-2576 | A | 2019-03-06 | IFR | OL1-2K34-0122 | CV | 2019-03-07 | 036909C-JVD-TRN-01004 | 036909C-JVD-TRN-01004, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01004 |  | 2019-03-08 | 2
036909C-102D-DW-1743-0032 | Foundation for 10-E-2515 | A | 2019-02-27 | IFR | OL1-2K34-0125 | CV | 2019-03-07 | 036909C-JVD-TRN-01004 | 036909C-JVD-TRN-01004, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01004 |  | 2019-03-08 | 2
036909C-102B-DW-1743-0031 | Foundation For 10-E-2636 | A | 2019-02-22 | IFR | OL1-2K34-0161 | CV | 2019-03-07 | 036909C-JVD-TRN-01004 | 036909C-JVD-TRN-01004, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01004 |  | 2019-03-08 | 2
036909C-102A-DW-1743-0016 | Foundation For 10-E-2166 | A | 2019-03-06 | IFR | OL1-2K34-0023 | CV | 2019-03-07 | 036909C-JVD-TRN-01004 | 036909C-JVD-TRN-01004, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01004 |  | 2019-03-08 | 2
036909C-102A-DW-1743-0013 | Foundation For 10-E-2136 | A | 2019-02-28 | IFR | OL1-2K34-0020 | CV | 2019-03-07 | 036909C-JVD-TRN-01004 | 036909C-JVD-TRN-01004, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01004 |  | 2019-03-08 | 2
036909C-102B-DW-1743-0013 | Foundation For 10-E-2630 | A | 2019-02-22 | IFR | OL1-2K34-0076 | CV | 2019-03-07 | 036909C-JVD-TRN-01004 | 036909C-JVD-TRN-01004, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01004 |  | 2019-03-08 | 2
036909C-101B-DW-1743-0002 | Foundation For 10-E-5200 | A | 2019-02-19 | IFR | OL1-2K34-0008 | CV | 2019-03-07 | 036909C-JVD-TRN-01004 | 036909C-JVD-TRN-01004, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-22 |  | Transmitted | TPSK-LSPA1-T-CV-01004 |  | 2019-03-08 | 2
036909C-102D-CN-1733-0032 | Calculation Note for Foundation Of 10-E-2545 | A | 2019-01-24 | IFR | OL1-2K13-0121 | CV | 2019-01-30 | 036909C-JVD-TRN-00762 | 036909C-JVD-TRN-00762, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-15 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00762 |  | 2019-01-31 | 1
036909C-102D-CN-1733-0043 | Calculation Note For Foundation Of 10-E-2504 | A | 2019-01-23 | IFR | OL1-2K13-0133 | CV | 2019-01-30 | 036909C-JVD-TRN-00762 | 036909C-JVD-TRN-00762, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-15 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00762 |  | 2019-01-31 | 1
036909C-102D-CN-1733-0030 | Calculation Note For Foundation Of 10-E-2546 | A | 2019-02-08 | IFR | OL1-2K13-0119 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843 |  | 2019-02-12 | 1
036909C-102D-CN-1733-0042 | Calculation Note For Foundation of 10-E-2582 | B | 2019-02-19 | IFR | OL1-2K13-0132 | CV | 2019-02-21 | 036909C-JVD-TRN-00904 | 036909C-JVD-TRN-00904, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-08 | 2019-03-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00904 |  | 2019-02-22 | 1
036909C-102D-CN-1733-0031 | Calculation Note For Foundation Of 10-E-2548 | A | 2019-02-01 | IFR | OL1-2K13-0120 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843 |  | 2019-02-12 | 1
036909C-102D-CN-1733-0036 | Calculation Note For Foundation Of 10-E-2856 | A | 2019-02-07 | IFR | OL1-2K13-0127 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843 |  | 2019-02-12 | 1
036909C-102D-CN-1733-0038 | Calculation Note For Foundation Of 10-E-2853 | A | 2019-02-06 | IFR | OL1-2K13-0129 | CV | 2019-02-19 | 036909C-JVD-TRN-00878 | 036909C-JVD-TRN-00878, ROC-TPSK-CECO-T-00024 | IFA | 2019-03-05 | 2019-03-11 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00878 |  | 2019-02-19 | 1
036909C-102D-CN-1733-0003 | Calculation Note For Foundation Of 10-T-2640 | A | 2019-03-13 | IFR | OL1-2K13-0089 | CV | 2019-03-15 | 036909C-JVD-TRN-01071 | 036909C-JVD-TRN-01071, ROC-TPSK-CECO-T-00024 | IFA | 2019-04-01 |  | Transmitted | TPSK-LSPA1-T-CV-01071 |  | 2019-03-18 | 1
036909C-102B-CN-1733-0026 | Calculation Note For Foundation Of 10-D-2600A-B | A | 2019-02-07 | IFR | OL1-2K13-0150 | CV | 2019-02-11 | 036909C-JVD-TRN-00832 | 036909C-JVD-TRN-00832, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-26 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00832 |  | 2019-02-11 | 1
036909C-102B-CN-1733-0003 | Calculation Note for Foundation of 10-D-2455 | A | 2019-02-07 | IFR | OL1-2K13-0044 | CV | 2019-02-11 | 036909C-JVD-TRN-00832 | 036909C-JVD-TRN-00832, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-26 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00832 |  | 2019-02-11 | 1
036909C-102B-CN-1733-0004 | Calculation Note for Foundation of 10-D-2310 | A | 2019-02-05 | IFR | OL1-2K13-0050 | CV | 2019-02-08 | 036909C-JVD-TRN-00827 | 036909C-JVD-TRN-00827, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-25 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00827 |  | 2019-02-08 | 1
036909C-102A-CN-1733-0016 | Calculation Note for Foundation of 10-E-2048 | A | 2019-02-04 | IFR | OL1-2K13-0022 | CV | 2019-02-07 | 036909C-JVD-TRN-00816 | 036909C-JVD-TRN-00816, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-22 | 2019-03-18 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00816 |  | 2019-02-07 | 1
036909C-102B-CN-1733-0013 | Calculation Note for Foundation of 10-D-2305 | A | 2019-02-05 | IFR | OL1-2K13-0071 | CV | 2019-02-08 | 036909C-JVD-TRN-00827 | 036909C-JVD-TRN-00827, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-25 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00827 |  | 2019-02-08 | 1
036909C-102D-CN-1733-0022 | Calculation Note For Foundation Of 10-E-2809 | A | 2019-02-07 | IFR | OL1-2K13-0124 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843 |  | 2019-02-12 | 1
036909C-102D-CN-1733-0017 | Calculation Note For Foundation Of 10-D-2575 | A | 2019-02-08 | IFR | OL1-2K13-0105 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843 |  | 2019-02-12 | 1
036909C-102D-CN-1733-0016 | Calculation Note For Foundation Of 10-E-2807 | A | 2019-02-06 | IFR | OL1-2K13-0123 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843 |  | 2019-02-12 | 1
036909C-102D-CN-1733-0024 | Calculation Note For Foundation Of 10-E-2858 | A | 2019-02-08 | IFR | OL1-2K13-0126 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843 |  | 2019-02-12 | 1
036909C-102D-CN-1733-0021 | Calculation Note For Foundation Of 10-D-2865 | A | 2019-02-05 | IFR | OL1-2K13-0109 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843 |  | 2019-02-12 | 1
036909C-102B-CN-1733-0002 | Calculation Note For Foundation Of 10-T-2330 | A | 2019-02-07 | IFR | OL1-2K13-0037 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843 |  | 2019-02-12 | 1
036909C-102B-CN-1733-0006 | Calculation Note for Foundation of 10-D-2316 | A | 2019-01-28 | IFR | OL1-2K13-0052 | CV | 2019-02-01 | 036909C-JVD-TRN-00783 | 036909C-JVD-TRN-00783, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-18 | 2019-02-25 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00783 |  | 2019-02-01 | 1
036909C-102A-CN-1733-0004 | Calculation Note For Foundation Of 10-D-5150 | A | 2019-02-05 | IFR | OL1-2K13-0010 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843 |  | 2019-02-12 | 1
036909C-101B-CN-1733-0001 | Calculation Note For Foundation Of 10-D-5200 | A | 2019-02-05 | IFR | OL1-2K13-0004 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843 |  | 2019-02-12 | 1
036909C-102A-CN-1733-0015 | Calculation Note For Foundation Of 10-E-2026 | A | 2019-02-07 | IFR | OL1-2K13-0021 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843 |  | 2019-02-12 | 1
036909C-102B-CN-1733-0008 | Calculation Note for Foundation of 10-D-2330 | A | 2019-01-28 | IFR | OL1-2K13-0054 | CV | 2019-02-01 | 036909C-JVD-TRN-00783 | 036909C-JVD-TRN-00783, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-18 | 2019-02-25 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00783 |  | 2019-02-01 | 1
036909C-102B-CN-1733-0025 | Calculation Note For Foundation Of 10-D-2610 | A | 2019-02-07 | IFR | OL1-2K13-0149 | CV | 2019-02-11 | 036909C-JVD-TRN-00832 | 036909C-JVD-TRN-00832, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-26 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00832 |  | 2019-02-11 | 1
036909C-1056-PDS-0200-5604 | Process Equipment Datasheet - 10-PIT-5604 - Refrig Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5604 | PE | 2019-03-04 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05 | 2
036909C-1056-PDS-0200-5631 | Process Equipment Datasheet - 10-PIT-5631 - CWWT Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5631 | PE | 2019-03-04 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05 | 2
036909C-1056-PDS-0200-5601 | Process Equipment Datasheet - 10-PIT-5601 - Butadiene Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5601 | PE | 2019-03-04 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05 | 2
036909C-1056-PDS-0200-5603 | Process Equipment Datasheet - 10-PIT-5603 - CGC Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5603 | PE | 2019-03-04 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05 | 2
036909C-1056-PDS-0200-5630 | Process Equipment Datasheet - 10-PIT-5630 - CT Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5630 | PE | 2019-03-04 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05 | 2
036909C-1056-PDS-0200-5600 | Process Equipment Datahseet - 10-PIT-5600 - Pygas Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5600 | PE | 2019-03-04 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05 | 2
036909C-1056-PDS-0200-5602 | Process Equipment Datasheet - 10-PIT-5602 - QW Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5602 | PE | 2019-03-04 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05 | 2
036909C-1056-PDS-0200-5632 | Process Equipment Datasheet - 10-PIT-5632 - HP Flare Area Oily WW Sump | C | 2019-03-04 | IFD | OL1-2G30-5632 | PE | 2019-03-04 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05 | 2
036909C-1056-PDS-0200-5646 | Process Equipment Datasheet - 10-PIT-5606 - C3 Hydrog Area Oily Wastewater Sump | C | 2019-03-04 | IFD | OL1-2G30-5646 | PE | 2019-03-04 | 036909C-JVD-TRN-00982 | 036909C-JVD-TRN-00982, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-19 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00982 |  | 2019-03-05 | 2
036909C-1053-PDS-0300-5355 | Process Equipment Datasheet - 10-PK-5355 - Side Stream Filter Pkg | C | 2019-01-03 | IFD | OL1-2G30-5355 | PE | 2019-01-08 | 036909C-JVD-TRN-00611 | 036909C-JVD-TRN-00611, ROC-TPSK-CECO-T-00020 | IFI |  | 2019-01-24 | A1-Approved without comments | TPSK-LSPA1-T-PE-00611 |  | 2019-01-08 | 1
036909C-1029-PDS-2600-2931 | Process Equipment Datasheet - 10-PK-2931 - Propanol Injection Pkg | B | 2019-02-12 | IFD | OL1-2G30-2931 | PE | 2019-02-12 | 036909C-JVD-TRN-00846 | 036909C-JVD-TRN-00846, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00846 |  | 2019-02-12 | 2
036909C-1026-PDS-4200-2624 | Process Equipment Datasheet - 10-X-2620 - C3 Hydrog Static Mixer | B | 2019-02-28 | IFD | OL1-2G30-2624 | PE | 2019-03-01 | 036909C-JVD-TRN-00968 | 036909C-JVD-TRN-00968, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-16 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00968 |  | 2019-03-04 | 2
036909C-1025-PDS-0600-2505 | Process Equipment Datasheet - 10-E2506 & 10-E-2508 - Demeth Prefrac Feed Cooler No 3 & No 4 | C | 2019-02-04 | IFD | OL1-2G30-2505 | PE | 2019-02-06 | 036909C-JVD-TRN-00811 | 036909C-JVD-TRN-00811, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00811 |  | 2019-02-06 | 2
036909C-1029-PDS-2600-2922 | Process Equipment Datasheet - 10-PK-2922 - CO Injection Pkg | B | 2019-01-14 | IFD | OL1-2G30-2922 | PE | 2019-01-16 | 036909C-JVD-TRN-00656 | 036909C-JVD-TRN-00656, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-01-31 | R1-No comments | TPSK-LSPA1-T-PE-00656 |  | 2019-01-16 | 2
036909C-1021-PDS-0800-2136 | Process Equipment Datasheet - 10-D-2136 - Process Water Feed Coalescer | B | 2019-01-16 | IFD | OL1-2G30-2136 | PE | 2019-01-18 | 036909C-JVD-TRN-00678 | 036909C-JVD-TRN-00678, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00678 |  | 2019-01-18 | 2
036909C-1020-PDS-4200-2036 | Process Equipment Datasheet - 10-X-2036 - Quench Fitting | B | 2019-01-07 | IFD | OL1-2G30-2036 | PE | 2019-01-07 | 036909C-JVD-TRN-00604 | 036909C-JVD-TRN-00604, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00604 |  | 2019-01-07 | 2
036909C-1055-SP-1040-5522 | Mechanical Equipment Datasheet - LP Vent Blower | A | 2019-01-10 | IFQ | OL1-2M03-5522 | ME | 2019-01-11 | 036909C-JVD-TRN-00640 | 036909C-JVD-TRN-00640, ROC-TPSK-CECO-T-00016 | IFR | 2019-01-24 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00640 |  | 2019-01-11 | 2
036909C-1020-SP-0840-2014 | Mechanical Equipment Datasheet - QO Pump Purge Oil Filter | A | 2019-01-10 | IFQ | OL1-2M03-2014 | ME | 2019-01-11 | 036909C-JVD-TRN-00639 | 036909C-JVD-TRN-00639, ROC-TPSK-CECO-T-00014 | IFR | 2019-01-24 | 2019-01-30 | R2-Comments as noted | TPSK-LSPA1-T-ME-00639 |  | 2019-01-11 | 2
036909C-1019-PDS-0900-1914 | Process Equipment Datasheet - 10-P-1912 - DMDS Presulfiding Injection Pump | B | 2019-02-28 | IFD | OL1-2G30-1914 | PE | 2019-03-01 | 036909C-JVD-TRN-00963 | 036909C-JVD-TRN-00963 | IFR | 2019-03-16 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-PE-00963 |  | 2019-03-04 | 2
036909C-1011-PDS-0853-1112 | Process Equipment Datasheet - 10-M-1100 - USC 36M Attemperator | B | 2019-01-24 | IFD | OL1-2G30-1112 | PE | 2019-01-29 | 036909C-JVD-TRN-00752 | 036909C-JVD-TRN-00752 | IFI |  | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-PE-00752 |  | 2019-01-29 | 2
036909C-1029-PDS-0900-2911 | Process Equipment Datasheet - 10-P-2910 - Wash Oil Injection Pump | B | 2019-02-26 | IFD | OL1-2G30-2911 | PE | 2019-02-26 | 036909C-JVD-TRN-00939 | 036909C-JVD-TRN-00939 | IFR | 2019-03-13 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-PE-00939 |  | 2019-02-27 | 2
036909C-1026-SP-0910-2669 | Mechanical Equipment Datasheet - Debutanizer Bottoms Pumps | 0 | 2019-03-19 | CAN | OL1-2M03-2669 | ME | 2019-03-20 | 036909C-JVD-TRN-01115 | 036909C-JVD-TRN-01115 | IFR | 2019-04-04 |  | Transmitted | TPSK-LSPA1-T-ME-01115 |  | 2019-03-21 | 2
036909C-1026-SP-0910-2669 | Mechanical Equipment Datasheet - Debutanizer Bottoms Pumps | B | 2019-01-31 | IFQ | OL1-2M03-2669 | ME | 2019-02-07 | 036909C-JVD-TRN-00823 | 036909C-JVD-TRN-00823 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00823 |  | 2019-02-07 | 2
036909C-1022-TDS-0610-2206 | Mechanical Equipment Data Sheet - 10-E-2206 - Wash Water Cooler | A | 2019-01-03 | IFQ | OL1-2M03-2206 | ME | 2019-01-07 | 036909C-JVD-TRN-00584 | 036909C-JVD-TRN-00584 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00584 |  | 2019-01-07 | 2
036909C-1056-SP-0910-5638 | Mechanical Equipment Datasheet - HP Flare Area SW Sump Pumps | A | 2019-02-06 | IFQ | OL1-2M03-5638 | ME | 2019-02-07 | 036909C-JVD-TRN-00817 | 036909C-JVD-TRN-00817 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00817 |  | 2019-02-07 | 2
036909C-1056-SP-0910-5637 | Mechanical Equipment Datasheet - HP Flare Area Oily Wastewater Sump Pumps | A | 2019-02-06 | IFQ | OL1-2M03-5637 | ME | 2019-02-07 | 036909C-JVD-TRN-00817 | 036909C-JVD-TRN-00817 | IFR | 2019-02-21 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00817 |  | 2019-02-07 | 2
036909C-1056-SP-0910-5621 | Mechanical Equipment Datasheet - Olefins Holding Basin Skimmed Oil Pump | A | 2019-01-11 | IFQ | OL1-2M03-5621 | ME | 2019-01-28 | 036909C-JVD-TRN-00742 | 036909C-JVD-TRN-00742 | IFR | 2019-02-11 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME -00742 |  | 2019-01-28 | 2
036909C-1029-SP-0940-2934 | Mechanical Equipment Datasheet - Methanol Injection Pump | A | 2019-01-16 | IFQ | OL1-2M03-2934 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716 |  | 2019-01-24 | 2
036909C-1023-PDS-0850-2323 | Process Equipment Datasheet - 10-EJ-2322 - Skim Oil Sump Eductor | A | 2019-01-03 | IFD | OL1-2G30-2323 | PE | 2019-01-07 | 036909C-JVD-TRN-00595 | 036909C-JVD-TRN-00595 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00595 |  | 2019-01-07 | 2
036909C-102A-CN-1733-0034 | Calculation Note For Foundation of 10-T-2100 | A | 2019-02-14 | IFR | OL1-2K13-0324 | CV | 2019-02-21 | 036909C-JVD-TRN-00904 | 036909C-JVD-TRN-00904 | IFA | 2019-03-08 | 2019-03-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00904 |  | 2019-02-22 | 1
036909C-1000-QCP-1812-0002 | Quality Control Plan Secondary Steel Structures Erection - Ladders Platforms Walkways Handrails Gratings | A | 2019-01-21 | IFR | OL1-2Q22-0002 | QM | 2019-01-28 | 036909C-JVD-TRN-00735 | 036909C-JVD-TRN-00735 | IFA | 2019-02-12 | 2019-03-18 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-QM-00735 |  | 2019-01-28 | 1
036909C-1056-PDS-0900-5621 | Process Equipment Datasheet - 10-P-5621 - Olefins Holding Basin Skimmed Oil Pump | B | 2019-01-29 | IFD | OL1-2G30-5621 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00774 |  | 2019-01-31 | 2
036909C-1056-PDS-0900-5648 | Process Equipment Datasheet - 10-P-5606 A-B - C3 Hydrog Area Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5648 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774 |  | 2019-01-31 | 2
036909C-1056-PDS-0900-5636 | Process Equipment Datasheet - 10-P-5631 A-B - CWWT Area Oily WWater Sump Pumps | B | 2019-01-29 | IFD | OL1-2G30-5636 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774 |  | 2019-01-31 | 2
036909C-1056-PDS-0900-5635 | Process Equipment Datasheet - 10-P-5630 A-B - CT Area Oily WWater Sump Pumps | B | 2019-01-29 | IFD | OL1-2G30-5635 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774 |  | 2019-01-31 | 2
036909C-1056-PDS-0900-5613 | Process Equipment Datasheet - 10-P-5604 A-B - Refrig Area Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5613 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774 |  | 2019-01-31 | 2
036909C-1056-PDS-0900-5616 | Process Equipment Datasheet - 10-P-5615 A-B - Olefins Stormwater Sump Pumps | B | 2019-01-29 | IFD | OL1-2G30-5616 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774 |  | 2019-01-31 | 2
036909C-1056-PDS-0900-5608 | Process Equipment Datasheet - 10-P-5602 A-B - QW Area Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5608 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774 |  | 2019-01-31 | 2
036909C-1056-PDS-0900-5607 | Process Equipment Datasheet - 10-P-5601 A-B - Butadiene Area Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5607 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774 |  | 2019-01-31 | 2
036909C-1056-PDS-0900-5609 | Process Equipment Datasheet - 10-P-5603 A-B - CGC Area Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5609 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774 |  | 2019-01-31 | 2
036909C-1055-PDS-0900-5501 | Process Equipment Datasheet - 10-P-5500 A-B - Hot Blowdown Pumps | B | 2019-01-29 | IFD | OL1-2G30-5501 | PE | 2019-01-30 | 036909C-JVD-TRN-00774 | 036909C-JVD-TRN-00774 | IFR | 2019-02-15 | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00774 |  | 2019-01-31 | 2
036909C-102D-CN-1733-0042 | Calculation Note For Foundation Of 10-E-2582 | A | 2019-02-07 | IFR | OL1-2K13-0132 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843 |  | 2019-02-12 | 1
036909C-1029-PDS-0900-2934 | Process Equipment Datasheet - 10-P-2930 - Methanol Injection Pump | B | 2019-02-12 | IFD | OL1-2G30-2934 | PE | 2019-02-12 | 036909C-JVD-TRN-00844 | 036909C-JVD-TRN-00844 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00844 |  | 2019-02-12 | 2
036909C-1027-PDS-0900-2714 | Process Equipment Datasheet - 10-P-2714 A-B - C5 Cut Pumps | A | 2019-02-11 | IFR | OL1-2G30-2714 | PE | 2019-02-12 | 036909C-JVD-TRN-00841 | 036909C-JVD-TRN-00841 | IFR | 2019-02-26 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00841 |  | 2019-02-12 | 2
036909C-1027-PDS-0800-2762 | Process Equipment Datasheet - 10-D-2760 - C4-C5 Hydrog Recycle Drum | A | 2019-01-31 | IFR | OL1-2G30-2762 | PE | 2019-02-01 | 036909C-JVD-TRN-00794 | 036909C-JVD-TRN-00794 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00794 |  | 2019-02-04 | 2
036909C-1027-PDS-0900-2713 | Process Equipment Datasheet - 10-P-2710 A-B - Depentanizer Reflux Pump | A | 2019-02-11 | IFR | OL1-2G30-2713 | PE | 2019-02-11 | 036909C-JVD-TRN-00834 | 036909C-JVD-TRN-00834 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00834 |  | 2019-02-11 | 2
036909C-1027-PDS-0800-2750 | Process Equipment Datasheet - 10-D-2750 - C4-C5 Hydrog Surge Drum | A | 2019-01-31 | IFR | OL1-2G30-2750 | PE | 2019-02-01 | 036909C-JVD-TRN-00794 | 036909C-JVD-TRN-00794 | IFR | 2019-02-15 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00794 |  | 2019-02-04 | 2
036909C-1026-PDS-0900-2633 | Process Equipment Datasheet - 10-P-2630 A-B - Secondary Deeth Reflux Pumps | B | 2019-02-12 | IFD | OL1-2G30-2633 | PE | 2019-02-12 | 036909C-JVD-TRN-00844 | 036909C-JVD-TRN-00844 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00844 |  | 2019-02-12 | 2
036909C-1026-PDS-0900-2646 | Process Equipment Datasheet - 10-P-2646 A-B - Propane Recycle Pumps | B | 2019-02-12 | IFD | OL1-2G30-2646 | PE | 2019-02-12 | 036909C-JVD-TRN-00844 | 036909C-JVD-TRN-00844 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00844 |  | 2019-02-12 | 2
036909C-1019-SP-0940-1914 | Mechanical Equipment Datasheet - DMDS Presulfiding Injection Pump | A | 2019-01-28 | IFQ | OL1-2M03-1914 | ME | 2019-02-01 | 036909C-JVD-TRN-00787 | 036909C-JVD-TRN-00787 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00787 |  | 2019-02-04 | 2
036909C-1012-TBT-0122-2006 | Technical Bid Tabulation For Burners | 0 | 2019-01-30 | IFI | OL1-2Y23-2006 | ME | 2019-02-01 | 036909C-JVD-TRN-00789 | 036909C-JVD-TRN-00789 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00789 |  | 2019-02-04 | 3
036909C-1019-SP-0940-1913 | Mechanical Equipment Datasheet - DMDS Feed Injection Pump | A | 2019-01-28 | IFQ | OL1-2M03-1913 | ME | 2019-02-01 | 036909C-JVD-TRN-00787 | 036909C-JVD-TRN-00787 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00787 |  | 2019-02-04 | 2
036909C-1012-DL-0191-2006 | Deviation List for Furnace Buners | B | 2019-01-22 | IFR | OL1-2C40-306000 | ME | 2019-02-01 | 036909C-JVD-TRN-00790 | 036909C-JVD-TRN-00790 | IFR | 2019-02-16 |  | Transmitted | TPSK-LSPA1-T-ME-00790 |  | 2019-02-04 | 3
036909C-1006-JSS-0117-0024 | ME-024 Elevator For 36M and 132U Furnace | 0 | 2018-12-18 | IMP | OL1-2R03-0024 | ME | 2018-12-20 | 036909C-JVD-TRN-00537 | 036909C-JVD-TRN-00537, ROC-TPSK-CECO-T-00003 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00537 |  | 2018-12-20 | 3
036909C-1000-PP-301 | Planning Scheduling And Progress Measurement Procedure | 1 | 2019-02-12 | IMP | OL1-2B92-0001 | PC | 2019-02-14 | 036909C-JVD-TRN-00851 | 036909C-JVD-TRN-00851 | IFR | 2019-03-01 | 2019-02-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-PC-00851 |  | 2019-02-13 | 2
036909C-1000-PP-853 | Site Emergency and Evacuation Plan | A | 2019-03-07 | IFR | OL1-2S92-0004 | ES | 2019-03-15 | 036909C-JVD-TRN-01069 | 036909C-JVD-TRN-01069 | IFA | 2019-03-29 |  | Transmitted | TPSK-LSPA-1--ES-01069 |  | 2019-03-15 | 1
036909C-1023-PDS-0840-2307 | Process Equipment Datasheet - 10-F-2306 A-B - Weak Caustic Circulating Filters | B | 2018-12-11 | IFD | OL1-2G30-2307 | PE | 2018-12-13 | 036909C-JVD-TRN-00493 | 036909C-JVD-TRN-00493 | IFI |  | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00493 |  | 2018-12-13 | 2
036909C-1000-QCP-1812-0001 | Quality Control Plan Steel Structures Erection | A | 2019-01-21 | IFR | OL1-2Q22-0001 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-QM-00729 |  | 2019-01-28 | 1
036909C-1000-QCP-1761-0001 | Quality Control Plan Concrete Protective Coating | A | 2019-01-21 | IFR | OL1-2Q20-0019 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-QM-00729 |  | 2019-01-28 | 1
036909C-1012-PDS-0811-1207 | Process Equipment Datasheet - 10-D-1200-1600 - USC 132U Cracking Furnace Steam Drum | B | 2018-12-10 | IFD | OL1-2G30-1207 | PE | 2018-12-12 | 036909C-JVD-TRN-00478 | 036909C-JVD-TRN-00478 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00478 |  | 2018-12-12 | 2
036909C-1011-PDS-0811-1107 | Process Equipment Datasheet - 10-D-1100 - USC 36M Cracking Furnace Steam Drum | B | 2018-12-10 | IFD | OL1-2G30-1107 | PE | 2018-12-12 | 036909C-JVD-TRN-00478 | 036909C-JVD-TRN-00478 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00478 |  | 2018-12-12 | 2
036909C-1020-SP-0910-2024 | Mechanical Equipment Datasheet - Light Fuel Oil Pumps | A | 2018-11-23 | IFQ | OL1-2M03-2024 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457 | IFR | 2018-12-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00457 |  | 2018-12-10 | 2
036909C-1053-PDS-0300-5370 | Process Equipment Datasheet - 10-PIT-5370 - CW Filter Backwash Sump | A | 2018-12-18 | IFR | OL1-2G30-5370 | PE | 2018-12-20 | 036909C-JVD-TRN-00539 | 036909C-JVD-TRN-00539 | IFR | 2019-01-02 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA-1-T-PE-00539 |  | 2018-12-20 | 2
036909C-1026-PDS-0800-2644 | Process Equipment Datasheet - 10-D-2645 - C3 Tower Reboiler Cond Pot | A | 2019-01-16 | IFR | OL1-2G30-2644 | PE | 2019-01-18 | 036909C-JVD-TRN-00677 | 036909C-JVD-TRN-00677 | IFR | 2019-01-31 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-PE-00677 |  | 2019-01-18 | 2
036909C-1054-PDS-0800-5400 | Process Equipment Datasheet - 10-D-5400 - Instrument Air Receiver | A | 2018-12-11 | IFR | OL1-2G30-5400 | PE | 2018-12-13 | 036909C-JVD-TRN-00485 | 036909C-JVD-TRN-00485 | IFR | 2018-12-25 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-PE-00485 |  | 2018-12-13 | 2
036909C-1056-PDS-0200-5646 | Process Equipment Datasheet - 10-PIT-5606 - C3 Hydrog Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5646 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1056-PDS-0200-5604 | Process Equipment Datasheet - 10-PIT-5604 - Refrig Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5604 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1056-PDS-0200-5603 | Process Equipment Datasheet - 10-PIT-5603 - CGC Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5603 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1056-PDS-0200-5602 | Process Equipment Datasheet - 10-PIT-5602 - QW Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5602 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1056-PDS-0200-5601 | Process Equipment Datasheet - 10-PIT-5601 - Butadiene Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5601 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1055-PDS-1000-5522 | Process Equipment Datasheet - 10-C-5520 A-B - LP Vent Blowers | A | 2018-12-17 | IFR | OL1-2G30-5522 | PE | 2018-12-20 | 036909C-JVD-TRN-00528 | 036909C-JVD-TRN-00528 | IFR | 2019-01-02 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00528 |  | 2018-12-20 | 2
036909C-1056-PDS-0200-5632 | Process Equipment Datasheet - 10-PIT-5632 - HP Flare Area Oily WW Sump | A | 2019-01-02 | IFR | OL1-2G30-5632 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1056-PDS-0200-5631 | Process Equipment Datasheet - 10-PIT-5631 - CWWT Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5631 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1056-PDS-0200-5630 | Process Equipment Datasheet - 10-PIT-5630 - CT Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5630 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1056-PDS-0200-5600 | Process Equipment Datahseet - 10-PIT-5600 - Pygas Area Oily Wastewater Sump | A | 2019-01-02 | IFR | OL1-2G30-5600 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1029-PDS-0900-2934 | Process Equipment Datasheet - 10-P-2930 - Methanol Injection Pump | A | 2019-01-10 | IFR | OL1-2G30-2934 | PE | 2019-01-14 | 036909C-JVD-TRN-00645 | 036909C-JVD-TRN-00645 | IFR | 2019-01-28 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00645 |  | 2019-01-14 | 2
036909C-1029-PDS-2600-2931 | Process Equipment Datasheet - 10-PK-2931 - Propanol Injection Pkg | A | 2019-01-17 | IFR | OL1-2G30-2931 | PE | 2019-01-22 | 036909C-JVD-TRN-00689 | 036909C-JVD-TRN-00689 | IFR | 2019-02-04 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00689 |  | 2019-01-22 | 2
036909C-1000-PP-301 | Planning Scheduling And Progress Measurement Procedure | 0 | 2018-12-06 | IMP | OL1-2B92-0001 | PC | 2018-12-11 | 036909C-JVD-TRN-00469 | 036909C-JVD-TRN-00469 | IFR | 2018-12-25 | 2019-02-25 | A4 - Not Approved, re-submit for approval | TPSK-LSPA1-T-PC-00469 |  | 2018-12-11 | 2
036909C-1052-PDS-0600-5201 | Process Equipment Datasheet - 10-E-5200 - MP Ethylene Superheater | B | 2019-01-29 | IFD | OL1-2G30-5201 | PE | 2019-02-15 | 036909C-JVD-TRN-00853 | 036909C-JVD-TRN-00853 | IFR | 2019-03-01 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00853 |  | 2019-02-15 | 2
036909C-1027-PDS-0400-2700 | Process Equipment Datasheet - 10-R-2700 A-B - GHU-1 Reactor | A | 2019-01-14 | IFR | OL1-2G30-2700 | PE | 2019-01-16 | 036909C-JVD-TRN-00659 | 036909C-JVD-TRN-00659 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00659 |  | 2019-01-16 | 2
036909C-1011-PDS-0610-1109 | Process Equipment Datasheet - 10-E-1110 - USC 36M TLX-1 Quench Exchanger | B | 2018-12-06 | IFD | OL1-2G30-1109 | PE | 2018-12-10 | 036909C-JVD-TRN-00459 | 036909C-JVD-TRN-00459 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00459 |  | 2018-12-10 | 2
036909C-1011-PDS-0610-1110 | Process Equipment Datasheet - 10-E-1120 - USC 36M TLX-2 Quench Exchanger | B | 2018-12-06 | IFD | OL1-2G30-1110 | PE | 2018-12-10 | 036909C-JVD-TRN-00459 | 036909C-JVD-TRN-00459 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00459 |  | 2018-12-10 | 2
036909C-1021-PDS-0840-2104 | Process Equipment Datasheet - 10-F-2105 A-B - Quench Oil Reflux Filter | B | 2019-01-07 | IFD | OL1-2G30-2104 | PE | 2019-01-07 | 036909C-JVD-TRN-00606 | 036909C-JVD-TRN-00606 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00606 |  | 2019-01-07 | 2
036909C-1012-TBT-0137-2010 | Technical Bid Tabulation for MOVs | 0 | 2019-03-05 | IFI | OL1-2C23-28500 | PL | 2019-03-14 | 036909C-JVD-TRN-01053 | 036909C-JVD-TRN-01053 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01053 |  | 2019-03-15 | 3
036909C-1012-TBT-2040-2005 | Technical Bid Tabulation for Furnace ID Fans | 0 | 2019-02-28 | IFI | OL1-2C23-301000 | PL | 2019-03-04 | 036909C-JVD-TRN-00979 | 036909C-JVD-TRN-00979 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PC-00979 |  | 2019-03-05 | 3
036909C-1012-DL-0137-2010 | Deviation List for MOVs | B | 2019-03-11 | IFR | OL1-2C40-285000 | PL | 2019-03-14 | 036909C-JVD-TRN-01050 | 036909C-JVD-TRN-01050 | IFR | 2019-03-29 |  | Transmitted | TPSK-LSPA1-T-PL-01050 |  | 2019-03-15 | 3
036909C-1000-PP-110 | Document Management Procedure | 0 | 2019-03-08 | IMP | OL1-2W92-0004 | PC | 2019-03-14 | 036909C-JVD-TRN-01062 | 036909C-JVD-TRN-01062 | IFR | 2019-03-29 |  | Transmitted | TPSL-LSPA1-T-PC-01062 |  | 2019-03-15 | 2
036909C-1024-PDS-0600-2432 | Process Equipment Datasheet - 10-E-2432 - Regen Gas Shp Heater | B | 2019-01-18 | IFD | OL1-2G30-2432 | PE | 2019-01-22 | 036909C-JVD-TRN-00696 | 036909C-JVD-TRN-00696 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00696 |  | 2019-01-22 | 2
036909C-1055-PDS-0800-5515 | Process Equipment Datasheet - 10-D-5515 - Methanol Makeup Drum | A | 2018-12-17 | IFR | OL1-2G30-5515 | PE | 2018-12-20 | 036909C-JVD-TRN-00527 | 036909C-JVD-TRN-00527 | IFR | 2019-01-02 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00527 |  | 2018-12-20 | 2
036909C-1056-PDS-0900-5611 | Process Equipment Datasheet - 10-P-5610 - Hydroblast Sump Pump | A | 2019-01-03 | IFR | OL1-2G30-5611 | PE | 2019-01-07 | 036909C-JVD-TRN-00590 | 036909C-JVD-TRN-00590 | IFR | 2019-01-21 | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00590 |  | 2019-01-07 | 2
036909C-1027-PDS-0400-2760 | Process Equipment Datasheet - 10-R-2760 - C4-C5 Hydrog Reactor | A | 2019-01-15 | IFR | OL1-2G30-2760 | PE | 2019-01-16 | 036909C-JVD-TRN-00659 | 036909C-JVD-TRN-00659 | IFR | 2019-01-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00659 |  | 2019-01-16 | 2
036909C-1026-PDS-0800-2622 | Process Equipment Datasheet - 10-D-2620 - C3 Hydrog Recycle Drum | A | 2019-01-07 | IFR | OL1-2G30-2622 | PE | 2019-01-10 | 036909C-JVD-TRN-00614 | 036909C-JVD-TRN-00614 | IFR | 2019-01-23 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00614 |  | 2019-01-10 | 2
036909C-1010-PDS-0600-1020 | Process Equipment Datasheet - 10-E-1020 - Liquid Feed Heater | D | 2019-03-06 | IFD | OL1-2G30-1020 | PE | 2019-03-06 | 036909C-JVD-TRN-00999 | 036909C-JVD-TRN-00999 | IFR | 2019-03-21 |  | Transmitted | TPSK-LSPA1-T-PE-00999 |  | 2019-03-07 | 2
036909C-1010-PDS-0600-1005 | Process Equipment Datasheet - 10-E-1005 - LPG Feed Heater | C | 2019-03-06 | IFD | OL1-2G30-1005 | PE | 2019-03-06 | 036909C-JVD-TRN-00999 | 036909C-JVD-TRN-00999 | IFR | 2019-03-21 |  | Transmitted | TPSK-LSPA1-T-PE-00999 |  | 2019-03-07 | 2
036909C-1055-PDS-0800-5565 | Process Equipment Datasheet - 10-D-5565 - Polyolefins Flare Knock-Out Drum | A | 2018-12-20 | IFR | OL1-2G30-5565 | PE | 2018-12-20 | 036909C-JVD-TRN-00558 | 036909C-JVD-TRN-00558 | IFR | 2019-01-03 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00558 |  | 2018-12-20 | 2
036909C-1010-PDS-0600-1003 | Process Equipment Datasheet - 10-E-1001 - LPG Steam Vaporizer | B | 2019-01-21 | IFD | OL1-2G30-1003 | PE | 2019-01-23 | 036909C-JVD-TRN-00712 | 036909C-JVD-TRN-00712 | IFI |  | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00712 |  | 2019-01-23 | 2
036909C-1026-PDS-4200-2624 | Process Equipment Datasheet - 10-X-2620 - C3 Hydrog Static Mixer | A | 2019-01-15 | IFR | OL1-2G30-2624 | PE | 2019-01-16 | 036909C-JVD-TRN-00664 | 036909C-JVD-TRN-00664 | IFR | 2019-01-29 | 2019-01-31 | R1-No comments | TPSK-LSPA1-T-PE-00664 |  | 2019-01-16 | 2
036909C-1021-PDS-0800-2110 | Process Equipment Datasheet - 10-D-2110 - Interception Drum | A | 2018-12-06 | IFR | OL1-2G30-2110 | PE | 2018-12-10 | 036909C-JVD-TRN-00453 | 036909C-JVD-TRN-00453 | IFR | 2018-12-21 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-00453 |  | 2018-12-10 | 2
036909C-1019-PDS-0900-1914 | Process Equipment Datasheet - 10-P-1912 - DMDS Presulfiding Injection Pump | A | 2019-01-17 | IFR | OL1-2G30-1914 | PE | 2019-01-22 | 036909C-JVD-TRN-00687 | 036909C-JVD-TRN-00687 | IFR | 2019-02-04 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE--00687 |  | 2019-01-22 | 2
036909C-1019-PDS-0900-1913 | Process Equipment Datasheet - 10-P-1910 A-B - DMDS Feed Injection Pump | A | 2019-01-17 | IFR | OL1-2G30-1913 | PE | 2019-01-22 | 036909C-JVD-TRN-00687 | 036909C-JVD-TRN-00687 | IFR | 2019-02-04 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE--00687 |  | 2019-01-22 | 2
036909C-1056-SP-0910-5616 | Mechanical Equipment Datasheet - Olefins Stormwater Sump Pumps | A | 2019-01-21 | IFQ | OL1-2M03-5616 | ME | 2019-01-24 | 036909C-JVD-TRN-00716 | 036909C-JVD-TRN-00716 | IFR | 2019-02-06 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00716 |  | 2019-01-24 | 2
036909C-1056-PDS-0200-5633 | Process Equipment Datasheet - 10-PIT-5633 - HP Flare Area Stormwater Sump | A | 2019-01-10 | IFR | OL1-2G30-5633 | PE | 2019-01-11 | 036909C-JVD-TRN-00636 | 036909C-JVD-TRN-00636 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00636 |  | 2019-01-11 | 2
036909C-1000-QCP-1760-0001 | Quality Control Plan Civil Works-Grouting | A | 2019-01-21 | IFR | OL1-2Q20-0018 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729 |  | 2019-01-28 | 1
036909C-1000-QCP-1740-0001 | Quality Control Plan Civil Works-Fire Proofing | A | 2019-01-21 | IFR | OL1-2Q20-0017 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729 |  | 2019-01-28 | 1
036909C-1000-QCP-1717-0001 | Quality Control Plan Civil Works-Concrete Structure for Cooling Tower | A | 2019-01-21 | IFR | OL1-2Q20-0016 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729 |  | 2019-01-28 | 1
036909C-1000-QCP-1714-0001 | Quality Control Plan U-G Civil Works-Installation of Concrete Pits Cable Duct Banks Trenches-Ditches Cable Trenches Direct Buried Box Culverts and Lighting Poles Foundations | A | 2019-01-21 | IFR | OL1-2Q20-0015 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729 |  | 2019-01-28 | 1
036909C-1000-QCP-1713-0001 | Quality Control Plan Civil Works-Rigid Paving | A | 2019-01-21 | IFR | OL1-2Q20-0014 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729 |  | 2019-01-28 | 1
036909C-1000-QCP-1710-0005 | Quality Control Plan Above Ground Civil Works- Concrete Elements Installation | A | 2019-01-21 | IFR | OL1-2Q20-0013 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729 |  | 2019-01-28 | 1
036909C-1000-QCP-1710-0004 | Quality Control Plan Civil Works-Tank Rings Foundations | A | 2019-01-21 | IFR | OL1-2Q20-0012 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729 |  | 2019-01-28 | 1
036909C-1000-QCP-1710-0003 | Quality Control Plan Precast Pipe-Rack Erection | A | 2019-01-21 | IFR | OL1-2Q20-0011 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729 |  | 2019-01-28 | 1
036909C-1000-QCP-1710-0002 | Quality Control Plan Civil Works-Prefabrication of Concrete Elements | A | 2019-01-21 | IFR | OL1-2Q20-0010 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729 |  | 2019-01-28 | 1
036909C-1000-QCP-1710-0001 | Quality Control Plan Civil Works-Reinforced Concrete For Foundation-Elevation Structures And Basins | A | 2019-01-21 | IFR | OL1-2Q20-0009 | QM | 2019-01-28 | 036909C-JVD-TRN-00729 | 036909C-JVD-TRN-00729 | IFA | 2019-02-11 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00729 |  | 2019-01-28 | 1
036909C-1000-QCP-1470-0001 | Quality Control Plan U-G Civil Works-Sewers | A | 2019-01-07 | IFR | OL1-2Q20-0007 | QM | 2019-01-11 | 036909C-JVD-TRN-00625 | 036909C-JVD-TRN-00625 | IFA | 2019-01-25 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00625 |  | 2019-01-11 | 1
036909C-1000-QCP-1450-0001 | Quality Control Plan Civil Works-Asphalt Roads And Yards | A | 2019-01-07 | IFR | OL1-2Q20-0006 | QM | 2019-01-11 | 036909C-JVD-TRN-00625 | 036909C-JVD-TRN-00625 | IFA | 2019-01-25 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00625 |  | 2019-01-11 | 1
036909C-1000-QCP-1440-0001 | Quality Control Plan Civil Works-Earth Moving | A | 2019-01-07 | IFR | OL1-2Q20-0005 | QM | 2019-01-11 | 036909C-JVD-TRN-00625 | 036909C-JVD-TRN-00625 | IFA | 2019-01-25 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00625 |  | 2019-01-11 | 1
036909C-1000-QCP-1430-0003 | Quality Control Plan Civil Works-Concrete Precast Driven Piles | A | 2019-01-07 | IFR | OL1-2Q20-0004 | QM | 2019-01-11 | 036909C-JVD-TRN-00625 | 036909C-JVD-TRN-00625 | IFA | 2019-01-25 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00625 |  | 2019-01-11 | 1
036909C-1000-QCP-1430-0002 | Quality Control Plan Civil Works-Continuous Flight Auger Piles | A | 2019-01-07 | IFR | OL1-2Q20-0003 | QM | 2019-01-11 | 036909C-JVD-TRN-00625 | 036909C-JVD-TRN-00625 | IFA | 2019-01-25 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00625 |  | 2019-01-11 | 1
036909C-1000-QCP-1430-0001 | Quality Control Plan Civil Works-Bored Cast In Situ Piles | A | 2019-01-07 | IFR | OL1-2Q20-0002 | QM | 2019-01-11 | 036909C-JVD-TRN-00625 | 036909C-JVD-TRN-00625 | IFA | 2019-01-25 | 2019-02-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00625 |  | 2019-01-11 | 1
036909C-1023-PDS-2500-2324 | Process Equipment Datasheet - 10-TK-2300 - Fresh Caustic Day Tank | A | 2018-12-12 | IFR | OL1-2G30-2324 | PE | 2018-12-13 | 036909C-JVD-TRN-00495 | 036909C-JVD-TRN-00495 | IFR | 2018-12-26 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00495 |  | 2018-12-13 | 2
036909C-1029-PDS-0900-2911 | Process Equipment Datasheet - 10-P-2910 - Wash Oil Injection Pump | A | 2019-01-07 | IFR | OL1-2G30-2911 | PE | 2019-01-10 | 036909C-JVD-TRN-00613 | 036909C-JVD-TRN-00613 | IFR | 2019-01-23 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00613 |  | 2019-01-10 | 2
036909C-1000-PP-851 | SITE HSSE PLAN | A | 2019-02-19 | IFR | OL1-2S92-0003 | ES | 2019-02-25 | 036909C-JVD-TRN-00915 | 036909C-JVD-TRN-00915 | IFR | 2019-03-11 |  | Transmitted | TPSK-LSPA1-T-ES-00915 |  | 2019-02-25 | 1
036909C-1026-PDS-0400-2620 | Process Equipment Data Sheet - 10-R-2620 - C3 Hydrog Reactor | A | 2019-01-03 | IFR | OL1-2G30-2620 | PE | 2019-01-03 | 036909C-JVD-TRN-00583 | 036909C-JVD-TRN-00583 | IFR | 2019-01-18 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-00583 |  | 2019-01-03 | 2
036909C-1012-PDS-0191-1206 | Process Equipment Datasheet - 10-H-1200-1600 - USC 132U Burner | B | 2019-01-29 | IFD | OL1-2G30-1206 | PE | 2019-01-29 | 036909C-JVD-TRN-00756 | 036909C-JVD-TRN-00756 | IFI |  | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00756 |  | 2019-01-29 | 2
036909C-1011-PDS-0191-1106 | Process Equipment Datasheet - 10-H-1100 - USC 36M Burner | B | 2019-01-29 | IFD | OL1-2G30-1106 | PE | 2019-01-29 | 036909C-JVD-TRN-00756 | 036909C-JVD-TRN-00756 | IFI |  | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00756 |  | 2019-01-29 | 2
036909C-1000-QCP-1420-0001 | Quality Control Plan Civil Works-Fencing | A | 2018-12-10 | IFR | OL1-2Q20-0001 | QM | 2018-12-13 | 036909C-JVD-TRN-00488 | 036909C-JVD-TRN-00488 | IFA | 2018-12-27 | 2019-02-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-00488 |  | 2018-12-13 | 1
036909C-1020-PDS-0600-2048 | Process Equipment Datasheet - 10-E-2048 - Heavy Fuel Oil Product Cooler | B | 2019-01-16 | IFD | OL1-2G30-2048 | PE | 2019-01-18 | 036909C-JVD-TRN-00680 | 036909C-JVD-TRN-00680 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00680 |  | 2019-01-18 | 2
036909C-1020-PDS-0600-2026 | Process Equipment Datasheet - 10-E-2026 - FO Product Cooler | B | 2019-01-16 | IFD | OL1-2G30-2026 | PE | 2019-01-18 | 036909C-JVD-TRN-00680 | 036909C-JVD-TRN-00680 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00680 |  | 2019-01-18 | 2
036909C-1012-JSS-0191-2009 | Project Specification for Furnace Burners | 0 | 2019-01-18 | IMP | OL1-2M92-2009 | ME | 2019-01-22 | 036909C-JVD-TRN-00698 | 036909C-JVD-TRN-00698 | IFI |  | 2019-02-14 | R1-No comments | TPSK-LSPA1-T-ME-00698 |  | 2019-01-22 | 2
036909C-1000-PP-500 | Overall Project Quality Plan | 0 | 2018-12-13 | IMP | OL1-2Q92-0001 | QM | 2018-12-17 | 036909C-JVD-TRN-00512 | 036909C-JVD-TRN-00512 | IFA | 2019-01-02 | 2019-02-11 | A1-Approved without comments | TPSK-LSPA1-T-QM-00512 |  | 2018-12-17 | 1
036909C-1020-PDS-0840-2028 | Process Equipment Datasheet - 10-F-2028 A-B - FO Pump Purge Oil Filter | B | 2019-01-16 | IFD | OL1-2G30-2028 | PE | 2019-01-18 | 036909C-JVD-TRN-00676 | 036909C-JVD-TRN-00676 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00676 |  | 2019-01-18 | 2
036909C-1020-PDS-0840-2025 | Process Equipment Datasheet - 10-F-2026 A-B Cracker Bottoms Product Filter | B | 2019-01-16 | IFD | OL1-2G30-2025 | PE | 2019-01-18 | 036909C-JVD-TRN-00676 | 036909C-JVD-TRN-00676 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00676 |  | 2019-01-18 | 2
036909C-1022-PDS-0600-2206 | Process Equipment Datasheet - 10-E-2206 - Wash Water Cooler | B | 2019-01-14 | IFD | OL1-2G30-2206 | PE | 2019-01-16 | 036909C-JVD-TRN-00655 | 036909C-JVD-TRN-00655 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00655 |  | 2019-01-16 | 2
036909C-1028-PDS-0600-2859 | Process Equipment Datasheet - 10-E-2856 - Ethylene Product Subcooler | C | 2019-01-21 | IFD | OL1-2G30-2859 | PE | 2019-01-23 | 036909C-JVD-TRN-00711 | 036909C-JVD-TRN-00711 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00711 |  | 2019-01-23 | 2
036909C-1024-PDS-0600-2434 | Process Equipment Datasheet - 10-E-2435 - Regen Gas Effluent Cooler | B | 2019-01-18 | IFD | OL1-2G30-2434 | PE | 2019-01-22 | 036909C-JVD-TRN-00696 | 036909C-JVD-TRN-00696 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00696 |  | 2019-01-22 | 2
036909C-1024-PDS-0600-2430 | Process Equipment Datasheet - 10-E-2430 - Regen Gas Feed Heater | B | 2019-01-18 | IFD | OL1-2G30-2430 | PE | 2019-01-22 | 036909C-JVD-TRN-00696 | 036909C-JVD-TRN-00696 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00696 |  | 2019-01-22 | 2
036909C-1023-SP-0910-2325 | Mechanical Equipment Datasheet for 10 Caustic Makeup Pumps | A | 2018-12-28 | IFQ | OL1-2M03-2325 | ME | 2019-01-03 | 036909C-JVD-TRN-00580 | 036909C-JVD-TRN-00580 | IFI |  | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00580 |  | 2019-01-03 | 2
036909C-1021-PDS-0600-2147 | Process Equipment Datasheet - 10-E-2146 - DSG Feed Heater | B | 2019-01-07 | IFD | OL1-2G30-2147 | PE | 2019-01-07 | 036909C-JVD-TRN-00605 | 036909C-JVD-TRN-00605 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00605 |  | 2019-01-07 | 2
036909C-1021-PDS-0600-2145 | Process Equipment Datasheet - 10-E-2145 - Process Water Stripper Reboiler | B | 2019-01-07 | IFD | OL1-2G30-2145 | PE | 2019-01-07 | 036909C-JVD-TRN-00605 | 036909C-JVD-TRN-00605 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00605 |  | 2019-01-07 | 2
036909C-1021-PDS-0900-2191 | Process Equipment Datasheet - 10-P-2190 - Quench Water Drain Drum Pump | B | 2019-01-07 | IFD | OL1-2G30-2191 | PE | 2019-01-07 | 036909C-JVD-TRN-00603 | 036909C-JVD-TRN-00603 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00603 |  | 2019-01-07 | 2
036909C-1028-PDS-0900-2816 | Process Equipment Datasheet - 10-P-2815 - Propylene Refrig Recovery Pump | B | 2018-12-10 | IFD | OL1-2G30-2816 | PE | 2018-12-13 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00481 |  | 2018-12-13 | 2
036909C-1028-PDS-0900-2801 | Process Equipment Datasheet - 10-P-2805 A-B - Propylene Product Pumps | B | 2019-01-10 | IFD | OL1-2G30-2801 | PE | 2019-01-14 | 036909C-JVD-TRN-00649 | 036909C-JVD-TRN-00649 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00649 |  | 2019-01-14 | 2
036909C-1026-PDS-0900-2647 | Process Equipment Datasheet - 10-P-2647 - HP Propylene - Off Spec Pumps | B | 2019-01-10 | IFD | OL1-2G30-2647 | PE | 2019-01-14 | 036909C-JVD-TRN-00649 | 036909C-JVD-TRN-00649 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00649 |  | 2019-01-14 | 2
036909C-1028-PDS-0900-2816 | Process Equipment Datasheet - 10-P-2815 - Propylene Refrig Recovery Pump | C | 2019-01-10 | IFD | OL1-2G30-2816 | PE | 2019-01-14 | 036909C-JVD-TRN-00648 | 036909C-JVD-TRN-00648 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00648 |  | 2019-01-14 | 2
036909C-1020-PDS-0900-2024 | Process Equipment Datasheet - 10-P-2026 A-B - Light Fuel Oil Pumps | B | 2019-01-10 | IFD | OL1-2G30-2024 | PE | 2019-01-14 | 036909C-JVD-TRN-00648 | 036909C-JVD-TRN-00648 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00648 |  | 2019-01-14 | 2
036909C-1020-PDS-0840-2014 | Process Equipment Datasheet - 10-F-2009 A-B - QO Pump Purge Oil Filter | B | 2019-01-07 | IFD | OL1-2G30-2014 | PE | 2019-01-07 | 036909C-JVD-TRN-00606 | 036909C-JVD-TRN-00606 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00606 |  | 2019-01-07 | 2
036909C-1020-PDS-0840-2010 | Process Equipment Datasheet - 10-F-2008 A-C - Quench Oil Filter | B | 2019-01-07 | IFD | OL1-2G30-2010 | PE | 2019-01-07 | 036909C-JVD-TRN-00606 | 036909C-JVD-TRN-00606 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00606 |  | 2019-01-07 | 2
036909C-1022-PDS-0900-2212 | Process Equipment Datasheet - 10-P-2210 A-B - CG 1st Stage Condensate Pumps | B | 2019-01-02 | IFD | OL1-2G30-2212 | PE | 2019-01-07 | 036909C-JVD-TRN-00593 | 036909C-JVD-TRN-00593 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00593 |  | 2019-01-07 | 2
036909C-1053-PDS-0900-5361 | Process Equipment Datasheet - 10-P-5360 A-C - CTU Cooling Water Pumps | D | 2019-01-03 | IFD | OL1-2G30-5361 | PE | 2019-01-07 | 036909C-JVD-TRN-00593 | 036909C-JVD-TRN-00593 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00593 |  | 2019-01-07 | 2
036909C-1022-PDS-0900-2222 | Process Equipment Datasheet - 10-P-2220 A-B - CG 2nd Stage Condensed HC Pumps | B | 2019-01-02 | IFD | OL1-2G30-2222 | PE | 2019-01-07 | 036909C-JVD-TRN-00593 | 036909C-JVD-TRN-00593 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00593 |  | 2019-01-07 | 2
036909C-1024-PDS-0800-2435 | Process Equipment Datasheet - 10-D-2435 - Regen Gas Separator | A | 2018-12-20 | IFR | OL1-2G30-2435 | PE | 2018-12-20 | 036909C-JVD-TRN-00559 | 036909C-JVD-TRN-00559 | IFR | 2019-01-03 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00559 |  | 2018-12-20 | 2
036909C-1023-PDS-0900-2325 | Process Equipment Datasheet - 10-P-2300 A-B - 10 Percent Caustic Makeup Pump | A | 2018-12-17 | IFR | OL1-2G30-2325 | PE | 2018-12-20 | 036909C-JVD-TRN-00526 | 036909C-JVD-TRN-00526 | IFR | 2019-01-02 | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00526 |  | 2018-12-20 | 2
036909C-1023-PDS-0900-2302 | Process Equipment Datasheet - 10-P-2302 A-B - Strong Caustic Circulating Pumps | B | 2018-12-17 | IFD | OL1-2G30-2302 | PE | 2018-12-20 | 036909C-JVD-TRN-00524 | 036909C-JVD-TRN-00524 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00524 |  | 2018-12-20 | 2
036909C-1023-PDS-0900-2311 | Process Equipment Datasheet - 10-P-2310 A-B - Wash Oil Circulating Pumps | B | 2018-12-17 | IFD | OL1-2G30-2311 | PE | 2018-12-20 | 036909C-JVD-TRN-00524 | 036909C-JVD-TRN-00524 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00524 |  | 2018-12-20 | 2
036909C-1023-PDS-0900-2393 | Process Equipment Datasheet - 10-P-2392 - Spent Caustic Drain Drum Pump | B | 2019-01-02 | IFD | OL1-2G30-2393 | PE | 2019-01-07 | 036909C-JVD-TRN-00598 | 036909C-JVD-TRN-00598 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00598 |  | 2019-01-07 | 2
036909C-1023-PDS-0900-2321 | Process Equipment Datasheet - 10-P-2320 A-B - Spent Caustic Pumps | B | 2019-01-02 | IFD | OL1-2G30-2321 | PE | 2019-01-07 | 036909C-JVD-TRN-00598 | 036909C-JVD-TRN-00598 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00598 |  | 2019-01-07 | 2
036909C-1012-JSS-0125-2003 | Project Specification for Cast Intermediate Tube Supports | 1 | 2018-12-13 | IMP | OL1-2M92-2003 | ME | 2018-12-17 | 036909C-JVD-TRN-00517 | 036909C-JVD-TRN-00517 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00517 |  | 2018-12-17 | 3
036909C-1024-PDS-0600-2455 | Process Equipment Datasheet - 10-E-2455 A-B - LP Depropanizer Reboilers | B | 2018-12-17 | IFD | OL1-2G30-2455 | PE | 2018-12-20 | 036909C-JVD-TRN-00523 | 036909C-JVD-TRN-00523 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00523 |  | 2018-12-20 | 2
036909C-1023-PDS-0600-2305 | Process Equipment Datasheet - 10-E-2305 - Caustic Tower Feed Heater | B | 2018-12-17 | IFD | OL1-2G30-2305 | PE | 2018-12-20 | 036909C-JVD-TRN-00523 | 036909C-JVD-TRN-00523 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00523 |  | 2018-12-20 | 2
036909C-1024-PDS-0600-2406 | Process Equipment Datasheet - 10-E-2405 - Gas Dryer Feed Chiller | B | 2018-12-17 | IFD | OL1-2G30-2406 | PE | 2018-12-20 | 036909C-JVD-TRN-00523 | 036909C-JVD-TRN-00523 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00523 |  | 2018-12-20 | 2
036909C-1024-PDS-0600-2412 | Process Equipment Datasheet - 10-E-2412 - HP Depropanizer Feed Chiller | B | 2018-12-17 | IFD | OL1-2G30-2412 | PE | 2018-12-20 | 036909C-JVD-TRN-00523 | 036909C-JVD-TRN-00523 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00523 |  | 2018-12-20 | 2
036909C-1011-DW-0125-1301 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details | 1 | 2018-12-12 | IMP | OL1-2M06-1301 | ME | 2018-12-17 | 036909C-JVD-TRN-00520 | 036909C-JVD-TRN-00520 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00520 |  | 2018-12-17 | 3
036909C-1012-DW-0125-2302 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details | 1 | 2018-12-12 | IMP | OL1-2M06-2302 | ME | 2018-12-17 | 036909C-JVD-TRN-00520 | 036909C-JVD-TRN-00520 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00520 |  | 2018-12-17 | 3
036909C-1012-DW-0125-2301 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details | 1 | 2018-12-12 | IMP | OL1-2M06-2301 | ME | 2018-12-17 | 036909C-JVD-TRN-00520 | 036909C-JVD-TRN-00520 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00520 |  | 2018-12-17 | 3
036909C-1028-PDS-0600-2859 | Process Equipment Datasheet - 10-E-2856 - Ethylene Product Subcooler | B | 2018-12-11 | IFD | OL1-2G30-2859 | PE | 2018-12-13 | 036909C-JVD-TRN-00492 | 036909C-JVD-TRN-00492 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00492 | CHANGE NUMBER - For revision A see document OL1-2G30-2591 - 1025-PDS-0600-2591 | 2018-12-13 | 2
036909C-1023-PDS-0840-2319 | Process Equipment Datasheet - 10-F-2320 A-B - Spent Caustic Pump Discharge Filters | B | 2018-12-11 | IFD | OL1-2G30-2319 | PE | 2018-12-13 | 036909C-JVD-TRN-00493 | 036909C-JVD-TRN-00493 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00493 |  | 2018-12-13 | 2
036909C-1023-PDS-0840-2314 | Process Equipment Datasheet - 10-F-2310 A-B - Wash Oil Circulating Filter | B | 2018-12-11 | IFD | OL1-2G30-2314 | PE | 2018-12-13 | 036909C-JVD-TRN-00493 | 036909C-JVD-TRN-00493 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00493 |  | 2018-12-13 | 2
036909C-1025-PDS-0600-2546 | Process Equipment Datasheet - 10-E-2546 - Demethanizer Bottoms Cooler | B | 2018-12-11 | IFD | OL1-2G30-2546 | PE | 2018-12-13 | 036909C-JVD-TRN-00492 | 036909C-JVD-TRN-00492 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00492 |  | 2018-12-13 | 2
036909C-1025-PDS-0600-2545 | Process Equipment Datasheet - 10-E-2545 - Demethanizer Reboiler | B | 2018-12-11 | IFD | OL1-2G30-2545 | PE | 2018-12-13 | 036909C-JVD-TRN-00492 | 036909C-JVD-TRN-00492 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00492 |  | 2018-12-13 | 2
036909C-1028-PDS-0600-2858 | Process Equipment Datasheet - 10-E-2858 - HP Ethylene Product Superheater | B | 2018-12-11 | IFD | OL1-2G30-2858 | PE | 2018-12-13 | 036909C-JVD-TRN-00492 | 036909C-JVD-TRN-00492 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00492 |  | 2018-12-13 | 2
036909C-1025-PDS-0600-2582 | Process Equipment Datasheet - 10-E-2582 - C2 Tower Reflux Cooler | B | 2018-12-11 | IFD | OL1-2G30-2582 | PE | 2018-12-13 | 036909C-JVD-TRN-00492 | 036909C-JVD-TRN-00492 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00492 |  | 2018-12-13 | 2
036909C-1021-PDS-0600-2125 | Process Equipment Datasheet - 10-E-2125 - Distillate Stripper Reboiler | B | 2018-12-11 | IFD | OL1-2G30-2125 | PE | 2018-12-13 | 036909C-JVD-TRN-00492 | 036909C-JVD-TRN-00492 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00492 |  | 2018-12-13 | 2
036909C-1025-PDS-0600-2515 | Process Equipment Datasheet - 10-E-2515 - Demeth Prefrac Reboiler | B | 2018-12-11 | IFD | OL1-2G30-2515 | PE | 2018-12-13 | 036909C-JVD-TRN-00492 | 036909C-JVD-TRN-00492 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00492 |  | 2018-12-13 | 2
036909C-1027-PDS-0800-2790 | Process Equipment Datasheet - 10-D-2790 - Light Oil Drain Drum | A | 2018-12-10 | IFR | OL1-2G30-2790 | PE | 2018-12-13 | 036909C-JVD-TRN-00482 | 036909C-JVD-TRN-00482 | IFR | 2018-12-25 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00482 |  | 2018-12-13 | 2
036909C-1025-PDS-0800-2574 | Process Equipment Datasheet - 10-D-2575 - Deethanizer Reboiler Cond Pot | A | 2018-12-07 | IFR | OL1-2G30-2574 | PE | 2018-12-11 | 036909C-JVD-TRN-00474 | 036909C-JVD-TRN-00474 | IFR | 2018-12-24 | 2018-12-21 | R1-No comments | TPSK-LSPA1-T-PE-00474 |  | 2018-12-11 | 2
036909C-1024-PDS-0800-2456 | Process Equipment Datasheet - 10-D-2455 - LP Deprop Reboiler Cond Pot | A | 2018-12-07 | IFR | OL1-2G30-2456 | PE | 2018-12-11 | 036909C-JVD-TRN-00474 | 036909C-JVD-TRN-00474 | IFR | 2018-12-24 | 2018-12-21 | R1-No comments | TPSK-LSPA1-T-PE-00474 |  | 2018-12-11 | 2
036909C-1024-PDS-0800-2444 | Process Equipment Datasheet - 10-D-2445 - HP Deprop Reboiler Cond Pot | A | 2018-12-07 | IFR | OL1-2G30-2444 | PE | 2018-12-11 | 036909C-JVD-TRN-00474 | 036909C-JVD-TRN-00474 | IFR | 2018-12-24 | 2018-12-21 | R1-No comments | TPSK-LSPA1-T-PE-00474 |  | 2018-12-11 | 2
036909C-1025-PDS-0600-2548 | Process Equipment Datasheet - 10-E-2548 - Demethanizer Bottoms Vaporizer | B | 2018-12-07 | IFD | OL1-2G30-2548 | PE | 2018-12-10 | 036909C-JVD-TRN-00464 | 036909C-JVD-TRN-00464 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00464 |  | 2018-12-10 | 2
036909C-1024-PDS-0800-2460 | Process Equipment Datasheet - 10-D-2460 - C2 Hydrog Arsine Guard Bed | A | 2018-12-06 | IFR | OL1-2G30-2460 | PE | 2018-12-10 | 036909C-JVD-TRN-00453 | 036909C-JVD-TRN-00453 | IFR | 2018-12-21 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-00453 |  | 2018-12-10 | 2
036909C-1022-PDS-0600-2211 | Process Equipment Datasheet - 10-E-2210 A-B - CG 1st Stage Aftercoolers | B | 2018-12-10 | IFD | OL1-2G30-2211 | PE | 2018-12-13 | 036909C-JVD-TRN-00479 | 036909C-JVD-TRN-00479 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00479 |  | 2018-12-13 | 2
036909C-1021-PDS-0800-2136 | Process Equipment Datasheet - 10-D-2136 - Process Water Feed Coalescer | A | 2018-12-06 | IFR | OL1-2G30-2136 | PE | 2018-12-10 | 036909C-JVD-TRN-00453 | 036909C-JVD-TRN-00453 | IFR | 2018-12-21 | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00453 |  | 2018-12-10 | 2
036909C-1021-PDS-0600-2161 | Process Equipment Datasheet - 10-E-2160 - Dilution Steam Superheater | B | 2018-12-07 | IFD | OL1-2G30-2161 | PE | 2018-12-10 | 036909C-JVD-TRN-00467 | 036909C-JVD-TRN-00467 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00467 |  | 2018-12-10 | 2
036909C-1025-PDS-0900-2573 | Process Equipment Datasheet - 10-P-2570 A-B - Deethanizer Reflux Pumps | B | 2018-12-10 | IFD | OL1-2G30-2573 | PE | 2018-12-13 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00481 |  | 2018-12-13 | 2
036909C-1025-PDS-0900-2586 | Process Equipment Datasheet - 10-P-2586 A-B - Ethane Recycle Pumps | B | 2018-12-10 | IFD | OL1-2G30-2586 | PE | 2018-12-13 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00481 |  | 2018-12-13 | 2
036909C-1011-DW-0122-1202 | USC 36M Recycle Furnace Transfer Line And Clean Out Details | 0 | 2018-12-11 | IMP | OL1-2M06-1202 | ME | 2018-12-13 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00486 |  | 2018-12-13 | 2
036909C-1012-DW-0122-2201 | USC 132U Cracking Furnace Radiant Coil Assembly and Details | 0 | 2018-12-11 | IMP | OL1-2M06-2201 | ME | 2018-12-13 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00486 |  | 2018-12-13 | 2
036909C-1011-DW-0122-1203 | USC 36M Recycle Furnace Radiant Coil Tubeskin Thermocouple Details | 0 | 2018-12-11 | IMP | OL1-2M06-1203 | ME | 2018-12-13 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00486 |  | 2018-12-13 | 2
036909C-1011-DW-0122-1201 | USC 36M Recycle Furnace Radiant Coil Assembly and Details | 0 | 2018-12-10 | IMP | OL1-2M06-1201 | ME | 2018-12-13 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00486 |  | 2018-12-13 | 2
036909C-1012-DW-0122-2202 | USC 132U Cracking Furnace Transfer Lines and Clean-Out Details | 0 | 2018-12-11 | IMP | OL1-2M06-2202 | ME | 2018-12-13 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00486 |  | 2018-12-13 | 2
036909C-1000-RT-1920-0051 | MSDS for Chemicals and Catalysts | 0 | 2019-01-21 | IFI | OL1-2L60-0051 | SE | 2019-01-23 | 036909C-JVD-TRN-00707 | 036909C-JVD-TRN-00707 | IFI |  |  | Transmitted | TPSK-LSPA1-T-SE-00707 |  | 2019-01-23 | 3
036909C-1024-PDS-0600-2434 | Process Equipment Datasheet - 10-E-2435 - Regen Gas Effluent Cooler | A | 2018-12-27 | IFR | OL1-2G30-2434 | PE | 2019-01-03 | 036909C-JVD-TRN-00574 | 036909C-JVD-TRN-00574 | IFR | 2019-01-15 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00574 |  | 2019-01-03 | 2
036909C-1024-PDS-0600-2432 | Process Equipment Datasheet - 10-E-2432 - Regen Gas Shp Heater | A | 2018-12-27 | IFR | OL1-2G30-2432 | PE | 2019-01-03 | 036909C-JVD-TRN-00574 | 036909C-JVD-TRN-00574 | IFR | 2019-01-15 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00574 |  | 2019-01-03 | 2
036909C-1024-PDS-0600-2430 | Process Equipment Datasheet - 10-E-2430 - Regen Gas Feed Heater | A | 2018-12-27 | IFR | OL1-2G30-2430 | PE | 2019-01-03 | 036909C-JVD-TRN-00574 | 036909C-JVD-TRN-00574 | IFR | 2019-01-15 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00574 |  | 2019-01-03 | 2
036909C-1000-PP-119 | Interface Management Plan | B | 2019-01-17 | IFA | OL1-2V92-0014 | IF | 2019-01-22 | 036909C-JVD-TRN-00703 | 036909C-JVD-TRN-00703 | IFA | 2019-02-05 |  | Transmitted | TPSK-LSPA1-T-IF-00703 |  | 2019-01-22 | 2
036909C-1000-PP-617 | Project Site Services Conditions For Supplier s Specialists | 1 | 2018-11-18 | IMP | OL1-2C92-0017 | PL | 2019-01-07 | 036909C-JVD-TRN-00594 | 036909C-JVD-TRN-00594 | IFR | 2019-01-22 | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PL-00594 |  | 2019-01-07 | 2
036909C-1000-PP-123 | Criticality Rating Procedure | 0 | 2019-01-07 | IMP | OL1-2W92-0009 | PC | 2019-01-14 | 036909C-JVD-TRN-00642 | 036909C-JVD-TRN-00642 | IFR | 2019-01-29 |  | Transmitted | TPSK-LSPA1-T-PC-00642 |  | 2019-01-14 | 2
036909C-1000-QCP-1470-0002 | Quality Control Plan Non Metallic Pressure Piping Installation - Above and Underground | A | 2019-01-07 | IFR | OL1-2Q20-0008 | QM | 2019-01-11 | 036909C-JVD-TRN-00625 | 036909C-JVD-TRN-00625 | IFA | 2019-01-25 |  | Transmitted | TPSK-LSPA1-T-QM-00625 |  | 2019-01-11 | 1
036909C-1000-JSS-1661-0001 | Substation Monitoring And Control System | 0 | 2018-12-03 | IMP | OL1-2R05-0005 | EE | 2018-12-05 | 036909C-JVD-TRN-00425 | 036909C-JVD-TRN-00425 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00425 |  | 2018-12-05 | 3
036909C-1012-TBT-0122-2004 | Technical Bid Tabulation for Radiant Coils | 0 | 2018-12-11 | IFI | OL1-2Y23-2004 | PC | 2018-12-13 | 036909C-JVD-TRN-00490 | 036909C-JVD-TRN-00490 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PC-00490 |  | 2018-12-13 | 3
036909C-1000-PID-0090-0011 | P&ID - Olefins Unit 10 - Common - EIV Block Valves Typical | B | 2019-03-19 | IBD | OL1-2G43-0011 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1000-PID-0090-0011 | P&ID - Olefins Unit 10 - Common - EIV Block Valves Typical | A | 2018-11-15 | IFR | OL1-2G43-0011 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323, ROC-TPSK-CECO-T-00010 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1000-PID-0090-0010 | P&ID - Olefins Unit 10 - Common - Instrument Details | B | 2019-03-19 | IBD | OL1-2G43-0010 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1000-PID-0090-0010 | P&ID - Olefins Unit 10 - Common - Instrument Details | A | 2018-11-15 | IFR | OL1-2G43-0010 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323, ROC-TPSK-CECO-T-00010 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1000-PID-0090-0005 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 2 | A | 2018-11-15 | IFR | OL1-2G43-0005 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323, ROC-TPSK-CECO-T-00010 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1000-PID-0090-0005 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 2 | B | 2019-03-19 | IBD | OL1-2G43-0005 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1000-PID-0090-0004 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 1 | B | 2019-03-19 | IBD | OL1-2G43-0004 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, ROC-TPSK-CECO-T-00065 | IFR | 2019-04-11 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1000-PID-0090-0004 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 1 | A | 2018-11-15 | IFR | OL1-2G43-0004 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323, ROC-TPSK-CECO-T-00010 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1000-PID-0090-0003 | P&ID - Olefins Unit 10 - Common - Instrumentation Symbols | A | 2018-11-15 | IFR | OL1-2G43-0003 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323, ROC-TPSK-CECO-T-00010 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1000-PID-0090-0003 | P&ID - Olefins Unit 10 - Common - Instrumentation Symbols | B | 2019-03-19 | IBD | OL1-2G43-0003 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-04-11 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1000-PID-0090-0002 | P&ID - Olefins Unit 10 - Common - Piping Symbols | B | 2019-03-19 | IBD | OL1-2G43-0002 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-04-11 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1000-PID-0090-0002 | P&ID - Olefins Unit 10 - Common - Piping Symbols | A | 2018-11-15 | IFR | OL1-2G43-0002 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323, ROC-TPSK-CECO-T-00010 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1000-PID-0090-0001 | P&ID - Olefins Unit 10 - Common - Abbreviations And Numbering | A | 2018-11-15 | IFR | OL1-2G43-0001 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323, ROC-TPSK-CECO-T-00010 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1000-PID-0090-0001 | P&ID - Olefins Unit 10 - Common - Abbreviations And Numbering | B | 2019-03-19 | IBD | OL1-2G43-0001 | PE | 2019-03-27 | 036909C-JVD-TRN-01180 | 036909C-JVD-TRN-01180, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-04-11 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01180 |  | 2019-03-28 | 2
036909C-1000-EL-001 | Item Index | A | 2019-03-15 | IFR | OL1-2M91-0001 | ME | 2019-03-15 | 036909C-JVD-TRN-01080 | 036909C-JVD-TRN-01080, ROC-TPSK-CECO-T-00013, ROC-TPSK-CECO-T-00013_1 | IFR | 2019-04-01 | 2019-04-05 | R1-No comments | TPSK-LSPA1-T-ME-01080 |  | 2019-03-18 | 2
036909C-1000-EL-001 | Item Index - Excluding Furnaces Island - Area 1A | B | 2019-06-10 | IBD | OL1-2M91-0001 | ME | 2019-06-13 | 036909C-JVD-TRN-01887 | 036909C-JVD-TRN-01887 | IFR | 2019-06-28 |  | Transmitted | TPSK-LSPA1-T-ME-01887 |  | 2019-06-14 | 2
036909C-1051-PID-0031-5102 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Stations - Sheet 2 | A | 2019-01-23 | IFR | OL1-2G43-5102 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5102 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Stations - Sheet 2 | B | 2019-04-24 | IBD | OL1-2G43-5102 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5101 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Stations - Sheet 1 | A | 2019-01-23 | IFR | OL1-2G43-5101 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5101 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Stations - Sheet 1 | B | 2019-04-24 | IBD | OL1-2G43-5101 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1000-PP-016 | Prescriptions For Preparation Of Vendor Data Book | A | 2018-11-26 | IFR | OL1-2W92-0010 | PC | 2018-12-07 | 036909C-JVD-TRN-00435 | 036909C-JVD-TRN-00435 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PC-00435 |  | 2018-12-07 | 2
036909C-1000-PP-014 | Requirements For Vendor Documentation And Exchange Of Correspondence | A | 2018-11-23 | IFR | OL1-2W92-0005 | PC | 2018-11-29 | 036909C-JVD-TRN-00385 | 036909C-JVD-TRN-00385 | IFR | 2018-12-14 |  | Transmitted | TPSK-LSPA1-T-PC-00385 |  | 2018-11-29 | 2
036909C-1000-PP-256 | 3D Modeling Procedure For Civil Designers | A | 2018-11-20 | IFR | OL1-2R02-0010 | ME | 2018-12-12 | 036909C-JVD-TRN-00353 | 036909C-JVD-TRN-00353 | IFR | 2018-12-25 | 2019-03-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00353 | LSP ask TPSK to revise Document Reference Number from 2RO7 (Mechanical) to 2R02 (Civil). They also want us to change transmittal date 12 Dec 2018. | 2018-12-12 | 2
036909C-1000-SL-0000-03 | Subvendor list for PSA/Deareator/Filter Package | 0 | 2018-11-15 | IMP | OL1-2C01-0002 | PL | 2018-11-19 | 036909C-JVD-TRN-00333 | 036909C-JVD-TRN-00333 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00333 |  | 2018-11-19 | 3
036909C-1012-PID-0021-1219 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1219 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1245 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Flue Gas | A | 2018-11-15 | IFR | OL1-2G43-1245 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1229 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Drum-SLE And TLX Risers | A | 2018-11-15 | IFR | OL1-2G43-1229 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1250 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas | A | 2018-11-15 | IFR | OL1-2G43-1250 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1221 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1221 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1220 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1220 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1227 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - SLE Drain Header | A | 2018-11-15 | IFR | OL1-2G43-1227 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1240 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Burners | A | 2018-11-15 | IFR | OL1-2G43-1240 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1118 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1118 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1145 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoking Effluent | A | 2018-11-15 | IFR | OL1-2G43-1145 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1119 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1119 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1115 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Convection Section | A | 2018-11-15 | IFR | OL1-2G43-1115 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1116 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1116 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1125 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - TLX Quench Exchangers | A | 2018-11-15 | IFR | OL1-2G43-1125 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1129 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Drum-USX And TLX-1 Risers | A | 2018-11-15 | IFR | OL1-2G43-1129 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1225 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - TLX Exchanger | A | 2018-11-15 | IFR | OL1-2G43-1225 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1217 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1217 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1228 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - VHP Steam Drum | A | 2018-11-15 | IFR | OL1-2G43-1228 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1231 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Coils | A | 2018-11-15 | IFR | OL1-2G43-1231 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1218 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1218 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1150 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Flue Gas | A | 2018-11-15 | IFR | OL1-2G43-1150 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1216 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1216 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1012-PID-0021-1215 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Convection Section | A | 2018-11-15 | IFR | OL1-2G43-1215 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1121 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1121 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1000-SR-0570-0004 | Scope of Supply for High Efficiency Internals for Columns | B | 2018-11-12 | IMP | OL1-2M56-0075 | ME | 2018-11-14 | 036909C-JVD-TRN-00314 | 036909C-JVD-TRN-00314 | IFR | 2018-11-29 | 2019-02-08 | R1-No comments | TPSK-LSPA1-T-ME-00314 |  | 2018-11-14 | 2
036909C-1011-PID-0021-1127 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - USX Drain Header | A | 2018-11-15 | IFR | OL1-2G43-1127 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1120 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1120 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1117 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1117 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1128 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - SHP Steam Drum | A | 2018-11-15 | IFR | OL1-2G43-1128 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1011-PID-0021-1131 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Coils | A | 2018-11-15 | IFR | OL1-2G43-1131 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1000-SP-0570-0004 | Particular Technical Specification for High Efficiency Internals for Columns | B | 2018-11-12 | IMP | OL1-2M57-0075 | ME | 2018-11-14 | 036909C-JVD-TRN-00314 | 036909C-JVD-TRN-00314 | IFR | 2018-11-29 | 2019-02-08 | R1-No comments | TPSK-LSPA1-T-ME-00314 |  | 2018-11-14 | 2
036909C-1000-PP-255 | 3D Modeling Procedure For Piping Designers | A | 2018-06-06 | IFR | OL1-2R07-0027 | ME | 2018-11-13 | 036909C-JVD-TRN-00311 | 036909C-JVD-TRN-00311 | IFR | 2018-11-28 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00311 |  | 2018-11-13 | 2
036909C-1059-PFD-0030-5911 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Complex U & O Chemical Storage | D | 2019-08-08 | IFD | OL1-2G42-5911 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1056-PFD-0030-5615 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Check Basin | D | 2019-08-08 | IFD | OL1-2G42-5615 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1056-PFD-0030-5614 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Biotreatment Package | D | 2019-08-08 | IFD | OL1-2G42-5614 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1056-PFD-0030-5612 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Equalization Tank | D | 2019-08-08 | IFD | OL1-2G42-5612 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1056-PFD-0030-5610 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - HP Flare Area SW & Oily WW Collection | D | 2019-08-08 | IFD | OL1-2G42-5610 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1056-PFD-0030-5604 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Domestic Wastewater Collection | D | 2019-08-08 | IFD | OL1-2G42-5604 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1055-PFD-0030-5512 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Enclosed Ground Flare | D | 2019-08-08 | IFD | OL1-2G42-5512 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1055-PFD-0030-5511 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - HP - LLDPE LP Flare | D | 2019-08-08 | IFD | OL1-2G42-5511 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1055-PFD-0030-5502 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Process Vent Gas Collection | D | 2019-08-08 | IFD | OL1-2G42-5502 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1055-PFD-0030-5501 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Flare and Blowdown System | D | 2019-08-08 | IFD | OL1-2G42-5501 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1054-PFD-0030-5401 | Utility Flow Diagram - Olefins Unit 10 - 54 - Air and Nitrogen System - Plant Air Instrument Air and Nitrogen Systems | D | 2019-08-08 | IFD | OL1-2G42-5401 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1053-PFD-0030-5311 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Tower | D | 2019-08-08 | IFD | OL1-2G42-5311 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1051-PFD-0030-5103 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate Treatment System | D | 2019-08-08 | IFD | OL1-2G42-5103 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1051-PFD-0030-5102 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate and Boiler Feedwater Systems | D | 2019-08-08 | IFD | OL1-2G42-5102 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1051-PFD-0030-5101 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Steam Balance Diagram | D | 2019-08-08 | IFD | OL1-2G42-5101 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1059-PFD-0030-5901 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Chemical Storage | D | 2019-08-08 | IFD | OL1-2G42-5901 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1056-PFD-0030-5617 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Slop & Oil Sludge | D | 2019-08-08 | IFD | OL1-2G42-5617 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1056-PFD-0030-5616 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Sludge Dewatering Package | D | 2019-08-08 | IFD | OL1-2G42-5616 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1056-PFD-0030-5613 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - CPI & IGF Packages | D | 2019-08-08 | IFD | OL1-2G42-5613 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1056-PFD-0030-5611 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - OSBL Oily Wastewater Collection | D | 2019-08-08 | IFD | OL1-2G42-5611 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1056-PFD-0030-5603 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Cracker Holding Basin | D | 2019-08-08 | IFD | OL1-2G42-5603 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1056-PFD-0030-5602 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Surface Runoff Collection | D | 2019-08-08 | IFD | OL1-2G42-5602 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1056-PFD-0030-5601 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Collection | D | 2019-08-08 | IFD | OL1-2G42-5601 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1053-PFD-0030-5301 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Water Diagram | D | 2019-08-08 | IFD | OL1-2G42-5301 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1052-PFD-0030-5201 | Utility Flow Diagram - Olefins Unit 10 - 52 - Fuel System - Fuel Gas System | D | 2019-08-08 | IFD | OL1-2G42-5201 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1051-PFD-0030-5104 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Furnace Blowdown System | D | 2019-08-08 | IFD | OL1-2G42-5104 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1050-PFD-0030-5001 | Utility Flow Diagram - Olefins Unit 10 - 50 - Water System - Treated Potable and Demin Water Systems | D | 2019-08-08 | IFD | OL1-2G42-5001 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-24 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1000-MR-0910-0002 | Material Requisition For API Centrifugal Pumps | A | 2019-02-15 | IFQ | OL1-2C13-442000 | PL | 2019-02-19 | 036909C-JVD-TRN-00880 | 036909C-JVD-TRN-00880 | IFR | 2019-03-05 |  | Transmitted | TPSK-LSPA1-T-PL-00880 |  | 2019-02-19 | 2
036909C-1030-PFD-0010-3001 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation | D | 2019-08-08 | IFD | OL1-2G41-3001 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1029-PFD-0010-2901 | Process Flow Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | D | 2019-08-08 | IFD | OL1-2G41-2901 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1028-PFD-0010-2804 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | D | 2019-08-08 | IFD | OL1-2G41-2804 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1028-PFD-0010-2803 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | D | 2019-08-08 | IFD | OL1-2G41-2803 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1028-PFD-0010-2802 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | D | 2019-08-08 | IFD | OL1-2G41-2802 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1028-PFD-0010-2801 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | D | 2019-08-08 | IFD | OL1-2G41-2801 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1027-PFD-0010-2704 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation | D | 2019-08-08 | IFD | OL1-2G41-2704 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1027-PFD-0010-2703 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - Hydrog Reactivation Gas System | D | 2019-08-08 | IFD | OL1-2G41-2703 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1027-PFD-0010-2702 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Rerun Tower | D | 2019-08-08 | IFD | OL1-2G41-2702 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1027-PFD-0010-2701 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Reactor & Depentanizer | D | 2019-08-08 | IFD | OL1-2G41-2701 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1026-PFD-0010-2604 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | D | 2019-08-08 | IFD | OL1-2G41-2604 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1026-PFD-0010-2603 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | D | 2019-08-08 | IFD | OL1-2G41-2603 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1026-PFD-0010-2602 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | D | 2019-08-08 | IFD | OL1-2G41-2602 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1026-PFD-0010-2601 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | D | 2019-08-08 | IFD | OL1-2G41-2601 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1025-PFD-0010-2502 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | D | 2019-08-08 | IFD | OL1-2G41-2502 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1025-PFD-0010-2505 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | D | 2019-08-08 | IFD | OL1-2G41-2505 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1025-PFD-0010-2503 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | D | 2019-08-08 | IFD | OL1-2G41-2503 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1025-PFD-0010-2504 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | D | 2019-08-08 | IFD | OL1-2G41-2504 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1025-PFD-0010-2501 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | D | 2019-08-08 | IFD | OL1-2G41-2501 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1024-PFD-0010-2405 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | D | 2019-08-08 | IFD | OL1-2G41-2405 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1024-PFD-0010-2404 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | D | 2019-08-08 | IFD | OL1-2G41-2404 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1039-PFD-0010-3901 | Process Flow Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage | D | 2019-08-08 | IFD | OL1-2G41-3901 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1031-PFD-0010-3102 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam and Condensate System | D | 2019-08-08 | IFD | OL1-2G41-3102 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1031-PFD-0010-3101 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration | D | 2019-08-08 | IFD | OL1-2G41-3101 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1030-PFD-0010-3005 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation | D | 2019-08-08 | IFD | OL1-2G41-3005 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1030-PFD-0010-3004 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing | D | 2019-08-08 | IFD | OL1-2G41-3004 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1030-PFD-0010-3003 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier | D | 2019-08-08 | IFD | OL1-2G41-3003 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1030-PFD-0010-3002 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Evaporation | D | 2019-08-08 | IFD | OL1-2G41-3002 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1025-PFD-0010-2506 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | D | 2019-08-08 | IFD | OL1-2G41-2506 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1024-PFD-0010-2403 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | D | 2019-08-08 | IFD | OL1-2G41-2403 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1024-PFD-0010-2402 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | D | 2019-08-08 | IFD | OL1-2G41-2402 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1024-PFD-0010-2401 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | D | 2019-08-08 | IFD | OL1-2G41-2401 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1023-PFD-0010-2305 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | D | 2019-08-08 | IFD | OL1-2G41-2305 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1023-PFD-0010-2304 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | D | 2019-08-08 | IFD | OL1-2G41-2304 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1023-PFD-0010-2303 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | D | 2019-08-08 | IFD | OL1-2G41-2303 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1023-PFD-0010-2302 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | D | 2019-08-08 | IFD | OL1-2G41-2302 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1023-PFD-0010-2301 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | D | 2019-08-08 | IFD | OL1-2G41-2301 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1022-PFD-0010-2201 | Process Flow Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | D | 2019-08-08 | IFD | OL1-2G41-2201 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1021-PFD-0010-2103 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | D | 2019-08-08 | IFD | OL1-2G41-2103 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1021-PFD-0010-2102 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | D | 2019-08-08 | IFD | OL1-2G41-2102 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1021-PFD-0010-2101 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | D | 2019-08-08 | IFD | OL1-2G41-2101 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1020-PFD-0010-2002 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | D | 2019-08-08 | IFD | OL1-2G41-2002 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1020-PFD-0010-2001 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | D | 2019-08-08 | IFD | OL1-2G41-2001 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1019-PFD-0010-1902 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | D | 2019-08-08 | IFD | OL1-2G41-1902 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1019-PFD-0010-1901 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | D | 2019-08-08 | IFD | OL1-2G41-1901 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1012-PFD-0010-1201 | Process Flow Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | D | 2019-08-08 | IFD | OL1-2G41-1201 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1011-PFD-0010-1101 | Process Flow Diagram - Olefins Unit 10 - 11 - Furnaces - Recycle Gas Cracking Furnace | D | 2019-08-08 | IFD | OL1-2G41-1101 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1010-PFD-0010-1003 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | D | 2019-08-08 | IFD | OL1-2G41-1003 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1010-PFD-0010-1001 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | D | 2019-08-08 | IFD | OL1-2G41-1001 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1000-PFD-0010-0002 | Process Flow Diagram - Olefins Unit 10 - 00-General - Drawing Index | D | 2019-08-08 | IFD | OL1-2G41-0002 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1000-PFD-0010-0001 | Process Flow Diagram - Olefins Unit 10 - 00-General - Legend & Symbols | D | 2019-08-08 | IFD | OL1-2G41-0001 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1000-PFD-0010-0010 | Block Flow Diagram - Olefins Unit 10 - 00-General - Overall Plant Scheme | D | 2019-08-08 | IFD | OL1-2G40-0010 | PE | 2019-08-12 | 036909C-JVD-TRN-02422 | 036909C-JVD-TRN-02422 | IFA | 2019-08-27 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02422 |  | 2019-08-14 | 1
036909C-1059-MSD-0011-5911 | Material Selection Diagram - Olefins Unit 10 - 59 Utilities And Auxiliaries Complex U & O Chemical Storage | B | 2019-08-07 | IFD | OL1-2G74-5911 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1059-MSD-0011-5901 | Material Selection Diagram - Olefins Unit 10 - 59 Utilities Aux - Chemical Storage | B | 2019-08-07 | IFD | OL1-2G74-5901 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1056-MSD-0011-5617 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Slop and Oil Sludge | B | 2019-08-07 | IFD | OL1-2G74-5617 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1056-MSD-0011-5616 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Sludge Dewatering Package | B | 2019-08-07 | IFD | OL1-2G74-5616 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1056-MSD-0011-5615 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Check Basin | B | 2019-08-07 | IFD | OL1-2G74-5615 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1056-MSD-0011-5614 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Biotreatment Package | B | 2019-08-07 | IFD | OL1-2G74-5614 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1056-MSD-0011-5613 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - CPI & IGF Packages | B | 2019-08-07 | IFD | OL1-2G74-5613 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1056-MSD-0011-5612 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Oily Wastewater Equilization Tank | B | 2019-08-07 | IFD | OL1-2G74-5612 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1056-MSD-0011-5611 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - OSBL Oily Wastewater Collection | B | 2019-08-07 | IFD | OL1-2G74-5611 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1056-MSD-0011-5610 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - HP Flare Area SW & Oily WW Collection | B | 2019-08-07 | IFD | OL1-2G74-5610 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1056-MSD-0011-5604 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Domestic Wastewater Collection | B | 2019-08-07 | IFD | OL1-2G74-5604 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1055-MSD-0011-5512 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - Enclosed Ground | B | 2019-08-07 | IFD | OL1-2G74-5512 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1055-MSD-0011-5502 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - Process Vent Gas Collection | B | 2019-08-07 | IFD | OL1-2G74-5502 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1055-MSD-0011-5501 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - Flare and Blowdown System | B | 2019-08-07 | IFD | OL1-2G74-5501 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1054-MSD-0011-5401 | Material Selection Diagram - Olefins Unit 10 - 54 Air and Nitrogen System - Plant Air - Instrument Air and Nitrogen Systems | B | 2019-08-07 | IFD | OL1-2G74-5401 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1053-MSD-0011-5301 | Material Selection Diagram - Olefins Unit 10 - 53 Cooling Water System Cooling Water Diagram | B | 2019-08-07 | IFD | OL1-2G74-5301 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1051-MSD-0011-5104 | Material Selection Diagram - Olefins Unit 10 - 51 BFW Steam Cond Systems - Furnace Blowdown System | B | 2019-08-07 | IFD | OL1-2G74-5104 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1051-MSD-0011-5101 | Material Selection Diagram - Olefins Unit 10 - 51 BFW- Steam- Cond Systems - Steam Balance Diagram | B | 2019-08-07 | IFD | OL1-2G74-5101 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1050-MSD-0011-5001 | Material Selection Diagram - Olefins Unit 10 - 50 Water Systems - Treated -Potable and Demin Water Systems | B | 2019-08-07 | IFD | OL1-2G74-5001 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1056-MSD-0011-5603 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Cracker Holding Basin | B | 2019-08-07 | IFD | OL1-2G74-5603 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1056-MSD-0011-5602 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Surface Runoff Collection | B | 2019-08-07 | IFD | OL1-2G74-5602 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1056-MSD-0011-5601 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Oily Wastewater Collection | B | 2019-08-07 | IFD | OL1-2G74-5601 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1055-MSD-0011-5511 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - HP-LLDPE LP Flare | B | 2019-08-07 | IFD | OL1-2G74-5511 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1052-MSD-0011-5201 | Material Selection Diagram - Olefins Unit 10 - 52 Fuel System - Fuel Gas System | B | 2019-08-07 | IFD | OL1-2G74-5201 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1053-MSD-0011-5311 | Material Selection Diagram - Olefins Unit 10 - 53-Cooling Water System Cooling Tower | B | 2019-08-07 | IFD | OL1-2G74-5311 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1051-MSD-0011-5103 | Material Selection Diagram - Olefins Unit 10 - 51 BFW Steam Cond Systems - Condensate Treatment System | B | 2019-08-07 | IFD | OL1-2G74-5103 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1051-MSD-0011-5102 | Material Selection Diagram - Olefins Unit 10 - 51 BFW Steam Cond Systems - Condensate and Boiler Feedwater Systems | B | 2019-08-07 | IFD | OL1-2G74-5102 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1026-MSD-0011-2604 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | B | 2019-08-07 | IFD | OL1-2G74-2604 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1026-MSD-0011-2601 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | B | 2019-08-07 | IFD | OL1-2G74-2601 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1025-MSD-0011-2506 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | B | 2019-08-07 | IFD | OL1-2G74-2506 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1025-MSD-0011-2504 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | B | 2019-08-07 | IFD | OL1-2G74-2504 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1025-MSD-0011-2503 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | B | 2019-08-07 | IFD | OL1-2G74-2503 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1025-MSD-0011-2502 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | B | 2019-08-07 | IFD | OL1-2G74-2502 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1025-MSD-0011-2501 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | B | 2019-08-07 | IFD | OL1-2G74-2501 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1024-MSD-0011-2405 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | B | 2019-08-07 | IFD | OL1-2G74-2405 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1024-MSD-0011-2404 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | B | 2019-08-07 | IFD | OL1-2G74-2404 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1024-MSD-0011-2403 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | B | 2019-08-07 | IFD | OL1-2G74-2403 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1024-MSD-0011-2402 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | B | 2019-08-07 | IFD | OL1-2G74-2402 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1024-MSD-0011-2401 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | B | 2019-08-07 | IFD | OL1-2G74-2401 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1028-MSD-0011-2803 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | B | 2019-08-07 | IFD | OL1-2G74-2803 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1028-MSD-0011-2801 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | B | 2019-08-07 | IFD | OL1-2G74-2801 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1029-MSD-0011-2901 | Material Selection Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | B | 2019-08-07 | IFD | OL1-2G74-2901 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1028-MSD-0011-2804 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | B | 2019-08-07 | IFD | OL1-2G74-2804 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1028-MSD-0011-2802 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | B | 2019-08-13 | IFD | OL1-2G74-2802 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1026-MSD-0011-2603 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | B | 2019-08-07 | IFD | OL1-2G74-2603 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1026-MSD-0011-2602 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | B | 2019-08-07 | IFD | OL1-2G74-2602 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1025-MSD-0011-2505 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | B | 2019-08-07 | IFD | OL1-2G74-2505 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1019-MSD-0011-1901 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | B | 2019-08-07 | IFD | OL1-2G74-1901 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1023-MSD-0011-2305 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | B | 2019-08-07 | IFD | OL1-2G74-2305 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1023-MSD-0011-2304 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | B | 2019-08-07 | IFD | OL1-2G74-2304 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1023-MSD-0011-2303 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | B | 2019-08-07 | IFD | OL1-2G74-2303 | ME | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1023-MSD-0011-2302 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | B | 2019-08-07 | IFD | OL1-2G74-2302 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1023-MSD-0011-2301 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | B | 2019-08-07 | IFD | OL1-2G74-2301 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1021-MSD-0011-2103 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | B | 2019-08-07 | IFD | OL1-2G74-2103 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1021-MSD-0011-2102 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | B | 2019-08-07 | IFD | OL1-2G74-2102 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1021-MSD-0011-2101 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | B | 2019-08-07 | IFD | OL1-2G74-2101 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1020-MSD-0011-2002 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | B | 2019-08-07 | IFD | OL1-2G74-2002 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1020-MSD-0011-2001 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | B | 2019-08-07 | IFD | OL1-2G74-2001 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1010-MSD-0011-1001 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | B | 2019-08-07 | IFD | OL1-2G74-1001 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1000-MSD-0011-0001 | Material Selection Diagram - Olefins Unit 10 - Legend & Notes | B | 2019-08-07 | IFD | OL1-2G74-0001 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1019-MSD-0011-1902 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | B | 2019-08-07 | IFD | OL1-2G74-1902 | ME | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-ME-02428 |  | 2019-08-15 | 3
036909C-1011-MSD-0011-1101 | Material Selection Diagram - Olefins Unit 10 - 11 - Furnaces - Gas Cracking Furnace | B | 2019-08-07 | IFD | OL1-2G74-1101 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1010-MSD-0011-1003 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | B | 2019-08-07 | IFD | OL1-2G74-1003 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1022-MSD-0011-2201 | Material Selection Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | B | 2019-08-07 | IFD | OL1-2G74-2201 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1012-MSD-0011-1201 | Material Selection Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | B | 2019-08-07 | IFD | OL1-2G74-1201 | PE | 2019-08-13 | 036909C-JVD-TRN-02428 | 036909C-JVD-TRN-02428 | IFI |  | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02428 |  | 2019-08-15 | 3
036909C-1056-PID-0031-5652 | P&ID - Olefins Unit 10 - Wastewater - Cooling Water Blowdown Basin | B | 2019-04-26 | IBD | OL1-2G43-5652 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5652 | P&ID - Olefins Unit 10 - Wastewater - Cooling Water Blowdown Basin | A | 2019-02-13 | IFR | OL1-2G43-5652 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00007 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5649 | P&ID - Olefins Unit 10 - Wastewater - HP Flare Area Oily Wastewater Sump | A | 2019-02-13 | IFR | OL1-2G43-5649 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5649 | P&ID - Olefins Unit 10 - Wastewater - HP Flare Area Oily Wastewater Sump | B | 2019-04-26 | IBD | OL1-2G43-5649 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5620 | P&ID - Olefins Unit 10 - Wastewater - Olefins Storm Water Collection | B | 2019-04-26 | IBD | OL1-2G43-5620 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5620 | P&ID - Olefins Unit 10 - Wastewater - Olefins Storm Water Collection | A | 2019-02-13 | IFR | OL1-2G43-5620 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1055-PID-0031-5520 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 1 | A | 2019-01-17 | IFR | OL1-2G43-5520 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5520 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 1 | B | 2019-05-06 | IBD | OL1-2G43-5520 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5512 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 3 | A | 2019-01-17 | IFR | OL1-2G43-5512 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5512 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 3 | B | 2019-05-06 | IBD | OL1-2G43-5512 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1051-PID-0031-5168 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Steam LS2 Distribution - Sheet 1 | B | 2019-04-24 | IBD | OL1-2G43-5168 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5168 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Steam Ls2 Distribution - Sheet 1 | A | 2019-01-23 | IFR | OL1-2G43-5168 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5166 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 6 | B | 2019-04-24 | IBD | OL1-2G43-5166 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5166 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 6 | A | 2019-01-23 | IFR | OL1-2G43-5166 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5164 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 5 | A | 2019-01-23 | IFR | OL1-2G43-5164 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5164 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 5 | B | 2019-04-24 | IBD | OL1-2G43-5164 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5163 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 4 | B | 2019-04-24 | IBD | OL1-2G43-5163 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5163 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 4 | A | 2019-01-23 | IFR | OL1-2G43-5163 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5162 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 3 | B | 2019-04-24 | IBD | OL1-2G43-5162 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5162 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 3 | A | 2019-01-23 | IFR | OL1-2G43-5162 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00006, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5161 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 2 | B | 2019-04-24 | IBD | OL1-2G43-5161 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5161 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 2 | A | 2019-01-23 | IFR | OL1-2G43-5161 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5160 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 1 | A | 2019-01-23 | IFR | OL1-2G43-5160 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5160 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 1 | B | 2019-04-24 | IBD | OL1-2G43-5160 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5152 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Steam Distribution - Sheet 3 | A | 2019-01-23 | IFR | OL1-2G43-5152 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5152 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Steam Distribution - Sheet 3 | B | 2019-04-24 | IBD | OL1-2G43-5152 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5151 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Steam Distribution - Sheet 2 | B | 2019-04-24 | IBD | OL1-2G43-5151 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5151 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Steam Distribution - Sheet 2 | A | 2019-01-23 | IFR | OL1-2G43-5151 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5150 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Steam Distribution - Sheet 01 | B | 2019-04-24 | IBD | OL1-2G43-5150 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5150 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Steam Distribution - Sheet 01 | A | 2019-01-23 | IFR | OL1-2G43-5150 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5144 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - HP Steam Distribution - Sheet 02 | B | 2019-04-24 | IBD | OL1-2G43-5144 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5144 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - HP Steam Distribution - Sheet 02 | A | 2019-01-23 | IFR | OL1-2G43-5144 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5143 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - HP Steam Distribtion - Sheet 1 | A | 2019-01-23 | IFR | OL1-2G43-5143 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5143 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - HP Steam Distribtion - Sheet 1 | B | 2019-04-24 | IBD | OL1-2G43-5143 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5114 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP BFW Distribution | A | 2019-01-23 | IFR | OL1-2G43-5114 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5114 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP BFW Distribution | B | 2019-04-24 | IBD | OL1-2G43-5114 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5113 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP & HP BFW Distribution | A | 2019-01-23 | IFR | OL1-2G43-5113 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5113 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP & HP BFW Distribution | B | 2019-04-24 | IBD | OL1-2G43-5113 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5103 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Station - Sheet 3 | A | 2019-01-23 | IFR | OL1-2G43-5103 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00008 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5103 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Station - Sheet 3 | B | 2019-04-24 | IBD | OL1-2G43-5103 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1000-PP-608 | Project QCS Expediting Procedure | 0 | 2018-10-29 | IMP | OL1-2C92-0008 | PL | 2018-11-09 | 036909C-JVD-TRN-00297 | 036909C-JVD-TRN-00297 | IFR | 2018-11-23 |  | Transmitted | TPSK-LSPA1-T-PL-00297 |  | 2018-11-09 | 2
036909C-1000-PP-015 | Prescriptions For Preparation Of Manufacturing Data Record Book | 0 | 2018-10-29 | IMP | OL1-2W92-0015 | PC | 2018-11-09 | 036909C-JVD-TRN-00296 | 036909C-JVD-TRN-00296 | IFR | 2018-11-23 |  | Transmitted | TPSK-LSPA1-T-PC-00296 |  | 2018-11-09 | 2
036909C-1000-PP-617 | Project Site Services Conditions For Supplier Specialists | 0 | 2018-11-05 | IMP | OL1-2C92-0017 | PL | 2018-11-07 | 036909C-JVD-TRN-00284 | 036909C-JVD-TRN-00284 | IFR | 2018-11-21 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PL-00284 |  | 2018-11-07 | 2
036909C-1000-PP-614 | Project Expediting And Inspection Level Definition | 0 | 2018-10-29 | IMP | OL1-2C92-0014 | PL | 2018-10-30 | 036909C-JVD-TRN-00244 | 036909C-JVD-TRN-00244 | IFR | 2018-11-15 | 2019-05-08 | R1-No comments | TPSK-LSPA1-T-PL-00244 |  | 2018-10-30 | 2
036909C-1000-PP-602 | Project QCS Coordination Procedure | 0 | 2018-10-29 | IMP | OL1-2C92-0002 | PL | 2018-10-30 | 036909C-JVD-TRN-00244 | 036909C-JVD-TRN-00244 | IFR | 2018-11-15 | 2019-05-08 | R1-No comments | TPSK-LSPA1-T-PL-00244 |  | 2018-10-30 | 2
036909C-1000-PP-107 | Project Document Coding | 0 | 2018-10-24 | IMP | OL1-2W92-0003 | PC | 2018-10-30 | 036909C-JVD-TRN-00240 | 036909C-JVD-TRN-00240 | IFR | 2018-11-13 |  | Transmitted | TPSK-LSPA1-T-PC-00240 |  | 2018-10-30 | 2
036909C-1000-PP-609 | Project QCS Inspection Procedure | 0 | 2018-10-29 | IMP | OL1-2C92-0009 | PL | 2018-10-30 | 036909C-JVD-TRN-00244 | 036909C-JVD-TRN-00244 | IFR | 2018-11-15 | 2019-05-06 | R1-No comments | TPSK-LSPA1-T-PL-00244 |  | 2018-10-30 | 2
036909C-1011-PID-0021-1140 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Burners | A | 2018-11-15 | IFR | OL1-2G43-1140 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-00323 |  | 2018-11-15 | 2
036909C-1026-SP-0510-2660 | Mechanical Equipment Datasheet for Debutanizer | A | 2018-10-23 | IFQ | OL1-2M03-2660 | ME | 2018-10-23 | 036909C-JVD-TRN-00215 | 036909C-JVD-TRN-00215 | IFR | 2018-11-06 |  | Transmitted | TPSK-LSPA1-T-ME-00215 |  | 2018-10-23 | 2
036909C-1000-PP-117 | ITC Plan | A | 2018-10-15 | IFR | OL1-2W92-0012 | PC | 2018-10-19 | 036909C-JVD-TRN-00197 | 036909C-JVD-TRN-00197 | IFR | 2018-11-02 |  | Transmitted | TPSK-LSPA1-T-PM-00197 |  | 2018-10-19 | 2
036909C-1000-PP-313 | Car & Third Party Insurance Claim Procedure | 0 | 2018-10-18 | IFI | OL1-2A92-0002 | CO | 2018-10-18 | 036909C-JVD-TRN-00192 | 036909C-JVD-TRN-00192 | IFI |  | 2018-10-26 | R2-Comments as noted | TPSK-LSPA1-T-CO-00192 |  | 2018-10-18 | 3
036909C-1000-RT-200 | Fire Fighting Basic Design Report For Package A1 | 1 | 2018-09-28 | IFI | OL1-2W90-0001 | PC | 2018-10-17 | 036909C-JVD-TRN-00187 | 036909C-JVD-TRN-00187 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PM-00187 |  | 2018-10-17 | 3
036909C-1000-PP-703 | Construction Subcontracting Plan | A | 2018-10-18 | IFR | OL1-2D92-0001 | CM | 2018-10-18 | 036909C-JVD-TRN-00193 | 036909C-JVD-TRN-00193 | IFR | 2018-11-01 |  | Transmitted | TPSK-LSPA1-T-CM-00193 |  | 2018-10-18 | 2
036909C-1000-PP-615 | Transportation Plan | 0 | 2018-10-16 | IMP | OL1-2C92-0015 | PL | 2018-10-16 | 036909C-JVD-TRN-00177 | 036909C-JVD-TRN-00177 | IFR | 2018-10-30 | 2018-10-30 | Transmitted | TPSK-LSPA1-T-PL-00177 |  | 2018-10-16 | 2
036909C-1000-PP-124 | Engineering Execution Plan | 0 | 2018-10-12 | IFI | OL1-2W92-0018 | PC | 2018-10-15 | 036909C-JVD-TRN-00170 | 036909C-JVD-TRN-00170 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PM-00170 |  | 2018-10-15 | 3
036909C-1000-JSD-2300-01 | Job Design Specification For Painting | A | 2018-08-22 | IFR | OL1-2R04-0005 | MP | 2018-08-22 | 036909C-JVD-TRN-00024 | 036909C-JVD-TRN-00024 | IFR | 2018-09-05 | 2018-09-12 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00024 |  | 2018-08-23 | 2
036909C-1000-MR-1541-0001 | Material Requisition For Control Valves | A | 2019-06-13 | IFQ | OL1-2C17-050101 | PL | 2019-06-13 | 036909C-JVD-TRN-01891 | 036909C-JVD-TRN-01891 | IFR | 2019-07-01 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PL-01891 |  | 2019-06-13 | 2
036909C-1000-SP-1562-0005 | Instrument Data Sheets for Particulate Analyzers | A | 2019-09-06 | IFQ | OL1-2I20-2018 | IE | 2019-09-09 | 036909C-JVD-TRN-02599 | 036909C-JVD-TRN-02599 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-IE-02599 |  | 2019-09-10 | 1
036909C-1000-SP-1562-0004 | Instrument Data Sheets for Continuous Emission Monitoring System - CEMS | A | 2019-09-06 | IFQ | OL1-2I20-2107 | IE | 2019-09-09 | 036909C-JVD-TRN-02599 | 036909C-JVD-TRN-02599 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-IE-02599 |  | 2019-09-10 | 1
036909C-1000-JSD-0001-0002 | Units Of Measurement | 0 | 2018-09-20 | IMP | OL1-2R07-0018 | ME | 2018-09-24 | 036909C-JVD-TRN-00080 | 036909C-JVD-TRN-00080 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00080 |  | 2018-09-25 | 3
036909C-1000-JSD-0001 | Project Design Basis | 1 | 2019-04-16 | IMP | OL1-2R07-0026 | ME | 2019-05-02 | 036909C-JVD-TRN-01547 | 036909C-JVD-TRN-01547 | IFR | 2019-05-17 | 2019-05-31 | R1-No comments | TPSK-LSPA1-T-ME-01547 |  | 2019-05-03 | 2
036909C-1000-PP-259 | Drafting Procedure For 2D Drawings | 1 | 2019-05-14 | IMP | OL1-2R07-0023 | ME | 2019-05-28 | 036909C-JVD-TRN-01755 | 036909C-JVD-TRN-01755 | IFR | 2019-06-12 |  | Transmitted | TPSK-LSPA1-T-ME-01755 |  | 2019-05-29 | 2
036909C-1000-PP-015 | Prescriptions For Preparation Of Manufacturing Data Record Book | 1 | 2019-03-19 | IMP | OL1-2W92-0015 | PC | 2019-03-22 | 036909C-JVD-TRN-01135 | 036909C-JVD-TRN-01135 | IFR | 2019-04-04 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-PC-01135 |  | 2019-03-22 | 2
036909C-1000-PP-605 | Project QCS Requirements For Suppliers | 0 | 2018-10-29 | IMP | OL1-2C92-0005 | PL | 2018-10-30 | 036909C-JVD-TRN-00244 | 036909C-JVD-TRN-00244 | IFR | 2018-11-15 | 2019-05-08 | R1-No comments | TPSK-LSPA1-T-PL-00244 |  | 2018-10-30 | 2
036909C-1000-NM-614 | Expediting Execution Plan | 3 | 2019-06-14 | IFE | OL1-2C95-0001 | PL | 2019-06-18 | 036909C-JVD-TRN-01915 | 036909C-JVD-TRN-01915 | IFI |  | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-PL-01915 |  | 2019-06-19 | 2
036909C-1000-NM-614 | Expediting Execution Plan | 4 | 2019-07-15 | IMP | OL1-2C95-0001 | PL | 2019-07-24 | 036909C-JVD-TRN-02256 | 036909C-JVD-TRN-02256 | IFI |  |  | Transmitted | LSPA1-TPSK-T-PL-02256 |  | 2019-07-25 | 2
036909C-1000-NM-614 | Expediting Execution Plan | 2 | 2019-05-14 | IFI | OL1-2C95-0001 | PL | 2019-05-16 | 036909C-JVD-TRN-01675 | 036909C-JVD-TRN-01675 | IFI |  | 2019-05-29 | A1-Approved without comments | TPSK-LSPA1-T-PL-01675 |  | 2019-05-17 | 2
036909C-1000-NM-614 | Expediting Execution Plan | 5 | 2019-08-20 | IMP | OL1-2C95-0001 | PL | 2019-09-04 | 036909C-JVD-TRN-02568 | 036909C-JVD-TRN-02568 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PL-02568 |  | 2019-09-05 | 2
036909C-1000-NM-614 | Expediting Execution Plan | 0 | 2019-03-14 | IFI | OL1-2C95-0001 | PL | 2019-03-22 | 036909C-JVD-TRN-01134 | 036909C-JVD-TRN-01134 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01134 |  | 2019-03-22 | 2
036909C-1000-NM-614 | Expediting Execution Plan | 1 | 2019-04-22 | IFI | OL1-2C95-0001 | PL | 2019-04-19 | 036909C-JVD-TRN-01419 | 036909C-JVD-TRN-01419 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01419 |  | 2019-04-19 | 2
036909C-1000-NM-617 | Monthly Complete Expediting Report | 3 | 2019-06-14 | IFE | OL1-2C95-0002 | PL | 2019-06-18 | 036909C-JVD-TRN-01915 | 036909C-JVD-TRN-01915 | IFI |  | 2019-06-27 | R1-No comments | TPSK-LSPA1-T-PL-01915 |  | 2019-06-19 | 2
036909C-1000-NM-617 | Monthly Complete Expediting Report | 5 | 2019-08-20 | IMP | OL1-2C95-0002 | PL | 2019-09-04 | 036909C-JVD-TRN-02568 | 036909C-JVD-TRN-02568 | IFR | 2019-09-18 | 2019-09-10 | R1-No comments | TPSK-LSPA1-T-PL-02568 |  | 2019-09-05 | 2
036909C-1000-NM-617 | Monthly Complete Expediting Report | 0 | 2019-03-14 | IFI | OL1-2C95-0002 | PL | 2019-03-22 | 036909C-JVD-TRN-01134 | 036909C-JVD-TRN-01134 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01134 |  | 2019-03-22 | 2
036909C-1000-NM-617 | Monthly Complete Expediting Report | 4 | 2019-07-15 | IMP | OL1-2C95-0002 | PL | 2019-07-24 | 036909C-JVD-TRN-02256 | 036909C-JVD-TRN-02256 | IFI |  | 2019-08-02 | R1-No comments | LSPA1-TPSK-T-PL-02256 |  | 2019-07-25 | 2
036909C-1000-PP-017 | Computerized Maintenance Management System CMMS - Ex Document Client reference OL1-2W92-0001 | 0 | 2019-01-25 | IMP | OL1-2R92-0001 | PM | 2019-01-28 | 036909C-JVD-TRN-00731 | 036909C-JVD-TRN-00731 | IFR | 2019-02-11 |  | Transmitted | TPSK-LSPA1-T-PM-00731 | Ex Document Client reference OL1-2W92-0001 | 2019-01-28 | 2
036909C-1055-PID-0031-5542 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 4 | B | 2019-05-06 | IBD | OL1-2G43-5542 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5542 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 4 | A | 2019-01-17 | IFR | OL1-2G43-5542 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5540 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 3 | B | 2019-05-06 | IBD | OL1-2G43-5540 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5540 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 3 | A | 2019-01-17 | IFR | OL1-2G43-5540 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5536 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 2 | B | 2019-05-06 | IBD | OL1-2G43-5536 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5536 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 2 | A | 2019-01-17 | IFR | OL1-2G43-5536 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5535 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 1 | A | 2019-01-17 | IFR | OL1-2G43-5535 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5535 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 1 | B | 2019-05-06 | IBD | OL1-2G43-5535 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5534 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 4 | B | 2019-05-06 | IBD | OL1-2G43-5534 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5534 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 4 | A | 2019-01-17 | IFR | OL1-2G43-5534 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5533 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 3 | A | 2019-01-17 | IFR | OL1-2G43-5533 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5533 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 3 | B | 2019-05-06 | IBD | OL1-2G43-5533 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5531 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 2 | A | 2019-01-17 | IFR | OL1-2G43-5531 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5531 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 2 | B | 2019-05-06 | IBD | OL1-2G43-5531 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5529 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 1 | A | 2019-01-17 | IFR | OL1-2G43-5529 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5529 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 1 | B | 2019-05-06 | IBD | OL1-2G43-5529 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5528 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Propylene Blowdown Header - Sheet 2 | A | 2019-01-17 | IFR | OL1-2G43-5528 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5528 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Propylene Blowdown Header - Sheet 2 | B | 2019-05-06 | IBD | OL1-2G43-5528 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5526 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Propylene Blowdown Header - Sheet 1 | A | 2019-01-17 | IFR | OL1-2G43-5526 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5526 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Propylene Blowdown Header - Sheet 1 | B | 2019-05-06 | IBD | OL1-2G43-5526 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5524 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 4 | A | 2019-01-17 | IFR | OL1-2G43-5524 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5524 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 4 | B | 2019-05-06 | IBD | OL1-2G43-5524 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5523 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 3 | B | 2019-05-06 | IBD | OL1-2G43-5523 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5523 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 3 | A | 2019-01-17 | IFR | OL1-2G43-5523 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5521 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 2 | B | 2019-05-06 | IBD | OL1-2G43-5521 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5521 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 2 | A | 2019-01-17 | IFR | OL1-2G43-5521 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5519 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - LP Flare Header - Sheet 1 | A | 2019-01-17 | IFR | OL1-2G43-5519 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5519 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - LP Flare Header - Sheet 1 | B | 2019-05-06 | IBD | OL1-2G43-5519 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5518 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 6 | A | 2019-01-17 | IFR | OL1-2G43-5518 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5518 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 6 | B | 2019-05-06 | IBD | OL1-2G43-5518 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5516 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 5 | B | 2019-05-06 | IBD | OL1-2G43-5516 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5516 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 5 | A | 2019-01-17 | IFR | OL1-2G43-5516 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5514 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 4 | A | 2019-01-17 | IFR | OL1-2G43-5514 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5514 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 4 | B | 2019-05-06 | IBD | OL1-2G43-5514 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5511 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 2 | B | 2019-05-06 | IBD | OL1-2G43-5511 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5511 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 2 | A | 2019-01-17 | IFR | OL1-2G43-5511 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5510 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 1 | A | 2019-01-17 | IFR | OL1-2G43-5510 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5510 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 1 | B | 2019-05-06 | IBD | OL1-2G43-5510 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1056-PID-0031-5656 | P&ID - Olefins Unit 10 - Wastewater - Domestic Wastewater Collection | A | 2019-02-13 | IFR | OL1-2G43-5656 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00007 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5656 | P&ID - Olefins Unit 10 - Wastewater - Domestic Wastewater Collection | B | 2019-04-26 | IBD | OL1-2G43-5656 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5654 | P&ID - Olefins Unit 10 - Wastewater - Equalization Tank | A | 2019-02-13 | IFR | OL1-2G43-5654 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00007 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5654 | P&ID - Olefins Unit 10 - Wastewater - Equalization Tank | B | 2019-04-26 | IBD | OL1-2G43-5654 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5653 | P&ID - Olefins Unit 10 - Wastewater - Oily Waste Water Distribution | A | 2019-02-13 | IFR | OL1-2G43-5653 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00007 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5653 | P&ID - Olefins Unit 10 - Wastewater - Oily Waste Water Distribution | B | 2019-04-26 | IBD | OL1-2G43-5653 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00070 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5631 | P&ID - Olefins Unit 10 - Wastewater - Olefins Holding Basin - Sheet 2 | B | 2019-04-26 | IBD | OL1-2G43-5631 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1056-PID-0031-5631 | P&ID - Olefins Unit 10 - Wastewater - Olefins Holding Basin - Sheet 2 | A | 2019-02-13 | IFR | OL1-2G43-5631 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5630 | P&ID - Olefins Unit 10 - Wastewater - Olefins Holding Basin - Sheet 1 | A | 2019-02-13 | IFR | OL1-2G43-5630 | PE | 2019-02-15 | 036909C-JVD-TRN-00855 | 036909C-JVD-TRN-00855, ROC-TPSK-CECO-T-00006 | IFR | 2019-03-01 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00855 |  | 2019-02-15 | 2
036909C-1056-PID-0031-5630 | P&ID - Olefins Unit 10 - Wastewater - Olefins Holding Basin - Sheet 1 | B | 2019-04-26 | IBD | OL1-2G43-5630 | PE | 2019-04-26 | 036909C-JVD-TRN-01499 | 036909C-JVD-TRN-01499, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-13 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01499 |  | 2019-04-29 | 2
036909C-1055-PID-0031-5546 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Vent Collection System - Sheet 2 | B | 2019-05-06 | IBD | OL1-2G43-5546 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1055-PID-0031-5546 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Vent Collection System - Sheet 2 | A | 2019-01-17 | IFR | OL1-2G43-5546 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5545 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Vent Collection System - Sheet 1 | A | 2019-01-17 | IFR | OL1-2G43-5545 | PE | 2019-01-23 | 036909C-JVD-TRN-00706 | 036909C-JVD-TRN-00706, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-05 | 2019-02-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00706 |  | 2019-01-23 | 2
036909C-1055-PID-0031-5545 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Vent Collection System - Sheet 1 | B | 2019-05-06 | IBD | OL1-2G43-5545 | PE | 2019-05-06 | 036909C-JVD-TRN-01587 | 036909C-JVD-TRN-01587, ROC-TPSK-CECO-T-00069 | IFR | 2019-05-21 | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-PE-01587 |  | 2019-05-07 | 2
036909C-1052-PID-0031-5211 | P&ID - Olefins Unit 10 - Fuel System - Fuel Gas Distribution - Sheet 2 | B | 2019-04-24 | IBD | OL1-2G43-5211 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1052-PID-0031-5211 | P&ID - Olefins Unit 10 - Fuel System - Fuel Gas Distribution - Sheet 2 | A | 2019-01-30 | IFR | OL1-2G43-5211 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1052-PID-0031-5210 | P&ID - Olefins Unit 10 - Fuel System - Fuel Gas Distribution - Sheet 1 | B | 2019-04-24 | IBD | OL1-2G43-5210 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1052-PID-0031-5210 | P&ID - Olefins Unit 10 - Fuel System - Fuel Gas Distribution - Sheet 1 | A | 2019-01-30 | IFR | OL1-2G43-5210 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1052-PID-0031-5203 | P&ID - Olefins Unit 10 - Fuel System - Pilot Gas Vaporizer | A | 2019-01-30 | IFR | OL1-2G43-5203 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1052-PID-0031-5203 | P&ID - Olefins Unit 10 - Fuel System - Pilot Gas Vaporizer | B | 2019-04-24 | IBD | OL1-2G43-5203 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1052-PID-0031-5202 | P&ID - Olefins Unit 10 - Fuel System - Fuel Gas Drum | B | 2019-04-24 | IBD | OL1-2G43-5202 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1052-PID-0031-5202 | P&ID - Olefins Unit 10 - Fuel System - Fuel Gas Drum | A | 2019-01-30 | IFR | OL1-2G43-5202 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1052-PID-0031-5201 | P&ID - Olefins Unit 10 - Fuel System - Fuel Gas | B | 2019-04-24 | IBD | OL1-2G43-5201 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1052-PID-0031-5201 | P&ID - Olefins Unit 10 - Fuel System - Fuel Gas | A | 2019-01-30 | IFR | OL1-2G43-5201 | PE | 2019-01-31 | 036909C-JVD-TRN-00776 | 036909C-JVD-TRN-00776, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-14 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00776 |  | 2019-02-01 | 2
036909C-1051-PID-0031-5179 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Condensate Collection | A | 2019-01-23 | IFR | OL1-2G43-5179 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5179 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Condensate Collection | B | 2019-04-24 | IBD | OL1-2G43-5179 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5178 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 3 | A | 2019-01-23 | IFR | OL1-2G43-5178 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5178 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 3 | B | 2019-04-24 | IBD | OL1-2G43-5178 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5177 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 2 | A | 2019-01-23 | IFR | OL1-2G43-5177 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5177 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 2 | B | 2019-04-24 | IBD | OL1-2G43-5177 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5176 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 1 | B | 2019-04-24 | IBD | OL1-2G43-5176 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5176 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 1 | A | 2019-01-23 | IFR | OL1-2G43-5176 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5172 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Condensate Collection | A | 2019-01-23 | IFR | OL1-2G43-5172 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5172 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Condensate Collection | B | 2019-04-24 | IBD | OL1-2G43-5172 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1051-PID-0031-5170 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP - HP Condensate Collection | A | 2019-01-23 | IFR | OL1-2G43-5170 | PE | 2019-01-25 | 036909C-JVD-TRN-00718 | 036909C-JVD-TRN-00718, ROC-TPSK-CECO-T-00007 | IFR | 2019-02-07 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00718 |  | 2019-01-25 | 2
036909C-1051-PID-0031-5170 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP - HP Condensate Collection | B | 2019-04-24 | IBD | OL1-2G43-5170 | PE | 2019-04-25 | 036909C-JVD-TRN-01478 | 036909C-JVD-TRN-01478, ROC-TPSK-CECO-T-00068 | IFR | 2019-05-10 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01478 |  | 2019-04-26 | 2
036909C-1000-PP-125 | Project Control Procedure | 0 | 2018-10-05 | IMP | OL1-2W92-0019 | PC | 2018-10-11 | 036909C-JVD-TRN-00156 | 036909C-JVD-TRN-00156 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PC-00156 |  | 2018-10-11 | 3
036909C-1000-PP-134 | TPSK SOC Organization Chart | 0 | 2018-10-11 | IFI | OL1-2W92-0020 | PC | 2018-10-11 | 036909C-JVD-TRN-00157 | 036909C-JVD-TRN-00157 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PC-00157 |  | 2018-10-11 | 3
036909C-1000-PP-552 | Incident Investigation And Reporting Procedure | A | 2018-10-05 | IFR | OL1-2S92-0002 | ES | 2018-10-10 | 036909C-JVD-TRN-00152 | 036909C-JVD-TRN-00152 | IFR | 2018-10-24 |  | Transmitted | TPSK-LSPA1-T-ES-00152 |  | 2018-10-10 | 2
036909C-1000-PP-119 | Interface Management Plan | A | 2018-09-20 | IFR | OL1-2V92-0014 | IF | 2018-10-08 | 036909C-JVD-TRN-00138 | 036909C-JVD-TRN-00138 | IFR | 2018-10-22 | 2018-10-25 | R2-Comments as noted | TPSK-LSPA1-T-IF-00138 |  | 2018-10-08 | 2
036909C-1000-SL-0000-02 | Subvendor List For Compressor And Turboexpander - Abstract From Approved Vendor List | 0 | 2018-10-05 | IMP | OL1-2C01-0001 | PL | 2018-10-05 | 036909C-JVD-TRN-00134 | 036909C-JVD-TRN-00134 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00134 |  | 2018-10-05 | 3
036909C-1000-PP-551 | Project HSSE Plan | A | 2018-10-02 | IFR | OL1-2S92-0001 | ES | 2018-10-04 | 036909C-JVD-TRN-00129 | 036909C-JVD-TRN-00129 | IFR | 2018-10-18 |  | Transmitted | TPSK-LSPA1-T-ES-00129 |  | 2018-10-04 | 2
036909C-1000-JSD-0000-0005 | Plate-Fin Exchanger Design Specification | A | 2018-10-01 | IFR | OL1-2G01-0003 | PE | 2018-10-03 | 036909C-JVD-TRN-00123 | 036909C-JVD-TRN-00123, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-10-17 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00123 |  | 2018-10-04 | 2
036909C-1000-PP-101 | Project Execution Plan | 0 | 2018-09-28 | IFI | OL1-2W92-0013 | PC | 2018-10-02 | 036909C-JVD-TRN-00118 | 036909C-JVD-TRN-00118 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PC-00118 |  | 2018-10-02 | 3
036909C-1000-JSD-0001 | Project Design Basis | 0 | 2018-09-26 | IMP | OL1-2R07-0026 | ME | 2018-09-28 | 036909C-JVD-TRN-00110 | 036909C-JVD-TRN-00110 | IFR | 2018-10-11 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00110 |  | 2018-09-28 | 2
036909C-1000-PP-259 | Drafting Procedure For 2D Drawings | A | 2018-09-18 | IFR | OL1-2R07-0023 | ME | 2018-09-25 | 036909C-JVD-TRN-00089 | 036909C-JVD-TRN-00089 | IFR | 2018-10-09 | 2018-10-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00089 |  | 2018-09-27 | 2
036909C-1000-PP-111 | Reporting Procedure | A | 2018-09-21 | IFR | OL1-2W92-0016 | PC | 2018-09-25 | 036909C-JVD-TRN-00083 | 036909C-JVD-TRN-00083 | IFR | 2018-10-08 | 2019-03-11 | R2-Comments as noted | TPSK-LSPA1-T-PC-00083 |  | 2018-09-25 | 2
036909C-1000-PP-500 | Overall Project Quality Plan | A | 2018-09-17 | IFR | OL1-2Q92-0001 | QM | 2018-09-24 | 036909C-JVD-TRN-00072 | 036909C-JVD-TRN-00072 | IFR | 2018-10-05 | 2018-10-12 | R2-Comments as noted | TPSK-LSPA1-T-QM-00072 |  | 2018-09-24 | 2
036909C-1000-PLG-103 | Plant And Zone Codes | B | 2018-09-17 | IFR | OL1-2W01-0002 | PC | 2018-09-24 | 036909C-JVD-TRN-00077 | 036909C-JVD-TRN-00077 | IFR | 2018-10-08 | 2018-10-17 | R2-Comments as noted | TPSK-LSPA1-T-PC-00077 |  | 2018-09-25 | 2
036909C-1000-PLG-102 | Plant And Section Codes | 0 | 2018-09-17 | IMP | OL1-2B92-0006 | PC | 2018-09-24 | 036909C-JVD-TRN-00076 | 036909C-JVD-TRN-00076 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PC-00076 | New Doc. Client Ref OL1-2B92-0006 | 2018-09-25 | 3
036909C-1000-PP-601 | Project Procurement Execution Plan | A | 2018-09-13 | IFR | OL1-2C92-0001 | PC | 2018-09-14 | 036909C-JVD-TRN-00051 | 036909C-JVD-TRN-00051 | IFR | 2018-09-28 | 2018-11-29 | R2-Comments as noted | TPSK-LSPA1-T-PC-00051 |  | 2018-09-14 | 2
036909C-1000-PP-617 | Project Site Services Conditions For Supplier Specialists | A | 2018-09-12 | IFR | OL1-2C92-0017 | PL | 2018-09-14 | 036909C-JVD-TRN-00052 | 036909C-JVD-TRN-00052 | IFR | 2018-09-28 | 2018-10-04 | R2-Comments as noted | TPSK-LSPA1-T-PL-00051 |  | 2018-09-14 | 2
036909C-1000-PP-613 | Spare Parts & Specials Tools Instruction | A | 2018-09-14 | IFR | OL1-2C92-0013 | PL | 2018-09-19 | 036909C-JVD-TRN-00064 | 036909C-JVD-TRN-00064 | IFR | 2018-10-03 | 2018-09-25 | R2-Comments as noted | TPSK-LSPA1-T-PL-00064 |  | 2018-10-19 | 2
036909C-1000-PP-608 | Project QCS Expediting Procedure | A | 2018-09-11 | IFR | OL1-2C92-0008 | PL | 2018-09-13 | 036909C-JVD-TRN-00046 | 036909C-JVD-TRN-00046 | IFR | 2018-09-28 | 2018-12-03 | R2-Comments as noted | TPSK-LSPA1-T-PL-00046 |  | 2018-09-13 | 2
036909C-1000-PP-605 | Project QCS Requirements For Suppliers | A | 2018-09-11 | IFR | OL1-2C92-0005 | PL | 2018-09-13 | 036909C-JVD-TRN-00046 | 036909C-JVD-TRN-00046 | IFR | 2018-09-28 | 2018-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PL-00046 |  | 2018-09-13 | 2
036909C-1000-PP-015 | Prescriptions For Preparation Of Manufacturing Data Record Book | A | 2018-09-11 | IFR | OL1-2W92-0015 | PC | 2018-09-13 | 036909C-JVD-TRN-00047 | 036909C-JVD-TRN-00047 | IFR | 2018-09-28 |  | Transmitted | TPSK-LSPA1-T-PC-00047 |  | 2018-09-13 | 2
036909C-1000-PP-602 | Project QCS Coordination Procedure | A | 2018-09-11 | IFR | OL1-2C92-0002 | PL | 2018-09-13 | 036909C-JVD-TRN-00046 | 036909C-JVD-TRN-00046 | IFR | 2018-09-28 | 2018-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PL-00046 |  | 2018-09-13 | 2
036909C-1000-PP-615 | Transport Plan | A | 2018-08-31 | IFR | OL1-2C92-0015 | PL | 2018-09-13 | 036909C-JVD-TRN-00048 | 036909C-JVD-TRN-00048 | IFR | 2018-09-28 | 2018-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PL-00048 |  | 2018-09-13 | 2
036909C-1000-PP-616 | Parking Marking And Shipping Instructions | A | 2018-08-28 | IFR | OL1-2C92-0016 | PL | 2018-09-13 | 036909C-JVD-TRN-00048 | 036909C-JVD-TRN-00048 | IFR | 2018-09-28 | 2018-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PL-00048 |  | 2018-09-13 | 2
036909C-1000-PP-301 | Planning Scheduling And Progress Measurement Procedure | A | 2018-09-11 | IFR | OL1-2B92-0001 | PC | 2018-09-13 | 036909C-JVD-TRN-00045 | 036909C-JVD-TRN-00045 | IFR | 2018-09-28 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PC-00045 |  | 2018-09-13 | 2
036909C-1000-PP-607 | Prescriptions For Preparation Of Documentation Package For Transportation | A | 2018-08-22 | IFR | OL1-2C92-0007 | PL | 2018-09-13 | 036909C-JVD-TRN-00048 | 036909C-JVD-TRN-00048 | IFR | 2018-09-28 | 2018-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PL-00048 |  | 2018-09-13 | 2
036909C-1000-PP-609 | Project QCS Inspection Procedure | A | 2018-09-11 | IFR | OL1-2C92-0009 | PL | 2018-09-13 | 036909C-JVD-TRN-00046 | 036909C-JVD-TRN-00046 | IFR | 2018-09-28 | 2018-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PL-00046 |  | 2018-09-13 | 2
036909C-1000-PP-614 | Project Expediting And Inspection Level Definition | A | 2018-09-11 | IFR | OL1-2C92-0014 | PL | 2018-09-13 | 036909C-JVD-TRN-00046 | 036909C-JVD-TRN-00046 | IFR | 2018-09-28 | 2018-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PL-00046 |  | 2018-09-13 | 2
036909C-1000-PP-833 | Child Labor Risk Assessment Checklist | 0 | 2018-09-12 | IFI | OL1-2J94-0004 | HR | 2018-09-12 | 036909C-JVD-TRN-00040 | 036909C-JVD-TRN-00040 | IFI |  |  | Transmitted | TPSK-LSPA1-T-HR-00040 |  | 2018-09-12 | 3
036909C-1000-PP-832 | Worker Code Of Conduct Declaration Form | 0 | 2018-09-12 | IFI | OL1-2J94-0002 | HR | 2018-09-12 | 036909C-JVD-TRN-00040 | 036909C-JVD-TRN-00040 | IFI |  |  | Transmitted | TPSK-LSPA1-T-HR-00040 |  | 2018-09-12 | 3
036909C-1000-PP-831 | Human Resource Policy And Procedures | 0 | 2018-09-12 | IFI | OL1-2J93-0004 | HR | 2018-09-12 | 036909C-JVD-TRN-00040 | 036909C-JVD-TRN-00040 | IFI |  |  | Transmitted | TPSK-LSPA1-T-HR-00040 |  | 2018-09-12 | 3
036909C-1000-PP-834 | Forced Labor Risk Assessment Checklist | 0 | 2018-09-12 | IFI | OL1-2J94-0005 | HR | 2018-09-12 | 036909C-JVD-TRN-00040 | 036909C-JVD-TRN-00040 | IFI |  |  | Transmitted | TPSK-LSPA1-T-HR-00040 |  | 2018-09-12 | 3
036909C-1000-JSS-6300-02 | Jo b Specification For Weldings and NDE Of Pressure Vessels And Heat Exchangers | A | 2018-08-24 | IFR | OL1-2R03-0001 | MP | 2018-08-27 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-ME-00029 |  | 2018-08-29 | 2
036909C-1000-PP-307 | Variation Order Procedure | A | 2018-09-05 | IFR | OL1-2A92-0001 | PC | 2018-09-10 | 036909C-JVD-TRN-00035 | 036909C-JVD-TRN-00035 | IFR | 2018-09-24 |  | Transmitted | TPSK-LSPA1-T-CO-00035 |  | 2018-09-10 | 2
036909C-1000-JSS-6300-04 | Job Specification For Supply Positive Alloy Material Identification Of Equipment And Piping | A | 2018-08-24 | IFR | OL1-2R03-0003 | MP | 2018-08-27 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | R1-No comments | TPSK-LSPA1-T-ME-00029 |  | 2018-08-29 | 2
036909C-1000-STC-1890-080 | Construction Standards For Ladders And Platforms Attached To Pressure Equipment | A | 2018-08-23 | IFR | OL1-2R03-0055 | ME | 2018-08-27 | 036909C-JVD-TRN-00027 | 036909C-JVD-TRN-00027 | IFR | 2018-09-10 | 2018-09-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-00027 |  | 2018-08-29 | 2
036909C-1000-JSS-6300-05 | Job Specification For Welding And NDE Storage Tanks | A | 2018-08-24 | IFR | OL1-2R03-0004 | MP | 2018-08-27 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | R1-No comments | TPSK-LSPA1-T-ME-00029 |  | 2018-08-29 | 2
036909C-1000-PP-131 | TPSK Roc Organization Chart | A | 2018-08-24 | IFI | OL1-2W92-0007 | PC | 2018-08-27 | 036909C-JVD-TRN-00030 | 036909C-JVD-TRN-00030 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PC-00030 |  | 2018-09-03 | 3
036909C-1000-JSS-1300-01 | General Supply Specification For Piping Material | A | 2018-08-22 | IFR | OL1-2R04-0006 | MP | 2018-08-27 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-00028 |  | 2018-08-29 | 2
036909C-1000-JSS-1340-01 | Job Supply Specification For Forged Fittings | A | 2018-08-22 | IFR | OL1-2R04-0014 | MP | 2018-08-27 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00028 |  | 2018-08-29 | 2
036909C-1000-PLG-102 | Plant and section codes | A | 2018-08-10 | IFR | OL1-2W01-0001 | PM | 2018-08-10 | 036909C-JVD-TRN-00019 | 036909C-JVD-TRN-00019 | IFR | 2018-08-24 | 2018-08-22 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PC-00019 |  | 2018-08-13 | 2
036909C-1000-JSS-1350-01 | Job Supply Specification For Flanges | A | 2018-08-24 | IFR | OL1-2R04-0015 | MP | 2018-08-27 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00028 |  | 2018-08-29 | 2
036909C-1000-PP-401 | Payment And Invoicing Procedure | 0 | 2018-08-15 | IFR | OL1-2X01-0001 | PC | 2018-08-17 | 036909C-JVD-TRN-00023 | 036909C-JVD-TRN-00023 | IFR | 2018-08-30 |  | Transmitted | TPSK-LSPA1-T-PC-00023 |  | 2018-08-17 | 2
036909C-1000-JSS-0400-01 | Job Specification for Supply of Pressure Vessels | A | 2018-08-10 | IFR | OL1-2R03-0051 | ME | 2018-08-13 | 036909C-JVD-TRN-00021 | 036909C-JVD-TRN-00021 | IFR | 2018-08-27 | 2018-08-27 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-ME-00021 |  | 2018-08-13 | 2
036909C-1000-JSS-6300-03 | Job Specification For Materials In Sour Services | A | 2018-08-24 | IFR | OL1-2R03-0002 | MP | 2018-08-27 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | R1-No comments | TPSK-LSPA1-T-ME-00029 |  | 2018-08-29 | 2
036909C-1000-JSS-1330-01 | Job Supply Specification For Butt Welding Fittings | A | 2018-08-22 | IFR | OL1-2R04-0013 | MP | 2018-08-27 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00028 |  | 2018-08-29 | 2
036909C-1000-JSS-1320-01 | Job Supply Specification For Pipes | A | 2018-08-22 | IFR | OL1-2R04-0011 | MP | 2018-08-27 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-00028 |  | 2018-08-29 | 2
036909C-1000-RT-200 | Firefighting basic design report for package A1 | 0 | 2018-08-10 | IFI | OL1-2W90-0001 | PM | 2018-08-10 | 036909C-JVD-TRN-00020 | 036909C-JVD-TRN-00020 | IFI |  | 2018-08-20 | R2-Comments as noted | TPSK-LSPA1-T-PC-00020 |  | 2018-08-13 | 3
036909C-1000-PP-123 | Criticality Rating Procedure | A | 2018-08-22 | IFR | OL1-2W92-0009 | PC | 2018-09-05 | 036909C-JVD-TRN-00033 | 036909C-JVD-TRN-00033 | IFR | 2018-09-19 | 2018-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PC-00033 |  | 2018-09-06 | 2
036909C-1000-STC-0490-000 | Construction Standards For Pressure Equipment | A | 2018-08-10 | IFR | OL1-2R03-0054 | ME | 2018-08-10 | 036909C-JVD-TRN-00018 | 036909C-JVD-TRN-00018 | IFR | 2018-08-24 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00018 |  | 2018-08-13 | 2
036909C-1000-PP-110 | Document management procedure | A | 2018-08-08 | IFR | OL1-2W92-0004 | PC | 2018-08-08 | 036909C-JVD-TRN-00013 | 036909C-JVD-TRN-00013 | IFR | 2018-08-22 | 2018-08-29 | R2-Comments as noted | TPSK-LSPA1-T-PC-00013 |  | 2018-08-09 | 2
036909C-1000-JSS-0570-01 | Job Specification For Supply Of Column Internals | A | 2018-08-09 | IFR | OL1-2R03-0052 | ME | 2018-08-10 | 036909C-JVD-TRN-00017 | 036909C-JVD-TRN-00017 | IFR | 2018-08-24 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00017 |  | 2018-08-13 | 2
036909C-1000-PLG-103 | Work Breakdown Structure | A | 2018-07-30 | IFR | OL1-2W01-0002 | PC | 2018-08-09 | 036909C-JVD-TRN-00015 | 036909C-JVD-TRN-00015 | IFR | 2018-08-23 | 2018-08-17 | A4 - Not approve | TPSK-LSPA1-T-PC-00015 |  | 2018-08-09 | 2
036909C-1000-JSD-1300-0002 | Piping Design Specification | A | 2018-08-07 | IFR | OL1-2R04-0002 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | 2018-08-08 | 2
036909C-1000-STC-1390-0001 | Piping Construction Drawing | A | 2018-08-07 | IFR | OL1-2P92-0003 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | 2018-08-08 | 2
036909C-1000-JSD-1300-0003 | Job Design Specification For Steam Tracing | A | 2018-08-07 | IFR | OL1-2R04-0031 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | 2018-08-08 | 2
036909C-1000-JSD-0400-01 | Job Specification For Design Of Pressure & Atmospheric Static Equipment | A | 2018-08-09 | IFR | OL1-2R03-0050 | ME | 2018-08-10 | 036909C-JVD-TRN-00017 | 036909C-JVD-TRN-00017 | IFR | 2018-08-24 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00017 |  | 2018-08-13 | 2
036909C-1000-JSS-1820-01 | Job Specification For Supply Of Equipment Ladders And Platforms | A | 2018-08-09 | IFR | OL1-2R03-0053 | ME | 2018-08-10 | 036909C-JVD-TRN-00017 | 036909C-JVD-TRN-00017 | IFR | 2018-08-24 | 2018-08-27 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-ME-00017 |  | 2018-08-13 | 2
036909C-1000-STD-1380-0001 | Piping Design Standard Drawings | A | 2018-08-07 | IFR | OL1-2P92-0002 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | 2018-08-08 | 2
036909C-1000-JSD-1600-008 | General Design Rule For Smartplant Electrical - For Next Revision See Document OL1-2E92-0001 | A | 2018-08-03 | IFR | OL1-2E92-0001 | EE | 2018-08-06 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 | For Next Revision See Document OL1-2E92-0001 | 2018-08-07 | 3
036909C-1000-JSD-1600-003 | General Design Rule For Package Equipment Electrical System - Client code for next revision will be OL1-2E04-6000 | A | 2018-08-03 | IFR | OL1-2R05-0042 | EE | 2018-08-06 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 |  | 2018-08-07 | 2
036909C-1000-PP-1600-003 | Coordination Procedure For ETAP For Next Revision See Document OL1-2E92-0003 | A | 2018-08-03 | IFI | OL1-2E92-0003 | EE | 2018-08-06 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 | For Next Revision See Document OL1-2E92-0003 | 2018-08-07 | 3
036909C-1000-PP-100 | TPSK Project Directorate Organization Chart | 0 | 2018-08-06 | IFI | OL1-2W92-0006 | PC | 2018-08-06 | 036909C-JVD-TRN-00010 | 036909C-JVD-TRN-00010 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PC-00010 |  | 2018-08-07 | 3
036909C-1000-DI-0007-0001 | Process Design Basis | A | 2018-07-20 | IFA | OL1-2G02-0001 | PE | 2018-07-30 | 036909C-JVD-TRN-00002 | 036909C-JVD-TRN-00002, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-10 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00002 |  | 2018-07-27 | 1
036909C-1000-PP-1600-001 | Coordination Procedure For Smartplant Electrical - For Next Revision See Document OL1-2E92-0002 | A | 2018-08-03 | IFR | OL1-2E92-0002 | EE | 2018-08-06 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 | For Next Revision See Document OL1-2E92-0002 | 2018-08-07 | 3
036909C-1000-DI-0007-0002 | Equipment Basis Of Design | A | 2018-07-24 | IFA | OL1-2G02-0002 | PE | 2018-07-30 | 036909C-JVD-TRN-00002 | 036909C-JVD-TRN-00002, ROC-TPSK-CECO-T-00012 | IFA | 2018-08-10 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00002 |  | 2018-07-27 | 1
036909C-1000-JSD-0000-03 | JSD for P&ID Preparation | A | 2018-07-31 | IFA | OL1-2G01-0001 | PE | 2018-07-31 | 036909C-JVD-TRN-00006 | 036909C-JVD-TRN-00006 | IFR | 2018-08-13 | 2018-08-21 | Transmitted | TPSK-LSPA1-T-PE-00006 |  | 2018-07-31 | 2
036909C-1000-PP-102 | Coordination Procedure | A | 2018-07-26 | IFR | OL1-2W92-0001 | PC | 2018-07-30 | 036909C-JVD-TRN-00001 | 036909C-JVD-TRN-00001 | IFR | 2018-08-10 | 2018-08-22 | Transmitted | TPSK-LSPA1-T-PM-00001 |  | 2018-07-27 | 2
036909C-1000-PP-107 | Project Document Coding | A | 2018-07-26 | IFR | OL1-2W92-0003 | PM | 2018-07-30 | 036909C-JVD-TRN-00001 | 036909C-JVD-TRN-00001 | IFR | 2018-08-10 | 2018-08-22 | Transmitted | TPSK-LSPA1-T-PM-00001 |  | 2018-07-27 | 2
036909C-1000-PP-106 | Tagging Procedure | A | 2018-07-26 | IFR | OL1-2R07-0001 | ME | 2018-07-30 | 036909C-JVD-TRN-00001 | 036909C-JVD-TRN-00001 | IFR | 2018-08-10 | 2018-08-22 | Transmitted | TPSK-LSPA1-T-PM-00001 |  | 2018-07-27 | 2
036909C-105U-DW-1442-0001 | Major Underground Networks - Zone 5U - Cooling Water Unit - Ex Doc Client Ref OL1-2K36-0011 | B | 2019-09-11 | IDD | OL1-2K26-0011 | CV | 2019-09-12 | 036909C-JVD-TRN-02635 | 036909C-JVD-TRN-02635 | IFA | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-CV-02635 | Ex Doc Client Ref OL1-2K36-0011 | 2019-09-13 | 1
036909C-105W-DW-1442-0001 | Major Underground Networks - Zone 5W - Waste Water Treatment - Ex Doc Client Ref OL1-2K36-0012 | B | 2019-09-11 | IDD | OL1-2K26-0012 | CV | 2019-09-12 | 036909C-JVD-TRN-02635 | 036909C-JVD-TRN-02635 | IFA | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-CV-02635 | Ex Doc Client Ref OL1-2K36-0012 | 2019-09-13 | 1
036909C-105T-DW-1442-0001 | Major Underground Networks - Zone 5T - Cooling Water Unit - Ex Doc Client Ref OL1-2K36-0010 | B | 2019-09-11 | IDD | OL1-2K26-0010 | CV | 2019-09-12 | 036909C-JVD-TRN-02635 | 036909C-JVD-TRN-02635 | IFA | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-CV-02635 | Ex Doc Client Ref OL1-2K36-0010 | 2019-09-13 | 1
036909C-103S-DW-1442-0001 | Major Underground Networks - Zone 3S - Substation-C Far-C - Ex Doc Client Ref OL1-2K36-0009 | B | 2019-09-11 | IDD | OL1-2K26-0009 | CV | 2019-09-12 | 036909C-JVD-TRN-02635 | 036909C-JVD-TRN-02635 | IFA | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-CV-02635 | Ex Doc Client Ref OL1-2K36-0009 | 2019-09-12 | 1
036909C-100C-DW-1442-0001 | Major Underground Networks Zone 0C - Common Area - Ex Doc Client Ref OL1-2K36-0014 | B | 2019-09-11 | IDD | OL1-2K26-0014 | CV | 2019-09-12 | 036909C-JVD-TRN-02635 | 036909C-JVD-TRN-02635 | IFA | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-CV-02635 | Common Area - Ex Doc Client Ref OL1-2K36-0014 | 2019-09-13 | 1
036909C-100S-DW-1442-0001 | Major Underground Networks Zone 0S - Substation-E And Far-E - Ex Doc Client Ref OL1-2K36-0001 | B | 2019-09-11 | IDD | OL1-2K26-0001 | CV | 2019-09-12 | 036909C-JVD-TRN-02635 | 036909C-JVD-TRN-02635 | IFA | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-CV-02635 | Ex Doc Client Ref OL1-2K36-0001 | 2019-09-13 | 1
036909C-105W-DW-1442-0001 | Major Underground Networks - Zone 5W - Waste Water Treatment | A | 2019-03-22 | IFR | OL1-2K36-0012 | CV | 2019-03-25 | 036909C-JVD-TRN-01138 | 036909C-JVD-TRN-01138, ROC-TPSK-CECO-T-00025 | IFR | 2019-04-09 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01138 |  | 2019-03-26 | 2
036909C-105U-DW-1442-0001 | Major Underground Networks - Zone 5U - Utilities | A | 2019-03-22 | IFR | OL1-2K36-0011 | CV | 2019-03-25 | 036909C-JVD-TRN-01138 | 036909C-JVD-TRN-01138, ROC-TPSK-CECO-T-00025 | IFR | 2019-04-09 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01138 |  | 2019-03-26 | 2
036909C-105T-DW-1442-0001 | Major Underground Networks - Zone 5T - Cooling Water Unit | A | 2019-03-22 | IFR | OL1-2K36-0010 | CV | 2019-03-25 | 036909C-JVD-TRN-01138 | 036909C-JVD-TRN-01138, ROC-TPSK-CECO-T-00025 | IFR | 2019-04-09 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01138 |  | 2019-03-26 | 2
036909C-100S-DW-1442-0001 | Major Underground Networks Zone 0S - Substation-E And Far-E | A | 2019-03-22 | IFR | OL1-2K36-0001 | CV | 2019-03-25 | 036909C-JVD-TRN-01138 | 036909C-JVD-TRN-01138, ROC-TPSK-CECO-T-00025 | IFR | 2019-04-09 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01138 |  | 2019-03-26 | 2
036909C-100C-DW-1442-0001 | Major Underground Networks Zone 0C - Common Area | A | 2019-03-26 | IFR | OL1-2K36-0014 | CV | 2019-03-27 | 036909C-JVD-TRN-01172 | 036909C-JVD-TRN-01172, ROC-TPSK-CECO-T-00037 | IFR | 2019-04-11 |  | Transmitted | TPSK-LSPA1-T-CV-01172 |  | 2019-03-28 | 2
036909C-1026-DI-0007-2601 | Area Basis of Design - 26 Hot Fractionation | B | 2019-04-03 | IFD | OL1-2G05-2601 | PE | 2019-04-04 | 036909C-JVD-TRN-01249 | 036909C-JVD-TRN-01249 | IFA | 2019-04-19 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01249 |  | 2019-04-05 | 1
036909C-103S-DW-1442-0001 | Major Underground Networks - Zone 3S - Substation-C Far-C | A | 2019-03-22 | IFR | OL1-2K36-0009 | CV | 2019-03-25 | 036909C-JVD-TRN-01138 | 036909C-JVD-TRN-01138, ROC-TPSK-CECO-T-00025 | IFR | 2019-04-09 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01138 |  | 2019-03-26 | 2
036909C-105U-DW-1622-0101 | Electrical Main Cable Routing Layout- Zone 5U Utilities | A | 2019-09-11 | IFR | OL1-2E31-0017 | EE | 2019-09-12 | 036909C-JVD-TRN-02632 | 036909C-JVD-TRN-02632 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-EE-02632 |  | 2019-09-12 | 2
036909C-105T-DW-1741-0002 | Foundation For Pipe Bridge 10-Prk-5T02 - Plan Sections & Details | A | 2019-09-06 | IFR | OL1-2K31-0390 | CV | 2019-09-12 | 036909C-JVD-TRN-02631 | 036909C-JVD-TRN-02631 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02631 |  | 2019-09-12 | 2
036909C-1030-SP-0510-3060 | Mechanical Equipment Data Sheet C4 Acetylene Washer | 0 | 2019-09-05 | IFP | OL1-2M03-3060 | ME | 2019-09-10 | 036909C-JVD-TRN-02613 | 036909C-JVD-TRN-02613 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-ME-02613 |  | 2019-09-12 | 2
036909C-1031-SP-0510-3110 | Mechanical Equipment Data Sheet Water Tower | 0 | 2019-09-03 | IFP | OL1-2M03-3110 | ME | 2019-09-10 | 036909C-JVD-TRN-02613 | 036909C-JVD-TRN-02613 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-ME-02613 |  | 2019-09-12 | 2
036909C-102E-DW-1841-0001-019 | Steel For Pipe Rack 10-PRK-2E01 - Details | A | 2019-09-09 | IFR | OL1-2K32-1138 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-1030-SP-0510-3020 | Mechanical Equipment Data Sheet Main Washer | 0 | 2019-09-10 | IFP | OL1-2M03-3020 | ME | 2019-09-10 | 036909C-JVD-TRN-02613 | 036909C-JVD-TRN-02613 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-ME-02613 |  | 2019-09-12 | 2
036909C-102E-DW-1841-0001-018 | Steel For Pipe Rack 10-PRK-2E01 - Ladder Platform | A | 2019-09-09 | IFR | OL1-2K32-1137 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-014 | Steel For Pipe Rack 10-PRK-2E01 - Elevations | A | 2019-09-09 | IFR | OL1-2K32-1133 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-016 | Steel Pipe Rack 10-PRK-2E01 - Stair Plan & Sections | A | 2019-09-09 | IFR | OL1-2K32-1135 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-015 | Steel For Pipe Rack 10-PRK-2E01 - Elevations | A | 2019-09-09 | IFR | OL1-2K32-1134 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-012 | Steel For Pipe Rack 10-PRK-2E01 - Elevations | A | 2019-09-09 | IFR | OL1-2K32-1131 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-017 | Steel Pipe Rack 10-PRK-2E01 - Stair Plan & Sections | A | 2019-09-09 | IFR | OL1-2K32-1136 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-013 | Steel For Pipe Rack 10-PRK-2E01 - Elevations | A | 2019-09-09 | IFR | OL1-2K32-1132 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-007 | Steel For Pipe Rack 10-PRK-2E01 - Plans | A | 2019-09-09 | IFR | OL1-2K32-1126 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-005 | Steel For Pipe Rack 10-PRK-2E01 - Plans | A | 2019-09-09 | IFR | OL1-2K32-1124 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-006 | Steel For Pipe Rack 10-PRK-2E01 - Plans | A | 2019-09-09 | IFR | OL1-2K32-1125 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-010 | Steel For Pipe Rack 10-PRK-2E01 - Elevations | A | 2019-09-09 | IFR | OL1-2K32-1129 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-011 | Steel For Pipe Rack 10-PRK-2E01 - Elevations | A | 2019-09-09 | IFR | OL1-2K32-1130 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-008 | Steel For Pipe Rack 10-PRK-2E01 - Elevations | A | 2019-09-09 | IFR | OL1-2K32-1127 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-009 | Steel For Pipe Rack 10-PRK-2E01 - Elevations | A | 2019-09-09 | IFR | OL1-2K32-1128 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-004 | Steel For Pipe Rack 10-PRK-2E01 - Plans | A | 2019-09-09 | IFR | OL1-2K32-1123 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102A-DW-1622-0101 | Electrical Main Cable Routing Layout Zone 2A | A | 2019-09-10 | IFR | OL1-2E31-0011 | EE | 2019-09-11 | 036909C-JVD-TRN-02622 | 036909C-JVD-TRN-02622 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-EE-02622 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-002 | Steel For Pipe Rack 10-PRK-2E01 - Plans | A | 2019-09-09 | IFR | OL1-2K32-1121 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-003 | Steel For Pipe Rack 10-PRK-2E01 - Plans | A | 2019-09-09 | IFR | OL1-2K32-1122 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-102D-DW-1622-0101 | Electrical Main Cable Routing Layout Zone 2D | A | 2019-09-10 | IFR | OL1-2E31-0014 | EE | 2019-09-11 | 036909C-JVD-TRN-02622 | 036909C-JVD-TRN-02622 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-EE-02622 |  | 2019-09-12 | 1
036909C-102E-DW-1622-0101 | Electrical Main Cable Routing Layout Zone 2E | A | 2019-09-10 | IFR | OL1-2E31-0015 | EE | 2019-09-11 | 036909C-JVD-TRN-02622 | 036909C-JVD-TRN-02622 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-EE-02622 |  | 2019-09-12 | 1
036909C-102B-DW-1622-0101 | Electrical Main Cable Routing Layout Zone 2B | A | 2019-09-10 | IFR | OL1-2E31-0012 | EE | 2019-09-11 | 036909C-JVD-TRN-02622 | 036909C-JVD-TRN-02622 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-EE-02622 |  | 2019-09-12 | 1
036909C-102C-DW-1622-0101 | Electrical Main Cable Routing Layout Zone 2C | A | 2019-09-10 | IFR | OL1-2E31-0013 | EE | 2019-09-11 | 036909C-JVD-TRN-02622 | 036909C-JVD-TRN-02622 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-EE-02622 |  | 2019-09-12 | 1
036909C-102E-DW-1841-0001-001 | Steel Elevation For Pipe Rack 10-PRK-2E01 - 3D View | A | 2019-09-09 | IFR | OL1-2K32-1120 | CV | 2019-09-11 | 036909C-JVD-TRN-02615 | 036909C-JVD-TRN-02615 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02615 |  | 2019-09-12 | 1
036909C-1012-MR-1553-1255 | Material Requisition for Draft Gauge | A | 2019-09-09 | IFQ | OL1-2C17-042255 | PL | 2019-09-11 | 036909C-JVD-TRN-02627 | 036909C-JVD-TRN-02627 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-PL-02627 |  | 2019-09-12 | 2
036909C-1012-DW-0131-2527 | USC 132U Cracking Furnace Steel Convection Section Header Box Elevations | 1 | 2019-09-09 | IMP | OL1-2K32-2527 | CV | 2019-09-11 | 036909C-JVD-TRN-02628 | 036909C-JVD-TRN-02628 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02628 |  | 2019-09-12 | 3
036909C-1012-DW-0131-2551 | USC 132U Cracking Furnace Steel Instrument Connection Details | 2 | 2019-09-09 | IMP | OL1-2K32-2551 | CV | 2019-09-11 | 036909C-JVD-TRN-02624 | 036909C-JVD-TRN-02624 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02624 |  | 2019-09-12 | 3
036909C-1012-DW-0131-2550 | USC 132U Cracking Furnace Steel Stack Sections and Details | 1 | 2019-08-26 | IMP | OL1-2K32-2550 | CV | 2019-09-10 | 036909C-JVD-TRN-02606 | 036909C-JVD-TRN-02606 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02606 |  | 2019-09-10 | 3
036909C-1012-DW-0127-2204 | USC 132U Cracking Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill of Material | 3 | 2019-09-09 | IMP | OL1-2M06-2204 | ME | 2019-09-11 | 036909C-JVD-TRN-02625 | 036909C-JVD-TRN-02625 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-ME-02625 |  | 2019-09-12 | 2
036909C-1012-DW-0117-2005 | USC 132U Cracking Furnace General Arrangement Instrumentation Sections | 2 | 2019-09-09 | IMP | OL1-2M06-2005 | ME | 2019-09-11 | 036909C-JVD-TRN-02626 | 036909C-JVD-TRN-02626 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-ME-02626 |  | 2019-09-12 | 2
036909C-1012-DW-0117-2004 | USC 132U Cracking Furnace General Arrangement Instrumentation | 2 | 2019-09-09 | IMP | OL1-2M06-2004 | ME | 2019-09-11 | 036909C-JVD-TRN-02626 | 036909C-JVD-TRN-02626 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-ME-02626 |  | 2019-09-12 | 2
036909C-100P-DW-1622-0101 | Electrical Main Cable Routing Layout Zone 0P | A | 2019-09-10 | IFR | OL1-2E31-0003 | EE | 2019-09-11 | 036909C-JVD-TRN-02622 | 036909C-JVD-TRN-02622 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-EE-02622 |  | 2019-09-12 | 1
036909C-1011-DW-0131-1527 | USC 36M Recycle Furnace Steel Convection Section Header Box Elevations | 1 | 2019-09-09 | IMP | OL1-2K32-1527 | CV | 2019-09-11 | 036909C-JVD-TRN-02628 | 036909C-JVD-TRN-02628 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02628 |  | 2019-09-12 | 3
036909C-1011-DW-0117-1551 | USC 36M Recycle Furnace Steel Instrument Connection Details | 3 | 2019-09-09 | IMP | OL1-2K32-1551 | CV | 2019-09-11 | 036909C-JVD-TRN-02624 | 036909C-JVD-TRN-02624 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02624 |  | 2019-09-12 | 3
036909C-1011-DW-0117-1004 | USC 36M Recycle Furnace General Arrangement Instrumentation | 2 | 2019-09-09 | IMP | OL1-2M06-1004 | ME | 2019-09-11 | 036909C-JVD-TRN-02626 | 036909C-JVD-TRN-02626 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-ME-02626 |  | 2019-09-12 | 2
036909C-1011-DW-0125-1304 | USC 36M Recycle Furnace Steel End Wall Tubesheet Details | 1 | 2019-09-09 | IMP | OL1-2K32-1304 | CV | 2019-09-11 | 036909C-JVD-TRN-02624 | 036909C-JVD-TRN-02624 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02624 |  | 2019-09-12 | 3
036909C-1011-DW-0127-1204 | USC 36M Recycle Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill of Material | 3 | 2019-09-09 | IMP | OL-2M06-1204 | ME | 2019-09-11 | 036909C-JVD-TRN-02629 | 036909C-JVD-TRN-02629 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-ME-02629 |  | 2019-09-12 | 2
036909C-1011-DW-0117-1005 | USC 36M Recycle Furnace General Arrangement Instrumentation Sections | 2 | 2019-09-09 | IMP | OL1-2M06-1005 | ME | 2019-09-11 | 036909C-JVD-TRN-02629 | 036909C-JVD-TRN-02629 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-ME-02629 |  | 2019-09-12 | 2
036909C-1000-PS-1422-0003 | Olefin Plant - Additional Ground Investigation - Phase 2 -Platform at 6-7m HDD- Price List | 0 | 2019-09-10 | IFP | OL1-2K43-0007 | CV | 2019-09-11 | 036909C-JVD-TRN-02617 | 036909C-JVD-TRN-02617 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02617 |  | 2019-09-12 | 2
036909C-1000-PS-1422-0004 | Flare Area - Additional Ground Investigation- Price List | 0 | 2019-09-10 | IFP | OL1-2K43-0009 | CV | 2019-09-11 | 036909C-JVD-TRN-02617 | 036909C-JVD-TRN-02617 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02617 |  | 2019-09-12 | 2
036909C-1000-PS-1422-0002 | Olefin Plant - Additional Ground Investigation - Phase 1 -Platform at 4-5m HDD- Price List | 0 | 2019-09-10 | IFP | OL1-2K43-0005 | CV | 2019-09-11 | 036909C-JVD-TRN-02617 | 036909C-JVD-TRN-02617 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02617 |  | 2019-09-12 | 2
036909C-1000-MR-0511-0003 | Material Requisition For Shop Assembled Columns (C4 Unit) | 0 | 2019-09-11 | IFP | OL1-2C13-102000 | PL | 2019-09-11 | 036909C-JVD-TRN-02616 | 036909C-JVD-TRN-02616 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PL-02616 |  | 2019-09-12 | 2
036909C-1000-MS-1422-0002 | Additional Ground Investigation Technical Specification | 0 | 2019-09-10 | IFP | OL1-2R02-0012 | CV | 2019-09-11 | 036909C-JVD-TRN-02618 | 036909C-JVD-TRN-02618 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02618 |  | 2019-09-12 | 2
036909C-1000-DW-1422-0004-001 | Flare Area - Additional Ground Investigation Layout Of Site Investigations | 0 | 2019-09-10 | IFP | OL1-2K43-0010 | CV | 2019-09-11 | 036909C-JVD-TRN-02619 | 036909C-JVD-TRN-02619 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02619 |  | 2019-09-12 | 2
036909C-1000-DW-1422-0003-001 | Olefins Plant - Additional Ground Investigation Phase 2 -Platform at 6-7m HDD - Layout of Site Investigations | 0 | 2019-09-10 | IFP | OL1-2K43-0008 | CV | 2019-09-11 | 036909C-JVD-TRN-02619 | 036909C-JVD-TRN-02619 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02619 |  | 2019-09-12 | 2
036909C-1000-CN-1651-0005 | Power Factor Improvement System Study | A | 2019-09-11 | IFR | OL1-2E13-0001 | EE | 2019-09-11 | 036909C-JVD-TRN-02623 | 036909C-JVD-TRN-02623 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-EE-02623 |  | 2019-09-12 | 1
036909C-1000-DW-1422-0002-001 | Olefins Plant - Additional Ground Investigation Phase 1 -Platform at 4-5m HDD - Layout of Site Investigations | 0 | 2019-09-10 | IFP | OL1-2K43-0006 | CV | 2019-09-11 | 036909C-JVD-TRN-02619 | 036909C-JVD-TRN-02619 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-CV-02619 |  | 2019-09-12 | 2
036909C-1000-CN-1600-0003 | Motor Starting Study | A | 2019-09-10 | IFR | OL1-2E10-0006 | EE | 2019-09-11 | 036909C-JVD-TRN-02623 | 036909C-JVD-TRN-02623 | IFA | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-EE-02623 |  | 2019-09-12 | 1
036909C-103S-DW-1625-0001 | Substation C Equipment Layout | B | 2019-08-23 | IFR | OL1-2E20-0002 | EE | 2019-08-23 | 036909C-JVD-TRN-02480 | 036909C-JVD-TRN-02480 | IFA | 2019-09-09 | 2019-09-09 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02480 |  | 2019-08-26 | 1
036909C-1012-DW-0117-2004 | USC 132U Cracking Furnace General Arrangement Instrumentation | A | 2019-01-28 | IFR | OL1-2M06-2004 | ME | 2019-01-30 | 036909C-JVD-TRN-00766 | 036909C-JVD-TRN-00766 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00766 |  | 2019-01-31 | 2
036909C-1012-DW-0117-2004 | USC 132U Cracking Furnace General Arrangement Instrumentation | 1 | 2019-06-21 | IMP | OL1-2M06-2004 | ME | 2019-06-25 | 036909C-JVD-TRN-01993 | 036909C-JVD-TRN-01993 | IFR | 2019-07-10 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-01993 |  | 2019-06-26 | 2
036909C-1012-DW-0117-2004 | USC 132U Cracking Furnace General Arrangement Instrumentation | 0 | 2019-04-25 | IMP | OL1-2M06-2004 | ME | 2019-04-26 | 036909C-JVD-TRN-01500 | 036909C-JVD-TRN-01500 | IFR | 2019-05-11 |  | Transmitted | TPSK-LSPA1-T-ME-01500 |  | 2019-04-26 | 2
036909C-1000-MR-0511-0003 | Material Requisition For Shop Assembled Columns (C4 Unit) | A | 2019-05-08 | IFQ | OL1-2C13-102000 | PL | 2019-05-09 | 036909C-JVD-TRN-01623 | 036909C-JVD-TRN-01623 | IFR | 2019-05-23 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PL-01623 |  | 2019-05-10 | 2
036909C-1000-PS-1422-0003 | Olefin Plant - Additional Ground Investigation - Phase 2 -Platform at 6-7m HDD- Price List | C | 2019-06-17 | IFI | OL1-2K43-0007 | CV | 2019-06-21 | 036909C-JVD-TRN-01963 | 036909C-JVD-TRN-01963 | IFR | 2019-07-08 |  | Transmitted | TPSK-LSPA1-T-CV-01963 |  | 2019-06-24 | 2
036909C-1000-PS-1422-0003 | Olefin Plant - Additional Ground Investigation - Phase 2 Platform at 6-7m HDD- Price List | B | 2019-06-06 | IFI | OL1-2K43-0007 | CV | 2019-06-11 | 036909C-JVD-TRN-01861 | 036909C-JVD-TRN-01861 | IFR | 2019-06-26 | 2019-06-27 | R1-No comments | TPSK-LSPA1-T-CV-01861 |  | 2019-06-11 | 2
036909C-1000-PS-1422-0002 | Olefin Plant - Additional Ground Investigation - Phase 1 -Platform at 4-5m HDD- Price List | C | 2019-06-17 | IFI | OL1-2K43-0005 | CV | 2019-06-21 | 036909C-JVD-TRN-01963 | 036909C-JVD-TRN-01963 | IFR | 2019-07-08 |  | Transmitted | TPSK-LSPA1-T-CV-01963 |  | 2019-06-24 | 2
036909C-1000-PS-1422-0002 | Olefin Plant - Additional Ground Investigation - Phase 1 Platform at 4-5m HDD- Price List | B | 2019-06-06 | IFI | OL1-2K43-0005 | CV | 2019-06-11 | 036909C-JVD-TRN-01861 | 036909C-JVD-TRN-01861 | IFR | 2019-06-26 | 2019-06-27 | R1-No comments | TPSK-LSPA1-T-CV-01861 |  | 2019-06-11 | 2
036909C-1000-MS-1422-0002 | Additional Ground Investigation Technical Specification | A | 2019-05-24 | IFR | OL1-2R02-0012 | CV | 2019-05-31 | 036909C-JVD-TRN-01788 | 036909C-JVD-TRN-01788 | IFR | 2019-06-17 | 2019-06-20 | R2-Comments as noted | TPSK-LSPA1-T-CV-01788 |  | 2019-06-03 | 2
036909C-1000-MS-1422-0002 | Additional Ground Investigation Technical Specification | B | 2019-06-06 | IFI | OL1-2R02-0012 | CV | 2019-06-11 | 036909C-JVD-TRN-01860 | 036909C-JVD-TRN-01860 | IFR | 2019-06-26 |  | Transmitted | TPSK-LSPA1-T-CV-01860 |  | 2019-06-11 | 2
036909C-1000-MS-1422-0002 | Additional Ground Investigation Technical Specification | C | 2019-06-17 | IFI | OL1-2R02-0012 | CV | 2019-06-21 | 036909C-JVD-TRN-01962 | 036909C-JVD-TRN-01962 | IFR | 2019-07-08 | 2019-08-21 | R1-No comments | TPSK-LSPA1-T-CV-01962 |  | 2019-06-24 | 2
036909C-1000-DW-1422-0004-001 | Flare Area - Additional Ground Investigation Layout Of Site Investigations | A | 2019-05-24 | IFR | OL1-2K43-0010 | CV | 2019-05-30 | 036909C-JVD-TRN-01768 | 036909C-JVD-TRN-01768 | IFR | 2019-06-14 | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-CV-01768 |  | 2019-05-31 | 2
036909C-1000-DW-1422-0003-001 | Olefins Plant - Additional Ground Investigation Phase 2 -Platform At +6-7m HDD- Layout Of Site Investigations | A | 2019-05-24 | IFR | OL1-2K43-0008 | CV | 2019-05-30 | 036909C-JVD-TRN-01768 | 036909C-JVD-TRN-01768 | IFR | 2019-06-14 | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-CV-01768 |  | 2019-05-31 | 2
036909C-1000-DW-1422-0003-001 | Olefins Plant - Additional Ground Investigation Phase 2 -Platform at 6-7m HDD - Layout Of Site Investigations | C | 2019-06-17 | IFI | OL1-2K43-0008 | CV | 2019-06-21 | 036909C-JVD-TRN-01957 | 036909C-JVD-TRN-01957 | IFR | 2019-07-08 |  | Transmitted | TPSK-LSPA1-T-CV-01957 |  | 2019-06-24 | 2
036909C-1000-DW-1422-0002-001 | Olefins Plant - Additional Ground Investigation Phase 1 Platform at 4-5m HDD - Layout of Site Investigations | B | 2019-06-06 | IFR | OL1-2K43-0006 | CV | 2019-06-11 | 036909C-JVD-TRN-01853 | 036909C-JVD-TRN-01853 | IFR | 2019-06-26 |  | Transmitted | TPSK-LSPA1-T-CV-01853 |  | 2019-06-11 | 2
036909C-1000-DW-1422-0002-001 | Olefins Plant - Additional Ground Investigation Phase 1 - Platform at 4-5m HDD - Layout Of Site Investigations | C | 2019-06-17 | IFI | OL1-2K43-0006 | CV | 2019-06-21 | 036909C-JVD-TRN-01957 | 036909C-JVD-TRN-01957 | IFR | 2019-07-08 |  | Transmitted | TPSK-LSPA1-T-CV-01957 |  | 2019-06-24 | 2
036909C-1000-DW-1422-0002-001 | Olefins Plant - Additional Ground Investigation Phase 1 - Platform At +4-5m HDD- Layout Of Site Investigations | A | 2019-05-24 | IFR | OL1-2K43-0006 | CV | 2019-05-30 | 036909C-JVD-TRN-01768 | 036909C-JVD-TRN-01768 | IFR | 2019-06-14 | 2019-07-16 | R2-Comments as noted | TPSK-LSPA1-T-CV-01768 |  | 2019-05-31 | 2
036909C-1012-DW-0131-2551 | USC 132U Cracking Furnace Steel Instrument Connection Details | A | 2019-01-28 | IFI | OL1-2K32-2551 | ME | 2019-01-30 | 036909C-JVD-TRN-00767 | 036909C-JVD-TRN-00767 | IFI |  | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00767 |  | 2019-01-31 | 3
036909C-1012-DW-0131-2551 | USC 132U Cracking Furnace Steel Instrument Connection Details | 0 | 2019-04-25 | IMP | OL1-2K32-2551 | ME | 2019-04-26 | 036909C-JVD-TRN-01501 | 036909C-JVD-TRN-01501 | IFI |  | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-ME-01501 |  | 2019-04-29 | 3
036909C-1012-DW-0131-2551 | USC 132U Cracking Furnace Steel Instrument Connection Details | 1 | 2019-06-21 | IMP | OL1-2K32-2551 | CV | 2019-06-25 | 036909C-JVD-TRN-01994 | 036909C-JVD-TRN-01994 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01994 |  | 2019-06-26 | 3
036909C-1011-DW-0125-1304 | USC 36M Recycle Furnace Steel End Wall Tubesheet Details | 0 | 2019-05-24 | IMP | OL1-2K32-1304 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1011-DW-0125-1304 | USC 36M Recycle Furnace Steel End Wall Tubesheet Details | A | 2019-04-05 | IFI | OL1-2K32-1304 | CV | 2019-04-11 | 036909C-JVD-TRN-01321 | 036909C-JVD-TRN-01321 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01321 |  | 2019-04-12 | 3
036909C-1011-DW-0117-1551 | USC 36M Recycle Furnace Steel Instrument Connection Details | 1 | 2019-05-24 | IMP | OL1-2K32-1551 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1011-DW-0117-1551 | USC 36M Recycle Furnace Steel Instrument Connection Details | 2 | 2019-06-21 | IMP | OL1-2K32-1551 | CV | 2019-06-25 | 036909C-JVD-TRN-01994 | 036909C-JVD-TRN-01994 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01994 |  | 2019-06-26 | 3
036909C-1011-DW-0117-1551 | USC 36M Recycle Furnace Steel Instrument Connection Details | A | 2019-01-28 | IFI | OL1-2K32-1551 | ME | 2019-01-30 | 036909C-JVD-TRN-00767 | 036909C-JVD-TRN-00767 | IFI |  | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00767 |  | 2019-01-31 | 3
036909C-1011-DW-0117-1551 | USC 36M Recycle Furnace Steel Instrument Connection Details | 0 | 2019-04-25 | IMP | OL1-2K32-1551 | ME | 2019-04-26 | 036909C-JVD-TRN-01501 | 036909C-JVD-TRN-01501 | IFI |  | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-ME-01501 |  | 2019-04-29 | 3
036909C-1012-DW-0127-2204 | USC 132U Cracking Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill of Material | 1 | 2019-04-12 | IMP | OL1-2M06-2204 | ME | 2019-04-15 | 036909C-JVD-TRN-01356 | 036909C-JVD-TRN-01356 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-ME-01356 |  | 2019-04-16 | 2
036909C-1012-DW-0127-2204 | USC 132U Cracking Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill of Material | 2 | 2019-05-22 | IMP | OL1-2M06-2204 | ME | 2019-05-28 | 036909C-JVD-TRN-01754 | 036909C-JVD-TRN-01754 | IFR | 2019-06-12 | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-ME-01754 |  | 2019-05-29 | 2
036909C-1012-DW-0127-2204 | USC 132U Cracking Furnace Fabricatin Assembly of Convection Coils Finned Tubes and Bill of Material | A | 2018-10-12 | IFR | OL1-2M06-2204 | ME | 2018-10-16 | 036909C-JVD-TRN-00182 | 036909C-JVD-TRN-00182 | IFR | 2018-10-30 |  | Transmitted | TPSK-LSPA1-T-ME-00182 |  | 2018-10-17 | 2
036909C-1012-DW-0127-2204 | USC 132U Cracking Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill of Material | 0 | 2019-02-11 | IMP | OL1-2M06-2204 | ME | 2019-02-13 | 036909C-JVD-TRN-00848 | 036909C-JVD-TRN-00848 | IFR | 2019-02-27 | 2019-03-07 | R1-No comments | TPSK-LSPA1-T-ME-00848 |  | 2019-02-13 | 2
036909C-1012-DW-0117-2005 | USC 132U Cracking Furnace General Arrangement Instrumentation Sections - For Next Revision See Document OL1-2M06-2005 | A | 2019-01-28 | IFR | OL1-2M06-2005 | ME | 2019-01-30 | 036909C-JVD-TRN-00768 | 036909C-JVD-TRN-00768 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00768 | For Next Revision See Document OL1-2M06-2005 | 2019-01-31 | 2
036909C-1012-DW-0117-2005 | USC 132U Cracking Furnace General Arrangement Instrumentation Sections | 1 | 2019-06-21 | IMP | OL1-2M06-2005 | ME | 2019-06-25 | 036909C-JVD-TRN-01993 | 036909C-JVD-TRN-01993 | IFR | 2019-07-10 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-01993 |  | 2019-06-26 | 2
036909C-1012-DW-0117-2005 | USC 132U Cracking Furnace General Arrangement Instrumentation Sections - Ex Doc. Client Reference OL1-2M06-2207 | 0 | 2019-04-25 | IMP | OL1-2M06-2005 | ME | 2019-04-26 | 036909C-JVD-TRN-01500 | 036909C-JVD-TRN-01500 | IFR | 2019-05-11 |  | Transmitted |  | Ex Doc. Client Reference OL1-2M06-2207 | 2019-04-26 | 2
036909C-1011-DW-0117-1004 | USC 36M Recycle Furnace General Arrangement Instrumentation | 1 | 2019-06-21 | IMP | OL1-2M06-1004 | ME | 2019-06-25 | 036909C-JVD-TRN-01993 | 036909C-JVD-TRN-01993 | IFR | 2019-07-10 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-01993 |  | 2019-06-26 | 2
036909C-1011-DW-0117-1004 | USC 36M Recycle Furnace General Arrangement Instrumentation | 0 | 2019-04-25 | IMP | OL1-2M06-1004 | ME | 2019-04-26 | 036909C-JVD-TRN-01500 | 036909C-JVD-TRN-01500 | IFR | 2019-05-11 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-ME-01500 |  | 2019-04-29 | 2
036909C-1011-DW-0117-1001 | USC 36M Recycle Furnace General Arrangement Cross Section Elevation | 1 | 2019-06-21 | IMP | OL1-2M06-1001 | ME | 2019-06-25 | 036909C-JVD-TRN-01993 | 036909C-JVD-TRN-01993 | IFR | 2019-07-10 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-01993 |  | 2019-06-26 | 2
036909C-1012-DW-0131-2527 | USC 132U Cracking Furnace Steel Convection Section Header Box Elevations | A | 2019-04-05 | IFI | OL1-2K32-2527 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1012-DW-0131-2527 | USC 132U Cracking Furnace Steel Convection Section Header Box Elevations | 0 | 2019-05-24 | IMP | OL1-2K32-2527 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1011-DW-0131-1527 | USC 36M Recycle Furnace Steel Convection Section Header Box Elevations | A | 2019-04-05 | IFI | OL1-2K32-1527 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1011-DW-0131-1527 | USC 36M Recycle Furnace Steel Convection Section Header Box Elevations | 0 | 2019-05-24 | IMP | OL1-2K32-1527 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1012-DW-0117-2001 | USC 132U Cracking Furnace General Arrangement Cross Section Elevation | 1 | 2019-06-21 | IMP | OL1-2M06-2001 | ME | 2019-06-25 | 036909C-JVD-TRN-01993 | 036909C-JVD-TRN-01993 | IFR | 2019-07-10 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-01993 |  | 2019-06-26 | 2
036909C-1011-DW-0127-1204 | USC 36M Recycle Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill of Material | 2 | 2019-05-24 | IMP | OL1-2M06-1204 | ME | 2019-05-28 | 036909C-JVD-TRN-01754 | 036909C-JVD-TRN-01754 | IFR | 2019-06-12 | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-ME-01754 |  | 2019-05-29 | 2
036909C-1011-DW-0127-1204 | USC 36M Recycle Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill Of Material | A | 2018-10-12 | IFR | OL1-2M06-1204 | ME | 2018-10-16 | 036909C-JVD-TRN-00182 | 036909C-JVD-TRN-00182 | IFR | 2018-10-30 |  | Transmitted | TPSK-LSPA1-T-ME-00182 |  | 2018-10-17 | 2
036909C-1011-DW-0127-1204 | USC 36M Recycle Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill of Material | 0 | 2019-02-11 | IMP | OL1-2M06-1204 | ME | 2019-02-13 | 036909C-JVD-TRN-00848 | 036909C-JVD-TRN-00848 | IFR | 2019-02-27 | 2019-03-07 | R1-No comments | TPSK-LSPA1-T-ME-00848 |  | 2019-02-13 | 2
036909C-1011-DW-0127-1204 | USC 36M Recycle Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill of Material | 1 | 2019-04-12 | IMP | OL1-2M06-1204 | ME | 2019-04-15 | 036909C-JVD-TRN-01356 | 036909C-JVD-TRN-01356 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-ME-01356 |  | 2019-04-16 | 2
036909C-1011-DW-0117-1005 | USC 36M Recycle Furnace General Arrangement Instrumentation Sections | 0 | 2019-04-25 | IMP | OL1-2M06-1005 | ME | 2019-04-26 | 036909C-JVD-TRN-01500 | 036909C-JVD-TRN-01500 | IFR | 2019-05-11 |  | Transmitted | TPSK-LSPA1-T-ME-01500 |  | 2019-04-26 | 2
036909C-1011-DW-0117-1005 | USC 36M Recycle Furnace General Arrangement Instrumentation Sections | 1 | 2019-06-21 | IMP | OL1-2M06-1005 | ME | 2019-06-25 | 036909C-JVD-TRN-01993 | 036909C-JVD-TRN-01993 | IFR | 2019-07-10 | 2019-08-05 | R2-Comments as noted | TPSK-LSPA1-T-ME-01993 |  | 2019-06-26 | 2
036909C-1011-DW-0117-1005 | USC 36M Recycle Furnace General Arrangement Instrumentation Sections | A | 2019-01-28 | IFR | OL1-2M06-1005 | ME | 2019-01-30 | 036909C-JVD-TRN-00764 | 036909C-JVD-TRN-00764 | IFR | 2019-02-15 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00764 |  | 2019-01-31 | 2
036909C-1012-DW-0131-2550 | USC 132U Cracking Furnace Steel Stack Sections and Details | 0 | 2019-06-21 | IMP | OL1-2K32-2550 | CV | 2019-06-26 | 036909C-JVD-TRN-02008 | 036909C-JVD-TRN-02008 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02008 |  | 2019-06-27 | 3
036909C-1012-DW-0131-2550 | USC 132U Cracking Furnace Steel Stack Sections and Details | A | 2019-04-04 | IFI | OL1-2K32-2550 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1011-DW-0131-1550 | USC 36M Cracking Furnace Steel Stack Sections and Details | A | 2019-04-04 | IFI | OL1-2K32-1550 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1011-DW-0131-1550 | USC 36M Cracking Furnace Steel Stack Sections and Details | 0 | 2019-06-21 | IMP | OL1-2K32-1550 | CV | 2019-06-26 | 036909C-JVD-TRN-02008 | 036909C-JVD-TRN-02008 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02008 |  | 2019-06-27 | 3
036909C-1027-PDS-1390-2736 | Piping Specialty Item - Datasheet - Flexible Hose - MP Nitrogen to GHU-1 Reactor R-2700B - FLX-27003 | A | 2019-08-02 | IFR | OL1-2P03-2736 | MP | 2019-08-06 | 036909C-JVD-TRN-02365 | 036909C-JVD-TRN-02365 | IFR | 2019-08-21 | 2019-09-11 | R1-No comments | TPSK-LSPA1-T-MP-02365 |  | 2019-08-07 | 2
036909C-1027-PDS-1390-2728 | Piping Specialty Item - Datasheet - Y-Type Filter - R-2760 Hydrogen Inlet - SRY-27001 | A | 2019-08-03 | IFR | OL1-2P03-2728 | MP | 2019-08-06 | 036909C-JVD-TRN-02365 | 036909C-JVD-TRN-02365 | IFR | 2019-08-21 | 2019-09-11 | R1-No comments | TPSK-LSPA1-T-MP-02365 |  | 2019-08-07 | 2
036909C-1027-PDS-1390-2724 | Piping Specialty Item - Datasheet - Flexible Hose - MP Nitrogen to C4 C5 Hydrogenation Reactor R-2760 - FLX-27002 | A | 2019-08-02 | IFR | OL1-2P03-2724 | MP | 2019-08-06 | 036909C-JVD-TRN-02365 | 036909C-JVD-TRN-02365 | IFR | 2019-08-21 | 2019-09-11 | R1-No comments | TPSK-LSPA1-T-MP-02365 |  | 2019-08-07 | 2
036909C-1027-PDS-1390-2718 | Piping Specialty Item - Datasheet - Flexible Hose - MP Nitrogen to GHU-1 Reactor R-2700A - FLX-27001 | A | 2019-08-02 | IFR | OL1-2P03-2718 | MP | 2019-08-06 | 036909C-JVD-TRN-02365 | 036909C-JVD-TRN-02365 | IFR | 2019-08-21 | 2019-09-11 | R1-No comments | TPSK-LSPA1-T-MP-02365 |  | 2019-08-07 | 2
036909C-1026-PDS-1390-2621 | Piping Specialty Item - Datasheet - Flexible Hose - MP Nitrogen to C3 Hydrogenation Reactor R-2620 - FLX-26001 | A | 2019-08-02 | IFR | OL1-2P03-2621 | MP | 2019-08-06 | 036909C-JVD-TRN-02365 | 036909C-JVD-TRN-02365 | IFR | 2019-08-21 | 2019-09-11 | R1-No comments | TPSK-LSPA1-T-MP-02365 |  | 2019-08-07 | 2
036909C-1026-PDS-1390-2617 | Piping Specialty Item - Datasheet - Y-Type Filter - R-2620 Hydrogen Inlet - SRY-26001 | A | 2019-08-03 | IFR | OL1-2P03-2617 | MP | 2019-08-06 | 036909C-JVD-TRN-02365 | 036909C-JVD-TRN-02365 | IFR | 2019-08-21 | 2019-09-11 | R1-No comments | TPSK-LSPA1-T-MP-02365 |  | 2019-08-07 | 2
036909C-1020-PDS-1390-2008 | Piping Specialty Item - Datasheet - Steam Trap - E-2008 A-B Shell Side Outlet - STT-20001 | A | 2019-08-02 | IFR | OL1-2P03-2008 | MP | 2019-08-06 | 036909C-JVD-TRN-02365 | 036909C-JVD-TRN-02365 | IFR | 2019-08-21 | 2019-09-11 | R1-No comments | TPSK-LSPA1-T-MP-02365 |  | 2019-08-07 | 2
036909C-1021-PDS-1390-2108 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Device - Process Water Stripper T-2140 Over-Pressure Protection - ILK-21004 | A | 2019-08-04 | IFR | OL1-2P03-2108 | MP | 2019-08-06 | 036909C-JVD-TRN-02365 | 036909C-JVD-TRN-02365 | IFR | 2019-08-21 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-MP-02365 |  | 2019-08-07 | 2
036909C-1021-PDS-1390-2118 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Device - Furnace Continous Blowdown Overpressure Protection - ILK-10003 | A | 2019-08-06 | IFR | OL1-2P03-2118 | MP | 2019-08-06 | 036909C-JVD-TRN-02365 | 036909C-JVD-TRN-02365 | IFR | 2019-08-21 | 2019-09-11 | R1-No comments | TPSK-LSPA1-T-MP-02365 |  | 2019-08-07 | 2
036909C-1021-PDS-1390-2107 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - Quench Water Tower T-2100 Vacuum Protection - ILK-21003 | A | 2019-07-31 | IFR | OL1-2P03-2107 | MP | 2019-08-05 | 036909C-JVD-TRN-02347 | 036909C-JVD-TRN-02347 | IFR | 2019-08-20 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-MP-02347 |  | 2019-08-06 | 2
036909C-1021-PDS-1390-2106 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2105 A-O - ILK-21002 | A | 2019-07-31 | IFR | OL1-2P03-2106 | MP | 2019-08-05 | 036909C-JVD-TRN-02347 | 036909C-JVD-TRN-02347 | IFR | 2019-08-20 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-MP-02347 |  | 2019-08-06 | 2
036909C-1021-PDS-1390-2105 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2120 A-B - ILK-21001 | A | 2019-07-31 | IFR | OL1-2P03-2105 | MP | 2019-08-05 | 036909C-JVD-TRN-02347 | 036909C-JVD-TRN-02347 | IFR | 2019-08-20 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-MP-02347 |  | 2019-08-06 | 2
036909C-1020-PDS-1390-2005 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2030 A-B - ILK-20001 | A | 2019-07-31 | IFR | OL1-2P03-2005 | MP | 2019-08-05 | 036909C-JVD-TRN-02347 | 036909C-JVD-TRN-02347 | IFR | 2019-08-20 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-MP-02347 |  | 2019-08-06 | 2
036909C-1023-TDS-0630-2326 | Mechanical Equipment Data Sheet - 10-E-2326 - Spent Caustic Stripper Feed Heater | 0 | 2019-08-02 | Issue for Purchase | OL1-2M03-2326 | ME | 2019-08-07 | 036909C-JVD-TRN-02379 | 036909C-JVD-TRN-02379 | IFR | 2019-08-22 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-02379 |  | 2019-08-08 | 2
036909C-1028-SP-1513-2801 | Complex Loop Narratives Area 28 Refrigeration System | B | 2019-08-08 | IBD | OL1-2I71-2801 | IE | 2019-08-08 | 036909C-JVD-TRN-02396 | 036909C-JVD-TRN-02396 | IFR | 2019-08-23 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-IE-02396 |  | 2019-08-09 | 2
036909C-1027-SP-1513-2702 | Instrument Interlock Descriptions Area 27 - Ghu &C4-C5 Hydrog | B | 2019-08-05 | Issued For Basic Design | OL1-2G50-2702 | PE | 2019-08-05 | 036909C-JVD-TRN-02354 | 036909C-JVD-TRN-02354 | IFR | 2019-08-20 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02354 |  | 2019-08-06 | 2
036909C-1051-PDS-1541-5101 | Process Data Sheet For SS/HS Desuperheater DH-5101 - Ex Doc Cliet Ref OL1-2P03-5108 | A | 2019-09-09 | IFR | OL1-2G31-5151 | PE | 2019-09-10 | 036909C-JVD-TRN-02605 | 036909C-JVD-TRN-02605 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02605 | Ex Doc Cliet Ref OL1-2P03-5108 | 2019-09-11 | 2
036909C-1051-PDS-1541-5102 | Process Data Sheet For HS-MS Desuperheater DH-5102 A-B - Ex Doc Client Ref OL1-2P03-5107 | A | 2019-09-05 | IFR | OL1-2G31-5102 | PE | 2019-09-06 | 036909C-JVD-TRN-02586 | 036909C-JVD-TRN-02586 | IFR | 2019-09-23 |  | Transmitted | TPSK-LSPA1-T-PE-02586 | Ex Doc Client Ref OL1-2P03-5107 | 2019-09-10 | 2
036909C-1051-PDS-1541-5103 | Process Data Sheet For MS/LS1 Desuperheater DH-3103 A/B - Ex Doc CLient Ref OL1-2P03-5106 | A | 2019-09-09 | IFR | OL1-2G31-5103 | PE | 2019-09-10 | 036909C-JVD-TRN-02605 | 036909C-JVD-TRN-02605 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-PE-02605 | Ex Doc CLient Ref OL1-2P03-5106 | 2019-09-11 | 2
036909C-1051-PDS-1541-5104 | Process Data Sheet For LS1-LS2 Desuperheater DH-5104 A-B - Ex Doc Client Ref OL1-2P03-5105 | A | 2019-09-05 | IFR | OL1-2G31-5104 | PE | 2019-09-06 | 036909C-JVD-TRN-02586 | 036909C-JVD-TRN-02586 | IFR | 2019-09-23 |  | Transmitted | TPSK-LSPA1-T-PE-02586 | Ex Doc Client Ref OL1-2P03-5105 | 2019-09-10 | 2
036909C-102C-DW-1841-0002-014 | Steel For Pipe Rack 10-PRK-2C02 - Stairs And Ladders | A | 2019-09-06 | IFR | OL1-2K32-1233 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102E-CN-1831-0001 | Calculation Note For Steel Pipe Rack 10-PRK-2E01 | A | 2019-09-09 | IFR | OL1-2K15-0006 | CV | 2019-09-10 | 036909C-JVD-TRN-02612 | 036909C-JVD-TRN-02612 | IFA | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-CV-02612 |  | 2019-09-11 | 1
036909C-102C-DW-1841-0002-015 | Steel For Pipe Rack 10-PRK-2C02 - Details | A | 2019-09-06 | IFR | OL1-2K32-1234 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102D-DW-1741-0001-001 | Piperack 10-PRK-2D01 Foundations -Formwork And Reinforcement | A | 2019-09-05 | IFR | OL1-2K31-1200 | CV | 2019-09-06 | 036909C-JVD-TRN-02584 | 036909C-JVD-TRN-02584 | IFA | 2019-09-23 |  | Transmitted | TPSK-LSPA1-T-CV-02584 |  | 2019-09-10 | 1
036909C-102D-CN-1731-0001 | Calculation Note For Foundations Of Pipe Rack 10-PRK-2D01 | A | 2019-09-05 | IFR | OL1-2K14-0009 | CV | 2019-09-06 | 036909C-JVD-TRN-02585 | 036909C-JVD-TRN-02585 | IFA | 2019-09-23 |  | Transmitted | TPSK-LSPA1-T-CV-02585 |  | 2019-09-10 | 1
036909C-102C-DW-1841-0002-013 | Steel For Pipe Rack 10-PRK-2C02 - Elevation | A | 2019-09-06 | IFR | OL1-2K32-1232 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102C-DW-1841-0002-012 | Steel For Pipe Rack 10-PRK-2C02 - Elevation | A | 2019-09-06 | IFR | OL1-2K32-1231 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102D-DW-1741-0001-002 | Piperack 10-PRK-2D01 Foundations -Formwork And Reinforcement | A | 2019-09-05 | IFR | OL1-2K31-1201 | CV | 2019-09-06 | 036909C-JVD-TRN-02584 | 036909C-JVD-TRN-02584 | IFA | 2019-09-23 |  | Transmitted | TPSK-LSPA1-T-CV-02584 |  | 2019-09-10 | 1
036909C-102C-DW-1841-0002-007 | Steel For Pipe Rack 10-PRK-2C02 - Plans & Sections | A | 2019-09-06 | IFR | OL1-2K32-1226 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102C-DW-1841-0002-005 | Steel For Pipe Rack 10-PRK-2C02 - Plans | A | 2019-09-06 | IFR | OL1-2K32-1224 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102C-DW-1841-0002-006 | Steel For Pipe Rack 10-PRK-2C02 - Plans | A | 2019-09-06 | IFR | OL1-2K32-1225 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102C-DW-1841-0002-010 | Steel For Pipe Rack 10-PRK-2C02 - Elevation | A | 2019-09-06 | IFR | OL1-2K32-1229 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102C-DW-1841-0002-004 | Steel For Pipe Rack 10-PRK-2C02 - Plans | A | 2019-09-06 | IFR | OL1-2K32-1223 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102C-DW-1841-0002-011 | Steel For Pipe Rack 10-PRK-2C02 - Elevation | A | 2019-09-06 | IFR | OL1-2K32-1230 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102C-DW-1841-0002-009 | Steel For Pipe Rack 10-PRK-2C02 - Plans | A | 2019-09-06 | IFR | OL1-2K32-1228 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102C-DW-1841-0002-008 | Steel For Pipe Rack 10-PRK-2C02 - Plans | A | 2019-09-06 | IFR | OL1-2K32-1227 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102C-CN-1831-0002 | Calculation Notes For Steel Pipe Rack 10-PRK-2C02 | A | 2019-09-06 | IFR | OL1-2K15-0057 | CV | 2019-09-09 | 036909C-JVD-TRN-02596 | 036909C-JVD-TRN-02596 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02596 |  | 2019-09-10 | 1
036909C-102C-DW-1841-0002-001 | Steel For Pipe Rack 10-PRK-2C02 - 3D View | A | 2019-09-06 | IFR | OL1-2K32-1220 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102C-DW-1841-0002-002 | Steel For Pipe Rack 10-PRK-2C02 - Plans | A | 2019-09-06 | IFR | OL1-2K32-1221 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102A-DW-1842-0002-001 | Steel Structure For 10-STR-2A02 | A | 2019-09-06 | IFR | OL1-2K32-1740 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102B-CN-1735-0003 | Calculation For Foundation And Elevation Of Retaining Wall For 10-TK-2320 | A | 2019-09-05 | IFR | OL1-2K13-0368 | CV | 2019-09-06 | 036909C-JVD-TRN-02585 | 036909C-JVD-TRN-02585 | IFA | 2019-09-23 |  | Transmitted | TPSK-LSPA1-T-CV-02585 |  | 2019-09-10 | 1
036909C-102B-DW-1745-0003-001 | Foundation And Elevation Of Retaining Wall For 10-TK-2320 | A | 2019-09-05 | IFR | OL1-2K31-0331 | CV | 2019-09-06 | 036909C-JVD-TRN-02584 | 036909C-JVD-TRN-02584 | IFA | 2019-09-23 |  | Transmitted | TPSK-LSPA1-T-CV-02584 |  | 2019-09-10 | 1
036909C-102C-DW-1841-0002-003 | Steel For Pipe Rack 10-PRK-2C02 - Plans | A | 2019-09-06 | IFR | OL1-2K32-1222 | CV | 2019-09-09 | 036909C-JVD-TRN-02595 | 036909C-JVD-TRN-02595 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02595 |  | 2019-09-10 | 1
036909C-102B-CN-1735-0004 | Calculation For Foundation And Elevation Of Retaining Wall For 10-TK-2910 | A | 2019-09-06 | IFR | OL1-2K13-0369 | CV | 2019-09-09 | 036909C-JVD-TRN-02589 | 036909C-JVD-TRN-02589 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02589 |  | 2019-09-10 | 1
036909C-102B-DW-1745-0004-001 | Foundation And Elevation Of Retaining Wall For 10-TK-2910 | A | 2019-09-06 | IFR | OL1-2K31-0332 | CV | 2019-09-09 | 036909C-JVD-TRN-02590 | 036909C-JVD-TRN-02590 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02590 |  | 2019-09-10 | 1
036909C-102A-CN-1832-0002 | Calculation Note For Steel Structure Of 10-STR-2A02 | A | 2019-09-05 | IFR | OL1-2K15-0035 | CV | 2019-09-09 | 036909C-JVD-TRN-02596 | 036909C-JVD-TRN-02596 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02596 |  | 2019-09-10 | 1
036909C-102A-CN-1732-0002 | Calculation Note For Foundation And Elevation Of 10-STR-2A02 | A | 2019-09-06 | IFR | OL1-2K14-0045 | CV | 2019-09-09 | 036909C-JVD-TRN-02596 | 036909C-JVD-TRN-02596 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02596 |  | 2019-09-10 | 1
036909C-1012-DW-0132-2104 | USC 132U Cracking Furnace Refractory and Insulation Anchor Details | 1 | 2019-08-26 | IMP | OL1-2M06-2104 | ME | 2019-09-10 | 036909C-JVD-TRN-02607 | 036909C-JVD-TRN-02607 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-ME-02607 |  | 2019-09-11 | 2
036909C-102A-DW-1742-0002-001 | Foundation For Structure 10-STR-2A02 & 10-T-2140 | A | 2019-09-06 | IFR | OL1-2K31-2000 | CV | 2019-09-09 | 036909C-JVD-TRN-02597 | 036909C-JVD-TRN-02597 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02597 |  | 2019-09-10 | 1
036909C-102A-DW-1743-0011-001 | Foundation For 10-D-2136 | A | 2019-09-05 | IFR | OL1-2K31-0018 | CV | 2019-09-06 | 036909C-JVD-TRN-02582 | 036909C-JVD-TRN-02582 | IFA | 2019-09-23 |  | Transmitted | TPSK-LSPA1-T-CV-02582 |  | 2019-09-10 | 1
036909C-1011-DW-0132-1104 | USC 36M Recycle Furnace Refractory and Insulation Anchor Details | 1 | 2019-08-26 | IMP | OL1-2M06-1104 | ME | 2019-09-10 | 036909C-JVD-TRN-02607 | 036909C-JVD-TRN-02607 | IFR | 2019-09-25 |  | Transmitted | TPSK-LSPA1-T-ME-02607 |  | 2019-09-11 | 2
036909C-1011-DW-0125-1303 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Location | 1 | 2019-08-26 | IMP | OL1-2M06-1303 | ME | 2019-09-10 | 036909C-JVD-TRN-02608 | 036909C-JVD-TRN-02608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-02608 |  | 2019-09-11 | 3
036909C-1012-DW-0117-2303 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Location | 1 | 2019-08-26 | IMP | OL1-2M06-2303 | ME | 2019-09-10 | 036909C-JVD-TRN-02608 | 036909C-JVD-TRN-02608 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-02608 |  | 2019-09-11 | 3
036909C-1000-MTO-1619-0002 | Earthing System Material Take-Off (OSBL Units) | A | 2019-09-04 | IF1T | OL1-2E63-0004 | EE | 2019-09-06 | 036909C-JVD-TRN-02581 | 036909C-JVD-TRN-02581 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-EE-02581 |  | 2019-09-11 | 2
036909C-1000-JSS-6300-02 | Job Specification For Welding And NDE Of Pressure Vessel And Heat Exchanger | 0 | 2019-02-21 | IMP | OL1-2R03-0001 | ME | 2019-02-25 | 036909C-JVD-TRN-00921 | 036909C-JVD-TRN-00921 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00921 |  | 2019-02-26 | 2
036909C-1000-JSD-2200-01 | Job Design Specification For Thermal Insulation (Hot Service) | C | 2019-08-06 | IFR | OL1-2R04-0003 | MP | 2019-08-08 | 036909C-JVD-TRN-02391 | 036909C-JVD-TRN-02391 | IFR | 2019-08-23 | 2019-08-28 | R1-No comments | TPSK-LSPA1-T-MP-02391 |  | 2019-08-09 | 2
036909C-1000-STC-0490-000 | Construction Standards For Pressure Equipment | 1 | 2019-02-15 | IMP | OL1-2R03-0054 | ME | 2019-02-19 | 036909C-JVD-TRN-00876 | 036909C-JVD-TRN-00876, ROC-TPSK-CECO-T-00004 | IFR | 2019-03-05 | 2019-03-11 | R1-No comments | TPSK-LSPA1-T-ME-00876 |  | 2019-02-19 | 2
036909C-1000-JSD-0500-1001 | Job Specification for Air Liquide-Design Rules- Codes and Standards for Columns and Column Internals | A | 2019-04-24 | IFR | OL1-2R03-1006 | ME | 2019-04-26 | 036909C-JVD-TRN-01504 | 036909C-JVD-TRN-01504 | IFR | 2019-05-13 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-ME-01504 |  | 2019-04-29 | 2
036909C-1000-JSS-0400-02 | Marking For Vessel & Heat Exchanger | 0 | 2018-09-10 | IMP | OL1-2R03-0102 | ME | 2018-09-12 | 036909C-JVD-TRN-00042 | 036909C-JVD-TRN-00042 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00042 |  | 2018-09-13 | 3
036909C-1000-JSS-0400-01 | Job Specification For Supply Of Pressure Vessels | 1 | 2019-04-11 | IMP | OL1-2R03-0051 | ME | 2019-04-15 | 036909C-JVD-TRN-01350 | 036909C-JVD-TRN-01350 | IFR | 2019-04-30 | 2019-05-13 | R1-No comments | TPSK-LSPA1-T-ME-01350 |  | 2019-04-16 | 2
036909C-100S-DW-1625-0001 | Substation E Equipment Layout | B | 2019-08-23 | IFR | OL1-2E20-0001 | EE | 2019-08-26 | 036909C-JVD-TRN-02488 | 036909C-JVD-TRN-02488 | IFA | 2019-09-10 | 2019-09-09 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-02488 |  | 2019-08-27 | 1
036909C-1000-MR-1310-0026 | Material Requisition For Spring-Assisted Check Valves | A | 2019-08-26 | IFQ | OL1-2C14-160001 | PL | 2019-08-30 | 036909C-JVD-TRN-02553 | 036909C-JVD-TRN-02553 | IFR | 2019-09-16 | 2019-09-05 | R2-Comments as noted | TPSK-LSPA1-T-PL-02553 |  | 2019-09-03 | 2
036909C-1000-MR-1395-0001 | Material Requisition for Filters | A | 2019-08-26 | IFQ | OL1-2C14-320001 | PL | 2019-08-30 | 036909C-JVD-TRN-02552 | 036909C-JVD-TRN-02552 | IFR | 2019-09-16 | 2019-09-05 | R2-Comments as noted | TPSK-LSPA1-T-PL-02552 |  | 2019-09-03 | 2
036909C-1029-PDS-2600-2920 | Process Equipment Datasheet - 10-PK-2920 - Polymerization Inhibitor Inj Pkg | F | 2019-07-25 | IFD | OL1-2G30-2920 | PE | 2019-07-30 | 036909C-JVD-TRN-02284 | 036909C-JVD-TRN-02284 | IFR | 2019-08-14 | 2019-09-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-02284 |  | 2019-07-31 | 2
036909C-1029-PDS-2600-2900 | Process Equipment Datasheet - 10-PK-2900 - pH Ctrl - Corrosion Inhibitor Inj Pkg | D | 2019-07-25 | IFD | OL1-2G30-2900 | PE | 2019-07-30 | 036909C-JVD-TRN-02284 | 036909C-JVD-TRN-02284 | IFR | 2019-08-14 | 2019-09-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-02284 |  | 2019-07-31 | 2
036909C-1012-DW-0117-2303 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Location | 0 | 2019-06-24 | IMP | OL1-2M06-2303 | ME | 2019-06-25 | 036909C-JVD-TRN-01995 | 036909C-JVD-TRN-01995 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-01995 |  | 2019-06-26 | 3
036909C-1012-DW-0117-2303 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Location | A | 2019-04-05 | IFI | OL1-2M06-2303 | ME | 2019-04-09 | 036909C-JVD-TRN-01291 | 036909C-JVD-TRN-01291 | IFI |  | 2019-05-15 | R1-No comments | TPSK-LSPA1-T-ME-01291 |  | 2019-04-10 | 3
036909C-1011-DW-0125-1303 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Location | A | 2019-04-05 | IFI | OL1-2M06-1303 | ME | 2019-04-09 | 036909C-JVD-TRN-01290 | 036909C-JVD-TRN-01290 | IFI |  | 2019-05-15 | R1-No comments | TPSK-LSPA1-T-ME-01290 |  | 2019-04-10 | 3
036909C-1011-DW-0125-1303 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Location | 0 | 2019-06-24 | IMP | OL1-2M06-1303 | ME | 2019-06-25 | 036909C-JVD-TRN-01995 | 036909C-JVD-TRN-01995 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-01995 |  | 2019-06-26 | 3
036909C-1012-DW-0132-2104 | USC 132U Cracking Furnace Refractory and Insulation Anchor Details | 0 | 2019-05-09 | IMP | OL1-2M06-2104 | ME | 2019-05-13 | 036909C-JVD-TRN-01653 | 036909C-JVD-TRN-01653 | IFR | 2019-05-28 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-ME-01653 |  | 2019-05-14 | 2
036909C-1012-DW-0132-2104 | USC 132U Cracking Furnace Refractory and Insulation Anchor Details | A | 2019-02-22 | IFR | OL1-2M06-2104 | ME | 2019-03-14 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15 | 2
036909C-1011-DW-0132-1104 | USC 36M Recycle Furnace Refractory and Insulation Anchor Details | 0 | 2019-05-09 | IMP | OL1-2M06-1104 | ME | 2019-05-13 | 036909C-JVD-TRN-01653 | 036909C-JVD-TRN-01653 | IFR | 2019-05-28 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-ME-01653 |  | 2019-05-14 | 2
036909C-1011-DW-0132-1104 | USC 36M Recycle Furnace Refractory and Insulation Anchor Details | A | 2019-02-22 | IFR | OL1-2M06-1104 | ME | 2019-03-14 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15 | 2
036909C-105F-DW-1622-0201 | Power Layout - Zone 5F HP & Polyolefins Flares | A | 2019-08-20 | IFR | OL1-2E32-0007 | EE | 2019-08-27 | 036909C-JVD-TRN-02496 | 036909C-JVD-TRN-02496 | IFR | 2019-09-10 | 2019-09-10 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02496 |  | 2019-08-28 | 1
036909C-105F-DW-1624-0001 | Cable Routing Cross Section - Zone 5F | A | 2019-08-28 | Issued For Review | OL1-2E34-0007 | EE | 2019-08-29 | 036909C-JVD-TRN-02530 | 036909C-JVD-TRN-02530 | IFR | 2019-09-12 | 2019-09-10 | R2-Comments as noted | TPSK-LSPA1-T-EE-02530 |  | 2019-08-29 | 2
036909C-100M-DW-1624-0001 | Cable Routing Cross Section - Zone 0M | A | 2019-08-26 | IFR | OL1-2E34-0006 | EE | 2019-08-29 | 036909C-JVD-TRN-02530 | 036909C-JVD-TRN-02530 | IFR | 2019-09-12 | 2019-09-10 | R2-Comments as noted | TPSK-LSPA1-T-EE-02530 |  | 2019-08-29 | 2
036909C-1000-MR-0570-0003 | MATERIAL REQUISITION FOR TRAYS COLUMNS (C4 UNIT) | 0 | 2019-08-30 | IFP | OL1-2C13-244000 | PL | 2019-08-30 | 036909C-JVD-TRN-02544 | 036909C-JVD-TRN-02544 | IFR | 2019-09-13 | 2019-09-10 | R2-Comments as noted | TPSK-LSPA1-T-PL-02544 |  | 2019-09-03 | 2
036909C-1000-PO-036909C001P59-059 | Vendor s Acknowledgment of Purchase Order For Shop Assembled CS Drums– MR 0811-0002 Rev 1 | 1 | 2019-08-23 | IFI | OL1-2C51-0122 | PL | 2019-08-27 | 036909C-JVD-TRN-02498 | 036909C-JVD-TRN-02498 | IFI | 2019-09-10 | 2019-09-10 | R1-No comments | TPSK-LSPA1-T-PL-02498 |  | 2019-08-28 | 3
036909C-105T-DW-1741-0001-002 | Foundation Details For Piperack 10-Prk-5T01 (Formwork & Reinforcement) | A | 2019-09-05 | IFR | OL1-2K31-0372 | CV | 2019-09-10 | 036909C-JVD-TRN-02601 | 036909C-JVD-TRN-02601 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02601 |  | 2019-09-10 | 2
036909C-105T-DW-1741-0001-003 | Foundation Details For Piperack 10-Prk-5T01 (Formwork & Reinforcement) | A | 2019-09-05 | IFR | OL1-2K31-0373 | CV | 2019-09-10 | 036909C-JVD-TRN-02601 | 036909C-JVD-TRN-02601 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02601 |  | 2019-09-10 | 2
036909C-105T-DW-1741-0001-004 | Foundation For Pipe Rack 10-Prk-5T01 - Tie Beams Details | A | 2019-09-05 | IFR | OL1-2K31-0374 | CV | 2019-09-10 | 036909C-JVD-TRN-02601 | 036909C-JVD-TRN-02601 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02601 |  | 2019-09-10 | 2
036909C-105T-DW-1741-0001-001 | Foundation For Piperack 10-Prk-5T01 - Plan (Formwork) | A | 2019-09-05 | IFR | OL1-2K31-1500 | CV | 2019-09-10 | 036909C-JVD-TRN-02601 | 036909C-JVD-TRN-02601 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-CV-02601 |  | 2019-09-10 | 2
036909C-1011-SP-1553-1155 | Instrument Datasheets for Draft Gauge | A | 2019-09-09 | IFQ | OL1-2I20-1155 | IE | 2019-09-09 | 036909C-JVD-TRN-02598 | 036909C-JVD-TRN-02598 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-IE-02598 |  | 2019-09-10 | 2
036909C-1000-MS-1800-0001 | Technical Specification For Steel Structures Erection | 0 | 2019-09-03 | IFP | OL1-2R02-0104 | CV | 2019-09-06 | 036909C-JVD-TRN-02587 | 036909C-JVD-TRN-02587 | IFR | 2019-09-23 |  | Transmitted | TPSK-LSPA1-T-CV-02587 |  | 2019-09-10 | 1
036909C-1000-CN-1621-0001 | Electrical Cable Sizing Criteria | B | 2019-09-05 | IFR | OL1-2E10-0001 | EE | 2019-09-09 | 036909C-JVD-TRN-02593 | 036909C-JVD-TRN-02593 | IFA | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-EE-02593 |  | 2019-09-10 | 1
036909C-1000-MS-1731-0001 | Technical Specification for Precast Concrete Pipe-Racks | 0 | 2019-08-29 | IFP | OL1-2R02-0103 | CV | 2019-09-06 | 036909C-JVD-TRN-02587 | 036909C-JVD-TRN-02587 | IFR | 2019-09-23 |  | Transmitted | TPSK-LSPA1-T-CV-02587 |  | 2019-09-10 | 2
036909C-1051-PDS-1390-5130 | Piping Specialty Item - Datasheet - Vent Silencer - PSV-5150 A-B-C-D Outlet - 10-SP-51030 | A | 2019-06-18 | IFR | OL1-2P03-5130 | MP | 2019-06-19 | 036909C-JVD-TRN-01941 | 036909C-JVD-TRN-01941 | IFR | 2019-07-04 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01941 |  | 2019-06-20 | 2
036909C-1051-PDS-1390-5126 | Piping Specialty Item - Datasheet - Vent Silencer - PSV-5134 A-H- Outlet - 10-SP-51026 | A | 2019-06-18 | IFR | OL1-2P03-5126 | MP | 2019-06-19 | 036909C-JVD-TRN-01941 | 036909C-JVD-TRN-01941 | IFR | 2019-07-04 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01941 |  | 2019-06-20 | 2
036909C-1051-PDS-1390-5125 | Piping Specialty Item - Datasheet - Vent Silencer - PV-5161 Outlet - 10-SP-51025 | A | 2019-06-03 | IFR | OL1-2P03-5125 | MP | 2019-06-05 | 036909C-JVD-TRN-01809 | 036909C-JVD-TRN-01809 | IFR | 2019-06-20 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-MP-01809 |  | 2019-06-10 | 2
036909C-1051-PDS-1390-5124 | Piping Specialty Item - Datasheet - Vent Silencer - PV-5158 Outlet - 10-SP-51024 | A | 2019-06-03 | IFR | OL1-2P03-5124 | MP | 2019-06-05 | 036909C-JVD-TRN-01809 | 036909C-JVD-TRN-01809 | IFR | 2019-06-20 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-MP-01809 |  | 2019-06-10 | 2
036909C-1051-PDS-1390-5123 | Piping Specialty Item - Datasheet - Vent Silencer - PV-5155 Outlet - 10-SP-51023 | A | 2019-06-03 | IFR | OL1-2P03-5123 | MP | 2019-06-05 | 036909C-JVD-TRN-01809 | 036909C-JVD-TRN-01809 | IFR | 2019-06-20 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-MP-01809 |  | 2019-06-10 | 2
036909C-1051-PDS-1390-5122 | Piping Specialty Item - Datasheet - Vent Silencer - PV-5147 Outlet - 10-SP-51022 | A | 2019-06-03 | IFR | OL1-2P03-5122 | MP | 2019-06-05 | 036909C-JVD-TRN-01809 | 036909C-JVD-TRN-01809 | IFR | 2019-06-20 | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-MP-01809 |  | 2019-06-10 | 2
036909C-1051-PDS-1390-5121 | Piping Specialty Item - Datasheet - Vent Silencer -PV-5143 Outlet - 10-SP-51021 | A | 2019-06-03 | IFR | OL1-2P03-5121 | MP | 2019-06-05 | 036909C-JVD-TRN-01809 | 036909C-JVD-TRN-01809 | IFR | 2019-06-20 | 2019-06-27 | R1-No comments | TPSK-LSPA1-T-MP-01809 |  | 2019-06-10 | 2
036909C-1000-MS-1800-0001 | Technical Specification For Steel Structures Erection | A | 2019-03-29 | IFQ | OL1-2R02-0104 | CV | 2019-04-12 | 036909C-JVD-TRN-INTERNAL-00152 | 036909C-JVD-TRN-01666 | IFI |  | 2019-06-08 | R2-Comments as noted | TPSK-LSPA1-T-CV-01666 |  | 2019-05-16 | 2
036909C-1000-MS-1731-0001 | Technical Specification for Precast Concrete Pipe-Racks | B | 2019-04-11 | IFQ | OL1-2R02-0103 | CV | 2019-04-16 | 036909C-JVD-TRN-INTERNAL-00160 | 036909C-JVD-TRN-01666 | IFI |  | 2019-06-08 | R2-Comments as noted | TPSK-LSPA1-T-CV-01666 |  | 2019-05-16 | 2
036909C-1031-PID-0031-3106 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Blow Down Drum | B | 2019-05-20 | IBD | OL1-2G43-3106 | PE | 2019-05-22 | 036909C-JVD-TRN-01722 | 036909C-JVD-TRN-01722 | IFR | 2019-06-06 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01722 |  | 2019-05-23 | 2
036909C-1021-PDS-1390-2104 | Piping Specialty Item - Datasheet - T-Type Filter - P-2146 A-B Suction - SRT-21002 | A | 2019-07-20 | IFR | OL1-2P03-2104 | MP | 2019-07-24 | 036909C-JVD-TRN-02259 | 036909C-JVD-TRN-02259 | IFR | 2019-08-08 | 2019-09-09 | R1-No comments | TPSK-LSPA1-T-MP-02259 |  | 2019-07-25 | 2
036909C-1021-PDS-1390-2103 | Piping Specialty Item - Datasheet - T-Type Filter - P-2106 A-B-C - SRT-21003 | A | 2019-07-20 | IFR | OL1-2P03-2103 | MP | 2019-07-24 | 036909C-JVD-TRN-02259 | 036909C-JVD-TRN-02259 | IFR | 2019-08-08 | 2019-09-09 | R1-No comments | TPSK-LSPA1-T-MP-02259 |  | 2019-07-25 | 2
036909C-1021-PDS-1390-2102 | Piping Specialty Item - Datasheet - T-Type Filter - P-2105 A-B Suction - SRT-21005 | A | 2019-07-20 | IFR | OL1-2P03-2102 | MP | 2019-07-24 | 036909C-JVD-TRN-02259 | 036909C-JVD-TRN-02259 | IFR | 2019-08-08 | 2019-09-09 | R1-No comments | TPSK-LSPA1-T-MP-02259 |  | 2019-07-25 | 2
036909C-1021-PDS-1390-2101 | Piping Specialty Item - Datasheet - T-Type Filter - P-2126 A-B Suction - SRT-21001 | A | 2019-07-20 | IFR | OL1-2P03-2101 | MP | 2019-07-24 | 036909C-JVD-TRN-02259 | 036909C-JVD-TRN-02259 | IFR | 2019-08-08 | 2019-09-09 | R1-No comments | TPSK-LSPA1-T-MP-02259 |  | 2019-07-25 | 2
036909C-1020-PDS-1390-2003 | Piping Specialty Item - Datasheet - T-Type Filter - P-2026 A-B Suction - SRT-20001 | A | 2019-07-20 | IFR | OL1-2P03-2003 | MP | 2019-07-24 | 036909C-JVD-TRN-02259 | 036909C-JVD-TRN-02259 | IFR | 2019-08-08 | 2019-09-09 | R1-No comments | TPSK-LSPA1-T-MP-02259 |  | 2019-07-25 | 2
036909C-1012-DW-0131-2659 | USC 36M Recycle and 132U Cracking Furnace Steel Moment Connection Details and Miscellaneous Details | 2 | 2019-08-30 | IMP | OL1-2K32-2659 | CV | 2019-09-05 | 036909C-JVD-TRN-02577 | 036909C-JVD-TRN-02577 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02577 |  | 2019-09-10 | 3
036909C-1012-DW-0131-2660 | USC 36M Recycle and 132U Cracking Furnaces Steel Standard Sections and Details | 1 | 2019-08-30 | IMP | OL1-2K32-2660 | CV | 2019-09-05 | 036909C-JVD-TRN-02577 | 036909C-JVD-TRN-02577 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02577 |  | 2019-09-10 | 3
036909C-1012-DW-0131-2500 | USC 36M Recycle And 132U Cracking Furnaces Steel General Notes and Abbreviations | 1 | 2019-08-30 | IMP | OL1-2K32-2500 | CV | 2019-09-05 | 036909C-JVD-TRN-02577 | 036909C-JVD-TRN-02577 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02577 |  | 2019-09-10 | 3
036909C-1000-SP-1561-0001 | Instrument Data Sheets for Gas Chromatographs | A | 2019-07-26 | IFQ | OL1-2I20-2100 | IE | 2019-07-29 | 036909C-JVD-TRN-02277 | 036909C-JVD-TRN-02277 | IFA | 2019-08-13 | 2019-08-20 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02277 |  | 2019-07-30 | 1
036909C-1000-NM-0003-1006 | Cooling Water Balance | 0 | 2019-09-04 | IFI | OL1-2G62-1006 | PE | 2019-09-05 | 036909C-JVD-TRN-02579 | 036909C-JVD-TRN-02579 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02579 |  | 2019-09-10 | 3
036909C-1000-NM-1990-0201 | Recovery Process And Utilities Section HAZOP FEED Recommendations Mitigation Report - Fisrt Batch | A | 2019-09-03 | IFA | OL1-2L62-0003 | SE | 2019-09-05 | 036909C-JVD-TRN-02575 | 036909C-JVD-TRN-02575 | IFA | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-SE-02575 |  | 2019-09-10 | 1
036909C-1000-PP-262 | Tekla Structure Management For LSP Complex Project | 0 | 2019-09-05 | IMP | OL1-2R02-0007 | CV | 2019-09-05 | 036909C-JVD-TRN-02576 | 036909C-JVD-TRN-02576 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-CV-02576 |  | 2019-09-10 | 2
036909C-1000-PP-264 | U-G And A-G Civil Model Management | 0 | 2019-09-05 | IMP | OL1-2R02-0009 | CV | 2019-09-05 | 036909C-JVD-TRN-02576 | 036909C-JVD-TRN-02576 | IFR | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-CV-02576 |  | 2019-09-10 | 2
036909C-105F-NM-1654-0001 | Substation F - Low Voltage - Switchboard Composition | A | 2019-07-31 | IFQ | OL1-2E15-0008 | EE | 2019-08-01 | 036909C-JVD-TRN-02315 | 036909C-JVD-TRN-02315 | IFA | 2019-08-16 | 2019-09-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02315 |  | 2019-08-05 | 1
036909C-103S-NM-1654-0001 | Substation C - Low Voltage - Switchboard Composition | A | 2019-07-31 | IFQ | OL1-2E15-0007 | EE | 2019-08-01 | 036909C-JVD-TRN-02315 | 036909C-JVD-TRN-02315 | IFA | 2019-08-16 | 2019-09-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02315 |  | 2019-08-05 | 1
036909C-100S-NM-1654-0001 | Substation E - Low Voltage - Switchboard Composition | A | 2019-07-31 | IFQ | OL1-2E15-0006 | EE | 2019-08-01 | 036909C-JVD-TRN-02315 | 036909C-JVD-TRN-02315 | IFA | 2019-08-16 | 2019-09-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02315 |  | 2019-08-05 | 1
036909C-1000-PP-264 | U/G And A/G Civil Model Management | A | 2018-11-21 | IFR | OL1-2R02-0009 | CV | 2018-11-26 | 036909C-JVD-TRN-00355 | 036909C-JVD-TRN-00355 | IFR | 2018-12-11 | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00355 |  | 2018-11-26 | 2
036909C-1000-PP-262 | Tekla Structure Management For LSP Complex Project | A | 2018-11-21 | IFR | OL1-2R02-0007 | CV | 2018-11-26 | 036909C-JVD-TRN-00355 | 036909C-JVD-TRN-00355 | IFR | 2018-12-11 | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00355 |  | 2018-11-26 | 2
036909C-1012-DW-0131-2660 | USC 36M Recycle and 132U Cracking Furnaces Steel Standard Sections and Details | 0 | 2019-04-30 | IMP | OL1-2K32-2660 | CV | 2019-05-06 | 036909C-JVD-TRN-01585 | 036909C-JVD-TRN-01585 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01585 |  | 2019-05-07 | 3
036909C-1012-DW-0131-2659 | USC 36M Recycle & 132U Cracking Furnace Steel Moment Connection Details & Miscellaneous Details | 1 | 2019-07-17 | IMP | OL1-2K32-2659 | CV | 2019-07-22 | 036909C-JVD-TRN-02221 | 036909C-JVD-TRN-02221 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02221 |  | 2019-07-23 | 3
036909C-1012-DW-0131-2659 | USC 36M Recycle & 132U Cracking Furnace Steel Moment Connection Details & Miscellaneous Details | 0 | 2019-05-15 | IMP | OL1-2K32-2659 | CV | 2019-05-20 | 036909C-JVD-TRN-01695 | 036909C-JVD-TRN-01695 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01695 |  | 2019-05-21 | 3
036909C-1012-DW-0131-2500 | USC 36M Recycle And 132U Cracking Furnaces Steel General Notes and Abbreviations | 0 | 2019-05-15 | IMP | OL1-2K32-2500 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-25 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1000-PO-036909C001P41-041 | Vendor s Acknowledgment of Purchase Order For Wet Air Oxidation - MR 4100-0001 Rev. 0 | 1 | 2019-08-20 | IFI | OL1-2C51-0121 | PL | 2019-08-21 | 036909C-JVD-TRN-02462 | 036909C-JVD-TRN-02462 | IFI | 2019-09-12 | 2019-09-04 | R1-No comments |  |  | 2019-08-22 | 3
036909C-1000-PO-036909C001P50-050 | Vendor Acknowledgment of Purchase Order for Shop Assembled Large Drums | 1 | 2019-08-20 | IFI | OL1-2C51-0120 | PL | 2019-08-21 | 036909C-JVD-TRN-02462 | 036909C-JVD-TRN-02462 | IFI | 2019-09-12 | 2019-09-04 | R1-No comments |  |  | 2019-08-22 | 3
036909C-103S-PFD-3410-0001 | Electrical Sub-C- And Far-C - HVAC Process Flow Diagram | C | 2019-08-22 | IDD | OL1-2H20-0003 | EE | 2019-08-26 | 036909C-JVD-TRN-02485 | 036909C-JVD-TRN-02485 | IFA | 2019-09-10 | 2019-09-03 | A4 - Not Approved, re-submit for approval | TPSK-LSPA1-T-EE-02485 |  | 2019-08-27 | 1
036909C-103S-DW-3432-0001 | Electrical SUB-C & FAR-C HVAC Layout | C | 2019-08-22 | IDD | OL1-2H21-0005 | EE | 2019-08-26 | 036909C-JVD-TRN-02486 | 036909C-JVD-TRN-02486 | IFA | 2019-09-10 | 2019-09-03 | A4 - Not Approved, re-submit for approval | TPSK-LSPA1-T-EE-02486 |  | 2019-08-27 | 1
036909C-105F-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 5F HP & Polyolefins Flares Unit | B | 2019-09-03 | IBD | OL1-2F75-0006 | FF | 2019-09-05 | 036909C-JVD-TRN-02573 | 036909C-JVD-TRN-02573 | IBD | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-FF-02573 |  | 2019-09-05 | 2
036909C-1011-SP-1553-1154 | Instrument Datasheets for Pressure Gauge | A | 2019-08-27 | IFQ | OL1-2I20-1154 | IE | 2019-09-04 | 036909C-JVD-TRN-02571 | 036909C-JVD-TRN-02571 | IFR | 2019-09-19 |  | Transmitted | TPSK-LSPA1-TE-IE-02571 |  | 2019-09-05 | 2
036909C-100M-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 0M Metering Station | B | 2019-09-03 | IBD | OL1-2F75-0007 | FF | 2019-09-05 | 036909C-JVD-TRN-02573 | 036909C-JVD-TRN-02573 | IBD | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-FF-02573 |  | 2019-09-05 | 2
036909C-1000-NM-6006-0001 | List For Acoustical Insulation On Lines And Associated Components | A | 2019-09-02 | IFR | OL1-2L10-0004 | SE | 2019-09-04 | 036909C-JVD-TRN-02569 | 036909C-JVD-TRN-02569 | IFR | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-SE-02569 |  | 2019-09-05 | 2
036909C-105F-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 5F HP & Polyoleffins Flares Unit | A | 2019-03-29 | IFR | OL1-2F75-0006 | FF | 2019-03-29 | 036909C-JVD-TRN-01191 | 036909C-JVD-TRN-01191, KLOC-TPSK-VSAFE-T-00002 | IFR | 2019-04-11 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01191 |  | 2019-03-29 | 2
036909C-100M-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 0M Metering Station | A | 2019-03-29 | IFR | OL1-2F75-0007 | FF | 2019-03-29 | 036909C-JVD-TRN-01191 | 036909C-JVD-TRN-01191, KLOC-TPSK-VSAFE-T-00002 | IFR | 2019-04-11 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01191 |  | 2019-03-29 | 2
036909C-105T-DW-1622-0201 | Power Layout - Zone 5T Cooling Water Unit | A | 2019-08-16 | IFR | OL1-2E32-0001 | EE | 2019-08-19 | 036909C-JVD-TRN-02448 | 036909C-JVD-TRN-02448 | IFR | 2019-09-18 | 2019-09-04 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02448 |  | 2019-08-21 | 1
036909C-100S-DW-1622-0201 | Power Layout - Zone 0S Electrical Substation E & Far E | A | 2019-08-14 | IFR | OL1-2E32-0003 | EE | 2019-08-16 | 036909C-JVD-TRN-02445 | 036909C-JVD-TRN-02445 | IFR | 2019-08-30 | 2019-09-04 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02445 |  | 2019-08-19 | 1
036909C-103S-DW-1622-0201 | Power Layout - Zone 3S Substation C & Far C | A | 2019-08-13 | IFR | OL1-2E32-0004 | EE | 2019-08-15 | 036909C-JVD-TRN-02440 | 036909C-JVD-TRN-02440 | IFR | 2019-08-29 | 2019-09-04 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02440 |  | 2019-08-16 | 1
036909C-1024-DW-1514-2401 | Cause And Effect Diagram Area 24 - Dehydration - Regen - Deprop - C2 Hydrog | B | 2019-07-25 | IBD | OL1-2G50-2401 | PE | 2019-07-30 | 036909C-JVD-TRN-02288 | 036909C-JVD-TRN-02288 | IFR | 2019-08-14 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-02288 |  | 2019-07-31 | 2
036909C-1000-PO-036909C004P9103905-05 | Vendor Acknowledgment of Purchase Order for HRS Valve Trays | 0 | 2019-06-03 | IFI | OL1-2C51-0219 | PL | 2019-08-21 | 036909C-JVD-TRN-02469 | 036909C-JVD-TRN-02469 | IFI |  | 2019-09-04 | R1-No comments | TPSK-LSPA1-T-PL-02469 |  | 2019-08-21 | 3
036909C-1000-PO-036909C004P9103904-04 | Vendor Acknowledgment of Purchase Order for HRS Gas Rectifier and Reflux Drum | 0 | 2019-06-04 | IFI | OL1-2C51-0218 | PL | 2019-08-21 | 036909C-JVD-TRN-02469 | 036909C-JVD-TRN-02469 | IFI |  | 2019-09-04 | R1-No comments | TPSK-LSPA1-T-PL-02469 |  | 2019-08-21 | 3
036909C-1000-PO-036909C004P9103910-10 | Vendor Acknowledgment of Purchase Order for Support Beams Distributors and Hardware | 0 | 2019-06-06 | IFI | OL1-2C51-0217 | PL | 2019-08-21 | 036909C-JVD-TRN-02469 | 036909C-JVD-TRN-02469 | IFI |  | 2019-09-04 | R1-No comments | TPSK-LSPA1-T-PL-02469 |  | 2019-08-22 | 3
036909C-1000-PO-036909C004P9103911-11 | Vendor Acknowledgment of Purchase Order for Mesh Pads and Hardware | 0 | 2019-06-06 | IFI | OL1-2C51-0215 | PL | 2019-08-21 | 036909C-JVD-TRN-02469 | 036909C-JVD-TRN-02469 | IFI |  | 2019-09-04 | R1-No comments | TPSK-LSPA1-T-PL-02469 |  | 2019-08-22 | 3
036909C-1000-PO-036909C004P9103908-08 | Vendor Acknowledgment of Purchase Order for Ripple Trays - Bubble Cap Trays and Hardware | 0 | 2019-06-06 | IFI | OL1-2C51-0214 | PL | 2019-08-21 | 036909C-JVD-TRN-02469 | 036909C-JVD-TRN-02469 | IFI |  | 2019-09-04 | R1-No comments | TPSK-LSPA1-T-PL-02469 |  | 2019-08-22 | 3
036909C-1012-PO-036909C004P9103883-83 | Vendor Acknowledgment of Purchase Order for Radiant Steel Panel | 0 | 2019-05-24 | IFI | OL1-2C51-0213 | PL | 2019-08-21 | 036909C-JVD-TRN-02469 | 036909C-JVD-TRN-02469 | IFI |  | 2019-09-04 | R1-No comments | TPSK-LSPA1-T-PL-02469 |  | 2019-08-22 | 3
036909C-1012-PO-036909C004P9103864-64 | Vendor Acknowledgment of Purchase Order for Radiant Refractory | 0 | 2019-05-24 | IFI | OL1-2C51-0212 | PL | 2019-08-21 | 036909C-JVD-TRN-02469 | 036909C-JVD-TRN-02469 | IFI |  | 2019-09-04 | R1-No comments | TPSK-LSPA1-T-PL-02469 |  | 2019-08-22 | 3
036909C-1012-PO-036909C004P9103827-27 | Vendor Acknowledgment of Purchase Order for Crack Gas and Decoke MOV | 0 | 2019-04-26 | IFI | OL1-2C51-0211 | PL | 2019-08-21 | 036909C-JVD-TRN-02469 | 036909C-JVD-TRN-02469 | IFI |  | 2019-09-04 | R1-No comments | TPSK-LSPA1-T-PL-02469 |  | 2019-08-22 | 3
036909C-1012-PO-036909C004P9103505-05 | Vendor Acknowledgment of Purchase Order for Furnace Steam Drums | 0 | 2018-12-26 | IFI | OL1-2C51-0209 | PL | 2019-08-21 | 036909C-JVD-TRN-02469 | 036909C-JVD-TRN-02469 | IFI |  | 2019-09-04 | R1-No comments | TPSK-LSPA1-T-PL-02469 |  | 2019-08-21 | 3
036909C-1027-PDS-1390-2727 | Piping Specialty Item - Datasheet - T-Type Filter - P-2760 A-B Suction - 10-SRT-27009 | A | 2019-07-20 | IFR | OL1-2P03-2727 | MP | 2019-07-30 | 036909C-JVD-TRN-02297 | 036909C-JVD-TRN-02297 | IFR | 2019-08-14 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-MP-02297 |  | 2019-07-31 | 2
036909C-1027-PDS-1390-2725 | Piping Specialty Item - Datasheet - T-Type Filter - P-2714 A-B Suction - SRT-27008 | A | 2019-07-20 | IFR | OL1-2P03-2725 | MP | 2019-07-30 | 036909C-JVD-TRN-02297 | 036909C-JVD-TRN-02297 | IFR | 2019-08-14 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-MP-02297 |  | 2019-07-31 | 2
036909C-1027-PDS-1390-2716 | Piping Specialty Item - Datasheet - T-Type Filter - P-2721 A-B Suction - SRT-27001 | A | 2019-07-20 | IFR | OL1-2P03-2716 | MP | 2019-07-30 | 036909C-JVD-TRN-02297 | 036909C-JVD-TRN-02297 | IFR | 2019-08-14 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-MP-02297 |  | 2019-07-31 | 2
036909C-1027-PDS-1390-2708 | Piping Specialty Item - Datasheet - T-Type Filter - P-2750 A-B Suction - SRT-27006 | A | 2019-07-20 | IFR | OL1-2P03-2708 | MP | 2019-07-30 | 036909C-JVD-TRN-02297 | 036909C-JVD-TRN-02297 | IFR | 2019-08-14 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-MP-02297 |  | 2019-07-31 | 2
036909C-1027-PDS-1390-2707 | Piping Specialty Item - Datasheet - T-Type Filter - P-2726 A-B Suction - SRT-27005 | A | 2019-07-20 | IFR | OL1-2P03-2707 | MP | 2019-07-30 | 036909C-JVD-TRN-02297 | 036909C-JVD-TRN-02297 | IFR | 2019-08-14 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-MP-02297 |  | 2019-07-31 | 2
036909C-1027-PDS-1390-2706 | Piping Specialty Item - Datasheet - T-Type Filter - P-2724 A-B Suction - SRT-27004 | A | 2019-07-20 | IFR | OL1-2P03-2706 | MP | 2019-07-30 | 036909C-JVD-TRN-02297 | 036909C-JVD-TRN-02297 | IFR | 2019-08-14 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-MP-02297 |  | 2019-07-31 | 2
036909C-1027-PDS-1390-2705 | Piping Specialty Item - Datasheet - T-Type Filter - P-2720 A-B Suction - SRT-27003 | A | 2019-07-20 | IFR | OL1-2P03-2705 | MP | 2019-07-30 | 036909C-JVD-TRN-02297 | 036909C-JVD-TRN-02297 | IFR | 2019-08-14 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-MP-02297 |  | 2019-07-31 | 2
036909C-1027-PDS-1390-2703 | Piping Specialty Item - Datasheet - T-Type Filter -P-2710 A-B Suction - SRT-27002 | A | 2019-07-20 | IFR | OL1-2P03-2703 | MP | 2019-07-30 | 036909C-JVD-TRN-02297 | 036909C-JVD-TRN-02297 | IFR | 2019-08-14 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-MP-02297 |  | 2019-07-31 | 2
036909C-1027-PDS-1390-2702 | Piping Specialty Item - Datasheet - T-Type Filter - P-2705 A-B Suction - SRT-27001 | A | 2019-07-20 | IFR | OL1-2P03-2702 | MP | 2019-07-30 | 036909C-JVD-TRN-02297 | 036909C-JVD-TRN-02297 | IFR | 2019-08-14 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-MP-02297 |  | 2019-07-31 | 2
036909C-1024-PDS-1390-2421 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - D-2480 - ILK-24011 | A | 2019-07-22 | IFR | OL1-2P03-2421 | MP | 2019-07-30 | 036909C-JVD-TRN-02297 | 036909C-JVD-TRN-02297 | IFR | 2019-08-14 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-MP-02297 |  | 2019-07-31 | 2
036909C-1021-PDS-1390-2123 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-2106 A-B-C Discharge - SCV-21002 | A | 2019-07-23 | IFR | OL1-2P03-2123 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-09-04 | R1-No comments | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1020-PDS-1390-2007 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-2006 A-B-C Discharge - SCV-20001 | A | 2019-07-23 | IFR | OL1-2P03-2007 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1011-PO-036909C004P9104000-00 | Vendor Acknowledgment of Purchase Order for Pressure Relief Valves | 0 | 2019-08-02 | IFI | OL1-2C55-0220 | PL | 2019-08-21 | 036909C-JVD-TRN-02469 | 036909C-JVD-TRN-02469 | IFI |  | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-PL-02469 |  | 2019-08-22 | 3
036909C-1012-MR-1552-2005 | Material Requisition for Level Gauges | 0 | 2019-08-07 | IFP | OL1-2C17-022005 | PL | 2019-08-13 | 036909C-JVD-TRN-02430 | 036909C-JVD-TRN-02430 | IFR | 2019-08-28 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-PL-02430 |  | 2019-08-15 | 2
036909C-1052-DW-1514-5201 | Cause And Effect Diagram Area 52 - Fuel System | B | 2019-08-02 | IBD | OL1-2G50-5201 | PE | 2019-08-05 | 036909C-JVD-TRN-02343 | 036909C-JVD-TRN-02343 | IFR | 2019-08-20 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-02343 |  | 2019-08-06 | 2
036909C-1051-DW-1514-5101 | Cause And Effect Diagram Area 51 - BFW - Steam - Steam Condensate System | B | 2019-08-02 | IBD | OL1-2G50-5101 | PE | 2019-08-05 | 036909C-JVD-TRN-02343 | 036909C-JVD-TRN-02343 | IFR | 2019-08-20 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-02343 |  | 2019-08-06 | 2
036909C-1027-DW-1514-2701 | Cause And Effect Diagram Area 27 - Ghu & C4-C5 Hydrog | B | 2019-08-05 | Issued For Basic Design | OL1-2G50-2701 | PE | 2019-08-05 | 036909C-JVD-TRN-02353 | 036909C-JVD-TRN-02353 | IFR | 2019-08-20 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-02353 |  | 2019-08-06 | 2
036909C-1025-PDS-1390-2550 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2520 A-B - ILK-25001 | A | 2019-07-31 | IFR | OL1-2P03-2550 | MP | 2019-08-05 | 036909C-JVD-TRN-02347 | 036909C-JVD-TRN-02347 | IFR | 2019-08-20 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-MP-02347 |  | 2019-08-06 | 2
036909C-1025-PDS-1390-2549 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2510 A-B - ILK-25011 | A | 2019-07-31 | IFR | OL1-2P03-2549 | MP | 2019-08-05 | 036909C-JVD-TRN-02347 | 036909C-JVD-TRN-02347 | IFR | 2019-08-20 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-MP-02347 |  | 2019-08-06 | 2
036909C-1025-PDS-1390-2546 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2530 A-B - ILK-25010 | A | 2019-07-31 | IFR | OL1-2P03-2546 | MP | 2019-08-05 | 036909C-JVD-TRN-02347 | 036909C-JVD-TRN-02347 | IFR | 2019-08-20 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-MP-02347 |  | 2019-08-06 | 2
036909C-1027-TDS-0630-2727 | Mechanical Equipment Data Sheet - 10-E-2726 - Pygas Fuel Oil Cooler | 0 | 2019-08-02 | Issue for Purchase | OL1-2M03-2727 | ME | 2019-08-07 | 036909C-JVD-TRN-02379 | 036909C-JVD-TRN-02379 | IFR | 2019-08-22 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-02379 |  | 2019-08-08 | 2
036909C-1027-TDS-0630-2723 | Mechanical Equipment Data Sheet - 10-E-2724 - Wash Oil Condenser | 0 | 2019-08-02 | Issue for Purchase | OL1-2M03-2723 | ME | 2019-08-07 | 036909C-JVD-TRN-02379 | 036909C-JVD-TRN-02379 | IFR | 2019-08-22 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-02379 |  | 2019-08-08 | 2
036909C-1027-TDS-0630-2716 | Mechanical Equipment Data Sheet - 10-E-2714 - C5 Cut Cooler | 0 | 2019-08-02 | Issue for Purchase | OL1-2M03-2716 | ME | 2019-08-07 | 036909C-JVD-TRN-02379 | 036909C-JVD-TRN-02379 | IFR | 2019-08-22 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-02379 |  | 2019-08-08 | 2
036909C-1021-SP-1545-2101 | Instrument Datasheets for Pressure Safety Valve - Area 21 | A | 2019-07-24 | IFQ | OL1-2I20-2116 | IE | 2019-07-30 | 036909C-JVD-TRN-02291 | 036909C-JVD-TRN-02291 | IFI |  | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-IE-02291 |  | 2019-07-31 | 3
036909C-1022-SP-1545-2201 | Instrument Datasheets for Pressure Safety Valve - Area 22 | A | 2019-07-23 | IFQ | OL1-2I20-2216 | IE | 2019-07-30 | 036909C-JVD-TRN-02291 | 036909C-JVD-TRN-02291 | IFI |  | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-IE-02291 |  | 2019-07-31 | 3
036909C-1114-NM-1551-1101 | Alarm & Setpoint Summary 36M Furnace 10-H-1100 | B | 2019-08-30 | IFD | OL1-2O67-1101 | IE | 2019-08-30 | 036909C-JVD-TRN-02556 | 036909C-JVD-TRN-02556 | IFR | 2019-09-14 |  | Transmitted | TPSK-LSPA1-T-IE-02556 |  | 2019-09-03 | 2
036909C-1214-NM-1551-1201 | Alarm & Setpoint Summary 132U Furnaces 10-H-1200 - 10-H-1600 | B | 2019-08-30 | IFD | OL1-2O67-1201 | IE | 2019-08-30 | 036909C-JVD-TRN-02556 | 036909C-JVD-TRN-02556 | IFR | 2019-09-14 |  | Transmitted | TPSK-LSPA1-T-IE-02556 |  | 2019-09-03 | 2
036909C-1031-SP-1545-3103 | Instrument Datasheets for Rupture Disc - Area 31 | A | 2019-08-30 | IFQ | OL1-2I20-3119 | IE | 2019-09-03 | 036909C-JVD-TRN-02565 | 036909C-JVD-TRN-02565 | IFQ |  |  | Transmitted | TPSK-LSPA1-T-IE-02565 |  | 2019-09-04 | 3
036909C-1030-SP-1545-3003 | Instrument Datasheets for Rupture Disc - Area 30 | A | 2019-08-30 | IFQ | OL1-2I20-3019 | IE | 2019-09-03 | 036909C-JVD-TRN-02565 | 036909C-JVD-TRN-02565 | IFQ |  |  | Transmitted | TPSK-LSPA1-T-IE-02565 |  | 2019-09-04 | 3
036909C-102E-DW-1844-0001-001 | Steel Railing For Protection Of Basin 10-PIT-2390 | A | 2019-08-19 | IFR | OL1-2K32-7740 | CV | 2019-09-02 | 036909C-JVD-TRN-02558 | 036909C-JVD-TRN-02558 | IFA | 2019-09-17 |  | Transmitted | TPSK-LSPA1-T-CV-02558 |  | 2019-09-03 | 1
036909C-102C-CN-1834-0001 | Calculation For Steel Platform For 10-PIT-2790 | A | 2019-08-29 | IFR | OL1-2K15-0096 | CV | 2019-09-02 | 036909C-JVD-TRN-02557 | 036909C-JVD-TRN-02557 | IFA | 2019-09-17 |  | Transmitted | TPSK-LSPA1-T-CV-02557 |  | 2019-09-03 | 1
036909C-102E-CN-1834-0001 | Calculation For Steel Platform For 10-PIT-2390 | A | 2019-08-29 | IFR | OL1-2K15-0097 | CV | 2019-09-02 | 036909C-JVD-TRN-02557 | 036909C-JVD-TRN-02557 | IFA | 2019-09-17 |  | Transmitted | TPSK-LSPA1-T-CV-02557 |  | 2019-09-03 | 1
036909C-102C-DW-1844-0001-001 | Steel Railng For Protection Of Basin 10-PIT-2790 | A | 2019-08-19 | IFR | OL1-2K32-7580 | CV | 2019-09-02 | 036909C-JVD-TRN-02558 | 036909C-JVD-TRN-02558 | IFA | 2019-09-17 |  | Transmitted | TPSK-LSPA1-T-CV-02558 |  | 2019-09-03 | 1
036909C-1027-PDS-1390-2720 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - ILK-27005 & ILK-27009 | A | 2019-08-31 | IFR | OL1-2P03-2720 | MP | 2019-09-03 | 036909C-JVD-TRN-02566 | 036909C-JVD-TRN-02566 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-MP-02566 |  | 2019-09-04 | 2
036909C-1026-SP-1545-2603 | Instrument Datasheets for Rupture Disc - Area 26 | A | 2019-08-30 | IFQ | OL1-2I20-2619 | IE | 2019-09-03 | 036909C-JVD-TRN-02565 | 036909C-JVD-TRN-02565 | IFQ |  |  | Transmitted | TPSK-LSPA1-T-IE-02565 |  | 2019-09-04 | 3
036909C-1026-PDS-1390-2614 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - ILK-26008 & ILK-26009 | A | 2019-08-31 | IFR | OL1-2P03-2614 | MP | 2019-09-03 | 036909C-JVD-TRN-02566 | 036909C-JVD-TRN-02566 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-MP-02566 |  | 2019-09-04 | 2
036909C-1026-PDS-1390-2613 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - ILK-26001 & ILK-26007 | A | 2019-08-31 | IFR | OL1-2P03-2613 | MP | 2019-09-03 | 036909C-JVD-TRN-02566 | 036909C-JVD-TRN-02566 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-MP-02566 |  | 2019-09-04 | 2
036909C-100P-DW-1842-0001-003 | Steel Structure For 10-STR-0P01 | A | 2019-08-28 | IFR | OL1-2K32-1702 | CV | 2019-08-30 | 036909C-JVD-TRN-02551 | 036909C-JVD-TRN-02551 | IFA | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-CV-02551 |  | 2019-09-03 | 1
036909C-100P-CN-1832-0001 | Calculation Note For Steel Structure Of 10-STR-0P01 | A | 2019-08-28 | IFR | OL1-2K15-0033 | CV | 2019-08-30 | 036909C-JVD-TRN-02550 | 036909C-JVD-TRN-02550 | IFA | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-CV-02550 |  | 2019-09-03 | 1
036909C-100P-DW-1842-0001-002 | Steel Structure For 10-STR-0P01 | A | 2019-08-28 | IFR | OL1-2K32-1701 | CV | 2019-08-30 | 036909C-JVD-TRN-02551 | 036909C-JVD-TRN-02551 | IFA | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-CV-02551 |  | 2019-09-03 | 1
036909C-100P-DW-1842-0001-001 | Steel Structure For 10-STR-0P01 | A | 2019-08-28 | IFR | OL1-2K32-1700 | CV | 2019-08-30 | 036909C-JVD-TRN-02551 | 036909C-JVD-TRN-02551 | IFA | 2019-09-16 |  | Transmitted | TPSK-LSPA1-T-CV-02551 |  | 2019-09-03 | 1
036909C-1000-MS-6893-0002 | Job Specification For Equipment Inspection | A | 2019-08-29 | IFR | OL1-2O71-0022 | PE | 2019-09-03 | 036909C-JVD-TRN-02562 | 036909C-JVD-TRN-02562 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02562 |  | 2019-09-04 | 2
036909C-1000-MS-2093-0002 | Job Specification For Electrical Substation Energization | A | 2019-08-29 | IFR | OL1-2O71-0020 | PE | 2019-09-03 | 036909C-JVD-TRN-02563 | 036909C-JVD-TRN-02563 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02563 |  | 2019-09-04 | 2
036909C-1000-MS-6893-0001 | Job Specification For Machinery Alignment | A | 2019-08-29 | IFR | OL1-2O71-0021 | PE | 2019-09-03 | 036909C-JVD-TRN-02562 | 036909C-JVD-TRN-02562 | IFR | 2019-09-18 |  | Transmitted | TPSK-LSPA1-T-PE-02562 |  | 2019-09-04 | 2
036909C-1000-DW-1572-0018 | Instrument Main Cable Routing Underground | A | 2019-08-09 | IFR | OL1-2I34-0018 | IE | 2019-08-09 | 036909C-JVD-TRN-02407 | 036909C-JVD-TRN-02407 | IFA | 2019-08-26 | 2019-08-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02407 |  | 2019-08-14 | 1
036909C-105T-DW-1572-0013 | Instrument Main Cable Routing Cooling Water Unit | A | 2019-08-08 | IFR | OL1-2I34-0013 | IE | 2019-08-09 | 036909C-JVD-TRN-02407 | 036909C-JVD-TRN-02407 | IFA | 2019-08-26 | 2019-08-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02407 |  | 2019-08-14 | 1
036909C-100M-DW-1572-0002 | Instrument Main Cable Routing Metering | A | 2019-08-08 | IFR | OL1-2I34-0002 | IE | 2019-08-09 | 036909C-JVD-TRN-02407 | 036909C-JVD-TRN-02407 | IFA | 2019-08-26 | 2019-08-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02407 |  | 2019-08-14 | 1
036909C-102C-DW-1933-0001 | Fire Protection & Firefighting Layout - Zone 2C Hot Fractionation/GHU Unit | D | 2019-07-03 | IBD | OL1-2F30-0015 | FF | 2019-07-08 | 036909C-JVD-TRN-02091 | 036909C-JVD-TRN-02091 | IFR | 2019-07-22 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-FF-02091 |  | 2019-07-08 | 2
036909C-103A-DW-1933-0001 | Fire Protection & Firefighting Layout - Zone 3A Butadiene Extraction Unit | D | 2019-07-03 | IBD | OL1-2F30-0014 | FF | 2019-07-08 | 036909C-JVD-TRN-02091 | 036909C-JVD-TRN-02091 | IFR | 2019-07-22 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-FF-02091 |  | 2019-07-08 | 2
036909C-1053-PDS-0281-5302 | Datasheet CTU Sump Sluice Gates Z-5302/Z-5303/Z-5304 | A | 2019-07-29 | IFR | OL1-2G30-6101 | PE | 2019-08-08 | 036909C-JVD-TRN-02387 | 036909C-JVD-TRN-02387 | IFR | 2019-08-23 | 2019-08-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-02387 |  | 2019-08-09 | 2
036909C-102E-DW-1933-0001 | Fire Protection & Firefighting Layout - Zone 2E Cracked Gas Compressor | D | 2019-07-03 | IBD | OL1-2F30-0013 | FF | 2019-07-08 | 036909C-JVD-TRN-02091 | 036909C-JVD-TRN-02091 | IFR | 2019-07-22 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-FF-02091 |  | 2019-07-08 | 2
036909C-1053-PDS-0281-5301 | Datasheet Cooling Water Basin Sluice Gates 10-Z-5301 A-I | A | 2019-07-29 | IFR | OL1-2G30-6100 | PE | 2019-08-08 | 036909C-JVD-TRN-02387 | 036909C-JVD-TRN-02387 | IFR | 2019-08-23 | 2019-08-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-02387 |  | 2019-08-09 | 2
036909C-102D-DW-1933-0001 | Fire Protection & Firefighting Layout - Zone 2D Process Cold Compressor | D | 2019-07-03 | IBD | OL1-2F30-0012 | FF | 2019-07-08 | 036909C-JVD-TRN-02091 | 036909C-JVD-TRN-02091 | IFR | 2019-07-22 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-FF-02091 |  | 2019-07-08 | 2
036909C-102B-DW-1933-0001 | Fire Protection & Firefighting Layout - Zone 2B C3 Hydrogenation | D | 2019-07-03 | IBD | OL1-2F30-0011 | FF | 2019-07-08 | 036909C-JVD-TRN-02091 | 036909C-JVD-TRN-02091 | IFR | 2019-07-22 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-FF-02091 |  | 2019-07-08 | 2
036909C-102A-DW-1933-0001 | Fire Protection & Firefighting Layout - Zone 2A Quench | D | 2019-07-03 | IBD | OL1-2F30-0010 | FF | 2019-07-08 | 036909C-JVD-TRN-02091 | 036909C-JVD-TRN-02091 | IFR | 2019-07-22 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-FF-02091 |  | 2019-07-08 | 2
036909C-101B-DW-1933-0001 | Fire Protection & Firefighting Layout - Zone 1B Furnaces Utilities | D | 2019-07-03 | IBD | OL1-2F30-0009 | FF | 2019-07-08 | 036909C-JVD-TRN-02091 | 036909C-JVD-TRN-02091 | IFR | 2019-07-22 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-FF-02091 |  | 2019-07-08 | 2
036909C-105U-DW-1933-0001 | Fire Protection & Firefighting Layout - Zone 5U Utilities | D | 2019-07-03 | IBD | OL1-2F30-0005 | FF | 2019-07-08 | 036909C-JVD-TRN-02091 | 036909C-JVD-TRN-02091 | IFR | 2019-07-22 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-FF-02091 |  | 2019-07-08 | 2
036909C-105W-DW-1933-0001 | Fire Protection & Firefighting Layout - Zone 5W Waste Water Treatment | D | 2019-07-03 | IBD | OL1-2F30-0004 | FF | 2019-07-08 | 036909C-JVD-TRN-02091 | 036909C-JVD-TRN-02091 | IFR | 2019-07-22 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-FF-02091 |  | 2019-07-08 | 2
036909C-105T-DW-1933-0001 | Fire Protection & Firefighting Layout - Zone 5T Cooling Water Unit | D | 2019-07-03 | IBD | OL1-2F30-0003 | FF | 2019-07-08 | 036909C-JVD-TRN-02091 | 036909C-JVD-TRN-02091 | IFR | 2019-07-22 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-FF-02091 |  | 2019-07-08 | 2
036909C-102D-DW-1743-0021-002 | Concrete Structure For 10-D-2880 And 10-D-2865 - Reinforcement | A | 2019-06-25 | IFR | OL1-2K31-0107 | CV | 2019-07-03 | 036909C-JVD-TRN-02071 | 036909C-JVD-TRN-02071 | IFA | 2019-07-18 | 2019-08-29 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02071 |  | 2019-07-04 | 1
036909C-1000-JSS-1800-0001 | Job Supply Specification for Steel Structures | 0 | 2019-06-25 | IFP | OL1-2R02-0006 | CV | 2019-07-03 | 036909C-JVD-TRN-02070 | 036909C-JVD-TRN-02070 | IFR | 2019-07-18 | 2019-08-29 | R1-No comments | TPSK-LSPA1-T-CV-02070 |  | 2019-07-04 | 2
036909C-103S-DW-1622-0101 | Electrical Main Cable Routing Layout - Zone 3S Substation & Far C | A | 2019-08-06 | IFR | OL1-2E31-0005 | EE | 2019-08-06 | 036909C-JVD-TRN-02356 | 036909C-JVD-TRN-02356 | IFR | 2019-08-20 | 2019-09-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02356 |  | 2019-08-07 | 1
036909C-100S-DW-1622-0101 | Electrical Main Cable Routing Layout - Zone 0S Substation E & Far E | A | 2019-08-07 | IFR | OL1-2E31-0004 | EE | 2019-08-08 | 036909C-JVD-TRN-02381 | 036909C-JVD-TRN-02381 | IFR | 2019-08-22 | 2019-09-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02381 |  | 2019-08-08 | 1
036909C-103A-CN-1733-0013 | Calculation Note For Foundation Of 10-T-3070 | A | 2019-07-01 | IFR | OL1-2K13-0212 | CV | 2019-07-03 | 036909C-JVD-TRN-02064 | 036909C-JVD-TRN-02064 | IFR | 2019-07-17 | 2019-09-03 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02064 |  | 2019-07-03 | 1
036909C-1114-NM-1551-1101 | Alarm & Setpoint Summary 36M Furnace 10-H-1100 | A | 2019-05-07 | IFR | OL1-2O67-1101 | IE | 2019-06-10 | 036909C-JVD-TRN-01848 | 036909C-JVD-TRN-01848 | IFR | 2019-06-25 | 2019-07-23 | R2-Comments as noted | TPSK-LSPA1-T-IE-01848 |  | 2019-06-11 | 2
036909C-1214-NM-1551-1201 | Alarm & Setpoint Summary 132U Furnaces 10-H-1200 - 10-H-1600 | A | 2019-05-07 | IFR | OL1-2O67-1201 | IE | 2019-06-10 | 036909C-JVD-TRN-01848 | 036909C-JVD-TRN-01848 | IFR | 2019-06-25 | 2019-07-23 | R2-Comments as noted | TPSK-LSPA1-T-IE-01848 |  | 2019-06-11 | 2
036909C-103A-DW-1743-0042 | Foundation For 10-D-3126 | A | 2019-06-27 | IFR | OL1-2K31-0266 | CV | 2019-07-02 | 036909C-JVD-TRN-02047 | 036909C-JVD-TRN-02047 | IFR | 2019-07-16 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-CV-02047 |  | 2019-07-02 | 2
036909C-103A-DW-1743-0020 | Foundation For 10-D-3110 | A | 2019-06-27 | IFR | OL1-2K31-0227 | CV | 2019-07-02 | 036909C-JVD-TRN-02047 | 036909C-JVD-TRN-02047 | IFR | 2019-07-16 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-CV-02047 |  | 2019-07-02 | 2
036909C-103A-DW-1743-0019 | Foundation For 10-D-3180 | A | 2019-06-27 | IFR | OL1-2K31-0226 | CV | 2019-07-02 | 036909C-JVD-TRN-02047 | 036909C-JVD-TRN-02047 | IFR | 2019-07-16 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-CV-02047 |  | 2019-07-02 | 2
036909C-103A-DW-1743-0013 | Foundation For 10-T-3070 | A | 2019-06-27 | IFR | OL1-2K31-0220 | CV | 2019-07-02 | 036909C-JVD-TRN-02047 | 036909C-JVD-TRN-02047 | IFR | 2019-07-16 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-CV-02047 |  | 2019-07-02 | 2
036909C-105T-DW-1622-0101 | Electrical Main Cable Routing Layout - Zone 5T Cooling Water Unit | A | 2019-08-05 | IFR | OL1-2E31-0002 | EE | 2019-08-06 | 036909C-JVD-TRN-02356 | 036909C-JVD-TRN-02356 | IFR | 2019-08-20 | 2019-09-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02356 |  | 2019-08-07 | 1
036909C-1011-PDS-1390-1101 | Piping Specialty Item Datasheet - Trapped Key Locking Devices - ILK-11001 | B | 2019-07-25 | IFD | OL1-2P03-1101 | MP | 2019-07-30 | 036909C-JVD-TRN-02294 | 036909C-JVD-TRN-02294 | IFR | 2019-08-14 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02294 |  | 2019-07-31 | 2
036909C-1056-PDS-1390-5611 | Piping Specialty Item - Datasheet - Steam Trap - TK-5676 Coil Outlet - STT-56003 | A | 2019-07-29 | IFR | OL1-2P03-5611 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1056-PDS-1390-5610 | Piping Specialty Item - Datasheet - Steam Trap - TK-5675B Coil Outlet - STT-56002 | A | 2019-07-29 | IFR | OL1-2P03-5610 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1056-PDS-1390-5609 | Piping Specialty Item - Datasheet - Steam Trap - TK-5675A Coil Outlet - STT-56001 | A | 2019-07-29 | IFR | OL1-2P03-5609 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1055-PDS-1390-5566 | Piping Specialty Item - Datasheet - Steam Trap - E-5552 Shell Side Outlet - STT-55002 | A | 2019-07-29 | IFR | OL1-2P03-5566 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1055-PDS-1390-5523 | Piping Specialty Item - Datasheet - Steam Trap - D-5565 Coil Outlet - STT-55004 | A | 2019-07-29 | IFR | OL1-2P03-5523 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1055-PDS-1390-5514 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5532 A-B - ILK-55001 | A | 2019-07-22 | IFR | OL1-2P03-5514 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1055-PDS-1390-5512 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5531 A-B - ILK-55002 | A | 2019-07-22 | IFR | OL1-2P03-5512 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1055-PDS-1390-5510 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5510 A-B - ILK-55003 | A | 2019-07-29 | IFR | OL1-2P03-5510 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1055-PDS-1390-5508 | Piping Specialty Item - Datasheet - Steam Trap - E-5513 Tube Side Outlet - STT-55001 | A | 2019-07-29 | IFR | OL1-2P03-5508 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1054-PDS-1390-5446 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5404 A-B - ILK-54001 | A | 2019-07-22 | IFR | OL1-2P03-5446 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1052-PDS-1390-5206 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5209 A-B - ILK-52002 | A | 2019-07-22 | IFR | OL1-2P03-5206 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1052-PDS-1390-5203 | Piping Specialty Item - Datasheet - Steam Trap - E-5200 Shell Side Outlet - STT-52001 | A | 2019-07-29 | IFR | OL1-2P03-5203 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5145 | Piping Specialty Item - Datasheet - Injection Quill - Phosphate Injection to SHP BFW - IJQ-51002 | A | 2019-07-27 | IFR | OL1-2P03-5145 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5144 | Piping Specialty Item - Datasheet - Injection Quill - Amine Injection to BFW Pump Suction - IJQ-51001 | A | 2019-07-27 | IFR | OL1-2P03-5144 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5128 | Piping Specialty Item - Datasheet – Double-Keyed Interlocked Locking Device - PSV-5143 A-H - ILK-51001 | A | 2019-07-22 | IFR | OL1-2P03-5128 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1029-PDS-1390-2918 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2976 A-B-C - ILK-29002 | A | 2019-08-01 | IFR | OL1-2P03-2918 | MP | 2019-08-05 | 036909C-JVD-TRN-02352 | 036909C-JVD-TRN-02352 | IFR | 2019-08-20 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02352 |  | 2019-08-06 | 2
036909C-1029-PDS-1390-2910 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2951 A-G - ILK-29003 | A | 2019-08-01 | IFR | OL1-2P03-2910 | MP | 2019-08-05 | 036909C-JVD-TRN-02352 | 036909C-JVD-TRN-02352 | IFR | 2019-08-20 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02352 |  | 2019-08-06 | 2
036909C-1029-PDS-1390-2902 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2925 - A-B - ILK-29001 | A | 2019-08-01 | IFR | OL1-2P03-2902 | MP | 2019-08-05 | 036909C-JVD-TRN-02352 | 036909C-JVD-TRN-02352 | IFR | 2019-08-20 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02352 |  | 2019-08-06 | 2
036909C-1028-PDS-1390-2868 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2854 A-B - ILK-28015 | A | 2019-08-01 | IFR | OL1-2P03-2868 | MP | 2019-08-05 | 036909C-JVD-TRN-02352 | 036909C-JVD-TRN-02352 | IFR | 2019-08-20 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02352 |  | 2019-08-06 | 2
036909C-1028-PDS-1390-2867 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2861 A-B - ILK-28010 | A | 2019-08-01 | IFR | OL1-2P03-2867 | MP | 2019-08-05 | 036909C-JVD-TRN-02352 | 036909C-JVD-TRN-02352 | IFR | 2019-08-20 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02352 |  | 2019-08-06 | 2
036909C-1028-PDS-1390-2866 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2858 A-B - ILK-28011 | A | 2019-08-01 | IFR | OL1-2P03-2866 | MP | 2019-08-05 | 036909C-JVD-TRN-02352 | 036909C-JVD-TRN-02352 | IFR | 2019-08-20 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02352 |  | 2019-08-06 | 2
036909C-1028-PDS-1390-2865 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2864 A-B - ILK-28009 | A | 2019-08-01 | IFR | OL1-2P03-2865 | MP | 2019-08-05 | 036909C-JVD-TRN-02352 | 036909C-JVD-TRN-02352 | IFR | 2019-08-20 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02352 |  | 2019-08-06 | 2
036909C-1028-PDS-1390-2864 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2841 A-D - ILK-28008 | A | 2019-08-01 | IFR | OL1-2P03-2864 | MP | 2019-08-05 | 036909C-JVD-TRN-02352 | 036909C-JVD-TRN-02352 | IFR | 2019-08-20 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02352 |  | 2019-08-06 | 2
036909C-1028-PDS-1390-2863 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2842 A-B - ILK-28007 | A | 2019-08-01 | IFR | OL1-2P03-2863 | MP | 2019-08-05 | 036909C-JVD-TRN-02352 | 036909C-JVD-TRN-02352 | IFR | 2019-08-20 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02352 |  | 2019-08-06 | 2
036909C-1028-PDS-1390-2862 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2867 A-B - ILK-28014 | A | 2019-08-01 | IFR | OL1-2P03-2862 | MP | 2019-08-05 | 036909C-JVD-TRN-02352 | 036909C-JVD-TRN-02352 | IFR | 2019-08-20 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02352 |  | 2019-08-06 | 2
036909C-1028-PDS-1390-2861 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2845 A-B - ILK-28013 | A | 2019-08-01 | IFR | OL1-2P03-2861 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1028-PDS-1390-2860 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2829 A-B - ILK-28006 | A | 2019-08-01 | IFR | OL1-2P03-2860 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1028-PDS-1390-2859 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2826 A-B - ILK-28005 | A | 2019-08-01 | IFR | OL1-2P03-2859 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1028-PDS-1390-2858 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2823 A-B - ILK-28004 | A | 2019-08-01 | IFR | OL1-2P03-2858 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1023-PDS-1390-2326 | SP Item Datasheet - Double-Keyed Interlocked Locking Device - PSV-2332 A-B - ILK-23005 | A | 2019-07-18 | IFR | OL1-2P03-2326 | MP | 2019-07-30 | 036909C-JVD-TRN-02296 | 036909C-JVD-TRN-02296 | IFR | 2019-08-14 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02296 |  | 2019-07-31 | 2
036909C-1023-PDS-1390-2308 | SP Item Datasheet - Double-Keyed Interlocked Locking Device - PSV-2316 A-B - ILK-23001 | A | 2019-07-18 | IFR | OL1-2P03-2308 | MP | 2019-07-30 | 036909C-JVD-TRN-02296 | 036909C-JVD-TRN-02296 | IFR | 2019-08-14 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02296 |  | 2019-07-31 | 2
036909C-1023-PDS-1390-2307 | SP Item Datasheet - Double-Keyed Interlocked Locking Device - PSV-2327 A-B - ILK-23004 | A | 2019-07-18 | IFR | OL1-2P03-2307 | MP | 2019-07-30 | 036909C-JVD-TRN-02296 | 036909C-JVD-TRN-02296 | IFR | 2019-08-14 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02296 |  | 2019-07-31 | 2
036909C-1023-PDS-1390-2305 | SP Item Datasheet - Double-Keyed Interlocked Locking Device - PSV-2335 A-B - ILK-23003 | A | 2019-07-18 | IFR | OL1-2P03-2305 | MP | 2019-07-30 | 036909C-JVD-TRN-02296 | 036909C-JVD-TRN-02296 | IFR | 2019-08-14 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02296 |  | 2019-07-31 | 2
036909C-1023-PDS-1390-2302 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2322 A-B - ILK-23002 | A | 2019-07-18 | IFR | OL1-2P03-2302 | MP | 2019-07-24 | 036909C-JVD-TRN-02259 | 036909C-JVD-TRN-02259 | IFR | 2019-08-08 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02259 |  | 2019-07-25 | 2
036909C-1022-PDS-1390-2201 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2201 A-B-C - ILK-22001 | A | 2019-07-18 | IFR | OL1-2P03-2201 | MP | 2019-07-24 | 036909C-JVD-TRN-02259 | 036909C-JVD-TRN-02259 | IFR | 2019-08-08 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02259 |  | 2019-07-25 | 2
036909C-1012-PDS-1390-1201 | Piping Specialty Item Datasheet - Trapped Key Locking Devices - ILK-12001-16001 | B | 2019-07-25 | IFD | OL1-2P03-1201 | MP | 2019-07-30 | 036909C-JVD-TRN-02294 | 036909C-JVD-TRN-02294 | IFR | 2019-08-14 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-02294 |  | 2019-07-31 | 2
036909C-1052-PDS-1390-5202 | Piping Specialty Item - Datasheet - Steam Trap - E-5210 Shell Side Outlet - STT-52002 | A | 2019-07-29 | IFR | OL1-2P03-5202 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R1-No comments | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1052-PDS-1390-5201 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5204 A-B-C-D - ILK-52001 | A | 2019-07-22 | IFR | OL1-2P03-5201 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R1-No comments | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5134 | Piping Specialty Item - Datasheet – Double-Keyed Interlocked Locking Device - PSV-5153 A-D - ILK-51002 | A | 2019-07-22 | IFR | OL1-2P03-5134 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R1-No comments | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5129 | Piping Specialty Item - Datasheet – Double-Keyed Interlocked Locking Device - PSV-5150 A-D - ILK-51004 | A | 2019-07-22 | IFR | OL1-2P03-5129 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 | 2019-09-03 | R1-No comments | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1023-SP-1513-2301 | Complex Loop Narratives Area 23 - Caustic and Spent Caustic Treatment | B | 2019-07-26 | IBD | OL1-2I71-2301 | IE | 2019-07-30 | 036909C-JVD-TRN-02290 | 036909C-JVD-TRN-02290 | IFR | 2019-08-14 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-IE-02290 |  | 2019-07-31 | 2
036909C-1023-SP-0510-2330 | Mechanical Equipment Data Sheet - Spent Caustic Stripper | 0 | 2019-05-29 | IFP | OL1-2M03-2330 | ME | 2019-05-30 | 036909C-JVD-TRN-01779 | 036909C-JVD-TRN-01779 | IFR | 2019-06-14 | 2019-07-01 | Response to Client Comments emailed Sept-03-2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01779 |  | 2019-05-31 | 2
036909C-1051-SP-0213-0002 | Mechanical Equipment Datasheet for Condensate Polisher Package | 0 | 2019-08-29 | IFP | OL1-2M03-5125 | ME | 2019-08-30 | 036909C-JVD-TRN-02546 | 036909C-JVD-TRN-02546 | IFP | 2019-09-13 |  | Transmitted | TPSK-LSPA1-T-ME-02546 |  | 2019-09-03 | 2
036909C-100C-NM-1350-0031 | LOADS ON SLEEPER WAY 10-SLW-0C02 | A | 2019-08-29 | IBD | OL1-2P05-0031 | MP | 2019-08-30 | 036909C-JVD-TRN-02549 | 036909C-JVD-TRN-02549 | IFR | 2019-09-13 |  | Transmitted | TPSK-LSPA1-T-MP-02549 |  | 2019-09-03 | 2
036909C-100C-NM-1350-0030 | LOADS ON SLEEPER WAY 10-SLW-0C01 | A | 2019-08-30 | IBD | OL1-2P05-0030 | MP | 2019-08-30 | 036909C-JVD-TRN-02549 | 036909C-JVD-TRN-02549 | IFR | 2019-09-13 |  | Transmitted | TPSK-LSPA1-T-MP-02549 |  | 2019-09-03 | 2
036909C-1000-MR-0580-0001 | Material Requisition for Packing of Columns (C4 Unit) | 0 | 2019-07-05 | IFP | OL1-2C13-246000 | PL | 2019-07-05 | 036909C-JVD-TRN-02081 | 036909C-JVD-TRN-02081 | IFR | 2019-07-19 | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-PL-02081 |  | 2019-07-08 | 2
036909C-1000-DW-1431-0001-001 | Olefins Plant - Preliminary Field Pile Trial - Layout And Programme | 1 | 2019-08-30 | IFC | OL1-2K31-0342 | CV | 2019-09-02 | 036909C-JVD-TRN-02559 | 036909C-JVD-TRN-02559 | IFA | 2019-09-17 |  | Transmitted | TPSK-LSPA1-T-CV-02559 |  | 2019-09-03 | 1
036909C-1000-DW-1431-0001-001 | Olefins Plant - Preliminary Field Pile Trial - Layout And Programme | 0 | 2019-07-24 | IFC | OL1-2K31-0342 | CV | 2019-07-25 | 036909C-JVD-TRN-02265 | 036909C-JVD-TRN-02265 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02265 |  | 2019-07-29 | 1
036909C-1000-DW-1431-0001-001 | Olefins Plant - Preliminary Field Pile Trial - Layout And Programme | A | 2019-05-24 | IFR | OL1-2K31-0342 | CV | 2019-05-30 | 036909C-JVD-TRN-01769 | 036909C-JVD-TRN-01769 | IFA | 2019-06-14 | 2019-07-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01769 |  | 2019-05-31 | 1
036909C-1000-DW-1532-0004 | Telecomm Syst Architecture Of Safety Supervisory System | A | 2019-02-27 | IFR | OL1-2T31-0001 | EE | 2019-03-04 | 036909C-JVD-TRN-00976 | 036909C-JVD-TRN-00976, ROC-TPSK-CECO-T-00021 | IFA | 2019-03-19 | 2019-03-21 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00976 |  | 2019-03-05 | 1
036909C-1051-SP-0213-0002 | Mechanical Equipment Datasheet for Condensate Polisher Package | A | 2019-02-26 | IFQ | OL1-2M03-5125 | ME | 2019-02-27 | 036909C-JVD-TRN-00941 | 036909C-JVD-TRN-00941 | IFR | 2019-03-13 | 2019-04-01 | R1-No comments | TPSK-LSPA1-T-ME-00941 |  | 2019-02-28 | 2
036909C-1000-MR-0213-0001 | Material Requisition for Condensate Polisher Package | A | 2019-02-26 | IFQ | OL1-2C13-701000 | PL | 2019-02-27 | 036909C-JVD-TRN-00940 | 036909C-JVD-TRN-00940 | IFR | 2019-03-12 | 2019-06-07 | R2-Comments as noted | TPSK-LSPA1-T-PL-00940 |  | 2019-02-27 | 2
036909C-1000-MR-0570-0003 | Material Requisition For Trays For Columns | A | 2019-04-05 | IFQ | OL1-2C13-244000 | PL | 2019-04-08 | 036909C-JVD-TRN-01268 | 036909C-JVD-TRN-01268 | IFR | 2019-04-22 | 2019-06-07 | R2-Comments as noted | TPSK-LSPA1-T-PL-01268 |  | 2019-04-08 | 2
036909C-1000-MR-0840-0001 | Material Requisition For Filters And Coalescers | A | 2019-01-22 | IFQ | OL1-2C13-152000- | PL | 2019-01-28 | 036909C-JVD-TRN-00737 | 036909C-JVD-TRN-00737 | IFR | 2019-02-12 | 2019-06-06 | R2-Comments as noted | TPSK-LSPA1-T-PL-00737 | For next revision refer to document 036909C-1000-MR-0841-0001 | 2019-01-28 | 2
036909C-1000-MR-0841-0001 | Material Requisition for Filters and Colaescer | 0 | 2019-05-15 | IFP | OL1-2C13-152000 | PL | 2019-05-17 | 036909C-JVD-TRN-01689 | 036909C-JVD-TRN-01689 | IFR | 2019-06-03 | 2019-05-30 | R2-Comments as noted | TPSK-LSPA1-T-PL-01689 | For previous revision refer to document 036909C-1000-MR-0840-0001 | 2019-05-21 | 2
036909C-102A-DW-1843-0001-001 | Steel Structure For 10-T-2040 | A | 2019-06-26 | IFR | OL1-2K32-7380 | CV | 2019-06-28 | 036909C-JVD-TRN-02029 | 036909C-JVD-TRN-02029 | IFA | 2019-07-15 | 2019-08-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02029 |  | 2019-07-01 | 1
036909C-102A-CN-1733-0035 | Calculation Note For Concrete Structure Of 10-T-2040 | A | 2019-06-18 | IFR | OL1-2K13-0325 | CV | 2019-06-28 | 036909C-JVD-TRN-02030 | 036909C-JVD-TRN-02030 | IFA | 2019-07-15 | 2019-08-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02030 |  | 2019-07-01 | 1
036909C-1000-JSD-2200-02 | Job Design Specification For Thermal Insulation (Cold Service) | D | 2019-08-06 | IFR | OL1-2R04-0004 | MP | 2019-08-08 | 036909C-JVD-TRN-02391 | 036909C-JVD-TRN-02391 | IFR | 2019-08-23 | 2019-08-28 | R1-No comments | TPSK-LSPA1-T-MP-02391 |  | 2019-08-09 | 2
036909C-1000-NM-1601-0001 | Electrical Consumer List | B | 2019-07-24 | IFR | OL1-2E15-0001 | EE | 2019-07-26 | 036909C-JVD-TRN-02270 | 036909C-JVD-TRN-02270 | IFA | 2019-08-12 | 2019-08-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02270 |  | 2019-07-29 | 1
036909C-1000-JSS-1340-01 | Job Supply Specification For Forged Fittings | 0 | 2019-04-16 | IMP | OL1-2R04-0014 | MP | 2019-04-24 | 036909C-JVD-TRN-01463 | 036909C-JVD-TRN-01463 | IFR | 2019-05-09 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-MP-01463 |  | 2019-04-25 | 2
036909C-1000-JSS-1330-01 | Job Supply Specification For Buttwelding Fittings | 0 | 2019-04-16 | IMP | OL1-2R04-0013 | MP | 2019-04-24 | 036909C-JVD-TRN-01463 | 036909C-JVD-TRN-01463 | IFR | 2019-05-09 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-MP-01463 |  | 2019-04-25 | 2
036909C-105T-NM-1350-0032 | Loads On Sleeper Way 10-SLW-5T01 | A | 2019-08-20 | IBD | OL1-2P05-0213 | MP | 2019-08-29 | 036909C-JVD-TRN-02534 | 036909C-JVD-TRN-02534 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-MP-02534 |  | 2019-08-30 | 2
036909C-105F-DW-1980-0001 | PASSIVE FIRE PROTECTION DRAWING - ZONE 5F - HP & POLYOLEFINS FLARES UNIT | B | 2019-08-26 | IBD | OL1-2F45-0008 | FF | 2019-08-29 | 036909C-JVD-TRN-02535 | 036909C-JVD-TRN-02535 | IFI | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-FF-02535 |  | 2019-08-30 | 2
036909C-102D-CN-1733-0044 | Calculation Note For Foundation Of PSA PKG 10-PK-2560 - 10-D-2560-A-E - 10-D-2565 | A | 2019-08-28 | IFR | OL1-2K13-0134 | CV | 2019-08-29 | 036909C-JVD-TRN-02537 | 036909C-JVD-TRN-02537 | IFA | 2019-09-13 |  | Transmitted | TPSK-LSPA1-T-CV-02537 |  | 2019-08-30 | 1
036909C-102A-DW-1743-0037-001 | Foundation For 10-F-2137-A-B | A | 2019-08-28 | IFR | OL1-2K31-4590 | CV | 2019-08-29 | 036909C-JVD-TRN-02540 | 036909C-JVD-TRN-02540 | IFA | 2019-09-13 |  | Transmitted | TPSK-LSPA1-T-CV-02540 |  | 2019-08-30 | 1
036909C-102D-DW-1743-0001-001 | Foundation For PSA Package 10-PK-2560 - 10-D-2560-A-E - 10-D-2565 | A | 2019-08-28 | IFR | OL1-2K31-2780 | CV | 2019-08-29 | 036909C-JVD-TRN-02538 | 036909C-JVD-TRN-02538 | IFA | 2019-09-13 |  | Transmitted | TPSK-LSPA1-T-CV-02538 |  | 2019-08-30 | 1
036909C-100M-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 0M METERING STATION | D | 2019-08-28 | IBD | OL1-2F30-0007 | FF | 2019-08-29 | 036909C-JVD-TRN-02535 | 036909C-JVD-TRN-02535 | IFI | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-FF-02535 |  | 2019-08-30 | 2
036909C-103S-NM-1652-0001 | Substation C - Medium Voltage - Switchboard Composition | A | 2019-07-31 | IFQ | OL1-2E15-0005 | EE | 2019-08-01 | 036909C-JVD-TRN-02315 | 036909C-JVD-TRN-02315 | IFA | 2019-08-16 | 2019-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02315 |  | 2019-08-05 | 1
036909C-100S-NM-1652-0001 | SUBSTATION E - Medium Voltage - Switchboard Composition | A | 2019-07-31 | IFQ | OL1-2E15-0004 | EE | 2019-08-01 | 036909C-JVD-TRN-02315 | 036909C-JVD-TRN-02315 | IFA | 2019-08-16 | 2019-08-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-02315 |  | 2019-08-05 | 1
036909C-1000-SP-1691-0100 | Typical Data Sheet for LV Motors | A | 2018-11-16 | IFQ | OL1-2E05-3100 | EE | 2018-11-26 | 036909C-JVD-TRN-00358 | 036909C-JVD-TRN-00358 | IFR | 2018-12-11 | 2019-01-03 | R1-No comments | TPSK-LSPA1-T-EE-00358 |  | 2018-11-26 | 2
036909C-1000-JSD-1547-0001 | Flow Measurement | 0 | 2018-09-28 | IMP | OL1-2R06-0003 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | 2018-10-03 | 3
036909C-1000-JSD-1545-0001 | Pressure Safety Valve | 0 | 2018-09-28 | IMP | OL1-2R06-0021 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | 2018-10-04 | 3
036909C-1000-JSD-1572-0004 | Instrument Installation | 0 | 2018-09-28 | IMP | OL1-2R08-0003 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | 2018-10-04 | 3
036909C-1000-JSD-1980-0001 | Fire Proof | 0 | 2019-06-04 | IFE | OL1-2L01-0002 | SE | 2019-06-11 | 036909C-JVD-TRN-01869 | 036909C-JVD-TRN-01869 | IFR | 2019-06-26 | 2019-07-03 | R2-Comments as noted | TPSK-LSPA1-T-SE-01869 |  | 2019-06-11 | 2
036909C-1000-JSD-6200-0001 | Environmental Protection Design Criteria | A | 2018-12-05 | IFR | OL1-2S08-0001 | ES | 2018-12-11 | 036909C-JVD-TRN-00473 | 036909C-JVD-TRN-00473 | IFR | 2018-12-27 |  | Transmitted | TPSK-LSPA1-T-ES-00473 |  | 2018-12-11 | 2
036909C-1000-JSD-1300-0008 | JSD For Piping Stress Analysis | 0 | 2019-02-14 | IMP | OL1-2R04-0032 | MP | 2019-02-19 | 036909C-JVD-TRN-00881 | 036909C-JVD-TRN-00881, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-18 | 2019-03-21 | R1-No Comments_TPSK-LSPA1-E-00157_02/05/2019 | TPSK-LSPA1-T-MP-00881 |  | 2019-02-19 | 2
036909C-1000-SP-1691-0500 | Typical Data Sheet For Low Voltage Variable Voltage Variable Frequency System | A | 2018-11-16 | IFQ | OL1-2E05-3500 | EE | 2018-11-26 | 036909C-JVD-TRN-00358 | 036909C-JVD-TRN-00358 | IFR | 2018-12-11 | 2019-01-03 | R1-No comments | TPSK-LSPA1-T-EE-00358 |  | 2018-11-26 | 2
036909C-1000-JSD-1552-0001 | Level Measurement | 0 | 2018-12-14 | IMP | OL1-2R06-0005 | IE | 2018-12-17 | 036909C-JVD-TRN-00507 | 036909C-JVD-TRN-00507, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-28 | 2018-12-26 | R1-No comments | TPSK-LSPA1-T-IE-00507 |  | 2018-12-17 | 2
036909C-1000-JSD-1300-0011 | Piping Flexibility | 0 | 2019-02-04 | IMP | OL1-2R04-0030 | MP | 2019-02-08 | 036909C-JVD-TRN-00828 | 036909C-JVD-TRN-00828, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-MP-00828 |  | 2019-02-08 | 2
036909C-1000-JSD-1553-0001 | Pressure Measurement | 0 | 2018-12-14 | IMP | OL1-2R06-0006 | IE | 2018-12-17 | 036909C-JVD-TRN-00507 | 036909C-JVD-TRN-00507, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-28 | 2018-12-26 | R1-No comments | TPSK-LSPA1-T-IE-00507 |  | 2018-12-17 | 2
036909C-1000-JSS-1622-0001 | Miscellaneous Equipment | 0 | 2018-09-20 | IMP | OL1-2R05-0022 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | 2018-11-05 | 3
036909C-1000-JSS-0920-0001 | ME-011 RECIPROCATING PUMP | A | 2019-04-23 | IFR | OL1-2R03-0011 | ME | 2019-04-24 | 036909C-JVD-TRN-01459 | 036909C-JVD-TRN-01459 | IFR | 2019-05-08 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-ME-01459 |  | 2019-04-25 | 2
036909C-1000-JSD-1572-0001 | Instrument Construction Material | 0 | 2018-09-28 | IMP | OL1-2R06-0010 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | 2018-10-04 | 3
036909C-1000-JSS-0900-0001 | ME-028 Mechanical Seal | 0 | 2018-09-14 | IMP | OL1-2R03-0028 | ME | 2018-09-17 | 036909C-JVD-TRN-00057 | 036909C-JVD-TRN-00057, ROC-TPSK-CECO-T-00003 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00057 |  | 2018-09-18 | 3
036909C-1000-JSD-1554-0001 | Temperature Measurement | 0 | 2018-12-14 | IMP | OL1-2R06-0007 | IE | 2018-12-17 | 036909C-JVD-TRN-00507 | 036909C-JVD-TRN-00507, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-28 | 2018-12-26 | R1-No comments | TPSK-LSPA1-T-IE-00507 |  | 2018-12-17 | 2
036909C-1000-JSS-1691-0001 | Electrical Motos Up To 300 kW | 0 | 2018-09-20 | IMP | OL1-2R05-0010 | EE | 2018-09-24 | 036909C-JVD-TRN-00079 | 036909C-JVD-TRN-00079 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00079 |  | 2018-09-25 | 3
036909C-1000-JSS-6300-05 | Job Specification For Welding And NDE Storage Tenks | 0 | 2019-02-21 | IMP | OL1-2R03-0004 | ME | 2019-02-25 | 036909C-JVD-TRN-00921 | 036909C-JVD-TRN-00921 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00921 |  | 2019-02-26 | 2
036909C-1000-JSD-1511-0001 | Instrument Cabinet | 0 | 2019-02-27 | IMP | OL1-2R06-0016 | IE | 2019-03-05 | 036909C-JVD-TRN-00986 | 036909C-JVD-TRN-00986, ROC-TPSK-CECO-T-00004 | IFR | 2019-03-20 | 2019-05-15 | R1-No comments | TPSK-LSPA1-T-IE-00986 |  | 2019-03-06 | 2
036909C-1000-JSD-1541-0001 | Final Control Element | 0 | 2019-05-20 | IMP | OL1-2R06-0008 | IE | 2019-05-23 | 036909C-JVD-TRN-01727 | 036909C-JVD-TRN-01727 | IFR | 2019-06-07 | 2019-06-12 | R2-Comments as noted | TPSK-LSPA1-T-IE-01727 |  | 2019-05-24 | 2
036909C-1000-DI-0007-0002 | Equipment Basis of Design | B | 2019-03-25 | IFD | OL1-2G02-0002 | PE | 2019-03-26 | 036909C-JVD-TRN-01154 | 036909C-JVD-TRN-01154 | IFA | 2019-04-10 |  | Transmitted | TPSK-LSPA1-T-PE-01154 |  | 2019-03-27 | 1
036909C-1000-JSD-1522-0001 | Electrical And Instrument Interface Philosophy | 0 | 2018-12-14 | IMP | OL1-2R07-0020 | IE | 2018-12-17 | 036909C-JVD-TRN-00507 | 036909C-JVD-TRN-00507, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-28 | 2018-12-26 | R1-No comments | TPSK-LSPA1-T-IE-00507 |  | 2018-12-17 | 2
036909C-1000-DI-0007-0001 | Process Basis of Design | B | 2019-03-25 | IFD | OL1-2G02-0001 | PE | 2019-03-26 | 036909C-JVD-TRN-01154 | 036909C-JVD-TRN-01154 | IFA | 2019-04-10 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01154 |  | 2019-03-27 | 1
036909C-1050-DI-0007-5001 | Area Basis of Design - 50 ISBL Supporting Utilities | A | 2018-07-25 | IFA | OL1-2G05-5001 | PE | 2018-07-31 | 036909C-JVD-TRN-00003 | 036909C-JVD-TRN-00003, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-13 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00003 |  | 2018-07-31 | 1
036909C-1031-PDS-0500-3110 | Process Equipment Datasheet - 10-T-3110 - Water Washer | C | 2019-07-25 | IFD | OL1-2G30-3110 | PE | 2019-07-25 | 036909C-JVD-TRN-02266 | 036909C-JVD-TRN-02266 | IFR | 2019-08-09 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PE-02266 |  | 2019-07-29 | 2
036909C-1030-PDS-0500-3080 | Process Equipment Datasheet - 10-T-3080 - Butadiene Tower | C | 2019-07-25 | IFD | OL1-2G30-3080 | PE | 2019-07-25 | 036909C-JVD-TRN-02266 | 036909C-JVD-TRN-02266 | IFR | 2019-08-09 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PE-02266 |  | 2019-07-29 | 2
036909C-1000-DL-0570-0003 | Deviation List For Trays For Columns (C4 Unit) | B | 2019-08-09 | IFR | OL1-2C40-244000 | PL | 2019-08-14 | 036909C-JVD-TRN-02432 | 036909C-JVD-TRN-02432 | IFR | 2019-08-28 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PL-02432 |  | 2019-08-15 | 2
036909C-1030-PDS-0500-3090 | Process Equipment Datasheet - 10-T-3090 - Butadiene Drying Tower | C | 2019-07-25 | IFD | OL1-2G30-3090 | PE | 2019-07-25 | 036909C-JVD-TRN-02266 | 036909C-JVD-TRN-02266 | IFR | 2019-08-09 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PE-02266 |  | 2019-07-29 | 2
036909C-1030-PDS-0500-3060 | Process Equipment Datasheet - 10-T-3060 - C4 Acetylene Washer | C | 2019-07-25 | IFD | OL1-2G30-3060 | PE | 2019-07-25 | 036909C-JVD-TRN-02266 | 036909C-JVD-TRN-02266 | IFR | 2019-08-09 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PE-02266 |  | 2019-07-29 | 2
036909C-1030-PDS-0500-3000 | Process Equipment Datasheet - 10-T-3000 - Predistillation Tower | C | 2019-07-25 | IFD | OL1-2G30-3000 | PE | 2019-07-25 | 036909C-JVD-TRN-02266 | 036909C-JVD-TRN-02266 | IFR | 2019-08-09 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PE-02266 |  | 2019-07-29 | 2
036909C-1030-PDS-0500-3010 | Process Equipment Datasheet - 10-T-3010 - C4 Vaporization Tower | C | 2019-07-25 | IFD | OL1-2G30-3010 | PE | 2019-07-25 | 036909C-JVD-TRN-02266 | 036909C-JVD-TRN-02266 | IFR | 2019-08-09 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PE-02266 |  | 2019-07-29 | 2
036909C-1012-ML-231 | Recovery Process and Utilities Sections SIL Classification Report | A | 2019-07-10 | IFR | OL1-2S95-0231 | ES | 2019-07-10 | 036909C-JVD-TRN-02124 | 036909C-JVD-TRN-02124 | IFR | 2019-07-25 | 2019-08-07 | R2-Comments as noted | TPSK-LSPA1-T-ES-02124 |  | 2019-07-11 | 2
036909C-1000-JSD-0000-0006 | Tray Design Specification | A | 2019-01-07 | IFR | OL1-2G01-0004 | PE | 2019-01-10 | 036909C-JVD-TRN-00624 | 036909C-JVD-TRN-00624 | IFR | 2019-01-25 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00624 |  | 2019-01-10 | 2
036909C-1000-JSS-0570-01 | Job Specification For Supply Of Column Internals | 0 | 2018-09-20 | IMP | OL1-2R03-0052 | ME | 2018-09-24 | 036909C-JVD-TRN-00081 | 036909C-JVD-TRN-00081, ROC-TPSK-CECO-T-00003 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00081 |  | 2018-09-25 | 3
036909C-100M-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 0M METERING STATION | C | 2019-05-06 | IFR | OL1-2F30-0007 | FF | 2019-05-08 | 036909C-JVD-TRN-01612 | 036909C-JVD-TRN-01612, KLOC-TPSK-VSAFE-T-00008 | IFR | 2019-05-22 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-0612 |  | 2019-05-09 | 2
036909C-100M-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 0M METERING STATION | B | 2019-04-25 | IFR | OL1-2F30-0007 | FF | 2019-04-30 | 036909C-JVD-TRN-01519 | 036909C-JVD-TRN-01519, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-05-14 |  | Transmitted | TPSK-LSPA1-T-FF-01519 |  | 2019-05-02 | 2
036909C-100M-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 0M METERING STATION | A | 2019-04-05 | IFR | OL1-2F30-0007 | FF | 2019-04-08 | 036909C-JVD-TRN-01270 | 036909C-JVD-TRN-01270, KLOC-TPSK-VSAFE-T-00003 | IFR | 2019-04-22 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01270 |  | 2019-04-08 | 2
036909C-105F-DW-1980-0001 | Passive Fire Protection Drawing - Zone 5F - Hp & Polyolefins Flares Unit | A | 2019-05-24 | IFR | OL1-2F45-0008 | FF | 2019-05-28 | 036909C-JVD-TRN-01751 | 036909C-JVD-TRN-01751 | IFR | 2019-06-11 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-FF-01751 |  | 2019-05-28 | 2
036909C-1000-PO-036909C001P57-057 | Vendor s Acknowledgment of Purchase Order For Shell & Tube Heat Exchangers Lot-3 – MR 0610-0004 Rev 0 | 0 | 2019-07-16 | IFI | OL1-2C51-0110 | ME | 2019-07-17 | 036909C-JVD-TRN-INTERNAL-00340 | 036909C-JVD-TRN-02355 |  |  | 2019-08-22 | R2-Comments as noted | TPSK-LSPA1-T-PL-02355 |  | 2019-08-07 | 3
036909C-1000-PO-036909C001P56-056 | Vendor s Acknowledgment of Purchase Order For Recycle Gas Compressor – MR 1031-0001 Rev 0 | 0 | 2019-07-16 | IFI | OL1-2C51-0109 | PL | 2019-07-17 | 036909C-JVD-TRN-INTERNAL-00340 | 036909C-JVD-TRN-02355 |  |  | 2019-08-22 | R1-No comments | TPSK-LSPA1-T-PL-02355 |  | 2019-08-07 | 3
036909C-1000-PO-036909C001P60-060 | Vendor s Acknowledgment of Purchase Order For Cooling Water Pumps – MR 0910-0003 Rev 0 | 0 | 2019-07-17 | IFI | OL1-2C51-0113 | PL | 2019-07-17 | 036909C-JVD-TRN-INTERNAL-00340 | 036909C-JVD-TRN-02355 |  |  | 2019-08-22 | R2-Comments as noted | TPSK-LSPA1-T-PL-02355 |  | 2019-08-07 | 3
036909C-1000-PO-036909C001P55-055 | Vendor s Acknowledgment of Purchase Order For Shell & Tube Heat Exchangers (Lot-1) | 0 | 2019-07-17 | IFI | OL1-2C51-0108 | PL | 2019-07-17 | 036909C-JVD-TRN-INTERNAL-00340 | 036909C-JVD-TRN-02355 |  |  |  | Transmitted | TPSK-LSPA1-T-PL-02355 |  | 2019-08-07 | 3
036909C-1030-SP-1513-3002 | Instrument Interlock Descriptions Area 30 - Butadiene Extraction Unit BDU | C | 2019-08-28 | IBD | OL1-2G50-3002 | PE | 2019-08-28 | 036909C-JVD-TRN-02526 | 036909C-JVD-TRN-02526 | IFR | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-PE-02526 |  | 2019-08-29 | 2
036909C-1030-SP-1513-3001 | Complex Loop Narratives Area 30 - Butadiene Extraction Unit BDU | C | 2019-08-28 | IBD | OL1-2I71-3001 | IE | 2019-08-28 | 036909C-JVD-TRN-02527 | 036909C-JVD-TRN-02527 | IFR | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-IE-02527 |  | 2019-08-29 | 2
036909C-1030-TDS-0610-3098 | Mechanical Equipment Data Sheet - 10-E-3098 - Butadiene Product Subcooler | B | 2019-08-26 | IFQ | OL1-2M03-3098 | ME | 2019-08-28 | 036909C-JVD-TRN-02520 | 036909C-JVD-TRN-02520 | IFR | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-ME-02520 |  | 2019-08-29 | 2
036909C-102B-CN-1733-0031 | Calculation Note For Foundation Of 10-TK-2320 | A | 2019-07-30 | IFR | OL1-2K13-0193 | CV | 2019-08-28 | 036909C-JVD-TRN-02517 | 036909C-JVD-TRN-02517 | IFA | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-CV-02517 |  | 2019-08-29 | 1
036909C-1030-TDS-0610-3085 | Mechanical Equipment Data Sheet - 10-E-3085 - Butadiene Tower Reboiler | B | 2019-08-26 | IFQ | OL1-2M03-3085 | ME | 2019-08-28 | 036909C-JVD-TRN-02524 | 036909C-JVD-TRN-02524 | IFR | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-ME-02524 |  | 2019-08-29 | 2
036909C-1030-DW-1514-3001 | Cause And Effect Diagram Area 30 - Butadiene Extraction Unit BDU | D | 2019-08-28 | IBD | OL1-2G50-3001 | PE | 2019-08-28 | 036909C-JVD-TRN-02525 | 036909C-JVD-TRN-02525 | IFR | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-PE-02525 |  | 2019-08-29 | 2
036909C-1031-TDS-0610-3160 | Mechanical Equipment Data Sheet - 10-E-3160 - BDU Condensate Cooler | B | 2019-08-26 | IFQ | OL1-2M03-3160 | ME | 2019-08-28 | 036909C-JVD-TRN-02520 | 036909C-JVD-TRN-02520 | IFR | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-ME-02520 |  | 2019-08-29 | 2
036909C-100M-DW-1622-0201 | Power Layout - Zone 0M Metering Station | A | 2019-08-26 | IFR | OL1-2E32-0006 | EE | 2019-08-29 | 036909C-JVD-TRN-02529 | 036909C-JVD-TRN-02529 | IFA | 2019-09-12 |  | Transmitted | TPSK-LSPA1-T-EE-02529 |  | 2019-08-29 | 1
036909C-1000-MS-1620-0001 | Work Method Statement For Temporary Power Package | A | 2019-08-23 | IFR | OL1-2D92-0004 | CM | 2019-08-29 | 036909C-JVD-TRN-02531 | 036909C-JVD-TRN-02531 | IFR | 2019-09-13 |  | Transmitted | TPSK-LSPA1-T-CM-02531 |  | 2019-08-29 | 2
036909C-1053-PDS-2600-5397 | Process Equipment Datasheet - 10-PK-5397 - Non-oxidizing Biocide Inj Pkg | 0 | 2019-07-25 | CAN | OL1-2G30-5397 | PE | 2019-07-30 | 036909C-JVD-TRN-02284 | 036909C-JVD-TRN-02284 | IFR | 2019-08-14 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-02284 |  | 2019-07-31 | 2
036909C-1023-SP-0910-2302 | Mechanical Equipment Datasheet - Strong Caustic Circulating Pumps | A | 2018-11-13 | IFQ | OL1-2M03-2302 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320, ROC-TPSK-CECO-T-00014 | IFR | 2018-11-29 | 2018-12-10 | TPSK-LSPA1-E-00104 march 20 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-00320 |  | 2018-11-15 | 2
036909C-1023-SP-0910-2306 | Mechanical Equipment Datasheet - Weak Caustic Circulating Pumps | B | 2018-12-03 | IFQ | OL1-2M03-2306 | ME | 2018-12-05 | 036909C-JVD-TRN-00411 | 036909C-JVD-TRN-00411, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-18 | 2018-12-27 | TPSK-LSPA1-E-00105 March 20 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-00411 |  | 2018-12-05 | 2
036909C-1023-SP-0910-2304 | Mechanical Equipment Datasheet - Intermediate Caustic Circulating Pump | B | 2018-12-03 | IFQ | OL1-2M03-2304 | ME | 2018-12-05 | 036909C-JVD-TRN-00411 | 036909C-JVD-TRN-00411, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-18 | 2018-12-27 | TPSK-LSPA1-E-00105 March 20 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-00411 |  | 2018-12-05 | 2
036909C-1000-SP-1641-1501 | Datasheet For Distribution Transformer | B | 2019-07-31 | IFR | OL1-2E05-1501 | EE | 2019-08-01 | 036909C-JVD-TRN-02316 | 036909C-JVD-TRN-02316 | IFA | 2019-08-16 | 2019-08-26 | A1-Approved without comments | TPSK-LSPA1-T-EE-02316 |  | 2019-08-05 | 1
036909C-1000-DW-1652-0001 | Key Single Line Diagram | B | 2019-08-01 | IFR | OL1-2E14-0001 | EE | 2019-08-02 | 036909C-JVD-TRN-02329 | 036909C-JVD-TRN-02329 | IFA | 2019-08-19 | 2019-08-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-02329 |  | 2019-08-05 | 1
036909C-1030-SP-1513-3001 | Complex Loop Narratives Area 30 - Butadiene Extraction Unit BDU | A | 2019-06-14 | IFR | OL1-2I71-3001 | IE | 2019-06-17 | 036909C-JVD-TRN-01906 | 036909C-JVD-TRN-01906 | IFR | 2019-07-02 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01906 |  | 2019-06-18 | 2
036909C-1030-SP-1513-3002 | Instrument Interlock Descriptions Area 30 - Butadiene Extraction Unit BDU | A | 2019-06-10 | IFR | OL1-2G50-3002 | PE | 2019-06-11 | 036909C-JVD-TRN-01868 | 036909C-JVD-TRN-01868 | IFR | 2019-06-26 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01868 |  | 2019-06-11 | 2
036909C-1030-SP-1513-3002 | Instrument Interlock Descriptions Area 30 - Butadiene Extraction Unit BDU | B | 2019-08-15 | IBD | OL1-2G50-3002 | PE | 2019-08-15 | 036909C-JVD-TRN-02443 | 036909C-JVD-TRN-02443 | IFR | 2019-08-30 |  | Transmitted | TPSK-LSPA1-T-PE-02443 |  | 2019-08-16 | 2
036909C-1030-DW-1514-3001 | Cause And Effect Diagram Area 30 - Butadiene Extraction Unit BDU | B | 2019-08-15 | IBD | OL1-2G50-3001 | PE | 2019-08-15 | 036909C-JVD-TRN-02442 | 036909C-JVD-TRN-02442 | IFR | 2019-08-30 |  | Transmitted | TPSK-LSPA1-T-PE-02442 |  | 2019-08-16 | 2
036909C-1030-DW-1514-3001 | Cause And Effect Diagram Area 30 - Butadiene Extraction Unit BDU | C | 2019-08-27 | IBD | OL1-2G50-3001 | PE | 2019-08-27 | 036909C-JVD-TRN-02505 | 036909C-JVD-TRN-02505 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-PE-02505 |  | 2019-08-28 | 2
036909C-1030-DW-1514-3001 | Cause and Effect Diagram - Area 30 - Butadiene Extraction Unit - BDU | A | 2019-05-29 | IFR | OL1-2G50-3001 | PE | 2019-05-30 | 036909C-JVD-TRN-01773 | 036909C-JVD-TRN-01773 | IFR | 2019-06-14 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01773 |  | 2019-05-31 | 2
036909C-1000-JSS-1657-0001 | Low Voltage Distribution Panel | 0 | 2018-09-20 | IMP | OL1-2R05-0007 | EE | 2018-11-12 | 036909C-JVD-TRN-00309 | 036909C-JVD-TRN-00309 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00309 |  | 2018-11-12 | 3
036909C-1028-PDS-1390-2857 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2820 A-B - ILK-28003 | A | 2019-08-01 | IFR | OL1-2P03-2857 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1028-PDS-1390-2856 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2806 A-D - ILK-28002 | A | 2019-08-01 | IFR | OL1-2P03-2856 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1028-PDS-1390-2855 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2805 A-E - ILK-28001 | A | 2019-08-01 | IFR | OL1-2P03-2855 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1027-PDS-1390-2726 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2761 A-B - ILK-27007 | A | 2019-08-01 | IFR | OL1-2P03-2726 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1027-PDS-1390-2719 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2723 A-D - ILK-27004 | A | 2019-08-01 | IFR | OL1-2P03-2719 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1027-PDS-1390-2715 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2733 A-E - ILK-27003 | A | 2019-08-01 | IFR | OL1-2P03-2715 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1027-PDS-1390-2713 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2716 A-B - ILK-27002 | A | 2019-08-01 | IFR | OL1-2P03-2713 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1027-PDS-1390-2712 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2750 A-B - ILK-27001 | A | 2019-08-01 | IFR | OL1-2P03-2712 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1026-PDS-1390-2612 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2626 A-B - ILK-26006 | A | 2019-08-01 | IFR | OL1-2P03-2612 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1026-PDS-1390-2610 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2620 A-B - ILK-26005 | A | 2019-08-01 | IFR | OL1-2P03-2610 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1026-PDS-1390-2609 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2633 A-B - ILK-26004 | A | 2019-08-01 | IFR | OL1-2P03-2609 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1026-PDS-1390-2605 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2639 A-B - ILK-26003 | A | 2019-08-01 | IFR | OL1-2P03-2605 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1025-PDS-1390-2559 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2545 A-B - ILK-25012 | A | 2019-07-31 | IFR | OL1-2P03-2559 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1025-PDS-1390-2558 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2548 A-B - ILK-25009 | A | 2019-07-31 | IFR | OL1-2P03-2558 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1025-PDS-1390-2557 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2565 A-B-C - ILK-25008 | A | 2019-07-31 | IFR | OL1-2P03-2557 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1025-PDS-1390-2556 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2550 A-B-C - ILK-25007 | A | 2019-07-31 | IFR | OL1-2P03-2556 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1025-PDS-1390-2555 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2544 A-B - ILK-25005 | A | 2019-07-31 | IFR | OL1-2P03-2555 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1025-PDS-1390-2554 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2540 A-B - ILK-25004 | A | 2019-07-31 | IFR | OL1-2P03-2554 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1025-PDS-1390-2553 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2539 A-B - ILK-25003 | A | 2019-07-31 | IFR | OL1-2P03-2553 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1025-PDS-1390-2552 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2525 A-B - ILK-25013 | A | 2019-07-31 | IFR | OL1-2P03-2552 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1025-PDS-1390-2551 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2524 A-B - ILK-25002 | A | 2019-07-31 | IFR | OL1-2P03-2551 | MP | 2019-08-05 | 036909C-JVD-TRN-02348 | 036909C-JVD-TRN-02348 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02348 |  | 2019-08-06 | 2
036909C-1025-CN-1390-2560 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2514 A-B - ILK-25014 | A | 2019-07-31 | IFR | OL1-2P03-2560 | MP | 2019-08-05 | 036909C-JVD-TRN-02349 | 036909C-JVD-TRN-02349 | IFR | 2019-08-20 | 2019-08-28 | R2-Comments as noted | TPSK-LSPA1-T-MP-02349 |  | 2019-08-06 | 2
036909C-105W-DW-1741-0001-001 | Foundation for Pipe Bridge 10-PRK-5W01 - Plan & Detail | A | 2019-08-26 | IFR | OL1-2K31-0365 | CV | 2019-08-27 | 036909C-JVD-TRN-02500 | 036909C-JVD-TRN-02500 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02500 |  | 2019-08-28 | 2
036909C-105W-DW-1741-0001-002 | Foundation for Pipe Bridge 10-PRK-5W01 - Detail | A | 2019-08-26 | IFR | OL1-2K31-0366 | CV | 2019-08-27 | 036909C-JVD-TRN-02500 | 036909C-JVD-TRN-02500 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02500 |  | 2019-08-28 | 2
036909C-1055-SP-4123-4313 | Mechanical Equipment Datasheet Emergency Diesel Engine Generator - Substation F | A | 2019-08-27 | IFQ | OL1-2M03-4313 | ME | 2019-08-28 | 036909C-JVD-TRN-02515 | 036909C-JVD-TRN-02515 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02515 |  | 2019-08-28 | 2
036909C-1050-SP-4123-4312 | Mechanical Equipment Datasheet Emergency Diesel Engine Generator - Substation E | A | 2019-08-27 | IFQ | OL1-2M03-4312 | ME | 2019-08-28 | 036909C-JVD-TRN-02515 | 036909C-JVD-TRN-02515 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02515 |  | 2019-08-28 | 2
036909C-105F-DW-1933-0001 | Fire Protection & Firefighting Layout - Zone 5F Hp & Polyolefins Flares Unit | D | 2019-08-26 | IBD | OL1-2F30-0006 | SE | 2019-08-27 | 036909C-JVD-TRN-02501 | 036909C-JVD-TRN-02501 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-SE-02501 |  | 2019-08-28 | 2
036909C-1030-TDS-0610-3018 | Mechanical Equipment Data Sheet - 10-E-3018 - Solvent Cooler | B | 2019-08-26 | IFQ | OL1-2M03-3018 | ME | 2019-08-27 | 036909C-JVD-TRN-02508 | 036909C-JVD-TRN-02508 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02508 |  | 2019-08-28 | 2
036909C-1030-TDS-0610-3004 | Mechanical Equipment Data Sheet - 10-E-3004 - Predistillation Tower Trim Reboiler | B | 2019-08-26 | IFQ | OL1-2M03-3004 | ME | 2019-08-27 | 036909C-JVD-TRN-02502 | 036909C-JVD-TRN-02502 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02502 |  | 2019-08-28 | 2
036909C-1030-TDS-0610-3031 | Mechanical Equipment Data Sheet - 10-E-3030 -After Washer Condenser | B | 2019-08-26 | IFQ | OL1-2M03-3031 | ME | 2019-08-27 | 036909C-JVD-TRN-02508 | 036909C-JVD-TRN-02508 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02508 |  | 2019-08-28 | 2
036909C-1030-TDS-0610-3084 | Mechanical Equipment Data Sheet - 10-E-3084 - Butadiene Tower Trim Reboiler | B | 2019-08-26 | IFQ | OL1-2M03-3084 | ME | 2019-08-27 | 036909C-JVD-TRN-02511 | 036909C-JVD-TRN-02511 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02511 |  | 2019-08-28 | 2
036909C-1030-TDS-0610-3062 | Mechanical Equipment Data Sheet - 10-E-3062 - Acetylene Condenser | B | 2019-08-15 | IFQ | OL1-2M03-3062 | ME | 2019-08-27 | 036909C-JVD-TRN-02509 | 036909C-JVD-TRN-02509 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02509 |  | 2019-08-28 | 2
036909C-1030-TDS-0610-3021 | Mechanical Equipment Data Sheet - 10-E-3020 - Main Washer Condenser | B | 2019-08-26 | IFQ | OL1-2M03-3021 | ME | 2019-08-27 | 036909C-JVD-TRN-02510 | 036909C-JVD-TRN-02510 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02510 |  | 2019-08-28 | 2
036909C-1030-TDS-0610-3063 | Mechanical Equipment Data Sheet - 10-E-3060 - C4 Acetylene Washer Condenser | B | 2019-08-26 | IFQ | OL1-2M03-3063 | ME | 2019-08-27 | 036909C-JVD-TRN-02510 | 036909C-JVD-TRN-02510 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02510 |  | 2019-08-28 | 2
036909C-1030-TDS-0610-3044 | Mechanical Equipment Data Sheet - 10-E-3044 - Solvent Heater | B | 2019-08-26 | IFQ | OL1-2M03-3044 | ME | 2019-08-27 | 036909C-JVD-TRN-02510 | 036909C-JVD-TRN-02510 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02510 |  | 2019-08-28 | 2
036909C-1030-TDS-0610-3081 | Mechanical Equipment Data Sheet - 10-E-3080 - Butadiene Tower Condenser | B | 2019-08-26 | IFQ | OL1-2M03-3081 | ME | 2019-08-27 | 036909C-JVD-TRN-02509 | 036909C-JVD-TRN-02509 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02509 |  | 2019-08-28 | 2
036909C-1030-TDS-0610-3055 | Mechanical Equipment Data Sheet - 10-E-3055 - Degasser Reboiler | B | 2019-08-26 | IFQ | OL1-2M03-3055 | ME | 2019-08-27 | 036909C-JVD-TRN-02509 | 036909C-JVD-TRN-02509 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02509 |  | 2019-08-28 | 2
036909C-1030-TDS-0610-3045 | Mechanical Equipment Data Sheet - 10-E-3045 A-D- Solvent Heat Exchanger | B | 2019-08-26 | IFQ | OL1-2M03-3045 | ME | 2019-08-27 | 036909C-JVD-TRN-02509 | 036909C-JVD-TRN-02509 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02509 |  | 2019-08-28 | 2
036909C-1030-TDS-0610-3071 | Mechanical Equipment Data Sheet - 10-E-3070 - Water - NMP Cooler | B | 2019-08-26 | IFQ | OL1-2M03-3071 | ME | 2019-08-27 | 036909C-JVD-TRN-02509 | 036909C-JVD-TRN-02509 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02509 |  | 2019-08-28 | 2
036909C-1030-SP-4123-4311 | Mechanical Equipment Datasheet Emergency Diesel Engine Generator - Substation C | A | 2019-08-27 | IFQ | OL1-2M03-4311 | ME | 2019-08-28 | 036909C-JVD-TRN-02515 | 036909C-JVD-TRN-02515 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02515 |  | 2019-08-28 | 2
036909C-1030-TDS-0610-3001 | Mechanical Equipment Data Sheet - 10-E-3000 - Predistillation Tower Condenser | B | 2019-08-26 | IFQ | OL1-2M03-3001 | ME | 2019-08-27 | 036909C-JVD-TRN-02502 | 036909C-JVD-TRN-02502 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02502 |  | 2019-08-28 | 2
036909C-1021-PDS-1390-2124 | Piping Speciality Item - Datasheet Cone Filter - E-2100A-E Quench Water Inlet SRC-21001 | A | 2019-08-27 | IFR | OL1-2P03-2124 | MP | 2019-08-27 | 036909C-JVD-TRN-02503 | 036909C-JVD-TRN-02503 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-MP-02503 |  | 2019-08-28 | 2
036909C-1000-JSD-6000-0001 | Noise Control | 0 | 2019-08-26 | IMP | OL1-2L10-0001 | SE | 2019-08-27 | 036909C-JVD-TRN-02504 | 036909C-JVD-TRN-02504 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-SE-02504 |  | 2019-08-28 | 2
036909C-1011-SP-1554-1159 | Instrument Datasheets for Temperature Transmitters | A | 2019-08-26 | IFQ | OL1-2I20-1159 | IE | 2019-08-27 | 036909C-JVD-TRN-02506 | 036909C-JVD-TRN-02506 | IFR | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-IE-02506 |  | 2019-08-28 | 2
036909C-1000-MR-0570-0004 | Material Requisition For High Efficiency Internals For Columns Requisition For Purchase - Ex Doc Client Ref OL1-2M55-0075 | 0 | 2019-05-20 | IFP | OL1-2C13-245000 | PL | 2019-05-21 | 036909C-JVD-TRN-01706 | 036909C-JVD-TRN-01706 | IFR | 2019-06-05 | 2019-05-30 | R1-No comments | TPSK-LSPA1-T-PL-01706 | Ex Doc Client Ref OL1-2M55-0075 | 2019-05-23 | 2
036909C-1001-DW-1522-0031 | Instrument / Telecom Earthing Layout - Central Control Building | A | 2019-07-31 | IFR | OL1-2I48-1002 | IE | 2019-08-07 | 036909C-JVD-TRN-02367 | 036909C-JVD-TRN-02367 | IFR | 2019-08-30 | 2019-08-23 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02367 |  | 2019-08-07 | 1
036909C-1051-SP-0214-0002 | Mechanical Equipment Datasheet For Condensate Carbon Filter Package | 0 | 2019-08-09 | IFP | OL1-2M03-5115 | ME | 2019-08-09 | 036909C-JVD-TRN-02401 | 036909C-JVD-TRN-02401 | IFR | 2019-08-23 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1000-DW-1662-0002 | Low Voltage Protection Diagram | A | 2018-12-18 | IFR | OL1-2E19-0002 | EE | 2018-12-20 | 036909C-JVD-TRN-00555 | 036909C-JVD-TRN-00555 | IFR | 2019-01-04 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00555 |  | 2018-12-20 | 2
036909C-1000-JSS-4123-0001 | Diesel Engine Generator | 0 | 2018-09-20 | IMP | OL1-2R05-0017 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | 2018-11-05 | 3
036909C-1000-JSD-1900-0001 | Fire Fighting And Fire Protection | 0 | 2019-07-03 | IMP | OL1-2L01-0001 | SE | 2019-07-04 | 036909C-JVD-TRN-02079 | 036909C-JVD-TRN-02079 | IFR | 2019-07-19 |  | Transmitted | TPSK-LSPA1-T-SE-02079 |  | 2019-07-05 | 2
036909C-1027-SP-1681-0002 | MECHANICAL EQUIPMENT DATASHEET FOR REGEN GAS ELECTRIC HEATER | A | 2019-04-15 | IFQ | OL1-2M03-2730 | ME | 2019-04-18 | 036909C-JVD-TRN-01410 | 036909C-JVD-TRN-01410 | IFR | 2019-05-02 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01410 |  | 2019-04-19 | 2
036909C-105F-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5F HP & POLYOLEFINS FLARES UNIT | C | 2019-05-06 | IFR | OL1-2F30-0006 | FF | 2019-05-08 | 036909C-JVD-TRN-01612 | 036909C-JVD-TRN-01612, KLOC-TPSK-VSAFE-T-00008 | IFR | 2019-05-22 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-01612 |  | 2019-05-09 | 2
036909C-105F-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5F HP & POLYOLEFINS FLARES UNIT | A | 2019-04-05 | IFR | OL1-2F30-0006 | FF | 2019-04-08 | 036909C-JVD-TRN-01270 | 036909C-JVD-TRN-01270, KLOC-TPSK-VSAFE-T-00003 | IFR | 2019-04-22 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01270 |  | 2019-04-08 | 2
036909C-105F-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5F HP & POLYOLEFINS FLARES UNIT | B | 2019-04-25 | IFR | OL1-2F30-0006 | FF | 2019-04-30 | 036909C-JVD-TRN-01519 | 036909C-JVD-TRN-01519, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-05-14 |  | Transmitted | TPSK-LSPA1-T-FF-01519 |  | 2019-05-02 | 2
036909C-1000-MR-1681-0001 | Material Requisition For Electric Heater | A | 2019-04-15 | IFQ | OL1-2C13-700000 | PL | 2019-04-18 | 036909C-JVD-TRN-01409 | 036909C-JVD-TRN-01409 | IFR | 2019-05-02 | 2019-05-30 | R2-Comments as noted | TPSK-LSPA1-T-PL-01409 |  | 2019-04-18 | 2
036909C-1000-MR-0570-0004 | Material Requisition For MD Trays For Columns Requisition For Inquiry | A | 2018-10-31 | IFQ | OL1-2M55-0075 | ME | 2018-11-07 | 036909C-JVD-TRN-00278 | 036909C-JVD-TRN-00278 | IFR | 2018-11-21 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00278 |  | 2018-11-07 | 2
036909C-1000-MR-0570-0004 | Material Requisition for High Efficiency Internals for Columns | B | 2018-11-12 | IMP | OL1-2M55-0075 | ME | 2018-11-14 | 036909C-JVD-TRN-00314 | 036909C-JVD-TRN-00314 | IFR | 2018-11-29 | 2019-02-08 | R1-No comments | TPSK-LSPA1-T-ME-00314 | Closure to comments for document OL1-2M07-0075_A sent by email TPSK-LSPA1-E-00194_21/05/2019 | 2018-11-14 | 2
036909C-1000-DW-1933-0001 | Overall Firewater Network Drawing | 0 | 2019-07-16 | IMP | OL1-2L40-1000 | SE | 2019-07-17 | 036909C-JVD-TRN-02172 | 036909C-JVD-TRN-02172 | IFR | 2019-08-01 | 2019-08-23 | R1-No comments | TPSK-LSPA1-T-SE-02172 |  | 2019-07-17 | 2
036909C-105U-DW-0053-0001 | Detail Key Plan - Zone 5U - Utilities | B | 2019-07-19 | IBD | OL1-2P06-0035 | MP | 2019-07-23 | 036909C-JVD-TRN-02242 | 036909C-JVD-TRN-02242 | IFR | 2019-08-07 | 2019-08-23 | R1-No comments | TPSK-LSPA1-T-MP-02242 |  | 2019-07-24 | 2
036909C-105T-DW-0053-0001 | Detail Key Plan - Zone 5T - Cooling Water Unit | B | 2019-07-19 | IBD | OL1-2P06-0034 | MP | 2019-07-23 | 036909C-JVD-TRN-02242 | 036909C-JVD-TRN-02242 | IFR | 2019-08-07 | 2019-08-23 | R1-No comments | TPSK-LSPA1-T-MP-02242 |  | 2019-07-24 | 2
036909C-102E-DW-0053-0001 | Detail Key Plan - Zone 2E - Cracked Gas Compressor | B | 2019-07-19 | IBD | OL1-2P06-0030 | MP | 2019-07-23 | 036909C-JVD-TRN-02242 | 036909C-JVD-TRN-02242 | IFR | 2019-08-07 | 2019-08-23 | R1-No comments | TPSK-LSPA1-T-MP-02242 |  | 2019-07-24 | 2
036909C-102C-DW-0053-0001 | Detail Key Plan - Zone 2C - Hot Fractionation-GHU Unit | B | 2019-07-19 | IBD | OL1-2P06-0028 | MP | 2019-07-23 | 036909C-JVD-TRN-02242 | 036909C-JVD-TRN-02242 | IFR | 2019-08-07 | 2019-08-23 | R1-No comments | TPSK-LSPA1-T-MP-02242 |  | 2019-07-24 | 2
036909C-102B-DW-0053-0001 | Detail Key Plan - Zone 2B - C3 Hydrogenation | B | 2019-07-19 | IBD | OL1-2P06-0027 | MP | 2019-07-23 | 036909C-JVD-TRN-02242 | 036909C-JVD-TRN-02242 | IFR | 2019-08-07 | 2019-08-23 | R1-No comments | TPSK-LSPA1-T-MP-02242 |  | 2019-07-24 | 2
036909C-102A-DW-0053-0001 | Detail Key Plan - Zone 2A - Quench | B | 2019-07-19 | IBD | OL1-2P06-0026 | MP | 2019-07-23 | 036909C-JVD-TRN-02242 | 036909C-JVD-TRN-02242 | IFR | 2019-08-07 | 2019-08-23 | R1-No comments | TPSK-LSPA1-T-MP-02242 |  | 2019-07-24 | 2
036909C-101B-DW-0053-0001 | Detail Key Plan - Zone 1B - Furnaces Utilities | B | 2019-07-19 | IBD | OL1-2P06-0025 | MP | 2019-07-23 | 036909C-JVD-TRN-02242 | 036909C-JVD-TRN-02242 | IFR | 2019-08-07 | 2019-08-23 | R1-No comments | TPSK-LSPA1-T-MP-02242 |  | 2019-07-24 | 2
036909C-101A-DW-0053-0001 | Detail Key Plan - Zone 1A - Furnaces | B | 2019-07-19 | IBD | OL1-2P06-0024 | MP | 2019-07-23 | 036909C-JVD-TRN-02242 | 036909C-JVD-TRN-02242 | IFR | 2019-08-07 | 2019-08-23 | R1-No comments | TPSK-LSPA1-T-MP-02242 |  | 2019-07-24 | 2
036909C-1056-PDS-2500-5676 | Process Equipment Datasheet - 10-TK-5676 - Oily Sludge Tank | D | 2019-08-07 | IFD | OL1-2G30-5676 | PE | 2019-08-07 | 036909C-JVD-TRN-02377 | 036909C-JVD-TRN-02377 | IFR | 2019-08-22 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02377 |  | 2019-08-08 | 2
036909C-1056-PDS-2500-5675 | Process Equipment Datasheet - 10-TK-5675 A-B - Slop Oil Tanks | D | 2019-08-01 | IFD | OL1-2G30-5675 | PE | 2019-08-07 | 036909C-JVD-TRN-02377 | 036909C-JVD-TRN-02377 | IFR | 2019-08-22 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02377 |  | 2019-08-08 | 2
036909C-1056-PDS-0900-5643 | Process Equipment Datasheet - 10-P-5642 A-B - Cooling Water BD Basin Pumps | D | 2019-08-01 | IFD | OL1-2G30-5643 | PE | 2019-08-07 | 036909C-JVD-TRN-02377 | 036909C-JVD-TRN-02377 | IFR | 2019-08-22 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02377 |  | 2019-08-08 | 2
036909C-1056-PDS-0900-5652 | Process Equipment Datasheet - 10-P-5653 - Bio Equalization Pit Sludge Pump | C | 2019-08-07 | IFD | OL1-2G30-5652 | PE | 2019-08-07 | 036909C-JVD-TRN-02377 | 036909C-JVD-TRN-02377 | IFR | 2019-08-22 | 2019-08-27 | R1-No comments | TPSK-LSPA1-T-PE-02377 |  | 2019-08-08 | 2
036909C-1024-SP-1513-2402 | Instrument Interlock Descriptions Area 24 - Dehydration - Regen - Deprop - C2 Hydrog | B | 2019-07-25 | IBD | OL1-2G50-2402 | PE | 2019-07-30 | 036909C-JVD-TRN-02289 | 036909C-JVD-TRN-02289 | IFR | 2019-08-14 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-02289 |  | 2019-07-31 | 2
036909C-100P-DW-0053-0001 | Detail Key Plan - Zone 0P - Main Pipe Rack | B | 2019-07-19 | IBD | OL1-2P06-0022 | MP | 2019-07-23 | 036909C-JVD-TRN-02242 | 036909C-JVD-TRN-02242 | IFR | 2019-08-07 | 2019-08-23 | R1-No comments | TPSK-LSPA1-T-MP-02242 |  | 2019-07-24 | 2
036909C-1000-DW-0053-0001 | General Key Plan | B | 2019-07-19 | IBD | OL1-2P06-0020 | MP | 2019-07-23 | 036909C-JVD-TRN-02242 | 036909C-JVD-TRN-02242 | IFR | 2019-08-07 | 2019-08-23 | R2-Comments as noted | TPSK-LSPA1-T-MP-02242 |  | 2019-07-24 | 2
036909C-1022-PDS-1390-2215 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2266 A-B - ILK-22004 | A | 2019-07-18 | IFR | OL1-2P03-2215 | MP | 2019-07-23 | 036909C-JVD-TRN-02252 | 036909C-JVD-TRN-02252 | IFR | 2019-08-07 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-MP-02252 |  | 2019-07-24 | 2
036909C-1022-PDS-1390-2213 | Piping Specialty Item - Datasheet - Y-Type Filter - C-2200 Heavy Wash Oil - SRY-22002 | A | 2019-07-18 | IFR | OL1-2P03-2213 | MP | 2019-07-23 | 036909C-JVD-TRN-02250 | 036909C-JVD-TRN-02250 | IFR | 2019-08-07 | 2019-08-27 | R2-Comments as noted | TPSK-LSPA1-T-MP-02250 |  | 2019-07-24 | 2
036909C-1000-JSS-1545-0001 | Job Supply Specification For Safety Relief Valves & Rupture Disks | A | 2019-06-21 | IFQ | OL1-2I92-0701 | IE | 2019-08-08 | 036909C-JVD-TRN-02394 | 036909C-JVD-TRN-02394 | IFA | 2019-08-23 | 2019-08-22 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02394 |  | 2019-08-09 | 1
036909C-105U-DW-1841-0001-002 | Steel for Pipe Rack 10-PRK-5U01 - Plans | A | 2019-08-15 | IFR | OL1-2K32-8281 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0002-012 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Column Details | A | 2019-08-15 | IFR | OL1-2K31-0359 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1841-0001-001 | Steel for Pipe Rack 10-PRK-5U01 - Plans | A | 2019-08-15 | IFR | OL1-2K32-1080 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0002-015 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Steel Bracing Details | A | 2019-08-15 | IFR | OL1-2K31-0362 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1841-0001-003 | Steel for Pipe Rack 10-PRK-5U01 - Elevations | A | 2019-08-15 | IFR | OL1-2K32-8282 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0002-011 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Column Details | A | 2019-08-15 | IFR | OL1-2K31-0358 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0002-013 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Corbel Details | A | 2019-08-15 | IFR | OL1-2K31-0360 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0002-010 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Column Details | A | 2019-08-15 | IFR | OL1-2K31-0357 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0002-008 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Beam Details | A | 2019-08-15 | IFR | OL1-2K31-0355 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0002-005 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Beam Details | A | 2019-08-15 | IFR | OL1-2K31-0352 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0002-004 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Elevations | A | 2019-08-15 | IFR | OL1-2K31-0351 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0002-002 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Plans | A | 2019-08-15 | IFR | OL1-2K31-0349 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0002-003 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Plans | A | 2019-08-15 | IFR | OL1-2K31-0350 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0002-009 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Beam Details | A | 2019-08-15 | IFR | OL1-2K31-0356 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0002-007 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Beams Details | A | 2019-08-15 | IFR | OL1-2K31-0354 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0002-006 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Beam Details | A | 2019-08-15 | IFR | OL1-2K31-0353 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0002-001 | Precast Concrete of Pipe Rack 10-PRK-5U01 - 3D View | A | 2019-08-15 | IFR | OL1-2K31-1180 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0001-001 | Foundation Plan and Details of Pipe Rack 10-PRK-5U01 (Formwork & Reinforcement) | A | 2019-08-15 | IFR | OL1-2K31-1160 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0001-003 | Foundation Details for Pipe Rack 10-PRK-5U01 (Formwork & Reinforcement) | A | 2019-08-15 | IFR | OL1-2K31-0347 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105F-DW-1743-0012 | Foundation for 10-D-5553 | A | 2019-08-21 | IFR | OL1-2K31-0345 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0001-002 | Foundation Details for Pipe Rack 10-PRK-5U01 (Formwork & Reinforcement) | A | 2019-08-15 | IFR | OL1-2K31-0346 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-105U-DW-1741-0001-004 | Foundation Details for Piperack 10-PRK-5U01 (Formwork & Reinforcement) | A | 2019-08-15 | IFR | OL1-2K31-0348 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02493 |  | 2019-08-27 | 2
036909C-1001-DW-2058-0001-03 | Operation Tool Room - Architectural Isometric Views | B | 2019-08-22 | IFR | OL1-2K30-0042 | CV | 2019-08-26 | 036909C-JVD-TRN-02484 | 036909C-JVD-TRN-02484 | IFA | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02484 |  | 2019-08-27 | 1
036909C-1012-ML-210 | Furnace Section HAZOP Report | B | 2019-08-21 | IFD | OL1-2S95-0210 | ES | 2019-08-26 | 036909C-JVD-TRN-02490 | 036909C-JVD-TRN-02490 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-ES-02490 |  | 2019-08-27 | 2
036909C-1001-DW-2054-0003 | Gatehouse A - Architectural Plans Elevations Sections And Schedules | B | 2019-08-22 | IFR | OL1-2K30-0038 | CV | 2019-08-26 | 036909C-JVD-TRN-02484 | 036909C-JVD-TRN-02484 | IFA | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02484 |  | 2019-08-27 | 1
036909C-1012-ML-230 | Furnace Section SIL Classification Report | B | 2019-08-05 | IFD | OL1-2S95-0230 | ES | 2019-08-26 | 036909C-JVD-TRN-02490 | 036909C-JVD-TRN-02490 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-ES-02490 |  | 2019-08-27 | 2
036909C-1001-DW-2058-0001-02 | Operation Tool Room - Architectural Elevations And Sections | B | 2019-08-22 | IFR | OL1-2K30-0041 | CV | 2019-08-26 | 036909C-JVD-TRN-02484 | 036909C-JVD-TRN-02484 | IFA | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02484 |  | 2019-08-27 | 1
036909C-1001-DW-2058-0001-01 | Operation Tool Room - Architectural Plans And Schedules | B | 2019-08-22 | IFR | OL1-2K30-0040 | CV | 2019-08-26 | 036909C-JVD-TRN-02484 | 036909C-JVD-TRN-02484 | IFA | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02484 |  | 2019-08-27 | 1
036909C-1000-SP-0340-0001 | Particular Technical Specification For Sluice Gates & Screens | A | 2019-08-23 | IFQ | OL1-2C13-331000-ATT2 | ME | 2019-08-27 | 036909C-JVD-TRN-INTERNAL-00416 | 036909C-JVD-TRN-02495 | IFI | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02495 |  | 2019-08-27
036909C-1000-MS-1693-0001 | Job Specification For Electrical Motor Solo Run | A | 2019-08-22 | IFR | OL1-2O71-0019 | PE | 2019-08-23 | 036909C-JVD-TRN-02482 | 036909C-JVD-TRN-02482 | IFR | 2019-09-03 |  | Transmitted | TPSK-LSPA1-T-PE-02482 |  | 2019-08-26 | 2
036909C-1000-SR-0340-0001 | Scope of Supply for Sluice Gates & Screens | A | 2019-08-23 | IFQ | OL1-2C13-331000-ATT1 | ME | 2019-08-27 | 036909C-JVD-TRN-INTERNAL-00416 | 036909C-JVD-TRN-02495 | IFI | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-CV-02495 |  | 2019-08-27
036909C-1000-NM-0014-0001 | Flare Load Summary | B | 2019-08-20 | IFR | OL1-2G22-0001 | PE | 2019-08-26 | 036909C-JVD-TRN-02492 | 036909C-JVD-TRN-02492 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-PE-02492 |  | 2019-08-27 | 2
036909C-1000-MR-0340-0001 | Material Requisition for Sluice Gates & Screens | A | 2019-08-23 | IFQ | OL1-2C13-331000 | PL | 2019-08-26 | 036909C-JVD-TRN-02483 | 036909C-JVD-TRN-02483 | IFR | 2019-09-09 |  | Transmitted | TPSK-LSPA1-T-PL-02483 |  | 2019-08-26 | 2
036909C-1000-JSD-3400-0001 | Air Conditioning Ventilating And Ducting Design | 1 | 2019-08-22 | IMP | OL1-2E05-0020 | EE | 2019-08-26 | 036909C-JVD-TRN-02487 | 036909C-JVD-TRN-02487 | IFR | 2019-09-10 |  | Transmitted | TPSK-LSPA1-T-EE-02487 |  | 2019-08-27 | 2
036909C-105U-DW-1572-0014 | Instr. Main Cable Routing Utilities | A | 2019-08-05 | IFR | OL1-2I34-0014 | IE | 2019-08-06 | 036909C-JVD-TRN-02363 | 036909C-JVD-TRN-02363 | IFA | 2019-08-21 | 2019-08-22 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02363 |  | 2019-08-07 | 1
036909C-103S-DW-1572-0005 | Instrument Main Cable Routing Area Sub C & FAR C | A | 2019-08-05 | IFR | OL1-2I34-0005 | IE | 2019-08-06 | 036909C-JVD-TRN-02363 | 036909C-JVD-TRN-02363 | IFA | 2019-08-21 | 2019-08-22 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02363 |  | 2019-08-07 | 1
036909C-100S-DW-1572-0004 | Instrument Main Cable Routing Area SuB E & FAR E | A | 2019-08-05 | IFR | OL1-2I34-0004 | IE | 2019-08-06 | 036909C-JVD-TRN-02362 | 036909C-JVD-TRN-02362 | IFA | 2019-08-21 | 2019-08-22 | A3-Approved with comments, re-submit for review. | 2344-TPSK-LSPA1-T-IE-02362 |  | 2019-08-07 | 1
036909C-103A-DW-1622-0101 | Electrical Cable Routing Layout - Zone 3A Butadiene Extraction Unit | A | 2019-07-29 | IFR | OL1-2E31-0016 | EE | 2019-07-29 | 036909C-JVD-TRN-02272 | 036909C-JVD-TRN-02272 | IFR | 2019-08-12 | 2019-08-22 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02272 |  | 2019-07-30 | 1
036909C-1012-ML-230 | Furnace Section SIL Classification Report | A | 2019-03-21 | IFR | OL1-2S95-0230 | ES | 2019-03-25 | 036909C-JVD-TRN-01146 | 036909C-JVD-TRN-01146 | IFR | 2019-04-09 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-ES-01146 |  | 2019-03-26 | 2
036909C-1000-NM-0014-0001 | Flare Load Summary | A | 2018-10-23 | IFR | OL1-2G22-0001 | PE | 2018-10-25 | 036909C-JVD-TRN-00229 | 036909C-JVD-TRN-00229 | IFR | 2018-11-08 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00229 |  | 2018-10-25 | 2
036909C-100S-DW-1625-0001 | Substation E Equipment Layout | A | 2019-03-28 | IFR | OL1-2E20-0001 | EE | 2019-04-01 | 036909C-JVD-TRN-01212 | 036909C-JVD-TRN-01213, 036909C-JVD-TRN-01212, ROC-TPSK-CECO-T-00033 | IFA | 2019-04-16 | 2019-06-04 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01212 |  | 2019-04-02 | 1
036909C-1000-JSD-3400-0001 | Air Conditioning Ventilating And Ducting Design - Ex Document Client Reference: OL1-2H03-0001 - | 0 | 2019-01-02 | IMP | OL1-2E05-0020 | EE | 2019-01-07 | 036909C-JVD-TRN-00585 | 036909C-JVD-TRN-00585, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-01-15 | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-EE-00585 | Ex Document Client Reference: OL1-2H03-0001 | 2019-01-07 | 2
036909C-1000-JSD-3400-0001 | Air Conditioning Ventilating And Ducting Design - For Next Revision See Document OL1-2E05-0020 | A | 2018-10-12 | IFR | OL1-2E05-0020 | EE | 2018-10-12 | 036909C-JVD-TRN-00165 | 036909C-JVD-TRN-00165 | IFR | 2018-10-26 | 2018-10-26 | R2-Comments as noted | TPSK-LSPA1-T-EE-00165 | For Next Revision See Document OL1-2E05-0020 | 2018-10-15 | 2
036909C-1001-DW-2054-0001-02 | Gatehouse A - Architectural Elevations And Sections | A | 2019-03-04 | IFR | OL1-2K30-0031 | CV | 2019-03-14 | 036909C-JVD-TRN-01064 | 036909C-JVD-TRN-01064, ROC-TPSK-CECO-T-00041 | IFA | 2019-03-29 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSL-LSPA1-T-CV-01064 |  | 2019-03-15 | 1
036909C-1000-NM-1900-0001 | Bill of Material for Firefighting and Safety Equipment | A | 2019-07-19 | IFR | OL1-2L40-0001 | SE | 2019-07-22 | 036909C-JVD-TRN-02205 | 036909C-JVD-TRN-02205 | IFR | 2019-08-05 | 2019-08-23 | R2-Comments as noted | TPSK-LSPA1-T-SE-02205 |  | 2019-07-23 | 2
036909C-1011-PDS-1390-1111 | Piping Specialty Item Datasheet - Stop Check Valve - SP-11011 | B | 2019-07-24 | IFD | OL1-2P03-1111 | MP | 2019-07-30 | 036909C-JVD-TRN-02292 | 036909C-JVD-TRN-02292 | IFR | 2019-08-14 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-MP-02292 |  | 2019-07-31 | 2
036909C-1011-PDS-1390-1105 | Piping Specialty Item Datasheet - T-Type Filter - Fuel Gas Line - SRT-11002 | B | 2019-07-24 | IFD | OL1-2P03-1105 | MP | 2019-07-30 | 036909C-JVD-TRN-02292 | 036909C-JVD-TRN-02292 | IFR | 2019-08-14 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-MP-02292 |  | 2019-07-31 | 2
036909C-1012-PDS-1390-1252 | Piping Specialty Item Datasheet - Flexible Hose - FLX-12001-16001 | B | 2019-07-24 | IFD | OL1-2P03-1252 | MP | 2019-07-30 | 036909C-JVD-TRN-02292 | 036909C-JVD-TRN-02292 | IFR | 2019-08-14 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-MP-02292 |  | 2019-07-31 | 2
036909C-1012-PDS-1390-1214 | Piping Specialty Item Datasheet - Vent Silencer - Start-Up - SP-12014-16014 | B | 2019-07-24 | IFD | OL1-2P03-1214 | MP | 2019-07-30 | 036909C-JVD-TRN-02292 | 036909C-JVD-TRN-02292 | IFR | 2019-08-14 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-MP-02292 |  | 2019-07-31 | 2
036909C-1012-PDS-1390-1213 | Piping Specialty Item Datasheet - Vent Silencer - PSV-1244 Outlet - SP-12013-16013 | B | 2019-07-24 | IFD | OL1-2P03-1213 | MP | 2019-07-30 | 036909C-JVD-TRN-02292 | 036909C-JVD-TRN-02292 | IFR | 2019-08-14 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-MP-02292 |  | 2019-07-31 | 2
036909C-1012-PDS-1390-1211 | Piping Specialty Item Datasheet - Stop Check Valve - SP-12011-16011 | B | 2019-07-24 | IFD | OL1-2P03-1211 | MP | 2019-07-30 | 036909C-JVD-TRN-02292 | 036909C-JVD-TRN-02292 | IFR | 2019-08-14 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-MP-02292 |  | 2019-07-31 | 2
036909C-1012-PDS-1390-1205 | Piping Specialty Item Datasheet - T-Type Filter - Fuel Gas Line - SRT-12002-16002 | B | 2019-07-24 | IFD | OL1-2P03-1205 | MP | 2019-07-30 | 036909C-JVD-TRN-02292 | 036909C-JVD-TRN-02292 | IFR | 2019-08-14 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-MP-02292 |  | 2019-07-31 | 2
036909C-1012-PDS-1390-1203 | Piping Specialty Item Datasheet - Exhaust Head - SP-12003-16003 | B | 2019-07-24 | IFD | OL1-2P03-1203 | MP | 2019-07-30 | 036909C-JVD-TRN-02292 | 036909C-JVD-TRN-02292 | IFR | 2019-08-14 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-MP-02292 |  | 2019-07-31 | 2
036909C-1011-PDS-1390-1152 | Piping Specialty Item Datasheet - Flexible Hose - FLX-11001 | B | 2019-07-24 | IFD | OL1-2P03-1152 | MP | 2019-07-30 | 036909C-JVD-TRN-02292 | 036909C-JVD-TRN-02292 | IFR | 2019-08-14 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-MP-02292 |  | 2019-07-31 | 2
036909C-1011-PDS-1390-1114 | Piping Specialty Item Datasheet - Vent Silencer - Start-Up - SP-11014 | B | 2019-07-24 | IFD | OL1-2P03-1114 | MP | 2019-07-30 | 036909C-JVD-TRN-02292 | 036909C-JVD-TRN-02292 | IFR | 2019-08-14 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-MP-02292 |  | 2019-07-30 | 2
036909C-1011-PDS-1390-1113 | Piping Specialty Item Datasheet - Vent Silencer - PSV-1144 Outlet - SP-11013 | B | 2019-07-24 | IFD | OL1-2P03-1113 | MP | 2019-07-30 | 036909C-JVD-TRN-02292 | 036909C-JVD-TRN-02292 | IFR | 2019-08-14 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-MP-02292 |  | 2019-07-31 | 2
036909C-1011-PDS-1390-1103 | Piping Specialty Item Datasheet - Exhaust Head - SP-11003 | B | 2019-07-24 | IFD | OL1-2P03-1103 | MP | 2019-07-30 | 036909C-JVD-TRN-02292 | 036909C-JVD-TRN-02292 | IFR | 2019-08-14 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-MP-02292 |  | 2019-07-31 | 2
036909C-1053-PDS-1390-5304 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-5360 A-B-C Discharge - SCV-53001 | A | 2019-07-23 | IFR | OL1-2P03-5304 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1053-PDS-1390-5303 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-5350 A-H Discharge - SCV-53004 | A | 2019-07-23 | IFR | OL1-2P03-5303 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5147 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-5100 A-B-C Discharge - SCV-51001 | A | 2019-07-23 | IFR | OL1-2P03-5147 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5146 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-5102 A-B Discharge - SCV-51004 | A | 2019-07-23 | IFR | OL1-2P03-5146 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5120 | Piping Specialty Item - Datasheet - T-Type Filter - P-5140 A-B Suction - SRT-51015 | A | 2019-07-24 | IFR | OL1-2P03-5120 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5118 | Piping Specialty Item - Datasheet - T-Type Filter - P-5110 A-B Suction - SRT-51027 | A | 2019-07-24 | IFR | OL1-2P03-5118 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5117 | Piping Specialty Item - Datasheet - T-Type Filter - P-5120 A-B Suction - SRT-51022 | A | 2019-07-24 | IFR | OL1-2P03-5117 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5116 | Piping Specialty Item - Datasheet - T-Type Filter - P-5112 A-B Suction - SRT-51023 | A | 2019-07-24 | IFR | OL1-2P03-5116 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5115 | Piping Specialty Item - Datasheet - T-Type Filter - P-5102 A-B Suction - SRT-51016 | A | 2019-07-24 | IFR | OL1-2P03-5115 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5113 | Piping Specialty Item - Datasheet - T-Type Filter - P-5100 A-B-C Suction - SRT-51018 | A | 2019-07-24 | IFR | OL1-2P03-5113 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5112 | Piping Specialty Item - Datasheet - T-Type Filter - HP BFW to SHP-HP Steam Letdown - SRT-51004 | A | 2019-07-24 | IFR | OL1-2P03-5112 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5104 | Piping Specialty Item - Datasheet - T-Type Filter - VLP BFW to LP LS1 - VLP LS2 Steam Letdown - SRT-51021 | A | 2019-07-24 | IFR | OL1-2P03-5104 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5103 | Piping Specialty Item - Datasheet - T-Type Filter - HP BFW to MP-LP LS1 Steam Letdown - SRT-51003 | A | 2019-07-24 | IFR | OL1-2P03-5103 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5102 | Piping Specialty Item - Datasheet - T-Type Filter - HP BFW to HP-MP Steam Letdown - SRT-51002 | A | 2019-07-24 | IFR | OL1-2P03-5102 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5101 | Piping Specialty Item - Datasheet - T-Type Filter - HP BFW to SHP-HP Steam Letdown - SRT-51001 | A | 2019-07-24 | IFR | OL1-2P03-5101 | MP | 2019-08-01 | 036909C-JVD-TRN-02319 | 036909C-JVD-TRN-02319 | IFR | 2019-08-16 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-MP-02319 |  | 2019-08-05 | 2
036909C-1023-PDS-1390-2310 | Piping Specialty Item – Datasheet - Y-Type Filter - SRY-23001 | A | 2019-07-17 | IFR | OL1-2P03-2310 | MP | 2019-07-23 | 036909C-JVD-TRN-02252 | 036909C-JVD-TRN-02252 | IFR | 2019-08-07 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02252 |  | 2019-07-24 | 2
036909C-1022-PDS-1390-2209 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Looking Device - PSV-2235 A-B-C-D - IKL-22003 | A | 2019-07-18 | IFR | OL1-2P03-2209 | MP | 2019-07-23 | 036909C-JVD-TRN-02250 | 036909C-JVD-TRN-02250 | IFR | 2019-08-07 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02250 |  | 2019-07-24 | 2
036909C-1027-SP-1513-2701 | Complex Loop Narratives Area 27 GHU & C4-C5 HYDROG | B | 2019-08-06 | IBD | OL1-2I71-2701 | IE | 2019-08-06 | 036909C-JVD-TRN-02366 | 036909C-JVD-TRN-02366 | IFR | 2019-08-21 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-IE-02366 |  | 2019-08-07 | 2
036909C-1030-PDS-0500-3070 | Process Equipment Datasheet - 10-T-3070 - Direct Cooler Tower | C | 2019-07-25 | IFD | OL1-2G30-3070 | PE | 2019-07-25 | 036909C-JVD-TRN-02266 | 036909C-JVD-TRN-02266 | IFR | 2019-08-09 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PE-02266 |  | 2019-07-29 | 2
036909C-1030-PDS-0500-3030 | Process Equipment Datasheet - 10-T-3030 - After Washer | C | 2019-07-25 | IFD | OL1-2G30-3030 | PE | 2019-07-25 | 036909C-JVD-TRN-02266 | 036909C-JVD-TRN-02266 | IFR | 2019-08-09 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-02266 |  | 2019-07-29 | 2
036909C-1020-SP-1545-2001 | Instrument Datasheets for Pressure Safety Valve - Area 20 | A | 2019-07-23 | IFQ | OL1-2I20-2016 | IE | 2019-07-30 | 036909C-JVD-TRN-02291 | 036909C-JVD-TRN-02291 | IFI |  | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-IE-02291 |  | 2019-07-31 | 3
036909C-1019-SP-1545-1901 | Instrument Datasheets for Pressure Safety Valve - Area 19 | A | 2019-07-22 | IFI | OL1-2I20-1916 | IE | 2019-07-24 | 036909C-JVD-TRN-02258 | 036909C-JVD-TRN-02258 | IFI |  | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-IE-02258 |  | 2019-07-25 | 3
036909C-1023-SP-1545-2301 | Instrument Datasheets for Pressure Safety Valve - Area 23 | A | 2019-07-22 | IFI | OL1-2I20-2316 | IE | 2019-07-24 | 036909C-JVD-TRN-02258 | 036909C-JVD-TRN-02258 | IFI |  | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-IE-02258 |  | 2019-07-25 | 3
036909C-1022-SP-1513-2201 | Complex Loop Narratives Area 22 - Cracked Gas Compressor | B | 2019-07-24 | IBD | OL1-2I71-2201 | IE | 2019-07-30 | 036909C-JVD-TRN-02290 | 036909C-JVD-TRN-02290 | IFR | 2019-08-14 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-IE-02290 |  | 2019-07-31 | 2
036909C-1056-SP-0910-5643 | Mechanical Equipment Datasheet for Cooling Water BD Basin Pumps | B | 2019-07-29 | IFQ | OL1-2M03-5643 | ME | 2019-07-30 | 036909C-JVD-TRN-02295 | 036909C-JVD-TRN-02295 | IFR | 2019-08-14 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-02295 |  | 2019-07-31 | 2
036909C-1027-SP-0910-2764 | Mechanical Equipment Datasheet for C4_C5 Hydrog Recycle Pump | D | 2019-07-24 | IFQ | OL1-2M03-2764 | ME | 2019-07-30 | 036909C-JVD-TRN-02295 | 036909C-JVD-TRN-02295 | IFR | 2019-08-14 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-02295 |  | 2019-07-31 | 2
036909C-1027-SP-0910-2704 | Mechanical Equipment Datasheet for GHU-1 Recycle Pump | D | 2019-07-24 | IFQ | OL1-2M03-2704 | ME | 2019-07-30 | 036909C-JVD-TRN-02295 | 036909C-JVD-TRN-02295 | IFR | 2019-08-14 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-02295 |  | 2019-07-31 | 2
036909C-1026-SP-0910-2623 | Mechanical Equipment Datasheet for C3 Hydrog Recycle Pumps | D | 2019-07-24 | IFQ | OL1-2M03-2623 | ME | 2019-07-30 | 036909C-JVD-TRN-02295 | 036909C-JVD-TRN-02295 | IFR | 2019-08-14 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-02295 |  | 2019-07-31 | 2
036909C-1024-PDS-1390-2416 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2435 A-B-C-D - ILK-24008 | A | 2019-07-18 | IFR | OL1-2P03-2416 | MP | 2019-07-24 | 036909C-JVD-TRN-02259 | 036909C-JVD-TRN-02259 | IFR | 2019-08-08 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02259 |  | 2019-07-25 | 2
036909C-1024-PDS-1390-2411 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2428 A-B - ILK-24005 | A | 2019-07-18 | IFR | OL1-2P03-2411 | MP | 2019-07-24 | 036909C-JVD-TRN-02259 | 036909C-JVD-TRN-02259 | IFR | 2019-08-08 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02259 |  | 2019-07-25 | 2
036909C-1024-PDS-1390-2408 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2423 A-B-C - ILK-24004 | A | 2019-07-18 | IFR | OL1-2P03-2408 | MP | 2019-07-24 | 036909C-JVD-TRN-02259 | 036909C-JVD-TRN-02259 | IFR | 2019-08-08 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02259 |  | 2019-07-25 | 2
036909C-1024-PDS-1900-2407 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2418 A-B-C-D - ILK-24009 | A | 2019-07-18 | IFR | OL1-2P03-2407 | MP | 2019-07-24 | 036909C-JVD-TRN-02259 | 036909C-JVD-TRN-02259 | IFR | 2019-08-08 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02259 |  | 2019-07-25 | 2
036909C-1024-PDS-1390-2406 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2415 A-B - ILK-24007 | A | 2019-07-18 | IFR | OL1-2P03-2406 | MP | 2019-07-24 | 036909C-JVD-TRN-02259 | 036909C-JVD-TRN-02259 | IFR | 2019-08-08 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02259 |  | 2019-07-25 | 2
036909C-1024-PDS-1390-2405 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2414 A-B - ILK-24010 | A | 2019-07-18 | IFR | OL1-2P03-2405 | MP | 2019-07-24 | 036909C-JVD-TRN-02259 | 036909C-JVD-TRN-02259 | IFR | 2019-08-08 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-02259 |  | 2019-07-25 | 2
036909C-1026-SP-1545-2601 | Instrument Datasheets for Pressure Safety Valve - Area 26 | A | 2019-07-23 | IFQ | OL1-2I20-2616 | IE | 2019-07-30 | 036909C-JVD-TRN-02291 | 036909C-JVD-TRN-02291 | IFI |  | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-IE-02291 |  | 2019-07-31 | 3
036909C-1028-SP-1545-2801 | Instrument Datasheets for Pressure Safety Valve - Area 28 | A | 2019-07-23 | IFQ | OL1-2I20-2816 | IE | 2019-07-30 | 036909C-JVD-TRN-02291 | 036909C-JVD-TRN-02291 | IFI |  | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-IE-02291 |  | 2019-07-31 | 3
036909C-1011-SP-1553-1156 | Instrument Datasheets for Pressure Indicating Transmitters & Flow Indicating DP Transmitters | A | 2019-07-19 | IFR | OL1-2I20-1156 | IE | 2019-07-22 | 036909C-JVD-TRN-02222 | 036909C-JVD-TRN-02222 | IFR | 2019-08-06 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-IE-02222 |  | 2019-07-23 | 2
036909C-1011-SP-1546-1152 | Instrument Datasheets for Orifice Plate | A | 2019-07-17 | IFQ | OL1-2I20-1152 | IE | 2019-07-22 | 036909C-JVD-TRN-02217 | 036909C-JVD-TRN-02217 | IFR | 2019-08-06 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-IE-02217 |  | 2019-07-23 | 2
036909C-1026-SP-1513-2601 | Complex Loop Narratives Area 26 - Hot Fractionation | B | 2019-07-31 | IBD | OL1-2I71-2601 | IE | 2019-08-01 | 036909C-JVD-TRN-02318 | 036909C-JVD-TRN-02318 | IFR | 2019-08-16 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-IE-02318 |  | 2019-08-05 | 2
036909C-1026-SP-1513-2602 | Instrument Interlock Descriptions Area 26 - Hot Fractionation | B | 2019-07-30 | IBD | OL1-2G50-2602 | PE | 2019-07-30 | 036909C-JVD-TRN-02298 | 036909C-JVD-TRN-02298 | IFR | 2019-08-14 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-02298 |  | 2019-07-31 | 2
036909C-1026-DW-1514-2601 | Cause and Effect Diagram Area 26 - Hot Fractionation | B | 2019-07-30 | IBD | OL1-2G50-2601 | PE | 2019-07-30 | 036909C-JVD-TRN-02299 | 036909C-JVD-TRN-02299 | IFR | 2019-08-14 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-02299 |  | 2019-07-31 | 2
036909C-1051-TDS-0610-5107 | Mechanical Equipment Data Sheet - 10-E-5112 - Suspect Cond Flash Drum Vent Condenser | 0 | 2019-07-23 | IFP | OL1-2M03-5107 | ME | 2019-07-30 | 036909C-JVD-TRN-02293 | 036909C-JVD-TRN-02293 | IFR | 2019-08-14 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-ME-02293 |  | 2019-07-31 | 2
036909C-1052-SP-1513-5201 | Complex Loop Narratives Area 52 - Fuel System | B | 2019-08-02 | IBD | OL1-2I71-5201 | IE | 2019-08-05 | 036909C-JVD-TRN-02344 | 036909C-JVD-TRN-02344 | IFR | 2019-08-20 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-IE-02344 |  | 2019-08-07 | 2
036909C-1051-SP-1513-5101 | Complex Loop Narratives Area 51 BFW - Steam - Steam Condensate System | B | 2019-08-02 | IBD | OL1-2I71-5101 | IE | 2019-08-05 | 036909C-JVD-TRN-02344 | 036909C-JVD-TRN-02344 | IFR | 2019-08-20 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-IE-02344 |  | 2019-08-07 | 2
036909C-1029-SP-1513-2901 | Complex Loop Narratives Area 29 Ethylene Auxiliaries | B | 2019-08-05 | IBD | OL1-2I71-2901 | IE | 2019-08-05 | 036909C-JVD-TRN-02344 | 036909C-JVD-TRN-02344 | IFR | 2019-08-20 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-IE-02344 |  | 2019-08-07 | 2
036909C-1024-TDS-0630-2432 | Mechanical Equipment Data Sheet - 10-E-2432 - Regen Gas SHP Heater | 0 | 2019-08-02 | Issue for Purchase | OL1-2M03-2432 | ME | 2019-08-07 | 036909C-JVD-TRN-02379 | 036909C-JVD-TRN-02379 | IFR | 2019-08-22 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-02379 |  | 2019-08-08 | 2
036909C-1027-PDS-0500-2720 | Process Equipment Datasheet - 10-T-2720 - Rerun Tower | B | 2019-04-11 | IFD | OL1-2G30-2720 | PE | 2019-04-12 | 036909C-JVD-TRN-01340 | 036909C-JVD-TRN-01340 | IFR | 2019-04-29 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PE-01340 |  | 2019-04-15 | 2
036909C-1000-JSD-1501-0002 | General Design Rules For SmartPlant Instrumentation Setup | 1 | 2019-07-23 | IFE | OL1-2R06-0024 | IE | 2019-07-30 | 036909C-JVD-TRN-02286 | 036909C-JVD-TRN-02286 | IFR | 2019-08-14 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-IE-02286 |  | 2019-07-31 | 2
036909C-102C-DW-1572-0009 | Instrument Main Cable Routing Zone 2C Hot Fractionation-GHU Unit | A | 2019-08-06 | IFR | OL1-2I34-0009 | IE | 2019-08-08 | 036909C-JVD-TRN-02392 | 036909C-JVD-TRN-02392 | IFA | 2019-08-23 | 2019-08-22 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02392 |  | 2019-08-09 | 1
036909C-1000-SP-1562-0003 | Instrument Datasheets for CO- CO2 Analyzers | A | 2019-07-26 | IFQ | OL1-2I20-2804 | IE | 2019-07-30 | 036909C-JVD-TRN-02280 | 036909C-JVD-TRN-02280 | IFA | 2019-08-14 | 2019-08-21 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02280 |  | 2019-07-31 | 1
036909C-1000-SP-1563-0002 | Instrument Datasheets for Wobbe Index Analyzers | A | 2019-07-26 | IFQ | OL1-2I20-2803 | IE | 2019-07-30 | 036909C-JVD-TRN-02280 | 036909C-JVD-TRN-02280 | IFA | 2019-08-14 | 2019-08-21 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02280 |  | 2019-07-31 | 1
036909C-102E-DW-1744-0002-002 | Concrete Basin 10-PIT-5603 - Reinforcement | A | 2019-06-17 | IFR | OL1-2K31-3141 | CV | 2019-06-26 | 036909C-JVD-TRN-02004 | 036909C-JVD-TRN-02004 | IFA | 2019-07-11 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02004 |  | 2019-06-27 | 1
036909C-102E-DW-1744-0002-001 | Concrete Basin 10-PIT-5603 - Formwork | A | 2019-06-20 | IFR | OL1-2K31-3140 | CV | 2019-06-26 | 036909C-JVD-TRN-02004 | 036909C-JVD-TRN-02004 | IFA | 2019-07-11 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02004 |  | 2019-06-27 | 1
036909C-102B-DW-1744-0003-002 | Concrete Basin 10-PIT-2392 | A | 2019-06-07 | IFR | OL1-2K31-2641 | CV | 2019-06-26 | 036909C-JVD-TRN-02004 | 036909C-JVD-TRN-02004 | IFA | 2019-07-11 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02004 |  | 2019-06-27 | 1
036909C-102C-DW-1743-0030-001 | Foundation For 10-E-2702 | A | 2019-06-20 | IFR | OL1-2K31-0188 | CV | 2019-06-26 | 036909C-JVD-TRN-02004 | 036909C-JVD-TRN-02004 | IFA | 2019-07-11 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02004 |  | 2019-06-27 | 1
036909C-103S-DW-1625-0001 | Substation C Equipment Layout | A | 2019-03-28 | IFR | OL1-2E20-0002 | EE | 2019-04-01 | 036909C-JVD-TRN-01212 | 036909C-JVD-TRN-01213, 036909C-JVD-TRN-01212, ROC-TPSK-CECO-T-00033 | IFA | 2019-04-16 | 2019-05-07 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01212 |  | 2019-04-02 | 1
036909C-102B-DW-1744-0003-001 | Foundation for Basin 10-PIT-2392 | A | 2019-06-07 | IFR | OL1-2K31-2640 | CV | 2019-06-21 | 036909C-JVD-TRN-01958 | 036909C-JVD-TRN-01958 | IFA | 2019-07-08 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01958 |  | 2019-06-24 | 1
036909C-1000-MR-0910-0006 | Material Requisition For API 685 Sealless Pump | A | 2019-06-21 | IFQ | OL1-2C13-446000 | PL | 2019-07-01 | 036909C-JVD-TRN-02034 | 036909C-JVD-TRN-02034 | IFR | 2019-07-16 | 2019-07-16 | R2-Comments as noted | TPSK-LSPA1-T-PL-02034 |  | 2019-07-02 | 2
036909C-1000-STC-1790-0001 | Construction Standards For Reinforced Concrete Works | 1 | 2019-07-10 | IFC | OL1-2K20-0001 | CV | 2019-07-11 | 036909C-JVD-TRN-02136 | 036909C-JVD-TRN-02136 | IFA | 2019-07-26 |  | Transmitted | TPSK-LSPA1-T-CV-02136 |  | 2019-07-15 | 1
036909C-1000-MR-0214-0001 | Material Requisition For Condensate Carbon Filter Package | 0 | 2019-08-09 | IFP | OL1-2C13-151000 | PL | 2019-08-09 | 036909C-JVD-TRN-02402 | 036909C-JVD-TRN-02402 | IFR | 2019-08-23 | 2019-08-22 | Transmitted | TPSK-LSPA1-T-PL-02402 |  | 2019-08-14 | 2
036909C-1012-MR-0131-2014 | Material Requisition for Radiant Steel Panel | A | 2019-04-01 | IFQ | OL1-2C12-307000 | PL | 2019-04-02 | 036909C-JVD-TRN-01229 | 036909C-JVD-TRN-01229 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01229 | For next revision see client doc. n. OL1-2C12-307000 | 2019-04-03 | 3
036909C-1012-MR-0131-2014 | Material Requisition for Radiant Steel Panel - Ex Document Client Reference OL1-2C12-301000 | 0 | 2019-05-16 | IFP | OL1-2C12-307000 | PL | 2019-05-20 | 036909C-JVD-TRN-01699 | 036909C-JVD-TRN-01699 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01699 | Ex Document Client Reference OL1-2C12-301000 | 2019-05-21 | 3
036909C-1000-MR-2630-0003 | Material Requisition For Molecular And HG Sieves | B | 2019-07-19 | IFQ | OL1-2C18-263000 | PL | 2019-07-19 | 036909C-JVD-TRN-02196 | 036909C-JVD-TRN-02196 | IFR | 2019-08-05 | 2019-08-21 | R2-Comments as noted | TPSK-LSPA1-T-PL-02196 |  | 2019-07-22 | 2
036909C-1000-MR-1309-0001 | Material Requisition For Carbon Steel Underground Piping | 0 | 2019-08-08 | IFP | OL1-2C14-360001 | PL | 2019-08-12 | 036909C-JVD-TRN-02412 | 036909C-JVD-TRN-02412 | IFR | 2019-08-27 | 2019-08-21 | R2-Comments as noted | TPSK-LSPA1-T-PL-02412 |  | 2019-08-14 | 2
036909C-1000-MR-1329-0002 | Material Requisition For Underground Welded Carbon Steel Pipes | 0 | 2019-08-08 | IFP | OL1-2C14-365001 | PL | 2019-08-08 | 036909C-JVD-TRN-02388 | 036909C-JVD-TRN-02388 | IFR | 2019-08-23 | 2019-08-21 | R1-No comments | TPSK-LSPA1-T-PL-02388 |  | 2019-08-09 | 2
036909C-102E-DW-1622-0201 | Power Layout - Zone 2E - Key Plan | A | 2019-07-18 | IFR | OL1-2E32-0014 | EE | 2019-07-22 | 036909C-JVD-TRN-02225 | 036909C-JVD-TRN-02225 | IFA | 2019-08-06 | 2019-08-21 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02225 |  | 2019-07-23 | 1
036909C-102C-DW-1622-0201 | Power Layout - Zone 2C - Key Plan | A | 2019-07-25 | IFR | OL1-2E32-0012 | EE | 2019-07-26 | 036909C-JVD-TRN-02268 | 036909C-JVD-TRN-02268 | IFA | 2019-08-12 | 2019-08-21 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02268 |  | 2019-07-29 | 1
036909C-102A-DW-1743-0004-002 | Concrete Structure For 10-T-2040 - Reinforcement | A | 2019-06-20 | IFR | OL1-2K31-4581 | CV | 2019-06-28 | 036909C-JVD-TRN-02028 | 036909C-JVD-TRN-02028 | IFA | 2019-07-15 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02028 |  | 2019-07-01 | 1
036909C-102A-DW-1743-0004-001 | Concrete Structure For 10-T-2040 - Formwork | A | 2019-06-20 | IFR | OL1-2K31-4580 | CV | 2019-06-28 | 036909C-JVD-TRN-02028 | 036909C-JVD-TRN-02028 | IFA | 2019-07-15 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02028 |  | 2019-07-01 | 1
036909C-102D-DW-1743-0021-001 | Concrete Structure For 10-D-2880 And 10-D-2865 - Formworks | A | 2019-06-25 | IFR | OL1-2K31-0113 | CV | 2019-06-28 | 036909C-JVD-TRN-02028 | 036909C-JVD-TRN-02028 | IFA | 2019-07-15 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-02028 |  | 2019-07-01 | 1
036909C-1027-PDS-0851-2795 | Data Sheet For Vacuum Units -Multistage Ejectors- Rerun Tower Vacuum Package PK-2720 | A | 2019-08-02 | IFR | OL1-2G30-2795 | PE | 2019-08-02 | 036909C-JVD-TRN-02333 | 036909C-JVD-TRN-02333 | IFR | 2019-08-19 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-PE-02333 |  | 2019-08-05 | 2
036909C-102B-DW-1844-0003-001 | Steel Structures for Concrete Basin 10-PIT-2392 | A | 2019-06-07 | IFR | OL1-2K32-7520 | CV | 2019-06-21 | 036909C-JVD-TRN-01959 | 036909C-JVD-TRN-01959 | IFA | 2019-07-08 | 2019-08-20 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01959 |  | 2019-06-24 | 1
036909C-105W-DW-1622-0101 | Electrical Main Cable Routing Layout - Zone 5W Waste Water Treatment | A | 2019-07-29 | IFR | OL1-2E31-0009 | EE | 2019-07-29 | 036909C-JVD-TRN-02272 | 036909C-JVD-TRN-02272 | IFR | 2019-08-12 | 2019-08-22 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02272 |  | 2019-07-30 | 1
036909C-1024-SP-1513-2401 | Complex Loop Narratives Area 24 - Dehydration - Regen - Deprop - C2 Hydrog | B | 2019-07-25 | IBD | OL1-2I71-2401 | IE | 2019-07-30 | 036909C-JVD-TRN-02290 | 036909C-JVD-TRN-02290 | IFR | 2019-08-14 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-IE-02290 |  | 2019-07-31 | 2
036909C-1000-SP-1563-0003 | Instrument Datasheets for TOC - COD Analyzers | A | 2019-07-26 | IFQ | OL1-2I20-2902 | IE | 2019-07-30 | 036909C-JVD-TRN-02280 | 036909C-JVD-TRN-02280 | IFA | 2019-08-14 | 2019-08-20 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02280 |  | 2019-07-31 | 1
036909C-102D-DW-1743-0009-001 | Foundation For 10-D-2525 | A | 2019-05-30 | IFR | OL1-2K31-0111 | CV | 2019-06-19 | 036909C-JVD-TRN-01926 | 036909C-JVD-TRN-01926 | IFA | 2019-07-04 | 2019-08-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01926 |  | 2019-06-20 | 1
036909C-105W-DW-1743-0001-001 | Foundation For 10-TK-5640 | A | 2019-06-18 | IFR | OL1-2K31-0278 SH001 | CV | 2019-06-19 | 036909C-JVD-TRN-01923 | 036909C-JVD-TRN-01923 | IFR | 2019-07-03 | 2019-08-21 | R2-Comments as noted | TPSK-LSPA1-T-CV-01923 |  | 2019-06-20 | 2
036909C-105U-DW-1743-0001 | Foundation For 10-D-5500 | A | 2019-06-18 | IFR | OL1-2K31-0268 | CV | 2019-06-19 | 036909C-JVD-TRN-01923 | 036909C-JVD-TRN-01923 | IFR | 2019-07-03 | 2019-08-21 | R2-Comments as noted | TPSK-LSPA1-T-CV-01923 |  | 2019-06-20 | 2
036909C-105U-CN-1733-0010 | Calculation Note For Foundation 0F 10-TK-5120 | A | 2019-06-14 | IFR | OL1-2K13-0282 | CV | 2019-06-17 | 036909C-JVD-TRN-01901 | 036909C-JVD-TRN-01901 | IFR | 2019-07-01 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01901 |  | 2019-06-18 | 1
036909C-105U-CN-1733-0009 | Calculation Note For Foundation 10-TK-5110 | A | 2019-06-14 | IFR | OL1-2K13-0281 | CV | 2019-06-17 | 036909C-JVD-TRN-01901 | 036909C-JVD-TRN-01901 | IFR | 2019-07-01 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01901 |  | 2019-06-18 | 1
036909C-103A-CN-1733-0011 | Calculation Note For Foundation OF 10-T-3080 | A | 2019-06-14 | IFR | OL1-2K13-0210 | CV | 2019-06-17 | 036909C-JVD-TRN-01901 | 036909C-JVD-TRN-01901 | IFR | 2019-07-01 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01901 |  | 2019-06-18 | 1
036909C-103A-CN-1733-0009 | Calculation Note For Foundation Of 10-T-3050 | A | 2019-06-14 | IFR | OL1-2K13-0208 | CV | 2019-06-17 | 036909C-JVD-TRN-01901 | 036909C-JVD-TRN-01901 | IFR | 2019-07-01 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01901 |  | 2019-06-18 | 1
036909C-103A-CN-1733-0008 | Calculation Note For Foundation Of 10-T-3030 | A | 2019-06-14 | IFR | OL1-2K13-0207 | CV | 2019-06-17 | 036909C-JVD-TRN-01901 | 036909C-JVD-TRN-01901 | IFR | 2019-07-01 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01901 |  | 2019-06-18 | 1
036909C-103A-CN-1733-0004 | Calculation Note For Foundation Of 10-T-3000 | A | 2019-06-14 | IFR | OL1-2K13-0203 | CV | 2019-06-17 | 036909C-JVD-TRN-01901 | 036909C-JVD-TRN-01901 | IFR | 2019-07-01 | 2019-08-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01901 |  | 2019-06-18 | 1
036909C-103S-DW-2052-0001-02 | Electrical SUB-C & FAR-C - Architectural First Floor Plan | B | 2019-08-12 | IFR | OL1-2K30-0016 | CV | 2019-08-21 | 036909C-JVD-TRN-02465 | 036909C-JVD-TRN-02465 | IFA | 2019-09-05 |  | Transmitted | TPSK-LPSA1-T-CV-02465 |  | 2019-08-22 | 1
036909C-103S-DW-2052-0001-05 | Electrical SUB-C & FAR-C - Architectural Elevations | B | 2019-08-12 | IFR | OL1-2K30-0019 | CV | 2019-08-21 | 036909C-JVD-TRN-02465 | 036909C-JVD-TRN-02465 | IFA | 2019-09-05 |  | Transmitted | TPSK-LPSA1-T-CV-02465 |  | 2019-08-22 | 1
036909C-1055-DI-0007-5501 | Area Basis of Design - 55 Flare System | B | 2019-08-21 | IFD | OL1-2G05-5501 | PE | 2019-08-21 | 036909C-JVD-TRN-02470 | 036909C-JVD-TRN-02470 | IFA | 2019-09-05 |  | Transmitted | TPSK-LSPA1-T-PE-02470 |  | 2019-08-22 | 1
036909C-103S-DW-2052-0001-03 | Electrical SUB-C & FAR-C - Architectural Ground Floor Plan | B | 2019-08-12 | IFR | OL1-2K30-0017 | CV | 2019-08-21 | 036909C-JVD-TRN-02465 | 036909C-JVD-TRN-02465 | IFA | 2019-09-05 |  | Transmitted | TPSK-LPSA1-T-CV-02465 |  | 2019-08-22 | 1
036909C-103S-DW-2052-0001-01 | Electrical SUB-C & FAR-C - Architectural Ground Floor Plan | B | 2019-08-12 | IFR | OL1-2K30-0015 | CV | 2019-08-21 | 036909C-JVD-TRN-02465 | 036909C-JVD-TRN-02465 | IFA | 2019-09-05 |  | Transmitted | TPSK-LPSA1-T-CV-02465 |  | 2019-08-22 | 1
036909C-1000-MS-1393-0006 | Job Specification For Steam Blowing Of Piping & Equipment | A | 2019-08-19 | IFR | OL1-2O71-0006 | PE | 2019-08-21 | 036909C-JVD-TRN-02463 | 036909C-JVD-TRN-02463 | IFR | 2019-09-05 |  | Transmitted |  |  | 2019-08-22 | 2
036909C-1000-MS-1393-0014 | Job Specification For Piping Inspection | A | 2019-08-19 | IFR | OL1-2O71-0013 | PE | 2019-08-21 | 036909C-JVD-TRN-02463 | 036909C-JVD-TRN-02463 | IFR | 2019-09-05 |  | Transmitted |  |  | 2019-08-22 | 2
036909C-1000-MS-1393-0012 | Job Specification For Manual Cleaning Of Large Bore Piping | A | 2019-08-19 | IFR | OL1-2O71-0012 | PE | 2019-08-21 | 036909C-JVD-TRN-02463 | 036909C-JVD-TRN-02463 | IFR | 2019-09-05 |  | Transmitted |  |  | 2019-08-22 | 2
036909C-1056-DI-0007-5601 | Area Basis of Design - 56 Waste Water Treatment System | B | 2018-09-13 | IFD | OL1-2G05-5601 | PE | 2018-09-26 | 036909C-JVD-TRN-00091 | 036909C-JVD-TRN-00091 | IFI |  | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00091 |  | 2018-09-27 | 3
036909C-1053-DI-0007-5301 | Area Basis of Design - 53 Cooling Tower System | C | 2019-08-16 | IFD | OL1-2G05-5301 | PE | 2019-08-19 | 036909C-JVD-TRN-02450 | 036909C-JVD-TRN-02450 | IFA | 2019-09-03 |  | Transmitted | TPSK-LSPA1-T-PE-02450 |  | 2019-08-21 | 1
036909C-103S-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 3S Electrical Sub-Station & FAR C | B | 2019-08-16 | IBD | OL1-2F75-0002 | FF | 2019-08-19 | 036909C-JVD-TRN-02449 | 036909C-JVD-TRN-02449 | IFR | 2019-09-02 |  | Transmitted | TPSK-LSPA1-T-FF-02449 |  | 2019-08-21 | 2
036909C-1039-SP-0810-3906 | Mechanical Equipment Data Sheet for BDU Anti Form Agent Drum | B | 2019-08-16 | IFQ | OL1-2M03-3906 | ME | 2019-08-19 | 036909C-JVD-TRN-02453 | 036909C-JVD-TRN-02453 | IFR | 2019-09-03 |  | Transmitted | TPSK-LSPA1-T-ME-02453 |  | 2019-08-21 | 2
036909C-1050-DI-0007-5001 | Area Basis of Design - 50 ISBL Supporting Utilities | B | 2019-08-16 | IFD | OL1-2G05-5001 | PE | 2019-08-19 | 036909C-JVD-TRN-02450 | 036909C-JVD-TRN-02450 | IFA | 2019-09-03 |  | Transmitted | TPSK-LSPA1-T-PE-02450 |  | 2019-08-21 | 1
036909C-1031-SP-0810-3180 | Mechanical Equipment Data Sheet for BDU Knock-Out Drum | B | 2019-08-16 | IFQ | OL1-2M03-3180 | ME | 2019-08-19 | 036909C-JVD-TRN-02453 | 036909C-JVD-TRN-02453 | IFR | 2019-09-03 |  | Transmitted | TPSK-LSPA1-T-ME-02453 |  | 2019-08-21 | 2
036909C-1030-SP-0810-3003 | Mechanical Equipment Data Sheet for Predistillation Tower Reflux Drum | B | 2019-08-16 | IFQ | OL1-2M03-3003 | ME | 2019-08-19 | 036909C-JVD-TRN-02453 | 036909C-JVD-TRN-02453 | IFR | 2019-09-03 |  | Transmitted | TPSK-LSPA1-T-ME-02453 |  | 2019-08-21 | 2
036909C-1031-SP-0810-3151 | Mechanical Equipment Data Sheet for BDU Condensate Flash Drum | B | 2019-08-16 | IFQ | OL1-2M03-3151 | ME | 2019-08-19 | 036909C-JVD-TRN-02453 | 036909C-JVD-TRN-02453 | IFR | 2019-09-03 |  | Transmitted | TPSK-LSPA1-T-ME-02453 |  | 2019-08-21 | 2
036909C-1011-SP-1552-1160 | Instrument Datasheets for Magnetostrictive Level Transmitter & Magnetic Level Gauge | 0 | 2019-08-14 | IFP | OL1-2I20-1160 | IE | 2019-08-19 | 036909C-JVD-TRN-02454 | 036909C-JVD-TRN-02454 | IFR | 2019-09-03 |  | Transmitted | TPSK-LSPA1-T-IE-02454 |  | 2019-08-21 | 2
036909C-1011-SP-1553-1156 | Instrument Datasheet for Pressure Indicating Transmitters & Flow Indicating D P Transmitters | B | 2019-07-31 | IFQ | OL1-2I20-1156 | IE | 2019-08-19 | 036909C-JVD-TRN-02456 | 036909C-JVD-TRN-02456 | IFR | 2019-09-03 |  | Transmitted | TPSK-LSPA1-T-IE-02456 |  | 2019-08-21 | 2
036909C-1011-PDS-1546-1190 | Process Datasheet for Restriction Orifice Furnace Area 10-H-1100 | B | 2019-08-16 | IFD | OL1-2G31-1190 | PE | 2019-08-19 | 036909C-JVD-TRN-02452 | 036909C-JVD-TRN-02452 | IFR | 2019-09-03 |  | Transmitted | TPSK-LSPA1-T-PE-02452 |  | 2019-08-21 | 2
036909C-1012-PDS-1546-1290 | Process Datasheet for Restriction Orifice Furnace Area 10-H-1200_1600 | B | 2019-08-16 | IFD | OL1-2G31-1290 | PE | 2019-08-19 | 036909C-JVD-TRN-02452 | 036909C-JVD-TRN-02452 | IFR | 2019-09-03 |  | Transmitted | TPSK-LSPA1-T-PE-02452 |  | 2019-08-21 | 2
036909C-100S-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 0S Electrical Sub-Station & FAR E | B | 2019-08-16 | IBD | OL1-2F75-0001 | FF | 2019-08-19 | 036909C-JVD-TRN-02449 | 036909C-JVD-TRN-02449 | IFR | 2019-09-02 |  | Transmitted | TPSK-LSPA1-T-FF-02449 |  | 2019-08-21 | 2
036909C-1031-PDS-0600-3150 | Process Equipment Datasheet - 10-E-3150 - BDU Condensate Heater | B | 2019-05-31 | IFD | OL1-2G30-3150 | PE | 2019-06-03 | 036909C-JVD-TRN-01796 | 036909C-JVD-TRN-01796 | IFR | 2019-06-18 | 2019-07-08 | Response to Client comments emailed Aug-20-19 R2-Comments as noted | TPSK-LSPA1-T-PE-01796 |  | 2019-06-10 | 2
036909C-1030-PDS-0600-3055 | Process Equipment Datasheet - 10-E-3055 A-B - Degasser Reboiler | B | 2019-05-29 | IFD | OL1-2G30-3055 | PE | 2019-05-30 | 036909C-JVD-TRN-01776 | 036909C-JVD-TRN-01776 | IFR | 2019-06-14 | 2019-06-25 | Response to Client comments emailed Aug-20-19 R2-Comments as noted | TPSK-LSPA1-T-PE-01776 |  | 2019-05-31 | 2
036909C-1000-DW-1451-0001 | Key Plan For UG Installation Drawings | B | 2019-06-12 | IBD | OL1-2K25-0001 | CV | 2019-06-19 | 036909C-JVD-TRN-01925 | 036909C-JVD-TRN-01925 | IFA | 2019-07-04 | 2019-08-16 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01925 |  | 2019-06-20 | 1
036909C-102E-CN-1733-0018 | Calculation Note for Foundation of 10-E-2413 | A | 2019-04-22 | IFR | OL1-2K13-0060 | CV | 2019-06-17 | 036909C-JVD-TRN-01903 | 036909C-JVD-TRN-01903 | IFA | 2019-07-02 | 2019-08-16 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01903 |  | 2019-06-18 | 1
036909C-102D-DW-1742-0001-001 | Foundation For Steel Shelter 10-SHT-2D01 - Formwork And Reinforcement | A | 2019-06-04 | IFR | OL1-2K31-1780 | CV | 2019-06-11 | 036909C-JVD-TRN-01858 | 036909C-JVD-TRN-01858 | IFA | 2019-06-26 | 2019-08-16 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01858 |  | 2019-06-11 | 1
036909C-102D-CN-1732-0005 | Calculation Note For Foundation Of 10-SHT-2D01 | A | 2019-06-04 | IFR | OL1-2K14-0053 | CV | 2019-06-11 | 036909C-JVD-TRN-01857 | 036909C-JVD-TRN-01857 | IFA | 2019-06-26 | 2019-08-16 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01857 |  | 2019-06-11 | 1
036909C-1000-DW-1563-0003 | AMADAS ARCHITECTURE | A | 2019-07-25 | IFR | OL1-2I84-2004 | IE | 2019-07-30 | 036909C-JVD-TRN-02283 | 036909C-JVD-TRN-02283 | IFA | 2019-08-14 | 2019-08-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02283 |  | 2019-07-31 | 1
036909C-1029-PDS-2600-2912 | Datasheet For Chemical Dosing Systems - 10-PK-2912 - Caustic Tower Anti-Foulant Inj Pkg | D | 2019-07-12 | IFD | OL1-2G30-2912 | PE | 2019-07-18 | 036909C-JVD-TRN-02184 | 036909C-JVD-TRN-02184 | IFR | 2019-08-02 | 2019-08-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02184 |  | 2019-07-19 | 2
036909C-1029-PDS-2600-2906 | Datasheet For Chemical Dosing Systems - 10-PK-2906 - DSG Anti-Foulant Injection Pkg | D | 2019-07-12 | IFD | OL1-2G30-2906 | PE | 2019-07-18 | 036909C-JVD-TRN-02184 | 036909C-JVD-TRN-02184 | IFR | 2019-08-02 | 2019-08-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02184 |  | 2019-07-19 | 2
036909C-1029-PDS-2600-2904 | Datasheet For Chemical Dosing Systems - 10-PK-2904 - Process Water Stripper Chem Inj Pkg | D | 2019-07-12 | IFD | OL1-2G30-2904 | PE | 2019-07-18 | 036909C-JVD-TRN-02184 | 036909C-JVD-TRN-02184 | IFR | 2019-08-02 | 2019-08-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02184 |  | 2019-07-19 | 2
036909C-1029-PDS-2600-2902 | Datasheet For Chemical Dosing System - 10-PK-2902 - Emulsion Breaker Injection Pkg | D | 2019-07-12 | IFD | OL1-2G30-2902 | PE | 2019-07-18 | 036909C-JVD-TRN-02184 | 036909C-JVD-TRN-02184 | IFR | 2019-08-02 | 2019-08-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02184 |  | 2019-07-19 | 2
036909C-1028-TDS-0610-2853 | Mechanical Equipment Data Sheet - 10-E-2853 - C2R Desuperheater No 2 | 0 | 2019-06-25 | Issue for Purchase | OL1-2M03-2853 | ME | 2019-07-18 | 036909C-JVD-TRN-02185 | 036909C-JVD-TRN-02185 | IFR | 2019-08-02 | 2019-08-16 | R2-Comments as noted | TPSK-LSPA1-T-ME-02185 |  | 2019-07-19 | 2
036909C-1030-PDS-0600-3098 | Process Equipment Datasheet - 10-E-3098 - Butadiene Product Subcooler | B | 2019-05-29 | IFD | OL1-2G30-3098 | PE | 2019-05-29 | 036909C-JVD-TRN-01762 | 036909C-JVD-TRN-01762 | IFR | 2019-06-13 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01762 |  | 2019-05-30 | 2
036909C-1030-PDS-0600-3085 | Process Equipment Datasheet - 10-E-3085 A-B - Butadiene Tower Reboiler | B | 2019-05-30 | IFD | OL1-2G30-3085 | PE | 2019-05-30 | 036909C-JVD-TRN-01784 | 036909C-JVD-TRN-01784 | IFR | 2019-06-14 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01784 |  | 2019-05-31 | 2
036909C-1030-PDS-0600-3084 | Process Equipment Datasheet - 10-E-3084 - Butadiene Tower Trim Reboiler | B | 2019-05-31 | IFD | OL1-2G30-3084 | PE | 2019-06-03 | 036909C-JVD-TRN-01796 | 036909C-JVD-TRN-01796 | IFR | 2019-06-18 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01796 |  | 2019-06-10 | 2
036909C-1030-PDS-0600-3081 | Process Equipment Datasheet - 10-E-3080 A-B - Butadiene Tower Condenser | B | 2019-05-30 | IFD | OL1-2G30-3081 | PE | 2019-05-30 | 036909C-JVD-TRN-01784 | 036909C-JVD-TRN-01784 | IFR | 2019-06-14 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01784 |  | 2019-05-31 | 2
036909C-1030-PDS-0600-3071 | Process Equipment Datasheet - 10-E-3070 - Water - NMP Cooler | B | 2019-05-31 | IFD | OL1-2G30-3071 | PE | 2019-06-03 | 036909C-JVD-TRN-01796 | 036909C-JVD-TRN-01796 | IFR | 2019-06-18 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01796 |  | 2019-06-10 | 2
036909C-1030-PDS-0600-3063 | Process Equipment Datasheet - 10-E-3060 - C4 Acetylene Washer Condenser | B | 2019-05-29 | IFD | OL1-2G30-3063 | PE | 2019-05-30 | 036909C-JVD-TRN-01776 | 036909C-JVD-TRN-01776 | IFR | 2019-06-14 | 2019-06-25 | R1-No comments | TPSK-LSPA1-T-PE-01776 |  | 2019-05-31 | 2
036909C-1030-PDS-0600-3062 | Process Equipment Datasheet - 10-E-3062 - C4 Acetylene Condenser | B | 2019-05-29 | IFD | OL1-2G30-3062 | PE | 2019-05-30 | 036909C-JVD-TRN-01776 | 036909C-JVD-TRN-01776 | IFR | 2019-06-14 | 2019-06-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-01776 |  | 2019-05-31 | 2
036909C-1030-PDS-0600-3031 | Process Equipment Datasheet - 10-E-3030 - After Washer Condenser | B | 2019-05-29 | IFD | OL1-2G30-3031 | PE | 2019-05-29 | 036909C-JVD-TRN-01762 | 036909C-JVD-TRN-01762 | IFR | 2019-06-13 | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-PE-01762 |  | 2019-05-30 | 2
036909C-1030-PDS-0600-3021 | Process Equipment Datasheet - 10-E-3020 - Main Washer Condenser | B | 2019-05-29 | IFD | OL1-2G30-3021 | PE | 2019-05-29 | 036909C-JVD-TRN-01762 | 036909C-JVD-TRN-01762 | IFR | 2019-06-13 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01762 |  | 2019-05-30 | 2
036909C-1030-PDS-0600-3018 | Process Equipment Datasheet - 10-E-3018 A-B - Solvent Cooler | B | 2019-05-29 | IFD | OL1-2G30-3018 | PE | 2019-05-29 | 036909C-JVD-TRN-01762 | 036909C-JVD-TRN-01762 | IFR | 2019-06-13 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01762 |  | 2019-05-30 | 2
036909C-1030-PDS-0600-3015 | Process Equipment Datasheet - 10-E-3015 - C4 Trim Vaporizer | B | 2019-05-29 | IFD | OL1-2G30-3015 | PE | 2019-05-30 | 036909C-JVD-TRN-01776 | 036909C-JVD-TRN-01776 | IFR | 2019-06-14 | 2019-06-25 | R1-No comments | TPSK-LSPA1-T-PE-01776 |  | 2019-05-31 | 2
036909C-1030-PDS-0600-3014 | Process Equipment Datasheet - 10-E-3014 A-B - C4 Trim Vaporizer | B | 2019-05-29 | IFD | OL1-2G30-3014 | PE | 2019-05-29 | 036909C-JVD-TRN-01762 | 036909C-JVD-TRN-01762 | IFR | 2019-06-13 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01762 |  | 2019-05-30 | 2
036909C-1030-PDS-0600-3005 | Process Equipment Datasheet - 10-E-3005 - Predistillation Tower Reboiler | B | 2019-05-31 | IFD | OL1-2G30-3005 | PE | 2019-06-03 | 036909C-JVD-TRN-01796 | 036909C-JVD-TRN-01796 | IFR | 2019-06-18 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01796 |  | 2019-06-10 | 2
036909C-1030-PDS-0600-3004 | Process Equipment Datasheet - 10-E-3004 A-B - Predistillation Tower Trim Reboiler | B | 2019-05-31 | IFD | OL1-2G30-3004 | PE | 2019-06-03 | 036909C-JVD-TRN-01796 | 036909C-JVD-TRN-01796 | IFR | 2019-06-18 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01796 |  | 2019-06-10 | 2
036909C-1030-PDS-0600-3001 | Process Equipment Datasheet - 10-E-3000 - Predistillation Tower Condenser | B | 2019-05-31 | IFD | OL1-2G30-3001 | PE | 2019-06-03 | 036909C-JVD-TRN-01796 | 036909C-JVD-TRN-01796 | IFR | 2019-06-18 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01796 |  | 2019-06-10 | 2
036909C-1011-SP-1552-1160 | Instrument Datasheets for Magnetostrictive Level Transmitter & Magnetic Level Gauge | B | 2019-06-17 | IFQ | OL1-2I20-1160 | IE | 2019-06-20 | 036909C-JVD-TRN-01953 | 036909C-JVD-TRN-01953 | IFR | 2019-07-05 | 2019-07-31 | R2-Comments as noted | TPSK-LSPA1-T-IE-01953 |  | 2019-06-21 | 2
036909C-1053-DI-0007-5301 | Area Basis of Design - 53 Cooling Tower System | B | 2018-09-24 | IFD | OL1-2G05-5301 | PE | 2018-09-26 | 036909C-JVD-TRN-00093 | 036909C-JVD-TRN-00093, ROC-TPSK-CECO-T-00001 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00003 |  | 2018-09-27 | 3
036909C-103S-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 3S Electrical Sub-station and Far C | A | 2019-03-29 | IFR | OL1-2F75-0002 | FF | 2019-03-29 | 036909C-JVD-TRN-01191 | 036909C-JVD-TRN-01191, KLOC-TPSK-VSAFE-T-00002 | IFR | 2019-04-11 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01191 |  | 2019-03-29 | 2
036909C-100S-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 0S Electrical Sub-station and Far E | A | 2019-03-29 | IFR | OL1-2F75-0001 | FF | 2019-03-29 | 036909C-JVD-TRN-01191 | 036909C-JVD-TRN-01191, KLOC-TPSK-VSAFE-T-00002 | IFR | 2019-04-11 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01191 |  | 2019-03-29 | 2
036909C-1028-TDS-0610-2852 | Mechanical Equipment Data Sheet - 10-E-2852 - C2R Desuperheater No 1 | 0 | 2019-07-12 | Issue for Purchase | OL1-2M03-2852 | ME | 2019-07-22 | 036909C-JVD-TRN-02235 | 036909C-JVD-TRN-02235 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02235 |  | 2019-07-23 | 2
036909C-1028-TDS-0610-2807 | Mechanical Equipment Data Sheet - 10-E-2807 - C3 Chiller No 1 | 0 | 2019-07-18 | Issue for Purchase | OL1-2M03-2807 | ME | 2019-07-22 | 036909C-JVD-TRN-02235 | 036909C-JVD-TRN-02235 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02235 |  | 2019-07-22 | 2
036909C-1027-TDS-0610-2725 | Mechanical Equipment Data Sheet - 10-E-2725 A B C - Rerun Tower Reboiler | 0 | 2019-07-16 | Issue for Purchase | OL1-2M03-2725 | ME | 2019-07-22 | 036909C-JVD-TRN-02231 | 036909C-JVD-TRN-02231 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02231 |  | 2019-07-23 | 2
036909C-1027-TDS-0610-2715 | Mechanical Equipment Data Sheet - 10-E-2715 A/B - Depentanizer Reboiler | 0 | 2019-07-18 | Issue for Purchase | OL1-2M03-2715 | ME | 2019-07-22 | 036909C-JVD-TRN-02235 | 036909C-JVD-TRN-02235 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02235 |  | 2019-07-23 | 2
036909C-1025-TDS-0610-2575 | Mechanical Equipment Data Sheet - 10-E-2575 - Deethanizer Reboiler | 0 | 2019-07-18 | Issue for Purchase | OL1-2M03-2575 | ME | 2019-07-22 | 036909C-JVD-TRN-02235 | 036909C-JVD-TRN-02235 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02235 |  | 2019-07-23 | 2
036909C-1021-TDS-0610-2166 | Mechanical Equipment Data Sheet - 10-E-2166 - DSG Blowdown Cooler | 0 | 2019-07-12 | Issue for Purchase | OL1-2M03-2166 | ME | 2019-07-22 | 036909C-JVD-TRN-02235 | 036909C-JVD-TRN-02235 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02235 |  | 2019-07-23 | 2
036909C-1021-TDS-0610-2147 | Mechanical Equipment Data Sheet - 10-E-2146 - DSG Feed Heater | 0 | 2019-07-17 | Issue for Purchase | OL1-2M03-2147 | ME | 2019-07-22 | 036909C-JVD-TRN-02235 | 036909C-JVD-TRN-02235 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02235 |  | 2019-07-23 | 2
036909C-1021-TDS-0610-2145 | Mechanical Equipment Data Sheet - 10-E-2145 - Process Water Stripper Reboiler | 0 | 2019-07-08 | Issue for Purchase | OL1-2M03-2145 | ME | 2019-07-22 | 036909C-JVD-TRN-02212 | 036909C-JVD-TRN-02212 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02212 |  | 2019-07-23 | 2
036909C-1021-TDS-0610-2137 | Mechanical Equipment Data Sheet - 10-E-2136 - Process Water Stripper Feed Heater | 0 | 2019-07-12 | Issue for Purchase | OL1-2M03-2137 | ME | 2019-07-22 | 036909C-JVD-TRN-02235 | 036909C-JVD-TRN-02235 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02235 |  | 2019-07-23 | 2
036909C-102B-DW-1743-0036-001 | Foundation for 10-D-2322 | A | 2019-06-07 | IFR | OL1-2K31-0103 | CV | 2019-06-11 | 036909C-JVD-TRN-01854 | 036909C-JVD-TRN-01854 | IFA | 2019-06-26 | 2019-08-14 | A2 - Approved with comments re-submit is not required | TPSK-LSPA1-T-CV-01854 |  | 2019-06-11 | 1
036909C-102E-DW-1743-0050-001 | Foundation for 10-T-2300 | A | 2019-06-03 | IFR | OL1-2K31-0040 | CV | 2019-06-11 | 036909C-JVD-TRN-01854 | 036909C-JVD-TRN-01854 | IFA | 2019-06-26 | 2019-08-14 | A2 - Approved with comments re-submit is not required | TPSK-LSPA1-T-CV-01854 |  | 2019-06-11 | 1
036909C-1052-TDS-0610-5201 | Mechanical Equipment Data Sheet - 10-E-5200 - MP Ethylene Superheater | 0 | 2019-07-18 | Issue for Purchase | OL1-2M03-5201 | ME | 2019-07-22 | 036909C-JVD-TRN-02235 | 036909C-JVD-TRN-02235 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02235 |  | 2019-07-23 | 2
036909C-1051-SP-0810-5150 | Mechanical Equipment Data Sheet For Continuous Blow Down Flash Drum | 0 | 2019-07-05 | IFP | OL1-2M03-5150 | ME | 2019-07-17 | 036909C-JVD-TRN-02177 | 036909C-JVD-TRN-02177 | IFR | 2019-08-01 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02177 |  | 2019-07-17 | 2
036909C-1019-SP-0810-1911 | Mechanical Equipment Data Sheet for DMDS Bulk Storage Drum | 0 | 2019-07-16 | Issue for Purchase | OL1-2M03-1911 | ME | 2019-07-22 | 036909C-JVD-TRN-02207 | 036909C-JVD-TRN-02207 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-02207 |  | 2019-07-23 | 2
036909C-1051-TDS-0610-5113 | Mechanical Equipment Data Sheet - 10-E-5113 - Foul Condensate Cooler | 0 | 2019-06-25 | Issue for Purchase | OL1-2M03-5113 | ME | 2019-07-18 | 036909C-JVD-TRN-02185 | 036909C-JVD-TRN-02185 | IFR | 2019-08-02 | 2019-08-20 | R1-No comments | TPSK-LSPA1-T-ME-02185 |  | 2019-07-19 | 2
036909C-1023-TDS-0610-2305 | Mechanical Equipment Data Sheet - 10-E-2305 - Caustic Tower Feed Heater | 0 | 2019-07-08 | Issue for Purchase | OL1-2M03-2305 | ME | 2019-07-22 | 036909C-JVD-TRN-02212 | 036909C-JVD-TRN-02212 | IFR | 2019-08-06 | 2019-08-20 | R1-No comments | TPSK-LSPA1-T-ME-02212 |  | 2019-07-23 | 2
036909C-1020-TDS-0610-2048 | Mechanical Equipment Data Sheet - 10-E-2048 - Heavy Fuel Oil Product Cooler | 0 | 2019-07-16 | Issue for Purchase | OL1-2M03-2048 | ME | 2019-07-22 | 036909C-JVD-TRN-02231 | 036909C-JVD-TRN-02231 | IFR | 2019-08-06 | 2019-08-20 | R1-No comments | TPSK-LSPA1-T-ME-02231 |  | 2019-07-23 | 2
036909C-1023-SP-0810-2322 | Mechanical Equipment Data Sheet Skim Oil Drum | 0 | 2019-07-16 | Issue for Purchase | OL1-2M03-2322 | ME | 2019-07-18 | 036909C-JVD-TRN-02188 | 036909C-JVD-TRN-02188 | IFR | 2019-08-02 | 2019-08-20 | R1-No comments | TPSK-LSPA1-T-ME-02188 |  | 2019-07-19 | 2
036909C-1019-SP-0810-1912 | Mechanical Equipment Data Sheet for DMDS Injection Drum | 0 | 2019-07-16 | Issue for Purchase | OL1-2M03-1912 | ME | 2019-07-22 | 036909C-JVD-TRN-02207 | 036909C-JVD-TRN-02207 | IFR | 2019-08-06 | 2019-08-20 | R1-No comments | TPSK-LSPA1-T-ME-02207 |  | 2019-07-23 | 2
036909C-1029-PDS-2600-2945 | Datasheet For Chemical Dosing Systems - 10-PK-2945 - Anti-Oxidant Injection Package | C | 2019-07-12 | IFD | OL1-2G30-2945 | PE | 2019-07-18 | 036909C-JVD-TRN-02184 | 036909C-JVD-TRN-02184 | IFR | 2019-08-02 | 2019-08-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-02184 |  | 2019-07-19 | 2
036909C-1029-PDS-2600-2940 | Datasheet For Chemical Dosing Systems - 10-PK-2940 - C4 Polymer Inhibitor Inj Pkg | E | 2019-07-12 | IFD | OL1-2G30-2940 | PE | 2019-07-18 | 036909C-JVD-TRN-02184 | 036909C-JVD-TRN-02184 | IFR | 2019-08-02 | 2019-08-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-02184 |  | 2019-07-19 | 2
036909C-1056-SP-1513-5601 | Complex Loop Narratives Area 56 Wastewater | B | 2019-07-19 | IBD | OL1-2I71-5601 | IE | 2019-07-22 | 036909C-JVD-TRN-02209 | 036909C-JVD-TRN-02209 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-IE-02209 |  | 2019-07-23 | 2
036909C-1055-SP-1513-5501 | Complex Loop Narratives Area 55 Vent Gas and Flare System | B | 2019-07-19 | IBD | OL1-2I71-5501 | IE | 2019-07-22 | 036909C-JVD-TRN-02209 | 036909C-JVD-TRN-02209 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-IE-02209 |  | 2019-07-23 | 2
036909C-1025-SP-1513-2501 | Complex Loop Narratives Area 25 Cold Fractionation | B | 2019-07-22 | IBD | OL1-2I71-2501 | IE | 2019-07-23 | 036909C-JVD-TRN-02240 | 036909C-JVD-TRN-02240 | IFR | 2019-08-07 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-IE-02240 |  | 2019-07-24 | 2
036909C-1021-SP-1513-2101 | Complex Loop Narratives Area 21 Quench Water Dilution Steam | B | 2019-07-19 | IBD | OL1-2I71-2101 | IE | 2019-07-22 | 036909C-JVD-TRN-02209 | 036909C-JVD-TRN-02209 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-IE-02209 |  | 2019-07-23 | 2
036909C-1055-SP-1545-5501 | Instrument Datasheets for Pressure Safety Valve - Area 55 | A | 2019-07-18 | IFI | OL1-2I20-5516 | IE | 2019-07-22 | 036909C-JVD-TRN-02213 | 036909C-JVD-TRN-02213 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-IE-02213 |  | 2019-07-23 | 2
036909C-1054-SP-1545-5401 | Instrument Datasheet for Pressure Safety Valve - Area 54 | A | 2019-07-18 | IFI | OL1-2I20-5416 | IE | 2019-07-22 | 036909C-JVD-TRN-02213 | 036909C-JVD-TRN-02213 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-IE-02213 |  | 2019-07-23 | 2
036909C-1052-SP-1545-5201 | Instrument Datasheets for Pressure Safety Valve - Area 52 | A | 2019-07-18 | IFI | OL1-2I20-5216 | IE | 2019-07-22 | 036909C-JVD-TRN-02213 | 036909C-JVD-TRN-02213 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-IE-02213 |  | 2019-07-23 | 2
036909C-1056-DW-1514-5601 | Cause and Effect Diagram Area 56 Wastewater | C | 2019-07-19 | IBD | OL1-2G50-5601 | IE | 2019-07-22 | 036909C-JVD-TRN-02211 | 036909C-JVD-TRN-02211 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-IE-02211 |  | 2019-07-23 | 2
036909C-1027-SP-1545-2701 | Instrument Datasheets for Pressure Safety Valve - Area 27 | A | 2019-07-19 | IFI | OL1-2I20-2716 | IE | 2019-07-24 | 036909C-JVD-TRN-02258 | 036909C-JVD-TRN-02258 | IFI |  | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-IE-02258 |  | 2019-07-25 | 3
036909C-1055-DW-1514-5501 | Cause and Effect Diagram Area 55 Vent Gas and Flare System | B | 2019-07-19 | IBD | OL1-2G50-5501 | PE | 2019-07-22 | 036909C-JVD-TRN-02216 | 036909C-JVD-TRN-02216 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-PE-02216 |  | 2019-07-23 | 2
036909C-1025-DW-1514-2501 | Cause and Effect Diagram Area 25 Cold Fractionation | B | 2019-07-19 | IBD | OL1-2G50-2501 | PE | 2019-07-22 | 036909C-JVD-TRN-02216 | 036909C-JVD-TRN-02216 | IFR | 2019-08-06 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-PE-02216 |  | 2019-07-23 | 2
036909C-1012-NM-0007-1201 | Piping Specialty Item Datasheet Index - Liquid Cracking Furnace Areas 12-16 | B | 2019-07-18 | IFD | OL1-2G91-1201 | PE | 2019-07-18 | 036909C-JVD-TRN-02193 | 036909C-JVD-TRN-02193 | IFR | 2019-08-02 | 2019-08-20 | R1-No comments | TPSK-LSPA1-T-PE-02193 |  | 2019-07-19 | 2
036909C-1011-NM-0007-1101 | Piping Specialty Item Datasheet Index - Recycle Gas Furnace Area 11 | B | 2019-07-18 | IFD | OL1-2G91-1101 | PE | 2019-07-18 | 036909C-JVD-TRN-02193 | 036909C-JVD-TRN-02193 | IFR | 2019-08-02 | 2019-08-20 | R1-No comments | TPSK-LSPA1-T-PE-02193 |  | 2019-07-19 | 2
036909C-1000-PP-868 | Piping System Pressure Test And Test Package Management Procedure | A | 2019-07-09 | IFR | OL1-2Q92-0009 | QM | 2019-07-16 | 036909C-JVD-TRN-02157 | 036909C-JVD-TRN-02157 | IFR | 2019-07-31 | 2019-08-12 | R1-No comments | TPSK-LSPA1-T-QM-02157 |  | 2019-07-17 | 2
036909C-1000-PP-809 | Site Quality Control Plan | A | 2019-07-09 | IFR | OL1-2Q92-0005 | QM | 2019-07-16 | 036909C-JVD-TRN-02157 | 036909C-JVD-TRN-02157 | IFR | 2019-07-31 | 2019-08-12 | R2-Comments as noted | TPSK-LSPA1-T-QM-02157 |  | 2019-07-17 | 2
036909C-105T-DW-1574-0032 | Telecom And Security System Devices Layout- Cooling Water Unit | A | 2019-07-12 | IFR | OL1-2T12-0014 | EE | 2019-07-16 | 036909C-JVD-TRN-02161 | 036909C-JVD-TRN-02161 | IFA | 2019-07-31 | 2019-08-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02161 |  | 2019-07-17 | 1
036909C-105W-DW-1574-0036 | Telecom and Security System Devices Layout- Waste Water Treatment | A | 2019-07-12 | IFR | OL1-2T12-0016 | EE | 2019-07-16 | 036909C-JVD-TRN-02161 | 036909C-JVD-TRN-02161 | IFA | 2019-07-31 | 2019-08-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02161 |  | 2019-07-17 | 1
036909C-105U-DW-1574-0033 | Telecom And Security System Devices Layout- Utilities | A | 2019-07-12 | IFR | OL1-2T12-0015 | EE | 2019-07-16 | 036909C-JVD-TRN-02161 | 036909C-JVD-TRN-02161 | IFA | 2019-07-31 | 2019-08-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02161 |  | 2019-07-17 | 1
036909C-102E-DW-1574-0030 | Telecom And Security System Devices Layout- Process Cracked Gas Compressor | A | 2019-07-12 | IFR | OL1-2T12-0012 | EE | 2019-07-16 | 036909C-JVD-TRN-02161 | 036909C-JVD-TRN-02161 | IFA | 2019-07-31 | 2019-08-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02161 |  | 2019-07-17 | 1
036909C-102D-DW-1574-0029 | Telecom And Security System Devices Layout- Process Cold Compressors | A | 2019-07-12 | IFR | OL1-2T12-0011 | EE | 2019-07-16 | 036909C-JVD-TRN-02161 | 036909C-JVD-TRN-02161 | IFA | 2019-07-31 | 2019-08-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02161 |  | 2019-07-17 | 1
036909C-102C-DW-1574-0028 | Telecom And Security System Devices Layout- Hot Fractionation - GHU Unit | A | 2019-07-12 | IFR | OL1-2T12-0010 | EE | 2019-07-16 | 036909C-JVD-TRN-02161 | 036909C-JVD-TRN-02161 | IFA | 2019-07-31 | 2019-08-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02161 |  | 2019-07-17 | 1
036909C-102B-DW-1574-0027 | Telecom And Security System Devices Layout- C3 Hydrogenation | A | 2019-07-12 | IFR | OL1-2T12-0009 | EE | 2019-07-16 | 036909C-JVD-TRN-02161 | 036909C-JVD-TRN-02161 | IFA | 2019-07-31 | 2019-08-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02161 |  | 2019-07-17 | 1
036909C-102A-DW-1574-0026 | Telecom and Security System Devices Layout- Quench | A | 2019-07-12 | IFR | OL1-2T12-0008 | EE | 2019-07-16 | 036909C-JVD-TRN-02161 | 036909C-JVD-TRN-02161 | IFA | 2019-07-31 | 2019-08-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02161 |  | 2019-07-17 | 1
036909C-101B-DW-1574-0025 | Telecom And Security System Devices Layout- Furnace Utility | A | 2019-07-12 | IFR | OL1-2T12-0007 | EE | 2019-07-16 | 036909C-JVD-TRN-02161 | 036909C-JVD-TRN-02161 | IFA | 2019-07-31 | 2019-08-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02161 |  | 2019-07-17 | 1
036909C-100S-DW-1574-0023 | Telecom And Security System Devices Layout- Area Substation E And FAR E | A | 2019-07-12 | IFR | OL1-2T12-0005 | EE | 2019-07-16 | 036909C-JVD-TRN-02161 | 036909C-JVD-TRN-02161 | IFA | 2019-07-31 | 2019-08-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02161 |  | 2019-07-17 | 1
036909C-1020-SP-0910-2006 | Mechanical Equipment Data Sheet - Quench Oil Pump | B | 2018-11-28 | IFQ | OL1-2M03-2006 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476, ROC-TPSK-CECO-T-00014 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00476 |  | 2018-12-11 | 2
036909C-103S-DW-1574-0024 | Telecom And Security System Devices Layout- Sub C And Far C | A | 2019-07-12 | IFR | OL1-2T12-0006 | EE | 2019-07-18 | 036909C-JVD-TRN-02183 | 036909C-JVD-TRN-02183 | IFA | 2019-08-02 | 2019-08-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02183 |  | 2019-07-19 | 1
036909C-103A-DW-1574-0034 | Telecom And Security System Devices Layout - Process 3A | A | 2019-07-12 | IFR | OL1-2T12-0018 | EE | 2019-07-17 | 036909C-JVD-TRN-02171 | 036909C-JVD-TRN-02171 | IFA | 2019-08-01 | 2019-08-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02171 |  | 2019-07-17 | 1
036909C-105F-DW-1574-0035 | Telecom And Security System Devices Layout- Flare Area Sub-Substation F and FAR FL Area | A | 2019-07-12 | IFR | OL1-2T12-0017 | EE | 2019-07-17 | 036909C-JVD-TRN-02171 | 036909C-JVD-TRN-02171 | IFA | 2019-08-01 | 2019-08-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02171 |  | 2019-07-17 | 1
036909C-103A-DW-1612-0001 | Earthing And Lightning Protection Layout - Zone 3A Butadiene Extraction Unit | A | 2019-06-27 | IFR | OL1-2E52-0017 | EE | 2019-06-28 | 036909C-JVD-TRN-02021 | 036909C-JVD-TRN-02021 | IFR | 2019-07-12 | 2019-07-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02021 |  | 2019-07-01 | 1
036909C-100M-DW-1574-0021 | Telecom and Security System Devices Layout- Metering | A | 2019-07-12 | IFR | OL1-2T12-0003 | EE | 2019-07-17 | 036909C-JVD-TRN-02171 | 036909C-JVD-TRN-02171 | IFA | 2019-08-01 | 2019-08-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02171 |  | 2019-07-17 | 1
036909C-105T-DW-1632-0001 | Lighting Layout-Zone 5T Cooling Water Unit | A | 2019-07-29 | IFR | OL1-2E43-0005 | EE | 2019-07-30 | 036909C-JVD-TRN-02281 | 036909C-JVD-TRN-02281 | IFA | 2019-08-13 | 2019-08-08 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02281 |  | 2019-07-31 | 1
036909C-103A-DW-1632-0001 | Lighting Layout - Zone 3A Butadiene Extraction Unit | A | 2019-08-01 | IFR | OL1-2E43-0019 | EE | 2019-08-01 | 036909C-JVD-TRN-02311 | 036909C-JVD-TRN-02311 | IFR | 2019-08-15 | 2019-08-08 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02311 |  | 2019-08-05 | 1
036909C-105W-DW-1632-0001 | Lighting Layout-Zone 5W Waste Water Treatment | A | 2019-07-18 | IFR | OL1-2E43-0012 | EE | 2019-07-22 | 036909C-JVD-TRN-02204 | 036909C-JVD-TRN-02204 | IFR | 2019-08-05 | 2019-08-08 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02204 |  | 2019-07-23 | 1
036909C-105F-DW-1632-0001 | Lighting Layout-Zone 5F HP & Polyolefins Flares Unit | A | 2019-07-22 | IFR | OL1-2E43-0011 | EE | 2019-07-23 | 036909C-JVD-TRN-02237 | 036909C-JVD-TRN-02237 | IFR | 2019-08-06 | 2019-08-08 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02237 |  | 2019-07-23 | 1
036909C-103S-DW-1632-0001 | Lighting Layout - Zone 3S Substation & Far C | A | 2019-07-19 | IFR | OL1-2E43-0008 | EE | 2019-07-22 | 036909C-JVD-TRN-02204 | 036909C-JVD-TRN-02204 | IFR | 2019-08-05 | 2019-08-08 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02204 |  | 2019-07-23 | 1
036909C-100S-DW-1632-0001 | Lighting Layout-Zone OS Electrical Substation E and FAR E | A | 2019-07-22 | IFR | OL1-2E43-0007 | EE | 2019-07-23 | 036909C-JVD-TRN-02237 | 036909C-JVD-TRN-02237 | IFR | 2019-08-06 | 2019-08-08 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02237 |  | 2019-07-23 | 1
036909C-100M-DW-1632-0001 | Lighting Layout-Zone OM Metering Zone | A | 2019-07-22 | IFR | OL1-2E43-0010 | EE | 2019-07-23 | 036909C-JVD-TRN-02237 | 036909C-JVD-TRN-02237 | IFR | 2019-08-06 | 2019-08-08 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02237 |  | 2019-07-23 | 1
036909C-105F-CN-1733-0008 | Calculation Note Foundation Of 10-D-5565 | A | 2019-05-31 | IFR | OL1-2K13-0285 | CV | 2019-06-10 | 036909C-JVD-TRN-01837 | 036909C-JVD-TRN-01837 | IFR | 2019-06-24 | 2019-08-08 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01837 |  | 2019-06-10 | 1
036909C-105U-DW-1743-0011-002 | Foundation For 10-TK-5120 | A | 2019-06-11 | IFR | OL1-2K31-0304-002 | CV | 2019-06-13 | 036909C-JVD-TRN-01886 | 036909C-JVD-TRN-01886 | IFR | 2019-06-27 | 2019-08-19 | R2-Comments as noted | TPSK-LSPA1-T-CV-01886 |  | 2019-06-14 | 2
036909C-105U-DW-1743-0011-001 | Foundation For 10-TK-5120 | A | 2019-06-11 | IFR | OL1-2K31-0304-001 | CV | 2019-06-13 | 036909C-JVD-TRN-01886 | 036909C-JVD-TRN-01886 | IFR | 2019-06-27 | 2019-08-19 | R2-Comments as noted | TPSK-LSPA1-T-CV-01886 |  | 2019-06-14 | 2
036909C-105U-DW-1743-0010-001 | Foundation For10-TK-5110 | A | 2019-06-11 | IFR | OL1-2K31-0303-001 | CV | 2019-06-13 | 036909C-JVD-TRN-01886 | 036909C-JVD-TRN-01886 | IFR | 2019-06-27 | 2019-08-19 | R2-Comments as noted | TPSK-LSPA1-T-CV-01886 |  | 2019-06-14 | 2
036909C-103A-DW-1743-0012 | Foundation For 10-T-3080 | A | 2019-06-14 | IFR | OL1-2K31-0219 | CV | 2019-06-17 | 036909C-JVD-TRN-01898 | 036909C-JVD-TRN-01898 | IFR | 2019-07-02 | 2019-08-19 | R2-Comments as noted | TPSK-LSPA1-T-CV-01898 |  | 2019-06-17 | 2
036909C-103A-DW-1743-0009 | Foundation For 10-T-3050 | A | 2019-06-14 | IFR | OL1-2K31-0216 | CV | 2019-06-17 | 036909C-JVD-TRN-01898 | 036909C-JVD-TRN-01898 | IFR | 2019-07-02 | 2019-08-19 | R2-Comments as noted | TPSK-LSPA1-T-CV-01898 |  | 2019-06-17 | 2
036909C-103A-DW-1743-0008 | Foundation For 10-T-3030 | A | 2019-06-14 | IFR | OL1-2K31-0215 | CV | 2019-06-14 | 036909C-JVD-TRN-01896 | 036909C-JVD-TRN-01896 | IFR | 2019-06-28 | 2019-08-19 | R2-Comments as noted | TPSK-LSPA1-T-CV-01896 |  | 2019-06-14 | 2
036909C-103A-DW-1743-0004 | Foundation For 10-T-3000 | A | 2019-06-14 | IFR | OL1-2K31-0211 | CV | 2019-06-14 | 036909C-JVD-TRN-01896 | 036909C-JVD-TRN-01896 | IFR | 2019-06-28 | 2019-08-19 | R2-Comments as noted | TPSK-LSPA1-T-CV-01896 |  | 2019-06-17 | 2
036909C-105U-DW-1743-0010-002 | Foundation For 10-TK-5110 | A | 2019-06-11 | IFR | OL1-2K31-0303-002 | CV | 2019-06-13 | 036909C-JVD-TRN-01886 | 036909C-JVD-TRN-01886 | IFR | 2019-06-27 |  | Transmitted | TPSK-LSPA1-T-CV-01886 |  | 2019-06-14 | 2
036909C-100P-DW-1552-0001 | Level Studies And Instrument Design ISBL - 0P | A | 2019-07-23 | IFR | OL1-2I31-0201 | IE | 2019-07-29 | 036909C-JVD-TRN-02278 | 036909C-JVD-TRN-02278 | IFA | 2019-08-13 | 2019-08-08 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02278 |  | 2019-07-30 | 1
036909C-1029-SP-2510-2910 | Mechanical Equipment Data Sheet For Wash Oil Day Tank | C | 2019-08-13 | IFQ | OL1-2M03-2910 | ME | 2019-08-16 | 036909C-JVD-TRN-02447 | 036909C-JVD-TRN-02447 | IFR | 2019-08-31 |  | Transmitted | TPSK-LSPA1-T-ME-02447 |  | 2019-08-19 | 2
036909C-1024-SP-1513-2403 | Sequence Narratives Area 24 - Dehydration_Regen_Deprop_C2 Hydrog | B | 2019-08-16 | IBD | OL1-2G51-2403 | PE | 2019-08-16 | 036909C-JVD-TRN-02446 | 036909C-JVD-TRN-02446 | IFR | 2019-08-31 |  | Transmitted | TPSK-LSPA1-T-PE-02446 |  | 2019-08-19 | 2
036909C-1000-DW-1425-0001 | Roads- Paving And Finishing Layout | C | 2019-08-08 | IDD | OL1-2K27-0001 | CV | 2019-08-16 | 036909C-JVD-TRN-02444 | 036909C-JVD-TRN-02444 | IFA | 2019-09-02 |  | Transmitted | TPSK-LSPA1-T-CV-02444 |  | 2019-08-19 | 1
036909C-1012-JSD-1513-1201 | Shutdown Interlock Narrative - 132U - Area 12-16 Liquid and Gas Cracking Furnaces | B | 2019-07-08 | IFD | OL1-2G50-1201 | PE | 2019-07-09 | 036909C-JVD-TRN-02112 | 036909C-JVD-TRN-02112 | IFR | 2019-07-24 | 2019-08-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-02112 |  | 2019-07-10 | 2
036909C-1000-JSD-1530-0003 | Telecom Numbering | B | 2019-07-30 | IFR | OL1-2R05-0028 | EE | 2019-08-01 | 036909C-JVD-TRN-02310 | 036909C-JVD-TRN-02310 | IFR | 2019-08-16 | 2019-08-08 | R2-Comments as noted | TPSK-LSPA1-T-EE-02310 |  | 2019-08-05 | 2
036909C-1024-SP-1513-2403 | Sequence Narratives - Area 24 - Dehydration - Regen - Deprop - C2 Hydrog | A | 2019-04-16 | IFR | OL1-2G51-2403 | PE | 2019-04-16 | 036909C-JVD-TRN-01374 | 036909C-JVD-TRN-01374 | IFR | 2019-05-01 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-01374 |  | 2019-04-17 | 2
036909C-1000-DW-1425-0001 | Roads- Paving And Finishing Layout | B | 2019-07-26 | IDD | OL1-2K27-0001 | CV | 2019-07-30 | 036909C-JVD-TRN-02287 | 036909C-JVD-TRN-02287 | IFA | 2019-08-14 |  | Transmitted | TPSK-LSPA1-T-CV-02287 |  | 2019-07-31 | 1
036909C-1000-DW-1425-0001 | Roads Paving And Finishing Layout | A | 2019-03-13 | IFR | OL1-2K27-0001 | CV | 2019-03-15 | 036909C-JVD-TRN-01074 | 036909C-JVD-TRN-01074, ROC-TPSK-CECO-T-00013, ROC-TPSK-CECO-T-00013_1 | IFA | 2019-04-01 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01074 |  | 2019-03-18 | 1
036909C-1012-PDS-1390-1251 | Piping Specialty Item – Datasheet Steam Drum Intermittent Blowdown Valve BVD-12001 - 16001 | B | 2019-07-15 | IFD | OL1-2P03-1251 | MP | 2019-07-16 | 036909C-JVD-TRN-02160 | 036909C-JVD-TRN-02160 | IFR | 2019-07-31 | 2019-08-16 | R1-No comments | TPSK-LSPA1-T-MP-02160 |  | 2019-07-16 | 2
036909C-1012-PDS-1390-1212 | Piping Specialty Item – Isokinetic Sampling Nozzle SP-12012 - 16012 | B | 2019-07-15 | IFD | OL1-2P03-1212 | MP | 2019-07-16 | 036909C-JVD-TRN-02160 | 036909C-JVD-TRN-02160 | IFR | 2019-07-31 | 2019-08-16 | R1-No comments | TPSK-LSPA1-T-MP-02160 |  | 2019-07-17 | 2
036909C-1012-PDS-1390-1204 | Piping Specialty Item – Datasheet Vent Silencer – PSV-1242A-B OutLet SP-12004-16004 | B | 2019-07-15 | IFD | OL1-2P03-1204 | MP | 2019-07-16 | 036909C-JVD-TRN-02162 | 036909C-JVD-TRN-02162 | IFR | 2019-07-31 | 2019-08-16 | R1-No comments | TPSK-LSPA1-T-MP-02162 |  | 2019-07-17 | 2
036909C-1011-PDS-1390-1151 | Piping Specialty Item – Datasheet Steam Drum Intermittent Blowdown Valve BVD-11001 | B | 2019-07-15 | IFD | OL1-2P03-1151 | MP | 2019-07-16 | 036909C-JVD-TRN-02160 | 036909C-JVD-TRN-02160 | IFR | 2019-07-31 | 2019-08-16 | R1-No comments | TPSK-LSPA1-T-MP-02160 |  | 2019-07-17 | 2
036909C-1012-TBT-1546-2203 | Technical Bid Tabulation for Restriction Orifice | 0 | 2019-07-30 | IFI | OL1-2C23-2203 | PL | 2019-07-31 | 036909C-JVD-TRN-02305 | 036909C-JVD-TRN-02305 | IFR | 2019-08-15 | 2019-08-16 | R1-No comments | TPSK-LSPA1-T-PL-02305 |  | 2019-08-01 | 2
036909C-1056-SP-0910-5645 | MECHANICAL EQUIPMENT DATASHEET - Oily Wastewater EQ Tank Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-5645 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1056-SP-0910-5641 | MECHANICAL EQUIPMENT DATASHEET - Wastewater EQ Tank Skimmed Oil Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-5641 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1055-SP-0910-5566 | MECHANICAL EQUIPMENT DATASHEET - Polyolefins Flare Knock-Out Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-5566 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1055-SP-0910-5551 | MECHANICAL EQUIPMENT DATASHEET - HP Flare Knock-Out Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-5551 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-103S-DW-1933-0001 | Fire Protection & Firefighting Layout - Zone 3S Electrical Substation & Far C | D | 2019-08-09 | IBD | OL1-2F30-0002 | FF | 2019-08-15 | 036909C-JVD-TRN-02441 | 036909C-JVD-TRN-02441 | IFR | 2019-08-29 |  | Transmitted | TPSK-LSPA1-T-FF-02441 |  | 2019-08-16 | 2
036909C-103A-DW-1743-0030 | Foundation For 10-E-3045 A/B/C/D | A | 2019-08-08 | IFR | OL1-2K31-0237 | CV | 2019-08-15 | 036909C-JVD-TRN-02439 | 036909C-JVD-TRN-02439 | IFR | 2019-08-29 |  | Transmitted | TPSK-LSPA1-T-CV-02439 |  | 2019-08-16 | 2
036909C-103A-DW-1743-0043 | Foundation For 10-E-3018 A/B | A | 2019-08-08 | IFR | OL1-2K31-0344 | CV | 2019-08-15 | 036909C-JVD-TRN-02439 | 036909C-JVD-TRN-02439 | IFR | 2019-08-29 |  | Transmitted | TPSK-LSPA1-T-CV-02439 |  | 2019-08-16 | 2
036909C-103A-DW-1743-0035 | Foundation For 10-E-3070 | A | 2019-08-08 | IFR | OL1-2K31-0242 | CV | 2019-08-15 | 036909C-JVD-TRN-02439 | 036909C-JVD-TRN-02439 | IFR | 2019-08-29 |  | Transmitted | TPSK-LSPA1-T-CV-02439 |  | 2019-08-16 | 2
036909C-103A-DW-1743-0031 | Foundation For 10-E-3044 | A | 2019-08-08 | IFR | OL1-2K31-0238 | CV | 2019-08-15 | 036909C-JVD-TRN-02439 | 036909C-JVD-TRN-02439 | IFR | 2019-08-29 |  | Transmitted | TPSK-LSPA1-T-CV-02439 |  | 2019-08-16 | 2
036909C-1031-PDS-1390-3123 | Piping Specialty Item - Datasheet - Steam Trap - LP Condensate from E-3150 - 10-STT-31005 | A | 2019-08-11 | IFR | OL1-2P03-3123 | MP | 2019-08-12 | 036909C-JVD-TRN-02419 | 036909C-JVD-TRN-02419 | IFR | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-MP-02419 |  | 2019-08-14 | 2
036909C-1031-PDS-1390-3114 | Piping Specialty Item - Datasheet - Steam Trap - LP Condensate D-3100 Jacket - STT-31003 | A | 2019-08-11 | IFR | OL1-2P03-3114 | MP | 2019-08-12 | 036909C-JVD-TRN-02419 | 036909C-JVD-TRN-02419 | IFR | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-MP-02419 |  | 2019-08-14 | 2
036909C-1031-PDS-1390-3108 | Piping Specialty Item - Datasheet - Steam Trap - D-3190 Heating Coil Outlet - 10-STT-31001 | A | 2019-08-11 | IFR | OL1-2P03-3108 | MP | 2019-08-12 | 036909C-JVD-TRN-02419 | 036909C-JVD-TRN-02419 | IFR | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-MP-02419 |  | 2019-08-14 | 2
036909C-1031-PDS-1390-3111 | Piping Specialty Item - Datasheet - Steam Trap - D-3180 Heating Coil Outlet - 10-STT-31004 | A | 2019-08-11 | IFR | OL1-2P03-3111 | MP | 2019-08-12 | 036909C-JVD-TRN-02419 | 036909C-JVD-TRN-02419 | IFR | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-MP-02419 |  | 2019-08-14 | 2
036909C-1031-PDS-1390-3115 | Piping Specialty Item - Datasheet - Steam Trap - LP Condensate from D-3100 Jacket LP Steam Inlet Line - STT-31002 | A | 2019-08-11 | IFR | OL1-2P03-3115 | MP | 2019-08-12 | 036909C-JVD-TRN-02419 | 036909C-JVD-TRN-02419 | IFR | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-MP-02419 |  | 2019-08-14 | 2
036909C-1030-PDS-1390-3031 | Piping Specialty Item - Datasheet - Steam Trap - E-3055 A-B MP Condensate Outlet - STT-30001 | A | 2019-08-10 | IFR | OL1-2P03-3031 | MP | 2019-08-12 | 036909C-JVD-TRN-02419 | 036909C-JVD-TRN-02419 | IFR | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-MP-02419 |  | 2019-08-14 | 2
036909C-102B-CN-1832-0003 | Calculation Note for Steel Structure 10-STR-2B03 | A | 2019-07-30 | IFR | OL1-2K15-0108 | CV | 2019-08-13 | 036909C-JVD-TRN-02425 | 036909C-JVD-TRN-02426, 036909C-JVD-TRN-02425 | IFA | 2019-08-28 |  | Transmitted | TPSK-LSPA1-T-CV-02425 |  | 2019-08-15 | 1
036909C-102B-DW-1742-0003 | Foundation And Elevation For 10-STR-2B03 | A | 2019-07-30 | IFR | OL1-2K31-1460 | CV | 2019-08-13 | 036909C-JVD-TRN-02424 | 036909C-JVD-TRN-02425, 036909C-JVD-TRN-02424 | IFA | 2019-08-28 |  | Transmitted | TPSK-LSPA1-T-CV-02424 |  | 2019-08-15 | 1
036909C-102B-DW-1743-0018 | Foundation For 10-F-2310A-B | A | 2019-08-09 | IFR | OL1-2K31-0083 | CV | 2019-08-12 | 036909C-JVD-TRN-02409 | 036909C-JVD-TRN-02409 | IFA | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-CV-02409 |  | 2019-08-14 | 1
036909C-102B-DW-1743-0017 | Foundation For 10-F-2320A-B | A | 2019-08-09 | IFR | OL1-2K31-0082 | CV | 2019-08-12 | 036909C-JVD-TRN-02409 | 036909C-JVD-TRN-02409 | IFA | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-CV-02409 |  | 2019-08-14 | 1
036909C-1027-PDS-1390-2717 | Piping Specialty Item - Datasheet - Liquid Drain Trap - D-2735 Drain to OWD - STT-27001 | A | 2019-08-12 | IFR | OL1-2P03-2717 | MP | 2019-08-12 | 036909C-JVD-TRN-02419 | 036909C-JVD-TRN-02419 | IFR | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-MP-02419 |  | 2019-08-14 | 2
036909C-1026-SP-0910-2633 | MECHANICAL EQUIPMENT DATASHEET - Secondary Deeth Reflux Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2633 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1021-SP-0910-2191 | MECHANICAL EQUIPMENT DATASHEET - Quench Water Drain Drum Pump | 0 | 2019-08-09 | IFP | OL1-2M03-2191 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1021-PDS-1390-2107 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - Quench Water Tower T-2100 Vacuum Protection - ILK-21003 | B | 2019-08-11 | IFR | OL1-2P03-2107 | MP | 2019-08-12 | 036909C-JVD-TRN-02419 | 036909C-JVD-TRN-02419 | IFR | 2019-08-27 |  | Transmitted | TPSK-LSPA1-T-MP-02419 |  | 2019-08-14 | 2
036909C-1021-SP-0910-2126 | MECHANICAL EQUIPMENT DATASHEET - Distillate Stripper Bottom Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2126 | ME | 2019-08-09 | 036909C-JVD-TRN-02405 | 036909C-JVD-TRN-02405 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-14 | 2
036909C-1012-DW-0130-2554 | USC 36M Recycle & 132U Cracking Furnace Standards Typical Peep Door Details | 2 | 2019-08-12 | IMP | OL1-2M06-2554 | ME | 2019-08-12 | 036909C-JVD-TRN-02417 | 036909C-JVD-TRN-02417 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-02417 |  | 2019-08-14 | 3
036909C-100S-DW-1933-0001 | Fire Protection & Firefighting Layout - Zone 0S Electrical Substation & Far E | D | 2019-08-09 | IBD | OL1-2F30-0001 | FF | 2019-08-15 | 036909C-JVD-TRN-02441 | 036909C-JVD-TRN-02441 | IFR | 2019-08-29 |  | Transmitted | TPSK-LSPA1-T-FF-02441 |  | 2019-08-16 | 2
036909C-1000-MS-1393-0002 | Job Specification For Air Blowing Of Piping & Equipment | A | 2019-08-12 | IFR | OL1-2O71-0002 | PE | 2019-08-13 | 036909C-JVD-TRN-INTERNAL-00396 | 036909C-JVD-TRN-02426 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02426 |  | 2019-08-15 | 2
036909C-1000-MS-1393-0001 | Job Specification For Water Flushing Of Piping & Equipment | A | 2019-08-12 | IFR | OL1-2O71-0001 | PE | 2019-08-13 | 036909C-JVD-TRN-INTERNAL-00396 | 036909C-JVD-TRN-02426 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02426 |  | 2019-08-15 | 2
036909C-1000-MR-0910-0008 | Material Requisition For API Centrifugal Pumps | 0 | 2019-08-09 | IFP | OL1-2C13-449000 | PL | 2019-08-09 | 036909C-JVD-TRN-02408 | 036909C-JVD-TRN-02408 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-PL-02408 |  | 2019-08-14 | 2
036909C-1000-MS-1593-0001 | Job Specification For Loop Check Execution | A | 2019-08-12 | IFR | OL1-2O71-0017 | PE | 2019-08-13 | 036909C-JVD-TRN-INTERNAL-00395 | 036909C-JVD-TRN-02426 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02426 |  | 2019-08-15 | 2
036909C-1000-MS-1393-0015 | Job Specification For Relief Valves Management | A | 2019-08-12 | IFR | OL1-2O71-0014 | PE | 2019-08-13 | 036909C-JVD-TRN-INTERNAL-00396 | 036909C-JVD-TRN-02426 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02426 |  | 2019-08-15 | 2
036909C-103S-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 3S ELECTRICAL SUBSTATION & FAR C | C | 2019-05-06 | IFR | OL1-2F30-0002 | FF | 2019-05-08 | 036909C-JVD-TRN-01612 | 036909C-JVD-TRN-01612, KLOC-TPSK-VSAFE-T-00008 | IFR | 2019-05-22 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-01612 |  | 2019-05-09 | 2
036909C-103S-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 3S ELECTRICAL SUBSTATION & FAR C | B | 2019-04-25 | IFR | OL1-2F30-0002 | FF | 2019-04-30 | 036909C-JVD-TRN-01519 | 036909C-JVD-TRN-01519, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-05-14 |  | Transmitted | TPSK-LSPA1-T-FF-01519 |  | 2019-05-02 | 2
036909C-103S-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 3S ELECTRICAL SUBSTATION & FAR C | A | 2019-04-05 | IFR | OL1-2F30-0002 | FF | 2019-04-08 | 036909C-JVD-TRN-01270 | 036909C-JVD-TRN-01270, KLOC-TPSK-VSAFE-T-00003 | IFR | 2019-04-22 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01270 |  | 2019-04-08 | 2
036909C-100S-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 0S ELECTRICAL SUBSTATION & FAR E | A | 2019-04-05 | IFR | OL1-2F30-0001 | FF | 2019-04-08 | 036909C-JVD-TRN-01270 | 036909C-JVD-TRN-01270, KLOC-TPSK-VSAFE-T-00003 | IFR | 2019-04-22 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01270 |  | 2019-04-08 | 2
036909C-100S-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 0S ELECTRICAL SUBSTATION & FAR E | B | 2019-04-25 | IFR | OL1-2F30-0001 | FF | 2019-04-30 | 036909C-JVD-TRN-01519 | 036909C-JVD-TRN-01519, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-05-14 |  | Transmitted | TPSK-LSPA1-T-FF-01519 |  | 2019-05-02 | 2
036909C-100S-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 0S ELECTRICAL SUBSTATION & FAR E | C | 2019-05-06 | IFR | OL1-2F30-0001 | FF | 2019-05-08 | 036909C-JVD-TRN-01612 | 036909C-JVD-TRN-01612, KLOC-TPSK-VSAFE-T-00008 | IFR | 2019-05-22 | 2019-05-29 | R1-No comments | TPSK-LSPA1-T-FF-01612 |  | 2019-05-09 | 2
036909C-1051-SP-0214-0002 | Mechanical Equipment Datasheet For Condensate Carbon Filter Package | A | 2019-03-11 | IFQ | OL1-2M03-5115 | ME | 2019-03-13 | 036909C-JVD-TRN-01040 | 036909C-JVD-TRN-01040 | IFR | 2019-03-27 | 2019-04-01 | R1-No comments | TPSK-LSPA1-T-ME-01040 |  | 2019-03-13 | 2
036909C-1000-MR-0214-0001 | Material Requisition For Condensate Carbon Filter Package | A | 2019-03-11 | IFQ | OL1-2C13-151000 | PL | 2019-03-13 | 036909C-JVD-TRN-01039 | 036909C-JVD-TRN-01039 | IFR | 2019-03-27 | 2019-06-07 | R2-Comments as noted | TPSK-LSPA1-T-PL-01039 |  | 2019-03-13 | 2
036909C-1056-SP-0910-5648 | Mechanical Equipment Datasheet - C3 Hydrog Area Oily Wastewater Pump | B | 2019-02-13 | IFQ | OL1-2M03-5648 | ME | 2019-03-01 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962, ROC-TPSK-CECO-T-00016 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04 | 2
036909C-1056-SP-0910-5613 | Mechanical Equipment Datasheet - Refrig Area Oily Wastewater Pump | B | 2019-02-13 | IFQ | OL1-2M03-5613 | ME | 2019-03-01 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962, ROC-TPSK-CECO-T-00016 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04 | 2
036909C-1056-SP-0910-5609 | Mechanical Equipment Datasheet - CGC Area Oily Wastewater Pump | B | 2019-02-13 | IFQ | OL1-2M03-5609 | ME | 2019-03-01 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962, ROC-TPSK-CECO-T-00016 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04 | 2
036909C-1029-PID-0021-2920 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Quench Oil Pump Turbine Details | A | 2019-01-30 | IFR | OL1-2G43-2920 | PE | 2019-02-04 | 036909C-JVD-TRN-00799 | 036909C-JVD-TRN-00799, ROC-TPSK-CECO-T-00006 | IFR | 2019-02-18 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00799 |  | 2019-02-04 | 2
036909C-1056-SP-0910-5608 | Mechanical Equipment Datasheet - QW Area Oily Wastewater Pump | B | 2019-02-13 | IFQ | OL1-2M03-5608 | ME | 2019-03-01 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962, ROC-TPSK-CECO-T-00016 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04 | 2
036909C-1056-SP-0910-5607 | Mechanical Equipment Datasheet - Butadiene Area Oily Wastewater Pump | B | 2019-02-13 | IFQ | OL1-2M03-5607 | ME | 2019-03-01 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962, ROC-TPSK-CECO-T-00016 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04 | 2
036909C-1055-SP-0910-5566 | Mechanical Equipment Datasheet - Polyolefins Flare Knock-Out Pumps | B | 2019-04-18 | IFQ | OL1-2M03-5566 | ME | 2019-04-22 | 036909C-JVD-TRN-01426 | 036909C-JVD-TRN-01426 | IFR | 2019-05-07 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01426 |  | 2019-04-23 | 2
036909C-1055-SP-0910-5501 | Mechanical Equipment Datasheet - Hot Blowdown Pumps | B | 2019-01-31 | IFQ | OL1-2M03-5501 | ME | 2019-02-07 | 036909C-JVD-TRN-00822 | 036909C-JVD-TRN-00822 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00822 |  | 2019-02-07 | 2
036909C-1051-SP-0910-5141 | Mechanical Equipment Datasheet - Intermittent Blowdown Pumps | A | 2018-11-16 | IFQ | OL1-2M03-5141 | ME | 2018-11-19 | 036909C-JVD-TRN-00335 | 036909C-JVD-TRN-00335, ROC-TPSK-CECO-T-00016 | IFR | 2018-12-03 | 2018-12-13 | TPSK-LSPA1-E-00104 march 20 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-00335 |  | 2018-11-19 | 2
036909C-1051-SP-0910-5121 | Mechanical Equipment Datasheet - Raw Condensate Pumps | B | 2018-12-18 | IFQ | OL1-2M03-5121 | ME | 2018-12-20 | 036909C-JVD-TRN-00544 | 036909C-JVD-TRN-00544, ROC-TPSK-CECO-T-00016 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00544 |  | 2018-12-20 | 2
036909C-1051-SP-0910-5111 | Mechanical Equipment Datasheet - Suspect Condensate Pumps | B | 2018-12-18 | IFQ | OL1-2M03-5111 | ME | 2018-12-20 | 036909C-JVD-TRN-00544 | 036909C-JVD-TRN-00544, ROC-TPSK-CECO-T-00016 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00544 |  | 2018-12-20 | 2
036909C-1028-SP-0910-2855 | Mechanical Equipment Datasheet - Ethylene Product Pumps | B | 2019-01-31 | IFQ | OL1-2M03-2855 | ME | 2019-03-12 | 036909C-JVD-TRN-01035 | 036909C-JVD-TRN-01035, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-27 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-ME-01035 |  | 2019-03-13 | 2
036909C-1028-SP-0910-2816 | Mechanical Equipment Datasheet - Propylene Refrig Recovery Pump | B | 2019-01-31 | IFQ | OL1-2M03-2816 | ME | 2019-02-07 | 036909C-JVD-TRN-00822 | 036909C-JVD-TRN-00822, ROC-TPSK-CECO-T-00015 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00822 |  | 2019-02-07 | 2
036909C-1028-SP-0910-2801 | Mechanical Equipment Datasheet - Propylene Product Pumps | B | 2019-01-31 | IFQ | OL1-2M03-2801 | ME | 2019-03-12 | 036909C-JVD-TRN-01035 | 036909C-JVD-TRN-01035, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-27 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-ME-01035 |  | 2019-03-13 | 2
036909C-1027-SP-0910-2791 | Mechanical Equipment Datasheet - Light Oil Drain Drum Pump | B | 2019-04-25 | IFQ | OL1-2M03-2791 | ME | 2019-04-26 | 036909C-JVD-TRN-01493 | 036909C-JVD-TRN-01493 | IFR | 2019-05-13 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01493 |  | 2019-04-29 | 2
036909C-1026-SP-0910-2663 | Mechanical Equipment Datasheet - Debutanizer Reflux - Product Pumps | B | 2019-01-30 | IFQ | OL1-2M03-2663 | ME | 2019-02-07 | 036909C-JVD-TRN-00822 | 036909C-JVD-TRN-00822, ROC-TPSK-CECO-T-00015 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00822 |  | 2019-02-07 | 2
036909C-1026-SP-0910-2647 | Mechanical Equipment Datasheet - HP Propylene - Off Spec Pump | B | 2019-01-22 | IFQ | OL1-2M03-2647 | ME | 2019-01-30 | 036909C-JVD-TRN-00770 | 036909C-JVD-TRN-00770, ROC-TPSK-CECO-T-00015 | IFR | 2019-02-15 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00770 |  | 2019-01-31 | 2
036909C-1026-SP-0910-2646 | Mechanical Equipment Datasheet - Propane Recycle Pumps | A | 2018-12-18 | IFQ | OL1-2M03-2646 | ME | 2018-12-20 | 036909C-JVD-TRN-00543 | 036909C-JVD-TRN-00543, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-02 | 2019-01-16 | TPSK-LSPA1-E-00104 march 20 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-00543 |  | 2018-12-20 | 2
036909C-1026-SP-0910-2633 | Mechanical Equipment Data Sheet - Secondary Deeth Reflux Pumps | B | 2018-12-20 | IFQ | OL1-2M03-2633 | ME | 2018-12-20 | 036909C-JVD-TRN-00554 | 036909C-JVD-TRN-00554, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-03 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-ME-00554 |  | 2018-12-20 | 2
036909C-1026-SP-0910-2623 | Mechanical Equipment Datasheet - C3 Hydrog Recycle Pumps | B | 2019-03-25 | IFQ | OL1-2M03-2623 | ME | 2019-03-26 | 036909C-JVD-TRN-01158 | 036909C-JVD-TRN-01158 | IFR | 2019-04-10 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-ME-01158 |  | 2019-03-27 | 2
036909C-1025-SP-0910-2586 | Mechanical Equipment Datasheet - Ethane Recycle Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2586 | ME | 2018-12-05 | 036909C-JVD-TRN-00413 | 036909C-JVD-TRN-00413, ROC-TPSK-CECO-T-00015 | IFR | 2018-12-18 | 2018-12-27 | TPSK-LSPA1-E-00104 march 20 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-00413 |  | 2018-12-05 | 2
036909C-1025-SP-0910-2577 | Mechanical Equipment Datasheet - Deethanizer Reboiler Cond Pumps | A | 2018-12-05 | IFQ | OL1-2M03-2577 | ME | 2018-12-13 | 036909C-JVD-TRN-00494 | 036909C-JVD-TRN-00494, ROC-TPSK-CECO-T-00015 | IFR | 2018-12-26 | 2019-01-14 | TPSK-LSPA1-E-00104 march 20 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-00494 |  | 2018-12-13 | 2
036909C-1025-SP-0910-2573 | Mechanical Equipment Datasheet - Deethanizer Reflux Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2573 | ME | 2018-12-20 | 036909C-JVD-TRN-00552 | 036909C-JVD-TRN-00552, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-03 | 2019-01-16 | TPSK-LSPA1-E-00104 march 20 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-00552 |  | 2018-12-20 | 2
036909C-1024-SP-0910-2457 | Mechanical Equipment Datasheet - LP Deprop Reboiler Cond Pump | B | 2019-01-21 | IFQ | OL1-2M03-2457 | ME | 2019-01-30 | 036909C-JVD-TRN-00770 | 036909C-JVD-TRN-00770, ROC-TPSK-CECO-T-00015 | IFR | 2019-02-15 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00770 |  | 2019-01-31 | 2
036909C-1022-SP-0910-2222 | Mechanical Equipment Datasheet - CG 2nd Stage Condensed HC Pump | A | 2018-11-16 | IFQ | OL1-2M03-2222 | ME | 2018-11-20 | 036909C-JVD-TRN-00343 | 036909C-JVD-TRN-00343, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-04 | 2019-02-11 | TPSK-LSPA1-E-00105 March 20 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-00343 |  | 2018-11-20 | 2
036909C-1021-SP-0910-2126 | Mechanical Equipment Datasheet - Distillate Stripper Bottom Pumps | B | 2019-03-18 | IFQ | OL1-2M03-2126 | ME | 2019-03-20 | 036909C-JVD-TRN-01102 | 036909C-JVD-TRN-01102, ROC-TPSK-CECO-T-00014 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-ME-01102 |  | 2019-03-21 | 2
036909C-1021-SP-0910-2105 | Mechanical Equipment Datasheet - Quench Oil Reflux Pumps | B | 2019-03-28 | IFQ | OL1-2M03-2105 | ME | 2019-04-08 | 036909C-JVD-TRN-01279 | 036909C-JVD-TRN-01279 | IFR | 2019-04-23 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-ME-01279 |  | 2019-04-09 | 2
036909C-1021-SP-0910-2105 | Mechanical Equipment Datasheet - Quench Oil Reflux Pumps | A | 2018-11-23 | IFQ | OL1-2M03-2105 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00457 |  | 2018-12-10 | 2
036909C-1026-PID-0021-2630 | P&ID - Olefins Unit 10 - Hot Fractionation - C5-Pygas Surge Drum | B | 2019-03-14 | IFR | OL1-2G43-2630 | PE | 2019-03-14 | 036909C-JVD-TRN-01061 | 036909C-JVD-TRN-01061 | IFR | 2019-03-29 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-PE-01061 |  | 2019-03-15 | 2
036909C-1000-MR-1309-0001 | Material Requisition For Carbon Steel Underground Piping | A | 2019-02-27 | IFQ | OL1-2C14-360001 | PL | 2019-03-01 | 036909C-JVD-TRN-00969 | 036909C-JVD-TRN-00969 | IFR | 2019-03-18 | 2019-06-06 | R2-Comments as noted | TPSK-LSPA1-T-PL-00969 |  | 2019-03-04 | 2
036909C-1011-SP-1552-1005 | USC 36M and USC 132U Instrument Datasheets for Level Gauge | A | 2019-03-07 | IFR | OL1-2I20-1005 | IE | 2019-03-13 | 036909C-JVD-TRN-01047 | 036909C-JVD-TRN-01047 | IFR | 2019-03-28 | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-IE-01047 |  | 2019-03-14 | 2
036909C-1039-PDS-0800-3910 | Process Equipment Data Sheet - 10-D-3908 - Predistillation Inhibitor Drum | B | 2019-06-05 | IFD | OL1-2G30-3910 | PE | 2019-06-06 | 036909C-JVD-TRN-01826 | 036909C-JVD-TRN-01826 | IFR | 2019-06-21 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01826 |  | 2019-06-10 | 2
036909C-1039-PDS-0800-3906 | Process Equipment Data Sheet - 10-D-3906 - BDU Anti Foam Agent Drum | B | 2019-06-05 | IFD | OL1-2G30-3906 | PE | 2019-06-06 | 036909C-JVD-TRN-01826 | 036909C-JVD-TRN-01826 | IFR | 2019-06-21 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01826 |  | 2019-06-10 | 2
036909C-1039-PDS-0800-3904 | Process Equipment Data Sheet - 10-D-3904 - BDU Solvent Inhibitor Drum | B | 2019-06-05 | IFD | OL1-2G30-3904 | PE | 2019-06-06 | 036909C-JVD-TRN-01826 | 036909C-JVD-TRN-01826 | IFR | 2019-06-21 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01826 |  | 2019-06-10 | 2
036909C-1039-PDS-0800-3902 | Process Equipment Data Sheet - 10-D-3902 - BDU Solvent Inhibitor Drum | B | 2019-06-05 | IFD | OL1-2G30-3902 | PE | 2019-06-10 | 036909C-JVD-TRN-01849 | 036909C-JVD-TRN-01849 | IFR | 2019-06-25 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01849 |  | 2019-06-11 | 2
036909C-1031-PDS-0800-3151 | Process Equipment Data Sheet - 10-D-3150 - BDU Condensate Flash Drum | B | 2019-06-04 | IFD | OL1-2G30-3151 | PE | 2019-06-05 | 036909C-JVD-TRN-01813 | 036909C-JVD-TRN-01813 | IFR | 2019-06-20 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01813 |  | 2019-06-10 | 2
036909C-1012-MR-1552-2005 | Material Requisition for Level Gauges | A | 2019-04-09 | IFQ | OL1-2C17-022005 | PL | 2019-04-17 | 036909C-JVD-TRN-01393 | 036909C-JVD-TRN-01393 | IFI |  | 2019-05-28 | R2-Comments as noted | TPSK-LSPA1-T-PL-01393 |  | 2019-04-18 | 3
036909C-1023-DI-0007-2301 | Area Basis of Design - 23 Caustic and Spent Caustic Pretreatment | A | 2018-08-08 | IFA | OL1-2G05-2301 | PE | 2018-08-08 | 036909C-JVD-TRN-00014 | 036909C-JVD-TRN-00014, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-22 | 2018-08-31 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00014 |  | 2018-08-09 | 1
036909C-1023-DI-0007-2301 | Area Basis of Design - 23 Caustic and Spent Caustic Pretreatment | B | 2019-04-10 | IFD | OL1-2G05-2301 | PE | 2019-04-11 | 036909C-JVD-TRN-01317 | 036909C-JVD-TRN-01317 | IFA | 2019-04-26 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01317 |  | 2019-04-12 | 1
036909C-1000-DW-1532-0003 | Telecomm Syst Architecture Of Intercom Paging and Audible Alarm Systems | A | 2019-03-01 | IFR | OL1-2T11-0001 | EE | 2019-03-04 | 036909C-JVD-TRN-00976 | 036909C-JVD-TRN-00976, ROC-TPSK-CECO-T-00012 | IFA | 2019-03-19 | 2019-03-21 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00976 |  | 2019-03-05 | 1
036909C-1059-PDS-1390-5918 | Piping Specialty Item - Datasheet - T-Type Filter - P-5955 A-B Suction - SRT-59006 | A | 2019-07-17 | IFR | OL1-2P03-5918 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1059-PDS-1390-5917 | Piping Specialty Item - Datasheet - T-Type Filter - P-5905 A-B Suction - SRT-59005 | A | 2019-07-17 | IFR | OL1-2P03-5917 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1059-PDS-1390-5915 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5105 A Inlet - SRT-51031 | A | 2019-07-17 | IFR | OL1-2P03-5915 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1059-PDS-1390-5914 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5102 A Inlet - SRT-51026 | A | 2019-07-17 | IFR | OL1-2P03-5914 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-22 | 2
036909C-1059-PDS-1390-5912 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5101 A Inlet - SRT-51029 | A | 2019-07-17 | IFR | OL1-2P03-5912 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1059-PDS-1390-5910 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5100 A-B Inlet - SRT-59002 | A | 2019-07-17 | IFR | OL1-2P03-5910 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1059-PDS-1390-5909 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5360 A Inlet - SRT-51011 | A | 2019-07-17 | IFR | OL1-2P03-5909 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1059-PDS-1390-5906 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5350 A-B-C Inlet - SRT- 51010 | A | 2019-07-17 | IFR | OL1-2P03-5906 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1059-PDS-1390-5905 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5110 A Inlet - SRT-51012 | A | 2019-07-17 | IFR | OL1-2P03-5905 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1059-PDS-1390-5904 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5901 A-B Suction - SRT-59003 | A | 2019-07-17 | IFR | OL1-2P03-5904 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1059-PDS-1390-5903 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5950 A-B Suction - SRT-59001 | A | 2019-07-17 | IFR | OL1-2P03-5903 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1059-PDS-1390-5902 | Piping Specialty Item - Datasheet - T-Type Filter - P-5900 A-B Suction - SRT-59004 | A | 2019-07-17 | IFR | OL1-2P03-5902 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1056-PDS-1390-5614 | Piping Specialty Item - Datasheet - T-Type Filter - P-5653 A-B Suction - SRT-56009 | A | 2019-07-17 | IFR | OL1-2P03-5614 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1056-PDS-1390-5613 | Piping Specialty Item - Datasheet - T-Type Filter - P-5656 A-B Suction - SRT-56008 | A | 2019-07-17 | IFR | OL1-2P03-5613 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1056-PDS-1390-5607 | Piping Specialty Item - Datasheet - T-Type Filter - P-5676 Suction - SRT-56001 | A | 2019-07-17 | IFR | OL1-2P03-5607 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1056-PDS-1390-5606 | Piping Specialty Item - Datasheet - T-Type Filter - P-5675 Suction - SRT-56004 | A | 2019-07-17 | IFR | OL1-2P03-5606 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1056-PDS-1390-5605 | Piping Specialty Item - Datasheet - T-Type Filter - P-5641 Suction - SRT-56003 | A | 2019-07-17 | IFR | OL1-2P03-5605 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1056-PDS-1390-5604 | Piping Specialty Item - Datasheet - T-Type Filter - P-5640 A-B Suction - SRT-56007 | A | 2019-07-17 | IFR | OL1-2P03-5604 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1056-PDS-1390-5603 | Piping Specialty Item - Datasheet - T-Type Filter - P-5655 A-C Suction - SRT-56006 | A | 2019-07-17 | IFR | OL1-2P03-5603 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1056-PDS-1390-5602 | Piping Specialty Item - Datasheet - T-Type Filter - P-5621 Suction - SRT-56002 | A | 2019-07-17 | IFR | OL1-2P03-5602 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1056-PDS-1390-5601 | Piping Specialty Item - Datasheet - T-Type Filter - P-5620 A-C Suction - SRT-56005 | A | 2019-07-17 | IFR | OL1-2P03-5601 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1055-PDS-1390-5522 | Piping Specialty Item - Datasheet - T-Type Filter - p-5565 A-B Suction - SRT-55002 | A | 2019-07-16 | IFR | OL1-2P03-5522 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1055-PDS-1390-5521 | Piping Specialty Item - Datasheet - T-Type Filter - P-5550 A-B Suction - SRT-55001 | A | 2019-07-16 | IFR | OL1-2P03-5521 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1055-PDS-1390-5501 | Piping Specialty Item - Datasheet - T-Type Filter - p-5500 A-B Suction - SRT-55003 | A | 2019-07-16 | IFR | OL1-2P03-5501 | MP | 2019-07-22 | 036909C-JVD-TRN-02215 | 036909C-JVD-TRN-02215 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-MP-02215 |  | 2019-07-23 | 2
036909C-1055-TDS-0610-5553 | Mechanical Equipment Data Sheet - 10-E-5552 - LPG Vaporizer / Superheater | 0 | 2019-07-12 | Issue for Purchase | OL1-2M03-5553 | ME | 2019-07-22 | 036909C-JVD-TRN-02208 | 036909C-JVD-TRN-02208 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02208 |  | 2019-07-23 | 2
036909C-1052-TDS-0610-5210 | Mechanical Equipment Data Sheet - 10-E-5210 - Pilot Gas Vaporizer | 0 | 2019-07-12 | Issue for Purchase | OL1-2M03-5210 | ME | 2019-07-22 | 036909C-JVD-TRN-02208 | 036909C-JVD-TRN-02208 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02208 |  | 2019-07-23 | 2
036909C-1028-SP-0810-2865 | Mechanical Equipment Data Sheet For C2R Drain Drum | 0 | 2019-07-17 | Issue for Purchase | OL1-2M03-2865 | ME | 2019-07-22 | 036909C-JVD-TRN-02207 | 036909C-JVD-TRN-02207 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02207 |  | 2019-07-23 | 2
036909C-1028-SP-0810-2860 | Mechanical Equipment Data Sheet C2R 1ST Stage Suction Drum | 0 | 2019-07-17 | Issue for Purchase | OL1-2M03-2860 | ME | 2019-07-22 | 036909C-JVD-TRN-02207 | 036909C-JVD-TRN-02207 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02207 |  | 2019-07-23 | 2
036909C-1028-SP-0810-2854 | Mechanical Equipment Data Sheet for C2R Surge Drum | 0 | 2019-07-17 | Issue for Purchase | OL1-2M03-2854 | ME | 2019-07-22 | 036909C-JVD-TRN-02207 | 036909C-JVD-TRN-02207 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02207 |  | 2019-07-23 | 2
036909C-1027-SP-0810-2706 | Mechanical Equipment Data Sheet GHU-1 Cold Separator | 0 | 2019-07-16 | Issue for Purchase | OL1-2M03-2706 | ME | 2019-07-22 | 036909C-JVD-TRN-02207 | 036909C-JVD-TRN-02207 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02207 |  | 2019-07-23 | 2
036909C-1026-TDS-0610-2666 | Mechanical Equipment Data Sheet - 10-E-2666 - Debutanizer Bottoms Cooler | 0 | 2019-07-12 | Issue for Purchase | OL1-2M03-2666 | ME | 2019-07-22 | 036909C-JVD-TRN-02212 | 036909C-JVD-TRN-02212 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02212 |  | 2019-07-23 | 2
036909C-1025-SP-0810-2551 | Mechanical Equipment Data Sheet Expander Suction Drum | 0 | 2019-07-17 | Issue for Purchase | OL1-2M03-2551 | ME | 2019-07-22 | 036909C-JVD-TRN-02207 | 036909C-JVD-TRN-02207 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02207 |  | 2019-07-23 | 2
036909C-1025-SP-0810-2525 | Mechanical Equipment Data Sheet for Hydrogen Drum | 0 | 2019-07-17 | Issue for Purchase | OL1-2M03-2525 | HOC Mech | 2019-07-22 | 036909C-JVD-TRN-02207 | 036909C-JVD-TRN-02207 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02207 |  | 2019-07-22 | 2
036909C-1025-SP-0810-2508 | Mechanical Equipment Data Sheet Demeth Prefrac Feed Separator No. 3 | 0 | 2019-07-17 | Issue for Purchase | OL1-2M03-2508 | ME | 2019-07-22 | 036909C-JVD-TRN-02207 | 036909C-JVD-TRN-02207 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02207 |  | 2019-07-23 | 2
036909C-1025-SP-0810-2506 | Mechanical Equipment Data Sheet Demeth Prefrac Feed Separator No. 2 | 0 | 2019-07-17 | Issue for Purchase | OL1-2M03-2506 | ME | 2019-07-22 | 036909C-JVD-TRN-02207 | 036909C-JVD-TRN-02207 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02207 |  | 2019-07-23 | 2
036909C-1024-TDS-0610-2455 | Mechanical Equipment Data Sheet - 10-E-2455 AB - LP Depropanizer Reboilers | 0 | 2019-07-09 | Issue for Purchase | OL1-2M03-2455 | ME | 2019-07-22 | 036909C-JVD-TRN-02212 | 036909C-JVD-TRN-02212 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02212 |  | 2019-07-23 | 2
036909C-1024-TDS-0610-2445 | Mechanical Equipment Data Sheet - 10-E-2445 - HP Depropanizer Reboiler | 0 | 2019-07-08 | Issue for Purchase | OL1-2M03-2445 | ME | 2019-07-22 | 036909C-JVD-TRN-02212 | 036909C-JVD-TRN-02212 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02212 |  | 2019-07-23 | 2
036909C-1024-TDS-0610-2442 | Mechanical Equipment Data Sheet - 10-E-2442 - HP Deprop Reflux Chiller no. 1 | 0 | 2019-07-08 | Issue for Purchase | OL1-2M03-2442 | ME | 2019-07-22 | 036909C-JVD-TRN-02212 | 036909C-JVD-TRN-02212 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02212 |  | 2019-07-23 | 2
036909C-1023-SP-0810-2310 | Mechanical Equipment Data Sheet Spent Caustic Deoiling Drum | 0 | 2019-07-18 | Issue for Purchase | OL1-2M03-2310 | ME | 2019-07-18 | 036909C-JVD-TRN-02188 | 036909C-JVD-TRN-02188 | IFR | 2019-08-02 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-ME-02188 |  | 2019-07-19 | 2
036909C-1025-SP-1513-2502 | Instrument Interlock Descriptions Area 25 Cold Fractionation | B | 2019-07-19 | IBD | OL1-2G50-2502 | PE | 2019-07-22 | 036909C-JVD-TRN-02230 | 036909C-JVD-TRN-02230 | IFR | 2019-08-06 | 2019-08-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-02230 |  | 2019-07-23 | 2
036909C-1056-PDS-0200-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg | E | 2019-07-18 | IFD | OL1-2G30-5653 | PE | 2019-07-22 | 036909C-JVD-TRN-02214 | 036909C-JVD-TRN-02214 | IFR | 2019-08-06 | 2019-08-15 | R1-No comments | TPSK-LSPA1-T-PE-02214 |  | 2019-07-23 | 2
036909C-1056-PDS-2600-5690 | Process Equipment Datasheet - 10-PK-5690 - Slop Tank Polymer Injection Pkg | C | 2019-07-18 | IFD | OL1-2G30-5690 | PE | 2019-07-22 | 036909C-JVD-TRN-02214 | 036909C-JVD-TRN-02214 | IFR | 2019-08-06 | 2019-08-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-02214 |  | 2019-07-23 | 2
036909C-1056-PDS-2600-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package | E | 2019-07-18 | IFD | OL1-2G30-5644 | PE | 2019-07-22 | 036909C-JVD-TRN-02214 | 036909C-JVD-TRN-02214 | IFR | 2019-08-06 | 2019-08-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-02214 |  | 2019-07-23 | 2
036909C-1012-MR-1546-2052 | Material Requisition for Orifice Plate | A | 2019-07-17 | IFQ | OL1-2C17-012052 | PL | 2019-07-23 | 036909C-JVD-TRN-02244 | 036909C-JVD-TRN-02244 | IFR | 2019-08-07 | 2019-08-15 | R2-Comments as noted | TPSK-LSPA1-T-PL-02244 |  | 2019-07-24 | 2
036909C-1056-SP-1513-5602 | Instrument Interlock Descriptions Area 56 Wastewater | B | 2019-07-19 | IBD | OL1-2G50-5602 | IE | 2019-07-22 | 036909C-JVD-TRN-02210 | 036909C-JVD-TRN-02210 | IFR | 2019-08-06 | 2019-08-15 | R2-Comments as noted | TPSK-LSPA1-T-IE-02210 |  | 2019-07-23 | 2
036909C-1055-SP-1513-5502 | Instrument Interlock Descriptions Area 55 Vent Gas and Flare System | B | 2019-07-19 | IBD | OL1-2G50-5502 | IE | 2019-07-22 | 036909C-JVD-TRN-02210 | 036909C-JVD-TRN-02210 | IFR | 2019-08-06 | 2019-08-15 | R2-Comments as noted | TPSK-LSPA1-T-IE-02210 |  | 2019-07-23 | 2
036909C-1000-MR-1530-0001 | Material Requisition For Intercom Paging Audible Alarm System | 0 | 2019-07-31 | IFP | OL1-2C16-881000 | PL | 2019-08-01 | 036909C-JVD-TRN-02306 | 036909C-JVD-TRN-02306 | IFR | 2019-08-15 | 2019-08-14 | R1-No comments | TPSK-LSPA1-T-PL-02306 |  | 2019-08-01 | 2
036909C-1056-SP-0910-5624 | Mechanical Equipment Datasheet - Gate 4 Septic Tank Pumps | B | 2019-04-12 | IFQ | OL1-2M03-5624 | ME | 2019-04-15 | 036909C-JVD-TRN-01363 | 036909C-JVD-TRN-01363 | IFR | 2019-04-30 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-ME-01363 |  | 2019-04-16 | 2
036909C-1056-SP-0910-5623 | Mechanical Equipment Datasheet - FAR C Septic Tank Pumps | B | 2019-04-12 | IFQ | OL1-2M03-5623 | ME | 2019-04-15 | 036909C-JVD-TRN-01363 | 036909C-JVD-TRN-01363 | IFR | 2019-04-30 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-ME-01363 |  | 2019-04-16 | 2
036909C-1000-DL-1530-0002 | Deviation List For Safety Supervisory System | 0 | 2019-07-30 | IFP | OL1-2C42-851000 | PL | 2019-07-31 | 036909C-JVD-TRN-02300 | 036909C-JVD-TRN-02300 | IFR | 2019-08-14 | 2019-08-14 | R1-No comments | TPSK-LSPA1-T-PL-02300 |  | 2019-08-01 | 2
036909C-1023-PFD-0010-2304 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | C | 2019-04-26 | IFD | OL1-2G41-2304 | PE | 2019-04-29 | 036909C-JVD-TRN-01516 | 036909C-JVD-TRN-01516, ROC-TPSK-CECO-T-00064 | IFA | 2019-05-14 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01516 |  | 2019-04-30 | 1
036909C-1000-MR-0910-0001 | Material Requisition For API Centrifugal Pumps - LLI | 0 | 2019-07-05 | IFP | OL1-2C13-441000 | PL | 2019-07-08 | 036909C-JVD-TRN-02095 | 036909C-JVD-TRN-02095 | IFR | 2019-07-23 | 2019-07-18 | R2-Comments as noted | TPSK-LSPA1-T-PL-02095 | Umbrella Contract for API Mechanical Seals And Seal System | 2019-07-09 | 2
036909C-105W-DW-1331-0001 | GAD KEY PLAN - ZONE 5W - WASTE WATER TREATMENT | A | 2019-04-16 | IFR | OL1-2P06-0085 | MP | 2019-04-17 | 036909C-JVD-TRN-01394 | 036909C-JVD-TRN-01394, ROC-TPSK-CECO-T-00052 | IFR | 2019-05-02 | 2019-06-14 | R2-Comments as noted | TPSK-LPSA1-T-MP-01394 |  | 2019-04-18 | 2
036909C-105W-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 5W Waste Water Treatment | B | 2019-07-01 | IBD | OL1-2F75-0004 | FF | 2019-07-02 | 036909C-JVD-TRN-02050 | 036909C-JVD-TRN-02050 | IFR | 2019-07-16 |  | Transmitted | TPSK-LSPA1-T-FF-02050 |  | 2019-07-03 | 2
036909C-105W-DW-1950-5015 | FIRE & GAS DEVICES LAYOUT - ZONE 5W - WASTE WATER TREATMENT | B | 2019-04-26 | IFR | OL1-2F40-5015 | FF | 2019-04-30 | 036909C-JVD-TRN-01518 | 036909C-JVD-TRN-01518, KLOC-TPSK-VSAFE-T-00007, KLOC-TPSK-CECO-T-00008 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-FF-01518 |  | 2019-05-02 | 2
036909C-1056-PDS-0200-5655 | Process Equipment Datasheet - 10-PIT-5655 - Bio Equalization Pit | C | 2019-06-21 | IFD | OL1-2G30-5655 | PE | 2019-06-24 | 036909C-JVD-TRN-01981 | 036909C-JVD-TRN-01981 | IFR | 2019-07-08 | 2019-07-17 | R1-No comments | TPSK-LSPA1-T-PE-01981 |  | 2019-06-25 | 2
036909C-1056-PDS-0900-5677 | Process Equipment Datasheet - 10-P-5676 - Oily Sludge Transfer Pump | B | 2019-03-21 | IFD | OL1-2G30-5677 | PE | 2019-03-25 | 036909C-JVD-TRN-01152 | 036909C-JVD-TRN-01152, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-09 | 2019-04-12 | CLIENT-COMMENT-TRN-01310- June 18 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01152 |  | 2019-03-26 | 2
036909C-1056-PDS-0200-5656 | Process Equipment Datasheet - 10-PIT-5656 - Final Check Basin | B | 2019-03-26 | IFD | OL1-2G30-5656 | PE | 2019-03-27 | 036909C-JVD-TRN-01178 | 036909C-JVD-TRN-01178, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-11 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01178 |  | 2019-03-28 | 2
036909C-1056-PDS-0900-5674 | Process Equipment Datasheet - 10-P-5675 - Slop Oil Transfer Pump | B | 2019-03-21 | IFD | OL1-2G30-5674 | PE | 2019-03-25 | 036909C-JVD-TRN-01152 | 036909C-JVD-TRN-01152, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-09 | 2019-04-12 | CLIENT-COMMENT-TRN-01310- June 18 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01152 |  | 2019-03-26 | 2
036909C-1000-JSS-1693-0001 | Low Voltage Variable Voltage Variable Frequency System | 0 | 2018-09-20 | IMP | OL1-2R05-0023 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | 2018-11-05 | 3
036909C-1056-PDS-0900-5654 | Process Equipment Datasheet - 10-P-5655 A-B-C - Equalization Pit Pumps | B | 2019-03-21 | IFD | OL1-2G30-5654 | PE | 2019-03-25 | 036909C-JVD-TRN-01152 | 036909C-JVD-TRN-01152, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-09 | 2019-04-12 | CLIENT-COMMENT-TRN-01310- June 18 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01152 |  | 2019-03-26 | 2
036909C-1000-JSD-1515-0004 | Machinery Monitoring System | 0 | 2019-02-18 | IMP | OL1-2R06-0013 | IE | 2019-02-19 | 036909C-JVD-TRN-00889 | 036909C-JVD-TRN-00889, ROC-TPSK-CECO-T-00004 | IFR | 2019-03-06 | 2019-03-08 | R1-No comments | TPSK-LSPA1-T-IE-00889 |  | 2019-02-19 | 2
036909C-1056-PDS-0900-5657 | Process Equipment Datasheet - 10-P-5656 A-B - Final Check Basin Pumps | B | 2019-04-26 | IFD | OL1-2G30-5657 | PE | 2019-04-26 | 036909C-JVD-TRN-01512 | 036909C-JVD-TRN-01512 | IFR | 2019-05-13 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-PE-01512 |  | 2019-04-29 | 2
036909C-1000-JSS-1040-0001 | ME-017 Root Blower | 0 | 2018-11-16 | IMP | OL1-2R03-0017 | ME | 2018-11-19 | 036909C-JVD-TRN-00334 | 036909C-JVD-TRN-00334, ROC-TPSK-CECO-T-00003 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00334 |  | 2018-11-19 | 3
036909C-1000-JSS-1692-0001 | Electrical Motors Greater Than 300 kW | 0 | 2018-09-20 | IMP | OL1-2R05-0011 | EE | 2018-11-08 | 036909C-JVD-TRN-00293 | 036909C-JVD-TRN-00293, 036909C-JVD-TRN-00748 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-EE-00748 |  | 2018-11-08 | 2
036909C-1024-SP-0910-2453 | Mechanical Equipment Datasheet - LP Depropanizer Reflux - Product Pump | B | 2019-02-27 | IFQ | OL1-2M03-2453 | ME | 2019-02-27 | 036909C-JVD-TRN-00944 | 036909C-JVD-TRN-00944, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-14 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00944 |  | 2019-02-28 | 2
036909C-1024-SP-0910-2443 | Mechanical Equipment Datasheet - HP Deprop Reboiler Cond Pump | B | 2019-01-21 | IFQ | OL1-2M03-2443 | ME | 2019-01-30 | 036909C-JVD-TRN-00770 | 036909C-JVD-TRN-00770, ROC-TPSK-CECO-T-00014 | IFR | 2019-02-15 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00770 |  | 2019-01-31 | 2
036909C-1024-SP-0910-2416 | Mechanical Equipment Datasheet - CG Liquid Dryer Feed Pumps | B | 2019-01-21 | IFQ | OL1-2M03-2416 | ME | 2019-01-30 | 036909C-JVD-TRN-00770 | 036909C-JVD-TRN-00770, ROC-TPSK-CECO-T-00014 | IFR | 2019-02-15 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00770 |  | 2019-01-31 | 2
036909C-1023-SP-0910-2393 | Mechanical Equipment Datasheet - Spent Caustic Drain Drum Pump | A | 2018-12-05 | IFQ | OL1-2M03-2393 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-21 | 2018-12-27 | TPSK-LSPA1-E-00104 march 20 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-00457 |  | 2018-12-10 | 2
036909C-1023-SP-0910-2391 | Mechanical Equipment Datasheet - Caustic Drain Drum Pump | B | 2019-01-28 | IFQ | OL1-2M03-2391 | ME | 2019-02-07 | 036909C-JVD-TRN-00822 | 036909C-JVD-TRN-00822, ROC-TPSK-CECO-T-00014 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00822 |  | 2019-02-07 | 2
036909C-1023-SP-0910-2321 | Mechanical Equipment Datasheet - Spent Caustic Pumps | A | 2018-11-16 | IFQ | OL1-2M03-2321 | ME | 2018-11-19 | 036909C-JVD-TRN-00335 | 036909C-JVD-TRN-00335, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-03 | 2018-12-13 | TPSK-LSPA1-E-00104 march 20 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-00335 |  | 2018-11-19 | 2
036909C-1023-SP-0910-2311 | Mechanical Equipment Datasheet - Wash Oil Circulating Pumps | A | 2018-11-13 | IFQ | OL1-2M03-2311 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320, ROC-TPSK-CECO-T-00014 | IFR | 2018-11-29 | 2018-12-10 | TPSK-LSPA1-E-00104 march 20 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-00320 |  | 2018-11-15 | 2
036909C-1000-MR-0910-0001 | Material Requisition For API Centrifugal Pumps - LLI | A | 2018-10-30 | IFQ | OL1-2M55-0015 | ME | 2018-10-31 | 036909C-JVD-TRN-00257 | 036909C-JVD-TRN-00257 | IFR | 2018-11-20 | 2018-11-27 | R1-No comments | TPSK-LSPA1-T-ME-00257 |  | 2018-10-31 | 2
036909C-1051-SP-0810-5114 | Mechanical Equipment Data Sheet for LP Condensate Flash Drum | 0 | 2019-07-12 | IFP | OL1-2M03-5114 | HOC Mech | 2019-07-16 | 036909C-JVD-TRN-02166 | 036909C-JVD-TRN-02166 | IFR | 2019-07-31 | 2019-08-12 | R1-No comments | TPSK-LSPA1-T-ME-02166 |  | 2019-07-16 | 2
036909C-1055-SP-0810-5552 | Mechanical Equipment Data Sheet for LPG Storage Drum | 0 | 2019-07-10 | IFP | OL1-2M03-5552 | ME | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-12 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1051-SP-0810-5112 | Mechanical Equipment Data Sheet for Suspect Condensate Flash Drum | 0 | 2019-07-12 | IFP | OL1-2M03-5112 | HOC Mech | 2019-07-16 | 036909C-JVD-TRN-02166 | 036909C-JVD-TRN-02166 | IFR | 2019-07-31 | 2019-08-12 | R1-No comments | TPSK-LSPA1-T-ME-02166 |  | 2019-07-16 | 2
036909C-1023-SP-0810-2331 | Mechanical Equipment Data Sheet for Spent Caustic Stripper OVHD Drum | 0 | 2019-07-05 | IFP | OL1-2M03-2331 | ME | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-12 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1023-SP-0810-2316 | Mechanical Equipment Data Sheet For Spent Caustic Degassing Drum | 0 | 2019-07-10 | IFP | OL1-2M03-2316 | ME | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-12 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1022-TDS-0610-2221 | Mechanical Equipment Data Sheet - 10-E-2220 - CG 2ND STAGE AFTERCOOLER | 0 | 2019-06-24 | IFP | OL1-2M03-2221 | ME | 2019-07-11 | 036909C-JVD-TRN-02139 | 036909C-JVD-TRN-02139 | IFR | 2019-07-26 | 2019-08-12 | R1-No comments | TPSK-LSPA1-T-ME-02139 |  | 2019-07-15 | 2
036909C-1022-TDS-0610-2211 | Mechanical Equipment Data Sheet - 10-E-2210A/B - CG 1st Stage Aftercoolers | 0 | 2019-06-24 | IFP | OL1-2M03-2211 | ME | 2019-07-11 | 036909C-JVD-TRN-02139 | 036909C-JVD-TRN-02139 | IFR | 2019-07-26 | 2019-08-12 | R1-No comments | TPSK-LSPA1-T-ME-02139 |  | 2019-07-15 | 2
036909C-1021-TDS-0610-2161 | Mechanical Equipment Data Sheet - 10-E-2160 - Dilution Steam Superheater | 0 | 2019-07-02 | IFP | OL1-2M03-2161 | ME | 2019-07-16 | 036909C-JVD-TRN-02163 | 036909C-JVD-TRN-02163 | IFR | 2019-07-31 | 2019-08-12 | R1-No comments | TPSK-LSPA1-T-ME-02163 |  | 2019-07-17 | 2
036909C-1000-NM-1551-0002 | Preliminary Alarm Summary and Setpoint List - Balance of Plant | A | 2019-07-10 | IBD | OL1-2I91-0002 | IE | 2019-07-11 | 036909C-JVD-TRN-02132 | 036909C-JVD-TRN-02132 | IFR | 2019-07-26 | 2019-08-12 | R2-Comments as noted | TPSK-LSPA1-T-IE-02132 |  | 2019-07-15 | 2
036909C-1000-MR-4065-0001 | Material Requisition For Bridge Crane | A | 2019-02-20 | IFQ | OL1-2C13-771000 | PL | 2019-02-22 | 036909C-JVD-TRN-00914 | 036909C-JVD-TRN-00914 | IFR | 2019-03-11 |  | Transmitted | TPSK-LSPA1-T-PC-00914 |  | 2019-02-25 | 2
036909C-102B-CN-1733-0030 | Calculation Note for Foundation of 10-E-2100 | A | 2019-08-06 | IFR | OL1-2K13-0191 | CV | 2019-08-08 | 036909C-JVD-TRN-02382 | 036909C-JVD-TRN-02382 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02382 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-017 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Steel Bracings Details | A | 2019-08-02 | IFR | OL1-2K31-1316 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-016 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Steel Bracings Details | A | 2019-08-02 | IFR | OL1-2K31-1315 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-011 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns | A | 2019-08-02 | IFR | OL1-2K31-1310 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-010 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns | A | 2019-08-02 | IFR | OL1-2K31-1309 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-009 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns | A | 2019-08-02 | IFR | OL1-2K31-1308 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-007 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns | A | 2019-08-02 | IFR | OL1-2K31-1306 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-004 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Elevations | A | 2019-08-02 | IFR | OL1-2K31-1303 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-001 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Isometric 3D View | A | 2019-08-02 | IFR | OL1-2K31-1300 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-006 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns | A | 2019-08-02 | IFR | OL1-2K31-1305 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-008 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns | A | 2019-08-02 | IFR | OL1-2K31-1307 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-DW-1741-0002-005 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Elevations | A | 2019-08-02 | IFR | OL1-2K31-1304 | CV | 2019-08-08 | 036909C-JVD-TRN-02383 | 036909C-JVD-TRN-02383 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02383 |  | 2019-08-09 | 1
036909C-102A-CN-1731-0001 | Calculation Notes for Foundations of Piperack 10-PRK-2A01 | A | 2019-08-02 | IFR | OL1-2K14-0013 | CV | 2019-08-08 | 036909C-JVD-TRN-02382 | 036909C-JVD-TRN-02382 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02382 |  | 2019-08-09 | 1
036909C-102A-CN-1731-0002 | Calculation Notes for Precast Concrete Piperack 10-PRK-2A01 | A | 2019-08-02 | IFR | OL1-2K14-0014 | CV | 2019-08-08 | 036909C-JVD-TRN-02382 | 036909C-JVD-TRN-02382 | IFA | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-CV-02382 |  | 2019-08-09 | 1
036909C-1000-MR-1545-0001 | Material Requisition for Safety Relief Valves & Rupture Disks | A | 2019-08-07 | IFQ | OL1-2C17-070201 | PL | 2019-08-08 | 036909C-JVD-TRN-02395 | 036909C-JVD-TRN-02395 | IFR | 2019-08-23 |  | Transmitted | TPSK-LSPA1-T-PL-02395 | Att. Attachment 4 in excel format | 2019-08-09 | 2
036909C-1000-MR-1329-0002 | Material Requisition For Underground Welded Carbon Steel Pipes | A | 2019-02-27 | IFQ | OL1-2C14-365001 | PL | 2019-03-04 | 036909C-JVD-TRN-00975 | 036909C-JVD-TRN-00975 | IFR | 2019-03-19 | 2019-06-06 | R2-Comments as noted | TPSK-LSPA1-T-PL-00975 |  | 2019-03-05 | 2
036909C-1000-JSS-1544-0001 | Job Supply Specification For Pneumatic Actuators For On Off Valves | A | 2019-07-17 | IFQ | OL1-2I92-0604 | IE | 2019-07-19 | 036909C-JVD-TRN-02199 | 036909C-JVD-TRN-02199 | IFA | 2019-08-05 | 2019-08-06 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-IE-02199 |  | 2019-07-22 | 1
036909C-102D-CN-1832-0001 | Calculation Note for Steel Structure 10-SHT-2D01 | A | 2019-05-29 | IFR | OL1-2K15-0024 | CV | 2019-06-06 | 036909C-JVD-TRN-01815 | 036909C-JVD-TRN-01815 | IFA | 2019-06-21 | 2019-08-06 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01815 |  | 2019-06-10 | 1
036909C-105W-DW-1743-0001-002 | Foundation For 10-TK-5640 | A | 2019-05-30 | IFR | OL1-2K31-0278 | CV | 2019-06-10 | 036909C-JVD-TRN-01837 | 036909C-JVD-TRN-01837 | IFR | 2019-06-24 | 2019-08-08 | R2-Comments as noted | TPSK-LSPA1-T-CV-01837 |  | 2019-06-10 | 2
036909C-105F-DW-1743-0011 | Foundation For 10-E-5552 | A | 2019-05-30 | IFR | OL1-2K31-0314 | CV | 2019-06-10 | 036909C-JVD-TRN-01837 | 036909C-JVD-TRN-01837 | IFR | 2019-06-24 | 2019-08-08 | R2-Comments as noted | TPSK-LSPA1-T-CV-01837 |  | 2019-06-10 | 2
036909C-105F-DW-1743-0010 | Foundation for 10-D-5565 | A | 2019-05-30 | IFR | OL1-2K31-0311 | CV | 2019-06-10 | 036909C-JVD-TRN-01837 | 036909C-JVD-TRN-01837 | IFR | 2019-06-24 | 2019-08-08 | R2-Comments as noted | TPSK-LSPA1-T-CV-01837 |  | 2019-06-10 | 2
036909C-105F-DW-1743-0009 | Foundation for 10-D-5552 | A | 2019-05-30 | IFR | OL1-2K31-0310 | CV | 2019-06-10 | 036909C-JVD-TRN-01837 | 036909C-JVD-TRN-01837 | IFR | 2019-06-24 | 2019-08-08 | R2-Comments as noted | TPSK-LSPA1-T-CV-01837 |  | 2019-06-10 | 2
036909C-1000-MR-1930-0002 | Material Requisition for Clean Agent Fire Extinguishing System | A | 2019-07-05 | IFQ | OL1-2C15-823001 | PL | 2019-07-05 | 036909C-JVD-TRN-02083 | 036909C-JVD-TRN-02083 | IFR | 2019-07-19 | 2019-08-08 | R1-No comments | TPSK-LSPA1-T-PL-02083 |  | 2019-07-08 | 2
036909C-1056-SP-0232-0002 | Mechanical Equipment Datasheet For Complex Waste Water Treatment Package | A | 2019-02-15 | IFQ | OL1-2M03-5644 | ME | 2019-02-15 | 036909C-JVD-TRN-00863 | 036909C-JVD-TRN-00863 |  |  | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-ME-00863 |  | 2019-02-15 | 2
036909C-1028-SP-1513-2802 | Instrument Interlock Descriptions Area 28 - Refrigeration System | A | 2019-05-24 | IFR | OL1-2G50-2802 | PE | 2019-05-28 | 036909C-JVD-TRN-01753 | 036909C-JVD-TRN-01753 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01753 |  | 2019-05-29 | 2
036909C-1000-JSD-2200-02 | Job Design Specification For Thermal Insulation - Cold Service | C | 2019-05-02 | IFR | OL1-2R04-0004 | MP | 2019-05-15 | 036909C-JVD-TRN-01665 | 036909C-JVD-TRN-01665 | IFR | 2019-05-30 | 2019-05-27 | R1-No comments | TPSK-LSPA1-T-MP-01665 |  | 2019-05-16 | 2
036909C-1000-MR-0630-0001 | Material Requisition For Hairpin Heat Exchangers Requisition For Inquiry | A | 2019-03-12 | IFQ | OL1-2C13-145000 | PL | 2019-03-13 | 036909C-JVD-TRN-01046 | 036909C-JVD-TRN-01046 | IFR | 2019-03-28 | 2019-06-06 | R1-No comments | TPSK-LSPA1-T-PL-01046 |  | 2019-03-14 | 2
036909C-1000-DW-0051-0001 | General Plot Plan | B | 2019-05-21 | IBD | OL1-2P06-0001 | MP | 2019-05-28 | 036909C-JVD-TRN-01752 | 036909C-JVD-TRN-01752 | IFR | 2019-06-12 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01752 |  | 2019-05-29 | 2
036909C-1025-SP-1545-2501 | Instrument Datasheets for Pressure Safety Valve - Area 25 | A | 2019-07-23 | IFQ | OL1-2I20-2516 | IE | 2019-07-30 | 036909C-JVD-TRN-02291 | 036909C-JVD-TRN-02291 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-02291 |  | 2019-07-31 | 3
036909C-1059-SP-1545-5901 | Instrument Datasheets for Pressure Safety Valve - Area 59 | A | 2019-07-23 | IFQ | OL1-2I20-5916 | IE | 2019-07-30 | 036909C-JVD-TRN-02291 | 036909C-JVD-TRN-02291 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-02291 |  | 2019-07-31 | 3
036909C-1024-SP-1545-2401 | Instrument Datasheets for Pressure Safety Valve - Area 24 | A | 2019-07-22 | IFI | OL1-2I20-2416 | IE | 2019-07-24 | 036909C-JVD-TRN-02258 | 036909C-JVD-TRN-02258 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-02258 |  | 2019-07-25 | 3
036909C-1051-SP-1545-5101 | Instrument Datasheets for Pressure Safety Valve - Area 51 | A | 2019-07-22 | IFI | OL1-2I20-5116 | IE | 2019-07-24 | 036909C-JVD-TRN-02258 | 036909C-JVD-TRN-02258, 036909C-JVD-TRN-02259 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-02258 |  | 2019-07-25 | 3
036909C-1029-SP-1545-2901 | Instrument Datasheets for Pressure Safety Valve - Area 29 | A | 2019-07-22 | IFI | OL1-2I20-2916 | IE | 2019-07-24 | 036909C-JVD-TRN-02258 | 036909C-JVD-TRN-02258 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-02258 |  | 2019-07-25 | 3
036909C-1031-PDS-4260-3101 | Process Equipment Datasheet - 10-A-3100 - Solvent Regen Agitator | B | 2019-06-06 | IFD | OL1-2G30-3101 | PE | 2019-06-06 | 036909C-JVD-TRN-01824 | 036909C-JVD-TRN-01824 | IFR | 2019-06-21 | 2019-07-08 | Response to Comments sent Aug-08-2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01824 |  | 2019-06-10 | 2
036909C-1030-PDS-0900-3067 | Process Equipment Data Sheet - 10-P-3062 A-B - C4 Acetylene Pump | B | 2019-06-18 | IFD | OL1-2G30-3067 | PE | 2019-06-20 | 036909C-JVD-TRN-01945 | 036909C-JVD-TRN-01945 | IFR | 2019-07-05 | 2019-07-11 | Response to comments sent Aug 8 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01945 |  | 2019-06-21 | 2
036909C-1012-PO-036909C004P9103906-06 | Vendors Acknowledgment of Purchase Order for Convection Boxes & Finning - Fabrication of Convection Modules | 0 | 2019-06-06 | IFI | OL1-2C51-0206 | PL | 2019-08-07 | 036909C-JVD-TRN-02380 | 036909C-JVD-TRN-02380 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02380 |  | 2019-08-08 | 3
036909C-1012-TBT-1552-2218 | Technical Bid Tabulation for Magnetostrictive Transmitter Magnetic Gauges | 0 | 2019-08-07 | IFI | OL1-2C27-2218 | PL | 2019-08-07 | 036909C-JVD-TRN-02376 | 036909C-JVD-TRN-02376 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02376 |  | 2019-08-08 | 3
036909C-1012-PO-036909C004P9103510-10 | Vendors Acknowledgment of Purchase Order for Radiant Coils | 0 | 2018-12-27 | IFI | OL1-2C51-0204 | PL | 2019-08-07 | 036909C-JVD-TRN-02380 | 036909C-JVD-TRN-02380 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02380 |  | 2019-08-08 | 3
036909C-1012-TBT-1552-2206 | Technical Bid Tabulation for Steam Drum Level Gauges | 0 | 2019-07-30 | IFI | OL1-2C27-2206 | PL | 2019-08-07 | 036909C-JVD-TRN-02373 | 036909C-JVD-TRN-02373 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02373 |  | 2019-08-08 | 3
036909C-1012-PO-036909C004P9103534-34 | Vendors Acknowledgment of Purchase Order for Convection Section Fitting - Fittings for Convection Modules | 0 | 2019-01-10 | IFI | OL1-2C51-0205 | PL | 2019-08-07 | 036909C-JVD-TRN-02380 | 036909C-JVD-TRN-02380 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02380 |  | 2019-08-08 | 3
036909C-1012-TBT-1540-2201 | Technical Bid Tabulation For Control Valves | 0 | 2019-07-03 | IFI | OL1-2C27-2201 | PL | 2019-07-08 | 036909C-JVD-TRN-02100 | 036909C-JVD-TRN-02100 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02100 | Resend on 09/08/2019 - LSP rejected because of wrong coding (C23 to C27) | 2019-07-11 | 3
036909C-1012-PO-036909C004P9103508-08 | Vendors Acknowledgment of Purchase Order for Cast Tube Supports - Support for Convection Modules | 0 | 2018-12-18 | IFI | OL1-2C51-0203 | PL | 2019-08-07 | 036909C-JVD-TRN-02380 | 036909C-JVD-TRN-02380 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02380 |  | 2019-08-08 | 3
036909C-1012-PO-036909C004P9103489-89 | Vendors Acknowledgment of Purchase Order for Quench System - Includes TLEs | 0 | 2018-12-26 | IFI | OL1-2C51-0201 | PL | 2019-08-07 | 036909C-JVD-TRN-02380 | 036909C-JVD-TRN-02380 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02380 |  | 2019-08-08 | 3
036909C-1012-PO-036909C004P9103499-99 | Vendors Acknowledgment of Purchase Order for Convection Section Tubes - Tubes for Convection Modules | 0 | 2018-12-19 | IFI | OL1-2C51-0202 | PL | 2019-08-07 | 036909C-JVD-TRN-02380 | 036909C-JVD-TRN-02380 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02380 |  | 2019-08-08 | 3
036909C-1029-PDS-2600-2920 | Process Equipment Datasheet - 10-PK-2920 - Polymerization Inhibitor Inj Pkg | E | 2019-07-08 | IFD | OL1-2G30-2920 | PE | 2019-07-08 | 036909C-JVD-TRN-02099 | 036909C-JVD-TRN-02099 | IFR | 2019-07-23 | 2019-08-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-02099 |  | 2019-07-09 | 2
036909C-1027-TDS-0630-2727 | Mechanical Equipment Data Sheet - 10-E-2726 - Pygas Fuel Oil Cooler | A | 2019-02-19 | IFQ | OL1-2M03-2727 | ME | 2019-02-20 | 036909C-JVD-TRN-00897 | 036909C-JVD-TRN-00897, ROC-TPSK-CECO-T-00018 | IFR | 2019-03-07 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00897 |  | 2019-02-20 | 2
036909C-1027-TDS-0630-2723 | Mechanical Equipment Data Sheet - 10-E-2724 - Wash Oil Condenser | A | 2019-02-21 | IFQ | OL1-2M03-2723 | ME | 2019-02-25 | 036909C-JVD-TRN-00929 | 036909C-JVD-TRN-00929, ROC-TPSK-CECO-T-00018 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00929 |  | 2019-02-26 | 2
036909C-1027-TDS-0630-2716 | Mechanical Equipment Data Sheet - 10-E-2714 - C5 Cut Cooler | A | 2019-02-12 | IFQ | OL1-2M03-2716 | ME | 2019-02-15 | 036909C-JVD-TRN-00872 | 036909C-JVD-TRN-00872, ROC-TPSK-CECO-T-00018 | IFR | 2019-03-04 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00872 |  | 2019-02-15 | 2
036909C-1024-TDS-0630-2432 | Mechanical Equipment Data Sheet - 10-E-2432 - Regen Gas SHP Heater | A | 2019-01-24 | IFQ | OL1-2M03-2432 | ME | 2019-01-29 | 036909C-JVD-TRN-00751 | 036909C-JVD-TRN-00751, ROC-TPSK-CECO-T-00017 | IFR | 2019-02-12 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00751 |  | 2019-01-29 | 2
036909C-1024-TDS-0630-2432 | Mechanical Equipment Data Sheet - 10-E-2432 - Regen Gas SHP Heater | B | 2019-05-23 | IFQ | OL1-2M03-2432 | ME | 2019-05-24 | 036909C-JVD-TRN-01743 | 036909C-JVD-TRN-01743 | IFR | 2019-06-10 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01743 |  | 2019-05-27 | 2
036909C-1023-TDS-0630-2326 | Mechanical Equipment Data Sheet - 10-E-2326 - Spent Caustic Stripper Feed Heater | B | 2019-05-06 | IFQ | OL1-2M03-2326 | ME | 2019-05-24 | 036909C-JVD-TRN-01743 | 036909C-JVD-TRN-01743 | IFR | 2019-06-10 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01743 |  | 2019-05-27 | 2
036909C-1056-PDS-2500-5640 | Process Equipment Datasheet - 10-TK-5640 - Oily Wastewater Tank | C | 2019-06-18 | IFD | OL1-2G30-5640 | PE | 2019-06-18 | 036909C-JVD-TRN-01920 | 036909C-JVD-TRN-01920 | IFR | 2019-07-03 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-01920 |  | 2019-06-19 | 2
036909C-1056-PDS-2500-5676 | Process Equipment Datasheet - 10-TK-5676 - Oily Sludge Tank | C | 2019-06-18 | IFD | OL1-2G30-5676 | PE | 2019-06-18 | 036909C-JVD-TRN-01920 | 036909C-JVD-TRN-01920 | IFR | 2019-07-03 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-01920 |  | 2019-06-19 | 2
036909C-1056-PDS-2500-5676 | Process Equipment Datasheet - 10-TK-5676 - Oily Sludge Tank | B | 2019-03-26 | IFD | OL1-2G30-5676 | PE | 2019-03-27 | 036909C-JVD-TRN-01176 | 036909C-JVD-TRN-01176, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01176 |  | 2019-03-28 | 2
036909C-1056-PDS-2500-5675 | Process Equipment Datasheet - 10-TK-5675 A-B - Slop Oil Tanks | B | 2019-03-26 | IFD | OL1-2G30-5675 | PE | 2019-03-27 | 036909C-JVD-TRN-01176 | 036909C-JVD-TRN-01176, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-11 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01176 |  | 2019-03-28 | 2
036909C-1056-PDS-2500-5675 | Process Equipment Datasheet - 10-TK-5675 A-B - Slop Oil Tanks | C | 2019-06-18 | IFD | OL1-2G30-5675 | PE | 2019-06-18 | 036909C-JVD-TRN-01920 | 036909C-JVD-TRN-01920 | IFR | 2019-07-03 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-01920 |  | 2019-06-19 | 2
036909C-1056-PDS-0900-5652 | Process Equipment Datasheet - 10-P-5653 - Bio Equalization Pit Sludge Pump | B | 2019-06-21 | IFD | OL1-2G30-5652 | PE | 2019-06-24 | 036909C-JVD-TRN-01981 | 036909C-JVD-TRN-01981 | IFR | 2019-07-08 | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01981 |  | 2019-06-25 | 2
036909C-1056-PDS-0900-5643 | Process Equipment Datasheet - 10-P-5642 A-B - Cooling Water BD Basin Pumps | B | 2019-05-01 | IFD | OL1-2G30-5643 | PE | 2019-05-01 | 036909C-JVD-TRN-01543 | 036909C-JVD-TRN-01543 | IFR | 2019-05-16 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01543 |  | 2019-05-02 | 2
036909C-1056-PDS-0900-5643 | Process Equipment Datasheet - 10-P-5642 A-B - Cooling Water BD Basin Pumps | C | 2019-06-21 | IFD | OL1-2G30-5643 | PE | 2019-06-24 | 036909C-JVD-TRN-01981 | 036909C-JVD-TRN-01981 | IFR | 2019-07-08 | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01981 |  | 2019-06-25 | 2
036909C-1028-DW-1514-2801 | Cause and Effect Diagram Area 28 - Refrigeration System | A | 2019-04-30 | IFR | OL1-2G50-2801 | PE | 2019-05-01 | 036909C-JVD-TRN-01540 | 036909C-JVD-TRN-01540, ROC-TPSK-CECO-T-00056 | IFR | 2019-05-16 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01540 |  | 2019-05-02 | 2
036909C-105T-NM-1350-0030 | Loads on Rack 10-PRK-5T01 | A | 2019-08-05 | IBD | OL1-2P05-0211 | MP | 2019-08-06 | 036909C-JVD-TRN-02357 | 036909C-JVD-TRN-02357 | IFR | 2019-08-20 |  | Transmitted | TPSK-LSPA1-T-MP-02357 |  | 2019-08-07 | 2
036909C-1051-PDS-1390-5148 | Piping Specialty Item - Datasheet - Multistage Restriction Orifice - SHP BFW Pump Warmup - ORI-51003 | A | 2019-07-29 | IFR | OL1-2P03-5148 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 |  | Transmitted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-1051-PDS-1390-5143 | Piping Specialty Item - Datasheet – Double-Keyed Interlocked Locking Device - PSV-5140 A-B - ILK-51005 | A | 2019-07-22 | IFR | OL1-2P03-5143 | MP | 2019-08-02 | 036909C-JVD-TRN-02335 | 036909C-JVD-TRN-02335 | IFR | 2019-08-17 |  | Transmitted | TPSK-LSPA1-T-MP-02335 |  | 2019-08-05 | 2
036909C-103A-DW-1743-0018 | FOUNDATION FOR 10-D-3906 | A | 2019-07-31 | IFR | OL1-2K31-0225 | CV | 2019-08-05 | 036909C-JVD-TRN-02340 | 036909C-JVD-TRN-02340 | IFR | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-CV-02340 |  | 2019-08-06 | 2
036909C-103A-DW-1743-0017 | FOUNDATION FOR 10-D-3904 | A | 2019-07-31 | IFR | OL1-2K31-0224 | CV | 2019-08-05 | 036909C-JVD-TRN-02340 | 036909C-JVD-TRN-02340 | IFR | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-CV-02340 |  | 2019-08-06 | 2
036909C-103A-DW-1743-0016 | FOUNDATION FOR 10-D-3902 | A | 2019-07-31 | IFR | OL1-2K31-0223 | CV | 2019-08-05 | 036909C-JVD-TRN-02340 | 036909C-JVD-TRN-02340 | IFR | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-CV-02340 |  | 2019-08-06 | 2
036909C-103A-CN-1733-0019 | Calculation Note For Foundation Of 10-D-3906 | A | 2019-08-05 | IFR | OL1-2K13-0218 | CV | 2019-08-06 | 036909C-JVD-TRN-02358 | 036909C-JVD-TRN-02358 | IFR | 2019-08-20 |  | Transmitted | TPSK-LSPA1-T-CV-02358 |  | 2019-08-07 | 1
036909C-103A-CN-1733-0017 | Calculation Note For Foundation Of 10-D-3902 | A | 2019-08-05 | IFR | OL1-2K13-0216 | CV | 2019-08-06 | 036909C-JVD-TRN-02358 | 036909C-JVD-TRN-02358 | IFR | 2019-08-20 |  | Transmitted | TPSK-LSPA1-T-CV-02358 |  | 2019-08-07 | 1
036909C-103A-DW-1743-0015 | FOUNDATION FOR 10-D-3908 | A | 2019-07-31 | IFR | OL1-2K31-0222 | CV | 2019-08-05 | 036909C-JVD-TRN-02340 | 036909C-JVD-TRN-02340 | IFR | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-CV-02340 |  | 2019-08-06 | 2
036909C-103A-CN-1733-0016 | Calculation Note For Foundation Of 10-D-3908 | A | 2019-08-05 | IFR | OL1-2K13-0215 | CV | 2019-08-06 | 036909C-JVD-TRN-02358 | 036909C-JVD-TRN-02358 | IFR | 2019-08-20 |  | Transmitted | TPSK-LSPA1-T-CV-02358 |  | 2019-08-07 | 1
036909C-103A-CN-1733-0018 | Calculation Note For Foundation Of 10-D-3904 | A | 2019-08-05 | IFR | OL1-2K13-0217 | CV | 2019-08-06 | 036909C-JVD-TRN-02358 | 036909C-JVD-TRN-02358 | IFR | 2019-08-20 |  | Transmitted | TPSK-LSPA1-T-CV-02358 |  | 2019-08-07 | 1
036909C-102C-DW-1741-0003-002 | Foundations Pipe Rack 10-PRK-2C02 - (Formworks And Reinforcements) | A | 2019-07-29 | IFR | OL1-2K31-1421 | CV | 2019-08-02 | 036909C-JVD-TRN-02330 | 036909C-JVD-TRN-02330 | IFA | 2019-08-19 |  | Transmitted | TPSK-LSPA1-T-CV-02330 |  | 2019-08-05 | 1
036909C-102C-CN-1731-0003 | Calculation Notes For Foundation & Elevation Of Pipe Rack 10-PRK-2C02 | A | 2019-08-01 | IFR | OL1-2K14-0169 | CV | 2019-08-02 | 036909C-JVD-TRN-02331 | 036909C-JVD-TRN-02331 | IFA | 2019-08-19 |  | Transmitted | TPSK-LSPA1-T-CV-02331 |  | 2019-08-05 | 1
036909C-102C-DW-1741-0003-001 | Foundations Pipe Rack 10-PRK-2C02 - (Formworks And Reinforcements) | A | 2019-07-29 | IFR | OL1-2K31-1420 | CV | 2019-08-02 | 036909C-JVD-TRN-02330 | 036909C-JVD-TRN-02330 | IFA | 2019-08-19 |  | Transmitted | TPSK-LSPA1-T-CV-02330 |  | 2019-08-05 | 1
036909C-100M-DW-1622-0101 | Electrical Main Cable Routing Layout - Zone 0M Metering Zone | A | 2019-08-02 | IFR | OL1-2E31-0007 | EE | 2019-08-06 | 036909C-JVD-TRN-02359 | 036909C-JVD-TRN-02359 | IFR | 2019-08-20 |  | Transmitted | TPSK-LSPA1-T-EE-02359 |  | 2019-08-07 | 1
036909C-1012-DW-1514-1202 | Cause and Effect Diagrams Liquid Cracking Furnaces - 132U - Ex Doc Client Ref OL1-2G50-1002 | B | 2019-07-08 | IBD | OL1-2G50-1202 | PE | 2019-07-09 | 036909C-JVD-TRN-02111 | 036909C-JVD-TRN-02111 | IFR | 2019-07-24 | 2019-08-07 | R2-Comments as noted | TPSK-LSPA1-T-PE-02111 | Ex Doc Client Ref OL1-2G50-1002 | 2019-07-10 | 2
036909C-1011-DW-1514-1102 | Cause and Effect Diagrams Cracking Furnace - 36M - Ex Doc Client Ref OL1-2G50-1001 | D | 2019-07-08 | IBD | OL1-2G50-1102 | PE | 2019-07-09 | 036909C-JVD-TRN-02111 | 036909C-JVD-TRN-02111 | IFR | 2019-07-24 | 2019-08-07 | R2-Comments as noted | TPSK-LSPA1-T-PE-02111 | Ex Doc Client Ref OL1-2G50-1001 | 2019-07-10 | 2
036909C-1011-JSD-1513-1101 | Shutdown Interlock Narrative - 36M - Area 11 Recycle Gas Cracking Furnace | B | 2019-07-08 | IFD | OL1-2G50-1101 | PE | 2019-07-09 | 036909C-JVD-TRN-02112 | 036909C-JVD-TRN-02112 | IFR | 2019-07-24 | 2019-08-07 | R2-Comments as noted | TPSK-LSPA1-T-PE-02112 |  | 2019-07-10 | 2
036909C-1022-TDS-0610-2231 | Mechanical Equipment Data Sheet - 10-E-2231 - CG 3RD STAGE AFTERCOOLER | 0 | 2019-06-24 | IFP | OL1-2M03-2231 | ME | 2019-07-11 | 036909C-JVD-TRN-02141 | 036909C-JVD-TRN-02141 | IFR | 2019-07-26 | 2019-08-07 | R1-No comments | TPSK-LSPA1-T-ME-02141 |  | 2019-07-15 | 2
036909C-1023-PDS-0800-2331 | Process Equipment Datasheet - 10-D-2330 - Spent Caustic Stripper Ovhd Drum | F | 2019-07-10 | IFD | OL1-2G30-2331 | PE | 2019-07-10 | 036909C-JVD-TRN-02125 | 036909C-JVD-TRN-02125 | IFR | 2019-07-25 | 2019-08-07 | R1-No comments | TPSK-LSPA1-T-PE-02125 |  | 2019-07-11 | 2
036909C-1030-SP-1541-3001 | Instrument Datasheets for Control Valve - Globe Type - Area 30 | A | 2019-07-10 | IFQ | OL1-2I20-3001 | IE | 2019-07-11 | 036909C-JVD-TRN-02133 | 036909C-JVD-TRN-02133 | IFI |  | 2019-08-07 | R2-Comments as noted | TPSK-LSPA1-T-IE-02133 |  | 2019-07-15 | 3
036909C-1012-DL-4061-2009 | Deviation List For Furnace Elevator | C | 2019-07-15 | IFR | OL1-2C40-709000 | PL | 2019-07-18 | 036909C-JVD-TRN-02191 | 036909C-JVD-TRN-02191 | IFR | 2019-08-02 | 2019-08-07 | R1-No comments | TPSK-LSPA1-T-PL-02191 |  | 2019-07-19 | 3
036909C-1029-DW-1514-2901 | Cause and Effect Diagram - Area 29 - Ethylene Auxiliaries | A | 2019-04-30 | IFR | OL1-2G50-2901 | PE | 2019-05-01 | 036909C-JVD-TRN-01539 | 036909C-JVD-TRN-01539, ROC-TPSK-CECO-T-00056 | IFR | 2019-05-16 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01539 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5708 | P&ID - TYPICAL INSTALLATION OF FIRE PROTECTION EQUIPMENT | B | 2019-05-08 | IFR | OL1-2L40-5708 | SE | 2019-05-09 | 036909C-JVD-TRN-01622 | 036909C-JVD-TRN-01622 | IFR | 2019-05-23 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-SE-01622 |  | 2019-05-09 | 2
036909C-1059-PDS-2600-5914 | Datasheet For Chemical Dosing Systems - 10-PK-5914 - Phosphate Injection Pkg | E | 2019-07-12 | IFD | OL1-2G30-5914 | PE | 2019-07-19 | 036909C-JVD-TRN-02198 | 036909C-JVD-TRN-02198 | IFR | 2019-08-05 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-PE-02198 |  | 2019-07-22 | 2
036909C-1059-PDS-2600-5912 | Datasheet For Chemical Dosing Systems - 10-PK-5912 - Neutralization Amine Inhibitor Inj Pkg | E | 2019-07-12 | IFD | OL1-2G30-5912 | PE | 2019-07-19 | 036909C-JVD-TRN-02198 | 036909C-JVD-TRN-02198 | IFR | 2019-08-05 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-PE-02198 |  | 2019-07-22 | 2
036909C-1059-PDS-2600-5910 | Datasheet For Chemical Dosing Systems - 10-PK-5910 - Oxygen Scavenger Inj Pkg | E | 2019-07-12 | IFD | OL1-2G30-5910 | PE | 2019-07-19 | 036909C-JVD-TRN-02198 | 036909C-JVD-TRN-02198 | IFR | 2019-08-05 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-PE-02198 |  | 2019-07-22 | 2
036909C-1053-PDS-2600-5394 | Datasheet For Chemical Dosing Systems - 10-PK-5394 - Dispersant Inj Pkg | D | 2019-07-12 | IFD | OL1-2G30-5394 | PE | 2019-07-19 | 036909C-JVD-TRN-02198 | 036909C-JVD-TRN-02198 | IFR | 2019-08-05 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-PE-02198 |  | 2019-07-22 | 2
036909C-1053-PDS-2600-5392 | Datasheet For Chemical Dosing Systems - 10-PK-5392 - Mild Steel Corr Inhibitor Inj Pkg | D | 2019-07-12 | IFD | OL1-2G30-5392 | PE | 2019-07-19 | 036909C-JVD-TRN-02198 | 036909C-JVD-TRN-02198 | IFR | 2019-08-05 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-PE-02198 |  | 2019-07-22 | 2
036909C-1000-SP-1930-0003 | Datasheet for Sprinkler System | B | 2019-07-05 | IFQ | OL1-2L03-2001 | SE | 2019-07-08 | 036909C-JVD-TRN-02090 | 036909C-JVD-TRN-02090 | IFR | 2019-07-22 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-SE-02090 |  | 2019-07-08 | 2
036909C-1000-SP-1930-0001 | Datasheet for Deluge System | B | 2019-07-05 | IFQ | OL1-2L03-1001 | SE | 2019-07-08 | 036909C-JVD-TRN-02090 | 036909C-JVD-TRN-02090 | IFR | 2019-07-22 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-SE-02090 |  | 2019-07-08 | 2
036909C-1053-PDS-2600-5390 | Datasheet For Chemical Dosing Systems - 10-PK-5390 - Copper Corrosion Inhibitor Inj Pkg | D | 2019-07-12 | IFD | OL1-2G30-5390 | PE | 2019-07-19 | 036909C-JVD-TRN-02198 | 036909C-JVD-TRN-02198 | IFR | 2019-08-05 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-PE-02198 |  | 2019-07-22 | 2
036909C-1000-SP-1920-0001 | Datasheet for Firefighting Equipment | B | 2019-07-05 | IFQ | OL1-2L03-0001 | SE | 2019-07-08 | 036909C-JVD-TRN-02090 | 036909C-JVD-TRN-02090 | IFR | 2019-07-22 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-SE-02090 |  | 2019-07-08 | 2
036909C-1000-MS-6740-52 | Job Specification for Material Preservation During Construction Precommissioning Commissioning and Start Up | 0 | 2019-06-19 | IMP | OL1-2O71-0023 | PE | 2019-07-03 | 036909C-JVD-TRN-02067 | 036909C-JVD-TRN-02067 | IFR | 2019-07-18 | 2019-08-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-02067 |  | 2019-07-04 | 2
036909C-1052-SP-1513-5202 | Instrument Interlock Descriptions - Area 52 - Fuel System | A | 2019-05-03 | IFR | OL1-2G50-5202 | PE | 2019-05-06 | 036909C-JVD-TRN-01573 | 036909C-JVD-TRN-01573 | IFR | 2019-05-21 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01573 |  | 2019-05-07 | 2
036909C-1051-SP-1513-5102 | Instrument Interlock Descriptions - Area 51 - BFW-Steam - Steam Condensate System | A | 2019-05-02 | IFR | OL1-2G50-5102 | PE | 2019-05-06 | 036909C-JVD-TRN-01573 | 036909C-JVD-TRN-01573 | IFR | 2019-05-21 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01573 |  | 2019-05-07 | 2
036909C-1052-SP-1513-5201 | Complex Loop Narratives Area 52 - Fuel System | A | 2019-05-08 | IFR | OL1-2I71-5201 | IE | 2019-05-09 | 036909C-JVD-TRN-01632 | 036909C-JVD-TRN-01632 | IFR | 2019-05-24 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-IE-01632 |  | 2019-05-10 | 2
036909C-1051-SP-1513-5101 | Complex Loop Narratives - Area 51 - BFW-Steam -Steam Condensate System | A | 2019-05-07 | IFR | OL1-2I71-5101 | IE | 2019-05-08 | 036909C-JVD-TRN-01614 | 036909C-JVD-TRN-01614 | IFR | 2019-05-23 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-IE-01614 |  | 2019-05-09 | 2
036909C-1029-SP-1513-2901 | Complex Loop Narratives Area 29 - Ethylene Auxiliaries | A | 2019-05-31 | IFR | OL1-2I71-2901 | IE | 2019-06-03 | 036909C-JVD-TRN-01791 | 036909C-JVD-TRN-01791 | IFR | 2019-06-18 | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01791 |  | 2019-06-10 | 2
036909C-1027-SP-1513-2701 | Complex Loop Narratives - Area 27 - GHU & C4-C5 Hydrog | A | 2019-05-13 | IFR | OL1-2I71-2701 | IE | 2019-05-14 | 036909C-JVD-TRN-01662 | 036909C-JVD-TRN-01662 | IFR | 2019-05-29 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-IE-01662 |  | 2019-05-15 | 2
036909C-1029-SP-1513-2902 | Instrument Interlock Descriptions Area 29 - Ethylene Auxliaries | A | 2019-05-24 | IFR | OL1-2G50-2902 | PE | 2019-05-28 | 036909C-JVD-TRN-01753 | 036909C-JVD-TRN-01753 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01753 |  | 2019-05-29 | 2
036909C-1028-SP-4065-6005 | Mechanical Equipment Datasheet For Ethylene And Propylene Compressor Bridge Crane (10-EL-2800) | A | 2019-02-20 | IFQ | OL1-2M03-6005 | ME | 2019-02-22 | 036909C-JVD-TRN-00913 | 036909C-JVD-TRN-00913 | IFR | 2019-02-22 | 2019-04-05 | R1-No comments | TPSK-LSPA1-T-ME-00913 |  | 2019-02-25 | 2
036909C-1023-SP-4065-6004 | Mechanical Equipment Datasheet For Cracked Gas Compressor Bridge Crane (10-EL-2300) | A | 2019-02-20 | IFQ | OL1-2M03-6004 | ME | 2019-02-22 | 036909C-JVD-TRN-00913 | 036909C-JVD-TRN-00913 | IFR | 2019-02-22 | 2019-04-05 | R1-No comments | TPSK-LSPA1-T-ME-00913 |  | 2019-02-25 | 2
036909C-1054-SP-0810-5400 | Mechanical Equipment Data Sheet for Instrument Air Receiver | 0 | 2019-07-03 | IFP | OL1-2M03-5400 | ME | 2019-07-11 | 036909C-JVD-TRN-02134 | 036909C-JVD-TRN-02134 | IFR | 2019-07-26 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02134 |  | 2019-07-15 | 2
036909C-1028-SP-0810-2880 | Mechanical Equipment Data Sheet for C2R 3RD Stage Suction Drum | 0 | 2019-07-03 | IFP | OL1-2M03-2880 | ME | 2019-07-08 | 036909C-JVD-TRN-02102 | 036909C-JVD-TRN-02102 | IFR | 2019-07-23 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02102 |  | 2019-07-08 | 2
036909C-1028-SP-0810-2810 | Mechanical Equipment Data Sheet C3R 1st Stage Suction Drum | 0 | 2019-07-03 | IFP | OL1-2M03-2810 | ME | 2019-07-08 | 036909C-JVD-TRN-02102 | 036909C-JVD-TRN-02102 | IFR | 2019-07-23 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02102 |  | 2019-07-09 | 2
036909C-1055-SP-0810-5550 | Mechanical Equipment Data Sheet For HP Flare Knock-Out Drum | 0 | 2019-07-11 | IFP | OL1-2M03-5550 | ME | 2019-07-11 | 036909C-JVD-TRN-02138 | 036909C-JVD-TRN-02138 | IFR | 2019-07-26 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02138 |  | 2019-07-15 | 2
036909C-1055-TDS-0610-5513 | Mechanical Equipment Data Sheet - 10-E-5513 - Methanol Vaporizer | 0 | 2019-06-24 | IFP | OL1-2M03-5513 | ME | 2019-07-11 | 036909C-JVD-TRN-02140 | 036909C-JVD-TRN-02140 | IFR | 2019-07-26 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02140 |  | 2019-07-15 | 2
036909C-1055-TDS-0610-5511 | Mechanical Equipment Data Sheet - 10-E-5510 - Cold Flare Blowdown Vaporizer | 0 | 2019-07-02 | IFP | OL1-2M03-5511 | ME | 2019-07-16 | 036909C-JVD-TRN-02164 | 036909C-JVD-TRN-02164 | IFR | 2019-07-31 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02164 |  | 2019-07-17 | 2
036909C-1027-TDS-0610-2765 | Mechanical Equipment Data Sheet - 10-E-2765 - C4 - C5 Hydrog Recycle Cooler | 0 | 2019-06-24 | IFP | OL1-2M03-2765 | ME | 2019-07-11 | 036909C-JVD-TRN-02140 | 036909C-JVD-TRN-02140 | IFR | 2019-07-26 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02140 |  | 2019-07-15 | 2
036909C-1027-TDS-0610-2703 | Mechanical Equipment Data Sheet - 10-E-2705 - GHU-1 Recycle Cooler | 0 | 2019-06-26 | IFP | OL1-2M03-2703 | ME | 2019-07-11 | 036909C-JVD-TRN-02140 | 036909C-JVD-TRN-02140 | IFR | 2019-07-26 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02140 |  | 2019-07-15 | 2
036909C-1027-TDS-0610-2701 | Mechanical Equipment Data Sheet - 10-E-2701 - GHU-1 FEED EFFLUENT EXCHANGER | 0 | 2019-06-25 | IFP | OL1-2M03-2701 | ME | 2019-07-11 | 036909C-JVD-TRN-02140 | 036909C-JVD-TRN-02140 | IFR | 2019-07-26 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02140 |  | 2019-07-15 | 2
036909C-1024-TDS-0610-2472 | Mechanical Equipment Data Sheet - 10-E-2472 - C2 Hydrog 2nd Stage Intercooler | 0 | 2019-06-24 | IFP | OL1-2M03-2472 | ME | 2019-07-11 | 036909C-JVD-TRN-02140 | 036909C-JVD-TRN-02140 | IFR | 2019-07-26 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02140 |  | 2019-07-15 | 2
036909C-1024-TDS-0610-2471 | Mechanical Equipment Data Sheet - 10-E-2470 - C2 Hydrog 1st Stage Intercooler | 0 | 2019-06-24 | IFP | OL1-2M03-2471 | ME | 2019-07-11 | 036909C-JVD-TRN-02140 | 036909C-JVD-TRN-02140 | IFR | 2019-07-26 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02140 |  | 2019-07-15 | 2
036909C-1024-TDS-0610-2461 | Mechanical Equipment Data Sheet - 10-E-2460 - C2 Hydrog Feed Cooler | 0 | 2019-06-24 | IFP | OL1-2M03-2461 | ME | 2019-07-11 | 036909C-JVD-TRN-02140 | 036909C-JVD-TRN-02140 | IFR | 2019-07-26 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02140 |  | 2019-07-15 | 2
036909C-1027-SP-0810-2790 | Mechanical Equipment Data Sheet For Light Oil Drain Drum | 0 | 2019-07-12 | IFP | OL1-2M03-2790 | HOC Mech | 2019-07-16 | 036909C-JVD-TRN-02166 | 036909C-JVD-TRN-02166 | IFR | 2019-07-31 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02166 |  | 2019-07-16 | 2
036909C-1026-SP-0810-2644 | Mechanical Equipment Data Sheet for C3 Tower Reboilder Cond Pot | 0 | 2019-07-05 | IFP | OL1-2M03-2644 | ME | 2019-07-17 | 036909C-JVD-TRN-02176 | 036909C-JVD-TRN-02176 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02176 |  | 2019-07-17 | 2
036909C-1026-TDS-0610-2635 | Mechanical Equipment Data Sheet - 10-E-2635 - Secondary Deeth Reboiler | 0 | 2019-06-25 | IFP | OL1-2M03-2635 | ME | 2019-07-18 | 036909C-JVD-TRN-02189 | 036909C-JVD-TRN-02189 | IFR | 2019-08-02 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02189 |  | 2019-07-19 | 2
036909C-1022-SP-0810-2210 | Mechanical Equipment Data Sheet for CG 1st Stage Suction Drum | 0 | 2019-07-03 | IFP | OL1-2M03-2210 | ME | 2019-07-08 | 036909C-JVD-TRN-02102 | 036909C-JVD-TRN-02102 | IFR | 2019-07-23 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02102 |  | 2019-07-09 | 2
036909C-1026-TDS-0610-2621 | Mechanical Equipment Data Sheet - 10-E-2620 - C3 Hydrog Aftercooler | 0 | 2019-06-24 | IFP | OL1-2M03-2621 | ME | 2019-07-11 | 036909C-JVD-TRN-02141 | 036909C-JVD-TRN-02141 | IFR | 2019-07-26 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02141 |  | 2019-07-15 | 2
036909C-1024-TDS-0610-2474 | Mechanical Equipment Data Sheet - 10-E-2474 - C2 Hydrog Aftercooler | 0 | 2019-06-24 | IFP | OL1-2M03-2474 | ME | 2019-07-11 | 036909C-JVD-TRN-02139 | 036909C-JVD-TRN-02139 | IFR | 2019-07-26 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02139 |  | 2019-07-15 | 2
036909C-1024-TDS-0610-2430 | Mechanical Equipment Data Sheet - 10-E-2430 - Regen Gas Feed Heater | 0 | 2019-07-02 | Issue for Purchase | OL1-2M03-2430 | ME | 2019-07-18 | 036909C-JVD-TRN-02189 | 036909C-JVD-TRN-02189 | IFR | 2019-08-02 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02189 |  | 2019-07-19 | 2
036909C-1021-SP-0810-2160 | Mechanical Equipment Data Sheet Dilution Steam Generator | 0 | 2019-07-03 | IFP | OL1-2M03-2160 | ME | 2019-07-08 | 036909C-JVD-TRN-02102 | 036909C-JVD-TRN-02102 | IFR | 2019-07-23 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02102 |  | 2019-07-09 | 2
036909C-1010-TDS-0610-1002 | Mechanical Equipment Data Sheet - 10-E-1000 - LPG Vaporizer | 0 | 2019-06-26 | IFP | OL1-2M03-1002 | ME | 2019-07-11 | 036909C-JVD-TRN-02140 | 036909C-JVD-TRN-02140 | IFR | 2019-07-26 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-ME-02140 |  | 2019-07-15 | 2
036909C-1031-SP-1542-3103 | Instrument Datasheets for Self Actuated Pressure Control Valve.Area 31 | A | 2019-07-05 | IFQ | OL1-2I20-3106 | IE | 2019-07-09 | 036909C-JVD-TRN-02110 | 036909C-JVD-TRN-02110 | IFI |  | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-IE-02110 |  | 2019-07-10 | 3
036909C-1030-SP-1547-3005 | Instrument Datasheets for Flow Transmitter Electromagnetic Area 30 | A | 2019-07-05 | IFQ | OL1-2I20-3029 | IE | 2019-07-09 | 036909C-JVD-TRN-02110 | 036909C-JVD-TRN-02110 | IFI |  | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-IE-02110 |  | 2019-07-10 | 3
036909C-1030-SP-1546-3005 | Instrument Datasheets for Flow Element Venturi Area 30 | A | 2019-07-04 | IFQ | OL1-2I20-3023 | IE | 2019-07-09 | 036909C-JVD-TRN-02110 | 036909C-JVD-TRN-02110 | IFI |  | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-IE-02110 |  | 2019-07-10 | 3
036909C-1030-SP-1543-3004 | Instrument Datasheets for ON-OFF Valve Butterfly Type Area 30 | A | 2019-07-03 | IFQ | OL1-2I20-3012 | IE | 2019-07-09 | 036909C-JVD-TRN-02110 | 036909C-JVD-TRN-02110 | IFI |  | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-IE-02110 |  | 2019-07-10 | 3
036909C-1030-SP-1543-3001 | Instrument Datasheets for ON-OFF Valve Ball Type Area 30 | A | 2019-07-03 | IFQ | OL1-2I20-3011 | IE | 2019-07-09 | 036909C-JVD-TRN-02110 | 036909C-JVD-TRN-02110 | IFI |  | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-IE-02110 |  | 2019-07-10 | 3
036909C-1030-SP-1541-3003 | Instrument Datasheets for Control Valve - Butterfly Type - Area 30 | A | 2019-07-10 | IFQ | OL1-2I20-3002 | IE | 2019-07-11 | 036909C-JVD-TRN-02133 | 036909C-JVD-TRN-02133 | IFI |  | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-IE-02133 |  | 2019-07-15 | 3
036909C-1028-TDS-0610-2858 | Mechanical Equipment Data Sheet - 10-E-2858 - HP Ethylene Product Superheater | 0 | 2019-07-09 | IFP | OL1-2M03-2858 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-18 | 2
036909C-1028-TDS-0610-2859 | Mechanical Equipment Data Sheet - 10-E-2856 - Ethylene Product Subcooler | 0 | 2019-07-02 | IFP | OL1-2M03-2859 | ME | 2019-07-16 | 036909C-JVD-TRN-02163 | 036909C-JVD-TRN-02163 | IFR | 2019-07-31 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02163 |  | 2019-07-17 | 2
036909C-1028-TDS-0610-2809 | Mechanical Equipment Data Sheet - 10-E-2809 - C3 Chiller No 2 | 0 | 2019-07-03 | IFP | OL1-2M03-2809 | ME | 2019-07-16 | 036909C-JVD-TRN-02163 | 036909C-JVD-TRN-02163 | IFR | 2019-07-31 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02163 |  | 2019-07-17 | 2
036909C-1027-TDS-0610-2711 | Mechanical Equipment Data Sheet - 10-E-2710 - Depentanizer Condenser | 0 | 2019-07-03 | IFP | OL1-2M03-2711 | ME | 2019-07-16 | 036909C-JVD-TRN-02163 | 036909C-JVD-TRN-02163 | IFR | 2019-07-31 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02163 |  | 2019-07-17 | 2
036909C-1027-TDS-0610-2702 | Mechanical Equipment Data Sheet - 10-E-2702 - GHU-1 Start-Up Heater | 0 | 2019-06-25 | IFP | OL1-2M03-2702 | ME | 2019-07-15 | 036909C-JVD-TRN-02153 | 036909C-JVD-TRN-02153 | IFR | 2019-07-30 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02153 |  | 2019-07-16 | 2
036909C-1026-TDS-0610-2665 | Mechanical Equipment Data Sheet - 10-E-2665 AB - Debutanizer Reboilers | 0 | 2019-06-25 | IFP | OL1-2M03-2665 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-17 | 2
036909C-1025-TDS-0610-2582 | Mechanical Equipment Data Sheet - 10-E-2582 - C2 Tower Reflux Cooler | 0 | 2019-07-03 | IFP | OL1-2M03-2582 | ME | 2019-07-16 | 036909C-JVD-TRN-02163 | 036909C-JVD-TRN-02163 | IFR | 2019-07-31 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02163 |  | 2019-07-17 | 2
036909C-1025-TDS-0610-2546 | Mechanical Equipment Data Sheet - 10-E-2546 - Demethanizer Bottoms Cooler | 0 | 2019-06-25 | IFP | OL1-2M03-2546 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-17 | 2
036909C-1024-TDS-0610-2465 | Mechanical Equipment Data Sheet - 10-E-2465 - C2 Hydrog Feed Heater | 0 | 2019-07-09 | IFP | OL1-2M03-2465 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-18 | 2
036909C-1000-STC-1391-0000 | Standard Auxiliary Piping Support Collection | 0 | 2019-06-28 | IMP | OL1-2P25-0085 | MP | 2019-07-03 | 036909C-JVD-TRN-02072 | 036909C-JVD-TRN-02072 | IFR | 2019-07-18 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-MP-02072 |  | 2019-07-04 | 2
036909C-1024-TDS-0610-2451 | Mechanical Equipment Data Sheet - 10-E-2450 - LP Depropanizer Condenser | 0 | 2019-06-24 | IFP | OL1-2M03-2451 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-17 | 2
036909C-1024-TDS-0610-2446 | Mechanical Equipment Data Sheet - 10-E-2446 - LP Depropanizer Feed Cooler | 0 | 2019-07-09 | IFP | OL1-2M03-2446 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-18 | 2
036909C-1024-TDS-0610-2441 | Mechanical Equipment Data Sheet - 10-E-2441 - HP Deprop Reflux Chiller No. 2 | 0 | 2019-06-24 | IFP | OL1-2M03-2441 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-17 | 2
036909C-1024-TDS-0610-2439 | Mechanical Equipment Data Sheet - 10-E-2440 - HP Depropanizer Condenser | 0 | 2019-06-24 | IFP | OL1-2M03-2439 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-17 | 2
036909C-1024-TDS-0610-2434 | Mechanical Equipment Data Sheet - 10-E-2435 - Regen Gas Effluent Cooler | 0 | 2019-07-08 | IFP | OL1-2M03-2434 | ME | 2019-07-17 | 036909C-JVD-TRN-02174 | 036909C-JVD-TRN-02174 | IFR | 2019-08-01 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02174 |  | 2019-07-17 | 2
036909C-1010-SP-0810-1000 | Mechanical Equipment Data Sheet LPG Drum | 0 | 2019-07-11 | IFP | OL1-2M03-1000 | ME | 2019-07-11 | 036909C-JVD-TRN-02137 | 036909C-JVD-TRN-02137 | IFR | 2019-07-26 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-ME-02137 |  | 2019-07-15 | 2
036909C-1051-SP-1111-0003 | Mechanical Data Sheet For General Purpose Steam Turbines PT-5110 A Condensate Pump Turbine | 0 | 2019-07-05 | IMP | OL1-2M03-5172 | ME | 2019-07-11 | 036909C-JVD-TRN-02130 | 036909C-JVD-TRN-02130 | IFR | 2019-07-26 | 2019-08-01 | R2-Comments as noted | TPSK-LSPA1-T-ME-02130 |  | 2019-07-15 | 2
036909C-1051-SP-1111-0002 | Mechanical Data Sheet For General Purpose Steam Turbines PT-5102 A VLP BFW Pump Turbine | 0 | 2019-07-05 | IMP | OL1-2M03-5171 | ME | 2019-07-11 | 036909C-JVD-TRN-02130 | 036909C-JVD-TRN-02130 | IFR | 2019-07-26 | 2019-08-01 | R2-Comments as noted | TPSK-LSPA1-T-ME-02130 |  | 2019-07-15 | 2
036909C-1021-SP-1111-0002 | Mechanical Equipment Data Sheet For DSG Feed Pump Turbine | 0 | 2019-07-05 | IMP | OL1-2M03-2171 | ME | 2019-07-11 | 036909C-JVD-TRN-02130 | 036909C-JVD-TRN-02130 | IFR | 2019-07-26 | 2019-08-01 | R2-Comments as noted | TPSK-LSPA1-T-ME-02130 |  | 2019-07-15 | 2
036909C-1020-SP-1111-0001 | Mechanical Data Sheet For General Purpose Steam Turbines PT-2006 A Quench Oil Pump Turbne | 0 | 2019-07-05 | IMP | OL1-2M03-2070 | ME | 2019-07-11 | 036909C-JVD-TRN-02130 | 036909C-JVD-TRN-02130 | IFR | 2019-07-26 | 2019-08-01 | R2-Comments as noted | TPSK-LSPA1-T-ME-02130 |  | 2019-07-15 | 2
036909C-1000-DW-1652-0001 | Key Single Line Diagram | A | 2019-03-22 | IFR | OL1-2E14-0001 | EE | 2019-03-28 | ROC-TPSK-CECO-T-00027 | ROC-TPSK-CECO-T-00027, 036909C-JVD-TRN-01412 | IFR | 2019-04-08 | 2019-05-15 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01412 |  | 2019-04-19 | 1
036909C-1053-SP-0910-5361 | Mechanical Equipment Datasheet - CTU Cooling Water Pumps | 0 | 2019-07-02 | IFP | OL1-2M03-5361 | ME | 2019-07-10 | 036909C-JVD-TRN-02115 | 036909C-JVD-TRN-02115 | IFR | 2019-07-24 | 2019-08-02 | R2-Comments as noted | TPSK-LSPA1-T-ME-02115 |  | 2019-07-11 | 2
036909C-1000-MR-0811-0002 | Material Requisition For Shop Assembled CS Drums | 0 | 2019-07-19 | IFP | OL1-2C13-132000 | PL | 2019-07-19 | 036909C-JVD-TRN-02197 | 036909C-JVD-TRN-02197 | IFR | 2019-08-02 | 2019-07-31 | R1-No comments | TPSK-LSPA1-T-PL-02197 |  | 2019-07-22 | 2
036909C-1000-DW-1662-0001 | Medium Voltage Protection Diagram | A | 2018-12-18 | IFR | OL1-2E19-0001 | EE | 2018-12-20 | 036909C-JVD-TRN-00555 | 036909C-JVD-TRN-00555 | IFR | 2019-01-04 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00555 |  | 2018-12-20 | 2
036909C-1027-SP-1513-2702 | Instrument Interlock Descriptions - Area 27 - GHU & C4-C5 Hydrog | A | 2019-05-20 | IFR | OL1-2G50-2702 | PE | 2019-05-20 | 036909C-JVD-TRN-01697 | 036909C-JVD-TRN-01697 | IFR | 2019-06-04 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01697 |  | 2019-05-21 | 2
036909C-1027-DW-1514-2701 | Cause and Effect Diagram - Area 27 - GHU & C4-C5 Hydrog | A | 2019-04-25 | IFR | OL1-2G50-2701 | PE | 2019-04-25 | 036909C-JVD-TRN-01481 | 036909C-JVD-TRN-01481, ROC-TPSK-CECO-T-00055 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01481 |  | 2019-04-26 | 2
036909C-1051-PDS-0600-5107 | Process Equipment Datasheet - 10-E-5112 - Suspect Cond Flash Drum Vent Condenser | B | 2019-01-10 | IFD | OL1-2G30-5107 | PE | 2019-01-14 | 036909C-JVD-TRN-00646 | 036909C-JVD-TRN-00646 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00646 |  | 2019-01-14 | 2
036909C-1031-PDS-0800-3180 | Process Equipment Data Sheet - 10-D-3180 - BDU Knock Out Drum | B | 2019-06-05 | IFD | OL1-2G30-3180 | PE | 2019-06-06 | 036909C-JVD-TRN-01820 | 036909C-JVD-TRN-01820 | IFR | 2019-06-21 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01820 |  | 2019-06-10 | 2
036909C-1031-PDS-0800-3161 | Process Equipment Data Sheet - 10-D-3160 - BDU Condensate Drum | B | 2019-06-04 | IFD | OL1-2G30-3161 | PE | 2019-06-05 | 036909C-JVD-TRN-01813 | 036909C-JVD-TRN-01813 | IFR | 2019-06-20 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01813 |  | 2019-06-10 | 2
036909C-1031-PDS-0800-3126 | Process Equipment Data Sheet - 10-D-3126 - Ejector Seal Drum | B | 2019-06-04 | IFD | OL1-2G30-3126 | PE | 2019-06-05 | 036909C-JVD-TRN-01813 | 036909C-JVD-TRN-01813 | IFR | 2019-06-20 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01813 |  | 2019-06-10 | 2
036909C-1031-PDS-0800-3112 | Process Equipment Data Sheet - 10-D-3110 - Water Washer Accumulator | B | 2019-06-04 | IFD | OL1-2G30-3112 | PE | 2019-06-05 | 036909C-JVD-TRN-01813 | 036909C-JVD-TRN-01813 | IFR | 2019-06-20 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01813 |  | 2019-06-10 | 2
036909C-1031-PDS-0800-3100 | Process Equipment Data Sheet - 10-D-3100 - Solvent Regen Drum | B | 2019-06-04 | IFD | OL1-2G30-3100 | PE | 2019-06-05 | 036909C-JVD-TRN-01813 | 036909C-JVD-TRN-01813 | IFR | 2019-06-20 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01813 |  | 2019-06-10 | 2
036909C-1030-PDS-0800-3082 | Process Equipment Data Sheet - 10-D-3080 - Butadiene Tower Reflux Drum | B | 2019-06-04 | IFD | OL1-2G30-3082 | PE | 2019-06-05 | 036909C-JVD-TRN-01813 | 036909C-JVD-TRN-01813 | IFR | 2019-06-20 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01813 |  | 2019-06-10 | 2
036909C-1030-PDS-0800-3065 | Process Equipment Data Sheet - 10-D-3062 - C4 Acetylene Accumulator | B | 2019-06-04 | IFD | OL1-2G30-3065 | PE | 2019-06-05 | 036909C-JVD-TRN-01813 | 036909C-JVD-TRN-01813 | IFR | 2019-06-20 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01813 |  | 2019-06-10 | 2
036909C-1030-PDS-0800-3064 | Process Equipment Data Sheet - 10-D-3060 - BDU HC-Water Separator | B | 2019-05-31 | IFD | OL1-2G30-3064 | PE | 2019-06-04 | 036909C-JVD-TRN-01802 | 036909C-JVD-TRN-01802 | IFR | 2019-06-19 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01802 |  | 2019-06-10 | 2
036909C-1030-PDS-0800-3032 | Process Equipment Data Sheet - 10-D-3030 - After Washer Reflux Drum | B | 2019-05-31 | IFD | OL1-2G30-3032 | PE | 2019-06-04 | 036909C-JVD-TRN-01802 | 036909C-JVD-TRN-01802 | IFR | 2019-06-19 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01802 |  | 2019-06-10 | 2
036909C-1030-PDS-0800-3022 | Process Equipment Data Sheet - 10-D-3020 - Main Washer Reflux Drum | B | 2019-06-05 | IFD | OL1-2G30-3022 | PE | 2019-06-06 | 036909C-JVD-TRN-01820 | 036909C-JVD-TRN-01820 | IFR | 2019-06-21 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01820 |  | 2019-06-10 | 2
036909C-1030-PDS-0800-3003 | Process Equipment Data Sheet - 10-D-3000 - Predistillation Tower Reflux Drum | B | 2019-05-31 | IFD | OL1-2G30-3003 | PE | 2019-06-04 | 036909C-JVD-TRN-01802 | 036909C-JVD-TRN-01802 | IFR | 2019-06-19 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01802 |  | 2019-06-10 | 2
036909C-1030-PDS-0800-3002 | Process Equipment Data Sheet - 10-D-3002 - Predistillation Feed Drum | B | 2019-05-31 | IFD | OL1-2G30-3002 | PE | 2019-06-04 | 036909C-JVD-TRN-01802 | 036909C-JVD-TRN-01802 | IFR | 2019-06-19 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PE-01802 |  | 2019-06-10 | 2
036909C-1052-DW-1514-5201 | Cause and Effect Diagram - Area 52 - Fuel System | A | 2019-04-24 | IFR | OL1-2G50-5201 | PE | 2019-04-25 | 036909C-JVD-TRN-01480 | 036909C-JVD-TRN-01480, ROC-TPSK-CECO-T-00055 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01480 |  | 2019-04-26 | 2
036909C-1051-DW-1514-5101 | Cause and Effect Diagram - Area 51 - BFW- Steam - Steam Condensate System | A | 2019-04-23 | IFR | OL1-2G50-5101 | PE | 2019-04-24 | 036909C-JVD-TRN-01471 | 036909C-JVD-TRN-01471, ROC-TPSK-CECO-T-00053 | IFR | 2019-05-09 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01471 |  | 2019-04-25 | 2
036909C-1053-PDS-0300-5351 | Process Equipment Datasheet - 10-PIT-5351 A-H - Olefins CW Pumps Sump | B | 2019-01-31 | IFD | OL1-2G30-5351 | PE | 2019-02-01 | 036909C-JVD-TRN-00791 | 036909C-JVD-TRN-00791, ROC-TPSK-CECO-T-00020 | IFI |  | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00791 |  | 2019-02-04 | 2
036909C-1055-SP-0810-5515 | Mechanical Equipment Data Sheet - Methanol Makeup Drum | 0 | 2019-07-10 | IFP | OL1-2M03-5515 | ME | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1055-TDS-0610-5512 | Mechanical Equipment Data Sheet - 10-E-5512 - Cold Flare Superheater | 0 | 2019-07-02 | IFP | OL1-2M03-5512 | ME | 2019-07-16 | 036909C-JVD-TRN-02165 | 036909C-JVD-TRN-02165 | IFR | 2019-07-31 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-02165 |  | 2019-07-17 | 2
036909C-1028-TDS-0610-2857 | Mechanical Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer | 0 | 2019-06-24 | IFP | OL1-2M03-2857 | ME | 2019-07-15 | 036909C-JVD-TRN-02155 | 036909C-JVD-TRN-02155 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | 036909C-JVD-TRN-02155 |  | 2019-07-16 | 2
036909C-1028-SP-0810-2820 | Mechanical Equipment Data Sheet C3R 2nd Stage Suction Drum | 0 | 2019-07-10 | IFP | OL1-2M03-2820 | HOC Mech | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1028-SP-0810-2815 | Mechanical Equipment Data Sheet For C3R Drain Drum | 0 | 2019-07-10 | IFP | OL1-2M03-2815 | ME | 2019-07-15 | 036909C-JVD-TRN-02154 | 036909C-JVD-TRN-02154 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-02154 |  | 2019-07-16 | 2
036909C-1024-TDS-0610-2413 | Mechanical Equipment Data Sheet - 10-E-2413 - HP Deprop Feed Overhead Exchanger | 0 | 2019-06-24 | IFP | OL1-2M03-2413 | ME | 2019-07-15 | 036909C-JVD-TRN-02155 | 036909C-JVD-TRN-02155 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | 036909C-JVD-TRN-02155 |  | 2019-07-16 | 2
036909C-1024-TDS-0610-2412 | Mechanical Equipment Data Sheet - 10-E-2412 - HP Deprop Feed Chiller | 0 | 2019-06-21 | IFP | OL1-2M03-2412 | ME | 2019-07-15 | 036909C-JVD-TRN-02155 | 036909C-JVD-TRN-02155 | IFR | 2019-07-30 | 2019-08-05 | R1-No comments | 036909C-JVD-TRN-02155 |  | 2019-07-16 | 2
036909C-1029-PDS-1390-2935 | Piping Specialty Item - Datasheet - T-Type Filter - P-2910 5th STG Suction - 10-SP-29035 | A | 2019-06-27 | IFR | OL1-2P03-2935 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2934 | Piping Specialty Item - Datasheet - T-Type Filter - P-2910 4th STG Suction - 10-SP-29034 | A | 2019-07-27 | IFR | OL1-2P03-2934 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2933 | Piping Specialty Item - Datasheet - T-Type Filter - P-2910 3rD STG Suction - 10-SP-29033 | A | 2019-06-27 | IFR | OL1-2P03-2933 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2932 | Piping Specialty Item - Datasheet - T-Type Filter - P-2910 2nd STG Suction - 10-SP-29032 | A | 2019-06-27 | IFR | OL1-2P03-2932 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2931 | Piping Specialty Item - Datasheet - T-Type Filter - P-2910 1st STG Suction - 10-SP-29031 | A | 2019-06-27 | IFR | OL1-2P03-2931 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2929 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2861A Suction - 10-SP-29029 | A | 2019-06-27 | IFR | OL1-2P03-2929 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2927 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2201A Suction - 10-SP-29027 | A | 2019-06-27 | IFR | OL1-2P03-2927 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2924 | Piping Specialty Item - Datasheet - T-Type Filter - CT-2800 Suction - 10-SP-29024 | A | 2019-06-27 | IFR | OL1-2P03-2924 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2922 | Piping Specialty Item - Datasheet - T-Type Filter - P-2802 A-B Suction - 10-SP-29022 | A | 2019-06-26 | IFR | OL1-2P03-2922 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2920 | Piping Specialty Item - Datasheet - T-Type Filter - CT-2800 Suction - 10-SP-29020 | A | 2019-06-27 | IFR | OL1-2P03-2920 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2919 | Piping Specialty Item - Datasheet - T-Type Filter - P2862 A-B Suction - 10-SP-29019 | A | 2019-06-26 | IFR | OL1-2P03-2919 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2916 | Piping Specialty Item - Datasheet - T-Type Filter - CT-2850 Suction - 10-SP-29016 | A | 2019-06-27 | IFR | OL1-2P03-2916 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2911 | Piping Specialty Item - Datasheet - T-Type Filter - CT-2200 Suction - 10-SP-29011 | A | 2019-06-27 | IFR | OL1-2P03-2911 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2907 | Piping Specialty Item - Datasheet - T-Type Filter - P-2202 A-B Suction - 10-SP-29007 | A | 2019-06-26 | IFR | OL1-2P03-2907 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2906 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2146A Suction - 10-SP-29006 | A | 2019-06-26 | IFR | OL1-2P03-2906 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-02 | 2
036909C-1029-PDS-1390-2905 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2106A Suction - 10-SP-29005 | A | 2019-06-26 | IFR | OL1-2P03-2905 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2904 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2006A Suction - 10-SP-29004 | A | 2019-06-26 | IFR | OL1-2P03-2904 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2901 | Piping Specialty Item - Datasheet - T-Type Filter - P-2930 Suction - 10-SP-29001 | A | 2019-06-26 | IFR | OL1-2P03-2901 | MP | 2019-07-02 | 036909C-JVD-TRN-02058 | 036909C-JVD-TRN-02058 | IFR | 2019-07-17 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-PE-02058 |  | 2019-07-03 | 2
036909C-1022-DW-1514-2201 | Cause and Effect Diagram - Area 22 - Cracked Gas Compressor | A | 2019-03-27 | IFR | OL1-2G50-2201 | PE | 2019-03-28 | 036909C-JVD-TRN-01183 | 036909C-JVD-TRN-01183 | IFR | 2019-04-12 | 2019-08-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-01183 |  | 2019-03-29 | 2
036909C-1022-DW-1514-2201 | Cause and Effect Diagram - Area 22 - Cracked Gas Compressor | B | 2019-03-29 | IFR | OL1-2G50-2201 | PE | 2019-03-29 | 036909C-JVD-TRN-01204 | 036909C-JVD-TRN-01204, ROC-TPSK-CECO-T-00032 | IFR | 2019-04-15 | 2019-08-05 | R2-Comments as noted | TPSK-LSPA1-T-PE--01204 |  | 2019-04-01 | 2
036909C-1022-PDS-1390-2214 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2200 4th Stage Suction - 10-SP-22014 | A | 2019-06-21 | IFR | OL1-2P03-2214 | MP | 2019-06-25 | 036909C-JVD-TRN-01985 | 036909C-JVD-TRN-01985 | IFR | 2019-07-09 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-MP-01985 |  | 2019-06-26 | 2
036909C-1010-SP-1513-1002 | Instrument Interlock Descriptions Area 10 Feed Preparation and Feed Preheat | B | 2019-06-26 | IBD | OL1-2G50-1004 | PE | 2019-06-26 | 036909C-JVD-TRN-02005 | 036909C-JVD-TRN-02005 | IFR | 2019-07-11 | 2019-08-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-02005 |  | 2019-06-27 | 2
036909C-1059-SP-1513-5902 | Instrument Interlock Descriptions Area 59 Supporting Utilities Auxiliaries | B | 2019-06-28 | IBD | OL1-2G50-5902 | IE | 2019-07-01 | 036909C-JVD-TRN-02038 | 036909C-JVD-TRN-02038 | IFR | 2019-07-16 | 2019-08-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-02038 |  | 2019-07-09 | 2
036909C-1053-SP-1513-5302 | Instrument Interlock Descriptions Area 53 Cooling Water System | B | 2019-06-28 | IBD | OL1-2G50-5302 | IE | 2019-07-01 | 036909C-JVD-TRN-02038 | 036909C-JVD-TRN-02038 | IFR | 2019-07-16 | 2019-08-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-02038 |  | 2019-07-09 | 2
036909C-1021-SP-1513-2102 | Instrument Interlock Descriptions Area 21 Quench Water Dilution Stem | B | 2019-06-28 | IBD | OL1-2G50-2102 | IE | 2019-07-01 | 036909C-JVD-TRN-02038 | 036909C-JVD-TRN-02038 | IFR | 2019-07-16 | 2019-08-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-02038 |  | 2019-07-09 | 2
036909C-1020-SP-1513-2002 | Instrument Interlock Descriptions Area 20 Quench Oil | B | 2019-06-28 | IBD | OL1-2G50-2002 | IE | 2019-07-01 | 036909C-JVD-TRN-02038 | 036909C-JVD-TRN-02038 | IFR | 2019-07-16 | 2019-08-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-02038 |  | 2019-07-09 | 2
036909C-1012-DW-0117-2002 | USC 132U Cracking Furnace General Arrangement Longitudinal Elevation | 1 | 2019-06-21 | IMP | OL1-2M06-2002 | ME | 2019-06-25 | 036909C-JVD-TRN-01993 | 036909C-JVD-TRN-01993 | IFR | 2019-07-10 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-01993 |  | 2019-06-26 | 2
036909C-1011-DW-0117-1002 | USC 36M Recycle Furnace General Arrangement Longitudinal Elevation | 1 | 2019-06-21 | IMP | OL1-2M06-1002 | ME | 2019-06-25 | 036909C-JVD-TRN-01993 | 036909C-JVD-TRN-01993 | IFR | 2019-07-10 | 2019-08-05 | R1-No comments | TPSK-LSPA1-T-ME-01993 |  | 2019-06-26 | 2
036909C-1055-SP-0810-5510 | Mechanical Equipment Data Sheet For Cold Flare Drum | 0 | 2019-07-11 | IFP | OL1-2M03-5510 | ME | 2019-07-11 | 036909C-JVD-TRN-02138 | 036909C-JVD-TRN-02138 | IFR | 2019-07-26 | 2019-08-05 | R2-Comments as noted | TPSK-LSPA1-T-ME-02138 |  | 2019-07-15 | 2
036909C-1055-SP-0810-5500 | Mechanical Equipment Data Sheet Hot Flare Drum | 0 | 2019-07-11 | IFP | OL1-2M03-5500 | ME | 2019-07-11 | 036909C-JVD-TRN-02138 | 036909C-JVD-TRN-02138 | IFR | 2019-07-26 | 2019-08-05 | R2-Comments as noted | TPSK-LSPA1-T-ME-02138 |  | 2019-07-15 | 2
036909C-102E-DW-1744-0001-001 | Concrete Basin 10-PIT-2390 - Formwork | A | 2019-07-22 | IFR | OL1-2K31-3120 | CV | 2019-08-01 | 036909C-JVD-TRN-02313 | 036909C-JVD-TRN-02313 | IFA | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-CV-02313 |  | 2019-08-05 | 1
036909C-102E-DW-1744-0001-002 | Concrete Basin 10-PIT-2390 - Reinforcement | A | 2019-07-22 | IFR | OL1-2K31-3121 | CV | 2019-08-01 | 036909C-JVD-TRN-02313 | 036909C-JVD-TRN-02313 | IFA | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-CV-02313 |  | 2019-08-05 | 1
036909C-102B-CN-1834-0003 | Calculation For Steel Platform For 10-PIT-2392 | A | 2019-07-10 | IFR | OL1-2K15-0095 | CV | 2019-08-01 | 036909C-JVD-TRN-02312 | 036909C-JVD-TRN-02312 | IFA | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-CV-02312 |  | 2019-08-05 | 1
036909C-1000-ML-1005 | Sampling and Analytical Manual | 0 | 2019-07-31 | IFI | OL1-2O80-1005 | PE | 2019-08-02 | 036909C-JVD-TRN-02325 | 036909C-JVD-TRN-02325 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02325 | TPSK-LSPA1-T-PE-02325 | 2019-08-05 | 3
036909C-1000-NM-0001-1001 | Overall Material Balance | 0 | 2019-03-29 | IFI | OL1-2G44-1001 | PE | 2019-03-29 | 036909C-JVD-TRN-01199 | 036909C-JVD-TRN-01199 | IFI |  | 2019-04-22 | R1-No comments | TPSK-LSPA1-T-PE-01199 |  | 2019-04-01 | 3
036909C-1056-PDS-2600-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg | C | 2019-02-01 | IFD | OL1-2G30-5670 | PE | 2019-02-01 | 036909C-JVD-TRN-00797 | 036909C-JVD-TRN-00797, ROC-TPSK-CECO-T-00020 | IFI |  | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00797 |  | 2019-02-04 | 2
036909C-1056-PDS-2600-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg | D | 2019-05-07 | IFD | OL1-2G30-5670 | PE | 2019-05-07 | 036909C-JVD-TRN-01606 | 036909C-JVD-TRN-01606 | IFR | 2019-05-22 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-01606 |  | 2019-05-08 | 2
036909C-1056-PDS-2600-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg | D | 2019-05-07 | IFD | OL1-2G30-5650 | PE | 2019-05-07 | 036909C-JVD-TRN-01606 | 036909C-JVD-TRN-01606 | IFR | 2019-05-22 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-01606 |  | 2019-05-08 | 2
036909C-1056-PDS-2600-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg | C | 2019-02-01 | IFD | OL1-2G30-5650 | PE | 2019-02-01 | 036909C-JVD-TRN-00797 | 036909C-JVD-TRN-00797, ROC-TPSK-CECO-T-00020 | IFI |  | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00797 |  | 2019-02-04 | 2
036909C-1056-PDS-2600-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package | D | 2019-05-07 | IFD | OL1-2G30-5644 | PE | 2019-05-07 | 036909C-JVD-TRN-01606 | 036909C-JVD-TRN-01606 | IFR | 2019-05-22 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-01606 |  | 2019-05-08 | 2
036909C-1056-PDS-2600-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package | C | 2019-02-01 | IFD | OL1-2G30-5644 | PE | 2019-02-01 | 036909C-JVD-TRN-00797 | 036909C-JVD-TRN-00797, ROC-TPSK-CECO-T-00020 | IFI |  | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00797 |  | 2019-02-04 | 2
036909C-1056-PDS-0200-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg | C | 2019-02-01 | IFD | OL1-2G30-5653 | PE | 2019-02-01 | 036909C-JVD-TRN-00798 | 036909C-JVD-TRN-00798, ROC-TPSK-CECO-T-00020 | IFI |  | 2019-03-11 | R1-No comments | TPSK-LSPA1-T-PE-00798 |  | 2019-02-04 | 2
036909C-1053-PDS-0300-5360 | Process Equipment Datasheet - 10-PIT-5360 A-C - CTU CW Pumps Sump | B | 2019-01-31 | IFD | OL1-2G30-5360 | PE | 2019-02-01 | 036909C-JVD-TRN-00791 | 036909C-JVD-TRN-00791, ROC-TPSK-CECO-T-00020 | IFI |  | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00791 |  | 2019-02-04 | 2
036909C-105F-DW-1622-0101 | Electrical Main Cable Routing Layout - Zone 5F HP & Polyolefins Flares | A | 2019-07-31 | IFR | OL1-2E31-0008 | EE | 2019-08-01 | 036909C-JVD-TRN-02307 | 036909C-JVD-TRN-02307 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-EE-02307 |  | 2019-08-05 | 1
036909C-1000-JSD-1900-0002 | Clean Agent Fire Extinguishing System | 0 | 2019-07-26 | IFE | OL1-2L01-0003 | SE | 2019-08-01 | 036909C-JVD-TRN-02308 | 036909C-JVD-TRN-02308 | IFR | 2019-08-16 |  | Transmitted | TPSK-LSPA1-T-SE-02308 |  | 2019-08-05 | 2
036909C-1000-JSD-1511-0002 | Integrated Control And Safety System | 0 | 2019-06-13 | IMP | OL1-2R06-0015 | IE | 2019-06-14 | 036909C-JVD-TRN-01897 | 036909C-JVD-TRN-01897 | IFR | 2019-07-01 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-IE-01897 |  | 2019-06-17 | 2
036909C-1051-SP-0836-5130 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51030A/B/C/D - PSV-5150A/B/C/D Outlet | A | 2019-07-09 | IFQ | OL1-2M03-5130 | ME | 2019-07-12 | 036909C-JVD-TRN-02143 | 036909C-JVD-TRN-02143 | IFR | 2019-07-26 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02143 |  | 2019-07-15 | 2
036909C-1051-SP-0836-5126 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51026A-H - PSV-5143A-H Outlet | A | 2019-07-09 | IFQ | OL1-2M03-5126 | ME | 2019-07-12 | 036909C-JVD-TRN-02143 | 036909C-JVD-TRN-02143 | IFR | 2019-07-26 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02143 |  | 2019-07-15 | 2
036909C-1051-SP-0836-5124 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51024 - PV-5158 Outlet | A | 2019-07-09 | IFQ | OL1-2M03-5124 | ME | 2019-07-12 | 036909C-JVD-TRN-02143 | 036909C-JVD-TRN-02143 | IFR | 2019-07-26 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02143 |  | 2019-07-15 | 2
036909C-1051-SP-0836-5123 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51023 - PV-5155 Outlet | A | 2019-07-09 | IFQ | OL1-2M03-5123 | ME | 2019-07-12 | 036909C-JVD-TRN-02143 | 036909C-JVD-TRN-02143 | IFR | 2019-07-26 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02143 |  | 2019-07-15 | 2
036909C-1051-SP-0836-5122 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51022 - PV-5147 Outlet | A | 2019-07-09 | IFQ | OL1-2M03-5122 | ME | 2019-07-12 | 036909C-JVD-TRN-02143 | 036909C-JVD-TRN-02143 | IFR | 2019-07-26 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02143 |  | 2019-07-15 | 2
036909C-1029-SP-0836-2926 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-29026 - Start-up | A | 2019-07-09 | IFQ | OL1-2M03-2926 | ME | 2019-07-12 | 036909C-JVD-TRN-02143 | 036909C-JVD-TRN-02143 | IFR | 2019-07-26 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02143 |  | 2019-07-15 | 2
036909C-1029-SP-0836-2921 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-29021 - Start-up | A | 2019-07-09 | IFQ | OL1-2M03-2921 | ME | 2019-07-12 | 036909C-JVD-TRN-02143 | 036909C-JVD-TRN-02143 | IFR | 2019-07-26 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02143 |  | 2019-07-15 | 2
036909C-1029-SP-0836-2915 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-29015 - Start-up | A | 2019-07-09 | IFQ | OL1-2M03-2915 | ME | 2019-07-12 | 036909C-JVD-TRN-02143 | 036909C-JVD-TRN-02143 | IFR | 2019-07-26 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02143 |  | 2019-07-15 | 2
036909C-1000-MR-1031-0001 | Material Requisition for Recycle Gas Compressor | 0 | 2019-07-09 | IFP | OL1-2C13-403000 | PL | 2019-07-09 | 036909C-JVD-TRN-02106 | 036909C-JVD-TRN-02106 | IFR | 2019-07-23 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-PL-02106 |  | 2019-07-10 | 2
036909C-1000-MR-0811-0001 | Material Requisition For Shop Assembled Large Drums | 0 | 2019-07-16 | IFP | OL1-2C13-131000 | PL | 2019-07-17 | 036909C-JVD-TRN-02170 | 036909C-JVD-TRN-02170 | IFR | 2019-07-31 | 2019-08-01 | R2-Comments as noted | TPSK-LSPA1-T-PL-02070 |  | 2019-07-17 | 2
036909C-1030-SP-1031-3073 | Mechanical Equipment Datasheet BDU Recycle Gas Compressor | 0 | 2019-07-02 | IFP | OL1-2M03-3073 | ME | 2019-07-09 | 036909C-JVD-TRN-02105 | 036909C-JVD-TRN-02105 | IFR | 2019-07-23 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02105 | Please note that Rev A and B were issued by HOC. We (KLOC) are now issuing Rev 0, hence we had to 'Create Document'. | 2019-07-10 | 2
036909C-1011-SP-0836-1114 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-11014 - Start-up | A | 2019-07-09 | IFQ | OL1-2M03-1114 | ME | 2019-07-11 | 036909C-JVD-TRN-02129 | 036909C-JVD-TRN-02129 | IFR | 2019-07-25 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02129 |  | 2019-07-15 | 2
036909C-1011-SP-0836-1113 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-11013 - PSV-1144 Outlet | A | 2019-07-09 | IFQ | OL1-2M03-1113 | ME | 2019-07-11 | 036909C-JVD-TRN-02129 | 036909C-JVD-TRN-02129 | IFR | 2019-07-25 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02129 |  | 2019-07-15 | 2
036909C-1012-SP-0836-1214 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-12014/16014 - Start-up | A | 2019-07-09 | IFQ | OL1-2M03-1214 | ME | 2019-07-11 | 036909C-JVD-TRN-02129 | 036909C-JVD-TRN-02129 | IFR | 2019-07-25 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02129 |  | 2019-07-15 | 2
036909C-1012-SP-0836-1213 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-12013/16013 - PSV-1244 Outlet | A | 2019-07-09 | IFQ | OL1-2M03-1213 | ME | 2019-07-11 | 036909C-JVD-TRN-02129 | 036909C-JVD-TRN-02129 | IFR | 2019-07-25 | 2019-08-01 | R1-No comments | TPSK-LSPA1-T-ME-02129 |  | 2019-07-15 | 2
036909C-1000-DL-1530-0002 | Deviation List For Safety Supervisory System | B | 2019-07-16 | IFR | OL1-2C42-851000 | PL | 2019-07-18 | 036909C-JVD-TRN-02180 | 036909C-JVD-TRN-02180 | IFR | 2019-08-01 | 2019-07-30 | R1-No comments | TPSK-LSPA1-T-PL-02180 |  | 2019-07-19 | 2
036909C-1056-PDS-0900-5624 | Process Equipment Datasheet - 10-P-5627 A-B - Gate 4 Septic Tank Pumps | C | 2019-03-21 | IFD | OL1-2G30-5624 | PE | 2019-03-25 | 036909C-JVD-TRN-01152 | 036909C-JVD-TRN-01152 | IFR | 2019-04-09 | 2019-04-12 | R1-No comments | TPSK-LSPA1-T-PE-01152 |  | 2019-03-26 | 2
036909C-1056-PDS-0200-5627 | Process Equipment Datasheet - 10-PIT-5627 - West Gate House Septic Tank | B | 2019-02-07 | IFD | OL1-2G30-5627 | PE | 2019-02-11 | 036909C-JVD-TRN-00838 | 036909C-JVD-TRN-00838, ROC-TPSK-CECO-T-00020 | IFI |  | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00838 |  | 2019-02-11 | 2
036909C-1056-PDS-0200-5627 | Process Equipment Datasheet - 10-PIT-5627 - Gate 4 Septic Tank | C | 2019-04-03 | IFD | OL1-2G30-5627 | PE | 2019-04-04 | 036909C-JVD-TRN-01257 | 036909C-JVD-TRN-01257, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-19 | 2019-05-16 | Response to Client Comments sent on July 02 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01257 |  | 2019-04-05 | 2
036909C-1056-PDS-0200-5626 | Process Equipment Datasheet - 10-PIT-5626 - Far C Septic Tank | C | 2019-04-03 | IFD | OL1-2G30-5626 | PE | 2019-04-04 | 036909C-JVD-TRN-01257 | 036909C-JVD-TRN-01257, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-19 | 2019-05-16 | Response to Client Comments sent July 02 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01257 |  | 2019-04-05 | 2
036909C-1056-PDS-0200-5626 | Process Equipment Datasheet - 10-PIT-5626 - Gate House Septic Tank | B | 2019-02-07 | IFD | OL1-2G30-5626 | PE | 2019-02-11 | 036909C-JVD-TRN-00838 | 036909C-JVD-TRN-00838, ROC-TPSK-CECO-T-00020 | IFI |  | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00838 |  | 2019-02-11 | 2
036909C-1026-SP-1513-2601 | Complex Loop Narratives - Area 26 - Hot Fractionation | A | 2019-05-13 | IFR | OL1-2I71-2601 | IE | 2019-05-14 | 036909C-JVD-TRN-01662 | 036909C-JVD-TRN-01662 | IFR | 2019-05-29 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-IE-01662 |  | 2019-05-15 | 2
036909C-1000-SP-1641-1501 | Data Sheet for Distribution Transformer | A | 2019-03-25 | IFR | OL1-2E05-1501 | EE | 2019-03-29 | 036909C-JVD-TRN-01192 | 036909C-JVD-TRN-01192, ROC-TPSK-CECO-T-00037 | IFA | 2019-04-08 | 2019-04-23 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01192 |  | 2019-04-01 | 1
036909C-1000-JSD-1530-0003 | Telecom Numbering | A | 2019-02-19 | IFR | OL1-2R05-0028 | EE | 2019-02-21 | 036909C-JVD-TRN-00905 | 036909C-JVD-TRN-00905 | IFR | 2019-03-08 | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-EE-00905 |  | 2019-02-22 | 2
036909C-1000-MR-1530-0002 | Material Requisition For Safety Supervisory System | A | 2019-03-01 | IFQ | OL1-2C16-851000 | PL | 2019-03-05 | 036909C-JVD-TRN-00984 | 036909C-JVD-TRN-00984 | IFR | 2019-03-18 | 2019-04-05 | R2-Comments as noted | TPSK-LSPA1-T-PL-00984 |  | 2019-03-05 | 2
036909C-1000-JSD-1900-0002 | Clean Agent Fire Extinguishing System | A | 2019-04-17 | IFR | OL1-2L01-0003 | SE | 2019-04-23 | 036909C-JVD-TRN-01441 | 036909C-JVD-TRN-01441 | IFI |  |  | Transmitted | TPSK-LSPA1-T-SE-01441 |  | 2019-04-24 | 3
036909C-102E-DW-1741-0002-033 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Steel Bracings Details | A | 2019-07-26 | IFR | OL1-2K31-5162 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-031 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Steel Bracings Details | A | 2019-07-26 | IFR | OL1-2K31-5160 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-030 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Steel Bracings Details | A | 2019-07-26 | IFR | OL1-2K31-5159 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-029 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams | A | 2019-07-25 | IFR | OL1-2K31-5158 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-032 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Steel Bracings Details | A | 2019-07-26 | IFR | OL1-2K31-5161 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-028 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams | A | 2019-07-25 | IFR | OL1-2K31-5157 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-022 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams | A | 2019-07-25 | IFR | OL1-2K31-5151 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-018 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns | A | 2019-07-25 | IFR | OL1-2K31-1277 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-019 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns | A | 2019-07-25 | IFR | OL1-2K31-1278 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-023 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams | A | 2019-07-25 | IFR | OL1-2K31-5152 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-017 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns | A | 2019-07-25 | IFR | OL1-2K31-1276 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-020 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns | A | 2019-07-25 | IFR | OL1-2K31-1279 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-026 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams | A | 2019-07-25 | IFR | OL1-2K31-5155 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-021 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams | A | 2019-07-25 | IFR | OL1-2K31-5150 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-024 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams | A | 2019-07-25 | IFR | OL1-2K31-5153 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-027 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams | A | 2019-07-25 | IFR | OL1-2K31-5156 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-025 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams | A | 2019-07-25 | IFR | OL1-2K31-5154 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-008 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations | A | 2019-07-25 | IFR | OL1-2K31-1267 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-011 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns | A | 2019-07-25 | IFR | OL1-2K31-1270 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-005 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations | A | 2019-07-25 | IFR | OL1-2K31-1264 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-010 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations | A | 2019-07-25 | IFR | OL1-2K31-1269 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-007 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations | A | 2019-07-25 | IFR | OL1-2K31-1266 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-012 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns | A | 2019-07-25 | IFR | OL1-2K31-1271 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-009 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations | A | 2019-07-25 | IFR | OL1-2K31-1268 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-003 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Plans | A | 2019-07-25 | IFR | OL1-2K31-1262 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-015 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns | A | 2019-07-25 | IFR | OL1-2K31-1274 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-004 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Plans | A | 2019-07-25 | IFR | OL1-2K31-1263 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-006 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations | A | 2019-07-25 | IFR | OL1-2K31-1265 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-014 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns | A | 2019-07-25 | IFR | OL1-2K31-1273 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-013 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns | A | 2019-07-25 | IFR | OL1-2K31-1272 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-016 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns | A | 2019-07-25 | IFR | OL1-2K31-1275 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102D-DW-1842-0002-002 | Steel Structure For 10-SHT-2D02 | A | 2019-07-29 | IFR | OL1-2K32-2121 | CV | 2019-07-31 | 036909C-JVD-TRN-02302 | 036909C-JVD-TRN-02302 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02302 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-002 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Plans | A | 2019-07-25 | IFR | OL1-2K31-1261 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102E-CN-1731-0002 | Calculation Notes For Precast Concrete Elevation Of Pipe Rack 10-PRK-2E01 | A | 2019-07-25 | IFR | OL1-2K14-0012 | CV | 2019-07-31 | 036909C-JVD-TRN-02303 | 036909C-JVD-TRN-02303 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02303 |  | 2019-08-01 | 1
036909C-102E-DW-1741-0002-001 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - 3D View | A | 2019-07-26 | IFR | OL1-2K31-1260 | CV | 2019-07-31 | 036909C-JVD-TRN-02301 | 036909C-JVD-TRN-02301 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02301 |  | 2019-08-01 | 1
036909C-102D-DW-1842-0002-001 | Steel Structure For 10-SHT-2D02 | A | 2019-07-29 | IFR | OL1-2K32-2120 | CV | 2019-07-31 | 036909C-JVD-TRN-02302 | 036909C-JVD-TRN-02302 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02302 |  | 2019-08-01 | 1
036909C-102D-DW-1742-0002-001 | Foundation Of Steel Structure For 10-SHT-2D02 | A | 2019-07-29 | IFR | OL1-2K31-1800 | CV | 2019-07-31 | 036909C-JVD-TRN-02304 | 036909C-JVD-TRN-02304 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02304 |  | 2019-08-01 | 1
036909C-102D-CN-1832-0002 | Calculation Note For Steel Structure 10-SHT-2D02 | A | 2019-07-26 | IFR | OL1-2K15-0025 | CV | 2019-07-31 | 036909C-JVD-TRN-02303 | 036909C-JVD-TRN-02303 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02303 |  | 2019-08-01 | 1
036909C-102D-CN-1732-0002 | Calculation Note For Foundation Of 10-SHT-2D02 | A | 2019-07-26 | IFR | OL1-2K14-0025 | CV | 2019-07-31 | 036909C-JVD-TRN-02303 | 036909C-JVD-TRN-02303 | IFA | 2019-08-15 |  | Transmitted | TPSK-LSPA1-T-CV-02303 |  | 2019-08-01 | 1
036909C-1012-JSS-0000-9999 | General Supply Rules for Supplier Documentation | C | 2019-01-30 | IFI | OL1-2C93-0001 | PL | 2019-02-06 | 036909C-JVD-TRN-00777 | 036909C-JVD-TRN-00777 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00777 |  | 2019-02-01 | 3
036909C-1000-STC-1691-0001 | Typical Installation Standards For Electrical Equipment | A | 2019-03-13 | IFR | OL1-2E03-0035 | EE | 2019-04-01 | ROC-TPSK-CECO-T-00032 | ROC-TPSK-CECO-T-00032, 036909C-JVD-TRN-01193 | IFR | 2019-04-10 | 2019-05-07 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01193 |  | 2019-04-02 | 1
036909C-1000-MR-1530-0001 | Material Requisition For Intercom/Paging/Audible Alarm System | A | 2019-03-01 | IFQ | OL1-2C16-881000 | PL | 2019-03-05 | 036909C-JVD-TRN-00984 | 036909C-JVD-TRN-00984 | IFR | 2019-03-18 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-PL-00984 |  | 2019-03-05 | 2
036909C-105F-NM-1350-0030 | Loads On Rack 10-PRK-5F01 | A | 2019-07-11 | IBD | OL1-2P05-0191 | MP | 2019-07-12 | 036909C-JVD-TRN-02142 | 036909C-JVD-TRN-02142 | IFR | 2019-07-26 | 2019-07-30 | R2-Comments as noted | TPSK-LSPA1-T-MP-02142 |  | 2019-07-15 | 2
036909C-1000-PO-036909C001P46-046 | Vendor Acknowledgment of Purchase Order for HP / Polyolefins Flare Package | 0 | 2019-07-10 | IFI | OL-1-2C51-0104 | PL | 2019-07-11 | 036909C-JVD-TRN-02126 | 036909C-JVD-TRN-02126 | IFI | 2019-07-25 | 2019-07-30 | R1-No comments | TPSK-LSPA1-T-PL-02126 |  | 2019-07-11 | 3
036909C-1000-DL-0232-0001 | Deviation List For Complex Waste Water Treatment Package | B | 2019-07-09 | IFR | OL1-2C40-702000 | PL | 2019-07-11 | 036909C-JVD-TRN-02127 | 036909C-JVD-TRN-02127 | IFR | 2019-07-25 | 2019-07-30 | R2-Comments as noted | TPSK-LSPA1-T-PL-02127 |  | 2019-07-15 | 2
036909C-1000-JSS-1530-0001 | Job Supply Specification For Intercom Paging And Audible Alarm System | 1 | 2019-06-27 | IFF | OL1-2T01-0001 | EE | 2019-06-28 | 036909C-JVD-TRN-02025 | 036909C-JVD-TRN-02025 | IFR | 2019-07-12 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-EE-02025 |  | 2019-07-01 | 1
036909C-1022-PDS-1390-2211 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2200 4th Stage Suction - 10-SP-22011 | A | 2019-06-21 | IFR | OL1-2P03-2211 | MP | 2019-06-25 | 036909C-JVD-TRN-01984 | 036909C-JVD-TRN-01984 | IFR | 2019-07-09 | 2019-07-31 | R1-No comments | TPSK-LSPA1-T-MP-01984 |  | 2019-06-26 | 2
036909C-1022-PDS-1390-2208 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2200 4th Stage Discharge - 10-SP-22008 | A | 2019-06-21 | IFR | OL1-2P03-2208 | MP | 2019-06-25 | 036909C-JVD-TRN-01984 | 036909C-JVD-TRN-01984 | IFR | 2019-07-09 | 2019-07-31 | R2-Comments as noted | TPSK-LSPA1-T-MP-01984 |  | 2019-06-26 | 2
036909C-1010-SP-1513-1001 | Complex Loop Narratives Area 10 Feed Preparation and Feed Preheat | B | 2019-06-26 | IBD | OL1-2I71-1001 | IE | 2019-06-26 | 036909C-JVD-TRN-02001 | 036909C-JVD-TRN-02001 | IFR | 2019-07-11 | 2019-07-31 | R2-Comments as noted | TPSK-LSPA1-T-IE-02001 |  | 2019-06-27 | 2
036909C-1011-SP-1546-1162 | Instrument Datasheets for Flow Element Venturi | B | 2019-06-24 | IFQ | OL1-2I20-1162 | IE | 2019-06-26 | 036909C-JVD-TRN-02006 | 036909C-JVD-TRN-02006 | IFR | 2019-07-11 | 2019-07-31 | R2-Comments as noted | TPSK-LSPA1-T-IE-02006 |  | 2019-06-27 | 2
036909C-1030-SP-1546-3002 | Instrument Datasheets for Flow Element (Orifice) Area 30 | A | 2019-07-05 | IFQ | OL1-2I20-3022 | IE | 2019-07-08 | 036909C-JVD-TRN-02097 | 036909C-JVD-TRN-02097 | IFI |  | 2019-07-31 | R2-Comments as noted | TPSK-LSPA1-T-IE-2097 |  | 2019-07-09 | 3
036909C-1030-SP-1547-3009 | Instrument Datasheets for Flow Element (Integral Orifice). Area 30 | A | 2019-07-05 | IFQ | OL1-2I20-3032 | IE | 2019-07-08 | 036909C-JVD-TRN-02097 | 036909C-JVD-TRN-02097 | IFI |  | 2019-07-31 | R2-Comments as noted | TPSK-LSPA1-T-IE-2097 |  | 2019-07-09 | 3
036909C-1031-SP-1547-3102 | Instrument Datasheets for Flow Element (Rotameter) Area 31 | A | 2019-07-03 | IFQ | OL1-2I20-3128 | IE | 2019-07-08 | 036909C-JVD-TRN-02097 | 036909C-JVD-TRN-02097 | IFI |  | 2019-07-31 | R2-Comments as noted | TPSK-LSPA1-T-IE-2097 |  | 2019-07-09 | 3
036909C-1039-SP-1542-3903 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 39 | A | 2019-07-05 | IFQ | OL1-2I20-3906 | IE | 2019-07-08 | 036909C-JVD-TRN-02097 | 036909C-JVD-TRN-02097 | IFI |  | 2019-07-31 | R2-Comments as noted | TPSK-LSPA1-T-IE-2097 |  | 2019-07-09 | 3
036909C-1011-SP-1552-1164 | Instrument Datasheets for Guided Wave Radar Level Transmitter & Magnetic Level Gauge | B | 2019-06-17 | IFQ | OL1-2I20-1164 | IE | 2019-06-20 | 036909C-JVD-TRN-01948 | 036909C-JVD-TRN-01948 | IFR | 2019-07-05 | 2019-07-31 | R2-Comments as noted | TPSK-LSPA1-T-IE-01948 |  | 2019-06-21 | 2
036909C-1011-SP-1554-1161 | Instrument Datasheets for Temperature Elements for Furnace Profile | B | 2019-06-18 | IFQ | OL1-2I20-1161 | IE | 2019-06-24 | 036909C-JVD-TRN-01975 | 036909C-JVD-TRN-01975 | IFR | 2019-07-09 | 2019-07-31 | R2-Comments as noted | TPSK-LSPA1-T-IE-01975 |  | 2019-06-25 | 2
036909C-1011-SP-1565-1151 | Instrument Datasheets for O2 & Combustible Analyzer | B | 2019-06-19 | IFQ | OL1-2I20-1151 | IE | 2019-06-24 | 036909C-JVD-TRN-01976 | 036909C-JVD-TRN-01976 | IFR | 2019-07-09 | 2019-07-31 | R2-Comments as noted | TPSK-LSPA1-T-IE-01976 |  | 2019-06-25 | 2
036909C-1000-MR-1515-0004 | Material Requisition for Machine Monitoring System - MMS | A | 2019-07-12 | IFQ | OL1-2C17-330101 | PL | 2019-07-12 | 036909C-JVD-TRN-02149 | 036909C-JVD-TRN-02149 | IFA | 2019-07-29 | 2019-07-30 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-PL-02149 |  | 2019-07-15 | 1
036909C-1012-SP-1546-0002 | Instrument Data Sheets For Flow Element Pitot Furmace Area 10-H-1200 | A | 2019-06-19 | IFI | OL1-2I20-1225 | IE | 2019-06-21 | 036909C-JVD-TRN-01965 | 036909C-JVD-TRN-01965 | IFA | 2019-07-08 | 2019-07-23 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-01965 |  | 2019-06-24 | 1
036909C-1011-SP-1546-0002 | Instrument Data Sheets Flow Element Pitot Furmace Area 10-H-1100 | A | 2019-06-19 | IFI | OL1-2I20-1125 | IE | 2019-06-21 | 036909C-JVD-TRN-01965 | 036909C-JVD-TRN-01965 | IFA | 2019-07-08 | 2019-07-23 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-01965 |  | 2019-06-24 | 1
036909C-102C-DW-1612-0001 | Earthing Layout - Zone 2C - Key Plan | A | 2019-06-18 | IFR | OL1-2E52-0014 | EE | 2019-07-16 | 036909C-JVD-TRN-02156 | 036909C-JVD-TRN-02156 | IFA | 2019-07-31 | 2019-07-23 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02156 |  | 2019-07-17 | 1
036909C-103A-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 3A Butadiene Extraction Unit | B | 2019-07-01 | IBD | OL1-2F75-0014 | FF | 2019-07-02 | 036909C-JVD-TRN-02048 | 036909C-JVD-TRN-02048 | IFR | 2019-07-16 | 2019-07-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-02048 |  | 2019-07-03 | 2
036909C-102E-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 2E Cracked Gas Compressor | B | 2019-07-01 | IBD | OL1-2F75-0013 | FF | 2019-07-02 | 036909C-JVD-TRN-02048 | 036909C-JVD-TRN-02048 | IFR | 2019-07-16 | 2019-07-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-02048 |  | 2019-07-03 | 2
036909C-102D-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 2D Process Cold Compressor | B | 2019-07-01 | IBD | OL1-2F75-0012 | FF | 2019-07-02 | 036909C-JVD-TRN-02048 | 036909C-JVD-TRN-02048 | IFR | 2019-07-16 | 2019-07-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-02048 |  | 2019-07-03 | 2
036909C-102B-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 2B C3 Hydrogenation | B | 2019-07-01 | IBD | OL1-2F75-0011 | FF | 2019-07-02 | 036909C-JVD-TRN-02048 | 036909C-JVD-TRN-02048 | IFR | 2019-07-16 | 2019-07-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-02048 |  | 2019-07-03 | 2
036909C-102A-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 2A Quench | B | 2019-07-01 | IBD | OL1-2F75-0010 | FF | 2019-07-02 | 036909C-JVD-TRN-02048 | 036909C-JVD-TRN-02048 | IFR | 2019-07-16 | 2019-07-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-02048 |  | 2019-07-03 | 2
036909C-101B-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 1B Furnaces Utilities | B | 2019-07-01 | IBD | OL1-2F75-0009 | FF | 2019-07-02 | 036909C-JVD-TRN-02048 | 036909C-JVD-TRN-02048 | IFR | 2019-07-16 | 2019-07-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-02048 |  | 2019-07-03 | 2
036909C-105U-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 5U Utilities | B | 2019-07-01 | IBD | OL1-2F75-0005 | FF | 2019-07-02 | 036909C-JVD-TRN-02048 | 036909C-JVD-TRN-02048 | IFR | 2019-07-16 | 2019-07-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-02048 |  | 2019-07-03 | 2
036909C-105T-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 5T Cooling Water Unit | B | 2019-07-01 | IBD | OL1-2F75-0003 | FF | 2019-07-02 | 036909C-JVD-TRN-02048 | 036909C-JVD-TRN-02048 | IFR | 2019-07-16 | 2019-07-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-02048 |  | 2019-07-03 | 2
036909C-1026-DW-1514-2601 | Cause and Effect Diagram - Area 26 - Hot Fractionation | A | 2019-04-22 | IFR | OL1-2G50-2601 | PE | 2019-04-22 | 036909C-JVD-TRN-01429 | 036909C-JVD-TRN-01429, ROC-TPSK-CECO-T-00053 | IFR | 2019-05-07 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-01429 |  | 2019-04-23 | 2
036909C-1026-SP-1513-2602 | Instrument Interlock Description Area 26 - Hot Fractionation | A | 2019-05-17 | IFR | OL1-2G50-2602 | PE | 2019-05-20 | 036909C-JVD-TRN-01691 | 036909C-JVD-TRN-01691 | IFR | 2019-06-04 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01691 |  | 2019-05-21 | 2
036909C-1012-PDS-1390-1201 | Piping Specialty Item Datasheet - Trapped Key Locking Devices - 10-SP-12001-16001 | A | 2019-05-15 | IFR | OL1-2P03-1201 | MP | 2019-05-16 | 036909C-JVD-TRN-01683 | 036909C-JVD-TRN-01683 | IFR | 2019-05-31 | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-MP-01683 |  | 2019-05-17 | 2
036909C-1011-PDS-1390-1101 | Piping Specialty Item Datasheet - Trapped Key Locking Devices - 10-SP-11001 | A | 2019-05-15 | IFR | OL1-2P03-1101 | MP | 2019-05-16 | 036909C-JVD-TRN-01683 | 036909C-JVD-TRN-01683 | IFR | 2019-05-31 | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-MP-01683 |  | 2019-05-17 | 2
036909C-1012-PDS-1390-1252 | Piping Specialty Item Datasheet - Flexible Hose - 10-FLX-12001-16001 | A | 2019-05-14 | IFR | OL1-2P03-1252 | MP | 2019-05-16 | 036909C-JVD-TRN-01683 | 036909C-JVD-TRN-01683 | IFR | 2019-05-31 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-MP-01683 |  | 2019-05-17 | 2
036909C-1012-PDS-1390-1211 | Piping Specialty Item Datasheet - Stop Check Valve - 10-SP-12011-16011 | A | 2019-05-06 | IFR | OL1-2P03-1211 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1011-PDS-1390-1152 | Piping Specialty Item Datasheet - Flexible Hose - 10-FLX-11001 | A | 2019-05-14 | IFR | OL1-2P03-1152 | MP | 2019-05-16 | 036909C-JVD-TRN-01683 | 036909C-JVD-TRN-01683 | IFR | 2019-05-31 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-MP-01683 |  | 2019-05-17 | 2
036909C-1011-PDS-1390-1113 | Piping Specialty Item Datasheet - Vent Silencer - PSV-1144 Outlet - 10-SP-11013 | A | 2019-05-08 | IFR | OL1-2P03-1113 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1011-PDS-1390-1111 | Piping Specialty Item Datasheet - Stop Check Valve - 10-SP-11011 | A | 2019-05-06 | IFR | OL1-2P03-1111 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1024-SP-1513-2401 | Complex Loop Narratives Area 24 - Dehydration -Regen - Deprop - C2 Hydrog | A | 2019-05-07 | IFR | OL1-2I71-2401 | IE | 2019-05-07 | 036909C-JVD-TRN-01605 | 036909C-JVD-TRN-01605 | IFR | 2019-05-22 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-IE-01605 |  | 2019-05-08 | 2
036909C-1023-SP-1513-2301 | Complex Loop Narratives - Area 23 - Caustic and Spent Caustic Treatment | A | 2019-04-15 | IFR | OL1-2I71-2301 | IE | 2019-04-15 | 036909C-JVD-TRN-01358 | 036909C-JVD-TRN-01358 | IFR | 2019-04-30 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-IE-01358 |  | 2019-04-16 | 2
036909C-1022-SP-1513-2201 | Complex Loop Narratives - Area 22 - Cracked Gas Compressor | A | 2019-05-01 | IFR | OL1-2I71-2201 | IE | 2019-05-01 | 036909C-JVD-TRN-01544 | 036909C-JVD-TRN-01544 | IFR | 2019-05-16 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-IE-01544 |  | 2019-05-02 | 2
036909C-1024-SP-1513-2402 | Instrument Interlock Descriptions - Area 24 - Dehydration - Regen - Deprop- C2 Hydrog | A | 2019-04-04 | IFR | OL1-2G50-2402 | PE | 2019-04-05 | 036909C-JVD-TRN-01266 | 036909C-JVD-TRN-01266 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01266 |  | 2019-04-08 | 2
036909C-1023-SP-1513-2302 | Instrument Interlock Descriptions - Area 23 - Caustic and Spent Caustic Treatment | A | 2019-03-27 | IFR | OL1-2G50-2302 | PE | 2019-03-28 | 036909C-JVD-TRN-01185 | 036909C-JVD-TRN-01185 | IFR | 2019-04-12 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01185 |  | 2019-03-29 | 2
036909C-1022-SP-1513-2202 | Instrument Interlock Descriptions - Area 22 - Cracked Gas Compressor | A | 2019-03-29 | IFR | OL1-2G50-2202 | PE | 2019-03-29 | 036909C-JVD-TRN-01203 | 036909C-JVD-TRN-01203 | IFR | 2019-04-15 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01203 |  | 2019-04-01 | 2
036909C-1024-DW-1514-2401 | Cause and Effect Diagram - Area 24 - Dehydration - Regen - Deprop- C2 Hydrog | A | 2019-04-04 | IFR | OL1-2G50-2401 | PE | 2019-04-05 | 036909C-JVD-TRN-01267 | 036909C-JVD-TRN-01267, ROC-TPSK-CECO-T-00042 | IFR | 2019-04-22 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01267 |  | 2019-04-08 | 2
036909C-1023-DW-1514-2301 | Cause and Effect Diagram - Area 23 - Caustic and Spent Caustic Treatment | A | 2019-03-26 | IFR | OL1-2G50-2301 | PE | 2019-03-28 | 036909C-JVD-TRN-01183 | 036909C-JVD-TRN-01183, ROC-TPSK-CECO-T-00032 | IFR | 2019-04-12 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01183 |  | 2019-03-29 | 2
036909C-1000-JSD-1501-0002 | General Design Rules For SmartPlant Instrumentation Setup | 0 | 2019-03-15 | IMP | OL1-2R06-0024 | IE | 2019-03-19 | 036909C-JVD-TRN-01094 | 036909C-JVD-TRN-01094 | IFR | 2019-04-03 | 2019-04-05 | R1-No comments | TPSK-LSPA1-T-IE-01094 |  | 2019-03-20 | 2
036909C-1053-PDS-2600-5397 | Process Equipment Datasheet - 10-PK-5397 - Non-oxidizing Biocide Inj Pkg | B | 2019-02-08 | IFD | OL1-2G30-5397 | PE | 2019-02-19 | 036909C-JVD-TRN-00877 | 036909C-JVD-TRN-00877 | IFR | 2019-03-05 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00877 |  | 2019-02-19 | 2
036909C-1029-PDS-2600-2900 | Process Equipment Datasheet - 10-PK-2900 - pH Ctrl - Corrosion Inhibitor Inj Pkg | C | 2019-03-19 | IFD | OL1-2G30-2900 | PE | 2019-03-20 | 036909C-JVD-TRN-01103 | 036909C-JVD-TRN-01103, ROC-TPSK-CECO-T-00019 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01103 |  | 2019-03-21 | 2
036909C-102E-DW-1741-0001-003 | Foundations Pipe Rack 10-PRK-2E01 - Formworks And Reinforcements | A | 2019-07-25 | IFR | OL1-2K31-1242 | CV | 2019-07-29 | 036909C-JVD-TRN-02274 | 036909C-JVD-TRN-02274 | IFA | 2019-08-13 |  | Transmitted | TPSK-LSPA1-T-CV-02274 |  | 2019-07-30 | 1
036909C-102E-CN-1731-0001 | Calculation Note For Foundations Of Pipe Rack 10-PRK-2E01 | A | 2019-07-25 | IFR | OL1-2K14-0011 | CV | 2019-07-29 | 036909C-JVD-TRN-02273 | 036909C-JVD-TRN-02273 | IFA | 2019-08-13 |  | Transmitted | TPSK-LSPA1-T-CV-02273 |  | 2019-07-30 | 1
036909C-102E-DW-1741-0001-002 | Foundations Pipe Rack 10-PRK-2E01 - Formworks And Reinforcements | A | 2019-07-25 | IFR | OL1-2K31-1241 | CV | 2019-07-29 | 036909C-JVD-TRN-02274 | 036909C-JVD-TRN-02274 | IFA | 2019-08-13 |  | Transmitted | TPSK-LSPA1-T-CV-02274 |  | 2019-07-30 | 1
036909C-102E-DW-1741-0001-001 | Foundations Pipe Rack 10-PRK-2E01 - Formworks And Reinforcements | A | 2019-07-25 | IFR | OL1-2K31-1240 | CV | 2019-07-29 | 036909C-JVD-TRN-02274 | 036909C-JVD-TRN-02274 | IFA | 2019-08-13 |  | Transmitted | TPSK-LSPA1-T-CV-02274 |  | 2019-07-30 | 1
036909C-102E-DW-1741-0001-004 | Foundations Pipe Rack 10-PRK-2E01 - Formworks And Reinforcements | A | 2019-07-25 | IFR | OL1-2K31-1243 | CV | 2019-07-29 | 036909C-JVD-TRN-02274 | 036909C-JVD-TRN-02274 | IFA | 2019-08-13 |  | Transmitted | TPSK-LSPA1-T-CV-02274 |  | 2019-07-30 | 1
036909C-102C-DW-1744-0001-001 | Concrete Basin 10-PIT-2790 - Formwork | A | 2019-07-22 | IFR | OL1-2K31-2700 | CV | 2019-07-29 | 036909C-JVD-TRN-02274 | 036909C-JVD-TRN-02274 | IFA | 2019-08-13 |  | Transmitted | TPSK-LSPA1-T-CV-02274 |  | 2019-07-30 | 1
036909C-102C-DW-1744-0002-002 | Concrete Basin 10-PIT-5600 - Reinforcement | A | 2019-07-19 | IFR | OL1-2K31-2721 | CV | 2019-07-29 | 036909C-JVD-TRN-02274 | 036909C-JVD-TRN-02274 | IFA | 2019-08-13 |  | Transmitted | TPSK-LSPA1-T-CV-02274 |  | 2019-07-30 | 1
036909C-102C-DW-1744-0002-001 | Concrete Basin 10-PIT-5600 - Formwork | A | 2019-07-19 | IFR | OL1-2K31-2720 | CV | 2019-07-29 | 036909C-JVD-TRN-02274 | 036909C-JVD-TRN-02274 | IFA | 2019-08-13 |  | Transmitted | TPSK-LSPA1-T-CV-02274 |  | 2019-07-30 | 1
036909C-102C-DW-1744-0001-002 | Concrete Basin 10-PIT-2790 - Reinforcement | A | 2019-07-19 | IFR | OL1-2K31-2701 | CV | 2019-07-29 | 036909C-JVD-TRN-02274 | 036909C-JVD-TRN-02274 | IFA | 2019-08-13 |  | Transmitted | TPSK-LSPA1-T-CV-02274 |  | 2019-07-30 | 1
036909C-100P-CN-1731-0005 | Calculation Note For Foundations For Pipe Rack 10-PRK-0P03 | A | 2019-07-19 | IFR | OL1-2K14-0020 | CV | 2019-07-29 | 036909C-JVD-TRN-02273 | 036909C-JVD-TRN-02273 | IFA | 2019-08-13 |  | Transmitted | TPSK-LSPA1-T-CV-02273 |  | 2019-07-30 | 1
036909C-100P-CN-1831-0003 | Calculation Note For Steel Pipe Rack 10-PRK-0P03 | A | 2019-07-19 | IFR | OL1-2K15-0045 | CV | 2019-07-29 | 036909C-JVD-TRN-02273 | 036909C-JVD-TRN-02273 | IFA | 2019-08-13 |  | Transmitted | TPSK-LSPA1-T-CV-02273 |  | 2019-07-30 | 1
036909C-100P-CN-1731-0006 | Calculation Note For Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 | A | 2019-07-19 | IFR | OL1-2K14-0066 | CV | 2019-07-29 | 036909C-JVD-TRN-02273 | 036909C-JVD-TRN-02273 | IFA | 2019-08-13 |  | Transmitted | TPSK-LSPA1-T-CV-02273 |  | 2019-07-30 | 1
036909C-1000-NM-1601-0001 | Electrical Consumer List | A | 2019-03-22 | IFR | OL1-2E15-0001 | EE | 2019-04-01 | 036909C-JVD-TRN-01213 | 036909C-JVD-TRN-01213, ROC-TPSK-CECO-T-00037 | IFA | 2019-04-16 | 2019-05-07 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01213 |  | 2019-04-02 | 1
036909C-100P-DW-1741-0006-011 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Beams | A | 2019-07-19 | IFR | OL1-2K31-1110 | CV | 2019-07-25 | 036909C-JVD-TRN-02263 | 036909C-JVD-TRN-02263 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02263 |  | 2019-07-29 | 1
036909C-100P-DW-1841-0003-002 | Steel For Pipe Rack 10-PRK-0P03 - Plans | A | 2019-07-19 | IFR | OL1-2K32-7201 | CV | 2019-07-25 | 036909C-JVD-TRN-02264 | 036909C-JVD-TRN-02264 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02264 |  | 2019-07-29 | 1
036909C-100P-DW-1841-0003-001 | Steel For Pipe Rack 10-PRK-0P03 - 3D View | A | 2019-07-19 | IFR | OL1-2K32-7200 | CV | 2019-07-25 | 036909C-JVD-TRN-02264 | 036909C-JVD-TRN-02264 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02264 |  | 2019-07-29 | 1
036909C-100P-DW-1741-0006-013 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Bracings | A | 2019-07-19 | IFR | OL1-2K31-1112 | CV | 2019-07-25 | 036909C-JVD-TRN-02263 | 036909C-JVD-TRN-02263 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02263 |  | 2019-07-29 | 1
036909C-100P-DW-1841-0003-006 | Steel For Pipe Rack 10-PRK-0P03 - Elevations | A | 2019-07-19 | IFR | OL1-2K32-7205 | CV | 2019-07-25 | 036909C-JVD-TRN-02264 | 036909C-JVD-TRN-02264 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02264 |  | 2019-07-29 | 1
036909C-100P-DW-1841-0003-003 | Steel For Pipe Rack 10-PRK-0P03 - Plans | A | 2019-07-19 | IFR | OL1-2K32-7202 | CV | 2019-07-25 | 036909C-JVD-TRN-02264 | 036909C-JVD-TRN-02264 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02264 |  | 2019-07-29 | 1
036909C-100P-DW-1741-0006-012 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Beams | A | 2019-07-19 | IFR | OL1-2K31-1111 | CV | 2019-07-25 | 036909C-JVD-TRN-02263 | 036909C-JVD-TRN-02263 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02263 |  | 2019-07-29 | 1
036909C-100P-DW-1841-0003-005 | Steel For Pipe Rack 10-PRK-0P03 - Elevations | A | 2019-07-19 | IFR | OL1-2K32-7204 | CV | 2019-07-25 | 036909C-JVD-TRN-02264 | 036909C-JVD-TRN-02264 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02264 |  | 2019-07-29 | 1
036909C-100P-DW-1841-0003-008 | Steel For Pipe Rack 10-PRK-0P03 - Elevations - Stair | A | 2019-07-19 | IFR | OL1-2K32-7207 | CV | 2019-07-25 | 036909C-JVD-TRN-02264 | 036909C-JVD-TRN-02264 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02264 |  | 2019-07-29 | 1
036909C-100P-DW-1841-0003-009 | Steel For Pipe Rack 10-PRK-0P03 - Details | A | 2019-07-19 | IFR | OL1-2K32-7208 | CV | 2019-07-25 | 036909C-JVD-TRN-02264 | 036909C-JVD-TRN-02264 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02264 |  | 2019-07-29 | 1
036909C-100P-DW-1741-0006-010 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Beams | A | 2019-07-19 | IFR | OL1-2K31-1109 | CV | 2019-07-25 | 036909C-JVD-TRN-02263 | 036909C-JVD-TRN-02263 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02263 |  | 2019-07-29 | 1
036909C-100P-DW-1841-0003-007 | Steel For Pipe Rack 10-PRK-0P03 - Elevations | A | 2019-07-19 | IFR | OL1-2K32-7206 | CV | 2019-07-25 | 036909C-JVD-TRN-02264 | 036909C-JVD-TRN-02264 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02264 |  | 2019-07-29 | 1
036909C-100P-DW-1741-0006-009 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Columns | A | 2019-07-19 | IFR | OL1-2K31-1108 | CV | 2019-07-25 | 036909C-JVD-TRN-02263 | 036909C-JVD-TRN-02263 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02263 |  | 2019-07-29 | 1
036909C-100P-DW-1841-0003-004 | Steel For Pipe Rack 10-PRK-0P03 - Elevations - Plans | A | 2019-07-19 | IFR | OL1-2K32-7203 | CV | 2019-07-25 | 036909C-JVD-TRN-02264 | 036909C-JVD-TRN-02264 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02264 |  | 2019-07-29 | 1
036909C-100P-DW-1741-0005-002 | Foundation And Elevation Of Pipe Rack 10-PRK-0P03 - Formwork And Reinforcement | A | 2019-07-19 | IFR | OL1-2K31-1081 | CV | 2019-07-25 | 036909C-JVD-TRN-02263 | 036909C-JVD-TRN-02263 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02263 |  | 2019-07-29 | 1
036909C-100P-DW-1741-0006-004 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Elevations | A | 2019-07-19 | IFR | OL1-2K31-1103 | CV | 2019-07-25 | 036909C-JVD-TRN-02263 | 036909C-JVD-TRN-02263 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02263 |  | 2019-07-29 | 1
036909C-100P-DW-1741-0006-007 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Columns | A | 2019-07-19 | IFR | OL1-2K31-1106 | CV | 2019-07-25 | 036909C-JVD-TRN-02263 | 036909C-JVD-TRN-02263 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02263 |  | 2019-07-29 | 1
036909C-100P-DW-1741-0006-003 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Plans | A | 2019-07-19 | IFR | OL1-2K31-1102 | CV | 2019-07-25 | 036909C-JVD-TRN-02263 | 036909C-JVD-TRN-02263 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02263 |  | 2019-07-29 | 1
036909C-100P-DW-1741-0006-001 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - 3D View | A | 2019-07-19 | IFR | OL1-2K31-1100 | CV | 2019-07-25 | 036909C-JVD-TRN-02263 | 036909C-JVD-TRN-02263 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02263 |  | 2019-07-29 | 1
036909C-1000-DW-1431-0001-002 | Bored Piles For Preliminary Test | 0 | 2019-07-24 | IFC | OL1-2K31-0343 | CV | 2019-07-25 | 036909C-JVD-TRN-02265 | 036909C-JVD-TRN-02265 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02265 |  | 2019-07-29 | 1
036909C-100P-DW-1741-0005-001 | Foundation And Elevation Of Pipe Rack 10-PRK-0P03 - Formwork And Reinforcement | A | 2019-07-19 | IFR | OL1-2K31-1080 | CV | 2019-07-25 | 036909C-JVD-TRN-02263 | 036909C-JVD-TRN-02263 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02263 |  | 2019-07-29 | 1
036909C-100P-DW-1741-0006-006 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Columns | A | 2019-07-19 | IFR | OL1-2K31-1105 | CV | 2019-07-25 | 036909C-JVD-TRN-02263 | 036909C-JVD-TRN-02263 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02263 |  | 2019-07-29 | 1
036909C-100P-DW-1741-0006-008 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Columns | A | 2019-07-19 | IFR | OL1-2K31-1107 | CV | 2019-07-25 | 036909C-JVD-TRN-02263 | 036909C-JVD-TRN-02263 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02263 |  | 2019-07-29 | 1
036909C-100P-DW-1741-0006-005 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Elevations | A | 2019-07-19 | IFR | OL1-2K31-1104 | CV | 2019-07-25 | 036909C-JVD-TRN-02263 | 036909C-JVD-TRN-02263 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02263 |  | 2019-07-29 | 1
036909C-100P-DW-1741-0006-002 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Plans | A | 2019-07-19 | IFR | OL1-2K31-1101 | CV | 2019-07-25 | 036909C-JVD-TRN-02263 | 036909C-JVD-TRN-02263 | IFA | 2019-08-09 |  | Transmitted | TPSK-LSPA1-T-CV-02263 |  | 2019-07-29 | 1
036909C-1000-MR-0811-0003 | Material Requisition For Shop Assembled CS Cladded And SS Vessels | A | 2019-03-26 | IFQ | OL1-2C13-133000 | PL | 2019-03-26 | 036909C-JVD-TRN-01156 | 036909C-JVD-TRN-01156 | IFR | 2019-04-10 | 2019-06-06 | R1-No comments | TPSK-LSPA1-T-PL-01156 |  | 2019-03-27 | 2
036909C-1000-DW-1431-0001-002 | Bored Piles For Preliminary Test | A | 2019-05-24 | IFR | OL1-2K31-0343 | CV | 2019-05-30 | 036909C-JVD-TRN-01769 | 036909C-JVD-TRN-01769 | IFA | 2019-06-14 | 2019-07-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01769 |  | 2019-05-31 | 1
036909C-1031-PDS-0500-3110 | Process Equipment Datasheet - 10-T-3110 - Water Washer | B | 2019-05-20 | IFD | OL1-2G30-3110 | PE | 2019-05-21 | 036909C-JVD-TRN-01711 | 036909C-JVD-TRN-01711 | IFR | 2019-06-05 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01711 |  | 2019-05-23 | 2
036909C-1030-PDS-0500-3090 | Process Equipment Datasheet - 10-T-3090 - Butadiene Drying Tower | B | 2019-05-17 | IFD | OL1-2G30-3090 | PE | 2019-05-21 | 036909C-JVD-TRN-01708 | 036909C-JVD-TRN-01708 | IFR | 2019-06-05 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01708 |  | 2019-05-23 | 2
036909C-1030-PDS-0500-3080 | Process Equipment Datasheet - 10-T-3080 - Butadiene Tower | B | 2019-05-16 | IFD | OL1-2G30-3080 | PE | 2019-05-16 | 036909C-JVD-TRN-01684 | 036909C-JVD-TRN-01684 | IFR | 2019-05-31 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01684 |  | 2019-05-21 | 2
036909C-1030-PDS-0500-3070 | Process Equipment Datasheet - 10-T-3070 - Direct Cooler Tower | B | 2019-05-16 | IFD | OL1-2G30-3070 | PE | 2019-05-16 | 036909C-JVD-TRN-01684 | 036909C-JVD-TRN-01684 | IFR | 2019-05-31 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01684 |  | 2019-05-21 | 2
036909C-1030-PDS-0500-3060 | Process Equipment Datasheet - 10-T-3060 - C4 Acetylene Washer | B | 2019-05-17 | IFD | OL1-2G30-3060 | PE | 2019-05-21 | 036909C-JVD-TRN-01708 | 036909C-JVD-TRN-01708 | IFR | 2019-06-05 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01708 |  | 2019-05-23 | 2
036909C-1030-PDS-0500-3050 | Process Equipment Datasheet - 10-T-3050 - Degasser | B | 2019-05-16 | IFD | OL1-2G30-3050 | PE | 2019-05-16 | 036909C-JVD-TRN-01684 | 036909C-JVD-TRN-01684 | IFR | 2019-05-31 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01684 |  | 2019-05-21 | 2
036909C-1030-PDS-0500-3040 | Process Equipment Datasheet - 10-T-3040 - Rectifier | B | 2019-05-17 | IFD | OL1-2G30-3040 | PE | 2019-05-21 | 036909C-JVD-TRN-01708 | 036909C-JVD-TRN-01708 | IFR | 2019-06-05 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01708 |  | 2019-05-23 | 2
036909C-1030-PDS-0500-3030 | Process Equipment Datasheet - 10-T-3030 - After Washer | B | 2019-05-16 | IFD | OL1-2G30-3030 | PE | 2019-05-16 | 036909C-JVD-TRN-01684 | 036909C-JVD-TRN-01684 | IFR | 2019-05-31 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01684 |  | 2019-05-21 | 2
036909C-1030-PDS-0500-3020 | Process Equipment Datasheet - 10-T-3020 - Main Washer | B | 2019-05-17 | IFD | OL1-2G30-3020 | PE | 2019-05-21 | 036909C-JVD-TRN-01708 | 036909C-JVD-TRN-01708 | IFR | 2019-06-05 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01708 |  | 2019-05-23 | 2
036909C-1030-PDS-0500-3010 | Process Equipment Datasheet - 10-T-3010 - C4 Vaporization Tower | B | 2019-05-16 | IFD | OL1-2G30-3010 | PE | 2019-05-16 | 036909C-JVD-TRN-01684 | 036909C-JVD-TRN-01684 | IFR | 2019-05-31 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01684 |  | 2019-05-21 | 2
036909C-1030-PDS-0500-3000 | Process Equipment Datasheet - 10-T-3000 - Predistillation Tower | B | 2019-05-17 | IFD | OL1-2G30-3000 | PE | 2019-05-21 | 036909C-JVD-TRN-01708 | 036909C-JVD-TRN-01708 | IFR | 2019-06-05 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-01708 |  | 2019-05-23 | 2
036909C-1026-TDS-0610-2631 | Mechanical Equipment Data Sheet - 10-E-2630 - Secondary Deeth Condenser | B | 2019-04-02 | IFQ | OL1-2M03-2631 | ME | 2019-04-03 | 036909C-JVD-TRN-01243 | 036909C-JVD-TRN-01243 | IFR | 2019-04-18 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME-01243 |  | 2019-04-04 | 2
036909C-102A-DW-1552-0001 | Level Instrument Design and Nozzle Study for Quench ISBL -2A | B | 2019-07-05 | IFR | OL1-2I31-0203 | IE | 2019-07-10 | 036909C-JVD-TRN-02120 | 036909C-JVD-TRN-02120 | IFA | 2019-07-25 | 2019-07-22 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-IE-02120 |  | 2019-07-11 | 1
036909C-1000-MR-1547-0006 | MR For Mass Flow Meters Coriolis Effect | A | 2019-05-28 | IFQ | OL1-2C17-010601 | PL | 2019-07-02 | 036909C-JVD-TRN-02049 | 036909C-JVD-TRN-02049 | IFR | 2019-07-17 | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-PL-02049 |  | 2019-07-03 | 2
036909C-1000-MR-1543-0002 | MR For Electric Operated Valves | A | 2019-06-24 | IFQ | OL1-2C17-060301 | PL | 2019-06-28 | 036909C-JVD-TRN-02026 | 036909C-JVD-TRN-02026 | IFR | 2019-07-15 | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-PL-02026 |  | 2019-07-01 | 2
036909C-1000-MR-1541-0003 | Material Requisition For Special Control Valves | B | 2019-06-25 | IFQ | OL1-2C17-050401 | PL | 2019-06-28 | 036909C-JVD-TRN-02022 | 036909C-JVD-TRN-02022 | IFR | 2019-07-15 | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-PL-02022 |  | 2019-07-01 | 2
036909C-1000-MR-1546-0002 | MR for Pitot Tube | A | 2019-06-26 | IFQ | OL1-2C17-010201 | PL | 2019-07-01 | 036909C-JVD-TRN-02035 | 036909C-JVD-TRN-02035 | IFR | 2019-07-16 | 2019-07-17 | R1-No comments | TPSK-LSPA1-T-PL-02035 |  | 2019-07-02 | 2
036909C-1027-PDS-0800-2706 | Process Equipment Datasheet - 10-D-2706 - GHU-1 Cold Separator | B | 2019-03-28 | IFD | OL1-2G30-2706 | PE | 2019-03-28 | 036909C-JVD-TRN-01188 | 036909C-JVD-TRN-01188 | IFR | 2019-04-12 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01188 |  | 2019-03-29 | 2
036909C-1000-PP-811 | Preparation Of Construction Quality Control Dossier | A | 2019-06-20 | IFR | OL1-2Q92-0007 | QM | 2019-06-24 | 036909C-JVD-TRN-01970 | 036909C-JVD-TRN-01970 | IFR | 2019-07-09 | 2019-07-22 | R1-No comments | TPSK-LSPA1-T-QM-01970 |  | 2019-06-25 | 2
036909C-100P-NM-1350-0030 | Loads On Rack 10-PRK-0P01 | B | 2019-07-01 | IDD | OL1-2P05-0041 | MP | 2019-07-09 | 036909C-JVD-TRN-02108 | 036909C-JVD-TRN-02108 | IFR | 2019-07-24 | 2019-07-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02108 |  | 2019-07-10 | 2
036909C-1000-JSS-6300-0006 | Job Specification for AXENS Standard Material Specifications - Carbon Steels For Pressure Service | A | 2019-02-21 | IFR | OL1-2R03-0007 | ME | 2019-02-21 | 036909C-JVD-TRN-00909 | 036909C-JVD-TRN-00909 | IFR | 2019-03-08 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00909 |  | 2019-02-22 | 2
036909C-1010-TDS-0610-1005 | Mechanical Equipment Data Sheet - 10-E-1005 - LPG Feed Heater | 0 | 2019-07-17 | Issue for Purchase | OL1-2M03-1005 | ME | 2019-07-22 | 036909C-JVD-TRN-02235 | 036909C-JVD-TRN-02235 | IFR | 2019-08-06 |  | Transmitted | TPSK-LSPA1-T-ME-02235 |  | 2019-07-23 | 2
036909C-1010-TDS-0610-1015 | Mechanical Equipment Data Sheet - 10-E-1015 - LPG Superheater | 0 | 2019-07-17 | Issue for Purchase | OL1-2M03-1015 | ME | 2019-07-22 | 036909C-JVD-TRN-02235 | 036909C-JVD-TRN-02235 | IFR | 2019-08-06 |  | Transmitted | TPSK-LSPA1-T-ME-02235 |  | 2019-07-23 | 2
036909C-1021-TDS-0610-2125 | Mechanical Equipment Data Sheet - 10-E-2125 - Distillate Stripper Reboiler | 0 | 2019-06-25 | Issue for Purchase | OL1-2M03-2125 | ME | 2019-07-22 | 036909C-JVD-TRN-02212 | 036909C-JVD-TRN-02212 | IFR | 2019-08-06 |  | Transmitted | TPSK-LSPA1-T-ME-02212 |  | 2019-07-23 | 2
036909C-1000-JSS-6300-1001 | Job Specification for Axens General Statement about Selection of Materials for Equipment and Piping | A | 2019-04-24 | IFR | OL1-2R03-1005 | ME | 2019-04-26 | 036909C-JVD-TRN-01505 | 036909C-JVD-TRN-01505 | IFR | 2019-05-13 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-01505 |  | 2019-04-29 | 2
036909C-1000-JSS-6300-0007 | Job Specification For Axens Standard Material Specifications - Low Alloyed Steels For Pressure Vessels | A | 2019-02-21 | IFR | OL1-2R03-0008 | ME | 2019-02-21 | 036909C-JVD-TRN-00909 | 036909C-JVD-TRN-00909 | IFR | 2019-03-08 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00909 |  | 2019-02-22 | 2
036909C-1000-MR-0610-0003 | Material Requisition For CS S-T Heat Exchangers - Lot 2 | A | 2019-02-11 | IFQ | OL1-2C13-273000 | PL | 2019-02-15 | 036909C-JVD-TRN-00866 | 036909C-JVD-TRN-00866 | IFR | 2019-03-04 | 2019-06-06 | R1-No comments | TPSK-LSPA1-T-PL-00866 |  | 2019-02-15 | 2
036909C-1012-MR-4061-2009 | Material Requisition for Furnace Elevator | A | 2019-01-16 | IFQ | OL1-2C13-709000 | PL | 2019-01-22 | 036909C-JVD-TRN-00697 | 036909C-JVD-TRN-00697 | IFI |  | 2019-02-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00697 |  | 2019-01-22 | 3
036909C-100P-DW-0053-0001 | Detail Key Plan - Zone 0P - Main Pipe Rack | A | 2019-05-24 | IFR | OL1-2P06-0022 | MP | 2019-05-30 | 036909C-JVD-TRN-01767 | 036909C-JVD-TRN-01767 | IFR | 2019-06-14 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01767 |  | 2019-05-31 | 2
036909C-1025-PDS-1390-2524 | Piping Specialty Item - Datasheet - Cone Filter - E-2525 Hydrogen Inlet - 10-SP-25024 | A | 2019-06-27 | IFR | OL1-2P03-25024 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2540 | Piping Specialty Item - Datasheet - Cone Filter - E-2510 Demeth Prefrac Ovhd Inlet - 10-SP-25040 | A | 2019-06-27 | IFR | OL1-2P03-2540 | MP | 2019-07-01 | 036909C-JVD-TRN-02045 | 036909C-JVD-TRN-02045 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02045 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2535 | Piping Specialty Item - Datasheet - Cone Filter - E-2587 C2R Inlet - 10-SP-25035 | A | 2019-06-27 | IFR | OL1-2P03-2535 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2533 | Piping Specialty Item - Datasheet - Cone Filter - E-2585 C2R Inlet - 10-SP-25033 | A | 2019-06-27 | IFR | OL1-2P03-2533 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2530 | Piping Specialty Item - Datasheet - Cone Filter - E-2500 Hydro gem Inlet - 10-SP-25030 | A | 2019-06-27 | IFR | OL1-2P03-2530 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2529 | Piping Specialty Item - Datasheet - Cone Filter - E-2500 Methane Recycle Inlet - 10-SP-25029 | A | 2019-06-27 | IFR | OL1-2P03-2529 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2528 | Piping Specialty Item - Datasheet Cone Filter - E-2500 Ethane Recycle Inlet - 10-SP-25028 | A | 2019-06-27 | IFR | OL1-2P03-2528 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2527 | Pipng Specialty Item - Datasheet - Cone Filter - E-2500 Residue Gas Inlet - 10-SO-25027 | A | 2019-06-27 | IFR | OL1-2P03-2527 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2525 | Piping Specialty Item - Datasheet - Cone Filter - E-2525 Rectifier Relux Drum Ovhd Inlet - 10-SP-25025 | A | 2019-06-27 | IFR | OL1-2P03-2525 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2520 | Piping Specialty Item - Datasheet - Cone Filter - E-2540 Demeth Ovhd Inlet - 10-SP-25020 | A | 2019-06-27 | IFR | OL1-2P03-2520 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2517 | Piping Specialty Item - Datasheet - Cone Filter - E-2530 Demeth Prefrac Ovhd Inlet - 10-SP-25017 | A | 2019-06-27 | IFR | OL1-2P03-2517 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2516 | Piping Specialty Item - Datasheet - Cone Filter - E-2520 Rectifier Ovhd Inlet - 10-SP-25016 | A | 2019-06-27 | IFR | OL1-2P03-2516 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2515 | Piping Specialty Item - Datasheet - Cone Filter - E-2520 Cracked Gas inlet - 10-SP-25015 | A | 2019-06-27 | IFR | OL1-2P03-2515 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2514 | Piping Specialty Item - Datasheet - Cone Filter - E-2520 Hydrogen Inlet - 10-SP-25014 | A | 2019-06-27 | IFR | OL1-2P03-2514 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2513 | Piping Specialty Item - Datasheet - Cone Filter - E-2520 Residue Gas Inlet - 10-SP-25013 | A | 2019-06-27 | IFR | OL1-2P03-2513 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2507 | Piping Specialty Item - Datasheet - Cone Filter - E-2508 Methane Recycle Inlet - 10-SP-25007 | A | 2019-06-27 | IFR | OL1-2P03-2507 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2506 | Piping Specialty Item - Datasheet - Cone Filter - E-2508 Hydrogen Inlet - 10-SP-25006 | A | 2019-06-27 | IFR | OL1-2P03-2506 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-01 | 2
036909C-1025-PDS-1390-2505 | Piping Specialty Item - Datasheet - Cone Filter - E-2508 Residue Gas Inlet - 10-SP-25005 | A | 2019-06-27 | IFR | OL1-2P03-2505 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2504 | Piping Specialty Item - Datasheet - Cone Filter - E-2508 Cracked Gas Inlet - 10-SP-25004 | A | 2019-06-27 | IFR | OL1-2P03-2504 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1025-PDS-1390-2501 | Piping Specialty Item - Datasheet - Cone Filter - E-2506 Cracked Gas Inlet - 10-SP-25001 | A | 2019-06-27 | IFR | OL1-2P03-2501 | MP | 2019-07-01 | 036909C-JVD-TRN-02046 | 036909C-JVD-TRN-02046 | IFR | 2019-07-16 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-MP-02046 |  | 2019-07-02 | 2
036909C-1024-PDS-1390-2417 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2200 5th Stage Discharge - SCV-24006 | A | 2019-06-21 | IFR | OL1-2P03-2417 | MP | 2019-07-02 | 036909C-JVD-TRN-02059 | 036909C-JVD-TRN-02059 | IFR | 2019-07-17 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-PE-02059 |  | 2019-07-03 | 2
036909C-1024-PDS-1390-2403 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - D-2405 Overhead Cracked Gas - SVC-24012 | A | 2019-06-25 | IFR | OL1-2P03-2403 | MP | 2019-07-02 | 036909C-JVD-TRN-02059 | 036909C-JVD-TRN-02059 | IFR | 2019-07-17 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-PE-02059 |  | 2019-07-03 | 2
036909C-1024-PDS-1390-2460 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - D-2440 Vapor Outlet - SCV-24009 | A | 2019-06-21 | IFR | OL1-2P03-2460 | MP | 2019-07-02 | 036909C-JVD-TRN-02062 | 036909C-JVD-TRN-02062 | IFR | 2019-07-17 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-PE-02062 |  | 2019-07-03 | 2
036909C-1024-PDS-1390-2451 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - D-2405 Overhead Cracked Gas - SCV-24013 | A | 2019-06-25 | IFR | OL1-2P03-2451 | MP | 2019-07-02 | 036909C-JVD-TRN-02062 | 036909C-JVD-TRN-02062 | IFR | 2019-07-17 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-PE-02062 |  | 2019-07-03 | 2
036909C-1024-PDS-1390-2428 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - D-2440 Vapor Outlet - SCV-24010 | A | 2019-06-21 | IFR | OL1-2P03-2428 | MP | 2019-07-02 | 036909C-JVD-TRN-02062 | 036909C-JVD-TRN-02062 | IFR | 2019-07-17 | 2019-07-24 | R1-No comments | TPSK-LSPA1-T-PE-02062 |  | 2019-07-03 | 2
036909C-1024-PDS-1390-2418 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - E-2460 -Shell Side- Outlet - SCV-24007 | A | 2019-06-21 | IFR | OL1-2P03-2418 | MP | 2019-07-02 | 036909C-JVD-TRN-02062 | 036909C-JVD-TRN-02062 | IFR | 2019-07-17 | 2019-07-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02062 |  | 2019-07-03 | 2
036909C-1029-PDS-1390-2928 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2801A Suction - 10-SP-29028 | A | 2019-06-27 | IFR | OL1-2P03-2928 | MP | 2019-07-02 | 036909C-JVD-TRN-02063 | 036909C-JVD-TRN-02063 | IFR | 2019-07-17 | 2019-07-24 | R2-Comments as noted | TPSK-LSPA1-T-MP-02063 |  | 2019-07-03 | 2
036909C-1024-PDS-1390-2446 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - E-2460 -Shell Side- Outlet - SCV-24008 | A | 2019-06-21 | IFR | OL1-2P03-2446 | MP | 2019-07-02 | 036909C-JVD-TRN-02062 | 036909C-JVD-TRN-02062 | IFR | 2019-07-17 | 2019-07-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02062 |  | 2019-07-03 | 2
036909C-1059-PDS-0900-5901 | Process Equipment Datasheet - 10-P-5900 A-B - Sulfuric Acid Distribution Pumps | C | 2019-05-15 | IFD | OL1-2G30-5901 | PE | 2019-05-16 | 036909C-JVD-TRN-01678 | 036909C-JVD-TRN-01678 | IFR | 2019-05-31 | 2019-06-04 | Response to Client Comment sent July 24 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01678 |  | 2019-05-17 | 2
036909C-1056-PDS-0200-5610 | Process Equipment Datasheet - 10-PIT-5610 - Hydroblast Sump | B | 2019-04-08 | IFD | OL1-2G30-5610 | PE | 2019-04-08 | 036909C-JVD-TRN-01281 | 036909C-JVD-TRN-01281, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-23 | 2019-06-07 | Response to Client Comment sent July 24 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01281 |  | 2019-04-09 | 2
036909C-1031-SP-1541-3107 | Instrument Datasheets for Control Valve Angle Type - Area 31 | A | 2019-07-01 | IFQ | OL1-2I20-3117 | IE | 2019-07-05 | 036909C-JVD-TRN-02087 | 036909C-JVD-TRN-02087 | IFI |  | 2019-07-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-02087 |  | 2019-07-08 | 3
036909C-1031-SP-1541-3101 | Instrument Datasheets for Control Valve Globe Type - Area 31 | A | 2019-07-01 | IFQ | OL1-2I20-3101 | IE | 2019-07-05 | 036909C-JVD-TRN-02087 | 036909C-JVD-TRN-02087 | IFI |  | 2019-07-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-02087 |  | 2019-07-08 | 3
036909C-1030-SP-1547-3002 | Instrument Datasheets for Flow Element Rotameter - Area 30 | A | 2019-07-01 | IFQ | OL1-2I20-3028 | IE | 2019-07-05 | 036909C-JVD-TRN-02087 | 036909C-JVD-TRN-02087 | IFI |  | 2019-07-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-02087 |  | 2019-07-08 | 3
036909C-1031-SP-1547-3109 | Instrument Datasheets for Flow Element Integral Orifice Area 31 | A | 2019-06-27 | IFQ | OL1-2I20-3132 | IE | 2019-07-01 | 036909C-JVD-TRN-02037 | 036909C-JVD-TRN-02037 | IFI |  | 2019-07-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-02037 |  | 2019-07-02 | 3
036909C-1031-SP-1546-3102 | Instrument Datasheets for Flow Element Orifice Area 31 | A | 2019-06-27 | IFQ | OL1-2I20-3122 | IE | 2019-07-01 | 036909C-JVD-TRN-02037 | 036909C-JVD-TRN-02037 | IFI |  | 2019-07-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-02037 |  | 2019-07-02 | 3
036909C-1031-SP-1543-3104 | Instrument Datasheets for ON-OFF Valve Butterfly Type Area 31 | A | 2019-06-26 | IFQ | OL1-2I20-3112 | IE | 2019-07-01 | 036909C-JVD-TRN-02037 | 036909C-JVD-TRN-02037 | IFI |  | 2019-07-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-02037 |  | 2019-07-02 | 3
036909C-1031-SP-1543-3101 | Instrument Datasheets for ON-OFF Valve Ball Type Area 31 | A | 2019-06-26 | IFQ | OL1-2I20-3111 | IE | 2019-07-01 | 036909C-JVD-TRN-02037 | 036909C-JVD-TRN-02037 | IFI |  | 2019-07-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-02037 |  | 2019-07-02 | 3
036909C-1059-DW-1514-5901 | Cause and Effect Diagram Area 59 Supporting Utilities Auxiliaries | B | 2019-06-28 | IBD | OL1-2G50-5901 | PE | 2019-07-01 | 036909C-JVD-TRN-02036 | 036909C-JVD-TRN-02036 | IFR | 2019-07-16 | 2019-07-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02036 |  | 2019-07-02 | 2
036909C-1053-DW-1514-5301 | Cause and Effect Diagram Area 53 Cooling Water System | B | 2019-06-28 | IBD | OL1-2G50-5301 | PE | 2019-07-01 | 036909C-JVD-TRN-02036 | 036909C-JVD-TRN-02036 | IFR | 2019-07-16 | 2019-07-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02036 |  | 2019-07-02 | 2
036909C-1021-DW-1514-2101 | Cause and Effect Diagram Area 21 Quench Water Dilution Steam | B | 2019-06-28 | IBD | OL1-2G50-2101 | PE | 2019-07-01 | 036909C-JVD-TRN-02036 | 036909C-JVD-TRN-02036 | IFR | 2019-07-16 | 2019-07-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02036 |  | 2019-07-02 | 2
036909C-1020-DW-1514-2001 | Cause and Effect Diagram Area 20 Quench Oil | B | 2019-06-28 | IBD | OL1-2G50-2001 | PE | 2019-07-01 | 036909C-JVD-TRN-02036 | 036909C-JVD-TRN-02036 | IFR | 2019-07-16 | 2019-07-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-02036 |  | 2019-07-02 | 2
036909C-1000-MR-1547-0007 | MR For Ultrasonic Flow Meter | A | 2019-07-03 | IFQ | OL1-2C17-010801 | PL | 2019-07-08 | 036909C-JVD-TRN-02093 | 036909C-JVD-TRN-02093 | IFR | 2019-07-23 | 2019-07-19 | R2-Comments as noted | TPSK-LSPA1-T-PL-02093 |  | 2019-07-09 | 2
036909C-1000-JSS-1543-0001 | Job Supply Specification For Pneumatic On Off Valves | A | 2019-06-21 | IFQ | OL1-2I92-0606 | IE | 2019-06-27 | 036909C-JVD-TRN-02016 | 036909C-JVD-TRN-02016 | IFA | 2019-07-12 | 2019-07-09 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-IE-02016 |  | 2019-06-28 | 1
036909C-1055-SP-1543-5501 | Instrument Datasheets for ON-OFF Valve - Ball Type - Area 55 | A | 2019-06-01 | IFQ | OL1-2I20-5511 | IE | 2019-06-03 | 036909C-JVD-TRN-01792 | 036909C-JVD-TRN-01792 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01792 |  | 2019-06-10 | 3
036909C-1059-SP-1543-5901 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 59 | A | 2019-06-06 | IFQ | OL1-2I20-5911 | IE | 2019-06-10 | 036909C-JVD-TRN-01845 | 036909C-JVD-TRN-01845 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01845 |  | 2019-06-11 | 3
036909C-1027-SP-1543-2704 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 27 | A | 2019-06-18 | IFQ | OL1-2I20-2712 | IE | 2019-06-18 | 036909C-JVD-TRN-01919 | 036909C-JVD-TRN-01919 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-01919 |  | 2019-06-19 | 3
036909C-1051-SP-1543-5104 | Instrument Datasheets for ON-OFF Valve -Butterfly Type - Area 51 | A | 2019-06-06 | IFQ | OL1-2I20-5112 | IE | 2019-06-07 | 036909C-JVD-TRN-01828 | 036909C-JVD-TRN-01828 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK- LSPA1-T-IE-01828 |  | 2019-06-10 | 3
036909C-1056-SP-1543-5601 | Instrument Datasheets for ON-OFF Valve - Ball Type - Area 56 | A | 2019-06-06 | IFQ | OL1-2I20-5611 | IE | 2019-06-11 | 036909C-JVD-TRN-01866 | 036909C-JVD-TRN-01866 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01866 |  | 2019-06-11 | 3
036909C-1056-SP-1543-5604 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 56 | A | 2019-06-06 | IFQ | OL1-2I20-5612 | IE | 2019-06-11 | 036909C-JVD-TRN-01866 | 036909C-JVD-TRN-01866 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01866 |  | 2019-06-11 | 3
036909C-1027-SP-1543-2701 | Instrument Datasheets for ON-OFF Valve - Ball Type - Area 27 | A | 2019-06-18 | IFQ | OL1-2I20-2711 | IE | 2019-06-18 | 036909C-JVD-TRN-01919 | 036909C-JVD-TRN-01919 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01919 |  | 2019-06-19 | 3
036909C-1055-SP-1543-5504 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 55 | A | 2019-05-29 | IFQ | OL1-2I20-5512 | IE | 2019-06-03 | 036909C-JVD-TRN-01792 | 036909C-JVD-TRN-01792 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01792 |  | 2019-06-10 | 3
036909C-1052-SP-1543-5204 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 52 | A | 2019-05-27 | IFQ | OL1-2I20-5212 | IE | 2019-06-03 | 036909C-JVD-TRN-01792 | 036909C-JVD-TRN-01792 | IFI |  | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-IE-01792 |  | 2019-06-10 | 3
036909C-1019-SP-1543-1901 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 19 | A | 2019-05-14 | IFQ | OL1-2I20-1911 | IE | 2019-05-14 | 036909C-JVD-TRN-01660 | 036909C-JVD-TRN-01660 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01660 |  | 2019-05-15 | 3
036909C-1020-SP-1543-2004 | Instrument Datasheets for ON-OFF Valve -Butterfly Type- Area 20 | A | 2019-05-08 | IFQ | OL1-2I20-2012 | IE | 2019-05-09 | 036909C-JVD-TRN-01625 | 036909C-JVD-TRN-01625 | IFI |  | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01625 |  | 2019-05-10 | 3
036909C-1021-SP-1543-2101 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 21 | A | 2019-05-08 | IFQ | OL1-2I20-2111 | IE | 2019-05-09 | 036909C-JVD-TRN-01625 | 036909C-JVD-TRN-01625 | IFI |  | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01625 |  | 2019-05-10 | 3
036909C-1020-SP-1543-2001 | Instrument Datasheets for ON-OFF Valve -Ball Type- Area 20 | A | 2019-05-07 | IFQ | OL1-2I20-2011 | IE | 2019-05-09 | 036909C-JVD-TRN-01625 | 036909C-JVD-TRN-01625 | IFI |  | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01625 |  | 2019-05-10 | 3
036909C-1012-SP-1543-1201 | Instrument Datasheets for ON-OFF Valve -Ball Type -Area 12 -BOP | A | 2019-05-07 | IFQ | OL1-2I20-1211 | IE | 2019-05-08 | 036909C-JVD-TRN-01615 | 036909C-JVD-TRN-01615 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01615 |  | 2019-05-09 | 3
036909C-1021-SP-1543-2104 | Instrument Datasheets for ON-OFF Valve - Butterfly Type -Area 21 | A | 2019-05-09 | IFQ | OL1-2I20-2112 | IE | 2019-05-13 | 036909C-JVD-TRN-01650 | 036909C-JVD-TRN-01650 | IFI |  | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-IE-01650 |  | 2019-05-14 | 3
036909C-1029-SP-1543-2901 | Instrument Datasheets for ON-OFF Valve (Ball Type) Area 29 | A | 2019-05-21 | IFQ | OL1-2I20-2911 | IE | 2019-05-22 | 036909C-JVD-TRN-01717 | 036909C-JVD-TRN-01717 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01717 |  | 2019-05-23 | 3
036909C-1011-SP-1543-1101 | Instrument Datasheets for ON-OFF Valve Ball Type - Area 11 BOP | A | 2019-05-06 | IFQ | OL1-2I20-1111 | IE | 2019-05-07 | 036909C-JVD-TRN-01594 | 036909C-JVD-TRN-01594 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01594 |  | 2019-05-08 | 3
036909C-1052-SP-1543-5201 | Instrument Datasheets for ON-OFF - Ball Type - Area 52 | A | 2019-05-27 | IFQ | OL1-2I20-5211 | IE | 2019-06-03 | 036909C-JVD-TRN-01792 | 036909C-JVD-TRN-01792 | IFI |  | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-IE-01792 |  | 2019-06-10 | 3
036909C-1024-SP-1543-2401 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 24 | A | 2019-04-24 | IFQ | OL1-2I20-2411 | IE | 2019-05-06 | 036909C-JVD-TRN-01581 | 036909C-JVD-TRN-01581 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01581 |  | 2019-05-07 | 3
036909C-1010-SP-1543-1004 | Instrument Datasheets for ON-OFF Valve -Butterfly Type- Area 10 | A | 2019-05-10 | IFQ | OL1-2I20-1012 | IE | 2019-05-14 | 036909C-JVD-TRN-01660 | 036909C-JVD-TRN-01660 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01660 |  | 2019-05-15 | 3
036909C-1026-SP-1543-2604 | Instrument Datasheets for ON-OFF Valve -Butterfly Type - Area 26 | A | 2019-05-31 | IFQ | OL1-2I20-2612 | IE | 2019-06-03 | 036909C-JVD-TRN-01792 | 036909C-JVD-TRN-01792 | IFI |  | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-IE-01792 |  | 2019-06-10 | 3
036909C-1012-SP-1543-1204 | Instrument Datasheets for ON-OFF Valve -Butterfly Type - Area 12 -BOP | A | 2019-05-07 | IFQ | OL1-2I20-1212 | IE | 2019-05-08 | 036909C-JVD-TRN-01615 | 036909C-JVD-TRN-01615 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01615 |  | 2019-05-09 | 3
036909C-1010-SP-1543-1001 | Instrument Datasheets for ON-OFF Valve -Ball Type -Area 10 | A | 2019-05-10 | IFQ | OL1-2I20-1010 | IE | 2019-05-13 | 036909C-JVD-TRN-01658 | 036909C-JVD-TRN-01658 | IFI |  | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01658 |  | 2019-05-14 | 3
036909C-1026-SP-1543-2601 | Instrument Datasheet for ON-OFF Valve - Ball Type- Area 26 | A | 2019-05-31 | IFQ | OL1-2I20-2611 | IE | 2019-06-05 | 036909C-JVD-TRN-01807 | 036909C-JVD-TRN-01807 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01807 |  | 2019-06-10 | 3
036909C-1000-MR-1547-0001 | MR For Vortex Meter | A | 2019-06-21 | IFQ | OL1-2C17-014001 | PL | 2019-07-05 | 036909C-JVD-TRN-02082 | 036909C-JVD-TRN-02082 | IFR | 2019-07-22 | 2019-07-18 | R2-Comments as noted | TPSK-LSPA1-T-PL-02082 |  | 2019-07-08 | 2
036909C-1000-MR-1547-0005 | MR For Electromagnetic Flow Meter | A | 2019-07-02 | IFQ | OL1-2C17-010301 | PL | 2019-07-04 | 036909C-JVD-TRN-02078 | 036909C-JVD-TRN-02078 | IFR | 2019-07-19 | 2019-07-18 | R2-Comments as noted | TPSK-LSPA1-T-PL-02078 |  | 2019-07-05 | 2
036909C-1012-DL-4061-2009 | Deviation List For Furnace Elevator | B | 2019-06-13 | IFR | OL1-2C40-709000 | PL | 2019-07-05 | 036909C-JVD-TRN-02084 | 036909C-JVD-TRN-02084 | IFR | 2019-07-20 | 2019-07-18 | R1-No comments | TPSK-LSPA1-T-PL-02084 |  | 2019-07-08 | 3
036909C-105W-DW-0053-0001 | Detail Key Plan - Zone 5W - Waste Water Treatment | B | 2019-07-19 | IBD | OL1-2P06-0036 | MP | 2019-07-23 | 036909C-JVD-TRN-02242 | 036909C-JVD-TRN-02242 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-MP-02242 |  | 2019-07-24 | 2
036909C-103A-DW-0053-0001 | Detail Key Plan - Zone 3 A Butadiene Extraction Unit | B | 2019-07-19 | IBD | OL1-2P06-0031 | MP | 2019-07-23 | 036909C-JVD-TRN-02242 | 036909C-JVD-TRN-02242 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-MP-02242 |  | 2019-07-24 | 2
036909C-1030-SP-0940-3061 | Mechanical Equipment Datasheet for Dimer Pumps | B | 2019-07-12 | Issue for Inquiry | OL1-2M03-3061 | ME | 2019-07-23 | 036909C-JVD-TRN-02241 | 036909C-JVD-TRN-02241 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02241 |  | 2019-07-24 | 2
036909C-1031-SP-0910-3127 | Mechanical Equipment Datasheet for BDU Ejector Seal Drum Pumps | B | 2019-07-03 | Issue for Inquiry | OL1-2M03-3127 | ME | 2019-07-23 | 036909C-JVD-TRN-02249 | 036909C-JVD-TRN-02249 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02249 |  | 2019-07-24 | 2
036909C-1030-SP-0910-3083 | Mechanical Equipment Datasheet for Butadiene Tower Refllux Pumps | B | 2019-07-03 | Issue for Inquiry | OL1-2M03-3083 | ME | 2019-07-23 | 036909C-JVD-TRN-02241 | 036909C-JVD-TRN-02241 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02241 |  | 2019-07-24 | 2
036909C-1031-SP-0910-3191 | Mechanical Equipment Datasheet for Solvent Slop Pump | B | 2019-07-12 | Issue for Inquiry | OL1-2M03-3191 | ME | 2019-07-23 | 036909C-JVD-TRN-02249 | 036909C-JVD-TRN-02249 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02249 |  | 2019-07-24 | 2
036909C-1031-SP-0910-3162 | Mechanical Equipment Datasheet for BDU Condensate Recycle Pumps | B | 2019-07-03 | Issue for Inquiry | OL1-2M03-3162 | ME | 2019-07-23 | 036909C-JVD-TRN-02249 | 036909C-JVD-TRN-02249 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02249 |  | 2019-07-24 | 2
036909C-1030-SP-0910-3097 | Mechanical Equipment Datasheet for Butadiene Product Pumps | B | 2019-07-03 | Issue for Inquiry | OL1-2M03-3097 | ME | 2019-07-23 | 036909C-JVD-TRN-02249 | 036909C-JVD-TRN-02249 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02249 |  | 2019-07-24 | 2
036909C-1031-SP-0910-3113 | Mechanical Equipment Datasheet for Solvent Return Pumps | B | 2019-07-03 | Issue for Inquiry | OL1-2M03-3113 | ME | 2019-07-23 | 036909C-JVD-TRN-02249 | 036909C-JVD-TRN-02249 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02249 |  | 2019-07-24 | 2
036909C-1030-SP-0910-3076 | Mechanical Equipment Datasheet for Direct Cooler Pumps | B | 2019-07-03 | Issue for Inquiry | OL1-2M03-3076 | ME | 2019-07-23 | 036909C-JVD-TRN-02241 | 036909C-JVD-TRN-02241 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02241 |  | 2019-07-24 | 2
036909C-1030-SP-0910-3086 | Mechanical Equipment Datasheet for Butadiene Tower Bottom Pumps | B | 2019-07-03 | Issue for Inquiry | OL1-2M03-3086 | ME | 2019-07-23 | 036909C-JVD-TRN-02241 | 036909C-JVD-TRN-02241 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02241 |  | 2019-07-24 | 2
036909C-1030-SP-0910-3067 | Mechanical Equipment Datasheet for C4 Acetylene Pumps | B | 2019-07-12 | Issue for Inquiry | OL1-2M03-3067 | ME | 2019-07-23 | 036909C-JVD-TRN-02241 | 036909C-JVD-TRN-02241 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02241 |  | 2019-07-24 | 2
036909C-1030-SP-0910-3066 | Mechanical Equipment Datasheet for Wastewater Pumps | B | 2019-07-03 | Issue for Inquiry | OL1-2M03-3066 | ME | 2019-07-23 | 036909C-JVD-TRN-02241 | 036909C-JVD-TRN-02241 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02241 |  | 2019-07-24 | 2
036909C-1030-SP-0910-3026 | Mechanical Equipment Datasheet for Main Washer Bottom Pumps | B | 2019-07-03 | Issue for Inquiry | OL1-2M03-3026 | ME | 2019-07-23 | 036909C-JVD-TRN-02241 | 036909C-JVD-TRN-02241 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02241 |  | 2019-07-24 | 2
036909C-102D-DW-0053-0001 | Detail Key Plan - Zone 2D - Process Cold Compressor | B | 2019-07-19 | IBD | OL1-2P06-0029 | MP | 2019-07-23 | 036909C-JVD-TRN-02242 | 036909C-JVD-TRN-02242 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-MP-02242 |  | 2019-07-24 | 2
036909C-102B-DW-1743-0047 | Foundation For 10-TK-2910 | A | 2019-07-16 | IFR | OL1-2K31-0060 | CV | 2019-07-22 | 036909C-JVD-TRN-02233 | 036909C-JVD-TRN-02233 | IFA | 2019-08-06 |  | Transmitted | TPSK-LSPA1-T-CV-02233 |  | 2019-07-23 | 1
036909C-1030-SP-0910-3056 | Mechanical Equipment Datasheet for Degasser Bottom Pumps | B | 2019-07-03 | Issue for Inquiry | OL1-2M03-3056 | ME | 2019-07-23 | 036909C-JVD-TRN-02241 | 036909C-JVD-TRN-02241 | IFR | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-ME-02241 |  | 2019-07-24 | 2
036909C-102B-DW-1744-0004-001 | Foundation For Basin 10-PIT-5606 | A | 2019-07-16 | IFR | OL1-2K31-4380 | CV | 2019-07-22 | 036909C-JVD-TRN-02233 | 036909C-JVD-TRN-02233 | IFA | 2019-08-06 |  | Transmitted | TPSK-LSPA1-T-CV-02233 |  | 2019-07-23 | 1
036909C-102B-DW-1743-0048-001 | Foundation For 10-TK-2300 | A | 2019-07-16 | IFR | OL1-2K31-0336 | CV | 2019-07-22 | 036909C-JVD-TRN-02233 | 036909C-JVD-TRN-02233 | IFA | 2019-08-06 |  | Transmitted | TPSK-LSPA1-T-CV-02233 |  | 2019-07-23 | 1
036909C-102B-DW-1744-0004-002 | Foundation For Basin 10-PIT-5606 | A | 2019-07-16 | IFR | OL1-2K31-4381 | CV | 2019-07-22 | 036909C-JVD-TRN-02233 | 036909C-JVD-TRN-02233 | IFA | 2019-08-06 |  | Transmitted | TPSK-LSPA1-T-CV-02233 |  | 2019-07-23 | 1
036909C-102A-DW-1842-0001-001 | Steel Structure For 10-STR-2A01 | A | 2019-07-19 | IFR | OL1-2K32-1720 | CV | 2019-07-22 | 036909C-JVD-TRN-02234 | 036909C-JVD-TRN-02234 | IFA | 2019-08-06 |  | Transmitted | TPSK-LSPA1-T-CV-02234 |  | 2019-07-23 | 1
036909C-102A-DW-1842-0001-002 | Steel Structure For 10-STR-2A01 | A | 2019-07-19 | IFR | OL1-2K32-1721 | CV | 2019-07-22 | 036909C-JVD-TRN-02234 | 036909C-JVD-TRN-02234 | IFA | 2019-08-06 |  | Transmitted | TPSK-LSPA1-T-CV-02234 |  | 2019-07-23 | 1
036909C-102A-CN-1832-0001 | Calculation Note For Steel Structure Of 10-STR-2A01 | A | 2019-07-19 | IFR | OL1-2K15-0034 | CV | 2019-07-23 | 036909C-JVD-TRN-02238 | 036909C-JVD-TRN-02238 | IFA | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-CV-02238 |  | 2019-07-24 | 1
036909C-1011-DW-0117-1563 | USC 36M Recycle Furnace Steel Access Door Davit Details | 0 | 2019-07-22 | IMP | OL1-2K32-1563 | CV | 2019-07-23 | 036909C-JVD-TRN-02248 | 036909C-JVD-TRN-02248 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02248 |  | 2019-07-24 | 3
036909C-1012-DW-0117-2563 | USC 132U Recycle Furnace Steel Access Door Davit Details | 0 | 2019-07-22 | IMP | OL1-2K32-2563 | CV | 2019-07-23 | 036909C-JVD-TRN-02248 | 036909C-JVD-TRN-02248 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02248 |  | 2019-07-24 | 3
036909C-100P-DW-1742-0001-003 | Concrete Structure 10-STR-0P01 - Foundations And Elevations - Reinforcement | A | 2019-07-11 | IFR | OL1-2K31-1962 | CV | 2019-07-22 | 036909C-JVD-TRN-02233 | 036909C-JVD-TRN-02233 | IFA | 2019-08-06 |  | Transmitted | TPSK-LSPA1-T-CV-02233 |  | 2019-07-23 | 1
036909C-100P-DW-1742-0001-004 | Concrete Structure 10-STR-0P01 - Foundations And Elevations - Reinforcement | A | 2019-07-11 | IFR | OL1-2K31-1963 | CV | 2019-07-22 | 036909C-JVD-TRN-02233 | 036909C-JVD-TRN-02233 | IFA | 2019-08-06 |  | Transmitted | TPSK-LSPA1-T-CV-02233 |  | 2019-07-23 | 1
036909C-100P-DW-1742-0001-002 | Concrete Structure 10-STR-0P01 - Foundations And Elevations - Formwork | A | 2019-07-11 | IFR | OL1-2K31-1961 | CV | 2019-07-22 | 036909C-JVD-TRN-02233 | 036909C-JVD-TRN-02233 | IFA | 2019-08-06 |  | Transmitted | TPSK-LSPA1-T-CV-02233 |  | 2019-07-23 | 1
036909C-100P-DW-1742-0001-001 | Concrete Structure 10-STR-0P01 - Foundations And Elevations - Formwork | A | 2019-07-11 | IFR | OL1-2K31-1960 | CV | 2019-07-22 | 036909C-JVD-TRN-02233 | 036909C-JVD-TRN-02233 | IFA | 2019-08-06 |  | Transmitted | TPSK-LSPA1-T-CV-02233 |  | 2019-07-23 | 1
036909C-1030-PDS-1560-0001 | Process Data Sheet For Analyzers Butadiene Extraction Unit Bdu - Area 30 | A | 2019-06-26 | IFR | OL1-2G31-3001 | PE | 2019-06-28 | 036909C-JVD-TRN-02027 | 036909C-JVD-TRN-02027 | IFR | 2019-07-15 | 2019-07-18 | R2-Comments as noted | TPSK-LSPA1-T-PE-02027 |  | 2019-07-01 | 2
036909C-1012-SP-4061-2002 | Elevator Data Sheet | 0 | 2019-06-07 | IMP | OL1-2M03-2002 | ME | 2019-06-07 | 036909C-JVD-TRN-01832 | 036909C-JVD-TRN-01832 | IFR | 2019-06-22 | 2019-07-03 | R2-Comments as noted | TPSK-LSPA1-T-ME-01832 |  | 2019-06-10 | 2
036909C-105W-DW-0053-0001 | Detail Key Plan - Zone 5W - Waste Water Treatment | A | 2019-05-24 | IFR | OL1-2P06-0036 | MP | 2019-05-30 | 036909C-JVD-TRN-01767 | 036909C-JVD-TRN-01767 | IFR | 2019-06-14 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-MP-01767 |  | 2019-05-31 | 2
036909C-105T-DW-0053-0001 | Detail Key Plan - Zone 5T - Cooling Water Unit | A | 2019-05-24 | IFR | OL1-2P06-0034 | MP | 2019-05-30 | 036909C-JVD-TRN-01767 | 036909C-JVD-TRN-01767 | IFR | 2019-06-14 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01767 |  | 2019-05-31 | 2
036909C-103A-DW-0053-0001 | Detail Key Plan - Zone 3 A Butadiene Extraction Unit | A | 2019-06-14 | IFR | OL1-2P06-0031 | MP | 2019-06-17 | 036909C-JVD-TRN-01904 | 036909C-JVD-TRN-01904 | IFR | 2019-07-02 | 2019-07-04 | R1-No comments | TPSK-LSPA1-T-MP-01904 |  | 2019-06-18 | 2
036909C-102C-DW-0053-0001 | Detail Key Plan - Zone 2C - Hot Fractionation-GHU Unit | A | 2019-05-24 | IFR | OL1-2P06-0028 | MP | 2019-05-30 | 036909C-JVD-TRN-01767 | 036909C-JVD-TRN-01767 | IFR | 2019-06-14 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01767 |  | 2019-05-31 | 2
036909C-102D-DW-0053-0001 | Detail Key Plan - Zone 2D - Process Cold Compressor | A | 2019-05-24 | IFR | OL1-2P06-0029 | MP | 2019-05-30 | 036909C-JVD-TRN-01767 | 036909C-JVD-TRN-01767 | IFR | 2019-06-14 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01767 |  | 2019-05-31 | 2
036909C-102E-DW-0053-0001 | Detail Key Plan - Zone 2E - Cracked Gas Compressor | A | 2019-05-24 | IFR | OL1-2P06-0030 | MP | 2019-05-30 | 036909C-JVD-TRN-01767 | 036909C-JVD-TRN-01767 | IFR | 2019-06-14 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01767 |  | 2019-05-31 | 2
036909C-102B-DW-0053-0001 | Detail Key Plan - Zone 2B - C3 Hydrogenation | A | 2019-05-24 | IFR | OL1-2P06-0027 | MP | 2019-05-30 | 036909C-JVD-TRN-01767 | 036909C-JVD-TRN-01767 | IFR | 2019-06-14 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01767 |  | 2019-05-31 | 2
036909C-101B-DW-0053-0001 | Detail Key Plan - Zone 1B - Furnaces Utilities | A | 2019-05-24 | IFR | OL1-2P06-0025 | MP | 2019-05-30 | 036909C-JVD-TRN-01767 | 036909C-JVD-TRN-01767 | IFR | 2019-06-14 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01767 |  | 2019-05-31 | 2
036909C-1025-SP-1513-2501 | Complex Loop Narratives - Area 25 - Cold Fractionation | A | 2019-04-15 | IFR | OL1-2I71-2501 | IE | 2019-04-15 | 036909C-JVD-TRN-01358 | 036909C-JVD-TRN-01358 | IFR | 2019-04-30 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-IE-01358 |  | 2019-04-16 | 2
036909C-1052-TDS-0610-5201 | Mechanical Equipment Data Sheet - 10-E-5200 - MP Ethylene Superheater | B | 2019-04-04 | IFQ | OL1-2M03-5201 | ME | 2019-04-12 | 036909C-JVD-TRN-01344 | 036909C-JVD-TRN-01344 | IFR | 2019-04-29 | 2019-05-20 | TPSK-LSPA1-E-00222 June 06 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01344 |  | 2019-04-15 | 2
036909C-1052-TDS-0610-5201 | Mechanical Equipment Data Sheet - 10-E-5200 - MP Ethylene Superheater | A | 2019-01-28 | IFQ | OL1-2M03-5201 | ME | 2019-01-29 | 036909C-JVD-TRN-00755 | 036909C-JVD-TRN-00755, ROC-TPSK-CECO-T-00018 | IFR | 2019-02-12 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00755 |  | 2019-01-29 | 2
036909C-1028-TDS-0610-2807 | Mechanical Equipment Data Sheet - 10-E-2807 - C3 Chiller No 1 | B | 2019-04-10 | IFQ | OL1-2M03-2807 | ME | 2019-04-11 | 036909C-JVD-TRN-01324 | 036909C-JVD-TRN-01324 | IFR | 2019-04-26 | 2019-05-20 | TPSK-LSPA1-E-00222 June 06 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01324 |  | 2019-04-12 | 2
036909C-1027-TDS-0610-2721 | Mechanical Equipment Data Sheet - 10-E-2720 - Rerun Tower Condenser | A | 2019-02-21 | IFQ | OL1-2M03-2721 | ME | 2019-02-28 | 036909C-JVD-TRN-00956 | 036909C-JVD-TRN-00956, ROC-TPSK-CECO-T-00018 | IFR | 2019-03-15 | 2019-03-25 | R1-No comments | TPSK-LSPA1-T-ME -00956 |  | 2019-03-01 | 2
036909C-1027-TDS-0610-2715 | Mechanical Equipment Data Sheet - 10-E-2715 A-B - Depentanizer Reboiler | A | 2019-02-13 | IFQ | OL1-2M03-2715 | ME | 2019-02-21 | 036909C-JVD-TRN-00908 | 036909C-JVD-TRN-00908, ROC-TPSK-CECO-T-00018 | IFR | 2019-03-08 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00908 |  | 2019-02-22 | 2
036909C-1027-TDS-0610-2715 | Mechanical Equipment Data Sheet - 10-E-2715 A-B - Depentanizer Reboiler | B | 2019-04-12 | IFQ | OL1-2M03-2715 | ME | 2019-04-15 | 036909C-JVD-TRN-01362 | 036909C-JVD-TRN-01362 | IFR | 2019-04-30 |  | Transmitted | TPSK-LSPA1-T-ME-01362 |  | 2019-04-16 | 2
036909C-1027-TDS-0610-2715 | Mechanical Equipment Data Sheet - 10-E-2715 A-B - Depentanizer Reboiler | C | 2019-05-14 | IFQ | OL1-2M03-2715 | ME | 2019-05-16 | 036909C-JVD-TRN-01685 | 036909C-JVD-TRN-01685 | IFR | 2019-05-31 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01685 |  | 2019-05-17 | 2
036909C-1025-TDS-0610-2575 | Mechanical Equipment Data Sheet - 10-E-2575 - Deethanizer Reboiler | B | 2019-03-01 | IFQ | OL1-2M03-2575 | ME | 2019-03-01 | 036909C-JVD-TRN-00961 | 036909C-JVD-TRN-00961, ROC-TPSK-CECO-T-00018 | IFR | 2019-03-16 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-ME-00961 |  | 2019-03-04 | 2
036909C-1021-TDS-0610-2166 | Mechanical Equipment Data Sheet - 10-E-2166 - DSG Blowdown Cooler | A | 2019-01-18 | IFQ | OL1-2M03-2166 | ME | 2019-01-22 | 036909C-JVD-TRN-00684 | 036909C-JVD-TRN-00684, ROC-TPSK-CECO-T-00017 | IFR | 2019-02-04 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00684 |  | 2019-01-22 | 2
036909C-1021-TDS-0610-2166 | Mechanical Equipment Data Sheet - 10-E-2166 - DSG Blowdown Cooler | B | 2019-03-27 | IFQ | OL1-2M03-2166 | ME | 2019-04-03 | 036909C-JVD-TRN-01248 | 036909C-JVD-TRN-01248 | IFR | 2019-04-18 | 2019-05-20 | TPSK-LSPA1-E-00222 June 06 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01248 |  | 2019-04-04 | 2
036909C-1021-TDS-0610-2147 | Mechanical Equipment Data Sheet - 10-E-2146 - DSG Feed Heater | B | 2019-04-03 | IFQ | OL1-2M03-2147 | ME | 2019-04-10 | 036909C-JVD-TRN-01302 | 036909C-JVD-TRN-01302 | IFR | 2019-04-25 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-ME-01302 |  | 2019-04-11 | 2
036909C-1021-TDS-0610-2137 | Mechanical Equipment Data Sheet - 10-E-2136 - Process Water Stripper Feed Heater | B | 2019-03-27 | IFQ | OL1-2M03-2137 | ME | 2019-04-04 | 036909C-JVD-TRN-01251 | 036909C-JVD-TRN-01251 | IFR | 2019-04-19 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-ME -01251 |  | 2019-04-05 | 2
036909C-1010-TDS-0610-1051 | Mechanical Equipment Data Sheet - 10-E-1050 - C2 Feed Superheater | B | 2019-02-26 | IFQ | OL1-2M03-1051 | ME | 2019-03-01 | 036909C-JVD-TRN-00961 | 036909C-JVD-TRN-00961, ROC-TPSK-CECO-T-00017 | IFR | 2019-03-16 | 2019-03-29 | TPSK-LSPA1-E-00154 April 26 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-00961 |  | 2019-03-04 | 2
036909C-1010-TDS-0610-1015 | Mechanical Equipment Data Sheet - 10-E-1015 - LPG Superheater | B | 2019-02-27 | IFQ | OL1-2M03-1015 | ME | 2019-03-01 | 036909C-JVD-TRN-00971 | 036909C-JVD-TRN-00971, ROC-TPSK-CECO-T-00017 | IFR | 2019-03-16 | 2019-03-29 | TPSK-LSPA1-E-00133 April 03 2019-Comments as noted | TPSK-LSPA1-T-ME-00971 |  | 2019-03-04 | 2
036909C-1001-CN-3444-0002 | Prefabricated Gatehouse Hvac Thermal Calculation | B | 2019-07-01 | IDD | OL1-2H10-0004 | EE | 2019-07-03 | 036909C-JVD-TRN-02068 | 036909C-JVD-TRN-02068 | IFA | 2019-07-18 | 2019-07-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-02068 |  | 2019-07-04 | 1
036909C-1028-PDS-1546-2890 | Process Datasheet for Restriction Orifice Unit 28 | A | 2019-06-26 | IFR | OL1-2G31-2890 | PE | 2019-06-27 | 036909C-JVD-TRN-02018 | 036909C-JVD-TRN-02018 | IFR | 2019-07-12 | 2019-07-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02018 |  | 2019-06-28 | 2
036909C-102D-DW-1842-0001-06 | Steel Structure For Shelter 10-SHT-2D01 - Elevations | A | 2019-05-29 | IFR | OL1-2K32-2105 | CV | 2019-06-06 | 036909C-JVD-TRN-01814 | 036909C-JVD-TRN-01814 | IFA | 2019-06-21 | 2019-07-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01814 |  | 2019-06-10 | 1
036909C-102D-DW-1842-0001-05 | Steel Structure For Shelter 10-SHT-2D01 - Elevations | A | 2019-05-29 | IFR | OL1-2K32-2104 | CV | 2019-06-06 | 036909C-JVD-TRN-01814 | 036909C-JVD-TRN-01814 | IFA | 2019-06-21 | 2019-07-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01814 |  | 2019-06-10 | 1
036909C-102D-DW-1842-0001-04 | Steel Structure For Shelter 10-SHT-2D01 - Plans | A | 2019-05-29 | IFR | OL1-2K32-2103 | CV | 2019-06-06 | 036909C-JVD-TRN-01814 | 036909C-JVD-TRN-01814 | IFA | 2019-06-21 | 2019-07-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01814 |  | 2019-06-10 | 1
036909C-102D-DW-1842-0001-03 | Steel Structure For Shelter 10-SHT-2D01 - Plan & Details | A | 2019-05-29 | IFR | OL1-2K32-2102 | CV | 2019-06-06 | 036909C-JVD-TRN-01814 | 036909C-JVD-TRN-01814 | IFA | 2019-06-21 | 2019-07-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01814 |  | 2019-06-10 | 1
036909C-102D-DW-1842-0001-02 | Steel Structure For Shelter 10-SHT-2D01 - Plans | A | 2019-05-29 | IFR | OL1-2K32-2101 | CV | 2019-06-06 | 036909C-JVD-TRN-01814 | 036909C-JVD-TRN-01814 | IFA | 2019-06-21 | 2019-07-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01814 |  | 2019-06-10 | 1
036909C-102D-DW-1842-0001-01 | Steel Structure For Shelter 10-SHT-2D01 - 3D View | A | 2019-05-29 | IFR | OL1-2K32-2100 | CV | 2019-06-06 | 036909C-JVD-TRN-01814 | 036909C-JVD-TRN-01814 | IFA | 2019-06-21 | 2019-07-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01814 |  | 2019-06-10 | 1
036909C-1012-DW-0131-2518 | USC 132U Cracking Furnace Steel Radiant Sections And Details | 1 | 2019-07-17 | IMP | OL1-2K32-2518 | CV | 2019-07-22 | 036909C-JVD-TRN-02228 | 036909C-JVD-TRN-02228 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02228 |  | 2019-07-23 | 3
036909C-1012-DW-0117-2552 | USC 132U Cracking Furnace Steel Radiant Coil Removal Access Door Details | 1 | 2019-07-17 | IMP | OL1-2K32-2552 | CV | 2019-07-22 | 036909C-JVD-TRN-02223 | 036909C-JVD-TRN-02223 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02223 |  | 2019-07-23 | 3
036909C-1012-DW-0117-2561 | USC 132U Cracking Furnace Steel Access Door Davit Details | 0 | 2019-07-17 | IMP | OL1-2K32-2561 | CV | 2019-07-22 | 036909C-JVD-TRN-02223 | 036909C-JVD-TRN-02223 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02223 |  | 2019-07-23 | 3
036909C-1011-DW-0117-1561 | USC 36M Recycle Furnace Steel Access Door Davit Details | 0 | 2019-07-17 | IMP | OL1-2K32-1561 | CV | 2019-07-22 | 036909C-JVD-TRN-02227 | 036909C-JVD-TRN-02227 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02227 |  | 2019-07-23 | 3
036909C-1011-DW-0117-1552 | USC 36M Recycle Furnace Steel Radiant Coil Removal Access Door Details | 1 | 2019-07-17 | IMP | OL1-2K32-1552 | CV | 2019-07-22 | 036909C-JVD-TRN-02227 | 036909C-JVD-TRN-02227 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02227 |  | 2019-07-23 | 3
036909C-1011-DW-0131-1518 | USC Recycle Furnace Steel Radiant Sections and Details | 1 | 2019-07-17 | IMP | OL1-2K32-1518 | CV | 2019-07-22 | 036909C-JVD-TRN-02224 | 036909C-JVD-TRN-02224 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02224 |  | 2019-07-23 | 3
036909C-1027-TDS-0610-2725 | Mechanical Equipment Data Sheet - 10-E-2725 A-B-C - Rerun Tower Reboiler | A | 2019-05-10 | IFQ | OL1-2M03-2725 | ME | 2019-05-16 | 036909C-JVD-TRN-01685 | 036909C-JVD-TRN-01685 | IFR | 2019-05-31 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01685 |  | 2019-05-17 | 2
036909C-1025-TDS-0610-2576 | Mechanical Equipment Data Sheet - 10-E-2576 - Deethanizer Bottoms Cooler | B | 2019-03-18 | IFQ | OL1-2M03-2576 | ME | 2019-03-21 | 036909C-JVD-TRN-01123 | 036909C-JVD-TRN-01123, ROC-TPSK-CECO-T-00018 | IFR | 2019-04-05 | 2019-04-11 | R1-No comments | TPSK-LSPA1-T-ME-01123 |  | 2019-03-22 | 2
036909C-1020-TDS-0610-2048 | Mechanical Equipment Data Sheet - 10-E-2048 - Heavy Fuel Oil Product Cooler | B | 2019-04-10 | IFQ | OL1-2M03-2048 | ME | 2019-04-11 | 036909C-JVD-TRN-01324 | 036909C-JVD-TRN-01324 | IFR | 2019-04-26 | 2019-05-20 | TPSK-LSPA1-E-00222 June 06 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01324 |  | 2019-04-12 | 2
036909C-1020-TDS-0610-2026 | Mechanical Equipment Data Sheet - 10-E-2026 - FO Product Cooler | A | 2019-01-17 | IFQ | OL1-2M03-2026 | ME | 2019-01-22 | 036909C-JVD-TRN-00683 | 036909C-JVD-TRN-00683, ROC-TPSK-CECO-T-00017 | IFR | 2019-02-04 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00683 |  | 2019-01-22 | 2
036909C-1025-SP-1513-2502 | Instrument Interlock Descriptions - Area 25 - Cold Fractionation | A | 2019-04-02 | IFR | OL1-2G50-2502 | PE | 2019-04-02 | 036909C-JVD-TRN-01225 | 036909C-JVD-TRN-01225 | IFR | 2019-04-17 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01225 |  | 2019-04-03 | 2
036909C-1011-DW-0117-1582 | USC 36M Recycle Furnace Steel Duct Plan and Elevations | A | 2019-04-05 | IFI | OL1-2K32-1582 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1011-DW-0117-1552 | USC 36M Recycle Furnace Steel Radiant Coil Removal Access Door Details | 0 | 2019-05-15 | IMP | OL1-2K32-1552 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1012-DW-0131-2518 | USC 132U Cracking Furnace Steel Radiant Sections And Details | 0 | 2019-05-15 | IMP | OL1-2K32-2518 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1011-DW-0131-1518 | USC Recycle Furnace Steel Radiant Sections and Details | 0 | 2019-05-15 | IMP | OL1-2K32-1518 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1012-DW-0117-2552 | USC 132U Cracking Furnace Steel Radiant Coil Removal Access Door Details | 0 | 2019-05-15 | IMP | OL1-2K32-2552 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-105W-DW-0051-0001 | Detail Plot Plan - Zone 5W Waste Water Treatment | B | 2019-05-21 | IBD | OL1-2P06-0017 | MP | 2019-05-28 | 036909C-JVD-TRN-01752 | 036909C-JVD-TRN-01752 | IFR | 2019-06-12 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01752 |  | 2019-05-29 | 2
036909C-105U-DW-0051-0001 | Detail Plot Plan - Zone 5U - Utilities | B | 2019-05-21 | IBD | OL1-2P06-0016 | MP | 2019-05-28 | 036909C-JVD-TRN-01752 | 036909C-JVD-TRN-01752 | IFR | 2019-06-12 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01752 |  | 2019-05-29 | 2
036909C-105T-DW-0051-0001 | Detail Plot Plan - Zone 5T - Cooling Water Unit | B | 2019-05-21 | IBD | OL1-2P06-0015 | MP | 2019-05-28 | 036909C-JVD-TRN-01752 | 036909C-JVD-TRN-01752 | IFR | 2019-06-12 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01752 |  | 2019-05-29 | 2
036909C-102E-DW-0051-0001 | Detail Plot Plan - Zone 2E - Cracked Gas Compressor | B | 2019-05-21 | IBD | OL1-2P06-0012 | MP | 2019-05-28 | 036909C-JVD-TRN-01752 | 036909C-JVD-TRN-01752 | IFR | 2019-06-12 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01752 |  | 2019-05-29 | 2
036909C-102D-DW-0051-0001 | Detail Plot Plan - Zone 2D - Process Cold Compressor | B | 2019-05-21 | IBD | OL1-2P06-0011 | MP | 2019-05-28 | 036909C-JVD-TRN-01752 | 036909C-JVD-TRN-01752 | IFR | 2019-06-12 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01752 |  | 2019-05-29 | 2
036909C-102C-DW-0051-0001 | Detail Plot Plan - Zone 2C - Hot Fractionation-GHU Unit | B | 2019-05-21 | IBD | OL1-2P06-0010 | MP | 2019-05-28 | 036909C-JVD-TRN-01752 | 036909C-JVD-TRN-01752 | IFR | 2019-06-12 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01752 |  | 2019-05-29 | 2
036909C-102B-DW-0051-0001 | Detail Plot Plan - Zone 2B - C3 Hydrogenation | B | 2019-05-21 | IBD | OL1-2P06-0009 | MP | 2019-05-28 | 036909C-JVD-TRN-01752 | 036909C-JVD-TRN-01752 | IFR | 2019-06-12 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01752 |  | 2019-05-29 | 2
036909C-101B-DW-0051-0001 | Detail Plot Plan - Zone 1B - Furnaces Utilities | B | 2019-05-15 | IBD | OL1-2P06-0007 | MP | 2019-05-28 | 036909C-JVD-TRN-01752 | 036909C-JVD-TRN-01752 | IFR | 2019-06-12 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01752 |  | 2019-05-29 | 2
036909C-100P-DW-0051-0001 | Unit Plot Plan - Zone 0P - Main Pipe Rack | B | 2019-05-21 | IBD | OL1-2P06-0003 | MP | 2019-05-28 | 036909C-JVD-TRN-01752 | 036909C-JVD-TRN-01752 | IFR | 2019-06-12 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01752 |  | 2019-05-29 | 2
036909C-1055-DW-1514-5501 | Cause and Effect Diagram - Area 55 - Vent Gas and Flare System | A | 2019-04-17 | IFR | OL1-2G50-5501 | PE | 2019-04-22 | 036909C-JVD-TRN-01429 | 036909C-JVD-TRN-01429, ROC-TPSK-CECO-T-00055 | IFR | 2019-05-07 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-01429 |  | 2019-04-23 | 2
036909C-1025-DW-1514-2501 | Cause and Effect Diagram - Area 25 - Cold Fractionation "CAUSE AND EFFECT DIAGRAM AREA 25: COLD FRACTIONATION" | A | 2019-03-21 | IFR | OL1-2G50-2501 | PE | 2019-03-21 | 036909C-JVD-TRN-01133 | 036909C-JVD-TRN-01133, ROC-TPSK-CECO-T-00032 | IFR | 2019-04-05 | 2019-04-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01133 |  | 2019-03-22 | 2
036909C-1026-TDS-0610-2666 | Mechanical Equipment Data Sheet - 10-E-2666 - Debutanizer Bottoms Cooler | B | 2019-04-11 | IFQ | OL1-2M03-2666 | ME | 2019-04-12 | 036909C-JVD-TRN-01344 | 036909C-JVD-TRN-01344 | IFR | 2019-04-29 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-ME-01344 |  | 2019-04-15 | 2
036909C-1026-TDS-0610-2666 | Mechanical Equipment Data Sheet - 10-E-2666 - Debutanizer Bottoms Cooler | C | 2019-05-20 | IFQ | OL1-2M03-2666 | ME | 2019-05-21 | 036909C-JVD-TRN-01712 | 036909C-JVD-TRN-01712 | IFR | 2019-06-05 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01712 |  | 2019-05-23 | 2
036909C-1024-TDS-0610-2455 | Mechanical Equipment Data Sheet - 10-E-2455 AB - LP Depropanizer Reboilers | C | 2019-05-14 | IFQ | OL1-2M03-2455 | ME | 2019-05-21 | 036909C-JVD-TRN-01713 | 036909C-JVD-TRN-01713 | IFR | 2019-06-05 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01713 |  | 2019-05-23 | 2
036909C-1024-TDS-0610-2455 | Mechanical Equipment Data Sheet - 10-E-2455 AB - LP Depropanizer Reboilers | B | 2019-03-20 | IFQ | OL1-2M03-2455 | ME | 2019-03-27 | 036909C-JVD-TRN-01179 | 036909C-JVD-TRN-01179 | IFR | 2019-04-11 | 2019-05-02 | TPSK-LSPA1-E-00190 May 09 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01179 |  | 2019-03-28 | 2
036909C-1024-TDS-0610-2445 | Mechanical Equipment Data Sheet - 10-E-2445 - HP Depropanizer Reboiler | B | 2019-03-30 | IFQ | OL1-2M03-2445 | ME | 2019-04-02 | 036909C-JVD-TRN-01231 | 036909C-JVD-TRN-01231 | IFR | 2019-04-17 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-01231 |  | 2019-04-03 | 2
036909C-1024-TDS-0610-2442 | Mechanical Equipment Data Sheet - 10-E-2442 - HP Deprop Reflux Chiller no 1 | A | 2019-01-14 | IFQ | OL1-2M03-2442 | ME | 2019-01-16 | 036909C-JVD-TRN-00662 | 036909C-JVD-TRN-00662, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-29 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00662 |  | 2019-01-16 | 2
036909C-1024-TDS-0610-2442 | Mechanical Equipment Data Sheet - 10-E-2442 - HP Deprop Reflux Chiller no 1 | B | 2019-03-30 | IFQ | OL1-2M03-2442 | ME | 2019-04-02 | 036909C-JVD-TRN-01231 | 036909C-JVD-TRN-01231 | IFR | 2019-04-17 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-01231 |  | 2019-04-03 | 2
036909C-1023-TDS-0610-2305 | Mechanical Equipment Data Sheet - 10-E-2305 - Caustic Tower Feed Heater | B | 2019-04-25 | IFQ | OL1-2M03-2305 | ME | 2019-04-26 | 036909C-JVD-TRN-01503 | 036909C-JVD-TRN-01503 | IFR | 2019-05-13 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01503 |  | 2019-04-29 | 2
036909C-1023-TDS-0610-2305 | Mechanical Equipment Data Sheet - 10-E-2305 - Caustic Tower Feed Heater | A | 2019-01-08 | IFQ | OL1-2M03-2305 | ME | 2019-01-10 | 036909C-JVD-TRN-00617 | 036909C-JVD-TRN-00617, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-23 | 2019-01-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-00617 |  | 2019-01-10 | 2
036909C-1021-TDS-0610-2145 | Mechanical Equipment Data Sheet - 10-E-2145 - Process Water Stripper Reboiler | A | 2019-01-17 | IFQ | OL1-2M03-2145 | ME | 2019-01-22 | 036909C-JVD-TRN-00684 | 036909C-JVD-TRN-00684, ROC-TPSK-CECO-T-00017 | IFR | 2019-02-04 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00684 |  | 2019-01-22 | 2
036909C-1021-TDS-0610-2125 | Mechanical Equipment Data Sheet - 10-E-2125 - Distillate Stripper Reboiler | B | 2019-04-03 | IFQ | OL1-2M03-2125 | ME | 2019-04-10 | 036909C-JVD-TRN-01302 | 036909C-JVD-TRN-01302 | IFR | 2019-04-25 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-ME-01302 |  | 2019-04-11 | 2
036909C-1056-DW-1514-5601 | Cause and Effect Diagram - Area 56 - Wastewater | B | 2019-04-30 | IFR | OL1-2G50-5601 | PE | 2019-05-01 | 036909C-JVD-TRN-01537 | 036909C-JVD-TRN-01537, ROC-TPSK-CECO-T-00074 | IFR | 2019-05-16 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01537 |  | 2019-05-02 | 2
036909C-1056-DW-1514-5601 | Cause and Effect Diagram - Area 56 - Wastewater | A | 2019-04-22 | IFR | OL1-2G50-5601 | PE | 2019-04-24 | 036909C-JVD-TRN-01462 | 036909C-JVD-TRN-01462, ROC-TPSK-CECO-T-00055 | IFR | 2019-05-09 |  | Transmitted | TPSK-LSPA1-T-PE-01462 |  | 2019-04-25 | 2
036909C-1056-SP-1513-5602 | Instrument Interlock Descriptions - Area 56 - Wastewater | A | 2019-04-30 | IFR | OL1-2G50-5602 | PE | 2019-05-01 | 036909C-JVD-TRN-01538 | 036909C-JVD-TRN-01538 | IFR | 2019-05-16 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01538 |  | 2019-05-02 | 2
036909C-1055-SP-1513-5502 | Instrument Interlock Descriptions Area 55 - Vent Gas and Flare System | A | 2019-04-29 | IFR | OL1-2G50-5502 | PE | 2019-04-30 | 036909C-JVD-TRN-01523 | 036909C-JVD-TRN-01523 | IFR | 2019-05-15 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01523 |  | 2019-05-02 | 2
036909C-1056-SP-1513-5601 | Complex Loop Narratives - Area 56 - Wastewater | A | 2019-05-01 | IFR | OL1-2I71-5601 | IE | 2019-05-01 | 036909C-JVD-TRN-01544 | 036909C-JVD-TRN-01544 | IFR | 2019-05-16 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-IE-01544 |  | 2019-05-02 | 2
036909C-1055-SP-1513-5501 | Complex Loop Narratives Area 55 - Vent Gas and Flare System | A | 2019-05-02 | IFR | OL1-2I71-5501 | IE | 2019-05-02 | 036909C-JVD-TRN-01564 | 036909C-JVD-TRN-01564 | IFR | 2019-05-17 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-IE-01564 |  | 2019-05-03 | 2
036909C-1021-SP-1513-2101 | Complex Loop Narratives Area 21 - Quench Water - Dilution Steam | A | 2019-03-25 | IFR | OL1-2I71-2101 | IE | 2019-03-25 | 036909C-JVD-TRN-01147 | 036909C-JVD-TRN-01147 | IFR | 2019-04-09 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-IE-01147 |  | 2019-03-26 | 2
036909C-1055-TDS-0610-5553 | Mechanical Equipment Data Sheet - 10-E-5552 - LPG Vaporizer - Superheater | B | 2019-04-17 | IFQ | OL1-2M03-5553 | ME | 2019-04-22 | 036909C-JVD-TRN-01436 | 036909C-JVD-TRN-01436 | IFR | 2019-05-07 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01436 |  | 2019-04-23 | 2
036909C-1055-TDS-0610-5553 | Mechanical Equipment Data Sheet - 10-E-5552 - LPG Vaporizer - Superheater | A | 2019-01-17 | IFQ | OL1-2M03-5553 | ME | 2019-01-22 | 036909C-JVD-TRN-00684 | 036909C-JVD-TRN-00684, ROC-TPSK-CECO-T-00018 | IFR | 2019-02-04 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00684 |  | 2019-01-22 | 2
036909C-1052-TDS-0610-5210 | Mechanical Equipment Data Sheet - 10-E-5210 - Pilot Gas Vaporizer | A | 2019-01-15 | IFQ | OL1-2M03-5210 | ME | 2019-01-17 | 036909C-JVD-TRN-00673 | 036909C-JVD-TRN-00673, ROC-TPSK-CECO-T-00018 | IFR | 2019-01-30 | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-ME-00673 |  | 2019-01-17 | 2
036909C-1052-TDS-0610-5210 | Mechanical Equipment Data Sheet - 10-E-5210 - Pilot Gas Vaporizer | B | 2019-04-16 | IFQ | OL1-2M03-5210 | ME | 2019-04-22 | 036909C-JVD-TRN-01436 | 036909C-JVD-TRN-01436 | IFR | 2019-05-07 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01436 |  | 2019-04-23 | 2
036909C-1027-SP-0810-2706 | Mechanical Equipment Data Sheet - GHU-1 Cold Separator | B | 2019-06-06 | IFQ | OL1-2M03-2706 | ME | 2019-06-10 | 036909C-JVD-TRN-01850 | 036909C-JVD-TRN-01850 | IFR | 2019-06-25 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-01850 |  | 2019-06-11 | 2
036909C-1025-SP-0810-2508 | Mechanical Equipment Data Sheet Demeth Prefrac Feed Separator No 3 | B | 2019-05-02 | IFQ | OL1-2M03-2508 | ME | 2019-05-06 | 036909C-JVD-TRN-01583 | 036909C-JVD-TRN-01583 | IFR | 2019-05-21 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01583 |  | 2019-05-07 | 2
036909C-1025-SP-0810-2506 | Mechanical Equipment Data Sheet Demeth Prefrac Feed Separator No 2 | B | 2019-05-02 | IFQ | OL1-2M03-2506 | ME | 2019-05-06 | 036909C-JVD-TRN-01583 | 036909C-JVD-TRN-01583 | IFR | 2019-05-21 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01583 |  | 2019-05-07 | 2
036909C-1028-SP-0810-2860 | Mechanical Equipment Data Sheet - C2R 1st Stage Suction Drum | B | 2019-05-27 | IFQ | OL1-2M03-2860 | ME | 2019-05-30 | 036909C-JVD-TRN-01783 | 036909C-JVD-TRN-01783 | IFR | 2019-06-14 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01783 |  | 2019-05-31 | 2
036909C-102A-DW-1742-0001-001 | Foundation And Elevation Of Concrete Structure For 10-STR-2A01 And 10-T-2120 | A | 2019-07-15 | IFR | OL1-2K31-1980 | CV | 2019-07-19 | 036909C-JVD-TRN-02203 | 036909C-JVD-TRN-02203 | IFA | 2019-08-05 |  | Transmitted | TPSK-LSPA1-T-CV-02203 |  | 2019-07-22 | 1
036909C-102D-DW-1743-0050-001 | Foundation For 10-TX-C-2550 | A | 2019-07-15 | IFR | OL1-2K31-0282 | CV | 2019-07-19 | 036909C-JVD-TRN-02203 | 036909C-JVD-TRN-02203 | IFA | 2019-08-05 |  | Transmitted | TPSK-LSPA1-T-CV-02203 |  | 2019-07-22 | 1
036909C-102A-CN-1732-0001 | Calculation Note For Foundation And Elevation Of 10-STR-2A01 | A | 2019-07-15 | IFR | OL1-2K14-0044 | CV | 2019-07-19 | 036909C-JVD-TRN-02202 | 036909C-JVD-TRN-02202 | IFA | 2019-08-05 |  | Transmitted | TPSK-LSPA1-T-CV-02202 |  | 2019-07-22 | 1
036909C-1000-MR-0811-0002 | Material Requisition For Shop Assembled CS Drums | A | 2019-03-08 | IFQ | OL1-2C13-132000 | PL | 2019-03-12 | 036909C-JVD-TRN-01032 | 036909C-JVD-TRN-01032 | IFR | 2019-03-27 | 2019-06-06 | R1-No Comments_TPSK-LSPA1-E-00246_21/06/2019 | TPSK-LSPA1-T-PL-01032 |  | 2019-03-13 | 2
036909C-1000-CN-1901-0001 | Fire Water Demand Calculation And Hydraulic Study For FW Network | A | 2019-03-06 | IFR | OL1-2L20-0001 | SE | 2019-03-07 | 036909C-JVD-TRN-01006 | 036909C-JVD-TRN-01006 | IFA | 2019-03-22 | 2019-04-09 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-SE-01006 |  | 2019-03-08 | 1
036909C-1059-PDS-2600-5914 | Process Equipment Datasheet - 10-PK-5914 - Phosphate Injection Pkg | C | 2019-03-14 | IFD | OL1-2G30-5914 | PE | 2019-03-14 | 036909C-JVD-TRN-01063 | 036909C-JVD-TRN-01063 | IFR | 2019-03-29 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01063 |  | 2019-03-15 | 2
036909C-1059-PDS-2600-5914 | Process Equipment Datasheet - 10-PK-5914 - Phosphate Injection Pkg | B | 2019-01-24 | IFD | OL1-2G30-5914 | PE | 2019-01-28 | 036909C-JVD-TRN-00739 | 036909C-JVD-TRN-00739 | IFI |  | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00739 |  | 2019-01-28 | 2
036909C-1059-PDS-2600-5912 | Process Equipment Datasheet - 10-PK-5912 - Neutralization Amine Inhibitor Inj Pkg | B | 2019-01-24 | IFD | OL1-2G30-5912 | PE | 2019-01-25 | 036909C-JVD-TRN-00727 | 036909C-JVD-TRN-00727 | IFI |  | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00727 |  | 2019-01-25 | 2
036909C-1059-PDS-2600-5912 | Process Equipment Datasheet - 10-PK-5912 - Neutralization Amine Inhibitor Inj Pkg | C | 2019-03-14 | IFD | OL1-2G30-5912 | PE | 2019-03-14 | 036909C-JVD-TRN-01063 | 036909C-JVD-TRN-01063 | IFR | 2019-03-29 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01063 |  | 2019-03-15 | 2
036909C-1059-PDS-2600-5910 | Process Equipment Datasheet - 10-PK-5910 - Oxygen Scavenger Inj Pkg | B | 2019-01-24 | IFD | OL1-2G30-5910 | PE | 2019-01-25 | 036909C-JVD-TRN-00727 | 036909C-JVD-TRN-00727 | IFI |  | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00727 |  | 2019-01-25 | 2
036909C-1059-PDS-2600-5910 | Process Equipment Datasheet - 10-PK-5910 - Oxygen Scavenger Inj Pkg | C | 2019-03-14 | IFD | OL1-2G30-5910 | PE | 2019-03-14 | 036909C-JVD-TRN-01063 | 036909C-JVD-TRN-01063 | IFR | 2019-03-29 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01063 |  | 2019-03-15 | 2
036909C-1053-PDS-2600-5394 | Process Equipment Datasheet - 10-PK-5394 - Dispersant Inj Pkg | B | 2019-02-15 | IFD | OL1-2G30-5394 | PE | 2019-02-19 | 036909C-JVD-TRN-00877 | 036909C-JVD-TRN-00877 | IFR | 2019-03-05 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00877 |  | 2019-02-19 | 2
036909C-1053-PDS-2600-5392 | Process Equipment Datasheet - 10-PK-5392 - Mild Steel Coor Inhibitor Inj Pkg | B | 2019-02-15 | IFD | OL1-2G30-5392 | PE | 2019-02-19 | 036909C-JVD-TRN-00890 | 036909C-JVD-TRN-00890 | IFR | 2019-03-06 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00890 |  | 2019-02-19 | 2
036909C-1053-PDS-2600-5390 | Process Equipment Datasheet - 10-PK-5390 - Copper Corrosion Inhibitor Inj Pkg | B | 2019-02-15 | IFD | OL1-2G30-5390 | PE | 2019-02-19 | 036909C-JVD-TRN-00877 | 036909C-JVD-TRN-00877 | IFR | 2019-03-05 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00877 |  | 2019-02-19 | 2
036909C-1000-MR-2630-0003 | Material Requisition For Molecular And HG Sieves | A | 2019-03-15 | IMP | OL1-2C18-263000 | PL | 2019-03-15 | 036909C-JVD-TRN-01076 | 036909C-JVD-TRN-01076 | IFR | 2019-04-01 | 2019-04-01 | R1-No comments | TPSK-LSPA1-T-PL-01076 |  | 2019-03-18 | 2
036909C-1000-MR-0610-0004 | Material Requisition For CS Clad SS And LAS S-T Heat Exchangers Requisition For Inquiry | A | 2019-02-15 | IFQ | OL1-2C13-274000 | PL | 2019-02-15 | 036909C-JVD-TRN-00870 | 036909C-JVD-TRN-00870 | IFR | 2019-03-04 | 2019-06-06 | R1-No comments | TPSK-LSPA1-T-PL-00870 |  | 2019-02-15 | 2
036909C-1000-PP-132 | TPSK KLOC Organization Chart | 2 | 2019-07-16 | IFI | OL1-2W92-0021 | PC | 2019-07-18 | 036909C-JVD-TRN-02182 | 036909C-JVD-TRN-02182 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PC-02182 |  | 2019-07-19 | 3
036909C-1027-PDS-0800-2705 | Process Equipment Datasheet - 10-D-2705 - GHU-1 Hot Separator | B | 2019-03-28 | IFD | OL1-2G30-2705 | PE | 2019-03-28 | 036909C-JVD-TRN-01188 | 036909C-JVD-TRN-01188 | IFR | 2019-04-12 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01188 |  | 2019-03-29 | 2
036909C-1023-PDS-0800-2316 | Process Equipment Datasheet - 10-D-2316 - Spent Caustic Degassing Drum | D | 2019-05-30 | IFD | OL1-2G30-2316 | PE | 2019-05-30 | 036909C-JVD-TRN-01785 | 036909C-JVD-TRN-01785 | IFR | 2019-06-14 | 2019-06-25 | R1-No comments | TPSK-LSPA1-T-PE-01785 | The client has commented the rev. C of this document in a pfd file so HOC can't reply to the comments in the excel file but just through the new revision | 2019-05-31 | 2
036909C-1027-PDS-0800-2724 | Process Equipment Datasheet - 10-D-2724 - Wash Oil Degrassing Drum | B | 2019-04-11 | IFD | OL1-2G30-2724 | PE | 2019-04-15 | 036909C-JVD-TRN-01354 | 036909C-JVD-TRN-01354 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-01354 |  | 2019-04-16 | 2
036909C-1055-PDS-0800-5515 | Process Equipment Datasheet - 10-D-5515 - Methanol Makeup Drum | B | 2019-03-13 | IFD | OL1-2G30-5515 | PE | 2019-03-14 | 036909C-JVD-TRN-01052 | 036909C-JVD-TRN-01052 | IFR | 2019-03-29 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-PE-01052 |  | 2019-03-15 | 2
036909C-1029-PDS-0800-2932 | Process Equipment Datasheet - 10-D-2930 - Methanol Drum | C | 2019-03-26 | IFD | OL1-2G30-2932 | PE | 2019-03-26 | 036909C-JVD-TRN-01162 | 036909C-JVD-TRN-01162 | IFR | 2019-04-10 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01162 |  | 2019-03-27 | 2
036909C-1055-PDS-0800-5552 | Process Equipment Datasheet - 10-D-5552 - LPG Storage Drum | D | 2019-05-15 | IFD | OL1-2G30-5552 | PE | 2019-05-16 | 036909C-JVD-TRN-01677 | 036909C-JVD-TRN-01677 | IFR | 2019-05-31 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01677 |  | 2019-05-17 | 2
036909C-1028-PDS-0800-2815 | Process Equipment Datasheet - 10-D-2815 - C3R Drain Drum | B | 2019-01-09 | IFD | OL1-2G30-2815 | PE | 2019-01-11 | 036909C-JVD-TRN-00633 | 036909C-JVD-TRN-00633 | IFI |  | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00633 |  | 2019-01-11 | 2
036909C-1026-PDS-0800-2632 | Process Equipment Datasheet - 10-D-2630 - Secondary Deeth Reflux Drum | B | 2018-11-29 | IFD | OL1-2G30-2632 | PE | 2019-01-11 | 036909C-JVD-TRN-00633 | 036909C-JVD-TRN-00633 | IFI |  | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00633 |  | 2019-01-11 | 2
036909C-1026-PDS-0800-2644 | Process Equipment Datasheet - 10-D-2645 - C3 Tower Reboiler Cond Pot | C | 2019-02-26 | IFD | OL1-2G30-2644 | PE | 2019-02-26 | 036909C-JVD-TRN-00938 | 036909C-JVD-TRN-00938 | IFR | 2019-03-13 | 2019-03-14 | R1-No comments | TPSK-LSPA1-T-PE-00938 |  | 2019-02-27 | 2
036909C-1051-PDS-0800-5112 | Process Equipment Datasheet - 10-D-5112 - Suspect Condensate Flash Drum | B | 2018-12-12 | IFD | OL1-2G30-5112 | PE | 2018-12-14 | 036909C-JVD-TRN-00498 | 036909C-JVD-TRN-00498 | IFI |  | 2019-01-10 | R1-No comments | TPSK-LSPA1-T-PE-00498 |  | 2018-12-14 | 2
036909C-1027-PDS-0800-2762 | Process Equipment Datasheet - 10-D-2760 - C4-C5 Hydrog Recycle Drum | B | 2019-03-06 | IFD | OL1-2G30-2762 | PE | 2019-03-11 | 036909C-JVD-TRN-01023 | 036909C-JVD-TRN-01023 | IFR | 2019-03-26 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-PE-01023 |  | 2019-03-12 | 2
036909C-1055-PDS-0800-5520 | Process Equipment Datasheet - 10-D-5520 - Vent Collection Drum | B | 2019-01-29 | IFD | OL1-2G30-5520 | PE | 2019-02-15 | 036909C-JVD-TRN-00856 | 036909C-JVD-TRN-00856 | IFR | 2019-03-01 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00856 |  | 2019-02-15 | 2
036909C-1024-PDS-0800-2435 | Process Equipment Datasheet - 10-D-2435 - Regen Gas Separator | B | 2019-01-24 | IFD | OL1-2G30-2435 | PE | 2019-01-25 | 036909C-JVD-TRN-00725 | 036909C-JVD-TRN-00725 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00725 |  | 2019-01-25 | 2
036909C-1020-PDS-0800-2090 | Process Equipment Datasheet - 10-D-2090 - Quench Oil Drain Drum | B | 2019-02-28 | IFD | OL1-2G30-2090 | PE | 2019-03-01 | 036909C-JVD-TRN-00964 | 036909C-JVD-TRN-00964 | IFR | 2019-03-16 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-PE-00964 |  | 2019-03-04 | 2
036909C-1021-PDS-0800-2110 | Process Equipment Datasheet - 10-D-2110 - Interception Drum | C | 2019-02-28 | IFD | OL1-2G30-2110 | PE | 2019-03-01 | 036909C-JVD-TRN-00964 | 036909C-JVD-TRN-00964 | IFR | 2019-03-16 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-PE-00964 |  | 2019-03-04 | 2
036909C-1021-PDS-0800-2190 | Process Equipment Datasheet - 10-D-2190 - Quench Water Drain Drum | B | 2019-02-28 | IFD | OL1-2G30-2190 | PE | 2019-03-01 | 036909C-JVD-TRN-00964 | 036909C-JVD-TRN-00964 | IFR | 2019-03-16 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-PE-00964 |  | 2019-03-04 | 2
036909C-1022-PDS-0800-2245 | Process Equipment Datasheet - 10-D-2245 - CG 4th Stage Discharge Drum | B | 2018-12-10 | IFD | OL1-2G30-2245 | PE | 2018-12-13 | 036909C-JVD-TRN-00480 | 036909C-JVD-TRN-00480 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00480 |  | 2018-12-13 | 2
036909C-1000-JSS-6300-0008 | Job Specification For Axens Standard Material Specifications For Wet H2S Service | A | 2019-02-21 | IFR | OL1-2R03-0009 | ME | 2019-02-21 | 036909C-JVD-TRN-00909 | 036909C-JVD-TRN-00909 | IFR | 2019-03-08 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00909 |  | 2019-02-22 | 2
036909C-1027-TDS-0610-2755 | Mechanical Equipment Data Sheet - 10-E-2755 - C4 C5 Hydrog Start-Up Heater | 0 | 2019-06-25 | IFP | OL1-2M03-2755 | ME | 2019-07-17 | 036909C-JVD-TRN-02175 | 036909C-JVD-TRN-02175 | IFR | 2019-08-01 |  | Transmitted | TPSK-LSPA1-T-ME-02175 |  | 2019-07-17 | 2
036909C-1000-PP-204 | SIL Study Procedure | 0 | 2019-03-26 | IMP | OL1-2S92-0007 | ES | 2019-03-28 | 036909C-JVD-TRN-01190 | 036909C-JVD-TRN-01190 | IFR | 2019-04-12 | 2019-04-22 | R2-Comments as noted | TPSK-LSAP1-T-ES-01190 |  | 2019-03-29 | 2
036909C-1000-PP-204 | SIL Study Procedure | 1 | 2019-04-29 | IMP | OL1-2S92-0007 | ES | 2019-05-06 | 036909C-JVD-TRN-01572 | 036909C-JVD-TRN-01572 | IFR | 2019-05-21 | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-ES-01572 |  | 2019-05-07 | 2
036909C-1026-TDS-0610-2635 | Mechanical Equipment Data Sheet - 10-E-2635 - Secondary Deeth Reboiler | B | 2019-04-16 | IFQ | OL1-2M03-2635 | ME | 2019-04-30 | 036909C-JVD-TRN-01532 | 036909C-JVD-TRN-01532 | IFR | 2019-05-15 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01532 |  | 2019-05-02 | 2
036909C-1024-TDS-0610-2430 | Mechanical Equipment Data Sheet - 10-E-2430 - Regen Gas Feed Heater | A | 2019-01-22 | IFQ | OL1-2M03-2430 | ME | 2019-01-28 | 036909C-JVD-TRN-00740 | 036909C-JVD-TRN-00740, ROC-TPSK-CECO-T-00017 | IFR | 2019-02-11 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00740 |  | 2019-01-28 | 2
036909C-1000-MR-2630-0005 | Material Requisition For Molecular Sieves | A | 2019-03-12 | IMP | OL1-2C18-265000 | PL | 2019-03-15 | 036909C-JVD-TRN-01077 | 036909C-JVD-TRN-01077 | IFR | 2019-04-01 | 2019-04-01 | R1-No comments | TPSK-LSPA1-T-PL-01077 |  | 2019-03-18 | 2
036909C-1051-TDS-0610-5113 | Mechanical Equipment Data Sheet - 10-E-5113 - Foul Condensate Cooler | B | 2019-04-26 | IFQ | OL1-2M03-5113 | ME | 2019-05-01 | 036909C-JVD-TRN-01545 | 036909C-JVD-TRN-01545 | IFR | 2019-05-16 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01545 |  | 2019-05-02 | 2
036909C-1028-TDS-0610-2853 | Mechanical Equipment Data Sheet - 10-E-2853 - C2R Desuperheater No 2 | B | 2019-04-10 | IFQ | OL1-2M03-2853 | ME | 2019-04-10 | 036909C-JVD-TRN-01313 | 036909C-JVD-TRN-01313 | IFR | 2019-04-25 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-ME -01313 |  | 2019-04-11 | 2
036909C-1026-TDS-0610-2636 | Mechanical Equipment Data Sheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | B | 2019-04-02 | IFQ | OL1-2M03-2636 | ME | 2019-04-10 | 036909C-JVD-TRN-01313 | 036909C-JVD-TRN-01313 | IFR | 2019-04-25 |  | Transmitted | TPSK-LSPA1-T-ME -01313 |  | 2019-04-11 | 2
036909C-1029-PDS-2600-2912 | Process Equipment Datasheet - 10-PK-2912 - Caustic Tower Anti-Foulant Inj Pkg | B | 2019-01-31 | IFD | OL1-2G30-2912 | PE | 2019-01-31 | 036909C-JVD-TRN-00780 | 036909C-JVD-TRN-00780 | IFI |  | 2019-02-28 | R1-No comments | TPSK-LSPA1-T-PE-00780 |  | 2019-02-01 | 2
036909C-1000-JSS-1530-0002 | Job Supply Specification For Safety Supervisory System - Ex Doc Client Ref OL1-2T92-0002 | B | 2019-02-26 | IFR | OL1-2T01-0002 | EE | 2019-03-07 | 036909C-JVD-TRN-00985 | 036909C-JVD-TRN-00985, ROC-TPSK-CECO-T-00003 | IFA | 2019-03-22 | 2019-03-21 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-00985 | Ex Doc Client Ref OL1-2T92-0002 | 2019-03-06 | 1
036909C-1000-JSS-1530-0002 | Job Supply Specification For Safety Supervisory System - For Next Revision See Document OL1-2T01-0002 | A | 2018-12-21 | IFR | OL1-2T01-0002 | EE | 2019-01-03 | 036909C-JVD-TRN-00577 | 036909C-JVD-TRN-00577 | IFR | 2019-01-17 | 2019-01-23 | R2-Comments as noted | TPSK-LSPA1-T-EE-00577 | For Next Revision See Document OL1-2T01-0002 | 2019-01-03 | 2
036909C-1000-JSD-1530-0002 | Safety Supervisory System | 0 | 2019-03-04 | IMP | OL1-2R05-0019 | EE | 2019-03-07 | 036909C-JVD-TRN-00987 | 036909C-JVD-TRN-00987, ROC-TPSK-CECO-T-00003 | IFR | 2019-03-22 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-EE-00987 |  | 2019-03-06 | 2
036909C-1051-SP-0836-5127 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51021 - PV-5143 Outlet | A | 2019-07-12 | IFQ | OL1-2M03-5127 | ME | 2019-07-12 | 036909C-JVD-TRN-02144 | 036909C-JVD-TRN-02144 | IFR | 2019-07-26 |  | Transmitted | TPSK-LSPA1-T-ME-02144 |  | 2019-07-15 | 2
036909C-1012-MR-0155-2018 | Material Requisition for Furnace Steam Drums - Ex Doc Client Ref OL1-2M55-2018 | 1 | 2019-03-08 | IFP | OL1-2C13-305000 | PL | 2019-03-25 | 036909C-JVD-TRN-01139 | 036909C-JVD-TRN-01139 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01139 | Ex Doc Client Ref OL1-2M55-2018 | 2019-03-26 | 3
036909C-1012-MR-0154-2003 | Material Requisition for Quench Exchangers - For Next Revision See Document OL1-2C13-140000 | 0 | 2018-12-07 | IFP | OL1-2C13-140000 | ME | 2018-12-10 | 036909C-JVD-TRN-00466 | 036909C-JVD-TRN-00466 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00466 | For Next Revision See Document OL1-2C13-140000 | 2018-12-10 | 3
036909C-1012-PDS-1390-1202 | Piping Specialty Item – Datasheet T-Type Filter – Crossover Line SRT-12001-16001 | B | 2019-07-15 | IFD | OL1-2P03-1202 | MP | 2019-07-16 | 036909C-JVD-TRN-02162 | 036909C-JVD-TRN-02162 | IFR | 2019-07-31 |  | Transmitted | TPSK-LSPA1-T-MP-02162 |  | 2019-07-17 | 2
036909C-1012-MR-0155-2018 | Material Requisition for Furnace Steam Drums - For Next Rev See OL1-2C13-305000 | 0 | 2018-12-12 | IFP | OL1-2C13-305000 | ME | 2018-12-17 | 036909C-JVD-TRN-00518 | 036909C-JVD-TRN-00518 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00518 | For Next Rev See OL1-2C13-305000 | 2018-12-17 | 3
036909C-1012-MR-0122-2004 | Material Requisition for Radiant Coil Assemblies - For Next Rev See OL1-2C13-300000 | 0 | 2018-12-11 | IFP | OL1-2C13-300000 | ME | 2018-12-14 | 036909C-JVD-TRN-00499 | 036909C-JVD-TRN-00499 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00499 | For Next Rev See OL1-2C13-300000 | 2018-12-14 | 3
036909C-1012-MR-0127-2002 | Material Requisition for Furnace Convection Fittings - For Next Rev See OL1-2C13-304000 | 0 | 2018-12-19 | IFP | OL1-2C13-304000 | ME | 2019-01-07 | 036909C-JVD-TRN-00592 | 036909C-JVD-TRN-00592 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00592 | For Next Rev See OL1-2C13-304000 | 2019-01-07 | 3
036909C-1012-MR-0125-2007 | Material Requisition for Cast Intermediate Tube Supports - Ex Doc Client Ref OL1-2M55-2007 | 1 | 2019-02-11 | IFP | OL1-2C13-302000 | PL | 2019-03-25 | 036909C-JVD-TRN-01139 | 036909C-JVD-TRN-01139 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01139 | Ex Doc Client Ref OL1-2M55-2007 | 2019-03-26 | 3
036909C-1012-MR-0122-2004 | Material Requisition for Radiant Coil Assemblies - Ex Doc Client Ref OL1-2M55-2004 | 1 | 2019-03-08 | IFP | OL1-2C13-300000 | PL | 2019-03-25 | 036909C-JVD-TRN-01139 | 036909C-JVD-TRN-01139 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01139 | Ex Doc Client Ref OL1-2M55-2004 | 2019-03-26 | 3
036909C-1011-PDS-1390-1102 | Piping Specialty Item – Datasheet-T-Type Filter – Crossover Line SRT-11001 | B | 2019-07-15 | IFD | OL1-2P03-1102 | MP | 2019-07-16 | 036909C-JVD-TRN-02162 | 036909C-JVD-TRN-02162 | IFR | 2019-07-31 |  | Transmitted | TPSK-LSPA1-T-MP-02162 |  | 2019-07-17 | 2
036909C-1012-MR-0125-2007 | Material Requisition for Cast Intermediate Tube Supports - For Next Revision see Doc. n. OL1-2C13-302000 | 0 | 2018-12-18 | IFP | OL1-2C13-302000 | ME | 2018-12-20 | 036909C-JVD-TRN-00542 | 036909C-JVD-TRN-00542 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00542 | For Next Revision see Doc. n. OL1-2C13-302000 | 2018-12-20 | 3
036909C-1000-DL-1031-0001 | Deviation List for Recycle Gas Compressor | D | 2019-07-09 | IFA | OL1-2C40-403000 | PL | 2019-07-09 | 036909C-JVD-TRN-02104 | 036909C-JVD-TRN-02104 | IFA | 2019-07-23 |  | Transmitted | TPSK-LSPA1-T-PL-02104 |  | 2019-07-10 | 1
036909C-1000-JSS-1530-0001 | Job Supply Specification For Intercom Paging Audible Alarm System - For Next Revision See Document OL1-2T01-0001 | A | 2018-12-21 | IFR | OL1-2T01-0001 | EE | 2019-01-03 | 036909C-JVD-TRN-00577 | 036909C-JVD-TRN-00577 | IFR | 2019-01-17 | 2019-01-23 | R2-Comments as noted | TPSK-LSPA1-T-EE-00577 | For Next Revision See Document OL1-2T01-0001 | 2019-01-03 | 2
036909C-1000-MS-1500-0051 | Job Construction Specification For Instrument Installation | A | 2019-06-18 | IFR | OL1-2Q92-0015 | QM | 2019-06-24 | 036909C-JVD-TRN-01973 | 036909C-JVD-TRN-01973 | IFR | 2019-07-09 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-QM-01973 |  | 2019-06-25 | 2
036909C-100P-DW-1741-0002-012 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Steel Bracings Details | A | 2019-05-27 | IFR | OL1-2K31-1031 | CV | 2019-05-30 | 036909C-JVD-TRN-01771 | 036909C-JVD-TRN-01771 | IFA | 2019-06-14 | 2019-07-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01771 |  | 2019-05-31 | 1
036909C-100P-CN-1731-0001 | Calculation Note For Precast Concrete and Foundations For Main Pipe Rack 10-PRK-0P01 | A | 2019-05-21 | IFR | OL1-2K14-0001 | CV | 2019-05-27 | 036909C-JVD-TRN-01749 | 036909C-JVD-TRN-01749 | IFA | 2019-06-11 | 2019-07-11 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01749 |  | 2019-05-28 | 1
036909C-100P-CN-1831-0001 | Calculation Note For Steel Pipe Rack 10-PRK-0P01 | A | 2019-05-21 | IFR | OL1-2K15-0001 | CV | 2019-05-27 | 036909C-JVD-TRN-01749 | 036909C-JVD-TRN-01749 | IFA | 2019-06-11 | 2019-07-11 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01749 |  | 2019-05-28 | 1
036909C-1025-SP-0510-2510 | Mechanical Equipment Data Sheet for Demethanizer Prefractionator & Reflux Drum | 1 | 2019-06-21 | IFP | OL1-2M03-2510 | ME | 2019-06-25 | 036909C-JVD-TRN-01986 | 036909C-JVD-TRN-01988, 036909C-JVD-TRN-01986 | IFA | 2019-07-10 | 2019-07-16 | R1-No comments | TPSK-LSPA1-T-ME-01986 |  | 2019-06-26 | 2
036909C-105U-DW-1950-5014 | FIRE & GAS DEVICES LAYOUT -ZONE 5U - UTILITIES | B | 2019-04-26 | IFR | OL1-2F40-5014 | FF | 2019-04-30 | 036909C-JVD-TRN-01518 | 036909C-JVD-TRN-01518, KLOC-TPSK-VSAFE-T-00007, KLOC-TPSK-CECO-T-00008 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-FF-01518 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5708 | P&ID - TYPICAL INSTALLATION OF FIRE PROTECTION EQUIPMENT | A | 2019-04-26 | IFR | OL1-2L40-5708 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-105F-DW-1950-5016 | FIRE & GAS DEVICES LAYOUT ZONE 5F - HP & POLYOLEFINS FLARES UNIT | B | 2019-04-26 | IFR | OL1-2F40-5016 | FF | 2019-04-30 | 036909C-JVD-TRN-01518 | 036909C-JVD-TRN-01518, KLOC-TPSK-VSAFE-T-00007, KLOC-TPSK-CECO-T-00008 | IFR | 2019-05-14 | 2019-05-31 | R2-Comments as noted | TPSK-LSPA1-T-FF-01518 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5709 | P&ID - AUTOMATIC PNEUMATIC & ELECTRIC OPERATED DELUGE SYSTEM | A | 2019-04-26 | IFR | OL1-2L40-5709 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5711 | P&ID - MANUAL ELECTRIC OPERATED DELUGE SYSTEM | A | 2019-04-26 | IFR | OL1-2L40-5711 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-105T-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5T COOLING WATER UNIT | B | 2019-04-25 | IFR | OL1-2F30-0003 | FF | 2019-04-30 | 036909C-JVD-TRN-01519 | 036909C-JVD-TRN-01519, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-05-14 |  | Transmitted | TPSK-LSPA1-T-FF-01519 |  | 2019-05-02 | 2
036909C-105U-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5U UTILITIES | B | 2019-04-25 | IFR | OL1-2F30-0005 | FF | 2019-04-30 | 036909C-JVD-TRN-01519 | 036909C-JVD-TRN-01519, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-05-14 |  | Transmitted | TPSK-LSPA1-T-FF-01519 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5710 | P&ID - AUTOMATIC ELECTRIC OPERATED DELUGE SYSTEM | A | 2019-04-26 | IFR | OL1-2L40-5710 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-105T-DW-1950-5013 | FIRE & GAS DEVICES LAYOUT -ZONE 5T - COOLING WATER UNIT | B | 2019-04-26 | IFR | OL1-2F40-5013 | FF | 2019-04-30 | 036909C-JVD-TRN-01518 | 036909C-JVD-TRN-01518, KLOC-TPSK-VSAFE-T-00007, KLOC-TPSK-CECO-T-00008 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-FF-01518 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5712 | P&ID - PRE-ACTION DOUBLE INTERLOCK SPRINKLER SYSTEM | A | 2019-04-26 | IFR | OL1-2L40-5712 | SE | 2019-04-30 | 036909C-JVD-TRN-01520 | 036909C-JVD-TRN-01520 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-105W-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5W WASTE WATER TREATMENT | B | 2019-04-25 | IFR | OL1-2F30-0004 | FF | 2019-04-30 | 036909C-JVD-TRN-01519 | 036909C-JVD-TRN-01519, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-05-14 |  | Transmitted | TPSK-LSPA1-T-FF-01519 |  | 2019-05-02 | 2
036909C-103A-DW-1950-5012 | FIRE & GAS DEVICES LAYOUT - ZONE 3A - BUTADIENE EXTRACTION UNIT | B | 2019-04-26 | IFR | OL1-2F40-5012 | FF | 2019-04-30 | 036909C-JVD-TRN-01518 | 036909C-JVD-TRN-01518, KLOC-TPSK-VSAFE-T-00007, KLOC-TPSK-CECO-T-00008 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-FF-01518 |  | 2019-05-02 | 2
036909C-102E-DW-1950-5011 | FIRE & GAS DEVICES LAYOUT - ZONE 2E - CRACKED GAS COMPRESSOR | B | 2019-04-26 | IFR | OL1-2F40-5011 | FF | 2019-04-30 | 036909C-JVD-TRN-01518 | 036909C-JVD-TRN-01518, KLOC-TPSK-VSAFE-T-00007, KLOC-TPSK-CECO-T-00008 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-FF-01518 |  | 2019-05-02 | 2
036909C-103S-DW-1950-5005 | FIRE & GAS DEVICES LAYOUT - ZONE 3S - ELECTRICAL SUBSTATION C & FAR C | B | 2019-04-26 | IFR | OL1-2F40-5005 | FF | 2019-04-30 | 036909C-JVD-TRN-01518 | 036909C-JVD-TRN-01518, KLOC-TPSK-VSAFE-T-00007, KLOC-TPSK-CECO-T-00008 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-FF-01518 |  | 2019-05-02 | 2
036909C-102E-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2E CRACKED GAS COMPRESSOR | B | 2019-04-25 | IFR | OL1-2F30-0013 | FF | 2019-04-30 | 036909C-JVD-TRN-01519 | 036909C-JVD-TRN-01519, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-05-14 |  | Transmitted | TPSK-LSPA1-T-FF-01519 |  | 2019-05-02 | 2
036909C-103A-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 3A BUTADIENE EXTRACTION UNIT | B | 2019-04-25 | IFR | OL1-2F30-0014 | FF | 2019-04-30 | 036909C-JVD-TRN-01519 | 036909C-JVD-TRN-01519, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-05-14 |  | Transmitted | TPSK-LSPA1-T-FF-01519 |  | 2019-05-02 | 2
036909C-102D-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2D PROCESS COLD COMPRESSOR | B | 2019-04-25 | IFR | OL1-2F30-0012 | FF | 2019-04-30 | 036909C-JVD-TRN-01519 | 036909C-JVD-TRN-01519, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-05-14 |  | Transmitted | TPSK-LSPA1-T-FF-01519 |  | 2019-05-02 | 2
036909C-100S-DW-1950-5004 | FIRE & GAS DEVICES LAYOUT -ZONE 0S - ELECTRICAL SUBSTATION E & FAR E | B | 2019-04-26 | IFR | OL1-2F40-5004 | FF | 2019-04-30 | 036909C-JVD-TRN-01518 | 036909C-JVD-TRN-01518, KLOC-TPSK-VSAFE-T-00007, KLOC-TPSK-CECO-T-00008 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-FF-01518 |  | 2019-05-02 | 2
036909C-101B-DW-1950-5006 | FIRE & GAS DEVICES LAYOUT - ZONE 1B - FURNACES UTILITIES | B | 2019-04-26 | IFR | OL1-2F40-5006 | FF | 2019-04-30 | 036909C-JVD-TRN-01518 | 036909C-JVD-TRN-01518, KLOC-TPSK-VSAFE-T-00007, KLOC-TPSK-CECO-T-00008 | IFR | 2019-05-14 | 2019-06-16 | R1-No comments | TPSK-LSPA1-T-FF-01518 |  | 2019-05-02 | 2
036909C-102C-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2C HOT FRACTIONATION/GHU UNIT | B | 2019-04-25 | IFR | OL1-2F30-0015 | FF | 2019-04-30 | 036909C-JVD-TRN-01519 | 036909C-JVD-TRN-01519, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-05-14 |  | Transmitted | TPSK-LSPA1-T-FF-01519 |  | 2019-05-02 | 2
036909C-102B-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2B C3 HYDROGENATION | B | 2019-04-25 | IFR | OL1-2F30-0011 | FF | 2019-04-30 | 036909C-JVD-TRN-01519 | 036909C-JVD-TRN-01519, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-05-14 |  | Transmitted | TPSK-LSPA1-T-FF-01519 |  | 2019-05-02 | 2
036909C-101B-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 1B FURNACES UTILITIES | B | 2019-04-25 | IFR | OL1-2F30-0009 | FF | 2019-04-30 | 036909C-JVD-TRN-01519 | 036909C-JVD-TRN-01519, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-05-14 |  | Transmitted | TPSK-LSPA1-T-FF-01519 |  | 2019-05-02 | 2
036909C-102B-DW-1950-5008 | FIRE & GAS DEVICES LAYOUT - ZONE 2B - C3 HYDROGENERATION | B | 2019-04-26 | IFR | OL1-2F40-5008 | FF | 2019-04-30 | 036909C-JVD-TRN-01518 | 036909C-JVD-TRN-01518, KLOC-TPSK-VSAFE-T-00007, KLOC-TPSK-CECO-T-00008 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-FF-01518 |  | 2019-05-02 | 2
036909C-102C-DW-1950-5009 | FIRE & GAS DEVICES LAYOUT - ZONE 2C - HOT FRACTIONATION / GHU UNIT | B | 2019-04-26 | IFR | OL1-2F40-5009 | FF | 2019-04-30 | 036909C-JVD-TRN-01518 | 036909C-JVD-TRN-01518, KLOC-TPSK-VSAFE-T-00007, KLOC-TPSK-CECO-T-00008 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-FF-01518 |  | 2019-05-02 | 2
036909C-102A-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2A QUENCH | B | 2019-04-25 | IFR | OL1-2F30-0010 | FF | 2019-04-30 | 036909C-JVD-TRN-01519 | 036909C-JVD-TRN-01519, KLOC-TPSK-VSAFE-T-00007 | IFR | 2019-05-14 |  | Transmitted | TPSK-LSPA1-T-FF-01519 |  | 2019-05-02 | 2
036909C-102A-DW-1950-5007 | FIRE & GAS DEVICES LAYOUT - ZONE 2A - QUENCH | B | 2019-04-26 | IFR | OL1-2F40-5007 | FF | 2019-04-30 | 036909C-JVD-TRN-01518 | 036909C-JVD-TRN-01518, KLOC-TPSK-VSAFE-T-00007, KLOC-TPSK-CECO-T-00008 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-FF-01518 |  | 2019-05-02 | 2
036909C-100M-DW-1950-5002 | FIRE & GAS DEVICES LAYOUT - ZONE 0M - METERING STATION | B | 2019-04-26 | IFR | OL1-2F40-5002 | FF | 2019-04-30 | 036909C-JVD-TRN-01518 | 036909C-JVD-TRN-01518, KLOC-TPSK-VSAFE-T-00007, KLOC-TPSK-CECO-T-00008 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-FF-01518 |  | 2019-05-02 | 2
036909C-100P-DW-1950-5003 | FIRE & GAS DEVICES LAYOUT - ZONE 0P - MAIN PIPE RACK | B | 2019-04-26 | IFR | OL1-2F40-5003 | FF | 2019-04-30 | 036909C-JVD-TRN-01518 | 036909C-JVD-TRN-01518, KLOC-TPSK-VSAFE-T-00007, KLOC-TPSK-CECO-T-00008 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-FF-01518 |  | 2019-05-02 | 2
036909C-1020-TDS-0610-2015 | Mechanical Equipment Data Sheet - 10-E-2008 - LS2 Steam Generators | B | 2019-03-29 | IFQ | OL1-2M03-2015 | ME | 2019-03-29 | 036909C-JVD-TRN-01205 | 036909C-JVD-TRN-01205 | IFR | 2019-04-15 | 2019-05-02 | TPSK-LSPA1-E-00190 May 09 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01205 |  | 2019-04-01 | 2
036909C-1010-TDS-0610-1006 | Mechanical Equipment Data Sheet - 10-E-1006 - LPG Feed Steam Heater | B | 2019-04-15 | IFQ | OL1-2M03-1006 | ME | 2019-04-15 | 036909C-JVD-TRN-01362 | 036909C-JVD-TRN-01362 | IFR | 2019-04-30 |  | Transmitted | TPSK-LSPA1-T-ME-01362 |  | 2019-04-16 | 2
036909C-1010-TDS-0610-1006 | Mechanical Equipment Data Sheet - 10-E-1006 - LPG Feed Steam Heater | A | 2019-03-07 | IFQ | OL1-2M03-1006 | ME | 2019-03-19 | 036909C-JVD-TRN-01095 | 036909C-JVD-TRN-01095 | IFR | 2019-04-03 | 2019-04-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-01095 |  | 2019-03-20 | 2
036909C-1010-TDS-0610-1003 | Mechanical Equipment Data Sheet - 10-E-1001 - LPG Steam Vaporizer | B | 2019-02-25 | IFQ | OL1-2M03-1003 | ME | 2019-02-27 | 036909C-JVD-TRN-00946 | 036909C-JVD-TRN-00946, ROC-TPSK-CECO-T-00017 | IFR | 2019-03-14 | 2019-03-25 | TPSK-LSPA1-E-00154 April 26 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-00946 |  | 2019-02-28 | 2
036909C-1010-TDS-0610-1002 | Mechanical Equipment Data Sheet - 10-E-1000 A-B - LPG Vaporizer | B | 2019-05-15 | IFQ | OL1-2M03-1002 | ME | 2019-05-16 | 036909C-JVD-TRN-01685 | 036909C-JVD-TRN-01685 | IFR | 2019-05-31 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01685 |  | 2019-05-17 | 2
036909C-1000-DL-1031-0001 | Deviation List for Recycle Gas Compressor | C | 2019-06-19 | IFA | OL1-2C40-403000 | PL | 2019-06-20 | 036909C-JVD-TRN-01942 | 036909C-JVD-TRN-01942 | IFA | 2019-07-04 |  | Transmitted | TPSK-LSPA1-T-PL-01942 |  | 2019-06-20 | 1
036909C-1000-DL-1031-0001 | Deviation List for Recycle Gas Compressor | B | 2019-05-24 | IFA | OL1-2C40-403000 | PL | 2019-05-27 | 036909C-JVD-TRN-01745 | 036909C-JVD-TRN-01745 | IFA | 2019-06-10 | 2019-06-11 | R2-Comments as noted | TPSK-LSPA1-T-PL-01745 |  | 2019-05-28 | 1
036909C-1051-SP-0810-5150 | Mechanical Equipment Data Sheet - Continuous Blow Down Flash Drum | B | 2019-05-29 | IFQ | OL1-2M03-5150 | ME | 2019-05-30 | 036909C-JVD-TRN-01780 | 036909C-JVD-TRN-01780 | IFR | 2019-06-14 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01780 |  | 2019-05-31 | 2
036909C-1026-SP-0810-2644 | Mechanical Equipment Data Sheet - C3 Tower Reboilder Cond Pot | B | 2019-05-28 | IFQ | OL1-2M03-2644 | ME | 2019-05-28 | 036909C-JVD-TRN-01760 | 036909C-JVD-TRN-01760 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-01760 |  | 2019-05-29 | 2
036909C-1027-TDS-0610-2755 | Mechanical Equipment Data Sheet - 10-E-2755 - C4 - C5 Hydrog Start-Up Heater | B | 2019-04-24 | IFQ | OL1-2M03-2755 | ME | 2019-04-29 | 036909C-JVD-TRN-01514 | 036909C-JVD-TRN-01514 | IFR | 2019-05-14 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01514 |  | 2019-04-30 | 2
036909C-1027-TDS-0610-2755 | Mechanical Equipment Data Sheet - 10-E-2755 - C4 -C5 Hydrog Start-Up Heater | A | 2019-03-15 | IFQ | OL1-2M03-2755 | ME | 2019-03-19 | 036909C-JVD-TRN-01095 | 036909C-JVD-TRN-01095 | IFR | 2019-04-03 | 2019-04-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-01095 |  | 2019-03-20 | 2
036909C-1028-TDS-0610-2858 | Mechanical Equipment Data Sheet - 10-E-2858 - HP Ethylene Product Superheater | A | 2019-01-17 | IFQ | OL1-2M03-2858 | ME | 2019-01-22 | 036909C-JVD-TRN-00684 | 036909C-JVD-TRN-00684, ROC-TPSK-CECO-T-00018 | IFR | 2019-02-04 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00684 |  | 2019-01-22 | 2
036909C-1028-TDS-0610-2858 | Mechanical Equipment Data Sheet - 10-E-2858 - HP Ethylene Product Superheater | B | 2019-04-03 | IFQ | OL1-2M03-2858 | ME | 2019-04-04 | 036909C-JVD-TRN-01256 | 036909C-JVD-TRN-01256 | IFR | 2019-04-19 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-ME-01256 |  | 2019-04-05 | 2
036909C-1028-TDS-0610-2806 | Mechanical Equipment Data Sheet - 10-E-2805A-C - C3 Refrig Condensers | B | 2019-03-19 | IFQ | OL1-2M03-2806 | ME | 2019-03-21 | 036909C-JVD-TRN-01123 | 036909C-JVD-TRN-01123, ROC-TPSK-CECO-T-00018 | IFR | 2019-04-05 | 2019-04-11 | R1-No comments | TPSK-LSPA1-T-ME-01123 |  | 2019-03-22 | 2
036909C-1027-TDS-0610-2707 | Mechanical Equipment Data Sheet - 10-E-2706 - GHU-1 Cooler | A | 2019-02-21 | IFQ | OL1-2M03-2707 | ME | 2019-02-25 | 036909C-JVD-TRN-00927 | 036909C-JVD-TRN-00927, ROC-TPSK-CECO-T-00018 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00927 |  | 2019-02-26 | 2
036909C-1026-TDS-0610-2665 | Mechanical Equipment Data Sheet - 10-E-2665 AB - Debutanizer Reboilers | B | 2019-04-02 | IFQ | OL1-2M03-2665 | ME | 2019-04-10 | 036909C-JVD-TRN-01313 | 036909C-JVD-TRN-01313 | IFR | 2019-04-25 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-ME -01313 |  | 2019-04-11 | 2
036909C-1025-TDS-0610-2548 | Mechanical Equipment Data Sheet - 10-E-2548 - Demethanizer Bottoms Vaporizer | B | 2019-02-27 | IFQ | OL1-2M03-2548 | ME | 2019-03-01 | 036909C-JVD-TRN-00961 | 036909C-JVD-TRN-00961, ROC-TPSK-CECO-T-00018 | IFR | 2019-03-16 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-ME-00961 |  | 2019-03-04 | 2
036909C-1025-TDS-0610-2545 | Mechanical Equipment Data Sheet - 10-E-2545 - Demethanizer Reboiler | B | 2019-03-19 | IFQ | OL1-2M03-2545 | ME | 2019-03-21 | 036909C-JVD-TRN-01123 | 036909C-JVD-TRN-01123, ROC-TPSK-CECO-T-00018 | IFR | 2019-04-05 | 2019-04-11 | R1-No comments | TPSK-LSPA1-T-ME-01123 |  | 2019-03-22 | 2
036909C-1025-TDS-0610-2515 | Mechanical Equipment Data Sheet - 10-E-2515- Demeth Prefrac Reboiler | B | 2019-02-28 | IFQ | OL1-2M03-2515 | ME | 2019-03-01 | 036909C-JVD-TRN-00971 | 036909C-JVD-TRN-00971, ROC-TPSK-CECO-T-00018 | IFR | 2019-03-16 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-ME-00971 |  | 2019-03-04 | 2
036909C-1024-TDS-0610-2465 | Mechanical Equipment Data Sheet - 10-E-2465 - C2 Hydrog Feed Heater | B | 2019-03-20 | IFQ | OL1-2M03-2465 | ME | 2019-04-02 | 036909C-JVD-TRN-01230 | 036909C-JVD-TRN-01230 | IFR | 2019-04-17 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-01230 |  | 2019-04-03 | 2
036909C-1024-TDS-0610-2451 | Mechanical Equipment Data Sheet - 10-E-2450 - LP Depropanizer Condenser | B | 2019-03-28 | IFQ | OL1-2M03-2451 | ME | 2019-03-29 | 036909C-JVD-TRN-01205 | 036909C-JVD-TRN-01205 | IFR | 2019-04-15 | 2019-05-02 | TPSK-LSPA1-E-00190 May 09 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01205 |  | 2019-04-01 | 2
036909C-1024-TDS-0610-2446 | Mechanical Equipment Data Sheet - 10-E-2446 - LP Depropanizer Feed Cooler | B | 2019-03-21 | IFQ | OL1-2M03-2446 | ME | 2019-04-01 | 036909C-JVD-TRN-01218 | 036909C-JVD-TRN-01218 | IFR | 2019-04-16 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-01218 |  | 2019-04-02 | 2
036909C-1024-TDS-0610-2441 | Mechanical Equipment Data Sheet - 10-E-2441 - HP Deprop Reflux Chiller No 2 | B | 2019-03-28 | IFQ | OL1-2M03-2441 | ME | 2019-04-01 | 036909C-JVD-TRN-01216 | 036909C-JVD-TRN-01216 | IFR | 2019-04-16 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-ME -01216 |  | 2019-04-02 | 2
036909C-1024-TDS-0610-2439 | Mechanical Equipment Data Sheet - 10-E-2440 - HP Depropanizer Condenser | B | 2019-03-18 | IFQ | OL1-2M03-2439 | ME | 2019-03-29 | 036909C-JVD-TRN-01205 | 036909C-JVD-TRN-01205 | IFR | 2019-04-15 | 2019-05-02 | TPSK-LSPA1-E-00190 May 09 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01205 |  | 2019-04-01 | 2
036909C-1024-TDS-0610-2434 | Mechanical Equipment Data Sheet - 10-E-2435 - Regen Gas Effluent Cooler | B | 2019-03-18 | IFQ | OL1-2M03-2434 | ME | 2019-04-01 | 036909C-JVD-TRN-01218 | 036909C-JVD-TRN-01218 | IFR | 2019-04-16 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-01218 |  | 2019-04-02 | 2
036909C-1024-TDS-0610-2434 | Mechanical Equipment Data Sheet - 10-E-2435 - Regen Gas Effluent Cooler | A | 2019-01-24 | IFQ | OL1-2M03-2434 | ME | 2019-01-25 | 036909C-JVD-TRN-00723 | 036909C-JVD-TRN-00723, ROC-TPSK-CECO-T-00017 | IFR | 2019-02-07 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00723 |  | 2019-01-25 | 2
036909C-1024-TDS-0610-2406 | Mechanical Equipment Data Sheet - 10-E-2405 - Gas Dryer Feed Chiller | B | 2019-03-28 | IFQ | OL1-2M03-2406 | ME | 2019-03-29 | 036909C-JVD-TRN-01205 | 036909C-JVD-TRN-01205 | IFR | 2019-04-15 | 2019-05-02 | TPSK-LSPA1-E-00190 May 09 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01205 |  | 2019-04-01 | 2
036909C-1026-SP-0810-2622 | Mechanical Equipment Data Sheet - C3 Hydrog Recycle Drum | B | 2019-06-06 | IFQ | OL1-2M03-2622 | ME | 2019-06-06 | 036909C-JVD-TRN-01817 | 036909C-JVD-TRN-01817 | IFR | 2019-06-21 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01817 |  | 2019-06-10 | 2
036909C-1028-SP-1547-2802 | Instrument Datasheet for Flow Element - Rotameter - Area 28 | A | 2019-05-16 | IFQ | OL1-2I20-2828 | IE | 2019-05-16 | 036909C-JVD-TRN-01681 | 036909C-JVD-TRN-01681 | IFI |  | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01681 |  | 2019-05-17 | 3
036909C-1021-SP-1542-2103 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 21 | A | 2019-05-08 | IFQ | OL1-2I20-2106 | IE | 2019-05-09 | 036909C-JVD-TRN-01625 | 036909C-JVD-TRN-01625 | IFI |  | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01625 |  | 2019-05-10 | 3
036909C-1020-SP-1541-2003 | Instrument Datasheets for Control Valve -Butterfly Type- Area 20 | A | 2019-05-08 | IFQ | OL1-2I20-2002 | IE | 2019-05-09 | 036909C-JVD-TRN-01625 | 036909C-JVD-TRN-01625 | IFI |  | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01625 |  | 2019-05-10 | 3
036909C-1012-PDS-1390-1202 | Piping Specialty Item Datasheet - T-Type Filter - Crossover Line - 10-SP-12002-16002 | A | 2019-05-07 | IFR | OL1-2P03-1202 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1000-JSS-1530-0001 | Job Supply Specification For Intercom Paging And Audible Alarm System -Ex Document Client Reference OL1-2T92-0001 | 0 | 2019-02-26 | IMP | OL1-2T01-0001 | EE | 2019-03-07 | 036909C-JVD-TRN-00985 | 036909C-JVD-TRN-00985, ROC-TPSK-CECO-T-00003 | IFA | 2019-03-22 | 2019-03-21 | R2-Comments as noted | TPSK-LSPA1-T-EE-00985 | Ex Document Client Reference: OL1-2T92-0001 | 2019-03-06 | 2
036909C-1000-MR-0610-0001 | Material Requisition For Wieland Tubes - Solo Source - Requisition For Purchase - Ex Doc. Client Reference OL1-2M55-0058 | 0 | 2019-02-05 | IFP | OL1-2C13-271000 | PL | 2019-02-08 | 036909C-JVD-TRN-00829 | 036909C-JVD-TRN-00829 | IFR | 2019-02-25 |  | Transmitted | TPSK-LSPA1-T-PL-00829 | Ex Doc. Client Reference OL1-2M55-0058 P.A. SOCOTEC-Poggi JeanJacques-Sog.It@socotec-oilandgas.com | 2019-02-08 | 2
036909C-1011-SP-1554-1011 | Instrument Datasheets for Temperature Elements for Coil Outlet | B | 2019-05-08 | IFQ | OL1-2I20-1011 | IE | 2019-05-23 | 036909C-JVD-TRN-01729 | 036909C-JVD-TRN-01729 | IFR | 2019-06-07 | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01729 |  | 2019-05-24 | 2
036909C-1055-PDS-0800-5500 | Process Equipment Datasheet - 10-D-5500 - Hot Flare Drum | C | 2019-03-09 | IFD | OL1-2G30-5500 | PE | 2019-03-11 | 036909C-JVD-TRN-01020 | 036909C-JVD-TRN-01020 | IFR | 2019-03-26 | 2019-03-27 | R1-No comments | TPSK-LSPA1-T-PE-01020 |  | 2019-03-12 | 2
036909C-1055-PDS-0800-5550 | Process Equipment Datasheet - 10-D-5550 - HP Flare Knock-Out Drum | C | 2019-03-09 | IFD | OL1-2G30-5550 | PE | 2019-03-11 | 036909C-JVD-TRN-01020 | 036909C-JVD-TRN-01020 | IFR | 2019-03-26 | 2019-03-27 | R1-No comments | TPSK-LSPA1-T-PE-01020 |  | 2019-03-12 | 2
036909C-1055-PDS-0800-5565 | Process Equipment Datasheet - 10-D-5565 - Polyolefins Flare Knock-Out Drum | B | 2019-03-04 | IFD | OL1-2G30-5565 | PE | 2019-03-05 | 036909C-JVD-TRN-00989 | 036909C-JVD-TRN-00989 | IFR | 2019-03-20 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-PE-00989 |  | 2019-03-06 | 2
036909C-105F-CN-1733-0010 | Calculation Note For Foundation Of 10-E-5552 | A | 2019-05-30 | IFR | OL1-2K13-0295 | CV | 2019-05-31 | 036909C-JVD-TRN-01731 | 036909C-JVD-TRN-01731 | IFR | 2019-06-14 | 2019-07-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01731 |  | 2019-06-03 | 1
036909C-105F-CN-1733-0007 | Calculation Note For Foundation 10-D-5552 | A | 2019-05-30 | IFR | OL1-2K13-0284 | CV | 2019-05-31 | 036909C-JVD-TRN-01731 | 036909C-JVD-TRN-01731 | IFR | 2019-06-14 | 2019-07-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01731 |  | 2019-06-03 | 1
036909C-105W-CN-1733-0001 | Calculation Note For Foundation Of 10-TK-5640 | A | 2019-05-30 | IFR | OL1-2K13-0256 | CV | 2019-05-31 | 036909C-JVD-TRN-01731 | 036909C-JVD-TRN-01731 | IFR | 2019-06-14 | 2019-07-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01731 |  | 2019-06-03 | 1
036909C-105F-CN-1733-0006 | Calculation Note For Foundation Of 10-D-5550 | A | 2019-05-30 | IFR | OL1-2K13-0247 | CV | 2019-05-31 | 036909C-JVD-TRN-01731 | 036909C-JVD-TRN-01731 | IFR | 2019-06-14 | 2019-07-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01731 |  | 2019-06-03 | 1
036909C-1022-PDS-0800-2220 | Process Equipment Datasheet - 10-D-2220 - CG 2nd Stage Suction Drum | C | 2019-01-16 | IFD | OL1-2G30-2220 | PE | 2019-01-18 | 036909C-JVD-TRN-00678 | 036909C-JVD-TRN-00678 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00678 |  | 2019-01-18 | 2
036909C-1028-PDS-0800-2880 | Process Equipment Datasheet - 10-D-2880 - C2R 3rd Stage Suction Drum | B | 2019-02-12 | IFD | OL1-2G30-2880 | PE | 2019-02-12 | 036909C-JVD-TRN-00845 | 036909C-JVD-TRN-00845 | IFI |  | 2019-02-25 | TPSK-LSPA1-E-00094 March 13 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-00845 |  | 2019-02-12 | 2
036909C-1021-PDS-0800-2160 | Process Equipment Datasheet - 10-D-2160 - Dilution System Generator | B | 2019-01-09 | IFD | OL1-2G30-2160 | PE | 2019-01-10 | 036909C-JVD-TRN-00620 | 036909C-JVD-TRN-00620 | IFI |  | 2019-02-11 | 036909C-JVD-CLIENT-COMMENT-TRN-01435-June 26-2019 R2-Comments as noted | TPSK-LSPA1-T-PE-00620 |  | 2019-01-10 | 1
036909C-1055-PDS-0800-5510 | Process Equipment Datasheet - 10-D-5510 - Cold Flare Drum | B | 2019-03-09 | IFD | OL1-2G30-5510 | PE | 2019-03-11 | 036909C-JVD-TRN-01018 | 036909C-JVD-TRN-01018 | IFR | 2019-03-26 | 2019-03-27 | R1-No comments | TPSK-LSPA1-T-PE-01018 |  | 2019-03-12 | 2
036909C-1000-MR-0811-0001 | Material Requisition For Shop Assembled Large Drums | A | 2019-03-01 | IFQ | OL1-2C13-131000 | PL | 2019-03-01 | 036909C-JVD-TRN-00967 | 036909C-JVD-TRN-00967 | IFR | 2019-03-18 | 2019-06-06 | R1-No comments | TPSK-LSPA1-T-PL-00967 |  | 2019-03-04 | 2
036909C-1000-MR-0661-0001 | Material Requisition For Purchase Plate And Frame Heat Exchangers Requisition For Purchase | 2 | 2019-07-08 | IFP | OL1-2C13-142000 | PL | 2019-07-08 | 036909C-JVD-TRN-02098 | 036909C-JVD-TRN-02098 | IFR | 2019-07-23 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-PL-02098 |  | 2019-07-09 | 2
036909C-1000-DW-1933-0001 | Overall Firewater Network Drawing | A | 2019-03-26 | IFR | OL1-2L40-1000 | SE | 2019-03-29 | 036909C-JVD-TRN-01198 | 036909C-JVD-TRN-01198 | IFR | 2019-04-08 | 2019-05-14 | R2-Comments as noted | TPSK-LSPA1-T-SE-01198 |  | 2019-04-01 | 2
036909C-1000-MR-0610-0002 | Material Requisition For S&T Heat Exchangers - Large - Requisition For Inquiry | A | 2019-02-08 | IFQ | OL1-2C13-272000 | PL | 2019-02-13 | 036909C-JVD-TRN-00849 | 036909C-JVD-TRN-00849 | IFR | 2019-02-28 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-PL-00849 |  | 2019-02-13 | 2
036909C-1000-PP-806 | Site Material Management | A | 2019-05-02 | IFR | OL1-2Q92-0010 | QM | 2019-05-07 | 036909C-JVD-TRN-01599 | 036909C-JVD-TRN-01599 | IFR | 2019-05-22 | 2019-06-20 | R1-No comments | TPSK-LSPA1-T-QM-01599 |  | 2019-05-08 | 2
036909C-1029-SP-0810-2932 | Mechanical Equipment Data Sheet - Methanol Drum | B | 2019-05-31 | IFQ | OL1-2M03-2932 | ME | 2019-06-04 | 036909C-JVD-TRN-01803 | 036909C-JVD-TRN-01803 | IFR | 2019-06-19 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01803 |  | 2019-06-10 | 2
036909C-1024-SP-0810-2456 | Mechanical Equipment Data Sheet - LP Deprop Reboiler Cond Pot | B | 2019-05-31 | IFQ | OL1-2M03-2456 | ME | 2019-06-04 | 036909C-JVD-TRN-01803 | 036909C-JVD-TRN-01803 | IFR | 2019-06-19 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01803 |  | 2019-06-10 | 2
036909C-1000-MS-6740-0051 | Job Construction Specification For Material Receiving And Warehousting | A | 2019-05-02 | IFR | OL1-2Q92-0017 | QM | 2019-05-07 | 036909C-JVD-TRN-01597 | 036909C-JVD-TRN-01597 | IFR | 2019-05-22 | 2019-06-20 | R1-No comments | TPSK-LSPA1-T-QM-01597 |  | 2019-05-08 | 2
036909C-1055-TDS-0610-5512 | Mechanical Equipment Data Sheet - 10-E-5512 - Cold Flare Superheater | B | 2019-03-26 | IFQ | OL1-2M03-5512 | ME | 2019-04-03 | 036909C-JVD-TRN-01247 | 036909C-JVD-TRN-01247 | IFR | 2019-04-18 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-ME-01247 |  | 2019-04-04 | 2
036909C-1055-TDS-0610-5512 | Mechanical Equipment Data Sheet - 10-E-5512 - Cold Flare Superheater | A | 2019-01-28 | IFQ | OL1-2M03-5512 | ME | 2019-01-29 | 036909C-JVD-TRN-00755 | 036909C-JVD-TRN-00755, ROC-TPSK-CECO-T-00018 | IFR | 2019-02-12 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00755 |  | 2019-01-29 | 2
036909C-1028-TDS-0610-2859 | Mechanical Equipment Data Sheet - 10-E-2856 - Ethylene Product Subcooler | B | 2019-03-30 | IFQ | OL1-2M03-2859 | ME | 2019-04-03 | 036909C-JVD-TRN-01234 | 036909C-JVD-TRN-01234 | IFR | 2019-04-18 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-ME -01234 |  | 2019-04-03 | 2
036909C-1028-TDS-0610-2809 | Mechanical Equipment Data Sheet - 10-E-2809 - C3 Chiller No 2 | B | 2019-04-01 | IFQ | OL1-2M03-2809 | ME | 2019-04-11 | 036909C-JVD-TRN-01324 | 036909C-JVD-TRN-01324 | IFR | 2019-04-26 | 2019-05-20 | TPSK-LSPA1-E-00222 June 06 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01324 |  | 2019-04-12 | 2
036909C-1027-TDS-0610-2711 | Mechanical Equipment Data Sheet - 10-E-2710 - Depentanizer Condenser | B | 2019-04-12 | IFQ | OL1-2M03-2711 | ME | 2019-04-15 | 036909C-JVD-TRN-01362 | 036909C-JVD-TRN-01362 | IFR | 2019-04-30 | 2019-05-24 | TPSK-LSPA1-E-00222 June 06 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01362 |  | 2019-04-16 | 2
036909C-1027-TDS-0610-2711 | Mechanical Equipment Data Sheet - 10-E-2710 - Depentanizer Condenser | A | 2019-02-08 | IFQ | OL1-2M03-2711 | ME | 2019-02-21 | 036909C-JVD-TRN-00908 | 036909C-JVD-TRN-00908, ROC-TPSK-CECO-T-00018 | IFR | 2019-03-08 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00908 |  | 2019-02-22 | 2
036909C-1025-TDS-0610-2582 | Mechanical Equipment Data Sheet - 10-E-2582 - C2 Tower Reflux Cooler | B | 2019-02-13 | IFQ | OL1-2M03-2582 | ME | 2019-02-15 | 036909C-JVD-TRN-00859 | 036909C-JVD-TRN-00859, ROC-TPSK-CECO-T-00018 | IFR | 2019-03-01 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00859 |  | 2019-02-15 | 2
036909C-1022-TDS-0610-2241 | Mechanical Equipment Data Sheet - 10-E-2240 - CG 4th Stage Aftercooler | A | 2019-01-07 | IFQ | OL1-2M03-2241 | ME | 2019-01-10 | 036909C-JVD-TRN-00617 | 036909C-JVD-TRN-00617, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-23 | 2019-01-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-00617 |  | 2019-01-10 | 2
036909C-1022-TDS-0610-2241 | Mechanical Equipment Data Sheet - 10-E-2240 - CG 4th Stage Aftercooler | B | 2019-03-28 | IFQ | OL1-2M03-2241 | ME | 2019-03-29 | 036909C-JVD-TRN-01205 | 036909C-JVD-TRN-01205 | IFR | 2019-04-15 | 2019-05-02 | TPSK-LSPA1-E-00190 May 09 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01205 |  | 2019-04-01 | 2
036909C-1021-TDS-0610-2165 | Mechanical Equipment Data Sheet - 10-E-2165 A-D - DSG Reboilers | B | 2019-03-27 | IFQ | OL1-2M03-2165 | ME | 2019-03-29 | 036909C-JVD-TRN-01205 | 036909C-JVD-TRN-01205 | IFR | 2019-04-15 | 2019-05-02 | TPSK-LSPA1-E-00190 May 09 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01205 |  | 2019-04-01 | 2
036909C-1000-CN-1441-0001 | Hydraulic Calculation Notes For Underground Systems | A | 2019-03-28 | IFR | OL1-2K16-0001 | CV | 2019-04-03 | 036909C-JVD-TRN-01239 | 036909C-JVD-TRN-01239, ROC-TPSK-CECO-T-00037 | IFA | 2019-04-18 | 2019-06-03 | A2 - Approved with comments re-submit is not required | TPSK-LSPA1-T-CV-01239 |  | 2019-04-04 | 1
036909-103S-DW-1652-0001 | Substation C Single Line Diagram | A | 2019-03-28 | IFR | OL1-2E14-0004 | EE | 2019-04-01 | 036909C-JVD-TRN-01211 | 036909C-JVD-TRN-01211, ROC-TPSK-CECO-T-00033 | IFA | 2019-04-16 | 2019-04-25 | A3 - Approved with comments re-submit for review | TPSK-LSPA1-T-CV-01211 |  | 2019-04-02 | 1
036909C-1028-PDS-1390-2828 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 3rd Stage Discharge - 10-SP-28602 | A | 2019-06-17 | IFR | OL1-2P03-2828 | MP | 2019-06-19 | 036909C-JVD-TRN-01938 | 036909C-JVD-TRN-01938 | IFR | 2019-07-04 | 2019-07-16 13:00 | R1-No comments | TPSK-LSPA1-T-MP-01938 |  | 2019-06-20 | 2
03609C-100P-DW-1632-0001 | Lighting Layout - Zone 0P Main Pipe Rack | A | 2019-04-18 | IFLA | OL1-2E43-0006 | EE | 2019-04-23 | 036909C-JVD-TRN-01437 | 036909C-JVD-TRN-01437, ROC-TPSK-CECO-T-00048 | IFA | 2019-05-08 | 2019-05-27 | A3 - Approved with comments re-submit for review | TPSK-LSPA1-T-EE-01437 |  | 2019-04-24 | 1
036909C-1000-MR-0570-0002 | Material Requisition For Ripple Trays And Internals | 0 | 2019-01-07 | IFP | OL1-2C13-243000 | PL | 2019-01-11 | 036909C-JVD-TRN-00628 | 036909C-JVD-TRN-00628 | IFR | 2019-01-25 | 2019-06-06 | R1-No Comments_TPSK-LSPA1-E-00235_14/06/2019 | TPSK-LSPA1-T-PL-00628 |  | 2019-01-11 | 2
036909C-1000-MR-0662-0001 | Material Requisition For Heat Recovery System Requisition For Purchase | 1 | 2019-04-19 | IFP | OL1-2C13-143000 | PL | 2019-04-23 | 036909C-JVD-TRN-01452 | 036909C-JVD-TRN-01452 | IFR | 2019-05-08 | 2019-05-20 | R1-No Comments_TPSK-LSPA1-E-00236_14/06/2019 | TPSK-LSPA1-T-PL-01452 |  | 2019-04-24 | 2
036909C-105T-NM-1350-0031 | Loads on Sleeper Way 10-SLW-5T02 | A | 2019-07-12 | IBD | OL1-2P05-0212 | MP | 2019-07-15 | 036909C-JVD-TRN-02151 | 036909C-JVD-TRN-02151 | IFR | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-MP-02151 |  | 2019-07-15 | 2
036909C-103A-DW-1743-0003 SH001 | Foundation For 10-TK-3900 | A | 2019-07-12 | IFR | OL1-2K31-0210 SH001 | CV | 2019-07-15 | 036909C-JVD-TRN-02152 | 036909C-JVD-TRN-02152 | IFR | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-CV-02152 |  | 2019-07-15 | 2
036909C-103A-DW-1743-0003 SH002 | Foundation For 10-TK-3900 | A | 2019-07-12 | IFR | OL1-2K31-0210 SH002 | CV | 2019-07-15 | 036909C-JVD-TRN-02152 | 036909C-JVD-TRN-02152 | IFR | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-CV-02152 |  | 2019-07-15 | 2
036909C-101A-DW-1743-0001-002 | Foundation For 10-H-1100 | A | 2019-07-11 | IFR | OL1-2K31-2561 | CV | 2019-07-12 | 036909C-JVD-TRN-02148 | 036909C-JVD-TRN-02148 | IFA | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-CV-02148 |  | 2019-07-15 | 1
036909C-101A-DW-1743-0001-001 | Foundation For 10-H-1100 | A | 2019-07-11 | IFR | OL1-2K31-2560 | CV | 2019-07-12 | 036909C-JVD-TRN-02148 | 036909C-JVD-TRN-02148 | IFA | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-CV-02148 |  | 2019-07-15 | 1
036909C-101A-DW-1743-0002-001 | Foundation For 10-H-1200 To 1600 | A | 2019-07-11 | IFR | OL1-2K31-2580 | CV | 2019-07-12 | 036909C-JVD-TRN-02148 | 036909C-JVD-TRN-02148 | IFA | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-CV-02148 |  | 2019-07-15 | 1
036909C-101A-DW-1743-0002-002 | Foundation For 10-H-1200 To 1600 | A | 2019-07-11 | IFR | OL1-2K31-2581 | CV | 2019-07-12 | 036909C-JVD-TRN-02148 | 036909C-JVD-TRN-02148 | IFA | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-CV-02148 |  | 2019-07-15 | 1
036909C-101A-CN-1733-0002 | Calculation Note For Foundation Of 10-H-1200-1600 | A | 2019-07-10 | IFR | OL1-2K13-0002 | CV | 2019-07-12 | 036909C-JVD-TRN-02150 | 036909C-JVD-TRN-02150 | IFA | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-CV-02150 |  | 2019-07-15 | 1
036909C-101A-CN-1733-0001 | Calculation Note For Foundation Of 10-H-1100 | A | 2019-07-11 | IFR | OL1-2K13-0001 | CV | 2019-07-12 | 036909C-JVD-TRN-02150 | 036909C-JVD-TRN-02150 | IFA | 2019-07-29 |  | Transmitted | TPSK-LSPA1-T-CV-02150 |  | 2019-07-15 | 1
036909C-100P-DW-1741-0002-011 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Beams | A | 2019-05-21 | IFR | OL1-2K31-1030 | CV | 2019-05-27 | 036909C-JVD-TRN-01747 | 036909C-JVD-TRN-01747 | IFA | 2019-06-11 | 2019-06-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01747 |  | 2019-05-28 | 1
036909C-100P-DW-1741-0002-010 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Beams | A | 2019-05-21 | IFR | OL1-2K31-1029 | CV | 2019-05-27 | 036909C-JVD-TRN-01747 | 036909C-JVD-TRN-01747 | IFA | 2019-06-11 | 2019-06-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01747 |  | 2019-05-28 | 1
036909C-100P-DW-1741-0002-009 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Columns | A | 2019-05-21 | IFR | OL1-2K31-1028 | CV | 2019-05-27 | 036909C-JVD-TRN-01747 | 036909C-JVD-TRN-01747 | IFA | 2019-06-11 | 2019-06-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01747 |  | 2019-05-28 | 1
036909C-100P-DW-1741-0002-008 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Columns | A | 2019-05-21 | IFR | OL1-2K31-1027 | CV | 2019-05-27 | 036909C-JVD-TRN-01747 | 036909C-JVD-TRN-01747 | IFA | 2019-06-11 | 2019-06-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01747 |  | 2019-05-28 | 1
036909C-100P-DW-1741-0002-007 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Columns | A | 2019-05-21 | IFR | OL1-2K31-1026 | CV | 2019-05-27 | 036909C-JVD-TRN-01747 | 036909C-JVD-TRN-01747 | IFA | 2019-06-11 | 2019-06-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01747 |  | 2019-05-28 | 1
036909C-100P-DW-1741-0002-006 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Elevations | A | 2019-05-21 | IFR | OL1-2K31-1025 | CV | 2019-05-27 | 036909C-JVD-TRN-01747 | 036909C-JVD-TRN-01747 | IFA | 2019-06-11 | 2019-06-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01747 |  | 2019-05-28 | 1
036909C-100P-DW-1741-0002-005 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Elevations | A | 2019-05-21 | IFR | OL1-2K31-1024 | CV | 2019-05-27 | 036909C-JVD-TRN-01747 | 036909C-JVD-TRN-01747 | IFA | 2019-06-11 | 2019-06-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01747 |  | 2019-05-28 | 1
036909C-100P-DW-1741-0002-004 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Elevations | A | 2019-05-21 | IFR | OL1-2K31-1023 | CV | 2019-05-27 | 036909C-JVD-TRN-01747 | 036909C-JVD-TRN-01747 | IFA | 2019-06-11 | 2019-06-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01747 |  | 2019-05-28 | 1
036909C-100P-DW-1741-0002-003 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Plans | A | 2019-05-21 | IFR | OL1-2K31-1022 | CV | 2019-05-27 | 036909C-JVD-TRN-01747 | 036909C-JVD-TRN-01747 | IFA | 2019-06-11 | 2019-06-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01747 |  | 2019-05-28 | 1
036909C-100P-DW-1741-0002-002 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Plans | A | 2019-05-21 | IFR | OL1-2K31-1021 | CV | 2019-05-27 | 036909C-JVD-TRN-01747 | 036909C-JVD-TRN-01747 | IFA | 2019-06-11 | 2019-06-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01747 |  | 2019-05-28 | 1
036909C-100P-DW-1741-0002-001 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - 3D View | A | 2019-05-21 | IFR | OL1-2K31-1020 | CV | 2019-05-27 | 036909C-JVD-TRN-01747 | 036909C-JVD-TRN-01747 | IFA | 2019-06-11 | 2019-06-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01747 |  | 2019-05-28 | 1
036909C-100P-DW-1741-0001-002 | Foundation And Elevation Of Pipe Rack 10-PRK-0P01 - Formwork And Reinforcement | A | 2019-05-21 | IFR | OL1-2K31-1001 | CV | 2019-05-27 | 036909C-JVD-TRN-01747 | 036909C-JVD-TRN-01747 | IFA | 2019-06-11 | 2019-06-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01747 |  | 2019-05-28 | 1
036909C-100P-DW-1741-0001-001 | Foundation And Elevation Of Pipe Rack 10-PRK-0P01 - Formwork And Reinforcement | A | 2019-05-21 | IFR | OL1-2K31-1000 | CV | 2019-05-27 | 036909C-JVD-TRN-01747 | 036909C-JVD-TRN-01747 | IFA | 2019-06-11 | 2019-06-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01747 |  | 2019-05-28 | 1
036909C-102B-DW-1743-0046-001 | Foundation For 10-E-1006 | A | 2019-05-21 | IFR | OL1-2K31-0104 | CV | 2019-05-27 | 036909C-JVD-TRN-01747 | 036909C-JVD-TRN-01747 | IFA | 2019-06-11 | 2019-06-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01747 |  | 2019-05-28 | 1
036909C-1000-DW-1512-0001 | CTRL And Safety Systems Connect Diagram | 0 | 2019-06-12 | IBD | OL1-2I81-1001 | IE | 2019-06-13 | 036909C-JVD-TRN-01889 | 036909C-JVD-TRN-01889 | IFA | 2019-06-28 | 2019-07-01 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-01889 |  | 2019-06-14 | 1
036909C-1000-DW-1512-0002 | Control and Safety Systems Architecture | B | 2019-04-23 | IFR | OL1-2I81-1002 | IE | 2019-05-02 | 036909C-JVD-TRN-01551 | 036909C-JVD-TRN-01551 | IFR | 2019-05-17 | 2019-05-18 | R2-Comments as noted | TPSK-LSPA1-T-IE-01551 |  | 2019-05-03 | 1
036909C-1000-JSD-1510-0001 | General Design Rules For Control And Safety Philosophy | 0 | 2019-04-23 | IFE | OL1-2R06-1025 | IE | 2019-05-02 | 036909C-JVD-TRN-01552 | 036909C-JVD-TRN-01552 | IFR | 2019-05-17 | 2019-05-18 | R2-Comments as noted | TPSK-LSPA1-T-IE-01552 |  | 2019-05-03 | 2
036909C-1000-MR-1541-0001 | Material Requisition For Control Valves | B | 2019-06-25 | IFQ | OL1-2C17-050101 | PL | 2019-06-27 | 036909C-JVD-TRN-02017 | 036909C-JVD-TRN-02017 | IFR | 2019-07-12 | 2019-07-10 | R2-Comments as noted | TPSK-LSPA1-T-PL-02017 |  | 2019-06-28 | 2
036909C-105U-DW-1743-0004 | FOUNDATION FOR 10-D-5515 | A | 2019-04-19 | IFR | OL1-2K31-0271 | CV | 2019-05-13 | 036909C-JVD-TRN-01647 | 036909C-JVD-TRN-01647, KLOC-TPSK-CECO-T-00009 | IFR | 2019-05-24 | 2019-07-16 | R2-Comments as noted | TPSK-LSPA1-T-CV-01647 |  | 2019-05-14 | 2
036909C-105U-DW-1743-0003 | FOUNDATION FOR 10-D-5513 | A | 2019-04-19 | IFR | OL1-2K31-0270 | CV | 2019-05-13 | 036909C-JVD-TRN-01647 | 036909C-JVD-TRN-01647, KLOC-TPSK-CECO-T-00009 | IFR | 2019-05-24 | 2019-07-16 | R2-Comments as noted | TPSK-LSPA1-T-CV-01647 |  | 2019-05-14 | 2
036909C-105U-DW-1743-0002 | FOUNDATION FOR 10-D-5510 | A | 2019-04-19 | IFR | OL1-2K31-0269 | CV | 2019-05-13 | 036909C-JVD-TRN-01647 | 036909C-JVD-TRN-01647, KLOC-TPSK-CECO-T-00009 | IFR | 2019-05-24 | 2019-07-16 | R2-Comments as noted | TPSK-LSPA1-T-CV-01647 |  | 2019-05-14 | 2
036909C-105T-CN-1733-0001 | Calculation Note For Foundation Of 10-TK-5900 | A | 2019-04-25 | IFR | OL1-2K13-0393 | CV | 2019-05-13 | 036909C-JVD-TRN-01647 | 036909C-JVD-TRN-01647, KLOC-TPSK-CECO-T-00009 | IFR | 2019-05-24 | 2019-07-16 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01647 |  | 2019-05-14 | 1
036909C-105T-DW-1743-0001 | FOUNDATION FOR 10-TK-5900 | A | 2019-04-19 | IFR | OL1-2K31-0323 | CV | 2019-05-13 | 036909C-JVD-TRN-01647 | 036909C-JVD-TRN-01647, KLOC-TPSK-CECO-T-00009 | IFR | 2019-05-24 | 2019-07-16 | R2-Comments as noted | TPSK-LSPA1-T-CV-01647 |  | 2019-05-14 | 2
036909C-105U-CN-1733-0005 | Calculation Note For Foundation Of 10-D-5520 | A | 2019-04-25 | IFR | OL1-2K13-0252 | CV | 2019-05-13 | 036909C-JVD-TRN-01647 | 036909C-JVD-TRN-01647, KLOC-TPSK-CECO-T-00009 | IFR | 2019-05-24 | 2019-07-16 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01647 |  | 2019-05-14 | 1
036909C-105U-CN-1733-0004 | Calculation Note For Foundation Of 10-D-5515 | A | 2019-04-25 | IFR | OL1-2K13-0251 | CV | 2019-05-13 | 036909C-JVD-TRN-01647 | 036909C-JVD-TRN-01647, KLOC-TPSK-CECO-T-00009 | IFR | 2019-05-24 | 2019-07-16 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01647 |  | 2019-05-14 | 1
036909C-105U-CN-1733-0003 | Calculation Note For Foundation Of 10-D-5513 | A | 2019-04-25 | IFR | OL1-2K13-0250 | CV | 2019-05-13 | 036909C-JVD-TRN-01647 | 036909C-JVD-TRN-01647, KLOC-TPSK-CECO-T-00009 | IFR | 2019-05-24 | 2019-07-16 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01647 |  | 2019-05-14 | 1
036909C-105U-DW-1743-0008 | FOUNDATION FOR 10-E-5513 | A | 2019-05-15 | IFR | OL1-2K31-0275 | CV | 2019-05-17 | 036909C-JVD-TRN-01687 | 036909C-JVD-TRN-01687 | IFR | 2019-05-31 | 2019-07-16 | R2-Comments as noted | TPSK-LSPA1-T-CV-01687 |  | 2019-05-21 | 2
036909C-105U-DW-1743-0048 | FOUNDATION FOR 10-E-5510 | A | 2019-05-15 | IFR | OL1-2K31-0284 | CV | 2019-05-17 | 036909C-JVD-TRN-01687 | 036909C-JVD-TRN-01687 | IFR | 2019-05-31 | 2019-07-16 | R2-Comments as noted | TPSK-LSPA1-T-CV-01687 |  | 2019-05-21 | 2
036909C-105U-CN-1733-0002 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5510 | A | 2019-04-25 | IFR | OL1-2K13-0249 | CV | 2019-05-13 | 036909C-JVD-TRN-01647 | 036909C-JVD-TRN-01647, KLOC-TPSK-CECO-T-00009 | IFR | 2019-05-24 | 2019-07-16 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01647 |  | 2019-05-14 | 1
036909C-1028-TDS-0610-2857 | Mechanical Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer | B | 2019-01-30 | IFQ | OL1-2M03-2857 | ME | 2019-01-30 | 036909C-JVD-TRN-00773 | 036909C-JVD-TRN-00773, ROC-TPSK-CECO-T-00018 | IFR | 2019-02-15 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00773 |  | 2019-01-31 | 2
036909C-1028-TDS-0610-2857 | Mechanical Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer | C | 2019-03-28 | IFQ | OL1-2M03-2857 | ME | 2019-04-03 | 036909C-JVD-TRN-01246 | 036909C-JVD-TRN-01246 | IFR | 2019-04-18 | 2019-05-20 | TPSK-LSPA1-E-00222 June 06 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01246 |  | 2019-04-04 | 2
036909C-1024-TDS-0610-2413 | Mechanical Equipment Data Sheet - 10-E-2413 - HP Deprop Feed - Overhead Exchanger | B | 2019-03-18 | IFQ | OL1-2M03-2413 | ME | 2019-03-27 | 036909C-JVD-TRN-01179 | 036909C-JVD-TRN-01179 | IFR | 2019-04-11 | 2019-05-02 | TPSK-LSPA1-E-00190 May 09 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01179 |  | 2019-03-28 | 2
036909C-1024-TDS-0610-2413 | Mechanical Equipment Data Sheet - 10-E-2413 - HP Deprop Feed-Overhead Exchanger | A | 2019-01-07 | IFR | OL1-2M03-2413 | ME | 2019-01-10 | 036909C-JVD-TRN-00617 | 036909C-JVD-TRN-00617, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-23 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00617 |  | 2019-01-10 | 2
036909C-1024-TDS-0610-2412 | Mechanical Equipment Data Sheet - 10-E-2412 - HP Deprop Feed Chiller | B | 2019-03-12 | IFQ | OL1-2M03-2412 | ME | 2019-03-27 | 036909C-JVD-TRN-01179 | 036909C-JVD-TRN-01179 | IFR | 2019-04-11 | 2019-05-02 | TPSK-LSPA1-E-00190 May 09 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01179 |  | 2019-03-28 | 2
036909C-1025-SP-0810-2574 | Mechanical Equipment Data Sheet - Deethanizer Reboiler Cond Pot | B | 2019-05-31 | IFQ | OL1-2M03-2574 | ME | 2019-06-04 | 036909C-JVD-TRN-01803 | 036909C-JVD-TRN-01803 | IFR | 2019-06-19 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-01803 |  | 2019-06-10 | 2
036909C-1024-SP-0810-2435 | Mechanical Equipment Data Sheet - Regen Gas Separator | B | 2019-05-27 | IFQ | OL1-2M03-2435 | ME | 2019-05-30 | 036909C-JVD-TRN-01783 | 036909C-JVD-TRN-01783 | IFR | 2019-06-14 | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-ME-01783 |  | 2019-05-31 | 2
036909C-1023-SP-0810-2316 | Mechanical Equipment Data Sheet - Spent Caustic Degassing Drum | B | 2019-05-25 | IFQ | OL1-2M03-2316 | ME | 2019-05-30 | 036909C-JVD-TRN-01783 | 036909C-JVD-TRN-01783 | IFR | 2019-06-14 | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-ME-01783 |  | 2019-05-31 | 2
036909C-1028-TDS-0610-2856 | Mechanical Equipment Data Sheet - 10-E-2855 - C2R Condenser | C | 2019-03-29 | IFQ | OL1-2M03-2856 | ME | 2019-03-29 | 036909C-JVD-TRN-01205 | 036909C-JVD-TRN-01205 | IFR | 2019-04-15 | 2019-05-02 | TPSK-LSPA1-E-00190 May 09 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01205 |  | 2019-04-01 | 2
036909C-1027-TDS-0610-2702 | Mechanical Equipment Data Sheet - 10-E-2702 - GHU-1 Start-Up Heater | A | 2019-03-15 | IFQ | OL1-2M03-2702 | ME | 2019-03-19 | 036909C-JVD-TRN-01095 | 036909C-JVD-TRN-01095 | IFR | 2019-04-03 | 2019-04-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-01095 |  | 2019-03-20 | 2
036909C-1026-TDS-0610-2645 | Mechanical Equipment Data Sheet - 10-E-2645 - C3 Tower Reboilers | C | 2019-04-04 | IFQ | OL1-2M03-2645 | ME | 2019-04-09 | 036909C-JVD-TRN-01286 | 036909C-JVD-TRN-01286 | IFR | 2019-04-24 | 2019-05-20 | TPSK-LSPA1-E-00222 June 06 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01286 |  | 2019-04-10 | 2
036909C-1025-TDS-0610-2571 | Mechanical Equipment Data Sheet - 10-E-2570 - Deethanizer Condenser | C | 2019-04-03 | IFQ | OL1-2M03-2571 | ME | 2019-04-03 | 036909C-JVD-TRN-01245 | 036909C-JVD-TRN-01245 | IFR | 2019-04-18 | 2019-05-20 | TPSK-LSPA1-E-00222 June 06 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01245 |  | 2019-04-04 | 2
036909C-1025-TDS-0610-2571 | Mechanical Equipment Data Sheet - 10-E-2570 - Deethanizer Condenser | B | 2019-01-30 | IFQ | OL1-2M03-2571 | ME | 2019-01-30 | 036909C-JVD-TRN-00773 | 036909C-JVD-TRN-00773, ROC-TPSK-CECO-T-00018 | IFR | 2019-02-15 | 2019-02-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00773 |  | 2019-01-31 | 2
036909C-1030-PDS-1390-3019 | Piping Specialty Item - Datasheet - T-Type Filter - P-3080 A-B Suction - 10-SP-30019 | A | 2019-06-24 | IFR | OL1-2P03-3019 | MP | 2019-06-26 | 036909C-JVD-TRN-02010 | 036909C-JVD-TRN-02010 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02010 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3018 | Piping Specialty Item - Datasheet - T-Type Filter - P-3096 A-B Suction - 10-SP-30018 | A | 2019-06-25 | IFR | OL1-2P03-3018 | MP | 2019-06-26 | 036909C-JVD-TRN-02010 | 036909C-JVD-TRN-02010 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02010 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3017 | Piping Specialty Item - Datasheet - T-Type Filter - P-3061 A-B Suction - 10-SP-30017 | A | 2019-06-25 | IFR | OL1-2P03-3017 | MP | 2019-06-26 | 036909C-JVD-TRN-02010 | 036909C-JVD-TRN-02010 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02010 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3016 | Piping Specialty Item - Datasheet - T-Type Filter - P-3060 A-B Suction - 10-SP-30016 | A | 2019-06-25 | IFR | OL1-2P03-3016 | MP | 2019-06-26 | 036909C-JVD-TRN-02010 | 036909C-JVD-TRN-02010 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02010 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3015 | Piping Specialty Item - Datasheet - T-Type Filter - P-3056 A-B Suction - 10-SP-30015 | A | 2019-06-25 | IFR | OL1-2P03-3015 | MP | 2019-06-26 | 036909C-JVD-TRN-02010 | 036909C-JVD-TRN-02010 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02010 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3014 | Piping Specialty Item - Datasheet - T-Type Filter - P-3076 A-B Suction - 10-SP-30014 | A | 2019-06-25 | IFR | OL1-2P03-3014 | MP | 2019-06-26 | 036909C-JVD-TRN-02010 | 036909C-JVD-TRN-02010 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02010 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3013 | Piping Specialty Item - Datasheet - T-Type Filter - P-3086 A-B Suction - 10-SP-30013 | A | 2019-06-25 | IFR | OL1-2P03-3013 | MP | 2019-06-26 | 036909C-JVD-TRN-02009 | 036909C-JVD-TRN-02009 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02009 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3012 | Piping Specialty Item - Datasheet - T-Type Filter - P-3062 A-B Suction - 10-SP-30012 | A | 2019-06-25 | IFR | OL1-2P03-3012 | MP | 2019-06-26 | 036909C-JVD-TRN-02009 | 036909C-JVD-TRN-02009 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02009 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3011 | Piping Specialty Item - Datasheet - T-Type Filter - P-3036 A-B Suction - 10-SP-30011 | A | 2019-06-25 | IFR | OL1-2P03-3011 | MP | 2019-06-26 | 036909C-JVD-TRN-02009 | 036909C-JVD-TRN-02009 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02009 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3010 | Piping Specialty Item - Datasheet - T-Type Filter - P-3046 A-B Suction - 10-SP-30010 | A | 2019-06-25 | IFR | OL1-2P03-3010 | MP | 2019-06-26 | 036909C-JVD-TRN-02009 | 036909C-JVD-TRN-02009 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02009 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3009 | Piping Specialty Item - Datasheet - T-Type Filter - P-3045 A-B Suction - 10-SP-30009 | A | 2019-06-25 | IFR | OL1-2P03-3009 | MP | 2019-06-26 | 036909C-JVD-TRN-02009 | 036909C-JVD-TRN-02009 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02009 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3008 | Piping Specialty Item - Datasheet - T-Type Filter - P-3030 A-B Suction - 10-SP-30008 | A | 2019-06-22 | IFR | OL1-2P03-3008 | MP | 2019-06-26 | 036909C-JVD-TRN-02009 | 036909C-JVD-TRN-02009 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02009 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3005 | Piping Specialty Item - Datasheet - T-Type Filter - P-3020 A-B Suction - 10-SP-30005 | A | 2019-06-22 | IFR | OL1-2P03-3005 | MP | 2019-06-26 | 036909C-JVD-TRN-02012 | 036909C-JVD-TRN-02012 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02012 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3004 | Piping Specialty Item - Datasheet - T-Type Filter - P-3026 A-B Suction - 10-SP-30004 | A | 2019-06-22 | IFR | OL1-2P03-3004 | MP | 2019-06-26 | 036909C-JVD-TRN-02009 | 036909C-JVD-TRN-02009 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02009 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3003 | Piping Specialty Item - Datasheet - T-Type Filter - P-3016 A-B Suction - 10-SP-30003 | A | 2019-06-22 | IFR | OL1-2P03-3003 | MP | 2019-06-26 | 036909C-JVD-TRN-02009 | 036909C-JVD-TRN-02009 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02009 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3002 | Piping Specialty Item - Datasheet - T-Type Filter - P-3000 A-B Suction - 10-SP-30002 | A | 2019-06-22 | IFR | OL1-2P03-3002 | MP | 2019-06-26 | 036909C-JVD-TRN-02009 | 036909C-JVD-TRN-02009 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02009 |  | 2019-06-27 | 2
036909C-1030-PDS-1390-3001 | Piping Specialty Item - Datasheet - T-Type Filter - P-3002 A-B Suction - 10-SP-30001 | A | 2019-06-22 | IFR | OL1-2P03-3001 | MP | 2019-06-26 | 036909C-JVD-TRN-02012 | 036909C-JVD-TRN-02012 | IFR | 2019-07-11 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-02012 |  | 2019-06-27 | 2
036909C-1028-PDS-1390-2830 | Piping Specialty Item - Datasheet -Non-Slam Check - C-2850 3 rd Stage Discharge - 10-SP-28607 | A | 2019-06-17 | IFR | OL1-2P03-2830 | MP | 2019-06-19 | 036909C-JVD-TRN-01938 | 036909C-JVD-TRN-01938 | IFR | 2019-07-04 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01938 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2829 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 4th Stage Discharge - 10-SP-28603 | A | 2019-06-17 | IFR | OL1-2P03-2829 | MP | 2019-06-19 | 036909C-JVD-TRN-01938 | 036909C-JVD-TRN-01938 | IFR | 2019-07-04 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01938 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2835 | Piping Specialty Item - Datasheet - T-Type Filter - P-2855 A-B Suction - 10-SP-28510 | A | 2019-06-17 | IFR | OL1-2P03-2835 | MP | 2019-06-19 | 036909C-JVD-TRN-01940 | 036909C-JVD-TRN-01940 | IFR | 2019-07-04 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01940 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2834 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C2R Desuperheater 2 Outlet - 10-SP-28608 | A | 2019-06-17 | IFR | OL1-2P03-2834 | MP | 2019-06-19 | 036909C-JVD-TRN-01939 | 036909C-JVD-TRN-01939 | IFR | 2019-07-04 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01939 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2833 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C2R Desuperheater 2 Outlet - 10-SP-28609 | A | 2019-06-17 | IFR | OL1-2P03-2833 | MP | 2019-06-19 | 036909C-JVD-TRN-01939 | 036909C-JVD-TRN-01939 | IFR | 2019-07-04 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01939 |  | 2019-06-20 | 2
036909C-102E-DW-1612-0001 | Earthing Layout - Zone 2E - Earthing Key Plan | A | 2019-06-06 | IFR | OL1-2E52-0016 | EE | 2019-06-11 | 036909C-JVD-TRN-01862 | 036909C-JVD-TRN-01862 | IFA | 2019-06-26 | 2019-06-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01862 |  | 2019-06-11 | 1
036909C-102D-DW-1612-0001 | Earthing and Lightning Protection Layout - Zone 2D | A | 2019-06-05 | IFR | OL1-2E52-0015 | EE | 2019-06-11 | 036909C-JVD-TRN-01862 | 036909C-JVD-TRN-01862 | IFA | 2019-06-26 | 2019-06-25 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-01862 |  | 2019-06-11 | 1
036909C-101B-DW-1612-0001 | Earthing And Lightning Protection Layout - Zone 1B | A | 2019-06-04 | IFR | OL1-2E52-0011 | EE | 2019-06-11 | 036909C-JVD-TRN-01862 | 036909C-JVD-TRN-01862 | IFA | 2019-06-26 | 2019-06-25 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-01862 |  | 2019-06-11 | 1
036909C-100P-DW-1612-0001 | Earthing and Lightning Protection Layout - Zone 0P | A | 2019-06-06 | IFR | OL1-2E52-0004 | EE | 2019-06-11 | 036909C-JVD-TRN-01862 | 036909C-JVD-TRN-01862 | IFA | 2019-06-26 | 2019-06-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01862 |  | 2019-06-11 | 1
036909C-102B-DW-1612-0001 | Earthing and Lightning Protection Layout - Zone 2B | A | 2019-05-29 | IFR | OL1-2E52-0013 | EE | 2019-06-03 | 036909C-JVD-TRN-01793 | 036909C-JVD-TRN-01793 | IFA | 2019-06-18 | 2019-06-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01793 |  | 2019-06-10 | 1
036909C-102A-DW-1612-0001 | Earthing and Lightning Protection Layout - Zone 2A | A | 2019-05-21 | IFR | OL1-2E52-0012 | EE | 2019-06-03 | 036909C-JVD-TRN-01793 | 036909C-JVD-TRN-01793 | IFA | 2019-06-18 | 2019-07-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01793 |  | 2019-06-10 | 1
036909C-1028-PDS-1390-2810 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 4th Stage Discharge - 10-SP-28109 | A | 2019-06-17 | IFR | OL1-2P03-2810 | MP | 2019-06-19 | 036909C-JVD-TRN-01935 | 036909C-JVD-TRN-01935 | IFR | 2019-07-04 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01935 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2809 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 4th Stage Discharge - 10-SP-28108 | A | 2019-06-17 | IFR | OL1-2P03-2809 | MP | 2019-06-19 | 036909C-JVD-TRN-01934 | 036909C-JVD-TRN-01934 | IFR | 2019-07-04 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01934 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-1808 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 4th Stage Suction - 10-SP-28105 | A | 2019-06-17 | IFR | OL1-2P03-2808 | MP | 2019-06-19 | 036909C-JVD-TRN-01933 | 036909C-JVD-TRN-01933 | IFR | 2019-07-04 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01933 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2807 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 5th Stage Discharge - 10-SP-28104 | A | 2019-06-17 | IFR | OL1-2P03-2807 | MP | 2019-06-19 | 036909C-JVD-TRN-01933 | 036909C-JVD-TRN-01933 | IFR | 2019-07-04 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01933 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2806 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 1st Stage Suction - 10-SP-28103 | A | 2019-06-17 | IFR | OL1-2P03-2806 | MP | 2019-06-19 | 036909C-JVD-TRN-01931 | 036909C-JVD-TRN-01931 | IFR | 2019-07-04 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01931 |  | 2019-06-20 | 2
036909C-1023-PDS-1390-2323 | Piping Specialty Item - Datasheet - T-Type Filter - P-2300 A-B Suction - 10-SP-23023 | A | 2019-06-07 | IFR | OL1-2P03-2323 | MP | 2019-06-12 | 036909C-JVD-TRN-01884 | 036909C-JVD-TRN-01884 | IFR | 2019-06-27 | 2019-07-15 | R2-Comments as noted | TPSK-LSPA1-T-MP-01884 |  | 2019-06-14 | 2
036909C-1023-PDS-1390-2312 | Piping Specialty Item - Datasheet - T-Type Filter - P-2300 A-B Suction - 10-SP-23012 | A | 2019-06-07 | IFR | OL1-2P03-2312 | MP | 2019-06-12 | 036909C-JVD-TRN-01884 | 036909C-JVD-TRN-01884 | IFR | 2019-06-27 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01884 |  | 2019-06-14 | 2
036909C-1023-PDS-1390-2309 | Piping Specialty Item - Datasheet - T-Type Filter - P-2320 A-B Suction - 10-SP-23009 | A | 2019-06-07 | IFR | OL1-2P03-2309 | MP | 2019-06-12 | 036909C-JVD-TRN-01884 | 036909C-JVD-TRN-01884 | IFR | 2019-06-27 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01884 |  | 2019-06-14 | 2
036909C-1023-PDS-1390-2306 | Piping Specialty Item - Datasheet - T-Type Filter - P-2310 A-B Suction - 10-SP-23006 | A | 2019-06-07 | IFR | OL1-2P03-2306 | MP | 2019-06-12 | 036909C-JVD-TRN-01884 | 036909C-JVD-TRN-01884 | IFR | 2019-06-27 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01884 |  | 2019-06-14 | 2
036909C-1023-PDS-1390-2304 | Piping Specialty Item - Datasheet - T-Type Filter - P-2302 A-B Suction - 10-SP-23004 | A | 2019-06-07 | IFR | OL1-2P03-2304 | MP | 2019-06-12 | 036909C-JVD-TRN-01884 | 036909C-JVD-TRN-01884 | IFR | 2019-06-27 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-MP-01884 |  | 2019-06-14 | 2
036909C-1000-MR-0511-0002 | Material Requisition For Shop Assembled Columns Requisition For Purchase | 0 | 2019-06-25 | IFP | OL1-2C13-101000 | PL | 2019-06-25 | 036909C-JVD-TRN-01989 | 036909C-JVD-TRN-01989 | IFR | 2019-07-10 | 2019-07-10 | R1-No comments | TPSK-LSPA1-T-PL-01989 |  | 2019-06-26 | 2
036909C-1000-MTO-1311-0001 | Piping MTO Assembly Collection | A | 2019-06-10 | IFR | OL1-2P92-0001 | MP | 2019-06-19 | 036909C-JVD-TRN-01927 | 036909C-JVD-TRN-01927 | IFR | 2019-07-04 | 2019-07-10 | R1-No comments | TPSK-LSPA1-T-MP-01927 |  | 2019-06-20 | 2
036909C-105W-DW-1552-0001 | Level Instrument Design And Nozzle Study For Water Treatment Osbl 5W | A | 2019-06-20 | IFR | OL1-2I31-0213 | IE | 2019-06-27 | 036909C-JVD-TRN-02015 | 036909C-JVD-TRN-02015 | IFA | 2019-07-12 | 2019-07-10 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02015 |  | 2019-06-28 | 1
036909C-103A-DW-1552-0001 | Level Instrument Design And Nozzle Study For Butadiene Extraction Unit Osbl 3A | A | 2019-06-21 | IFR | OL1-2I31-0208 | IE | 2019-06-27 | 036909C-JVD-TRN-02015 | 036909C-JVD-TRN-02015 | IFA | 2019-07-12 | 2019-07-10 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02015 |  | 2019-06-28 | 1
036909C-102C-DW-1552-0001 | Level Instrument Design And Nozzle Study Hot Fractionation -Ghu Unit Isbl -2C | A | 2019-06-20 | IFR | OL1-2I31-0205 | IE | 2019-06-27 | 036909C-JVD-TRN-02015 | 036909C-JVD-TRN-02015 | IFA | 2019-07-12 | 2019-07-10 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02015 |  | 2019-06-28 | 1
036909C-101B-DW-1552-0001 | Level Instrument Design And Nozzle Study for Furnaces Utilities ISBL 1B | A | 2019-06-24 | IFR | OL1-2I31-0202 | IE | 2019-06-27 | 036909C-JVD-TRN-02015 | 036909C-JVD-TRN-02015 | IFA | 2019-07-12 | 2019-07-10 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02015 |  | 2019-06-28 | 1
036909C-100C-DW-1552-0001 | Level Istrument Design And Nozzle Study Common Area OSBL 0C | A | 2019-06-21 | IFR | OL1-2I31-0200 | IE | 2019-06-27 | 036909C-JVD-TRN-02015 | 036909C-JVD-TRN-02015 | IFA | 2019-07-12 | 2019-07-10 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02015 |  | 2019-06-28 | 1
036909C-1000-QCP-1590-0001 | Quality Control Plan - Instrumentation And Communication System Installation - Package Instrumentation Test | A | 2019-05-07 | IFR | OL1-2Q27-0006 | QM | 2019-05-10 | 036909C-JVD-TRN-01636 | 036909C-JVD-TRN-01636 | IFA | 2019-05-27 | 2019-06-17 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-QM-01636 |  | 2019-05-13 | 1
036909C-1000-QCP-1560-0001 | Quality Control Plan - Instrumentation And Communication System Installation - Analyzer Installation | A | 2019-05-07 | IFR | OL1-2Q27-0004 | QM | 2019-05-10 | 036909C-JVD-TRN-01636 | 036909C-JVD-TRN-01636 | IFA | 2019-05-27 | 2019-06-17 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-QM-01636 |  | 2019-05-13 | 1
036909C-1000-QCP-1530-0001 | Quality Control Plan - Instrumentation And Communication System Installation - Field Instrumentation Works | A | 2019-05-07 | IFR | OL1-2Q27-0003 | QM | 2019-05-10 | 036909C-JVD-TRN-01636 | 036909C-JVD-TRN-01636 | IFA | 2019-05-27 | 2019-06-17 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-QM-01636 |  | 2019-05-13 | 1
036909C-1000-QCP-1520-0001 | Quality Control Plan - Instrumentation And Communication System Installation - Instrument Cables Junction Boxes And Local Panels Installation | A | 2019-05-07 | IFR | OL1-2Q27-0002 | QM | 2019-05-10 | 036909C-JVD-TRN-01636 | 036909C-JVD-TRN-01636 | IFA | 2019-05-27 | 2019-06-17 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-QM-01636 |  | 2019-05-13 | 1
036909C-1000-QCP-1510-0001 | Quality Control Plan - Instrumentation And Communication System - Installation Works In Control Room | A | 2019-05-07 | IFR | OL1-2Q27-0001 | QM | 2019-05-10 | 036909C-JVD-TRN-01636 | 036909C-JVD-TRN-01636 | IFA | 2019-05-27 | 2019-06-17 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-QM-01636 |  | 2019-05-13 | 1
036909C-1000-SP-0184-0002 | MECHANICAL EQUIPMENT DATASHEET FOR HP/ POLYOLEFINS FLARE PACKAGE | 0 | 2019-06-21 | IFP | OL1-2M03-5560 | ME | 2019-06-24 | 036909C-JVD-TRN-01969 | 036909C-JVD-TRN-01969 | IFR | 2019-07-08 | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-ME-01969 |  | 2019-06-25 | 2
036909C-105F-DW-1612-0001 | Earthing And Lightning Protection Layout-Zone 5F HP & Polyolefins Flares | A | 2019-07-05 | IFR | OL1-2E52-0009 | EE | 2019-07-08 | 036909C-JVD-TRN-02089 | 036909C-JVD-TRN-02089 | IFR | 2019-07-22 | 2019-07-15 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02089 |  | 2019-07-08 | 1
036909C-103S-DW-1612-0001 | Earthing And Lightning Protection Layout - Zone 3S Substation & Far C | A | 2019-07-05 | IFR | OL1-2E52-0006 | EE | 2019-07-05 | 036909C-JVD-TRN-02080 | 036909C-JVD-TRN-02080 | IFR | 2019-07-19 | 2019-07-15 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02080 |  | 2019-07-08 | 1
036909C-100S-DW-1612-0001 | Earthing And Lightning Protection Layout - Zone 0S Electrical Substation & Far E | A | 2019-07-05 | IFR | OL1-2E52-0005 | EE | 2019-07-08 | 036909C-JVD-TRN-02089 | 036909C-JVD-TRN-02089 | IFR | 2019-07-22 | 2019-07-15 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02089 |  | 2019-07-08 | 1
036909C-1051-SP-0836-5128 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51025 - PV-5161 Outlet | A | 2019-07-12 | IFQ | OL1-2M03-5128 | ME | 2019-07-12 | 036909C-JVD-TRN-02144 | 036909C-JVD-TRN-02144 | IFR | 2019-07-26 |  | Transmitted | TPSK-LSPA1-T-ME-02144 |  | 2019-07-15 | 2
036909C-1029-SP-0836-2913 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-29012 - Start-up | A | 2019-07-12 | IFQ | OL1-2M03-2913 | ME | 2019-07-12 | 036909C-JVD-TRN-02144 | 036909C-JVD-TRN-02144 | IFR | 2019-07-26 |  | Transmitted | TPSK-LSPA1-T-ME-02144 |  | 2019-07-15 | 2
036909C-1000-DL-4100-0001 | Deviation List for Wet Air Oxidation Package | 0 | 2019-06-19 | IFP | OL1-2C40-704000 | PL | 2019-06-20 | 036909C-JVD-TRN-01943 | 036909C-JVD-TRN-01943 | IFR | 2019-07-04 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PL-01943 |  | 2019-06-20 | 2
036909C-1000-DL-0184-0001 | Deviation List For HP / Polyolefins Flare Package | C | 2019-06-21 | IFR | OL1-2C40-708000 | PL | 2019-06-24 | 036909C-JVD-TRN-01968 | 036909C-JVD-TRN-01968 | IFR | 2019-07-08 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PL-01968 |  | 2019-06-25 | 2
036909C-105W-DW-1612-0001 | Earthing And Lightning Protection Layout - Zone 5W Waste Water Treatment | A | 2019-06-25 | IFR | OL1-2E52-0010 | EE | 2019-06-27 | 036909C-JVD-TRN-02014 | 036909C-JVD-TRN-02014 | IFR | 2019-07-11 | 2019-07-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02014 |  | 2019-06-28 | 1
036909C-100M-DW-1612-0001 | Earthing And Lightning Protection Layout - Zone 0M Metering Station | A | 2019-06-27 | IFR | OL1-2E52-0008 | EE | 2019-06-27 | 036909C-JVD-TRN-02014 | 036909C-JVD-TRN-02014 | IFR | 2019-07-11 | 2019-07-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02014 |  | 2019-06-28 | 1
036909C-100C-DW-1612-0001 | Earthing And Lightning Protection Layout - Zone 0C Common Area | A | 2019-06-27 | IFR | OL1-2E52-0007 | EE | 2019-06-27 | 036909C-JVD-TRN-02014 | 036909C-JVD-TRN-02014 | IFR | 2019-07-11 | 2019-07-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02014 |  | 2019-06-28 | 1
036909C-105T-DW-1612-0001 | Earthing And Lightning Protection Layout - Zone 5T Cooling Water Unit | A | 2019-06-27 | IFR | OL1-2E52-0003 | EE | 2019-06-27 | 036909C-JVD-TRN-02014 | 036909C-JVD-TRN-02014 | IFR | 2019-07-11 | 2019-07-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02014 |  | 2019-06-28 | 1
036909C-1000-JSS-1543-0002 | Job Supply Specification For Electric Operated Valves | A | 2019-06-21 | IFQ | OL1-2I92-0602 | IE | 2019-06-27 | 036909C-JVD-TRN-02016 | 036909C-JVD-TRN-02016 | IFA | 2019-07-12 | 2019-07-09 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-IE-02016 |  | 2019-06-28 | 1
036909C-1000-JSS-1547-0001 | Job Supply Specification For Flow Meters And Flow Elements | A | 2019-06-21 | IFR | OL1-2I92-0100 | IE | 2019-06-27 | 036909C-JVD-TRN-02016 | 036909C-JVD-TRN-02016 | IFA | 2019-07-12 | 2019-07-09 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-IE-02016 |  | 2019-06-27 | 1
036909C-1012-PDS-1546-0001 | Process Data Sheet For Pitot Tube On Cems Furnace Area 12-H-1200-1600 | A | 2019-06-11 | IFR | OL1-2G31-1203 | PE | 2019-06-12 | 036909C-JVD-TRN-01875 | 036909C-JVD-TRN-01875 | IFR | 2019-06-27 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01875 | Instrument datasheet page is the output of SPI software. | 2019-06-14 | 2
036909C-1012-PDS-1560-0002 | Process Data Sheet For CEMS - Area 12 | A | 2019-06-06 | IFR | OL1-2G31-1202 | PE | 2019-06-12 | 036909C-JVD-TRN-01875 | 036909C-JVD-TRN-01875 | IFR | 2019-06-27 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01875 |  | 2019-06-14 | 2
036909C-1011-PDS-1546-0001 | Process Data Sheet For Pitot Tube On Cems Furnace Area 10-H-1100 | A | 2019-06-11 | IFR | OL1-2G31-1103 | PE | 2019-06-12 | 036909C-JVD-TRN-01875 | 036909C-JVD-TRN-01875 | IFR | 2019-06-27 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01875 | Instrument datasheet page is the output of SPI software. | 2019-06-14 | 2
036909C-1011-PDS-1560-0002 | Process Data Sheet For CEMS - Area 11 | A | 2019-06-06 | IFR | OL1-2G31-1102 | PE | 2019-06-12 | 036909C-JVD-TRN-01875 | 036909C-JVD-TRN-01875 | IFR | 2019-06-27 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-PE-01875 |  | 2019-06-14 | 2
036909C-1051-PDS-1111-0002 | Process Data Sheet For General Purpose Steam Turbines - API 611-4TH - PT-5102 A VLP BFW Pump Turbine | A | 2019-06-07 | IFR | OL1-2G30-5171 | PL | 2019-06-12 | 036909C-JVD-TRN-01875 | 036909C-JVD-TRN-01875 | IFR | 2019-06-27 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-PE-01875 |  | 2019-06-14 | 2
036909C-1051-PDS-1111-0001 | Process Data Sheet For General Purpose Steam Turbines - API 611-4TH - PT-5100 A-B SHP BFW Pumps Turbines | A | 2019-06-07 | IFR | OL1-2G30-5170 | PE | 2019-06-12 | 036909C-JVD-TRN-01875 | 036909C-JVD-TRN-01875 | IFR | 2019-06-27 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-PE-01875 |  | 2019-06-14 | 2
036909C-1021-PDS-1111-0002 | Process Data Sheet For General Purpose Steam Turbines - API 611-4TH - PT-2146 A DSG Feed Pump Turbine | A | 2019-06-07 | IFR | OL1-2G30-2171 | PE | 2019-06-12 | 036909C-JVD-TRN-01875 | 036909C-JVD-TRN-01875 | IFR | 2019-06-27 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-PE-01875 |  | 2019-06-14 | 2
036909C-1021-PDS-1111-0001 | Process Data Sheet For General Purpose Steam Turbines - API 611-4TH - PT-2106 A Quench Water Pump Turbine | A | 2019-06-07 | IFR | OL1-2G30-2170 | PE | 2019-06-12 | 036909C-JVD-TRN-01875 | 036909C-JVD-TRN-01875 | IFR | 2019-06-27 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-PE-01875 |  | 2019-06-14 | 2
036909C-1020-PDS-1111-0001 | Process Data Sheet For General Purpose Steam Turbines - API 611-4TH - PT-2006 A Quench Oil Pump Turbine | A | 2019-06-07 | IFR | OL1-2G30-2070 | PE | 2019-06-12 | 036909C-JVD-TRN-01875 | 036909C-JVD-TRN-01875 | IFR | 2019-06-27 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-PE-01875 |  | 2019-06-14 | 2
036909C-1051-PDS-1111-0003 | Process Data Sheet For General Purpose Steam Turbines Pt-5110A Condensate Pump Turbine | A | 2019-06-07 | IFR | OL1-2G30-5172 | PE | 2019-06-11 | 036909C-JVD-TRN-01867 | 036909C-JVD-TRN-01867 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01867 |  | 2019-06-11 | 2
036909C-1051-SP-1111-0001 | Mechanical Data Sheet For General Purpose Turbines PT-5100 A-B SHP BFW Pumps Turbines | 0 | 2019-07-05 | IMP | OL1-2M03-5170 | ME | 2019-07-11 | 036909C-JVD-TRN-02130 | 036909C-JVD-TRN-02130 | IFR | 2019-07-26 |  | Transmitted | TPSK-LSPA1-T-ME-02130 |  | 2019-07-15 | 2
036909C-1000-MR-0661-0001 | Material Requisition For Plate And Frame Heat Exchangers Requisition For Purchase | 1 | 2019-06-20 | IFP | OL1-2C13-142000 | PL | 2019-06-24 | 036909C-JVD-TRN-01971 | 036909C-JVD-TRN-01971 | IFR | 2019-07-09 | 2019-07-04 | R1-No comments | TPSK-LSPA1-T-PL-01971 |  | 2019-06-25 | 2
036909C-1000-MR-0570-0001 | Material Requisition For Trays For Columns Requisition For Purchase | 1 | 2019-06-05 | IFP | OL1-2C13-242000 | PL | 2019-06-10 | 036909C-JVD-TRN-01844 | 036909C-JVD-TRN-01844 | IFR | 2019-06-25 | 2019-06-24 | R1-No comments | TPSK-LSPA1-T-PL-01844 |  | 2019-06-11 | 2
036909C-1000-QCP-2045-0002 | Quality Control Plan Fire Fighting System Installation | A | 2019-05-02 | IFR | OL1-2Q25-0001 | QM | 2019-05-07 | 036909C-JVD-TRN-01596 | 036909C-JVD-TRN-01596 | IFA | 2019-05-22 | 2019-06-19 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-QM-01596 |  | 2019-05-08 | 1
036909C-1026-TDS-0610-2621 | Mechanical Equipment Data Sheet - 10-E-2620 - C3 Hydrog Aftercooler | B | 2019-04-02 | IFQ | OL1-2M03-2621 | ME | 2019-04-02 | 036909C-JVD-TRN-01233 | 036909C-JVD-TRN-01233 | IFR | 2019-04-17 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-01233 |  | 2019-04-03 | 2
036909C-1026-TDS-0610-2621 | Mechanical Equipment Data Sheet - 10-E-2620 - C3 Hydrog Aftercooler | A | 2019-02-21 | IFQ | OL1-2M03-2621 | ME | 2019-02-25 | 036909C-JVD-TRN-00929 | 036909C-JVD-TRN-00929, ROC-TPSK-CECO-T-00018 | IFR | 2019-03-12 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-00929 |  | 2019-02-26 | 2
036909C-1022-TDS-0610-2231 | Mechanical Equipment Data Sheet - 10-E-2230 - CG 3rd Stage Aftercooler | B | 2019-03-19 | IFQ | OL1-2M03-2231 | ME | 2019-03-20 | 036909C-JVD-TRN-01110 | 036909C-JVD-TRN-01110, ROC-TPSK-CECO-T-00017 | IFR | 2019-04-04 | 2019-04-11 | TPSK-LSPA1-E-00150 April 24 2019 - R2-Comments as noted | TPSK-LSPA1-T-ME-01110 |  | 2019-03-21 | 2
036909C-1055-TDS-0610-5513 | Mechanical Equipment Data Sheet - 10-E-5513 - Methanol Vaporizer | A | 2019-01-23 | IFQ | OL1-2M03-5513 | ME | 2019-01-25 | 036909C-JVD-TRN-00723 | 036909C-JVD-TRN-00723, ROC-TPSK-CECO-T-00018 | IFR | 2019-02-07 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00723 |  | 2019-01-25 | 2
036909C-1027-TDS-0610-2765 | Mechanical Equipment Data Sheet - 10-E-2765 - C4 - C5 Hydrog Recycle Cooler | B | 2019-03-29 | IFQ | OL1-2M03-2765 | ME | 2019-04-03 | 036909C-JVD-TRN-01242 | 036909C-JVD-TRN-01242 | IFR | 2019-04-18 |  | Transmitted | TPSK-LSPA1-T-ME -01242 |  | 2019-04-04 | 2
036909C-1027-TDS-0610-2765 | Mechanical Equipment Data Sheet - 10-E-2765 - C4 -C5 Hydrog Recycle Cooler | A | 2019-03-04 | IFQ | OL1-2M03-2765 | ME | 2019-03-05 | 036909C-JVD-TRN-00991 | 036909C-JVD-TRN-00991, ROC-TPSK-CECO-T-00018 | IFR | 2019-03-20 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-00991 |  | 2019-03-05 | 2
036909C-1027-TDS-0610-2763 | Mechanical Equipment Data Sheet - 10-E-2760 - C4-C5 Hydro Vent Condenser | A | 2019-03-07 | IFQ | OL1-2M03-2763 | ME | 2019-03-15 | 036909C-JVD-TRN-01075 | 036909C-JVD-TRN-01075 | IFR | 2019-04-01 | 2019-05-02 | TPSK-LSPA1-E-00190 May 09 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01075 |  | 2019-03-18 | 2
036909C-1027-TDS-0610-2703 | Mechanical Equipment Data Sheet - 10-E-2705 - GHU-1 Recycle Cooler | A | 2019-02-18 | IFQ | OL1-2M03-2703 | ME | 2019-02-19 | 036909C-JVD-TRN-00895 | 036909C-JVD-TRN-00895, ROC-TPSK-CECO-T-00018 | IFR | 2019-03-06 | 2019-03-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00895 |  | 2019-02-19 | 2
036909C-1024-TDS-0610-2472 | Mechanical Equipment Data Sheet - 10-E-2472 - C2 Hydrog 2nd Stage Intercooler | B | 2019-03-29 | IFQ | OL1-2M03-2472 | ME | 2019-03-29 | 036909C-JVD-TRN-01205 | 036909C-JVD-TRN-01205 | IFR | 2019-04-15 | 2019-05-02 | TPSK-LSPA1-E-00190 May 09 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01205 |  | 2019-04-01 | 2
036909C-1024-TDS-0610-2471 | Mechanical Equipment Data Sheet - 10-E-2470 - C2 Hydrog 1st Stage Intercooler | B | 2019-03-30 | IFQ | OL1-2M03-2471 | ME | 2019-04-02 | 036909C-JVD-TRN-01231 | 036909C-JVD-TRN-01231 | IFR | 2019-04-17 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-01231 |  | 2019-04-03 | 2
036909C-1024-TDS-0610-2461 | Mechanical Equipment Data Sheet - 10-E-2460 - C2 Hydrog Feed Cooler | B | 2019-03-20 | IFQ | OL1-2M03-2461 | ME | 2019-03-27 | 036909C-JVD-TRN-01179 | 036909C-JVD-TRN-01179 | IFR | 2019-04-11 | 2019-05-02 | TPSK-LSPA1-E-00190 May 09 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01179 |  | 2019-03-28 | 2
036909C-1022-TDS-0610-2221 | Mechanical Equipment Data Sheet - 10-E-2220 - CG 2nd Stage After cooler | B | 2019-03-19 | IFQ | OL1-2M03-2221 | ME | 2019-03-20 | 036909C-JVD-TRN-01110 | 036909C-JVD-TRN-01110, ROC-TPSK-CECO-T-00017 | IFR | 2019-04-04 | 2019-04-11 | TPSK-LSPA1-E-00150 April 24 2019- R2-Comments as noted | TPSK-LSPA1-T-ME-01110 |  | 2019-03-21 | 2
036909C-1022-TDS-0610-2211 | Mechanical Equipment Data Sheet - 10-E-2210 A-B - CG 1st Stage Aftercoolers | B | 2019-03-19 | IFQ | OL1-2M03-2211 | ME | 2019-03-20 | 036909C-JVD-TRN-01110 | 036909C-JVD-TRN-01110, ROC-TPSK-CECO-T-00017 | IFR | 2019-04-04 | 2019-04-11 | TPSK-LSPA1-E-00176 May 08 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-01110 |  | 2019-03-21 | 2
036909C-1000-STC-1790-0001 | Construction Standards For Reinforced Concrete Works | 0 | 2019-02-26 | IFC | OL1-2K20-0001 | CV | 2019-03-06 | 036909C-JVD-TRN-00997 | 036909C-JVD-TRN-00997, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFA | 2019-03-21 | 2019-03-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00997 |  | 2019-03-07 | 1
036909C-1000-DW-1522-0002 | Instrument And Telecom Grounding Philosophy Diagram | A | 2019-03-05 | IFR | OL1-2I48-1001 | IE | 2019-03-08 | 036909C-JVD-TRN-01013 | 036909C-JVD-TRN-01013 | IFA | 2019-03-25 | 2019-05-15 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-IE-01013 |  | 2019-03-11 | 1
036909C-102D-DW-1980-0001 | Passive Fire Protection Drawing - Zone 2D - Process Cold Compressor | B | 2019-06-14 | IBD | OL1-2F45-0005 | FF | 2019-06-18 | 036909C-JVD-TRN-01914 | 036909C-JVD-TRN-01914 | IFR | 2019-07-02 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-FF-01914 |  | 2019-06-18 | 2
036909C-102C-DW-1980-0001 | Passive Fire Protection Drawing - Zone 2C - Hot Fractionation / GHU Unit | B | 2019-06-14 | IBD | OL1-2F45-0004 | FF | 2019-06-18 | 036909C-JVD-TRN-01914 | 036909C-JVD-TRN-01914 | IFR | 2019-07-02 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-FF-01914 |  | 2019-06-18 | 2
036909C-102B-DW-1980-0001 | Passive Fire Protection Drawing - Zone 2b - C3 Hydrogenation | B | 2019-06-14 | IBD | OL1-2F45-0003 | FF | 2019-06-18 | 036909C-JVD-TRN-01914 | 036909C-JVD-TRN-01914 | IFR | 2019-07-02 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-FF-01914 |  | 2019-06-18 | 2
036909C-102A-DW-1980-0001 | Passive Fire Protection Drawing - Zone 2A - Quench | B | 2019-06-14 | IBD | OL1-2F45-0002 | FF | 2019-06-18 | 036909C-JVD-TRN-01914 | 036909C-JVD-TRN-01914 | IFR | 2019-07-02 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-FF-01914 |  | 2019-06-18 | 2
036909C-101B-DW-1980-0001 | Passive Fire Protection Drawing - Zone 1B - Furnace Utilities | B | 2019-06-14 | IBD | OL1-2F45-0001 | FF | 2019-06-18 | 036909C-JVD-TRN-01914 | 036909C-JVD-TRN-01914 | IFR | 2019-07-02 | 2019-07-12 | R2-Comments as noted | TPSK-LSPA1-T-FF-01914 |  | 2019-06-18 | 2
036909C-1000-DW-1980-0001 | Overall Passive Fire Protection Drawing | B | 2019-06-14 | IBD | OL1-2F45-1000 | FF | 2019-06-18 | 036909C-JVD-TRN-01914 | 036909C-JVD-TRN-01914 | IFR | 2019-07-02 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-FF-01914 |  | 2019-06-18 | 2
036909C-1031-PDS-0900-3191 | Process Equipment Data Sheet - 10-P-3190 - Solvent Slop Pump | B | 2019-06-18 | IFD | OL1-2G30-3191 | PE | 2019-06-20 | 036909C-JVD-TRN-01945 | 036909C-JVD-TRN-01945 | IFR | 2019-07-05 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01945 |  | 2019-06-21 | 2
036909C-1031-PDS-0900-3162 | Process Equipment Data Sheet - 10-P-3160 - BDU Condensate Recycle Pump | B | 2019-06-18 | IFD | OL1-2G30-3162 | PE | 2019-06-20 | 036909C-JVD-TRN-01947 | 036909C-JVD-TRN-01947 | IFA | 2019-07-05 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01947 |  | 2019-06-21 | 2
036909C-1031-PDS-0900-3127 | Process Equipment Data Sheet - 10-P-3126 A-B - BDU Ejector Seal Drum Pump | B | 2019-06-18 | IFD | OL1-2G30-3127 | PE | 2019-06-20 | 036909C-JVD-TRN-01947 | 036909C-JVD-TRN-01947 | IFA | 2019-07-05 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01947 |  | 2019-06-21 | 2
036909C-1031-PDS-0900-3113 | Process Equipment Data Sheet - 10-P-3110 A-B - Solvent Return Pump | B | 2019-06-18 | IFD | OL1-2G30-3113 | PE | 2019-06-20 | 036909C-JVD-TRN-01947 | 036909C-JVD-TRN-01947 | IFA | 2019-07-05 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01947 |  | 2019-06-21 | 2
036909C-1030-PDS-0900-3097 | Process Equipment Data Sheet - 10-P-3096 A-B Butadiene Product Pumps | B | 2019-06-18 | IFD | OL1-2G30-3097 | PE | 2019-06-20 | 036909C-JVD-TRN-01946 | 036909C-JVD-TRN-01946 | IFR | 2019-07-05 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01946 |  | 2019-06-21 | 2
036909C-1030-PDS-0900-3086 | Process Equipment Data Sheet - 10-P-3086 A-B Butadiene Tower Bottom Pump | B | 2019-06-18 | IFD | OL1-2G30-3086 | PE | 2019-06-20 | 036909C-JVD-TRN-01946 | 036909C-JVD-TRN-01946 | IFR | 2019-07-05 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01946 |  | 2019-06-21 | 2
036909C-1030-PDS-0900-3083 | Process Equipment Data Sheet - 10-P-3080 A-B Butadiene Tower Reflux Pumps | B | 2019-06-18 | IFD | OL1-2G30-3083 | PE | 2019-06-20 | 036909C-JVD-TRN-01946 | 036909C-JVD-TRN-01946 | IFR | 2019-07-05 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01946 |  | 2019-06-21 | 2
036909C-1030-PDS-0900-3076 | Process Equipment Data Sheet - 10-P-3076 A-B - Direct Cooler Pump | B | 2019-06-18 | IFD | OL1-2G30-3076 | PE | 2019-06-20 | 036909C-JVD-TRN-01946 | 036909C-JVD-TRN-01946 | IFR | 2019-07-05 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01946 |  | 2019-06-21 | 2
036909C-1030-PDS-0900-3061 | Process Equipment Data Sheet - 10-P-3061 A-B - Dimer Pump | B | 2019-06-18 | IFD | OL1-2G30-3061 | PE | 2019-06-20 | 036909C-JVD-TRN-01945 | 036909C-JVD-TRN-01945 | IFR | 2019-07-05 | 2019-07-11 | R1-No comments | TPSK-LSPA1-T-PE-01945 |  | 2019-06-21 | 2
036909C-1030-DI-0007-3001 | Area Basis of Design - 30 BDU | B | 2019-06-10 | IFD | OL1-2G05-3001 | PE | 2019-06-19 | 036909C-JVD-TRN-01932 | 036909C-JVD-TRN-01932 | IFR | 2019-07-04 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-01932 |  | 2019-06-20 | 1
036909C-1030-SP-1547-3006 | Instrument Datasheets for Flow Element Coriolis Area 30 | A | 2019-06-25 | IFQ | OL1-2I20-3030 | IE | 2019-06-26 | 036909C-JVD-TRN-02000 | 036909C-JVD-TRN-02000 | IFI |  | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-IE-02000 |  | 2019-06-27 | 3
036909C-102D-DW-1744-0001-002 | Concrete Basin 10-PIT-5604 | A | 2019-07-05 | IFR | OL1-2K31-3041 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-102B-DW-1744-0001-002 | Foundation For Basin 10-PIT-2190 | A | 2019-07-02 | IFR | OL1-2K31-2601 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-1053-SP-0910-5352 | Mechanical Equipment Datasheet - Olefins Cooling Water Pumps | 0 | 2019-07-02 | IFP | OL1-2M03-5352 | ME | 2019-07-10 | 036909C-JVD-TRN-02115 | 036909C-JVD-TRN-02115 | IFR | 2019-07-24 |  | Transmitted | TPSK-LSPA1-T-ME-02115 |  | 2019-07-11 | 2
036909C-102D-DW-1744-0001-001 | Concrete Basin 10-PIT-5604 | A | 2019-07-05 | IFR | OL1-2K31-3040 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-102B-DW-1844-0001-001 | Steel Railing For Protection Of Basin 10-PIT-2190 | A | 2019-07-02 | IFR | OL1-2K32-7480 | CV | 2019-07-10 | 036909C-JVD-TRN-02117 | 036909C-JVD-TRN-02117 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02117 |  | 2019-07-11 | 1
036909C-102A-DW-1744-0002-002 | Concrete Basin 10-PIT-5602 | A | 2019-07-02 | IFR | OL1-2K31-2541 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-101B-DW-1744-0002-002 | Concrete Basin 10-PIT-5610 | A | 2019-07-05 | IFR | OL1-2K31-4461 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-102B-DW-1744-0001-001 | Foundation For Basin 10-PIT-2190 | A | 2019-07-02 | IFR | OL1-2K31-2600 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-102A-DW-1744-0002-001 | Concrete Basin 10-PIT-5602 | A | 2019-07-02 | IFR | OL1-2K31-2540 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1841-0002-009 | Steel For Piperack 10-PRK-0P02 - Elevations - | A | 2019-06-28 | IFR | OL1-2K32-7108 | CV | 2019-07-10 | 036909C-JVD-TRN-02117 | 036909C-JVD-TRN-02117 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02117 |  | 2019-07-11 | 1
036909C-101B-DW-1744-0002-001 | Concrete Basin 10-PIT-5610 | A | 2019-07-05 | IFR | OL1-2K31-4460 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1841-0002-010 | Steel For Piperack 10-PRK-0P02 - Details - | A | 2019-06-28 | IFR | OL1-2K32-7109 | CV | 2019-07-10 | 036909C-JVD-TRN-02117 | 036909C-JVD-TRN-02117 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02117 |  | 2019-07-11 | 1
036909C-100P-DW-1841-0002-004 | Steel For Piperack 10-PRK-0P02 - Plans - | A | 2019-06-28 | IFR | OL1-2K32-7103 | CV | 2019-07-10 | 036909C-JVD-TRN-02117 | 036909C-JVD-TRN-02117 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02117 |  | 2019-07-11 | 1
036909C-100P-DW-1841-0002-001 | Steel For Piperack 10-PRK-0P02 - 3D View - | A | 2019-06-28 | IFR | OL1-2K32-7100 | CV | 2019-07-10 | 036909C-JVD-TRN-02117 | 036909C-JVD-TRN-02117 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02117 |  | 2019-07-11 | 1
036909C-100P-DW-1841-0002-002 | Steel For Piperack 10-PRK-0P02 - Plans- | A | 2019-06-28 | IFR | OL1-2K32-7101 | CV | 2019-07-10 | 036909C-JVD-TRN-02117 | 036909C-JVD-TRN-02117 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02117 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-022 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Steel Bracings Details - | A | 2019-06-28 | IFR | OL1-2K31-5141 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-021 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Steel Bracings Details - | A | 2019-06-28 | IFR | OL1-2K31-5140 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1841-0002-006 | Steel For Piperack 10-PRK-0P02 - Elevations - | A | 2019-06-28 | IFR | OL1-2K32-7105 | CV | 2019-07-10 | 036909C-JVD-TRN-02117 | 036909C-JVD-TRN-02117 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02117 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-020 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Steel Bracings Details - | A | 2019-06-28 | IFR | OL1-2K31-1079 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1841-0002-007 | Steel For Piperack 10-PRK-0P02 - Elevations - | A | 2019-06-28 | IFR | OL1-2K32-7106 | CV | 2019-07-10 | 036909C-JVD-TRN-02117 | 036909C-JVD-TRN-02117 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02117 |  | 2019-07-11 | 1
036909C-100P-DW-1841-0002-003 | Steel For Piperack 10-PRK-0P02 (Plans) | A | 2019-06-28 | IFR | OL1-2K32-7102 | CV | 2019-07-10 | 036909C-JVD-TRN-02117 | 036909C-JVD-TRN-02117 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02117 |  | 2019-07-11 | 1
036909C-100P-DW-1841-0002-005 | Steel For Piperack 10-PRK-0P02 - Plans And Section - | A | 2019-06-28 | IFR | OL1-2K32-7104 | CV | 2019-07-10 | 036909C-JVD-TRN-02117 | 036909C-JVD-TRN-02117 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02117 |  | 2019-07-11 | 1
036909C-100P-DW-1841-0002-008 | Steel For Piperack 10-PRK-0P02 - Elevations - | A | 2019-06-28 | IFR | OL1-2K32-7107 | CV | 2019-07-10 | 036909C-JVD-TRN-02117 | 036909C-JVD-TRN-02117 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02117 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-010 | Precast Concrete Elevation For Piperack 10-PRK-0P02 -Columns - | A | 2019-06-28 | IFR | OL1-2K31-1069 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-015 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Beams - | A | 2019-06-28 | IFR | OL1-2K31-1074 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-011 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Columns - | A | 2019-06-28 | IFR | OL1-2K31-1070 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-013 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Columns - | A | 2019-06-28 | IFR | OL1-2K31-1072 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-012 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Columns - | A | 2019-06-28 | IFR | OL1-2K31-1071 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-017 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Beams - | A | 2019-06-28 | IFR | OL1-2K31-1076 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-019 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Steel Bracings Details - | A | 2019-06-28 | IFR | OL1-2K31-1078 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-016 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Beams - | A | 2019-06-28 | IFR | OL1-2K31-1075 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-014 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Beams - | A | 2019-06-28 | IFR | OL1-2K31-1073 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-018 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Beams - | A | 2019-06-28 | IFR | OL1-2K31-1077 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-002 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Plans - | A | 2019-06-28 | IFR | OL1-2K31-1061 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0003-001 | Foundation And Elevation Of Piperack 10-PRK-0P02 - Formwork And Reinforcement - | A | 2019-06-28 | IFR | OL1-2K31-1040 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0003-002 | Foundation And Elevation Of Piperack 10-PRK-0P02 - Formwork And Reinforcement - | A | 2019-06-28 | IFR | OL1-2K31-1041 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-001 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - 3D View - | A | 2019-06-28 | IFR | OL1-2K31-1060 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-009 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Columns - | A | 2019-06-28 | IFR | OL1-2K31-1068 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-006 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Elevations - | A | 2019-06-28 | IFR | OL1-2K31-1065 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-007 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Elevations - | A | 2019-06-28 | IFR | OL1-2K31-1066 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-005 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Elevations - | A | 2019-06-28 | IFR | OL1-2K31-1064 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-003 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Plans - | A | 2019-06-28 | IFR | OL1-2K31-1062 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-008 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Columns - | A | 2019-06-28 | IFR | OL1-2K31-1067 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-DW-1741-0004-004 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Elevations - | A | 2019-06-28 | IFR | OL1-2K31-1063 | CV | 2019-07-10 | 036909C-JVD-TRN-02116 | 036909C-JVD-TRN-02116 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02116 |  | 2019-07-11 | 1
036909C-100P-CN-1831-0002 | Calculation Note For Steel Pipe Rack 10-PRK-0P02 | A | 2019-06-28 | IFR | OL1-2K15-0002 | CV | 2019-07-10 | 036909C-JVD-TRN-02121 | 036909C-JVD-TRN-02121 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02121 |  | 2019-07-11 | 1
036909C-100P-CN-1731-0003 | Calculation Note For Foundations Of Pipe Rack 10-PRK-0P02 | A | 2019-06-28 | IFR | OL1-2K14-0003 | CV | 2019-07-10 | 036909C-JVD-TRN-02121 | 036909C-JVD-TRN-02121 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02121 |  | 2019-07-11 | 1
036909C-100P-CN-1731-0004 | Calculation Note For Precast Concrete Pipe Rack 10-PRK-0P02 | A | 2019-06-28 | IFR | OL1-2K14-0004 | CV | 2019-07-10 | 036909C-JVD-TRN-02121 | 036909C-JVD-TRN-02121 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02121 |  | 2019-07-11 | 1
036909C-1000-DW-1702-0002 | General Notes For Precast Concrete Works | 0 | 2019-07-09 | IFC | OL1-2K92-0002 | CV | 2019-07-10 | 036909C-JVD-TRN-02119 | 036909C-JVD-TRN-02119 | IFA | 2019-07-25 |  | Transmitted | TPSK-LSPA1-T-CV-02119 |  | 2019-07-11 | 1
036909C-102B-DW-1552-0001 | Level Instrument Design C3 Hydrogenation ISBL | A | 2019-05-31 | IFR | OL1-2I31-0204 | IE | 2019-06-13 | 036909C-JVD-TRN-01888 | 036909C-JVD-TRN-01888 | IFA | 2019-06-28 | 2019-07-01 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-01888 |  | 2019-06-14 | 1
036909C-105F-DW-1552-0001 | Level Instrument Design Flare Unit; OSBL | A | 2019-06-07 | IFR | OL1-2I31-0210 | IE | 2019-06-13 | 036909C-JVD-TRN-01888 | 036909C-JVD-TRN-01888 | IFA | 2019-06-28 | 2019-07-01 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-01888 |  | 2019-06-14 | 1
036909C-1000-MR-0411-0001 | Material Requisition For Reactors And Thicker Vessels Requisition For Purchase | 0 | 2019-06-21 | IFP | OL1-2C13-111000 | PL | 2019-06-24 | 036909C-JVD-TRN-01972 | 036909C-JVD-TRN-01972 | IFR | 2019-07-09 | 2019-07-04 | R2-Comments as noted | TPSK-LSPA1-T-PL-01972 |  | 2019-06-25 | 2
036909C-1000-DL-0910-0003 | Deviation List for Cooling Water Pumps | 0 | 2019-07-09 | IFP | OL1-2C40-440003 | PL | 2019-07-10 | 036909C-JVD-TRN-02114 | 036909C-JVD-TRN-02114 | IFR | 2019-07-24 |  | Transmitted | TPSK-LSPA1-T-PL-02114 |  | 2019-07-10 | 2
036909C-1023-PDS-0800-2331 | Process Equipment Datasheet - 10-D-2330 - Spent Caustic Stripper Ovhd Drum | E | 2019-05-20 | IFD | OL1-2G30-2331 | PE | 2019-05-20 | 036909C-JVD-TRN-01694 | 036909C-JVD-TRN-01694 | IFR | 2019-06-04 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-PE-01694 |  | 2019-05-21 | 2
036909C-1023-PDS-0800-2331 | Process Equipment Datasheet - 10-D-2330 - Spent Caustic Stripper Ovhd Drum | B | 2019-01-10 | IFD | OL1-2G30-2331 | PE | 2019-01-11 | 036909C-JVD-TRN-00634 | 036909C-JVD-TRN-00634 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00634 |  | 2019-01-11 | 2
036909C-102A-DW-1552-0001 | Level Instrument Design Quench ISBL | A | 2019-04-16 | IFR | OL1-2I31-0203 | IE | 2019-04-18 | 036909C-JVD-TRN-01413 | 036909C-JVD-TRN-01413 | IFA | 2019-05-03 | 2019-05-18 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-IE-01413 |  | 2019-04-19 | 1
036909C-1012-DL-0155-2018 | Deviation List for Furnace Steam Drums | B | 2019-06-12 | IFR | OL1-2C40-305000 | PL | 2019-06-24 | 036909C-JVD-TRN-01974 | 036909C-JVD-TRN-01974 | IFR | 2019-07-09 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PL-01974 |  | 2019-06-25 | 2
036909C-1012-DW-0132-2108 | USC 132U Cracking Furnace Decoke Nozzle Details | 1 | 2019-06-06 | IMP | OL1-2M06-2108 | ME | 2019-06-12 | 036909C-JVD-TRN-01876 | 036909C-JVD-TRN-01876 | IFR | 2019-06-27 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01876 |  | 2019-06-14 | 2
036909C-1011-DW-0132-1108 | USC 36M Recycle Furnace Decoke Nozzle Details | 1 | 2019-06-06 | IMP | OL1-2M06-1108 | ME | 2019-06-12 | 036909C-JVD-TRN-01876 | 036909C-JVD-TRN-01876 | IFR | 2019-06-27 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01876 |  | 2019-06-14 | 2
036909C-1012-DW-0132-2107 | USC 132U Cracking Furnace SLE Assembly Insulation Details | 0 | 2019-06-06 | IMP | OL1-2M06-2107 | ME | 2019-06-12 | 036909C-JVD-TRN-01876 | 036909C-JVD-TRN-01876 | IFR | 2019-06-27 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01876 |  | 2019-06-14 | 2
036909C-1011-DW-0132-1107 | USC 36M Recycle Furnace USX Assembly Insulation Details | 0 | 2019-06-06 | IMP | OL1-2M06-1107 | ME | 2019-06-12 | 036909C-JVD-TRN-01876 | 036909C-JVD-TRN-01876 | IFR | 2019-06-27 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01876 |  | 2019-06-14 | 2
036909C-1012-DW-0132-2101 | USC 132U Cracking Furnace Refractory and Insulation Radiant Section Details | 1 | 2019-06-06 | IMP | OL1-2M06-2101 | ME | 2019-06-12 | 036909C-JVD-TRN-01876 | 036909C-JVD-TRN-01876 | IFR | 2019-06-27 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01876 |  | 2019-06-14 | 2
036909C-1011-DW-0132-1101 | USC 36M Recycle Furnace Refractory and Insulation Radiant Section Details | 1 | 2019-06-06 | IMP | OL1-2M06-1101 | ME | 2019-06-12 | 036909C-JVD-TRN-01876 | 036909C-JVD-TRN-01876 | IFR | 2019-06-27 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01876 |  | 2019-06-14 | 2
036909C-100P-DW-1841-0001-009 | Steel For Pipe Rack 10-PRK-0P01 - Details | A | 2019-05-21 | IFR | OL1-2K32-7008 | CV | 2019-05-27 | 036909C-JVD-TRN-01748 | 036909C-JVD-TRN-01748 | IFA | 2019-06-11 | 2019-07-05 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01748 |  | 2019-05-28 | 1
036909C-100P-DW-1841-0001-008 | Steel For Pipe Rack 10-PRK-0P01 - Elevations - Stair | A | 2019-05-21 | IFR | OL1-2K32-7007 | CV | 2019-05-27 | 036909C-JVD-TRN-01748 | 036909C-JVD-TRN-01748 | IFA | 2019-06-11 | 2019-07-05 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01748 |  | 2019-05-28 | 1
036909C-100P-DW-1841-0001-007 | Steel For Pipe Rack 10-PRK-0P01 - Elevations | A | 2019-05-21 | IFR | OL1-2K32-7006 | CV | 2019-05-27 | 036909C-JVD-TRN-01748 | 036909C-JVD-TRN-01748 | IFA | 2019-06-11 | 2019-07-05 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01748 |  | 2019-05-28 | 1
036909C-100P-DW-1841-0001-006 | Steel For Pipe Rack 10-PRK-0P01 - Elevations | A | 2019-05-21 | IFR | OL1-2K32-7005 | CV | 2019-05-27 | 036909C-JVD-TRN-01748 | 036909C-JVD-TRN-01748 | IFA | 2019-06-11 | 2019-07-05 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01748 |  | 2019-05-28 | 1
036909C-100P-DW-1841-0001-005 | Steel For Pipe Rack 10-PRK-0P01 - Elevations | A | 2019-05-21 | IFR | OL1-2K32-7004 | CV | 2019-05-27 | 036909C-JVD-TRN-01748 | 036909C-JVD-TRN-01748 | IFA | 2019-06-11 | 2019-07-05 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01748 |  | 2019-05-28 | 1
036909C-100P-DW-1841-0001-004 | Steel For Pipe Rack 10-PRK-0P01 - Plans | A | 2019-05-21 | IFR | OL1-2K32-7003 | CV | 2019-05-27 | 036909C-JVD-TRN-01748 | 036909C-JVD-TRN-01748 | IFA | 2019-06-11 | 2019-07-05 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01748 |  | 2019-05-28 | 1
036909C-100P-DW-1841-0001-003 | Steel For Pipe Rack 10-PRK-0P01 - Plans | A | 2019-05-21 | IFR | OL1-2K32-7002 | CV | 2019-05-27 | 036909C-JVD-TRN-01748 | 036909C-JVD-TRN-01748 | IFA | 2019-06-11 | 2019-07-05 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01748 |  | 2019-05-28 | 1
036909C-1030-SP-1547-3001 | Instrument Datasheets for Flow Instrument Vortex Area 30 | A | 2019-07-03 | IFQ | OL1-2I20-3027 | IE | 2019-07-09 | 036909C-JVD-TRN-02110 | 036909C-JVD-TRN-02110 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-02110 |  | 2019-07-10 | 3
036909C-102C-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 2C Hot Fractionation/GHU Unit | B | 2019-07-01 | IBD | OL1-2F75-0015 | FF | 2019-07-02 | 036909C-JVD-TRN-02048 | 036909C-JVD-TRN-02048 | IFR | 2019-07-16 |  | Transmitted | TPSK-LSPA1-T-FF-02048 |  | 2019-07-03 | 2
036909C-100P-DW-1841-0001-002 | Steel For Pipe Rack 10-PRK-0P01- Plans | A | 2019-05-21 | IFR | OL1-2K32-7001 | CV | 2019-05-27 | 036909C-JVD-TRN-01748 | 036909C-JVD-TRN-01748 | IFA | 2019-06-11 | 2019-07-05 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01748 |  | 2019-05-28 | 1
036909C-100P-DW-1841-0001-001 | Steel For Pipe Rack 10-PRK-0P01 - 3D View | A | 2019-05-21 | IFR | OL1-2K32-7000 | CV | 2019-05-27 | 036909C-JVD-TRN-01748 | 036909C-JVD-TRN-01748 | IFA | 2019-06-11 | 2019-07-05 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01748 |  | 2019-05-28 | 1
036909C-105U-DW-1552-0001 | Level Instrument Design Utilities OSBL | A | 2019-06-14 | IFR | OL1-2I31-0212 | IE | 2019-06-21 | 036909C-JVD-TRN-01964 | 036909C-JVD-TRN-01964 | IFA | 2019-07-08 | 2019-07-05 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-01964 |  | 2019-06-24 | 1
036909C-105T-DW-1552-0001 | Level Instument Design And Nozzle Studies For Cooling Water Unit OSBL 5T | A | 2019-06-24 | IFR | OL1-2I31-0211 | IE | 2019-06-21 | 036909C-JVD-TRN-01964 | 036909C-JVD-TRN-01964 | IFA | 2019-07-08 | 2019-07-05 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-01964 |  | 2019-06-24 | 1
036909C-102D-DW-1552-0001 | Level Instrument Design Process Cold Compressors ISBL | A | 2019-06-14 | IFR | OL1-2I31-0206 | IE | 2019-06-21 | 036909C-JVD-TRN-01964 | 036909C-JVD-TRN-01964 | IFA | 2019-07-08 | 2019-07-05 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-01964 |  | 2019-06-24 | 1
036909C-102C-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 2C Hot Fractionation/GHU Unit | A | 2019-03-29 | IFR | OL1-2F75-0015 | FF | 2019-03-29 | 036909C-JVD-TRN-01191 | 036909C-JVD-TRN-01191, KLOC-TPSK-VSAFE-T-00002 | IFR | 2019-04-11 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01191 |  | 2019-03-29 | 2
036909C-103A-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 3A Butadiene Extraction Unit | A | 2019-03-29 | IFR | OL1-2F75-0014 | FF | 2019-03-29 | 036909C-JVD-TRN-01191 | 036909C-JVD-TRN-01191, KLOC-TPSK-VSAFE-T-00002 | IFR | 2019-04-11 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01191 |  | 2019-03-29 | 2
036909C-102E-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 2E Cracked Gas Compressor | A | 2019-03-29 | IFR | OL1-2F75-0013 | FF | 2019-03-29 | 036909C-JVD-TRN-01191 | 036909C-JVD-TRN-01191, KLOC-TPSK-VSAFE-T-00002 | IFR | 2019-04-11 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01191 |  | 2019-03-29 | 2
036909C-102D-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 2D Process Cold Compressor | A | 2019-03-29 | IFR | OL1-2F75-0012 | FF | 2019-03-29 | 036909C-JVD-TRN-01191 | 036909C-JVD-TRN-01191, KLOC-TPSK-VSAFE-T-00002 | IFR | 2019-04-11 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01191 |  | 2019-03-29 | 2
036909C-102B-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 2B C3 Hydrogenation | A | 2019-03-29 | IFR | OL1-2F75-0011 | FF | 2019-03-29 | 036909C-JVD-TRN-01191 | 036909C-JVD-TRN-01191, KLOC-TPSK-VSAFE-T-00002 | IFR | 2019-04-11 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01191 |  | 2019-03-29 | 2
036909C-102A-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 2A Quench | A | 2019-03-29 | IFR | OL1-2F75-0010 | FF | 2019-03-29 | 036909C-JVD-TRN-01191 | 036909C-JVD-TRN-01191, KLOC-TPSK-VSAFE-T-00002 | IFR | 2019-04-11 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01191 |  | 2019-03-29 | 2
036909C-101B-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - - Zone 1B Furnaces Utility | A | 2019-03-29 | IFR | OL1-2F75-0009 | FF | 2019-03-29 | 036909C-JVD-TRN-01191 | 036909C-JVD-TRN-01191, KLOC-TPSK-VSAFE-T-00002 | IFR | 2019-04-11 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01191 |  | 2019-03-29 | 2
036909C-105U-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 5U Utilities | A | 2019-03-29 | IFR | OL1-2F75-0005 | FF | 2019-03-29 | 036909C-JVD-TRN-01191 | 036909C-JVD-TRN-01191, KLOC-TPSK-VSAFE-T-00002 | IFR | 2019-04-11 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01191 |  | 2019-03-29 | 2
036909C-105W-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 5W Waste Water Treatment | A | 2019-03-29 | IFR | OL1-2F75-0004 | FF | 2019-03-29 | 036909C-JVD-TRN-01191 | 036909C-JVD-TRN-01191, KLOC-TPSK-VSAFE-T-00002 | IFR | 2019-04-11 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01191 |  | 2019-03-29 | 2
036909C-105T-DW-1960-0001 | Life Saving Equipment and Escape Route Layout - Zone 5T Cooling Water Unit | A | 2019-03-29 | IFR | OL1-2F75-0003 | FF | 2019-03-29 | 036909C-JVD-TRN-01191 | 036909C-JVD-TRN-01191, KLOC-TPSK-VSAFE-T-00002 | IFR | 2019-04-11 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01191 |  | 2019-03-29 | 2
036909C-1011-JSD-1513-1101 | Instrument Interlock Descriptions Area 11 - 10-H-1100 | A | 2019-04-15 | IFR | OL1-2G50-1101 | PE | 2019-04-16 | 036909C-JVD-TRN-01367 | 036909C-JVD-TRN-01367 | IFR | 2019-05-01 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-01367 |  | 2019-04-17 | 2
036909C-1000-JSS-0184-0001 | ME-021 FLARE SYSTEM | 0 | 2019-06-21 | IMP | OL1-2R03-0021 | ME | 2019-06-24 | 036909C-JVD-TRN-01969 | 036909C-JVD-TRN-01969 | IFR | 2019-07-08 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-ME-01969 |  | 2019-06-25 | 2
036909C-101A-ML-251 | Model Review Report Furnace Island Action List 30 Percent | A | 2019-03-18 | IFR | OL1-2P30-0014 | MP | 2019-04-11 | 036909C-JVD-TRN-01331 | 036909C-JVD-TRN-01331 | IFR | 2019-04-26 | 2019-05-27 | R2-Comments as noted | TPSK-LSPA1-T-MP-01331 |  | 2019-04-12 | 2
036909C-1000-DL-0910-0003 | Deviation List for Cooling Water Pumps | B | 2019-05-06 | IFA | OL1-2C40-440003 | PL | 2019-05-07 | 036909C-JVD-TRN-01591 | 036909C-JVD-TRN-01591 | IFA | 2019-05-21 |  | Transmitted | TPSK-LSPA1-T-PL-01591 |  | 2019-05-08 | 2
036909C-1012-JSD-1513-1201 | Instrument Interlock Descriptions Area 12-16 | A | 2019-05-01 | IFR | OL1-2G50-1201 | IE | 2019-05-02 | 036909C-JVD-TRN-01561 | 036909C-JVD-TRN-01561 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-IE-01561 |  | 2019-05-03 | 2
036909C-100P-NM-1350-0030 | Loads On Rack 10-PRK-0P01 | A | 2019-03-29 | IBD | OL1-2P05-0041 | MP | 2019-04-02 | 036909C-JVD-TRN-01228 | 036909C-JVD-TRN-01228, ROC-TPSK-CECO-T-00050 | IFR | 2019-04-17 | 2019-04-26 | R1-No comments | TPSK-LSPA1-T-MP-01228 |  | 2019-04-03 | 2
036909C-1000-MR-1031-0001 | Material Requisition for Recycle Gas Compressor | A | 2019-01-23 | IFQ | OL1-2C13-403000 | PL | 2019-01-23 | 036909C-JVD-TRN-00714 | 036909C-JVD-TRN-00714 | IFR | 2019-02-06 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-PL-00714 |  | 2019-01-23 | 2
036909C-1030-SP-1031-3073 | Mechanical Equipment Datasheet - BDU Recycle Gas Compressor | B | 2019-03-13 | IFQ | OL1-2M03-3073 | ME | 2019-03-14 | 036909C-JVD-TRN-01066 | 036909C-JVD-TRN-01066, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-01066 |  | 2019-03-15 | 2
036909C-105F-DW-1625-0001 | Substation F Equipment Layout | A | 2019-03-28 | IFR | OL1-2E20-0003 | EE | 2019-04-01 | 036909C-JVD-TRN-01212 | 036909C-JVD-TRN-01213, 036909C-JVD-TRN-01212, ROC-TPSK-CECO-T-00033 | IFA | 2019-04-16 | 2019-06-04 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01212 |  | 2019-04-02 | 1
036909C-1000-MS-0000-0052 | Job Construction Specification For Welding Activities Management | A | 2019-03-26 | IFR | OL1-2Q92-0012 | QM | 2019-04-03 | 036909C-JVD-TRN-01236 | 036909C-JVD-TRN-01236 | IFR | 2019-04-18 |  | Transmitted | TPSK-LSPA1-T-QM-01236 |  | 2019-04-04 | 2
036909C-1028-PDS-1390-2824 | Piping Specialty Item - Datasheets - T-Type Filter - C-2850 1st Stage Ethylene Refrig. Compressor Suction - 10-SP-28506 | A | 2019-06-17 | IFR | OL1-2P03-2824 | MP | 2019-06-19 | 036909C-JVD-TRN-01936 | 036909C-JVD-TRN-01936 | IFR | 2019-07-04 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-MP-01936 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2823 | Piping Specialty Item - Datasheet - T-Type Filter - C-2850 2nd Stage Ethylene Refrig. Compressor Suction - 10-SP-28505 | A | 2019-06-17 | IFR | OL1-2P03-2823 | MP | 2019-06-19 | 036909C-JVD-TRN-01936 | 036909C-JVD-TRN-01936 | IFR | 2019-07-04 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-MP-01936 |  | 2019-06-19 | 2
036909C-1028-PDS-1390-2821 | Piping Specialty Item - Datasheet - T-Type Filter - P-2805 A-B Suction - 10-SP-28010 | A | 2019-06-17 | IFR | OL1-2P03-2821 | MP | 2019-06-19 | 036909C-JVD-TRN-01936 | 036909C-JVD-TRN-01936 | IFR | 2019-07-04 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-MP-01936 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2811 | Piping Specialty Item - Datasheet - T-Type Filter - C-2800 th Stage Propylene Refrig. Compressor Suction - 10-SP-28003 | A | 2019-06-17 | IFR | OL1-2P03-2811 | MP | 2019-06-19 | 036909C-JVD-TRN-01936 | 036909C-JVD-TRN-01936 | IFR | 2019-07-04 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-MP-01936 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2827 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 1st Stage Suction - 10-SP-28606 | A | 2019-06-17 | IFR | OL1-2P03-2827 | MP | 2019-06-19 | 036909C-JVD-TRN-01937 | 036909C-JVD-TRN-01937 | IFR | 2019-07-04 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01937 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2826 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 2nd Stage Suction - 10-SP-28605 | A | 2019-06-17 | IFR | OL1-2P03-2826 | MP | 2019-06-19 | 036909C-JVD-TRN-01937 | 036909C-JVD-TRN-01937 | IFR | 2019-07-04 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01937 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2825 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 3rd Stage Suction - 10-SP-28604 | A | 2019-06-17 | IFR | OL1-2P03-2825 | MP | 2019-06-19 | 036909C-JVD-TRN-01937 | 036909C-JVD-TRN-01937 | IFR | 2019-07-04 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01937 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2820 | Piping Specialty Item - Datasheet - T-Type Filter - P-2815 Suction - 10-SP-28009 | A | 2019-06-17 | IFR | OL1-2P03-2820 | MP | 2019-06-19 | 036909C-JVD-TRN-01936 | 036909C-JVD-TRN-01936 | IFR | 2019-07-04 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01936 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2804 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 3rd Stage Suction - 10-SP-28101 | A | 2019-06-17 | IFR | OL1-2P03-2804 | MP | 2019-06-19 | 036909C-JVD-TRN-01928 | 036909C-JVD-TRN-01928 | IFR | 2019-07-04 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01928 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2805 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 2nd Stage Suction - 10-SP-28102 | A | 2019-06-17 | IFR | OL1-2P03-2805 | MP | 2019-06-19 | 036909C-JVD-TRN-01928 | 036909C-JVD-TRN-01928 | IFR | 2019-07-04 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01928 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2812 | Piping Specialty Item - Datasheet - Non-Slam Check valve - C-2800 5th Stage Discharge - 10-SP-28106 | A | 2019-06-17 | IFR | OL1-2P03-2812 | MP | 2019-06-19 | 036909C-JVD-TRN-01937 | 036909C-JVD-TRN-01937 | IFR | 2019-07-04 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01937 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2813 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 5th Stage Discharge - 10-SP-28011 | A | 2019-06-17 | IFR | OL1-2P03-2813 | MP | 2019-06-19 | 036909C-JVD-TRN-01937 | 036909C-JVD-TRN-01937 | IFR | 2019-07-04 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01937 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2803 | Piping Specialty Item - Datasheet - T-Type Filter - C-2800 - 1st Stage Propylene Refrig. Compressor Suction - 10-SP-28002 | A | 2019-06-17 | IFR | OL1-2P03-2803 | MP | 2019-06-19 | 036909C-JVD-TRN-01928 | 036909C-JVD-TRN-01928 | IFR | 2019-07-04 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01928 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2802 | Piping Specialty Item - Database - T-Type Filter - C-2800 2nd Stage Propylene Refrig. Compressor Suction - 10-SP-28001 | A | 2019-06-17 | IFR | OL1-2P03-2802 | MP | 2019-06-19 | 036909C-JVD-TRN-01928 | 036909C-JVD-TRN-01928 | IFR | 2019-07-04 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01928 |  | 2019-06-20 | 2
036909C-1028-PDS-1390-2801 | Piping Specialty Item - Datasheet - T-Type Filter - C-2800 3rd Stage Propylene Refrig. Compressor Suction - 10-SP-28000 | A | 2019-06-17 | IFR | OL12P03-2801 | MP | 2019-06-19 | 036909C-JVD-TRN-01928 | 036909C-JVD-TRN-01928 | IFR | 2019-07-04 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01928 |  | 2019-06-20 | 2
036909C-1025-PDS-1390-2502 | Piping Specialty Item - Datasheet - Basket-Type Filter - D-2506 BTMS TO E-2506 - 10-SP-25002 | A | 2019-06-10 | IFR | OL1-2P03-2502 | MP | 2019-06-11 | 036909C-JVD-TRN-01871 | 036909C-JVD-TRN-01871 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01871 |  | 2019-06-18 | 2
036909C-1023-PDS-1390-2301 | Piping Specialty Item - Datasheet - T-Type Filter - P-2306 A-B Suction - 10-SP-23001 | A | 2019-06-06 | IFR | OL1-2P03-2301 | MP | 2019-06-12 | 036909C-JVD-TRN-01884 | 036909C-JVD-TRN-01884 | IFR | 2019-06-27 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01884 |  | 2019-06-14 | 2
036909C-1022-PDS-1390-2205 | Piping Specialty Item - Datasheet - T-Type Filter - P-2220 A-B Suction - 10-SP-22005 | A | 2019-06-03 | IFR | OL1-2P03-2205 | MP | 2019-06-06 | 036909C-JVD-TRN-01821 | 036909C-JVD-TRN-01821 | IFR | 2019-06-21 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01821 |  | 2019-06-10 | 2
036909C-1028-PDS-1390-2844 | Piping Specialty Item - Datasheet - Basket-Type Filter - LP Ethylene To D-2882 & E-2882 - 10-SP-28512 | A | 2019-06-10 | IFR | OL1-2P03-2844 | MP | 2019-06-11 | 036909C-JVD-TRN-01872 | 036909C-JVD-TRN-01872 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01872 |  | 2019-06-11 | 2
036909C-1028-PDS-1390-2843 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2884 - 10-SP-28508 | A | 2019-06-10 | IFR | OL1-2P03-2843 | MP | 2019-06-11 | 036909C-JVD-TRN-01872 | 036909C-JVD-TRN-01872 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01872 |  | 2019-06-11 | 2
036909C-1025-PDS-1390-2539 | Piping Specialty Item - Datasheet - Basket-Type Filter - T-2580 Bottoms Reboiler Inlet - 10-SP-25039 | A | 2019-06-10 | IFR | OL1-2P03-2539 | MP | 2019-06-11 | 036909C-JVD-TRN-01872 | 036909C-JVD-TRN-01872 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01872 |  | 2019-06-11 | 2
036909C-1025-PDS-1390-2534 | Piping Specialty Item - Datasheet - Basket-Type Filter - T-2580 Side Reboiler Inlet - 10-SP-25034 | A | 2019-06-10 | IFR | OL1-2P03-2534 | MP | 2019-06-11 | 036909C-JVD-TRN-01872 | 036909C-JVD-TRN-01872 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01872 |  | 2019-06-11 | 2
036909C-1025-PDS-1390-2503 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2507 - 10-SP-25003 | A | 2019-06-10 | IFR | OL1-2P03-2503 | MP | 2019-06-11 | 036909C-JVD-TRN-01871 | 036909C-JVD-TRN-01871 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01871 |  | 2019-06-11 | 2
036909C-1024-PDS-1390-2415 | Piping Specialty Item - Datasheet - T-Type Filter - 5th Stage CG Compressor Suction - 10-SP-24015 | A | 2019-06-06 | IFR | OL1-2P03-2415 | MP | 2019-06-07 | 036909C-JVD-TRN-01835 | 036909C-JVD-TRN-01835 | IFR | 2019-06-24 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01835 |  | 2019-06-10 | 2
036909C-1025-PDS-1390-2532 | Piping Specialty Item - Datasheet - Basket-Type Filter - C3R To E-2500 - 10-SP-25032 | A | 2019-06-10 | IFR | OL1-2P03-2532 | MP | 2019-06-11 | 036909C-JVD-TRN-01872 | 036909C-JVD-TRN-01872 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01872 |  | 2019-06-11 | 2
036909C-1025-PDS-1390-2531 | Piping Specialty Item - Datasheet - Basket-Type Filter - C3R To E-2500 - 10-SP-25031 | A | 2019-06-10 | IFR | OL1-2P03-2531 | MP | 2019-06-11 | 036909C-JVD-TRN-01872 | 036909C-JVD-TRN-01872 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01872 |  | 2019-06-11 | 2
036909C-1025-PDS-1390-2526 | Piping Specialty Item - Datasheet - Basket-Type Filter - Residue Gas To E-2525 - 10-SP-25026 | A | 2019-06-10 | IFR | OL1-2P03-2526 | MP | 2019-06-11 | 036909C-JVD-TRN-01872 | 036909C-JVD-TRN-01872 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01872 |  | 2019-06-11 | 2
036909C-1025-PDS-1390-2521 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To E-2540 - 10-SP-25021 | A | 2019-06-10 | IFR | OL1-2P03-2521 | MP | 2019-06-11 | 036909C-JVD-TRN-01872 | 036909C-JVD-TRN-01872 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01872 |  | 2019-06-11 | 2
036909C-1025-PDS-1390-2519 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2530 - 10-SP-25019 | A | 2019-06-10 | IFR | OL1-2P03-2519 | MP | 2019-06-11 | 036909C-JVD-TRN-01872 | 036909C-JVD-TRN-01872 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01872 |  | 2019-06-11 | 2
036909C-1025-PDS-1390-2518 | Piping Specialty Item - Datasheet - Basket-Type Filter - T-2520 BTMS To E-2530 - 10-SP-25018 | A | 2019-06-10 | IFR | OL1-2P03-2518 | MP | 2019-06-11 | 036909C-JVD-TRN-01872 | 036909C-JVD-TRN-01872 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01872 |  | 2019-06-11 | 2
036909C-1025-PDS-1390-2512 | Piping Specialty Item - Datasheet - Basket-Type Filter - Methane Recycle To E-2520 - 10-SP-25012 | A | 2019-06-10 | IFR | OL1-2P03-2512 | MP | 2019-06-11 | 036909C-JVD-TRN-01872 | 036909C-JVD-TRN-01872 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01872 |  | 2019-06-11 | 2
036909C-1025-PDS-1390-2511 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2521 - 10-SP-25011 | A | 2019-06-10 | IFR | OL1-2P03-2511 | MP | 2019-06-11 | 036909C-JVD-TRN-01872 | 036909C-JVD-TRN-01872 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01872 |  | 2019-06-11 | 2
036909C-1025-PDS-1390-2510 | Piping Specialty Item - Datasheet - Basket-Type Filter - Demeth BTMS To E-2510 - 10-SP-25010 | A | 2019-06-10 | IFR | OL1-2P03-2510 | MP | 2019-06-11 | 036909C-JVD-TRN-01872 | 036909C-JVD-TRN-01872 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01872 |  | 2019-06-11 | 2
036909C-1025-PDS-1390-2509 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2509 - 10-SP-25009 | A | 2019-06-10 | IFR | OL1-2P03-2509 | MP | 2019-06-11 | 036909C-JVD-TRN-01872 | 036909C-JVD-TRN-01872 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01872 |  | 2019-06-11 | 2
036909C-1025-PDS-1390-2508 | Piping Specialty Item - Datasheet - Basket-Type Filter - D-2508 BTMS To E-2508 - 10-SP-25008 | A | 2019-06-10 | IFR | OL1-2P03-2508 | MP | 2019-06-11 | 036909C-JVD-TRN-01872 | 036909C-JVD-TRN-01872 | IFR | 2019-06-26 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01872 |  | 2019-06-11 | 2
036909C-1028-PDS-1390-2822 | Piping Specialty Item - Datasheet - T-Type Filter - C-2850 3rd Stage Ethylene Refrig. Compressor Suction - 10-SP-28504 | A | 2019-06-17 | IFR | OL1-2P03-2822 | MP | 2019-06-19 | 036909C-JVD-TRN-01936 | 036909C-JVD-TRN-01936 | IFR | 2019-07-04 | 2019-07-09 | R1-No comments | TPSK-LSPA1-T-MP-01936 |  | 2019-06-20 | 2
036909C-1027-SP-1546-2702 | Instrument Datasheets for Flow Element - Orifice - Area 27 | A | 2019-06-12 | IFQ | OL1-2I20-2722 | IE | 2019-06-17 | 036909C-JVD-TRN-01908 | 036909C-JVD-TRN-01908 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01908 |  | 2019-06-18 | 3
036909C-1027-SP-1541-2701 | Instrument Datasheets for Control Valve - Globe Type - Area 27 | A | 2019-06-18 | IFQ | OL1-2I20-2701 | IE | 2019-06-18 | 036909C-JVD-TRN-01919 | 036909C-JVD-TRN-01919 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01919 |  | 2019-06-19 | 3
036909C-1000-NM-1551-0001 | Preliminary Instrument List | A | 2019-06-24 | IBD | OL1-2I91-0001 | IE | 2019-06-24 | 036909C-JVD-TRN-01980 | 036909C-JVD-TRN-01980 | IFR | 2019-07-08 | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01980 |  | 2019-06-25 | 2
036909C-1056-SP-1541-5601 | Instrument Datasheets for Control Valve - Globe Type - Area 56 | A | 2019-06-06 | IFQ | OL1-2I20-5601 | IE | 2019-06-11 | 036909C-JVD-TRN-01866 | 036909C-JVD-TRN-01866 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01866 |  | 2019-06-11 | 3
036909C-1055-SP-1546-5502 | Instrument Datasheets for Flow Element - Orifice - Area 55 | A | 2019-06-03 | IFQ | OL1-2I20-5522 | IE | 2019-06-07 | 036909C-JVD-TRN-01828 | 036909C-JVD-TRN-01828 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK- LSPA1-T-IE-01828 |  | 2019-06-10 | 3
036909C-1055-SP-1541-5501 | Instrument Datasheets for Control Valve - Globe Type- Area 55 | A | 2019-06-06 | IFQ | OL1-2I20-5501 | IE | 2019-06-07 | 036909C-JVD-TRN-01828 | 036909C-JVD-TRN-01828 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK- LSPA1-T-IE-01828 |  | 2019-06-10 | 3
036909C-1051-SP-1547-5102 | Instrument Datasheets for Flow Element - Rotameter - Area 51 | A | 2019-06-07 | IFQ | OL1-2I20-5128 | IE | 2019-06-10 | 036909C-JVD-TRN-01845 | 036909C-JVD-TRN-01845 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01845 |  | 2019-06-11 | 3
036909C-1051-SP-1546-5106 | Instrument Datasheets for Flow Element - Flow Nozzle - Area 51 | A | 2019-06-06 | IFQ | OL1-2I20-5124 | IE | 2019-06-10 | 036909C-JVD-TRN-01845 | 036909C-JVD-TRN-01845 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01845 |  | 2019-06-11 | 3
036909C-1051-SP-1546-5102 | Instrument Datasheets for Flow Element - Orifice - Area 51 | A | 2019-06-06 | IFQ | OL1-2I20-5122 | IE | 2019-06-10 | 036909C-JVD-TRN-01845 | 036909C-JVD-TRN-01845 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01845 |  | 2019-06-11 | 3
036909C-1051-SP-1541-5111 | Instrument Datasheets for Control Valve - Three way Type - Area 51 | A | 2019-06-10 | IFQ | OL1-2I20-5118 | IE | 2019-06-12 | 036909C-JVD-TRN-01878 | 036909C-JVD-TRN-01878 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01878 |  | 2019-06-14 | 3
036909C-1051-SP-1541-5101 | Instrument Datasheets for Control Valve - Globe Type- Area 51 | A | 2019-06-10 | IFQ | OL1-2I20-5101 | IE | 2019-06-12 | 036909C-JVD-TRN-01878 | 036909C-JVD-TRN-01878 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01878 |  | 2019-06-14 | 3
036909C-1026-SP-1546-2602 | Instrument Datasheets for Flow Element Orifice Area 26 | A | 2019-06-12 | IFQ | OL1-2I20-2622 | IE | 2019-06-13 | 036909C-JVD-TRN-01890 | 036909C-JVD-TRN-01890 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSAP1-T-IE-01890 |  | 2019-06-14 | 3
036909C-1026-SP-1541-2601 | Instrument Datasheets for Control Valve - Globe Type - Area 26 | A | 2019-06-06 | IFQ | OL1-2I20-2601 | IE | 2019-06-10 | 036909C-JVD-TRN-01845 | 036909C-JVD-TRN-01845 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01845 |  | 2019-06-11 | 3
036909C-1026-SP-1541-2602 | Instrument Datasheet for Control Valve - Butterfly Type - Area 26 | A | 2019-06-04 | IFQ | OL1-2I20-2602 | IE | 2019-06-05 | 036909C-JVD-TRN-01807 | 036909C-JVD-TRN-01807 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01807 |  | 2019-06-10 | 3
036909C-1000-QCP-1570-0001 | Quality Control Plan - Instrumentation And Communication System Installation - Telecommunication Systems Installation | A | 2019-05-07 | IFR | OL1-2Q27-0005 | QM | 2019-05-10 | 036909C-JVD-TRN-01636 | 036909C-JVD-TRN-01636 | IFA | 2019-05-27 | 2019-06-10 | A1-Approved without comments | TPSK-LSPA1-T-QM-01636 |  | 2019-05-13 | 1
036909C-1000-SP-1920-0001 | Datasheet for Firefighting Equipment | A | 2019-06-04 | IFR | OL1-2L03-0001 | SE | 2019-06-10 | 036909C-JVD-TRN-01840 | 036909C-JVD-TRN-01840 | IFR | 2019-06-24 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-SE-01840 |  | 2019-06-10 | 2
036909C-1000-CN-1631-0001 | Lighting Calculation Report | A | 2019-06-10 | IFR | OL1-2E40-0001 | EE | 2019-06-11 | 036909C-JVD-TRN-01864 | 036909C-JVD-TRN-01864 | IFA | 2019-06-26 | 2019-07-01 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-01864 |  | 2019-06-11 | 1
036909C-1051-SP-0910-5109 | Mechanical Equipment Data Sheet - Condensate Pumps | C | 2018-11-28 | IFQ | OL1-2M03-5109 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476, ROC-TPSK-CECO-T-00016 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00476 |  | 2018-12-11 | 2
036909C-1051-SP-0910-5102 | Mechanical Equipment Data Sheet - VLP BFW Pumps | B | 2018-11-28 | IFQ | OL1-2M03-5102 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476, ROC-TPSK-CECO-T-00016 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00476 |  | 2018-12-11 | 2
036909C-1021-SP-0910-2146 | Mechanical Equipment Data Sheet - DSG Feed Pumps | B | 2018-11-28 | IFQ | OL1-2M03-2146 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476, ROC-TPSK-CECO-T-00014 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00476 |  | 2018-12-11 | 2
036909C-1021-SP-0910-2106 | Mechanical Equipment Data Sheet - Quench Water Pumps | B | 2018-11-28 | IFQ | OL1-2M03-2106 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476, ROC-TPSK-CECO-T-00014 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-ME-00476 |  | 2018-12-11 | 2
036909C-1059-SP-1513-5902 | Instrument Interlock Descriptions Area 59 - Supporting Utilities Auxiliaries | A | 2019-03-15 | IFR | OL1-2I30-5902 | IE | 2019-03-15 | 036909C-JVD-TRN-01088 | 036909C-JVD-TRN-01088 | IFR | 2019-04-01 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-IE-01088 |  | 2019-03-18 | 2
036909C-1053-SP-1513-5302 | Instrument Interlock Descriptions - Area 53- Cooling Water System | A | 2019-03-11 | IFR | OL1-2I30-5302 | IE | 2019-03-12 | 036909C-JVD-TRN-01037 | 036909C-JVD-TRN-01037 | IFR | 2019-03-27 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-IE-01037 |  | 2019-03-13 | 2
036909C-1021-SP-1513-2102 | Instrument Interlock Descriptions - Area 21 - Quench Water - Dilution Steam | A | 2019-03-25 | IFR | OL1-2G50-2102 | PE | 2019-03-25 | 036909C-JVD-TRN-01149 | 036909C-JVD-TRN-01149 | IFR | 2019-04-09 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01149 |  | 2019-03-26 | 2
036909C-1020-SP-1513-2002 | Instrument Interlock Descriptions Area 20 - Quench Oil | A | 2019-03-15 | IFR | OL1-2I30-2002 | IE | 2019-03-15 | 036909C-JVD-TRN-01088 | 036909C-JVD-TRN-01088 | IFR | 2019-04-01 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-IE-01088 |  | 2019-03-18 | 2
036909C-1039-PDS-2500-3900 | Process Equipment Datasheet - 10-TK-3900 - NMP Storage Tank | B | 2019-06-06 | IFD | OL1-2G30-3900 | PE | 2019-06-06 | 036909C-JVD-TRN-01825 | 036909C-JVD-TRN-01825 | IFR | 2019-06-21 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01825 |  | 2019-06-10 | 2
036909C-1031-PDS-0600-3160 | Process Equipment Datasheet - 10-E-3160 - BDU Condensate Cooler | B | 2019-05-31 | IFD | OL1-2G30-3160 | PE | 2019-06-03 | 036909C-JVD-TRN-01796 | 036909C-JVD-TRN-01796 | IFR | 2019-06-18 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01796 |  | 2019-06-10 | 2
036909C-1031-PDS-4100-3123 | Process Equipment Datasheet - 10-PK-3120 - Regeneration Steam Ejector Package Unit | B | 2019-06-06 | IFD | OL1-2G30-3123 | PE | 2019-06-06 | 036909C-JVD-TRN-01823 | 036909C-JVD-TRN-01823 | IFR | 2019-06-21 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01823 |  | 2019-06-10 | 2
036909C-1030-PDS-0600-3095 | Process Equipment Datasheet - 10-E-3095 - Butadiene Drying Tower Reboiler | B | 2019-05-31 | IFD | OL1-2G30-3095 | PE | 2019-06-03 | 036909C-JVD-TRN-01796 | 036909C-JVD-TRN-01796 | IFR | 2019-06-18 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01796 |  | 2019-06-10 | 2
036909C-1030-PDS-0850-3072 | Process Equipment Datasheet - 10-EJ-3070 - BDU Recycle Gas Ejector | B | 2019-06-06 | IFD | OL1-2G30-3072 | PE | 2019-06-07 | 036909C-JVD-TRN-01827 | 036909C-JVD-TRN-01827 | IFR | 2019-06-24 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01827 |  | 2019-06-10 | 2
036909C-1030-PDS-0900-3047 | Process Equipment Data Sheet - 10-P-3045 A-B - Rectifier Bottom Pump | B | 2019-06-07 | IFD | OL1-2G30-3047 | PE | 2019-06-10 | 036909C-JVD-TRN-01847 | 036909C-JVD-TRN-01847 | IFR | 2019-06-25 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01847 |  | 2019-06-11 | 2
036909C-1030-PDS-0900-3036 | Process Equipment Data Sheet - 10-P-3036 A-B - After Washer Bottom Pump | B | 2019-06-07 | IFD | OL1-2G30-3036 | PE | 2019-06-10 | 036909C-JVD-TRN-01846 | 036909C-JVD-TRN-01846 | IFR | 2019-06-25 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01846 |  | 2019-06-11 | 2
036909C-1030-PDS-0900-3033 | Process Equipment Data Sheet - 10-P-3030 A-B - After Washer Reflux - Crude Butadiene Pump | B | 2019-06-07 | IFD | OL1-2G30-3033 | PE | 2019-06-07 | 036909C-JVD-TRN-01836 | 036909C-JVD-TRN-01836 | IFR | 2019-06-24 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01836 |  | 2019-06-10 | 2
036909C-1030-PDS-0900-3016 | Process Equipment Data Sheet - 10-P-3016 A-B Heavy End Discharge Pump | B | 2019-06-07 | IFD | OL1-2G30-3016 | PE | 2019-06-07 | 036909C-JVD-TRN-01836 | 036909C-JVD-TRN-01836 | IFR | 2019-06-24 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01836 |  | 2019-06-10 | 2
036909C-1030-PDS-0900-3007 | Process Equipment Data Sheet - 10-P-3000 A-B - Predistillation Tower Reflux Pump | B | 2019-06-07 | IFD | OL1-2G30-3007 | PE | 2019-06-07 | 036909C-JVD-TRN-01836 | 036909C-JVD-TRN-01836 | IFR | 2019-06-24 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01836 |  | 2019-06-10 | 2
036909C-1030-PDS-0900-3006 | Process Equipment Data Sheet - 10-P-3002 A-B - Predistillation Tower Feed Pump | B | 2019-06-07 | IFD | OL1-2G30-3006 | PE | 2019-06-07 | 036909C-JVD-TRN-01836 | 036909C-JVD-TRN-01836 | IFR | 2019-06-24 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PE-01836 |  | 2019-06-10 | 2
036909C-1056-PDS-1560-0001 | Data Sheet For Analyzers Wastewater - Area 56 | A | 2019-06-05 | IFR | OL1-2G31-5601 | PE | 2019-06-06 | 036909C-JVD-TRN-01816 | 036909C-JVD-TRN-01816 | IFR | 2019-06-21 | 2019-06-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-01816 |  | 2019-06-10 | 2
036909C-1050-SP-1547-5007 | Instrument Datasheet for Flow Element - Ultrasonic - Area 50 | A | 2019-05-27 | IFQ | OL1-2I20-5031 | IE | 2019-06-03 | 036909C-JVD-TRN-01792 | 036909C-JVD-TRN-01792 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01792 |  | 2019-06-10 | 3
036909C-1055-SP-1547-5507 | Instrument Datasheets for Flow Element - Ultrasonic - Area 55 | A | 2019-06-03 | IFQ | OL1-2I20-5531 | IE | 2019-06-05 | 036909C-JVD-TRN-01807 | 036909C-JVD-TRN-01807 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01807 |  | 2019-06-10 | 3
036909C-1024-PDS-1390-2414 | Piping Specialty Item - Datasheet - T-Type Filter - P-2450 A-B Suction - 10-SP-24014 | A | 2019-06-05 | IFR | OL1-2P03-2414 | MP | 2019-06-07 | 036909C-JVD-TRN-01835 | 036909C-JVD-TRN-01835 | IFR | 2019-06-24 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-MP-01835 |  | 2019-06-10 | 2
036909C-1024-PDS-1390-2410 | Piping Specialty Item - Datasheet - T-Type Filter - P-2445 A-B Suction - 10-SP-24010 | A | 2019-06-04 | IFR | OL1-2P03-2410 | MP | 2019-06-07 | 036909C-JVD-TRN-01835 | 036909C-JVD-TRN-01835 | IFR | 2019-06-24 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-MP-01835 |  | 2019-06-10 | 2
036909C-1024-PDS-1390-2404 | Piping Specialty Item - Datasheet - T-Type Filter - P-2415 A-B Suction - 10-SP-24004 | A | 2019-06-04 | IFR | OL1-2P03-2404 | MP | 2019-06-07 | 036909C-JVD-TRN-01835 | 036909C-JVD-TRN-01835 | IFR | 2019-06-24 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-MP-01835 |  | 2019-06-10 | 2
036909C-1024-PDS-1390-2413 | Piping Specialty Item - Datasheet - T-Type Filter - P-2455 A-B Suction - 10-SP-24013 | A | 2019-06-05 | IFR | OL1-2P03-2413 | MP | 2019-06-07 | 036909C-JVD-TRN-01835 | 036909C-JVD-TRN-01835 | IFR | 2019-06-24 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-MP-01835 |  | 2019-06-10 | 2
036909C-1029-PDS-1390-2926 | Piping Specialty Item - Datasheet - Vent Silencer - Start-Up - 10-SP-29026 | A | 2019-06-03 | IFR | OL1-2P03-2926 | MP | 2019-06-05 | 036909C-JVD-TRN-01809 | 036909C-JVD-TRN-01809 | IFR | 2019-06-20 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-MP-01809 |  | 2019-06-10 | 2
036909C-1029-PDS-1390-2921 | Piping Specialty Item - Datasheet - Vent Silencer - Start-Up - 10-SP-29021 | A | 2019-06-03 | IFR | OL1-2P03-2921 | MP | 2019-06-05 | 036909C-JVD-TRN-01809 | 036909C-JVD-TRN-01809 | IFR | 2019-06-20 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-MP-01809 |  | 2019-06-10 | 2
036909C-1029-PDS-1390-2915 | Piping Speacialty Item - Datasheet - Vent Silencer - Start-Up - 10-SP-29015 | A | 2019-06-03 | IFR | OL1-2P03-2915 | MP | 2019-06-05 | 036909C-JVD-TRN-01809 | 036909C-JVD-TRN-01809 | IFR | 2019-06-20 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-MP-01809 |  | 2019-06-10 | 2
036909C-1029-PDS-1390-2912 | Piping Specialty Item - Datasheet - Vent Silencer - Start-Up - 10-SP-29012 | A | 2019-06-03 | IFR | OL1-2P03-2912 | MP | 2019-06-05 | 036909C-JVD-TRN-01809 | 036909C-JVD-TRN-01809 | IFR | 2019-06-20 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-MP-01809 |  | 2019-06-10 | 2
036909C-1022-PDS-1390-2207 | Piping Specialty Item - Datasheet - T-Type Filter - 4th Stage CG Compressor Suction - 10-SP-22007 | A | 2019-06-03 | IFR | OL1-2P03-2207 | MP | 2019-06-06 | 036909C-JVD-TRN-01819 | 036909C-JVD-TRN-01819 | IFR | 2019-06-21 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-MP-01819 |  | 2019-06-10 | 2
036909C-1022-PDS-1390-2206 | Piping Specialty Item - Datasheet - T-Type Filter - 3rd Stage CG Compressor Suction - 10-SP-22006 | A | 2019-06-03 | IFR | OL1-2P03-2206 | MP | 2019-06-06 | 036909C-JVD-TRN-01819 | 036909C-JVD-TRN-01819 | IFR | 2019-06-21 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-MP-01819 |  | 2019-06-10 | 2
036909C-1022-PDS-1390-2204 | Piping Specialty Item - Datasheet - T-Type Filter - 2nd Stage CG Compressor Suction - 10-SP-22004 | A | 2019-06-03 | IFR | OL1-2P03-2204 | MP | 2019-06-06 | 036909C-JVD-TRN-01819 | 036909C-JVD-TRN-01819 | IFR | 2019-06-21 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-MP-01819 |  | 2019-06-10 | 2
036909C-1022-PDS-1390-2203 | Piping Specialty Item - Datasheet - T-Type Filter - 1st Stage CG Compressor Suction - 10-SP-22003 | A | 2019-05-30 | IFR | OL1-2P03-2203 | MP | 2019-06-06 | 036909C-JVD-TRN-01819 | 036909C-JVD-TRN-01819 | IFR | 2019-06-21 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-MP-01819 |  | 2019-06-10 | 2
036909C-1022-PDS-1390-2202 | Piping Specialty Item - Datasheet - T-Type Filter - P-2210 A-B Suction - 10-SP-22002 | A | 2019-05-30 | IFR | OL1-2P03-2202 | MP | 2019-06-06 | 036909C-JVD-TRN-01819 | 036909C-JVD-TRN-01819 | IFR | 2019-06-21 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-MP-01819 |  | 2019-06-10 | 2
036909C-1012-MR-1565-2051 | Material Requisition for O2 & Combustible Analyzer | A | 2019-06-19 | IFQ | OL1-2C17-212051 | PL | 2019-06-24 | 036909C-JVD-TRN-01979 | 036909C-JVD-TRN-01979 | IFI |  | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PL-01979 |  | 2019-06-25 | 3
036909C-1055-PDS-1560-0001 | Data Sheet For Analyzers Vent Gas And Flare System - Area 55 | A | 2019-06-05 | IFR | OL1-2G31-5501 | PE | 2019-06-06 | 036909C-JVD-TRN-01816 | 036909C-JVD-TRN-01816 | IFR | 2019-06-21 | 2019-06-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-01816 |  | 2019-06-10 | 2
036909C-1020-SP-1513-2001 | Complex Loop Narratives Area 20 Quench Oil | B | 2019-06-28 | IBD | OL1-2I71-2001 | IE | 2019-07-01 | 036909C-JVD-TRN-02052 | 036909C-JVD-TRN-02052, 036909C-JVD-TRN-02038 | IFR | 2019-07-16 |  | Transmitted | TPSK-LSPA1-T-IE-02052 |  | 2019-07-03 | 2
036909C-1059-SP-1513-5901 | Complex Loop Narratives Area 59 Supporting Utilities Auxiliaries | B | 2019-06-28 | IBD | OL1-2I71-5901 | IE | 2019-07-01 | 036909C-JVD-TRN-02052 | 036909C-JVD-TRN-02052, 036909C-JVD-TRN-02038 | IFR | 2019-07-16 |  | Transmitted | TPSK-LSPA1-T-IE-02052 |  | 2019-07-03 | 2
036909C-1053-SP-1513-5301 | Complex Loop Narratives Area 53 Cooling Water System | B | 2019-06-28 | IBD | OL1-2I71-5301 | IE | 2019-07-01 | 036909C-JVD-TRN-02052 | 036909C-JVD-TRN-02052, 036909C-JVD-TRN-02038 | IFR | 2019-07-16 |  | Transmitted | TPSK-LSPA1-T-IE-02052 |  | 2019-07-03 | 2
036909C-102D-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2D PROCESS COLD COMPRESSOR | A | 2019-04-05 | IFR | OL1-2F30-0012 | FF | 2019-04-08 | 036909C-JVD-TRN-01270 | 036909C-JVD-TRN-01270, KLOC-TPSK-VSAFE-T-00003 | IFR | 2019-04-22 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01270 |  | 2019-04-08 | 2
036909C-102D-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2D PROCESS COLD COMPRESSOR | C | 2019-05-06 | IFR | OL1-2F30-0012 | FF | 2019-05-08 | 036909C-JVD-TRN-01612 | 036909C-JVD-TRN-01612, KLOC-TPSK-VSAFE-T-00008 | IFR | 2019-05-22 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-01612 |  | 2019-05-09 | 2
036909C-1000-MR-4100-0001 | Material Requisition for Wet Air Oxidation Package | 1 | 2019-06-19 | IFP | OL1-2C13-704000 | PL | 2019-06-20 | 036909C-JVD-TRN-01943 | 036909C-JVD-TRN-01943 | IFR | 2019-07-04 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PL-01943 |  | 2019-06-20 | 2
036909C-105W-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5W WASTE WATER TREATMENT | A | 2019-04-05 | IFR | OL1-2F30-0004 | FF | 2019-04-08 | 036909C-JVD-TRN-01270 | 036909C-JVD-TRN-01270, KLOC-TPSK-VSAFE-T-00003 | IFR | 2019-04-22 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01270 |  | 2019-04-08 | 2
036909C-105W-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5W WASTE WATER TREATMENT | C | 2019-05-06 | IFR | OL1-2F30-0004 | FF | 2019-05-08 | 036909C-JVD-TRN-01612 | 036909C-JVD-TRN-01612, KLOC-TPSK-VSAFE-T-00008 | IFR | 2019-05-22 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-01612 |  | 2019-05-09 | 2
036909C-105U-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5U UTILITIES | A | 2019-04-05 | IFR | OL1-2F30-0005 | FF | 2019-04-08 | 036909C-JVD-TRN-01270 | 036909C-JVD-TRN-01270, KLOC-TPSK-VSAFE-T-00003 | IFR | 2019-04-22 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01270 |  | 2019-04-08 | 2
036909C-105U-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5U UTILITIES | C | 2019-05-06 | IFR | OL1-2F30-0005 | FF | 2019-05-08 | 036909C-JVD-TRN-01612 | 036909C-JVD-TRN-01612, KLOC-TPSK-VSAFE-T-00008 | IFR | 2019-05-22 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-01612 |  | 2019-05-09 | 2
036909C-105T-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5T COOLING WATER UNIT | A | 2019-04-05 | IFR | OL1-2F30-0003 | FF | 2019-04-08 | 036909C-JVD-TRN-01270 | 036909C-JVD-TRN-01270, KLOC-TPSK-VSAFE-T-00003 | IFR | 2019-04-22 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01270 |  | 2019-04-08 | 2
036909C-105T-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5T COOLING WATER UNIT | C | 2019-05-06 | IFR | OL1-2F30-0003 | FF | 2019-05-08 | 036909C-JVD-TRN-01612 | 036909C-JVD-TRN-01612, KLOC-TPSK-VSAFE-T-00008 | IFR | 2019-05-22 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-01612 |  | 2019-05-09 | 2
036909C-103A-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 3A BUTADIENE EXTRACTION UNIT | C | 2019-05-06 | IFR | OL1-2F30-0014 | FF | 2019-05-08 | 036909C-JVD-TRN-01612 | 036909C-JVD-TRN-01612, KLOC-TPSK-VSAFE-T-00008 | IFR | 2019-05-22 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-01612 |  | 2019-05-09 | 2
036909C-103A-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 3A BUTADIENE EXTRACTION UNIT | A | 2019-04-05 | IFR | OL1-2F30-0014 | FF | 2019-04-08 | 036909C-JVD-TRN-01270 | 036909C-JVD-TRN-01270, KLOC-TPSK-VSAFE-T-00003 | IFR | 2019-04-22 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01270 |  | 2019-04-08 | 2
036909C-102E-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2E CRACKED GAS COMPRESSOR | A | 2019-04-05 | IFR | OL1-2F30-0013 | FF | 2019-04-08 | 036909C-JVD-TRN-01270 | 036909C-JVD-TRN-01270, KLOC-TPSK-VSAFE-T-00003 | IFR | 2019-04-22 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01270 |  | 2019-04-08 | 2
036909C-102E-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2E CRACKED GAS COMPRESSOR | C | 2019-05-06 | IFR | OL1-2F30-0013 | FF | 2019-05-08 | 036909C-JVD-TRN-01612 | 036909C-JVD-TRN-01612, KLOC-TPSK-VSAFE-T-00008 | IFR | 2019-05-22 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-01612 |  | 2019-05-09 | 2
036909C-102C-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2C HOT FRACTIONATION/GHU UNIT | C | 2019-05-06 | IFR | OL1-2F30-0015 | FF | 2019-05-08 | 036909C-JVD-TRN-01612 | 036909C-JVD-TRN-01612, KLOC-TPSK-VSAFE-T-00008 | IFR | 2019-05-22 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-01612 |  | 2019-05-09 | 2
036909C-102C-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2C HOT FRACTIONATION/GHU UNIT | A | 2019-04-05 | IFR | OL1-2F30-0015 | FF | 2019-04-08 | 036909C-JVD-TRN-01270 | 036909C-JVD-TRN-01270, KLOC-TPSK-VSAFE-T-00003 | IFR | 2019-04-22 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01270 |  | 2019-04-08 | 2
036909C-102B-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2B C3 HYDROGENATION | C | 2019-05-06 | IFR | OL1-2F30-0011 | FF | 2019-05-08 | 036909C-JVD-TRN-01612 | 036909C-JVD-TRN-01612, KLOC-TPSK-VSAFE-T-00008 | IFR | 2019-05-22 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-01612 |  | 2019-05-09 | 2
036909C-102B-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2B C3 HYDROGENATION | A | 2019-04-05 | IFR | OL1-2F30-0011 | FF | 2019-04-08 | 036909C-JVD-TRN-01270 | 036909C-JVD-TRN-01270, KLOC-TPSK-VSAFE-T-00003 | IFR | 2019-04-22 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01270 |  | 2019-04-08 | 2
036909C-102A-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2A QUENCH | C | 2019-05-06 | IFR | OL1-2F30-0010 | FF | 2019-05-08 | 036909C-JVD-TRN-01612 | 036909C-JVD-TRN-01612, KLOC-TPSK-VSAFE-T-00008 | IFR | 2019-05-22 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-01612 |  | 2019-05-09 | 2
036909C-102A-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2A QUENCH | A | 2019-04-05 | IFR | OL1-2F30-0010 | FF | 2019-04-08 | 036909C-JVD-TRN-01270 | 036909C-JVD-TRN-01270, KLOC-TPSK-VSAFE-T-00003 | IFR | 2019-04-22 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01270 |  | 2019-04-08 | 2
036909C-101B-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 1B FURNACES UTILITIES | C | 2019-05-06 | IFR | OL1-2F30-0009 | FF | 2019-05-08 | 036909C-JVD-TRN-01612 | 036909C-JVD-TRN-01612, KLOC-TPSK-VSAFE-T-00008 | IFR | 2019-05-22 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-FF-01612 |  | 2019-05-09 | 2
036909C-101B-DW-1933-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 1B FURNACES UTILITIES | A | 2019-04-05 | IFR | OL1-2F30-0009 | FF | 2019-04-08 | 036909C-JVD-TRN-01270 | 036909C-JVD-TRN-01270, KLOC-TPSK-VSAFE-T-00003 | IFR | 2019-04-22 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01270 |  | 2019-04-08 | 2
036909C-1000-SP-1930-0003 | Datasheet for Sprinkler System | A | 2019-06-03 | IFR | OL1-2L03-2001 | SE | 2019-06-03 | 036909C-JVD-TRN-01746 | 036909C-JVD-TRN-01746 | IFR | 2019-06-19 | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-SE-01746 |  | 2019-06-03 | 2
036909C-1000-SP-1930-0001 | Datasheet for Deluge System | A | 2019-06-03 | IFR | OL1-2L03-1001 | SE | 2019-06-03 | 036909C-JVD-TRN-01746 | 036909C-JVD-TRN-01746 | IFR | 2019-06-19 | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-SE-01746 |  | 2019-06-03 | 2
036909C-1012-SP-1547-1201 | Instrument Datasheets for Flow Instrument -Vortex - Area 12 - BOP | A | 2019-05-06 | IFQ | OL1-2I20-1227 | IE | 2019-05-08 | 036909C-JVD-TRN-01615 | 036909C-JVD-TRN-01615 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01615 |  | 2019-05-09 | 3
036909C-1011-SP-1547-1101 | Instrument Datasheets for Flow Instrument -Vortex-Area 11 -BOP | A | 2019-05-06 | IFQ | OL1-2I20-1127 | IE | 2019-05-07 | 036909C-JVD-TRN-01594 | 036909C-JVD-TRN-01594 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01594 |  | 2019-05-08 | 3
036909C-1053-SP-1547-5305 | Instrument Datasheets for Flow Transmitter - Electromagnetic - Area 53 | A | 2019-06-07 | IFQ | OL1-2I20-5329 | IE | 2019-06-10 | 036909C-JVD-TRN-01845 | 036909C-JVD-TRN-01845 | IFI |  | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-IE-01845 |  | 2019-06-11 | 3
036909C-1050-SP-1547-5005 | Instrument Datasheets for Flow Transmitter -Electromagnetic- Area 50 | A | 2019-05-29 | IFQ | OL1-2I20-5029 | IE | 2019-05-30 | 036909C-JVD-TRN-01774 | 036909C-JVD-TRN-01774 | IFI |  | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-IE-01774 |  | 2019-05-31 | 3
036909C-1000-JSD-1900-0001 | Fire Fighting And Fire Protection | A | 2019-01-30 | IFR | OL1-2L01-0001 | PE | 2019-02-01 | 036909C-JVD-TRN-00782 | 036909C-JVD-TRN-00782, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-18 | 2019-03-18 | R2-Comments as noted | TPSK-LSPA1-T-PE-00782 |  | 2019-02-01 | 2
036909C-1024-SP-1546-2405 | Instrument Datasheets for Flow Element - Venturi - Area 24 | A | 2019-04-22 | IFQ | OL1-2I20-2423 | IE | 2019-04-22 | 036909C-JVD-TRN-01428 | 036909C-JVD-TRN-01428 | IFI |  | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-01428 |  | 2019-04-23 | 3
036909C-1029-SP-1546-2905 | Instrument Datasheets for Flow Element (Venturi Type) Area 29 | A | 2019-05-21 | IFQ | OL1-2I20-2923 | IE | 2019-05-22 | 036909C-JVD-TRN-01717 | 036909C-JVD-TRN-01717 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01717 |  | 2019-05-23 | 3
036909C-1012-MR-1399-2102 | Material Requisition for SP Item - Sample Cooler | A | 2019-06-19 | IFQ | OL1-2C14-503000 | PL | 2019-07-02 | 036909C-JVD-TRN-02057 | 036909C-JVD-TRN-02057 | IFR | 2019-07-17 |  | Transmitted | TPSK-LSPA1-T-PL-02057 |  | 2019-07-03 | 2
036909C-1012-MR-1399-2105 | Material Requisition for SP Item - Vent Silencer | A | 2019-06-07 | IFQ | OL1-2C14-506000 | PL | 2019-07-02 | 036909C-JVD-TRN-02060 | 036909C-JVD-TRN-02060 | IFR | 2019-07-17 |  | Transmitted | TPSK-LSPA1-T-PL-02060 |  | 2019-07-03 | 2
036909C-102E-DW-1552-0001 | Level Instrument Design Cracked Gas Compressor - ISBL | A | 2019-06-17 | IFR | OL1-2I31-0207 | IE | 2019-06-17 | 036909C-JVD-TRN-01905 | 036909C-JVD-TRN-01905 | IFA | 2019-07-02 | 2019-06-28 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-IE-01905 |  | 2019-06-18 | 1
036909C-1000-STC-1391-0000 | Standard Auxiliary Piping Support Collection | A | 2019-02-11 | IFR | OL1-2P25-0085 | MP | 2019-02-20 | 036909C-JVD-TRN-00896 | 036909C-JVD-TRN-00896, ROC-TPSK-CECO-T-00013, ROC-TPSK-CECO-T-00013_1 | IFR | 2019-02-20 | 2019-04-05 | R2-Comments as noted | TPSK-LSPA1-T-MP-00896 |  | 2019-02-20 | 2
036909C-1000-NM-0050-0001 | Battery Limit Summary | B | 2019-05-02 | IFD | OL1-2G60-0001 | PE | 2019-05-02 | 036909C-JVD-TRN-01560 | 036909C-JVD-TRN-01560 | IFR | 2019-05-17 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01560 |  | 2019-05-03 | 2
036909C-1000-MS-6740-52 | Job Specification For Material Preservation During Construction Precommissioning Commissioning And Start Up | A | 2019-03-08 | IFR | OL1-2O71-0023 | PE | 2019-03-18 | 036909C-JVD-TRN-01090 | 036909C-JVD-TRN-01090 | IFR | 2019-04-02 |  | Transmitted | TPSK-LSPA1-T-PE-01090 |  | 2019-03-19 | 2
036909C-1000-JSD-1700-0001 | Job Design Specification For Foundations And Structures | 0 | 2019-02-14 | IMP | OL1-2R02-0004 | CV | 2019-02-19 | 036909C-JVD-TRN-00887 | 036909C-JVD-TRN-00887, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-03-06 | 2019-03-18 | R2-Comments as noted | TPSK-LSPA1-T-CV-00887 |  | 2019-02-19 | 2
036909C-1000-DW-1703-0001 | Key Plan For Structures | A | 2019-03-21 | IFR | OL1-2K25-0002 | CV | 2019-03-27 | 036909C-JVD-TRN-01171 | 036909C-JVD-TRN-01171 | IFR | 2019-04-11 | 2019-06-03 | A1-Approved without comments | TPSK-LSPA1-T-CV-01171 |  | 2019-03-28 | 2
036909C-1027-PDS-0800-2718 | Process Equipment Datasheet - 10-D-2720 - Rerun Tower Reflux Drum | B | 2019-04-12 | IFD | OL1-2G30-2718 | PE | 2019-04-12 | 036909C-JVD-TRN-01342 | 036909C-JVD-TRN-01342 | IFR | 2019-04-29 |  | Transmitted | TPSK-LSPA1-T-PE-01342 |  | 2019-04-15 | 2
036909C-1000-DW-1802-0001 | General Notes For Steel Structure | 1 | 2019-03-01 | IFC1 | OL1-2K92-0004 | CV | 2019-03-06 | 036909C-JVD-TRN-00993 | 036909C-JVD-TRN-00993, ROC-TPSK-CECO-T-00003 | IFA | 2019-03-21 | 2019-03-31 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00993 |  | 2019-03-07 | 1
036909C-1059-SP-1513-5901 | Complex Loop Narratives - Area 59 - Supporting Utilities Auxiliaries | A | 2019-03-25 | IFR | OL1-2I71-5901 | IE | 2019-03-25 | 036909C-JVD-TRN-01140 | 036909C-JVD-TRN-01140 | IFR | 2019-04-09 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-01140 |  | 2019-03-26 | 2
036909C-1053-SP-1513-5301 | Complex Loop Narratives - Area 53 - Cooling Water System | A | 2019-03-11 | IFR | OL1-2I71-5301 | IE | 2019-03-12 | 036909C-JVD-TRN-01037 | 036909C-JVD-TRN-01037 | IFR | 2019-03-27 |  | Transmitted | TPSK-LSPA1-T-IE-01037 |  | 2019-03-13 | 2
036909C-1020-SP-1513-2001 | Complex Loop Narratives - Area 20 - Quench Oil | A | 2019-03-21 | IFR | OL1-2I71-2001 | IE | 2019-03-21 | 036909C-JVD-TRN-01132 | 036909C-JVD-TRN-01132 | IFR | 2019-04-05 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01132 |  | 2019-03-22 | 2
036909C-1000-STC-1890-0001 | Construction Standards For Steel Structures | 0 | 2019-02-27 | IFC | OL1-2K21-0001 | CV | 2019-03-06 | 036909C-JVD-TRN-00996 | 036909C-JVD-TRN-00996, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFA | 2019-03-21 | 2019-03-31 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00996 |  | 2019-03-07 | 1
036909C-1011-PDS-1040-1111 | Process Equipment Datasheet - 10-C-1100 - USC 36M Induced Draft Fan | C | 2019-03-13 | IFD | OL1-2G30-1111 | PE | 2019-03-15 | 036909C-JVD-TRN-01079 | 036909C-JVD-TRN-01079, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-30 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01079 |  | 2019-03-18 | 2
036909C-1000-DW-1612-0002 | Overall Lightning Protection Layout | A | 2019-06-13 | IFR | OL1-2E52-0002 | EE | 2019-06-14 | 036909C-JVD-TRN-01894 | 036909C-JVD-TRN-01894 | IFR | 2019-06-28 | 2019-07-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-01894 |  | 2019-06-14 | 1
036909C-1028-SP-1543-2814 | Instrument Datasheets for Motor Operated Valve Area 28 | A | 2019-04-23 | IFQ | OL1-2I20-2813 | IE | 2019-04-24 | 036909C-JVD-TRN-01464 | 036909C-JVD-TRN-01464, ROC-TPSK-CECO-T-00056 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01464 |  | 2019-04-25 | 3
036909C-1024-SP-1546-2402 | Instrument Datasheets for Flow Element -Orifice- Area 24 | A | 2019-05-02 | IFQ | OL1-2I20-2422 | IE | 2019-05-02 | 036909C-JVD-TRN-01548 | 036909C-JVD-TRN-01548 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01548 |  | 2019-05-03 | 3
036909C-1023-SP-1541-2301 | Instrument Datasheets for Control Valve - Globe Type - Area 23 | A | 2019-05-02 | IFQ | OL1-2I20-2301 | IE | 2019-05-02 | 036909C-JVD-TRN-01548 | 036909C-JVD-TRN-01548 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01548 |  | 2019-05-03 | 3
036909C-1012-SP-1546-1202 | Instrument Datasheets for Flow Element -Orifice- Area 12 -BOP | A | 2019-05-06 | IFQ | OL1-2I20-1222 | IE | 2019-05-07 | 036909C-JVD-TRN-01594 | 036909C-JVD-TRN-01594 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01594 |  | 2019-05-08 | 3
036909C-1012-SP-1541-1201 | Instrument Datasheets for Control Valve - Globe Type Area 12 -BOP | A | 2019-05-06 | IFQ | OL1-2I20-1201 | IE | 2019-05-07 | 036909C-JVD-TRN-01594 | 036909C-JVD-TRN-01594 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01594 |  | 2019-05-08 | 3
036909C-1011-SP-1546-1102 | Instrument Datasheets for Flow Element Orifice- Area 11 -BOP | A | 2019-05-07 | IFQ | OL1-2I20-1122 | IE | 2019-05-08 | 036909C-JVD-TRN-01615 | 036909C-JVD-TRN-01615 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01615 |  | 2019-05-09 | 3
036909C-1056-PDS-0200-5628 | Process Equipment Datasheet - 10-PIT-5628 - Gate 3 Septic Tank | C | 2019-04-03 | IFD | OL1-2G30-5628 | PE | 2019-04-04 | 036909C-JVD-TRN-01257 | 036909C-JVD-TRN-01257, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-19 | 2019-05-16 | Response to Client Comments sent July 01 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01257 |  | 2019-04-05 | 2
036909C-1054-SP-1547-5406 | Instrument Datasheets for Flow Element - Coriolis- Area 54 | A | 2019-05-25 | IFQ | OL1-2I20-5430 | IE | 2019-06-03 | 036909C-JVD-TRN-01792 | 036909C-JVD-TRN-01792 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01792 |  | 2019-06-10 | 3
036909C-1055-PDS-0800-5555 | Process Equipment Datasheet - 10-D-5553 - LPG Vaporizer - Superhtr Cond Pot | B | 2019-03-09 | IFD | OL1-2G30-5555 | PE | 2019-03-11 | 036909C-JVD-TRN-01018 | 036909C-JVD-TRN-01018 | IFR | 2019-03-26 | 2019-03-27 | R1-No comments | TPSK-LSPA1-T-PE-01018 |  | 2019-03-12 | 2
036909C-1055-PDS-0800-5514 | Process Equipment Datasheet - 10-D-5513 - Methanol Vaporizer Cond Pot | B | 2019-01-29 | IFD | OL1-2G30-5514 | PE | 2019-02-01 | 036909C-JVD-TRN-00785 | 036909C-JVD-TRN-00785 | IFI |  | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00785 |  | 2019-02-04 | 2
036909C-1052-PDS-0800-5202 | Process Equipment Datasheet - 10-D-5220 - MP Ethylene Superhtr Cond Pot | B | 2019-02-10 | IFD | OL1-2G30-5202 | PE | 2019-02-11 | 036909C-JVD-TRN-00836 | 036909C-JVD-TRN-00836 | IFI |  | 2019-03-27 | R1-No comments | TPSK-LSPA1-T-PE--00836 |  | 2019-02-11 | 2
036909C-1052-PDS-0800-5211 | Process Equipment Datasheet - 10-D-5210 - Pilot Gas Vaporizer Cond Pot | B | 2019-02-10 | IFD | OL1-2G30-5211 | PE | 2019-02-11 | 036909C-JVD-TRN-00836 | 036909C-JVD-TRN-00836 | IFI |  | 2019-03-27 | R1-No comments | TPSK-LSPA1-T-PE--00836 |  | 2019-02-11 | 2
036909C-1059-DW-1514-5901 | Cause and Effect Diagram Area 59 - Supporting Utilities Auxiliaries | A | 2019-03-15 | IFR | OL1-2I30-5901 | IE | 2019-03-15 | 036909C-JVD-TRN-01087 | 036909C-JVD-TRN-01087, ROC-TPSK-CECO-T-00032 | IFR | 2019-04-01 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-IE-01087 |  | 2019-03-18 | 2
036909C-1053-DW-1514-5301 | Cause and Effect Diagram - Area 53 - Cooling Water System | A | 2019-03-11 | IFR | OL1-2I30-5301 | IE | 2019-03-12 | 036909C-JVD-TRN-01036 | 036909C-JVD-TRN-01036, ROC-TPSK-CECO-T-00013, ROC-TPSK-CECO-T-00013_1, ROC-TPSK-CECO-T-00029 | IFR | 2019-03-27 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-IE-01036 |  | 2019-03-13 | 2
036909C-1021-DW-1514-2101 | Cause and Effect Diagram - Area 21 - Quench Water - Dilution Steam | A | 2019-03-22 | IFR | OL1-2G50-2101 | PE | 2019-03-25 | 036909C-JVD-TRN-01137 | 036909C-JVD-TRN-01137, ROC-TPSK-CECO-T-00032 | IFR | 2019-04-09 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-01137 |  | 2019-03-26 | 2
036909C-1020-DW-1514-2001 | Cause and Effect Diagram Area 20 - Quench Oil | A | 2019-03-15 | IFR | OL1-2I30-2001 | IE | 2019-03-15 | 036909C-JVD-TRN-01087 | 036909C-JVD-TRN-01087, ROC-TPSK-CECO-T-00013, ROC-TPSK-CECO-T-00013_1, ROC-TPSK-CECO-T-00029 | IFR | 2019-04-01 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-IE-01087 |  | 2019-03-18 | 2
036909C-1056-PDS-0900-5622 | Process Equipment Datasheet - 10-P-5620 A-C - Olefins Holding Basin Pumps | B | 2019-04-03 | IFD | OL1-2G30-5622 | PE | 2019-04-04 | 036909C-JVD-TRN-01255 | 036909C-JVD-TRN-01255 | IFR | 2019-04-19 | 2019-05-09 | Response to Client Comments sent 01 July 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01255 |  | 2019-04-05 | 2
036909C-1059-SP-1547-5909 | Instrument Datasheets for Flow Element - Integral Orifice - Area 59 | A | 2019-06-07 | IFQ | OL1-2I20-5932 | IE | 2019-06-10 | 036909C-JVD-TRN-01845 | 036909C-JVD-TRN-01845 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01845 |  | 2019-06-11 | 3
036909C-1059-SP-1546-5906 | Instrument Datasheets for Flow Element - Flow Nozzle- Area 59 | A | 2019-06-04 | IFQ | OL1-2I20-5924 | IE | 2019-06-07 | 036909C-JVD-TRN-01828 | 036909C-JVD-TRN-01828 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK- LSPA1-T-IE-01828 |  | 2019-06-10 | 3
036909C-1059-SP-1546-5902 | Instrument Datasheets for Flow Element - Orifice - Area 59 | A | 2019-06-06 | IFQ | OL1-2I20-5922 | IE | 2019-06-10 | 036909C-JVD-TRN-01845 | 036909C-JVD-TRN-01845 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01845 |  | 2019-06-11 | 3
036909C-1059-SP-1541-5901 | Instrument Datasheets for Control Valve - Globe Type - Area 59 | A | 2019-06-06 | IFQ | OL1-2I20-5901 | IE | 2019-06-10 | 036909C-JVD-TRN-01845 | 036909C-JVD-TRN-01845 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01845 |  | 2019-06-11 | 3
036909C-1056-SP-1546-5602 | Instrument Datasheets for Flow Element - Orifice - Area 56 | A | 2019-06-06 | IFQ | OL1-2I20-5622 | IE | 2019-06-07 | 036909C-JVD-TRN-01828 | 036909C-JVD-TRN-01828 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK- LSPA1-T-IE-01828 |  | 2019-06-10 | 3
036909C-1053-SP-1546-5307 | Instrument Datasheets for Flow Element - Pitot - Area 53 | A | 2019-06-03 | IFQ | OL1-2I20-5325 | IE | 2019-06-07 | 036909C-JVD-TRN-01828 | 036909C-JVD-TRN-01828 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK- LSPA1-T-IE-01828 |  | 2019-06-10 | 3
036909C-1053-SP-1546-5302 | Instrument Datasheets for Flow Element - Orifice - Area 53 | A | 2019-06-03 | IFQ | OL1-2I20-5322 | IE | 2019-06-07 | 036909C-JVD-TRN-01828 | 036909C-JVD-TRN-01828 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK- LSPA1-T-IE-01828 |  | 2019-06-10 | 3
036909C-1053-SP-1541-5303 | Instrument Datasheets for Control Valve -Butterfly Type - Area 53 | A | 2019-06-07 | IFQ | OL1-2I20-5302 | IE | 2019-06-10 | 036909C-JVD-TRN-01845 | 036909C-JVD-TRN-01845 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01845 |  | 2019-06-11 | 3
036909C-1053-SP-1541-5301 | Instrument Datasheets for Control Valve - Globe Type - Area 53 | A | 2019-06-06 | IFQ | OL1-2I20-5301 | IE | 2019-06-10 | 036909C-JVD-TRN-01845 | 036909C-JVD-TRN-01845 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01845 |  | 2019-06-11 | 3
036909C-1054-SP-1546-5402 | Instrument Datasheets for Flow Element - Orifice- Area 54 | A | 2019-05-25 | IFQ | OL1-2I20-5422 | IE | 2019-06-03 | 036909C-JVD-TRN-01792 | 036909C-JVD-TRN-01792 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01792 |  | 2019-06-10 | 3
036909C-1054-SP-1541-5401 | Instrument Datasheets Control Valve - Globe Type - Area 54 | A | 2019-05-24 | IFQ | OL1-2120-5401 | IE | 2019-06-03 | 036909C-JVD-TRN-01792 | 036909C-JVD-TRN-01792 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01792 |  | 2019-06-10 | 3
036909C-1024-SP-1546-2407 | Instrument Datasheets for Flow Element -Pitot - Area 24 | A | 2019-04-22 | IFQ | OL1-2I20-2425 | IE | 2019-04-22 | 036909C-JVD-TRN-01428 | 036909C-JVD-TRN-01428 | IFI |  | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-01428 |  | 2019-04-23 | 3
036909C-103S-DW-1663-0001 | Substation Monitoring & Control System Block Diagram for Substation C | A | 2019-06-13 | IFR | OL1-2E18-0002 | EE | 2019-06-14 | 036909C-JVD-TRN-01895 | 036909C-JVD-TRN-01895 | IFR | 2019-06-28 | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-EE-01895 |  | 2019-06-14 | 2
036909C-100S-DW-1663-0001 | Substation Monitoring & Control System Block Diagram for Substation E | A | 2019-06-13 | IFR | OL1-2E18-0001 | EE | 2019-06-14 | 036909C-JVD-TRN-01895 | 036909C-JVD-TRN-01895 | IFR | 2019-06-28 | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-EE-01895 |  | 2019-06-14 | 2
036909C-1000-DW-1612-0001 | Overall Earthing Layout | A | 2019-06-13 | IFR | OL1-2E52-0001 | EE | 2019-06-14 | 036909C-JVD-TRN-01894 | 036909C-JVD-TRN-01894 | IFR | 2019-06-28 | 2019-07-01 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-01894 |  | 2019-06-14 | 1
036909C-105F-DW-1663-0001 | Substation Monitoring & Control System Block Diagram for Substation F | A | 2019-06-13 | IFR | OL1-2E18-0003 | EE | 2019-06-14 | 036909C-JVD-TRN-01895 | 036909C-JVD-TRN-01895 | IFR | 2019-06-28 | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-EE-01895 |  | 2019-06-14 | 2
036909C-1000-DL-0213-0001 | Deviation List for Condensate Polisher Package | B | 2019-06-18 | IFR | OL1-2C40-701000 | PL | 2019-06-19 | 036909C-JVD-TRN-01922 | 036909C-JVD-TRN-01922 | IFR | 2019-07-03 | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-PL-01922 |  | 2019-06-20 | 2
036909C-1000-DL-0184-0001 | Deviation List for HP/Polyolefins Flare Package | B | 2019-05-21 | IFR | OL1-2C40-708000 | PL | 2019-05-21 | 036909C-JVD-TRN-01705 | 036909C-JVD-TRN-01705 | IFR | 2019-06-04 | 2019-06-18 | R2-Comments as noted | LSPA1-TPSK-T-PL-01705 |  | 2019-05-21 | 2
036909C-102A-DW-1980-0001 | Passive Fire Protection Drawing - Zone 2A - Quench | A | 2019-05-24 | IFR | OL1-2F45-0002 | FF | 2019-05-28 | 036909C-JVD-TRN-01751 | 036909C-JVD-TRN-01751 | IFR | 2019-06-11 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-FF-01751 |  | 2019-05-28 | 2
036909C-1000-JSD-1530-0001 | Intercom-Paging-Audible Alarm System | 0 | 2019-02-19 | IMP | OL1-2R05-0013 | EE | 2019-03-07 | 036909C-JVD-TRN-00987 | 036909C-JVD-TRN-00987, ROC-TPSK-CECO-T-00003 | IFR | 2019-03-22 | 2019-03-21 | R2-Comments as noted | TPSK-LSPA1-T-EE-00987 |  | 2019-03-06 | 2
036909C-1026-SP-1543-2614 | Instrument Datasheets for Motor Operated Valve - Area 26 | A | 2019-05-31 | IFQ | OL1-2I20-2613 | IE | 2019-06-03 | 036909C-JVD-TRN-01792 | 036909C-JVD-TRN-01792 | IFI |  | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-IE-01792 |  | 2019-06-10 | 3
036909C-1028-SP-1541-2803 | Instrument Datasheets for Control Valve -Butterfly Type- Area 28 | A | 2019-04-23 | IFQ | OL1-2I20-2802 | IE | 2019-04-24 | 036909C-JVD-TRN-01464 | 036909C-JVD-TRN-01464, ROC-TPSK-CECO-T-00056 | IFI |  | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-IE-01464 |  | 2019-04-25 | 3
036909C-1052-SP-1541-5203 | Instrument Datasheets for Control Valve - Butterfly Type - Area 52 | A | 2019-05-27 | IFQ | OL1-2I20-5202 | IE | 2019-06-03 | 036909C-JVD-TRN-01792 | 036909C-JVD-TRN-01792 | IFI |  | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-IE-01792 |  | 2019-06-10 | 3
036909C-1021-SP-1541-2103 | Instrument Datasheets for Control Valve - Butterfly Type- Area 21 | A | 2019-05-14 | IFQ | OL1-2I20-2102 | IE | 2019-05-14 | 036909C-JVD-TRN-01660 | 036909C-JVD-TRN-01660 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01660 |  | 2019-05-15 | 3
036909C-1025-SP-1543-2514 | Instrument Datasheets for Motor Operated Valve Area 25 | A | 2019-05-13 | IFQ | OL1-2I20-2513 | IE | 2019-05-14 | 036909C-JVD-TRN-01660 | 036909C-JVD-TRN-01660 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01660 |  | 2019-05-15 | 3
036909C-1039-PDS-0900-3908 | Process Equipment Datasheet - 10-P-3908 A-B - BDU Predistillation Inhibitor Dosing Pump | B | 2019-06-20 | IFR | OL1-2G30-3908 | PE | 2019-06-24 | 036909C-JVD-TRN-01978 | 036909C-JVD-TRN-01978 | IFR | 2019-07-08 |  | Transmitted | TPSK-LSPA1-T-PE-01978 |  | 2019-06-25 | 2
036909C-1012-DW-0131-2560 | USC 132U Cracking Furnace Steel Standard Sections and Details | 0 | 2019-06-24 | IMP | OL1-2K32-2560 | CV | 2019-06-25 | 036909C-JVD-TRN-01994 | 036909C-JVD-TRN-01994 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01994 |  | 2019-06-26 | 3
036909C-1012-MR-1546-2062 | Material Requisition for Flow Element Venturi | A | 2019-06-24 | IFQ | OL1-2C17-012062 | PL | 2019-06-26 | 036909C-JVD-TRN-02011 | 036909C-JVD-TRN-02011 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02011 |  | 2019-06-27 | 3
036909C-1012-MR-1399-2103 | Material Requisition for SP Item T-Type Filter | A | 2019-06-06 | IFQ | OL1-2C14-504000 | PL | 2019-06-25 | 036909C-JVD-TRN-01996 | 036909C-JVD-TRN-01996 | IFR | 2019-07-10 |  | Transmitted | TPSK-LSPA1-T-PL-01996 |  | 2019-06-26 | 3
036909C-1011-DW-0117-1560 | USC 36M Recycle Furnace Steel Standard Sections and Details | 0 | 2019-06-24 | IMP | OL1-2K32-1560 | CV | 2019-06-25 | 036909C-JVD-TRN-01994 | 036909C-JVD-TRN-01994 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01994 |  | 2019-06-26 | 3
036909C-1000-TBT-0910-0003 | Technical Bid Evaluation Report for Cooling Water Pumps | C | 2019-05-28 | IFA | OL1-2C23-440003 | PL | 2019-06-11 | 036909C-JVD-TRN-01855 | 036909C-JVD-TRN-01855 | IFA | 2019-06-25 | 2019-06-27 | R1-No comments | TPSK-LSPA1-T-PL-01855 |  | 2019-06-11 | 1
036909C-1000-PP-502 | Confidentiality Plan | 0 | 2019-06-14 | IMP | OL1-2Q92-0002 | QM | 2019-07-03 | 036909C-JVD-TRN-01998 | 036909C-JVD-TRN-01998 | IFR | 2019-07-10 |  | Transmitted | TPSK-LSPA1-T-QM-01998 |  | 2019-06-27 | 2
036909C-1000-MS-2000-0001 | Technical Specification For Buildings | C | 2019-06-25 | IFQ | OL1-2R02-5001 | CV | 2019-06-26 | 036909C-JVD-TRN-01997 | 036909C-JVD-TRN-01997 | IFR | 2019-07-10 |  | Transmitted | TPSK-LSPA1-T-CV-01997 |  | 2019-06-26 | 2
036909C-1052-SP-1541-5201 | Instrument Datasheets for Control Valve - Globe Type - Area 52 | A | 2019-05-27 | IFQ | OL1-2I20-5201 | IE | 2019-06-03 | 036909C-JVD-TRN-01792 | 036909C-JVD-TRN-01792 | IFI |  | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-IE-01792 |  | 2019-06-10 | 3
036909C-1050-SP-1541-5001 | Instrument Datasheets for Control Valve - Globe Type - Area 50 | A | 2019-05-25 | IFQ | OL1-2120-5001 | IE | 2019-05-30 | 036909C-JVD-TRN-01774 | 036909C-JVD-TRN-01774 | IFI |  | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-IE-01774 |  | 2019-05-31 | 3
036909C-1029-SP-1541-2901 | Instrument Datasheets for Control Valve - Globe Type - Area 29 | A | 2019-05-21 | IFQ | OL1-2I20-2901 | IE | 2019-05-22 | 036909C-JVD-TRN-01717 | 036909C-JVD-TRN-01717 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01717 |  | 2019-05-23 | 3
036909C-1025-SP-1542-2503 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 25 | A | 2019-05-17 | IFQ | OL1-2I20-2506 | IE | 2019-05-20 | 036909C-JVD-TRN-01692 | 036909C-JVD-TRN-01692 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01692 |  | 2019-05-21 | 3
036909C-1028-SP-1541-2801 | Instrument Datasheets for Control Valve - Globe Type -Area 28 | A | 2019-04-23 | IFQ | OL1-2I20-2801 | IE | 2019-04-24 | 036909C-JVD-TRN-01464 | 036909C-JVD-TRN-01464, ROC-TPSK-CECO-T-00056 | IFI |  | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-IE-01464 |  | 2019-04-25 | 3
036909C-1011-SP-1541-1101 | Instrument Datasheets for Control Valve -Globe Type- Area 11 -BOP | A | 2019-05-03 | IFQ | OL1-2I20-1101 | IE | 2019-05-06 | 036909C-JVD-TRN-01581 | 036909C-JVD-TRN-01581 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-01581 |  | 2019-05-07 | 3
036909C-1020-SP-1541-2001 | Instrument Datasheets for Control Valve -Globe Type- Area 20 | A | 2019-05-09 | IFQ | OL1-2I20-2001 | IE | 2019-05-13 | 036909C-JVD-TRN-01650 | 036909C-JVD-TRN-01650 | IFI |  | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-IE-01650 |  | 2019-05-14 | 3
036909C-1021-SP-1541-2101 | Instrument Datasheets for Control Valve - Globe Type- Area 21 | A | 2019-05-14 | IFQ | OL1-2I20-2101 | IE | 2019-05-14 | 036909C-JVD-TRN-01660 | 036909C-JVD-TRN-01660 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01660 |  | 2019-05-15 | 3
036909C-1000-JSS-1300-01 | General Supply Specification For Piping Material | 0 | 2019-02-27 | IMP | OL1-2R04-0006 | MP | 2019-02-28 | 036909C-JVD-TRN-00951 | 036909C-JVD-TRN-00951 | IFR | 2019-03-15 | 2019-04-01 | R2-Comments as noted | TPSK-LSPA1-T-MP-00951 |  | 2019-03-01 | 2
036909C-103A-DW-1980-0001 | Passive Fire Protection Drawing - Zone 3A - Butadiene Extraction Unit | A | 2019-05-24 | IFR | OL1-2F45-0007 | FF | 2019-05-28 | 036909C-JVD-TRN-01751 | 036909C-JVD-TRN-01751 | IFR | 2019-06-11 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-FF-01751 |  | 2019-05-28 | 2
036909C-102E-DW-1980-0001 | Passive Fire Protection Drawing - Zone 2E - Cracked Gas Compressor | A | 2019-05-24 | IFR | OL1-2F45-0006 | FF | 2019-05-28 | 036909C-JVD-TRN-01751 | 036909C-JVD-TRN-01751 | IFR | 2019-06-11 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-FF-01751 |  | 2019-05-28 | 2
036909C-102D-DW-1980-0001 | Passive Fire Protection Drawing - Zone 2D - Process Cold Compressor | A | 2019-05-24 | IFR | OL1-2F45-0005 | FF | 2019-05-28 | 036909C-JVD-TRN-01751 | 036909C-JVD-TRN-01751 | IFR | 2019-06-11 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-FF-01751 |  | 2019-05-28 | 2
036909C-102C-DW-1980-0001 | Passive Fire Protection Drawing - Zone 2C - Hot Fractionation / GHU Unit | A | 2019-05-24 | IFR | OL1-2F45-0004 | FF | 2019-05-28 | 036909C-JVD-TRN-01751 | 036909C-JVD-TRN-01751 | IFR | 2019-06-11 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-FF-01751 |  | 2019-05-28 | 2
036909C-102B-DW-1980-0001 | Passive Fire Protection Drawing - Zone 2B - C3 Hydrogenation | A | 2019-05-24 | IFR | OL1-2F45-0003 | FF | 2019-05-28 | 036909C-JVD-TRN-01751 | 036909C-JVD-TRN-01751 | IFR | 2019-06-11 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-FF-01751 |  | 2019-05-28 | 2
036909C-101B-DW-1980-0001 | Passive Fire Protection Drawing - Zone 1B - Furnace Utilities | A | 2019-05-24 | IFR | OL1-2F45-0001 | FF | 2019-05-28 | 036909C-JVD-TRN-01751 | 036909C-JVD-TRN-01751 | IFR | 2019-06-11 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-FF-01751 |  | 2019-05-28 | 2
036909C-1000-DW-1980-0001 | Overall Passive Fire Protection Drawing | A | 2019-05-24 | IFR | OL1-2F45-1000 | FF | 2019-05-28 | 036909C-JVD-TRN-01751 | 036909C-JVD-TRN-01751 | IFR | 2019-06-11 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-FF-01751 |  | 2019-05-28 | 2
036909C-PO-036909C001P12-0102 | Purchase Order for MR-0310-0001 - Cooling Tower | 0 | 2019-05-03 | IFI | OL1-2C51-0102 | PL | 2019-06-10 | 036909C-JVD-TRN-01842 | 036909C-JVD-TRN-01842 | IFR | 2019-06-24 | 2019-06-28 | R1-No comments | TPSK-LSPA1-T-PL-01842 |  | 2019-06-10 | 3
036909C-1000-MR-0610-0005 | Material Requisition For CS S&T Heat Exchangers (C4 UNIT) | A | 2019-06-04 | IFQ | OL1-2C13-275000 | PL | 2019-06-10 | 036909C-JVD-TRN-01838 | 036909C-JVD-TRN-01838 | IFR | 2019-06-24 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-PL-01838 |  | 2019-06-10 | 2
036909C-1057-NM-1932-0001 | Line Designation Table - Fire Water | A | 2019-06-04 | IFR | OL1-2P91-5701 | MP | 2019-06-10 | 036909C-JVD-TRN-01841 | 036909C-JVD-TRN-01841 | IFR | 2019-06-24 | 2019-06-27 | R1-No comments | TPSK-LSPA1-T-MP-01841 |  | 2019-06-10 | 2
036909C-105W-NM-1350-0030 | Loads On Sleeper Way 10-SLW-5W01 | A | 2019-06-04 | IFD | OL1-2P05-0251 | MP | 2019-06-10 | 036909C-JVD-TRN-01839 | 036909C-JVD-TRN-01839 | IFR | 2019-06-24 | 2019-06-27 | R1-No comments | TPSK-LSPA1-T-MP-01839 |  | 2019-06-10 | 2
036909C-105U-NM-1350-0031 | Loads On Rack 10-PRK-5U01 | A | 2019-06-04 | IFD | OL1-2P05-0231 | MP | 2019-06-10 | 036909C-JVD-TRN-01839 | 036909C-JVD-TRN-01839 | IFR | 2019-06-24 | 2019-06-27 | R1-No comments | TPSK-LSPA1-T-MP-01839 |  | 2019-06-10 | 2
036909C-1000-TBT-1031-0001 | Technical Bid Evaluation Report for Recycle Gas Compressor Package | B | 2019-05-28 | IFA | OL1-2C23-403000 | PL | 2019-06-12 | 036909C-JVD-TRN-01874 | 036909C-JVD-TRN-01874 | IFA | 2019-06-25 | 2019-06-27 | R1-No comments |  |  | 2019-06-12 | 1
036909C-1052-SP-1546-5202 | Instrument Datasheets for Flow Element -Orifice- Area 52 | A | 2019-05-27 | IFQ | OL1-2I20-5222 | IE | 2019-06-03 | 036909C-JVD-TRN-01792 | 036909C-JVD-TRN-01792 | IFI |  | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-IE-01792 |  | 2019-06-10 | 3
036909C-1010-SP-1513-1002 | Instrument Interlock Descriptions - Area 10 - Feed Preparation and Feed Preheat | A | 2019-03-13 | IFR | OL1-2I30-1002 | IE | 2019-03-13 | 036909C-JVD-TRN-01045 | 036909C-JVD-TRN-01045 | IFR | 2019-03-28 | 2019-04-10 | R2-Comments as noted | TPSK-LSPA1-T-IE-01045 |  | 2019-03-14 | 2
036909C-1011-SP-1546-1162 | Instrument Datasheets for Flow Element Venturi | A | 2019-05-28 | IFR | OL1-2I20-1162 | IE | 2019-05-28 | 036909C-JVD-TRN-01757 | 036909C-JVD-TRN-01757 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-IE-01757 |  | 2019-05-29 | 2
036909C-1010-SP-1513-1001 | Complex Loop Narratives Area 10 - Feed Preparation and Feed Preheat | A | 2019-03-21 | IFR | OL1-2I71-1001 | IE | 2019-03-21 | 036909C-JVD-TRN-01128 | 036909C-JVD-TRN-01128 | IFR | 2019-04-05 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01128 |  | 2019-03-22 | 2
036909C-101A-DW-0051-0001 | Detail Plot Plan Zone 1A Furnaces | B | 2019-05-21 | IBD | OL1-2P06-0006 | MP | 2019-05-28 | 036909C-JVD-TRN-01752 | 036909C-JVD-TRN-01752 | IFR | 2019-06-12 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01752 |  | 2019-05-29 | 2
036909C-1000-MS-1320-0052 | Job Construction Specification For Pressure Testing | 0 | 2019-05-16 | IFC | OL1-2P92-0008 | MP | 2019-05-23 | 036909C-JVD-TRN-01726 | 036909C-JVD-TRN-01726 | IFR | 2019-06-07 | 2019-06-14 | R2-Comments as noted | TPSK-LSPA1-T-MP-01726 |  | 2019-05-24 | 2
036909C-100M-DW-0053-0001 | Detail Key Plan Zone 0M - Metering Station | A | 2019-04-19 | IFR | OL1-2P06-0021 | MP | 2019-04-24 | 036909C-JVD-TRN-01468 | 036909C-JVD-TRN-01468 | IFR | 2019-05-09 | 2019-06-14 | R2-Comments as noted | TPSK-LSPA1-T-MP-01468 |  | 2019-04-25 | 2
036909C-100P-NM-1350-0032 | Loads On Rack 10-PRK-0P03 | A | 2019-04-19 | IBD | OL1-2P05-0043 | MP | 2019-04-23 | 036909C-JVD-TRN-01439 | 036909C-JVD-TRN-01439 | IFR | 2019-05-08 | 2019-06-14 | R2-Comments as noted | TPSK-LSPA1-T-MP-01439 |  | 2019-04-24 | 2
036909C-100P-NM-1350-0031 | Loads On Rack 10-PRK-0P02 | A | 2019-04-12 | IBD | OL1-2P05-0042 | MP | 2019-04-23 | 036909C-JVD-TRN-01439 | 036909C-JVD-TRN-01439 | IFR | 2019-05-08 | 2019-06-14 | R2-Comments as noted | TPSK-LSPA1-T-MP-01439 |  | 2019-04-24 | 2
036909C-101A-DW-1331-0001 | GAD KEY PLAN - ZONE 1A - FURNACES | A | 2019-04-16 | IFR | OL1-2P06-0086 | MP | 2019-04-17 | 036909C-JVD-TRN-01394 | 036909C-JVD-TRN-01394, ROC-TPSK-CECO-T-00052 | IFR | 2019-05-02 | 2019-06-14 | R1-No comments | TPSK-LPSA1-T-MP-01394 |  | 2019-04-18 | 2
036909C-105U-DW-1331-0001 | GAD KEY PLAN - ZONE 5U - UTILITIES | A | 2019-04-16 | IFR | OL1-2P06-0084 | MP | 2019-04-17 | 036909C-JVD-TRN-01394 | 036909C-JVD-TRN-01394, ROC-TPSK-CECO-T-00052 | IFR | 2019-05-02 | 2019-06-14 | R1-No comments | TPSK-LPSA1-T-MP-01394 |  | 2019-04-18 | 2
036909C-105T-DW-1331-0001 | GAD KEY PLAN - ZONE 5T - COOLING WATER | A | 2019-04-16 | IFR | OL1-2P06-0083 | MP | 2019-04-17 | 036909C-JVD-TRN-01394 | 036909C-JVD-TRN-01394, ROC-TPSK-CECO-T-00052 | IFR | 2019-05-02 | 2019-06-14 | R2-Comments as noted | TPSK-LPSA1-T-MP-01394 |  | 2019-04-18 | 2
036909C-105F-DW-1331-0001 | GAD KEY PLAN - ZONE 5F - HP & POLYOLEFINS FLARES | A | 2019-04-16 | IFR | OL1-2P06-0081 | MP | 2019-04-17 | 036909C-JVD-TRN-01394 | 036909C-JVD-TRN-01394, ROC-TPSK-CECO-T-00052 | IFR | 2019-05-02 | 2019-06-14 | R2-Comments as noted | TPSK-LPSA1-T-MP-01394 |  | 2019-04-18 | 2
036909C-103A-DW-1331-0001 | GAD KEY PLAN - ZONE 3A - BUTADIENE EXTRACTION | A | 2019-04-16 | IFR | OL1-2P06-0079 | MP | 2019-04-17 | 036909C-JVD-TRN-01394 | 036909C-JVD-TRN-01394, ROC-TPSK-CECO-T-00052 | IFR | 2019-05-02 | 2019-06-14 | R2-Comments as noted | TPSK-LPSA1-T-MP-01394 |  | 2019-04-18 | 2
036909C-102E-DW-1331-0001 | GAD KEY PLAN - ZONE 2E - CRACKED GAS COMPRESSOR | A | 2019-04-16 | IFR | OL1-2P06-0078 | MP | 2019-04-17 | 036909C-JVD-TRN-01394 | 036909C-JVD-TRN-01394, ROC-TPSK-CECO-T-00052 | IFR | 2019-05-02 | 2019-06-14 | R2-Comments as noted | TPSK-LPSA1-T-MP-01394 |  | 2019-04-18 | 2
036909C-1000-MS-2000-0001 | Technical Specification For Buildings | A | 2019-03-19 | IFQ | OL1-2K97-0001 | CV | 2019-03-21 | 036909C-JVD-TRN-01117 | 036909C-JVD-TRN-01117 | IFR | 2019-04-03 |  | Transmitted | 1117-TPSK-LSPA1-T-CV-01117 |  | 2019-03-21 | 2
036909C-1012-DW-0131-2560 | USC 132U Cracking Furnace Steel Standard Sections and Details | A | 2019-04-05 | IFI | OL1-2K32-2560 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1011-DW-0117-1560 | USC 36M Recycle Furnace Steel Standard Sections and Details | A | 2019-04-05 | IFI | OL1-2K32-1560 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1027-PDS-0600-2716 | Process Equipment Datasheet - 10-E-2714 - C5 Cut Cooler | B | 2019-03-28 | IFD | OL1-2G30-2716 | PE | 2019-03-28 | 036909C-JVD-TRN-01187 | 036909C-JVD-TRN-01187 | IFR | 2019-04-12 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01187 |  | 2019-03-29 | 2
036909C-1000-MR-0511-0002 | Material Requisition For Shop Assembled Columns | A | 2019-01-18 | IFQ | OL1-2C13-101000 | PL | 2019-01-23 | 036909C-JVD-TRN-00705 | 036909C-JVD-TRN-00705 | IFR | 2019-02-06 | 2019-06-06 | R1-No comments | TPSK-LSPA1-T-PL-00705 |  | 2019-01-23 | 2
036909C-1025-SP-0510-2510 | Mechanical Equipment Data Sheet - Demethanizer Prefractionator & Reflux Drum | C | 2019-02-28 | IFQ | OL1-2M03-2510 | ME | 2019-03-01 | 036909C-JVD-TRN-00970 | 036909C-JVD-TRN-00970, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-16 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-00970 |  | 2019-03-04 | 2
036909C-1026-PDS-0400-2620 | Process Equipment Data Sheet - 10-R-2620 - C3 Hydrog Reactor | B | 2019-02-20 | IFD | OL1-2G30-2620 | PE | 2019-02-21 | 036909C-JVD-TRN-00910 | 036909C-JVD-TRN-00910 | IFR | 2019-03-08 | 2019-03-19 | 036909C-JVD-CLIENT-COMMENT-TRN-01405 - 25-June-2019 R2-Comments as noted | TPSK-LSPA1-T-PE-00910 |  | 2019-02-22 | 2
036909C-1012-DW-0125-2304 | USC 132U Recycle Furnace Steel End Wall Tubesheet Details | 0 | 2019-05-24 | IMP | OL1-2K32-2304 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1012-DW-0117-2555 | USC 132U Cracking Furnace Steel Inspection Door Lance Door and Access Door Details | 0 | 2019-05-24 | IMP | OL1-2K32-2555 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | LSPA1-TPSK-T-CV-0903 | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1012-DW-0131-2525 | USC 132U Cracking Furnace Steel Convection Section Header Box Details | 0 | 2019-05-24 | IMP | OL1-2K32-2525 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1012-DW-0131-2524 | USC 132U Cracking Furnace Steel Convection End Wall Tubesheet Details | 0 | 2019-05-24 | IMP | OL1-2K32-2524 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1012-DW-0117-2553 | USC 132U Cracking Furnace Steel Radiant Coil Tube Pulling Panel Detail | 0 | 2019-05-15 | IMP | OL1-2K32-2553 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1012-DW-0131-2661 | USC 36M Recycle Furnace and 132U Cracking Furnaces Steel Platform and TOE Details | 0 | 2019-04-30 | IMP | OL1-2K32-2661 | CV | 2019-05-06 | 036909C-JVD-TRN-01585 | 036909C-JVD-TRN-01585 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01585 |  | 2019-05-07 | 3
036909C-1012-DW-0131-2519 | USC 132U Cracking Furnace Steel Radiant Sections And Details | 0 | 2019-05-15 | IMP | OL1-2K32-2519 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1012-DW-0131-2517 | USC 132U Cracking Furnace Steel Radiant Sections And Details | 0 | 2019-05-15 | IMP | OL1-2K32-2517 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-102D-DW-1331-0001 | GAD KEY PLAN - ZONE 2D - PROCESS COLD COMPRESSOR | A | 2019-04-16 | IFR | OL1-2P06-0077 | MP | 2019-04-17 | 036909C-JVD-TRN-01394 | 036909C-JVD-TRN-01394, ROC-TPSK-CECO-T-00052 | IFR | 2019-05-02 | 2019-06-14 | R2-Comments as noted | TPSK-LPSA1-T-MP-01394 |  | 2019-04-18 | 2
036909C-1011-DW-0117-1555 | USC 36M Recycle Furnace Steel Inspection Door Lance Door and Access Door Details | 0 | 2019-05-24 | IMP | OL1-2K32-1555 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1011-DW-0117-1553 | USC 36M Recycle Furnace Steel Radiant Coil Tube Pulling Panel Details | 0 | 2019-05-15 | IMP | OL1-2K32-1553 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-102C-DW-1331-0001 | GAD KEY PLAN - ZONE 2C - HOT FRACTIONATION GHU | A | 2019-04-16 | IFR | OL1-2P06-0076 | MP | 2019-04-17 | 036909C-JVD-TRN-01394 | 036909C-JVD-TRN-01394, ROC-TPSK-CECO-T-00052 | IFR | 2019-05-02 | 2019-06-14 | R2-Comments as noted | TPSK-LPSA1-T-MP-01394 |  | 2019-04-18 | 2
036909C-1031-PDS-0600-3111 | Process Equipment Datasheet - 10-E-3110 - Water Washer Condenser | B | 2019-05-30 | IFD | OL1-2G30-3111 | PE | 2019-05-30 | 036909C-JVD-TRN-01786 | 036909C-JVD-TRN-01786 | IFR | 2019-06-14 | 2019-06-25 | R1-No comments | TPSK-LSPA1-T-PE-01786 |  | 2019-05-31 | 2
036909C-1030-PDS-0600-3045 | Process Equipment Datasheet - 10-E-3045 A-D - Solvent Heat Exchanger | B | 2019-05-29 | IFD | OL1-2G30-3045 | PE | 2019-05-30 | 036909C-JVD-TRN-01776 | 036909C-JVD-TRN-01776 | IFR | 2019-06-14 | 2019-06-25 | R1-No comments | TPSK-LSPA1-T-PE-01776 |  | 2019-05-31 | 2
036909C-1030-PDS-0600-3044 | Process Equipment Datasheet - 10-E-3044 - Solvent Heater | B | 2019-05-29 | IFD | OL1-2G30-3044 | PE | 2019-05-30 | 036909C-JVD-TRN-01776 | 036909C-JVD-TRN-01776 | IFR | 2019-06-14 | 2019-06-25 | R1-No comments | TPSK-LSPA1-T-PE-01776 |  | 2019-05-31 | 2
036909C-102B-DW-1331-0001 | GAD KEY PLAN - ZONE 2B - C3 HYDROGENATION | A | 2019-04-16 | IFR | OL1-2P06-0075 | MP | 2019-04-17 | 036909C-JVD-TRN-01394 | 036909C-JVD-TRN-01394, ROC-TPSK-CECO-T-00052 | IFR | 2019-05-02 | 2019-06-14 | R1-No comments | TPSK-LPSA1-T-MP-01394 |  | 2019-04-18 | 2
036909C-1012-TBT-0853-2011 | Technical Bid Tabulation For Attemperators | 0 | 2019-05-21 | IFI | OL1-2C23-2011 | PL | 2019-05-23 | 036909C-JVD-TRN-01734 | 036909C-JVD-TRN-01734 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-PL-01734 |  | 2019-05-24 | 3
036909C-100P-DW-1331-0001 | GAD KEY PLAN - ZONE 0P - MAIN PIPE RACK | A | 2019-04-16 | IFR | OL1-2P06-0070 | MP | 2019-04-17 | 036909C-JVD-TRN-01394 | 036909C-JVD-TRN-01394, ROC-TPSK-CECO-T-00052 | IFR | 2019-05-02 | 2019-06-14 | R2-Comments as noted | TPSK-LPSA1-T-MP-01394 |  | 2019-04-18 | 2
036909C-1012-MR-0131-2015 | Material Requisition for Convection Fabrication | 0 | 2019-05-29 | IFP | OL1-2C13-282000 | PL | 2019-06-04 | 036909C-JVD-TRN-01798 | 036909C-JVD-TRN-01798 | IFI |  | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PL-01798 |  | 2019-06-10 | 3
036909C-1012-MR-1399-2101 | Material Requisition for SP Item Angle Valves | A | 2019-05-24 | IFQ | OL1-2C14-502000 | PL | 2019-06-04 | 036909C-JVD-TRN-01800 | 036909C-JVD-TRN-01800 | IFI |  | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PL-01800 |  | 2019-06-10 | 3
036909C-1000-QCP-2000-0001 | Quality Control Plan Building -Concrete And Masonry- | A | 2019-05-02 | IFR | OL1-2Q21-0001 | QM | 2019-05-07 | 036909C-JVD-TRN-01596 | 036909C-JVD-TRN-01596 | IFA | 2019-05-22 | 2019-06-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-QM-01596 |  | 2019-05-08 | 1
036909C-1000-DW-1552-0001 | Level Instrument Design for Towers and Reactors | A | 2019-05-17 | IFR | OL1-2I31-0214 | IE | 2019-05-23 | 036909C-JVD-TRN-01725 | 036909C-JVD-TRN-01725 | IFA | 2019-06-07 | 2019-06-19 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-IE-01725 |  | 2019-05-24 | 1
036909C-1000-QCP-1680-0001 | Quality Control PlanElectrical InstallationLighting System | A | 2019-05-22 | IFR | OL1-2Q26-0007 | QM | 2019-05-27 | 036909C-JVD-TRN-01750 | 036909C-JVD-TRN-01750 | IFA | 2019-06-11 | 2019-06-18 | A1-Approved without comments | TPSK-LSPA1-T-QM-01750 |  | 2019-05-28 | 1
036909C-1000-QCP-1640-0001 | Quality Control Plan - Electrical Iinstallation - High Voltage Equipment | A | 2019-05-14 | IFR | OL1-2Q26-0004 | QM | 2019-05-16 | 036909C-JVD-TRN-01676 | 036909C-JVD-TRN-01676 | IFA | 2019-05-31 | 2019-06-18 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-QM-01676 |  | 2019-05-17 | 1
036909C-1000-QCP-2041-0001 | Quality Control Plan Building HVAC -Heating Ventilation And Air Conditioning- System Installation | A | 2019-05-02 | IFR | OL1-2Q26-0009 | QM | 2019-05-07 | 036909C-JVD-TRN-01596 | 036909C-JVD-TRN-01596 | IFA | 2019-05-22 | 2019-06-18 | A1-Approved without comments | TPSK-LSPA1-T-QM-01596 |  | 2019-05-08 | 1
036909C-1000-QCP-1610-0001 | Quality Control Plan - Electrical Installation - Grounding And Lightning System | A | 2019-05-14 | IFR | OL1-2Q26-0001 | QM | 2019-05-16 | 036909C-JVD-TRN-01676 | 036909C-JVD-TRN-01676 | IFA | 2019-05-31 | 2019-06-18 | A1-Approved without comments | TPSK-LSPA1-T-QM-01676 |  | 2019-05-17 | 1
036909C-1056-PDS-0200-5655 | Process Equipment Datasheet - 10-PIT-5655 - Bio Equalization Pit | B | 2019-03-26 | IFD | OL1-2G30-5655 | PE | 2019-03-27 | 036909C-JVD-TRN-01178 | 036909C-JVD-TRN-01178, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-11 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01178 |  | 2019-03-28 | 2
036909C-1011-SP-1565-1151 | Instrument Datasheets for O2 & Combustible Analyzer | A | 2019-05-28 | IFR | OL1-2I20-1151 | IE | 2019-05-29 | 036909C-JVD-TRN-01761 | 036909C-JVD-TRN-01761 | IFR | 2019-06-13 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-IE-01761 |  | 2019-05-30 | 2
036909C-1000-MR-0411-0001 | Material Requisition For Reactors And Thicker Vessels Requisition For Iinquiry | A | 2019-02-21 | IFQ | OL1-2C13-111000 | PL | 2019-02-25 | 036909C-JVD-TRN-00918 | 036909C-JVD-TRN-00918 | IFR | 2019-03-12 | 2019-06-06 | R1-No comments | TPSK-LSPA1-T-PL-00918 |  | 2019-02-26 | 2
036909C-1000-SP-0184-0002 | Mechanical Data Sheet for HP / Polyolefins Flare Package | A | 2019-01-15 | IFQ | OL1-2M03-5560 | ME | 2019-01-17 | 036909C-JVD-TRN-00667 | 036909C-JVD-TRN-00667 | IFR | 2019-01-30 | 2019-02-08 | R2-Comments as noted | TPSK-LSPA1-T-ME-00667 |  | 2019-01-17 | 2
036909C-1000-QCP-1690-0001 | Quality Control Plan -Electrical Installation- Rotating Equipment | A | 2019-05-17 | IFR | OL1-2Q26-0008 | QM | 2019-05-23 | 036909C-JVD-TRN-01724 | 036909C-JVD-TRN-01724 | IFA | 2019-06-07 | 2019-06-18 | A1-Approved without comments | TPSK-LSPA1-T-QM-01724 |  | 2019-05-24 | 1
036909C-1000-QCP-1620-0001 | Quality Control Plan -Electrical Installation- Substation Equipment | A | 2019-05-17 | IFR | OL1-2Q26-0002 | QM | 2019-05-23 | 036909C-JVD-TRN-01724 | 036909C-JVD-TRN-01724 | IFA | 2019-06-07 | 2019-06-18 | A1-Approved without comments | TPSK-LSPA1-T-QM-01724 |  | 2019-05-24 | 1
036909C-102E-DW-1743-0049-001 | Foundation For 10-E-2405 | A | 2019-05-06 | IFR | OL1-2K31-0340 | CV | 2019-05-14 | 036909C-JVD-TRN-01663 | 036909C-JVD-TRN-01663, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 | 2019-06-13 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01663 |  | 2019-05-15 | 1
036909C-102C-DW-1743-0002-001 | Foundation For 10-E-5113 | A | 2019-05-13 | IFR | OL1-2K31-0313 | CV | 2019-05-14 | 036909C-JVD-TRN-01663 | 036909C-JVD-TRN-01663, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 | 2019-06-13 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01663 |  | 2019-05-15 | 1
036909C-102C-DW-1743-0032-001 | Foundation For 10-E-2706 | A | 2019-05-09 | IFR | OL1-2K31-0190 | CV | 2019-05-14 | 036909C-JVD-TRN-01663 | 036909C-JVD-TRN-01663, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 | 2019-06-13 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01663 |  | 2019-05-15 | 1
036909C-102C-DW-1743-0025-001 | Foundation For 10-E-2755 | A | 2019-05-13 | IFR | OL1-2K31-0184 | CV | 2019-05-14 | 036909C-JVD-TRN-01663 | 036909C-JVD-TRN-01663, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 | 2019-06-13 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01663 |  | 2019-05-15 | 1
036909C-102E-DW-1743-0035-001 | Foundation For 10-R-2470A-B-C | A | 2019-05-13 | IFR | OL1-2K31-0154 | CV | 2019-05-14 | 036909C-JVD-TRN-01663 | 036909C-JVD-TRN-01663, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 | 2019-06-13 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01663 |  | 2019-05-15 | 1
036909C-102C-DW-1743-0016-001 | Foundation For 10-E-2666 | A | 2019-05-09 | IFR | OL1-2K31-0147 | CV | 2019-05-14 | 036909C-JVD-TRN-01663 | 036909C-JVD-TRN-01663, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 | 2019-06-13 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01663 |  | 2019-05-15 | 1
036909C-102C-DW-1743-0007-001 | Foundation For 10-R-2700A-B | A | 2019-05-13 | IFR | OL1-2K31-0143 | CV | 2019-05-14 | 036909C-JVD-TRN-01663 | 036909C-JVD-TRN-01663, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 | 2019-06-13 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01663 |  | 2019-05-15 | 1
036909C-102E-DW-1743-0025-001 | Foundation For 10-D-2420A-B | A | 2019-05-13 | IFR | OL1-2K31-0106 | CV | 2019-05-14 | 036909C-JVD-TRN-01663 | 036909C-JVD-TRN-01663, ROC-TPSK-CECO-T-00073 | IFA | 2019-05-29 | 2019-06-13 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01663 |  | 2019-05-15 | 1
036909C-1000-PP-810 | Site Inspection Coordination Procedure - Construction Precommissioning And Commissioning | A | 2019-06-17 | IFR | OL1-2Q92-0006 | QM | 2019-06-21 | 036909C-JVD-TRN-01956 | 036909C-JVD-TRN-01956 | IFR | 2019-07-08 |  | Transmitted | TPSK-LSPA1-T-QM-01956 |  | 2019-06-24 | 2
036909C-1024-SP-0410-2470 | Mechanical Equipment Data Sheet - C2 Hydrog Reactor | B | 2019-02-26 | IFQ | OL1-2M03-2470 | ME | 2019-02-28 | 036909C-JVD-TRN-00953 | 036909C-JVD-TRN-00953, ROC-TPSK-CECO-T-00014 | IFR | 2019-03-15 | 2019-03-25 | R2-Comments as noted | TPSK-LSPA1-T-ME-00953 |  | 2019-03-01 | 2
036909C-1012-MR-0137-2010 | Material Requisition for MOVs - Ex Doc. Client Reference OL1-2M55-2010 | 0 | 2019-03-28 | IFP | OL1-2C13-285000 | PL | 2019-04-01 | 036909C-JVD-TRN-01219 | 036909C-JVD-TRN-01219 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01219 | Ex Doc. Client Reference OL1-2M55-2010 | 2019-04-02 | 3
036909C-1012-MR-0133-2008 | Material Requisition for Peep Doors - Ex Doc. Client Reference OL1-2M55-2008 | 0 | 2019-03-19 | IFP | OL1-2C13-284000 | PL | 2019-03-27 | 036909C-JVD-TRN-01181 | 036909C-JVD-TRN-01181 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01181 | Ex Doc. Client Reference OL1-2M55-2008 | 2019-03-28 | 3
036909C-1012-MR-0133-2008 | Material Requisition for Peep Doors - For next Rev. see Doc. Client Ref. OL1-2C13-284000 | A | 2018-12-06 | IFQ | OL1-2C13-284000 | ME | 2018-12-14 | 036909C-JVD-TRN-00502 | 036909C-JVD-TRN-00502 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00502 | For next Rev. see Doc. Client Ref. OL1-2C13-284000 | 2018-12-14 | 3
036909C-1012-MR-0137-2010 | Material Requisition for MOVs - For next Rev. see Doc. Client Ref. OL1-2C13-285000 | A | 2018-12-12 | IFQ | OL1-2C13-285000 | ME | 2018-12-18 | 036909C-JVD-TRN-00534 | 036909C-JVD-TRN-00534 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00534 | For next Rev. see Doc. Client Ref. OL1-2C13-285000 | 2018-12-18 | 3
036909C-1012-MR-0191-2006 | Material Requisition for Furnace Burners - Ex Doc. Client Ref. OL1-2M55-2006 | 0 | 2019-01-31 | IFP | OL1-2C13-306000 | PL | 2019-02-07 | 036909C-JVD-TRN-00820 | 036909C-JVD-TRN-00820 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00820 | Ex Doc. Client Ref. OL1-2M55-2006 | 2019-02-07 | 3
036909C-1012-MR-1040-2005 | Material Requisition for Furnace ID Fans - Ex Doc. Client Ref. OL1-2M55-2005 | 0 | 2019-03-11 | IFP | OL1-2C13-301000 | PL | 2019-03-20 | 036909C-JVD-TRN-01109 | 036909C-JVD-TRN-01109 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01109 | Ex Doc. Client Ref. OL1-2M55-2005 | 2019-03-21 | 3
036909C-1012-JSS-0122-2002 | Project Specification for Statically Cast Fittings For Radiant Coils and Transfer Lines in Cracking Furnaces - Ex Doc. Client Ref. OL1-4M92-2002 | 0 | 2018-12-07 | IMP | OL1-2M92-2002 | ME | 2018-12-11 | 036909C-JVD-TRN-00471 | 036909C-JVD-TRN-00471 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00471 | Ex Doc. Client Ref. OL1-4M92-2002 | 2018-12-11 | 2
036909C-1012-MR-0127-2001 | Material Requisition for Convection Tubes - Ex Doc. Client Ref. OL1-2M55-2001 | 1 | 2019-03-11 | IFP | OL1-2C13-303000 | PL | 2019-03-25 | 036909C-JVD-TRN-01139 | 036909C-JVD-TRN-01139 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01139 | Ex Doc. Client Ref. OL1-2M55-2001 | 2019-03-26 | 3
036909C-1012-JSS-0122-2001 | Project Specification for Centrifugally Cast Tubes for Radiant Coils and Transfer Lines in Cracking Furnaces - Ex Doc. Client Ref. OL1-4M92-2001 | 0 | 2018-12-07 | IMP | OL1-2M92-2001 | ME | 2018-12-11 | 036909C-JVD-TRN-00470 | 036909C-JVD-TRN-00470 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00470 | Ex Doc. Client Ref. OL1-4M92-2001 | 2018-12-11 | 2
036909C-1011-DW-1514-1001 | Cause and Effect Diagram Cracking Furnaces - For next rev. see Doc. Client Ref. OL1-2G50-1001 | B | 2019-02-13 | IBD | OL1-2G50-1001 | IE | 2019-02-15 | 036909C-JVD-TRN-00860 | 036909C-JVD-TRN-00860, ROC-TPSK-CECO-T-00043 | IFR | 2019-02-28 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-IE-00556 | For next rev. see Doc. Client Ref. OL1-2G50-1001 | 2019-02-15 | 2
036909C-1011-DW-1514-1001 | 36M Cause and Effect Diagram Cracking Furnaces - Ex Doc. Client Ref. OL1-2I72-1001 | C | 2019-05-23 | IBD | OL1-2G50-1001 | PE | 2019-05-28 | 036909C-JVD-TRN-01758 | 036909C-JVD-TRN-01758 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01758 | Ex Doc. Client Ref. OL1-2I72-1001 | 2019-05-29 | 2
036909C-1000-MR-0845-0001 | Material Requisition for Deaerator D-5100 - Ex Doc. Client Ref. OL1-2M55-0108 | 0 | 2019-03-29 | IFP | OL1-2C13-120000 | PL | 2019-04-01 | 036909C-JVD-TRN-01210 | 036909C-JVD-TRN-01210 | IFR | 2019-04-16 | 2019-06-06 | R1-No comments | TPSK-LSPA1-T-PL-01210 | Ex Doc. Client Ref. OL1-2M55-0108 | 2019-04-02 | 2
036909C-1019-SP-1013-1950 | Mechanical Equipment Datasheet For Decoking Air Compressors | 0 | 2019-05-22 | IFP | OL1-2M03-1950 | ME | 2019-05-22 | 036909C-JVD-TRN-01715 | 036909C-JVD-TRN-01715 | IFR | 2019-06-06 | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-ME-01715 |  | 2019-05-23 | 2
036909C-1011-DW-0131-1525 | USC 36M Recycle Furnace Steel Convection Section Header Box Details | 0 | 2019-05-24 | IMP | OL1-2K32-1525 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1011-DW-0131-1524 | USC 36M Recycle Furnace Steel Convection Section End Wall Tubesheet Details | 0 | 2019-05-24 | IMP | OL1-2K32-1524 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1011-DW-0131-1519 | USC 36M Recycle Furnace Steel Radiant Sections and Details | 0 | 2019-05-15 | IMP | OL1-2K32-1519 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1011-DW-0131-1517 | USC 36M Recycle Furnace Steel Radiant Sections and Details | 0 | 2019-05-15 | IMP | OL1-2K32-1517 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1011-DW-1514-1002 | 132U Cause and Effect Diagram Cracking Furnaces | A | 2019-05-23 | IBD | OL1-2G50-1002 | PE | 2019-05-28 | 036909C-JVD-TRN-01758 | 036909C-JVD-TRN-01758 | IFR | 2019-06-12 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01758 |  | 2019-05-29 | 2
036909C-1011-DW-1514-1001 | Cause and Effect Diagram Cracking Furnaces | A | 2019-01-15 | IFR | OL1-2I72-1001 | IE | 2019-01-17 | 036909C-JVD-TRN-00674 | 036909C-JVD-TRN-00674 | IFR | 2019-01-31 | 2019-03-08 | R1-No comments | TPSK-LSPA1-T-IE-00674 |  | 2019-01-17 | 2
036909C-1050-SP-1546-5002 | Instrument Datasheets for Flow Element -Orifice - Area 50 | A | 2019-05-24 | IFQ | OL1-2I20-5022 | IE | 2019-05-30 | 036909C-JVD-TRN-01774 | 036909C-JVD-TRN-01774 | IFI |  | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-IE-01774 |  | 2019-05-31 | 3
036909C-1030-PDS-0900-3066 | Process Equipment Data Sheet - 10-P-3060 A-B - Wastewater Pump | B | 2019-06-20 | IFD | OL1-2G30-3066 | PE | 2019-06-20 | 036909C-JVD-TRN-01954 | 036909C-JVD-TRN-01953, 036909C-JVD-TRN-01954 | IFD | 2019-07-05 |  | Transmitted | TPSK-LSPA1-T-PE-01954 |  | 2019-06-21 | 2
036909C-1039-PDS-0900-3901 | Process Equipment Datasheet - 10-P-3900 - NMP Storage Pump | B | 2019-06-19 | IFD | OL1-2G30-3901 | PE | 2019-06-20 | 036909C-JVD-TRN-01954 | 036909C-JVD-TRN-01953, 036909C-JVD-TRN-01954 | IFD | 2019-07-05 |  | Transmitted | TPSK-LSPA1-T-PE-01954 |  | 2019-06-21 | 2
036909C-1039-PDS-0900-3903 | Process Equipment Datasheet - 10-P-3902 A-B - BDU Solvent Inhibitor Dosing Pump | B | 2019-06-20 | IFD | OL1-2G30-3903 | PE | 2019-06-20 | 036909C-JVD-TRN-01954 | 036909C-JVD-TRN-01953, 036909C-JVD-TRN-01954 | IFD | 2019-07-05 |  | Transmitted | TPSK-LSPA1-T-PE-01954 |  | 2019-06-21 | 2
036909C-1030-PDS-0900-3023 | Process Equipment Data Sheet - 10-P-3020 A-B - Main Washer Reflux - C4 Raffinate-I Pump | B | 2019-06-19 | IFD | OL1-2G30-3023 | PE | 2019-06-20 | 036909C-JVD-TRN-01954 | 036909C-JVD-TRN-01953, 036909C-JVD-TRN-01954 | IFD | 2019-07-05 |  | Transmitted | TPSK-LSPA1-T-PE-01954 |  | 2019-06-21 | 2
036909C-1030-PDS-0900-3026 | Process Equipment Data Sheet - 10-P-3026 A-B - Main Washer Bottom Pump | B | 2019-06-19 | IFD | OL1-2G30-3026 | PE | 2019-06-20 | 036909C-JVD-TRN-01954 | 036909C-JVD-TRN-01953, 036909C-JVD-TRN-01954 | IFD | 2019-07-05 |  | Transmitted | TPSK-LSPA1-T-PE-01954 |  | 2019-06-21 | 2
036909C-1030-PDS-0900-3046 | Process Equipment Data Sheet - 10-P-3046 A-B - Degasser Feed Pump | B | 2019-06-19 | IFD | OL1-2G30-3046 | PE | 2019-06-20 | 036909C-JVD-TRN-01954 | 036909C-JVD-TRN-01953, 036909C-JVD-TRN-01954 | IFD | 2019-07-05 |  | Transmitted | TPSK-LSPA1-T-PE-01954 |  | 2019-06-21 | 2
036909C-1030-PDS-0900-3056 | Process Equipment Data Sheet - 10-P-3056 A-B - Degasser Bottom Pump | B | 2019-06-20 | IFD | OL1-2G30-3056 | PE | 2019-06-20 | 036909C-JVD-TRN-01954 | 036909C-JVD-TRN-01953, 036909C-JVD-TRN-01954 | IFD | 2019-07-05 |  | Transmitted | TPSK-LSPA1-T-PE-01954 |  | 2019-06-21 | 2
036909C-1012-MR-0131-2016 | Material Requisition for Utility Steel | A | 2019-06-13 | IFQ | OL1-2C12-308000 | PL | 2019-06-20 | 036909C-JVD-TRN-01952 | 036909C-JVD-TRN-01952 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01952 |  | 2019-06-21 | 3
036909C-105U-CN-1733-0007 | Calculation Note For Foundation Of 10-E-5510 | A | 2019-05-17 | IFR | OL1-2K13-0254 | CV | 2019-05-21 | 036909C-JVD-TRN-01702 | 036909C-JVD-TRN-01702 | IFR | 2019-06-04 | 2019-06-20 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01702 |  | 2019-05-21 | 1
036909C-105U-CN-1733-0008 | Calculation Note For Foundation Of 10-E-5513 | A | 2019-05-17 | IFR | OL1-2K13-0255 | CV | 2019-05-21 | 036909C-JVD-TRN-01702 | 036909C-JVD-TRN-01702 | IFR | 2019-06-04 | 2019-06-20 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01702 |  | 2019-05-21 | 1
036909C-1012-MR-1554-2015 | Material Requisition for pH and Conductivity Analyzer | A | 2019-04-29 | IFQ | OL1-2C17-232015 | PL | 2019-05-24 | 036909C-JVD-TRN-01744 | 036909C-JVD-TRN-01744 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PL-01744 |  | 2019-05-27 | 3
036909C-1023-SP-4100-0002 | Mechanical Equipment Datasheet for Wet Air Oxidation Package | 1 | 2019-06-19 | IFP | OL1-2M03-2350 | ME | 2019-06-20 | 036909C-JVD-TRN-01944 | 036909C-JVD-TRN-01944 | IFR | 2019-07-04 |  | Transmitted | TPSK-LSPA1-T-ME-01944 |  | 2019-06-20 | 2
036909C-1000-MR-1684-0001 | Material Requisition For Cathodic Protection System | A | 2019-05-17 | IFQ | OL1-2C16-800000 | PL | 2019-05-24 | 036909C-JVD-TRN-01735 | 036909C-JVD-TRN-01735 | IFR | 2019-06-07 | 2019-06-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01735 |  | 2019-05-24 | 2
036909C-1000-DL-0310-0001 | Deviation List for Cooling Tower | B | 2019-03-07 | IFR | OL1-2C40-311000 | PL | 2019-03-08 | 036909C-JVD-TRN-00879 | 036909C-JVD-TRN-00879 | IFR | 2019-03-21 | 2019-06-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-00879 |  | 2019-03-08 | 2
036909C-1025-PDS-4100-2560 | Process Equipment Datasheet - 10-PK-2560 - PSA Unit | C | 2019-04-24 | IFD | OL1-2G30-2560 | PE | 2019-04-25 | 036909C-JVD-TRN-01485 | 036909C-JVD-TRN-01485 | IFR | 2019-05-10 | 2019-06-17 | CLIENT-COMMENT-TRN-01342-20 June 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01485 |  | 2019-04-26 | 2
036909C-103A-DW-1980-0001 | Passive Fire Protection Drawing - Zone 3A - Butadiene Extraction Unit | B | 2019-06-14 | IBD | OL1-2F45-0007 | FF | 2019-06-18 | 036909C-JVD-TRN-01914 | 036909C-JVD-TRN-01914 | IFR | 2019-07-02 |  | Transmitted | TPSK-LSPA1-T-FF-01914 |  | 2019-06-18 | 2
036909C-102E-DW-1980-0001 | Passive Fire Protection Drawing - Zone 2E - Cracked Gas Compressor | B | 2019-06-14 | IBD | OL1-2F45-0006 | FF | 2019-06-18 | 036909C-JVD-TRN-01914 | 036909C-JVD-TRN-01914 | IFR | 2019-07-02 |  | Transmitted | TPSK-LSPA1-T-FF-01914 |  | 2019-06-18 | 2
036909C-1028-PDS-1390-2843 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2884 - 10-SP-28508 | B | 2019-06-13 | IFR | OL1-2P03-2843 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1028-PDS-1390-2844 | Piping Specialty Item - Datasheet - Basket-Type Filter - LP Ethylene To D-2882 & E-2882 - 10-SP-28512 | B | 2019-06-13 | IFR | OL1-2P03-2844 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1028-PDS-1390-2828 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 3rd Stage Discharge - 10-SP-28602 | A | 2019-06-17 | IFR | OL1-2P03-2828 | MP | 2019-06-19 | 036909C-JVD-TRN-01938 | 036909C-JVD-TRN-01938 |  | 2019-07-04 |  | Transmitted | TPSK-LSPA1-T-MP-01938 |  | 2019-06-20 | 2
036909C-1025-PDS-1390-2518 | Piping Specialty Item - Datasheet - Basket-Type Filter - T-2520 BTMS To E-2530 - 10-SP-25018 | B | 2019-06-13 | IFR | OL1-2P03-2518 | MP | 2019-06-17 | 036909C-JVD-TRN-01913 | 036909C-JVD-TRN-01913 | IFR | 2019-07-02 |  | Transmitted | TPSK-LSPA1-T-MP-01913 |  | 2019-06-18 | 2
036909C-1025-PDS-1390-2519 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2530 - 10-SP-25019 | B | 2019-06-13 | IFR | OL1-2P03-2519 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1025-PDS-1390-2521 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To E-2540 - 10-SP-25021 | B | 2019-06-13 | IFR | OL1-2P03-2521 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1025-PDS-1390-2539 | Piping Specialty Item - Datasheet - Basket-Type Filter - T-2580 Bottoms Reboiler Inlet - 10-SP-25039 | B | 2019-06-13 | IFR | OL1-2P03-2539 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1025-PDS-1390-2534 | Piping Specialty Item - Datasheet - Basket-Type Filter - T-2580 Side Reboiler Inlet - 10-SP-25034 | B | 2019-06-13 | IFR | OL1-2P03-2534 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1025-PDS-1390-2531 | Piping Specialty Item - Datasheet - Basket-Type Filter - C3R To E-2500 - 10-SP-25031 | B | 2019-06-13 | IFR | OL1-2P03-2531 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1025-PDS-1390-2526 | Piping Specialty Item - Datasheet - Basket-Type Filter - Residue Gas To E-2525 - 10-SP-25026 | B | 2019-06-13 | IFR | OL1-2P03-2526 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1025-PDS-1390-2523 | Piping Specialty Item - Datasheet - T-Type Filter - C-2550 Residue Gas Recompressor Suction - 10-SP-25023 | A | 2019-06-12 | IFR | OL1-2P03-2523 | MP | 2019-06-18 | 036909C-JVD-TRN-01917 | 036909C-JVD-TRN-01917 | IFR |  |  | Transmitted | TPSK-LSPA1-T-MP-01917 |  | 2019-06-19 | 2
036909C-1025-PDS-1390-2512 | Piping Specialty Item - Datasheet - Basket-Type Filter - Methane Recycle To E-2520 - 10-SP-25012 | B | 2019-06-13 | IFR | OL1-2P03-2512 | MP | 2019-06-17 | 036909C-JVD-TRN-01913 | 036909C-JVD-TRN-01913 | IFR | 2019-07-02 |  | Transmitted | TPSK-LSPA1-T-MP-01913 |  | 2019-06-17 | 2
036909C-1025-PDS-1390-2511 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2521 - 10-SP-25011 | B | 2019-06-13 | IFR | OL1-2P03-2511 | MP | 2019-06-17 | 036909C-JVD-TRN-01913 | 036909C-JVD-TRN-01913 | IFR | 2019-07-02 |  | Transmitted | TPSK-LSPA1-T-MP-01913 |  | 2019-06-17 | 2
036909C-1056-PDS-0900-5641 | Process Equipment Datasheet - 10-P-5641 - Wastewater EQ Tank Skimmed Oil Pumps | B | 2019-03-21 | IFD | OL1-2G30-5641 | PE | 2019-03-25 | 036909C-JVD-TRN-01152 | 036909C-JVD-TRN-01152, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-09 | 2019-04-12 | CLIENT-COMMENT-TRN-01310- June 18 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-01152 |  | 2019-03-26 | 2
036909C-1025-PDS-1390-2510 | Piping Specialty Item - Datasheet - Basket-Type Filter - Demeth BTMS To E-2510 - 10-SP-25010 | B | 2019-06-13 | IFR | OL1-2P03-2510 | MP | 2019-06-17 | 036909C-JVD-TRN-01913 | 036909C-JVD-TRN-01913 | IFR | 2019-07-02 |  | Transmitted | TPSK-LSPA1-T-MP-01913 |  | 2019-06-17 | 2
036909C-1025-PDS-1390-2508 | Piping Specialty Item - Datasheet - Basket-Type Filter - D-2508 BTMS To E-2508 - 10-SP-25008 | B | 2019-06-13 | IFR | OL1-2P03-2508 | MP | 2019-06-17 | 036909C-JVD-TRN-01913 | 036909C-JVD-TRN-01913 | IFR | 2019-07-02 |  | Transmitted | TPSK-LSPA1-T-MP-01913 |  | 2019-06-17 | 2
036909C-1025-PDS-1390-2502 | Piping Specialty Item - Datasheet - Basket-Type Filter - D-2506 BTMS To E-2506 - 10-SP-25002 | B | 2019-06-13 | IFR | OL1-2P03-2502 | MP | 2019-06-17 | 036909C-JVD-TRN-01913 | 036909C-JVD-TRN-01913 | IFR | 2019-07-02 |  | Transmitted | TPSK-LSPA1-T-MP-01913 |  | 2019-06-17 | 2
036909C-1025-PDS-1390-2503 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2507 - 10-SP-25003 | B | 2019-06-13 | IFR | OL1-2P03-2503 | MP | 2019-06-17 | 036909C-JVD-TRN-01913 | 036909C-JVD-TRN-01913 | IFR | 2019-07-02 |  | Transmitted | TPSK-LSPA1-T-MP-01913 |  | 2019-06-17 | 2
036909C-1025-PDS-1390-2509 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2509 - 10-SP-25009 | B | 2019-06-13 | IFR | OL1-2P03-2509 | MP | 2019-06-17 | 036909C-JVD-TRN-01913 | 036909C-JVD-TRN-01913 | IFR | 2019-07-02 |  | Transmitted | TPSK-LSPA1-T-MP-01913 |  | 2019-06-17 | 2
036909C-1000-RT-1980-0001 | Fire Proofing Schedule | 0 | 2019-06-14 | IFE | OL1-2F45-1001 | FF | 2019-06-17 | 036909C-JVD-TRN-01900 | 036909C-JVD-TRN-01900 | IFR | 2019-07-02 |  | Transmitted | TPSK-LSPA1-T-FF-01900 |  | 2019-06-17 | 2
036909C-1000-NM-1601-0003 | Electrical Equipment List | A | 2019-03-29 | IFR | OL1-2E15-0002 | EE | 2019-04-01 | 036909C-JVD-TRN-01213 | 036909C-JVD-TRN-01213, ROC-TPSK-CECO-T-00033 | IFA | 2019-04-16 | 2019-05-07 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01213 |  | 2019-04-02 | 1
036909C-1000-DL-4100-0001 | Deviation List for Wet Air Oxidation Package | B | 2019-04-04 | IFR | OL1-2C40-704000 | PL | 2019-04-08 | 036909C-JVD-TRN-01269 | 036909C-JVD-TRN-01269 | IFR | 2019-04-22 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PL-01269 | Previously client number was OL1-2M58-0103 Rev A | 2019-04-08 | 2
036909C-1023-SP-4100-0002 | Mechanical Equipment Datasheet for Wet Air Oxidation Package | 0 | 2019-05-07 | IFP | OL1-2M03-2350 | PL | 2019-05-08 | 036909C-JVD-TRN-01611 | 036909C-JVD-TRN-01611 | IFR | 2019-05-22 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-PL-01611 |  | 2019-05-09 | 2
036909C-1000-DL-4100-0001 | Deviation List for Wet Air Oxidation Package | C | 2019-05-07 | IFR | OL1-2C40-704000 | PL | 2019-05-08 | 036909C-JVD-TRN-01611 | 036909C-JVD-TRN-01611 | IFR | 2019-05-22 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-PL-01611 |  | 2019-05-09 | 2
036909C-1000-DW-1451-0001 | Key Plan For Installation Drawings | A | 2019-04-04 | IFR | OL1-2K25-0001 | CV | 2019-04-08 | 036909C-JVD-TRN-01271 | 036909C-JVD-TRN-01271 | IFA | 2019-04-23 | 2019-05-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01271 |  | 2019-04-09 | 1
036909C-1012-TBT-0131-2014 | Technical Bid Tabulation for Radiant Steel Panel | 0 | 2019-05-07 | IFI | OL1-2C23-2014 | PL | 2019-05-13 | 036909C-JVD-TRN-01649 | 036909C-JVD-TRN-01649 | IFI |  | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-PL-01649 |  | 2019-05-15 | 3
036909C-1012-TBT-0131-2015 | Technical Bid Tabulation for Convection Fabrication | 0 | 2019-05-20 | IFI | OL1-2C23-282000 | PL | 2019-05-22 | 036909C-JVD-TRN-01719 | 036909C-JVD-TRN-01719 | IFI |  | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-PL-01719 |  | 2019-05-23 | 3
036909C-1012-DL-0853-2011 | Deviation List for Attemperators | 0 | 2019-05-21 | IFP | OL1-2C40-286000 | PL | 2019-05-23 | 036909C-JVD-TRN-01733 | 036909C-JVD-TRN-01733 | IFI |  | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-PL-01733 |  | 2019-05-24 | 3
036909C-1012-MR-0853-2011 | Material Requisition for Attemperators | 0 | 2019-05-23 | IFP | OL1-2C13-286000 | PL | 2019-05-28 | 036909C-JVD-TRN-01756 | 036909C-JVD-TRN-01756 | IFI |  | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PL-01756 |  | 2019-05-29 | 3
036909C-1027-PDS-0900-2751 | Process Equipment Datasheet - 10-P-2750 A-B - C4 - C5 Hydrog Feed Pump | C | 2019-05-06 | IFD | OL1-2G30-2751 | PE | 2019-05-07 | 036909C-JVD-TRN-01610 | 036909C-JVD-TRN-01610 | IFR | 2019-05-22 | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-PE-01610 |  | 2019-05-08 | 2
036909C-1012-DL-0131-2016 | Deviation List for Convection Fabrication | B | 2019-05-21 | IFR | OL1-2C40-282000 | PL | 2019-05-22 | 036909C-JVD-TRN-01718 | 036909C-JVD-TRN-01718 | IFR | 2019-06-06 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-PL-01718 |  | 2019-05-23 | 3
036909C-1051-PDS-0600-5108 | Process Equipment Datasheet - 10-E-5110 - Suspect Condensate Cooler | B | 2019-01-14 | IFD | OL1-2G30-5108 | PE | 2019-01-14 | 036909C-JVD-TRN-00652 | 036909C-JVD-TRN-00652 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00652 |  | 2019-01-14 | 2
036909C-1056-SP-0910-5622 | Mechanical Equipment Datasheet - Olefins Holding Basin Pumps | B | 2019-04-16 | IFQ | OL1-2M03-5622 | ME | 2019-04-17 | 036909C-JVD-TRN-01390 | 036909C-JVD-TRN-01390 | IFR | 2019-05-02 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01390 |  | 2019-04-18 | 2
036909C-1029-SP-4046-0017 | MECHANICAL EQUIPMENT DATASHEET FOR ANTI-OXIDANT INJECTION PACKAGE TAG: 10-PK-2945 | A | 2019-05-13 | IFQ | OL1-2M03-2945 | ME | 2019-05-16 | 036909C-JVD-TRN-01673 | 036909C-JVD-TRN-01673 | IFR | 2019-05-30 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01673 |  | 2019-05-17 | 2
036909C-1059-SP-4046-0004 | MECHANICAL EQUIPMENT DATASHEET FOR NEUTRALIZATION AMINE INHIBITOR INJECTION PACKAGE TAG: 10-PK-5912 | A | 2019-04-24 | IFQ | OL1-2M03-5912 | ME | 2019-04-26 | 036909C-JVD-TRN-01490 | 036909C-JVD-TRN-01490 | IFR | 2019-05-10 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01490 |  | 2019-04-29 | 2
036909C-1059-SP-4046-0003 | MECHANICAL EQUIPMENT DATASHEET FOR OXYGEN SCAVENGER INJECTION PACKAGE TAG: 10-PK-5910 | A | 2019-04-24 | IFQ | OL1-2M03-5910 | ME | 2019-04-26 | 036909C-JVD-TRN-01490 | 036909C-JVD-TRN-01490 | IFR | 2019-05-10 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01490 |  | 2019-04-29 | 2
036909C-1059-SP-4046-0002 | MECHANICAL EQUIPMENT DATASHEET FOR PHOSPHATE INJECTION PACKAGE TAG: 10-PK-5914 | A | 2019-04-24 | IFQ | OL1-2M03-5914 | ME | 2019-04-26 | 036909C-JVD-TRN-01490 | 036909C-JVD-TRN-01490 | IFR | 2019-05-10 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01490 |  | 2019-04-29 | 2
036909C-1053-SP-4046-0015 | MECHANICAL EQUIPMENT DATASHEET FOR NON-OXIDIZING BIOCIDE INJECTION PACKAGE TAG: 10-PK-5397 | A | 2019-04-24 | IFQ | OL1-2M03-5397 | ME | 2019-04-26 | 036909C-JVD-TRN-01490 | 036909C-JVD-TRN-01490 | IFR | 2019-05-10 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01490 |  | 2019-04-29 | 2
036909C-1053-SP-4046-0014 | MECHANICAL EQUIPMENT DATASHEET FOR DISPERSANT INJECTION PACKAGE TAG: 10-PK-5394 | A | 2019-04-24 | IFQ | OL1-2M03-5394 | ME | 2019-04-26 | 036909C-JVD-TRN-01490 | 036909C-JVD-TRN-01490 | IFR | 2019-05-10 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01490 |  | 2019-04-29 | 2
036909C-1053-SP-4046-0013 | MECHANICAL EQUIPMENT DATASHEET FOR MILD STEEL CORROSION INHIBITOR INJECTION PACKAGE TAG: 10-PK-5392 | A | 2019-04-24 | IFQ | OL1-2M03-5392 | ME | 2019-04-26 | 036909C-JVD-TRN-01490 | 036909C-JVD-TRN-01490 | IFR | 2019-05-10 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01490 |  | 2019-04-29 | 2
036909C-1053-SP-4046-0012 | MECHANICAL EQUIPMENT DATASHEET FOR COPPER CORROSION INHIBITOR INJECTION PACKAGE TAG: 10-PK-5390 | A | 2019-04-24 | IFQ | OL1-2M03-5390 | ME | 2019-04-26 | 036909C-JVD-TRN-01490 | 036909C-JVD-TRN-01490 | IFR | 2019-05-10 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01490 |  | 2019-04-29 | 2
036909C-1029-SP-4046-0016 | MECHANICAL EQUIPMENT DATASHEET FOR PROPANOL INJECTION PACKAGE TAG: 10-PK-2931 | A | 2019-04-24 | IFQ | OL1-2M03-2931 | ME | 2019-04-26 | 036909C-JVD-TRN-01490 | 036909C-JVD-TRN-01490 | IFR | 2019-05-10 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01490 |  | 2019-04-29 | 2
036909C-1029-SP-4046-0011 | MECHANICAL EQUIPMENT DATASHEET FOR C4 POLYMER INHIBITOR INJECTION PACKAGE TAG: 10-PK-2940 | A | 2019-04-24 | IFQ | OL1-2M03-2940 | ME | 2019-04-26 | 036909C-JVD-TRN-01490 | 036909C-JVD-TRN-01490 | IFR | 2019-05-10 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01490 |  | 2019-04-29 | 2
036909C-1029-SP-4046-0010 | MECHANICAL EQUIPMENT DATASHEET FOR POLYMERIZATION INHIBITOR INJECTION PACKAGE TAG: 10-PK-2920 | A | 2019-04-24 | IFQ | OL1-2M03-2920 | ME | 2019-04-26 | 036909C-JVD-TRN-01490 | 036909C-JVD-TRN-01490 | IFR | 2019-05-10 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01490 |  | 2019-04-29 | 2
036909C-1029-SP-4046-0009 | MECHANICAL EQUIPMENT DATASHEET FOR CAUSTIC TOWER ANTI-FOULANT INJECTION PACKAGE TAG: 10-PK-2912 | A | 2019-04-24 | IFQ | OL1-2M03-2912 | ME | 2019-04-26 | 036909C-JVD-TRN-01490 | 036909C-JVD-TRN-01490 | IFR | 2019-05-10 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01490 |  | 2019-04-29 | 2
036909C-1029-SP-4046-0008 | MECHANICAL EQUIPMENT DATASHEET FOR DSG ANTI-FOULANT INJECTION PACKAGE TAG: 10-PK-2906 | A | 2019-04-24 | IFQ | OL1-2M03-2906 | ME | 2019-04-26 | 036909C-JVD-TRN-01490 | 036909C-JVD-TRN-01490 | IFR | 2019-05-10 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01490 |  | 2019-04-29 | 2
036909C-1029-SP-4046-0007 | MECHANICAL EQUIPMENT DATASHEET FOR PROCESS WATER STRIPPER CHEMICAL INJECTION PACKAGE TAG: 10-PK-2904 | A | 2019-04-24 | IFQ | OL1-2M03-2904 | ME | 2019-04-26 | 036909C-JVD-TRN-01490 | 036909C-JVD-TRN-01490 | IFR | 2019-05-10 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01490 |  | 2019-04-29 | 2
036909C-1029-SP-4046-0006 | MECHANICAL EQUIPMENT DATASHEET FOR EMULSION BREAKER INJECTION PACKAGE TAG: 10-PK-2902 | A | 2019-04-24 | IFQ | OL1-2M03-2902 | ME | 2019-04-26 | 036909C-JVD-TRN-01490 | 036909C-JVD-TRN-01490 | IFR | 2019-05-10 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01490 |  | 2019-04-29 | 2
036909C-1029-SP-4046-0005 | MECHANICAL EQUIPMENT DATASHEET FOR pH CTRL / CORROSION INHIBITOR INJECTION PACKAGE TAG: 10-PK-2900 | A | 2019-04-24 | IFQ | OL1-2M03-2900 | ME | 2019-04-26 | 036909C-JVD-TRN-01490 | 036909C-JVD-TRN-01490 | IFR | 2019-05-10 | 2019-06-18 | R1-No comments | TPSK-LSPA1-T-ME-01490 |  | 2019-04-29 | 2
036909C-1053-SP-0310-0002 | Mechanical Equipment Datasheet for Cooling Tower | 0 | 2019-04-18 | IFP | OL1-2M03-5350 | ME | 2019-04-25 | 036909C-JVD-TRN-01476 | 036909C-JVD-TRN-01476 | IFR | 2019-05-09 | 2019-06-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-01476 |  | 2019-04-25 | 2
036909C-1029-SP-1546-2906 | Instrument Datasheets for Flow Element - Flow Nozzle - Area 29 | A | 2019-05-23 | IFQ | OL1-2I20-2924 | IE | 2019-05-24 | 036909C-JVD-TRN-01738 | 036909C-JVD-TRN-01738 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01738 |  | 2019-05-27 | 3
036909C-1029-SP-1546-2902 | Instrument Datasheets for Flow Element -Orifice- Area 29 | A | 2019-05-21 | IFQ | OL1-2I20-2922 | IE | 2019-05-22 | 036909C-JVD-TRN-01717 | 036909C-JVD-TRN-01717 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01717 |  | 2019-05-23 | 3
036909C-1025-SP-1547-2502 | Instrument Datasheets for Flow Element - Rotameter- Area 25 | B | 2019-05-22 | IFQ | OL1-2I20-2528 | IE | 2019-05-23 | 036909C-JVD-TRN-01728 | 036909C-JVD-TRN-01728 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01728 |  | 2019-05-24 | 3
036909C-1021-SP-1546-2102 | Instrument Datasheets for Flow Element -Orifice -Area 21 | A | 2019-05-14 | IFQ | OL1-2I20-2122 | IE | 2019-05-14 | 036909C-JVD-TRN-01660 | 036909C-JVD-TRN-01660 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01660 |  | 2019-05-15 | 3
036909C-1020-SP-1547-2002 | Instrument Datasheets for Flow Element - Rotameter - Area 20 | A | 2019-05-14 | IFQ | OL1-2I20-2028 | IE | 2019-05-14 | 036909C-JVD-TRN-01660 | 036909C-JVD-TRN-01660 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01660 |  | 2019-05-15 | 3
036909C-1010-SP-1546-1002 | Instrument Datasheets for Flow Element -Orifice - Area 10 | A | 2019-05-14 | IFQ | OL1-2I20-1022 | IE | 2019-05-14 | 036909C-JVD-TRN-01660 | 036909C-JVD-TRN-01660 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01660 |  | 2019-05-15 | 3
036909C-1028-PDS-1560-0001 | Process Data Sheet For Analyzers Refrigeration Sytem - Area 28 | A | 2019-05-16 | IFR | OL1-2G31-2801 | PE | 2019-05-20 | 036909C-JVD-TRN-01693 | 036909C-JVD-TRN-01693 | IFR | 2019-06-04 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01693 |  | 2019-05-21 | 2
036909C-1027-PDS-1560-0001 | Process Data Sheet For Analyzers Ghu And C4 - C5 Hydrog - Area 27 | A | 2019-05-16 | IFR | OL1-2G31-2701 | PE | 2019-05-20 | 036909C-JVD-TRN-01693 | 036909C-JVD-TRN-01693 | IFR | 2019-06-04 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01693 |  | 2019-05-21 | 2
036909C-1029-PDS-1560-0001 | Process Data Sheet For Analyzers Ethylene Auxiliariers - Area 29 | A | 2019-05-16 | IFR | OL1-2G31-2901 | PE | 2019-05-20 | 036909C-JVD-TRN-01693 | 036909C-JVD-TRN-01693 | IFR | 2019-06-04 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01693 |  | 2019-05-21 | 2
036909C-1026-PDS-1560-0001 | Process Data Sheet For Analyzers Hot Fractionantion - Area 26 | A | 2019-05-16 | IFR | OL1-2G31-2601 | PE | 2019-05-20 | 036909C-JVD-TRN-01693 | 036909C-JVD-TRN-01693 | IFR | 2019-06-04 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01693 |  | 2019-05-21 | 2
036909C-1059-SP-0910-5903 | Mechanical Equipment Datasheet - Sulfuric Acid Distribution Pumps | A | 2019-04-15 | IFQ | OL1-2M03-5903 | ME | 2019-04-15 | 036909C-JVD-TRN-01363 | 036909C-JVD-TRN-01363 | IFR | 2019-04-30 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-ME-01363 | This datasheet supersedes OL1-2M03-5901 (036909C-1059-SP-0940-5901) | 2019-04-16 | 2
036909C-1056-SP-0910-5625 | Mechanical Equipment Datasheet - Gate 3 Septic Tank Pumps | B | 2019-04-12 | IFQ | OL1-2M03-5625 | ME | 2019-04-15 | 036909C-JVD-TRN-01363 | 036909C-JVD-TRN-01363 | IFR | 2019-04-30 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-ME-01363 |  | 2019-04-16 | 2
036909C-100S-DW-1523-0003 | FAR-E Instrument Equipment Layout | A | 2019-03-22 | IFR | OL1-2I46-1003 | IE | 2019-03-26 | 036909C-JVD-TRN-01153 | 036909C-JVD-TRN-01153, ROC-TPSK-CECO-T-00026 | IFA | 2019-04-10 | 2019-04-05 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-IE-01153 |  | 2019-03-27 | 1
036909C-1000-JSD-1510-0002 | JSD For Automation System Availability | A | 2019-04-10 | IFR | OL1-2R06-0026 | IE | 2019-04-15 | 036909C-JVD-TRN-01355 | 036909C-JVD-TRN-01355 | IFR | 2019-04-30 | 2019-05-07 | R2-Comments as noted | TPSK-LSPA1-T-IE-01355 |  | 2019-04-16 | 2
036909C-103S-DW-1523-0002 | FAR-C Instrument Equipment Layout | A | 2019-03-22 | IFR | OL1-2I46-1002 | IE | 2019-03-26 | 036909C-JVD-TRN-01153 | 036909C-JVD-TRN-01153, ROC-TPSK-CECO-T-00026 | IFA | 2019-04-10 | 2019-04-05 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-IE-01153 |  | 2019-03-27 | 1
036909C-105F-DW-1523-0004 | FAR-FL Instrument Equipment Layout | A | 2019-03-22 | IFR | OL1-2I46-1004 | IE | 2019-03-26 | 036909C-JVD-TRN-01153 | 036909C-JVD-TRN-01153, ROC-TPSK-CECO-T-00026 | IFA | 2019-04-10 | 2019-04-05 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-IE-01153 |  | 2019-03-27 | 1
036909C-1055-PDS-0180-5560 | Process Equipment Datasheet - 10-PK-5560 - HP - Polyolefins Flare Pkg | C | 2019-04-25 | IFD | OL1-2G30-5560 | PE | 2019-04-26 | 036909C-JVD-TRN-01506 | 036909C-JVD-TRN-01506 | IFR | 2019-05-13 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-PE-01506 |  | 2019-04-29 | 2
036909C-1012-MR-1554-2063 | Material Requisition for Temperature Elements for Coil Outlet | A | 2019-05-08 | IFQ | OL1-2C17-032063 | PL | 2019-05-23 | 036909C-JVD-TRN-01732 | 036909C-JVD-TRN-01732 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PL-01732 |  | 2019-05-24 | 3
036909C-1026-PDS-0840-2664 | Process Equipment Datasheet - 10-F-2666 A-B - C5 - Pygas Feed Filters | C | 2019-05-03 | IFD | OL1-2G30-2664 | PE | 2019-05-07 | 036909C-JVD-TRN-01601 | 036909C-JVD-TRN-01601 | IFR | 2019-05-22 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-01601 |  | 2019-05-08 | 2
036909C-1000-RT-1980-0001 | Fire Proofing Schedule | A | 2019-05-17 | IFR | OL1-2F45-1001 | FF | 2019-05-21 | 036909C-JVD-TRN-01704 | 036909C-JVD-TRN-01704 | IFR | 2019-06-04 |  | Transmitted | TPSK-LSPA1-T-FF-01704 |  | 2019-05-21 | 2
036909C-105F-DW-1950-5016 | FIRE & GAS DEVICES LAYOUT ZONE 5F - HP & POLYOLEFINS FLARES UNIT | A | 2019-03-20 | IFR | OL1-2F40-5016 | FF | 2019-03-21 | 036909C-JVD-TRN-01120 | 036909C-JVD-TRN-01120, KLOC-TPSK-CECO-T-00002 | IFR | 2019-04-03 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01120 |  | 2019-03-22 | 2
036909C-103S-DW-1950-5005 | FIRE & GAS DEVICES LAYOUT - ZONE 3S - AREA SUBSTATION C & FAR C | A | 2019-03-20 | IFR | OL1-2F40-5005 | FF | 2019-03-21 | 036909C-JVD-TRN-01120 | 036909C-JVD-TRN-01120, KLOC-TPSK-CECO-T-00002 | IFR | 2019-04-03 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01120 |  | 2019-03-22 | 2
036909C-100S-DW-1950-5004 | FIRE & GAS DEVICES LAYOUT -ZONE 0S - ELECTRICAL SUBSTATION E & FAR E | A | 2019-03-20 | IFR | OL1-2F40-5004 | FF | 2019-03-21 | 036909C-JVD-TRN-01120 | 036909C-JVD-TRN-01120, KLOC-TPSK-CECO-T-00002 | IFR | 2019-04-03 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01120 |  | 2019-03-22 | 2
036909C-PO-036909C001P8-001 | Purchase Order for MR-4234-0001 - Side Stream Filter | 0 | 2019-04-16 | IFI | OL1-2C51-0101 | PL | 2019-04-17 | 036909C-JVD-TRN-01385 | 036909C-JVD-TRN-01385 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01385 |  | 2019-06-10 | 3
036909C-105F-DW-1743-0007 | Foundation For 10-D-5550 | A | 2019-05-30 | IFR | OL1-2K31-0267 | CV | 2019-06-11 | 036909C-JVD-TRN-01852 | 036909C-JVD-TRN-01852 | IFR | 2019-06-25 |  | Transmitted | TPSK-LSPA1-T-CV-01852 |  | 2019-06-11 | 2
036909C-1024-PDS-0800-2415 | Process Equipment Datasheet - 10-D-2415 - CG Liquid Dryer Feed Coalescer | B | 2019-01-04 | IFD | OL1-2G30-2415 | PE | 2019-01-07 | 036909C-JVD-TRN-00596 | 036909C-JVD-TRN-00596, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-01-22 | TPSK-LSPA1-E-00226 on June 10 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-00596 |  | 2019-01-07 | 2
036909C-1012-MR-1399-2104 | Material Requisition for SP Item Isokinetic Sampling Nozzle | A | 2019-05-28 | IFQ | OL1-2C14-505000 | PL | 2019-06-07 | 036909C-JVD-TRN-01833 | 036909C-JVD-TRN-01833 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01833 |  | 2019-06-10 | 3
036909C-1012-DL-0131-2016 | Deviation List for Convection Fabrication | C | 2019-05-29 | IFR | OL1-2C40-282000 | PL | 2019-05-30 | 036909C-JVD-TRN-01772 | 036909C-JVD-TRN-01772 | IFR | 2019-06-14 |  | Transmitted | TPSK-LSPA1-T-PL-01772 |  | 2019-05-31 | 2
036909C-102B-DW-1743-0045-001 | Foundation For 10-E-1050 | A | 2019-03-28 | IFR | OL1-2K34-0202 | CV | 2019-04-01 | 036909C-JVD-TRN-01208 | 036909C-JVD-TRN-01208, ROC-TPSK-CECO-T-00034 | IFA | 2019-04-16 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01208 |  | 2019-04-02 | 1
036909C-102B-DW-1743-0044-001 | Foundation For 10-E-1020 | A | 2019-03-28 | IFR | OL1-2K34-0167 | CV | 2019-04-01 | 036909C-JVD-TRN-01208 | 036909C-JVD-TRN-01208, ROC-TPSK-CECO-T-00034 | IFA | 2019-04-16 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01208 |  | 2019-04-02 | 1
036909C-102E-DW-1743-0047-001 | Foundation For 10-E-2441 | A | 2019-04-05 | IFR | OL1-2K31-0338 | CV | 2019-04-12 | 036909C-JVD-TRN-01334 | 036909C-JVD-TRN-01334, ROC-TPSK-CECO-T-00044 | IFA | 2019-04-29 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01334 |  | 2019-04-15 | 1
036909C-102E-DW-1743-0042-001 | Foundation For 10-E-2440 | A | 2019-04-05 | IFR | OL1-2K31-0166 | CV | 2019-04-12 | 036909C-JVD-TRN-01334 | 036909C-JVD-TRN-01334, ROC-TPSK-CECO-T-00044 | IFA | 2019-04-29 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01334 |  | 2019-04-15 | 1
036909C-102E-DW-1743-0016-001 | Foundation For 10-E-2412 | A | 2019-04-05 | IFR | OL1-2K31-0063 | CV | 2019-04-12 | 036909C-JVD-TRN-01334 | 036909C-JVD-TRN-01334, ROC-TPSK-CECO-T-00044 | IFA | 2019-04-29 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01334 |  | 2019-04-15 | 1
036909C-102D-DW-1743-0046-001 | Foundation For 10-E-2882 And 10-E-2884 | A | 2019-03-22 | IFR | OL1-2K31-0198 | CV | 2019-04-01 | 036909C-JVD-TRN-01206 | 036909C-JVD-TRN-01206, ROC-TPSK-CECO-T-00034 | IFA | 2019-04-16 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01206 |  | 2019-04-02 | 1
036909C-102D-DW-1743-0051-001 | Foundation For 10-E-2587 | A | 2019-03-22 | IFR | OL1-2K31-0117 | CV | 2019-04-01 | 036909C-JVD-TRN-01206 | 036909C-JVD-TRN-01206, ROC-TPSK-CECO-T-00034 | IFA | 2019-04-16 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01206 |  | 2019-04-02 | 1
036909C-102E-DW-1743-0021-001 | Foundation For 10-E-2206 | A | 2019-03-28 | IFR | OL1-2K31-0070 | CV | 2019-04-01 | 036909C-JVD-TRN-01206 | 036909C-JVD-TRN-01206, ROC-TPSK-CECO-T-00034 | IFA | 2019-04-16 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01206 |  | 2019-04-02 | 1
036909C-102D-DW-1743-0042-001 | Foundation For 10-E-2585 | A | 2019-03-22 | IFR | OL1-2K31-0005 | CV | 2019-04-01 | 036909C-JVD-TRN-01206 | 036909C-JVD-TRN-01206, ROC-TPSK-CECO-T-00034 | IFA | 2019-04-16 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01206 |  | 2019-04-02 | 2
036909C-102D-CN-1733-0048 | Calculation Note For Foundation Of 10-E-2882 And 10-E-2884 | A | 2019-03-21 | IFR | OL1-2K13-0188 | CV | 2019-04-01 | 036909C-JVD-TRN-01207 | 036909C-JVD-TRN-01207, ROC-TPSK-CECO-T-00034 | IFA | 2019-04-16 | 2019-06-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01207 |  | 2019-04-02 | 1
036909C-1021-PDS-1560-0001 | Process Data Sheet For Analyzer Quench Water - Dilution Steam - Area 21 | A | 2019-05-08 | IFR | OL1-2G31-2101 | PE | 2019-05-10 | 036909C-JVD-TRN-01634 | 036909C-JVD-TRN-01634 | IFR | 2019-05-27 | 2019-06-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-01634 |  | 2019-05-13 | 2
036909C-1020-PDS-1560-0001 | Process Data Sheet For Analyzers Quench Oil - Area 20 | A | 2019-05-08 | IFR | OL1-2G31-2001 | PE | 2019-05-10 | 036909C-JVD-TRN-01634 | 036909C-JVD-TRN-01634 | IFR | 2019-05-27 | 2019-06-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-01634 |  | 2019-05-13 | 2
036909C-1012-PDS-1560-0001 | Process Data Sheet For Analyzers Liquid Cracking Furnace - Area 12 | A | 2019-05-08 | IFR | OL1-2G31-1201 | PE | 2019-05-10 | 036909C-JVD-TRN-01634 | 036909C-JVD-TRN-01634 | IFR | 2019-05-27 | 2019-06-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-01634 |  | 2019-05-13 | 2
036909C-1011-PDS-1560-0001 | Process Data Sheet For Analyzers Recycle Gas Furnace - Area 11 | A | 2019-05-08 | IFR | OL1-2G31-1101 | PE | 2019-05-10 | 036909C-JVD-TRN-01634 | 036909C-JVD-TRN-01634 | IFR | 2019-05-27 | 2019-06-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-01634 |  | 2019-05-13 | 2
036909C-1010-PDS-1560-0001 | Process Data Sheet For Analyzers Feed Preparation - Area 10 | A | 2019-05-08 | IFR | OL1-2G31-1001 | PE | 2019-05-10 | 036909C-JVD-TRN-01634 | 036909C-JVD-TRN-01634 | IFR | 2019-05-27 | 2019-06-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-01634 |  | 2019-05-13 | 2
036909C-1023-PDS-1560-0001 | Process Data Sheet For Analyzers Caustic - Area 23 | A | 2019-05-08 | IFR | OL1-2G31-2301 | PE | 2019-05-10 | 036909C-JVD-TRN-01637 | 036909C-JVD-TRN-01637 | IFR | 2019-05-27 | 2019-06-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-01637 |  | 2019-05-13 | 2
036909C-1000-QCP-1630-0001 | Quality Control PlanElectrical InstallationPower System | A | 2019-05-27 | IFR | OL1-2Q26-0003 | QM | 2019-05-31 | 036909C-JVD-TRN-01789 | 036909C-JVD-TRN-01789 | IFA | 2019-06-17 | 2019-06-10 | A1-Approved without comments | TPSK-LSPA1-T-QM-01789 |  | 2019-06-03 | 1
036909C-1000-QCP-1670-0001 | Quality Control Plan - Electrical Installation-Cathodic Protection System | A | 2019-05-22 | IFR | OL1-2Q26-0006 | QM | 2019-05-27 | 036909C-JVD-TRN-01750 | 036909C-JVD-TRN-01750 | IFA | 2019-06-11 | 2019-06-10 | A1-Approved without comments | TPSK-LSPA1-T-QM-01750 |  | 2019-05-28 | 1
036909C-1000-QCP-1650-0001 | Quality Control Plan - Electrical Installation-Electrical Heat Tracing System | A | 2019-05-22 | IFR | OL1-2Q26-0005 | QM | 2019-05-27 | 036909C-JVD-TRN-01750 | 036909C-JVD-TRN-01750 | IFA | 2019-06-11 | 2019-06-10 | A1-Approved without comments | TPSK-LSPA1-T-QM-01750 |  | 2019-05-28 | 1
036909C-1000-DW-1512-0001 | Control And Safety Systems Connection Diagram | A | 2019-03-08 | IFR | OL1-2I81-1001 | IE | 2019-03-08 | 036909C-JVD-TRN-01012 | 036909C-JVD-TRN-01012 | IFA | 2019-03-25 | 2019-05-15 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-IE-01012 |  | 2019-03-11 | 1
036909C-1012-DW-0132-2108 | USC 132U Cracking Furnace Decoke Nozzle Details | 0 | 2019-05-09 | IMP | OL1-2M06-2108 | ME | 2019-05-13 | 036909C-JVD-TRN-01653 | 036909C-JVD-TRN-01653 | IFR | 2019-05-28 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-ME-01653 |  | 2019-05-14 | 2
036909C-1012-DW-0132-2107 | USC 132U Cracking Furnace SLE Assembly Insulation Details | A | 2019-05-02 | IFR | OL1-2M06-2107 | ME | 2019-05-08 | 036909C-JVD-TRN-01619 | 036909C-JVD-TRN-01619 | IFR | 2019-05-23 | 2019-05-31 | R1-No comments | TPSK-LSPA1-T-ME-01619 |  | 2019-05-09 | 2
036909C-1012-DW-0132-2101 | USC 132U Cracking Furnace Refractory and Insulation Radiant Section Details | A | 2019-02-22 | IFR | OL1-2M06-2101 | ME | 2019-03-14 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15
036909C-1012-DW-0132-2101 | USC 132U Cracking Furnace Refractory and Insulation Radiant Section Details | 0 | 2019-05-09 | IMP | OL1-2M06-2101 | ME | 2019-05-13 | 036909C-JVD-TRN-01653 | 036909C-JVD-TRN-01653 | IFR | 2019-05-28 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-ME-01653 |  | 2019-05-14 | 2
036909C-1011-DW-0132-1108 | USC 36M Recycle Furnace Decoke Nozzle Details | 0 | 2019-05-09 | IMP | OL1-2M06-1108 | ME | 2019-05-13 | 036909C-JVD-TRN-01653 | 036909C-JVD-TRN-01653 | IFR | 2019-05-28 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-ME-01653 |  | 2019-05-14 | 2
036909C-1011-DW-0132-1107 | USC 36M Recycle Furnace USX Assembly Insulation Details | A | 2019-05-02 | IFR | OL1-2M06-1107 | ME | 2019-05-08 | 036909C-JVD-TRN-01619 | 036909C-JVD-TRN-01619 | IFR | 2019-05-23 | 2019-05-31 | R1-No comments | TPSK-LSPA1-T-ME-01619 |  | 2019-05-09 | 2
036909C-1011-DW-0132-1101 | USC 36M Recycle Furnace Refractory and Insulation Radiant Section Details | 0 | 2019-05-09 | IMP | OL1-2M06-1101 | ME | 2019-05-13 | 036909C-JVD-TRN-01653 | 036909C-JVD-TRN-01653 | IFR | 2019-05-28 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-ME-01653 |  | 2019-05-14 | 2
036909C-1011-DW-0132-1101 | USC 36M Recycle Furnace Refractory and Insulation Radiant Section Details | A | 2019-02-22 | IFR | OL1-2M06-1101 | ME | 2019-03-14 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15 | 2
036909C-1012-DW-0132-2106 | USC 132U Cracking Furnace Peep Door Insert Details | 0 | 2019-05-09 | IMP | OL1-2M06-2106 | ME | 2019-05-13 | 036909C-JVD-TRN-01653 | 036909C-JVD-TRN-01653 | IFR | 2019-05-28 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-ME-01653 |  | 2019-05-14 | 2
036909C-1012-DW-0132-2105 | USC 132U Cracking Furnace Insulation Details at Radiant Floor Burners | 0 | 2019-05-09 | IMP | OL1-2M06-2105 | ME | 2019-05-13 | 036909C-JVD-TRN-01653 | 036909C-JVD-TRN-01653 | IFR | 2019-05-28 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-ME-01653 |  | 2019-05-14 | 2
036909C-1012-DW-0132-2103 | USC 132U Cracking Furnace Refractory and Insulation Installation Details | 0 | 2019-05-09 | IMP | OL1-2M06-2103 | ME | 2019-05-13 | 036909C-JVD-TRN-01653 | 036909C-JVD-TRN-01653 | IFR | 2019-05-28 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-ME-01653 |  | 2019-05-14 | 2
036909C-1012-DW-0132-2102 | USC 132U Cracking Furnace Refractory and Insulation Convection Section Details | 0 | 2019-05-09 | IMP | OL1-2M06-2102 | ME | 2019-05-13 | 036909C-JVD-TRN-01653 | 036909C-JVD-TRN-01653 | IFR | 2019-05-28 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-ME-01653 |  | 2019-05-14 | 2
036909C-1011-DW-0132-1106 | USC 36M Recycle Furnace Peep Door Insert Details | 0 | 2019-05-09 | IMP | OL1-2M06-1106 | ME | 2019-05-13 | 036909C-JVD-TRN-01653 | 036909C-JVD-TRN-01653 | IFR | 2019-05-28 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-ME-01653 |  | 2019-05-14 | 2
036909C-1011-DW-0132-1105 | USC 36M Recycle Furnace Insulation Details at Radiant Floor Burners | 0 | 2019-05-09 | IMP | OL1-2M06-1105 | ME | 2019-05-13 | 036909C-JVD-TRN-01653 | 036909C-JVD-TRN-01653 | IFR | 2019-05-28 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-ME-01653 |  | 2019-05-14 | 2
036909C-1011-DW-0132-1103 | USC 36M Recycle Furnace Refractory and Insulation Installation Details | 0 | 2019-05-09 | IMP | OL1-2M06-1103 | ME | 2019-05-13 | 036909C-JVD-TRN-01653 | 036909C-JVD-TRN-01653 | IFR | 2019-05-28 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-ME-01653 |  | 2019-05-14 | 2
036909C-1020-SP-1547-2009 | Instrument Datasheets for Flow Element -Integral Orifice- Area 20 | A | 2019-05-09 | IFQ | OL1-2I20-2032 | IE | 2019-05-13 | 036909C-JVD-TRN-01650 | 036909C-JVD-TRN-01650 | IFI |  | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-IE-01650 |  | 2019-05-14 | 3
036909C-1020-SP-1546-2002 | Instrument Datasheets for Flow Element - Orifice - Area 20 | A | 2019-05-07 | IFQ | OL1-2I20-2022 | IE | 2019-05-13 | 036909C-JVD-TRN-01650 | 036909C-JVD-TRN-01650 | IFI |  | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-IE-01650 |  | 2019-05-14 | 3
036909C-1012-DW-1513-1201 | Complex Control Narratives_132U Furnaces H-1200 - H1600 | B | 2019-05-20 | IFD | OL1-2I71-1201 | IE | 2019-05-20 | 036909C-JVD-TRN-01700 | 036909C-JVD-TRN-01700 | IFR | 2019-06-04 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-IE-01700 |  | 2019-05-20 | 2
036909C-1011-DW-1513-1101 | Complex Control Narratives_36M Furnace H-1100 | B | 2019-05-20 | IFD | OL1-2I71-1101 | IE | 2019-05-20 | 036909C-JVD-TRN-01700 | 036909C-JVD-TRN-01700 | IFR | 2019-06-04 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-IE-01700 |  | 2019-05-21 | 2
036909C-1011-SP-1554-1015 | Instrument Datasheets for pH and Conductivity Analyzer | B | 2019-05-13 | IFQ | OL1-2I20-1015 | IE | 2019-05-23 | 036909C-JVD-TRN-01730 | 036909C-JVD-TRN-01730 | IFR | 2019-06-07 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-IE-01730 |  | 2019-05-24 | 2
036909C-1020-SP-1546-2004 | Instrument Datasheets for Flow Element -Wedge Type-Area 20 | A | 2019-05-09 | IFQ | OL1-2I20-2026 | IE | 2019-05-13 | 036909C-JVD-TRN-01650 | 036909C-JVD-TRN-01650 | IFI |  | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-IE-01650 |  | 2019-05-14 | 3
036909C-1020-SP-1546-2006 | Instrument Datasheets for Flow Element -Flow Nozzle -Area 20 | A | 2019-05-09 | IFQ | OL1-2I20-2024 | IE | 2019-05-13 | 036909C-JVD-TRN-01650 | 036909C-JVD-TRN-01650 | IFI |  | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-IE-01650 |  | 2019-05-14 | 3
036909C-1012-DW-1513-1201 | Complex Control Narratives | A | 2019-04-08 | IFR | OL1-2I71-1201 | IE | 2019-04-09 | 036909C-JVD-TRN-01289 | 036909C-JVD-TRN-01289 | IFR | 2019-04-24 | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-IE-01289 |  | 2019-04-10 | 2
036909C-1023-SP-1547-2309 | Instrument Datasheets for Flow Element - Integral Orifice- Area 23 | A | 2019-05-03 | IFQ | OL1-2I20-2332 | IE | 2019-05-06 | 036909C-JVD-TRN-01581 | 036909C-JVD-TRN-01581 | IFI |  | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-IE-01581 |  | 2019-05-07 | 3
036909C-1023-SP-1546-2302 | Instrument Datasheets for Flow Element -Orifice -Area 23 | A | 2019-05-02 | IFQ | OL1-2I20-2322 | IE | 2019-05-06 | 036909C-JVD-TRN-01581 | 036909C-JVD-TRN-01581 | IFI |  | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-IE-01581 |  | 2019-05-07 | 3
036909C-1000-CN-1901-0003 | DELUGE NOZZLES ARRANGEMENT CALCULATION NOTE | A | 2019-04-17 | IFR | OL1-2F26-0003 | FF | 2019-04-19 | 036909C-JVD-TRN-01418 | 036909C-JVD-TRN-01418, KLOC-TPSK-VSAFE-T-00005 | IFR | 2019-05-03 | 2019-06-07 | R2-Comments as noted | TPSK-LSPA1-T-FF-01418 |  | 2019-04-19 | 2
036909C-1000-CN-1901-0002 | Hydraulic Calculation For Firewater Deluge / Water Spray System | A | 2019-04-19 | IFR | OL1-2F26-0002 | FF | 2019-04-22 | 036909C-JVD-TRN-01424 | 036909C-JVD-TRN-01424, KLOC-TPSK-VSAFE-T-00006 | IFR | 2019-05-06 | 2019-06-07 | R2-Comments as noted | TPSK-LSPA1-T-FF-01424 |  | 2019-04-22 | 2
036909C-1012-DL-0126-2012 | Deviation List for Furnace Convection Finnings | 0 | 2019-03-07 | IFP | OL1-2C40-281000 | PL | 2019-03-14 | 036909C-JVD-TRN-01056 | 036909C-JVD-TRN-01056 | IFI |  | 2019-06-07 | R1-No comments | TPSK-LSPA1-T-PL-01056 |  | 2019-03-15 | 3
036909C-1012-MR-0853-2011 | Material Requisition for Attemperators | A | 2019-01-25 | IFQ | OL1-2C13-286000 | PL | 2019-01-30 | 036909C-JVD-TRN-00771 | 036909C-JVD-TRN-00771 | IFI |  | 2019-06-07 | R2-Comments as noted | TPSK-LSPA1-T-PL-00771 |  | 2019-01-31 | 3
036909C-1012-PDS-1545-1203 | USC 132U Superheater Outlet PSV - 10-PSV-1244 | B | 2019-05-06 | IFD | OL1-2G32-1203 | PE | 2019-05-07 | 036909C-JVD-TRN-01603 | 036909C-JVD-TRN-01603 | IFR | 2019-05-22 | 2019-05-31 | R2-Comments as noted | TPSK-LSPA1-T-PE-01603 |  | 2019-05-08 | 2
036909C-1012-PDS-1545-1202 | USC 132U Steam Drum PSV Datasheet - 10-PSV-1242B | B | 2019-05-06 | IFD | OL1-2G32-1202 | PE | 2019-05-07 | 036909C-JVD-TRN-01603 | 036909C-JVD-TRN-01603 | IFR | 2019-05-22 | 2019-05-31 | R2-Comments as noted | TPSK-LSPA1-T-PE-01603 |  | 2019-05-08 | 2
036909C-1012-PDS-1545-1201 | USC 132U Steam Drum PSV Datasheet - 10-PSV-1242A | B | 2019-05-06 | IFD | OL1-2G32-1201 | PE | 2019-05-07 | 036909C-JVD-TRN-01603 | 036909C-JVD-TRN-01603 | IFR | 2019-05-22 | 2019-05-31 | R2-Comments as noted | TPSK-LSPA1-T-PE-01603 |  | 2019-05-08 | 2
036909C-1011-PDS-1545-1103 | USC 36M Superheater Outlet PSV Datasheet - 10-PSV-1144 | B | 2019-05-06 | IFD | OL1-2G32-1103 | PE | 2019-05-07 | 036909C-JVD-TRN-01602 | 036909C-JVD-TRN-01602 | IFR | 2019-05-22 | 2019-05-31 | R2-Comments as noted | TPSK-LSPA1-T-PE-01602 |  | 2019-05-08 | 2
036909C-1011-PDS-1545-1102 | USC 36M Steam Drum PSV Datasheet - 10-PSV-1142B | B | 2019-05-06 | IFD | OL1-2G32-1102 | PE | 2019-05-07 | 036909C-JVD-TRN-01602 | 036909C-JVD-TRN-01602 | IFR | 2019-05-22 | 2019-05-31 | R2-Comments as noted | TPSK-LSPA1-T-PE-01602 |  | 2019-05-08 | 2
036909C-1011-PDS-1545-1101 | USC 36M Steam Drum PSV Datasheet - 10-PSV-1142A | B | 2019-05-06 | IFD | OL1-2G32-1101 | PE | 2019-05-07 | 036909C-JVD-TRN-01602 | 036909C-JVD-TRN-01602 | IFR | 2019-05-22 | 2019-05-31 | R2-Comments as noted | TPSK-LSPA1-T-PE-01602 |  | 2019-05-08 | 2
036909C-105F-DW-1442-0001 | Major Underground Network And Finishing Layout - Zone 5F - HP And Polyefins Flares Unit | A | 2019-03-28 | IFR | OL1-2K36-0013 | CV | 2019-04-03 | 036909C-JVD-TRN-01240 | 036909C-JVD-TRN-01240, ROC-TPSK-CECO-T-00045 | IFR | 2019-04-18 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01240 |  | 2019-04-04 | 2
036909C-102E-DW-1442-0001 | Major Underground Networks - Zone 2E - Cracked Gas Compressor | A | 2019-03-22 | IFR | OL1-2K36-0007 | CV | 2019-03-25 | 036909C-JVD-TRN-01138 | 036909C-JVD-TRN-01138, ROC-TPSK-CECO-T-00025 | IFR | 2019-04-09 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01138 |  | 2019-03-26 | 2
036909C-102D-DW-1442-0001 | Major Underground Networks - Zone 2D - Process Cold Compressor | A | 2019-03-22 | IFR | OL1-2K36-0006 | CV | 2019-03-25 | 036909C-JVD-TRN-01138 | 036909C-JVD-TRN-01138, ROC-TPSK-CECO-T-00025 | IFR | 2019-04-09 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01138 |  | 2019-03-26 | 2
036909C-102B-DW-1442-0001 | Major Underground Networks - Zone 2B - C3 Hydrogenation | A | 2019-03-22 | IFR | OL1-2K36-0004 | CV | 2019-03-25 | 036909C-JVD-TRN-01138 | 036909C-JVD-TRN-01138, ROC-TPSK-CECO-T-00025 | IFR | 2019-04-09 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01138 |  | 2019-03-26 | 2
036909C-102A-DW-1442-0001 | Major Underground Networks Zone 2A - Quench | A | 2019-03-22 | IFR | OL1-2K36-0003 | CV | 2019-03-25 | 036909C-JVD-TRN-01138 | 036909C-JVD-TRN-01138, ROC-TPSK-CECO-T-00025 | IFR | 2019-04-09 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01138 |  | 2019-03-26 | 2
036909C-101B-DW-1442-0001 | Major Undergroud Networks - Zone 1B - Furnaces Utilities | A | 2019-03-22 | IFR | OL1-2K36-0002 | CV | 2019-03-25 | 036909C-JVD-TRN-01138 | 036909C-JVD-TRN-01138, ROC-TPSK-CECO-T-00025 | IFR | 2019-04-09 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01138 |  | 2019-03-26 | 2
036909C-102D-DW-1743-0040 | Foundation For 10-E-2852 | A | 2019-03-08 | IFR | OL1-2K34-0137 | CV | 2019-03-12 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-27 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13 | 2
036909C-102B-DW-1743-0041 | Foundation For 10-E-1001 | A | 2019-03-05 | IFR | OL1-2K34-0169 | CV | 2019-03-12 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-27 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13 | 2
036909C-102B-DW-1743-0043 | Foundation For 10-E-1015 | A | 2019-03-05 | IFR | OL1-2K34-0168 | CV | 2019-03-12 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-27 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13 | 2
036909C-102B-DW-1743-0022 | Foundation For 10-E-2620 | A | 2019-03-05 | IFR | OL1-2K34-0146 | CV | 2019-03-12 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-27 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13 | 2
036909C-102E-DW-1743-0009 | Foundation For 10-D-2220 | A | 2019-03-07 | IFR | OL1-2K34-0050 | CV | 2019-03-12 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-27 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13 | 2
036909C-102E-DW-1743-0008 | Foundation For 10-D-2445 | A | 2019-03-07 | IFR | OL1-2K34-0048 | CV | 2019-03-12 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-27 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13 | 2
036909C-102E-DW-1743-0007 | Foundation For 10-D-2245 | A | 2019-03-06 | IFR | OL1-2K34-0047 | CV | 2019-03-12 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-27 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13 | 2
036909C-102E-DW-1743-0006 | Foundation For 10-D-2240 | A | 2019-03-06 | IFR | OL1-2K34-0046 | CV | 2019-03-12 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-27 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13 | 2
036909C-102E-DW-1743-0004 | Foundation For 10-D-2435 | A | 2019-03-07 | IFR | OL1-2K34-0044 | CV | 2019-03-12 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-27 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13 | 2
036909C-102E-DW-1743-0003 | Foundation For 10-D-2410 A/B/C | A | 2019-03-07 | IFR | OL1-2K34-0043 | CV | 2019-03-12 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-27 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13 | 2
036909C-101B-DW-1743-0003 | Foundation For 10-E-5210 | A | 2019-03-08 | IFR | OL1-2K34-0009 | CV | 2019-03-12 | 036909C-JVD-TRN-01034 | 036909C-JVD-TRN-01034, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-27 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01034 |  | 2019-03-13 | 2
036909C-102D-DW-1743-0039 | Foundation For 10-E-2853 | A | 2019-02-07 | IFR | OL1-2K34-0136 | CV | 2019-02-15 | 036909C-JVD-TRN-00868 | 036909C-JVD-TRN-00868, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-04 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-00868 |  | 2019-02-15 | 2
036909C-1000-STC-1490-0001 | Standard Construction Drawings For Underground Systems - Ex Document Client Reference OL1-2K23-0001 | 0 | 2019-01-30 | IFC | OL1-2K24-0001 | CV | 2019-02-06 | 036909C-JVD-TRN-00806 | 036909C-JVD-TRN-00806, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-20 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-00806 | Ex Document Client Reference OL1-2K23-0001 | 2019-02-06 | 2
036909C-1012-MR-0131-2015 | Material Requisition for Convection Fabrication | A | 2019-04-08 | IFQ | OL1-2C13-282000 | PL | 2019-04-11 | 036909C-JVD-TRN-01316 | 036909C-JVD-TRN-01316 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-01316 |  | 2019-04-12 | 3
036909C-1012-PDS-1040-1211 | Process Equipment Datasheet - 10-C-1200_1600 - USC 132U Induced Draft Fan | C | 2019-03-13 | IFD | OL1-2G30-1211 | PE | 2019-03-15 | 036909C-JVD-TRN-01079 | 036909C-JVD-TRN-01079, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-30 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01079 |  | 2019-03-18 | 2
036909C-1000-PP-014 | Requirements For Vendor Documentation And Exchange Of Correspondence | 0 | 2019-01-22 | IMP | OL1-2W92-0005 | PC | 2019-01-24 | 036909C-JVD-TRN-00717 | 036909C-JVD-TRN-00717 | IFR | 2019-02-08 |  | Transmitted | TPSK-LSPA1-T-PC-00717 |  | 2019-01-24 | 2
036909C-1027-PDS-0600-2703 | Process Equipment Datasheet - 10-E-2705 - GHU-1 Recycle Cooler | B | 2019-03-28 | IFD | OL1-2G30-2703 | PE | 2019-03-28 | 036909C-JVD-TRN-01187 | 036909C-JVD-TRN-01187 | IFR | 2019-04-12 | 2019-06-07 | R1-No comments | TPSK-LSPA1-T-PE-01187 |  | 2019-03-29 | 2
036909C-102D-DW-1431-0001 | Zone 2D - Piling Plan | A | 2019-03-22 | IFR | OL1-2K31-4120 | CV | 2019-03-27 | 036909C-JVD-TRN-01170 | 036909C-JVD-TRN-01170, ROC-TPSK-CECO-T-00035 | IFR | 2019-04-11 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-CV-01170 |  | 2019-03-28 | 2
036909C-102A-DW-1431-0001 | Zone 2A - Piling Plan | A | 2019-03-22 | IFR | OL1-2K31-4060 | CV | 2019-03-27 | 036909C-JVD-TRN-01170 | 036909C-JVD-TRN-01170, ROC-TPSK-CECO-T-00035 | IFR | 2019-04-11 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-CV-01170 |  | 2019-03-28 | 2
036909C-1025-SP-1011-2550 | Mechanical Equipment Datasheet For Residue Gas Expander-Recompressor | 0 | 2019-03-15 | IFP | OL1-2M03-2550 | ME | 2019-03-20 | 036909C-JVD-TRN-01101 | 036909C-JVD-TRN-01101, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-20 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-ME-01101 |  | 2019-03-21 | 2
036909C-1027-PDS-0600-2725 | Process Equipment Datasheet - 10-E-2725 A-B - Rerun Tower Reboiler | B | 2019-04-17 | IFD | OL1-2G30-2725 | PE | 2019-04-17 | 036909C-JVD-TRN-01405 | 036909C-JVD-TRN-01405 | IFR | 2019-05-02 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01405 |  | 2019-04-18 | 2
036909C-1027-PDS-0600-2727 | Process Equipment Datasheet - 10-E-2726 - Pygas Fuel Oil Cooler | B | 2019-04-17 | IFD | OL1-2G30-2727 | PE | 2019-04-22 | 036909C-JVD-TRN-01431 | 036909C-JVD-TRN-01431 | IFR | 2019-05-07 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01431 |  | 2019-04-23 | 2
036909C-1027-PDS-4100-2717 | Process Equipment Datasheet - 10-PK-2720 - Rerun Tower Liquid Ring Pump | B | 2019-04-17 | IFD | OL1-2G30-2717 | PE | 2019-04-17 | 036909C-JVD-TRN-01403 | 036909C-JVD-TRN-01403 | IFR | 2019-05-02 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01403 |  | 2019-04-18 | 2
036909C-1027-PDS-0900-2728 | Process Equipment Datasheet - 10-P-2724 A-B - Recycle Wash Oil Pumps | B | 2019-04-22 | IFD | OL1-2G30-2728 | PE | 2019-04-23 | 036909C-JVD-TRN-01458 | 036909C-JVD-TRN-01458 | IFR | 2019-05-08 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01458 |  | 2019-04-24 | 2
036909C-102D-DW-1743-0030 | Foundation for 10-E-2645A/B | A | 2019-03-07 | IFR | OL1-2K34-0123 | CV | 2019-03-13 | 036909C-JVD-TRN-01042 | 036909C-JVD-TRN-01042, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-28 | 2019-06-04 | R2-Comments as noted | TPSK-LSPA1-T-CV-01042 |  | 2019-03-14 | 2
036909C-1025-PDS-1560-0001 | Data Sheet For Analyzers Cold Fractionation - Area 25 | A | 2019-05-10 | IFR | OL1-2G31-2501 | PE | 2019-05-14 | 036909C-JVD-TRN-01664 | 036909C-JVD-TRN-01664 | IFR | 2019-05-29 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01664 |  | 2019-05-15 | 2
036909C-1024-PDS-1560-0001 | Data Sheet For Analyzers Dehydration - Regen - Deprop - C2 Hydrog - Area 24 | A | 2019-05-10 | IFR | OL1-2G31-2401 | PE | 2019-05-14 | 036909C-JVD-TRN-01664 | 036909C-JVD-TRN-01664 | IFR | 2019-05-29 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-PE-01664 |  | 2019-05-15 | 2
036909C-1023-PDS-0800-2316 | Process Equipment Datasheet - 10-D-2316 - Spent Caustic Degassing Drum | B | 2019-01-10 | IFD | OL1-2G30-2316 | PE | 2019-01-11 | 036909C-JVD-TRN-00634 | 036909C-JVD-TRN-00634 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00634 |  | 2019-01-11 | 2
036909C-105S-NM-1623-0003 | Electrical Cable Schedule Sub F | A | 2019-04-18 | IFR | OL1-2E61-0003 | EE | 2019-04-23 | 036909C-JVD-TRN-01440 | 036909C-JVD-TRN-01440, ROC-TPSK-CECO-T-00051 | IFA | 2019-05-08 | 2019-05-29 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01440 |  | 2019-04-24 | 1
036909C-103S-NM-1623-0002 | Electrical Cable Schedule Sub C | A | 2019-04-18 | IFR | OL1-2E61-0002 | EE | 2019-04-23 | 036909C-JVD-TRN-01440 | 036909C-JVD-TRN-01440, ROC-TPSK-CECO-T-00051 | IFA | 2019-05-08 | 2019-05-29 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01440 |  | 2019-04-24 | 1
036909C-100S-NM-1623-0001 | Electrical Cable Schedule Sub E | A | 2019-04-18 | IFLA | OL1-2E61-0001 | EE | 2019-04-23 | 036909C-JVD-TRN-01440 | 036909C-JVD-TRN-01440, ROC-TPSK-CECO-T-00048 | IFA | 2019-05-08 | 2019-05-29 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01440 |  | 2019-04-24 | 1
036909C-1000-DW-1600-0001 | Electrical Drawings Legend And Symbols | A | 2019-03-18 | IFR | OL1-2E02-0001 | EE | 2019-03-28 | ROC-TPSK-CECO-T-00027 | ROC-TPSK-CECO-T-00027, 036909C-JVD-TRN-01411 | IFR | 2019-04-08 | 2019-05-15 | R2-Comments as noted | TPSK-LSPA1-T-EE-01411 |  | 2019-04-19 | 2
036909C-102B-DW-1743-0029 | Foundation For 10-D-2600 A-B | A | 2019-02-07 | IFR | OL1-2K34-0156 | CV | 2019-02-11 | 036909C-JVD-TRN-00833 | 036909C-JVD-TRN-00833, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-26 | 2019-05-31 | R2-Comments as noted | TPSK-LSPA1-T-CV-00833 |  | 2019-02-11 | 2
036909C-102B-DW-1743-0028 | Foundation For 10-D-2610 | A | 2019-02-07 | IFR | OL1-2K34-0155 | CV | 2019-02-11 | 036909C-JVD-TRN-00833 | 036909C-JVD-TRN-00833, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-26 | 2019-05-31 | R2-Comments as noted | TPSK-LSPA1-T-CV-00833 |  | 2019-02-11 | 2
036909C-102B-DW-1743-0003 | Foundation For 10-D-2455 | A | 2019-02-07 | IFR | OL1-2K34-0049 | CV | 2019-02-11 | 036909C-JVD-TRN-00833 | 036909C-JVD-TRN-00833, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-26 | 2019-05-31 | R2-Comments as noted | TPSK-LSPA1-T-CV-00833 |  | 2019-02-11 | 2
036909C-1012-PDS-1390-1207 | Piping Specialty Item Datasheet - Special Tee Fitting 30 inches - 10-SP-12007-16007 | A | 2019-05-08 | IFR | OL1-2P03-1207 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1012-PDS-1390-1208 | Piping Specialty Item Datasheet - Special Tee Fitting 20 inches - 10-SP-12008-16008 | A | 2019-05-08 | IFR | OL1-2P03-1208 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1012-PDS-1390-1209 | Piping Specialty Item Datasheet - Special Tee Fitting 16 inches - 10-SP-12009-16009 | A | 2019-05-08 | IFR | OL1-2P03-1209 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1012-PDS-1390-1206 | Piping Specialty Item Datasheet - Special Tee Fitting 36 inches - 10-SP-12006-16006 | A | 2019-05-08 | IFR | OL1-2P03-1206 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1000-JSD-1422-0001 | Geotechnical Interpretative Report | A | 2019-04-29 | IFR | OL1-2R02-0002 | CV | 2019-05-02 | 036909C-JVD-TRN-01598 | 036909C-JVD-TRN-01598, ROC-TPSK-CECO-T-00058 | IFR | 2019-05-17 | 2019-05-31 | R2-Comments as noted | TPSK-LSPA1-T-CV-01598 |  | 2019-05-08 | 2
036909C-1000-MS-1370-0001 | Job Construction Specification for Bolted Flanged Joints Assembly | A | 2019-05-09 | IFR | OL1-2P92-0004 | MP | 2019-05-10 | 036909C-JVD-TRN-01635 | 036909C-JVD-TRN-01635 | IFR | 2019-05-27 | 2019-05-31 | R2-Comments as noted | TPSK-LSPA1-T-MP-01635 |  | 2019-05-13 | 2
036909C-1011-PDS-1390-1110 | Piping Specialty Item Datasheet - Special Tee Fitting 12 inches - 10-SP-11010 | A | 2019-05-08 | IFR | OL1-2P03-1110 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1011-PDS-1390-1109 | Piping Specialty Item Datasheet - Special Tee Fitting 16 inches - 10-SP-11009 | A | 2019-05-08 | IFR | OL1-2P03-1109 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1011-PDS-1390-1108 | Piping Specialty Item Datasheet - Special Tee Fitting 20 inches - 10-SP-11008 | A | 2019-05-08 | IFR | OL1-2P03-1108 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1011-PDS-1390-1107 | Piping Specialty Item Datasheet - Special Tee Fitting 30 inches - 10-SP-11007 | A | 2019-05-08 | IFR | OL1-2P03-1107 | MP | 2019-05-10 | 036909C-JVD-TRN-01643 | 036909C-JVD-TRN-01643 | IFR | 2019-05-28 | 2019-06-03 | R2-Comments as noted | TPSK-LSPA1-T-MP-01643 |  | 2019-05-13 | 2
036909C-1027-PDS-0600-2730 | Process Equipment Datasheet - 10-E-2730 - Regen Gas Electric Heater | B | 2019-05-06 | IFD | OL1-2G30-2730 | PE | 2019-05-06 | 036909C-JVD-TRN-01586 | 036909C-JVD-TRN-01586 | IFR | 2019-05-21 | 2019-06-03 | R1-No comments | TPSK-LSPA1-T-PE-01586 |  | 2019-05-07 | 2
036909C-102C-DW-1743-0044-001 | Foundation For 10-D-5112 | A | 2019-04-17 | IFR | OL1-2K31-0309 | CV | 2019-04-23 | 036909C-JVD-TRN-01455 | 036909C-JVD-TRN-01455, ROC-TPSK-CECO-T-00051 | IFA | 2019-05-08 | 2019-05-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01455 |  | 2019-04-24 | 1
036909C-102C-DW-1743-0043-001 | Foundation For 10-D-5114 | A | 2019-04-17 | IFR | OL1-2K31-0308 | CV | 2019-04-23 | 036909C-JVD-TRN-01455 | 036909C-JVD-TRN-01455, ROC-TPSK-CECO-T-00051 | IFA | 2019-05-08 | 2019-05-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01455 |  | 2019-04-24 | 1
036909C-102C-DW-1743-0031-001 | Foundation For 10-E-2701 | A | 2019-04-17 | IFR | OL1-2K31-0189 | CV | 2019-04-23 | 036909C-JVD-TRN-01455 | 036909C-JVD-TRN-01455, ROC-TPSK-CECO-T-00051 | IFA | 2019-05-08 | 2019-05-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01455 |  | 2019-04-24 | 1
036909C-102C-DW-1743-0042-001 | Foundation For 10-D-5400 | A | 2019-04-24 | IFR | OL1-2K31-0307 | CV | 2019-04-30 | 036909C-JVD-TRN-01522 | 036909C-JVD-TRN-01522, ROC-TPSK-CECO-T-00056 | IFA | 2019-05-15 | 2019-05-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01522 |  | 2019-05-02 | 1
036909C-102C-DW-1743-0020-001 | Foundation For 10-E-2705 | A | 2019-04-25 | IFR | OL1-2K31-0178 | CV | 2019-04-30 | 036909C-JVD-TRN-01522 | 036909C-JVD-TRN-01522, ROC-TPSK-CECO-T-00056 | IFA | 2019-05-15 | 2019-05-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01522 |  | 2019-05-02 | 1
036909C-102C-DW-1743-0019-001 | Foundation For 10-D-2705 | A | 2019-04-25 | IFR | OL1-2K31-0177 | CV | 2019-04-30 | 036909C-JVD-TRN-01522 | 036909C-JVD-TRN-01522, ROC-TPSK-CECO-T-00056 | IFA | 2019-05-15 | 2019-05-27 | A4 - Not Approved, re-submit for approval | TPSK-LSPA1-T-CV-01522 |  | 2019-05-02 | 1
036909C-102C-DW-1743-0026-001 | Foundation For 10-E-2765 | A | 2019-04-24 | IFR | OL1-2K31-0004 | CV | 2019-04-30 | 036909C-JVD-TRN-01522 | 036909C-JVD-TRN-01522, ROC-TPSK-CECO-T-00056 | IFA | 2019-05-15 | 2019-05-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01522 |  | 2019-05-02 | 1
036909C-102A-DW-1743-0033-001 | Foundation For 10-D-2735 | A | 2019-04-16 | IFR | OL1-2K31-0180 | CV | 2019-04-18 | 036909C-JVD-TRN-01414 | 036909C-JVD-TRN-01414, ROC-TPSK-CECO-T-00047 | IFA | 2019-05-03 | 2019-05-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01414 |  | 2019-04-19 | 1
036909C-1002E-DW-1632-0001 | Lighting layout 2E | A | 2019-04-17 | IFR | OL1-2E43-0018 | EE | 2019-04-19 | 036909C-JVD-TRN-01423 | 036909C-JVD-TRN-01423, ROC-TPSK-CECO-T-00048 | IFA | 2019-05-06 | 2019-05-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01423 |  | 2019-04-22 | 1
036909C-102D-DW-1632-0001 | Lighting Layout - Zone 2D - Process Cold Compressor | A | 2019-04-18 | IFR | OL1-2E43-0017 | EE | 2019-04-19 | 036909C-JVD-TRN-01423 | 036909C-JVD-TRN-01423, ROC-TPSK-CECO-T-00048 | IFA | 2019-05-06 | 2019-05-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01423 |  | 2019-04-22 | 1
036909C-1000-DW-1632-0001 | Lighting Layout 2C | A | 2019-04-17 | IFR | OL1-2E43-0016 | EE | 2019-04-19 | 036909C-JVD-TRN-01423 | 036909C-JVD-TRN-01423, ROC-TPSK-CECO-T-00048 | IFA | 2019-05-06 | 2019-05-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01423 |  | 2019-04-22 | 1
036909C-102B-DW-1632-0001 | Lighting Layout - Zone 2B C3 Hydrogenation | A | 2019-04-19 | IFR | OL1-2E43-0015 | EE | 2019-04-19 | 036909C-JVD-TRN-01423 | 036909C-JVD-TRN-01423, ROC-TPSK-CECO-T-00048 | IFA | 2019-05-06 | 2019-05-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01423 |  | 2019-04-22 | 1
036909C-102A-DW-1632-0001 | Lighting layout - Zone 2A Quench | A | 2019-04-19 | IFR | OL1-2E43-0014 | EE | 2019-04-19 | 036909C-JVD-TRN-01423 | 036909C-JVD-TRN-01423, ROC-TPSK-CECO-T-00048 | IFA | 2019-05-06 | 2019-05-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01423 |  | 2019-04-22 | 1
036909C-101B-DW-1632-0001 | Lighting Layout 1B | A | 2019-04-19 | IFR | OL1-2E43-0013 | EE | 2019-04-19 | 036909C-JVD-TRN-01423 | 036909C-JVD-TRN-01423, ROC-TPSK-CECO-T-00048 | IFA | 2019-05-06 | 2019-05-27 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01423 |  | 2019-04-22 | 1
036909C-1000-MR-4046-0001 | Material Requisition For Chemical Dosing System | A | 2019-04-24 | IFQ | OL1-2C13-707000 | PL | 2019-04-26 | 036909C-JVD-TRN-01491 | 036909C-JVD-TRN-01491 | IFR | 2019-05-10 | 2019-05-31 | R1-No comments | TPSK-LSPA1-T-PL-01491 |  | 2019-04-29 | 2
036909C-105U-DW-1743-0005 | FOUNDATION FOR 10-D-5520 | A | 2019-04-19 | IFR | OL1-2K31-0272 | CV | 2019-05-13 | 036909C-JVD-TRN-01647 | 036909C-JVD-TRN-01647, KLOC-TPSK-CECO-T-00009 | IFR | 2019-05-24 |  | Transmitted | TPSK-LSPA1-T-CV-01647 |  | 2019-05-14 | 2
036909C-1056-PDS-0200-5628 | Process Equipment Datasheet - 10-PIT-5628 - East Gate House Septic Tank | B | 2019-02-07 | IFD | OL1-2G30-5628 | PE | 2019-02-11 | 036909C-JVD-TRN-00838 | 036909C-JVD-TRN-00838, ROC-TPSK-CECO-T-00020 | IFI |  | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00838 |  | 2019-02-11 | 2
036909C-1000-JSD-1540-0001 | Instrument General Design | 0 | 2018-12-14 | IMP | OL1-2R06-0001 | IE | 2018-12-17 | 036909C-JVD-TRN-00507 | 036909C-JVD-TRN-00507, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-28 | 2018-12-26 | R1-No comments | TPSK-LSPA1-T-IE-00507 |  | 2018-12-17 | 2
036909C-1000-JSS-1684-0001 | Cathodic Protection | 1 | 2019-04-29 | IMP | OL1-2R05-0016 | EE | 2019-05-02 | 036909C-JVD-TRN-01556 | 036909C-JVD-TRN-01556 | IFR | 2019-05-17 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-EE-01556 |  | 2019-05-03 | 2
036909C-1000-CN-1626-0001 | Electrical Power Balance | A | 2019-04-19 | IFR | OL1-2E10-0002 | EE | 2019-04-23 | 036909C-JVD-TRN-01438 | 036909C-JVD-TRN-01438, ROC-TPSK-CECO-T-00048 | IFA | 2019-05-08 | 2019-05-17 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01438 |  | 2019-04-24 | 1
036909C-1000-MR-1820-0001 | Material Requisition For Ladders And Platforms For Equipment Requisition For Inquiry | A | 2019-05-06 | IFI | OL1-2C13-321001 | PL | 2019-05-07 | 036909C-JVD-TRN-01593 | 036909C-JVD-TRN-01593 | IFR | 2019-05-22 | 2019-05-23 | R2-Comments as noted | TPSK-LSPA1-T-PL-01593 |  | 2019-05-08 | 2
036909C-1000-CN-1651-0002 | Load Flow And Voltage Drop Analysis | A | 2019-04-17 | IFR | OL1-2E10-0005 | EE | 2019-04-23 | 036909C-JVD-TRN-01438 | 036909C-JVD-TRN-01438, ROC-TPSK-CECO-T-00048 | IFA | 2019-05-08 | 2019-05-18 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01438 |  | 2019-04-24 | 1
036909C-1000-CN-1651-0001 | Short Circuit Analysis | A | 2019-04-17 | IFR | OL1-2E10-0004 | EE | 2019-04-23 | 036909C-JVD-TRN-01438 | 036909C-JVD-TRN-01438, ROC-TPSK-CECO-T-00048 | IFA | 2019-05-08 | 2019-05-18 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01438 |  | 2019-04-24 | 1
036909C-1012-DW-0131-2525 | USC 132U Cracking Furnace Steel Convection Section Header Box Elevations | A | 2019-04-05 | IFI | OL1-2K32-2525 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1012-DW-0131-2524 | USC 132U Cracking Furnace Steel Convection End Wall Tubesheet Details | A | 2019-04-05 | IFI | OL1-2K32-2524 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1012-DW-0125-2304 | USC 132U Recycle Furnace Steel End Wall Tubesheet Details | A | 2019-04-05 | IFI | OL1-2K32-2304 | CV | 2019-04-11 | 036909C-JVD-TRN-01321 | 036909C-JVD-TRN-01321 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01321 |  | 2019-04-12 | 3
036909C-1012-DW-0117-2555 | USC 132U Cracking Furnace Steel Inspection Door Lance Door and Access Door Details | A | 2019-04-09 | IFI | OL1-2K32-2555 | CV | 2019-04-10 | 036909C-JVD-TRN-01308 | 036909C-JVD-TRN-01308 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01308 |  | 2019-04-11 | 3
036909C-1011-DW-0131-1525 | USC 36M Recycle Furnace Steel Convection Section Header Box Details | A | 2019-04-05 | IFI | OL1-2K32-1525 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1011-DW-0131-1524 | USC 36M Recycle Furnace Steel Convection Section End Wall Tubesheet Details | A | 2019-04-05 | IFI | OL1-2K32-1524 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1011-DW-0117-1555 | USC 36M Recycle Furnace Steel Inspection Door Lance Door and Access Door Details | A | 2019-04-05 | IFI | OL1-2K32-1555 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1024-SP-1547-2402 | Instrument Datasheets for Flow Element - Rotameter- Area 24 | A | 2019-04-22 | IFQ | OL1-2I20-2428 | IE | 2019-04-22 | 036909C-JVD-TRN-01428 | 036909C-JVD-TRN-01428 | IFI |  | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-01428 |  | 2019-04-23 | 3
036909C-1027-PDS-0600-2723 | Process Equipment Datasheet - 10-E-2724 - Wash Oil Condenser | B | 2019-04-12 | IFD | OL1-2G30-2723 | PE | 2019-04-15 | 036909C-JVD-TRN-01353 | 036909C-JVD-TRN-01353 | IFR | 2019-04-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-01353 |  | 2019-04-16 | 2
036909C-1026-PDS-0600-2666 | Process Equipment Datasheet - 10-E-2666 - Debutanizer Bottoms Cooler | D | 2019-04-15 | IFD | OL1-2G30-2666 | PE | 2019-04-17 | 036909C-JVD-TRN-01387 | 036909C-JVD-TRN-01387 | IFR | 2019-05-02 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-01387 |  | 2019-04-18 | 2
036909C-1000-MR-0511-0001 | Material Requisition For Shop Assembled Large Columns Requisition For Purchase | 0 | 2019-04-30 | IFP | OL1-2C13-100000 | PL | 2019-04-30 | 036909C-JVD-TRN-01526 | 036909C-JVD-TRN-01526 | IFR | 2019-05-15 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01526 | Closure to comments for document OL1-2C13-100000_A sent by email TPSK-LSPA1-E-00192_21/05/2019 | 2019-05-02 | 2
036909C-1012-SP-0117-1205 | API Fired Heater Mechanical Datasheet 10-H-1200_1600 | 0 | 2019-04-23 | IMP | OL1-2M03-1205 | ME | 2019-04-25 | 036909C-JVD-TRN-01486 | 036909C-JVD-TRN-01486 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01486 |  | 2019-04-26 | 2
036909C-1011-SP-0117-1105 | API Fired Heater Mechanical Datasheet 10-H-1100 | 0 | 2019-04-23 | IMP | OL1-2M03-1105 | ME | 2019-04-25 | 036909C-JVD-TRN-01486 | 036909C-JVD-TRN-01486 | IFR | 2019-05-10 | 2019-05-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-01486 |  | 2019-04-26 | 2
036909C-101B-DW-1743-0009-001 | Foundation For 10-D-1912 | A | 2019-04-19 | IFR | OL1-2K31-0341 | CV | 2019-04-24 | 036909C-JVD-TRN-01470 | 036909C-JVD-TRN-01470, ROC-TPSK-CECO-T-00053 | IFA | 2019-05-09 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01470 |  | 2019-04-25 | 1
036909C-101B-DW-1743-0008-001 | Foundation For 10-D-1910 | A | 2019-04-19 | IFR | OL1-2K31-0203 | CV | 2019-04-24 | 036909C-JVD-TRN-01470 | 036909C-JVD-TRN-01470, ROC-TPSK-CECO-T-00053 | IFA | 2019-05-09 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01470 |  | 2019-04-25 | 1
036909C-102C-DW-1743-0015-001 | Foundation For 10-E-2660 | A | 2019-04-17 | IFR | OL1-2K31-0149 | CV | 2019-04-24 | 036909C-JVD-TRN-01470 | 036909C-JVD-TRN-01470, ROC-TPSK-CECO-T-00053 | IFA | 2019-05-09 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01470 |  | 2019-04-25 | 1
036909C-102E-DW-1743-0017-001 | Foundation for 10-E-2413 | A | 2019-04-22 | IFR | OL1-2K31-0064 | CV | 2019-04-24 | 036909C-JVD-TRN-01470 | 036909C-JVD-TRN-01470, ROC-TPSK-CECO-T-00053 | IFA | 2019-05-09 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01470 |  | 2019-04-25 | 1
036909C-102E-DW-1743-0048-001 | Foundation for 10-E-2442 | A | 2019-04-15 | IFR | OL1-2K31-0339 | CV | 2019-04-16 | 036909C-JVD-TRN-01373 | 036909C-JVD-TRN-01373, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01373 |  | 2019-04-17 | 1
036909C-102E-DW-1743-0041-001 | Foundation For 10-E-2460 | A | 2019-04-15 | IFR | OL1-2K31-0165 | CV | 2019-04-16 | 036909C-JVD-TRN-01373 | 036909C-JVD-TRN-01373, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01373 |  | 2019-04-17 | 1
036909C-102E-DW-1743-0040-001 | Foundation For 10-E-2465 | A | 2019-04-11 | IFR | OL1-2K31-0164 | CV | 2019-04-16 | 036909C-JVD-TRN-01373 | 036909C-JVD-TRN-01373, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01373 |  | 2019-04-17 | 1
036909C-102E-DW-1743-0039-001 | Foundation for 10-E-2474 | A | 2019-04-11 | IFR | OL1-2K31-0163 | CV | 2019-04-16 | 036909C-JVD-TRN-01373 | 036909C-JVD-TRN-01373, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01373 |  | 2019-04-17 | 1
036909C-102B-DW-1743-0021-001 | Foundation For 10-R-2620 A | A | 2019-04-09 | IFR | OL1-2K31-0144 | CV | 2019-04-16 | 036909C-JVD-TRN-01373 | 036909C-JVD-TRN-01373, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01373 |  | 2019-04-17 | 1
036909C-102E-DW-1743-0026-001 | Foundation For 10-E-2305 | A | 2019-04-11 | IFR | OL1-2K31-0075 | CV | 2019-04-16 | 036909C-JVD-TRN-01373 | 036909C-JVD-TRN-01373, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01373 |  | 2019-04-17 | 1
036909C-102E-DW-1743-0024-001 | Foundation For 10-E-2240A-B | A | 2019-04-11 | IFR | OL1-2K31-0073 | CV | 2019-04-16 | 036909C-JVD-TRN-01373 | 036909C-JVD-TRN-01373, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01373 |  | 2019-04-17 | 1
036909C-102E-DW-1743-0023-001 | Foundation For 10-E-2220A-B | A | 2019-04-15 | IFR | OL1-2K31-0072 | CV | 2019-04-16 | 036909C-JVD-TRN-01373 | 036909C-JVD-TRN-01373, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01373 |  | 2019-04-17 | 1
036909C-102E-DW-1743-0019-001 | Foundation For 10-E-2446 | A | 2019-04-11 | IFR | OL1-2K31-0066 | CV | 2019-04-16 | 036909C-JVD-TRN-01373 | 036909C-JVD-TRN-01373, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01373 |  | 2019-04-17 | 1
036909C-102E-DW-1743-0015-001 | Foundation For 10-E-2230A-B | A | 2019-04-11 | IFR | OL1-2K31-0062 | CV | 2019-04-16 | 036909C-JVD-TRN-01373 | 036909C-JVD-TRN-01373, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 | 2019-05-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01373 |  | 2019-04-17 | 1
036909C-1055-PDS-0900-5566 | Process Equipment Datasheet - 10-P-5565 A-B - Polyolefins Flare Knock-out Pumps | B | 2019-04-15 | IFD | OL1-2G30-5566 | PE | 2019-04-16 | 036909C-JVD-TRN-01366 | 036909C-JVD-TRN-01366 | IFR | 2019-05-01 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-01366 |  | 2019-04-17 | 2
036909C-1055-PDS-0900-5551 | Process Equipment Datasheet - 10-P-5550 A-B - HP Flare Knock-Out Pumps | C | 2019-04-15 | IFD | OL1-2G30-5551 | PE | 2019-04-16 | 036909C-JVD-TRN-01366 | 036909C-JVD-TRN-01366 | IFR | 2019-05-01 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-01366 |  | 2019-04-17 | 2
036909C-1053-PDS-0900-5371 | Process Equipment Datasheet - 10-P-5370 A-B - CW Filter Backwash Pumps | B | 2019-04-15 | IFD | OL1-2G30-5371 | PE | 2019-04-16 | 036909C-JVD-TRN-01366 | 036909C-JVD-TRN-01366 | IFR | 2019-05-01 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PE-01366 |  | 2019-04-17 | 2
036909C-1012-DL-0122-2004 | Deviation List for Radiant Coil | B | 2019-04-22 | IFR | OL1-2C40-300000 | PL | 2019-04-24 | 036909C-JVD-TRN-01473 | 036909C-JVD-TRN-01473 | IFR | 2019-05-09 | 2019-05-28 | R1-No comments | TPSK-LSPA1-T-PL-01473 |  | 2019-04-25 | 2
036909C-1012-DL-0133-2008 | Deviation List for Peep Doors | 0 | 2019-04-16 | IFP | OL1-2C40-284000 | PL | 2019-04-17 | 036909C-JVD-TRN-01400 | 036909C-JVD-TRN-01400 | IFR | 2019-05-02 | 2019-05-28 | R1-No comments | TPSK-LSPA1-T-ME-01400 |  | 2019-04-18 | 2
036909C-1011-MR-1541-2001 | Material Requistion for Control Valves | A | 2019-04-11 | IFQ | OL1-2C17-052001 | PL | 2019-04-25 | 036909C-JVD-TRN-01482 | 036909C-JVD-TRN-01482 | IFI |  | 2019-05-28 | R2-Comments as noted | TPSK-LSPA1-T-PL-01482 |  | 2019-04-26 | 3
036909C-1011-SP-1554-1010 | Instrument Datasheets for Temperature Elements for Furnace Profile | A | 2019-04-30 | IFR | OL1-2C17-032010-ATT2 | PL | 2019-05-01 | 036909C-JVD-TRN-01542 | 036909C-JVD-TRN-01542 | IFR | 2019-05-16 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-IE-01542 |  | 2019-05-02 | 2
036909C-1000-MR-1310-0003 | Material Requisition For Butterfly Valves Low Pressure Category A | A | 2019-04-29 | IFQ | OL1-2C14-120001 | PL | 2019-05-07 | 036909C-JVD-TRN-01592 | 036909C-JVD-TRN-01592 | IFR | 2019-05-22 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01592 |  | 2019-05-08 | 2
036909C-1000-MR-1310-0014 | Material Requisition For Dual Plate Check Valves | A | 2019-04-29 | IFQ | OL1-2C14-150001 | PL | 2019-05-06 | 036909C-JVD-TRN-01578 | 036909C-JVD-TRN-01578 | IFR | 2019-05-21 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01578 |  | 2019-05-07 | 2
036909C-1000-MR-1310-0102 | Material Requisition For Gate Globe Check Cast Valves High Pressure | A | 2019-04-29 | IFQ | OL1-2C14-115001 | PL | 2019-05-06 | 036909C-JVD-TRN-01579 | 036909C-JVD-TRN-01579 | IFR | 2019-05-21 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01579 |  | 2019-05-07 | 2
036909C-1000-MR-1310-0008 | Material Requisition For Ball Valves | A | 2019-04-29 | IFQ | OL1-2C14-140001 | PL | 2019-05-06 | 036909C-JVD-TRN-01577 | 036909C-JVD-TRN-01577 | IFR | 2019-05-21 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01577 |  | 2019-05-07 | 2
036909C-1000-MR-1310-0006 | Material Requisition For Plug Valves | A | 2019-04-29 | IFQ | OL1-2C14-130001 | PL | 2019-05-06 | 036909C-JVD-TRN-01576 | 036909C-JVD-TRN-01576 | IFR | 2019-05-21 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01576 |  | 2019-05-07 | 2
036909C-1012-DL-0154-2003 | Deviation List for Quench Exchangers | B | 2019-04-25 | IFR | OL1-2C40-140000 | ME | 2019-04-26 | 036909C-JVD-TRN-01496 | 036909C-JVD-TRN-01496 | IFR | 2019-05-11 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-ME-01496 |  | 2019-04-29 | 2
036909C-1000-MR-1310-0004 | Material Requisition For Butterfly Valves High Performance (Category B) | A | 2019-04-29 | IFQ | OL1-2C14-125001 | PL | 2019-05-06 | 036909C-JVD-TRN-01575 | 036909C-JVD-TRN-01575 | IFR | 2019-05-21 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01575 |  | 2019-05-07 | 2
036909C-1000-MR-1310-0002 | Material Requisition For Gate Globe And Check Cast Valves Low Pressure | A | 2019-04-29 | IFQ | OL1-2C14-110001 | PL | 2019-05-06 | 036909C-JVD-TRN-01574 | 036909C-JVD-TRN-01574 | IFR | 2019-05-21 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01574 |  | 2019-05-07 | 2
036909C-1000-MR-1310-0001 | Material Requisition For Gate Globe And Check Forged Valves | A | 2019-04-29 | IFQ | OL1-2C14-100001 | PL | 2019-05-03 | 036909C-JVD-TRN-01567 | 036909C-JVD-TRN-01567 | IFR | 2019-05-20 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01567 |  | 2019-05-06 | 2
036909C-1000-MR-1350-0001 | Material Requisition For Flanges Blinds And Drip Rings | A | 2019-04-17 | IFQ | OL1-2C14-270001 | PL | 2019-05-02 | 036909C-JVD-TRN-01558 | 036909C-JVD-TRN-01558 | IFR | 2019-05-17 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01558 |  | 2019-05-03 | 2
036909C-1000-MR-1340-0001 | Material Requisition For Forged Fittings | A | 2019-04-17 | IFQ | OL1-2C14-260001 | PL | 2019-05-02 | 036909C-JVD-TRN-01559 | 036909C-JVD-TRN-01559 | IFR | 2019-05-17 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01559 |  | 2019-05-03 | 2
036909C-1000-MR-1330-0001 | Material Requisition For Buttwelding Fittings | A | 2019-04-17 | IFQ | OL1-2C14-250001 | PL | 2019-05-02 | 036909C-JVD-TRN-01557 | 036909C-JVD-TRN-01557 | IFR | 2019-05-17 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01557 |  | 2019-05-03 | 2
036909C-1000-MR-1324-0002 | Material Requisition For Stainless Steel Welded Pipe | A | 2019-04-17 | IFQ | OL1-2C14-235001 | PL | 2019-05-02 | 036909C-JVD-TRN-01555 | 036909C-JVD-TRN-01555 | IFR | 2019-05-17 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01555 |  | 2019-05-03 | 2
036909C-1000-MR-1322-0002 | Material Requisition For Alloy Steel Welded Pipe | A | 2019-04-17 | IFQ | OL1-2C14-225001 | PL | 2019-04-30 | 036909C-JVD-TRN-01529 | 036909C-JVD-TRN-01529 | IFR | 2019-05-15 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01529 |  | 2019-05-02 | 2
036909C-1000-MR-1322-0001 | Material Requisition For Alloy Steel Seamless Pipe | A | 2019-04-17 | IFQ | OL1-2C14-220001 | PL | 2019-04-30 | 036909C-JVD-TRN-01528 | 036909C-JVD-TRN-01528 | IFR | 2019-05-15 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01528 |  | 2019-05-02 | 2
036909C-1000-MR-1321-0002 | Material Requisition For Carbon Steel Welded Pipe | A | 2019-04-17 | IFQ | OL1-2C14-215001 | PL | 2019-04-30 | 036909C-JVD-TRN-01527 | 036909C-JVD-TRN-01527 | IFR | 2019-05-15 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01527 |  | 2019-05-02 | 2
036909C-1000-MR-0850-0001 | Material Requisition For Ejectors And Static Mixers | A | 2019-04-18 | IFQ | OL1-2C13-801000 | PL | 2019-04-18 | 036909C-JVD-TRN-01408 | 036909C-JVD-TRN-01408 | IFR | 2019-05-02 | 2019-05-24 | R2-Comments as noted | TPSK-LSPA1-T-PL-01408 |  | 2019-04-18 | 2
036909C-1000-MR-0511-0001 | Material Requisition For Shop Assembled Large Columns | A | 2019-01-04 | IFQ | OL1-2C13-100000 | ME | 2019-01-07 | 036909C-JVD-TRN-00586 | 036909C-JVD-TRN-00586 | IFR | 2019-01-15 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00586 |  | 2019-01-07 | 2
036909C-1025-PDS-4100-2560 | Process Equipment Datasheet - 10-PK-2560 - PSA Unit | B | 2018-12-18 | IFD | OL1-2G30-2560 | PE | 2018-12-20 | 036909C-JVD-TRN-00530 | 036909C-JVD-TRN-00530, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00530 |  | 2018-12-20 | 2
036909C-1000-MR-1011-0001 | Material Requisition For Centrifugal Compressors Steam Turbine Driven | 1 | 2019-04-12 | IFP | OL1-2C13-401000 | PL | 2019-04-19 | 036909C-JVD-TRN-01420 | 036909C-JVD-TRN-01420 | IFA | 2019-05-06 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-PL-01420 |  | 2019-04-22 | 1
036909C-1010-PDS-0600-1005 | Process Equipment Datasheet - 10-E-1005 - LPG Feed Heater | B | 2019-01-16 | IFD | OL1-2G30-1005 | PE | 2019-01-18 | 036909C-JVD-TRN-00680 | 036909C-JVD-TRN-00680 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00680 |  | 2019-01-18 | 2
036909C-1000-MR-1321-0001 | Material Requisition For Carbon Steel Seamless Pipe | A | 2019-04-17 | IFQ | OL1-2C14-210001 | PL | 2019-04-30 | 036909C-JVD-TRN-01525 | 036909C-JVD-TRN-01525 | IFR | 2019-05-15 | 2019-05-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01525 |  | 2019-05-02 | 2
036909C-1053-PDS-1560-0001 | Process Data Sheet For Anaqlyzers Cooling Water - Area 53 | A | 2019-05-24 | IFR | OL1-2G31-5301 | PE | 2019-05-24 | 036909C-JVD-TRN-01740 | 036909C-JVD-TRN-01740 | IFR | 2019-06-10 |  | Transmitted | TPSK-LSPA1-T-PE-01740 |  | 2019-05-27 | 2
036909C-1052-PDS-1560-0001 | Process Data Sheet For Analyzers Fuel System - Area 52 | A | 2019-05-24 | IFR | OL1-2G31-5201 | PE | 2019-05-24 | 036909C-JVD-TRN-01740 | 036909C-JVD-TRN-01740 | IFR | 2019-06-10 |  | Transmitted | TPSK-LSPA1-T-PE-01740 |  | 2019-05-27 | 2
036909C-1051-PDS-1560-0001 | Process Data Sheeet For Analyzers BFW-Steam-Steam OCndensate System - Area 51 | A | 2019-05-24 | IFR | OL1-2G31-5101 | PE | 2019-05-24 | 036909C-JVD-TRN-01740 | 036909C-JVD-TRN-01740 | IFR | 2019-06-10 |  | Transmitted | TPSK-LSPA1-T-PE-01740 |  | 2019-05-27 | 2
036909C-1011-DW-1513-1101 | Complex Control Narratives_36M Furnace H-1100 | A | 2019-04-03 | IFR | OL1-2I71-1101 | IE | 2019-05-20 | 036909C-JVD-TRN-01696 | 036909C-JVD-TRN-01696 | IFR | 2019-06-04 |  | Transmitted | TPSK-LSPA1-T-IE-01696 |  | 2019-05-21 | 2
036909C-1027-PDS-0900-2764 | Process Equipment Datasheet - 10-P-2760 A-B - C4 - C5 Hydrog Recycle Pump | B | 2019-02-28 | IFD | OL1-2G30-2764 | PE | 2019-03-01 | 036909C-JVD-TRN-00963 | 036909C-JVD-TRN-00963 | IFR | 2019-03-16 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-PE-00963 |  | 2019-03-04 | 2
036909C-1000-DW-1442-0001 | Major Underground Networks | A | 2019-03-13 | IFR | OL1-2K36-1000 | CV | 2019-03-15 | 036909C-JVD-TRN-01073 | 036909C-JVD-TRN-01073, ROC-TPSK-CECO-T-00013, ROC-TPSK-CECO-T-00013_1 | IFR | 2019-04-01 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01073 |  | 2019-03-18 | 2
036909C-1011-SP-1554-1015 | USC 36M and USC 132U Instrument Datasheets for pH and Conductivity Analyzer | A | 2019-03-20 | IFR | OL1-2I20-1015 | IE | 2019-03-21 | 036909C-JVD-TRN-01131 | 036909C-JVD-TRN-01131 | IFR | 2019-04-05 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01131 |  | 2019-03-22 | 2
036909C-1011-SP-1554-1011 | Instrument Datasheets for Temperature Elements for Coil Outlet | A | 2019-04-09 | IFR | OL1-2I20-1011 | IE | 2019-04-10 | 036909C-JVD-TRN-01309 | 036909C-JVD-TRN-01309, ROC-TPSK-CECO-T-00056 | IFR | 2019-04-25 |  | Transmitted | TPSK-LSPA1-T-IE-01309 |  | 2019-04-11 | 3
036909C-1000-MS-1320-0052 | Job Construction Specification For Pressure Testing | A | 2019-03-22 | IFR | OL1-2P92-0008 | MP | 2019-03-25 | 036909C-JVD-TRN-01136 | 036909C-JVD-TRN-01136 | IFR | 2019-04-09 | 2019-04-11 | R2-Comments as noted | TPSK-LSPA1-T-MP-01136 |  | 2019-03-26 | 2
036909C-1026-SP-0510-2660 | Mechanical Equipment Datasheet - Debutanizer | D | 2019-02-13 | IFQ | OL1-2M03-2660 | ME | 2019-02-15 | 036909C-JVD-TRN-00861 | 036909C-JVD-TRN-00861, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-04 | 2019-03-12 | R1-No comments | TPSK-LSPA1-T-ME-00861 |  | 2019-02-15 | 2
036909C-1056-PDS-0840-5612 | Process Equipment Datasheet - 10-F-5610 - Hydroblast Filter | C | 2019-04-03 | IFD | OL1-2G30-5612 | PE | 2019-04-04 | 036909C-JVD-TRN-01259 | 036909C-JVD-TRN-01259 | IFR | 2019-04-19 | 2019-05-09 | R1-No comments | TPSK-LSPA1-T-PE-01259 |  | 2019-04-05 | 2
036909C-1055-PDS-0600-5511 | Process Equipment Datasheet - 10-E-5510 - Cold Flare Blowdown Vaporizer | C | 2019-04-03 | IFD | OL1-2G30-5511 | PE | 2019-04-04 | 036909C-JVD-TRN-01261 | 036909C-JVD-TRN-01261 | IFR | 2019-04-19 | 2019-05-09 | R1-No comments | TPSK-LSPA1-T-PE-01261 |  | 2019-04-05 | 2
036909C-1000-JSS-1391-0002 | Job Supply Specification For Non Metallic Expansion Joints | A | 2019-03-06 | IFR | OL1-2R04-0042 | MP | 2019-03-07 | 036909C-JVD-TRN-01000 | 036909C-JVD-TRN-01000, ROC-TPSK-CECO-T-00012 | IFR | 2019-03-22 | 2019-04-01 | R1-No Comments_TPSK-LSPA1-E-00157_02/05/2019 | TPSK-LSPA1-T-MP-01000 |  | 2019-03-08 | 2
036909C-1012-DL-0131-2014 | Deviation List for Radiant Steel Panel | 0 | 2019-05-07 | IFP | OL1-2C40-307000 | PL | 2019-05-15 | 036909C-JVD-TRN-01668 | 036909C-JVD-TRN-01668 | IFI |  |  | Transmitted | LSPA1-TPSK-T-PL-01668 |  | 2019-05-16 | 3
036909C-1012-PIM-0125-2007 | Pre-Inspection Meeting Report - Intermediate Tube Supports | 0 | 2019-04-15 | IFI | OL1-2C95-302000 | PL | 2019-04-15 | 036909C-JVD-TRN-01359 | 036909C-JVD-TRN-01359 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01359 |  | 2019-04-16 | 3
036909C-1027-PDS-0600-2755 | Process Equipment Datasheet - 10-E-2755 - C4 - C5 Hydrog Start-up Heater | B | 2019-03-22 | IFD | OL1-2G30-2755 | PE | 2019-03-25 | 036909C-JVD-TRN-01148 | 036909C-JVD-TRN-01148 | IFR | 2019-04-09 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01148 |  | 2019-03-26 | 2
036909C-1027-PDS-0600-2707 | Process Equipment Datasheet - 10-E-2706 - GHU-1 Cooler | B | 2019-03-28 | IFD | OL1-2G30-2707 | PE | 2019-03-28 | 036909C-JVD-TRN-01187 | 036909C-JVD-TRN-01187 | IFR | 2019-04-12 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01187 |  | 2019-03-29 | 2
036909C-1055-PDS-0180-5570 | Process Equipment Datasheet - 10-PK-5570 - Enclosed Ground Flare Package | B | 2019-04-11 | IFD | OL1-2G30-5570 | PE | 2019-04-11 | 036909C-JVD-TRN-01326 | 036909C-JVD-TRN-01326, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-26 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01326 |  | 2019-04-12 | 2
036909C-1059-PDS-0900-5955 | Process Equipment Datasheet - 10-P-5955 A-B - CTU NaOCL Metering Pumps | B | 2019-04-11 | IFD | OL1-2G30-5955 | PE | 2019-04-11 | 036909C-JVD-TRN-01323 | 036909C-JVD-TRN-01323 | IFR | 2019-04-26 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01323 |  | 2019-04-12 | 2
036909C-1059-PDS-0900-5951 | Process Equipment Datasheet - 10-P-5950 A-B - Olefins NaOCL Metering Pumps | C | 2019-04-11 | IFD | OL1-2G30-5951 | PE | 2019-04-11 | 036909C-JVD-TRN-01323 | 036909C-JVD-TRN-01323 | IFR | 2019-04-26 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01323 |  | 2019-04-12 | 2
036909C-1059-PDS-0900-5905 | Process Equipment Datasheet - 10-P-5905 A-B - CTU Sulfuric Acid Metering Pumps | B | 2019-04-11 | IFD | OL1-2G30-5905 | PE | 2019-04-11 | 036909C-JVD-TRN-01323 | 036909C-JVD-TRN-01323 | IFR | 2019-04-26 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01323 |  | 2019-04-12 | 2
036909C-1059-PDS-0900-5902 | Process Equipment Datasheet - 10-P-5901 A-B - Olefins Sulfuric Acid Metering Pumps | D | 2019-04-11 | IFD | OL1-2G30-5902 | PE | 2019-04-11 | 036909C-JVD-TRN-01323 | 036909C-JVD-TRN-01323 | IFR | 2019-04-26 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01323 |  | 2019-04-12 | 2
036909C-1011-DW-0132-1105 | USC 36M Recycle Furnace Insulation Details at Radiant Floor Burners | A | 2019-02-22 | IFR | OL1-2M06-1105 | ME | 2019-03-14 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15 | 2
036909C-1011-DW-0132-1103 | USC 36M Recycle Furnace Refractory and Insulation Installation Details | A | 2019-02-22 | IFR | OL1-2M06-1103 | ME | 2019-03-14 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15 | 2
036909C-1059-PDS-0900-5901 | Process Equipment Datasheet - 10-P-5900 A-B - Sulfuric Acid Distribution Pumps | B | 2019-03-26 | IFD | OL1-2G30-5901 | PE | 2019-03-27 | 036909C-JVD-TRN-01177 | 036909C-JVD-TRN-01177 | IFR | 2019-04-11 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01177 |  | 2019-03-28 | 2
036909C-1055-PDS-0800-5552 | Process Equipment Datasheet - 10-D-5552 - LPG Storage Drum | C | 2019-04-03 | IFD | OL1-2G30-5552 | PE | 2019-04-04 | 036909C-JVD-TRN-01260 | 036909C-JVD-TRN-01260 | IFR | 2019-04-19 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01260 |  | 2019-04-05 | 2
036909C-1055-PDS-0800-5552 | Process Equipment Datasheet - 10-D-5552 - LPG Storage Drum | B | 2019-03-07 | IFD | OL1-2G30-5552 | PE | 2019-03-07 | 036909C-JVD-TRN-01008 | 036909C-JVD-TRN-01008 | IFR | 2019-03-22 | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-01008 |  | 2019-03-08 | 2
036909C-1028-DI-0007-2801 | Area Basis of Design - 28 Refrigeration | B | 2019-04-01 | IFD | OL1-2G05-2801 | PE | 2019-04-02 | 036909C-JVD-TRN-01224 | 036909C-JVD-TRN-01224 | IFA | 2019-04-17 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01224 |  | 2019-04-03 | 1
036909C-1022-DI-0007-2201 | Area Basis of Design - 22-24 Compression Train | B | 2019-04-04 | IFD | OL1-2G05-2201 | PE | 2019-04-08 | 036909C-JVD-TRN-01272 | 036909C-JVD-TRN-01272 | IFA | 2019-04-23 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01272 |  | 2019-04-09 | 1
036909C-1027-PDS-0800-2767 | Process Equipment Datasheet - 10-D-2765 - C4 - C5 Hydrog Coalescer Drum | B | 2019-03-22 | IFD | OL1-2G30-2767 | PE | 2019-03-25 | 036909C-JVD-TRN-01145 | 036909C-JVD-TRN-01145 | IFR | 2019-04-09 | 2019-05-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-01145 |  | 2019-03-26 | 2
036909C-1027-PDS-0600-2702 | Process Equipment Datasheet - 10-E-2702 - GHU-1 Start-up Heater | B | 2019-04-03 | IFD | OL1-2G30-2702 | PE | 2019-04-04 | 036909C-JVD-TRN-01250 | 036909C-JVD-TRN-01250 | IFR | 2019-04-19 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01250 |  | 2019-04-05 | 2
036909C-1010-PDS-0600-1006 | Process Equipment Datasheet - 10-E-1006 - LPG Feed Steam Heater | B | 2019-04-03 | IFD | OL1-2G30-1006 | PE | 2019-04-04 | 036909C-JVD-TRN-01261 | 036909C-JVD-TRN-01261 | IFR | 2019-04-19 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01261 |  | 2019-04-05 | 2
036909C-1023-PDS-4100-2350 | Process Equipment Datasheet - 10-PK-2350 - Wet Air Oxidation Pkg | B | 2019-04-11 | IFD | OL1-2G30-2350 | PE | 2019-04-11 | 036909C-JVD-TRN-01328 | 036909C-JVD-TRN-01328, ROC-TPSK-CECO-T-00057 | IFR | 2019-04-26 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01328 |  | 2019-04-12 | 2
036909C-1020-DI-0007-2001 | Area Basis of Design - 20- 21 Quench and Dilution Steam | B | 2019-04-01 | IFD | OL1-2G05-2001 | PE | 2019-04-02 | 036909C-JVD-TRN-01224 | 036909C-JVD-TRN-01224 | IFA | 2019-04-17 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-PE-01224 |  | 2019-04-03 | 1
036909C-1056-SP-0910-5611 | Mechanical Equipment Datasheet - Hydroblast Sump Pump | B | 2019-03-25 | IFQ | OL1-2M03-5611 | ME | 2019-04-08 | 036909C-JVD-TRN-01279 | 036909C-JVD-TRN-01279 | IFR | 2019-04-23 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-ME-01279 |  | 2019-04-09 | 2
036909C-1029-SP-0940-2911 | Mechanical Equipment Datasheet - Wash Oil Injection Pump | B | 2019-03-26 | IFQ | OL1-2M03-2911 | ME | 2019-04-08 | 036909C-JVD-TRN-01279 | 036909C-JVD-TRN-01279 | IFR | 2019-04-23 | 2019-05-16 | R1-No comments | TPSK-LSPA1-T-ME-01279 |  | 2019-04-09 | 2
036909C-1012-PDS-1542-1212 | Process Equipment Datasheet - 10-ZZ-1200_1600 USC 132U Attemperator | B | 2019-04-01 | IFD | OL1-2G31-1212 | PE | 2019-04-11 | 036909C-JVD-TRN-01330 | 036909C-JVD-TRN-01330 | IFR | 2019-04-26 | 2019-05-15 | R1-No comments | TPSK-LSPA1-T-PE-01330 |  | 2019-04-12 | 2
036909C-1012-PDS-0117-1205 | Process Equipment Datasheet - 10-H-1200_1600 - API Fired Heater Process Datasheet | B | 2019-04-10 | IFD | OL1-2G30-1205 | PE | 2019-04-11 | 036909C-JVD-TRN-01322 | 036909C-JVD-TRN-01322 | IFR | 2019-04-26 | 2019-05-15 | R1-No comments | TPSK-LSPA1-T-PE-01322 |  | 2019-04-12 | 2
036909C-102D-DW-1743-0008-002 | Foundation For 10-T-2510 And 10-T-2540 | A | 2019-03-22 | IFR | OL1-2K31-0098 | CV | 2019-04-03 | 036909C-JVD-TRN-01241 | 036909C-JVD-TRN-01241, ROC-TPSK-CECO-T-00039 | IFA | 2019-04-18 | 2019-05-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01241 |  | 2019-04-04 | 1
036909C-102D-DW-1743-0008-001 | Foundation For 10-T-2510 And 10-T-2540 | A | 2019-03-22 | IFR | OL1-2K31-0097 | CV | 2019-04-03 | 036909C-JVD-TRN-01241 | 036909C-JVD-TRN-01241, ROC-TPSK-CECO-T-00039 | IFA | 2019-04-18 | 2019-05-07 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01241 |  | 2019-04-04 | 1
036909C-1057-PID-0031-5729 | P&ID - SPRINKLER SYSTEM - SUBSTATION C CABLE CELLAR | XB | 2019-05-13 | IFLA | OL1-2L40-5729 | SE | 2019-05-14 | KLOC-TPSK-VSAFE-T-00009 | KLOC-TPSK-VSAFE-T-00009 | IFR | 2019-05-28 |  | Transmitted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5728 | P&ID - SPRINKLER SYSTEM - SUBSTATION E CABLE CELLAR | XB | 2019-05-13 | IFLA | OL1-2L40-5728 | SE | 2019-05-14 | KLOC-TPSK-VSAFE-T-00009 | KLOC-TPSK-VSAFE-T-00009 | IFR | 2019-05-28 |  | Transmitted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-1057-PID-0031-5730 | P&ID - SPRINKLER SYSTEM - SUBSTATION F CABLE CELLAR | XB | 2019-05-13 | IFLA | OL1-2L40-5730 | SE | 2019-05-14 | KLOC-TPSK-VSAFE-T-00009 | KLOC-TPSK-VSAFE-T-00009 | IFR | 2019-05-28 |  | Transmitted | TPSK-LSPA1-T-SE-01520 |  | 2019-05-02 | 2
036909C-105W-DW-1950-5015 | FIRE & GAS DEVICES LAYOUT - ZONE 5W - WASTE WATER TREATMENT | A | 2019-03-20 | IFR | OL1-2F40-5015 | FF | 2019-03-21 | 036909C-JVD-TRN-01120 | 036909C-JVD-TRN-01120, KLOC-TPSK-CECO-T-00002 | IFR | 2019-04-03 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01120 |  | 2019-03-22 | 2
036909C-105U-DW-1950-5014 | FIRE & GAS DEVICES LAYOUT -ZONE 5U - UTILITIES | A | 2019-03-20 | IFR | OL1-2F40-5014 | FF | 2019-03-21 | 036909C-JVD-TRN-01120 | 036909C-JVD-TRN-01120, KLOC-TPSK-CECO-T-00002 | IFR | 2019-04-03 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01120 |  | 2019-03-22 | 2
036909C-105T-DW-1950-5013 | FIRE & GAS DEVICES LAYOUT -ZONE 5T - COOLING WATER UNIT | A | 2019-03-20 | IFR | OL1-2F40-5013 | FF | 2019-03-21 | 036909C-JVD-TRN-01120 | 036909C-JVD-TRN-01120, KLOC-TPSK-CECO-T-00002 | IFR | 2019-04-03 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01120 |  | 2019-03-22 | 2
036909C-103A-DW-1950-5012 | FIRE & GAS DEVICES LAYOUT - ZONE 3A - BUTADIENE EXTRACTION UNIT | A | 2019-03-20 | IFR | OL1-2F40-5012 | FF | 2019-03-21 | 036909C-JVD-TRN-01120 | 036909C-JVD-TRN-01120, KLOC-TPSK-CECO-T-00002 | IFR | 2019-04-03 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01120 |  | 2019-03-22 | 2
036909C-102E-DW-1950-5011 | FIRE & GAS DEVICES LAYOUT - ZONE 2E - CRACKED GAS COMPRESSOR | A | 2019-03-20 | IFR | OL1-2F40-5011 | FF | 2019-03-21 | 036909C-JVD-TRN-01120 | 036909C-JVD-TRN-01120, KLOC-TPSK-CECO-T-00002 | IFR | 2019-04-03 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01120 |  | 2019-03-22 | 2
036909C-102C-DW-1950-5009 | FIRE & GAS DEVICES LAYOUT - ZONE 2C - HOT FRACTIONATION / GHU UNIT | A | 2019-03-20 | IFR | OL1-2F40-5009 | FF | 2019-03-21 | 036909C-JVD-TRN-01120 | 036909C-JVD-TRN-01120, KLOC-TPSK-CECO-T-00002 | IFR | 2019-04-03 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01120 |  | 2019-03-21 | 2
036909C-102B-DW-1950-5008 | FIRE & GAS DEVICES LAYOUT - ZONE 2B - C3 HYDROGENERATION | A | 2019-03-20 | IFR | OL1-2F40-5008 | FF | 2019-03-21 | 036909C-JVD-TRN-01120 | 036909C-JVD-TRN-01120, KLOC-TPSK-CECO-T-00002 | IFR | 2019-04-03 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01120 |  | 2019-03-22 | 2
036909C-102A-DW-1950-5007 | FIRE & GAS DEVICES LAYOUT - ZONE 2A - QUENCH | A | 2019-03-20 | IFR | OL1-2F40-5007 | FF | 2019-03-21 | 036909C-JVD-TRN-01120 | 036909C-JVD-TRN-01120, KLOC-TPSK-CECO-T-00002 | IFR | 2019-04-03 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01120 |  | 2019-03-22 | 2
036909C-101B-DW-1950-5006 | FIRE & GAS DEVICES LAYOUT - ZONE 1B - FURNACES UTILITIES | A | 2019-03-20 | IFR | OL1-2F40-5006 | FF | 2019-03-21 | 036909C-JVD-TRN-01120 | 036909C-JVD-TRN-01120, KLOC-TPSK-CECO-T-00002 | IFR | 2019-04-03 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01120 |  | 2019-03-22 | 2
036909C-100P-DW-1950-5003 | FIRE & GAS DEVICES LAYOUT - ZONE 0P - MAIN PIPE RACK | A | 2019-03-20 | IFR | OL1-2F40-5003 | FF | 2019-03-21 | 036909C-JVD-TRN-01119 | 036909C-JVD-TRN-01119, KLOC-TPSK-CECO-T-00002 | IFR | 2019-04-03 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01119 |  | 2019-03-22 | 2
036909C-100M-DW-1950-5002 | FIRE & GAS DEVICES LAYOUT - ZONE 0M - METERING STATION | A | 2019-03-20 | IFR | OL1-2F40-5002 | FF | 2019-03-21 | 036909C-JVD-TRN-01119 | 036909C-JVD-TRN-01119, KLOC-TPSK-CECO-T-00002 | IFR | 2019-04-03 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01119 |  | 2019-03-22 | 2
036909C-1056-SP-0910-5649 | Mechanical Equipment Datasheet - Flare KO Drum Oily Wastewater Pump | B | 2019-02-13 | IFQ | OL1-2M03-5649 | ME | 2019-03-01 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962, ROC-TPSK-CECO-T-00016 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04 | 2
036909C-1056-SP-0910-5614 | Mechanical Equipment Datasheet - Furnace Area Oily Wastewater Pump | B | 2019-02-13 | IFQ | OL1-2M03-5614 | ME | 2019-03-01 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962, ROC-TPSK-CECO-T-00016 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04 | 2
036909C-1012-DW-0132-2105 | USC 132U Cracking Furnace Insulation Details at Radiant Floor Burners | A | 2019-02-22 | IFR | OL1-2M06-2105 | ME | 2019-03-14 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15 | 2
036909C-1012-DW-0132-2103 | USC 132U Cracking Furnace Refractory and Insulation Installation Details | A | 2019-02-22 | IFR | OL1-2M06-2103 | ME | 2019-03-14 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15 | 2
036909C-1012-DW-0132-2102 | USC 132U Cracking Furnace Refractory and Insulation Convection Section Details | A | 2019-02-22 | IFR | OL1-2M06-2102 | ME | 2019-03-14 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15 | 2
036909C-1023-PDS-0800-2322 | Process Equipment Datasheet - 10-D-2322 - Skim Oil Drum | B | 2019-03-21 | IFD | OL1-2G30-2322 | PE | 2019-03-25 | 036909C-JVD-TRN-01142 | 036909C-JVD-TRN-01142 | IFR | 2019-04-09 | 2019-04-22 | TPSK-LSPA1-E-00187 -R2-Comments as noted | TPSK-LSPA1-T-PE-01142 |  | 2019-03-26 | 2
036909C-1011-SP-1552-1006 | Instrument Datasheets for Level Transmitter and Level Transmitter W-Gauge | A | 2019-04-08 | IFR | OL1-2I20-1006 | IE | 2019-04-09 | 036909C-JVD-TRN-01288 | 036909C-JVD-TRN-01288, ROC-TPSK-CECO-T-00056 | IFR | 2019-04-24 | 2019-05-13 | R2-Comments as noted | TPSK-LSPA1-T-IE-01288 |  | 2019-04-10 | 2
036909C-1012-JSS-0132-2006 | Project Specification for Supply and Installation of Refractory Insulation and Cracking Furnaces | 0 | 2019-05-07 | IMP | OL1-2M92-2006 | ME | 2019-05-10 | 036909C-JVD-TRN-01640 | 036909C-JVD-TRN-01640 | IFR | 2019-05-28 |  | Transmitted | TPSK-LSPA1-T-ME -01640 |  | 2019-05-13 | 2
036909C-1012-JSS-0127-2004 | Project Specification for Fabrication of Convection Coil for Cracking Furnaces | 0 | 2019-04-16 | IMP | OL1-2M92-2004 | ME | 2019-05-10 | 036909C-JVD-TRN-01640 | 036909C-JVD-TRN-01640 | IFR | 2019-05-28 |  | Transmitted | TPSK-LSPA1-T-ME -01640 |  | 2019-05-13 | 2
036909C-1012-JSS-0132-2005 | Project Specification for Supply and Installation of Ceramics Fiber Blanket and Ceramics Fiber Module | 0 | 2019-05-07 | IMP | OL1-2M92-2005 | ME | 2019-05-10 | 036909C-JVD-TRN-01640 | 036909C-JVD-TRN-01640 | IFR | 2019-05-28 |  | Transmitted | TPSK-LSPA1-T-ME -01640 |  | 2019-05-13 | 2
036909C-1000-DW-1576-0001 | Instrument Typical Hook-up | A | 2019-03-28 | IFR | OL1-2I51-0001 | IE | 2019-04-04 | 036909C-JVD-TRN-01254 | 036909C-JVD-TRN-01254, ROC-TPSK-CECO-T-00040 | IFA | 2019-04-19 | 2019-05-09 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-IE-1254 |  | 2019-04-05 | 1
036909C-102A-DW-1744-0001-002 | Concrete Basin 10-PIT-2090 | A | 2019-04-08 | IFR | OL1-2K31-2521 | CV | 2019-04-10 | 036909C-JVD-TRN-01304 | 036909C-JVD-TRN-01304, ROC-TPSK-CECO-T-00050 | IFA | 2019-04-25 | 2019-05-09 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01304 |  | 2019-04-11 | 1
036909C-102A-DW-1744-0001-001 | Concrete Basin 10-PIT-2090 | A | 2019-04-08 | IFR | OL1-2K31-2520 | CV | 2019-04-10 | 036909C-JVD-TRN-01304 | 036909C-JVD-TRN-01304, ROC-TPSK-CECO-T-00050 | IFA | 2019-04-25 | 2019-05-09 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01304 |  | 2019-04-11 | 1
036909C-1012-JSS-0132-2006 | Project Specification for Supply and Installation of Refractory Insulation and Cracking Furnaces | A | 2019-02-04 | IFR | OL1-2M92-2006 | ME | 2019-02-12 | 036909C-JVD-TRN-00842 | 036909C-JVD-TRN-00842 | IFR | 2019-02-26 | 2019-03-07 | R1-No comments | TPSK-LSPA1-T-ME-00842 |  | 2019-02-12 | 2
036909C-1012-JSS-0132-2005 | Project Specification for Supply and Installation of Ceramics Fiber Blanket and Ceramics Fiber Modules | A | 2019-02-04 | IFR | OL1-2M92-2005 | ME | 2019-02-12 | 036909C-JVD-TRN-00842 | 036909C-JVD-TRN-00842 | IFR | 2019-02-26 | 2019-03-07 | R1-No comments | TPSK-LSPA1-T-ME-00842 |  | 2019-02-12 | 2
036909C-1012-JSS-0127-2004 | Project Specification for Fabrication of Convection Coil for Cracking Furnaces | A | 2019-02-07 | IFR | OL1-2M92-2004 | ME | 2019-02-12 | 036909C-JVD-TRN-00842 | 036909C-JVD-TRN-00842 | IFR | 2019-02-26 | 2019-03-07 | R1-No comments | TPSK-LSPA1-T-ME-00842 |  | 2019-02-12 | 2
036909C-1023-PDS-0500-2300 | Process Equipment Datasheet - 10-T-2300 - Caustic Tower | C | 2019-01-04 | IFD | OL1-2G30-2300 | PE | 2019-01-07 | 036909C-JVD-TRN-00597 | 036909C-JVD-TRN-00597 | IFI |  | 2019-01-28 | A1-Approved without comments | TPSK-LSPA1-T-PE-00597 |  | 2019-01-07 | 1
036909C-1025-PDS-0500-2570 | Process Equipment Datasheet - 10-T-2570 - Deethanizer | C | 2018-12-18 | IFD | OL1-2G30-2570 | PE | 2018-12-20 | 036909C-JVD-TRN-00538 | 036909C-JVD-TRN-00538 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00538 |  | 2018-12-20 | 2
036909C-1012-DI-1607-2001 | Electrical Basis of Design For Furnace Island | B | 2019-03-29 | IFA | OL1-2E01-2001 | EE | 2019-03-29 | 036909C-JVD-TRN-01200 | 036909C-JVD-TRN-01200 | IFA | 2019-04-13 | 2019-04-22 | R2-Comments as noted | TPSK-LSPA1-T-EE-01200 |  | 2019-04-01 | 2
036909C-1000-JSS-1391-0002 | Job Supply Specification For Non Metallic Expansion Joints | 0 | 2019-04-01 | IMP | OL1-2R04-0042 | MP | 2019-04-02 | 036909C-JVD-TRN-01223 | 036909C-JVD-TRN-01223 | IFR | 2019-04-17 | 2019-04-26 | R1-No comments | TPSK-LSPA1-T-MP-01223 |  | 2019-04-03 | 2
036909C-1000-JSS-1391-0001 | General Supply Rules For Metallic Expansion Joints | 0 | 2019-04-01 | IMP | OL1-2R04-0040 | MP | 2019-04-02 | 036909C-JVD-TRN-01223 | 036909C-JVD-TRN-01223 | IFR | 2019-04-17 | 2019-04-26 | R1-No comments | TPSK-LSPA1-T-MP-01223 |  | 2019-04-03 | 2
036909C-1000-JSS-1386-0001 | General Supply Rules For Dynamic Piping Supports | 0 | 2019-04-01 | IMP | OL1-2R04-0039 | MP | 2019-04-02 | 036909C-JVD-TRN-01223 | 036909C-JVD-TRN-01223 | IFR | 2019-04-17 | 2019-04-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-01223 |  | 2019-04-03 | 2
036909C-1000-JSS-1384-0001 | General Supply Rules For Sliding Plates | 0 | 2019-04-01 | IMP | OL1-2R04-0038 | MP | 2019-04-02 | 036909C-JVD-TRN-01223 | 036909C-JVD-TRN-01223 | IFR | 2019-04-17 | 2019-04-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-01223 |  | 2019-04-03 | 2
036909C-1000-JSS-1383-0001 | General Supply Rules For Rod And Spring Hangers | 0 | 2019-04-01 | IMP | OL1-2R04-0037 | MP | 2019-04-02 | 036909C-JVD-TRN-01223 | 036909C-JVD-TRN-01223 | IFR | 2019-04-17 | 2019-04-26 | R2-Comments as noted | TPSK-LSPA1-T-MP-01223 |  | 2019-04-03 | 2
036909C-1000-JSS-1382-0001 | General Supply Rules For Polyurethane Piping Supports | 0 | 2019-04-01 | IMP | OL1-2R04-0036 | MP | 2019-04-02 | 036909C-JVD-TRN-01223 | 036909C-JVD-TRN-01223 | IFR | 2019-04-17 | 2019-04-26 | R1-No comments | TPSK-LSPA1-T-MP-01223 |  | 2019-04-03 | 2
036909C-1056-PDS-0900-5649 | Process Equipment Datasheet - 10-P-5607 A-B - Flare KO Drum Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5649 | PE | 2019-01-31 | 036909C-JVD-TRN-00779 | 036909C-JVD-TRN-00779 | IFI |  | 2019-03-04 | R1-No comments | TPSK-LSPA1-T-PE-00779 |  | 2019-02-01 | 2
036909C-1056-PDS-0200-5647 | Process Equipment Datasheet - 10-PIT-5607 - Flare KO Drum Oily Wastewater Sump | B | 2019-02-06 | IFD | OL1-2G30-5647 | PE | 2019-02-07 | 036909C-JVD-TRN-00819 | 036909C-JVD-TRN-00819 | IFI |  | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00819 |  | 2019-02-07 | 2
036909C-1056-PDS-0200-5605 | Process Equipment Datasheet - 10-PIT-5605 - Furnace Area Oily Wastewater Sump | B | 2019-02-06 | IFD | OL1-2G30-5605 | PE | 2019-02-07 | 036909C-JVD-TRN-00819 | 036909C-JVD-TRN-00819 | IFI |  | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00819 |  | 2019-02-07 | 2
036909C-1012-DI-1607-2001 | Electrical Basis of Design | A | 2019-01-29 | IFR | OL1-2E01-2001 | EE | 2019-01-30 | 036909C-JVD-TRN-00772 | 036909C-JVD-TRN-00772 | IFR | 2019-02-15 | 2019-02-27 | A4 - Not Approved, re-submit for approval | TPSK-LSPA1-T-EE-00772 |  | 2019-01-31 | 2
036909C-1026-PDS-0600-2621 | Process Equipment Datasheet - 10-E-2620 - C3 Hydrog Aftercooler | B | 2019-02-28 | IFD | OL1-2G30-2621 | PE | 2019-03-01 | 036909C-JVD-TRN-00966 | 036909C-JVD-TRN-00966 | IFR | 2019-03-16 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00966 |  | 2019-03-04 | 2
036909C-1027-PDS-0600-2763 | Process Equipment Datasheet - 10-E-2760 - C4-C5 Hydrog Vent Condenser | B | 2019-03-04 | IFD | OL1-2G30-2763 | PE | 2019-03-11 | 036909C-JVD-TRN-01027 | 036909C-JVD-TRN-01027, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-26 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-PE-01027 |  | 2019-03-12 | 2
036909C-1027-PDS-0600-2701 | Process Equipment Datasheet - 10-E-2701 - GHU-1 Feed - Effluent Exchangers | B | 2019-03-20 | IFD | OL1-2G30-2701 | PE | 2019-03-20 | 036909C-JVD-TRN-01107 | 036909C-JVD-TRN-01107, ROC-TPSK-CECO-T-00019 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01107 |  | 2019-03-21 | 2
036909C-1027-PDS-0800-2712 | Process Equipment Datasheet - 10-D-2710 - Depentanizer Reflux Drum | B | 2019-03-20 | IFD | OL1-2G30-2712 | PE | 2019-03-20 | 036909C-JVD-TRN-01106 | 036909C-JVD-TRN-01106 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01106 |  | 2019-03-21 | 2
036909C-1026-PDS-0800-2667 | Process Equipment Datasheet - 10-D-2666 - C5 - Pygas Surge Drum | B | 2019-03-20 | IFD | OL1-2G30-2667 | PE | 2019-03-20 | 036909C-JVD-TRN-01106 | 036909C-JVD-TRN-01106 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01106 |  | 2019-03-21 | 2
036909C-1012-DL-0133-2008 | Deviation List for Peep Doors | B | 2019-02-04 | IFR | OL1-2C40-284000 | ME | 2019-02-06 | 036909C-JVD-TRN-00812 | 036909C-JVD-TRN-00812 | IFR | 2019-02-20 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00812 |  | 2019-02-06 | 2
036909C-1053-SP-4234-0002 | Mechanical Equipment Datasheet for Side Stream Filter Package | 0 | 2019-03-22 | IFP | OL1-2M03-5355 | ME | 2019-03-27 | 036909C-JVD-TRN-01164 | 036909C-JVD-TRN-01164 | IFR | 2019-04-09 | 2019-04-25 | R2-Comments as noted | TPSK-LSPA1-T-ME-01164 |  | 2019-03-27 | 2
036909C-1000-JSD-1510-0001 | General Design Rules For Control and Safety Philosophy | A | 2019-01-29 | IFR | OL1-2R06-1025 | IE | 2019-01-29 | 036909C-JVD-TRN-00750 | 036909C-JVD-TRN-00750, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-13 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-IE-00750 |  | 2019-01-29 | 2
036909C-1000-DW-1512-0002 | Control And Safety Systems Architecture | A | 2019-02-20 | IFR | OL1-2I81-1002 | IE | 2019-02-22 | 036909C-JVD-TRN-00912 | 036909C-JVD-TRN-00912, ROC-TPSK-CECO-T-00012 | IFA | 2019-03-11 | 2019-03-08 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-00912 |  | 2019-02-25 | 1
036909C-102B-DW-1743-0011-001 | Foundation For 10-E-2450 | A | 2019-04-09 | IFR | OL1-2K31-0068 | CV | 2019-04-15 | 036909C-JVD-TRN-01349 | 036909C-JVD-TRN-01349, ROC-TPSK-CECO-T-00046 | IFA | 2019-04-30 | 2019-04-23 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01349 |  | 2019-04-16 | 1
036909C-102B-DW-1743-0042-001 | Foundation For 10-E-1005 | A | 2019-04-03 | IFR | OL1-2K31-0171 | CV | 2019-04-15 | 036909C-JVD-TRN-01349 | 036909C-JVD-TRN-01349, ROC-TPSK-CECO-T-00046 | IFA | 2019-04-30 | 2019-04-23 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01349 |  | 2019-04-16 | 1
036909C-102B-DW-1743-0040-001 | Foundation For 10-E-1000 A/B | A | 2019-04-05 | IFR | OL1-2K31-0170 | CV | 2019-04-15 | 036909C-JVD-TRN-01349 | 036909C-JVD-TRN-01349, ROC-TPSK-CECO-T-00046 | IFA | 2019-04-30 | 2019-04-23 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01349 |  | 2019-04-16 | 1
036909C-102B-DW-1743-0030-001 | Foundation For 10-E-2635 | A | 2019-04-05 | IFR | OL1-2K31-0160 | CV | 2019-04-15 | 036909C-JVD-TRN-01349 | 036909C-JVD-TRN-01349, ROC-TPSK-CECO-T-00046 | IFA | 2019-04-30 | 2019-04-23 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01349 |  | 2019-04-16 | 1
036909C-102B-CN-1733-0040 | Calculation Note For Foundation Of 10-E-1000A/B | A | 2019-04-05 | IFR | OL1-2K13-0164 | CV | 2019-04-15 | 036909C-JVD-TRN-01348 | 036909C-JVD-TRN-01348, ROC-TPSK-CECO-T-00046 | IFA | 2019-04-30 | 2019-04-23 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01348 |  | 2019-04-16 | 1
036909C-105F-DW-1652-0001 | Substation F Single Line Diagram | A | 2019-03-28 | IFR | OL1-2E14-0005 | EE | 2019-04-01 | 036909C-JVD-TRN-01211 | 036909C-JVD-TRN-01211, ROC-TPSK-CECO-T-00033 | IFA | 2019-04-16 | 2019-04-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01211 |  | 2019-04-02 | 1
036909C-100S-DW-1652-0001 | Substation E Single Line Diagram | A | 2019-03-28 | IFR | OL1-2E14-0003 | EE | 2019-04-01 | 036909C-JVD-TRN-01211 | 036909C-JVD-TRN-01211, ROC-TPSK-CECO-T-00033 | IFA | 2019-04-16 | 2019-04-25 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01211 |  | 2019-04-02 | 1
036909C-1027-SP-0940-2729 | Mechanical Equipment Datasheet - Wash Oil Pumps | B | 2019-04-05 | IFQ | OL1-2M03-2729 | ME | 2019-04-09 | 036909C-JVD-TRN-01287 | 036909C-JVD-TRN-01287 | IFR | 2019-04-24 |  | Transmitted | TPSK-LSPA1-T-ME-01287 |  | 2019-04-10 | 2
036909C-1026-SP-0510-2640 | Mechanical Equipment Data Sheet - C3 Tower | C | 2019-03-01 | IFQ | OL1-2M03-2640 | ME | 2019-03-04 | 036909C-JVD-TRN-00981 | 036909C-JVD-TRN-00981, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-19 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-ME-00981 |  | 2019-03-05 | 2
036909C-1019-SP-0940-1914 | Mechanical Equipment Datasheet - DMDS Presulfiding Injection Pump | B | 2019-03-07 | IFQ | OL1-2M03-1914 | ME | 2019-03-15 | 036909C-JVD-TRN-01086 | 036909C-JVD-TRN-01086, ROC-TPSK-CECO-T-00014 | IFR | 2019-04-01 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-01086 |  | 2019-03-18 | 2
036909C-1029-SP-0940-2934 | Mechanical Equipment Datasheet - Methanol Injection Pump | B | 2019-03-07 | IFQ | OL1-2M03-2934 | ME | 2019-03-20 | 036909C-JVD-TRN-01102 | 036909C-JVD-TRN-01102, ROC-TPSK-CECO-T-00015 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-ME-01102 |  | 2019-03-21 | 2
036909C-1019-SP-0940-1913 | Mechanical Equipment Datasheet - DMDS Feed Injection Pump | B | 2019-03-07 | IFQ | OL1-2M03-1913 | ME | 2019-03-15 | 036909C-JVD-TRN-01086 | 036909C-JVD-TRN-01086, ROC-TPSK-CECO-T-00014 | IFR | 2019-04-01 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-01086 |  | 2019-03-18 | 2
036909C-1055-PDS-0180-5560 | Process Equipment Datasheet - 10-PK-5560 - HP - Polyolefins Flare Pkg | B | 2019-03-07 | IFD | OL1-2G30-5560 | PE | 2019-03-07 | 036909C-JVD-TRN-01007 | 036909C-JVD-TRN-01007, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-22 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01007 |  | 2019-03-08 | 2
036909C-1025-SP-0510-2570 | Mechanical Equipment Data Sheet - Deethanizer | C | 2019-02-19 | IFQ | OL1-2M03-2570 | ME | 2019-02-26 | 036909C-JVD-TRN-00931 | 036909C-JVD-TRN-00931, ROC-TPSK-CECO-T-00015 | IFR | 2019-03-13 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-ME-00931 |  | 2019-02-27 | 2
036909C-1020-SP-0910-2046 | Mechanical Equipment Datasheet - Heavy Fuel Oil Pumps | B | 2019-01-22 | IFQ | OL1-2M03-2046 | ME | 2019-02-01 | 036909C-JVD-TRN-00786 | 036909C-JVD-TRN-00786, ROC-TPSK-CECO-T-00014 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00786 |  | 2019-02-04 | 2
036909C-1000-SP-1672-2101 | Data Sheet For DC UPS | A | 2019-03-25 | IFR | OL1-2E05-2101 | EE | 2019-03-29 | 036909C-JVD-TRN-01192 | 036909C-JVD-TRN-01192, ROC-TPSK-CECO-T-00037 | IFA | 2019-04-08 | 2019-04-23 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01192 |  | 2019-04-01 | 1
036909C-1000-SP-1671-2001 | Data Sheet for AC UPS | A | 2019-03-25 | IFR | OL1-2E05-2001 | EE | 2019-03-29 | 036909C-JVD-TRN-01192 | 036909C-JVD-TRN-01192, ROC-TPSK-CECO-T-00037 | IFA | 2019-04-08 | 2019-04-23 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01192 |  | 2019-04-01 | 1
036909C-1000-SP-1654-1311 | Data Sheet for 400V SwitchgearAndMCC | A | 2019-03-25 | IFR | OL1-2E05-1311 | EE | 2019-03-29 | 036909C-JVD-TRN-01192 | 036909C-JVD-TRN-01192, ROC-TPSK-CECO-T-00037 | IFA | 2019-04-08 | 2019-04-23 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01192 |  | 2019-04-01 | 1
036909C-1000-SP-1654-1211 | Data Sheet for 690V Switchgear And MCC | A | 2019-03-25 | IFR | OL1-2E05-1211 | EE | 2019-03-29 | 036909C-JVD-TRN-01192 | 036909C-JVD-TRN-01192, ROC-TPSK-CECO-T-00037 | IFA | 2019-04-08 | 2019-04-23 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01192 |  | 2019-04-01 | 1
036909C-1000-SP-1652-1111 | Data Sheet for Medium Voltage Switchgear | A | 2019-03-25 | IFR | OL1-2E05-1111 | EE | 2019-03-29 | 036909C-JVD-TRN-01192 | 036909C-JVD-TRN-01192, ROC-TPSK-CECO-T-00037 | IFA | 2019-04-08 | 2019-04-23 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01192 |  | 2019-04-01 | 1
036909C-1012-SP-0117-1205 | API Fired Heater Datasheet 10-H-1200_1600 | A | 2019-03-01 | IFR | OL1-2M03-1205 | ME | 2019-03-15 | 036909C-JVD-TRN-01084 | 036909C-JVD-TRN-01084 | IFR | 2019-03-30 |  | Transmitted | TPSK-LSPA1-T-ME-01084 |  | 2019-03-18 | 2
036909C-1053-SP-0910-5371 | Mechanical Equipment Datasheet - CW Filter Backwash Pumps | B | 2019-03-05 | IFQ | OL1-2M03-5371 | ME | 2019-03-12 | 036909C-JVD-TRN-01038 | 036909C-JVD-TRN-01038, ROC-TPSK-CECO-T-00016 | IFR | 2019-03-27 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-ME-01038 |  | 2019-03-13 | 2
036909C-1012-PDS-1543-1253 | Process Equipment Datasheet 10-MOV-1202B USC 132U Decoke Effluent Bypass MOV | B | 2019-03-28 | IFD | OL1-2G30-1253 | PE | 2019-03-29 | 036909C-JVD-TRN-01195 | 036909C-JVD-TRN-01195 | IFR |  | 2019-04-22 | R1-No comments | TPSK-LSPA1-T-PE-01195 |  | 2019-04-01 | 2
036909C-1012-PDS-1543-1252 | Process Equipment Datasheet 10-MOV-1202A USC 132U Decoke Effluent MOV | B | 2019-03-28 | IFD | OL1-2G30-1252 | PE | 2019-03-29 | 036909C-JVD-TRN-01195 | 036909C-JVD-TRN-01195 | IFR |  | 2019-04-22 | R1-No comments | TPSK-LSPA1-T-PE-01195 |  | 2019-04-01 | 2
036909C-1012-PDS-1543-1251 | Process Equipment Datasheet 10-MOV-1201 USC 132U Effluent MOV | B | 2019-03-28 | IFD | OL1-2G30-1251 | PE | 2019-03-29 | 036909C-JVD-TRN-01195 | 036909C-JVD-TRN-01195 | IFR |  | 2019-04-22 | R1-No comments | TPSK-LSPA1-T-PE-01195 |  | 2019-04-01 | 2
036909C-1000-PP-202 | HAZOP Procedure | 0 | 2019-03-26 | IMP | OL1-2S92-0006 | ES | 2019-03-27 | 036909C-JVD-TRN-01175 | 036909C-JVD-TRN-01175 | IFR | 2019-04-11 | 2019-04-22 | R1-No comments | TPSK-LSPA1-T-ES-01175 |  | 2019-03-28 | 2
036909C-1010-DI-0007-1001 | Area Basis of Design - 10 Feed Preparation | B | 2019-03-25 | IFD | OL1-2G05-1001 | PE | 2019-03-26 | 036909C-JVD-TRN-01154 | 036909C-JVD-TRN-01154 | IFA | 2019-04-10 | 2019-04-22 | A1-Approved without comments | TPSK-LSPA1-T-PE-01154 |  | 2019-03-27 | 1
036909C-102B-DW-1743-0039-001 | Foundation for 10-D-1000 | A | 2019-04-09 | IFR | OL1-2K31-0159 | CV | 2019-04-16 | 036909C-JVD-TRN-01373 | 036909C-JVD-TRN-01373, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 |  | Transmitted | TPSK-LSPA1-T-CV-01373 |  | 2019-04-17 | 1
036909C-102E-DW-1743-0022-001 | Foundation For 10-E-2210AB | A | 2019-04-11 | IFR | OL1-2K31-0071 | CV | 2019-04-16 | 036909C-JVD-TRN-01373 | 036909C-JVD-TRN-01373, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 |  | Transmitted | TPSK-LSPA1-T-CV-01373 |  | 2019-04-17 | 1
036909C-102B-DW-1743-0027-001 | Foundation for 10-T-2630 | A | 2019-04-09 | IFR | OL1-2K31-0153 | CV | 2019-04-16 | 036909C-JVD-TRN-01373 | 036909C-JVD-TRN-01373, ROC-TPSK-CECO-T-00046 | IFA | 2019-05-01 |  | Transmitted | TPSK-LSPA1-T-CV-01373 |  | 2019-04-17 | 1
036909C-1000-DW-1576-0005 | Instr Supports Typical Mount Details | A | 2019-03-12 | IFR | OL1-2I31-0001 | IE | 2019-03-14 | 036909C-JVD-TRN-01058 | 036909C-JVD-TRN-01058, ROC-TPSK-CECO-T-00037 | IFA | 2019-03-29 | 2019-04-05 | A3 - Approved with comments, re-submit for review | TPSL-LSPA1-T-IE-01058 |  | 2019-03-15 | 1
036909C-1000-JSD-1515-0001 | General Design Rules For SIS Safety Requirements Specification | A | 2019-01-23 | IFR | OL1-2I61-1102 | IE | 2019-01-25 | 036909C-JVD-TRN-00719 | 036909C-JVD-TRN-00719, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-08 | 2019-03-05 | R2-Comments as noted | TPSK-LSPA1-T-IE-00719 |  | 2019-01-25 | 2
036909C-1059-SP-0940-5951 | Mechanical Equipment Datasheet - Olefins NaOCl Metering Pumps | B | 2019-03-26 | IFQ | OL1-2M03-5951 | ME | 2019-04-08 | 036909C-JVD-TRN-01279 | 036909C-JVD-TRN-01279 | IFR | 2019-04-23 |  | Transmitted | TPSK-LSPA1-T-ME-01279 |  | 2019-04-09 | 2
036909C-1059-SP-0940-5902 | Mechanical Equipment Datasheet - Olefins Sulfuric Acid Metering Pumps | B | 2019-03-26 | IFQ | OL1-2M03-5902 | ME | 2019-04-08 | 036909C-JVD-TRN-01279 | 036909C-JVD-TRN-01279 | IFR | 2019-04-23 |  | Transmitted | TPSK-LSPA1-T-ME-01279 |  | 2019-04-09 | 2
036909C-1026-PDS-0900-2663 | Process Equipment Datasheet - 10-P-2660 A-B - Debutanizer Reflux - Product Pumps | B | 2018-12-10 | IFD | OL1-2G30-2663 | PE | 2018-12-13 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00481 |  | 2018-12-13 | 2
036909C-1021-PDS-0900-2126 | Process Equipment Datasheet - 10-P-2126 A-B - Distillate Stripper Bottom Pumps | B | 2019-02-28 | IFD | OL1-2G30-2126 | PE | 2019-03-01 | 036909C-JVD-TRN-00963 | 036909C-JVD-TRN-00963 | IFR | 2019-03-16 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-PE-00963 |  | 2019-03-04 | 2
036909C-1023-PDS-0800-2309 | Process Equipment Datasheet - 10-D-2305 - Yellow Oil Drum | B | 2019-01-10 | IFD | OL1-2G30-2309 | PE | 2019-01-11 | 036909C-JVD-TRN-00634 | 036909C-JVD-TRN-00634 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00634 |  | 2019-01-11 | 1
036909C-1020-SP-0910-2091 | Mechanical Equipment Datasheet - Quench Oil Drain Drum Pumps | B | 2019-03-28 | IFQ | OL1-2M03-2091 | ME | 2019-04-02 | 036909C-JVD-TRN-01227 | 036909C-JVD-TRN-01227 | IFR | 2019-04-17 |  | Transmitted | TPSK-LSPA1-T-ME-01227 |  | 2019-04-03 | 2
036909C-1020-SP-0910-2091 | Mechanical Equipment Datasheet - Quench Oil Drain Drum Pumps | A | 2018-12-05 | IFQ | OL1-2M03-2091 | ME | 2018-12-13 | 036909C-JVD-TRN-00494 | 036909C-JVD-TRN-00494, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-26 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00494 |  | 2018-12-13 | 2
036909C-102E-DW-1743-0037 | Foundation For 10-D-2440 | A | 2019-03-20 | IFR | OL1-2K31-0158 | CV | 2019-03-27 | 036909C-JVD-TRN-01169 | 036909C-JVD-TRN-01169, ROC-TPSK-CECO-T-00028 | IFR | 2019-04-11 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01169 |  | 2019-03-28 | 2
036909C-102E-DW-1743-0036 | Foundation For 10-D-2460 | A | 2019-03-20 | IFR | OL1-2K31-0157 | CV | 2019-03-27 | 036909C-JVD-TRN-01169 | 036909C-JVD-TRN-01169, ROC-TPSK-CECO-T-00028 | IFR | 2019-04-11 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01169 |  | 2019-03-28 | 2
036909C-102E-DW-1743-0033 | Foundation Vor 10-D-2480A | A | 2019-03-20 | IFR | OL1-2K31-0101 | CV | 2019-03-27 | 036909C-JVD-TRN-01169 | 036909C-JVD-TRN-01169, ROC-TPSK-CECO-T-00028 | IFR | 2019-04-11 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01169 |  | 2019-03-28 | 2
036909C-102E-DW-1743-0032 | Foundation For 10-D-2411 | A | 2019-03-20 | IFR | OL1-2K31-0100 | CV | 2019-03-27 | 036909C-JVD-TRN-01169 | 036909C-JVD-TRN-01169, ROC-TPSK-CECO-T-00028 | IFR | 2019-04-11 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01169 |  | 2019-03-28 | 2
036909C-102E-DW-1743-0012 | Foundation for 10-D-2405 | A | 2019-03-20 | IFR | OL1-2K31-0053 | CV | 2019-03-27 | 036909C-JVD-TRN-01169 | 036909C-JVD-TRN-01169, ROC-TPSK-CECO-T-00028 | IFR | 2019-04-11 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01169 |  | 2019-03-28 | 2
036909C-102E-DW-1743-0011 | Foundation For 10-D-2230 | A | 2019-03-20 | IFR | OL1-2K31-0052 | CV | 2019-03-27 | 036909C-JVD-TRN-01169 | 036909C-JVD-TRN-01169, ROC-TPSK-CECO-T-00028 | IFR | 2019-04-11 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01169 |  | 2019-03-28 | 2
036909C-102E-DW-1743-0010 | Foundation For 10-D-2210 | A | 2019-03-20 | IFR | OL1-2K31-0051 | CV | 2019-03-27 | 036909C-JVD-TRN-01169 | 036909C-JVD-TRN-01169, ROC-TPSK-CECO-T-00028 | IFR | 2019-04-11 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01169 |  | 2019-03-28 | 2
036909C-102D-DW-1743-0007 | Foundation For 10-T-2570 | A | 2019-03-22 | IFR | OL1-2K31-0096 | CV | 2019-03-27 | 036909C-JVD-TRN-01169 | 036909C-JVD-TRN-01169, ROC-TPSK-CECO-T-00028 | IFR | 2019-04-11 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01169 |  | 2019-03-28 | 2
036909C-102D-DW-1743-0005 | Foundation For 10-T-2580 | A | 2019-03-22 | IFR | OL1-2K31-0094 | CV | 2019-03-27 | 036909C-JVD-TRN-01169 | 036909C-JVD-TRN-01169, ROC-TPSK-CECO-T-00028 | IFR | 2019-04-11 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01169 |  | 2019-03-28 | 2
036909C-102D-CN-1733-0005 | Calculation Note For Foundation Of 10-T-2540 And 10-T-2510 | A | 2019-03-22 | IFR | OL1-2K13-0091 | CV | 2019-03-27 | 036909C-JVD-TRN-01168 | 036909C-JVD-TRN-01168, ROC-TPSK-CECO-T-00028 | IFA | 2019-04-11 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01168 |  | 2019-03-28 | 1
036909C-102D-DW-1743-0038 | Foundation For 10-E-2855 | A | 2019-03-19 | IFR | OL1-2K34-0135 | CV | 2019-03-20 | 036909C-JVD-TRN-01104 | 036909C-JVD-TRN-01104, ROC-TPSK-CECO-T-00023 | IFR | 2019-04-04 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01104 |  | 2019-03-21 | 2
036909C-102D-DW-1743-0018 | Foundation For 10-D-2550 | A | 2019-03-15 | IFR | OL1-2K34-0110 | CV | 2019-03-20 | 036909C-JVD-TRN-01104 | 036909C-JVD-TRN-01104, ROC-TPSK-CECO-T-00023 | IFR | 2019-04-04 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01104 |  | 2019-03-21 | 2
036909C-102D-DW-1743-0017 | Foundation For 10-D-2555 | A | 2019-03-15 | IFR | OL1-2K34-0109 | CV | 2019-03-20 | 036909C-JVD-TRN-01104 | 036909C-JVD-TRN-01104, ROC-TPSK-CECO-T-00023 | IFR | 2019-04-04 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01104 |  | 2019-03-21 | 2
036909C-102A-DW-1743-0003 | Foundation For 10-T-2100 | B | 2019-03-18 | IFR | OL1-2K34-1040 | CV | 2019-03-20 | 036909C-JVD-TRN-01104 | 036909C-JVD-TRN-01104, ROC-TPSK-CECO-T-00023 | IFR | 2019-04-04 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01104 |  | 2019-03-21 | 2
036909C-102A-DW-1743-0002 | Foundation For 10-T-2020 | A | 2019-03-18 | IFR | OL1-2K34-1020 | CV | 2019-03-20 | 036909C-JVD-TRN-01104 | 036909C-JVD-TRN-01104, ROC-TPSK-CECO-T-00023 | IFR | 2019-04-04 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01104 |  | 2019-03-21 | 2
036909C-102A-DW-1743-0001 | Foundation for 10-T-2000 | A | 2019-03-18 | IFR | OL1-2K34-1001 | CV | 2019-03-20 | 036909C-JVD-TRN-01104 | 036909C-JVD-TRN-01104, ROC-TPSK-CECO-T-00023 | IFR | 2019-04-04 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-01104 |  | 2019-03-21 | 2
036909C-102A-CN-1733-0034 | Calculation Note For Foundation Of 10-T-2100 | B | 2019-03-18 | IFR | OL1-2K13-0324 | CV | 2019-03-19 | 036909C-JVD-TRN-01092 | 036909C-JVD-TRN-01092, ROC-TPSK-CECO-T-00024 | IFA | 2019-04-03 | 2019-04-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-01092 |  | 2019-03-20 | 1
036909C-102D-DW-1743-0043 | Foundation For 10-E-2582 | B | 2019-02-19 | IFR | OL1-2K34-0139 | CV | 2019-02-21 | 036909C-JVD-TRN-00903 | 036909C-JVD-TRN-00903, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-08 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00903 |  | 2019-02-21 | 2
036909C-102D-DW-1743-0041 | Foundation For 10-E-2858 | A | 2019-02-08 | IFR | OL1-2K34-0133 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-01 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15 | 2
036909C-102D-DW-1743-0037 | Foundation For 10-E-2856 | A | 2019-02-07 | IFR | OL1-2K34-0134 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-01 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15 | 2
036909C-102D-DW-1743-0034 | Foundation For 10-E-2548 | A | 2019-02-04 | IFR | OL1-2K34-0127 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-01 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15 | 2
036909C-102D-DW-1743-0033 | Foundation For 10-E-2546 | A | 2019-02-08 | IFR | OL1-2K34-0126 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-01 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15 | 2
036909C-102D-DW-1743-0026 | Foundation For 10-E-2809 | A | 2019-02-07 | IFR | OL1-2K34-0131 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-01 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15 | 2
036909C-102D-DW-1743-0025 | Foundation For 10-E-2807 | A | 2019-02-06 | IFR | OL1-2K34-0130 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-01 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15 | 2
036909C-102D-DW-1743-0024 | Foundation For 10-D-2865 | A | 2019-02-06 | IFR | OL1-2K34-0116 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-01 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15 | 2
036909C-102D-DW-1743-0020 | Foundation For 10-D-2575 | A | 2019-02-11 | IFR | OL1-2K34-0112 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-01 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15 | 2
036909C-102B-DW-1743-0002 | Foundation For 10-T-2330 | A | 2019-02-07 | IFR | OL1-2K34-0042 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-01 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15 | 2
036909C-102A-DW-1743-0034 | Foundation For 10-E-2008A/B/C/D/E | A | 2019-02-05 | IFR | OL1-2K34-0191 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-01 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15 | 2
036909C-102A-DW-1743-0019 | Foundation For 10-E-2026 | A | 2019-02-08 | IFR | OL1-2K34-0026 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-01 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15 | 2
036909C-102A-DW-1743-0017 | Foundation For 10-E-2146 | A | 2019-02-05 | IFR | OL1-2K34-0024 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-01 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15 | 2
036909C-102A-DW-1743-0008 | Foundation for 10-D-5150 | A | 2019-02-05 | IFR | OL1-2K34-0015 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-01 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15 | 2
036909C-101B-DW-1743-0001 | Foundation For 10-D-5200 | A | 2019-02-05 | IFR | OL1-2K34-0007 | CV | 2019-02-15 | 036909C-JVD-TRN-00854 | 036909C-JVD-TRN-00854, ROC-TPSK-CECO-T-00023 | IFR | 2019-03-01 | 2019-04-12 | R2-Comments as noted | TPSK-LSPA1-T-CV-00854 |  | 2019-02-15 | 2
036909C-1056-PDS-0900-5625 | Process Equipment Datasheet - 10-P-5628 A-B - Gate 3 Septic Tank Pumps | C | 2019-03-21 | IFD | OL1-2G30-5625 | PE | 2019-03-25 | 036909C-JVD-TRN-01152 | 036909C-JVD-TRN-01152 | IFR | 2019-04-09 | 2019-04-12 | R1-No comments | TPSK-LSPA1-T-PE-01152 |  | 2019-03-26 | 2
036909C-1059-PDS-0900-5951 | Process Equipment Datasheet - 10-P-5950 A-B - Olefins NaOCL Metering Pumps | B | 2019-03-20 | IFD | OL1-2G30-5951 | PE | 2019-03-21 | 036909C-JVD-TRN-01129 | 036909C-JVD-TRN-01129 | IFR | 2019-04-05 | 2019-04-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01129 |  | 2019-03-22 | 2
036909C-1059-PDS-0900-5902 | Process Equipment Datasheet - 10-P-5901 A-B - Sulfuric Acid Metering Pumps | C | 2019-03-20 | IFD | OL1-2G30-5902 | PE | 2019-03-21 | 036909C-JVD-TRN-01129 | 036909C-JVD-TRN-01129 | IFR | 2019-04-05 | 2019-04-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-01129 |  | 2019-03-22 | 2
036909C-1022-TDS-0610-2206 | Mechanical Equipment Data Sheet - 10-E-2206 - Wash Water Cooler | B | 2019-03-13 | IFQ | OL1-2M03-2206 | ME | 2019-03-20 | 036909C-JVD-TRN-01110 | 036909C-JVD-TRN-01110, ROC-TPSK-CECO-T-00017 | IFR | 2019-04-04 | 2019-04-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-01110 |  | 2019-03-21 | 2
036909C-1000-MS-6850-0051 | Job Construction Specification For Machinery And Air Coolers Installation | A | 2019-04-04 | IFR | OL1-2Q92-0019 | QM | 2019-04-10 | 036909C-JVD-TRN-01305 | 036909C-JVD-TRN-01305 | IFR | 2019-04-25 |  | Transmitted | TPSK-LSPA1-T-QM-01305 |  | 2019-04-11 | 2
036909C-1000-MS-1359-0071 | Job Construction Specification For Bolted Flange Joint Assembly Management During Construction Precommissioning And Commissioning | A | 2019-04-08 | IFR | OL1-2Q92-0014 | QM | 2019-04-10 | 036909C-JVD-TRN-01306 | 036909C-JVD-TRN-01306 | IFR | 2019-04-25 |  | Transmitted | TPSK-LSPA1-T-QM-01306 |  | 2019-04-11 | 2
036909C-1024-PDS-0800-2410 | Process Equipment Datasheet - 10-D-2410 A-B - Cracked Gas Dryer | B | 2019-01-15 | IFD | OL1-2G30-2410 | PE | 2019-01-18 | 036909C-JVD-TRN-00678 | 036909C-JVD-TRN-00678 | IFI |  | 2019-01-29 | R1-No comments | TPSK-LSPA1-T-PE-00678 |  | 2019-01-18 | 2
036909C-1019-PDS-0800-1912 | Process Equipment Datasheet - 10-D-1912 - DMDS Injection Drum | B | 2019-03-18 | IFD | OL1-2G30-1912 | PE | 2019-03-19 | 036909C-JVD-TRN-01096 | 036909C-JVD-TRN-01096 | IFR | 2019-04-03 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01096 |  | 2019-03-20 | 2
036909C-1019-PDS-0800-1911 | Process Equipment Datasheet - 10-D-1910 - DMDS Bulk Storage Drum | B | 2019-03-18 | IFD | OL1-2G30-1911 | PE | 2019-03-19 | 036909C-JVD-TRN-01096 | 036909C-JVD-TRN-01096 | IFR | 2019-04-03 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01096 |  | 2019-03-20 | 2
036909C-1012-PDS-0610-1209 | Process Equipment Datasheet - 10-E-1210_10-E-1610 - USC 132U TLX Quench Exchanger | C | 2019-03-14 | IFD | OL1-2G30-1209 | PE | 2019-03-15 | 036909C-JVD-TRN-01078 | 036909C-JVD-TRN-01078, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-30 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-PE-01078 |  | 2019-03-18 | 2
036909C-1056-SP-0910-5637 | Mechanical Equipment Datasheet - HP Flare Area Oily Wastewater Sump Pumps | B | 2019-03-12 | IFQ | OL1-2M03-5637 | ME | 2019-03-20 | 036909C-JVD-TRN-01102 | 036909C-JVD-TRN-01102, ROC-TPSK-CECO-T-00016 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-ME-01102 |  | 2019-03-21 | 2
036909C-1056-SP-0910-5621 | Mechanical Equipment Datasheet - Olefins Holding Basin Skimmed Oil Pump | B | 2019-03-12 | IFQ | OL1-2M03-5621 | ME | 2019-03-20 | 036909C-JVD-TRN-01102 | 036909C-JVD-TRN-01102, ROC-TPSK-CECO-T-00016 | IFR | 2019-04-04 | 2019-04-10 | R1-No comments | TPSK-LSPA1-T-ME-01102 |  | 2019-03-21 | 2
036909C-1028-SP-1011-2850 | Mechanical Equipment DataSeet For Ethylene Refrigeration Compressor | 0 | 2019-03-15 | IFP | OL1-2M03-2850 | ME | 2019-03-21 | 036909C-JVD-TRN-01121 | 036909C-JVD-TRN-01121, ROC-TPSK-CECO-T-00015 | IFR | 2019-04-05 | 2019-04-05 | R1-No comments | TPSK-LSPA1-T-ME-01121 |  | 2019-03-22 | 2
036909C-1028-SP-1011-2800 | Mechanical Datasheet For Propylene Refrigeration Compressor | 0 | 2019-03-15 | IFP | OL1-2M03-2800 | ME | 2019-03-21 | 036909C-JVD-TRN-01121 | 036909C-JVD-TRN-01121, ROC-TPSK-CECO-T-00015 | IFR | 2019-04-05 | 2019-04-05 | R1-No comments | TPSK-LSPA1-T-ME-01121 |  | 2019-03-22 | 2
036909C-1022-SP-1011-2200 | Mechanical DataSheet For Cracked Gas Compressor | 0 | 2019-03-15 | IFP | OL1-2M03-2200 | ME | 2019-03-21 | 036909C-JVD-TRN-01121 | 036909C-JVD-TRN-01121, ROC-TPSK-CECO-T-00014 | IFR | 2019-04-05 | 2019-04-05 | R1-No comments | TPSK-LSPA1-T-ME-01121 |  | 2019-03-22 | 2
036909C-1025-DI-0007-2501 | Area Basis of Design - 25 Cold Fractionation | B | 2019-04-08 | IFD | OL1-2G05-2501 | PE | 2019-04-08 | 036909C-JVD-TRN-01276 | 036909C-JVD-TRN-01276 | IFA | 2019-04-23 |  | Transmitted | TPSK-LSPA1-T-PE-01276 |  | 2019-04-09 | 1
036909C-1000-JSD-1584-0001 | Custody Transfer System | 0 | 2019-03-19 | IMP | OL1-2R06-3101 | IE | 2019-03-19 | 036909C-JVD-TRN-01094 | 036909C-JVD-TRN-01094 | IFR | 2019-04-03 | 2019-04-05 | R1-No comments | TPSK-LSPA1-T-IE-01094 |  | 2019-03-20 | 2
036909C-1052-PDS-0600-5210 | Process Equipment Datasheet - 10-E-5210 - Pilot Gas Vaporizer | B | 2019-03-13 | IFD | OL1-2G30-5210 | PE | 2019-03-14 | 036909C-JVD-TRN-01054 | 036909C-JVD-TRN-01054 | IFR | 2019-03-29 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-PE-01054 |  | 2019-03-15 | 2
036909C-1011-SP-1541-1001 | USC 36M and USC 132U Instrument Datasheets for Control Valve | A | 2019-03-21 | IFA | OL1-2I20-1001 | IE | 2019-03-21 | 036909C-JVD-TRN-01130 | 036909C-JVD-TRN-01130 | IFA | 2019-04-05 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01130 |  | 2019-03-22 | 1
036909C-1000-QCP-2520-0003 | Quality Control Plan Cryogenic Tanks Erection | A | 2019-02-19 | IFR | OL1-2Q23-0003 | QM | 2019-02-27 | 036909C-JVD-TRN-00942 | 036909C-JVD-TRN-00942 | IFA | 2019-03-14 |  | Transmitted | TPSK-LSPA1-T-QM-00942 |  | 2019-02-28 | 1
036909C-1000-QCP-0000-0001 | Quality Control Plan Material Management and Warehouse | A | 2019-01-31 | IFR | OL1-2Q92-0008 | QM | 2019-02-07 | 036909C-JVD-TRN-00818 | 036909C-JVD-TRN-00818 | IFA | 2019-02-22 |  | Transmitted | TPSK-LSPA1-T-QM-00818 |  | 2019-02-07 | 1
036909C-1000-JSD-1300-0012 | Pipe Support | 0 | 2019-02-04 | IMP | OL1-2R04-0012 | MP | 2019-02-08 | 036909C-JVD-TRN-00828 | 036909C-JVD-TRN-00828, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-MP-00828 |  | 2019-02-08 | 2
036909C-1000-JSD-1300-0009 | JSD for Piping Loads On PRK SLW STR IS | 0 | 2019-02-04 | IMP | OL1-2R04-0033 | MP | 2019-02-08 | 036909C-JVD-TRN-00828 | 036909C-JVD-TRN-00828, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-MP-00828 |  | 2019-02-08 | 2
036909C-1000-JSD-1560-0001 | Process On-Line Analyzer And Analyzer Housing | A | 2019-01-31 | IFR | OL1-2R06-2003 | IE | 2019-02-08 | 036909C-JVD-TRN-00825 | 036909C-JVD-TRN-00825, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-25 | 2019-03-08 | R1-No comments | TPSK-LSPA1-T-IE-00825 |  | 2019-02-08 | 2
036909C-1012-SP-0137-2010 | Particular Technical Specification for MOVs | A | 2018-12-12 | IFQ | OL1-2M57-2010 | ME | 2018-12-18 | 036909C-JVD-TRN-00534 | 036909C-JVD-TRN-00534 | IFI |  | 2019-02-28 | R2-Comments as noted | TPSK-LSPA1-T-ME-00534 |  | 2018-12-18 | 3
036909C-1000-MS-6820-0051 | Job Construction Specification For Static Equipment and Trays-Internals Installation | A | 2019-04-02 | IFR | OL1-2Q92-0018 | QM | 2019-04-03 | 036909C-JVD-TRN-01237 | 036909C-JVD-TRN-01237 | IFR | 2019-04-18 |  | Transmitted | TPSK-LSPA1-T-QM-01237 |  | 2019-04-03 | 2
036909C-1000-MS-0000-0051 | Job Construction Specification For Welders Management | A | 2019-03-26 | IFR | OL1-2Q92-0011 | QM | 2019-04-03 | 036909C-JVD-TRN-01236 | 036909C-JVD-TRN-01236 | IFR | 2019-04-18 |  | Transmitted | TPSK-LSPA1-T-QM-01236 |  | 2019-04-04 | 2
036909C-1000-MS-0000-0053 | Job Construction Specification For Piping Material Traceability | A | 2019-03-29 | IFR | OL1-2Q92-0013 | QM | 2019-04-03 | 036909C-JVD-TRN-01236 | 036909C-JVD-TRN-01236 | IFR | 2019-04-18 |  | Transmitted | TPSK-LSPA1-T-QM-01236 |  | 2019-04-04 | 2
036909C-1051-SP-0845-0001 | Mechanical Equipment Datasheet for Deaerator D-5100 | 0 | 2019-03-29 | IFP | OL1-2M03-5100 | ME | 2019-04-01 | 036909C-JVD-TRN-01209 | 036909C-JVD-TRN-01209 | IFR | 2019-04-16 |  | Transmitted | TPSK-LSPA1-T-ME-01209 |  | 2019-04-02 | 2
036909C-1000-JSS-1391-0001 | General Supply Rules For Metallic Expansion Joints | A | 2019-02-04 | IFR | OL1-2R04-0040 | MP | 2019-02-08 | 036909C-JVD-TRN-00831 | 036909C-JVD-TRN-00831, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 | 2019-03-21 | R2-Comments as noted | TPSK-LSPA1-T-MP-00831 |  | 2019-02-08 | 2
036909C-1000-JSS-1386-0001 | General Supply Rules For Dynamic Piping Supports | A | 2019-02-04 | IFR | OL1-2R04-0039 | MP | 2019-02-08 | 036909C-JVD-TRN-00831 | 036909C-JVD-TRN-00831, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-MP-00831 |  | 2019-02-08 | 2
036909C-1000-JSS-1384-0001 | General Supply Rules For Sliding Plates | A | 2019-02-04 | IFR | OL1-2R04-0038 | MP | 2019-02-08 | 036909C-JVD-TRN-00831 | 036909C-JVD-TRN-00831, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-MP-00831 |  | 2019-02-08 | 2
036909C-1000-JSS-1383-0001 | General Supply Rules For Rod And Spring Hangers | A | 2019-02-04 | IFR | OL1-2R04-0037 | MP | 2019-02-08 | 036909C-JVD-TRN-00831 | 036909C-JVD-TRN-00831, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 | 2019-03-21 | R2-Comments as noted | TPSK-LSPA1-T-MP-00831 |  | 2019-02-08 | 2
036909C-1000-JSS-1382-0001 | General Supply Rules For Polyurethane Piping Supports | A | 2019-02-04 | IFR | OL1-2R04-0036 | MP | 2019-02-08 | 036909C-JVD-TRN-00831 | 036909C-JVD-TRN-00831, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-25 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-MP-00831 |  | 2019-02-08 | 2
036909C-1000-JSD-1300-0010 | JSD For Auxiliary Piping Supports | 0 | 2019-03-06 | IMP | OL1-2R04-0034 | MP | 2019-03-07 | 036909C-JVD-TRN-01002 | 036909C-JVD-TRN-01002, ROC-TPSK-CECO-T-00003 | IFR | 2019-03-22 | 2019-04-01 | R1-No comments | TPSK-LSPA1-T-MP-01002 |  | 2019-03-08 | 2
036909C-1056-PDS-0900-5606 | Process Equipment Datasheet - 10-P-5600 A-B - Pygas Area Oily Wastewater Pump | C | 2019-03-13 | IFD | OL1-2G30-5606 | PE | 2019-03-14 | 036909C-JVD-TRN-01051 | 036909C-JVD-TRN-01051 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-PE-01051 |  | 2019-03-15 | 2
036909C-1051-PDS-0900-5109 | Process Equipment Datasheet - 10-P-5110 A-B-C - Condensate Pumps | C | 2019-03-13 | IFD | OL1-2G30-5109 | PE | 2019-03-14 | 036909C-JVD-TRN-01051 | 036909C-JVD-TRN-01051 | IFR | 2019-03-29 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-01051 |  | 2019-03-15 | 2
036909C-1000-QCP-6882-0001 | Quality Control Plan Bridge Crane Installation | A | 2019-03-06 | IFR | OL1-2Q23-0022 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 | 2019-04-01 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1000-QCP-6880-0002 | Quality Control Plan Skid Mounted Packages | A | 2019-03-05 | IFR | OL1-2Q23-0021 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 | 2019-04-01 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1000-QCP-6880-0001 | Quality Control Plan Packages Installation | A | 2019-03-04 | IFR | OL1-2Q23-0020 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 | 2019-04-01 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1000-QCP-6872-0001 | Quality Control Plan Cooling Tower Mechanical Installation | A | 2019-03-04 | IFR | OL1-2Q23-0019 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 | 2019-04-01 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1000-QCP-6860-0002 | Quality Control Plan Equipment Internals Installation - Distributors-Grids-Demisters-etc | A | 2019-03-04 | IFR | OL1-2Q23-0017 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 | 2019-04-01 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1000-QCP-6852-0001 | Quality Control Plan Elevator Installation | A | 2019-03-04 | IFR | OL1-2Q23-0015 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 | 2019-04-01 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1000-QCP-6850-0005 | Quality Control Plan Machinery Installation - Mixers and Agitators | A | 2019-03-04 | IFR | OL1-2Q23-0014 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 | 2019-04-01 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1000-QCP-6850-0004 | Quality Control Plan Machinery Installation - Reciprocating Compressors | A | 2019-03-04 | IFR | OL1-2Q23-0013 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 | 2019-04-01 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1000-QCP-6850-0003 | Quality Control Plan Machinery Installation - Centrifugal Compressors | A | 2019-02-28 | IFR | OL1-2Q23-0012 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 | 2019-04-01 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1000-QCP-6850-0002 | Quality Control Plan Machinery Installation - Blower and Fans | A | 2019-03-04 | IFR | OL1-2Q23-0011 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 | 2019-04-01 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1000-QCP-6850-0001 | Quality Control Plan Machinery Installation - Centrifugal and Rotary Pumps | A | 2019-03-04 | IFR | OL1-2Q23-0010 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 | 2019-04-01 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1000-QCP-6835-0001 | Quality Control Plan Refractory Installation | A | 2019-02-28 | IFR | OL1-2Q23-0009 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 | 2019-04-01 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1000-QCP-6833-0001 | Quality Control Plan Flare System Erection | A | 2019-02-28 | IFR | OL1-2Q23-0008 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 | 2019-04-01 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1000-QCP-6831-0001 | Quality Control Plan Package Furnace - Site Assembled - Installation | A | 2019-02-28 | IFR | OL1-2Q23-0007 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 | 2019-04-01 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1000-QCP-6820-0001 | Quality Control Plan Static Equipment Installation | A | 2019-02-28 | IFR | OL1-2Q23-0006 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 | 2019-04-01 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1012-SR-0155-2018 | Scope of Supply for Furnace Steam Drums | 0 | 2018-12-11 | IFP | OL1-2M56-2018 | ME | 2018-12-17 | 036909C-JVD-TRN-00518 | 036909C-JVD-TRN-00518 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00518 |  | 2018-12-17 | 3
036909C-1012-SP-0155-2018 | Particular Technical Specification for Furnace Steam Drums | 0 | 2018-12-11 | IFP | OL1-2M57-2018 | ME | 2018-12-17 | 036909C-JVD-TRN-00518 | 036909C-JVD-TRN-00518 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00518 |  | 2018-12-17 | 3
036909C-1012-SR-0127-2002 | Scope of Supply for Furnace Convection Fittings | 0 | 2018-12-19 | IFP | OL1-2M56-2002 | ME | 2019-01-07 | 036909C-JVD-TRN-00592 | 036909C-JVD-TRN-00592 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00592 |  | 2019-01-07 | 3
036909C-1012-SP-0127-2002 | Particular Technical Specification for Furnace Convection Fittings | 0 | 2018-12-19 | IFP | OL1-2M57-2002 | ME | 2019-01-07 | 036909C-JVD-TRN-00592 | 036909C-JVD-TRN-00592 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00592 |  | 2019-01-07 | 3
036909C-1012-SR-0125-2007 | Scope of Supply For Cast Intermediate Tube Supports | 0 | 2018-12-18 | IFP | OL1-2M56-2007 | ME | 2018-12-20 | 036909C-JVD-TRN-00542 | 036909C-JVD-TRN-00542 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00542 |  | 2018-12-20 | 3
036909C-1012-SP-0125-2007 | Particular Technical Specification for Cast Intermediate Tube Supports | 0 | 2018-12-18 | IFP | OL1-2M57-2007 | ME | 2018-12-20 | 036909C-JVD-TRN-00542 | 036909C-JVD-TRN-00542 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00542 |  | 2018-12-20 | 3
036909C-1012-SR-0154-2003 | Scope of Supply for Quench Exchangers | 0 | 2018-12-06 | IFP | OL1-2M56-2003 | ME | 2018-12-10 | 036909C-JVD-TRN-00466 | 036909C-JVD-TRN-00466 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00466 |  | 2018-12-10 | 3
036909C-1012-SP-0154-2003 | Particular Techanical Specification for Quench Exchangers | 0 | 2018-12-06 | IFP | OL1-2M57-2003 | ME | 2018-12-10 | 036909C-JVD-TRN-00466 | 036909C-JVD-TRN-00466 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00466 |  | 2018-12-10 | 3
036909C-1011-SP-1040-1001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 36M | 0 | 2019-03-06 | IMP | OL1-2M03-1001 | ME | 2019-03-11 | 036909C-JVD-TRN-01021 | 036909C-JVD-TRN-01021, ROC-TPSK-CECO-T-00014 | IFR |  | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-ME-01021 |  | 2019-03-12 | 2
036909C-1012-SP-1040-2001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 132U | 0 | 2019-03-06 | IMP | OL1-2M03-2001 | ME | 2019-03-11 | 036909C-JVD-TRN-01021 | 036909C-JVD-TRN-01021, ROC-TPSK-CECO-T-00014 | IFR |  | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-ME-01021 |  | 2019-03-12 | 2
036909C-1000-DW-1702-0001 | General Notes For Concrete Works | 0 | 2019-02-12 | IFC | OL1-2K92-0003 | CV | 2019-02-19 | 036909C-JVD-TRN-00886 | 036909C-JVD-TRN-00886, ROC-TPSK-CECO-T-00003 | IFA | 2019-03-06 | 2019-03-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00886 |  | 2019-02-19 | 1
036909C-1056-PDS-0900-5621 | Process Equipment Datasheet - 10-P-5621 - Olefins Holding Basin Skimmed Oil Pump | C | 2019-03-09 | IFD | OL1-2G30-5621 | PE | 2019-03-11 | 036909C-JVD-TRN-01022 | 036909C-JVD-TRN-01022 | IFR | 2019-03-26 | 2019-03-27 | R1-No comments | TPSK-LSPA1-T-PE-01022 |  | 2019-03-12 | 2
036909C-102D-DW-1743-0023 | Foundation For 10-D-2860 | A | 2019-01-24 | IFR | OL1-2K34-0115 | CV | 2019-01-28 | 036909C-JVD-TRN-00734 | 036909C-JVD-TRN-00734, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-12 | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00734 |  | 2019-01-28 | 2
036909C-102D-DW-1743-0013 | Foundation For 10-D-2815 | A | 2019-01-23 | IFR | OL1-2K34-0105 | CV | 2019-01-28 | 036909C-JVD-TRN-00734 | 036909C-JVD-TRN-00734, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-12 | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00734 |  | 2019-01-28 | 2
036909C-102A-DW-1743-0009 | Foundation For 10-D-2160 | A | 2019-01-23 | IFR | OL1-2K34-0016 | CV | 2019-01-28 | 036909C-JVD-TRN-00734 | 036909C-JVD-TRN-00734, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-12 | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00734 |  | 2019-01-28 | 2
036909C-1056-PDS-0200-5646 | Process Equipment Datasheet - 10-PIT-5606 - C3 Hydrog Area Oily Wastewater Sump | B | 2019-02-06 | IFD | OL1-2G30-5646 | PE | 2019-02-07 | 036909C-JVD-TRN-00819 | 036909C-JVD-TRN-00819 | IFI |  | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00819 |  | 2019-02-07 | 2
036909C-1056-PDS-0200-5604 | Process Equipment Datasheet - 10-PIT-5604 - Refrig Area Oily Wastewater Sump | B | 2019-02-06 | IFD | OL1-2G30-5604 | PE | 2019-02-07 | 036909C-JVD-TRN-00819 | 036909C-JVD-TRN-00819 | IFI |  | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00819 |  | 2019-02-07 | 2
036909C-1056-PDS-0200-5603 | Process Equipment Datasheet - 10-PIT-5603 - CGC Area Oily Wastewater Sump | B | 2019-02-06 | IFD | OL1-2G30-5603 | PE | 2019-02-07 | 036909C-JVD-TRN-00819 | 036909C-JVD-TRN-00819 | IFI |  | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00819 |  | 2019-02-07 | 2
036909C-1056-PDS-0200-5602 | Process Equipment Datasheet - 10-PIT-5602 - QW Area Oily Wastewater Sump | B | 2019-02-06 | IFD | OL1-2G30-5602 | PE | 2019-02-07 | 036909C-JVD-TRN-00819 | 036909C-JVD-TRN-00819 | IFI |  | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00819 |  | 2019-02-07 | 2
036909C-1056-PDS-0200-5601 | Process Equipment Datasheet - 10-PIT-5601 - Butadiene Area Oily Wastewater Sump | B | 2019-02-06 | IFD | OL1-2G30-5601 | PE | 2019-02-07 | 036909C-JVD-TRN-00819 | 036909C-JVD-TRN-00819 | IFI |  | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00819 |  | 2019-02-07 | 2
036909C-1056-PDS-0200-5632 | Process Equipment Datasheet - 10-PIT-5632 - HP Flare Area Oily WW Sump | B | 2019-02-07 | IFD | OL1-2G30-5632 | PE | 2019-02-11 | 036909C-JVD-TRN-00838 | 036909C-JVD-TRN-00838 | IFI |  | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00838 |  | 2019-02-11 | 2
036909C-1056-PDS-0200-5631 | Process Equipment Datasheet - 10-PIT-5631 - CWWT Area Oily Wastewater Sump | B | 2019-02-07 | IFD | OL1-2G30-5631 | PE | 2019-02-11 | 036909C-JVD-TRN-00838 | 036909C-JVD-TRN-00838 | IFI |  | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00838 |  | 2019-02-11 | 2
036909C-1056-PDS-0200-5630 | Process Equipment Datasheet - 10-PIT-5630 - CT Area Oily Wastewater Sump | B | 2019-02-07 | IFD | OL1-2G30-5630 | PE | 2019-02-11 | 036909C-JVD-TRN-00838 | 036909C-JVD-TRN-00838 | IFI |  | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00838 |  | 2019-02-11 | 2
036909C-1056-PDS-0200-5600 | Process Equipment Datahseet - 10-PIT-5600 - Pygas Area Oily Wastewater Sump | B | 2019-02-07 | IFD | OL1-2G30-5600 | PE | 2019-02-11 | 036909C-JVD-TRN-00838 | 036909C-JVD-TRN-00838 | IFI |  | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00838 |  | 2019-02-11 | 2
036909C-102D-DW-1743-0031 | Foundation for 10-E-2502 | A | 2019-01-17 | IFR | OL1-2K34-0124 | CV | 2019-01-28 | 036909C-JVD-TRN-00728 | 036909C-JVD-TRN-00728, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-11 | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00728 |  | 2019-01-28 | 2
036909C-102D-DW-1743-0022 | Foundation For 10-D-2870 | A | 2019-01-22 | IFR | OL1-2K34-0114 | CV | 2019-01-28 | 036909C-JVD-TRN-00728 | 036909C-JVD-TRN-00728, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-11 | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00728 |  | 2019-01-28 | 2
036909C-102D-DW-1743-0010 | Foundation for 10-T-2520/10-D-2520 | A | 2019-01-23 | IFR | OL1-2K34-0099 | CV | 2019-01-28 | 036909C-JVD-TRN-00728 | 036909C-JVD-TRN-00728, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-11 | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00728 |  | 2019-01-28 | 2
036909C-102A-DW-1743-0035 | Foundation for 10-D-5140 | A | 2019-01-22 | IFR | OL1-2K34-0306 | CV | 2019-01-28 | 036909C-JVD-TRN-00728 | 036909C-JVD-TRN-00728, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-11 | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00728 |  | 2019-01-28 | 2
036909C-102D-DW-1743-0016 | Foundation For 10-D-2645 | A | 2019-02-05 | IFR | OL1-2K34-0108 | CV | 2019-02-06 | 036909C-JVD-TRN-00807 | 036909C-JVD-TRN-00807, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-20 | 2019-03-18 | R2-Comments as noted | TPSK-LSPA1-T-CV-00807 |  | 2019-02-06 | 2
036909C-102D-DW-1743-0044 | Foundation For 10-E-2504 | A | 2019-01-25 | IFR | OL1-2K34-0140 | CV | 2019-01-30 | 036909C-JVD-TRN-00763 | 036909C-JVD-TRN-00763, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-15 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00763 |  | 2019-01-31 | 2
036909C-102D-DW-1743-0035 | Foundation For 10-E-2545 | A | 2019-01-25 | IFR | OL1-2K34-0128 | CV | 2019-01-30 | 036909C-JVD-TRN-00763 | 036909C-JVD-TRN-00763, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-15 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00763 |  | 2019-01-31 | 2
036909C-102B-DW-1743-0006 | Foundation For 10-D-2316 | A | 2019-01-28 | IFR | OL1-2K34-0057 | CV | 2019-02-06 | 036909C-JVD-TRN-00807 | 036909C-JVD-TRN-00807, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-20 | 2019-03-18 | R2-Comments as noted | TPSK-LSPA1-T-CV-00807 |  | 2019-02-06 | 2
036909C-102B-DW-1743-0008 | Foundation For 10-D-2330 | A | 2019-01-28 | IFR | OL1-2K34-0059 | CV | 2019-02-06 | 036909C-JVD-TRN-00807 | 036909C-JVD-TRN-00807, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-20 | 2019-03-18 | R2-Comments as noted | TPSK-LSPA1-T-CV-00807 |  | 2019-02-06 | 2
036909C-102B-DW-1743-0012 | Foundation For 10-D-2305 | A | 2019-02-05 | IFR | OL1-2K34-0074 | CV | 2019-02-08 | 036909C-JVD-TRN-00826 | 036909C-JVD-TRN-00826, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-25 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00826 |  | 2019-02-08 | 2
036909C-102A-DW-1743-0020 | Foundation For 10-E-2048 | A | 2019-02-04 | IFR | OL1-2K34-0027 | CV | 2019-02-06 | 036909C-JVD-TRN-00807 | 036909C-JVD-TRN-00807, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-20 | 2019-03-18 | R2-Comments as noted | TPSK-LSPA1-T-CV-00807 |  | 2019-02-06 | 2
036909C-102B-DW-1743-0004 | Foundation For 10-D-2310 | A | 2019-02-05 | IFR | OL1-2K34-0055 | CV | 2019-02-08 | 036909C-JVD-TRN-00826 | 036909C-JVD-TRN-00826, ROC-TPSK-CECO-T-00023 | IFR | 2019-02-25 | 2019-02-27 | R2-Comments as noted | TPSK-LSPA1-T-CV-00826 |  | 2019-02-08 | 2
036909C-102D-CN-1733-0013 | Calculation Note for Foundation of 10-D-2645 | A | 2019-02-01 | IFR | OL1-2K13-0101 | CV | 2019-02-07 | 036909C-JVD-TRN-00816 | 036909C-JVD-TRN-00816, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-22 | 2019-03-18 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00816 |  | 2019-02-07 | 1
036909C-102A-CN-1733-0029 | Calculation Note For Foundation Of 10-E-2008A-B-C-D-E | A | 2019-02-05 | IFR | OL1-2K13-0182 | CV | 2019-02-12 | 036909C-JVD-TRN-00843 | 036909C-JVD-TRN-00843, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-27 | 2019-02-27 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00843 |  | 2019-02-12 | 1
036909C-102D-CN-1733-0023 | Calculation Note for Foundation of 10-E-2857 | A | 2019-02-04 | IFR | OL1-2K13-0125 | CV | 2019-02-07 | 036909C-JVD-TRN-00816 | 036909C-JVD-TRN-00816, ROC-TPSK-CECO-T-00024 | IFA | 2019-02-22 | 2019-03-18 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-CV-00816 |  | 2019-02-07 | 1
036909C-1056-PDS-0200-5633 | Process Equipment Datasheet - 10-PIT-5633 - HP Flare Area Stormwater Sump | B | 2019-02-28 | IFD | OL1-2G30-5633 | PE | 2019-03-01 | 036909C-JVD-TRN-00960 | 036909C-JVD-TRN-00960, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-16 | 2019-03-14 | R1-No comments | TPSK-LSPA1-T-PE-00960 |  | 2019-03-04 | 2
036909C-1051-PDS-0200-5115 | Process Equipment Datasheet - 10-PK-5115 - Condensate Carbon Filter Pkg | B | 2019-01-29 | IFD | OL1-2G30-5115 | PE | 2019-01-31 | 036909C-JVD-TRN-00778 | 036909C-JVD-TRN-00778, ROC-TPSK-CECO-T-00020 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00778 |  | 2019-02-01 | 2
036909C-1053-PDS-0300-5370 | Process Equipment Datasheet - 10-PIT-5370 - CW Filter Backwash Sump | B | 2019-01-31 | IFD | OL1-2G30-5370 | PE | 2019-02-01 | 036909C-JVD-TRN-00791 | 036909C-JVD-TRN-00791, ROC-TPSK-CECO-T-00020 | IFI |  | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00791 |  | 2019-02-04 | 2
036909C-1051-PDS-0200-5125 | Process Equipment Datasheet - 10-PK-5125 - Condensate Polisher Pkg | B | 2019-01-29 | IFD | OL1-2G30-5125 | PE | 2019-01-31 | 036909C-JVD-TRN-00778 | 036909C-JVD-TRN-00778, ROC-TPSK-CECO-T-00020 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00778 |  | 2019-02-01 | 2
036909C-1000-JSD-1400-0001 | Job Design Specification For Underground Systems | 0 | 2019-03-04 | IMP | OL1-2R02-0001 | CV | 2019-03-06 | 036909C-JVD-TRN-00994 | 036909C-JVD-TRN-00994, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-03-21 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-CV-00994 |  | 2019-03-07 | 2
036909C-1012-PDS-1542-1213 | Process Equipment Datasheet - 10-X-1200_1600 A-F - USC 132U Dilution Steam Mixing Tee | B | 2019-02-25 | IFD | OL1-2G30-1213 | PE | 2019-02-26 | 036909C-JVD-TRN-00936 | 036909C-JVD-TRN-00936, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-PE-00936 |  | 2019-02-27 | 2
036909C-1012-PDS-0811-1207 | Process Equipment Datasheet - 10-D-1200_1600 - USC 132U Cracking Furnace Steam Drum | C | 2019-02-26 | IFD | OL1-2G30-1207 | PE | 2019-02-26 | 036909C-JVD-TRN-00935 | 036909C-JVD-TRN-00935, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-PE-00935 |  | 2019-02-27 | 2
036909C-1011-PDS-0811-1107 | Process Equipment Datasheet - 10-D-1100 - USC 36M Cracking Furnace Steam Drum | C | 2019-02-26 | IFD | OL1-2G30-1107 | PE | 2019-02-26 | 036909C-JVD-TRN-00935 | 036909C-JVD-TRN-00935, ROC-TPSK-CECO-T-00019 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-PE-00935 |  | 2019-02-27 | 2
036909C-1056-SP-0910-5616 | Mechanical Equipment Datasheet - Olefins Stormwater Sump Pumps | B | 2019-02-11 | IFQ | OL1-2M03-5616 | ME | 2019-03-01 | 036909C-JVD-TRN-00962 | 036909C-JVD-TRN-00962, ROC-TPSK-CECO-T-00016 | IFR | 2019-03-16 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00962 |  | 2019-03-04 | 2
036909C-1023-SP-0910-2325 | Mechanical Equipment Datasheet - 10 percent Caustic Makeup Pumps | B | 2019-01-31 | IFQ | OL1-2M03-2325 | ME | 2019-02-07 | 036909C-JVD-TRN-00822 | 036909C-JVD-TRN-00822, ROC-TPSK-CECO-T-00014 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00822 |  | 2019-02-07 | 2
036909C-1020-SP-0910-2024 | Mechanical Equipment Datasheet - Light Fuel Oil Pumps | B | 2019-01-22 | IFQ | OL1-2M03-2024 | ME | 2019-02-01 | 036909C-JVD-TRN-00786 | 036909C-JVD-TRN-00786, ROC-TPSK-CECO-T-00014 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00786 |  | 2019-02-04 | 2
036909C-1019-PDS-0900-1913 | Process Equipment Datasheet - 10-P-1910 A-B - DMDS Feed Injection Pump | B | 2019-02-28 | IFD | OL1-2G30-1913 | PE | 2019-03-01 | 036909C-JVD-TRN-00963 | 036909C-JVD-TRN-00963 | IFR | 2019-03-16 | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-PE-00963 |  | 2019-03-04 | 2
036909C-1030-PDS-1000-3073 | Process Equipment Data Sheet - 10-C-3070 - BDU Recycle Gas Compressor | B | 2019-01-15 | IFD | OL1-2G30-3073 | PE | 2019-01-18 | 036909C-JVD-TRN-00675 | 036909C-JVD-TRN-00675 | IFI |  | 2019-03-21 | R1-No comments | TPSK-LSPA1-T-PE-00675 |  | 2019-01-18 | 2
036909C-1000-QCP-6871-0001 | Quality Control Plan Air Coolers Installation | A | 2019-03-18 | IFR | OL1-2Q23-0018 | QM | 2019-03-19 | 036909C-JVD-TRN-01091 | 036909C-JVD-TRN-01091 | IFA | 2019-04-03 |  | Transmitted | TPSK-LSPA1-T-QM-01091 |  | 2019-03-20 | 1
036909C-1026-PDS-0900-2669 | Process Equipment Datasheet - 10-P-2665 A-B - Debutanizer Bottoms Pumps | B | 2019-01-10 | IFD | OL1-2G30-2669 | PE | 2019-01-14 | 036909C-JVD-TRN-00648 | 036909C-JVD-TRN-00648 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00648 |  | 2019-01-14 | 2
036909C-1056-PDS-0900-5606 | Process Equipment Datasheet - 10-P-5600 A-B - Pygas Area Oily Wastewater Pump | B | 2019-01-29 | IFD | OL1-2G30-5606 | PE | 2019-01-31 | 036909C-JVD-TRN-00779 | 036909C-JVD-TRN-00779 | IFI |  | 2019-03-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00779 |  | 2019-02-01 | 2
036909C-1054-PDS-0800-5400 | Process Equipment Datasheet - 10-D-5400 - Instrument Air Receiver | B | 2019-01-29 | IFD | OL1-2G30-5400 | PE | 2019-02-06 | 036909C-JVD-TRN-00800 | 036909C-JVD-TRN-00800 | IFI |  | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00800 |  | 2019-02-06 | 2
036909C-1055-PDS-1000-5522 | Process Equipment Datasheet - 10-C-5520 A-B - LP Vent Blowers | B | 2019-01-29 | IFD | OL1-2G30-5522 | PE | 2019-02-11 | 036909C-JVD-TRN-00837 | 036909C-JVD-TRN-00837 | IFI |  | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00837 |  | 2019-02-11 | 2
036909C-1026-PDS-0800-2644 | Process Equipment Datasheet - 10-D-2645 - C3 Tower Reboiler Cond Pot | B | 2019-02-01 | IFD | OL1-2G30-2644 | PE | 2019-02-01 | 036909C-JVD-TRN-00796 | 036909C-JVD-TRN-00796 | IFI |  | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00796 |  | 2019-02-04 | 2
036909C-1023-PDS-0840-2307 | Process Equipment Datasheet - 10-F-2306 A-B - Weak Caustic Circulating Filters | C | 2019-01-29 | IFD | OL1-2G30-2307 | PE | 2019-01-30 | 036909C-JVD-TRN-00775 | 036909C-JVD-TRN-00775 | IFI |  | 2019-02-28 | R1-No comments | TPSK-LSPA1-T-PE-00775 |  | 2019-01-31 | 2
036909C-1012-TBT-0133-2008 | Technical Bid Tabulation for Peep Doors | 0 | 2019-02-04 | IFI | OL1-2Y23-2008 | ME | 2019-02-06 | 036909C-JVD-TRN-00813 | 036909C-JVD-TRN-00813 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00813 |  | 2019-02-06 | 3
036909C-1000-JSD-1300-0010 | JSD For Auxiliary Piping Supports | B | 2019-02-04 | IFR | OL1-2R04-0034 | MP | 2019-02-08 | 036909C-JVD-TRN-00830 | 036909C-JVD-TRN-00830 | IFR | 2019-02-25 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-MP-00830 |  | 2019-02-08 | 2
036909C-1000-JSD-1300-0003 | A1 Scope Annex C– Ppiping Specification PIP-006 Steam Tracing Piping | 0 | 2019-01-25 | IMP | OL1-2R04-0031 | MP | 2019-01-28 | 036909C-JVD-TRN-00736 | 036909C-JVD-TRN-00736, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-12 | 2019-03-01 | R2-Comments as noted | TPSK-LSPA1-T-MP-00736 |  | 2019-01-28 | 2
036909C-1000-DW-1402-0001 | General Notes For Underground Works | 0 | 2019-01-30 | IFC | OL1-2K92-0001 | CV | 2019-02-01 | 036909C-JVD-TRN-00784 | 036909C-JVD-TRN-00784, ROC-TPSK-CECO-T-00003 | IFR | 2019-02-18 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-CV-00784 |  | 2019-02-01 | 2
036909C-1024-PDS-0800-2420 | Process Equipment Datasheet - 10-D-2420 A-B - CG Liquid Dryer | B | 2019-01-04 | IFD | OL1-2G30-2420 | PE | 2019-01-08 | 036909C-JVD-TRN-00610 | 036909C-JVD-TRN-00610 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00610 |  | 2019-01-08 | 2
036909C-1024-PDS-0800-2411 | Process Equipment Datasheet - 10-D-2411 - Cracked Gas Mercury Adsorber | B | 2019-01-04 | IFD | OL1-2G30-2411 | PE | 2019-01-08 | 036909C-JVD-TRN-00610 | 036909C-JVD-TRN-00610 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00610 |  | 2019-01-08 | 2
036909C-1012-MR-0126-2012 | Material Requisition for Furnace Convection Finnings | 0 | 2019-03-07 | IFP | OL1-2C13-281000 | PL | 2019-03-15 | 036909C-JVD-TRN-01085 | 036909C-JVD-TRN-01085 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01085 |  | 2019-03-18 | 3
036909C-1012-MR-0126-2012 | Material Requisition for Furnace Convection Finnings | A | 2019-01-16 | IFQ | OL1-2C13-281000 | PL | 2019-01-23 | 036909C-JVD-TRN-00713 | 036909C-JVD-TRN-00713 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00713 |  | 2019-01-23 | 3
036909C-1023-PDS-2500-2324 | Process Equipment Datasheet - 10-TK-2300 - Fresh Caustic Day Tank | C | 2019-02-26 | IFD | OL1-2G30-2324 | PE | 2019-02-26 | 036909C-JVD-TRN-00937 | 036909C-JVD-TRN-00937 | IFR | 2019-03-13 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-PE-00937 |  | 2019-02-27 | 2
036909C-1023-PDS-0600-2326 | Process Equipment Datasheet - 10-E-2326 - Spent Caustic Stripper Feed Heater | B | 2019-01-17 | IFD | OL1-2G30-2326 | PE | 2019-01-22 | 036909C-JVD-TRN-00690 | 036909C-JVD-TRN-00690 | IFI |  | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00690 |  | 2019-01-22 | 2
036909C-1012-TBT-0122-2012 | Technical Bid Tabulation for Convection Tubes Finnings | 0 | 2019-03-06 | IFI | OL1-2C23-281000 | PL | 2019-03-13 | 036909C-JVD-TRN-01048 | 036909C-JVD-TRN-01048 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01048 |  | 2019-03-14 | 3
036909C-1026-PDS-0800-2600 | Process Equipment Datasheet - 10-D-2600 A-B - C3 Hydrog Guard Adsorber | B | 2019-01-08 | IFD | OL1-2G30-2600 | PE | 2019-01-10 | 036909C-JVD-TRN-00618 | 036909C-JVD-TRN-00618 | IFI |  | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00618 |  | 2019-01-10 | 2
036909C-1000-JSD-1580-0001 | Integrated Turbine And Compressor Control System | 0 | 2018-12-14 | IMP | OL1-2R06-0017 | IE | 2018-12-17 | 036909C-JVD-TRN-00507 | 036909C-JVD-TRN-00507, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-28 | 2018-12-26 | R1-No comments | TPSK-LSPA1-T-IE-00507 |  | 2018-12-17 | 2
036909C-1000-JSD-1600-0006 | Protective Relay And Control Unit | 0 | 2018-12-13 | IMP | OL1-2R05-0004 | EE | 2018-12-20 | 036909C-JVD-TRN-00522 | 036909C-JVD-TRN-00522, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00522 |  | 2018-12-20 | 3
036909C-1000-QCP-6860-0001 | Quality Control Plan Equipment Internals Installation - Trays | A | 2019-03-04 | IFR | OL1-2Q23-0016 | QM | 2019-03-08 | 036909C-JVD-TRN-01011 | 036909C-JVD-TRN-01011 | IFA | 2019-03-25 |  | Transmitted | TPSK-LSPA1-T-QM-01011 |  | 2019-03-11 | 1
036909C-1010-PDS-0600-1020 | Process Equipment Datasheet - 10-E-1020 - Liquid Feed Heater | C | 2019-01-16 | IFD | OL1-2G30-1020 | PE | 2019-01-18 | 036909C-JVD-TRN-00680 | 036909C-JVD-TRN-00680 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00680 |  | 2019-01-18 | 2
036909C-1051-PDS-0800-5140 | Process Equipment Datasheet - 10-D-5140 - Intermittent Blowdown Drum | B | 2018-12-13 | IFD | OL1-2G30-5140 | PE | 2018-12-14 | 036909C-JVD-TRN-00504 | 036909C-JVD-TRN-00504 | IFI |  | 2019-01-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00504 |  | 2018-12-14 | 2
036909C-1023-PDS-0900-2391 | Process Equipment Datasheet - 10-P-2390 - Caustic Drain Drum Pump | B | 2019-01-18 | IFD | OL1-2G30-2391 | PE | 2019-01-22 | 036909C-JVD-TRN-00695 | 036909C-JVD-TRN-00695 | IFI |  | 2019-03-05 | R1-No comments | TPSK-LSPA1-T-PE-00695 |  | 2019-01-22 | 2
036909C-1021-PDS-0800-2110 | Process Equipment Datasheet - 10-D-2110 - Interception Drum | B | 2019-01-16 | IFD | OL1-2G30-2110 | PE | 2019-01-18 | 036909C-JVD-TRN-00678 | 036909C-JVD-TRN-00678 | IFI |  | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-00678 |  | 2019-01-18 | 2
036909C-1000-QCP-2520-0002 | Quality Control Plan Floating Roof Tanks Erection | A | 2019-02-19 | IFR | OL1-2Q23-0002 | QM | 2019-02-27 | 036909C-JVD-TRN-00942 | 036909C-JVD-TRN-00942 | IFA | 2019-03-14 |  | Transmitted | TPSK-LSPA1-T-QM-00942 |  | 2019-02-28 | 1
036909C-1000-QCP-2520-0001 | Quality Control Plan Fixed Roof Tanks Erection | A | 2019-02-19 | IFR | OL1-2Q23-0001 | QM | 2019-02-27 | 036909C-JVD-TRN-00942 | 036909C-JVD-TRN-00942 | IFA | 2019-03-14 |  | Transmitted | TPSK-LSPA1-T-QM-00942 |  | 2019-02-28 | 1
036909C-1023-PDS-2500-2324 | Process Equipment Datasheet - 10-TK-2300 - Fresh Caustic Day Tank | B | 2019-01-29 | IFD | OL1-2G30-2324 | PE | 2019-01-29 | 036909C-JVD-TRN-00760 | 036909C-JVD-TRN-00760 | IFI |  | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00760 |  | 2019-01-29 | 2
036909C-1024-PDS-0800-2460 | Process Equipment Datasheet - 10-D-2460 - C2 Hydrog Arsine Guard Bed | B | 2019-01-14 | IFD | OL1-2G30-2460 | PE | 2019-01-16 | 036909C-JVD-TRN-00660 | 036909C-JVD-TRN-00660 | IFI |  | 2019-01-29 | R1-No comments | TPSK-LSPA1-T-PE-00660 |  | 2019-01-16 | 2
036909C-1026-PDS-0800-2610 | Process Equipment Datasheet - 10-D-2610 - C3 Hydrog Arsine Guard Bed | B | 2019-01-08 | IFD | OL1-2G30-2610 | PE | 2019-01-10 | 036909C-JVD-TRN-00618 | 036909C-JVD-TRN-00618 | IFI |  | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00618 |  | 2019-01-10 | 2
036909C-1024-PDS-0800-2480 | Process Equipment Datasheet - 10-D-2480 - CG Secondary Dryer | B | 2019-01-10 | IFD | OL1-2G30-2480 | PE | 2019-01-11 | 036909C-JVD-TRN-00637 | 036909C-JVD-TRN-00637 | IFI |  | 2019-01-31 | R1-No comments | TPSK-LSPA1-T-PE-00637 |  | 2019-01-11 | 2
036909C-1024-PDS-0400-2470 | Process Equipment Datasheet - 10-R-2470 A-C - C2 Hydrog Reactor | B | 2019-01-04 | IFD | OL1-2G30-2470 | PE | 2019-01-08 | 036909C-JVD-TRN-00609 | 036909C-JVD-TRN-00609 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00609 |  | 2019-01-08 | 2
036909C-1029-PDS-2500-2910 | Process Equipment Datasheet - 10-TK-2910 - Wash Oil Day Tank | B | 2019-01-29 | IFD | OL1-2G30-2910 | PE | 2019-01-29 | 036909C-JVD-TRN-00760 | 036909C-JVD-TRN-00760 | IFI |  | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00760 |  | 2019-01-29 | 2
036909C-1020-PDS-0600-2015 | Process Equipment Datasheet - 10-E-2008 A-C - LS2 Steam Generators | B | 2019-01-09 | IFD | OL1-2G30-2015 | PE | 2019-01-11 | 036909C-JVD-TRN-00632 | 036909C-JVD-TRN-00632 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00632 |  | 2019-01-11 | 2
036909C-1012-TBT-0127-2002 | Technical Bid Tabulation for Convection Fittings | 1 | 2019-01-07 | IFI | OL1-2Y23-2002 | PC | 2019-01-07 | 036909C-JVD-TRN-00591 | 036909C-JVD-TRN-00591 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PC-00591 |  | 2019-01-07 | 3
036909C-1028-PDS-0900-2855 | Process Equipment Datasheet - 10-P-2855 A-B - Ethylene Product Pumps | B | 2019-01-10 | IFD | OL1-2G30-2855 | PE | 2019-01-14 | 036909C-JVD-TRN-00648 | 036909C-JVD-TRN-00648 | IFI |  | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00648 |  | 2019-01-14 | 2
036909C-1024-PDS-0600-2474 | Process Equipment Datasheet - 10-E-2474 - C2 Hydrog Aftercooler | B | 2019-01-07 | IFD | OL1-2G30-2474 | PE | 2019-01-07 | 036909C-JVD-TRN-00602 | 036909C-JVD-TRN-00602 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00602 |  | 2019-01-07 | 2
036909C-1024-PDS-0600-2472 | Process Equipment Datasheet - 10-E-2472 - C2 Hydrog 2nd Stage Intercooler | B | 2019-01-07 | IFD | OL1-2G30-2472 | PE | 2019-01-07 | 036909C-JVD-TRN-00602 | 036909C-JVD-TRN-00602 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00602 |  | 2019-01-07 | 2
036909C-1024-PDS-0600-2465 | Process Equipment Datasheet - 10-E-2465 - C2 Hydrog Feed Heater | B | 2019-01-07 | IFD | OL1-2G30-2465 | PE | 2019-01-07 | 036909C-JVD-TRN-00602 | 036909C-JVD-TRN-00602 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00602 |  | 2019-01-07 | 2
036909C-1024-PDS-0600-2471 | Process Equipment Datasheet - 10-E-2470 - C2 Hydrog 1st Stage Intercooler | B | 2019-01-07 | IFD | OL1-2G30-2471 | PE | 2019-01-07 | 036909C-JVD-TRN-00602 | 036909C-JVD-TRN-00602 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00602 |  | 2019-01-07 | 2
036909C-1012-TBT-0127-2002 | Technical Bid Tabulation for Convection Fittings | 0 | 2018-12-19 | IFI | OL1-2Y23-2002 | ME | 2018-12-20 | 036909C-JVD-TRN-00545 | 036909C-JVD-TRN-00545 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00545 |  | 2018-12-20 | 3
036909C-1024-PDS-0900-2453 | Process Equipment Datasheet - 10-P-2450 A-B - LP Depropanizer Reflux-Product Pump | B | 2019-01-04 | IFD | OL1-2G30-2453 | PE | 2019-01-07 | 036909C-JVD-TRN-00593 | 036909C-JVD-TRN-00593 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00593 |  | 2019-01-07 | 2
036909C-1024-PDS-0900-2416 | Process Equipment Datasheet - 10-P-2415 A-B - CG Liquid Dryer Feed Pumps | B | 2019-01-04 | IFD | OL1-2G30-2416 | PE | 2019-01-07 | 036909C-JVD-TRN-00593 | 036909C-JVD-TRN-00593 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00593 |  | 2019-01-07 | 2
036909C-1012-TBT-0125-2007 | Technical Bid Tabulation for Cast Intermediate Tube Supports | 0 | 2018-12-11 | IFI | OL1-2Y23-2007 | ME | 2018-12-17 | 036909C-JVD-TRN-00519 | 036909C-JVD-TRN-00519 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00519 |  | 2018-12-17 | 3
036909C-1012-TBT-0155-2018 | Technical Bid Tabulation for Furnace Steam Drums | 0 | 2018-12-10 | IFI | OL1-2Y23-2018 | ME | 2018-12-14 | 036909C-JVD-TRN-00500 | 036909C-JVD-TRN-00500 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00500 |  | 2018-12-14 | 3
036909C-1025-PDS-0600-2502 | Process Equipment Datasheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | C | 2018-12-07 | IFD | OL1-2G30-2502 | PE | 2018-12-11 | 036909C-JVD-TRN-00475 | 036909C-JVD-TRN-00475 | IFI |  | 2019-01-10 | A1-Approved without comments | TPSK-LSPA1-T-PE-00475 |  | 2018-12-11 | 1
036909C-1021-PDS-0600-2137 | Process Equipment Datasheet - 10-E-2136 - Process Water Stripper Feed Heater | B | 2018-12-07 | IFD | OL1-2G30-2137 | PE | 2018-12-10 | 036909C-JVD-TRN-00467 | 036909C-JVD-TRN-00467 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00467 |  | 2018-12-10 | 2
036909C-1000-SP-1692-0001 | Particular Technical Specification for Medium Voltage Motors Medium Voltage Variable Voltage Variable Frequency System | A | 2018-12-14 | IFQ | OL1-2E57-4100 | EE | 2018-12-20 | 036909C-JVD-TRN-00540 | 036909C-JVD-TRN-00540 | IFR | 2018-12-19 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-EE-00540 |  | 2018-12-20 | 2
036909C-1000-SR-1692-0001 | Scope Of Supply For Medium Voltage Motors Medium Voltage Variable Voltage Variable Frequency System | A | 2018-12-14 | IFQ | OL1-2E56-4100 | EE | 2018-12-20 | 036909C-JVD-TRN-00540 | 036909C-JVD-TRN-00540 | IFR | 2018-12-19 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-EE-00540 |  | 2018-12-20 | 2
036909C-1000-MR-1692-0001 | Material Requisition For Medium Voltage Motors Medium Voltage Variable Voltage Variable Frequency System | A | 2018-12-14 | IFQ | OL1-2E55-4100 | EE | 2018-12-20 | 036909C-JVD-TRN-00540 | 036909C-JVD-TRN-00540 | IFR | 2018-12-19 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-EE-00540 |  | 2018-12-20 | 2
036909C-1000-SP-1661-0001 | Particular Technical Specification for Substation Monitoring & Control System (SMCS) | A | 2018-12-14 | IFQ | OL1-2E57-1800 | EE | 2018-12-17 | 036909C-JVD-TRN-00510 | 036909C-JVD-TRN-00510 | IFR | 2018-12-31 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00510 |  | 2018-12-17 | 2
036909C-1000-SR-1661-0001 | Scope of Supply for Substation Monitoring & Control System (SMCS) | A | 2018-12-14 | IFQ | OL1-2E56-1800 | EE | 2018-12-17 | 036909C-JVD-TRN-00510 | 036909C-JVD-TRN-00510 | IFR | 2018-12-31 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00510 |  | 2018-12-17 | 2
036909C-1000-MR-1661-0001 | Material Requisition for Substation Monitoring & Control System (SMCS) | A | 2018-12-14 | IFQ | OL1-2E55-1800 | EE | 2018-12-17 | 036909C-JVD-TRN-00510 | 036909C-JVD-TRN-00510 | IFR | 2018-12-31 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00510 |  | 2018-12-17 | 2
036909C-1000-SP-1654-0001 | Particular Technical Specification for Low Voltage Switchgears/MCCs & Busducts | A | 2018-12-11 | IFQ | OL1-2E57-1200 | EE | 2018-12-14 | 036909C-JVD-TRN-00497 | 036909C-JVD-TRN-00497 | IFR | 2018-12-27 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00497 |  | 2018-12-14 | 2
036909C-1000-SR-1654-0001 | Scope of Supply for Low Voltage Switchgears/MCCs & Busducts | A | 2018-12-11 | IFQ | OL1-2E56-1200 | EE | 2018-12-14 | 036909C-JVD-TRN-00497 | 036909C-JVD-TRN-00497 | IFR | 2018-12-27 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00497 |  | 2018-12-14 | 2
036909C-1000-MR-1654-0001 | Material Requisition for Low Voltage Switchgears/MCCs & Busducts | A | 2018-12-11 | IFQ | OL1-2E55-1200 | EE | 2018-12-14 | 036909C-JVD-TRN-00497 | 036909C-JVD-TRN-00497 | IFR | 2018-12-27 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00497 |  | 2018-12-14 | 2
036909C-1000-SP-1655-1400 | Typical Data Sheet for Low Voltage Bus Ducts | A | 2018-12-11 | IFQ | CL1-2E05-1400 | EE | 2018-12-14 | 036909C-JVD-TRN-00497 | 036909C-JVD-TRN-00497 | IFR | 2018-12-27 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-EE-00497 |  | 2018-12-14 | 2
036909C-1000-SP-1654-1200 | Typical Data Sheet for Low Voltage Switchgears/MCCs | A | 2018-12-11 | IFQ | CL1-2E05-1200 | EE | 2018-12-14 | 036909C-JVD-TRN-00497 | 036909C-JVD-TRN-00497 | IFR | 2018-12-27 | 2019-01-07 | R1-No comments | TPSK-LSPA1-T-EE-00497 |  | 2018-12-14 | 2
036909C-1000-SR-1652-0001 | Scope of Supply for Medium Voltage Switchgears | A | 2018-12-07 | IFQ | OL1-2E56-1100 | EE | 2018-12-11 | 036909C-JVD-TRN-00477 | 036909C-JVD-TRN-00477 | IFR | 2018-12-25 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-ME-00476 |  | 2018-12-11 | 2
036909C-1000-SP-1652-1100 | Typical Data Sheet for Medium Voltage Switchgears | A | 2018-12-07 | IFQ | OL1-2E05-1100 | EE | 2018-12-11 | 036909C-JVD-TRN-00477 | 036909C-JVD-TRN-00477 | IFR | 2018-12-25 | 2019-01-07 | R1-No comments | TPSK-LSPA1-T-ME-00476 |  | 2018-12-11 | 2
036909C-1000-MR-1652-0001 | Material Requisition for Medium Voltage Switchgears | A | 2018-12-07 | IFQ | OL1-2E55-1100 | EE | 2018-12-11 | 036909C-JVD-TRN-00477 | 036909C-JVD-TRN-00477 | IFR | 2018-12-25 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-ME-00476 |  | 2018-12-11 | 2
036909C-1000-SP-1652-0001 | Particular Technical Specification for Medium Voltage Switchgears | A | 2018-12-07 | IFQ | OL1-2E57-1100 | EE | 2018-12-11 | 036909C-JVD-TRN-00477 | 036909C-JVD-TRN-00477 | IFR | 2018-12-25 | 2019-01-07 | R2-Comments as noted | TPSK-LSPA1-T-ME-00476 |  | 2018-12-11 | 2
036909C-1000-SP-1692-4100 | Typical Data Sheet For MV Motor | A | 2018-12-14 | IFQ | OL1-2E05-4100 | EE | 2018-12-20 | 036909C-JVD-TRN-00529 | 036909C-JVD-TRN-00529 | IFR | 2019-01-02 | 2019-01-03 | R1-No comments | TPSK-LSPA1-T-EE-00529 |  | 2018-12-20 | 2
036909C-1000-SP-1692-1700 | Typical Data Sheet For Medium Voltage Variable Voltage Variable Frequency System | A | 2018-12-14 | IFQ | OL1-2E05-1700 | EE | 2018-12-20 | 036909C-JVD-TRN-00529 | 036909C-JVD-TRN-00529 | IFR | 2019-01-02 | 2019-01-03 | R1-No comments | TPSK-LSPA1-T-EE-00529 |  | 2018-12-20 | 2
036909C-1000-PP-704 | Schedule of Construction Subcontracts and Progress Report | A | 2018-12-14 | IFI | OL1-2D92-0003 | CM | 2018-12-14 | 036909C-JVD-TRN-00506 | 036909C-JVD-TRN-00506 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CM-00506 |  | 2018-12-14 | 3
036909C-1000-NM-1990-0001 | HAZOP & SIL Classification Actions Register | A | 2019-09-03 | IFR | OL1-2L60-0002 | SE | 2019-09-05 | 036909C-JVD-TRN-02575 | 036909C-JVD-TRN-02575 | IFA | 2019-09-20 |  | Transmitted | TPSK-LSPA1-T-SE-02575 | Updated category code from L62 to L60 as per Client s request | 2019-09-10 | 2
036909C-1010-DW-1514-1001 | Cause and Effect Diagram - Area 10 - Feed Preparation and Feed Preheat | A | 2019-03-13 | IFR | OL1-2G50-1003 | IE | 2019-03-13 | 036909C-JVD-TRN-01043 | 036909C-JVD-TRN-01043, ROC-TPSK-CECO-T-00013, ROC-TPSK-CECO-T-00013_1, ROC-TPSK-CECO-T-00029 | IFR | 2019-03-28 |  | Transmitted | TPSK-LSPA1-T-IE-01043 | For next revision see Doc. N. OL1-2G50-1003 | 2019-03-14 | 2
036909C-1010-DW-1514-1001 | Cause and Effect Diagram Area 10 Feed Preparation and Feed Preheat - Ex. Client Doc. N. OL1-2I30-1001 | B | 2019-06-26 | IBD | OL1-2G50-1003 | PE | 2019-06-26 | 036909C-JVD-TRN-01999 | 036909C-JVD-TRN-01999 | IFR | 2019-07-11 | 2019-08-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-01999 | Ex. Client Doc. N. OL1-2I30-1001 | 2019-06-27 | 2
036909C-105U-DW-1741-0002-014 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Steel Bracing Details | A | 2019-08-15 | IFR | OL1-2K31-0361 | CV | 2019-08-20 | 036909C-JVD-TRN-02493 | 036909C-JVD-TRN-02493 | IFR | 2019-09-10 |  | Transmitted | IFR |  | 2019-08-27 | 2
036909C-1027-DI-0007-2702 | Area Basis of Design - Area 275 C4 C5 Hydrogenation | C | 2019-09-12 | IFD | OL1-2G05-2702 | PE | 2019-09-12 | 036909C-JVD-TRN-02638 | 036909C-JVD-TRN-02638 | IFA | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-PE-02638 |  | 2019-09-13 | 1
036909C-100P-CN-1732-0001 | Calculation Note For Foundation And Elevation Of 10-STR-0P01 | A | 2019-07-11 | IFR | OL1-2K14-0043 | CV | 2019-07-23 | 036909C-JVD-TRN-02238 | 036909C-JVD-TRN-02238 | IFA | 2019-08-07 |  | Transmitted | TPSK-LSPA1-T-CV-02238 |  | 2019-07-24 | 1
036909C-1000-MR-3400-0001 | Material Requisition for HVAC System | A | 2019-07-05 | IFQ | OL1-2C16-340000 | PL | 2019-07-08 | 036909C-JVD-TRN-02092 | 036909C-JVD-TRN-02092 | IFR | 2019-07-22 | 2019-07-23 | R2-Comments as noted | TPSK-LSPA1-T-PL-02092 |  | 2019-07-08 | 2
036909C-1000-NM-0001-1013 | Heat and Material Balance - 56 Waste Water Treatment System | 1 | 2019-02-18 | IFI | OL1-2G44-1013 | PE | 2019-02-19 | 036909C-JVD-TRN-00892 | 036909C-JVD-TRN-00892, ROC-TPSK-CECO-T-00012 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00892 |  | 2019-02-19 | 3
036909C-1000-NM-0001-1013 | Heat and Material Balance - 56 Waste Water Treatment System | A | 2019-01-02 | IFI | OL1-2G44-1013 | PE | 2019-01-03 | 036909C-JVD-TRN-00581 | 036909C-JVD-TRN-00581 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00581 |  | 2019-01-03 | 3
036909C-101A-ML-252 | Model Review Report Furnace Island Action List 60 | A | 2019-09-12 | IFR | OL1-2P30-0033 | MP | 2019-09-13 | 036909C-JVD-TRN-02642 | 036909C-JVD-TRN-02642 | IFR | 2019-09-28 |  | Transmitted | TPSK-LSPA1-T-MP-02642 |  | 2019-09-17 | 2
036909C-1059-PDS-2500-5950 | Process Equipment Datasheet - 10-TK-5950 - Sodium Hypochlorite Tank | A | 2018-11-29 | IFR | OL1-2G30-5950 | PE | 2018-12-04 | 036909C-JVD-TRN-00406 | 036909C-JVD-TRN-00406 | IFR | 2018-12-17 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00406 |  | 2018-12-04 | 2
036909C-1059-PDS-2500-5950 | Process Equipment Datasheet - 10-TK-5950 - Sodium Hypochlorite Tank | C | 2019-04-03 | IFD | OL1-2G30-5950 | PE | 2019-04-04 | 036909C-JVD-TRN-01258 | 036909C-JVD-TRN-01258 | IFR | 2019-04-19 | 2019-05-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-01258 |  | 2019-04-05 | 2
036909C-1059-PDS-2500-5950 | Process Equipment Datasheet - 10-TK-5950 - Sodium Hypochlorite Tank | B | 2019-03-13 | IFD | OL1-2G30-5950 | PE | 2019-03-14 | 036909C-JVD-TRN-01055 | 036909C-JVD-TRN-01055 | IFR | 2019-03-29 | 2019-03-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-01055 |  | 2019-03-15 | 2
036909C-1059-PDS-2500-5950 | Process Equipment Datasheet - 10-TK-5950 - Sodium Hypochlorite Tank | D | 2019-05-15 | IFD | OL1-2G30-5950 | PE | 2019-05-16 | 036909C-JVD-TRN-01679 | 036909C-JVD-TRN-01679 | IFR | 2019-05-31 | 2019-06-04 | R1-No comments | TPSK-LSPA1-T-PE-01679 |  | 2019-05-17 | 2
036909C-1059-PDS-2500-5900 | Process Equipment Datasheet - 10-TK-5900 - Sulfuric Acid Tank | A | 2018-11-16 | IFR | OL1-2G30-5900 | PE | 2018-11-26 | 036909C-JVD-TRN-00364 | 036909C-JVD-TRN-00364 | IFR | 2018-12-10 | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-00364 |  | 2018-11-26 | 2
036909C-1059-PDS-2500-5900 | Process Equipment Datasheet - 10-TK-5900 - Sulfuric Acid Tank | B | 2019-01-10 | IFD | OL1-2G30-5900 | PE | 2019-01-14 | 036909C-JVD-TRN-00647 | 036909C-JVD-TRN-00647 | IFI |  | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00647 |  | 2019-01-14 | 2
036909C-1051-PDS-2500-5120 | Process Equipment Datasheet - 10-TK-5120 - Raw Condensate Tank | B | 2019-03-13 | IFD | OL1-2G30-5120 | PE | 2019-03-14 | 036909C-JVD-TRN-01055 | 036909C-JVD-TRN-01055 | IFR | 2019-03-29 | 2019-03-29 | R1-No comments | TPSK-LSPA1-T-PE-01055 |  | 2019-03-15 | 2
036909C-1051-PDS-2500-5120 | Process Equipment Datasheet - 10-TK-5120 - Raw Condensate Tank | A | 2018-11-16 | IFR | OL1-2G30-5120 | PE | 2018-11-26 | 036909C-JVD-TRN-00364 | 036909C-JVD-TRN-00364 | IFR | 2018-12-10 | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-00364 |  | 2018-11-26 | 2
036909C-1051-PDS-2500-5110 | Process Equipment Datasheet - 10-TK-5110 - Condensate Tank | B | 2019-03-09 | IFD | OL1-2G30-5110 | PE | 2019-03-11 | 036909C-JVD-TRN-01017 | 036909C-JVD-TRN-01017 | IFR | 2019-03-26 | 2019-03-27 | R1-No comments | TPSK-LSPA1-T-PE-01017 |  | 2019-03-12 | 2
036909C-1051-PDS-2500-5110 | Process Equipment Datasheet - 10-TK-5110 - Condensate Tank | A | 2018-11-27 | IFR | OL1-2G30-5110 | PE | 2018-11-27 | 036909C-JVD-TRN-00374 | 036909C-JVD-TRN-00374 | IFR | 2018-12-11 | 2018-12-18 | R2-Comments as noted | TPSK-LSPA1-T-PE-00374 |  | 2018-11-27 | 2
036909C-1011-DW-0132-1102 | USC 36M Recycle Furnace Refractory and Insulation Convection Section Details | A | 2019-02-22 | IFR | OL1-2M06-1102 | ME | 2019-03-14 | 036909C-JVD-TRN-01065 | 036909C-JVD-TRN-01065 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-ME-01065 |  | 2019-03-15 | 2
036909C-1011-DW-0132-1102 | USC 36M Recycle Furnace Refractory and Insulation Convection Section Details | 0 | 2019-05-09 | IMP | OL1-2M06-1102 | ME | 2019-05-13 | 036909C-JVD-TRN-01653 | 036909C-JVD-TRN-01653 | IFR | 2019-05-28 | 2019-06-13 | R1-No comments | TPSK-LSPA1-T-ME-01653 |  | 2019-05-14 | 2
036909C-102C-DW-1442-0001 | Major Underground Networks - Zone 2C - Hot Fractination-Ghu Unit | A | 2019-03-22 | IFR | OL1-2K36-0005 | CV | 2019-03-25 | 036909C-JVD-TRN-01138 | 036909C-JVD-TRN-01138, ROC-TPSK-CECO-T-00025 | IFR | 2019-04-09 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01138 |  | 2019-03-26 | 2
036909C-1022-SP-0910-2212 | Mechanical Equipment Datasheet - CG 1st Stage Condensate Pumps | A | 2018-12-04 | IFQ | OL1-2M03-2212 | ME | 2018-12-05 | 036909C-JVD-TRN-00413 | 036909C-JVD-TRN-00413, ROC-TPSK-CECO-T-00014 | IFR | 2018-12-18 | 2018-12-27 | TPSK-LSPA1-E-00104 march 20 2019 R2-Comments as noted | TPSK-LSPA1-T-ME-00413 |  | 2018-12-05 | 2
036909C-1000-JSD-1950-0001 | Fire And Gas Detection | A | 2019-03-18 | IFR | OL1-2F92-0001 | FF | 2019-03-21 | 036909C-JVD-TRN-01125 | 036909C-JVD-TRN-01125 | IFR | 2019-04-05 | 2019-05-09 | R1-No comments | TPSK-LSPA1-T-FF-01125 |  | 2019-03-22 | 2
036909C-1012-DW-0131-2580 | USC 132U Cracking Furnace Steel Breeching Plan and Elevations | 1 | 2019-07-17 | IMP | OL1-2K32-2580 | CV | 2019-07-22 | 036909C-JVD-TRN-02228 | 036909C-JVD-TRN-02228 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02228 |  | 2019-07-23 | 3
036909C-1012-DW-0131-2580 | USC 132U Cracking Furnace Steel Breeching Plan and Elevations | A | 2019-04-08 | IFI | OL1-2K32-2580 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1012-DW-0131-2580 | USC 132U Cracking Furnace Steel Breeching Plan and Elevations | 0 | 2019-05-24 | IMP | OL1-2K32-2580 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1012-DW-0131-2502 | USC 36M Recycle And 132U Cracking Furnace Steel Base Plate Details | A | 2019-03-29 | IFI | OL1-2K32-2502 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1012-DW-0131-2502 | USC 36M Recycle and 132U Cracking Furnace Steel Base Plate Details | 0 | 2019-05-07 | IMP | OL1-2K32-2502 | CV | 2019-05-08 | 036909C-JVD-TRN-01616 | 036909C-JVD-TRN-01616 | IFI |  | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-CV-01616 |  | 2019-05-09 | 3
036909C-1012-DW-0131-2502 | USC 36M Recycle And 132U Cracking Furnace Steel Base Plate Details | 1 | 2019-05-15 | IMP | OL1-2K32-2502 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1012-DW-0131-2502 | USC 36M Recycle And 132U Cracking Furnace Steel Base Plate Details | 2 | 2019-07-11 | IMP | OL1-2K32-2502 | CV | 2019-07-22 | 036909C-JVD-TRN-02229 | 036909C-JVD-TRN-02229 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02229 |  | 2019-07-23 | 3
036909C-1012-DW-0131-2501 | USC 36M Recycle and 132U Cracking Recycle Furnaces Steel Foundation Plan and Loading Diagram | 0 | 2019-05-07 | IFI | OL1-2K32-2501 | CV | 2019-05-08 | 036909C-JVD-TRN-01618 | 036909C-JVD-TRN-01618 | IFI |  | 2019-07-01 | R1-No comments | TPSK-LSPA1-T-CV-01618 |  | 2019-05-09 | 3
036909C-1012-DW-0131-2501 | USC 132U Cracking and 36M Recycle Furnaces Steel Foundation Plan and Loading Diagram | 1 | 2019-05-23 | IMP | OL1-2K32-2501 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1025-PDS-0800-2572 | Process Equipment Datasheet - 10-D-2570 - Deethanizer Reflux Drum | B | 2018-12-06 | IFD | OL1-2G30-2572 | PE | 2018-12-07 | 036909C-JVD-TRN-00446 | 036909C-JVD-TRN-00446 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00446 |  | 2018-12-07 | 2
036909C-1012-SR-0127-2001 | Scope of Supply for Convection Tubes | 0 | 2018-12-04 | IFP | OL1-2M56-2001 | ME | 2018-12-10 | 036909C-JVD-TRN-00450 | 036909C-JVD-TRN-00450 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00450 |  | 2018-12-10 | 3
036909C-1028-PDS-0800-2865 | Process Equipment Datasheet - 10-D-2865 - C2R Drain Drum | A | 2018-12-06 | IFR | OL1-2G30-2865 | PE | 2018-12-07 | 036909C-JVD-TRN-00445 | 036909C-JVD-TRN-00445 | IFR | 2018-12-20 | 2019-01-10 | R1-No comments | TPSK-LSPA1-T-PE-00445 |  | 2018-12-07 | 2
036909C-1023-PDS-0900-2391 | Process Equipment Datasheet - 10-P-2390 - Caustic Drain Drum Pump | A | 2018-12-06 | IFR | OL1-2G30-2391 | PE | 2018-12-07 | 036909C-JVD-TRN-00444 | 036909C-JVD-TRN-00444 | IFR | 2018-12-20 | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-00444 |  | 2018-12-07 | 2
036909C-1010-PDS-0600-1001 | Process Equipment Datasheet - 10-E-1000 - LPG Vaporizer | B | 2018-12-06 | IFD | OL1-2G30-1001 | PE | 2018-12-10 | 036909C-JVD-TRN-00451 | 036909C-JVD-TRN-00451 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00451 |  | 2018-12-10 | 2
036909C-1022-PDS-0800-2210 | Process Equipment Datasheet - 10-D-2210 - CG 1st Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2210 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00448 |  | 2018-12-10 | 2
036909C-1022-PDS-0800-2240 | Process Equipment Datasheet - 10-D-2240 - CG 4th Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2240 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00448 |  | 2018-12-10 | 2
036909C-1020-SP-0510-2020 | Mechanical Equipment Data Sheet - Light Fuel Oil Stripper | A | 2018-12-07 | IFQ | OL1-2M03-2020 | ME | 2018-12-10 | 036909C-JVD-TRN-00447 | 036909C-JVD-TRN-00447 | IFR | 2018-12-21 | 2019-01-27 | R1-No comments | TPSK-LSPA1-T-ME-00447 |  | 2018-12-10 | 2
036909C-1022-PDS-0800-2220 | Process Equipment Datasheet - 10-D-2220 - CG 2nd Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2220 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-00448 |  | 2018-12-10 | 2
036909C-1012-PDS-0610-1209 | Process Equipment Datasheet - 10-E-1210 - 10-E-1610 - USC 132U TLX Quench Exchanger | B | 2018-12-06 | IFD | OL1-2G30-1209 | PE | 2018-12-10 | 036909C-JVD-TRN-00449 | 036909C-JVD-TRN-00449 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00449 |  | 2018-12-10 | 2
036909C-1022-PDS-0800-2230 | Process Equipment Datasheet - 10-D-2230 - CG 3rd Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2230 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00448 |  | 2018-12-10 | 2
036909C-1012-MR-0127-2001 | Material Requisition for Convection Tubes - For next Rev. see Doc. Client Ref. OL1-2C13-303000 | 0 | 2018-12-06 | IFP | OL1-2C13-303000 | ME | 2018-12-10 | 036909C-JVD-TRN-00450 | 036909C-JVD-TRN-00450 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00450 | For next Rev. see Doc. Client Ref. OL1-2C13-303000 | 2018-12-10 | 3
036909C-1012-SP-0127-2001 | Particular Technical Specification for Convection Tubes | 0 | 2018-12-04 | IFP | OL1-2M57-2001 | ME | 2018-12-10 | 036909C-JVD-TRN-00450 | 036909C-JVD-TRN-00450 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00450 |  | 2018-12-10 | 3
036909C-1026-PDS-0600-2645 | Process Equipment Datasheet - 10-E-2645 A-B - C3 Tower Reboilers | C | 2018-12-04 | IFD | OL1-2G30-2645 | PE | 2018-12-07 | 036909C-JVD-TRN-00438 | 036909C-JVD-TRN-00438 | IFI |  | 2018-11-27 | A1-Approved without comments | TPSK-LSPA1-T-PE-00438 |  | 2018-12-07 | 1
036909C-1056-PDS-2600-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg | B | 2018-12-05 | IFD | OL1-2G30-5650 | PE | 2018-12-07 | 036909C-JVD-TRN-00442 | 036909C-JVD-TRN-00442 | IFI |  | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00442 |  | 2018-12-07 | 2
036909C-1056-PDS-2600-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package | B | 2018-12-05 | IFD | OL1-2G30-5644 | PE | 2018-12-07 | 036909C-JVD-TRN-00442 | 036909C-JVD-TRN-00442 | IFI |  | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00442 |  | 2018-12-07 | 2
036909C-1055-PDS-0800-5552 | Process Equipment Datasheet - 10-D-5552 - LPG Storage Drum | A | 2018-12-05 | IFR | OL1-2G30-5552 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00439 |  | 2018-12-07 | 2
036909C-1021-PDS-0500-2120 | Process Equipment Datasheet - 10-T-2120 - Distillate Stripper | C | 2018-12-05 | IFD | OL1-2G30-2120 | PE | 2018-12-07 | 036909C-JVD-TRN-00437 | 036909C-JVD-TRN-00437 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00437 |  | 2018-12-07 | 2
036909C-1056-PDS-0200-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg | B | 2018-12-05 | IFD | OL1-2G30-5653 | PE | 2018-12-07 | 036909C-JVD-TRN-00441 | 036909C-JVD-TRN-00441 | IFI |  | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00441 |  | 2018-12-07 | 2
036909C-1055-PDS-0800-5550 | Process Equipment Datasheet - 10-D-5550 - HP Flare Knock-Out Drum | B | 2018-12-05 | IFD | OL1-2G30-5550 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00440 |  | 2018-12-07 | 2
036909C-1010-PDS-0600-1051 | Process Equipment Datasheet - 10-E-1050 - C2 Feed Superheater | B | 2018-12-04 | IFD | OL1-2G30-1051 | PE | 2018-12-07 | 036909C-JVD-TRN-00436 | 036909C-JVD-TRN-00436 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00436 |  | 2018-12-07 | 2
036909C-1024-PDS-0600-2445 | Process Equipment Datasheet - 10-E-2445 A-B - HP Depropanizer Reboilers | B | 2018-12-04 | IFD | OL1-2G30-2445 | PE | 2018-12-07 | 036909C-JVD-TRN-00436 | 036909C-JVD-TRN-00436 | IFI |  | 2018-12-18 | R1-No comments | TPSK-LSPA1-T-PE-00436 |  | 2018-12-07 | 2
036909C-1020-PDS-0500-2020 | Process Equipment Datasheet - 10-T-2020 - Light Fuel Oil Stripper | B | 2018-12-05 | IFD | OL1-2G30-2020 | PE | 2018-12-07 | 036909C-JVD-TRN-00437 | 036909C-JVD-TRN-00437 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00437 |  | 2018-12-07 | 2
036909C-1052-PDS-0800-5200 | Process Equipment Datasheet - 10-D-5200 - Fuel Gas Drum | B | 2018-12-05 | IFD | OL1-2G30-5200 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  | 2019-01-04 | TPSK-LSPA1-E-00093 March 13 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-00440 |  | 2018-12-07 | 2
036909C-1051-PDS-0800-5150 | Process Equipment Datasheet - 10-D-5150 - Continuous Blow Down Flash Drum | B | 2018-12-05 | IFD | OL1-2G30-5150 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  | 2019-03-11 | R1-No comments | TPSK-LSPA1-T-PE-00440 |  | 2018-12-07 | 2
036909C-1056-PDS-2600-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg | B | 2018-12-05 | IFD | OL1-2G30-5670 | PE | 2018-12-07 | 036909C-JVD-TRN-00442 | 036909C-JVD-TRN-00442 | IFI |  | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00442 |  | 2018-12-07 | 2
036909C-1021-PDS-0500-2100 | Process Equipment Datasheet - 10-T-2100 - Quench Water Tower | B | 2018-12-05 | IFD | OL1-2G30-2100 | PE | 2018-12-07 | 036909C-JVD-TRN-00437 | 036909C-JVD-TRN-00437 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00437 |  | 2018-12-07 | 2
036909C-1022-PDS-0600-2241 | Process Equipment Datasheet - 10-E-2240 A-B - CG 4th Stage Aftercooler | B | 2018-12-04 | IFD | OL1-2G30-2241 | PE | 2018-12-07 | 036909C-JVD-TRN-00436 | 036909C-JVD-TRN-00436 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00436 |  | 2018-12-07 | 2
036909C-1025-PDS-0800-2551 | Process Equipment Datasheet - 10-D-2550 - Expander Suction Drum | B | 2018-12-04 | IFD | OL1-2G30-2551 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00440 |  | 2018-12-07 | 2
036909C-1028-PDS-0800-2815 | Process Equipment Datasheet - 10-D-2815 - C3R Drain Drum | A | 2018-12-04 | IFR | OL1-2G30-2815 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00439 |  | 2018-12-07 | 2
036909C-1026-PDS-0800-2600 | Process Equipment Datasheet - 10-D-2600 A-B - C3 Hydrog Guard Adsorber | A | 2018-12-05 | IFR | OL1-2G30-2600 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00439 |  | 2018-12-07 | 2
036909C-1026-PDS-0600-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler | C | 2018-12-04 | IFD | OL1-2G30-2635 | PE | 2018-12-07 | 036909C-JVD-TRN-00438 | 036909C-JVD-TRN-00438 | IFI |  | 2018-12-27 | A1-Approved without comments | TPSK-LSPA1-T-PE-00438 |  | 2018-12-07 | 1
036909C-1000-PP-1600-003 | Coordination Procedure For ETAP - Ex Document Client Reference OL1-2R05-0045 | 0 | 2018-12-03 | IFI | OL1-2E92-0003 | EE | 2018-12-05 | 036909C-JVD-TRN-00426 | 036909C-JVD-TRN-00426 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00426 | Ex Document Client Reference OL1-2R05-0045 | 2018-12-05 | 3
036909C-1055-PDS-0800-5500 | Process Equipment Datasheet - 10-D-5500 - Hot Flare Drum | B | 2018-12-04 | IFD | OL1-2G30-5500 | PE | 2018-12-05 | 036909C-JVD-TRN-00417 | 036909C-JVD-TRN-00417 | IFI |  | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00417 |  | 2018-12-05 | 2
036909C-1020-SP-0510-2040 | Mechanical Equipment Data Sheet - Heavy Fuel Oil Stripper | B | 2018-12-04 | IFQ | OL1-2M03-2040 | ME | 2018-12-05 | 036909C-JVD-TRN-00418 | 036909C-JVD-TRN-00418 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00418 |  | 2018-12-05 | 2
036909C-1025-PDS-0800-2525 | Process Equipment Datasheet - 10-D-2525 - Hydrogen Drum | B | 2018-12-04 | IFD | OL1-2G30-2525 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  | 2018-12-18 | R1-No comments | TPSK-LSPA1-T-PE-00430 |  | 2018-12-07 | 2
036909C-1024-PDS-0800-2410 | Process Equipment Datasheet - 10-D-2410 A-B - Cracked Gas Dryer | A | 2018-12-06 | IFR | OL1-2G30-2410 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00439 |  | 2018-12-07 | 2
036909C-1024-SP-0510-2440 | Mechanical Equipment Datasheet - HP Depropanizer | B | 2018-11-28 | IFQ | OL1-2M03-2440 | ME | 2018-12-05 | 036909C-JVD-TRN-00416 | 036909C-JVD-TRN-00416 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00416 |  | 2018-12-05 | 2
036909C-1024-PDS-0800-2438 | Process Equipment Datasheet - 10-D-2440 - HP Depropanizer Reflux Drum | B | 2018-12-04 | IFD | OL1-2G30-2438 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  | 2018-12-18 | R1-No comments | TPSK-LSPA1-T-PE-00430 |  | 2018-12-07 | 2
036909C-1025-PDS-0800-2555 | Process Equipment Datasheet - 10-D-2555 - Expander Discharge Drum | B | 2018-12-04 | IFD | OL1-2G30-2555 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  | 2018-12-18 | email to client on December 21 2018 R2-Comments as noted | TPSK-LSPA1-T-PE-00430 |  | 2018-12-07 | 2
036909C-1024-PDS-0800-2452 | Process Equipment Datasheet - 10-D-2450 - LP Depropanizer Reflux Drum | B | 2018-12-04 | IFD | OL1-2G30-2452 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  | 2018-12-18 | R1-No comments | TPSK-LSPA1-T-PE-00430 |  | 2018-12-07 | 2
036909C-1000-JSS-1031-0001 | ME-047 Dry Screw Compressor for Hydrocarbon Services | A | 2018-11-30 | IFR | OL1-2R03-0047 | ME | 2018-12-06 | 036909C-JVD-TRN-00429 | 036909C-JVD-TRN-00429 | IFR | 2018-12-20 | 2018-12-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00429 |  | 2018-12-06 | 2
036909C-1012-DW-0131-2546 | USC 132U Cracking Furnace Name Plate Details | 0 | 2018-12-04 | IFI | OL1-2K32-2546 | ME | 2018-12-04 | 036909C-JVD-TRN-00423 | 036909C-JVD-TRN-00423 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00423 |  | 2018-12-04 | 3
036909C-1012-JSS-0154-2008 | Project Specification For Transfer Line Exchangers - Ex Doc. Client Ref. OL1-4M92-2008 | 0 | 2018-11-28 | IMP | OL1-2M92-2008 | ME | 2018-12-05 | 036909C-JVD-TRN-00428 | 036909C-JVD-TRN-00428 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00428 | Ex Doc. Client Ref. OL1-4M92-2008 | 2018-12-05 | 3
036909C-1012-JSS-0154-2007 | Project Specification For SLE and USX Exchangers - Ex Doc. Client Ref. OL1-4M92-2007 | 0 | 2018-11-28 | IMP | OL1-2M92-2007 | ME | 2018-12-05 | 036909C-JVD-TRN-00427 | 036909C-JVD-TRN-00427 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00427 | Ex Doc. Client Ref. OL1-4M92-2007 | 2018-12-05 | 3
036909C-1000-JSS-1641-0002 | Neutral Grounding Resistor | 0 | 2018-12-03 | IMP | OL1-2R05-0027 | EE | 2018-12-05 | 036909C-JVD-TRN-00425 | 036909C-JVD-TRN-00425 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00425 |  | 2018-12-05 | 3
036909C-1026-SP-0910-2669 | Mechanical Equipment Datasheet - Debutanizer Bottoms Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2669 | ME | 2018-12-04 | 036909C-JVD-TRN-00421 | 036909C-JVD-TRN-00421 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00421 |  | 2018-12-04 | 2
036909C-1025-SP-0510-2540 | Mechanical Equipment Data Sheet - Demethanizer and Demethanizer Reflux Drum | B | 2018-11-30 | IFQ | OL1-2M03-2540 | ME | 2018-12-05 | 036909C-JVD-TRN-00415 | 036909C-JVD-TRN-00415 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00415 |  | 2018-12-05 | 2
036909C-1025-SP-0510-2510 | Mechanical Equipment Data Sheet - Demethanizer Prefractionator & Reflux Drum | B | 2018-11-30 | IFQ | OL1-2M03-2510 | ME | 2018-12-05 | 036909C-JVD-TRN-00414 | 036909C-JVD-TRN-00414 | IFI |  | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00414 |  | 2018-12-05 | 2
036909C-1000-JSS-0184-0001 | ME-021 Flare System | A | 2018-11-29 | IFR | OL1-2R03-0021 | ME | 2018-12-06 | 036909C-JVD-TRN-00429 | 036909C-JVD-TRN-00429, ROC-TPSK-CECO-T-00003 | IFR | 2018-12-20 | 2018-12-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00429 |  | 2018-12-06 | 2
036909C-1023-SP-0510-2300 | Mechanical Equipment Data Sheet - Caustic Tower | B | 2018-12-04 | IFQ | OL1-2M03-2300 | ME | 2018-12-05 | 036909C-JVD-TRN-00419 | 036909C-JVD-TRN-00419 | IFI |  | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00419 |  | 2018-12-05 | 2
036909C-1020-SP-0510-2000 | Mechanical Equipment Data Sheet - Quench Oil Tower | A | 2018-12-04 | IFQ | OL1-2M03-2000 | ME | 2018-12-04 | 036909C-JVD-TRN-00420 | 036909C-JVD-TRN-00420 | IFR | 2018-12-18 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-ME-00420 |  | 2018-12-04 | 2
036909C-1010-PDS-0600-1015 | Process Equipment Datasheet - 10-E-1015 - LPG Superheater | B | 2018-12-04 | IFD | OL1-2G30-1015 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00431 |  | 2018-12-07 | 2
036909C-1012-PDS-0630-1208 | Process Equipment Datasheet - 10-E-1200A-F - 10-E-1600A-F - USC 132U SLE Exchanger | B | 2018-12-05 | IFD | OL1-2G30-1208 | PE | 2018-12-07 | 036909C-JVD-TRN-00433 | 036909C-JVD-TRN-00433, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00433 |  | 2018-12-07 | 2
036909C-1010-PDS-0600-1020 | Process Equipment Datasheet - 10-E-1020 - Liquid Feed Heater | B | 2018-12-04 | IFD | OL1-2G30-1020 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  | 2019-01-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-00431 |  | 2018-12-07 | 2
036909C-1012-PDS-1542-1213 | Process Equipment Datasheet - 10-M-1201 - 1601 A-F - USC 132U Dilution Steam Mixing Tee | A | 2018-12-04 | IFR | OL1-2G30-1213 | PE | 2018-12-07 | 036909C-JVD-TRN-00434 | 036909C-JVD-TRN-00434 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00434 |  | 2018-12-07 | 2
036909C-1021-PDS-0600-2166 | Process Equipment Datasheet - 10-E-2166 - DSG Blowdown Cooler | B | 2018-12-04 | IFD | OL1-2G30-2166 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00431 |  | 2018-12-07 | 2
036909C-1022-PDS-0600-2221 | Process Equipment Datasheet - 10-E-2220 A-B - CG 2nd Stage Aftercooler | B | 2018-12-04 | IFD | OL1-2G30-2221 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00431 |  | 2018-12-07 | 2
036909C-1011-PDS-0630-1108 | Process Equipment Datasheet - 10-E-1100A1 - F6 - USC 36M USX Exchanger | B | 2018-12-05 | IFD | OL1-2G30-1108 | PE | 2018-12-07 | 036909C-JVD-TRN-00432 | 036909C-JVD-TRN-00432 | IFI |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00432 |  | 2018-12-07 | 2
036909C-1022-PDS-0600-2231 | Process Equipment Datasheet - 10-E-2230 A-B - CG 3rd Stage Aftercooler | B | 2018-12-04 | IFD | OL1-2G30-2231 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  | 2019-01-16 | R1-No comments | TPSK-LSPA1-T-PE-00431 |  | 2018-12-07 | 2
036909C-1026-SP-0510-2640 | Mechanical Equipment Data Sheet - C3 Tower | A | 2018-11-30 | IFQ | OL1-2M03-2640 | ME | 2018-12-05 | 036909C-JVD-TRN-00415 | 036909C-JVD-TRN-00415 | IFR | 2018-12-18 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00415 |  | 2018-12-05 | 2
036909C-1024-PDS-0900-2457 | Process Equipment Datasheet - 10-P-2455 A-B - LP Deprop Reboiler Cond Pump | A | 2018-12-03 | IFR | OL1-2G30-2457 | PE | 2018-12-04 | 036909C-JVD-TRN-00408 | 036909C-JVD-TRN-00408 | IFR | 2018-12-17 | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-00408 |  | 2018-12-04 | 2
036909C-1026-SP-0510-2660 | Mechanical Equipment Datasheet - Debutanizer | C | 2018-11-30 | IFQ | OL1-2M03-2660 | ME | 2018-12-05 | 036909C-JVD-TRN-00415 | 036909C-JVD-TRN-00415 | IFR | 2018-12-18 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00415 |  | 2018-12-05 | 2
036909C-1024-PDS-0900-2443 | Process Equipment Datasheet - 10-P-2445 A-B - HP Deprop Reboiler Cond Pump | A | 2018-12-03 | IFR | OL1-2G30-2443 | PE | 2018-12-04 | 036909C-JVD-TRN-00408 | 036909C-JVD-TRN-00408 | IFR | 2018-12-17 | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-00408 |  | 2018-12-04 | 2
036909C-1025-PDS-0900-2577 | Process Equipment Datasheet - 10-P-2575 A-B - Deethanizer Reboiler Cond Pumps | A | 2018-12-03 | IFR | OL1-2G30-2577 | PE | 2018-12-04 | 036909C-JVD-TRN-00408 | 036909C-JVD-TRN-00408 | IFR | 2018-12-17 | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-00408 |  | 2018-12-04 | 2
036909C-1026-PDS-0500-2630 | Process Equipment Datasheet - 10-T-2630 - Secondary Deethanizer | C | 2018-11-30 | IFD | OL1-2G30-2630 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-PE-00407 |  | 2018-12-04 | 3
036909C-1024-SP-0510-2450 | Mechanical Equipment Data Sheet - LP Depropanizer | C | 2018-11-30 | IFQ | OL1-2M03-2450 | ME | 2018-12-05 | 036909C-JVD-TRN-00412 | 036909C-JVD-TRN-00412 | IFI |  | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00412 |  | 2018-12-05 | 2
036909C-1025-PDS-0500-2580 | Process Equipment Datasheet - 10-T-2580 - C2 Tower | B | 2018-11-30 | IFD | OL1-2G30-2580 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-PE-00407 |  | 2018-12-04 | 2
036909C-1026-PDS-0500-2640 | Process Equipment Datasheet - 10-T-2640 - C3 Tower | B | 2018-11-30 | IFD | OL1-2G30-2640 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-PE-00407 |  | 2018-12-04 | 2
036909C-1000-JSD-1530-0001 | Intercom/Paging/Audible Alarm System | A | 2018-11-30 | IFR | OL1-2R05-0013 | EE | 2018-12-04 | 036909C-JVD-TRN-00403 | 036909C-JVD-TRN-00403 | IFR | 2018-12-18 | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-EE-00403 |  | 2018-12-04 | 2
036909C-1025-PDS-0500-2540 | Process Equipment Datasheet - 10-T-2540 - 10-D-2540 - Demethanizer & Reflux Drum | C | 2018-11-30 | IFD | OL1-2G30-2540 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-PE-00407 |  | 2018-12-04 | 1
036909C-1012-TBT-0127-2001 | Technical Bid Tabulation for Convection Tubes | 0 | 2018-11-29 | IFI | OL1-2Y23-2001 | ME | 2018-12-04 | 036909C-JVD-TRN-00404 | 036909C-JVD-TRN-00404 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00404 |  | 2018-12-04 | 3
036909C-1025-PDS-0500-2520 | Process Equipment Datasheet - 10-T-2520 - 10-D2520 - Residue Gas Rectifier & Reflux Drum | B | 2018-11-30 | IFD | OL1-2G30-2520 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-PE-00407 |  | 2018-12-04 | 2
036909C-1024-PDS-0600-2451 | Process Equipment Datasheet - 10-E-2450 - LP Depropanizer Condenser | B | 2018-11-28 | IFD | OL1-2G30-2451 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | 2018-11-29 | 2
036909C-1000-JSD-1530-0002 | Safety Supervisory System | A | 2018-11-30 | IFR | OL1-2R05-0019 | EE | 2018-12-04 | 036909C-JVD-TRN-00403 | 036909C-JVD-TRN-00403 | IFR | 2018-12-18 | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-EE-00403 |  | 2018-12-04 | 2
036909C-1024-PDS-0600-2442 | Process Equipment Datasheet - 10-E-2442 - HP Deprop Reflux Chiller No 1 | B | 2018-11-28 | IFD | OL1-2G30-2442 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | 2018-11-29 | 2
036909C-1053-SP-0910-5352 | Mechanical Equipment DataSheet - Olefins Cooling Water Pumps | B | 2018-11-26 | IFQ | OL1-2M03-5352 | ME | 2018-11-28 | 036909C-JVD-TRN-00388 | 036909C-JVD-TRN-00388, ROC-TPSK-CECO-T-00016 | IFI |  | 2018-12-18 | R1-No comments | TPSK-LSPA1-T-ME-00388 |  | 2018-11-28 | 2
036909C-1000-SP-4100-0001 | Particular Technical Specification for Wet Air Oxidation Package | A | 2018-11-26 | IFQ | OL1-2M57-0103 | ME | 2018-11-29 | 036909C-JVD-TRN-00390 | 036909C-JVD-TRN-00390 | IFR | 2018-12-13 | 2019-02-07 | R1-No comments | TPSK-LSPA1-T-ME-00390 |  | 2018-11-29 | 2
036909C-1024-PDS-0600-2441 | Process Equipment Datasheet - 10-E-2441 - HP Deprop Reflux Chiller No 2 | B | 2018-11-28 | IFD | OL1-2G30-2441 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | 2018-11-29 | 2
036909C-1055-PDS-0800-5510 | Process Equipment Datasheet - 10-D-5510 - Cold Flare Drum | A | 2018-11-29 | IFR | OL1-2G30-5510 | PE | 2018-11-29 | 036909C-JVD-TRN-00397 | 036909C-JVD-TRN-00397 | IFR | 2018-12-13 | 2019-01-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00397 |  | 2018-11-29 | 2
036909C-1020-PDS-0500-2000 | Process Equipment Datasheet - 10-T-2000 - Quench Oil Tower | B | 2018-11-29 | IFD | OL1-2G30-2000 | PE | 2018-12-04 | 036909C-JVD-TRN-00402 | 036909C-JVD-TRN-00402 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00402 |  | 2018-12-04 | 2
036909C-1053-SP-0910-5361 | Mechanical Equipment Data Sheet - CTU Cooling Water Pumps | C | 2018-11-26 | IFQ | OL1-2M03-5361 | ME | 2018-11-28 | 036909C-JVD-TRN-00388 | 036909C-JVD-TRN-00388 | IFI |  | 2018-12-18 | R1-No comments | TPSK-LSPA1-T-ME-00388 |  | 2018-11-28 | 2
036909C-1021-PDS-0500-2140 | Process Equipment Datasheet - 10-T-2140 - Process Water Stripper | B | 2018-11-29 | IFD | OL1-2G30-2140 | PE | 2018-11-29 | 036909C-JVD-TRN-00401 | 036909C-JVD-TRN-00401 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00401 |  | 2018-11-29 | 2
036909C-1024-PDS-0600-2471 | Process Equipment Datasheet - 10-E-2470 - C2 Hydrog 1st Stage Intercooler | A | 2018-11-28 | IFR | OL1-2G30-2471 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00391 |  | 2018-11-29 | 2
036909C-1025-PDS-0500-2570 | Process Equipment Datasheet - 10-T-2570 - Deethanizer | B | 2018-11-30 | IFD | OL1-2G30-2570 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-00407 |  | 2018-12-04 | 2
036909C-1000-JSD-1600-008 | General Design Rules For Smartplant Electrical - Ex Document Client Reference OL1-2R05-0043 | 0 | 2018-11-09 | IFI | OL1-2E92-0001 | EE | 2018-11-29 | 036909C-JVD-TRN-00396 | 036909C-JVD-TRN-00396 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00396 | Ex Document Client Reference: OL1-2R05-0043 | 2018-11-29 | 3
036909C-1024-PDS-0600-2439 | Process Equipment Datasheet - 10-E-2440 - HP Depropanizer Condenser | B | 2018-11-28 | IFD | OL1-2G30-2439 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | 2018-11-29 | 2
036909C-1025-TDS-0610-2503 | Mechanical Equipment Data Sheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | A | 2018-11-28 | IFQ | OL1-2M03-2503 | ME | 2018-11-28 | 036909C-JVD-TRN-00389 | 036909C-JVD-TRN-00389, ROC-TPSK-CECO-T-00018 | IFR | 2018-12-12 | 2018-12-13 | R1-No comments | TPSK-LSPA1-T-ME-00389 |  | 2018-11-28 | 2
036909C-1000-PP-1600-001 | Coordination Procedure For Smartplant Electrical - Ex Document Client Reference OL1-2R05-0044 | 0 | 2018-11-09 | IFI | OL1-2E92-0002 | EE | 2018-11-29 | 036909C-JVD-TRN-00395 | 036909C-JVD-TRN-00395 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00395 | Ex Document Client Reference OL1-2R05-0044 | 2018-11-29 | 3
036909C-1024-PDS-0600-2461 | Process Equipment Datasheet - 10-E-2460 - C2 Hydrog Feed Cooler | B | 2018-11-28 | IFD | OL1-2G30-2461 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | 2018-11-29 | 2
036909C-1025-SP-0510-2570 | Mechanical Equipment Data Sheet - Deethanizer | A | 2018-11-28 | IFQ | OL1-2M03-2570 | ME | 2018-11-29 | 036909C-JVD-TRN-00394 | 036909C-JVD-TRN-00394 | IFR | 2018-12-13 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00394 |  | 2018-11-29 | 2
036909C-1000-JSD-1580-0003 | General Design Rules For Instrumentation And Control Of Packaged Equipment | 0 | 2018-11-29 | IMP | OL1-2R06-0035 | IE | 2018-11-29 | 036909C-JVD-TRN-00393 | 036909C-JVD-TRN-00393, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-14 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-IE-00393 |  | 2018-11-29 | 2
036909C-1024-PDS-0600-2472 | Process Equipment Datasheet - 10-E-2472 - C2 Hydrog 2nd Stage Intercooler | A | 2018-11-28 | IFR | OL1-2G30-2472 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00391 |  | 2018-11-29 | 2
036909C-1024-PDS-0600-2465 | Process Equipment Datasheet - 10-E-2465 - C2 Hydrog Feed Heater | A | 2018-11-28 | IFR | OL1-2G30-2465 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00391 |  | 2018-11-29 | 2
036909C-1024-PDS-0600-2446 | Process Equipment Datasheet - 10-E-2446 - LP Depropanizer Feed Cooler | B | 2018-11-28 | IFD | OL1-2G30-2446 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | 2018-11-29 | 2
036909C-1021-PDS-0500-2120 | Process Equipment Datasheet - 10-T-2120 - Distillate Stripper | B | 2018-11-29 | IFD | OL1-2G30-2120 | PE | 2018-11-29 | 036909C-JVD-TRN-00401 | 036909C-JVD-TRN-00401 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00401 |  | 2018-11-29 | 2
036909C-1055-PDS-0180-5560 | Process Equipment Datasheet - 10-PK-5560 - HP - Polyolefins Flare Pkg | A | 2018-11-29 | IFR | OL1-2G30-5560 | PE | 2018-11-29 | 036909C-JVD-TRN-00398 | 036909C-JVD-TRN-00398 | IFR | 2018-12-13 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00398 |  | 2018-11-29 | 2
036909C-1024-PDS-0600-2413 | Process Equipment Datasheet - 10-E-2413 - HP Deprop Feed - Overhead Exchanger | B | 2018-11-28 | IFD | OL1-2G30-2413 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | 2018-11-29 | 2
036909C-1024-PDS-0600-2474 | Process Equipment Datasheet - 10-E-2474 - C2 Hydrog Aftercooler | A | 2018-11-28 | IFR | OL1-2G30-2474 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00391 |  | 2018-11-29 | 2
036909C-1000-SR-0610-0001 | Scope Of Supply For Wieland Tubes (Solo Source) | A | 2018-11-27 | IFQ | OL1-2M56-0058 | ME | 2018-11-28 | 036909C-JVD-TRN-00377 | 036909C-JVD-TRN-00377 | IFR | 2018-12-13 | 2019-02-07 | R1-No comments | TPSK-LSPA1-T-ME-00377 |  | 2018-11-28 | 2
036909C-1023-PDS-0900-2304 | Process Equipment Datasheet - 10-P-2304 - Intermediate Caustic Circulating Pump | B | 2018-11-27 | IFD | OL1-2G30-2304 | PE | 2018-11-28 | 036909C-JVD-TRN-00382 | 036909C-JVD-TRN-00382 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00382 |  | 2018-11-28 | 2
036909C-1023-PDS-0600-2326 | Process Equipment Datasheet - 10-E-2326 - Spent Caustic Stripper Feed Heater | A | 2018-11-27 | IFR | OL1-2G30-2326 | PE | 2018-11-28 | 036909C-JVD-TRN-00381 | 036909C-JVD-TRN-00381 | IFR | 2018-12-12 | 2019-01-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00381 |  | 2018-11-28 | 2
036909C-1028-PDS-0900-2855 | Process Equipment Datasheet - 10-P-2855 A-B - Ethylene Product Pumps | A | 2018-11-27 | IFR | OL1-2G30-2855 | PE | 2018-11-28 | 036909C-JVD-TRN-00379 | 036909C-JVD-TRN-00379 | IFR | 2018-12-12 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00379 |  | 2018-11-28 | 2
036909C-1023-PDS-0500-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper | C | 2018-11-27 | IFD | OL1-2G30-2330 | PE | 2018-11-28 | 036909C-JVD-TRN-00384 | 036909C-JVD-TRN-00384 | IFI |  | 2018-12-27 | TPSK-LSPA1-E-00049 January 2019 R2-Comments as noted | TPSK-LSPA1-T-PE-00384 |  | 2018-11-28 | 1
036909C-1000-SP-0610-0001 | Particular Technical Specification For Wieland Tubes (Solo Source) | A | 2018-11-27 | IFQ | OL1-2M57-0058 | ME | 2018-11-28 | 036909C-JVD-TRN-00377 | 036909C-JVD-TRN-00377 | IFR | 2018-12-13 | 2019-02-07 | R1-No comments | TPSK-LSPA1-T-ME-00377 |  | 2018-11-28 | 2
036909C-1022-PDS-0600-2206 | Process Equipment Datasheet - 10-E-2206 - Wash Water Cooler | A | 2018-11-27 | IFR | OL1-2G30-2206 | PE | 2018-11-28 | 036909C-JVD-TRN-00381 | 036909C-JVD-TRN-00381 | IFR | 2018-12-12 | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00381 |  | 2018-11-28 | 2
036909C-1023-PDS-0900-2306 | Process Equipment Datasheet - 10-P-2306 A-B - Weak Caustic Circulating Pumps | B | 2018-11-27 | IFD | OL1-2G30-2306 | PE | 2018-11-28 | 036909C-JVD-TRN-00382 | 036909C-JVD-TRN-00382 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00382 |  | 2018-11-28 | 2
036909C-1012-TBT-0154-2003 | Technical Bid Tabulation for Quench Exchangers | 0 | 2018-11-26 | IFI | OL1-2Y23-2003 | ME | 2018-11-28 | 036909C-JVD-TRN-00380 | 036909C-JVD-TRN-00380 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00380 |  | 2018-11-28 | 3
036909C-1023-PDS-4200-2308 | Process Equipment Datasheet - 10-X-2306 - Weak Caustic - Wash Oil Mixer | B | 2018-11-27 | IFD | OL1-2G30-2308 | PE | 2018-11-28 | 036909C-JVD-TRN-00383 | 036909C-JVD-TRN-00383, ROC-TPSK-CECO-T-00019 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00383 |  | 2018-11-28 | 2
036909C-1023-SP-4100-0002 | Mechanical Equipment Datasheet for Wet Air Oxidation Package | A | 2018-11-27 | IFQ | OL1-2M03-2350 | ME | 2018-11-29 | 036909C-JVD-TRN-00390 | 036909C-JVD-TRN-00390 | IFR | 2018-12-13 | 2019-02-07 | R1-No comments | TPSK-LSPA1-T-ME-00390 |  | 2018-11-29 | 2
036909C-1000-MR-0610-0001 | Material Requisition For Wieland Tubes (Solo Source) Requisition For Inquiry - For Next Revision See Document OL1-2C13-271000 | A | 2018-11-27 | IFQ | OL1-2C13-271000 | ME | 2018-11-28 | 036909C-JVD-TRN-00377 | 036909C-JVD-TRN-00377 | IFR | 2018-12-13 | 2019-02-07 | R1-No comments | TPSK-LSPA1-T-ME-00377 | For Next Revision See Document OL1-2C13-271000 | 2018-11-28 | 2
036909C-1053-PDS-2600-5394 | Process Equipment Datasheet - 10-PK-5394 - Dispersant Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5394 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00375 |  | 2018-11-27 | 2
036909C-1023-PDS-4200-2301 | Process Equipment Datasheet - 10-X-2300 - Caustic Dilution Mixer | B | 2018-11-27 | IFD | OL1-2G30-2301 | PE | 2018-11-28 | 036909C-JVD-TRN-00383 | 036909C-JVD-TRN-00383 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00383 |  | 2018-11-28 | 2
036909C-1053-PDS-2600-5392 | Process Equipment Datasheet - 10-PK-5392 - Mild Steel Corr Inhibitor Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5392 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00375 |  | 2018-11-27 | 2
036909C-1020-SP-0510-2040 | Mechanical Equipment Data Sheet - Heavy Fuel Oil Stripper | A | 2018-11-28 | IFQ | OL1-2M03-2040 | ME | 2018-11-28 | 036909C-JVD-TRN-00387 | 036909C-JVD-TRN-00387 | IFR | 2018-12-12 | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-ME-00387 |  | 2018-11-28 | 2
036909C-1024-PDS-0800-2480 | Process Equipment Datasheet - 10-D-2480 - CG Secondary Dryer | A | 2018-11-28 | IFR | OL1-2G30-2480 | PE | 2018-11-28 | 036909C-JVD-TRN-00386 | 036909C-JVD-TRN-00386 | IFR | 2018-12-12 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00386 |  | 2018-11-28 | 2
036909C-1020-PDS-0800-2090 | Process Equipment Datasheet - 10-D-2090 - Quench Oil Drain Drum | A | 2018-11-26 | IFR | OL1-2G30-2090 | PE | 2018-11-27 | 036909C-JVD-TRN-00368 | 036909C-JVD-TRN-00368 | IFR | 2018-12-11 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00368 |  | 2018-11-27 | 2
036909C-1026-PDS-0600-2666 | Process Equipment Datasheet - 10-E-2666 - Debutanizer Bottoms Cooler | B | 2018-11-26 | IFD | OL1-2G30-2666 | PE | 2018-11-27 | 036909C-JVD-TRN-00370 | 036909C-JVD-TRN-00370 | IFI |  | 2018-12-10 | A1-Approved without comments | TPSK-LSPA1-T-PE-00370 |  | 2018-11-27 | 1
036909C-1000-MR-4100-0001 | Material Requisition for Wet Air Oxidation Package - For Next Revision See Document OL1-2C13-704000 | A | 2018-11-22 | IFQ | OL1-2C13-704000 | ME | 2018-11-27 | 036909C-JVD-TRN-00367 | 036909C-JVD-TRN-00367 | IFR | 2018-12-11 | 2019-02-07 | R1-No comments | TPSK-LSPA1-T-ME-00367 | For Next Revision See Document OL1-2C13-704000 | 2018-11-27 | 2
036909C-1053-PDS-2600-5397 | Process Equipment Datasheet - 10-PK-5397 - Non-oxidizing Biocide Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5397 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00375 |  | 2018-11-27 | 2
036909C-1023-PDS-0800-2392 | Process Equipment Datasheet - 10-D-2392 - Spent Caustic Drain Drum | B | 2018-11-26 | IFD | OL1-2G30-2392 | PE | 2018-11-27 | 036909C-JVD-TRN-00369 | 036909C-JVD-TRN-00369 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00369 |  | 2018-11-27 | 2
036909C-1023-PDS-0800-2390 | Process Equipment Datasheet - 10-D-2390 - Caustic Drain Drum | B | 2018-11-26 | IFD | OL1-2G30-2390 | PE | 2018-11-27 | 036909C-JVD-TRN-00369 | 036909C-JVD-TRN-00369 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00369 |  | 2018-11-27 | 1
036909C-1026-TDS-0610-2645 | Mechanical Equipment Data Sheet - 10-E-2645 - C3 Tower Reboilers | A | 2018-11-19 | IFQ | OL1-2M03-2645 | ME | 2018-11-26 | 036909C-JVD-TRN-00361 | 036909C-JVD-TRN-00361 | IFR | 2018-12-10 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00361 |  | 2018-11-26 | 2
036909C-1051-PDS-0200-5115 | Process Equipment Datasheet - 10-PK-5115 - Condensate Carbon Filter Pkg | A | 2018-11-16 | IFR | OL1-2G30-5115 | PE | 2018-11-26 | 036909C-JVD-TRN-00362 | 036909C-JVD-TRN-00362 | IFR | 2018-12-10 | 2018-12-18 | R2-Comments as noted | TPSK-LSPA1-T-PE-00362 |  | 2018-11-26 | 2
036909C-1021-PDS-0900-2126 | Process Equipment Datasheet - 10-P-2126 A-B - Distillate Stripper Bottom Pumps | A | 2018-11-26 | IFR | OL1-2G30-2126 | PE | 2018-11-27 | 036909C-JVD-TRN-00371 | 036909C-JVD-TRN-00371 | IFR | 2018-12-11 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00371 |  | 2018-11-27 | 2
036909C-1000-DI-0007-0006 | Furnace Process Basis of Design | B | 2018-11-27 | IFD | OL1-2G02-0006 | PE | 2018-11-27 | 036909C-JVD-TRN-00376 | 036909C-JVD-TRN-00376, ROC-TPSK-CECO-T-00001 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00376 |  | 2018-11-27 | 1
036909C-1000-JSD-1572-0003 | Instrument Air Supply | A | 2018-11-20 | IFR | OL1-2R06-0011 | IE | 2018-11-26 | 036909C-JVD-TRN-00357 | 036909C-JVD-TRN-00357 | IFR | 2018-12-11 | 2019-02-01 | R1-No comments | TPSK-LSPA1-T-IE-00357 |  | 2018-11-26 | 2
036909C-1026-PDS-0900-2669 | Process Equipment Datasheet - 10-P-2665 A-B - Debutanizer Bottoms Pumps | A | 2018-11-26 | IFR | OL1-2G30-2669 | PE | 2018-11-27 | 036909C-JVD-TRN-00371 | 036909C-JVD-TRN-00371 | IFR | 2018-12-11 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00371 |  | 2018-11-27 | 2
036909C-1053-PDS-2600-5390 | Process Equipment Datasheet - 10-PK-5390 - Copper Corrosion Inhibitor Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5390 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00375 |  | 2018-11-27 | 2
036909C-1051-PDS-0600-5103 | Process Equipment Datasheet - 10-E-5100 - Deaerator Vent Condenser | B | 2018-11-19 | IFD | OL1-2G30-5103 | PE | 2018-11-26 | 036909C-JVD-TRN-00366 | 036909C-JVD-TRN-00366 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00366 |  | 2018-11-26 | 2
036909C-1051-PDS-0900-5121 | Process Equipment Datasheet - 10-P-5120 A-B - Raw Condensate Pumps | B | 2018-11-16 | IFD | OL1-2G30-5121 | PE | 2018-11-26 | 036909C-JVD-TRN-00363 | 036909C-JVD-TRN-00363 | IFI |  | 2018-12-13 | R1-No comments | TPSK-LSPA1-T-PE-00363 |  | 2018-11-26 | 2
036909C-1051-PDS-0600-5113 | Process Equipment Datasheet - 10-E-5113 - Foul Condensate Cooler | B | 2018-11-19 | IFD | OL1-2G30-5113 | PE | 2018-11-26 | 036909C-JVD-TRN-00366 | 036909C-JVD-TRN-00366 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00366 |  | 2018-11-26 | 2
036909C-1000-SP-1691-0001 | Particular Technical Specification For Low Voltage Motors Low Voltage Variable Voltage Variable Frequency System | A | 2018-11-16 | IFQ | OL1-2E57-3001 | EE | 2018-11-26 | 036909C-JVD-TRN-00359 | 036909C-JVD-TRN-00359 | IFR | 2018-12-11 | 2019-01-03 | R2-Comments as noted | TPSK-LSPA1-T-EE-00359 |  | 2018-11-26 | 2
036909C-1055-PDS-0800-5520 | Process Equipment Datasheet - 10-D-5520 - Vent Collection Drum | A | 2018-11-16 | IFR | OL1-2G30-5520 | PE | 2018-11-26 | 036909C-JVD-TRN-00365 | 036909C-JVD-TRN-00365 | IFR | 2018-12-10 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00365 |  | 2018-11-26 | 2
036909C-1051-PDS-0200-5125 | Process Equipment Datasheet - 10-PK-5125 - Condensate Polisher Pkg | A | 2018-11-27 | IFR | OL1-2G30-5125 | PE | 2018-11-27 | 036909C-JVD-TRN-00373 | 036909C-JVD-TRN-00373 | IFR | 2018-12-11 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00373 |  | 2018-11-27 | 2
036909C-1000-MR-1691-0001 | Material Requisition For Low Voltage Motors Low Voltage Variable Voltage Variable Frequency System | A | 2018-11-16 | IFQ | OL1-2E55-3001 | EE | 2018-11-26 | 036909C-JVD-TRN-00359 | 036909C-JVD-TRN-00359 | IFR | 2018-12-11 | 2019-01-03 | R2-Comments as noted | TPSK-LSPA1-T-EE-00359 |  | 2018-11-26 | 2
036909C-1000-SR-4100-0001 | Scope of Supply for Wet Air Oxidation Package | A | 2018-11-22 | IFQ | OL1-2M56-0103 | ME | 2018-11-27 | 036909C-JVD-TRN-00367 | 036909C-JVD-TRN-00367 | IFR | 2018-12-11 | 2019-02-07 | R1-No comments | TPSK-LSPA1-T-ME-00367 |  | 2018-11-27 | 2
036909C-1021-PDS-0800-2190 | Process Equipment Datasheet - 10-D-2190 - Quench Water Drain Drum | A | 2018-11-26 | IFR | OL1-2G30-2190 | PE | 2018-11-27 | 036909C-JVD-TRN-00368 | 036909C-JVD-TRN-00368 | IFR | 2018-12-11 | 2019-02-25 | R2-Comments as noted | TPSK-LSPA1-T-PE-00368 |  | 2018-11-27 | 2
036909C-1051-PDS-0900-5111 | Process Equipment Datasheet - 10-P-5112 A-B - Suspect Condensate Pumps | B | 2018-11-16 | IFD | OL1-2G30-5111 | PE | 2018-11-26 | 036909C-JVD-TRN-00363 | 036909C-JVD-TRN-00363 | IFI |  | 2018-12-13 | R1-No comments | TPSK-LSPA1-T-PE-00363 |  | 2018-11-26 | 2
036909C-1020-PDS-0900-2091 | Process Equipment Datasheet - 10-P-2090 A-B - Quench Oil Drain Drum Pumps | A | 2018-11-26 | IFR | OL1-2G30-2091 | PE | 2018-11-27 | 036909C-JVD-TRN-00371 | 036909C-JVD-TRN-00371 | IFR | 2018-12-11 | 2019-02-25 | R1-No comments | TPSK-LSPA1-T-PE-00371 |  | 2018-11-27 | 2
036909C-1012-PDS-0117-1201 | Process Equipment Datasheet - 10-H-1200 - 132U Cracking Furnace Yields | B | 2018-11-27 | IFD | OL1-2G30-1201 | PE | 2018-11-27 | 036909C-JVD-TRN-00372 | 036909C-JVD-TRN-00372 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00372 |  | 2018-11-27 | 2
036909C-1000-JSS-1310-0001 | Job Supply Specification For Valves (Gate - Globe - Check) | A | 2018-11-20 | IFR | OL1-2R04-0041 | MP | 2018-11-26 | 036909C-JVD-TRN-00356 | 036909C-JVD-TRN-00356 | IFR | 2018-12-11 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00356 |  | 2018-11-26 | 2
036909C-1000-JSS-1310-0006 | Job Supply Specification For Plug Valves | A | 2018-11-20 | IFR | OL1-2R04-0009 | MP | 2018-11-26 | 036909C-JVD-TRN-00352 | 036909C-JVD-TRN-00352 | IFR | 2018-12-11 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00352 |  | 2018-11-26 | 2
036909C-1021-PDS-0840-2138 | Process Equipment Datasheet - 10-F-2136 A-B Process Water Feed Filters | A | 2018-11-21 | IFR | OL1-2G30-2138 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00350 |  | 2018-11-21 | 2
036909C-1000-JSS-1310-0004 | Job Supply Specification For Butterfly Valves | A | 2018-11-20 | IFR | OL1-2R04-0008 | MP | 2018-11-26 | 036909C-JVD-TRN-00352 | 036909C-JVD-TRN-00352 | IFR | 2018-12-11 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00352 |  | 2018-11-26 | 2
036909C-1000-JSD-1511-0002 | Integrated Control And Safety System | A | 2018-11-20 | IFR | OL1-2R06-0015 | IE | 2018-11-26 | 036909C-JVD-TRN-00357 | 036909C-JVD-TRN-00357, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-11 | 2019-02-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-00357 |  | 2018-11-26 | 2
036909C-1000-JSD-1584-0001 | Custody Transfer System | A | 2018-11-20 | IFR | OL1-2R06-3101 | IE | 2018-11-26 | 036909C-JVD-TRN-00357 | 036909C-JVD-TRN-00357, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-12-11 | 2019-02-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-00357 |  | 2018-11-26 | 2
036909C-1000-JSS-1310-0008 | Job Supply Specification For Ball Valves | A | 2018-11-20 | IFR | OL1-2R04-0010 | MP | 2018-11-26 | 036909C-JVD-TRN-00352 | 036909C-JVD-TRN-00352 | IFR | 2018-12-11 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00352 |  | 2018-11-26 | 2
036909C-1000-SR-1691-0001 | Scope Of Supply For Low Voltage Motors Low Voltage Variable Voltage Variable Frequency System | A | 2018-11-16 | IFQ | OL1-2E56-3001 | EE | 2018-11-26 | 036909C-JVD-TRN-00359 | 036909C-JVD-TRN-00359 | IFR | 2018-12-11 | 2019-01-03 | R2-Comments as noted | TPSK-LSPA1-T-EE-00359 |  | 2018-11-26 | 2
036909C-1028-PDS-0800-2810 | Process Equipment Datasheet - 10-D-2810 - C3R 1st Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2810 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349 |  | 2018-11-21 | 2
036909C-1028-PDS-0800-2830 | Process Equipment Datasheet - 10-D-2830 - C3R 3rd Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2830 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349 |  | 2018-11-21 | 2
036909C-1028-PDS-0800-2840 | Process Equipment Datasheet - 10-D-2840 - C3R 4th Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2840 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349 |  | 2018-11-21 | 2
036909C-1020-PDS-0840-2014 | Process Equipment Datasheet - 10-F-2009 A-B QO Pump Purge Oil Filter | A | 2018-11-21 | IFR | OL1-2G30-2014 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00350 |  | 2018-11-21 | 2
036909C-1020-PDS-0840-2028 | Process Equipment Datasheet - 10-F-2028 A-B - FO Pump Purge Oil Filter | A | 2018-11-21 | IFR | OL1-2G30-2028 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00350 |  | 2018-11-21 | 2
036909C-1028-PDS-0800-2870 | Process Equipment Datasheet - 10-D-2870 - C2R 2nd Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2870 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349 |  | 2018-11-21 | 2
036909C-1028-PDS-0800-2820 | Process Equipment Datasheet - 10-D-2820 - C3R 2nd Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2820 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349 |  | 2018-11-21 | 2
036909C-1030-PDS-1000-3073 | Process Equipment Data Sheet - 10-C-3070 - BDU Recycle Gas Compressor | A | 2018-11-20 | IFR | OL1-2G30-3073 | PE | 2018-11-20 | 036909C-JVD-TRN-00344 | 036909C-JVD-TRN-00344 | IFR | 2018-12-04 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00344 |  | 2018-11-20 | 2
036909C-1000-JSS-1350-01 | Job Supply Specification For Flanges | B | 2018-11-19 | IFR | OL1-2R04-0015 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00342 |  | 2018-11-20 | 2
036909C-1000-JSS-1320-01 | Job Supply Specification For Pipes | B | 2018-11-19 | IFR | OL1-2R04-0011 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00342 |  | 2018-11-20 | 2
036909C-1028-PDS-0800-2805 | Process Equipment Datasheet - 10-D-2805 - C3R Surge Drum | B | 2018-11-21 | IFD | OL1-2G30-2805 | PE | 2018-11-21 | 036909C-JVD-TRN-00348 | 036909C-JVD-TRN-00348 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00348 |  | 2018-11-21 | 2
036909C-1020-PDS-0500-2040 | Process Equipment Datasheet - 10-T-2040 - Heavy Fuel Oil Stripper | B | 2018-11-21 | IFD | OL1-2G30-2040 | PE | 2018-11-21 | 036909C-JVD-TRN-00347 | 036909C-JVD-TRN-00347 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00347 |  | 2018-11-21 | 2
036909C-1026-PDS-0800-2610 | Process Equipment Datasheet - 10-D-2610 - C3 Hydrog Arsine Guard Bed | A | 2018-11-20 | IFR | OL1-2G30-2610 | PE | 2018-11-21 | 036909C-JVD-TRN-00345 | 036909C-JVD-TRN-00345 | IFR | 2018-12-05 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00345 |  | 2018-11-21 | 2
036909C-1021-PDS-0900-2191 | Process Equipment Datasheet - 10-P-2190- Quench Water Drain Drum Pump | A | 2018-11-20 | IFR | OL1-2G30-2191 | PE | 2018-11-21 | 036909C-JVD-TRN-00346 | 036909C-JVD-TRN-00346 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00346 |  | 2018-11-21 | 2
036909C-1020-PDS-0840-2025 | Process Equipment Datasheet - 10-F-2026 A-B Cracker Bottoms Product Filter | A | 2018-11-21 | IFR | OL1-2G30-2025 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00350 |  | 2018-11-21 | 2
036909C-1020-PDS-0840-2010 | Process Equipment Datasheet - 10-F-2008 A-C Quench Oil Filter | A | 2018-11-21 | IFR | OL1-2G30-2010 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00350 |  | 2018-11-21 | 2
036909C-1020-PDS-0840-2049 | Process Equipment Datasheet - 10-F-2048 A-B Heavy Fuel Oil Filters | A | 2018-11-21 | IFR | OL1-2G30-2049 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00350 |  | 2018-11-21 | 2
036909C-1021-PDS-0840-2104 | Process Equipment Datasheet - 10-F-2105 A-B Quench Oil Reflux Filter | A | 2018-11-21 | IFR | OL1-2G30-2104 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00350 |  | 2018-11-21 | 2
036909C-1000-JSS-1340-01 | Job Supply Specification For Forged Fittings | B | 2018-11-19 | IFR | OL1-2R04-0014 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00342 |  | 2018-11-20 | 2
036909C-1024-PDS-0800-2415 | Process Equipment Datasheet - 10-D-2415 - CG Liquid Dryer Feed Coalescer | A | 2018-11-19 | IFR | OL1-2G30-2415 | PE | 2018-11-20 | 036909C-JVD-TRN-00339 | 036909C-JVD-TRN-00339 | IFR | 2018-12-04 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00339 |  | 2018-11-20 | 2
036909C-1000-JSS-1330-01 | Job Supply Specification For Buttwelding Fittings | B | 2018-11-19 | IFR | OL1-2R04-0013 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00342 |  | 2018-11-20 | 2
036909C-1026-PDS-0900-2663 | Process Equipment Datasheet - 10-P-2660 A-B - Debutanizer Reflux - Product Pumps | A | 2018-11-14 | IFR | OL1-2G30-2663 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00340 |  | 2018-11-20 | 2
036909C-1028-PDS-0900-2816 | Process Equipment Datasheet - 10-P-2815 - Propylene Refrig Recovery Pump | A | 2018-11-14 | IFR | OL1-2G30-2816 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00340 |  | 2018-11-20 | 2
036909C-1000-JSS-1300-01 | General Supply Specification For Piping Material | B | 2018-11-19 | IFR | OL1-2R04-0006 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 | 2019-01-30 | R1-No comments | TPSK-LSPA1-T-MP-00342 |  | 2018-11-20 | 2
036909C-1025-PDS-0900-2586 | Process Equipment Datasheet - 10-P-2586 A-B - Ethane Recycle Pumps | A | 2018-11-14 | IFR | OL1-2G30-2586 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00340 |  | 2018-11-20 | 2
036909C-1025-PDS-0900-2573 | Process Equipment Datasheet - 10-P-2570 A-B - Deethanizer Reflux Pumps | A | 2018-11-14 | IFR | OL1-2G30-2573 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00340 |  | 2018-11-20 | 2
036909C-1055-PDS-1000-5521 | Process Equipment Datasheet - 10-PK-5520 - LP Vent Blower Pkg | A | 2018-11-15 | IFR | OL1-2G30-5521 | PE | 2018-11-19 | 036909C-JVD-TRN-00332 | 036909C-JVD-TRN-00332 | IFR | 2018-12-03 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-PE-00332 |  | 2018-11-19 | 2
036909C-1011-PDS-0117-1101 | Process Equipment Datasheet - 10-H-1100 - USM 36M Cracking Furnace Yields | B | 2018-11-15 | IFD | OL1-2G30-1101 | PE | 2018-11-26 | 036909C-JVD-TRN-00360 | 036909C-JVD-TRN-00360 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00360 |  | 2018-11-26 | 2
036909C-1051-PDS-0800-5140 | Process Equipment Datasheet - 10-D-5140 - Intermittent Blowdown Drum | A | 2018-11-15 | IFR | OL1-2G30-5140 | PE | 2018-11-19 | 036909C-JVD-TRN-00331 | 036909C-JVD-TRN-00331 | IFR | 2018-12-03 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00331 |  | 2018-11-19 | 2
036909C-1052-PDS-0800-5200 | Process Equipment Datasheet - 10-D-5200 - Fuel Gas Drum | A | 2018-11-15 | IFR | OL1-2G30-5200 | PE | 2018-11-19 | 036909C-JVD-TRN-00331 | 036909C-JVD-TRN-00331 | IFR | 2018-12-03 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00331 |  | 2018-11-19 | 2
036909C-1020-PDS-4200-2036 | Process Equipment Datasheet - 10-X-2036 - Quench Fitting | A | 2018-11-19 | IFR | OL1-2G30-2036 | PE | 2018-11-20 | 036909C-JVD-TRN-00338 | 036909C-JVD-TRN-00338 | IFR | 2018-12-04 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00338 |  | 2018-11-20 | 2
036909C-1000-JSD-1300-0011 | Piping Flexibility | A | 2018-11-19 | IFR | OL1-2R04-0030 | MP | 2018-11-20 | 036909C-JVD-TRN-00336 | 036909C-JVD-TRN-00336 | IFR | 2018-12-05 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00336 |  | 2018-11-20 | 2
036909C-1024-PDS-0800-2411 | Process Equipment Datasheet - 10-D-2411 - Cracked Gas Mercury Adsorber | A | 2018-11-19 | IFR | OL1-2G30-2411 | PE | 2018-11-20 | 036909C-JVD-TRN-00339 | 036909C-JVD-TRN-00339 | IFR | 2018-12-04 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00339 |  | 2018-11-20 | 2
036909C-1000-JSD-1300-0008 | JSD For Piping Stress Analysis | A | 2018-11-12 | IFR | OL1-2R04-0032 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 | 2018-12-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-00324 |  | 2018-11-16 | 2
036909C-1012-PDS-0853-1212 | Process Equipment Datasheet - 10-M-1200 1600 - USC 132U Attemperator | A | 2018-11-14 | IFR | OL1-2G30-1212 | PE | 2018-11-16 | 036909C-JVD-TRN-00330 | 036909C-JVD-TRN-00330 | IFR | 2018-11-30 | 2018-12-13 | R1-No comments | TPSK-LSPA1-T-PE-00330 |  | 2018-11-16 | 2
036909C-1012-SR-0125-2007 | Scope of Supply For Cast Intermediate Tube Supports | A | 2018-11-12 | IFQ | OL1-2M56-2007 | ME | 2018-11-16 | 036909C-JVD-TRN-00329 | 036909C-JVD-TRN-00329 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00329 |  | 2018-11-16 | 3
036909C-1051-PDS-0800-5150 | Process Equipment Datasheet - 10-D-5150 - Continuous Blow Down Flash Drum | A | 2018-11-15 | IFR | OL1-2G30-5150 | PE | 2018-11-19 | 036909C-JVD-TRN-00331 | 036909C-JVD-TRN-00331 | IFR | 2018-12-03 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00331 |  | 2018-11-19 | 2
036909C-1011-PDS-0853-1112 | Process Equipment Datasheet - 10-M-1100 - USC 36M Attemperator | A | 2018-11-14 | IFR | OL1-2G30-1112 | PE | 2018-11-16 | 036909C-JVD-TRN-00330 | 036909C-JVD-TRN-00330 | IFR | 2018-11-30 | 2018-12-13 | R1-No comments | TPSK-LSPA1-T-PE-00330 |  | 2018-11-16 | 2
036909C-1012-SP-0125-2007 | Particular Technical Specification for Cast Intermediate Tube Supports | A | 2018-11-12 | IFQ | OL1-2M57-2007 | ME | 2018-11-16 | 036909C-JVD-TRN-00329 | 036909C-JVD-TRN-00329 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00329 |  | 2018-11-16 | 3
036909C-1000-JSD-1300-0002 | Job Specification For Detail Design Piping - Includes ex doc. OL1-2P92-0002 as attachment | B | 2018-11-12 | IFR | OL1-2R04-0002 | MP | 2018-11-16 | 036909C-JVD-TRN-00326 | 036909C-JVD-TRN-00326 | IFR | 2018-12-03 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00012 | Includes ex doc. OL1-2P92-0002 as attachment | 2018-11-16 | 2
036909C-1000-STC-1390-0001 | Piping Standard Construction Drawings - For next revision see document OL1-2R04-0001 - included as attachment | 0 | 2018-11-12 | CAN | OL1-2R04-0001 | MP | 2018-11-16 | 036909C-JVD-TRN-00325 | 036909C-JVD-TRN-00325 | IFR | 2018-12-03 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00325 | For next revision see document OL1-2R04-0001 - included as attachment | 2018-11-16 | 2
036909C-1011-DW-0117-1002 | USC 36M Recycle Furnace General Arrangement Longitudinal Elevation | A | 2018-11-15 | IFR | OL1-2M06-1002 | ME | 2018-11-16 | 036909C-JVD-TRN-00327 | 036909C-JVD-TRN-00327 | IFR | 2018-11-30 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-ME-00327 |  | 2018-11-16 | 2
036909C-1012-MR-0125-2007 | Material Requisition for Cast Intermediate Tube Supports | A | 2018-11-12 | IFQ | OL1-2M55-2007 | ME | 2018-11-16 | 036909C-JVD-TRN-00329 | 036909C-JVD-TRN-00329 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00329 |  | 2018-11-16 | 3
036909C-1012-DW-0117-2002 | USC 132U Cracking Furnace General Arrangement Longitudinal Elevation | A | 2018-11-15 | IFR | OL1-2M06-2002 | ME | 2018-11-16 | 036909C-JVD-TRN-00328 | 036909C-JVD-TRN-00328 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-ME-00328 |  | 2018-11-16 | 2
036909C-1000-JSD-1300-0012 | Pipe Support | A | 2018-11-12 | IFR | OL1-2R04-0012 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 | 2018-12-18 | R1-No comments | TPSK-LSPA1-T-MP-00324 |  | 2018-11-16 | 2
036909C-1000-JSD-1300-0010 | JSD For Auxiliary Piping Supports | A | 2018-11-12 | IFR | OL1-2R04-0034 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 | 2018-12-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-00324 |  | 2018-11-16 | 2
036909C-1000-JSD-1300-0009 | JSD for piping loads on PRK SLW STR IS | A | 2018-11-12 | IFR | OL1-2R04-0033 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 | 2018-12-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-00324 |  | 2018-11-16 | 2
036909C-1051-PDS-0800-5100 | Process Equipment Datasheet - 10-D-5100 - Deaerator | B | 2018-11-14 | IFD | OL1-2G30-5100 | PE | 2018-11-14 | 036909C-JVD-TRN-00318 | 036909C-JVD-TRN-00318, ROC-TPSK-CECO-T-00020 | IFI |  | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-PE-00318 |  | 2018-11-14 | 2
036909C-1052-PDS-0600-5210 | Process Equipment Datasheet - 10-E-5210 - Pilot Gas Vaporizer | A | 2018-11-14 | IFR | OL1-2G30-5210 | PE | 2018-11-15 | 036909C-JVD-TRN-00321 | 036909C-JVD-TRN-00321 | IFR | 2018-11-29 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00321 |  | 2018-11-15 | 2
036909C-1000-SP-0910-0003 | Particular Technical Specification for Cooling Water Pumps | A | 2018-11-14 | IFQ | OL1-2M57-0003 | ME | 2018-11-15 | 036909C-JVD-TRN-00319 | 036909C-JVD-TRN-00319 | IFR | 2018-11-29 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00319 |  | 2018-11-15 | 2
036909C-1028-TDS-0610-2856 | Mechanical Equipment Data Sheet - 10-E-2855 - C2R Condenser | A | 2018-11-14 | IFQ | OL1-2M03-2856 | ME | 2018-11-14 | 036909C-JVD-TRN-00316 | 036909C-JVD-TRN-00316 | IFR | 2018-11-28 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-ME-00316 |  | 2018-11-14 | 2
036909C-1024-PDS-0800-2405 | Process Equipment Datasheet - 10-D-2405 - Gas Dryer Feed KO Drum | A | 2018-11-13 | IFR | OL1-2G30-2405 | PE | 2018-11-14 | 036909C-JVD-TRN-00315 | 036909C-JVD-TRN-00315 | IFR | 2018-11-28 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00315 |  | 2018-11-14 | 2
036909C-1000-SR-0910-0003 | Scope of Supply for Cooling Water Pumps | A | 2018-11-14 | IFQ | OL1-2M56-0003 | ME | 2018-11-15 | 036909C-JVD-TRN-00319 | 036909C-JVD-TRN-00319 | IFR | 2018-11-29 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00319 |  | 2018-11-15 | 2
036909C-1000-MR-0910-0003 | Material Requisition for Cooling Water Pumps | A | 2018-11-14 | IFQ | OL1-2M55-0003 | ME | 2018-11-15 | 036909C-JVD-TRN-00319 | 036909C-JVD-TRN-00319 | IFR | 2018-11-29 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00319 |  | 2018-11-15 | 2
036909C-1051-SP-0910-5109 | Mechanical Equipment Data Sheet - Condensate Pumps | B | 2018-11-12 | IFQ | OL1-2M03-5109 | ME | 2018-11-14 | 036909C-JVD-TRN-00317 | 036909C-JVD-TRN-00317 | IFR | 2018-11-28 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00317 |  | 2018-11-14 | 2
036909C-1051-SP-0910-5101 | Mechanical Equipment Data Sheet for SHP BFW Pumps | B | 2018-11-12 | IFQ | OL1-2M03-5101 | ME | 2018-11-15 | 036909C-JVD-TRN-00322 | 036909C-JVD-TRN-00322 | IFR | 2018-11-29 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00322 |  | 2018-11-15 | 2
036909C-1000-JSS-1654-0001 | Low Voltage Switchgear And Motor Control Center | 0 | 2018-09-20 | IFE | OL1-2R05-0008 | EE | 2018-11-12 | 036909C-JVD-TRN-00309 | 036909C-JVD-TRN-00309 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00309 |  | 2018-11-12 | 3
036909C-1025-TDS-0610-2571 | Mechanical Equipment Data Sheet - 10-E-2570 - Deethanizer Condenser | A | 2018-11-12 | IFQ | OL1-2M03-2571 | ME | 2018-11-13 | 036909C-JVD-TRN-00310 | 036909C-JVD-TRN-00310 | IFR | 2018-11-27 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00310 |  | 2018-11-13 | 2
036909C-1053-SP-0910-5361 | Mechanical Equipment Data Sheet - CTU Cooling Water Pumps | B | 2018-11-12 | IFQ | OL1-2M03-5361 | ME | 2018-11-14 | 036909C-JVD-TRN-00317 | 036909C-JVD-TRN-00317 | IFR | 2018-11-28 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00317 |  | 2018-11-14 | 2
036909C-1012-MR-0191-2006 | Material Requisition for Furnace Burners - For next Rev. see Doc. Client Ref. OL1-2C13-306000 | A | 2018-11-07 | IFQ | OL1-2C13-306000 | ME | 2018-11-13 | 036909C-JVD-TRN-00313 | 036909C-JVD-TRN-00313 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00313 | For next Rev. see Doc. Client Ref. OL1-2C13-306000 | 2018-11-13 | 3
036909C-1028-TDS-0610-2857 | Mechanical Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer | A | 2018-11-13 | IFQ | OL1-2M03-2857 | ME | 2018-11-13 | 036909C-JVD-TRN-00312 | 036909C-JVD-TRN-00312 | IFR | 2018-11-27 | 2019-02-11 | R2-Comments as noted | TPSK-LSPA1-T-ME-00312 |  | 2018-11-13 | 2
036909C-1012-SP-0191-2006 | Particular Technical Specification for Furnace Burners | A | 2018-11-07 | IFQ | OL1-2M57-2006 | ME | 2018-11-13 | 036909C-JVD-TRN-00313 | 036909C-JVD-TRN-00313 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00313 |  | 2018-11-13 | 3
036909C-1012-SR-0191-2006 | Scope of Supply for Furnace Burners | A | 2018-11-07 | IFQ | OL1-2M56-2006 | ME | 2018-11-13 | 036909C-JVD-TRN-00313 | 036909C-JVD-TRN-00313 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00313 |  | 2018-11-13 | 3
036909C-1000-JSS-0910-0002 | ME-050 Centrifugal Pump (Non API) | A | 2018-10-25 | IFR | OL1-2R03-0500 | ME | 2018-11-12 | 036909C-JVD-TRN-00308 | 036909C-JVD-TRN-00308 | IFR | 2018-11-27 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-ME-00308 |  | 2018-11-12 | 2
036909C-1056-PDS-2600-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package | A | 2018-11-06 | IFR | OL1-2G30-5644 | PE | 2018-11-06 | 036909C-JVD-TRN-00281 | 036909C-JVD-TRN-00281 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00281 |  | 2018-11-06 | 2
036909C-1025-PDS-0500-2540 | Process Equipment Datasheet - 10-T-2540 - 10-D-2540 - Demethanizer & Reflux Drum | B | 2018-11-09 | IFD | OL1-2G30-2540 | PE | 2018-11-09 | 036909C-JVD-TRN-00306 | 036909C-JVD-TRN-00306 | IFI |  | 2018-11-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00306 |  | 2018-11-09 | 1
036909C-1000-JSS-1641-0001 | Oil Filled Distribution Transformer | 0 | 2018-09-20 | IMP | OL1-2R05-0003 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | 2018-11-05 | 3
036909C-1025-PDS-0800-2506 | Process Equipment Datasheet - 10-D-2506 - Demeth Prefrac Feed Separator No 2 | B | 2018-11-08 | IFD | OL1-2G30-2506 | PE | 2018-11-09 | 036909C-JVD-TRN-00303 | 036909C-JVD-TRN-00303 | IFI |  | 2018-11-26 | R1-No comments | TPSK-LSPA1-T-PE-00303 |  | 2018-11-09 | 2
036909C-1056-PDS-2600-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg | A | 2018-11-06 | IFR | OL1-2G30-5650 | PE | 2018-11-06 | 036909C-JVD-TRN-00281 | 036909C-JVD-TRN-00281 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00281 |  | 2018-11-06 | 2
036909C-1000-NM-0001-1001 | Overall Material Balance | A | 2018-08-03 | IFI | OL1-2G44-1001 | PE | 2018-08-06 | 036909C-JVD-TRN-00009 | 036909C-JVD-TRN-00009, ROC-TPSK-CECO-T-00012 | IFI |  | 2018-08-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-00009 |  | 2018-08-07 | 3
036909C-1025-SP-0510-2540 | Mechanical Equipment Data Sheet - Demethanizer and Demethanizer Reflux Drum | A | 2018-11-09 | IFQ | OL1-2M03-2540 | ME | 2018-11-09 | 036909C-JVD-TRN-00304 | 036909C-JVD-TRN-00304 | IFR | 2018-11-23 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00304 |  | 2018-11-09 | 2
036909C-1000-NM-0001-1004 | Heat & Material Balance - Design Case 9 | A | 2018-08-30 | IFI | OL1-2G44-1004 | PE | 2018-08-31 | 036909C-JVD-TRN-00032 | 036909C-JVD-TRN-00032, ROC-TPSK-CECO-T-00012 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00032 |  | 2018-09-03 | 3
036909C-1000-NM-0001-1002 | Heat & Material Balance - Design Case 6 | A | 2018-08-30 | IFI | OL1-2G44-1002 | PE | 2018-08-31 | 036909C-JVD-TRN-00032 | 036909C-JVD-TRN-00032, ROC-TPSK-CECO-T-00012 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00032 |  | 2018-09-03 | 3
036909C-1024-PDS-0800-2420 | Process Equipment Datasheet - 10-D-2420 A-B - CG Liquid Dryer | A | 2018-11-08 | IFR | OL1-2G30-2420 | PE | 2018-11-09 | 036909C-JVD-TRN-00301 | 036909C-JVD-TRN-00301 | IFR | 2018-11-23 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00301 |  | 2018-11-09 | 2
036909C-1025-PDS-0800-2508 | Process Equipment Datasheet - 10-D-2508 - Demeth Prefrac Feed Separator No 3 | B | 2018-11-08 | IFD | OL1-2G30-2508 | PE | 2018-11-09 | 036909C-JVD-TRN-00303 | 036909C-JVD-TRN-00303 | IFI |  | 2018-11-26 | R1-No comments | TPSK-LSPA1-T-PE-00303 |  | 2018-11-09 | 2
036909C-1056-PDS-0200-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg | A | 2018-11-06 | IFR | OL1-2G30-5653 | PE | 2018-11-06 | 036909C-JVD-TRN-00282 | 036909C-JVD-TRN-00282 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00282 |  | 2018-11-06 | 2
036909C-1000-NM-0001-1003 | Heat & Material Balance - Design Case 8 | A | 2018-08-30 | IFI | OL1-2G44-1003 | PE | 2018-08-31 | 036909C-JVD-TRN-00032 | 036909C-JVD-TRN-00032, ROC-TPSK-CECO-T-00012 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00032 |  | 2018-09-03 | 3
036909C-1026-PDS-0900-2647 | Process Equipment Datasheet - 10-P-2647 - HP Propylene - Off Spec Pumps | A | 2018-11-08 | IFR | OL1-2G30-2647 | PE | 2018-11-09 | 036909C-JVD-TRN-00302 | 036909C-JVD-TRN-00302 | IFR | 2018-11-23 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00302 |  | 2018-11-09 | 2
036909C-1025-PDS-0800-2504 | Process Equipment Datasheet - 10-D-2504 - Demeth Prefrac Feed Separator No 1 | B | 2018-11-08 | IFD | OL1-2G30-2504 | PE | 2018-11-09 | 036909C-JVD-TRN-00303 | 036909C-JVD-TRN-00303 | IFI |  | 2018-11-26 | R1-No comments | TPSK-LSPA1-T-PE-00303 |  | 2018-11-09 | 2
036909C-1020-PDS-0600-2015 | Process Equipment Datasheet - 10-E-2008 A-C - LS2 Steam Generators | A | 2018-11-09 | IFR | OL1-2G30-2015 | PE | 2018-11-09 | 036909C-JVD-TRN-00305 | 036909C-JVD-TRN-00305 | IFR | 2018-11-23 | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00305 |  | 2018-11-09 | 2
036909C-1027-DI-0007-2701 | Area Basis of Design - 270 Gasoline Hydrogenation -GHU-1 | A | 2018-11-09 | IFA | OL1-2G05-2701 | PE | 2018-11-12 | 036909C-JVD-TRN-00307 | 036909C-JVD-TRN-00307, ROC-TPSK-CECO-T-00001 | IFA | 2018-11-26 | 2019-02-04 | A1-Approved without comments | TPSK-LSPA1-T-PE-00307 |  | 2018-11-12 | 1
036909C-1056-PDS-2600-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg | A | 2018-11-06 | IFR | OL1-2G30-5670 | PE | 2018-11-06 | 036909C-JVD-TRN-00281 | 036909C-JVD-TRN-00281 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00281 |  | 2018-11-06 | 2
036909C-1027-DI-0007-2702 | Area Basis of Design - Area 275 C4-C5 Hydrogenation | A | 2018-11-09 | IFA | OL1-2G05-2702 | PE | 2018-11-12 | 036909C-JVD-TRN-00307 | 036909C-JVD-TRN-00307, ROC-TPSK-CECO-T-00001 | IFA | 2018-11-26 | 2019-02-04 | A1-Approved without comments | TPSK-LSPA1-T-PE-00307 |  | 2018-11-12 | 1
036909C-1027-DI-0007-2702 | Area Basis of Design - Area 275 C4-C5 Hydrogenation | B | 2019-05-15 | IFD | OL1-2G05-2702 | PE | 2019-05-15 | 036909C-JVD-TRN-01667 | 036909C-JVD-TRN-01667 | IFA | 2019-05-30 | 2019-06-21 | R2-Comments as noted | TPSK-LSPA1-T-PE-01667 |  | 2019-05-16 | 1
036909C-1000-PO-036909C001P83-083 | Vendor's Acknowledgment of Purchase Order for Safety Supervisory System - MR 1530-0002 | 0 | 2019-08-16 | IFI | OL1-2C51-0118 | PL | 2019-08-16 | 036909C-JVD-TRN-02690 | 036909C-JVD-TRN-02690 |  |  |  | Transmitted | TPSK-LSPA1-T-PL-02690 |  | 2019-09-24 | 3
036909C-1054-PID-0031-5412 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Instrument Air Distribution - Sheet 2 | C | 2019-08-26 | IDD1 | OL1-2G43-5412 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1054-PID-0031-5411 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Instrument Air Distribution - Sheet 1 | C | 2019-08-26 | IDD1 | OL1-2G43-5411 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1054-PID-0031-5410 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Instrument Air Receiver | C | 2019-08-26 | IDD1 | OL1-2G43-5410 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5390 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Return - Cooling Water Supply B L | A | 2019-08-26 | IDD1 | OL1-2G43-5390 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5352 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Corrosion Inhibitor Injection | C | 2019-08-26 | IDD1 | OL1-2G43-5352 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5351 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Chemical Injection | C | 2019-08-26 | IDD1 | OL1-2G43-5351 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5339 | P&Id - Olefins Unit 10 - Cooling Water - CTU Cooling Water Pump Turbine Details | A | 2019-08-26 | IDD1 | OL1-2G43-5339 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5333 | P&Id - Olefins Unit 10 - Cooling Water -Olefins CW Pump Turbine Details - Sheet 2 | A | 2019-08-26 | IDD1 | OL1-2G43-5333 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5326 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 7 | C | 2019-08-26 | IDD1 | OL1-2G43-5326 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5324 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 5 | C | 2019-08-26 | IDD1 | OL1-2G43-5324 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5322 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 3 | C | 2019-08-26 | IDD1 | OL1-2G43-5322 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5320 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 1 | C | 2019-08-26 | IDD1 | OL1-2G43-5320 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5317 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Filter Backwash | C | 2019-08-26 | IDD1 | OL1-2G43-5317 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5315 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Side Stream Filter Package Sheet 3 | C | 2019-08-26 | IDD1 | OL1-2G43-5315 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5314 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Side Stream Filter Package | A | 2019-08-26 | IDD1 | OL1-2G43-5314 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5313 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Side Stream Filter Package | A | 2019-08-26 | IDD1 | OL1-2G43-5313 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5311 | P&Id - Olefins Unit 10 - Cooling Water - CTU Cooling Water Supply | C | 2019-08-26 | IDD1 | OL1-2G43-5311 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5310 | P&Id - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Suppy | C | 2019-08-26 | IDD1 | OL1-2G43-5310 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5307 | P&Id - Olefins Unit 10 - Cooling Water - CTU Cooling Water Supply Pumps | C | 2019-08-26 | IDD1 | OL1-2G43-5307 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5306 | P&Id - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 2 | C | 2019-08-26 | IDD1 | OL1-2G43-5306 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5305 | P&Id - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 1 | C | 2019-08-26 | IDD1 | OL1-2G43-5305 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5303 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Tower - Sheet 3 | C | 2019-08-26 | IDD1 | OL1-2G43-5303 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5302 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Tower - Sheet 2 | C | 2019-08-26 | IDD1 | OL1-2G43-5302 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1053-PID-0031-5301 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Tower - Sheet 1 | C | 2019-08-26 | IDD1 | OL1-2G43-5301 | PE | 2019-08-29 | 036909C-JVD-TRN-02541 | 036909C-JVD-TRN-02541 | IFR | 2019-09-13 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02541 |  | 2019-08-30 | 2
036909C-1059-PID-0031-5930 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - VLP BFW Lube Oil Pump Turbine Details | 0 | 2019-08-26 | CAN | OL1-2G43-5930 | PE | 2019-08-28 | 036909C-JVD-TRN-02516 | 036909C-JVD-TRN-02516 | IFR | 2019-09-12 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02516 |  | 2019-08-29 | 2
036909C-1059-PID-0031-5929 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - VLP BFW Pump Turbine Details | 0 | 2019-08-26 | CAN | OL1-2G43-5929 | PE | 2019-08-28 | 036909C-JVD-TRN-02516 | 036909C-JVD-TRN-02516 | IFR | 2019-09-12 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02516 |  | 2019-08-29 | 2
036909C-1059-PID-0031-5928 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Lube Oil Pump Turbine B Details | 0 | 2019-08-26 | CAN | OL1-2G43-5928 | PE | 2019-08-28 | 036909C-JVD-TRN-02516 | 036909C-JVD-TRN-02516 | IFR | 2019-09-12 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02516 |  | 2019-08-29 | 2
036909C-1059-PID-0031-5927 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Lube Oil Pump Turbine A Details | 0 | 2019-08-26 | CAN | OL1-2G43-5927 | PE | 2019-08-28 | 036909C-JVD-TRN-02516 | 036909C-JVD-TRN-02516 | IFR | 2019-09-12 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02516 |  | 2019-08-29 | 2
036909C-1059-PID-0031-5925 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Pump Turbine Details | 0 | 2019-08-26 | CAN | OL1-2G43-5925 | PE | 2019-08-28 | 036909C-JVD-TRN-02516 | 036909C-JVD-TRN-02516 | IFR | 2019-09-12 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02516 |  | 2019-08-29 | 2
036909C-1059-PID-0031-5922 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - CTU Cooling Water Pump Turbine Details | 0 | 2019-08-26 | CAN | OL1-2G43-5922 | PE | 2019-08-28 | 036909C-JVD-TRN-02516 | 036909C-JVD-TRN-02516 | IFR | 2019-09-12 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02516 |  | 2019-08-29 | 2
036909C-1059-PID-0031-5921 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Olefins CW Pump Turbine Details - Sheet 2 | 0 | 2019-08-26 | CAN | OL1-2G43-5921 | PE | 2019-08-28 | 036909C-JVD-TRN-02516 | 036909C-JVD-TRN-02516 | IFR | 2019-09-12 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02516 |  | 2019-08-29 | 2
036909C-1059-PID-0031-5920 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Olefins CW Pump Turbine Details - Sheet 1 | 0 | 2019-08-26 | CAN | OL1-2G43-5920 | PE | 2019-08-28 | 036909C-JVD-TRN-02516 | 036909C-JVD-TRN-02516 | IFR | 2019-09-12 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02516 |  | 2019-08-29 | 2
036909C-1059-PID-0031-5915 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Condensate Pump Turbine Details | 0 | 2019-08-26 | CAN | OL1-2G43-5915 | PE | 2019-08-28 | 036909C-JVD-TRN-02516 | 036909C-JVD-TRN-02516 | IFR | 2019-09-12 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02516 |  | 2019-08-29 | 2
036909C-1056-PID-0031-5642 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 3 | C | 2019-08-16 | IDD1 | OL1-2G43-5642 | PE | 2019-08-28 | 036909C-JVD-TRN-02516 | 036909C-JVD-TRN-02516 | IFR | 2019-09-12 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02516 |  | 2019-08-29 | 2
036909C-1056-PID-0031-5607 | P&ID - Olefins Unit 10 - Wastewater - Hydroblast Sump | C | 2019-08-16 | IDD1 | OL1-2G43-5607 | PE | 2019-08-28 | 036909C-JVD-TRN-02516 | 036909C-JVD-TRN-02516 | IFR | 2019-09-12 | 2019-09-17 | R2-Comments as noted | TPSK-LSPA1-T-PE-02516 |  | 2019-08-28 | 2
036909C-1023-SP-1513-2302 | Instrument Interlock Descriptions Area 23 - Caustic and Spent Caustic Treatment | B | 2019-07-26 | IBD | OL1-2G50-2302 | PE | 2019-07-30 | 036909C-JVD-TRN-02289 | 036909C-JVD-TRN-02289 | IFR | 2019-08-14 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02289 |  | 2019-07-31 | 2
036909C-1022-SP-1513-2202 | Instrument Interlock Descriptions Area 22 - Cracked Gas Compressor | B | 2019-07-24 | IBD | OL1-2G50-2202 | PE | 2019-07-30 | 036909C-JVD-TRN-02289 | 036909C-JVD-TRN-02289 | IFR | 2019-08-14 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02289 |  | 2019-07-31 | 2
036909C-1023-DW-1514-2301 | Cause and Effect Diagram Area 23: Caustic and Spent Caustic Treatment | B | 2019-07-26 | IBD | OL1-2G50-2301 | PE | 2019-07-30 | 036909C-JVD-TRN-02288 | 036909C-JVD-TRN-02288 | IFR | 2019-08-14 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02288 |  | 2019-07-31 | 2
036909C-1022-DW-1514-2201 | Cause and Effect Diagram Area 22 - Cracked Gas Compressor | C | 2019-07-24 | IBD | OL1-2G50-2201 | PE | 2019-07-30 | 036909C-JVD-TRN-02288 | 036909C-JVD-TRN-02288 | IFR | 2019-08-14 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02288 |  | 2019-07-31 | 2
036909C-1051-PDS-0600-5107 | Process Equipment Datasheet - 10-E-5112 - Suspect Cond Flash Drum Vent Condenser | C | 2019-08-02 | IFD | OL1-2G30-5107 | PE | 2019-08-05 | 036909C-JVD-TRN-02346 | 036909C-JVD-TRN-02346 | IFR | 2019-08-20 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02346 |  | 2019-08-06 | 2
036909C-1031-PDS-0800-3190 | Process Equipment Data Sheet - 10-D-3190 - NMP Slop Drum | C | 2019-08-02 | IFD | OL1-2G30-3190 | PE | 2019-08-05 | 036909C-JVD-TRN-02346 | 036909C-JVD-TRN-02346 | IFR | 2019-08-20 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02346 |  | 2019-08-06 | 2
036909C-1031-PDS-0800-3180 | Process Equipment Data Sheet - 10-D-3180 - BDU Knock-Out Drum | C | 2019-08-01 | IFD | OL1-2G30-3180 | PE | 2019-08-05 | 036909C-JVD-TRN-02346 | 036909C-JVD-TRN-02346 | IFR | 2019-08-20 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02346 |  | 2019-08-06 | 2
036909C-1031-PDS-0800-3161 | Process Equipment Data Sheet - 10-D-3160 - BDU Condensate Drum | C | 2019-08-01 | IFD | OL1-2G30-3161 | PE | 2019-08-05 | 036909C-JVD-TRN-02346 | 036909C-JVD-TRN-02346 | IFR | 2019-08-20 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02346 |  | 2019-08-06 | 2
036909C-1031-PDS-0800-3126 | Process Equipment Data Sheet - 10-D-3126 - Ejector Seal Drum | C | 2019-08-01 | IFD | OL1-2G30-3126 | PE | 2019-08-05 | 036909C-JVD-TRN-02346 | 036909C-JVD-TRN-02346 | IFR | 2019-08-20 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02346 |  | 2019-08-06 | 2
036909C-1031-PDS-0800-3112 | Process Equipment Data Sheet - 10-D-3110 - Water Washer Accumulator | C | 2019-08-01 | IFD | OL1-2G30-3112 | PE | 2019-08-05 | 036909C-JVD-TRN-02346 | 036909C-JVD-TRN-02346 | IFR | 2019-08-20 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02346 |  | 2019-08-06 | 2
036909C-1031-PDS-0800-3100 | Process Equipment Data Sheet - 10-D-3100 - Solvent Regen Drum | C | 2019-08-01 | IFD | OL1-2G30-3100 | PE | 2019-08-05 | 036909C-JVD-TRN-02346 | 036909C-JVD-TRN-02346 | IFR | 2019-08-20 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02346 |  | 2019-08-06 | 2
036909C-1030-PDS-0800-3082 | Process Equipment Data Sheet - 10-D-3080 - Butadiene Tower Reflux Drum | C | 2019-08-01 | IFD | OL1-2G30-3082 | PE | 2019-08-05 | 036909C-JVD-TRN-02346 | 036909C-JVD-TRN-02346 | IFR | 2019-08-20 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02346 |  | 2019-08-06 | 2
036909C-1030-PDS-0800-3065 | Process Equipment Data Sheet - 10-D-3062 - C4 Acetylene Accumulator | C | 2019-08-01 | IFD | OL1-2G30-3065 | PE | 2019-08-05 | 036909C-JVD-TRN-02346 | 036909C-JVD-TRN-02346 | IFR | 2019-08-20 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02346 |  | 2019-08-06 | 2
036909C-1030-PDS-0800-3064 | Process Equipment Datasheet - 10-D-3060 - BDU HC - Water Separator | C | 2019-08-01 | IFD | OL1-2G30-3064 | PE | 2019-08-05 | 036909C-JVD-TRN-02346 | 036909C-JVD-TRN-02346 | IFR | 2019-08-20 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02346 |  | 2019-08-06 | 2
036909C-1030-PDS-0800-3032 | Process Equipment Data Sheet - 10-D-3030 - After Washer Reflux Drum | C | 2019-08-01 | IFD | OL1-2G30-3032 | PE | 2019-08-05 | 036909C-JVD-TRN-02346 | 036909C-JVD-TRN-02346 | IFR | 2019-08-20 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02346 |  | 2019-08-06 | 2
036909C-1030-PDS-0800-3022 | Process Equipment Data Sheet - 10-D-3020 - Main Washer Reflux Drum | C | 2019-08-01 | IFD | OL1-2G30-3022 | PE | 2019-08-05 | 036909C-JVD-TRN-02346 | 036909C-JVD-TRN-02346 | IFR | 2019-08-20 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02346 |  | 2019-08-06 | 2
036909C-1030-PDS-0800-3003 | Process Equipment Data Sheet - 10-D-3000 - Predistillation Tower Reflux Drum | C | 2019-08-01 | IFD | OL1-2G30-3003 | PE | 2019-08-05 | 036909C-JVD-TRN-02346 | 036909C-JVD-TRN-02346 | IFR | 2019-08-20 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02346 |  | 2019-08-06 | 2
036909C-1030-PDS-0800-3002 | Process Equipment Data Sheet - 10-D-3002 - Predistillation Feed Drum | C | 2019-08-01 | IFD | OL1-2G30-3002 | PE | 2019-08-05 | 036909C-JVD-TRN-02346 | 036909C-JVD-TRN-02346 | IFR | 2019-08-20 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02346 |  | 2019-08-06 | 2
036909C-1000-NM-0001-1006 | Heat & Material Balance - Butadiene Unit BDU | 0 | 2019-08-01 | IFI | OL1-2G44-1006 | PE | 2019-08-02 | 036909C-JVD-TRN-02334 | 036909C-JVD-TRN-02334 | IFI |  | 2019-09-11 | Response to Client Comments emailed Sept-23-2019 R2-Comments as noted | TPSK-LSPA1-T-PE-02334 |  | 2019-08-05 | 3
036909C-1000-NM-0001-1005 | Heat & Material Balance - C3 Hydrogenation Unit & Gasoline Hydrogenation GHU & C4-C5 Hydrogenation Unit | 0 | 2019-08-01 | IFI | OL1-2G44-1005 | PE | 2019-08-02 | 036909C-JVD-TRN-02334 | 036909C-JVD-TRN-02334 | IFI |  | 2019-09-11 | Response to Client Comments emailed Sept-23-2019 R2-Comments as noted | TPSK-LSPA1-T-PE-02334 |  | 2019-08-05 | 3
036909C-1000-NM-0001-1004 | Heat & Material Balance - Design Case 9 | 0 | 2019-08-01 | IFI | OL1-2G44-1004 | PE | 2019-08-02 | 036909C-JVD-TRN-02334 | 036909C-JVD-TRN-02334 | IFI |  | 2019-09-11 | Response to Client Comments emailed Sept-23-2019 R2-Comments as noted | TPSK-LSPA1-T-PE-02334 |  | 2019-08-05 | 3
036909C-1000-NM-0001-1003 | Heat & Material Balance - Design Case 8 | 0 | 2019-08-01 | IFI | OL1-2G44-1003 | PE | 2019-08-02 | 036909C-JVD-TRN-02334 | 036909C-JVD-TRN-02334 | IFI |  | 2019-09-11 | Response to Client Comments emailed Sept-23-2019 R2-Comments as noted | TPSK-LSPA1-T-PE-02334 |  | 2019-08-05 | 3
036909C-1000-NM-0001-1002 | Heat & Material Balance - Design Case 6 | 0 | 2019-08-01 | IFI | OL1-2G44-1002 | PE | 2019-08-02 | 036909C-JVD-TRN-02334 | 036909C-JVD-TRN-02334 | IFI |  | 2019-09-11 | Response to Client Comments emailed Sept-23-2019 R2-Comments as noted | TPSK-LSPA1-T-PE-02334 |  | 2019-08-05 | 3
036909C-1029-DW-1514-2901 | Cause And Effect Diagram Area 29 - Ethylene Auxiliaries | B | 2019-08-05 | IBD | OL1-2G50-2901 | PE | 2019-08-05 | 036909C-JVD-TRN-02343 | 036909C-JVD-TRN-02343 | IFR | 2019-08-20 | 2019-09-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-02343 |  | 2019-08-06 | 2
036909C-1039-PDS-0800-3910 | Process Equipment Data Sheet - 10-D-3908 - Predistillation Inhibitor Drum | C | 2019-08-12 | IFD | OL1-2G30-3910 | PE | 2019-08-13 | 036909C-JVD-TRN-02427 | 036909C-JVD-TRN-02427 | IFR | 2019-08-28 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02427 |  | 2019-08-15 | 2
036909C-1039-PDS-0800-3904 | Process Equipment Data Sheet - 10-D-3904 - BDU Product Inhibitor Drum | C | 2019-08-08 | IFD | OL1-2G30-3904 | PE | 2019-08-13 | 036909C-JVD-TRN-02427 | 036909C-JVD-TRN-02427 | IFR | 2019-08-28 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02427 |  | 2019-08-15 | 2
036909C-1039-PDS-0800-3902 | Process Equipment Data Sheet - 10-D-3902 - BDU Solvent Inhibitor Drum | C | 2019-08-08 | IFD | OL1-2G30-3902 | PE | 2019-08-13 | 036909C-JVD-TRN-02427 | 036909C-JVD-TRN-02427 | IFR | 2019-08-28 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02427 |  | 2019-08-15 | 2
036909C-1031-PDS-0800-3151 | Process Equipment Data Sheet - 10-D-3150 - BDU Condensate Flash Drum | C | 2019-08-12 | IFD | OL1-2G30-3151 | PE | 2019-08-13 | 036909C-JVD-TRN-02427 | 036909C-JVD-TRN-02427 | IFR | 2019-08-28 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02427 |  | 2019-08-15 | 2
036909C-1030-PDS-0600-3098 | Process Equipment Datasheet - 10-E-3098 - Butadiene Product Subcooler | C | 2019-08-16 | IFD | OL1-2G30-3098 | PE | 2019-08-20 | 036909C-JVD-TRN-02461 | 036909C-JVD-TRN-02461 | IFR | 2019-09-04 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02461 |  | 2019-08-21 | 2
036909C-1030-PDS-0600-3085 | Process Equipment Datasheet - 10-E-3085 A-B - Butadiene Tower Reboiler | C | 2019-08-16 | IFD | OL1-2G30-3085 | PE | 2019-08-20 | 036909C-JVD-TRN-02461 | 036909C-JVD-TRN-02461 | IFR | 2019-09-04 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02461 |  | 2019-08-21 | 2
036909C-1030-PDS-0600-3084 | Process Equipment Datasheet - 10-E-3084 - Butadiene Tower Trim Reboiler | C | 2019-08-16 | IFD | OL1-2G30-3084 | PE | 2019-08-20 | 036909C-JVD-TRN-02461 | 036909C-JVD-TRN-02461 | IFR | 2019-09-04 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02461 |  | 2019-08-21 | 2
036909C-1030-PDS-0600-3081 | Process Equipment Datasheet - 10-E-3080 A-B - Butadiene Tower Condenser | C | 2019-08-16 | IFD | OL1-2G30-3081 | PE | 2019-08-20 | 036909C-JVD-TRN-02461 | 036909C-JVD-TRN-02461 | IFR | 2019-09-04 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02461 |  | 2019-08-21 | 2
036909C-1030-PDS-0600-3071 | Process Equipment Datasheet - 10-E-3070 - Water - NMP Cooler | C | 2019-08-16 | IFD | OL1-2G30-3071 | PE | 2019-08-20 | 036909C-JVD-TRN-02461 | 036909C-JVD-TRN-02461 | IFR | 2019-09-04 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02461 |  | 2019-08-21 | 2
036909C-1030-PDS-0600-3063 | Process Equipment Datasheet - 10-E-3060 - C4 Acetylene Washer Condenser | C | 2019-08-16 | IFD | OL1-2G30-3063 | PE | 2019-08-20 | 036909C-JVD-TRN-02461 | 036909C-JVD-TRN-02461 | IFR | 2019-09-04 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02461 |  | 2019-08-21 | 2
036909C-1030-PDS-0600-3031 | Process Equipment Datasheet - 10-E-3030 - After Washer Condenser | C | 2019-08-18 | IFD | OL1-2G30-3031 | PE | 2019-08-20 | 036909C-JVD-TRN-02461 | 036909C-JVD-TRN-02461 | IFR | 2019-09-04 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02461 |  | 2019-08-21 | 2
036909C-1030-PDS-0600-3021 | Process Equipment Datasheet - 10-E-3020 - Main Washer Condenser | C | 2019-08-16 | IFD | OL1-2G30-3021 | PE | 2019-08-20 | 036909C-JVD-TRN-02461 | 036909C-JVD-TRN-02461 | IFR | 2019-09-04 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02461 |  | 2019-08-21 | 2
036909C-1030-PDS-0600-3018 | Process Equipment Datasheet - 10-E-3018 A-B - Solvent Cooler | C | 2019-08-16 | IFD | OL1-2G30-3018 | PE | 2019-08-20 | 036909C-JVD-TRN-02461 | 036909C-JVD-TRN-02461 | IFR | 2019-09-04 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02461 |  | 2019-08-21 | 2
036909C-1030-PDS-0600-3015 | Process Equipment Datasheet - 10-E-3015 - C4 Trim Vaporizer | C | 2019-08-16 | IFD | OL1-2G30-3015 | PE | 2019-08-20 | 036909C-JVD-TRN-02461 | 036909C-JVD-TRN-02461 | IFR | 2019-09-04 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02461 |  | 2019-08-21 | 2
036909C-1030-PDS-0600-3014 | Process Equipment Datasheet - 10-E-3014 A-B - C4 Trim Vaporizer | C | 2019-08-16 | IFD | OL1-2G30-3014 | PE | 2019-08-20 | 036909C-JVD-TRN-02461 | 036909C-JVD-TRN-02461 | IFR | 2019-09-04 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02461 |  | 2019-08-21 | 2
036909C-1030-PDS-0600-3005 | Process Equipment Datasheet - 10-E-3005 - Predistillation Tower Reboiler | C | 2019-07-24 | IFD | OL1-2G30-3005 | PE | 2019-08-20 | 036909C-JVD-TRN-02461 | 036909C-JVD-TRN-02461 | IFR | 2019-09-04 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02461 |  | 2019-08-21 | 2
036909C-1030-PDS-0600-3004 | Process Equipment Datasheet - 10-E-3004 A-B - Predistillation Tower Trim Reboiler | C | 2019-08-16 | IFD | OL1-2G30-3004 | PE | 2019-08-20 | 036909C-JVD-TRN-02461 | 036909C-JVD-TRN-02461 | IFR | 2019-09-04 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02461 |  | 2019-08-21 | 2
036909C-1030-PDS-0600-3001 | Process Equipment Datasheet - 10-E-3000 - Predistillation Tower Condenser | C | 2019-08-16 | IFD | OL1-2G30-3001 | PE | 2019-08-20 | 036909C-JVD-TRN-02461 | 036909C-JVD-TRN-02461 | IFR | 2019-09-04 | 2019-09-23 | R1-No comments | TPSK-LSPA1-T-PE-02461 |  | 2019-08-21 | 2
036909C-1000-JSS-1370-0001 | Job Supply Specification For Bolting | A | 2019-09-06 | IFR | OL1-2R04-0017 | MP | 2019-09-09 | 036909C-JVD-TRN-02591 | 036909C-JVD-TRN-02591 | IFR | 2019-09-24 | 2019-09-18 | R1-No comments | TPSK-LSPA1-T-MP-02591 |  | 2019-09-10 | 2
036909C-1000-JSS-1360-0001 | Job Supply Specification For Gaskets | A | 2019-09-06 | IFR | OL1-2R04-0016 | MP | 2019-09-09 | 036909C-JVD-TRN-02591 | 036909C-JVD-TRN-02591 | IFR | 2019-09-24 | 2019-09-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-02591 |  | 2019-09-10 | 2
036909C-1000-DW-1703-0001 | Key Plan For Structures | B | 2019-06-28 | IBD | OL1-2K25-0002 | CV | 2019-07-03 | 036909C-JVD-TRN-02065 | 036909C-JVD-TRN-02065 | IFA | 2019-07-18 | 2019-09-17 | A1-Approved without comments | TPSK-LSPA1-T-CV-02065 |  | 2019-07-04 | 1
036909C-105F-DW-0051-0001 | Detail Plot Plan Zone 5F HP & Polyolefins Flares Unit | B | 2019-08-06 | IBD | OL1-2P06-0014 | MP | 2019-08-20 | 036909C-JVD-TRN-02460 | 036909C-JVD-TRN-02460 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-MP-02460 |  | 2019-08-21 | 2
036909C-1056-PID-0031-5662 | P&ID - Olefins Unit 10 - Wastewater - Dewatering System | C | 2019-08-16 | IDD1 | OL1-2G43-5662 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5667 | P&ID - Olefins Unit 10 - Wastewater - Oily Sludge Tank | C | 2019-08-16 | IDD1 | OL1-2G43-5667 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5666 | P&ID - Olefins Unit 10 - Wastewater - Slop Oil Tank B | C | 2019-08-16 | IDD1 | OL1-2G43-5666 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5665 | P&ID - Olefins Unit 10 - Wastewater - Slop Oil Tank A | C | 2019-08-16 | IDD1 | OL1-2G43-5665 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5658 | P&ID - Olefins Unit 10 - Wastewater - Bio Treatment Package | C | 2019-08-16 | IDD1 | OL1-2G43-5658 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5657 | P&ID - Olefins Unit 10 - Wastewater - Bio Equalization Pit | C | 2019-08-16 | IDD1 | OL1-2G43-5657 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5655 | P&ID - Olefins Unit 10 - Wastewater - Waste Water Cpi - Igf Package | C | 2019-08-16 | IDD1 | OL1-2G43-5655 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5651 | P&ID - Olefins Unit 10 - Wastewater - CWWT Area Oily Wastewater Sump | C | 2019-08-16 | IDD1 | OL1-2G43-5651 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5650 | P&ID - Olefins Unit 10 - Wastewater - CT Area Oily Wastewater Sump | C | 2019-08-16 | IDD1 | OL1-2G43-5650 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5641 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 2 | 0 | 2019-08-16 | CAN | OL1-2G43-5641 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5640 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 1 | 0 | 2019-08-16 | CAN | OL1-2G43-5640 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5610 | P&ID - Olefins Unit 10 - Wastewater - Oily Waste Water Collection | C | 2019-08-16 | IDD1 | OL1-2G43-5610 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5609 | P&ID - Olefins Unit 10 - Wastewater - Flare Kod Area Oily Wastewater Sump | C | 2019-08-16 | IDD1 | OL1-2G43-5609 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5608 | P&ID - Olefins Unit 10 - Wastewater - C3 Hydrog Area Oily Wastewater Sump | C | 2019-08-16 | IDD1 | OL1-2G43-5608 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5606 | P&ID - Olefins Unit 10 - Wastewater - Furnace Area Oily Wastewater Sump | 0 | 2019-08-16 | CAN | OL1-2G43-5606 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5605 | P&ID - Olefins Unit 10 - Wastewater - Refrig Area Oily Wastewater Sump | C | 2019-08-16 | IDD1 | OL1-2G43-5605 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5604 | P&ID - Olefins Unit 10 - Wastewater - CGC Area Oily Wastewater Sump | C | 2019-08-16 | IDD1 | OL1-2G43-5604 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5603 | P&ID - Olefins Unit 10 - Wastewater - QW Area Oily Wastewater Sump | C | 2019-08-16 | IDD1 | OL1-2G43-5603 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5602 | P&ID - Olefins Unit 10 - Wastewater - Butadiene Area Oily Wastewater Sump | C | 2019-08-16 | IDD1 | OL1-2G43-5602 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1056-PID-0031-5601 | P&ID - Olefins Unit 10 - Wastewater - Pygas Area Oily Wastewater Sump | C | 2019-08-16 | IDD1 | OL1-2G43-5601 | PE | 2019-08-23 | 036909C-JVD-TRN-02479 | 036909C-JVD-TRN-02479 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02479 |  | 2019-08-26 | 2
036909C-1027-PID-0021-2790 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Pygas - C4/C5 - Treated Gas Battery Limit | A | 2019-08-16 | IDD1 | OL1-2G43-2790 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2742 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Light Oil Drain Drum | C | 2019-08-16 | IDD1 | OL1-2G43-2742 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2740 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Light Oil Drain Collection | C | 2019-08-16 | IDD1 | OL1-2G43-2740 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2738 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Recycle-Product Cooling | C | 2019-08-16 | IDD1 | OL1-2G43-2738 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2736 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Separator Drum | C | 2019-08-16 | IDD1 | OL1-2G43-2736 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2734 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Reactor | C | 2019-08-16 | IDD1 | OL1-2G43-2734 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2733 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Feed Heating | C | 2019-08-16 | IDD1 | OL1-2G43-2733 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2732 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Feed Pump | C | 2019-08-16 | IDD1 | OL1-2G43-2732 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2730 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Feed Surge Drum | C | 2019-08-16 | IDD1 | OL1-2G43-2730 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2722 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Regen Hydrog Drum | C | 2019-08-16 | IDD1 | OL1-2G43-2722 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2718 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Anti-Oxidant Injection Package | 0 | 2019-08-16 | CAN | OL1-2G43-2718 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2720 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Regen Gas Electric Heater | C | 2019-08-16 | IDD1 | OL1-2G43-2720 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2717 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Rerun Tower Liquid Ring Pump | C | 2019-08-16 | IDD1 | OL1-2G43-2717 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2716 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Pygas Fuel Oil Product | C | 2019-08-16 | IDD1 | OL1-2G43-2716 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2715 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Recycle Wash Oil | C | 2019-08-16 | IDD1 | OL1-2G43-2715 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2713 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Product - Wash Oil Pumps | C | 2019-08-16 | IDD1 | OL1-2G43-2713 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2712 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU Rerun Tower Reflux-Product Pump | C | 2019-08-16 | IDD1 | OL1-2G43-2712 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2711 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU Rerun Tower Condenser | C | 2019-08-16 | IDD1 | OL1-2G43-2711 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2710 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Rerun Tower | C | 2019-08-16 | IDD1 | OL1-2G43-2710 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2708 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Depentanizer Overhead | C | 2019-08-16 | IDD1 | OL1-2G43-2708 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2707 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU C5 Cut Pumps | C | 2019-08-16 | IDD1 | OL1-2G43-2707 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2706 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Depentanizer | C | 2019-08-16 | IDD1 | OL1-2G43-2706 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2705 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Cold Separator | C | 2019-08-16 | IDD1 | OL1-2G43-2705 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2704 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Hot Separator | C | 2019-08-16 | IDD1 | OL1-2G43-2704 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2703 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Reactors - Sheet 2 | C | 2019-08-16 | IDD1 | OL1-2G43-2703 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2702 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Reactors - Sheet 1 | C | 2019-08-16 | IDD1 | OL1-2G43-2702 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1027-PID-0021-2701 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Feed Heating | C | 2019-08-16 | IDD1 | OL1-2G43-2701 | PE | 2019-08-22 | 036909C-JVD-TRN-02471 | 036909C-JVD-TRN-02471 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02471 |  | 2019-08-22 | 2
036909C-1025-PID-0021-2590 | P&ID - Olefins Unit 10 - Cold Fractionation - Hydrogrn Battery Limit | A | 2019-08-26 | IDD1 | OL1-2G43-2590 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2556 | P&ID - Olefins Unit 10 - Cold Fractionation - Ethane Recycle Pumps | C | 2019-08-26 | IDD1 | OL1-2G43-2556 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2554 | P&ID - Olefins Unit 10 - Cold Fractionation - C2 Tower Side Reboiler | C | 2019-08-26 | IDD1 | OL1-2G43-2554 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2553 | P&ID - Olefins Unit 10 - Cold Fractionation - C2 Tower Bottoms Reboiler | C | 2019-08-26 | IDD1 | OL1-2G43-2553 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2552 | P&ID - Olefins Unit 10 - Cold Fractionation - C2 Tower | C | 2019-08-26 | IDD1 | OL1-2G43-2552 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2551 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Bottoms | C | 2019-08-26 | IDD1 | OL1-2G43-2551 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2547 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer Overhead | C | 2019-08-26 | IDD1 | OL1-2G43-2547 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2546 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer Condenser | C | 2019-08-26 | IDD1 | OL1-2G43-2546 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2543 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer Reboiler | C | 2019-08-26 | IDD1 | OL1-2G43-2543 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2541 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer | C | 2019-08-26 | IDD1 | OL1-2G43-2541 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2532 | P&ID - Olefins Unit 10 - Cold Fractionation - Pressure Swing Absorption Unit | C | 2019-08-26 | IDD1 | OL1-2G43-2532 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2531 | P&ID - Olefins Unit 10 - Cold Fractionation - Propylene Refrigerant Subcooler - Sheet 2 | C | 2019-08-26 | IDD1 | OL1-2G43-2531 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2530 | P&ID - Olefins Unit 10 - Cold Fractionation - Propylene Refrigerant Subcooler - Sheet 1 | C | 2019-08-26 | IDD1 | OL1-2G43-2530 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2529 | P&ID - Olefins Unit 10 - Cold Fractionation - Hydrogen Recovery | C | 2019-08-26 | IDD1 | OL1-2G43-2529 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2527 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Expander-Recompressor | C | 2019-08-26 | IDD1 | OL1-2G43-2527 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2525 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Expander Suction-Discharge Drums | C | 2019-08-26 | IDD1 | OL1-2G43-2525 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2522 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Reboiler | C | 2019-08-26 | IDD1 | OL1-2G43-2522 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2521 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer | C | 2019-08-26 | IDD1 | OL1-2G43-2521 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2520 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Feed Cooling | C | 2019-08-26 | IDD1 | OL1-2G43-2520 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2517 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Rectifier | C | 2019-08-26 | IDD1 | OL1-2G43-2517 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2515 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Rectifier Condenser | C | 2019-08-26 | IDD1 | OL1-2G43-2515 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2513 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Reboiler | C | 2019-08-26 | IDD1 | OL1-2G43-2513 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2511 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Prefractionator | C | 2019-08-26 | IDD1 | OL1-2G43-2511 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2507 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Separator No 3 | C | 2019-08-26 | IDD1 | OL1-2G43-2507 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2505 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Separator No 2 | C | 2019-08-26 | IDD1 | OL1-2G43-2505 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2503 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Separator No 1 | C | 2019-08-26 | IDD1 | OL1-2G43-2503 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1025-PID-0021-2501 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Chilling | C | 2019-08-26 | IDD1 | OL1-2G43-2501 | PE | 2019-08-26 | 036909C-JVD-TRN-02489 | 036909C-JVD-TRN-02489 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02489 |  | 2019-08-27 | 2
036909C-1024-PID-0021-2490 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Off-Spec Ethylene Liquid Battery Limit | A | 2019-08-16 | IDD1 | OL1-2G43-2490 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2447 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer Reflux | C | 2019-08-16 | IDD1 | OL1-2G43-2447 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2446 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer Reflux Chilling | C | 2019-08-16 | IDD1 | OL1-2G43-2446 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1000-SL-0000-05 | Subvendor List For Mechanical Packages | 1 | 2019-07-18 | IFI | OL1-2C91-0004 | PL | 2019-07-29 | 036909C-JVD-TRN-02271 | 036909C-JVD-TRN-02271 | IFR | 2019-08-12 | 2019-08-14 | R2-Comments as noted | TPSK-LSPA1-T-PL-02271 |  | 2019-07-29 | 3
036909C-1020-PDS-0600-2026 | Process Equipment Datasheet - 10-E-2026 - FO Product Cooler | A | 2018-11-08 | IFR | OL1-2G30-2026 | PE | 2018-11-09 | 036909C-JVD-TRN-00298 | 036909C-JVD-TRN-00298 | IFR | 2018-11-23 | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-PE-00298 |  | 2018-11-09 | 2
036909C-1024-PDS-0400-2470 | Process Equipment Datasheet - 10-R-2470 A-C - C2 Hydrog Reactor | A | 2018-11-08 | IFR | OL1-2G30-2470 | PE | 2018-11-09 | 036909C-JVD-TRN-00299 | 036909C-JVD-TRN-00299 | IFR | 2018-11-23 | 2018-11-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-00299 |  | 2018-11-09 | 2
036909C-1020-PDS-0600-2048 | Process Equipment Datasheet - 10-E-2048 - Heavy Fuel Oil Product Cooler | A | 2018-11-08 | IFR | OL1-2G30-2048 | PE | 2018-11-09 | 036909C-JVD-TRN-00298 | 036909C-JVD-TRN-00298 | IFR | 2018-11-23 | 2018-12-17 | R1-No comments | TPSK-LSPA1-T-PE-00298 |  | 2018-11-09 | 2
036909C-1025-PDS-0500-2510 | Process Equipment Datasheet - 10-T-2510 - 10-D-2510 - Demethanizer Prefractionator & Reflux Drum | B | 2018-11-09 | IFD | OL1-2G30-2510 | PE | 2018-11-09 | 036909C-JVD-TRN-00306 | 036909C-JVD-TRN-00306 | IFI |  | 2018-11-29 | A1-Approved without comments | TPSK-LSPA1-T-PE-00306 |  | 2018-11-09 | 1
036909C-1000-MR-0570-0001 | Material Requisition For Trays For Columns Requisition For Inquiry - For Next Revision See Document OL1-2C13-242000 | A | 2018-11-06 | IFQ | OL1-2C13-242000 | ME | 2018-11-09 | 036909C-JVD-TRN-00300 | 036909C-JVD-TRN-00300 | IFR | 2018-11-26 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-ME-00300 | For Next Revision See Document OL1-2C13-242000 | 2018-11-09 | 2
036909C-1000-JSD-1501-0002 | General Design Rules For SmartPlant Instrumentation Setup | B | 2018-10-24 | IFR | OL1-2R06-0024 | IE | 2018-11-08 | 036909C-JVD-TRN-00291 | 036909C-JVD-TRN-00291, ROC-TPSK-CECO-T-00004 | IFR | 2018-11-23 | 2019-02-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-00291 |  | 2018-11-08 | 2
036909C-1055-SP-0810-5552 | Mechanical Equipment Data Sheet - LPG Storage Drum | A | 2018-12-18 | IFQ | OL1-2M03-5552 | ME | 2019-01-11 | 036909C-JVD-TRN-00638 | 036909C-JVD-TRN-00638, ROC-TPSK-CECO-T-00016 | IFR | 2019-01-24 | 2019-01-31 | R2-Comments as noted | TPSK-LSPA1-T-ME-00638 |  | 2019-01-11 | 2
036909C-1024-PDS-0800-2405 | Process Equipment Datasheet - 10-D-2405 - Gas Dryer Feed KO Drum | B | 2018-12-10 | IFD | OL1-2G30-2405 | PE | 2018-12-13 | 036909C-JVD-TRN-00480 | 036909C-JVD-TRN-00480 | IFI |  | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00480 |  | 2018-12-13 | 2
036909C-1012-DW-0125-2302 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-2302 | ME | 2018-11-08 | 036909C-JVD-TRN-00289 | 036909C-JVD-TRN-00289 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00289 |  | 2018-11-08 | 3
036909C-1000-JSD-1300-0003 | A1 Scope Annex C– Ppiping Specification PIP-006 Steam Tracing Piping | B | 2018-11-06 | IFR | OL1-2R04-0031 | MP | 2018-11-09 | 036909C-JVD-TRN-00292 | 036909C-JVD-TRN-00292 | IFR | 2018-11-26 | 2019-01-23 | R1-No comments | TPSK-LSPA1-T-MP-00292 |  | 2018-11-09 | 2
036909C-1000-JSD-1580-0002 | Progammable Logic Controller | A | 2018-11-07 | IFR | OL1-2R06-1301 | IE | 2018-11-08 | 036909C-JVD-TRN-00291 | 036909C-JVD-TRN-00291, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-11-23 | 2019-02-01 | R1-No comments | TPSK-LSPA1-T-IE-00291 |  | 2018-11-08 | 2
036909C-1012-DW-0125-2301 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-2301 | ME | 2018-11-08 | 036909C-JVD-TRN-00289 | 036909C-JVD-TRN-00289 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00289 |  | 2018-11-08 | 3
036909C-1023-PDS-0500-2300 | Process Equipment Datasheet - 10-T-2300 - Caustic Tower | B | 2018-11-08 | IFD | OL1-2G30-2300 | PE | 2018-11-08 | 036909C-JVD-TRN-00290 | 036909C-JVD-TRN-00290 | IFI |  | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00290 |  | 2018-11-08 | 1
036909C-1022-PDS-0900-2212 | Process Equipment Datasheet - 10-P-2210 A-B - CG 1st Stage Condensate Pumps | A | 2018-11-06 | IFR | OL1-2G30-2212 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00285 |  | 2018-11-07 | 2
036909C-1024-PDS-0900-2453 | Process Equipment Datasheet - 10-P-2450 A-B - LP Depropanizer Reflux-Product Pump | A | 2018-11-06 | IFR | OL1-2G30-2453 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00285 |  | 2018-11-07 | 2
036909C-1021-PDS-0900-2105 | Process Equipment Datasheet - 10-P-2105 A-B - Quench Oil Reflux Pumps | A | 2018-11-06 | IFR | OL1-2G30-2105 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00285 |  | 2018-11-07 | 2
036909C-1020-PDS-0900-2024 | Process Equipment Datasheet - 10-P-2026 A-B - Light Fuel Oil Pumps | A | 2018-11-06 | IFR | OL1-2G30-2024 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00285 |  | 2018-11-07 | 2
036909C-1000-SP-0570-0001 | Particular Technical Specification For Trays For Columns | A | 2018-11-06 | IFQ | OL1-2M57-0055 | ME | 2018-11-09 | 036909C-JVD-TRN-00300 | 036909C-JVD-TRN-00300 | IFR | 2018-11-26 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-ME-00300 |  | 2018-11-09 | 2
036909C-1026-PDS-0800-2632 | Process Equipment Datasheet - 10-D-2630 - Secondary Deeth Reflux Drum | A | 2018-11-07 | IFR | OL1-2G30-2632 | PE | 2018-11-07 | 036909C-JVD-TRN-00287 | 036909C-JVD-TRN-00287 | IFR | 2018-11-21 | 2019-01-11 | R1-No comments | TPSK-LSPA1-T-PE-00287 |  | 2018-11-07 | 2
036909C-1011-DW-0125-1302 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-1302 | ME | 2018-11-07 | 036909C-JVD-TRN-00286 | 036909C-JVD-TRN-00286 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00286 |  | 2018-11-07 | 3
036909C-1026-SP-0510-2660 | Mechanical Equipment Datasheet - Debutanizer | B | 2018-11-07 | IFQ | OL1-2M03-2660 | ME | 2018-11-08 | 036909C-JVD-TRN-00288 | 036909C-JVD-TRN-00288 | IFR | 2018-11-22 | 2018-11-17 | R2-Comments as noted | TPSK-LSPA1-T-ME-00288 |  | 2018-11-08 | 2
036909C-1026-PDS-0800-2662 | Process Equipment Datasheet - 10-D-2660 - Debutanizer Reflux Drum | A | 2018-11-07 | IFR | OL1-2G30-2662 | PE | 2018-11-07 | 036909C-JVD-TRN-00287 | 036909C-JVD-TRN-00287 | IFR | 2018-11-21 | 2019-01-11 | R1-No comments | TPSK-LSPA1-T-PE-00287 |  | 2018-11-07 | 2
036909C-1024-PDS-0900-2416 | Process Equipment Datasheet - 10-P-2415 A-B - CG Liquid Dryer Feed Pumps | A | 2018-11-06 | IFR | OL1-2G30-2416 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00285 |  | 2018-11-07 | 2
036909C-1022-PDS-0900-2222 | Process Equipment Datasheet - 10-P-2220 A-B - CG 2nd Stage Condensed HC Pumps | A | 2018-11-06 | IFR | OL1-2G30-2222 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00285 |  | 2018-11-07 | 2
036909C-1011-DW-0125-1301 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-1301 | ME | 2018-11-07 | 036909C-JVD-TRN-00286 | 036909C-JVD-TRN-00286 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00286 |  | 2018-11-07 | 3
036909C-1020-PDS-0900-2046 | Process Equipment Datasheet - 10-P-2046 A-B - Heavy Fuel Oil Pumps | A | 2018-11-06 | IFR | OL1-2G30-2046 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00285 |  | 2018-11-07 | 2
036909C-1026-PDS-0900-2633 | Process Equipment Datasheet - 10-P-2630 A-B - Secondary Deeth Reflux Pumps | A | 2018-11-05 | IFR | OL1-2G30-2633 | PE | 2018-11-06 | 036909C-JVD-TRN-00277 | 036909C-JVD-TRN-00277 | IFR | 2018-11-20 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00277 |  | 2018-11-06 | 2
036909C-1053-SP-0310-0002 | Mechanical Equipment Datasheet for Cooling Tower | B | 2018-10-30 | IFQ | OL1-2M03-5350 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276 | IFR | 2018-11-19 | 2019-02-15 | R1-No comments | TPSK-LSPA1-T-ME-00276 |  | 2018-11-06 | 2
036909C-1000-SR-0310-0001 | Scope of Supply for Cooling Tower | A | 2018-10-30 | IFQ | OL1-2M56-0104 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276 | IFR | 2018-11-19 | 2019-02-15 | R1-No comments | TPSK-LSPA1-T-ME-00276 |  | 2018-11-06 | 2
036909C-1000-MR-0310-0001 | Material Requisition for Cooling Tower - For Next Revision See Document OL1-2C13-311000 | A | 2018-10-30 | IFQ | OL1-2C13-311000 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276 | IFR | 2018-11-19 | 2019-02-15 | R1-No comments | TPSK-LSPA1-T-ME-00276 | For Next Revision See Document OL1-2C13-311000 | 2018-11-06 | 2
036909C-1026-PDS-0900-2646 | Process Equipment Datasheet - 10-P-2646 A-B - Propane Recycle Pumps | A | 2018-11-05 | IFR | OL1-2G30-2646 | PE | 2018-11-06 | 036909C-JVD-TRN-00277 | 036909C-JVD-TRN-00277 | IFR | 2018-11-20 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00277 |  | 2018-11-06 | 2
036909C-1022-SP-1011-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor | C | 2018-10-31 | IFQ | OL1-2M03-2200 | ME | 2018-11-06 | 036909C-JVD-TRN-00280 | 036909C-JVD-TRN-00280 | IFI |  | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-ME-00280 |  | 2018-11-06 | 2
036909C-1000-SP-0310-0001 | Particular Technical Specification for Cooling Tower | A | 2018-10-30 | IFQ | OL1-2M57-0104 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276 | IFR | 2018-11-19 | 2019-02-15 | R1-No comments | TPSK-LSPA1-T-ME-00276 |  | 2018-11-06 | 2
036909C-1028-PDS-0900-2801 | Process Equipment Datasheet - 10-P-2805 A-B - Propylene Product Pumps | A | 2018-11-05 | IFR | OL1-2G30-2801 | PE | 2018-11-06 | 036909C-JVD-TRN-00277 | 036909C-JVD-TRN-00277 | IFR | 2018-11-20 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00277 |  | 2018-11-06 | 2
036909C-1052-PDS-0600-5201 | Process Equipment Datasheet - 10-E-5200 - MP Ethylene Superheater | A | 2018-11-05 | IFR | OL1-2G30-5201 | PE | 2018-11-05 | 036909C-JVD-TRN-00275 | 036909C-JVD-TRN-00275 | IFR | 2018-11-19 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-PE-00275 |  | 2018-11-05 | 2
036909C-1051-PDS-0800-5114 | Process Equipment Datasheet - 10-D-5114 - LP Condensate Flash Drum | A | 2018-11-05 | IFR | OL1-2G30-5114 | PE | 2018-11-05 | 036909C-JVD-TRN-00274 | 036909C-JVD-TRN-00274 | IFR | 2018-11-21 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00274 |  | 2018-11-05 | 2
036909C-1024-SP-0510-2450 | Mechanical Equipment Datasheet - LP Depropanizer | B | 2018-11-06 | IFQ | OL1-2M03-2450 | ME | 2018-11-06 | 036909C-JVD-TRN-00283 | 036909C-JVD-TRN-00283 | IFI |  | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-ME-00283 |  | 2018-11-06 | 2
036909C-1000-JSS-0310-0001 | ME-008 Cooling Water | A | 2018-10-30 | IFQ | OL1-2R03-0104 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276, ROC-TPSK-CECO-T-00003 | IFR | 2018-11-19 | 2019-02-15 | Transmitted | TPSK-LSPA1-T-ME-00276 |  | 2018-11-06 | 2
036909C-1000-SR-0570-0001 | Scope Of Supply For Trays For Columns | A | 2018-11-06 | IFQ | OL1-2M56-0055 | ME | 2018-11-09 | 036909C-JVD-TRN-00300 | 036909C-JVD-TRN-00300 | IFR | 2018-11-26 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-ME-00300 |  | 2018-11-09 | 2
036909C-1026-PDS-0600-2665 | Process Equipment Datasheet - 10-E-2665 A-B - Debutanizer Reboilers | B | 2018-11-01 | IFD | OL1-2G30-2665 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1028-PDS-0600-2807 | Process Equipment Datasheet - 10-E-2807 - C3 Chiller No 1 | B | 2018-11-01 | IFD | OL1-2G30-2807 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1026-PDS-0600-2636 | Process Equipment Datasheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | B | 2018-11-01 | IFD | OL1-2G30-2636 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1026-PDS-0600-2645 | Process Equipment Datasheet - 10-E-2645 A-B - C3 Tower Reboilers | B | 2018-11-01 | IFD | OL1-2G30-2645 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1028-PDS-0600-2853 | Process Equipment Datasheet - 10-E-2853 - C2R Desuperheater No 2 | B | 2018-11-01 | IFD | OL1-2G30-2853 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1028-PDS-0600-2857 | Process Equipment Datasheet - 10-E-2857 - HP Ethylene Product Vaporizer | B | 2018-11-01 | IFD | OL1-2G30-2857 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1026-PDS-0600-2661 | Process Equipment Datasheet - 10-E-2660 - Debutanizer Condenser | B | 2018-11-01 | IFD | OL1-2G30-2661 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1028-PDS-0600-2852 | Process Equipment Datasheet - 10-E-2852 - C2R Desuperheater No 1 | B | 2018-11-01 | IFD | OL1-2G30-2852 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1028-PDS-0600-2806 | Process Equipment Datasheet - 10-E-2805 A-B - C3 Refrig Condensers | B | 2018-11-01 | IFD | OL1-2G30-2806 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1025-PDS-0600-2571 | Process Equipment Datasheet - 10-E-2570 - Deethanizer Condenser | B | 2018-11-01 | IFD | OL1-2G30-2571 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1025-PDS-0600-2503 | Process Equipment Datasheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | B | 2018-11-01 | IFD | OL1-2G30-2503 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1000-MR-0845-0001 | Material Requisition for Deareator - For next Rev. see Doc. Client Ref. OL1-2C13-120000 | A | 2018-10-29 | IFQ | OL1-2C13-120000 | ME | 2018-11-06 | 036909C-JVD-TRN-00270 | 036909C-JVD-TRN-00270 | IFR | 2018-11-20 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00270 | For next Rev. see Doc. Client Ref. OL1-2C13-120000 | 2018-11-06 | 2
036909C-1028-PDS-0600-2809 | Process Equipment Datasheet - 10-E-2809 - C3 Chiller No 2 | B | 2018-11-01 | IFD | OL1-2G30-2809 | PE | 2018-11-05 | 036909C-JVD-TRN-00273 | 036909C-JVD-TRN-00273 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00273 |  | 2018-11-05 | 1
036909C-1051-PDS-0800-5112 | Process Equipment Datasheet - 10-D-5112 - Suspect Condensate Flash Drum | A | 2018-11-05 | IFR | OL1-2G30-5112 | PE | 2018-11-05 | 036909C-JVD-TRN-00274 | 036909C-JVD-TRN-00274 | IFR | 2018-11-21 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00274 |  | 2018-11-05 | 2
036909C-1026-PDS-0600-2631 | Process Equipment Datasheet - 10-E-2630 - Secondary Deeth Condenser | B | 2018-11-01 | IFD | OL1-2G30-2631 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1025-PDS-0600-2576 | Process Equipment Datasheet - 10-E-2576 - Deethanizer Bottoms Cooler | B | 2018-11-01 | IFD | OL1-2G30-2576 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1025-PDS-0600-2502 | Process Equipment Datasheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | B | 2018-11-01 | IFD | OL1-2G30-2502 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1026-PDS-0600-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler | B | 2018-11-01 | IFD | OL1-2G30-2635 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1025-PDS-0600-2575 | Process Equipment Datasheet - 10-E-2575 - Deethanizer Reboiler | B | 2018-11-01 | IFD | OL1-2G30-2575 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1000-MR-4111-0001 | Material Requisition for Hydrogen Production Unit - For Next Revision See Document OL1-2C13-705000 | A | 2018-10-26 | IFQ | OL1-2C13-705000 | ME | 2018-11-06 | 036909C-JVD-TRN-00271 | 036909C-JVD-TRN-00271 | IFR | 2018-11-20 | 2019-02-07 | R1-No comments | TPSK-LSPA1-T-ME-00271 | For Next Revision See Document OL1-2C13-705000 | 2018-11-06 | 2
036909C-1000-JSS-1694-0001 | Medium Voltage Variable Voltage Variable Frequency System | 0 | 2018-09-20 | IMP | OL1-2R05-0040 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | 2018-11-05 | 3
036909C-1000-JSS-1671-0001 | Uninterruptible Power Supplies | 0 | 2018-09-20 | IMP | OL1-2R05-0012 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | 2018-11-05 | 3
036909C-1000-SP-0570-0004 | Particular Technical Specification For MD Trays For Columns | A | 2018-10-31 | IFQ | OL1-2M57-0075 | ME | 2018-11-07 | 036909C-JVD-TRN-00278 | 036909C-JVD-TRN-00278 | IFR | 2018-11-21 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00278 |  | 2018-11-07 | 2
036909C-1000-SR-0570-0004 | Scope Of Supply For MD Trays For Columns | A | 2018-10-31 | IFQ | OL1-2M56-0075 | ME | 2018-11-07 | 036909C-JVD-TRN-00278 | 036909C-JVD-TRN-00278 | IFR | 2018-11-21 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00278 |  | 2018-11-07 | 2
036909C-1000-JSS-1684-0001 | Cathodic Protection | 0 | 2018-09-20 | IMP | OL1-2R05-0016 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | 2018-11-05 | 3
036909C-1028-PDS-0600-2856 | Process Equipment Datasheet - 10-E-2855 - C2R Condenser | B | 2018-11-01 | IFD | OL1-2G30-2856 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | 2018-11-05 | 1
036909C-1012-SP-1040-2005 | Particular Technical Specification for Furnace ID Fans | A | 2018-11-01 | IFQ | OL1-2M57-2005 | ME | 2018-11-05 | 036909C-JVD-TRN-00269 | 036909C-JVD-TRN-00269 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00269 |  | 2018-11-05 | 3
036909C-1022-PDS-0800-2245 | Process Equipment Datasheet - 10-D-2245 - CG 4th Stage Discharge Drum | A | 2018-10-31 | IFR | OL1-2G30-2245 | PE | 2018-11-01 | 036909C-JVD-TRN-00264 | 036909C-JVD-TRN-00264 | IFR | 2018-11-15 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00264 |  | 2018-11-01 | 2
036909C-1000-JSS-1655-0001 | Low Voltage Bus Duct | 0 | 2018-09-20 | IMP | OL1-2R05-0038 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | 2018-11-05 | 3
036909C-1022-PDS-0600-2211 | Process Equipment Datasheet - 10-E-2210 A-B - CG 1st Stage Aftercoolers | A | 2018-11-01 | IFR | OL1-2G30-2211 | PE | 2018-11-01 | 036909C-JVD-TRN-00266 | 036909C-JVD-TRN-00266 | IFR | 2018-11-15 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00266 |  | 2018-11-01 | 2
036909C-1024-PDS-0600-2445 | Process Equipment Datasheet - 10-E-2445 A-B - HP Depropanizer Reboilers | A | 2018-11-01 | IFR | OL1-2G30-2445 | PE | 2018-11-01 | 036909C-JVD-TRN-00267 | 036909C-JVD-TRN-00267 | IFR | 2018-11-15 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00267 |  | 2018-11-01 | 2
036909C-1000-SP-4111-0001 | Particular Technical Specification For Hydrogen Production Unit | A | 2018-10-26 | IFQ | OL1-2M57-0114 | ME | 2018-11-06 | 036909C-JVD-TRN-00271 | 036909C-JVD-TRN-00271 | IFR | 2018-11-20 | 2019-02-07 | R2-Comments as noted | TPSK-LSPA1-T-ME-00271 |  | 2018-11-06 | 2
036909C-1012-MR-1040-2005 | Material Requisition for Furnace ID Fans - For next Rev. see Doc. Client Ref. OL1-2C13-301000 | A | 2018-11-01 | IFQ | OL1-2C13-301000 | ME | 2018-11-05 | 036909C-JVD-TRN-00269 | 036909C-JVD-TRN-00269 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00269 | For next Rev. see Doc. Client Ref. OL1-2C13-301000 | 2018-11-05 | 3
036909C-1000-JSS-1652-0001 | Medium Voltage Switchgear | 0 | 2018-09-20 | IMP | OL1-2R05-0006 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | 2018-11-05 | 3
036909C-1012-SR-1040-2005 | Scope of Supply for Furnace ID Fans | A | 2018-11-01 | IFQ | OL1-2M56-2005 | ME | 2018-11-05 | 036909C-JVD-TRN-00269 | 036909C-JVD-TRN-00269 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00269 |  | 2018-11-05 | 3
036909C-1025-PDS-0600-2582 | Process Equipment Datasheet - 10-E-2582 - C2 Tower Reflux Cooler | A | 2018-11-01 | IFR | OL1-2G30-2582 | PE | 2018-11-01 | 036909C-JVD-TRN-00265 | 036909C-JVD-TRN-00265 | IFR | 2018-11-15 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00265 |  | 2018-11-01 | 2
036909C-1012-MR-0155-2018 | Material Requisition for Furnace Steam Drums | A | 2018-11-01 | IFQ | OL1-2M55-2018 | ME | 2018-11-01 | 036909C-JVD-TRN-00263 | 036909C-JVD-TRN-00263 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00263 |  | 2018-11-01 | 3
036909C-1024-PDS-0800-2438 | Process Equipment Datasheet - 10-D-2440 - HP Depropanizer Reflux Drum | A | 2018-10-31 | IFR | OL1-2G30-2438 | PE | 2018-11-01 | 036909C-JVD-TRN-00264 | 036909C-JVD-TRN-00264 | IFR | 2018-11-15 | 2018-11-27 | R1-No comments | TPSK-LSPA1-T-PE-00264 |  | 2018-11-01 | 2
036909C-1021-PDS-0600-2125 | Process Equipment Datasheet - 10-E-2125 - Distillate Stripper Reboiler | A | 2018-11-01 | IFR | OL1-2G30-2125 | PE | 2018-11-01 | 036909C-JVD-TRN-00265 | 036909C-JVD-TRN-00265 | IFR | 2018-11-15 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00265 |  | 2018-11-01 | 2
036909C-1024-PDS-0800-2452 | Process Equipment Datasheet - 10-D-2450 - LP Depropanizer Reflux Drum | A | 2018-10-31 | IFR | OL1-2G30-2452 | PE | 2018-11-01 | 036909C-JVD-TRN-00264 | 036909C-JVD-TRN-00264 | IFR | 2018-11-15 | 2018-11-27 | R1-No comments | TPSK-LSPA1-T-PE-00264 |  | 2018-11-01 | 2
036909C-1019-SP-1013-1950 | Mechanical Equipment Datasheet - Decoking Air Compressor Package | C | 2018-10-31 | IFQ | OL1-2M03-1950 | ME | 2018-11-01 | 036909C-JVD-TRN-00261 | 036909C-JVD-TRN-00261, ROC-TPSK-CECO-T-00014 | IFI |  | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00261 |  | 2018-11-01 | 1
036909C-1023-PDS-0600-2305 | Process Equipment Datasheet - 10-E-2305 - Caustic Tower Feed Heater | A | 2018-10-31 | IFR | OL1-2G30-2305 | PE | 2018-10-31 | 036909C-JVD-TRN-00259 | 036909C-JVD-TRN-00259 | IFR | 2018-11-14 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00259 |  | 2018-10-31 | 2
036909C-1025-SP-0510-2510 | Mechanical Equipment Data Sheet - Demethanizer Prefractionator and Reflux Drum | A | 2018-10-29 | IFQ | OL1-2M03-2510 | ME | 2018-10-31 | 036909C-JVD-TRN-00260 | 036909C-JVD-TRN-00260 | IFR | 2018-11-14 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00260 |  | 2018-10-31 | 2
036909C-1012-SR-0155-2018 | Scope of Supply for Furnace Steam Drums | A | 2018-11-01 | IFQ | OL1-2M56-2018 | ME | 2018-11-01 | 036909C-JVD-TRN-00263 | 036909C-JVD-TRN-00263 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00263 |  | 2018-11-01 | 3
036909C-1012-SP-0155-2018 | Particular Technical Specification for Furnace Steam Drums | A | 2018-11-01 | IFQ | OL1-2M57-2018 | ME | 2018-11-01 | 036909C-JVD-TRN-00263 | 036909C-JVD-TRN-00263 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00263 |  | 2018-11-01 | 3
036909C-1006-JSS-0117-3001 | ME-001 Pressure Vessel for 36M and 132U Furnace | 0 | 2018-10-18 | IFE | OL1-2R03-1001 | ME | 2018-11-07 | 036909C-JVD-TRN-00262 | 036909C-JVD-TRN-00262, ROC-TPSK-CECO-T-00003 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00262 |  | 2018-11-07 | 3
036909C-1051-PDS-0900-5101 | Process Equipment Datasheet - 10-P-5100 A-C - SHP BFW Pumps | B | 2018-10-30 | IFD | OL1-2G30-5101 | PE | 2018-10-31 | 036909C-JVD-TRN-00251 | 036909C-JVD-TRN-00251 | IFI |  | 2018-12-13 | R1-No comments | TPSK-LSPA1-T-PE-00251 |  | 2018-10-31 | 2
036909C-1023-PDS-0900-2321 | Process Equipment Datasheet - 10-P-2320 A-B - Spent Caustic Pumps | A | 2018-10-29 | IFR | OL1-2G30-2321 | PE | 2018-10-31 | 036909C-JVD-TRN-00252 | 036909C-JVD-TRN-00252 | IFR | 2018-11-14 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00252 |  | 2018-10-31 | 2
036909C-1051-PDS-0900-5109 | Process Equipment Datasheet - 10-P-5110 A-B - Condensate Pumps | B | 2018-10-30 | IFD | OL1-2G30-5109 | PE | 2018-10-31 | 036909C-JVD-TRN-00251 | 036909C-JVD-TRN-00251 | IFI |  | 2018-12-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00251 |  | 2018-10-31 | 2
036909C-1051-PDS-0900-5102 | Process Equipment Datasheet - 10-P-5102 A-B - VLP BFW Pumps | B | 2018-10-30 | IFD | OL1-2G30-5102 | PE | 2018-10-31 | 036909C-JVD-TRN-00251 | 036909C-JVD-TRN-00251 | IFI |  | 2018-12-13 | R1-No comments | TPSK-LSPA1-T-PE-00251 |  | 2018-10-31 | 2
036909C-1024-PDS-0600-2413 | Process Equipment Datasheet - 10-E-2413 - HP Deprop Feed - Overhead Exchanger | A | 2018-10-30 | IFR | OL1-2G30-2413 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R2-Comments as noted | TPSK-LSPA1-T-PE-00250 |  | 2018-10-31 | 2
036909C-1024-PDS-0600-2439 | Process Equipment Datasheet - 10-E-2440 - HP Depropanizer Condenser | A | 2018-10-30 | IFR | OL1-2G30-2439 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250 |  | 2018-10-31 | 2
036909C-1024-PDS-0600-2442 | Process Equipment Datasheet - 10-E-2442 - HP Deprop Reflux Chiller No 1 | A | 2018-10-30 | IFR | OL1-2G30-2442 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250 |  | 2018-10-31 | 2
036909C-1024-PDS-0600-2461 | Process Equipment Datasheet - 10-E-2460 - C2 Hydrog Feed Cooler | A | 2018-10-30 | IFR | OL1-2G30-2461 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250 |  | 2018-10-31 | 2
036909C-1024-PDS-0600-2446 | Process Equipment Datasheet - 10-E-2446 - LP Depropanizer Feed Cooler | A | 2018-10-30 | IFR | OL1-2G30-2446 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250 |  | 2018-10-31 | 2
036909C-1023-PDS-0840-2319 | Process Equipment Datasheet - 10-F-2320 A-B - Spent Caustic Pump Discharge Filters | A | 2018-10-29 | IFR | OL1-2G30-2319 | PE | 2018-10-31 | 036909C-JVD-TRN-00255 | 036909C-JVD-TRN-00255 | IFR | 2018-11-14 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00255 |  | 2018-10-31 | 2
036909C-1024-PDS-0600-2451 | Process Equipment Datasheet - 10-E-2450 - LP Depropanizer Condenser | A | 2018-10-31 | IFR | OL1-2G30-2451 | PE | 2018-10-31 | 036909C-JVD-TRN-00259 | 036909C-JVD-TRN-00259 | IFR | 2018-11-14 | 2018-11-20 | R2-Comments as noted | TPSK-LSPA1-T-PE-00259 |  | 2018-10-31 | 2
036909C-1000-SR-4111-0001 | Scope Of Supply For Hydrogen Production Unit | A | 2018-10-26 | IFQ | OL1-2M56-0114 | ME | 2018-11-06 | 036909C-JVD-TRN-00271 | 036909C-JVD-TRN-00271 | IFR | 2018-11-20 | 2019-02-07 | R1-No comments | TPSK-LSPA1-T-ME-00271 |  | 2018-11-06 | 2
036909C-1000-JSD-1600-0007 | Functional and Schematic Diagram | 0 | 2018-09-20 | IMP | OL1-2R05-0029 | EE | 2018-11-05 | 036909C-JVD-TRN-00258 | 036909C-JVD-TRN-00258, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00258 |  | 2018-11-05 | 3
036909C-1023-PDS-0900-2393 | Process Equipment Datasheet - 10-P-2392 - Spent Caustic Drain Drum Pump | A | 2018-10-29 | IFR | OL1-2G30-2393 | PE | 2018-10-31 | 036909C-JVD-TRN-00252 | 036909C-JVD-TRN-00252 | IFR | 2018-11-14 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00252 |  | 2018-10-31 | 2
036909C-1021-PDS-0500-2120 | Process Equipment Datasheet - 10-T-2120 - Distillate Stripper | A | 2018-10-29 | IFR | OL1-2G30-2120 | PE | 2018-10-31 | 036909C-JVD-TRN-00253 | 036909C-JVD-TRN-00253 | IFR | 2018-11-14 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00253 |  | 2018-10-31 | 2
036909C-1023-PDS-0800-2310 | Process Equipment Datasheet - 10-D-2310 - Spent Caustic Deoiling Drum | A | 2018-10-29 | IFR | OL1-2G30-2310 | PE | 2018-10-31 | 036909C-JVD-TRN-00254 | 036909C-JVD-TRN-00254 | IFR | 2018-11-14 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00254 |  | 2018-10-31 | 2
036909C-1000-SP-0845-0001 | Particular Technical Specification For Deaerator | A | 2018-10-29 | IFQ | OL1-2M57-0108 | ME | 2018-11-06 | 036909C-JVD-TRN-00270 | 036909C-JVD-TRN-00270 | IFR | 2018-11-20 | 2018-11-29 | Transmitted | TPSK-LSPA1-T-ME-00270 |  | 2018-11-06 | 2
036909C-1000-SR-0845-0001 | Scope Of Supply For Deareator | A | 2018-10-29 | IFQ | OL1-2M56-0108 | ME | 2018-11-06 | 036909C-JVD-TRN-00270 | 036909C-JVD-TRN-00270 | IFR | 2018-11-20 | 2018-11-29 | Transmitted | TPSK-LSPA1-T-ME-00270 |  | 2018-11-06 | 2
036909C-1053-SP-4234-0002 | Mechanical Equipment Datasheet for Side Stream Filter Package | B | 2018-10-29 | IFQ | OL1-2M03-5355 | ME | 2018-10-31 | 036909C-JVD-TRN-00248 | 036909C-JVD-TRN-00248 | IFR | 2018-11-16 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00248 |  | 2018-10-31 | 2
036909C-1024-PDS-0600-2441 | Process Equipment Datasheet - 10-E-2441 - HP Deprop Reflux Chiller No 2 | A | 2018-10-30 | IFR | OL1-2G30-2441 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250 |  | 2018-10-31 | 2
036909C-1000-SR-0910-0001 | Scope Of Supply For API Centrifugal Pumps - LLI | A | 2018-10-30 | IFQ | OL1-2M56-0015 | ME | 2018-10-31 | 036909C-JVD-TRN-00257 | 036909C-JVD-TRN-00257 | IFR | 2018-11-20 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00257 |  | 2018-10-31 | 2
036909C-1000-SP-0910-0001 | Particular Technical Specification For API Centrifugal Pumps - LLI | A | 2018-10-30 | IFQ | OL1-2M57-0015 | ME | 2018-10-31 | 036909C-JVD-TRN-00257 | 036909C-JVD-TRN-00257 | IFR | 2018-11-20 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00257 |  | 2018-10-31 | 2
036909C-1023-SP-0510-2300 | Mechanical Equipment Data Sheet Caustic Tower 10-T-2300 | A | 2018-10-26 | IFQ | OL1-2M03-2300 | ME | 2018-10-31 | 036909C-JVD-TRN-00246 | 036909C-JVD-TRN-00246 | IFR | 2018-11-13 | 2018-11-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00246 |  | 2018-10-31 | 2
036909C-1000-JSS-0400-01 | Job Specification For Supply Of Pressure Vessels | 0 | 2018-10-26 | IMP | OL1-2R03-0051 | ME | 2018-10-31 | 036909C-JVD-TRN-00249 | 036909C-JVD-TRN-00249, ROC-TPSK-CECO-T-00003 | IFR | 2018-11-14 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00249 |  | 2018-10-31 | 2
036909C-1000-JSD-0400-01 | Job Specification For Design Of Pressure & Atmospheric Static Equipment | 0 | 2018-10-26 | IMP | OL1-2R03-0050 | ME | 2018-10-31 | 036909C-JVD-TRN-00245 | 036909C-JVD-TRN-00245 | IFR | 2018-11-14 | 2018-11-26 | Transmitted | TPSK-LSPA1-T-ME-00245 |  | 2018-10-31 | 2
036909C-1025-SP-0810-2555 | Mechanical Equipment Data Sheet - Expander Discharge Drum | A | 2018-12-13 | IFQ | OL1-2M03-2555 | ME | 2019-01-08 | 036909C-JVD-TRN-00607 | 036909C-JVD-TRN-00607, ROC-TPSK-CECO-T-00015 | IFR | 2019-01-22 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-ME-00607 |  | 2019-01-08 | 2
036909C-1000-STC-0490-000 | Construction Standards For Pressure Equipment | 0 | 2018-10-26 | IMP | OL1-2R03-0054 | ME | 2018-10-31 | 036909C-JVD-TRN-00256 | 036909C-JVD-TRN-00256 | IFR | 2018-11-14 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00256 |  | 2018-10-31 | 2
036909C-1000-SR-4234-0001 | Scope of Supply for Side Stream Filter Package | A | 2018-10-29 | IFQ | OL1-2M56-0109 | ME | 2018-10-31 | 036909C-JVD-TRN-00248 | 036909C-JVD-TRN-00248 | IFR | 2018-11-16 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00248 |  | 2018-10-31 | 2
036909C-1000-SP-4234-0001 | Particular Technical Specification for Side Steam Filter Package | A | 2018-10-29 | IFQ | OL1-2M57-0109 | ME | 2018-10-31 | 036909C-JVD-TRN-00248 | 036909C-JVD-TRN-00248 | IFR | 2018-11-16 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00248 |  | 2018-10-31 | 2
036909C-1000-MR-4234-0001 | Material Requisition for Side Stream Filter Package - For Next Revision See Document OL1-2C13-706000 | A | 2018-10-29 | IFQ | OL1-2C13-706000 | ME | 2018-10-31 | 036909C-JVD-TRN-00248 | 036909C-JVD-TRN-00248 | IFR | 2018-11-16 | 2018-11-27 | R1-No comments | TPSK-LSPA1-T-ME-00248 | For Next Revision See Document OL1-2C13-706000 | 2018-10-31 | 2
036909C-1012-SP-1040-2001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 132U | A | 2018-10-29 | IFR | OL1-2M03-2001 | ME | 2018-10-31 | 036909C-JVD-TRN-00247 | 036909C-JVD-TRN-00247 | IFR | 2018-11-13 |  | Transmitted | TPSK-LSPA1-T-ME-00247 |  | 2018-10-31 | 2
036909C-1011-SP-1040-1001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 36M | A | 2018-10-30 | IFR | OL1-2M03-1001 | ME | 2018-10-31 | 036909C-JVD-TRN-00247 | 036909C-JVD-TRN-00247 | IFR | 2018-11-13 |  | Transmitted | TPSK-LSPA1-T-ME-00247 |  | 2018-10-31 | 2
036909C-1024-PDS-0600-2406 | Process Equipment Datasheet - 10-E-2405 - Gas Dryer Feed Chiller | A | 2018-10-26 | IFR | OL1-2G30-2406 | PE | 2018-10-30 | 036909C-JVD-TRN-00239 | 036909C-JVD-TRN-00239 | IFR | 2018-11-12 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00239 |  | 2018-10-30 | 2
036909C-1021-PDS-0500-2100 | Process Equipment Datasheet - 10-T-2100 - Quench Water Tower | A | 2018-10-26 | IFR | OL1-2G30-2100 | PE | 2018-10-29 | 036909C-JVD-TRN-00238 | 036909C-JVD-TRN-00238 | IFR | 2018-11-12 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00238 |  | 2018-10-29 | 2
036909C-1012-PDS-0610-1209 | Process Equipment Datasheet - 10-E-1210 - 10-E-1610 - USC 132U TLX Quench Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1209 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237 |  | 2018-10-29 | 2
036909C-1012-PDS-0630-1208 | Process Equipment Datasheet - 10-E-1200A-F - 10-E-1600A-F - USC 132U SLE Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1208 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237 |  | 2018-10-29 | 2
036909C-1019-PDS-1000-1950 | Process Equipment Datasheet - 10-PK-1950 - Decoke Air Compressor Pkg | C | 2018-10-29 | IFD | OL1-2G30-1950 | PE | 2018-10-30 | 036909C-JVD-TRN-00242 | 036909C-JVD-TRN-00242 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00242 |  | 2018-10-30 | 1
036909C-1051-PDS-0600-5108 | Process Equipment Datasheet - 10-E-5110 - Suspect Condensate Cooler | A | 2018-10-29 | IFR | OL1-2G30-5108 | PE | 2018-10-30 | 036909C-JVD-TRN-00243 | 036909C-JVD-TRN-00243 | IFR | 2018-11-12 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00243 |  | 2018-10-30 | 2
036909C-1024-PDS-0600-2412 | Process Equipment Datasheet - 10-E-2412 - HP Depropanizer Feed Chiller | A | 2018-10-26 | IFR | OL1-2G30-2412 | PE | 2018-10-30 | 036909C-JVD-TRN-00239 | 036909C-JVD-TRN-00239 | IFR | 2018-11-12 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00239 |  | 2018-10-30 | 2
036909C-1012-PDS-0191-1206 | Process Equipment Datasheet - 10-H-1200 - 1600 - USC 132U Burner | A | 2018-10-26 | IFR | OL1-2G30-1206 | PE | 2018-10-30 | 036909C-JVD-TRN-00241 | 036909C-JVD-TRN-00241 | IFR | 2018-11-12 | 2018-12-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00241 |  | 2018-10-30 | 2
036909C-1011-PDS-0191-1106 | Process Equipment Datasheet - 10-H-1100 - USC 36M Burner | A | 2018-10-26 | IFR | OL1-2G30-1106 | PE | 2018-10-30 | 036909C-JVD-TRN-00241 | 036909C-JVD-TRN-00241 | IFR | 2018-11-12 | 2018-11-27 | R2-Comments as noted | TPSK-LSPA1-T-PE-00241 |  | 2018-10-30 | 2
036909C-1012-JSS-0125-2003 | Project Specification for Cast Intermediate Tube Supports | 0 | 2018-10-15 | IFI | OL1-2M92-2003 | ME | 2018-10-26 | 036909C-JVD-TRN-00232 | 036909C-JVD-TRN-00232 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00232 |  | 2018-10-26 | 3
036909C-1051-SP-0910-5109 | Mechanical Equipment Data Sheet - Condensate Pumps 10-P-5110 A-B | A | 2018-10-25 | IFQ | OL1-2M03-5109 | ME | 2018-10-26 | 036909C-JVD-TRN-00235 | 036909C-JVD-TRN-00235 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00235 |  | 2018-10-26 | 2
036909C-1012-SP-0154-2003 | Particular Techanical Specification for Quench Exchangers | A | 2018-10-18 | IFQ | OL1-2M57-2003 | ME | 2018-10-26 | 036909C-JVD-TRN-00233 | 036909C-JVD-TRN-00233 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00233 |  | 2018-10-26 | 3
036909C-1012-SR-0154-2003 | Scope of Supply for Quench Exchangers | A | 2018-10-18 | IFQ | OL1-2M56-2003 | ME | 2018-10-26 | 036909C-JVD-TRN-00233 | 036909C-JVD-TRN-00233 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00233 |  | 2018-10-26 | 3
036909C-1051-PDS-0600-5103 | Process Equipment Datasheet - 10-E-5100 - Deaerator Vent Condenser | A | 2018-10-25 | IFR | OL1-2G30-5103 | PE | 2018-10-25 | 036909C-JVD-TRN-00230 | 036909C-JVD-TRN-00230 | IFR | 2018-11-08 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00230 |  | 2018-10-25 | 2
036909C-1012-JSS-0191-2009 | Project Specification for Furnace Burners | A | 2018-10-15 | IFR | OL1-2M92-2009 | ME | 2018-10-25 | 036909C-JVD-TRN-00231 | 036909C-JVD-TRN-00231 | IFR | 2018-11-08 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00231 |  | 2018-10-25 | 2
036909C-1012-MR-0154-2003 | Material Requisition for Quench Exchangers | A | 2018-10-18 | IFQ | OL1-2M55-2003 | ME | 2018-10-26 | 036909C-JVD-TRN-00233 | 036909C-JVD-TRN-00233 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00233 |  | 2018-10-26 | 3
036909C-1011-PDS-0610-1109 | Process Equipment Datasheet - 10-E-1110 - USC 36M TLX-1 Quench Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1109 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237 |  | 2018-10-29 | 2
036909C-1021-SP-0910-2146 | Mechanical Equipment Data Sheet - DSG Feed Pumps 10-P-2146 A-B | A | 2018-10-25 | IFQ | OL1-2M03-2146 | ME | 2018-10-26 | 036909C-JVD-TRN-00235 | 036909C-JVD-TRN-00235 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00235 |  | 2018-10-26 | 2
036909C-1011-PDS-0610-1110 | Process Equipment Datasheet - 10-E-1120 - USC 36M TLX-2 Quench Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1110 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237 |  | 2018-10-29 | 2
036909C-1011-PDS-0630-1108 | Process Equipment Datasheet - 10-E-1100A1 - F6 - USC 36M USX Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1108 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237 |  | 2018-10-29 | 2
036909C-1020-PDS-0500-2020 | Process Equipment Datasheet - 10-T-2020 - Light Fuel Oil Stripper | A | 2018-10-26 | IFR | OL1-2G30-2020 | PE | 2018-10-29 | 036909C-JVD-TRN-00238 | 036909C-JVD-TRN-00238 | IFR | 2018-11-12 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00238 |  | 2018-10-29 | 2
036909C-1021-SP-0910-2106 | Mechanical Equipment Data Sheet - Quench Water Pumps - 10-P-2106 A-B-C | A | 2018-10-25 | IFQ | OL1-2M03-2106 | ME | 2018-10-27 | 036909C-JVD-TRN-00236 | 036909C-JVD-TRN-00236 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00236 |  | 2018-10-27 | 2
036909C-1051-SP-0910-5102 | Mechanical Equipment Data Sheet VLP BFW Pumps - 10-P-5102 A-B | A | 2018-10-25 | IFQ | OL1-2M03-5102 | ME | 2018-10-27 | 036909C-JVD-TRN-00236 | 036909C-JVD-TRN-00236 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00236 |  | 2018-10-27 | 2
036909C-1051-SP-0910-5101 | Mechanical Equipment Data Sheet SHP BFW Pumps - 10-P-5100 A-B-C | A | 2018-10-25 | IFQ | OL1-2M03-5101 | ME | 2018-10-27 | 036909C-JVD-TRN-00236 | 036909C-JVD-TRN-00236 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00236 |  | 2018-10-27 | 2
036909C-1012-PDS-0117-1202 | Anticipated Operating Conditions - 10-H-1200/1600 - USC 132U Liquid Cracking Furnace | 0 | 2018-10-24 | IFI | OL1-2G30-1202 | PE | 2018-10-24 | 036909C-JVD-TRN-00224 | 036909C-JVD-TRN-00224 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00224 |  | 2018-10-24 | 3
036909C-1053-PDS-0900-5361 | Process Equipment Datasheet - 10-P-5360 A-C - CTU Cooling Water Pumps | C | 2018-10-25 | IFD | OL1-2G30-5361 | PE | 2018-10-26 | 036909C-JVD-TRN-00234 | 036909C-JVD-TRN-00234 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00075 |  | 2018-10-26 | 1
036909C-1053-PDS-0900-5352 | Process Equipment Datasheet - 10-P-5350 A-H - Olefins Cooling Water Pumps | B | 2018-10-24 | IFD | OL1-2G30-5352 | PE | 2018-10-24 | 036909C-JVD-TRN-00225 | 036909C-JVD-TRN-00225 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00225 |  | 2018-10-24 | 1
036909C-1053-PDS-0300-5355 | Process Equipment Datasheet - 10-PK-5355 - Side Stream Filter Pkg | B | 2018-10-24 | IFD | OL1-2G30-5355 | PE | 2018-10-24 | 036909C-JVD-TRN-00226 | 036909C-JVD-TRN-00226 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00226 |  | 2018-10-24 | 1
036909C-1051-PDS-0600-5113 | Process Equipment Datasheet - 10-E-5113 - Foul Condensate Cooler | A | 2018-10-25 | IFR | OL1-2G30-5113 | PE | 2018-10-25 | 036909C-JVD-TRN-00230 | 036909C-JVD-TRN-00230 | IFR | 2018-11-08 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00230 |  | 2018-10-25 | 2
036909C-1053-PDS-0900-5352 | Process Equipment Datasheet - 10-P-5350 A-H - Olefins Cooling Water Pumps | C | 2018-10-25 | IFD | OL1-2G30-5352 | PE | 2018-10-26 | 036909C-JVD-TRN-00234 | 036909C-JVD-TRN-00234 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00075 |  | 2018-10-26 | 1
036909C-1025-PDS-0800-2572 | Process Equipment Datasheet - 10-D-2570 - Deethanizer Reflux Drum | A | 2018-10-24 | IFR | OL1-2G30-2572 | PE | 2018-10-25 | 036909C-JVD-TRN-00227 | 036909C-JVD-TRN-00227 | IFR | 2018-11-08 | 2018-12-05 | R1-No comments | TPSK-LSPA1-T-PE-00227 |  | 2018-10-25 | 2
036909C-1024-PDS-0600-2455 | Process Equipment Datasheet - 10-E-2455 A-B - LP Depropanizer Reboilers | A | 2018-10-24 | IFR | OL1-2G30-2455 | PE | 2018-10-25 | 036909C-JVD-TRN-00228 | 036909C-JVD-TRN-00228 | IFR | 2018-11-08 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00228 |  | 2018-10-25 | 2
036909C-1010-PDS-0800-1000 | Process Equipment Datasheet - 10-D-1000 - LPG Drum | A | 2018-10-25 | IFR | OL1-2G30-1000 | PE | 2018-10-25 | 036909C-JVD-TRN-00227 | 036909C-JVD-TRN-00227 | IFR | 2018-11-08 | 2018-12-05 | R1-No comments | TPSK-LSPA1-T-PE-00227 |  | 2018-10-25 | 2
036909C-1028-PDS-0600-2858 | Process Equipment Datasheet - 10-E-2858 - HP Ethylene Product Superheater | A | 2018-10-23 | IFR | OL1-2G30-2858 | PE | 2018-10-24 | 036909C-JVD-TRN-00223 | 036909C-JVD-TRN-00223 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00223 |  | 2018-10-24 | 2
036909C-1012-PDS-1040-1211 | Process Equipment Datasheet - 10-C-1200 1600 - USC 132U Induced Draft Fan | B | 2018-10-23 | IFD | OL1-2G30-1211 | PE | 2018-10-24 | 036909C-JVD-TRN-00222 | 036909C-JVD-TRN-00222 | IFI | 2018-11-08 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00222 |  | 2018-10-24 | 2
036909C-1011-PDS-0117-1102 | Anticipated Operating Conditions - 10-H-1100 - USC 36M Gas Cracking Furnace | 0 | 2018-10-24 | IFI | OL1-2G30-1102 | PE | 2018-10-24 | 036909C-JVD-TRN-00224 | 036909C-JVD-TRN-00224 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00224 |  | 2018-10-24 | 3
036909C-1053-PDS-0900-5361 | Process Equipment Datasheet - 10-P-5360 A-C - CTU Cooling Water Pumps | B | 2018-10-24 | IFD | OL1-2G30-5361 | PE | 2018-10-24 | 036909C-JVD-TRN-00225 | 036909C-JVD-TRN-00225 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00225 |  | 2018-10-24 | 1
036909C-1053-PDS-0300-5350 | Process Equipment Datasheet - 10-PK-5350 - Cooling Tower | B | 2018-10-24 | IFD | OL1-2G30-5350 | PE | 2018-10-24 | 036909C-JVD-TRN-00226 | 036909C-JVD-TRN-00226, ROC-TPSK-CECO-T-00020 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00226 |  | 2018-10-24 | 1
036909C-1025-PDS-0800-2506 | Process Equipment Datasheet - 10-D-2506 - Demeth Prefrac Feed Separator No 2 | A | 2018-10-23 | IFR | OL1-2G30-2506 | PE | 2018-10-24 | 036909C-JVD-TRN-00217 | 036909C-JVD-TRN-00217 | IFR | 2018-11-07 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-PE-00217 |  | 2018-10-24 | 2
036909C-1025-PDS-0600-2591 | Process Equipment Datasheet - 10-E-2856 - Ethylene Product Subcooler (FOR NEXT REVISION SEE OL1-2G30-2859) | A | 2018-10-23 | IFR | OL1-2G30-2859 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216 | CHANGE NUMBER - For next revision see 1025-PDS-0600-2859 - OL1-2G30-2859 | 2018-10-24 | 2
036909C-1025-PDS-0800-2551 | Process Equipment Datasheet - 10-D-2550 - Expander Suction Drum | A | 2018-10-23 | IFR | OL1-2G30-2551 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-00218 |  | 2018-10-24 | 2
036909C-1025-PDS-0800-2504 | Process Equipment Datasheet - 10-D-2504 - Demeth Prefrac Feed Separator No 1 | A | 2018-10-23 | IFR | OL1-2G30-2504 | PE | 2018-10-24 | 036909C-JVD-TRN-00217 | 036909C-JVD-TRN-00217 | IFR | 2018-11-07 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-PE-00217 |  | 2018-10-24 | 2
036909C-1025-PDS-0800-2508 | Process Equipment Datasheet - 10-D-2508 - Demeth Prefrac Feed Separator No 3 | A | 2018-10-23 | IFR | OL1-2G30-2508 | PE | 2018-10-24 | 036909C-JVD-TRN-00217 | 036909C-JVD-TRN-00217 | IFR | 2018-11-07 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-PE-00217 |  | 2018-10-24 | 2
036909C-1025-PDS-0600-2545 | Process Equipment Datasheet - 10-E-2545 - Demethanizer Reboiler | A | 2018-10-23 | IFR | OL1-2G30-2545 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216 |  | 2018-10-24 | 2
036909C-1024-SP-0510-2440 | Mechanical Equipment Datasheet for HP Depropanizer | A | 2018-10-23 | IFQ | OL1-2M03-2440 | ME | 2018-10-23 | 036909C-JVD-TRN-00215 | 036909C-JVD-TRN-00215 | IFR | 2018-11-06 | 2018-12-17 | R2-Comments as noted | TPSK-LSPA1-T-ME-00215 |  | 2018-10-23 | 2
036909C-1025-PDS-0600-2515 | Process Equipment Datasheet - 10-E-2515 - Demeth Prefrac Reboiler | A | 2018-10-23 | IFR | OL1-2G30-2515 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216 |  | 2018-10-24 | 2
036909C-1025-PDS-0600-2546 | Process Equipment Datasheet - 10-E-2546 - Demethanizer Bottoms Cooler | A | 2018-10-23 | IFR | OL1-2G30-2546 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216 |  | 2018-10-24 | 2
036909C-1025-PDS-0600-2548 | Process Equipment Datasheet - 10-E-2548 - Demethanizer Bottoms Vaporizer | A | 2018-10-23 | IFR | OL1-2G30-2548 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00216 |  | 2018-10-24 | 2
036909C-1051-PDS-0900-5141 | Process Equipment Datasheet - 10-P-5140 A-B - Intermittent Blowdown Pumps | A | 2018-10-23 | IFR | OL1-2G30-5141 | PE | 2018-10-24 | 036909C-JVD-TRN-00219 | 036909C-JVD-TRN-00219 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00219 |  | 2018-10-24 | 2
036909C-1051-PDS-0900-5111 | Process Equipment Datasheet - 10-P-5112 A-B - Suspect Condensate Pumps | A | 2018-10-23 | IFR | OL1-2G30-5111 | PE | 2018-10-24 | 036909C-JVD-TRN-00219 | 036909C-JVD-TRN-00219 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00219 |  | 2018-10-24 | 2
036909C-1006-JSS-0117-3004 | ME-004 Shell and Tube Heat Exchangers for 36M and 132U Furnace | 0 | 2018-10-18 | IFI | OL1-2R03-1004 | ME | 2018-10-24 | 036909C-JVD-TRN-00221 | 036909C-JVD-TRN-00221, ROC-TPSK-CECO-T-00003 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00221 |  | 2018-10-24 | 3
036909C-1011-PDS-1040-1111 | Process Equipment Datasheet - 10-C-1100 - USC 36M Induced Draft Fan | B | 2018-10-23 | IFD | OL1-2G30-1111 | PE | 2018-10-24 | 036909C-JVD-TRN-00222 | 036909C-JVD-TRN-00222 | IFI | 2018-11-08 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00222 |  | 2018-10-24 | 2
036909C-1012-PP-122 | Project Engineering Plan - Package A1 - Furnaces - Houston Scope (Internal Only) | 0 | 2018-10-22 | IFI | OL1-2W92-2122 | PC | 2018-10-24 | 036909C-JVD-TRN-00220 | 036909C-JVD-TRN-00220 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PM-00220 |  | 2018-10-24 | 3
036909C-1028-PDS-0800-2805 | Process Equipment Datasheet - 10-D-2805 - C3R Surge Drum | A | 2018-10-23 | IFR | OL1-2G30-2805 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218 |  | 2018-10-24 | 2
036909C-1025-PDS-0800-2525 | Process Equipment Datasheet - 10-D-2525 - Hydrogen Drum | A | 2018-10-23 | IFR | OL1-2G30-2525 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218 |  | 2018-10-24 | 2
036909C-1025-PDS-0800-2555 | Process Equipment Datasheet - 10-D-2555 - Expander Discharge Drum | A | 2018-10-23 | IFR | OL1-2G30-2555 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218 |  | 2018-10-24 | 2
036909C-1051-PDS-0900-5121 | Process Equipment Datasheet - 10-P-5120 A-B - Raw Condensate Pumps | A | 2018-10-23 | IFR | OL1-2G30-5121 | PE | 2018-10-24 | 036909C-JVD-TRN-00219 | 036909C-JVD-TRN-00219 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00219 |  | 2018-10-24 | 2
036909C-1028-PDS-0800-2870 | Process Equipment Datasheet - 10-D-2870 - C2R 2nd Stage Suction Drum | A | 2018-10-23 | IFR | OL1-2G30-2870 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-00218 |  | 2018-10-24 | 2
036909C-1028-PDS-0800-2854 | Process Equipment Datasheet - 10-D-2855 - C2R Surge Drum | A | 2018-10-23 | IFR | OL1-2G30-2854 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218 |  | 2018-10-24 | 2
036909C-1006-JSS-0117-0005 | ME-005 Double Jacket Pipe Heat Exchangers for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL1-2R03-0005 | ME | 2018-10-23 | 036909C-JVD-TRN-00212 | 036909C-JVD-TRN-00212, ROC-TPSK-CECO-T-00003 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00212 |  | 2018-10-23 | 3
036909C-1053-SP-0910-5361 | Mechanical Equipment Data Sheet for CTU Cooling Water Pumps 10-P-5360 A-B-C | A | 2018-10-22 | IFQ | OL1-2M03-5361 | ME | 2018-10-23 | 036909C-JVD-TRN-00210 | 036909C-JVD-TRN-00210 | IFR | 2018-11-06 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00210 |  | 2018-10-23 | 2
036909C-1021-PDS-0600-2166 | Process Equipment Datasheet - 10-E-2166 - DSG Blowdown Cooler | A | 2018-10-22 | IFR | OL1-2G30-2166 | PE | 2018-10-23 | 036909C-JVD-TRN-00209 | 036909C-JVD-TRN-00209 | IFR | 2018-11-06 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00209 |  | 2018-10-23 | 2
036909C-1028-PDS-0800-2880 | Process Equipment Datasheet - 10-D-2880 - C2R 3rd Stage Suction Drum | A | 2018-10-22 | IFR | OL1-2G30-2880 | PE | 2018-10-23 | 036909C-JVD-TRN-00208 | 036909C-JVD-TRN-00208 | IFR | 2018-11-06 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00208 |  | 2018-10-23 | 2
036909C-1006-JSS-0117-0009 | SP-009 Painting for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL1-2R07-0009 | ME | 2018-10-23 | 036909C-JVD-TRN-00214 | 036909C-JVD-TRN-00214 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00214 |  | 2018-10-23 | 3
036909C-1006-JSS-0117-1001 | Approved Vendor List for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL1-2M91-1001 | ME | 2018-10-23 | 036909C-JVD-TRN-00211 | 036909C-JVD-TRN-00211 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00211 |  | 2018-10-23 | 3
036909C-1053-SP-0910-5352 | Mechanical Equipment Data Sheet for Olefins Cooling Water Pumps 10-P-5350 A-H | A | 2018-10-22 | IFQ | OL1-2M03-5352 | ME | 2018-10-23 | 036909C-JVD-TRN-00210 | 036909C-JVD-TRN-00210 | IFR | 2018-11-06 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00210 |  | 2018-10-23 | 2
036909C-1006-JSS-0117-0007 | PIP-007 Marking of Piping Material for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL1-2R04-0007 | ME | 2018-10-23 | 036909C-JVD-TRN-00213 | 036909C-JVD-TRN-00213 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00213 |  | 2018-10-23 | 3
036909C-1023-PDS-0840-2307 | Process Equipment Datasheet - 10-F-2306 A-B - Weak Caustic Circulating Filters | A | 2018-10-18 | IFR | OL1-2G30-2307 | PE | 2018-10-22 | 036909C-JVD-TRN-00205 | 036909C-JVD-TRN-00205 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00205 |  | 2018-10-22 | 2
036909C-1022-PDS-0600-2221 | Process Equipment Datasheet - 10-E-2220 A-B - CG 2nd Stage Aftercoolers | A | 2018-10-18 | IFR | OL1-2G30-2221 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00206 |  | 2018-10-22 | 2
036909C-1010-PDS-0600-1051 | Process Equipment Datasheet - 10-E-1050 - C2 Feed Superheater | A | 2018-10-18 | IFR | OL1-2G30-1051 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00206 |  | 2018-10-22 | 2
036909C-1023-PDS-0840-2314 | Process Equipment Datasheet - 10-F-2310 A-B - Wash Oil Circulating Filter | A | 2018-10-18 | IFR | OL1-2G30-2314 | PE | 2018-10-22 | 036909C-JVD-TRN-00205 | 036909C-JVD-TRN-00205 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00205 |  | 2018-10-22 | 2
036909C-1012-MR-0127-2002 | Material Requisition for Furnace Convection Fittings | A | 2018-10-16 | IFQ | OL1-2M55-2002 | ME | 2018-10-22 | 036909C-JVD-TRN-00207 | 036909C-JVD-TRN-00207 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00207 |  | 2018-10-22 | 3
036909C-1012-SP-0127-2002 | Particular Technical Specification for Furnace Convection Fittings | A | 2018-10-16 | IFQ | OL1-2M57-2002 | ME | 2018-10-22 | 036909C-JVD-TRN-00207 | 036909C-JVD-TRN-00207 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00207 |  | 2018-10-22 | 3
036909C-1010-PDS-0600-1020 | Process Equipment Datasheet - 10-E-1020 - Liquid Feed Heater | A | 2018-10-18 | IFR | OL1-2G30-1020 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00206 |  | 2018-10-22 | 2
036909C-1012-SR-0127-2002 | Scope of Supply for Furnace Convection Fittings | A | 2018-10-16 | IFQ | OL1-2M56-2002 | ME | 2018-10-22 | 036909C-JVD-TRN-00207 | 036909C-JVD-TRN-00207 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00207 |  | 2018-10-22 | 3
036909C-1026-PDS-0500-2640 | Process Equipment Datasheet - 10-T-2640 - C3 Tower | A | 2018-10-18 | IFR | OL1-2G30-2640 | PE | 2018-10-22 | 036909C-JVD-TRN-00201 | 036909C-JVD-TRN-00201 | IFR | 2018-11-05 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00201 |  | 2018-10-22 | 2
036909C-1021-PDS-0900-2146 | Process Equipment Datasheet - 10-P-2146 A-B - DSG Feed Pumps | B | 2018-10-18 | IFD | OL1-2G30-2146 | PE | 2018-10-22 | 036909C-JVD-TRN-00202 | 036909C-JVD-TRN-00202 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00202 |  | 2018-10-22 | 1
036909C-1020-PDS-0900-2006 | Process Equipment Datasheet - 10-P-2006 A-C - Quench Oil Pumps | B | 2018-10-18 | IFD | OL1-2G30-2006 | PE | 2018-10-22 | 036909C-JVD-TRN-00202 | 036909C-JVD-TRN-00202 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00202 |  | 2018-10-22 | 1
036909C-1000-MS-1422-0001 | Technical Specification for Geotechnical Investigation | B | 2018-10-15 | IFR | OL1-2K43-0002 | CV | 2018-10-17 | 036909C-JVD-TRN-00188 | 036909C-JVD-TRN-00188 | IFR | 2018-11-05 | 2018-11-01 | R1-No comments | TPSK-LSPA1-T-CV-00188 |  | 2018-10-22 | 2
036909C-1021-PDS-0900-2106 | Process Equipment Datasheet - 10-P-2106 A-C - Quench Water Pumps | B | 2018-10-18 | IFD | OL1-2G30-2106 | PE | 2018-10-22 | 036909C-JVD-TRN-00202 | 036909C-JVD-TRN-00202 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00202 |  | 2018-10-22 | 1
036909C-1012-PDS-0117-1201 | Process Equipment Datasheet - 10-H-1200 - 132U Cracking Furnace Yields | A | 2018-10-15 | IFR | OL1-2G30-1201 | PE | 2018-10-22 | 036909C-JVD-TRN-00204 | 036909C-JVD-TRN-00204 | IFR | 2018-11-05 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00204 |  | 2018-10-22 | 2
036909C-1022-PDS-0600-2231 | Process Equipment Datasheet - 10-E-2230 A-B - CG 3rd Stage Aftercooler | A | 2018-10-18 | IFR | OL1-2G30-2231 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00206 |  | 2018-10-22 | 2
036909C-1023-PDS-2500-2320 | Process Equipment Datasheet - 10-TK-2320 - Spent Caustic Storage Tank | B | 2018-10-18 | IFD | OL1-2G30-2320 | PE | 2018-10-22 | 036909C-JVD-TRN-00203 | 036909C-JVD-TRN-00203 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00203 |  | 2018-10-22 | 1
036909C-1022-PDS-0600-2241 | Process Equipment Datasheet - 10-E-2240 A-B - CG 4th Stage Aftercooler | A | 2018-10-18 | IFR | OL1-2G30-2241 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00206 |  | 2018-10-22 | 2
036909C-1011-PDS-0117-1101 | Process Equipment Datasheet - 10-H-1100 - 36M Cracking Furnace Yields | A | 2018-10-15 | IFR | OL1-2G30-1101 | PE | 2018-10-22 | 036909C-JVD-TRN-00204 | 036909C-JVD-TRN-00204 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00204 |  | 2018-10-22 | 2
036909C-1000-JSS-1140-0001 | ME-013 Diesel Engine | A | 2018-10-22 | IFR | OL1-2R03-0013 | ME | 2018-10-18 | 036909C-JVD-TRN-00196 | 036909C-JVD-TRN-00196 | IFR | 2018-11-06 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-ME-00196 |  | 2018-10-18 | 2
036909C-1028-PDS-0800-2860 | Process Equipment Datasheet - 10-D-2860 - C2R 1st Stage Suction Drum | A | 2018-10-22 | IFR | OL1-2G30-2860 | PE | 2018-10-23 | 036909C-JVD-TRN-00208 | 036909C-JVD-TRN-00208 | IFR | 2018-11-06 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-PE-00208 |  | 2018-10-23 | 2
036909C-1021-PDS-0600-2165 | Process Equipment Datasheet - 10-E-2165 A-D DSG Reboilers | A | 2018-10-17 | IFR | OL1-2G30-2165 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00194 |  | 2018-10-18 | 2
036909C-1000-SP-1013-0001 | Particular Technical Specification for Integrally Geared Decoking Air Compressors | A | 2018-10-18 | IFQ | OL1-2M57-0014 | ME | 2018-10-19 | 036909C-JVD-TRN-00198 | 036909C-JVD-TRN-00198 | IFR | 2018-11-02 | 2018-11-07 | Transmitted | TPSK-LSPA1-T-ME-00198 |  | 2018-10-19 | 2
036909C-1021-PDS-0600-2161 | Process Equipment Datasheet - 10-E-2160 - Dilution Steam Superheater | A | 2018-10-17 | IFR | OL1-2G30-2161 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00194 |  | 2018-10-18 | 2
036909C-1000-PP-502 | Confidentiality Plan | A | 2018-10-18 | IFR | OL1-2Q92-0002 | QM | 2018-10-19 | 036909C-JVD-TRN-00199 | 036909C-JVD-TRN-00199 | IFR | 2018-11-02 |  | Transmitted | TPSK-LSPA1-T-QM-00199 |  | 2018-10-19 | 2
036909C-1000-PS-1422-0001 | Price List for Geotechnical Investigation | B | 2018-10-15 | IFR | OL1-2K43-0003 | CV | 2018-10-17 | 036909C-JVD-TRN-00188 | 036909C-JVD-TRN-00188 | IFR | 2018-11-05 | 2018-11-01 | R1-No comments | TPSK-LSPA1-T-CV-00188 |  | 2018-10-22 | 2
036909C-1021-PDS-0600-2147 | Process Equipment Datasheet - 10-E-2146 - DSG Feed Heater | A | 2018-10-17 | IFR | OL1-2G30-2147 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00194 |  | 2018-10-18 | 2
036909C-1000-MR-1013-0001 | Material Requisition For Integrally Geared Decoking Air Compressors | A | 2018-10-18 | IFQ | OL1-2M55-0014 | ME | 2018-10-19 | 036909C-JVD-TRN-00198 | 036909C-JVD-TRN-00198 | IFR | 2018-11-02 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-ME-00198 |  | 2018-10-19 | 2
036909C-1000-SR-1013-0001 | Scope Of Supply For Integrally Geared Decoking Air Compressors | A | 2018-10-18 | IFQ | OL1-2M56-0014 | ME | 2018-10-19 | 036909C-JVD-TRN-00198 | 036909C-JVD-TRN-00198 | IFR | 2018-11-02 | 2018-11-07 | Transmitted | TPSK-LSPA1-T-ME-00198 |  | 2018-10-19 | 2
036909C-1025-PDS-0500-2570 | Process Equipment Datasheet - 10-T-2570 - Deethanizer | A | 2018-10-17 | IFR | OL1-2G30-2570 | PE | 2018-10-17 | 036909C-JVD-TRN-00191 | 036909C-JVD-TRN-00191 | IFR | 2018-10-31 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00191 |  | 2018-10-18 | 2
036909C-1025-PDS-4100-2560 | Process Equipment Datasheet - 10-PK-2560 - PSA Unit | A | 2018-10-17 | IFR | OL1-2G30-2560 | PE | 2018-10-17 | 036909C-JVD-TRN-00190 | 036909C-JVD-TRN-00190 | IFR | 2018-10-31 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00190 |  | 2018-10-18 | 2
036909C-1021-PDS-0600-2145 | Process Equipment Datasheet - 10-E-2145 - Process Water Stripper Reboiler | A | 2018-10-17 | IFR | OL1-2G30-2145 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-12-27 | R1-No comments | TPSK-LSPA1-T-PE-00194 |  | 2018-10-18 | 2
036909C-1021-PDS-0600-2137 | Process Equipment Datasheet - 10-E-2136 - Process Water Stripper Feed Heater | A | 2018-10-17 | IFR | OL1-2G30-2137 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00194 |  | 2018-10-18 | 2
036909C-1006-JSS-0117-1004 | PIP-004 Piping Welding Specification for 36M and 132U Furnace | 0 | 2018-10-15 | IMP | OL1-2R04-1004 | ME | 2018-10-16 | 036909C-JVD-TRN-00184 | 036909C-JVD-TRN-00184 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00184 |  | 2018-10-17 | 3
036909C-1024-SP-0510-2450 | Mechanical Equipment Datasheet LP Depropanizer | A | 2018-10-15 | IFQ | OL1-2M03-2450 | ME | 2018-10-16 | 036909C-JVD-TRN-00183 | 036909C-JVD-TRN-00183 | IFR | 2018-10-30 | 2018-11-05 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00183 |  | 2018-10-17 | 2
036909C-1021-PDS-0500-2140 | Process Equipment Datasheet - 10-T-2140 - Process Water Stripper | A | 2018-10-17 | IFR | OL1-2G30-2140 | PE | 2018-10-17 | 036909C-JVD-TRN-00189 | 036909C-JVD-TRN-00189 | IFR | 2018-10-31 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00189 |  | 2018-10-18 | 2
036909C-1006-JSS-0117-0029 | ME-029 Centrifugal Blower for 36M and 132U Furnace | 0 | 2018-10-16 | IMP | OL1-2R03-0029 | ME | 2018-10-17 | 036909C-JVD-TRN-00185 | 036909C-JVD-TRN-00185, ROC-TPSK-CECO-T-00003 | IFI |  | 2018-11-05 | Transmitted | TPSK-LSPA1-T-ME-00185 |  | 2018-10-17 | 3
036909C-1012-SP-0122-2004 | Particular Technical Specification For Radiant Coil Assemblies | A | 2018-09-10 | IFI | OL1-2M57-2004 | ME | 2018-09-18 | 036909C-JVD-TRN-00063 | 036909C-JVD-TRN-00063 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00063 |  | 2018-10-18 | 3
036909C-1010-PDS-0600-1005 | Process Equipment Datasheet - 10-E-1005 - LPG Feed Heater | A | 2018-10-15 | IFR | OL1-2G30-1005 | PE | 2018-10-15 | 036909C-JVD-TRN-00176 | 036909C-JVD-TRN-00176 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00176 |  | 2018-10-16 | 2
036909C-1010-PDS-0600-1015 | Process Equipment Datasheet - 10-E-1015 - LPG Superheater | A | 2018-10-15 | IFR | OL1-2G30-1015 | PE | 2018-10-15 | 036909C-JVD-TRN-00176 | 036909C-JVD-TRN-00176 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00176 |  | 2018-10-16 | 2
036909C-1010-PDS-0600-1003 | Process Equipment Datasheet - 10-E-1001 - LPG Steam Vaporizer | A | 2018-10-15 | IFR | OL1-2G30-1003 | PE | 2018-10-16 | 036909C-JVD-TRN-00179 | 036909C-JVD-TRN-00179 | IFR | 2018-10-30 | 2019-01-28 | R1-No comments | TPSK-LSPA1-T-PE-00179 |  | 2018-10-16 | 2
036909C-1023-PDS-0900-2304 | Process Equipment Datasheet - 10-P-2304 - Intermediate Caustic Circulating Pump | A | 2018-10-12 | IFR | OL1-2G30-2304 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00174 |  | 2018-10-16 | 2
036909C-1024-PDS-0500-2450 | Process Equipment Datasheet - 10-T-2450 - LP Depropanizer | B | 2018-10-11 | IFD | OL1-2G30-2450 | PE | 2018-10-12 | 036909C-JVD-TRN-00167 | 036909C-JVD-TRN-00167 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00167 |  | 2018-10-15 | 3
036909C-1000-PP-132 | TPSK KLOC Organization Chart | 0 | 2018-10-15 | IFI | OL1-2W92-0021 | PC | 2018-10-15 | 036909C-JVD-TRN-00171 | 036909C-JVD-TRN-00171 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PC-00171 |  | 2018-10-15 | 3
036909C-1023-PDS-4200-2313 | Process Equipment Datasheet - 10-X-2312 - Spent Wash Oil Mixer | A | 2018-10-12 | IFR | OL1-2G30-2313 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00173 |  | 2018-10-16 | 2
036909C-1023-PDS-4200-2315 | Process Equipment Datasheet - 10-X-2310 - Spent Caustic Mixer | A | 2018-10-12 | IFR | OL1-2G30-2315 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00173 |  | 2018-10-16 | 2
036909C-1023-PDS-0900-2306 | Process Equipment Datasheet - 10-P-2306 A-B - Weak Caustic Circulating Pumps | A | 2018-10-12 | IFR | OL1-2G30-2306 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00174 |  | 2018-10-16 | 2
036909C-1023-PDS-0900-2302 | Process Equipment Datasheet - 10-P-2302 A-B - Strong Caustic Circulating Pumps | A | 2018-10-12 | IFR | OL1-2G30-2302 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00174 |  | 2018-10-16 | 2
036909C-1026-PDS-0500-2660 | Process Equipment Datasheet - 10-T-2660 - Debutanizer | B | 2018-10-12 | IFD | OL1-2G30-2660 | PE | 2018-10-12 | 036909C-JVD-TRN-00169 | 036909C-JVD-TRN-00169 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00169 |  | 2018-10-15 | 3
036909C-1026-PDS-0500-2630 | Process Equipment Datasheet - 10-T-2630 - Secondary Deethanizer | B | 2018-10-12 | IFD | OL1-2G30-2630 | PE | 2018-10-12 | 036909C-JVD-TRN-00169 | 036909C-JVD-TRN-00169 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00169 |  | 2018-10-15 | 3
036909C-1023-PDS-0900-2311 | Process Equipment Datasheet - 10-P-2310 A-B - Wash Oil Circulating Pumps | A | 2018-10-12 | IFR | OL1-2G30-2311 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00174 |  | 2018-10-16 | 2
036909C-1010-PDS-0600-1001 | Process Equipment Datasheet - 10-E-1000 - LPG Vaporizer | A | 2018-10-15 | IFR | OL1-2G30-1001 | PE | 2018-10-15 | 036909C-JVD-TRN-00176 | 036909C-JVD-TRN-00176 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00176 |  | 2018-10-16 | 2
036909C-1022-PDS-0800-2240 | Process Equipment Datasheet - 10-D-2240 - CG 4th Stage Suction Drum | A | 2018-10-12 | IFR | OL1-2G30-2240 | PE | 2018-10-15 | 036909C-JVD-TRN-00175 | 036909C-JVD-TRN-00175 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00175 |  | 2018-10-16 | 2
036909C-1055-PDS-0800-5500 | Process Equipment Datasheet - 10-D-5500 - Hot Flare Drum | A | 2018-10-12 | IFR | OL1-2G30-5500 | PE | 2018-10-12 | 036909C-JVD-TRN-00168 | 036909C-JVD-TRN-00168 | IFR | 2018-10-26 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00168 |  | 2018-10-15 | 2
036909C-1023-PDS-4200-2308 | Process Equipment Datasheet - 10-X-2306 - Weak Caustic - Wash Oil Mixer | A | 2018-10-12 | IFR | OL1-2G30-2308 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00173 |  | 2018-10-16 | 2
036909C-1025-PDS-0500-2520 | Process Equipment Datasheet - 10-T-2520 and 10-D-2520 - Residue Gas Rectifier & Reflux Drum | A | 2018-10-12 | IFR | OL1-2G30-2520 | PE | 2018-10-15 | 036909C-JVD-TRN-00172 | 036909C-JVD-TRN-00172 | IFR | 2018-10-29 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00172 |  | 2018-10-16 | 2
036909C-1023-PDS-0800-2316 | Process Equipment Datasheet - 10-D-2316 - Spent Caustic Degassing Drum | A | 2018-10-12 | IFR | OL1-2G30-2316 | PE | 2018-10-15 | 036909C-JVD-TRN-00175 | 036909C-JVD-TRN-00175 | IFR | 2018-10-29 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00175 |  | 2018-10-16 | 2
036909C-1023-PDS-0800-2331 | Process Equipment Datasheet - 10-D-2330 - Spent Caustic Stripper Ovhd Drum | A | 2018-10-12 | IFR | OL1-2G30-2331 | PE | 2018-10-15 | 036909C-JVD-TRN-00175 | 036909C-JVD-TRN-00175 | IFR | 2018-10-29 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00175 |  | 2018-10-16 | 2
036909C-1029-PDS-2600-2914 | Process Equipment Datasheet - 10-PK-2914 - Neutralization Injection Pkg | A | 2018-10-15 | IFR | OL1-2G30-2914 | PE | 2018-10-16 | 036909C-JVD-TRN-00181 | 036909C-JVD-TRN-00181, ROC-TPSK-CECO-T-00019 | IFR | 2018-10-30 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00181 |  | 2018-10-16 | 2
036909C-1023-PDS-4200-2301 | Process Equipment Datasheet - 10-X-2300 - Caustic Dilution Mixer | A | 2018-10-12 | IFR | OL1-2G30-2301 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00173 |  | 2018-10-16 | 2
036909C-1023-PDS-4100-2350 | Process Equipment Datasheet - 10-PK-2350 - Wet Air Oxidation Pkg | A | 2018-10-15 | IFR | OL1-2G30-2350 | PE | 2018-10-16 | 036909C-JVD-TRN-00180 | 036909C-JVD-TRN-00180, ROC-TPSK-CECO-T-00019 | IFR | 2018-10-30 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00180 |  | 2018-10-16 | 2
036909C-1020-PDS-0500-2000 | Process Equipment Datasheet - 10-T-2000 - Quench Oil Tower | A | 2018-10-11 | IFR | OL1-2G30-2000 | PE | 2018-10-12 | 036909C-JVD-TRN-00162 | 036909C-JVD-TRN-00162 | IFR | 2018-10-26 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00162 |  | 2018-10-15 | 2
036909C-1020-PDS-0500-2040 | Process Equipment Datasheet - 10-T-2040 - Heavy Fuel Oil Stripper | A | 2018-10-11 | IFR | OL1-2G30-2040 | PE | 2018-10-12 | 036909C-JVD-TRN-00162 | 036909C-JVD-TRN-00162 | IFR | 2018-10-26 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00162 |  | 2018-10-15 | 2
036909C-1024-PDS-0500-2440 | Process Equipment Datasheet - 10-T-2440 - HP Depropanizer | B | 2018-10-11 | IFD | OL1-2G30-2440 | PE | 2018-10-12 | 036909C-JVD-TRN-00167 | 036909C-JVD-TRN-00167 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00167 |  | 2018-10-15 | 3
036909C-1025-PDS-0500-2580 | Process Equipment Datasheet - 10-T-2580 - C2 Tower | A | 2018-10-11 | IFR | OL1-2G30-2580 | PE | 2018-10-12 | 036909C-JVD-TRN-00162 | 036909C-JVD-TRN-00162 | IFR | 2018-10-26 | 2018-10-31 | R2-Comments as noted | TPSK-LSPA1-T-PE-00162 |  | 2018-10-15 | 2
036909C-1000-JSS-1160-0001 | ME-022 Special Purpose Gear | A | 2018-10-12 | IFR | OL1-2R03-0022 | ME | 2018-10-12 | 036909C-JVD-TRN-00166 | 036909C-JVD-TRN-00166 | IFR | 2018-10-26 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-ME-00166 |  | 2018-10-15 | 2
036909C-1000-JSD-1501-0002 | General Design Rules For SmartPlant Instrumentation Setup | A | 2018-09-27 | IFR | OL1-2R06-0024 | IE | 2018-09-28 | 036909C-JVD-TRN-00109 | 036909C-JVD-TRN-00109 | IFR | 2018-10-11 | 2018-10-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-00109 |  | 2018-09-28 | 2
036909C-1011-PDS-0811-1107 | Process Equipment Datasheet - 10-D-1100 - 36M Cracking Furnace Steam Drum | A | 2018-10-11 | IFR | OL1-2G30-1107 | PE | 2018-10-11 | 036909C-JVD-TRN-00159 | 036909C-JVD-TRN-00159 | IFR | 2018-10-25 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00159 |  | 2018-10-12 | 2
036909C-1019-SP-1013-1950 | Mechanical Equipment Datasheet for Decoke Air Compressor Package | B | 2018-10-10 | IFQ | OL1-2M03-1950 | ME | 2018-10-11 | 036909C-JVD-TRN-00161 | 036909C-JVD-TRN-00161 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00161 |  | 2018-10-12 | 3
036909C-1000-JSS-1013-0001 | ME-016 Centrifugal Compressor For PA/IA Servise | A | 2018-10-09 | IFR | OL1-2R03-0016 | ME | 2018-10-12 | 036909C-JVD-TRN-00164 | 036909C-JVD-TRN-00164 | IFR | 2018-10-26 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-ME-00164 |  | 2018-10-15 | 2
036909C-1023-PDS-0500-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper | B | 2018-10-10 | IFA | OL1-2G30-2330 | PE | 2018-10-11 | 036909C-JVD-TRN-00160 | 036909C-JVD-TRN-00160 | IFA | 2018-10-25 | 2019-02-25 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00160 |  | 2018-10-12 | 1
036909C-1056-PDS-0200-5620 | Process Equipment Datasheet - 10-PIT-5620 A-C - Olefins Holding Basin | C | 2019-03-14 | IFD | OL1-2G30-5620 | PE | 2019-03-14 | 036909C-JVD-TRN-01068 | 036909C-JVD-TRN-01068, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-PE-01068 |  | 2019-03-15 | 2
036909C-1056-PDS-0200-5620 | Process Equipment Datasheet - 10-PIT-5620 A-C - Olefins Holding Basin | A | 2019-01-02 | IFR | OL1-2G30-5620 | PE | 2019-01-07 | 036909C-JVD-TRN-00589 | 036909C-JVD-TRN-00589 | IFR | 2019-01-21 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00589 |  | 2019-01-07 | 2
036909C-1056-PDS-0200-5620 | Process Equipment Datasheet - 10-PIT-5620 A-C - Olefins Holding Basin | B | 2019-02-28 | IFD | OL1-2G30-5620 | PE | 2019-03-01 | 036909C-JVD-TRN-00960 | 036909C-JVD-TRN-00960 | IFR | 2019-03-16 | 2019-03-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00960 |  | 2019-03-04 | 2
036909C-1056-PDS-0200-5642 | Process Equipment Datasheet - 10-PIT-5642 - Cooling Water Blowdown Basin | B | 2019-04-26 | IFD | OL1-2G30-5642 | PE | 2019-04-26 | 036909C-JVD-TRN-01511 | 036909C-JVD-TRN-01511 | IFR | 2019-05-13 | 2019-06-17 | R1-No comments | TPSK-LSPA1-T-PE-01511 |  | 2019-04-29 | 2
036909C-1056-PDS-0200-5642 | Process Equipment Datasheet - 10-PIT-5642 - Cooling Water Blowdown Basin | A | 2019-02-05 | IFR | OL1-2G30-5642 | PE | 2019-02-06 | 036909C-JVD-TRN-00808 | 036909C-JVD-TRN-00808, ROC-TPSK-CECO-T-00020 | IFR | 2019-02-19 | 2019-03-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-00808 |  | 2019-02-06 | 2
036909C-1056-PDS-0200-5615 | Process Equipment Datasheet - 10-PIT-5615 - Olefins Stormwater Sump | A | 2019-01-10 | IFR | OL1-2G30-5615 | PE | 2019-01-11 | 036909C-JVD-TRN-00636 | 036909C-JVD-TRN-00636 | IFR | 2019-01-24 | 2019-02-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00636 |  | 2019-01-11 | 2
036909C-1056-PDS-0200-5615 | Process Equipment Datasheet - 10-PIT-5615 - Olefins Stormwater Sump | C | 2019-03-14 | IFD | OL1-2G30-5615 | PE | 2019-03-14 | 036909C-JVD-TRN-01068 | 036909C-JVD-TRN-01068, ROC-TPSK-CECO-T-00020 | IFR | 2019-03-29 | 2019-04-02 | R1-No comments | TPSK-LSPA1-T-PE-01068 |  | 2019-03-15 | 2
036909C-1056-PDS-0200-5615 | Process Equipment Datasheet - 10-PIT-5615 - Olefins Stormwater Sump | B | 2019-02-28 | IFD | OL1-2G30-5615 | PE | 2019-03-01 | 036909C-JVD-TRN-00960 | 036909C-JVD-TRN-00960 | IFR | 2019-03-16 | 2019-03-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00960 |  | 2019-03-04 | 2
036909C-100M-DW-0051-0001 | Detail Plot Plan Zone 0M Metering Station | B | 2019-08-20 | IBD | OL1-2P06-0002 | MP | 2019-08-22 | 036909C-JVD-TRN-02472 | 036909C-JVD-TRN-02472 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-MP-02472 |  | 2019-08-23 | 2
036909C-103A-DW-1442-0001 | Major Underground Networks - Zone 3A - Butadiene Extraction Unit - New doc Client Ref OL1-2K26-0008 | A | 2019-03-22 | IFR | OL1-2K36-0008 | CV | 2019-03-25 | 036909C-JVD-TRN-01138 | 036909C-JVD-TRN-01138, ROC-TPSK-CECO-T-00025 | IFR | 2019-04-09 | 2019-06-05 | R2-Comments as noted | TPSK-LSPA1-T-CV-01138 | New doc Client Ref OL1-2K26-0008 | 2019-03-26 | 2
036909C-102E-DW-1624-0001 | Electrical Cable Routing Cross Sections - Zone 2E | A | 2019-07-18 | IFR | OL1-2E34-0014 | EE | 2019-07-22 | 036909C-JVD-TRN-02226 | 036909C-JVD-TRN-02226 | IFR | 2019-08-06 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-EE-02226 |  | 2019-07-23 | 2
036909C-102C-DW-1624-0001 | Electrical Cable Routing Cross Sections Cover Page - Zone-2C | A | 2019-07-25 | IFR | OL1-2E34-0012 | EE | 2019-07-26 | 036909C-JVD-TRN-02269 | 036909C-JVD-TRN-02269 | IFR | 2019-08-12 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-EE-02269 |  | 2019-07-29 | 2
036909C-102D-DW-1624-0001 | Electrical Cable Routing Cross Sections - Zone-2D | A | 2019-07-24 | IFR | OL1-2E34-0013 | EE | 2019-07-29 | 036909C-JVD-TRN-02276 | 036909C-JVD-TRN-02276 | IFR | 2019-08-13 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-EE-02276 |  | 2019-07-30 | 2
036909C-102B-DW-1624-0001 | Electrical Cable Routing Cross Sections - Zone-2B | A | 2019-07-24 | IFR | OL1-2E34-0011 | EE | 2019-07-29 | 036909C-JVD-TRN-02276 | 036909C-JVD-TRN-02276 | IFR | 2019-08-13 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-EE-02276 |  | 2019-07-30 | 2
036909C-102A-DW-1624-0001 | Electrical Cable Routing Cross Sections - Zone-2A | A | 2019-07-24 | IFR | OL1-2E34-0010 | EE | 2019-07-29 | 036909C-JVD-TRN-02276 | 036909C-JVD-TRN-02276 | IFR | 2019-08-13 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-EE-02276 |  | 2019-07-30 | 2
036909C-101B-DW-1624-0001 | Electrical Cable Routing Cross Sections - Zone-1B | A | 2019-07-24 | IFR | OL1-2E34-0009 | EE | 2019-07-29 | 036909C-JVD-TRN-02276 | 036909C-JVD-TRN-02276 | IFR | 2019-08-13 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-EE-02276 |  | 2019-07-30 | 2
036909C-1024-PID-0021-2444 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - CG Secondary Dehydrator | C | 2019-08-16 | IDD1 | OL1-2G43-2444 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2442 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Reactor C | C | 2019-08-16 | IDD1 | OL1-2G43-2442 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2440 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Reactor B Intercooling | C | 2019-08-16 | IDD1 | OL1-2G43-2440 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2439 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Reactor B | C | 2019-08-16 | IDD1 | OL1-2G43-2439 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2438 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Reactor A Intercooling | C | 2019-08-16 | IDD1 | OL1-2G43-2438 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2437 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Reactor A | C | 2019-08-16 | IDD1 | OL1-2G43-2437 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2435 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Feed Heating | C | 2019-08-16 | IDD1 | OL1-2G43-2435 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2433 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Arsine Guard Removal | C | 2019-08-16 | IDD1 | OL1-2G43-2433 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2432 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - CG Compressor 5th Stage Aftercooling | C | 2019-08-16 | IDD1 | OL1-2G43-2432 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2430 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - 5th Stage Cracked Gas Compression | C | 2019-08-16 | IDD1 | OL1-2G43-2430 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2428 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer Product-Reflux Pumps | C | 2019-08-16 | IDD1 | OL1-2G43-2428 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2427 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer Overhead | C | 2019-08-16 | IDD1 | OL1-2G43-2427 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2426 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer Reboiler | C | 2019-08-16 | IDD1 | OL1-2G43-2426 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2425 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | C | 2019-08-16 | IDD1 | OL1-2G43-2425 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2423 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer Reboiler | C | 2019-08-16 | IDD1 | OL1-2G43-2423 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2422 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | C | 2019-08-16 | IDD1 | OL1-2G43-2422 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2420 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer Feed Chilling | C | 2019-08-16 | IDD1 | OL1-2G43-2420 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2419 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Cracked Gas Mercury Adsorber | C | 2019-08-16 | IDD1 | OL1-2G43-2419 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2414 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration Gas Cooling | C | 2019-08-16 | IDD1 | OL1-2G43-2414 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2412 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration Gas Heating | C | 2019-08-16 | IDD1 | OL1-2G43-2412 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2410 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration - Sheet 2 | C | 2019-08-16 | IDD1 | OL1-2G43-2410 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2409 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration - Sheet 1 | C | 2019-08-16 | IDD1 | OL1-2G43-2409 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2407 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Liquid Dryers - Sheet 2 | C | 2019-08-16 | IDD1 | OL1-2G43-2407 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2406 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Liquid Dryers - Sheet 1 | C | 2019-08-16 | IDD1 | OL1-2G43-2406 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2404 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Liquid Drier Feed Coalescer | C | 2019-08-16 | IDD1 | OL1-2G43-2404 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2402 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Caustic Tower Overhead KO Drum | C | 2019-08-16 | IDD1 | OL1-2G43-2402 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1024-PID-0021-2401 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Caustic Tower Overhead Chilling | C | 2019-08-16 | IDD1 | OL1-2G43-2401 | PE | 2019-08-20 | 036909C-JVD-TRN-02459 | 036909C-JVD-TRN-02459 | IFR | 2019-09-04 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02459 |  | 2019-08-21 | 2
036909C-1023-PID-0021-2390 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Caustic - Vent Gas Battery Limit | A | 2019-08-16 | IDD1 | OL1-2G43-2390 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2329 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Wet Air Oxidation Package | C | 2019-08-16 | IDD1 | OL1-2G43-2329 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2328 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Stripper Ovhd Drum | C | 2019-08-16 | IDD1 | OL1-2G43-2328 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2326 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Stripper | C | 2019-08-16 | IDD1 | OL1-2G43-2326 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2325 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Stripper Feed Heater | C | 2019-08-16 | IDD1 | OL1-2G43-2325 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2320 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Storage | C | 2019-08-16 | IDD1 | OL1-2G43-2320 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2319 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Skim Oil Drum | C | 2019-08-16 | IDD1 | OL1-2G43-2319 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2318 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Drain Sump | C | 2019-08-16 | IDD1 | OL1-2G43-2318 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2317 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Yellow Oil Drum | C | 2019-08-16 | IDD1 | OL1-2G43-2317 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2316 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Caustic Drain Sump | C | 2019-08-16 | IDD1 | OL1-2G43-2316 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2315 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Caustic Drain Collection | C | 2019-08-16 | IDD1 | OL1-2G43-2315 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2314 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Drain Collection | C | 2019-08-16 | IDD1 | OL1-2G43-2314 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2313 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Degassing | C | 2019-08-16 | IDD1 | OL1-2G43-2313 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2311 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Deoiling | C | 2019-08-16 | IDD1 | OL1-2G43-2311 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2310 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Fresh Caustic Supply | C | 2019-08-16 | IDD1 | OL1-2G43-2310 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2305 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Strong Caustic Circulation | C | 2019-08-16 | IDD1 | OL1-2G43-2305 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2303 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Weak-Intermediate Caustic Circulation | C | 2019-08-16 | IDD1 | OL1-2G43-2303 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1023-PID-0021-2301 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Caustic Tower | C | 2019-08-16 | IDD1 | OL1-2G43-2301 | PE | 2019-08-23 | 036909C-JVD-TRN-02477 | 036909C-JVD-TRN-02477 | IFR | 2019-09-03 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02477 |  | 2019-08-26 | 2
036909C-1022-PID-0021-2290 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Propylene Off Gas-C2 Off-C3-C4 Vapor Battery Limit | A | 2019-08-16 | IDD1 | OL1-2G43-2290 | PE | 2019-08-23 | 036909C-JVD-TRN-02478 | 036909C-JVD-TRN-02478 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02478 |  | 2019-08-26 | 2
036909C-1022-PID-0021-2224 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Wash Oil Injection | C | 2019-08-16 | IDD1 | OL1-2G43-2224 | PE | 2019-08-23 | 036909C-JVD-TRN-02478 | 036909C-JVD-TRN-02478 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02478 |  | 2019-08-26 | 2
036909C-1022-PID-0021-2222 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Wash Water Injection | C | 2019-08-16 | IDD1 | OL1-2G43-2222 | PE | 2019-08-23 | 036909C-JVD-TRN-02478 | 036909C-JVD-TRN-02478 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02478 |  | 2019-08-26 | 2
036909C-1022-PID-0021-2220 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Wash Water Cooling | C | 2019-08-16 | IDD1 | OL1-2G43-2220 | PE | 2019-08-23 | 036909C-JVD-TRN-02478 | 036909C-JVD-TRN-02478 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02478 |  | 2019-08-26 | 2
036909C-1022-PID-0021-2217 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 4th Stage Discharge Drum | C | 2019-08-16 | IDD1 | OL1-2G43-2217 | PE | 2019-08-23 | 036909C-JVD-TRN-02478 | 036909C-JVD-TRN-02478 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02478 |  | 2019-08-26 | 2
036909C-1022-PID-0021-2215 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 4th Stage Aftercooling | C | 2019-08-16 | IDD1 | OL1-2G43-2215 | PE | 2019-08-23 | 036909C-JVD-TRN-02478 | 036909C-JVD-TRN-02478 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02478 |  | 2019-08-26 | 2
036909C-1022-PID-0021-2214 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 4th Stage Suction Drum | C | 2019-08-16 | IDD1 | OL1-2G43-2214 | PE | 2019-08-23 | 036909C-JVD-TRN-02478 | 036909C-JVD-TRN-02478 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02478 |  | 2019-08-26 | 2
036909C-1022-PID-0021-2212 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 3rd Stage Aftercooling | C | 2019-08-16 | IDD1 | OL1-2G43-2212 | PE | 2019-08-23 | 036909C-JVD-TRN-02478 | 036909C-JVD-TRN-02478 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02478 |  | 2019-08-26 | 2
036909C-1022-PID-0021-2211 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 3rd And 4th Stages | C | 2019-08-16 | IDD1 | OL1-2G43-2211 | PE | 2019-08-23 | 036909C-JVD-TRN-02478 | 036909C-JVD-TRN-02478 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02478 |  | 2019-08-26 | 2
036909C-1022-PID-0021-2210 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 3rd Stage Suction Drum | C | 2019-08-16 | IDD1 | OL1-2G43-2210 | PE | 2019-08-23 | 036909C-JVD-TRN-02478 | 036909C-JVD-TRN-02478 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02478 |  | 2019-08-26 | 2
036909C-1022-PID-0021-2208 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 2nd Stage Aftercooling | C | 2019-08-16 | IDD1 | OL1-2G43-2208 | PE | 2019-08-23 | 036909C-JVD-TRN-02478 | 036909C-JVD-TRN-02478 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02478 |  | 2019-08-26 | 2
036909C-1000-PP-014 | Requirements For Vendor Documentation And Exchange Of Correspondence | 1 | 2019-05-30 | IMP | OL1-2W92-0005 | PC | 2019-06-03 | 036909C-JVD-TRN-01790 | 036909C-JVD-TRN-01790 | IFR | 2019-06-18 | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-PC-01790 |  | 2019-06-10 | 2
036909C-1000-JSS-1621-0001 | Power Control And Fiber Optic Cables | 0 | 2018-12-03 | IMP | OL1-2R05-0018 | EE | 2018-12-05 | 036909C-JVD-TRN-00425 | 036909C-JVD-TRN-00425 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00425 |  | 2018-12-05 | 3
036909C-1000-JSD-1600-0002 | Electrical System Design | 0 | 2018-12-03 | IMP | OL1-2R05-0002 | EE | 2018-12-05 | 036909C-JVD-TRN-00424 | 036909C-JVD-TRN-00424, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00424 |  | 2018-12-05 | 3
036909C-1000-JSD-1600-0001 | General Electrical Design | 0 | 2018-12-03 | IMP | OL1-2R05-0001 | EE | 2018-12-05 | 036909C-JVD-TRN-00424 | 036909C-JVD-TRN-00424, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00424 |  | 2018-12-05 | 3
036909C-1000-JSS-6300-04 | Job Specification For Supply Positive Alloy Material Identification Of Equipment And Piping | 0 | 2019-02-21 | IMP | OL1-2R03-0003 | ME | 2019-02-25 | 036909C-JVD-TRN-00921 | 036909C-JVD-TRN-00921 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00921 |  | 2019-02-26 | 2
036909C-1000-JSD-1580-0002 | Progammable Logic Controller | 0 | 2019-03-11 | IMP | OL1-2R06-1301 | IE | 2019-03-19 | 036909C-JVD-TRN-01094 | 036909C-JVD-TRN-01094 | IFR | 2019-04-03 | 2019-04-05 | R1-No comments | TPSK-LSPA1-T-IE-01094 |  | 2019-03-20 | 2
036909C-1000-JSD-1572-0005 | Grounding System for Instrument | 0 | 2018-12-14 | IMP | OL1-2R06-0012 | IE | 2018-12-17 | 036909C-JVD-TRN-00508 | 036909C-JVD-TRN-00508, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00508 |  | 2018-12-17 | 3
036909C-1000-JSD-1600-0010 | Earthing And Lightning Protection | 0 | 2018-09-20 | IMP | OL1-2R05-0015 | EE | 2018-11-05 | 036909C-JVD-TRN-00258 | 036909C-JVD-TRN-00258, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00258 |  | 2018-11-05 | 3
036909C-1000-PP-106 | Tagging Procedure | 0 | 2018-10-29 | IMP | OL1-2R07-0001 | ME | 2018-11-07 | 036909C-JVD-TRN-00279 | 036909C-JVD-TRN-00279 | IFI |  | 2019-04-01 | R1-No comments | TPSK-LSPA1-T-ME-00279 |  | 2018-11-07 | 2
036909C-1000-JSD-1600-0004 | LIGHTING SYSTEM | 0 | 2018-09-20 | IMP | OL1-2R05-0014 | EE | 2018-11-05 | 036909C-JVD-TRN-00258 | 036909C-JVD-TRN-00258, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00258 |  | 2018-11-05 | 3
036909C-1000-PP-607 | Prescriptions For Preparation Of Documentation Package For Transportation | 0 | 2018-10-05 | IMP | OL1-2C92-0007 | PL | 2018-10-08 | 036909C-JVD-TRN-00140 | 036909C-JVD-TRN-00140 | IFR | 2018-10-22 | 2018-10-30 | Transmitted | TPSK-LSPA1-T-PL-00140 |  | 2018-10-08 | 2
036909C-1000-JSS-1682-0001 | Electrical Heat Tracing | 0 | 2018-09-20 | IMP | OL1-2R05-0037 | EE | 2018-09-24 | 036909C-JVD-TRN-00079 | 036909C-JVD-TRN-00079 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00079 |  | 2018-09-25 | 3
036909C-1000-JSD-1501-0003 | Instrument Inspection And Test Plan | 0 | 2018-09-28 | IMP | OL1-2R06-0023 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | 2018-10-04 | 3
036909C-1000-JSS-1585-0001 | Job Supply Specification For Analyzer Systems and Analyzer Houses | A | 2019-04-08 | IFR | OL1-2I92-0050 | IE | 2019-04-12 | 036909C-JVD-TRN-01332 | 036909C-JVD-TRN-01332 | IFA | 2019-04-29 | 2019-05-09 | R1-No comments | TPSK-LSPA1-T-CV-01332 |  | 2019-04-15 | 2
036909C-1000-JSD-1560-0001 | Process On-Line Analyzer And Analyzer Housing | 0 | 2019-03-08 | IMP | OL1-2R06-2003 | IE | 2019-03-13 | 036909C-JVD-TRN-01044 | 036909C-JVD-TRN-01044 | IFR | 2019-03-28 | 2019-05-09 | R1-No comments | TPSK-LSPA1-T-IE-01044 |  | 2019-03-14 | 2
036909C-1000-JSS-1300-01 | General Supply Specification For Piping Material | 1 | 2019-04-16 | IFE | OL1-2R04-0006 | MP | 2019-04-24 | 036909C-JVD-TRN-01463 | 036909C-JVD-TRN-01463 | IFR | 2019-05-09 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-MP-01463 |  | 2019-04-25 | 2
036909C-1000-JSD-1572-0003 | Instrument Air Supply | 0 | 2019-02-28 | IMP | OL1-2R06-0011 | IE | 2019-03-08 | 036909C-JVD-TRN-01014 | 036909C-JVD-TRN-01014, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-03-25 | 2019-04-05 | R1-No comments | TPSK-LSPA1-T-IE-01014 |  | 2019-03-11 | 2
036909C-1000-JSS-1310-0008 | Job Supply Specification For Ball Valves | 0 | 2019-04-16 | IMP | OL1-2R04-0010 | MP | 2019-04-24 | 036909C-JVD-TRN-01463 | 036909C-JVD-TRN-01463 | IFR | 2019-05-09 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-MP-01463 |  | 2019-04-25 | 2
036909C-1000-JSS-1320-01 | Job Supply Specification For Pipes | 0 | 2019-04-16 | IMP | OL1-2R04-0011 | MP | 2019-04-24 | 036909C-JVD-TRN-01463 | 036909C-JVD-TRN-01463 | IFR | 2019-05-09 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-MP-01463 |  | 2019-04-25 | 2
036909C-1000-JSD-1300-0001 | Piping Class Summary And Piping Classes - Includes ex doc. OL1-2P92-0003 as attachment | 0 | 2019-04-01 | IMP | OL1-2R04-0001 | MP | 2019-04-05 | 036909C-JVD-TRN-01262 | 036909C-JVD-TRN-01262 | IFR | 2019-04-22 |  | Transmitted | 1262-TPSK-LSPA1-T-MP-01262 |  | 2019-04-08 | 2
036909C-1000-PP-016 | Prescriptions For Preparation Of Vendor Data Book | 0 | 2019-01-24 | IMP | OL1-2W92-0010 | PC | 2019-02-08 | 036909C-JVD-TRN-00824 | 036909C-JVD-TRN-00824 | IFR | 2019-02-25 | 2019-05-30 | R2-Comments as noted | TPSK-LSPA1-T-PC-00824 |  | 2019-02-07 | 2
036909C-1000-JSS-1350-01 | Job Supply Specification For Flanges | 0 | 2019-04-16 | IMP | OL1-2R04-0015 | MP | 2019-04-24 | 036909C-JVD-TRN-01463 | 036909C-JVD-TRN-01463 | IFR | 2019-05-09 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-MP-01463 |  | 2019-04-25 | 2
036909C-1000-JSS-6300-03 | Job Specification For Materials In Sour Service | 0 | 2019-02-21 | IMP | OL1-2R03-0002 | ME | 2019-02-25 | 036909C-JVD-TRN-00921 | 036909C-JVD-TRN-00921 | IFR | 2019-03-12 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00921 |  | 2019-02-26 | 2
036909C-1000-PP-908 | Instructions To Supplier For Filling-Up Of Spare Parts And Interchangeability Record (SPIR Form) | 0 | 2019-02-28 | IMP | OL1-2O92-0001 | PE | 2019-03-01 | 036909C-JVD-TRN-00957 | 036909C-JVD-TRN-00957 | IFR | 2019-03-18 |  | Transmitted | TPSK-LSPA1-T-PE--00957 |  | 2019-03-04 | 2
036909C-1000-JSD-1540-0001 | Instrument General Design | 1 | 2019-05-10 | IMP | OL1-2R06-0001 | IE | 2019-05-24 | 036909C-JVD-TRN-01741 | 036909C-JVD-TRN-01741 | IFR | 2019-06-10 | 2019-06-17 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-IE-01741 |  | 2019-05-27 | 2
036909C-1000-JSD-1501-0001 | Instrument Numbering | 0 | 2019-04-04 | IMP | OL1-2R06-0022 | IE | 2019-04-11 | 036909C-JVD-TRN-01320 | 036909C-JVD-TRN-01320 | IFR | 2019-04-26 | 2019-05-09 | R1-No comments | TPSK-LSPA1-T-IE-01320 |  | 2019-04-12 | 2
036909C-1000-JSD-2300-01 | Job Design Specification For Painting | 0 | 2019-05-16 | IMP | OL1-2R04-0005 | MP | 2019-05-17 | 036909C-JVD-TRN-01690 | 036909C-JVD-TRN-01690 | IFR | 2019-06-03 | 2019-06-14 | R2-Comments as noted | TPSK-LSPA1-T-MP-01690 |  | 2019-05-21 | 2
036909C-1022-PID-0021-2206 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 2nd Stage Suction Drum | C | 2019-08-16 | IDD1 | OL1-2G43-2206 | PE | 2019-08-23 | 036909C-JVD-TRN-02478 | 036909C-JVD-TRN-02478 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02478 |  | 2019-08-26 | 2
036909C-1022-PID-0021-2204 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 1st Stage Aftercooling | C | 2019-08-16 | IDD1 | OL1-2G43-2204 | PE | 2019-08-23 | 036909C-JVD-TRN-02478 | 036909C-JVD-TRN-02478 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02478 |  | 2019-08-26 | 2
036909C-1022-PID-0021-2203 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 1st And 2nd Stages | C | 2019-08-16 | IDD1 | OL1-2G43-2203 | PE | 2019-08-23 | 036909C-JVD-TRN-02478 | 036909C-JVD-TRN-02478 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02478 |  | 2019-08-26 | 2
036909C-1022-PID-0021-2201 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 1st Stage Suction Drum | C | 2019-08-16 | IDD1 | OL1-2G43-2201 | PE | 2019-08-23 | 036909C-JVD-TRN-02478 | 036909C-JVD-TRN-02478 | IFR | 2019-09-09 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02478 |  | 2019-08-26 | 2
036909C-1021-PID-0021-2138 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Blowdown Cooling | C | 2019-08-16 | IDD1 | OL1-2G43-2138 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2137 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Superheating | C | 2019-08-16 | IDD1 | OL1-2G43-2137 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2134 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Generator Reboilers - Sheet 2 | C | 2019-08-16 | IDD1 | OL1-2G43-2134 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1000-NM-617 | Monthly Complete Expediting Report | 2 | 2019-05-14 | IFI | OL1-2C95-0002 | PL | 2019-05-16 | 036909C-JVD-TRN-01675 | 036909C-JVD-TRN-01675 | IFI |  | 2019-05-29 | A1-Approved without comments | TPSK-LSPA1-T-PL-01675 |  | 2019-05-17 | 2
036909C-1021-PID-0021-2132 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Generator Reboilers - Sheet 1 | C | 2019-08-16 | IDD1 | OL1-2G43-2132 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2131 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Generator | C | 2019-08-16 | IDD1 | OL1-2G43-2131 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2130 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Generator Feed Heating | C | 2019-08-16 | IDD1 | OL1-2G43-2130 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2127 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Generator Feed Pumps | C | 2019-08-16 | IDD1 | OL1-2G43-2127 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2126 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Process Water Stripper Reboiler | C | 2019-08-16 | IDD1 | OL1-2G43-2126 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2125 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Process Water Stripper | C | 2019-08-16 | IDD1 | OL1-2G43-2125 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2123 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Process Water Stripper Feed | C | 2019-08-16 | IDD1 | OL1-2G43-2123 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2122 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Distillate Stripper Reboiler | C | 2019-08-16 | IDD1 | OL1-2G43-2122 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2120 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Distillate Stripper | C | 2019-08-16 | IDD1 | OL1-2G43-2120 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2117 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Water Drain Drum | C | 2019-08-16 | IDD1 | OL1-2G43-2117 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2115 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Water Drain Collection | C | 2019-08-16 | IDD1 | OL1-2G43-2115 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2110 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Water Cooling | C | 2019-08-16 | IDD1 | OL1-2G43-2110 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2108 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Water Distribution | C | 2019-08-16 | IDD1 | OL1-2G43-2108 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2106 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Water Pumps | C | 2019-08-16 | IDD1 | OL1-2G43-2106 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2104 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Oil Fractionator Reflux | C | 2019-08-16 | IDD1 | OL1-2G43-2104 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2102 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Water Tower Overhead | C | 2019-08-16 | IDD1 | OL1-2G43-2102 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1021-PID-0021-2101 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Water Tower | C | 2019-08-16 | IDD1 | OL1-2G43-2101 | PE | 2019-08-22 | 036909C-JVD-TRN-02473 | 036909C-JVD-TRN-02473 | IFR | 2019-09-06 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-PE-02473 |  | 2019-08-22 | 2
036909C-1000-JSD-1300-0002 | Job Specification For Detail Design Piping | 0 | 2019-01-25 | IMP | OL1-2R04-0002 | MP | 2019-01-28 | 036909C-JVD-TRN-00736 | 036909C-JVD-TRN-00736, ROC-TPSK-CECO-T-00004 | IFR | 2019-02-12 | 2019-03-01 | R2-Comments as noted | TPSK-LSPA1-T-MP-00736 |  | 2019-01-28 | 2
036909C-1059-SP-2510-5950 | Mechanical Equipment Data Sheet - Sodium Hypochlorite Tank | A | 2019-02-07 | IFQ | OL1-2M03-5950 | ME | 2019-02-11 | 036909C-JVD-TRN-00839 | 036909C-JVD-TRN-00839, ROC-TPSK-CECO-T-00016 | IFR | 2019-02-25 | 2019-02-28 | R1-No comments | TPSK-LSPA1-T-ME-00839 |  | 2019-02-11 | 2
036909C-1000-STD-1380-0001 | Piping Design Standard Drawings - For next revision see document OL1-2R04-0002 - included as attachment | 0 | 2018-11-12 | CAN | OL1-2R04-0002 | MP | 2018-11-16 | 036909C-JVD-TRN-00325 | 036909C-JVD-TRN-00325 | IFR | 2018-12-03 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00325 | For next revision see document OL1-2R04-0002 - inclueded as attachment | 2018-11-16 | 2
036909C-1000-DW-1802-0001 | General Notes For Steel Structures | 2 | 2019-06-24 | IFC | OL1-2K92-0004 | CV | 2019-07-02 | 036909C-JVD-TRN-02054 | 036909C-JVD-TRN-02054 | IFA | 2019-07-17 | 2019-08-29 | A1-Approved without comments | TPSK-LSPA1-T-CV-02054 |  | 2019-07-03 | 1
036909C-1000-PP-616 | Parking Marking And Shipping Instructions | 0 | 2018-10-05 | IMP | OL1-2C92-0016 | PL | 2018-10-08 | 036909C-JVD-TRN-00140 | 036909C-JVD-TRN-00140 | IFR | 2018-10-22 | 2018-10-30 | Transmitted | TPSK-LSPA1-T-PL-00140 |  | 2018-10-08 | 2
036909C-1000-JSD-0400-01 | Job Specification For Design Of Pressure And Atmospheric Static Equipment | 1 | 2019-02-18 | IMP | OL1-2R03-0050 | ME | 2019-02-19 | 036909C-JVD-TRN-00888 | 036909C-JVD-TRN-00888, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2019-03-06 | 2019-03-15 | R1-No comments | TPSK-LSPA1-T-ME-00888 |  | 2019-02-19 | 2
036909C-1000-JSD-2300-01 | Job Design Specification For Painting | 1 | 2019-07-24 | IMP | OL1-2R04-0005 | MP | 2019-08-01 | 036909C-JVD-TRN-02314 | 036909C-JVD-TRN-02314 | IFR | 2019-08-16 | 2019-08-13 | R1-No comments | TPSK-LSPA1-T-MP-02314 |  | 2019-08-05 | 2
036909C-1000-JSS-1820-01 | Job Specification For Supply Of Equipment Ladders And Platforms | 0 | 2018-09-20 | IFR | OL1-2R03-0053 | ME | 2018-09-24 | 036909C-JVD-TRN-00081 | 036909C-JVD-TRN-00081 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00081 |  | 2018-09-25 | 3
036909C-1000-PP-923 | Equipment Preservation | 0 | 2018-10-09 | IMP | OL1-2R07-0010 | ME | 2018-10-09 | 036909C-JVD-TRN-00149 | 036909C-JVD-TRN-00149 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00149 |  | 2018-10-10 | 3
036909C-105F-NM-1350-0031 | Loads On Sleeper Way 10-SLW-5F01 | A | 2019-07-08 | IBD | OL1-2P05-0192 | MP | 2019-07-09 | 036909C-JVD-TRN-02103 | 036909C-JVD-TRN-02103 | IFR | 2019-07-23 | 2019-09-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-02103 |  | 2019-07-10 | 2
036909C-1039-PDS-0800-3906 | Process Equipment Data Sheet - 10-D-3906 - BDU Anti Foam Agent Drum | C | 2019-08-12 | IFD | OL1-2G30-3906 | PE | 2019-08-13 | 036909C-JVD-TRN-02427 | 036909C-JVD-TRN-02427 | IFR | 2019-08-28 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-02427 |  | 2019-08-15 | 2
036909C-1030-PDS-0600-3062 | Process Equipment Datasheet - 10-E-3062 - C4 Acetylene Condenser | C | 2019-08-16 | IFD | OL1-2G30-3062 | PE | 2019-08-20 | 036909C-JVD-TRN-02461 | 036909C-JVD-TRN-02461 | IFR | 2019-09-04 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-02461 |  | 2019-08-21 | 2
036909C-1039-CN-0014-3943 | PSV-3943 Sizing Calculation | B | 2019-08-06 | IFR | OL1-2G23-3643 | PE | 2019-08-12 | 036909C-JVD-TRN-02416 | 036909C-JVD-TRN-02416 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-02416 |  | 2019-08-14 | 2
036909C-1030-CN-0014-3079 | PSV-3079 Sizing Calculation | A | 2019-08-06 | IFR | OL1-2G23-3079 | PE | 2019-08-12 | 036909C-JVD-TRN-02416 | 036909C-JVD-TRN-02416 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-02416 |  | 2019-08-14 | 2
036909C-1030-CN-0014-3009 | PSV-3009 Sizing Calculation | A | 2019-08-06 | IFR | OL1-2G23-3009 | PE | 2019-08-12 | 036909C-JVD-TRN-02416 | 036909C-JVD-TRN-02416 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-02416 |  | 2019-08-14 | 2
036909C-1029-SP-1513-2902 | Instrument Interlock Descriptions Area 29 - Ethylene Auxiliaries | B | 2019-08-06 | IBD | OL1-2G50-2902 | PE | 2019-08-06 | 036909C-JVD-TRN-02364 | 036909C-JVD-TRN-02364 | IFR | 2019-08-21 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-02364 |  | 2019-08-07 | 2
036909C-1028-SP-1513-2802 | Instrument Interlock Descriptions Area 28 - Refrigeration System | B | 2019-08-08 | IBD | OL1-2G50-2802 | PE | 2019-08-08 | 036909C-JVD-TRN-02397 | 036909C-JVD-TRN-02397 | IFR | 2019-08-23 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-02397 |  | 2019-08-09 | 2
036909C-1028-DW-1514-2801 | Cause And Effect Diagram Area 28 - Refrigeration System | B | 2019-08-07 | IBD | OL1-2G50-2801 | PE | 2019-08-07 | 036909C-JVD-TRN-02374 | 036909C-JVD-TRN-02374 | IFR | 2019-08-22 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-02374 |  | 2019-08-08 | 2
036909C-1056-DI-0007-5601 | Area Basis of Design - 56 Waste Water Treatment System | D | 2019-08-20 | IFD | OL1-2G05-5601 | PE | 2019-08-21 | 036909C-JVD-TRN-02466 | 036909C-JVD-TRN-02466 | IFR | 2019-09-05 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-02466 |  | 2019-08-22 | 2
036909C-1031-PDS-1390-3119 | SP Item Datasheet - BDU LP Steam Desuperheater - SP-31019 | A | 2019-08-11 | IFR | OL1-2P03-3119 | MP | 2019-08-12 | 036909C-JVD-TRN-02420 | 036909C-JVD-TRN-02420 | IFR | 2019-08-27 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-MP-02420 |  | 2019-08-14 | 2
036909C-1031-PDS-1390-3118 | SP Item Datasheet - BDU MP Steam Desuperheater - SP-31018 | A | 2019-08-11 | IFR | OL1-2P03-3118 | MP | 2019-08-12 | 036909C-JVD-TRN-02420 | 036909C-JVD-TRN-02420 | IFR | 2019-08-27 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-MP-02420 |  | 2019-08-14 | 2
036909C-1055-PDS-1390-5524 | Piping Specialty Item - Datasheet - Liquid Drain Trap - Vent Gas Header in WWT Unit - STT-55005 | A | 2019-08-12 | IFR | OL1-2P03-5524 | MP | 2019-08-12 | 036909C-JVD-TRN-02421 | 036909C-JVD-TRN-02421 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02421 |  | 2019-08-14 | 2
036909C-1054-PDS-1390-5401 | Piping Specialty Item - Datasheet - Liquid Drain Trap - D-5400 Drain to OWD - STT-54001 | A | 2019-08-12 | IFR | OL1-2P03-5401 | MP | 2019-08-12 | 036909C-JVD-TRN-02421 | 036909C-JVD-TRN-02421 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02421 |  | 2019-08-14 | 2
036909C-1031-PDS-1390-3122 | Piping Specialty Item - Datasheet - Y-Type Filter - E-3150 LP Condensate Outlet - SRY-31006 | A | 2019-08-09 | IFR | OL1-2P03-3122 | MP | 2019-08-12 | 036909C-JVD-TRN-02415 | 036909C-JVD-TRN-02415 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02415 |  | 2019-08-14 | 2
036909C-1031-PDS-1390-3120 | Piping Specialty Item - Datasheet - Y-Type Filter - HP BFW to Desuperheaters - 10-SRY-31005 | A | 2019-08-09 | IFR | OL1-2P03-3120 | MP | 2019-08-12 | 036909C-JVD-TRN-02415 | 036909C-JVD-TRN-02415 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02415 |  | 2019-08-14 | 2
036909C-1031-PDS-1390-3113 | Piping Specialty Item - Datasheet - Y-Type Filter - LP Condensate from D-3100 Jacket LP Steam Inlet Line - SRY-31004 | A | 2019-08-09 | IFR | OL1-2P03-3113 | MP | 2019-08-12 | 036909C-JVD-TRN-02415 | 036909C-JVD-TRN-02415 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02415 |  | 2019-08-14 | 2
036909C-1031-PDS-1390-3112 | Piping Specialty Item - Datasheet - Y-Type Filter - D-3100 Jacket LP Condensate Outlet - SRY-31003 | A | 2019-08-09 | IFR | OL1-2P03-3112 | MP | 2019-08-12 | 036909C-JVD-TRN-02415 | 036909C-JVD-TRN-02415 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02415 |  | 2019-08-14 | 2
036909C-1031-PDS-1390-3110 | Piping Specialty Item - Datasheet - Y-Type Filter - D-3190 LP Condensate Outlet - SRY-31001 | A | 2019-08-09 | IFR | OL1-2P03-3110 | MP | 2019-08-12 | 036909C-JVD-TRN-02415 | 036909C-JVD-TRN-02415 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02415 |  | 2019-08-14 | 2
036909C-1031-PDS-1390-3109 | Piping Specialty Item - Datasheet - Y-Type Filter - D-3190 LP Condensate Outlet - SRY-31002 | A | 2019-08-09 | IFR | OL1-2P03-3109 | MP | 2019-08-12 | 036909C-JVD-TRN-02415 | 036909C-JVD-TRN-02415 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02415 |  | 2019-08-14 | 2
036909C-1030-PDS-1390-3030 | Piping Specialty Item - Datasheet - Y-Type Filter - E-3055 A-B MP Condensate Outlet - SRY-30003 | A | 2019-08-09 | IFR | OL1-2P03-3030 | MP | 2019-08-12 | 036909C-JVD-TRN-02415 | 036909C-JVD-TRN-02415 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02415 |  | 2019-08-14 | 2
036909C-1030-PDS-1390-3026 | Piping Specialty Item - Datasheet - Y-Type Filter - E-3080 Product Inhiditor Inlet - SRY-39005 | A | 2019-08-09 | IFR | OL1-2P03-3026 | MP | 2019-08-12 | 036909C-JVD-TRN-02415 | 036909C-JVD-TRN-02415 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02415 |  | 2019-08-14 | 2
036909C-1031-SP-0810-3190 | Mechanical Equipment Data Sheet for NMP Slop Drum | B | 2019-08-13 | IFQ | OL1-2M03-3190 | ME | 2019-08-14 | 036909C-JVD-TRN-02437 | 036909C-JVD-TRN-02437 | IFR | 2019-08-29 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-ME-02437 |  | 2019-08-15 | 2
036909C-1031-SP-0810-3161 | Mechanical Equipment Data Sheet for BDU Condensate Drum | B | 2019-08-13 | IFQ | OL1-2M03-3161 | ME | 2019-08-14 | 036909C-JVD-TRN-02437 | 036909C-JVD-TRN-02437 | IFR | 2019-08-29 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-ME-02437 |  | 2019-08-15 | 2
036909C-1031-SP-0810-3100 | Mechanical Equipment Data Sheet for Solvent Regen Drum | B | 2019-08-13 | IFQ | OL1-2M03-3100 | ME | 2019-08-14 | 036909C-JVD-TRN-02437 | 036909C-JVD-TRN-02437 | IFR | 2019-08-29 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-ME-02437 |  | 2019-08-15 | 2
036909C-1030-SP-0810-3082 | Mechanical Equipment Data Sheet for Butadiene Tower Reflux Drum | B | 2019-08-08 | IFQ | OL1-2M03-3082 | ME | 2019-08-14 | 036909C-JVD-TRN-02437 | 036909C-JVD-TRN-02437 | IFR | 2019-08-29 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-ME-02437 |  | 2019-08-15 | 2
036909C-1030-SP-0810-3065 | Mechanical Equipment Data Sheet for C4 Acetylene Accumulator Drum | B | 2019-08-08 | Issue for Inquiry | OL1-2M03-3065 | ME | 2019-08-14 | 036909C-JVD-TRN-02437 | 036909C-JVD-TRN-02437 | IFR | 2019-08-29 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-ME-02437 |  | 2019-08-15 | 2
036909C-1030-SP-0810-3064 | Mechanical Equipment Data Sheet for BDU HC-Water Separator Drum | B | 2019-08-13 | Issue for Inquiry | OL1-2M03-3064 | ME | 2019-08-14 | 036909C-JVD-TRN-02437 | 036909C-JVD-TRN-02437 | IFR | 2019-08-29 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-ME-02437 |  | 2019-08-15 | 2
036909C-1030-SP-0810-3032 | Mechanical Equipment Data Sheet for After Washer Reflux Drum | B | 2019-08-08 | IFQ | OL1-2M03-3032 | ME | 2019-08-14 | 036909C-JVD-TRN-02437 | 036909C-JVD-TRN-02437 | IFR | 2019-08-29 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-ME-02437 |  | 2019-08-15 | 2
036909C-1030-SP-0810-3022 | Mechanical Equipment Data Sheet for Main Washer Reflux Drum | B | 2019-08-08 | IFQ | OL1-2M03-3022 | ME | 2019-08-14 | 036909C-JVD-TRN-02437 | 036909C-JVD-TRN-02437 | IFR | 2019-08-29 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-ME-02437 |  | 2019-08-15 | 2
036909C-1030-SP-0810-3002 | Mechanical Equipment Data Sheet for Predistillation Feed Drum | B | 2019-08-08 | IFQ | OL1-2M03-3002 | ME | 2019-08-14 | 036909C-JVD-TRN-02437 | 036909C-JVD-TRN-02437 | IFR | 2019-08-29 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-ME-02437 |  | 2019-08-15 | 2
036909C-1012-PDS-1390-1254 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-12002-16002 | B | 2019-07-30 | IFD | OL1-2P03-1254 | MP | 2019-08-02 | 036909C-JVD-TRN-02324 | 036909C-JVD-TRN-02324 | IFR | 2019-08-17 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02324 |  | 2019-08-02 | 2
036909C-1012-PDS-1390-1253 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-12001-16001 | B | 2019-07-30 | IFD | OL1-2P03-1253 | MP | 2019-08-02 | 036909C-JVD-TRN-02324 | 036909C-JVD-TRN-02324 | IFR | 2019-08-17 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02324 |  | 2019-08-05 | 2
036909C-1012-PDS-1390-1216 | Piping Specialty Item – Data Sheet Y-Type Filter – Purge Steam SRY-12003-16003 | A | 2019-08-08 | IFR | OL1-2P03-1216 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1012-PDS-1390-1215 | Piping Specialty Item – Data Sheet Y-Type Filter – Purge Steam SRY-12002-16002 | A | 2019-08-08 | IFR | OL1-2P03-1215 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1011-PDS-1390-1116 | Piping Specialty Item – Data Sheet Y-Type Filter – Purge Steam SRY-11003 | A | 2019-08-08 | IFR | OL1-2P03-1116 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-19 | R2-Comments as noted | - |  | 2019-08-09 | 2
036909C-1011-PDS-1390-1115 | Piping Specialty Item – Data Sheet Y-Type Filter – Purge SRY-11002 | A | 2019-08-08 | IFR | OL1-2P03-1115 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-19 | R2-Comments as noted | - |  | 2019-08-09 | 2
036909C-1019-PDS-1390-1903 | Piping Specialty Item – Data Sheet T-Type Filter – P-1910/P-1912 SRT-19001 | A | 2019-08-08 | IFR | OL1-2P03-1903 | MP | 2019-08-08 | 036909C-JVD-TRN-02398 | 036909C-JVD-TRN-02398 | IFR | 2019-08-23 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-MP-02398 |  | 2019-08-09 | 2
036909C-1030-PDS-1390-3024 | Piping Specialty Item - Datasheet - Y-Type Filter - E-3030 Product Inhibitor Inlet - SRY-30002 | A | 2019-08-09 | IFR | OL1-2P03-3024 | MP | 2019-08-12 | 036909C-JVD-TRN-02415 | 036909C-JVD-TRN-02415 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02415 |  | 2019-08-14 | 2
036909C-1030-PDS-1390-3020 | Piping Specialty Item - Datasheet - Y-Type Filter - P-3016 A-B Discharge - SRY-30001 | A | 2019-08-09 | IFR | OL1-2P03-3020 | MP | 2019-08-12 | 036909C-JVD-TRN-02415 | 036909C-JVD-TRN-02415 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02415 |  | 2019-08-14 | 2
036909C-1025-PDS-1390-2548 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - TX-2550 Discharge - 10-SP-25048 | A | 2019-06-21 | IFR | OL1-2P03-2548 | MP | 2019-08-12 | 036909C-JVD-TRN-02418 | 036909C-JVD-TRN-02418 | IFR | 2019-08-27 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-MP-02418 |  | 2019-08-14 | 2
036909C-1025-PDS-1390-2547 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2550 Discharge - 10-SP-25047 | A | 2019-06-21 | IFR | OL1-2P03-2547 | MP | 2019-08-12 | 036909C-JVD-TRN-02418 | 036909C-JVD-TRN-02418 | IFR | 2019-08-27 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-MP-02418 |  | 2019-08-14 | 2
036909C-1021-PDS-1390-2122 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-2146 A-B Discharge - SCV-21001 | A | 2019-08-12 | IFR | OL1-2P03-2122 | MP | 2019-08-12 | 036909C-JVD-TRN-02418 | 036909C-JVD-TRN-02418 | IFR | 2019-08-27 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-MP-02418 |  | 2019-08-14 | 2
036909C-1055-PDS-1390-5503 | Piping Specialty Item - Datasheet - Flame Arrestor - Vent Gas to Tank Farm Flare SP-55003 | A | 2019-08-19 | IFR | OL1-2P03-5503 | MP | 2019-08-19 | 036909C-JVD-TRN-02457 | 036909C-JVD-TRN-02457 | IFR | 2019-09-03 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02457 |  | 2019-08-21 | 2
036909C-1055-PDS-1390-5502 | Piping Specialty Item – Datasheet Flame Arrestor - Vent Gas to Furnace Fire-Box SP-55002 | A | 2019-08-19 | IFR | OL1-2P03-5502 | MP | 2019-08-19 | 036909C-JVD-TRN-02457 | 036909C-JVD-TRN-02457 | IFR | 2019-09-03 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02457 |  | 2019-08-21 | 2
036909C-1053-PDS-1390-5302 | Piping Specialty Item - Datasheet - Coupon Rack - CTU Cooling Tower SP-53002 | A | 2019-08-21 | IFR | OL1-2P03-5302 | MP | 2019-08-21 | 036909C-JVD-TRN-02468 | 036909C-JVD-TRN-02468 | IFR | 2019-09-05 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02468 |  | 2019-08-22 | 2
036909C-1053-PDS-1390-5301 | Piping Specialty Item - Datasheet - Coupon Rack - Olefins Cooling Tower SP-53001 | A | 2019-08-21 | IFR | OL1-2P03-5301 | MP | 2019-08-21 | 036909C-JVD-TRN-02468 | 036909C-JVD-TRN-02468 | IFR | 2019-09-05 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02468 |  | 2019-08-22 | 2
036909C-1039-PDS-1390-3910 | Piping Specialty Item - Datasheet - Flame Arrestor - TK-3900 Vent FLA-39001 | A | 2019-08-19 | IFR | OL1-2P03-3910 | MP | 2019-08-19 | 036909C-JVD-TRN-02457 | 036909C-JVD-TRN-02457 | IFR | 2019-09-03 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02457 |  | 2019-08-21 | 2
036909C-1059-PDS-1390-5901 | Piping Specialty Item - Datasheet - Carbon Canister - TK-5900 Sulfuric Acid Tank Vent SP-59001 | A | 2019-08-13 | IFR | OL1-2P03-5901 | MP | 2019-08-14 | 036909C-JVD-TRN-02438 | 036909C-JVD-TRN-02438 | IFR | 2019-08-29 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02438 |  | 2019-08-15 | 2
036909C-1056-PDS-1390-5608 | Piping Specialty Item - Datasheet - Carbon Canister - PIT-5632 Vent SP-56008 | A | 2019-08-13 | IFR | OL1-2P03-5608 | MP | 2019-08-14 | 036909C-JVD-TRN-02438 | 036909C-JVD-TRN-02438 | IFR | 2019-08-29 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02438 |  | 2019-08-15 | 2
036909C-1056-PDS-1390-5615 | Piping Specialty Item - Datasheet - Sight Glass -P-5621 Discharge STG-56001 | A | 2019-08-12 | IFR | OL1-2P03-5615 | MP | 2019-08-14 | 036909C-JVD-TRN-02438 | 036909C-JVD-TRN-02438 | IFR | 2019-08-29 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-MP-02438 |  | 2019-08-15 | 2
036909C-1030-SP-1513-3001 | Complex Loop Narratives Area 30: Butadiene Extraction Unit BDU | B | 2019-08-16 | IBD | OL1-2I71-3001 | IE | 2019-08-19 | 036909C-JVD-TRN-02451 | 036909C-JVD-TRN-02451 | IFR | 2019-09-03 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-IE-02451 |  | 2019-08-21 | 2
036909C-1030-SP-1545-3001 | Instrument Datasheets for Pressure Safety Valve - Area 30 | A | 2019-08-13 | IFR | OL1-2I20-3016 | IE | 2019-08-13 | 036909C-JVD-TRN-02429 | 036909C-JVD-TRN-02429 | IFR | 2019-08-28 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-IE-02429 |  | 2019-08-15 | 2
036909C-1011-PID-0021-1130 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Boiler Feed Water Supply-Export Steam | C | 2019-08-07 | IDD1 | OL1-2G43-1130 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-11 | R1-No comments | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1010-SP-1545-1001 | Instrument Datasheets for Pressure Safety Valve - Area 10 | A | 2019-07-18 | IFI | OL1-2I20-1016 | IE | 2019-07-24 | 036909C-JVD-TRN-02258 | 036909C-JVD-TRN-02258 | IFI |  | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-IE-02258 |  | 2019-07-25 | 3
036909C-1029-PID-0021-2930 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - CG Compressor Auxiliaries - Sheet 1 | C | 2019-08-07 | IDD1 | OL1-2G43-2930 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1011-PDS-1390-1154 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-11002 | B | 2019-07-30 | IFD | OL1-2P03-1154 | MP | 2019-08-02 | 036909C-JVD-TRN-02324 | 036909C-JVD-TRN-02324 | IFR | 2019-08-17 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02324 |  | 2019-08-05 | 2
036909C-1012-PID-0021-1230 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Boiler Feed Water Supply-Export Steam | C | 2019-08-07 | IDD1 | OL1-2G43-1230 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1011-PDS-1390-1153 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-11001 | B | 2019-07-30 | IFD | OL1-2P03-1153 | MP | 2019-08-02 | 036909C-JVD-TRN-02324 | 036909C-JVD-TRN-02324 | IFR | 2019-08-17 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-02324 |  | 2019-08-05 | 2
036909C-1010-PID-0021-1036 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Cracking Furnace Distribution Utility Sheet 2 | C | 2019-08-07 | IDD1 | OL1-2G43-1036 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1010-PID-0021-1035 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Cracking Furnace Distribution Utility Sheet 1 | C | 2019-08-07 | IDD1 | OL1-2G43-1035 | PE | 2019-08-09 | 036909C-JVD-TRN-02406 | 036909C-JVD-TRN-02406 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02406 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2934 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - CGC Lube Oil Pump Turbine Details | C | 2019-08-07 | IDD1 | OL1-2G43-2934 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2932 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - CG Compressor Auxiliaries - Sheet 2 | C | 2019-08-07 | IDD1 | OL1-2G43-2932 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2924 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - DSG Feed Pump Turbine Details | C | 2019-08-07 | IDD1 | OL1-2G43-2924 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2922 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Quench Water Pump Turbine Details | C | 2019-08-07 | IDD1 | OL1-2G43-2922 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2920 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Quench Oil Pump Turbine Details | C | 2019-08-07 | IDD1 | OL1-2G43-2920 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2915 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Wash Oil Storage | C | 2019-08-07 | IDD1 | OL1-2G43-2915 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1052-SP-1513-5202 | Instrument Interlock Descriptions Area 52 - Fuel System | B | 2019-08-02 | IBD | OL1-2G50-5202 | IE | 2019-08-05 | 036909C-JVD-TRN-02345 | 036909C-JVD-TRN-02345 | IFR | 2019-08-20 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-IE-02345 |  | 2019-08-07 | 2
036909C-1029-PID-0021-2910 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Anti-Oxidant Injection Package | A | 2019-08-07 | IDD1 | OL1-2G43-2910 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1051-SP-1513-5102 | Instrument Interlock Descriptions Area 51- BFW - Steam - Steam Condensate System | B | 2019-08-02 | IBD | OL1-2G50-5102 | IE | 2019-08-05 | 036909C-JVD-TRN-02345 | 036909C-JVD-TRN-02345 | IFR | 2019-08-20 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-IE-02345 |  | 2019-08-07 | 2
036909C-1029-PID-0021-2907 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Caustic Tower Anti Foulant Injection System | C | 2019-08-07 | IDD1 | OL1-2G43-2907 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2904 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - DSG Anti Foulant Injection Package | C | 2019-08-07 | IDD1 | OL1-2G43-2904 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2903 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Process Water Stripping Chemical Injection Pkg | C | 2019-08-07 | IDD1 | OL1-2G43-2903 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2902 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Emulsion Breaker Injection System | C | 2019-08-07 | IDD1 | OL1-2G43-2902 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1029-PID-0021-2901 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - PH Control - Corrosion Injection System | C | 2019-08-07 | IDD1 | OL1-2G43-2901 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1019-PID-0021-1915 | P&ID - Olefins Unit 10 - Furnace Auxiliaries - Decoke Air Compressor | C | 2019-08-07 | IDD1 | OL1-2G43-1915 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1019-PID-0021-1901 | P&ID - Olefins Unit 10 - Furnace Auxiliaries - DMDS Injection System | C | 2019-08-07 | IDD1 | OL1-2G43-1901 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1031-SP-1545-3101 | Instrument Datasheets for Pressure Safety Valve - Area 31 | A | 2019-08-09 | IFI | OL1-2I20-3116 | IE | 2019-08-12 | 036909C-JVD-TRN-02413 | 036909C-JVD-TRN-02413 | IFI |  | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-IE-02413 |  | 2019-08-14 | 3
036909C-1012-PID-0021-1235 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas | C | 2019-08-07 | IDD1 | OL1-2G43-1235 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1039-SP-1545-3901 | Instrument Datasheets for Pressure Safety Valve - Area 39 | A | 2019-08-09 | IFI | OL1-2I20-3916 | IE | 2019-08-12 | 036909C-JVD-TRN-02413 | 036909C-JVD-TRN-02413 | IFI |  | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-IE-02413 |  | 2019-08-14 | 3
036909C-1012-PID-0021-1226 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Furnace Effluent & Decoke MOV S | C | 2019-08-07 | IDD1 | OL1-2G43-1226 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1012-PID-0021-1212 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 6 | C | 2019-08-07 | IDD1 | OL1-2G43-1212 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1012-PID-0021-1211 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 5 | C | 2019-08-07 | IDD1 | OL1-2G43-1211 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1012-PID-0021-1210 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 4 | C | 2019-08-07 | IDD1 | OL1-2G43-1210 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1012-PID-0021-1209 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 3 | C | 2019-08-07 | IDD1 | OL1-2G43-1209 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1000-ML-231 | Recovery Process and Utilities Sections SIL Classification Report | A | 2019-07-10 | IFR | OL1-2L60-0231 | SE | 2019-08-08 | 036909C-JVD-TRN-02393 | 036909C-JVD-TRN-02393 | IFR | 2019-08-23 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-PE-02393 |  | 2019-08-09 | 2
036909C-1012-PID-0021-1208 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 2 | C | 2019-08-07 | IDD1 | OL1-2G43-1208 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1012-PID-0021-1207 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 1 | C | 2019-08-07 | IDD1 | OL1-2G43-1207 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1000-MS-1700-0001 | Technical Specification for Civil Works | A | 2019-04-19 | IFQ | OL1-2R02-0102 | CV | 2019-04-24 | 036909C-JVD-TRN-INTERNAL-00171 | 036909C-JVD-TRN-01666 | IFI |  | 2019-06-08 | R2-Comments as noted | TPSK-LSPA1-T-CV-01666 |  | 2019-05-16 | 2
036909C-1039-SP-2510-3900 | Mechanical Equipment Data Sheet For NMP Storage Tank | B | 2019-08-20 | IFQ | OL1-2M03-3900 | ME | 2019-08-21 | 036909C-JVD-TRN-02467 | 036909C-JVD-TRN-02467 | IFR | 2019-09-05 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-ME-02467 |  | 2019-08-22 | 2
036909C-1059-SP-2510-5900 | Mechanical Equipment Data Sheet For Sulfuric Acid Tank | B | 2019-08-19 | IFQ | OL1-2M03-5900 | ME | 2019-08-19 | 036909C-JVD-TRN-02455 | 036909C-JVD-TRN-02455 | IFR | 2019-09-03 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-02455 |  | 2019-08-21 | 2
036909C-1056-SP-2510-5640 | Mechanical Equipment Data Sheet For Oily Wastewater Tank | B | 2019-08-23 | IFQ | OL1-2M03-5640 | ME | 2019-08-26 | 036909C-JVD-TRN-02491 | 036909C-JVD-TRN-02491 | IFR | 2019-09-10 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-02491 |  | 2019-08-27 | 2
036909C-1012-PID-0021-1206 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Decoke Air Header Distribution Header | C | 2019-08-07 | IDD1 | OL1-2G43-1206 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1051-SP-2510-5120 | Mechanical Equipment Data Sheet For Raw Condensate Tank | B | 2019-08-22 | IFQ | OL1-2M03-5120 | ME | 2019-08-22 | 036909C-JVD-TRN-02474 | 036909C-JVD-TRN-02474 | IFR | 2019-09-06 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-02474 |  | 2019-08-22 | 2
036909C-1012-PID-0021-1205 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Dilution Steam Distribution Header | C | 2019-08-07 | IDD1 | OL1-2G43-1205 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1051-SP-2510-5110 | Mechanical Equipment Data Sheet For Condensate Tank | C | 2019-08-22 | IFQ | OL1-2M03-5110 | ME | 2019-08-22 | 036909C-JVD-TRN-02474 | 036909C-JVD-TRN-02474 | IFR | 2019-09-06 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-02474 |  | 2019-08-22 | 2
036909C-1023-SP-2510-2324 | Mechanical Equipment Data Sheet For Fresh Caustic Day Tank | B | 2019-08-09 | IFQ | OL1-2M03-2324 | ME | 2019-08-16 | 036909C-JVD-TRN-02447 | 036909C-JVD-TRN-02447 | IFR | 2019-08-31 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-02447 |  | 2019-08-19 | 2
036909C-1012-PID-0021-1202 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Liquid Feed Distribution Header | C | 2019-08-07 | IDD1 | OL1-2G43-1202 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1012-PID-0021-1201 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - C3 LPG Feed Distribution Header | C | 2019-08-07 | IDD1 | OL1-2G43-1201 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1039-SP-0810-3904 | Mechanical Equipment Data Sheet for BDU Product Inhibitor Drum | B | 2019-08-19 | IFQ | OL1-2M03-3904 | ME | 2019-08-19 | 036909C-JVD-TRN-02455 | 036909C-JVD-TRN-02455 | IFR | 2019-09-03 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-02455 |  | 2019-08-21 | 2
036909C-1011-PID-0021-1135 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Fuel Gas | C | 2019-08-07 | IDD1 | OL1-2G43-1135 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1011-PID-0021-1126 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Furnace Effluent & Decoke MOV S | C | 2019-08-07 | IDD1 | OL1-2G43-1126 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1039-SP-0810-3902 | Mechanical Equipment Data Sheet for BDU Solvent Inhibitor Drum | B | 2019-08-19 | IFQ | OL1-2M03-3902 | ME | 2019-08-19 | 036909C-JVD-TRN-02455 | 036909C-JVD-TRN-02455 | IFR | 2019-09-03 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-ME-02455 |  | 2019-08-21 | 2
036909C-1011-PID-0021-1112 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 6 | C | 2019-08-07 | IDD1 | OL1-2G43-1112 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1011-PID-0021-1111 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 5 | C | 2019-08-07 | IDD1 | OL1-2G43-1111 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1011-PID-0021-1110 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 4 | C | 2019-08-07 | IDD1 | OL1-2G43-1110 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1011-PID-0021-1109 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 3 | C | 2019-08-07 | IDD1 | OL1-2G43-1109 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1011-PID-0021-1108 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 2 | C | 2019-08-07 | IDD1 | OL1-2G43-1108 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1011-PID-0021-1107 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 1 | C | 2019-08-07 | IDD1 | OL1-2G43-1107 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1011-PID-0021-1106 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoke Air Header Distribution Header | C | 2019-08-07 | IDD1 | OL1-2G43-1106 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1011-PID-0021-1105 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Dilution Steam Distribution Header | C | 2019-08-07 | IDD1 | OL1-2G43-1105 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1011-PID-0021-1101 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed Distribution Header | C | 2019-08-07 | IDD1 | OL1-2G43-1101 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1010-PID-0021-1090 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Naphtha Feed - C3 LPG Battery Limit | A | 2019-08-07 | IDD1 | OL1-2G43-1090 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1010-PID-0021-1031 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Cracking Furnace Distribution - Sheet 2 | C | 2019-08-07 | IDD1 | OL1-2G43-1031 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1010-PID-0021-1030 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Cracking Furnace Distribution - Sheet 1 | C | 2019-08-07 | IDD1 | OL1-2G43-1030 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1010-PID-0021-1023 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - C2 Feed Superheater | C | 2019-08-07 | IDD1 | OL1-2G43-1023 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1010-PID-0021-1006 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - LPG Feed Steam Heater | B | 2019-08-07 | IDD1 | OL1-2G43-1006 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1010-PID-0021-1005 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - LPG Steam Vaporizer | C | 2019-08-07 | IDD1 | OL1-2G43-1005 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1010-PID-0021-1004 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - LPG Superheater | C | 2019-08-07 | IDD1 | OL1-2G43-1004 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1010-PID-0021-1003 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - LPG Drum & LPG Vaporizer | C | 2019-08-07 | IDD1 | OL1-2G43-1003 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1010-PID-0021-1002 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - LPG Feed Heater | C | 2019-08-07 | IDD1 | OL1-2G43-1002 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1010-PID-0021-1001 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Liquid Feed Heater | C | 2019-08-07 | IDD1 | OL1-2G43-1001 | PE | 2019-08-09 | 036909C-JVD-TRN-02403 | 036909C-JVD-TRN-02403 | IFR | 2019-08-26 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PE-02403 |  | 2019-08-14 | 2
036909C-1000-JSS-1310-0004 | Job Supply Specification For Butterfly Valves | 0 | 2019-04-16 | IMP | OL1-2R04-0008 | MP | 2019-04-24 | 036909C-JVD-TRN-01463 | 036909C-JVD-TRN-01463 | IFR | 2019-05-09 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-MP-01463 |  | 2019-04-25 | 2
036909C-1000-JSS-1310-0006 | Job Supply Specification For Plug Valves | 0 | 2019-04-16 | IMP | OL1-2R04-0009 | MP | 2019-04-24 | 036909C-JVD-TRN-01463 | 036909C-JVD-TRN-01463 | IFR | 2019-05-09 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-MP-01463 |  | 2019-04-25 | 2
036909C-1000-JSS-1310-0001 | Job Supply Specification For Valves -Gate-Globe-Check | 0 | 2019-04-16 | IMP | OL1-2R04-0041 | MP | 2019-04-24 | 036909C-JVD-TRN-01463 | 036909C-JVD-TRN-01463 | IFR | 2019-05-09 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-MP-01463 |  | 2019-04-25 | 2
036909C-1000-JSS-1541-0001 | Job Supply Specification For Control Valves | A | 2019-05-20 | IFR | OL1-2I92-0501 | IE | 2019-05-30 | 036909C-JVD-TRN-01770 | 036909C-JVD-TRN-01770 | IFA | 2019-06-14 | 2019-06-19 | A1-Approved without comments | TPSK-LSPA1-T-IE-01770 |  | 2019-05-31 | 1
036909C-1000-JSD-1300-0001 | Piping Class Summary And Piping Classes - Includes ex doc OL1-2P92-0003 as attachment | 1 | 2019-08-07 | IMP | OL1-2R04-0001 | MP | 2019-08-08 | 036909C-JVD-TRN-02390 | 036909C-JVD-TRN-02390 | IFR | 2019-08-23 | 2019-08-23 | R2-Comments as noted | TPSK-LSPA1-T-MP-02390 |  | 2019-08-09 | 2
036909C-1000-JSS-6300-0009 | Job Sprcification For Supply And Fabrication Of Grade 91 Alloy Steel Piping | A | 2019-04-16 | IFR | OL1-2R03-0030 | MP | 2019-04-24 | 036909C-JVD-TRN-01465 | 036909C-JVD-TRN-01465 | IFR | 2019-05-09 | 2019-05-17 | R1-No comments | TPSK-LSPA1-T-MP-01465 |  | 2019-04-25 | 2
036909C-1000-PP-613 | Spare Parts & Special Tools Instructions | 0 | 2018-10-01 | IMP | OL1-2C92-0013 | PL | 2018-10-02 | 036909C-JVD-TRN-00119 | 036909C-JVD-TRN-00119 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00119 |  | 2018-10-02 | 3
036909C-1028-PID-0021-2891 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Battery Limit | A | 2019-08-07 | IDD1 | OL1-2G43-2891 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-16 | 2
036909C-1028-PID-0021-2890 | P&ID - Olefins Unit 10 - Refrigeration System - HP Vapor-Liquid Ethylene-HP-LP Propylene BL | A | 2019-08-07 | IDD1 | OL1-2G43-2890 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2846 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Drain Drum | C | 2019-08-07 | IDD1 | OL1-2G43-2846 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2842 | P&ID - Olefins Unit 10 - Refrigeration System - LP Ethylene Product Cooling | C | 2019-08-07 | IDD1 | OL1-2G43-2842 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2840 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant 1st Stage Suction | C | 2019-08-07 | IDD1 | OL1-2G43-2840 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2838 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant 2nd Stage Suction | C | 2019-08-07 | IDD1 | OL1-2G43-2838 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2836 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant 3rd Stage Suction | C | 2019-08-07 | IDD1 | OL1-2G43-2836 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2834 | P&ID - Olefins Unit 10 - Refrigeration System - HP Ethylene Vapor Product | C | 2019-08-07 | IDD1 | OL1-2G43-2834 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1000-SP-1563-0001 | Instrument DS For Density Analyzers | A | 2019-09-02 | IFQ | OL1-2I20-2604 | IE | 2019-09-04 | 036909C-JVD-TRN-02570 | 036909C-JVD-TRN-02570 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-IE-02570 |  | 2019-09-05 | 1
036909C-1000-SP-1562-0001 | Instrument DS For Moisture Analyzers | A | 2019-09-02 | IFQ | OL1-2I20-2203 | IE | 2019-09-04 | 036909C-JVD-TRN-02570 | 036909C-JVD-TRN-02570 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-IE-02570 |  | 2019-09-05 | 1
036909C-1000-SP-1562-0002 | Instrument DS For Oxygen Analyzers | A | 2019-09-02 | IFQ | OL1-2I20-2103 | IE | 2019-09-04 | 036909C-JVD-TRN-02570 | 036909C-JVD-TRN-02570 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-IE-02570 |  | 2019-09-05 | 1
036909C-1000-SP-1563-0004 | Instrument DS For Viscosity Analyzer | A | 2019-09-02 | IFQ | OL1-2I20-2603 | IE | 2019-09-04 | 036909C-JVD-TRN-02570 | 036909C-JVD-TRN-02570 | IFA | 2019-09-19 |  | Transmitted | TPSK-LSPA1-T-IE-02570 |  | 2019-09-05 | 1
036909C-1028-PID-0021-2830 | P&ID - Olefins Unit 10 - Refrigeration System - HP Ethylene Liquid Product Chiller | C | 2019-08-07 | IDD1 | OL1-2G43-2830 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2828 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Surge Drum | C | 2019-08-07 | IDD1 | OL1-2G43-2828 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2825 | P&ID - Olefins Unit 10 - Refrigeration System - C2R Desuperheater And Condenser | C | 2019-08-07 | IDD1 | OL1-2G43-2825 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2824 | P&ID - Olefins Unit 10 - Refrigeration System - C2 Refrigerant Desuperheaters | C | 2019-08-07 | IDD1 | OL1-2G43-2824 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2823 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Compressor - Sheet 3 | B | 2019-08-07 | IDD1 | OL1-2G43-2823 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2822 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Compressor - Sheet 2 | C | 2019-08-07 | IDD1 | OL1-2G43-2822 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2821 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Compressor - Sheet 1 | C | 2019-08-07 | IDD1 | OL1-2G43-2821 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2819 | P&ID - Olefins Unit 10 - Refrigeration System - Propylene Product Chilling - Sheet 2 | C | 2019-08-07 | IDD1 | OL1-2G43-2819 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2818 | P&ID - Olefins Unit 10 - Refrigeration System - Propylene Product Chilling - Sheet 1 | C | 2019-08-07 | IDD1 | OL1-2G43-2818 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2816 | P&ID - Olefins Unit 10 - Refrigeration System - Propylene Product Pump | C | 2019-08-07 | IDD1 | OL1-2G43-2816 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2814 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Drain Drum | C | 2019-08-07 | IDD1 | OL1-2G43-2814 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2812 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 1st Stage Suction | C | 2019-08-07 | IDD1 | OL1-2G43-2812 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2810 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 2nd Stage Suction | C | 2019-08-07 | IDD1 | OL1-2G43-2810 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2808 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 3rd Stage Suction | C | 2019-08-07 | IDD1 | OL1-2G43-2808 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2807 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 3 | C | 2019-08-07 | IDD1 | OL1-2G43-2807 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2806 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 4th Stage Suction | C | 2019-08-07 | IDD1 | OL1-2G43-2806 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2805 | P&ID - Olefins Unit 10 - Refrigeration System - Hp C3 Refrigeration Distribution | C | 2019-08-07 | IDD1 | OL1-2G43-2805 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2804 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Receiver | C | 2019-08-07 | IDD1 | OL1-2G43-2804 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2803 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Condenser | C | 2019-08-07 | IDD1 | OL1-2G43-2803 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2802 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 2 | C | 2019-08-07 | IDD1 | OL1-2G43-2802 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1028-PID-0021-2801 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 1 | C | 2019-08-07 | IDD1 | OL1-2G43-2801 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1020-PID-0021-2090 | P&ID - Olefins Unit 10 - Quench Oil - Cracker Product- Hexane- Flux Oil Battery Limit | A | 2019-08-07 | IDD1 | OL1-2G43-2090 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1020-PID-0021-2042 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Drain Drum | C | 2019-08-07 | IDD1 | OL1-2G43-2042 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1020-PID-0021-2040 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Drain Collection | C | 2019-08-07 | IDD1 | OL1-2G43-2040 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1020-PID-0021-2027 | P&ID - Olefins Unit 10 - Quench Oil - Heavy Fuel Oil Product Cooling | C | 2019-08-07 | IDD1 | OL1-2G43-2027 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1020-PID-0021-2026 | P&ID - Olefins Unit 10 - Quench Oil - Heavy Fuel Oil Pumps | C | 2019-08-07 | IDD1 | OL1-2G43-2026 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1020-PID-0021-2025 | P&ID - Olefins Unit 10 - Quench Oil - Heavy Fuel Oil Stripper | C | 2019-08-07 | IDD1 | OL1-2G43-2025 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1020-PID-0021-2022 | P&ID - Olefins Unit 10 - Quench Oil - Purge Oil Filtration | C | 2019-08-07 | IDD1 | OL1-2G43-2022 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1020-PID-0021-2021 | P&ID - Olefins Unit 10 - Quench Oil - Fuel Oil Product Cooling | C | 2019-08-07 | IDD1 | OL1-2G43-2021 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1020-PID-0021-2020 | P&ID - Olefins Unit 10 - Quench Oil - Light Fuel Oil Stripper | C | 2019-08-07 | IDD1 | OL1-2G43-2020 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1020-PID-0021-2008 | P&ID - Olefins Unit 10 - Quench Oil - VLP Steam Generation - Sheet 3 | B | 2019-08-07 | IDD1 | OL1-2G43-2008 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1020-PID-0021-2007 | P&ID - Olefins Unit 10 - Quench Oil - VLP Steam Generation - Sheet 2 | C | 2019-08-07 | IDD1 | OL1-2G43-2007 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1020-PID-0021-2006 | P&ID - Olefins Unit 10 - Quench Oil - VLP Steam Generation - Sheet 1 | C | 2019-08-07 | IDD1 | OL1-2G43-2006 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1020-PID-0021-2005 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Filtration | C | 2019-08-07 | IDD1 | OL1-2G43-2005 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1020-PID-0021-2003 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Pumps | C | 2019-08-07 | IDD1 | OL1-2G43-2003 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1020-PID-0021-2001 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Tower | C | 2019-08-07 | IDD1 | OL1-2G43-2001 | PE | 2019-08-14 | 036909C-JVD-TRN-02434 | 036909C-JVD-TRN-02434 | IFR | 2019-08-29 | 2019-09-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-02434 |  | 2019-08-15 | 2
036909C-1011-DW-0131-1514 | USC 36M Recycle Furnace Steel Radiant End Wall at Col Line 1 and 6_8 | A | 2019-03-29 | IFI | OL1-2K32-1514 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1011-DW-0131-1514 | USC 36M Recycle Furnace Steel Radiant End Wall at Col 1 and 6_8 | 1 | 2019-07-17 | IMP | OL1-2K32-1514 | CV | 2019-07-23 | 036909C-JVD-TRN-02248 | 036909C-JVD-TRN-02248 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02248 |  | 2019-07-24 | 3
036909C-1011-DW-0131-1514 | USC Recycle Furnace Steel Radiant End Wall at Col 1 and 6_8 | 0 | 2019-05-17 | IMP | OL1-2K32-1514 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1011-DW-0131-1520 | USC 36M Recycle Furnace Steel Convection Side Wall at Col Line B1 | A | 2019-04-08 | IFI | OL1-2K32-1520 | CV | 2019-04-10 | 036909C-JVD-TRN-01308 | 036909C-JVD-TRN-01308 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01308 | TPSK-LSPA1-T-CV-01308 | 2019-04-11 | 3
036909C-1011-DW-0131-1520 | USC 36M Recycle Furnace Steel Convection Side Wall at Col Line B1 | 0 | 2019-05-24 | IMP | OL1-2K32-1520 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1011-DW-0131-1521 | USC 36M Recycle Furnace Steel Convection Side Wall at COL Line C1 | A | 2019-04-08 | IFI | OL1-2K32-1521 | CV | 2019-04-10 | 036909C-JVD-TRN-01308 | 036909C-JVD-TRN-01308 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01308 |  | 2019-04-11 | 3
036909C-1011-DW-0131-1521 | USC 36M Recycle Furnace Steel Convection Side Wall at COL Line C1 | 0 | 2019-05-24 | IMP | OL1-2K32-1521 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1011-DW-0131-1540 | USC 36M Recycle Furnace Steel Crossover Limit Stop Details | 0 | 2019-05-24 | IMP | OL1-2K32-1540 | CV | 2019-05-30 | 036909C-JVD-TRN-01777 | 036909C-JVD-TRN-01777 | IFI |  | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-CV-01777 |  | 2019-05-31 | 3
036909C-1011-DW-0131-1541 | USC 36M Recycle Furnace Steel Convection Sections and Details | 0 | 2019-05-24 | IMP | OL1-2K32-1541 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1011-DW-0131-1541 | USC 36M Recycle Furnace Steel Convection Sections and Details | A | 2019-04-08 | IFI | OL1-2K32-1541 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1012-DW-0131-2514 | USC 132U Cracking Furnace Steel Radiant End Wall At COL Line 1 And 5 | 1 | 2019-07-17 | IMP | OL1-2K32-2514 | CV | 2019-07-23 | 036909C-JVD-TRN-02248 | 036909C-JVD-TRN-02248 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02248 |  | 2019-07-24 | 3
036909C-1012-DW-0131-2514 | USC 132U Cracking Furnace Steel Radiant End Wall At COL Line 1 And 5 | A | 2019-03-29 | IFI | OL1-2K32-2514 | CV | 2019-04-01 | 036909C-JVD-TRN-01222 | 036909C-JVD-TRN-01222 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01222 |  | 2019-04-02 | 3
036909C-1012-DW-0131-2514 | USC 132U Cracking Furnace Steel Radiant End Wall At COL Line 1 And 5 | 0 | 2019-05-15 | IMP | OL1-2K32-2514 | CV | 2019-05-21 | 036909C-JVD-TRN-01709 | 036909C-JVD-TRN-01709 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01709 |  | 2019-05-23 | 3
036909C-1012-DW-0131-2541 | USC 132U Cracking Furnace Steel Convection Sections and Details | A | 2019-04-08 | IFI | OL1-2K32-2541 | CV | 2019-04-10 | 036909C-JVD-TRN-01308 | 036909C-JVD-TRN-01308 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01308 |  | 2019-04-11 | 3
036909C-1012-DW-0131-2541 | USC 132U Cracking Furnace Steel Convection Sections and Details | 0 | 2019-05-24 | IMP | OL1-2K32-2541 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1012-DW-0131-2540 | USC 132U Cracking Furnace Steel Crossover Limit Stop Details | 0 | 2019-05-24 | IMP | OL1-2K32-2540 | CV | 2019-05-30 | 036909C-JVD-TRN-01777 | 036909C-JVD-TRN-01777 | IFI |  | 2019-07-15 | R1-No comments | TPSK-LSPA1-T-CV-01777 |  | 2019-05-31 | 3
036909C-1012-DW-0131-2521 | USC 132U Cracking Furnace Steel Convection Side Wall at COL Line 2 thru C6 | A | 2019-04-08 | IFI | OL1-2K32-2521 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1012-DW-0131-2521 | USC 132U Cracking Furnace Steel Convection Side Wall at COL Line C2 thru C6 | 0 | 2019-05-24 | IMP | OL1-2K32-2521 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-1012-DW-0131-2520 | USC 132U Cracking Furnace Steel Convection Side Wall at COL Line B2 thru B6 | A | 2019-04-08 | IFI | OL1-2K32-2520 | CV | 2019-04-09 | 036909C-JVD-TRN-01293 | 036909C-JVD-TRN-01293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-01293 |  | 2019-04-10 | 3
036909C-1012-DW-0131-2520 | USC 132U Cracking Furnace Steel Convection Side Wall at COL Line B2 thru B6 | 0 | 2019-05-24 | IMP | OL1-2K32-2520 | CV | 2019-05-29 | 036909C-JVD-TRN-01765 | 036909C-JVD-TRN-01765 | IFI |  | 2019-06-21 | R1-No comments | TPSK-LSPA1-T-CV-01765 |  | 2019-05-30 | 3
036909C-105U-DW-1612-0001 | Earthing and Lightning Protection Layout- Zone 5U Utilities | A | 2019-09-03 | IFR | OL1-2E52-0018 | EE | 2019-09-06 | 036909C-JVD-TRN-02580 | 036909C-JVD-TRN-02580 | IFR | 2019-09-20 | 2019-09-18 | R2-Comments as noted | TPSK-LSPA1-T-EE-02580 |  | 2019-09-10 | 2
036909C-105U-DW-1632-0001 | Lighting Layout- Zone 5U Utilities | A | 2019-09-13 | IFR | OL1-2E43-0020 | EE | 2019-09-13 | 036909C-JVD-TRN-02640 | 036909C-JVD-TRN-02640 | IFR | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-EE-02640 |  | 2019-09-17 | 1
036909C-102C-DW-1742-0003-001 | Foundation And Elevation Of Steel Structure For 10-STR-2C03 & 10-T-2720 | A | 2019-09-11 | IFR | OL1-2K31-1860 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-021 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Steel Bracings Details | A | 2019-08-19 | IFR | OL1-2K31-5170 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-015 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams | A | 2019-08-19 | IFR | OL1-2K31-1494 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-016 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams | A | 2019-08-19 | IFR | OL1-2K31-1495 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-013 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams | A | 2019-08-19 | IFR | OL1-2K31-1492 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-014 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams | A | 2019-08-19 | IFR | OL1-2K31-1493 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-019 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams | A | 2019-08-19 | IFR | OL1-2K31-1498 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-020 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Steel Bracings Details | A | 2019-08-19 | IFR | OL1-2K31-1499 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-017 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams | A | 2019-08-19 | IFR | OL1-2K31-1496 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-018 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams | A | 2019-08-19 | IFR | OL1-2K31-1497 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-011 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams | A | 2019-08-19 | IFR | OL1-2K31-1490 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-012 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams | A | 2019-08-19 | IFR | OL1-2K31-1491 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-006 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Elevation 6 To 13 | A | 2019-08-19 | IFR | OL1-2K31-1485 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-007 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Columns | A | 2019-08-19 | IFR | OL1-2K31-1486 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-010 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams | A | 2019-08-19 | IFR | OL1-2K31-1489 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-008 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Columns | A | 2019-08-19 | IFR | OL1-2K31-1487 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-009 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Columns | A | 2019-08-19 | IFR | OL1-2K31-1488 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-002 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Plans | A | 2019-08-19 | IFR | OL1-2K31-1481 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-003 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Plans | A | 2019-08-19 | IFR | OL1-2K31-1482 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-004 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Elevation A/B | A | 2019-08-19 | IFR | OL1-2K31-1483 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-001 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - 3D View | A | 2019-08-19 | IFR | OL1-2K31-1480 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-102C-DW-1741-0004-005 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Elevation 6 To 13 | A | 2019-08-19 | IFR | OL1-2K31-1484 | CV | 2019-09-13 | 036909C-JVD-TRN-02641 | 036909C-JVD-TRN-02641 | IFA | 2019-09-30 |  | Transmitted | TPSK-LSPA1-T-CV-02641 |  | 2019-09-17 | 1
036909C-1000-NM-1661-0001 | SMCS I/O List | B | 2019-09-11 | IFR | OL1-2R05-0009 | EE | 2019-09-13 | 036909C-JVD-TRN-02639 | 036909C-JVD-TRN-02639 | IFR | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-EE-02639 |  | 2019-09-17 | 1
036909C-105W-DW-1624-0001 | Cable Routing Cross Section - Zone 5W | A | 2019-08-23 | IFR | OL1-2E34-0008 | EE | 2019-08-27 | 036909C-JVD-TRN-02495 | 036909C-JVD-TRN-02495 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-EE-02495 |  | 2019-08-28 | 2
036909C-103A-DW-1624-0001 | Cable Routing Cross Section - Zone 3A | A | 2019-08-28 | IFR | OL1-2E34-0015 | EE | 2019-08-29 | 036909C-JVD-TRN-02530 | 036909C-JVD-TRN-02530 | IFR | 2019-09-12 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-EE-02530 |  | 2019-08-29 | 2
036909C-103S-DW-1624-0001 | Cable Routing Cross Section - Zone 3S | A | 2019-08-20 | IFR | OL1-2E34-0004 | EE | 2019-08-27 | 036909C-JVD-TRN-02495 | 036909C-JVD-TRN-02495 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-EE-02495 |  | 2019-08-28 | 2
036909C-100S-DW-1624-0001 | Cable Routing Cross Section - Zone 0S | A | 2019-08-20 | IFR | OL1-2E34-0003 | EE | 2019-08-27 | 036909C-JVD-TRN-02495 | 036909C-JVD-TRN-02495 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-EE-02495 |  | 2019-08-28 | 2
036909C-105T-DW-1624-0001 | Cable Routing Cross Section - Zone 5T | A | 2019-08-28 | IFR | OL1-2E34-0001 | EE | 2019-08-30 | 036909C-JVD-TRN-02548 | 036909C-JVD-TRN-02548 | IFR | 2019-09-13 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-EE-02548 |  | 2019-09-03 | 2
036909C-103A-DW-1622-0201 | Power Layout - Zone 3A Butadiene Extraction Unit | A | 2019-08-23 | IFR | OL1-2E32-0015 | EE | 2019-08-27 | 036909C-JVD-TRN-02496 | 036909C-JVD-TRN-02496 | IFR | 2019-09-10 | 2019-09-16 | R2-Comments as noted | TPSK-LSPA1-T-EE-02496 |  | 2019-08-28 | 1
036909C-105W-DW-1622-0201 | Power Layout - Zone 5W Waste Water Treatment | A | 2019-08-20 | IFR | OL1-2E32-0008 | EE | 2019-08-27 | 036909C-JVD-TRN-02496 | 036909C-JVD-TRN-02496 | IFR | 2019-09-10 | 2019-09-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02496 |  | 2019-08-28 | 1
036909C-1012-MR-1546-1253 | Material Requisition for Restriction Orifice | A | 2019-06-11 | IFQ | OL1-2C17-012253 | PL | 2019-06-12 | 036909C-JVD-TRN-01881 | 036909C-JVD-TRN-01881 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-PL-01881 |  | 2019-06-14 | 3
036909C-1011-SP-1546-1153 | Instrument Datasheets for Restriction Orifice | A | 2019-06-11 | IFQ | OL1-2I20-1153 | IE | 2019-06-12 | 036909C-JVD-TRN-01879 | 036909C-JVD-TRN-01879 | IFR | 2019-06-27 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-IE-01879 |  | 2019-06-14 | 2
036909C-1000-NM-1661-0001 | SMCS I/O List | A | 2019-06-27 | IFR | OL1-2R05-0009 | EE | 2019-06-28 | 036909C-JVD-TRN-02023 | 036909C-JVD-TRN-02023 | IFR | 2019-07-12 | 2019-07-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02023 | Please issue document IFR. | 2019-07-01 | 1
036909C-1000-DW-1422-0001 | Soil Investigation Plan | B | 2018-10-10 | IFR | OL1-2K43-0004 | CV | 2018-10-12 | 036909C-JVD-TRN-00163 | 036909C-JVD-TRN-00163 | IFR | 2018-10-26 | 2018-12-24 | R1-No comments | TPSK-LSPA1-T-CV-00163 |  | 2018-10-15 | 2
036909C-1000-JSD-2000-0001 | Buildings Design And Construction | A | 2018-10-10 | IFR | OL1-2R02-0005 | CV | 2018-10-11 | 036909C-JVD-TRN-00158 | 036909C-JVD-TRN-00158, ROC-TPSK-CECO-T-00004 | IFR | 2018-10-25 | 2019-03-18 | R2-Comments as noted | TPSK-LSPA1-T-CV-00158 |  | 2018-10-11 | 2
036909C-1012-PDS-0811-1207 | Process Equipment Datasheet - 10-D-1200-1600 - 132U Cracking Furnace Steam Drum | A | 2018-10-11 | IFR | OL1-2G30-1207 | PE | 2018-10-11 | 036909C-JVD-TRN-00159 | 036909C-JVD-TRN-00159 | IFR | 2018-10-25 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00159 |  | 2018-10-12 | 2
036909C-1030-DI-0007-3001 | Area Basis of Design - 30 BDU | A | 2018-10-09 | IFA | OL1-2G05-3001 | PE | 2018-10-09 | 036909C-JVD-TRN-00150 | 036909C-JVD-TRN-00150, ROC-TPSK-CECO-T-00001 | IFA | 2018-10-23 | 2019-04-02 | R2-Comments as noted | TPSK-LSPA1-T-PE-00150 |  | 2018-10-10 | 1
036909C-1000-MR-0662-0002 | Material Requisition For Cold Box And Core Exchangers Requisition For Inquiry - For next rev. see Doc. Client Ref. OL1-2C13-144000 | B | 2018-10-09 | IFQ | OL1-2C13-144000 | ME | 2018-10-10 | 036909C-JVD-TRN-00153 | 036909C-JVD-TRN-00153 | IFR | 2018-10-24 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-ME-00153 | For next rev. see Doc. Client Ref. OL1-2C13-144000 | 2018-10-11 | 2
036909C-1021-TDS-0661-2101 | Mechanical Equipment Data Sheet - 10-E-2100 - Quench Water Cooler | B | 2018-10-09 | IFQ | OL1-2M03-2101 | ME | 2018-10-10 | 036909C-JVD-TRN-00154 | 036909C-JVD-TRN-00154 | IFI |  | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-ME-00154 |  | 2018-10-11 | 3
036909C-1000-PS-1422-0001 | Price List For Geotechnical Investigation | A | 2018-10-04 | IFR | OL1-2K43-0003 | CV | 2018-10-10 | 036909C-JVD-TRN-00147 | 036909C-JVD-TRN-00147 | IFR | 2018-10-24 | 2018-12-24 | R1-No comments | TPSK-LSPA1-T-CV-00147 |  | 2018-10-09 | 2
036909C-1000-MS-1422-0001 | Technical Specification For Geotechnical Investigation | A | 2018-10-04 | IFR | OL1-2K43-0002 | CV | 2018-10-10 | 036909C-JVD-TRN-00147 | 036909C-JVD-TRN-00147 | IFR | 2018-10-24 | 2018-12-24 | R1-No comments | TPSK-LSPA1-T-CV-00147 |  | 2018-10-09 | 2
036909C-1028-PDS-0800-2830 | Process Equipment Datasheet - 10-D-2830 - C3R 3rd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2830 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | 2018-10-08 | 2
036909C-1000-DW-1422-0001 | Soil Investigation Plan | A | 2018-10-04 | IFR | OL1-2K43-0004 | CV | 2018-10-10 | 036909C-JVD-TRN-00145 | 036909C-JVD-TRN-00145 | IFR | 2018-10-24 | 2018-12-24 | R1-No comments | TPSK-LSPA1-T-CV-00145 |  | 2018-10-09 | 2
036909C-1000-PP-133 | TPSK HOC Organization Chart | 0 | 2018-10-09 | IFI | OL1-2W92-0011 | PC | 2018-10-09 | 036909C-JVD-TRN-00146 | 036909C-JVD-TRN-00146 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PM-00146 |  | 2018-10-08 | 3
036909C-1051-PDS-0800-5100 | Process Equipment Data Sheet - 10-D-5100 - Deaerator | A | 2018-10-09 | IFR | OL1-2G30-5100 | PE | 2018-10-09 | 036909C-JVD-TRN-00151 | 036909C-JVD-TRN-00151 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00151 |  | 2018-10-10 | 2
036909C-1022-PDS-0800-2230 | Process Equipment Datasheet - 10-D-2230 - CG 3rd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2230 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | 2018-10-08 | 2
036909C-1028-PDS-0800-2840 | Process Equipment Datasheet - 10-D-2840 - C3R 4th Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2840 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | 2018-10-08 | 2
036909C-1000-JSD-1580-0001 | Integrated Turbine And Compressor Control System | A | 2018-10-08 | IFR | OL1-2R06-0017 | IE | 2018-10-10 | 036909C-JVD-TRN-00148 | 036909C-JVD-TRN-00148 | IFR | 2018-10-24 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-IE-00148 |  | 2018-10-09 | 2
036909C-1000-SP-1130-0001 | Particular Technical Specification For Residue Gas Expander/Recompressor | A | 2018-10-05 | IFQ | OL1-2M57-0012 | ME | 2018-10-09 | 036909C-JVD-TRN-00139 | 036909C-JVD-TRN-00139 | IFR | 2018-10-22 | 2018-10-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00139 |  | 2018-10-07 | 2
036909C-1000-SR-1011-0001 | Scope Of Supply For Centrifugal Compressors Steam Turbine Driven | A | 2018-10-04 | IFQ | OL1-2M56-0008 | ME | 2018-10-08 | 036909C-JVD-TRN-00136 | 036909C-JVD-TRN-00136 | IFR | 2018-10-22 | 2018-10-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00136 |  | 2018-10-08 | 2
036909C-1000-JSD-1501-0001 | Instrument Numbering | A | 2018-10-03 | IFR | OL1-2R06-0022 | IE | 2018-10-05 | 036909C-JVD-TRN-00132 | 036909C-JVD-TRN-00132 | IFR | 2018-10-19 | 2018-10-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05 | 2
036909C-1000-DW-1702-0002 | General Notes For Precast Concrete Works | A | 2018-10-04 | IFR | OL1-2K92-0002 | CV | 2018-10-08 | 036909C-JVD-TRN-00137 | 036909C-JVD-TRN-00137, ROC-TPSK-CECO-T-00003 | IFR | 2018-10-22 | 2018-12-24 | R1-No comments | TPSK-LSPA1-T-CV-00137 |  | 2018-10-08 | 2
036909C-1000-SP-1011-0001 | Particular Technical Specification For Centrifugal Compressors Steam Turbine Driven | A | 2018-10-04 | IFQ | OL1-2M57-0008 | ME | 2018-10-08 | 036909C-JVD-TRN-00136 | 036909C-JVD-TRN-00136 | IFR | 2018-10-22 | 2018-10-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00136 |  | 2018-10-08 | 2
036909C-1000-MR-1011-0001 | Material Requisition For Centrifugal Compressors Steam Turbine Driven - For Next Revision See Document OL1-2C13-401000 | A | 2018-10-04 | IFQ | OL1-2C13-401000 | ME | 2018-10-08 | 036909C-JVD-TRN-00136 | 036909C-JVD-TRN-00136 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-ME-00136 | For Next Revision See Document OL1-2C13-401000 | 2018-10-08 | 2
036909C-1028-PDS-0800-2820 | Process Equipment Datasheet - 10-D-2820 - C3R 2nd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2820 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | 2018-10-08 | 2
036909C-1051-PDS-0900-5109 | Process Equipment Datasheet - 10-P-5110 A-B - Condensate Pumps | A | 2018-10-04 | IFR | OL1-2G30-5109 | PE | 2018-10-08 | 036909C-JVD-TRN-00141 | 036909C-JVD-TRN-00141 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-PE-00141 |  | 2018-10-09 | 2
036909C-1021-PDS-0600-2101 | Process Equipment Datasheet - 10-E-2100 A-F - Quench Water Cooler | B | 2018-10-04 | IFD | OL1-2G30-2101 | PE | 2018-10-08 | 036909C-JVD-TRN-00143 | 036909C-JVD-TRN-00143 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00143 |  | 2018-10-07 | 3
036909C-1028-PDS-0800-2810 | Process Equipment Datasheet - 10-D-2810 - C3R 1st Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2810 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | 2018-10-08 | 2
036909C-1022-PDS-0800-2210 | Process Equipment Datasheet - 10-D-2210 - CG 1st Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2210 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | 2018-10-08 | 2
036909C-1022-PDS-0800-2220 | Process Equipment Datasheet - 10-D-2220 - CG 2nd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2220 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | 2018-10-08 | 2
036909C-1000-SR-1130-0001 | Scope Of Supply For Residue Gas Expander/Recompressor | A | 2018-10-05 | IFQ | OL1-2M56-0012 | ME | 2018-10-09 | 036909C-JVD-TRN-00139 | 036909C-JVD-TRN-00139 | IFR | 2018-10-22 | 2018-10-26 | R2-Comments as noted | TPSK-LSPA1-T-ME-00139 |  | 2018-10-07 | 2
036909C-1051-PDS-0900-5102 | Process Equipment Datasheet - 10-P-5102 A-B - VLP BFW Pumps | A | 2018-10-04 | IFR | OL1-2G30-5102 | PE | 2018-10-08 | 036909C-JVD-TRN-00141 | 036909C-JVD-TRN-00141 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-PE-00141 |  | 2018-10-09 | 2
036909C-1051-PDS-0900-5101 | Process Equipment Datasheet - 10-P-5100 A-C - SHP BFW Pumps | A | 2018-10-04 | IFR | OL1-2G30-5101 | PE | 2018-10-08 | 036909C-JVD-TRN-00141 | 036909C-JVD-TRN-00141 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-PE-00141 |  | 2018-10-09 | 2
036909C-1000-MR-1130-0001 | Material Requisition For Residue Gas Expander/Recompressor - For Next Revision See Document OL1-2C13-421000 | A | 2018-10-05 | IFQ | OL1-2C13-421000 | ME | 2018-10-09 | 036909C-JVD-TRN-00139 | 036909C-JVD-TRN-00139 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-ME-00139 | For Next Revision See Document OL1-2C13-421000 | 2018-10-07 | 2
036909C-1055-PDS-0800-5550 | Process Equipment Datasheet - 10-D-5550 - HP Flare Knock-Out Drum | A | 2018-10-04 | IFR | OL1-2G30-5550 | PE | 2018-10-08 | 036909C-JVD-TRN-00142 | 036909C-JVD-TRN-00142 | IFR | 2018-10-22 | 2018-10-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00142 |  | 2018-10-07 | 2
036909C-1000-NM-0001-1010 | Heat and Material Balance - ISBL Supporting Utilities | A | 2018-10-03 | IFI | OL1-2G44-1010 | PE | 2018-10-03 | 036909C-JVD-TRN-00128 | 036909C-JVD-TRN-00128, ROC-TPSK-CECO-T-00012 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00128 |  | 2018-10-04 | 3
036909C-1025-PDS-0600-2511 | Process Equipment Datasheet - 10-E-2510 - Demeth Prefrac Condenser | B | 2018-10-03 | IFD | OL1-2G30-2511 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131, ROC-TPSK-CECO-T-00019 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05 | 3
036909C-1025-PDS-0600-2505 | Process Equipment Datasheet - 10-E2506 and 10-E2508 - Demeth Prefrac Feed Cooler No 3 and No 4 | B | 2018-10-03 | IFD | OL1-2G30-2505 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05 | 3
036909C-1025-SP-1011-2550 | Mechanical Equipment Datasheet for Residue Gas Expander-Recompressor | B | 2018-10-04 | IFQ | OL1-2M03-2550 | ME | 2018-10-05 | 036909C-JVD-TRN-00130 | 036909C-JVD-TRN-00130 | IFI |  | 2018-10-26 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00130 |  | 2018-10-05 | 3
036909C-1028-PDS-0600-2884 | Process Equipment Datasheet - 10-E-2884 - LP Ethylene Product Cooler No 2 | B | 2018-10-03 | IFD | OL1-2G30-2884 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131, ROC-TPSK-CECO-T-00019 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05 | 3
036909C-1025-PDS-0600-2541 | Process Equipment Datasheet - 10-E-2540 - Demethanizer Condenser | B | 2018-10-03 | IFD | OL1-2G30-2541 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131, ROC-TPSK-CECO-T-00019 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05 | 3
036909C-1025-PDS-0600-2526 | Process Equipment Datasheet - 10-E-2525 - Hydrogen Core Exchanger | B | 2018-10-03 | IFD | OL1-2G30-2526 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131, ROC-TPSK-CECO-T-00019 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05 | 3
036909C-1025-PDS-0600-2587 | Process Equipment Datasheet - 10-E-2587 - C2 Tower Side Reboiler | B | 2018-10-03 | IFD | OL1-2G30-2587 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131, ROC-TPSK-CECO-T-00019 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05 | 3
036909C-1025-PDS-0600-2521 | Process Equipment Datasheet - 10-E-2520 - Rectifier Condenser | B | 2018-10-03 | IFD | OL1-2G30-2521 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131, ROC-TPSK-CECO-T-00019 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05 | 3
036909C-1028-PDS-0600-2882 | Process Equipment Datasheet - 10-E-2882 - LP Ethylene Product Cooler No 1 | B | 2018-10-03 | IFD | OL1-2G30-2882 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131, ROC-TPSK-CECO-T-00019 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05 | 3
036909C-1022-SP-1011-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor | B | 2018-10-02 | IFQ | OL1-2M03-2200 | ME | 2018-10-03 | 036909C-JVD-TRN-00127 | 036909C-JVD-TRN-00127 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00127 |  | 2018-10-04 | 3
036909C-1025-PDS-0600-2585 | Process Equipment Datasheet - 10-E-2585 - C2 Tower Bottoms Reboiler | B | 2018-10-03 | IFD | OL1-2G30-2585 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131, ROC-TPSK-CECO-T-00019 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05 | 3
036909C-1025-PDS-0600-2500 | Process Equipment Datasheet - 10-E-2500 - Propylene Refrig Subcooler | B | 2018-10-03 | IFD | OL1-2G30-2500 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131, ROC-TPSK-CECO-T-00019 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05 | 3
036909C-1025-PDS-0600-2531 | Process Equipment Datasheet - 10-E-2530 - Demeth Feed Cooler | B | 2018-10-03 | IFD | OL1-2G30-2531 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131, ROC-TPSK-CECO-T-00019 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | 2018-10-05 | 3
036909C-1028-SP-1011-2800 | Mechanical Equipment Data Sheet for Propylene Refrigeration Compressor | B | 2018-10-02 | IFQ | OL1-2M03-2800 | ME | 2018-10-03 | 036909C-JVD-TRN-00127 | 036909C-JVD-TRN-00127 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00127 |  | 2018-10-04 | 3
036909C-1000-SR-0661-0001 | Scope Of Supply For Plate And Frame Heat Exchangers | A | 2018-10-01 | IFQ | OL1-2M56-0064 | ME | 2018-10-03 | 036909C-JVD-TRN-00124 | 036909C-JVD-TRN-00124 | IFR | 2018-10-17 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00124 |  | 2018-10-04 | 2
036909C-1000-JSD-1554-0001 | TEMPERATURE MEASUREMENT | A | 2018-09-28 | IFR | OL1-2R06-0007 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04 | 2
036909C-1000-JSD-1511-0001 | Instrument Cabinet | A | 2018-09-28 | IFR | OL1-2R06-0016 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04 | 2
036909C-1000-MR-0661-0001 | Material Requisition For Plate And Frame Heat Exchangers Requisition For Inquiry - For next Rev. see Doc. Client Ref. OL1-2C13-142000 | A | 2018-10-01 | IFQ | OL1-2C13-142000 | ME | 2018-10-03 | 036909C-JVD-TRN-00124 | 036909C-JVD-TRN-00124 | IFR | 2018-10-17 | 2018-10-24 | A1-Approved without comments | TPSK-LSPA1-T-ME-00124 | For next Rev. see Doc. Client Ref. OL1-2C13-142000 | 2018-10-04 | 2
036909C-1000-JSD-1541-0001 | Final Control Element | A | 2018-09-28 | IFR | OL1-2R06-0008 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121, ROC-TPSK-CECO-T-00004 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04 | 2
036909C-1000-SR-0662-0002 | Scope Of Supply For Cold Box And Core Exchangers | A | 2018-10-01 | IFQ | OL1-2M56-0066 | ME | 2018-10-03 | 036909C-JVD-TRN-00125 | 036909C-JVD-TRN-00125 | IFR | 2018-10-17 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00125 |  | 2018-10-04 | 2
036909C-1000-JSD-1540-0001 | Instrument General Design | A | 2018-09-28 | IFR | OL1-2R06-0001 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04 | 2
036909C-1000-JSD-1552-0001 | LEVEL MEASUREMENT | A | 2018-09-28 | IFR | OL1-2R06-0005 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04 | 2
036909C-1000-SP-0661-0001 | Particular Technical Specification For Plate And Frame Heat Exchangers | A | 2018-10-01 | IFQ | OL1-2M57-0064 | ME | 2018-10-03 | 036909C-JVD-TRN-00124 | 036909C-JVD-TRN-00124 | IFR | 2018-10-17 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00124 |  | 2018-10-04 | 2
036909C-1000-JSD-1515-0004 | Machinery Monitoring System | A | 2018-09-28 | IFR | OL1-2R06-0013 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04 | 2
036909C-1000-JSD-1553-0001 | PRESSURE MEASUREMENT | A | 2018-09-28 | IFR | OL1-2R06-0006 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04 | 2
036909C-1000-JSD-0000-0004 | Cold Box Design Specification | A | 2018-10-01 | IFR | OL1-2G01-0002 | PE | 2018-10-03 | 036909C-JVD-TRN-00123 | 036909C-JVD-TRN-00123, ROC-TPSK-CECO-T-00003, ROC-TPSK-CECO-T-00004 | IFR | 2018-10-17 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00123 |  | 2018-10-04 | 2
036909C-1000-JSD-1522-0001 | Electrical And Instrument Interface Philosophy | A | 2018-09-28 | IFR | OL1-2R07-0020 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | 2018-10-04 | 2
036909C-1000-MR-0662-0002 | Material Requisition For Cold Box And Core Exchangers Requisition For Inquiry | A | 2018-10-01 | IFQ | OL1-2M55-0066 | ME | 2018-10-03 | 036909C-JVD-TRN-00125 | 036909C-JVD-TRN-00125 | IFR | 2018-10-17 | 2018-10-24 | A1-Approved without comments | TPSK-LSPA1-T-ME-00125 |  | 2018-10-04 | 2
036909C-1028-SP-1011-2850 | Mechanical Equipment Data Sheet for Ethylene Refrigeration Compressor | B | 2018-10-02 | IFQ | OL1-2M03-2850 | ME | 2018-10-03 | 036909C-JVD-TRN-00127 | 036909C-JVD-TRN-00127 | IFI |  | 2018-10-26 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00127 |  | 2018-10-04 | 3
036909C-1000-SP-0662-0002 | Particular Technical Specification For Cold Box And Core Exchangers | A | 2018-10-01 | IFQ | OL1-2M57-0066 | ME | 2018-10-03 | 036909C-JVD-TRN-00125 | 036909C-JVD-TRN-00125 | IFR | 2018-10-17 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00125 |  | 2018-10-04 | 2
036909C-1025-PDS-0600-2575 | Process Equipment Datasheet - 10-E-2575 - Deethanizer Reboiler | A | 2018-09-26 | IFA | OL1-2G30-2575 | PE | 2018-09-26 | 036909C-JVD-TRN-00094 | 036909C-JVD-TRN-00094 | IFA | 2018-10-10 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00094 |  | 2018-09-27 | 1
036909C-1028-PDS-0600-2809 | Process Equipment Datasheet - 10-E-2809 - C3 Chiller No 2 | A | 2018-09-28 | IFA | OL1-2G30-2809 | PE | 2018-09-28 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | 2018-10-01 | 1
036909C-1021-PDS-0800-2160 | Process Equipment Datasheet - 10-D-2160 - Dilution Steam Generator | A | 2018-09-28 | IFA | OL1-2G30-2160 | PE | 2018-09-28 | 036909C-JVD-TRN-00115 | 036909C-JVD-TRN-00115 | IFA | 2018-10-12 | 2018-11-05 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00115 |  | 2018-10-01 | 1
036909C-1025-PDS-0600-2576 | Process Equipment Datasheet - 10-E-2576 - Deethanizer Bottoms Cooler | A | 2018-09-26 | IFA | OL1-2G30-2576 | PE | 2018-09-26 | 036909C-JVD-TRN-00094 | 036909C-JVD-TRN-00094 | IFA | 2018-10-10 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00094 |  | 2018-09-27 | 1
036909C-1028-PDS-0600-2852 | Process Equipment Datasheet - 10-E-2852 - C2R Desuperheater No 1 | A | 2018-09-28 | IFA | OL1-2G30-2852 | PE | 2018-09-28 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | 2018-10-01 | 1
036909C-1025-PDS-0500-2510 | Process Equipment Datasheet - 10-T-2510 and 10-D-2510 - Demethanizer Prefractionator & Reflux Drum | A | 2018-09-26 | IFA | OL1-2G30-2510 | PE | 2018-09-26 | 036909C-JVD-TRN-00092 | 036909C-JVD-TRN-00092 | IFA | 2018-10-09 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00092 |  | 2018-09-25 | 1
036909C-1028-PDS-0600-2806 | Process Equipment Datasheet - 10-E-2805 - C3 Refrig Condensers | A | 2018-09-28 | IFA | OL1-2G30-2806 | PE | 2018-09-28 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00113 |  | 2018-10-01 | 1
036909C-1023-PDS-0800-2392 | Process Equipment Datasheet - 10-D-2392 Spent Caustic Drain Drum | A | 2018-09-27 | IFA | OL1-2G30-2392 | PE | 2018-09-27 | 036909C-JVD-TRN-00102 | 036909C-JVD-TRN-00102 | IFA | 2018-10-11 | 2018-11-14 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00102 |  | 2018-09-28 | 1
036909C-1012-PDS-1040-2011 | See document number 036909C-1012-PDS-1040-1211 or OL1-2G30-1211 | A | 2018-09-25 | IFR | OL1-4G30-2011 | PE | 2018-09-26 | 036909C-JVD-TRN-00090 | 036909C-JVD-TRN-00090 | IFR | 2018-10-10 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00090 |  | 2018-09-27 | 2
036909C-1026-PDS-0600-2661 | Process Equipment Datasheet - 10-E-2660 - Debutanizer Condenser | A | 2018-09-26 | IFA | OL1-2G30-2661 | PE | 2018-09-26 | 036909C-JVD-TRN-00094 | 036909C-JVD-TRN-00094 | IFA | 2018-10-10 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00094 |  | 2018-09-27 | 1
036909C-1025-PDS-1000-2550 | Process Equipment Datasheet - 10-TX-2550 - 10-C-2550 - Residue Gas Expander - Recompressor | B | 2018-09-28 | IFD | OL1-2G30-2550 | PE | 2018-09-28 | 036909C-JVD-TRN-00114 | 036909C-JVD-TRN-00114 | IFI |  | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-PE-00114 |  | 2018-10-01 | 3
036909C-1000-NM-0001-1011 | Heat & Material Balance - Cooling Water System | A | 2018-09-28 | IFI | OL1-2G44-1011 | PE | 2018-10-01 | 036909C-JVD-TRN-00116 | 036909C-JVD-TRN-00116, ROC-TPSK-CECO-T-00012 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00116 |  | 2018-10-02 | 3
036909C-1012-PDS-0117-2001 | See document number 036909C-1012-PDS-0117-1201 or OL1-2G30-1201 | A | 2018-09-28 | IFR | OL1-4G30-2001 | PE | 2018-10-01 | 036909C-JVD-TRN-00117 | 036909C-JVD-TRN-00117 | IFR | 2018-10-15 |  | Transmitted | TPSK-LSPA1-T-PE-00117 |  | 2018-10-01 | 2
036909C-1000-PP-908 | Instructions To Supplier For Filling-Up Of Spare Parts And Interchangeability Record (SPIR Form) | A | 2018-09-24 | IFR | OL1-2O92-0001 | PE | 2018-09-27 | 036909C-JVD-TRN-00095 | 036909C-JVD-TRN-00095 | IFR | 2018-10-11 |  | Transmitted | TPSK-LSPA1-T-PE-00095 |  | 2018-09-27 | 2
036909C-1019-PDS-1000-1950 | Process Equipment Datasheet - 10-PK-1950 - Decoke Air Compressor Pkg | B | 2018-09-28 | IFD | OL1-2G30-1950 | PE | 2018-09-28 | 036909C-JVD-TRN-00114 | 036909C-JVD-TRN-00114 | IFI |  | 2018-10-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00114 |  | 2018-10-01 | 3
036909C-1028-PDS-0600-2807 | Process Equipment Datasheet - 10-E-2807 - C3 Chiller No 1 | A | 2018-09-28 | IFA | OL1-2G30-2807 | PE | 2018-09-28 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | 2018-10-01 | 1
036909C-1028-PDS-0600-2853 | Process Equipment Datasheet - 10-E-2853 - C2R Desuperheater No 2 | A | 2018-09-28 | IFA | OL1-2G30-2853 | PE | 2018-09-28 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | 2018-10-01 | 1
036909C-1026-PDS-0600-2666 | Process Equipment Datasheet - 10-E-2666 - Debutanizer Bottoms Cooler | A | 2018-09-27 | IFA | OL1-2G30-2666 | PE | 2018-09-28 | 036909C-JVD-TRN-00112 | 036909C-JVD-TRN-00112 | IFA | 2018-10-12 | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00112 |  | 2018-09-28 | 1
036909C-1023-PDS-0800-2322 | Process Equipment Datasheet - 10-D-2322 - Skim Oil Drum | A | 2018-09-27 | IFA | OL1-2G30-2322 | PE | 2018-09-28 | 036909C-JVD-TRN-00111 | 036909C-JVD-TRN-00111 | IFA | 2018-10-12 | 2019-02-25 | A1-Approved without comments | TPSK-LSPA1-T-PE-00111 |  | 2018-09-28 | 1
036909C-1023-PDS-0800-2309 | Process Equipment Datasheet - 10-D-2305 - Yellow Oil Drum | A | 2018-09-27 | IFA | OL1-2G30-2309 | PE | 2018-09-27 | 036909C-JVD-TRN-00102 | 036909C-JVD-TRN-00102 | IFA | 2018-10-11 | 2018-11-14 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00102 |  | 2018-09-28 | 1
036909C-1023-PDS-0800-2390 | Process Equipment Datasheet - 10-D-2390 - Caustic Drain Drum | A | 2018-09-27 | IFA | OL1-2G30-2390 | PE | 2018-09-27 | 036909C-JVD-TRN-00102 | 036909C-JVD-TRN-00102 | IFA | 2018-10-11 | 2018-11-14 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00102 |  | 2018-09-28 | 1
036909C-1011-PDS-0117-1001 | See document number 036909C-1011-PDS-0117-1101 or OL1-2G30-1101 | A | 2018-09-28 | IFR | OL1-4G30-1001 | PE | 2018-10-01 | 036909C-JVD-TRN-00117 | 036909C-JVD-TRN-00117 | IFR | 2018-10-15 |  | Transmitted | TPSK-LSPA1-T-PE-00117 |  | 2018-10-01 | 2
036909C-1026-PDS-0600-2665 | Process Equipment Datasheet - 10-E-2665 A-B - Debutanizer Reboilers | A | 2018-09-27 | IFA | OL1-2G30-2665 | PE | 2018-09-27 | 036909C-JVD-TRN-00101 | 036909C-JVD-TRN-00101 | IFA | 2018-10-11 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00101 |  | 2018-09-28 | 1
036909C-1000-DW-1402-0001 | General Notes For Underground Works | A | 2018-09-18 | IFR | OL1-2K92-0001 | CV | 2018-09-25 | 036909C-JVD-TRN-00086 | 036909C-JVD-TRN-00086 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00086 |  | 2018-09-27 | 2
036909C-1000-DW-1702-0001 | General Notes For Concrete Works | A | 2018-09-19 | IFR | OL1-2K92-0003 | CV | 2018-09-25 | 036909C-JVD-TRN-00086 | 036909C-JVD-TRN-00086 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00086 |  | 2018-09-27 | 2
036909C-1000-STC-0490-000 | Construction Standards For Pressure Equipment | B | 2018-09-20 | IFR | OL1-2R03-0054 | ME | 2018-09-25 | 036909C-JVD-TRN-00085 | 036909C-JVD-TRN-00085 | IFR | 2018-10-09 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-ME-00084 |  | 2018-09-27 | 2
036909C-1011-PDS-1040-1011 | See document number 036909C-1011-PDS-1040-1111 or OL1-2G30-1111 | A | 2018-09-25 | IFR | OL1-4G30-1011 | PE | 2018-09-26 | 036909C-JVD-TRN-00090 | 036909C-JVD-TRN-00090 | IFR | 2018-10-10 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00090 |  | 2018-09-27 | 2
036909C-1000-STC-1790-0001 | Construction Standards for Reinforced Concrete Works | A | 2018-09-19 | IFR | OL1-2K20-0001 | CV | 2018-09-25 | 036909C-JVD-TRN-00088 | 036909C-JVD-TRN-00088 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00088 |  | 2018-09-27 | 2
036909C-1000-JSD-1700-0001 | Job Design Specification For Foundations And Structures | A | 2018-09-19 | IFR | OL1-2R02-0004 | CV | 2018-09-25 | 036909C-JVD-TRN-00087 | 036909C-JVD-TRN-00087 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00087 |  | 2018-09-27 | 2
036909C-1000-STC-1890-0001 | Construction Standards For Steel Structures | A | 2018-09-19 | IFR | OL1-2K21-0001 | CV | 2018-09-25 | 036909C-JVD-TRN-00088 | 036909C-JVD-TRN-00088 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00088 |  | 2018-09-27 | 2
036909C-1000-JSD-1400-0001 | Job Design Specification For Underground Systems | A | 2018-09-18 | IFR | OL1-2R02-0001 | CV | 2018-09-25 | 036909C-JVD-TRN-00087 | 036909C-JVD-TRN-00087 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00087 |  | 2018-09-27 | 2
036909C-1000-STC-1490-0001 | Standard Construction Drawings For Underground Systems - For Next Revision See Document OL1-2K24-0001 | A | 2018-09-18 | IFR | OL1-2K24-0001 | CV | 2018-09-25 | 036909C-JVD-TRN-00088 | 036909C-JVD-TRN-00088 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00088 | For Next Revision See Document OL1-2K24-0001 | 2018-09-27 | 2
036909C-1000-JSS-0400-01 | Job Specification For Supply Of Pressure Vessels | B | 2018-09-20 | IFR | OL1-2R03-0051 | ME | 2018-09-25 | 036909C-JVD-TRN-00084 | 036909C-JVD-TRN-00084 | IFR | 2018-10-09 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-ME-00084 |  | 2018-09-27 | 2
036909C-1053-PDS-0300-5355 | Process Equipment Data Sheet - 10-PK-5355 - Side Stream Filter Package | A | 2018-09-24 | IFA | OL1-2G30-5355 | PE | 2018-09-25 | 036909C-JVD-TRN-00082 | 036909C-JVD-TRN-00082 | IFA | 2018-10-09 | 2018-10-13 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00082 |  | 2018-09-25 | 1
036909C-1053-PDS-0300-5350 | Process Equipment Data Sheet - 10-PK-5350 - Cooling Tower | A | 2018-09-24 | IFA | OL1-2G30-5350 | PE | 2018-09-25 | 036909C-JVD-TRN-00082 | 036909C-JVD-TRN-00082 | IFA | 2018-10-09 | 2018-10-13 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00082 |  | 2018-09-25 | 1
036909C-1000-DW-1802-0001 | General Notes For Steel Structures | A | 2018-09-19 | IFR | OL1-2K92-0004 | CV | 2018-09-25 | 036909C-JVD-TRN-00086 | 036909C-JVD-TRN-00086 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00086 |  | 2018-09-27 | 2
036909C-1025-PDS-0500-2540 | Process Equipment Datasheet - 10-T-2540 and 10-D-2540 - Demethanizer and Reflux Drum | A | 2018-09-20 | IFA | OL1-2G30-2540 | PE | 2018-09-24 | 036909C-JVD-TRN-00073 | 036909C-JVD-TRN-00073 | IFA | 2018-10-08 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00073 |  | 2018-09-25 | 1
036909C-1000-JSD-0400-01 | Job Specification For Design Of Pressure & Atmospheric Static Equipment | B | 2018-09-20 | IFR | OL1-2R03-0050 | ME | 2018-09-25 | 036909C-JVD-TRN-00084 | 036909C-JVD-TRN-00084 | IFR | 2018-10-09 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-ME-00084 |  | 2018-09-27 | 2
036909C-1026-PDS-0600-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler | A | 2018-09-20 | IFA | OL1-2G30-2635 | PE | 2018-09-24 | 036909C-JVD-TRN-00074 | 036909C-JVD-TRN-00074 | IFA | 2018-10-08 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00074 |  | 2018-09-25 | 1
036909C-1026-PDS-0600-2636 | Process Equipment Datasheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | A | 2018-09-20 | IFA | OL1-2G30-2636 | PE | 2018-09-24 | 036909C-JVD-TRN-00074 | 036909C-JVD-TRN-00074 | IFA | 2018-10-08 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00074 |  | 2018-09-25 | 1
036909C-1053-PDS-0900-5361 | Process Equipment Data Sheet - 10-P-5360 A-C - CTU Cooling Water Pumps | A | 2018-09-20 | IFA | OL1-2G30-5361 | PE | 2018-09-24 | 036909C-JVD-TRN-00075 | 036909C-JVD-TRN-00075 | IFA | 2018-10-08 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00075 |  | 2018-09-25 | 1
036909C-1053-PDS-0900-5352 | Process Equipment Data Sheet - 10-P-5350 A-H - Olefins Cooling Water Pumps | A | 2018-09-20 | IFA | OL1-2G30-5352 | PE | 2018-09-24 | 036909C-JVD-TRN-00075 | 036909C-JVD-TRN-00075 | IFA | 2018-10-08 | 2019-04-22 | A1-Approved without comments | TPSK-LSPA1-T-PE-00075 |  | 2018-09-25 | 1
036909C-1000-JSS-1111-0001 | ME-018 General Purpose Steam Turbines | A | 2018-09-20 | IFR | OL1-2R03-0018 | ME | 2018-09-24 | 036909C-JVD-TRN-00078 | 036909C-JVD-TRN-00078 | IFR | 2018-10-08 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-ME-00078 |  | 2018-09-25 | 2
036909C-1000-JSS-0910-0001 | ME-010 Centrifugal Pump | A | 2018-09-20 | IFR | OL1-2R03-0010 | ME | 2018-09-24 | 036909C-JVD-TRN-00078 | 036909C-JVD-TRN-00078 | IFR | 2018-10-08 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-ME-00078 |  | 2018-09-25 | 2
036909C-1026-PDS-0600-2631 | Process Equipment Datasheet - 10-E-2630 - Secondary Deeth Condenser | A | 2018-09-20 | IFA | OL1-2G30-2631 | PE | 2018-09-24 | 036909C-JVD-TRN-00074 | 036909C-JVD-TRN-00074 | IFA | 2018-10-08 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00074 |  | 2018-09-25 | 1
036909C-1023-PDS-0500-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper | A | 2018-09-20 | IFA | OL1-2G30-2330 | PE | 2018-09-24 | 036909C-JVD-TRN-00073 | 036909C-JVD-TRN-00073 | IFA | 2018-10-08 | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00073 |  | 2018-09-25 | 1
036909C-1000-JSS-1112-0001 | ME-020 Special Purpose Steam Tturbines | A | 2018-09-20 | IFR | OL1-2R03-0020 | ME | 2018-09-24 | 036909C-JVD-TRN-00078 | 036909C-JVD-TRN-00078 | IFR | 2018-10-08 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-ME-00078 |  | 2018-09-25 | 2
036909C-1012-JSS-0154-2008 | Project Specification For Transfer Line Exchangers - For next Rev. see Doc. Client Ref. OL1-2M92-2008 | A | 2018-09-20 | IFR | OL1-2M92-2008 | ME | 2018-09-20 | 036909C-JVD-TRN-00067 | 036909C-JVD-TRN-00067 | IFR | 2018-10-04 | 2018-10-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00067 | For next Rev. see Doc. Client Ref. OL1-2M92-2008 | 2018-09-24 | 2
036909C-1023-PDS-2500-2320 | Process Equipment Data Sheet - 10-TK-2320 - Spent Caustic Storage Tank | A | 2018-09-20 | IFA | OL1-2G30-2320 | PE | 2018-09-20 | 036909C-JVD-TRN-00068 | 036909C-JVD-TRN-00068 | IFA | 2018-10-04 | 2018-10-09 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00068 |  | 2018-09-24 | 1
036909C-1012-JSS-0154-2007 | Project Specification For SLE and USX Exchangers - For next Rev. see Doc. Client Ref. OL1-2M92-2007 | A | 2018-09-20 | IFR | OL1-2M92-2007 | ME | 2018-09-20 | 036909C-JVD-TRN-00067 | 036909C-JVD-TRN-00067 | IFR | 2018-10-04 | 2018-10-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00067 | For next Rev. see Doc. Client Ref. OL1-2M92-2007 | 2018-09-24 | 2
036909C-1020-PDS-0900-2006 | Process Equipment Datasheet - 10-P-2006 A-C - Quench Oil Pumps | A | 2018-09-20 | IFA | OL1-2G30-2006 | PE | 2018-09-20 | 036909C-JVD-TRN-00071 | 036909C-JVD-TRN-00071 | IFA | 2018-10-04 | 2018-10-09 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00071 |  | 2018-09-24 | 1
036909C-1021-PDS-0900-2146 | Process Equipment Datasheet 10-P-2146 DSG Feed Pumps | A | 2018-09-20 | IFA | OL1-2G30-2146 | PE | 2018-09-20 | 036909C-JVD-TRN-00069 | 036909C-JVD-TRN-00069 | IFA | 2018-10-04 | 2018-10-09 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00069 |  | 2018-09-24 | 1
036909C-1021-PDS-0900-2106 | Process Equipment Datasheet - 10-P-2106 A-C - Quench Water Pumps | A | 2018-09-20 | IFA | OL1-2G30-2106 | PE | 2018-09-20 | 036909C-JVD-TRN-00070 | 036909C-JVD-TRN-00070 | IFA | 2018-10-04 | 2018-10-09 | A1-Approved without comments | TPSK-LSPA1-T-PE-00070 |  | 2018-09-24 | 1
036909C-1011-DW-0122-1202 | USC 36M Recycle Furnace Transfer Line and Clean-Out Details | A | 2018-09-11 | IFR | OL1-2M06-1202 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00062 |  | 2018-10-08 | 2
036909C-1000-JSS-1061-0001 | ME-019 Lube Oil Unit And Seal Oil System | A | 2018-09-18 | IFR | OL1-2R03-0019 | ME | 2018-09-18 | 036909C-JVD-TRN-00065 | 036909C-JVD-TRN-00065 | IFR | 2018-10-03 | 2018-10-10 | R1-No comments | TPSK-LSPA1-T-ME-00065 |  | 2018-10-19 | 2
036909C-1012-DW-0122-2202 | USC 132U Cracking Furnace Transfer Lines and Clean-Out Details | A | 2018-09-11 | IFR | OL1-2M06-2202 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00062 |  | 2018-10-08 | 2
036909C-1012-MR-0122-2004 | Material Requisition for Radiant Coil Assemblies | A | 2018-09-12 | IFQ | OL1-2M55-2004 | ME | 2018-09-18 | 036909C-JVD-TRN-00063 | 036909C-JVD-TRN-00063 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00063 |  | 2018-10-18 | 3
036909C-1012-DW-0122-2201 | USC 132U Furnace Radiant Coil Assembly and Details | A | 2018-09-11 | IFR | OL1-2M06-2201 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00062 |  | 2018-10-08 | 2
036909C-1012-PDS-0630-2008 | See document number 036909C-1012-PDS-0630-1208 or OL1-2G30-1208 | A | 2018-09-17 | IFR | OL1-4G30-2008 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066 |  | 2018-09-19 | 2
036909C-1012-PDS-0610-2009 | See document number 036909C-1012-PDS-0610-1209 or OL1-2G30-1209 | A | 2018-09-17 | IFR | OL1-4G30-2009 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066 |  | 2018-09-19 | 2
036909C-1011-PDS-0610-1010 | See document number 036909C-1011-PDS-0610-1110 or OL1-2G30-1110 | A | 2018-09-17 | IFR | OL1-4G30-1010 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066, ROC-TPSK-CECO-T-00019 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066 |  | 2018-09-19 | 2
036909C-1000-JSS-1011-0001 | ME-014 Centrifugal Compressor | A | 2018-09-18 | IFR | OL1-2R03-0014 | ME | 2018-09-18 | 036909C-JVD-TRN-00065 | 036909C-JVD-TRN-00065 | IFR | 2018-10-03 | 2018-10-10 | R1-No comments | TPSK-LSPA1-T-ME-00065 |  | 2018-10-19 | 2
036909C-1011-PDS-0630-1008 | See document number 036909C-1011-PDS-0630-1108 or OL1-2G30-1108 | A | 2018-09-17 | IFR | OL1-4G30-1008 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066, ROC-TPSK-CECO-T-00019 | IFR |  | 2019-02-11 | R1-No comments | TPSK-LSPA1-T-PE-00066 |  | 2018-09-19 | 2
036909C-1011-PDS-0610-1009 | See document number 036909C-1011-PDS-0610-1109 or OL1-2G30-1109 | A | 2018-09-17 | IFR | OL1-4G30-1009 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066, ROC-TPSK-CECO-T-00019 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066 |  | 2018-09-19 | 2
036909C-1012-SR-0122-2004 | Scope of Supply for Radiant Coil Assemblies | A | 2018-09-10 | IFQ | OL1-2M56-2004 | ME | 2018-09-18 | 036909C-JVD-TRN-00063 | 036909C-JVD-TRN-00063 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00063 |  | 2018-10-18 | 3
036909C-1022-PDS-1000-2200 | Process Equipment Data Sheet - 10-C-2200 - Cracked Gas Compressor | B | 2018-09-14 | IFD | OL1-2G30-2200 | PE | 2018-09-17 | 036909C-JVD-TRN-00055 | 036909C-JVD-TRN-00055 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00055 |  | 2018-09-18 | 3
036909C-1023-PDS-0500-2300 | Process Equipment Data Sheet - 10-T-2300 - Caustic Tower | A | 2018-09-17 | IFA | OL1-2G30-2300 | PE | 2018-09-18 | 036909C-JVD-TRN-00060 | 036909C-JVD-TRN-00060 | IFA | 2018-10-02 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00060 |  | 2018-09-19 | 1
036909C-1011-DW-0122-1203 | USC 36M Recycle Furnace Radiant Coil Tubeskin Thermocouple Details | A | 2018-09-11 | IFR | OL1-2M06-1203 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 | 2019-02-21 | R1-No comments | TPSK-LSPA1-T-ME-00062 |  | 2018-10-08 | 2
036909C-1011-DW-0122-1201 | USC 36M Recycle Furnace Radiant Coil Assembly and Details | A | 2018-09-11 | IFR | OL1-2M06-1201 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-21 | 2019-02-21 | R2-Comments as noted | TPSK-LSPA1-T-ME-00062 |  | 2018-10-08 | 2
036909C-1026-PDS-0500-2630 | Process Equipment Data Sheet - 10-T-2630 - Secondary Deethanizer | A | 2018-09-13 | IFA | OL1-2G30-2630 | PE | 2018-09-14 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | 2018-09-17 | 1
036909C-1026-PDS-0500-2660 | Process Equipment Data Sheet - 10-T-2660 - Debutanizer | A | 2018-09-13 | IFA | OL1-2G30-2660 | PE | 2018-09-14 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | 2018-09-17 | 1
036909C-1028-PDS-1000-2800 | Process Equipment Data Sheet - 10-C-2800 - Propylene Refrig Compressor | B | 2018-09-14 | IFD | OL1-2G30-2800 | PE | 2018-09-17 | 036909C-JVD-TRN-00055 | 036909C-JVD-TRN-00055 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00055 |  | 2018-09-18 | 3
036909C-1021-TDS-0661-2101 | Mechanical Data Sheet - 10-E-2100 - Quench Water Cooler | A | 2018-09-14 | IFA | OL1-2M03-2101 | ME | 2018-09-17 | 036909C-JVD-TRN-00058 | 036909C-JVD-TRN-00058 | IFA | 2018-10-01 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00058 |  | 2018-09-18 | 1
036909C-1000-NM-0003-1001 | Steam Balance | A | 2018-09-17 | IFI | OL1-2G62-1001 | PE | 2018-09-17 | 036909C-JVD-TRN-00059 | 036909C-JVD-TRN-00059, ROC-TPSK-CECO-T-00012 | IFI | 2018-10-01 | 2018-10-04 | Transmitted | TPSK-LSPA1-T-PE-00059 |  | 2018-09-18 | 3
036909C-1000-JSD-1580-0003 | General Design Rules For Instrumentation And Control Of Packaged Equipment | A | 2018-09-14 | IFR | OL1-2R06-0035 | IE | 2018-09-17 | 036909C-JVD-TRN-00056 | 036909C-JVD-TRN-00056 | IFR | 2018-10-01 | 2018-10-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-00056 |  | 2018-09-18 | 2
036909C-1028-PDS-1000-2850 | Process Equipment Data Sheet - 10-C-2850 - Ethylene Refrig Compressor | B | 2018-09-14 | IFD | OL1-2G30-2850 | PE | 2018-09-17 | 036909C-JVD-TRN-00055 | 036909C-JVD-TRN-00055 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00055 |  | 2018-09-18 | 3
036909C-1000-JSS-0660-01 | Plate Heat Exchanger | 0 | 2018-09-10 | IMP | OL1-2R03-0006 | ME | 2018-09-12 | 036909C-JVD-TRN-00042 | 036909C-JVD-TRN-00042, ROC-TPSK-CECO-T-00003 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00042 |  | 2018-09-13 | 3
036909C-1012-SR-0127-2001 | Material Requisition Scope of Supply for Convection Tubes | A | 2018-09-06 | IFQ | OL1-4M56-2001 | ME | 2018-09-12 | 036909C-JVD-TRN-00044 | 036909C-JVD-TRN-00044 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00044 |  | 2018-09-13 | 3
036909C-1012-MR-0127-2001 | Material Requisition for Convection Tubes | A | 2018-09-06 | IFQ | OL1-4M55-2001 | ME | 2018-09-12 | 036909C-JVD-TRN-00044 | 036909C-JVD-TRN-00044 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00044 |  | 2018-09-13 | 3
036909C-1000-NM-0003-1008 | Fuel Balance | A | 2018-09-12 | IFI | OL1-2G62-1008 | PE | 2018-09-13 | 036909C-JVD-TRN-00049 | 036909C-JVD-TRN-00049, ROC-TPSK-CECO-T-00012 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00049 |  | 2018-09-14 | 3
036909C-1012-TEN-0127-2001 | See document number 036909C-1012-SP-0127-2001 or OL1-2M57-2001 | A | 2018-09-06 | IFQ | OL1-4M57-2001 | ME | 2018-09-12 | 036909C-JVD-TRN-00044 | 036909C-JVD-TRN-00044 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00044 |  | 2018-09-13 | 3
036909C-1025-SP-1011-2550 | Mechanical Equipment Datasheet for Residue Gas Expander-Recompressor | A | 2018-09-13 | IFA | OL1-2M03-2550 | ME | 2018-09-13 | 036909C-JVD-TRN-00050 | 036909C-JVD-TRN-00050 | IFA | 2018-09-27 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00050 |  | 2018-09-14 | 1
036909C-1024-PDS-0500-2440 | Process Equipment Data Sheet - 10-T-2440 - HP Depropanizer | A | 2018-09-13 | IFA | OL1-2G30-2440 | PE | 2018-09-14 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | 2018-09-17 | 1
036909C-1012-JSS-0000-9999 | General Supply Rules for Supplier Documentation | A | 2018-09-12 | IFI | OL1-2C93-0001 | PL | 2018-09-12 | 036909C-JVD-TRN-00043 | 036909C-JVD-TRN-00043 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00043 |  | 2018-09-19 | 3
036909C-1019-SP-1013-1950 | Mechanical Equipment Datasheet for Decoking Air Compressor Package | A | 2018-09-13 | IFA | OL1-2M03-1950 | ME | 2018-09-13 | 036909C-JVD-TRN-00050 | 036909C-JVD-TRN-00050 | IFA | 2018-09-27 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00050 |  | 2018-09-14 | 1
036909C-1024-PDS-0500-2450 | Process Equipment Data Sheet - 10-T-2450 - LP Depropanizer | A | 2018-09-13 | IFA | OL1-2G30-2450 | PE | 2018-09-14 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | 2018-09-17 | 1
036909C-1028-PDS-0600-2856 | Process Equipment Data Sheet - 10-E-2855 - C2R Condenser | A | 2018-09-10 | IFA | OL1-2G30-2856 | PE | 2018-09-11 | 036909C-JVD-TRN-00039 | 036909C-JVD-TRN-00039 | IFA | 2018-09-25 | 2018-09-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00039 |  | 2018-09-12 | 1
036909C-1000-PP-830 | Employee Grievance Management Plan | 0 | 2018-09-12 | IFI | OL1-2J92-0002 | HR | 2018-09-12 | 036909C-JVD-TRN-00040 | 036909C-JVD-TRN-00040 | IFI |  |  | Transmitted | TPSK-LSPA1-T-HR-00040 |  | 2018-09-12 | 3
036909C-1022-SP-1011-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor | A | 2018-09-06 | IFA | OL1-2M03-2200 | ME | 2018-09-10 | 036909C-JVD-TRN-00038 | 036909C-JVD-TRN-00038 | IFA | 2018-09-24 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00038 |  | 2018-09-11 | 1
036909C-1025-PDS-0600-2500 | Process Equipment Data Sheet - 10-E-2500 - Propylene Refrig Subcooler | A | 2018-09-10 | IFA | OL1-2G30-2500 | PE | 2018-09-11 | 036909C-JVD-TRN-00039 | 036909C-JVD-TRN-00039 | IFA | 2018-09-25 | 2018-09-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00039 |  | 2018-09-12 | 1
036909C-1012-JSS-0122-2001 | Project Specification for Centrifugally Cast Tubes for Radiant Coils and Transfer Lines in Cracking Furnaces - For next Rev. see Doc. Client Ref. OL1-2M92-2001 | A | 2018-09-10 | IFR | OL1-2M92-2001 | ME | 2018-09-10 | 036909C-JVD-TRN-00037 | 036909C-JVD-TRN-00037 | IFR | 2018-09-24 | 2018-09-25 | R2-Comments as noted | TPSK-LSPA1-T-ME-00037 | For next Rev. see Doc. Client Ref. OL1-2M92-2001 | 2018-09-11 | 2
036909C-1028-SP-1011-2800 | Mechanical Equipment Data Sheet for Propylene Refrigeration Compressor | A | 2018-09-06 | IFA | OL1-2M03-2800 | ME | 2018-09-10 | 036909C-JVD-TRN-00038 | 036909C-JVD-TRN-00038 | IFA | 2018-09-24 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00038 |  | 2018-09-11 | 1
036909C-1012-JSS-0122-2002 | Project Specification for Statically Cast Fittings for Radiant Coils and Transfer Lines in Cracking Furnaces - For Next Revision See Document OL1-2M92-2002 | A | 2018-09-10 | IFR | OL1-2M92-2002 | ME | 2018-09-10 | 036909C-JVD-TRN-00037 | 036909C-JVD-TRN-00037 | IFR | 2018-09-24 | 2018-09-25 | R2-Comments as noted | TPSK-LSPA1-T-ME-00037 | For Next Revision See Document OL1-2M92-2002 | 2018-09-11 | 2
036909C-1025-PDS-0600-2587 | Process Equipment Data Sheet - 10-E-2587 - C2 Tower Side Reboiler | A | 2018-09-06 | IFA | OL1-2G30-2587 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11 | 1
036909C-1028-PDS-0600-2857 | Process Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer | A | 2018-09-11 | IFA | OL1-2G30-2857 | PE | 2018-09-12 | 036909C-JVD-TRN-00041 | 036909C-JVD-TRN-00041 | IFA | 2018-09-26 | 2018-10-01 | A1-Approved without comments | TPSK-LSPA1-T-PE-00041 |  | 2018-09-12 | 1
036909C-1026-PDS-0600-2645 | Process Equipment Data Sheet - 10-E-2645 - C3 Tower Reboilers | A | 2018-09-11 | IFA | OL1-2G30-2645 | PE | 2018-09-12 | 036909C-JVD-TRN-00041 | 036909C-JVD-TRN-00041 | IFA | 2018-09-26 | 2018-10-01 | A1-Approved without comments | TPSK-LSPA1-T-PE-00041 |  | 2018-09-12 | 1
036909C-1019-PDS-1000-1950 | Process Equipment Data Sheet - 10-PK-1950 - Decoke Air Compressor Package | A | 2018-08-29 | IFA | OL1-2G30-1950 | PE | 2018-08-29 | 036909C-JVD-TRN-00031 | 036909C-JVD-TRN-00031 | IFA |  | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00031 |  | 2018-09-03 | 1
036909C-1025-PDS-0600-2531 | Process Equipment Data Sheet - 10-E-2530 - Demeth Feed Cooler | A | 2018-09-06 | IFA | OL1-2G30-2531 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11 | 1
036909C-1028-SP-1011-2850 | Mechanical Equipment Data Sheet for Ethylene Refrigeration Compressor | A | 2018-09-06 | IFA | OL1-2M03-2850 | ME | 2018-09-10 | 036909C-JVD-TRN-00038 | 036909C-JVD-TRN-00038 | IFA | 2018-09-24 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00038 |  | 2018-09-11 | 1
036909C-1025-PDS-0600-2585 | Process Equipment Data Sheet - 10-E-2585 - C2 Tower Bottoms Reboiler | A | 2018-09-06 | IFA | OL1-2G30-2585 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11 | 1
036909C-1000-DI-0007-0003 | Flare and Blowdown System Design Basis | A | 2018-09-06 | IFA | OL1-2G02-0003 | PE | 2018-09-06 | 036909C-JVD-TRN-00034 | 036909C-JVD-TRN-00034, ROC-TPSK-CECO-T-00001 | IFA | 2018-09-20 | 2018-09-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-00034 |  | 2018-09-07 | 1
036909C-1025-PDS-0600-2541 | Process Equipment Data Sheet - 10-E-2540 - Demethanizer Condenser | A | 2018-09-06 | IFA | OL1-2G30-2541 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11 | 1
036909C-1025-PDS-0600-2502 | Process Equipment Data Sheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | A | 2018-09-07 | IFA | OL1-2G30-2502 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11 | 1
036909C-1025-PDS-0600-2505 | Process Equipment Data Sheet - 10-E-2506 & 2508 - Demeth Prefrac Feed Cooler No 3 & No 4 | A | 2018-09-06 | IFA | OL1-2G30-2505 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11 | 1
036909C-1025-PDS-0600-2521 | Process Equipment Data Sheet - 10-E-2520 - Rectifier Condenser | A | 2018-09-06 | IFA | OL1-2G30-2521 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11 | 1
036909C-1025-PDS-0600-2511 | Process Equipment Data Sheet - 10-E-2510 - Demeth Prefrac Condenser | A | 2018-09-06 | IFA | OL1-2G30-2511 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11 | 1
036909C-1025-PDS-0600-2503 | Process Equipment Data Sheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | A | 2018-09-07 | IFA | OL1-2G30-2503 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11 | 1
036909C-1025-PDS-1000-2550 | Process Equipment Data Sheet - 10-C-TX-2550 - Residue Gas Expander - Recompressor | A | 2018-08-29 | IFA | OL1-2G30-2550 | PE | 2018-08-29 | 036909C-JVD-TRN-00031 | 036909C-JVD-TRN-00031 | IFA |  | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00031 |  | 2018-09-03 | 1
036909C-1021-PDS-0600-2101 | Process Equipment Data Sheet - 10-E-2100 - Quench Water Cooler | A | 2018-09-07 | IFA | OL1-2G30-2101 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11 | 1
036909C-1025-PDS-0600-2526 | Process Equipment Data Sheet - 10-E-2525 - Hydrogen Core Exchanger | A | 2018-09-06 | IFA | OL1-2G30-2526 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11 | 1
036909C-1028-PDS-0600-2884 | Process Equipment Data Sheet - 10-E-2884 - LP Ethylene Product Cooler No 2 | A | 2018-09-06 | IFA | OL1-2G30-2884 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11 | 1
036909C-1025-PDS-0600-2571 | Process Equipment Data Sheet - 10-E-2570 Deethanizer Condenser | A | 2018-09-07 | IFA | OL1-2G30-2571 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11 | 1
036909C-1028-PDS-0600-2882 | Process Equipment Data Sheet - 10-E-2882 - LP Ethylene Product Cooler No 1 | A | 2018-09-06 | IFA | OL1-2G30-2882 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | 2018-09-11 | 1
036909C-1028-PDS-1000-2850 | Process Equipment Data Sheet - 10-C-2850 - Ethylene Refrig Compressor | A | 2018-08-22 | IFA | OL1-2G30-2850 | PE | 2018-08-22 | 036909C-JVD-TRN-00025 | 036909C-JVD-TRN-00025 | IFA | 2018-09-05 | 2018-09-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00025 |  | 2018-08-23 | 1
036909C-1028-DI-0007-2801 | Area Basis of Design - 28 Refrigeration | A | 2018-08-09 | IFA | OL1-2G05-2801 | PE | 2018-08-13 | 036909C-JVD-TRN-00022 | 036909C-JVD-TRN-00022, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-27 | 2018-09-05 | A1-Approved without comments | TPSK-LSPA1-T-PE-00022 |  | 2018-08-15 | 1
036909C-1022-DI-0007-2201 | Area Basis of Design - 22-24 Compresssion Train | A | 2018-08-09 | IFA | OL1-2G05-2201 | PE | 2018-08-13 | 036909C-JVD-TRN-00022 | 036909C-JVD-TRN-00022, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-27 | 2018-09-05 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00022 |  | 2018-08-15 | 1
036909C-1028-PDS-1000-2800 | Process Equipment Data Sheet - 10-C-2800 - Propylene Refrig Compressor | A | 2018-08-22 | IFA | OL1-2G30-2800 | PE | 2018-08-22 | 036909C-JVD-TRN-00025 | 036909C-JVD-TRN-00025 | IFA | 2018-09-05 | 2018-09-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00025 |  | 2018-08-23 | 1
036909C-1022-PDS-1000-2200 | Process Equipment Data Sheet - 10-C-2200 - Cracked Gas Compressor | A | 2018-08-22 | IFA | OL1-2G30-2200 | PE | 2018-08-22 | 036909C-JVD-TRN-00025 | 036909C-JVD-TRN-00025 | IFA | 2018-09-05 | 2018-09-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00025 |  | 2018-08-23 | 1
036909C-1020-DI-0007-2001 | Area Basis of Design - 20-21 Quench and Dilution Steam | A | 2018-08-06 | IFA | OL1-2G05-2001 | PE | 2018-08-07 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | 2018-08-08 | 1
036909C-1025-DI-0007-2501 | Area Basis of Design - 25 Cold Fractionation | A | 2018-08-06 | IFA | OL1-2G05-2501 | PE | 2018-08-07 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | 2018-08-08 | 1
036909C-1010-DI-0007-1001 | Area Basis of Design - 10 Feed Preparation | A | 2018-08-06 | IFA | OL1-2G05-1001 | PE | 2018-08-07 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011, ROC-TPSK-CECO-T-00001 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | 2018-08-08 | 1
036909C-1000-DI-0007-0006 | Furnace Process Basis of Design | A | 2018-07-26 | IFA | OL1-2G02-0006 | PE | 2018-07-31 | 036909C-JVD-TRN-00004 | 036909C-JVD-TRN-00004 | IFA | 2018-08-13 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00004 |  | 2018-07-31 | 1
036909C-1012-MR-1554-1257 | Material Requisition for Temperature Elements for Thermocouples & RTDs with Wells | A | 2019-09-05 | IFQ | OL1-2C17-032257 | PL | 2019-09-11 | 036909C-JVD-TRN-02630 | 036909C-JVD-TRN-02630 | IFR | 2019-09-26 |  | Transmitted | TPSK-LSPA1-T-PL-02630 |  | 2019-09-12 | 2
036909C-1012-MR-1554-1259 | Material Requisition for Temperature Transmitters | A | 2019-08-26 | IFQ | OL1-2C17-032259 | PL | 2019-08-27 | 036909C-JVD-TRN-02507 | 036909C-JVD-TRN-02507 | IFR | 2019-09-11 | 2019-09-11 | R2-Comments as noted | TPSK-LSPA1-T-PL-02507 |  | 2019-08-28 | 2
036909C-1000-MR-0213-0001 | Material Requisition for Condensate Polisher Package | 0 | 2019-08-29 | IFP | OL1-2C13-701000 | PL | 2019-08-30 | 036909C-JVD-TRN-02545 | 036909C-JVD-TRN-02545 | IFR | 2019-09-13 | 2019-09-10 | R2-Comments as noted | TPSK-LSPA1-T-PL-02545 |  | 2019-09-03 | 2
036909C-1000-MR-1681-0001 | Material Requisition For Electric Heater | 0 | 2019-08-26 | IFP | OL1-2C13-700000 | PL | 2019-08-28 | 036909C-JVD-TRN-02512 | 036909C-JVD-TRN-02512 | IFP | 2019-09-11 | 2019-09-10 | R2-Comments as noted | TPSK-LSPA1-T-PL-02512 |  | 2019-08-28 | 2
036909C-1000-MR-4123-0001 | Material Requisition For Emergency Diesel Engine Generator | A | 2019-08-27 | IFQ | OL1-2C13-431000 | PL | 2019-08-28 | 036909C-JVD-TRN-02514 | 036909C-JVD-TRN-02514 | IFR | 2019-09-11 | 2019-09-10 | R1-No comments | TPSK-LSPA1-T-PL-02514 |  | 2019-08-28 | 2
036909C-1011-SP-1554-1157 | Instrument Datasheets for Temperature Elements for Thermocouples & RTDs with Wells | A | 2019-09-05 | IFQ | OL1-2I20-1157 | IE | 2019-09-09 | 036909C-JVD-TRN-02598 | 036909C-JVD-TRN-02598 | IFR | 2019-09-24 |  | Transmitted | TPSK-LSPA1-T-IE-02598 |  | 2019-09-10 | 2
036909C-1000-MR-0910-0006 | Material Requisition For API 685 Sealless Pump | B | 2019-08-23 | IFQ | OL1-2C13-446000 | PL | 2019-08-23 | 036909C-JVD-TRN-02476 | 036909C-JVD-TRN-02476 | IFR | 2019-09-09 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-PL-02476 |  | 2019-08-26 | 2
036909C-1012-MR-1552-2060 | Material Requisition for Magnetostrictive Level Transmitter & Magnetic Level Gauge | 0 | 2019-08-14 | IFP | OL1-2C17-022060 | PL | 2019-08-19 | 036909C-JVD-TRN-02458 | 036909C-JVD-TRN-02458 | IFR | 2019-09-03 | 2019-09-04 | R2-Comments as noted | TPSK-LSPA1-T-PL-02458 |  | 2019-08-21 | 2
036909C-1056-SP-0232-0002 | Mechanical Equipment Datasheet For Complex Waste Water Treatment Package | 0 | 2019-08-08 | IFP | OL1-2M03-5644 | ME | 2019-08-09 | 036909C-JVD-TRN-02400 | 036909C-JVD-TRN-02400 | IFR | 2019-08-23 | 2019-09-03 | R2-Comments as noted | TPSK-LSPA1-T-ME-02405 |  | 2019-08-09 | 2
036909C-1000-MR-0580-0001 | Material Requisition for Packing of Columns (C4 Unit) | A | 2019-03-27 | IFQ | OL1-2C13-246000 | PL | 2019-03-28 | 036909C-JVD-TRN-01182 | 036909C-JVD-TRN-01182 | IFI |  | 2019-06-07 | R1-No comments | TPSK-LSPA1-T-PL-01182 |  | 2019-03-28 | 2
036909C-1000-DW-1532-0004 | Telecomm Syst Architecture Of Safety Supervisory System | B | 2019-05-08 | IBD | OL1-2T31-0001 | EE | 2019-05-09 | 036909C-JVD-TRN-01624 | 036909C-JVD-TRN-01624 | IFA | 2019-05-24 | 2019-05-26 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01624 |  | 2019-05-10 | 1
036909C-1000-DW-1532-0004 | TELECOM SYSTEM ARCHITECTURE OF SAFETY SUPERVISORY SYSTEM | C | 2019-07-29 | IFA | OL1-2T31-0001 | EE | 2019-07-30 | 036909C-JVD-TRN-02282 | 036909C-JVD-TRN-02282 | IFA | 2019-08-13 | 2019-08-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-02282 |  | 2019-07-31 | 1
036909C-1000-MR-1641-0001 | Material Requisition For Distribution Transformer | A | 2019-07-31 | IFQ | OL1-2C16-150000 | PL | 2019-08-02 | 036909C-JVD-TRN-02326 | 036909C-JVD-TRN-02326 | IFR | 2019-08-19 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-PL-02326 |  | 2019-08-05 | 2
036909C-1000-MR-1656-0001 | Material Requisition For Power Capacitors | A | 2019-08-01 | IFQ | OL1-2C16-160000 | PL | 2019-08-05 | 036909C-JVD-TRN-02342 | 036909C-JVD-TRN-02342 | IFR | 2019-08-20 | 2019-08-26 | R2-Comments as noted | TPSK-LPSA1-T-PL-02342 |  | 2019-08-06 | 2
036909C-1000-MR-1621-0001 | Material Requisition For Electrical Cables | A | 2019-07-19 | IFQ | OL1-2C16-900000 | PL | 2019-08-02 | 036909C-JVD-TRN-02328 | 036909C-JVD-TRN-02328 | IFR | 2019-08-19 | 2019-08-26 | R2-Comments as noted | TPSK-LSPA1-T-PL-02328 |  | 2019-08-05 | 2
036909C-1027-SP-1681-0002 | Mechanical Equipment Datasheet For Regen Gas Electric Heater | 0 | 2019-08-26 | IFP | OL1-2M03-2730 | ME | 2019-08-28 | 036909C-JVD-TRN-02513 | 036909C-JVD-TRN-02513 | IFP | 2019-09-11 |  | Transmitted | TPSK-LSPA1-T-ME-02513 |  | 2019-08-28 | 2
036909C-1000-MR-0232-0001 | Material Requisition For Complex Waste Water Treatment Package | 0 | 2019-08-09 | IFP | OL1-2C13-702000 | PL | 2019-08-09 | 036909C-JVD-TRN-02399 | 036909C-JVD-TRN-02399 | IFR | 2019-08-23 | 2019-08-26 | R1-No comments | TPSK-LSPA1-T-PL-02399 |  | 2019-08-09 | Class 2
036909C-103A-DW-1572-0012 | Instrument Main Cable Routing Butadiene | A | 2019-08-06 | IFR | OL1-2I34-0012 | IE | 2019-08-08 | 036909C-JVD-TRN-02384 | 036909C-JVD-TRN-02384 | IFA | 2019-08-23 | 2019-08-22 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02384 |  | 2019-08-09 | 1
036909C-102D-DW-1572-0010 | Instrument Main Cable Routing Process Cold Compressors | A | 2019-08-06 | IFR | OL1-2I34-0010 | IE | 2019-08-07 | 036909C-JVD-TRN-02372 | 036909C-JVD-TRN-02372 | IFA | 2019-08-22 | 2019-08-22 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02372 |  | 2019-08-08 | 1
036909C-102B-DW-1572-0008 | Instrument Main Cable Routing C3 Hydrogenation | A | 2019-08-06 | IFR | OL1-2I34-0008 | IE | 2019-08-07 | 036909C-JVD-TRN-02372 | 036909C-JVD-TRN-02372 | IFA | 2019-08-22 | 2019-08-22 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02372 |  | 2019-08-08 | 1
036909C-105F-DW-1572-0016 | Instrument Main Cable Routing Flare Area | A | 2019-08-05 | IFR | OL1-2I34-0016 | IE | 2019-08-06 | 036909C-JVD-TRN-02363 | 036909C-JVD-TRN-02363 | IFA | 2019-08-21 | 2019-08-22 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02363 |  | 2019-08-07 | 1
036909C-105W-DW-1572-0015 | Instrument Main Cable Routing Waste Water Treatment | A | 2019-08-05 | IFR | OL1-2I34-0015 | IE | 2019-08-06 | 036909C-JVD-TRN-02363 | 036909C-JVD-TRN-02363 | IFA | 2019-08-21 | 2019-08-22 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02363 |  | 2019-08-07 | 1
036909C-102E-DW-1572-0011 | Instrument Main Cable Routing Zone 2E Crack Gas Compressor | A | 2019-08-06 | IFR | OL1-2I34-0011 | IE | 2019-08-08 | 036909C-JVD-TRN-02392 | 036909C-JVD-TRN-02392 | IFA | 2019-08-23 | 2019-08-22 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02392 |  | 2019-08-09 | 1
036909C-102A-DW-1572-0007 | Instrument Main Cable Routing Quench | A | 2019-08-07 | IFR | OL1-2I34-0007 | IE | 2019-08-08 | 036909C-JVD-TRN-02392 | 036909C-JVD-TRN-02392 | IFA | 2019-08-23 | 2019-08-22 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02392 |  | 2019-08-09 | 1
036909C-101B-DW-1572-0006 | Instrument Main Cable Routing Furnaces Utilities | A | 2019-08-07 | IFR | OL1-2I34-0006 | IE | 2019-08-08 | 036909C-JVD-TRN-02392 | 036909C-JVD-TRN-02392 | IFA | 2019-08-23 | 2019-08-22 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02392 |  | 2019-08-09 | 1
036909C-1000-MR-1585-0001 | Material Requisition for Analyzer Houses Package | A | 2019-07-26 | IFQ | OL1-2C17-290000 | PL | 2019-07-30 | 036909C-JVD-TRN-02285 | 036909C-JVD-TRN-02285 | IFA | 2019-08-14 | 2019-08-20 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PL-02285 |  | 2019-07-31 | 1
036909C-1000-MR-0630-0001 | Material Requisition For Hairpin Heat Exchangers Requisition For Purchase | 0 | 2019-08-05 | IFP | OL1-2C13-145000 | PL | 2019-08-08 | 036909C-JVD-TRN-02389 | 036909C-JVD-TRN-02389 | IFR | 2019-08-23 | 2019-08-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-02389 |  | 2019-08-09 | 2
036909C-1012-MR-1552-2060 | Material Requisition for Magnetostrictive Level Transmitter & Magnetic Level Gauge | A | 2019-06-17 | IFQ | OL1-2C17-022060 | PL | 2019-06-21 | 036909C-JVD-TRN-01960 | 036909C-JVD-TRN-01960 | IFI |  | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PL-01960 |  | 2019-06-24 | 3
036909C-1000-CN-1611-0001 | Earthing and Lightning Protection System Calculation | A | 2019-06-24 | IFR | OL1-2E50-0001 | EE | 2019-06-25 | 036909C-JVD-TRN-01982 | 036909C-JVD-TRN-01982 | IFR | 2019-07-09 | 2019-07-22 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-01982 |  | 2019-06-25 | 2
036909C-1000-MR-1544-0001 | Material Requisition For Pneumatic Actuators For On Off Valves | A | 2019-07-17 | IFQ | OL1-2C17-060401 | PL | 2019-07-24 | 036909C-JVD-TRN-02257 | 036909C-JVD-TRN-02257 | IFR | 2019-08-08 | 2019-08-07 | R2-Comments as noted | TPSK-LSPA1-T-PL-02257 | file excel da inviare al vendor | 2019-07-25 | 2
036909C-1000-MR-1543-0001 | MR For Electric Pneumatic On Off Valves | A | 2019-07-16 | IFQ | OL1-2C17-060501 | PL | 2019-07-23 | 036909C-JVD-TRN-02245 | 036909C-JVD-TRN-02245 | IFR | 2019-08-07 | 2019-08-07 | R2-Comments as noted | TPSK-LSPA1-T-PL-02245 | C'è un fle Excel da inviare | 2019-07-24 | 2
036909C-1000-MR-1543-0003 | MR For Special On Off Valves | A | 2019-07-16 | IFQ | OL1-2C17-060201 | PL | 2019-07-24 | 036909C-JVD-TRN-02255 | 036909C-JVD-TRN-02255 | IFR | 2019-08-08 | 2019-08-07 | R2-Comments as noted | TPSK-LSPA1-T-PL-02255 | File Excel da trasferire al vendor | 2019-07-25 | 2
036909C-1000-MR-0811-0003 | Material Requisition For Shop Assembled CS Cladded & SS Vessels | 0 | 2019-07-24 | IFP | OL1-2C13-133000 | PL | 2019-07-25 | 036909C-JVD-TRN-02262 | 036909C-JVD-TRN-02262 | IFR | 2019-08-08 | 2019-08-16 | R1-No comments | TPSK-LSPA1-T-PL-02262 |  | 2019-07-29 | 2
036909C-1000-DW-1532-0003 | Telecomm Syst Architecture Of Intercom Paging and Audible Alarm Systems | B | 2019-05-07 | IFR | OL1-2T11-0001 | EE | 2019-05-09 | 036909C-JVD-TRN-01624 | 036909C-JVD-TRN-01624, ROC-TPSK-CECO-T-00072 | IFA | 2019-05-24 | 2019-05-26 | A3 - Approved with comments, re-submit for review | TPSK-LSPA1-T-EE-01624 |  | 2019-05-10 | 1
036909C-1000-DW-1532-0003 | Telecomm. Syst Architecture Of Intercom Paging And Audible Alarm Systems | C | 2019-06-26 | IFR | OL1-2T11-0001 | EE | 2019-06-28 | 036909C-JVD-TRN-02024 | 036909C-JVD-TRN-02024 | IFR | 2019-07-12 | 2019-07-22 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-02024 |  | 2019-07-01 | 1
036909C-1000-MR-1530-0002 | Material Requisition For Safety Supervisory System | 0 | 2019-08-01 | IFP | OL1-2C16-851000 | PL | 2019-08-01 | 036909C-JVD-TRN-02309 | 036909C-JVD-TRN-02309 |  | 2019-08-08 | 2019-08-14 | R1-No comments | TPSK-LSPA1-T-PL-02309 |  | 2019-08-05 | 2
036909C-1000-MR-0610-0004 | Material Requisition for Shell & Tube Heat Exchangers - Lot-3 | 0 | 2019-07-19 | IFP | OL1-2C13-274000 | PL | 2019-07-19 | 036909C-JVD-TRN-02195 | 036909C-JVD-TRN-02195 | IFR | 2019-08-02 | 2019-07-31 | R2-Comments as noted | TPSK-LSPA1-T-PL-02195 |  | 2019-07-22 | 2
036909C-1000-MR-0610-0003 | Material Requisition for Shell & Tube Heat Exchangers (Lot-2) | 0 | 2019-07-24 | IFP | OL1-2C13-273000 | PL | 2019-07-25 | 036909C-JVD-TRN-02261 | 036909C-JVD-TRN-02261 | IFR | 2019-08-08 | 2019-08-14 | R1-No comments | TPSK-LSPA1-T-PL-02261 |  | 2019-07-25 | 2
036909C-1000-MR-1111-0001 | Material Requisition For General Purpose Steam Turbines | 0 | 2019-07-05 | IMP | OL1-2C13-404000 | PL | 2019-07-11 | 036909C-JVD-TRN-02131 | 036909C-JVD-TRN-02131 | IFR | 2019-07-26 | 2019-07-25 | R2-Comments as noted | TPSK-LSPA1-T-PL-02131 | Umbrella Contract for Steam Turbines | 2019-07-15 | 2
036909C-1000-MR-1930-0001 | Material Requisition for Deluge and Sprinkler System Package | A | 2019-07-05 | IFQ | OL1-2C15-822001 | PL | 2019-07-05 | 036909C-JVD-TRN-02083 | 036909C-JVD-TRN-02083 | IFR | 2019-07-19 | 2019-08-08 | R1-No comments | TPSK-LSPA1-T-PL-02083 |  | 2019-07-08 | 2
036909C-1000-MR-1920-0001 | Material Requisition for Fire Fighting and Safety Equipment Package | A | 2019-07-05 | IFQ | OL1-2C15-821001 | PL | 2019-07-05 | 036909C-JVD-TRN-02083 | 036909C-JVD-TRN-02083 | IFR | 2019-07-19 | 2019-08-06 | R1-No comments | TPSK-LSPA1-T-PL-02083 |  | 2019-07-08 | 2
036909C-1000-MR-0232-0001 | Material Requisition For Complex Waste Water Treatment Package | A | 2019-02-15 | IFQ | OL1-2C13-702000 | PL | 2019-02-15 | 036909C-JVD-TRN-00862 | 036909C-JVD-TRN-00862 | IFR | 2019-03-01 | 2019-06-07 | R2-Comments as noted | TPSK-LSPA1-T-PL-00862 |  | 2019-02-15 | 2
036909C-1012-MR-1553-1256 | Material Requisition for Material Requisition for Pressure Indicating Transmitters & Flow Indicating D P Transmitters | A | 2019-07-31 | IFQ | OL1-2C17-042256 | PL | 2019-08-07 | 036909C-JVD-TRN-02375 | 036909C-JVD-TRN-02375 | IFR | 2019-08-22 |  | Transmitted | TPSK-LSPA1-T-PL-02375 |  | 2019-08-08 | 2
036909C-1000-SP-1970-0001 | Datasheet for Safety & Life Saving Equipment | B | 2019-07-05 | IFQ | OL1-2L03-5001 | SE | 2019-07-08 | 036909C-JVD-TRN-02090 | 036909C-JVD-TRN-02090 | IFR | 2019-07-22 | 2019-08-06 | R2-Comments as noted | TPSK-LSPA1-T-SE-02090 |  | 2019-07-08 | 2
036909C-1000-MR-0836-0001 | Material Requisition for Silencers | A | 2019-07-12 | IFQ | OL1-2C13-161000 | PL | 2019-07-12 | 036909C-JVD-TRN-02146 | 036909C-JVD-TRN-02146 | IFR | 2019-07-26 | 2019-08-01 | R2-Comments as noted | TPSK-LSPA1-T-PL-02146 |  | 2019-07-15 | 2
036909C-1000-JSS-1530-0002 | Job Supply Specification For Safety Supervisory System | 0 | 2019-07-17 | IMP | OL1-2T01-0002 | EE | 2019-07-18 | 036909C-JVD-TRN-02181 | 036909C-JVD-TRN-02181 | IFR | 2019-08-01 | 2019-08-01 | A1-Approved without comments | TPSK-LSPA1-T-EE-02181 |  | 2019-07-19 | 1
036909C-1056-PDS-0900-5624 | Process Equipment Datasheet - 10-P-5627 A-B - West Gate House Septic Tank Pumps | A | 2018-12-26 | IFR | OL1-2G30-5624 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572 |  | 2019-01-03 | 2
036909C-1056-PDS-0900-5623 | Process Equipment Datasheet - 10-P-5626 A-B - Gate House Septic Tank Pumps | A | 2018-12-26 | IFR | OL1-2G30-5623 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572 |  | 2019-01-03 | 2
036909C-1000-MR-0910-0003 | Material Requisition for Cooling Water Pumps | 0 | 2019-07-09 | IFP | OL1-2C13-440003 | PL | 2019-07-10 | 036909C-JVD-TRN-02113 | 036909C-JVD-TRN-02113 | IFR | 2019-07-24 | 2019-07-30 | R1-No comments | TPSK-LSPA1-T-PL-02113 |  | 2019-07-10 | 2
036909C-1000-JSD-1530-0001 | Intercom/Paging/Audible Alarm System | 1 | 2019-06-27 | IMP | OL1-2R05-0013 | EE | 2019-07-01 | 036909C-JVD-TRN-02031 | 036909C-JVD-TRN-02031 | IFR | 2019-07-15 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-EE-02031 |  | 2019-07-01 | 2
036909C-1012-ML-211 | Recovery Process and Utilities Sections HAZOP Report | A | 2019-07-05 | IFR | OL1-2L60-0211 | SE | 2019-07-08 | 036909C-JVD-TRN-02101 | 036909C-JVD-TRN-02101 | IFR | 2019-07-23 |  | Transmitted | TPSK-LSPA1-T-SE-02101 |  | 2019-07-08 | 2
036909C-1000-DW-1522-0002 | Instrument And Telecom Grounding Philosophy Diagram | 0 | 2019-07-10 | IBD | OL1-2I48-1001 | IE | 2019-07-11 | 036909C-JVD-TRN-02135 | 036909C-JVD-TRN-02135 | IFA | 2019-07-26 | 2019-07-30 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-IE-02135 |  | 2019-07-15 | 1
036909C-1000-SP-1930-0002 | Datasheet for Clean Agent Fire Extinguishing System | B | 2019-07-05 | IFQ | OL1-2L03-3001 | SE | 2019-07-08 | 036909C-JVD-TRN-02088 | 036909C-JVD-TRN-02088 | IFR | 2019-07-22 | 2019-07-29 | R2-Comments as noted | TPSK-LSPA1-T-SE-02088 |  | 2019-07-08 | 2
036909C-1000-PP-501 | NON CONFORMITY MANAGEMENT PROCEDURE | 0 | 2019-06-14 | IMP | OL1-2Q92-0003 | QM | 2019-07-03 | 036909C-JVD-TRN-01998 | 036909C-JVD-TRN-01998 | IFR | 2019-07-10 | 2019-07-22 | R1-No comments | TPSK-LSPA1-T-QM-01998 |  | 2019-06-27 | 2
036909C-1024-SP-1543-2404 | Instrument Datasheets for On-Off Valve - Butterfly Type - Area 24 | A | 2019-05-02 | IFQ | OL1-2I20-2412 | IE | 2019-05-02 | 036909C-JVD-TRN-01548 | 036909C-JVD-TRN-01548 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01548 |  | 2019-05-03 | 3
036909C-1011-SP-1543-1104 | Instrument Datasheets for ON-OFF Valve Butterfly Type - Area 11 BOP | A | 2019-05-06 | IFQ | OL1-2I20-1112 | IE | 2019-05-07 | 036909C-JVD-TRN-01594 | 036909C-JVD-TRN-01594 | IFI |  | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-IE-01594 |  | 2019-05-08 | 3
036909C-1000-MR-0950-0001 | Technical Agreement For Mechanical Seals And Seal System | 0 | 2019-07-01 | IMP | OL1-2C13-251000 | PL | 2019-07-08 | 036909C-JVD-TRN-02096 | 036909C-JVD-TRN-02096 | IFR | 2019-07-23 | 2019-07-18 | R1-No comments | TPSK-LSPA1-T-PL-02096 |  | 2019-07-09 | 2
036909C-1010-TDS-0610-1015 | Mechanical Equipment Data Sheet - 10-E-1015 - LPG Superheater | A | 2018-12-18 | IFQ | OL1-2M03-1015 | ME | 2018-12-27 | 036909C-JVD-TRN-00571 | 036909C-JVD-TRN-00571 | IFR | 2019-01-11 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00571 |  | 2018-12-27 | 2
036909C-102A-DW-0051-0001 | Detail Plot Plan - Zone 2A - Quench | B | 2019-05-21 | IBD | OL1-2P06-0008 | MP | 2019-05-28 | 036909C-JVD-TRN-01752 | 036909C-JVD-TRN-01752 | IFR | 2019-06-12 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-MP-01752 |  | 2019-05-29 | 2
036909C-1000-MS-2000-0001 | Technical Specification For Buildings | B | 2019-04-26 | IFR | OL1-2R02-5001 | CV | 2019-06-13 | 036909C-JVD-TRN-01885 | 036909C-JVD-TRN-01885 | IFR | 2019-06-27 | 2019-07-22 | R1-No comments | TPSK-LSPA1-T-CV-01885 |  | 2019-06-14 | 2
036909C-1024-PDS-0800-2444 | Process Equipment Datasheet - 10-D-2445 - HP Deprop Reboiler Cond Pot | B | 2018-12-21 | IFD | OL1-2G30-2444 | PE | 2018-12-27 | 036909C-JVD-TRN-00563 | 036909C-JVD-TRN-00563 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00563 |  | 2018-12-27 | 2
036909C-1025-PDS-0800-2574 | Process Equipment Datasheet - 10-D-2575 - Deethanizer Reboiler Cond Pot | B | 2018-12-21 | IFD | OL1-2G30-2574 | PE | 2018-12-27 | 036909C-JVD-TRN-00563 | 036909C-JVD-TRN-00563 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00563 |  | 2018-12-27 | 2
036909C-1024-PDS-0800-2456 | Process Equipment Datasheet - 10-D-2455 - LP Deprop Reboiler Cond Pot | B | 2018-12-21 | IFD | OL1-2G30-2456 | PE | 2018-12-27 | 036909C-JVD-TRN-00563 | 036909C-JVD-TRN-00563 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00563 |  | 2018-12-27 | 2
036909C-1012-MR-0154-2003 | Material Requisition for Quench Exchangers - Ex Doc. Client Reference OL1-2M55-2003 | 1 | 2019-03-08 | IFP | OL1-2C13-140000 | PL | 2019-04-01 | 036909C-JVD-TRN-01221 | 036909C-JVD-TRN-01221 | IFI |  | 2019-06-20 | R2-Comments as noted | TPSK-LSPA1-T-PL-01221 | Ex Doc. Client Reference OL1-2M55-2003 | 2019-04-02 | 3
036909C-1012-MR-0127-2002 | Material Requisition for Furnace Convection Fittings - Ex Doc Client Ref OL1-2M55-2002 | 1 | 2019-03-08 | IFP | OL1-2C13-304000 | PL | 2019-03-25 | 036909C-JVD-TRN-01139 | 036909C-JVD-TRN-01139 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01139 | Ex Doc Client Ref OL1-2M55-2002 | 2019-03-26 | 3
036909C-1000-MR-1130-0001 | Material Requisition For Residue Gas Expander/Recompressor - Ex Doc. Client Reference OL1-2M55-0012 | 0 | 2019-03-15 | IFP | OL1-2C13-421000 | PL | 2019-03-21 | 036909C-JVD-TRN-01118 | 036909C-JVD-TRN-01118 | IFA | 2019-04-05 |  | Transmitted | TPSK-LSPA1-T-PL-01118 | Ex Doc. Client Reference OL1-2M55-0012 | 2019-03-22 | 1
036909C-1000-MR-4234-0001 | Material Requisition for Side Stream Filter Package - Ex Doc. Client Reference OL1-2M55-0109 | 0 | 2019-03-22 | IFP | OL1-2C13-706000 | PL | 2019-03-27 | 036909C-JVD-TRN-01165 | 036909C-JVD-TRN-01165 | IFR | 2019-03-27 | 2019-06-07 | R1-No comments | TPSK-LSPA1-T-PL-01165 | Ex Doc. Client Reference OL1-2M55-0109 | 2019-03-27 | 2
036909C-102D-DW-1950-5010 | FIRE & GAS DEVICES LAYOUT - ZONE 2D - PROCESS COLD COMPRESSOR | B | 2019-04-26 | IFR | OL1-2F40-5010 | FF | 2019-04-30 | 036909C-JVD-TRN-01518 | 036909C-JVD-TRN-01518, KLOC-TPSK-VSAFE-T-00007, KLOC-TPSK-CECO-T-00008 | IFR | 2019-05-14 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-FF-01518 |  | 2019-05-02 | 2
036909C-1024-TDS-0610-2446 | Mechanical Equipment Data Sheet - 10-E-2446 - LP Depropanizer Feed Cooler | A | 2018-12-20 | IFQ | OL1-2M03-2446 | ME | 2018-12-27 | 036909C-JVD-TRN-00565 | 036909C-JVD-TRN-00565, ROC-TPSK-CECO-T-00017 | IFR | 2019-01-11 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-ME-00565 |  | 2018-12-27 | 2
036909C-1020-SP-1542-2003 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 20 | A | 2019-05-08 | IFQ | OL1-2I20-2006 | IE | 2019-05-09 | 036909C-JVD-TRN-01625 | 036909C-JVD-TRN-01625 | IFI |  | 2019-07-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01625 |  | 2019-05-10 | 3
036909C-1000-MR-1011-0001 | Material Requisition For Centrifugal Compressors Steam Turbine Driven - Ex Document Cliet Reference OL1-2M55-0008 | 0 | 2019-03-15 | IFP | OL1-2C13-401000 | PL | 2019-03-21 | 036909C-JVD-TRN-01124 | 036909C-JVD-TRN-01124 | IFA | 2019-04-05 |  | Transmitted | TPSK-LSPA1-T-PL-01124 | Ex Document Cliet Reference OL1-2M55-0008 | 2019-03-22 | 1
036909C-1000-MR-0610-0002 | Material Requisition for Shell & Tube Heat Exchangers Lot-1 | 0 | 2019-07-16 | IFP | OL1-2C13-272000 | PL | 2019-07-17 | 036909C-JVD-TRN-02169 | 036909C-JVD-TRN-02169 | IFR | 2019-07-31 |  | Transmitted | TPSK-LSPA1-T-PL-02169 |  | 2019-07-17 | 2
036909C-1000-MR-4111-0001 | Material Requisition For Hydrogen Production Unit PK-2560 - Ex Doc. Client Reference OL1-2M55-0114 | 0 | 2019-04-30 | IFP | OL1-2C13-705000 | PL | 2019-05-06 | 036909C-JVD-TRN-01580 | 036909C-JVD-TRN-01580 | IFR | 2019-05-21 | 2019-05-27 | R2-Comments as noted | TPSK-LSPA1-T-PL-01580 | Ex Doc. Client Reference OL1-2M55-0114 | 2019-05-07 | 2
036909C-1000-MR-4100-0001 | Material Requisition for Wet Air Oxidation Package - Ex Doc. Client Reference OL1-2M55-0103 | 0 | 2019-05-07 | IFP | OL1-2C13-704000 | PL | 2019-05-08 | 036909C-JVD-TRN-01611 | 036909C-JVD-TRN-01611 | IFR | 2019-05-22 | 2019-06-16 | R2-Comments as noted | TPSK-LSPA1-T-PL-01611 | Ex Doc. Client Reference OL1-2M55-0103 | 2019-05-09 | 2
036909C-1000-MR-0570-0001 | Material Requisition For Trays For Columns Ex Doc. Client Reference OL1-2M55-0055 | 0 | 2019-04-15 | IFP | OL1-2C13-242000 | PL | 2019-04-15 | 036909C-JVD-TRN-01352 | 036909C-JVD-TRN-01352 | IFR | 2019-04-30 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-PL-01352 | Ex Doc. Client Reference OL1-2M55-0055 Closure to comments for document OL1-2M07-0055_A sent by email TPSK-LSPA1-E-00193_21/05/2019 | 2019-04-17 | 2
036909C-1000-MR-0310-0001 | Material Requisition for Cooling Tower - Ex Doc. Client Reference OL1-2M55-0104 | 0 | 2019-04-18 | IFP | OL1-2C13-311000 | PL | 2019-04-24 | 036909C-JVD-TRN-01460 | 036909C-JVD-TRN-01460 | IFR | 2019-05-08 | 2019-05-24 | R1-No comments | TPSK-LSPA1-T-PL-01460 | Ex Doc. Client Reference OL1-2M55-0104 | 2019-04-25 | 2
036909C-1000-MR-0811-0004 | Material Requisition for Shop Assembled Drums (C4 Unit) | A | 2019-06-28 | IFQ | OL1-2C13-134000 | PL | 2019-07-01 | 036909C-JVD-TRN-02033 | 036909C-JVD-TRN-02033 | IFR | 2019-07-15 | 2019-07-11 | R2-Comments as noted | TPSK-LSPA1-T-PL-02033 |  | 2019-07-01 | 2
036909C-1000-JSS-1031-0001 | ME-047 Dry Screw Compressor for Hydrocarbon Services | 0 | 2019-01-16 | IMP | OL1-2R03-0047 | ME | 2019-01-17 | 036909C-JVD-TRN-00666 | 036909C-JVD-TRN-00666, ROC-TPSK-CECO-T-00003 | IFR | 2019-01-30 | 2019-02-04 | R1-No comments | TPSK-LSPA1-T-ME-00666 |  | 2019-01-17 | 2
036909C-1027-SP-1542-2703 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 27 | A | 2019-06-14 | IFQ | OL1-2I20-2706 | IE | 2019-06-17 | 036909C-JVD-TRN-01907 | 036909C-JVD-TRN-01907 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01907 |  | 2019-06-18 | 3
036909C-1056-SP-1542-5603 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 56 | A | 2019-06-11 | IFQ | OL1-2I20-5606 | IE | 2019-06-12 | 036909C-JVD-TRN-01878 | 036909C-JVD-TRN-01878 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01878 |  | 2019-06-14 | 3
036909C-1051-SP-1542-5103 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 51 | A | 2019-06-07 | IFQ | OL1-2I20-5106 | IE | 2019-06-10 | 036909C-JVD-TRN-01845 | 036909C-JVD-TRN-01845 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01845 |  | 2019-06-11 | 3
036909C-1000-SP-1930-0002 | Datasheet for Clean Agent Fire Extinguishing System | A | 2019-06-14 | IFR | OL1-2L03-3001 | SE | 2019-06-17 | 036909C-JVD-TRN-01899 | 036909C-JVD-TRN-01899 | IFR | 2019-07-02 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-SE-01899 |  | 2019-06-17 | 2
036909C-1000-MR-0661-0001 | Material Requisition Plate And Frame Heat Exchangers Requisition For Purchase - Ex Doc. Client Ref. OL1-2M55-0064 | 0 | 2019-02-25 | IFP | OL1-2C13-142000 | PL | 2019-02-25 | 036909C-JVD-TRN-00916 | 036909C-JVD-TRN-00916 | IFR | 2019-03-12 | 2019-06-06 | R1-No comments | TPSK-LSPA1-T-PL-00916 | Ex Doc. Client Ref. OL1-2M55-0064 Closure to comments for document OL1-2M07-0064_A sent by email TPSK-LSPA1-E-00195_21/05/2019 | 2019-02-26 | 2
036909C-1000-MR-0950-0001 | Material Requisition For API Mechanical Seals and Seal System | A | 2019-02-22 | IFQ | OL1-2C13-251000 | PL | 2019-02-28 | 036909C-JVD-TRN-00949 | 036909C-JVD-TRN-00949 | IFR | 2019-03-08 |  | Transmitted | TPSK-LSPA1-T-PL-00949 |  | 2019-03-01 | 2
036909C-1012-MR-1552-2064 | Material Requisition for Guided Wave Radar Level Transmitter & Magnetic Level Gauge | A | 2019-06-17 | IFQ | OL1-2C17-022064 | PL | 2019-06-20 | 036909C-JVD-TRN-01949 | 036909C-JVD-TRN-01949 | IFI |  | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PL-01949 |  | 2019-06-21 | 3
036909C-1012-MR-1554-2015 | Material Requisition for pH and Conductivity Analyzer | B | 2019-06-19 | IFQ | OL1-2C17-232015 | PL | 2019-06-20 | 036909C-JVD-TRN-01950 | 036909C-JVD-TRN-01950 | IFR | 2019-07-05 | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PL-01950 |  | 2019-06-21 | 3
036909C-1012-MR-1554-2061 | Material Requisition for Temperature Elements for Furnace Profile | A | 2019-06-18 | IFQ | OL1-2C17-032061 | PL | 2019-06-24 | 036909C-JVD-TRN-01977 | 036909C-JVD-TRN-01977 | IFI |  | 2019-07-08 | R2-Comments as noted | TPSK-LSPA1-T-PL-01977 |  | 2019-06-25 | 3
036909C-1000-MR-0184-0001 | Material Requisition For HP / Polyolefins Flare Package | 0 | 2019-06-21 | IFP | OL1-2C13-708000 | PL | 2019-06-21 | 036909C-JVD-TRN-01951 | 036909C-JVD-TRN-01951 | IFR | 2019-07-08 | 2019-07-08 | R1-No comments | TPSK-LSPA1-T-PL-01951 |  | 2019-06-25 | 2
036909C-1000-SP-1970-0001 | Datasheet for Safety & Life Saving Equipment | A | 2019-05-17 | IFR | OL1-2L03-5001 | SE | 2019-05-21 | 036909C-JVD-TRN-01703 | 036909C-JVD-TRN-01703 | IFR | 2019-06-04 | 2019-06-10 | R2-Comments as noted | TPSK-LSPA1-T-SE-01703 |  | 2019-05-21 | 2
036909C-1055-SP-1547-5505 | Instrument Datasheets for Flow Transmitter - Electromagnetic - Area 55 | A | 2019-06-03 | IFQ | OL1-2I20-5529 | IE | 2019-06-05 | 036909C-JVD-TRN-01807 | 036909C-JVD-TRN-01807 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01807 |  | 2019-06-10 | 3
036909C-1023-SP-1547-2305 | Instrument Datasheets for Flow transmitter - Electromagnetic - Area 23 | A | 2019-05-03 | IFQ | OL1-2I20-2329 | IE | 2019-05-06 | 036909C-JVD-TRN-01581 | 036909C-JVD-TRN-01581 | IFI |  | 2019-06-13 | R2-Comments as noted | TPSK-LSPA1-T-IE-01581 |  | 2019-05-07 | 3
036909C-1011-SP-1542-1103 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 11 -BOP | A | 2019-05-06 | IFQ | OL1-2I20-1106 | IE | 2019-05-07 | 036909C-JVD-TRN-01594 | 036909C-JVD-TRN-01594 | IFI |  | 2019-07-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-01594 |  | 2019-05-08 | 3
036909C-1023-SP-1542-2303 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 23 | A | 2019-05-02 | IFQ | OL1-2I20-2306 | IE | 2019-05-02 | 036909C-JVD-TRN-01548 | 036909C-JVD-TRN-01548 | IFI |  | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-IE-01548 |  | 2019-05-03 | 3
036909C-1012-SP-1542-1203 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 12 - BOP | A | 2019-05-06 | IFQ | OL1-2I20-1206 | IE | 2019-05-07 | 036909C-JVD-TRN-01594 | 036909C-JVD-TRN-01594 | IFI |  | 2019-07-02 | R1-No comments | TPSK-LSPA1-T-IE-01594 |  | 2019-05-08 | 3
036909C-1059-SP-1542-5903 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 59 | A | 2019-06-07 | IFQ | OL1-2I20-5906 | IE | 2019-06-10 | 036909C-JVD-TRN-01845 | 036909C-JVD-TRN-01845 | IFI |  | 2019-07-01 | R2-Comments as noted | TPSK-LSPA1-T-IE-01845 |  | 2019-06-11 | 3
036909C-1028-SP-1542-2803 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 28 | B | 2019-05-23 | IFQ | OL1-2I20-2806 | IE | 2019-05-24 | 036909C-JVD-TRN-01738 | 036909C-JVD-TRN-01738 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01738 |  | 2019-05-27 | 3
036909C-1055-SP-1542-5503 | Instrument Datasheets for Self Actuated Pressure Control Valve - Area 55 | A | 2019-05-27 | IFQ | OL1-2I20-5506 | IE | 2019-06-03 | 036909C-JVD-TRN-01792 | 036909C-JVD-TRN-01792 | IFI |  | 2019-06-27 | R2-Comments as noted | TPSK-LSPA1-T-IE-01792 |  | 2019-06-10 | 3
036909C-1010-SP-1541-1001 | Instrument Datasheets for Control Valve - Globe Type - Area 10 | A | 2019-05-16 | IFQ | OL1-2I20-1009 | IE | 2019-05-20 | 036909C-JVD-TRN-01692 | 036909C-JVD-TRN-01692 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01692 |  | 2019-05-21 | 3
036909C-1019-SP-1542-1903 | Instrument Datasheets for Self Actuated pressure Control Valve Area 19 | A | 2019-05-17 | IFQ | OL1-2I20-1906 | IE | 2019-05-20 | 036909C-JVD-TRN-01692 | 036909C-JVD-TRN-01692 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01692 |  | 2019-05-21 | 3
036909C-1029-SP-1542-2903 | Instrument Datasheets for Self Actuated Pressure Control Valve - Area 29 | A | 2019-05-21 | IFQ | OL1-2I20-2906 | IE | 2019-05-22 | 036909C-JVD-TRN-01717 | 036909C-JVD-TRN-01717 | IFI |  | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-IE-01717 |  | 2019-05-23 | 3
036909C-1000-DW-1632-0010 | Street Lighting System Layout | A | 2019-05-31 | IFR | OL1-2E43-0001 | EE | 2019-06-03 | 036909C-JVD-TRN-01794 | 036909C-JVD-TRN-01794 | IFA | 2019-06-18 | 2019-06-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-01794 |  | 2019-06-10 | 1
036909C-1000-JSD-1515-0001 | General Design Rules For SIS Safety Requirements Specification | 0 | 2019-04-17 | IMP | OL1-2I61-1102 | IE | 2019-04-17 | 036909C-JVD-TRN-01392 | 036909C-JVD-TRN-01392 | IFR | 2019-05-02 | 2019-06-19 | R2-Comments as noted | TPSK-LSPA1-T-IE-01392 |  | 2019-04-18 | 2
036909C-1000-MR-0910-0005 | Material Requisition For Submersible Pumps | A | 2019-05-17 | IFQ | OL1-2C13-443000 | PL | 2019-05-24 | 036909C-JVD-TRN-01736 | 036909C-JVD-TRN-01736 | IFR | 2019-06-10 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PL-01736 |  | 2019-05-27 | 2
036909C-1000-MR-0184-0001 | MR for HP / Polyolefins Flare Package | A | 2019-01-15 | IFQ | OL1-2C13-708000 | PL | 2019-01-17 | 036909C-JVD-TRN-00665 | 036909C-JVD-TRN-00665 | IFR | 2019-01-30 | 2019-06-11 | R2-Comments as noted | TPSK-LSPA1-T-PL-00665 |  | 2019-01-17 | 2
036909C-1026-SP-0810-2610 | Mechanical Equipment Datasheet - C3 Hydrog Arsine Guard Bed | A | 2018-12-20 | IFQ | OL1-2M03-2610 | ME | 2018-12-27 | 036909C-JVD-TRN-00570 | 036909C-JVD-TRN-00570 | IFR | 2019-01-11 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-ME-00570 |  | 2018-12-27 | 2
036909C-1000-MR-0662-0002 | Material Requisition For Cold Box And Core Exchangers Requisition For Purchase - Ex Doc. Client Ref. OL1-2M55-0066 | 0 | 2019-04-15 | IFP | OL1-2C13-144000 | PL | 2019-04-15 | 036909C-JVD-TRN-01351 | 036909C-JVD-TRN-01351 | IFR | 2019-04-30 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-PL-1351 | Ex Doc. Client Ref. OL1-2M55-0066 Closure to comments for document OL1-2M07-0066_A sent by email TPSK-LSPA1-E-00196_21/05/2019 | 2019-04-17 | 2
036909C-1012-MR-0132-2013 | Material Requisition for Radiant Refractory | 0 | 2019-05-09 | IFP | OL1-2C13-283000 | PL | 2019-05-13 | 036909C-JVD-TRN-01657 | 036909C-JVD-TRN-01657 | IFI |  | 2019-06-19 | R1-No comments | TPSK-LSPA1-T-PL-01657 |  | 2019-05-14 | 3
036909C-1000-JSD-1422-0002 | Geotechnical Factual Report | A | 2019-04-29 | IFR | OL1-2R02-0011 | CV | 2019-05-02 | 036909C-JVD-TRN-01549 | 036909C-JVD-TRN-01549, ROC-TPSK-CECO-T-00058 | IFR | 2019-05-17 | 2019-05-27 | A2-Approved with comments, re-submit is not required. | TPSK-LPSA1-T-CV-01549 |  | 2019-05-03 | 2
036909C-1000-MR-2520-0001 | MATERIAL REQUISITION FOR SITE ASSEMBLED TANKS | A | 2019-05-17 | IFQ | OL1-2C13-201000 | PL | 2019-05-17 | 036909C-JVD-TRN-01688 | 036909C-JVD-TRN-01688 | IFR | 2019-05-31 | 2019-05-31 | R2-Comments as noted | TPSK-LSPA1-T-PL-01688 |  | 2019-05-21 | 2
036909C-1000-TBT-1013-0001 | Technical Bid Evaluation For Integrally Geared Decoking Air Compressors | 1 | 2019-05-06 | IFI | OL1-2C23-0014 | PL | 2019-05-07 | 036909C-JVD-TRN-01595 | 036909C-JVD-TRN-01595 | IFA | 2019-05-22 | 2019-05-26 | R2-Comments as noted | TPSK-LSPA1-T-PL-01595 |  | 2019-05-08 | 1
036909C-1000-DW-1576-0005 | Instr Supports Typical Mount Details | B | 2019-04-16 | IFR | OL1-2I31-0001 | IE | 2019-04-17 | 036909C-JVD-TRN-01391 | 036909C-JVD-TRN-01391 | IFA | 2019-05-02 | 2019-05-18 | A3 - Approved with comments, re-submit for review | TPSK-LPSA1-T-IE-01391 |  | 2019-04-18 | 1
036909C-1000-MR-1130-0001 | Material Requisition For Residue Gas Expander/Recompressor | 1 | 2019-04-18 | IFP | OL1-2C13-421000 | PL | 2019-04-23 | 036909C-JVD-TRN-01443 | 036909C-JVD-TRN-01443 | IFA | 2019-05-08 | 2019-05-20 | R1-No comments | TPSK-LSPA1-T-PL-01443 |  | 2019-04-24 | 1
036909C-1000-MS-1320-0051 | Construction Specification For Piping Prefabrication Erection And Non Destructive Examination | A | 2019-02-21 | IFR | OL1-2P92-0007 | MP | 2019-02-25 | 036909C-JVD-TRN-00917 | 036909C-JVD-TRN-00917 | IFR | 2019-03-12 | 2019-05-07 | R2-Comments as noted | TPSK-LSPA1-T-MP-00917 |  | 2019-02-26 | 2
036909C-102D-DW-1950-5010 | FIRE & GAS DEVICES LAYOUT - ZONE 2D - PROCESS COLD COMPRESSOR | A | 2019-03-20 | IFR | OL1-2F40-5010 | FF | 2019-03-21 | 036909C-JVD-TRN-01120 | 036909C-JVD-TRN-01120, KLOC-TPSK-CECO-T-00002 | IFR | 2019-04-03 | 2019-05-10 | R2-Comments as noted | TPSK-LSPA1-T-FF-01120 |  | 2019-03-22 | 2
036909C-1012-MR-0132-2013 | Material Requisition for Radiant Refractory | A | 2019-03-15 | IFQ | OL1-2C13-283000 | PL | 2019-03-20 | 036909C-JVD-TRN-01108 | 036909C-JVD-TRN-01108 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01108 |  | 2019-03-21 | 3
036909C-1056-PDS-0900-5649 | Process Equipment Datasheet - 10-P-5607 A-B - Flare KO Drum Oily Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5649 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00572 |  | 2019-01-03 | 2
036909C-1056-PDS-0900-5614 | Process Equipment Datasheet - 10-P-5605 A-B - Furnace Area Oily Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5614 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572 |  | 2019-01-03 | 2
036909C-1055-PDS-0900-5551 | Process Equipment Datasheet - 10-P-5550 A-B - HP Flare Knock-Out Pumps | A | 2018-12-21 | IFR | OL1-2G30-5551 | PE | 2018-12-27 | 036909C-JVD-TRN-00569 | 036909C-JVD-TRN-00569 | IFR | 2019-01-11 | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00569 |  | 2018-12-27 | 2
036909C-1059-PDS-0900-5951 | Process Equipment Datasheet - 10-P-5950 A-B - Sodium Hypochlorite Metering Pumps | A | 2018-12-21 | IFR | OL1-2G30-5951 | PE | 2018-12-27 | 036909C-JVD-TRN-00569 | 036909C-JVD-TRN-00569 | IFR | 2019-01-11 | 2019-01-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00569 |  | 2018-12-27 | 2
036909C-1059-PDS-0900-5902 | Process Equipment Datasheet - 10-P-5901 A-B - Sulfuric Acid Metering Pumps | A | 2018-12-21 | IFR | OL1-2G30-5902 | PE | 2018-12-27 | 036909C-JVD-TRN-00569 | 036909C-JVD-TRN-00569 | IFR | 2019-01-11 | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00569 |  | 2018-12-27 | 2
036909C-1055-PDS-0600-5511 | Process Equipment Datasheet - 10-E-5510 - Cold Flare Blowdown Vaporizer | A | 2018-12-28 | IFR | OL1-2G30-5511 | PE | 2019-01-03 | 036909C-JVD-TRN-00575 | 036909C-JVD-TRN-00575 | IFR | 2019-01-15 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00575 |  | 2019-01-03 | 2
036909C-1000-MR-1040-0001 | Material Requisition For Vent Gas Blower | A | 2019-03-04 | IFQ | OL1-2C13-451000 | PL | 2019-03-07 | 036909C-JVD-TRN-01001 | 036909C-JVD-TRN-01001 | IFR | 2019-03-22 | 2019-03-27 | R2-Comments as noted | TPSK-LSPA1-T-PL-01001 |  | 2019-03-08 | 2
036909C-1055-PDS-0600-5512 | Process Equipment Datasheet - 10-E-5512 - Cold Flare Superheater | A | 2018-12-28 | IFR | OL1-2G30-5512 | PE | 2019-01-03 | 036909C-JVD-TRN-00575 | 036909C-JVD-TRN-00575 | IFR | 2019-01-15 | 2019-03-13 | R1-No comments | TPSK-LSPA1-T-PE-00575 |  | 2019-01-03 | 2
036909C-1055-PDS-0600-5513 | Process Equipment Datasheet - 10-E-5513 - Methanol Vaporizer | A | 2018-12-28 | IFR | OL1-2G30-5513 | PE | 2019-01-03 | 036909C-JVD-TRN-00575 | 036909C-JVD-TRN-00575 | IFR | 2019-01-15 | 2019-03-13 | R2-Comments as noted | TPSK-LSPA1-T-PE-00575 |  | 2019-01-03 | 2
036909C-1056-PDS-0900-5625 | Process Equipment Datasheet - 10-P-5628 A-B - East Gate House Septic Tank Pumps | A | 2018-12-26 | IFR | OL1-2G30-5625 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572 |  | 2019-01-03 | 2
036909C-1056-PDS-0900-5616 | Process Equipment Datasheet - 10-P-5615 A-B - Olefins Stormwater Sump Pumps | A | 2018-12-28 | IFR | OL1-2G30-5616 | PE | 2019-01-03 | 036909C-JVD-TRN-00576 | 036909C-JVD-TRN-00576 | IFR | 2019-01-15 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00576 |  | 2019-01-03 | 2
036909C-1056-PDS-0900-5621 | Process Equipment Datasheet - 10-P-5621 - Olefins Holding Basin Skimmed Oil Pump | A | 2018-12-28 | IFR | OL1-2G30-5621 | PE | 2019-01-03 | 036909C-JVD-TRN-00576 | 036909C-JVD-TRN-00576 | IFR | 2019-01-15 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00576 |  | 2019-01-03 | 2
036909C-1055-PDS-0900-5501 | Process Equipment Datasheet - 10-P-5500 A-B - Hot Blowdown Pumps | A | 2018-12-21 | IFR | OL1-2G30-5501 | PE | 2018-12-27 | 036909C-JVD-TRN-00569 | 036909C-JVD-TRN-00569 | IFR | 2019-01-11 | 2019-01-24 | R1-No comments | TPSK-LSPA1-T-PE-00569 |  | 2018-12-27 | 2
036909C-1056-PDS-0900-5607 | Process Equipment Datasheet - 10-P-5601 A-B - Butadiene Area Oily Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5607 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572 |  | 2019-01-03 | 2
036909C-1056-PDS-0900-5608 | Process Equipment Datasheet - 10-P-5602 A-B - QW Area Oily Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5608 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572 |  | 2019-01-03 | 2
036909C-1056-PDS-0900-5609 | Process Equipment Datasheet - 10-P-5603 A-B - CGC Area Oily Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5609 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572 |  | 2019-01-03 | 2
036909C-1056-PDS-0900-5613 | Process Equipment Datasheet - 10-P-5604 A-B - Refrig Area Oily Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5613 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572 |  | 2019-01-03 | 2
036909C-1056-PDS-0900-5635 | Process Equipment Datasheet - 10-P-5630 A-B - CT Area Oily WWater Sump Pumps | A | 2018-12-26 | IFR | OL1-2G30-5635 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572 |  | 2019-01-03 | 2
036909C-1056-PDS-0900-5648 | Process Equipment Datasheet - 10-P-5606 A-B - C3 Hydrog Area Oily Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5648 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572 |  | 2019-01-03 | 2
036909C-1056-PDS-0900-5636 | Process Equipment Datasheet - 10-P-5631 A-B - CWWT Area Oily WWater Sump Pumps | A | 2018-12-26 | IFR | OL1-2G30-5636 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00572 |  | 2019-01-03 | 2
036909C-1056-PDS-0900-5606 | Process Equipment Datasheet - 10-P-5600 A-B - Pygas Area Only Wastewater Pump | A | 2018-12-26 | IFR | OL1-2G30-5606 | PE | 2019-01-03 | 036909C-JVD-TRN-00572 | 036909C-JVD-TRN-00572 | IFR | 2019-01-17 | 2019-01-22 | R2-Comments as noted | TPSK-LSPA1-T-PE-00572 |  | 2019-01-03 | 2
036909C-1000-TBT-1130-0001 | Technical Bid Evaluation For Residue Gas Expander - Recompressor | 2 | 2019-03-13 | IFI | OL1-2C23-0012 | PL | 2019-03-14 | 036909C-JVD-TRN-01057 | 036909C-JVD-TRN-01057 | IFA | 2019-03-29 |  | Transmitted | TPSL-LSPA1-T-PL-01057 |  | 2019-03-15 | 1
036909C-1000-TBT-1130-0001 | Technical Bid Evaluation For Residue Gas Expander - Recompressor | 1 | 2019-01-28 | IFI | OL1-2C23-0012 | PL | 2019-01-29 | 036909C-JVD-TRN-00747 | 036909C-JVD-TRN-00747 | IFA | 2019-02-13 |  | Transmitted | TPSK-LSPA1-T-PL-00747 |  | 2019-01-29 | 1
036909C-1056-PDS-0900-5637 | Process Equipment Datasheet - 10-P-5632 A-B - HP Flare Area Oily WW Sump Pumps | A | 2018-12-28 | IFR | OL1-2G30-5637 | PE | 2019-01-03 | 036909C-JVD-TRN-00576 | 036909C-JVD-TRN-00576 | IFR | 2019-01-15 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00576 |  | 2019-01-03 | 2
036909C-1056-PDS-0900-5638 | Process Equipment Datasheet - 10-P-5633 A-B - HP Flare Area SW Sump Pumps | A | 2018-12-28 | IFR | OL1-2G30-5638 | PE | 2019-01-03 | 036909C-JVD-TRN-00576 | 036909C-JVD-TRN-00576 | IFR | 2019-01-15 | 2019-01-22 | R1-No comments | TPSK-LSPA1-T-PE-00576 |  | 2019-01-03 | 2
036909C-1025-PDS-0900-2577 | Process Equipment Datasheet - 10-P-2575 A-B - Deethanizer Reboiler Cond Pumps | B | 2018-12-21 | IFD | OL1-2G30-2577 | PE | 2018-12-27 | 036909C-JVD-TRN-00568 | 036909C-JVD-TRN-00568 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00568 |  | 2018-12-27 | 2
036909C-1024-PDS-0900-2457 | Process Equipment Datasheet - 10-P-2455 A-B - LP Deprop Reboiler Cond Pump | B | 2018-12-21 | IFD | OL1-2G30-2457 | PE | 2018-12-27 | 036909C-JVD-TRN-00568 | 036909C-JVD-TRN-00568 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00568 |  | 2018-12-27 | 2
036909C-1024-PDS-0900-2443 | Process Equipment Datasheet - 10-P-2445 A-B - HP Deprop Reboiler Cond Pump | B | 2018-12-21 | IFD | OL1-2G30-2443 | PE | 2018-12-27 | 036909C-JVD-TRN-00568 | 036909C-JVD-TRN-00568 | IFI |  | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00568 |  | 2018-12-27 | 2
036909C-1029-PDS-2500-2910 | Process Equipment Datasheet - 10-TK-2910 - Wash Oil Day Tank | A | 2018-12-20 | IFR | OL1-2G30-2910 | PE | 2018-12-27 | 036909C-JVD-TRN-00561 | 036909C-JVD-TRN-00561 | IFR | 2019-01-11 | 2019-01-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-00561 |  | 2018-12-27 | 2
036909C-1029-PDS-2600-2922 | Process Equipment Datasheet - 10-PK-2922 - Co Injection Pkg | A | 2018-12-20 | IFR | OL1-2G30-2922 | PE | 2018-12-20 | 036909C-JVD-TRN-00560 | 036909C-JVD-TRN-00560 | IFR | 2019-01-03 | 2019-01-14 | R1-No comments | TPSK-LSPA1-T-PE-00560 |  | 2018-12-20 | 2
036909C-1001-DW-1523-0001 | Control and Technical Room Equipment Layout - Central Control Building | B | 2019-08-29 | IDD | OL1-2I46-1001 | IE | 2019-08-30 | 036909C-JVD-TRN-02543 | 036909C-JVD-TRN-02543 | IFA | 2019-09-13 |  | Transmitted | TPSK-LSPA1-T-IE-02543 |  | 2019-09-03 | 1
036909C-1001-DW-1523-0001 | Control and Technical Room Equipment Layout - Central Control Building | A | 2019-05-03 | IFR | OL1-2I46-1001 | IE | 2019-05-06 | 036909C-JVD-TRN-01568 | 036909C-JVD-TRN-01568 | IFA | 2019-05-20 | 2019-05-23 | R2-Comments as noted | TPSK-LSPA1-T-IE-01568 |  | 2019-05-06 | 1
036909C-1000-MR-0910-0007 | Material Requisition For API Centrifugal Pumps | 0 | 2019-08-09 | IFP | OL1-2C13-447000 | PL | 2019-08-09 | 036909C-JVD-TRN-02408 | 036909C-JVD-TRN-02408 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-PL-02408 |  | 2019-08-14 | 2
036909C-1011-MR-1545-2002 | Material Requisition for Pressure Relief Valves | A | 2019-04-11 | IFQ | OL1-2C17-072002 | PL | 2019-04-22 | 036909C-JVD-TRN-01427 | 036909C-JVD-TRN-01427 | IFI |  | 2019-05-28 | R2-Comments as noted | TPSK-LSPA1-T-PL-01427 |  | 2019-04-23 | 3
036909C-1011-MR-1545-2002 | Material Requisition for Pressure Relief Valves | 0 | 2019-07-31 | IFP | OL1-2C17-072002 | PL | 2019-08-05 | 036909C-JVD-TRN-02351 | 036909C-JVD-TRN-02351 | IFR | 2019-08-20 |  | Transmitted | TPSK-LSPA1-T-PL-02351 |  | 2019-08-06 | 2
036909C-1011-SP-1545-1002 | Instrument Datasheet for Pressure Relief Valve | 0 | 2019-07-31 | IFP | OL1-2I20-1002 | IE | 2019-08-05 | 036909C-JVD-TRN-02350 | 036909C-JVD-TRN-02350, 036909C-JVD-TRN-02351 | IFR | 2019-08-20 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-IE-02350 |  | 2019-08-06 | 2
036909C-1000-MR-0910-0002 | Material Requisition For API Centrifugal Pumps | 0 | 2019-08-09 | IFP | OL1-2C13-442000 | PL | 2019-08-09 | 036909C-JVD-TRN-02408 | 036909C-JVD-TRN-02408 | IFR | 2019-08-26 |  | Transmitted | TPSK-LSPA1-T-PL-02408 |  | 2019-08-14 | 2
036909C-1000-JSD-1600-003 | General Design Rule for Package Equipment Electrical System - Ex Client code OL1-2R05-0042 | B | 2018-09-20 | IFR | OL1-2E04-6000 | EE | 2018-10-04 | 036909C-JVD-TRN-00126 | 036909C-JVD-TRN-00126, ROC-TPSK-CECO-T-00004 | IFR | 2018-10-18 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-EE-00126 | Ex Document Client Reference OL1-2R05-0042 | 2018-10-04 | 2
036909C-1000-JSD-1580-0003 | General Design Rules For Instrumentation And Control Of Packaged Equipment | 1 | 2019-04-09 | IMP | OL1-2R06-0035 | IE | 2019-04-11 | 036909C-JVD-TRN-01320 | 036909C-JVD-TRN-01320 | IFR | 2019-04-26 | 2019-05-09 | R1-No comments | TPSK-LSPA1-T-IE-01320 |  | 2019-04-12 | 2
036909C-1000-NM-617 | Monthly Complete Expediting Report | 1 | 2019-04-16 | IFI | OL1-2C95-0002 | PL | 2019-04-19 | 036909C-JVD-TRN-01419 | 036909C-JVD-TRN-01419 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-01419 |  | 2019-04-19 | 2
036909C-1000-MR-2511-0002 | MATERIAL REQUISITION FOR FRP TANK | A | 2019-05-08 | IFI | OL1-2C13-202000 | PL | 2019-05-13 | 036909C-JVD-TRN-01646 | 036909C-JVD-TRN-01646 | IFI | 2019-05-24 | 2019-05-31 | R2-Comments as noted | TPSK-LSPA1-T-PL-01646 |  | 2019-05-13 | 2
036909C-1000-STC-1890-0001 | Construction Standards For Steel Structures | 1 | 2019-06-25 | IFC | OL1-2K21-0001 | CV | 2019-07-02 | 036909C-JVD-TRN-02051 | 036909C-JVD-TRN-02051 | IFA | 2019-07-17 | 2019-08-29 | A1-Approved without comments | TPSK-LSPA1-T-CV-02051 |  | 2019-07-03 | 1
036909C-1000-STC-1890-080 | Construction Standards For Ladders & Platforms Attached To Pressure Equipment | 0 | 2018-10-01 | IMP | OL1-2R03-0055 | ME | 2018-10-03 | 036909C-JVD-TRN-00120 | 036909C-JVD-TRN-00120, ROC-TPSK-CECO-T-00004 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00120 |  | 2018-10-04 | 3
036909C-1000-JSD-1700-0001 | Job Design Specification For Foundations And Structures | 1 | 2019-06-26 | IMP | OL1-2R02-0004 | CV | 2019-07-03 | 036909C-JVD-TRN-02066 | 036909C-JVD-TRN-02066 | IFA | 2019-07-18 | 2019-08-29 | R1-No comments | TPSK-LSPA1-T-CV-02066 |  | 2019-07-04 | 2
036909C-1011-SP-1552-1005 | Instrument Datasheets for Level Gauge | 0 | 2019-08-07 | IFP | OL1-2I20-1005 | IE | 2019-08-12 | 036909C-JVD-TRN-02414 | 036909C-JVD-TRN-02414 | IFR | 2019-08-27 | 2019-09-19 | R2-Comments as noted | TPSK-LSPA1-T-IE-02414 |  | 2019-08-14 | 2
036909C-1012-MR-1553-1254 | Material Requisition for Pressure Gauge | A | 2019-08-27 | IFQ | OL1-2C17-042254 | PL | 2019-09-04 | 036909C-JVD-TRN-02572 | 036909C-JVD-TRN-02572 | IFR | 2019-09-19 | 2019-09-19 | R1-No comments | TPSK-LSPA1-T-PL-02572 |  | 2019-09-05 | 2
036909C-1000-MS-1320-0051 | Construction Specification For Piping Prefabrication Erection And Non Descructive Examination | 0 | 2019-05-17 | IFC | OL1-2P92-0007 | MP | 2019-05-23 | 036909C-JVD-TRN-01726 | 036909C-JVD-TRN-01726 | IFR | 2019-06-07 | 2019-06-14 | R1-No comments | TPSK-LSPA1-T-MP-01726 |  | 2019-05-24 | 2
036909C-1000-CN-1901-0001 | Fire Water Demand Calculation And Hydraulic Study For FW Network | 0 | 2019-07-18 | IMP | OL1-2L20-0001 | SE | 2019-07-19 | 036909C-JVD-TRN-02200 | 036909C-JVD-TRN-02200 | IFA | 2019-08-05 | 2019-09-10 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-SE-02200 |  | 2019-07-22 | 1
036909C-1051-SP-1541-5107 | Instrument Datasheets for Control Valve - Angle Type - Area 51 | A | 2019-06-10 | IFQ | OL1-2I20-5117 | IE | 2019-06-12 | 036909C-JVD-TRN-01878 | 036909C-JVD-TRN-01878 | IFI |  | 2019-07-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-01878 |  | 2019-06-14 | 3
036909C-1011-SP-1546-1153 | Instrument Datasheets for Orifice Plate & Restriction Orifice | 0 | 2019-09-12 | IFP | OL1-2I20-1153 | IE | 2019-09-13 | 036909C-JVD-TRN-02643 | 036909C-JVD-TRN-02643 | IFR | 2019-09-28 |  | Transmitted | TPSK-LSPA1-T-IE-02643 |  | 2019-09-17 | 2
036909C-1012-MR-1546-1253 | Material Requisition for Orifice Plate & Restriction Orifice | 0 | 2019-09-12 | IFP | OL1-2C17-012253 | PL | 2019-09-13 | 036909C-JVD-TRN-02644 | 036909C-JVD-TRN-02644 | IFR | 2019-09-28 |  | Transmitted | TPSK-LSPA1-T-PL-02644 |  | 2019-09-17 | 2
036909C-1000-DW-1532-0004 | TELECOM SYSTEM ARCHITECTURE OF SAFETY SUPERVISORY SYSTEM | 0 | 2019-08-29 | IMP | OL1-2T31-0001 | EE | 2019-08-30 | 036909C-JVD-TRN-02547 | 036909C-JVD-TRN-02547 | IFA | 2019-09-13 |  | Transmitted | TPSK-LSPA1-T-EE-02547 |  | 2019-09-03 | 1
036909C-1000-JSD-1530-0002 | Safety Supervisory System | 1 | 2019-07-17 | IMP | OL1-2R05-0019 | EE | 2019-07-18 | 036909C-JVD-TRN-02179 | 036909C-JVD-TRN-02179 | IFR |  | 2019-07-30 | R1-No comments | TPSK-LSPA1-T-EE-02179 |  | 2019-07-19 | 2
036909C-1000-MR-1013-0001 | Material Requisition for Integrally Geared Decoking Air Compressors - Ex Document Client Reference OL1-2M55-0014 | 0 | 2019-05-22 | IFP | OL1-2C13-402000 | PL | 2019-05-22 | 036909C-JVD-TRN-01720 | 036909C-JVD-TRN-01720 | IFA | 2019-06-06 | 2019-06-17 | R2-Comments as noted | TPSK-LSPA1-T-PL-01720 | Ex Document Client Reference OL1-2M55-0014 Included closure to comments for document ex document Client n OL1-2M07-0014 Rev A | 2019-05-23 | 1
036909C-1000-TBT-1011-0001 | Technical Bid Evaluation For Centrifugal Compressor Steam Turbine Driven | 1 | 2019-02-26 | IFI | OL1-2C23-0008 | PL | 2019-02-28 | 036909C-JVD-TRN-00947 | 036909C-JVD-TRN-00947 | IFA | 2019-03-15 |  | Transmitted | TPSK-LSPA1-T-PL-00947 |  | 2019-03-01 | 1
036909C-1000-DW-1532-0003 | Telecomm System Architecture Of Intercom Paging And Audible Alarm Systems | 0 | 2019-08-09 | IMP | OL1-2T11-0001 | EE | 2019-08-14 | 036909C-JVD-TRN-02433 | 036909C-JVD-TRN-02433 | IFR | 2019-08-14 | 2019-09-16 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-EE-02433 |  | 2019-08-15 | 1