## Document
Document Reference | Document Title | Revision Number | Revision Date | Document Revision Object | Document Client Reference | Discipline | Transmittal Date | Transmittal Reference | Specific Transmittal Number | Required Action | Response Due Date | Actual Response Date | Document Status | Client Transmittal Ref Number | Remarks | Client Transmittal Date | Document Class
036909C-102A-DW-1572-0107 | Zone 2A Telecom Main Cable Tray Routing Quench | A | 2019-08-30 | IFR | OL1-2T12-0107 | EE | 2019-09-25 | 036909C-JVD-TRN-02715 | 036909C-JVD-TRN-02715 | IFA | 2019-10-10 | 2019-10-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02715 |  | 2019-09-28 | 1
036909C-1059-PDS-2500-5950 | Sodium Hypochlorite Tank PDS | E | 2019-09-20 | IFD | OL1-2G30-5950 | PE | 2019-09-24 | 036909C-JVD-TRN-02701 | 036909C-JVD-TRN-02701 | IFR | 2019-10-09 | 2019-10-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-02701 |  | 2019-09-25 | 2
036909C-1059-PDS-2500-5900 | Sulfuric Acid Tank PDS | C | 2019-09-20 | IFD | OL1-2G30-5900 | PE | 2019-09-24 | 036909C-JVD-TRN-02701 | 036909C-JVD-TRN-02701 | IFR | 2019-10-09 | 2019-10-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-02701 |  | 2019-09-25 | 2
036909C-1051-PDS-2500-5120 | Raw Condensate Tank PDS | C | 2019-09-20 | IFD | OL1-2G30-5120 | PE | 2019-09-24 | 036909C-JVD-TRN-02701 | 036909C-JVD-TRN-02701 | IFR | 2019-10-09 | 2019-10-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-02701 |  | 2019-09-25 | 2
036909C-1051-PDS-2500-5110 | Condensate Tank PDS | C | 2019-09-20 | IFD | OL1-2G30-5110 | PE | 2019-09-24 | 036909C-JVD-TRN-02701 | 036909C-JVD-TRN-02701 | IFR | 2019-10-09 | 2019-10-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-02701 |  | 2019-09-25 | 2
036909C-1030-TDS-0610-3081 | Mechanical Equipment Data Sheet - 10-E-3080 - Butadiene Tower Condenser | 0 | 2019-10-03 | IFP | OL1-2M03-3081 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3084 | Mechanical Equipment Data Sheet - 10-E-3084 - Butadiene Tower Trim Reboiler | 0 | 2019-09-26 | IFP | OL1-2M03-3084 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3055 | Mechanical Equipment Data Sheet - 10-E-3055 - Degasser Reboiler | 0 | 2019-10-03 | IFP | OL1-2M03-3055 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3071 | Mechanical Equipment Data Sheet - 10-E-3070 - Water - NMP Cooler | 0 | 2019-09-26 | IFP | OL1-2M03-3071 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3063 | Mechanical Equipment Data Sheet - 10-E-3060 - C4 Acetylene Washer Condenser | 0 | 2019-10-10 | IFP | OL1-2M03-3063 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1031-TDS-0610-3160 | Mechanical Equipment Data Sheet - 10-E-3160 - BDU Condensate Cooler | 0 | 2019-09-26 | IFP | OL1-2M03-3160 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3095 | Mechanical Equipment Data Sheet - 10-E-3095 - Butadiene Drying Tower Reboiler | 0 | 2019-10-10 | IFP | OL1-2M03-3095 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1031-TDS-0610-3150 | Mechanical Equipment Data Sheet - 10-E-3150 - BDU Condensate Heater | 0 | 2019-10-10 | IFP | OL1-2M03-3150 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3085 | Mechanical Equipment Data Sheet - 10-E-3085 - Butadiene Tower Reboiler | 0 | 2019-09-26 | IFP | OL1-2M03-3085 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3098 | Mechanical Equipment Data Sheet - 10-E-3098 - Butadiene Product Subcooler | 0 | 2019-10-03 | IFP | OL1-2M03-3098 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1031-TDS-0610-3111 | Mechanical Equipment Data Sheet - 10-E-3110 - Water Washer Condenser | 0 | 2019-09-26 | IFP | OL1-2M03-3111 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3001 | Mechanical Equipment Data Sheet - 10-E-3000 - Predistillation Tower Condenser | 0 | 2019-09-26 | IFP | OL1-2M03-3001 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-15 | 2
036909C-1030-TDS-0610-3004 | Mechanical Equipment Data Sheet - 10-E-3004 - Predistillation Tower Trim Reboiler | 0 | 2019-09-26 | IFP | OL1-2M03-3004 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-15 | 2
036909C-1030-TDS-0610-3014 | Mechanical Equipment Data Sheet - 10-E-3014 - C4 Solvent Vaporizer | 0 | 2019-09-26 | IFP | OL1-2M03-3014 |  | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3062 | Mechanical Equipment Data Sheet - 10-E-3062 - Acetylene Condenser | 0 | 2019-10-10 | IFP | OL1-2M03-3062 |  | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3018 | Mechanical Equipment Data Sheet - 10-E-3018 - Solvent Cooler | 0 | 2019-09-26 | IFP | OL1-2M03-3018 |  | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3031 | Mechanical Equipment Data Sheet - 10-E-3030 -After Washer Condenser | 0 | 2019-10-10 | IFP | OL1-2M03-3031 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3045 | Mechanical Equipment Data Sheet - 10-E-3045 A-D- Solvent Heat Exchanger | 0 | 2019-09-26 | IFP | OL1-2M03-3045 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3044 | Mechanical Equipment Data Sheet - 10-E-3044 - Solvent Heater | 0 | 2019-09-26 | IFP | OL1-2M03-3044 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3005 | Mechanical Equipment Data Sheet - 10-E-3005- Predistillation Tower Reboiler | 0 | 2019-09-26 | IFP | OL1-2M03-3005 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3021 | Mechanical Equipment Data Sheet - 10-E-3020 - Main Washer Condenser | 0 | 2019-09-26 | IFP | OL1-2M03-3021 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1030-TDS-0610-3015 | Mechanical Equipment Data Sheet - 10-E-3015 - C4 Trim Vaporizer | 0 | 2019-09-26 | IFP | OL1-2M03-3015 | ME | 2019-10-14 | 036909C-JVD-TRN-02828 | 036909C-JVD-TRN-02828 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02828 |  | 2019-10-16 | 2
036909C-1000-NM-0001-1013 | Heat and Material Balance - 56 Waste Water Treatment System | 2 | 2019-09-10 | IFI | OL1-2G44-1013 | PE | 2019-09-24 | 036909C-JVD-TRN-02705 | 036909C-JVD-TRN-02705 | IFI |  | 2019-10-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-02705 |  | 2019-09-25 | 3
036909C-1000-ML-1003 | C3 Hydrogenation Unit Operating Manual | 0 | 2019-09-24 | IFI | OL1-2G76-1003 | PE | 2019-09-24 | 036909C-JVD-TRN-02699 | 036909C-JVD-TRN-02699 | IFI |  | 2019-10-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-02699 |  | 2019-09-25 | 3
036909C-1000-ML-103 | Firefighting Technical Design Dossier (Approved by VFFPD) | 0 | 2019-09-20 | IFI | OL1-2A19-0004 | CO | 2019-09-24 | 036909C-JVD-TRN-02693 | 036909C-JVD-TRN-02693 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CO-02693 |  | 2019-09-26 | 3
036909C-1000-PP-863 | Site Work Permit Procedure | A | 2019-09-25 | IFR | OL1-2S92-0009 | ES | 2019-09-26 | 036909C-JVD-TRN-02719 | 036909C-JVD-TRN-02719 | IFR | 2019-10-09 |  | Transmitted | TPSK-LSPA1-T-ES-02719 |  | 2019-09-28 | 2
036909C-1000-NM-1551-0001 | Instrument List | B | 2019-10-14 | IDD | OL1-2I91-0001 | IE | 2019-10-15 | 036909C-JVD-TRN-02842 | 036909C-JVD-TRN-02842 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-IE-02842 |  | 2019-10-15 | 1
036909C-1000-EL-001 | Item Index - Excluding Furnaces Island - Area 1A | C | 2019-09-20 | IFR | OL1-2M91-0001 | ME | 2019-09-25 | 036909C-JVD-TRN-02708 | 036909C-JVD-TRN-02708 | IFR | 2019-10-10 | 2019-10-09 | R1-No comments | TPSK-LSPA1-T-ME-02708 |  | 2019-09-27 | 2
036909C-1000-PID-0090-0018 | P&ID- Olefins Unit 10- Common- Typicals For ON-OFF Valves-2 | A | 2019-09-17 | IDD1 | OL1-2G43-0018 | PE | 2019-09-25 | 036909C-JVD-TRN-02709 | 036909C-JVD-TRN-02709 | IFR | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-PE-02709 |  | 2019-09-27 | 2
036909C-1000-DI-0007-0002 | Equipment Basis of Design | C | 2019-09-27 | IFD | OL1-2G02-0002 | PE | 2019-09-27 | 036909C-JVD-TRN-02734 | 036909C-JVD-TRN-02734 | IFA | 2019-10-12 |  | Transmitted | TPSK-LSPA1-T-PE-02734 |  | 2019-10-04 | 1
036909C-1000-PID-0090-0019 | P&ID- Olefins Unit 10- Common- Typicals For Control Valves | A | 2019-09-17 | IDD1 | OL1-2G43-0019 | PE | 2019-09-25 | 036909C-JVD-TRN-02709 | 036909C-JVD-TRN-02709 | IFR | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-PE-02709 |  | 2019-09-27 | 2
036909C-1000-PID-0090-0013 | P&ID- Olefins Unit 10- Common- Typicals For Motors | A | 2019-09-17 | IDD1 | OL1-2G43-0013 | PE | 2019-09-25 | 036909C-JVD-TRN-02709 | 036909C-JVD-TRN-02709 | IFR | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-PE-02709 |  | 2019-09-27 | 2
036909C-1000-PID-0090-0017 | P&ID- Olefins Unit 10- Common- Typicals For ON-OFF Valves-1 | A | 2019-09-17 | IDD1 | OL1-2G43-0017 | PE | 2019-09-25 | 036909C-JVD-TRN-02709 | 036909C-JVD-TRN-02709 | IFR | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-PE-02709 |  | 2019-09-27 | 2
036909C-1000-PID-0090-0014 | P&ID- Olefins Unit 10- Common- Typicals For Motors | A | 2019-09-17 | IDD1 | OL1-2G43-0014 | PE | 2019-09-25 | 036909C-JVD-TRN-02709 | 036909C-JVD-TRN-02709 | IFR | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-PE-02709 |  | 2019-09-27 | 2
036909C-1000-PID-0090-0001 | P&ID- Olefins Unit 10- Common- Abreviations And Numbering | C | 2019-09-17 | IDD1 | OL1-2G43-0001 | PE | 2019-09-25 | 036909C-JVD-TRN-02709 | 036909C-JVD-TRN-02709 | IFR | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-PE-02709 |  | 2019-09-27 | 2
036909C-1000-PID-0090-0005 | P&ID- Olefins Unit 10- Common- Equipment Symbols 2 | C | 2019-09-17 | IDD1 | OL1-2G43-0005 | PE | 2019-09-25 | 036909C-JVD-TRN-02709 | 036909C-JVD-TRN-02709 | IFR | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-PE-02709 |  | 2019-09-27 | 2
036909C-1000-PID-0090-0011 | P&ID- Olefins Unit 10- Common-EIV Block Valve Typical | 0 | 2019-09-17 | CAN | OL1-2G43-0011 | PE | 2019-09-25 | 036909C-JVD-TRN-02709 | 036909C-JVD-TRN-02709 | IFR | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-PE-02709 |  | 2019-09-27 | 2
036909C-1000-PID-0090-0010 | P&ID- Olefins Unit 10- Common-Instrument Details | C | 2019-09-17 | IDD1 | OL1-2G43-0010 | PE | 2019-09-25 | 036909C-JVD-TRN-02709 | 036909C-JVD-TRN-02709 | IFR | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-PE-02709 |  | 2019-09-27 | 2
036909C-1000-PID-0090-0002 | P&ID- Olefins Unit 10- Common- Piping Symbols | C | 2019-09-17 | IDD1 | OL1-2G43-0002 | PE | 2019-09-25 | 036909C-JVD-TRN-02709 | 036909C-JVD-TRN-02709 | IFR | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-PE-02709 |  | 2019-09-27 | 2
036909C-1000-PID-0090-0004 | P&ID- Olefins Unit 10- Common- Equipment Symbols 1 | C | 2019-09-17 | IDD1 | OL1-2G43-0004 | PE | 2019-09-25 | 036909C-JVD-TRN-02709 | 036909C-JVD-TRN-02709 | IFR | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-PE-02709 |  | 2019-09-27 | 2
036909C-1000-PID-0090-0003 | P&ID- Olefins Unit 10- Common- Instrumentation Symbols | C | 2019-09-17 | IDD1 | OL1-2G43-0003 | PE | 2019-09-25 | 036909C-JVD-TRN-02709 | 036909C-JVD-TRN-02709 | IFR | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-PE-02709 |  | 2019-09-27 | 2
036909C-1000-MR-1546-0001 | Material Requisition For Orifice And Restriction Orifice | A | 2019-09-20 | IFQ | OL1-2C17-010101 | PL | 2019-10-15 | 036909C-JVD-TRN-02847 | 036909C-JVD-TRN-02847 | IFR | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-PL-02847 |  | 2019-10-15 | 2
036909C-1056-PDS-0200-5642 | Process Equipment Datasheet - 10-PIT-5642 - Cooling Water Blowdown Basin | C | 2019-09-19 | IFD | OL1-2G30-5642 | PE | 2019-09-20 | 036909C-JVD-TRN-02673 | 036909C-JVD-TRN-02672, 036909C-JVD-TRN-02673 | IFR | 2019-10-07 | 2019-10-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-02673 |  | 2019-09-24 | 2
036909C-1056-PDS-0200-5620 | Process Equipment Datasheet - 10-PIT-5620 A-C - Olefins Holding Basin | D | 2019-09-19 | IFD | OL1-2G30-5620 | PE | 2019-09-20 | 036909C-JVD-TRN-02673 | 036909C-JVD-TRN-02672, 036909C-JVD-TRN-02673 | IFR | 2019-10-07 | 2019-10-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-02673 |  | 2019-09-24 | 2
036909C-1056-PDS-0200-5615 | Process Equipment Datasheet - 10-PIT-5615 - Olefins Stormwater Sump | D | 2019-09-19 | IFD | OL1-2G30-5615 | PE | 2019-09-20 | 036909C-JVD-TRN-02673 | 036909C-JVD-TRN-02672, 036909C-JVD-TRN-02673 | IFR | 2019-10-07 | 2019-10-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-02673 |  | 2019-09-24 | 2
036909C-1056-PID-0031-5652 | P&ID - Olefins Unit 10 - Wastewater - Cooling Water Blowdown Basin | C | 2019-09-17 | IDD1 | OL1-2G43-5652 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1056-PID-0031-5649 | P&ID - Olefins Unit 10 - Wastewater - HP Flare Area Oily Wastewater Sump | 0 | 2019-09-17 | CAN | OL1-2G43-5649 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R1-No comments | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1056-PID-0031-5632 | P&ID - Olefins Unit 10 - Wastewater - Skimmed Oil Sump | A | 2019-09-17 | IDD1 | OL1-2G43-5632 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1056-PID-0031-5620 | P&ID - Olefins Unit 10 - Wastewater - Olefins Storm Water Collection | C | 2019-09-17 | IDD1 | OL1-2G43-5620 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1055-PID-0031-5520 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 1 | C | 2019-09-17 | IDD1 | OL1-2G43-5520 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1055-PID-0031-5512 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 3 | C | 2019-09-17 | IDD1 | OL1-2G43-5512 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5168 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Steam LS2 Distribution - Sheet 1 | C | 2019-09-17 | IDD1 | OL1-2G43-5168 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5166 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 6 | C | 2019-09-17 | IDD1 | OL1-2G43-5166 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5164 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 5 | C | 2019-09-17 | IDD1 | OL1-2G43-5164 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5163 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 4 | C | 2019-09-17 | IDD1 | OL1-2G43-5163 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5162 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 3 | C | 2019-09-17 | IDD1 | OL1-2G43-5162 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5161 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 2 | C | 2019-09-17 | IDD1 | OL1-2G43-5161 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5160 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 1 | C | 2019-09-17 | IDD1 | OL1-2G43-5160 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5152 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Steam Distribution - Sheet 3 | C | 2019-09-17 | IDD1 | OL1-2G43-5152 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5151 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Steam Distribution - Sheet 2 | C | 2019-09-17 | IDD1 | OL1-2G43-5151 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5150 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Steam Distribution - Sheet 01 | C | 2019-09-17 | IDD1 | OL1-2G43-5150 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5144 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - HP Steam Distribution - Sheet 02 | C | 2019-09-17 | IDD1 | OL1-2G43-5144 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5143 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - HP Steam Distribtion - Sheet 1 | C | 2019-09-17 | IDD1 | OL1-2G43-5143 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5114 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP BFW Distribution | C | 2019-09-17 | IDD1 | OL1-2G43-5114 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5113 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP & HP BFW Distribution | C | 2019-09-17 | IDD1 | OL1-2G43-5113 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5103 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Station - Sheet 3 | C | 2019-09-17 | IDD1 | OL1-2G43-5103 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5102 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Stations - Sheet 2 | C | 2019-09-17 | IDD1 | OL1-2G43-5102 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1051-PID-0031-5101 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Stations - Sheet 1 | C | 2019-09-17 | IDD1 | OL1-2G43-5101 | PE | 2019-09-23 | 036909C-JVD-TRN-02680 | 036909C-JVD-TRN-02680 | IFR | 2019-10-08 | 2019-10-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-02680 |  | 2019-09-25 | 2
036909C-1056-PID-0021-5691 | PID Olefins Unit 10 Wastewater Domestic - Neutralization - Oily Waste Water B.L. | A | 2019-09-09 | IDD1 | OL1-3G43-5691 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1056-PID-0021-5690 | PID Olefins Unit 10 Wastewater Oily-Treated-CW- BD-Domestic-Mixed Wastewater BL | A | 2019-09-09 | IDD1 | OL1-3G43-5690 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1052-PID-0021-5290 | PID Olefins Unit 10 Fuel System Pilot Gas And Fuel Gas Battery Limit | A | 2019-09-09 | IDD1 | OL1-3G43-5290 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5542 | PID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 4 | C | 2019-09-09 | IDD1 | OL1-2G43-5542 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5540 | PID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 3 | C | 2019-09-09 | IDD1 | OL1-2G43-5540 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5536 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 2 | C | 2019-09-09 | IDD1 | OL1-2G43-5536 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5535 | PID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 1 | C | 2019-09-09 | IDD1 | OL1-2G43-5535 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5534 | PID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 4 | C | 2019-09-09 | IDD1 | OL1-2G43-5534 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5533 | PID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 3 | C | 2019-08-07 | IDD1 | OL1-2G43-5533 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5531 | PID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 2 | C | 2019-09-09 | IDD1 | OL1-2G43-5531 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5529 | PID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 1 | C | 2019-09-09 | IDD1 | OL1-2G43-5529 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5528 | PID - Olefins Unit 10 - Vent Gas And Flare System - Propylene Blowdown Header - Sheet 2 | C | 2019-09-09 | IDD1 | OL1-2G43-5528 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5526 | PID - Olefins Unit 10 - Vent Gas And Flare System - Propylene Blowdown Header - Sheet 1 | C | 2019-09-09 | IDD1 | OL1-2G43-5526 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5524 | PID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 4 | C | 2019-09-09 | IDD1 | OL1-2G43-5524 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5523 | PID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 3 | C | 2019-09-09 | IDD1 | OL1-2G43-5523 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5521 | PID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 2 | C | 2019-09-09 | IDD1 | OL1-2G43-5521 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5519 | PID - Olefins Unit 10 - Vent Gas And Flare System - LP Flare Header - Sheet 1 | C | 2019-08-07 | IDD1 | OL1-2G43-5519 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5518 | PID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 6 | C | 2019-09-09 | IDD1 | OL1-2G43-5518 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5516 | PID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 5 | C | 2019-09-09 | IDD1 | OL1-2G43-5516 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5514 | PID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 4 | C | 2019-08-07 | IDD1 | OL1-2G43-5514 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5511 | PID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 2 | C | 2019-09-09 | IDD1 | OL1-2G43-5511 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5510 | PID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 1 | C | 2019-09-09 | IDD1 | OL1-2G43-5510 | PE | 2019-09-16 | 036909C-JVD-TRN-02651 | 036909C-JVD-TRN-02651 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02651 |  | 2019-09-17 | 2
036909C-1056-PID-0031-5656 | PID - Olefins Unit 10 - Wastewater - Domestic Wastewater Collection | C | 2019-09-09 | IDD1 | OL1-2G43-5656 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1056-PID-0031-5654 | PID - Olefins Unit 10 - Wastewater - Oily Waste Water Tank | C | 2019-09-09 | IDD1 | OL1-2G43-5654 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1056-PID-0031-5653 | PID - Olefins Unit 10 - Wastewater - Oily Waste Water Distribution | C | 2019-08-07 | IDD1 | OL1-2G43-5653 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1056-PID-0031-5631 | PID - Olefins Unit 10 - Wastewater - Olefins Holding Basin - Sheet 2 | C | 2019-09-09 | IDD1 | OL1-2G43-5631 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1056-PID-0031-5630 | PID - Olefins Unit 10 - Wastewater - Olefins Holding Basin - Sheet 1 | C | 2019-09-09 | IDD1 | OL1-2G43-5630 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5546 | PID - Olefins Unit 10 - Vent Gas And Flare System - Vent Collection System - Sheet 2 | C | 2019-09-09 | IDD1 | OL1-2G43-5546 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1055-PID-0031-5545 | PID - Olefins Unit 10 - Vent Gas And Flare System - Vent Collection System - Sheet 1 | C | 2019-09-09 | IDD1 | OL1-2G43-5545 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1052-PID-0031-5211 | PID - Olefins Unit 10 - Fuel System - Fuel Gas Distribution - Sheet 2 | C | 2019-09-09 | IDD1 | OL1-2G43-5211 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1052-PID-0031-5210 | PID - Olefins Unit 10 - Fuel System - Fuel Gas Distribution - Sheet 1 | C | 2019-08-07 | IDD1 | OL1-2G43-5210 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1052-PID-0031-5203 | PID - Olefins Unit 10 - Fuel System - Pilot Gas Vaporizer | C | 2019-09-09 | IDD1 | OL1-2G43-5203 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1052-PID-0031-5202 | PID - Olefins Unit 10 - Fuel System - Fuel Gas Drum | C | 2019-09-09 | IDD1 | OL1-2G43-5202 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1052-PID-0031-5201 | PID - Olefins Unit 10 - Fuel System - Fuel Gas | C | 2019-09-09 | IDD1 | OL1-2G43-5201 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1051-PID-0031-5179 | PID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Condensate Collection | C | 2019-09-09 | IDD1 | OL1-2G43-5179 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1051-PID-0031-5178 | PID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 3 | C | 2019-09-09 | IDD1 | OL1-2G43-5178 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1051-PID-0031-5177 | PID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 2 | C | 2019-08-07 | IDD1 | OL1-2G43-5177 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1051-PID-0031-5176 | PID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 1 | C | 2019-09-09 | IDD1 | OL1-2G43-5176 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1051-PID-0031-5172 | PID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Condensate Collection | C | 2019-09-09 | IDD1 | OL1-2G43-5172 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1051-PID-0031-5170 | PID - Instrument Diagram Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP - HP Condensate Collection | C | 2019-09-09 | IDD1 | OL1-2G43-5170 | PE | 2019-09-16 | 036909C-JVD-TRN-02649 | 036909C-JVD-TRN-02649 | IFR | 2019-10-01 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PE-02649 |  | 2019-09-17 | 2
036909C-1030-SP-0810-3003 | Mechanical Equipment Data Sheet for Predistillation Tower Reflux Drum | 0 | 2019-10-10 | IFP | OL1-2M03-3003 | MECHANICAL | 2019-10-15 | 036909C-JVD-TRN-02861 | 036909C-JVD-TRN-02861 | IFR | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-ME-02861 |  | 2019-10-20 | 2
036909C-1030-SP-0810-3002 | Mechanical Equipment Data Sheet for Predistillation Feed Drum | 0 | 2019-10-10 | IFP | OL1-2M03-3002 | MECHANICAL | 2019-10-15 | 036909C-JVD-TRN-02861 | 036909C-JVD-TRN-02861 | IFR | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-ME-02861 |  | 2019-10-20 | 2
036909C-1030-SP-0810-3022 | Mechanical Equipment Data Sheet for Main Washer Reflux Drum | 0 | 2019-10-11 | IFP | OL1-2M03-3022 | MECHANICAL | 2019-10-15 | 036909C-JVD-TRN-02861 | 036909C-JVD-TRN-02861 | IFR | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-ME-02861 |  | 2019-10-20 | 2
036909C-102E-DW-0051-0001 | Detail Plot Plan - Zone 2E - Cracked Gas Compressor | D | 2019-10-14 | IDD | OL1-2P06-0012 | MP | 2019-10-15 | 036909C-JVD-TRN-02860 | 036909C-JVD-TRN-02860 | IFR | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-MP-02860 |  | 2019-10-20 | 2
036909C-102D-DW-0051-0001 | Detail Plot Plan - Zone 2D - Process Cold Compressor | D | 2019-10-14 | IDD | OL1-2P06-0011 | MP | 2019-10-15 | 036909C-JVD-TRN-02860 | 036909C-JVD-TRN-02860 | IFR | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-MP-02860 |  | 2019-10-20 | 2
036909C-102B-DW-0051-0001 | Detail Plot Plan - Zone 2B - C3 Hydrogenation | D | 2019-10-14 | IDD | OL1-2P06-0009 | MP | 2019-10-15 | 036909C-JVD-TRN-02860 | 036909C-JVD-TRN-02860 | IFR | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-MP-02860 |  | 2019-10-20 | 2
036909C-101B-DW-0051-0001 | Detail Plot Plan - Zone 1B - Furnaces Utilities | D | 2019-10-14 | IDD | OL1-2P06-0007 | MP | 2019-10-15 | 036909C-JVD-TRN-02860 | 036909C-JVD-TRN-02860 | IFR | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-MP-02860 |  | 2019-10-20 | 2
036909C-102A-DW-0051-0001 | Detail Plot Plan - Zone 2A - Quench | D | 2019-10-14 | IDD | OL1-2P06-0008 | MP | 2019-10-15 | 036909C-JVD-TRN-02860 | 036909C-JVD-TRN-02860 | IFR | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-MP-02860 |  | 2019-10-20 | 2
036909C-100P-DW-0051-0001 | Unit Plot Plan - Zone 0P - Main Pipe Rack | D | 2019-10-14 | IDD | OL1-2P06-0003 | MP | 2019-10-15 | 036909C-JVD-TRN-02860 | 036909C-JVD-TRN-02860 | IFR | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-MP-02860 |  | 2019-10-20 | 2
036909C-1000-DW-0051-0001 | General Plot Plan | E | 2019-10-14 | IDD | OL1-2P06-0001 | MP | 2019-10-15 | 036909C-JVD-TRN-02860 | 036909C-JVD-TRN-02860 | IFR | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-MP-02860 |  | 2019-10-20 | 2
036909C-103S-DW-1572-0005 | Instrument Main Cable Tray Routing SUB C And FAR C | B | 2019-10-10 | IBD | OL1-2I34-0005 | IE | 2019-10-14 | 036909C-JVD-TRN-02829 | 036909C-JVD-TRN-02829 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-IE-02829 |  | 2019-10-17 | 1
036909C-1039-MSD-0011-3901 | Material Selection Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage | B | 2019-10-11 | IFD | OL1-2G74-3901 | PE | 2019-10-15 | 036909C-JVD-TRN-02850 | 036909C-JVD-TRN-02850 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02850 |  | 2019-10-20 | 3
036909C-1031-MSD-0011-3101 | Material Selection Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration | B | 2019-10-11 | IFD | OL1-2G74-3101 | PE | 2019-10-15 | 036909C-JVD-TRN-02850 | 036909C-JVD-TRN-02850 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02850 |  | 2019-10-20 | 3
036909C-1030-MSD-0011-3001 | Material Selection Diagram - Olefins Unit 10 - 30-C4 Unit BDU - Predistillation | B | 2019-10-11 | IFD | OL1-2G74-3001 | PROCESS | 2019-10-15 | 036909C-JVD-TRN-02850 | 036909C-JVD-TRN-02850 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02850 |  | 2019-10-20 | 3
036909C-102E-DW-1572-0011 | Instrument Main Cable Tray Routing Crack Gas Compressor | B | 2019-10-10 | IBD | OL1-2I34-0011 | IE | 2019-10-14 | 036909C-JVD-TRN-02829 | 036909C-JVD-TRN-02829 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-IE-02829 |  | 2019-10-17 | 1
036909C-1012-DW-0131-2703 | USC 132U Cracking Furnace Steel Stair Tower Plans | 0 | 2019-10-11 | IMP | OL1-2K32-2703 | CV | 2019-10-14 | 036909C-JVD-TRN-02826 | 036909C-JVD-TRN-02826 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02826 |  | 2019-10-15 | 3
036909C-101B-DW-1622-0301 | Welding Receptacles Panel Schedule - Zone 1B | A | 2019-10-10 | IFR | OL1-2E42-0025 | EE | 2019-10-11 | 036909C-JVD-TRN-02816 | 036909C-JVD-TRN-02816 | IFR | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-EE-02816 |  | 2019-10-15 | 2
036909C-1012-DW-0131-2702 | USC 132U Cracking Furnace Steel Stair Tower Elevation Views | 0 | 2019-10-11 | IMP | OL1-2K32-2702 | CV | 2019-10-14 | 036909C-JVD-TRN-02826 | 036909C-JVD-TRN-02826 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02826 |  | 2019-10-16 | 3
036909C-1012-DW-0131-2706 | USC 132U Cracking Furnace Steel Stair Tower Plans | 0 | 2019-10-11 | IMP | OL1-2K32-2706 | CV | 2019-10-14 | 036909C-JVD-TRN-02826 | 036909C-JVD-TRN-02826 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02826 |  | 2019-10-15 | 3
036909C-1012-DW-0131-2707 | USC 132U Cracking Furnace Steel Stair Tower Elevation Views | 0 | 2019-10-11 | IMP | OL1-2K32-2707 | CV | 2019-10-14 | 036909C-JVD-TRN-02826 | 036909C-JVD-TRN-02826 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02826 |  | 2019-10-15 | 3
036909C-1012-DW-0131-2704 | USC 132 Cracking Furnace Steel Stair Tower Plans | 0 | 2019-10-11 | IMP | OL1-2K32-2704 | CV | 2019-10-14 | 036909C-JVD-TRN-02826 | 036909C-JVD-TRN-02826 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02826 |  | 2019-10-16 | 3
036909C-1012-DW-0131-2705 | USC 132U Cracking Furnace Steel Stair Tower Plans | 0 | 2019-10-11 | IMP | OL1-2K32-2705 | CV | 2019-10-14 | 036909C-JVD-TRN-02826 | 036909C-JVD-TRN-02826 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02826 |  | 2019-10-16 | 3
036909C-1012-DW-0131-2701 | USC 132U Cracking Furnace Steel Stair Tower Elevation Views | 0 | 2019-10-11 | IMP | OL1-2K32-2701 | CV | 2019-10-14 | 036909C-JVD-TRN-02826 | 036909C-JVD-TRN-02826 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02826 |  | 2019-10-15 | 3
036909C-1000-PP-866 | Site Security Plan | A | 2019-10-08 | IFR | OL1-2S92-0010 | SE | 2019-10-12 | 036909C-JVD-TRN-02822 | 036909C-JVD-TRN-02822 | IFA | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-SE-02822 |  | 2019-10-15 | 1
036909C-100C-CN-1733-0001 | Calculation Note For Foundation Of 10-PIT-5628 | A | 2019-10-07 | IFR | OL1-2K13-0104 | CV | 2019-10-15 | 036909C-JVD-TRN-02841 | 036909C-JVD-TRN-02841 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02841 |  | 2019-10-15 | 1
036909C-1000-PP-808 | Site Hand Over Procedure | 0 | 2019-10-03 | IMP | OL1-2D92-0005 | CM | 2019-10-15 | 036909C-JVD-TRN-02843 | 036909C-JVD-TRN-02843 | IFR | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CM-02843 |  | 2019-10-15 | 2
036909C-1000-PP-860 | Site Traffic Management Plan | A | 2019-10-08 | IFR | OL1-2S92-0011 | ES | 2019-10-12 | 036909C-JVD-TRN-02821 | 036909C-JVD-TRN-02821 | IFR | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-SE-02821 |  | 2019-10-08 | 2
036909C-1000-PP-255 | 3D Modeling Procedure For Piping Designers | 1 | 2019-09-30 | IMP | OL1-2R07-0027 | ME | 2019-10-14 | 036909C-JVD-TRN-02823 | 036909C-JVD-TRN-02823 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-ME-02823 |  | 2019-10-15 | 2
036909C-105W-ML-251 | Model Review Report Waste Water Treatment Unit Action List 30 Per Cent | 1 | 2019-10-04 | IFI | OL1-2P30-0032 | MP | 2019-10-10 | 036909C-JVD-TRN-02805 | 036909C-JVD-TRN-02805 | IFR | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-MP-02805 |  | 2019-10-11 | 2
036909C-105U-ML-251 | Model Review Report Utilities And Flare KO Drum Action List 30 Per Cent | 1 | 2019-10-04 | IFI | OL1-2P30-0031 | MP | 2019-10-10 | 036909C-JVD-TRN-02805 | 036909C-JVD-TRN-02805 | IFR | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-MP-02805 |  | 2019-10-11 | 2
036909C-1031-MSD-0011-3102 | Material Selection Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam And Condensate System | B | 2019-10-04 | IFD | OL1-2G74-3102 | HOC Mech | 2019-10-10 | 036909C-JVD-TRN-02809 | 036909C-JVD-TRN-02809 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02809 |  | 2019-10-11 | 3
036909C-105F-ML-251 | Model Review Report Flare Unit Action List 30 Per Cent | 1 | 2019-10-04 | IFI | OL1-2P30-0029 | MP | 2019-10-10 | 036909C-JVD-TRN-02805 | 036909C-JVD-TRN-02805 | IFR | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-MP-02805 |  | 2019-10-11 | 2
036909C-1055-PDS-1390-5502 | Piping Specialty Item – Flame Arrestor - Vent Gas to Furnace Fire-Box SP-55002 | 0 | 2019-10-10 | CAN | OL1-2P03-5502 | HOC Process | 2019-10-10 | 036909C-JVD-TRN-02808 | 036909C-JVD-TRN-02808 | IFR | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-MP-02808 |  | 2019-10-11 | 2
036909C-103A-ML-251 | Model Review Report Butadeine Extraction Unit Action List 30 Per Cent | 1 | 2019-10-04 | IFI | OL1-2P30-0028 | MP | 2019-10-10 | 036909C-JVD-TRN-02805 | 036909C-JVD-TRN-02805 | IFR | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-MP-02805 |  | 2019-10-11 | 2
036909C-1030-MSD-0011-3004 | Material Selection Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing | B | 2019-10-04 | IFD | OL1-2G74-3004 | HOC Mech | 2019-10-10 | 036909C-JVD-TRN-02809 | 036909C-JVD-TRN-02809 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02809 |  | 2019-10-11 | 3
036909C-1030-MSD-0011-3005 | Material Selection Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation | B | 2019-10-04 | IFD | OL1-2G74-3005 | HOC Mech | 2019-10-10 | 036909C-JVD-TRN-02809 | 036909C-JVD-TRN-02809 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02809 |  | 2019-10-11 | 3
036909C-1030-MSD-0011-3002 | Material Selection Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation | B | 2019-10-04 | IFD | OL1-2G74-3002 | HOC Mech | 2019-10-10 | 036909C-JVD-TRN-02809 | 036909C-JVD-TRN-02809 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02809 |  | 2019-10-11 | 3
036909C-1030-MSD-0011-3003 | Material Selection Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier | B | 2019-10-04 | IFD | OL1-2G74-3003 | HOC Mech | 2019-10-10 | 036909C-JVD-TRN-02809 | 036909C-JVD-TRN-02809 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02809 |  | 2019-10-11 | 3
036909C-102B-ML-251 | Model Review Report C3 Hydrogenation Action List 30 Per Cent | 1 | 2019-10-04 | IFI | OL1-2P30-0024 | MP | 2019-10-10 | 036909C-JVD-TRN-02805 | 036909C-JVD-TRN-02805 | IFR | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-MP-02805 |  | 2019-10-11 | 2
036909C-102D-ML-251 | Model Review Report Cold Compression Action List 30 Per Cent | 1 | 2019-10-04 | IFI | OL1-2P30-0026 | MP | 2019-10-10 | 036909C-JVD-TRN-02805 | 036909C-JVD-TRN-02805 | IFR | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-MP-02805 |  | 2019-10-11 | 2
036909C-102E-ML-251 | Model Review Report Cracked Gas Compressor Action List 30 Per Cent | 1 | 2019-10-04 | IFI | OL1-2P30-0027 | MP | 2019-10-10 | 036909C-JVD-TRN-02805 | 036909C-JVD-TRN-02805 | IFR | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-MP-02805 |  | 2019-10-11 | 2
036909C-102C-ML-251 | Model Review Report Hot Fractioning Action List 30 Per Cent | 1 | 2019-10-04 | IFI | OL1-2P30-0025 | MP | 2019-10-10 | 036909C-JVD-TRN-02805 | 036909C-JVD-TRN-02805 | IFR | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-MP-02805 |  | 2019-10-11 | 2
036909C-101B-ML-251 | Model Review Report Furnace Utilities And Action List 30 Per Cent | 1 | 2019-10-04 | IFI | OL1-2P30-0022 | MP | 2019-10-10 | 036909C-JVD-TRN-02805 | 036909C-JVD-TRN-02805 | IFR | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-MP-02805 |  | 2019-10-11 | 2
036909C-1027-MSD-0011-2701 | Material Selection Diagram - Olefins Unit 10 - 27 - GHU & C4/C5 Hydrog GHU-1 Reactor & Depentanizer | B | 2019-10-04 | IFD | OL1-2G74-2701 | HOC Mech | 2019-10-10 | 036909C-JVD-TRN-02809 | 036909C-JVD-TRN-02809 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02809 |  | 2019-10-11 | 3
036909C-1027-MSD-0011-2702 | Material Selection Diagram - Olefins Unit 10 - 27 - GHU & C4/C5 Hydrog - GHU-1 Rerun Tower | B | 2019-10-04 | IFD | OL1-2G74-2702 | HOC Mech | 2019-10-10 | 036909C-JVD-TRN-02809 | 036909C-JVD-TRN-02809 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02809 |  | 2019-10-11 | 3
036909C-1027-MSD-0011-2704 | Material Selection Diagram - Olefins Unit 10 - 27 - GHU & C4/C5 Hydrog - C4/C5 Hydrogenation | B | 2019-10-04 | IFD | OL1-2G74-2704 | HOC Mech | 2019-10-10 | 036909C-JVD-TRN-02809 | 036909C-JVD-TRN-02809 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02809 |  | 2019-10-11 | 3
036909C-1027-MSD-0011-2703 | Material Selection Diagram - Olefins Unit 10 - 27 - GHU & C4/C5 Hydrog - Hydrog Reactivation Gas System | B | 2019-10-04 | IFD | OL1-2G74-2703 | HOC Mech | 2019-10-10 | 036909C-JVD-TRN-02809 | 036909C-JVD-TRN-02809 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02809 |  | 2019-10-11 | 3
036909C-100M-ML-251 | Model Review Report Metering Station And General Action List 30 Per Cent | 1 | 2019-10-04 | IFI | OL1-2P30-0020 | MP | 2019-10-10 | 036909C-JVD-TRN-02805 | 036909C-JVD-TRN-02805 | IFR | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-MP-02805 |  | 2019-10-10 | 2
036909C-1056-PID-0031-5621 | P&ID - Olefins Unit 10 - Wastewater - HP Flare Area Oily Storm Water Collection | C | 2019-09-27 | IDD1 | OL1-2G43-5621 | PE | 2019-10-02 | 036909C-JVD-TRN-02750 | 036909C-JVD-TRN-02750 | IFR | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-PE-02750 |  | 2019-10-09 | 2
036909C-1024-PDS-1390-2412 | Piping Specialty Item - Datasheet - Desuperheater - SP-24012 | 0 | 2019-10-04 | CAN | OL1-2P03-2412 | MP | 2019-10-09 | 036909C-JVD-TRN-02793 | 036909C-JVD-TRN-02793 | IFR | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-MP-02793 |  | 2019-10-10 | 2
036909C-1020-SP-0840-2028 | Mechanical Equipment Datasheet for FO Pump Purge Oil Filter | 0 | 2019-10-02 | IFP | OL1-2M03-2028 | ME | 2019-10-03 | 036909C-JVD-TRN-02767 | 036909C-JVD-TRN-02767 | IFR | 2019-10-18 |  | Transmitted | TPSK-LSPA1-T-ME-02767 |  | 2019-10-10 | 2
036909C-1000-PP-843 | Cultural Heritage Chance Finds Procedure | 0 | 2019-10-01 | IMP | OL1-2J92-0008 | HR | 2019-10-07 | 036909C-JVD-TRN-02779 | 036909C-JVD-TRN-02779 | IFR | 2019-10-22 |  | Transmitted | TPSK-LSPA1-T-HR-02779 |  | 2019-10-10 | 2
036909C-1000-PP-840 | Community Healt Action Plan | 0 | 2019-09-20 | IMP | OL1-2J92-0005 | HR | 2019-10-01 | 036909C-JVD-TRN-02745 | 036909C-JVD-TRN-02745 | IFR | 2019-10-16 |  | Transmitted | TPSK-LSPA1-T-HR-02745 |  | 2019-10-09 | 2
036909C-1000-PP-841 | Community Grievance Management Plan | 0 | 2019-09-20 | 0 | OL1-2J92-0006 | HR | 2019-10-01 | 036909C-JVD-TRN-02745 | 036909C-JVD-TRN-02745 | IFR | 2019-10-16 |  | Transmitted | TPSK-LSPA1-T-HR-02745 |  | 2019-10-09 | 2
036909C-1000-NM-2000-0001 | Building List | A | 2019-09-26 | IFR | OL1-2K30-0001 | CV | 2019-09-27 | 036909C-JVD-TRN-02707 | 036909C-JVD-TRN-02707 | IFA | 2019-10-14 |  | Transmitted | TPSK-LSPA1-T-CV-02707 |  | 2019-10-09 | 1
036909C-1000-PP-839 | Local Infrastructure Improvement Program | 0 | 2019-09-20 | IMP | OL1-2J92-0004 | HR | 2019-10-01 | 036909C-JVD-TRN-02745 | 036909C-JVD-TRN-02745 | IFR | 2019-10-16 |  | Transmitted | TPSK-LSPA1-T-HR-02745 |  | 2019-10-09 | 2
036909C-1000-PP-838 | Local Recruitment And Procurement Plan | 0 | 2019-09-20 | IMP | OL1-2J92-0003 | HR | 2019-10-01 | 036909C-JVD-TRN-02745 | 036909C-JVD-TRN-02745 | IFR | 2019-10-16 |  | Transmitted | TPSK-LSPA1-T-HR-02745 |  | 2019-10-09 | 2
036909C-1000-PP-835 | HR Department Labor Contract | 0 | 2019-09-20 | IMP | OL1-2J94-0003 | HR | 2019-10-01 | 036909C-JVD-TRN-02746 | 036909C-JVD-TRN-02746 | IFR | 2019-10-16 |  | Transmitted | TPSK-LSPA1-T-HR-02746 |  | 2019-10-09 | 2
036909C-1000-PP-836 | Code Of Conduct | 0 | 2019-09-20 | IMP | OL1-2J93-0005 | HR | 2019-10-01 | 036909C-JVD-TRN-02747 | 036909C-JVD-TRN-02747 | IFR | 2019-10-16 |  | Transmitted | TPSK-LSPA1-T-HR-02747 |  | 2019-10-10 | 2
036909C-1000-MR-1564-0001 | MR For Water Analyzers | A | 2019-09-30 | IFQ | OL1-2C17-230101 | PL | 2019-09-30 | 036909C-JVD-TRN-02764 | 036909C-JVD-TRN-02764 | IFA | 2019-10-18 |  | Transmitted | TPSK-LSPA1-T-PL-02764 |  | 2019-10-10 | 1
036909C-1000-DI-0007-0003 | Flare and Blowdown System Design Basis | B | 2019-10-01 | IFD | OL1-2G02-0003 | PE | 2019-10-03 | 036909C-JVD-TRN-02765 | 036909C-JVD-TRN-02765 | IFA | 2019-10-18 |  | Transmitted | TPSK-LSPA1-T-PE-02765 |  | 2019-10-10 | 1
036909C-1012-DW-0131-2540 | USC 132U Cracking Furnace Steel Crossover Limit Stop Details | 1 | 2019-09-17 | IMP | OL1-2K32-2540 | CV | 2019-09-18 | 036909C-JVD-TRN-02667 | 036909C-JVD-TRN-02668, 036909C-JVD-TRN-02667 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02667 |  | 2019-09-19 | 3
036909C-1000-RT-6000-0001 | Noise Map | A | 2019-09-20 | IFR | OL1-2L09-0001 | SE | 2019-09-26 | 036909C-JVD-TRN-02721 | 036909C-JVD-TRN-02721 | IFR | 2019-10-11 |  | Transmitted | TPSK-LSPA1-T-SE-02721 |  | 2019-09-28 | 2
036909C-1011-DW-0117-1604 | USC 36M Recycle Furnace Steel Platform Plan at TOS EL 112690 | 0 | 2019-09-25 | IMP | OL1-2K32-1604 | CV | 2019-09-26 | 036909C-JVD-TRN-02722 | 036909C-JVD-TRN-02722 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02722 |  | 2019-09-28 | 3
036909C-1012-DW-0131-2604 | USC 132U Cracking Furnace Steel Platform Plan at TOS EL 115870 | 0 | 2019-09-25 | IMP | OL1-2K32-2604 | CV | 2019-09-26 | 036909C-JVD-TRN-02722 | 036909C-JVD-TRN-02722 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02722 |  | 2019-09-28 | 3
036909C-1030-DI-0007-3001 | Area Basis of Design - 30 BDU | C | 2019-09-25 | IFD | OL1-2G05-3001 | PE | 2019-09-25 | 036909C-JVD-TRN-02718 | 036909C-JVD-TRN-02718 | IFA | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-PE-02718 |  | 2019-09-28 | 1
036909C-1000-DI-1500-0002 | Design Instruction For Typical Loops For SPI Database | A | 2019-09-09 | IFI | OL1-2I70-0002 | IE | 2019-09-25 | 036909C-JVD-TRN-02714 | 036909C-JVD-TRN-02714 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-02714 |  | 2019-09-28 | 3
036909C-1000-PID-0090-0016 | P&ID- Olefins Unit 10- Common- Typicals For Mov | A | 2019-09-17 | IDD1 | OL1-2G43-0016 | PE | 2019-09-25 | 036909C-JVD-TRN-02709 | 036909C-JVD-TRN-02709 | IFR | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-PE-02709 |  | 2019-09-27 | 2
036909C-1000-PID-0090-0015 | P&ID- Olefins Unit 10- Common- Typicals For Mov | A | 2019-09-17 | IDD1 | OL1-2G43-0015 | PE | 2019-09-25 | 036909C-JVD-TRN-02709 | 036909C-JVD-TRN-02709 | IFR | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-PE-02709 |  | 2019-09-27 | 2
036909C-1022-SP-0910-2212 | Mechanical Equipment Datasheet - CG 1st Stage Condensate Pumps | 0 | 2019-08-09 | IFP | OL1-2M03-2212 | ME | 2019-09-23 | 036909C-JVD-TRN-02685 | 036909C-JVD-TRN-02685 | IFR | 2019-10-08 |  | Transmitted | TPSK-LSPA1-T-ME-02685 |  | 2019-09-25 | 2
036909C-101A-ML-252 | Model Review Report Furnace Island Action List 60 | B | 2019-09-24 | IFR | OL1-2P30-0033 | MP | 2019-09-24 | 036909C-JVD-TRN-02704 | 036909C-JVD-TRN-02704 | IFR | 2019-10-09 |  | Transmitted | TPSK-LSPA1-T-MP-02704 |  | 2019-09-25 | 2
036909C-1012-DW-0131-2541 | USC 132U Cracking Furnace Steel Convection Sections and Details | 1 | 2019-09-17 | IMP | OL1-2K32-2541 | CV | 2019-09-18 | 036909C-JVD-TRN-02667 | 036909C-JVD-TRN-02668, 036909C-JVD-TRN-02667 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02667 |  | 2019-09-19 | 3
036909C-1012-DW-0131-2520 | USC 132U Cracking Furnace Steel Convection Side Wall at COL Line B2 thru B6 | 1 | 2019-09-17 | IMP | OL1-2K32-2520 | CV | 2019-09-18 | 036909C-JVD-TRN-02667 | 036909C-JVD-TRN-02668, 036909C-JVD-TRN-02667 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02667 |  | 2019-09-19 | 3
036909C-1012-DW-0131-2521 | USC 132U Cracking Furnace Steel Convection Side Wall at COL Line C2 thru C6 | 1 | 2019-09-17 | IMP | OL1-2K32-2521 | CV | 2019-09-18 | 036909C-JVD-TRN-02667 | 036909C-JVD-TRN-02668, 036909C-JVD-TRN-02667 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02667 |  | 2019-09-19 | 3
036909C-1000-NM-614 | Expediting Execution Plan | 6 | 2019-09-13 | IMP | OL1-2C95-0001 | PL | 2019-09-19 | 036909C-JVD-TRN-02668 | 036909C-JVD-TRN-02668 | IFR | 2019-10-03 |  | Transmitted | TPSK-LSPA1-T-PL-02668 |  | 2019-09-20 | 2
036909C-1000-NM-617 | Monthly Complete Expediting Report | 6 | 2019-09-13 | IMP | OL1-2C95-0002 | PL | 2019-09-19 | 036909C-JVD-TRN-02668 | 036909C-JVD-TRN-02668 | IFR | 2019-10-03 |  | Transmitted | TPSK-LSPA1-T-PL-02668 |  | 2019-09-20 | 2
036909C-103A-DW-1572-0112 | Zone 3A Telecom Main Cable Tray Routing Butadiene | A | 2019-08-30 | IFR | OL1-2T12-0112 | EE | 2019-09-25 | 036909C-JVD-TRN-02715 | 036909C-JVD-TRN-02715 | IFA | 2019-10-10 | 2019-10-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02715 |  | 2019-09-28 | 1
036909C-105F-DW-1572-0116 | Zone 5F Telecom Main Cable Tray Routing Flare Area | A | 2019-08-30 | IFR | OL1-2T12-0116 | EE | 2019-09-25 | 036909C-JVD-TRN-02715 | 036909C-JVD-TRN-02715 | IFA | 2019-10-10 | 2019-10-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02715 |  | 2019-09-28 | 1
036909C-105W-DW-1572-0115 | Zone 5W Telecom Main Cable Tray Routing Waste Water Treatment | A | 2019-08-30 | IFR | OL1-2T12-0115 | EE | 2019-09-25 | 036909C-JVD-TRN-02715 | 036909C-JVD-TRN-02715 | IFA | 2019-10-10 | 2019-10-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02715 |  | 2019-09-28 | 1
036909C-105U-DW-1572-0114 | Zone 5U Telecom Main Cable Tray Routing Utilities | A | 2019-08-30 | IFR | OL1-2T12-0114 | EE | 2019-09-25 | 036909C-JVD-TRN-02715 | 036909C-JVD-TRN-02715 | IFA | 2019-10-10 | 2019-10-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02715 |  | 2019-09-28 | 1
036909C-105T-DW-1572-0113 | Zone 5T Telecom Main Cable Tray Routing Cooling Water Unit | A | 2019-08-30 | IFR | OL1-2T12-0113 | EE | 2019-09-25 | 036909C-JVD-TRN-02715 | 036909C-JVD-TRN-02715 | IFA | 2019-10-10 | 2019-10-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02715 |  | 2019-09-28 | 1
036909C-102E-DW-1572-0111 | Zone 2E Telecom Main Cable Tray Routing Crack Gas Compressor | A | 2019-08-30 | IFR | OL1-2T12-0111 | EE | 2019-09-25 | 036909C-JVD-TRN-02715 | 036909C-JVD-TRN-02715 | IFA | 2019-10-10 | 2019-10-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02715 |  | 2019-09-28 | 1
036909C-102D-DW-1572-0004 | Zone 2D Telecom Main Cable Tray Routing Process Cold Compressors | A | 2019-08-30 | IFR | OL1-2T12-0110 | EE | 2019-09-25 | 036909C-JVD-TRN-02715 | 036909C-JVD-TRN-02715 | IFA | 2019-10-10 | 2019-10-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02715 |  | 2019-09-28 | 1
036909C-102C-DW-1572-0109 | Telecom Main Cable Tray Routing Hot Fractionation GHU Unit | A | 2019-08-30 | IFR | OL1-2T12-0109 | EE | 2019-09-25 | 036909C-JVD-TRN-02715 | 036909C-JVD-TRN-02715 | IFA | 2019-10-10 | 2019-10-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02715 |  | 2019-09-28 | 1
036909C-103S-DW-1572-0105 | Zone 3S Telecom Main Cable Tray Routing Area SUB C and FAR C | A | 2019-08-30 | IFR | OL1-2T12-0105 | EE | 2019-09-25 | 036909C-JVD-TRN-02715 | 036909C-JVD-TRN-02715 | IFA | 2019-10-10 | 2019-10-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02715 |  | 2019-09-28 | 1
036909C-100S-DW-1572-0104 | Telecom Main Cable Tray Rout SUB E and FAR E | A | 2019-08-30 | IFR | OL1-2T12-0104 | EE | 2019-09-25 | 036909C-JVD-TRN-02715 | 036909C-JVD-TRN-02715 | IFA | 2019-10-10 | 2019-10-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02715 |  | 2019-09-28 | 1
036909C-100P-DW-1572-0103 | Telecom Main Cable Tray Routing Main Pipe Rack | A | 2019-08-30 | IFR | OL1-2T12-0103 | EE | 2019-09-25 | 036909C-JVD-TRN-02715 | 036909C-JVD-TRN-02715 | IFA | 2019-10-10 | 2019-10-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02715 |  | 2019-09-28 | 1
036909C-100M-DW-1572-0102 | Zone 0M Tel Main Cable Tray Rout Metering | A | 2019-08-30 | IFR | OL1-2T12-0102 | EE | 2019-09-25 | 036909C-JVD-TRN-02715 | 036909C-JVD-TRN-02715 | IFA | 2019-10-10 | 2019-10-16 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-02715 |  | 2019-09-28 | 1
036909C-1051-SP-1541-5107 | Instr. DS for Control Valve - Angle Type - Area 51 | B | 2019-09-13 | IFQ | OL1-2I20-5117 | IE | 2019-09-18 | 036909C-JVD-TRN-02663 | 036909C-JVD-TRN-02663 | IFA | 2019-10-03 | 2019-10-16 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-IE-02663 |  | 2019-09-19 | 1
036909C-1056-PDS-2500-5640 | Process Equipment Datasheet - Oily Waste Water Tank PDS 10-TK-5640 | E | 2019-09-20 | IFD | OL1-2G30-5640 | PE | 2019-09-26 | 036909C-JVD-TRN-02720 | 036909C-JVD-TRN-02720 | IFR | 2019-10-11 | 2019-10-15 | R2-Comments as noted | TPSK-LSPA1-T-PE-02720 |  | 2019-09-28 | 2
036909C-103A-DW-1622-0301 | Welding And Receptacles Panel Schedule - Zone 3A | A | 2019-09-24 | IFR | OL1-2E42-0031 | EE | 2019-10-01 | 036909C-JVD-TRN-02737 | 036909C-JVD-TRN-02737 | IFR | 2019-10-15 | 2019-10-17 | R2-Comments as noted | TPSK-LSPA1-T-EE-02737 |  | 2019-10-09 | 2
036909C-105T-DW-1622-0301 | Welding And Receptacles Panel Schedule - Zone 5T | A | 2019-09-24 | IFR | OL1-2E42-0017 | EE | 2019-10-01 | 036909C-JVD-TRN-02737 | 036909C-JVD-TRN-02737 | IFR | 2019-10-15 | 2019-10-17 | R2-Comments as noted | TPSK-LSPA1-T-EE-02737 |  | 2019-10-09 | 2
036909C-103S-DW-1970-2002 | Electrical Sub-C & FAR-C Fire Protection & Life Saving Equipment Drawing - First Floor | A | 2019-09-13 | IFR | OL1-2F65-2002 | FF | 2019-09-18 | 036909C-JVD-TRN-02662 | 036909C-JVD-TRN-02662 | IFR | 2019-10-02 | 2019-10-17 | R2-Comments as noted | TPSK-LSPA1-T-FF-02662 |  | 2019-09-19 | 2
036909C-103S-DW-1970-2001 | Electrical Sub-C & FAR-C Fire Protection & Life Saving Equipment Drawing - Ground Floor | A | 2019-09-13 | IFR | OL1-2F65-2001 | FF | 2019-09-18 | 036909C-JVD-TRN-02662 | 036909C-JVD-TRN-02662 | IFR | 2019-10-02 | 2019-10-17 | R2-Comments as noted | TPSK-LSPA1-T-FF-02662 |  | 2019-09-19 | 2
036909C-100S-DW-1970-1002 | Electrical Sub-E & FAR-E Fire Protection & Life Saving Equipment Drawing - First Floor | A | 2019-09-13 | IFR | OL1-2F65-1002 | FF | 2019-09-18 | 036909C-JVD-TRN-02662 | 036909C-JVD-TRN-02662 | IFR | 2019-10-02 | 2019-10-17 | R2-Comments as noted | TPSK-LSPA1-T-FF-02662 |  | 2019-09-19 | 2
036909C-100S-DW-1970-1001 | Electrical Sub-E & FAR-E Fire Protection & Life Saving Equipment Drawing - Ground Floor | A | 2019-09-13 | IFR | OL1-2F65-1001 | FF | 2019-09-18 | 036909C-JVD-TRN-02662 | 036909C-JVD-TRN-02662 | IFR | 2019-10-02 | 2019-10-17 | R2-Comments as noted | TPSK-LSPA1-T-FF-02662 |  | 2019-09-19 | 2
036909C-1000-JSD-6200-0001 | Environmental Protection Design Criteria | 0 | 2019-10-10 | IMP | OL1-2S08-0001 | ES | 2019-10-14 | 036909C-JVD-TRN-02837 | 036909C-JVD-TRN-02837 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-SE-02837 |  | 2019-10-15 | 2
036909C-1000-DI-0007-0001 | Process Basis of Design | C | 2019-09-27 | IFD | OL1-2G02-0001 | PE | 2019-09-27 | 036909C-JVD-TRN-02733 | 036909C-JVD-TRN-02733 | IFA | 2019-10-12 |  | Transmitted | TPSK-LSPA1-T-PE-02733 |  | 2019-10-04 | 1
036909C-1011-SP-1546-1153 | Instrument Datasheets for Orifice Plate & Restriction Orifice | 1 | 2019-10-08 | IFP | OL1-2I20-1153 | IE | 2019-10-09 | 036909C-JVD-TRN-02802 | 036909C-JVD-TRN-02802 | IFR | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-IE-02802 |  | 2019-10-10 | 2
036909C-103A-DW-1442-0001 | Major Underground Networks - Zone 3A - Butadiene Extraction Unit - Ex Doc Client Ref OL1-2K36-0008 | B | 2019-09-18 | IDD | OL1-2K26-0008 | CV | 2019-09-20 | 036909C-JVD-TRN-02674 | 036909C-JVD-TRN-02674 | IFA | 2019-10-07 |  | Transmitted | TPSK-LSPA1-T-CV-02674 | Ex Doc Client Ref OL1-2K36-0008 | 2019-09-24 | 1
036909C-1056-PDS-0200-5629 | Data Sheet For Basins PIT-5621 Skimmed Oil Sump | A | 2019-09-19 | IFR | OL1-2G30-5629 | PE | 2019-09-20 | 036909C-JVD-TRN-02673 | 036909C-JVD-TRN-02672, 036909C-JVD-TRN-02673 | IFR | 2019-10-07 | 2019-10-14 | R1-No comments | TPSK-LSPA1-T-PE-02673 |  | 2019-09-24 | 2
036909C-101B-DW-1572-0006 | Instrument Main Cable Routing Furnace Utilities | B | 2019-10-10 | IBD | OL1-2I34-0006 | IE | 2019-10-14 | 036909C-JVD-TRN-02829 | 036909C-JVD-TRN-02829 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-IE-02829 |  | 2019-10-15 | 1
036909C-100S-DW-1622-0101 | Electrical Main Cable Routing Layout - Zone 0S | B | 2019-09-30 | IFR | OL1-2E31-0004 | EE | 2019-10-08 | 036909C-JVD-TRN-02787 | 036909C-JVD-TRN-02787 | IFA | 2019-10-22 |  | Transmitted | TPSK-LSPA1-T-EE-02787 |  | 2019-10-10 | 1
036909C-1000-MS-6800-0001 | Technical Specification For Mechanical Erection | A | 2019-09-18 | IFQ | OL1-2M92-0001 | ME | 2019-09-25 | 036909C-JVD-TRN-02706 | 036909C-JVD-TRN-02706 | IFR | 2019-10-10 | 2019-10-09 | R2-Comments as noted | TPSK-LSPA1-T-ME-02706 |  | 2019-09-27 | 2
036909C-102E-DW-1842-0001-015 | Steel For Structure 10-SHT-2E01 - Stair Plans And Elevations | A | 2019-10-14 | IFR | OL1-2K32-1294 | CV | 2019-10-15 | 036909C-JVD-TRN-02856 | 036909C-JVD-TRN-02856 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02856 |  | 2019-10-20 | 1
036909C-102E-DW-1842-0001-013 | Steel For Structure 10-SHT-2E01 - Elevation | A | 2019-10-14 | IFR | OL1-2K32-1292 | CV | 2019-10-15 | 036909C-JVD-TRN-02856 | 036909C-JVD-TRN-02856 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02856 |  | 2019-10-20 | 1
036909C-102E-DW-1842-0001-012 | Steel For Structure 10-SHT-2E01 - Elevation | A | 2019-10-14 | IFR | OL1-2K32-1291 | CV | 2019-10-15 | 036909C-JVD-TRN-02856 | 036909C-JVD-TRN-02856 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02856 |  | 2019-10-20 | 1
036909C-102D-CN-1733-0052 | Calculation Note Of Concrete Structure Of 10-C-2850- 10-E-2850 | A | 2019-10-11 | IFR | OL1-2K13-0262 | CV | 2019-10-15 | 036909C-JVD-TRN-02857 | 036909C-JVD-TRN-02857 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02857 |  | 2019-10-20 | 1
036909C-1023-PDS-1390-2311 | SP Item Data Sheet - Desuperheater - SP-23011 - Superseded By OL1-2G31-2311 | 0 | 2019-10-14 | CAN | OL1-2P03-2311 | MP | 2019-10-15 | 036909C-JVD-TRN-02858 | 036909C-JVD-TRN-02858 | IFR | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-MP-02858 | Superseded By OL1-2G31-2311 | 2019-10-20 | 2
036909C-1023-PDS-1541-2301 | Process Data Sheet For Spent Caustic Desuperheater DH-2301 - Ex Doc Client Reference OL1-2P03-2311 | A | 2019-10-14 | IFR | OL1-2G31-2311 | PE | 2019-10-15 | 036909C-JVD-TRN-02859 | 036909C-JVD-TRN-02859 | IFR | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-PE-02859 | Ex Doc Client Reference OL1-2P03-2311 | 2019-10-20 | 2
036909C-100P-CN-1831-0001 | Calculation Note For Steel Pipe Rack 10-PRK-0P01 | 0 | 2019-10-08 | IFC | OL1-2K15-0001 | CV | 2019-10-14 | 036909C-JVD-TRN-02834 | 036909C-JVD-TRN-02834 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02834 |  | 2019-10-15 | 1
036909C-100P-DW-1841-0001-001 | Steel Structure For Pipe Rack 10-PRK-0P01- 3D View | 0 | 2019-10-08 | IFC | OL1-2K32-7000 | CV | 2019-10-14 | 036909C-JVD-TRN-02833 | 036909C-JVD-TRN-02833 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02833 |  | 2019-10-15 | 1
036909C-100P-DW-1841-0001-005 | Steel Structure For Pipe Rack 10-PRK-0P01- Plans | 0 | 2019-10-08 | IFC | OL1-2K32-7004 | CV | 2019-10-14 | 036909C-JVD-TRN-02833 | 036909C-JVD-TRN-02833 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02833 |  | 2019-10-17 | 1
036909C-100P-DW-1841-0001-013 | Steel Structure For Pipe Rack 10-PRK-0P01- Details | 0 | 2019-10-08 | IFC | OL1-2K32-7012 | CV | 2019-10-14 | 036909C-JVD-TRN-02833 | 036909C-JVD-TRN-02833 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02833 |  | 2019-10-17 | 1
036909C-100P-DW-1841-0001-014 | Steel Structure For Pipe Rack 10-PRK-0P01- Ladders Platforms And Details | 0 | 2019-10-08 | IFC | OL1-2K32-7013 | CV | 2019-10-14 | 036909C-JVD-TRN-02833 | 036909C-JVD-TRN-02833 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02833 |  | 2019-10-17 | 1
036909C-100P-DW-1841-0001-009 | Steel Structure For Pipe Rack 10-PRK-0P01- Sections | 0 | 2019-10-08 | IFC | OL1-2K32-7008 | CV | 2019-10-14 | 036909C-JVD-TRN-02833 | 036909C-JVD-TRN-02833 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02833 |  | 2019-10-17 | 1
036909C-100P-DW-1841-0001-010 | Steel Structure For Pipe Rack 10-PRK-0P01 - Details | 0 | 2019-10-08 | IFC | OL1-2K32-7009 | CV | 2019-10-14 | 036909C-JVD-TRN-02833 | 036909C-JVD-TRN-02833 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02833 |  | 2019-10-17 | 1
036909C-100P-DW-1841-0001-011 | Steel Structure For Pipe Rack 10-PRK-0P01- Details | 0 | 2019-10-08 | IFC | OL1-2K32-7010 | CV | 2019-10-14 | 036909C-JVD-TRN-02833 | 036909C-JVD-TRN-02833 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02833 |  | 2019-10-17 | 1
036909C-100P-DW-1841-0001-012 | Steel Structure For Pipe Rack 10-PRK-0P01- Stair | 0 | 2019-10-08 | IFC | OL1-2K32-7011 | CV | 2019-10-14 | 036909C-JVD-TRN-02833 | 036909C-JVD-TRN-02833 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02833 |  | 2019-10-17 | 1
036909C-100P-DW-1841-0001-006 | Steel Structure For Pipe Rack 10-PRK-0P01- Elevations | 0 | 2019-10-08 | IFC | OL1-2K32-7005 | CV | 2019-10-14 | 036909C-JVD-TRN-02833 | 036909C-JVD-TRN-02833 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02833 |  | 2019-10-17 | 1
036909C-100P-DW-1841-0001-008 | Steel Structure For Pipe Rack 10-PRK-0P01- Elevations | 0 | 2019-10-08 | IFC | OL1-2K32-7007 | CV | 2019-10-14 | 036909C-JVD-TRN-02833 | 036909C-JVD-TRN-02833 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02833 |  | 2019-10-17 | 1
036909C-100P-DW-1841-0001-007 | Steel Structure For Pipe Rack 10-PRK-0P01- Elevations | 0 | 2019-10-08 | IFC | OL1-2K32-7006 | CV | 2019-10-14 | 036909C-JVD-TRN-02833 | 036909C-JVD-TRN-02833 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02833 |  | 2019-10-17 | 1
036909C-100P-DW-1841-0001-004 | Steel Structure For Pipe Rack 10-PRK-0P01- Plans | 0 | 2019-10-08 | IFC | OL1-2K32-7003 | CV | 2019-10-14 | 036909C-JVD-TRN-02833 | 036909C-JVD-TRN-02833 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02833 |  | 2019-10-17 | 1
036909C-100P-DW-1841-0001-003 | Steel Structure For Pipe Rack 10-PRK-0P01- Plans | 0 | 2019-10-08 | IFC | OL1-2K32-7002 | CV | 2019-10-14 | 036909C-JVD-TRN-02833 | 036909C-JVD-TRN-02833 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02833 |  | 2019-10-17 | 1
036909C-100P-DW-1841-0001-002 | Steel Structure For Pipe Rack 10-PRK-0P01- Plans | 0 | 2019-10-08 | IFC | OL1-2K32-7001 | CV | 2019-10-14 | 036909C-JVD-TRN-02833 | 036909C-JVD-TRN-02833 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02833 |  | 2019-10-17 | 1
036909C-1000-MR-0910-0007 | Material Requisition For API Centrifugal Pumps | 1 | 2019-09-23 | IFP | OL1-2C13-447000 | PL | 2019-09-23 | 036909C-JVD-TRN-02686 | 036909C-JVD-TRN-02686 | IFR | 2019-10-08 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-PL-02686 |  | 2019-09-25 | 2
036909C-103A-DW-1622-0101 | Electrical Main Cable Routing Layout - Zone 3A Butadiene Extraction Unit | B | 2019-09-27 | IFR | OL1-2E31-0016 | EE | 2019-10-01 | 036909C-JVD-TRN-02736 | 036909C-JVD-TRN-02736 | IFA | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-EE-02736 |  | 2019-10-09 | 1
036909C-103S-DW-1622-0101 | Electrical Main Cable Routing Layout - Zone 3S Substation & Far C | B | 2019-09-27 | IFR | OL1-2E31-0005 | EE | 2019-10-01 | 036909C-JVD-TRN-02736 | 036909C-JVD-TRN-02736 | IFA | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-EE-02736 |  | 2019-10-09 | 1
036909C-102E-DW-1842-0001-007 | Steel For Structure 10-SHT-2E01 - Elevation | A | 2019-10-14 | IFR | OL1-2K32-1286 | CV | 2019-10-15 | 036909C-JVD-TRN-02856 | 036909C-JVD-TRN-02856 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02856 |  | 2019-10-20 | 1
036909C-102E-DW-1842-0001-006 | Steel For Structure 10-SHT-2E01 - Elevation | A | 2019-10-14 | IFR | OL1-2K32-1285 | CV | 2019-10-15 | 036909C-JVD-TRN-02856 | 036909C-JVD-TRN-02856 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02856 |  | 2019-10-20 | 1
036909C-102E-DW-1842-0001-011 | Steel For Structure 10-SHT-2E01 - Elevation | A | 2019-10-14 | IFR | OL1-2K32-1290 | CV | 2019-10-15 | 036909C-JVD-TRN-02856 | 036909C-JVD-TRN-02856 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02856 |  | 2019-10-20 | 1
036909C-102E-DW-1842-0001-010 | Steel For Structure 10-SHT-2E01 - Elevation | A | 2019-10-14 | IFR | OL1-2K32-1289 | CV | 2019-10-15 | 036909C-JVD-TRN-02856 | 036909C-JVD-TRN-02856 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02856 |  | 2019-10-20 | 1
036909C-102E-DW-1842-0001-004 | Steel For Structure 10-SHT-2E01 - Plans | A | 2019-10-14 | IFR | OL1-2K32-1283 | CV | 2019-10-15 | 036909C-JVD-TRN-02856 | 036909C-JVD-TRN-02856 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02856 |  | 2019-10-20 | 1
036909C-102E-DW-1842-0001-003 | Steel For Structure 10-SHT-2E01 - Plans | A | 2019-10-14 | IFR | OL1-2K32-1282 | CV | 2019-10-15 | 036909C-JVD-TRN-02856 | 036909C-JVD-TRN-02856 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02856 |  | 2019-10-20 | 1
036909C-102E-DW-1842-0001-005 | Steel For Structure 10-SHT-2E01 - Plans | A | 2019-10-14 | IFR | OL1-2K32-1284 | CV | 2019-10-15 | 036909C-JVD-TRN-02856 | 036909C-JVD-TRN-02856 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02856 |  | 2019-10-20 | 1
036909C-102E-DW-1842-0001-009 | Steel For Structure 10-SHT-2E01 - Elevation | A | 2019-10-14 | IFR | OL1-2K32-1288 | CV | 2019-10-15 | 036909C-JVD-TRN-02856 | 036909C-JVD-TRN-02856 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02856 |  | 2019-10-20 | 1
036909C-102E-DW-1842-0001-008 | Steel For Structure 10-SHT-2E01 - Elevation | A | 2019-10-14 | IFR | OL1-2K32-1287 | CV | 2019-10-15 | 036909C-JVD-TRN-02856 | 036909C-JVD-TRN-02856 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02856 |  | 2019-10-20 | 1
036909C-102E-DW-1842-0001-002 | Steel For Structure 10-SHT-2E01 - Plans | A | 2019-10-14 | IFR | OL1-2K32-1281 | CV | 2019-10-15 | 036909C-JVD-TRN-02856 | 036909C-JVD-TRN-02856 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02856 |  | 2019-10-20 | 1
036909C-102E-DW-1842-0001-001 | Steel For Structure 10-SHT-2E01 - 3D View | A | 2019-10-14 | IFR | OL1-2K32-1280 | CV | 2019-10-15 | 036909C-JVD-TRN-02856 | 036909C-JVD-TRN-02856 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02856 |  | 2019-10-20 | 1
036909C-102E-CN-1832-0003 | Calculation Note For Steel Structure 10-STR-2E02 | A | 2019-10-11 | IFR | OL1-2K15-0014 | CV | 2019-10-15 | 036909C-JVD-TRN-02857 | 036909C-JVD-TRN-02857 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02857 |  | 2019-10-20 | 1
036909C-102E-CN-1832-0001 | Calculation Note For Steel Of Structure 10-SHT-2E01 | A | 2019-10-14 | IFR | OL1-2K15-0012 | CV | 2019-10-15 | 036909C-JVD-TRN-02857 | 036909C-JVD-TRN-02857 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02857 |  | 2019-10-20 | 1
036909C-102E-CN-1733-0042 | Calculation Note For Foundation Of 10-C-2200- 10- E-2200 | A | 2019-10-11 | IFR | OL1-2K13-0263 | CV | 2019-10-15 | 036909C-JVD-TRN-02857 | 036909C-JVD-TRN-02857 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02857 |  | 2019-10-20 | 1
036909C-1000-MR-1562-0001 | MR for Specific Components & Property Analyzers | A | 2019-09-02 | IFQ | OL1-2C17-260101 | PL | 2019-09-17 | 036909C-JVD-TRN-02657 | 036909C-JVD-TRN-02657 | IFA | 2019-10-02 | 2019-10-04 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PL-02657 |  | 2019-09-18 | 1
036909C-1000-MR-1565-0001 | MR For CEMS | A | 2019-09-06 | IFQ | OL1-2C17-2400000 | PL | 2019-09-17 | 036909C-JVD-TRN-02654 | 036909C-JVD-TRN-02654 | IFA | 2019-10-02 | 2019-10-04 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PL-02654 |  | 2019-09-18 | 1
036909C-102E-DW-1842-0003-002 | Steel Structure For 10-STR-2E02 | A | 2019-10-11 | IFR | OL1-2K32-1321 | CV | 2019-10-15 | 036909C-JVD-TRN-02853 | 036909C-JVD-TRN-02853 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02853 |  | 2019-10-20 | 1
036909C-102E-DW-1743-0046-005 | Foundation And Elevation For 10-C-2200- 10-E-2200- Section A-A -Reinforcement | A | 2019-10-04 | IFR | OL1-2K31-3104 | CV | 2019-10-15 | 036909C-JVD-TRN-02851 | 036909C-JVD-TRN-02851 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02851 |  | 2019-10-20 | 1
036909C-102E-DW-1743-0046-006 | Foundation And Elevation For 10-C-2200- 10-E-2200- Column And Saddle- Reinforcement | A | 2019-10-11 | IFR | OL1-2K31-3105 | CV | 2019-10-15 | 036909C-JVD-TRN-02851 | 036909C-JVD-TRN-02851 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02851 |  | 2019-10-20 | 1
036909C-102E-DW-1743-0046-007 | Foundation And Elevation For 10-C-2200- 10-E-2200- Slab- Reinforcement | A | 2019-10-04 | IFR | OL1-2K31-3106 | CV | 2019-10-15 | 036909C-JVD-TRN-02851 | 036909C-JVD-TRN-02851 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02851 |  | 2019-10-20 | 1
036909C-102E-DW-1743-0046-004 | Foundation And Elevation For 10-C-2200- 10-E-2200- Plan- Reinforcement | A | 2019-10-11 | IFR | OL1-2K31-3103 | CV | 2019-10-15 | 036909C-JVD-TRN-02851 | 036909C-JVD-TRN-02851 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02851 |  | 2019-10-20 | 1
036909C-102E-DW-1842-0003-001 | Steel Structure For 10-STR-2E02 | A | 2019-10-11 | IFR | OL1-2K32-1320 | CV | 2019-10-15 | 036909C-JVD-TRN-02853 | 036909C-JVD-TRN-02853 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02853 |  | 2019-10-20 | 1
036909C-102E-DW-1743-0046-001 | Foundation And Elevation For 10-C-2200- 10-E-2200 - Plan- Formwork | A | 2019-10-11 | IFR | OL1-2K31-3100 | CV | 2019-10-15 | 036909C-JVD-TRN-02851 | 036909C-JVD-TRN-02851 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02851 |  | 2019-10-20 | 1
036909C-102E-DW-1743-0046-003 | Foundation And Elevation For 10-C-2200- 10-E-2200- Sections And Details- Formwork | A | 2019-10-11 | IFR | OL1-2K31-3102 | CV | 2019-10-15 | 036909C-JVD-TRN-02851 | 036909C-JVD-TRN-02851 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02851 |  | 2019-10-20 | 1
036909C-102E-DW-1743-0046-002 | Foundation And Elevation For 10-C-2200- 10-E-2200- View 1-2-3-4-Formwork | A | 2019-10-11 | IFR | OL1-2K31-3101 | CV | 2019-10-15 | 036909C-JVD-TRN-02851 | 036909C-JVD-TRN-02851 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02851 |  | 2019-10-20 | 1
036909C-102B-DW-1425-0001 | Roads Paving And Finishing Layout | A | 2019-10-14 | IFR | OL1-2K27-0004 | CV | 2019-10-15 | 036909C-JVD-TRN-02854 | 036909C-JVD-TRN-02854 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02854 |  | 2019-10-20 | 1
036909C-1000-DW-1442-0001 | Major Underground Networks- Ex Doc Client Ref OL1-2K36-1000 | B | 2019-10-11 | IDD | OL1-2K26-1000 | CV | 2019-10-15 | 036909C-JVD-TRN-02855 | 036909C-JVD-TRN-02855 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-CV-02855 |  | 2019-10-20 | 1
036909C-105W-DW-1744-0001-004 | Foundation For Basin 10-Pit-5631 - Section - Reinforcement | A | 2019-10-11 | IFR | OL1-2K31-8432 | CV | 2019-10-15 | 036909C-JVD-TRN-02846 | 036909C-JVD-TRN-02846 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02846 |  | 2019-10-15 | 2
036909C-105W-DW-1744-0001-003 | Foundation For Basin 10-Pit-5631 - Plans - Reinforcement | A | 2019-10-11 | IFR | OL1-2K31-8431 | CV | 2019-10-15 | 036909C-JVD-TRN-02846 | 036909C-JVD-TRN-02846 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02846 |  | 2019-10-15 | 2
036909C-105U-DW-1572-0014 | Instrument Main Cable Routing Utilities | B | 2019-10-10 | IBD | OL1-2I34-0014 | IE | 2019-10-14 | 036909C-JVD-TRN-02829 | 036909C-JVD-TRN-02829 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-IE-02829 |  | 2019-10-17 | 1
036909C-105W-DW-1744-0001-002 | Foundation For Basin 10-Pit-5631 - Sections - Formwork | A | 2019-10-11 | IFR | OL1-2K31-8430 | CV | 2019-10-15 | 036909C-JVD-TRN-02846 | 036909C-JVD-TRN-02846 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02846 |  | 2019-10-15 | 2
036909C-105W-DW-1744-0001-001 | Foundation For Basin 10-Pit-5631 - Plans - Formwork | A | 2019-10-11 | IFR | OL1-2K31-8429 | CV | 2019-10-15 | 036909C-JVD-TRN-02846 | 036909C-JVD-TRN-02846 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02846 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0004-004 | Foundation For Basin 10-Pit-5630 - Sections - Reinforcement | A | 2019-10-11 | IFR | OL1-2K31-8436 | CV | 2019-10-15 | 036909C-JVD-TRN-02846 | 036909C-JVD-TRN-02846 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02846 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0004-003 | Foundation For Basin 10-Pit-5630 - Plans - Reinforcement | A | 2019-10-11 | IFR | OL1-2K31-8435 | CV | 2019-10-15 | 036909C-JVD-TRN-02846 | 036909C-JVD-TRN-02846 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02846 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0004-002 | Foundation For Basin 10-Pit-5630 - Sections - Formwork | A | 2019-10-11 | IFR | OL1-2K31-8434 | KLOC Civil | 2019-10-15 | 036909C-JVD-TRN-02846 | 036909C-JVD-TRN-02846 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02846 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0004-001 | Foundation For Basin 10-Pit-5630 - Plans - Formwork | A | 2019-10-11 | IFR | OL1-2K31-8433 | CV | 2019-10-15 | 036909C-JVD-TRN-02846 | 036909C-JVD-TRN-02846 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02846 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0001-020 | Basin For Cooling Tower 10-Pit-5350 - Plan (Reinforcement) | A | 2019-10-11 | IFR | OL1-2K31-2519 | CV | 2019-10-15 | 036909C-JVD-TRN-02845 | 036909C-JVD-TRN-02845 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02845 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0001-010 | Basin For Cooling Tower 10-PIT-5350 - Plan (Formwork) | A | 2019-10-04 | IFR | OL1-2K31-2509 | CV | 2019-10-15 | 036909C-JVD-TRN-02845 | 036909C-JVD-TRN-02845 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02845 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0001-011 | Basin For Cooling Tower 10-PIT-5350 - Plan (Formwork) | A | 2019-10-04 | IFR | OL1-2K31-2510 | CV | 2019-10-15 | 036909C-JVD-TRN-02845 | 036909C-JVD-TRN-02845 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02845 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0001-009 | Basin For Cooling Tower 10-PIT-5350 - Plan (Formwork) | A | 2019-10-04 | IFR | OL1-2K31-2508 | CV | 2019-10-15 | 036909C-JVD-TRN-02845 | 036909C-JVD-TRN-02845 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02845 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0001-021 | Basin For Cooling Tower 10-PIT-5350 - Plan (Reinforcement) | A | 2019-10-11 | IFR | OL1-2K31-8300 | CV | 2019-10-15 | 036909C-JVD-TRN-02845 | 036909C-JVD-TRN-02845 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02845 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0001-012 | Basin For Cooling Tower 10-Pit-5350 - Sections (Formwork) | A | 2019-10-04 | IFR | OL1-2K31-2511 | CV | 2019-10-15 | 036909C-JVD-TRN-02845 | 036909C-JVD-TRN-02845 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02845 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0001-017 | Basin For Cooling Tower 10-PIT-5350 - Plan (Reinforcement) | A | 2019-10-11 | IFR | OL1-2K31-2516 | CV | 2019-10-15 | 036909C-JVD-TRN-02845 | 036909C-JVD-TRN-02845 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02845 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0001-018 | Basin For Cooling Tower 10-PIT-5350 - Plan (Reinforcement) | A | 2019-10-11 | IFR | OL1-2K31-2517 | CV | 2019-10-15 | 036909C-JVD-TRN-02845 | 036909C-JVD-TRN-02845 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02845 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0001-019 | Basin For Cooling Tower 10-PIT-5350 - Plan (Reinforcement) | A | 2019-10-11 | IFR | OL1-2K31-2518 | CV | 2019-10-15 | 036909C-JVD-TRN-02845 | 036909C-JVD-TRN-02845 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02845 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0001-014 | Basin For Cooling Tower 10-PIT-5350 - Opening Details For Trash Screen (Formwork) | A | 2019-10-04 | IFR | OL1-2K31-2513 | CV | 2019-10-15 | 036909C-JVD-TRN-02845 | 036909C-JVD-TRN-02845 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02845 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0001-013 | Basin For Cooling Tower 10-PIT-5350 - Sections (Formwork) | A | 2019-10-04 | IFR | OL1-2K31-2512 | CV | 2019-10-15 | 036909C-JVD-TRN-02845 | 036909C-JVD-TRN-02845 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02845 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0001-015 | Basin For Cooling Tower 10-PIT-5350 - Opening Details For Sluice Gate (Formwork) | A | 2019-10-04 | IFR | OL1-2K31-2514 | CV | 2019-10-15 | 036909C-JVD-TRN-02845 | 036909C-JVD-TRN-02845 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02845 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0001-007 | Basin For Cooling Tower 10-PIT-5350 - Plan (Formwork) | A | 2019-10-04 | IFR | OL1-2K31-2506 | CV | 2019-10-15 | 036909C-JVD-TRN-02845 | 036909C-JVD-TRN-02845 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02845 |  | 2019-10-15 | 2
036909C-105F-DW-1741-0001-006 | Foundation For Pipe Rack 10-PRK-5F01 - Tie Beam Details - Formwork & Reinforcement | A | 2019-10-11 | IFR | OL1-2K31-1545 | CV | 2019-10-15 | 036909C-JVD-TRN-02839 | 036909C-JVD-TRN-02839 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02839 |  | 2019-10-15 | 2
036909C-105T-DW-1744-0001-006 | Basin For Cooling Tower 10-PIT-5350 - Plan (Formwork) | A | 2019-10-04 | IFR | OL1-2K31-2505 | CV | 2019-10-15 | 036909C-JVD-TRN-02845 | 036909C-JVD-TRN-02845 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02845 |  | 2019-10-15 | 2
036909C-105T-CN-1831-0001 | Calculation Note For Steel Pipe Rack 10-PRK-5T01 | A | 2019-10-14 | IFR | OL1-2K15-0010 | CV | 2019-10-15 | 036909C-JVD-TRN-02840 | 036909C-JVD-TRN-02840 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02840 |  | 2019-10-15 | 1
036909C-105F-DW-1741-0001-005 | Foundation For Pipe Rack 10-PRK-5F01 - Pilecap PC3 - Formwork & Reinforcement | A | 2019-10-14 | IFR | OL1-2K31-1544 | CV | 2019-10-15 | 036909C-JVD-TRN-02839 | 036909C-JVD-TRN-02839 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02839 |  | 2019-10-15 | 2
036909C-105T-DW-1572-0013 | Instrument Main Cable Routing Cooling Water Unit | B | 2019-10-10 | IBD | OL1-2I34-0013 | IE | 2019-10-14 | 036909C-JVD-TRN-02829 | 036909C-JVD-TRN-02829 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-IE-02829 |  | 2019-10-17 | 1
036909C-105T-DW-1744-0001-008 | Basin For Cooling Tower 10-PIT-5350 - Plan (Formwork) | A | 2019-10-04 | IFR | OL1-2K31-2507 | CV | 2019-10-15 | 036909C-JVD-TRN-02845 | 036909C-JVD-TRN-02845 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02845 |  | 2019-10-17 | 2
036909C-105F-DW-1572-0016 | Instrument Main Cable Tray Routing Flare Area | B | 2019-10-10 | IBD | OL1-2I34-0016 | IE | 2019-10-14 | 036909C-JVD-TRN-02829 | 036909C-JVD-TRN-02829 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-IE-02829 |  | 2019-10-17 | 1
036909C-105F-DW-1741-0001-004 | Foundation For Pipe Rack 10-PRK-5F01 - Pilecap PC3A - Formwork & Reinforcement | A | 2019-10-14 | IFR | OL1-2K31-1543 | CV | 2019-10-15 | 036909C-JVD-TRN-02839 | 036909C-JVD-TRN-02839 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02839 |  | 2019-10-15 | 2
036909C-105F-DW-1741-0001-001 | Foundation For Pipe Rack 10-PRK-5F01 - Plan | A | 2019-10-14 | IFR | OL1-2K31-1540 | CV | 2019-10-15 | 036909C-JVD-TRN-02839 | 036909C-JVD-TRN-02839 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02839 |  | 2019-10-15 | 2
036909C-105F-DW-1741-0001-002 | Foundation For Pipe Rack 10-PRK-5F01 - Pilecap PC2A - Formwork & Reinforcement | A | 2019-10-14 | IFR | OL1-2K31-1541 | CV | 2019-10-15 | 036909C-JVD-TRN-02839 | 036909C-JVD-TRN-02839 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02839 |  | 2019-10-15 | 2
036909C-105F-DW-1741-0001-003 | Foundation For Pipe Rack 10-PRK-5F01 - Pilecap PC2 - Formwork & Reinforcement | A | 2019-10-14 | IFR | OL1-2K31-1542 | CV | 2019-10-15 | 036909C-JVD-TRN-02839 | 036909C-JVD-TRN-02839 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02839 |  | 2019-10-15 | 2
036909C-103A-DW-1744-0002-002 | Foundation For Basin 10-Pit-5601 - Sections - Formwork | A | 2019-10-11 | IFR | OL1-2K31-8438 | CV | 2019-10-15 | 036909C-JVD-TRN-02838 | 036909C-JVD-TRN-02838 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02838 |  | 2019-10-15 | 2
036909C-1053-SP-1513-5302 | Instrument Interlock Descriptions Area 53 Cooling Water System | C | 2019-10-11 | IDD1 | OL1-2G50-5302 | PE | 2019-10-14 | 036909C-JVD-TRN-02836 | 036909C-JVD-TRN-02836 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-PE-02836 |  | 2019-10-15 | 2
036909C-103A-DW-1744-0002-001 | Foundation For Basin 10-Pit-5601 - Plans - Formwork | A | 2019-10-11 | IFR | OL1-2K31-8437 | CV | 2019-10-15 | 036909C-JVD-TRN-02838 | 036909C-JVD-TRN-02838 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02838 |  | 2019-10-15 | 2
036909C-103A-DW-1744-0002-004 | Foundation For Basin 10-Pit-5601 - Sections - Reinforcement | A | 2019-10-11 | IFR | OL1-2K31-8440 | CV | 2019-10-15 | 036909C-JVD-TRN-02839 | 036909C-JVD-TRN-02839 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02839 |  | 2019-10-15 | 2
036909C-103A-DW-1744-0002-003 | Foundation For Basin 10-Pit-5601 - Plans - Reinforcement | A | 2019-10-11 | IFR | OL1-2K31-8439 | CV | 2019-10-15 | 036909C-JVD-TRN-02838 | 036909C-JVD-TRN-02838 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02838 |  | 2019-10-15 | 2
036909C-103S-NM-1652-0001 | SUBSTATION C - Medium Voltage - Switchboard Composition | B | 2019-10-10 | IFQ | OL1-2E15-0005 | EE | 2019-10-11 | 036909C-JVD-TRN-02817 | 036909C-JVD-TRN-02817 | IFA | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-EE-02817 |  | 2019-10-15 | 1
036909C-103A-DW-1572-0012 | Instrument Main Cable Tray Routing Butadiene | B | 2019-10-10 | IBD | OL1-2I34-0012 | IE | 2019-10-14 | 036909C-JVD-TRN-02829 | 036909C-JVD-TRN-02829 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-IE-02829 |  | 2019-10-17 | 1
036909C-103A-DW-1552-0001 | Level Studies And Instrument Design - OSBL - 3A Area | B | 2019-10-11 | IDD | OL1-2I31-0208 | IE | 2019-10-15 | 036909C-JVD-TRN-02844 | 036909C-JVD-TRN-02844 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-IE-02844 |  | 2019-10-15 | 1
036909C-102E-DW-1742-0006-004 | Foundations Compressor Shelter 10-SHT-2E01 -Formworks And Reinforcements- | A | 2019-10-11 | IFR | OL1-2K31-2143 | CV | 2019-10-14 | 036909C-JVD-TRN-02831 | 036909C-JVD-TRN-02831 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02831 |  | 2019-10-17 | 1
036909C-102E-DW-1742-0006-002 | Foundations Compressor Shelter 10-SHT-2E01 -Formworks And Reinforcements- | A | 2019-10-11 | IFR | OL1-2K31-2141 | CV | 2019-10-14 | 036909C-JVD-TRN-02831 | 036909C-JVD-TRN-02831 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02831 |  | 2019-10-17 | 1
036909C-102E-DW-1742-0006-003 | Foundations Compressor Shelter 10-SHT-2E01 -Formworks And Reinforcements- | A | 2019-10-11 | IFR | OL1-2K31-2142 | CV | 2019-10-14 | 036909C-JVD-TRN-02831 | 036909C-JVD-TRN-02831 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02831 |  | 2019-10-17 | 1
036909C-102D-DW-1572-0010 | Instrument Main Cable Tray Routing Process Cold Compressors | B | 2019-10-10 | IBD | OL1-2I34-0010 | IE | 2019-10-14 | 036909C-JVD-TRN-02829 | 036909C-JVD-TRN-02829 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-IE-02829 |  | 2019-10-17 | 1
036909C-102E-DW-1742-0006-001 | Foundations Compressor Shelter 10-SHT-2E01 -Formworks And Reinforcements- | A | 2019-10-11 | IFR | OL1-2K31-2140 | CV | 2019-10-14 | 036909C-JVD-TRN-02831 | 036909C-JVD-TRN-02831 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02831 |  | 2019-10-15 | 1
036909C-102E-CN-1732-0001 | Calculation Note For Foundation Of 10-SHT-2E01 | A | 2019-10-11 | IFR | OL1-2K14-0023 | CV | 2019-10-14 | 036909C-JVD-TRN-02830 | 036909C-JVD-TRN-02830 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-CV-02830 |  | 2019-10-15 | 1
036909C-102C-DW-1572-0009 | Instrument Main Cable Routing Hot Fractionation-GHU Unit | B | 2019-10-10 | IBD | OL1-2I34-0009 | IE | 2019-10-14 | 036909C-JVD-TRN-02829 | 036909C-JVD-TRN-02829 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-IE-02829 |  | 2019-10-17 | 1
036909C-102C-DW-1552-0001 | Level Studies And Instrument Design - ISBL - 2C Area | B | 2019-10-11 | IDD | OL1-2I31-0205 | IE | 2019-10-15 | 036909C-JVD-TRN-02844 | 036909C-JVD-TRN-02844 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-IE-02844 |  | 2019-10-15 | 1
036909C-102D-CN-1733-0021 | Calculation Note For Foundation Of 10-D-2865 | 0 | 2019-10-08 | CAN | OL1-2K13-0109 | CV | 2019-10-11 | 036909C-JVD-TRN-02814 | 036909C-JVD-TRN-02814 | IFA | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-CV-02814 |  | 2019-10-15 | 1
036909C-102D-CN-1733-0017 | Calculation Note For Foundation Of 10-D-2575 | 0 | 2019-10-10 | CAN | OL1-2K13-0105 | CV | 2019-10-11 | 036909C-JVD-TRN-02814 | 036909C-JVD-TRN-02814 | IFA | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-CV-02814 |  | 2019-10-15 | 1
036909C-102B-DW-1552-0001 | Level Studies And Instrument Design - ISBL - 2B Area | B | 2019-10-04 | IDD | OL1-2I31-0204 | IE | 2019-10-15 | 036909C-JVD-TRN-02844 | 036909C-JVD-TRN-02844 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-IE-02844 |  | 2019-10-15 | 1
036909C-102A-DW-1622-0301 | Welding Receptacles Panel Schedule - Zone 2A | A | 2019-10-10 | IFR | OL1-2E42-0026 | EE | 2019-10-11 | 036909C-JVD-TRN-02816 | 036909C-JVD-TRN-02816 | IFR | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-EE-02816 |  | 2019-10-15 | 2
036909C-102A-DW-1743-0021-001 | Foundation For Pumps 10-P-2106 A-B-C | A | 2019-10-08 | IFR | OL1-2K31-0028 | CV | 2019-10-11 | 036909C-JVD-TRN-02815 | 036909C-JVD-TRN-02815 | IFA | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-CV-02815 |  | 2019-10-15 | 1
036909C-102A-DW-1743-0023-001 | Foundation For Pumps 10-P-2006 A-B-C | A | 2019-10-08 | IFR | OL1-2K31-0030 | CV | 2019-10-11 | 036909C-JVD-TRN-02815 | 036909C-JVD-TRN-02815 | IFA | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-CV-02815 |  | 2019-10-15 | 1
036909C-102A-DW-1572-0007 | Instrument Main Cable Routing Quench | B | 2019-10-10 | IBD | OL1-2I34-0007 | IE | 2019-10-14 | 036909C-JVD-TRN-02829 | 036909C-JVD-TRN-02829 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-IE-02829 |  | 2019-10-17 | 1
036909C-1012-PDS-1390-1217 | Piping Specialty Item – Flame Arrestor - Vent Gas to Furnace Firebox FLA-12001-13001 | A | 2019-10-10 | IFR | OL1-2P03-1217 | PE | 2019-10-14 | 036909C-JVD-TRN-02827 | 036909C-JVD-TRN-02827 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-PE-02827 |  | 2019-10-15 | 2
036909C-102A-CN-1733-0005 | Calculation Note For Foundation Of 10-D-2160 | 0 | 2019-10-08 | CAN | OL1-2K13-0011 | CV | 2019-10-11 | 036909C-JVD-TRN-02814 | 036909C-JVD-TRN-02814 | IFA | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-CV-02814 |  | 2019-10-15 | 1
036909C-100S-DW-1572-0004 | Instrument Main Cable Tray Routing Area Substation E And FAR E | B | 2019-10-10 | IBD | OL1-2I34-0004 | IE | 2019-10-11 | 036909C-JVD-TRN-02818 | 036909C-JVD-TRN-02818 | IFA | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-IE-02818 |  | 2019-10-15 | 1
036909C-100S-NM-1652-0001 | SUBSTATION E - Medium Voltage - Switchboard Composition | B | 2019-10-10 | IFQ | OL1-2E15-0004 | EE | 2019-10-11 | 036909C-JVD-TRN-02817 | 036909C-JVD-TRN-02817 | IFA | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-EE-02817 |  | 2019-10-15 | 1
036909C-100P-DW-1552-0001 | Level Studies And Instrument Design ISBL - 0P | B | 2019-10-11 | IDD | OL1-2I31-0201 | IE | 2019-10-15 | 036909C-JVD-TRN-02844 | 036909C-JVD-TRN-02844 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-IE-02844 |  | 2019-10-15 | 1
036909C-100P-DW-1622-0301 | Welding Receptacles Panel Schedule - Zone 0P | A | 2019-10-10 | IFR | OL1-2E42-0018 | EE | 2019-10-11 | 036909C-JVD-TRN-02816 | 036909C-JVD-TRN-02816 | IFR | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-EE-02816 |  | 2019-10-15 | 2
036909C-100P-DW-1572-0003 | Instrument Main Cable Tray Routing Maain Pipe Rack | B | 2019-10-10 | IBD | OL1-2I34-0003 | IE | 2019-10-11 | 036909C-JVD-TRN-02818 | 036909C-JVD-TRN-02818 | IFA | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-IE-02818 |  | 2019-10-15 | 1
036909C-100M-DW-1572-0002 | Instrument Main Cable Tray Routing Metering | B | 2019-10-10 | IBD | OL1-2I34-0002 | IE | 2019-10-11 | 036909C-JVD-TRN-02818 | 036909C-JVD-TRN-02818 | IFA | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-IE-02818 |  | 2019-10-15 | 1
036909C-100C-DW-1552-0001 | Level Studies And Instrument Design - OSLB - 0C Area | B | 2019-10-04 | IDD | OL1-2I31-0200 | IE | 2019-10-15 | 036909C-JVD-TRN-02844 | 036909C-JVD-TRN-02844 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-IE-02844 |  | 2019-10-15 | 1
036909C-1000-PP-301 | Planning Scheduling And Progress Measurement Procedure | 2 | 2019-10-28 | IMP | OL1-2B92-0001 | PC | 2019-10-11 | 036909C-JVD-TRN-02813 | 036909C-JVD-TRN-02813 | IFR | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-PC-02813 |  | 2019-10-15 | 2
036909C-1000-MS-6800-0001 | Technical Specification For Mechanical Erection | 0 | 2019-10-09 | IFP | OL1-2M92-0001 | ME | 2019-10-11 | 036909C-JVD-TRN-02819 | 036909C-JVD-TRN-02819 | IFR | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-ME-02819 |  | 2019-10-15 | 2
036909C-1000-MTO-1574-0001 | Instrument & Fibre Optic Cables Material Take-Off | A | 2019-10-15 | ISSUED FOR 1ST TAKE OFF | OL1-2I54-4101 | IE | 2019-10-15 | 036909C-JVD-TRN-02849 | 036909C-JVD-TRN-02849 | IFR | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-IE-02849 |  | 2019-10-15 | 2
036909C-1000-MTO-1311-0001 | Piping MTO Assembly Collection | 0 | 2019-10-04 | IMP | OL1-2P92-0001 | MP | 2019-10-11 | 036909C-JVD-TRN-02820 | 036909C-JVD-TRN-02820 | IFR | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-MP-02820 |  | 2019-10-15 | 2
036909C-1000-NM-0050-0001 | Battery Limit Summary | D | 2019-10-11 | IFD | OL1-2G60-0001 | PE | 2019-10-14 | 036909C-JVD-TRN-02832 | 036909C-JVD-TRN-02832 | IFR | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-PE-02832 |  | 2019-10-15 | 2
036909C-1000-MR-1547-0002 | Material Requisition for Flow Element Rotameter | A | 2019-09-23 | IFQ | OL1-2C17-010401 | PL | 2019-10-15 | 036909C-JVD-TRN-02847 | 036909C-JVD-TRN-02847 | IFR | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-PL-02847 |  | 2019-10-15 | 2
036909C-1000-ML-235 | Wet Air Oxidation Package SIL Classification Report (Tag No 10-PK-2350) | A | 2019-10-10 | IFR | OL1-2S95-0235 | ES | 2019-10-14 | 036909C-JVD-TRN-02825 | 036909C-JVD-TRN-02825 | IFR | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-ES-02825 |  | 2019-10-15 | Class 2
036909C-1000-ML-215 | Side Stream Filter Package HAZOP Report (Tag No 10-PK-5355) | A | 2019-10-04 | IFR | OL1-2L60-0215 | SE | 2019-10-14 | 036909C-JVD-TRN-02824 | 036909C-JVD-TRN-02824 | IFR | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-SE-02824 |  | 2019-10-15 | 2
036909C-1000-ML-216 | Wet Air Oxidation Package HAZOP Report (Tag No 10-PK-2350) | A | 2019-10-10 | IFR | OL1-2L60-0216 | SE | 2019-10-14 | 036909C-JVD-TRN-02824 | 036909C-JVD-TRN-02824 | IFR | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-SE-02824 |  | 2019-10-15 | Class 2
036909C-1000-DW-1572-0030 | Instrument Main Cable Tray Routing Overall | A | 2019-10-14 | IFR | OL1-2I34-0017 | IE | 2019-10-15 | 036909C-JVD-TRN-02848 | 036909C-JVD-TRN-02848 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-IE-02848 |  | 2019-10-17 | 1
036909C-1000-DW-1552-0002 | Level Instrument Design for Towers and Reactors - OSBL - For Previous Revision See OL1-2I31-0214 | A | 2019-10-11 | IDD | OL1-2I31-0215 | IE | 2019-10-15 | 036909C-JVD-TRN-02844 | 036909C-JVD-TRN-02844 | IFA | 2019-10-30 |  | Transmitted | TPSK-LSPA1-T-IE-02844 | For Previous Revision See OL1-2I31-0214 | 2019-10-15 | 1
036909C-1000-MR-0910-0002 | Material Requisition For API Centrifugal Pumps | 1 | 2019-09-13 | IFP | OL1-2C13-442000 | PL | 2019-09-24 | 036909C-JVD-TRN-02691 | 036909C-JVD-TRN-02691 | IFR | 2019-10-09 | 2019-10-03 | R2-Comments as noted | TPSK-LSPA1-T-PL-02691 |  | 2019-09-26 | 2
036909C-1012-DL-0131-2015 | Deviation List for Utility Steel | 0 | 2019-09-23 | IFP | OL1-2C40-308000 | PL | 2019-09-24 | 036909C-JVD-TRN-02697 | 036909C-JVD-TRN-02697 | IFI |  | 2019-10-14 | R1-No comments | TPSK-LSPA1-T-PL-02697 |  | 2019-09-25 | 3
036909C-105T-ML-251 | Model Review Report Cooling Water Unit Action List 30 Per Cent | 1 | 2019-10-04 | IFI | OL1-2P30-0030 | MP | 2019-10-10 | 036909C-JVD-TRN-02805 | 036909C-JVD-TRN-02805 | IFR | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-MP-02805 |  | 2019-10-11 | 2
036909C-102D-DW-1442-0001 | Major Underground Networks - Zone 2D - Process Cold Compressor - Ex Doc Client Ref OL1-2K36-0006 | B | 2019-10-07 | IDD | OL1-2K26-0006 | CV | 2019-10-10 | 036909C-JVD-TRN-02807 | 036909C-JVD-TRN-02807 | IFA | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-CV-02807 | Ex Doc Client Ref OL1-2K36-0006 | 2019-10-11 | 1
036909C-102A-CN-1733-0039 | Calculation Note For Foundation Of 10-P-2146 A-B | A | 2019-10-08 | IFR | OL1-2K13-0407 | CV | 2019-10-10 | 036909C-JVD-TRN-02806 | 036909C-JVD-TRN-02806 | IFA | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-CV-02806 |  | 2019-10-11 | 1
036909C-102A-CN-1733-0018 | Calculation Note For Foundation Of 10-P-2006 A-B-C | A | 2019-10-08 | IFR | OL1-2K13-0025 | CV | 2019-10-10 | 036909C-JVD-TRN-02806 | 036909C-JVD-TRN-02806 | IFA | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-CV-02806 |  | 2019-10-11 | 1
036909C-102A-CN-1733-0031 | Calculation Note For Foundation Of 10-P-2106 A-B-C | A | 2019-10-08 | IFR | OL1-2K13-0301 | CV | 2019-10-10 | 036909C-JVD-TRN-02806 | 036909C-JVD-TRN-02806 | IFA | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-CV-02806 |  | 2019-10-11 | 1
036909C-1000-NM-0003-1001 | Steam Balance | 0 | 2019-10-09 | IFI | OL1-2G62-1001 | PE | 2019-10-10 | 036909C-JVD-TRN-02811 | 036909C-JVD-TRN-02811 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02811 |  | 2019-10-11 | 3
036909C-1000-NM-0001-1010 | Heat and Material Balance - ISBL Supporting Utilities | 0 | 2019-10-10 | IFI | OL1-2G44-1010 | PE | 2019-10-10 | 036909C-JVD-TRN-02810 | 036909C-JVD-TRN-02810 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02810 |  | 2019-10-11 | 3
036909C-1000-DL-1684-0001 | Deviation List For Cathodic Protection System | 0 | 2019-09-20 | IFP | OL1-2C42-800000 | PL | 2019-09-20 | 036909C-JVD-TRN-02669 | 036909C-JVD-TRN-02669 | IFR | 2019-10-04 | 2019-10-01 | R1-No comments | TPSK-LSPA1-T-PL-02669 |  | 2019-09-20 | 2
036909C-1000-MR-2410-0001 | Material Requisition For Cathodic Protection System | 0 | 2019-10-09 | IFP | OL1-2C16-800000. | PL | 2019-10-11 | 036909C-JVD-TRN-02812 | 036909C-JVD-TRN-02812 | IFR | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-PL-2812 | This doc supersedes previous doc.036909C-1000-MR-1684-0001 | 2019-10-11 | 2
036909C-105U-DW-1622-0201 | Power Layout- Zone 5U | A | 2019-09-20 | IFR | OL1-2E32-0016 | EE | 2019-09-22 | 036909C-JVD-TRN-02677 | 036909C-JVD-TRN-02677 | IFR | 2019-10-06 | 2019-10-01 | A3 - Approved with comments re-submit for review | TPSK-LSPA1-T-EE-02677 |  | 2019-09-23 | 2
036909C-105W-DW-1622-0301 | Welding And Receptacles Panel Schedule - Zone 5W | A | 2019-09-17 | IFR | OL1-2E42-0024 | EE | 2019-09-18 | 036909C-JVD-TRN-02659 | 036909C-JVD-TRN-02659 | IFR | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-EE-02659 |  | 2019-09-19 | 2
036909C-1000-MTO-1621-0002 | Cables Material Take-Off (OSBL Units) | A | 2019-09-13 | IFT1 | OL1-2E63-0009 | EE | 2019-09-18 | 036909C-JVD-TRN-02658 | 036909C-JVD-TRN-02658 | IFR | 2019-10-02 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-EE-02658 |  | 2019-09-19 | 2
036909C-105U-DW-1624-0001 | Electrical Cable Routing Cross Section- Zone 5U | A | 2019-09-20 | IFR | OL1-2E34-0016 | EE | 2019-10-06 | 036909C-JVD-TRN-02678 | 036909C-JVD-TRN-02678 | IFR | 2019-10-06 | 2019-10-01 | R2-Comments as noted | TPSK-LSPA1-T-EE-02678 |  | 2019-09-23 | 2
036909C-102E-DW-1442-0001 | Major Underground Networks - Zone 2E- Ex Doc Client Ref OL1-2K36-0007 | B | 2019-09-27 | IDD | OL1-2K26-0007 | CV | 2019-10-02 | 036909C-JVD-TRN-02752 | 036909C-JVD-TRN-02752 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02752 | Ex Doc Client Ref OL1-2K36-0007 | 2019-10-09 | 1
036909C-102B-DW-1442-0001 | Major Underground Networks - Zone 2B - C3 Hydrogenation - Ex Doc Client Ref OL1-2K36-0004 | B | 2019-09-27 | IDD | OL1-2K26-0004 | ROC Civil | 2019-10-02 | 036909C-JVD-TRN-02759 | 036909C-JVD-TRN-02759 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02759 | Ex Doc Client Ref OL1-2K36-0004 | 2019-10-10 | 1
036909C-101B-DW-1442-0001 | Major Underground Networks - Zone 1B- Furnaces Utilities- Ex Doc Client Ref OL1-2K36-0002 | B | 2019-10-02 | IDD | OL1-2K26-0002 | CV | 2019-10-03 | 036909C-JVD-TRN-02762 | 036909C-JVD-TRN-02762 | IFA | 2019-10-18 |  | Transmitted | TPSK-LSPA1-T-CV-02762 |  | 2019-10-09 | 1
036909C-102C-DW-1442-0001 | Major Underground Networks - Zone 2C | B | 2019-09-23 | IDD | OL1-2K26-0005 | CV | 2019-09-24 | 036909C-JVD-TRN-02694 | 036909C-JVD-TRN-02694 | IFA | 2019-10-09 |  | Transmitted | TPSK-LSPA1-T-CV-02694 |  | 2019-09-25 | 1
036909C-1000-JSD-1530-0003 | Telecom Numbering - Ex Doc Client Ref OL1-2R05-0028 | C | 2019-09-23 | IFR | OL1-2T01-0028 | EE | 2019-10-10 | 036909C-JVD-TRN-02804 | 036909C-JVD-TRN-02804 | IFA | 2019-10-25 |  | Transmitted | TPSK-LSPA1-T-EE-02804 | Ex Doc Client Ref OL1-2R05-0028 | 2019-10-11 | 1
036909C-105W-DW-1622-0101 | Electrical Main Cable Routing Layout - Zone 5W Waste Water Treatment | B | 2019-09-27 | IFR | OL1-2E31-0009 | EE | 2019-10-01 | 036909C-JVD-TRN-02736 | 036909C-JVD-TRN-02736 | IFA | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-EE-02736 |  | 2019-10-09 | 1
036909C-105W-DW-1841-0001-001 | Steel For Pipe Bridge 10-PRK-5W01 - Plans And Elevations | A | 2019-09-26 | IFR | OL1-2K32-8283 | CV | 2019-10-01 | 036909C-JVD-TRN-02740 | 036909C-JVD-TRN-02740 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02740 |  | 2019-10-09 | 2
036909C-105W-DW-1841-0001-002 | Steel For Pipe Bridge 10-PRK-5W01 - Connection Details | A | 2019-09-26 | IFR | OL1-2K32-8284 | CV | 2019-10-01 | 036909C-JVD-TRN-02740 | 036909C-JVD-TRN-02740 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02740 |  | 2019-10-09 | 2
036909C-105U-CN-1831-0001 | CALCULATION NOTE FOR STEEL PIPE RACK 10-PRK-5U01 | A | 2019-09-30 | IFR | OL1-2K15-0004 | CV | 2019-10-09 | 036909C-JVD-TRN-02791 | 036909C-JVD-TRN-02791 | IFR | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-CV-02791 |  | 2019-10-10 | 1
036909C-105T-DW-1745-0002-002 | RETAINING WALL FOR 10-TK-5950 - SECTION - REINFORCEMENT | A | 2019-10-01 | IFR | OL1-2K31-0376 | CV | 2019-10-09 | 036909C-JVD-TRN-02792 | 036909C-JVD-TRN-02792 | IFR | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-CV-02792 |  | 2019-10-10 | 2
036909C-105U-DW-1622-0301 | Welding and Receptacles Panel Schedule- Zone 5U | A | 2019-10-03 | IFQ | OL1-2E42-0032 | EE | 2019-10-08 | 036909C-JVD-TRN-02788 | 036909C-JVD-TRN-02788 | IFA | 2019-10-22 |  | Transmitted | TPSK-LSPA1-T-EE-02788 |  | 2019-10-10 | 2
036909C-105T-CN-1735-0002 | CALCULATION NOTE FOR RETAINING WALL 10-TK-5950 | A | 2019-09-30 | IFR | OL1-2K13-0367 | CV | 2019-10-09 | 036909C-JVD-TRN-02791 | 036909C-JVD-TRN-02791 | IFR | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-CV-02791 |  | 2019-10-10 | 1
036909C-105F-DW-1625-0001 | Substation F Equipement Layout | B | 2019-09-30 | IFR | OL1-2E20-0003 | EE | 2019-10-04 | 036909C-JVD-TRN-02778 | 036909C-JVD-TRN-02778 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-EE-02778 |  | 2019-10-10 | 1
036909C-105F-DW-3432-0001 | Electrical SUB-F And FAR-FL - HVAC Layout | B | 2019-10-01 | IFR | OL1-2H21-0020 | EE | 2019-10-04 | 036909C-JVD-TRN-02774 | 036909C-JVD-TRN-02774 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-EE-02774 |  | 2019-10-10 | 1
036909C-105T-CN-1735-0001 | CALCULATION NOTE FOR RETAINING WALL 10-TK-5900 | A | 2019-09-30 | IFR | OL1-2K13-0366 | CV | 2019-10-09 | 036909C-JVD-TRN-02791 | 036909C-JVD-TRN-02791 | IFR | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-CV-02791 |  | 2019-10-10 | 1
036909C-105F-PFD-3410-0001 | Electrical SUB-F And FAR-FL - HVAC Process Flow Diagram | B | 2019-10-01 | IFR | OL1-2H20-0010 | EE | 2019-10-04 | 036909C-JVD-TRN-02775 | 036909C-JVD-TRN-02775 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-EE-02775 |  | 2019-10-10 | 1
036909C-105F-DW-1844-0001 | Steel Railing For Protection Of Basin 10-PIT-5633 | A | 2019-09-24 | IFR | OL1-2K32-8286 | CV | 2019-10-01 | 036909C-JVD-TRN-02740 | 036909C-JVD-TRN-02740 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02740 |  | 2019-10-09 | 2
036909C-105T-DW-1622-0101 | Electrical Main Cable Routing Layout - Zone 5T Cooling Water Unit | B | 2019-09-30 | IFR | OL1-2E31-0002 | EE | 2019-10-08 | 036909C-JVD-TRN-02787 | 036909C-JVD-TRN-02787 | IFA | 2019-10-22 |  | Transmitted | TPSK-LSPA1-T-EE-2787 |  | 2019-10-10 | 1
036909C-103A-DW-1743-0006 | Foundation For 10-T-3020 | A | 2019-09-06 | IFR | OL1-2K31-0213 | CV | 2019-10-01 | 036909C-JVD-TRN-02741 | 036909C-JVD-TRN-02741 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02741 |  | 2019-10-09 | 2
036909C-1056-SP-0840-5612 | Mechanical Equipment Datasheet for Hydroblast Filter | 0 | 2019-10-02 | IFP | OL1-2M03-5612 | ME | 2019-10-03 | 036909C-JVD-TRN-02767 | 036909C-JVD-TRN-02767 | IFR | 2019-10-18 |  | Transmitted | TPSK-LSPA1-T-ME-02767 |  | 2019-10-10 | 2
036909C-105F-CN-3442-0001 | Electrical SUB-F And FAR-FL - HVAC Thermal Calculation | B | 2019-10-01 | IFR | OL1-2H10-0005 | EE | 2019-10-04 | 036909C-JVD-TRN-02773 | 036909C-JVD-TRN-02773 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-EE-02773 |  | 2019-10-10 | 1
036909C-103A-DW-1743-0005 | Foundation For 10-T-3040 | A | 2019-09-06 | IFR | OL1-2K31-0212 | CV | 2019-10-01 | 036909C-JVD-TRN-02741 | 036909C-JVD-TRN-02741 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02741 |  | 2019-10-09 | 2
036909C-1055-SP-0810-5565 | Mechanical Equipment Data Sheet for Polyolefins Flare Knock-Out Drum | 1 | 2019-10-07 | IFP | OL1-2M03-5565 | ME | 2019-10-07 | 036909C-JVD-TRN-02785 | 036909C-JVD-TRN-02785 | IFR | 2019-10-22 |  | Transmitted | TPSK-LSPA1-T-ME-02785 |  | 2019-10-10 | 2
036909C-103A-NM-1350-0030 | Loads On Rack 10-PRK-3A01 | A | 2019-10-03 | IBD | OL1-2P05-0171 | MP | 2019-10-08 | 036909C-JVD-TRN-02786 | 036909C-JVD-TRN-02786 | IFR | 2019-10-22 |  | Transmitted | TPSK-LSPA1-T-MP-2786 |  | 2019-10-10 | 2
036909C-105F-CN-1734-0001 | CALCULATION NOTE FOR FOUNDATION OF 10-PIT-5633 | A | 2019-10-01 | IFR | OL1-2K13-0347 | CV | 2019-10-09 | 036909C-JVD-TRN-02791 | 036909C-JVD-TRN-02791 | IFR | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-CV-02791 |  | 2019-10-10 | 1
036909C-103A-DW-1431-0001 | Zone 3A - Piling Plan | A | 2019-09-27 | IFR | OL1-2K31-4160 | CV | 2019-10-01 | 036909C-JVD-TRN-02742 | 036909C-JVD-TRN-02742 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02742 |  | 2019-10-09 | 2
036909C-103A-CN-1733-0015 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3126 | A | 2019-10-01 | IFR | OL1-2K13-0214 | CV | 2019-10-09 | 036909C-JVD-TRN-02791 | 036909C-JVD-TRN-02791 | IFR | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-CV-02791 |  | 2019-10-10 | 1
036909C-103A-CN-1733-0005 | Calculation Note For Foundation Of 10-T-3040 | A | 2019-09-13 | IFR | OL1-2K13-0204 | CV | 2019-10-01 | 036909C-JVD-TRN-02739 | 036909C-JVD-TRN-02739 | IFA | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02739 |  | 2019-10-09 | 1
036909C-103A-CN-1733-0006 | Calculation Note For Foundation Of 10-T-3020 | A | 2019-09-13 | IFR | OL1-2K13-0205 | CV | 2019-10-01 | 036909C-JVD-TRN-02739 | 036909C-JVD-TRN-02739 | IFA | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-CV-02739 |  | 2019-10-09 | 1
036909C-103A-CN-1735-0001 | CALCULATION NOTE FOR RETAINING WALL 10-TK-3900 | A | 2019-09-30 | IFR | OL1-2K13-0370 | CV | 2019-10-09 | 036909C-JVD-TRN-02791 | 036909C-JVD-TRN-02791 | IFR | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-CV-02791 |  | 2019-10-10 | 1
036909C-103A-CN-1834-0001 | CALCULATION NOTE FOR STEEL PLATFORM 10-PIT-3190 | A | 2019-09-30 | IFR | OL1-2K15-0098 | CV | 2019-10-09 | 036909C-JVD-TRN-02791 | 036909C-JVD-TRN-02791 | IFR | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-CV-02791 |  | 2019-10-10 | 1
036909C-103A-CN-1733-0021 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3110 | A | 2019-10-01 | IFR | OL1-2K13-0220 | CV | 2019-10-09 | 036909C-JVD-TRN-02791 | 036909C-JVD-TRN-02791 | IFR | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-CV-02791 |  | 2019-10-10 | 1
036909C-103A-CN-1734-0001 | CALCULATION NOTE FOR FOUNDATION OF 10-PIT-3190 | A | 2019-09-30 | IFR | OL1-2K13-0335 | CV | 2019-10-09 | 036909C-JVD-TRN-02791 | 036909C-JVD-TRN-02791 | IFR | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-CV-02791 |  | 2019-10-10 | 1
036909C-102E-DW-1842-0005-002 | Steel Structure For 10-STR-2E04 - Elevations | A | 2019-10-03 | IFR | OL1-2K32-1361 | CV | 2019-10-04 | 036909C-JVD-TRN-02771 | 036909C-JVD-TRN-02771 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02771 |  | 2019-10-10 | 1
036909C-1031-PDS-1541-3102 | Process Data Sheet For BDU LP Desuperheater DH-3102 - Ex Doc Client Ref OL1-2P03-3119 | A | 2019-10-04 | IFR | OL1-2G31-3102 | PE | 2019-10-09 | 036909C-JVD-TRN-02794 | 036909C-JVD-TRN-02794 | IFR | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-PE-02794 |  | 2019-10-10 | 2
036909C-102E-DW-1742-0004-001 | Foundation And Elevation For 10-STR-2E04 | A | 2019-10-01 | IFR | OL1-2K31-1620 | CV | 2019-10-04 | 036909C-JVD-TRN-02776 | 036909C-JVD-TRN-02776 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02776 |  | 2019-10-10 | 1
036909C-102E-DW-1842-0005-001 | Steel Structure For 10-STR-2E04 - Plans | A | 2019-10-03 | IFR | OL1-2K32-1360 | CV | 2019-10-04 | 036909C-JVD-TRN-02771 | 036909C-JVD-TRN-02771 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02771 |  | 2019-10-10 | 1
036909C-1031-PDS-1390-3119 | SP Item Datasheet - BDU LP Steam Desuperheater - SP-31019 - Superseded by OL1-2G31-3102 | 0 | 2019-10-04 | CAN | OL1-2P03-3119 | MP | 2019-10-09 | 036909C-JVD-TRN-02793 | 036909C-JVD-TRN-02793 | IFR | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-MP-02793 | Superseded by OL1-2G31-3102 | 2019-10-10 | 2
036909C-1031-PDS-1390-3118 | SP Item Datasheet - BDU MP Steam Desuperheater - SP-31018 - Superseded by OL1-2G31-3101 | 0 | 2019-10-04 | CAN | OL1-2P03-3118 | MP | 2019-10-09 | 036909C-JVD-TRN-02793 | 036909C-JVD-TRN-02793 | IFR | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-MP-02793 | Superseded by OL1-2G31-3101 | 2019-10-10 | 2
036909C-1031-PDS-1541-3101 | Process Data Sheet For BDU MP Desuperheater DH-3101- Ex Doc Client Ref OL1-2P03-3118 | A | 2019-10-04 | IFR | OL1-2G31-3101 | PE | 2019-10-09 | 036909C-JVD-TRN-02794 | 036909C-JVD-TRN-02794 | IFR | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-PE-02794 | Ex Doc Client Ref OL1-2P03-3118 | 2019-10-10 | 2
036909C-1031-PDS-1541-2402 | Process Data Sheet For LP Depropanizer Desuperheatr DH-2402 - Ex Doc Client Ref OL1-2P03-2412 | A | 2019-10-04 | IFR | OL1-2G31-2402 | PE | 2019-10-09 | 036909C-JVD-TRN-02794 | 036909C-JVD-TRN-02794 | IFR | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-PE-02794 | Ex Doc Client Ref OL1-2P03-2412 | 2019-10-10 | 2
036909C-102B-DW-1841-0001-008 | Steel For Pipe Rack 10-PRK-2B01 – Elevation Stair | A | 2019-09-25 | IFR | OL1-2K32-1167 | CV | 2019-10-02 | 036909C-JVD-TRN-02751 | 036909C-JVD-TRN-02751 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02751 |  | 2019-10-09 | 1
036909C-102E-CN-1732-0005 | Calculation Note For Foundation Of 10-STR-2E04 | A | 2019-09-26 | IFR | OL1-2K14-0041 | CV | 2019-10-04 | 036909C-JVD-TRN-02772 | 036909C-JVD-TRN-02772 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02772 |  | 2019-10-10 | 1
036909C-102E-CN-1832-0005 | Calculation Note For Steel Structure 10-STR-2E04 | A | 2019-10-03 | IFR | OL1-2K15-0016 | CV | 2019-10-04 | 036909C-JVD-TRN-02772 | 036909C-JVD-TRN-02772 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02772 |  | 2019-10-10 | 1
036909C-102B-DW-1841-0001-005 | Steel For Pipe Rack 10-PRK-2B01 - Elevations | A | 2019-09-25 | IFR | OL1-2K32-1164 | CV | 2019-10-02 | 036909C-JVD-TRN-02751 | 036909C-JVD-TRN-02751 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02757 |  | 2019-10-09 | 1
036909C-102B-DW-1841-0001-004 | Steel For Pipe Rack 10-PRK-2B01 - Elevations | A | 2019-09-25 | IFR | OL1-2K32-1163 | CV | 2019-10-02 | 036909C-JVD-TRN-02751 | 036909C-JVD-TRN-02751 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02757 |  | 2019-10-09 | 1
036909C-102B-DW-1841-0001-007 | Steel For Pipe Rack 10-PRK-2B01 – Elevations And Details | A | 2019-09-25 | IFR | OL1-2K32-1166 | CV | 2019-10-02 | 036909C-JVD-TRN-02751 | 036909C-JVD-TRN-02751 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02751 |  | 2019-10-09 | 1
036909C-102B-DW-1841-0001-006 | Steel For Pipe Rack 10-PRK-2B01 - Elevations | A | 2019-09-25 | IFR | OL1-2K32-1165 | CV | 2019-10-02 | 036909C-JVD-TRN-02751 | 036909C-JVD-TRN-02751 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02751 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-014 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Beams | A | 2019-09-25 | IFR | OL1-2K31-1373 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-016 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 – Steel Bracings Details | A | 2019-09-25 | IFR | OL1-2K31-1375 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-015 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 – Steel Bracings Details | A | 2019-09-25 | IFR | OL1-2K31-1374 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102B-DW-1841-0001-003 | Steel For Pipe Rack 10-PRK-2B01 - Plans | A | 2019-09-25 | IFR | OL1-2K32-1162 | CV | 2019-10-02 | 036909C-JVD-TRN-02751 | 036909C-JVD-TRN-02751 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02757 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-013 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Beams | A | 2019-09-25 | IFR | OL1-2K31-1372 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102B-DW-1841-0001-001 | Steel For Pipe Rack 10-PRK-2B01 - 3D View | A | 2019-09-25 | IFR | OL1-2K32-1160 | CV | 2019-10-02 | 036909C-JVD-TRN-02751 | 036909C-JVD-TRN-02751 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02757 |  | 2019-10-09 | 1
036909C-102B-DW-1841-0001-002 | Steel For Pipe Rack 10-PRK-2B01 - Plans | A | 2019-09-25 | IFR | OL1-2K32-1161 | CV | 2019-10-02 | 036909C-JVD-TRN-02751 | 036909C-JVD-TRN-02751 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02757 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-005 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Elevations | A | 2019-09-25 | IFR | OL1-2K31-1364 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-006 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Columns | A | 2019-09-25 | IFR | OL1-2K31-1365 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-007 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Columns | A | 2019-09-25 | IFR | OL1-2K31-1366 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-010 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Columns | A | 2019-09-25 | IFR | OL1-2K31-1369 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-012 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Beams | A | 2019-09-25 | IFR | OL1-2K31-1371 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-011 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Columns | A | 2019-09-25 | IFR | OL1-2K31-1370 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-008 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Columns | A | 2019-09-25 | IFR | OL1-2K31-1367 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-009 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Columns | A | 2019-09-25 | IFR | OL1-2K31-1368 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-004 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Elevations | A | 2019-09-25 | IFR | OL1-2K31-1363 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-002 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Plans | A | 2019-09-25 | IFR | OL1-2K31-1361 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-003 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Elevations | A | 2019-09-25 | IFR | OL1-2K31-1362 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102A-DW-1841-0001-005 | Steel For Pipe Rack 10-PRK-2A01 – Elevations | A | 2019-09-24 | IFR | OL1-2K32-1144 | CV | 2019-10-02 | 036909C-JVD-TRN-02757 | 036909C-JVD-TRN-02757 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02757 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0002-001 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - 3D View | A | 2019-09-25 | IFR | OL1-2K31-1360 | CV | 2019-10-02 | 036909C-JVD-TRN-02753 | 036909C-JVD-TRN-02753 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02753 |  | 2019-10-09 | 1
036909C-102B-CN-1831-0001 | Calculation Notes For Steel Pipe Rack 10-PRK-2B01 | A | 2019-09-25 | IFR | OL1-2K15-0008 | CV | 2019-10-02 | 036909C-JVD-TRN-02756 | 036909C-JVD-TRN-02756 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02756 |  | 2019-10-09 | 1
036909C-102B-CN-1731-0002 | Calculation Notes For Precast Concrete Elevation Of Pipe Rack 10-PRK-2B01 | A | 2019-09-25 | IFR | OL1-2K14-0016 | CV | 2019-10-02 | 036909C-JVD-TRN-02758 | 036909C-JVD-TRN-02758 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02758 |  | 2019-10-09 | 1
036909C-102B-DW-1741-0001-002 | Foundation And Elevation Of Pipe Rack 10-PRK-2B01 - Formwork And Reinforcement | A | 2019-09-25 | IFR | OL1-2K31-1332 | CV | 2019-10-02 | 036909C-JVD-TRN-02760 | 036909C-JVD-TRN-02760 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02760 |  | 2019-10-10 | 1
036909C-102B-DW-1741-0001-001 | Foundation And Elevation Of Pipe Rack 10-PRK-2B01 - Formwork And Reinforcement | A | 2019-09-25 | IFR | OL1-2K31-1331 | CV | 2019-10-02 | 036909C-JVD-TRN-02760 | 036909C-JVD-TRN-02760 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02760 |  | 2019-10-10 | 1
036909C-102A-DW-1844-0002-001 | Steel Structures For Concrete Basin 10-PIT-2090 | A | 2019-09-30 | IFR | OL1-2K32-7420 | CV | 2019-10-04 | 036909C-JVD-TRN-02771 | 036909C-JVD-TRN-02771 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02771 |  | 2019-10-10 | 1
036909C-102A-DW-1841-0001-003 | Steel For Pipe Rack 10-PRK-2A01 – Plans And Sections | A | 2019-09-24 | IFR | OL1-2K32-1142 | CV | 2019-10-02 | 036909C-JVD-TRN-02757 | 036909C-JVD-TRN-02757 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02757 |  | 2019-10-09 | 1
036909C-102A-DW-1841-0001-004 | Steel For Pipe Rack 10-PRK-2A01 – Elevations And Sections | A | 2019-09-24 | IFR | OL1-2K32-1143 | CV | 2019-10-02 | 036909C-JVD-TRN-02757 | 036909C-JVD-TRN-02757 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02757 |  | 2019-10-09 | 1
036909C-102A-DW-1841-0001-001 | Steel For Pipe Rack 10-PRK-2A01 - 3D View | A | 2019-09-24 | IFR | OL1-2K32-1145 | CV | 2019-10-03 | 036909C-JVD-TRN-02763 | 036909C-JVD-TRN-02763 | IFA | 2019-10-18 |  | Transmitted | TPSK-LSPA1-T-CV-02763 |  | 2019-10-10 | 1
036909C-102A-DW-1841-0001-002 | Steel For Pipe Rack 10-PRK-2A01 - Plans And Sections | A | 2019-09-24 | IFR | OL1-2K32-1146 | CV | 2019-10-03 | 036909C-JVD-TRN-02763 | 036909C-JVD-TRN-02763 | IFA | 2019-10-18 |  | Transmitted | TPSK-LSPA1-T-CV-02763 |  | 2019-10-10 | 1
036909C-1027-PDS-1541-2701 | Process Data Sheet For Depentanizer-Rerun Tower Desuperheater DH-2701 - Ex Doc CLient Ref OL1-2P03-2710 | A | 2019-10-04 | IFR | OL1-2G31-2710 | PE | 2019-10-09 | 036909C-JVD-TRN-02794 | 036909C-JVD-TRN-02794 | IFR | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-PE-02794 | Ex Doc CLient Ref OL1-2P03-2710 | 2019-10-10 | 2
036909C-102A-DW-1552-0001 | Level Instrument Design and Nozzle Study for Quench - ISBL (2A) | C | 2019-09-30 | IDD | OL1-2I31-0203 | IE | 2019-10-08 | 036909C-JVD-TRN-02789 | 036909C-JVD-TRN-02789 | IFA | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-IE-02789 |  | 2019-10-10 | 1
036909C-1027-PDS-1390-2710 | SP Item Datasheet - Desuperheater - HP Steam to E-2715 A-B & E-2725 A-C - SP-27010 - Superseded by OL1-2G31-2710 | 0 | 2019-10-04 | CAN | OL1-2P03-2710 | MP | 2019-10-09 | 036909C-JVD-TRN-02793 | 036909C-JVD-TRN-02793 | IFR | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-MP-02793 | Superseded by OL1-2G31-2710 | 2019-10-10 | 2
036909C-1024-PDS-1541-2401 | Process Data Sheet For HP Depropanizer Desuperheater DH-2401 - Ex Doc Client Ref OL1-2P03-2409 | A | 2019-10-04 | IFR | OL1-2G31-2411 | PE | 2019-10-09 | 036909C-JVD-TRN-02794 | 036909C-JVD-TRN-02794 | IFR | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-PE-02794 | Ex Doc Client Ref OL1-2P03-2409 | 2019-10-10 | 2
036909C-102A-CN-1834-0002 | Calculation For Steel Platform For 10-PIT-2090 | A | 2019-09-30 | IFR | OL1-2K15-0110 | CV | 2019-10-04 | 036909C-JVD-TRN-02772 | 036909C-JVD-TRN-02772 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02772 |  | 2019-10-10 | 1
036909C-102A-DW-1442-0001 | Major Underground Networks Zone 2A - Quench - Ex Doc Client Ref OL1-2K36-0003 | B | 2019-10-07 | IDD | OL1-2K26-0003 | CV | 2019-10-09 | 036909C-JVD-TRN-02797 | 036909C-JVD-TRN-02797 | IFA | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-CV-02797 | Ex Doc Client Ref OL1-2K36-0003 | 2019-10-10 | 1
036909C-1020-SP-0840-2014 | Mechanical Equipment Datasheet for QO Pump Purge Oil Filter | 0 | 2019-10-02 | IFP | OL1-2M03-2014 | ME | 2019-10-03 | 036909C-JVD-TRN-02767 | 036909C-JVD-TRN-02767 | IFR | 2019-10-18 |  | Transmitted | TPSK-LSPA1-T-ME-02767 |  | 2019-10-10 | 2
036909C-101B-DW-1842-0002-002 | Steel For Structure 10-STR-1B01 - Plans | A | 2019-09-30 | IFR | OL1-2K32-3081 | CV | 2019-10-02 | 036909C-JVD-TRN-02757 | 036909C-JVD-TRN-02757 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02757 |  | 2019-10-09 | 1
036909C-1023-SP-0910-2325 | Mechanical Equipment Datasheet For 10% Caustic Makeup Pumps | 0 | 2019-10-11 | IFP | OL1-2M03-2325 | ME | 2019-10-07 | 036909C-JVD-TRN-02781 | 036909C-JVD-TRN-02781 | IFR | 2019-10-22 |  | Transmitted | TPSK-LSPA1-T-MP-02793 |  | 2019-10-10 | 2
036909C-101B-DW-1842-0002-001 | Steel For Structure 10-STR-1B01 - 3D View | A | 2019-09-30 | IFR | OL1-2K32-3080 | CV | 2019-10-02 | 036909C-JVD-TRN-02757 | 036909C-JVD-TRN-02757 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02757 |  | 2019-10-10 | 1
036909C-101B-DW-1842-0002-005 | Steel For Structure 10-STR-1B01 - Elevations | A | 2019-09-30 | IFR | OL1-2K32-3084 | CV | 2019-10-02 | 036909C-JVD-TRN-02757 | 036909C-JVD-TRN-02757 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02757 |  | 2019-10-09 | 1
036909C-101B-DW-1742-0002-001 | Foundation Of 10-STR-1B01 - Formwork And Reinforcement | A | 2019-10-04 | IFR | OL1-2K31-2460 | CV | 2019-10-09 | 036909C-JVD-TRN-02798 | 036909C-JVD-TRN-02798 | IFA | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-CV-02798 |  | 2019-10-10 | 1
036909C-101B-DW-1842-0002-003 | Steel For Structure 10-STR-1B01 - Plans | A | 2019-09-30 | IFR | OL1-2K32-3082 | CV | 2019-10-02 | 036909C-JVD-TRN-02757 | 036909C-JVD-TRN-02757 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02757 |  | 2019-10-09 | 1
036909C-101B-DW-1842-0002-004 | Steel For Structure 10-STR-1B01 - Elevations | A | 2019-09-30 | IFR | OL1-2K32-3083 | CV | 2019-10-02 | 036909C-JVD-TRN-02757 | 036909C-JVD-TRN-02757 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02757 |  | 2019-10-09 | 1
036909C-1024-PDS-1390-2409 | Piping Specialty Item - Datasheet - Desuperheater - SP-24009 - Superseded by OL1-2G31-2411 | 0 | 2019-10-04 | CAN | OL1-2P03-2409 | PE | 2019-10-09 | 036909C-JVD-TRN-02793 | 036909C-JVD-TRN-02793 | IFR | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-MP-02793 | Superseded by OL1-2G31-2411 | 2019-10-10 | 2
036909C-101B-CN-1832-0002 | Calculation Note For Steel Structure 10-STR-1B01 | A | 2019-09-30 | IFR | OL1-2K15-0060 | CV | 2019-10-02 | 036909C-JVD-TRN-02756 | 036909C-JVD-TRN-02756 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-CV-02756 |  | 2019-10-09 | 1
036909C-1012-MR-1546-1253 | Material Requisition for Orifice Plate & Restriction Orifice | 1 | 2019-10-08 | IFP | OL1-2C17-012253 | PL | 2019-10-09 | 036909C-JVD-TRN-02803 | 036909C-JVD-TRN-02803 | IFR | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-PL-02803 |  | 2019-10-10 | 2
036909C-101B-CN-1732-0002 | Calculation Note For Foundations Of 10-STR-1B01 | A | 2019-09-30 | IFR | OL1-2K14-0073 | CV | 2019-10-09 | 036909C-JVD-TRN-02799 | 036909C-JVD-TRN-02799 | IFA | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-CV-02799 |  | 2019-10-10 | 1
036909C-1012-DW-0131-2540 | USC 132U Cracking Furnace Steel Crossover Limit Stop Details | 2 | 2019-10-01 | IMP | OL1-2K32-2540 | CV | 2019-10-01 | 036909C-JVD-TRN-02749 | 036909C-JVD-TRN-02749 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02749 |  | 2019-10-09 | 3
036909C-1011-DW-0131-1540 | USC 36M Recycle Furnace Steel Crossover Limit Stop Details | 2 | 2019-10-01 | IMP | OL1-2K32-1540 | CV | 2019-10-01 | 036909C-JVD-TRN-02749 | 036909C-JVD-TRN-02749 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02749 |  | 2019-10-09 | 3
036909C-100S-PFD-3410-0001 | Electrical SUB-E And FAR-E - HVAC Process Flow Diagram | B | 2019-10-01 | IFR | OL1-2H20-0001 | EE | 2019-10-04 | 036909C-JVD-TRN-02775 | 036909C-JVD-TRN-02775 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-EE-02775 |  | 2019-10-10 | 1
036909C-100S-CN-3442-0001 | Electrical SUB-E And FAR-E - HVAC Thermal Calculation | B | 2019-10-01 | IFR | OL1-2H10-0001 | EE | 2019-10-04 | 036909C-JVD-TRN-02773 | 036909C-JVD-TRN-02773 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-EE-02773 |  | 2019-10-10 | 1
036909C-100P-DW-1741-0002-014 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Steel Bracings Details | 0 | 2019-10-02 | IFC | OL1-2K31-1033 | CV | 2019-10-04 | 036909C-JVD-TRN-02770 | 036909C-JVD-TRN-02770 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02770 |  | 2019-10-10 | 1
036909C-1012-MR-0131-2016 | Material Requisition for Utility Steel | 0 | 2019-10-03 | IFP | OL1-2C12-308000 | PL | 2019-10-07 | 036909C-JVD-TRN-02784 | 036909C-JVD-TRN-02784 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02784 |  | 2019-10-10 | 3
036909C-100S-DW-3432-0001 | Electrical SUB-E And FAR-E - HVAC Layout | B | 2019-10-01 | IFR | OL1-2H21-0001 | EE | 2019-10-04 | 036909C-JVD-TRN-02774 | 036909C-JVD-TRN-02774 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-EE-02774 |  | 2019-10-10 | 1
036909C-100P-DW-1741-0002-013 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Steel Bracings Details | 0 | 2019-10-02 | IFC | OL1-2K31-1032 | CV | 2019-10-09 | 036909C-JVD-TRN-02800 | 036909C-JVD-TRN-02800 | IFA | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-CV-02800 |  | 2019-10-10 | 1
036909C-100P-DW-1741-0002-009 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Columns | 0 | 2019-10-02 | IFC | OL1-2K31-1028 | CV | 2019-10-04 | 036909C-JVD-TRN-02770 | 036909C-JVD-TRN-02770 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02770 |  | 2019-10-10 | 1
036909C-100P-DW-1741-0002-008 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Columns | 0 | 2019-10-02 | IFC | OL1-2K31-1027 | CV | 2019-10-04 | 036909C-JVD-TRN-02770 | 036909C-JVD-TRN-02770 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02770 |  | 2019-10-10 | 1
036909C-100P-DW-1741-0002-007 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Columns | 0 | 2019-10-02 | IFC | OL1-2K31-1026 | CV | 2019-10-04 | 036909C-JVD-TRN-02770 | 036909C-JVD-TRN-02770 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02770 |  | 2019-10-10 | 1
036909C-100P-DW-1741-0002-012 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Beams | 0 | 2019-10-02 | IFC | OL1-2K31-1031 | CV | 2019-10-04 | 036909C-JVD-TRN-02770 | 036909C-JVD-TRN-02770 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02770 |  | 2019-10-10 | 1
036909C-100P-DW-1741-0002-010 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Beams | 0 | 2019-10-02 | IFC | OL1-2K31-1029 | CV | 2019-10-04 | 036909C-JVD-TRN-02770 | 036909C-JVD-TRN-02770 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02770 |  | 2019-10-10 | 1
036909C-100P-DW-1741-0002-011 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Beams | 0 | 2019-10-02 | IFC | OL1-2K31-1030 | CV | 2019-10-04 | 036909C-JVD-TRN-02770 | 036909C-JVD-TRN-02770 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02770 |  | 2019-10-10 | 1
036909C-100P-CN-1731-0002 | Calculation Note For Precast Concrete Pipe Rack 10-PRK-0P01 - For Previous revision see OL1-2K14-0001 | 0 | 2019-10-02 | IFC | OL1-2K14-0002 | CV | 2019-10-07 | 036909C-JVD-TRN-02783 | 036909C-JVD-TRN-02783 | IFA | 2019-10-22 |  | Transmitted | TPSK-LSPA1-T-CV-02783 | For Previous revision see OL1-2K14-0001 | 2019-10-10 | 1
036909C-100C-DW-1452-0001-004 | GRADING UNDERGROUND AND FOUNDATION PLAN - ZONE OC - COMMON AREA | A | 2019-10-07 | IFR | OL1-2K26-1044 | CV | 2019-10-09 | 036909C-JVD-TRN-02790 | 036909C-JVD-TRN-02790 | IFR | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-CV-02790 |  | 2019-10-10 | 2
036909C-100P-DW-1741-0002-006 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Elevations | 0 | 2019-10-02 | IFC | OL1-2K31-1025 | CV | 2019-10-04 | 036909C-JVD-TRN-02770 | 036909C-JVD-TRN-02770 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02770 |  | 2019-10-10 | 1
036909C-100P-DW-1741-0002-005 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Elevations | 0 | 2019-10-02 | IFC | OL1-2K31-1024 | CV | 2019-10-04 | 036909C-JVD-TRN-02770 | 036909C-JVD-TRN-02770 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02770 |  | 2019-10-10 | 1
036909C-100P-DW-1741-0002-002 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Plans | 0 | 2019-10-02 | IFC | OL1-2K31-1021 | CV | 2019-10-04 | 036909C-JVD-TRN-02770 | 036909C-JVD-TRN-02770 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02770 |  | 2019-10-10 | 1
036909C-100P-DW-1741-0002-003 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Plans | 0 | 2019-10-02 | IFC | OL1-2K31-1022 | CV | 2019-10-04 | 036909C-JVD-TRN-02770 | 036909C-JVD-TRN-02770 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02770 |  | 2019-10-10 | 1
036909C-100P-DW-1741-0002-004 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Elevations | 0 | 2019-10-02 | IFC | OL1-2K31-1023 | CV | 2019-10-04 | 036909C-JVD-TRN-02770 | 036909C-JVD-TRN-02770 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02770 |  | 2019-10-10 | 1
036909C-100P-DW-1741-0002-001 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - 3D View | 0 | 2019-10-02 | IFC | OL1-2K31-1020 | CV | 2019-10-04 | 036909C-JVD-TRN-02770 | 036909C-JVD-TRN-02770 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-CV-02770 |  | 2019-10-10 | 1
036909C-100C-DW-1452-0001-002 | GRADING UNDERGROUND AND FOUNDATION PLAN - ZONE OC - COMMON AREA | A | 2019-09-30 | IFR | OL1-2K26-1042 | CV | 2019-10-09 | 036909C-JVD-TRN-02790 | 036909C-JVD-TRN-02790 | IFR | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-CV-02790 |  | 2019-10-10 | 2
036909C-100C-DW-1452-0001-003 | GRADING UNDERGROUND AND FOUNDATION PLAN - ZONE OC - COMMON AREA | A | 2019-09-30 | IFR | OL1-2K26-1043 | CV | 2019-10-09 | 036909C-JVD-TRN-02790 | 036909C-JVD-TRN-02790 | IFR | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-CV-02790 |  | 2019-10-10 | 2
036909C-100C-DW-1452-0001-001 | GRADING UNDERGROUND AND FOUNDATION PLAN - ZONE OC - COMMON AREA | A | 2019-09-30 | IFR | OL1-2K26-1041 | CV | 2019-10-09 | 036909C-JVD-TRN-02790 | 036909C-JVD-TRN-02790 | IFR | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-CV-02790 |  | 2019-10-10 | 2
036909C-1000-PP-842 | Project Induced In-Migration Management Plan | 0 | 2019-09-20 | IMP | OL1-2J92-0007 | HR | 2019-10-01 | 036909C-JVD-TRN-02745 | 036909C-JVD-TRN-02745 | IFR | 2019-10-16 |  | Transmitted | TPSK-LSPA1-T-HR-02745 |  | 2019-10-09 | 2
036909C-1000-SP-1564-0001 | Instrument Data Sheet For Water Analyzer | A | 2019-09-30 | IFQ | OL1-2I20-2403 | IE | 2019-10-02 | 036909C-JVD-TRN-02761 | 036909C-JVD-TRN-02761 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-IE-02761 |  | 2019-10-09 | 1
036909C-1000-STC-1391-0000 | Standard Auxiliary Piping Support Collection | 1 | 2019-09-24 | IMP | OL1-2P25-0085 | MP | 2019-10-09 | 036909C-JVD-TRN-02795 | 036909C-JVD-TRN-02795 | IFR | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-MP-02795 |  | 2019-10-10 | 2
036909C-1000-PP-268 | Piping Spooling Into 3D Model | A | 2019-09-16 | IFR | OL1-2P92-0013 | MP | 2019-10-09 | 036909C-JVD-TRN-02796 | 036909C-JVD-TRN-02796 | IFR | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-MP-02796 |  | 2019-10-10 | 2
036909C-1000-PP-269 | Spooling Activity Definition | A | 2019-09-16 | IFR | OL1-2P92-0014 | MP | 2019-10-09 | 036909C-JVD-TRN-02796 | 036909C-JVD-TRN-02796 | IFR | 2019-10-24 |  | Transmitted | TPSK-LSPA1-T-MP-02796 |  | 2019-10-10 | 2
036909C-1000-PO-036909C001P105-105 | Vendor's Acknowledgment of Purchase Order for Condensate Polisher Package - MR 0213-0001 | 0 | 2019-10-01 | IFI | OL1-2C51-0126 | PL | 2019-10-01 | 036909C-JVD-TRN-02743 | 036909C-JVD-TRN-02743 | IFI | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-PL-02743 |  | 2019-10-09 | 3
036909C-1000-PO-036909C001P104-104 | Vendor's Acknowledgment of Purchase Order for Trays for Columns (C4 Unit) - MR 0570-0003 | 0 | 2019-09-24 | IFI | OL1-2C51-0124 | PL | 2019-10-01 | 036909C-JVD-TRN-02743 | 036909C-JVD-TRN-02743 | IFI | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-PL-02743 |  | 2019-10-09 | 3
036909C-1000-PO-036909C001P107-107 | Vendor's Acknowledgment of Purchase Order for Shop Assembled Columns (C4 Unit) MR 0511-0003 | 0 | 2019-09-26 | IFI | OL1-2C51-0125 | PL | 2019-10-01 | 036909C-JVD-TRN-02743 | 036909C-JVD-TRN-02743 | IFI | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-PL-02743 |  | 2019-10-09 | 3
036909C-1000-PO-036909C001P74-074 | Vendor's Acknowledgment of Purchase Order for Freight Forwarding Services - MR 6720-0001 | 0 | 2019-08-16 | IFI | OL1-2C51-0116 | PL | 2019-10-01 | 036909C-JVD-TRN-02744 | 036909C-JVD-TRN-02744 | IFI | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-PL-02744 |  | 2019-10-09 | 3
036909C-1000-NM-0001-1012 | Heat & Material Balance Area 55 - Flare System | 1 | 2019-09-30 | IFI | OL1-2G44-1012 | PE | 2019-10-02 | 036909C-JVD-TRN-02755 | 036909C-JVD-TRN-02755 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02755 |  | 2019-10-09 | 3
036909C-1000-NM-0003-1008 | Fuel Balance | 0 | 2019-10-03 | IFI | OL1-2G62-1008 | PE | 2019-10-07 | 036909C-JVD-TRN-02780 | 036909C-JVD-TRN-02780 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02780 |  | 2019-10-10 | 3
036909C-1000-MTO-1574-1001 | Furnace - Instrument_Telecom and Fibre Optic Cables Material Take-Off | A | 2019-10-03 | IFR | OL1-2I54-1001 | IE | 2019-10-03 | 036909C-JVD-TRN-02766 | 036909C-JVD-TRN-02766 | IFR | 2019-10-18 |  | Transmitted | TPSK-LSPA1-T-IE-02766 |  | 2019-10-10 | 2
036909C-1000-MR-1800-0002 | Material Requisition For Steel Structures | 0 | 2019-10-02 | IFP | OL1-2C12-000002 | PL | 2019-10-04 | 036909C-JVD-TRN-02769 | 036909C-JVD-TRN-02769 | IFR | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-PL-02769 | In next revision should be included in MR the PLG (Doc Ref: 036909C-1000-PLG-1800-0002-001/002/003) | 2019-10-10 | 2
036909C-1000-NM-0001-1011 | Heat & Material Balance - Cooling Water System | 0 | 2019-10-03 | IFI | OL1-2G44-1011 | PE | 2019-10-07 | 036909C-JVD-TRN-02780 | 036909C-JVD-TRN-02780 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-02780 |  | 2019-10-10 | 3
036909C-1000-DW-1552-0001 | Level Instrument Design For Towers and Reactors | B | 2019-09-19 | IDD | OL1-2I31-0214 | IE | 2019-10-08 | 036909C-JVD-TRN-02789 | 036909C-JVD-TRN-02789 | IFA | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-IE-02789 |  | 2019-10-10 | 1
036909C-1000-DW-1576-0005 | Instr Supports Typical Mount Details | C | 2019-09-27 | IDD | OL1-2I31-0001 | IE | 2019-10-08 | 036909C-JVD-TRN-02789 | 036909C-JVD-TRN-02789 | IFA | 2019-10-23 |  | Transmitted | TPSK-LSPA1-T-IE-02789 |  | 2019-10-10 | 1
036909C-1000-MR-0910-0004 | Material Requisition For High Speed Pumps | 0 | 2019-10-11 | IFP | OL1-2C13-444000 | PL | 2019-10-07 | 036909C-JVD-TRN-02782 | 036909C-JVD-TRN-02782 | IFR | 2019-10-22 |  | Transmitted | TPSK-LSPA1-T-PL-02782 | For inquiry refer to MR OL1-2C13-442000 | 2019-10-10 | 2
036909C-1000-MR-1800-0001 | Material Requisition For Steel Structures | 0 | 2019-10-02 | IFP | OL1-2C12-000001 | PL | 2019-10-04 | 036909C-JVD-TRN-02768 | 036909C-JVD-TRN-02768 | IFR | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-PL-02768 | In next revision should be included in MR the PLG (Doc Ref: 036909C-1000-PLG-1800-0001-001/002/003) | 2019-10-10 | 2
036909C-1000-JSS-1584-0001 | JSS for Cross Check Custody Metering System | A | 2019-09-30 | IFR | OL1-2I92-0057 | IE | 2019-10-01 | 036909C-JVD-TRN-02738 | 036909C-JVD-TRN-02738 | IFA | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-IE-02738 |  | 2019-10-09 | 1
036909C-1000-CN-1626-0001 | Electrical Power Balance | B | 2019-09-25 | IFR | OL1-2E10-0002 | EE | 2019-10-01 | 036909C-JVD-TRN-02748 | 036909C-JVD-TRN-02748 | IFA | 2019-10-16 |  | Transmitted | TPSK-LSPA1-T-EE-02748 |  | 2019-10-09 | 1
036909C-1000-CN-1651-0002 | Load And Flow Voltage Drop Analysis | B | 2019-09-27 | IFR | OL1-2E10-0005 | EE | 2019-10-01 | 036909C-JVD-TRN-02748 | 036909C-JVD-TRN-02748 | IFA | 2019-10-16 |  | Transmitted | TPSK-LSPA1-T-EE-02748 |  | 2019-10-09 | 1
036909C-1000-CN-1651-0001 | Short-Circuit Analysis | B | 2019-09-27 | IFR | OL1-2E10-0004 | EE | 2019-10-04 | 036909C-JVD-TRN-02777 | 036909C-JVD-TRN-02777 | IFA | 2019-10-21 |  | Transmitted | TPSK-LSPA1-T-EE-02777 |  | 2019-10-10 | 1
036909C-1000-MR-1541-0002 | Material Requisition for Severe Service Control Valves | A | 2019-09-13 | IFQ | OL1-2C17-050501 | PL | 2019-09-18 | 036909C-JVD-TRN-02664 | 036909C-JVD-TRN-02664 | IFR | 2019-10-03 | 2019-09-27 | R2-Comments as noted | TPSK-LSPA1-T-PL-02664 | ATT. NE C'è il ifle excel ( attachment 4 allegato come native file dell'MR) | 2019-09-19 | 2
036909C-1011-DW-0131-1540 | USC 36M Recycle Furnace Steel Crossover Limit Stop Details | 1 | 2019-09-17 | IMP | OL1-2K32-1540 | CV | 2019-09-18 | 036909C-JVD-TRN-02667 | 036909C-JVD-TRN-02668, 036909C-JVD-TRN-02667 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02667 |  | 2019-09-19 | 3
036909C-1012-TBT-0131-2016 | Technical Bid Tabulation for Utility Steel | 0 | 2019-09-23 | IFI | OL1-2C23-2016 | PL | 2019-09-24 | 036909C-JVD-TRN-02698 | 036909C-JVD-TRN-02698 | IFI |  | 2019-10-08 | R1-No comments | TPSK-LSPA1-T-PL-02698 |  | 2019-09-25 | 3
036909C-1012-TBT-1564-2209 | Technical Bid Tabulation for pH & Conductivity Analyzers | 0 | 2019-07-29 | IFI | OL1-2C23-2209 | PL | 2019-09-16 | 036909C-JVD-TRN-02652 | 036909C-JVD-TRN-02652 | IFI |  | 2019-10-08 | R2-Comments as noted | TPSK-LSPA1-T-PL-02652 |  | 2019-09-17 | 3
036909C-102D-DW-1743-0002-003 | Foundation And Elevation For 10-C-2800 - Plants - Foundation Elevations And Lube Oil Console - Reinforcements | A | 2019-09-26 | IFR | OL1-2K31-3002 | CV | 2019-09-27 | 036909C-JVD-TRN-02730 | 036909C-JVD-TRN-02730 | IFA | 2019-10-14 |  | Transmitted | TPSK-LSPA1-T-CV-02730 |  | 2019-10-04 | 1
036909C-102D-DW-1743-0002-002 | Foundation And Elevation For 10-C-2800 - Sections And Details - (Formworks) | A | 2019-09-26 | IFR | OL1-2K31-3001 | CV | 2019-09-27 | 036909C-JVD-TRN-02730 | 036909C-JVD-TRN-02730 | IFA | 2019-10-14 |  | Transmitted | TPSK-LSPA1-T-CV-02730 |  | 2019-10-04 | 1
036909C-102D-DW-1743-0002-005 | Foundation And Elevation For 10-C-2800 - Details - Reinforcements | A | 2019-09-26 | IFR | OL1-2K31-3004 | CV | 2019-09-27 | 036909C-JVD-TRN-02730 | 036909C-JVD-TRN-02730 | IFA | 2019-10-14 |  | Transmitted | TPSK-LSPA1-T-CV-02730 |  | 2019-10-04 | 1
036909C-102D-DW-1743-0002-004 | Foundation And Elevation For 10-C-2800 - Sections - Reinforcements | A | 2019-09-26 | IFR | OL1-2K31-3003 | CV | 2019-09-27 | 036909C-JVD-TRN-02730 | 036909C-JVD-TRN-02730 | IFA | 2019-10-14 |  | Transmitted | TPSK-LSPA1-T-CV-02730 |  | 2019-10-04 | 1
036909C-102C-DW-1742-0007-002 | Foundation And Elevation Of Concrete Structure 10-STR-2C07 | A | 2019-09-26 | IFR | OL1-2K31-1701 | CV | 2019-09-27 | 036909C-JVD-TRN-02730 | 036909C-JVD-TRN-02730 | IFA | 2019-10-14 |  | Transmitted | TPSK-LSPA1-T-CV-02730 |  | 2019-10-04 | 1
036909C-102C-DW-1742-0007-003 | Foundation And Elevation Of Concrete Structure 10-STR-2C07 | A | 2019-09-26 | IFR | OL1-2K31-1702 | CV | 2019-09-27 | 036909C-JVD-TRN-02730 | 036909C-JVD-TRN-02730 | IFA | 2019-10-14 |  | Transmitted | TPSK-LSPA1-T-CV-02730 |  | 2019-10-04 | 1
036909C-102D-DW-1743-0002-001 | Foundation And Elevation For 10-C-2800 - Plants - Foundations And Elevations - Formworks | A | 2019-09-26 | IFR | OL1-2K31-3000 | CV | 2019-09-27 | 036909C-JVD-TRN-02730 | 036909C-JVD-TRN-02730 | IFA | 2019-10-14 |  | Transmitted | TPSK-LSPA1-T-CV-02730 |  | 2019-10-04 | 1
036909C-102C-DW-1742-0007-001 | Foundation And Elevation Of Concrete Structure 10-STR-2C07 | A | 2019-09-26 | IFR | OL1-2K31-1700 | CV | 2019-09-27 | 036909C-JVD-TRN-02730 | 036909C-JVD-TRN-02730 | IFA | 2019-10-14 |  | Transmitted | TPSK-LSPA1-T-CV-02730 |  | 2019-10-04 | 1
036909C-1056-PDS-0200-5633 | Process Equipment Datasheet - 10-PIT-5633 - HP Flare Area Stormwater Sump | C | 2019-09-27 | IFD | OL1-2G30-5633 | PE | 2019-09-30 | 036909C-JVD-TRN-02735 | 036909C-JVD-TRN-02735 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-PE-02735 |  | 2019-10-04 | 2
036909C-1056-PDS-0200-5632 | Process Equipment Datasheet - 10-PIT-5632 - HP Flare Area Oily WW Sump | 0 | 2019-09-27 | CAN | OL1-2G30-5632 | PE | 2019-09-30 | 036909C-JVD-TRN-02735 | 036909C-JVD-TRN-02735 | IFR | 2019-10-15 |  | Transmitted | TPSK-LSPA1-T-PE-02735 |  | 2019-10-04 | 2
036909C-1011-DW-0132-1102 | USC 36M Recycle Furnace Refractory and Insulation Convection Section Details | 1 | 2019-09-12 | IMP | OL1-2M06-1102 | ME | 2019-10-02 | 036909C-JVD-TRN-02700 | 036909C-JVD-TRN-02700 | IFR | 2019-10-09 |  | Transmitted | TPSK-LSPA1-T-ME-02700 |  | 2019-09-25 | 2
036909C-1000-NM-1990-0001 | HAZOP And SIL Classification Actions Register | B | 2019-09-24 | IFR | OL1-2L60-0002 | SE | 2019-09-25 | 036909C-JVD-TRN-02716 | 036909C-JVD-TRN-02716 | IFR | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-SE-02716 |  | 2019-09-28 | 2
036909C-1000-NM-1990-0202 | Recovery Process And Utilities Section HAZOP FEED Recommendations Mitigation Report - Second Batch | A | 2019-09-24 | IFA | OL1-2L62-0004 | SE | 2019-09-25 | 036909C-JVD-TRN-02717 | 036909C-JVD-TRN-02717 | IFA | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-SE-02717 |  | 2019-09-28 | 1
036909C-1012-DW-0131-2601 | USC 132U Cracking Furnace Steel Platform Plan at TOS EL 103360 | 1 | 2019-08-30 | IMP | OL1-2K32-2601- | CV | 2019-09-26 | 036909C-JVD-TRN-02724 | 036909C-JVD-TRN-02724 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02724 |  | 2019-09-28 | 3
036909C-1011-SP-1554-1158 | Instrument Datasheets for Temperature Gauge and Thermowell | A | 2019-09-23 | IFQ | OL1-2I20-1158 | PL | 2019-09-26 | 036909C-JVD-TRN-02723 | 036909C-JVD-TRN-02723 | IFR | 2019-10-11 |  | Transmitted | TPSK-LSPA1-T-PL-02723 |  | 2019-09-28 | 2
036909C-102B-CN-1732-0005 | Calculation Note For Foundation And Elevation Of 10-STR-2B02 And 10-T-2330 | A | 2019-09-18 | IFR | OL1-2K14-0051 | CV | 2019-09-25 | 036909C-JVD-TRN-02713 | 036909C-JVD-TRN-02713 | IFA | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-CV-02713 |  | 2019-09-28 | 1
036909C-102B-CN-1832-0005 | Calculation Note For Steel Structure 10-STR-2B02 | A | 2019-09-18 | IFR | OL1-2K15-0022 | CV | 2019-09-25 | 036909C-JVD-TRN-02711 | 036909C-JVD-TRN-02711 | IFA | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-CV-02711 |  | 2019-09-28 | 1
036909C-102B-DW-1842-0005-001 | Steel For Structure 10-STR-2B02 | A | 2019-09-16 | IFR | OL1-2K32-1480 | CV | 2019-09-25 | 036909C-JVD-TRN-02710 | 036909C-JVD-TRN-02710 | IFA | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-CV-02710 |  | 2019-09-27 | 1
036909C-102B-DW-1842-0005-002 | Steel For Structure 10-STR-2B02 | A | 2019-09-16 | IFR | OL1-2K32-1481 | CV | 2019-09-25 | 036909C-JVD-TRN-02710 | 036909C-JVD-TRN-02710 | IFA | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-CV-02710 |  | 2019-09-27 | 1
036909C-1012-MR-1554-1258 | Material Requisition for Temperature Gauge and Thermowell | A | 2019-09-23 | IFQ | OL1-2C17-032258 | PL | 2019-09-27 | 036909C-JVD-TRN-02732 | 036909C-JVD-TRN-02732 | IFR | 2019-10-12 |  | Transmitted | TPSK-LSPA1-T-PL-02732 |  | 2019-10-04 | 2
036909C-1053-SP-0910-5361 | Mechanical Equipment Datasheet - CTU Cooling Water Pumps | 1 | 2019-09-27 | IFP | OL1-2M03-5361 | ME | 2019-09-27 | 036909C-JVD-TRN-02726 | 036909C-JVD-TRN-02726 | IFR | 2019-10-11 |  | Transmitted | TPSK-LSPA1-T-ME-02726 |  | 2019-10-04 | 2
036909C-1053-SP-0910-5352 | Mechanical Equipment Datasheet - Olefins Cooling Water Pumps | 1 | 2019-09-27 | IFP | OL1-2M03-5352 | ME | 2019-09-27 | 036909C-JVD-TRN-02726 | 036909C-JVD-TRN-02726 | IFR | 2019-10-11 |  | Transmitted | TPSK-LSPA1-T-ME-02726 |  | 2019-10-04 | 2
036909C-102C-DW-1842-0007-002 | Steel For Structure 10-STR-2C07 - Elevations | A | 2019-09-26 | IFR | OL1-2K32-1441 | CV | 2019-09-27 | 036909C-JVD-TRN-02731 | 036909C-JVD-TRN-02731 | IFA | 2019-10-14 |  | Transmitted | TPSK-LSPA1-T-CV-02731 |  | 2019-10-04 | 1
036909C-102D-CN-1733-0051 | Calculation Note For Foundations And Elevation Of 10-C-2800 - 10-E-2800 | A | 2019-09-13 | IFR | OL1-2K13-0261 | CV | 2019-09-27 | 036909C-JVD-TRN-02729 | 036909C-JVD-TRN-02729 | IFA | 2019-10-14 |  | Transmitted | TPSK-LSPA1-T-CV-02729 |  | 2019-10-04 | 1
036909C-102D-CN-1731-0002 | Calculation Note For Precast Concrete Pipe-Rack 10-PRK-2D01 | A | 2019-09-12 | IFR | OL1-2K14-0010 | CV | 2019-09-16 | 036909C-JVD-TRN-02646 | 036909C-JVD-TRN-02646 | IFA | 2019-10-01 |  | Transmitted | TPSK-LSPA1-T-CV-02646 |  | 2019-09-17 | 1
036909C-102C-DW-1842-0007-001 | Steel For Structure 10-STR-2C07 - Plans | A | 2019-09-26 | IFR | OL1-2K32-1440 | CV | 2019-09-27 | 036909C-JVD-TRN-02731 | 036909C-JVD-TRN-02731 | IFA | 2019-10-14 |  | Transmitted | TPSK-LSPA1-T-CV-02731 |  | 2019-10-04 | 1
036909C-102C-CN-1732-0008 | Calculation Note For Foundation And Elevation Of 10-STR-2C07 | A | 2019-09-24 | IFR | OL1-2K14-0049 | CV | 2019-09-27 | 036909C-JVD-TRN-02727 | 036909C-JVD-TRN-02727 | IFA | 2019-10-14 |  | Transmitted | TPSK-LSPA1-T-CV-02727 |  | 2019-10-04 | 1
036909C-102C-CN-1832-0007 | Calculation Note For Steel Structure 10-STR-2C07 | A | 2019-09-24 | IFR | OL1-2K15-0020 | CV | 2019-09-27 | 036909C-JVD-TRN-02728 | 036909C-JVD-TRN-02728 | IFA | 2019-10-14 |  | Transmitted | TPSK-LSPA1-T-CV-02728 |  | 2019-10-04 | 1
036909C-102B-CN-1731-0001 | Calculation Notes For Foundation And Elevation Of 10-PRK-2B01 | A | 2019-09-24 | IFR | OL1-2K14-0015 | CV | 2019-09-27 | 036909C-JVD-TRN-02727 | 036909C-JVD-TRN-02727 | IFA | 2019-10-14 |  | Transmitted | TPSK-LSPA1-T-CV-02727 |  | 2019-10-04 | 1
036909C-102C-CN-1731-0004 | Calculation Notes For Precast Concrete Elevation Of Pipe Rack 10-PRK-2C02 | A | 2019-08-19 | IFR | OL1-2K14-0069 | CV | 2019-09-16 | 036909C-JVD-TRN-02646 | 036909C-JVD-TRN-02646 | IFA | 2019-10-01 |  | Transmitted | TPSK-LSPA1-T-CV-02646 |  | 2019-09-17 | 1
036909C-102B-CN-1731-0003 | Calculation Note For Foundation And Elevation Of 10-PRK-2B02 | A | 2019-09-11 | IFR | OL1-2K14-0067 | CV | 2019-09-16 | 036909C-JVD-TRN-02646 | 036909C-JVD-TRN-02646 | IFA | 2019-10-01 |  | Transmitted | TPSK-LSPA1-T-CV-02646 |  | 2019-09-17 | 1
036909C-1000-MR-0910-0003 | Material Requisition for Cooling Water Pumps | 1 | 2019-09-27 | IFP | OL1-2C13-440003 | PL | 2019-09-27 | 036909C-JVD-TRN-02725 | 036909C-JVD-TRN-02725 | IFR | 2019-10-11 |  | Transmitted | TPSK-LSPA1-T-PL-02725 |  | 2019-10-03 | 2
036909C-102B-DW-1742-0005-001 | Foundation And Elevation Of Steel Structure For 10-STR-2B02 & 10-T-2330 | A | 2019-09-18 | IFR | OL1-2K31-1740 | CV | 2019-09-25 | 036909C-JVD-TRN-02712 | 036909C-JVD-TRN-02712 | IFA | 2019-10-10 |  | Transmitted | TPSK-LSPA1-T-CV-02712 |  | 2019-09-28 | 1
036909C-105F-DW-1744-0001-001 | Concrete Basin 10-PIT-5633 -Plans (Formwork) | A | 2019-09-23 | IFR | OL1-2K31-1565 | CV | 2019-09-25 | 036909C-JVD-TRN-02689 | 036909C-JVD-TRN-02689 | IFR | 2019-10-08 |  | Transmitted | TPSK-LSPA1-T-CV-02689 |  | 2019-09-24 | 2
036909C-102D-DW-1842-0008-001 | Steel Structure For 10-STR-2D06 | A | 2019-09-23 | IFR | OL1-2K32-0001 | CV | 2019-09-24 | 036909C-JVD-TRN-02695 | 036909C-JVD-TRN-02695 | IFA | 2019-10-09 |  | Transmitted | TPSK-LSPA1-T-CV-02695 |  | 2019-09-25 | 1
036909C-102D-CN-1832-0008 | Calculation Note For Steel Structure Of 10-STR-2D06 | A | 2019-09-23 | IFR | OL1-2K15-0031 | CV | 2019-09-24 | 036909C-JVD-TRN-02696 | 036909C-JVD-TRN-02696 | IFA | 2019-10-09 |  | Transmitted | TPSK-LSPA1-T-CV-02696 |  | 2019-09-25 | 1
036909C-1012-TBT-1399-2103 | Technical Bid Tabulation for SP Item T-Type Filter | 0 | 2019-09-03 | IFI | OL1-2C24-504000 | PL | 2019-09-24 | 036909C-JVD-TRN-02703 | 036909C-JVD-TRN-02703 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-02703 |  | 2019-09-25 | 3
036909C-1012-DW-0131-2502 | USC 36M Recycle And 132U Cracking Furnace Steel Base Plate Details | 3 | 2019-09-19 | IMP | OL1-2K32-2502 | CV | 2019-09-23 | 036909C-JVD-TRN-02682 | 036909C-JVD-TRN-02682 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02682 |  | 2019-09-25 | 3
036909C-1012-DW-0131-2501 | USC 132U Cracking and 36M Recycle Furnaces Steel Foundation Plan and Loading Diagram | 2 | 2019-09-19 | IMP | OL1-2K32-2501 | CV | 2019-09-23 | 036909C-JVD-TRN-02682 | 036909C-JVD-TRN-02682 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02682 |  | 2019-09-25 | 3
036909C-1012-DW-0131-2580 | USC 132U Cracking Furnace Steel Breeching Plan and Elevations | 2 | 2019-09-19 | IMP | OL1-2K32-2580 | CV | 2019-09-23 | 036909C-JVD-TRN-02682 | 036909C-JVD-TRN-02682 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02682 |  | 2019-09-25 | 3
036909C-1011-MR-1545-2002 | Material Requisition for Pressure Relief Valves | 1 | 2019-09-18 | IFP | OL1-2C17-072002 | PL | 2019-09-23 | 036909C-JVD-TRN-02683 | 036909C-JVD-TRN-02683 | IFR | 2019-10-08 |  | Transmitted | TPSK-LSPA1-T-PL-02683 |  | 2019-09-25 | 2
036909C-1011-SP-1545-1002 | Instrument Datasheet for Pressure Relief Valve | 1 | 2019-09-18 | IFP | OL1-2I20-1002 | IE | 2019-09-23 | 036909C-JVD-TRN-02681 | 036909C-JVD-TRN-02681 | IFR | 2019-10-08 |  | Transmitted | TPSK-LSPA1-T-IE-02681 |  | 2019-09-25 | 2
036909C-1000-MS-1393-0016 | Job Specification For Deblocking And-Or Adjustment Of Piping And Equipment Special Supports | A | 2019-09-12 | IFR | OL1-2O71-0015 | PE | 2019-09-24 | 036909C-JVD-TRN-02702 | 036909C-JVD-TRN-02702 | IFR | 2019-10-09 |  | Transmitted | TPSK-LSPA1-T-PE-02702 |  | 2019-09-25 | 2
036909C-1000-MS-1393-0005 | Job Specification For Tightness Test Of Piping And Equipment | A | 2019-09-12 | IFR | OL1-2O71-0005 | PE | 2019-09-24 | 036909C-JVD-TRN-02702 | 036909C-JVD-TRN-02702 | IFR | 2019-10-09 |  | Transmitted | TPSK-LSPA1-T-PE-02702 |  | 2019-09-25 | 2
036909C-1000-MS-1393-0009 | Job Specification For Nitrogen Purging Of Piping And Equipment | A | 2019-09-12 | IFR | OL1-2O71-0009 | PE | 2019-09-24 | 036909C-JVD-TRN-02702 | 036909C-JVD-TRN-02702 | IFR | 2019-10-09 |  | Transmitted | TPSK-LSPA1-T-PE-02702 |  | 2019-09-25 | 2
036909C-1000-DW-1572-0024 | CCB Instrument-Telecom Cable Entry Details | A | 2019-09-03 | IFR | OL1-2I47-1005 | IE | 2019-09-24 | 036909C-JVD-TRN-02687 | 036909C-JVD-TRN-02687 | IFA | 2019-10-08 |  | Transmitted | TPSK-LSPA1-T-IE-02687 |  | 2019-09-25 | 1
036909C-1000-JSD-1950-0001 | Fire and Gas Detection | 0 | 2019-09-19 | IMP | OL1-2F92-0001 | FF | 2019-09-23 | 036909C-JVD-TRN-02684 | 036909C-JVD-TRN-02684 | IFR | 2019-10-08 |  | Transmitted | TPSK-LSPA1-T-FF-02684 |  | 2019-09-25 | 2
036909C-1000-DW-1442-0002-001 | Interface Point Layout | A | 2019-09-18 | IFR | OL1-2K26-0020 | CV | 2019-09-24 | 036909C-JVD-TRN-02688 | 036909C-JVD-TRN-02688 | IFA | 2019-10-09 |  | Transmitted | TPSK-LSPA1-T-CV-02688 |  | 2019-09-25 | 1
036909C-1000-ML-102 | Appraisal BD & TD Documents For Olefins Plant (Excluding EGF) | 0 | 2019-09-20 | IFI | OL1-2A19-0003 | CO | 2019-09-24 | 036909C-JVD-TRN-02692 | 036909C-JVD-TRN-02692 | IFI |  |  | Transmitted | TPSK-LPSA1-T-CO-02692 |  | 2019-09-24 | 3
036909C-105F-DW-1744-0001-005 | Concrete Basin 10-Pit-5633 - Sections (Reinforcement) | A | 2019-09-17 | IFR | OL1-2K31-1564 | CV | 2019-09-22 | 036909C-JVD-TRN-02675 | 036909C-JVD-TRN-02675 | IFR | 2019-10-06 |  | Transmitted | TPSK-LSPA1-T-CV-02675 |  | 2019-09-23 | 2
036909C-105F-DW-1744-0001-003 | Concrete Basin 10-Pit-5633 - Plans And Details (Reinforcement) | A | 2019-09-17 | IFR | OL1-2K31-1562 | CV | 2019-09-22 | 036909C-JVD-TRN-02675 | 036909C-JVD-TRN-02675 | IFR | 2019-10-06 |  | Transmitted | TPSK-LSPA1-T-CV-02675 |  | 2019-09-23 | 2
036909C-105F-DW-1744-0001-004 | Concrete Basin 10-Pit-5633 - Sections (Reinforcement) | A | 2019-09-17 | IFR | OL1-2K31-1563 | CV | 2019-09-22 | 036909C-JVD-TRN-02675 | 036909C-JVD-TRN-02675 | IFR | 2019-10-06 |  | Transmitted | TPSK-LSPA1-T-CV-02675 |  | 2019-09-23 | 2
036909C-103A-DW-1844-0002-002 | Steel Structure For Concrete Basin 10-Pit-3190 - Connection Details | A | 2019-09-17 | IFR | OL1-2K32-1141 | CV | 2019-09-22 | 036909C-JVD-TRN-02676 | 036909C-JVD-TRN-02676 | IFR | 2019-10-06 |  | Transmitted | TPSK-LSPA1-T-CV-02676 |  | 2019-09-23 | 2
036909C-105F-DW-1744-0001-002 | Concrete Basin 10-Pit-5633 - Sections (Formwork) | A | 2019-09-12 | IFR | OL1-2K31-1561 | CV | 2019-09-22 | 036909C-JVD-TRN-02675 | 036909C-JVD-TRN-02675 | IFR | 2019-10-06 |  | Transmitted | TPSK-LSPA1-T-CV-02675 |  | 2019-09-23 | 2
036909C-103A-DW-1744-0001-002 | Concrete Basin 10-Pit-3190 - Sections - Formwork | A | 2019-09-17 | IFR | OL1-2K31-1321 | CV | 2019-09-22 | 036909C-JVD-TRN-02675 | 036909C-JVD-TRN-02675 | IFR | 2019-10-06 |  | Transmitted | TPSK-LSPA1-T-CV-02675 |  | 2019-09-23 | 2
036909C-103A-DW-1744-0001-003 | Concrete Basin 10-Pit-3190 - Plan & Sections - Reinforcement | A | 2019-09-17 | IFR | OL1-2K31-1322 | CV | 2019-09-22 | 036909C-JVD-TRN-02675 | 036909C-JVD-TRN-02675 | IFR | 2019-10-06 |  | Transmitted | TPSK-LSPA1-T-CV-02675 |  | 2019-09-23 | 2
036909C-103A-DW-1844-0002-001 | Steel Structural For Concrete Basin 10-Pit-3190 - Plan And Sections | A | 2019-09-17 | IFR | OL1-2K32-1140 | CV | 2019-09-22 | 036909C-JVD-TRN-02676 | 036909C-JVD-TRN-02676 | IFR | 2019-10-06 |  | Transmitted | TPSK-LSPA1-T-CV-02676 |  | 2019-09-23 | 2
036909C-103A-DW-1744-0001-001 | Concrete Basin 10-Pit-3190 - Plan & Details - Formwork | A | 2019-09-17 | IFR | OL1-2K31-1320 | CV | 2019-09-22 | 036909C-JVD-TRN-02675 | 036909C-JVD-TRN-02675 | IFR | 2019-10-06 |  | Transmitted | TPSK-LSPA1-T-CV-02675 |  | 2019-09-23 | 2
036909C-103A-DW-1745-0001-001 | Retaining Wall For 10-Tk-3900 - Plan & Sections - Formwork | A | 2019-09-13 | IFR | OL1-2K31-0333 | CV | 2019-09-22 | 036909C-JVD-TRN-02675 | 036909C-JVD-TRN-02675 | IFR | 2019-10-06 |  | Transmitted | TPSK-LSPA1-T-CV-02675 |  | 2019-09-23 | 2
036909C-102D-DW-1741-0002-005 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Elevations | A | 2019-09-16 | IFR | OL1-2K31-1224 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-006 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Elevations | A | 2019-09-16 | IFR | OL1-2K31-1225 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-002 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Plans | A | 2019-09-16 | IFR | OL1-2K31-1221 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-001 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Isometric 3D View | A | 2019-09-16 | IFR | OL1-2K31-1220 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-004 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Elevations | A | 2019-09-16 | IFR | OL1-2K31-1223 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-003 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Plans | A | 2019-09-16 | IFR | OL1-2K31-1222 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-016 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Beams | A | 2019-09-16 | IFR | OL1-2K31-1235 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-014 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Beams | A | 2019-09-16 | IFR | OL1-2K31-1233 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-015 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Beams | A | 2019-09-16 | IFR | OL1-2K31-1234 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-018 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Bracings | A | 2019-09-16 | IFR | OL1-2K31-1237 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-017 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Bracings | A | 2019-09-16 | IFR | OL1-2K31-1236 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-019 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Bracings | A | 2019-09-16 | IFR | OL1-2K31-1238 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-009 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Columns | A | 2019-09-16 | IFR | OL1-2K31-1228 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-007 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Columns | A | 2019-09-16 | IFR | OL1-2K31-1226 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-008 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Columns | A | 2019-09-16 | IFR | OL1-2K31-1227 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-012 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Columns | A | 2019-09-16 | IFR | OL1-2K31-1231 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-013 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Columns | A | 2019-09-16 | IFR | OL1-2K31-1232 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-010 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Columns | A | 2019-09-16 | IFR | OL1-2K31-1229 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-102D-DW-1741-0002-011 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Columns | A | 2019-09-16 | IFR | OL1-2K31-1230 | CV | 2019-09-20 | 036909C-JVD-TRN-02672 | 036909C-JVD-TRN-02672 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02672 |  | 2019-09-24 | 1
036909C-105T-DW-1745-0001-002 | Retaining Wall For 10-Tk-5900 - Sections - Reinforcement | A | 2019-09-13 | IFR | OL1-2K31-0329 | CV | 2019-09-18 | 036909C-JVD-TRN-02660 | 036909C-JVD-TRN-02660 | IFR | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02660 |  | 2019-09-19 | 2
036909C-105T-DW-1745-0001-001 | Retaining Wall For 10-Tk-5900 - Plan And Sections - Formwork | A | 2019-09-13 | IFR | OL1-2K31-0328 | CV | 2019-09-18 | 036909C-JVD-TRN-02660 | 036909C-JVD-TRN-02660 | IFR | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02660 |  | 2019-09-19 | 2
036909C-105U-CN-1731-0002 | Calculation Note For Precast Concrete Elevation Of Pipe Rack 10-Prk-5U01 | A | 2019-09-12 | IFR | OL1-2K14-0008 | CV | 2019-09-18 | 036909C-JVD-TRN-02660 | 036909C-JVD-TRN-02660 | IFR | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02660 |  | 2019-09-19 | 2
036909C-105T-DW-1745-0002-001 | Retaining Wall For 10-Tk-5950 - Plan And Section - Formwork | A | 2019-09-13 | IFR | OL1-2K31-0330 | CV | 2019-09-18 | 036909C-JVD-TRN-02660 | 036909C-JVD-TRN-02660 | IFR | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02660 |  | 2019-09-19 | 2
036909C-105U-CN-1731-0001 | Calculation Note For Foundation & Elevation Of Pipe Rack 10-Prk-5U01 | A | 2019-09-12 | IFR | OL1-2K14-0007 | CV | 2019-09-18 | 036909C-JVD-TRN-02660 | 036909C-JVD-TRN-02660 | IFR | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02660 |  | 2019-09-19 | 2
036909C-105T-DW-1743-0007 | Foundation for 10-PK-5355 | A | 2019-09-11 | Issued for Review | OL1-2K31-0259 | CV | 2019-09-18 | 036909C-JVD-TRN-02660 | 036909C-JVD-TRN-02660 | IFR | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02660 |  | 2019-09-19 | 2
036909C-105T-DW-1744-0001-002 | Basin For Cooling Tower 10-Pit-5350 - Plan (Formwork) | A | 2019-09-12 | IFR | OL1-2K31-2501 | CV | 2019-09-18 | 036909C-JVD-TRN-02660 | 036909C-JVD-TRN-02660 | IFR | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02660 |  | 2019-09-19 | 2
036909C-105T-DW-1744-0001-005 | Basin For Cooling Tower 10-Pit-5350 - Plan (Formwork) | A | 2019-09-12 | IFR | OL1-2K31-2504 | CV | 2019-09-18 | 036909C-JVD-TRN-02660 | 036909C-JVD-TRN-02660 | IFR | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02660 |  | 2019-09-19 | 2
036909C-105T-DW-1744-0001-003 | Basin For Cooling Tower 10-Pit-5350 - Plan (Formwork) | A | 2019-09-12 | Issued for Review | OL1-2K31-2502 | CV | 2019-09-18 | 036909C-JVD-TRN-02660 | 036909C-JVD-TRN-02660 | IFR | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02660 |  | 2019-09-19 | 2
036909C-105T-DW-1744-0001-004 | Basin For Cooling Tower 10-Pit-5350 - Plan (Formwork) | A | 2019-09-12 | IFR | OL1-2K31-2503 | CV | 2019-09-18 | 036909C-JVD-TRN-02660 | 036909C-JVD-TRN-02660 | IFR | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02660 |  | 2019-09-19 | 2
036909C-103A-DW-1745-0001-002 | Retaining Wall For 10-Tk-3900 - Sections - Reinforcement | A | 2019-09-13 | IFR | OL1-2K31-0334 | CV | 2019-09-18 | 036909C-JVD-TRN-02660 | 036909C-JVD-TRN-02660 | IFR | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02660 |  | 2019-09-19 | 2
036909C-102D-DW-1841-0001-010 | Steel For Pipe Rack 10-PRK-2D01 - Details | A | 2019-09-13 | IFR | OL1-2K32-1109 | CV | 2019-09-20 | 036909C-JVD-TRN-02671 | 036909C-JVD-TRN-02671 | IFA | 2019-10-07 |  | Transmitted | TPSK-LSPA1-T-CV-02671 |  | 2019-09-22 | 1
036909C-102D-DW-1841-0001-004 | Steel For Pipe Rack 10-PRK-2D01 - Plans | A | 2019-09-13 | IFR | OL1-2K32-1103 | CV | 2019-09-20 | 036909C-JVD-TRN-02671 | 036909C-JVD-TRN-02671 | IFA | 2019-10-07 |  | Transmitted | TPSK-LSPA1-T-CV-02671 |  | 2019-09-22 | 1
036909C-102D-DW-1841-0001-005 | Steel For Pipe Rack 10-PRK-2D01 - Plans | A | 2019-09-13 | IFR | OL1-2K32-1104 | CV | 2019-09-20 | 036909C-JVD-TRN-02671 | 036909C-JVD-TRN-02671 | IFA | 2019-10-07 |  | Transmitted | TPSK-LSPA1-T-CV-02671 |  | 2019-09-22 | 1
036909C-102D-DW-1841-0001-002 | Steel For Pipe Rack 10-PRK-2D01 - Plans | A | 2019-09-13 | IFR | OL1-2K32-1101 | CV | 2019-09-20 | 036909C-JVD-TRN-02671 | 036909C-JVD-TRN-02671 | IFA | 2019-10-07 |  | Transmitted | TPSK-LSPA1-T-CV-02671 |  | 2019-09-22 | 1
036909C-102D-DW-1841-0001-003 | Steel For Pipe Rack 10-PRK-2D01 - Plans | A | 2019-09-13 | IFR | OL1-2K32-1102 | CV | 2019-09-20 | 036909C-JVD-TRN-02671 | 036909C-JVD-TRN-02671 | IFA | 2019-10-07 |  | Transmitted | TPSK-LSPA1-T-CV-02671 |  | 2019-09-22 | 1
036909C-102D-DW-1841-0001-008 | Steel For Pipe Rack 10-PRK-2D01 - Transv Elevations Al 2D-10 To Al 2D-17 | A | 2019-09-13 | IFR | OL1-2K32-1107 | CV | 2019-09-20 | 036909C-JVD-TRN-02671 | 036909C-JVD-TRN-02671 | IFA | 2019-10-07 |  | Transmitted | TPSK-LSPA1-T-CV-02671 |  | 2019-09-22 | 1
036909C-102D-DW-1841-0001-009 | Steel For Pipe Rack 10-PRK-2D01 - Transv Elevations Al 2D-18 To Al 2D-23 | A | 2019-09-13 | IFR | OL1-2K32-1108 | CV | 2019-09-20 | 036909C-JVD-TRN-02671 | 036909C-JVD-TRN-02671 | IFA | 2019-10-07 |  | Transmitted | TPSK-LSPA1-T-CV-02671 |  | 2019-09-22 | 1
036909C-102D-DW-1841-0001-006 | Steel For Pipe Rack 10-PRK-2D01 - Longitudinal Elevations | A | 2019-09-13 | IFR | OL1-2K32-1105 | CV | 2019-09-20 | 036909C-JVD-TRN-02671 | 036909C-JVD-TRN-02671 | IFA | 2019-10-07 |  | Transmitted | TPSK-LSPA1-T-CV-02671 |  | 2019-09-22 | 1
036909C-102D-DW-1841-0001-007 | Steel For Pipe Rack 10-PRK-2D01 - Transv. Elevations Al.2D-02 To Al.2D-09 | A | 2019-09-13 | IFR | OL1-2K32-1106 | CV | 2019-09-20 | 036909C-JVD-TRN-02671 | 036909C-JVD-TRN-02671 | IFA | 2019-10-07 |  | Transmitted | TPSK-LSPA1-T-CV-02671 |  | 2019-09-22 | 1
036909C-102D-DW-1841-0001-001 | Steel For Pipe Rack 10-PRK-2D01- 3D View | A | 2019-09-13 | IFR | OL1-2K32-1100 | CV | 2019-09-20 | 036909C-JVD-TRN-02671 | 036909C-JVD-TRN-02671 | IFA | 2019-10-07 |  | Transmitted | TPSK-LSPA1-T-CV-02671 |  | 2019-09-22 | 1
036909C-102C-DW-1842-0001-002 | Steel For Structure 10-STR-2C01 - Elevations | A | 2019-09-16 | IFR | OL1-2K32-2141 | CV | 2019-09-17 | 036909C-JVD-TRN-02656 | 036909C-JVD-TRN-02656 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02656 |  | 2019-09-18 | 1
036909C-102C-DW-1842-0003-002 | Steel For Structure 10-STR-2C03 - Elevations | A | 2019-09-12 | IFR | OL1-2K32-1624 | CV | 2019-09-17 | 036909C-JVD-TRN-02656 | 036909C-JVD-TRN-02656 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02656 |  | 2019-09-18 | 1
036909C-102C-DW-1842-0001-001 | Steel For Structure 10-STR-2C01 - Plans | A | 2019-09-16 | IFR | OL1-2K32-2140 | CV | 2019-09-17 | 036909C-JVD-TRN-02656 | 036909C-JVD-TRN-02656 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02656 |  | 2019-09-18 | 1
036909C-102C-DW-1742-0001-003 | Foundation And Elevation Of Concrete Structure 10-STR-2C01 | A | 2019-09-16 | IFR | OL1-2K31-1822 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-DW-1841-0002-005 | Steel For Pipe Rack 10-PRK-2B02 - Elevations | A | 2019-09-11 | IFR | OL1-2K32-1184 | CV | 2019-09-17 | 036909C-JVD-TRN-02656 | 036909C-JVD-TRN-02656 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02656 |  | 2019-09-18 | 1
036909C-102C-CN-1732-0001 | Calculation Note For Foundation And Elevation Of 10-STR-2C01 | A | 2019-09-16 | IFR | OL1-2K14-0055 | CV | 2019-09-18 | 036909C-JVD-TRN-02665 | 036909C-JVD-TRN-02665 | IFA | 2019-10-03 |  | Transmitted | TPSK-LSPA1-T-CV-02665 |  | 2019-09-19 | 1
036909C-102C-DW-1742-0001-002 | Foundation And Elevation Of Concrete Structure 10-STR-2C01 | A | 2019-09-16 | IFR | OL1-2K31-1821 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-DW-1841-0004-006 | Steel For Pipe Rack 10-PRK-2B02 - Details | A | 2019-09-11 | IFR | OL1-2K32-1185 | CV | 2019-09-17 | 036909C-JVD-TRN-02656 | 036909C-JVD-TRN-02656 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02656 |  | 2019-09-18 | 1
036909C-102B-DW-1841-0002-004 | Steel For Pipe Rack 10-PRK-2B02 - Elevations | A | 2019-09-11 | IFR | OL1-2K32-1183 | CV | 2019-09-17 | 036909C-JVD-TRN-02656 | 036909C-JVD-TRN-02656 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02656 |  | 2019-09-18 | 1
036909C-102B-DW-1741-0004-010 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Columns | A | 2019-09-11 | IFR | OL1-2K31-1389 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-DW-1841-0002-001 | Steel For Pipe Rack 10-PRK-2B02 - 3D View | A | 2019-09-11 | IFR | OL1-2K32-1180 | CV | 2019-09-17 | 036909C-JVD-TRN-02656 | 036909C-JVD-TRN-02656 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02656 |  | 2019-09-18 | 1
036909C-102B-DW-1841-0002-002 | Steel For Pipe Rack 10-PRK-2B02 - Plans | A | 2019-09-11 | IFR | OL1-2K32-1181 | CV | 2019-09-17 | 036909C-JVD-TRN-02656 | 036909C-JVD-TRN-02656 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02656 |  | 2019-09-18 | 1
036909C-102B-DW-1741-0004-014 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Steel Bracings Details | A | 2019-09-11 | IFR | OL1-2K31-1393 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-DW-1741-0004-015 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Steel Bracings Details | A | 2019-09-11 | IFR | OL1-2K31-1394 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-DW-1741-0004-012 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Beams | A | 2019-09-11 | IFR | OL1-2K31-1391 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-DW-1741-0004-011 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Beams | A | 2019-09-11 | IFR | OL1-2K31-1390 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-DW-1841-0002-003 | Steel For Pipe Rack 10-PRK-2B02 - Plans | A | 2019-09-11 | IFR | OL1-2K32-1182 | CV | 2019-09-17 | 036909C-JVD-TRN-02656 | 036909C-JVD-TRN-02656 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02656 |  | 2019-09-18 | 1
036909C-102B-DW-1741-0004-013 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Beams | A | 2019-09-11 | IFR | OL1-2K31-1392 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-DW-1741-0004-007 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Columns | A | 2019-09-11 | IFR | OL1-2K31-1386 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-DW-1741-0004-008 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Columns | A | 2019-09-11 | IFR | OL1-2K31-1387 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-DW-1741-0004-009 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Columns | A | 2019-09-11 | IFR | OL1-2K31-1388 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-DW-1741-0004-004 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Elevations | A | 2019-09-11 | IFR | OL1-2K31-1383 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-DW-1741-0004-006 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Columns | A | 2019-09-11 | IFR | OL1-2K31-1385 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-DW-1741-0004-005 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Elevations | A | 2019-09-11 | IFR | OL1-2K31-1384 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-DW-1741-0004-001 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - 3D View | A | 2019-09-11 | IFR | OL1-2K31-1380 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-CN-1731-0004 | Calculation Note For Precast Concrete Elevation Of Pipe Rack 10-PRK-2B02 | A | 2019-09-11 | IFR | OL1-2K14-0068 | CV | 2019-09-18 | 036909C-JVD-TRN-02665 | 036909C-JVD-TRN-02665 | IFA | 2019-10-03 |  | Transmitted | TPSK-LSPA1-T-CV-02665 |  | 2019-09-19 | 1
036909C-102B-CN-1831-0002 | Calculation Note For Steel Pipe Rack 10-PRK-2B02 | A | 2019-09-11 | IFR | OL1-2K14-0056 | CV | 2019-09-18 | 036909C-JVD-TRN-02665 | 036909C-JVD-TRN-02665 | IFA | 2019-10-03 |  | Transmitted | TPSK-LSPA1-T-CV-02665 |  | 2019-09-19 | 1
036909C-102B-DW-1741-0004-003 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Plans | A | 2019-09-11 | IFR | OL1-2K31-1382 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102B-DW-1741-0004-002 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Plans | A | 2019-09-11 | IFR | OL1-2K31-1381 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-1011-DW-0131-1521 | USC 36M Recycle Furnace Steel Convection Side Wall at COL Line C1 | 1 | 2019-09-17 | IMP | OL1-2K32-1521 | CV | 2019-09-18 | 036909C-JVD-TRN-02667 | 036909C-JVD-TRN-02668, 036909C-JVD-TRN-02667 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02667 |  | 2019-09-19 | 3
036909C-1011-DW-0131-1541 | USC 36M Recycle Furnace Steel Convection Sections and Details | 1 | 2019-09-17 | IMP | OL1-2K32-1541 | CV | 2019-09-18 | 036909C-JVD-TRN-02667 | 036909C-JVD-TRN-02668, 036909C-JVD-TRN-02667 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02667 |  | 2019-09-19 | 3
036909C-1012-DW-0131-2514 | USC 132U Cracking Furnace Steel Radiant End Wall At COL Line 1 And 5 | 2 | 2019-09-17 | IMP | OL1-2K32-2514 | CV | 2019-09-18 | 036909C-JVD-TRN-02667 | 036909C-JVD-TRN-02668, 036909C-JVD-TRN-02667 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02667 |  | 2019-09-19 | 3
036909C-1011-DW-0131-1514 | USC Recycle Furnace Steel Radiant End Wall at Col 1 and 6_8 | 2 | 2019-09-17 | IMP | OL1-2K32-1514 | CV | 2019-09-18 | 036909C-JVD-TRN-02667 | 036909C-JVD-TRN-02668, 036909C-JVD-TRN-02667 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02667 |  | 2019-09-19 | 3
036909C-1011-DW-0131-1520 | USC 36M Recycle Furnace Steel Convection Side Wall at Col Line B1 | 1 | 2019-09-17 | IMP | OL1-2K32-1520 | CV | 2019-09-18 | 036909C-JVD-TRN-02667 | 036909C-JVD-TRN-02668, 036909C-JVD-TRN-02667 | IFI |  |  | Transmitted | TPSK-LSPA1-T-CV-02667 |  | 2019-09-19 | 3
036909C-1000-MS-1700-0001 | Technical Specification for Civil Works | 0 | 2019-09-09 | IFP | OL1-2R02-0102 | CV | 2019-09-18 | 036909C-JVD-TRN-02666 | 036909C-JVD-TRN-02666 | IFR | 2019-10-03 |  | Transmitted | TPSK-LSPA1-T-CV-02666 |  | 2019-09-20 | 2
036909C-1000-DW-1430-0003-001 | Olefins Plant - Preliminary Field Pile Trial - PHC Piles - Layout And Programme | A | 2019-09-09 | IFR | OL1-2K31-0450 | CV | 2019-09-20 | 036909C-JVD-TRN-02670 | 036909C-JVD-TRN-02670 | IFA | 2019-10-06 |  | Transmitted | TPSK-LSPA1-T-CV-02670 |  | 2019-09-20 | 1
036909C-1000-DL-4046-0001 | Deviation List For Chemical Dosing System | B | 2019-09-17 | IFR | OL1-2C40-707000 | PL | 2019-09-18 | 036909C-JVD-TRN-02661 | 036909C-JVD-TRN-02661 | IFR | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-PL-02661 |  | 2019-09-19 | 2
036909C-102E-CN-1832-0002 | Calculation Note For Steel Structure Of 10-STR-2E01 | A | 2019-09-11 | IFR | OL1-2K15-0013 | CV | 2019-09-16 | 036909C-JVD-TRN-02645 | 036909C-JVD-TRN-02645 | IFA | 2019-10-01 |  | Transmitted | TPSK-LSPA1-T-CV-02645 |  | 2019-09-17 | 1
036909C-102D-CN-1831-0001 | Calculation Note For Steel Pipe-Rack 10-PRK-2D01 | A | 2019-09-12 | IFR | OL1-2K15-0005 | CV | 2019-09-16 | 036909C-JVD-TRN-02645 | 036909C-JVD-TRN-02645 | IFA | 2019-10-01 |  | Transmitted | TPSK-LSPA1-T-CV-02645 |  | 2019-09-17 | 1
036909C-102A-CN-1831-0001 | Calculation Note For Steel Pipe-Rack 10-PRK-2A01 | A | 2019-09-12 | IFR | OL1-2K15-0007 | CV | 2019-09-16 | 036909C-JVD-TRN-02645 | 036909C-JVD-TRN-02645 | IFA | 2019-10-01 |  | Transmitted | TPSK-LSPA1-T-CV-02645 |  | 2019-09-17 | 1
036909C-102C-CN-1832-0003 | Calculation Note For Steel Structure 10-STR-2C03 | A | 2019-09-11 | IFR | OL1-2K15-0028 | CV | 2019-09-16 | 036909C-JVD-TRN-02645 | 036909C-JVD-TRN-02645 | IFA | 2019-10-01 |  | Transmitted | TPSK-LSPA1-T-CV-02645 |  | 2019-09-17 | 1
036909C-102E-DW-1742-0001-001 | Foundation And Elevation Of Steel Structure For 10-STR-2E01 and 10-T-2440 | A | 2019-09-11 | IFR | OL1-2K31-1560 | CV | 2019-09-16 | 036909C-JVD-TRN-02648 | 036909C-JVD-TRN-02648 | IFA | 2019-10-01 |  | Transmitted | TPSK-LSPA1-T-CV-02648 |  | 2019-09-17 | 1
036909C-102E-DW-1842-0002-001 | Steel Structure For 10-STR-2E01 | A | 2019-09-12 | IFR | OL1-2K32-1300 | CV | 2019-09-16 | 036909C-JVD-TRN-02647 | 036909C-JVD-TRN-02647 | IFA | 2019-10-01 |  | Transmitted | TPSK-LSPA1-T-CV-02647 |  | 2019-09-17 | 1
036909C-102E-DW-1842-0002-002 | Steel Structure For 10-STR-2E01 | A | 2019-09-12 | IFR | OL1-2K32-1301 | CV | 2019-09-16 | 036909C-JVD-TRN-02647 | 036909C-JVD-TRN-02647 | IFA | 2019-10-01 |  | Transmitted | TPSK-LSPA1-T-CV-02647 |  | 2019-09-17 | 1
036909C-102E-CN-1732-0002 | Calculation Note For Foundation And Elevation Of 10-STR-2E01 | A | 2019-09-13 | IFR | OL1-2K14-0038 | CV | 2019-09-16 | 036909C-JVD-TRN-02650 | 036909C-JVD-TRN-02650 | IFA | 2019-10-01 |  | Transmitted | TPSK-LSPA1-T-CV-02650 |  | 2019-09-17 | 1
036909C-102C-DW-1842-0003-001 | Steel For Structure 10-STR-2C03 | A | 2019-09-12 | IFR | OL1-2K32-1600 | CV | 2019-09-16 | 036909C-JVD-TRN-02647 | 036909C-JVD-TRN-02647 | IFA | 2019-10-01 |  | Transmitted | TPSK-LSPA1-T-CV-02647 |  | 2019-09-17 | 1
036909C-102C-DW-1742-0001-001 | Foundation And Elevation Of Concrete Structure 10-STR-2C01 | A | 2019-09-16 | IFR | OL1-2K31-1820 | CV | 2019-09-17 | 036909C-JVD-TRN-02655 | 036909C-JVD-TRN-02655 | IFA | 2019-10-02 |  | Transmitted | TPSK-LSPA1-T-CV-02655 |  | 2019-09-18 | 1
036909C-102C-CN-1732-0003 | Calculation Note For Foundation And Elevation Of 10-STR-2C03 | A | 2019-09-13 | IFR | OL1-2K14-0057 | CV | 2019-09-16 | 036909C-JVD-TRN-02650 | 036909C-JVD-TRN-02650 | IFA | 2019-10-01 |  | Transmitted | TPSK-LSPA1-T-CV-02650 |  | 2019-09-17 | 1
036909C-102B-DW-1741-0003-001 | Foundation And Elevation Of Pipe Rack 10-PRK-2B02 - Formwork And Reinforcement | A | 2019-09-11 | IFR | OL1-2K31-1340 | CV | 2019-09-16 | 036909C-JVD-TRN-02648 | 036909C-JVD-TRN-02648 | IFA | 2019-10-01 |  | Transmitted | TPSK-LSPA1-T-CV-02648 |  | 2019-09-17 | 1
036909C-1000-DW-1430-0003-002 | Spun Piles For Preliminary Test | A | 2019-09-09 | IFR | OL1-2K31-0391 | CV | 2019-09-19 | 036909C-JVD-TRN-02636 | 036909C-JVD-TRN-02636 | IFA | 2019-09-27 |  | Transmitted | TPSK-LSPA1-T-CV-02636 |  | 2019-09-13 | 1
036909C-105W-DW-1572-0015 | Instrument Main Cable Routing Waste Water Treatment | B | 2019-10-10 | IBD | OL1-2I34-0015 | IE | 2019-10-14 | 036909C-JVD-TRN-02829 | 036909C-JVD-TRN-02829 | IFA | 2019-10-29 |  | Transmitted | TPSK-LSPA1-T-IE-02829 |  | 2019-10-17 | 1
036909C-102B-DW-1572-0008 | Instrument Main Cable Tray Routing C3 Hydrogenation | B | 2019-10-10 | IBD | OL1-2I34-0008 | IE | 2019-10-11 | 036909C-JVD-TRN-02818 | 036909C-JVD-TRN-02818 | IFA | 2019-10-28 |  | Transmitted | TPSK-LSPA1-T-IE-02818 |  | 2019-10-15 | 1
036909C-1000-MR-1130-0001 | Material Requisition For Residue Gas Expander-Recompressor | 2 | 2019-10-01 | IFP | OL1-2C13-421000 | PL | 2019-10-02 | 036909C-JVD-TRN-02754 | 036909C-JVD-TRN-02754 | IFA | 2019-10-17 |  | Transmitted | TPSK-LSPA1-T-PL-02754 |  | 2019-10-09 | 1