## CPY_Format
|  |  |  | Master Document Index (MDI) |  | ABBREVIATION | [10 empty] | DOCUMENT NO. |  | REV.
[6 empty] | **Revision Purpose of Issued Document |  |  |  | *Owner Feedback (Comment) |  |  |  |  | ***Classification
[6 empty] | IFR = Issue For Review |  | IFF = Issue For Final |  | A1 = App. w/o comments |  |  | R1 = No comments |  | Class 1 = For Approval |  | LSP-2W91-0001 |  | 10
[6 empty] | IFA = Issue For Approval |  | ASB = Issue For As-Built |  | A2 = App. with comments, re-submit not required |  |  | R2 = Comments as noted |  | Class 2 = For Review
[6 empty] | IFC = Issue For Construction |  | AFC = Approved for Construction |  | A3 = App. with comments, re-submit for review |  |  |  |  | Class 3 = For Information
Owner: |  | Long Son Pterochemicals C0., Ltd. |  | Plant Name: PACKAGE A1: OLEFINS PLANT |  | IFI = Issue For Information |  | IMP = Issue for Implementation |  | A4 = Not App., re-submit for approval | [6 empty] | Issue Date | 2019-09-02
|  |  |  | Att. To OL1-2W91-0001 036909C-1000-NM-107 |  | IFP = Issue For Planning |  | / Execution
Document Code : | [5 empty] | IFD = Issue For Design |  | CAN = Issue for Cancellation |  | Period for Company's comment |  |  |  |  | __________ | Working Days
Item | Org. | Document No. | Document Name |  | Classification
Category Code: =Index!B30 =Index!C30
Category Code: A03 Technology transfer dossiers
Category Code: A04 Confidentiality Agreements
Category Code: A05 Laws and Regulations
Category Code: A06 Local content
Category Code: A09 Arbitration and Dispute Resolution
Category Code: A10 Guarantee of Labour Payment Affidavit
Category Code: A11 Termination or Amendment of Contracts
Category Code: A12 Liquidation Contract
Category Code: A13 Claim & Complaint from contractors
Category Code: A14 Claim & Complaint to contractors
Category Code: A15 Variation Change Notice
Category Code: A16 ITC - Instruction to Contractor
Category Code: A17 Contract Variation Form
Category Code: A18 License Agreement
Category Code: A19 Supplement Dossier
Category Code: A20 Certificates
Category Code: A21 Approval Letter
Category Code: A30 Certificate of Work Completion
Category Code: A41 Power of Attorney
Category Code: A42 Power of Attorney
Category Code: A43 Power of Attorney
Category Code: A44 Power of Attorney
Category Code: A51 Contract Document of Consultancy Service
Category Code: A52 Contract Document of EPC Contractor
Category Code: A53 Contract Document of Vendor/Supplier
Category Code: A61 Records of Management of Change (before final investment decision)
Category Code: A62 Records of Management of Change (after final investment decision)
Category Code: A71 Appraisal Report for Consultancy Service
Category Code: A72 Appraisal Report for EPC Contractor Work
Category Code: A73 Appraisal Report for Vendor/Supplier
Category Code: A91 Index/List
Category Code: A92 Procedures & Standards
Category Code: A93 Policy , Guidelines & Memo
Category Code: A94 Forms & Templates
Category Code: A95 Progress/Status Reports
Category Code: B01 Project Schedule
Category Code: B71 Appraisal Report for Consultancy Service
Category Code: B72 Appraisal Report for EPC Contractor Work
Category Code: B73 Appraisal Report for Vendor/Supplier
Category Code: B91 Index/List
Category Code: B92 Procedures & Standards
| PC | OL1-2B92-0006 | Plant And Section Codes |  | Class 2 | Purpose** | IMP | IMP
[6 empty] | Rev. | 0 | 1
Issue Plan
[6 empty] | Revised Plan | 2018-09-25 | 2019-07-09
[6 empty] | Issue Actual | 2018-09-25 | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00076 | TPSK-LSPA1-T-PC-02075
[6 empty] | Return Date |  | 2019-07-15
[6 empty] | Owner Cmmt* |  | R1
Category Code: B93 Policy , Guidelines & Memo
Category Code: B94 Forms & Templates
Category Code: B95 Progress/Status Reports
Category Code: C01 Subvendor List
| PL | OL1-2C01-0001 | Subvendor List For Compressor And Turboexpander - Abstract From Approved Vendor List |  |  | Purpose** | IMP | IMP
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-05 | 2018-10-05
[6 empty] | Issue Actual | 2018-10-05 | 2018-10-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00134 | TPSK-LSPA1-T-PL-00134
Return Date
Owner Cmmt*
| PL | OL1-2C01-0002 | Subvendor list for PSA/Deareator/Filter Package |  |  | Purpose** | IMP | IMP
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2018-11-19 | 2018-11-19
[6 empty] | Issue Actual | 2018-11-19 | 2018-11-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00333 | TPSK-LSPA1-T-PL-00333
Return Date
Owner Cmmt*
| PL | OL1-2C01-0003 | Subvendor list for Pumps |  |  | Purpose** | IMP | IMP
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2018-11-19 | 2018-11-19
[6 empty] | Issue Actual | 2018-11-19 | 2018-11-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00333 | TPSK-LSPA1-T-PL-00333
Return Date
Owner Cmmt*
Category Code: C10 Request for Quotation (RFQ) for Civil work (Engineering and Procurement) | [5 empty] | Purpose**
Category Code: C11 Request for Quotation (RFQ) for Building work (Engineering and Procurement) | [5 empty] | Rev.
Category Code: C12 Request for Quotation (RFQ) for Steel Structure work (Engineering and Procurement) | [5 empty] | Issue Plan
| PL | OL1-2C12-000001 | Material Requisition For Steel Structures |  | Class 2 | Purpose** | IFQ | IFQ | IFP
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-05-06 |  | 2019-09-13
[6 empty] | Revised Plan |  |  | 2019-09-13
[6 empty] | Issue Actual | 2019-03-08 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-1010 | TPSK-LSPA1-T-PL-1010
[6 empty] | Return Date | 2019-05-07 | 2019-05-07
[6 empty] | Owner Cmmt* | R1 | R1
| PL | OL1-2C12-301000 | Material Requisition for Radiant Steel Panel |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-02 | 2019-04-03
[6 empty] | Issue Actual | 2019-04-02 | 2019-04-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01229 | TPSK-LSPA1-T-PL-01229
Return Date
Owner Cmmt*
| PL | OL1-2C12-307000 | Material Requisition for Radiant Steel Panel |  | Class 2 | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2019-07-16 | 2019-10-21
Revised Plan
[6 empty] | Issue Actual |  | 2019-05-20 | 2019-05-21
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01699 | TPSK-LSPA1-T-PL-01699
Return Date
Owner Cmmt*
| PL | OL1-2C12-308000 | Material Requisition for Utility Steel |  | Class 2 | Purpose** | IFQ | IFQ | IFP
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-07-16 |  | 2019-10-21
[6 empty] | Revised Plan |  |  | 2019-10-21
[6 empty] | Issue Actual | 2019-06-21 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01952 | TPSK-LSPA1-T-PL-01952
Return Date
Owner Cmmt*
Category Code: C13 Request for Quotation (RFQ) for Mechanical work (Engineering and Procurement)
| ME | OL1-2C13-100000 | Material Requisition For Shop Assembled Large Columns |  | Class 2 | Purpose** | IFQ | IFQ | IFP | IFP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-05-15 |  | 2019-09-26
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-04-30 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00586 | TPSK-LSPA1-T-ME-00586 | TPSK-LSPA1-T-PL-01526 | TPSK-LSPA1-T-PL-01526
[6 empty] | Return Date | 2019-01-24 | 2019-01-24 | 2019-05-20 | 2019-05-20
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PL | OL1-2C13-101000 | Material Requisition For Shop Assembled Columns |  | Class 2 | Purpose** | IFQ | IFQ | IFP | IFP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-05-15 |  | 2019-09-26
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-06-26 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00705 | TPSK-LSPA1-T-PL-00705 | TPSK-LSPA1-T-PL-01989 | TPSK-LSPA1-T-PL-01989
[6 empty] | Return Date | 2019-06-06 | 2019-06-06 | 2019-07-10 | 2019-07-10
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PL | OL1-2C13-102000 | Material Requisition For Shop Assembled Columns (C4 Unit) |  | Class 2 | Purpose** | IFQ | IFQ | IFP
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-05-15 |  | 2019-09-26
[6 empty] | Revised Plan |  |  | 2019-09-26
[6 empty] | Issue Actual | 2019-05-09 | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01623 | TPSK-LSPA1-T-PL-01623
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PL | OL1-2C13-111000 | Material Requisition For Reactors And Thicker Vessels Requisition For Iinquiry |  | Class 2 | Purpose** | IFQ | IFQ | IFP | IFP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-01-22 |  | 2019-06-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-25 | 2019-02-26 | 2019-06-25 | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00918 | TPSK-LSPA1-T-PL-00918 | TPSK-LSPA1-T-PL-01972 | TPSK-LSPA1-T-PL-01972
[6 empty] | Return Date | 2019-06-06 | 2019-06-06 | 2019-07-04 | 2019-07-04
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R2
| PL | OL1-2C13-120000 | Material Requisition for Deaerator D-5100 |  | Class 2 | Purpose** | IFQ | IFQ | IFP | IFP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2018-11-06 |  | 2019-02-15
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-06 | 2019-04-01 | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00270 | TPSK-LSPA1-T-ME-00270 | TPSK-LSPA1-T-PL-01210 | TPSK-LSPA1-T-PL-01210
[6 empty] | Return Date | 2018-11-29 | 2018-11-29 | 2019-06-06 | 2019-06-06
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PL | OL1-2C13-131000 | Material Requisition For Shop Assembled Large Drums |  | Class 2 | Purpose** | IFQ | IFQ | IFP
[6 empty] | Rev. | A | A | 0
[6 empty] | Issue Plan | 2019-06-03 |  | 2019-10-30
Revised Plan
[6 empty] | Issue Actual | 2019-03-01 | 2019-03-04 | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00967 | TPSK-LSPA1-T-PL-00967 | TPSK-LSPA1-T-PL-02070
[6 empty] | Return Date | 2019-06-06 | 2019-06-06 | 2019-08-01
[6 empty] | Owner Cmmt* | R1 | R1 | R2
| PL | OL1-2C13-132000 | Material Requisition For Shop Assembled CS Drums |  | Class 2 | Purpose** | IFQ | IFQ | IFP
[6 empty] | Rev. | A | A | 0
[6 empty] | Issue Plan | 2019-06-03 |  | 2019-10-30
Revised Plan
[6 empty] | Issue Actual | 2019-03-12 | 2019-03-13 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01032 | TPSK-LSPA1-T-PL-01032 | TPSK-LSPA1-T-PL-02197
[6 empty] | Return Date | 2019-06-06 | 2019-06-06 | 2019-07-31
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PL | OL1-2C13-133000 | Material Requisition For Shop Assembled CS Cladded And SS Vessels |  | Class 2 | Purpose** | IFQ | IFQ | IFP
[6 empty] | Rev. | A | A | 0
[6 empty] | Issue Plan | 2019-06-03 |  | 2019-10-30
Revised Plan
[6 empty] | Issue Actual | 2019-03-26 | 2019-03-27 | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01156 | TPSK-LSPA1-T-PL-01156 | TPSK-LSPA1-T-PL-02262
[6 empty] | Return Date | 2019-06-06 | 2019-06-06 | 2019-08-16
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PL | OL1-2C13-134000 | Material Requisition for Shop Assembled Drums (C4 Unit) |  | Class 2 | Purpose** | IFQ | IFQ | IFP
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-06-03 |  | 2019-10-30
[6 empty] | Revised Plan |  |  | 2019-10-30
[6 empty] | Issue Actual | 2019-07-01 | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02033 | TPSK-LSPA1-T-PL-02033
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2
| PL | OL1-2C13-140000 | Material Requisition for Quench Exchangers |  | Class 2 | Purpose** | IFQ | IFP | IFP | IFP
[6 empty] | Rev. |  | 0 | 1 | 1
[6 empty] | Issue Plan | 2018-10-26 | 2018-12-17
Revised Plan
[6 empty] | Issue Actual |  |  | 2019-04-01 | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00466 | TPSK-LSPA1-T-PL-01221 | TPSK-LSPA1-T-PL-01221
[6 empty] | Return Date |  |  | 2019-06-20 | 2019-06-20
[6 empty] | Owner Cmmt* |  |  | R2 | R2
| PL | OL1-2C13-142000 | Material Requisition Plate And Frame Heat Exchangers Requisition For Purchase |  | Class 2 | Purpose** | IFQ | IFQ | IFP | IFP | IFP | IFP | IFP | IFP
[6 empty] | Rev. | A | A | 0 | 0 | 1 | 1 | 2 | 2
[6 empty] | Issue Plan | 2018-10-08 |  | 2019-02-14
Revised Plan
[6 empty] | Issue Actual | 2018-10-03 | 2018-10-04 | 2019-02-25 | 2019-02-26 | 2019-06-25 | 2019-06-25 | 2019-07-09 | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00124 | TPSK-LSPA1-T-ME-00124 | TPSK-LSPA1-T-PL-00916 | TPSK-LSPA1-T-PL-00916 | TPSK-LSPA1-T-PL-01971 | TPSK-LSPA1-T-PL-01971 | TPSK-LSPA1-T-PL-02098 | TPSK-LSPA1-T-PL-02098
[6 empty] | Return Date | 2018-10-24 | 2018-10-24 | 2019-06-06 | 2019-06-06 | 2019-07-04 | 2019-07-04 | 2019-07-15 | 2019-07-15
Owner Cmmt* | bar: 2018-10-24 to 2019-07-15
| PL | OL1-2C13-143000 | Material Requisition For Heat Recovery System Requisition For Purchase |  | Class 2 | Purpose** | 2018-10-24: IFP; 2018-10-24: IFP; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0; 2019-06-06: 1; 2019-06-06: 1
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-02-21; 2018-10-24: 2019-02-22; 2019-06-06: 2019-04-23; 2019-06-06: 2019-04-24
[6 empty] | Issue Actual | 2018-10-24: 2019-02-21; 2018-10-24: 2019-02-22; 2019-06-06: 2019-04-23; 2019-06-06: 2019-04-24
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00906; 2018-10-24: TPSK-LSPA1-T-PL-00906; 2019-06-06: TPSK-LSPA1-T-PL-01452; 2019-06-06: TPSK-LSPA1-T-PL-01452
[6 empty] | Return Date | 2018-10-24: 2019-06-06; 2018-10-24: 2019-06-06; 2019-06-06: 2019-05-20; 2019-06-06: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C13-144000 | Material Requisition For Cold Box And Core Exchangers Requisition For Purchase |  | Class 2 | Purpose** | IFQ | IFQ | IFQ | IFP | IFP
[6 empty] | Rev. | A | B | B | 0 | 0
[6 empty] | Issue Plan | 2018-10-24: 2018-10-15; 2019-06-06: 2019-02-21
Revised Plan
[6 empty] | Issue Actual | 2018-10-03 | 2018-10-10 | 2018-10-11 | 2019-04-15 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00125 | TPSK-LSPA1-T-ME-00153 | TPSK-LSPA1-T-ME-00153 | TPSK-LSPA1-T-PL-1351 | TPSK-LSPA1-T-PL-1351
[6 empty] | Return Date | 2018-10-24 | 2018-11-02 | 2018-11-02 | 2019-05-20 | 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2019-07-04
| PL | OL1-2C13-145000 | Material Requisition For Hairpin Heat Exchangers Requisition For Inquiry |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-01-30; 2019-06-06: 2019-05-10
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-03-13; 2018-10-24: 2019-03-14; 2019-06-06: 2019-08-09
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01046; 2018-10-24: TPSK-LSPA1-T-PL-01046; 2019-06-06: TPSK-LSPA1-T-PL-02389
[6 empty] | Return Date | 2018-10-24: 2019-06-06; 2018-10-24: 2019-06-06
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C13-151000 | Material Requisition For Condensate Carbon Filter Package |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-03-19; 2019-06-06: 2019-07-16
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-03-13; 2018-10-24: 2019-03-13; 2019-06-06: 2019-08-14
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01039; 2018-10-24: TPSK-LSPA1-T-PL-01039; 2019-06-06: TPSK-LSPA1-T-PL-02402
[6 empty] | Return Date | 2018-10-24: 2019-06-07; 2018-10-24: 2019-06-07
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C13-152000 | Material Requisition For Filters And Coalescers |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-01-24; 2019-06-06: 2019-05-30
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-01-28; 2019-06-06: 2019-05-17
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00737; 2018-10-24: TPSK-LSPA1-T-PL-00737; 2019-06-06: TPSK-LSPA1-T-PL-01689
[6 empty] | Return Date | 2018-10-24: 2019-06-06; 2018-10-24: 2019-06-06; 2019-06-06: 2019-05-30
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C13-152000- | Material Requisition for Filters and Colaescer |  | Class 2 | Purpose** | 2018-10-24: IFP
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-21
[6 empty] | Issue Actual | 2018-10-24: 2019-05-21
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01689
[6 empty] | Return Date | 2018-10-24: 2019-05-30
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C13-161000 | Material Requisition for Silencers |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-03-18; 2019-06-06: 2019-07-05
[6 empty] | Revised Plan | 2019-06-06: 2019-11-05
[6 empty] | Issue Actual | 2018-10-24: 2019-07-15; 2018-10-24: 2019-07-15
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02146; 2018-10-24: TPSK-LSPA1-T-PL-02146
[6 empty] | Return Date | 2018-10-24: 2019-08-01
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C13-201000 | MATERIAL REQUISITION FOR SITE ASSEMBLED TANKS |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-06-03; 2019-06-06: 2019-10-30
[6 empty] | Revised Plan | 2019-06-06: 2019-10-30
[6 empty] | Issue Actual | 2018-10-24: 2019-05-17; 2018-10-24: 2019-05-21
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01688; 2018-10-24: TPSK-LSPA1-T-PL-01688
[6 empty] | Return Date | 2018-10-24: 2019-05-31; 2018-10-24: 2019-05-31
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C13-202000 | MATERIAL REQUISITION FOR FRP TANK |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-13; 2018-10-24: 2019-05-13
[6 empty] | Issue Actual | 2018-10-24: 2019-05-13; 2018-10-24: 2019-05-13
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01646; 2018-10-24: TPSK-LSPA1-T-PL-01646
[6 empty] | Return Date | 2018-10-24: 2019-05-31; 2018-10-24: 2019-05-31
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C13-242000 | Material Requisition For Trays For Columns |  | Class 2 | Purpose** | IFQ | IFP | IFP | IFP | IFP
[6 empty] | Rev. | A | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2018-10-24: 2018-12-17; 2018-10-24: 2019-04-10
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-04-15; 2019-06-06: 2019-04-17; 2019-06-06: 2019-06-10; 2019-07-04: 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00300 | TPSK-LSPA1-T-PL-01352 | TPSK-LSPA1-T-PL-01352 | TPSK-LSPA1-T-PL-01844 | TPSK-LSPA1-T-PL-01844
[6 empty] | Return Date | 2018-10-24: 2018-12-06; 2018-10-24: 2019-05-20; 2019-06-06: 2019-05-20; 2019-07-04: 2019-06-24
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06; 2019-07-04
| PL | OL1-2C13-243000 | Material Requisition For Ripple Trays And Internals |  | Class 2 | Purpose** | 2018-10-24: IFP; 2018-10-24: IFP
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-01-11
[6 empty] | Issue Actual | 2018-10-24: 2019-01-11
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00628; 2018-10-24: TPSK-LSPA1-T-PL-00628
[6 empty] | Return Date | 2018-10-24: 2019-06-06; 2018-10-24: 2019-06-06
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C13-244000 | MATERIAL REQUISITION FOR TRAYS FOR COLUMNS |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-03-27; 2019-06-06: 2019-07-09
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-04-08; 2018-10-24: 2019-04-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01268; 2018-10-24: TPSK-LSPA1-T-PL-01268
[6 empty] | Return Date | 2018-10-24: 2019-06-07; 2018-10-24: 2019-06-07
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C13-245000 | Material Requisition For High Efficiency Internals For Columns Requisition For Purchase |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2018-12-24; 2018-10-24: 2019-04-17
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-05-21; 2019-06-06: 2019-05-23
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-00278; 2018-10-24: TPSK-LSPA1-T-PL-01706; 2019-06-06: TPSK-LSPA1-T-PL-01706
[6 empty] | Return Date | 2018-10-24: 2018-11-29; 2018-10-24: 2019-05-30; 2019-06-06: 2019-05-30
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C13-246000 | Material Requisition for Packing of Columns (C4 Unit) |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFR; 2019-06-06: IFR
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0; 2019-06-06: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-03-28; 2018-10-24: 2019-03-28; 2019-06-06: 2019-07-08; 2019-06-06: 2019-07-08
[6 empty] | Issue Actual | 2018-10-24: 2019-03-28; 2018-10-24: 2019-03-28; 2019-06-06: 2019-07-08; 2019-06-06: 2019-07-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01182; 2018-10-24: TPSK-LSPA1-T-PL-01182; 2019-06-06: TPSK-LSPA1-T-PL-02081; 2019-06-06: TPSK-LSPA1-T-PL-02081
[6 empty] | Return Date | 2018-10-24: 2019-06-07; 2018-10-24: 2019-06-07; 2019-06-06: 2019-07-16; 2019-06-06: 2019-07-16
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C13-251000 | Material Requisition For API Mechanical Seals and Seal System |  | Class 2 | Purpose** | IFQ | IFQ | IFP | IMP | IMP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0; 2019-07-04: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-01-17; 2019-06-06: 2019-05-01
[6 empty] | Revised Plan | 2019-06-06: 2019-07-09; 2019-07-04: 2019-07-09
[6 empty] | Issue Actual | 2018-10-24: 2019-02-28; 2018-10-24: 2019-03-01; 2019-06-06: 2019-07-09; 2019-07-04: 2019-07-09
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00949; 2018-10-24: TPSK-LSPA1-T-PL-00949; 2019-06-06: TPSK-LSPA1-T-PL-02096; 2019-07-04: TPSK-LSPA1-T-PL-02096
[6 empty] | Return Date | 2019-06-06: 2019-07-18
Owner Cmmt* | bar: 2019-06-06
| PL | OL1-2C13-271000 | Material Requisition For Wieland Tubes - Solo Source - Requisition For Purchase - Ex Doc. Client Reference OL1-2M57-0058 |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-06-03; 2019-06-06: 2019-10-30
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2018-11-28; 2019-06-06: 2019-02-08; 2019-06-06: 2019-02-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-00377; 2018-10-24: TPSK-LSPA1-T-ME-00377; 2019-06-06: TPSK-LSPA1-T-PL-00829; 2019-06-06: TPSK-LSPA1-T-PL-00829
[6 empty] | Return Date | 2018-10-24: 2019-02-07; 2018-10-24: 2019-02-07
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C13-272000 | Material Requisition For S&T Heat Exchangers - Large - Requisition For Inquiry |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-06-03; 2019-06-06: 2019-10-30
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-02-13; 2018-10-24: 2019-02-13; 2019-06-06: 2019-07-17
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00849; 2018-10-24: TPSK-LSPA1-T-PL-00849; 2019-06-06: TPSK-LSPA1-T-PL-02169
[6 empty] | Return Date | 2018-10-24: 2019-02-27; 2018-10-24: 2019-02-27
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C13-273000 | Material Requisition For CS S-T Heat Exchangers Requisition For Inquiry |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-06-03; 2019-06-06: 2019-10-30
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-02-15; 2018-10-24: 2019-02-15; 2019-06-06: 2019-07-25
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00866; 2018-10-24: TPSK-LSPA1-T-PL-00866; 2019-06-06: TPSK-LSPA1-T-PL-02261
[6 empty] | Return Date | 2018-10-24: 2019-06-06; 2018-10-24: 2019-06-06; 2019-06-06: 2019-08-14
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C13-274000 | Material Requisition For CS Clad SS And LAS S-T Heat Exchangers Requisition For Inquiry |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-06-03; 2019-06-06: 2019-10-30
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-02-15; 2018-10-24: 2019-02-15; 2019-06-06: 2019-07-22
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00870; 2018-10-24: TPSK-LSPA1-T-PL-00870; 2019-06-06: TPSK-LSPA1-T-PL-02195
[6 empty] | Return Date | 2018-10-24: 2019-06-06; 2018-10-24: 2019-06-06; 2019-06-06: 2019-07-31
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C13-275000 | Material Requisition For CS S&T Heat Exchangers (C4 UNIT) |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-06-03; 2019-06-06: 2019-10-30
[6 empty] | Revised Plan | 2019-06-06: 2019-10-30
[6 empty] | Issue Actual | 2018-10-24: 2019-06-10; 2018-10-24: 2019-06-10
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01838; 2018-10-24: TPSK-LSPA1-T-PL-01838
[6 empty] | Return Date | 2018-10-24: 2019-06-27
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C13-281000 | Material Requisition for Furnace Convection Finnings |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-01-21; 2019-06-06: 2019-03-20
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-01-23; 2019-06-06: 2019-03-15; 2019-06-06: 2019-03-18
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00713; 2018-10-24: TPSK-LSPA1-T-PL-00713; 2019-06-06: TPSK-LSPA1-T-PL-01085; 2019-06-06: TPSK-LSPA1-T-PL-01085
Return Date
Owner Cmmt*
| PL | OL1-2C13-282000 | Material Requisition for Convection Fabrication |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-07-16; 2019-06-06: 2019-10-21
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-04-11; 2018-10-24: 2019-04-12; 2019-06-06: 2019-06-04; 2019-06-06: 2019-06-10
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-01316; 2018-10-24: TPSK-LSPA1-T-ME-01316; 2019-06-06: TPSK-LSPA1-T-PL-01798; 2019-06-06: TPSK-LSPA1-T-PL-01798
[6 empty] | Return Date | 2019-06-06: 2019-06-21
Owner Cmmt* | bar: 2019-06-06
| PL | OL1-2C13-283000 | Material Requisition for Radiant Refractory |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-02-07; 2019-06-06: 2019-04-15
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-03-20; 2018-10-24: 2019-03-21; 2019-06-06: 2019-05-13; 2019-06-06: 2019-05-14
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01108; 2018-10-24: TPSK-LSPA1-T-PL-01108; 2019-06-06: TPSK-LSPA1-T-PL-01657; 2019-06-06: TPSK-LSPA1-T-PL-01657
[6 empty] | Return Date | 2019-06-06: 2019-06-19; 2019-06-06: 2019-06-19
Owner Cmmt* | bar: 2019-06-06 to 2019-06-06
| PL | OL1-2C13-284000 | Material Requisition for Peep Doors |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2018-12-10; 2019-06-06: 2019-04-03
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2018-12-14; 2019-06-06: 2019-03-27; 2019-06-06: 2019-03-28
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-00502; 2018-10-24: TPSK-LSPA1-T-ME-00502; 2019-06-06: TPSK-LSPA1-T-PL-01181; 2019-06-06: TPSK-LSPA1-T-PL-01181
Return Date
Owner Cmmt*
| PL | OL1-2C13-285000 | Material Requisition for MOVs |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2018-12-18; 2019-06-06: 2019-03-19
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2018-12-18; 2019-06-06: 2019-04-01; 2019-06-06: 2019-04-02
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-00534; 2018-10-24: TPSK-LSPA1-T-ME-00534; 2019-06-06: TPSK-LSPA1-T-PL-01219; 2019-06-06: TPSK-LSPA1-T-PL-01219
Return Date
Owner Cmmt*
| PL | OL1-2C13-286000 | Material Requisition for Attemperators |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-01-16; 2019-06-06: 2019-04-03
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-01-30; 2018-10-24: 2019-01-31; 2019-06-06: 2019-05-28; 2019-06-06: 2019-05-29
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00771; 2018-10-24: TPSK-LSPA1-T-PL-00771; 2019-06-06: TPSK-LSPA1-T-PL-01756; 2019-06-06: TPSK-LSPA1-T-PL-01756
[6 empty] | Return Date | 2018-10-24: 2019-06-07; 2018-10-24: 2019-06-07; 2019-06-06: 2019-06-19; 2019-06-06: 2019-06-19
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C13-300000 | Material Requisition for Radiant Coil Assemblies |  | Class 2 | Purpose** | IFQ | IFP | IFP | IFP | IFP
[6 empty] | Rev. | A | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2018-10-24: 2018-09-19; 2018-10-24: 2019-02-14
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2018-09-18; 2019-06-06: 2018-12-14; 2019-06-06: 2019-03-25; 2019-07-04: 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00063 | TPSK-LSPA1-T-ME-00499 | TPSK-LSPA1-T-ME-00499 | TPSK-LSPA1-T-PL-01139 | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| PL | OL1-2C13-301000 | Material Requisition for Furnace ID Fans |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2018-11-05; 2018-10-24: 2019-01-17
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-03-20; 2019-06-06: 2019-03-21
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-00269; 2018-10-24: TPSK-LSPA1-T-PL-01109; 2019-06-06: TPSK-LSPA1-T-PL-01109
Return Date
Owner Cmmt*
| PL | OL1-2C13-302000 | Material Requisition for Cast Intermediate Tube Supports |  | Class 2 | Purpose** | IFQ | IFP | IFP | IFP | IFP
[6 empty] | Rev. | A | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2018-10-24: 2018-11-16; 2018-10-24: 2019-01-28
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2018-11-16; 2019-06-06: 2018-12-20; 2019-06-06: 2019-03-25; 2019-07-04: 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00329 | TPSK-LSPA1-T-ME-00542 | TPSK-LSPA1-T-ME-00542 | TPSK-LSPA1-T-PL-01139 | TPSK-LSPA1-T-PL-01139
[6 empty] | Return Date | 2018-10-24: 2018-12-10
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C13-303000 | Material Requisition for Convection Tubes |  | Class 2 | Purpose** | IFQ | IFP | IFP | IFP | IFP
[6 empty] | Rev. | A | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2018-10-24: 2018-10-22; 2018-10-24: 2018-12-21
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2018-09-12; 2019-06-06: 2018-12-10; 2019-06-06: 2019-03-25; 2019-07-04: 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00044 | TPSK-LSPA1-T-ME-00450 | TPSK-LSPA1-T-ME-00450 | TPSK-LSPA1-T-PL-01139 | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| PL | OL1-2C13-304000 | Material Requisition for Furnace Convection Fittings |  | Class 2 | Purpose** | IFQ | IFP | IFP | IFP | IFP
[6 empty] | Rev. | A | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2018-10-24: 2018-10-22; 2018-10-24: 2018-12-21
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2018-10-22; 2019-06-06: 2019-01-07; 2019-06-06: 2019-03-25; 2019-07-04: 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00207 | TPSK-LSPA1-T-ME-00592 | TPSK-LSPA1-T-ME-00592 | TPSK-LSPA1-T-PL-01139 | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| PL | OL1-2C13-305000 | Material Requisition for Furnace Steam Drums |  | Class 2 | Purpose** | IFQ | IFP | IFP | IFP | IFP
[6 empty] | Rev. | A | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2018-10-24: 2018-10-26; 2018-10-24: 2018-12-17
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2018-11-01; 2019-06-06: 2018-12-17; 2019-06-06: 2019-03-25; 2019-07-04: 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00263 | TPSK-LSPA1-T-ME-00518 | TPSK-LSPA1-T-ME-00518 | TPSK-LSPA1-T-PL-01139 | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| ME | OL1-2C13-306000 | Material Requisition for Furnace Burners |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2018-11-13; 2019-06-06: 2019-01-23
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2018-11-13; 2019-06-06: 2019-02-07; 2019-06-06: 2019-02-07
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-00313; 2018-10-24: TPSK-LSPA1-T-ME-00313; 2019-06-06: TPSK-LSPA1-T-ME-00820; 2019-06-06: TPSK-LSPA1-T-ME-00820
Return Date
Owner Cmmt*
| PL | OL1-2C13-311000 | Material Requisition for Cooling Tower |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2018-10-31; 2019-06-06: 2019-03-26
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2018-11-06; 2019-06-06: 2019-04-24; 2019-06-06: 2019-04-25
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-00276; 2018-10-24: TPSK-LSPA1-T-ME-00276; 2019-06-06: TPSK-LSPA1-T-PL-01460; 2019-06-06: TPSK-LSPA1-T-PL-01460
[6 empty] | Return Date | 2018-10-24: 2019-02-15; 2018-10-24: 2019-02-15; 2019-06-06: 2019-05-24; 2019-06-06: 2019-05-24
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C13-321001 | Material Requisition For Ladders And Platforms For Equipment Requisition For Inquiry |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-07; 2018-10-24: 2019-05-08
[6 empty] | Issue Actual | 2018-10-24: 2019-05-07; 2018-10-24: 2019-05-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01593; 2018-10-24: TPSK-LSPA1-T-PL-01593
[6 empty] | Return Date | 2018-10-24: 2019-05-23; 2018-10-24: 2019-05-23
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C13-401000 | Material Requisition For Centrifugal Compressors Steam Turbine Driven - Ex Document Cliet Reference OL1-2M55-0008 |  | Class 2 | Purpose** | IFQ | IFQ | IFP | IFP | IFP | IFP
[6 empty] | Rev. | A | A | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2018-10-24: 2018-10-04; 2019-06-06: 2019-04-03
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-08 | 2019-03-21 | 2019-03-22 | 2019-04-19 | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00136 | TPSK-LSPA1-T-ME-00136 | TPSK-LSPA1-T-PL-01124 | TPSK-LSPA1-T-PL-01124 | TPSK-LSPA1-T-PL-01420 | TPSK-LSPA1-T-PL-01420
[6 empty] | Return Date | 2018-10-24: 2018-10-26; 2018-10-24: 2018-10-26; 2019-07-04: 2019-05-20; 2019-07-04: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24; 2019-07-04 to 2019-07-04
| PL | OL1-2C13-402000 | Material Requisition for Integrally Geared Decoking Air Compressors - Ex Document Client Reference OL1-2M55-0014 |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2018-10-18; 2018-10-24: 2019-04-17
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2018-10-19; 2018-10-24: 2019-05-22; 2019-06-06: 2019-05-23
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-00198; 2018-10-24: TPSK-LSPA1-T-PL-01720; 2019-06-06: TPSK-LSPA1-T-PL-01720
[6 empty] | Return Date | 2018-10-24: 2018-11-07; 2019-06-06: 2019-06-17
Owner Cmmt* | bar: 2018-10-24; 2019-06-06
| PL | OL1-2C13-403000 | Material Requisition for Recycle Gas Compressor |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-02-25; 2019-06-06: 2019-07-22
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-01-23; 2019-06-06: 2019-07-10; 2019-06-06: 2019-07-10
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00714; 2018-10-24: TPSK-LSPA1-T-PL-00714; 2019-06-06: TPSK-LSPA1-T-PL-02106; 2019-06-06: TPSK-LSPA1-T-PL-02106
[6 empty] | Return Date | 2018-10-24: 2019-06-27; 2019-06-06: 2019-08-01
Owner Cmmt* | bar: 2018-10-24; 2019-06-06
| PL | OL1-2C13-404000 | Material Requisition For General Purpose Steam Turbines |  | Class 2 | Purpose** | 2018-10-24: IMP; 2018-10-24: IMP
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-15; 2018-10-24: 2019-07-15
[6 empty] | Issue Actual | 2018-10-24: 2019-07-15; 2018-10-24: 2019-07-15
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02131; 2018-10-24: TPSK-LSPA1-T-PL-02131
[6 empty] | Return Date | 2018-10-24: 2019-07-25
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C13-421000 | Material Requisition For Residue Gas Expander/Recompressor |  | Class 2 | Purpose** | IFQ | IFQ | IFP | IFP | IFP | IFP
[6 empty] | Rev. | A | A | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2018-10-24: 2018-10-05; 2019-06-06: 2019-04-05
Revised Plan
[6 empty] | Issue Actual | 2018-10-07 | 2018-10-09 | 2019-03-21 | 2019-03-22 | 2019-04-23 | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00139 | TPSK-LSPA1-T-ME-00139 | TPSK-LSPA1-T-PL-01118 | TPSK-LSPA1-T-PL-01118 | TPSK-LSPA1-T-PL-01443 | TPSK-LSPA1-T-PL-01443
[6 empty] | Return Date | 2018-10-24: 2018-10-26; 2018-10-24: 2018-10-26; 2019-07-04: 2019-05-20; 2019-07-04: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24; 2019-07-04 to 2019-07-04
| PL | OL1-2C13-440003 | Material Requisition for Cooling Water Pumps |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-01-31; 2018-10-24: 2019-05-23
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-07-10; 2019-06-06: 2019-07-10
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02113; 2019-06-06: TPSK-LSPA1-T-PL-02113
[6 empty] | Return Date | 2019-06-06: 2019-07-30
Owner Cmmt* | bar: 2019-06-06
| PL | OL1-2C13-441000 | Material Requisition For API Centrifugal Pumps - LLI |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-01-31; 2018-10-24: 2019-05-23
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-07-09; 2019-06-06: 2019-07-09
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02095; 2019-06-06: TPSK-LSPA1-T-PL-02095
[6 empty] | Return Date | 2019-06-06: 2019-07-18
Owner Cmmt* | bar: 2019-06-06
| PL | OL1-2C13-442000 | Material Requisition For API Centrifugal Pumps |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-01-31; 2019-06-06: 2019-05-23
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-02-19; 2018-10-24: 2019-02-19; 2019-06-06: 2019-08-14
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00880; 2018-10-24: TPSK-LSPA1-T-PL-00880; 2019-06-06: TPSK-LSPA1-T-PL-02408
Return Date
Owner Cmmt*
| PL | OL1-2C13-443000 | Material Requisition For Submersible Pumps |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-01-31; 2019-06-06: 2019-05-23
[6 empty] | Revised Plan | 2019-06-06: 2019-10-18
[6 empty] | Issue Actual | 2018-10-24: 2019-05-24; 2018-10-24: 2019-05-27
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01736; 2018-10-24: TPSK-LSPA1-T-PL-01736
[6 empty] | Return Date | 2018-10-24: 2019-06-17
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C13-446000 | Material Requisition For API 685 Sealless Pump |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-02; 2018-10-24: 2019-07-02
[6 empty] | Issue Actual | 2018-10-24: 2019-07-02; 2018-10-24: 2019-07-02
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02034; 2018-10-24: TPSK-LSPA1-T-PL-02034
[6 empty] | Return Date | 2018-10-24: 2019-07-16; 2018-10-24: 2019-07-16
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C13-447000 | Material Requisition For API Centrifugal Pumps |  | Class 2 | Purpose** | 2018-10-24: IFP
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-14
[6 empty] | Issue Actual | 2018-10-24: 2019-08-14
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02408
Return Date
Owner Cmmt*
| PL | OL1-2C13-449000 | Material Requisition For API Centrifugal Pumps |  | Class 2 | Purpose** | 2018-10-24: IFP
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-14
[6 empty] | Issue Actual | 2018-10-24: 2019-08-14
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02408
Return Date
Owner Cmmt*
| PL | OL1-2C13-451000 | Material Requisition For Vent Gas Blower |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2018-12-21; 2019-06-06: 2019-04-30
[6 empty] | Revised Plan | 2019-06-06: 2019-10-18
[6 empty] | Issue Actual | 2018-10-24: 2019-03-07; 2018-10-24: 2019-03-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01001; 2018-10-24: TPSK-LSPA1-T-PL-01001
[6 empty] | Return Date | 2018-10-24: 2019-03-27; 2018-10-24: 2019-03-27
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C13-700000 | Material Requisition For Electric Heater |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-04-18; 2018-10-24: 2019-04-18
[6 empty] | Issue Actual | 2018-10-24: 2019-04-18; 2018-10-24: 2019-04-18
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01409; 2018-10-24: TPSK-LSPA1-T-PL-01409
[6 empty] | Return Date | 2018-10-24: 2019-05-30; 2018-10-24: 2019-05-30
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C13-701000 | Material Requisition for Condensate Polisher Package |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-02-22; 2019-06-06: 2019-06-10
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-02-27; 2018-10-24: 2019-02-27
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00940; 2018-10-24: TPSK-LSPA1-T-PL-00940
[6 empty] | Return Date | 2018-10-24: 2019-06-07; 2018-10-24: 2019-06-07
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C13-702000 | Material Requisition For Complex Waste Water Treatment Package |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-01-25; 2019-06-06: 2019-05-31
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-02-15; 2018-10-24: 2019-02-15; 2019-06-06: 2019-08-09
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00862; 2018-10-24: TPSK-LSPA1-T-PL-00862; 2019-06-06: TPSK-LSPA1-T-PL-02399
[6 empty] | Return Date | 2018-10-24: 2019-06-07; 2018-10-24: 2019-06-07
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C13-704000 | Material Requisition for Wet Air Oxidation Package |  | Class 2 | Purpose** | IFQ | IFQ | IFP | IFP | IFP | IFP
[6 empty] | Rev. | A | A | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2018-10-24: 2018-11-30; 2019-06-06: 2019-04-15
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-27 | 2019-05-08 | 2019-05-09 | 2019-06-20 | 2019-06-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00367 | TPSK-LSPA1-T-ME-00367 | TPSK-LSPA1-T-PL-01611 | TPSK-LSPA1-T-PL-01611 | TPSK-LSPA1-T-PL-01943 | TPSK-LSPA1-T-PL-01943
[6 empty] | Return Date | 2019-02-07 | 2019-02-07 | 2019-06-16 | 2019-06-16 | 2019-07-08 | 2019-07-08
Owner Cmmt* | bar: 2018-10-24 to 2019-07-04
| PL | OL1-2C13-705000 | Material Requisition For Hydrogen Production Unit PK-2560 |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2018-11-14; 2019-06-06: 2019-02-15
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2018-11-06; 2019-06-06: 2019-05-06; 2019-06-06: 2019-05-07
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-00271; 2018-10-24: TPSK-LSPA1-T-ME-00271; 2019-06-06: TPSK-LSPA1-T-PL-01580; 2019-06-06: TPSK-LSPA1-T-PL-01580
[6 empty] | Return Date | 2018-10-24: 2019-02-07; 2018-10-24: 2019-02-07; 2019-06-06: 2019-05-27; 2019-06-06: 2019-05-27
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C13-706000 | Material Requisition for Side Stream Filter Package |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2018-11-07; 2019-06-06: 2019-04-05
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2018-10-31; 2019-06-06: 2019-03-27; 2019-06-06: 2019-03-27
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-00248; 2018-10-24: TPSK-LSPA1-T-ME-00248; 2019-06-06: TPSK-LSPA1-T-PL-01165; 2019-06-06: TPSK-LSPA1-T-PL-01165
[6 empty] | Return Date | 2018-10-24: 2018-11-27; 2018-10-24: 2018-11-27; 2019-06-06: 2019-06-07; 2019-06-06: 2019-06-07
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C13-707000 | Material Requisition For Chemical Dosing System |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-06; 2019-06-06: 2019-07-02
[6 empty] | Revised Plan | 2019-06-06: 2019-09-13
[6 empty] | Issue Actual | 2018-10-24: 2019-04-26; 2018-10-24: 2019-04-29
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01491; 2018-10-24: TPSK-LSPA1-T-PL-01491
[6 empty] | Return Date | 2018-10-24: 2019-05-31; 2018-10-24: 2019-05-31
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C13-708000 | MR for HP / Polyolefins Flare Package |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-02-18; 2019-06-06: 2019-06-21
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-01-17; 2019-06-06: 2019-06-25; 2019-06-06: 2019-06-25
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00665; 2018-10-24: TPSK-LSPA1-T-PL-00665; 2019-06-06: TPSK-LSPA1-T-PL-01951; 2019-06-06: TPSK-LSPA1-T-PL-01951
[6 empty] | Return Date | 2018-10-24: 2019-06-11; 2018-10-24: 2019-06-11; 2019-06-06: 2019-07-08; 2019-06-06: 2019-07-08
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| ME | OL1-2C13-709000 | Material Requisition for Furnace Elevator |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2018-12-19; 2019-06-06: 2019-02-19
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-01-22; 2019-06-06: 2019-07-25
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-00697; 2018-10-24: TPSK-LSPA1-T-ME-00697; 2019-06-06: TPSK-LSPA1-T-PL-02260
[6 empty] | Return Date | 2018-10-24: 2019-02-14; 2018-10-24: 2019-02-14; 2019-06-06: 2019-08-15
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C13-771000 | Material Requisition For Bridge Crane |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-05-09; 2019-06-06: 2019-09-15
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-02-22; 2018-10-24: 2019-02-25; 2019-06-06: 2019-08-07
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PC-00914; 2018-10-24: TPSK-LSPA1-T-PC-00914; 2019-06-06: TPSK-LSPA1-T-PL-02361
Return Date
Owner Cmmt*
| PL | OL1-2C13-801000 | Material Requisition For Ejectors And Static Mixers |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-05; 2019-06-06: 2019-07-24
[6 empty] | Revised Plan | 2019-06-06: 2019-09-03
[6 empty] | Issue Actual | 2018-10-24: 2019-04-18; 2018-10-24: 2019-04-18
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01408; 2018-10-24: TPSK-LSPA1-T-PL-01408
[6 empty] | Return Date | 2018-10-24: 2019-05-24; 2018-10-24: 2019-05-24
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
Category Code: C14 Request for Quotation (RFQ) Piping work (Engineering and Procurement)
| PL | OL1-2C14-100001 | Material Requisition For Gate Globe And Check Forged Valves |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-13; 2019-06-06: 2020-10-15
[6 empty] | Revised Plan | 2019-06-06: 2020-10-15
[6 empty] | Issue Actual | 2018-10-24: 2019-05-03; 2018-10-24: 2019-05-06
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01567; 2018-10-24: TPSK-LSPA1-T-PL-01567
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-110001 | Material Requisition For Gate Globe And Check Cast Valves Low Pressure |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-13; 2019-06-06: 2020-07-01
[6 empty] | Revised Plan | 2019-06-06: 2020-07-01
[6 empty] | Issue Actual | 2018-10-24: 2019-05-06; 2018-10-24: 2019-05-07
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01574; 2018-10-24: TPSK-LSPA1-T-PL-01574
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-115001 | Material Requisition For Gate Globe Check Cast Valves High Pressure |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-06; 2018-10-24: 2019-05-07
[6 empty] | Issue Actual | 2018-10-24: 2019-05-06; 2018-10-24: 2019-05-07
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01579; 2018-10-24: TPSK-LSPA1-T-PL-01579
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-120001 | Material Requisition For Butterfly Valves Low Pressure Category A |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-07; 2018-10-24: 2019-05-08
[6 empty] | Issue Actual | 2018-10-24: 2019-05-07; 2018-10-24: 2019-05-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01592; 2018-10-24: TPSK-LSPA1-T-PL-01592
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-125001 | Material Requisition For Butterfly Valves High Performance (Category B) |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-13; 2019-06-06: 2020-07-01
[6 empty] | Revised Plan | 2019-06-06: 2020-07-01
[6 empty] | Issue Actual | 2018-10-24: 2019-05-06; 2018-10-24: 2019-05-07
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01575; 2018-10-24: TPSK-LSPA1-T-PL-01575
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-130001 | Material Requisition For Plug Valves |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-13; 2019-06-06: 2020-07-01
[6 empty] | Revised Plan | 2019-06-06: 2020-07-01
[6 empty] | Issue Actual | 2018-10-24: 2019-05-06; 2018-10-24: 2019-05-07
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01576; 2018-10-24: TPSK-LSPA1-T-PL-01576
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-140001 | Material Requisition For Ball Valves |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-13; 2019-06-06: 2020-07-01
[6 empty] | Revised Plan | 2019-06-06: 2020-07-01
[6 empty] | Issue Actual | 2018-10-24: 2019-05-06; 2018-10-24: 2019-05-07
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01577; 2018-10-24: TPSK-LSPA1-T-PL-01577
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-150001 | Material Requisition For Dual Plate Check Valves |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-13; 2019-06-06: 2020-07-01
[6 empty] | Revised Plan | 2019-06-06: 2020-07-01
[6 empty] | Issue Actual | 2018-10-24: 2019-05-06; 2018-10-24: 2019-05-07
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01578; 2018-10-24: TPSK-LSPA1-T-PL-01578
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-210001 | Material Requisition For Carbon Steel Seamless Pipe |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-06; 2019-06-06: 2020-10-15
[6 empty] | Revised Plan | 2019-06-06: 2020-10-15
[6 empty] | Issue Actual | 2018-10-24: 2019-04-30; 2018-10-24: 2019-05-02
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01525; 2018-10-24: TPSK-LSPA1-T-PL-01525
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-215001 | Material Requisition For Carbon Steel Welded Pipe |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-06; 2019-06-06: 2020-06-17
[6 empty] | Revised Plan | 2019-06-06: 2020-06-17
[6 empty] | Issue Actual | 2018-10-24: 2019-04-30; 2018-10-24: 2019-05-02
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01527; 2018-10-24: TPSK-LSPA1-T-PL-01527
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-220001 | Material Requisition For Alloy Steel Seamless Pipe |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-06; 2019-06-06: 2020-06-17
[6 empty] | Revised Plan | 2019-06-06: 2020-06-17
[6 empty] | Issue Actual | 2018-10-24: 2019-04-30; 2018-10-24: 2019-05-02
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01528; 2018-10-24: TPSK-LSPA1-T-PL-01528
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-225001 | Material Requisition For Alloy Steel Welded Pipe |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-06; 2019-06-06: 2020-06-17
[6 empty] | Revised Plan | 2019-06-06: 2020-06-17
[6 empty] | Issue Actual | 2018-10-24: 2019-04-30; 2018-10-24: 2019-05-02
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01529; 2018-10-24: TPSK-LSPA1-T-PL-01529
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-230001 | Material Requisition For Stainless Steel Seamless Pipe |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-06; 2019-06-06: 2020-10-15
[6 empty] | Revised Plan | 2019-06-06: 2020-10-15
[6 empty] | Issue Actual | 2018-10-24: 2019-05-02; 2018-10-24: 2019-05-03
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01553; 2018-10-24: TPSK-LSPA1-T-PL-01553
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-235001 | Material Requisition For Stainless Steel Welded Pipe |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-06; 2019-06-06: 2020-10-15
[6 empty] | Revised Plan | 2019-06-06: 2020-10-15
[6 empty] | Issue Actual | 2018-10-24: 2019-05-02; 2018-10-24: 2019-05-03
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01555; 2018-10-24: TPSK-LSPA1-T-PL-01555
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-250001 | Material Requisition For Buttwelding Fittings |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-06; 2019-06-06: 2020-10-15
[6 empty] | Revised Plan | 2019-06-06: 2020-10-15
[6 empty] | Issue Actual | 2018-10-24: 2019-05-02; 2018-10-24: 2019-05-03
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01557; 2018-10-24: TPSK-LSPA1-T-PL-01557
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-260001 | Material Requisition For Forged Fittings |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-06; 2019-06-06: 2020-10-15
[6 empty] | Revised Plan | 2019-06-06: 2020-10-15
[6 empty] | Issue Actual | 2018-10-24: 2019-05-02; 2018-10-24: 2019-05-03
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01559; 2018-10-24: TPSK-LSPA1-T-PL-01559
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-270001 | Material Requisition For Flanges Blinds And Drip Rings |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-06; 2019-06-06: 2020-10-15
[6 empty] | Revised Plan | 2019-06-06: 2020-10-15
[6 empty] | Issue Actual | 2018-10-24: 2019-05-02; 2018-10-24: 2019-05-03
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01558; 2018-10-24: TPSK-LSPA1-T-PL-01558
[6 empty] | Return Date | 2018-10-24: 2019-05-20; 2018-10-24: 2019-05-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-360001 | Material Requisition For Carbon Steel Underground Piping |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-03-01; 2018-10-24: 2019-03-04; 2019-06-06: 2019-08-14
[6 empty] | Issue Actual | 2018-10-24: 2019-03-01; 2018-10-24: 2019-03-04; 2019-06-06: 2019-08-14
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00969; 2018-10-24: TPSK-LSPA1-T-PL-00969; 2019-06-06: TPSK-LSPA1-T-PL-02412
[6 empty] | Return Date | 2018-10-24: 2019-06-06; 2018-10-24: 2019-06-06
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-365001 | Material Requisition For Underground Welded Carbon Steel Pipes |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-03-04; 2018-10-24: 2019-03-05; 2019-06-06: 2019-08-09
[6 empty] | Issue Actual | 2018-10-24: 2019-03-04; 2018-10-24: 2019-03-05; 2019-06-06: 2019-08-09
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00975; 2018-10-24: TPSK-LSPA1-T-PL-00975; 2019-06-06: TPSK-LSPA1-T-PL-02388
[6 empty] | Return Date | 2018-10-24: 2019-06-06; 2018-10-24: 2019-06-06
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C14-502000 | Material Requisition for SP Item Angle Valves |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-02-20; 2019-06-06: 2019-04-24
[6 empty] | Revised Plan | 2019-06-06: 2019-08-23
[6 empty] | Issue Actual | 2018-10-24: 2019-06-04; 2018-10-24: 2019-06-10
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01800; 2018-10-24: TPSK-LSPA1-T-PL-01800
[6 empty] | Return Date | 2018-10-24: 2019-06-21
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C14-503000 | Material Requisition for SP Item - Sample Cooler |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-02-20; 2019-06-06: 2019-04-24
[6 empty] | Revised Plan | 2019-06-06: 2019-08-23
[6 empty] | Issue Actual | 2018-10-24: 2019-07-03; 2018-10-24: 2019-07-03
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02057; 2018-10-24: TPSK-LSPA1-T-PL-02057
Return Date
Owner Cmmt*
| PL | OL1-2C14-504000 | Material Requisition for SP Item T-Type Filter |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-02-20; 2019-06-06: 2019-04-24
[6 empty] | Revised Plan | 2019-06-06: 2019-08-23
[6 empty] | Issue Actual | 2018-10-24: 2019-06-26; 2018-10-24: 2019-06-26
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01996; 2018-10-24: TPSK-LSPA1-T-PL-01996
Return Date
Owner Cmmt*
| PL | OL1-2C14-505000 | Material Requisition for SP Item Isokinetic Sampling Nozzle |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-02-20; 2019-06-06: 2019-04-24
[6 empty] | Revised Plan | 2019-06-06: 2019-08-23
[6 empty] | Issue Actual | 2018-10-24: 2019-06-07; 2018-10-24: 2019-06-10
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01833; 2018-10-24: TPSK-LSPA1-T-PL-01833
Return Date
Owner Cmmt*
| PL | OL1-2C14-506000 | Material Requisition for SP Item - Vent Silencer |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-03; 2018-10-24: 2019-07-03
[6 empty] | Issue Actual | 2018-10-24: 2019-07-03; 2018-10-24: 2019-07-03
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02060; 2018-10-24: TPSK-LSPA1-T-PL-02060
Return Date
Owner Cmmt*
Category Code: C15 Request for Quotation (RFQ) for Fire Fighting work (Engineering and Procurement)
| PL | OL1-2C15-821001 | Material Requisition for Fire Fighting and Safety Equipment Package |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-07-05; 2019-06-06: 2019-10-09
[6 empty] | Revised Plan | 2019-06-06: 2019-10-09
[6 empty] | Issue Actual | 2018-10-24: 2019-07-08; 2018-10-24: 2019-07-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02083; 2018-10-24: TPSK-LSPA1-T-PL-02083
[6 empty] | Return Date | 2018-10-24: 2019-08-06
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C15-822001 | Material Requisition for Deluge and Sprinkler System Package |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-07-05; 2019-06-06: 2019-10-09
[6 empty] | Revised Plan | 2019-06-06: 2019-10-09
[6 empty] | Issue Actual | 2018-10-24: 2019-07-08; 2018-10-24: 2019-07-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02083; 2018-10-24: TPSK-LSPA1-T-PL-02083
[6 empty] | Return Date | 2018-10-24: 2019-08-08
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C15-823001 | Material Requisition for Clean Agent Fire Extinguishing System |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-07-05; 2019-06-06: 2019-10-09
[6 empty] | Revised Plan | 2019-06-06: 2019-10-09
[6 empty] | Issue Actual | 2018-10-24: 2019-07-08; 2018-10-24: 2019-07-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02083; 2018-10-24: TPSK-LSPA1-T-PL-02083
[6 empty] | Return Date | 2018-10-24: 2019-08-08
Owner Cmmt* | bar: 2018-10-24
Category Code: C16 Request for Quotation (RFQ) for Electrical and HVAC work (Engineering and Procurement)
| PL | OL1-2C16-150000 | Material Requisition For Distribution Transformer |  | Class 2 | Purpose** | 2018-10-24: IFQ
Rev. | bar: 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-06-03
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-08-05
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02326
Return Date
Owner Cmmt*
| PL | OL1-2C16-160000 | Material Requisition For Power Capacitors |  | Class 2 | Purpose** | 2018-10-24: IFQ
Rev. | bar: 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-06-14
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-08-06
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LPSA1-T-PL-02342
Return Date
Owner Cmmt*
| PL | OL1-2C16-3400 | Material Requisition for HVAC System |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-08; 2018-10-24: 2019-07-08
[6 empty] | Issue Actual | 2018-10-24: 2019-07-08; 2018-10-24: 2019-07-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02092; 2018-10-24: TPSK-LSPA1-T-PL-02092
[6 empty] | Return Date | 2018-10-24: 2019-07-23
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C16-800000 | Material Requisition For Cathodic Protection System |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IF1T; 2019-06-06: IF2T
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2020-03-18; 2019-06-06: 2020-06-28; 2019-06-06: 2020-07-20
[6 empty] | Revised Plan | 2019-06-06: 2020-06-28; 2019-06-06: 2020-07-20
[6 empty] | Issue Actual | 2018-10-24: 2019-05-24; 2018-10-24: 2019-05-24
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01735; 2018-10-24: TPSK-LSPA1-T-PL-01735
[6 empty] | Return Date | 2018-10-24: 2019-06-20; 2018-10-24: 2019-06-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C16-851000 | MATERIAL REQUISITION FOR SAFETY SUPERVISORY SYSTEM |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-03-04; 2019-06-06: 2020-01-15
[6 empty] | Revised Plan | 2019-06-06: 2020-01-15
[6 empty] | Issue Actual | 2018-10-24: 2019-03-05; 2018-10-24: 2019-03-05; 2019-06-06: 2019-08-05
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00984; 2018-10-24: TPSK-LSPA1-T-PL-00984; 2019-06-06: TPSK-LSPA1-T-PL-02309
[6 empty] | Return Date | 2018-10-24: 2019-04-05; 2018-10-24: 2019-04-05; 2019-06-06: 2019-08-14
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C16-881000 | MATERIAL REQUISITION FOR INTERCOM/PAGING/AUDIBLE ALARM SYSTEM |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-03-04; 2019-06-06: 2020-01-15
[6 empty] | Revised Plan | 2019-06-06: 2020-01-15
[6 empty] | Issue Actual | 2018-10-24: 2019-03-05; 2018-10-24: 2019-03-05; 2019-06-06: 2019-08-01
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00984; 2018-10-24: TPSK-LSPA1-T-PL-00984; 2019-06-06: TPSK-LSPA1-T-PL-02306
[6 empty] | Return Date | 2018-10-24: 2019-04-10; 2018-10-24: 2019-04-10; 2019-06-06: 2019-08-14
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C16-900000 | Material Requisition For Electrical Cables |  | Class 2 | Purpose** | 2018-10-24: IFQ
Rev. | bar: 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-07-16
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-08-05
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02328
Return Date
Owner Cmmt*
Category Code: C17 Request for Quotation (RFQ) for Instrumentation work (Engineering and Procurement)
| PL | OL1-2C17-010201 | MR for Pitot Tube |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-06-04; 2019-06-06: 2019-09-20
[6 empty] | Revised Plan | 2019-06-06: 2019-09-20
[6 empty] | Issue Actual | 2018-10-24: 2019-07-02; 2018-10-24: 2019-07-02
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02035; 2018-10-24: TPSK-LSPA1-T-PL-02035
[6 empty] | Return Date | 2018-10-24: 2019-07-17
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C17-010301 | MR For Electromagnetic Flow Meter |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-06-04; 2019-06-06: 2019-09-20
[6 empty] | Revised Plan | 2019-06-06: 2019-09-20
[6 empty] | Issue Actual | 2018-10-24: 2019-07-05; 2018-10-24: 2019-07-05
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02078; 2018-10-24: TPSK-LSPA1-T-PL-02078
[6 empty] | Return Date | 2018-10-24: 2019-07-18
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C17-010601 | MR For Mass Flow Meters Coriolis Effect |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-06-04; 2019-06-06: 2019-09-20
[6 empty] | Revised Plan | 2019-06-06: 2019-09-20
[6 empty] | Issue Actual | 2018-10-24: 2019-07-03; 2018-10-24: 2019-07-03
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02049; 2018-10-24: TPSK-LSPA1-T-PL-02049
[6 empty] | Return Date | 2018-10-24: 2019-07-17
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C17-010701 | MR For Venturi |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-06-04; 2019-06-06: 2019-09-20
[6 empty] | Revised Plan | 2019-06-06: 2019-09-20
[6 empty] | Issue Actual | 2018-10-24: 2019-07-05; 2018-10-24: 2019-07-05
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02077; 2018-10-24: TPSK-LSPA1-T-PL-02077
[6 empty] | Return Date | 2018-10-24: 2019-07-18
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C17-010801 | MR For Ultrasonic Flow Meter |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-06-04; 2019-06-06: 2019-09-20
[6 empty] | Revised Plan | 2019-06-06: 2019-09-20
[6 empty] | Issue Actual | 2018-10-24: 2019-07-09; 2018-10-24: 2019-07-09
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02093; 2018-10-24: TPSK-LSPA1-T-PL-02093
[6 empty] | Return Date | 2018-10-24: 2019-07-19
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C17-012052 | Material Requisition for Orifice Plate |  | Class 2 | Purpose** | 2018-10-24: IFQ
Rev. | bar: 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-24
[6 empty] | Issue Actual | 2018-10-24: 2019-07-24
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02244
[6 empty] | Return Date | 2018-10-24: 2019-08-15
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C17-012062 | Material Requisition for Flow Element Venturi |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-09; 2019-06-06: 2019-07-30
[6 empty] | Revised Plan | 2019-06-06: 2019-09-06
[6 empty] | Issue Actual | 2018-10-24: 2019-06-27; 2018-10-24: 2019-06-27
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02011; 2018-10-24: TPSK-LSPA1-T-PL-02011
Return Date
Owner Cmmt*
| PL | OL1-2C17-012253 | Material Requisition for Restriction Orifice |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-09; 2019-06-06: 2019-07-30
[6 empty] | Revised Plan | 2019-06-06: 2019-09-06
[6 empty] | Issue Actual | 2018-10-24: 2019-06-12; 2018-10-24: 2019-06-14
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01881; 2018-10-24: TPSK-LSPA1-T-PL-01881
[6 empty] | Return Date | 2018-10-24: 2019-07-01
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C17-014001 | MR For Vortex Meter |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-06-04; 2019-06-06: 2019-09-20
[6 empty] | Revised Plan | 2019-06-06: 2019-09-20
[6 empty] | Issue Actual | 2018-10-24: 2019-07-08; 2018-10-24: 2019-07-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02082; 2018-10-24: TPSK-LSPA1-T-PL-02082
[6 empty] | Return Date | 2018-10-24: 2019-07-18
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C17-022005 | Material Requisition for Level Gauges |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
[6 empty] | Issue Plan | 2018-10-24: 2019-03-26; 2019-06-06: 2019-06-26
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-04-17; 2018-10-24: 2019-04-18; 2019-06-06: 2019-08-15
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01393; 2018-10-24: TPSK-LSPA1-T-PL-01393; 2019-06-06: TPSK-LSPA1-T-PL-02430
[6 empty] | Return Date | 2018-10-24: 2019-05-28; 2018-10-24: 2019-05-28
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C17-022060 | Material Requisition for Magnetostrictive Level Transmitter & Magnetic Level Gauge |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-03-26; 2019-06-06: 2019-06-26
[6 empty] | Revised Plan | 2019-06-06: 2019-12-04
[6 empty] | Issue Actual | 2018-10-24: 2019-06-24; 2018-10-24: 2019-06-24
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01960; 2018-10-24: TPSK-LSPA1-T-PL-01960
[6 empty] | Return Date | 2018-10-24: 2019-07-08; 2018-10-24: 2019-07-08
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C17-022064 | Material Requisition for Guided Wave Radar Level Transmitter & Magnetic Level Gauge |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-03-26; 2019-06-06: 2019-06-26
[6 empty] | Revised Plan | 2019-06-06: 2019-12-04
[6 empty] | Issue Actual | 2018-10-24: 2019-06-21; 2018-10-24: 2019-06-21
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01949; 2018-10-24: TPSK-LSPA1-T-PL-01949
[6 empty] | Return Date | 2018-10-24: 2019-07-08; 2018-10-24: 2019-07-08
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C17-032010-ATT2 | Instrument Datasheets for Temperature Elements for Furnace Profile |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFR
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-01; 2018-10-24: 2019-05-02
[6 empty] | Issue Actual | 2018-10-24: 2019-05-01; 2018-10-24: 2019-05-02
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-IE-01542; 2018-10-24: TPSK-LSPA1-T-IE-01542
[6 empty] | Return Date | 2018-10-24: 2019-05-24; 2018-10-24: 2019-05-24
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C17-032061 | Material Requisition for Temperature Elements for Furnace Profile |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-08-27; 2019-06-06: 2019-12-03
[6 empty] | Revised Plan | 2019-06-06: 2019-12-03
[6 empty] | Issue Actual | 2018-10-24: 2019-06-25; 2018-10-24: 2019-06-25
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01977; 2018-10-24: TPSK-LSPA1-T-PL-01977
[6 empty] | Return Date | 2018-10-24: 2019-07-08; 2018-10-24: 2019-07-08
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C17-032063 | Material Requisition for Temperature Elements for Coil Outlet |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-08-27; 2019-06-06: 2019-12-03
[6 empty] | Revised Plan | 2019-06-06: 2019-12-03
[6 empty] | Issue Actual | 2018-10-24: 2019-05-23; 2018-10-24: 2019-05-24
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01732; 2018-10-24: TPSK-LSPA1-T-PL-01732
[6 empty] | Return Date | 2018-10-24: 2019-06-17; 2018-10-24: 2019-06-17
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C17-042256 | Material Requisition for Material Requisition for Pressure Indicating Transmitters & Flow Indicating D P Transmitters |  | Class 2 | Purpose** | 2018-10-24: IFQ
Rev. | bar: 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-08
[6 empty] | Issue Actual | 2018-10-24: 2019-08-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02375
Return Date
Owner Cmmt*
| PL | OL1-2C17-050101 | Material Requisition For Control Valves |  | Class 2 | Purpose** | IFQ | IFQ | IFQ | IFQ | IFP
Rev. | bar: 2018-10-24 to 2019-06-06
[6 empty] | Issue Plan | 2018-10-24: 2019-05-28; 2019-07-04: 2019-11-13
[6 empty] | Revised Plan | 2019-07-04: 2019-11-13
[6 empty] | Issue Actual | 2018-10-24: 2019-06-13; 2019-06-06: 2019-06-28; 2019-06-06: 2019-06-28
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01891; 2018-10-24: TPSK-LSPA1-T-PL-01891; 2019-06-06: TPSK-LSPA1-T-PL-02017; 2019-06-06: TPSK-LSPA1-T-PL-02017
[6 empty] | Return Date | 2019-06-06: 2019-07-10; 2019-06-06: 2019-07-10
Owner Cmmt* | bar: 2019-06-06 to 2019-06-06
| PL | OL1-2C17-050401 | Material Requisition for Special Control Valves |  | Class 2 | Purpose** | IFQ | IFQ | IFQ | IFQ | IFP
Rev. | bar: 2018-10-24 to 2019-06-06
[6 empty] | Issue Plan | 2018-10-24: 2019-05-28; 2019-07-04: 2019-11-13
[6 empty] | Revised Plan | 2019-07-04: 2019-11-13
[6 empty] | Issue Actual | 2018-10-24: 2019-06-13; 2019-06-06: 2019-07-01; 2019-06-06: 2019-07-01
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01891; 2018-10-24: TPSK-LSPA1-T-PL-01891; 2019-06-06: TPSK-LSPA1-T-PL-02022; 2019-06-06: TPSK-LSPA1-T-PL-02022
[6 empty] | Return Date | 2018-10-24: 2019-06-28; 2019-06-06: 2019-07-17
Owner Cmmt* | bar: 2018-10-24; 2019-06-06
| PL | OL1-2C17-052001 | Material Requistion for Control Valves |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-04-25; 2018-10-24: 2019-04-26
[6 empty] | Issue Actual | 2018-10-24: 2019-04-25; 2018-10-24: 2019-04-26
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01482; 2018-10-24: TPSK-LSPA1-T-PL-01482
[6 empty] | Return Date | 2018-10-24: 2019-05-28; 2018-10-24: 2019-05-28
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C17-060201 | MR For Special On Off Valves |  | Class 2 | Purpose** | 2018-10-24: IFQ
Rev. | bar: 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-05-28
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-07-25
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02255
[6 empty] | Return Date | 2018-10-24: 2019-08-07
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C17-060301 | MR For Electric Operated Valves |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-05-28; 2019-06-06: 2019-11-13
[6 empty] | Revised Plan | 2019-06-06: 2019-11-13
[6 empty] | Issue Actual | 2018-10-24: 2019-07-01; 2018-10-24: 2019-07-01
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02026; 2018-10-24: TPSK-LSPA1-T-PL-02026
[6 empty] | Return Date | 2018-10-24: 2019-07-17
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C17-060401 | Material Requisition For Pneumatic Actuators For On Off Valves |  | Class 2 | Purpose** | 2018-10-24: IFQ
Rev. | bar: 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-05-28
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-07-25
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02257
[6 empty] | Return Date | 2018-10-24: 2019-08-07
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C17-060501 | MR For Electric Pneumatic On Off Valves |  | Class 2 | Purpose** | 2018-10-24: IFQ
Rev. | bar: 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-05-28
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-07-24
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02245
[6 empty] | Return Date | 2018-10-24: 2019-08-07
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C17-070201 | Material Requisition for Safety Relief Valves & Rupture Disks |  | Class 2 | Purpose** | 2018-10-24: IFQ
Rev. | bar: 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-05-31
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-08-09
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02395
Return Date
Owner Cmmt*
| PL | OL1-2C17-072002 | Material Requisition for Pressure Relief Valves |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-04-22; 2018-10-24: 2019-04-23; 2019-06-06: 2019-08-06
[6 empty] | Issue Actual | 2018-10-24: 2019-04-22; 2018-10-24: 2019-04-23; 2019-06-06: 2019-08-06
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01427; 2018-10-24: TPSK-LSPA1-T-PL-01427; 2019-06-06: TPSK-LSPA1-T-PL-02351
[6 empty] | Return Date | 2018-10-24: 2019-05-28; 2018-10-24: 2019-05-28
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C17-101001 | Material Requisition for Integrated Control And Safety Systems - ICSS |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-06-06; 2019-06-06: 2020-06-15
[6 empty] | Revised Plan | 2019-06-06: 2020-06-15
[6 empty] | Issue Actual | 2018-10-24: 2019-06-13
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01892; 2018-10-24: TPSK-LSPA1-T-PL-01892
[6 empty] | Return Date | 2018-10-24: 2019-06-28
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C17-212051 | Material Requisition for O2 & Combustible Analyzer |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-05-23; 2019-06-06: 2019-08-26
[6 empty] | Revised Plan | 2019-06-06: 2019-11-13
[6 empty] | Issue Actual | 2018-10-24: 2019-06-25; 2018-10-24: 2019-06-25
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01979; 2018-10-24: TPSK-LSPA1-T-PL-01979
[6 empty] | Return Date | 2018-10-24: 2019-07-08; 2018-10-24: 2019-07-08
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C17-232015 | Material Requisition for pH and Conductivity Analyzer |  | Class 2 | Purpose** | IFQ | IFQ | IFQ | IFQ | IFP
Rev. | bar: 2018-10-24 to 2019-06-06
[6 empty] | Issue Plan | 2018-10-24: 2019-08-27; 2019-07-04: 2019-12-03
[6 empty] | Revised Plan | 2019-07-04: 2019-12-03
[6 empty] | Issue Actual | 2018-10-24: 2019-05-24; 2018-10-24: 2019-05-27; 2019-06-06: 2019-06-21; 2019-06-06: 2019-06-21
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01744; 2018-10-24: TPSK-LSPA1-T-PL-01744; 2019-06-06: TPSK-LSPA1-T-PL-01950; 2019-06-06: TPSK-LSPA1-T-PL-01950
[6 empty] | Return Date | 2018-10-24: 2019-06-17; 2018-10-24: 2019-06-17; 2019-06-06: 2019-07-08; 2019-06-06: 2019-07-08
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C17-290000 | Material Requisition for Analyzer Houses Package |  | Class 2 | Purpose** | 2018-10-24: IFQ
Rev. | bar: 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-04-30
Revised Plan
[6 empty] | Issue Actual | 2018-10-24: 2019-07-31
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02285
Return Date
Owner Cmmt*
| PL | OL1-2C17-330101 | Material Requisition for Machine Monitoring System - MMS |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ; 2019-06-06: IFP
Rev. | bar: 2018-10-24 to 2018-10-24
[6 empty] | Issue Plan | 2018-10-24: 2019-06-21; 2019-06-06: 2020-06-30
[6 empty] | Revised Plan | 2019-06-06: 2020-06-30
[6 empty] | Issue Actual | 2018-10-24: 2019-07-15; 2018-10-24: 2019-07-15
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02149; 2018-10-24: TPSK-LSPA1-T-PL-02149
[6 empty] | Return Date | 2018-10-24: 2019-07-30
Owner Cmmt* | bar: 2018-10-24
Category Code: C18 Request for Quotation (RFQ) for Chemicals (Engineering and Procurement)
| PL | OL1-2C18-263000 | Material Requisition For Molecular And HG Sieves |  | Class 2 | Purpose** | 2018-10-24: IMP; 2018-10-24: IMP; 2019-06-06: IFQ
Rev. | bar: 2018-10-24 to 2019-06-06
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-03-15; 2018-10-24: 2019-03-18; 2019-06-06: 2019-07-22
[6 empty] | Issue Actual | 2018-10-24: 2019-03-15; 2018-10-24: 2019-03-18; 2019-06-06: 2019-07-22
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01076; 2018-10-24: TPSK-LSPA1-T-PL-01076; 2019-06-06: TPSK-LSPA1-T-PL-02196
[6 empty] | Return Date | 2018-10-24: 2019-04-01; 2018-10-24: 2019-04-01
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C18-264000 | Material Requisition For Adsorbents |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-04-10; 2018-10-24: 2019-04-11
[6 empty] | Issue Actual | 2018-10-24: 2019-04-10; 2018-10-24: 2019-04-11
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01295; 2018-10-24: TPSK-LSPA1-T-PL-01295
Return Date
Owner Cmmt*
| PL | OL1-2C18-265000 | Material Requisition For Molecular Sieves |  | Class 2 | Purpose** | 2018-10-24: IMP; 2018-10-24: IMP; 2019-06-06: CAN
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: A; 2019-06-06: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-03-15; 2018-10-24: 2019-03-18; 2019-06-06: 2019-07-19
[6 empty] | Issue Actual | 2018-10-24: 2019-03-15; 2018-10-24: 2019-03-18; 2019-06-06: 2019-07-19
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01077; 2018-10-24: TPSK-LSPA1-T-PL-01077; 2019-06-06: TPSK-LSPA1-T-PL-02186
[6 empty] | Return Date | 2018-10-24: 2019-04-01; 2018-10-24: 2019-04-01
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C18-266000 | Material Requisition For Adsorbents |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-04-10; 2018-10-24: 2019-04-11
[6 empty] | Issue Actual | 2018-10-24: 2019-04-10; 2018-10-24: 2019-04-11
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01299; 2018-10-24: TPSK-LSPA1-T-PL-01299
Return Date
Owner Cmmt*
| PL | OL1-2C18-267000 | Material Requisition For Hg Sieves |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-04-10; 2018-10-24: 2019-04-11
[6 empty] | Issue Actual | 2018-10-24: 2019-04-10; 2018-10-24: 2019-04-11
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01296; 2018-10-24: TPSK-LSPA1-T-PL-01296
Return Date
Owner Cmmt*
| PL | OL1-2C18-268000 | Material Requisition For Support Balls |  | Class 2 | Purpose** | 2018-10-24: IFQ; 2018-10-24: IFQ
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-04-10; 2018-10-24: 2019-04-11
[6 empty] | Issue Actual | 2018-10-24: 2019-04-10; 2018-10-24: 2019-04-11
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01297; 2018-10-24: TPSK-LSPA1-T-PL-01297
Return Date
Owner Cmmt*
Category Code: C20 Technical Bid Evaluation for Civil work (Engineering and Procurement)
Category Code: C21 Technical Bid Evaluation for Building work (Engineering and Procurement)
Category Code: C22 Technical Bid Evaluation for Steel Structure work (Engineering and Procurement)
Category Code: C23 Technical Bid Evaluation for Mechanical work (Engineering and Procurement)
| PL | OL1-2C23-0008 | Technical Bid Evaluation For Centrifugal Compressor Steam Turbine Driven |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-03-01; 2018-10-24: 2019-03-01
[6 empty] | Issue Actual | 2018-10-24: 2019-03-01; 2018-10-24: 2019-03-01
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00947; 2018-10-24: TPSK-LSPA1-T-PL-00947
Return Date
Owner Cmmt*
| PL | OL1-2C23-0012 | Technical Bid Evaluation For Residue Gas Expander - Recompressor |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI; 2019-06-06: IFI; 2019-06-06: IFI
[6 empty] | Rev. | 2018-10-24: 1; 2018-10-24: 1; 2019-06-06: 2; 2019-06-06: 2
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-01-29; 2019-06-06: 2019-03-15; 2019-06-06: 2019-03-15
[6 empty] | Issue Actual | 2018-10-24: 2019-01-29; 2019-06-06: 2019-03-15; 2019-06-06: 2019-03-15
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00747; 2018-10-24: TPSK-LSPA1-T-PL-00747; 2019-06-06: TPSL-LSPA1-T-PL-01057; 2019-06-06: TPSL-LSPA1-T-PL-01057
Return Date
Owner Cmmt*
| PL | OL1-2C23-0014 | Technical Bid Evaluation For Integrally Geared Decoking Air Compressors |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-08
[6 empty] | Issue Actual | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01595; 2018-10-24: TPSK-LSPA1-T-PL-01595
[6 empty] | Return Date | 2018-10-24: 2019-05-26; 2018-10-24: 2019-05-26
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C23-2009 | Technical Bid Tabulation For Elevator |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-19
[6 empty] | Issue Actual | 2018-10-24: 2019-07-19
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02190
Return Date
Owner Cmmt*
| PL | OL1-2C23-2011 | Technical Bid Tabulation For Attemperators |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-24; 2018-10-24: 2019-05-24
[6 empty] | Issue Actual | 2018-10-24: 2019-05-24; 2018-10-24: 2019-05-24
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01734; 2018-10-24: TPSK-LSPA1-T-PL-01734
[6 empty] | Return Date | 2018-10-24: 2019-06-21; 2018-10-24: 2019-06-21
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C23-2013 | Technical Bid Tabulation for Radiant Refractory |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-08
[6 empty] | Issue Actual | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-01608; 2018-10-24: TPSK-LSPA1-T-ME-01608
[6 empty] | Return Date | 2018-10-24: 2019-07-15; 2018-10-24: 2019-07-15
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C23-2014 | Technical Bid Tabulation for Radiant Steel Panel |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-15; 2018-10-24: 2019-05-15
[6 empty] | Issue Actual | 2018-10-24: 2019-05-15; 2018-10-24: 2019-05-15
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01649; 2018-10-24: TPSK-LSPA1-T-PL-01649
[6 empty] | Return Date | 2018-10-24: 2019-06-19; 2018-10-24: 2019-06-19
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C23-2202 | Technical Bid Tabulation For Pressure Relief Valves |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-24
[6 empty] | Issue Actual | 2018-10-24: 2019-07-24
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02243
[6 empty] | Return Date | 2018-10-24: 2019-08-15
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C23-2203 | Technical Bid Tabulation for Restriction Orifice |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-01
[6 empty] | Issue Actual | 2018-10-24: 2019-08-01
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02305
[6 empty] | Return Date | 2018-10-24: 2019-08-16
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C23-281000 | Technical Bid Tabulation for Convection Tubes Finnings |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-03-14; 2018-10-24: 2019-03-14
[6 empty] | Issue Actual | 2018-10-24: 2019-03-14; 2018-10-24: 2019-03-14
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01048; 2018-10-24: TPSK-LSPA1-T-PL-01048
Return Date
Owner Cmmt*
| PL | OL1-2C23-282000 | Technical Bid Tabulation for Convection Fabrication |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-23; 2018-10-24: 2019-05-23
[6 empty] | Issue Actual | 2018-10-24: 2019-05-23; 2018-10-24: 2019-05-23
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01719; 2018-10-24: TPSK-LSPA1-T-PL-01719
[6 empty] | Return Date | 2018-10-24: 2019-06-19; 2018-10-24: 2019-06-19
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C23-28500 | Technical Bid Tabulation for MOVs |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-03-15; 2018-10-24: 2019-03-15
[6 empty] | Issue Actual | 2018-10-24: 2019-03-15; 2018-10-24: 2019-03-15
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01053; 2018-10-24: TPSK-LSPA1-T-PL-01053
Return Date
Owner Cmmt*
| PL | OL1-2C23-301000 | Technical Bid Tabulation for Furnace ID Fans |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-03-05; 2018-10-24: 2019-03-05
[6 empty] | Issue Actual | 2018-10-24: 2019-03-05; 2018-10-24: 2019-03-05
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PC-00979; 2018-10-24: TPSK-LSPA1-T-PC-00979
Return Date
Owner Cmmt*
| PL | OL1-2C23-440003 | Technical Bid Evaluation Report for Cooling Water Pumps |  | Class 2 | Purpose** | 2018-10-24: IFA; 2018-10-24: IFA
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-06-11; 2018-10-24: 2019-06-11
[6 empty] | Issue Actual | 2018-10-24: 2019-06-11; 2018-10-24: 2019-06-11
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01855; 2018-10-24: TPSK-LSPA1-T-PL-01855
[6 empty] | Return Date | 2018-10-24: 2019-06-27; 2018-10-24: 2019-06-27
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
Category Code: C24 Technical Bid Evaluation for Piping work (Engineering and Procurement)
Category Code: C25 Technical Bid Evaluation for Fire Fighting work (Engineering and Procurement)
Category Code: C26 Technical Bid Evaluation for Electrical and HVAC work (Engineering and Procurement)
Category Code: C27 Technical Bid Evaluation for Instrumentation work (Engineering and Procurement)
| PL | OL1-2C27-2201 | Technical Bid Tabulation For Control Valves |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-11
[6 empty] | Issue Actual | 2018-10-24: 2019-07-11
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02100
Return Date
Owner Cmmt*
| PL | OL1-2C27-2206 | Technical Bid Tabulation for Steam Drum Level Gauges |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-08
[6 empty] | Issue Actual | 2018-10-24: 2019-08-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02373
Return Date
Owner Cmmt*
| PL | OL1-2C27-2218 | Technical Bid Tabulation for Magnetostrictive Transmitter Magnetic Gauges |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-08
[6 empty] | Issue Actual | 2018-10-24: 2019-08-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02376
Return Date
Owner Cmmt*
Category Code: C28 Technical Bid Evaluation for Chemicals (Engineering and Procurement)
Category Code: C30 Scope of Supply (SR) for Mechanical Work
Category Code: C31 Scope of Supply (SR) for Piping Work
Category Code: C32 Scope of Supply (SR) for Electrical work
Category Code: C33 Scope of Supply (SR) for Instrumentation work
Category Code: C34 Scope of Supply (SR) for Civil,Structure and Architecture.
Category Code: C35 Extend of Supply (SP) Mechanical Work
Category Code: C36 Extend of Supply (SP) for Piping Work
Category Code: C37 Extend of Supply (SP) for Electrical work
Category Code: C38 Extend of Supply (SP) for Instrumentation work
Category Code: C39 Extend of Supply (SP) for Civil,Structure and Architecture
Category Code: C40 Deviation List (DL) for Mechanical Work
| ME | OL1-2C40-140000 | Deviation List for Quench Exchangers |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFR
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-04-26; 2018-10-24: 2019-04-29
[6 empty] | Issue Actual | 2018-10-24: 2019-04-26; 2018-10-24: 2019-04-29
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-01496; 2018-10-24: TPSK-LSPA1-T-ME-01496
[6 empty] | Return Date | 2018-10-24: 2019-05-24; 2018-10-24: 2019-05-24
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C40-244000 | Deviation List For Trays For Columns (C4 Unit) |  | Class 2 | Purpose** | 2018-10-24: IFR
Rev. | bar: 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-15
[6 empty] | Issue Actual | 2018-10-24: 2019-08-15
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02432
Return Date
Owner Cmmt*
| PL | OL1-2C40-281000 | Deviation List for Furnace Convection Finnings |  | Class 2 | Purpose** | 2018-10-24: IFP; 2018-10-24: IFP
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-03-14; 2018-10-24: 2019-03-15
[6 empty] | Issue Actual | 2018-10-24: 2019-03-14; 2018-10-24: 2019-03-15
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01056; 2018-10-24: TPSK-LSPA1-T-PL-01056
[6 empty] | Return Date | 2018-10-24: 2019-06-07; 2018-10-24: 2019-06-07
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C40-282000 | Deviation List for Convection Fabrication |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFR; 2019-06-06: IFR; 2019-06-06: IFR
Rev. | bar: 2018-10-24 to 2019-06-06
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-22; 2018-10-24: 2019-05-23; 2019-06-06: 2019-05-30; 2019-06-06: 2019-05-31
[6 empty] | Issue Actual | 2018-10-24: 2019-05-22; 2018-10-24: 2019-05-23; 2019-06-06: 2019-05-30; 2019-06-06: 2019-05-31
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01718; 2018-10-24: TPSK-LSPA1-T-PL-01718; 2019-06-06: TPSK-LSPA1-T-PL-01772; 2019-06-06: TPSK-LSPA1-T-PL-01772
[6 empty] | Return Date | 2018-10-24: 2019-06-19; 2018-10-24: 2019-06-19
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C40-284000 | Deviation List for Peep Doors |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFR; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: B; 2018-10-24: B; 2019-06-06: 0; 2019-06-06: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-02-06; 2018-10-24: 2019-02-06; 2019-06-06: 2019-04-17; 2019-06-06: 2019-04-18
[6 empty] | Issue Actual | 2018-10-24: 2019-02-06; 2018-10-24: 2019-02-06; 2019-06-06: 2019-04-17; 2019-06-06: 2019-04-18
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-00812; 2018-10-24: TPSK-LSPA1-T-ME-00812; 2019-06-06: TPSK-LSPA1-T-ME-01400; 2019-06-06: TPSK-LSPA1-T-ME-01400
[6 empty] | Return Date | 2018-10-24: 2019-02-21; 2018-10-24: 2019-02-21; 2019-06-06: 2019-05-28; 2019-06-06: 2019-05-28
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C40-285000 | Deviation List for MOVs |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFR
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-03-14; 2018-10-24: 2019-03-15
[6 empty] | Issue Actual | 2018-10-24: 2019-03-14; 2018-10-24: 2019-03-15
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01050; 2018-10-24: TPSK-LSPA1-T-PL-01050
Return Date
Owner Cmmt*
| PL | OL1-2C40-286000 | Deviation List for Attemperators |  | Class 2 | Purpose** | 2018-10-24: IFP; 2018-10-24: IFP
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-23; 2018-10-24: 2019-05-24
[6 empty] | Issue Actual | 2018-10-24: 2019-05-23; 2018-10-24: 2019-05-24
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01733; 2018-10-24: TPSK-LSPA1-T-PL-01733
[6 empty] | Return Date | 2018-10-24: 2019-06-19; 2018-10-24: 2019-06-19
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C40-300000 | Deviation List for Radiant Coil |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFR
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-04-24; 2018-10-24: 2019-04-25
[6 empty] | Issue Actual | 2018-10-24: 2019-04-24; 2018-10-24: 2019-04-25
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01473; 2018-10-24: TPSK-LSPA1-T-PL-01473
[6 empty] | Return Date | 2018-10-24: 2019-05-28; 2018-10-24: 2019-05-28
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C40-301000 | Deviation List for Furnace ID Fans |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFR
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-03-04; 2018-10-24: 2019-03-05
[6 empty] | Issue Actual | 2018-10-24: 2019-03-04; 2018-10-24: 2019-03-05
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00978; 2018-10-24: TPSK-LSPA1-T-PL-00978
Return Date
Owner Cmmt*
| PL | OL1-2C40-305000 | Deviation List for Furnace Steam Drums |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFR
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-06-25; 2018-10-24: 2019-06-25
[6 empty] | Issue Actual | 2018-10-24: 2019-06-25; 2018-10-24: 2019-06-25
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01974; 2018-10-24: TPSK-LSPA1-T-PL-01974
[6 empty] | Return Date | 2018-10-24: 2019-07-08; 2018-10-24: 2019-07-08
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| ME | OL1-2C40-306000 | Deviation List for Furnace Buners |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFR
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-02-01; 2018-10-24: 2019-02-04
[6 empty] | Issue Actual | 2018-10-24: 2019-02-01; 2018-10-24: 2019-02-04
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-ME-00790; 2018-10-24: TPSK-LSPA1-T-ME-00790
Return Date
Owner Cmmt*
| PL | OL1-2C40-307000 | Deviation List for Radiant Steel Panel |  | Class 2 | Purpose** | 2018-10-24: IFP; 2018-10-24: IFP
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-15; 2018-10-24: 2019-05-16
[6 empty] | Issue Actual | 2018-10-24: 2019-05-15; 2018-10-24: 2019-05-16
[6 empty] | Transmittal no. | 2018-10-24: LSPA1-TPSK-T-PL-01668; 2018-10-24: LSPA1-TPSK-T-PL-01668
Return Date
Owner Cmmt*
| PL | OL1-2C40-311000 | Deviation List for Cooling Tower |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFR
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-03-08; 2018-10-24: 2019-03-08
[6 empty] | Issue Actual | 2018-10-24: 2019-03-08; 2018-10-24: 2019-03-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00879; 2018-10-24: TPSK-LSPA1-T-PL-00879
[6 empty] | Return Date | 2018-10-24: 2019-06-20; 2018-10-24: 2019-06-20
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C40-403000 | Deviation List for Recycle Gas Compressor |  | Class 2 | Purpose** | IFA | IFA | IFA | IFA | IFA | IFA
[6 empty] | Rev. | B | B | C | C | D | D
Issue Plan
[6 empty] | Revised Plan | 2019-05-27 | 2019-05-28 | 2019-06-20 | 2019-06-20 | 2019-07-10 | 2019-07-10
[6 empty] | Issue Actual | 2019-05-27 | 2019-05-28 | 2019-06-20 | 2019-06-20 | 2019-07-10 | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01745 | TPSK-LSPA1-T-PL-01745 | TPSK-LSPA1-T-PL-01942 | TPSK-LSPA1-T-PL-01942 | TPSK-LSPA1-T-PL-02104 | TPSK-LSPA1-T-PL-02104
[6 empty] | Return Date | 2018-10-24: 2019-06-11; 2018-10-24: 2019-06-11
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C40-440003 | Deviation List for Cooling Water Pumps |  | Class 2 | Purpose** | 2018-10-24: IFA; 2018-10-24: IFA; 2019-06-06: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: B; 2018-10-24: B; 2019-06-06: 0; 2019-06-06: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-07; 2018-10-24: 2019-05-08; 2019-06-06: 2019-07-10; 2019-06-06: 2019-07-10
[6 empty] | Issue Actual | 2018-10-24: 2019-05-07; 2018-10-24: 2019-05-08; 2019-06-06: 2019-07-10; 2019-06-06: 2019-07-10
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01591; 2018-10-24: TPSK-LSPA1-T-PL-01591; 2019-06-06: TPSK-LSPA1-T-PL-02114; 2019-06-06: TPSK-LSPA1-T-PL-02114
Return Date
Owner Cmmt*
| PL | OL1-2C40-701000 | Deviation List for Condensate Polisher Package |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFR
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-06-20; 2018-10-24: 2019-06-20
[6 empty] | Issue Actual | 2018-10-24: 2019-06-20; 2018-10-24: 2019-06-20
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01922; 2018-10-24: TPSK-LSPA1-T-PL-01922
[6 empty] | Return Date | 2018-10-24: 2019-07-01; 2018-10-24: 2019-07-01
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C40-702000 | Deviation List For Complex Waste Water Treatment Package |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFR
Rev. | bar: 2018-10-24 to 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-15; 2018-10-24: 2019-07-15
[6 empty] | Issue Actual | 2018-10-24: 2019-07-15; 2018-10-24: 2019-07-15
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02127; 2018-10-24: TPSK-LSPA1-T-PL-02127
[6 empty] | Return Date | 2018-10-24: 2019-07-30
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C40-704000 | Deviation List for Wet Air Oxidation Package |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IFP | IFP
[6 empty] | Rev. | B | B | C | C | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2019-04-08 | 2019-04-08 | 2019-05-08 | 2019-05-09 | 2019-06-20 | 2019-06-20
[6 empty] | Issue Actual | 2019-04-08 | 2019-04-08 | 2019-05-08 | 2019-05-09 | 2019-06-20 | 2019-06-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01269 | TPSK-LSPA1-T-PL-01269 | TPSK-LSPA1-T-PL-01611 | TPSK-LSPA1-T-PL-01611 | TPSK-LSPA1-T-PL-01943 | TPSK-LSPA1-T-PL-01943
[6 empty] | Return Date | 2019-06-19 | 2019-06-19 | 2019-06-16 | 2019-06-16 | 2019-07-11 | 2019-07-11
Owner Cmmt* | bar: 2018-10-24 to 2019-07-04
| PL | OL1-2C40-708000 | Deviation List for HP/Polyolefins Flare Package |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFR; 2019-06-06: IFR; 2019-06-06: IFR
Rev. | bar: 2018-10-24 to 2019-06-06
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-21; 2018-10-24: 2019-05-21; 2019-06-06: 2019-06-25; 2019-06-06: 2019-06-25
[6 empty] | Issue Actual | 2018-10-24: 2019-05-21; 2018-10-24: 2019-05-21; 2019-06-06: 2019-06-25; 2019-06-06: 2019-06-25
[6 empty] | Transmittal no. | 2018-10-24: LSPA1-TPSK-T-PL-01705; 2018-10-24: LSPA1-TPSK-T-PL-01705; 2019-06-06: TPSK-LSPA1-T-PL-01968; 2019-06-06: TPSK-LSPA1-T-PL-01968
[6 empty] | Return Date | 2018-10-24: 2019-06-18; 2018-10-24: 2019-06-18; 2019-06-06: 2019-07-11; 2019-06-06: 2019-07-11
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C40-709000 | Deviation List For Furnace Elevator |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFR; 2019-06-06: IFR
Rev. | bar: 2018-10-24 to 2019-06-06
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-08; 2018-10-24: 2019-07-08; 2019-06-06: 2019-07-19
[6 empty] | Issue Actual | 2018-10-24: 2019-07-08; 2018-10-24: 2019-07-08; 2019-06-06: 2019-07-19
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02084; 2018-10-24: TPSK-LSPA1-T-PL-02084; 2019-06-06: TPSK-LSPA1-T-PL-02191
[6 empty] | Return Date | 2018-10-24: 2019-07-18; 2019-06-06: 2019-08-07
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
Category Code: C41 Deviation List (DL) for Piping Work
Category Code: C42 Deviation List (DL) for Electrical work
| PL | OL1-2C42-851000 | Deviation List For Safety Supervisory System |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFP
[6 empty] | Rev. | 2018-10-24: B; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-19; 2018-10-24: 2019-08-01
[6 empty] | Issue Actual | 2018-10-24: 2019-07-19; 2018-10-24: 2019-08-01
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02180; 2018-10-24: TPSK-LSPA1-T-PL-02300
[6 empty] | Return Date | 2018-10-24: 2019-07-30; 2018-10-24: 2019-08-14
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C42-881000 | Attachment 4 Deviation List For Intercom/Paging/Audible Alarm System |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IFP; 2019-06-06: IFP
[6 empty] | Rev. | 2018-10-24: B; 2018-10-24: 0; 2019-06-06: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-06-11; 2018-10-24: 2019-07-01; 2019-06-06: 2019-07-01
[6 empty] | Issue Actual | 2018-10-24: 2019-06-11; 2018-10-24: 2019-07-01; 2019-06-06: 2019-07-01
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01859; 2018-10-24: TPSK-LSPA1-T-PL-02032; 2019-06-06: TPSK-LSPA1-T-PL-02032
[6 empty] | Return Date | 2018-10-24: 2019-06-24; 2018-10-24: 2019-07-08; 2019-06-06: 2019-07-08
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
Category Code: C43 Deviation List (DL) for Instrumentation work
Category Code: C44 Deviation List (DL) for Civil,Structure and Architecture
Category Code: C50 Purchase Order (PO) for Civil work, Building work, Steel Structure work
Category Code: C51 Purchase Order (PO) for Mechanical work
| PL | OL1-2C51-0001 | Vendor s Acknowledgment of Purchase Order For Wieland Tubes -Sole Source - MR 0610-0001 Rev 0 |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-09
[6 empty] | Issue Actual | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-09
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01613; 2018-10-24: TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2018-10-24: 2019-05-22; 2018-10-24: 2019-05-22
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C51-0002 | Vendor s Acknowledgment of Purchase Order For Residue Gas Expander Recompressor – MR 1130-0001 Rev 0 |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-04-11; 2018-10-24: 2019-05-08
[6 empty] | Issue Actual | 2018-10-24: 2019-04-11; 2018-10-24: 2019-05-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01613; 2018-10-24: TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2018-10-24: 2019-05-22; 2018-10-24: 2019-05-22
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C51-0003 | Vendor s Acknowledgment of Purchase Order For Steam Turbine Drive Centrifugal Compressor – MR 1011-0001 Rev 0 |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-09
[6 empty] | Issue Actual | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-09
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01613; 2018-10-24: TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2018-10-24: 2019-05-22; 2018-10-24: 2019-05-22
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C51-0004 | Vendor s Acknowledgment of Purchase Order For Centrifugal Compressor Steam Turbine Driven Site Services |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-09
[6 empty] | Issue Actual | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-09
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01613; 2018-10-24: TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2018-10-24: 2019-05-22; 2018-10-24: 2019-05-22
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C51-0005 | Vendor s Acknowledgment of Purchase Order For Deareator MR-0845-0001 |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-09
[6 empty] | Issue Actual | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-09
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01613; 2018-10-24: TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2018-10-24: 2019-05-22; 2018-10-24: 2019-05-22
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C51-0006 | Vendor s Acknowledgment of Purchase Order For Plate And Frame Heat Exchangers – MR 0661-0001 Rev 0 |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-09
[6 empty] | Issue Actual | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-09
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01613; 2018-10-24: TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2018-10-24: 2019-05-22; 2018-10-24: 2019-05-22
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C51-0007 | Vendor s Acknowledgment of Purchase Order For Trays For Columns – MR 0570-0001 Rev 0 |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-21; 2018-10-24: 2019-05-23
[6 empty] | Issue Actual | 2018-10-24: 2019-05-21; 2018-10-24: 2019-05-23
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01707; 2018-10-24: TPSK-LSPA1-T-PL-01707
[6 empty] | Return Date | 2018-10-24: 2019-05-30; 2018-10-24: 2019-05-30
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C51-0008 | Vendor s Acknowledgment of Purchase Order For Cold Box And Core Exchangers – MR 0662-0002 Rev 0 |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-09
[6 empty] | Issue Actual | 2018-10-24: 2019-05-08; 2018-10-24: 2019-05-09
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01613; 2018-10-24: TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2018-10-24: 2019-05-22; 2018-10-24: 2019-05-22
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C51-0009 | Vendor s Acknowledgment of Purchase Order For Trays For Shop Assembled Large Columns – MR 0511-0001 Rev 0 |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-21; 2018-10-24: 2019-05-23
[6 empty] | Issue Actual | 2018-10-24: 2019-05-21; 2018-10-24: 2019-05-23
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01707; 2018-10-24: TPSK-LSPA1-T-PL-01707
[6 empty] | Return Date | 2018-10-24: 2019-05-30; 2018-10-24: 2019-05-30
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C51-0010 | Vendor s Acknowledgment of Purchase Order For Cold Box And Core Exchangers Rev. 0 – MR 0662-0002 Rev 1 |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-05; 2018-10-24: 2019-07-05
[6 empty] | Issue Actual | 2018-10-24: 2019-07-05; 2018-10-24: 2019-07-05
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02073; 2018-10-24: TPSK-LSPA1-T-PL-02073
[6 empty] | Return Date | 2018-10-24: 2019-07-16; 2018-10-24: 2019-07-16
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C51-0011 | Vendor s Acknowledgment of Purchase Order For Integrally Geared Decoking Air Compressor Rev 1 – MR 1013-0001 Rev 0 |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-05; 2018-10-24: 2019-07-05
[6 empty] | Issue Actual | 2018-10-24: 2019-07-05; 2018-10-24: 2019-07-05
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02074; 2018-10-24: TPSK-LSPA1-T-PL-02074
[6 empty] | Return Date | 2018-10-24: 2019-07-16; 2018-10-24: 2019-07-16
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C51-0012 | Vendor s Acknowledgment of Purchase Order For Hydrogen Production Unit - MR 4111-0001 Rev 0 |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-05; 2018-10-24: 2019-07-05
[6 empty] | Issue Actual | 2018-10-24: 2019-07-05; 2018-10-24: 2019-07-05
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02076; 2018-10-24: TPSK-LSPA1-T-PL-02076
[6 empty] | Return Date | 2018-10-24: 2019-07-16; 2018-10-24: 2019-07-16
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C51-0013 | Vendor s Acknowledgment of Purchase Order For Steam Turbine Drive Centrifugal Compressor Rev 1 – MR 1011-0001 Rev 1 |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-05; 2018-10-24: 2019-07-05
[6 empty] | Issue Actual | 2018-10-24: 2019-07-05; 2018-10-24: 2019-07-05
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02076; 2018-10-24: TPSK-LSPA1-T-PL-02076
[6 empty] | Return Date | 2018-10-24: 2019-07-16; 2018-10-24: 2019-07-16
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C51-0014 | Vendor s Acknowledgment of Purchase Order For Centrifugal Compressor Steam Turbine Driven Site Services Rev 1 |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-05; 2018-10-24: 2019-07-05
[6 empty] | Issue Actual | 2018-10-24: 2019-07-05; 2018-10-24: 2019-07-05
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02076; 2018-10-24: TPSK-LSPA1-T-PL-02076
[6 empty] | Return Date | 2018-10-24: 2019-07-16; 2018-10-24: 2019-07-16
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C51-0015 | Vendor s Acknowledgment of Purchase Order For Reactors and Thicker Vessels Rev. 0 MR-0411-0001 Rev. 0 |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-17
[6 empty] | Issue Actual | 2018-10-24: 2019-07-17
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02159
[6 empty] | Return Date | 2018-10-24: 2019-07-31
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C51-0016 | Vendor s Acknowledgment of Purchase Order For Residue Gas Expander Recompressor Amd 1 – MR 1130-0001 Rev 1 |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-19
[6 empty] | Issue Actual | 2018-10-24: 2019-07-19
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02187
[6 empty] | Return Date | 2018-10-24: 2019-07-31
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C51-0101 | Purchase Order for MR-4234-0001 - Side Stream Filter |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-04-17; 2018-10-24: 2019-06-10
[6 empty] | Issue Actual | 2018-10-24: 2019-04-17; 2018-10-24: 2019-06-10
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01385; 2018-10-24: TPSK-LSPA1-T-PL-01385
Return Date
Owner Cmmt*
| PL | OL1-2C51-0102 | Purchase Order for MR-0310-0001 - Cooling Tower |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-06-10; 2018-10-24: 2019-06-10
[6 empty] | Issue Actual | 2018-10-24: 2019-06-10; 2018-10-24: 2019-06-10
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01842; 2018-10-24: TPSK-LSPA1-T-PL-01842
[6 empty] | Return Date | 2018-10-24: 2019-06-28
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C51-0103 | Vendor s Acknowledgment of Purchase Order For Wet Air Oxidation - MR 4100-0001 Rev. 0 |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-06-11; 2018-10-24: 2019-06-11
[6 empty] | Issue Actual | 2018-10-24: 2019-06-11; 2018-10-24: 2019-06-11
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01856; 2018-10-24: TPSK-LSPA1-T-PL-01856
[6 empty] | Return Date | 2018-10-24: 2019-06-28
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C51-0104 | Vendor Acknowledgment of Purchase Order for HP / Polyolefins Flare Package |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-07-11
[6 empty] | Issue Actual | 2018-10-24: 2019-07-11
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02126
Return Date
Owner Cmmt*
| PL | OL1-2C51-0105 | Vendor’s Acknowledgment of Purchase Order For Packings for Columns (C4 Unit) - MR-0580-0001 Rev. 0 |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-08
[6 empty] | Issue Actual | 2018-10-24: 2019-08-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02368
Return Date
Owner Cmmt*
| PL | OL1-2C51-0108 | Vendor s Acknowledgment of Purchase Order For Shell & Tube Heat Exchangers (Lot-1) |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-07
[6 empty] | Issue Actual | 2018-10-24: 2019-08-07
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02355
Return Date
Owner Cmmt*
| PL | OL1-2C51-0109 | Vendor s Acknowledgment of Purchase Order For Recycle Gas Compressor – MR 1031-0001 Rev 0 |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-07
[6 empty] | Issue Actual | 2018-10-24: 2019-08-07
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02355
Return Date
Owner Cmmt*
| ME | OL1-2C51-0110 | Vendor s Acknowledgment of Purchase Order For Shell & Tube Heat Exchangers Lot-3 – MR 0610-0004 Rev 0 |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-07
[6 empty] | Issue Actual | 2018-10-24: 2019-08-07
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02355
Return Date
Owner Cmmt*
| PL | OL1-2C51-0113 | Vendor s Acknowledgment of Purchase Order For Cooling Water Pumps – MR 0910-0003 Rev 0 |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-07
[6 empty] | Issue Actual | 2018-10-24: 2019-08-07
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02355
Return Date
Owner Cmmt*
| PL | OL1-2C51-0201 | Vendors Acknowledgment of Purchase Order for Quench System - Includes TLEs |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-08
[6 empty] | Issue Actual | 2018-10-24: 2019-08-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
| PL | OL1-2C51-0202 | Vendors Acknowledgment of Purchase Order for Convection Section Tubes - Tubes for Convection Modules |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-08
[6 empty] | Issue Actual | 2018-10-24: 2019-08-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
| PL | OL1-2C51-0203 | Vendors Acknowledgment of Purchase Order for Cast Tube Supports - Support for Convection Modules |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-08
[6 empty] | Issue Actual | 2018-10-24: 2019-08-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
| PL | OL1-2C51-0204 | Vendors Acknowledgment of Purchase Order for Radiant Coils |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-08
[6 empty] | Issue Actual | 2018-10-24: 2019-08-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
| PL | OL1-2C51-0205 | Vendors Acknowledgment of Purchase Order for Convection Section Fitting - Fittings for Convection Modules |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-08
[6 empty] | Issue Actual | 2018-10-24: 2019-08-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
| PL | OL1-2C51-0206 | Vendors Acknowledgment of Purchase Order for Convection Boxes & Finning - Fabrication of Convection Modules |  | Class 2 | Purpose** | 2018-10-24: IFI
[6 empty] | Rev. | 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-08-08
[6 empty] | Issue Actual | 2018-10-24: 2019-08-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
Category Code: C52 Purchase Order (PO) for Piping work
Category Code: C53 Purchase Order (PO) for Fire Fighting work
Category Code: C54 Purchase Order (PO) for Electrical and HVAC work
Category Code: C55 Purchase Order (PO) for Instrumentation work
Category Code: C56 Purchase Order (PO) for Chemicals
Category Code: C71 Appraisal Report for Consultancy Service
Category Code: C72 Appraisal Report for EPC Contractor Work
Category Code: C73 Appraisal Report for Vendor/Supplier
Category Code: C91 Index/List
| PL | OL1-2C91-0004 | Sub Vendor List For Mechanical Packages |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI; 2019-06-06: IFI
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 0; 2019-06-06: 1
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2019-05-10; 2018-10-24: 2019-05-13; 2019-06-06: 2019-07-29
[6 empty] | Issue Actual | 2018-10-24: 2019-05-10; 2018-10-24: 2019-05-13; 2019-06-06: 2019-07-29
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LPSA1-T-PL-01633; 2018-10-24: TPSK-LPSA1-T-PL-01633; 2019-06-06: TPSK-LSPA1-T-PL-02271
[6 empty] | Return Date | 2018-10-24: 2019-06-20; 2018-10-24: 2019-06-20; 2019-06-06: 2019-08-14
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
Category Code: C92 Procedures & Standards
| PC | OL1-2C92-0001 | Project Procurement Execution Plan |  | Class 2 | Purpose** | 2018-10-24: IFR
Rev. | bar: 2018-10-24
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2018-09-14
[6 empty] | Issue Actual | 2018-10-24: 2018-09-14
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PC-00051
[6 empty] | Return Date | 2018-10-24: 2018-11-29
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C92-0002 | Project QCS Coordination Procedure |  | Class 2 | Purpose** | 2018-10-24: IMP; 2018-10-24: IFR
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: A
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2018-09-13
[6 empty] | Issue Actual | 2018-10-24: 2018-09-13
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00244; 2018-10-24: TPSK-LSPA1-T-PL-00046
[6 empty] | Return Date | 2018-10-24: 2019-05-08; 2018-10-24: 2018-10-01
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C92-0005 | Project QCS Requirements For Suppliers |  | Class 2 | Purpose** | 2018-10-24: IMP; 2018-10-24: IFR
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: A
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2018-09-13
[6 empty] | Issue Actual | 2018-10-24: 2018-09-13
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00244; 2018-10-24: TPSK-LSPA1-T-PL-00046
[6 empty] | Return Date | 2018-10-24: 2019-05-08; 2018-10-24: 2018-10-01
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C92-0007 | Prescriptions For Preparation Of Documentation Package For Transportation |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IMP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2018-09-13; 2018-10-24: 2018-10-08
[6 empty] | Issue Actual | 2018-10-24: 2018-09-13; 2018-10-24: 2018-10-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00048; 2018-10-24: TPSK-LSPA1-T-PL-00140
[6 empty] | Return Date | 2018-10-24: 2018-10-01; 2018-10-24: 2018-10-30
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C92-0008 | Project QCS Expediting Procedure |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IMP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: 0
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00046; 2018-10-24: TPSK-LSPA1-T-PL-00297
[6 empty] | Return Date | 2018-10-24: 2018-12-03
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C92-0009 | Project QCS Inspection Procedure |  | Class 2 | Purpose** | 2018-10-24: IMP; 2018-10-24: IFR
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: A
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2018-09-13
[6 empty] | Issue Actual | 2018-10-24: 2018-09-13
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00244; 2018-10-24: TPSK-LSPA1-T-PL-00046
[6 empty] | Return Date | 2018-10-24: 2019-05-06; 2018-10-24: 2018-10-01
Owner Cmmt* | bar: 2018-10-24 to 2018-10-24
| PL | OL1-2C92-0013 | Spare Parts & Special Tools Instructions |  | Class 2 | Purpose** | 2018-10-24: IMP; 2018-10-24: IFR
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: A
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2018-10-02; 2018-10-24: 2018-10-19
[6 empty] | Issue Actual | 2018-10-24: 2018-10-02; 2018-10-24: 2018-10-19
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00119; 2018-10-24: TPSK-LSPA1-T-PL-00064
[6 empty] | Return Date | 2018-10-24: 2018-09-25
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C92-0014 | Project Expediting And Inspection Level Definition |  | Class 2 | Purpose** | 2018-10-24: IMP; 2018-10-24: IMP; 2019-06-06: IFR
[6 empty] | Rev. | 2018-10-24: 1; 2018-10-24: 0; 2019-06-06: A
Issue Plan
[6 empty] | Revised Plan | 2019-06-06: 2018-09-13
[6 empty] | Issue Actual | 2019-06-06: 2018-09-13
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-01473; 2018-10-24: TPSK-LSPA1-T-PL-00244; 2019-06-06: TPSK-LSPA1-T-PL-00046
[6 empty] | Return Date | 2018-10-24: 2019-07-02; 2018-10-24: 2019-05-08; 2019-06-06: 2018-10-01
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
| PL | OL1-2C92-0015 | Transportation Plan |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IMP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2018-09-13; 2018-10-24: 2018-10-16
[6 empty] | Issue Actual | 2018-10-24: 2018-09-13; 2018-10-24: 2018-10-16
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00048; 2018-10-24: TPSK-LSPA1-T-PL-00177
[6 empty] | Return Date | 2018-10-24: 2018-10-01; 2018-10-24: 2018-10-30
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C92-0016 | Parking Marking And Shipping Instructions |  | Class 2 | Purpose** | 2018-10-24: IFR; 2018-10-24: IMP
[6 empty] | Rev. | 2018-10-24: A; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2018-09-13; 2018-10-24: 2018-10-08
[6 empty] | Issue Actual | 2018-10-24: 2018-09-13; 2018-10-24: 2018-10-08
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00048; 2018-10-24: TPSK-LSPA1-T-PL-00140
[6 empty] | Return Date | 2018-10-24: 2018-10-01; 2018-10-24: 2018-10-30
Owner Cmmt* | bar: 2018-10-24
| PL | OL1-2C92-0017 | Project Site Services Conditions For Supplier Specialists |  | Class 2 | Purpose** | 2018-10-24: IMP; 2018-10-24: IMP; 2019-06-06: IFR
[6 empty] | Rev. | 2018-10-24: 0; 2018-10-24: 1; 2019-06-06: A
Issue Plan
[6 empty] | Revised Plan | 2019-06-06: 2018-09-14
[6 empty] | Issue Actual | 2019-06-06: 2018-09-14
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00284; 2018-10-24: TPSK-LSPA1-T-PL-00594; 2019-06-06: TPSK-LSPA1-T-PL-00051
[6 empty] | Return Date | 2018-10-24: 2018-11-20; 2018-10-24: 2019-01-16; 2019-06-06: 2018-10-04
Owner Cmmt* | bar: 2018-10-24 to 2019-06-06
Category Code: C93 Policy , Guidelines & Memo
| PL | OL1-2C93-0001 | General Supply Rules for Supplier Documentation |  | Class 2 | Purpose** | 2018-10-24: IFI; 2018-10-24: IFI; 2019-06-06: IFI; 2019-06-06: IFI
Rev. | bar: 2018-10-24 to 2019-06-06
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2018-09-12; 2018-10-24: 2018-09-19; 2019-06-06: 2019-02-01; 2019-06-06: 2019-02-06
[6 empty] | Issue Actual | 2018-10-24: 2018-09-12; 2018-10-24: 2018-09-19; 2019-06-06: 2019-02-01; 2019-06-06: 2019-02-06
[6 empty] | Transmittal no. | 2018-10-24: TPSK-LSPA1-T-PL-00043; 2018-10-24: TPSK-LSPA1-T-PL-00043; 2019-06-06: TPSK-LSPA1-T-PL-00777; 2019-06-06: TPSK-LSPA1-T-PL-00777
Return Date
Owner Cmmt*
Category Code: C94 Forms & Templates
Category Code: C95 Progress/Status Reports
| PL | OL1-2C95-0001 | Expediting Execution Plan |  | Class 2 | Purpose** | IFI | IFI | IFI | IFI | IFI | IFI | IFE | IFE | IMP
[6 empty] | Rev. | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 4
Issue Plan
[6 empty] | Revised Plan | 2019-03-22 | 2019-03-22 | 2019-04-19 | 2019-04-19 | 2019-05-16 | 2019-05-17 | 2019-06-19 | 2019-06-19 | 2019-07-25
[6 empty] | Issue Actual | 2019-03-22 | 2019-03-22 | 2019-04-19 | 2019-04-19 | 2019-05-16 | 2019-05-17 | 2019-06-19 | 2019-06-19 | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01134 | TPSK-LSPA1-T-PL-01134 | TPSK-LSPA1-T-PL-01419 | TPSK-LSPA1-T-PL-01419 | TPSK-LSPA1-T-PL-01675 | TPSK-LSPA1-T-PL-01675 | TPSK-LSPA1-T-PL-01915 | TPSK-LSPA1-T-PL-01915 | LSPA1-TPSK-T-PL-02256
[6 empty] | Return Date | 2019-05-16: 2019-05-29; 2019-05-17: 2019-05-29; 2019-06-19: 2019-06-27; 2019-06-19: 2019-06-27
Owner Cmmt* | bar: 2019-05-16 to 2019-06-19
| PL | OL1-2C95-0002 | Monthly Complete Expediting Report |  | Class 2 | Purpose** | IFI | IFI | IFI | IFI | IFI | IFI | IFE | IFE | IMP
[6 empty] | Rev. | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 4
Issue Plan
[6 empty] | Revised Plan | 2019-03-22 | 2019-03-22 | 2019-04-19 | 2019-04-19 | 2019-05-16 | 2019-05-17 | 2019-06-19 | 2019-06-19 | 2019-07-25
[6 empty] | Issue Actual | 2019-03-22 | 2019-03-22 | 2019-04-19 | 2019-04-19 | 2019-05-16 | 2019-05-17 | 2019-06-19 | 2019-06-19 | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01134 | TPSK-LSPA1-T-PL-01134 | TPSK-LSPA1-T-PL-01419 | TPSK-LSPA1-T-PL-01419 | TPSK-LSPA1-T-PL-01675 | TPSK-LSPA1-T-PL-01675 | TPSK-LSPA1-T-PL-01915 | TPSK-LSPA1-T-PL-01915 | LSPA1-TPSK-T-PL-02256
[6 empty] | Return Date | 2019-05-16: 2019-05-29; 2019-05-17: 2019-05-29; 2019-06-19: 2019-06-27; 2019-06-19: 2019-06-27; 2019-07-25: 2019-08-02
Owner Cmmt* | bar: 2019-05-16 to 2019-07-25
| PL | OL1-2C95-140000 | Hand-Over Meeting Report - Quench Exchanger and Steam D |  | Class 2 | Purpose** | 2019-03-22: IFI
[6 empty] | Rev. | 2019-03-22: 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2019-03-11
[6 empty] | Issue Actual | 2019-03-22: 2019-03-11
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-PL-01026
Return Date
Owner Cmmt*
| PL | OL1-2C95-300000 | Hand-Over Meeting Report - Radiant Coils |  | Class 2 | Purpose** | 2019-03-22: IFI
[6 empty] | Rev. | 2019-03-22: 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2019-03-29
[6 empty] | Issue Actual | 2019-03-22: 2019-03-29
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-PL-01194
Return Date
Owner Cmmt*
| PL | OL1-2C95-302000 | Pre-Inspection Meeting Report - Intermediate Tube Supports |  | Class 2 | Purpose** | 2019-03-22: IFI
[6 empty] | Rev. | 2019-03-22: 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2019-04-15
[6 empty] | Issue Actual | 2019-03-22: 2019-04-15
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-PL-01359
Return Date
Owner Cmmt*
Category Code: Code Information
Category Code: D01 Construction Permits/License/Permit Plan
Category Code: D03 Security Plan
Category Code: D04 Transportation Program
Category Code: D05 Office & Construction Camp Plan
Category Code: D06 Work Change Proposal
Category Code: D71 Appraisal Report for Consultancy Service
Category Code: D72 Appraisal Report for EPC Contractor Work
Category Code: D73 Appraisal Report for Vendor/Supplier
Category Code: D91 Index/List
Category Code: D92 Procedures & Standards
Category Code: D93 Policy , Guidelines & Memo
Category Code: D94 Forms & Templates
Category Code: D95 Progress/Status Reports
Category Code: D96 Hydrostatic leak testing for piping systems
Category Code: E01 Electrical design basis
| EE | OL1-2E01-2001 | ELECTRICAL BASIS OF FURNACE DETAILED DESIGN |  | Class 1 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IFD; 2019-04-19: IFF
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-01-24; 2019-04-19: 2019-03-28; 2019-04-19: 2019-03-28
[6 empty] | Revised Plan | 2019-04-19: 2019-08-30; 2019-04-19: 2019-08-30
[6 empty] | Issue Actual | 2019-03-22: 2019-01-30; 2019-03-22: 2019-01-31
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00772; 2019-03-22: TPSK-LSPA1-T-EE-00772
[6 empty] | Return Date | 2019-03-22: 2019-02-27; 2019-03-22: 2019-02-27
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
Category Code: E02 Abbreviation and standard symbols
| EE | OL1-2E02-0001 | ELECTRICAL DRAWINGS LEGEND AND SYMBOLS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IFC
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-05-30; 2019-04-19: 2019-10-30
[6 empty] | Revised Plan | 2019-04-19: 2019-10-30
[6 empty] | Issue Actual | 2019-03-22: 2019-03-28; 2019-03-22: 2019-04-19
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01411; 2019-03-22: TPSK-LSPA1-T-EE-01411
[6 empty] | Return Date | 2019-03-22: 2019-05-15; 2019-03-22: 2019-05-15
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
Category Code: E03 Project electrical specification
| EE | OL1-2E03-0035 | TYPICAL INSTALLATION STANDARDS FOR ELECTRICAL EQUIPMENT |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-02-14; 2019-04-19: 2019-10-07; 2019-04-19: 2020-02-14
[6 empty] | Revised Plan | 2019-04-19: 2019-10-07; 2019-04-19: 2020-02-14
[6 empty] | Issue Actual | 2019-03-22: 2019-04-01; 2019-03-22: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01193; 2019-03-22: TPSK-LSPA1-T-EE-01193
[6 empty] | Return Date | 2019-03-22: 2019-05-07; 2019-03-22: 2019-05-07
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
Category Code: E04 Electrical requirement for package unit
| EE | OL1-2E04-6000 | GENERAL DEIGN RULES FOR ELECTRICAL SYSTEM OF PACKAGED EQUIPMENT |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IFR; 2019-04-19: IMP
Rev. | bar: 2019-03-22 to 2019-04-19
[6 empty] | Issue Plan | 2019-03-22: 2018-10-14; 2019-04-19: 2019-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-03-22: 2018-08-06; 2019-03-22: 2018-10-04; 2019-04-19: 2018-10-04
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00008; 2019-03-22: TPSK-LSPA1-T-EE-00126; 2019-04-19: TPSK-LSPA1-T-EE-00126
[6 empty] | Return Date | 2019-03-22: 2018-08-24; 2019-03-22: 2018-10-12; 2019-04-19: 2018-10-12
Owner Cmmt* | bar: 2019-03-22 to 2019-04-19
Category Code: E05 Electrical Equipment datasheets
| EE | CL1-2E05-1200 | Typical Data Sheet for Low Voltage Switchgears/MCCs |  | Class As Built | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFQ
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2018-12-14
[6 empty] | Issue Actual | 2019-03-22: 2018-12-14
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00497; 2019-03-22: TPSK-LSPA1-T-EE-00497
[6 empty] | Return Date | 2019-03-22: 2019-01-07; 2019-03-22: 2019-01-07
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | CL1-2E05-1400 | Typical Data Sheet for Low Voltage Bus Ducts |  | Class As Built | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFQ
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2018-12-14
[6 empty] | Issue Actual | 2019-03-22: 2018-12-14
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00497; 2019-03-22: TPSK-LSPA1-T-EE-00497
[6 empty] | Return Date | 2019-03-22: 2019-01-07; 2019-03-22: 2019-01-07
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E05-0020 | Air Conditioning Ventilating And Ducting Design - Ex Document Client Reference: OL1-2H03-0001 - |  | Class As Built | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IMP; 2019-04-19: IMP
[6 empty] | Rev. | 2019-03-22: A; 2019-03-22: A; 2019-04-19: 0; 2019-04-19: 0
[6 empty] | Issue Plan | 2019-03-22: 2018-10-12; 2019-04-19: 2019-01-15
Revised Plan
[6 empty] | Issue Actual | 2019-03-22: 2018-10-12; 2019-03-22: 2018-10-15; 2019-04-19: 2019-01-07
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00165; 2019-03-22: TPSK-LSPA1-T-EE-00165; 2019-04-19: TPSK-LSPA1-T-EE-00585; 2019-04-19: TPSK-LSPA1-T-EE-00585
[6 empty] | Return Date | 2019-03-22: 2018-10-26; 2019-03-22: 2018-10-26; 2019-04-19: 2019-01-16; 2019-04-19: 2019-01-16
Owner Cmmt* | bar: 2019-03-22 to 2019-04-19
| EE | OL1-2E05-1100 | Typical Data Sheet for Medium Voltage Switchgears |  | Class As Built | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFQ
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2018-12-11
[6 empty] | Issue Actual | 2019-03-22: 2018-12-11
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-ME-00476; 2019-03-22: TPSK-LSPA1-T-ME-00476
[6 empty] | Return Date | 2019-03-22: 2019-01-07; 2019-03-22: 2019-01-07
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E05-1111 | Data Sheet for Medium Voltage Switchgear |  | Class As Built | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2019-03-29; 2019-03-22: 2019-04-01
[6 empty] | Issue Actual | 2019-03-22: 2019-03-29; 2019-03-22: 2019-04-01
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01192; 2019-03-22: TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-03-22: 2019-04-23; 2019-03-22: 2019-04-23
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E05-1211 | Data Sheet for 690V Switchgear And MCC |  | Class As Built | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2019-03-29; 2019-03-22: 2019-04-01
[6 empty] | Issue Actual | 2019-03-22: 2019-03-29; 2019-03-22: 2019-04-01
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01192; 2019-03-22: TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-03-22: 2019-04-23; 2019-03-22: 2019-04-23
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E05-1311 | Data Sheet for 400V SwitchgearAndMCC |  | Class As Built | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2019-03-29; 2019-03-22: 2019-04-01
[6 empty] | Issue Actual | 2019-03-22: 2019-03-29; 2019-03-22: 2019-04-01
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01192; 2019-03-22: TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-03-22: 2019-04-23; 2019-03-22: 2019-04-23
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E05-1501 | Data Sheet for Distribution Transformer |  | Class As Built | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IFR
Rev. | bar: 2019-03-22 to 2019-04-19
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2019-03-29; 2019-03-22: 2019-04-01; 2019-04-19: 2019-08-05
[6 empty] | Issue Actual | 2019-03-22: 2019-03-29; 2019-03-22: 2019-04-01; 2019-04-19: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01192; 2019-03-22: TPSK-LSPA1-T-EE-01192; 2019-04-19: TPSK-LSPA1-T-EE-02316
[6 empty] | Return Date | 2019-03-22: 2019-04-23; 2019-03-22: 2019-04-23
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E05-1700 | Typical Data Sheet For Medium Voltage Variable Voltage Variable Frequency System |  | Class As Built | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFQ
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2018-12-20
[6 empty] | Issue Actual | 2019-03-22: 2018-12-20
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00529; 2019-03-22: TPSK-LSPA1-T-EE-00529
[6 empty] | Return Date | 2019-03-22: 2019-01-03; 2019-03-22: 2019-01-03
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E05-2001 | Data Sheet for AC UPS |  | Class As Built | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2019-03-29; 2019-03-22: 2019-04-01
[6 empty] | Issue Actual | 2019-03-22: 2019-03-29; 2019-03-22: 2019-04-01
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01192; 2019-03-22: TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-03-22: 2019-04-23; 2019-03-22: 2019-04-23
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E05-2101 | Data Sheet For DC UPS |  | Class As Built | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2019-03-29; 2019-03-22: 2019-04-01
[6 empty] | Issue Actual | 2019-03-22: 2019-03-29; 2019-03-22: 2019-04-01
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01192; 2019-03-22: TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-03-22: 2019-04-23; 2019-03-22: 2019-04-23
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E05-3100 | Typical Data Sheet for LV Motors |  | Class As Built | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFQ
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2018-11-26
[6 empty] | Issue Actual | 2019-03-22: 2018-11-26
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00358; 2019-03-22: TPSK-LSPA1-T-EE-00358
[6 empty] | Return Date | 2019-03-22: 2019-01-03; 2019-03-22: 2019-01-03
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E05-3500 | Typical Data Sheet For Low Voltage Variable Voltage Variable Frequency System |  | Class As Built | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFQ
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2018-11-26
[6 empty] | Issue Actual | 2019-03-22: 2018-11-26
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00358; 2019-03-22: TPSK-LSPA1-T-EE-00358
[6 empty] | Return Date | 2019-03-22: 2019-01-03; 2019-03-22: 2019-01-03
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E05-4100 | Typical Data Sheet For MV Motor |  | Class As Built | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFQ
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2018-12-20
[6 empty] | Issue Actual | 2019-03-22: 2018-12-20
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00529; 2019-03-22: TPSK-LSPA1-T-EE-00529
[6 empty] | Return Date | 2019-03-22: 2019-01-03; 2019-03-22: 2019-01-03
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
Category Code: E10 Power system studies
| EE | OL1-2E10-0001 | ELECTRICAL CABLE SIZING CALCULATION NOTES |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFF
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-02-14; 2019-04-19: 2019-10-15; 2019-04-19: 2020-01-15
[6 empty] | Revised Plan | 2019-04-19: 2019-10-15; 2019-04-19: 2020-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-04-23; 2019-03-22: 2019-04-24
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01438; 2019-03-22: TPSK-LSPA1-T-EE-01438
[6 empty] | Return Date | 2019-03-22: 2019-05-15; 2019-03-22: 2019-05-15
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E10-0002 | ELECTRICAL POWER BALANCE |  | Class 2 | Purpose** | 2019-03-22: IDD; 2019-03-22: IDD1; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-05-18; 2019-03-22: 2019-10-21; 2019-04-19: 2020-01-30
[6 empty] | Revised Plan | 2019-03-22: 2019-10-14; 2019-03-22: 2019-10-21; 2019-04-19: 2020-01-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0003 | LIGHTING SYSTEM CALCULATION NOTES |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-03-22: 2019-12-04; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-12-04; 2019-04-19: 2020-08-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0004 | SHORT CIRCUIT ANALYSIS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFF
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2020-01-15; 2019-04-19: 2020-03-17; 2019-04-19: 2020-05-21
[6 empty] | Revised Plan | 2019-04-19: 2020-03-17; 2019-04-19: 2020-05-21
[6 empty] | Issue Actual | 2019-03-22: 2019-04-23; 2019-03-22: 2019-04-24
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01438; 2019-03-22: TPSK-LSPA1-T-EE-01438
[6 empty] | Return Date | 2019-03-22: 2019-05-18; 2019-03-22: 2019-05-18
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E10-0005 | LOAD FLOW AND VOLTAGE DROP ANALYSIS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFF
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2020-01-15; 2019-04-19: 2020-03-17; 2019-04-19: 2020-05-21
[6 empty] | Revised Plan | 2019-04-19: 2020-03-17; 2019-04-19: 2020-05-21
[6 empty] | Issue Actual | 2019-03-22: 2019-04-23; 2019-03-22: 2019-04-24
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01438; 2019-03-22: TPSK-LSPA1-T-EE-01438
[6 empty] | Return Date | 2019-03-22: 2019-05-18; 2019-03-22: 2019-05-18
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E10-0006 | MOTOR STARTING ANALYSIS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
[6 empty] | Revised Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0007 | REACCELERATION STUDY |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
[6 empty] | Revised Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0008 | HARMONIC ANALYSIS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
[6 empty] | Revised Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0009 | EMC STUDY |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
[6 empty] | Revised Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0010 | ELECTRICAL RELIABILITY ANALYSIS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
[6 empty] | Revised Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0011 | INSULATION COORDINATION STUDY |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
[6 empty] | Revised Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E11 Arc flash studies
| EE | OL1-2E11-0001 | FLASH PROTECTION STUDY |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
[6 empty] | Revised Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E12 Protective relay selection and coordination study
| EE | OL1-2E12-0001 | PROTECTIVE RELAY SELECTIVITY STUDY |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-10-21; 2019-03-22: 2020-11-21; 2019-04-19: 2020-12-21
[6 empty] | Revised Plan | 2019-03-22: 2020-10-21; 2019-03-22: 2020-11-21; 2019-04-19: 2020-12-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E13 Electrical equipment sizing
| EE | OL1-2E13-0001 | POWER FACTOR IMPROVEMENT SYSTEM SIZING |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
[6 empty] | Revised Plan | 2019-03-22: 2020-01-15; 2019-03-22: 2020-03-17; 2019-04-19: 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E13-0002 | AC UPS SYSTEM SIZING |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-10-11; 2019-03-22: 2020-03-15; 2019-04-19: 2020-05-21
[6 empty] | Revised Plan | 2019-03-22: 2019-10-11; 2019-03-22: 2020-03-15; 2019-04-19: 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E13-0003 | DC SYSTEM SIZING |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-10-11; 2019-03-22: 2020-03-15; 2019-04-19: 2020-05-21
[6 empty] | Revised Plan | 2019-03-22: 2019-10-11; 2019-03-22: 2020-03-15; 2019-04-19: 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E14 Single line diagram
| EE | OL1-2E14-0001 | KEY SINGLE LINE DIAGRAM |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IFR; 2019-04-19: IDD; 2019-05-16: IFC
Rev. | bar: 2019-03-22 to 2019-04-19
[6 empty] | Issue Plan | 2019-03-22: 2019-06-03; 2019-04-19: 2019-11-07; 2019-05-16: 2020-04-17
[6 empty] | Revised Plan | 2019-04-19: 2019-11-07; 2019-05-16: 2020-04-17
[6 empty] | Issue Actual | 2019-03-22: 2019-03-28; 2019-03-22: 2019-04-19; 2019-04-19: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01412; 2019-03-22: TPSK-LSPA1-T-EE-01412; 2019-04-19: TPSK-LSPA1-T-EE-02329
[6 empty] | Return Date | 2019-03-22: 2019-05-15; 2019-03-22: 2019-05-15
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E14-0002 | INTERLOCKING SYSTEM PHYLOSOPHY DRAWING |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-06-03; 2019-03-22: 2019-11-07; 2019-04-19: 2020-04-17
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-07; 2019-04-19: 2020-04-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E14-0003 | SUBSTATION E SINGLE LINE DIAGRAM (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-06-03; 2019-04-19: 2019-11-07; 2019-04-19: 2020-04-17; 2019-05-16: 2020-07-17
[6 empty] | Revised Plan | 2019-04-19: 2019-11-07; 2019-04-19: 2020-04-17; 2019-05-16: 2020-07-17
[6 empty] | Issue Actual | 2019-03-22: 2019-04-01; 2019-03-22: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01211; 2019-03-22: TPSK-LSPA1-T-EE-01211
[6 empty] | Return Date | 2019-03-22: 2019-04-25; 2019-03-22: 2019-04-25
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E14-0004 | SUBSTATION C SINGLE LINE DIAGRAM (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-06-03; 2019-04-19: 2019-11-07; 2019-04-19: 2020-04-17; 2019-05-16: 2020-07-17
[6 empty] | Revised Plan | 2019-04-19: 2019-11-07; 2019-04-19: 2020-04-17; 2019-05-16: 2020-07-17
[6 empty] | Issue Actual | 2019-03-22: 2019-04-01; 2019-03-22: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-CV-01211; 2019-03-22: TPSK-LSPA1-T-CV-01211
[6 empty] | Return Date | 2019-03-22: 2019-04-25; 2019-03-22: 2019-04-25
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E14-0005 | SATELLITE SUBSTATION SINGLE LINE DIAGRAM (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-06-03; 2019-04-19: 2019-11-07; 2019-04-19: 2020-04-17; 2019-05-16: 2020-07-17
[6 empty] | Revised Plan | 2019-04-19: 2019-11-07; 2019-04-19: 2020-04-17; 2019-05-16: 2020-07-17
[6 empty] | Issue Actual | 2019-03-22: 2019-04-01; 2019-03-22: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01211; 2019-03-22: TPSK-LSPA1-T-EE-01211
[6 empty] | Return Date | 2019-03-22: 2019-04-25; 2019-03-22: 2019-04-25
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
Category Code: E15 Electrical load schedule |  |  |  |  | Class 3 | Purpose**
| EE | OL1-2E15-0001 | PRELIMINARY ELECTRICAL LOAD SCHEDULE - OLEFINS UNIT |  | Class 3 | Purpose** | 2019-03-22: IDD; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-05-03; 2019-03-22: 2020-03-17
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-0002 | ELECTRICAL EQUIPMENT LIST |  | Class 2 | Purpose** | 2019-03-22: IDD; 2019-03-22: IDD1; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-06-03; 2019-03-22: 2019-11-07; 2019-04-19: 2020-04-17
[6 empty] | Revised Plan | 2019-03-22: 2019-11-07; 2019-04-19: 2020-04-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-0003 | EX-EQUIPMENT REGISTER LIST |  | Class 2 | Purpose** | 2019-03-22: IF1T; 2019-03-22: IF2T
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-14; 2019-03-22: 2020-10-19
[6 empty] | Revised Plan | 2019-03-22: 2020-04-14; 2019-03-22: 2020-10-19
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-0004 | ELECTRICAL CONSUMERS LIST |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-03-19; 2019-03-22: 2019-04-23
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-0005 | Substation C - Medium Voltage - Switchboard Composition |  | Class As Built | Purpose** | 2019-03-22: IFQ
Rev. | bar: 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2019-08-05
[6 empty] | Issue Actual | 2019-03-22: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02315
Return Date
Owner Cmmt*
| EE | OL1-2E15-0006 | Substation E - Low Voltage - Switchboard Composition |  | Class As Built | Purpose** | 2019-03-22: IFQ
Rev. | bar: 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2019-08-05
[6 empty] | Issue Actual | 2019-03-22: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02315
Return Date
Owner Cmmt*
| EE | OL1-2E15-0007 | Substation C - Low Voltage - Switchboard Composition |  | Class As Built | Purpose** | 2019-03-22: IFQ
Rev. | bar: 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2019-08-05
[6 empty] | Issue Actual | 2019-03-22: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02315
Return Date
Owner Cmmt*
| EE | OL1-2E15-0008 | Substation F - Low Voltage - Switchboard Composition |  | Class As Built | Purpose** | 2019-03-22: IFQ
Rev. | bar: 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2019-08-05
[6 empty] | Issue Actual | 2019-03-22: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02315
Return Date
Owner Cmmt*
| EE | OL1-2E15-1001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-09-10; 2019-03-22: 2019-10-08; 2019-04-19: 2019-10-08
[6 empty] | Revised Plan | 2019-03-22: 2019-09-10; 2019-03-22: 2019-10-08; 2019-04-19: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-2001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-09-10; 2019-03-22: 2019-10-08; 2019-04-19: 2019-10-08
[6 empty] | Revised Plan | 2019-03-22: 2019-09-10; 2019-03-22: 2019-10-08; 2019-04-19: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-3001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose** | 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-10-14
[6 empty] | Revised Plan | 2019-03-22: 2019-10-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-4001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose** | 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-10-14
[6 empty] | Revised Plan | 2019-03-22: 2019-10-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-5001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose** | 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-10-14
[6 empty] | Revised Plan | 2019-03-22: 2019-10-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-6001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose** | 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-10-14
[6 empty] | Revised Plan | 2019-03-22: 2019-10-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E16 Emergency power supply load schedule
Category Code: E17 Motor list
| EE | OL1-2E17-1001 | PRELIMINARY MOTOR LIST - OLEFINS UNIT |  |  | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-02-18; 2019-03-22: 2019-04-23
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E18 Control and Signal List
| EE | OL1-2E18-0001 | SUBSTATION MONITORING AND CONTROL SYSTEM BLOCK DIAGRAM FOR SUBSTATION E |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-14; 2019-03-22: 2019-11-04
[6 empty] | Revised Plan | 2019-03-22: 2019-11-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E18-0002 | SUBSTATION MONITORING AND CONTROL SYSTEM BLOCK DIAGRAM FOR SUBSTATION C |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-14; 2019-03-22: 2019-11-04
[6 empty] | Revised Plan | 2019-03-22: 2019-11-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E18-0003 | SUBSTATION MONITORING AND CONTROL SYSTEM BLOCK DIAGRAM FOR SATELLITE SUBSTATION |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-14; 2019-03-22: 2019-11-04
[6 empty] | Revised Plan | 2019-03-22: 2019-11-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E19 Control schematic and control logic diagrams
| EE | OL1-2E19-0001 | MEDIUM VOLTAGE PROTECTION DIAGRAMS |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-09-07; 2019-03-22: 2019-11-12
[6 empty] | Revised Plan | 2019-03-22: 2019-11-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E19-0002 | LOW VOLTAGE PROTECTION DIAGRAMS |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-09-07; 2019-03-22: 2019-11-12
[6 empty] | Revised Plan | 2019-03-22: 2019-11-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E20 Substation equipment layout
| EE | OL1-2E20-0001 | SUBSTATION E EQUIPMENT LAYOUT |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-06-03; 2019-04-19: 2019-10-08; 2019-04-19: 2020-04-17; 2019-05-16: 2020-06-17
[6 empty] | Revised Plan | 2019-04-19: 2019-10-08; 2019-04-19: 2020-04-17; 2019-05-16: 2020-06-17
[6 empty] | Issue Actual | 2019-03-22: 2019-04-01; 2019-03-22: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01212; 2019-03-22: TPSK-LSPA1-T-EE-01212
[6 empty] | Return Date | 2019-03-22: 2019-06-04; 2019-03-22: 2019-06-04
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E20-0002 | SUBSTATION C EQUIPMENT LAYOUT |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-06-03; 2019-04-19: 2019-10-08; 2019-04-19: 2020-04-17; 2019-05-16: 2020-06-17
[6 empty] | Revised Plan | 2019-04-19: 2019-10-08; 2019-04-19: 2020-04-17; 2019-05-16: 2020-06-17
[6 empty] | Issue Actual | 2019-03-22: 2019-04-01; 2019-03-22: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01212; 2019-03-22: TPSK-LSPA1-T-EE-01212
[6 empty] | Return Date | 2019-03-22: 2019-05-07; 2019-03-22: 2019-05-07
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E20-0003 | SATELLITE ELECTRICAL / INSTRUMENT EQUIPMENT LAYOUT |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-06-03; 2019-04-19: 2019-10-08; 2019-04-19: 2020-04-17; 2019-05-16: 2020-06-17
[6 empty] | Revised Plan | 2019-04-19: 2019-10-08; 2019-04-19: 2020-04-17; 2019-05-16: 2020-06-17
[6 empty] | Issue Actual | 2019-03-22: 2019-04-01; 2019-03-22: 2019-04-02
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01212; 2019-03-22: TPSK-LSPA1-T-EE-01212
[6 empty] | Return Date | 2019-03-22: 2019-06-04; 2019-03-22: 2019-06-04
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
Category Code: E21 Layout of busduct for substation
Category Code: E22 Cable tray layout for substation
| EE | OL1-2E22-0001 | SUBSTATION E CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFC; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-11-08; 2019-03-22: 2020-05-17; 2019-04-19: 2020-11-05; 2019-04-19: 2021-09-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-08; 2019-03-22: 2020-05-17; 2019-04-19: 2020-11-05; 2019-04-19: 2021-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E22-0002 | SUBSTATION C CABLE ROUTING LAYOUT (N…) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFC; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-11-08; 2019-03-22: 2020-05-17; 2019-04-19: 2020-11-05; 2019-04-19: 2021-09-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-08; 2019-03-22: 2020-05-17; 2019-04-19: 2020-11-05; 2019-04-19: 2021-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E22-0003 | SATELLITE SUBSTATION CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFC; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-11-08; 2019-03-22: 2020-05-17; 2019-04-19: 2020-11-05; 2019-04-19: 2021-09-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-08; 2019-03-22: 2020-05-17; 2019-04-19: 2020-11-05; 2019-04-19: 2021-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E23 Wiring drawing for substation system
Category Code: E24 Diesel engine generator equipment layout
Category Code: E25 Motor Auto restart for power dift.
Category Code: E31 Power equipment layout
| EE | OL1-2E31-0001 | OVERALL ELECTRICAL MAIN CABLE ROUTING LAYOUT |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0002 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-08-07
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02356
Return Date
Owner Cmmt*
| EE | OL1-2E31-0003 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0004 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-08-08
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02381
Return Date
Owner Cmmt*
| EE | OL1-2E31-0005 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-08-07
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02356
Return Date
Owner Cmmt*
| EE | OL1-2E31-0006 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0007 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-08-07
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02359
Return Date
Owner Cmmt*
| EE | OL1-2E31-0008 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02307
Return Date
Owner Cmmt*
| EE | OL1-2E31-0009 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-07-30
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02272
Return Date
Owner Cmmt*
| EE | OL1-2E31-0010 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0011 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0012 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0013 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0014 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0015 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0016 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-07-30
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02272
Return Date
Owner Cmmt*
| EE | OL1-2E31-0017 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-1001 | USC 36M FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-1002 | USC 36M FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-1003 | USC 36M FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-2001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-2002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-2003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-3001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-3002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-3003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-4001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-4002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-4003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-5001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-5002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-5003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-6001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-6002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-6003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
[6 empty] | Revised Plan | 2019-03-22: 2019-12-19; 2019-03-22: 2020-01-09; 2019-04-19: 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E32 Main cable route layout
| EE | OL1-2E32-0001 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0002 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-07-30
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02275
Return Date
Owner Cmmt*
| EE | OL1-2E32-0003 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0004 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-08-16
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02440
Return Date
Owner Cmmt*
| EE | OL1-2E32-0005 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0006 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0007 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0008 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0009 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-07-30
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02275
Return Date
Owner Cmmt*
| EE | OL1-2E32-0010 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-07-30
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02275
Return Date
Owner Cmmt*
| EE | OL1-2E32-0011 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-07-30
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02275
Return Date
Owner Cmmt*
| EE | OL1-2E32-0012 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-07-29
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02268
Return Date
Owner Cmmt*
| EE | OL1-2E32-0013 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-07-30
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02275
Return Date
Owner Cmmt*
| EE | OL1-2E32-0014 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Issue Actual | 2019-03-22: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02225
Return Date
Owner Cmmt*
| EE | OL1-2E32-0015 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0016 | POWER LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-11-30; 2019-04-19: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1001 | USC 36M FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1002 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1003 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1004 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1005 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1006 | USC 36M FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1007 | USC 36M FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1008 | USC 36M FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1009 | USC 36M FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
[6 empty] | Revised Plan | 2019-03-22: 2020-01-31; 2019-03-22: 2020-02-24; 2019-04-19: 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E33 Power and control wiring layout
Category Code: E34 Power and control cable arrangement drawing
| EE | OL1-2E34-0001 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0002 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-07-30
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02276
Return Date
Owner Cmmt*
| EE | OL1-2E34-0003 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0004 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0005 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0006 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0007 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0008 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0009 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-07-30
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02276
Return Date
Owner Cmmt*
| EE | OL1-2E34-0010 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-07-30
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02276
Return Date
Owner Cmmt*
| EE | OL1-2E34-0011 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-07-30
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02276
Return Date
Owner Cmmt*
| EE | OL1-2E34-0012 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-07-29
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02269
Return Date
Owner Cmmt*
| EE | OL1-2E34-0013 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-07-30
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02276
Return Date
Owner Cmmt*
| EE | OL1-2E34-0014 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02226
Return Date
Owner Cmmt*
| EE | OL1-2E34-0015 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0016 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-12; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-22; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E40 Lighting illumination level calculation
| EE | OL1-2E40-0001 | Lighting Calculation Report |  | Class As Built | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2019-06-11; 2019-03-22: 2019-06-11
[6 empty] | Issue Actual | 2019-03-22: 2019-06-11; 2019-03-22: 2019-06-11
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01864; 2019-03-22: TPSK-LSPA1-T-EE-01864
[6 empty] | Return Date | 2019-03-22: 2019-07-01
Owner Cmmt* | bar: 2019-03-22
Category Code: E41 Voltage drop calculation for lighting system
Category Code: E42 Lighting and receptacle panel board circuit schedule
| EE | OL1-2E42-0001 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0002 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0003 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0004 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0005 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0006 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0007 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0008 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0009 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0010 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0011 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0012 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0013 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0014 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0015 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0016 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
[6 empty] | Revised Plan | 2019-03-22: 2020-01-20; 2019-03-22: 2020-03-30; 2019-04-19: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-1001 | USC 36M FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
[6 empty] | Revised Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-1002 | USC 36M FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-01; 2019-03-22: 2020-06-01
[6 empty] | Revised Plan | 2019-03-22: 2020-06-01; 2019-03-22: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-1003 | USC 36M FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
[6 empty] | Revised Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-2001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
[6 empty] | Revised Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-2002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-01; 2019-03-22: 2020-06-01
[6 empty] | Revised Plan | 2019-03-22: 2020-06-01; 2019-03-22: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-2003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
[6 empty] | Revised Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-3001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
[6 empty] | Revised Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-3002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-01; 2019-03-22: 2020-06-01
[6 empty] | Revised Plan | 2019-03-22: 2020-06-01; 2019-03-22: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-3003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
[6 empty] | Revised Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-4001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
[6 empty] | Revised Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-4002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-01; 2019-03-22: 2020-06-01
[6 empty] | Revised Plan | 2019-03-22: 2020-06-01; 2019-03-22: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-4003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
[6 empty] | Revised Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-5001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
[6 empty] | Revised Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-5002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-01; 2019-03-22: 2020-06-01
[6 empty] | Revised Plan | 2019-03-22: 2020-06-01; 2019-03-22: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-5003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
[6 empty] | Revised Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-6001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
[6 empty] | Revised Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-6002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-01; 2019-03-22: 2020-06-01
[6 empty] | Revised Plan | 2019-03-22: 2020-06-01; 2019-03-22: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-6003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
[6 empty] | Revised Plan | 2019-03-22: 2020-07-28; 2019-03-22: 2020-08-17; 2019-04-19: 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E43 Lighting and receptacle system layout
| EE | OL1-2E43-0001 | STREET LIGHTING SYSTEM LAYOUT |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-04-19: 2019-12-04; 2019-04-19: 2020-06-08; 2019-05-16: 2020-08-08
[6 empty] | Revised Plan | 2019-04-19: 2019-12-04; 2019-04-19: 2020-06-08; 2019-05-16: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-06-03; 2019-03-22: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01794; 2019-03-22: TPSK-LSPA1-T-EE-01794
[6 empty] | Return Date | 2019-03-22: 2019-06-12
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E43-0005 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02281
[6 empty] | Return Date | 2019-03-22: 2019-08-08
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E43-0006 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0007 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02237
[6 empty] | Return Date | 2019-03-22: 2019-08-08
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E43-0008 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02204
[6 empty] | Return Date | 2019-03-22: 2019-08-08
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E43-0009 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0010 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02237
[6 empty] | Return Date | 2019-03-22: 2019-08-08
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E43-0011 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02237
[6 empty] | Return Date | 2019-03-22: 2019-08-08
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E43-0012 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02204
[6 empty] | Return Date | 2019-03-22: 2019-08-08
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E43-0013 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-04-19: 2019-12-04; 2019-04-19: 2020-06-08; 2019-05-16: 2020-08-08
[6 empty] | Revised Plan | 2019-04-19: 2019-12-04; 2019-04-19: 2020-06-08; 2019-05-16: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-04-19; 2019-03-22: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01423; 2019-03-22: TPSK-LSPA1-T-EE-01423
[6 empty] | Return Date | 2019-03-22: 2019-05-27; 2019-03-22: 2019-05-27
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E43-0014 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-04-19: 2019-12-04; 2019-04-19: 2020-06-08; 2019-05-16: 2020-08-08
[6 empty] | Revised Plan | 2019-04-19: 2019-12-04; 2019-04-19: 2020-06-08; 2019-05-16: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-04-19; 2019-03-22: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01423; 2019-03-22: TPSK-LSPA1-T-EE-01423
[6 empty] | Return Date | 2019-03-22: 2019-05-27; 2019-03-22: 2019-05-27
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E43-0015 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-04-19: 2019-12-04; 2019-04-19: 2020-06-08; 2019-05-16: 2020-08-08
[6 empty] | Revised Plan | 2019-04-19: 2019-12-04; 2019-04-19: 2020-06-08; 2019-05-16: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-04-19; 2019-03-22: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01423; 2019-03-22: TPSK-LSPA1-T-EE-01423
[6 empty] | Return Date | 2019-03-22: 2019-05-27; 2019-03-22: 2019-05-27
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E43-0016 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-04-19: 2019-12-04; 2019-04-19: 2020-06-08; 2019-05-16: 2020-08-08
[6 empty] | Revised Plan | 2019-04-19: 2019-12-04; 2019-04-19: 2020-06-08; 2019-05-16: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-04-19; 2019-03-22: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01423; 2019-03-22: TPSK-LSPA1-T-EE-01423
[6 empty] | Return Date | 2019-03-22: 2019-05-27; 2019-03-22: 2019-05-27
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E43-0017 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-04-19: 2019-12-04; 2019-04-19: 2020-06-08; 2019-05-16: 2020-08-08
[6 empty] | Revised Plan | 2019-04-19: 2019-12-04; 2019-04-19: 2020-06-08; 2019-05-16: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-04-19; 2019-03-22: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01423; 2019-03-22: TPSK-LSPA1-T-EE-01423
[6 empty] | Return Date | 2019-03-22: 2019-05-27; 2019-03-22: 2019-05-27
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E43-0018 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-04-19: 2019-12-04; 2019-04-19: 2020-06-08; 2019-05-16: 2020-08-08
[6 empty] | Revised Plan | 2019-04-19: 2019-12-04; 2019-04-19: 2020-06-08; 2019-05-16: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-04-19; 2019-03-22: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01423; 2019-03-22: TPSK-LSPA1-T-EE-01423
[6 empty] | Return Date | 2019-03-22: 2019-05-27; 2019-03-22: 2019-05-27
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E43-0019 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Issue Actual | 2019-03-22: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02311
[6 empty] | Return Date | 2019-03-22: 2019-08-08
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E43-0020 | LIGHTING LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-05-19; 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-12-04; 2019-04-19: 2020-06-08; 2019-04-19: 2020-08-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1001 | USC 36M FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1002 | USC 36M FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1003 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1004 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1005 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1006 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1007 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1008 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1009 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1010 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1011 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1012 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1013 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1014 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1015 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2016 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2017 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2018 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2019 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2020 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3016 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3017 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4016 | ELECTRICAL LIGHTING FOR ELEVATOR LANDINGS ASSOCIATED WITH FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4017 | ELECTRICAL LIGHTING FOR ELEVATOR LANDINGS ASSOCIATED WITH FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4018 | ELECTRICAL LIGHTING FOR ELEVATOR LANDINGS ASSOCIATED WITH FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4019 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4020 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5016 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5017 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6016 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6017 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6018 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6019 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6020 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
[6 empty] | Revised Plan | 2019-03-22: 2020-04-16; 2019-03-22: 2020-05-07; 2019-04-19: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E44 Lighting and receptacle system wiring layout
| EE | OL1-2E44-0001 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0002 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0003 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0004 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0005 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0006 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0007 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0008 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0009 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0010 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0011 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0012 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0013 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0014 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0015 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0016 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose** | 2019-03-22: IFC1; 2019-03-22: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
[6 empty] | Revised Plan | 2019-03-22: 2020-07-08; 2019-03-22: 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E45 POWER BLOCK DIAGRAM (WELDING AND RECEPACLES)
Category Code: E50 Grounding and lightning network calculation
| EE | OL1-2E50-0001 | EARTHING AND LIGHTNING SYSTEM CALCULATION |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFF
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-04-19; 2019-04-19: 2019-10-15; 2019-04-19: 2020-07-08
[6 empty] | Revised Plan | 2019-04-19: 2019-10-15; 2019-04-19: 2020-07-08
[6 empty] | Issue Actual | 2019-03-22: 2019-06-25; 2019-03-22: 2019-06-25
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01982; 2019-03-22: TPSK-LSPA1-T-EE-01982
[6 empty] | Return Date | 2019-03-22: 2019-07-22
Owner Cmmt* | bar: 2019-03-22
Category Code: E51 Protective zone for lightning system
Category Code: E52 Grounding and lightning system layout
| EE | OL1-2E52-0001 | OVERALL EARTHING LAYOUT |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-06-14; 2019-03-22: 2019-06-14
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01894; 2019-03-22: TPSK-LSPA1-T-EE-01894
[6 empty] | Return Date | 2019-03-22: 2019-07-01
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E52-0002 | OVERALL LIGHTNING PROTECTION LAYOUT |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-06-14; 2019-03-22: 2019-06-14
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01894; 2019-03-22: TPSK-LSPA1-T-EE-01894
[6 empty] | Return Date | 2019-03-22: 2019-07-02
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E52-0003 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-06-28; 2019-03-22: 2019-06-28
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02014; 2019-03-22: TPSK-LSPA1-T-EE-02014
[6 empty] | Return Date | 2019-03-22: 2019-07-11; 2019-03-22: 2019-07-11
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E52-0004 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-06-11; 2019-03-22: 2019-06-11
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01862; 2019-03-22: TPSK-LSPA1-T-EE-01862
[6 empty] | Return Date | 2019-03-22: 2019-06-25
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E52-0005 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-07-08; 2019-03-22: 2019-07-08
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02089; 2019-03-22: TPSK-LSPA1-T-EE-02089
[6 empty] | Return Date | 2019-03-22: 2019-07-15; 2019-03-22: 2019-07-15
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E52-0006 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-07-08; 2019-03-22: 2019-07-08
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02080; 2019-03-22: TPSK-LSPA1-T-EE-02080
[6 empty] | Return Date | 2019-03-22: 2019-07-15; 2019-03-22: 2019-07-15
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E52-0007 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-06-28; 2019-03-22: 2019-06-28
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02014; 2019-03-22: TPSK-LSPA1-T-EE-02014
[6 empty] | Return Date | 2019-03-22: 2019-07-11; 2019-03-22: 2019-07-11
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E52-0008 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-06-28; 2019-03-22: 2019-06-28
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02014; 2019-03-22: TPSK-LSPA1-T-EE-02014
[6 empty] | Return Date | 2019-03-22: 2019-07-11; 2019-03-22: 2019-07-11
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E52-0009 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-07-08; 2019-03-22: 2019-07-08
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02089; 2019-03-22: TPSK-LSPA1-T-EE-02089
[6 empty] | Return Date | 2019-03-22: 2019-07-15; 2019-03-22: 2019-07-15
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E52-0010 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-06-28; 2019-03-22: 2019-06-28
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02014; 2019-03-22: TPSK-LSPA1-T-EE-02014
[6 empty] | Return Date | 2019-03-22: 2019-07-11; 2019-03-22: 2019-07-11
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E52-0011 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-06-11; 2019-03-22: 2019-06-11
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01862; 2019-03-22: TPSK-LSPA1-T-EE-01862
[6 empty] | Return Date | 2019-03-22: 2019-06-25
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E52-0012 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-06-03; 2019-03-22: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01793; 2019-03-22: TPSK-LSPA1-T-EE-01793
[6 empty] | Return Date | 2019-03-22: 2019-07-25
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E52-0013 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-06-03; 2019-03-22: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01793; 2019-03-22: TPSK-LSPA1-T-EE-01793
[6 empty] | Return Date | 2019-03-22: 2019-06-25
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E52-0014 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev. | bar: 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-03-22: 2019-11-15; 2019-04-19: 2020-07-20; 2019-04-19: 2020-09-20
[6 empty] | Revised Plan | 2019-03-22: 2019-11-15; 2019-04-19: 2020-07-20; 2019-04-19: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-07-17
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02156
[6 empty] | Return Date | 2019-03-22: 2019-07-23
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E52-0015 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-06-11; 2019-03-22: 2019-06-11
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01862; 2019-03-22: TPSK-LSPA1-T-EE-01862
[6 empty] | Return Date | 2019-03-22: 2019-06-25
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E52-0016 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-06-11; 2019-03-22: 2019-06-11
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-01862; 2019-03-22: TPSK-LSPA1-T-EE-01862
[6 empty] | Return Date | 2019-03-22: 2019-06-25
Owner Cmmt* | bar: 2019-03-22
| EE | OL1-2E52-0017 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IDD; 2019-04-19: IFC1; 2019-05-16: IFC2
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Revised Plan | 2019-04-19: 2019-11-15; 2019-04-19: 2020-07-20; 2019-05-16: 2020-09-20
[6 empty] | Issue Actual | 2019-03-22: 2019-07-01; 2019-03-22: 2019-07-01
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-02021; 2019-03-22: TPSK-LSPA1-T-EE-02021
[6 empty] | Return Date | 2019-03-22: 2019-07-11; 2019-03-22: 2019-07-11
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E52-0018 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IDD; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-07-03; 2019-03-22: 2019-11-15; 2019-04-19: 2020-07-20; 2019-04-19: 2020-09-20
[6 empty] | Revised Plan | 2019-03-22: 2019-08-30; 2019-03-22: 2019-11-15; 2019-04-19: 2020-07-20; 2019-04-19: 2020-09-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0021 | SUBSTATION E EARTHING LAYOUT |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFC; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-11-08; 2019-03-22: 2020-05-17; 2019-04-19: 2020-11-05; 2019-04-19: 2021-09-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-08; 2019-03-22: 2020-05-17; 2019-04-19: 2020-11-05; 2019-04-19: 2021-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0022 | SUBSTATION C EARTHING LAYOUT |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFC; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-11-08; 2019-03-22: 2020-05-17; 2019-04-19: 2020-11-05; 2019-04-19: 2021-09-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-08; 2019-03-22: 2020-05-17; 2019-04-19: 2020-11-05; 2019-04-19: 2021-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0023 | SATELLITE SUBSTATION EARTHING LAYOUT |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFC; 2019-04-19: IFC1; 2019-04-19: IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-11-08; 2019-03-22: 2020-05-17; 2019-04-19: 2020-11-05; 2019-04-19: 2021-09-15
[6 empty] | Revised Plan | 2019-03-22: 2019-11-08; 2019-03-22: 2020-05-17; 2019-04-19: 2020-11-05; 2019-04-19: 2021-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-1001 | USC 36M FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-02-03; 2019-03-22: 2020-02-03
[6 empty] | Revised Plan | 2019-03-22: 2020-02-03; 2019-03-22: 2020-02-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-1002 | USC 36M FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-02-03; 2019-03-22: 2020-02-03
[6 empty] | Revised Plan | 2019-03-22: 2020-02-03; 2019-03-22: 2020-02-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-1003 | USC 36M FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1100 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-02-03; 2019-03-22: 2020-02-03
[6 empty] | Revised Plan | 2019-03-22: 2020-02-03; 2019-03-22: 2020-02-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-2001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
[6 empty] | Revised Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-2002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
[6 empty] | Revised Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-2003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1200 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
[6 empty] | Revised Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-3001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
[6 empty] | Revised Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-3002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
[6 empty] | Revised Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-3003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1300 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
[6 empty] | Revised Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-4001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
[6 empty] | Revised Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-4002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
[6 empty] | Revised Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-4003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1400 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
[6 empty] | Revised Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-5001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
[6 empty] | Revised Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-5002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
[6 empty] | Revised Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-5003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1500 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
[6 empty] | Revised Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-6001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
[6 empty] | Revised Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-6002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
[6 empty] | Revised Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-6003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1600 |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
[6 empty] | Revised Plan | 2019-03-22: 2020-06-05; 2019-03-22: 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E53 Wiring drawing for grounding and lightning system
Category Code: E54 Layout of grounding lug
Category Code: E55 Request for Quotation (RFQ) for Electrical
| EE | OL1-2E55-1100 | MR FOR MV SWITCHGEARS (> 1 KV, = 52 KV) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFQ
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2018-12-11
[6 empty] | Issue Actual | 2019-03-22: 2018-12-11
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-ME-00476; 2019-03-22: TPSK-LSPA1-T-ME-00476
[6 empty] | Return Date | 2019-03-22: 2019-01-07; 2019-03-22: 2019-01-07
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E55-1200 | MR FOR LV SWITCHGEARS AND LV BUS DUCTS (= 1 KV) |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFQ
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2018-12-14
[6 empty] | Issue Actual | 2019-03-22: 2018-12-14
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00497; 2019-03-22: TPSK-LSPA1-T-EE-00497
[6 empty] | Return Date | 2019-03-22: 2019-01-07; 2019-03-22: 2019-01-07
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E55-1800 | MR FOR SMCS SYSTEM |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFQ
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2018-12-17
[6 empty] | Issue Actual | 2019-03-22: 2018-12-17
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00510; 2019-03-22: TPSK-LSPA1-T-EE-00510
[6 empty] | Return Date | 2019-03-22: 2019-01-07; 2019-03-22: 2019-01-07
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E55-3001 | MR FOR LV ELECTRIC MOTORS AND LV VVVF |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFQ
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2018-11-26
[6 empty] | Issue Actual | 2019-03-22: 2018-11-26
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00359; 2019-03-22: TPSK-LSPA1-T-EE-00359
[6 empty] | Return Date | 2019-03-22: 2019-01-03; 2019-03-22: 2019-01-03
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E55-4100 | Material Requisition For Medium Voltage Motors Medium Voltage Variable Voltage Variable Frequency System |  |  | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFQ
Rev. | bar: 2019-03-22 to 2019-03-22
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2018-12-20
[6 empty] | Issue Actual | 2019-03-22: 2018-12-20
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00540; 2019-03-22: TPSK-LSPA1-T-EE-00540
[6 empty] | Return Date | 2019-03-22: 2019-01-14; 2019-03-22: 2019-01-14
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
Category Code: E60 Cable drum schedule |  |  |  |  | Class 2 | Purpose**
| EE | OL1-2E60-0001 | ELECTRICAL CABLE DRUM SCHEDULE |  | Class 2 | Purpose** | 2019-03-22: IF1T; 2019-03-22: IF2T
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-04-14; 2019-03-22: 2020-10-19
[6 empty] | Revised Plan | 2019-03-22: 2020-04-14; 2019-03-22: 2020-10-19
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E61 Cable schedule
| EE | OL1-2E61-0001 | ELECTRICAL CABLE SCHEDULE - SUBSTATION - E |  | Class 2 | Purpose** | 2019-03-22: IDD; 2019-03-22: IF1T; 2019-04-19: IF2T; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-08-10; 2019-03-22: 2019-11-15; 2019-04-19: 2020-02-15; 2019-04-19: 2020-05-15
[6 empty] | Revised Plan | 2019-03-22: 2019-09-13; 2019-03-22: 2019-11-15; 2019-04-19: 2020-02-15; 2019-04-19: 2020-05-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E61-0002 | ELECTRICAL CABLE SCHEDULE - SUBSTATION - C |  | Class 2 | Purpose** | 2019-03-22: IDD; 2019-03-22: IF1T; 2019-04-19: IF2T; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-08-10; 2019-03-22: 2019-11-15; 2019-04-19: 2020-02-15; 2019-04-19: 2020-05-15
[6 empty] | Revised Plan | 2019-03-22: 2019-09-13; 2019-03-22: 2019-11-15; 2019-04-19: 2020-02-15; 2019-04-19: 2020-05-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E61-0003 | ELECTRICAL CABLE SCHEDULE - SATELLITE SUBSTATION |  | Class 2 | Purpose** | 2019-03-22: IDD; 2019-03-22: IF1T; 2019-04-19: IF2T; 2019-04-19: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-08-10; 2019-03-22: 2019-11-15; 2019-04-19: 2020-02-15; 2019-04-19: 2020-05-15
[6 empty] | Revised Plan | 2019-03-22: 2019-09-13; 2019-03-22: 2019-11-15; 2019-04-19: 2020-02-15; 2019-04-19: 2020-05-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E62 Connection List
Category Code: E63 Construction material and Bill of quantities
| EE | OL1-2E63-0002 | TECHNICAL SPECIFICATION FOR ELECTRICAL INSTALLATION |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-02-20; 2019-03-22: 2020-05-22
[6 empty] | Revised Plan | 2019-03-22: 2020-02-20; 2019-03-22: 2020-05-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-0003 | JOB QC SPECIFICATION FOR ELECTRICAL INSTALLATION |  | Class 2 | Purpose** | 2019-03-22: IFQ; 2019-03-22: IFP
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2020-02-20; 2019-03-22: 2020-05-22
[6 empty] | Revised Plan | 2019-03-22: 2020-02-20; 2019-03-22: 2020-05-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-1001 | ELECTRICAL BULK MATERIAL |  | Class 3 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-10-22; 2019-03-22: 2020-02-20
[6 empty] | Revised Plan | 2019-03-22: 2019-10-22; 2019-03-22: 2020-02-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-2001 | ELECTRICAL BULK MATERIAL |  | Class 3 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-10-22; 2019-03-22: 2020-02-20
[6 empty] | Revised Plan | 2019-03-22: 2019-10-22; 2019-03-22: 2020-02-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-3001 | ELECTRICAL BULK MATERIAL |  | Class 3 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-10-22; 2019-03-22: 2020-02-20
[6 empty] | Revised Plan | 2019-03-22: 2019-10-22; 2019-03-22: 2020-02-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-4001 | ELECTRICAL BULK MATERIAL |  | Class 3 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-10-22; 2019-03-22: 2020-02-20
[6 empty] | Revised Plan | 2019-03-22: 2019-10-22; 2019-03-22: 2020-02-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-5001 | ELECTRICAL BULK MATERIAL |  | Class 3 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-10-22; 2019-03-22: 2020-02-20
[6 empty] | Revised Plan | 2019-03-22: 2019-10-22; 2019-03-22: 2020-02-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-6001 | ELECTRICAL BULK MATERIAL |  | Class 3 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFD
Rev.
[6 empty] | Issue Plan | 2019-03-22: 2019-10-22; 2019-03-22: 2020-02-20
[6 empty] | Revised Plan | 2019-03-22: 2019-10-22; 2019-03-22: 2020-02-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E64 Typical drawing
Category Code: E70 Cathodic Protection system schematic diagram
Category Code: E71 Cathodic Protection system layout
Category Code: E72 Cathodic Protection calculation
Category Code: E80 SMCS and PMS system equipment data sheets
Category Code: E81 SMCS and PMS system schematic diagram
Category Code: E82 SMCS and PMS system layout
Category Code: E86 Appraisal Report for Consultancy Service
Category Code: E87 Appraisal Report for EPC Contractor Work
Category Code: E88 Appraisal Report for Vendor/Supplier
Category Code: E90 Vendor documents
Category Code: E91 Index/List
Category Code: E92 Procedures & Standards
| EE | OL1-2E92-0001 | GENERAL DESIGN RULES FOR FOR SMART PLAN ELECTRICAL |  | Class 2 | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IMP
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2018-10-14; 2019-04-19: 2019-01-30
Revised Plan
[6 empty] | Issue Actual | 2019-03-22: 2018-08-06; 2019-03-22: 2018-08-07
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00008; 2019-03-22: TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | 2019-03-22: 2018-08-24; 2019-03-22: 2018-08-24
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| EE | OL1-2E92-0002 | Coordination Procedure For Smartplant Electrical |  | Class 2 | Purpose** | 2019-03-22: IFI; 2019-03-22: IFR; 2019-04-19: IFR; 2019-04-19: IFI
[6 empty] | Rev. | 2019-03-22: 0; 2019-03-22: A; 2019-04-19: A; 2019-04-19: 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-22: 2018-08-06; 2019-04-19: 2018-08-07; 2019-04-19: 2018-11-29
[6 empty] | Issue Actual | 2019-03-22: 2018-08-06; 2019-04-19: 2018-08-07; 2019-04-19: 2018-11-29
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00395; 2019-03-22: TPSK-LSPA1-T-EE-00008; 2019-04-19: TPSK-LSPA1-T-EE-00008; 2019-04-19: TPSK-LSPA1-T-EE-00395
[6 empty] | Return Date | 2019-03-22: 2018-08-24; 2019-04-19: 2018-08-24
Owner Cmmt* | bar: 2019-03-22 to 2019-04-19
| EE | OL1-2E92-0003 | Coordination Procedure For ETAP |  | Class 2 | Purpose** | IFR | IFI | IFI | IFI | IFI | IMP
[6 empty] | Rev. | 2019-03-22: 0; 2019-04-19: A; 2019-04-19: A; 2019-05-16: 0
[6 empty] | Issue Plan | 2019-03-22: 2018-10-14; 2019-05-17: 2018-12-03
[6 empty] | Revised Plan | 2019-04-19: 2018-08-06; 2019-04-19: 2018-08-07; 2019-05-16: 2018-12-05
[6 empty] | Issue Actual | 2019-04-19: 2018-08-06; 2019-04-19: 2018-08-07; 2019-05-16: 2018-12-05
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-EE-00426; 2019-04-19: TPSK-LSPA1-T-EE-00008; 2019-04-19: TPSK-LSPA1-T-EE-00008; 2019-05-16: TPSK-LSPA1-T-EE-00426
[6 empty] | Return Date | 2019-04-19: 2018-08-24; 2019-04-19: 2018-08-24
Owner Cmmt* | bar: 2019-04-19 to 2019-04-19
Category Code: E93 Policy , Guidelines & Memo
Category Code: E94 Forms & Templates
Category Code: E95 Progress/Status Reports
Category Code: F26 Hydraulic Calculation for Fixed FF Systems
| FF | OL1-2F26-0002 | Hydraulic Calculation For Firewater Deluge / Water Spray System |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-04-22; 2019-04-19: 2020-03-06; 2019-04-19: 2020-05-29; 2019-05-16: 2020-06-08; 2019-05-17: 2020-09-08
[6 empty] | Revised Plan | 2019-04-19: 2020-03-06; 2019-04-19: 2020-05-29; 2019-05-16: 2020-06-08; 2019-05-17: 2020-09-08
[6 empty] | Issue Actual | 2019-03-22: 2019-04-22
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-FF-01424; 2019-03-22: TPSK-LSPA1-T-FF-01424
[6 empty] | Return Date | 2019-03-22: 2019-06-07; 2019-03-22: 2019-06-07
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
| FF | OL1-2F26-0003 | DELUGE NOZZLES ARRANGEMENT CALCULATION NOTE |  |  | Purpose** | 2019-03-22: IFR; 2019-03-22: IFR; 2019-04-19: IMP
Rev. | bar: 2019-03-22 to 2019-03-22
[6 empty] | Issue Plan | 2019-03-22: 2019-09-17; 2019-04-19: 2020-03-06
[6 empty] | Revised Plan | 2019-04-19: 2020-03-06
[6 empty] | Issue Actual | 2019-03-22: 2019-04-19; 2019-03-22: 2019-04-19
[6 empty] | Transmittal no. | 2019-03-22: TPSK-LSPA1-T-FF-01418; 2019-03-22: TPSK-LSPA1-T-FF-01418
[6 empty] | Return Date | 2019-03-22: 2019-06-07; 2019-03-22: 2019-06-07
Owner Cmmt* | bar: 2019-03-22 to 2019-03-22
Category Code: F30 Fire Fighting Layout
| FF | OL1-2F30-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 0S ELECTRICAL SUBSTATION & FAR E |  |  | Purpose** | IFR | IFR | IFR | IFR | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | C | C | D
[6 empty] | Issue Plan | IFR: 2019-04-10; IBD: 2019-06-07; IDD: 2019-09-23; IFC: 2020-04-06
[6 empty] | Revised Plan | IDD: 2019-09-23; IFC: 2020-04-06
[6 empty] | Issue Actual | 2019-04-08 | 2019-04-08 | 2019-05-02 | 2019-05-08 | 2019-05-09 | 2019-08-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01519 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-02441
[6 empty] | Return Date | IFR: 2019-05-10; IFR: 2019-05-10; IFR: 2019-05-29; IFR: 2019-05-29
Owner Cmmt* | bar: IFR to IFR; IFR to IFR
| FF | OL1-2F30-0002 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 3S ELECTRICAL SUBSTATION & FAR C |  |  | Purpose** | IFR | IFR | IFR | IFR | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | C | C | D
[6 empty] | Issue Plan | IFR: 2019-04-10; IBD: 2019-06-07; IDD: 2019-09-23; IFC: 2020-04-06
[6 empty] | Revised Plan | IDD: 2019-09-23; IFC: 2020-04-06
[6 empty] | Issue Actual | 2019-04-08 | 2019-04-08 | 2019-05-02 | 2019-05-08 | 2019-05-09 | 2019-08-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01519 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-02441
[6 empty] | Return Date | IFR: 2019-05-10; IFR: 2019-05-10; IFR: 2019-05-29; IFR: 2019-05-29
Owner Cmmt* | bar: IFR to IFR; IFR to IFR
| FF | OL1-2F30-0003 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5T COOLING WATER UNIT |  |  | Purpose** | IFR | IFR | IFR | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | C | C | D | D
[6 empty] | Rev.: Issue Plan; IFR A: 2019-04-10; IBD D: 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Rev.: Revised Plan | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-04-08 | 2019-04-08 | 2019-05-02 | 2019-05-08 | 2019-05-09 | 2019-07-08 | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01519 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-02091 | TPSK-LSPA1-T-FF-02091
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2 | R2
| FF | OL1-2F30-0004 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5W WASTE WATER TREATMENT |  |  | Purpose** | IFR | IFR | IFR | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | C | C | D | D
[6 empty] | Rev.: Issue Plan; IFR A: 2019-04-10; IBD D: 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Rev.: Revised Plan | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-04-08 | 2019-04-08 | 2019-05-02 | 2019-05-08 | 2019-05-09 | 2019-07-08 | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01519 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-02091 | TPSK-LSPA1-T-FF-02091
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2 | R2
| FF | OL1-2F30-0005 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5U UTILITIES |  |  | Purpose** | IFR | IFR | IFR | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | C | C | D | D
[6 empty] | Rev.: Issue Plan; IFR A: 2019-04-10; IBD D: 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Rev.: Revised Plan | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-04-08 | 2019-04-08 | 2019-05-02 | 2019-05-08 | 2019-05-09 | 2019-07-08 | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01519 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-02091 | TPSK-LSPA1-T-FF-02091
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2 | R2
| FF | OL1-2F30-0006 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 5F HP & POLYOLEFINS FLARES UNIT |  |  | Purpose** | IFR | IFR | IFR | IFR | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | C | C
[6 empty] | Issue Plan | IFR: 2019-04-10; IBD: 2019-06-07; IDD: 2019-09-23; IFC: 2020-04-06
[6 empty] | Revised Plan | IBD: 2019-08-22; IDD: 2019-09-23; IFC: 2020-04-06
[6 empty] | Issue Actual | 2019-04-08 | 2019-04-08 | 2019-05-02 | 2019-05-08 | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01519 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-01612
[6 empty] | Return Date | IFR: 2019-05-10; IFR: 2019-05-10; IFR: 2019-05-29; IFR: 2019-05-29
Owner Cmmt* | bar: IFR to IFR; IFR to IFR
| FF | OL1-2F30-0007 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 0M METERING STATION |  |  | Purpose** | IFR | IFR | IFR | IFR | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | C | C
[6 empty] | Issue Plan | IFR: 2019-04-10; IBD: 2019-06-07; IDD: 2019-09-23; IFC: 2020-04-06
[6 empty] | Revised Plan | IBD: 2019-08-22; IDD: 2019-09-23; IFC: 2020-04-06
[6 empty] | Issue Actual | 2019-04-08 | 2019-04-08 | 2019-05-02 | 2019-05-08 | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01519 | TPSK-LSPA1-T-FF-0612 | TPSK-LSPA1-T-FF-0612
[6 empty] | Return Date | IFR: 2019-05-10; IFR: 2019-05-10; IFR: 2019-05-29; IFR: 2019-05-29
Owner Cmmt* | bar: IFR to IFR; IFR to IFR
| FF | OL1-2F30-0009 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 1B FURNACES UTILITIES |  |  | Purpose** | IFR | IFR | IFR | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | C | C | D | D
[6 empty] | Rev.: Issue Plan; IFR A: 2019-04-10; IBD D: 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Rev.: Revised Plan | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-04-08 | 2019-04-08 | 2019-05-02 | 2019-05-08 | 2019-05-09 | 2019-07-08 | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01519 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-02091 | TPSK-LSPA1-T-FF-02091
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2 | R2
| FF | OL1-2F30-0010 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2A QUENCH |  |  | Purpose** | IFR | IFR | IFR | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | C | C | D | D
[6 empty] | Rev.: Issue Plan; IFR A: 2019-04-10; IBD D: 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Rev.: Revised Plan | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-04-08 | 2019-04-08 | 2019-05-02 | 2019-05-08 | 2019-05-09 | 2019-07-08 | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01519 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-02091 | TPSK-LSPA1-T-FF-02091
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2 | R2
| FF | OL1-2F30-0011 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2B C3 HYDROGENATION |  |  | Purpose** | IFR | IFR | IFR | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | C | C | D | D
[6 empty] | Rev.: Issue Plan; IFR A: 2019-04-10; IBD D: 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Rev.: Revised Plan | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-04-08 | 2019-04-08 | 2019-05-02 | 2019-05-08 | 2019-05-09 | 2019-07-08 | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01519 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-02091 | TPSK-LSPA1-T-FF-02091
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2 | R2
| FF | OL1-2F30-0012 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2D PROCESS COLD COMPRESSOR |  |  | Purpose** | IFR | IFR | IFR | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | C | C | D | D
[6 empty] | Rev.: Issue Plan; IFR A: 2019-04-10; IBD D: 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Rev.: Revised Plan | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-04-08 | 2019-04-08 | 2019-05-02 | 2019-05-08 | 2019-05-09 | 2019-07-08 | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01519 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-02091 | TPSK-LSPA1-T-FF-02091
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2 | R2
| FF | OL1-2F30-0013 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2E CRACKED GAS COMPRESSOR |  |  | Purpose** | IFR | IFR | IFR | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | C | C | D | D
[6 empty] | Rev.: Issue Plan; IFR A: 2019-04-10; IBD D: 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Rev.: Revised Plan | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-04-08 | 2019-04-08 | 2019-05-02 | 2019-05-08 | 2019-05-09 | 2019-07-08 | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01519 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-02091 | TPSK-LSPA1-T-FF-02091
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2 | R2
| FF | OL1-2F30-0014 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 3A BUTADIENE EXTRACTION UNIT |  |  | Purpose** | IFR | IFR | IFR | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | C | C | D | D
[6 empty] | Rev.: Issue Plan; IFR A: 2019-04-10; IBD D: 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Rev.: Revised Plan | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-04-08 | 2019-04-08 | 2019-05-02 | 2019-05-08 | 2019-05-09 | 2019-07-08 | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01519 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-02091 | TPSK-LSPA1-T-FF-02091
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2 | R2
| FF | OL1-2F30-0015 | FIRE PROTECTION & FIREFIGHTING LAYOUT - ZONE 2C HOT FRACTIONATION/GHU UNIT |  |  | Purpose** | IFR | IFR | IFR | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | C | C | D | D
[6 empty] | Rev.: Issue Plan; IFR A: 2019-04-10; IBD D: 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Rev.: Revised Plan | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-04-08 | 2019-04-08 | 2019-05-02 | 2019-05-08 | 2019-05-09 | 2019-07-08 | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01270 | TPSK-LSPA1-T-FF-01519 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-01612 | TPSK-LSPA1-T-FF-02091 | TPSK-LSPA1-T-FF-02091
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2 | R2
Category Code: F40 Fire and Gas Layout
| FF | OL1-2F40-5002 | FIRE & GAS DEVICES LAYOUT METERING |  |  | Purpose** | IFR | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-06-15 |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan |  |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01119 | TPSK-LSPA1-T-FF-01119 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| FF | OL1-2F40-5003 | FIRE & GAS DEVICES LAYOUT MAIN PIPE RACK |  |  | Purpose** | IFR | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-06-15 |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan |  |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01119 | TPSK-LSPA1-T-FF-01119 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| FF | OL1-2F40-5004 | FIRE & GAS DEVICES LAYOUT AREA SUBSTATION E & FAR E |  |  | Purpose** | IFR | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-06-15 |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan |  |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| FF | OL1-2F40-5005 | FIRE & GAS DEVICES LAYOUT AREA SUBSTATION C & FAR C |  |  | Purpose** | IFR | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-06-15 |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan |  |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| FF | OL1-2F40-5006 | FIRE & GAS DEVICES LAYOUT FURNACES UTILITY |  |  | Purpose** | IFR | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-06-15 |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan |  |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| FF | OL1-2F40-5007 | FIRE & GAS DEVICES LAYOUT QUENCH |  |  | Purpose** | IFR | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-06-15 |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan |  |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| FF | OL1-2F40-5008 | FIRE & GAS DEVICES LAYOUT PROCESS 20B |  |  | Purpose** | IFR | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-06-15 |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan |  |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| FF | OL1-2F40-5009 | FIRE & GAS DEVICES LAYOUT PROCESS 20C |  |  | Purpose** | IFR | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-06-15 |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan |  |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-21 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| FF | OL1-2F40-5010 | FIRE & GAS DEVICES LAYOUT PROCESS COLD COMPRESSORS |  |  | Purpose** | IFR | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-06-15 |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan |  |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| FF | OL1-2F40-5011 | FIRE & GAS DEVICES LAYOUT PROCESS CGC |  |  | Purpose** | IFR | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-06-15 |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan |  |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| FF | OL1-2F40-5012 | FIRE & GAS DEVICES LAYOUT BUTADIENE |  |  | Purpose** | IFR | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-06-15 |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan |  |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| FF | OL1-2F40-5013 | FIRE & GAS DEVICES LAYOUT COOLING WATER UNIT |  |  | Purpose** | IFR | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-06-15 |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan |  |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| FF | OL1-2F40-5014 | FIRE & GAS DEVICES LAYOUT UTILITIES |  |  | Purpose** | IFR | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-06-15 |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan |  |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| FF | OL1-2F40-5015 | FIRE & GAS DEVICES LAYOUT WASTE WATER TREATMENT |  |  | Purpose** | IFR | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-06-15 |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan |  |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| FF | OL1-2F40-5016 | FIRE & GAS DEVICES LAYOUT FLARE AREA |  |  | Purpose** | IFR | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-06-15 |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan |  |  |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 | 2019-05-31
[6 empty] | Owner Cmmt* | R2 | R2 | R2
Category Code: F41 Fire and Gas Detector C&E
| FF | OL1-2F41-5001 | FIRE AND GAS CAUSE & EFFECT CHART FAR-E SYSTEM |  |  | Rev.: Purpose**; IFR A: IFR; IFR A: IDD; IFR B: IFC
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-06-07 | 2020-09-30
[6 empty] | Revised Plan | 2020-02-28 | 2020-06-07 | 2020-09-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F41-5002 | FIRE AND GAS CAUSE & EFFECT CHART FAR-C SYSTEM |  |  | Rev.: Purpose**; IFR A: IFR; IFR A: IDD; IFR B: IFC
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-06-07 | 2020-09-30
[6 empty] | Revised Plan | 2020-02-28 | 2020-06-07 | 2020-09-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F41-5003 | FIRE AND GAS CAUSE & EFFECT CHART CCB SYSTEM |  |  | Rev.: Purpose**; IFR A: IFR; IFR A: IDD; IFR B: IFC
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-06-07 | 2020-09-30
[6 empty] | Revised Plan | 2020-02-28 | 2020-06-07 | 2020-09-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: F71 Appraisal Report for Consultancy Service
Category Code: F72 Appraisal Report for EPC Contractor Work
Category Code: F73 Appraisal Report for Vendor/Supplier
Category Code: F75 Escape Ways Drawing
| FF | OL1-2F75-0001 | Life Saving Equipment and Escape Route Layout - Zone 0S Electrical Sub-station and Far E |  | Class 2 | Purpose** | IFR | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-04-10 |  | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan |  |  | 2019-08-22 | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10 | 2019-05-10
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F75-0002 | Life Saving Equipment and Escape Route Layout - Zone 3S Electrical Sub-station and Far C |  | Class 2 | Purpose** | IFR | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-04-10 |  | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan |  |  | 2019-08-22 | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10 | 2019-05-10
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F75-0003 | Life Saving Equipment and Escape Route Layout - Zone 5T Cooling Water Unit |  | Class 2 | Purpose** | IFR | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-04-10 |  | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan |  |  |  | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10 | 2019-05-10
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F75-0004 | Life Saving Equipment and Escape Route Layout - Zone 5W Waste Water Treatment |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-04-10 |  | 2019-06-07 |  | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan |  |  |  |  | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-03-29 | 2019-07-03 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02050 | TPSK-LSPA1-T-FF-02050
[6 empty] | Return Date | 2019-05-10 | 2019-05-10
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F75-0005 | Life Saving Equipment and Escape Route Layout - Zone 5U Utilities |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-04-10 |  | 2019-06-07 |  | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan |  |  |  |  | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-03-29 | 2019-07-03 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-07-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| FF | OL1-2F75-0006 | Life Saving Equipment and Escape Route Layout - Zone 5F HP & Polyoleffins Flares Unit |  | Class 2 | Purpose** | IFR | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-04-10 |  | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan |  |  | 2019-08-22 | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10 | 2019-05-10
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F75-0007 | Life Saving Equipment and Escape Route Layout - Zone 0M Metering Station |  | Class 2 | Purpose** | IFR | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-04-10 |  | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan |  |  | 2019-08-22 | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10 | 2019-05-10
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F75-0009 | Life Saving Equipment and Escape Route Layout - - Zone 1B Furnaces Utility |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-04-10 |  | 2019-06-07 |  | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan |  |  |  |  | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-03-29 | 2019-07-03 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-07-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| FF | OL1-2F75-0010 | Life Saving Equipment and Escape Route Layout - Zone 2A Quench |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-04-10 |  | 2019-06-07 |  | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan |  |  |  |  | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-03-29 | 2019-07-03 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-07-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| FF | OL1-2F75-0011 | Life Saving Equipment and Escape Route Layout - Zone 2B C3 Hydrogenation |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-04-10 |  | 2019-06-07 |  | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan |  |  |  |  | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-03-29 | 2019-07-03 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-07-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| FF | OL1-2F75-0012 | Life Saving Equipment and Escape Route Layout - Zone 2D Process Cold Compressor |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-04-10 |  | 2019-06-07 |  | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan |  |  |  |  | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-03-29 | 2019-07-03 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-07-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| FF | OL1-2F75-0013 | Life Saving Equipment and Escape Route Layout - Zone 2E Cracked Gas Compressor |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-04-10 |  | 2019-06-07 |  | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan |  |  |  |  | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-03-29 | 2019-07-03 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-07-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| FF | OL1-2F75-0014 | Life Saving Equipment and Escape Route Layout - Zone 3A Butadiene Extraction Unit |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-04-10 |  | 2019-06-07 |  | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan |  |  |  |  | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-03-29 | 2019-07-03 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10 | 2019-05-10 |  | 2019-07-29
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| FF | OL1-2F75-0015 | Life Saving Equipment and Escape Route Layout - Zone 2C Hot Fractionation/GHU Unit |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-04-10 |  | 2019-06-07 |  | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan |  |  |  |  | 2019-09-23 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-03-29 | 2019-07-03 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10 | 2019-05-10
[6 empty] | Owner Cmmt* | R2 | R2
Category Code: F90 Vendor Document
Category Code: F91 Index/List
Category Code: F92 Procedures & Standards
| FF | OL1-2F92-0001 | Fire And Gas Detection |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR; IFR B: IMP
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-01-18 |  | 2019-02-15
[6 empty] | Revised Plan |  |  | 2019-09-06
[6 empty] | Issue Actual | 2019-03-21 | 2019-03-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01125 | TPSK-LSPA1-T-FF-01125
[6 empty] | Return Date | 2019-05-09 | 2019-05-09
[6 empty] | Owner Cmmt* | R1 | R1
Category Code: F93 Policy , Guidelines & Memo
Category Code: F94 Forms & Templates
Category Code: F95 Progress/Status Reports |  |  |  |  | Class 2 | Rev.: Purpose**
Category Code: G01 All Project Philosophies and Process design standard and All Project Studies Records | [5 empty] | Rev.: Rev.
| PE | OL1-2G01-0001 | JSD FOR P & ID PREPARATION |  |  | Purpose** | IFR | IFA | IFA | IMP | IMP
[6 empty] | Rev. |  | A | A | 0 | 0
[6 empty] | Issue Plan | 2018-07-31 |  |  | 2019-03-01
[6 empty] | Revised Plan |  | 2018-07-31 | 2018-07-31
[6 empty] | Issue Actual |  | 2018-07-31 | 2018-07-31 | 2019-03-01 | 2019-03-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00006 | TPSK-LSPA1-T-PE-00006 | TPSK-LSPA1-T-PE-00965 | TPSK-LSPA1-T-PE-00965
[6 empty] | Return Date |  | 2018-08-21 | 2018-08-21 | 2019-04-05 | 2019-04-05
[6 empty] | Owner Cmmt* |  |  |  | R2 | R2
| PE | OL1-2G01-0002 | Cold Box Design Specification |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2018-10-03 | 2018-10-04
[6 empty] | Issue Actual | 2018-10-03 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00123 | TPSK-LSPA1-T-PE-00123
[6 empty] | Return Date | 2018-10-12 | 2018-10-12
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G01-0003 | Plate-Fin Exchanger Design Specification |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2018-10-03 | 2018-10-04
[6 empty] | Issue Actual | 2018-10-03 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00123 | TPSK-LSPA1-T-PE-00123
[6 empty] | Return Date | 2018-10-12 | 2018-10-12
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G01-0004 | Tray Design Specification |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan |  | 2019-01-10
[6 empty] | Issue Actual |  | 2019-01-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00624 | TPSK-LSPA1-T-PE-00624
[6 empty] | Return Date | 2019-02-04 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1
Category Code: G02 Design Basis
| PE | OL1-2G02-0001 | PROCESS BASIS OF DESIGN |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2018-11-12 |  |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-07-27 | 2018-07-30
[6 empty] | Issue Actual |  | 2018-07-27 | 2018-07-30 | 2019-03-26 | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00002 | TPSK-LSPA1-T-PE-00002 | TPSK-LSPA1-T-PE-01154 | TPSK-LSPA1-T-PE-01154
[6 empty] | Return Date |  | 2018-08-17 | 2018-08-17 | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G02-0002 | EQUIPMENT BASIS OF DESIGN |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2018-11-12 |  |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-07-27 | 2018-07-30
[6 empty] | Issue Actual |  | 2018-07-27 | 2018-07-30 | 2019-03-26 | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00002 | TPSK-LSPA1-T-PE-00002 | TPSK-LSPA1-T-PE-01154 | TPSK-LSPA1-T-PE-01154
[6 empty] | Return Date |  | 2018-08-17 | 2018-08-17
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G02-0003 | FLARE AND BLOWDOWN SYSTEM BASIS OF DESIGN |  | Class 2 | Purpose** | IFR | IFA | IFA | IFD
[6 empty] | Rev. |  | A | A
[6 empty] | Issue Plan | 2018-09-04 |  |  | 2019-06-13
[6 empty] | Revised Plan |  | 2018-09-06 | 2018-09-07 | 2019-09-20
[6 empty] | Issue Actual |  | 2018-09-06 | 2018-09-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00034 | TPSK-LSPA1-T-PE-00034
[6 empty] | Return Date |  | 2018-09-28 | 2018-09-28
[6 empty] | Owner Cmmt* |  | R2 | R2
| PE | OL1-2G02-0006 | FURNACE BASIS OF DESIGN |  | Class 3 | Purpose** | IFR | IFA | IFA | IFF
[6 empty] | Rev. |  | A | A
[6 empty] | Issue Plan | 2018-07-31 |  |  | 2018-11-27
[6 empty] | Revised Plan |  | 2018-07-31 | 2018-07-31
[6 empty] | Issue Actual |  | 2018-07-31 | 2018-07-31
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00004 | TPSK-LSPA1-T-PE-00004
[6 empty] | Return Date |  | 2018-08-17 | 2018-08-17
[6 empty] | Owner Cmmt* |  | A3 | A3
Category Code: G03 Conceptual Design
Category Code: G04 Process Design Package
Category Code: G05 Equipment and Unit Functional Design
| PE | OL1-2G05-1001 | AREA BASIS OF DESIGN - 10 FEED |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2018-11-12 |  |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-08-07 | 2018-08-08
[6 empty] | Issue Actual |  | 2018-08-07 | 2018-08-08 | 2019-03-26 | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-01154 | TPSK-LSPA1-T-PE-01154
[6 empty] | Return Date |  | 2018-08-27 | 2018-08-27 | 2019-04-22 | 2019-04-22
[6 empty] | Owner Cmmt* |  | A3 | A3 | A1 | A1
| PE | OL1-2G05-1101 | SIZING OF STEAM DRUM & SUPERHEATER PSVS |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR; IFR B: IFF
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-01-10 |  | 2019-01-10
[6 empty] | Revised Plan |  |  | 2019-10-15
[6 empty] | Issue Actual | 2019-01-30 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00769 | TPSK-LSPA1-T-PE-00769
[6 empty] | Return Date | 2019-03-21 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G05-1201 | Steam Drum and Superheater PSVs Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-01-30 | 2019-01-31 | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-01-30 | 2019-01-31 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00769 | TPSK-LSPA1-T-PE-00769 | TPSK-LSPA1-T-PE-01513 | TPSK-LSPA1-T-PE-01513
[6 empty] | Return Date | 2019-03-21 | 2019-03-21 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G05-2001 | AREA BASIS OF DESIGN - 20/21 QUENCH |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2018-11-12 |  |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-08-07 | 2018-08-08
[6 empty] | Issue Actual |  | 2018-08-07 | 2018-08-08 | 2019-04-02 | 2019-04-03
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-01224 | TPSK-LSPA1-T-PE-01224
[6 empty] | Return Date |  | 2018-08-27 | 2018-08-27 | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R1
| PE | OL1-2G05-2101 | SIZING OF STEAM DRUM & SUPERHEATER PSVS |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-10
[6 empty] | Revised Plan |  | 2019-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G05-2201 | AREA BASIS OF DESIGN - 22/24 COMPRESSION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2018-11-12 |  |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-08-13 | 2018-08-15
[6 empty] | Issue Actual |  | 2018-08-13 | 2018-08-15 | 2019-04-08 | 2019-04-09
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00022 | TPSK-LSPA1-T-PE-00022 | TPSK-LSPA1-T-PE-01272 | TPSK-LSPA1-T-PE-01272
[6 empty] | Return Date |  | 2018-09-05 | 2018-09-05 | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G05-2301 | AREA BASIS OF DESIGN - 23 CAUSTIC |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C
[6 empty] | Issue Plan | 2018-11-12 |  |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-08-08 | 2018-08-09
[6 empty] | Issue Actual |  | 2018-08-08 | 2018-08-09 | 2019-04-11 | 2019-04-12 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00014 | TPSK-LSPA1-T-PE-00014 | TPSK-LSPA1-T-PE-01317 | TPSK-LSPA1-T-PE-01317 | TPSK-LSPA1-T-PE-02431
[6 empty] | Return Date |  | 2018-08-31 | 2018-08-31 | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G05-2501 | AREA BASIS OF DESIGN - 25 COLD FRACTIONATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2018-11-12 |  |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-08-07 | 2018-08-08
[6 empty] | Issue Actual |  | 2018-08-07 | 2018-08-08 | 2019-04-08 | 2019-04-09
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-01276 | TPSK-LSPA1-T-PE-01276
[6 empty] | Return Date |  | 2018-08-27 | 2018-08-27
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G05-2601 | AREA BASIS OF DESIGN - 26 HOT FRACTIONATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2018-11-12 |  |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-08-08 | 2018-08-09
[6 empty] | Issue Actual |  | 2018-08-08 | 2018-08-09 | 2019-04-04 | 2019-04-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00014 | TPSK-LSPA1-T-PE-00014 | TPSK-LSPA1-T-PE-01249 | TPSK-LSPA1-T-PE-01249
[6 empty] | Return Date |  | 2018-08-31 | 2018-08-31 | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R1
| PE | OL1-2G05-2602 | AREA BASIS OF DESIGN - 262 C3 HYDROGENATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2018-11-12 |  |  | 2019-02-25
[6 empty] | Revised Plan |  |  | 2018-11-12
[6 empty] | Issue Actual |  |  | 2018-11-12 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00307 | TPSK-LSPA1-T-PE-00307 | TPSK-LSPA1-T-PE-01510 | TPSK-LSPA1-T-PE-01510
[6 empty] | Return Date |  | 2019-02-04 | 2019-02-04 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* |  | A1 | A1 | R2 | R2
| PE | OL1-2G05-2701 | AREA BASIS OF DESIGN - 270 GHU-1 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2018-11-12 |  |  | 2019-02-25
[6 empty] | Revised Plan |  |  | 2018-11-12
[6 empty] | Issue Actual |  |  | 2018-11-12 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00307 | TPSK-LSPA1-T-PE-00307 | TPSK-LSPA1-T-PE-01510 | TPSK-LSPA1-T-PE-01510
[6 empty] | Return Date |  | 2019-02-04 | 2019-02-04 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* |  | A1 | A1 | R2 | R2
| PE | OL1-2G05-2702 | AREA BASIS OF DESIGN - 275 C4/C5 HYDROGENATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2018-11-12 |  |  | 2019-02-25
[6 empty] | Revised Plan |  |  | 2018-11-12
[6 empty] | Issue Actual |  |  | 2018-11-12 | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00307 | TPSK-LSPA1-T-PE-00307 | TPSK-LSPA1-T-PE-01667 | TPSK-LSPA1-T-PE-01667
[6 empty] | Return Date |  | 2019-02-04 | 2019-02-04 | 2019-06-21 | 2019-06-21
[6 empty] | Owner Cmmt* |  | A1 | A1 | R2 | R2
| PE | OL1-2G05-2801 | AREA BASIS OF DESIGN - 28 REFRIG |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2018-11-12 |  |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-08-13 | 2018-08-15
[6 empty] | Issue Actual |  | 2018-08-13 | 2018-08-15 | 2019-04-02 | 2019-04-03
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00022 | TPSK-LSPA1-T-PE-00022 | TPSK-LSPA1-T-PE-01224 | TPSK-LSPA1-T-PE-01224
[6 empty] | Return Date |  | 2018-09-05 | 2018-09-05 | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* |  | A1 | A1 | R1 | R1
| PE | OL1-2G05-3001 | AREA BASIS OF DESIGN - 30 BDU |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2018-11-12 |  |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-10-09 | 2018-10-10
[6 empty] | Issue Actual |  | 2018-10-09 | 2018-10-10 | 2019-06-20 | 2019-06-20
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00150 | TPSK-LSPA1-T-PE-00150 | TPSK-LSPA1-T-PE-01932 | TPSK-LSPA1-T-PE-01932
[6 empty] | Return Date |  | 2019-04-02 | 2019-04-02 | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* |  | R2 | R2 | R2 | R2
| PE | OL1-2G05-5001 | AREA BASIS OF DESIGN - 50 ISBL SUPPORTING UTILITIES |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD
[6 empty] | Rev. |  | A | A
[6 empty] | Issue Plan | 2018-11-12 |  |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-07-31 | 2018-07-31 | 2019-08-19
[6 empty] | Issue Actual |  | 2018-07-31 | 2018-07-31
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00003 | TPSK-LSPA1-T-PE-00003
[6 empty] | Return Date |  | 2018-08-17 | 2018-08-17
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G05-5301 | AREA BASIS OF DESIGN - 53 COOLING WATER TOWER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2018-08-09 |  |  | 2019-03-21
[6 empty] | Revised Plan |  | 2018-07-31 | 2018-07-31 | 2019-08-30
[6 empty] | Issue Actual |  | 2018-07-31 | 2018-07-31 | 2018-09-26 | 2018-09-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00003 | TPSK-LSPA1-T-PE-00003 | TPSK-LSPA1-T-PE-00003 | TPSK-LSPA1-T-PE-00003
[6 empty] | Return Date |  | 2018-08-17 | 2018-08-17
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G05-5501 | AREA BASIS OF DESIGN - 55 FLARE SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD
[6 empty] | Rev. |  | A | A
[6 empty] | Issue Plan | 2018-08-09 |  |  | 2019-03-21
[6 empty] | Revised Plan |  | 2018-08-09 | 2018-08-10 | 2019-08-30
[6 empty] | Issue Actual |  | 2018-08-09 | 2018-08-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00016 | TPSK-LSPA1-T-PE-00016
[6 empty] | Return Date |  | 2018-08-29 | 2018-08-29
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G05-5601 | AREA BASIS OF DESIGN - 56 WASTEWATER TREATMENT SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-08-09 |  |  | 2019-03-21
[6 empty] | Revised Plan |  | 2018-08-07 | 2018-08-08 | 2019-08-30
[6 empty] | Issue Actual |  | 2018-08-07 | 2018-08-08 | 2018-09-26 | 2018-09-27 | 2019-02-25 | 2019-02-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-00091 | TPSK-LSPA1-T-PE-00091 | TPSK-LSPA1-T-PE-00920 | TPSK-LSPA1-T-PE-00920
[6 empty] | Return Date |  | 2018-08-27 | 2018-08-27 | 2018-10-12 | 2018-10-12 | 2019-03-29 | 2019-03-29
[6 empty] | Owner Cmmt* |  | A3 | A3 | A3 | A3 | R1 | R1
Category Code: G06 Process simulation model |  |  |  |  | Class 2 | Rev.: Purpose**
Category Code: G20 Design calculations | [5 empty] | Rev.: Rev.
Category Code: G21 Hydraulic Calculation | [5 empty] | Rev.: Issue Plan
| PE | OL1-2G21-12XX | HYDRAULICS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan |  |  |  | 2019-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G21-13XX | HYDRAULICS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan |  |  |  | 2019-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G21-14XX | HYDRAULICS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan |  |  |  | 2019-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G21-15XX | HYDRAULICS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan |  |  |  | 2019-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G21-16XX | HYDRAULICS |  | Class 2 | Purpose** | IFR | IBD | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan |  |  |  | 2019-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G22 Flare Calculation
| PE | OL1-2G22-0001 | FLARE LOAD SUMMARY |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2018-10-25 |  | 2019-06-20 | 2019-10-10
[6 empty] | Revised Plan |  |  | 2019-09-13 | 2019-10-10
[6 empty] | Issue Actual |  | 2018-10-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00229 | TPSK-LSPA1-T-PE-00229
[6 empty] | Return Date | 2018-11-14 | 2018-11-14
[6 empty] | Owner Cmmt* | R2 | R2
Category Code: G23 Sizing data for the relief and blowdown systems
| PE | OL1-2G23-1001 | PSV-1001 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-1002 | PSV-1002 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380 | TPSK-LSPA1-T-PE-01380
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-1003 | PSV-1003 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380 | TPSK-LSPA1-T-PE-01380
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-1004 | PSV-1004 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380 | TPSK-LSPA1-T-PE-01380
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-1006 | PSV-1006 and PSV-1009 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-1007 | PSV-1007 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-1008 | PSV-1008 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380 | TPSK-LSPA1-T-PE-01380
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-1010 | PSV-1010 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-1011 | PSV-1011 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380 | TPSK-LSPA1-T-PE-01380
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-1012 | PSV-1012 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-1015 | PSV-1015 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-1016 | PSV-1016 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380 | TPSK-LSPA1-T-PE-01380
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-1901 | PSV-1911 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25 | 2019-04-26
[6 empty] | Issue Actual | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488 | TPSK-LSPA1-T-PE-01488
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-1902 | PSV-1912 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25 | 2019-04-26
[6 empty] | Issue Actual | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488 | TPSK-LSPA1-T-PE-01488
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2001 | PSV-2005 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2002 | PSV-2006 A-C Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2003 | PSV-2010 A-E Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2004 | PSV-2016 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2005 | PSV-2020 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2006 | PSV-2025 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2007 | PSV-2030 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-05 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-05 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2008 | PSV-2017 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2009 | PSV-2028 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-05 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-05 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2010 | PSV-2027 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-05 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-05 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2011 | PSV-2011 A-B-C-D-E Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-05 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-05 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2012 | PSV-2018 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-05 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-05 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2101 | PSV-2105 A-O Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-07 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-07 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date |  | 2019-07-11
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2102 | PSV-2108 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-05 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-05 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date |  | 2019-07-09
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2103 | PSV-2111 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-05 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-05 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date |  | 2019-07-09
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2104 | PSV-2115 A-E Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-06 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-06 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01822 | TPSK-LSPA1-T-PE-01822
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2105 | PSV-2120 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-06 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-06 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01822 | TPSK-LSPA1-T-PE-01822
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2106 | PSV-2125 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | B | A | A | B
Issue Plan
[6 empty] | Revised Plan |  | 2019-06-05 | 2019-06-10 | 2019-06-11
[6 empty] | Issue Actual |  | 2019-06-05 | 2019-06-10 | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873 | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01873
[6 empty] | Return Date |  |  | 2019-07-09
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G23-2108 | PSV-2131 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-07 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-07 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date |  | 2019-07-15
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2109 | PSV-2130 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-05 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-05 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date |  | 2019-07-09
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2110 | PSV-2135 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-05 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-05 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date |  | 2019-07-09
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2111 | PSV-2136 Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | B | A | A | B
Issue Plan
[6 empty] | Revised Plan |  | 2019-05-29 | 2019-05-30 | 2019-06-11
[6 empty] | Issue Actual |  | 2019-05-29 | 2019-05-30 | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873 | TPSK-LSPA1-T-PE-01763 | TPSK-LSPA1-T-PE-01763 | TPSK-LSPA1-T-PE-01873
[6 empty] | Return Date |  |  | 2019-06-25
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G23-2112 | PSV-2145 A-B-C-D Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | B | A | A | B
Issue Plan
[6 empty] | Revised Plan |  | 2019-06-07 | 2019-06-10 | 2019-06-11
[6 empty] | Issue Actual |  | 2019-06-07 | 2019-06-10 | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873 | TPSK-LSPA1-T-PE-01831 | TPSK-LSPA1-T-PE-01831 | TPSK-LSPA1-T-PE-01873
[6 empty] | Return Date |  |  | 2019-07-09
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G23-2113 | PSV-2146 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-29 | 2019-05-30
[6 empty] | Issue Actual | 2019-05-29 | 2019-05-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01763 | TPSK-LSPA1-T-PE-01763
[6 empty] | Return Date |  | 2019-06-25
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2116 | PSV-2165 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-07 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-07 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2117 | PSV-2166 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-06 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-06 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01822 | TPSK-LSPA1-T-PE-01822
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2118 | PSV-2132 Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-05 | 2019-06-10 | 2019-06-12 | 2019-06-14
[6 empty] | Issue Actual | 2019-06-05 | 2019-06-10 | 2019-06-12 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01883 | TPSK-LSPA1-T-PE-01883
[6 empty] | Return Date |  | 2019-07-09
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2119 | PSV-2126 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-05 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-05 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date |  | 2019-07-09
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2120 | PSV-2113 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-05 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-05 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date |  | 2019-07-09
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2201 | PSV-2201 Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25 | 2019-06-07 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25 | 2019-06-07 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01831 | TPSK-LSPA1-T-PE-01831
[6 empty] | Return Date | 2019-06-04 | 2019-06-04 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G23-2202 | PSV-2210 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2203 | PSV-2225 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2204 | PSV-2230 Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25 | 2019-06-07 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25 | 2019-06-07 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01831 | TPSK-LSPA1-T-PE-01831
[6 empty] | Return Date | 2019-06-04 | 2019-06-04 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G23-2205 | PSV-2235 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2206 | PSV-2246 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01475 | TPSK-LSPA1-T-PE-01475
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2207 | PSV-2255 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2208 | PSV-2260 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2209 | PSV-2265 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2210 | PSV-2266 A-B Sizing Calulation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25 | 2019-06-07 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25 | 2019-06-07 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01475 | TPSK-LSPA1-T-PE-01475 | TPSK-LSPA1-T-PE-01831 | TPSK-LSPA1-T-PE-01831
[6 empty] | Return Date | 2019-05-29 | 2019-05-29 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G23-2301 | PSV-2301 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-28 | 2019-05-29
[6 empty] | Issue Actual | 2019-05-28 | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759 | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2302 | PSV-2310 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-28 | 2019-05-29
[6 empty] | Issue Actual | 2019-05-28 | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759 | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21 | 2019-06-21
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2303 | PSV-2316 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-30 | 2019-05-02 | 2019-05-20 | 2019-05-21
[6 empty] | Issue Actual | 2019-04-30 | 2019-05-02 | 2019-05-20 | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01530 | TPSK-LSPA1-T-PE-01530 | TPSK-LSPA1-T-PE-01698 | TPSK-LSPA1-T-PE-01698
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2304 | PSV-2322 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2305 | PSV-2327 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2306 | PSV-2332 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2307 | PSV-2335 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2308 | PSV-2341 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2309 | PSV-2343 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-05-20 | 2019-05-21
[6 empty] | Issue Actual | 2019-05-20 | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01698 | TPSK-LSPA1-T-PE-01698
Return Date
Owner Cmmt*
| PE | OL1-2G23-2390 | Process Datasheet for Restriction Orifice - Unit 23 |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-20 | 2019-06-20
[6 empty] | Issue Actual | 2019-06-20 | 2019-06-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01929 | TPSK-LSPA1-T-PE-01929
Return Date
Owner Cmmt*
| PE | OL1-2G23-2401 | PSV-2401 Sizing Calculaiton |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2402 | PSV-2403 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2403 | PSV-2405 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2404 | PSV-2407 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2405 | PSV-2408 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-04-25
[6 empty] | Issue Actual | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2406 | PSV-2410 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-22 | 2019-04-23
[6 empty] | Issue Actual | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435 | TPSK-LSPA1-T-PE-01435
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2407 | PSV-2411 Sizing Calcuation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-22 | 2019-04-23
[6 empty] | Issue Actual | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435 | TPSK-LSPA1-T-PE-01435
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2408 | PSV-2414 Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29 | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29 | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508 | TPSK-LSPA1-T-PE-01508 | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-03 | 2019-06-03 | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G23-2409 | PSV-2415 Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-30 | 2019-05-02 | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-04-30 | 2019-05-02 | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01530 | TPSK-LSPA1-T-PE-01530 | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-03 | 2019-06-03 | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G23-2410 | PSV-2416 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508 | TPSK-LSPA1-T-PE-01508
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2411 | PSV-2418 A-D Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16 | 2019-05-17
[6 empty] | Issue Actual | 2019-05-16 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01680 | TPSK-LSPA1-T-PE-01680
Return Date
Owner Cmmt*
| PE | OL1-2G23-2412 | PSV-2419 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25 | 2019-04-26
[6 empty] | Issue Actual | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488 | TPSK-LSPA1-T-PE-01488
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2413 | PSV-2422 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2414 | PSV-2423 A-B-C Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2415 | PSV-2425 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16 | 2019-05-16 | 2019-05-17
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16 | 2019-05-16 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-01680 | TPSK-LSPA1-T-PE-01680
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2416 | PSV-2426 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2417 | PSV-2428 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2418 | PSV-2429 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-30 | 2019-05-02
[6 empty] | Issue Actual | 2019-04-30 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01530 | TPSK-LSPA1-T-PE-01530
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2419 | PSV-2431 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16 | 2019-05-16 | 2019-05-17
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16 | 2019-05-16 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-01680 | TPSK-LSPA1-T-PE-01680
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2420 | PSV-2432 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2422 | PSV-2435 A-D Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2423 | PSV-2436 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2424 | PSV-2437 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2425 | PSV-2438 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2426 | PSV-2441 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2427 | PSV-2443 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2428 | PSV-2444 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2429 | PSV-2445 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2430 | PSV-2446 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2431 | PSV-2447 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2432 | PSV-2448 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2433 | PSV-2449 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2434 | PSV-2450 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25 | 2019-04-26
[6 empty] | Issue Actual | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488 | TPSK-LSPA1-T-PE-01488
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2435 | PSV-2440 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2436 | PSV-2413 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-30 | 2019-05-02
[6 empty] | Issue Actual | 2019-04-30 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01530 | TPSK-LSPA1-T-PE-01530
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2437 | PSV-2452 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-20 | 2019-06-20
[6 empty] | Issue Actual | 2019-06-20 | 2019-06-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01924 | TPSK-LSPA1-T-PE-01924
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2490 | Process Datasheet for Restriction Orifice - Area 24 |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-20 | 2019-06-20
[6 empty] | Issue Actual | 2019-06-20 | 2019-06-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01929 | TPSK-LSPA1-T-PE-01929
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2501 | PSV-2504 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25 | 2019-04-26
[6 empty] | Issue Actual | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488 | TPSK-LSPA1-T-PE-01488
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2503 | PSV-2514 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25 | 2019-04-26
[6 empty] | Issue Actual | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488 | TPSK-LSPA1-T-PE-01488
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2504 | PSV-2517 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-22 | 2019-04-23
[6 empty] | Issue Actual | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435 | TPSK-LSPA1-T-PE-01435
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2505 | PSV-2520 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2506 | PSV-2522 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01382 | TPSK-LSPA1-T-PE-01382
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2507 | PSV-2524 Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-25 | 2019-04-26 | 2019-04-30 | 2019-05-02
[6 empty] | Issue Actual | 2019-04-25 | 2019-04-26 | 2019-04-30 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488 | TPSK-LSPA1-T-PE-01488 | TPSK-LSPA1-T-PE-01530 | TPSK-LSPA1-T-PE-01530
[6 empty] | Return Date |  |  | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* |  |  | R2 | R2
| PE | OL1-2G23-2508 | PSV-2525 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01382 | TPSK-LSPA1-T-PE-01382
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2509 | PSV-2530 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17 | 2019-04-18
[6 empty] | Issue Actual | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395 | TPSK-LSPA1-T-PE-01395
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2510 | PSV-2531 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01382 | TPSK-LSPA1-T-PE-01382
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2511 | PSV-2535 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17 | 2019-04-18
[6 empty] | Issue Actual | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395 | TPSK-LSPA1-T-PE-01395
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2512 | PSV-2539 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-22 | 2019-04-23
[6 empty] | Issue Actual | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435 | TPSK-LSPA1-T-PE-01435
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2513 | PSV-2540 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17 | 2019-04-18
[6 empty] | Issue Actual | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395 | TPSK-LSPA1-T-PE-01395
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2514 | PSV-2544 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-22 | 2019-04-23
[6 empty] | Issue Actual | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435 | TPSK-LSPA1-T-PE-01435
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2515 | PSV-2545 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-22 | 2019-04-23
[6 empty] | Issue Actual | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435 | TPSK-LSPA1-T-PE-01435
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2517 | PSV-2548 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17 | 2019-04-18
[6 empty] | Issue Actual | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395 | TPSK-LSPA1-T-PE-01395
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2518 | PSV-2550 A-B-C Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2519 | PSV-2551 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25 | 2019-04-26
[6 empty] | Issue Actual | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488 | TPSK-LSPA1-T-PE-01488
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2520 | PSV-2555 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17 | 2019-04-18
[6 empty] | Issue Actual | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395 | TPSK-LSPA1-T-PE-01395
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2521 | PSV-2553 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-22 | 2019-04-23
[6 empty] | Issue Actual | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435 | TPSK-LSPA1-T-PE-01435
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2522 | PSV-2560 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17 | 2019-04-18
[6 empty] | Issue Actual | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395 | TPSK-LSPA1-T-PE-01395
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2523 | PSV-2565 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-28 | 2019-05-29
[6 empty] | Issue Actual | 2019-05-28 | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759 | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21 | 2019-06-21
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2524 | PSV-2556 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17 | 2019-04-18
[6 empty] | Issue Actual | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395 | TPSK-LSPA1-T-PE-01395
[6 empty] | Return Date | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2601 | PSV-2626 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2602 | PSV-2639 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2603 | PSV-2633 A-B-C-D-E Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-05-28 | 2019-05-29 | 2019-06-12 | 2019-06-14
[6 empty] | Issue Actual | 2019-05-28 | 2019-05-29 | 2019-06-12 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759 | TPSK-LSPA1-T-PE-01759 | TPSK-LSPA1-T-PE-01883 | TPSK-LSPA1-T-PE-01883
[6 empty] | Return Date | 2019-06-21 | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2604 | PSV-2601 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805 | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2605 | PSV-2605 Sizinig Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805 | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2606 | PSV-2610 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805 | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2607 | PSV-2614 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805 | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2608 | PSV-2615 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805 | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2609 | PSV-2620 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805 | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2610 | PSV-2624 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805 | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2611 | PSV-2630 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805 | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2612 | PSV-2637 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805 | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2613 | PSV-2638 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805 | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2614 | PSV-2645 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805 | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2615 | PSV-2650 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2616 | PSV-2652 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805 | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2617 | PSV-2655 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805 | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2618 | PSV-2625 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2619 | PSV-2631 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2620 | PSV-2646 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2621 | PSV-2651 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-12 | 2019-06-14
[6 empty] | Issue Actual | 2019-06-12 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01883 | TPSK-LSPA1-T-PE-01883
Return Date
Owner Cmmt*
| PE | OL1-2G23-2622 | PSV 2616 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-2701 | PSV-2703 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-07 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-07 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01831 | TPSK-LSPA1-T-PE-01831
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2702 | PSV-2704 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-07 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-07 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01831 | TPSK-LSPA1-T-PE-01831
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2703 | PSV-2706 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-07 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-07 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2704 | PSV-2716 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-07 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-07 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2705 | PSV-2705 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-12 | 2019-06-14
[6 empty] | Issue Actual | 2019-06-12 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01883 | TPSK-LSPA1-T-PE-01883
Return Date
Owner Cmmt*
| PE | OL1-2G23-2707 | PSV-2715 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-12 | 2019-06-14
[6 empty] | Issue Actual | 2019-06-12 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01883 | TPSK-LSPA1-T-PE-01883
Return Date
Owner Cmmt*
| PE | OL1-2G23-2708 | PSV-2719 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911 | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2709 | PSV-2723 A-B-C-D Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-07 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-07 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2710 | PSV-2721 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan |  | 2019-06-11
[6 empty] | Issue Actual |  | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873 | TPSK-LSPA1-T-PE-01873
Return Date
Owner Cmmt*
| PE | OL1-2G23-2711 | PSV-2726 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911 | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2712 | PSV-2729 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911 | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2713 | PSV-2733 A-B-C-D-E Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-27 | 2019-06-27
[6 empty] | Issue Actual | 2019-06-27 | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02002 | TPSK-LSPA1-T-PE-02002
[6 empty] | Return Date | 2019-07-17 | 2019-07-17
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2714 | PSV-2734 A-B-C Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan |  | 2019-06-11
[6 empty] | Issue Actual |  | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873 | TPSK-LSPA1-T-PE-01873
Return Date
Owner Cmmt*
| PE | OL1-2G23-2715 | PSV-2737 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911 | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2716 | PSV-2738 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-12 | 2019-06-14
[6 empty] | Issue Actual | 2019-06-12 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01883 | TPSK-LSPA1-T-PE-01883
Return Date
Owner Cmmt*
| PE | OL1-2G23-2717 | PSV-2741 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911 | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2718 | PSV-2744 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911 | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2720 | PSV-2748 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911 | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2721 | PSV-2746 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911 | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2722 | PSV-2749 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911 | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2723 | PSV-2750 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911 | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2724 | PSV-2751 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-26 | 2019-06-26
[6 empty] | Issue Actual | 2019-06-26 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01983 | TPSK-LSPA1-T-PE-01983
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2725 | PSV-2755 Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-26 | 2019-06-26
[6 empty] | Issue Actual | 2019-06-26 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01983 | TPSK-LSPA1-T-PE-01983
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2726 | PSV-2760 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911 | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2727 | PSV-2761 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-26 | 2019-06-26
[6 empty] | Issue Actual | 2019-06-26 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01983 | TPSK-LSPA1-T-PE-01983
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2728 | PSV-2766 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911 | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2729 | PSV-2767 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-26 | 2019-06-26
[6 empty] | Issue Actual | 2019-06-26 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01988 | TPSK-LSPA1-T-PE-01988
[6 empty] | Return Date | 2019-07-17 | 2019-07-17
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2730 | PSV-2771 Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-26 | 2019-06-26
[6 empty] | Issue Actual | 2019-06-26 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01983 | TPSK-LSPA1-T-PE-01983
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2731 | PSV-2720 A-B-C Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan |  | 2019-06-11
[6 empty] | Issue Actual |  | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873 | TPSK-LSPA1-T-PE-01873
Return Date
Owner Cmmt*
| PE | OL1-2G23-2732 | PSV-2752 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-26 | 2019-06-26
[6 empty] | Issue Actual | 2019-06-26 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01983 | TPSK-LSPA1-T-PE-01983
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2733 | PSV-2707 AB Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan |  | 2019-06-11
[6 empty] | Issue Actual |  | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873 | TPSK-LSPA1-T-PE-01873
Return Date
Owner Cmmt*
| PE | OL1-2G23-2734 | PSV-2714 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan |  | 2019-06-11
[6 empty] | Issue Actual |  | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873 | TPSK-LSPA1-T-PE-01873
Return Date
Owner Cmmt*
| PE | OL1-2G23-2735 | PSV-2745 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-12 | 2019-06-14
[6 empty] | Issue Actual | 2019-06-12 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01883 | TPSK-LSPA1-T-PE-01883
Return Date
Owner Cmmt*
| PE | OL1-2G23-2736 | PSV-2768 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-27 | 2019-06-27
[6 empty] | Issue Actual | 2019-06-27 | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02002 | TPSK-LSPA1-T-PE-02002
[6 empty] | Return Date | 2019-07-17 | 2019-07-17
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2801 | PSV-2810 A-C Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508 | TPSK-LSPA1-T-PE-01508
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2802 | PSV-2815 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508 | TPSK-LSPA1-T-PE-01508
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2803 | PSV-2820 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508 | TPSK-LSPA1-T-PE-01508
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2804 | PSV-2805 A-D Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508 | TPSK-LSPA1-T-PE-01508
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2805 | PSV-2806 A-D Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508 | TPSK-LSPA1-T-PE-01508
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2806 | PSV-2823 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672 | TPSK-LPSA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2807 | PSV-2826 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672 | TPSK-LPSA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2808 | PSV-2829 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672 | TPSK-LPSA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2809 | PSV-2832 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16 | 2019-05-17
[6 empty] | Issue Actual | 2019-05-16 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01680 | TPSK-LSPA1-T-PE-01680
Return Date
Owner Cmmt*
| PE | OL1-2G23-2810 | PSV-2835 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672 | TPSK-LPSA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2811 | PSV-2836 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672 | TPSK-LPSA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2812 | PSV-2837 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16 | 2019-05-17
[6 empty] | Issue Actual | 2019-05-16 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01680 | TPSK-LSPA1-T-PE-01680
Return Date
Owner Cmmt*
| PE | OL1-2G23-2813 | PSV-2838 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672 | TPSK-LPSA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2814 | PSV-2839 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2815 | PSV-2841 A-D Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2816 | PSV-2842 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2817 | PSV-2843 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2818 | PSV-2845 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672 | TPSK-LPSA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2819 | PSV-2846 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2820 | PSV-2847 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2821 | PSV-2851 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2822 | PSV-2852 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2823 | PSV-2854 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2824 | PSV-2855 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16 | 2019-05-17
[6 empty] | Issue Actual | 2019-05-16 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01680 | TPSK-LSPA1-T-PE-01680
Return Date
Owner Cmmt*
| PE | OL1-2G23-2825 | PSV-2856 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2826 | PSV-2857 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-20 | 2019-05-21
[6 empty] | Issue Actual | 2019-05-20 | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01698 | TPSK-LSPA1-T-PE-01698
Return Date
Owner Cmmt*
| PE | OL1-2G23-2827 | PSV-2858 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-20 | 2019-05-21
[6 empty] | Issue Actual | 2019-05-20 | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01698 | TPSK-LSPA1-T-PE-01698
Return Date
Owner Cmmt*
| PE | OL1-2G23-2828 | PSV-2861 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-20 | 2019-05-21
[6 empty] | Issue Actual | 2019-05-20 | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01698 | TPSK-LSPA1-T-PE-01698
Return Date
Owner Cmmt*
| PE | OL1-2G23-2829 | PSV-2864 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-20 | 2019-05-21
[6 empty] | Issue Actual | 2019-05-20 | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01698 | TPSK-LSPA1-T-PE-01698
Return Date
Owner Cmmt*
| PE | OL1-2G23-2830 | PSV-2867 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-20 | 2019-05-21
[6 empty] | Issue Actual | 2019-05-20 | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01698 | TPSK-LSPA1-T-PE-01698
Return Date
Owner Cmmt*
| PE | OL1-2G23-2831 | PSV-2870 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-20 | 2019-05-21
[6 empty] | Issue Actual | 2019-05-20 | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01698 | TPSK-LSPA1-T-PE-01698
Return Date
Owner Cmmt*
| PE | OL1-2G23-2832 | PSV-2833 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-07 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-07 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-2901 | PSV-2925 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2902 | PSV-2926 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2903 | PSV-2928 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2904 | PSV-2929 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2905 | PSV-2930 Sizing Calulation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2906 | PSV-2931 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2907 | PSV-2932 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672 | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2908 | PSV-2934 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-28 | 2019-05-29
[6 empty] | Issue Actual | 2019-05-28 | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759 | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21 | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2909 | PSV-2936 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-28 | 2019-05-29
[6 empty] | Issue Actual | 2019-05-28 | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759 | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21 | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2910 | PSV-2938 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-28 | 2019-05-29
[6 empty] | Issue Actual | 2019-05-28 | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759 | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21 | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2911 | PSV-2951 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-28 | 2019-05-29
[6 empty] | Issue Actual | 2019-05-28 | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759 | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21 | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2912 | PSV-2956 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2913 | PSV-2958 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2914 | PSV-2959 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2916 | PSV-2962 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-28 | 2019-05-29
[6 empty] | Issue Actual | 2019-05-28 | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759 | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21 | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2917 | PSV-2965 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2918 | PSV-2966 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2919 | PSV-2967 Sizing Calcuation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2921 | PSV-2974 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-28 | 2019-05-29
[6 empty] | Issue Actual | 2019-05-28 | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759 | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21 | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2922 | PSV-2976 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-28 | 2019-05-29
[6 empty] | Issue Actual | 2019-05-28 | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759 | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21 | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2923 | PSV-2981 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2924 | PSV-2985 Sizing Calucation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2925 | PSV-2986 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2927 | PSV-2988 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-28 | 2019-05-29
[6 empty] | Issue Actual | 2019-05-28 | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759 | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21 | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2928 | PSV-2963 Sizing Caluclation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2929 | PSV-2975 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2930 | PSV-2989 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-24 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-3001 | PSV-3001 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
Return Date
Owner Cmmt*
| PE | OL1-2G23-3004 | PSV-3004 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3005 | PSV-3005 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3006 | PSV-3006 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3007 | PSV-3007 & PSV-3008 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3009 | PSV-3009 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-14
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02416
Return Date
Owner Cmmt*
| PE | OL1-2G23-3010 | PSV-3010 & PSV-3012 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3011 | PSV-3011 & PSV-3013 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3014 | PSV-3014 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3015 | PSV-3015 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3016 | PSV-3016 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3017 | PSV-3017 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3018 | PSV-3018 - PSV-3020 - PSV-3022 - PSV-3025 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3019 | PSV-3019 - PSV-3021 - PSV-3023 - PSV-3024 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3026 | PSV-3026 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3027 | PSV-3027 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3028 | PSV-3028 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3029 | PSV-3029 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3031 | PSV-3031 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
Return Date
Owner Cmmt*
| PE | OL1-2G23-3032 | PSV-3032 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3033 | PSV-3033 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3034 | PSV-3034 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3035 | PSV-3035 & PSV-3036 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3037 | PSV-3037 & PSV-3038 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3039 | PSV-3039 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3041 | PSV-3041 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3042 | PSV-3042 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
Return Date
Owner Cmmt*
| PE | OL1-2G23-3046 | PSV-3046 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3049 | PSV-3049 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
Return Date
Owner Cmmt*
| PE | OL1-2G23-3072 | PSV-3072 & PSV-3073 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3074 | PSV-3074 & PSV-3075 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3077 | PSV-3077 & PSV-3078 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3079 | PSV-3079 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-14
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02416
Return Date
Owner Cmmt*
| PE | OL1-2G23-3102 | PSV-3102 & PSV-3103 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
Return Date
Owner Cmmt*
| PE | OL1-2G23-3140 | PSV-3140 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
Return Date
Owner Cmmt*
| PE | OL1-2G23-3150 | PSV-3150 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
Return Date
Owner Cmmt*
| PE | OL1-2G23-3151 | PSV-3151 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
Return Date
Owner Cmmt*
| PE | OL1-2G23-3152 | PSV-3152 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
Return Date
Owner Cmmt*
| PE | OL1-2G23-3162 | PSV-3162 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
Return Date
Owner Cmmt*
| PE | OL1-2G23-3163 | PSV-3163 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
Return Date
Owner Cmmt*
| PE | OL1-2G23-3164 | PSV-3164 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
Return Date
Owner Cmmt*
| PE | OL1-2G23-3165 | PSV-3165 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
Return Date
Owner Cmmt*
| PE | OL1-2G23-3166 | PSV-3166 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
Return Date
Owner Cmmt*
| PE | OL1-2G23-3167 | PSV-3167 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
Return Date
Owner Cmmt*
| PE | OL1-2G23-3168 | PSV-3168 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
Return Date
Owner Cmmt*
| PE | OL1-2G23-3169 | PSV-3169 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
Return Date
Owner Cmmt*
| PE | OL1-2G23-3176 | PSV-3176 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
Return Date
Owner Cmmt*
| PE | OL1-2G23-3643 | PSV-3943 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-08-14
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02416
Return Date
Owner Cmmt*
| PE | OL1-2G23-3943 | PSV-3943 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
Return Date
Owner Cmmt*
| PE | OL1-2G23-3944 | PSV-3944 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
Return Date
Owner Cmmt*
| PE | OL1-2G23-3945 | PSV-3945 & PSV-3946 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
Return Date
Owner Cmmt*
| PE | OL1-2G23-3947 | PSV-3947 & PSV-3948 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
Return Date
Owner Cmmt*
| PE | OL1-2G23-3953 | PSV-3953 & PSV-3970 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
Return Date
Owner Cmmt*
| PE | OL1-2G23-3954 | PSV-3954 PSV-3955 PSV-3956 PSV-3957 PSV-3958 PSV-3959 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
Return Date
Owner Cmmt*
| PE | OL1-2G23-3960 | PSV-3960 & PSV-3961 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
Return Date
Owner Cmmt*
| PE | OL1-2G23-5102 | PSV-5113 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-06 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-06 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01822 | TPSK-LSPA1-T-PE-01822
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5103 | PSV-5120 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-06 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-06 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01822 | TPSK-LSPA1-T-PE-01822
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5104 | PSV-5140 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-07 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-07 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date |  | 2019-07-09
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-5105 | PSV-5143 A-K Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-10 | 2019-06-11 | 2019-06-19 | 2019-06-19
[6 empty] | Issue Actual | 2019-06-10 | 2019-06-11 | 2019-06-19 | 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01851 | TPSK-LSPA1-T-PE-01851 | TPSK-LSPA1-T-PE-01921 | TPSK-LSPA1-T-PE-01921
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5106 | PSV-5150 A-D Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-07 | 2019-06-10 | 2019-06-19 | 2019-06-19
[6 empty] | Issue Actual | 2019-06-07 | 2019-06-10 | 2019-06-19 | 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01921 | TPSK-LSPA1-T-PE-01921
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-5107 | PSV-5153 A-D Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-07 | 2019-06-10 | 2019-06-19 | 2019-06-19
[6 empty] | Issue Actual | 2019-06-07 | 2019-06-10 | 2019-06-19 | 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01921 | TPSK-LSPA1-T-PE-01921
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5201 | PSV-5201 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-07 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-07 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5202 | PSV-5204 A-D Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-19 | 2019-06-19
[6 empty] | Issue Actual | 2019-06-19 | 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01921 | TPSK-LSPA1-T-PE-01921
Return Date
Owner Cmmt*
| PE | OL1-2G23-5203 | PSV-5208 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-07 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-07 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5204 | PSV-5209 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10 | 2019-06-11
[6 empty] | Issue Actual | 2019-06-10 | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01851 | TPSK-LSPA1-T-PE-01851
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-5401 | PSV-5401 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-06 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-06 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01822 | TPSK-LSPA1-T-PE-01822
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5402 | PSV-5404 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-05 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-05 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5501 | PSV-5507 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan |  | 2019-06-11
[6 empty] | Issue Actual |  | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873 | TPSK-LSPA1-T-PE-01873
Return Date
Owner Cmmt*
| PE | OL1-2G23-5502 | PSV-5506 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan |  | 2019-06-11
[6 empty] | Issue Actual |  | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873 | TPSK-LSPA1-T-PE-01873
Return Date
Owner Cmmt*
| PE | OL1-2G23-5503 | PSV-5509 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01912 | TPSK-LSPA1-T-PE-01912
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-5504 | PSV-5510 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10 | 2019-06-11
[6 empty] | Issue Actual | 2019-06-10 | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01851 | TPSK-LSPA1-T-PE-01851
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5506 | PSV-5520 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan |  | 2019-06-11
[6 empty] | Issue Actual |  | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873 | TPSK-LSPA1-T-PE-01873
Return Date
Owner Cmmt*
| PE | OL1-2G23-5507 | PSV-5521 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan |  | 2019-06-11
[6 empty] | Issue Actual |  | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873 | TPSK-LSPA1-T-PE-01873
Return Date
Owner Cmmt*
| PE | OL1-2G23-5508 | PSV-5530 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-12 | 2019-06-14
[6 empty] | Issue Actual | 2019-06-12 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01883 | TPSK-LSPA1-T-PE-01883
Return Date
Owner Cmmt*
| PE | OL1-2G23-5509 | PSV-5531 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01912 | TPSK-LSPA1-T-PE-01912
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-5510 | PSV-5532 A-B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01912 | TPSK-LSPA1-T-PE-01912
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-5901 | PSV-5901 A Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5902 | PSV-5901 B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5903 | PSV-5908 A Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5904 | PSV-5908 B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5905 | PSV-5920 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5906 | PSV-5924 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5907 | PSV-5926 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5908 | PSV-5930 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5909 | PSV-5934 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5910 | PSV-5938 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5911 | PSV-5940 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5912 | PSV-5944 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5913 | PSV-5948 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5914 | PSV-5952 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5915 | PSV-5956 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5916 | PSV-5962 A Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5917 | PSV-5962 B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5918 | PSV-5965 A Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G23-5919 | PSV-5965 B Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-04 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801 | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date |  | 2019-07-02
[6 empty] | Owner Cmmt* |  | R1
| PE | OL2-2G23-2719 | PSV-2747 Sizing Calculation |  | Class 2 | Rev.: Purpose**; IFR A: IFR; IFR A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911 | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11 | 2019-07-11
[6 empty] | Owner Cmmt* | R1 | R1
Category Code: G30 Process Equipment Data Sheets
| PE | OL1-2G30-1000 | PROCESS EQUIPMENT DATA SHEET - 10-D-1000 - LPG FEED DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-25 |  | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00227 | TPSK-LSPA1-T-PE-00227 | TPSK-LSPA1-T-PE-00463 | TPSK-LSPA1-T-PE-00463
[6 empty] | Return Date | 2018-12-05 | 2018-12-05 | 2019-01-16 | 2019-01-16
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-1001 | PROCESS EQUIPMENT DATA SHEET - 10-E-1000 - LPG VAPORIZER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-10-16 |  | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00176 | TPSK-LSPA1-T-PE-00176 | TPSK-LSPA1-T-PE-00451 | TPSK-LSPA1-T-PE-00451
[6 empty] | Return Date | 2018-11-14 | 2018-11-14 | 2019-01-16 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-1003 | PROCESS EQUIPMENT DATA SHEET - 10-E-1001 - LPG STEAM VAPORIZER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-16 | 2018-10-16 |  | 2019-01-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00179 | TPSK-LSPA1-T-PE-00179 | TPSK-LSPA1-T-PE-00712 | TPSK-LSPA1-T-PE-00712
[6 empty] | Return Date | 2019-01-28 | 2019-01-28 | 2019-03-05 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-1005 | PROCESS EQUIPMENT DATA SHEET - 10-E-1005 - LPG FEED HEATER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-10-16 |  | 2019-01-18 | 2019-03-06 | 2019-03-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00176 | TPSK-LSPA1-T-PE-00176 | TPSK-LSPA1-T-PE-00680 | TPSK-LSPA1-T-PE-00680 | TPSK-LSPA1-T-PE-00999 | TPSK-LSPA1-T-PE-00999
[6 empty] | Return Date | 2018-11-14 | 2018-11-14 | 2019-02-21 | 2019-02-21
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-1006 | Process Equipment Datasheet - 10-E-1006 - LPG Feed Steam Heater |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-06 | 2019-03-07 | 2019-04-04 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00998 | TPSK-LSPA1-T-PE-00998 | TPSK-LSPA1-T-PE-01261 | TPSK-LSPA1-T-PE-01261
[6 empty] | Return Date |  |  | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* |  |  | R1 | R1
| PE | OL1-2G30-1015 | PROCESS EQUIPMENT DATA SHEET - 10-E-1015 - LPG SUPERHEATER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-10-16 |  | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00176 | TPSK-LSPA1-T-PE-00176 | TPSK-LSPA1-T-PE-00431 | TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-11-14 | 2018-11-14 | 2019-01-16 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-1020 | PROCESS EQUIPMENT DATA SHEET - 10-E-1020 - LIQUID FEED HEATER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | C | B | C | D | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-22 |  |  | 2018-12-07 | 2019-01-18 | 2019-03-06 | 2019-03-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00431 | TPSK-LSPA1-T-PE-00680 | TPSK-LSPA1-T-PE-00431 | TPSK-LSPA1-T-PE-00680 | TPSK-LSPA1-T-PE-00999 | TPSK-LSPA1-T-PE-00999
[6 empty] | Return Date | 2018-11-30 | 2018-11-30 | 2019-01-16 | 2019-02-21 | 2019-01-16 | 2019-02-21
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R1 | R2 | R1
| PE | OL1-2G30-1051 | PROCESS EQUIPMENT DATA SHEET - 10-E-1050 - C2 FEED SUPERHEATER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-22 |  | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00436 | TPSK-LSPA1-T-PE-00436
[6 empty] | Return Date | 2018-11-30 | 2018-11-30 | 2019-01-16 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-1101 | PROCESS DATA SHEETS YIELDS FOR 36M FURNACE |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-08-15 |  | 2018-08-15
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-22 |  | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00204 | TPSK-LSPA1-T-PE-00204 | TPSK-LSPA1-T-PE-00360 | TPSK-LSPA1-T-PE-00360
[6 empty] | Return Date | 2018-11-30 | 2018-11-30 | 2018-12-27 | 2018-12-27
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-1102 | AOCS PDS (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFI | IFI | IFD | IFD | IFF
[6 empty] | Rev. |  | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2019-01-09 |  |  | 2019-03-06 |  | 2019-09-30
[6 empty] | Revised Plan |  |  | 2018-10-24
[6 empty] | Issue Actual |  |  | 2018-10-24 | 2019-04-02 | 2019-04-03
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00224 | TPSK-LSPA1-T-PE-00224 | TPSK-LSPA1-T-PE-01232 | TPSK-LSPA1-T-PE-01232
Return Date
Owner Cmmt*
| PE | OL1-2G30-1105 | API FIRED HEATER DATA SHEET (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-01-09 |  | 2019-03-06 |  | 2019-09-30
[6 empty] | Revised Plan |  |  |  |  | 2019-09-30
[6 empty] | Issue Actual | 2019-02-06 | 2019-02-06 | 2019-04-11 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00814 | TPSK-LSPA1-T-PE-00814 | TPSK-LSPA1-T-PE-01322 | TPSK-LSPA1-T-PE-01322
[6 empty] | Return Date |  |  | 2019-05-15 | 2019-05-15
[6 empty] | Owner Cmmt* |  |  | R1 | R1
| PE | OL1-2G30-1106 | BURNERS PDS (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-10-30 |  | 2019-01-16 |  | 2019-01-16
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-30 |  | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00241 | TPSK-LSPA1-T-PE-00241 | TPSK-LSPA1-T-PE-00756 | TPSK-LSPA1-T-PE-00756
[6 empty] | Return Date | 2018-11-27 | 2018-11-27 | 2019-02-26 | 2019-02-26
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G30-1107 | STEAM DRUM PDS (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFF
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-10-11 |  | 2018-12-03 |  |  |  | 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2018-10-11 | 2018-10-12 |  | 2018-12-12 | 2019-02-26 | 2019-02-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00159 | TPSK-LSPA1-T-PE-00159 | TPSK-LSPA1-T-PE-00478 | TPSK-LSPA1-T-PE-00478 | TPSK-LSPA1-T-PE-00935 | TPSK-LSPA1-T-PE-00935
[6 empty] | Return Date | 2018-11-05 | 2018-11-05 | 2019-02-11 | 2019-02-11 | 2019-03-15 | 2019-03-15
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-1108 | USX QUENCH EXCHANGERS PDS (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-09-19 |  | 2018-12-10 |  | 2018-12-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-29 |  | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00432 | TPSK-LSPA1-T-PE-00432
[6 empty] | Return Date | 2018-11-30 | 2018-11-30 | 2019-02-11 | 2019-02-11
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-1109 | TLX 1 QUENCH EXCHANGER PDS (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFF
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-09-19 |  | 2018-12-10 |  |  |  | 2018-12-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-29 |  | 2018-12-10 | 2019-03-15 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00459 | TPSK-LSPA1-T-PE-00459 | TPSK-LSPA1-T-PE-01078 | TPSK-LSPA1-T-PE-01078
[6 empty] | Return Date | 2018-11-30 | 2018-11-30 | 2019-02-11 | 2019-02-11 | 2019-04-10 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-1110 | TLX 2 QUENCH EXCHANGER PDS (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFF
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-09-19 |  | 2018-12-10 |  |  |  | 2018-12-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-29 |  | 2018-12-10 | 2019-03-15 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00459 | TPSK-LSPA1-T-PE-00459 | TPSK-LSPA1-T-PE-01078 | TPSK-LSPA1-T-PE-01078
[6 empty] | Return Date | 2018-11-30 | 2018-11-30 | 2019-02-11 | 2019-02-11 | 2019-04-10 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-1111 | ID FAN DATA SHEET (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFD | IFD | IFD | IFD | IFD | IFF
[6 empty] | Rev. |  | B | B | C | C | D | D
[6 empty] | Issue Plan | 2018-09-26 | 2018-11-17 | [5 empty] | 2018-11-17
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-10-24 | 2019-03-15 | 2019-03-18 | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00222 | TPSK-LSPA1-T-PE-00222 | TPSK-LSPA1-T-PE-01079 | TPSK-LSPA1-T-PE-01079 | TPSK-LSPA1-T-PE-01797 | TPSK-LSPA1-T-PE-01797
[6 empty] | Return Date |  | 2018-11-30 | 2018-11-30 | 2019-04-10 | 2019-04-10 |  | 2019-07-03
[6 empty] | Owner Cmmt* |  | R1 | R1 | R1 | R1 |  | R2
| PE | OL1-2G30-1112 | ATTEMPERATOR DATA SHEET (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-11-16 |  | 2019-03-13 |  | 2019-03-13
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-16 |  | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00330 | TPSK-LSPA1-T-PE-00330 | TPSK-LSPA1-T-PE-00752 | TPSK-LSPA1-T-PE-00752
[6 empty] | Return Date | 2018-12-13 | 2018-12-13 | 2019-03-21 | 2019-03-21
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-1151 | USC 36M EFFLUENT MOV - DATA SHEET |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR; B: IFF
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2018-12-20 |  | 2019-03-05
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521 | TPSK-LSPA1-T-PE-00521
[6 empty] | Return Date | 2019-01-28 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-1152 | USC 36M DECOKE MOV - DATA SHEET |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR; B: IFF
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2018-12-20 |  | 2019-03-05
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521 | TPSK-LSPA1-T-PE-00521
[6 empty] | Return Date | 2019-01-28 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-1153 | Process Equipment Datasheet 10-MOV-1102B USC 36M Decoke Effluent Bypass MOV |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan |  | 2018-12-20 | 2019-03-29 | 2019-04-01
[6 empty] | Issue Actual |  | 2018-12-20 | 2019-03-29 | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521 | TPSK-LSPA1-T-PE-00521 | TPSK-LSPA1-T-PE-01195 | TPSK-LSPA1-T-PE-01195
[6 empty] | Return Date | 2019-01-28 | 2019-01-28 | 2019-04-22 | 2019-04-22
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-1201 | PROCESS DATA SHEETS YIELDS FOR 132 U FURNACE |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-08-15 |  | 2018-08-15
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-22 |  | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00204 | TPSK-LSPA1-T-PE-00204 | TPSK-LSPA1-T-PE-00372 | TPSK-LSPA1-T-PE-00372
[6 empty] | Return Date | 2018-11-30 | 2018-11-30 | 2019-01-14 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-1202 | AOCS PDS (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFI | IFI | IFD | IFD | IFF
[6 empty] | Rev. |  | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2019-01-09 |  |  | 2019-03-06 |  | 2019-09-30
[6 empty] | Revised Plan |  |  | 2018-10-24
[6 empty] | Issue Actual |  |  | 2018-10-24 | 2019-04-02 | 2019-04-03
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00224 | TPSK-LSPA1-T-PE-00224 | TPSK-LSPA1-T-PE-01232 | TPSK-LSPA1-T-PE-01232
Return Date
Owner Cmmt*
| PE | OL1-2G30-1205 | Process Equipment Datasheet - 10-H-1200/1600 - API Fired Heater Process Datasheet |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-01-09 |  | 2019-03-06 |  | 2019-09-30
[6 empty] | Revised Plan |  |  |  |  | 2019-09-30
[6 empty] | Issue Actual | 2019-02-06 | 2019-02-06 | 2019-04-11 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00814 | TPSK-LSPA1-T-PE-00814 | TPSK-LSPA1-T-PE-01322 | TPSK-LSPA1-T-PE-01322
[6 empty] | Return Date |  |  | 2019-05-15 | 2019-05-15
[6 empty] | Owner Cmmt* |  |  | R1 | R1
| PE | OL1-2G30-1206 | BURNERS PDS (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-10-30 |  | 2019-01-16 |  | 2019-01-16
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-30 |  | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00241 | TPSK-LSPA1-T-PE-00241 | TPSK-LSPA1-T-PE-00756 | TPSK-LSPA1-T-PE-00756
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-02-26 | 2019-02-26
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G30-1207 | STEAM DRUM PDS (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFF
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-10-11 |  | 2018-12-03 |  |  |  | 2018-12-03
Revised Plan
[6 empty] | Issue Actual | 2018-10-11 | 2018-10-12 |  | 2018-12-12 | 2019-02-26 | 2019-02-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00159 | TPSK-LSPA1-T-PE-00159 | TPSK-LSPA1-T-PE-00478 | TPSK-LSPA1-T-PE-00478 | TPSK-LSPA1-T-PE-00935 | TPSK-LSPA1-T-PE-00935
[6 empty] | Return Date | 2018-11-05 | 2018-11-05 | 2019-02-11 | 2019-02-11 | 2019-03-15 | 2019-03-15
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-1208 | SLE QUENCH EXCHANGERS PDS (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-09-19 |  | 2018-12-10 |  | 2018-12-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-29 |  | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00433 | TPSK-LSPA1-T-PE-00433
[6 empty] | Return Date | 2018-11-30 | 2018-11-30 | 2019-02-11 | 2019-02-11
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-1209 | TLX QUENCH EXCHANGER PDS (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFF
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-09-19 |  | 2018-12-10 |  |  |  | 2018-12-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-29 |  | 2018-12-10 | 2019-03-15 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00449 | TPSK-LSPA1-T-PE-00449 | TPSK-LSPA1-T-PE-01078 | TPSK-LSPA1-T-PE-01078
[6 empty] | Return Date | 2018-11-30 | 2018-11-30 | 2019-02-11 | 2019-02-11 | 2019-04-10 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-1211 | ID FAN DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IFD | IFD | IFD | IFD | IFD | IFF
[6 empty] | Rev. |  | B | B | C | C | D | D
[6 empty] | Issue Plan | 2018-09-26 | 2018-11-17 | [5 empty] | 2018-11-17
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-10-24 | 2019-03-15 | 2019-03-18 | 2019-06-04 | 2019-06-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00222 | TPSK-LSPA1-T-PE-00222 | TPSK-LSPA1-T-PE-01079 | TPSK-LSPA1-T-PE-01079 | TPSK-LSPA1-T-PE-01797 | TPSK-LSPA1-T-PE-01797
[6 empty] | Return Date |  | 2018-11-30 | 2018-11-30 | 2019-04-10 | 2019-04-10 |  | 2019-07-03
[6 empty] | Owner Cmmt* |  | R1 | R1 | R1 | R1 |  | R2
| PE | OL1-2G30-1212 | ATTEMPERATOR DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFF
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-11-16 |  | 2019-03-13 |  |  |  | 2019-03-13
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-16 |  | 2019-01-29 | 2019-04-01 | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00330 | TPSK-LSPA1-T-PE-00330 | TPSK-LSPA1-T-PE-00752 | TPSK-LSPA1-T-PE-00752 | TPSK-LSPA1-T-PE-01220 | TPSK-LSPA1-T-PE-01220
[6 empty] | Return Date | 2018-12-13 | 2018-12-13 | 2019-03-21 | 2019-03-21
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R2
| PE | OL1-2G30-1213 | MIXING TEE PDS (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-09 |  | 2019-01-09
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-07 | 2019-02-26 | 2019-02-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00434 | TPSK-LSPA1-T-PE-00434 | TPSK-LSPA1-T-PE-00936 | TPSK-LSPA1-T-PE-00936
[6 empty] | Return Date |  |  | 2019-03-15 | 2019-03-15
[6 empty] | Owner Cmmt* |  |  | R1 | R1
| PE | OL1-2G30-1251 | USC 132SU EFFLUENT MOV - DATA SHEET |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR; B: IFF
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2018-12-20 |  | 2019-03-05
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521 | TPSK-LSPA1-T-PE-00521
[6 empty] | Return Date | 2019-01-28 | 2019-01-28
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-1252 | USC 132SU DECOKE MOV - DATA SHEET |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR; B: IFF
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2018-12-20 |  | 2019-03-05
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521 | TPSK-LSPA1-T-PE-00521
[6 empty] | Return Date | 2019-01-28 | 2019-01-28
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-1253 | Process Equipment Datasheet 10-MOV-1202B USC 132U Decoke Effluent Bypass MOV |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
Issue Plan
[6 empty] | Revised Plan |  | 2018-12-20 | 2019-03-29 | 2019-04-01
[6 empty] | Issue Actual |  | 2018-12-20 | 2019-03-29 | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521 | TPSK-LSPA1-T-PE-00521 | TPSK-LSPA1-T-PE-01195 | TPSK-LSPA1-T-PE-01195
[6 empty] | Return Date | 2019-01-28 | 2019-01-28 | 2019-04-22 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-1911 | Process Equipment Datasheet - 10-D-1910 - DMDS Bulk Storage Drum |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-22 | 2019-03-19 | 2019-03-20 | 2019-04-08 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00686 | TPSK-LSPA1-T-PE-00686 | TPSK-LSPA1-T-PE-01096 | TPSK-LSPA1-T-PE-01096 | TPSK-LSPA1-T-PE--01280 | TPSK-LSPA1-T-PE--01280
[6 empty] | Return Date | 2019-02-21 | 2019-02-21 | 2019-04-10 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-1912 | Process Equipment Datasheet - 10-D-1912 - DMDS Injection Drum |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-22 | 2019-03-19 | 2019-03-20 | 2019-04-08 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00686 | TPSK-LSPA1-T-PE-00686 | TPSK-LSPA1-T-PE-01096 | TPSK-LSPA1-T-PE-01096 | TPSK-LSPA1-T-PE-01280 | TPSK-LSPA1-T-PE-01280
[6 empty] | Return Date | 2019-02-21 | 2019-02-21 | 2019-04-10 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-1913 | Process Equipment Datasheet - 10-P-1910 A-B - DMDS Feed Injection Pump |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-22 | 2019-03-01 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE--00687 | TPSK-LSPA1-T-PE--00687 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-00963
[6 empty] | Return Date | 2019-02-21 | 2019-02-21 | 2019-03-21 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-1914 | Process Equipment Datasheet - 10-P-1912 - DMDS Presulfiding Injection Pump |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-22 | 2019-03-01 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE--00687 | TPSK-LSPA1-T-PE--00687 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-00963
[6 empty] | Return Date | 2019-02-21 | 2019-02-21 | 2019-03-21 | 2019-03-21
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-1950 | PROCESS EQUIPMENT DATA SHEET - 10-PK-1950 - DECOKE AIR COMPRESSOR PACKAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | C | B | B | C
[6 empty] | Issue Plan | 2018-12-07 |  |  | 2019-01-02
[6 empty] | Revised Plan |  | 2018-08-29 | 2018-09-03
[6 empty] | Issue Actual |  | 2018-08-29 | 2018-09-03 |  | 2018-09-28 | 2018-10-01 | 2018-10-30
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00031 | TPSK-LSPA1-T-PE-00031 | TPSK-LSPA1-T-PE-00242 | TPSK-LSPA1-T-PE-00114 | TPSK-LSPA1-T-PE-00114 | TPSK-LSPA1-T-PE-00242
[6 empty] | Return Date |  | 2018-09-28 | 2018-09-28 | 2018-11-30 | 2018-10-24 | 2018-10-24 | 2018-11-30
[6 empty] | Owner Cmmt* |  | A3 | A3 | A1 | R2 | R2 | A1
| PE | OL1-2G30-2000 | PROCESS EQUIPMENT DATA SHEET - 10-T-2000 - QUENCH OIL TOWER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-12 | 2018-10-15 |  | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00162 | TPSK-LSPA1-T-PE-00162 | TPSK-LSPA1-T-PE-00402 | TPSK-LSPA1-T-PE-00402
[6 empty] | Return Date | 2018-11-05 | 2018-11-05 | 2019-01-14 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2006 | PROCESS EQUIPMENT DATA SHEET - 10-P-2006 - QUENCH OIL PUMP |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-11 |  |  | 2019-04-01
[6 empty] | Revised Plan |  | 2018-09-20 | 2018-09-24
[6 empty] | Issue Actual |  | 2018-09-20 | 2018-09-24 |  | 2018-10-22 | 2019-03-26 | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00071 | TPSK-LSPA1-T-PE-00071 | TPSK-LSPA1-T-PE-00202 | TPSK-LSPA1-T-PE-00202 | TPSK-LSPA1-T-PE-01159 | TPSK-LSPA1-T-PE-01159
[6 empty] | Return Date |  | 2018-10-09 | 2018-10-09 | 2018-11-30 | 2018-11-30 | 2019-04-12 | 2019-04-12
[6 empty] | Owner Cmmt* |  | A3 | A3 | A1 | A1 | R1 | R1
| PE | OL1-2G30-2010 | PROCESS EQUIPMENT DATA SHEET - 10-F-2008 - QUENCH OIL FILTER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-21 |  | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00606 | TPSK-LSPA1-T-PE-00606
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-02-04 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2014 | PROCESS EQUIPMENT DATA SHEET - 10-F-2009 - QO PUMP PURGE OIL FILTER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-21 |  | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00606 | TPSK-LSPA1-T-PE-00606
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-02-04 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2015 | PROCESS EQUIPMENT DATA SHEET - 10-E-2008 - VLP STEAM GENERATORS |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-09 |  | 2019-01-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00305 | TPSK-LSPA1-T-PE-00305 | TPSK-LSPA1-T-PE-00632 | TPSK-LSPA1-T-PE-00632
[6 empty] | Return Date | 2018-12-13 | 2018-12-13 | 2019-02-11 | 2019-02-11
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2020 | PROCESS EQUIPMENT DATA SHEET - 10-T-2020 - LIGHT FUEL OIL STRIPPER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-29 |  | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00238 | TPSK-LSPA1-T-PE-00238 | TPSK-LSPA1-T-PE-00437 | TPSK-LSPA1-T-PE-00437
[6 empty] | Return Date | 2018-12-04 | 2018-12-04 | 2019-01-16 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2024 | PROCESS EQUIPMENT DATA SHEET - 10-P-2026 - LIGHT FUEL OIL PUMP |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-07 |  | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00648 | TPSK-LSPA1-T-PE-00648
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-01-28 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2025 | PROCESS EQUIPMENT DATA SHEET - 10-F-2026 - CRACKER BOTTOMS PRODUCT FILTER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-21 |  | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00676 | TPSK-LSPA1-T-PE-00676
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-02-11 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2026 | PROCESS EQUIPMENT DATA SHEET - 10-E-2026 - FUEL OIL PRODUCT COOLER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-09 |  | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00298 | TPSK-LSPA1-T-PE-00298 | TPSK-LSPA1-T-PE-00680 | TPSK-LSPA1-T-PE-00680
[6 empty] | Return Date | 2018-12-17 | 2018-12-17 | 2019-02-21 | 2019-02-21
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2028 | PROCESS EQUIPMENT DATA SHEET - 10-F-2028 - FO PUMP PURGE OIL FILTER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-21 |  | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00676 | TPSK-LSPA1-T-PE-00676
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-02-11 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2036 | PROCESS EQUIPMENT DATA SHEET - 10-X-2036 - QUENCH FITTING |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-11
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-20 |  | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00338 | TPSK-LSPA1-T-PE-00338 | TPSK-LSPA1-T-PE-00604 | TPSK-LSPA1-T-PE-00604
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-02-04 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2040 | PROCESS EQUIPMENT DATA SHEET - 10-T-2040 - HEAVY FUEL OIL STRIPPER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-12 | 2018-10-15 |  | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00162 | TPSK-LSPA1-T-PE-00162 | TPSK-LSPA1-T-PE-00347 | TPSK-LSPA1-T-PE-00347
[6 empty] | Return Date | 2018-11-05 | 2018-11-05 | 2019-01-14 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2046 | PROCESS EQUIPMENT DATA SHEET - 10-P-2046 - HEAVY FUEL OIL PUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-07 |  | 2019-01-14 | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00648 | TPSK-LSPA1-T-PE-00648 | TPSK-LPSA1-T-PE-01402 | TPSK-LPSA1-T-PE-01402
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-01-28 | 2019-01-28 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2048 | PROCESS EQUIPMENT DATA SHEET - 10-E-2048 - HEAVY FUEL OIL PRODUCT COOLER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-09 |  | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00298 | TPSK-LSPA1-T-PE-00298 | TPSK-LSPA1-T-PE-00680 | TPSK-LSPA1-T-PE-00680
[6 empty] | Return Date | 2018-12-17 | 2018-12-17 | 2019-02-21 | 2019-02-21
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2049 | PROCESS EQUIPMENT DATA SHEET - 10-F-2048 - HEAVY FUEL OIL FILTERS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-21 |  | 2019-01-18 | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00676 | TPSK-LSPA1-T-PE-00676 | TPSK-LSPA1-T-PE-01401 | TPSK-LSPA1-T-PE-01401
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-02-11 | 2019-02-11 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2070 | Process Data Sheet For General Purpose Steam Turbines - API 611-4TH - PT-2006 A Quench Oil Pump Turbine |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-12 | 2019-06-14
[6 empty] | Issue Actual | 2019-06-12 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01875 | TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date |  | 2019-07-09
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-2090 | PROCESS EQUIPMENT DATA SHEET - 10-D-2090 - QUENCH OIL DRAIN DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; C: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-27 | 2019-03-01 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00368 | TPSK-LSPA1-T-PE-00368 | TPSK-LSPA1-T-PE-00964 | TPSK-LSPA1-T-PE-00964
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-03-21 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2091 | PROCESS EQUIPMENT DATA SHEET - 10-P-2090 - QUENCH OIL DRAIN DRUM PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-27 | 2019-03-01 | 2019-03-04 | 2019-03-26 | 2019-03-27 | 2019-04-04 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00371 | TPSK-LSPA1-T-PE-00371 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-01159 | TPSK-LSPA1-T-PE-01159 | TPSK-LSPA1-T-PE-01255 | TPSK-LSPA1-T-PE-01255
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-03-21 | 2019-03-21 | 2019-04-12 | 2019-04-12
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2092 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2090 - QUENCH OIL DRAIN SUMP EDUCTOR |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFD; B: IFD
[6 empty] | Rev. |  | A | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual |  |  | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00595 | TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date |  | 2019-01-28 | 2019-01-28
[6 empty] | Owner Cmmt* |  | R1 | R1
| PE | OL1-2G30-2100 | PROCESS EQUIPMENT DATA SHEET - 10-T-2100 - QUENCH WATER TOWER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-29 |  | 2018-12-07 | 2019-03-28 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00238 | TPSK-LSPA1-T-PE-00238 | TPSK-LSPA1-T-PE-00437 | TPSK-LSPA1-T-PE-00437 | TPSK-LSPA1-T-PE-01184 | TPSK-LSPA1-T-PE-01184
[6 empty] | Return Date | 2018-12-04 | 2018-12-04 | 2019-01-16 | 2019-01-16 | 2019-04-22 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2101 | PROCESS EQUIPMENT DATA SHEET - 10-E-2100 - QUENCH WATER COOLER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-10 | 2018-09-11
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-09-11 | 2018-10-07 | 2018-10-08 | 2019-04-04 | 2019-04-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00143 | TPSK-LSPA1-T-PE-00143 | TPSK-LSPA1-T-PE-01261 | TPSK-LSPA1-T-PE-01261
[6 empty] | Return Date |  | 2018-10-02 | 2018-10-02
[6 empty] | Owner Cmmt* |  | A1 | A1
| PE | OL1-2G30-2104 | PROCESS EQUIPMENT DATA SHEET - 10-F-2105 - QUENCH OIL REFLUX FILTER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-21 |  | 2019-01-07 | 2019-03-15 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00606 | TPSK-LSPA1-T-PE-00606 | TPSK-LSPA1-T-PE-01072 | TPSK-LSPA1-T-PE-01072
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-02-04 | 2019-02-04 | 2019-04-10 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2105 | PROCESS EQUIPMENT DATA SHEET - 10-P-2105 - QUENCH OIL REFLUX PUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-07 |  | 2019-01-07 | 2019-03-26 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00603 | TPSK-LSPA1-T-PE-00603 | TPSK-LSPA1-T-PE-01159 | TPSK-LSPA1-T-PE-01159
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-02-04 | 2019-02-04 | 2019-04-12 | 2019-04-12
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2106 | PROCESS EQUIPMENT DATA SHEET - 10-P-2106 - QUENCH WATER PUMP |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-11 |  |  | 2019-04-01
[6 empty] | Revised Plan |  | 2018-09-20 | 2018-09-24
[6 empty] | Issue Actual |  | 2018-09-20 | 2018-09-24 |  | 2018-10-22 | 2019-03-26 | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00070 | TPSK-LSPA1-T-PE-00070 | TPSK-LSPA1-T-PE-00202 | TPSK-LSPA1-T-PE-00202 | TPSK-LSPA1-T-PE-01159 | TPSK-LSPA1-T-PE-01159
[6 empty] | Return Date |  | 2018-10-09 | 2018-10-09 | 2018-11-30 | 2018-11-30 | 2019-04-12 | 2019-04-12
[6 empty] | Owner Cmmt* |  | A1 | A1 | A1 | A1 | R1 | R1
| PE | OL1-2G30-2110 | PROCESS EQUIPMENT DATA SHEET - 10-D-2110 - INTERCEPTION DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-10 |  | 2019-01-18 | 2019-03-01 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00453 | TPSK-LSPA1-T-PE-00453 | TPSK-LSPA1-T-PE-00678 | TPSK-LSPA1-T-PE-00678 | TPSK-LSPA1-T-PE-00964 | TPSK-LSPA1-T-PE-00964
[6 empty] | Return Date | 2019-01-16 | 2019-01-16 | 2019-02-21 | 2019-02-21 | 2019-03-21 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R1 | R1
| PE | OL1-2G30-2120 | PROCESS EQUIPMENT DATA SHEET - 10-T-2120 - DISTILLTATE STRIPPER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | C | B | C
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-31 |  |  | 2018-11-29 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00253 | TPSK-LSPA1-T-PE-00253 | TPSK-LSPA1-T-PE-00401 | TPSK-LSPA1-T-PE-00437 | TPSK-LSPA1-T-PE-00401 | TPSK-LSPA1-T-PE-00437
[6 empty] | Return Date | 2018-12-04 | 2018-12-04 | 2019-01-14 | 2019-01-16 | 2019-01-14 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2125 | PROCESS EQUIPMENT DATA SHEET - 10-E-2125 - DISTILLATE STRIPPER REBOILER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-01 |  | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00265 | TPSK-LSPA1-T-PE-00265 | TPSK-LSPA1-T-PE-00492 | TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-12-10 | 2018-12-10 | 2019-01-22 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2126 | PROCESS EQUIPMENT DATA SHEET - 10-P-2126 - DISTILLATE STRIPPER BOTTOMS PUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-27 | 2019-03-01 | 2019-03-04 | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00371 | TPSK-LSPA1-T-PE-00371 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-01383 | TPSK-LSPA1-T-PE-01383
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-03-21 | 2019-03-21 | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2136 | PROCESS EQUIPMENT DATA SHEET - 10-D-2136 - PROCESS WATER FEED COALESCER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-10 |  | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00453 | TPSK-LSPA1-T-PE-00453 | TPSK-LSPA1-T-PE-00678 | TPSK-LSPA1-T-PE-00678
[6 empty] | Return Date | 2019-01-16 | 2019-01-16 | 2019-02-21 | 2019-02-21
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2137 | PROCESS EQUIPMENT DATA SHEET - 10-E-2136 - PROCESS WATER STRIPPER FEED HEATER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-18 | 2018-10-18 |  | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194 | TPSK-LSPA1-T-PE-00194 | TPSK-LSPA1-T-PE-00467 | TPSK-LSPA1-T-PE-00467
[6 empty] | Return Date | 2018-11-26 | 2018-11-26 | 2019-01-22 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2138 | PROCESS EQUIPMENT DATA SHEET - 10-F-2136 - PROCESS WATER FEED FILTER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-21 |  | 2019-01-07 | 2019-03-15 | 2019-03-18 | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00606 | TPSK-LSPA1-T-PE-00606 | TPSK-LSPA1-T-PE-01072 | TPSK-LSPA1-T-PE-01072 | TPSK-LSPA1-T-PE-01401 | TPSK-LSPA1-T-PE-01401
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-02-04 | 2019-02-04 | 2019-04-10 | 2019-04-10 | 2019-06-04 | 2019-06-04
Owner Cmmt* | bar: 2018-12-27 to 2019-06-04
| PE | OL1-2G30-2139 | Process Equipment Datasheet - 10-F-2137 A-B - Process Water Coalescer Prefilters |  | Class 2 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2018-12-07; 2019-02-04: 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-04-17; 2018-12-27: 2019-04-18; 2019-02-04: 2019-06-04; 2019-02-04: 2019-06-10
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-01401; 2018-12-27: TPSK-LSPA1-T-PE-01401; 2019-02-04: TPSK-LSPA1-T-PE-01804; 2019-02-04: TPSK-LSPA1-T-PE-01804
[6 empty] | Return Date | 2018-12-27: 2019-06-04; 2018-12-27: 2019-06-04; 2019-02-04: 2019-07-08
Owner Cmmt* | bar: 2018-12-27 to 2018-12-27; 2019-02-04
| PE | OL1-2G30-2140 | PROCESS EQUIPMENT DATA SHEET - 10-T-2140 - PROCESS WATER STRIPPER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-01-21; 2019-02-04: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-17; 2018-12-27: 2018-10-18; 2019-02-04: 2018-11-29
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00189; 2018-12-27: TPSK-LSPA1-T-PE-00189; 2019-02-04: TPSK-LSPA1-T-PE-00401; 2019-02-04: TPSK-LSPA1-T-PE-00401
[6 empty] | Return Date | 2018-12-27: 2018-11-26; 2018-12-27: 2018-11-26; 2019-02-04: 2019-01-14; 2019-02-04: 2019-01-14
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2145 | PROCESS EQUIPMENT DATA SHEET - 10-E-2145 - PROCESS WATER STRIPPER REBOILER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-18; 2018-12-27: 2018-10-18; 2019-02-04: 2019-01-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00194; 2018-12-27: TPSK-LSPA1-T-PE-00194; 2019-02-04: TPSK-LSPA1-T-PE-00605; 2019-02-04: TPSK-LSPA1-T-PE-00605
[6 empty] | Return Date | 2018-12-27: 2018-12-27; 2018-12-27: 2018-12-27; 2019-02-04: 2019-02-04; 2019-02-04: 2019-02-04
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2146 | PROCESS EQUIPMENT DATA SHEET - 10-P-2146 - DSG FEED PUMP |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-04-10
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-02-04: 2019-04-01
[6 empty] | Revised Plan | 2018-12-27: 2018-09-20; 2019-02-04: 2018-09-24
[6 empty] | Issue Actual | 2018-12-27: 2018-09-20; 2019-02-04: 2018-09-24; 2019-04-10: 2018-10-22
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00069; 2019-02-04: TPSK-LSPA1-T-PE-00069; 2019-02-04: TPSK-LSPA1-T-PE-00202; 2019-04-10: TPSK-LSPA1-T-PE-00202
[6 empty] | Return Date | 2018-12-27: 2018-10-09; 2019-02-04: 2018-10-09; 2019-02-04: 2018-11-30; 2019-04-10: 2018-11-30
Owner Cmmt* | bar: 2018-12-27 to 2019-04-10
| PE | OL1-2G30-2147 | PROCESS EQUIPMENT DATA SHEET - 10-E-2146 - DSG FEED HEATER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-18; 2018-12-27: 2018-10-18; 2019-02-04: 2019-01-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00194; 2018-12-27: TPSK-LSPA1-T-PE-00194; 2019-02-04: TPSK-LSPA1-T-PE-00605; 2019-02-04: TPSK-LSPA1-T-PE-00605
[6 empty] | Return Date | 2018-12-27: 2018-12-27; 2018-12-27: 2018-12-27; 2019-02-04: 2019-02-04; 2019-02-04: 2019-02-04
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2160 | PROCESS EQUIPMENT DATA SHEET - 10-D-2160 - DILUTION STEAM GENERATOR |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-04-10
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-25
[6 empty] | Revised Plan | 2018-12-27: 2018-09-28; 2019-02-04: 2018-10-01
[6 empty] | Issue Actual | 2018-12-27: 2018-09-28; 2019-02-04: 2018-10-01; 2019-04-10: 2019-01-10
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00115; 2019-02-04: TPSK-LSPA1-T-PE-00115; 2019-02-04: TPSK-LSPA1-T-PE-00620; 2019-04-10: TPSK-LSPA1-T-PE-00620
[6 empty] | Return Date | 2018-12-27: 2018-11-05; 2019-02-04: 2018-11-05; 2019-02-04: 2019-02-11; 2019-04-10: 2019-02-11
[6 empty] | Owner Cmmt* | 2018-12-27: A3; 2019-02-04: A3; 2019-02-04: 03; 2019-04-10: R2
| PE | OL1-2G30-2161 | PROCESS EQUIPMENT DATA SHEET - 10-E-2160 - DILUTION STEAM SUPERHEATER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-18; 2019-02-04: 2018-12-10
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00194; 2018-12-27: TPSK-LSPA1-T-PE-00194; 2019-02-04: TPSK-LSPA1-T-PE-00467; 2019-02-04: TPSK-LSPA1-T-PE-00467
[6 empty] | Return Date | 2018-12-27: 2018-11-26; 2018-12-27: 2018-11-26; 2019-02-04: 2019-01-22; 2019-02-04: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2165 | PROCESS EQUIPMENT DATA SHEET - 10-E-2165 - DSG REBOILER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-18; 2018-12-27: 2018-10-18; 2019-02-04: 2018-12-10
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00194; 2018-12-27: TPSK-LSPA1-T-PE-00194; 2019-02-04: TPSK-LSPA1-T-PE-00467; 2019-02-04: TPSK-LSPA1-T-PE-00467
[6 empty] | Return Date | 2018-12-27: 2018-11-26; 2018-12-27: 2018-11-26; 2019-02-04: 2019-01-22; 2019-02-04: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2166 | PROCESS EQUIPMENT DATA SHEET - 10-E-2166 - DSG BLOWDOWN COOLER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-23; 2019-02-04: 2018-12-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00209; 2018-12-27: TPSK-LSPA1-T-PE-00209; 2019-02-04: TPSK-LSPA1-T-PE-00431; 2019-02-04: TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-12-27: 2018-11-30; 2018-12-27: 2018-11-30; 2019-02-04: 2019-01-16; 2019-02-04: 2019-01-16
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2170 | Process Data Sheet For General Purpose Steam Turbines - API 611-4TH - PT-2106 A Quench Water Pump Turbine |  | Class 2 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR
Rev. | bar: 2018-12-27 to 2018-12-27
Issue Plan
[6 empty] | Revised Plan | 2018-12-27: 2019-06-12; 2018-12-27: 2019-06-14
[6 empty] | Issue Actual | 2018-12-27: 2019-06-12; 2018-12-27: 2019-06-14
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-01875; 2018-12-27: TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date | 2018-12-27: 2019-07-09
Owner Cmmt* | bar: 2018-12-27
| PE | OL1-2G30-2171 | Process Data Sheet For General Purpose Steam Turbines - API 611-4TH - PT-2146 A DSG Feed Pump Turbine |  | Class 2 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR
Rev. | bar: 2018-12-27 to 2018-12-27
Issue Plan
[6 empty] | Revised Plan | 2018-12-27: 2019-06-12; 2018-12-27: 2019-06-14
[6 empty] | Issue Actual | 2018-12-27: 2019-06-12; 2018-12-27: 2019-06-14
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-01875; 2018-12-27: TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date | 2018-12-27: 2019-07-09
Owner Cmmt* | bar: 2018-12-27
| PE | OL1-2G30-2190 | PROCESS EQUIPMENT DATA SHEET - 10-D-2190 - QUENCH WATER DRAIN DRUM |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-27; 2019-02-04: 2019-03-01; 2019-02-04: 2019-03-04
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00368; 2018-12-27: TPSK-LSPA1-T-PE-00368; 2019-02-04: TPSK-LSPA1-T-PE-00964; 2019-02-04: TPSK-LSPA1-T-PE-00964
[6 empty] | Return Date | 2018-12-27: 2019-02-25; 2018-12-27: 2019-02-25; 2019-02-04: 2019-03-21; 2019-02-04: 2019-03-21
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2191 | PROCESS EQUIPMENT DATA SHEET - 10-P-2190 - QUENCH WATER DRAIN DRUM PUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-02-04: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-21; 2019-02-04: 2019-01-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00346; 2018-12-27: TPSK-LSPA1-T-PE-00346; 2019-02-04: TPSK-LSPA1-T-PE-00603; 2019-02-04: TPSK-LSPA1-T-PE-00603
[6 empty] | Return Date | 2018-12-27: 2018-12-27; 2018-12-27: 2018-12-27; 2019-02-04: 2019-02-04; 2019-02-04: 2019-02-04
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2192 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2190 - QUENCH WATER DRAING SUMP EDUCTOR |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2018-12-27: 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2019-02-04: 2019-01-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00595; 2019-02-04: TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date | 2018-12-27: 2019-01-28; 2019-02-04: 2019-01-28
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2200 | PROCESS EQUIPMENT DATA SHEET - 10-C-2200 - CRACKED GAS COMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-04-10
[6 empty] | Issue Plan | 2018-12-27: 2018-12-07; 2019-02-04: 2019-01-02
[6 empty] | Revised Plan | 2018-12-27: 2018-08-22; 2019-02-04: 2018-08-23
[6 empty] | Issue Actual | 2018-12-27: 2018-08-22; 2019-02-04: 2018-08-23; 2019-02-04: 2018-09-17; 2019-04-10: 2018-09-18
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00025; 2019-02-04: TPSK-LSPA1-T-PE-00025; 2019-02-04: TPSK-LSPA1-T-PE-00055; 2019-04-10: TPSK-LSPA1-T-PE-00055
[6 empty] | Return Date | 2018-12-27: 2018-09-11; 2019-02-04: 2018-09-11
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2206 | PROCESS EQUIPMENT DATA SHEET - 10-E-2206 - WASH WATER COOLER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-28; 2019-02-04: 2019-01-16
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00381; 2018-12-27: TPSK-LSPA1-T-PE-00381; 2019-02-04: TPSK-LSPA1-T-PE-00655; 2019-02-04: TPSK-LSPA1-T-PE-00655
[6 empty] | Return Date | 2018-12-27: 2019-01-14; 2018-12-27: 2019-01-14; 2019-02-04: 2019-02-11; 2019-02-04: 2019-02-11
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2210 | PROCESS EQUIPMENT DATA SHEET - 10-D-2210 - CG 1ST STAGE SUCTION DRUM |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-08; 2018-12-27: 2018-10-09; 2019-02-04: 2018-12-10
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00144; 2018-12-27: TPSK-LSPA1-T-PE-00144; 2019-02-04: TPSK-LSPA1-T-PE-00448; 2019-02-04: TPSK-LSPA1-T-PE-00448
[6 empty] | Return Date | 2018-12-27: 2018-11-05; 2018-12-27: 2018-11-05; 2019-02-04: 2019-01-16; 2019-02-04: 2019-01-16
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2211 | PROCESS EQUIPMENT DATA SHEET - 10-E-2210 - CG 1ST STAGE AFTERCOOLER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-01; 2019-02-04: 2018-12-13
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00266; 2018-12-27: TPSK-LSPA1-T-PE-00266; 2019-02-04: TPSK-LSPA1-T-PE-00479; 2019-02-04: TPSK-LSPA1-T-PE-00479
[6 empty] | Return Date | 2018-12-27: 2018-12-10; 2018-12-27: 2018-12-10; 2019-02-04: 2019-01-22; 2019-02-04: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2212 | PROCESS EQUIPMENT DATA SHEET - 10-P-2210 - CG 1ST STAGE CONDENSATE PUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-02-04: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-07; 2019-02-04: 2019-01-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00285; 2018-12-27: TPSK-LSPA1-T-PE-00285; 2019-02-04: TPSK-LSPA1-T-PE-00593; 2019-02-04: TPSK-LSPA1-T-PE-00593
[6 empty] | Return Date | 2018-12-27: 2018-12-27; 2018-12-27: 2018-12-27; 2019-02-04: 2019-01-28; 2019-02-04: 2019-01-28
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2220 | PROCESS EQUIPMENT DATA SHEET - 10-D-2220 - CG 2ND STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | C | B | B | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-08; 2018-12-27: 2018-10-09; 2019-04-10: 2018-12-10; 2019-04-10: 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00678 | TPSK-LSPA1-T-PE-00448 | TPSK-LSPA1-T-PE-00448 | TPSK-LSPA1-T-PE-00678
[6 empty] | Return Date | 2018-11-05 | 2018-11-05 | 2019-02-21 | 2019-01-16 | 2019-01-16 | 2019-02-21
Owner Cmmt* | bar: 2018-12-27 to 2019-04-10
| PE | OL1-2G30-2221 | PROCESS EQUIPMENT DATA SHEET - 10-E-2220 - CG 2ND STAGE AFTERCOOLER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-22; 2019-02-04: 2018-12-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00206; 2018-12-27: TPSK-LSPA1-T-PE-00206; 2019-02-04: TPSK-LSPA1-T-PE-00431; 2019-02-04: TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-12-27: 2018-11-30; 2018-12-27: 2018-11-30; 2019-02-04: 2019-01-16; 2019-02-04: 2019-01-16
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2222 | PROCESS EQUIPMENT DATA SHEET - 10-P-2220 - CG 2ND STAGE CONDENSED HC PUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-02-04: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-07; 2019-02-04: 2019-01-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00285; 2018-12-27: TPSK-LSPA1-T-PE-00285; 2019-02-04: TPSK-LSPA1-T-PE-00593; 2019-02-04: TPSK-LSPA1-T-PE-00593
[6 empty] | Return Date | 2018-12-27: 2018-12-27; 2018-12-27: 2018-12-27; 2019-02-04: 2019-01-28; 2019-02-04: 2019-01-28
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2230 | PROCESS EQUIPMENT DATA SHEET - 10-D-2230 - CG 3RD STAGE SUCTION DRUM |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-08; 2018-12-27: 2018-10-09; 2019-02-04: 2018-12-10
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00144; 2018-12-27: TPSK-LSPA1-T-PE-00144; 2019-02-04: TPSK-LSPA1-T-PE-00448; 2019-02-04: TPSK-LSPA1-T-PE-00448
[6 empty] | Return Date | 2018-12-27: 2018-11-05; 2018-12-27: 2018-11-05; 2019-02-04: 2019-01-16; 2019-02-04: 2019-01-16
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2231 | PROCESS EQUIPMENT DATA SHEET - 10-E-2230 - CG 3RD STAGE AFTERCOOLER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-22; 2019-02-04: 2018-12-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00206; 2018-12-27: TPSK-LSPA1-T-PE-00206; 2019-02-04: TPSK-LSPA1-T-PE-00431; 2019-02-04: TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-12-27: 2018-11-30; 2018-12-27: 2018-11-30; 2019-02-04: 2019-01-16; 2019-02-04: 2019-01-16
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2240 | PROCESS EQUIPMENT DATA SHEET - 10-D-2240 - CG 4TH STAGE SUCTION DRUM |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-15; 2018-12-27: 2018-10-16; 2019-02-04: 2018-12-10
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00175; 2018-12-27: TPSK-LSPA1-T-PE-00175; 2019-02-04: TPSK-LSPA1-T-PE-00448; 2019-02-04: TPSK-LSPA1-T-PE-00448
[6 empty] | Return Date | 2018-12-27: 2018-11-14; 2018-12-27: 2018-11-14; 2019-02-04: 2019-01-16; 2019-02-04: 2019-01-16
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2241 | PROCESS EQUIPMENT DATA SHEET - 10-E-2240 - CG 4TH STAGE AFTERCOOLER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-22; 2019-02-04: 2018-12-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00206; 2018-12-27: TPSK-LSPA1-T-PE-00206; 2019-02-04: TPSK-LSPA1-T-PE-00436; 2019-02-04: TPSK-LSPA1-T-PE-00436
[6 empty] | Return Date | 2018-12-27: 2018-11-30; 2018-12-27: 2018-11-30; 2019-02-04: 2019-01-16; 2019-02-04: 2019-01-16
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2245 | PROCESS EQUIPMENT DATA SHEET - 10-D-2245 - CG 4TH STAGE DISCHARGE DRUM |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-01; 2019-02-04: 2018-12-13
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00264; 2018-12-27: TPSK-LSPA1-T-PE-00264; 2019-02-04: TPSK-LSPA1-T-PE-00480; 2019-02-04: TPSK-LSPA1-T-PE-00480
[6 empty] | Return Date | 2018-12-27: 2018-12-10; 2018-12-27: 2018-12-10; 2019-02-04: 2019-01-22; 2019-02-04: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2300 | PROCESS EQUIPMENT DATA SHEET - 10-T-2300 - CAUSTIC TOWER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | C | B | B | C
[6 empty] | Issue Plan | 2018-12-27: 2019-01-21; 2019-02-04: 2019-02-25
[6 empty] | Revised Plan | 2018-12-27: 2018-09-18; 2019-02-04: 2018-09-19
[6 empty] | Issue Actual | 2018-12-27: 2018-09-18; 2019-02-04: 2018-09-19; 2019-04-10: 2018-11-08; 2019-06-04: 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00060 | TPSK-LSPA1-T-PE-00060 | TPSK-LSPA1-T-PE-00597 | TPSK-LSPA1-T-PE-00290 | TPSK-LSPA1-T-PE-00290 | TPSK-LSPA1-T-PE-00597
[6 empty] | Return Date |  | 2018-10-24 | 2018-10-24 | 2019-01-28 | 2018-12-27 | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* |  | A3 | A3 | A1 | R2 | R2 | A1
| PE | OL1-2G30-2301 | PROCESS EQUIPMENT DATA SHEET - 10-X-2300 - CAUSTIC DILUENT MIXER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | C | B | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-15; 2018-12-27: 2018-10-16; 2019-04-10: 2018-11-28; 2019-04-10: 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00383 | TPSK-LSPA1-T-PE-00600 | TPSK-LSPA1-T-PE-00383 | TPSK-LSPA1-T-PE-00600
[6 empty] | Return Date | 2018-11-14 | 2018-11-14 | 2019-01-14 | 2019-02-04 | 2019-01-14 | 2019-02-04
Owner Cmmt* | bar: 2018-12-27 to 2019-04-10
| PE | OL1-2G30-2302 | PROCESS EQUIPMENT DATA SHEET - 10-P-2302 - STRONG CAUSTIC CIRCULATING PUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-02-04: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-15; 2018-12-27: 2018-10-16; 2019-02-04: 2018-12-20
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00174; 2018-12-27: TPSK-LSPA1-T-PE-00174; 2019-02-04: TPSK-LSPA1-T-PE-00524; 2019-02-04: TPSK-LSPA1-T-PE-00524
[6 empty] | Return Date | 2018-12-27: 2018-11-14; 2018-12-27: 2018-11-14; 2019-02-04: 2019-01-28; 2019-02-04: 2019-01-28
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2304 | PROCESS EQUIPMENT DATA SHEET - 10-P-2304 - INTERMEDIATE CAUSTIC CIRCULATING PUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-02-04: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-15; 2018-12-27: 2018-10-16; 2019-02-04: 2018-11-28
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00174; 2018-12-27: TPSK-LSPA1-T-PE-00174; 2019-02-04: TPSK-LSPA1-T-PE-00382; 2019-02-04: TPSK-LSPA1-T-PE-00382
[6 empty] | Return Date | 2018-12-27: 2018-11-14; 2018-12-27: 2018-11-14; 2019-02-04: 2019-01-14; 2019-02-04: 2019-01-14
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2305 | PROCESS EQUIPMENT DATA SHEET - 10-E-2305 - CAUSTIC TOWER FEED HEATER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-31; 2019-02-04: 2018-12-20
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00259; 2018-12-27: TPSK-LSPA1-T-PE-00259; 2019-02-04: TPSK-LSPA1-T-PE-00523; 2019-02-04: TPSK-LSPA1-T-PE-00523
[6 empty] | Return Date | 2018-12-27: 2018-12-10; 2018-12-27: 2018-12-10; 2019-02-04: 2019-01-28; 2019-02-04: 2019-01-28
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2306 | PROCESS EQUIPMENT DATA SHEET - 10-P-2306 - WEAK CAUSTIC CIRCULATING PUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-02-04: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-15; 2018-12-27: 2018-10-16; 2019-02-04: 2018-11-28
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00174; 2018-12-27: TPSK-LSPA1-T-PE-00174; 2019-02-04: TPSK-LSPA1-T-PE-00382; 2019-02-04: TPSK-LSPA1-T-PE-00382
[6 empty] | Return Date | 2018-12-27: 2018-11-14; 2018-12-27: 2018-11-14; 2019-02-04: 2019-01-14; 2019-02-04: 2019-01-14
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2307 | PROCESS EQUIPMENT DATA SHEET - 10-F-2306 - WEAK CAUSTIC STRAINER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2018-12-07; 2019-02-04: 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-22; 2019-02-04: 2018-12-13; 2019-04-10: 2019-01-30; 2019-04-10: 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00205 | TPSK-LSPA1-T-PE-00205 | TPSK-LSPA1-T-PE-00493 | TPSK-LSPA1-T-PE-00493 | TPSK-LSPA1-T-PE-00775 | TPSK-LSPA1-T-PE-00775
[6 empty] | Return Date | 2018-11-30 | 2018-11-30 | 2019-01-22 | 2019-01-22 | 2019-02-28 | 2019-02-28
Owner Cmmt* | bar: 2018-12-27 to 2019-04-10
| PE | OL1-2G30-2308 | PROCESS EQUIPMENT DATA SHEET - 10-X-2306 - WEAK CAUSTIC / WASH OIL MIXER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-02-04: IFD; 2019-02-04: IFD
Rev. | bar: 2018-12-27 to 2019-02-04
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-02-04: 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-15; 2018-12-27: 2018-10-16; 2019-02-04: 2018-11-28
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00173; 2018-12-27: TPSK-LSPA1-T-PE-00173; 2019-02-04: TPSK-LSPA1-T-PE-00383; 2019-02-04: TPSK-LSPA1-T-PE-00383
[6 empty] | Return Date | 2018-12-27: 2018-11-14; 2018-12-27: 2018-11-14; 2019-02-04: 2019-01-14; 2019-02-04: 2019-01-14
Owner Cmmt* | bar: 2018-12-27 to 2019-02-04
| PE | OL1-2G30-2309 | PROCESS EQUIPMENT DATA SHEET - 10-D-2305 - YELLOW OIL DRUM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-02-18 | B: 2019-03-25
[6 empty] | Revised Plan |  | A: 2018-09-27; A: 2018-09-28
[6 empty] | Issue Actual |  | 2018-09-27 | 2018-09-28 |  | 2019-01-11 | 2019-04-04 | 2019-04-05 | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00102 | TPSK-LSPA1-T-PE-00102 | TPSK-LSPA1-T-PE-00634 | TPSK-LSPA1-T-PE-00634 | TPSK-LSPA1-T-PE-01260 | TPSK-LSPA1-T-PE-01260 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01377
[6 empty] | Return Date |  | 2018-11-14 | 2018-11-14 | 2019-02-11 | 2019-02-11 |  |  | 2019-05-24 | 2019-05-24
Owner Cmmt* | bar: A to B; D to D
| PE | OL1-2G30-2310 | PROCESS EQUIPMENT DATA SHEET - 10-D-2310 - SPENT CAUSTIC DEOILING DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-31 |  | 2019-01-07 | 2019-07-02 | 2019-07-02 | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00254 | TPSK-LSPA1-T-PE-00254 | TPSK-LSPA1-T-PE-00599 | TPSK-LSPA1-T-PE-00599 | TPSK-LSPA1-T-PE-02043 | TPSK-LSPA1-T-PE-02043 | TPSK-LSPA1-T-PE-02168
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-01-28 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2311 | PROCESS EQUIPMENT DATA SHEET - 10-P-2310 - WASH OIL CIRCULATING PUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-10-16 |  | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174 | TPSK-LSPA1-T-PE-00174 | TPSK-LSPA1-T-PE-00524 | TPSK-LSPA1-T-PE-00524
[6 empty] | Return Date | 2018-11-14 | 2018-11-14 | 2019-01-28 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2313 | PROCESS EQUIPMENT DATA SHEET - 10-X-2312 - SPENT WASH OIL MIXER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-10-16 |  | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00525 | TPSK-LSPA1-T-PE-00525
[6 empty] | Return Date | 2018-11-14 | 2018-11-14 | 2019-01-28 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2314 | PROCESS EQUIPMENT DATA SHEET - 10-F-2310 - WASH OIL CIRCULATION FILTER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-22 |  | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00205 | TPSK-LSPA1-T-PE-00205 | TPSK-LSPA1-T-PE-00493 | TPSK-LSPA1-T-PE-00493
[6 empty] | Return Date | 2018-11-30 | 2018-11-30 | 2019-01-22 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2315 | PROCESS EQUIPMENT DATA SHEET - 10-X-2310 - SPENT CAUSTIC MIXER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-10-16 |  | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00525 | TPSK-LSPA1-T-PE-00525
[6 empty] | Return Date | 2018-11-14 | 2018-11-14 | 2019-01-28 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2316 | PROCESS EQUIPMENT DATA SHEET - 10-D-2316 - SPENT CAUSTIC DEGASSING DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-10-16 |  | 2019-01-11 | 2019-04-16 | 2019-04-17 | 2019-05-30 | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00175 | TPSK-LSPA1-T-PE-00175 | TPSK-LSPA1-T-PE-00634 | TPSK-LSPA1-T-PE-00634 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01785 | TPSK-LSPA1-T-PE-01785
[6 empty] | Return Date | 2018-11-26 | 2018-11-26 | 2019-02-11 | 2019-02-11 | 2019-05-24 | 2019-05-24 |  | 2019-06-25
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R2 | R2 |  | R1
| PE | OL1-2G30-2319 | PROCESS EQUIPMENT DATA SHEET - 10-F-2320 - SPENT CAUSTIC PUMP DISCHARGE FILTER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-31 |  | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00255 | TPSK-LSPA1-T-PE-00255 | TPSK-LSPA1-T-PE-00493 | TPSK-LSPA1-T-PE-00493
[6 empty] | Return Date | 2018-12-10 | 2018-12-10 | 2019-01-22 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2320 | PROCESS EQUIPMENT DATA SHEET - 10-TK-2320 - SPENT CAUSTIC STORAGE TANK |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-20 | 2018-09-24
[6 empty] | Issue Actual |  | 2018-09-20 | 2018-09-24 |  | 2018-10-22
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00068 | TPSK-LSPA1-T-PE-00068 | TPSK-LSPA1-T-PE-00203 | TPSK-LSPA1-T-PE-00203
[6 empty] | Return Date |  | 2018-10-09 | 2018-10-09 | 2018-11-30 | 2018-11-30
[6 empty] | Owner Cmmt* |  | A3 | A3 | A1 | A1
| PE | OL1-2G30-2321 | PROCESS EQUIPMENT DATA SHEET - 10-P-2320 - SPENT CAUSTIC PUMP |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-31 |  | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00252 | TPSK-LSPA1-T-PE-00252 | TPSK-LSPA1-T-PE-00598 | TPSK-LSPA1-T-PE-00598
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-01-28 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2322 | PROCESS EQUIPMENT DATA SHEET - 10-D-2322 - SKIM OIL DRUM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-02-18 | B: 2019-03-25
[6 empty] | Revised Plan |  | A: 2018-09-28; A: 2018-09-28
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-09-28 | 2019-03-25 | 2019-03-26 | 2019-04-16 | 2019-04-17 | 2019-05-13 | 2019-05-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00111 | TPSK-LSPA1-T-PE-00111 | TPSK-LSPA1-T-PE-01142 | TPSK-LSPA1-T-PE-01142 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01652 | TPSK-LSPA1-T-PE-01652
[6 empty] | Return Date |  | 2019-02-25 | 2019-02-25 | 2019-04-22 | 2019-04-22 | 2019-06-13 | 2019-06-13 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* |  | A1 | A1 | TP | TP | R1 | R1 | R1 | R1
| PE | OL1-2G30-2323 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2322 - SKIM OIL SUMP EDUCTOR |  | Class 1 | Purpose** | IFD | 2018-09-28: IFD; 2018-09-28: CAN; 2019-03-25: CAN
[6 empty] | Rev. | A | 2018-09-28: A; 2018-09-28: 0; 2019-03-25: 0
Issue Plan
[6 empty] | Revised Plan |  | 2018-09-28: 2019-01-07; 2018-09-28: 2019-03-19; 2019-03-25: 2019-03-20
[6 empty] | Issue Actual |  | 2018-09-28: 2019-01-07; 2018-09-28: 2019-03-19; 2019-03-25: 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00595 | 2018-09-28: TPSK-LSPA1-T-PE-00595; 2018-09-28: TPSK-LSPA1-T-PE-01098; 2019-03-25: TPSK-LSPA1-T-PE-01098
[6 empty] | Return Date | 2019-01-28 | 2018-09-28: 2019-01-28; 2018-09-28: 2019-04-10; 2019-03-25: 2019-04-10
[6 empty] | Owner Cmmt* | R1 | bar: 2018-09-28 to 2019-03-25
| PE | OL1-2G30-2324 | Process Equipment Datasheet - 10-TK-2300 - Fresh Caustic Day Tank |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 | 2018-09-28: 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-28: 2018-12-13; 2019-03-25: 2019-01-29; 2019-03-26: 2019-02-26; 2019-04-16: 2019-02-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00495 | TPSK-LSPA1-T-PE-00495 | TPSK-LSPA1-T-PE-00760 | TPSK-LSPA1-T-PE-00760 | TPSK-LSPA1-T-PE-00937 | TPSK-LSPA1-T-PE-00937
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-02-25 | 2019-02-25 | 2019-03-15 | 2019-03-15
[6 empty] | Owner Cmmt* | R2 | bar: 2018-09-28 to 2019-04-16
| PE | OL1-2G30-2325 | Process Equipment Datasheet - 10-P-2300 A-B - 10 Percent Caustic Makeup Pump |  | Class 2 | Purpose** | IFR | 2018-09-28: IFR; 2018-09-28: IFD; 2019-03-25: IFD
[6 empty] | Rev. | A | bar: 2018-09-28 to 2019-03-25
[6 empty] | Issue Plan | 2019-03-11 | 2018-09-28: 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-28: 2018-12-20; 2019-03-25: 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00526 | 2018-09-28: TPSK-LSPA1-T-PE-00526; 2018-09-28: TPSK-LSPA1-T-PE-00759; 2019-03-25: TPSK-LSPA1-T-PE-00759
[6 empty] | Return Date | 2019-01-28 | 2018-09-28: 2019-01-28; 2018-09-28: 2019-02-25; 2019-03-25: 2019-02-25
[6 empty] | Owner Cmmt* | R1 | bar: 2018-09-28 to 2019-03-25
| PE | OL1-2G30-2326 | PROCESS EQUIPMENT DATA SHEET - 10-E-2326 - SPENT CAUSTIC STRIPPER FEED HEATER |  | Class 1 | Purpose** | IFR | 2018-09-28: IFR; 2018-09-28: IFD; 2019-03-25: IFD
[6 empty] | Rev. | A | bar: 2018-09-28 to 2019-03-25
[6 empty] | Issue Plan | 2019-02-18 | 2018-09-28: 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-28: 2018-11-28; 2019-03-25: 2019-01-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00381 | 2018-09-28: TPSK-LSPA1-T-PE-00381; 2018-09-28: TPSK-LSPA1-T-PE-00690; 2019-03-25: TPSK-LSPA1-T-PE-00690
[6 empty] | Return Date | 2019-01-14 | 2018-09-28: 2019-01-14; 2018-09-28: 2019-03-05; 2019-03-25: 2019-03-05
[6 empty] | Owner Cmmt* | R2 | bar: 2018-09-28 to 2019-03-25
| PE | OL1-2G30-2327 | PROCESS EQUIPMENT DATA SHEET - 10-D-2326 - SPENT CAUSTIC STRIPPER FEED HTR COND POT |  | Class 1 | Purpose** | IFR | 2018-09-28: IFR; 2018-09-28: IFD; 2019-03-25: IFD
[6 empty] | Rev. | A | bar: 2018-09-28 to 2019-03-25
[6 empty] | Issue Plan | 2019-03-11 | 2018-09-28: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-03-25 | 2018-09-28: 2019-03-26; 2018-09-28: 2019-04-29; 2019-03-25: 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01152 | 2018-09-28: TPSK-LSPA1-T-PE-01152; 2018-09-28: TPSK-LSPA1-T-PE-01517; 2019-03-25: TPSK-LSPA1-T-PE-01517
[6 empty] | Return Date | 2019-04-12 | 2018-09-28: 2019-04-12; 2018-09-28: 2019-06-03; 2019-03-25: 2019-06-03
[6 empty] | Owner Cmmt* | R1 | bar: 2018-09-28 to 2019-03-25
| PE | OL1-2G30-2330 | PROCESS EQUIPMENT DATA SHEET - 10-T-2330 - SPENT CAUSTIC STRIPPER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-01-21 | C: 2019-02-25
[6 empty] | Revised Plan |  | A: 2018-09-24; A: 2018-09-25; B: 2018-10-11; B: 2018-10-12
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-09-25 | 2018-10-11 | 2018-10-12 |  | 2018-11-28 | 2019-06-05 | 2019-06-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00073 | TPSK-LSPA1-T-PE-00073 | TPSK-LSPA1-T-PE-00160 | TPSK-LSPA1-T-PE-00160 | TPSK-LSPA1-T-PE-00384 | TPSK-LSPA1-T-PE-00384 | TPSK-LSPA1-T-PE-01808 | TPSK-LSPA1-T-PE-01808
[6 empty] | Return Date |  | 2018-10-12 | 2018-10-12 | 2019-02-25 | 2019-02-25 | 2018-12-27 | 2018-12-27 |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | A3 | A3 | A2 | A2 | TP | TP |  | R2
| PE | OL1-2G30-2331 | PROCESS EQUIPMENT DATA SHEET - 10-D-2330 - SPENT CAUSTIC STRIPPER OVERHEAD DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D | E | E | F | F
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-10-16 |  | 2019-01-11 | 2019-04-11 | 2019-04-12 | 2019-04-16 | 2019-04-17 | 2019-05-20 | 2019-05-21 | 2019-07-11 | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00175 | TPSK-LSPA1-T-PE-00175 | TPSK-LSPA1-T-PE-00634 | TPSK-LSPA1-T-PE-00634 | TPSK-LSPA1-T-PE-01327 | TPSK-LSPA1-T-PE-01327 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01694 | TPSK-LSPA1-T-PE-01694 | TPSK-LSPA1-T-PE-02125 | TPSK-LSPA1-T-PE-02125
[6 empty] | Return Date | 2018-11-26 | 2018-11-26 | 2019-02-11 | 2019-02-11 | 2019-05-16 | 2019-05-16 |  |  | 2019-06-13 | 2019-06-13 | 2019-08-07
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | bar: 2019-01-11 to 2019-04-12; 2019-05-20 to 2019-07-11
| PE | OL1-2G30-2350 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2350 - WET AIR OXIDATION PACKAGE |  | Class 1 | Purpose** | IFR | IFR | IFD | 2019-01-11: IFD
[6 empty] | Rev. | A | A | B | bar: 2019-01-11
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2018-10-16 | 2018-10-16 | 2019-04-11 | 2019-01-11: 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00180 | TPSK-LSPA1-T-PE-00180 | TPSK-LSPA1-T-PE-01328 | 2019-01-11: TPSK-LSPA1-T-PE-01328
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-05-16 | 2019-01-11: 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | bar: 2019-01-11
| PE | OL1-2G30-2389 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2390 - CAUSTIC DRAIN SUMP EDUCTOR |  | Class 1 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. |  | A | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual |  |  | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00595 | TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date |  | 2019-01-28 | 2019-01-28
[6 empty] | Owner Cmmt* |  | R1 | R1
| PE | OL1-2G30-2390 | PROCESS EQUIPMENT DATA SHEET - 10-D-2390 - CAUSTIC DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-02-18 | B: 2019-03-25
[6 empty] | Revised Plan |  | A: 2018-09-27; A: 2018-09-28
[6 empty] | Issue Actual |  | 2018-09-27 | 2018-09-28 |  | 2018-11-27 | 2019-04-16 | 2019-04-17 | 2019-05-13 | 2019-05-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00102 | TPSK-LSPA1-T-PE-00102 | TPSK-LSPA1-T-PE-00369 | TPSK-LSPA1-T-PE-00369 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01652 | TPSK-LSPA1-T-PE-01652
[6 empty] | Return Date |  | 2018-11-14 | 2018-11-14 | 2019-01-14 | 2019-01-14 | 2019-06-13 | 2019-06-13 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: A to D
| PE | OL1-2G30-2391 | PROCESS EQUIPMENT DATA SHEET - 10-P-2390 - CAUSTIC DRAIN DRUM PUMP |  | Class 1 | Purpose** | IFR | A: IFR; A: IFD; B: IFD
[6 empty] | Rev. | A | bar: A to B
[6 empty] | Issue Plan | 2019-03-11 | A: 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | A: 2018-12-07; B: 2019-01-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00444 | A: TPSK-LSPA1-T-PE-00444; A: TPSK-LSPA1-T-PE-00695; B: TPSK-LSPA1-T-PE-00695
[6 empty] | Return Date | 2019-01-16 | A: 2019-01-16; A: 2019-03-05; B: 2019-03-05
[6 empty] | Owner Cmmt* | R2 | bar: A to B
| PE | OL1-2G30-2392 | PROCESS EQUIPMENT DATA SHEET - 10-D-2392 - SPENT CAUSTIC DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-02-18 | B: 2019-03-25
[6 empty] | Revised Plan |  | A: 2018-09-27; A: 2018-09-28
[6 empty] | Issue Actual |  | 2018-09-27 | 2018-09-28 |  | 2018-11-27 | 2019-04-16 | 2019-04-17 | 2019-05-13 | 2019-05-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00102 | TPSK-LSPA1-T-PE-00102 | TPSK-LSPA1-T-PE-00369 | TPSK-LSPA1-T-PE-00369 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01652 | TPSK-LSPA1-T-PE-01652
[6 empty] | Return Date |  | 2018-11-14 | 2018-11-14 | 2019-01-14 | 2019-01-14 | 2019-06-13 | 2019-06-13 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: A to D
| PE | OL1-2G30-2393 | PROCESS EQUIPMENT DATA SHEET - 10-P-2392 - SPENT CAUSTIC DRAIN DRUM PUMP |  | Class 1 | Purpose** | IFR | A: IFR; A: IFD; B: IFD
[6 empty] | Rev. | A | bar: A to B
[6 empty] | Issue Plan | 2019-03-11 | A: 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | A: 2018-10-31; B: 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00252 | A: TPSK-LSPA1-T-PE-00252; A: TPSK-LSPA1-T-PE-00598; B: TPSK-LSPA1-T-PE-00598
[6 empty] | Return Date | 2018-12-27 | A: 2018-12-27; A: 2019-01-28; B: 2019-01-28
[6 empty] | Owner Cmmt* | R1 | bar: A to B
| PE | OL1-2G30-2394 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2392 - SPENT CAUSTIC DRAIN SUMP EDUCTOR |  | Class 1 | Purpose** | IFR | A: IFD; A: IFD
Rev. | bar: A to A
[6 empty] | Issue Plan | 2019-02-18 | A: 2019-03-11
Revised Plan
[6 empty] | Issue Actual |  | A: 2019-01-07
[6 empty] | Transmittal no. |  | A: TPSK-LSPA1-T-PE-00595; A: TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date |  | A: 2019-01-28; A: 2019-01-28
Owner Cmmt* | bar: A to A
| PE | OL1-2G30-2405 | PROCESS EQUIPMENT DATA SHEET - 10-D-2405 - GAS DRYER FEED KO DRUM |  | Class 1 | Purpose** | IFR | A: IFR; A: IFD; B: IFD
[6 empty] | Rev. | A | bar: A to B
[6 empty] | Issue Plan | 2019-02-18 | A: 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | A: 2018-11-14; B: 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00315 | A: TPSK-LSPA1-T-PE-00315; A: TPSK-LSPA1-T-PE-00480; B: TPSK-LSPA1-T-PE-00480
[6 empty] | Return Date | 2018-12-10 | A: 2018-12-10; A: 2018-12-27; B: 2018-12-27
[6 empty] | Owner Cmmt* | R2 | bar: A to B
| PE | OL1-2G30-2406 | PROCESS EQUIPMENT DATA SHEET - 10-E-2405 - GAS DRYER FEED CHILLER |  | Class 1 | Purpose** | IFR | A: IFR; A: IFD; B: IFD
[6 empty] | Rev. | A | bar: A to B
[6 empty] | Issue Plan | 2019-02-18 | A: 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | A: 2018-10-30; B: 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00239 | A: TPSK-LSPA1-T-PE-00239; A: TPSK-LSPA1-T-PE-00523; B: TPSK-LSPA1-T-PE-00523
[6 empty] | Return Date | 2018-11-14 | A: 2018-11-14; A: 2019-01-14; B: 2019-01-14
[6 empty] | Owner Cmmt* | R1 | bar: A to B
| PE | OL1-2G30-2410 | PROCESS EQUIPMENT DATA SHEET - 10-D-2410 - CRACKED GAS DRYER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-07 |  | 2019-01-18 | 2019-03-04 | 2019-03-05 | 2019-04-10 | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-00678 | TPSK-LSPA1-T-PE-00678 | TPSK-LSPA1-T-PE-00980 | TPSK-LSPA1-T-PE-00980 | TPSK-LSPA1-T-PE-01310 | TPSK-LSPA1-T-PE-01310
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-01-29 | 2019-01-29 | 2019-03-13 | 2019-03-13 | 2019-05-16 | 2019-05-16
Owner Cmmt* | bar: 2018-12-27 to 2019-05-16
| PE | OL1-2G30-2411 | PROCESS EQUIPMENT DATA SHEET - 10-D-2411 - CRACKED GAS MERCURY ADSORBER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-20; 2019-01-29: 2019-01-08; 2019-03-13: 2019-03-18; 2019-03-13: 2019-03-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00339 | TPSK-LSPA1-T-PE-00339 | TPSK-LSPA1-T-PE-00610 | TPSK-LSPA1-T-PE-00610 | TPSK-LSPA1-T-PE-01089 | TPSK-LSPA1-T-PE-01089
[6 empty] | Return Date | 2018-12-13 | 2018-12-13 | 2019-01-22 | 2019-01-22 | 2019-04-02 | 2019-04-02
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2412 | PROCESS EQUIPMENT DATA SHEET - 10-E-2412 - HP DEPROPANIZER FEED CHILLER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-30; 2019-01-29: 2018-12-20
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00239; 2018-12-27: TPSK-LSPA1-T-PE-00239; 2019-01-29: TPSK-LSPA1-T-PE-00523; 2019-01-29: TPSK-LSPA1-T-PE-00523
[6 empty] | Return Date | 2018-12-27: 2018-11-14; 2018-12-27: 2018-11-14; 2019-01-29: 2019-01-14; 2019-01-29: 2019-01-14
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2413 | PROCESS EQUIPMENT DATA SHEET - 10-E-2413 - HP DEPROP FEED / OVERHEAD EXCHANGER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-31; 2019-01-29: 2018-11-29
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00250; 2018-12-27: TPSK-LSPA1-T-PE-00250; 2019-01-29: TPSK-LSPA1-T-PE-00392; 2019-01-29: TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-12-27: 2018-11-20; 2018-12-27: 2018-11-20; 2019-01-29: 2018-12-10; 2019-01-29: 2018-12-10
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2415 | PROCESS EQUIPMENT DATA SHEET - 10-D-2415 - CG LIQUID DRYER FEED COALESCER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-20; 2019-01-29: 2019-01-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00339; 2018-12-27: TPSK-LSPA1-T-PE-00339; 2019-01-29: TPSK-LSPA1-T-PE-00596; 2019-01-29: TPSK-LSPA1-T-PE-00596
[6 empty] | Return Date | 2018-12-27: 2018-12-13; 2018-12-27: 2018-12-13; 2019-01-29: 2019-01-22; 2019-01-29: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2416 | PROCESS EQUIPMENT DATA SHEET - 10-P-2415 - CG LIQUID DRYER FEED PUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-01-29: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-07; 2019-01-29: 2019-01-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00285; 2018-12-27: TPSK-LSPA1-T-PE-00285; 2019-01-29: TPSK-LSPA1-T-PE-00593; 2019-01-29: TPSK-LSPA1-T-PE-00593
[6 empty] | Return Date | 2018-12-27: 2018-12-27; 2018-12-27: 2018-12-27; 2019-01-29: 2019-01-22; 2019-01-29: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2420 | PROCESS EQUIPMENT DATA SHEET - 10-D-2420 - CG LIQUID DRYER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-09; 2019-01-29: 2019-01-08; 2019-03-13: 2019-03-18; 2019-03-13: 2019-03-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00301 | TPSK-LSPA1-T-PE-00301 | TPSK-LSPA1-T-PE-00610 | TPSK-LSPA1-T-PE-00610 | TPSK-LSPA1-T-PE-01089 | TPSK-LSPA1-T-PE-01089
[6 empty] | Return Date | 2018-11-30 | 2018-11-30 | 2019-01-22 | 2019-01-22 | 2019-04-02 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | CL | CL
| PE | OL1-2G30-2430 | PROCESS EQUIPMENT DATA SHEET - 10-E-2430 - REGEN GAS FEED HEATER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-01-03; 2019-01-29: 2019-01-22
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00574; 2018-12-27: TPSK-LSPA1-T-PE-00574; 2019-01-29: TPSK-LSPA1-T-PE-00696; 2019-01-29: TPSK-LSPA1-T-PE-00696
[6 empty] | Return Date | 2018-12-27: 2019-01-22; 2018-12-27: 2019-01-22; 2019-01-29: 2019-02-11; 2019-01-29: 2019-02-11
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2432 | PROCESS EQUIPMENT DATA SHEET - 10-E-2432 - REGEN GAS SHP HEATER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-01-03; 2019-01-29: 2019-01-22
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00574; 2018-12-27: TPSK-LSPA1-T-PE-00574; 2019-01-29: TPSK-LSPA1-T-PE-00696; 2019-01-29: TPSK-LSPA1-T-PE-00696
[6 empty] | Return Date | 2018-12-27: 2019-01-22; 2018-12-27: 2019-01-22; 2019-01-29: 2019-02-11; 2019-01-29: 2019-02-11
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2434 | PROCESS EQUIPMENT DATA SHEET - 10-E-2435 - REGEN GAS EFFLUENT COOLER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-01-03; 2019-01-29: 2019-01-22
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00574; 2018-12-27: TPSK-LSPA1-T-PE-00574; 2019-01-29: TPSK-LSPA1-T-PE-00696; 2019-01-29: TPSK-LSPA1-T-PE-00696
[6 empty] | Return Date | 2018-12-27: 2019-01-22; 2018-12-27: 2019-01-22; 2019-01-29: 2019-02-11; 2019-01-29: 2019-02-11
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2435 | PROCESS EQUIPMENT DATA SHEET - 10-D-2435 - REGEN GAS SEPARATOR |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-12-20; 2019-01-29: 2019-01-25
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00559; 2018-12-27: TPSK-LSPA1-T-PE-00559; 2019-01-29: TPSK-LSPA1-T-PE-00725; 2019-01-29: TPSK-LSPA1-T-PE-00725
[6 empty] | Return Date | 2018-12-27: 2019-01-22; 2018-12-27: 2019-01-22; 2019-01-29: 2019-02-11; 2019-01-29: 2019-02-11
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2438 | PROCESS EQUIPMENT DATA SHEET - 10-D-2440 - HP DEPROPANIZER REFLUX DRUM |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-01; 2019-01-29: 2018-12-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00264; 2018-12-27: TPSK-LSPA1-T-PE-00264; 2019-01-29: TPSK-LSPA1-T-PE-00430; 2019-01-29: TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-12-27: 2018-11-27; 2018-12-27: 2018-11-27; 2019-01-29: 2018-12-18; 2019-01-29: 2018-12-18
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2439 | PROCESS EQUIPMENT DATA SHEET - 10-E-2440 - HP DEPROPANIZER CONDENSER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-31; 2019-01-29: 2018-11-29
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00250; 2018-12-27: TPSK-LSPA1-T-PE-00250; 2019-01-29: TPSK-LSPA1-T-PE-00392; 2019-01-29: TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-12-27: 2018-11-20; 2018-12-27: 2018-11-20; 2019-01-29: 2018-12-10; 2019-01-29: 2018-12-10
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2440 | PROCESS EQUIPMENT DATA SHEET - 10-T-2440 - HP DEPROPANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-01-21; 2019-01-29: 2019-02-25
[6 empty] | Revised Plan | 2018-12-27: 2018-09-14; 2019-01-29: 2018-09-17
[6 empty] | Issue Actual | 2018-12-27: 2018-09-14; 2019-01-29: 2018-09-17; 2019-01-29: 2018-10-12; 2019-03-13: 2018-10-15
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00053; 2019-01-29: TPSK-LSPA1-T-PE-00053; 2019-01-29: TPSK-LSPA1-T-PE-00167; 2019-03-13: TPSK-LSPA1-T-PE-00167
[6 empty] | Return Date | 2018-12-27: 2018-10-03; 2019-01-29: 2018-10-03
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2441 | PROCESS EQUIPMENT DATA SHEET - 10-E-2441 - HP DEPROP REFLUX CHILLER NO. 2 |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-31; 2019-01-29: 2018-11-29
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00250; 2018-12-27: TPSK-LSPA1-T-PE-00250; 2019-01-29: TPSK-LSPA1-T-PE-00392; 2019-01-29: TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-12-27: 2018-11-20; 2018-12-27: 2018-11-20; 2019-01-29: 2018-12-10; 2019-01-29: 2018-12-10
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2442 | PROCESS EQUIPMENT DATA SHEET - 10-E-2442 - HP DEPROP REFLUX CHILLER NO. 1 |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-31; 2019-01-29: 2018-11-29
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00250; 2018-12-27: TPSK-LSPA1-T-PE-00250; 2019-01-29: TPSK-LSPA1-T-PE-00392; 2019-01-29: TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-12-27: 2018-11-20; 2018-12-27: 2018-11-20; 2019-01-29: 2018-12-10; 2019-01-29: 2018-12-10
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2443 | PROCESS EQUIPMENT DATA SHEET - 10-P-2445 - HP DEPROPANIZER COND PUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-01-29: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-12-04; 2019-01-29: 2018-12-27
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00408; 2018-12-27: TPSK-LSPA1-T-PE-00408; 2019-01-29: TPSK-LSPA1-T-PE-00568; 2019-01-29: TPSK-LSPA1-T-PE-00568
[6 empty] | Return Date | 2018-12-27: 2018-12-17; 2018-12-27: 2018-12-17; 2019-01-29: 2019-01-14; 2019-01-29: 2019-01-14
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2444 | PROCESS EQUIPMENT DATA SHEET - 10-D-2445 - HP DEPROP REBOILER COND POT |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-12-11; 2019-01-29: 2018-12-27
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00474; 2018-12-27: TPSK-LSPA1-T-PE-00474; 2019-01-29: TPSK-LSPA1-T-PE-00563; 2019-01-29: TPSK-LSPA1-T-PE-00563
[6 empty] | Return Date | 2018-12-27: 2018-12-21; 2018-12-27: 2018-12-21; 2019-01-29: 2019-01-14; 2019-01-29: 2019-01-14
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2445 | PROCESS EQUIPMENT DATA SHEET - 10-E-2445 - HP DEPROPANIZER REBOILER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-01; 2019-01-29: 2018-12-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00267; 2018-12-27: TPSK-LSPA1-T-PE-00267; 2019-01-29: TPSK-LSPA1-T-PE-00436; 2019-01-29: TPSK-LSPA1-T-PE-00436
[6 empty] | Return Date | 2018-12-27: 2018-11-26; 2018-12-27: 2018-11-26; 2019-01-29: 2018-12-18; 2019-01-29: 2018-12-18
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2446 | PROCESS EQUIPMENT DATA SHEET - 10-E-2446 - LP DEPROPANIZER FEED COOLER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-31; 2019-01-29: 2018-11-29
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00250; 2018-12-27: TPSK-LSPA1-T-PE-00250; 2019-01-29: TPSK-LSPA1-T-PE-00392; 2019-01-29: TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-12-27: 2018-11-20; 2018-12-27: 2018-11-20; 2019-01-29: 2018-12-10; 2019-01-29: 2018-12-10
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2450 | PROCESS EQUIPMENT DATA SHEET - 10-T-2450 - LP DEPROPANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-01-21; 2019-01-29: 2019-02-25
[6 empty] | Revised Plan | 2018-12-27: 2018-09-14; 2019-01-29: 2018-09-17
[6 empty] | Issue Actual | 2018-12-27: 2018-09-14; 2019-01-29: 2018-09-17; 2019-01-29: 2018-10-12; 2019-03-13: 2018-10-15
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00053; 2019-01-29: TPSK-LSPA1-T-PE-00053; 2019-01-29: TPSK-LSPA1-T-PE-00167; 2019-03-13: TPSK-LSPA1-T-PE-00167
[6 empty] | Return Date | 2018-12-27: 2018-10-03; 2019-01-29: 2018-10-03
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2451 | PROCESS EQUIPMENT DATA SHEET - 10-E-2450 - LP DEPROPANIZER CONDENSER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-31; 2019-01-29: 2018-11-29
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00259; 2018-12-27: TPSK-LSPA1-T-PE-00259; 2019-01-29: TPSK-LSPA1-T-PE-00392; 2019-01-29: TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-12-27: 2018-11-20; 2018-12-27: 2018-11-20; 2019-01-29: 2018-12-10; 2019-01-29: 2018-12-10
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2452 | PROCESS EQUIPMENT DATA SHEET - 10-D-2450 - LP DEPROPANIZER REFLUX DRUM |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-01; 2019-01-29: 2018-12-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00264; 2018-12-27: TPSK-LSPA1-T-PE-00264; 2019-01-29: TPSK-LSPA1-T-PE-00430; 2019-01-29: TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-12-27: 2018-11-27; 2018-12-27: 2018-11-27; 2019-01-29: 2018-12-18; 2019-01-29: 2018-12-18
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2453 | PROCESS EQUIPMENT DATA SHEET - 10-P-2450 - LP DEPROPANIZER REFLUX / PRODUCT PUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-01-29: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-07; 2019-01-29: 2019-01-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00285; 2018-12-27: TPSK-LSPA1-T-PE-00285; 2019-01-29: TPSK-LSPA1-T-PE-00593; 2019-01-29: TPSK-LSPA1-T-PE-00593
[6 empty] | Return Date | 2018-12-27: 2018-12-27; 2018-12-27: 2018-12-27; 2019-01-29: 2019-01-22; 2019-01-29: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2455 | PROCESS EQUIPMENT DATA SHEET - 10-E-2455 - LP DEPROPANIZER REBOILER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-25; 2019-01-29: 2018-12-20
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00228; 2018-12-27: TPSK-LSPA1-T-PE-00228; 2019-01-29: TPSK-LSPA1-T-PE-00523; 2019-01-29: TPSK-LSPA1-T-PE-00523
[6 empty] | Return Date | 2018-12-27: 2018-11-14; 2018-12-27: 2018-11-14; 2019-01-29: 2019-01-14; 2019-01-29: 2019-01-14
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2456 | PROCESS EQUIPMENT DATA SHEET - 10-D-2455 - LP DEPROP REBOILER COND POT |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-12-11; 2019-01-29: 2018-12-27
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00474; 2018-12-27: TPSK-LSPA1-T-PE-00474; 2019-01-29: TPSK-LSPA1-T-PE-00563; 2019-01-29: TPSK-LSPA1-T-PE-00563
[6 empty] | Return Date | 2018-12-27: 2018-12-21; 2018-12-27: 2018-12-21; 2019-01-29: 2019-01-14; 2019-01-29: 2019-01-14
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2457 | PROCESS EQUIPMENT DATA SHEET - 10-P-2455 - LP DEPROPANIZER COND PUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-01-29: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-12-04; 2019-01-29: 2018-12-27
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00408; 2018-12-27: TPSK-LSPA1-T-PE-00408; 2019-01-29: TPSK-LSPA1-T-PE-00568; 2019-01-29: TPSK-LSPA1-T-PE-00568
[6 empty] | Return Date | 2018-12-27: 2018-12-17; 2018-12-27: 2018-12-17; 2019-01-29: 2019-01-14; 2019-01-29: 2019-01-14
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2460 | PROCESS EQUIPMENT DATA SHEET - 10-D-2460 - C2 HYDROG ARSINE GUARD BED |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-12-10; 2019-01-29: 2019-01-16
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00453; 2018-12-27: TPSK-LSPA1-T-PE-00453; 2019-01-29: TPSK-LSPA1-T-PE-00660; 2019-01-29: TPSK-LSPA1-T-PE-00660
[6 empty] | Return Date | 2018-12-27: 2019-01-16; 2018-12-27: 2019-01-16; 2019-01-29: 2019-01-29; 2019-01-29: 2019-01-29
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2461 | PROCESS EQUIPMENT DATA SHEET - 10-E-2460 - C2 HYDROG FEED COOLER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-31; 2019-01-29: 2018-11-29
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00250; 2018-12-27: TPSK-LSPA1-T-PE-00250; 2019-01-29: TPSK-LSPA1-T-PE-00392; 2019-01-29: TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-12-27: 2018-11-20; 2018-12-27: 2018-11-20; 2019-01-29: 2018-12-10; 2019-01-29: 2018-12-10
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2465 | PROCESS EQUIPMENT DATA SHEET - 10-E-2465 - C2 HYDROG FEED HEATER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-29; 2019-01-29: 2019-01-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00391; 2018-12-27: TPSK-LSPA1-T-PE-00391; 2019-01-29: TPSK-LSPA1-T-PE-00602; 2019-01-29: TPSK-LSPA1-T-PE-00602
[6 empty] | Return Date | 2018-12-27: 2018-12-13; 2018-12-27: 2018-12-13; 2019-01-29: 2019-01-22; 2019-01-29: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2470 | PROCESS EQUIPMENT DATA SHEET - 10-R-2470 - C2 HYDROG REACTOR |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-01-16; 2019-01-29: 2019-02-06
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-09; 2019-01-29: 2019-01-08
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00299; 2018-12-27: TPSK-LSPA1-T-PE-00299; 2019-01-29: TPSK-LSPA1-T-PE-00609; 2019-01-29: TPSK-LSPA1-T-PE-00609
[6 empty] | Return Date | 2018-12-27: 2018-11-29; 2018-12-27: 2018-11-29; 2019-01-29: 2019-01-22; 2019-01-29: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2471 | PROCESS EQUIPMENT DATA SHEET - 10-E-2470 - C2 HYDROG 1ST STAGE INTERCOOLER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-29; 2019-01-29: 2019-01-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00391; 2018-12-27: TPSK-LSPA1-T-PE-00391; 2019-01-29: TPSK-LSPA1-T-PE-00602; 2019-01-29: TPSK-LSPA1-T-PE-00602
[6 empty] | Return Date | 2018-12-27: 2018-12-13; 2018-12-27: 2018-12-13; 2019-01-29: 2019-01-22; 2019-01-29: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2472 | PROCESS EQUIPMENT DATA SHEET - 10-E-2472 - C2 HYDROG 2ND STAGE INTERCOOLER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-29; 2019-01-29: 2019-01-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00391; 2018-12-27: TPSK-LSPA1-T-PE-00391; 2019-01-29: TPSK-LSPA1-T-PE-00602; 2019-01-29: TPSK-LSPA1-T-PE-00602
[6 empty] | Return Date | 2018-12-27: 2018-12-13; 2018-12-27: 2018-12-13; 2019-01-29: 2019-01-22; 2019-01-29: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2474 | PROCESS EQUIPMENT DATA SHEET - 10-E-2474 - C2 HYDROG AFTERCOOLER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-29; 2019-01-29: 2019-01-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00391; 2018-12-27: TPSK-LSPA1-T-PE-00391; 2019-01-29: TPSK-LSPA1-T-PE-00602; 2019-01-29: TPSK-LSPA1-T-PE-00602
[6 empty] | Return Date | 2018-12-27: 2018-12-13; 2018-12-27: 2018-12-13; 2019-01-29: 2019-01-22; 2019-01-29: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2480 | PROCESS EQUIPMENT DATA SHEET - 10-D-2480 - CG SECONDARY DRYER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-28; 2019-01-29: 2019-01-11
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00386; 2018-12-27: TPSK-LSPA1-T-PE-00386; 2019-01-29: TPSK-LSPA1-T-PE-00637; 2019-01-29: TPSK-LSPA1-T-PE-00637
[6 empty] | Return Date | 2018-12-27: 2018-12-13; 2018-12-27: 2018-12-13; 2019-01-29: 2019-01-31; 2019-01-29: 2019-01-31
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2500 | PROCESS EQUIPMENT DATA SHEET - 10-E-2500 - PROPYLENE REFRIG SUBCOOLER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-11; 2019-01-29: 2018-09-12
[6 empty] | Issue Actual | 2018-12-27: 2018-09-11; 2019-01-29: 2018-09-12; 2019-01-29: 2018-10-04; 2019-03-13: 2018-10-05
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00039; 2019-01-29: TPSK-LSPA1-T-PE-00039; 2019-01-29: TPSK-LSPA1-T-PE-00131; 2019-03-13: TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-12-27: 2018-09-28; 2019-01-29: 2018-09-28
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2502 | PROCESS EQUIPMENT DATA SHEET - 10-E-2502 - DEMETH PREFRAC FEED COOLER NO. 1 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | C | B | B | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11
[6 empty] | Issue Actual | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11; 2019-03-13: 2018-11-05; 2019-05-16: 2018-12-11
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00475 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00475
[6 empty] | Return Date |  | 2018-10-02 | 2018-10-02 | 2019-01-10 | 2018-11-26 | 2018-11-26 | 2019-01-10
Owner Cmmt* | bar: 2018-12-27 to 2019-05-16
| PE | OL1-2G30-2503 | PROCESS EQUIPMENT DATA SHEET - 10-E-2504 - DEMETH PREFRAC FEED COOLER NO. 2 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11
[6 empty] | Issue Actual | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11; 2019-03-13: 2018-11-05
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00036; 2019-01-29: TPSK-LSPA1-T-PE-00036; 2019-01-29: TPSK-LSPA1-T-PE-00272; 2019-03-13: TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-12-27: 2018-10-02; 2019-01-29: 2018-10-02; 2019-01-29: 2018-11-26; 2019-03-13: 2018-11-26
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2504 | PROCESS EQUIPMENT DATA SHEET - 10-D-2504 - DEMETH PREFRAC FEED SEPARATOR NO. 1 |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-24; 2019-01-29: 2018-11-09
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00217; 2018-12-27: TPSK-LSPA1-T-PE-00217; 2019-01-29: TPSK-LSPA1-T-PE-00303; 2019-01-29: TPSK-LSPA1-T-PE-00303
[6 empty] | Return Date | 2018-12-27: 2018-11-07; 2018-12-27: 2018-11-07; 2019-01-29: 2018-11-26; 2019-01-29: 2018-11-26
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2505 | PROCESS EQUIPMENT DATA SHEET - 10-E-2506 - DEMETH PREFRAC FEED COOLER NO. 3 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-09-11 | 2018-10-04 | 2018-10-05 | 2019-02-06 | 2019-02-06
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-PE-00811 | TPSK-LSPA1-T-PE-00811
[6 empty] | Return Date | 2018-12-27: 2018-10-02; 2019-01-29: 2018-10-02; 2019-03-13: 2019-02-25; 2019-05-16: 2019-02-25
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29; 2019-03-13 to 2019-05-16
| PE | OL1-2G30-2506 | PROCESS EQUIPMENT DATA SHEET - 10-D-2506 - DEMETH PREFRAC FEED SEPARATOR NO. 2 |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-24; 2019-01-29: 2018-11-09; 2019-03-13: 2019-07-02; 2019-03-13: 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00217 | TPSK-LSPA1-T-PE-00217 | TPSK-LSPA1-T-PE-00303 | TPSK-LSPA1-T-PE-00303 | TPSK-LSPA1-T-PE-02040 | TPSK-LSPA1-T-PE-02040
[6 empty] | Return Date | 2018-11-07 | 2018-11-07 | 2018-11-26 | 2018-11-26 | 2019-07-17 | 2019-07-17
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2508 | PROCESS EQUIPMENT DATA SHEET - 10-D-2508 - DEMETH PREFRAC FEED SEPARATOR NO. 3 |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-24; 2019-01-29: 2018-11-09
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00217; 2018-12-27: TPSK-LSPA1-T-PE-00217; 2019-01-29: TPSK-LSPA1-T-PE-00303; 2019-01-29: TPSK-LSPA1-T-PE-00303
[6 empty] | Return Date | 2018-12-27: 2018-11-07; 2018-12-27: 2018-11-07; 2019-01-29: 2018-11-26; 2019-01-29: 2018-11-26
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2510 | PROCESS EQUIPMENT DATA SHEET - 10-T-2510 - DEMETHANIZER PREFRACTIONATOR |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-01-21; 2019-01-29: 2019-02-25
[6 empty] | Revised Plan | 2018-12-27: 2018-09-25; 2019-01-29: 2018-09-26
[6 empty] | Issue Actual | 2018-12-27: 2018-09-25; 2019-01-29: 2018-09-26; 2019-03-13: 2018-11-09
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00092; 2019-01-29: TPSK-LSPA1-T-PE-00092; 2019-01-29: TPSK-LSPA1-T-PE-00306; 2019-03-13: TPSK-LSPA1-T-PE-00306
[6 empty] | Return Date | 2018-12-27: 2018-10-24; 2019-01-29: 2018-10-24; 2019-01-29: 2018-11-29; 2019-03-13: 2018-11-29
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2511 | PROCESS EQUIPMENT DATA SHEET - 10-E-2510 - DEMETH PREFRAC CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11
[6 empty] | Issue Actual | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11; 2019-01-29: 2018-10-04; 2019-03-13: 2018-10-05
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00036; 2019-01-29: TPSK-LSPA1-T-PE-00036; 2019-01-29: TPSK-LSPA1-T-PE-00131; 2019-03-13: TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-12-27: 2018-10-02; 2019-01-29: 2018-10-02
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2515 | PROCESS EQUIPMENT DATA SHEET - 10-E-2515 - DEMETH PREFRACTIONATOR REBOILER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-24; 2019-01-29: 2018-12-13
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00216; 2018-12-27: TPSK-LSPA1-T-PE-00216; 2019-01-29: TPSK-LSPA1-T-PE-00492; 2019-01-29: TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-12-27: 2018-11-14; 2018-12-27: 2018-11-14; 2019-01-29: 2019-01-22; 2019-01-29: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2520 | PROCESS EQUIPMENT DATA SHEET - 10-T-2520 - RESIDUE GAS RECTIFIER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-01-21; 2019-01-29: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-15; 2018-12-27: 2018-10-16; 2019-01-29: 2018-12-04
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00172; 2018-12-27: TPSK-LSPA1-T-PE-00172; 2019-01-29: TPSK-LSPA1-T-PE-00407; 2019-01-29: TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-12-27: 2018-11-05; 2018-12-27: 2018-11-05; 2019-01-29: 2018-12-17; 2019-01-29: 2018-12-17
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2521 | PROCESS EQUIPMENT DATA SHEET - 10-E-2520 - RECTIFIER CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11
[6 empty] | Issue Actual | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11; 2019-01-29: 2018-10-04; 2019-03-13: 2018-10-05
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00036; 2019-01-29: TPSK-LSPA1-T-PE-00036; 2019-01-29: TPSK-LSPA1-T-PE-00131; 2019-03-13: TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-12-27: 2018-10-02; 2019-01-29: 2018-10-02
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2525 | PROCESS EQUIPMENT DATA SHEET - 10-D-2525 - HYDROGEN DRUM |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-24; 2019-01-29: 2018-12-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00218; 2018-12-27: TPSK-LSPA1-T-PE-00218; 2019-01-29: TPSK-LSPA1-T-PE-00430; 2019-01-29: TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-12-27: 2018-11-09; 2018-12-27: 2018-11-09; 2019-01-29: 2018-12-18; 2019-01-29: 2018-12-18
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2526 | PROCESS EQUIPMENT DATA SHEET - 10-E-2525 - HYDROGEN CORE EXCHANGER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11
[6 empty] | Issue Actual | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11; 2019-01-29: 2018-10-04; 2019-03-13: 2018-10-05
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00036; 2019-01-29: TPSK-LSPA1-T-PE-00036; 2019-01-29: TPSK-LSPA1-T-PE-00131; 2019-03-13: TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-12-27: 2018-10-02; 2019-01-29: 2018-10-02
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2531 | PROCESS EQUIPMENT DATA SHEET - 10-E-2530 - DEMETH FEED COOLER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11
[6 empty] | Issue Actual | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11; 2019-01-29: 2018-10-04; 2019-03-13: 2018-10-05
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00036; 2019-01-29: TPSK-LSPA1-T-PE-00036; 2019-01-29: TPSK-LSPA1-T-PE-00131; 2019-03-13: TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-12-27: 2018-10-02; 2019-01-29: 2018-10-02
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2540 | PROCESS EQUIPMENT DATA SHEET - 10-T-2540 - DEMETHANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | C | B | B | C
[6 empty] | Issue Plan | 2018-12-27: 2019-01-21; 2019-01-29: 2019-02-25
[6 empty] | Revised Plan | 2018-12-27: 2018-09-24; 2019-01-29: 2018-09-25
[6 empty] | Issue Actual | 2018-12-27: 2018-09-24; 2019-01-29: 2018-09-25; 2019-03-13: 2018-11-09; 2019-05-16: 2018-12-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00073 | TPSK-LSPA1-T-PE-00073 | TPSK-LSPA1-T-PE-00407 | TPSK-LSPA1-T-PE-00306 | TPSK-LSPA1-T-PE-00306 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date |  | 2018-10-24 | 2018-10-24 | 2018-12-17 | 2018-11-29 | 2018-11-29 | 2018-12-17
Owner Cmmt* | bar: 2018-12-27 to 2019-05-16
| PE | OL1-2G30-2541 | PROCESS EQUIPMENT DATA SHEET - 10-E-2540 - DEMETHANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11
[6 empty] | Issue Actual | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11; 2019-01-29: 2018-10-04; 2019-03-13: 2018-10-05
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00036; 2019-01-29: TPSK-LSPA1-T-PE-00036; 2019-01-29: TPSK-LSPA1-T-PE-00131; 2019-03-13: TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-12-27: 2018-10-02; 2019-01-29: 2018-10-02
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2545 | PROCESS EQUIPMENT DATA SHEET - 10-E-2545 - DEMETHANIZER REBOILER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-24; 2019-01-29: 2018-12-13
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00216; 2018-12-27: TPSK-LSPA1-T-PE-00216; 2019-01-29: TPSK-LSPA1-T-PE-00492; 2019-01-29: TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-12-27: 2018-11-14; 2018-12-27: 2018-11-14; 2019-01-29: 2019-01-22; 2019-01-29: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2546 | PROCESS EQUIPMENT DATA SHEET - 10-E-2546 - DEMETHANIZER BOTTOMS COOLER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-24; 2019-01-29: 2018-12-13
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00216; 2018-12-27: TPSK-LSPA1-T-PE-00216; 2019-01-29: TPSK-LSPA1-T-PE-00492; 2019-01-29: TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-12-27: 2018-11-14; 2018-12-27: 2018-11-14; 2019-01-29: 2019-01-22; 2019-01-29: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2548 | PROCESS EQUIPMENT DATA SHEET - 10-E-2548 - DEMETHANIZER BOTTOMS VAPORIZER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-24; 2019-01-29: 2018-12-10
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00216; 2018-12-27: TPSK-LSPA1-T-PE-00216; 2019-01-29: TPSK-LSPA1-T-PE-00464; 2019-01-29: TPSK-LSPA1-T-PE-00464
[6 empty] | Return Date | 2018-12-27: 2018-11-14; 2018-12-27: 2018-11-14; 2019-01-29: 2018-12-27; 2019-01-29: 2018-12-27
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2550 | PROCESS EQUIPMENT DATA SHEET - 10-C-2550 - RESIDUE GAS EXPANDER / RECOMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2018-12-07; 2019-01-29: 2019-01-02
[6 empty] | Revised Plan | 2018-12-27: 2018-08-29; 2019-01-29: 2018-09-03
[6 empty] | Issue Actual | 2018-12-27: 2018-08-29; 2019-01-29: 2018-09-03; 2019-01-29: 2018-09-28; 2019-03-13: 2018-10-01
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00031; 2019-01-29: TPSK-LSPA1-T-PE-00031; 2019-01-29: TPSK-LSPA1-T-PE-00114; 2019-03-13: TPSK-LSPA1-T-PE-00114
[6 empty] | Return Date | 2018-12-27: 2018-09-28; 2019-01-29: 2018-09-28; 2019-01-29: 2018-10-24; 2019-03-13: 2018-10-24
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2551 | PROCESS EQUIPMENT DATA SHEET - 10-D-2550 - EXPANDER SUCTION DRUM |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-24; 2019-01-29: 2018-12-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00218; 2018-12-27: TPSK-LSPA1-T-PE-00218; 2019-01-29: TPSK-LSPA1-T-PE-00440; 2019-01-29: TPSK-LSPA1-T-PE-00440
[6 empty] | Return Date | 2018-12-27: 2018-11-09; 2018-12-27: 2018-11-09; 2019-01-29: 2019-01-22; 2019-01-29: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2555 | PROCESS EQUIPMENT DATA SHEET - 10-D-2555 - EXPANDER DISCHARGE DRUM |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-24; 2019-01-29: 2018-12-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00218; 2018-12-27: TPSK-LSPA1-T-PE-00218; 2019-01-29: TPSK-LSPA1-T-PE-00430; 2019-01-29: TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-12-27: 2018-11-09; 2018-12-27: 2018-11-09; 2019-01-29: 2018-12-18; 2019-01-29: 2018-12-18
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2560 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2560 - PSA UNIT |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2018-10-17 | 2018-10-18 |  | 2018-12-20 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00190 | TPSK-LSPA1-T-PE-00190 | TPSK-LSPA1-T-PE-00530 | TPSK-LSPA1-T-PE-00530 | TPSK-LSPA1-T-PE-01485 | TPSK-LSPA1-T-PE-01485
[6 empty] | Return Date | 2018-11-05 | 2018-11-05 | 2019-01-14 | 2019-01-14 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | CL | CL
| PE | OL1-2G30-2570 | PROCESS EQUIPMENT DATA SHEET - 10-T-2570 - DEETHANIZER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | C | B | B | C
[6 empty] | Issue Plan | 2018-12-27: 2019-01-21; 2019-01-29: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-17; 2018-12-27: 2018-10-18; 2019-03-13: 2018-12-04; 2019-03-13: 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00191 | TPSK-LSPA1-T-PE-00191 | TPSK-LSPA1-T-PE-00538 | TPSK-LSPA1-T-PE-00407 | TPSK-LSPA1-T-PE-00407 | TPSK-LSPA1-T-PE-00538
[6 empty] | Return Date | 2018-11-05 | 2018-11-05 | 2019-01-14 | 2018-12-17 | 2018-12-17 | 2019-01-14
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2571 | PROCESS EQUIPMENT DATA SHEET - 10-E-2570 - DEETHANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11
[6 empty] | Issue Actual | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11; 2019-03-13: 2018-11-05
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00036; 2019-01-29: TPSK-LSPA1-T-PE-00036; 2019-01-29: TPSK-LSPA1-T-PE-00272; 2019-03-13: TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-12-27: 2018-10-02; 2019-01-29: 2018-10-02; 2019-01-29: 2018-11-26; 2019-03-13: 2018-11-26
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2572 | PROCESS EQUIPMENT DATA SHEET - 10-D-2570 - DEETHANIZER REFLUX DRUM |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-25; 2019-01-29: 2018-12-07
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00227; 2018-12-27: TPSK-LSPA1-T-PE-00227; 2019-01-29: TPSK-LSPA1-T-PE-00446; 2019-01-29: TPSK-LSPA1-T-PE-00446
[6 empty] | Return Date | 2018-12-27: 2018-12-05; 2018-12-27: 2018-12-05; 2019-01-29: 2018-12-27; 2019-01-29: 2018-12-27
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2573 | PROCESS EQUIPMENT DATA SHEET - 10-P-2570 - DEETHANIZER REFLUX PUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-01-29: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-20; 2019-01-29: 2018-12-13
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00340; 2018-12-27: TPSK-LSPA1-T-PE-00340; 2019-01-29: TPSK-LSPA1-T-PE-00481; 2019-01-29: TPSK-LSPA1-T-PE-00481
[6 empty] | Return Date | 2018-12-27: 2018-12-10; 2018-12-27: 2018-12-10; 2019-01-29: 2018-12-27; 2019-01-29: 2018-12-27
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2574 | PROCESS EQUIPMENT DATA SHEET - 10-D-2575 - DEETHANIZER REBOILER COND POT |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-12-11; 2019-01-29: 2018-12-27
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00474; 2018-12-27: TPSK-LSPA1-T-PE-00474; 2019-01-29: TPSK-LSPA1-T-PE-00563; 2019-01-29: TPSK-LSPA1-T-PE-00563
[6 empty] | Return Date | 2018-12-27: 2018-12-21; 2018-12-27: 2018-12-21; 2019-01-29: 2019-01-14; 2019-01-29: 2019-01-14
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2575 | PROCESS EQUIPMENT DATA SHEET - 10-E-2575 - DEETHANIZER REBOILER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-26; 2019-01-29: 2018-09-27
[6 empty] | Issue Actual | 2018-12-27: 2018-09-26; 2019-01-29: 2018-09-27; 2019-03-13: 2018-11-05
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00094; 2019-01-29: TPSK-LSPA1-T-PE-00094; 2019-01-29: TPSK-LSPA1-T-PE-00272; 2019-03-13: TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-12-27: 2018-10-12; 2019-01-29: 2018-10-12; 2019-01-29: 2018-11-26; 2019-03-13: 2018-11-26
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2576 | PROCESS EQUIPMENT DATA SHEET - 10-E-2576 - DEETHANIZER BOTTOMS COOLER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-26; 2019-01-29: 2018-09-27
[6 empty] | Issue Actual | 2018-12-27: 2018-09-26; 2019-01-29: 2018-09-27; 2019-03-13: 2018-11-05
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00094; 2019-01-29: TPSK-LSPA1-T-PE-00094; 2019-01-29: TPSK-LSPA1-T-PE-00272; 2019-03-13: TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-12-27: 2018-10-12; 2019-01-29: 2018-10-12; 2019-01-29: 2018-11-26; 2019-03-13: 2018-11-26
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2577 | PROCESS EQUIPMENT DATA SHEET - 10-P-2575 - DEETHANIZER REBOILER COND PUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-01-29: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-12-04; 2019-01-29: 2018-12-27
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00408; 2018-12-27: TPSK-LSPA1-T-PE-00408; 2019-01-29: TPSK-LSPA1-T-PE-00568; 2019-01-29: TPSK-LSPA1-T-PE-00568
[6 empty] | Return Date | 2018-12-27: 2018-12-17; 2018-12-27: 2018-12-17; 2019-01-29: 2019-01-14; 2019-01-29: 2019-01-14
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2580 | PROCESS EQUIPMENT DATA SHEET - 10-T-2580 - C2 TOWER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-01-21; 2019-01-29: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-12; 2018-12-27: 2018-10-15; 2019-01-29: 2018-12-04
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00162; 2018-12-27: TPSK-LSPA1-T-PE-00162; 2019-01-29: TPSK-LSPA1-T-PE-00407; 2019-01-29: TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-12-27: 2018-10-31; 2018-12-27: 2018-10-31; 2019-01-29: 2018-12-17; 2019-01-29: 2018-12-17
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2582 | PROCESS EQUIPMENT DATA SHEET - 10-E-2582 - C2 TOWER REFLUX COOLER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-01; 2019-01-29: 2018-12-13
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00265; 2018-12-27: TPSK-LSPA1-T-PE-00265; 2019-01-29: TPSK-LSPA1-T-PE-00492; 2019-01-29: TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-12-27: 2018-11-20; 2018-12-27: 2018-11-20; 2019-01-29: 2019-01-22; 2019-01-29: 2019-01-22
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2585 | PROCESS EQUIPMENT DATA SHEET - 10-E-2585 - C2 TOWER BOTTOMS REBOILER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-09-11 | 2018-10-04 | 2018-10-05 | 2019-04-04 | 2019-04-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-PE-01261 | TPSK-LSPA1-T-PE-01261
[6 empty] | Return Date | 2018-12-27: 2018-10-02; 2019-01-29: 2018-10-02; 2019-03-13: 2019-06-07; 2019-05-16: 2019-06-07
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29; 2019-03-13 to 2019-05-16
| PE | OL1-2G30-2586 | PROCESS EQUIPMENT DATA SHEET - 10-P-2586 - ETHANE RECYCLE PUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-01-29: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-20; 2019-01-29: 2018-12-13
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00340; 2018-12-27: TPSK-LSPA1-T-PE-00340; 2019-01-29: TPSK-LSPA1-T-PE-00481; 2019-01-29: TPSK-LSPA1-T-PE-00481
[6 empty] | Return Date | 2018-12-27: 2018-12-10; 2018-12-27: 2018-12-10; 2019-01-29: 2018-12-27; 2019-01-29: 2018-12-27
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2587 | PROCESS EQUIPMENT DATA SHEET - 10-E-2587 - C2 TOWER SIDE REBOILER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-10; 2019-01-29: 2018-09-11
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-09-11 | 2018-10-04 | 2018-10-05 | 2019-04-04 | 2019-04-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-PE-01261 | TPSK-LSPA1-T-PE-01261
[6 empty] | Return Date | 2018-12-27: 2018-10-02; 2019-01-29: 2018-10-02; 2019-03-13: 2019-06-07; 2019-05-16: 2019-06-07
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29; 2019-03-13 to 2019-05-16
| PE | OL1-2G30-2600 | PROCESS EQUIPMENT DATA SHEET - 10-D-2600 - C3 HYDROG GUARD ADSORBER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-12-07; 2019-01-29: 2019-01-10; 2019-03-13: 2019-03-13; 2019-03-13: 2019-03-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-00618 | TPSK-LSPA1-T-PE-00618 | TPSK-LSPA1-T-PE-01049 | TPSK-LSPA1-T-PE-01049
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-01-24 | 2019-01-24 | 2019-04-02 | 2019-04-02
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2610 | PROCESS EQUIPMENT DATA SHEET - 10-D-2610 - C3 HYDROG ARSINE GUARD BED |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-21; 2019-01-29: 2019-01-10
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00345; 2018-12-27: TPSK-LSPA1-T-PE-00345; 2019-01-29: TPSK-LSPA1-T-PE-00618; 2019-01-29: TPSK-LSPA1-T-PE-00618
[6 empty] | Return Date | 2018-12-27: 2018-12-13; 2018-12-27: 2018-12-13; 2019-01-29: 2019-01-24; 2019-01-29: 2019-01-24
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2620 | PROCESS EQUIPMENT DATA SHEET - 10-R-2620 - C3 HYDROG REACTOR |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-01-16; 2019-01-29: 2019-02-06
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-01-03; 2019-01-29: 2019-02-21; 2019-01-29: 2019-02-22
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00583; 2018-12-27: TPSK-LSPA1-T-PE-00583; 2019-01-29: TPSK-LSPA1-T-PE-00910; 2019-01-29: TPSK-LSPA1-T-PE-00910
[6 empty] | Return Date | 2018-12-27: 2019-01-16; 2018-12-27: 2019-01-16; 2019-01-29: 2019-03-19; 2019-01-29: 2019-03-19
[6 empty] | Owner Cmmt* | 2018-12-27: R2; 2018-12-27: R2; 2019-01-29: R2; 2019-01-29: 03
| PE | OL1-2G30-2621 | PROCESS EQUIPMENT DATA SHEET - 10-E-2620 - C3 HYDROG AFTERCOOLER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-10 | 2019-03-01 | 2019-03-04 | 2019-05-07 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00615 | TPSK-LSPA1-T-PE-00615 | TPSK-LSPA1-T-PE-00966 | TPSK-LSPA1-T-PE-00966 | TPSK-LSPA1-T-PE-01609 | TPSK-LSPA1-T-PE-01609
[6 empty] | Return Date | 2019-01-24 | 2019-01-24 | 2019-03-13 | 2019-03-13 | 2019-06-19 | 2019-06-19
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2622 | PROCESS EQUIPMENT DATA SHEET - 10-D-2620 - C3 HYDROG RECYCLE DRUM |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-01-10; 2019-01-29: 2019-03-11; 2019-01-29: 2019-03-12
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00614; 2018-12-27: TPSK-LSPA1-T-PE-00614; 2019-01-29: TPSK-LSPA1-T-PE-01023; 2019-01-29: TPSK-LSPA1-T-PE-01023
[6 empty] | Return Date | 2018-12-27: 2019-01-24; 2018-12-27: 2019-01-24; 2019-01-29: 2019-03-29; 2019-01-29: 2019-03-29
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2623 | PROCESS EQUIPMENT DATA SHEET - 10-P-2620 - C3 HYDROG RECYCLE PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-01-29: 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-03-01 | 2019-03-04 | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00587 | TPSK-LSPA1-T-PE-00587 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-01739 | TPSK-LSPA1-T-PE-01739
[6 empty] | Return Date | 2019-01-31 | 2019-01-31 | 2019-03-21 | 2019-03-21 | 2019-06-13 | 2019-06-13
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2624 | Process Equipment Datasheet - 10-X-2620 - C3 Hydrog Static Mixer |  | Class 2 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-01-16; 2019-01-29: 2019-03-01; 2019-01-29: 2019-03-04
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00664; 2018-12-27: TPSK-LSPA1-T-PE-00664; 2019-01-29: TPSK-LSPA1-T-PE-00968; 2019-01-29: TPSK-LSPA1-T-PE-00968
[6 empty] | Return Date | 2018-12-27: 2019-01-31; 2018-12-27: 2019-01-31; 2019-01-29: 2019-03-13; 2019-01-29: 2019-03-13
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2630 | PROCESS EQUIPMENT DATA SHEET - 10-T-2630 - SECONDARY DEETHANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | C | B | B | C
[6 empty] | Issue Plan | 2018-12-27: 2019-01-21; 2019-01-29: 2019-02-25
[6 empty] | Revised Plan | 2018-12-27: 2018-09-14; 2019-01-29: 2018-09-17
[6 empty] | Issue Actual |  | 2018-09-14 | 2018-09-17 |  | 2018-10-12 | 2018-10-15 | 2018-12-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00407 | TPSK-LSPA1-T-PE-00169 | TPSK-LSPA1-T-PE-00169 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-12-27: 2018-10-03; 2019-01-29: 2018-10-03; 2019-01-29: 2018-12-17; 2019-05-16: 2018-12-17
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29; 2019-05-16
| PE | OL1-2G30-2631 | PROCESS EQUIPMENT DATA SHEET - 10-E-2630 - SECONDARY DEETH CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-24; 2019-01-29: 2018-09-25
[6 empty] | Issue Actual | 2018-12-27: 2018-09-24; 2019-01-29: 2018-09-25; 2019-03-13: 2018-11-05
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00074; 2019-01-29: TPSK-LSPA1-T-PE-00074; 2019-01-29: TPSK-LSPA1-T-PE-00272; 2019-03-13: TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-12-27: 2018-10-12; 2019-01-29: 2018-10-12; 2019-01-29: 2018-11-26; 2019-03-13: 2018-11-26
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2632 | PROCESS EQUIPMENT DATA SHEET - 10-D-2630 - SECONDARY DEETH REFLUX DRUM |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-07; 2019-01-29: 2019-01-11
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00287; 2018-12-27: TPSK-LSPA1-T-PE-00287; 2019-01-29: TPSK-LSPA1-T-PE-00633; 2019-01-29: TPSK-LSPA1-T-PE-00633
[6 empty] | Return Date | 2018-12-27: 2019-01-11; 2018-12-27: 2019-01-11; 2019-01-29: 2019-01-24; 2019-01-29: 2019-01-24
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2633 | PROCESS EQUIPMENT DATA SHEET - 10-P-2630 - SECONDARY DEETH REFLUX PUMPS |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-01-29: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-06; 2019-01-29: 2019-02-12; 2019-01-29: 2019-02-12
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00277; 2018-12-27: TPSK-LSPA1-T-PE-00277; 2019-01-29: TPSK-LSPA1-T-PE-00844; 2019-01-29: TPSK-LSPA1-T-PE-00844
[6 empty] | Return Date | 2018-12-27: 2019-02-04; 2018-12-27: 2019-02-04; 2019-01-29: 2019-02-25; 2019-01-29: 2019-02-25
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2635 | PROCESS EQUIPMENT DATA SHEET - 10-E-2635 - SECONDARY DEETH REBOILER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | C | B | B | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-24; 2019-01-29: 2018-09-25
[6 empty] | Issue Actual | 2018-12-27: 2018-09-24; 2019-01-29: 2018-09-25; 2019-03-13: 2018-11-05; 2019-05-16: 2018-12-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00074 | TPSK-LSPA1-T-PE-00074 | TPSK-LSPA1-T-PE-00438 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00438
[6 empty] | Return Date |  | 2018-10-12 | 2018-10-12 | 2018-12-27 | 2018-11-26 | 2018-11-26 | 2018-12-27
Owner Cmmt* | bar: 2018-12-27 to 2019-05-16
| PE | OL1-2G30-2636 | PROCESS EQUIPMENT DATA SHEET - 10-E-2636 - SECONDARY DEETH BOTTOMS COOLER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-24; 2019-01-29: 2018-09-25
[6 empty] | Issue Actual | 2018-12-27: 2018-09-24; 2019-01-29: 2018-09-25; 2019-03-13: 2018-11-05
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00074; 2019-01-29: TPSK-LSPA1-T-PE-00074; 2019-01-29: TPSK-LSPA1-T-PE-00272; 2019-03-13: TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-12-27: 2018-10-12; 2019-01-29: 2018-10-12; 2019-01-29: 2018-11-26; 2019-03-13: 2018-11-26
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2640 | PROCESS EQUIPMENT DATA SHEET - 10-T-2640 - C3 TOWER |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-01-21; 2019-01-29: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-10-22; 2019-01-29: 2018-12-04
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00201; 2018-12-27: TPSK-LSPA1-T-PE-00201; 2019-01-29: TPSK-LSPA1-T-PE-00407; 2019-01-29: TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-12-27: 2018-11-05; 2018-12-27: 2018-11-05; 2019-01-29: 2018-12-17; 2019-01-29: 2018-12-17
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2644 | PROCESS EQUIPMENT DATA SHEET - 10-D-2645 - C3 TOWER REBOILER COND POT |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-18 | 2019-02-01 | 2019-02-04 | 2019-02-26 | 2019-02-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00677 | TPSK-LSPA1-T-PE-00677 | TPSK-LSPA1-T-PE-00796 | TPSK-LSPA1-T-PE-00796 | TPSK-LSPA1-T-PE-00938 | TPSK-LSPA1-T-PE-00938
[6 empty] | Return Date | 2019-01-31 | 2019-01-31 | 2019-02-21 | 2019-02-21 | 2019-03-14 | 2019-03-14
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2645 | PROCESS EQUIPMENT DATA SHEET - 10-E-2645 - C3 TOWER REBOILER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | C | B | B | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-12; 2019-01-29: 2018-09-12
[6 empty] | Issue Actual | 2018-12-27: 2018-09-12; 2019-01-29: 2018-09-12; 2019-03-13: 2018-11-05; 2019-05-16: 2018-12-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00041 | TPSK-LSPA1-T-PE-00041 | TPSK-LSPA1-T-PE-00438 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00438
[6 empty] | Return Date |  | 2018-10-01 | 2018-10-01 | 2018-11-27 | 2018-11-26 | 2018-11-26 | 2018-11-27
Owner Cmmt* | bar: 2018-12-27 to 2019-05-16
| PE | OL1-2G30-2646 | PROCESS EQUIPMENT DATA SHEET - 10-P-2646 - PROPANE RECYCLE PUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-01-29: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-06; 2019-01-29: 2019-02-12; 2019-01-29: 2019-02-12
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00277; 2018-12-27: TPSK-LSPA1-T-PE-00277; 2019-01-29: TPSK-LSPA1-T-PE-00844; 2019-01-29: TPSK-LSPA1-T-PE-00844
[6 empty] | Return Date | 2018-12-27: 2019-02-04; 2018-12-27: 2019-02-04; 2019-01-29: 2019-02-25; 2019-01-29: 2019-02-25
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2647 | PROCESS EQUIPMENT DATA SHEET - 10-P-2647 - HP PROPYLENE / OFF SPEC PUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-01-29: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-09; 2019-01-29: 2019-01-14
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00302; 2018-12-27: TPSK-LSPA1-T-PE-00302; 2019-01-29: TPSK-LSPA1-T-PE-00649; 2019-01-29: TPSK-LSPA1-T-PE-00649
[6 empty] | Return Date | 2018-12-27: 2019-02-04; 2018-12-27: 2019-02-04; 2019-01-29: 2019-01-28; 2019-01-29: 2019-01-28
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2660 | PROCESS EQUIPMENT DATA SHEET - 10-T-2660 - DEBUTANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-01-21; 2019-01-29: 2019-02-25
[6 empty] | Revised Plan | 2018-12-27: 2018-09-14; 2019-01-29: 2018-09-17
[6 empty] | Issue Actual | 2018-12-27: 2018-09-14; 2019-01-29: 2018-09-17; 2019-01-29: 2018-10-12; 2019-03-13: 2018-10-15
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00053; 2019-01-29: TPSK-LSPA1-T-PE-00053; 2019-01-29: TPSK-LSPA1-T-PE-00169; 2019-03-13: TPSK-LSPA1-T-PE-00169
[6 empty] | Return Date | 2018-12-27: 2018-10-03; 2019-01-29: 2018-10-03
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2661 | PROCESS EQUIPMENT DATA SHEET - 10-E-2660 - DEBUTANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
Rev. | bar: 2018-12-27 to 2019-03-13
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-18
[6 empty] | Revised Plan | 2018-12-27: 2018-09-26; 2019-01-29: 2018-09-27
[6 empty] | Issue Actual | 2018-12-27: 2018-09-26; 2019-01-29: 2018-09-27; 2019-03-13: 2018-11-05
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00094; 2019-01-29: TPSK-LSPA1-T-PE-00094; 2019-01-29: TPSK-LSPA1-T-PE-00272; 2019-03-13: TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-12-27: 2018-10-12; 2019-01-29: 2018-10-12; 2019-01-29: 2018-11-26; 2019-03-13: 2018-11-26
Owner Cmmt* | bar: 2018-12-27 to 2019-03-13
| PE | OL1-2G30-2662 | PROCESS EQUIPMENT DATA SHEET - 10-D-2660 - DEBUTANIZER REFLUX DRUM |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-01-29: IFD; 2019-01-29: IFD
Rev. | bar: 2018-12-27 to 2019-01-29
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-01-29: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-11-07; 2019-01-29: 2019-01-16
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00287; 2018-12-27: TPSK-LSPA1-T-PE-00287; 2019-01-29: TPSK-LSPA1-T-PE-00660; 2019-01-29: TPSK-LSPA1-T-PE-00660
[6 empty] | Return Date | 2018-12-27: 2019-01-11; 2018-12-27: 2019-01-11; 2019-01-29: 2019-01-29; 2019-01-29: 2019-01-29
Owner Cmmt* | bar: 2018-12-27 to 2019-01-29
| PE | OL1-2G30-2663 | PROCESS EQUIPMENT DATA SHEET - 10-P-2660 - DEBUTANIZER REFLUX / PRODUCT PUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | C | B | C | D | D
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-20 |  |  | 2018-12-13 | 2019-01-14 | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00481 | TPSK-LSPA1-T-PE-00648 | TPSK-LSPA1-T-PE-00481 | TPSK-LSPA1-T-PE-00648 | TPSK-LSPA1-T-PE-01383 | TPSK-LSPA1-T-PE-01383
[6 empty] | Return Date | 2018-12-10 | 2018-12-10 | 2018-12-27 | 2019-01-28 | 2018-12-27 | 2019-01-28 | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2664 | Process Equipment Datasheet - 10-F-2666 A-B - C5 - Pygas Feed Filters |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2019-02-20 | 2019-02-20 | 2019-03-11 | 2019-03-12 | 2019-05-07 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-0900 | TPSK-LSPA1-T-PE-0900 | TPSK-LSPA1-T-PE-01024 | TPSK-LSPA1-T-PE-01024 | TPSK-LSPA1-T-PE-01601 | TPSK-LSPA1-T-PE-01601
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-03-29 | 2019-03-29 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R2 | R2 | R2
| PE | OL1-2G30-2665 | PROCESS EQUIPMENT DATA SHEET - 10-E-2665 - DEBUTANIZER REBOILER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-27 | 2018-09-28
[6 empty] | Issue Actual |  | 2018-09-27 | 2018-09-28 |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00101 | TPSK-LSPA1-T-PE-00101 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-10-12 | 2018-11-26 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A1 | A1 | A1
| PE | OL1-2G30-2666 | PROCESS EQUIPMENT DATA SHEET - 10-E-2666 - DEBUTANIZER BOTTOMS COOLER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | C | B | B | C | D | D
[6 empty] | Issue Plan | 2019-02-18 | C: 2019-03-18
[6 empty] | Revised Plan |  | A: 2018-09-28; A: 2018-09-28
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-09-28 |  |  | 2018-11-27 | 2019-01-23 | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00112 | TPSK-LSPA1-T-PE-00112 | TPSK-LSPA1-T-PE-00711 | TPSK-LSPA1-T-PE-00370 | TPSK-LSPA1-T-PE-00370 | TPSK-LSPA1-T-PE-00711 | TPSK-LSPA1-T-PE-01387 | TPSK-LSPA1-T-PE-01387
[6 empty] | Return Date |  | 2018-10-12 | 2018-10-12 | 2019-02-11 | 2018-12-10 | 2018-12-10 | 2019-02-11 | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | A2 | A1 | A1 | A2 | R1 | R1
| PE | OL1-2G30-2667 | PROCESS EQUIPMENT DATA SHEET - 10-D-2666 - C5 / PYGAS SURGE DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 | A: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-02-01 | 2019-03-20 | 2019-03-21 | 2019-05-07 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01106 | TPSK-LSPA1-T-PE-01106 | TPSK-LSPA1-T-PE-01600 | TPSK-LSPA1-T-PE-01600
[6 empty] | Return Date | 2019-02-21 | 2019-02-21 | 2019-04-10 | 2019-04-10 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | bar: A to B
| PE | OL1-2G30-2668 | PROCESS EQUIPMENT DATA SHEET - 10-P-2666 - C5 / PYGAS PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | D | B | B | C | C | D
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-11 | 2019-02-11 |  | 2019-03-11 | 2019-03-12 | 2019-04-12 | 2019-04-15 | 2019-05-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00834 | TPSK-LSPA1-T-PE-00834 | TPSK-LSPA1-T-PE-01739 | TPSK-LSPA1-T-PE-01025 | TPSK-LSPA1-T-PE-01025 | TPSK-LSPA1-T-PE-01339 | TPSK-LSPA1-T-PE-01339 | TPSK-LSPA1-T-PE-01739
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-13 | 2019-03-29 | 2019-03-29 |  |  | 2019-06-13
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 |  |  | R1
| PE | OL1-2G30-2669 | Process Equipment Datasheet - 10-P-2665 A-B - Debutanizer Bottoms Pumps |  | Class 2 | Purpose** | IFD | IFR | IFR | IFD | CAN | CAN
[6 empty] | Rev. | B | A | A | B | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  |  | 2018-11-27 | 2019-01-14 | 2019-03-19 | 2019-03-20
[6 empty] | Issue Actual |  |  | 2018-11-27 | 2019-01-14 | 2019-03-19 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00648 | TPSK-LSPA1-T-PE-00371 | TPSK-LSPA1-T-PE-00371 | TPSK-LSPA1-T-PE-00648 | TPSK-LSPA1-T-PE-01099 | TPSK-LSPA1-T-PE-01099
[6 empty] | Return Date | 2019-01-28 | 2018-12-13 | 2018-12-13 | 2019-01-28 | 2019-04-10 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R2 | R2 | R1 | R1 | R1
| PE | OL1-2G30-2700 | PROCESS EQUIPMENT DATA SHEET - 10-R-2700 - GHU-1 REACTOR |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; D: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-01-16 |  | 2019-02-06
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-03-15 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00659 | TPSK-LSPA1-T-PE-00659 | TPSK-LSPA1-T-PE-01081 | TPSK-LSPA1-T-PE-01081
[6 empty] | Return Date | 2019-02-11 | 2019-02-11 | 2019-04-02 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2701 | PROCESS EQUIPMENT DATA SHEET - 10-E-2701 - GHU-1 FEED / EFFLUENT EXCHANGERS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-03-20 | 2019-03-21 | 2019-05-07 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00710 | TPSK-LSPA1-T-PE-00710 | TPSK-LSPA1-T-PE-01107 | TPSK-LSPA1-T-PE-01107 | TPSK-LSPA1-T-PE-01604 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-11 | 2019-02-11 | 2019-04-10 | 2019-04-10 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2702 | PROCESS EQUIPMENT DATA SHEET - 10-E-2702 - GHU-1 S/U HEATER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-20 | 2019-02-20 | 2019-04-04 | 2019-04-05 | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00899 | TPSK-LSPA1-T-PE-00899 | TPSK-LSPA1-T-PE-01250 | TPSK-LSPA1-T-PE-01250 | TPSK-LSPA1-T-PE-01371 | TPSK-LSPA1-T-PE-01371
[6 empty] | Return Date | 2019-03-19 | 2019-03-19 | 2019-05-16 | 2019-05-16 | 2019-06-07 | 2019-06-07
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2703 | PROCESS EQUIPMENT DATA SHEET - 10-E-2705 - GHU-1 RECYCLE COOLER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-03-28 | 2019-03-29 | 2019-05-07 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-01187 | TPSK-LSPA1-T-PE-01187 | TPSK-LSPA1-T-PE-01604 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-07 | 2019-06-07 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2704 | PROCESS EQUIPMENT DATA SHEET - 10-P-2705 - GHU-1 RECYCLE PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-11 | 2019-02-11 | 2019-03-11 | 2019-03-12 | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00834 | TPSK-LSPA1-T-PE-00834 | TPSK-LSPA1-T-PE-01025 | TPSK-LSPA1-T-PE-01025 | TPSK-LSPA1-T-PE-01739 | TPSK-LSPA1-T-PE-01739
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-03-29 | 2019-03-29 | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2705 | PROCESS EQUIPMENT DATA SHEET - 10-D-2705 - GHU-1 HOT SEPARATOR |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; D: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-02-01 | 2019-03-28 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01188 | TPSK-LSPA1-T-PE-01188
[6 empty] | Return Date | 2019-02-21 | 2019-02-21 | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2706 | PROCESS EQUIPMENT DATA SHEET - 10-D-2706 - GHU-1 COLD SEPARATOR |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; D: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-02-01 | 2019-03-28 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01188 | TPSK-LSPA1-T-PE-01188
[6 empty] | Return Date | 2019-02-21 | 2019-02-21 | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2707 | PROCESS EQUIPMENT DATA SHEET - 10-E-2706 - GHU-1 COOLER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-03-28 | 2019-03-29 | 2019-05-07 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-01187 | TPSK-LSPA1-T-PE-01187 | TPSK-LSPA1-T-PE-01604 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-05-16 | 2019-05-16 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2710 | PROCESS EQUIPMENT DATA SHEET - 10-T-2710 - DEPENTANIZER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-22 | 2019-03-15 | 2019-03-18 | 2019-05-21 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00688 | TPSK-LSPA1-T-PE-00688 | TPSK-LSPA1-T-PE-01082 | TPSK-LSPA1-T-PE-01082 | TPSK-LSPA1-T-PE-01708 | TPSK-LSPA1-T-PE-01708
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-04-02 | 2019-04-02 |  | 2019-06-12
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 |  | CL
| PE | OL1-2G30-2711 | PROCESS EQUIPMENT DATA SHEET - 10-E-2710 -DEPENTANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-03-20 | 2019-03-21 | 2019-05-07 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-01107 | TPSK-LSPA1-T-PE-01107 | TPSK-LSPA1-T-PE-01604 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-04-10 | 2019-04-10 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2712 | PROCESS EQUIPMENT DATA SHEET - 10-D-2710 - DEPENTANIZER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-02-01 | 2019-03-20 | 2019-03-21 | 2019-05-07 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01106 | TPSK-LSPA1-T-PE-01106 | TPSK-LSPA1-T-PE-01600 | TPSK-LSPA1-T-PE-01600
[6 empty] | Return Date | 2019-02-21 | 2019-02-21 | 2019-04-10 | 2019-04-10 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2713 | PROCESS EQUIPMENT DATA SHEET - 10-P-2710 - DEPENTANIZER REFLUX PUMPS |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; D: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-11 | 2019-02-11 | 2019-03-11 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00834 | TPSK-LSPA1-T-PE-00834 | TPSK-LSPA1-T-PE-01025 | TPSK-LSPA1-T-PE-01025
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-03-29 | 2019-03-29
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2714 | PROCESS EQUIPMENT DATA SHEET - 10-P-2714 - C5 CUT PUMPS |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; D: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-12 | 2019-02-12 | 2019-03-15 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00841 | TPSK-LSPA1-T-PE-00841 | TPSK-LSPA1-T-PE-01083 | TPSK-LSPA1-T-PE-01083
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-04-02 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2715 | PROCESS EQUIPMENT DATA SHEET - 10-E-2715 - DEPENTANIZER REBOILER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-03-20 | 2019-03-21 | 2019-04-26 | 2019-04-29 | 2019-05-07 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00724 | TPSK-LSPA1-T-PE-00724 | TPSK-LSPA1-T-PE-01107 | TPSK-LSPA1-T-PE-01107 | TPSK-LSPA1-T-PE-01507 | TPSK-LSPA1-T-PE-01507 | TPSK-LSPA1-T-PE-01604 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-11 | 2019-02-11 | 2019-04-10 | 2019-04-10 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2716 | PROCESS EQUIPMENT DATA SHEET - 10-E-2714 - C5 CUT COOLER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-03-28 | 2019-03-29 | 2019-06-26 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-01187 | TPSK-LSPA1-T-PE-01187 | TPSK-LSPA1-T-PE-01990 | TPSK-LSPA1-T-PE-01990
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-05-16 | 2019-05-16 | 2019-07-17 | 2019-07-17
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2717 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2720 - RERUN TOWER EDUCTOR PKG |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2019-02-20 | 2019-02-20 | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00902 | TPSK-LSPA1-T-PE-00902 | TPSK-LSPA1-T-PE-01403 | TPSK-LSPA1-T-PE-01403
[6 empty] | Return Date | 2019-03-19 | 2019-03-19 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2718 | PROCESS EQUIPMENT DATA SHEET - 10-D-2720 - RERUN TOWER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-02-01 | 2019-04-12 | 2019-04-15 | 2019-07-03 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01342 | TPSK-LSPA1-T-PE-01342 | TPSK-LSPA1-T-PE-02056 | TPSK-LSPA1-T-PE-02056
[6 empty] | Return Date | 2019-02-21 | 2019-02-21 |  |  |  | 2019-08-05
[6 empty] | Owner Cmmt* | R2 | R2 |  |  |  | R1
| PE | OL1-2G30-2719 | PROCESS EQUIPMENT DATA SHEET - 10-P-2720 - RERUN TOWER REFLUX / PRODUCT PUMPS |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-12 | 2019-02-12 | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00841 | TPSK-LSPA1-T-PE-00841 | TPSK-LSPA1-T-PE-01404 | TPSK-LSPA1-T-PE-01404
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2720 | PROCESS EQUIPMENT DATA SHEET - 10-T-2720 - RERUN TOWER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-22 | 2019-04-12 | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00669 | TPSK-LSPA1-T-PE-00669 | TPSK-LSPA1-T-PE-01340 | TPSK-LSPA1-T-PE-01340
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-08-20
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G30-2721 | PROCESS EQUIPMENT DATA SHEET - 10-E-2720 - RERUN TOWER CONDENSER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-11 | 2019-02-11 | 2019-04-12 | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-01341 | TPSK-LSPA1-T-PE-01341
[6 empty] | Return Date | 2019-02-25 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2723 | PROCESS EQUIPMENT DATA SHEET - 10-E-2724 - WASH OIL CONDENSER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-11 | 2019-02-11 | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-01353 | TPSK-LSPA1-T-PE-01353
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2724 | PROCESS EQUIPMENT DATA SHEET - 10-D-2724 - WASH OIL DEGASSING DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-02-01 | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01354 | TPSK-LSPA1-T-PE-01354
[6 empty] | Return Date | 2019-02-21 | 2019-02-21 | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2725 | PROCESS EQUIPMENT DATA SHEET - 10-E-2725 - RERUN TOWER REBOILER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-11 | 2019-02-11 | 2019-04-17 | 2019-04-18 | 2019-05-07 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-01405 | TPSK-LSPA1-T-PE-01405 | TPSK-LSPA1-T-PE-01604 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2726 | PROCESS EQUIPMENT DATA SHEET - 10-P-2726 - PYGAS FUEL OIL PUMPS |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00873 | TPSK-LSPA1-T-PE-00873 | TPSK-LSPA1-T-PE-01432 | TPSK-LSPA1-T-PE-01432
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | Re
| PE | OL1-2G30-2727 | PROCESS EQUIPMENT DATA SHEET - 10-E-2726 - PYGAS FUEL OIL COOLER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-11 | 2019-02-11 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-01431 | TPSK-LSPA1-T-PE-01431
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2728 | PROCESS EQUIPMENT DATA SHEET - 10-P-2724 - RECYCLE WASH OIL PUMPS |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-12 | 2019-02-12 | 2019-04-23 | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00841 | TPSK-LSPA1-T-PE-00841 | TPSK-LSPA1-T-PE-01458 | TPSK-LSPA1-T-PE-01458
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2729 | Process Equipment Datasheet - 10-P-2721 A-B - Wash Oil Pumps |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-23 | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00873 | TPSK-LSPA1-T-PE-00873 | TPSK-LSPA1-T-PE-01458 | TPSK-LSPA1-T-PE-01458
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2730 | PROCESS EQUIPMENT DATA SHEET - 10-E-2730 - HYDROG REGEN HEATER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-03-15 | 2019-03-18 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01070 | TPSK-LSPA1-T-PE-01070 | TPSK-LSPA1-T-PE-01586 | TPSK-LSPA1-T-PE-01586
[6 empty] | Return Date | 2019-04-02 | 2019-04-02 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2735 | PROCESS EQUIPMENT DATA SHEET - 10-D-2735 - REGEN HYDROG DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-03-13 | 2019-03-14 | 2019-04-08 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01049 | TPSK-LSPA1-T-PE-01049 | TPSK-LSPA1-T-PE-01277 | TPSK-LSPA1-T-PE-01277
[6 empty] | Return Date | 2019-04-02 | 2019-04-02 | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2750 | PROCESS EQUIPMENT DATA SHEET - 10-D-2750 - C4 / C5 HYDROG SURGE DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-02-04 | 2019-03-11 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00794 | TPSK-LSPA1-T-PE-00794 | TPSK-LSPA1-T-PE-01023 | TPSK-LSPA1-T-PE-01023
[6 empty] | Return Date | 2019-02-21 | 2019-02-21 | 2019-03-29 | 2019-03-29
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2751 | PROCESS EQUIPMENT DATA SHEET - 10-P-2750 - C4 / C5 HYDROG FEED PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-02-04 | 2019-03-01 | 2019-03-04 | 2019-05-07 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00788 | TPSK-LSPA1-T-PE-00788 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-01610 | TPSK-LSPA1-T-PE-01610
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-03-21 | 2019-03-21 | 2019-06-19 | 2019-06-19
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R2 | R1 | R1
| PE | OL1-2G30-2755 | PROCESS EQUIPMENT DATA SHEET - 10-E-2755 - C4 / C5 HYDROG S/U HEATER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-25 | 2019-02-26 | 2019-03-25 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00924 | TPSK-LSPA1-T-PE-00924 | TPSK-LSPA1-T-PE-01148 | TPSK-LSPA1-T-PE-01148
[6 empty] | Return Date | 2019-03-19 | 2019-03-19 | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2760 | PROCESS EQUIPMENT DATA SHEET - 10-R-2760 - C4 / C5 HYDROG REACTOR |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-01-16 |  | 2019-02-06
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-03-11 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00659 | TPSK-LSPA1-T-PE-00659 | TPSK-LSPA1-T-PE-01030 | TPSK-LSPA1-T-PE-01030
[6 empty] | Return Date | 2019-02-11 | 2019-02-11 | 2019-03-29 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2762 | PROCESS EQUIPMENT DATA SHEET - 10-D-2760 - C4 / C5 HYDROG RECYCLE DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-02-04 | 2019-03-11 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00794 | TPSK-LSPA1-T-PE-00794 | TPSK-LSPA1-T-PE-01023 | TPSK-LSPA1-T-PE-01023
[6 empty] | Return Date | 2019-02-21 | 2019-02-21 | 2019-03-29 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2763 | PROCESS EQUIPMENT DATA SHEET - 10-E-2760 - C4 / C5 HYDROG VENT CONDENSER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-02-04 | 2019-03-11 | 2019-03-12 | 2019-05-07 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00793 | TPSK-LSPA1-T-PE-00793 | TPSK-LSPA1-T-PE-01027 | TPSK-LSPA1-T-PE-01027 | TPSK-LSPA1-T-PE-01604 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-21 | 2019-02-21 | 2019-03-29 | 2019-03-29 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2764 | PROCESS EQUIPMENT DATA SHEET - 10-P-2760 - C4 / C5 HYDROG RECYCLE PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-02-04 | 2019-03-01 | 2019-03-04 | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00788 | TPSK-LSPA1-T-PE-00788 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-01739 | TPSK-LSPA1-T-PE-01739
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-03-21 | 2019-03-21 | 2019-06-13 | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2765 | PROCESS EQUIPMENT DATA SHEET - 10-E-2765 - C4 / C5 HYDROG RECYCLE COOLER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-01 | 2019-02-04 | 2019-03-11 | 2019-03-12 | 2019-05-07 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00793 | TPSK-LSPA1-T-PE-00793 | TPSK-LSPA1-T-PE-01027 | TPSK-LSPA1-T-PE-01027 | TPSK-LSPA1-T-PE-01604 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-21 | 2019-02-21 | 2019-03-29 | 2019-03-29 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2767 | Process Equipment Datasheet - 10-D-2765 - C4 - C5 Hydrog Coalescer Drum |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-02-20 | 2019-02-20 | 2019-03-25 | 2019-03-26 | 2019-05-07 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE--00901 | TPSK-LSPA1-T-PE--00901 | TPSK-LSPA1-T-PE-01145 | TPSK-LSPA1-T-PE-01145 | TPSK-LSPA1-T-PE-01600 | TPSK-LSPA1-T-PE-01600
[6 empty] | Return Date | 2019-03-19 | 2019-03-19 | 2019-05-16 | 2019-05-16 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R2 | R2
| PE | OL1-2G30-2790 | PROCESS EQUIPMENT DATA SHEET - 10-D-2790 - LIGHT OIL DRAIN DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-13 |  | 2019-01-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00482 | TPSK-LSPA1-T-PE-00482 | TPSK-LSPA1-T-PE-00721 | TPSK-LSPA1-T-PE-00721
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-02-11 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2791 | PROCESS EQUIPMENT DATA SHEET - 10-P-2790 - LIGHT OIL DRAIN DRUM PUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-13 |  | 2019-01-25 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00496 | TPSK-LSPA1-T-PE-00496 | TPSK-LSPA1-T-PE-00722 | TPSK-LSPA1-T-PE-00722 | TPSK-LSPA1-T-PE-01434 | TPSK-LSPA1-T-PE-01434
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-02-11 | 2019-02-11 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R2 | R2
| PE | OL1-2G30-2792 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2790 - LIGHT OIL DRAIN SUMP EDUCTOR |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFD; B: IFD
[6 empty] | Rev. |  | A | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
Revised Plan
[6 empty] | Issue Actual |  |  | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00595 | TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date |  | 2019-01-22 | 2019-01-22
[6 empty] | Owner Cmmt* |  | R1 | R1
| PE | OL1-2G30-2795 | Data Sheet For Vacuum Units -Multistage Ejectors- Rerun Tower Vacuum Package PK-2720 |  | Class 2 | Rev.: Purpose**; A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02333
Return Date
Owner Cmmt*
| PE | OL1-2G30-2800 | PROCESS EQUIPMENT DATA SHEET - 10-C-2800 - PROPYLENE REFRIG COMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2018-12-07 |  |  | 2019-01-02
[6 empty] | Revised Plan |  | 2018-08-22 | 2018-08-23
[6 empty] | Issue Actual |  | 2018-08-22 | 2018-08-23 | 2018-09-17 | 2018-09-18
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00055 | TPSK-LSPA1-T-PE-00055
[6 empty] | Return Date |  | 2018-09-11 | 2018-09-11
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G30-2801 | PROCESS EQUIPMENT DATA SHEET - 10-P-2805 - PROPYLENE PRODUCT PUMP |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-06 |  | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00277 | TPSK-LSPA1-T-PE-00277 | TPSK-LSPA1-T-PE-00649 | TPSK-LSPA1-T-PE-00649
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-01-28 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2805 | PROCESS EQUIPMENT DATA SHEET - 10-D-2805 - C3R SURGE DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-24 |  | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00348 | TPSK-LSPA1-T-PE-00348
[6 empty] | Return Date | 2018-11-09 | 2018-11-09 | 2018-12-10 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2806 | PROCESS EQUIPMENT DATA SHEET - 10-E-2805 - C3R CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-28 | 2018-10-01
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-10-01 |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-10-12 | 2018-11-26 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A3 | A3 | A1 | A1
| PE | OL1-2G30-2807 | PROCESS EQUIPMENT DATA SHEET - 10-E-2807 - C3 CHILLER NO. 1 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-28 | 2018-10-01
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-10-01 |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-10-12 | 2018-11-26 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A1 | A2 | A2
| PE | OL1-2G30-2809 | PROCESS EQUIPMENT DATA SHEET - 10-E-2809 - C3 CHILLER NO. 2 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-28 | 2018-10-01
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-10-01 |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00273 | TPSK-LSPA1-T-PE-00273
[6 empty] | Return Date |  | 2018-10-12 | 2018-10-12 | 2018-11-26 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A1 | A1 | A1
| PE | OL1-2G30-2810 | PROCESS EQUIPMENT DATA SHEET - 10-D-2810 - C3R 1ST STAGE SUCTION DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-09 |  | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-11-05 | 2018-12-10 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2815 | PROCESS EQUIPMENT DATA SHEET - 10-D-2815 - C3R DRAIN DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-07 |  | 2019-01-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-00633 | TPSK-LSPA1-T-PE-00633
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-01-24 | 2019-01-24
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2816 | PROCESS EQUIPMENT DATA SHEET - 10-P-2815 - PROPYLENE REFRIG RECOVERY PUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | C | B | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-20 |  |  | 2018-12-13 | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00481 | TPSK-LSPA1-T-PE-00648 | TPSK-LSPA1-T-PE-00481 | TPSK-LSPA1-T-PE-00648
[6 empty] | Return Date | 2018-12-10 | 2018-12-10 | 2018-12-27 | 2019-01-28 | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2820 | PROCESS EQUIPMENT DATA SHEET - 10-D-2820 - C3R 2ND STAGE SUCTION DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-09 |  | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-11-05 | 2018-12-10 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2830 | PROCESS EQUIPMENT DATA SHEET - 10-D-2830 - C3R 3RD STAGE SUCTION DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-09 |  | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-11-05 | 2018-12-10 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2840 | PROCESS EQUIPMENT DATA SHEET - 10-D-2840 - C3R 4TH STAGE SUCTION DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-09 |  | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-11-05 | 2018-12-10 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2850 | PROCESS EQUIPMENT DATA SHEET - 10-C-2850 - ETHYLENE REFRIG COMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2018-12-07 |  |  | 2019-01-02
[6 empty] | Revised Plan |  | 2018-08-22 | 2018-08-23
[6 empty] | Issue Actual |  | 2018-08-22 | 2018-08-23 | 2018-09-17 | 2018-09-18
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00055 | TPSK-LSPA1-T-PE-00055
[6 empty] | Return Date |  | 2018-09-11 | 2018-09-11
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G30-2852 | PROCESS EQUIPMENT DATA SHEET - 10-E-2852 - C2R DESUPERHEATER NO. 1 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-28 | 2018-10-01
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-10-01 |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-10-12 | 2018-11-26 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A1 | A2 | A2
| PE | OL1-2G30-2853 | PROCESS EQUIPMENT DATA SHEET - 10-E-2852 - C2R DESUPERHEATER NO. 2 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-28 | 2018-10-01
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-10-01 |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-10-12 | 2018-11-26 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A1 | A2 | A2
| PE | OL1-2G30-2854 | PROCESS EQUIPMENT DATA SHEET - 10-D-2855 - C2R SURGE DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-24 |  | 2019-01-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00621 | TPSK-LSPA1-T-PE-00621
[6 empty] | Return Date | 2018-11-09 | 2018-11-09 | 2019-01-24 | 2019-01-24
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2855 | PROCESS EQUIPMENT DATA SHEET - 10-P-2855 - ETHYLENE PRODUCT PUMP |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-28 |  | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00379 | TPSK-LSPA1-T-PE-00379 | TPSK-LSPA1-T-PE-00648 | TPSK-LSPA1-T-PE-00648
[6 empty] | Return Date | 2018-12-13 | 2018-12-13 | 2019-01-28 | 2019-01-28
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2856 | PROCESS EQUIPMENT DATA SHEET - 10-E-2855 - C2R CONDENSER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-11 | 2018-09-12
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-09-12 |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00039 | TPSK-LSPA1-T-PE-00039 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-09-28 | 2018-09-28 | 2018-11-26 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A2 | A2 | A1 | A1
| PE | OL1-2G30-2857 | PROCESS EQUIPMENT DATA SHEET - 10-E-2857 - HP ETHYLENE PRODUCT VAPORIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-12 | 2018-09-12
[6 empty] | Issue Actual |  | 2018-09-12 | 2018-09-12 |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00041 | TPSK-LSPA1-T-PE-00041 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-01 | 2018-10-01 | 2018-11-26 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A1 | A1 | A1
| PE | OL1-2G30-2858 | PROCESS EQUIPMENT DATA SHEET - 10-E-2858 - HP ETHYLENE PRODUCT SUPERHEATER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-24 |  | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00223 | TPSK-LSPA1-T-PE-00223 | TPSK-LSPA1-T-PE-00492 | TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-11-14 | 2018-11-14 | 2019-01-22 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2859 | Process Equipment Datasheet - 10-E-2856 - Ethylene Product Subcooler |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | C | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-24 |  |  | 2018-12-13 | 2019-01-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216 | TPSK-LSPA1-T-PE-00216 | TPSK-LSPA1-T-PE-00492 | TPSK-LSPA1-T-PE-00711 | TPSK-LSPA1-T-PE-00492 | TPSK-LSPA1-T-PE-00711
[6 empty] | Return Date | 2018-11-14 | 2018-11-14 | 2019-01-22 | 2019-02-11 | 2019-01-22 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1
| PE | OL1-2G30-2860 | PROCESS EQUIPMENT DATA SHEET - 10-D-2860 - C2R 1ST STAGE SUCTION DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-23 | 2019-02-12 | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00208 | TPSK-LSPA1-T-PE-00208 | TPSK-LSPA1-T-PE-00845 | TPSK-LSPA1-T-PE-00845
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-02-25 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2865 | PROCESS EQUIPMENT DATA SHEET - 10-D-2865 - C2R DRAIN DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-07 |  | 2019-01-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00445 | TPSK-LSPA1-T-PE-00445 | TPSK-LSPA1-T-PE-00633 | TPSK-LSPA1-T-PE-00633
[6 empty] | Return Date | 2019-01-10 | 2019-01-10 | 2019-01-24 | 2019-01-24
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2870 | PROCESS EQUIPMENT DATA SHEET - 10-D-2870 - C2R 2ND STAGE SUCTION DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-24 |  | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00349 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-09 | 2018-11-09 | 2018-12-10 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2880 | PROCESS EQUIPMENT DATA SHEET - 10-D-2880 - C2R 3RD STAGE SUCTION DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-23 | 2019-02-12 | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00208 | TPSK-LSPA1-T-PE-00208 | TPSK-LSPA1-T-PE-00845 | TPSK-LSPA1-T-PE-00845
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-02-25 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1 | TP | TP
| PE | OL1-2G30-2882 | PROCESS EQUIPMENT DATA SHEET - 10-E-2882 - LP ETHYLENE PRODUCT COOLER NO. 1 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-10 | 2018-09-11
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-09-11 | 2018-10-04 | 2018-10-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02 | 2018-10-02
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G30-2884 | PROCESS EQUIPMENT DATA SHEET - 10-E-2884 - LP ETHYLENE PRODUCT COOLER NO. 2 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-10 | 2018-09-11
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-09-11 | 2018-10-04 | 2018-10-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02 | 2018-10-02
[6 empty] | Owner Cmmt* |  | A3 | A3
| PE | OL1-2G30-2900 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2900 - PH CTRL / CORROSION INHIBITOR INJ PKG |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-20 | 2019-01-31 | 2019-02-01 | 2019-03-20 | 2019-03-21 | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00532 | TPSK-LSPA1-T-PE-00532 | TPSK-LSPA1-T-PE-00780 | TPSK-LSPA1-T-PE-00780 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-02284
[6 empty] | Return Date | 2019-01-28 | 2019-01-28 | 2019-02-28 | 2019-02-28 | 2019-04-10 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R2 | R1 | R1
| PE | OL1-2G30-2902 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2902 - EMULSION BREAKER INJ PKG |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-20 |  | 2019-01-25 | 2019-03-20 | 2019-03-21 | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-02184
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-05 | 2019-03-05 | 2019-04-10 | 2019-04-10 | 2019-08-16
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1 | R2
| PE | OL1-2G30-2904 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2904 - WATER STRIPPER CHEMICAL INJ PKG |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-20 |  | 2019-01-25 | 2019-03-20 | 2019-03-21 | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-02184
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-05 | 2019-03-05 | 2019-04-10 | 2019-04-10 | 2019-08-16
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1 | R2
| PE | OL1-2G30-2906 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2906 - DSG ANTI-FOULANT INJ PKG |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-20 |  | 2019-01-25 | 2019-03-20 | 2019-03-21 | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-02184
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-05 | 2019-03-05 | 2019-04-10 | 2019-04-10 | 2019-08-16
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1 | R2
| PE | OL1-2G30-2910 | PROCESS EQUIPMENT DATA SHEET - 10-TK-2910 - WASH OIL DAY TANK |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-27 |  | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00561 | TPSK-LSPA1-T-PE-00561 | TPSK-LSPA1-T-PE-00760 | TPSK-LSPA1-T-PE-00760
[6 empty] | Return Date | 2019-01-28 | 2019-01-28 | 2019-02-25 | 2019-02-25
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2911 | PROCESS EQUIPMENT DATA SHEET - 10-P-2910 - WASH OIL INJECTION PUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-10 | 2019-02-26 | 2019-02-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00613 | TPSK-LSPA1-T-PE-00613 | TPSK-LSPA1-T-PE-00939 | TPSK-LSPA1-T-PE-00939
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-21 | 2019-03-21
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2912 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2912 - CAUSTIC TOWER ANTI-FOULANT INJ PKG |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-20 | 2019-01-31 | 2019-02-01 | 2019-03-20 | 2019-03-21 | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00780 | TPSK-LSPA1-T-PE-00780 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-02184
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-02-28 | 2019-02-28 | 2019-04-10 | 2019-04-10 | 2019-08-16
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1 | R2
| PE | OL1-2G30-2914 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2914 - NEUTRALIZATION INJECTION PKG |  | Class 1 | Purpose** | IFR | IFR | CAN | CAN
[6 empty] | Rev. | A | A | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-16 | 2018-10-16 | 2019-04-11 | 2019-04-12
[6 empty] | Issue Actual | 2018-10-16 | 2018-10-16 | 2019-04-11 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00181 | TPSK-LSPA1-T-PE-00181 | TPSK-LSPA1-T-PE-01329 | TPSK-LSPA1-T-PE-01329
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-2920 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2920 - POLYMERIZATION INHIBITOR INJ PKG |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D | E | E | F
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-20 |  | 2019-01-25 | 2019-03-20 | 2019-03-21 | 2019-05-16 | 2019-05-17 | 2019-07-09 | 2019-07-09 | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-01686 | TPSK-LSPA1-T-PE-01686 | TPSK-LSPA1-T-PE-02099 | TPSK-LSPA1-T-PE-02099 | TPSK-LSPA1-T-PE-02284
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-02-11 | 2019-02-11 | 2019-04-10 | 2019-04-10 | 2019-06-13 | 2019-06-13 |  | 2019-08-08
[6 empty] | Owner Cmmt* | [9 empty] | R2 | bar: 2019-01-22 to 2019-06-13
| PE | OL1-2G30-2922 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2922 - CO INJECTION PACKAGE |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-02-11: IFD; 2019-02-11: IFD
Rev. | bar: 2019-01-22 to 2019-02-11
[6 empty] | Issue Plan | 2019-01-22: 2018-12-13; 2019-02-11: 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2018-12-20; 2019-02-11: 2019-01-16
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00560; 2019-01-22: TPSK-LSPA1-T-PE-00560; 2019-02-11: TPSK-LSPA1-T-PE-00656; 2019-02-11: TPSK-LSPA1-T-PE-00656
[6 empty] | Return Date | 2019-01-22: 2019-01-14; 2019-01-22: 2019-01-14; 2019-02-11: 2019-01-31; 2019-02-11: 2019-01-31
Owner Cmmt* | bar: 2019-01-22 to 2019-02-11
| PE | OL1-2G30-2931 | Process Equipment Datasheet - 10-PK-2931 - Propanol Injection Pkg |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-02-11: IFD; 2019-02-11: IFD
Rev. | bar: 2019-01-22 to 2019-02-11
[6 empty] | Issue Plan | 2019-01-22: 2018-12-13; 2019-02-11: 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-01-22; 2019-02-11: 2019-02-12; 2019-02-11: 2019-02-12
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00689; 2019-01-22: TPSK-LSPA1-T-PE-00689; 2019-02-11: TPSK-LSPA1-T-PE-00846; 2019-02-11: TPSK-LSPA1-T-PE-00846
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-02-11: 2019-02-25; 2019-02-11: 2019-02-25
Owner Cmmt* | bar: 2019-01-22 to 2019-02-11
| PE | OL1-2G30-2932 | Process Equipment Datasheet - 10-D-2930 - Methanol Drum |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-02-11: 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-14 | 2019-02-01 | 2019-02-04 | 2019-03-26 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA-1-T-PE-00644 | TPSK-LSPA-1-T-PE-00644 | TPSK-LSPA1-T-PE-00796 | TPSK-LSPA1-T-PE-00796 | TPSK-LSPA1-T-PE-01162 | TPSK-LSPA1-T-PE-01162
[6 empty] | Return Date | 2019-01-31 | 2019-01-31 | 2019-02-21 | 2019-02-21 | 2019-05-16 | 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-04-10
| PE | OL1-2G30-2934 | Process Equipment Datasheet - 10-P-2930 - Methanol Injection Pump |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-02-11: IFD; 2019-02-11: IFD
Rev. | bar: 2019-01-22 to 2019-02-11
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-02-11: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-01-14; 2019-02-11: 2019-02-12; 2019-02-11: 2019-02-12
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00645; 2019-01-22: TPSK-LSPA1-T-PE-00645; 2019-02-11: TPSK-LSPA1-T-PE-00844; 2019-02-11: TPSK-LSPA1-T-PE-00844
[6 empty] | Return Date | 2019-01-22: 2019-02-04; 2019-01-22: 2019-02-04; 2019-02-11: 2019-02-25; 2019-02-11: 2019-02-25
Owner Cmmt* | bar: 2019-01-22 to 2019-02-11
| PE | OL1-2G30-2940 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2940 - C4 POLYMER INHIBITOR INJECTION PKG |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D | E
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-20 |  | 2019-01-25 | 2019-03-20 | 2019-03-21 | 2019-04-16 | 2019-04-17 | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-01384 | TPSK-LSPA1-T-PE-01384 | TPSK-LSPA1-T-PE-02184
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-14 | 2019-03-14 | 2019-04-10 | 2019-04-10 | 2019-05-24 | 2019-05-24 | 2019-08-09
Owner Cmmt* | bar: 2019-01-22 to 2019-08-09
| PE | OL1-2G30-2945 | Process Equipment Datasheet - 10-PK-2945 - Anti-Oxidant Injection Package |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2018-12-13; 2019-03-14: 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-05-08; 2019-01-22: 2019-05-09; 2019-03-14: 2019-06-20; 2019-03-14: 2019-06-20; 2019-04-10: 2019-07-19
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01617; 2019-01-22: TPSK-LSPA1-T-PE-01617; 2019-03-14: TPSK-LSPA1-T-PE-01930; 2019-03-14: TPSK-LSPA1-T-PE-01930; 2019-04-10: TPSK-LSPA1-T-PE-02184
[6 empty] | Return Date | 2019-01-22: 2019-06-19; 2019-01-22: 2019-06-19; 2019-03-14: 2019-07-11; 2019-03-14: 2019-07-11; 2019-04-10: 2019-08-09
Owner Cmmt* | bar: 2019-01-22 to 2019-04-10
| PE | OL1-2G30-3000 | PROCESS EQUIPMENT DATA SHEET - 10-T-3000 - PREDISTILLATION TOWER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-01-21; 2019-03-14: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-26; 2019-03-14: 2019-05-21; 2019-03-14: 2019-05-23; 2019-04-10: 2019-07-29
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00923; 2019-01-22: TPSK-LSPA1-T-PE-00923; 2019-03-14: TPSK-LSPA1-T-PE-01708; 2019-03-14: TPSK-LSPA1-T-PE-01708; 2019-04-10: TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-01-22: 2019-03-15; 2019-01-22: 2019-03-15; 2019-03-14: 2019-06-13; 2019-03-14: 2019-06-13
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3001 | PROCESS EQUIPMENT DATA SHEET - 10-E-3000 - PREDISTILLATION CONDENSER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-25; 2019-01-22: 2019-03-26; 2019-03-14: 2019-06-03; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01148; 2019-01-22: TPSK-LSPA1-T-PE-01148; 2019-03-14: TPSK-LSPA1-T-PE-01796; 2019-03-14: TPSK-LSPA1-T-PE-01796
[6 empty] | Return Date | 2019-01-22: 2019-04-11; 2019-01-22: 2019-04-11; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3002 | PROCESS EQUIPMENT DATA SHEET - 10-P-3002 - PREDISTILLATION FEED PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-04; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-06
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01802; 2019-03-14: TPSK-LSPA1-T-PE-01802; 2019-04-10: TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3003 | PROCESS EQUIPMENT DATA SHEET - 10-P-3000 - PREDISTILLATION REFLUX PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-04; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-06
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01802; 2019-03-14: TPSK-LSPA1-T-PE-01802; 2019-04-10: TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3004 | PROCESS EQUIPMENT DATA SHEET - 10-E-3004 - PREDISTILLATION TRIM REBOILER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-25; 2019-01-22: 2019-03-26; 2019-03-14: 2019-06-03; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01148; 2019-01-22: TPSK-LSPA1-T-PE-01148; 2019-03-14: TPSK-LSPA1-T-PE-01796; 2019-03-14: TPSK-LSPA1-T-PE-01796
[6 empty] | Return Date | 2019-01-22: 2019-04-11; 2019-01-22: 2019-04-11; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3005 | PROCESS EQUIPMENT DATA SHEET - 10-E-3005 - PREDISTILLATION REBOILER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-25; 2019-01-22: 2019-03-26; 2019-03-14: 2019-06-03; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01148; 2019-01-22: TPSK-LSPA1-T-PE-01148; 2019-03-14: TPSK-LSPA1-T-PE-01796; 2019-03-14: TPSK-LSPA1-T-PE-01796
[6 empty] | Return Date | 2019-01-22: 2019-04-11; 2019-01-22: 2019-04-11; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3006 | PROCESS EQUIPMENT DATA SHEET - 10-D-3000 - PREDISTILLATION REFLUX DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-07; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01836; 2019-03-14: TPSK-LSPA1-T-PE-01836
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3007 | PROCESS EQUIPMENT DATA SHEET - 10-D-3002 - PREDISTILLATION FEED DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-07; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01836; 2019-03-14: TPSK-LSPA1-T-PE-01836
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3010 | PROCESS EQUIPMENT DATA SHEET - 10-D-3010 - C4 FEED DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-01-21; 2019-03-14: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-26; 2019-03-14: 2019-05-16; 2019-03-14: 2019-05-21; 2019-04-10: 2019-07-29
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00923; 2019-01-22: TPSK-LSPA1-T-PE-00923; 2019-03-14: TPSK-LSPA1-T-PE-01684; 2019-03-14: TPSK-LSPA1-T-PE-01684; 2019-04-10: TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-01-22: 2019-03-15; 2019-01-22: 2019-03-15; 2019-03-14: 2019-06-13; 2019-03-14: 2019-06-13
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3014 | PROCESS EQUIPMENT DATA SHEET - 10-E-3014 - C4 SOLVENT VAPORIZER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-25; 2019-01-22: 2019-03-26; 2019-03-14: 2019-05-29; 2019-03-14: 2019-05-30
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01148; 2019-01-22: TPSK-LSPA1-T-PE-01148; 2019-03-14: TPSK-LSPA1-T-PE-01762; 2019-03-14: TPSK-LSPA1-T-PE-01762
[6 empty] | Return Date | 2019-01-22: 2019-04-11; 2019-01-22: 2019-04-11; 2019-03-14: 2019-06-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3015 | PROCESS EQUIPMENT DATA SHEET - 10-E-3015 - C4 VAPORIZER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-29; 2019-01-22: 2019-04-01; 2019-03-14: 2019-05-30; 2019-03-14: 2019-05-31
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-03-14: TPSK-LSPA1-T-PE-01776; 2019-03-14: TPSK-LSPA1-T-PE-01776
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-06-25
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3016 | PROCESS EQUIPMENT DATA SHEET - 10-P-3016 - HEAVY END DISCHARGE PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-07; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01836; 2019-03-14: TPSK-LSPA1-T-PE-01836
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3018 | PROCESS EQUIPMENT DATA SHEET - 10-E-3018 - SOLVENT COOLER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-01; 2019-01-22: 2019-04-02; 2019-03-14: 2019-05-29; 2019-03-14: 2019-05-30
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01214; 2019-01-22: TPSK-LSAP1-T-PE-01214; 2019-03-14: TPSK-LSPA1-T-PE-01762; 2019-03-14: TPSK-LSPA1-T-PE-01762
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-06-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3020 | PROCESS EQUIPMENT DATA SHEET - 10-T-3020 - MAIN WASHER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-01-21; 2019-03-14: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-02-26; 2019-01-22: 2019-02-27; 2019-03-14: 2019-05-21; 2019-03-14: 2019-05-23; 2019-04-10: 2019-07-29
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00932; 2019-01-22: TPSK-LSPA1-T-PE-00932; 2019-03-14: TPSK-LSPA1-T-PE-01708; 2019-03-14: TPSK-LSPA1-T-PE-01708; 2019-04-10: TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-01-22: 2019-03-15; 2019-01-22: 2019-03-15; 2019-03-14: 2019-06-13; 2019-03-14: 2019-06-13
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3021 | PROCESS EQUIPMENT DATA SHEET - 10-D-3020 - MAIN WASHER REFLUX DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-01; 2019-01-22: 2019-04-02; 2019-03-14: 2019-05-29; 2019-03-14: 2019-05-30
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01214; 2019-01-22: TPSK-LSAP1-T-PE-01214; 2019-03-14: TPSK-LSPA1-T-PE-01762; 2019-03-14: TPSK-LSPA1-T-PE-01762
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-06-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3022 | PROCESS EQUIPMENT DATA SHEET - 10-P-3020 - MAIN WASHER REFLUX PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-06; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-06
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01820; 2019-03-14: TPSK-LSPA1-T-PE-01820; 2019-04-10: TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3023 | PROCESS EQUIPMENT DATA SHEET - 10-E-3020 - MAIN WASHER CONDENSER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01954; 2019-03-14: TPSK-LSPA1-T-PE-01954
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G30-3026 | PROCESS EQUIPMENT DATA SHEET - 10-P-3026 - MAIN WASHER BOTTOM PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01954; 2019-03-14: TPSK-LSPA1-T-PE-01954
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G30-3030 | PROCESS EQUIPMENT DATA SHEET - 10-T-3030 - AFTER WASHER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-01-21; 2019-03-14: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-02-28; 2019-01-22: 2019-03-01; 2019-03-14: 2019-05-16; 2019-03-14: 2019-05-21; 2019-04-10: 2019-07-29
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00955; 2019-01-22: TPSK-LSPA1-T-PE-00955; 2019-03-14: TPSK-LSPA1-T-PE-01684; 2019-03-14: TPSK-LSPA1-T-PE-01684; 2019-04-10: TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-01-22: 2019-03-15; 2019-01-22: 2019-03-15; 2019-03-14: 2019-06-13; 2019-03-14: 2019-06-13
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3031 | PROCESS EQUIPMENT DATA SHEET - 10-E-3030 - AFTER WASHER CONDENSER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-01; 2019-01-22: 2019-04-02; 2019-03-14: 2019-05-29; 2019-03-14: 2019-05-30
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01214; 2019-01-22: TPSK-LSAP1-T-PE-01214; 2019-03-14: TPSK-LSPA1-T-PE-01762; 2019-03-14: TPSK-LSPA1-T-PE-01762
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3032 | PROCESS EQUIPMENT DATA SHEET - 10-P-3030 - AFTER WASHER REFLUX PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-04; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-06
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01802; 2019-03-14: TPSK-LSPA1-T-PE-01802; 2019-04-10: TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3033 | PROCESS EQUIPMENT DATA SHEET - 10-D-3030 - AFTER WASHER REFLUX DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-07; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01836; 2019-03-14: TPSK-LSPA1-T-PE-01836
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3036 | PROCESS EQUIPMENT DATA SHEET - 10-P-3036 - AFTER WASHER BOTTOM PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-10; 2019-03-14: 2019-06-11
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01846; 2019-03-14: TPSK-LSPA1-T-PE-01846
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3040 | PROCESS EQUIPMENT DATA SHEET - 10-T-3040 - RECTIFIER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-01-21; 2019-03-14: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-01; 2019-01-22: 2019-03-04; 2019-03-14: 2019-05-21; 2019-03-14: 2019-05-23; 2019-04-10: 2019-07-29
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00958; 2019-01-22: TPSK-LSPA1-T-PE-00958; 2019-03-14: TPSK-LSPA1-T-PE-01708; 2019-03-14: TPSK-LSPA1-T-PE-01708; 2019-04-10: TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-01-22: 2019-04-02; 2019-01-22: 2019-04-02; 2019-03-14: 2019-06-13; 2019-03-14: 2019-06-13
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3044 | PROCESS EQUIPMENT DATA SHEET - 10-E-3044 - SOLVENT HEATER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-01; 2019-01-22: 2019-04-02; 2019-03-14: 2019-05-30; 2019-03-14: 2019-05-31
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01214; 2019-01-22: TPSK-LSAP1-T-PE-01214; 2019-03-14: TPSK-LSPA1-T-PE-01776; 2019-03-14: TPSK-LSPA1-T-PE-01776
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-06-25
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3045 | PROCESS EQUIPMENT DATA SHEET - 10-E-3045 - SOLVENT HEAT EXCHANGER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-01; 2019-01-22: 2019-04-02; 2019-03-14: 2019-05-30; 2019-03-14: 2019-05-31
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01214; 2019-01-22: TPSK-LSAP1-T-PE-01214; 2019-03-14: TPSK-LSPA1-T-PE-01776; 2019-03-14: TPSK-LSPA1-T-PE-01776
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-06-25
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3046 | PROCESS EQUIPMENT DATA SHEET - 10-P-3046 - DEGASSER FEED PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01954; 2019-03-14: TPSK-LSPA1-T-PE-01954
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G30-3047 | PROCESS EQUIPMENT DATA SHEET - 10-P-3045 - RECTIFIER PUMPS |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-10; 2019-03-14: 2019-06-11
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01847; 2019-03-14: TPSK-LSPA1-T-PE-01847
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3050 | PROCESS EQUIPMENT DATA SHEET - 10-T-3050 - DEGASSER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-01-21; 2019-03-14: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-02-28; 2019-01-22: 2019-03-01; 2019-03-14: 2019-05-16; 2019-03-14: 2019-05-21; 2019-04-10: 2019-07-29
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00955; 2019-01-22: TPSK-LSPA1-T-PE-00955; 2019-03-14: TPSK-LSPA1-T-PE-01684; 2019-03-14: TPSK-LSPA1-T-PE-01684; 2019-04-10: TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-01-22: 2019-03-15; 2019-01-22: 2019-03-15; 2019-03-14: 2019-06-13; 2019-03-14: 2019-06-13
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3055 | PROCESS EQUIPMENT DATA SHEET - 10-E-3055 - DEGASSER REBOILER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-29; 2019-01-22: 2019-04-01; 2019-03-14: 2019-05-30; 2019-03-14: 2019-05-31
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-03-14: TPSK-LSPA1-T-PE-01776; 2019-03-14: TPSK-LSPA1-T-PE-01776
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-06-25
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3056 | PROCESS EQUIPMENT DATA SHEET - 10-P-3056 - DEGASSER BOTTOM PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01954; 2019-03-14: TPSK-LSPA1-T-PE-01954
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G30-3060 | PROCESS EQUIPMENT DATA SHEET - 10-T-3060 - ACETYLENE WASHER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-01-21; 2019-03-14: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-26; 2019-03-14: 2019-05-21; 2019-03-14: 2019-05-23; 2019-04-10: 2019-07-29
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00923; 2019-01-22: TPSK-LSPA1-T-PE-00923; 2019-03-14: TPSK-LSPA1-T-PE-01708; 2019-03-14: TPSK-LSPA1-T-PE-01708; 2019-04-10: TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-01-22: 2019-03-15; 2019-01-22: 2019-03-15; 2019-03-14: 2019-06-13; 2019-03-14: 2019-06-13
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3061 | PROCESS EQUIPMENT DATA SHEET - 10-E-3060 - ACETYLENE WASHER CONDENSER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01945; 2019-03-14: TPSK-LSPA1-T-PE-01945
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-11; 2019-03-14: 2019-07-11
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3062 | PROCESS EQUIPMENT DATA SHEET - 10-E-3062 - ACETYLENE CONDENSER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-29; 2019-01-22: 2019-04-01; 2019-03-14: 2019-05-30; 2019-03-14: 2019-05-31
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-03-14: TPSK-LSPA1-T-PE-01776; 2019-03-14: TPSK-LSPA1-T-PE-01776
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-06-25
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3063 | PROCESS EQUIPMENT DATA SHEET - 10-P-3060 - WWASTE WATER PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-29; 2019-01-22: 2019-04-01; 2019-03-14: 2019-05-30; 2019-03-14: 2019-05-31
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-03-14: TPSK-LSPA1-T-PE-01776; 2019-03-14: TPSK-LSPA1-T-PE-01776
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-06-25
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3064 | PROCESS EQUIPMENT DATA SHEET - 10-P-3062 - C4 ACETYLENE PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-04; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-06
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01802; 2019-03-14: TPSK-LSPA1-T-PE-01802; 2019-04-10: TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3065 | PROCESS EQUIPMENT DATA SHEET - 10-P-3061 - WASTE HC PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-05; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-06
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01813; 2019-03-14: TPSK-LSPA1-T-PE-01813; 2019-04-10: TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3066 | PROCESS EQUIPMENT DATA SHEET - 10-D-3062 - ACETYLENE ACCUMULATOR |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01954; 2019-03-14: TPSK-LSPA1-T-PE-01954
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G30-3067 | PROCESS EQUIPMENT DATA SHEET - 10-D-3060 - C4 FEED DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01945; 2019-03-14: TPSK-LSPA1-T-PE-01945
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-11; 2019-03-14: 2019-07-11
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3070 | PROCESS EQUIPMENT DATA SHEET - 10-T-3070 - DIRECT COOLER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-01-21; 2019-03-14: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-02-28; 2019-01-22: 2019-03-01; 2019-03-14: 2019-05-16; 2019-03-14: 2019-05-21; 2019-04-10: 2019-07-29
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00955; 2019-01-22: TPSK-LSPA1-T-PE-00955; 2019-03-14: TPSK-LSPA1-T-PE-01684; 2019-03-14: TPSK-LSPA1-T-PE-01684; 2019-04-10: TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-01-22: 2019-03-15; 2019-01-22: 2019-03-15; 2019-03-14: 2019-06-13; 2019-03-14: 2019-06-13
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3071 | PROCESS EQUIPMENT DATA SHEET - 10-E-3070 - WATER / NMP COOLER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-29; 2019-01-22: 2019-04-01; 2019-03-14: 2019-06-03; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-03-14: TPSK-LSPA1-T-PE-01796; 2019-03-14: TPSK-LSPA1-T-PE-01796
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3072 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-3070 - RECYCLE GAS STEAM EJECTOR |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-09; 2019-01-22: 2019-04-10; 2019-03-14: 2019-06-07; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01283; 2019-01-22: TPSK-LSPA1-T-PE-01283; 2019-03-14: TPSK-LSPA1-T-PE-01827; 2019-03-14: TPSK-LSPA1-T-PE-01827
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3073 | PROCESS EQUIPMENT DATA SHEET - 10-C-3070 - RECYCLE GAS COMPRESSOR |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2018-12-07; 2019-03-14: 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2018-11-20; 2019-03-14: 2019-01-18
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00344; 2019-01-22: TPSK-LSPA1-T-PE-00344; 2019-03-14: TPSK-LSPA1-T-PE-00675; 2019-03-14: TPSK-LSPA1-T-PE-00675
[6 empty] | Return Date | 2019-01-22: 2018-12-13; 2019-01-22: 2018-12-13; 2019-03-14: 2019-03-21; 2019-03-14: 2019-03-21
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3076 | PROCESS EQUIPMENT DATA SHEET - 10-P-3076 - DIRECT COOLER PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01946; 2019-03-14: TPSK-LSPA1-T-PE-01946
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-11; 2019-03-14: 2019-07-11
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3080 | PROCESS EQUIPMENT DATA SHEET - 10-T-3080 - BUTADIENE TOWER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-01-21; 2019-03-14: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-26; 2019-03-14: 2019-05-16; 2019-03-14: 2019-05-21; 2019-04-10: 2019-07-29
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00923; 2019-01-22: TPSK-LSPA1-T-PE-00923; 2019-03-14: TPSK-LSPA1-T-PE-01684; 2019-03-14: TPSK-LSPA1-T-PE-01684; 2019-04-10: TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-01-22: 2019-03-15; 2019-01-22: 2019-03-15; 2019-03-14: 2019-06-13; 2019-03-14: 2019-06-13
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3081 | PROCESS EQUIPMENT DATA SHEET - 10-D-3080 - BUTADIENE TOWER REFLUX DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-29; 2019-01-22: 2019-04-01; 2019-03-14: 2019-05-30; 2019-03-14: 2019-05-31
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-03-14: TPSK-LSPA1-T-PE-01784; 2019-03-14: TPSK-LSPA1-T-PE-01784
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3082 | PROCESS EQUIPMENT DATA SHEET - 10-E-3080 - BUTADIENE TOWER CONDENSER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-05; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-06
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01813; 2019-03-14: TPSK-LSPA1-T-PE-01813; 2019-04-10: TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3083 | Process Equipment Data Sheet - 10-P-3080 A-B Butadiene Tower Reflux Pumps |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01946; 2019-03-14: TPSK-LSPA1-T-PE-01946
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-11; 2019-03-14: 2019-07-11
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3084 | PROCESS EQUIPMENT DATA SHEET - 10-E-3084 - BUTADIENE TOWER TRIM REBOILER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-29; 2019-01-22: 2019-04-01; 2019-03-14: 2019-06-03; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-03-14: TPSK-LSPA1-T-PE-01796; 2019-03-14: TPSK-LSPA1-T-PE-01796
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3085 | PROCESS EQUIPMENT DATA SHEET - 10-E-3085 - BUTADIENE TOWER REBOILER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-29; 2019-01-22: 2019-04-01; 2019-03-14: 2019-05-30; 2019-03-14: 2019-05-31
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-03-14: TPSK-LSPA1-T-PE-01784; 2019-03-14: TPSK-LSPA1-T-PE-01784
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3086 | PROCESS EQUIPMENT DATA SHEET - 10-P-3086 - C4 / C5 HC PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01946; 2019-03-14: TPSK-LSPA1-T-PE-01946
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-11; 2019-03-14: 2019-07-11
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3090 | PROCESS EQUIPMENT DATA SHEET - 10-T-3090 - BUTADIENE DRYING TOWER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-01-21; 2019-03-14: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-02-26; 2019-01-22: 2019-02-27; 2019-03-14: 2019-05-21; 2019-03-14: 2019-05-23; 2019-04-10: 2019-07-29
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00932; 2019-01-22: TPSK-LSPA1-T-PE-00932; 2019-03-14: TPSK-LSPA1-T-PE-01708; 2019-03-14: TPSK-LSPA1-T-PE-01708; 2019-04-10: TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-01-22: 2019-03-15; 2019-01-22: 2019-03-15; 2019-03-14: 2019-06-13; 2019-03-14: 2019-06-13
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3095 | PROCESS EQUIPMENT DATA SHEET - 10-E-3095 - BUTADIENE DRYING TOWER REBOILER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-29; 2019-01-22: 2019-04-01; 2019-03-14: 2019-06-03; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-03-14: TPSK-LSPA1-T-PE-01796; 2019-03-14: TPSK-LSPA1-T-PE-01796
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3097 | PROCESS EQUIPMENT DATA SHEET - 10-P-3096 - BUTADIENE PRODUCT PUMPS |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01946; 2019-03-14: TPSK-LSPA1-T-PE-01946
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-11; 2019-03-14: 2019-07-11
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3098 | PROCESS EQUIPMENT DATA SHEET - 10-E-3098 - BUTADIENE PRODUCT SUBCOOLER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-29; 2019-01-22: 2019-04-01; 2019-03-14: 2019-05-29; 2019-03-14: 2019-05-30
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-03-14: TPSK-LSPA1-T-PE-01762; 2019-03-14: TPSK-LSPA1-T-PE-01762
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-06-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3100 | PROCESS EQUIPMENT DATA SHEET - 10-D-3100 - SOLVENT REGEN DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-05; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-06
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01813; 2019-03-14: TPSK-LSPA1-T-PE-01813; 2019-04-10: TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3101 | PROCESS EQUIPMENT DATA SHEET - 10-A-3100 - SOLVENT REGEN AGITATOR |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-11; 2019-01-22: 2019-04-12; 2019-03-14: 2019-06-06; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01319; 2019-01-22: TPSK-LSPA1-T-PE-01319; 2019-03-14: TPSK-LSPA1-T-PE-01824; 2019-03-14: TPSK-LSPA1-T-PE-01824
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3110 | PROCESS EQUIPMENT DATA SHEET - 10-T-3110 - WATER WASHER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-01-21; 2019-03-14: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-01; 2019-01-22: 2019-03-04; 2019-03-14: 2019-05-21; 2019-03-14: 2019-05-23; 2019-04-10: 2019-07-29
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00973; 2019-01-22: TPSK-LSPA1-T-PE-00973; 2019-03-14: TPSK-LSPA1-T-PE-01711; 2019-03-14: TPSK-LSPA1-T-PE-01711; 2019-04-10: TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-01-22: 2019-04-02; 2019-01-22: 2019-04-02; 2019-03-14: 2019-06-13; 2019-03-14: 2019-06-13
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3111 | PROCESS EQUIPMENT DATA SHEET - 10-D-3110 - WATER WASHER ACCUMULATOR |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-29; 2019-01-22: 2019-04-01; 2019-03-14: 2019-05-30; 2019-03-14: 2019-05-31
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-01-22: TPSK-LSAP1-T-PE-01202; 2019-03-14: TPSK-LSPA1-T-PE-01786; 2019-03-14: TPSK-LSPA1-T-PE-01786
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-06-25
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3112 | PROCESS EQUIPMENT DATA SHEET - 10-E-3110 - WATER WASHER CONDENSER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-05; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-06
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01813; 2019-03-14: TPSK-LSPA1-T-PE-01813; 2019-04-10: TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3113 | PROCESS EQUIPMENT DATA SHEET - 10-P-3110 - SOLVENT RETURN PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01947; 2019-03-14: TPSK-LSPA1-T-PE-01947
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-11; 2019-03-14: 2019-07-11
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3123 | PROCESS EQUIPMENT DATA SHEET - 10-PK-3120 - REGEN STEAM EJECTOR PKG |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-09; 2019-01-22: 2019-04-10; 2019-03-14: 2019-06-06; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01284; 2019-01-22: TPSK-LSPA1-T-PE-01284; 2019-03-14: TPSK-LSPA1-T-PE-01823; 2019-03-14: TPSK-LSPA1-T-PE-01823
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3126 | PROCESS EQUIPMENT DATA SHEET - 10-D-3126 - EJECTOR SEAL DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-05; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-06
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01813; 2019-03-14: TPSK-LSPA1-T-PE-01813; 2019-04-10: TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3127 | PROCESS EQUIPMENT DATA SHEET - 10-P-3126 - WASTE WATER RETURN PUMPS |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01947; 2019-03-14: TPSK-LSPA1-T-PE-01947
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-11; 2019-03-14: 2019-07-11
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3150 | PROCESS EQUIPMENT DATA SHEET - 10-E-3150 - CONDENSATE HEATER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-01; 2019-01-22: 2019-04-02; 2019-03-14: 2019-06-03; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01214; 2019-01-22: TPSK-LSAP1-T-PE-01214; 2019-03-14: TPSK-LSPA1-T-PE-01796; 2019-03-14: TPSK-LSPA1-T-PE-01796
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3151 | PROCESS EQUIPMENT DATA SHEET - 10-D-3150 - CONDENSATE FLASH DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-05; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-15
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01813; 2019-03-14: TPSK-LSPA1-T-PE-01813; 2019-04-10: TPSK-LSPA1-T-PE-02427
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3160 | PROCESS EQUIPMENT DATA SHEET - 10-E-3160 - CONDENSATE COOLER |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-01; 2019-01-22: 2019-04-02; 2019-03-14: 2019-06-03; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSAP1-T-PE-01214; 2019-01-22: TPSK-LSAP1-T-PE-01214; 2019-03-14: TPSK-LSPA1-T-PE-01796; 2019-03-14: TPSK-LSPA1-T-PE-01796
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3161 | PROCESS EQUIPMENT DATA SHEET - 10-D-3160 - CONDENSATE DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-05; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-06
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01813; 2019-03-14: TPSK-LSPA1-T-PE-01813; 2019-04-10: TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3162 | PROCESS EQUIPMENT DATA SHEET - 10-P-3160 - CONDENSATE RECYCLE PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01947; 2019-03-14: TPSK-LSPA1-T-PE-01947
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-11; 2019-03-14: 2019-07-11
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3180 | PROCESS EQUIPMENT DATA SHEET - 10-D-3180 - BLOWDOWN DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-06; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-06
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01820; 2019-03-14: TPSK-LSPA1-T-PE-01820; 2019-04-10: TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3190 | PROCESS EQUIPMENT DATA SHEET - 10-D-3190 - NMP SLOP DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-06; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-06
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01820; 2019-03-14: TPSK-LSPA1-T-PE-01820; 2019-04-10: TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3191 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-3190 - NMP SLOP SUMP EDUCTOR |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-01-22: TPSK-LSPA1-T-PE-01265; 2019-03-14: TPSK-LSPA1-T-PE-01945; 2019-03-14: TPSK-LSPA1-T-PE-01945
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-11; 2019-03-14: 2019-07-11
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3192 | PROCESS EQUIPMENT DATA SHEET - 10-P-3190 - SOLVENT SLOP PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-01-22: 2019-03-11
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-26; 2019-03-14: 2019-03-27
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01160; 2019-03-14: TPSK-LSPA1-T-PE-01160
[6 empty] | Return Date | 2019-01-22: 2019-04-11; 2019-03-14: 2019-04-11
Owner Cmmt* | bar: 2019-01-22 to 2019-03-14
| PE | OL1-2G30-3900 | PROCESS EQUIPMENT DATA SHEET - 10-TK-3900 - NMP STORAGE TANK |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-11; 2019-01-22: 2019-04-12; 2019-03-14: 2019-06-06; 2019-03-14: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01318; 2019-01-22: TPSK-LSPA1-T-PE-01318; 2019-03-14: TPSK-LSPA1-T-PE-01825; 2019-03-14: TPSK-LSPA1-T-PE-01825
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3901 | PROCESS EQUIPMENT DATA SHEET - 10-P-3900 - NMP STORAGE PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-09; 2019-01-22: 2019-04-10; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA-1-PE-01285; 2019-01-22: TPSK-LSPA-1-PE-01285; 2019-03-14: TPSK-LSPA1-T-PE-01954; 2019-03-14: TPSK-LSPA1-T-PE-01954
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G30-3902 | PROCESS EQUIPMENT DATA SHEET - 10-P-3902 - SOLVENT INHIBITOR DOSING PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-10; 2019-03-14: 2019-06-11; 2019-04-10: 2019-08-15
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01849; 2019-03-14: TPSK-LSPA1-T-PE-01849; 2019-04-10: TPSK-LSPA1-T-PE-02427
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3903 | PROCESS EQUIPMENT DATA SHEET - 10-D-3902 - SOLVENT INHIBITOR DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-09; 2019-01-22: 2019-04-10; 2019-03-14: 2019-06-21; 2019-03-14: 2019-06-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA-1-PE-01285; 2019-01-22: TPSK-LSPA-1-PE-01285; 2019-03-14: TPSK-LSPA1-T-PE-01954; 2019-03-14: TPSK-LSPA1-T-PE-01954
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G30-3904 | PROCESS EQUIPMENT DATA SHEET - 10-D-3904 - PRODUCT INHIBITOR DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-06; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-15
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01826; 2019-03-14: TPSK-LSPA1-T-PE-01826; 2019-04-10: TPSK-LSPA1-T-PE-02427
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3905 | PROCESS EQUIPMENT DATA SHEET - 10-P-3904 - PRODUCT INHIBITOR DOSING PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFR; 2019-03-14: IFR; 2019-04-10: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-04-10: 2019-04-01
[6 empty] | Revised Plan | 2019-04-10: 2019-08-16
[6 empty] | Issue Actual | 2019-01-22: 2019-04-09; 2019-01-22: 2019-04-10; 2019-03-14: 2019-06-25; 2019-03-14: 2019-06-25
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA-1-PE-01285; 2019-01-22: TPSK-LSPA-1-PE-01285; 2019-03-14: TPSK-LSPA1-T-PE-01978; 2019-03-14: TPSK-LSPA1-T-PE-01978
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G30-3906 | PROCESS EQUIPMENT DATA SHEET - 10-D-3906 - ANTI FOAM AGENT DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-06; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-15
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01826; 2019-03-14: TPSK-LSPA1-T-PE-01826; 2019-04-10: TPSK-LSPA1-T-PE-02427
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-3907 | PROCESS EQUIPMENT DATA SHEET - 10-P-3906 - ANTIFOAM DOSING PUMP |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFR; 2019-03-14: IFR; 2019-04-10: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-04-10: 2019-04-01
[6 empty] | Revised Plan | 2019-04-10: 2019-08-16
[6 empty] | Issue Actual | 2019-01-22: 2019-04-09; 2019-01-22: 2019-04-10; 2019-03-14: 2019-06-25; 2019-03-14: 2019-06-25
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA-1-PE-01285; 2019-01-22: TPSK-LSPA-1-PE-01285; 2019-03-14: TPSK-LSPA1-T-PE-01978; 2019-03-14: TPSK-LSPA1-T-PE-01978
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G30-3908 | PROCESS EQUIPMENT DATA SHEET - 10-D-3908 - PREDISTILLATION INHIBITOR DRUM |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFR; 2019-03-14: IFR; 2019-04-10: IFD
Rev. | bar: 2019-01-22 to 2019-03-14
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-04-10: 2019-04-01
[6 empty] | Revised Plan | 2019-04-10: 2019-08-16
[6 empty] | Issue Actual | 2019-01-22: 2019-04-09; 2019-01-22: 2019-04-10; 2019-03-14: 2019-06-25; 2019-03-14: 2019-06-25
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA-1-PE-01285; 2019-01-22: TPSK-LSPA-1-PE-01285; 2019-03-14: TPSK-LSPA1-T-PE-01978; 2019-03-14: TPSK-LSPA1-T-PE-01978
[6 empty] | Return Date | 2019-01-22: 2019-05-16; 2019-01-22: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G30-3910 | Process Equipment Data Sheet - 10-D-3908 - Predistillation Inhibitor Drum |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-14: IFD; 2019-03-14: IFD; 2019-04-10: IFD
[6 empty] | Rev. | 2019-01-22: A; 2019-01-22: A; 2019-03-14: B; 2019-03-14: B; 2019-04-10: C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-04-05; 2019-01-22: 2019-04-08; 2019-03-14: 2019-06-06; 2019-03-14: 2019-06-10; 2019-04-10: 2019-08-15
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-01-22: TPSK-LSPA1-T-PE-01263; 2019-03-14: TPSK-LSPA1-T-PE-01826; 2019-03-14: TPSK-LSPA1-T-PE-01826; 2019-04-10: TPSK-LSPA1-T-PE-02427
[6 empty] | Return Date | 2019-01-22: 2019-05-09; 2019-01-22: 2019-05-09; 2019-03-14: 2019-07-08
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-14
| PE | OL1-2G30-5100 | PROCESS EQUIPMENT DATA SHEET - 10-D-5100 - DEAERATOR |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-01-22: 2019-02-18; 2019-03-14: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2018-10-09; 2019-01-22: 2018-10-10; 2019-03-14: 2018-11-14; 2019-04-10: 2019-03-27; 2019-04-10: 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00151 | TPSK-LSPA1-T-PE-00151 | TPSK-LSPA1-T-PE-00318 | TPSK-LSPA1-T-PE-00318 | TPSK-LSPA1-T-PE-01174 | TPSK-LSPA1-T-PE-01174
[6 empty] | Return Date | 2018-11-05 | 2018-11-05 | 2019-02-21 | 2019-02-21 | 2019-04-22 | 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-04-10
| PE | OL1-2G30-5101 | PROCESS EQUIPMENT DATA SHEET - 10-P-5100 - SHP BFW PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-14: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2018-10-08; 2019-01-22: 2018-10-09; 2019-03-14: 2018-10-31; 2019-04-10: 2019-04-25; 2019-04-10: 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00251 | TPSK-LSPA1-T-PE-00251 | TPSK-LSPA1-T-PE-01483 | TPSK-LSPA1-T-PE-01483
[6 empty] | Return Date | 2018-10-26 | 2018-10-26 | 2018-12-13 | 2018-12-13 | 2019-06-17 | 2019-06-17
Owner Cmmt* | bar: 2019-01-22 to 2019-04-10
| PE | OL1-2G30-5102 | PROCESS EQUIPMENT DATA SHEET - 10-P-5102 - BFW PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-09 |  | 2018-10-31 | 2019-03-29 | 2019-04-01 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00251 | TPSK-LSPA1-T-PE-00251 | TPSK-LSPA1-T-PE-01196 | TPSK-LSPA1-T-PE-01196 | TPSK-LSPA1-T-PE-01484 | TPSK-LSPA1-T-PE-01484
[6 empty] | Return Date | 2018-10-26 | 2018-10-26 | 2018-12-13 | 2018-12-13 | 2019-06-07 | 2019-06-07 | 2019-06-17 | 2019-06-17
Owner Cmmt* | bar: 2018-10-26 to 2019-06-17
| PE | OL1-2G30-5103 | PROCESS EQUIPMENT DATA SHEET - 10-E-5100 - DEARATOR VENT CONDENSER |  | Class 1 | Purpose** | IFD | IFR | IFR | IFD | CAN | CAN
[6 empty] | Rev. | B | A | A | B | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2018-12-13: 2018-10-25; 2018-12-13: 2018-11-26; 2019-06-07: 2019-03-19; 2019-06-07: 2019-03-20
[6 empty] | Issue Actual | 2018-12-13: 2018-10-25; 2018-12-13: 2018-11-26; 2019-06-07: 2019-03-19; 2019-06-07: 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00366 | TPSK-LSPA1-T-PE-00230 | TPSK-LSPA1-T-PE-00230 | TPSK-LSPA1-T-PE-00366 | TPSK-LSPA1-T-PE-01097 | TPSK-LSPA1-T-PE-01097
[6 empty] | Return Date | 2018-12-10 | 2018-11-14 | 2018-11-14 | 2018-12-10 | 2019-04-02 | 2019-04-02
Owner Cmmt* | bar: 2018-10-26 to 2019-06-07
| PE | OL1-2G30-5107 | PROCESS EQUIPMENT DATA SHEET - 10-E-5112 - SUSPECT CONDENSATE FLASH DRUM VENT CONDENSER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2018-10-26: 2019-02-18; 2018-12-13: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-26: 2018-10-30; 2018-12-13: 2019-01-14; 2019-06-07: 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00243 | TPSK-LSPA1-T-PE-00243 | TPSK-LSPA1-T-PE-00646 | TPSK-LSPA1-T-PE-00646 | TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2018-10-26: 2018-11-14; 2018-10-26: 2018-11-14; 2018-12-13: 2019-02-21; 2018-12-13: 2019-02-21
Owner Cmmt* | bar: 2018-10-26 to 2018-12-13
| PE | OL1-2G30-5108 | PROCESS EQUIPMENT DATA SHEET - 10-E-5110 - SUSPECT CONDENSATE COOLER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-10-26: 2019-02-18; 2018-12-13: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-26: 2018-10-30; 2018-12-13: 2019-01-14; 2019-06-07: 2019-06-19; 2019-06-07: 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00243 | TPSK-LSPA1-T-PE-00243 | TPSK-LSPA1-T-PE-00652 | TPSK-LSPA1-T-PE-00652 | TPSK-LSPA1-T-PE-01918 | TPSK-LSPA1-T-PE-01918
[6 empty] | Return Date | 2018-11-14 | 2018-11-14 | 2019-02-21 | 2019-02-21 | 2019-07-11 | 2019-07-11
Owner Cmmt* | bar: 2018-10-26 to 2019-06-07
| PE | OL1-2G30-5109 | PROCESS EQUIPMENT DATA SHEET - 10-P-5110 - CONDENSATE PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-09 |  | 2018-10-31 | 2019-03-14 | 2019-03-15 | 2019-03-28 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00251 | TPSK-LSPA1-T-PE-00251 | TPSK-LSPA1-T-PE-01051 | TPSK-LSPA1-T-PE-01051 | TPSK-LSAP1-T-PE-01189 | TPSK-LSAP1-T-PE-01189
[6 empty] | Return Date | 2018-10-26 | 2018-10-26 | 2018-12-13 | 2018-12-13 | 2019-04-02 | 2019-04-02 | 2019-05-09 | 2019-05-09
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R2 | R2 | R2 | R2 | Re
| PE | OL1-2G30-5110 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5110 - CONDENSATE TANK |  | Class 1 | Purpose** | 2018-10-26: IFR; 2018-10-26: IFR; 2018-12-13: IFD; 2018-12-13: IFD
Rev. | bar: 2018-10-26 to 2018-12-13
[6 empty] | Issue Plan | 2018-10-26: 2019-02-18; 2018-12-13: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2018-10-26: 2018-11-27; 2018-12-13: 2019-03-11; 2018-12-13: 2019-03-12
[6 empty] | Transmittal no. | 2018-10-26: TPSK-LSPA1-T-PE-00374; 2018-10-26: TPSK-LSPA1-T-PE-00374; 2018-12-13: TPSK-LSPA1-T-PE-01017; 2018-12-13: TPSK-LSPA1-T-PE-01017
[6 empty] | Return Date | 2018-10-26: 2018-12-18; 2018-10-26: 2018-12-18; 2018-12-13: 2019-03-27; 2018-12-13: 2019-03-27
Owner Cmmt* | bar: 2018-10-26 to 2018-12-13
| PE | OL1-2G30-5111 | PROCESS EQUIPMENT DATA SHEET - 10-P-5112 - SUSPECT CONDENSATE PUMPS |  | Class 1 | Purpose** | 2018-10-26: IFR; 2018-10-26: IFR; 2018-12-13: IFD; 2018-12-13: IFD
Rev. | bar: 2018-10-26 to 2018-12-13
[6 empty] | Issue Plan | 2018-10-26: 2019-03-11; 2018-12-13: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-10-26: 2018-10-24; 2018-12-13: 2018-11-26
[6 empty] | Transmittal no. | 2018-10-26: TPSK-LSPA1-T-PE-00219; 2018-10-26: TPSK-LSPA1-T-PE-00219; 2018-12-13: TPSK-LSPA1-T-PE-00363; 2018-12-13: TPSK-LSPA1-T-PE-00363
[6 empty] | Return Date | 2018-10-26: 2018-11-14; 2018-10-26: 2018-11-14; 2018-12-13: 2018-12-13; 2018-12-13: 2018-12-13
Owner Cmmt* | bar: 2018-10-26 to 2018-12-13
| PE | OL1-2G30-5112 | PROCESS EQUIPMENT DATA SHEET - 10-D-5112 - SUSPECT CONDENSATE FLASH DRUM |  | Class 1 | Purpose** | 2018-10-26: IFR; 2018-10-26: IFR; 2018-12-13: IFD; 2018-12-13: IFD
Rev. | bar: 2018-10-26 to 2018-12-13
[6 empty] | Issue Plan | 2018-10-26: 2019-02-18; 2018-12-13: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-26: 2018-11-05; 2018-12-13: 2018-12-14
[6 empty] | Transmittal no. | 2018-10-26: TPSK-LSPA1-T-PE-00274; 2018-10-26: TPSK-LSPA1-T-PE-00274; 2018-12-13: TPSK-LSPA1-T-PE-00498; 2018-12-13: TPSK-LSPA1-T-PE-00498
[6 empty] | Return Date | 2018-10-26: 2018-12-10; 2018-10-26: 2018-12-10; 2018-12-13: 2019-01-10; 2018-12-13: 2019-01-10
Owner Cmmt* | bar: 2018-10-26 to 2018-12-13
| PE | OL1-2G30-5113 | PROCESS EQUIPMENT DATA SHEET - 10-E-5113 - FOUL CONDENSATE COOLER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-25 |  | 2018-11-26 | 2019-04-08 | 2019-04-09 | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00230 | TPSK-LSPA1-T-PE-00230 | TPSK-LSPA1-T-PE-00366 | TPSK-LSPA1-T-PE-00366 | TPSK-LSPA1-T-PE-01278 | TPSK-LSPA1-T-PE-01278 | TPSK-LSPA1-T-PE-01406 | TPSK-LSPA1-T-PE-01406
[6 empty] | Return Date | 2018-11-14 | 2018-11-14 | 2018-12-10 | 2018-12-10 | 2019-06-07 | 2019-06-07 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1 | R1 | R1
| PE | OL1-2G30-5114 | PROCESS EQUIPMENT DATA SHEET - 10-D-5114 - LP CONDENSATE FLASH DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-05 |  | 2018-12-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00274 | TPSK-LSPA1-T-PE-00274 | TPSK-LSPA1-T-PE-00498 | TPSK-LSPA1-T-PE-00498
[6 empty] | Return Date | 2018-12-10 | 2018-12-10 | 2019-01-10 | 2019-01-10
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5115 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5115 - CONDENSATE CARBON FILTERS |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-12-20 |  | 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-26 | 2019-01-31 | 2019-02-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00362 | TPSK-LSPA1-T-PE-00362 | TPSK-LSPA1-T-PE-00778 | TPSK-LSPA1-T-PE-00778
[6 empty] | Return Date | 2018-12-18 | 2018-12-18 | 2019-02-21 | 2019-02-21
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5120 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5120 - RAW CONDENSATE TANK |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-26 | 2019-03-14 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00364 | TPSK-LSPA1-T-PE-00364 | TPSK-LSPA1-T-PE-01055 | TPSK-LSPA1-T-PE-01055
[6 empty] | Return Date | 2018-12-17 | 2018-12-17 | 2019-03-29 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5121 | PROCESS EQUIPMENT DATA SHEET - 10-P-5120 - RAW CONDENSATE PUMPS |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-24 |  | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00219 | TPSK-LSPA1-T-PE-00219 | TPSK-LSPA1-T-PE-00363 | TPSK-LSPA1-T-PE-00363
[6 empty] | Return Date | 2018-11-14 | 2018-11-14 | 2018-12-13 | 2018-12-13
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-5125 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5125 - CONDENSATE POLISHER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-12-20 |  | 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-27 | 2019-01-31 | 2019-02-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00373 | TPSK-LSPA1-T-PE-00373 | TPSK-LSPA1-T-PE-00778 | TPSK-LSPA1-T-PE-00778
[6 empty] | Return Date | 2018-12-13 | 2018-12-13 | 2019-02-21 | 2019-02-21
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5140 | PROCESS EQUIPMENT DATA SHEET - 10-D-5140 - INTERMITTENT BLOWDOWN DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-19 |  | 2018-12-14 | 2019-03-05 | 2019-03-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00331 | TPSK-LSPA1-T-PE-00331 | TPSK-LSPA1-T-PE-00504 | TPSK-LSPA1-T-PE-00504 | TPSK-LSPA1-T-PE-00988 | TPSK-LSPA1-T-PE-00988
[6 empty] | Return Date | 2018-12-04 | 2018-12-04 | 2019-01-10 | 2019-01-10 | 2019-03-15 | 2019-03-15
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R1 | R1
| PE | OL1-2G30-5141 | PROCESS EQUIPMENT DATA SHEET - 10-P-5140 - INTERMITTENT BLOWDOWN PUMPS |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-24 | 2019-03-14 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00219 | TPSK-LSPA1-T-PE-00219 | TPSK-LSPA1-T-PE-01051 | TPSK-LSPA1-T-PE-01051
[6 empty] | Return Date | 2018-11-14 | 2018-11-14 | 2019-04-02 | 2019-04-02
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-5150 | PROCESS EQUIPMENT DATA SHEET - 10-D-5150 - CONTINUOUS BLOWDOWN FLASH DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-19 |  | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00331 | TPSK-LSPA1-T-PE-00331 | TPSK-LSPA1-T-PE-00440 | TPSK-LSPA1-T-PE-00440
[6 empty] | Return Date | 2018-12-04 | 2018-12-04 | 2019-03-11 | 2019-03-11
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5170 | Process Data Sheet For General Purpose Steam Turbines - API 611-4TH - PT-5100 A-B SHP BFW Pumps Turbines |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-12 | 2019-06-14
[6 empty] | Issue Actual | 2019-06-12 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01875 | TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date |  | 2019-07-09
[6 empty] | Owner Cmmt* |  | R1
| PL | OL1-2G30-5171 | Process Data Sheet For General Purpose Steam Turbines - API 611-4TH - PT-5102 A VLP BFW Pump Turbine |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-12 | 2019-06-14
[6 empty] | Issue Actual | 2019-06-12 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01875 | TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date |  | 2019-07-09
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-5172 | Process Data Sheet For General Purpose Steam Turbines Pt-5110A Condensate Pump Turbine |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11 | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11 | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-01867 | TPSK-LSPA1-T-MP-01867
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5200 | PROCESS EQUIPMENT DATA SHEET - 10-D-5200 - FUEL GAS DRUM |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-19 |  | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00331 | TPSK-LSPA1-T-PE-00331 | TPSK-LSPA1-T-PE-00440 | TPSK-LSPA1-T-PE-00440
[6 empty] | Return Date | 2018-12-04 | 2018-12-04 | 2019-01-04 | 2019-01-04
[6 empty] | Owner Cmmt* | R2 | R2 | TP | TP
| PE | OL1-2G30-5201 | PROCESS EQUIPMENT DATA SHEET - 10-E-5200 - MP ETHYLENE SUPERHEATER |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-05 | 2019-02-15 | 2019-02-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00275 | TPSK-LSPA1-T-PE-00275 | TPSK-LSPA1-T-PE-00853 | TPSK-LSPA1-T-PE-00853
[6 empty] | Return Date | 2018-11-29 | 2018-11-29 | 2019-03-13 | 2019-03-13
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-5202 | Process Equipment Datasheet - 10-D-5220 - MP Ethylene Superhtr Cond Pot |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-10 | 2019-02-11 | 2019-02-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00614 | TPSK-LSPA1-T-PE-00614 | TPSK-LSPA1-T-PE--00836 | TPSK-LSPA1-T-PE--00836
[6 empty] | Return Date | 2019-01-24 | 2019-01-24 | 2019-03-27 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5210 | PROCESS EQUIPMENT DATA SHEET - 10-E-5210 - PILOT GAS VAPORIZER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-15 | 2019-03-14 | 2019-03-15 | 2019-04-08 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00321 | TPSK-LSPA1-T-PE-00321 | TPSK-LSPA1-T-PE-01054 | TPSK-LSPA1-T-PE-01054 | TPSK-LSPA1-T-PE-01278 | TPSK-LSPA1-T-PE-01278
[6 empty] | Return Date | 2018-12-13 | 2018-12-13 | 2019-03-29 | 2019-03-29 | 2019-06-07 | 2019-06-07
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-5211 | PROCESS EQUIPMENT DATA SHEET - 10-D-5210 - PILOT GAS VAPORIZER COND POT |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-10 | 2019-02-11 | 2019-02-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00614 | TPSK-LSPA1-T-PE-00614 | TPSK-LSPA1-T-PE--00836 | TPSK-LSPA1-T-PE--00836
[6 empty] | Return Date | 2019-01-24 | 2019-01-24 | 2019-03-27 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5301 | Process Data Sheet for 10-S-5301 A-H |  | Class 2 | Rev.: Purpose**; A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02323
Return Date
Owner Cmmt*
| PE | OL1-2G30-5302 | Process Data Sheet for 10-S-5302 A-B |  | Class 2 | Rev.: Purpose**; A: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02323
Return Date
Owner Cmmt*
| PE | OL1-2G30-5350 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5350 - COOLING TOWER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-03 |  |  | 2018-12-26
[6 empty] | Revised Plan |  | 2018-09-25 | 2018-09-25
[6 empty] | Issue Actual |  | 2018-09-25 | 2018-09-25 |  | 2018-10-24 | 2019-03-25 | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00082 | TPSK-LSPA1-T-PE-00082 | TPSK-LSPA1-T-PE-00226 | TPSK-LSPA1-T-PE-00226 | TPSK-LSPA1-T-PE-01150 | TPSK-LSPA1-T-PE-01150
[6 empty] | Return Date |  | 2018-10-13 | 2018-10-13 | 2018-11-14 | 2018-11-14 | 2019-04-12 | 2019-04-12
[6 empty] | Owner Cmmt* |  | A3 | A3 | A1 | A1 | R2 | R2
| PE | OL1-2G30-5351 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5351 - OLEFINS CW PUMPS SUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2018-12-03 |  | 2018-12-26
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-20 | 2019-02-01 | 2019-02-04 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA-1-T-PE-00539 | TPSK-LSPA-1-T-PE-00539 | TPSK-LSPA1-T-PE-00791 | TPSK-LSPA1-T-PE-00791 | TPSK-LSPA1-T-PE-02339
[6 empty] | Return Date | 2019-01-16 | 2019-01-16 | 2019-03-13 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5352 | PROCESS EQUIPMENT DATA SHEET - 10-P-5350 - OLEFINS COOLING WATER PUMPS |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | C | B | C
[6 empty] | Issue Plan | 2019-03-11 |  |  | 2019-04-01
[6 empty] | Revised Plan |  | 2018-09-24 | 2018-09-25
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-09-25 |  |  | 2018-10-24 | 2018-10-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00225 | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00225 | TPSK-LSPA1-T-PE-00075
[6 empty] | Return Date |  | 2019-04-22 | 2019-04-22 | 2018-11-14 | 2018-11-14 | 2018-11-14 | 2018-11-14
[6 empty] | Owner Cmmt* |  | A1 | A1 | A1 | A1 | A1 | A1
| PE | OL1-2G30-5355 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5355 - SIDE STREAM FILTER PKG |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | C | B | B | C
[6 empty] | Issue Plan | 2018-12-03 |  |  | 2018-12-26
[6 empty] | Revised Plan |  | 2018-09-25 | 2018-09-25
[6 empty] | Issue Actual |  | 2018-09-25 | 2018-09-25 |  |  | 2018-10-24 | 2019-01-08
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00082 | TPSK-LSPA1-T-PE-00082 | TPSK-LSPA1-T-PE-00611 | TPSK-LSPA1-T-PE-00226 | TPSK-LSPA1-T-PE-00226 | TPSK-LSPA1-T-PE-00611
[6 empty] | Return Date |  | 2018-10-13 | 2018-10-13 | 2019-01-24 | 2018-11-14 | 2018-11-14 | 2019-01-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | A1 | A1 | A1 | A1
| PE | OL1-2G30-5360 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5360 - CTU CW PUMPS SUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2018-12-03 |  | 2018-12-26
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-20 | 2019-02-01 | 2019-02-04 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA-1-T-PE-00539 | TPSK-LSPA-1-T-PE-00539 | TPSK-LSPA1-T-PE-00791 | TPSK-LSPA1-T-PE-00791 | TPSK-LSPA1-T-PE-02323
[6 empty] | Return Date | 2019-01-16 | 2019-01-16 | 2019-03-13 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5361 | PROCESS EQUIPMENT DATA SHEET - 10-P-5360 - CTU COOLING WATER PUMPS |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | D | C | B | B | C | D
[6 empty] | Issue Plan | 2019-03-11 | D: 2019-04-01
[6 empty] | Revised Plan |  | A: 2018-09-24; A: 2018-09-25
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-09-25 |  |  |  | 2018-10-24 | 2018-10-26 | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00593 | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00225 | TPSK-LSPA1-T-PE-00225 | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00593
[6 empty] | Return Date |  | 2018-10-24 | 2018-10-24 | 2019-02-04 | 2018-11-14 | 2018-11-14 | 2018-11-14 | 2018-11-14 | 2019-02-04
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | A1 | A1 | A1 | A1 | R1
| PE | OL1-2G30-5370 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5370 - CW FILTER BACKWASH SUMP |  | Class 1 | Purpose** | IFR | A: IFR; A: IFD; D: IFD
[6 empty] | Rev. | A | bar: A to D
[6 empty] | Issue Plan | 2018-12-03 | A: 2018-12-26
Revised Plan
[6 empty] | Issue Actual |  | A: 2018-12-20; A: 2019-02-01; D: 2019-02-04
[6 empty] | Transmittal no. | TPSK-LSPA-1-T-PE-00539 | A: TPSK-LSPA-1-T-PE-00539; A: TPSK-LSPA1-T-PE-00791; D: TPSK-LSPA1-T-PE-00791
[6 empty] | Return Date | 2019-01-16 | A: 2019-01-16; A: 2019-03-13; D: 2019-03-13
[6 empty] | Owner Cmmt* | R2 | bar: A to D
| PE | OL1-2G30-5371 | PROCESS EQUIPMENT DATA SHEET - 10-P-5370 - CW FILTER BACKWASH PUMPS |  | Class 1 | Purpose** | IFR | A: IFR; A: IFD; D: IFD
[6 empty] | Rev. | A | bar: A to D
[6 empty] | Issue Plan | 2019-03-11 | A: 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | A: 2019-01-10; A: 2019-04-16; D: 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00623 | A: TPSK-LSPA1-T-PE-00623; A: TPSK-LSPA1-T-PE-01366; D: TPSK-LSPA1-T-PE-01366
[6 empty] | Return Date | 2019-02-04 | A: 2019-02-04; A: 2019-05-24; D: 2019-05-24
[6 empty] | Owner Cmmt* | R2 | bar: A to D
| PE | OL1-2G30-5390 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5390 - COPPER CORROSION INHIBITOR INJ PKG |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-27 | 2019-02-19 | 2019-02-19 | 2019-03-20 | 2019-03-21 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00877 | TPSK-LSPA1-T-PE-00877 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-02198
[6 empty] | Return Date | 2018-12-13 | 2018-12-13 | 2019-03-13 | 2019-03-13 | 2019-04-10 | 2019-04-10 | 2019-08-06
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1 | R2
| PE | OL1-2G30-5392 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5392 - MILD STEEL CORROSION INHIBITOR INJ PKG |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-27 | 2019-02-19 | 2019-02-19 | 2019-03-20 | 2019-03-21 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00890 | TPSK-LSPA1-T-PE-00890 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-02198
[6 empty] | Return Date | 2018-12-13 | 2018-12-13 | 2019-03-13 | 2019-03-13 | 2019-04-10 | 2019-04-10 | 2019-08-06
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1 | R2
| PE | OL1-2G30-5394 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5394 - DISPERSANT INJ PKG |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-27 | 2019-02-19 | 2019-02-19 | 2019-03-20 | 2019-03-21 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00877 | TPSK-LSPA1-T-PE-00877 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-02198
[6 empty] | Return Date | 2018-12-13 | 2018-12-13 | 2019-03-13 | 2019-03-13 | 2019-04-10 | 2019-04-10 | 2019-08-06
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1 | R2
| PE | OL1-2G30-5397 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5397 - NON-OXIDIZING BIOCIDE INJ PKG |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-27 | 2019-02-19 | 2019-02-19 | 2019-03-20 | 2019-03-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00877 | TPSK-LSPA1-T-PE-00877 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-01111
[6 empty] | Return Date | 2018-12-13 | 2018-12-13 | 2019-03-13 | 2019-03-13 | 2019-04-10 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-5400 | PROCESS EQUIPMENT DATA SHEET - 10-D-5400 - INSTRUMENT AIR RECEIVER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-02-06 | 2019-02-06 | 2019-03-04 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00485 | TPSK-LSPA1-T-PE-00485 | TPSK-LSPA1-T-PE-00800 | TPSK-LSPA1-T-PE-00800 | TPSK-LSPA1-T-PE-00983 | TPSK-LSPA1-T-PE-00983
[6 empty] | Return Date | 2019-01-07 | 2019-01-07 | 2019-03-13 | 2019-03-13 | 2019-03-13 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| PE | OL1-2G30-5500 | PROCESS EQUIPMENT DATA SHEET - 10-D-5500 - WARM FLARE DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-12 | 2018-10-15 |  | 2018-12-05 | 2019-03-11 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00168 | TPSK-LSPA1-T-PE-00168 | TPSK-LSPA1-T-PE-00417 | TPSK-LSPA1-T-PE-00417 | TPSK-LSPA1-T-PE-01020 | TPSK-LSPA1-T-PE-01020
[6 empty] | Return Date | 2018-11-14 | 2018-11-14 | 2019-01-04 | 2019-01-04 | 2019-03-27 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R1 | R1
| PE | OL1-2G30-5501 | PROCESS EQUIPMENT DATA SHEET - 10-P-5500 - HOT BLOWDOWN PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-27 | 2019-01-30 | 2019-01-31 | 2019-03-11 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01022 | TPSK-LSPA1-T-PE-01022
[6 empty] | Return Date | 2019-01-24 | 2019-01-24 | 2019-03-05 | 2019-03-05 | 2019-03-27 | 2019-03-27
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1
| PE | OL1-2G30-5510 | PROCESS EQUIPMENT DATA SHEET - 10-D-5510 - COLD FLARE DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-29 | 2019-03-11 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00397 | TPSK-LSPA1-T-PE-00397 | TPSK-LSPA1-T-PE-01018 | TPSK-LSPA1-T-PE-01018
[6 empty] | Return Date | 2019-01-04 | 2019-01-04 | 2019-03-27 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5511 | PROCESS EQUIPMENT DATA SHEET - 10-E-5510 - COLD FLARE BLOWDOWN VAPORIZER |  | Class 1 | Purpose** | IFR | IFR | IFR | IFR | IFD | IFD
[6 empty] | Rev. | B | A | A | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  |  |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  |  | 2019-01-03 | 2019-01-11 | 2019-04-04 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00626 | TPSK-LSPA1-T-PE-00575 | TPSK-LSPA1-T-PE-00575 | TPSK-LSPA1-T-PE-00626 | TPSK-LSPA1-T-PE-01261 | TPSK-LSPA1-T-PE-01261
[6 empty] | Return Date | 2019-02-04 | 2019-03-13 | 2019-03-13 | 2019-02-04 | 2019-05-09 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R1 | R1
| PE | OL1-2G30-5512 | PROCESS EQUIPMENT DATA SHEET - 10-E-5512 - COLD FLARE SUPERHEATER |  | Class 1 | Purpose** | IFR | IFR | IFR | IFR | IFD | IFD
[6 empty] | Rev. | B | A | A | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  |  |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  |  | 2019-01-03 | 2019-01-11 | 2019-03-26 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00626 | TPSK-LSPA1-T-PE-00575 | TPSK-LSPA1-T-PE-00575 | TPSK-LSPA1-T-PE-00626 | TPSK-LSPA1-T-PE-01161 | TPSK-LSPA1-T-PE-01161
[6 empty] | Return Date | 2019-02-04 | 2019-03-13 | 2019-03-13 | 2019-02-04 | 2019-04-11 | 2019-04-11
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1
| PE | OL1-2G30-5513 | PROCESS EQUIPMENT DATA SHEET - 10-E-5513 - METHANOL VAPORIZER |  | Class 1 | Purpose** | IFR | IFR | IFR | IFR | IFD | IFD
[6 empty] | Rev. | B | A | A | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  |  |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  |  | 2019-01-03 | 2019-01-11 | 2019-03-26 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00626 | TPSK-LSPA1-T-PE-00575 | TPSK-LSPA1-T-PE-00575 | TPSK-LSPA1-T-PE-00626 | TPSK-LSPA1-T-PE-01161 | TPSK-LSPA1-T-PE-01161
[6 empty] | Return Date | 2019-02-04 | 2019-03-13 | 2019-03-13 | 2019-02-04 | 2019-04-11 | 2019-04-11
[6 empty] | Owner Cmmt* | R1 | R2 | R2 | R1 | R1 | R1
| PE | OL1-2G30-5514 | PROCESS EQUIPMENT DATA SHEET - 10-D-5513 - METHANOL VAPROIZER COND POT |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-10 | 2019-02-01 | 2019-02-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00614 | TPSK-LSPA1-T-PE-00614 | TPSK-LSPA1-T-PE-00785 | TPSK-LSPA1-T-PE-00785
[6 empty] | Return Date | 2019-01-24 | 2019-01-24 | 2019-03-13 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5515 | PROCESS EQUIPMENT DATA SHEET - 10-D-5515 - METHANOL MAKE-UP DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-20 | 2019-03-14 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00527 | TPSK-LSPA1-T-PE-00527 | TPSK-LSPA1-T-PE-01052 | TPSK-LSPA1-T-PE-01052
[6 empty] | Return Date | 2019-01-24 | 2019-01-24 | 2019-03-29 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5520 | PROCESS EQUIPMENT DATA SHEET - 10-D-5520 - VENT COLLECTION DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-26 | 2019-02-15 | 2019-02-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00365 | TPSK-LSPA1-T-PE-00365 | TPSK-LSPA1-T-PE-00856 | TPSK-LSPA1-T-PE-00856
[6 empty] | Return Date | 2018-12-13 | 2018-12-13 | 2019-03-13 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5521 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5520 - LP VENT BLOWER PKG |  | Class 1 | Purpose** | IFR | IFR | CAN | CAN
[6 empty] | Rev. | A | A | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  | 2018-11-19 | 2019-03-20 | 2019-03-21
[6 empty] | Issue Actual |  | 2018-11-19 | 2019-03-20 | 2019-03-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00332 | TPSK-LSPA1-T-PE-00332 | TPSK-LSPA1-T-PE-01112 | TPSK-LSPA1-T-PE-01112
[6 empty] | Return Date | 2018-12-06 | 2018-12-06 | 2019-04-10 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-5522 | Process Equipment Datasheet - 10-C-5520 A-B - LP Vent Blowers |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-20 | 2019-02-11 | 2019-02-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00528 | TPSK-LSPA1-T-PE-00528 | TPSK-LSPA1-T-PE-00837 | TPSK-LSPA1-T-PE-00837
[6 empty] | Return Date | 2019-01-24 | 2019-01-24 | 2019-03-13 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5550 | PROCESS EQUIPMENT DATA SHEET - 10-D-5550 - HP FLARE KNOCK OUT DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-10-07 | 2018-10-08 |  | 2018-12-07 | 2019-03-11 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00142 | TPSK-LSPA1-T-PE-00142 | TPSK-LSPA1-T-PE-00440 | TPSK-LSPA1-T-PE-00440 | TPSK-LSPA1-T-PE-01020 | TPSK-LSPA1-T-PE-01020
[6 empty] | Return Date | 2018-10-26 | 2018-10-26 | 2019-01-04 | 2019-01-04 | 2019-03-27 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R1 | R1
| PE | OL1-2G30-5551 | PROCESS EQUIPMENT DATA SHEET - 10-P-5550 - HP FLARE KNOCK OUT DRUM PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-27 | 2019-01-30 | 2019-01-31 | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01366 | TPSK-LSPA1-T-PE-01366
[6 empty] | Return Date | 2019-01-24 | 2019-01-24 | 2019-03-05 | 2019-03-05 | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R2 | R1 | R1
| PE | OL1-2G30-5552 | PROCESS EQUIPMENT DATA SHEET - 10-D-5552 - LPG STORAGE DRUM |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-07 | 2019-03-07 | 2019-03-08 | 2019-04-04 | 2019-04-05 | 2019-05-16 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-01008 | TPSK-LSPA1-T-PE-01008 | TPSK-LSPA1-T-PE-01260 | TPSK-LSPA1-T-PE-01260 | TPSK-LSPA1-T-PE-01677 | TPSK-LSPA1-T-PE-01677
[6 empty] | Return Date | 2018-12-27 | 2018-12-27 | 2019-03-27 | 2019-03-27 | 2019-05-09 | 2019-05-09 | 2019-06-04 | 2019-06-04
Owner Cmmt* | bar: 2018-12-27 to 2019-06-04
| PE | OL1-2G30-5553 | PROCESS EQUIPMENT DATA SHEET - 10-E-5552 - LPG VAPORIZER / SUPERHEATER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-03-27: 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-10 | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00622 | TPSK-LSPA1-T-PE-00622 | TPSK-LSPA1-T-PE-01054 | TPSK-LSPA1-T-PE-01054 | TPSK-LSPA1-T-PE-01589 | TPSK-LSPA1-T-PE-01589
[6 empty] | Return Date | 2018-12-27: 2019-02-04; 2018-12-27: 2019-02-04; 2019-03-27: 2019-03-29; 2019-03-27: 2019-03-29
Owner Cmmt* | bar: 2018-12-27 to 2019-03-27
| PE | OL1-2G30-5555 | Process Equipment Datasheet - 10-D-5553 - LPG Vaporizer - Superhtr Cond Pot |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-03-27: 2019-03-25
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-10 | 2019-03-11 | 2019-03-12 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00619 | TPSK-LSPA1-T-PE-00619 | TPSK-LSPA1-T-PE-01018 | TPSK-LSPA1-T-PE-01018 | TPSK-LSPA1-T-PE-01590 | TPSK-LSPA1-T-PE-01590
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-27 | 2019-03-27 | 2019-06-17 | 2019-06-17
Owner Cmmt* | bar: 2018-12-27 to 2019-05-09
| PE | OL1-2G30-5560 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5560 - HP/LLDPE LP FLARE PACKAGE |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2018-12-07; 2019-03-27: 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-29 | 2019-03-07 | 2019-03-08 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00398 | TPSK-LSPA1-T-PE-00398 | TPSK-LSPA1-T-PE-01007 | TPSK-LSPA1-T-PE-01007 | TPSK-LSPA1-T-PE-01506 | TPSK-LSPA1-T-PE-01506
[6 empty] | Return Date | 2018-12-13 | 2018-12-13 | 2019-03-29 | 2019-03-29 | 2019-06-17 | 2019-06-17
Owner Cmmt* | bar: 2018-12-27 to 2019-05-09
| PE | OL1-2G30-5565 | PROCESS EQUIPMENT DATA SHEET- 10-D-5565 - LLDPE LP FLARE KNOCK OUT DRUM |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-03-27: IFD; 2019-03-27: IFD
Rev. | bar: 2018-12-27 to 2019-03-27
[6 empty] | Issue Plan | 2018-12-27: 2019-02-18; 2019-03-27: 2019-03-25
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2018-12-20; 2019-03-27: 2019-03-05; 2019-03-27: 2019-03-06
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00558; 2018-12-27: TPSK-LSPA1-T-PE-00558; 2019-03-27: TPSK-LSPA1-T-PE-00989; 2019-03-27: TPSK-LSPA1-T-PE-00989
[6 empty] | Return Date | 2018-12-27: 2019-01-22; 2018-12-27: 2019-01-22; 2019-03-27: 2019-03-21; 2019-03-27: 2019-03-21
Owner Cmmt* | bar: 2018-12-27 to 2019-03-27
| PE | OL1-2G30-5566 | Process Equipment Datasheet - 10-P-5565 A-B - Polyolefins Flare Knock-out Pumps |  | Class 2 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-03-27: IFD; 2019-03-27: IFD
Rev. | bar: 2018-12-27 to 2019-03-27
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-03-27: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-01-10; 2019-03-27: 2019-04-16; 2019-03-27: 2019-04-17
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00623; 2018-12-27: TPSK-LSPA1-T-PE-00623; 2019-03-27: TPSK-LSPA1-T-PE-01366; 2019-03-27: TPSK-LSPA1-T-PE-01366
[6 empty] | Return Date | 2018-12-27: 2019-02-04; 2018-12-27: 2019-02-04; 2019-03-27: 2019-05-24; 2019-03-27: 2019-05-24
Owner Cmmt* | bar: 2018-12-27 to 2019-03-27
| PE | OL1-2G30-5570 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5570 - ENCLOSED GROUND FLARE PACKAGE |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-03-27: IFD; 2019-03-27: IFD
Rev. | bar: 2018-12-27 to 2019-03-27
[6 empty] | Issue Plan | 2018-12-27: 2018-12-07; 2019-03-27: 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-03-01; 2018-12-27: 2019-03-04; 2019-03-27: 2019-04-11; 2019-03-27: 2019-04-12
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00959; 2018-12-27: TPSK-LSPA1-T-PE-00959; 2019-03-27: TPSK-LSPA1-T-PE-01326; 2019-03-27: TPSK-LSPA1-T-PE-01326
[6 empty] | Return Date | 2018-12-27: 2019-03-21; 2018-12-27: 2019-03-21; 2019-03-27: 2019-05-16; 2019-03-27: 2019-05-16
Owner Cmmt* | bar: 2018-12-27 to 2019-03-27
| PE | OL1-2G30-5600 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5600 - PYGAS AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2018-12-20; 2019-03-27: 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-02-11 | 2019-02-11 | 2019-03-04 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00982 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-27 | 2019-03-27 | 2019-03-13 | 2019-03-13
Owner Cmmt* | bar: 2018-12-27 to 2019-05-09
| PE | OL1-2G30-5601 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5601 - BUTADIENE AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2018-12-20; 2019-03-27: 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-02-07 | 2019-02-07 | 2019-03-04 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-27 | 2019-03-27 | 2019-03-13 | 2019-03-13
Owner Cmmt* | bar: 2018-12-27 to 2019-05-09
| PE | OL1-2G30-5602 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5602 - QW AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2018-12-20; 2019-03-27: 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-02-07 | 2019-02-07 | 2019-03-04 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-27 | 2019-03-27 | 2019-03-13 | 2019-03-13
Owner Cmmt* | bar: 2018-12-27 to 2019-05-09
| PE | OL1-2G30-5603 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5603 - CGC AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2018-12-20; 2019-03-27: 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-02-07 | 2019-02-07 | 2019-03-04 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-27 | 2019-03-27 | 2019-03-13 | 2019-03-13
Owner Cmmt* | bar: 2018-12-27 to 2019-05-09
| PE | OL1-2G30-5604 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5604 - REFRIG AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2018-12-20; 2019-03-27: 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-02-07 | 2019-02-07 | 2019-03-04 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-27 | 2019-03-27 | 2019-03-13 | 2019-03-13
Owner Cmmt* | bar: 2018-12-27 to 2019-05-09
| PE | OL1-2G30-5605 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5605 - FURNACE AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | CAN | CAN
[6 empty] | Rev. | A | A | B | B | C | C | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  | 2019-01-07 | 2019-02-07 | 2019-02-07 | 2019-03-04 | 2019-03-05 | 2019-05-09 | 2019-05-10
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-02-07 | 2019-02-07 | 2019-03-04 | 2019-03-05 | 2019-05-09 | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982 | TPSK-LSPA1-T-PE-00982 | TPSK-LSPA1-T-PE-01630 | TPSK-LSPA1-T-PE-01630
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-27 | 2019-03-27 | 2019-03-13 | 2019-03-13 | 2019-06-04 | 2019-06-04
Owner Cmmt* | bar: 2018-12-27 to 2019-06-04
| PE | OL1-2G30-5606 | PROCESS EQUIPMENT DATA SHEET - 10-P-5600 - PYGAS AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-03-27: 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-03 | 2019-01-31 | 2019-02-01 | 2019-03-14 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00779 | TPSK-LSPA1-T-PE-00779 | TPSK-LSPA1-T-PE-01051 | TPSK-LSPA1-T-PE-01051
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-04 | 2019-03-04 | 2019-04-02 | 2019-04-02
Owner Cmmt* | bar: 2018-12-27 to 2019-05-09
| PE | OL1-2G30-5607 | PROCESS EQUIPMENT DATA SHEET - 10-P-5601 - BUTADIENE AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-03-27: IFD; 2019-03-27: IFD
Rev. | bar: 2018-12-27 to 2019-03-27
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-03-27: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-01-03; 2019-03-27: 2019-01-30; 2019-03-27: 2019-01-31
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00572; 2018-12-27: TPSK-LSPA1-T-PE-00572; 2019-03-27: TPSK-LSPA1-T-PE-00774; 2019-03-27: TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2018-12-27: 2019-01-22; 2018-12-27: 2019-01-22; 2019-03-27: 2019-03-05; 2019-03-27: 2019-03-05
Owner Cmmt* | bar: 2018-12-27 to 2019-03-27
| PE | OL1-2G30-5608 | PROCESS EQUIPMENT DATA SHEET - 10-P-5602 - QW AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-03-27: IFD; 2019-03-27: IFD
Rev. | bar: 2018-12-27 to 2019-03-27
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-03-27: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-01-03; 2019-03-27: 2019-01-30; 2019-03-27: 2019-01-31
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00572; 2018-12-27: TPSK-LSPA1-T-PE-00572; 2019-03-27: TPSK-LSPA1-T-PE-00774; 2019-03-27: TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2018-12-27: 2019-01-22; 2018-12-27: 2019-01-22; 2019-03-27: 2019-03-05; 2019-03-27: 2019-03-05
Owner Cmmt* | bar: 2018-12-27 to 2019-03-27
| PE | OL1-2G30-5609 | PROCESS EQUIPMENT DATA SHEET - 10-P-5603 - CGC AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-03-27: IFD; 2019-03-27: IFD
Rev. | bar: 2018-12-27 to 2019-03-27
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-03-27: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-01-03; 2019-03-27: 2019-01-30; 2019-03-27: 2019-01-31
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00572; 2018-12-27: TPSK-LSPA1-T-PE-00572; 2019-03-27: TPSK-LSPA1-T-PE-00774; 2019-03-27: TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2018-12-27: 2019-01-22; 2018-12-27: 2019-01-22; 2019-03-27: 2019-03-05; 2019-03-27: 2019-03-05
Owner Cmmt* | bar: 2018-12-27 to 2019-03-27
| PE | OL1-2G30-5610 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5610 - HYDROBLAST SUMP |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-03-27: IFD; 2019-03-27: IFD
Rev. | bar: 2018-12-27 to 2019-03-27
[6 empty] | Issue Plan | 2018-12-27: 2018-12-20; 2019-03-27: 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-01-07; 2019-03-27: 2019-04-08; 2019-03-27: 2019-04-09
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00589; 2018-12-27: TPSK-LSPA1-T-PE-00589; 2019-03-27: TPSK-LSPA1-T-PE-01281; 2019-03-27: TPSK-LSPA1-T-PE-01281
[6 empty] | Return Date | 2018-12-27: 2019-02-04; 2018-12-27: 2019-02-04; 2019-03-27: 2019-06-07; 2019-03-27: 2019-06-07
Owner Cmmt* | bar: 2018-12-27 to 2019-03-27
| PE | OL1-2G30-5611 | PROCESS EQUIPMENT DATA SHEET - 10-P-5610 - HYDROBLAST PUMPS |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-03-27: IFD; 2019-03-27: IFD
Rev. | bar: 2018-12-27 to 2019-03-27
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-03-27: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-01-07; 2019-03-27: 2019-03-14; 2019-03-27: 2019-03-15
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00590; 2018-12-27: TPSK-LSPA1-T-PE-00590; 2019-03-27: TPSK-LSPA1-T-PE-01051; 2019-03-27: TPSK-LSPA1-T-PE-01051
[6 empty] | Return Date | 2018-12-27: 2019-01-24; 2018-12-27: 2019-01-24; 2019-03-27: 2019-04-02; 2019-03-27: 2019-04-02
Owner Cmmt* | bar: 2018-12-27 to 2019-03-27
| PE | OL1-2G30-5612 | PROCESS EQUIPMENT DATA SHEET - 10-F-5610 - HYDROBLAST FILTER |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2018-12-07; 2019-03-27: 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-10 | 2019-03-07 | 2019-03-08 | 2019-04-04 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00454 | TPSK-LSPA1-T-PE-00454 | TPSK-LSPA1-T-PE-01009 | TPSK-LSPA1-T-PE-01009 | TPSK-LSPA1-T-PE-01259 | TPSK-LSPA1-T-PE-01259
[6 empty] | Return Date | 2019-03-11 | 2019-03-11 | 2019-03-27 | 2019-03-27 | 2019-05-09 | 2019-05-09
Owner Cmmt* | bar: 2018-12-27 to 2019-05-09
| PE | OL1-2G30-5613 | PROCESS EQUIPMENT DATA SHEET - 10-P-5604 - REFRIG AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-03-27: IFD; 2019-03-27: IFD
Rev. | bar: 2018-12-27 to 2019-03-27
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-03-27: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-01-03; 2019-03-27: 2019-01-30; 2019-03-27: 2019-01-31
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00572; 2018-12-27: TPSK-LSPA1-T-PE-00572; 2019-03-27: TPSK-LSPA1-T-PE-00774; 2019-03-27: TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2018-12-27: 2019-01-22; 2018-12-27: 2019-01-22; 2019-03-27: 2019-03-05; 2019-03-27: 2019-03-05
Owner Cmmt* | bar: 2018-12-27 to 2019-03-27
| PE | OL1-2G30-5614 | PROCESS EQUIPMENT DATA SHEET - 10-P-5605 - FURNACE AREA OILY WATER PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | CAN | CAN
[6 empty] | Rev. | A | A | B | B | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  | 2019-01-03 | 2019-01-31 | 2019-02-01 | 2019-05-09 | 2019-05-10
[6 empty] | Issue Actual |  | 2019-01-03 | 2019-01-31 | 2019-02-01 | 2019-05-09 | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00779 | TPSK-LSPA1-T-PE-00779 | TPSK-LSPA1-T-PE-01631 | TPSK-LSPA1-T-PE-01631
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-04 | 2019-03-04 | 2019-06-04 | 2019-06-04
Owner Cmmt* | bar: 2018-12-27 to 2019-05-09
| PE | OL1-2G30-5615 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5615 - OLEFINS STORMWATER SUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2018-12-20; 2019-03-27: 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-11 | 2019-03-01 | 2019-03-04 | 2019-03-14 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00636 | TPSK-LSPA1-T-PE-00636 | TPSK-LSPA1-T-PE-00960 | TPSK-LSPA1-T-PE-00960 | TPSK-LSPA1-T-PE-01068 | TPSK-LSPA1-T-PE-01068
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-14 | 2019-03-14 | 2019-04-02 | 2019-04-02
Owner Cmmt* | bar: 2018-12-27 to 2019-05-09
| PE | OL1-2G30-5616 | PROCESS EQUIPMENT DATA SHEET - 10-P-5615 - OLEFINS STORMWATER SUMP PUMPS |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-03-27: IFD; 2019-03-27: IFD
Rev. | bar: 2018-12-27 to 2019-03-27
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-03-27: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-01-03; 2019-03-27: 2019-01-30; 2019-03-27: 2019-01-31
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00576; 2018-12-27: TPSK-LSPA1-T-PE-00576; 2019-03-27: TPSK-LSPA1-T-PE-00774; 2019-03-27: TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2018-12-27: 2019-01-22; 2018-12-27: 2019-01-22; 2019-03-27: 2019-03-05; 2019-03-27: 2019-03-05
Owner Cmmt* | bar: 2018-12-27 to 2019-03-27
| PE | OL1-2G30-5620 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5620 - OLEFINS HOLDING BASIN |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2018-12-20; 2019-03-27: 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-03-01 | 2019-03-04 | 2019-03-14 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00960 | TPSK-LSPA1-T-PE-00960 | TPSK-LSPA1-T-PE-01068 | TPSK-LSPA1-T-PE-01068
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-14 | 2019-03-14 | 2019-04-02 | 2019-04-02
Owner Cmmt* | bar: 2018-12-27 to 2019-05-09
| PE | OL1-2G30-5621 | PROCESS EQUIPMENT DATA SHEET - 10-P-5621 - OLEFINS HOLDING BASIN SKIM OIL PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-03-27: 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-03 | 2019-01-30 | 2019-01-31 | 2019-03-11 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00576 | TPSK-LSPA1-T-PE-00576 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01022 | TPSK-LSPA1-T-PE-01022
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-05 | 2019-03-05 | 2019-03-27 | 2019-03-27
Owner Cmmt* | bar: 2018-12-27 to 2019-05-09
| PE | OL1-2G30-5622 | PROCESS EQUIPMENT DATA SHEET - 10-P-5620 - OLEFINS HOLDING BASIN PUMPS |  | Class 1 | Purpose** | 2018-12-27: IFR; 2018-12-27: IFR; 2019-03-27: IFD; 2019-03-27: IFD
Rev. | bar: 2018-12-27 to 2019-03-27
[6 empty] | Issue Plan | 2018-12-27: 2019-03-11; 2019-03-27: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-12-27: 2019-01-11; 2019-03-27: 2019-04-04; 2019-03-27: 2019-04-05
[6 empty] | Transmittal no. | 2018-12-27: TPSK-LSPA1-T-PE-00635; 2018-12-27: TPSK-LSPA1-T-PE-00635; 2019-03-27: TPSK-LSPA1-T-PE-01255; 2019-03-27: TPSK-LSPA1-T-PE-01255
[6 empty] | Return Date | 2018-12-27: 2019-02-04; 2018-12-27: 2019-02-04; 2019-03-27: 2019-05-09; 2019-03-27: 2019-05-09
Owner Cmmt* | bar: 2018-12-27 to 2019-03-27
| PE | OL1-2G30-5623 | Process Equipment Datasheet - 10-P-5626 A-B - Gate House Septic Tank Pumps |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-03 | 2019-01-30 | 2019-01-31 | 2019-03-25 | 2019-03-26 | 2019-04-04 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01152 | TPSK-LSPA1-T-PE-01152 | TPSK-LSPA1-T-PE-01255 | TPSK-LSPA1-T-PE-01255
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-05 | 2019-03-05 | 2019-04-12 | 2019-04-12
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1 | R1
| PE | OL1-2G30-5624 | Process Equipment Datasheet - 10-P-5627 A-B - West Gate House Septic Tank Pumps |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-03 | 2019-01-30 | 2019-01-31 | 2019-03-25 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01152 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-05 | 2019-03-05 | 2019-04-12 | 2019-04-12
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R2 | R1 | R1
| PE | OL1-2G30-5625 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5625 - SANITARY LIFT STATION IFAR 1 |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-03 | 2019-01-30 | 2019-01-31 | 2019-03-25 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01152 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-05 | 2019-03-05 | 2019-04-12 | 2019-04-12
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R2 | R1 | R1
| PE | OL1-2G30-5626 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5626 - SANITARY LIFT STATION IFAR 2 |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-20 |  | 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-02-11 | 2019-02-11 | 2019-04-04 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-01257 | TPSK-LSPA1-T-PE-01257
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-27 | 2019-03-27 | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R2 | Re
| PE | OL1-2G30-5627 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5627 - SANITARY LIFT STATION WEST GATE HOUSE |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-20 |  | 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-02-11 | 2019-02-11 | 2019-04-04 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-01257 | TPSK-LSPA1-T-PE-01257
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-27 | 2019-03-27 | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R2 | Re
| PE | OL1-2G30-5628 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5628 - SANITARY LIFT STATION EAST GATE HOUSE |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-20 |  | 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-02-11 | 2019-02-11 | 2019-04-04 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-01257 | TPSK-LSPA1-T-PE-01257
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-27 | 2019-03-27 | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R2 | Re
| PE | OL1-2G30-5630 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5630 - CT AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-20 |  | 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-02-11 | 2019-02-11 | 2019-03-04 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00982 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-27 | 2019-03-27 | 2019-03-13 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R1 | R1
| PE | OL1-2G30-5631 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5631 - CWWT AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-20 |  | 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-02-11 | 2019-02-11 | 2019-03-04 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00982 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-27 | 2019-03-27 | 2019-03-13 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R1 | R1
| PE | OL1-2G30-5632 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5632 - HP FLARE AREA OILY WASTEWATER SUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-20 |  | 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-02-11 | 2019-02-11 | 2019-03-04 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00982 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-27 | 2019-03-27 | 2019-03-13 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R1 | R1
| PE | OL1-2G30-5633 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5633 - HP FLARE AREA STORMWATER SUMP |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-12-20 |  | 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-11 | 2019-03-01 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00636 | TPSK-LSPA1-T-PE-00636 | TPSK-LSPA1-T-PE-00960 | TPSK-LSPA1-T-PE-00960
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-14 | 2019-03-14
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5635 | PROCESS EQUIPMENT DATA SHEET - 10-P-5630 - CT AREA OILY WASTEWATER PUMPS |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-03 | 2019-01-30 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-05 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-5636 | PROCESS EQUIPMENT DATA SHEET - 10-P-5631 - CWWT AREA OILY WASTEWATER PUMPS |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-03 | 2019-01-30 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-05 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-5637 | PROCESS EQUIPMENT DATA SHEET - 10-P-5632 - HP FLARE AREA OILY WASTEWATER SUMP PUMPS |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-03 | 2019-03-11 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00576 | TPSK-LSPA1-T-PE-00576 | TPSK-LSPA1-T-PE-01019 | TPSK-LSPA1-T-PE-01019
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-27 | 2019-03-27
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-5638 | PROCESS EQUIPMENT DATA SHEET - 10-P-5633 - HP FLARE AREA STORMWATER SUMP PUMPS |  | Class 1 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD; B: IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-03 | 2019-03-11 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00576 | TPSK-LSPA1-T-PE-00576 | TPSK-LSPA1-T-PE-01019 | TPSK-LSPA1-T-PE-01019
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-27 | 2019-03-27
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-5640 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5640 - OILY WASTEWATER EQUALIZATION TANKS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-02-06 | 2019-03-27 | 2019-03-28 | 2019-06-19 | 2019-06-19 | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00809 | TPSK-LSPA1-T-PE-00809 | TPSK-LSPA1-T-PE-01176 | TPSK-LSPA1-T-PE-01176 | TPSK-LSPA1-T-PE-01920 | TPSK-LSPA1-T-PE-01920 | TPSK-LSPA1-T-PE-02378
[6 empty] | Return Date | 2019-03-15 | 2019-03-15 | 2019-04-22 | 2019-04-22 | 2019-07-15 | 2019-07-15
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R2 | R2 | R2
| PE | OL1-2G30-5641 | PROCESS EQUIPMENT DATA SHEET - 10-P-5641 - WASTEWATER EQ TANK SKIMMED OIL PUMP |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-02-06 | 2019-03-25 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01152 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-03-15 | 2019-03-15 | 2019-04-12 | 2019-04-12
[6 empty] | Owner Cmmt* | R2 | R2 | CL | CL
| PE | OL1-2G30-5642 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5642 - COOLING WATER BLOWDOWN BASIS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2018-12-20 |  | 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-02-06 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00808 | TPSK-LSPA1-T-PE-00808 | TPSK-LSPA1-T-PE-01511 | TPSK-LSPA1-T-PE-01511
[6 empty] | Return Date | 2019-03-15 | 2019-03-15 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5643 | PROCESS EQUIPMENT DATA SHEET - 10-P-5642 - COOLING WATER BD BASIN PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-02-06 | 2019-05-01 | 2019-05-02 | 2019-06-25 | 2019-06-25 | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01543 | TPSK-LSPA1-T-PE-01543 | TPSK-LSPA1-T-PE-01981 | TPSK-LSPA1-T-PE-01981 | TPSK-LSPA1-T-PE-02377
[6 empty] | Return Date | 2019-03-15 | 2019-03-15 | 2019-06-17 | 2019-06-17 | 2019-07-17 | 2019-07-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R2 | R2
| PE | OL1-2G30-5644 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5644 - WASTE WATER CPI / IGF PACKAGE |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D | E | F
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-06 |  | 2018-12-07 | 2019-02-01 | 2019-02-04 | 2019-05-07 | 2019-05-08 | 2019-07-23 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00281 | TPSK-LSPA1-T-PE-00281 | TPSK-LSPA1-T-PE-00442 | TPSK-LSPA1-T-PE-00442 | TPSK-LSPA1-T-PE-00797 | TPSK-LSPA1-T-PE-00797 | TPSK-LSPA1-T-PE-01606 | TPSK-LSPA1-T-PE-01606 | TPSK-LSPA1-T-PE-02214 | TPSK-LSPA1-T-PE-02327
[6 empty] | Return Date | 2018-11-26 | 2018-11-26 | 2019-01-04 | 2019-01-04 | 2019-03-04 | 2019-03-04 | 2019-06-19 | 2019-06-19 | 2019-08-15
Owner Cmmt* | bar: 2018-11-26 to 2019-08-15
| PE | OL1-2G30-5645 | PROCESS EQUIPMENT DATA SHEET - 10-P-5640 - OILY WASTEWATER EQ TANK PUMPS |  | Class 1 | Purpose** | 2018-11-26: IFR; 2018-11-26: IFR; 2019-01-04: IFD; 2019-01-04: IFD
Rev. | bar: 2018-11-26 to 2019-01-04
[6 empty] | Issue Plan | 2018-11-26: 2019-03-11; 2019-01-04: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-26: 2019-02-06; 2018-11-26: 2019-02-06; 2019-01-04: 2019-03-27; 2019-01-04: 2019-03-28
[6 empty] | Transmittal no. | 2018-11-26: TPSK-LSPA1-T-PE-00810; 2018-11-26: TPSK-LSPA1-T-PE-00810; 2019-01-04: TPSK-LSPA1-T-PE-01177; 2019-01-04: TPSK-LSPA1-T-PE-01177
[6 empty] | Return Date | 2018-11-26: 2019-03-15; 2018-11-26: 2019-03-15
Owner Cmmt* | bar: 2018-11-26 to 2018-11-26
| PE | OL1-2G30-5646 | Process Equipment Datasheet - 10-PIT-5606 - C3 Hydrog Area Oily Wastewater Sump |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-11-26: 2018-12-20; 2019-01-04: 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2018-11-26: 2019-01-07; 2019-01-04: 2019-02-07; 2019-01-04: 2019-02-07; 2019-03-04: 2019-03-04; 2019-03-04: 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-27 | 2019-03-27 | 2019-03-13 | 2019-03-13
Owner Cmmt* | bar: 2018-11-26 to 2019-03-04
| PE | OL1-2G30-5647 | Process Equipment Datasheet - 10-PIT-5607 - Flare KO Drum Oily Wastewater Sump |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | CAN | CAN
[6 empty] | Rev. | A | A | B | B | C | C | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  | 2019-01-07 | 2019-02-07 | 2019-02-07 | 2019-03-04 | 2019-03-05 | 2019-05-09 | 2019-05-10
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-02-07 | 2019-02-07 | 2019-03-04 | 2019-03-05 | 2019-05-09 | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982 | TPSK-LSPA1-T-PE-00982 | TPSK-LSPA1-T-PE-01630 | TPSK-LSPA1-T-PE-01630
[6 empty] | Return Date | 2019-02-04 | 2019-02-04 | 2019-03-27 | 2019-03-27 | 2019-03-13 | 2019-03-13 | 2019-06-04 | 2019-06-04
Owner Cmmt* | bar: 2018-11-26 to 2019-06-19
| PE | OL1-2G30-5648 | Process Equipment Datasheet - 10-P-5606 A-B - C3 Hydrog Area Oily Wastewater Pump |  | Class 2 | Purpose** | 2018-11-26: IFR; 2018-11-26: IFR; 2019-01-04: IFD; 2019-01-04: IFD
Rev. | bar: 2018-11-26 to 2019-01-04
[6 empty] | Issue Plan | 2018-11-26: 2019-03-11; 2019-01-04: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-26: 2019-01-03; 2019-01-04: 2019-01-30; 2019-01-04: 2019-01-31
[6 empty] | Transmittal no. | 2018-11-26: TPSK-LSPA1-T-PE-00572; 2018-11-26: TPSK-LSPA1-T-PE-00572; 2019-01-04: TPSK-LSPA1-T-PE-00774; 2019-01-04: TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2018-11-26: 2019-01-22; 2018-11-26: 2019-01-22; 2019-01-04: 2019-03-05; 2019-01-04: 2019-03-05
Owner Cmmt* | bar: 2018-11-26 to 2019-01-04
| PE | OL1-2G30-5649 | Process Equipment Datasheet - 10-P-5607 A-B - Flare KO Drum Oily Wastewater Pump |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | CAN | CAN
[6 empty] | Rev. | A | A | B | B | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2018-11-26: 2019-01-03; 2019-01-04: 2019-01-31; 2019-01-04: 2019-02-01; 2019-03-04: 2019-05-09; 2019-03-04: 2019-05-10
[6 empty] | Issue Actual | 2018-11-26: 2019-01-03; 2019-01-04: 2019-01-31; 2019-01-04: 2019-02-01; 2019-03-04: 2019-05-09; 2019-03-04: 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00779 | TPSK-LSPA1-T-PE-00779 | TPSK-LSPA1-T-PE-01631 | TPSK-LSPA1-T-PE-01631
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-04 | 2019-03-04 | 2019-06-04 | 2019-06-04
Owner Cmmt* | bar: 2018-11-26 to 2019-03-04
| PE | OL1-2G30-5650 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5650 - BIO TREATMENT UNIT |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D | E | F
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-06 |  | 2018-12-07 | 2019-02-01 | 2019-02-04 | 2019-05-07 | 2019-05-08 | 2019-07-23 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00281 | TPSK-LSPA1-T-PE-00281 | TPSK-LSPA1-T-PE-00442 | TPSK-LSPA1-T-PE-00442 | TPSK-LSPA1-T-PE-00797 | TPSK-LSPA1-T-PE-00797 | TPSK-LSPA1-T-PE-01606 | TPSK-LSPA1-T-PE-01606 | TPSK-LSPA1-T-PE-02214 | TPSK-LSPA1-T-PE-02327
[6 empty] | Return Date | 2018-11-26 | 2018-11-26 | 2019-01-04 | 2019-01-04 | 2019-03-04 | 2019-03-04 | 2019-06-19 | 2019-06-19 | 2019-08-15
Owner Cmmt* | bar: 2018-11-26 to 2019-08-15
| PE | OL1-2G30-5652 | Process Equipment Datasheet - 10-P-5653 - Bio Equalization Pit Sludge Pump |  | Class 2 | Purpose** | 2018-11-26: IFR; 2018-11-26: IFR; 2019-01-04: IFD; 2019-01-04: IFD; 2019-03-04: IFD
[6 empty] | Rev. | 2018-11-26: A; 2018-11-26: A; 2019-01-04: B; 2019-01-04: B; 2019-03-04: C
[6 empty] | Issue Plan | 2018-11-26: 2019-03-11; 2019-01-04: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-26: 2019-05-30; 2018-11-26: 2019-05-31; 2019-01-04: 2019-06-25; 2019-01-04: 2019-06-25; 2019-03-04: 2019-08-08
[6 empty] | Transmittal no. | 2018-11-26: TPSK-LSPA1-T-PE--01775; 2018-11-26: TPSK-LSPA1-T-PE--01775; 2019-01-04: TPSK-LSPA1-T-PE-01981; 2019-01-04: TPSK-LSPA1-T-PE-01981; 2019-03-04: TPSK-LSPA1-T-PE-02377
[6 empty] | Return Date | 2018-11-26: 2019-06-21; 2019-01-04: 2019-07-17; 2019-01-04: 2019-07-17
Owner Cmmt* | bar: 2018-11-26 to 2019-01-04
| PE | OL1-2G30-5653 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5655 - WASTEWATER DUAL MEDIA FILTERS PKG |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D | E | F
[6 empty] | Issue Plan | 2018-12-20 |  | 2019-01-07
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-06 |  | 2018-12-07 | 2019-02-01 | 2019-02-04 | 2019-05-07 | 2019-05-08 | 2019-07-23 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00282 | TPSK-LSPA1-T-PE-00282 | TPSK-LSPA1-T-PE-00441 | TPSK-LSPA1-T-PE-00441 | TPSK-LSPA1-T-PE-00798 | TPSK-LSPA1-T-PE-00798 | TPSK-LSPA1-T-PE-01607 | TPSK-LSPA1-T-PE-01607 | TPSK-LSPA1-T-PE-02214 | TPSK-LSPA1-T-PE-02327
[6 empty] | Return Date | 2018-11-26 | 2018-11-26 | 2019-01-04 | 2019-01-04 | 2019-03-11 | 2019-03-11 | 2019-06-19 | 2019-06-19 | 2019-08-15
Owner Cmmt* | bar: 2018-11-26 to 2019-08-15
| PE | OL1-2G30-5654 | PROCESS EQUIPMENT DATA SHEET - 10-P-5655 - EQUALIZATION PIT PUMPS |  | Class 1 | Purpose** | 2018-11-26: IFR; 2018-11-26: IFR; 2019-01-04: IFD; 2019-01-04: IFD
Rev. | bar: 2018-11-26 to 2019-01-04
[6 empty] | Issue Plan | 2018-11-26: 2019-03-11; 2019-01-04: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-26: 2019-02-06; 2018-11-26: 2019-02-06; 2019-01-04: 2019-03-25; 2019-01-04: 2019-03-26
[6 empty] | Transmittal no. | 2018-11-26: TPSK-LSPA1-T-PE-00810; 2018-11-26: TPSK-LSPA1-T-PE-00810; 2019-01-04: TPSK-LSPA1-T-PE-01152; 2019-01-04: TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2018-11-26: 2019-03-15; 2018-11-26: 2019-03-15; 2019-01-04: 2019-04-12; 2019-01-04: 2019-04-12
Owner Cmmt* | bar: 2018-11-26 to 2019-01-04
| PE | OL1-2G30-5655 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5655 - EQUALIZATION PIT |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-11-26: 2018-12-20; 2019-01-04: 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-02-06 | 2019-03-27 | 2019-03-28 | 2019-06-25 | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00808 | TPSK-LSPA1-T-PE-00808 | TPSK-LSPA1-T-PE-01178 | TPSK-LSPA1-T-PE-01178 | TPSK-LSPA1-T-PE-01981 | TPSK-LSPA1-T-PE-01981
[6 empty] | Return Date | 2019-03-15 | 2019-03-15 | 2019-05-09 | 2019-05-09 | 2019-07-17 | 2019-07-17
Owner Cmmt* | bar: 2018-11-26 to 2019-03-11
| PE | OL1-2G30-5656 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5656 - FINAL CHECK BASIN |  | Class 1 | Purpose** | 2018-11-26: IFR; 2018-11-26: IFR; 2019-01-04: IFD; 2019-01-04: IFD
Rev. | bar: 2018-11-26 to 2019-01-04
[6 empty] | Issue Plan | 2018-11-26: 2018-12-20; 2019-01-04: 2019-01-07
Revised Plan
[6 empty] | Issue Actual | 2018-11-26: 2019-02-06; 2018-11-26: 2019-02-06; 2019-01-04: 2019-03-27; 2019-01-04: 2019-03-28
[6 empty] | Transmittal no. | 2018-11-26: TPSK-LSPA1-T-PE-00808; 2018-11-26: TPSK-LSPA1-T-PE-00808; 2019-01-04: TPSK-LSPA1-T-PE-01178; 2019-01-04: TPSK-LSPA1-T-PE-01178
[6 empty] | Return Date | 2018-11-26: 2019-03-15; 2018-11-26: 2019-03-15; 2019-01-04: 2019-06-04; 2019-01-04: 2019-06-04
Owner Cmmt* | bar: 2018-11-26 to 2019-01-04
| PE | OL1-2G30-5657 | PROCESS EQUIPMENT DATA SHEET - 10-P-5656 - FINAL CHECK BASIN PUMPS |  | Class 1 | Purpose** | 2018-11-26: IFR; 2018-11-26: IFR; 2019-01-04: IFD; 2019-01-04: IFD
Rev. | bar: 2018-11-26 to 2019-01-04
[6 empty] | Issue Plan | 2018-11-26: 2019-03-11; 2019-01-04: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-26: 2019-02-06; 2018-11-26: 2019-02-06; 2019-01-04: 2019-04-26; 2019-01-04: 2019-04-29
[6 empty] | Transmittal no. | 2018-11-26: TPSK-LSPA1-T-PE-00810; 2018-11-26: TPSK-LSPA1-T-PE-00810; 2019-01-04: TPSK-LSPA1-T-PE-01512; 2019-01-04: TPSK-LSPA1-T-PE-01512
[6 empty] | Return Date | 2018-11-26: 2019-03-15; 2018-11-26: 2019-03-15; 2019-01-04: 2019-06-17; 2019-01-04: 2019-06-17
Owner Cmmt* | bar: 2018-11-26 to 2019-01-04
| PE | OL1-2G30-5670 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5670 - DEWATERING PACKAGE |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D | E | F
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-06 |  | 2018-12-07 | 2019-02-01 | 2019-02-04 | 2019-05-07 | 2019-05-08 | 2019-07-23 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00281 | TPSK-LSPA1-T-PE-00281 | TPSK-LSPA1-T-PE-00442 | TPSK-LSPA1-T-PE-00442 | TPSK-LSPA1-T-PE-00797 | TPSK-LSPA1-T-PE-00797 | TPSK-LSPA1-T-PE-01606 | TPSK-LSPA1-T-PE-01606 | TPSK-LSPA1-T-PE-02214 | TPSK-LSPA1-T-PE-02327
[6 empty] | Return Date | 2018-11-26 | 2018-11-26 | 2019-01-04 | 2019-01-04 | 2019-03-04 | 2019-03-04 | 2019-06-19 | 2019-06-19 | 2019-08-15
Owner Cmmt* | bar: 2018-11-26 to 2019-08-15
| PE | OL1-2G30-5674 | PROCESS EQUIPMENT DATA SHEET - 10-P-5675 - SLOP OIL TRANSFER PUMPS |  | Class 1 | Purpose** | 2018-11-26: IFR; 2018-11-26: IFR; 2019-01-04: IFD; 2019-01-04: IFD
Rev. | bar: 2018-11-26 to 2019-01-04
[6 empty] | Issue Plan | 2018-11-26: 2019-03-11; 2019-01-04: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2018-11-26: 2019-02-06; 2018-11-26: 2019-02-06; 2019-01-04: 2019-03-25; 2019-01-04: 2019-03-26
[6 empty] | Transmittal no. | 2018-11-26: TPSK-LSPA1-T-PE-00810; 2018-11-26: TPSK-LSPA1-T-PE-00810; 2019-01-04: TPSK-LSPA1-T-PE-01152; 2019-01-04: TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2018-11-26: 2019-03-15; 2018-11-26: 2019-03-15; 2019-01-04: 2019-04-12; 2019-01-04: 2019-04-12
Owner Cmmt* | bar: 2018-11-26 to 2019-01-04
| PE | OL1-2G30-5675 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5675 - SLOP OIL TANKS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-02-06 | 2019-03-27 | 2019-03-28 | 2019-06-19 | 2019-06-19 | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00809 | TPSK-LSPA1-T-PE-00809 | TPSK-LSPA1-T-PE-01176 | TPSK-LSPA1-T-PE-01176 | TPSK-LSPA1-T-PE-01920 | TPSK-LSPA1-T-PE-01920 | TPSK-LSPA1-T-PE-02377
[6 empty] | Return Date | 2019-03-15 | 2019-03-15 | 2019-04-22 | 2019-04-22 | 2019-07-15 | 2019-07-15
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R2 | R2
| PE | OL1-2G30-5676 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5676 - OILY SLUDGE TANK |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D
Issue Plan
[6 empty] | Revised Plan | 2019-02-06 | 2019-02-06 | 2019-03-27 | 2019-03-28 | 2019-06-19 | 2019-06-19 | 2019-08-08
[6 empty] | Issue Actual | 2019-02-06 | 2019-02-06 | 2019-03-27 | 2019-03-28 | 2019-06-19 | 2019-06-19 | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00809 | TPSK-LSPA1-T-PE-00809 | TPSK-LSPA1-T-PE-01176 | TPSK-LSPA1-T-PE-01176 | TPSK-LSPA1-T-PE-01920 | TPSK-LSPA1-T-PE-01920 | TPSK-LSPA1-T-PE-02377
[6 empty] | Return Date | 2019-03-15 | 2019-03-15 | 2019-04-22 | 2019-04-22 | 2019-07-15 | 2019-07-15
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R2 | R2
| PE | OL1-2G30-5677 | PROCESS EQUIPMENT DATA SHEET - 10-P-5676 - OILY SLUDGE TRANSFER PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-02-06 | 2019-02-06 | 2019-03-25 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01152 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-03-15 | 2019-03-15 | 2019-04-12 | 2019-04-12
[6 empty] | Owner Cmmt* | R2 | R2 | CL | CL
| PE | OL1-2G30-5690 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5690 - SLOP TANK POLYMER INJECTION PKG |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual | 2019-02-07 | 2019-02-07 | 2019-04-08 | 2019-04-09 | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00821 | TPSK-LSPA1-T-PE-00821 | TPSK-LSPA1-T-PE-01274 | TPSK-LSPA1-T-PE-01274 | TPSK-LSPA1-T-PE-02214
[6 empty] | Return Date | 2019-03-14 | 2019-03-14 | 2019-05-16 | 2019-05-16 | 2019-08-15
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R2 | R2
| PE | OL1-2G30-5691 | Process Equipment Datasheet - 10-PK-5691 - Slop Tank Acid Injection Pkg |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | CAN | CAN
[6 empty] | Rev. | A | A | B | B | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-07 | 2019-02-07 | 2019-04-08 | 2019-04-09 | 2019-05-09 | 2019-05-10
[6 empty] | Issue Actual | 2019-02-07 | 2019-02-07 | 2019-04-08 | 2019-04-09 | 2019-05-09 | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00821 | TPSK-LSPA1-T-PE-00821 | TPSK-LSPA1-T-PE-01274 | TPSK-LSPA1-T-PE-01274 | TPSK-LSPA1-T-PE-01628 | TPSK-LSPA1-T-PE-01628
[6 empty] | Return Date | 2019-03-14 | 2019-03-14 | 2019-05-16 | 2019-05-16 |  | 2019-06-25
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R2 |  | R2
| PE | OL1-2G30-5695 | Process Equipment Datasheet - 10-PK-5695 - Bio Treat Sulfuric Acid Inj Pkg |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
[6 empty] | Revised Plan |  |  | 2019-08-16
[6 empty] | Issue Actual | 2019-05-09 | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01629 | TPSK-LSPA1-T-PE-01629
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5698 | Process Equipment Datasheet - 10-PK-5698 - Bio Treat Caustic Inj Pkg |  | Class 2 | Rev.: Purpose**; A: IFR; A: IFR; B: IFD
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
[6 empty] | Revised Plan |  |  | 2019-08-16
[6 empty] | Issue Actual | 2019-05-09 | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01629 | TPSK-LSPA1-T-PE-01629
[6 empty] | Return Date | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-5900 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5900 - SULFURIC ACID TANK |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-26 |  | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00364 | TPSK-LSPA1-T-PE-00364 | TPSK-LSPA1-T-PE-00647 | TPSK-LSPA1-T-PE-00647
[6 empty] | Return Date | 2018-12-17 | 2018-12-17 | 2019-02-04 | 2019-02-04
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5901 | PROCESS EQUIPMENT DATA SHEET - 10-P-5900 - SULFURIC ACID PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-28 | 2019-03-27 | 2019-03-28 | 2019-05-16 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00738 | TPSK-LSPA1-T-PE-00738 | TPSK-LSPA1-T-PE-01177 | TPSK-LSPA1-T-PE-01177 | TPSK-LSPA1-T-PE-01678 | TPSK-LSPA1-T-PE-01678
[6 empty] | Return Date | 2019-03-04 | 2019-03-04 | 2019-05-09 | 2019-05-09 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R2 | Re
| PE | OL1-2G30-5902 | Process Equipment Datasheet - 10-P-5901 A-B - Sulfuric Acid Metering Pumps |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-27 | 2019-01-30 | 2019-01-31 | 2019-03-21 | 2019-03-22 | 2019-04-11 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01129 | TPSK-LSPA1-T-PE-01129 | TPSK-LSPA1-T-PE-01323 | TPSK-LSPA1-T-PE-01323
[6 empty] | Return Date | 2019-01-24 | 2019-01-24 | 2019-03-05 | 2019-03-05 | 2019-04-04 | 2019-04-04 | 2019-05-16 | 2019-05-16
Owner Cmmt* | bar: 2019-01-24 to 2019-05-16
| PE | OL1-2G30-5905 | Process Equipment Datasheet - 10-P-5905 A-B - CTU Sulfuric Acid Metering Pumps |  | Class 2 | Purpose** | IFR | IFD | IFD | IFD | IFD
Rev. | bar: 2019-01-24 to 2019-04-04
[6 empty] | Issue Plan | 2019-01-24: 2019-03-11; 2019-01-24: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-24: 2019-03-21; 2019-03-05: 2019-03-22; 2019-03-05: 2019-04-11; 2019-04-04: 2019-04-12
[6 empty] | Transmittal no. | 2019-01-24: TPSK-LSPA1-T-PE-01129; 2019-03-05: TPSK-LSPA1-T-PE-01129; 2019-03-05: TPSK-LSPA1-T-PE-01323; 2019-04-04: TPSK-LSPA1-T-PE-01323
[6 empty] | Return Date | 2019-01-24: 2019-04-04; 2019-03-05: 2019-04-04; 2019-03-05: 2019-05-16; 2019-04-04: 2019-05-16
Owner Cmmt* | bar: 2019-01-24 to 2019-04-04
| PE | OL1-2G30-5910 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5910 - OXYGEN SCAVENGER INJ PKG |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D | E
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-10 |  | 2019-01-25 | 2019-03-14 | 2019-03-15 | 2019-03-20 | 2019-03-21 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00456 | TPSK-LSPA1-T-PE-00456 | TPSK-LSPA1-T-PE-00727 | TPSK-LSPA1-T-PE-00727 | TPSK-LSPA1-T-PE-01063 | TPSK-LSPA1-T-PE-01063 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-02198
[6 empty] | Return Date | 2019-01-04 | 2019-01-04 | 2019-03-04 | 2019-03-04 | 2019-04-02 | 2019-04-02 | 2019-04-10 | 2019-04-10 | 2019-08-06
Owner Cmmt* | bar: 2019-01-04 to 2019-08-06
| PE | OL1-2G30-5912 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5912 - NEUTRALIZING AMINE INHIBITOR INJ PKG |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D | E
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-10 |  | 2019-01-25 | 2019-03-14 | 2019-03-15 | 2019-03-20 | 2019-03-21 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00456 | TPSK-LSPA1-T-PE-00456 | TPSK-LSPA1-T-PE-00727 | TPSK-LSPA1-T-PE-00727 | TPSK-LSPA1-T-PE-01063 | TPSK-LSPA1-T-PE-01063 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-02198
[6 empty] | Return Date | 2019-01-04 | 2019-01-04 | 2019-03-04 | 2019-03-04 | 2019-04-02 | 2019-04-02 | 2019-04-10 | 2019-04-10 | 2019-08-06
Owner Cmmt* | bar: 2019-01-04 to 2019-08-06
| PE | OL1-2G30-5914 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5914 - PHOSPHATE INJECTION PACKAGE |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D | E
[6 empty] | Issue Plan | 2018-12-13 |  | 2019-01-10
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-10 |  | 2019-01-28 | 2019-03-14 | 2019-03-15 | 2019-03-20 | 2019-03-21 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00456 | TPSK-LSPA1-T-PE-00456 | TPSK-LSPA1-T-PE-00739 | TPSK-LSPA1-T-PE-00739 | TPSK-LSPA1-T-PE-01063 | TPSK-LSPA1-T-PE-01063 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-02198
[6 empty] | Return Date | 2019-01-04 | 2019-01-04 | 2019-03-04 | 2019-03-04 | 2019-04-02 | 2019-04-02 | 2019-04-10 | 2019-04-10 | 2019-08-06
Owner Cmmt* | bar: 2019-01-04 to 2019-08-06
| PE | OL1-2G30-5950 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5950 - SODIUM HYPOCHLORITE TANK |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-04 | 2019-03-14 | 2019-03-15 | 2019-04-04 | 2019-04-05 | 2019-05-16 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00406 | TPSK-LSPA1-T-PE-00406 | TPSK-LSPA1-T-PE-01055 | TPSK-LSPA1-T-PE-01055 | TPSK-LSPA1-T-PE-01258 | TPSK-LSPA1-T-PE-01258 | TPSK-LSPA1-T-PE-01679 | TPSK-LSPA1-T-PE-01679
[6 empty] | Return Date | 2019-01-22 | 2019-01-22 | 2019-03-29 | 2019-03-29 | 2019-05-09 | 2019-05-09 | 2019-06-04 | 2019-06-04
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G30-5951 | PROCESS EQUIPMENT DATA SHEET - 10-P-5950 - SODIUM HYPOCHLORITE METERING PUMPS |  | Class 1 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-03-29: 2019-04-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-27 | 2019-03-21 | 2019-03-22 | 2019-04-11 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-01129 | TPSK-LSPA1-T-PE-01129 | TPSK-LSPA1-T-PE-01323 | TPSK-LSPA1-T-PE-01323
[6 empty] | Return Date | 2019-01-24 | 2019-01-24 | 2019-04-04 | 2019-04-04 | 2019-05-16 | 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-05-09
| PE | OL1-2G30-5955 | Process Equipment Datasheet - 10-P-5955 A-B - CTU NaOCL Metering Pumps |  | Class 2 | Purpose** | IFR | IFD | IFD | IFD | IFD
Rev. | bar: 2019-01-22 to 2019-05-09
[6 empty] | Issue Plan | 2019-01-22: 2019-03-11; 2019-01-22: 2019-04-01
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-03-21; 2019-03-29: 2019-03-22; 2019-03-29: 2019-04-11; 2019-05-09: 2019-04-12
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01129; 2019-03-29: TPSK-LSPA1-T-PE-01129; 2019-03-29: TPSK-LSPA1-T-PE-01323; 2019-05-09: TPSK-LSPA1-T-PE-01323
[6 empty] | Return Date | 2019-01-22: 2019-04-04; 2019-03-29: 2019-04-04; 2019-03-29: 2019-05-16; 2019-05-09: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-05-09
| PE | OL1-2G30-6100 | Datasheet Cooling Water Basin Sluice Gates 10-Z-5301 A-I |  | Class 2 | Purpose** | 2019-01-22: IFR
Rev. | bar: 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-08-09
[6 empty] | Issue Actual | 2019-01-22: 2019-08-09
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02387
Return Date
Owner Cmmt*
| PE | OL1-2G30-6101 | Datasheet CTU Sump Sluice Gates Z-5302/Z-5303/Z-5304 |  | Class 2 | Purpose** | 2019-01-22: IFR
Rev. | bar: 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-08-09
[6 empty] | Issue Actual | 2019-01-22: 2019-08-09
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02387
Return Date
Owner Cmmt*
| PE | OL1-4G30-1001 | See document number 036909C-1011-PDS-0117-1101 or OL1-2G30-1101 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2018-10-01
[6 empty] | Issue Actual | 2019-01-22: 2018-10-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00117; 2019-01-22: TPSK-LSPA1-T-PE-00117
Return Date
Owner Cmmt*
| PE | OL1-4G30-1008 | See document number 036909C-1011-PDS-0630-1108 or OL1-2G30-1108 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2018-09-19
[6 empty] | Issue Actual | 2019-01-22: 2018-09-19
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00066; 2019-01-22: TPSK-LSPA1-T-PE-00066
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-4G30-1009 | See document number 036909C-1011-PDS-0610-1109 or OL1-2G30-1109 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2018-09-19
[6 empty] | Issue Actual | 2019-01-22: 2018-09-19
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00066; 2019-01-22: TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-1010 | See document number 036909C-1011-PDS-0610-1110 or OL1-2G30-1110 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2018-09-19
[6 empty] | Issue Actual | 2019-01-22: 2018-09-19
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00066; 2019-01-22: TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-1011 | See document number 036909C-1011-PDS-1040-1111 or OL1-2G30-1111 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2018-09-26; 2019-01-22: 2018-09-27
[6 empty] | Issue Actual | 2019-01-22: 2018-09-26; 2019-01-22: 2018-09-27
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00090; 2019-01-22: TPSK-LSPA1-T-PE-00090
[6 empty] | Return Date | 2019-01-22: 2018-10-12; 2019-01-22: 2018-10-12
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-4G30-2001 | See document number 036909C-1012-PDS-0117-1201 or OL1-2G30-1201 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2018-10-01
[6 empty] | Issue Actual | 2019-01-22: 2018-10-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00117; 2019-01-22: TPSK-LSPA1-T-PE-00117
Return Date
Owner Cmmt*
| PE | OL1-4G30-2008 | See document number 036909C-1012-PDS-0630-1208 or OL1-2G30-1208 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2018-09-19
[6 empty] | Issue Actual | 2019-01-22: 2018-09-19
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00066; 2019-01-22: TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-2009 | See document number 036909C-1012-PDS-0610-1209 or OL1-2G30-1209 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2018-09-19
[6 empty] | Issue Actual | 2019-01-22: 2018-09-19
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00066; 2019-01-22: TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-2011 | See document number 036909C-1012-PDS-1040-1211 or OL1-2G30-1211 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2018-09-26; 2019-01-22: 2018-09-27
[6 empty] | Issue Actual | 2019-01-22: 2018-09-26; 2019-01-22: 2018-09-27
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00090; 2019-01-22: TPSK-LSPA1-T-PE-00090
[6 empty] | Return Date | 2019-01-22: 2018-10-12; 2019-01-22: 2018-10-12
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
Category Code: G31 Process Instrument Data sheets
| PE | OL1-2G31-1001 | Process Data Sheet For Analyzers Feed Preparation - Area 10 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-10; 2019-01-22: 2019-05-13
[6 empty] | Issue Actual | 2019-01-22: 2019-05-10; 2019-01-22: 2019-05-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01634; 2019-01-22: TPSK-LSPA1-T-PE-01634
[6 empty] | Return Date | 2019-01-22: 2019-06-10; 2019-01-22: 2019-06-10
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G31-1101 | Process Data Sheet For Analyzers Recycle Gas Furnace - Area 11 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-10; 2019-01-22: 2019-05-13
[6 empty] | Issue Actual | 2019-01-22: 2019-05-10; 2019-01-22: 2019-05-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01634; 2019-01-22: TPSK-LSPA1-T-PE-01634
[6 empty] | Return Date | 2019-01-22: 2019-06-10; 2019-01-22: 2019-06-10
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G31-1102 | Process Data Sheet For CEMS - Area 11 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-06-12; 2019-01-22: 2019-06-14
[6 empty] | Issue Actual | 2019-01-22: 2019-06-12; 2019-01-22: 2019-06-14
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01875; 2019-01-22: TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date | 2019-01-22: 2019-07-09
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-1103 | Process Data Sheet For Pitot Tube On Cems Furnace Area 10-H-1100 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-06-12; 2019-01-22: 2019-06-14
[6 empty] | Issue Actual | 2019-01-22: 2019-06-12; 2019-01-22: 2019-06-14
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01875; 2019-01-22: TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date | 2019-01-22: 2019-07-09
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-1112 | ATTEMPERATOR DATA SHEET |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-29: IFF
Rev. | bar: 2019-01-22 to 2019-01-22
[6 empty] | Issue Plan | 2019-01-22: 2018-12-14; 2019-03-29: 2019-03-27
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-01-29
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00757; 2019-01-22: TPSK-LSPA1-T-PE-00757
[6 empty] | Return Date | 2019-01-22: 2019-02-26; 2019-01-22: 2019-02-26
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G31-1190 | Process Datasheet for Restriction Orifice Furnace Area 10-H-1100 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-06-07; 2019-01-22: 2019-06-10
[6 empty] | Issue Actual | 2019-01-22: 2019-06-07; 2019-01-22: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01830; 2019-01-22: TPSK-LSPA1-T-PE-01830
[6 empty] | Return Date | 2019-01-22: 2019-07-08
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-11YY | RESTRICTION ORIFICE DATA SHEETS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-12-20; 2019-01-22: 2019-01-07
[6 empty] | Revised Plan | 2019-01-22: 2019-08-19
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-1201 | Process Data Sheet For Analyzers Liquid Cracking Furnace - Area 12 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-10; 2019-01-22: 2019-05-13
[6 empty] | Issue Actual | 2019-01-22: 2019-05-10; 2019-01-22: 2019-05-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01634; 2019-01-22: TPSK-LSPA1-T-PE-01634
[6 empty] | Return Date | 2019-01-22: 2019-06-10; 2019-01-22: 2019-06-10
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G31-1202 | Process Data Sheet For CEMS - Area 12 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-06-12; 2019-01-22: 2019-06-14
[6 empty] | Issue Actual | 2019-01-22: 2019-06-12; 2019-01-22: 2019-06-14
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01875; 2019-01-22: TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date | 2019-01-22: 2019-07-09
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-1203 | Process Data Sheet For Pitot Tube On Cems Furnace Area 12-H-1200-1600 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-06-12; 2019-01-22: 2019-06-14
[6 empty] | Issue Actual | 2019-01-22: 2019-06-12; 2019-01-22: 2019-06-14
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01875; 2019-01-22: TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date | 2019-01-22: 2019-07-09
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-1212 | ATTEMPERATOR DATA SHEET |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-29: IFF
Rev. | bar: 2019-01-22 to 2019-01-22
[6 empty] | Issue Plan | 2019-01-22: 2018-12-14; 2019-03-29: 2019-03-27
Revised Plan
[6 empty] | Issue Actual | 2019-01-22: 2019-01-29
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00757; 2019-01-22: TPSK-LSPA1-T-PE-00757
[6 empty] | Return Date | 2019-01-22: 2019-02-26; 2019-01-22: 2019-02-26
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G31-1290 | Process Datasheet for Restriction Orifice Furnace Area 10-H-1200_1600 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-30; 2019-01-22: 2019-05-31
[6 empty] | Issue Actual | 2019-01-22: 2019-05-30; 2019-01-22: 2019-05-31
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01781; 2019-01-22: TPSK-LSPA1-T-PE-01781
[6 empty] | Return Date | 2019-01-22: 2019-06-21; 2019-01-22: 2019-06-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G31-12YY | RESTRICTION ORIFICE DATA SHEETS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-12-20; 2019-01-22: 2019-01-07
[6 empty] | Revised Plan | 2019-01-22: 2019-08-19
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-2001 | Process Data Sheet For Analyzers Quench Oil - Area 20 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-10; 2019-01-22: 2019-05-13
[6 empty] | Issue Actual | 2019-01-22: 2019-05-10; 2019-01-22: 2019-05-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01634; 2019-01-22: TPSK-LSPA1-T-PE-01634
[6 empty] | Return Date | 2019-01-22: 2019-06-10; 2019-01-22: 2019-06-10
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G31-2090 | Process Datasheet for Restriction Orifice - Area 20 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-07-03; 2019-01-22: 2019-07-03
[6 empty] | Issue Actual | 2019-01-22: 2019-07-03; 2019-01-22: 2019-07-03
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02061; 2019-01-22: TPSK-LSPA1-T-PE-02061
[6 empty] | Return Date | 2019-01-22: 2019-07-23
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-2101 | Process Data Sheet For Analyzer Quench Water - Dilution Steam - Area 21 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-10; 2019-01-22: 2019-05-13
[6 empty] | Issue Actual | 2019-01-22: 2019-05-10; 2019-01-22: 2019-05-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01634; 2019-01-22: TPSK-LSPA1-T-PE-01634
[6 empty] | Return Date | 2019-01-22: 2019-06-10; 2019-01-22: 2019-06-10
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G31-2190 | Process Datasheet for Restriction Orifice - Area 21 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-07-02; 2019-01-22: 2019-07-02
[6 empty] | Issue Actual | 2019-01-22: 2019-07-02; 2019-01-22: 2019-07-02
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02044; 2019-01-22: TPSK-LSPA1-T-PE-02044
[6 empty] | Return Date | 2019-01-22: 2019-07-23
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-2301 | Process Data Sheet For Analyzers Caustic - Area 23 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-10; 2019-01-22: 2019-05-13
[6 empty] | Issue Actual | 2019-01-22: 2019-05-10; 2019-01-22: 2019-05-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01637; 2019-01-22: TPSK-LSPA1-T-PE-01637
[6 empty] | Return Date | 2019-01-22: 2019-06-10; 2019-01-22: 2019-06-10
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G31-2401 | Data Sheet For Analyzers Dehydration - Regen - Deprop - C2 Hydrog - Area 24 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-14; 2019-01-22: 2019-05-15
[6 empty] | Issue Actual | 2019-01-22: 2019-05-14; 2019-01-22: 2019-05-15
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01664; 2019-01-22: TPSK-LSPA1-T-PE-01664
[6 empty] | Return Date | 2019-01-22: 2019-06-03; 2019-01-22: 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G31-2501 | Data Sheet For Analyzers Cold Fractionation - Area 25 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-14; 2019-01-22: 2019-05-15
[6 empty] | Issue Actual | 2019-01-22: 2019-05-14; 2019-01-22: 2019-05-15
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01664; 2019-01-22: TPSK-LSPA1-T-PE-01664
[6 empty] | Return Date | 2019-01-22: 2019-06-03; 2019-01-22: 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G31-2590 | Process Datasheet for Restriction Orifice Unit 25 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-06-28; 2019-01-22: 2019-06-28
[6 empty] | Issue Actual | 2019-01-22: 2019-06-28; 2019-01-22: 2019-06-28
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02018; 2019-01-22: TPSK-LSPA1-T-PE-02018
[6 empty] | Return Date | 2019-01-22: 2019-07-23
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-2601 | Process Data Sheet For Analyzers Hot Fractionantion - Area 26 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-20; 2019-01-22: 2019-05-21
[6 empty] | Issue Actual | 2019-01-22: 2019-05-20; 2019-01-22: 2019-05-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01693; 2019-01-22: TPSK-LSPA1-T-PE-01693
[6 empty] | Return Date | 2019-01-22: 2019-06-17; 2019-01-22: 2019-06-17
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G31-2690 | Process Datasheet for Restriction Orifice - Unit 26 |  | Class 2 | Purpose** | 2019-01-22: IFR
Rev. | bar: 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-08-05
[6 empty] | Issue Actual | 2019-01-22: 2019-08-05
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02338
Return Date
Owner Cmmt*
| PE | OL1-2G31-2701 | Process Data Sheet For Analyzers Ghu And C4 - C5 Hydrog - Area 27 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-20; 2019-01-22: 2019-05-21
[6 empty] | Issue Actual | 2019-01-22: 2019-05-20; 2019-01-22: 2019-05-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01693; 2019-01-22: TPSK-LSPA1-T-PE-01693
[6 empty] | Return Date | 2019-01-22: 2019-06-17; 2019-01-22: 2019-06-17
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G31-2790 | Process Datasheet for Restriction Orifice - Unit 27 |  | Class 2 | Purpose** | 2019-01-22: IFR
Rev. | bar: 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-08-05
[6 empty] | Issue Actual | 2019-01-22: 2019-08-05
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02338
Return Date
Owner Cmmt*
| PE | OL1-2G31-2801 | Process Data Sheet For Analyzers Refrigeration Sytem - Area 28 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-20; 2019-01-22: 2019-05-21
[6 empty] | Issue Actual | 2019-01-22: 2019-05-20; 2019-01-22: 2019-05-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01693; 2019-01-22: TPSK-LSPA1-T-PE-01693
[6 empty] | Return Date | 2019-01-22: 2019-06-17; 2019-01-22: 2019-06-17
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G31-2890 | Process Datasheet for Restriction Orifice Unit 28 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-06-28; 2019-01-22: 2019-06-28
[6 empty] | Issue Actual | 2019-01-22: 2019-06-28; 2019-01-22: 2019-06-28
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02018; 2019-01-22: TPSK-LSPA1-T-PE-02018
[6 empty] | Return Date | 2019-01-22: 2019-07-23
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-2901 | Process Data Sheet For Analyzers Ethylene Auxiliariers - Area 29 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-20; 2019-01-22: 2019-05-21
[6 empty] | Issue Actual | 2019-01-22: 2019-05-20; 2019-01-22: 2019-05-21
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01693; 2019-01-22: TPSK-LSPA1-T-PE-01693
[6 empty] | Return Date | 2019-01-22: 2019-06-17; 2019-01-22: 2019-06-17
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G31-2990 | Process Datasheet for Restriction Orifice Unit 29 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-06-28; 2019-01-22: 2019-06-28
[6 empty] | Issue Actual | 2019-01-22: 2019-06-28; 2019-01-22: 2019-06-28
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02018; 2019-01-22: TPSK-LSPA1-T-PE-02018
[6 empty] | Return Date | 2019-01-22: 2019-07-23
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-3001 | Process Data Sheet For Analyzers Butadiene Extraction Unit Bdu - Area 30 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-07-01; 2019-01-22: 2019-07-01
[6 empty] | Issue Actual | 2019-01-22: 2019-07-01; 2019-01-22: 2019-07-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02027; 2019-01-22: TPSK-LSPA1-T-PE-02027
[6 empty] | Return Date | 2019-01-22: 2019-07-18
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-3090 | Process Datasheet for Restriction Orifice Unit 30 |  | Class 2 | Purpose** | 2019-01-22: IFR
Rev. | bar: 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-08-15
[6 empty] | Issue Actual | 2019-01-22: 2019-08-15
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02436
Return Date
Owner Cmmt*
| PE | OL1-2G31-3190 | Process Datasheet for Restriction Orifice Unit 31 |  | Class 2 | Purpose** | 2019-01-22: IFR
Rev. | bar: 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-08-15
[6 empty] | Issue Actual | 2019-01-22: 2019-08-15
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02436
Return Date
Owner Cmmt*
| PE | OL1-2G31-3990 | Process Datasheet for Restriction Orifice Unit 39 |  | Class 2 | Purpose** | 2019-01-22: IFR
Rev. | bar: 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-08-15
[6 empty] | Issue Actual | 2019-01-22: 2019-08-15
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02436
Return Date
Owner Cmmt*
| PE | OL1-2G31-5101 | Process Data Sheeet For Analyzers BFW-Steam-Steam OCndensate System - Area 51 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-24; 2019-01-22: 2019-05-27
[6 empty] | Issue Actual | 2019-01-22: 2019-05-24; 2019-01-22: 2019-05-27
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01740; 2019-01-22: TPSK-LSPA1-T-PE-01740
Return Date
Owner Cmmt*
| PE | OL1-2G31-5190 | Process Datasheet for Restriction Orifice - Area 51 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-07-02; 2019-01-22: 2019-07-02
[6 empty] | Issue Actual | 2019-01-22: 2019-07-02; 2019-01-22: 2019-07-02
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02044; 2019-01-22: TPSK-LSPA1-T-PE-02044
[6 empty] | Return Date | 2019-01-22: 2019-07-23
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-5201 | Process Data Sheet For Analyzers Fuel System - Area 52 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-24; 2019-01-22: 2019-05-27
[6 empty] | Issue Actual | 2019-01-22: 2019-05-24; 2019-01-22: 2019-05-27
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01740; 2019-01-22: TPSK-LSPA1-T-PE-01740
Return Date
Owner Cmmt*
| PE | OL1-2G31-5301 | Process Data Sheet For Anaqlyzers Cooling Water - Area 53 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-05-24; 2019-01-22: 2019-05-27
[6 empty] | Issue Actual | 2019-01-22: 2019-05-24; 2019-01-22: 2019-05-27
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01740; 2019-01-22: TPSK-LSPA1-T-PE-01740
Return Date
Owner Cmmt*
| PE | OL1-2G31-5390 | Process Datasheet for Restriction Orifice Area 53 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-29: IFD
Rev. | bar: 2019-01-22 to 2019-01-22
[6 empty] | Issue Plan | 2019-01-22: 2019-04-18; 2019-03-29: 2019-05-16
[6 empty] | Revised Plan | 2019-03-29: 2019-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-06-28; 2019-01-22: 2019-06-28
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02018; 2019-01-22: TPSK-LSPA1-T-PE-02018
[6 empty] | Return Date | 2019-01-22: 2019-07-23
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-5501 | Data Sheet For Analyzers Vent Gas And Flare System - Area 55 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-06-06; 2019-01-22: 2019-06-10
[6 empty] | Issue Actual | 2019-01-22: 2019-06-06; 2019-01-22: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01816; 2019-01-22: TPSK-LSPA1-T-PE-01816
[6 empty] | Return Date | 2019-01-22: 2019-06-28
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-5590 | Process Datasheet for Restriction Orifice - Area 55 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-29: IFD
Rev. | bar: 2019-01-22 to 2019-01-22
[6 empty] | Issue Plan | 2019-01-22: 2019-04-18; 2019-03-29: 2019-05-16
[6 empty] | Revised Plan | 2019-03-29: 2019-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-07-02; 2019-01-22: 2019-07-02
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02044; 2019-01-22: TPSK-LSPA1-T-PE-02044
[6 empty] | Return Date | 2019-01-22: 2019-07-23
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-5601 | Data Sheet For Analyzers Wastewater - Area 56 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-06-06; 2019-01-22: 2019-06-10
[6 empty] | Issue Actual | 2019-01-22: 2019-06-06; 2019-01-22: 2019-06-10
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01816; 2019-01-22: TPSK-LSPA1-T-PE-01816
[6 empty] | Return Date | 2019-01-22: 2019-06-28
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-5690 | Process Datasheet for Restriction Orifice Area 56 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-29: IFD
Rev. | bar: 2019-01-22 to 2019-01-22
[6 empty] | Issue Plan | 2019-01-22: 2019-04-18; 2019-03-29: 2019-05-16
[6 empty] | Revised Plan | 2019-03-29: 2019-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-06-28; 2019-01-22: 2019-06-28
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02018; 2019-01-22: TPSK-LSPA1-T-PE-02018
[6 empty] | Return Date | 2019-01-22: 2019-07-23
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-5990 | Process Datasheet for Restriction Orifice Area 59 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-06-28; 2019-01-22: 2019-06-28
[6 empty] | Issue Actual | 2019-01-22: 2019-06-28; 2019-01-22: 2019-06-28
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02019; 2019-01-22: TPSK-LSPA1-T-PE-02019
[6 empty] | Return Date | 2019-01-22: 2019-07-23
Owner Cmmt* | bar: 2019-01-22
| PE | OL1-2G31-XXXA | AREA 30 RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFD
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2019-04-18; 2019-01-22: 2019-05-16
[6 empty] | Revised Plan | 2019-01-22: 2019-08-19; 2019-01-22: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-XXXX | RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFD
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2019-04-18; 2019-01-22: 2019-05-16
[6 empty] | Revised Plan | 2019-01-22: 2019-08-19; 2019-01-22: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G32 Process Safety Valve Data sheets
| PE | OL1-2G32-1101 | USC 36M Steam Drum PSV Datasheet - 10-PSV-1142A |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-29: IFD; 2019-03-29: IFD
Rev. | bar: 2019-01-22 to 2019-03-29
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-03-11; 2019-01-22: 2019-03-12; 2019-03-29: 2019-05-07; 2019-03-29: 2019-05-08
[6 empty] | Issue Actual | 2019-01-22: 2019-03-11; 2019-01-22: 2019-03-12; 2019-03-29: 2019-05-07; 2019-03-29: 2019-05-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01028; 2019-01-22: TPSK-LSPA1-T-PE-01028; 2019-03-29: TPSK-LSPA1-T-PE-01602; 2019-03-29: TPSK-LSPA1-T-PE-01602
[6 empty] | Return Date | 2019-01-22: 2019-04-02; 2019-01-22: 2019-04-02; 2019-03-29: 2019-05-31; 2019-03-29: 2019-05-31
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G32-1102 | USC 36M Steam Drum PSV Datasheet - 10-PSV-1142B |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-29: IFD; 2019-03-29: IFD
Rev. | bar: 2019-01-22 to 2019-03-29
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-03-11; 2019-01-22: 2019-03-12; 2019-03-29: 2019-05-07; 2019-03-29: 2019-05-08
[6 empty] | Issue Actual | 2019-01-22: 2019-03-11; 2019-01-22: 2019-03-12; 2019-03-29: 2019-05-07; 2019-03-29: 2019-05-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01028; 2019-01-22: TPSK-LSPA1-T-PE-01028; 2019-03-29: TPSK-LSPA1-T-PE-01602; 2019-03-29: TPSK-LSPA1-T-PE-01602
[6 empty] | Return Date | 2019-01-22: 2019-04-02; 2019-01-22: 2019-04-02; 2019-03-29: 2019-05-31; 2019-03-29: 2019-05-31
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G32-1103 | USC 36M Superheater Outlet PSV Datasheet - 10-PSV-1144 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-29: IFD; 2019-03-29: IFD
Rev. | bar: 2019-01-22 to 2019-03-29
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-03-11; 2019-01-22: 2019-03-12; 2019-03-29: 2019-05-07; 2019-03-29: 2019-05-08
[6 empty] | Issue Actual | 2019-01-22: 2019-03-11; 2019-01-22: 2019-03-12; 2019-03-29: 2019-05-07; 2019-03-29: 2019-05-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01028; 2019-01-22: TPSK-LSPA1-T-PE-01028; 2019-03-29: TPSK-LSPA1-T-PE-01602; 2019-03-29: TPSK-LSPA1-T-PE-01602
[6 empty] | Return Date | 2019-01-22: 2019-04-02; 2019-01-22: 2019-04-02; 2019-03-29: 2019-05-31; 2019-03-29: 2019-05-31
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G32-11XX | PRESSURE RELIEF VALVE DATA SHEETS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2019-01-18; 2019-01-22: 2019-06-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-1201 | USC 132U Steam Drum PSV Datasheet - 10-PSV-1242A |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-29: IFD; 2019-03-29: IFD
Rev. | bar: 2019-01-22 to 2019-03-29
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-03-11; 2019-01-22: 2019-03-12; 2019-03-29: 2019-05-07; 2019-03-29: 2019-05-08
[6 empty] | Issue Actual | 2019-01-22: 2019-03-11; 2019-01-22: 2019-03-12; 2019-03-29: 2019-05-07; 2019-03-29: 2019-05-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01029; 2019-01-22: TPSK-LSPA1-T-PE-01029; 2019-03-29: TPSK-LSPA1-T-PE-01603; 2019-03-29: TPSK-LSPA1-T-PE-01603
[6 empty] | Return Date | 2019-01-22: 2019-04-02; 2019-01-22: 2019-04-02; 2019-03-29: 2019-05-31; 2019-03-29: 2019-05-31
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G32-1202 | USC 132U Steam Drum PSV Datasheet - 10-PSV-1242B |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-29: IFD; 2019-03-29: IFD
Rev. | bar: 2019-01-22 to 2019-03-29
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-03-11; 2019-01-22: 2019-03-12; 2019-03-29: 2019-05-07; 2019-03-29: 2019-05-08
[6 empty] | Issue Actual | 2019-01-22: 2019-03-11; 2019-01-22: 2019-03-12; 2019-03-29: 2019-05-07; 2019-03-29: 2019-05-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01029; 2019-01-22: TPSK-LSPA1-T-PE-01029; 2019-03-29: TPSK-LSPA1-T-PE-01603; 2019-03-29: TPSK-LSPA1-T-PE-01603
[6 empty] | Return Date | 2019-01-22: 2019-04-02; 2019-01-22: 2019-04-02; 2019-03-29: 2019-05-31; 2019-03-29: 2019-05-31
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G32-1203 | USC 132U Superheater Outlet PSV Datasheet - 10-PSV-1244 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFR; 2019-03-29: IFD; 2019-03-29: IFD
Rev. | bar: 2019-01-22 to 2019-03-29
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-03-11; 2019-01-22: 2019-03-12; 2019-03-29: 2019-05-07; 2019-03-29: 2019-05-08
[6 empty] | Issue Actual | 2019-01-22: 2019-03-11; 2019-01-22: 2019-03-12; 2019-03-29: 2019-05-07; 2019-03-29: 2019-05-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01029; 2019-01-22: TPSK-LSPA1-T-PE-01029; 2019-03-29: TPSK-LSPA1-T-PE-01603; 2019-03-29: TPSK-LSPA1-T-PE-01603
[6 empty] | Return Date | 2019-01-22: 2019-04-02; 2019-01-22: 2019-04-02; 2019-03-29: 2019-05-31; 2019-03-29: 2019-05-31
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G32-12XX | PRESSURE RELIEF VALVE DATA SHEETS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2019-01-18; 2019-01-22: 2019-06-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-XXXA | AREA 30 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2019-05-06; 2019-01-22: 2019-09-15; 2019-03-29: 2020-04-15
[6 empty] | Revised Plan | 2019-01-22: 2019-08-19; 2019-01-22: 2019-09-15; 2019-03-29: 2020-04-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-XXXB | AREA 53 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2019-05-06; 2019-01-22: 2019-09-15; 2019-03-29: 2020-04-15
[6 empty] | Revised Plan | 2019-01-22: 2019-09-15; 2019-03-29: 2020-04-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-XXXC | AREA 55 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2019-05-06; 2019-01-22: 2019-09-15; 2019-03-29: 2020-04-15
[6 empty] | Revised Plan | 2019-01-22: 2019-09-15; 2019-03-29: 2020-04-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-XXXD | AREA 56 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2019-05-06; 2019-01-22: 2019-09-15; 2019-03-29: 2020-04-15
[6 empty] | Revised Plan | 2019-01-22: 2019-09-15; 2019-03-29: 2020-04-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-XXXE | PSV DATA SHEETS & INDEX & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-01-22: IFR; 2019-01-22: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2019-05-06; 2019-01-22: 2019-09-15; 2019-03-29: 2020-04-15
[6 empty] | Revised Plan | 2019-01-22: 2019-09-15; 2019-03-29: 2020-04-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G40 Block Flow Diagram
| PE | OL1-2G40-0010 | BLOCK FLOW DIAGRAM - OLEFINS UNIT 10 - OVERALL PLANT SCHEME |  | Class 2 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-10-10
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-19 | 2019-06-19
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
Category Code: G41 Process Flow Diagrams
| PE | OL1-2G41-0001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - GENERAL - LEGENDS & SYMBOLS |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-0002 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - GENERAL - DRAWING INDEX |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-1001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 10 FEED PREPARATION - FEED PREHEAT |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-1003 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 10 FEED PREPARATION - FEEDSTOCK DISTRIBUTION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-1101 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 11 FURNACES - RECYCLE GAS CRACKING FURNACE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-1201 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 12 FURNACES - LIQUID CRACKING FURNACE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-1901 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 19 FEED PREPARATION & FURNACES AUX - DECOKE AIR COMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-1902 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 19 FEED PREPARATION & FURNACES AUX - CHEMICAL STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 20 QUENCH OIL - QUENCH OIL TOWER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2002 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 20 QUENCH OIL - HEAVY FUEL OIL STRIPPER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2101 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 21 QUENCH WATER / DILUTION STEAM - QUENCH WATER TOWER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2102 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 21 QUENCH WATER / DILUTION STEAM - QUENCH WATER CIRCUIT |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2103 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 21 QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2201 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 22 CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2301 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - CAUSTIC TOWER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2302 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC HANDLING |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2303 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2304 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC TREATMENT |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2305 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - WET AIR OXIDATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-06-03 | 2019-06-03
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2401 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CG DEHYDRATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2402 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - REGENERATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2403 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2404 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2405 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2501 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2502 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - RESIDUE GAS SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2503 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - DEMETHANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2504 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - DEETHANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2505 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - ETHYLENE FRACTIONATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2506 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - HYDROGEN PURIFICATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2601 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - C3 HYDROGENATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2602 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - SECONDARY DEETHANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2603 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - PROPYLENE FRACTIONATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2604 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - DEBUTANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2701 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - GHU-1 REACTOR & DEPENTANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2702 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - GHU-1 RERUN TOWER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-11 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2703 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - HYDROG REACTIVATION GAS SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2704 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2801 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - PROPYLENE REFRIGERATION 1 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2802 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - PROPYLENE REFRIGERATION 2 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2803 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - ETHYLENE REFRIGERATION 1 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2804 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - ETHYLENE REFRIGERATION 2 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-2901 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 29 OLEFINS RECOVERY AUX - CHEMICAL STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-3001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU PREDISTILLATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-3002 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU EVAPORATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-3003 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU RECTIFIER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-3004 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU DEGASSING |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-3005 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU FRACTIONATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-3101 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 31 C4 UNIT UTILITIES - BDU SOLVENT REGENERATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-3102 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 31 C4 UNIT UTILITIES - BDU STEAM AND CONDENSATE SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G41-3901 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 39 C4 UNIT AUX - BDU CHEMICAL STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
Category Code: G42 Utility Flow Diagrams
| PE | OL1-2G42-5001 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 50 WATER SYSTEMS - TREATED, POTABLE, AND DEMIN WATER SYSTEMS |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5101 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - STEAM BALANCE DIAGRAM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5102 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - CONDENSATE AND BOILER FEEDWATER SYSTEMS |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5103 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - CONDENSATE TREATMENT SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5104 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - FURNACE BLOWDOWN SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5201 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 52 FUEL SYSTEM - FUEL GAS SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5301 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 53 COOLING WATER SYSTEM - COOLING WATER DIAGRAM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5311 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 53 COOLING WATER SYSTEM - COOLING TOWER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5401 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 54 AIR AND NITROGEN SYSTEM - PLANT AIR, INSTRUMENT AIR, AND NITROGEN SYSTEMS |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5501 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - FLARE AND BLOWDOWN SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5502 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - PROCESS VENT GAS COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5511 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - HP AND LLDPE LP FLARE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5512 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - ENCLOSED GROUND FLARE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5601 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OILY WASTEWATER COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5602 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SURFACE RUNOFF COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5603 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CRACKER HOLDING BASIN |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5604 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - DOMESTIC WASTEWATER COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5610 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - HP FLARE AREA STORMWATER AND OILY WASTEWATER COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5611 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OSBL OILY WASTEWATER COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5612 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OILY WASTEWATER EQUILIZATION TANK |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5613 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CPI & IGF PACKAGES |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5614 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - BIOTREATMENT PACKAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5615 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CHECK BASIN |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5616 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SLUDGE DEWATERING PACKAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5617 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SLOP AND OIL SLUDGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5901 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 59 UTILITIES AUX - CHEMICAL STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
| PE | OL1-2G42-5911 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 59 UTILITIES AUX - COMPLEX U & O CHEMICAL STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-01-22: 2018-08-27; 2019-03-29: 2019-06-20
[6 empty] | Revised Plan | 2019-01-22: 2018-08-23; 2019-03-29: 2018-08-24
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-08-24 | 2018-10-10 | 2018-10-11 | 2019-04-29 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-10-29 | 2018-12-27 | 2018-12-27 | 2019-05-29 | 2019-05-29
Owner Cmmt* | bar: 2019-01-22 to 2019-06-04
Category Code: G43 Process and Instrument Diagrams (P&ID)
| PE | OL1-2G43-0001 | P&ID - Olefins Unit 10 - Common - Abbreviations And Numbering |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-05-16 |  | 2019-05-16 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-01180; 2019-03-29: TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-0002 | P&ID - Olefins Unit 10 - Common - Piping Symbols |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-05-16 |  | 2019-05-16 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-01180; 2019-03-29: TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-0003 | P&ID - Olefins Unit 10 - Common - Instrumentation Symbols |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-05-16 |  | 2019-05-16 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-01180; 2019-03-29: TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-0004 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 1 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-05-16 |  | 2019-05-16 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-01180; 2019-03-29: TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-0005 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 2 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-05-16 |  | 2019-05-16 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-01180; 2019-03-29: TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-0010 | P&ID - Olefins Unit 10 - Common - Instrument Details |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-05-16 |  | 2019-05-16 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-01180; 2019-03-29: TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-0011 | P&ID - Olefins Unit 10 - Common - EIV Block Valves Typical |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-05-16 |  | 2019-05-16 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-01180; 2019-03-29: TPSK-LSPA1-T-PE-01180
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1001 | P&ID - FEED PREPARATION - FURNACE LIQUID FEED |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1002 | P&ID - FEED PREPARATION - FURNACE LPG FEED HEATER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1003 | P&ID - FEED PREPARATION - FURNACE LPG FEED VAPORIZER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1004 | P&ID - FEED PREPARATION - FURNACE LPG FEED SUPERHEATER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1005 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - LPG Steam Vaporizer |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1006 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - LPG Feed Steam Heater |  | Class As built | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-05-09: 2020-02-07; 2019-06-04: 2020-05-30; 2019-06-04: 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-03-27; 2019-03-29: 2019-03-28; 2019-03-29: 2019-08-14
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01180; 2019-03-29: TPSK-LSPA1-T-PE-01180; 2019-03-29: TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-05-05; 2019-03-29: 2019-05-05
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1023 | P&ID - FEED PREPARATION - C2 FEED SUPERHEATER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1030 | P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1031 | P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1035 | P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION (UTILITY) - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1036 | P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION (UTILITY) - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1090 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Naphtha Feed - C3 LPG Battery Limit |  | Class As built | Purpose** | 2019-01-22: IDD1
Rev. | bar: 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-08-14
[6 empty] | Issue Actual | 2019-01-22: 2019-08-14
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02403
Return Date
Owner Cmmt*
| PE | OL1-2G43-1101 | P&ID - RECYCLE GAS CRACKING FURNACE - ETHANE FEED DISTRIBUTION HEADER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1
[6 empty] | Rev. | A | A | B | B | C
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1105 | P&ID - RECYCLE GAS CRACKING FURNACE - DILUTION STEAM DISTRIBUTION HEADER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1106 | P&ID - RECYCLE GAS CRACKING FURNACE - DECOKE AIR HEADER DISTRIBUTION HEADER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1107 | P&ID - RECYCLE GAS CRACKING FURNACE - FEED- SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1108 | P&ID - RECYCLE GAS CRACKING FURNACE - FEED- SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1109 | P&ID - RECYCLE GAS CRACKING FURNACE - FEED- SHEET 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1110 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed-Sheet 4 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1111 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 5 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1112 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 6 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1115 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 CONVECTION SECTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1116 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1117 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1118 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1119 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 RADIANT SECTION CELL A - SHEET 4 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1120 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 RADIANT SECTION CELL B - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1121 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 RADIANT SECTION CELL B - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1125 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 TLX EXCHANGER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1126 | P&ID - RECYCLE GAS CRACKING FURNACE - FURNACE EFFLUENT AND DECOKE MOVS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1127 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1128 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 VHP STEAM DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1129 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1130 | P&ID - RECYCLE GAS CRACKING FURNACE - BOILER FEED WATER SUPPLY/EXPORT STEAM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1131 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 STEAM COILS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1135 | P&ID - RECYCLE GAS CRACKING FURNACE - FUEL GAS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1140 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 BURNERS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1145 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 DECOKING EFFLUENT |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1150 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 FLUE GAS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1201 | P&ID - LIQUID FEED CRACKING FURNACE -C3 LPG FEED DISTRIBUTION HEADER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1202 | P&ID - LIQUID FEED CRACKING FURNACE -LIQUID FEED DISTRIBUTION HEADER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1205 | P&ID - LIQUID FEED CRACKING FURNACE - DILUTION STEAM DISTRIBUTION HEADER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1206 | P&ID - LIQUID FEED CRACKING FURNACE -DECOKE AIR HEADER DISTRIBUTION HEADER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1207 | P&ID - LIQUID FEED CRACKING FURNACE - FEED- SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1208 | P&ID - LIQUID FEED CRACKING FURNACE - FEED - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1209 | P&ID - LIQUID FEED CRACKING FURNACE - FEED - SHEET 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1210 | P&ID - LIQUID FEED CRACKING FURNACE - FEED- SHEET 4 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1211 | P&ID - LIQUID FEED CRACKING FURNACE - FEED - SHEET 5 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1212 | P&ID - LIQUID FEED CRACKING FURNACE - FEED - SHEET 6 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1215 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 CONVECTION SECTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1216 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1217 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1218 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-01-22
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-03-29: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-1218. | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 3 |  | Class As built | Purpose** | 2019-01-22: IBD; 2019-01-22: IBD
Rev. | bar: 2019-01-22 to 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-02-13; 2019-01-22: 2019-02-13
[6 empty] | Issue Actual | 2019-01-22: 2019-02-13; 2019-01-22: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00850; 2019-01-22: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-04-10; 2019-01-22: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-1219 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 RADIANT SECTION CELL B - SHEET 4 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1220 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 RADIANT SECTION CELL B - SHEET 5 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1221 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 RADIANT SECTION CELL B - SHEET 6 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1225 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 TLX EXCHANGER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1226 | P&ID - LIQUID FEED CRACKING FURNACE -FURNACE EFFLUENT & DECOKE MOVS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1227 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1228 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 VHP STEAM DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1229 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1230 | P&ID - LIQUID FEED CRACKING FURNACE -BOILER FEED WATER SUPPLY/EXPORT STEAM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1231 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 STEAM COILS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1235 | P&ID - LIQUID FEED CRACKING FURNACE -FUEL GAS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1240 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 BURNERS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1245 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 DECOKING EFFLUENT |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1250 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 FLUE GAS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IFD | IFF
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-03-29: 2019-01-28; 2019-05-09: 2019-05-24; 2019-05-09: 2019-10-14
[6 empty] | Revised Plan | 2019-05-09: 2019-10-14
[6 empty] | Issue Actual | 2019-01-22: 2018-11-15; 2019-03-29: 2019-02-13; 2019-03-29: 2019-02-13
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-01-22: TPSK-LSPA1-T-PE-00323; 2019-03-29: TPSK-LSPA1-T-PE-00850; 2019-03-29: TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-01-22: 2019-02-11; 2019-01-22: 2019-02-11; 2019-03-29: 2019-04-10; 2019-03-29: 2019-04-10
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1315 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 CONVECTION SECTION |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1316 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1317 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1318 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1319 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL B - SHEET 4 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1320 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL B - SHEET 5 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1321 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL B - SHEET 6 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1325 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 TLX EXCHANGER |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1327 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1328 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 VHP STEAM DRUM |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1329 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1331 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 STEAM COILS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1340 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 BURNERS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1345 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 DECOKING EFFLUENT |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1350 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 FLUE GAS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1360 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 UTILITY STATION |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1361 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 UTILITY DISTRIBUTION |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1415 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 CONVECTION SECTION |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1416 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1417 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1418 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1419 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL B - SHEET 4 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1420 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL B - SHEET 5 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1421 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL B - SHEET 6 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1425 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 TLX EXCHANGER |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1427 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1428 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 VHP STEAM DRUM |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1429 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1431 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 STEAM COILS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1440 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 BURNERS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1445 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 DECOKING EFFLUENT |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1450 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 FLUE GAS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1460 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 UTILITY STATION |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1461 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 UTILITY DISTRIBUTION |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1515 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 CONVECTION SECTION |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1516 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1517 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1518 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1519 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL B - SHEET 4 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1520 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL B - SHEET 5 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1521 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL B - SHEET 6 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1525 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 TLX EXCHANGER |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1527 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1528 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 VHP STEAM DRUM |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1529 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1531 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 STEAM COILS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1540 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 BURNERS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1545 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 DECOKING EFFLUENT |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1550 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 FLUE GAS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1560 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 UTILITY STATION |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1561 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 UTILITY DISTRIBUTION |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1615 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 CONVECTION SECTION |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1616 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1617 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1618 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1619 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL B - SHEET 4 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1620 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL B - SHEET 5 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1621 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL B - SHEET 6 |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1625 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 TLX EXCHANGER |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1627 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1628 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 VHP STEAM DRUM |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1629 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1631 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 STEAM COILS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1640 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 BURNERS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1645 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 DECOKING EFFLUENT |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1650 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 FLUE GAS |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1660 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 UTILITY STATION |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1661 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 UTILITY DISTRIBUTION |  | Class 2 | Purpose** | 2019-01-22: IFR; 2019-01-22: IBD; 2019-03-29: IFD; 2019-03-29: IFF
Rev.
[6 empty] | Issue Plan | 2019-01-22: 2018-11-16; 2019-01-22: 2019-01-28; 2019-03-29: 2019-05-24; 2019-03-29: 2019-10-14
[6 empty] | Revised Plan | 2019-01-22: 2019-11-29; 2019-01-22: 2019-11-29; 2019-03-29: 2019-11-29; 2019-03-29: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1901 | P&ID - FEED PREPARATION & FURNACES AUX - DMDS INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-1915 | P&ID - FEED PREPARATION & FURNACES AUX - DECOKE AIR RECEIVER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2001 | P&ID - QUENCH OIL - QUENCH OIL FRACTIONATOR |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2003 | P&ID - QUENCH OIL - QUENCH OIL CIRCULATING PUMPS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2005 | P&ID - QUENCH OIL - QUENCH OIL FILTRATION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2006 | P&ID - QUENCH OIL - VLP STEAM GENERATION - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2007 | P&ID - QUENCH OIL - VLP STEAM GENERATION - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2008 | P&ID - Olefins Unit 10 - Quench Oil - VLP Steam Generation - Sheet 3 |  | Class As built | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-05-09: 2020-02-07; 2019-06-04: 2020-05-30; 2019-06-04: 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-03-27; 2019-03-29: 2019-03-28; 2019-03-29: 2019-08-15
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-01180; 2019-03-29: TPSK-LSPA1-T-PE-01180; 2019-03-29: TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-01-22: 2019-04-05; 2019-03-29: 2019-04-05
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2020 | P&ID - QUENCH OIL - LIGHT FUEL OIL STRIPPER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2021 | P&ID - QUENCH OIL - FUEL OIL PRODUCT COOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2022 | P&ID - QUENCH OIL - FUEL OIL FILTRATION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2025 | P&ID - QUENCH OIL - HEAVY FUEL OIL STRIPPER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2026 | P&ID - QUENCH OIL - HEAVY FUEL OIL PUMPS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2027 | P&ID - QUENCH OIL - HEAVY FUEL OIL PRODUCT COOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2040 | P&ID - QUENCH OIL DRAIN COLLECTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2042 | P&ID - QUENCH OIL DRAIN DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-27; 2019-03-29: 2019-03-28; 2019-05-09: 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2090 | P&ID - Olefins Unit 10 - Quench Oil - Cracker Product- Hexane- Flux Oil Battery Limit |  | Class As built | Purpose** | 2019-01-22: IDD1
Rev. | bar: 2019-01-22
Issue Plan
[6 empty] | Revised Plan | 2019-01-22: 2019-08-15
[6 empty] | Issue Actual | 2019-01-22: 2019-08-15
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-02434
Return Date
Owner Cmmt*
| PE | OL1-2G43-2101 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER TOWER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2102 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER TOWER OVERHEAD |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2104 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH OIL FRACTIONATOR REFLUX |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2106 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER PUMPS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2108 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER DISTRIBUTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2110 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER COOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2115 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER DRAIN DISTRIBUTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2117 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER DRAIN DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2120 | P&ID - QUENCH WATER / DILUTION STEAM - DISTILLATE STRIPPER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2122 | P&ID - QUENCH WATER / DILUTION STEAM - DISTILLATE STRIPPER REBOILER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2123 | P&ID - QUENCH WATER / DILUTION STEAM - PROCESS WATER STRIPPER FEED |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2125 | P&ID - QUENCH WATER / DILUTION STEAM - PROCESS WATER STRIPPER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2126 | P&ID - QUENCH WATER / DILUTION STEAM - PRCOESS WATER STRIPPER REBOILER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2127 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR FEED PUMPS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2130 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR FEED HEATING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2131 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2132 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR REBOILERS - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2134 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR REBOILERS - SHEET 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2137 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM SUPERHEATING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2138 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM BLOWDOWN COOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2201 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS 1ST STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2203 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 1ST AND 2ND STAGES |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2204 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 1ST STAGE AFTERCOOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2206 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 2ND STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2208 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 2ND STAGE AFTERCOOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2210 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 3RD STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2211 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 3RD AND 4TH STAGES |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2212 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 3RD STAGE AFTERCOOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2214 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 4TH STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2215 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 4TH STAGE AFTERCOOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2217 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 4TH STAGE DISCHARGE DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2220 | P&ID - CRACKED GAS COMPRESSION - WASH WATER COOLER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2222 | P&ID - CRACKED GAS COMPRESSION - WASH WATER INJECTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2224 | P&ID - CRACKED GAS COMPRESSION - WASH OIL INJECTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-01-22: TPSK-LSPA1-T-PE-00566; 2019-03-29: TPSK-LSPA1-T-PE-01201; 2019-03-29: TPSK-LSPA1-T-PE-01201
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-04-22; 2019-03-29: 2019-04-22
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2301 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - CAUSTIC TOWER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2303 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - WEAK/INTERMEDIATE CAUSTIC CIRCULATION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2305 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - STRONG CAUSTIC CIRCULATION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2310 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - FRESH CAUSTIC STORAGE |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2311 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC DEOILING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2313 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC DEGASSING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2314 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Spent Caustic Drain Collection |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2315 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT WASH OIL DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2316 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - CAUSTIC DRAIN SUMP |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2317 | P&ID - Olefins Unit 10 - Caustic and Spent Caustic Treatment - Yellow Oil Drum |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2318 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC DRAIN SUMP |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2319 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SKIM OIL DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2320 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STORAGE |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2325 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STRIPPER FEED HEATING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2326 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STRIPPER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2328 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STRIPPER OVERHEAD |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2329 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - WAO PACKAGE |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22
| PE | OL1-2G43-2401 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CAUSTIC TOWER OVERHEAD CHILLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2402 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CAUSTIC TOWER OVERHEAD KO DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2404 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LIQUID DRIER FEED COALESCER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2406 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LIQUID DRIERS - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2407 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LIQUID DRIERS - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2409 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS DEHYDRATION - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2410 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS DEHYDRATION - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2412 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - REGENERATION GAS HEATING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2414 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - REGENERATION GAS COOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2419 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS MERCURY ABSORBER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2420 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER FEED CHILLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2422 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2423 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER REBOILER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2425 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2426 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER REBOILER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2427 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER OVERHEAD |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2428 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER PRODUCT/REFLUX PUMPS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2430 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - 5TH STAGE CRACKED GAS COMPRESSION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2432 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS COMPRESSOR 5TH STAGE AFTERCOOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2433 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION FEED ARSINE REMOVAL |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2435 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION FEED HEATING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2437 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR A |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2438 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR A INTERCOOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2439 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR B |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2440 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR B INTERCOOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2442 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR C |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2444 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CG SECONDARY DEHYDRATOR |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2446 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER REFLUX CHILLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2447 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER REFLUX |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2018-12-27; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-01-22: TPSK-LSPA1-T-PE-00567; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-21; 2019-01-22: 2019-02-21; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2501 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED CHILLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2503 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED SEPARATOR NO. 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2505 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED SEPARATOR NO. 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2507 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED SEPARATOR NO. 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2511 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2513 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR REBOILER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2515 | P&ID - COLD FRACTIONATION - RESIDUE GAS RECTIFIER CONDENSER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2517 | P&ID - COLD FRACTIONATION - RESIDUE GAS RECTIFIER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2520 | P&ID - COLD FRACTIONATION - DEMETHANIZER FEED COOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2521 | P&ID - COLD FRACTIONATION - DEMETHANIZER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2522 | P&ID - COLD FRACTIONATION - DEMETHANIZER REBOILER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2525 | P&ID - COLD FRACTIONATION - RESIDUE GAS EXPANDER SUCTION/DISCHARGE DRUMS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2527 | P&ID - COLD FRACTIONATION - RESIDUE GAS EXPANDER/RECOMPRESSOR |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2529 | P&ID - COLD FRACTIONATION - HYDROGEN RECOVERY |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2530 | P&ID - COLD FRACTIONATION - PROPYLENE REFRIGERANT SUBCOOLER SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2531 | P&ID - COLD FRACTIONATION - PROPYLENE REFRIGERANT SUBCOOLER SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2532 | P&ID - COLD FRACTIONATION - PRESSURE SWING ABSORPTION UNIT |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2541 | P&ID - COLD FRACTIONATION - DEETHANIZER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2543 | P&ID - COLD FRACTIONATION - DEETHANIZER REBOILER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2546 | P&ID - COLD FRACTIONATION - DEETHANIZER CONDENSER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2547 | P&ID - COLD FRACTIONATION - DEETHANIZER OVERHEAD |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2551 | P&ID - COLD FRACTIONATION - DEMETHANIZER BOTTOMS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2552 | P&ID - COLD FRACTIONATION - C2 SPLITTER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2553 | P&ID - COLD FRACTIONATION - C2 SPLITTER BOTTOMS REBOILER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2554 | P&ID - COLD FRACTIONATION - C2 SPLITTER INTER-REBOILER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2556 | P&ID - COLD FRACTIONATION - ETHANE RECYCLE PUMPS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-01-22 to 2019-03-29
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-08-23; 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-08; 2019-03-29: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. | 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-01-22: TPSK-LSPA1-T-PE-00612; 2019-03-29: TPSK-LSPA1-T-PE-01264; 2019-03-29: TPSK-LSPA1-T-PE-01264
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2601 | P&ID - HOT FRACTIONATION - C3 HYDROGENATION ARSINE GUARD BED |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-16; 2019-03-29: 2019-04-09; 2019-03-29: 2019-04-10; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2602 | P&ID - HOT FRACTIONATION - C3 GUARD ADSORBERS - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-16; 2019-03-29: 2019-04-09; 2019-03-29: 2019-04-10; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2603 | P&ID - HOT FRACTIONATION - C3 GUARD ADSORBERS - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-16; 2019-03-29: 2019-04-09; 2019-03-29: 2019-04-10; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2604 | P&ID - Olefins Unit 10 - Hot Fractionation - Feed Section |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-29: 2019-07-02
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-29
| PE | OL1-2G43-2605 | P&ID - HOT FRACTIONATION - C3 HYDROGENATION REACTORS - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-29: 2019-07-02
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-29
| PE | OL1-2G43-2608 | P&ID - HOT FRACTIONATION - C3 HYDROGENATION AFTERCOOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-29: 2019-07-02
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-29
| PE | OL1-2G43-2610 | P&ID - HOT FRACTIONATION - C3 HYDROGENATION RECYCLE |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-04-12; 2019-01-22: 2019-04-12; 2019-03-29: 2019-07-02
Owner Cmmt* | bar: 2019-01-22 to 2019-01-22; 2019-03-29
| PE | OL1-2G43-2615 | P&ID - HOT FRACTIONATION - SECONDARY DEETHANIZER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-16; 2019-03-29: 2019-04-09; 2019-03-29: 2019-04-10; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2616 | P&ID - HOT FRACTIONATION - SECONDARY DEETHANIZER OVERHEAD |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-16; 2019-03-29: 2019-04-09; 2019-03-29: 2019-04-10; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2620 | P&ID - HOT FRACTIONATION - C3 SPLITTER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-16; 2019-03-29: 2019-04-09; 2019-03-29: 2019-04-10; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2621 | P&ID - HOT FRACTIONATION - C3 SPLITTER REBOILERS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-16; 2019-03-29: 2019-04-09; 2019-03-29: 2019-04-10; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2622 | P&ID - HOT FRACTIONATION - C3 SPLITTER BOTTOMS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-16; 2019-03-29: 2019-04-09; 2019-03-29: 2019-04-10; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2625 | P&ID - HOT FRACTIONATION - DEBUTANIZER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-16; 2019-03-29: 2019-04-09; 2019-03-29: 2019-04-10; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2627 | P&ID - HOT FRACTIONATION - DEBUTANIZER OVERHEAD |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-16; 2019-03-29: 2019-04-09; 2019-03-29: 2019-04-10; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2628 | P&ID - HOT FRACTIONATION - DEBUTANIZER OVERHEAD PRODUCT/REFLUX |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-05-09: 2019-11-11; 2019-06-04: 2020-02-07; 2019-06-04: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-22: 2019-01-16; 2019-03-29: 2019-04-09; 2019-03-29: 2019-04-10; 2019-05-09: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-01-22: 2019-02-25; 2019-01-22: 2019-02-25; 2019-03-29: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-01-22 to 2019-03-29
| PE | OL1-2G43-2629 | P&ID - HOT FRACTIONATION - DEBUTANIZER BOTTOMS COOLING |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C | C | D
[6 empty] | Rev.: Issue Plan; A: 2019-02-20; C: 2019-03-29; D: 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 |  | R1
| PE | OL1-2G43-2630 | P&ID - HOT FRACTIONATION - C5/PYGAS SURGE DRUM |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C | C | D
[6 empty] | Rev.: Issue Plan; A: 2019-02-20; C: 2019-03-29; D: 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 |  | R1
| PE | OL1-2G43-2631 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Bottoms Pumps |  | Class As built | Purpose** | IFR | IFR | CAN | CAN
[6 empty] | Rev. | A | A | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  | 2019-01-16 | 2019-04-10 | 2019-04-11
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-10 | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01298 | TPSK-LSPA1-T-PE-01298
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-05-16 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G43-2690 | P&ID - Olefins Unit 10 - Hot Fractionation - RAW C4S - PYGAS - OFF-SPEC PROPYLENE BATTERY LIMIT |  | Class As built | Rev.: Purpose**; A: IDD1
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-14
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02406
Return Date
Owner Cmmt*
| PE | OL1-2G43-2701 | P&ID - GHU & C4/C5 HYDROG - GHU-1 FEED HEATING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2702 | P&ID - GHU & C4/C5 HYDROG - GHU-1 REACTORS - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2703 | P&ID - GHU & C4/C5 HYDROG - GHU-1 REACTORS - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2704 | P&ID - GHU & C4/C5 HYDROG - GHU-1 HOT SEPARATOR |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2705 | P&ID - GHU & C4/C5 HYDROG - GHU-1 COLD SEPARATOR |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2706 | P&ID - GHU & C4/C5 HYDROG - GHU-1 DEPENTANIZER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2707 | P&ID - GHU & C4/C5 HYDROG - GHU C5 CUT PUMPS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2708 | P&ID - GHU & C4/C5 HYDROG - GHU-1 DEPENTANIZER OVERHEAD |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2710 | P&ID - GHU & C4/C5 HYDROG - GHU RERUN TOWER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2711 | P&ID - GHU & C4/C5 HYDROG - GHU RERUN TOWER CONDENSER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2712 | P&ID - GHU & C4/C5 HYDROG - GHU RERUN TOWER REFLUX/PRODUCT PUMP |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2713 | P&ID - GHU & C4/C5 HYDROG - GHU-1 PRODUCT COOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2715 | P&ID - GHU & C4/C5 HYDROG - GHU-1 RECYCLE WASH OIL |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2716 | P&ID - GHU & C4/C5 HYDROG - PYGAS FUEL OIL PRODUCT |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2717 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Refun Tower Liquid Ring Pump |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2718 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Anti-Oxidant Injection Package |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2720 | P&ID - GHU & C4/C5 HYDROG - REACTIVATION GAS HEATING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2722 | P&ID - GHU & C4/C5 HYDROG - REGENERATION DECOKE DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2730 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION FEED SURGE DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2732 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION FEED PUMP |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2733 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION FEED HEATING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2734 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION REACTOR |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2736 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION RECYCLE DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2738 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION RECYCLE/PRODUCT COOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2740 | P&ID - GHU & C4/C5 HYDROG - LIGHT OIL DRAIN DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2742 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Light Oil Drain Drum |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-2801 | P&ID - REFRIGERATION - C3 REFRIGERANT COMPRESSOR SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2802 | P&ID - REFRIGERATION - C3 REFRIGERANT COMPRESSOR SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2803 | P&ID - REFRIGERATION - C3 REFRIGERANT CONDENSER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2804 | P&ID - REFRIGERATION - C3 REFRIGERANT RECEIVER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2805 | P&ID - REFRIGERATION - HP C3 REFRIGERATION DISTRIBUTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2806 | P&ID - REFRIGERATION - C3 REFRIGERANT 4TH STAGE SUCTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2807 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 3 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2808 | P&ID - REFRIGERATION - C3 REFRIGERANT 3RD STAGE SUCTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2810 | P&ID - REFRIGERATION - C3 REFRIGERANT 2ND STAGE SUCTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2812 | P&ID - REFRIGERATION - C3 REFRIGERANT 1ST STAGE SUCTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2814 | P&ID - REFRIGERATION - C3 REFRIGERANT DRAIN DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2816 | P&ID - REFRIGERATION - PROPYLENE PRODUCT PUMP |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2818 | P&ID - REFRIGERATION - PROPYLENE PRODUCT CHILLING SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2819 | P&ID - REFRIGERATION - PROPYLENE PRODUCT CHILLING SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2821 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT COMPRESSOR SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2822 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT COMPRESSOR SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2823 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Compressor - Sheet 3 |  | Class As built | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; C: 2020-02-07; D: 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date |  |  | 2019-07-02
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-2824 | P&ID - REFRIGERATION - C2 REFRIGERANT DESUPERHEATERS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2825 | P&ID - REFRIGERATION - C2 REFRIGERANT DESUPERHEATERS AND CONDENSING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2828 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT SURGE DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2830 | P&ID - REFRIGERATION - HP ETHYLENE LIQUID PRODUCT CHILLER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2834 | P&ID - REFRIGERATION - HP ETHYLENE VAPOR PRODUCT |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2836 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT 3RD STAGE SUCTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2838 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT 2ND STAGE SUCTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2840 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT 1ST STAGE SUCTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2842 | P&ID - REFRIGERATION - LP ETHYLENE PRODUCT COOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2846 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT DRAIN DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-01-16 | 2019-04-12 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-2890 | P&ID - Olefins Unit 10 - Refrigeration System - HP Vapor-Liquid Ethylene-HP-LP Propylene BL |  | Class As built | Rev.: Purpose**; A: IDD1
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-15
[6 empty] | Issue Actual | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02434
Return Date
Owner Cmmt*
| PE | OL1-2G43-2891 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Battery Limit |  | Class As built | Rev.: Purpose**; A: IDD1
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-16
[6 empty] | Issue Actual | 2019-08-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02434
Return Date
Owner Cmmt*
| PE | OL1-2G43-2901 | P&ID - OLEFINS RECOVERY AUXILLARY - EMULSION BREAKER INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2902 | P&ID - OLEFINS RECOVERY AUXILLARY - PH CONTROL INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2903 | P&ID - OLEFINS RECOVERY AUXILLARY - POLYMERIZATION INHIBITOR INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2904 | P&ID - OLEFINS RECOVERY AUXILLARY - PROCESS WATER STRIPPER CHEMICAL INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2905 | P&ID - OLEFINS RECOVERY AUXILLARY - CORROSION INHIBITOR INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2906 | P&ID - OLEFINS RECOVERY AUXILLARY - DSG ANTI-FOULANT INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2907 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Caustic Tower Anti Foulant Injection System |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2908 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Neutralization Injection |  | Class As built | Purpose** | IFR | IFR | CAN | CAN
[6 empty] | Rev. | A | A | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G43-2909 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Methanol Injection System |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2910 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Anti-Oxidant Injection Package |  | Class As built | Rev.: Purpose**; A: IDD1
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-14
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02403
Return Date
Owner Cmmt*
| PE | OL1-2G43-2915 | P&ID - OLEFINS RECOVERY AUXILLARY - WASH OIL STORAGE |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2920 | P&ID - OLEFINS RECOVERY AUXILLARY - QUENCH OIL PUMP TURBINE DETAILS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-02-04 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2922 | P&ID - OLEFINS RECOVERY AUXILLARY - QUENCH WATER PUMP TURBINE DETAILS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2924 | P&ID - OLEFINS RECOVERY AUXILLARY - DSG FEED PUMP TURBINE DETAILS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2930 | P&ID - OLEFINS RECOVERY AUXILLARY - CG COMP. TURBINE DETAILS - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2932 | P&ID - OLEFINS RECOVERY AUXILLARY - CG COMP. TURBINE DETAILS - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2934 | P&ID - OLEFINS RECOVERY AUXILLARY - CG COMP. TURBINE DETAILS - SHEET 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2955 | P&ID - OLEFINS RECOVERY AUXILLARY - C3 REFRIGERANT COMP. TURBINE DETAILS - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2960 | P&ID - OLEFINS RECOVERY AUXILLARY - C3 REFRIGERANT COMP. TURBINE DETAILS - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2965 | P&ID - OLEFINS RECOVERY AUXILLARY - C3 REFRIGERANT COMP. TURBINE DETAILS - SHEET 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2970 | P&ID - OLEFINS RECOVERY AUXILLARY - C2 REFRIGERANT COMP. TURBINE DETAILS - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2975 | P&ID - OLEFINS RECOVERY AUXILLARY - C2 REFRIGERANT COMP. TURBINE DETAILS - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-2976 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C2R Lube Oil Pump Turbine Details |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-05 | 2019-04-17 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-02-25 | 2019-06-03 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-3001 | P&ID - C4 UNIT - PREDISTILLATION FEED DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-3002 | P&ID - C4 UNIT - PREDISTILLATION FEED PUMPS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-3003 | P&ID - C4 UNIT - PREDISTILLATION TOWER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-3004 | P&ID - C4 UNIT - PREDISTILLATION TOWER REBOILERS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-3005 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - C4 Vaporization Tower & Heavy End Disch. Pumps |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-3006 | P&ID - C4 UNIT - PREDISTILLATION TOWER OVERHEAD |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-3007 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Main Washer & Solvent Cooler |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-3008 | P&ID - C4 UNIT - FEED VAPORIZER DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-3009 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Main Washer Bottom Pump & Reflux Pump |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-3010 | P&ID - C4 UNIT - C4 EVAPORATORS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-3011 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Rectifier Pump And Degasser Feed Pump |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-3012 | P&ID - C4 UNIT - MAIN WASHER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-3013 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - After Washer Overhead |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3014 | P&ID - C4 UNIT - MAIN WASHER OVERHEAD |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3015 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Solvent Heat Exchanger-II And Solvent Heater |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-04-12 | 2019-04-12 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3016 | P&ID - C4 UNIT - RECTIFIER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3017 | P&ID - C4 UNIT - RECTIFIER BOTTOMS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3018 | P&ID - C4 UNIT - AFTERWASHER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3019 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - HC - Water Separator |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3020 | P&ID - C4 UNIT - AFTERWASHER OVERHEAD |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3021 | P&ID - C4 UNIT - SOLVENT HEAT EXCHANGERS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3022 | P&ID - C4 UNIT - SOLVENT HEATING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3023 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit - BDU - Recycle Gas Compressor |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3024 | P&ID - C4 UNIT - SOLVENT COOLING/DEGASSING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3025 | P&ID - C4 UNIT - DEGASSING TOWER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3026 | P&ID - C4 UNIT - DEGASSING TOWER REBOILERS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3027 | P&ID - C4 UNIT - ACETYLENE WASHER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3028 | P&ID - C4 UNIT - ACETYLENE CONDENSING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3029 | P&ID - C4 UNIT - HC/WATER SEPARATOR |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3101 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Solvent Regeneration |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3102 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Water Washer And Condenser |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3103 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Regen Steam Ejector Package |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3104 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Water Washer Accumulator & Solvent Return Pumps |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3105 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Ejector Seal Drum And Waste Water Pumps |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3106 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Blow Down Drum |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3107 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drum |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3108 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Flash Drum |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3109 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Drum And Recycle Pumps |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-29 | 2019-03-29 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-3110 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Heater And Cooler |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-30 | 2019-03-30 |  | 2019-06-21
[6 empty] | Owner Cmmt* | CA | CA |  | R2
| PE | OL1-2G43-3111 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - BDU Steam Letdown |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-30 | 2019-03-30 |  | 2019-06-21
[6 empty] | Owner Cmmt* | CA | CA |  | R2
| PE | OL1-2G43-3112 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drain System - Sheet 1 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-30 | 2019-03-30 | 2019-06-21 | 2019-06-21
[6 empty] | Owner Cmmt* | CA | CA | R1 | R1
| PE | OL1-2G43-3113 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drain System - Sheet 2 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-30 | 2019-03-30 | 2019-06-21 | 2019-06-21
[6 empty] | Owner Cmmt* | CA | CA | R1 | R1
| PE | OL1-2G43-3901 | P&ID - C4 UNIT - SOLVENT STORAGE |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-30 | 2019-03-30 |  | 2019-06-21
[6 empty] | Owner Cmmt* | CA | CA |  | R2
| PE | OL1-2G43-3902 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Solvent Inhibitor Injection System |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-30 | 2019-03-30 |  | 2019-06-21
[6 empty] | Owner Cmmt* | CA | CA |  | R2
| PE | OL1-2G43-3903 | P&ID - C4 UNIT - SOLVENT INHIBITOR INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-30 | 2019-03-30 |  | 2019-06-21
[6 empty] | Owner Cmmt* | CA | CA |  | R2
| PE | OL1-2G43-3904 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Anti-Foam Agent Injection System |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-30 | 2019-03-30 |  | 2019-06-21
[6 empty] | Owner Cmmt* | CA | CA |  | R2
| PE | OL1-2G43-3905 | P&ID - C4 UNIT - PRODUCT INHIBITOR INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 | 2019-05-22 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-01722
[6 empty] | Return Date | 2019-03-30 | 2019-03-30 |  | 2019-06-21
[6 empty] | Owner Cmmt* | CA | CA |  | R2
| PE | OL1-2G43-5001 | P&ID - UTILITY SYSTEMS - DEMINERALIZATION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5010 | P&ID - UTILITY SYSTEMS - TREATED WATER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5020 | P&ID - UTILITY SYSTEMS - POTABLE WATER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5101 | P&ID - UTILITY SYSTEMS - STEAM LETDOWN STATIONS - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5102 | P&ID - UTILITY SYSTEMS - STEAM LETDOWN STATIONS - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5103 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Station - Sheet 3 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5105 | P&ID - UTILITY SYSTEMS - DEAERATOR |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5110 | P&ID - UTILITY SYSTEMS - SHP BOILER FEEDWATER PUMPS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5111 | P&ID - UTILITY SYSTEMS - BOILER FEEDWATER PUMPS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5113 | P&ID - UTILITY SYSTEMS - SHP BOILER FEEDWATER DISTRIBUTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5114 | P&ID - UTILITY SYSTEMS - BOILER FEEDWATER DISTRIBUTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5115 | P&ID - UTILITY SYSTEMS - SUSPECT CONDENSATE FLASH DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5118 | P&ID - UTILITY SYSTEMS - SUSPECT CONDENSATE COOLING |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5120 | P&ID - UTILITY SYSTEMS - CONDENSATE CARBON FILTERS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5125 | P&ID - UTILITY SYSTEMS - RAW CONDENSATE TANK |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5127 | P&ID - UTILITY SYSTEMS - CONDENSATE POLISHER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5128 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Polisher - Sheet 2 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5130 | P&ID - UTILITY SYSTEMS - CONDENSATE TANK |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5132 | P&ID - UTILITY SYSTEMS - LOW PRESSURE CONDENSATE FLASH DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5134 | P&ID - UTILITY SYSTEMS - INTERMITTENT FURNACE BLOWDOWN DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5140 | P&ID - UTILITY SYSTEMS - SHP STEAM DISTRIBUTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5143 | P&ID - UTILITY SYSTEMS - HP STEAM DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5144 | P&ID - UTILITY SYSTEMS - HP STEAM DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5150 | P&ID - UTILITY SYSTEMS - MP STEAM DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5151 | P&ID - UTILITY SYSTEMS - MP STEAM DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5152 | P&ID - UTILITY SYSTEMS - MP STEAM DISTRIBUTION - SHEET 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5160 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5161 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5162 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-5163 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 4 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5164 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 5 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-5166 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 6 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5168 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Steam Ls2 Distribution - Sheet 1 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-5170 | P&ID - UTILITY SYSTEMS - SHP/HP CONDENSATE COLLECTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5172 | P&ID - UTILITY SYSTEMS - MP CONDENSATE COLLECTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5176 | P&ID - UTILITY SYSTEMS - LP CONDENSATE COLLECTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5177 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 2 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5178 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 3 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5179 | P&ID - UTILITY SYSTEMS - VLP CONDENSATE COLLECTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-25 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5201 | P&ID - UTILITY SYSTEMS - FUEL GAS SYSTEM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-19 | 2019-06-19
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5202 | P&ID - Olefins Unit 10 - Fuel System - Fuel Gas Drum |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-19 | 2019-06-19
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5203 | P&ID - UTILITY SYSTEMS - PILOT GAS VAPORIZER AND SUPERHEATER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-19 | 2019-06-19
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5210 | P&ID - UTILITY SYSTEMS - FUEL GAS DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-19 | 2019-06-19
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G43-5211 | P&ID - UTILITY SYSTEMS - FUEL GAS DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-19 | 2019-06-19
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5301 | P&ID - COOLING WATER TOWER - COOLING TOWER - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5302 | P&ID - UTILITY SYSTEMS - COOLING TOWER - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5303 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 3 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5305 | P&ID - UTILITY SYSTEMS - COOLING WATER SUPPLY PUMPS - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5306 | P&ID - UTILITY SYSTEMS - COOLING WATER SUPPLY PUMPS - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5307 | P&ID - UTILITY SYSTEMS - CTU COOLING WATER SUPPY PUMPS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5310 | P&ID - UTILITY SYSTEMS - COOLING WATER SUPPY |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5311 | P&ID - UTILITY SYSTEMS - CTU COOLING WATER SUPPY |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5315 | P&ID - UTILITY SYSTEMS - COOLING WATER SIDE STREAM FILTER PACKAGE |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5317 | P&ID - UTILITY SYSTEMS - COOLING WATER FILTER BACKWASH |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5320 | P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5321 | P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5322 | P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5323 | P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 4 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5324 | P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 5 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5325 | P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 6 |  | Class 2 | Purpose** | IFR | IFR | CAN | CAN
[6 empty] | Rev. | A | A | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G43-5326 | P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 7 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5351 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Chemical Injection |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5352 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Corrosion Inhibitor Injection |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5401 | P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-29 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5402 | P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-29 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5403 | P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-29 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5404 | P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 4 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-29 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5410 | P&ID - UTILITY SYSTEMS - INSTRUMENT AIR RECEIVER |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-29 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5411 | P&ID - UTILITY SYSTEMS - INSTRUMENT AIR DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-29 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5412 | P&ID - UTILITY SYSTEMS - INSTRUMENT AIR DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-29 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5420 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-29 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5421 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-29 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-5422 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-29 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G43-5424 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 5 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-29 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-19 | 2019-06-19
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G43-5425 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 6 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-29 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-19 | 2019-06-19
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5426 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 6 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-29 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-01478
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-19 | 2019-06-19
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5501 | P&ID - UTILITY SYSTEMS - HOT FLARE KO DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5502 | P&ID - UTILITY SYSTEMS - COLD FLARE KO DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5503 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Methanol Vaporizer |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5510 | P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5511 | P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5512 | P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5514 | P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 5 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5516 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 5 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5518 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 6 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5519 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - LP Flare Header - Sheet 1 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5520 | P&ID - UTILITY SYSTEMS - COLD FLARE HEADER - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5521 | P&ID - UTILITY SYSTEMS - COLD FLARE HEADER - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5523 | P&ID - UTILITY SYSTEMS - COLD FLARE HEADER - SHEET 4 - DELETED |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5524 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 4 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5526 | P&ID - UTILITY SYSTEMS - PROPYLENE BLOWDOWN HEADER - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5528 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Propylene Blowdown Header - Sheet 2 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5529 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 1 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5531 | P&ID - UTILITY SYSTEMS - HOT BLOWDOWN HEADER - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5533 | P&ID - UTILITY SYSTEMS - HOT BLOWDOWN HEADER - SHEET 4 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5534 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 4 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5535 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 1 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5536 | P&ID - UTILITY SYSTEMS - COLD BLOWDOWN HEADER - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5540 | P&ID - UTILITY SYSTEMS - VOC VENT COLLECTION SYSTEM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5542 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 4 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5545 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Vent Collection System - Sheet 1 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5546 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Vent Collection System - Sheet 2 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5551 | P&ID - UTILITY SYSTEMS - HP FLARE KO DRUM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5553 | P&ID - UTILITY SYSTEMS - HP FLARE PILOT GAS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5555 | P&ID - UTILITY SYSTEMS - HP FLARE |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5575 | P&ID - UTILITY SYSTEMS - LLDPE FLARE |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-01-23 | 2019-05-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-01587
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 |  | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R2 |  | R1
| PE | OL1-2G43-5601 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5602 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5603 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5604 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 4 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5605 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 5 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5606 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 6 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5607 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 7 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5608 | P&ID - Olefins Unit 10 - Wastewater - C3 Hydrog Area Oily Wastewater Sump |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5609 | P&ID - Olefins Unit 10 - Wastewater - Flare Kod Area Oily Wastewater Sump |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5610 | P&ID - Olefins Unit 10 - Wastewater - Oily Waste Water Collection |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5620 | P&ID - UTILITY SYSTEMS - OLEFINS STORM WATER COLLECTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5621 | P&ID - Olefins Unit 10 - Wastewater - HP Flare Area Storm Water Collection |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5630 | P&ID - UTILITY SYSTEMS - OLEFINS HOLDING BASIN |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5631 | P&ID - Olefins Unit 10 - Wastewater - Olefins Holding Basin - Sheet 2 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5640 | P&ID - UTILITY SYSTEMS - SANITARY LIFT STATION - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5641 | P&ID - UTILITY SYSTEMS - SANITARY LIFT STATION - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5642 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 3 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5649 | P&ID - Olefins Unit 10 - Wastewater - HP Flare Area Oily Wastewater Sump |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5650 | P&ID - Olefins Unit 10 - Wastewater - CT Area Oily Wastewater Sump |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5651 | P&ID - UTILITY SYSTEMS - OSBL OILY WATER COLLECTION - SHEET 1 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5652 | P&ID - UTILITY SYSTEMS - OSBL OILY WATER COLLECTION - SHEET 2 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5653 | P&ID - UTILITY SYSTEMS - OSBL OILY WATER COLLECTION - SHEET 3 |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5654 | P&ID - Olefins Unit 10 - Wastewater - Equalization Tank |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5655 | P&ID - Olefins Unit 10 - Wastewater - Waste Water CPI-IGF Package |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5656 | P&ID - Olefins Unit 10 - Wastewater - Domestic Wastewater Collection |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5657 | P&ID - Olefins Unit 10 - Wastewater - Bio Equalization Pit |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5658 | P&ID - Olefins Unit 10 - Wastewater - Bio Treatment Package |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5660 | P&ID - Olefins Unit 10 - Wastewater - Final Check Basin |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5662 | P&ID - Olefins Unit 10 - Wastewater - Dewatering System |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5665 | P&ID - Olefins Unit 10 - Wastewater - Slop Oil Tank A |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5666 | P&ID - Olefins Unit 10 - Wastewater - Slop Oil Tank B |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5667 | P&ID - Olefins Unit 10 - Wastewater - Oily Sludge Tank |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-01499
[6 empty] | Return Date | 2019-03-13 | 2019-03-13 | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5903 | P&ID - UTILITY SYSTEMS - COOLING WATER HYPOCHLORIDE AND ACID INJECTION |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5904 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - 98 percent Sulfuric Acid Chemical Injection |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5905 | P&ID - UTILITY SYSTEMS - NEUTRALIZING AMINE INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5907 | P&ID - UTILITY SYSTEMS - OXYGEN SCAVENGER INJECTION SYSTEM |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5908 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Phosphate Injection System |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5915 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Condensate Pump Turbine Details |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5920 | P&ID - UTILITY SYSTEMS - COOLING WATER SUPPLY PUMP TURBINES |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5921 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Olefins CW Pump Turbine Details - Sheet 2 |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5922 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Ctu Cooling Water Pump Turbine Details |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5925 | P&ID - UTILITY SYSTEMS - SHP BFW PUMP TURBINE DETAILS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5927 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Lube Oil Pump Turbine A Details |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5928 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Lube Oil Pump Turbine B Details |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5929 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - VLP BFW Pump Turbine Details |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5930 | P&ID - UTILITY SYSTEMS - SHP BFW LUBE OIL PUMP TURBINE DETAILS |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-31 | 2019-02-01 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-26 | 2019-02-26 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5932 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - 98 percent Sulfuric Acid Pumps |  | Class As built | Purpose** | IFR | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Rev.: Revised Plan; C: 2019-08-23; C: 2019-11-11; D: 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G43-5933 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sulfuric Acid Chemical Injection - Sheet 3 |  | Class As built | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  |  | 2019-08-23 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date |  | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* |  | R2 | R2
| PE | OL1-2G43-5934 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sodium Hypochlorite Chemical Injection - Sheet 2 |  | Class As built | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 |  | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  |  | 2019-08-23 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date |  | 2019-06-04 | 2019-06-04
[6 empty] | Owner Cmmt* |  | R2 | R2
Category Code: G44 Heat and Material Balance
| PE | OL1-2G44-1001 | OVERALL MATERIAL BALANCE |  | Class 3 | Purpose** | IFI | IFI | IFI | IFI | IFI
[6 empty] | Rev. | A | A | 0 | 0 | 1
[6 empty] | Issue Plan | 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2018-08-06 | 2018-08-07 | 2019-03-29 | 2019-04-01 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00009 | TPSK-LSPA1-T-PE-00009 | TPSK-LSPA1-T-PE-01199 | TPSK-LSPA1-T-PE-01199 | TPSK-LSPA1-T-PE-02336
[6 empty] | Return Date | 2018-08-23 | 2018-08-23 | 2019-04-22 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G44-1002 | HEAT & MATERIAL BALANCE - DESIGN CASE 6 |  | Class 3 | Rev.: Purpose**; A: IFI; A: IFI; B: IFI
[6 empty] | Rev. | A | A | 0
[6 empty] | Issue Plan | 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2018-08-31 | 2018-09-03 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00032 | TPSK-LSPA1-T-PE-00032 | TPSK-LSPA1-T-PE-02334
Return Date
Owner Cmmt*
| PE | OL1-2G44-1003 | HEAT & MATERIAL BALANCE - DESIGN CASE 8 |  | Class 3 | Rev.: Purpose**; A: IFI; A: IFI; B: IFI
[6 empty] | Rev. | A | A | 0
[6 empty] | Issue Plan | 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2018-08-31 | 2018-09-03 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00032 | TPSK-LSPA1-T-PE-00032 | TPSK-LSPA1-T-PE-02334
Return Date
Owner Cmmt*
| PE | OL1-2G44-1004 | HEAT & MATERIAL BALANCE - DESIGN CASE 9 |  | Class 3 | Rev.: Purpose**; A: IFI; A: IFI; B: IFI
[6 empty] | Rev. | A | A | 0
[6 empty] | Issue Plan | 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2018-08-31 | 2018-09-03 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00032 | TPSK-LSPA1-T-PE-00032 | TPSK-LSPA1-T-PE-02334
Return Date
Owner Cmmt*
| PE | OL1-2G44-1005 | Heat & Material Balance - C3 Hydrogenation Unit & Gasoline Hydrogenation GHU & C4-C5 Hydrogenation Unit |  | Class 2 | Rev.: Purpose**; A: IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02334
Return Date
Owner Cmmt*
| PE | OL1-2G44-1006 | Heat & Material Balance - Butadiene Unit BDU |  | Class 2 | Rev.: Purpose**; A: IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02334
Return Date
Owner Cmmt*
| PE | OL1-2G44-1010 | HEAT & MATERIAL BALANCE - ISBL SUPPORTING UTILITIES |  | Class 3 | Rev.: Purpose**; A: IFI; A: IFI
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2018-10-03 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00128 | TPSK-LSPA1-T-PE-00128
Return Date
Owner Cmmt*
| PE | OL1-2G44-1011 | HEAT & MATERIAL BALANCE - AREA-53 (COOLING WATER SYSTEM) |  | Class 3 | Rev.: Purpose**; A: IFI; A: IFI
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2018-10-01 | 2018-10-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00116 | TPSK-LSPA1-T-PE-00116
Return Date
Owner Cmmt*
| PE | OL1-2G44-1012 | HEAT & MATERIAL BALANCE - AREA-55 (FLARE SYSTEM) |  | Class 3 | Rev.: Purpose**; A: IFI; A: IFI
[6 empty] | Rev. | 0 | 0
[6 empty] | Issue Plan | 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01492 | TPSK-LSPA1-T-PE-01492
[6 empty] | Return Date | 2019-05-29 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G44-1013 | HEAT & MATERIAL BALANCE - AREA-56 (WWT SYSTEM) |  | Class 3 | Purpose** | IFI | IFI | IFI | IFI
[6 empty] | Rev. | A | A | 1 | 1
[6 empty] | Issue Plan | 2019-01-21
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-03 | 2019-02-19 | 2019-02-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00581 | TPSK-LSPA1-T-PE-00581 | TPSK-LSPA1-T-PE-00892 | TPSK-LSPA1-T-PE-00892
Return Date
Owner Cmmt*
Category Code: G50 Interlocking Description/Cause and Effect Diagrams
| PE | OL1-2G50-1001 | SHUTDOWN INTERLOCK NARRATIVE (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFD | IBD | IBD | IBD | IBD | IFC
[6 empty] | Rev. | A |  | B | B | C | C
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-16 | 2019-03-15 |  |  |  | 2019-10-28
[6 empty] | Revised Plan | [6 empty] | 2019-10-28
[6 empty] | Issue Actual | 2019-01-17 |  | 2019-02-15 | 2019-02-15 | 2019-05-28 | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00674 |  | TPSK-LSPA1-T-IE-00556 | TPSK-LSPA1-T-IE-00556 | TPSK-LSPA1-T-PE-01758 | TPSK-LSPA1-T-PE-01758
[6 empty] | Return Date | 2019-03-08 |  | 2019-03-29 | 2019-03-29 | 2019-06-21 | 2019-06-21
[6 empty] | Owner Cmmt* | R1 |  | R2 | R2 | R2 | R2
| PE | OL1-2G50-1002 | 132U Cause and Effect Diagram Cracking Furnaces |  | Class 2 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G50-1003 | Cause and Effect Diagram Area 10 Feed Preparation and Feed Preheat |  | Class 2 | Rev.: Purpose**; A: IBD; A: Issued For Basic Design
[6 empty] | Rev. | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-27 | 2019-06-27
[6 empty] | Issue Actual | 2019-06-27 | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01999 | TPSK-LSPA1-T-PE-01999
[6 empty] | Return Date | 2019-08-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G50-1004 | Instrument Interlock Descriptions Area 10 Feed Preparation and Feed Preheat |  | Class 2 | Rev.: Purpose**; A: IBD; A: Issued For Basic Design
[6 empty] | Rev. | B | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-27 | 2019-06-27
[6 empty] | Issue Actual | 2019-06-27 | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02005 | TPSK-LSPA1-T-PE-02005
[6 empty] | Return Date | 2019-08-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G50-1101 | Instrument Interlock Descriptions Area 11 - 10-H-1100 |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IBD | IFD | IFD | IFC
Rev. | bar: R2 IFR to R2 IFD; R2 IFD to R2 IFD
[6 empty] | Issue Plan | 2019-03-19 |  | 2019-04-11 |  | 2019-10-22 | 2019-04-11 |  | 2019-10-28
[6 empty] | Revised Plan | R2 IFC: 2019-10-28
[6 empty] | Issue Actual | 2019-04-16 | 2019-04-17 | 2019-07-10 | 2019-07-10 |  | 2019-07-10 | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01367 | TPSK-LSPA1-T-IE-01367 | TPSK-LSPA1-T-PE-02112 | TPSK-LSPA1-T-PE-02112 |  | TPSK-LSPA1-T-PE-02112 | TPSK-LSPA1-T-PE-02112
[6 empty] | Return Date | R2 IFR: 2019-05-24; R2 IFR: 2019-05-24; R2 IFD: 2019-08-07; R2 IFD: 2019-08-07
Owner Cmmt* | bar: R2 IFR to R2 IFR; R2 IFD; R2 IFD
| PE | OL1-2G50-1102 | Cause and Effect Diagrams Cracking Furnace - 36M - Ex Doc Client Ref OL1-2G50-1001 |  | Class 2 | Purpose** | R2 IFR: IBD; R2 IFR: IBD
Rev. | bar: R2 IFR to R2 IFR
Issue Plan
[6 empty] | Revised Plan | R2 IFR: 2019-07-10; R2 IFR: 2019-07-10
[6 empty] | Issue Actual | R2 IFR: 2019-07-10; R2 IFR: 2019-07-10
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-PE-02111; R2 IFR: TPSK-LSPA1-T-PE-02111
[6 empty] | Return Date | R2 IFR: 2019-08-07
Owner Cmmt* | bar: R2 IFR
| IE | OL1-2G50-1201 | Instrument Interlock Descriptions Area 12-16 |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IBD | IFD | IFD | IFC
Rev. | bar: IFR to R2 IFD; R2 IFD to R2 IFD
[6 empty] | Issue Plan | 2019-03-19 |  | 2019-04-11 |  | 2019-10-22 | 2019-04-11 |  | 2019-10-28
[6 empty] | Revised Plan | R2 IFC: 2019-10-28
[6 empty] | Issue Actual | 2019-05-02 | 2019-05-03 | 2019-07-10 | 2019-07-10 |  | 2019-07-10 | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01561 | TPSK-LSPA1-T-IE-01561 | TPSK-LSPA1-T-PE-02112 | TPSK-LSPA1-T-PE-02112 |  | TPSK-LSPA1-T-PE-02112 | TPSK-LSPA1-T-PE-02112
[6 empty] | Return Date | IFR: 2019-05-29; R2 IFR: 2019-05-29; R2 IFD: 2019-08-19; R2 IFD: 2019-08-19
Owner Cmmt* | bar: IFR to R2 IFD; R2 IFD
| PE | OL1-2G50-1202 | Cause and Effect Diagrams Liquid Cracking Furnaces - 132U - Ex Doc Client Ref OL1-2G50-1002 |  | Class 2 | Purpose** | IFR: IBD; R2 IFR: IBD
Rev. | bar: IFR to R2 IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-10; R2 IFR: 2019-07-10
[6 empty] | Issue Actual | IFR: 2019-07-10; R2 IFR: 2019-07-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02111; R2 IFR: TPSK-LSPA1-T-PE-02111
[6 empty] | Return Date | R2 IFR: 2019-08-07
Owner Cmmt* | bar: R2 IFR
| PE | OL1-2G50-2001 | SHUTDOWN INTERLOCK NARRATIVE |  | Class 2 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2G50-2002 | Instrument Interlock Descriptions Area 20 Quench Oil |  | Class 2 | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G50-2101 | Cause and Effect Diagram - Area 21 - Quench Water - Dilution Steam |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | 2019-07-19 |  |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-03-25 | 2019-03-26 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual | R2 IFR: 2019-03-25; R2 IFD: 2019-03-26
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-PE-01137; R2 IFD: TPSK-LSPA1-T-PE-01137
[6 empty] | Return Date | R2 IFR: 2019-04-22; R2 IFD: 2019-04-22
Owner Cmmt* | bar: R2 IFR to R2 IFD
| PE | OL1-2G50-2102 | Instrument Interlock Descriptions - Area 21 - Quench Water - Dilution Steam |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | 2019-07-19 |  |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-03-25 | 2019-03-26 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | R2 IFR: 2019-03-25; R2 IFD: 2019-03-26
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-PE-01149; R2 IFD: TPSK-LSPA1-T-PE-01149
[6 empty] | Return Date | R2 IFR: 2019-04-22; R2 IFD: 2019-04-22
Owner Cmmt* | bar: R2 IFR to R2 IFD
| PE | OL1-2G50-2201 | Cause and Effect Diagram - Area 22 - Cracked Gas Compressor |  | Class 2 | Purpose** | IFI | IFR | IFR | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R2 IFR to R2 IBD
[6 empty] | Issue Plan | IFR: 2019-07-19; R2 IFD: 2019-09-05; R2 IFD: 2019-12-12; R2 IFC: 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-03-28 | 2019-03-29 | 2019-03-29 | 2019-04-01 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-03-28: 2019-03-28; 2019-03-29: 2019-03-29; 2019-03-29: 2019-03-29; 2019-04-01: 2019-04-01
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01183; 2019-03-29: TPSK-LSPA1-T-PE-01183; 2019-03-29: TPSK-LSPA1-T-PE--01204; 2019-04-01: TPSK-LSPA1-T-PE--01204
[6 empty] | Return Date |  | 2019-03-29: 2019-08-05; 2019-04-01: 2019-08-05
Owner Cmmt* | bar: 2019-03-29; 2019-04-01
| PE | OL1-2G50-2202 | Instrument Interlock Descriptions - Area 22 - Cracked Gas Compressor |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2020-01-07; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-30; 2020-03-06: 2020-08-30
[6 empty] | Revised Plan |  | 2019-03-29 | 2019-04-01 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-03-28: 2019-03-29; 2019-03-29: 2019-04-01
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01203; 2019-03-29: TPSK-LSPA1-T-PE-01203
[6 empty] | Return Date |  | 2019-03-28: 2019-06-04; 2019-03-29: 2019-06-04
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-2301 | Cause and Effect Diagram - Area 23 - Caustic and Spent Caustic Treatment |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2019-12-12; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-05; 2020-03-06: 2020-08-05
[6 empty] | Revised Plan |  | 2019-03-28 | 2019-03-29 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-03-28: 2019-03-28; 2019-03-29: 2019-03-29
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01183; 2019-03-29: TPSK-LSPA1-T-PE-01183
[6 empty] | Return Date |  | 2019-03-28: 2019-06-04; 2019-03-29: 2019-06-04
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-2302 | Instrument Interlock Descriptions - Area 23 - Caustic and Spent Caustic Treatment |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2020-01-07; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-30; 2020-03-06: 2020-08-30
[6 empty] | Revised Plan |  | 2019-03-28 | 2019-03-29 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-03-28: 2019-03-28; 2019-03-29: 2019-03-29
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01185; 2019-03-29: TPSK-LSPA1-T-PE-01185
[6 empty] | Return Date |  | 2019-03-28: 2019-06-04; 2019-03-29: 2019-06-04
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-2401 | Cause and Effect Diagram - Area 24 - Dehydration - Regen - Deprop- C2 Hydrog |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2019-12-12; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-05; 2020-03-06: 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-05 | 2019-04-08 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-03-28: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01267; 2019-03-29: TPSK-LSPA1-T-PE-01267
[6 empty] | Return Date |  | 2019-03-28: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-2402 | Instrument Interlock Descriptions - Area 24 - Dehydration - Regen - Deprop- C2 Hydrog |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2020-01-07; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-30; 2020-03-06: 2020-08-30
[6 empty] | Revised Plan |  | 2019-04-05 | 2019-04-08 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-03-28: 2019-04-05; 2019-03-29: 2019-04-08
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01266; 2019-03-29: TPSK-LSPA1-T-PE-01266
[6 empty] | Return Date |  | 2019-03-28: 2019-05-09; 2019-03-29: 2019-05-09
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-2501 | Cause and Effect Diagram - Area 25 - Cold Fractionation "CAUSE AND EFFECT DIAGRAM AREA 25: COLD FRACTIONATION" |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2019-12-12; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-05; 2020-03-06: 2020-08-05
[6 empty] | Revised Plan |  | 2019-03-21 | 2019-03-22 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-03-28: 2019-03-21; 2019-03-29: 2019-03-22
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01133; 2019-03-29: TPSK-LSPA1-T-PE-01133
[6 empty] | Return Date |  | 2019-03-28: 2019-04-11; 2019-03-29: 2019-04-11
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-2502 | Instrument Interlock Descriptions - Area 25 - Cold Fractionation |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2020-01-07; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-30; 2020-03-06: 2020-08-30
[6 empty] | Revised Plan |  | 2019-04-02 | 2019-04-03 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-03-28: 2019-04-02; 2019-03-29: 2019-04-03
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01225; 2019-03-29: TPSK-LSPA1-T-PE-01225
[6 empty] | Return Date |  | 2019-03-28: 2019-05-16; 2019-03-29: 2019-05-16
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-2601 | Cause and Effect Diagram - Area 26 - Hot Fractionation |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2019-12-12; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-05; 2020-03-06: 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-22 | 2019-04-23 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-03-28: 2019-04-22; 2019-03-29: 2019-04-23
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01429; 2019-03-29: TPSK-LSPA1-T-PE-01429
[6 empty] | Return Date |  | 2019-03-28: 2019-06-05; 2019-03-29: 2019-06-05
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-2602 | Instrument Interlock Description Area 26 - Hot Fractionation |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2020-01-07; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-30; 2020-03-06: 2020-08-30
[6 empty] | Revised Plan |  | 2019-05-20 | 2019-05-21 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-03-28: 2019-05-20; 2019-03-29: 2019-05-21
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01691; 2019-03-29: TPSK-LSPA1-T-PE-01691
[6 empty] | Return Date |  | 2019-03-28: 2019-06-13; 2019-03-29: 2019-06-13
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-2701 | Cause and Effect Diagram - Area 27 - GHU & C4-C5 Hydrog |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2019-12-12; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-05; 2020-03-06: 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-25 | 2019-04-26 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-03-28: 2019-04-25; 2019-03-29: 2019-04-26
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01481; 2019-03-29: TPSK-LSPA1-T-PE-01481
[6 empty] | Return Date |  | 2019-03-28: 2019-05-29; 2019-03-29: 2019-05-29
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-2702 | Instrument Interlock Descriptions - Area 27 - GHU & C4-C5 Hydrog |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2020-01-07; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-30; 2020-03-06: 2020-08-30
[6 empty] | Revised Plan |  | 2019-05-20 | 2019-05-21 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-03-28: 2019-05-20; 2019-03-29: 2019-05-21
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01697; 2019-03-29: TPSK-LSPA1-T-PE-01697
[6 empty] | Return Date |  | 2019-03-28: 2019-06-13; 2019-03-29: 2019-06-13
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-2801 | Cause and Effect Diagram Area 28 - Refrigeration System |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2019-12-12; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-05; 2020-03-06: 2020-08-05
[6 empty] | Revised Plan |  | 2019-05-01 | 2019-05-02 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-03-28: 2019-05-01; 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01540; 2019-03-29: TPSK-LSPA1-T-PE-01540
[6 empty] | Return Date |  | 2019-03-28: 2019-05-29; 2019-03-29: 2019-05-29
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-2802 | Instrument Interlock Descriptions Area 28 - Refrigeration System |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2020-01-07; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-30; 2020-03-06: 2020-08-30
[6 empty] | Revised Plan |  | 2019-05-28 | 2019-05-29 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-03-28: 2019-05-28; 2019-03-29: 2019-05-29
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01753; 2019-03-29: TPSK-LSPA1-T-PE-01753
[6 empty] | Return Date |  | 2019-03-29: 2019-06-21
Owner Cmmt* | bar: 2019-03-29
| PE | OL1-2G50-2901 | Cause and Effect Diagram - Area 29 - Ethylene Auxiliaries |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2019-12-12; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-05; 2020-03-06: 2020-08-05
[6 empty] | Revised Plan |  | 2019-05-01 | 2019-05-02 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-03-28: 2019-05-01; 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01539; 2019-03-29: TPSK-LSPA1-T-PE-01539
[6 empty] | Return Date |  | 2019-03-28: 2019-05-29; 2019-03-29: 2019-05-29
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-2902 | Instrument Interlock Descriptions Area 29 - Ethylene Auxliaries |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2020-01-07; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-30; 2020-03-06: 2020-08-30
[6 empty] | Revised Plan |  | 2019-05-28 | 2019-05-29 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-03-28: 2019-05-28; 2019-03-29: 2019-05-29
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01753; 2019-03-29: TPSK-LSPA1-T-PE-01753
[6 empty] | Return Date |  | 2019-03-29: 2019-06-21
Owner Cmmt* | bar: 2019-03-29
| PE | OL1-2G50-3001 | SHUTDOWN INTERLOCK NARRATIVE |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2019-12-12; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-05; 2020-03-06: 2020-08-05
[6 empty] | Revised Plan |  | 2019-05-30 | 2019-05-31 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-03-28: 2019-05-30; 2019-03-29: 2019-05-31
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01773; 2019-03-29: TPSK-LSPA1-T-PE-01773
[6 empty] | Return Date |  | 2019-03-28: 2019-06-21; 2019-03-29: 2019-06-21
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-3002 | Instrument Interlock Descriptions Area 30 - Butadiene Extraction Unit BDU |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2020-01-07; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-30; 2020-03-06: 2020-08-30
[6 empty] | Revised Plan |  | 2019-06-11 | 2019-06-11 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-03-28: 2019-06-11; 2019-03-29: 2019-06-11
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01868; 2019-03-29: TPSK-LSPA1-T-PE-01868
[6 empty] | Return Date |  | 2019-03-28: 2019-07-08
Owner Cmmt* | bar: 2019-03-28
| PE | OL1-2G50-5001 | SHUTDOWN INTERLOCK NARRATIVE |  | Class 2 | Purpose** | IFI | 2019-03-28: IDD1; 2019-03-29: IDD2; 2019-03-29: IFC1; 2019-04-01: IFC2; 2019-09-05: IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-28: 2019-09-05; 2019-03-29: 2019-12-12; 2019-03-29: 2020-03-06; 2019-04-01: 2020-05-05; 2019-09-05: 2020-08-05
[6 empty] | Revised Plan |  | 2019-03-28: 2019-09-05; 2019-03-29: 2019-12-12; 2019-03-29: 2020-03-06; 2019-04-01: 2020-05-05; 2019-09-05: 2020-08-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G50-5101 | Cause and Effect Diagram - Area 51 - BFW- Steam - Steam Condensate System |  | Class 2 | Purpose** | IFR | 2019-03-28: IFR; 2019-03-29: IBD
[6 empty] | Rev. | A | bar: 2019-03-28 to 2019-03-29
Issue Plan
[6 empty] | Revised Plan | 2019-04-24 | 2019-03-28: 2019-04-25; 2019-03-29: 2019-08-06
[6 empty] | Issue Actual | 2019-04-24 | 2019-03-28: 2019-04-25; 2019-03-29: 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01471 | 2019-03-28: TPSK-LSPA1-T-PE-01471; 2019-03-29: TPSK-LSPA1-T-PE-02343
[6 empty] | Return Date | 2019-05-29 | 2019-03-28: 2019-05-29
[6 empty] | Owner Cmmt* | R2 | bar: 2019-03-28
| PE | OL1-2G50-5102 | Instrument Interlock Descriptions - Area 51 - BFW-Steam - Steam Condensate System |  | Class 2 | Purpose** | IFR | 2019-03-28: IFR; 2019-03-29: IBD
[6 empty] | Rev. | A | bar: 2019-03-28 to 2019-03-29
Issue Plan
[6 empty] | Revised Plan | 2019-05-06 | 2019-03-28: 2019-05-07; 2019-03-29: 2019-08-07
[6 empty] | Issue Actual | 2019-05-06 | 2019-03-28: 2019-05-07; 2019-03-29: 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01573 | 2019-03-28: TPSK-LSPA1-T-PE-01573; 2019-03-29: TPSK-LSPA1-T-IE-02345
[6 empty] | Return Date | 2019-05-29 | 2019-03-28: 2019-05-29
[6 empty] | Owner Cmmt* | R2 | bar: 2019-03-28
| PE | OL1-2G50-5201 | Cause and Effect Diagram - Area 52 - Fuel System |  | Class 2 | Purpose** | IFR | 2019-03-28: IFR; 2019-03-29: IBD
[6 empty] | Rev. | A | bar: 2019-03-28 to 2019-03-29
Issue Plan
[6 empty] | Revised Plan | 2019-04-25 | 2019-03-28: 2019-04-26; 2019-03-29: 2019-08-06
[6 empty] | Issue Actual | 2019-04-25 | 2019-03-28: 2019-04-26; 2019-03-29: 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01480 | 2019-03-28: TPSK-LSPA1-T-PE-01480; 2019-03-29: TPSK-LSPA1-T-PE-02343
[6 empty] | Return Date | 2019-05-29 | 2019-03-28: 2019-05-29
[6 empty] | Owner Cmmt* | R2 | bar: 2019-03-28
| PE | OL1-2G50-5202 | Instrument Interlock Descriptions - Area 52 - Fuel System |  | Class 2 | Purpose** | IFR | 2019-03-28: IFR; 2019-03-29: IBD
[6 empty] | Rev. | A | bar: 2019-03-28 to 2019-03-29
Issue Plan
[6 empty] | Revised Plan | 2019-05-06 | 2019-03-28: 2019-05-07; 2019-03-29: 2019-08-07
[6 empty] | Issue Actual | 2019-05-06 | 2019-03-28: 2019-05-07; 2019-03-29: 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01573 | 2019-03-28: TPSK-LSPA1-T-PE-01573; 2019-03-29: TPSK-LSPA1-T-IE-02345
[6 empty] | Return Date | 2019-05-29 | 2019-03-28: 2019-05-29
[6 empty] | Owner Cmmt* | R2 | bar: 2019-03-28
| PE | OL1-2G50-5301 | Cause and Effect Diagram Area 53 Cooling Water System |  | Class 2 | Purpose** | IFI | 2019-03-28: IDD1; 2019-03-29: IDD2; 2019-03-29: IFC1; 2019-04-01: IFC2; 2019-09-05: IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-28: 2019-09-05; 2019-03-29: 2019-12-12; 2019-03-29: 2020-03-06; 2019-04-01: 2020-05-05; 2019-09-05: 2020-08-05
[6 empty] | Revised Plan |  | 2019-03-28: 2019-09-05; 2019-03-29: 2019-12-12; 2019-03-29: 2020-03-06; 2019-04-01: 2020-05-05; 2019-09-05: 2020-08-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2G50-5302 | Instrument Interlock Descriptions Area 53 Cooling Water System |  | Class 2 | Purpose** | IFI | 2019-03-28: IDD1; 2019-03-29: IDD2; 2019-03-29: IFC1; 2019-04-01: IFC2; 2019-09-05: IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-28: 2019-09-05; 2019-03-29: 2020-01-07; 2019-03-29: 2020-03-06; 2019-04-01: 2020-05-30; 2019-09-05: 2020-08-30
[6 empty] | Revised Plan |  | 2019-03-28: 2019-09-05; 2019-03-29: 2020-01-07; 2019-03-29: 2020-03-06; 2019-04-01: 2020-05-30; 2019-09-05: 2020-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G50-5501 | Cause and Effect Diagram - Area 55 - Vent Gas and Flare System |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2019-12-12; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-05; 2020-03-06: 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-22 | 2019-04-23 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-03-28: 2019-04-22; 2019-03-29: 2019-04-23
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01429; 2019-03-29: TPSK-LSPA1-T-PE-01429
[6 empty] | Return Date |  | 2019-03-28: 2019-06-05; 2019-03-29: 2019-06-05
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-5502 | Instrument Interlock Descriptions Area 55 - Vent Gas and Flare System |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-03-29
[6 empty] | Issue Plan | 2019-07-19 | 2019-03-29: 2019-09-05; 2019-04-01: 2020-01-07; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-30; 2020-03-06: 2020-08-30
[6 empty] | Revised Plan |  | 2019-04-30 | 2019-05-02 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-03-28: 2019-04-30; 2019-03-29: 2019-05-02
[6 empty] | Transmittal no. |  | 2019-03-28: TPSK-LSPA1-T-PE-01523; 2019-03-29: TPSK-LSPA1-T-PE-01523
[6 empty] | Return Date |  | 2019-03-28: 2019-05-29; 2019-03-29: 2019-05-29
Owner Cmmt* | bar: 2019-03-28 to 2019-03-29
| PE | OL1-2G50-5601 | Cause and Effect Diagram - Area 56 - Wastewater |  | Class 2 | Purpose** | IFI | IFR | IFR | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-03-28 to 2019-04-01
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05: 2019-09-05; 2019-12-12: 2019-12-12; 2020-03-06: 2020-03-06; 2020-05-05: 2020-05-05; 2020-08-05: 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-24 | 2019-04-25 | 2019-05-01 | 2019-05-02 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-04-24: 2019-04-24; 2019-04-25: 2019-04-25; 2019-05-01: 2019-05-01; 2019-05-02: 2019-05-02
[6 empty] | Transmittal no. |  | 2019-04-24: TPSK-LSPA1-T-PE-01462; 2019-04-25: TPSK-LSPA1-T-PE-01462; 2019-05-01: TPSK-LSPA1-T-PE-01537; 2019-05-02: TPSK-LSPA1-T-PE-01537
[6 empty] | Return Date |  | 2019-05-01: 2019-05-29; 2019-05-02: 2019-05-29
Owner Cmmt* | bar: 2019-05-01 to 2019-05-02
| PE | OL1-2G50-5602 | Instrument Interlock Descriptions - Area 56 - Wastewater |  | Class 2 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: 2019-04-24 to 2019-04-25
[6 empty] | Issue Plan | 2019-07-19 | 2019-05-01: 2019-09-05; 2019-05-02: 2020-01-07; 2019-09-05: 2020-03-06; 2019-12-12: 2020-05-30; 2020-03-06: 2020-08-30
[6 empty] | Revised Plan |  | 2019-05-01 | 2019-05-02 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-04-24: 2019-05-01; 2019-04-25: 2019-05-02
[6 empty] | Transmittal no. |  | 2019-04-24: TPSK-LSPA1-T-PE-01538; 2019-04-25: TPSK-LSPA1-T-PE-01538
[6 empty] | Return Date |  | 2019-04-24: 2019-05-29; 2019-04-25: 2019-05-29
Owner Cmmt* | bar: 2019-04-24 to 2019-04-25
| PE | OL1-2G50-5901 | Cause and Effect Diagram Area 59 Supporting Utilities Auxiliaries |  | Class 2 | Purpose** | Issued For Basic Design | 2019-04-24: IBD
[6 empty] | Rev. | B | bar: 2019-04-24
Issue Plan
[6 empty] | Revised Plan | 2019-07-02 | 2019-04-24: 2019-07-02
[6 empty] | Issue Actual | 2019-07-02 | 2019-04-24: 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02036 | 2019-04-24: TPSK-LSPA1-T-PE-02036
[6 empty] | Return Date |  | 2019-04-24: 2019-07-24
Owner Cmmt* | bar: 2019-04-24
| IE | OL1-2G50-5902 | Instrument Interlock Descriptions Area 59 Supporting Utilities Auxiliaries |  | Class 2 | Purpose** | IBD | 2019-04-24: Issued For Basic Design
[6 empty] | Rev. | B | bar: 2019-04-24
Issue Plan
[6 empty] | Revised Plan | 2019-07-09 | 2019-04-24: 2019-07-09
[6 empty] | Issue Actual | 2019-07-09 | 2019-04-24: 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02038 | 2019-04-24: TPSK-LSPA1-T-PE-02038
[6 empty] | Return Date | 2019-08-05
[6 empty] | Owner Cmmt* | R2
Category Code: G51 Sequence of Operation |  |  |  |  | Class 2 | Purpose**
| PE | OL1-2G51-2403 | Sequence Narratives - Area 24 - Dehydration - Regen - Deprop - C2 Hydrog |  | Class 2 | Purpose** | IFR | 2019-04-24: IFR
[6 empty] | Rev. | A | bar: 2019-04-24
Issue Plan
[6 empty] | Revised Plan | 2019-04-16 | 2019-04-24: 2019-04-17
[6 empty] | Issue Actual | 2019-04-16 | 2019-04-24: 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01374 | 2019-04-24: TPSK-LSPA1-T-PE-01374
[6 empty] | Return Date | 2019-05-24 | 2019-04-24: 2019-05-24
[6 empty] | Owner Cmmt* | R2 | bar: 2019-04-24
Category Code: G60 Battery Limit and Tie-in
| PE | OL1-2G60-0001 | BATTERY LIMIT SUMMARY |  | Class 2 | Purpose** | IFR | 2019-04-24: IFR; 2019-04-25: IDD; 2019-05-01: IFF
[6 empty] | Rev. | A | bar: 2019-04-24
[6 empty] | Issue Plan | 2019-04-12 | 2019-04-25: 2019-11-15; 2019-05-01: 2020-08-15
[6 empty] | Revised Plan |  | 2019-04-25: 2019-11-15; 2019-05-01: 2020-08-15
[6 empty] | Issue Actual | 2019-02-28 | 2019-04-24: 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00948 | 2019-04-24: TPSK-LSPA1-T-PE-00948
[6 empty] | Return Date | 2019-04-10 | 2019-04-24: 2019-04-10
[6 empty] | Owner Cmmt* | R2 | bar: 2019-04-24
Category Code: G61 Equipment List |  |  |  |  | Class 2 | Purpose**
Category Code: G62 Utility Summary |  |  |  |  | Class 3 | Purpose**
| PE | OL1-2G62-1001 | STEAM BALANCE - DESIGN CASES |  | Class 3 | Purpose** | IFI | 2019-04-24: IFI
[6 empty] | Rev. | A | bar: 2019-04-24
[6 empty] | Issue Plan | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-09-17 | 2019-04-24: 2018-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00059 | 2019-04-24: TPSK-LSPA1-T-PE-00059
[6 empty] | Return Date | 2018-10-04 | 2019-04-24: 2018-10-04
Owner Cmmt*
| PE | OL1-2G62-1006 | COOLING WATER BALANCE - DESIGN CASES |  | Class 3 | Purpose** | IFI | 2019-04-24: IFI; 2019-04-25: IFF
[6 empty] | Rev. | A | bar: 2019-04-24
[6 empty] | Issue Plan | 2018-09-12 | 2019-04-25: 2020-04-30
[6 empty] | Revised Plan |  | 2019-04-25: 2020-04-30
[6 empty] | Issue Actual | 2018-09-17 | 2019-04-24: 2018-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00054 | 2019-04-24: TPSK-LSPA1-T-PE-00054
[6 empty] | Return Date | 2018-10-09 | 2019-04-24: 2018-10-09
[6 empty] | Owner Cmmt* | R2 | bar: 2019-04-24
| PE | OL1-2G62-1008 | FUEL BALANCE - DESIGN CASES |  | Class 3 | Purpose** | IFI | 2019-04-24: IFI
[6 empty] | Rev. | A | bar: 2019-04-24
[6 empty] | Issue Plan | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2018-09-13 | 2019-04-24: 2018-09-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00049 | 2019-04-24: TPSK-LSPA1-T-PE-00049
Return Date
Owner Cmmt*
| PE | OL1-2G62-1010 | AIR & NITROGEN BALANCES |  | Class 3 | Purpose** | IFI | 2019-04-24: IFI
[6 empty] | Rev. | 0 | 2019-04-24: 0
[6 empty] | Issue Plan | 2019-01-02
Revised Plan
[6 empty] | Issue Actual | 2019-05-10 | 2019-04-24: 2019-05-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01644 | 2019-04-24: TPSK-LSPA1-T-PE-01644
[6 empty] | Return Date | 2019-06-03 | 2019-04-24: 2019-06-03
[6 empty] | Owner Cmmt* | R2 | bar: 2019-04-24
| PE | OL1-2G62-1011 | ELECTRICAL LOAD SUMMARY |  | Class 3 | Purpose** | IFI
Rev.
[6 empty] | Issue Plan | 2019-01-04
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G63 Plant Efffluent Summary
| PE | OL1-2G63-0001 | Effluent Summary |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IFD | IFD | IDD | IFF
[6 empty] | Rev. | A | A | C | B | B | C
[6 empty] | Issue Plan | IFR: 2019-02-21; IFD: 2019-03-14; IDD: 2019-12-03; IFF: 2020-03-30
[6 empty] | Revised Plan | IDD: 2019-12-03; IFF: 2020-03-30
[6 empty] | Issue Actual | 2019-02-25 | 2019-02-26 |  | 2019-05-10 | 2019-05-13 | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00922 | TPSK-LSPA1-T-PE-00922 | TPSK-LSPA1-T-PE-02123 | TPSK-LSPA1-T-PE-01639 | TPSK-LSPA1-T-PE-01639 | TPSK-LSPA1-T-PE-02123
[6 empty] | Return Date | IFR: 2019-03-21; IFR: 2019-03-21; IFD: 2019-05-31; IFD: 2019-05-31
Owner Cmmt* | bar: IFR to IFR; IFD to IFD
Category Code: G64 Catalyst, Adsobent, and Chemicals Summary |  |  |  |  | Class 1 | Purpose**
| PE | OL1-2G64-1002 | Catalyst & Chemicals Summary |  | Class 2 | Purpose** | IFI | IFI | IFI | IFI | IFI | IFI | IFF
[6 empty] | Rev. | 0 | 0 | 1 | 1 | 2 | 2
[6 empty] | Issue Plan | IFR: 2019-02-07; IDD: 2019-12-13
[6 empty] | Revised Plan | IDD: 2019-12-13
[6 empty] | Issue Actual | 2019-03-25 | 2019-03-26 | 2019-05-14 | 2019-05-15 | 2019-07-02 | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01143 | TPSK-LSPA1-T-PE-01143 | TPSK-LSPA1-T-PE-01659 | TPSK-LSPA1-T-PE-01659 | TPSK-LSPA1-T-PE-02039 | TPSK-LSPA1-T-PE-02039
[6 empty] | Return Date | IFR: 2019-04-22; IFR: 2019-04-22; IFD: 2019-06-03; IFD: 2019-06-03
Owner Cmmt* | bar: IFR to IFD
Category Code: G70 Materials specification and; Utilities specfication and; Catalyst, Adsobent,; and Chemicals specification and ; Fluid and Solid properties
Category Code: G71 Effluent and Waste specification
Category Code: G72 Standard and Specification
Category Code: G73 Guide to Safe Handling of Material
Category Code: G74 Material Selection Guideline
| ME | OL1-2G74-0001 | Material Selection Diagram - Olefins Unit 10 - Legend & Notes |  | Class 2 | Purpose** | IFR: IFA; IFR: IFA; IFD: IFD
Rev. | bar: IFR to IFD
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-09; IFD: 2019-08-15
[6 empty] | Issue Actual | IFR: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFR: 2018-12-10
Owner Cmmt* | bar: IFR to IFR
| PE | OL1-2G74-1001 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 10 FEED PREPARATION - FEED PREHEAT |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-1003 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 10 FEED PREPARATION - FEEDSTOCK DISTRIBUTION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-1101 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 11 FURNACES - RECYCLE GAS CRACKING FURNACE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-1201 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 12 FURNACES - LIQUID CRACKING FURNACE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-1901 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 19 FEED PREPARATION & FURNACES AUX - DECOKE AIR COMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-1902 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 19 FEED PREPARATION & FURNACES AUX - CHEMICAL STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2001 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 20 QUENCH OIL - QUENCH OIL TOWER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2002 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 20 QUENCH OIL - HEAVY FUEL OIL STRIPPER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2101 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 21 QUENCH WATER / DILUTION STEAM - QUENCH WATER TOWER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2102 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 21 QUENCH WATER / DILUTION STEAM - QUENCH WATER CIRCUIT |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2103 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 21 QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2201 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 22 CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2301 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - CAUSTIC TOWER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2302 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC HANDLING |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2303 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2304 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC TREATMENT |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2305 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 23 CAUSTIC & SPENT CAUSTIC TREATMENT - WET AIR OXIDATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2401 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CG DEHYDRATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2402 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - REGENERATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2403 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2404 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2405 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 24 DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2501 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2502 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - RESIDUE GAS SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2503 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - DEMETHANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2504 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - DEETHANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2505 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - ETHYLENE FRACTIONATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2506 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 25 COLD FRACTIONATION - HYDROGEN PURIFICATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2601 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - C3 HYDROGENATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2602 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - SECONDARY DEETHANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2603 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - PROPYLENE FRACTIONATION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2604 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 26 HOT FRACTIONATION - DEBUTANIZER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2701 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - GHU-1 REACTOR & DEPENTANIZER |  | Class 1 | Purpose** | IFR: IFR; IFR: IFA; IFD: IFD; IFD: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFR: 2019-06-27; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02007
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G74-2702 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - GHU-1 RERUN TOWER |  | Class 1 | Purpose** | IFR: IFR; IFR: IFA; IFD: IFD; IFD: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFR: 2019-06-27; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02007
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G74-2703 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - HYDROG REACTIVATION GAS SYSTEM |  | Class 1 | Purpose** | IFR: IFR; IFR: IFA; IFD: IFD; IFD: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFR: 2019-06-27; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02013
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G74-2704 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION |  | Class 1 | Purpose** | IFR: IFR; IFR: IFA; IFD: IFD; IFD: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFR: 2019-06-27; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02013
Return Date
Owner Cmmt*
| PE | OL1-2G74-2801 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - PROPYLENE REFRIGERATION 1 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2802 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - PROPYLENE REFRIGERATION 2 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2803 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - ETHYLENE REFRIGERATION 1 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2804 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 28 REFRIGERATION SYSTEM - ETHYLENE REFRIGERATION 2 |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-2901 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 29 OLEFINS RECOVERY AUX - CHEMICAL STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2018-11-09; IFD: 2019-04-08; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-09; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-09; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-ME-00295; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2018-12-10; IFD: 2018-12-10
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-3001 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU PREDISTILLATION |  | Class 1 | Purpose** | IFR: IFR; IFR: IFA; IFD: IFD; IFD: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFR: 2019-06-27; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02013
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G74-3002 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU EVAPORATION |  | Class 1 | Purpose** | IFR: IFR; IFR: IFA; IFD: IFD; IFD: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFR: 2019-06-27; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02013
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G74-3003 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU RECTIFIER |  | Class 1 | Purpose** | IFR: IFR; IFR: IFA; IFD: IFD; IFD: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFR: 2019-06-27; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02013
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G74-3004 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU DEGASSING |  | Class 1 | Purpose** | IFR: IFR; IFR: IFA; IFD: IFD; IFD: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFR: 2019-06-27; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02013
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G74-3005 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU FRACTIONATION |  | Class 1 | Purpose** | IFR: IFR; IFR: IFA; IFD: IFD; IFD: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFR: 2019-06-27; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02013
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G74-3101 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 31 C4 UNIT UTILITIES - BDU SOLVENT REGENERATION |  | Class 1 | Purpose** | IFR: IFR; IFR: IFA; IFD: IFD; IFD: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFR: 2019-06-27; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02013
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G74-3102 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 31 C4 UNIT UTILITIES - BDU STEAM AND CONDENSATE SYSTEM |  | Class 1 | Purpose** | IFR: IFR; IFR: IFA; IFD: IFD; IFD: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFR: 2019-06-27; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02013
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G74-3901 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 39 C4 UNIT AUX - BDU CHEMICAL STORAGE |  | Class 1 | Purpose** | IFR: IFR; IFR: IFA; IFD: IFD; IFD: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFR: 2019-06-27; IFD: 2019-08-23; IFD: 2019-09-15
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02013
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G74-5001 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 50 WATER SYSTEMS - TREATED, POTABLE, AND DEMIN WATER SYSTEMS |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5101 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - STEAM BALANCE DIAGRAM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5102 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - CONDENSATE AND BOILER FEEDWATER SYSTEMS |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608, TPSK-LSPA1-T-PE-02428, TPSK-LSPA1-T-PE-02428; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5103 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - CONDENSATE TREATMENT SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608, TPSK-LSPA1-T-PE-02428, TPSK-LSPA1-T-PE-02428; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5104 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - FURNACE BLOWDOWN SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608, TPSK-LSPA1-T-PE-02428, TPSK-LSPA1-T-PE-02428; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5201 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 52 FUEL SYSTEM - FUEL GAS SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5301 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 53 COOLING WATER SYSTEM - COOLING WATER DIAGRAM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-29; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-29; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00399; IFD: TPSK-LSPA1-T-ME-00399; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2019-02-15; IFD: 2019-02-15
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-5311 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 53 COOLING WATER SYSTEM - COOLING TOWER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2018-11-29; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2018-11-29; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00399; IFD: TPSK-LSPA1-T-ME-00399; IFD: TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | IFR: 2019-02-15; IFD: 2019-02-15
Owner Cmmt* | bar: IFR to IFD
| PE | OL1-2G74-5401 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 54 AIR AND NITROGEN SYSTEM - PLANT AIR, INSTRUMENT AIR, AND NITROGEN SYSTEMS |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5501 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - FLARE AND BLOWDOWN SYSTEM |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5502 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - PROCESS VENT GAS COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5511 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - HP FLARE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5512 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - HP FLARE AREA |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5601 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OILY WASTEWATER COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5602 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SURFACE RUNOFF COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5603 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CRACKER HOLDING BASIN |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5604 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - DOMESTIC WASTEWATER COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| ME | OL1-2G74-5610 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - HP Flare Area SW & Oily WW Collection |  | Class 2 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5611 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OSBL OILY WASTEWATER COLLECTION |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5612 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OILY WASTEWATER EQUILIZATION TANK |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5613 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CPI & IGF PACKAGES |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5614 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - BIOTREATMENT PACKAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5615 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CHECK BASIN |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5616 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SLUDGE DEWATERING PACKAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5617 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SLOP AND OIL SLUDGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5901 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 59 UTILITIES AUX - CHEMICAL STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
| PE | OL1-2G74-5911 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 59 UTILITIES AUX - COMPLEX U & O CHEMICAL STORAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFF
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-04; IFD: 2019-06-15; IFD: 2019-09-15
[6 empty] | Revised Plan | IFD: 2019-01-08; IFD: 2019-09-15
[6 empty] | Issue Actual | IFD: 2019-01-08; IFD: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-ME-00608; IFD: TPSK-LSPA1-T-PE-02428
Return Date
Owner Cmmt*
Category Code: G75 Engineering Procedure
Category Code: G76 Supervisory Level Operating Procedures for all Process/Utility System(s). (Shall include Steady State, Stat-Up, Shutdown & transient Operations
| PE | OL1-2G76-1002 | BALANCE OF PLANT SUPERVISORY OPERATING MANUAL |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-19; IFR: 2019-08-30
[6 empty] | Revised Plan | IFR: 2019-09-12; IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G77 APC Functional specification
Category Code: G81 Appraisal Report for Consultancy Service
Category Code: G82 Appraisal Report for EPC Contractor Work
Category Code: G83 Appraisal Report for Vendor/Supplier
Category Code: G90 Vendor Document/drawings
Category Code: G91 Index/List
| PE | OL1-2G91-1001 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 10 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-18; IFD: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFD: 2019-09-09; IFD: 2020-08-15
[6 empty] | Issue Actual | IFR: 2019-06-28; IFR: 2019-06-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02020; IFR: TPSK-LSPA1-T-PE-02020
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-1002 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 10 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
[6 empty] | Revised Plan | IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1003 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 10 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1101 | PIPING SPECIALTY ITEM INDEX |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-01-10; IFD: 2019-02-20
[6 empty] | Revised Plan | IFD: 2019-09-10
[6 empty] | Issue Actual | IFR: 2019-05-10; IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-01642; IFR: TPSK-LSPA1-T-PE-01642
[6 empty] | Return Date | IFR: 2019-06-03; IFR: 2019-06-03
Owner Cmmt* | bar: IFR to IFR
| PE | OL1-2G91-1201 | PIPING SPECIALTY ITEM INDEX |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-01-10; IFD: 2019-02-20
[6 empty] | Revised Plan | IFD: 2019-09-10
[6 empty] | Issue Actual | IFR: 2019-05-10; IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-01642; IFR: TPSK-LSPA1-T-PE-01642
[6 empty] | Return Date | IFR: 2019-06-03; IFR: 2019-06-03
Owner Cmmt* | bar: IFR to IFR
| PE | OL1-2G91-1901 | Piping Specialty Item - Datasheet Index - Furnace Auxiliaries - Area 19 |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-28; IFR: 2019-06-28
[6 empty] | Issue Actual | IFR: 2019-06-28; IFR: 2019-06-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02020; IFR: TPSK-LSPA1-T-PE-02020
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-2001 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 20 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-18; IFD: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFD: 2019-09-09; IFD: 2020-08-15
[6 empty] | Issue Actual | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02055; IFR: TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-2002 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 20 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
[6 empty] | Revised Plan | IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2003 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 20 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2101 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 21 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-18; IFD: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFD: 2019-09-09; IFD: 2020-08-15
[6 empty] | Issue Actual | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02055; IFR: TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-2102 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 21 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
[6 empty] | Revised Plan | IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2103 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 21 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2201 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 22 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-18; IFD: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFD: 2019-09-09; IFD: 2020-08-15
[6 empty] | Issue Actual | IFR: 2019-06-26; IFR: 2019-06-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-01991; IFR: TPSK-LSPA1-T-PE-01991
[6 empty] | Return Date | IFR: 2019-07-11; IFR: 2019-07-11
Owner Cmmt* | bar: IFR to IFR
| PE | OL1-2G91-2202 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 22 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
[6 empty] | Revised Plan | IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2203 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 22 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2301 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 23 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-18; IFD: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFD: 2019-09-09; IFD: 2020-08-15
[6 empty] | Issue Actual | IFR: 2019-06-26; IFR: 2019-06-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-01992; IFR: TPSK-LSPA1-T-PE-01992
[6 empty] | Return Date | IFR: 2019-07-11; IFR: 2019-07-11
Owner Cmmt* | bar: IFR to IFR
| PE | OL1-2G91-2302 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 23 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
[6 empty] | Revised Plan | IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2303 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 23 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2401 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 24 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFR: 2019-08-16; IFR: 2019-09-09; IFD: 2020-08-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2402 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 24 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
[6 empty] | Revised Plan | IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2403 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 24 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2501 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 25 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-18; IFD: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFD: 2019-09-09; IFD: 2020-08-15
[6 empty] | Issue Actual | IFR: 2019-06-28; IFR: 2019-06-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02020; IFR: TPSK-LSPA1-T-PE-02020
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-2502 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 25 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
[6 empty] | Revised Plan | IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2503 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 25 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2601 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 26 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-18; IFD: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFD: 2019-09-09; IFD: 2020-08-15
[6 empty] | Issue Actual | IFR: 2019-06-28; IFR: 2019-06-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02020; IFR: TPSK-LSPA1-T-PE-02020
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-2602 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 26 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
[6 empty] | Revised Plan | IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2603 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 26 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2701 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 27 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-18; IFD: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFD: 2019-09-09; IFD: 2020-08-15
[6 empty] | Issue Actual | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02055; IFR: TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-2702 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 27 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
[6 empty] | Revised Plan | IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2703 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 27 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2801 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 28 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-18; IFD: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFD: 2019-09-09; IFD: 2020-08-15
[6 empty] | Issue Actual | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02055; IFR: TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-2802 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 28 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
[6 empty] | Revised Plan | IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2803 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 28 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2901 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 29 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-18; IFD: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFD: 2019-09-09; IFD: 2020-08-15
[6 empty] | Issue Actual | IFR: 2019-06-28; IFR: 2019-06-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02020; IFR: TPSK-LSPA1-T-PE-02020
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-2902 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 29 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
[6 empty] | Revised Plan | IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2903 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 29 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-3001 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 30 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-18; IFD: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFD: 2019-09-09; IFD: 2020-08-15
[6 empty] | Issue Actual | IFR: 2019-07-08; IFR: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02085; IFR: TPSK-LSPA1-T-PE-02085
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-3002 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 30 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
[6 empty] | Revised Plan | IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-3003 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 30 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-3101 | Piping Specialty Item - Datasheet Index - Butadiene Extraction Unit Utilities - Area 31 |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-08; IFR: 2019-07-08
[6 empty] | Issue Actual | IFR: 2019-07-08; IFR: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02085; IFR: TPSK-LSPA1-T-PE-02085
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-3901 | Piping Specialty Item - Datasheet Index - Butadiene Extraction Unit Auxiliaries - Area 39 |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-08; IFR: 2019-07-08
[6 empty] | Issue Actual | IFR: 2019-07-08; IFR: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02085; IFR: TPSK-LSPA1-T-PE-02085
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-5001 | PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 50 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-18; IFD: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFD: 2019-09-09; IFD: 2020-08-15
[6 empty] | Issue Actual | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02055; IFR: TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-5002 | PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 50 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
[6 empty] | Revised Plan | IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5003 | RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 50 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5101 | Piping Specialty Item - Datasheet Index - BFW-Steam-Steam Condensation System - Area 51 |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02055; IFR: TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-5201 | Piping Specialty Item - Datasheet Index - Fuel Gas System - Area 52 |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02055; IFR: TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-5301 | PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 53 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-18; IFD: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFD: 2019-09-09; IFD: 2020-08-15
[6 empty] | Issue Actual | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02055; IFR: TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-5302 | PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 53 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5303 | RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 53 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5401 | Piping Specialty Item - Datasheet Index - Plant Air-Instrument Air-Nitrogen - Area 54 |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02055; IFR: TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-5501 | PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 55 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-18; IFD: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFD: 2019-09-09; IFD: 2020-08-15
[6 empty] | Issue Actual | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02055; IFR: TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-5502 | PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 55 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
[6 empty] | Revised Plan | IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5503 | RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 55 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5601 | PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 56 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD; IFD: IFF
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-18; IFD: 2019-05-16; IFD: 2020-08-15
[6 empty] | Revised Plan | IFD: 2019-09-09; IFD: 2020-08-15
[6 empty] | Issue Actual | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02055; IFR: TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| PE | OL1-2G91-5602 | PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 56 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-06; IFR: 2019-06-13
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5603 | RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 56 |  | Class 1 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-18; IFR: 2019-12-03; IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-12-03; IFD: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5901 | Piping Specialty Item - Datasheet Index - Supporting Utilities Auxiliaries - Area 59 |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03; IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02055; IFR: TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
Category Code: G92 Procedures & Standards
Category Code: G93 Policy , Guidelines & Memo
Category Code: G94 Forms & Templates
Category Code: G95 Progress/Status Reports
Category Code: H01 Design basis
Category Code: H02 Abbreviation and standard symbols
Category Code: H03 Project HVAC specification
| EE | OL1-2H03-0002 | JOB SUPPLY SPEC. FOR HVAC SYSTEMS |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IMP
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-06-30; IFD: 2019-07-29
[6 empty] | Revised Plan | IFD: 2019-08-20
[6 empty] | Issue Actual | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02147; IFR: TPSK-LSPA1-T-EE-02147
[6 empty] | Return Date | IFR: 2019-07-31
Owner Cmmt* | bar: IFR
Category Code: H04 Equipment, material specification
Category Code: H05 Equipment datasheet
Category Code: H10 Calculation
| EE | OL1-2H10-0001 | HVAC THERMAL CALC. - ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-06-30; IFD: 2019-07-29
[6 empty] | Revised Plan | IFD: 2019-09-16
[6 empty] | Issue Actual | IFR: 2019-04-23; IFR: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-01442; IFR: TPSK-LSPA1-T-EE-01442
[6 empty] | Return Date | IFR: 2019-05-17; IFR: 2019-05-17
Owner Cmmt* | bar: IFR to IFR
| EE | OL1-2H10-0002 | HVAC THERMAL CALC. - ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-06-30; IFD: 2019-07-29
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-04-23; IFR: 2019-04-24; IFD: 2019-08-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-01446; IFR: TPSK-LSPA1-T-EE-01446; IFD: TPSK-LSPA1-T-EE-02369
[6 empty] | Return Date | IFR: 2019-05-17; IFR: 2019-05-17
Owner Cmmt* | bar: IFR to IFR
| EE | OL1-2H10-0003 | HVAC THERMAL CALC. - GATEHOUSE |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IDD
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-05-02; IFD: 2019-06-01
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-04-08; IFR: 2019-04-09; IFD: 2019-07-04; IFD: 2019-07-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-01273; IFR: TPSK-LSPA1-T-EE-01273; IFD: TPSK-LSPA1-T-EE-02068; IFD: TPSK-LSPA1-T-EE-02068
[6 empty] | Return Date | IFR: 2019-05-07; IFR: 2019-05-07; IFD: 2019-07-17
Owner Cmmt* | bar: IFR to IFR; IFD
| EE | OL1-2H10-0004 | HVAC THERMAL CALC. - OPERATION TOOL ROOM |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IDD
Rev. | bar: IFR to IFD
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-08; IFR: 2019-04-09; IFD: 2019-07-04; IFD: 2019-07-04
[6 empty] | Issue Actual | IFR: 2019-04-08; IFR: 2019-04-09; IFD: 2019-07-04; IFD: 2019-07-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-01273; IFR: TPSK-LSPA1-T-EE-01273; IFD: TPSK-LSPA1-T-EE-02068; IFD: TPSK-LSPA1-T-EE-02068
[6 empty] | Return Date | IFR: 2019-05-07; IFR: 2019-05-07; IFD: 2019-07-17
Owner Cmmt* | bar: IFR to IFR; IFD
| EE | OL1-2H10-0005 | Electrical SUB-F & FAR-F – HVAC Thermal Calculation |  | Class As Built | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-06-30; IFD: 2019-07-29
[6 empty] | Revised Plan | IFD: 2019-09-16
[6 empty] | Issue Actual | IFR: 2019-04-23; IFR: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-01446; IFR: TPSK-LSPA1-T-EE-01446
[6 empty] | Return Date | IFR: 2019-05-17; IFR: 2019-05-17
Owner Cmmt* | bar: IFR to IFR
Category Code: H20 System schematic diagram
| EE | OL1-2H20-0001 | HVAC PROCESS FLOW DIAGRAM - ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-06-30; IFD: 2019-07-29
[6 empty] | Revised Plan | IFD: 2019-09-16
[6 empty] | Issue Actual | IFR: 2019-04-18; IFR: 2019-04-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-01416; IFR: TPSK-LSPA1-T-EE-01416
[6 empty] | Return Date | IFR: 2019-05-17; IFR: 2019-05-17
Owner Cmmt* | bar: IFR to IFR
| EE | OL1-2H20-0003 | HVAC PROCESS FLOW DIAGRAM - ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-06-30; IFD: 2019-07-29
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-04-23; IFR: 2019-04-24; IFD: 2019-08-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-01454; IFR: TPSK-LSPA1-T-EE-01454; IFD: TPSK-LSPA1-T-EE-02371
[6 empty] | Return Date | IFR: 2019-05-17; IFR: 2019-05-17
Owner Cmmt* | bar: IFR to IFR
| EE | OL1-2H20-0005 | HVAC PROCESS FLOW DIAGRAM - GATEHOUSE |  | Class 2 | Purpose** | IFR: IFR; IFR: IDD
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-30; IFR: 2019-07-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2H20-0010 | Electrical Sub-F- And Far-F - HVAC Process Flow Diagram |  | Class As Built | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-06-30; IFD: 2019-07-29
[6 empty] | Revised Plan | IFD: 2019-09-16
[6 empty] | Issue Actual | IFR: 2019-04-23; IFR: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-01454; IFR: TPSK-LSPA1-T-EE-01454
[6 empty] | Return Date | IFR: 2019-05-17; IFR: 2019-05-17
Owner Cmmt* | bar: IFR to IFR
Category Code: H21 Arrangement drawing
| EE | OL1-2H21-0001 | HVAC LAYOUT- ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-06-30; IFD: 2019-07-29
[6 empty] | Revised Plan | IFD: 2019-09-16
[6 empty] | Issue Actual | IFR: 2019-04-18; IFR: 2019-04-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-01417; IFR: TPSK-LSPA1-T-EE-01417
[6 empty] | Return Date | IFR: 2019-05-17; IFR: 2019-05-17
Owner Cmmt* | bar: IFR to IFR
| EE | OL1-2H21-0005 | HVAC LAYOUT- ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-06-30; IFD: 2019-07-29
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-04-23; IFR: 2019-04-24; IFD: 2019-08-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-01453; IFR: TPSK-LSPA1-T-EE-01453; IFD: TPSK-LSPA1-T-EE-02370
[6 empty] | Return Date | IFR: 2019-05-17; IFR: 2019-05-17
Owner Cmmt* | bar: IFR to IFR
| EE | OL1-2H21-0010 | HVAC LAYOUT- GATEHOUSE |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IDD
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-05-02; IFD: 2019-06-01
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-04-04; IFR: 2019-04-05; IFD: 2019-07-03; IFD: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-1238; IFR: TPSK-LSPA1-T-EE-1238; IFD: TPSK-LSPA1-T-EE-02053; IFD: TPSK-LSPA1-T-EE-02053
[6 empty] | Return Date | IFD: 2019-07-17
Owner Cmmt* | bar: IFD
| EE | OL1-2H21-0011 | Prefabricated Gatehouse - HVAC Layout And Process Flow Diagram |  | Class As Built | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IDD
Rev. | bar: IFR to IFD
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-04; IFR: 2019-04-05; IFD: 2019-07-03; IFD: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-04-04; IFR: 2019-04-05; IFD: 2019-07-03; IFD: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-1238; IFR: TPSK-LSPA1-T-EE-1238; IFD: TPSK-LSPA1-T-EE-02053; IFD: TPSK-LSPA1-T-EE-02053
[6 empty] | Return Date | IFD: 2019-07-17
Owner Cmmt* | bar: IFD
| EE | OL1-2H21-0015 | HVAC LAYOUT- OPERATION TOOL ROOM |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IDD
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-05-02; IFD: 2019-06-01
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-04-04; IFR: 2019-04-05; IFD: 2019-07-03; IFD: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-1238; IFR: TPSK-LSPA1-T-EE-1238; IFD: TPSK-LSPA1-T-EE-02053; IFD: TPSK-LSPA1-T-EE-02053
[6 empty] | Return Date | IFD: 2019-07-17
Owner Cmmt* | bar: IFD
| EE | OL1-2H21-0020 | Electrical Sub-F- And Far-F - HVAC Layout |  | Class As Built | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-06-30; IFD: 2019-07-29
[6 empty] | Revised Plan | IFD: 2019-09-16
[6 empty] | Issue Actual | IFR: 2019-04-23; IFR: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-01453; IFR: TPSK-LSPA1-T-EE-01453
[6 empty] | Return Date | IFR: 2019-05-17; IFR: 2019-05-17
Owner Cmmt* | bar: IFR to IFR
Category Code: H22 Electrical and control drawing/ document
Category Code: H60 Cable drum schedule
Category Code: H61 Cable schedule
Category Code: H62 Connection list
Category Code: H63 Construction material and Bill of quantities
Category Code: H64 Typical installation drawing
Category Code: H71 Appraisal Report for Consultancy Service
Category Code: H72 Appraisal Report for EPC Contractor Work
Category Code: H73 Appraisal Report for Vendor/Supplier
Category Code: H90 Vendor documents
Category Code: H91 Index/List
Category Code: H92 Procedures & Standards
Category Code: H93 Policy , Guidelines & Memo
Category Code: H94 Forms & Templates
Category Code: H95 Progress/Status Reports
Category Code: I10 MAC FEED Document
Category Code: I20 Instrument datasheet
| IE | OL1-2I20-0101 | D/S MECHANICAL RESTRICTION ORIFICE AND ORIFICE |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-02-09; IFR: 2019-09-04
[6 empty] | Revised Plan | IFR: 2019-08-30; IFR: 2019-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0102 | DATA SHEET FOR PITOT TUBE |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-02-09; IFR: 2019-09-04
[6 empty] | Revised Plan | IFR: 2019-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0103 | D/S MECHANICAL ELECTROMAGNETIC FLOW METER |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-02-09; IFR: 2019-09-04
[6 empty] | Revised Plan | IFR: 2019-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0104 | D/S MECHANICAL ROTAMETERS |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-02-09; IFR: 2019-09-04
[6 empty] | Revised Plan | IFR: 2019-08-30; IFR: 2019-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0106 | D/S MECHANICAL MASS FLOW MET.CORIOLIS EFFECT |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-02-09; IFR: 2019-09-04
[6 empty] | Revised Plan | IFR: 2019-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0107 | D/S MECHANICAL VENTURI |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-02-09; IFR: 2019-09-04
[6 empty] | Revised Plan | IFR: 2019-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0108 | D/S MECHANICAL ULTRASONIC FLOW METER |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-02-09; IFR: 2019-09-04
[6 empty] | Revised Plan | IFR: 2019-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0112 | D/S MECHANICAL VORTEX METER |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-02-09; IFR: 2019-09-04
[6 empty] | Revised Plan | IFR: 2019-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0120 | DATA SHEET FOR CUSTODY TRANSFER METERING |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-26; IFR: 2019-11-30
[6 empty] | Revised Plan | IFR: 2019-09-06; IFR: 2019-11-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0202 | D/S MECHANICAL MAGNETIC LEVEL GAUGE |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-20; IFR: 2020-07-12
[6 empty] | Revised Plan | IFR: 2019-12-20; IFR: 2020-07-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0203 | D/S MECHANICAL RADAR LEVEL INSTRUMENTS |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-20; IFR: 2020-07-12
[6 empty] | Revised Plan | IFR: 2019-12-20; IFR: 2020-07-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0211 | D/S MECHANICAL SPECIAL LEVEL TRANSMITTERS |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-20; IFR: 2020-07-12
[6 empty] | Revised Plan | IFR: 2019-12-20; IFR: 2020-07-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0212 | D/S MECHANICAL LEVEL GLASS |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-20; IFR: 2020-07-12
[6 empty] | Revised Plan | IFR: 2019-12-20; IFR: 2020-07-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0301 | D/S MECHANICAL PRESSURE & DIFFER.PRESS.GAUGE |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-05; IFR: 2020-09-05
[6 empty] | Revised Plan | IFR: 2020-02-05; IFR: 2020-09-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0302 | DATA SHEET FOR THERMOCOUPLE/RTD WITH WELL |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-05; IFR: 2020-05-26
[6 empty] | Revised Plan | IFR: 2020-02-05; IFR: 2020-05-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0304 | D/S MECHANICAL THERMOMETER WITH WELL |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-05; IFR: 2020-05-26
[6 empty] | Revised Plan | IFR: 2020-02-05; IFR: 2020-05-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0305 | DATA SHEET FOR MULTIPLE THERMOCOUPLE / RTD |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-05; IFR: 2020-05-26
[6 empty] | Revised Plan | IFR: 2020-02-05; IFR: 2020-05-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0501 | D/S MECHANICAL CONTROL VALVES |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-28; IFR: 2019-11-13
[6 empty] | Revised Plan | IFR: 2019-11-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0503 | D/S MECHANICAL SPECIAL CONTROL VALVE |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-28; IFR: 2019-11-13
[6 empty] | Revised Plan | IFR: 2019-11-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0504 | D/S MECHANICAL SEVERE SERVICE CONTROL VALVE |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-28; IFR: 2019-11-13
[6 empty] | Revised Plan | IFR: 2019-09-30; IFR: 2019-11-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0505 | D/S ANTISURGE VALVES |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-28; IFR: 2019-11-13
[6 empty] | Revised Plan | IFR: 2019-09-30; IFR: 2019-11-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0506 | D/S MECHANICAL DESUPERHEATER VALVES |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-28; IFR: 2019-11-13
[6 empty] | Revised Plan | IFR: 2019-09-30; IFR: 2019-11-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0606 | D/S MECHANICAL PNEUMATIC ON OFF VALVES |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-28; IFR: 2019-11-13
[6 empty] | Revised Plan | IFR: 2019-11-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0608 | D/S MECHANICAL SPECIAL ON OFF VALVES |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-28; IFR: 2019-11-13
[6 empty] | Revised Plan | IFR: 2019-11-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0609 | D/S MECHANICAL ELECTRIC OPERATED VALVES |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-28; IFR: 2019-11-13
[6 empty] | Revised Plan | IFR: 2019-11-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0701 | D/S MECHANICAL SAFETY RELIEF VALVE & RUPTURE DISKS |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-31; IFR: 2019-10-29
[6 empty] | Revised Plan | IFR: 2019-10-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0801 | D/S MECHANICAL ELECTRONIC TRANSMITTER |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-05; IFR: 2020-09-05
[6 empty] | Revised Plan | IFR: 2020-02-05; IFR: 2020-09-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1001 | CONTROL VALVE DATASHEETS |  | Class 1 | Purpose** | IFR | IFA | IFA | IFQ | IFP
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-02-25; IFD: 2019-04-03; IFD: 2019-05-10
[6 empty] | Revised Plan | IFR: 2019-03-21; IFD: 2019-03-22; IFD: 2019-08-30
[6 empty] | Issue Actual | IFR: 2019-03-21; IFD: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01130; IFD: TPSK-LSPA1-T-IE-01130
[6 empty] | Return Date | IFR: 2019-04-02; IFD: 2019-04-02
Owner Cmmt* | bar: IFR to IFD
| IE | OL1-2I20-1002 | INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  | Class 2 | Purpose** | IFR: IFP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02350
Return Date
Owner Cmmt*
| IE | OL1-2I20-1005 | INSTRUMENT LEVEL GAUGE DATASHEET |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFQ; IFD: IFP
[6 empty] | Rev. | IFR: A; IFR: A; IFD: 0
[6 empty] | Issue Plan | IFR: 2019-08-06; IFD: 2019-09-20; IFD: 2019-11-05
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-03-13; IFR: 2019-03-14; IFD: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01047; IFR: TPSK-LSPA1-T-IE-01047; IFD: TPSK-LSPA1-T-IE-02414
[6 empty] | Return Date | IFR: 2019-03-27; IFR: 2019-03-27
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-1006 | D/P LEVEL TRANSMITTERS |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFQ; IFD: IFP
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-08-06; IFD: 2019-09-20; IFD: 2019-11-05
[6 empty] | Revised Plan | IFD: 2019-11-05
[6 empty] | Issue Actual | IFR: 2019-04-09; IFR: 2019-04-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01288; IFR: TPSK-LSPA1-T-IE-01288
[6 empty] | Return Date | IFR: 2019-05-13; IFR: 2019-05-13
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-1007 | DATA SHEET FOR PRESSURE GAUGES |  | Class 2 | Purpose** | IFR: IFR; IFR: IFQ; IFD: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-01; IFR: 2019-08-14; IFD: 2019-09-27
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-09-27; IFD: 2019-09-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1008 | DATA SHEET FOR DRAFT PRESSURE GAUGES |  | Class 2 | Purpose** | IFR: IFR; IFR: IFQ; IFD: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-01; IFR: 2019-08-14; IFD: 2019-09-27
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-09-27; IFD: 2019-09-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1009 | PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  | Class 2 | Purpose** | IFR: IFR; IFR: IFQ; IFD: IFQ; IFD: IFP
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-07-01; IFR: 2019-08-14; IFD: 2019-09-27
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-09-27; IFD: 2019-09-27
[6 empty] | Issue Actual | IFR: 2019-05-20; IFD: 2019-05-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01692; IFD: TPSK-LSPA1-T-IE-01692
[6 empty] | Return Date | IFR: 2019-06-17; IFD: 2019-06-17
Owner Cmmt* | bar: IFR to IFD
| IE | OL1-2I20-1010 | TEMPERATURE ELEMENTS FOR FURNACE PROFILE DATA SHEET |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01658; IFR: TPSK-LSPA1-T-IE-01658
[6 empty] | Return Date | IFR: 2019-07-17
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1011 | TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  | Class 2 | Purpose** | IFR | IFR | IFQ | IFQ | IFP
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-08-06; IFD: 2019-09-20; IFD: 2019-11-05
[6 empty] | Revised Plan | IFD: 2019-11-05
[6 empty] | Issue Actual | IFR: 2019-04-10; IFR: 2019-04-11; IFD: 2019-05-23; IFD: 2019-05-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01309; IFR: TPSK-LSPA1-T-IE-01309; IFD: TPSK-LSPA1-T-IE-01729; IFD: TPSK-LSPA1-T-IE-01729
[6 empty] | Return Date | IFD: 2019-07-17
Owner Cmmt* | bar: IFD
| IE | OL1-2I20-1012 | TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  | Class 2 | Purpose** | IFR: IFR; IFR: IFQ; IFD: IFQ; IFD: IFP
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-08-06; IFR: 2019-09-20; IFD: 2019-11-05
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-09-20; IFD: 2019-11-05
[6 empty] | Issue Actual | IFR: 2019-05-14; IFD: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01660; IFD: TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | IFR: 2019-06-17; IFD: 2019-06-17
Owner Cmmt* | bar: IFR to IFD
| IE | OL1-2I20-1013 | TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  | Class 2 | Purpose** | IFR: IFR; IFR: IFQ; IFD: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-06; IFR: 2019-09-20; IFD: 2019-11-05
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-09-20; IFD: 2019-11-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1014 | TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  | Class 2 | Purpose** | IFR: IFR; IFR: IFQ; IFD: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-06; IFR: 2019-09-20; IFD: 2019-11-05
[6 empty] | Revised Plan | IFR: 2019-08-23; IFR: 2019-09-20; IFD: 2019-11-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1015 | INSTRUMENT PH AND CONDUCTIVITY ANALYZER DATASHEETS |  | Class 2 | Purpose** | IFR | IFR | IFQ | IFQ | IFP
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-08-06; IFD: 2019-09-20; IFD: 2019-11-05
[6 empty] | Revised Plan | IFD: 2019-11-05
[6 empty] | Issue Actual | IFR: 2019-03-21; IFR: 2019-03-22; IFD: 2019-05-23; IFD: 2019-05-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01131; IFR: TPSK-LSPA1-T-IE-01131; IFD: TPSK-LSPA1-T-IE-01730; IFD: TPSK-LSPA1-T-IE-01730
[6 empty] | Return Date | IFR: 2019-04-02; IFR: 2019-04-02; IFD: 2019-06-13; IFD: 2019-06-13
Owner Cmmt* | bar: IFR to IFD
| IE | OL1-2I20-1016 | O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  | Class 2 | Purpose** | IFR: IFR; IFR: IFI; IFD: IFQ; IFD: IFP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-05-09; IFD: 2019-06-22; IFD: 2019-08-05
[6 empty] | Revised Plan | IFR: 2019-07-25; IFD: 2019-11-08
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02258
Return Date
Owner Cmmt*
| IE | OL1-2I20-1022 | Instrument Datasheets for Flow Element -Orifice - Area 10 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-14; IFR: 2019-05-15
[6 empty] | Issue Actual | IFR: 2019-05-14; IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01660; IFR: TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-1101 | Instrument Datasheets for Control Valve -Globe Type- Area 11 -BOP |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-06; IFR: 2019-05-07
[6 empty] | Issue Actual | IFR: 2019-05-06; IFR: 2019-05-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01581; IFR: TPSK-LSPA1-T-IE-01581
Return Date
Owner Cmmt*
| IE | OL1-2I20-1106 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 11 -BOP |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01594; IFR: TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1111 | Instrument Datasheets for ON-OFF Valve Ball Type - Area 11 BOP |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01594; IFR: TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1112 | Instrument Datasheets for ON-OFF Valve Butterfly Type - Area 11 BOP |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01594; IFR: TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1122 | Instrument Datasheets for Flow Element Orifice- Area 11 -BOP |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-08; IFR: 2019-05-09
[6 empty] | Issue Actual | IFR: 2019-05-08; IFR: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01615; IFR: TPSK-LSPA1-T-IE-01615
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1125 | Instrument Data Sheets Flow Element Pitot Furmace Area 10-H-1100 |  | Class 2 | Purpose** | IFR: IFI; IFR: IFI
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-24; IFR: 2019-06-24
[6 empty] | Issue Actual | IFR: 2019-06-24; IFR: 2019-06-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01965; IFR: TPSK-LSPA1-T-IE-01965
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1127 | Instrument Datasheets for Flow Instrument -Vortex-Area 11 -BOP |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01594; IFR: TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1151 | Instrument Datasheets for O2 & Combustible Analyzer |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFQ; IFD: IFQ
Rev. | bar: IFR to IFD
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-29; IFR: 2019-05-30; IFD: 2019-06-25; IFD: 2019-06-25
[6 empty] | Issue Actual | IFR: 2019-05-29; IFR: 2019-05-30; IFD: 2019-06-25; IFD: 2019-06-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01761; IFR: TPSK-LSPA1-T-IE-01761; IFD: TPSK-LSPA1-T-IE-01976; IFD: TPSK-LSPA1-T-IE-01976
[6 empty] | Return Date | IFR: 2019-06-21; IFR: 2019-06-21; IFD: 2019-07-31
Owner Cmmt* | bar: IFR to IFD
| IE | OL1-2I20-1152 | Instrument Datasheets for Orifice Plate |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02217
Return Date
Owner Cmmt*
| IE | OL1-2I20-1153 | Instrument Datasheets for Restriction Orifice |  | Class 2 | Purpose** | IFR: IFR; IFR: IFQ; IFD: IFQ; IFD: IFP
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-11; IFR: 2019-04-17; IFD: 2019-05-24
[6 empty] | Revised Plan | IFD: 2019-08-26
[6 empty] | Issue Actual | IFR: 2019-06-12; IFD: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01879; IFD: TPSK-LSPA1-T-IE-01879
[6 empty] | Return Date | IFD: 2019-07-08
Owner Cmmt* | bar: IFD
| IE | OL1-2I20-1156 | Instrument Datasheets for Pressure Indicating Transmitters & Flow Indicating DP Transmitters |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02222
Return Date
Owner Cmmt*
| IE | OL1-2I20-1160 | Instrument Datasheets for Magnetostrictive Level Transmitter & Magnetic Level Gauge |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-21; IFR: 2019-06-21
[6 empty] | Issue Actual | IFR: 2019-06-21; IFR: 2019-06-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01953; IFR: TPSK-LSPA1-T-IE-01953
[6 empty] | Return Date | IFR: 2019-07-31
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1161 | Instrument Datasheets for Temperature Elements for Furnace Profile |  | Class 2 | Purpose** | IFR: IFR; IFR: IFQ; IFD: IFQ; IFD: IFP
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-08-06; IFR: 2019-09-20; IFD: 2019-11-05
[6 empty] | Revised Plan | IFD: 2019-11-05
[6 empty] | Issue Actual | IFR: 2019-06-25; IFD: 2019-06-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01975; IFD: TPSK-LSPA1-T-IE-01975
[6 empty] | Return Date | IFR: 2019-07-31
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1162 | Instrument Datasheets for Flow Element Venturi |  | Class 2 | Purpose** | IFR | IFR | IFQ | IFQ | IFP
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-03-11; IFD: 2019-04-17; IFD: 2019-05-24
[6 empty] | Revised Plan | IFD: 2019-08-26
[6 empty] | Issue Actual | IFR: 2019-05-28; IFR: 2019-05-29; IFD: 2019-06-27; IFD: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01757; IFR: TPSK-LSPA1-T-IE-01757; IFD: TPSK-LSPA1-T-IE-02006; IFD: TPSK-LSPA1-T-IE-02006
[6 empty] | Return Date | IFR: 2019-06-21; IFR: 2019-06-21; IFD: 2019-07-31
Owner Cmmt* | bar: IFR to IFD
| IE | OL1-2I20-1164 | Instrument Datasheets for Guided Wave Radar Level Transmitter & Magnetic Level Gauge |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-21; IFR: 2019-06-21
[6 empty] | Issue Actual | IFR: 2019-06-21; IFR: 2019-06-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01948; IFR: TPSK-LSPA1-T-IE-01948
[6 empty] | Return Date | IFR: 2019-07-31
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1201 | Instrument Datasheets for Control Valve - Globe Type Area 12 -BOP |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01594; IFR: TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1206 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 12 - BOP |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01594; IFR: TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1211 | Instrument Datasheets for ON-OFF Valve -Ball Type -Area 12 -BOP |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-08; IFR: 2019-05-09
[6 empty] | Issue Actual | IFR: 2019-05-08; IFR: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01615; IFR: TPSK-LSPA1-T-IE-01615
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1212 | Instrument Datasheets for ON-OFF Valve -Butterfly Type - Area 12 -BOP |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-08; IFR: 2019-05-09
[6 empty] | Issue Actual | IFR: 2019-05-08; IFR: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01615; IFR: TPSK-LSPA1-T-IE-01615
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1222 | Instrument Datasheets for Flow Element -Orifice- Area 12 -BOP |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01594; IFR: TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1225 | Instrument Data Sheets For Flow Element Pitot Furmace Area 10-H-1200 |  | Class 2 | Purpose** | IFR: IFI; IFR: IFI
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-24; IFR: 2019-06-24
[6 empty] | Issue Actual | IFR: 2019-06-24; IFR: 2019-06-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01965; IFR: TPSK-LSPA1-T-IE-01965
[6 empty] | Return Date | IFR: 2019-07-23
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1227 | Instrument Datasheets for Flow Instrument -Vortex - Area 12 - BOP |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-08; IFR: 2019-05-09
[6 empty] | Issue Actual | IFR: 2019-05-08; IFR: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01615; IFR: TPSK-LSPA1-T-IE-01615
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-1906 | Instrument Datasheets for Self Actuated pressure Control Valve Area 19 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-20; IFR: 2019-05-21
[6 empty] | Issue Actual | IFR: 2019-05-20; IFR: 2019-05-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01692; IFR: TPSK-LSPA1-T-IE-01692
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-1911 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 19 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-14; IFR: 2019-05-15
[6 empty] | Issue Actual | IFR: 2019-05-14; IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01660; IFR: TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-1916 | Instrument Datasheets for Pressure Safety Valve - Area 19 |  | Class 2 | Purpose** | IFR: IFI
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02258
Return Date
Owner Cmmt*
| IE | OL1-2I20-2001 | CONTROL VALVE DATASHEETS |  | Class 1 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01650; IFR: TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | IFR: 2019-06-13; IFR: 2019-06-13
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2002 | INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Issue Actual | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01625; IFR: TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | IFR: 2019-07-17
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2006 | D/P LEVEL TRANSMITTERS |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Issue Actual | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01625; IFR: TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | IFR: 2019-07-17
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2011 | TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Issue Actual | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01625; IFR: TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | IFR: 2019-07-17
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2012 | TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Issue Actual | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01625; IFR: TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | IFR: 2019-07-17
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2016 | O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02291
Return Date
Owner Cmmt*
| IE | OL1-2I20-2022 | Instrument Datasheets for Flow Element - Orifice - Area 20 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01650; IFR: TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | IFR: 2019-06-13; IFR: 2019-06-13
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2024 | Instrument Datasheets for Flow Element -Flow Nozzle -Area 20 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01650; IFR: TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | IFR: 2019-06-13; IFR: 2019-06-13
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2026 | Instrument Datasheets for Flow Element -Wedge Type-Area 20 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01650; IFR: TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | IFR: 2019-06-13; IFR: 2019-06-13
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2028 | Instrument Datasheets for Flow Element - Rotameter - Area 20 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-14; IFR: 2019-05-15
[6 empty] | Issue Actual | IFR: 2019-05-14; IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01660; IFR: TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2032 | Instrument Datasheets for Flow Element -Integral Orifice- Area 20 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01650; IFR: TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | IFR: 2019-06-13; IFR: 2019-06-13
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2100 | D/S MECHANICAL CHROMATOGRAPH |  |  | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-30
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02277
Return Date
Owner Cmmt*
| IE | OL1-2I20-2101 | D/S CEMS / O2 FLUE GAS (MULTICOMPONENTS ANALYZER) |  |  | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-14; IFR: 2019-05-15
[6 empty] | Issue Actual | IFR: 2019-05-14; IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01660; IFR: TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2102 | Instrument Datasheets for Control Valve - Butterfly Type- Area 21 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-14; IFR: 2019-05-15
[6 empty] | Issue Actual | IFR: 2019-05-14; IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01660; IFR: TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2106 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 21 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Issue Actual | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01625; IFR: TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | IFR: 2019-07-17
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2111 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 21 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Issue Actual | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01625; IFR: TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | IFR: 2019-07-17
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2112 | Instrument Datasheets for ON-OFF Valve - Butterfly Type -Area 21 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01650; IFR: TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | IFR: 2019-06-13; IFR: 2019-06-13
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2116 | Instrument Datasheets for Pressure Safety Valve - Area 21 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02291
Return Date
Owner Cmmt*
| IE | OL1-2I20-2122 | Instrument Datasheets for Flow Element -Orifice -Area 21 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-14; IFR: 2019-05-15
[6 empty] | Issue Actual | IFR: 2019-05-14; IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01660; IFR: TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2201 | D/S MECHANICAL O2 PROCESS ANALYSER |  |  | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-23
[6 empty] | Issue Actual | IFR: 2019-04-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01301; IFR: TPSK-LSPA1-T-IE-01301
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2211 | Instrument Datasheets for On-Off Vales - Ball Type - Area 22 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-23
[6 empty] | Issue Actual | IFR: 2019-04-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01301; IFR: TPSK-LSPA1-T-IE-01301
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2213 | Instrument Datasheets for Motor Operated Valve - MOV - Area 22 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-23
[6 empty] | Issue Actual | IFR: 2019-04-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01301; IFR: TPSK-LSPA1-T-IE-01301
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2216 | Instrument Datasheets for Pressure Safety Valve - Area 22 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02291
Return Date
Owner Cmmt*
| IE | OL1-2I20-2301 | D/S MECHANICAL MOISTURE ANALYSER |  |  | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Issue Actual | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01548; IFR: TPSK-LSPA1-T-IE-01548
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2306 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 23 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Issue Actual | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01548; IFR: TPSK-LSPA1-T-IE-01548
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2311 | Instrument Datasheets - ON-OFF Valve - Ball Type - Area 23 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Issue Actual | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01550; IFR: TPSK-LSPA1-T-IE-01550
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2313 | Instrument Datasheets for Motor Operated Valve Area 23 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Issue Actual | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01550; IFR: TPSK-LSPA1-T-IE-01550
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2316 | Instrument Datasheets for Pressure Safety Valve - Area 23 |  | Class 2 | Purpose** | IFR: IFI
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02258
Return Date
Owner Cmmt*
| IE | OL1-2I20-2322 | Instrument Datasheets for Flow Element -Orifice -Area 23 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-06; IFR: 2019-05-07
[6 empty] | Issue Actual | IFR: 2019-05-06; IFR: 2019-05-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01581; IFR: TPSK-LSPA1-T-IE-01581
[6 empty] | Return Date | IFR: 2019-06-13; IFR: 2019-06-13
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2329 | Instrument Datasheets for Flow transmitter - Electromagnetic - Area 23 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-06; IFR: 2019-05-07
[6 empty] | Issue Actual | IFR: 2019-05-06; IFR: 2019-05-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01581; IFR: TPSK-LSPA1-T-IE-01581
[6 empty] | Return Date | IFR: 2019-06-13; IFR: 2019-06-13
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2332 | Instrument Datasheets for Flow Element - Integral Orifice- Area 23 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-06; IFR: 2019-05-07
[6 empty] | Issue Actual | IFR: 2019-05-06; IFR: 2019-05-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01581; IFR: TPSK-LSPA1-T-IE-01581
[6 empty] | Return Date | IFR: 2019-06-13; IFR: 2019-06-13
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2401 | D/S MECHANICAL PH / CONDUCTIVITY / TURBIDITY / SILICA / ORP / TSS / MLSS METER |  |  | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Issue Actual | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01550; IFR: TPSK-LSPA1-T-IE-01550
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2402 | Instrument Datasheets for Control Valve - Butterfly Type - Area 24 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Issue Actual | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01550; IFR: TPSK-LSPA1-T-IE-01550
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2411 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 24 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-06; IFR: 2019-05-07
[6 empty] | Issue Actual | IFR: 2019-05-06; IFR: 2019-05-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01581; IFR: TPSK-LSPA1-T-IE-01581
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2412 | Instrument Datasheets for On-Off Valve - Butterfly Type - Area 24 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Issue Actual | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01548; IFR: TPSK-LSPA1-T-IE-01548
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2413 | Instrument Datasheets for Motor Operated Valve - Area 24 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Issue Actual | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01550; IFR: TPSK-LSPA1-T-IE-01550
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2416 | Instrument Datasheets for Pressure Safety Valve - Area 24 |  | Class 2 | Purpose** | IFR: IFI
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02258
Return Date
Owner Cmmt*
| IE | OL1-2I20-2422 | Instrument Datasheets for Flow Element -Orifice- Area 24 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Issue Actual | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01548; IFR: TPSK-LSPA1-T-IE-01548
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2423 | Instrument Datasheets for Flow Element - Venturi - Area 24 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-22; IFR: 2019-04-23
[6 empty] | Issue Actual | IFR: 2019-04-22; IFR: 2019-04-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01428; IFR: TPSK-LSPA1-T-IE-01428
[6 empty] | Return Date | IFR: 2019-05-24; IFR: 2019-05-24
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2425 | Instrument Datasheets for Flow Element -Pitot - Area 24 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-22; IFR: 2019-04-23
[6 empty] | Issue Actual | IFR: 2019-04-22; IFR: 2019-04-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01428; IFR: TPSK-LSPA1-T-IE-01428
[6 empty] | Return Date | IFR: 2019-05-24; IFR: 2019-05-24
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2428 | Instrument Datasheets for Flow Element - Rotameter- Area 24 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-22; IFR: 2019-04-23
[6 empty] | Issue Actual | IFR: 2019-04-22; IFR: 2019-04-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01428; IFR: TPSK-LSPA1-T-IE-01428
[6 empty] | Return Date | IFR: 2019-05-24; IFR: 2019-05-24
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2501 | Instrument Datasheets for Control Valve - Globe Type -Area 25 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-24; IFR: 2019-04-25
[6 empty] | Issue Actual | IFR: 2019-04-24; IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01464; IFR: TPSK-LSPA1-T-IE-01464
[6 empty] | Return Date | IFR: 2019-05-29; IFR: 2019-05-29
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2502 | Instrument Datasheets for Control Valve - Butterfly Type- Area 25 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-24; IFR: 2019-04-25
[6 empty] | Issue Actual | IFR: 2019-04-24; IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01464; IFR: TPSK-LSPA1-T-IE-01464
[6 empty] | Return Date | IFR: 2019-05-29; IFR: 2019-05-29
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2506 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 25 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-20; IFR: 2019-05-21
[6 empty] | Issue Actual | IFR: 2019-05-20; IFR: 2019-05-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01692; IFR: TPSK-LSPA1-T-IE-01692
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2511 | Instrument Datasheets - ON-OFF Valve - Ball Type - Area 25 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-23
[6 empty] | Issue Actual | IFR: 2019-04-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01376; IFR: TPSK-LSPA1-T-IE-01376
[6 empty] | Return Date | IFR: 2019-05-24; IFR: 2019-05-24
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2512 | Instrument Datasheets - ON-OFF Valve - Butterfly Type - Area 25 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-23
[6 empty] | Issue Actual | IFR: 2019-04-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01376; IFR: TPSK-LSPA1-T-IE-01376
[6 empty] | Return Date | IFR: 2019-05-29; IFR: 2019-05-29
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2513 | Instrument Datasheets for Motor Operated Valve Area 25 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-14; IFR: 2019-05-15
[6 empty] | Issue Actual | IFR: 2019-05-14; IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01660; IFR: TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2516 | Instrument Datasheets for Pressure Safety Valve - Area 25 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02291
Return Date
Owner Cmmt*
| IE | OL1-2I20-2522 | Instrument Datasheets for Flow Element - Orifice - Area 25 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-23
[6 empty] | Issue Actual | IFR: 2019-04-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01338; IFR: TPSK-LSPA1-T-IE-01338
Return Date
Owner Cmmt*
| IE | OL1-2I20-2523 | Instrument Datasheets for Flow Element -Venturi - Area 25 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-23
[6 empty] | Issue Actual | IFR: 2019-04-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01388; IFR: TPSK-LSPA1-T-IE-01388
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2528 | Instrument Datasheets for Flow Element - Rotameter - Area 25 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ; IFD: IFQ; IFD: IFQ
Rev. | bar: IFR to IFD
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-15; IFR: 2019-04-23; IFD: 2019-05-23; IFD: 2019-05-24
[6 empty] | Issue Actual | IFR: 2019-04-15; IFR: 2019-04-23; IFD: 2019-05-23; IFD: 2019-05-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01338; IFR: TPSK-LSPA1-T-IE-01338; IFD: TPSK-LSPA1-T-IE-01728; IFD: TPSK-LSPA1-T-IE-01728
[6 empty] | Return Date | IFD: 2019-06-17; IFD: 2019-06-17
Owner Cmmt* | bar: IFD to IFD
| IE | OL1-2I20-2601 | DATA SHEET FOR FIRE AND GAS DEVICES |  |  | Purpose** | IFR: IFQ; IFR: IFQ; IFD: IFP
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-12-20; IFD: 2020-07-20
[6 empty] | Revised Plan | IFR: 2019-12-20; IFD: 2020-07-20
[6 empty] | Issue Actual | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01845; IFR: TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2602 | Instrument Datasheet for Control Valve - Butterfly Type - Area 26 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-05; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-05; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01807; IFR: TPSK-LSPA1-T-IE-01807
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2611 | Instrument Datasheet for ON-OFF Valve - Ball Type- Area 26 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-05; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-05; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01807; IFR: TPSK-LSPA1-T-IE-01807
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2612 | Instrument Datasheets for ON-OFF Valve -Butterfly Type - Area 26 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01792; IFR: TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | IFR: 2019-06-27
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2613 | Instrument Datasheets for Motor Operated Valve - Area 26 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01792; IFR: TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | IFR: 2019-06-27
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2616 | Instrument Datasheets for Pressure Safety Valve - Area 26 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02291
Return Date
Owner Cmmt*
| IE | OL1-2I20-2622 | Instrument Datasheets for Flow Element Orifice Area 26 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-13; IFR: 2019-06-14
[6 empty] | Issue Actual | IFR: 2019-06-13; IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSAP1-T-IE-01890; IFR: TPSK-LSAP1-T-IE-01890
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2701 | D/S MECHANICAL DENSITY ANALYSER |  |  | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-19; IFR: 2019-06-19
[6 empty] | Issue Actual | IFR: 2019-06-19; IFR: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01919; IFR: TPSK-LSPA1-T-IE-01919
[6 empty] | Return Date | IFR: 2019-07-09; IFR: 2019-07-09
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2706 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 27 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-18; IFR: 2019-06-18
[6 empty] | Issue Actual | IFR: 2019-06-18; IFR: 2019-06-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01907; IFR: TPSK-LSPA1-T-IE-01907
[6 empty] | Return Date | IFR: 2019-07-09; IFR: 2019-07-09
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2711 | Instrument Datasheets for ON-OFF Valve - Ball Type - Area 27 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-19; IFR: 2019-06-19
[6 empty] | Issue Actual | IFR: 2019-06-19; IFR: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01919; IFR: TPSK-LSPA1-T-IE-01919
[6 empty] | Return Date | IFR: 2019-07-09; IFR: 2019-07-09
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2712 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 27 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-19; IFR: 2019-06-19
[6 empty] | Issue Actual | IFR: 2019-06-19; IFR: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01919; IFR: TPSK-LSPA1-T-ME-01919
[6 empty] | Return Date | IFR: 2019-07-09; IFR: 2019-07-09
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2716 | Instrument Datasheets for Pressure Safety Valve - Area 27 |  | Class 2 | Purpose** | IFR: IFI
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02258
[6 empty] | Return Date | IFR: 2019-08-20
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2722 | Instrument Datasheets for Flow Element - Orifice - Area 27 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-18; IFR: 2019-06-18
[6 empty] | Issue Actual | IFR: 2019-06-18; IFR: 2019-06-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01908; IFR: TPSK-LSPA1-T-IE-01908
[6 empty] | Return Date | IFR: 2019-07-09; IFR: 2019-07-09
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2801 | D/S MECHANICAL CALORIMETER |  |  | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-24; IFR: 2019-04-25
[6 empty] | Issue Actual | IFR: 2019-04-24; IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01464; IFR: TPSK-LSPA1-T-IE-01464
[6 empty] | Return Date | IFR: 2019-05-29; IFR: 2019-05-29
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2802 | D/S MECHANICAL HC INFRARED ANALYSER |  |  | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-24; IFR: 2019-04-25
[6 empty] | Issue Actual | IFR: 2019-04-24; IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01464; IFR: TPSK-LSPA1-T-IE-01464
[6 empty] | Return Date | IFR: 2019-05-29; IFR: 2019-05-29
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2803 | Instrument Datasheets for Wobbe Index Analyzers |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02280
Return Date
Owner Cmmt*
| IE | OL1-2I20-2804 | Instrument Datasheets for CO- CO2 Analyzers |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02280
Return Date
Owner Cmmt*
| IE | OL1-2I20-2806 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 28 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ; IFD: IFQ; IFD: IFQ
Rev. | bar: IFR to IFD
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-23; IFD: 2019-05-24; IFD: 2019-05-27
[6 empty] | Issue Actual | IFR: 2019-04-23; IFD: 2019-05-24; IFD: 2019-05-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01338; IFR: TPSK-LSPA1-T-IE-01338; IFD: TPSK-LSPA1-T-IE-01738; IFD: TPSK-LSPA1-T-IE-01738
[6 empty] | Return Date | IFD: 2019-06-17; IFD: 2019-06-17
Owner Cmmt* | bar: IFD to IFD
| IE | OL1-2I20-2811 | Instrument Datasheets - ON-OFF Valve - Ball Type - Area 28 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-23
[6 empty] | Issue Actual | IFR: 2019-04-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01376; IFR: TPSK-LSPA1-T-IE-01376
[6 empty] | Return Date | IFR: 2019-06-24; IFR: 2019-05-29
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2812 | Instrument Datasheets - ON-OFF Valve - Butterfly Type- Area 28 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-23
[6 empty] | Issue Actual | IFR: 2019-04-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01376; IFR: TPSK-LSPA1-T-IE-01376
[6 empty] | Return Date | IFR: 2019-05-29; IFR: 2019-05-29
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2813 | Instrument Datasheets for Motor Operated Valve Area 28 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-24; IFR: 2019-04-25
[6 empty] | Issue Actual | IFR: 2019-04-24; IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01464; IFR: TPSK-LSPA1-T-IE-01464
[6 empty] | Return Date | IFR: 2019-07-02
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2816 | Instrument Datasheets for Pressure Safety Valve - Area 28 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02291
Return Date
Owner Cmmt*
| IE | OL1-2I20-2822 | Instrument Datasheet for Flow Element -Orifice- Area 28 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-23
[6 empty] | Issue Actual | IFR: 2019-04-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01360; IFR: TPSK-LSPA1-T-IE-01360
[6 empty] | Return Date | IFR: 2019-05-24; IFR: 2019-05-24
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2823 | Instrument Datasheets for Flow Element -Venturi- Area 28 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-23
[6 empty] | Issue Actual | IFR: 2019-04-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01360; IFR: TPSK-LSPA1-T-IE-01360
[6 empty] | Return Date | IFR: 2019-05-24; IFR: 2019-05-24
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2828 | Instrument Datasheet for Flow Element - Rotameter - Area 28 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-16; IFR: 2019-05-17
[6 empty] | Issue Actual | IFR: 2019-05-16; IFR: 2019-05-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01681; IFR: TPSK-LSPA1-T-IE-01681
[6 empty] | Return Date | IFR: 2019-07-17
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-2830 | Instrument Datasheets for Flow Element - Coriolis - Area 28 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-23
[6 empty] | Issue Actual | IFR: 2019-04-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01360; IFR: TPSK-LSPA1-T-IE-01360
[6 empty] | Return Date | IFR: 2019-05-24; IFR: 2019-05-24
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2901 | D/S MECHANICAL TOTAL CARBON ANALYSER (BOC/TOC) / COD |  |  | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-22; IFR: 2019-05-23
[6 empty] | Issue Actual | IFR: 2019-05-22; IFR: 2019-05-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01717; IFR: TPSK-LSPA1-T-IE-01717
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2902 | Instrument Datasheets for TOC - COD Analyzers |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02280
Return Date
Owner Cmmt*
| IE | OL1-2I20-2906 | Instrument Datasheets for Self Actuated Pressure Control Valve - Area 29 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-22; IFR: 2019-05-23
[6 empty] | Issue Actual | IFR: 2019-05-22; IFR: 2019-05-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01717; IFR: TPSK-LSPA1-T-IE-01717
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2911 | Instrument Datasheets for ON-OFF Valve (Ball Type) Area 29 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-22; IFR: 2019-05-23
[6 empty] | Issue Actual | IFR: 2019-05-22; IFR: 2019-05-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01717; IFR: TPSK-LSPA1-T-IE-01717
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2916 | Instrument Datasheets for Pressure Safety Valve - Area 29 |  | Class 2 | Purpose** | IFR: IFI
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02258
Return Date
Owner Cmmt*
| IE | OL1-2I20-2922 | Instrument Datasheets for Flow Element -Orifice- Area 29 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-22; IFR: 2019-05-23
[6 empty] | Issue Actual | IFR: 2019-05-22; IFR: 2019-05-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01717; IFR: TPSK-LSPA1-T-IE-01717
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2923 | Instrument Datasheets for Flow Element (Venturi Type) Area 29 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-22; IFR: 2019-05-23
[6 empty] | Issue Actual | IFR: 2019-05-22; IFR: 2019-05-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01717; IFR: TPSK-LSPA1-T-IE-01717
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-2924 | Instrument Datasheets for Flow Element - Flow Nozzle - Area 29 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-24; IFR: 2019-05-27
[6 empty] | Issue Actual | IFR: 2019-05-24; IFR: 2019-05-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01738; IFR: TPSK-LSPA1-T-IE-01738
[6 empty] | Return Date | IFR: 2019-06-17; IFR: 2019-06-17
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-3001 | CONTROL VALVE DATASHEETS |  | Class 1 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02133; IFR: TPSK-LSPA1-T-IE-02133
[6 empty] | Return Date | IFR: 2019-08-07
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3002 | INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02133; IFR: TPSK-LSPA1-T-IE-02133
[6 empty] | Return Date | IFR: 2019-08-06
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3011 | TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-10; IFR: 2019-07-10
[6 empty] | Issue Actual | IFR: 2019-07-10; IFR: 2019-07-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02110; IFR: TPSK-LSPA1-T-IE-02110
[6 empty] | Return Date | IFR: 2019-08-06
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3012 | TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-10; IFR: 2019-07-10
[6 empty] | Issue Actual | IFR: 2019-07-10; IFR: 2019-07-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02110; IFR: TPSK-LSPA1-T-IE-02110
[6 empty] | Return Date | IFR: 2019-08-06
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3016 | O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-15
[6 empty] | Issue Actual | IFR: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02429
Return Date
Owner Cmmt*
| IE | OL1-2I20-3022 | Instrument Datasheets for Flow Element (Orifice) Area 30 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-09; IFR: 2019-07-09
[6 empty] | Issue Actual | IFR: 2019-07-09; IFR: 2019-07-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-2097; IFR: TPSK-LSPA1-T-IE-2097
[6 empty] | Return Date | IFR: 2019-07-31
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3023 | Instrument Datasheets for Flow Element Venturi Area 30 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-10; IFR: 2019-07-10
[6 empty] | Issue Actual | IFR: 2019-07-10; IFR: 2019-07-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02110; IFR: TPSK-LSPA1-T-IE-02110
[6 empty] | Return Date | IFR: 2019-08-06
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3027 | Instrument Datasheets for Flow Instrument Vortex Area 30 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-10; IFR: 2019-07-10
[6 empty] | Issue Actual | IFR: 2019-07-10; IFR: 2019-07-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02110; IFR: TPSK-LSPA1-T-IE-02110
Return Date
Owner Cmmt*
| IE | OL1-2I20-3028 | Instrument Datasheets for Flow Element Rotameter - Area 30 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-08; IFR: 2019-07-08
[6 empty] | Issue Actual | IFR: 2019-07-08; IFR: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02087; IFR: TPSK-LSPA1-T-IE-02087
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3029 | Instrument Datasheets for Flow Transmitter Electromagnetic Area 30 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-10; IFR: 2019-07-10
[6 empty] | Issue Actual | IFR: 2019-07-10; IFR: 2019-07-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02110; IFR: TPSK-LSPA1-T-IE-02110
[6 empty] | Return Date | IFR: 2019-08-06
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3030 | Instrument Datasheets for Flow Element Coriolis Area 30 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27; IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27; IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02000; IFR: TPSK-LSPA1-T-IE-02000
[6 empty] | Return Date | IFR: 2019-07-11; IFR: 2019-07-11
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-3032 | Instrument Datasheets for Flow Element (Integral Orifice). Area 30 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-09; IFR: 2019-07-09
[6 empty] | Issue Actual | IFR: 2019-07-09; IFR: 2019-07-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-2097; IFR: TPSK-LSPA1-T-IE-2097
[6 empty] | Return Date | IFR: 2019-07-31
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3101 | Instrument Datasheets for Control Valve Globe Type - Area 31 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-08; IFR: 2019-07-08
[6 empty] | Issue Actual | IFR: 2019-07-08; IFR: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02087; IFR: TPSK-LSPA1-T-IE-02087
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3106 | Instrument Datasheets for Self Actuated Pressure Control Valve.Area 31 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-10; IFR: 2019-07-10
[6 empty] | Issue Actual | IFR: 2019-07-10; IFR: 2019-07-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02110; IFR: TPSK-LSPA1-T-IE-02110
[6 empty] | Return Date | IFR: 2019-08-06
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3111 | Instrument Datasheets for ON-OFF Valve Ball Type Area 31 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02; IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02; IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02037; IFR: TPSK-LSPA1-T-IE-02037
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3112 | Instrument Datasheets for ON-OFF Valve Butterfly Type Area 31 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02; IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02; IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02037; IFR: TPSK-LSPA1-T-IE-02037
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3116 | Instrument Datasheets for Pressure Safety Valve - Area 31 |  | Class 2 | Purpose** | IFR: IFI
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02413
Return Date
Owner Cmmt*
| IE | OL1-2I20-3117 | Instrument Datasheets for Control Valve Angle Type - Area 31 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-08; IFR: 2019-07-08
[6 empty] | Issue Actual | IFR: 2019-07-08; IFR: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02087; IFR: TPSK-LSPA1-T-IE-02087
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3122 | Instrument Datasheets for Flow Element Orifice Area 31 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02; IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02; IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02037; IFR: TPSK-LSPA1-T-IE-02037
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3128 | Instrument Datasheets for Flow Element (Rotameter) Area 31 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-09; IFR: 2019-07-09
[6 empty] | Issue Actual | IFR: 2019-07-09; IFR: 2019-07-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-2097; IFR: TPSK-LSPA1-T-IE-2097
[6 empty] | Return Date | IFR: 2019-07-31
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3132 | Instrument Datasheets for Flow Element Integral Orifice Area 31 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02; IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02; IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02037; IFR: TPSK-LSPA1-T-IE-02037
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3906 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 39 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-09; IFR: 2019-07-09
[6 empty] | Issue Actual | IFR: 2019-07-09; IFR: 2019-07-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-2097; IFR: TPSK-LSPA1-T-IE-2097
[6 empty] | Return Date | IFR: 2019-07-31
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-3916 | Instrument Datasheets for Pressure Safety Valve - Area 39 |  | Class 2 | Purpose** | IFR: IFI
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02413
Return Date
Owner Cmmt*
| IE | OL1-2I20-5022 | Instrument Datasheets for Flow Element -Orifice - Area 50 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-30; IFR: 2019-05-31
[6 empty] | Issue Actual | IFR: 2019-05-30; IFR: 2019-05-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01774; IFR: TPSK-LSPA1-T-IE-01774
[6 empty] | Return Date | IFR: 2019-06-21; IFR: 2019-06-21
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-5029 | Instrument Datasheets for Flow Transmitter -Electromagnetic- Area 50 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-30; IFR: 2019-05-31
[6 empty] | Issue Actual | IFR: 2019-05-30; IFR: 2019-05-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01774; IFR: TPSK-LSPA1-T-IE-01774
[6 empty] | Return Date | IFR: 2019-06-21; IFR: 2019-06-21
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I20-5031 | Instrument Datasheet for Flow Element - Ultrasonic - Area 50 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01792; IFR: TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5101 | Instrument Datasheets for Control Valve - Globe Type- Area 51 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-12; IFR: 2019-06-14
[6 empty] | Issue Actual | IFR: 2019-06-12; IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01878; IFR: TPSK-LSPA1-T-IE-01878
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5106 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 51 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01845; IFR: TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5112 | Instrument Datasheets for ON-OFF Valve -Butterfly Type - Area 51 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-07; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-07; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK- LSPA1-T-IE-01828; IFR: TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5116 | Instrument Datasheets for Pressure Safety Valve - Area 51 |  | Class 2 | Purpose** | IFR: IFI
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02258
Return Date
Owner Cmmt*
| IE | OL1-2I20-5117 | Instrument Datasheets for Control Valve - Angle Type - Area 51 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-12; IFR: 2019-06-14
[6 empty] | Issue Actual | IFR: 2019-06-12; IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01878; IFR: TPSK-LSPA1-T-IE-01878
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5118 | Instrument Datasheets for Control Valve - Three way Type - Area 51 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-12; IFR: 2019-06-14
[6 empty] | Issue Actual | IFR: 2019-06-12; IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01878; IFR: TPSK-LSPA1-T-IE-01878
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5122 | Instrument Datasheets for Flow Element - Orifice - Area 51 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01845; IFR: TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5124 | Instrument Datasheets for Flow Element - Flow Nozzle - Area 51 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01845; IFR: TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5128 | Instrument Datasheets for Flow Element - Rotameter - Area 51 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01845; IFR: TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5201 | Instrument Datasheets for Control Valve - Globe Type - Area 52 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01792; IFR: TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | IFR: 2019-06-27
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5202 | Instrument Datasheets for Control Valve - Butterfly Type - Area 52 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01792; IFR: TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | IFR: 2019-06-27
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5211 | Instrument Datasheets for ON-OFF - Ball Type - Area 52 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01792; IFR: TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | IFR: 2019-06-27
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5212 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 52 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01792; IFR: TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | IFR: 2019-06-27
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5216 | Instrument Datasheets for Pressure Safety Valve - Area 52 |  | Class 2 | Purpose** | IFR: IFI
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02213
[6 empty] | Return Date | IFR: 2019-08-20
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5222 | Instrument Datasheets for Flow Element -Orifice- Area 52 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01792; IFR: TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | IFR: 2019-06-27
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5301 | Instrument Datasheets for Control Valve - Globe Type - Area 53 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01845; IFR: TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5302 | Instrument Datasheets for Control Valve -Butterfly Type - Area 53 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01845; IFR: TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5322 | Instrument Datasheets for Flow Element - Orifice - Area 53 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-07; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-07; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK- LSPA1-T-IE-01828; IFR: TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5325 | Instrument Datasheets for Flow Element - Pitot - Area 53 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-07; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-07; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK- LSPA1-T-IE-01828; IFR: TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5329 | Instrument Datasheets for Flow Transmitter - Electromagnetic - Area 53 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01845; IFR: TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5416 | Instrument Datasheet for Pressure Safety Valve - Area 54 |  | Class 2 | Purpose** | IFR: IFI
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02213
[6 empty] | Return Date | IFR: 2019-08-20
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5422 | Instrument Datasheets for Flow Element - Orifice- Area 54 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01792; IFR: TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5430 | Instrument Datasheets for Flow Element - Coriolis- Area 54 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01792; IFR: TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5501 | Instrument Datasheets for Control Valve - Globe Type- Area 55 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-07; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-07; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK- LSPA1-T-IE-01828; IFR: TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5506 | Instrument Datasheets for Self Actuated Pressure Control Valve - Area 55 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01792; IFR: TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | IFR: 2019-06-27
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5511 | Instrument Datasheets for ON-OFF Valve - Ball Type - Area 55 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01792; IFR: TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5512 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 55 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01792; IFR: TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5516 | Instrument Datasheets for Pressure Safety Valve - Area 55 |  | Class 2 | Purpose** | IFR: IFI
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02213
[6 empty] | Return Date | IFR: 2019-08-20
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5522 | Instrument Datasheets for Flow Element - Orifice - Area 55 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-07; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-07; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK- LSPA1-T-IE-01828; IFR: TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5529 | Instrument Datasheets for Flow Transmitter - Electromagnetic - Area 55 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-05; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-05; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01807; IFR: TPSK-LSPA1-T-IE-01807
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5531 | Instrument Datasheets for Flow Element - Ultrasonic - Area 55 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-05; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-05; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01807; IFR: TPSK-LSPA1-T-IE-01807
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5601 | Instrument Datasheets for Control Valve - Globe Type - Area 56 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11; IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01866; IFR: TPSK-LSPA1-T-IE-01866
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5606 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 56 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-12; IFR: 2019-06-14
[6 empty] | Issue Actual | IFR: 2019-06-12; IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01878; IFR: TPSK-LSPA1-T-IE-01878
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5611 | Instrument Datasheets for ON-OFF Valve - Ball Type - Area 56 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11; IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01866; IFR: TPSK-LSPA1-T-IE-01866
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5612 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 56 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11; IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01866; IFR: TPSK-LSPA1-T-IE-01866
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5622 | Instrument Datasheets for Flow Element - Orifice - Area 56 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-07; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-07; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK- LSPA1-T-IE-01828; IFR: TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5901 | Instrument Datasheets for Control Valve - Globe Type - Area 59 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01845; IFR: TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5906 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 59 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01845; IFR: TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5911 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 59 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01845; IFR: TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5916 | Instrument Datasheets for Pressure Safety Valve - Area 59 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02291
Return Date
Owner Cmmt*
| IE | OL1-2I20-5922 | Instrument Datasheets for Flow Element - Orifice - Area 59 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01845; IFR: TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5924 | Instrument Datasheets for Flow Element - Flow Nozzle- Area 59 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-07; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-07; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK- LSPA1-T-IE-01828; IFR: TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I20-5932 | Instrument Datasheets for Flow Element - Integral Orifice - Area 59 |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-10; IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01845; IFR: TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
Category Code: I21 Instrument Calculation sheet |  |  |  |  | Class 2 | Purpose**
| IE | OL1-2I21-1001 | INTRINSIC SAFETY LOOP CALCULATION |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18
[6 empty] | Revised Plan | IFR: 2019-09-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I30 Interlock Logic and Sequence Diagram
| IE | OL1-2I30-1001 | CAUSE AND EFFECT DIAGRAMS - AREA 10 |  | Class 3 | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | 2019-07-19 |  |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-03-13 | 2019-03-14 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-03-13; IFD: 2019-03-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01043; IFD: TPSK-LSPA1-T-IE-01043
Return Date
Owner Cmmt*
| IE | OL1-2I30-1002 | Instrument Interlock Descriptions - Area 10 - Feed Preparation and Feed Preheat |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-13; IFR: 2019-03-14
[6 empty] | Issue Actual | IFR: 2019-03-13; IFR: 2019-03-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01045; IFR: TPSK-LSPA1-T-IE-01045
[6 empty] | Return Date | IFR: 2019-04-10; IFR: 2019-04-10
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I30-1101 | DCS INTERLOCK AND SEQUENCES DIAGRAMS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-29; IFR: 2020-03-21; IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2019-11-29; IFR: 2020-03-21; IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-1102 | ESD INTERLOCK LOGIC DIAGRAMS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-29; IFR: 2020-03-21; IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2019-11-29; IFR: 2020-03-21; IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2001 | CAUSE AND EFFECT DIAGRAMS - AREA 20 |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-15; IFR: 2019-03-18
[6 empty] | Issue Actual | IFR: 2019-03-15; IFR: 2019-03-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01087; IFR: TPSK-LSPA1-T-IE-01087
[6 empty] | Return Date | IFR: 2019-04-10; IFR: 2019-04-10
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I30-2002 | Instrument Interlock Descriptions Area 20 - Quench Oil |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-15; IFR: 2019-03-18
[6 empty] | Issue Actual | IFR: 2019-03-15; IFR: 2019-03-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01088; IFR: TPSK-LSPA1-T-IE-01088
[6 empty] | Return Date | IFR: 2019-04-10; IFR: 2019-04-10
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I30-5301 | CAUSE AND EFFECT DIAGRAMS - AREA 53 |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-12; IFR: 2019-03-13
[6 empty] | Issue Actual | IFR: 2019-03-12; IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01036; IFR: TPSK-LSPA1-T-IE-01036
[6 empty] | Return Date | IFR: 2019-03-29; IFR: 2019-03-29
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I30-5302 | Instrument Interlock Descriptions - Area 53- Cooling Water System |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-12; IFR: 2019-03-13
[6 empty] | Issue Actual | IFR: 2019-03-12; IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01037; IFR: TPSK-LSPA1-T-IE-01037
[6 empty] | Return Date | IFR: 2019-03-29; IFR: 2019-03-29
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I30-5901 | Cause and Effect Diagram Area 59 - Supporting Utilities Auxiliaries |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-15; IFR: 2019-03-18
[6 empty] | Issue Actual | IFR: 2019-03-15; IFR: 2019-03-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01087; IFR: TPSK-LSPA1-T-IE-01087
[6 empty] | Return Date | IFR: 2019-04-10; IFR: 2019-04-10
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I30-5902 | Instrument Interlock Descriptions Area 59 - Supporting Utilities Auxiliaries |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-15; IFR: 2019-03-18
[6 empty] | Issue Actual | IFR: 2019-03-15; IFR: 2019-03-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01088; IFR: TPSK-LSPA1-T-IE-01088
[6 empty] | Return Date | IFR: 2019-04-10; IFR: 2019-04-10
Owner Cmmt* | bar: IFR to IFR
Category Code: I31 Typical installation / fabrication drawing
| IE | OL1-2I31-0001 | INSTR.SUPPORTS TYPICAL MOUNT.DETAILS |  |  | Purpose** | IFR | IFR | IFR | IFR | IDD | IFC
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-12-31; IFD: 2020-05-25; IFD: 2020-09-29
[6 empty] | Revised Plan | IFD: 2020-05-25; IFD: 2020-09-29
[6 empty] | Issue Actual | IFR: 2019-03-14; IFR: 2019-03-15; IFD: 2019-04-17; IFD: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSL-LSPA1-T-IE-01058; IFR: TPSL-LSPA1-T-IE-01058; IFD: TPSK-LPSA1-T-IE-01391; IFD: TPSK-LPSA1-T-IE-01391
[6 empty] | Return Date | IFR: 2019-04-05; IFR: 2019-04-05; IFD: 2019-05-18; IFD: 2019-05-18
Owner Cmmt* | bar: IFR to IFD
| IE | OL1-2I31-0200 | LEVEL INSTRUMENT DESIGN, ISBL UNITS |  |  | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-28; IFR: 2019-06-28
[6 empty] | Issue Actual | IFR: 2019-06-28; IFR: 2019-06-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02015; IFR: TPSK-LSPA1-T-IE-02015
[6 empty] | Return Date | IFR: 2019-07-10; IFR: 2019-07-10
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I31-0201 | LEVEL INSTRUMENT DESIGN, OSBL UNITS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-04-15; IFR: 2019-06-15; IFD: 2019-12-15
[6 empty] | Revised Plan | IFR: 2019-09-13; IFD: 2019-12-15
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02278
[6 empty] | Return Date | IFR: 2019-08-08
Owner Cmmt* | bar: IFR
| IE | OL1-2I31-0202 | Level Instrument Design And Nozzle Study for Furnaces Utilities ISBL 1B |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-15; IFD: 2019-06-15; IFD: 2019-12-15
[6 empty] | Revised Plan | IFD: 2019-09-13; IFD: 2019-12-15
[6 empty] | Issue Actual | IFR: 2019-06-28; IFR: 2019-06-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02015; IFR: TPSK-LSPA1-T-IE-02015
[6 empty] | Return Date | IFR: 2019-07-10; IFR: 2019-07-10
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I31-0203 | Level Instrument Design Quench ISBL |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IDD | IFC
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-04-15; IFD: 2019-06-15; IFD: 2019-12-15
[6 empty] | Revised Plan | IFD: 2019-09-13; IFD: 2019-12-15
[6 empty] | Issue Actual | IFR: 2019-04-18; IFR: 2019-04-19; IFD: 2019-07-11; IFD: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01413; IFR: TPSK-LSPA1-T-IE-01413; IFD: TPSK-LSPA1-T-IE-02120; IFD: TPSK-LSPA1-T-IE-02120
[6 empty] | Return Date | IFR: 2019-05-18; IFR: 2019-05-18; IFD: 2019-07-22
Owner Cmmt* | bar: IFR to IFR; IFD
| IE | OL1-2I31-0204 | Level Instrument Design C3 Hydrogenation ISBL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-15; IFD: 2019-06-15; IFD: 2019-12-15
[6 empty] | Revised Plan | IFD: 2019-09-13; IFD: 2019-12-15
[6 empty] | Issue Actual | IFR: 2019-06-13; IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01888; IFR: TPSK-LSPA1-T-IE-01888
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I31-0205 | Level Instrument Design And Nozzle Study Hot Fractionation -Ghu Unit Isbl -2C |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-15; IFD: 2019-06-15; IFD: 2019-12-15
[6 empty] | Revised Plan | IFD: 2019-09-13; IFD: 2019-12-15
[6 empty] | Issue Actual | IFR: 2019-06-28; IFR: 2019-06-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02015; IFR: TPSK-LSPA1-T-IE-02015
[6 empty] | Return Date | IFR: 2019-07-10; IFR: 2019-07-10
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I31-0206 | Level Instrument Design Process Cold Compressors ISBL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-15; IFD: 2019-06-15; IFD: 2019-12-15
[6 empty] | Revised Plan | IFD: 2019-09-13; IFD: 2019-12-15
[6 empty] | Issue Actual | IFR: 2019-06-24; IFR: 2019-06-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01964; IFR: TPSK-LSPA1-T-IE-01964
[6 empty] | Return Date | IFR: 2019-07-05; IFR: 2019-07-05
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I31-0207 | Level Instrument Design Cracked Gas Compressor - ISBL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-15; IFD: 2019-06-15; IFD: 2019-12-15
[6 empty] | Revised Plan | IFD: 2019-09-13; IFD: 2019-12-15
[6 empty] | Issue Actual | IFR: 2019-06-18; IFR: 2019-06-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01905; IFR: TPSK-LSPA1-T-IE-01905
[6 empty] | Return Date | IFR: 2019-06-28; IFR: 2019-06-28
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I31-0208 | Level Instrument Design And Nozzle Study For Butadiene Extraction Unit Osbl 3A |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-15; IFD: 2019-06-15; IFD: 2019-12-15
[6 empty] | Revised Plan | IFD: 2019-09-13; IFD: 2019-12-15
[6 empty] | Issue Actual | IFR: 2019-06-28; IFR: 2019-06-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02015; IFR: TPSK-LSPA1-T-IE-02015
[6 empty] | Return Date | IFR: 2019-07-10; IFR: 2019-07-10
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I31-0210 | Level Instrument Design for Towers and Reactors |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-15; IFD: 2019-06-15; IFD: 2019-12-15
[6 empty] | Revised Plan | IFD: 2019-09-13; IFD: 2019-12-15
[6 empty] | Issue Actual | IFR: 2019-06-13; IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01888; IFR: TPSK-LSPA1-T-IE-01888
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| IE | OL1-2I31-0211 | Level Instument Design And Nozzle Studies For Cooling Water Unit OSBL 5T |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-15; IFD: 2019-06-15; IFD: 2019-12-15
[6 empty] | Revised Plan | IFD: 2019-09-13; IFD: 2019-12-15
[6 empty] | Issue Actual | IFR: 2019-06-24; IFR: 2019-06-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01964; IFR: TPSK-LSPA1-T-IE-01964
[6 empty] | Return Date | IFR: 2019-07-05; IFR: 2019-07-05
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I31-0212 | Level Instrument Design Utilities OSBL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-15; IFD: 2019-06-15; IFD: 2019-12-15
[6 empty] | Revised Plan | IFD: 2019-09-13; IFD: 2019-12-15
[6 empty] | Issue Actual | IFR: 2019-06-24; IFR: 2019-06-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01964; IFR: TPSK-LSPA1-T-IE-01964
[6 empty] | Return Date | IFR: 2019-07-05; IFR: 2019-07-05
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I31-0213 | Level Instrument Design And Nozzle Study For Water Treatment Osbl 5W |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-15; IFD: 2019-06-15; IFD: 2019-12-15
[6 empty] | Revised Plan | IFD: 2019-09-13; IFD: 2019-12-15
[6 empty] | Issue Actual | IFR: 2019-06-28; IFR: 2019-06-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02015; IFR: TPSK-LSPA1-T-IE-02015
[6 empty] | Return Date | IFR: 2019-07-10; IFR: 2019-07-10
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I31-0214 | Level Instrument Design for Towers and Reactors |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-15; IFD: 2019-06-15; IFD: 2019-12-15
[6 empty] | Revised Plan | IFD: 2019-09-13; IFD: 2019-12-15
[6 empty] | Issue Actual | IFR: 2019-05-23; IFR: 2019-05-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01725; IFR: TPSK-LSPA1-T-IE-01725
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| IE | OL1-2I31-1003 | FLOW TRANSMITTER - VENTURI STEAM LIQUID SERVICE - 900 AND ABOVE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1005 | PRESSURE TRANSMITTER - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1012 | PRESSURE GAUGE - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1019 | FLOW TRANSMITTER - LIQUID SERVICE 900 AND ABOVE W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1020 | PRESSURE TRANSMITTER - STEAM SVC 1500 W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1021 | LEVEL TRANSMITTER - STEAM LIQ 900 AND ABOVE W ELECT TRACE INSTALLATION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1022 | PRESSURE GAUGE - STEAM SRV 1500 REMOTE MTD W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2001 | O2 COMBUSTIBLE ANALYZER PROCESS CONNECTION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2002 | O2 COMBUSTIBLE ANALYZER INSTRUMENT ELECTRICAL CONNECTION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2003 | FLOW TRANSMITTER - VENTURI STEAM LIQUID SERVICE - 900 AND ABOVE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2004 | PRESSURE GAUGE - GAS SERVICE DRAFT REMOTE MOUNTING |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2005 | PRESSURE TRANSMITTER - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2006 | EYE-HYE LEVEL COMPONENTS ON STEAM DRUM ELECTRICAL CONNECTION |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2007 | COT INSERTION WELL T-C CONNECTION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2008 | INSTRUMENT SUPPORT DETAIL EYE-HYE LEVEL CONTROL UNIT |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2009 | INSTRUMENT PROCESS DETAILS DRAFT D-P TRANSMITTER GAS SERVICE REMOTE MOUNTED |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2010 | INSTRUMENT SUPPORT DETAILS DUAL STAND 4FT-4IN OUTSIDE HANDRAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2011 | INSTRUMENT SUPPORT DETAILS TRIPLE STAND 4FT-4IN OUTSIDE HANDRAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2012 | PRESSURE GAUGE - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2013 | THERMOCOUPLE HEAD ELECTRICAL CONNECTION DETAIL 3-4IN CONDUIT |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2014 | TEMPERATURE TRANSMITTER ELECTRICAL CONNECTION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2015 | LUBE OIL VENDOR JUNCTION BOX TO FIE CHARM BOX ELECTRICAL CONNECTION |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2016 | INSTRUMENT SUPPORT DETAIL EYE-HYE MINIATURE LEVEL INDICATOR |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2017 | PH CONDUCTIVITY ANALYZER SAMPLING SYTEM PROCESS CONNECTION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2018 | PH CONDUCTIVITY ANALYZER SAMPLING SYTEM PROCESS CONNECTION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2019 | FLOW TRANSMITTER - LIQUID SERVICE 900 AND ABOVE W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2020 | PRESSURE TRANSMITTER - STEAM SVC 1500 W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2021 | LEVEL TRANSMITTER - STEAM LIQ 900 AND ABOVE W ELECT TRACE INSTALLATION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2022 | PRESSURE GAUGE - STEAM SRV 1500 REMOTE MTD W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2023 | LEVEL GAUGE - STEAM SERVICE DIRECT MTD W ELECTRIC TRACED |  | Class 2 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-19; IFR: 2020-03-15
[6 empty] | Revised Plan | IFR: 2019-09-19; IFR: 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I32 Instrument installation key plan drawing
Category Code: I33 Instrument cable trays and support layout
Category Code: I34 Instrument main cable layout
| IE | OL1-2I34-0001 | INSTR.MAIN CABLE ROUTING COMMON AREA |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-30 | 2019-09-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0002 | INSTR.MAIN CABLE ROUTING METERING |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | IFR: 2019-09-30; IFD: 2019-12-24; IFD: 2020-10-09; IFD: 2021-01-31
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02407
Return Date
Owner Cmmt*
| IE | OL1-2I34-0003 | INSTR.MAIN CABLE ROUTING MAIN PIPE RACK |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | IFR: 2019-09-30; IFD: 2019-12-24; IFD: 2020-10-09; IFD: 2021-01-31
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02407
Return Date
Owner Cmmt*
| IE | OL1-2I34-0004 | INSTR.MAIN CABLE ROUTING AREA SUBSTATION E & FAR E |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | IFR: 2019-09-30; IFD: 2019-12-24; IFD: 2020-10-09; IFD: 2021-01-31
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: 2344-TPSK-LSPA1-T-IE-02362
Return Date
Owner Cmmt*
| IE | OL1-2I34-0005 | INSTR.MAIN CABLE ROUTING AREA SUBSTATION C & FAR C |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | IFR: 2019-09-30; IFD: 2019-12-24; IFD: 2020-10-09; IFD: 2021-01-31
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02363
Return Date
Owner Cmmt*
| IE | OL1-2I34-0006 | INSTR.MAIN CABLE ROUTING FURNACES UTILITY |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | IFR: 2019-09-30; IFD: 2019-12-24; IFD: 2020-10-09; IFD: 2021-01-31
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02392
Return Date
Owner Cmmt*
| IE | OL1-2I34-0007 | INSTR.MAIN CABLE ROUTING QUENCH |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | IFR: 2019-09-30; IFD: 2019-12-24; IFD: 2020-10-09; IFD: 2021-01-31
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02392
Return Date
Owner Cmmt*
| IE | OL1-2I34-0008 | INSTR.MAIN CABLE ROUTING PROCESS 20B |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | IFR: 2019-09-30; IFD: 2019-12-24; IFD: 2020-10-09; IFD: 2021-01-31
[6 empty] | Issue Actual | IFR: 2019-08-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02372
Return Date
Owner Cmmt*
| IE | OL1-2I34-0009 | INSTR.MAIN CABLE ROUTING PROCESS 20C |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | IFR: 2019-09-30; IFD: 2019-12-24; IFD: 2020-10-09; IFD: 2021-01-31
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02392
Return Date
Owner Cmmt*
| IE | OL1-2I34-0010 | INSTR.MAIN CABLE ROUTING PROCESS COLD COMPRESSORS |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | IFR: 2019-09-30; IFD: 2019-12-24; IFD: 2020-10-09; IFD: 2021-01-31
[6 empty] | Issue Actual | IFR: 2019-08-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02372
Return Date
Owner Cmmt*
| IE | OL1-2I34-0011 | INSTR.MAIN CABLE ROUTING PROCESS CGC |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | IFR: 2019-09-30; IFD: 2019-12-24; IFD: 2020-10-09; IFD: 2021-01-31
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02392
Return Date
Owner Cmmt*
| IE | OL1-2I34-0012 | INSTR.MAIN CABLE ROUTING BUTADIENE |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | IFR: 2019-09-30; IFD: 2019-12-24; IFD: 2020-10-09; IFD: 2021-01-31
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02384
Return Date
Owner Cmmt*
| IE | OL1-2I34-0013 | INSTR.MAIN CABLE ROUTING COOLING WATER UNIT |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | IFR: 2019-09-30; IFD: 2019-12-24; IFD: 2020-10-09; IFD: 2021-01-31
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02407
Return Date
Owner Cmmt*
| IE | OL1-2I34-0014 | INSTR.MAIN CABLE ROUTING UTILITIES |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | IFR: 2019-09-30; IFD: 2019-12-24; IFD: 2020-10-09; IFD: 2021-01-31
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02363
Return Date
Owner Cmmt*
| IE | OL1-2I34-0015 | INSTR.MAIN CABLE ROUTING WASTE WATER TREATMENT |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | IFR: 2019-09-30; IFD: 2019-12-24; IFD: 2020-10-09; IFD: 2021-01-31
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02363
Return Date
Owner Cmmt*
| IE | OL1-2I34-0016 | INSTR.MAIN CABLE ROUTING FLARE AREA |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | IFR: 2019-09-30; IFD: 2019-12-24; IFD: 2020-10-09; IFD: 2021-01-31
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02363
Return Date
Owner Cmmt*
| IE | OL1-2I34-0017 | INSTR.OVERALL CABLE ROUTING |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-11; IFR: 2019-07-11; IFD: 2020-04-30
[6 empty] | Revised Plan | IFR: 2019-09-03; IFR: 2019-09-30; IFD: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0018 | Instrument Main Cable Routing Underground |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02407
Return Date
Owner Cmmt*
Category Code: I35 Instrument, Junction box and instrument air supply station plot plan drawing
| IE | OL1-2I35-0001 | INSTRUMENT LAYOUT COMMON AREA |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0002 | INSTRUMENT LAYOUT METERING |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0003 | INSTRUMENT LAYOUT MAIN PIPE RACK |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0004 | INSTRUMENT LAYOUT AREA SUBSTATION E & FAR E |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0005 | INSTRUMENT LAYOUT AREA SUBSTATION E & FAR C |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0006 | INSTRUMENT LAYOUT FURNACES UTILITY |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0007 | INSTRUMENT LAYOUT QUENCH |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0008 | INSTRUMENT LAYOUT PROCESS 20B |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0009 | INSTRUMENT LAYOUT PROCESS 20C |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0010 | INSTRUMENT LAYOUT PROCESS COLD COMPRESSORS |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0011 | INSTRUMENT LAYOUT PROCESS CGC |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0012 | INSTRUMENT LAYOUT BUTADIENE |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0013 | INSTRUMENT LAYOUT COOLING WATER UNIT |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0014 | INSTRUMENT LAYOUT UTILITIES |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0015 | INSTRUMENT LAYOUT WASTE WATER TREATMENT |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0016 | INSTRUMENT LAYOUT FLARE AREA |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0020 | INSTRUMENT AIR DISTRIBUTION LAYOUT COMMON AREA |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0021 | INSTRUMENT AIR DISTRIBUTION LAYOUT METERING |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0022 | INSTRUMENT AIR DISTRIBUTION LAYOUT MAIN PIPE RACK |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0023 | INSTRUMENT AIR DISTRIBUTION LAYOUT AREA SUBSTATION E & FAR E |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0024 | INSTRUMENT AIR DISTRIBUTION LAYOUT AREA SUBSTATION C & FAR C |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0025 | INSTRUMENT AIR DISTRIBUTION LAYOUT FURNACES UTILITY |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0026 | INSTRUMENT AIR DISTRIBUTION LAYOUT QUENCH |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0027 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS 20B |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0028 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS 20C |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0029 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS COLD COMPRESSORS |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0030 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS CGC |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0031 | INSTRUMENT AIR DISTRIBUTION LAYOUT BUTADIENE |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0032 | INSTRUMENT AIR DISTRIBUTION LAYOUT COOLING WATER UNIT |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0033 | INSTRUMENT AIR DISTRIBUTION LAYOUT UTILITIES |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0034 | INSTRUMENT AIR DISTRIBUTION LAYOUT WASTE WATER TREATMENT |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0035 | INSTRUMENT AIR DISTRIBUTION LAYOUT FLARE AREA |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-10-09
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I36 Local panel plot plan drawing
Category Code: I37 Local panel arrangement drawing
Category Code: I38 Layout of inst wiring (grounding)
Category Code: I39 Instrument air piping and tubing drawing
Category Code: I40 Instrument utilities tubing layout drawing
Category Code: I41 Instrument wiring connection list
Category Code: I42 Junction box Arrangement Drawing
| IE | OL1-2I42-0001 | INSTRUMENT AND F&G WIRING DRAWINGS FOR FAR-E SYSTEMS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC1; IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-28; IFR: 2020-06-15; IFD: 2020-10-31; IFD: 2021-02-26
[6 empty] | Revised Plan | IFR: 2020-02-28; IFR: 2020-06-15; IFD: 2020-10-31; IFD: 2021-02-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-0002 | INSTRUMENT AND F&G WIRING DRAWINGS FOR FAR-C SYSTEMS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC1; IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-28; IFR: 2020-06-15; IFD: 2020-10-31; IFD: 2021-02-26
[6 empty] | Revised Plan | IFR: 2020-02-28; IFR: 2020-06-15; IFD: 2020-10-31; IFD: 2021-02-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-0003 | INSTRUMENT AND F&G WIRING DRAWINGS FOR FAR FL SYSTEMS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC1; IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-28; IFR: 2020-06-15; IFD: 2020-10-31; IFD: 2021-02-26
[6 empty] | Revised Plan | IFR: 2020-02-28; IFR: 2020-06-15; IFD: 2020-10-31; IFD: 2021-02-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-0004 | INSTRUMENT AND F&G WIRING DRAWINGS FOR CCB AND OTHER BUILDINGS SYSTEMS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC1; IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-28; IFR: 2020-06-15; IFD: 2020-10-31; IFD: 2021-02-26
[6 empty] | Revised Plan | IFR: 2020-02-28; IFR: 2020-06-15; IFD: 2020-10-31; IFD: 2021-02-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT GRADE TO EL AAFT-AIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1100 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1100 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT GRADE TO EL AAFT-AIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1200 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1200 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT GRADE TO EL AAFT-AIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1300 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1300 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT GRADE TO EL AAFT-AIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1400 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1400 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT GRADE TO EL AAFT-AIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1500 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1500 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT GRADE TO EL AAFT-AIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1600 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1600 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 3 | Purpose** | IFR: IFR; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-16; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-16; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I43 Instrument cable list and cable cutting plan
| IE | OL1-2I43-0001 | INSTRUMENT CABLE LIST FOR FAR C SYSTEMS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC1; IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; IFR: 2020-08-15; IFD: 2020-11-15; IFD: 2021-01-31
[6 empty] | Revised Plan | IFR: 2020-05-15; IFR: 2020-08-15; IFD: 2020-11-15; IFD: 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0002 | INSTRUMENT CABLE LIST FOR FAR E SYSTEMS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC1; IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; IFR: 2020-08-15; IFD: 2020-11-15; IFD: 2021-01-31
[6 empty] | Revised Plan | IFR: 2020-05-15; IFR: 2020-08-15; IFD: 2020-11-15; IFD: 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0003 | INSTRUMENT CABLE LIST FOR FAR FL SYSTEMS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC1; IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; IFR: 2020-08-15; IFD: 2020-11-15; IFD: 2021-01-31
[6 empty] | Revised Plan | IFR: 2020-05-15; IFR: 2020-08-15; IFD: 2020-11-15; IFD: 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0004 | INSTRUMENT CABLE LIST FOR CCB AND OTHER BULDINGS SYSTEMS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC1; IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; IFR: 2020-08-15; IFD: 2020-11-15; IFD: 2021-01-31
[6 empty] | Revised Plan | IFR: 2020-05-15; IFR: 2020-08-15; IFD: 2020-11-15; IFD: 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0011 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FOR FAR C SYSTEMS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-09-15; IFD: 2020-12-31
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-09-15; IFD: 2020-12-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0012 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FOR FAR E SYSTEMS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-09-15; IFD: 2020-12-31
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-09-15; IFD: 2020-12-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0013 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FOR FAR FL SYSTEMS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-09-15; IFD: 2020-12-31
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-09-15; IFD: 2020-12-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0014 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FORCCB AND OTHER BULDINGS SYSTEMS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-15; IFR: 2020-09-15; IFD: 2020-12-31
[6 empty] | Revised Plan | IFR: 2020-06-15; IFR: 2020-09-15; IFD: 2020-12-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I44 Power Supply Distribution Drawing
| IE | OL1-2I44-1001 | INST.POW.SUP.DISTRIBUTION FOR CCB |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-22; IFR: 2020-01-29; IFD: 2020-06-17
[6 empty] | Revised Plan | IFR: 2019-10-31; IFR: 2020-01-29; IFD: 2020-06-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I44-1002 | INST.POW.SUP.DISTRIBUTION FOR FAR C |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-22; IFR: 2020-01-29; IFD: 2020-06-17
[6 empty] | Revised Plan | IFR: 2019-10-31; IFR: 2020-01-29; IFD: 2020-06-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I44-1003 | INST.POW.SUP.DISTRIBUTION FOR FAR E |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-22; IFR: 2020-01-29; IFD: 2020-06-17
[6 empty] | Revised Plan | IFR: 2019-10-31; IFR: 2020-01-29; IFD: 2020-06-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I44-1004 | INST.POW.SUP.DISTRIBUTION FOR FAR FL |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-22; IFR: 2020-01-29; IFD: 2020-06-17
[6 empty] | Revised Plan | IFR: 2019-10-31; IFR: 2020-01-29; IFD: 2020-06-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I45 Control Room and Rack Room Drawings
Category Code: I46 Layout of instrument cabinets / panels in Control Room and Rack Room
| IE | OL1-2I46-1001 | CONTROL & TECH.ROOM LAYOUT, CENTRAL CONTROL BUILDING |  |  | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; IFD: 2020-04-30; IFD: 2020-08-31
[6 empty] | Revised Plan | IFD: 2020-04-30; IFD: 2020-08-31
[6 empty] | Issue Actual | IFR: 2019-05-06; IFR: 2019-05-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01568; IFR: TPSK-LSPA1-T-IE-01568
[6 empty] | Return Date | IFR: 2019-05-23; IFR: 2019-05-23
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I46-1002 | FAR C INSTRUMENT EQUIPMENT LAYOUT |  |  | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; IFD: 2020-04-30; IFD: 2020-08-31
[6 empty] | Revised Plan | IFD: 2020-04-30; IFD: 2020-08-31
[6 empty] | Issue Actual | IFR: 2019-03-26; IFR: 2019-03-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01153; IFR: TPSK-LSPA1-T-IE-01153
[6 empty] | Return Date | IFR: 2019-04-05; IFR: 2019-04-05
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I46-1003 | FAR E INSTRUMENT EQUIPMENT LAYOUT |  |  | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; IFD: 2020-04-30; IFD: 2020-08-31
[6 empty] | Revised Plan | IFD: 2020-04-30; IFD: 2020-08-31
[6 empty] | Issue Actual | IFR: 2019-03-26; IFR: 2019-03-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01153; IFR: TPSK-LSPA1-T-IE-01153
[6 empty] | Return Date | IFR: 2019-04-05; IFR: 2019-04-05
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I46-1004 | FAR FL INSTRUMENT EQUIPMENT LAYOUT |  |  | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; IFD: 2020-04-30; IFD: 2020-08-31
[6 empty] | Revised Plan | IFD: 2020-04-30; IFD: 2020-08-31
[6 empty] | Issue Actual | IFR: 2019-03-26; IFR: 2019-03-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01153; IFR: TPSK-LSPA1-T-IE-01153
[6 empty] | Return Date | IFR: 2019-04-05; IFR: 2019-04-05
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I46-1005 | MAINTENANCE BUILDING INSTRUMENT EQUIPMENT LAYOUT |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-30; IFR: 2020-04-30; IFD: 2020-08-31
[6 empty] | Revised Plan | IFR: 2019-11-30; IFR: 2020-04-30; IFD: 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I46-1006 | EMERGENCY CENTER BUILDING INSTRUMENT EQUIPMENT LAYOUT |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-30; IFR: 2020-04-30; IFD: 2020-08-31
[6 empty] | Revised Plan | IFR: 2019-11-30; IFR: 2020-04-30; IFD: 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I47 Layout of instrument main and secondary cable route in Control Room and Rack Room
| IE | OL1-2I47-1001 | FAR E INSTRUMENT CABLE ROUTING |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC1; IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-28; IFR: 2020-07-31; IFD: 2020-11-15; IFD: 2021-01-15
[6 empty] | Revised Plan | IFR: 2020-02-28; IFR: 2020-07-31; IFD: 2020-11-15; IFD: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1002 | FAR C INSTRUMENT CABLE ROUTING |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC1; IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-28; IFR: 2020-07-31; IFD: 2020-11-15; IFD: 2021-01-15
[6 empty] | Revised Plan | IFR: 2020-02-28; IFR: 2020-07-31; IFD: 2020-11-15; IFD: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1003 | FAR FL INSTRUMENT CABLE ROUTING |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC1; IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-28; IFR: 2020-07-31; IFD: 2020-11-15; IFD: 2021-01-15
[6 empty] | Revised Plan | IFR: 2020-02-28; IFR: 2020-07-31; IFD: 2020-11-15; IFD: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1004 | INSTRUMENT CABLE ROUTING CENTRAL CONTROL BUILDING AND OTHER BUILDINGS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC1; IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-28; IFR: 2020-07-31; IFD: 2020-11-15; IFD: 2021-01-15
[6 empty] | Revised Plan | IFR: 2020-02-28; IFR: 2020-07-31; IFD: 2020-11-15; IFD: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1005 | CCB INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT PACKAGE A1 |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-15; IFR: 2020-07-15; IFD: 2020-12-01
[6 empty] | Revised Plan | IFR: 2020-02-15; IFR: 2020-07-15; IFD: 2020-12-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1006 | FAR E INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-15; IFR: 2020-07-15; IFD: 2020-12-01
[6 empty] | Revised Plan | IFR: 2020-02-15; IFR: 2020-07-15; IFD: 2020-12-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1007 | FAR C INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-15; IFR: 2020-07-15; IFD: 2020-12-01
[6 empty] | Revised Plan | IFR: 2020-02-15; IFR: 2020-07-15; IFD: 2020-12-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1008 | FAR FL INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-15; IFR: 2020-07-15; IFD: 2020-12-01
[6 empty] | Revised Plan | IFR: 2020-02-15; IFR: 2020-07-15; IFD: 2020-12-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1021 | TELECOM LOCATION AND CABLE ROUTING FAR E |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-31; IFR: 2020-02-28; IFD: 2020-08-31
[6 empty] | Revised Plan | IFR: 2019-12-31; IFR: 2020-02-28; IFD: 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1022 | TELECOM LOCATION AND CABLE ROUTING FAR C |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-31; IFR: 2020-02-28; IFD: 2020-08-31
[6 empty] | Revised Plan | IFR: 2019-12-31; IFR: 2020-02-28; IFD: 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1023 | TELECOM LOCATION AND CABLE ROUTING FAR FL |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-31; IFR: 2020-02-28; IFD: 2020-08-31
[6 empty] | Revised Plan | IFR: 2019-12-31; IFR: 2020-02-28; IFD: 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1024 | TELECOM LOCATION AND CABLE ROUTING CENTRAL CONTROL BUILDING |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-31; IFR: 2020-02-28; IFD: 2020-08-31
[6 empty] | Revised Plan | IFR: 2019-12-31; IFR: 2020-02-28; IFD: 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1050 | SUB E INSTRUMENT CABLE ROUTING |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC1; IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-28; IFR: 2020-07-31; IFD: 2020-11-15; IFD: 2021-01-15
[6 empty] | Revised Plan | IFR: 2020-02-28; IFR: 2020-07-31; IFD: 2020-11-15; IFD: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1051 | SUB C INSTRUMENT CABLE ROUTING |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC1; IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-28; IFR: 2020-07-31; IFD: 2020-11-15; IFD: 2021-01-15
[6 empty] | Revised Plan | IFR: 2020-02-28; IFR: 2020-07-31; IFD: 2020-11-15; IFD: 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I48 Layout of instrument grounding wiring in Control Room and Rack Room
| IE | OL1-2I48-1001 | INSTRUMENT & TELECOM GROUNDING PHILOSOPHY DIAGRAM |  |  | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-02-14; IFD: 2019-03-14; IFD: 2019-04-14
[6 empty] | Revised Plan | IFD: 2019-09-04
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01013; IFR: TPSK-LSPA1-T-IE-01013
[6 empty] | Return Date | IFR: 2019-05-15; IFR: 2019-05-15
Owner Cmmt* | bar: IFR to IFR
| IE | OL1-2I48-1002 | INSTRUMENT / TELECOM EARTHING LAYOUT CENTRAL CONTROL BUILDING |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-01-31; IFR: 2020-05-30; IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-05-30; IFD: 2020-09-15
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02367
Return Date
Owner Cmmt*
| IE | OL1-2I48-1003 | INSTRUMENT / TELECOM EARTHING LAYOUT FAR E AND SUB E |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-31; IFR: 2020-05-30; IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-01-31; IFR: 2020-05-30; IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I48-1004 | INSTRUMENT / TELECOM EARTHING LAYOUT FAR C AND SUB C |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-31; IFR: 2020-05-30; IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-01-31; IFR: 2020-05-30; IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I48-1005 | INSTRUMENT / TELECOM EARTHING LAYOUT FAR FL |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-31; IFR: 2020-05-30; IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-01-31; IFR: 2020-05-30; IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I48-1006 | INSTRUMENT / TELECOM EARTHING LAYOUT OTHER BUILDINGS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-31; IFR: 2020-05-30; IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-01-31; IFR: 2020-05-30; IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I49 Instrument Hook-up Drawing
| IE | OL1-2I49-4101 | INSTRUMENT/TELECOM AND FIBRE OPTIC CABLES MATERIALTAKE-OFF |  |  | Purpose** | IFR: IF1T; IFR: IF2T; IFD: IF3T; IFD: IF4T
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-15; IFR: 2020-02-15; IFD: 2020-06-15; IFD: 2020-11-18
[6 empty] | Revised Plan | IFR: 2019-10-15; IFR: 2020-02-15; IFD: 2020-06-15; IFD: 2020-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4201 | CABLE TRAY & ACCESSORIES MAT.TAKE-OFF |  |  | Purpose** | IFR: IF1T; IFR: IF2T; IFD: IF3T; IFD: IF4T
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; IFR: 2020-08-30; IFD: 2020-11-30; IFD: 2021-01-31
[6 empty] | Revised Plan | IFR: 2020-05-30; IFR: 2020-08-30; IFD: 2020-11-30; IFD: 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4203 | SECONDARY CABLE TRAY & ACCESSORIES MAT.TAKE-OFF |  |  | Purpose** | IFR: IF1T; IFR: IF2T; IFD: IF3T; IFD: IF4T
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; IFR: 2020-08-30; IFD: 2020-11-30; IFD: 2021-01-31
[6 empty] | Revised Plan | IFR: 2020-05-30; IFR: 2020-08-30; IFD: 2020-11-30; IFD: 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4301 | JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES MATERIAL TAKE-OFF |  |  | Purpose** | IFR: IF1T; IFR: IF2T; IFD: IF3T; IFD: IF4T
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-24; IFR: 2020-06-01; IFD: 2020-08-15; IFD: 2020-10-15
[6 empty] | Revised Plan | IFR: 2020-02-24; IFR: 2020-06-01; IFD: 2020-08-15; IFD: 2020-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4303 | CABLE GLANDS MAT.TAKE-OFF |  |  | Purpose** | IFR: IF1T; IFR: IF2T
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; IFR: 2020-10-01
[6 empty] | Revised Plan | IFR: 2020-05-15; IFR: 2020-10-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4304 | MAIN CABLE TRANSIT (MCT) & ACCESSORIES MATERIAL TAKE OFF |  |  | Purpose** | IFR: IF1T; IFR: IF2T
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; IFR: 2020-10-01
[6 empty] | Revised Plan | IFR: 2020-05-15; IFR: 2020-10-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I50 Hook-up drawing for process lead piping for each instrument
| IE | OL1-2I50-0001 | INSTRUMENT HOOK-UP DRAWINGS ISBL UNITS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-31; IFR: 2020-05-25; IFD: 2020-09-29
[6 empty] | Revised Plan | IFR: 2019-12-31; IFR: 2020-05-25; IFD: 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I51 Hook-up drawing for IA and pneumatic
| IE | OL1-2I51-0001 | INSTRUMENT TYPICAL HOOK -UP |  |  | Purpose** | IFR: IFR; IFR: IFR; IFD: IDD; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-12-31; IFD: 2020-05-25; IFD: 2020-09-29
[6 empty] | Revised Plan | IFD: 2020-05-25; IFD: 2020-09-29
[6 empty] | Issue Actual | IFR: 2019-04-04; IFR: 2019-04-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-1254; IFR: TPSK-LSPA1-T-IE-1254
[6 empty] | Return Date | IFR: 2019-05-09; IFR: 2019-05-09
Owner Cmmt* | bar: IFR to IFR
Category Code: I52 Hook-up drawing for Steam tracing
| IE | OL1-2I52-0001 | INSTRUMENT HOOK-UP DRAWINGS OSBL UNITS |  |  | Purpose** | IFR: IFR; IFR: IDD; IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-31; IFR: 2020-05-25; IFD: 2020-09-29
[6 empty] | Revised Plan | IFR: 2019-12-31; IFR: 2020-05-25; IFD: 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I53 Instrument loop drawing diagram
| IE | OL1-2I53-0001 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - FURNACES UTILITY |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-02-15; IFR: 2021-04-06
[6 empty] | Revised Plan | IFR: 2021-02-15; IFR: 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0002 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - QUENCH |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-02-15; IFR: 2021-04-06
[6 empty] | Revised Plan | IFR: 2021-02-15; IFR: 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0003 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS 20B |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-02-15; IFR: 2021-04-06
[6 empty] | Revised Plan | IFR: 2021-02-15; IFR: 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0004 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS 20C |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-02-15; IFR: 2021-04-06
[6 empty] | Revised Plan | IFR: 2021-02-15; IFR: 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0005 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS COLD COMPRESSORS |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-02-15; IFR: 2021-04-06
[6 empty] | Revised Plan | IFR: 2021-02-15; IFR: 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0006 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS CGC |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-02-15; IFR: 2021-04-06
[6 empty] | Revised Plan | IFR: 2021-02-15; IFR: 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0007 | INSTRUMENT LOOP DRAWINGS FAR-E- METERING |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-02-15; IFR: 2021-04-06
[6 empty] | Revised Plan | IFR: 2021-02-15; IFR: 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0008 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - SUBSTATION E & FAR E |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-02-15; IFR: 2021-04-06
[6 empty] | Revised Plan | IFR: 2021-02-15; IFR: 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0009 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - SUBSTATION C & FAR C |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-02-15; IFR: 2021-04-06
[6 empty] | Revised Plan | IFR: 2021-02-15; IFR: 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0010 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - BUTADIENE |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-02-15; IFR: 2021-04-06
[6 empty] | Revised Plan | IFR: 2021-02-15; IFR: 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0011 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - COOLING WATER UNIT |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-02-15; IFR: 2021-04-06
[6 empty] | Revised Plan | IFR: 2021-02-15; IFR: 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0012 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - UTILITIES |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-02-15; IFR: 2021-04-06
[6 empty] | Revised Plan | IFR: 2021-02-15; IFR: 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0013 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - WASTE WATER TREATMENT |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-02-15; IFR: 2021-04-06
[6 empty] | Revised Plan | IFR: 2021-02-15; IFR: 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0014 | INSTRUMENT LOOP DRAWINGS FAR-FL DCS, ESD, FGS - FLARE |  |  | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-02-15; IFR: 2021-04-06
[6 empty] | Revised Plan | IFR: 2021-02-15; IFR: 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I54 Bill of bulk materials take-off
| IE | OL1-2I54-1001 | INSTRUMENT MTO 10-H-1100 |  | Class 3 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-22
[6 empty] | Revised Plan | IFR: 2019-10-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I54-2001 | INSTRUMENT MTO 10-H-1200 |  | Class 3 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-22
[6 empty] | Revised Plan | IFR: 2019-10-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I54-3001 | INSTRUMENT MTO 10-H-1300 |  | Class 3 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-22
[6 empty] | Revised Plan | IFR: 2019-10-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I54-4001 | INSTRUMENT MTO 10-H-1400 |  | Class 3 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-22
[6 empty] | Revised Plan | IFR: 2019-10-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I54-5001 | INSTRUMENT MTO 10-H-1500 |  | Class 3 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-22
[6 empty] | Revised Plan | IFR: 2019-10-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I54-6001 | INSTRUMENT MTO 10-H-1600 |  | Class 3 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-22
[6 empty] | Revised Plan | IFR: 2019-10-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I55 In-line & On equipment
| IE | OL1-2I55-0101 | MR ORIFICE AND RESTRICTION ORIFICE |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-04; IFR: 2019-09-20
[6 empty] | Revised Plan | IFR: 2019-09-13; IFR: 2019-09-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0104 | MR ROTAMETERS |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-04; IFR: 2019-09-20
[6 empty] | Revised Plan | IFR: 2019-08-30; IFR: 2019-09-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0111 | MR TURBINE METER |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-04; IFR: 2019-09-20
[6 empty] | Revised Plan | IFR: 2019-08-30; IFR: 2019-09-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0120 | MR CUSTODY TRANSFER SYSTEM |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-26; IFR: 2019-11-30
[6 empty] | Revised Plan | IFR: 2019-09-06; IFR: 2019-11-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0202 | MR MAGNETIC LEVEL GAUGE |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-20; IFR: 2020-06-12
[6 empty] | Revised Plan | IFR: 2019-12-20; IFR: 2020-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0203 | MR RADAR LEVEL INSTRUMENTS |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-20; IFR: 2020-06-12
[6 empty] | Revised Plan | IFR: 2019-12-20; IFR: 2020-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0211 | MR SPECIAL LEVEL TRANSMITTERS |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-20; IFR: 2020-06-12
[6 empty] | Revised Plan | IFR: 2019-12-20; IFR: 2020-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0212 | MR LEVEL GLASS |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-20; IFR: 2020-06-12
[6 empty] | Revised Plan | IFR: 2019-12-20; IFR: 2020-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0213 | MR LEVEL GLASS FOR STEAM DRUM |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-20; IFR: 2020-06-12
[6 empty] | Revised Plan | IFR: 2019-12-20; IFR: 2020-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0302 | MR THERMOCOUPLE/RTD WITH WELL |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-05; IFR: 2020-07-03
[6 empty] | Revised Plan | IFR: 2020-02-05; IFR: 2020-07-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0304 | MR THERMOMETER WITH WELL |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-05; IFR: 2020-07-03
[6 empty] | Revised Plan | IFR: 2020-02-05; IFR: 2020-07-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0305 | MR MULTIPLE THERMOCOUPLE / RTD |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-05; IFR: 2020-07-03
[6 empty] | Revised Plan | IFR: 2020-02-05; IFR: 2020-07-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0402 | MR PRESSURE & DIFFER.PRESS.GAUGE |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-05; IFR: 2020-08-05
[6 empty] | Revised Plan | IFR: 2020-02-05; IFR: 2020-08-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0504 | MR SEVERE SERVICE CONTROL VALVE |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-28; IFR: 2019-11-13
[6 empty] | Revised Plan | IFR: 2019-09-30; IFR: 2019-11-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0505 | MR ANTISURGE VALVES |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-28; IFR: 2019-11-13
[6 empty] | Revised Plan | IFR: 2019-09-30; IFR: 2019-11-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0506 | MR DESUPERHEATER VALVES |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-28; IFR: 2019-11-13
[6 empty] | Revised Plan | IFR: 2019-09-30; IFR: 2019-11-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0801 | MR ELECTRONIC TRANSMITTER |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-05; IFR: 2020-08-05
[6 empty] | Revised Plan | IFR: 2020-02-05; IFR: 2020-08-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2002 | MR CEMS / O2 FLUE GAS |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-06; IFR: 2019-10-30
[6 empty] | Revised Plan | IFR: 2019-08-30; IFR: 2019-10-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2201 | INLINE INSTRUMENT REQUISITION - CONTROL VALVES |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-25; IFR: 2019-07-17
[6 empty] | Revised Plan | IFR: 2019-09-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2202 | INLINE INSTRUMENT REQUISITION - PRESSURE & SAFETY RELIEF VAVLE |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-03-28; IFR: 2019-06-14
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2210 | OFFLINE INSTRUMENT REQUISITION - PRESSURE & DIFF PRESSURE TRANSMITTER |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-23; IFR: 2019-11-05
[6 empty] | Revised Plan | IFR: 2019-08-28; IFR: 2019-11-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2211 | OFFLINE INSTRUMENT REQUISITION - PRESSURE GAUGES/DRAFT GAUGES |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-23; IFR: 2019-11-05
[6 empty] | Revised Plan | IFR: 2019-08-28; IFR: 2019-11-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2212 | OFFLINE INSTRUMENT REQUISITION - TEMPERATURE TRANSMITTER |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-27; IFR: 2019-12-03
[6 empty] | Revised Plan | IFR: 2019-08-27; IFR: 2019-12-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2214 | OFFLINE INSTRUMENT REQUISITION - THERMOCOUPLE TYPE K / RTD WITH WELL |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-27; IFR: 2019-12-03
[6 empty] | Revised Plan | IFR: 2019-08-27; IFR: 2019-12-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2301 | MR SIMPLE SPECIFIC COMPONENT AND PROPERTY ANALYZERS |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-06; IFR: 2019-10-30
[6 empty] | Revised Plan | IFR: 2019-09-03; IFR: 2019-10-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2401 | MR WATER ANALYZERS |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-30; IFR: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-09-30; IFR: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2601 | MR FIRE AND GAS DEVICES |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-20; IFR: 2020-06-20
[6 empty] | Revised Plan | IFR: 2019-12-20; IFR: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4101 | MR INSTRUMENT / TELECOM AND FIBRE OPTIC CABLES |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-04; IFR: 2020-11-15
[6 empty] | Revised Plan | IFR: 2019-11-04; IFR: 2020-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4201 | MR CABLE TRAY AND ACCESSORIES |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-11; IFR: 2020-11-15
[6 empty] | Revised Plan | IFR: 2020-04-11; IFR: 2020-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4301 | MR FOR JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-01; IFR: 2020-12-15
[6 empty] | Revised Plan | IFR: 2020-06-01; IFR: 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4302 | MR CABLE GLANDS |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-01; IFR: 2020-12-15
[6 empty] | Revised Plan | IFR: 2020-06-01; IFR: 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4501 | MR MOUNTING ACCESSORIES (TUBING & FITTINGS) |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-11; IFR: 2020-11-15
[6 empty] | Revised Plan | IFR: 2020-04-11; IFR: 2020-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4502 | MR SUNSHADES |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-01; IFR: 2020-12-15
[6 empty] | Revised Plan | IFR: 2020-06-01; IFR: 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4503 | MOUNTING ACCESSORIES (TUBING & FITTINGS) MATERIALTAKE-OFF |  |  | Purpose** | IFR: IF1T; IFR: IF2T; IFD: IF3T; IFD: IF4T
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-30; IFR: 2020-06-15; IFD: 2020-09-15; IFD: 2020-11-15
[6 empty] | Revised Plan | IFR: 2020-03-30; IFR: 2020-06-15; IFD: 2020-09-15; IFD: 2020-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4505 | MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) TAKE-OFF |  |  | Purpose** | IFR: IF1T; IFR: IF2T; IFD: IF3T; IFD: IF4T
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-30; IFR: 2020-06-15; IFD: 2020-09-15; IFD: 2020-11-15
[6 empty] | Revised Plan | IFR: 2020-03-30; IFR: 2020-06-15; IFD: 2020-09-15; IFD: 2020-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4507 | STEAM & ELECTRICALTRACING MAT.TAKE-OFF |  |  | Purpose** | IFR: IF1T; IFR: IF2T
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-28; IFR: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-02-28; IFR: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4510 | MR MAIN CABLE TRANSIT (MCT) & ACCESSORIES |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-01; IFR: 2020-12-15
[6 empty] | Revised Plan | IFR: 2020-06-01; IFR: 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4511 | MR FOR MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) |  |  | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-11; IFR: 2020-11-15
[6 empty] | Revised Plan | IFR: 2020-04-11; IFR: 2020-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I61 SIL Study Document
| IE | OL1-2I61-1101 | SIS IMPLEMENTATION CALCULATION NOTES |  |  | Purpose** | IFR: IDD; IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-30; IFR: 2020-03-05
[6 empty] | Revised Plan | IFR: 2019-11-15; IFR: 2020-03-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I61-1102 | GENERAL SIS SAFETY REQUIREMENTS SPECIFICATION |  |  | Purpose** | IFR: IFR; IFR: IFR; IFD: IMP; IFD: IMP
[6 empty] | Rev. | IFR: A; IFR: A; IFD: 0; IFD: 0
[6 empty] | Issue Plan | IFR: 2019-07-30; IFD: 2020-03-05
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-01-25; IFD: 2019-04-17; IFD: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00719; IFR: TPSK-LSPA1-T-IE-00719; IFD: TPSK-LSPA1-T-IE-01392; IFD: TPSK-LSPA1-T-IE-01392
[6 empty] | Return Date | IFR: 2019-03-05; IFR: 2019-03-05; IFD: 2019-06-19
Owner Cmmt* | bar: IFR to IFR; IFD
| IE | OL1-2I61-1103 | PARTICULAR SIS SAFETY REQUIREMENTS SPECIFICATION |  |  | Purpose** | IFR: IFR; IFR: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-30; IFR: 2020-03-05
[6 empty] | Revised Plan | IFR: 2019-12-13; IFR: 2020-03-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I62 FAT Punch Lists
Category Code: I63 SAT Punch Lists
Category Code: I64 Operation and maintenance spare part for 2 years list
Category Code: I65 Initial Spare part list
Category Code: I66 Special tools book
Category Code: I70 Instruction Manual of Instrument
Category Code: I71 Control narative for complex loop
| IE | OL1-2I71-1001 | COMPLEX LOOP NARRATIVES - AREA 10 |  | Class 3 | Purpose** | IFR: IFI; IFR: IFR; IFD: IFR
Rev. | bar: IFR to IFD
[6 empty] | Issue Plan | IFR: 2019-07-19
[6 empty] | Revised Plan | IFR: 2019-03-21; IFD: 2019-03-22
[6 empty] | Issue Actual | IFR: 2019-03-21; IFD: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01128; IFD: TPSK-LSPA1-T-IE-01128
[6 empty] | Return Date | IFR: 2019-04-02; IFD: 2019-04-02
Owner Cmmt* | bar: IFR to IFD
| IE | OL1-2I71-1101 | COMPLEX CONTROL NARRATIVES (36M FURNACE) |  | Class 2 | Purpose** | IFR: IFR; IFR: IFD; IFD: IFR; IFD: IFD
Rev. | bar: IFR to IFD
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-20; IFR: 2019-05-20; IFD: 2019-05-21; IFD: 2019-05-21
[6 empty] | Issue Actual | IFR: 2019-05-20; IFR: 2019-05-20; IFD: 2019-05-21; IFD: 2019-05-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01696; IFR: TPSK-LSPA1-T-IE-01700; IFD: TPSK-LSPA1-T-IE-01696; IFD: TPSK-LSPA1-T-IE-01700
[6 empty] | Return Date | IFR: 2019-06-13; IFD: 2019-06-13
Owner Cmmt* | bar: IFR; IFD
| IE | OL1-2I71-1201 | COMPLEX CONTROL NARRATIVES |  | Class 2 | Purpose** | IFR | IFR | IFD | IFD | IBD | IFD | IFD | IFC
Rev. | bar: IFR to R2 IFD; R2 IFD to R2 IFD
[6 empty] | Issue Plan | 2019-03-19 |  | 2019-03-19 |  | 2019-03-19 | 2019-03-19 |  | 2019-10-28
[6 empty] | Revised Plan | R2 IFC: 2019-10-28
[6 empty] | Issue Actual | IFR: 2019-04-09; R2 IFR: 2019-04-10; R2 IFD: 2019-05-20; R2 IFD: 2019-05-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01289 | TPSK-LSPA1-T-IE-01289 | TPSK-LSPA1-T-IE-01700 | TPSK-LSPA1-T-IE-01700 |  | TPSK-LSPA1-T-IE-01700 | TPSK-LSPA1-T-IE-01700
[6 empty] | Return Date | 2019-06-13 | 2019-06-13 | 2019-06-13 | 2019-06-13 |  | 2019-06-13 | 2019-06-13
Owner Cmmt* | bar: IFR to R2 IFD; R2 IFD to R2 IFD
| IE | OL1-2I71-2001 | COMPLEX LOOP NARRATIVES - AREA 20 |  | Class 3 | Purpose** | IFR: IFI; R2 IFR: IFR; R2 IFD: IFR
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-07-19
[6 empty] | Revised Plan | R2 IFR: 2019-03-21; R2 IFD: 2019-03-22
[6 empty] | Issue Actual | R2 IFR: 2019-03-21; R2 IFD: 2019-03-22
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-IE-01132; R2 IFD: TPSK-LSPA1-T-IE-01132
[6 empty] | Return Date | R2 IFR: 2019-04-02; R2 IFD: 2019-04-02
Owner Cmmt* | bar: R2 IFR to R2 IFD
| IE | OL1-2I71-2101 | COMPLEX LOOP NARRATIVES - AREA 21 |  | Class 3 | Purpose** | IFR: IFI; R2 IFR: IFR; R2 IFD: IFR
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-07-19
[6 empty] | Revised Plan | R2 IFR: 2019-03-25; R2 IFD: 2019-03-26
[6 empty] | Issue Actual | R2 IFR: 2019-03-25; R2 IFD: 2019-03-26
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-IE-01147; R2 IFD: TPSK-LSPA1-T-IE-01147
[6 empty] | Return Date | R2 IFR: 2019-05-24; R2 IFD: 2019-05-24
Owner Cmmt* | bar: R2 IFR to R2 IFD
| IE | OL1-2I71-2201 | COMPLEX LOOP NARRATIVES - AREA 22 |  | Class 3 | Purpose** | IFR: IFI; R2 IFR: IFR; R2 IFD: IFR
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-07-19
[6 empty] | Revised Plan | R2 IFR: 2019-05-01; R2 IFD: 2019-05-02
[6 empty] | Issue Actual | R2 IFR: 2019-05-01; R2 IFD: 2019-05-02
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-IE-01544; R2 IFD: TPSK-LSPA1-T-IE-01544
[6 empty] | Return Date | R2 IFR: 2019-06-03; R2 IFD: 2019-06-03
Owner Cmmt* | bar: R2 IFR to R2 IFD
| IE | OL1-2I71-2301 | COMPLEX LOOP NARRATIVES - AREA 23 |  | Class 3 | Purpose** | IFR: IFI; R2 IFR: IFR; R2 IFD: IFR
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-07-19
[6 empty] | Revised Plan | R2 IFR: 2019-04-15; R2 IFD: 2019-04-16
[6 empty] | Issue Actual | R2 IFR: 2019-04-15; R2 IFD: 2019-04-16
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-IE-01358; R2 IFD: TPSK-LSPA1-T-IE-01358
[6 empty] | Return Date | R2 IFR: 2019-06-03; R2 IFD: 2019-06-03
Owner Cmmt* | bar: R2 IFR to R2 IFD
| IE | OL1-2I71-2401 | COMPLEX LOOP NARRATIVES - AREA 24 |  | Class 3 | Purpose** | IFR: IFI; R2 IFR: IFR; R2 IFD: IFR
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-07-19
[6 empty] | Revised Plan | R2 IFR: 2019-05-07; R2 IFD: 2019-05-08
[6 empty] | Issue Actual | R2 IFR: 2019-05-07; R2 IFD: 2019-05-08
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-IE-01605; R2 IFD: TPSK-LSPA1-T-IE-01605
[6 empty] | Return Date | R2 IFR: 2019-06-19; R2 IFD: 2019-06-19
Owner Cmmt* | bar: R2 IFR to R2 IFD
| IE | OL1-2I71-2501 | COMPLEX LOOP NARRATIVES - AREA 25 |  | Class 3 | Purpose** | IFR: IFI; R2 IFR: IFR; R2 IFD: IFR
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-07-19
[6 empty] | Revised Plan | R2 IFR: 2019-04-15; R2 IFD: 2019-04-16
[6 empty] | Issue Actual | R2 IFR: 2019-04-15; R2 IFD: 2019-04-16
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-IE-01358; R2 IFD: TPSK-LSPA1-T-IE-01358
[6 empty] | Return Date | R2 IFR: 2019-06-03; R2 IFD: 2019-06-03
Owner Cmmt* | bar: R2 IFR to R2 IFD
| IE | OL1-2I71-2601 | COMPLEX LOOP NARRATIVES - AREA 26 |  | Class 3 | Purpose** | IFR: IFI; R2 IFR: IFR; R2 IFD: IFR
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-07-19
[6 empty] | Revised Plan | R2 IFR: 2019-05-14; R2 IFD: 2019-05-15
[6 empty] | Issue Actual | R2 IFR: 2019-05-14; R2 IFD: 2019-05-15
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-IE-01662; R2 IFD: TPSK-LSPA1-T-IE-01662
[6 empty] | Return Date | R2 IFR: 2019-06-19; R2 IFD: 2019-06-19
Owner Cmmt* | bar: R2 IFR to R2 IFD
| IE | OL1-2I71-2701 | COMPLEX LOOP NARRATIVES - AREA 27 |  | Class 3 | Purpose** | IFR: IFI; R2 IFR: IFR; R2 IFD: IFR
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-07-19
[6 empty] | Revised Plan | R2 IFR: 2019-05-14; R2 IFD: 2019-05-15
[6 empty] | Issue Actual | R2 IFR: 2019-05-14; R2 IFD: 2019-05-15
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-IE-01662; R2 IFD: TPSK-LSPA1-T-IE-01662
[6 empty] | Return Date | R2 IFR: 2019-06-19; R2 IFD: 2019-06-19
Owner Cmmt* | bar: R2 IFR to R2 IFD
| IE | OL1-2I71-2801 | COMPLEX LOOP NARRATIVES - AREA 28 |  | Class 3 | Purpose** | IFR: IFI; R2 IFR: IFR; R2 IFD: IFR
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-07-19
[6 empty] | Revised Plan | R2 IFR: 2019-05-30; R2 IFD: 2019-05-31
[6 empty] | Issue Actual | R2 IFR: 2019-05-30; R2 IFD: 2019-05-31
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-IE-01778; R2 IFD: TPSK-LSPA1-T-IE-01778
[6 empty] | Return Date | R2 IFR: 2019-06-21; R2 IFD: 2019-06-21
Owner Cmmt* | bar: R2 IFR to R2 IFD
| IE | OL1-2I71-2901 | COMPLEX LOOP NARRATIVES - AREA 29 |  | Class 3 | Purpose** | IFR: IFI; R2 IFR: IFR; R2 IFD: IFR
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-07-19
[6 empty] | Revised Plan | R2 IFR: 2019-06-03; R2 IFD: 2019-06-10
[6 empty] | Issue Actual | R2 IFR: 2019-06-03; R2 IFD: 2019-06-10
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-IE-01791; R2 IFD: TPSK-LSPA1-T-IE-01791
[6 empty] | Return Date | R2 IFD: 2019-07-01
Owner Cmmt* | bar: R2 IFD
| IE | OL1-2I71-3001 | COMPLEX LOOP NARRATIVES - AREA 30 |  | Class 3 | Purpose** | IFR: IFI; R2 IFR: IFR; R2 IFD: IFR
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-07-19
[6 empty] | Revised Plan | IFR: 2019-08-19; R2 IFR: 2019-06-18; R2 IFD: 2019-06-18
[6 empty] | Issue Actual | R2 IFR: 2019-06-18; R2 IFD: 2019-06-18
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-IE-01906; R2 IFD: TPSK-LSPA1-T-IE-01906
[6 empty] | Return Date | R2 IFR: 2019-07-09; R2 IFD: 2019-07-09
Owner Cmmt* | bar: R2 IFR to R2 IFD
| IE | OL1-2I71-5001 | COMPLEX LOOP NARRATIVES - AREA 50 |  | Class 3 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-19
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-5101 | Complex Loop Narratives - Area 51 - BFW-Steam -Steam Condensate System |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IBD
Rev. | bar: IFR to R2 IFD
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-08; R2 IFR: 2019-05-09; R2 IFD: 2019-08-07
[6 empty] | Issue Actual | IFR: 2019-05-08; R2 IFR: 2019-05-09; R2 IFD: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01614; R2 IFR: TPSK-LSPA1-T-IE-01614; R2 IFD: TPSK-LSPA1-T-IE-02344
[6 empty] | Return Date | IFR: 2019-06-19; R2 IFR: 2019-06-19
Owner Cmmt* | bar: IFR to R2 IFR
| IE | OL1-2I71-5201 | Complex Loop Narratives Area 52 - Fuel System |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IBD
Rev. | bar: IFR to R2 IFD
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-09; R2 IFR: 2019-05-10; R2 IFD: 2019-08-07
[6 empty] | Issue Actual | IFR: 2019-05-09; R2 IFR: 2019-05-10; R2 IFD: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01632; R2 IFR: TPSK-LSPA1-T-IE-01632; R2 IFD: TPSK-LSPA1-T-IE-02344
[6 empty] | Return Date | IFR: 2019-06-19; R2 IFR: 2019-06-19
Owner Cmmt* | bar: IFR to R2 IFR
| IE | OL1-2I71-5301 | COMPLEX LOOP NARRATIVES - AREA 53 |  | Class 3 | Purpose** | IFR: IFI; R2 IFR: IFR; R2 IFD: IFR
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-07-19
[6 empty] | Revised Plan | R2 IFR: 2019-03-12; R2 IFD: 2019-03-13
[6 empty] | Issue Actual | R2 IFR: 2019-03-12; R2 IFD: 2019-03-13
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-IE-01037; R2 IFD: TPSK-LSPA1-T-IE-01037
Return Date
Owner Cmmt*
| IE | OL1-2I71-5501 | COMPLEX LOOP NARRATIVES - AREA 55 |  | Class 3 | Purpose** | IFR: IFI; R2 IFR: IFR; R2 IFD: IFR
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-07-19
[6 empty] | Revised Plan | R2 IFR: 2019-05-02; R2 IFD: 2019-05-03
[6 empty] | Issue Actual | R2 IFR: 2019-05-02; R2 IFD: 2019-05-03
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-IE-01564; R2 IFD: TPSK-LSPA1-T-IE-01564
[6 empty] | Return Date | R2 IFR: 2019-06-03; R2 IFD: 2019-06-03
Owner Cmmt* | bar: R2 IFR to R2 IFD
| IE | OL1-2I71-5601 | COMPLEX LOOP NARRATIVES - AREA 56 |  | Class 3 | Purpose** | IFR: IFI; R2 IFR: IFR; R2 IFD: IFR
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-07-19
[6 empty] | Revised Plan | R2 IFR: 2019-05-01; R2 IFD: 2019-05-02
[6 empty] | Issue Actual | R2 IFR: 2019-05-01; R2 IFD: 2019-05-02
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-IE-01544; R2 IFD: TPSK-LSPA1-T-IE-01544
[6 empty] | Return Date | R2 IFR: 2019-06-03; R2 IFD: 2019-06-03
Owner Cmmt* | bar: R2 IFR to R2 IFD
| IE | OL1-2I71-5901 | Complex Loop Narratives - Area 59 - Supporting Utilities Auxiliaries |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IBD; R2 IFD: IBD
Rev. | bar: IFR to R2 IFD
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-25; R2 IFR: 2019-03-26; R2 IFD: 2019-07-03; R2 IFD: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-03-25; R2 IFR: 2019-03-26; R2 IFD: 2019-07-03; R2 IFD: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01140; R2 IFR: TPSK-LSPA1-T-IE-01140; R2 IFD: TPSK-LSPA1-T-IE-02052; R2 IFD: TPSK-LSPA1-T-IE-02052
[6 empty] | Return Date | IFR: 2019-05-24; R2 IFR: 2019-05-24
Owner Cmmt* | bar: IFR to R2 IFR
Category Code: I76 Appraisal Report for Consultancy Service |  |  |  |  | Class 2 | Purpose**
Category Code: I77 Appraisal Report for EPC Contractor Work | [5 empty] | Rev.
Category Code: I78 Appraisal Report for Vendor/Supplier | [5 empty] | Issue Plan
Category Code: I81 DCS System Document | [5 empty] | Revised Plan
| IE | OL1-2I81-1001 | CTRL & SAFETY SYST.CONNECTION DIAG. |  |  | Purpose** | IFR | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | IFR: A; R2 IFR: A; R2 IFD: 0; R2 IFD: 0
[6 empty] | Issue Plan | IFR: 2019-01-24; R2 IFD: 2019-05-21; R2 IBD: 2019-10-04; R2 IFD: 2019-10-04
[6 empty] | Revised Plan | R2 IBD: 2019-10-04; R2 IFD: 2019-10-04
[6 empty] | Issue Actual | IFR: 2019-03-08; R2 IFR: 2019-03-11; R2 IFD: 2019-06-13; R2 IFD: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01012; R2 IFR: TPSK-LSPA1-T-IE-01012; R2 IFD: TPSK-LSPA1-T-IE-01889; R2 IFD: TPSK-LSPA1-T-IE-01889
[6 empty] | Return Date | IFR: 2019-05-15; R2 IFR: 2019-05-15; R2 IFD: 2019-07-01
Owner Cmmt* | bar: IFR to R2 IFR; R2 IFD
| IE | OL1-2I81-1002 | CTRL & SAFETY SYST.ARCHITECTURE |  |  | Purpose** | IFR | IFR | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-01-24; R2 IBD: 2019-05-21; R2 IFD: 2019-10-04; R2 IFD: 2019-10-04
[6 empty] | Revised Plan | R2 IBD: 2019-09-03; R2 IFD: 2019-10-04; R2 IFD: 2019-10-04
[6 empty] | Issue Actual | IFR: 2019-02-22; R2 IFR: 2019-02-25; R2 IFD: 2019-05-02; R2 IFD: 2019-05-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00912; R2 IFR: TPSK-LSPA1-T-IE-00912; R2 IFD: TPSK-LSPA1-T-IE-01551; R2 IFD: TPSK-LSPA1-T-IE-01551
[6 empty] | Return Date | IFR: 2019-03-08; R2 IFR: 2019-03-08; R2 IFD: 2019-05-18; R2 IFD: 2019-05-18
Owner Cmmt* | bar: IFR to R2 IFD
| IE | OL1-2I81-1003 | ELECTRIC.INSTRUMENT INTERF. |  |  | Purpose** | IFR: IFR; R2 IFR: IDD; R2 IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-28; R2 IFR: 2019-12-13; R2 IFD: 2020-06-01
[6 empty] | Revised Plan | IFR: 2019-09-27; R2 IFR: 2019-12-13; R2 IFD: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I81-1004 | GRAPHIC DISLAYS |  |  | Purpose** | IFR: IFR; R2 IFR: IDD; R2 IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-29; R2 IFR: 2020-03-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2019-11-29; R2 IFR: 2020-03-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I81-1005 | OPERATOR TREND DISPLAY DEFINITION |  |  | Purpose** | IFR: IFR; R2 IFR: IDD; R2 IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-29; R2 IFR: 2020-03-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2019-11-29; R2 IFR: 2020-03-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I82 ESD system Document
Category Code: I83 FGS system Document
Category Code: I84 Analyzer system Document
| IE | OL1-2I84-2001 | ANALYZER SYST.BLOCK DIAGRAM |  |  | Purpose** | IFR: IFR; R2 IFR: IBD; R2 IFD: IDD
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-18; R2 IFR: 2020-05-18; R2 IFD: 2020-11-07
[6 empty] | Revised Plan | IFR: 2020-03-18; R2 IFR: 2020-05-18; R2 IFD: 2020-11-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I84-2002 | ANALYZER SHELTER LAYOUT |  |  | Purpose** | IFR: IBD
Rev.
[6 empty] | Issue Plan | IFR: 2019-03-04
[6 empty] | Revised Plan | IFR: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I84-2003 | ANALYZER SAMPLE LOOP ARRANGEMENT |  |  | Purpose** | IFR: IFR; R2 IFR: IDD; R2 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-17; R2 IFR: 2020-06-17; R2 IFD: 2020-12-07
[6 empty] | Revised Plan | IFR: 2020-04-17; R2 IFR: 2020-06-17; R2 IFD: 2020-12-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I84-2004 | AMADAS ARCHITECTURE |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02283
[6 empty] | Return Date | IFR: 2019-08-16
Owner Cmmt* | bar: IFR
Category Code: I85 Custody meter Document
Category Code: I86 Tank gauging Document
Category Code: I87 Pelletizing system Document
Category Code: I90 Vendor documents of Instrument
Category Code: I91 Index/List
| IE | OL1-2I91-0001 | INSTRUMENT LIST |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0002 | INSTRUMENT LIST - SUBSTATION E & FAR E |  |  | Purpose** | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | 2019-05-30 |  | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2019-10-15 |  | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Issue Actual | IFR: 2019-07-15; R2 IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02132; R2 IFR: TPSK-LSPA1-T-IE-02132
[6 empty] | Return Date | R2 IFR: 2019-08-12
Owner Cmmt* | bar: R2 IFR
| IE | OL1-2I91-0003 | INSTRUMENT LIST - SUBSTATION C & FAR C |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2019-10-15 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0004 | INSTRUMENT LIST - FURNACES UTILITY |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2019-10-15 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0005 | INSTRUMENT LIST - QUENCH |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2019-10-15 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0006 | INSTRUMENT LIST - PROCESS 20B |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2019-10-15 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0007 | INSTRUMENT LIST - PROCESS 20C |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2019-10-15 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0008 | INSTRUMENT LIST - PROCESS COLD COMPRESSORS |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2019-10-15 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0009 | INSTRUMENT LIST - PROCESS CGC |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2019-10-15 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0010 | INSTRUMENT LIST - BUTADIENE |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2019-10-15 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0011 | INSTRUMENT LIST - COOLING WATER UNIT |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2019-10-15 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0012 | INSTRUMENT LIST - UTILITIES |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2019-10-15 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0013 | INSTRUMENT LIST - WASTE WATER TREATMENT |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2019-10-15 | 2019-12-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0014 | INSTRUMENT LIST - FLARE |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2019-10-15 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0020 | INSTRUMENT CLASSES |  |  | Purpose** | IFR: IFR; R2 IFR: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-19; R2 IFR: 2020-06-30
[6 empty] | Revised Plan | IFR: 2020-05-19; R2 IFR: 2020-06-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0100 | INSTRUMENT CONTROL SYSTEMS EQUIPMENT LIST |  |  | Purpose** | IFR: IFR; R2 IFR: IDD; R2 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30; R2 IFR: 2020-08-30; R2 IFD: 2020-12-31
[6 empty] | Revised Plan | IFR: 2020-04-30; R2 IFR: 2020-08-30; R2 IFD: 2020-12-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0102 | ICSS DATA BASE |  |  | Purpose** | IFR: IBD; R2 IFR: IDD; R2 IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-28; R2 IFR: 2020-01-29; R2 IFD: 2020-06-01
[6 empty] | Revised Plan | IFR: 2019-08-30; R2 IFR: 2020-01-29; R2 IFD: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0103 | INSTRUMENT RANGE, ALARM & TRIP LIST |  |  | Purpose** | IFR: IDD; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R2 IFR: 2020-07-15
[6 empty] | Revised Plan | IFR: 2020-05-30; R2 IFR: 2020-07-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0104 | INSTRUMENT LIST - METERING |  |  | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2019-10-15 | 2019-10-15 | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1001 | IN/OUT SUMMARY |  |  | Purpose** | IFR: IBD; R2 IFR: IDD; R2 IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-28; R2 IFR: 2020-01-29; R2 IFD: 2020-06-01
[6 empty] | Revised Plan | IFR: 2019-08-30; R2 IFR: 2020-01-29; R2 IFD: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1002 | INSTRUMENT INDEX |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IBD; R2 IFD: IFD; R2 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-04; R2 IFR: 2019-06-13; R2 IFD: 2019-06-24; R2 IFD: 2019-10-28
[6 empty] | Revised Plan | R2 IFD: 2019-10-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1003 | FURNACE ANALYZER LIST |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-10; R2 IFR: 2019-07-01
[6 empty] | Revised Plan | R2 IFR: 2019-08-23
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1004 | CONTROLLER AND SPLIT-RANGE LIST OSBL |  |  | Purpose** | IFR: IDD; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R2 IFR: 2020-07-15
[6 empty] | Revised Plan | IFR: 2020-05-30; R2 IFR: 2020-07-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1005 | CONTROLLER AND SPLIT-RANGE LIST ISBL |  |  | Purpose** | IFR: IDD; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R2 IFR: 2020-07-15
[6 empty] | Revised Plan | IFR: 2020-05-30; R2 IFR: 2020-07-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-2000 | ANALYZER LIST |  |  | Purpose** | IFR: IBD; R2 IFR: IDD
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-30; R2 IFR: 2020-02-02
[6 empty] | Revised Plan | IFR: 2019-09-06; R2 IFR: 2020-02-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-2002 | INSTRUMENT INDEX |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IBD; R2 IFD: IFD; R2 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-04; R2 IFR: 2019-06-13; R2 IFD: 2019-06-24; R2 IFD: 2019-10-28
[6 empty] | Revised Plan | R2 IFD: 2019-10-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-2003 | FURNACE ANALYZER LIST - FURNACES 10-H-1200 - 10-H-1500 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-10; R2 IFR: 2019-07-01
[6 empty] | Revised Plan | R2 IFR: 2019-08-23
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-3002 | INSTRUMENT INDEX |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IBD; R2 IFD: IFD; R2 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-04; R2 IFR: 2019-06-13; R2 IFD: 2019-06-24; R2 IFD: 2019-10-28
[6 empty] | Revised Plan | R2 IFD: 2019-10-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-3003 | FURNACE ANALYZER LIST - FURNACES 10-H-1300 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-10; R2 IFR: 2019-07-01
[6 empty] | Revised Plan | R2 IFR: 2019-08-23
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-4002 | INSTRUMENT INDEX |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IBD; R2 IFD: IFD; R2 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-04; R2 IFR: 2019-06-13; R2 IFD: 2019-06-24; R2 IFD: 2019-10-28
[6 empty] | Revised Plan | R2 IFD: 2019-10-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-4003 | FURNACE ANALYZER LIST - FURNACES 10-H-1400 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-10; R2 IFR: 2019-07-01
[6 empty] | Revised Plan | R2 IFR: 2019-08-23
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-5002 | INSTRUMENT INDEX |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IBD; R2 IFD: IFD; R2 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-04; R2 IFR: 2019-06-13; R2 IFD: 2019-06-24; R2 IFD: 2019-10-28
[6 empty] | Revised Plan | R2 IFD: 2019-10-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-5003 | FURNACE ANALYZER LIST - FURNACES 10-H-1500 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-10; R2 IFR: 2019-07-01
[6 empty] | Revised Plan | R2 IFR: 2019-08-23
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-6002 | INSTRUMENT INDEX |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IBD; R2 IFD: IFD; R2 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-04; R2 IFR: 2019-06-13; R2 IFD: 2019-06-24; R2 IFD: 2019-10-28
[6 empty] | Revised Plan | R2 IFD: 2019-10-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-6003 | FURNACE ANALYZER LIST - FURNACES 10-H-1600 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-10; R2 IFR: 2019-07-01
[6 empty] | Revised Plan | R2 IFR: 2019-08-23
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I92 Procedures & Standards
| IE | OL1-2I92-0050 | JSS FOR ANALYSER SYSTEMS & HOUSES |  |  | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFF
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-04-02; R2 IFD: 2019-09-06
[6 empty] | Revised Plan | R2 IFD: 2019-09-06
[6 empty] | Issue Actual | IFR: 2019-04-12; R2 IFR: 2019-04-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01332; R2 IFR: TPSK-LSPA1-T-CV-01332
[6 empty] | Return Date | IFR: 2019-05-09; R2 IFR: 2019-05-09
Owner Cmmt* | bar: IFR to R2 IFR
| IE | OL1-2I92-0051 | JSS MOUNTING ACCESSORIES (TUBING & FITTINGS) |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0052 | JSS CABLE TRAY AND ACCESSORIES |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0053 | JSS FOR INSTRUMENT / TELECOM AND FIBRE OPTIC CABLES |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-15; R2 IFR: 2019-05-15
[6 empty] | Revised Plan | IFR: 2019-09-13; R2 IFR: 2019-09-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0054 | JSS FOR JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0055 | JSS FOR CABLE GLANDS AND ACCESSORIES |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0056 | JSS FOR SUNSHADES |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0057 | JSS FOR CUSTODY TRANSFER SYSTEM |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-08; R2 IFR: 2019-05-08
[6 empty] | Revised Plan | IFR: 2019-09-27; R2 IFR: 2019-09-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0058 | JSS FOR MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0059 | JSS FOR MAIN CABLE TRANSIT & ACCESSORIES |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0060 | JSS FOR FIRE AND GAS DEVICES |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-17; R2 IFR: 2020-01-16
[6 empty] | Revised Plan | IFR: 2019-12-17; R2 IFR: 2020-01-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0100 | JSS FOR FLOW METER |  |  | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFF
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-04-15; R2 IFD: 2019-05-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-13
[6 empty] | Issue Actual | R2 IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-02016; R2 IFR: TPSK-LSPA1-T-IE-02016
[6 empty] | Return Date | IFR: 2019-07-09; R2 IFR: 2019-07-09
Owner Cmmt* | bar: IFR to R2 IFR
| IE | OL1-2I92-0101 | JSS DIFFERENTIAL PRESSURE FLOW ELEMENTS |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-17; R2 IFR: 2020-01-16
[6 empty] | Revised Plan | IFR: 2019-12-17; R2 IFR: 2020-01-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0200 | JSS LEVEL INSTRUMENTS |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-17; R2 IFR: 2020-01-16
[6 empty] | Revised Plan | IFR: 2019-12-17; R2 IFR: 2020-01-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0201 | JSS FOR SURGE PROTECTION DEVICES |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2020-01-01; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0300 | JSS TEMPERATURE INSTRUMENTS |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-17; R2 IFR: 2020-01-16
[6 empty] | Revised Plan | IFR: 2019-12-17; R2 IFR: 2020-01-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0301 | JSS FOR PRESSURE & DIFF.PRESSURE INSTRUMENTS |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-17; R2 IFR: 2020-01-16
[6 empty] | Revised Plan | IFR: 2019-12-17; R2 IFR: 2020-01-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0404 | JSS ANTISURGE VALVES |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-08; R2 IFR: 2019-05-08
[6 empty] | Revised Plan | IFR: 2019-09-30; R2 IFR: 2019-12-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0405 | JSS DESUPERHEATERS VALVES |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-08; R2 IFR: 2019-05-08
[6 empty] | Revised Plan | IFR: 2019-09-30; R2 IFR: 2019-12-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0501 | JSS CONTROL VALVES |  |  | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFF
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-04-08; R2 IFD: 2019-05-08
[6 empty] | Revised Plan | R2 IFD: 2019-12-02
[6 empty] | Issue Actual | IFR: 2019-05-30; R2 IFR: 2019-05-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01770; R2 IFR: TPSK-LSPA1-T-IE-01770
[6 empty] | Return Date | R2 IFR: 2019-06-19
Owner Cmmt* | bar: R2 IFR
| IE | OL1-2I92-0503 | JSS SPECIAL CONTROL VALVE |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-08; R2 IFR: 2019-05-08
[6 empty] | Revised Plan | R2 IFR: 2019-12-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0504 | JSS SEVERE SERVICE CONTROL VALVE |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-08; R2 IFR: 2019-05-08
[6 empty] | Revised Plan | IFR: 2019-09-30; R2 IFR: 2019-12-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0602 | JSS FOR ELECTRIC OPERATED VALVES |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-08; R2 IFR: 2019-05-08
[6 empty] | Revised Plan | R2 IFR: 2019-12-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0603 | JSS FOR SPECIAL ON OFF VALVES |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-08; R2 IFR: 2019-05-08
[6 empty] | Revised Plan | R2 IFR: 2019-12-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0604 | JSS FOR ACTUATORS |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-08; R2 IFR: 2019-05-08
[6 empty] | Revised Plan | R2 IFR: 2019-12-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0606 | JSS FOR PNEUMATIC ON OFF VALVES |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-08; R2 IFR: 2019-05-08
[6 empty] | Revised Plan | R2 IFR: 2019-12-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0701 | JSS FOR SAFETY RELIEF VALVE & RUPTURE DISKS |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-11; R2 IFR: 2019-05-11
[6 empty] | Revised Plan | R2 IFR: 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0801 | JSS ELECTRONIC TRANSMITER |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-17; R2 IFR: 2020-01-16
[6 empty] | Revised Plan | IFR: 2019-12-17; R2 IFR: 2020-01-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-1701 | JSS FOR MACHINE MONITORING SYST. |  |  | Purpose** | IFR: IFR; R2 IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-04-17; R2 IFR: 2019-05-17
[6 empty] | Revised Plan | R2 IFR: 2019-10-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I93 Policy , Guidelines & Memo
Category Code: I94 SPARE NUMBER
Category Code: I94 Forms & Templates
Category Code: I95 SPARE NUMBER
Category Code: I95 Progress/Status Reports
Category Code: I96 SPARE NUMBER
Category Code: I97 SPARE NUMBER
Category Code: I98 SPARE NUMBER
Category Code: I99 SPARE NUMBER
Category Code: J71 Appraisal Report for Consultancy Service
Category Code: J72 Appraisal Report for EPC Contractor Work
Category Code: J73 Appraisal Report for Vendor/Supplier
Category Code: J91 Index/List
Category Code: J92 Procedures & Standards
Category Code: J93 Policy , Guidelines & Memo
Category Code: J94 Forms & Templates
Category Code: J95 Progress/Status Reports
Category Code: K01 Design Basis Reports
Category Code: K02 Design Verification Reports
Category Code: K03 Master Plan Document
Category Code: K04 Cadastal Map
Category Code: K08 Material Take Off UG
Category Code: K11 Design calculation for pile (including pile driven design)
| CV | OL1-2K11-0001 | CALCULATION NOTES FOR PILES |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-02-28; R2 IFD: 2019-04-01
[6 empty] | Revised Plan | R2 IFD: 2019-08-28
[6 empty] | Issue Actual | IFR: 2019-03-19; R2 IFR: 2019-03-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01092; R2 IFR: TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
Category Code: K12 Design calculation for paving
| CV | OL1-2K12-0001 | CALCULATION NOTES FOR ROAD AND PAVING THICKNESS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-30; R2 IFR: 2020-09-29
[6 empty] | Revised Plan | IFR: 2019-10-31; R2 IFR: 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K13 Design calculation for foundations
| CV | OL1-2K13-0001 | CALCULATION NOTE FOR FOUNDATION OF 10-H-1100 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-15; R2 IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02150; R2 IFR: TPSK-LSPA1-T-CV-02150
Return Date
Owner Cmmt*
| CV | OL1-2K13-0002 | CALCULATION NOTE FOR FOUNDATION OF 10-H-1200/1600 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-15; R2 IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02150; R2 IFR: TPSK-LSPA1-T-CV-02150
Return Date
Owner Cmmt*
| CV | OL1-2K13-0004 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5200 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-12; R2 IFR: 2019-02-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00843; R2 IFR: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0005 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5200 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-27; R2 IFR: 2019-02-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00943; R2 IFR: TPSK-LSPA1-T-CV-00943
[6 empty] | Return Date | IFR: 2019-03-28; R2 IFR: 2019-03-28
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0006 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5210 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01033; R2 IFR: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0008 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2140 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0010 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5150 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-12; R2 IFR: 2019-02-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00843; R2 IFR: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0011 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2160 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR
Rev. | bar: IFR to R2 IFR
Issue Plan
[6 empty] | Revised Plan | R2 IFR: 2019-01-28
[6 empty] | Issue Actual | R2 IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00732; R2 IFR: TPSK-LSPA1-T-CV-00732
[6 empty] | Return Date | IFR: 2019-03-27; R2 IFR: 2019-03-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0013 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2136 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0014 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2160 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0016 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2136 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-06; R2 IFR: 2019-03-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00992; R2 IFR: TPSK-LSPA1-T-CV-00992
[6 empty] | Return Date | IFR: 2019-03-28; R2 IFR: 2019-03-28
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0017 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2165A/D |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0018 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2166 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-07; R2 IFR: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01005; R2 IFR: TPSK-LSPA1-T-CV-01005
[6 empty] | Return Date | IFR: 2019-03-28; R2 IFR: 2019-03-28
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0019 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2145 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0020 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2146 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-12; R2 IFR: 2019-02-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00843; R2 IFR: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0021 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2026 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-12; R2 IFR: 2019-02-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00843; R2 IFR: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0022 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2048 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-07; R2 IFR: 2019-02-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00816; R2 IFR: TPSK-LSPA1-T-CV-00816
[6 empty] | Return Date | IFR: 2019-03-18; R2 IFR: 2019-03-18
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0023 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5102A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0024 | CALCULATION NOTE FOR FOUNDATION PUMPS 10-P-2026A/B, 10-P-2126A/B, 10-P-2046A/B, 10-P-5140A/B, 10-P-2146A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0025 | CALCULATION NOTE FOR FOUNDATION OF 10-P-2105A/B AND 10-P-2006A/B/C |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0026 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2105A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0027 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2009A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0028 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2008A/B/C |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0029 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2026A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0030 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2028A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0031 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2136A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0033 | CALCULATION NOTE FOR FOUNDATION OF ANALYZER HOUSE |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0034 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2440 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0036 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2300 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-11; R2 IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01857; R2 IFR: TPSK-LSPA1-T-CV-01857
[6 empty] | Return Date | IFR: 2019-08-16
Owner Cmmt* | bar: IFR
| CV | OL1-2K13-0037 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2330 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-12; R2 IFR: 2019-02-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00843; R2 IFR: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0038 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2410A/B/C |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01033; R2 IFR: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0039 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2435 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01033; R2 IFR: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0041 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2240 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01033; R2 IFR: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0042 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2245 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01033; R2 IFR: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0043 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2445 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01033; R2 IFR: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0044 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2455 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-11; R2 IFR: 2019-02-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00832; R2 IFR: TPSK-LSPA1-T-CV-00832
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0045 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2220 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01033; R2 IFR: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0046 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2210 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01168; R2 IFR: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0047 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2230 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01168; R2 IFR: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0048 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2405 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01168; R2 IFR: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0049 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2415 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0050 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2310 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-08; R2 IFR: 2019-02-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00827; R2 IFR: TPSK-LSPA1-T-CV-00827
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0052 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2316 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-01; R2 IFR: 2019-02-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00783; R2 IFR: TPSK-LSPA1-T-CV-00783
[6 empty] | Return Date | IFR: 2019-02-25; R2 IFR: 2019-02-25
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0054 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2330 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-01; R2 IFR: 2019-02-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00783; R2 IFR: TPSK-LSPA1-T-CV-00783
[6 empty] | Return Date | IFR: 2019-02-25; R2 IFR: 2019-02-25
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0055 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2411 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01168; R2 IFR: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0056 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-2910 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | R2 IFR: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02238
Return Date
Owner Cmmt*
| CV | OL1-2K13-0058 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2230A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01372; R2 IFR: TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | IFR: 2019-05-18; R2 IFR: 2019-05-18
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0059 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2412 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-12; R2 IFR: 2019-04-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01333; R2 IFR: TPSK-LSPA1-T-CV-01333
[6 empty] | Return Date | IFR: 2019-05-09; R2 IFR: 2019-05-09
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0060 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2413 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-18; R2 IFR: 2019-06-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01903; R2 IFR: TPSK-LSPA1-T-CV-01903
[6 empty] | Return Date | R2 IFR: 2019-08-16
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K13-0061 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2432 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0063 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2446 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01372; R2 IFR: TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0065 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2450 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-15; R2 IFR: 2019-04-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01348; R2 IFR: TPSK-LSPA1-T-CV-01348
[6 empty] | Return Date | IFR: 2019-04-23; R2 IFR: 2019-04-23
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0066 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2470 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0067 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2206 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-01; R2 IFR: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01207; R2 IFR: TPSK-LSPA1-T-CV-01207
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFR: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0068 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2210A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01372; R2 IFR: TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0069 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2220A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01372; R2 IFR: TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0070 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2240A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01372; R2 IFR: TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0071 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2305 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-08; R2 IFR: 2019-02-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00827; R2 IFR: TPSK-LSPA1-T-CV-00827
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0072 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2630 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-07; R2 IFR: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01005; R2 IFR: TPSK-LSPA1-T-CV-01005
[6 empty] | Return Date | IFR: 2019-03-28; R2 IFR: 2019-03-28
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0073 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2326 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0074 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2320A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | R2 IFR: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02410
Return Date
Owner Cmmt*
| CV | OL1-2K13-0075 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2310A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | R2 IFR: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02410
Return Date
Owner Cmmt*
| CV | OL1-2K13-0076 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2306A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0077 | CALCULATION NOTE FOR FOUNDATION OF ANALYZER HOUSE |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0078 | CALCULATION NOTE FOR FOUNDATION OF ANALYZER HOUSE |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0079 | CALCULATION NOTE FOR FOUNDATION FOR PUMPS 10-P-5112A/B, 10-P-2714A/B, 10-P-2710A/B, 10-P-2720A/B, 10-P-2721A/B, 10-P-2910 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0080 | CALCULATION NOTE FOR FOUNDATION FOR PUMPS 10-P-2724A/B, 10-P-2726A/B, 10-P-2750A/B, 10-P-2760A/B/C, 10-P-2705A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0081 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5100A/B/C |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0082 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2900/2902/2906 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0083 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2920 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0084 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-1920 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0085 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2350 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0087 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2048A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0088 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2580 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01168; R2 IFR: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0089 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2640 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-15; R2 IFR: 2019-03-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01071; R2 IFR: TPSK-LSPA1-T-CV-01071
Return Date
Owner Cmmt*
| CV | OL1-2K13-0090 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2570 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01168; R2 IFR: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0091 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2510, 10-D-2510 AND 10-E-2510 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01168; R2 IFR: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0093 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2520 AND 10-D-2520 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | R2 IFR: 2019-01-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00679; R2 IFR: TPSK-LSPA1-T-CV-00679
[6 empty] | Return Date | IFR: 2019-06-03; R2 IFR: 2019-06-03
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0094 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2480A |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01168; R2 IFR: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0096 | Calculation Note For Foundation Of 10-D-2420A-B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01661; R2 IFR: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0097 | Calculation Note For Foundation Of 10-E-1006 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01749; R2 IFR: TPSK-LSPA1-T-CV-01749
[6 empty] | Return Date | R2 IFR: 2019-06-28
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K13-0098 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2815 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | R2 IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00732; R2 IFR: TPSK-LSPA1-T-CV-00732
[6 empty] | Return Date | IFR: 2019-03-27; R2 IFR: 2019-03-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0099 | Calculation Note for Foundation of 10-D-2525 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-18; R2 IFR: 2019-06-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01903; R2 IFR: TPSK-LSPA1-T-CV-01903
[6 empty] | Return Date | IFR: 2019-08-16
Owner Cmmt* | bar: IFR
| CV | OL1-2K13-0100 | Calculation Note For Foundation Of 10-PIT-5606 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-12-30
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02238
Return Date
Owner Cmmt*
| CV | OL1-2K13-0101 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2645 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-07; R2 IFR: 2019-02-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00816; R2 IFR: TPSK-LSPA1-T-CV-00816
[6 empty] | Return Date | IFR: 2019-03-18; R2 IFR: 2019-03-18
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0102 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2555 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-19; R2 IFR: 2019-03-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01092; R2 IFR: TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0103 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2550 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-19; R2 IFR: 2019-03-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01092; R2 IFR: TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0104 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5628, 10-PIT-5628, P-10-5628A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0105 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2575 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-12; R2 IFR: 2019-02-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00843; R2 IFR: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0106 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2880 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-01; R2 IFR: 2019-07-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02030; R2 IFR: TPSK-LSPA1-T-CV-02030
Return Date
Owner Cmmt*
| CV | OL1-2K13-0107 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2870 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | R2 IFR: 2019-01-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00679; R2 IFR: TPSK-LSPA1-T-CV-00679
[6 empty] | Return Date | IFR: 2019-06-03; R2 IFR: 2019-06-03
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0108 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2860 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | R2 IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00732; R2 IFR: TPSK-LSPA1-T-CV-00732
[6 empty] | Return Date | IFR: 2019-03-27; R2 IFR: 2019-03-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0109 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2865 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-12; R2 IFR: 2019-02-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00843; R2 IFR: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0110 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5632 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0111 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2587 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-01; R2 IFR: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01207; R2 IFR: TPSK-LSPA1-T-CV-01207
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFR: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0113 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2305 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01372; R2 IFR: TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0115 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2576 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-07; R2 IFR: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01005; R2 IFR: TPSK-LSPA1-T-CV-01005
[6 empty] | Return Date | IFR: 2019-03-28; R2 IFR: 2019-03-28
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0116 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2645A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-14; R2 IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSL-LSPA1-T-CV-01059; R2 IFR: TPSL-LSPA1-T-CV-01059
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0117 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2502 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | R2 IFR: 2019-01-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00679; R2 IFR: TPSK-LSPA1-T-CV-00679
[6 empty] | Return Date | IFR: 2019-06-03; R2 IFR: 2019-06-03
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0118 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2515 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-06; R2 IFR: 2019-03-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00992; R2 IFR: TPSK-LSPA1-T-CV-00992
[6 empty] | Return Date | IFR: 2019-03-28; R2 IFR: 2019-03-28
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0119 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2546 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-12; R2 IFR: 2019-02-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00843; R2 IFR: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0120 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2548 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-12; R2 IFR: 2019-02-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00843; R2 IFR: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0121 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2545 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-01-30; R2 IFR: 2019-01-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00762; R2 IFR: TPSK-LSPA1-T-CV-00762
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0123 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2807 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-12; R2 IFR: 2019-02-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00843; R2 IFR: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0124 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2809 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-12; R2 IFR: 2019-02-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00843; R2 IFR: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0125 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2857 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-07; R2 IFR: 2019-02-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00816; R2 IFR: TPSK-LSPA1-T-CV-00816
[6 empty] | Return Date | IFR: 2019-03-18; R2 IFR: 2019-03-18
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0126 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2858 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-12; R2 IFR: 2019-02-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00843; R2 IFR: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0127 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2856 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-12; R2 IFR: 2019-02-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00843; R2 IFR: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0128 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2855 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-21; R2 IFR: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01126; R2 IFR: TPSK-LSPA1-T-CV-01126
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0129 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2853 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-19; R2 IFR: 2019-02-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00878; R2 IFR: TPSK-LSPA1-T-CV-00878
[6 empty] | Return Date | IFR: 2019-03-11; R2 IFR: 2019-03-11
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0130 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2852 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01033; R2 IFR: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0132 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2582 |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IFC
Rev. | bar: IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IBD: 2020-06-15
[6 empty] | Revised Plan | R2 IBD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-12; R2 IFR: 2019-02-12; R2 IFD: 2019-02-21; R2 IFD: 2019-02-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00843; R2 IFR: TPSK-LSPA1-T-CV-00843; R2 IFD: TPSK-LSPA1-T-CV-00904; R2 IFD: TPSK-LSPA1-T-CV-00904
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27; R2 IFD: 2019-03-12; R2 IFD: 2019-03-12
Owner Cmmt* | bar: IFR to R2 IFD
| CV | OL1-2K13-0133 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2504 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-01-30; R2 IFR: 2019-01-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00762; R2 IFR: TPSK-LSPA1-T-CV-00762
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0134 | CALCULATION NOTE FOR FOUNDATION OF PSA PACKAGE 10-PK-2560, 10-D-2560A/F, 10-D-2565 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0135 | CALCULATION NOTE FOR PUMPS 10-P-2570A/B, 10-P-2575A/B, 10-P-2586A/B, 10-P-2647, 10-P-2646A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0136 | CALCULATION NOTE FOR PUMPS 10-P-2802A/B, 10-P-2805A/B, 10-P-2815, 10-P-2855A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0137 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2930, 10-D-2930 AND 10-P-2930 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0138 | CALCULATION NOTE FOR FOUNDATION OF 10-R-2700A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01661; R2 IFR: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0140 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2620 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01033; R2 IFR: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0141 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2666 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01661; R2 IFR: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0143 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2660 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-24; R2 IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01469; R2 IFR: TPSK-LSPA1-T-CV-01469
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0147 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2630 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01372; R2 IFR: TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0148 | CALCULATION NOTE FOR FOUNDATION OF 10-R-2470A/B/C |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01661; R2 IFR: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0149 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2610 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-11; R2 IFR: 2019-02-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00832; R2 IFR: TPSK-LSPA1-T-CV-00832
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0150 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2600A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-11; R2 IFR: 2019-02-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00832; R2 IFR: TPSK-LSPA1-T-CV-00832
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0151 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2460 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01168; R2 IFR: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0152 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2440 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01168; R2 IFR: TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0153 | CALCULATION NOTE FOR FOUNDATION OF 10-D-1000 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01372; R2 IFR: TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0154 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2635 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-15; R2 IFR: 2019-04-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01348; R2 IFR: TPSK-LSPA1-T-CV-01348
[6 empty] | Return Date | IFR: 2019-04-23; R2 IFR: 2019-04-23
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0155 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2636 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-07; R2 IFR: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01005; R2 IFR: TPSK-LSPA1-T-CV-01005
[6 empty] | Return Date | IFR: 2019-03-28; R2 IFR: 2019-03-28
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0156 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2472 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0157 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2474 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01372; R2 IFR: TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0158 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2465 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01372; R2 IFR: TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0159 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2460 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01372; R2 IFR: TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0160 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2440/2441/2442 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-12; R2 IFR: 2019-04-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01333; R2 IFR: TPSK-LSPA1-T-CV-01333
[6 empty] | Return Date | IFR: 2019-05-09; R2 IFR: 2019-05-09
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0161 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1020 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-01; R2 IFR: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01207; R2 IFR: TPSK-LSPA1-T-CV-01207
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFR: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0162 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1015 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01033; R2 IFR: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0163 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1001A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01033; R2 IFR: TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0164 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1000 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-15; R2 IFR: 2019-04-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01348; R2 IFR: TPSK-LSPA1-T-CV-01348
[6 empty] | Return Date | IFR: 2019-04-23; R2 IFR: 2019-04-23
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0165 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1005 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-15; R2 IFR: 2019-04-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01348; R2 IFR: TPSK-LSPA1-T-CV-01348
[6 empty] | Return Date | IFR: 2019-04-23; R2 IFR: 2019-04-23
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0166 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2912 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0167 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2922 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0168 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2940 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0169 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2705 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-30; R2 IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01521; R2 IFR: TPSK-LSPA1-T-CV-01521
[6 empty] | Return Date | IFR: 2019-05-27; R2 IFR: 2019-05-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0170 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2706 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0171 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2735 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-18; R2 IFR: 2019-04-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01415; R2 IFR: TPSK-LSPA1-T-CV-01415
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0172 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2724 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0173 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2730 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0175 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2755 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01661; R2 IFR: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0176 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2725A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0177 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2726 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0179 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2702 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-27; R2 IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02003; R2 IFR: TPSK-LSPA1-T-CV-02003
Return Date
Owner Cmmt*
| CV | OL1-2K13-0180 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2701 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-23; R2 IFR: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01456; R2 IFR: TPSK-LSPA1-T-CV-01456
[6 empty] | Return Date | IFR: 2019-05-27; R2 IFR: 2019-05-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0181 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2706 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01661; R2 IFR: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0182 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2008A/B/C |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-12; R2 IFR: 2019-02-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00843; R2 IFR: TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFR: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0186 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2724 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0187 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2714 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0188 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2882 AND 10-D-2882 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-01; R2 IFR: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01207; R2 IFR: TPSK-LSPA1-T-CV-01207
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFR: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0190 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2715A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0191 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2100A/B/C/D/E/F |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | R2 IFR: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02382
Return Date
Owner Cmmt*
| CV | OL1-2K13-0192 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2705 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-30; R2 IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01521; R2 IFR: TPSK-LSPA1-T-CV-01521
[6 empty] | Return Date | IFR: 2019-05-27; R2 IFR: 2019-05-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0193 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-2320 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0194 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1050 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-01; R2 IFR: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01207; R2 IFR: TPSK-LSPA1-T-CV-01207
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFR: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0195 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-1910 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-24; R2 IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01469; R2 IFR: TPSK-LSPA1-T-CV-01469
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0196 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5910 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0197 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5914 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0198 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5912 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0199 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2914 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0200 | CALCULATION NOTE FOR FOUNDATION OF IGNITION SYSTEM |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0201 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION FOR 10-C-3070 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0202 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-3900 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | R2 IFR: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02194
Return Date
Owner Cmmt*
| CV | OL1-2K13-0203 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3000 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-18; R2 IFR: 2019-06-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01901; R2 IFR: TPSK-LSPA1-T-CV-01901
Return Date
Owner Cmmt*
| CV | OL1-2K13-0204 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3040 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0205 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3020 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0206 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3010 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0207 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3030 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-18; R2 IFR: 2019-06-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01901; R2 IFR: TPSK-LSPA1-T-CV-01901
Return Date
Owner Cmmt*
| CV | OL1-2K13-0208 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3050 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-18; R2 IFR: 2019-06-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01901; R2 IFR: TPSK-LSPA1-T-CV-01901
Return Date
Owner Cmmt*
| CV | OL1-2K13-0209 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3060 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0210 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3080 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-18; R2 IFR: 2019-06-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01901; R2 IFR: TPSK-LSPA1-T-CV-01901
Return Date
Owner Cmmt*
| CV | OL1-2K13-0211 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3090 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0212 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3070 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-03; R2 IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02064; R2 IFR: TPSK-LSPA1-T-CV-02064
Return Date
Owner Cmmt*
| CV | OL1-2K13-0213 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3100, 10-A-3100 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0214 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3126 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0215 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3908 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | R2 IFR: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02358
Return Date
Owner Cmmt*
| CV | OL1-2K13-0216 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3902 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | R2 IFR: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02358
Return Date
Owner Cmmt*
| CV | OL1-2K13-0217 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3904 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | R2 IFR: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02358
Return Date
Owner Cmmt*
| CV | OL1-2K13-0218 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3906 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | R2 IFR: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02358
Return Date
Owner Cmmt*
| CV | OL1-2K13-0219 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3180 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-03; R2 IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02064; R2 IFR: TPSK-LSPA1-T-CV-02064
Return Date
Owner Cmmt*
| CV | OL1-2K13-0220 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3110 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0221 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3004A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0222 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3014A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0223 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3015 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0224 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3084 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0225 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3085A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0226 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3095 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0227 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3096 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0228 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3098 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0229 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3055A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0230 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3045A/B/C/D |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0231 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3044 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0232 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2585 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-01; R2 IFR: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01207; R2 IFR: TPSK-LSPA1-T-CV-01207
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFR: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0233 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3150 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0234 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3160 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0235 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3005 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0236 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3070 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0237 | CALCULATION FOR FOUNDATION OF METERING STATION |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0238 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2765 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-30; R2 IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01521; R2 IFR: TPSK-LSPA1-T-CV-01521
[6 empty] | Return Date | IFR: 2019-05-27; R2 IFR: 2019-05-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0239 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5560 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0240 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5560 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0241 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5394 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0242 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5398 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0243 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5355 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0244 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5392 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0245 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5390 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0246 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5396 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0247 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5550 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | R2 IFR: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01731
[6 empty] | Return Date | IFR: 2019-07-17
Owner Cmmt* | bar: IFR
| CV | OL1-2K13-0248 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5500 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0249 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5510 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-13; R2 IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01647; R2 IFR: TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | R2 IFR: 2019-07-16
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K13-0250 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5513 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-13; R2 IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01647; R2 IFR: TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | R2 IFR: 2019-07-16
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K13-0251 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5515 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-13; R2 IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01647; R2 IFR: TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | R2 IFR: 2019-07-16
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K13-0252 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5520 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-13; R2 IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01647; R2 IFR: TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | R2 IFR: 2019-07-16
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K13-0253 | CALCULATION NOTE FOR FOUNDATION OF 10-C-5520A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0254 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5510 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-21; R2 IFR: 2019-05-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01702; R2 IFR: TPSK-LSPA1-T-CV-01702
[6 empty] | Return Date | IFR: 2019-06-20; R2 IFR: 2019-06-20
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0255 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5513 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-21; R2 IFR: 2019-05-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01702; R2 IFR: TPSK-LSPA1-T-CV-01702
[6 empty] | Return Date | IFR: 2019-06-20; R2 IFR: 2019-06-20
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0256 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5640 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | R2 IFR: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01731
[6 empty] | Return Date | IFR: 2019-07-17
Owner Cmmt* | bar: IFR
| CV | OL1-2K13-0257 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5675A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0258 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5676 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0259 | CALCULATION NOTE FOR FOUNDATION OF 10-TX/C-2550 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | R2 IFR: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02202
Return Date
Owner Cmmt*
| CV | OL1-2K13-0260 | CALCULATION NOTE FOR FOUNDATION OF 10-C-5650A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0261 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-C-2800, 10-E-2800 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0262 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-C-2850, 10-E-2850 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0263 | CALCULATION NOTE FOR FOUNDATION OF 10-C-2200, 10-E-2200 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0264 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5627, 10-PIT-5627, P-10-5627A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0265 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5397 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0266 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5692 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0267 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5693 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0268 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5694 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0269 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5671 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0270 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5672 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0271 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5697 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0272 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5690 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0273 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5691 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0274 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5670 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0275 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5670A/B, 10-P-5671A/B, 10-P-5644A/B, 10-P-5645A/B, 10-P-5646A/B, 10-P-5647A/B, 10-P-5675 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0276 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5646 AND 10-X-5646 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0277 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5644 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0278 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5644 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0279 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5653 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0280 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5650 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0281 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5110 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-18; R2 IFR: 2019-06-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01901; R2 IFR: TPSK-LSPA1-T-CV-01901
Return Date
Owner Cmmt*
| CV | OL1-2K13-0282 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5120 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-18; R2 IFR: 2019-06-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01901; R2 IFR: TPSK-LSPA1-T-CV-01901
Return Date
Owner Cmmt*
| CV | OL1-2K13-0283 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5130 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0284 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5552 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-31; R2 IFR: 2019-06-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01731; R2 IFR: TPSK-LSPA1-T-CV-01731
[6 empty] | Return Date | R2 IFR: 2019-07-17
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K13-0285 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5565 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | R2 IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01837; R2 IFR: TPSK-LSPA1-T-CV-01837
[6 empty] | Return Date | IFR: 2019-08-08
Owner Cmmt* | bar: IFR
| CV | OL1-2K13-0286 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-1950, 10-C-1950A/B, 10-E-1951A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0287 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5140 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | R2 IFR: 2019-01-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00679; R2 IFR: TPSK-LSPA1-T-CV-00679
[6 empty] | Return Date | IFR: 2019-06-03; R2 IFR: 2019-06-03
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0288 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5400 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-30; R2 IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01521; R2 IFR: TPSK-LSPA1-T-CV-01521
[6 empty] | Return Date | IFR: 2019-05-27; R2 IFR: 2019-05-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0289 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5114 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-23; R2 IFR: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01456; R2 IFR: TPSK-LSPA1-T-CV-01456
[6 empty] | Return Date | IFR: 2019-05-27; R2 IFR: 2019-05-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0290 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5112, 10-E-5112 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR
Rev. | bar: IFR to R2 IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-23; R2 IFR: 2019-04-24
[6 empty] | Issue Actual | IFR: 2019-04-23; R2 IFR: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01456; R2 IFR: TPSK-LSPA1-T-CV-01456
[6 empty] | Return Date | IFR: 2019-05-27; R2 IFR: 2019-05-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0291 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5520 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0292 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5113 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01661; R2 IFR: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0294 | CALCULATION NOTE FOR FOUNDATION OF 10-F-5610 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0295 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5552 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | R2 IFR: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01731
[6 empty] | Return Date | IFR: 2019-07-17
Owner Cmmt* | bar: IFR
| CV | OL1-2K13-0296 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5110 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0297 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5191 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0298 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5192 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0299 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5115, 10-F-5115A/B/C |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0300 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5125, 10-D-5125A/B, 10-F-5125A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0301 | CALCULATION NOTE FOR FOUNDATION OF 10-P-2106A/B/C |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0302 | CALCULATION NOTE FOR SKID 10-P-2201A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0303 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5360A/B/C |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0304 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5670 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0305 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5695 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0306 | CALCULATION NOTE FOR PUMPS 10-P-5900A/B, 10-P-5950A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0307 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5350 A/B/C/D/E/F/G/H |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0308 | CALCULATION NOTE FOR PUMPS 10-P-3080A/B, 10-P-3030A/B, 10-P-3000A/B, 10-P-3020A/B, 10-P-3061A/B, 10-P-3060A/B, 10-P-3062A/B, 10- |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0309 | CALCULATION NOTE FOR PUMPS 10-P-3096A/B, 10-P-3086A/B, 10-P-3036A/B, 10-P-3016A/B, 10-P-3900, 10-P-3160A/B, 10-P-3076A/B, 10-P-3 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0310 | CALCULATION NOTE FOR PUMPS 10-P-3046A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0311 | CALCULATION NOTE FOR PUMPS 10-P-3045A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0312 | CALCULATION NOTE FOR PUMPS 10-P-3026A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0313 | CALCULATION NOTE FOR PUMPS 10-P-3056A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0314 | CALCULATION NOTE FOR FOUNDATION OF 10-R-2620A |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01372; R2 IFR: TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0315 | CALCULATION NOTE FOR FOUNDATION PUMPS FOR 10-P-2450A/B, 10-P-2455A/B, 10-P-2620A/B, 10-P-2666A/B, 10-P-2660A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0316 | CALCULATION NOTE FOR FOUNDATION PUMPS FOR 10-P-2630A/B, 10-P-2310A/B, 10-P-2316A/B, 10-P-2326A/B, 10-P-2320A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0317 | CALCULATION NOTE FOR PUMPS 10-P-2302A/B, 10-P-2415A/B, 10-P-2445A/B, 10-P-2304, 10-P-2306A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0318 | CALCULATION NOTE FOR PUMPS 10-P-2200A/B, 10-P-2220A/B, 10-P-2210A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0319 | CALCULATION NOTE FOR PUMPS 10-P-5620A/B/C,10-P-5621,10-P-5650A/B, 10-P-5651A/B, 10-P-5640A/B, 10-P-5641 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0320 | CALCULATION NOTE FOR PUMPS 10-P-5550A/B, 10-P-5552 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0321 | CALCULATION NOTE FOR PUMPS 10-P-5110A/B, 10-P-5120A/B, 10-P-5130A/B, 10-P-5500A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0322 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2000 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-19; R2 IFR: 2019-03-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01092; R2 IFR: TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0323 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2020 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-19; R2 IFR: 2019-03-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01092; R2 IFR: TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0324 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2100 |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IFC
Rev. | bar: IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IBD: 2020-06-15
[6 empty] | Revised Plan | R2 IBD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-21; R2 IFR: 2019-02-22; R2 IFD: 2019-03-19; R2 IFD: 2019-03-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00904; R2 IFR: TPSK-LSPA1-T-CV-00904; R2 IFD: TPSK-LSPA1-T-CV-01092; R2 IFD: TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | IFR: 2019-03-12; R2 IFR: 2019-03-12; R2 IFD: 2019-04-12; R2 IFD: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFD
| CV | OL1-2K13-0325 | CALCULATION NOTE FOR CONCRETE STRUCTURE OF 10-T-2040 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-01; R2 IFR: 2019-07-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02030; R2 IFR: TPSK-LSPA1-T-CV-02030
Return Date
Owner Cmmt*
| CV | OL1-2K13-0326 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5605 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0327 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5610 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFD: 2020-01-31
[6 empty] | Revised Plan | R2 IFD: 2020-01-31
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02118; R2 IFR: TPSK-LSPA1-T-CV-02118
Return Date
Owner Cmmt*
| CV | OL1-2K13-0328 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2390 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | R2 IFR: 2020-01-31
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02312
Return Date
Owner Cmmt*
| CV | OL1-2K13-0329 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5603 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFD: 2020-01-31
[6 empty] | Revised Plan | R2 IFD: 2020-01-31
[6 empty] | Issue Actual | IFR: 2019-06-27; R2 IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02003; R2 IFR: TPSK-LSPA1-T-CV-02003
Return Date
Owner Cmmt*
| CV | OL1-2K13-0330 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5604 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFD: 2020-01-31
[6 empty] | Revised Plan | R2 IFD: 2020-01-31
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02118; R2 IFR: TPSK-LSPA1-T-CV-02118
Return Date
Owner Cmmt*
| CV | OL1-2K13-0331 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2090 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFD: 2020-01-31
[6 empty] | Revised Plan | R2 IFD: 2020-01-31
[6 empty] | Issue Actual | IFR: 2019-04-10; R2 IFR: 2019-04-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01303; R2 IFR: TPSK-LSPA1-T-CV-01303
[6 empty] | Return Date | IFR: 2019-05-09; R2 IFR: 2019-05-09
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0332 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2190 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFD: 2020-01-31
[6 empty] | Revised Plan | R2 IFD: 2020-01-31
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02118; R2 IFR: TPSK-LSPA1-T-CV-02118
Return Date
Owner Cmmt*
| CV | OL1-2K13-0333 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2790 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | R2 IFR: 2020-01-31
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02273
Return Date
Owner Cmmt*
| CV | OL1-2K13-0335 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-3190 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0336 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5601 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0337 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5600 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | R2 IFR: 2020-01-31
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02273
Return Date
Owner Cmmt*
| CV | OL1-2K13-0338 | CALCULATION OF BASIN FOR COOLING TOWER 10-PIT-5350 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-12; R2 IFR: 2020-01-02; R2 IFD: 2020-01-23; R2 IFD: 2020-03-08
[6 empty] | Revised Plan | IFR: 2019-12-12; R2 IFR: 2020-01-02; R2 IFD: 2020-01-23; R2 IFD: 2020-03-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0339 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5370 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0340 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5602 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFD: 2020-01-31
[6 empty] | Revised Plan | R2 IFD: 2020-01-31
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02118; R2 IFR: TPSK-LSPA1-T-CV-02118
Return Date
Owner Cmmt*
| CV | OL1-2K13-0341 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2392 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFD: 2020-01-31
[6 empty] | Revised Plan | R2 IFD: 2020-01-31
[6 empty] | Issue Actual | IFR: 2019-06-24; R2 IFR: 2019-06-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01961; R2 IFR: TPSK-LSPA1-T-CV-01961
Return Date
Owner Cmmt*
| CV | OL1-2K13-0343 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5615 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0344 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5656 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0345 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5620A/B/C |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0346 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5630 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0347 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5633 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0348 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5631 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0349 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5671 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0350 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5650A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0351 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5655 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0352 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5696 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0353 | CALCULATION NOTE FOR FOUNDATION OF CLARIFIER 10-TK-5651A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0356 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0357 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0358 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0359 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0360 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0361 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0362 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0363 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0364 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0365 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0366 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-5900 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0367 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-5950 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0368 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-2320 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0369 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-2910 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0370 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-3900 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0371 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-PK-1910 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0372 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS FLARE UNIT |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0373 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0374 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0375 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0376 | CALCULATION FOR FOUNDATION OF SUPPORTS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0377 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0378 | CALCULATION NOTE FOR 10-SLW-5T02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0379 | CALCULATION NOTE FOR 10-SLW-5T01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0380 | CALCULATION NOTE FOR 10-SLW-0C01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0381 | CALCULATION NOTE FOR 10-SLW-5W01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0382 | CALCULATION NOTE FOR 10-SLW-5F01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0383 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0384 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0385 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0386 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0387 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0388 | CALCULATION FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0389 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0391 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0393 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5900 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-13; R2 IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01647; R2 IFR: TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | R2 IFR: 2019-07-16
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K13-0394 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5950 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0396 | CALCULATION NOTE FOR SKID 10-P-2801A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0398 | CALCULATION FOR BASIN 10-PIT-5642 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
[6 empty] | Revised Plan | IFR: 2019-12-30; R2 IFR: 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0399 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2904 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0400 | Calculation Note For Foundation Of 10-TK-2300 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02238
Return Date
Owner Cmmt*
| CV | OL1-2K13-0401 | Calculation Note For Foundation Of 10-E-2441 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-12; R2 IFR: 2019-04-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01333; R2 IFR: TPSK-LSPA1-T-CV-01333
[6 empty] | Return Date | IFR: 2019-05-09; R2 IFR: 2019-05-09
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0402 | Calculation Note For Foundation Of 10-E-2442 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01372; R2 IFR: TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0403 | Calculation Note For Foundation Of 10-E-2405 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01661; R2 IFR: TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0404 | Calculation Note For Foundation Of 10-D-1912 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-24; R2 IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01469; R2 IFR: TPSK-LSPA1-T-CV-01469
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K13-0405 | Calculation Note For Foundation Of 10-D-2322 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | R2 IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01857; R2 IFR: TPSK-LSPA1-T-CV-01857
[6 empty] | Return Date | IFR: 2019-08-16
Owner Cmmt* | bar: IFR
Category Code: K14 Design calculation for concrete structure (including reinforcement detail)
| CV | OL1-2K14 -0043 | Calculation Note For Foundation And Elevation Of 10-STR-0P01 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-02-12
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02238
Return Date
Owner Cmmt*
| CV | OL1-2K14-0001 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-0P01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18
[6 empty] | Revised Plan | R2 IFD: 2019-11-18
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01749; R2 IFR: TPSK-LSPA1-T-CV-01749
[6 empty] | Return Date | R2 IFR: 2019-07-11
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K14-0002 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-0P01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0003 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-0P02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18
[6 empty] | Revised Plan | R2 IFD: 2019-11-18
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02121; R2 IFR: TPSK-LSPA1-T-CV-02121
Return Date
Owner Cmmt*
| CV | OL1-2K14-0004 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-0P02 |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02121; R2 IFR: TPSK-LSPA1-T-CV-02121
Return Date
Owner Cmmt*
| CV | OL1-2K14-0005 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-3A01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0006 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-3A01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0007 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-5U01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0008 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-5U01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0009 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2D01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0010 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-2D01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0011 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2E01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | R2 IFR: 2019-11-18
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02273
Return Date
Owner Cmmt*
| CV | OL1-2K14-0012 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-2E01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02303
Return Date
Owner Cmmt*
| CV | OL1-2K14-0013 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2A01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | R2 IFR: 2019-11-18
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02382
Return Date
Owner Cmmt*
| CV | OL1-2K14-0014 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-2A01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02382
Return Date
Owner Cmmt*
| CV | OL1-2K14-0015 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0016 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-2B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0017 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2C01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0018 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-2C01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | R2 IFR: 2020-05-04
[6 empty] | Issue Actual | IFR: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02425
Return Date
Owner Cmmt*
| CV | OL1-2K14-0019 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-5T01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0020 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-0P03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | R2 IFR: 2019-11-18
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02273
Return Date
Owner Cmmt*
| CV | OL1-2K14-0021 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-5F01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0022 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-5F01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0023 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2E01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0024 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0025 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | R2 IFR: 2020-04-08
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02303
Return Date
Owner Cmmt*
| CV | OL1-2K14-0026 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0027 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D04 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0028 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A06 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0029 | CALCULATION NOTE FOR FOUNDATION AND ELEVATIONOF 10-STR-3A03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0030 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A05 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0031 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A04 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0032 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0033 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0034 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-3A01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0035 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-5T01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0036 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-5T02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0037 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-5U01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0038 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0039 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E02, 10-D-2420A/B AND 10-E-2430 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0040 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0041 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E04 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0042 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D05 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0043 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-0P01 |  | Class 2 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0044 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2A01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | R2 IFR: 2020-04-08
[6 empty] | Issue Actual | IFR: 2019-07-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02202
Return Date
Owner Cmmt*
| CV | OL1-2K14-0045 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2A02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0046 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2A03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0047 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0048 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0049 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0050 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B04 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0051 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B05 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0052 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B06 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0053 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2D01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFD: 2020-04-08
[6 empty] | Revised Plan | R2 IFD: 2020-04-08
[6 empty] | Issue Actual | IFR: 2019-06-11; R2 IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01857; R2 IFR: TPSK-LSPA1-T-CV-01857
[6 empty] | Return Date | IFR: 2019-08-16
Owner Cmmt* | bar: IFR
| CV | OL1-2K14-0054 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2D02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0055 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0056 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0057 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0058 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C04 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0059 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C05 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0060 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0061 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-1B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0062 | CALCULATION NOTE FOR FOUNDATION OF WASTE STORAGE BUILDING |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0063 | CALCULATION NOTE FOR FOUNDATION OF LUBRIFICATION OIL & GREASE STORAGE |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0064 | CALCULATION NOTE FOR FOUNDATION OF GAS CYLINDER STORAGE |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0065 | CALCULATION NOTE FOR FOUNDATION OF TOOL ROOM OPERATION |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0066 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-0P03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02273
Return Date
Owner Cmmt*
| CV | OL1-2K14-0067 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2B02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0068 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-2B02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0069 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-2C02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0070 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-5T03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0071 | CALCULATION NOTE FOR FOUNDATION OF STORAGE SHELTER FOR CHENICALS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0073 | CALCULATION NOTE FOR FOUNDATION OF 10-STR-1B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0169 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2C02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | R2 IFR: 2019-11-18
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02331
Return Date
Owner Cmmt*
Category Code: K15 Design calculation for steel structure (including connection joint)
| CV | OL1-2K15-0001 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-0P01 |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-03-15; R2 IFD: 2020-04-15; R2 IFD: 2020-05-16; R2 IBD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-04-15; R2 IFD: 2020-05-16; R2 IBD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01749; R2 IFR: TPSK-LSPA1-T-CV-01749
[6 empty] | Return Date | R2 IFR: 2019-07-11
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K15-0002 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-0P02 |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-03-15; R2 IFD: 2020-04-15; R2 IFD: 2020-05-16; R2 IBD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-04-15; R2 IFD: 2020-05-16; R2 IBD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02121; R2 IFR: TPSK-LSPA1-T-CV-02121
Return Date
Owner Cmmt*
| CV | OL1-2K15-0003 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-3A01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0004 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-5U01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0005 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2D01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0006 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2E01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0007 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2A01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0008 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0009 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2C01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0010 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-5T01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0011 | CALCULATION NOTES FOR STEEL 10-PRK-5F01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0012 | CALCULATION NOTE FOR STEEL OF 10-SHT-2E01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0013 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0014 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0015 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0016 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E04 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0017 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D05 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0018 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0019 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0020 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0021 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B04 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0022 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B05 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0023 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B06 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0024 | CALCULATION NOTE FOR STEEL STRUCTURE 10-SHT-2D01 |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFD: 2020-05-14; R2 IFD: 2020-07-21; R2 IBD: 2020-09-04
[6 empty] | Revised Plan | R2 IFD: 2020-05-14; R2 IFD: 2020-07-21; R2 IBD: 2020-09-04
[6 empty] | Issue Actual | IFR: 2019-06-06; R2 IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01815; R2 IFR: TPSK-LSPA1-T-CV-01815
[6 empty] | Return Date | R2 IFR: 2019-08-06
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K15-0025 | CALCULATION NOTE FOR STEEL STRUCTURE 10-SHT-2D02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02303
Return Date
Owner Cmmt*
| CV | OL1-2K15-0026 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0027 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0028 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0029 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C04 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0030 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C05 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0032 | CALCULATION NOTE FOR STEEL STRUCTURE 10-SHT-1B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0033 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-0P01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0034 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2A01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Issue Actual | IFR: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02238
Return Date
Owner Cmmt*
| CV | OL1-2K15-0035 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2A02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0036 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2A03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0037 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0038 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0039 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0040 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D04 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0041 | CALCULATION NOTE FOR STEEL FOR WASTE STORAGE BUILDING |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0042 | CALCULATION NOTE FOR STEEL FOR LUBRIFICATION OIL & GREASE STORAGE |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0043 | CALCULATION NOTE FOR STEEL FOR GAS CYLINDER STORAGE |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0044 | CALCULATION NOTE FOR STEEL FOR TOOL ROOM OPERATION |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0045 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-0P03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02273
Return Date
Owner Cmmt*
| CV | OL1-2K15-0046 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A06 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0047 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0048 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A05 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0049 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A04 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0050 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0051 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0052 | CALCULATION FOR STEEL STRUCTURE 10-SHT-3A01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0053 | CALCULATION FOR STEEL STRUCTURE 10-SHT-5T01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0054 | CALCULATION FOR STEEL STRUCTURE 10-SHT-5T02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0055 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-5U01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0056 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2B02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0057 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2C02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-03-15; R2 IFR: 2020-04-15; R2 IFD: 2020-05-16; R2 IFD: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0058 | CALCULATION NOTE FOR STEEL FOR STORAGE SHELTER FOR CHENICALS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0059 | CALCULATION FOR STEEL STRUCTURE 10-SHT-5T03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0060 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-1B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
[6 empty] | Revised Plan | IFR: 2020-04-13; R2 IFR: 2020-05-14; R2 IFD: 2020-07-21; R2 IFD: 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0065 | Calculation Note For Steel Structure Of 10-T-2040 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-02-18; R2 IFD: 2019-09-16
[6 empty] | Revised Plan | R2 IFD: 2019-09-16
[6 empty] | Issue Actual | IFR: 2019-07-01; R2 IFR: 2019-07-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02030; R2 IFR: TPSK-LSPA1-T-CV-02030
Return Date
Owner Cmmt*
| CV | OL1-2K15-0094 | Calculation For Steel Platform For 10-PIT-2190 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-25
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02312
Return Date
Owner Cmmt*
| CV | OL1-2K15-0095 | Calculation For Steel Platform For 10-PIT-2392 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-25
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02312
Return Date
Owner Cmmt*
| CV | OL1-2K15-0108 | Calculation Note for Steel Structure 10-STR-2B03 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-04-13
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02425
Return Date
Owner Cmmt*
Category Code: K16 Design calculation for all drainage systems (including roof gutter, down spout, and grating cover)
| CV | OL1-2K16-0001 | UNDERGROUND CALCULATION NOTES |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IDD
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-06-18; R2 IFD: 2019-12-20
[6 empty] | Revised Plan | R2 IFD: 2019-12-20
[6 empty] | Issue Actual | IFR: 2019-04-03; R2 IFR: 2019-04-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01239; R2 IFR: TPSK-LSPA1-T-CV-01239
[6 empty] | Return Date | IFR: 2019-06-03; R2 IFR: 2019-06-03
Owner Cmmt* | bar: IFR to R2 IFR
Category Code: K17 Design calculation for all blast material i.e. door,wall
Category Code: K20 Standard drawing for civil work
| CV | OL1-2K20-0001 | CONSTR.STDS.FOR CONCRETE WORKS |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC | IFC | IFC
[6 empty] | Rev. | A | A | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | IFR: 2018-09-25; R2 IFD: 2019-01-20
Revised Plan
[6 empty] | Issue Actual | 2018-09-25 | 2018-09-27 | 2019-03-06 | 2019-03-07 | 2019-07-15 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00088 | TPSK-LSPA1-T-CV-00088 | TPSK-LSPA1-T-CV-00997 | TPSK-LSPA1-T-CV-00997 | TPSK-LSPA1-T-CV-02136 | TPSK-LSPA1-T-CV-02136
[6 empty] | Return Date | IFR: 2018-11-02; R2 IFR: 2018-11-02; R2 IFD: 2019-03-28; R2 IFD: 2019-03-28
Owner Cmmt* | bar: IFR to R2 IFD
Category Code: K21 Standard drawing for steel structure work
| CV | OL1-2K21-0001 | CONSTR.STD.STEEL STRUCTURES |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC | IFC | IFC
[6 empty] | Rev. | A | A | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | IFR: 2018-09-25; R2 IFD: 2019-01-31
Revised Plan
[6 empty] | Issue Actual | 2018-09-25 | 2018-09-27 | 2019-03-06 | 2019-03-07 | 2019-07-03 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00088 | TPSK-LSPA1-T-CV-00088 | TPSK-LSPA1-T-CV-00996 | TPSK-LSPA1-T-CV-00996 | TPSK-LSPA1-T-CV-02051 | TPSK-LSPA1-T-CV-02051
[6 empty] | Return Date | IFR: 2018-11-02; R2 IFR: 2018-11-02; R2 IFD: 2019-03-31; R2 IFD: 2019-03-31
Owner Cmmt* | bar: IFR to R2 IFD
Category Code: K22 Standard drawing for architecture work
Category Code: K23 Land Developmemt Drawing
| CV | OL1-2K23-1511 | USC 36M Recycle Furnace Steel Radiant Floor and Radiant Arch Plans |  | Class 2 | Purpose** | IFR: IFR
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K25 Plant Layouts
| CV | OL1-2K25-0001 | KEY PLAN FOR INSTALLATION DWGS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IDD
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-08-01; R2 IFD: 2019-10-30
[6 empty] | Revised Plan | R2 IFD: 2019-10-30
[6 empty] | Issue Actual | IFR: 2019-04-08; R2 IFR: 2019-04-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01271; R2 IFR: TPSK-LSPA1-T-CV-01271
[6 empty] | Return Date | IFR: 2019-05-07; R2 IFR: 2019-05-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K25-0002 | KEY PLAN FOR STRUCTURES |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IDD
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-05-06; R2 IFD: 2019-08-01
[6 empty] | Revised Plan | R2 IFD: 2019-09-13
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01171; R2 IFR: TPSK-LSPA1-T-CV-01171
[6 empty] | Return Date | IFR: 2019-06-03; R2 IFR: 2019-06-03
Owner Cmmt* | bar: IFR to R2 IFR
Category Code: K26 Underground communication Layouts
Category Code: K27 Road and Drainage Layouts
| CV | OL1-2K27-0001 | ROADS, PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-15; R2 IFD: 2020-09-29
[6 empty] | Revised Plan | R2 IFD: 2020-09-29
[6 empty] | Issue Actual | IFR: 2019-03-15; R2 IFR: 2019-03-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01074; R2 IFR: TPSK-LSPA1-T-CV-01074
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K27-0002 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; R2 IFR: 2020-09-29
[6 empty] | Revised Plan | IFR: 2020-05-15; R2 IFR: 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0003 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; R2 IFR: 2020-09-29
[6 empty] | Revised Plan | IFR: 2020-05-15; R2 IFR: 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0004 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; R2 IFR: 2020-09-29
[6 empty] | Revised Plan | IFR: 2020-05-15; R2 IFR: 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0005 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; R2 IFR: 2020-09-29
[6 empty] | Revised Plan | IFR: 2020-05-15; R2 IFR: 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0006 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; R2 IFR: 2020-09-29
[6 empty] | Revised Plan | IFR: 2020-05-15; R2 IFR: 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K28 Fireproofing Plan |  |  |  |  | Class 2 | Purpose**
Category Code: K30 General Arrangement for Architectural drawings of Buildings | [5 empty] | Rev.
| CV | OL1-2K30-0002 | Electrical SUB-E And FAR-1 - Architectural Ground Floor Plan |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-03-29; R2 IFD: 2020-05-13
[6 empty] | Revised Plan | R2 IFD: 2020-05-13
[6 empty] | Issue Actual | IFR: 2019-03-21; R2 IFR: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01122; R2 IFR: TPSK-LSPA1-T-CV-01122
[6 empty] | Return Date | IFR: 2019-05-30; R2 IFR: 2019-05-30
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0003 | Electrical SUB-E And FAR-1 - Architectural First Floor Plan |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-03-29; R2 IFD: 2020-05-13
[6 empty] | Revised Plan | R2 IFD: 2020-05-13
[6 empty] | Issue Actual | IFR: 2019-03-21; R2 IFR: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01122; R2 IFR: TPSK-LSPA1-T-CV-01122
[6 empty] | Return Date | IFR: 2019-05-30; R2 IFR: 2019-05-30
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0004 | Electrical SUB-E And FAR-1 - Architectural First Floor Plan |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-03-29; R2 IFD: 2020-05-13
[6 empty] | Revised Plan | R2 IFD: 2020-05-13
[6 empty] | Issue Actual | IFR: 2019-03-21; R2 IFR: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01122; R2 IFR: TPSK-LSPA1-T-CV-01122
[6 empty] | Return Date | IFR: 2019-05-30; R2 IFR: 2019-05-30
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0005 | Electrical SUB-E And FAR-1 - Architectural Sections |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-03-29; R2 IFD: 2020-05-13
[6 empty] | Revised Plan | R2 IFD: 2020-05-13
[6 empty] | Issue Actual | IFR: 2019-03-21; R2 IFR: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01122; R2 IFR: TPSK-LSPA1-T-CV-01122
[6 empty] | Return Date | IFR: 2019-05-30; R2 IFR: 2019-05-30
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0006 | Electrical SUB-E And FAR-1 - Architectural Section D And Elevation 1 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-03-29; R2 IFD: 2020-05-13
[6 empty] | Revised Plan | R2 IFD: 2020-05-13
[6 empty] | Issue Actual | IFR: 2019-03-21; R2 IFR: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01122; R2 IFR: TPSK-LSPA1-T-CV-01122
[6 empty] | Return Date | IFR: 2019-05-30; R2 IFR: 2019-05-30
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0007 | Electrical SUB-E And FAR-1 - Architectural Elevations |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-03-29; R2 IFD: 2020-05-13
[6 empty] | Revised Plan | R2 IFD: 2020-05-13
[6 empty] | Issue Actual | IFR: 2019-03-21; R2 IFR: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01122; R2 IFR: TPSK-LSPA1-T-CV-01122
[6 empty] | Return Date | IFR: 2019-05-30; R2 IFR: 2019-05-30
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0015 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - ARCHITECTURAL CONSTR. DWGS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-03-29; R2 IFD: 2020-05-13
[6 empty] | Revised Plan | R2 IFD: 2020-05-13
[6 empty] | Issue Actual | IFR: 2019-03-21; R2 IFR: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01122; R2 IFR: TPSK-LSPA1-T-CV-01122
[6 empty] | Return Date | IFR: 2019-05-30; R2 IFR: 2019-05-30
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0016 | Electrical SUB-C And FAR-2 - Architectural First Floor Plan |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-03-29; R2 IFD: 2020-05-13
[6 empty] | Revised Plan | R2 IFD: 2020-05-13
[6 empty] | Issue Actual | IFR: 2019-03-21; R2 IFR: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01122; R2 IFR: TPSK-LSPA1-T-CV-01122
[6 empty] | Return Date | IFR: 2019-05-30; R2 IFR: 2019-05-30
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0017 | Electrical SUB-C And FAR-2 - Architectural Roof Floor Plan |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-03-29; R2 IFD: 2020-05-13
[6 empty] | Revised Plan | R2 IFD: 2020-05-13
[6 empty] | Issue Actual | IFR: 2019-03-21; R2 IFR: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01122; R2 IFR: TPSK-LSPA1-T-CV-01122
[6 empty] | Return Date | IFR: 2019-05-30; R2 IFR: 2019-05-30
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0018 | Electrical SUB-C And FAR-2 - Architectural Sections |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-03-29; R2 IFD: 2020-05-13
[6 empty] | Revised Plan | R2 IFD: 2020-05-13
[6 empty] | Issue Actual | IFR: 2019-03-21; R2 IFR: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01122; R2 IFR: TPSK-LSPA1-T-CV-01122
[6 empty] | Return Date | IFR: 2019-05-30; R2 IFR: 2019-05-30
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0019 | Electrical SUB-C And FAR-2 - Architectural Elevations |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-03-29; R2 IFD: 2020-05-13
[6 empty] | Revised Plan | R2 IFD: 2020-05-13
[6 empty] | Issue Actual | IFR: 2019-03-21; R2 IFR: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01122; R2 IFR: TPSK-LSPA1-T-CV-01122
[6 empty] | Return Date | IFR: 2019-05-30; R2 IFR: 2019-05-30
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0030 | GATEHOUSE - ARCHITECTURAL CONSTR. DWGS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFD: 2020-01-28
[6 empty] | Revised Plan | R2 IFD: 2020-01-28
[6 empty] | Issue Actual | IFR: 2019-03-14; R2 IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSL-LSPA1-T-CV-01064; R2 IFR: TPSL-LSPA1-T-CV-01064
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0031 | Gatehouse A - Architectural Elevations And Sections |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFD: 2020-01-28
[6 empty] | Revised Plan | R2 IFD: 2020-01-28
[6 empty] | Issue Actual | IFR: 2019-03-14; R2 IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSL-LSPA1-T-CV-01064; R2 IFR: TPSL-LSPA1-T-CV-01064
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0032 | Gatehouse A - Architectural Isometric Views |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFD: 2020-01-28
[6 empty] | Revised Plan | R2 IFD: 2020-01-28
[6 empty] | Issue Actual | IFR: 2019-03-14; R2 IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSL-LSPA1-T-CV-01064; R2 IFR: TPSL-LSPA1-T-CV-01064
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0038 | Gatehouse A - Architectural Plans Elevations Sections And Schedules |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR
Rev. | bar: IFR to R2 IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-14; R2 IFR: 2019-03-15
[6 empty] | Issue Actual | IFR: 2019-03-14; R2 IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSL-LSPA1-T-CV-01064; R2 IFR: TPSL-LSPA1-T-CV-01064
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0040 | OPERATION TOOL ROOM - ARCHITECTURAL CONSTR. DWGS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-16; R2 IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-12-16; R2 IFD: 2020-02-15
[6 empty] | Issue Actual | IFR: 2019-03-14; R2 IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSL-LSPA1-T-CV-01064; R2 IFR: TPSL-LSPA1-T-CV-01064
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0041 | Operation Tool Room - Architectural Elevations And Sections |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-16; R2 IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-12-16; R2 IFD: 2020-02-15
[6 empty] | Issue Actual | IFR: 2019-03-14; R2 IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSL-LSPA1-T-CV-01064; R2 IFR: TPSL-LSPA1-T-CV-01064
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0042 | Operation Tool Room - Architectural Isometric Views |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-16; R2 IFD: 2020-02-15
[6 empty] | Revised Plan | IFR: 2019-12-16; R2 IFD: 2020-02-15
[6 empty] | Issue Actual | IFR: 2019-03-14; R2 IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSL-LSPA1-T-CV-01064; R2 IFR: TPSL-LSPA1-T-CV-01064
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0050 | Electrical SUB-F And FAR-F - Architectural Plans And Schedules |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IDD
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-05-17; R2 IFD: 2019-08-30
[6 empty] | Revised Plan | R2 IFD: 2019-08-30
[6 empty] | Issue Actual | IFR: 2019-03-21; R2 IFR: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01122; R2 IFR: TPSK-LSPA1-T-CV-01122
[6 empty] | Return Date | IFR: 2019-05-30; R2 IFR: 2019-05-30
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K30-0051 | Electrical SUB-F And FAR-F - Architectural Sections And Elevations |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IDD
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-05-17; R2 IFD: 2019-08-30
[6 empty] | Revised Plan | R2 IFD: 2019-08-30
[6 empty] | Issue Actual | IFR: 2019-03-21; R2 IFR: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01122; R2 IFR: TPSK-LSPA1-T-CV-01122
[6 empty] | Return Date | IFR: 2019-05-30; R2 IFR: 2019-05-30
Owner Cmmt* | bar: IFR to R2 IFR
Category Code: K31 General Arrangement for Civil Concrete Works drawings
| CV | OL1-2K31-0004 | Foundation For 10-E-2765 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-30; R2 IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01522; R2 IFR: TPSK-LSPA1-T-CV-01522
[6 empty] | Return Date | IFR: 2019-05-27; R2 IFR: 2019-05-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0005 | Foundation For 10-E-2585 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-01; R2 IFR: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01206; R2 IFR: TPSK-LSPA1-T-CV-01206
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFR: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0040 | Foundation for 10-T-2300 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-11; R2 IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01854; R2 IFR: TPSK-LSPA1-T-CV-01854
[6 empty] | Return Date | IFR: 2019-08-14
Owner Cmmt* | bar: IFR
| CV | OL1-2K31-0051 | Foundation For 10-D-2210 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01169; R2 IFR: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0052 | Foundation For 10-D-2230 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01169; R2 IFR: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0053 | Foundation for 10-D-2405 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01169; R2 IFR: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0060 | Foundation For 10-TK-2910 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-0062 | Foundation For 10-E-2230A-B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01373; R2 IFR: TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0063 | Foundation For 10-E-2412 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-12; R2 IFR: 2019-04-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01334; R2 IFR: TPSK-LSPA1-T-CV-01334
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFR: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0064 | Foundation for 10-E-2413 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-24; R2 IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01470; R2 IFR: TPSK-LSPA1-T-CV-01470
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0066 | Foundation For 10-E-2446 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01373; R2 IFR: TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0068 | Foundation For 10-E-2450 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-15; R2 IFR: 2019-04-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01349; R2 IFR: TPSK-LSPA1-T-CV-01349
[6 empty] | Return Date | IFR: 2019-04-23; R2 IFR: 2019-04-23
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0070 | Foundation For 10-E-2206 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-01; R2 IFR: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01206; R2 IFR: TPSK-LSPA1-T-CV-01206
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFR: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0071 | Foundation For 10-E-2210AB |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01373; R2 IFR: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0072 | Foundation For 10-E-2220A-B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01373; R2 IFR: TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0073 | Foundation For 10-E-2240A-B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01373; R2 IFR: TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0075 | Foundation For 10-E-2305 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01373; R2 IFR: TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0082 | Foundation For 10-F-2320A-B |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02409
Return Date
Owner Cmmt*
| CV | OL1-2K31-0083 | Foundation For 10-F-2310A-B |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02409
Return Date
Owner Cmmt*
| CV | OL1-2K31-0094 | Foundation For 10-T-2580 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01169; R2 IFR: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0096 | Foundation For 10-T-2570 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01169; R2 IFR: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0097 | Foundation For 10-T-2510 And 10-T-2540 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-03; R2 IFR: 2019-04-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01241; R2 IFR: TPSK-LSPA1-T-CV-01241
[6 empty] | Return Date | IFR: 2019-05-07; R2 IFR: 2019-05-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0098 | Foundation For 10-T-2510 And 10-T-2540 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-03; R2 IFR: 2019-04-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01241; R2 IFR: TPSK-LSPA1-T-CV-01241
[6 empty] | Return Date | IFR: 2019-05-07; R2 IFR: 2019-05-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0100 | Foundation For 10-D-2411 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01169; R2 IFR: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0101 | Foundation Vor 10-D-2480A |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01169; R2 IFR: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0103 | Foundation for 10-D-2322 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-11; R2 IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01854; R2 IFR: TPSK-LSPA1-T-CV-01854
[6 empty] | Return Date | IFR: 2019-08-14
Owner Cmmt* | bar: IFR
| CV | OL1-2K31-0104 | Foundation For 10-E-1006 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01747; R2 IFR: TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | R2 IFR: 2019-06-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0106 | Foundation For 10-D-2420A-B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01663; R2 IFR: TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | R2 IFR: 2019-06-13
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0107 | Concrete Structure For 10-D-2880 And 10-D-2865 - Reinforcement |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-04; R2 IFR: 2019-07-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02071; R2 IFR: TPSK-LSPA1-T-CV-02071
Return Date
Owner Cmmt*
| CV | OL1-2K31-0111 | Foundation For 10-D-2525 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-20; R2 IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01926; R2 IFR: TPSK-LSPA1-T-CV-01926
Return Date
Owner Cmmt*
| CV | OL1-2K31-0113 | Concrete Structure For 10-D-2880 And 10-D-2865 - Formworks |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-01; R2 IFR: 2019-07-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02028; R2 IFR: TPSK-LSPA1-T-CV-02028
Return Date
Owner Cmmt*
| CV | OL1-2K31-0117 | Foundation For 10-E-2587 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-01; R2 IFR: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01206; R2 IFR: TPSK-LSPA1-T-CV-01206
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFR: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0143 | Foundation For 10-R-2700A-B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01663; R2 IFR: TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | R2 IFR: 2019-06-13
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0144 | Foundation For 10-R-2620 A |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01373; R2 IFR: TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0147 | Foundation For 10-E-2666 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01663; R2 IFR: TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | R2 IFR: 2019-06-13
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0149 | Foundation For 10-E-2660 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-24; R2 IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01470; R2 IFR: TPSK-LSPA1-T-CV-01470
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0153 | Foundation for 10-T-2630 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01373; R2 IFR: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0154 | Foundation For 10-R-2470A-B-C |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01663; R2 IFR: TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | R2 IFR: 2019-06-13
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0157 | Foundation For 10-D-2460 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01169; R2 IFR: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0158 | Foundation For 10-D-2440 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01169; R2 IFR: TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFR: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0159 | Foundation for 10-D-1000 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01373; R2 IFR: TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0160 | Foundation For 10-E-2635 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-15; R2 IFR: 2019-04-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01349; R2 IFR: TPSK-LSPA1-T-CV-01349
[6 empty] | Return Date | IFR: 2019-04-23; R2 IFR: 2019-04-23
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0163 | Foundation for 10-E-2474 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01373; R2 IFR: TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0164 | Foundation For 10-E-2465 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01373; R2 IFR: TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0165 | Foundation For 10-E-2460 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01373; R2 IFR: TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0166 | Foundation For 10-E-2440 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-12; R2 IFR: 2019-04-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01334; R2 IFR: TPSK-LSPA1-T-CV-01334
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFR: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0170 | Foundation For 10-E-1000 A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-15; R2 IFR: 2019-04-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01349; R2 IFR: TPSK-LSPA1-T-CV-01349
[6 empty] | Return Date | IFR: 2019-04-23; R2 IFR: 2019-04-23
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0171 | Foundation For 10-E-1005 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-15; R2 IFR: 2019-04-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01349; R2 IFR: TPSK-LSPA1-T-CV-01349
[6 empty] | Return Date | IFR: 2019-04-23; R2 IFR: 2019-04-23
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0177 | Foundation For 10-D-2705 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-30; R2 IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01522; R2 IFR: TPSK-LSPA1-T-CV-01522
[6 empty] | Return Date | IFR: 2019-05-27; R2 IFR: 2019-05-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0178 | Foundation For 10-E-2705 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-30; R2 IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01522; R2 IFR: TPSK-LSPA1-T-CV-01522
[6 empty] | Return Date | IFR: 2019-05-27; R2 IFR: 2019-05-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0180 | Foundation For 10-D-2735 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-18; R2 IFR: 2019-04-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01414; R2 IFR: TPSK-LSPA1-T-CV-01414
[6 empty] | Return Date | IFR: 2019-05-27; R2 IFR: 2019-05-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0184 | Foundation For 10-E-2755 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01663; R2 IFR: TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | R2 IFR: 2019-06-13
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0188 | Foundation For 10-E-2702 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-27; R2 IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02004; R2 IFR: TPSK-LSPA1-T-CV-02004
Return Date
Owner Cmmt*
| CV | OL1-2K31-0189 | Foundation For 10-E-2701 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-23; R2 IFR: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01455; R2 IFR: TPSK-LSPA1-T-CV-01455
[6 empty] | Return Date | IFR: 2019-05-27; R2 IFR: 2019-05-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0190 | Foundation For 10-E-2706 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01663; R2 IFR: TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | R2 IFR: 2019-06-13
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0198 | Foundation For 10-E-2882 And 10-E-2884 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-01; R2 IFR: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01206; R2 IFR: TPSK-LSPA1-T-CV-01206
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFR: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0200 | Foundation For 10-E-2100 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-0201 | Foundation For 10-TK-2320 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02409
Return Date
Owner Cmmt*
| CV | OL1-2K31-0203 | Foundation For 10-D-1910 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-24; R2 IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01470; R2 IFR: TPSK-LSPA1-T-CV-01470
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0210 SH001 | Foundation For 10-TK-3900 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR
Rev. | bar: IFR to R2 IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; R2 IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; R2 IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02152; R2 IFR: TPSK-LSPA1-T-CV-02152
Return Date
Owner Cmmt*
| CV | OL1-2K31-0210 SH002 | Foundation For 10-TK-3900 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR
Rev. | bar: IFR to R2 IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; R2 IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; R2 IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02152; R2 IFR: TPSK-LSPA1-T-CV-02152
Return Date
Owner Cmmt*
| CV | OL1-2K31-0211 | Foundation For 10-T-3000 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-14; R2 IFR: 2019-06-17; R2 IFD: 2019-06-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01896; R2 IFR: TPSK-LSPA1-T-CV-01896; R2 IFD: TPSK-LSPA1-T-CV-01896
[6 empty] | Return Date | R2 IFD: 2019-08-19
Owner Cmmt* | bar: R2 IFD
| CV | OL1-2K31-0215 | Foundation For 10-T-3030 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-14; R2 IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01896; R2 IFR: TPSK-LSPA1-T-CV-01896
[6 empty] | Return Date | R2 IFR: 2019-08-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0216 | Foundation For 10-T-3050 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-17; R2 IFR: 2019-06-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01898; R2 IFR: TPSK-LSPA1-T-CV-01898
[6 empty] | Return Date | R2 IFR: 2019-08-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0219 | Foundation For 10-T-3080 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-17; R2 IFR: 2019-06-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01898; R2 IFR: TPSK-LSPA1-T-CV-01898
[6 empty] | Return Date | R2 IFR: 2019-08-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0220 | Foundation For 10-T-3070 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-02; R2 IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02047; R2 IFR: TPSK-LSPA1-T-CV-02047
Return Date
Owner Cmmt*
| CV | OL1-2K31-0222 | FOUNDATION FOR 10-D-3908 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02340
Return Date
Owner Cmmt*
| CV | OL1-2K31-0223 | FOUNDATION FOR 10-D-3902 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02340
Return Date
Owner Cmmt*
| CV | OL1-2K31-0224 | FOUNDATION FOR 10-D-3904 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02340
Return Date
Owner Cmmt*
| CV | OL1-2K31-0225 | FOUNDATION FOR 10-D-3906 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02340
Return Date
Owner Cmmt*
| CV | OL1-2K31-0226 | Foundation For 10-D-3180 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-02; R2 IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02047; R2 IFR: TPSK-LSPA1-T-CV-02047
Return Date
Owner Cmmt*
| CV | OL1-2K31-0227 | Foundation For 10-D-3110 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-02; R2 IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02047; R2 IFR: TPSK-LSPA1-T-CV-02047
Return Date
Owner Cmmt*
| CV | OL1-2K31-0237 | Foundation For 10-E-3045 A/B/C/D |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02439
Return Date
Owner Cmmt*
| CV | OL1-2K31-0238 | Foundation For 10-E-3044 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02439
Return Date
Owner Cmmt*
| CV | OL1-2K31-0242 | Foundation For 10-E-3070 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02439
Return Date
Owner Cmmt*
| CV | OL1-2K31-0266 | Foundation For 10-D-3126 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-02; R2 IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02047; R2 IFR: TPSK-LSPA1-T-CV-02047
Return Date
Owner Cmmt*
| CV | OL1-2K31-0267 | Foundation For 10-D-5550 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR
Rev. | bar: IFR to R2 IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11; R2 IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R2 IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01852; R2 IFR: TPSK-LSPA1-T-CV-01852
Return Date
Owner Cmmt*
| CV | OL1-2K31-0268 | Foundation For 10-D-5500 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-20; R2 IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01923; R2 IFR: TPSK-LSPA1-T-CV-01923
Return Date
Owner Cmmt*
| CV | OL1-2K31-0269 | FOUNDATION FOR 10-D-5510 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-13; R2 IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01647; R2 IFR: TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | R2 IFR: 2019-07-16
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0270 | FOUNDATION FOR 10-D-5513 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-13; R2 IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01647; R2 IFR: TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | R2 IFR: 2019-07-16
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0271 | FOUNDATION FOR 10-D-5515 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-13; R2 IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01647; R2 IFR: TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | R2 IFR: 2019-07-16
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0272 | FOUNDATION FOR 10-D-5520 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-13; R2 IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01647; R2 IFR: TPSK-LSPA1-T-CV-01647
Return Date
Owner Cmmt*
| CV | OL1-2K31-0275 | FOUNDATION FOR 10-E-5513 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-17; R2 IFR: 2019-05-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01687; R2 IFR: TPSK-LSPA1-T-CV-01687
[6 empty] | Return Date | R2 IFR: 2019-07-16
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0278 | Foundation For 10-TK-5640 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-10; R2 IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01837; R2 IFR: TPSK-LSPA1-T-CV-01837
[6 empty] | Return Date | R2 IFR: 2019-08-08
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0278 SH001 | Foundation For 10-TK-5640 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR
Rev. | bar: IFR to R2 IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20; R2 IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20; R2 IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01923; R2 IFR: TPSK-LSPA1-T-CV-01923
Return Date
Owner Cmmt*
| CV | OL1-2K31-0282 | Foundation For 10-TX-C-2550 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02203
Return Date
Owner Cmmt*
| CV | OL1-2K31-0284 | FOUNDATION FOR 10-E-5510 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR
Rev. | bar: IFR to R2 IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-17; R2 IFR: 2019-05-21
[6 empty] | Issue Actual | IFR: 2019-05-17; R2 IFR: 2019-05-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01687; R2 IFR: TPSK-LSPA1-T-CV-01687
[6 empty] | Return Date | R2 IFR: 2019-07-16
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0303-001 | Foundation For10-TK-5110 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-13; R2 IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01886; R2 IFR: TPSK-LSPA1-T-CV-01886
[6 empty] | Return Date | R2 IFR: 2019-08-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0303-002 | Foundation For 10-TK-5110 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-13; R2 IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01886; R2 IFR: TPSK-LSPA1-T-CV-01886
Return Date
Owner Cmmt*
| CV | OL1-2K31-0304-001 | Foundation For 10-TK-5120 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-13; R2 IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01886; R2 IFR: TPSK-LSPA1-T-CV-01886
[6 empty] | Return Date | R2 IFR: 2019-08-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0304-002 | Foundation For 10-TK-5120 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-13; R2 IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01886; R2 IFR: TPSK-LSPA1-T-CV-01886
[6 empty] | Return Date | R2 IFR: 2019-08-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0307 | Foundation For 10-D-5400 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-30; R2 IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01522; R2 IFR: TPSK-LSPA1-T-CV-01522
[6 empty] | Return Date | IFR: 2019-05-27; R2 IFR: 2019-05-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0308 | Foundation For 10-D-5114 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-23; R2 IFR: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01455; R2 IFR: TPSK-LSPA1-T-CV-01455
[6 empty] | Return Date | IFR: 2019-05-27; R2 IFR: 2019-05-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0309 | Foundation For 10-D-5112 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-23; R2 IFR: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01455; R2 IFR: TPSK-LSPA1-T-CV-01455
[6 empty] | Return Date | IFR: 2019-05-27; R2 IFR: 2019-05-27
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0310 | Foundation for 10-D-5552 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-10; R2 IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01837; R2 IFR: TPSK-LSPA1-T-CV-01837
[6 empty] | Return Date | R2 IFR: 2019-08-08
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0311 | Foundation for 10-D-5565 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-10; R2 IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01837; R2 IFR: TPSK-LSPA1-T-CV-01837
[6 empty] | Return Date | R2 IFR: 2019-08-08
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0313 | Foundation For 10-E-5113 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01663; R2 IFR: TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | R2 IFR: 2019-06-13
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0314 | Foundation For 10-E-5552 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-06-10; R2 IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01837; R2 IFR: TPSK-LSPA1-T-CV-01837
[6 empty] | Return Date | R2 IFR: 2019-08-08
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0323 | FOUNDATION FOR 10-TK-5900 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-13; R2 IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01647; R2 IFR: TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | R2 IFR: 2019-07-16
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0336 | Foundation For 10-TK-2300 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-0338 | Foundation For 10-E-2441 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR
Rev. | bar: IFR to R2 IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-12; R2 IFR: 2019-04-15
[6 empty] | Issue Actual | IFR: 2019-04-12; R2 IFR: 2019-04-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01334; R2 IFR: TPSK-LSPA1-T-CV-01334
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFR: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0339 | Foundation for 10-E-2442 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-16; R2 IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01373; R2 IFR: TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0340 | Foundation For 10-E-2405 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-05-14; R2 IFR: 2019-05-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01663; R2 IFR: TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | R2 IFR: 2019-06-13
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0341 | Foundation For 10-D-1912 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-24; R2 IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01470; R2 IFR: TPSK-LSPA1-T-CV-01470
[6 empty] | Return Date | IFR: 2019-05-17; R2 IFR: 2019-05-17
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-0342 | Olefins Plant - Preliminary Field Pile Trial - Layout And Programme |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IMP
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-05-30; R2 IFD: 2019-07-29
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-05-30; R2 IFR: 2019-05-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01769; R2 IFR: TPSK-LSPA1-T-CV-01769
[6 empty] | Return Date | R2 IFR: 2019-07-12
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0343 | Bored Piles For Preliminary Test |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IMP
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-05-30; R2 IFD: 2019-07-29
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-05-30; R2 IFR: 2019-05-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01769; R2 IFR: TPSK-LSPA1-T-CV-01769
[6 empty] | Return Date | R2 IFR: 2019-07-12
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-0344 | Foundation For 10-E-3018 A/B |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02439
Return Date
Owner Cmmt*
| CV | OL1-2K31-1000 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-0P01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18
[6 empty] | Revised Plan | R2 IFD: 2019-11-18
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01747; R2 IFR: TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | R2 IFR: 2019-06-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-1001 | Foundation And Elevation Of Pipe Rack 10-PRK-0P01 - Formwork And Reinforcement |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18
[6 empty] | Revised Plan | R2 IFD: 2019-11-18
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01747; R2 IFR: TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | R2 IFR: 2019-06-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-1020 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-0P01 |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01747; R2 IFR: TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | R2 IFR: 2019-06-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-1021 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Plans |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01747; R2 IFR: TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | R2 IFR: 2019-06-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-1022 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Plans |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01747; R2 IFR: TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | R2 IFR: 2019-06-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-1023 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Elevations |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01747; R2 IFR: TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | R2 IFR: 2019-06-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-1024 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Elevations |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01747; R2 IFR: TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | R2 IFR: 2019-06-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-1025 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Elevations |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01747; R2 IFR: TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | R2 IFR: 2019-06-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-1026 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Columns |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01747; R2 IFR: TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | R2 IFR: 2019-06-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-1027 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Columns |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01747; R2 IFR: TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | R2 IFR: 2019-06-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-1028 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Columns |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01747; R2 IFR: TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | R2 IFR: 2019-06-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-1029 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Beams |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01747; R2 IFR: TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | R2 IFR: 2019-06-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-1030 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Beams |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-05-27; R2 IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01747; R2 IFR: TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | R2 IFR: 2019-06-19
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-1031 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Steel Bracings Details |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-05-30; R2 IFR: 2019-05-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01771; R2 IFR: TPSK-LSPA1-T-CV-01771
[6 empty] | Return Date | R2 IFR: 2019-07-12
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-1040 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-0P02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18
[6 empty] | Revised Plan | R2 IFD: 2019-11-18
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1041 | Foundation And Elevation Of Piperack 10-PRK-0P02 - Formwork And Reinforcement - |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18
[6 empty] | Revised Plan | R2 IFD: 2019-11-18
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1060 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-0P02 |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1061 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Plans - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1062 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Plans - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1063 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Elevations - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1064 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Elevations - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1065 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Elevations - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1066 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Elevations - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1067 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Columns - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1068 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Columns - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1069 | Precast Concrete Elevation For Piperack 10-PRK-0P02 -Columns - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1070 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Columns - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1071 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Columns - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1072 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Columns - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1073 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Beams - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1074 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Beams - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1075 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Beams - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1076 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Beams - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1077 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Beams - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1078 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Steel Bracings Details - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1079 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Steel Bracings Details - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-1080 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-0P03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | R2 IFR: 2019-12-16
[6 empty] | Issue Actual | IFR: 2019-07-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1081 | Foundation And Elevation Of Pipe Rack 10-PRK-0P03 - Formwork And Reinforcement |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1100 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-0P03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | R2 IFR: 2019-12-16; R2 IFD: 2020-01-16; R2 IFD: 2020-02-16
[6 empty] | Issue Actual | IFR: 2019-07-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1101 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Plans |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1102 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Plans |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1103 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Elevations |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1104 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Elevations |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1105 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1106 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1107 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1108 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1109 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1110 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1111 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1112 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Bracings |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1200 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2D01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1220 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2D01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1240 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2E01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | R2 IFR: 2019-12-16
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-1241 | Foundations Pipe Rack 10-PRK-2E01 - Formworks And Reinforcements |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-1242 | Foundations Pipe Rack 10-PRK-2E01 - Formworks And Reinforcements |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-1243 | Foundations Pipe Rack 10-PRK-2E01 - Formworks And Reinforcements |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-1260 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2E01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | R2 IFR: 2019-12-16; R2 IFD: 2020-01-16; R2 IFD: 2020-02-16
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1261 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Plans |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1262 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Plans |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1263 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Plans |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1264 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1265 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1266 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1267 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1268 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1269 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1270 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1271 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1272 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1273 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1274 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1275 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1276 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1277 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1278 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1279 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1280 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2A01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | R2 IFR: 2019-12-16
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1281 | Piperack 10-PRK-2A01 Foundation (Formwork and Reinforcement) |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1300 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2A01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | R2 IFR: 2019-12-16; R2 IFD: 2020-01-16; R2 IFD: 2020-02-16
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1301 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Plans |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1302 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Plans |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1303 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Elevations |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1304 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Elevations |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1305 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1306 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1307 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1308 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1309 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1310 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1311 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1312 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1313 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1314 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1315 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Steel Bracings Details |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1316 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Steel Bracings Details |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1320 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1340 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2B02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1360 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1380 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2B02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC; R2 IFD: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18; R2 IFD: 2019-12-18; R2 IFD: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1400 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2C01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1420 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2C02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFR: 2019-11-18
[6 empty] | Revised Plan | R2 IFR: 2019-12-16
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02330
Return Date
Owner Cmmt*
| CV | OL1-2K31-1421 | Foundations Pipe Rack 10-PRK-2C02 - (Formworks And Reinforcements) |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02330
Return Date
Owner Cmmt*
| CV | OL1-2K31-1460 | Foundation And Elevation For 10-STR-2B03 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-02-12
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02424
Return Date
Owner Cmmt*
| CV | OL1-2K31-1560 | FOUNDATION AND ELEVATION FOR 10-STR-2E01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1580 | FOUNDATION AND ELEVATION FOR 10-STR-2E02, 10-D-2420A/B AND 10-E-2430 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1600 | FOUNDATION AND ELEVATION FOR 10-STR-2E03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1620 | FOUNDATION AND ELEVATION FOR 10-STR-2E04 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1640 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D05 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1660 | FOUNDATION AND ELEVATION FOR 10-STR-2B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1680 | FOUNDATION AND ELEVATION FOR 10-STR-2B02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1700 | FOUNDATION AND ELEVATION FOR 10-STR-2B03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1720 | FOUNDATION AND ELEVATION FOR 10-STR-2B04 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1740 | FOUNDATION AND ELEVATION FOR 10-STR-2B05 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1760 | FOUNDATION AND ELEVATION FOR 10-STR-2B06 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1780 | FOUNDATION AND ELEVATION FOR 10-SHT-2D01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFD: 2020-05-13
[6 empty] | Revised Plan | R2 IFD: 2020-05-13
[6 empty] | Issue Actual | IFR: 2019-06-11; R2 IFR: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01858; R2 IFR: TPSK-LSPA1-T-CV-01858
[6 empty] | Return Date | R2 IFR: 2019-08-16
Owner Cmmt* | bar: R2 IFR
| CV | OL1-2K31-1800 | FOUNDATION AND ELEVATION FOR 10-SHT-2D02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | R2 IFR: 2020-04-17
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02304
Return Date
Owner Cmmt*
| CV | OL1-2K31-1820 | FOUNDATION AND ELEVATION FOR 10-STR-2C01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1840 | FOUNDATION AND ELEVATION FOR 10-STR-2C02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1860 | FOUNDATION AND ELEVATION FOR 10-STR-2C03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1880 | FOUNDATION AND ELEVATION FOR 10-STR-2C04 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1900 | FOUNDATION AND ELEVATION FOR 10-STR-2C05 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1920 | FOUNDATION AND ELEVATION FOR 10-SHT-2B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1940 | FOUNDATION AND ELEVATION FOR 10-SHT-1B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1960 | FOUNDATION AND ELEVATION FOR 10-STR-0P01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | R2 IFR: 2020-04-17
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-1961 | Concrete Structure 10-STR-0P01 - Foundations And Elevations - Formwork |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-02-12
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-1962 | Concrete Structure 10-STR-0P01 - Foundations And Elevations - Reinforcement |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-02-12
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-1963 | Concrete Structure 10-STR-0P01 - Foundations And Elevations - Reinforcement |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-02-12
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-1980 | FOUNDATION AND ELEVATION FOR 10-STR-2A01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | R2 IFR: 2020-04-17
[6 empty] | Issue Actual | IFR: 2019-07-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02203
Return Date
Owner Cmmt*
| CV | OL1-2K31-2000 | FOUNDATION AND ELEVATION FOR 10-STR-2A02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2020 | FOUNDATION AND ELEVATION FOR 10-STR-2A03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2120 | FOUNDATION AND ELEVATION FOR TOOL ROOM OPERATION |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2140 | FOUNDATION FOR 10-SHT-2E01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2160 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2180 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D02 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2200 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D03 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2220 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D04 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
[6 empty] | Revised Plan | IFR: 2020-02-12; R2 IFR: 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2520 | Concrete Basin 10-PIT-2090 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-24; R2 IFD: 2020-01-24
[6 empty] | Revised Plan | R2 IFD: 2020-01-24
[6 empty] | Issue Actual | IFR: 2019-04-10; R2 IFR: 2019-04-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01304; R2 IFR: TPSK-LSPA1-T-CV-01304
[6 empty] | Return Date | IFR: 2019-05-09; R2 IFR: 2019-05-09
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-2521 | Concrete Basin 10-PIT-2090 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-24; R2 IFD: 2020-01-24
[6 empty] | Revised Plan | R2 IFD: 2020-01-24
[6 empty] | Issue Actual | IFR: 2019-04-10; R2 IFR: 2019-04-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01304; R2 IFR: TPSK-LSPA1-T-CV-01304
[6 empty] | Return Date | IFR: 2019-05-09; R2 IFR: 2019-05-09
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-2540 | Concrete Basin 10-PIT-5602 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-24; R2 IFD: 2020-01-24
[6 empty] | Revised Plan | R2 IFD: 2020-01-24
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-2541 | Concrete Basin 10-PIT-5602 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-24; R2 IFD: 2020-01-24
[6 empty] | Revised Plan | R2 IFD: 2020-01-24
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-2560 | Foundation For 10-H-1100 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-15; R2 IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02148; R2 IFR: TPSK-LSPA1-T-CV-02148
Return Date
Owner Cmmt*
| CV | OL1-2K31-2561 | Foundation For 10-H-1100 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-15; R2 IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02148; R2 IFR: TPSK-LSPA1-T-CV-02148
Return Date
Owner Cmmt*
| CV | OL1-2K31-2580 | Foundation For 10-H-1200 To 1600 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-15; R2 IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02148; R2 IFR: TPSK-LSPA1-T-CV-02148
Return Date
Owner Cmmt*
| CV | OL1-2K31-2581 | Foundation For 10-H-1200 To 1600 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-15; R2 IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02148; R2 IFR: TPSK-LSPA1-T-CV-02148
Return Date
Owner Cmmt*
| CV | OL1-2K31-2600 | Foundation For Basin 10-PIT-2190 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-24; R2 IFD: 2020-01-24
[6 empty] | Revised Plan | R2 IFD: 2020-01-24
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-2601 | Foundation For Basin 10-PIT-2190 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-24; R2 IFD: 2020-01-24
[6 empty] | Revised Plan | R2 IFD: 2020-01-24
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-2640 | Foundation for Basin 10-PIT-2392 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-24; R2 IFD: 2020-01-24
[6 empty] | Revised Plan | R2 IFD: 2020-01-24
[6 empty] | Issue Actual | IFR: 2019-06-24; R2 IFR: 2019-06-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01958; R2 IFR: TPSK-LSPA1-T-CV-01958
Return Date
Owner Cmmt*
| CV | OL1-2K31-2641 | Concrete Basin 10-PIT-2392 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-24; R2 IFD: 2020-01-24
[6 empty] | Revised Plan | R2 IFD: 2020-01-24
[6 empty] | Issue Actual | IFR: 2019-06-27; R2 IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02004; R2 IFR: TPSK-LSPA1-T-CV-02004
Return Date
Owner Cmmt*
| CV | OL1-2K31-2700 | Concrete Basin 10-PIT-2790 - Formwork |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-12-24
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-2701 | Concrete Basin 10-PIT-2790 - Reinforcement |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-12-24
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-2720 | Concrete Basin 10-PIT-5600 - Formwork |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-12-24
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-2721 | Concrete Basin 10-PIT-5600 - Reinforcement |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-12-24
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-3000 | FOUNDATION FOR 10-STR-1B01 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R2 IFR: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-3040 | Concrete Basin 10-PIT-5604 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-24; R2 IFD: 2020-01-24
[6 empty] | Revised Plan | R2 IFD: 2020-01-24
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-3041 | Concrete Basin 10-PIT-5604 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-24; R2 IFD: 2020-01-24
[6 empty] | Revised Plan | R2 IFD: 2020-01-24
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-3120 | Concrete Basin 10-PIT-2390 - Formwork |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-12-24
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02313
Return Date
Owner Cmmt*
| CV | OL1-2K31-3121 | Concrete Basin 10-PIT-2390 - Reinforcement |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-12-24
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02313
Return Date
Owner Cmmt*
| CV | OL1-2K31-3140 | Concrete Basin 10-PIT-5603 - Formwork |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-24; R2 IFD: 2020-01-24
[6 empty] | Revised Plan | R2 IFD: 2020-01-24
[6 empty] | Issue Actual | IFR: 2019-06-27; R2 IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02004; R2 IFR: TPSK-LSPA1-T-CV-02004
Return Date
Owner Cmmt*
| CV | OL1-2K31-3141 | Concrete Basin 10-PIT-5603 - Reinforcement |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-24; R2 IFD: 2020-01-24
[6 empty] | Revised Plan | R2 IFD: 2020-01-24
[6 empty] | Issue Actual | IFR: 2019-06-27; R2 IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02004; R2 IFR: TPSK-LSPA1-T-CV-02004
Return Date
Owner Cmmt*
| CV | OL1-2K31-4060 | Zone 2A - Piling Plan |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-10-15; R2 IFD: 2019-12-15
[6 empty] | Revised Plan | R2 IFD: 2019-12-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01170; R2 IFR: TPSK-LSPA1-T-CV-01170
[6 empty] | Return Date | IFR: 2019-06-03; R2 IFR: 2019-06-03
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-4120 | Zone 2D - Piling Plan |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-10-15; R2 IFD: 2019-12-15
[6 empty] | Revised Plan | R2 IFD: 2019-12-15
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01170; R2 IFR: TPSK-LSPA1-T-CV-01170
[6 empty] | Return Date | IFR: 2019-06-03; R2 IFR: 2019-06-03
Owner Cmmt* | bar: IFR to R2 IFR
| CV | OL1-2K31-4380 | Foundation For Basin 10-PIT-5606 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-12-24
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-4381 | Foundation For Basin 10-PIT-5606 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-12-24
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-4460 | Concrete Basin 10-PIT-5610 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-24; R2 IFD: 2020-01-24
[6 empty] | Revised Plan | R2 IFD: 2020-01-24
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-4461 | Concrete Basin 10-PIT-5610 |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-12-24; R2 IFD: 2020-01-24
[6 empty] | Revised Plan | R2 IFD: 2020-01-24
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-4580 | Concrete Structure For 10-T-2040 - Formwork |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-01; R2 IFR: 2019-07-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02028; R2 IFR: TPSK-LSPA1-T-CV-02028
Return Date
Owner Cmmt*
| CV | OL1-2K31-4581 | Concrete Structure For 10-T-2040 - Reinforcement |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFD: 2020-06-15
[6 empty] | Revised Plan | R2 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-07-01; R2 IFR: 2019-07-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02028; R2 IFR: TPSK-LSPA1-T-CV-02028
Return Date
Owner Cmmt*
| CV | OL1-2K31-5140 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Steel Bracings Details - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-5141 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Steel Bracings Details - |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC1 | IFC2
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-18; R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Revised Plan | R2 IFD: 2019-11-18; R2 IFD: 2019-12-18; R2 IBD: 2020-01-15
[6 empty] | Issue Actual | IFR: 2019-07-11; R2 IFR: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02116; R2 IFR: TPSK-LSPA1-T-CV-02116
Return Date
Owner Cmmt*
| CV | OL1-2K31-5150 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5151 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5152 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5153 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5154 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5155 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5156 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5157 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5158 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5159 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Steel Bracings Details |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5160 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Steel Bracings Details |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5161 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Steel Bracings Details |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5162 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Steel Bracings Details |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-08-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
Category Code: K32 General Arrangement for Steel Structure drawings
| CV | OL1-2K32-1100 | STEEL FOR PIPE RACK 10-PRK-2D01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFR: 2020-02-01; R2 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFR: 2020-02-01; R2 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1120 | STEEL FOR PIPE RACK 10-PRK-2E01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFR: 2020-02-01; R2 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFR: 2020-02-01; R2 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1140 | STEEL FOR PIPE RACK 10-PRK-2A01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFR: 2020-02-01; R2 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFR: 2020-02-01; R2 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1160 | STEEL FOR PIPE RACK 10-PRK-2B01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFR: 2020-02-01; R2 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFR: 2020-02-01; R2 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1180 | STEEL FOR PIPE RACK 10-PRK-2B02 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFR: 2020-02-01; R2 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFR: 2020-02-01; R2 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1200 | STEEL FOR PIPE RACK 10-PRK-2C01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFR: 2020-02-01; R2 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFR: 2020-02-01; R2 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1220 | STEEL FOR PIPE RACK 10-PRK-2C02 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFR: 2020-02-01; R2 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFR: 2020-02-01; R2 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1280 | STEEL FOR 10-SHT-2E01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1300 | STEEL FOR STRUCTURE 10-STR-2E01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1304 | FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-03-20; R2 IFD: 2019-04-10
[6 empty] | Revised Plan | R2 IFR: 2019-04-11; R2 IFD: 2019-04-12
[6 empty] | Issue Actual | R2 IFR: 2019-04-11; R2 IFD: 2019-04-12
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01321; R2 IFD: TPSK-LSPA1-T-CV-01321
Return Date
Owner Cmmt*
| CV | OL1-2K32-1320 | STEEL FOR STRUCTURE 10-STR-2E02 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1340 | STEEL FOR STRUCTURE 10-STR-2E03 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1360 | STEEL FOR STRUCTURE 10-STR-2E04 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1380 | STEEL FOR STRUCTURE 10-STR-2D05 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1400 | STEEL FOR STRUCTURE 10-STR-2B01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1420 | STEEL FOR STRUCTURE 10-STR-2B02 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1440 | STEEL FOR STRUCTURE 10-STR-2B03 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1460 | STEEL FOR STRUCTURE 10-STR-2B04 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1480 | STEEL FOR STRUCTURE 10-STR-2B05 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1500 | STEEL FOR STRUCTURE 10-STR-2B06 |  | Class 2 | Purpose** | IFR: IFC; R2 IFR: IFC1; R2 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFR: 2020-07-24; R2 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1511 | USC 36M FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1512 | USC 36M FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Issue Actual | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01222; R2 IFD: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1513 | USC 36M FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Issue Actual | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01222; R2 IFD: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1514 | USC 36M FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Issue Actual | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01222; R2 IFD: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1515 | USC 36M FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Issue Actual | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01222; R2 IFD: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1516 | USC 36M FURNACE STEEL SHADOW BOX DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Issue Actual | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01222; R2 IFD: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1517 | USC 36M FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Issue Actual | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01222; R2 IFD: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1518 | USC 36M FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Issue Actual | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01222; R2 IFD: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1519 | USC 36M FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Issue Actual | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01222; R2 IFD: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1520 | USC 36M FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-04-10; R2 IFD: 2019-04-11
[6 empty] | Issue Actual | R2 IFR: 2019-04-10; R2 IFD: 2019-04-11
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01308; R2 IFD: TPSK-LSPA1-T-CV-01308
Return Date
Owner Cmmt*
| CV | OL1-2K32-1521 | USC 36M FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-04-10; R2 IFD: 2019-04-11
[6 empty] | Issue Actual | R2 IFR: 2019-04-10; R2 IFD: 2019-04-11
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01308; R2 IFD: TPSK-LSPA1-T-CV-01308
Return Date
Owner Cmmt*
| CV | OL1-2K32-1522 | USC 36M FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148-2 1/2 & EL 221-10 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Issue Actual | R2 IFR: 2019-04-01; R2 IFD: 2019-04-02
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01222; R2 IFD: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1523 | USC 36M FURNACE STEEL END WALL TUBE SHEET ELEVATION |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1524 | USC 36M FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-03-20; R2 IFD: 2019-04-10
[6 empty] | Revised Plan | R2 IFR: 2019-04-09; R2 IFD: 2019-04-10
[6 empty] | Issue Actual | R2 IFR: 2019-04-09; R2 IFD: 2019-04-10
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01293; R2 IFD: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1525 | USC 36M FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-04-09; R2 IFD: 2019-04-10
[6 empty] | Issue Actual | R2 IFR: 2019-04-09; R2 IFD: 2019-04-10
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01293; R2 IFD: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1526 | USC 36M FURNACE STEEL CONVECTION SECTION HEADER BOX ELEVATIONS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1527 | USC 36M FURNACE STEEL CONVECTION SECTION HEADER BOX DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-04-09; R2 IFD: 2019-04-10
[6 empty] | Issue Actual | R2 IFR: 2019-04-09; R2 IFD: 2019-04-10
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01293; R2 IFD: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1528 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE A2 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1529 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE B2 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1530 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE C2 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1531 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D2 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1532 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D0 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1533 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1534 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1535 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1536 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1537 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1538 | USC 36M FURNACE STEEL CONVECTION SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1539 | USC 36M FURNACE STEEL CROSSOVER LIMIT STOP DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1540 | USC 36M FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1541 | USC 36M FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-04-09; R2 IFD: 2019-04-10
[6 empty] | Issue Actual | R2 IFR: 2019-04-09; R2 IFD: 2019-04-10
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01293; R2 IFD: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1542 | USC 36M FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1543 | USC 36M FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1544 | USC 36M FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1545 | USC 36M FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1546 | USC 36M FURNACE STEEL NAME PLATE |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFR: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1550 | USC 36M FURNACE STEEL STACK AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-04-09; R2 IFD: 2019-04-10
[6 empty] | Issue Actual | R2 IFR: 2019-04-09; R2 IFD: 2019-04-10
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-CV-01293; R2 IFD: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1551 | USC 36M FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFD: IFC
Rev. | bar: R2 IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFR: 2019-01-30; R2 IFD: 2019-01-31
[6 empty] | Issue Actual | R2 IFR: 2019-01-30; R2 IFD: 2019-01-31
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-ME-00767; R2 IFD: TPSK-LSPA1-T-ME-00767
[6 empty] | Return Date | R2 IFR: 2019-02-21; R2 IFD: 2019-02-21
Owner Cmmt* | bar: R2 IFR to R2 IFD
| CV | OL1-2K32-1552 | USC 36M FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  | Class 3 | Purpose** | IFR | IFI | IFI | IFD | IFF | IMP | IMP | IMP
[6 empty] | Rev. |  | A | A |  |  | 0 | 0 | 1
[6 empty] | Issue Plan | IFR: 2018-09-18; R2 IFD: 2018-12-07; R2 IFF: 2019-01-31
[6 empty] | Revised Plan |  | 2019-04-01 | 2019-04-02 |  |  | 2019-05-21 | 2019-05-23 | 2019-07-23
[6 empty] | Issue Actual |  | 2019-04-01 | 2019-04-02 |  |  | 2019-05-21 | 2019-05-23 | 2019-07-23
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222 | TPSK-LSPA1-T-CV-01222 |  |  | TPSK-LSPA1-T-CV-01709 | TPSK-LSPA1-T-CV-01709 | TPSK-LSPA1-T-CV-02227
[6 empty] | Return Date | R2 IMP: 2019-06-21
Owner Cmmt* | bar: R2 IMP
| CV | OL1-2K32-1553 | USC 36M FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
Rev. | bar: R2 IFI to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-04-01; R2 IFI: 2019-04-02
[6 empty] | Issue Actual | R2 IFI: 2019-04-01; R2 IFI: 2019-04-02
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01222; R2 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1555 | USC 36M Recycle Furnace Steel Inspection Door Lance Door and Access Door Details |  | Class 2 | Purpose** | IFR: IFI; R2 IFI: IFI; R2 IFI: IMP; R2 IFD: IMP
[6 empty] | Rev. | IFR: A; R2 IFI: A; R2 IFI: 0; R2 IFD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-09; R2 IFI: 2019-04-10; R2 IFI: 2019-05-29; R2 IFD: 2019-05-30
[6 empty] | Issue Actual | IFR: 2019-04-09; R2 IFI: 2019-04-10; R2 IFI: 2019-05-29; R2 IFD: 2019-05-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01293; R2 IFI: TPSK-LSPA1-T-CV-01293; R2 IFI: TPSK-LSPA1-T-CV-01765; R2 IFD: TPSK-LSPA1-T-CV-01765
[6 empty] | Return Date | R2 IFD: 2019-06-21
Owner Cmmt* | bar: R2 IFD
| CV | OL1-2K32-1560 | USC 36M FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
Rev. | bar: R2 IFI to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Issue Actual | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01293; R2 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1561 | USC 36M FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1562 | USC 36M Recycle Furnace Steel Access Door Davit Details |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02227
Return Date
Owner Cmmt*
| CV | OL1-2K32-1563 | USC 36M Recycle Furnace Steel Access Door Davit Details |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-24
[6 empty] | Issue Actual | IFR: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02248
Return Date
Owner Cmmt*
| CV | OL1-2K32-1580 | USC 36M FURNACE STEEL BREECHING PLAN AND ELEVATIONS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
Rev. | bar: R2 IFI to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Issue Actual | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01293; R2 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1581 | USC 36M FURNACE STEEL BREECHING SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
Rev. | bar: R2 IFI to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Issue Actual | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01293; R2 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1582 | USC 36M FURNACE STEEL DUCT PLAN AND ELEVATIONS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
Rev. | bar: R2 IFI to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Issue Actual | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01293; R2 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1583 | USC 36M FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1584 | USC 36M FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1585 | USC 36M FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1586 | USC 36M FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1587 | USC 36M FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1600 | STEEL FOR STRUCTURE 10-STR-2C03 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1601 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
[6 empty] | Rev. | R2 IFI: 0; R2 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-05-06; R2 IFI: 2019-05-07
[6 empty] | Issue Actual | R2 IFI: 2019-05-06; R2 IFI: 2019-05-07
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01584; R2 IFI: TPSK-LSPA1-T-CV-01584
[6 empty] | Return Date | R2 IFI: 2019-06-21
Owner Cmmt* | bar: R2 IFI
| CV | OL1-2K32-1602 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
[6 empty] | Rev. | R2 IFI: 0; R2 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-05-06; R2 IFI: 2019-05-07
[6 empty] | Issue Actual | R2 IFI: 2019-05-06; R2 IFI: 2019-05-07
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01584; R2 IFI: TPSK-LSPA1-T-CV-01584
[6 empty] | Return Date | R2 IFI: 2019-06-21
Owner Cmmt* | bar: R2 IFI
| CV | OL1-2K32-1603 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
[6 empty] | Rev. | R2 IFI: 0; R2 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-05-06; R2 IFI: 2019-05-07
[6 empty] | Issue Actual | R2 IFI: 2019-05-06; R2 IFI: 2019-05-07
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01584; R2 IFI: TPSK-LSPA1-T-CV-01584
[6 empty] | Return Date | R2 IFI: 2019-06-21
Owner Cmmt* | bar: R2 IFI
| CV | OL1-2K32-1604 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1605 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1606 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1607 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1608 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1609 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1610 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1611 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1612 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1613 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1614 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1615 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1616 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1617 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1618 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1619 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1620 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1621 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1622 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1623 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1631 | USC 36M FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1632 | USC 36M FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1640 | STEEL FOR STRUCTURE 10-STR-2C05 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1641 | USC 36M FURNACE STEEL ID FAN BOLTING PLAN |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1651 | USC 36M FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1660 | STEEL FOR STRUCTURE 10-SHT-2B01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1680 | STEEL FOR STRUCTURE 10-SHT-1B01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1700 | STEEL FOR STRUCTURE 10-STR-0P01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1701 | USC 36M FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1702 | USC 36M FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1703 | USC 36M FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1704 | USC 36M FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1705 | USC 36M FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1706 | USC 36M FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1707 | USC 36M FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1708 | USC 36M FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1720 | STEEL FOR STRUCTURE 10-STR-2A01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-04-30; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1721 | Steel Structure For 10-STR-2A01 |  | Class 2 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1740 | STEEL FOR STRUCTURE 10-STR-2A02 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1760 | STEEL FOR STRUCTURE 10-STR-2A03 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1780 | STEEL FOR STRUCTURE 10-STR-2D01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1800 | STEEL FOR STRUCTURE 10-STR-2D02 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1820 | STEEL FOR STRUCTURE 10-STR-2D03 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1840 | STEEL FOR STRUCTURE 10-STR-2D04 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1901 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1902 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1903 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1904 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1905 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1906 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1907 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1908 | USC 36M FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1909 | USC 36M FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1910 | USC 36M FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1911 | USC 36M FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1912 | USC 36M FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1913 | USC 36M FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1914 | USC 36M FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1940 | STEEL FOR TOOL ROOM OPERATION |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2100 | STEEL FOR STRUCTURE 10-SHT-2D01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2101 | Steel Structure For Shelter 10-SHT-2D01 - Plans |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2102 | Steel Structure For Shelter 10-SHT-2D01 - Plan & Details |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2103 | Steel Structure For Shelter 10-SHT-2D01 - Plans |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2104 | Steel Structure For Shelter 10-SHT-2D01 - Elevations |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2105 | Steel Structure For Shelter 10-SHT-2D01 - Elevations |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2120 | STEEL FOR STRUCTURE 10-SHT-2D02 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-04-30; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2121 | Steel Structure For 10-SHT-2D02 |  | Class 2 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2140 | STEEL FOR STRUCTURE 10-STR-2C01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2160 | STEEL FOR STRUCTURE 10-STR-2C02 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2161 | FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2162 | FURNACE STEEL MOMENT CONNECTION DETAIL AND MISCELLANEOUS DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2163 | FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2164 | FURNACE STEEL STANDARD FLOOR - TOE PLATE DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2180 | STEEL FOR STRUCTURE 10-STR-2C04 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2304 | FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
Rev. | bar: R2 IFI to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-03-20; R2 IFD: 2019-04-10
[6 empty] | Revised Plan | R2 IFI: 2019-04-11; R2 IFI: 2019-04-12
[6 empty] | Issue Actual | R2 IFI: 2019-04-11; R2 IFI: 2019-04-12
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01321; R2 IFI: TPSK-LSPA1-T-CV-01321
Return Date
Owner Cmmt*
| CV | OL1-2K32-2500 | USC 132U & 36M FURNACE GENERAL NOTES & ABBREVIATIONS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
Rev. | bar: R2 IFI to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-04-01; R2 IFI: 2019-04-02
[6 empty] | Issue Actual | R2 IFI: 2019-04-01; R2 IFI: 2019-04-02
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01222; R2 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2501 | USC 132U & 36M FURNACE STEEL FOUNDATION PLAN & LOADING DIAGRAM |  | Class 3 | Purpose** | IFR | IFI | IFI | IFD | IFF | IMP | IMP
[6 empty] | Rev. | R2 IFI: 0; R2 IFI: 0; R2 IMP: 1; R2 IMP: 1
[6 empty] | Issue Plan | IFR: 2019-05-07; R2 IFD: 2019-06-05; R2 IFF: 2019-06-05
[6 empty] | Revised Plan | R2 IFI: 2019-05-08; R2 IFI: 2019-05-09; R2 IMP: 2019-05-29; R2 IMP: 2019-05-30
[6 empty] | Issue Actual | R2 IFI: 2019-05-08; R2 IFI: 2019-05-09; R2 IMP: 2019-05-29; R2 IMP: 2019-05-30
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01618; R2 IFI: TPSK-LSPA1-T-CV-01618; R2 IMP: TPSK-LSPA1-T-CV-01765; R2 IMP: TPSK-LSPA1-T-CV-01765
[6 empty] | Return Date | R2 IFI: 2019-07-01
Owner Cmmt* | bar: R2 IFI
| CV | OL1-2K32-2502 | USC 132U & 36M FURNACE STEEL BASE PLATE DETAILS |  | Class 3 | Purpose** | IFR | IFI | IFI | IFD | IFF | IMP | IMP | IMP | IMP | IMP
[6 empty] | Rev. |  | A | A |  |  | 0 | 0 | 1 | 1 | 2
[6 empty] | Issue Plan | IFR: 2019-05-07; R1 IFD: 2019-06-05; R1 IFF: 2019-06-05
[6 empty] | Revised Plan |  | 2019-04-01 | 2019-04-02 |  |  | 2019-05-08 | 2019-05-09 | 2019-05-29 | 2019-05-30 | 2019-07-23
[6 empty] | Issue Actual |  | 2019-04-01 | 2019-04-02 |  |  | 2019-05-08 | 2019-05-09 | 2019-05-29 | 2019-05-30 | 2019-07-23
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222 | TPSK-LSPA1-T-CV-01222 |  |  | TPSK-LSPA1-T-CV-01616 | TPSK-LSPA1-T-CV-01616 | TPSK-LSPA1-T-CV-01765 | TPSK-LSPA1-T-CV-01765 | TPSK-LSPA1-T-CV-02229
[6 empty] | Return Date | R1 IMP: 2019-07-01
Owner Cmmt* | bar: R1 IMP
| CV | OL1-2K32-2511 | USC 132U FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Issue Actual | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01222; R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2512 | USC 132U FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Issue Actual | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01222; R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2513 | USC 132U FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D2 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Issue Actual | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01222; R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2514 | USC 132U FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Issue Actual | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01222; R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2515 | USC 132U FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Issue Actual | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01222; R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2516 | USC 132U FURNACE STEEL SHADOW BOX DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Issue Actual | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01222; R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2517 | USC 132U FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Issue Actual | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01222; R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2518 | USC 132U FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Issue Actual | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01222; R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2519 | USC 132U FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Issue Actual | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01222; R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2520 | USC 132U FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-09; R1 IFI: 2019-04-10
[6 empty] | Issue Actual | IFI: 2019-04-09; R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01293; R1 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2521 | USC 132U FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-09; R1 IFI: 2019-04-10
[6 empty] | Issue Actual | IFI: 2019-04-09; R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01293; R1 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2522 | USC 132U FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148-2 1/2 & EL 221-10 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Issue Actual | IFI: 2019-04-01; R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01222; R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2523 | USC 132U FURNACE STEEL END WALL TUBE SHEET ELEVATION |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2524 | USC 132U FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-09; R1 IFI: 2019-04-10
[6 empty] | Issue Actual | IFI: 2019-04-09; R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01293; R1 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2525 | USC 132U FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-09; R1 IFI: 2019-04-10
[6 empty] | Issue Actual | IFI: 2019-04-09; R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01293; R1 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2526 | USC 132U FURNACE STEEL CONVECTION SECTION HEADER BOX ELEVATIONS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2527 | USC 132U FURNACE STEEL CONVECTION SECTION HEADER BOX DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-09; R1 IFI: 2019-04-10
[6 empty] | Issue Actual | IFI: 2019-04-09; R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01293; R1 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2528 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE A2 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2529 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE B2 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2530 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE C2 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2531 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D2 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2532 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D0 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2533 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2534 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2535 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2536 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2537 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2538 | USC 132U FURNACE STEEL CONVECTION SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2539 | USC 132U FURNACE STEEL CROSSOVER LIMIT STOP DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2540 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2541 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-10; R1 IFI: 2019-04-11
[6 empty] | Issue Actual | IFI: 2019-04-10; R1 IFI: 2019-04-11
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01308; R1 IFI: TPSK-LSPA1-T-CV-01308
Return Date
Owner Cmmt*
| CV | OL1-2K32-2542 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2543 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2544 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2545 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2546 | USC 132U FURNACE STEEL NAME PLATE |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
[6 empty] | Rev. | IFI: 0; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2018-12-04
[6 empty] | Issue Actual | R1 IFI: 2018-12-04
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-ME-00423; R1 IFI: TPSK-LSPA1-T-ME-00423
Return Date
Owner Cmmt*
| CV | OL1-2K32-2550 | USC 132U FURNACE STEEL STACK AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-04-09; R1 IFI: 2019-04-10
[6 empty] | Issue Actual | IFI: 2019-04-09; R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-CV-01293; R1 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2551 | USC 132U FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFI: IFI; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: IFI to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | IFI: 2019-01-30; R1 IFI: 2019-01-31
[6 empty] | Issue Actual | IFI: 2019-01-30; R1 IFI: 2019-01-31
[6 empty] | Transmittal no. | IFI: TPSK-LSPA1-T-ME-00767; R1 IFI: TPSK-LSPA1-T-ME-00767
[6 empty] | Return Date | IFI: 2019-02-21; R1 IFI: 2019-02-21
Owner Cmmt* | bar: IFI to R1 IFI
| CV | OL1-2K32-2552 | USC 132U FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  | Class 3 | Purpose** | IFR | IFI | IFI | IFD | IFF | IMP | IMP | IMP
[6 empty] | Rev. |  | A | A |  |  | 0 | 0 | 1
[6 empty] | Issue Plan | IFR: 2018-09-18; R2 IFD: 2018-12-07; R2 IFF: 2019-01-31
[6 empty] | Revised Plan |  | 2019-04-01 | 2019-04-02 |  |  | 2019-05-21 | 2019-05-23 | 2019-07-23
[6 empty] | Issue Actual |  | 2019-04-01 | 2019-04-02 |  |  | 2019-05-21 | 2019-05-23 | 2019-07-23
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222 | TPSK-LSPA1-T-CV-01222 |  |  | TPSK-LSPA1-T-CV-01709 | TPSK-LSPA1-T-CV-01709 | TPSK-LSPA1-T-CV-02223
[6 empty] | Return Date | R2 IMP: 2019-06-21
Owner Cmmt* | bar: R2 IMP
| CV | OL1-2K32-2553 | USC 132U FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
Rev. | bar: R2 IFI to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-04-01; R2 IFI: 2019-04-02
[6 empty] | Issue Actual | R2 IFI: 2019-04-01; R2 IFI: 2019-04-02
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01222; R2 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2555 | USC 132U Cracking Furnace Steel Inspection Door Lance Door and Access Door Details |  | Class 2 | Purpose** | IFR: IFI; R2 IFI: IFI; R2 IFI: IMP; R2 IFD: IMP
[6 empty] | Rev. | IFR: A; R2 IFI: A; R2 IFI: 0; R2 IFD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-10; R2 IFI: 2019-04-11; R2 IFI: 2019-05-29; R2 IFD: 2019-05-30
[6 empty] | Issue Actual | IFR: 2019-04-10; R2 IFI: 2019-04-11; R2 IFI: 2019-05-29; R2 IFD: 2019-05-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01308; R2 IFI: TPSK-LSPA1-T-CV-01308; R2 IFI: TPSK-LSPA1-T-CV-01765; R2 IFD: TPSK-LSPA1-T-CV-01765
[6 empty] | Return Date | R2 IFD: 2019-06-21
Owner Cmmt* | bar: R2 IFD
| CV | OL1-2K32-2560 | USC 132U FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
Rev. | bar: R2 IFI to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Issue Actual | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01293; R2 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2561 | USC 132U FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2562 | USC 132U Cracking Furnace Steel Access Door Davit Details |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02236
Return Date
Owner Cmmt*
| CV | OL1-2K32-2563 | USC 132U Recycle Furnace Steel Access Door Davit Details |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-24
[6 empty] | Issue Actual | IFR: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02248
Return Date
Owner Cmmt*
| CV | OL1-2K32-2580 | USC 132U FURNACE STEEL BREECHING PLAN AND ELEVATIONS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
Rev. | bar: R2 IFI to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Issue Actual | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01293; R2 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2581 | USC 132U FURNACE STEEL BREECHING SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
Rev. | bar: R2 IFI to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Issue Actual | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01293; R2 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2582 | USC 132U FURNACE STEEL DUCT PLAN AND ELEVATIONS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
Rev. | bar: R2 IFI to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Issue Actual | R2 IFI: 2019-04-09; R2 IFI: 2019-04-10
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01293; R2 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2583 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2584 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2585 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2586 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2587 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2601 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
[6 empty] | Rev. | R2 IFI: 0; R2 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-05-06; R2 IFI: 2019-05-07; R2 IFD: 2019-10-09
[6 empty] | Issue Actual | R2 IFI: 2019-05-06; R2 IFI: 2019-05-07
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01584; R2 IFI: TPSK-LSPA1-T-CV-01584
[6 empty] | Return Date | R2 IFI: 2019-06-21
Owner Cmmt* | bar: R2 IFI
| CV | OL1-2K32-2602 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
[6 empty] | Rev. | R2 IFI: 0; R2 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-05-06
[6 empty] | Issue Actual | R2 IFI: 2019-05-06
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01584; R2 IFI: TPSK-LSPA1-T-CV-01584
[6 empty] | Return Date | R2 IFI: 2019-06-21
Owner Cmmt* | bar: R2 IFI
| CV | OL1-2K32-2603 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI; R2 IFD: IFC
[6 empty] | Rev. | R2 IFI: 0; R2 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFD: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-05-06; R2 IFI: 2019-05-07
[6 empty] | Issue Actual | R2 IFI: 2019-05-06; R2 IFI: 2019-05-07
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01584; R2 IFI: TPSK-LSPA1-T-CV-01584
[6 empty] | Return Date | R2 IFI: 2019-06-21
Owner Cmmt* | bar: R2 IFI
| CV | OL1-2K32-2604 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2605 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2606 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2607 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2608 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2609 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2610 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2611 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2612 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2613 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2614 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2615 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2616 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2617 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2618 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2619 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2620 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2621 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2622 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2623 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2631 | USC 132U FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2632 | USC 132U FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2641 | USC 132U FURNACE STEEL ID FAN BOLTING PLAN |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2651 | USC 132U FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2659 | USC 132U & 36M FURNACE STEEL MOMENT CONNECTION DETAIL & MISCELLANEOUS DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2660 | USC 132U & 36M FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2661 | USC 36M Recycle Furnace and 132U Cracking Furnaces Steel Platform and TOE Details |  | Class 2 | Purpose** | IFR: IMP; R2 IFI: IMP
[6 empty] | Rev. | IFR: 0; R2 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-06; R2 IFI: 2019-05-07
[6 empty] | Issue Actual | IFR: 2019-05-06; R2 IFI: 2019-05-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01585; R2 IFI: TPSK-LSPA1-T-CV-01585
[6 empty] | Return Date | R2 IFI: 2019-06-21
Owner Cmmt* | bar: R2 IFI
| CV | OL1-2K32-2701 | USC 132U FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2702 | USC 132U FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2703 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2704 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2705 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2706 | USC 132U FURNACE STEEL STAIR TOWER PLANS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2707 | USC 132U FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2708 | USC 132U FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2801 | USC FURNACE STEEL ELEVATOR ACCESS PLATFORM |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2802 | USC FURNACE STEEL ELEVATOR PLANS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2803 | USC FURNACE STEEL ELEVATOR PLANS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2804 | USC FURNACE STEEL ELEVATOR PLANS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2805 | USC FURNACE STEEL ELEVATOR PLANS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2901 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2902 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2903 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2904 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2905 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2906 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2907 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2908 | USC 132U FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2909 | USC 132U FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2910 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2911 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2912 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2913 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2914 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-09-02; R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3080 | STEEL FOR STRUCTURE 10-STR-1B01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R2 IFI: 2020-07-24; R2 IFI: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7000 | STEEL FOR PIPE RACK 10-PRK-0P01 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7001 | Steel For Pipe Rack 10-PRK-0P01- Plans |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7002 | Steel For Pipe Rack 10-PRK-0P01 - Plans |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7003 | Steel For Pipe Rack 10-PRK-0P01 - Plans |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7004 | Steel For Pipe Rack 10-PRK-0P01 - Elevations |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7005 | Steel For Pipe Rack 10-PRK-0P01 - Elevations |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7006 | Steel For Pipe Rack 10-PRK-0P01 - Elevations |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7007 | Steel For Pipe Rack 10-PRK-0P01 - Elevations - Stair |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7008 | Steel For Pipe Rack 10-PRK-0P01 - Details |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7100 | STEEL FOR PIPE RACK 10-PRK-0P02 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7101 | Steel For Piperack 10-PRK-0P02 - Plans- |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7102 | Steel For Piperack 10-PRK-0P02 (Plans) |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7103 | Steel For Piperack 10-PRK-0P02 - Plans - |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7104 | Steel For Piperack 10-PRK-0P02 - Plans And Section - |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7105 | Steel For Piperack 10-PRK-0P02 - Elevations - |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7106 | Steel For Piperack 10-PRK-0P02 - Elevations - |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7107 | Steel For Piperack 10-PRK-0P02 - Elevations - |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7108 | Steel For Piperack 10-PRK-0P02 - Elevations - |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7109 | Steel For Piperack 10-PRK-0P02 - Details - |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7200 | STEEL FOR PIPE RACK 10-PRK-0P03 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R2 IFI: 2020-02-01; R2 IFI: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R2 IFI: 2020-02-03; R2 IFI: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7201 | Steel For Pipe Rack 10-PRK-0P03 - Plans |  | Class 2 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28
[6 empty] | Revised Plan | IFR: 2019-11-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7202 | Steel For Pipe Rack 10-PRK-0P03 - Plans |  | Class 2 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28
[6 empty] | Revised Plan | IFR: 2019-11-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7203 | Steel For Pipe Rack 10-PRK-0P03 - Elevations - Plans |  | Class 2 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28
[6 empty] | Revised Plan | IFR: 2019-11-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7204 | Steel For Pipe Rack 10-PRK-0P03 - Elevations |  | Class 2 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28
[6 empty] | Revised Plan | IFR: 2019-11-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7205 | Steel For Pipe Rack 10-PRK-0P03 - Elevations |  | Class 2 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28
[6 empty] | Revised Plan | IFR: 2019-11-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7206 | Steel For Pipe Rack 10-PRK-0P03 - Elevations |  | Class 2 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28
[6 empty] | Revised Plan | IFR: 2019-11-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7207 | Steel For Pipe Rack 10-PRK-0P03 - Elevations - Stair |  | Class 2 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28
[6 empty] | Revised Plan | IFR: 2019-11-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7208 | Steel For Pipe Rack 10-PRK-0P03 - Details |  | Class 2 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28
[6 empty] | Revised Plan | IFR: 2019-11-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7380 | Steel Structure For 10-T-2040 |  | Class 2 | Purpose** | IFR: IFC; R2 IFI: IFC1; R2 IFI: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-26; R2 IFI: 2020-06-10; R2 IFI: 2020-07-25
[6 empty] | Revised Plan | IFR: 2020-02-26; R2 IFI: 2020-06-10; R2 IFI: 2020-07-25
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7480 | Steel Railing For Protection Of Basin 10-PIT-2190 |  | Class 2 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-07
[6 empty] | Revised Plan | IFR: 2019-09-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7520 | Steel Structures for Concrete Basin 10-PIT-2392 |  | Class 2 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8260 | Steel For Structure 10-STR-2B03 |  | Class 2 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8261 | Steel For Structure 10-STR-2B03 |  | Class 2 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K33 Shop Detail Drawings
Category Code: K34 Foundation for equipment, basin, cooling tower, supports and miscellaneous
| CV | OL1-2K34-0007 | FOUNDATION FOR 10-D-5200 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0008 | FOUNDATION FOR 10-E-5200 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-07; R2 IFI: 2019-03-08
[6 empty] | Issue Actual | IFR: 2019-03-07; R2 IFI: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01004; R2 IFI: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0009 | FOUNDATION FOR 10-E-5210 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034; R2 IFI: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0015 | FOUNDATION FOR 10-D-5150 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0016 | FOUNDATION FOR 10-D-2160 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | R2 IFI: 2019-01-28
[6 empty] | Issue Actual | R2 IFI: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00734; R2 IFI: TPSK-LSPA1-T-CV-00734
[6 empty] | Return Date | IFR: 2019-03-27; R2 IFI: 2019-03-27
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0020 | FOUNDATION FOR 10-E-2136 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-07; R2 IFI: 2019-03-08
[6 empty] | Issue Actual | IFR: 2019-03-07; R2 IFI: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01004; R2 IFI: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0023 | FOUNDATION FOR 10-E-2166 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-07; R2 IFI: 2019-03-08
[6 empty] | Issue Actual | IFR: 2019-03-07; R2 IFI: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01004; R2 IFI: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0024 | FOUNDATION FOR 10-E-2146 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0026 | FOUNDATION FOR 10-E-2026 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0027 | FOUNDATION FOR 10-E-2048 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-06; R2 IFI: 2019-02-06
[6 empty] | Issue Actual | IFR: 2019-02-06; R2 IFI: 2019-02-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00807; R2 IFI: TPSK-LSPA1-T-CV-00807
[6 empty] | Return Date | IFR: 2019-03-18; R2 IFI: 2019-03-18
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0042 | FOUNDATION FOR 10-T-2330 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0043 | FOUNDATION FOR 10-D-2410A/B/C |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034; R2 IFI: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0044 | FOUNDATION FOR 10-D-2435 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034; R2 IFI: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0046 | FOUNDATION FOR 10-D-2240 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034; R2 IFI: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0047 | FOUNDATION FOR 10-D-2245 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034; R2 IFI: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0048 | FOUNDATION FOR 10-D-2445 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034; R2 IFI: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0049 | FOUNDATION FOR 10-D-2455 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-11; R2 IFI: 2019-02-11
[6 empty] | Issue Actual | IFR: 2019-02-11; R2 IFI: 2019-02-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00833; R2 IFI: TPSK-LSPA1-T-CV-00833
[6 empty] | Return Date | IFR: 2019-05-31; R2 IFI: 2019-05-31
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0050 | FOUNDATION FOR 10-D-2220 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034; R2 IFI: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0055 | FOUNDATION FOR 10-D-2310 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-08; R2 IFI: 2019-02-08
[6 empty] | Issue Actual | IFR: 2019-02-08; R2 IFI: 2019-02-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00826; R2 IFI: TPSK-LSPA1-T-CV-00826
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFI: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0057 | FOUNDATION FOR 10-D-2316 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-06; R2 IFI: 2019-02-06
[6 empty] | Issue Actual | IFR: 2019-02-06; R2 IFI: 2019-02-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00807; R2 IFI: TPSK-LSPA1-T-CV-00807
[6 empty] | Return Date | IFR: 2019-03-18; R2 IFI: 2019-03-18
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0059 | FOUNDATION FOR 10-D-2330 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-06; R2 IFI: 2019-02-06
[6 empty] | Issue Actual | IFR: 2019-02-06; R2 IFI: 2019-02-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00807; R2 IFI: TPSK-LSPA1-T-CV-00807
[6 empty] | Return Date | IFR: 2019-03-18; R2 IFI: 2019-03-18
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0074 | FOUNDATION FOR 10-D-2305 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-08; R2 IFI: 2019-02-08
[6 empty] | Issue Actual | IFR: 2019-02-08; R2 IFI: 2019-02-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00826; R2 IFI: TPSK-LSPA1-T-CV-00826
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFI: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0076 | FOUNDATION FOR 10-E-2630 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-07; R2 IFI: 2019-03-08
[6 empty] | Issue Actual | IFR: 2019-03-07; R2 IFI: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01004; R2 IFI: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0095 | FOUNDATION FOR 10-T-2640 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | R2 IFI: 2019-03-20
[6 empty] | Issue Actual | R2 IFI: 2019-03-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01105; R2 IFI: TPSK-LSPA1-T-CV-01105
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0099 | FOUNDATION FOR 10-T-2520 AND 10-D-2520 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | R2 IFI: 2019-01-28
[6 empty] | Issue Actual | R2 IFI: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00728; R2 IFI: TPSK-LSPA1-T-CV-00728
[6 empty] | Return Date | IFR: 2019-03-27; R2 IFI: 2019-03-27
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0105 | FOUNDATION FOR 10-D-2815 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | R2 IFI: 2019-01-28
[6 empty] | Issue Actual | R2 IFI: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00734; R2 IFI: TPSK-LSPA1-T-CV-00734
[6 empty] | Return Date | IFR: 2019-03-27; R2 IFI: 2019-03-27
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0108 | FOUNDATION FOR 10-D-2645 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-06; R2 IFI: 2019-02-06
[6 empty] | Issue Actual | IFR: 2019-02-06; R2 IFI: 2019-02-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00807; R2 IFI: TPSK-LSPA1-T-CV-00807
[6 empty] | Return Date | IFR: 2019-03-18; R2 IFI: 2019-03-18
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0109 | FOUNDATION FOR 10-D-2555 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-20; R2 IFI: 2019-03-21
[6 empty] | Issue Actual | IFR: 2019-03-20; R2 IFI: 2019-03-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01104; R2 IFI: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0110 | FOUNDATION FOR 10-D-2550 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-20; R2 IFI: 2019-03-21
[6 empty] | Issue Actual | IFR: 2019-03-20; R2 IFI: 2019-03-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01104; R2 IFI: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0112 | FOUNDATION FOR 10-D-2575 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0114 | FOUNDATION FOR 10-D-2870 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | R2 IFI: 2019-01-28
[6 empty] | Issue Actual | R2 IFI: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00728; R2 IFI: TPSK-LSPA1-T-CV-00728
[6 empty] | Return Date | IFR: 2019-03-27; R2 IFI: 2019-03-27
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0115 | FOUNDATION FOR 10-D-2860 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | R2 IFI: 2019-01-28
[6 empty] | Issue Actual | R2 IFI: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00734; R2 IFI: TPSK-LSPA1-T-CV-00734
[6 empty] | Return Date | IFR: 2019-03-27; R2 IFI: 2019-03-27
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0116 | FOUNDATION FOR 10-D-2865 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0122 | FOUNDATION FOR 10-E-2576 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-07; R2 IFI: 2019-03-08
[6 empty] | Issue Actual | IFR: 2019-03-07; R2 IFI: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01004; R2 IFI: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0123 | FOUNDATION FOR 10-E-2645A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-13; R2 IFI: 2019-03-14
[6 empty] | Issue Actual | IFR: 2019-03-13; R2 IFI: 2019-03-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01042; R2 IFI: TPSK-LSPA1-T-CV-01042
[6 empty] | Return Date | IFR: 2019-06-04; R2 IFI: 2019-06-04
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0124 | FOUNDATION FOR 10-E-2502 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | R2 IFI: 2019-01-28
[6 empty] | Issue Actual | R2 IFI: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00728; R2 IFI: TPSK-LSPA1-T-CV-00728
[6 empty] | Return Date | IFR: 2019-03-27; R2 IFI: 2019-03-27
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0125 | FOUNDATION FOR 10-E-2515 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-07; R2 IFI: 2019-03-08
[6 empty] | Issue Actual | IFR: 2019-03-07; R2 IFI: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01004; R2 IFI: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0126 | FOUNDATION FOR 10-E-2546 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0127 | FOUNDATION FOR 10-E-2548 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0128 | FOUNDATION FOR 10-E-2545 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-30; R2 IFI: 2019-01-31
[6 empty] | Issue Actual | IFR: 2019-01-30; R2 IFI: 2019-01-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00763; R2 IFI: TPSK-LSPA1-T-CV-00763
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFI: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0130 | FOUNDATION FOR 10-E-2807 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0131 | FOUNDATION FOR 10-E-2809 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0132 | FOUNDATION FOR 10-E-2857 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-06; R2 IFI: 2019-02-06
[6 empty] | Issue Actual | IFR: 2019-02-06; R2 IFI: 2019-02-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00807; R2 IFI: TPSK-LSPA1-T-CV-00807
[6 empty] | Return Date | IFR: 2019-03-18; R2 IFI: 2019-03-18
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0133 | FOUNDATION FOR 10-E-2858 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0134 | FOUNDATION FOR 10-E-2856 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0135 | FOUNDATION FOR 10-E-2855 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-20; R2 IFI: 2019-03-21
[6 empty] | Issue Actual | IFR: 2019-03-20; R2 IFI: 2019-03-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01104; R2 IFI: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0136 | FOUNDATION FOR 10-E-2853 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00868; R2 IFI: TPSK-LSPA1-T-CV-00868
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0137 | FOUNDATION FOR 10-E-2852 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034; R2 IFI: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0139 | FOUNDATION FOR 10-E-2582 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IFR; R2 IFD: IFR
Rev. | bar: IFR to R2 IFD
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15; R2 IFI: 2019-02-21; R2 IFD: 2019-02-21
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15; R2 IFI: 2019-02-21; R2 IFD: 2019-02-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00903; R2 IFD: TPSK-LSPA1-T-CV-00903
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12; R2 IFI: 2019-04-12; R2 IFD: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFD
| CV | OL1-2K34-0140 | FOUNDATION FOR 10-E-2504 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-30; R2 IFI: 2019-01-31
[6 empty] | Issue Actual | IFR: 2019-01-30; R2 IFI: 2019-01-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00763; R2 IFI: TPSK-LSPA1-T-CV-00763
[6 empty] | Return Date | IFR: 2019-02-27; R2 IFI: 2019-02-27
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0146 | FOUNDATION FOR 10-E-2620 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034; R2 IFI: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0155 | FOUNDATION FOR 10-D-2610 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-11; R2 IFI: 2019-02-11
[6 empty] | Issue Actual | IFR: 2019-02-11; R2 IFI: 2019-02-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00833; R2 IFI: TPSK-LSPA1-T-CV-00833
[6 empty] | Return Date | IFR: 2019-05-31; R2 IFI: 2019-05-31
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0156 | FOUNDATION FOR 10-D-2600A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-11; R2 IFI: 2019-02-11
[6 empty] | Issue Actual | IFR: 2019-02-11; R2 IFI: 2019-02-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00833; R2 IFI: TPSK-LSPA1-T-CV-00833
[6 empty] | Return Date | IFR: 2019-05-31; R2 IFI: 2019-05-31
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0161 | FOUNDATION FOR 10-E-2636 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-07; R2 IFI: 2019-03-08
[6 empty] | Issue Actual | IFR: 2019-03-07; R2 IFI: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01004; R2 IFI: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0167 | FOUNDATION FOR 10-E-1020 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-01; R2 IFI: 2019-04-02
[6 empty] | Issue Actual | IFR: 2019-04-01; R2 IFI: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01208; R2 IFI: TPSK-LSPA1-T-CV-01208
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFI: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0168 | FOUNDATION FOR 10-E-1015 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034; R2 IFI: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0169 | FOUNDATION FOR 10-E-1001A/B |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Issue Actual | IFR: 2019-03-12; R2 IFI: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034; R2 IFI: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0191 | FOUNDATION FOR 10-E-2008A/B/C |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R2 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R2 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0202 | FOUNDATION FOR 10-E-1050 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-01; R2 IFI: 2019-04-02
[6 empty] | Issue Actual | IFR: 2019-04-01; R2 IFI: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01208; R2 IFI: TPSK-LSPA1-T-CV-01208
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFI: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-0267 | FOUNDATION FOR 10-D-5550 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R2 IFI: 2020-06-15
[6 empty] | Revised Plan | R2 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0306 | FOUNDATION FOR 10-D-5140 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | R2 IFI: 2019-01-28
[6 empty] | Issue Actual | R2 IFI: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00728; R2 IFI: TPSK-LSPA1-T-CV-00728
[6 empty] | Return Date | IFR: 2019-03-27; R2 IFI: 2019-03-27
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-1001 | Foundation for 10-T-2000 |  |  | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-20; R2 IFI: 2019-03-21
[6 empty] | Issue Actual | IFR: 2019-03-20; R2 IFI: 2019-03-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01104; R2 IFI: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-1020 | FOUNDATION FOR 10-T-2020 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-20; R2 IFI: 2019-03-21
[6 empty] | Issue Actual | IFR: 2019-03-20; R2 IFI: 2019-03-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01104; R2 IFI: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K34-1040 | FOUNDATION FOR 10-T-2100 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IFR; R2 IFD: IFR
Rev. | bar: IFR to R2 IFD
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-21; R2 IFI: 2019-02-21; R2 IFI: 2019-03-20; R2 IFD: 2019-03-21
[6 empty] | Issue Actual | IFR: 2019-02-21; R2 IFI: 2019-02-21; R2 IFI: 2019-03-20; R2 IFD: 2019-03-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00903; R2 IFI: TPSK-LSPA1-T-CV-00903; R2 IFI: TPSK-LSPA1-T-CV-01104; R2 IFD: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12; R2 IFI: 2019-04-12; R2 IFD: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFD
Category Code: K36 Major UG networks (Nuovo codice richiesto dal Cliente K26/K27) |  |  |  |  | Class 2 | Purpose**
| CV | OL1-2K36-0001 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138; R2 IFI: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K36-0002 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138; R2 IFI: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K36-0003 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138; R2 IFI: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K36-0004 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138; R2 IFI: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K36-0005 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138; R2 IFI: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K36-0006 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138; R2 IFI: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K36-0007 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138; R2 IFI: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K36-0008 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138; R2 IFI: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K36-0009 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138; R2 IFI: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K36-0010 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138; R2 IFI: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K36-0011 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138; R2 IFI: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K36-0012 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-25; R2 IFI: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138; R2 IFI: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K36-0013 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-03; R2 IFI: 2019-04-04
[6 empty] | Issue Actual | IFR: 2019-04-03; R2 IFI: 2019-04-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01240; R2 IFI: TPSK-LSPA1-T-CV-01240
[6 empty] | Return Date | IFR: 2019-06-05; R2 IFI: 2019-06-05
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K36-0014 | Major Underground Networks Zone 0C - Common Area |  |  | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-27; R2 IFI: 2019-03-28
[6 empty] | Issue Actual | IFR: 2019-03-27; R2 IFI: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01172; R2 IFI: TPSK-LSPA1-T-CV-01172
Return Date
Owner Cmmt*
| CV | OL1-2K36-1000 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-15; R2 IFI: 2019-03-18
[6 empty] | Issue Actual | IFR: 2019-03-15; R2 IFI: 2019-03-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01073; R2 IFI: TPSK-LSPA1-T-CV-01073
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
Category Code: K40 Topographic survey report
Category Code: K41 Hydrological survey report
Category Code: K42 Bathymetric survey report
Category Code: K43 Soil investigation & resisitivity report
| CV | OL1-2K43-0002 | TECHNICAL SPECIFICATION FOR GEOTECHNICAL INVESTIGATION |  |  | Purpose** | IFR | IFR | IFR | IFR | IMP
Rev. | bar: IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2018-10-08; R2 IFF: 2019-12-17
[6 empty] | Revised Plan | R2 IFF: 2019-12-17
[6 empty] | Issue Actual | IFR: 2018-10-09; R2 IFI: 2018-10-10; R2 IFI: 2018-10-17; R2 IFD: 2018-10-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00147; R2 IFI: TPSK-LSPA1-T-CV-00147; R2 IFI: TPSK-LSPA1-T-CV-00188; R2 IFD: TPSK-LSPA1-T-CV-00188
[6 empty] | Return Date | IFR: 2018-12-24; R2 IFI: 2018-12-24; R2 IFI: 2018-11-01; R2 IFD: 2018-11-01
Owner Cmmt* | bar: IFR to R2 IFD
| CV | OL1-2K43-0003 | Price List For Geotechnical Investigation |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IFR; R2 IFD: IFR
Rev. | bar: IFR to R2 IFD
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-09; R2 IFI: 2018-10-10; R2 IFI: 2018-10-17; R2 IFD: 2018-10-22
[6 empty] | Issue Actual | IFR: 2018-10-09; R2 IFI: 2018-10-10; R2 IFI: 2018-10-17; R2 IFD: 2018-10-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00147; R2 IFI: TPSK-LSPA1-T-CV-00147; R2 IFI: TPSK-LSPA1-T-CV-00188; R2 IFD: TPSK-LSPA1-T-CV-00188
[6 empty] | Return Date | IFR: 2018-12-24; R2 IFI: 2018-12-24; R2 IFI: 2018-11-01; R2 IFD: 2018-11-01
Owner Cmmt* | bar: IFR to R2 IFD
| CV | OL1-2K43-0004 | SOIL INVESTIGATION LAYOUT |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IMP
Rev. | bar: IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2018-10-08; R2 IFF: 2019-12-17
[6 empty] | Revised Plan | R2 IFF: 2019-12-17
[6 empty] | Issue Actual | IFR: 2018-10-09; R2 IFI: 2018-10-10; R2 IFI: 2018-10-12; R2 IFD: 2018-10-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00145; R2 IFI: TPSK-LSPA1-T-CV-00145; R2 IFI: TPSK-LSPA1-T-CV-00163; R2 IFD: TPSK-LSPA1-T-CV-00163
[6 empty] | Return Date | IFR: 2018-12-24; R2 IFI: 2018-12-24; R2 IFI: 2018-12-24; R2 IFD: 2018-12-24
Owner Cmmt* | bar: IFR to R2 IFD
| CV | OL1-2K43-0005 | Olefin Plant - Additional Ground Investigation - Phase 1 Platform at 4-5m HDD- Price List |  | Class 2 | Purpose** | IFR | IFI | IFI | IFI | IFI | IMP
Rev. | bar: R2 IFI to R2 IFF
[6 empty] | Issue Plan | IFR: 2019-05-31; R2 IMP: 2019-08-30
[6 empty] | Revised Plan | R2 IFI: 2019-06-11; R2 IFD: 2019-06-24; R2 IFF: 2019-06-24; R2 IMP: 2019-08-30
[6 empty] | Issue Actual | R2 IFI: 2019-06-11; R2 IFD: 2019-06-24; R2 IFF: 2019-06-24
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01861; R2 IFI: TPSK-LSPA1-T-CV-01861; R2 IFD: TPSK-LSPA1-T-CV-01963; R2 IFF: TPSK-LSPA1-T-CV-01963
[6 empty] | Return Date | R2 IFI: 2019-06-27
Owner Cmmt* | bar: R2 IFI
| CV | OL1-2K43-0006 | Olefins Plant - Additional Ground Investigation Phase 1 - Platform At +4-5m HDD- Layout Of Site Investigations |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IMP
Rev. | bar: IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2018-10-08; R2 IFF: 2019-12-17
[6 empty] | Revised Plan | R2 IFF: 2019-12-17
[6 empty] | Issue Actual | IFR: 2019-05-30; R2 IFI: 2019-05-31; R2 IFI: 2019-06-11; R2 IFD: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01768; R2 IFI: TPSK-LSPA1-T-CV-01768; R2 IFI: TPSK-LSPA1-T-CV-01853; R2 IFD: TPSK-LSPA1-T-CV-01853
[6 empty] | Return Date | R2 IFI: 2019-07-16
Owner Cmmt* | bar: R2 IFI
| CV | OL1-2K43-0007 | Olefin Plant - Additional Ground Investigation - Phase 2 Platform at 6-7m HDD- Price List |  | Class 2 | Purpose** | IFR | IFI | IFI | IFI | IFI | IMP
Rev. | bar: R2 IFI to R2 IFF
[6 empty] | Issue Plan | IFR: 2019-05-31; R2 IMP: 2019-08-30
[6 empty] | Revised Plan | R2 IFI: 2019-06-11; R2 IFD: 2019-06-24; R2 IFF: 2019-06-24; R2 IMP: 2019-08-30
[6 empty] | Issue Actual | R2 IFI: 2019-06-11; R2 IFD: 2019-06-24; R2 IFF: 2019-06-24
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-CV-01861; R2 IFI: TPSK-LSPA1-T-CV-01861; R2 IFD: TPSK-LSPA1-T-CV-01963; R2 IFF: TPSK-LSPA1-T-CV-01963
[6 empty] | Return Date | R2 IFI: 2019-06-27
Owner Cmmt* | bar: R2 IFI
| CV | OL1-2K43-0008 | Olefins Plant - Additional Ground Investigation Phase 2 -Platform At +6-7m HDD- Layout Of Site Investigations |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IMP
Rev. | bar: IFR to R2 IFI
[6 empty] | Issue Plan | IFR: 2018-10-08; R2 IFI: 2019-12-17
[6 empty] | Revised Plan | R2 IFI: 2019-12-17
[6 empty] | Issue Actual | IFR: 2019-05-30; R2 IFI: 2019-05-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01768; R2 IFI: TPSK-LSPA1-T-CV-01768
[6 empty] | Return Date | R2 IFI: 2019-07-16
Owner Cmmt* | bar: R2 IFI
| CV | OL1-2K43-0010 | Flare Area - Additional Ground Investigation Layout Of Site Investigations |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IMP
Rev. | bar: IFR to R2 IFI
[6 empty] | Issue Plan | IFR: 2018-10-08; R2 IFI: 2019-12-17
[6 empty] | Revised Plan | R2 IFI: 2019-12-17
[6 empty] | Issue Actual | IFR: 2019-05-30; R2 IFI: 2019-05-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01768; R2 IFI: TPSK-LSPA1-T-CV-01768
[6 empty] | Return Date | R2 IFI: 2019-07-16
Owner Cmmt* | bar: R2 IFI
Category Code: K50 Concrete Test Results
Category Code: K71 Appraisal Report for Consultancy Service
Category Code: K72 Appraisal Report for EPC Contractor Work
Category Code: K73 Appraisal Report for Vendor/Supplier
Category Code: K90 Vendor Document/drawings
Category Code: K91 Index/List
Category Code: K92 Procedures & Standards
| CV | OL1-2K92-0001 | GENERAL NOTES FOR UNDERGROUND WORKS |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IFC; R2 IFD: IFC
[6 empty] | Rev. | IFR: A; R2 IFI: A; R2 IFI: 0; R2 IFD: 0
[6 empty] | Issue Plan | IFR: 2018-09-24; R2 IFI: 2019-02-10
Revised Plan
[6 empty] | Issue Actual | IFR: 2018-09-25; R2 IFI: 2018-09-27; R2 IFI: 2019-02-01; R2 IFD: 2019-02-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00086; R2 IFI: TPSK-LSPA1-T-CV-00086; R2 IFI: TPSK-LSPA1-T-CV-00784; R2 IFD: TPSK-LSPA1-T-CV-00784
[6 empty] | Return Date | IFR: 2018-11-02; R2 IFI: 2018-11-02; R2 IFI: 2019-02-25; R2 IFD: 2019-02-25
Owner Cmmt* | bar: IFR to R2 IFD
| CV | OL1-2K92-0002 | GENERAL NOTES FOR PRECAST CONCRETE WORKS |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IFC; R2 IFD: IFC
[6 empty] | Rev. | IFR: A; R2 IFI: A; R2 IFI: 0; R2 IFD: 0
[6 empty] | Issue Plan | IFR: 2018-10-05; R2 IFI: 2019-01-30
Revised Plan
[6 empty] | Issue Actual | IFR: 2018-10-08; R2 IFI: 2018-10-08; R2 IFI: 2019-07-11; R2 IFD: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00137; R2 IFI: TPSK-LSPA1-T-CV-00137; R2 IFI: TPSK-LSPA1-T-CV-02119; R2 IFD: TPSK-LSPA1-T-CV-02119
[6 empty] | Return Date | IFR: 2018-12-24; R2 IFI: 2018-12-24
Owner Cmmt* | bar: IFR to R2 IFI
| CV | OL1-2K92-0003 | GENERAL NOTES FOR CONCRETE WORKS |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IFC; R2 IFD: IFC
[6 empty] | Rev. | IFR: A; R2 IFI: A; R2 IFI: 0; R2 IFD: 0
[6 empty] | Issue Plan | IFR: 2018-09-24; R2 IFI: 2019-01-15
Revised Plan
[6 empty] | Issue Actual | IFR: 2018-09-25; R2 IFI: 2018-09-27; R2 IFI: 2019-02-19; R2 IFD: 2019-02-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00086; R2 IFI: TPSK-LSPA1-T-CV-00086; R2 IFI: TPSK-LSPA1-T-CV-00886; R2 IFD: TPSK-LSPA1-T-CV-00886
[6 empty] | Return Date | IFR: 2018-11-02; R2 IFI: 2018-11-02; R2 IFI: 2019-03-27; R2 IFD: 2019-03-27
Owner Cmmt* | bar: IFR to R2 IFD
| CV | OL1-2K92-0004 | GENERAL NOTES FOR STEEL STRUCTURE |  | Class 2 | Purpose** | IFR | IFR | IFC | IFC | IFC | IFC
[6 empty] | Rev. | A | A | 0 | 0 | 2 | 2
[6 empty] | Issue Plan | IFR: 2018-09-24; R2 IFI: 2019-01-15
Revised Plan
[6 empty] | Issue Actual | 2018-09-25 | 2018-09-27 | 2019-02-15 | 2019-02-15 | 2019-07-03 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00086 | TPSK-LSPA1-T-CV-00086 | TPSK-LSPA1-T-CV-00867 | TPSK-LSPA1-T-CV-00867 | TPSK-LSPA1-T-CV-02054 | TPSK-LSPA1-T-CV-02054
[6 empty] | Return Date | IFR: 2018-11-02; R2 IFI: 2018-11-02; R2 IFI: 2019-03-27; R2 IFD: 2019-03-27
Owner Cmmt* | bar: IFR to R2 IFD
| CV | OL1-2K92-0005 | GENERAL NOTES FOR PILES |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IFC
Rev. | bar: IFR to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-02-28; R2 IFI: 2019-04-01
[6 empty] | Revised Plan | R2 IFI: 2019-08-21
[6 empty] | Issue Actual | IFR: 2019-03-19; R2 IFI: 2019-03-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01093; R2 IFI: TPSK-LSPA1-T-CV-01093
[6 empty] | Return Date | IFR: 2019-04-12; R2 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R2 IFI
Category Code: K93 Policy , Guidelines & Memo
Category Code: K94 Forms & Templates
Category Code: K95 Progress/Status Reports
Category Code: K97 Technical Specification/Price list for Architectural Works (Nuovo codice richiesto dal Cliente R02)
| CV | OL1-2K97-0001 | JOB CONST.SPEC.FOR BUILDINGS |  | Class 2 | Purpose** | IFR: IFQ; R2 IFI: IFQ
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | R2 IFI: 2019-03-21
[6 empty] | Issue Actual | R2 IFI: 2019-03-21
[6 empty] | Transmittal no. | IFR: 1117-TPSK-LSPA1-T-CV-01117; R2 IFI: 1117-TPSK-LSPA1-T-CV-01117
Return Date
Owner Cmmt*
Category Code: L01 Passive & Active Fire Protection Philosophy
| SE | OL1-2L01-0001 | FIREFIGHTING SYSTEM SPECIFICATION |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IMP; R2 IFD: IMP
[6 empty] | Rev. | IFR: A; R2 IFI: A; R2 IFI: 0; R2 IFD: 0
[6 empty] | Issue Plan | IFR: 2019-01-16; R2 IFI: 2019-02-13
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-02-01; R2 IFI: 2019-02-01; R2 IFI: 2019-07-05; R2 IFD: 2019-07-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-00782; R2 IFI: TPSK-LSPA1-T-PE-00782; R2 IFI: TPSK-LSPA1-T-SE-02079; R2 IFD: TPSK-LSPA1-T-SE-02079
[6 empty] | Return Date | IFR: 2019-03-18; R2 IFI: 2019-03-18
Owner Cmmt* | bar: IFR to R2 IFI
| SE | OL1-2L01-0002 | PASSIVE FIRE PROTECTION SPECIFICATION |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IMP
Rev. | bar: IFR to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-01-18; R2 IFI: 2019-02-15
Revised Plan
[6 empty] | Issue Actual | R2 IFI: 2019-01-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-00749; R2 IFI: TPSK-LSPA1-T-PE-00749
[6 empty] | Return Date | IFR: 2019-04-04; R2 IFI: 2019-04-04
Owner Cmmt* | bar: IFR to R2 IFI
| SE | OL1-2L01-0003 | Clean Agent Fire Extinguishing System |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IMP
Rev. | bar: IFR to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-01-16; R2 IFI: 2019-02-13
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-04-23; R2 IFI: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01441; R2 IFI: TPSK-LSPA1-T-SE-01441
Return Date
Owner Cmmt*
Category Code: L02 Active Fire Protection System
Category Code: L03 Firefighting equipment data sheet |  |  |  |  | Class 2 | Purpose**
| SE | OL1-2L03-0001 | Datasheet for Firefighting Equipment |  | Class 2 | Purpose** | IFR | IFR | IFQ | IFQ | IFP
Rev. | bar: IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-03-08; R2 IFI: 2019-07-19; R2 IFF: 2019-10-09
[6 empty] | Revised Plan | R2 IFF: 2019-10-09
[6 empty] | Issue Actual | IFR: 2019-06-10; R2 IFI: 2019-06-10; R2 IFI: 2019-07-08; R2 IFD: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01840; R2 IFI: TPSK-LSPA1-T-SE-01840; R2 IFI: TPSK-LSPA1-T-SE-02090; R2 IFD: TPSK-LSPA1-T-SE-02090
[6 empty] | Return Date | R2 IFI: 2019-07-08; R2 IFI: 2019-08-06
Owner Cmmt* | bar: R2 IFI to R2 IFI
| SE | OL1-2L03-1001 | Datasheet for Deluge System |  | Class 2 | Purpose** | IFR | IFR | IFQ | IFQ | IFP
Rev. | bar: IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-03-08; R2 IFI: 2019-07-19; R2 IFF: 2019-10-09
[6 empty] | Revised Plan | R2 IFF: 2019-10-09
[6 empty] | Issue Actual | IFR: 2019-06-03; R2 IFI: 2019-06-03; R2 IFI: 2019-07-08; R2 IFD: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01746; R2 IFI: TPSK-LSPA1-T-SE-01746; R2 IFI: TPSK-LSPA1-T-SE-02090; R2 IFD: TPSK-LSPA1-T-SE-02090
[6 empty] | Return Date | IFR: 2019-07-01; R2 IFI: 2019-08-06
Owner Cmmt* | bar: IFR; R2 IFI
| SE | OL1-2L03-2001 | Datasheet for Sprinkler System |  | Class 2 | Purpose** | IFR | IFR | IFQ | IFQ | IFP
Rev. | bar: IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-03-08; R2 IFI: 2019-07-19; R2 IFF: 2019-10-09
[6 empty] | Revised Plan | R2 IFF: 2019-10-09
[6 empty] | Issue Actual | IFR: 2019-06-03; R2 IFI: 2019-06-03; R2 IFI: 2019-07-08; R2 IFD: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01746; R2 IFI: TPSK-LSPA1-T-SE-01746; R2 IFI: TPSK-LSPA1-T-SE-02090; R2 IFD: TPSK-LSPA1-T-SE-02090
[6 empty] | Return Date | IFR: 2019-07-01; R2 IFI: 2019-08-06
Owner Cmmt* | bar: IFR; R2 IFI
| SE | OL1-2L03-3001 | Datasheet for Clean Agent Fire Extinguishing System |  | Class 2 | Purpose** | IFR | IFR | IFQ | IFQ | IFP
Rev. | bar: IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-03-08; R2 IFI: 2019-07-19; R2 IFF: 2019-10-09
[6 empty] | Revised Plan | R2 IFF: 2019-10-09
[6 empty] | Issue Actual | IFR: 2019-06-17; R2 IFI: 2019-06-17; R2 IFI: 2019-07-08; R2 IFD: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01899; R2 IFI: TPSK-LSPA1-T-SE-01899; R2 IFI: TPSK-LSPA1-T-SE-02088; R2 IFD: TPSK-LSPA1-T-SE-02088
[6 empty] | Return Date | IFR: 2019-07-08; R2 IFI: 2019-07-08; R2 IFD: 2019-07-29
Owner Cmmt* | bar: IFR to R2 IFI; R2 IFD
| SE | OL1-2L03-5001 | Datasheet for Safety & Life Saving Equipment |  | Class 2 | Purpose** | IFR | IFR | IFQ | IFQ | IFP
Rev. | bar: IFR to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-03-08; R2 IFI: 2019-07-19; R2 IFF: 2019-10-09
[6 empty] | Revised Plan | R2 IFF: 2019-10-09
[6 empty] | Issue Actual | IFR: 2019-05-21; R2 IFI: 2019-05-21; R2 IFI: 2019-07-08; R2 IFD: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01703; R2 IFI: TPSK-LSPA1-T-SE-01703; R2 IFI: TPSK-LSPA1-T-SE-02090; R2 IFD: TPSK-LSPA1-T-SE-02090
[6 empty] | Return Date | IFR: 2019-06-10; R2 IFI: 2019-06-10; R2 IFI: 2019-08-06
Owner Cmmt* | bar: IFR to R2 IFI
Category Code: L08 Noise General Specification
Category Code: L09 Noise Map
Category Code: L10 Acoustic Calculation Note
| SE | OL1-2L10-0001 | PLANT/EQUIPMENT NOISE CONTROL SPECIFICATION |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IMP
Rev. | bar: IFR to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-02-04; R2 IFI: 2019-02-28
[6 empty] | Revised Plan | R2 IFI: 2019-09-06
[6 empty] | Issue Actual | R2 IFI: 2018-12-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-00472; R2 IFI: TPSK-LSPA1-T-SE-00472
[6 empty] | Return Date | IFR: 2019-06-07; R2 IFI: 2019-06-07
Owner Cmmt* | bar: IFR to R2 IFI
| SE | OL1-2L10-0003 | ACUSTIC INSULATION SPECIFICATION |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IMP
Rev. | bar: IFR to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-02-04; R2 IFI: 2019-02-28
[6 empty] | Revised Plan | R2 IFI: 2019-09-06
[6 empty] | Issue Actual | IFR: 2019-04-24; R2 IFI: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01461; R2 IFI: TPSK-LSPA1-T-SE-01461
[6 empty] | Return Date | R2 IFI: 2019-06-25
Owner Cmmt* | bar: R2 IFI
Category Code: L11 Noise Rep
| SE | OL1-2L11-0001 | NOISE STUDY (NOISE MAP) |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-31; R2 IFI: 2019-09-20
[6 empty] | Revised Plan | IFR: 2019-09-30; R2 IFI: 2019-09-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L20 Fire system calculation
| SE | OL1-2L20-0001 | FIRE WATER DEMAND CALCULATION AND HYDRAULIC STUDY FOR FW NETWORK |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IMP
[6 empty] | Rev. | IFR: A; R2 IFI: A; R2 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-09-17; R2 IFI: 2020-03-06
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-03-07; R2 IFI: 2019-03-08; R2 IFI: 2019-07-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01006; R2 IFI: TPSK-LSPA1-T-SE-01006; R2 IFI: TPSK-LSPA1-T-SE-02200
[6 empty] | Return Date | IFR: 2019-04-09; R2 IFI: 2019-04-09
Owner Cmmt* | bar: IFR to R2 IFI
Category Code: L40 Active Fire Fighting Systems |  |  |  |  | Class 2 | Purpose**
| SE | OL1-2L40-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - SUBSTATION & FAR E |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-03-18
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-02205
Return Date
Owner Cmmt*
| SE | OL1-2L40-1000 | OVERALL FIRE WATER NETWORK DRAWING |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IMP
[6 empty] | Rev. | IFR: A; R2 IFI: A; R2 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-02-08; R2 IFI: 2019-05-08
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-03-29; R2 IFI: 2019-04-01; R2 IFI: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01198; R2 IFI: TPSK-LSPA1-T-SE-01198; R2 IFI: TPSK-LSPA1-T-SE-02172
[6 empty] | Return Date | IFR: 2019-05-14; R2 IFI: 2019-05-14
Owner Cmmt* | bar: IFR to R2 IFI
| SE | OL1-2L40-5701 | P&ID - FIRE WATER NETWORK (1/6) |  | Class As built | Purpose** | IFR | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to R2 IFI
[6 empty] | Issue Plan | 2019-05-09 |  |  | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFD: 2019-09-30; R2 IFF: 2020-04-06; R2 IMP: 2020-05-29; R2 IMP: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02; R2 IFI: 2019-05-09; R2 IFI: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520; R2 IFI: TPSK-LSPA1-T-SE-01622; R2 IFI: TPSK-LSPA1-T-SE-01622
[6 empty] | Return Date | IFR: 2019-06-16; R2 IFI: 2019-08-06
Owner Cmmt* | bar: IFR; R2 IFI
| SE | OL1-2L40-5702 | P&ID - FIRE WATER NETWORK (2/6) |  | Class As built | Purpose** | IFR | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to R2 IFI
[6 empty] | Issue Plan | 2019-05-09 |  |  | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFD: 2019-09-30; R2 IFF: 2020-04-06; R2 IMP: 2020-05-29; R2 IMP: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02; R2 IFI: 2019-05-09; R2 IFI: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520; R2 IFI: TPSK-LSPA1-T-SE-01622; R2 IFI: TPSK-LSPA1-T-SE-01622
[6 empty] | Return Date | IFR: 2019-06-16; R2 IFI: 2019-08-06
Owner Cmmt* | bar: IFR; R2 IFI
| SE | OL1-2L40-5703 | P&ID - FIRE WATER NETWORK (3/6) |  | Class As built | Purpose** | IFR | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to R2 IFI
[6 empty] | Issue Plan | 2019-05-09 |  |  | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFD: 2019-09-30; R2 IFF: 2020-04-06; R2 IMP: 2020-05-29; R2 IMP: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02; R2 IFI: 2019-05-09; R2 IFI: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520; R2 IFI: TPSK-LSPA1-T-SE-01622; R2 IFI: TPSK-LSPA1-T-SE-01622
[6 empty] | Return Date | IFR: 2019-06-16; R2 IFI: 2019-08-06
Owner Cmmt* | bar: IFR; R2 IFI
| SE | OL1-2L40-5704 | P&ID - FIRE WATER NETWORK (4/6) |  | Class As built | Purpose** | IFR | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to R2 IFI
[6 empty] | Issue Plan | 2019-05-09 |  |  | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFD: 2019-09-30; R2 IFF: 2020-04-06; R2 IMP: 2020-05-29; R2 IMP: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02; R2 IFI: 2019-05-09; R2 IFI: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520; R2 IFI: TPSK-LSPA1-T-SE-01622; R2 IFI: TPSK-LSPA1-T-SE-01622
[6 empty] | Return Date | IFR: 2019-06-16; R2 IFI: 2019-08-06
Owner Cmmt* | bar: IFR to R2 IFI
| SE | OL1-2L40-5705 | P&ID - FIRE WATER NETWORK (5/6) |  | Class As built | Purpose** | IFR | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to R2 IFI
[6 empty] | Issue Plan | 2019-05-09 |  |  | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFD: 2019-09-30; R2 IFF: 2020-04-06; R2 IMP: 2020-05-29; R2 IMP: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02; R2 IFI: 2019-05-09; R2 IFI: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520; R2 IFI: TPSK-LSPA1-T-SE-01622; R2 IFI: TPSK-LSPA1-T-SE-01622
[6 empty] | Return Date | IFR: 2019-06-16; R2 IFI: 2019-08-06
Owner Cmmt* | bar: IFR; R2 IFI
| SE | OL1-2L40-5706 | P&ID - FIRE WATER NETWORK (6/6) |  | Class As built | Purpose** | IFR | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to R2 IFI
[6 empty] | Issue Plan | 2019-05-09 |  |  | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFD: 2019-09-30; R2 IFF: 2020-04-06; R2 IMP: 2020-05-29; R2 IMP: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02; R2 IFI: 2019-05-09; R2 IFI: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520; R2 IFI: TPSK-LSPA1-T-SE-01622; R2 IFI: TPSK-LSPA1-T-SE-01622
[6 empty] | Return Date | IFR: 2019-06-16; R2 IFI: 2019-08-06
Owner Cmmt* | bar: IFR; R2 IFI
| SE | OL1-2L40-5707 | P&ID - DRY RISER SYSTEM |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5708 | P&ID - TYPICAL INSTALLATION OF FIRE PROTECTION EQUIPMENT |  | Class As built | Purpose** | IFR | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to R2 IFI
[6 empty] | Issue Plan | 2019-05-09 |  |  | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFD: 2019-09-30; R2 IFF: 2020-04-06; R2 IMP: 2020-05-29; R2 IMP: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02; R2 IFI: 2019-05-09; R2 IFI: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520; R2 IFI: TPSK-LSPA1-T-SE-01622; R2 IFI: TPSK-LSPA1-T-SE-01622
[6 empty] | Return Date | IFR: 2019-06-16; R2 IFI: 2019-08-06
Owner Cmmt* | bar: IFR; R2 IFI
| SE | OL1-2L40-5709 | P&ID - AUTOMATIC PNEUMATIC & ELECTRIC OPERATED DELUGE SYSTEM |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5710 | P&ID - AUTOMATIC ELECTRIC OPERATED DELUGE SYSTEM |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5711 | P&ID - MANUAL ELECTRIC OPERATED DELUGE SYSTEM |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5712 | P&ID - PRE-ACTION DOUBLE INTERLOCK SPRINKLER SYSTEM |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5713 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 0S |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5714 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2A |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5715 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2B |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5716 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2C (1/2) |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5717 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2C (2/2) |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5718 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2D (1/3) |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5719 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2D (2/3) |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5720 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2D (3/3) |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5721 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2E |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5722 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 3A (1/2) |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5723 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 3A (2/2) |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5724 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 3S |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5725 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 5F |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5726 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 5U |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5727 | P&ID - FIRE WATER CURTAIN SYSTEM - ZONE 1B |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5728 | P&ID - SPRINKLER SYSTEM - SUBSTATION E CABLE CELLAR |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5729 | P&ID - SPRINKLER SYSTEM - SUBSTATION C CABLE CELLAR |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5730 | P&ID - SPRINKLER SYSTEM - SUBSTATION F CABLE CELLAR |  | Class As built | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | R2 IFI: 2019-09-30; R2 IFI: 2020-04-06; R2 IFD: 2020-05-29; R2 IFF: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
Category Code: L41 Passive Fire Protection Drawings
Category Code: L42 Hazardous Area Classification |  |  |  |  | Class 2 | Purpose**
| SE | OL1-2L42-0001 | Hazardous Area Classification - Overall |  | Class As built | Purpose** | IFR: IFR; R2 IFI: IFA; R2 IFI: IFA
Rev. | bar: R2 IFI to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-03-20
[6 empty] | Revised Plan | R2 IFI: 2019-03-11; R2 IFI: 2019-03-12
[6 empty] | Issue Actual | R2 IFI: 2019-03-11; R2 IFI: 2019-03-12
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-SE-01015; R2 IFI: TPSK-LSPA1-T-SE-01015
[6 empty] | Return Date | R2 IFI: 2019-03-25; R2 IFI: 2019-03-25
Owner Cmmt* | bar: R2 IFI to R2 IFI
| SE | OL1-2L42-0002 | HAZARDOUS AREA CLASSIFICATION DRAWING, OLEFINS UNIT |  | Class 1 | Purpose** | IFR: IDD; R2 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0003 | HAZARDOUS AREA CLASSIFICATION DRAWING |  | Class 2 | Purpose** | IFR: IDD; R2 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0004 | Hazardous Area Classification - Zone 0S - Electrical Substation and Far E |  | Class As built | Purpose** | IFR: IFA; R2 IFI: IFA
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11; R2 IFI: 2019-03-12
[6 empty] | Issue Actual | IFR: 2019-03-11; R2 IFI: 2019-03-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01015; R2 IFI: TPSK-LSPA1-T-SE-01015
[6 empty] | Return Date | IFR: 2019-03-25; R2 IFI: 2019-03-25
Owner Cmmt* | bar: IFR to R2 IFI
| SE | OL1-2L42-0005 | HAZARDOUS AREA CLASSIFICATION DRAWING - COOLING WATER UNIT |  | Class 2 | Purpose** | IFR: IFA; R2 IFI: IFA
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11; R2 IFI: 2019-03-12
[6 empty] | Issue Actual | IFR: 2019-03-11; R2 IFI: 2019-03-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01015; R2 IFI: TPSK-LSPA1-T-SE-01015
[6 empty] | Return Date | IFR: 2019-03-25; R2 IFI: 2019-03-25
Owner Cmmt* | bar: IFR to R2 IFI
| SE | OL1-2L42-0006 | HAZARDOUS AREA CLASSIFICATION DRAWING - WASTE WATER TREATMENT UNIT |  | Class 2 | Purpose** | IFR: IDD; R2 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0007 | HAZARDOUS AREA CLASSIFICATION DRAWING - UTILITIES |  | Class 2 | Purpose** | IFR: IDD; R2 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0008 | HAZARDOUS AREA CLASSIFICATION DRAWING - FLARE UNIT |  | Class 2 | Purpose** | IFR: IDD; R2 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0009 | HAZARDOUS AREA CLASSIFICATION DRAWING - METERING STATION |  | Class 2 | Purpose** | IFR: IDD; R2 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0010 | HAZARDOUS AREA CLASSIFICATION DRAWING - FURNACES |  | Class 2 | Purpose** | IFR: IDD; R2 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0011 | HAZARDOUS AREA CLASSIFICATION DRAWING - FURNACES AND AUXILIARIES |  | Class 2 | Purpose** | IFR: IDD; R2 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0012 | HAZARDOUS AREA CLASSIFICATION DRAWING - QUENCH |  | Class 2 | Purpose** | IFR: IDD; R2 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0013 | HAZARDOUS AREA CLASSIFICATION DRAWING - C3 HYDROGENATION |  | Class 2 | Purpose** | IFR: IDD; R2 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0014 | HAZARDOUS AREA CLASSIFICATION DRAWING - PROCESS COLD COMPRESSORS |  | Class 2 | Purpose** | IFR: IDD; R2 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0015 | HAZARDOUS AREA CLASSIFICATION DRAWING - CRACKED GAS COMPRESSOR / DE-PROPANIZER / C2 HYDROGENATION |  | Class 2 | Purpose** | IFR: IDD; R2 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0016 | HAZARDOUS AREA CLASSIFICATION DRAWING - BUTADIENE EXTRACT UNIT |  | Class 2 | Purpose** | IFR: IDD; R2 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0017 | HAZARDOUS AREA CLASSIFICATION DRAWING - HOT FRACTIONATION / GHU UNIT |  | Class 2 | Purpose** | IFR: IDD; R2 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0018 | HAZARDOUS AREA CLASSIFICATION DRAWING |  | Class 2 | Purpose** | IFR: IDD; R2 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R2 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0020 | Hazardous Area Classification - Details |  | Class As built | Purpose** | IFR: IFR; R2 IFI: IFA; R2 IFI: IFA
Rev. | bar: R2 IFI to R2 IFI
[6 empty] | Issue Plan | IFR: 2019-03-20
[6 empty] | Revised Plan | R2 IFI: 2019-03-11; R2 IFI: 2019-03-12
[6 empty] | Issue Actual | R2 IFI: 2019-03-11; R2 IFI: 2019-03-12
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-SE-01015; R2 IFI: TPSK-LSPA1-T-SE-01015
[6 empty] | Return Date | R2 IFI: 2019-03-25; R2 IFI: 2019-03-25
Owner Cmmt* | bar: R2 IFI to R2 IFI
Category Code: L43 Risk Matrix
Category Code: L44 Life saving Equip & Escape Route Drawing
Category Code: L60 All project study and Report pertain to Loss control and Safety Process safety report; HAZOP Report; LOPA Report; PSSR Reports; Risk analysis dossiers; and and Project Response; |  |  |  |  | Class 2 | Purpose**
| SE | OL1-2L60-0051 | MSDS for Chemicals and Catalysts |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFI; R2 IFI: IFI
[6 empty] | Rev. | R2 IFI: 0; R2 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-01-03
[6 empty] | Revised Plan | R2 IFI: 2019-01-23
[6 empty] | Issue Actual | R2 IFI: 2019-01-23
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-SE-00707; R2 IFI: TPSK-LSPA1-T-SE-00707
Return Date
Owner Cmmt*
| SE | OL1-2L60-0211 | Recovery Process and Utilities Sections HAZOP Report |  | Class 2 | Purpose** | IFR: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L60-0231 | Recovery Process and Utilities Sections SIL Classification Report |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02393
Return Date
Owner Cmmt*
| SE | OL1-2L60-1001 | HAZARD & OPERABILITY STUDY (DETAIL DESIGN) REPORT |  | Class 3 | Purpose** | IFR: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-04
[6 empty] | Revised Plan | IFR: 2019-11-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L60-3001 | SIL CLASSIFICATION REPORT |  | Class 2 | Purpose** | IFR: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-10
[6 empty] | Revised Plan | IFR: 2020-03-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L62 Recommendation Monitoring System |  |  |  |  | Class 2 | Purpose**
| SE | OL1-2L62-0001 | HAZARD & OPERABILITY STUDY (FEED) CLOSEOUT REPORT |  | Class 2 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-10
[6 empty] | Revised Plan | IFR: 2019-09-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L62-1001 | HAZARD & OPERABILITY STUDY (DETAIL DESIGN) CLOSEOUT REPORT |  | Class 2 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-10
[6 empty] | Revised Plan | IFR: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L62-2001 | HAZARD & OPERABILITY STUDY (DETAIL DESIGN) CLOSEOUT REPORT |  | Class 2 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-10
[6 empty] | Revised Plan | IFR: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L63 Record of Survey
Category Code: L64 Report of audit
Category Code: L65 Hazardous Source Data
Category Code: L66 Register of Safety Devices |  |  |  |  | Class 2 | Purpose**
| SE | OL1-2L66-0001 | BILL OF MATERIAL FOR FIREFIGHTING AND SAFETY EQUIPMENT |  | Class 2 | Purpose** | IFR: IFQ; R2 IFI: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-05; R2 IFI: 2019-10-09
[6 empty] | Revised Plan | R2 IFI: 2019-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L67 Equipment Failure Information
Category Code: L70 Emergency Procedures Manual
Category Code: L71 Test Procedures
Category Code: L72 Loss Control and Safety procedure
Category Code: L81 Appraisal Report for Consultancy Service
Category Code: L82 Appraisal Report for EPC Contractor Work
Category Code: L83 Appraisal Report for Vendor/Supplier
Category Code: L90 Vendor Document/drawings
Category Code: L91 Index/List
Category Code: L92 Procedures & Standards
Category Code: L93 Policy , Guidelines & Memo
Category Code: L94 Forms & Templates
Category Code: L95 Progress/Status Reports
Category Code: M03 Mechanical datasheet
| ME | 0L1-2M03-2610 | Mechanical Equipment Datasheet - C3 Hydrog Arsine Guard Bed |  | Class 2 | Purpose** | IFR: Issue for Purchase; R2 IFI: IFP
[6 empty] | Rev. | IFR: 0; R2 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-24; R2 IFI: 2019-06-24
[6 empty] | Issue Actual | IFR: 2019-06-24; R2 IFI: 2019-06-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01966; R2 IFI: TPSK-LSPA1-T-ME-01966
[6 empty] | Return Date | IFR: 2019-07-16; R2 IFI: 2019-07-16
Owner Cmmt* | bar: IFR to R2 IFI
| ME | OL1-2M03-1000 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-1000 - LPG FEED DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFI to R2 IMP
[6 empty] | Issue Plan | IFR: 2019-04-08; R2 IFI: 2019-05-13
[6 empty] | Revised Plan | R2 IFD: 2018-12-13; R2 IFF: 2019-04-23; R2 IMP: 2019-04-24
[6 empty] | Issue Actual | R2 IFD: 2018-12-13; R2 IFF: 2019-04-23; R2 IMP: 2019-04-24
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-ME-00483; R2 IFD: TPSK-LSPA1-T-ME-00483; R2 IFF: TPSK-LSPA1-T-ME-01448; R2 IMP: TPSK-LSPA1-T-ME-01448
[6 empty] | Return Date | R2 IFI: 2019-01-22; R2 IFD: 2019-01-22; R2 IFF: 2019-06-18; R2 IMP: 2019-06-18
Owner Cmmt* | bar: R2 IFI to R2 IMP
| ME | OL1-2M03-1001 | MECHANICAL DATASHEET FOR API 560 INDUCED DRAFT FAN (36M FURNACE) |  | Class 2 | Purpose** | IFR | IFR | IFQ | IFP | IMP | IMP
[6 empty] | Rev. | IFR: A; R2 IFI: A; R2 IFF: 0; R2 IMP: 0
[6 empty] | Issue Plan | IFR: 2018-10-31; R2 IFI: 2018-11-05; R2 IFD: 2019-01-03
[6 empty] | Revised Plan | R2 IFF: 2019-03-11; R2 IMP: 2019-03-12
[6 empty] | Issue Actual | R2 IFI: 2018-10-31; R2 IFF: 2019-03-11; R2 IMP: 2019-03-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00247; R2 IFI: TPSK-LSPA1-T-ME-00247; R2 IFF: TPSK-LSPA1-T-ME-01021; R2 IMP: TPSK-LSPA1-T-ME-01021
[6 empty] | Return Date | R2 IFF: 2019-03-29; R2 IMP: 2019-03-29
Owner Cmmt* | bar: R2 IFF to R2 IMP
| ME | OL1-2M03-1002 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1000 - LPG VAPORIZER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFI to R2 IMP
[6 empty] | Issue Plan | IFR: 2019-04-15; R2 IFI: 2019-05-20
[6 empty] | Revised Plan | R2 IFD: 2019-01-22; R2 IFF: 2019-05-16; R2 IMP: 2019-05-17
[6 empty] | Issue Actual | R2 IFD: 2019-01-22; R2 IFF: 2019-05-16; R2 IMP: 2019-05-17
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-ME-00684; R2 IFD: TPSK-LSPA1-T-ME-00684; R2 IFF: TPSK-LSPA1-T-ME-01685; R2 IMP: TPSK-LSPA1-T-ME-01685
[6 empty] | Return Date | R2 IFI: 2019-02-11; R2 IFD: 2019-02-11; R2 IMP: 2019-06-21
Owner Cmmt* | bar: R2 IFI to R2 IFD; R2 IMP
| ME | OL1-2M03-1003 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1001 - LPG STEAM VAPORIZER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFI to R2 IMP
[6 empty] | Issue Plan | IFR: 2019-04-15; R2 IFI: 2019-05-20
[6 empty] | Revised Plan | R2 IFD: 2019-01-03; R2 IFF: 2019-02-27; R2 IMP: 2019-02-28
[6 empty] | Issue Actual | R2 IFD: 2019-01-03; R2 IFF: 2019-02-27; R2 IMP: 2019-02-28
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-ME-00573; R2 IFD: TPSK-LSPA1-T-ME-00573; R2 IFF: TPSK-LSPA1-T-ME-00946; R2 IMP: TPSK-LSPA1-T-ME-00946
[6 empty] | Return Date | R2 IFI: 2019-01-24; R2 IFD: 2019-01-24; R2 IFF: 2019-03-25; R2 IMP: 2019-03-25
Owner Cmmt* | bar: R2 IFI to R2 IMP
| ME | OL1-2M03-1005 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1005 - LPG FEED HEATER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFI to R2 IMP
[6 empty] | Issue Plan | IFR: 2019-04-15; R2 IFI: 2019-05-20
[6 empty] | Revised Plan | R2 IFD: 2019-01-03; R2 IFF: 2019-04-02; R2 IMP: 2019-04-03
[6 empty] | Issue Actual | R2 IFD: 2019-01-03; R2 IFF: 2019-04-02; R2 IMP: 2019-04-03
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-ME-00573; R2 IFD: TPSK-LSPA1-T-ME-00573; R2 IFF: TPSK-LSPA1-T-ME-01230; R2 IMP: TPSK-LSPA1-T-ME-01230
[6 empty] | Return Date | R2 IFI: 2019-01-24; R2 IFD: 2019-01-24; R2 IFF: 2019-05-09; R2 IMP: 2019-05-09
Owner Cmmt* | bar: R2 IFI to R2 IMP
| ME | OL1-2M03-1006 | Mechanical Equipment Data Sheet - 10-E-1006 - LPG Feed Steam Heater |  | Class 2 | Purpose** | IFP | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | 0 | A | A | B | B
Issue Plan
[6 empty] | Revised Plan | R2 IFI: 2019-03-19; R2 IFI: 2019-03-20; R2 IFD: 2019-04-15; R2 IFF: 2019-04-16
[6 empty] | Issue Actual | R2 IFI: 2019-03-19; R2 IFI: 2019-03-20; R2 IFD: 2019-04-15; R2 IFF: 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-02175 | TPSK-LSPA1-T-ME-01095 | TPSK-LSPA1-T-ME-01095 | TPSK-LSPA1-T-ME-01362 | TPSK-LSPA1-T-ME-01362
[6 empty] | Return Date | IFR: 2019-08-15; R2 IFI: 2019-04-11; R2 IFI: 2019-04-11
Owner Cmmt* | bar: IFR to R2 IFI
| ME | OL1-2M03-1015 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1015 - LPG SUPERHEATER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFI to R2 IMP
[6 empty] | Issue Plan | IFR: 2019-04-15; R2 IFI: 2019-05-20
[6 empty] | Revised Plan | R2 IFD: 2018-12-27; R2 IFF: 2019-03-01; R2 IMP: 2019-03-04
[6 empty] | Issue Actual | R2 IFD: 2018-12-27; R2 IFF: 2019-03-01; R2 IMP: 2019-03-04
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-ME-00571; R2 IFD: TPSK-LSPA1-T-ME-00571; R2 IFF: TPSK-LSPA1-T-ME-00971; R2 IMP: TPSK-LSPA1-T-ME-00971
[6 empty] | Return Date | R2 IFI: 2019-01-22; R2 IFD: 2019-01-22; R2 IFF: 2019-03-29; R2 IMP: 2019-03-29
Owner Cmmt* | bar: R2 IFI to R2 IMP
| ME | OL1-2M03-1020 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1020 - LIQUID FEED HEATER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFI to R2 IMP
[6 empty] | Issue Plan | IFR: 2019-04-15; R2 IFI: 2019-05-20
[6 empty] | Revised Plan | R2 IFD: 2019-01-17; R2 IFF: 2019-04-02; R2 IMP: 2019-04-03
[6 empty] | Issue Actual | R2 IFD: 2019-01-17; R2 IFF: 2019-04-02; R2 IMP: 2019-04-03
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-ME-00671; R2 IFD: TPSK-LSPA1-T-ME-00671; R2 IFF: TPSK-LSPA1-T-ME-01230; R2 IMP: TPSK-LSPA1-T-ME-01230
[6 empty] | Return Date | R2 IFI: 2019-02-11; R2 IFD: 2019-02-11; R2 IFF: 2019-05-09; R2 IMP: 2019-05-09
Owner Cmmt* | bar: R2 IFI to R2 IMP
| ME | OL1-2M03-1051 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1050 - C2 FEED SUPERHEATER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFI to R2 IMP
[6 empty] | Issue Plan | IFR: 2019-04-15; R2 IFI: 2019-05-20
[6 empty] | Revised Plan | R2 IFD: 2019-01-03; R2 IFF: 2019-03-01; R2 IMP: 2019-03-04
[6 empty] | Issue Actual | R2 IFD: 2019-01-03; R2 IFF: 2019-03-01; R2 IMP: 2019-03-04
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-ME-00573; R2 IFD: TPSK-LSPA1-T-ME-00573; R2 IFF: TPSK-LSPA1-T-ME-00961; R2 IMP: TPSK-LSPA1-T-ME-00961
[6 empty] | Return Date | R2 IFI: 2019-01-24; R2 IFD: 2019-01-24; R2 IFF: 2019-03-29; R2 IMP: 2019-03-29
Owner Cmmt* | bar: R2 IFI to R2 IMP
| ME | OL1-2M03-1105 | API Fired Heater Datasheet 10-H-1100 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IMP; R2 IFD: IMP
[6 empty] | Rev. | IFR: A; R2 IFI: A; R2 IFI: 0; R2 IFD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-15; R2 IFI: 2019-03-18; R2 IFI: 2019-04-25; R2 IFD: 2019-04-26
[6 empty] | Issue Actual | IFR: 2019-03-15; R2 IFI: 2019-03-18; R2 IFI: 2019-04-25; R2 IFD: 2019-04-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01084; R2 IFI: TPSK-LSPA1-T-ME-01084; R2 IFI: TPSK-LSPA1-T-ME-01486; R2 IFD: TPSK-LSPA1-T-ME-01486
[6 empty] | Return Date | R2 IFI: 2019-05-29; R2 IFD: 2019-05-29
Owner Cmmt* | bar: R2 IFI to R2 IFD
| ME | OL1-2M03-1113 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-11013 - PSV-1144 Outlet |  | Class 2 | Purpose** | IFR: IFQ; R2 IFI: IFQ
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; R2 IFI: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; R2 IFI: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02129; R2 IFI: TPSK-LSPA1-T-ME-02129
[6 empty] | Return Date | R2 IFI: 2019-08-01
Owner Cmmt* | bar: R2 IFI
| ME | OL1-2M03-1114 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-11014 - Start-up |  | Class 2 | Purpose** | IFR: IFQ; R2 IFI: IFQ
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; R2 IFI: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; R2 IFI: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02129; R2 IFI: TPSK-LSPA1-T-ME-02129
[6 empty] | Return Date | R2 IFI: 2019-08-01
Owner Cmmt* | bar: R2 IFI
| ME | OL1-2M03-1205 | API Fired Heater Datasheet 10-H-1200_1600 |  | Class 2 | Purpose** | IFR: IFR; R2 IFI: IFR; R2 IFI: IMP; R2 IFD: IMP
[6 empty] | Rev. | IFR: A; R2 IFI: A; R2 IFI: 0; R2 IFD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-15; R2 IFI: 2019-03-18; R2 IFI: 2019-04-25; R2 IFD: 2019-04-26
[6 empty] | Issue Actual | IFR: 2019-03-15; R2 IFI: 2019-03-18; R2 IFI: 2019-04-25; R2 IFD: 2019-04-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01084; R2 IFI: TPSK-LSPA1-T-ME-01084; R2 IFI: TPSK-LSPA1-T-ME-01486; R2 IFD: TPSK-LSPA1-T-ME-01486
[6 empty] | Return Date | R2 IFI: 2019-05-29; R2 IFD: 2019-05-29
Owner Cmmt* | bar: R2 IFI to R2 IFD
| ME | OL1-2M03-1213 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-12013/16013 - PSV-1244 Outlet |  | Class 2 | Purpose** | IFR: IFQ; R2 IFI: IFQ
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; R2 IFI: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; R2 IFI: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02129; R2 IFI: TPSK-LSPA1-T-ME-02129
[6 empty] | Return Date | R2 IFI: 2019-08-01
Owner Cmmt* | bar: R2 IFI
| ME | OL1-2M03-1214 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-12014/16014 - Start-up |  | Class 2 | Purpose** | IFR: IFQ; R2 IFI: IFQ
Rev. | bar: IFR to R2 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; R2 IFI: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; R2 IFI: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02129; R2 IFI: TPSK-LSPA1-T-ME-02129
[6 empty] | Return Date | R2 IFI: 2019-08-01
Owner Cmmt* | bar: R2 IFI
| ME | OL1-2M03-1911 | Mechanical Equipment Data Sheet - DMDS Bulk Storage Drum |  | Class 2 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFI to R2 IMP
[6 empty] | Issue Plan | IFR: 2019-04-08; R2 IFI: 2019-05-13
[6 empty] | Revised Plan | R2 IFD: 2019-01-28; R2 IFF: 2019-04-12; R2 IMP: 2019-04-15
[6 empty] | Issue Actual | R2 IFD: 2019-01-28; R2 IFF: 2019-04-12; R2 IMP: 2019-04-15
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-ME-00743; R2 IFD: TPSK-LSPA1-T-ME-00743; R2 IFF: TPSK-LSPA1-T-ME-01347; R2 IMP: TPSK-LSPA1-T-ME-01347
[6 empty] | Return Date | R2 IFI: 2019-02-21; R2 IFD: 2019-02-21; R2 IFF: 2019-05-20; R2 IMP: 2019-05-20
Owner Cmmt* | bar: R2 IFI to R2 IMP
| ME | OL1-2M03-1912 | Mechanical Equipment Data Sheet - DMDS Injection Drum |  | Class 2 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFI to R2 IMP
[6 empty] | Issue Plan | IFR: 2019-04-08; R2 IFI: 2019-05-13
[6 empty] | Revised Plan | R2 IFD: 2019-01-28; R2 IFF: 2019-04-12; R2 IMP: 2019-04-15
[6 empty] | Issue Actual | R2 IFD: 2019-01-28; R2 IFF: 2019-04-12; R2 IMP: 2019-04-15
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-ME-00744; R2 IFD: TPSK-LSPA1-T-ME-00744; R2 IFF: TPSK-LSPA1-T-ME-01347; R2 IMP: TPSK-LSPA1-T-ME-01347
[6 empty] | Return Date | R2 IFI: 2019-02-21; R2 IFD: 2019-02-21; R2 IFF: 2019-05-20; R2 IMP: 2019-05-20
Owner Cmmt* | bar: R2 IFI to R2 IMP
| ME | OL1-2M03-1913 | Mechanical Equipment Datasheet - DMDS Feed Injection Pump |  | Class 2 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFI to R2 IMP
[6 empty] | Issue Plan | IFR: 2018-12-27; R2 IFI: 2019-01-17
[6 empty] | Revised Plan | R2 IFI: 2019-02-01; R2 IFD: 2019-02-04; R2 IFF: 2019-03-15; R2 IMP: 2019-03-18
[6 empty] | Issue Actual | R2 IFI: 2019-02-01; R2 IFD: 2019-02-04; R2 IFF: 2019-03-15; R2 IMP: 2019-03-18
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-ME-00787; R2 IFD: TPSK-LSPA1-T-ME-00787; R2 IFF: TPSK-LSPA1-T-ME-01086; R2 IMP: TPSK-LSPA1-T-ME-01086
[6 empty] | Return Date | R2 IFI: 2019-02-21; R2 IFD: 2019-02-21; R2 IFF: 2019-04-02; R2 IMP: 2019-04-02
Owner Cmmt* | bar: R2 IFI to R2 IMP
| ME | OL1-2M03-1914 | Mechanical Equipment Datasheet - DMDS Presulfiding Injection Pump |  | Class 2 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFI to R2 IMP
[6 empty] | Issue Plan | IFR: 2018-12-27; R2 IFI: 2019-01-17
[6 empty] | Revised Plan | R2 IFI: 2019-02-01; R2 IFD: 2019-02-04; R2 IFF: 2019-03-15; R2 IMP: 2019-03-18
[6 empty] | Issue Actual | R2 IFI: 2019-02-01; R2 IFD: 2019-02-04; R2 IFF: 2019-03-15; R2 IMP: 2019-03-18
[6 empty] | Transmittal no. | R2 IFI: TPSK-LSPA1-T-ME-00787; R2 IFD: TPSK-LSPA1-T-ME-00787; R2 IFF: TPSK-LSPA1-T-ME-01086; R2 IMP: TPSK-LSPA1-T-ME-01086
[6 empty] | Return Date | R2 IFI: 2019-02-21; R2 IFD: 2019-02-21; R2 IFF: 2019-04-02; R2 IMP: 2019-04-02
Owner Cmmt* | bar: R2 IFI to R2 IMP
| ME | OL1-2M03-1950 | MECHANICAL EQUIPMENT DATA SHEET - 10-PK-1950 - DECOKE AIR COMPRESSOR PACKAGE |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  | A | A |  | C | B | B | C
[6 empty] | Issue Plan | IFR: 2018-09-13; IFD: 2018-10-11
[6 empty] | Revised Plan |  | 2018-09-13 | 2018-09-14 |  |  | 2018-10-11 | 2018-10-12 | 2018-11-01
[6 empty] | Issue Actual |  | 2018-09-13 | 2018-09-14 |  |  | 2018-10-11 | 2018-10-12 | 2018-11-01
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00050 | TPSK-LSPA1-T-ME-00050 |  | TPSK-LSPA1-T-ME-00261 | TPSK-LSPA1-T-ME-00161 | TPSK-LSPA1-T-ME-00161 | TPSK-LSPA1-T-ME-00261
[6 empty] | Return Date | IFA: 2018-10-02; IFA: 2018-10-02; IFQ: 2018-11-29; IFQ: 2018-11-29
Owner Cmmt* | bar: IFA to IFA; IFQ; IFQ
| ME | OL1-2M03-2000 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2000 - QUENCH OIL TOWER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-03-14; IFA: 2019-04-11
[6 empty] | Revised Plan | IFD: 2018-12-04; IFQ: 2019-02-06; IFQ: 2019-02-06
[6 empty] | Issue Actual | IFD: 2018-12-04; IFQ: 2019-02-06; IFQ: 2019-02-06
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00420; IFD: TPSK-LSPA1-T-ME-00420; IFQ: TPSK-LSPA1-T-ME-00801; IFQ: TPSK-LSPA1-T-ME-00801
[6 empty] | Return Date | IFA: 2018-12-27; IFD: 2018-12-27; IFQ: 2019-02-25; IFQ: 2019-02-25
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2001 | MECHANICAL DATASHEET FOR API 560 INDUCED DRAFT FAN (132SU FURNACE) |  | Class 2 | Purpose** | IFR | IFR | IFQ | IFP | IMP | IMP
[6 empty] | Rev. | IFR: A; IFA: A; IFQ: 0; IFQ: 0
[6 empty] | Issue Plan | IFR: 2018-10-31; IFA: 2018-11-05; IFD: 2019-01-03
[6 empty] | Revised Plan | IFQ: 2019-03-11; IFQ: 2019-03-12
[6 empty] | Issue Actual | IFA: 2018-10-31; IFQ: 2019-03-11; IFQ: 2019-03-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00247; IFA: TPSK-LSPA1-T-ME-00247; IFQ: TPSK-LSPA1-T-ME-01021; IFQ: TPSK-LSPA1-T-ME-01021
[6 empty] | Return Date | IFQ: 2019-03-29; IFQ: 2019-03-29
Owner Cmmt* | bar: IFQ to IFQ
| ME | OL1-2M03-2002 | ELEVATOR DATA SHEET |  | Class 2 | Purpose** | IFR | IFR | IFQ | IFP | IMP | IMP | IMP
[6 empty] | Rev. | A | A |  |  | 0 | 0 | 1
[6 empty] | Issue Plan | IFR: 2018-12-19; IFA: 2018-12-19; IFD: 2019-02-19
[6 empty] | Revised Plan | IFQ: 2019-06-07; IFQ: 2019-06-10; IFQ: 2019-07-24
[6 empty] | Issue Actual | IFA: 2019-01-18; IFQ: 2019-06-07; IFQ: 2019-06-10; IFQ: 2019-07-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00681 | TPSK-LSPA1-T-ME-00681 |  |  | TPSK-LSPA1-T-ME-01832 | TPSK-LSPA1-T-ME-01832 | TPSK-LSPA1-T-ME-02246
[6 empty] | Return Date | IFR: 2019-02-08; IFA: 2019-02-08; IFQ: 2019-07-03
Owner Cmmt* | bar: IFR to IFA; IFQ
| ME | OL1-2M03-2006 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2006 - QUENCH OIL PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | B | A | B | C | C
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan | IFQ: 2018-10-26; IFQ: 2018-12-11; IFQ: 2019-03-27; IFQ: 2019-03-28
[6 empty] | Issue Actual | IFQ: 2018-10-26; IFQ: 2018-12-11; IFQ: 2019-03-27; IFQ: 2019-03-28
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00235 | TPSK-LSPA1-T-ME-00476 | TPSK-LSPA1-T-ME-00235 | TPSK-LSPA1-T-ME-00476 | TPSK-LSPA1-T-ME-01173 | TPSK-LSPA1-T-ME-01173
[6 empty] | Return Date |  |  | 2018-11-19 | 2019-01-16 | 2018-11-19 | 2019-01-16 | 2019-04-22 | 2019-04-22
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2010 | Mechanical Equipment Data sheet - Quench Oil Filter |  | Class 2 | Purpose** | IFR: IFR; IFA: IFD; IFA: IFQ; IFD: IFQ
Rev. | bar: IFA to IFD
[6 empty] | Issue Plan | IFR: 2019-02-25; IFA: 2019-03-18
[6 empty] | Revised Plan | IFD: 2019-01-11
[6 empty] | Issue Actual | IFD: 2019-01-11
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00639; IFD: TPSK-LSPA1-T-ME-00639
[6 empty] | Return Date | IFA: 2019-01-30; IFD: 2019-01-30
Owner Cmmt* | bar: IFA to IFD
| ME | OL1-2M03-2014 | Mechanical Equipment Datasheet - QO Pump Purge Oil Filter |  | Class 2 | Purpose** | IFR: IFR; IFA: IFD; IFA: IFQ; IFD: IFQ
Rev. | bar: IFA to IFD
[6 empty] | Issue Plan | IFR: 2019-02-25; IFA: 2019-03-18
[6 empty] | Revised Plan | IFD: 2019-01-11
[6 empty] | Issue Actual | IFD: 2019-01-11
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00639; IFD: TPSK-LSPA1-T-ME-00639
[6 empty] | Return Date | IFA: 2019-01-30; IFD: 2019-01-30
Owner Cmmt* | bar: IFA to IFD
| ME | OL1-2M03-2015 | Mechanical Equipment Data Sheet - 10-E-2008 - LS2 Steam Generators |  | Class 2 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | IFD: 2019-01-14; IFQ: 2019-03-29; IFQ: 2019-04-01
[6 empty] | Issue Actual | IFD: 2019-01-14; IFQ: 2019-03-29; IFQ: 2019-04-01
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00643; IFD: TPSK-LSPA1-T-ME-00643; IFQ: TPSK-LSPA1-T-ME-01205; IFQ: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | IFA: 2019-02-04; IFD: 2019-02-04; IFQ: 2019-05-02; IFQ: 2019-05-02
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2020 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2020 - LIGHT FUEL OIL STRIPPER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-03-14; IFA: 2019-04-11
[6 empty] | Revised Plan | IFD: 2018-12-10; IFQ: 2019-02-06; IFQ: 2019-02-06
[6 empty] | Issue Actual | IFD: 2018-12-10; IFQ: 2019-02-06; IFQ: 2019-02-06
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00447; IFD: TPSK-LSPA1-T-ME-00447; IFQ: TPSK-LSPA1-T-ME-00801; IFQ: TPSK-LSPA1-T-ME-00801
[6 empty] | Return Date | IFA: 2019-01-27; IFD: 2019-01-27; IFQ: 2019-02-25; IFQ: 2019-02-25
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2024 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2026 - LIGHT FUEL OIL PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan | IFD: 2018-12-10; IFQ: 2019-02-01; IFQ: 2019-02-04
[6 empty] | Issue Actual | IFD: 2018-12-10; IFQ: 2019-02-01; IFQ: 2019-02-04
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00457; IFD: TPSK-LSPA1-T-ME-00457; IFQ: TPSK-LSPA1-T-ME-00786; IFQ: TPSK-LSPA1-T-ME-00786
[6 empty] | Return Date | IFA: 2018-12-27; IFD: 2018-12-27; IFQ: 2019-02-21; IFQ: 2019-02-21
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2025 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2026 - CRACKER BOTTOMS PRODUCT FILTER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-02-25; IFA: 2019-03-18
[6 empty] | Revised Plan | IFD: 2019-01-11; IFQ: 2019-03-25; IFQ: 2019-03-26
[6 empty] | Issue Actual | IFD: 2019-01-11; IFQ: 2019-03-25; IFQ: 2019-03-26
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00639; IFD: TPSK-LSPA1-T-ME-00639; IFQ: TPSK-LSPA1-T-ME-01141; IFQ: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | IFA: 2019-01-30; IFD: 2019-01-30; IFQ: 2019-04-11; IFQ: 2019-04-11
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2026 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2026 - FUEL OIL PRODUCT COOLER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | IFD: 2019-01-22; IFQ: 2019-04-10; IFQ: 2019-04-11
[6 empty] | Issue Actual | IFD: 2019-01-22; IFQ: 2019-04-10; IFQ: 2019-04-11
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00683; IFD: TPSK-LSPA1-T-ME-00683; IFQ: TPSK-LSPA1-T-ME-01307; IFQ: TPSK-LSPA1-T-ME-01307
[6 empty] | Return Date | IFA: 2019-02-11; IFD: 2019-02-11
Owner Cmmt* | bar: IFA to IFD
| ME | OL1-2M03-2028 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2028 - FO PUMP PURGE OIL FILTER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-02-25; IFA: 2019-03-18
[6 empty] | Revised Plan | IFD: 2019-01-11; IFQ: 2019-03-25; IFQ: 2019-03-26
[6 empty] | Issue Actual | IFD: 2019-01-11; IFQ: 2019-03-25; IFQ: 2019-03-26
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00639; IFD: TPSK-LSPA1-T-ME-00639; IFQ: TPSK-LSPA1-T-ME-01141; IFQ: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | IFA: 2019-01-30; IFD: 2019-01-30; IFQ: 2019-04-11; IFQ: 2019-04-11
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2040 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2040 - HEAVY FUEL OIL STRIPPER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | B | A | A | B | C | C
[6 empty] | Issue Plan | IFR: 2019-03-14; IFA: 2019-04-11
[6 empty] | Revised Plan | IFQ: 2018-11-28; IFQ: 2018-12-05; IFQ: 2019-02-06; IFQ: 2019-02-06
[6 empty] | Issue Actual | IFQ: 2018-11-28; IFQ: 2018-12-05; IFQ: 2019-02-06; IFQ: 2019-02-06
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00418 | TPSK-LSPA1-T-ME-00387 | TPSK-LSPA1-T-ME-00387 | TPSK-LSPA1-T-ME-00418 | TPSK-LSPA1-T-ME-00815 | TPSK-LSPA1-T-ME-00815
[6 empty] | Return Date |  |  | 2018-12-27 | 2018-12-17 | 2018-12-17 | 2018-12-27 | 2019-02-21 | 2019-02-21
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2046 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2046 - HEAVY FUEL OIL PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan |  |  |  | 2018-12-10 | 2019-02-01 | 2019-02-04 | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual |  |  |  | 2018-12-10 | 2019-02-01 | 2019-02-04 | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00457 | TPSK-LSPA1-T-ME-00457 | TPSK-LSPA1-T-ME-00786 | TPSK-LSPA1-T-ME-00786 | TPSK-LSPA1-T-ME-01493 | TPSK-LSPA1-T-ME-01493
[6 empty] | Return Date |  |  | 2018-12-27 | 2018-12-27 | 2019-02-21 | 2019-02-21 | 2019-06-18 | 2019-06-18
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2048 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2048 - HEAVY FUEL OIL PRODUCT COOLER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | IFD: 2019-01-22; IFQ: 2019-04-11; IFQ: 2019-04-12
[6 empty] | Issue Actual | IFD: 2019-01-22; IFQ: 2019-04-11; IFQ: 2019-04-12
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00683; IFD: TPSK-LSPA1-T-ME-00683; IFQ: TPSK-LSPA1-T-ME-01324; IFQ: TPSK-LSPA1-T-ME-01324
[6 empty] | Return Date | IFA: 2019-02-11; IFD: 2019-02-11; IFQ: 2019-05-20; IFQ: 2019-05-20
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2049 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2048 - HEAVY FUEL OIL FILTERS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-02-25; IFA: 2019-03-18
[6 empty] | Revised Plan | IFD: 2019-01-11; IFQ: 2019-03-26; IFQ: 2019-03-27
[6 empty] | Issue Actual | IFD: 2019-01-11; IFQ: 2019-03-26; IFQ: 2019-03-27
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00639; IFD: TPSK-LSPA1-T-ME-00639; IFQ: TPSK-LSPA1-T-ME-01157; IFQ: TPSK-LSPA1-T-ME-01157
[6 empty] | Return Date | IFA: 2019-01-30; IFD: 2019-01-30; IFQ: 2019-04-11; IFQ: 2019-04-11
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2070 | Mechanical Data Sheet For General Purpose Steam Turbines PT-2006 A Quench Oil Pump Turbne |  | Class 2 | Purpose** | IFR: IMP; IFA: IMP
[6 empty] | Rev. | IFR: 0; IFA: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFA: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFA: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02130; IFA: TPSK-LSPA1-T-ME-02130
[6 empty] | Return Date | IFA: 2019-08-01
Owner Cmmt* | bar: IFA
| ME | OL1-2M03-2090 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2090 - QUENCH OIL DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-01-21; IFA: 2019-02-08
[6 empty] | Revised Plan | IFD: 2019-01-11; IFQ: 2019-04-02; IFQ: 2019-04-03
[6 empty] | Issue Actual | IFD: 2019-01-11; IFQ: 2019-04-02; IFQ: 2019-04-03
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00638; IFD: TPSK-LSPA1-T-ME-00638; IFQ: TPSK-LSPA1-T-ME -1226; IFQ: TPSK-LSPA1-T-ME -1226
[6 empty] | Return Date | IFA: 2019-01-31; IFD: 2019-01-31; IFQ: 2019-05-16; IFQ: 2019-05-16
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2091 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2090 - QUENCH OIL DRAIN DRUM PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan |  |  |  | 2018-12-13 | 2019-04-02 | 2019-04-03 | 2019-04-15 | 2019-04-16
[6 empty] | Issue Actual |  |  |  | 2018-12-13 | 2019-04-02 | 2019-04-03 | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00494 | TPSK-LSPA1-T-ME-00494 | TPSK-LSPA1-T-ME-01227 | TPSK-LSPA1-T-ME-01227 | TPSK-LSPA1-T-ME-01363 | TPSK-LSPA1-T-ME-01363
[6 empty] | Return Date | IFA: 2019-01-14; IFD: 2019-01-14
Owner Cmmt* | bar: IFA to IFD
| ME | OL1-2M03-2100 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2100 - QUENCH WATER TOWER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-03-14; IFA: 2019-04-11
[6 empty] | Revised Plan | IFD: 2018-12-07; IFQ: 2019-02-06; IFQ: 2019-02-06
[6 empty] | Issue Actual | IFD: 2018-12-07; IFQ: 2019-02-06; IFQ: 2019-02-06
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00443; IFD: TPSK-LSPA1-T-ME-00443; IFQ: TPSK-LSPA1-T-ME -00803; IFQ: TPSK-LSPA1-T-ME -00803
[6 empty] | Return Date | IFA: 2018-12-27; IFD: 2018-12-27; IFQ: 2019-02-25; IFQ: 2019-02-25
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2101 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2100 - QUENCH WATER COOLER |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFQ | IFQ
Rev. | bar: IFA to IFA; IFQ to IFQ
[6 empty] | Issue Plan | IFR: 2018-10-20; IFD: 2018-10-20
[6 empty] | Revised Plan | IFA: 2018-09-17; IFA: 2018-09-18; IFQ: 2018-10-10; IFQ: 2018-10-11
[6 empty] | Issue Actual | IFA: 2018-09-17; IFA: 2018-09-18; IFQ: 2018-10-10; IFQ: 2018-10-11
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00058; IFA: TPSK-LSPA1-T-ME-00058; IFQ: TPSK-LSPA1-T-ME-00154; IFQ: TPSK-LSPA1-T-ME-00154
[6 empty] | Return Date | IFA: 2018-09-28; IFA: 2018-09-28; IFQ: 2018-11-07; IFQ: 2018-11-07
Owner Cmmt* | bar: IFA to IFA; IFQ to IFQ
| ME | OL1-2M03-2104 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2105 - QUENCH OIL REFLUX FILTER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-02-25; IFA: 2019-03-18
[6 empty] | Revised Plan | IFD: 2019-01-11; IFQ: 2019-03-25; IFQ: 2019-03-26
[6 empty] | Issue Actual | IFD: 2019-01-11; IFQ: 2019-03-25; IFQ: 2019-03-26
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00639; IFD: TPSK-LSPA1-T-ME-00639; IFQ: TPSK-LSPA1-T-ME-01141; IFQ: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | IFA: 2019-01-30; IFD: 2019-01-30; IFQ: 2019-04-11; IFQ: 2019-04-11
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2105 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2105 - QUENCH OIL REFLUX PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan | IFD: 2018-12-10; IFQ: 2019-04-08; IFQ: 2019-04-09
[6 empty] | Issue Actual | IFD: 2018-12-10; IFQ: 2019-04-08; IFQ: 2019-04-09
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00457; IFD: TPSK-LSPA1-T-ME-00457; IFQ: TPSK-LSPA1-T-ME-01279; IFQ: TPSK-LSPA1-T-ME-01279
[6 empty] | Return Date | IFA: 2018-12-27; IFD: 2018-12-27; IFQ: 2019-05-16; IFQ: 2019-05-16
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2106 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2106 - QUENCH WATER PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | B | A | A | B | C | C
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan | IFQ: 2018-10-27; IFQ: 2018-12-11; IFQ: 2019-03-27; IFQ: 2019-03-28
[6 empty] | Issue Actual | IFQ: 2018-10-27; IFQ: 2018-12-11; IFQ: 2019-03-27; IFQ: 2019-03-28
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00476 | TPSK-LSPA1-T-ME-00236 | TPSK-LSPA1-T-ME-00236 | TPSK-LSPA1-T-ME-00476 | TPSK-LSPA1-T-ME-01173 | TPSK-LSPA1-T-ME-01173
[6 empty] | Return Date |  |  | 2019-01-16 | 2018-11-19 | 2018-11-19 | 2019-01-16 | 2019-04-22 | 2019-04-22
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2110 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2110 - INTERCEPTION DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan | IFD: 2019-01-22; IFQ: 2019-06-10; IFQ: 2019-06-11
[6 empty] | Issue Actual | IFD: 2019-01-22; IFQ: 2019-06-10; IFQ: 2019-06-11
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00685; IFD: TPSK-LSPA1-T-ME-00685; IFQ: TPSK-LSPA1-T-ME-01850; IFQ: TPSK-LSPA1-T-ME-01850
[6 empty] | Return Date | IFA: 2019-02-15; IFD: 2019-02-15; IFQ: 2019-07-08
Owner Cmmt* | bar: IFA to IFD; IFQ
| ME | OL1-2M03-2120 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2120 - DISTILLTATE STRIPPER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-03-14; IFA: 2019-04-11
[6 empty] | Revised Plan | IFD: 2018-12-20; IFQ: 2019-02-12; IFQ: 2019-02-12
[6 empty] | Issue Actual | IFD: 2018-12-20; IFQ: 2019-02-12; IFQ: 2019-02-12
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00546; IFD: TPSK-LSPA1-T-ME-00546; IFQ: TPSK-LSPA1-T-ME-00840; IFQ: TPSK-LSPA1-T-ME-00840
[6 empty] | Return Date | IFA: 2019-01-22; IFD: 2019-01-22; IFQ: 2019-02-28; IFQ: 2019-02-28
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2125 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2125 - DISTILLATE STRIPPER REBOILER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | IFD: 2019-01-07; IFQ: 2019-04-10; IFQ: 2019-04-11
[6 empty] | Issue Actual | IFD: 2019-01-07; IFQ: 2019-04-10; IFQ: 2019-04-11
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00584; IFD: TPSK-LSPA1-T-ME-00584; IFQ: TPSK-LSPA1-T-ME-01302; IFQ: TPSK-LSPA1-T-ME-01302
[6 empty] | Return Date | IFA: 2019-01-24; IFD: 2019-01-24; IFQ: 2019-06-05; IFQ: 2019-06-05
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2126 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2126 - DISTILLATE STRIPPER BOTTOMS PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan |  |  |  | 2018-12-05 | 2019-03-20 | 2019-03-21 | 2019-04-22 | 2019-04-23
[6 empty] | Issue Actual |  |  |  | 2018-12-05 | 2019-03-20 | 2019-03-21 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00410 | TPSK-LSPA1-T-ME-00410 | TPSK-LSPA1-T-ME-01102 | TPSK-LSPA1-T-ME-01102 | TPSK-LSPA1-T-ME-01426 | TPSK-LSPA1-T-ME-01426
[6 empty] | Return Date |  |  | 2018-12-27 | 2018-12-27 | 2019-04-10 | 2019-04-10 | 2019-06-18 | 2019-06-18
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2137 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2136 - PROCESS WATER STRIPPER FEED HEATER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | IFD: 2019-01-03; IFQ: 2019-04-04; IFQ: 2019-04-05
[6 empty] | Issue Actual | IFD: 2019-01-03; IFQ: 2019-04-04; IFQ: 2019-04-05
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00573; IFD: TPSK-LSPA1-T-ME-00573; IFQ: TPSK-LSPA1-T-ME -01251; IFQ: TPSK-LSPA1-T-ME -01251
[6 empty] | Return Date | IFA: 2019-01-24; IFD: 2019-01-24; IFQ: 2019-06-05; IFQ: 2019-06-05
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2138 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2136 - PROCESS WATER FEED FILTER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-02-25; IFA: 2019-03-18
[6 empty] | Revised Plan | IFD: 2019-01-11; IFQ: 2019-03-25; IFQ: 2019-03-26
[6 empty] | Issue Actual | IFD: 2019-01-11; IFQ: 2019-03-25; IFQ: 2019-03-26
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00639; IFD: TPSK-LSPA1-T-ME-00639; IFQ: TPSK-LSPA1-T-ME-01141; IFQ: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | IFA: 2019-01-30; IFD: 2019-01-30; IFQ: 2019-04-11; IFQ: 2019-04-11
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2139 | Mechanical Equipment Datasheet - Process Water Coalescer Prefilters |  | Class 2 | Purpose** | IFR: IFQ; IFA: IFQ; IFA: IFP; IFD: IFP
[6 empty] | Rev. | IFR: A; IFA: A; IFA: 0; IFD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-10; IFA: 2019-05-13; IFA: 2019-05-15; IFD: 2019-05-16
[6 empty] | Issue Actual | IFR: 2019-05-10; IFA: 2019-05-13; IFA: 2019-05-15; IFD: 2019-05-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01641; IFA: TPSK-LSPA1-T-ME-01641; IFA: TPSK-LSPA1-T-ME-01669; IFD: TPSK-LSPA1-T-ME-01669
[6 empty] | Return Date | IFR: 2019-06-03; IFA: 2019-06-03
Owner Cmmt* | bar: IFR to IFA
| ME | OL1-2M03-2140 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2140 - PROCESS WATER STRIPPER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-03-14; IFA: 2019-04-11
[6 empty] | Revised Plan | IFD: 2018-12-10; IFQ: 2019-02-06; IFQ: 2019-02-06
[6 empty] | Issue Actual | IFD: 2018-12-10; IFQ: 2019-02-06; IFQ: 2019-02-06
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00458; IFD: TPSK-LSPA1-T-ME-00458; IFQ: TPSK-LSPA1-T-ME-00801; IFQ: TPSK-LSPA1-T-ME-00801
[6 empty] | Return Date | IFA: 2018-12-27; IFD: 2018-12-27; IFQ: 2019-02-25; IFQ: 2019-02-25
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2145 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2145 - PROCESS WATER STRIPPER REBOILER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | IFD: 2019-01-22; IFQ: 2019-04-16; IFQ: 2019-04-17
[6 empty] | Issue Actual | IFD: 2019-01-22; IFQ: 2019-04-16; IFQ: 2019-04-17
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00684; IFD: TPSK-LSPA1-T-ME-00684; IFQ: TPSK-LSPA1-T-ME-01357; IFQ: TPSK-LSPA1-T-ME-01357
[6 empty] | Return Date | IFA: 2019-02-11; IFD: 2019-02-11
Owner Cmmt* | bar: IFA to IFD
| ME | OL1-2M03-2146 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2146 - DSG FEED PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan | IFQ: 2018-10-26; IFQ: 2018-12-11
[6 empty] | Issue Actual | IFQ: 2018-10-26; IFQ: 2018-12-11
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00476; IFD: TPSK-LSPA1-T-ME-00235; IFQ: TPSK-LSPA1-T-ME-00235; IFQ: TPSK-LSPA1-T-ME-00476
[6 empty] | Return Date | IFA: 2019-01-16; IFD: 2018-11-19; IFQ: 2018-11-19; IFQ: 2019-01-16
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2147 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2146 - DSG FEED HEATER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | IFD: 2019-01-14; IFQ: 2019-04-10; IFQ: 2019-04-11
[6 empty] | Issue Actual | IFD: 2019-01-14; IFQ: 2019-04-10; IFQ: 2019-04-11
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00650; IFD: TPSK-LSPA1-T-ME-00650; IFQ: TPSK-LSPA1-T-ME-01302; IFQ: TPSK-LSPA1-T-ME-01302
[6 empty] | Return Date | IFA: 2019-01-31; IFD: 2019-01-31; IFQ: 2019-06-05; IFQ: 2019-06-05
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2160 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2160 - DILUTION STEAM GENERATOR |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-01-21; IFA: 2019-02-08
[6 empty] | Revised Plan | IFD: 2018-12-13; IFQ: 2019-05-28; IFQ: 2019-05-29
[6 empty] | Issue Actual | IFD: 2018-12-13; IFQ: 2019-05-28; IFQ: 2019-05-29
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00483; IFD: TPSK-LSPA1-T-ME-00483; IFQ: TPSK-LSPA1-T-ME-01760; IFQ: TPSK-LSPA1-T-ME-01760
[6 empty] | Return Date | IFA: 2019-01-22; IFD: 2019-01-22; IFQ: 2019-06-21
Owner Cmmt* | bar: IFA to IFD; IFQ
| ME | OL1-2M03-2161 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2160 - DILUTION STEAM SUPERHEATER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | IFD: 2019-01-11; IFQ: 2019-04-02; IFQ: 2019-04-03
[6 empty] | Issue Actual | IFD: 2019-01-11; IFQ: 2019-04-02; IFQ: 2019-04-03
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00641; IFD: TPSK-LSPA1-T-ME-00641; IFQ: TPSK-LSPA1-T-ME-01230; IFQ: TPSK-LSPA1-T-ME-01230
[6 empty] | Return Date | IFA: 2019-02-04; IFD: 2019-02-04; IFQ: 2019-05-09; IFQ: 2019-05-09
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2165 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2165 - DSG REBOILER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | 0
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | IFD: 2019-01-03; IFQ: 2019-03-29; IFQ: 2019-04-01; IFQ: 2019-07-17
[6 empty] | Issue Actual | IFD: 2019-01-03; IFQ: 2019-03-29; IFQ: 2019-04-01; IFQ: 2019-07-17
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00582 | TPSK-LSPA1-T-ME-00582 | TPSK-LSPA1-T-ME-01205 | TPSK-LSPA1-T-ME-01205 | TPSK-LSPA1-T-ME-02163
[6 empty] | Return Date |  |  | 2019-01-24 | 2019-01-24 | 2019-05-02 | 2019-05-02 | 2019-08-12
[6 empty] | Owner Cmmt* |  |  | R2 | R2 | TP | TP | R1
| ME | OL1-2M03-2166 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2166 - DSG BLOWDOWN COOLER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | IFD: 2019-01-22; IFQ: 2019-04-03; IFQ: 2019-04-04
[6 empty] | Issue Actual | IFD: 2019-01-22; IFQ: 2019-04-03; IFQ: 2019-04-04
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00684; IFD: TPSK-LSPA1-T-ME-00684; IFQ: TPSK-LSPA1-T-ME-01248; IFQ: TPSK-LSPA1-T-ME-01248
[6 empty] | Return Date | IFA: 2019-02-11; IFD: 2019-02-11; IFQ: 2019-05-20; IFQ: 2019-05-20
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2170 | Mechanical Data Sheet For General Purpose Steam Turbines PT-2106 A Quench Water Pump Turbne |  | Class 2 | Purpose** | IFR: IMP; IFA: IMP
[6 empty] | Rev. | IFR: 0; IFA: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFA: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFA: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02130; IFA: TPSK-LSPA1-T-ME-02130
[6 empty] | Return Date | IFA: 2019-08-01
Owner Cmmt* | bar: IFA
| ME | OL1-2M03-2171 | Mechanical Equipment Data Sheet For DSG Feed Pump Turbine |  | Class 2 | Purpose** | IFR: IMP; IFA: IMP
[6 empty] | Rev. | IFR: 0; IFA: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFA: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFA: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02130; IFA: TPSK-LSPA1-T-ME-02130
[6 empty] | Return Date | IFA: 2019-08-01
Owner Cmmt* | bar: IFA
| ME | OL1-2M03-2190 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2190 - QUENCH WATER DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: IFA to IFQ
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan | IFD: 2019-01-11; IFQ: 2019-04-02; IFQ: 2019-04-03
[6 empty] | Issue Actual | IFD: 2019-01-11; IFQ: 2019-04-02; IFQ: 2019-04-03
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00638; IFD: TPSK-LSPA1-T-ME-00638; IFQ: TPSK-LSPA1-T-ME -1226; IFQ: TPSK-LSPA1-T-ME -1226
[6 empty] | Return Date | IFA: 2019-01-31; IFD: 2019-01-31; IFQ: 2019-05-16; IFQ: 2019-05-16
Owner Cmmt* | bar: IFA to IFQ
| ME | OL1-2M03-2191 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2190 - QUENCH WATER DRAIN DRUM PUMP |  | Class 1 | Purpose** | IFR: IFR; IFA: IFD; IFA: IFQ; IFD: IFQ
Rev. | bar: IFA to IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan | IFD: 2018-11-29
[6 empty] | Issue Actual | IFD: 2018-11-29
[6 empty] | Transmittal no. | IFA: TPSK-LSPA1-T-ME-00400; IFD: TPSK-LSPA1-T-ME-00400
[6 empty] | Return Date | IFA: 2019-02-21; IFD: 2019-02-21
Owner Cmmt* | bar: IFA to IFD
| ME | OL1-2M03-2200 | MECHANICAL EQUIPMENT DATA SHEET - 10-C-2200 - CRACKED GAS COMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | IFA | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  | A | A |  | C | B | B | C
[6 empty] | Issue Plan | IFR: 2018-09-13; R2 IFD: 2018-10-04
[6 empty] | Revised Plan |  | 2018-09-10 | 2018-09-11 |  |  | 2018-10-03 | 2018-10-04 | 2018-11-06
[6 empty] | Issue Actual |  | 2018-09-10 | 2018-09-11 |  |  | 2018-10-03 | 2018-10-04 | 2018-11-06
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00038 | TPSK-LSPA1-T-ME-00038 |  | TPSK-LSPA1-T-ME-00280 | TPSK-LSPA1-T-ME-00127 | TPSK-LSPA1-T-ME-00127 | TPSK-LSPA1-T-ME-00280
[6 empty] | Return Date | IFA: 2018-09-28; R2 IFA: 2018-09-28; R2 IFQ: 2018-11-30; R2 IFQ: 2018-11-30
Owner Cmmt* | bar: IFA to R2 IFA; R2 IFQ; R2 IFQ
| ME | OL1-2M03-2206 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2206 - WASH WATER COOLER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | R2 IFD: 2019-01-07; R2 IFQ: 2019-03-20; R2 IFQ: 2019-03-21
[6 empty] | Issue Actual | R2 IFD: 2019-01-07; R2 IFQ: 2019-03-20; R2 IFQ: 2019-03-21
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00584; R2 IFD: TPSK-LSPA1-T-ME-00584; R2 IFQ: TPSK-LSPA1-T-ME-01110; R2 IFQ: TPSK-LSPA1-T-ME-01110
[6 empty] | Return Date | R2 IFA: 2019-01-24; R2 IFD: 2019-01-24; R2 IFQ: 2019-04-11; R2 IFQ: 2019-04-11
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2210 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2210 - CG 1ST STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan | R2 IFD: 2019-01-22; R2 IFQ: 2019-04-23; R2 IFQ: 2019-04-24
[6 empty] | Issue Actual | R2 IFD: 2019-01-22; R2 IFQ: 2019-04-23; R2 IFQ: 2019-04-24
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00685; R2 IFD: TPSK-LSPA1-T-ME-00685; R2 IFQ: TPSK-LSPA1-T-ME-01448; R2 IFQ: TPSK-LSPA1-T-ME-01448
[6 empty] | Return Date | R2 IFA: 2019-02-15; R2 IFD: 2019-02-15; R2 IFQ: 2019-06-18; R2 IFQ: 2019-06-18
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2211 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2210 - CG 1ST STAGE AFTERCOOLER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | R2 IFD: 2019-01-22; R2 IFQ: 2019-03-20; R2 IFQ: 2019-03-21
[6 empty] | Issue Actual | R2 IFD: 2019-01-22; R2 IFQ: 2019-03-20; R2 IFQ: 2019-03-21
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00683; R2 IFD: TPSK-LSPA1-T-ME-00683; R2 IFQ: TPSK-LSPA1-T-ME-01110; R2 IFQ: TPSK-LSPA1-T-ME-01110
[6 empty] | Return Date | R2 IFA: 2019-02-11; R2 IFD: 2019-02-11; R2 IFQ: 2019-04-11; R2 IFQ: 2019-04-11
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2212 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2210 - CG 1ST STAGE CONDENSATE PUMP |  | Class 1 | Purpose** | IFR: IFR; IFA: IFD; R2 IFA: IFQ; R2 IFD: IFQ
Rev. | bar: R2 IFA to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan | R2 IFD: 2018-12-05
[6 empty] | Issue Actual | R2 IFD: 2018-12-05
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00413; R2 IFD: TPSK-LSPA1-T-ME-00413
[6 empty] | Return Date | R2 IFA: 2018-12-27; R2 IFD: 2018-12-27
Owner Cmmt* | bar: R2 IFA to R2 IFD
| ME | OL1-2M03-2220 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2220 - CG 2ND STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan | R2 IFD: 2018-12-13; R2 IFQ: 2019-03-28; R2 IFQ: 2019-03-29
[6 empty] | Issue Actual | R2 IFD: 2018-12-13; R2 IFQ: 2019-03-28; R2 IFQ: 2019-03-29
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00483; R2 IFD: TPSK-LSPA1-T-ME-00483; R2 IFQ: TPSK-LSPA1-T-ME-01186; R2 IFQ: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | R2 IFA: 2019-01-22; R2 IFD: 2019-01-22; R2 IFQ: 2019-05-02; R2 IFQ: 2019-05-02
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2221 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2220 - CG 2ND STAGE AFTERCOOLER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | R2 IFD: 2019-01-07; R2 IFQ: 2019-03-20; R2 IFQ: 2019-03-21
[6 empty] | Issue Actual | R2 IFD: 2019-01-07; R2 IFQ: 2019-03-20; R2 IFQ: 2019-03-21
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00588; R2 IFD: TPSK-LSPA1-T-ME-00588; R2 IFQ: TPSK-LSPA1-T-ME-01110; R2 IFQ: TPSK-LSPA1-T-ME-01110
[6 empty] | Return Date | R2 IFA: 2019-01-30; R2 IFD: 2019-01-30; R2 IFQ: 2019-04-11; R2 IFQ: 2019-04-11
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2222 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2220 - CG 2ND STAGE CONDENSED HC PUMP |  | Class 1 | Purpose** | IFR: IFR; IFA: IFD; R2 IFA: IFQ; R2 IFD: IFQ
Rev. | bar: R2 IFA to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan | R2 IFD: 2018-11-20
[6 empty] | Issue Actual | R2 IFD: 2018-11-20
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00343; R2 IFD: TPSK-LSPA1-T-ME-00343
[6 empty] | Return Date | R2 IFA: 2019-02-11; R2 IFD: 2019-02-11
Owner Cmmt* | bar: R2 IFA to R2 IFD
| ME | OL1-2M03-2230 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2230 - CG 3RD STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan | R2 IFD: 2018-12-13; R2 IFQ: 2019-03-28; R2 IFQ: 2019-03-29
[6 empty] | Issue Actual | R2 IFD: 2018-12-13; R2 IFQ: 2019-03-28; R2 IFQ: 2019-03-29
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00483; R2 IFD: TPSK-LSPA1-T-ME-00483; R2 IFQ: TPSK-LSPA1-T-ME-01186; R2 IFQ: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | R2 IFA: 2019-01-22; R2 IFD: 2019-01-22; R2 IFQ: 2019-05-02; R2 IFQ: 2019-05-02
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2231 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2230 - CG 3RD STAGE AFTERCOOLER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | R2 IFD: 2019-01-07; R2 IFQ: 2019-03-20; R2 IFQ: 2019-03-21
[6 empty] | Issue Actual | R2 IFD: 2019-01-07; R2 IFQ: 2019-03-20; R2 IFQ: 2019-03-21
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00588; R2 IFD: TPSK-LSPA1-T-ME-00588; R2 IFQ: TPSK-LSPA1-T-ME-01110; R2 IFQ: TPSK-LSPA1-T-ME-01110
[6 empty] | Return Date | R2 IFA: 2019-01-30; R2 IFD: 2019-01-30; R2 IFQ: 2019-04-11; R2 IFQ: 2019-04-11
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2240 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2240 - CG 4TH STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan | R2 IFD: 2018-12-13; R2 IFQ: 2019-03-28; R2 IFQ: 2019-03-29
[6 empty] | Issue Actual | R2 IFD: 2018-12-13; R2 IFQ: 2019-03-28; R2 IFQ: 2019-03-29
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00483; R2 IFD: TPSK-LSPA1-T-ME-00483; R2 IFQ: TPSK-LSPA1-T-ME-01186; R2 IFQ: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | R2 IFA: 2019-01-22; R2 IFD: 2019-01-22; R2 IFQ: 2019-05-02; R2 IFQ: 2019-05-02
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2241 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2240 - CG 4TH STAGE AFTERCOOLER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | R2 IFD: 2019-01-10; R2 IFQ: 2019-03-29; R2 IFQ: 2019-04-01
[6 empty] | Issue Actual | R2 IFD: 2019-01-10; R2 IFQ: 2019-03-29; R2 IFQ: 2019-04-01
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00617; R2 IFD: TPSK-LSPA1-T-ME-00617; R2 IFQ: TPSK-LSPA1-T-ME-01205; R2 IFQ: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | R2 IFA: 2019-01-29; R2 IFD: 2019-01-29; R2 IFQ: 2019-05-02; R2 IFQ: 2019-05-02
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2245 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2245 - CG 4TH STAGE DISCHARGE DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan | R2 IFD: 2019-01-16; R2 IFQ: 2019-04-12; R2 IFQ: 2019-04-15
[6 empty] | Issue Actual | R2 IFD: 2019-01-16; R2 IFQ: 2019-04-12; R2 IFQ: 2019-04-15
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00657; R2 IFD: TPSK-LSPA1-T-ME-00657; R2 IFQ: TPSK-LSPA1-T-ME-01347; R2 IFQ: TPSK-LSPA1-T-ME-01347
[6 empty] | Return Date | R2 IFA: 2019-02-11; R2 IFD: 2019-02-11; R2 IFQ: 2019-05-20; R2 IFQ: 2019-05-20
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2300 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2300 - CAUSTIC TOWER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | B | A | B | C | C
[6 empty] | Issue Plan | IFR: 2019-03-14; IFA: 2019-04-11
[6 empty] | Revised Plan | R2 IFQ: 2018-10-31; R2 IFQ: 2018-12-05; R2 IFQ: 2019-02-19; R2 IFQ: 2019-02-19
[6 empty] | Issue Actual | R2 IFQ: 2018-10-31; R2 IFQ: 2018-12-05; R2 IFQ: 2019-02-19; R2 IFQ: 2019-02-19
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00246 | TPSK-LSPA1-T-ME-00419 | TPSK-LSPA1-T-ME-00246 | TPSK-LSPA1-T-ME-00419 | TPSK-LSPA1-T-ME -00883 | TPSK-LSPA1-T-ME -00883
[6 empty] | Return Date |  |  | 2018-11-27 | 2018-12-27 | 2018-11-27 | 2018-12-27 | 2019-03-12 | 2019-03-12
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2302 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2302 - STRONG CAUSTIC CIRCULATING PUMP |  | Class 1 | Purpose** | IFR: IFR; IFA: IFD; R2 IFA: IFQ; R2 IFD: IFQ
Rev. | bar: R2 IFA to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan | R2 IFD: 2018-11-15
[6 empty] | Issue Actual | R2 IFD: 2018-11-15
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00320; R2 IFD: TPSK-LSPA1-T-ME-00320
[6 empty] | Return Date | R2 IFA: 2018-12-10; R2 IFD: 2018-12-10
Owner Cmmt* | bar: R2 IFA to R2 IFD
| ME | OL1-2M03-2304 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2304 - INTERMEDIATE CAUSTIC CIRCULATING PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan | R2 IFQ: 2018-11-15; R2 IFQ: 2018-12-05
[6 empty] | Issue Actual | R2 IFQ: 2018-11-15; R2 IFQ: 2018-12-05
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00320; R2 IFD: TPSK-LSPA1-T-ME-00411; R2 IFQ: TPSK-LSPA1-T-ME-00320; R2 IFQ: TPSK-LSPA1-T-ME-00411
[6 empty] | Return Date | R2 IFA: 2018-12-10; R2 IFD: 2018-12-27; R2 IFQ: 2018-12-10; R2 IFQ: 2018-12-27
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2305 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2305 - CAUSTIC TOWER FEED HEATER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | R2 IFD: 2019-01-10; R2 IFQ: 2019-04-26; R2 IFQ: 2019-04-29
[6 empty] | Issue Actual | R2 IFD: 2019-01-10; R2 IFQ: 2019-04-26; R2 IFQ: 2019-04-29
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00617; R2 IFD: TPSK-LSPA1-T-ME-00617; R2 IFQ: TPSK-LSPA1-T-ME-01503; R2 IFQ: TPSK-LSPA1-T-ME-01503
[6 empty] | Return Date | R2 IFA: 2019-01-29; R2 IFD: 2019-01-29; R2 IFQ: 2019-06-18; R2 IFQ: 2019-06-18
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2306 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2306 - WEAK CAUSTIC CIRCULATING PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan | R2 IFQ: 2018-11-15; R2 IFQ: 2018-12-05
[6 empty] | Issue Actual | R2 IFQ: 2018-11-15; R2 IFQ: 2018-12-05
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00320; R2 IFD: TPSK-LSPA1-T-ME-00411; R2 IFQ: TPSK-LSPA1-T-ME-00320; R2 IFQ: TPSK-LSPA1-T-ME-00411
[6 empty] | Return Date | R2 IFA: 2018-12-10; R2 IFD: 2018-12-27; R2 IFQ: 2018-12-10; R2 IFQ: 2018-12-27
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2307 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2306 - WEAK CAUSTIC STRAINER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-02-25; IFA: 2019-03-18
[6 empty] | Revised Plan | R2 IFD: 2019-01-11; R2 IFQ: 2019-03-25; R2 IFQ: 2019-03-26
[6 empty] | Issue Actual | R2 IFD: 2019-01-11; R2 IFQ: 2019-03-25; R2 IFQ: 2019-03-26
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00639; R2 IFD: TPSK-LSPA1-T-ME-00639; R2 IFQ: TPSK-LSPA1-T-ME-01141; R2 IFQ: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | R2 IFA: 2019-01-30; R2 IFD: 2019-01-30; R2 IFQ: 2019-04-11; R2 IFQ: 2019-04-11
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2309 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2305 - YELLOW OIL DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan | R2 IFD: 2018-12-13; R2 IFQ: 2019-05-06; R2 IFQ: 2019-05-07
[6 empty] | Issue Actual | R2 IFD: 2018-12-13; R2 IFQ: 2019-05-06; R2 IFQ: 2019-05-07
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00484; R2 IFD: TPSK-LSPA1-T-ME-00484; R2 IFQ: TPSK-LSPA1-T-ME-01571; R2 IFQ: TPSK-LSPA1-T-ME-01571
[6 empty] | Return Date | R2 IFA: 2019-01-22; R2 IFD: 2019-01-22; R2 IFQ: 2019-05-29; R2 IFQ: 2019-05-29
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2310 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2310 - SPENT CAUSTIC DEOILING DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan | R2 IFD: 2018-12-17; R2 IFQ: 2019-04-23; R2 IFQ: 2019-04-24
[6 empty] | Issue Actual | R2 IFD: 2018-12-17; R2 IFQ: 2019-04-23; R2 IFQ: 2019-04-24
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00513; R2 IFD: TPSK-LSPA1-T-ME-00513; R2 IFQ: TPSK-LSPA1-T-ME-01448; R2 IFQ: TPSK-LSPA1-T-ME-01448
[6 empty] | Return Date | R2 IFA: 2019-01-22; R2 IFD: 2019-01-22; R2 IFQ: 2019-06-18; R2 IFQ: 2019-06-18
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2311 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2310 - WASH OIL CIRCULATING PUMP |  | Class 1 | Purpose** | IFR: IFR; IFA: IFD; R2 IFA: IFQ; R2 IFD: IFQ
Rev. | bar: R2 IFA to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan | R2 IFD: 2018-11-15
[6 empty] | Issue Actual | R2 IFD: 2018-11-15
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00320; R2 IFD: TPSK-LSPA1-T-ME-00320
[6 empty] | Return Date | R2 IFA: 2018-12-10; R2 IFD: 2018-12-10
Owner Cmmt* | bar: R2 IFA to R2 IFD
| ME | OL1-2M03-2314 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2310 - WASH OIL CIRCULATION FILTER |  | Class 1 | Purpose** | IFR: IFR; IFA: IFD; R2 IFA: IFQ; R2 IFD: IFQ
Rev. | bar: R2 IFA to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-02-25; IFA: 2019-03-18
[6 empty] | Revised Plan | R2 IFD: 2019-01-11
[6 empty] | Issue Actual | R2 IFD: 2019-01-11
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00639; R2 IFD: TPSK-LSPA1-T-ME-00639
[6 empty] | Return Date | R2 IFA: 2019-01-30; R2 IFD: 2019-01-30
Owner Cmmt* | bar: R2 IFA to R2 IFD
| ME | OL1-2M03-2316 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2316 - SPENT CAUSTIC DEGASSING DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan | R2 IFD: 2019-01-07; R2 IFQ: 2019-05-30; R2 IFQ: 2019-05-31
[6 empty] | Issue Actual | R2 IFD: 2019-01-07; R2 IFQ: 2019-05-30; R2 IFQ: 2019-05-31
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00601; R2 IFD: TPSK-LSPA1-T-ME-00601; R2 IFQ: TPSK-LSPA1-T-ME-01783; R2 IFQ: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date | R2 IFA: 2019-01-30; R2 IFD: 2019-01-30; R2 IFQ: 2019-07-01
Owner Cmmt* | bar: R2 IFA to R2 IFD; R2 IFQ
| ME | OL1-2M03-2319 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2320 - SPENT CAUSTIC PUMP DISCHARGE FILTER |  | Class 1 | Purpose** | IFR: IFR; IFA: IFD; R2 IFA: IFQ; R2 IFD: IFQ
Rev. | bar: R2 IFA to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-02-25; IFA: 2019-03-18
[6 empty] | Revised Plan | R2 IFD: 2019-01-11
[6 empty] | Issue Actual | R2 IFD: 2019-01-11
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00639; R2 IFD: TPSK-LSPA1-T-ME-00639
[6 empty] | Return Date | R2 IFA: 2019-01-30; R2 IFD: 2019-01-30
Owner Cmmt* | bar: R2 IFA to R2 IFD
| ME | OL1-2M03-2320 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-2320 - SPENT CAUSTIC STORAGE TANK |  | Class 1 | Purpose** | IFR: IFR; IFA: IFD; R2 IFA: IFQ; R2 IFD: IFQ
Rev. | bar: R2 IFA to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-02-18; IFA: 2019-02-26
[6 empty] | Revised Plan | R2 IFD: 2019-01-28
[6 empty] | Issue Actual | R2 IFD: 2019-01-28
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00745; R2 IFD: TPSK-LSPA1-T-ME-00745
[6 empty] | Return Date | R2 IFA: 2019-02-21; R2 IFD: 2019-02-21
Owner Cmmt* | bar: R2 IFA to R2 IFD
| ME | OL1-2M03-2321 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2320 - SPENT CAUSTIC PUMP |  | Class 1 | Purpose** | IFR: IFR; IFA: IFD; R2 IFA: IFQ; R2 IFD: IFQ
Rev. | bar: R2 IFA to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan | R2 IFD: 2018-11-19
[6 empty] | Issue Actual | R2 IFD: 2018-11-19
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00335; R2 IFD: TPSK-LSPA1-T-ME-00335
[6 empty] | Return Date | R2 IFA: 2018-12-13; R2 IFD: 2018-12-13
Owner Cmmt* | bar: R2 IFA to R2 IFD
| ME | OL1-2M03-2322 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2322 - SKIM OIL DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan | R2 IFD: 2018-12-13; R2 IFQ: 2019-05-30; R2 IFQ: 2019-05-31
[6 empty] | Issue Actual | R2 IFD: 2018-12-13; R2 IFQ: 2019-05-30; R2 IFQ: 2019-05-31
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00483; R2 IFD: TPSK-LSPA1-T-ME-00483; R2 IFQ: TPSK-LSPA1-T-ME-01783; R2 IFQ: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date | R2 IFA: 2019-01-22; R2 IFD: 2019-01-22; R2 IFQ: 2019-07-01
Owner Cmmt* | bar: R2 IFA to R2 IFD; R2 IFQ
| ME | OL1-2M03-2324 | Mechanical Equipment Data Sheet - Fresh Caustic Day Tank |  | Class 2 | Purpose** | IFR: IFR; IFA: IFD; R2 IFA: IFQ; R2 IFD: IFQ
Rev. | bar: R2 IFA to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-02-18; IFA: 2019-02-26
[6 empty] | Revised Plan | R2 IFD: 2019-01-28
[6 empty] | Issue Actual | R2 IFD: 2019-01-28
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00745; R2 IFD: TPSK-LSPA1-T-ME-00745
[6 empty] | Return Date | R2 IFA: 2019-02-21; R2 IFD: 2019-02-21
Owner Cmmt* | bar: R2 IFA to R2 IFD
| ME | OL1-2M03-2325 | Mechanical Equipment Datasheet - 10 percent Caustic Makeup Pumps |  | Class 2 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan | R2 IFQ: 2019-01-03; R2 IFQ: 2019-02-07
[6 empty] | Issue Actual | R2 IFQ: 2019-01-03; R2 IFQ: 2019-02-07
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00580; R2 IFD: TPSK-LSPA1-T-ME-00822; R2 IFQ: TPSK-LSPA1-T-ME-00580; R2 IFQ: TPSK-LSPA1-T-ME-00822
[6 empty] | Return Date | R2 IFA: 2019-01-24; R2 IFD: 2019-02-21; R2 IFQ: 2019-01-24; R2 IFQ: 2019-02-21
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2326 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2326 - SPENT CAUSTIC STRIPPER FEED HEATER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-01-29; IFA: 2019-01-29
[6 empty] | Revised Plan | R2 IFD: 2019-01-28; R2 IFQ: 2019-05-24; R2 IFQ: 2019-05-27
[6 empty] | Issue Actual | R2 IFD: 2019-01-28; R2 IFQ: 2019-05-24; R2 IFQ: 2019-05-27
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00740; R2 IFD: TPSK-LSPA1-T-ME-00740; R2 IFQ: TPSK-LSPA1-T-ME-01743; R2 IFQ: TPSK-LSPA1-T-ME-01743
[6 empty] | Return Date | R2 IFA: 2019-02-28; R2 IFD: 2019-02-28; R2 IFQ: 2019-06-21
Owner Cmmt* | bar: R2 IFA to R2 IFD; R2 IFQ
| ME | OL1-2M03-2327 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2326 - SPENT CAUSTIC STRIPPER FEED HTR COND POT |  | Class 1 | Purpose** | IFR: IFQ; IFA: IFQ
Rev. | bar: IFR to IFA
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-30; IFA: 2019-05-02
[6 empty] | Issue Actual | IFR: 2019-04-30; IFA: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01524; IFA: TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date | IFR: 2019-06-03; IFA: 2019-06-03
Owner Cmmt* | bar: IFR to IFA
| ME | OL1-2M03-2330 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2330 - SPENT CAUSTIC STRIPPER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-03-14; IFA: 2019-04-11
[6 empty] | Revised Plan | R2 IFD: 2018-12-10; R2 IFQ: 2019-02-15; R2 IFQ: 2019-02-15
[6 empty] | Issue Actual | R2 IFD: 2018-12-10; R2 IFQ: 2019-02-15; R2 IFQ: 2019-02-15
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00462; R2 IFD: TPSK-LSPA1-T-ME-00462; R2 IFQ: TPSK-LSPA1-T-ME-00857; R2 IFQ: TPSK-LSPA1-T-ME-00857
[6 empty] | Return Date | R2 IFA: 2018-12-27; R2 IFD: 2018-12-27; R2 IFQ: 2019-03-12; R2 IFQ: 2019-03-12
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2331 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2330 - SPENT CAUSTIC STRIPPER OVERHEAD DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan | R2 IFD: 2019-01-11; R2 IFQ: 2019-05-01; R2 IFQ: 2019-05-02
[6 empty] | Issue Actual | R2 IFD: 2019-01-11; R2 IFQ: 2019-05-01; R2 IFQ: 2019-05-02
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00638; R2 IFD: TPSK-LSPA1-T-ME-00638; R2 IFQ: TPSK-LSPA1-T-ME-01536; R2 IFQ: TPSK-LSPA1-T-ME-01536
[6 empty] | Return Date | R2 IFA: 2019-01-31; R2 IFD: 2019-01-31; R2 IFQ: 2019-06-18; R2 IFQ: 2019-06-18
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2350 | Mechanical Equipment Datasheet for Wet Air Oxidation Package |  | Class 2 | Purpose** | IFQ | IFQ | IFP | IFP | IFP | IFP
[6 empty] | Rev. | A | A | 0 | 0 | 1 | 1
Issue Plan
[6 empty] | Revised Plan |  | 2018-11-29 | 2019-05-08 | 2019-05-09 | 2019-06-20 | 2019-06-20
[6 empty] | Issue Actual |  | 2018-11-29 | 2019-05-08 | 2019-05-09 | 2019-06-20 | 2019-06-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00390 | TPSK-LSPA1-T-ME-00390 | TPSK-LSPA1-T-PL-01611 | TPSK-LSPA1-T-PL-01611 | TPSK-LSPA1-T-ME-01944 | TPSK-LSPA1-T-ME-01944
[6 empty] | Return Date | IFR: 2019-02-07; IFA: 2019-02-07; R2 IFA: 2019-05-29; R2 IFD: 2019-05-29
Owner Cmmt* | bar: IFR to R2 IFD
| ME | OL1-2M03-2390 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2390 - CAUSTIC DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan |  |  |  | 2018-12-17 | 2019-03-28 | 2019-03-29 | 2019-05-30 | 2019-05-31
[6 empty] | Issue Actual |  |  |  | 2018-12-17 | 2019-03-28 | 2019-03-29 | 2019-05-30 | 2019-05-31
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00514 | TPSK-LSPA1-T-ME-00514 | TPSK-LSPA1-T-ME-01186 | TPSK-LSPA1-T-ME-01186 | TPSK-LSPA1-T-ME-01783 | TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date |  |  | 2019-01-22 | 2019-01-22 | 2019-05-02 | 2019-05-02 |  | 2019-07-01
Owner Cmmt* | bar: R2 IFA to R2 IFQ; R2 IFQ
| ME | OL1-2M03-2391 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2390 - CAUSTIC DRAIN DRUM PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan | R2 IFD: 2018-12-17; R2 IFQ: 2019-02-07; R2 IFQ: 2019-02-07
[6 empty] | Issue Actual | R2 IFD: 2018-12-17; R2 IFQ: 2019-02-07; R2 IFQ: 2019-02-07
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00511; R2 IFD: TPSK-LSPA1-T-ME-00511; R2 IFQ: TPSK-LSPA1-T-ME-00822; R2 IFQ: TPSK-LSPA1-T-ME-00822
[6 empty] | Return Date | R2 IFA: 2019-01-14; R2 IFD: 2019-01-14; R2 IFQ: 2019-02-21; R2 IFQ: 2019-02-21
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2392 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2392 - SPENT CAUSTIC DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan |  |  |  | 2019-01-22 | 2019-04-03 | 2019-04-04 | 2019-05-30 | 2019-05-31
[6 empty] | Issue Actual |  |  |  | 2019-01-22 | 2019-04-03 | 2019-04-04 | 2019-05-30 | 2019-05-31
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00685 | TPSK-LSPA1-T-ME-00685 | TPSK-LSPA1-T-ME-01244 | TPSK-LSPA1-T-ME-01244 | TPSK-LSPA1-T-ME-01783 | TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date |  |  | 2019-02-15 | 2019-02-15 | 2019-05-20 | 2019-05-20 |  | 2019-07-01
Owner Cmmt* | bar: R2 IFA to R2 IFQ; R2 IFQ
| ME | OL1-2M03-2393 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2392 - SPENT CAUSTIC DRAIN DRUM PUMP |  | Class 1 | Purpose** | IFR: IFR; IFA: IFD; R2 IFA: IFQ; R2 IFD: IFQ
Rev. | bar: R2 IFA to R2 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; IFA: 2019-05-07
[6 empty] | Revised Plan | R2 IFD: 2018-12-10
[6 empty] | Issue Actual | R2 IFD: 2018-12-10
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00457; R2 IFD: TPSK-LSPA1-T-ME-00457
[6 empty] | Return Date | R2 IFA: 2018-12-27; R2 IFD: 2018-12-27
Owner Cmmt* | bar: R2 IFA to R2 IFD
| ME | OL1-2M03-2405 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2405 - GAS DRYER FEED KO DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-08; IFA: 2019-05-13
[6 empty] | Revised Plan | R2 IFD: 2019-01-11; R2 IFQ: 2019-04-30; R2 IFQ: 2019-05-02
[6 empty] | Issue Actual | R2 IFD: 2019-01-11; R2 IFQ: 2019-04-30; R2 IFQ: 2019-05-02
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00629; R2 IFD: TPSK-LSPA1-T-ME-00629; R2 IFQ: TPSK-LSPA1-T-ME-01533; R2 IFQ: TPSK-LSPA1-T-ME-01533
[6 empty] | Return Date | R2 IFA: 2019-01-31; R2 IFD: 2019-01-31; R2 IFQ: 2019-06-18; R2 IFQ: 2019-06-18
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2406 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2405 - GAS DRYER FEED CHILLER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
Rev. | bar: R2 IFA to R2 IFQ
[6 empty] | Issue Plan | IFR: 2019-04-15; IFA: 2019-05-20
[6 empty] | Revised Plan | R2 IFD: 2019-01-07; R2 IFQ: 2019-03-29; R2 IFQ: 2019-04-01
[6 empty] | Issue Actual | R2 IFD: 2019-01-07; R2 IFQ: 2019-03-29; R2 IFQ: 2019-04-01
[6 empty] | Transmittal no. | R2 IFA: TPSK-LSPA1-T-ME-00584; R2 IFD: TPSK-LSPA1-T-ME-00584; R2 IFQ: TPSK-LSPA1-T-ME-01205; R2 IFQ: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | R2 IFA: 2019-01-24; R2 IFD: 2019-01-24; R2 IFQ: 2019-05-02; R2 IFQ: 2019-05-02
Owner Cmmt* | bar: R2 IFA to R2 IFQ
| ME | OL1-2M03-2410 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2410 - CRACKED GAS DRYER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C | D | D
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  |  | 2019-01-22 | 2019-03-01 | 2019-03-04 | 2019-03-11 | 2019-03-12 | 2019-04-12 | 2019-04-15
[6 empty] | Issue Actual |  |  |  | 2019-01-22 | 2019-03-01 | 2019-03-04 | 2019-03-11 | 2019-03-12 | 2019-04-12 | 2019-04-15
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00700 | TPSK-LSPA1-T-ME-00700 | TPSK-LSPA1-T-ME-00972 | TPSK-LSPA1-T-ME-00972 | TPSK-LSPA1-T-ME-01016 | TPSK-LSPA1-T-ME-01016 | TPSK-LSPA1-T-ME-01347 | TPSK-LSPA1-T-ME-01347
[6 empty] | Return Date |  |  | 2019-04-01 | 2019-04-01 | 2019-03-29 | 2019-03-29 | 2019-04-02 | 2019-04-02 | 2019-05-20 | 2019-05-20
Owner Cmmt* | bar: A to D
| ME | OL1-2M03-2411 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2411 - CRACKED GAS MERCURY ADSORBER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  |  | 2019-01-11 | 2019-02-28 | 2019-03-01 | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual |  |  |  | 2019-01-11 | 2019-02-28 | 2019-03-01 | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00631 | TPSK-LSPA1-T-ME-00631 | TPSK-LSPA1-T-ME-00954 | TPSK-LSPA1-T-ME-00954 | TPSK-LSPA1-T-ME-01378 | TPSK-LSPA1-T-ME-01378
[6 empty] | Return Date |  |  | 2019-02-21 | 2019-02-21 | 2019-03-25 | 2019-03-25 | 2019-06-04 | 2019-06-04
Owner Cmmt* | bar: A to C
| ME | OL1-2M03-2412 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2412 - HP DEPROPANIZER FEED CHILLER |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; A: IFQ; B: IFQ; B: IFQ
Rev. | bar: A to B
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-10; B: 2019-03-27; B: 2019-03-28
[6 empty] | Issue Actual |  |  | A: 2019-01-10; B: 2019-03-27; B: 2019-03-28
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00617; A: TPSK-LSPA1-T-ME-00617; B: TPSK-LSPA1-T-ME-01179; B: TPSK-LSPA1-T-ME-01179
[6 empty] | Return Date |  |  | A: 2019-01-29; A: 2019-01-29; B: 2019-05-02; B: 2019-05-02
Owner Cmmt* | bar: A to B
| ME | OL1-2M03-2413 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2413 - HP DEPROP FEED / OVERHEAD EXCHANGER |  | Class 1 | Purpose** | IFR | IFR | A: IFD; A: IFQ; B: IFQ
[6 empty] | Rev. | A | A | bar: A to B
[6 empty] | Issue Plan | 2019-04-15 |  | A: 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-03-27; B: 2019-03-28
[6 empty] | Issue Actual |  | 2019-01-10 | A: 2019-03-27; B: 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00617 | TPSK-LSPA1-T-ME-00617 | A: TPSK-LSPA1-T-ME-01179; B: TPSK-LSPA1-T-ME-01179
[6 empty] | Return Date | 2019-02-11 | 2019-02-11 | A: 2019-05-02; B: 2019-05-02
[6 empty] | Owner Cmmt* | R2 | R2 | bar: A to B
| ME | OL1-2M03-2416 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2415 - CG LIQUID DRYER FEED PUMP |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; A: IFQ; B: IFQ; B: IFQ
Rev. | bar: A to B
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2018-12-05; B: 2019-01-30; B: 2019-01-31
[6 empty] | Issue Actual |  |  | A: 2018-12-05; B: 2019-01-30; B: 2019-01-31
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00413; A: TPSK-LSPA1-T-ME-00413; B: TPSK-LSPA1-T-ME-00770; B: TPSK-LSPA1-T-ME-00770
[6 empty] | Return Date |  |  | A: 2018-12-27; A: 2018-12-27; B: 2019-02-21; B: 2019-02-21
Owner Cmmt* | bar: A to B
| ME | OL1-2M03-2420 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2420 - CG LIQUID DRYER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  |  | 2019-01-22 | 2019-02-28 | 2019-03-01 | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual |  |  |  | 2019-01-22 | 2019-02-28 | 2019-03-01 | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00702 | TPSK-LSPA1-T-ME-00702 | TPSK-LSPA1-T-ME-00950 | TPSK-LSPA1-T-ME-00950 | TPSK-LSPA1-T-ME-01378 | TPSK-LSPA1-T-ME-01378
[6 empty] | Return Date |  |  | 2019-02-21 | 2019-02-21 | 2019-04-02 | 2019-04-02 | 2019-06-04 | 2019-06-04
Owner Cmmt* | bar: A to C
| ME | OL1-2M03-2430 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2430 - REGEN GAS FEED HEATER |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; A: IFQ; B: IFQ; B: IFQ
Rev. | bar: A to B
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-28; B: 2019-04-10; B: 2019-04-11
[6 empty] | Issue Actual |  |  | A: 2019-01-28; B: 2019-04-10; B: 2019-04-11
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00740; A: TPSK-LSPA1-T-ME-00740; B: TPSK-LSPA1-T-ME-01315; B: TPSK-LSPA1-T-ME-01315
[6 empty] | Return Date |  |  | A: 2019-02-21; A: 2019-02-21; B: 2019-06-05; B: 2019-06-05
Owner Cmmt* | bar: A to B
| ME | OL1-2M03-2432 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2432 - REGEN GAS SHP HEATER |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; A: IFQ; B: IFQ; B: IFQ
Rev. | bar: A to B
[6 empty] | Issue Plan | 2019-01-29 | 2019-01-29
[6 empty] | Revised Plan |  |  | A: 2019-01-29; B: 2019-05-24; B: 2019-05-27
[6 empty] | Issue Actual |  |  | A: 2019-01-29; B: 2019-05-24; B: 2019-05-27
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00751; A: TPSK-LSPA1-T-ME-00751; B: TPSK-LSPA1-T-ME-01743; B: TPSK-LSPA1-T-ME-01743
[6 empty] | Return Date |  |  | A: 2019-02-21; A: 2019-02-21; B: 2019-06-21
Owner Cmmt* | bar: A to A; B
| ME | OL1-2M03-2434 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2435 - REGEN GAS EFFLUENT COOLER |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; A: IFQ; B: IFQ; B: IFQ
Rev. | bar: A to B
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-25; B: 2019-04-01; B: 2019-04-02
[6 empty] | Issue Actual |  |  | A: 2019-01-25; B: 2019-04-01; B: 2019-04-02
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00723; A: TPSK-LSPA1-T-ME-00723; B: TPSK-LSPA1-T-ME-01218; B: TPSK-LSPA1-T-ME-01218
[6 empty] | Return Date |  |  | A: 2019-02-21; A: 2019-02-21; B: 2019-05-09; B: 2019-05-09
Owner Cmmt* | bar: A to B
| ME | OL1-2M03-2435 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2435 - REGEN GAS SEPARATOR |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; A: IFQ; B: IFQ; B: IFQ
Rev. | bar: A to B
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-22; B: 2019-05-30; B: 2019-05-31
[6 empty] | Issue Actual |  |  | A: 2019-01-22; B: 2019-05-30; B: 2019-05-31
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00685; A: TPSK-LSPA1-T-ME-00685; B: TPSK-LSPA1-T-ME-01783; B: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date |  |  | A: 2019-02-21; A: 2019-02-21; B: 2019-06-21
Owner Cmmt* | bar: A to A; B
| ME | OL1-2M03-2438 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2440 - HP DEPROPANIZER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; A: IFQ; B: IFQ; B: IFQ
Rev. | bar: A to B
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2018-12-13; B: 2019-04-16; B: 2019-04-17
[6 empty] | Issue Actual |  |  | A: 2018-12-13; B: 2019-04-16; B: 2019-04-17
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00484; A: TPSK-LSPA1-T-ME-00484; B: TPSK-LSPA1-T-ME-01378; B: TPSK-LSPA1-T-ME-01378
[6 empty] | Return Date |  |  | A: 2019-01-22; A: 2019-01-22; B: 2019-06-04; B: 2019-06-04
Owner Cmmt* | bar: A to B
| ME | OL1-2M03-2439 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2440 - HP DEPROPANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; A: IFQ; B: IFQ; B: IFQ
Rev. | bar: A to B
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-22; B: 2019-03-29; B: 2019-04-01
[6 empty] | Issue Actual |  |  | A: 2019-01-22; B: 2019-03-29; B: 2019-04-01
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00683; A: TPSK-LSPA1-T-ME-00683; B: TPSK-LSPA1-T-ME-01205; B: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date |  |  | A: 2019-02-11; A: 2019-02-11; B: 2019-05-02; B: 2019-05-02
Owner Cmmt* | bar: A to B
| ME | OL1-2M03-2440 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2440 - HP DEPROPANIZER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | B | A | B | C | C
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | B: 2018-10-23; B: 2018-12-05; C: 2019-02-19; C: 2019-02-19
[6 empty] | Issue Actual |  |  | B: 2018-10-23; B: 2018-12-05; C: 2019-02-19; C: 2019-02-19
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00215 | TPSK-LSPA1-T-ME-00416 | TPSK-LSPA1-T-ME-00215 | TPSK-LSPA1-T-ME-00416 | TPSK-LSPA1-T-ME-00884 | TPSK-LSPA1-T-ME-00884
[6 empty] | Return Date |  |  | 2018-12-17 | 2018-12-27 | 2018-12-17 | 2018-12-27 | 2019-03-12 | 2019-03-12
Owner Cmmt* | bar: A to C
| ME | OL1-2M03-2441 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2441 - HP DEPROP REFLUX CHILLER NO. 2 |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; A: IFQ; B: IFQ; B: IFQ
Rev. | bar: A to B
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-16; B: 2019-04-01; B: 2019-04-02
[6 empty] | Issue Actual |  |  | A: 2019-01-16; B: 2019-04-01; B: 2019-04-02
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00663; A: TPSK-LSPA1-T-ME-00663; B: TPSK-LSPA1-T-ME -01216; B: TPSK-LSPA1-T-ME -01216
[6 empty] | Return Date |  |  | A: 2019-02-11; A: 2019-02-11; B: 2019-05-09; B: 2019-05-09
Owner Cmmt* | bar: A to B
| ME | OL1-2M03-2442 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2442 - HP DEPROP REFLUX CHILLER NO. 1 |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; A: IFQ; B: IFQ; B: IFQ
Rev. | bar: A to B
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-16; B: 2019-04-02; B: 2019-04-03
[6 empty] | Issue Actual |  |  | A: 2019-01-16; B: 2019-04-02; B: 2019-04-03
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00662; A: TPSK-LSPA1-T-ME-00662; B: TPSK-LSPA1-T-ME-01231; B: TPSK-LSPA1-T-ME-01231
[6 empty] | Return Date |  |  | A: 2019-02-11; A: 2019-02-11; B: 2019-05-09; B: 2019-05-09
Owner Cmmt* | bar: A to B
| ME | OL1-2M03-2443 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2445 - HP DEPROPANIZER COND PUMP |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; A: IFQ; B: IFQ; B: IFQ
Rev. | bar: A to B
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2018-12-13; B: 2019-01-30; B: 2019-01-31
[6 empty] | Issue Actual |  |  | A: 2018-12-13; B: 2019-01-30; B: 2019-01-31
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00494; A: TPSK-LSPA1-T-ME-00494; B: TPSK-LSPA1-T-ME-00770; B: TPSK-LSPA1-T-ME-00770
[6 empty] | Return Date |  |  | A: 2019-01-14; A: 2019-01-14; B: 2019-02-21; B: 2019-02-21
Owner Cmmt* | bar: A to B
| ME | OL1-2M03-2444 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2445 - HP DEPROP REBOILER COND POT |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  |  | 2019-01-11 | 2019-04-10 | 2019-04-11 | 2019-05-15 | 2019-05-16
[6 empty] | Issue Actual |  |  |  | 2019-01-11 | 2019-04-10 | 2019-04-11 | 2019-05-15 | 2019-05-16
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00629 | TPSK-LSPA1-T-ME-00629 | TPSK-LSPA1-T-ME -01314 | TPSK-LSPA1-T-ME -01314 | TPSK-LSPA1-T-ME-01670 | TPSK-LSPA1-T-ME-01670
[6 empty] | Return Date |  |  | 2019-01-31 | 2019-01-31 | 2019-06-05 | 2019-06-05 | 2019-06-19 | 2019-06-19
Owner Cmmt* | bar: A to C
| ME | OL1-2M03-2445 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2445 - HP DEPROPANIZER REBOILER |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; A: IFQ; B: IFQ; B: IFQ
Rev. | bar: A to B
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-17; B: 2019-04-02; B: 2019-04-03
[6 empty] | Issue Actual |  |  | A: 2019-01-17; B: 2019-04-02; B: 2019-04-03
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00671; A: TPSK-LSPA1-T-ME-00671; B: TPSK-LSPA1-T-ME-01231; B: TPSK-LSPA1-T-ME-01231
[6 empty] | Return Date |  |  | A: 2019-02-11; A: 2019-02-11; B: 2019-05-09; B: 2019-05-09
Owner Cmmt* | bar: A to B
| ME | OL1-2M03-2446 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2446 - LP DEPROPANIZER FEED COOLER |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; A: IFQ; B: IFQ; B: IFQ
Rev. | bar: A to B
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2018-12-27; B: 2019-04-01; B: 2019-04-02
[6 empty] | Issue Actual |  |  | A: 2018-12-27; B: 2019-04-01; B: 2019-04-02
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00565; A: TPSK-LSPA1-T-ME-00565; B: TPSK-LSPA1-T-ME-01218; B: TPSK-LSPA1-T-ME-01218
[6 empty] | Return Date |  |  | A: 2019-01-22; A: 2019-01-22; B: 2019-05-09; B: 2019-05-09
Owner Cmmt* | bar: A to B
| ME | OL1-2M03-2450 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2450 - LP DEPROPANIZER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | C | B | A | A | B | C | D | D
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  |  |  | 2018-10-16 | 2018-10-17 | 2018-11-06 | 2018-12-05 | 2019-02-19 | 2019-02-19
[6 empty] | Issue Actual |  |  |  |  | 2018-10-16 | 2018-10-17 | 2018-11-06 | 2018-12-05 | 2019-02-19 | 2019-02-19
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00412 | TPSK-LSPA1-T-ME-00283 | TPSK-LSPA1-T-ME-00183 | TPSK-LSPA1-T-ME-00183 | TPSK-LSPA1-T-ME-00283 | TPSK-LSPA1-T-ME-00412 | TPSK-LSPA1-T-ME-00884 | TPSK-LSPA1-T-ME-00884
[6 empty] | Return Date |  |  | 2018-12-27 | 2018-11-30 | 2018-11-05 | 2018-11-05 | 2018-11-30 | 2018-12-27 | 2019-03-12 | 2019-03-12
[6 empty] | Owner Cmmt* |  |  | R2 | R1 | A3 | A3 | R1 | R2 | R2 | R2
| ME | OL1-2M03-2451 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2450 - LP DEPROPANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-01-07; A: 2019-03-29; A: 2019-04-01
[6 empty] | Issue Actual |  |  | B: 2019-01-07; A: 2019-03-29; A: 2019-04-01
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00588; B: TPSK-LSPA1-T-ME-00588; A: TPSK-LSPA1-T-ME-01205; A: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date |  |  | C: 2019-01-30; B: 2019-01-30; A: 2019-05-02; A: 2019-05-02
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2452 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2450 - LP DEPROPANIZER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2018-12-17; A: 2019-04-30; A: 2019-05-02
[6 empty] | Issue Actual |  |  | B: 2018-12-17; A: 2019-04-30; A: 2019-05-02
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00516; B: TPSK-LSPA1-T-ME-00516; A: TPSK-LSPA1-T-ME-01533; A: TPSK-LSPA1-T-ME-01533
[6 empty] | Return Date |  |  | C: 2019-01-22; B: 2019-01-22; A: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2453 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2450 - LP DEPROPANIZER REFLUX / PRODUCT PUMP |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2018-11-08; A: 2019-02-27; A: 2019-02-28
[6 empty] | Issue Actual |  |  | B: 2018-11-08; A: 2019-02-27; A: 2019-02-28
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00294; B: TPSK-LSPA1-T-ME-00294; A: TPSK-LSPA1-T-ME-00944; A: TPSK-LSPA1-T-ME-00944
[6 empty] | Return Date |  |  | C: 2019-02-21; B: 2019-02-21; A: 2019-03-12; A: 2019-03-12
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2455 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2455 - LP DEPROPANIZER REBOILER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  |  | 2019-01-07 | 2019-03-27 | 2019-03-28 | 2019-05-21 | 2019-05-23
[6 empty] | Issue Actual |  |  |  | 2019-01-07 | 2019-03-27 | 2019-03-28 | 2019-05-21 | 2019-05-23
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00584 | TPSK-LSPA1-T-ME-00584 | TPSK-LSPA1-T-ME-01179 | TPSK-LSPA1-T-ME-01179 | TPSK-LSPA1-T-ME-01713 | TPSK-LSPA1-T-ME-01713
[6 empty] | Return Date |  |  | 2019-01-24 | 2019-01-24 | 2019-05-02 | 2019-05-02 |  | 2019-06-21
Owner Cmmt* | bar: C to A; C
| ME | OL1-2M03-2456 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2455 - LP DEPROP REBOILER COND POT |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-01-22; A: 2019-06-04; A: 2019-06-10
[6 empty] | Issue Actual |  |  | B: 2019-01-22; A: 2019-06-04; A: 2019-06-10
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00685; B: TPSK-LSPA1-T-ME-00685; A: TPSK-LSPA1-T-ME-01803; A: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date |  |  | C: 2019-02-21; B: 2019-02-21; A: 2019-07-08
Owner Cmmt* | bar: C to B; A
| ME | OL1-2M03-2457 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2455 - LP DEPROPANIZER COND PUMP |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2018-12-13; A: 2019-01-30; A: 2019-01-31
[6 empty] | Issue Actual |  |  | B: 2018-12-13; A: 2019-01-30; A: 2019-01-31
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00494; B: TPSK-LSPA1-T-ME-00494; A: TPSK-LSPA1-T-ME-00770; A: TPSK-LSPA1-T-ME-00770
[6 empty] | Return Date |  |  | C: 2019-01-14; B: 2019-01-14; A: 2019-02-21; A: 2019-02-21
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2460 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2460 - C2 HYDROG ARSINE GUARD BED |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  |  | 2019-01-16 | 2019-02-15 | 2019-02-15 | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual |  |  |  | 2019-01-16 | 2019-02-15 | 2019-02-15 | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00657 | TPSK-LSPA1-T-ME-00657 | TPSK-LSPA1-T-ME -00858 | TPSK-LSPA1-T-ME -00858 | TPSK-LSPA1-T-ME-01378 | TPSK-LSPA1-T-ME-01378
[6 empty] | Return Date |  |  | 2019-02-11 | 2019-02-11 | 2019-03-12 | 2019-03-12 | 2019-06-04 | 2019-06-04
Owner Cmmt* | bar: C to C
| ME | OL1-2M03-2461 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2460 - C2 HYDROG FEED COOLER |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-01-03; A: 2019-03-27; A: 2019-03-28
[6 empty] | Issue Actual |  |  | B: 2019-01-03; A: 2019-03-27; A: 2019-03-28
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00573; B: TPSK-LSPA1-T-ME-00573; A: TPSK-LSPA1-T-ME-01179; A: TPSK-LSPA1-T-ME-01179
[6 empty] | Return Date |  |  | C: 2019-01-24; B: 2019-01-24; A: 2019-05-02; A: 2019-05-02
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2465 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2465 - C2 HYDROG FEED HEATER |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-01-11; A: 2019-04-02; A: 2019-04-03
[6 empty] | Issue Actual |  |  | B: 2019-01-11; A: 2019-04-02; A: 2019-04-03
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00641; B: TPSK-LSPA1-T-ME-00641; A: TPSK-LSPA1-T-ME-01230; A: TPSK-LSPA1-T-ME-01230
[6 empty] | Return Date |  |  | C: 2019-02-04; B: 2019-02-04; A: 2019-05-09; A: 2019-05-09
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2470 | MECHANICAL EQUIPMENT DATA SHEET - 10-R-2470 - C2 HYDROG REACTOR |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-16 | 2019-02-16
[6 empty] | Revised Plan |  |  |  | 2019-01-11 | 2019-02-28 | 2019-03-01 | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual |  |  |  | 2019-01-11 | 2019-02-28 | 2019-03-01 | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00630 | TPSK-LSPA1-T-ME-00630 | TPSK-LSPA1-T-ME-00953 | TPSK-LSPA1-T-ME-00953 | TPSK-LSPA1-T-ME-01379 | TPSK-LSPA1-T-ME-01379
[6 empty] | Return Date |  |  | 2019-02-21 | 2019-02-21 | 2019-03-25 | 2019-03-25 | 2019-06-04 | 2019-06-04
Owner Cmmt* | bar: C to C
| ME | OL1-2M03-2471 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2470 - C2 HYDROG 1ST STAGE INTERCOOLER |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-01-11; A: 2019-04-02; A: 2019-04-03
[6 empty] | Issue Actual |  |  | B: 2019-01-11; A: 2019-04-02; A: 2019-04-03
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00641; B: TPSK-LSPA1-T-ME-00641; A: TPSK-LSPA1-T-ME-01231; A: TPSK-LSPA1-T-ME-01231
[6 empty] | Return Date |  |  | C: 2019-02-11; B: 2019-02-11; A: 2019-05-09; A: 2019-05-09
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2472 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2472 - C2 HYDROG 2ND STAGE INTERCOOLER |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-01-11; A: 2019-03-29; A: 2019-04-01
[6 empty] | Issue Actual |  |  | B: 2019-01-11; A: 2019-03-29; A: 2019-04-01
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00641; B: TPSK-LSPA1-T-ME-00641; A: TPSK-LSPA1-T-ME-01205; A: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date |  |  | C: 2019-02-04; B: 2019-02-04; A: 2019-05-02; A: 2019-05-02
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2474 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2474 - C2 HYDROG AFTERCOOLER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  |  | 2019-01-11 | 2019-03-29 | 2019-04-01 | 2019-05-21 | 2019-05-23
[6 empty] | Issue Actual |  |  |  | 2019-01-11 | 2019-03-29 | 2019-04-01 | 2019-05-21 | 2019-05-23
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00641 | TPSK-LSPA1-T-ME-00641 | TPSK-LSPA1-T-ME-01205 | TPSK-LSPA1-T-ME-01205 | TPSK-LSPA1-T-ME-01714 | TPSK-LSPA1-T-ME-01714
[6 empty] | Return Date |  |  | 2019-02-04 | 2019-02-04 | 2019-05-02 | 2019-05-02 |  | 2019-06-21
Owner Cmmt* | bar: C to A; C
| ME | OL1-2M03-2480 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2480 - CG SECONDARY DRYER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  |  | 2019-01-22 | 2019-02-28 | 2019-03-01 | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual |  |  |  | 2019-01-22 | 2019-02-28 | 2019-03-01 | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00702 | TPSK-LSPA1-T-ME-00702 | TPSK-LSPA1-T-ME-00954 | TPSK-LSPA1-T-ME-00954 | TPSK-LSPA1-T-ME-01378 | TPSK-LSPA1-T-ME-01378
[6 empty] | Return Date |  |  | 2019-02-21 | 2019-02-21 | 2019-03-25 | 2019-03-25 | 2019-06-04 | 2019-06-04
Owner Cmmt* | bar: C to C
| ME | OL1-2M03-2502 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2502 - DEMETH PREFRAC FEED COOLER NO. 1 |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2018-12-10; A: 2019-03-29; A: 2019-04-01
[6 empty] | Issue Actual |  |  | B: 2018-12-10; A: 2019-03-29; A: 2019-04-01
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00461; B: TPSK-LSPA1-T-ME-00461; A: TPSK-LSPA1-T-ME-01205; A: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date |  |  | C: 2018-12-27; B: 2018-12-27; A: 2019-05-02; A: 2019-05-02
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2503 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2504 - DEMETH PREFRAC FEED COOLER NO. 2 |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2018-11-28; A: 2019-03-29; A: 2019-04-01
[6 empty] | Issue Actual |  |  | B: 2018-11-28; A: 2019-03-29; A: 2019-04-01
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00389; B: TPSK-LSPA1-T-ME-00389; A: TPSK-LSPA1-T-ME-01205; A: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date |  |  | C: 2018-12-13; B: 2018-12-13; A: 2019-05-02; A: 2019-05-02
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2504 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2504 - DEMETH PREFRAC FEED SEPARATOR NO. 1 |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2018-12-13; A: 2019-04-30; A: 2019-05-02
[6 empty] | Issue Actual |  |  | B: 2018-12-13; A: 2019-04-30; A: 2019-05-02
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00483; B: TPSK-LSPA1-T-ME-00483; A: TPSK-LPSA1-T-ME-01534; A: TPSK-LPSA1-T-ME-01534
[6 empty] | Return Date |  |  | C: 2019-01-22; B: 2019-01-22; A: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2506 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2506 - DEMETH PREFRAC FEED SEPARATOR NO. 2 |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2018-12-20; A: 2019-05-06; A: 2019-05-07
[6 empty] | Issue Actual |  |  | B: 2018-12-20; A: 2019-05-06; A: 2019-05-07
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00551; B: TPSK-LSPA1-T-ME-00551; A: TPSK-LSPA1-T-ME-01583; A: TPSK-LSPA1-T-ME-01583
[6 empty] | Return Date |  |  | C: 2019-01-24; B: 2019-01-24; A: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2508 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2508 - DEMETH PREFRAC FEED SEPARATOR NO. 3 |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2018-12-20; A: 2019-05-06; A: 2019-05-07
[6 empty] | Issue Actual |  |  | B: 2018-12-20; A: 2019-05-06; A: 2019-05-07
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00551; B: TPSK-LSPA1-T-ME-00551; A: TPSK-LSPA1-T-ME-01583; A: TPSK-LSPA1-T-ME-01583
[6 empty] | Return Date |  |  | C: 2019-01-24; B: 2019-01-24; A: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2510 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2510 - DEMETHANIZER PREFRACTIONATOR |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | B | A | A | B | C | C
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | A: 2018-10-31; A: 2018-12-05; B: 2019-03-01; C: 2019-03-04
[6 empty] | Issue Actual |  |  | A: 2018-10-31; A: 2018-12-05; B: 2019-03-01; C: 2019-03-04
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00414 | TPSK-LSPA1-T-ME-00260 | TPSK-LSPA1-T-ME-00260 | TPSK-LSPA1-T-ME-00414 | TPSK-LSPA1-T-ME-00970 | TPSK-LSPA1-T-ME-00970
[6 empty] | Return Date |  |  | 2018-12-27 | 2018-11-29 | 2018-11-29 | 2018-12-27 | 2019-03-29 | 2019-03-29
Owner Cmmt* | bar: C to C
| ME | OL1-2M03-2515 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2515 - DEMETH PREFRACTIONATOR REBOILER |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-01-03; A: 2019-03-01; A: 2019-03-04
[6 empty] | Issue Actual |  |  | B: 2019-01-03; A: 2019-03-01; A: 2019-03-04
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00573; B: TPSK-LSPA1-T-ME-00573; A: TPSK-LSPA1-T-ME-00971; A: TPSK-LSPA1-T-ME-00971
[6 empty] | Return Date |  |  | C: 2019-01-24; B: 2019-01-24; A: 2019-03-29; A: 2019-03-29
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2520 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2520 - RESIDUE GAS RECTIFIER |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | B: 2018-12-20; A: 2019-02-01; A: 2019-02-04
[6 empty] | Issue Actual |  |  | B: 2018-12-20; A: 2019-02-01; A: 2019-02-04
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00534; B: TPSK-LSPA1-T-ME-00534; A: TPSK-LSPA1-T-ME-00792; A: TPSK-LSPA1-T-ME-00792
[6 empty] | Return Date |  |  | C: 2019-01-22; B: 2019-01-22; A: 2019-02-21; A: 2019-02-21
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2525 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2525 - HYDROGEN DRUM |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-01-16; A: 2019-05-06; A: 2019-05-07
[6 empty] | Issue Actual |  |  | B: 2019-01-16; A: 2019-05-06; A: 2019-05-07
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00657; B: TPSK-LSPA1-T-ME-00657; A: TPSK-LSPA1-T-ME-01583; A: TPSK-LSPA1-T-ME-01583
[6 empty] | Return Date |  |  | C: 2019-02-11; B: 2019-02-11; A: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2540 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2540 - DEMETHANIZER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | B | A | A | B | C | C
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | A: 2018-11-09; A: 2018-12-05; B: 2019-02-27; C: 2019-02-28
[6 empty] | Issue Actual |  |  | A: 2018-11-09; A: 2018-12-05; B: 2019-02-27; C: 2019-02-28
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00415 | TPSK-LSPA1-T-ME-00304 | TPSK-LSPA1-T-ME-00304 | TPSK-LSPA1-T-ME-00415 | TPSK-LSPA1-T-ME-00945 | TPSK-LSPA1-T-ME-00945
[6 empty] | Return Date |  |  | 2018-12-27 | 2018-12-10 | 2018-12-10 | 2018-12-27 | 2019-03-25 | 2019-03-25
Owner Cmmt* | bar: C to C
| ME | OL1-2M03-2545 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2545 - DEMETHANIZER REBOILER |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-01-14; A: 2019-03-21; A: 2019-03-22
[6 empty] | Issue Actual |  |  | B: 2019-01-14; A: 2019-03-21; A: 2019-03-22
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00651; B: TPSK-LSPA1-T-ME-00651; A: TPSK-LSPA1-T-ME-01123; A: TPSK-LSPA1-T-ME-01123
[6 empty] | Return Date |  |  | C: 2019-01-31; B: 2019-01-31; A: 2019-04-11; A: 2019-04-11
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2546 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2546 - DEMETHANIZER BOTTOMS COOLER |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-01-16; A: 2019-03-29; A: 2019-04-01
[6 empty] | Issue Actual |  |  | B: 2019-01-16; A: 2019-03-29; A: 2019-04-01
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00654; B: TPSK-LSPA1-T-ME-00654; A: TPSK-LSPA1-T-ME-01205; A: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date |  |  | C: 2019-01-31; B: 2019-01-31; A: 2019-05-02; A: 2019-05-02
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2548 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2548 - DEMETHANIZER BOTTOMS VAPORIZER |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-01-10; A: 2019-03-01; A: 2019-03-04
[6 empty] | Issue Actual |  |  | B: 2019-01-10; A: 2019-03-01; A: 2019-03-04
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00617; B: TPSK-LSPA1-T-ME-00617; A: TPSK-LSPA1-T-ME-00961; A: TPSK-LSPA1-T-ME-00961
[6 empty] | Return Date |  |  | C: 2019-01-29; B: 2019-01-29; A: 2019-03-29; A: 2019-03-29
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2550 | MECHANICAL EQUIPMENT DATA SHEET - 10-C-2550 - RESIDUE GAS EXPANDER / RECOMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | C: IFA; B: IFD; A: IFQ; A: IFQ
[6 empty] | Rev. |  | A | bar: C; A to A
[6 empty] | Issue Plan | 2018-09-13 |  | B: 2018-10-04
[6 empty] | Revised Plan |  | 2018-09-13 | C: 2018-09-14; A: 2018-10-05; A: 2018-10-05
[6 empty] | Issue Actual |  | 2018-09-13 | C: 2018-09-14; A: 2018-10-05; A: 2018-10-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00050 | C: TPSK-LSPA1-T-ME-00050; A: TPSK-LSPA1-T-ME-00130; A: TPSK-LSPA1-T-ME-00130
[6 empty] | Return Date |  | 2018-10-02 | C: 2018-10-02; A: 2018-10-26; A: 2018-10-26
[6 empty] | Owner Cmmt* |  | A3 | bar: C; A to A
| ME | OL1-2M03-2551 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2550 - EXPANDER SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2018-12-20; A: 2019-05-29; A: 2019-05-30
[6 empty] | Issue Actual |  |  | B: 2018-12-20; A: 2019-05-29; A: 2019-05-30
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00551; B: TPSK-LSPA1-T-ME-00551; A: TPSK-LSPA1-T-ME-01764; A: TPSK-LSPA1-T-ME-01764
[6 empty] | Return Date |  |  | C: 2019-01-24; B: 2019-01-24; A: 2019-06-21
Owner Cmmt* | bar: C to B; A
| ME | OL1-2M03-2555 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2555 - EXPANDER DISCHARGE DRUM |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-01-08; A: 2019-05-28; A: 2019-05-29
[6 empty] | Issue Actual |  |  | B: 2019-01-08; A: 2019-05-28; A: 2019-05-29
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00607; B: TPSK-LSPA1-T-ME-00607; A: TPSK-LSPA1-T-ME-01760; A: TPSK-LSPA1-T-ME-01760
[6 empty] | Return Date |  |  | C: 2019-01-28; B: 2019-01-28; A: 2019-06-21
Owner Cmmt* | bar: C to B; A
| ME | OL1-2M03-2570 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2570 - DEETHANIZER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | B | A | B | C | C
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | A: 2018-11-29; A: 2018-12-20; B: 2019-02-26; C: 2019-02-27
[6 empty] | Issue Actual |  |  | A: 2018-11-29; A: 2018-12-20; B: 2019-02-26; C: 2019-02-27
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00394 | TPSK-LSPA1-T-ME-00547 | TPSK-LSPA1-T-ME-00394 | TPSK-LSPA1-T-ME-00547 | TPSK-LSPA1-T-ME-00931 | TPSK-LSPA1-T-ME-00931
[6 empty] | Return Date |  |  | 2018-12-27 | 2019-01-22 | 2018-12-27 | 2019-01-22 | 2019-03-15 | 2019-03-15
Owner Cmmt* | bar: C to C
| ME | OL1-2M03-2571 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2570 - DEETHANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  |  | 2018-11-13 | 2019-01-30 | 2019-01-31 | 2019-04-03 | 2019-04-04
[6 empty] | Issue Actual |  |  |  | 2018-11-13 | 2019-01-30 | 2019-01-31 | 2019-04-03 | 2019-04-04
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00310 | TPSK-LSPA1-T-ME-00310 | TPSK-LSPA1-T-ME-00773 | TPSK-LSPA1-T-ME-00773 | TPSK-LSPA1-T-ME-01245 | TPSK-LSPA1-T-ME-01245
[6 empty] | Return Date |  |  | 2019-02-11 | 2019-02-11 | 2019-02-26 | 2019-02-26 | 2019-05-20 | 2019-05-20
Owner Cmmt* | bar: C to C
| ME | OL1-2M03-2572 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2570 - DEETHANIZER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ
Rev. | bar: C to B
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2018-12-13
[6 empty] | Issue Actual |  |  | B: 2018-12-13
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00484; B: TPSK-LSPA1-T-ME-00484
[6 empty] | Return Date |  |  | C: 2019-01-22; B: 2019-01-22
Owner Cmmt* | bar: C to B
| ME | OL1-2M03-2573 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2570 - DEETHANIZER REFLUX PUMP |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ
Rev. | bar: C to B
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2018-12-20
[6 empty] | Issue Actual |  |  | B: 2018-12-20
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00552; B: TPSK-LSPA1-T-ME-00552
[6 empty] | Return Date |  |  | C: 2019-01-16; B: 2019-01-16
Owner Cmmt* | bar: C to B
| ME | OL1-2M03-2574 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2575 - DEETHANIZER REBOILER COND POT |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-01-22; A: 2019-06-04; A: 2019-06-10
[6 empty] | Issue Actual |  |  | B: 2019-01-22; A: 2019-06-04; A: 2019-06-10
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00685; B: TPSK-LSPA1-T-ME-00685; A: TPSK-LSPA1-T-ME-01803; A: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date |  |  | C: 2019-02-21; B: 2019-02-21; A: 2019-07-08
Owner Cmmt* | bar: C to B; A
| ME | OL1-2M03-2575 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2575 - DEETHANIZER REBOILER |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-01-22; A: 2019-03-01; A: 2019-03-04
[6 empty] | Issue Actual |  |  | B: 2019-01-22; A: 2019-03-01; A: 2019-03-04
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00684; B: TPSK-LSPA1-T-ME-00684; A: TPSK-LSPA1-T-ME-00961; A: TPSK-LSPA1-T-ME-00961
[6 empty] | Return Date |  |  | C: 2019-02-11; B: 2019-02-11; A: 2019-03-29; A: 2019-03-29
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2576 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2576 - DEETHANIZER BOTTOMS COOLER |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-01-03; A: 2019-03-21; A: 2019-03-22
[6 empty] | Issue Actual |  |  | B: 2019-01-03; A: 2019-03-21; A: 2019-03-22
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00582; B: TPSK-LSPA1-T-ME-00582; A: TPSK-LSPA1-T-ME-01123; A: TPSK-LSPA1-T-ME-01123
[6 empty] | Return Date |  |  | C: 2019-01-24; B: 2019-01-24; A: 2019-04-11; A: 2019-04-11
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2577 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2575 - DEETHANIZER REBOILER COND PUMP |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ
Rev. | bar: C to B
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2018-12-13
[6 empty] | Issue Actual |  |  | B: 2018-12-13
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00494; B: TPSK-LSPA1-T-ME-00494
[6 empty] | Return Date |  |  | C: 2019-01-14; B: 2019-01-14
Owner Cmmt* | bar: C to B
| ME | OL1-2M03-2580 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2580 - C2 TOWER |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | B: 2018-12-20; A: 2019-03-04; A: 2019-03-05
[6 empty] | Issue Actual |  |  | B: 2018-12-20; A: 2019-03-04; A: 2019-03-05
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00531; B: TPSK-LSPA1-T-ME-00531; A: TPSK-LSPA1-T-ME-00981; A: TPSK-LSPA1-T-ME-00981
[6 empty] | Return Date |  |  | C: 2019-01-22; B: 2019-01-22; A: 2019-03-29; A: 2019-03-29
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2582 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2582 - C2 TOWER REFLUX COOLER |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ; A: IFQ; A: IFQ
Rev. | bar: C to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-01-16; A: 2019-02-15; A: 2019-02-15
[6 empty] | Issue Actual |  |  | B: 2019-01-16; A: 2019-02-15; A: 2019-02-15
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00661; B: TPSK-LSPA1-T-ME-00661; A: TPSK-LSPA1-T-ME-00859; A: TPSK-LSPA1-T-ME-00859
[6 empty] | Return Date |  |  | C: 2019-02-11; B: 2019-02-11; A: 2019-03-12; A: 2019-03-12
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2586 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2586 - ETHANE RECYCLE PUMP |  | Class 1 | Purpose** | IFR | IFD | C: IFQ; B: IFQ
Rev. | bar: C to B
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2018-12-05
[6 empty] | Issue Actual |  |  | B: 2018-12-05
[6 empty] | Transmittal no. |  |  | C: TPSK-LSPA1-T-ME-00413; B: TPSK-LSPA1-T-ME-00413
[6 empty] | Return Date |  |  | C: 2018-12-27; B: 2018-12-27
Owner Cmmt* | bar: C to B
| ME | OL1-2M03-2600 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2600 - C3 HYDROG GUARD ADSORBER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | B | A | B | C | C | D | D
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  |  |  | 2019-01-17 | 2019-01-22 | 2019-02-28 | 2019-03-01 | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual |  |  |  |  | 2019-01-17 | 2019-01-22 | 2019-02-28 | 2019-03-01 | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00672 | TPSK-LSPA1-T-ME -00701 | TPSK-LSPA1-T-ME-00672 | TPSK-LSPA1-T-ME -00701 | TPSK-LSPA1-T-ME-00954 | TPSK-LSPA1-T-ME-00954 | TPSK-LSPA1-T-ME -01381 | TPSK-LSPA1-T-ME -01381
[6 empty] | Return Date |  |  | 2019-02-11 | 2019-02-21 | 2019-02-11 | 2019-02-21 | 2019-03-25 | 2019-03-25 | 2019-06-04 | 2019-06-04
Owner Cmmt* | bar: A to D
| ME | OL1-2M03-2610 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2610 - C3 HYDROG ARSINE GUARD BED |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | B | A | A | B | C | C | D | D
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  |  |  | 2018-12-27 | 2019-01-16 | 2019-02-28 | 2019-03-01 | 2019-04-16 | 2019-04-17
[6 empty] | Issue Actual |  |  |  |  | 2018-12-27 | 2019-01-16 | 2019-02-28 | 2019-03-01 | 2019-04-16 | 2019-04-17
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00658 | TPSK-LSPA1-T-ME-00570 | TPSK-LSPA1-T-ME-00570 | TPSK-LSPA1-T-ME-00658 | TPSK-LSPA1-T-ME-00950 | TPSK-LSPA1-T-ME-00950 | TPSK-LSPA1-T-ME-01381 | TPSK-LSPA1-T-ME-01381
[6 empty] | Return Date |  |  | 2019-02-11 | 2019-01-24 | 2019-01-24 | 2019-02-11 | 2019-04-01 | 2019-04-01 | 2019-06-04 | 2019-06-04
Owner Cmmt* | bar: B to D
| ME | OL1-2M03-2620 | MECHANICAL EQUIPMENT DATA SHEET - 10-R-2620 - C3 HYDROG REACTOR |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | C | A | A | B | B | C
[6 empty] | Issue Plan | 2019-02-16 | 2019-02-16
[6 empty] | Revised Plan |  |  |  | 2019-02-06 | 2019-02-06 | 2019-03-05 | 2019-03-06 | 2019-04-12
[6 empty] | Issue Actual |  |  |  | 2019-02-06 | 2019-02-06 | 2019-03-05 | 2019-03-06 | 2019-04-12
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-01346 | TPSK-LSPA1-T-ME-00802 | TPSK-LSPA1-T-ME-00802 | TPSK-LSPA1-T-ME-00990 | TPSK-LSPA1-T-ME-00990 | TPSK-LSPA1-T-ME-01346
[6 empty] | Return Date |  |  | 2019-05-20 | 2019-02-26 | 2019-02-26 | 2019-03-29 | 2019-03-29 | 2019-05-20
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-2621 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2620 - C3 HYDROG AFTERCOOLER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; A: IFQ; B: IFQ
Rev. | bar: B to B
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-02-25; A: 2019-02-26; A: 2019-04-02; B: 2019-04-03
[6 empty] | Issue Actual |  |  | B: 2019-02-25; A: 2019-02-26; A: 2019-04-02; B: 2019-04-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00929; A: TPSK-LSPA1-T-ME-00929; A: TPSK-LSPA1-T-ME-01233; B: TPSK-LSPA1-T-ME-01233
[6 empty] | Return Date |  |  | B: 2019-03-15; A: 2019-03-15; A: 2019-05-09; B: 2019-05-09
Owner Cmmt* | bar: B to B
| ME | OL1-2M03-2622 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2620 - C3 HYDROG RECYCLE DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; A: IFQ; B: IFQ
Rev. | bar: B to B
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-22; A: 2019-06-06; B: 2019-06-10
[6 empty] | Issue Actual |  |  | A: 2019-01-22; A: 2019-06-06; B: 2019-06-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00685; A: TPSK-LSPA1-T-ME-00685; A: TPSK-LSPA1-T-ME-01817; B: TPSK-LSPA1-T-ME-01817
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; B: 2019-07-08
Owner Cmmt* | bar: B to A; B
| ME | OL1-2M03-2623 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2620 - C3 HYDROG RECYCLE PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  |  | 2019-01-24 | 2019-03-26 | 2019-03-27 | 2019-06-12 | 2019-06-14 | 2019-07-31
[6 empty] | Issue Actual |  |  |  | 2019-01-24 | 2019-03-26 | 2019-03-27 | 2019-06-12 | 2019-06-14 | 2019-07-31
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00716 | TPSK-LSPA1-T-ME-00716 | TPSK-LSPA1-T-ME-01158 | TPSK-LSPA1-T-ME-01158 | TPSK-LSPA1-T-ME-01880 | TPSK-LSPA1-T-ME-01880 | TPSK-LSPA1-T-ME-02295
[6 empty] | Return Date |  |  | 2019-02-21 | 2019-02-21 | 2019-04-10 | 2019-04-10 |  | 2019-07-09
Owner Cmmt* | bar: B to B; C
| ME | OL1-2M03-2630 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2630 - SECONDARY DEETHANIZER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; A: IFQ; B: IFQ
Rev. | bar: B to B
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | A: 2018-12-10; A: 2019-03-01; B: 2019-03-04
[6 empty] | Issue Actual |  |  | A: 2018-12-10; A: 2019-03-01; B: 2019-03-04
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00458; A: TPSK-LSPA1-T-ME-00458; A: TPSK-LSPA1-T-ME-00974; B: TPSK-LSPA1-T-ME-00974
[6 empty] | Return Date |  |  | B: 2018-12-27; A: 2018-12-27; A: 2019-03-29; B: 2019-03-29
Owner Cmmt* | bar: B to B
| ME | OL1-2M03-2631 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2630 - SECONDARY DEETH CONDENSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; A: IFQ; B: IFQ
Rev. | bar: B to B
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2018-12-10; A: 2019-04-03; B: 2019-04-04
[6 empty] | Issue Actual |  |  | A: 2018-12-10; A: 2019-04-03; B: 2019-04-04
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00455; A: TPSK-LSPA1-T-ME-00455; A: TPSK-LSPA1-T-ME-01243; B: TPSK-LSPA1-T-ME-01243
[6 empty] | Return Date |  |  | B: 2018-12-27; A: 2018-12-27; A: 2019-05-20; B: 2019-05-20
Owner Cmmt* | bar: B to B
| ME | OL1-2M03-2632 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2630 - SECONDARY DEETH REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; A: IFQ; B: IFQ
Rev. | bar: B to B
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-11; A: 2019-04-10; B: 2019-04-11
[6 empty] | Issue Actual |  |  | A: 2019-01-11; A: 2019-04-10; B: 2019-04-11
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00629; A: TPSK-LSPA1-T-ME-00629; A: TPSK-LSPA1-T-ME -01314; B: TPSK-LSPA1-T-ME -01314
[6 empty] | Return Date |  |  | B: 2019-01-31; A: 2019-01-31; A: 2019-06-05; B: 2019-06-05
Owner Cmmt* | bar: B to B
| ME | OL1-2M03-2633 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2630 - SECONDARY DEETH REFLUX PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; A: IFQ; B: IFQ
Rev. | bar: B to B
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2018-12-13; B: 2018-12-20
[6 empty] | Issue Actual |  |  | A: 2018-12-13; B: 2018-12-20
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00487; A: TPSK-LSPA1-T-ME-00554; A: TPSK-LSPA1-T-ME-00487; B: TPSK-LSPA1-T-ME-00554
[6 empty] | Return Date |  |  | B: 2019-01-16; A: 2019-01-16; A: 2019-01-16; B: 2019-01-16
Owner Cmmt* | bar: B to B
| ME | OL1-2M03-2635 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2635 - SECONDARY DEETH REBOILER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; A: IFQ; B: IFQ
Rev. | bar: B to B
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-03; A: 2019-04-30; B: 2019-05-02
[6 empty] | Issue Actual |  |  | A: 2019-01-03; A: 2019-04-30; B: 2019-05-02
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00582; A: TPSK-LSPA1-T-ME-00582; A: TPSK-LSPA1-T-ME-01532; B: TPSK-LSPA1-T-ME-01532
[6 empty] | Return Date |  |  | B: 2019-01-24; A: 2019-01-24; A: 2019-06-18; B: 2019-06-18
Owner Cmmt* | bar: B to B
| ME | OL1-2M03-2636 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2636 - SECONDARY DEETH BOTTOMS COOLER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; A: IFQ; B: IFQ
Rev. | bar: B to B
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2018-12-10; A: 2019-04-10; B: 2019-04-11
[6 empty] | Issue Actual |  |  | A: 2018-12-10; A: 2019-04-10; B: 2019-04-11
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00465; A: TPSK-LSPA1-T-ME-00465; A: TPSK-LSPA1-T-ME -01313; B: TPSK-LSPA1-T-ME -01313
[6 empty] | Return Date |  |  | B: 2018-12-27; A: 2018-12-27
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2640 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2640 - C3 TOWER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  |  | 2018-12-05 | 2019-02-19 | 2019-02-19 | 2019-03-04 | 2019-03-05
[6 empty] | Issue Actual |  |  |  | 2018-12-05 | 2019-02-19 | 2019-02-19 | 2019-03-04 | 2019-03-05
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00415 | TPSK-LSPA1-T-ME-00415 | TPSK-LSPA1-T-ME-00885 | TPSK-LSPA1-T-ME-00885 | TPSK-LSPA1-T-ME-00981 | TPSK-LSPA1-T-ME-00981
[6 empty] | Return Date |  |  | 2019-02-21 | 2019-02-21 | 2019-03-12 | 2019-03-12 | 2019-03-29 | 2019-03-29
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-2644 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2645 - C3 TOWER REBOILER COND POT |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; A: IFQ; B: IFQ
Rev. | bar: B to B
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-29; A: 2019-05-28; B: 2019-05-29
[6 empty] | Issue Actual |  |  | A: 2019-01-29; A: 2019-05-28; B: 2019-05-29
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00753; A: TPSK-LSPA1-T-ME-00753; A: TPSK-LSPA1-T-ME-01760; B: TPSK-LSPA1-T-ME-01760
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; B: 2019-06-21
Owner Cmmt* | bar: B to A; B
| ME | OL1-2M03-2645 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2645 - C3 TOWER REBOILER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  |  | 2018-11-26 | 2019-01-30 | 2019-01-31 | 2019-04-09 | 2019-04-10
[6 empty] | Issue Actual |  |  |  | 2018-11-26 | 2019-01-30 | 2019-01-31 | 2019-04-09 | 2019-04-10
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00361 | TPSK-LSPA1-T-ME-00361 | TPSK-LSPA1-T-ME-00773 | TPSK-LSPA1-T-ME-00773 | TPSK-LSPA1-T-ME-01286 | TPSK-LSPA1-T-ME-01286
[6 empty] | Return Date |  |  | 2019-02-11 | 2019-02-11 | 2019-02-26 | 2019-02-26 | 2019-05-20 | 2019-05-20
[6 empty] | Owner Cmmt* |  |  | R2 | R2 | R1 | R1 | TP | TP
| ME | OL1-2M03-2646 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2646 - PROPANE RECYCLE PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2018-12-20
[6 empty] | Issue Actual |  |  | A: 2018-12-20
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00543; A: TPSK-LSPA1-T-ME-00543
[6 empty] | Return Date |  |  | B: 2019-01-16; A: 2019-01-16
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2647 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2647 - HP PROPYLENE / OFF SPEC PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; A: IFQ; B: IFQ
Rev. | bar: B to B
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2018-12-13; A: 2019-01-30; B: 2019-01-31
[6 empty] | Issue Actual |  |  | A: 2018-12-13; A: 2019-01-30; B: 2019-01-31
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00494; A: TPSK-LSPA1-T-ME-00494; A: TPSK-LSPA1-T-ME-00770; B: TPSK-LSPA1-T-ME-00770
[6 empty] | Return Date |  |  | B: 2019-01-14; A: 2019-01-14; A: 2019-02-21; B: 2019-02-21
Owner Cmmt* | bar: B to B
| ME | OL1-2M03-2660 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2660 - DEBUTANIZER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | B | A | C | A | B | C | D | D
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan | [5 empty] | 2018-10-23 | 2018-11-08 | 2018-12-05 | 2019-02-15 | 2019-02-15
[6 empty] | Issue Actual | [5 empty] | 2018-10-23 | 2018-11-08 | 2018-12-05 | 2019-02-15 | 2019-02-15
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00288 | TPSK-LSPA1-T-ME-00215 | TPSK-LSPA1-T-ME-00415 | TPSK-LSPA1-T-ME-00215 | TPSK-LSPA1-T-ME-00288 | TPSK-LSPA1-T-ME-00415 | TPSK-LSPA1-T-ME-00861 | TPSK-LSPA1-T-ME-00861
[6 empty] | Return Date |  |  | 2018-11-17 |  | 2018-12-27 |  | 2018-11-17 | 2018-12-27 | 2019-03-12 | 2019-03-12
Owner Cmmt* | bar: B; C; B to D
| ME | OL1-2M03-2661 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2660 - DEBUTANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2018-12-10; C: 2019-03-29; A: 2019-04-01
[6 empty] | Issue Actual |  |  | A: 2018-12-10; C: 2019-03-29; A: 2019-04-01
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00465; A: TPSK-LSPA1-T-ME-00465; C: TPSK-LSPA1-T-ME-01205; A: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date |  |  | B: 2018-12-27; A: 2018-12-27; C: 2019-05-02; A: 2019-05-02
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2662 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2660 - DEBUTANIZER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2018-12-17; C: 2019-04-30; A: 2019-05-02
[6 empty] | Issue Actual |  |  | A: 2018-12-17; C: 2019-04-30; A: 2019-05-02
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00516; A: TPSK-LSPA1-T-ME-00516; C: TPSK-LSPA1-T-ME-01535; A: TPSK-LSPA1-T-ME-01535
[6 empty] | Return Date |  |  | B: 2019-01-22; A: 2019-01-22; C: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2663 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2660 - DEBUTANIZER REFLUX / PRODUCT PUMP |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  |  | 2018-12-17 | 2019-02-07 | 2019-02-07 | 2019-04-25 | 2019-04-26
[6 empty] | Issue Actual |  |  |  | 2018-12-17 | 2019-02-07 | 2019-02-07 | 2019-04-25 | 2019-04-26
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00511 | TPSK-LSPA1-T-ME-00511 | TPSK-LSPA1-T-ME-00822 | TPSK-LSPA1-T-ME-00822 | TPSK-LSPA1-T-ME-01479 | TPSK-LSPA1-T-ME-01479
[6 empty] | Return Date |  |  | 2019-01-14 | 2019-01-14 | 2019-02-21 | 2019-02-21 | 2019-06-18 | 2019-06-18
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-2664 | Mechanical Equipment Datasheet - C5 - Pygas Feed Filters |  | Class 2 | Purpose** | IFQ | IFQ | B: IFP; A: IFP
[6 empty] | Rev. | A | A | B: 0; A: 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-25 | 2019-03-26 | B: 2019-05-15; A: 2019-05-16
[6 empty] | Issue Actual | 2019-03-25 | 2019-03-26 | B: 2019-05-15; A: 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01141 | TPSK-LSPA1-T-ME-01141 | B: TPSK-LSPA1-T-ME-01669; A: TPSK-LSPA1-T-ME-01669
[6 empty] | Return Date | 2019-04-11 | 2019-04-11 | B: 2019-06-19; A: 2019-06-19
[6 empty] | Owner Cmmt* | R1 | R1 | bar: B to A
| ME | OL1-2M03-2665 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2665 - DEBUTANIZER REBOILER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2018-12-10; C: 2019-04-10; A: 2019-04-11
[6 empty] | Issue Actual |  |  | A: 2018-12-10; C: 2019-04-10; A: 2019-04-11
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00468; A: TPSK-LSPA1-T-ME-00468; C: TPSK-LSPA1-T-ME -01313; A: TPSK-LSPA1-T-ME -01313
[6 empty] | Return Date |  |  | B: 2018-12-27; A: 2018-12-27; C: 2019-06-05; A: 2019-06-05
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2666 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2666 - DEBUTANIZER BOTTOMS COOLER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  |  | 2018-12-10 | 2019-04-12 | 2019-04-15 | 2019-05-21 | 2019-05-23
[6 empty] | Issue Actual |  |  |  | 2018-12-10 | 2019-04-12 | 2019-04-15 | 2019-05-21 | 2019-05-23
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00468 | TPSK-LSPA1-T-ME-00468 | TPSK-LSPA1-T-ME-01344 | TPSK-LSPA1-T-ME-01344 | TPSK-LSPA1-T-ME-01712 | TPSK-LSPA1-T-ME-01712
[6 empty] | Return Date |  |  | 2018-12-27 | 2018-12-27 | 2019-05-20 | 2019-05-20 |  | 2019-06-21
Owner Cmmt* | bar: B to A; C
| ME | OL1-2M03-2667 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2666 - C5 / PYGAS SURGE DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-02-15; A: 2019-02-15; C: 2019-06-04; A: 2019-06-10
[6 empty] | Issue Actual |  |  | B: 2019-02-15; A: 2019-02-15; C: 2019-06-04; A: 2019-06-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00869; A: TPSK-LSPA1-T-ME-00869; C: TPSK-LSPA1-T-ME-01803; A: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; A: 2019-07-08
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2668 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2666 - C5 / PYGAS PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | 2019-02-20 | 2019-02-20 | 2019-03-20 | 2019-03-21 | 2019-04-22 | 2019-04-23
[6 empty] | Issue Actual |  |  | 2019-02-20 | 2019-02-20 | 2019-03-20 | 2019-03-21 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00898 | TPSK-LSPA1-T-ME-00898 | TPSK-LSPA1-T-ME-01102 | TPSK-LSPA1-T-ME-01102 | TPSK-LSPA1-T-ME-01426 | TPSK-LSPA1-T-ME-01426
[6 empty] | Return Date |  |  | 2019-03-12 | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-06-18 | 2019-06-18
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-2669 | Mechanical Equipment Datasheet - Debutanizer Bottoms Pumps |  | Class 2 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2018-12-04; C: 2019-02-07; A: 2019-02-07
[6 empty] | Issue Actual |  |  | A: 2018-12-04; C: 2019-02-07; A: 2019-02-07
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00421; A: TPSK-LSPA1-T-ME-00421; C: TPSK-LSPA1-T-ME-00823; A: TPSK-LSPA1-T-ME-00823
[6 empty] | Return Date |  |  | C: 2019-03-15; A: 2019-03-15
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2700 | MECHANICAL EQUIPMENT DATA SHEET - 10-R-2700 - GHU-1 REACTOR |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-16 | 2019-02-16
[6 empty] | Revised Plan |  |  | A: 2019-02-01; C: 2019-02-04; A: 2019-04-12
[6 empty] | Issue Actual |  |  | A: 2019-02-01; C: 2019-02-04; A: 2019-04-12
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01346; A: TPSK-LSPA1-T-ME-00795; C: TPSK-LSPA1-T-ME-00795; A: TPSK-LSPA1-T-ME-01346
[6 empty] | Return Date |  |  | B: 2019-05-20; A: 2019-02-21; C: 2019-02-21; A: 2019-05-20
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2701 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2701 - GHU-1 FEED / EFFLUENT EXCHANGERS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-03-20; A: 2019-03-21; C: 2019-04-02; A: 2019-04-03
[6 empty] | Issue Actual |  |  | B: 2019-03-20; A: 2019-03-21; C: 2019-04-02; A: 2019-04-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01100; A: TPSK-LSPA1-T-ME-01100; C: TPSK-LSPA1-T-ME-01230; A: TPSK-LSPA1-T-ME-01230
[6 empty] | Return Date |  |  | C: 2019-05-09; A: 2019-05-09
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-2702 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2702 - GHU-1 S/U HEATER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-03-19; A: 2019-03-20; C: 2019-06-04; A: 2019-06-10
[6 empty] | Issue Actual |  |  | B: 2019-03-19; A: 2019-03-20; C: 2019-06-04; A: 2019-06-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01095; A: TPSK-LSPA1-T-ME-01095; C: TPSK-LSPA1-T-ME -01806; A: TPSK-LSPA1-T-ME -01806
[6 empty] | Return Date |  |  | B: 2019-04-11; A: 2019-04-11; A: 2019-07-08
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2703 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2705 - GHU-1 RECYCLE COOLER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | B | A | A | B | C | C
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  |  | 2019-02-19 | 2019-02-19 | 2019-04-16 | 2019-05-21 | 2019-05-23
[6 empty] | Issue Actual |  |  |  | 2019-02-19 | 2019-02-19 | 2019-04-16 | 2019-05-21 | 2019-05-23
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-01357 | TPSK-LSPA1-T-ME-00895 | TPSK-LSPA1-T-ME-00895 | TPSK-LSPA1-T-ME-01357 | TPSK-LSPA1-T-ME-01712 | TPSK-LSPA1-T-ME-01712
[6 empty] | Return Date |  |  | A: 2019-03-12; C: 2019-03-12; C: 2019-06-21
Owner Cmmt* | bar: A to C; C
| ME | OL1-2M03-2704 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2705 - GHU-1 RECYCLE PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | 2019-02-19 | 2019-02-19 | 2019-03-20 | 2019-03-21 | 2019-06-12 | 2019-06-14 | 2019-07-31
[6 empty] | Issue Actual |  |  | 2019-02-19 | 2019-02-19 | 2019-03-20 | 2019-03-21 | 2019-06-12 | 2019-06-14 | 2019-07-31
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00891 | TPSK-LSPA1-T-ME-00891 | TPSK-LSPA1-T-ME-01102 | TPSK-LSPA1-T-ME-01102 | TPSK-LSPA1-T-ME-01880 | TPSK-LSPA1-T-ME-01880 | TPSK-LSPA1-T-ME-02295
[6 empty] | Return Date |  |  | 2019-03-12 | 2019-03-12 | 2019-04-10 | 2019-04-10 |  | 2019-07-09
Owner Cmmt* | bar: B to A; C
| ME | OL1-2M03-2705 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2705 - GHU-1 HOT SEPARATOR |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-02-19; A: 2019-02-19; C: 2019-06-04; A: 2019-06-10
[6 empty] | Issue Actual |  |  | B: 2019-02-19; A: 2019-02-19; C: 2019-06-04; A: 2019-06-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00893; A: TPSK-LSPA1-T-ME-00893; C: TPSK-LSPA1-T-ME-01803; A: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; A: 2019-07-08
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2706 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2706 - GHU-1 COLD SEPARATOR |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-02-25; A: 2019-02-26; C: 2019-06-10; A: 2019-06-11
[6 empty] | Issue Actual |  |  | B: 2019-02-25; A: 2019-02-26; C: 2019-06-10; A: 2019-06-11
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00928; A: TPSK-LSPA1-T-ME-00928; C: TPSK-LSPA1-T-ME-01850; A: TPSK-LSPA1-T-ME-01850
[6 empty] | Return Date |  |  | B: 2019-03-15; A: 2019-03-15; A: 2019-07-08
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2707 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2706 - GHU-1 COOLER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-02-25; A: 2019-02-26; C: 2019-04-24; A: 2019-04-25
[6 empty] | Issue Actual |  |  | B: 2019-02-25; A: 2019-02-26; C: 2019-04-24; A: 2019-04-25
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00927; A: TPSK-LSPA1-T-ME-00927; C: TPSK-LSPA1-T-ME -01467; A: TPSK-LSPA1-T-ME -01467
[6 empty] | Return Date |  |  | B: 2019-03-15; A: 2019-03-15; C: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2710 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2710 - DEPENTANIZER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | B: 2019-02-06; A: 2019-02-06; C: 2019-05-06; A: 2019-05-07
[6 empty] | Issue Actual |  |  | B: 2019-02-06; A: 2019-02-06; C: 2019-05-06; A: 2019-05-07
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00805; A: TPSK-LSPA1-T-ME-00805; C: TPSK-LSPA1-T-ME -01588; A: TPSK-LSPA1-T-ME -01588
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; A: 2019-07-17
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2711 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2710 -DEPENTANIZER CONDENSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-02-21; A: 2019-02-22; C: 2019-04-15; A: 2019-04-16
[6 empty] | Issue Actual |  |  | B: 2019-02-21; A: 2019-02-22; C: 2019-04-15; A: 2019-04-16
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00908; A: TPSK-LSPA1-T-ME-00908; C: TPSK-LSPA1-T-ME-01362; A: TPSK-LSPA1-T-ME-01362
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; C: 2019-05-24; A: 2019-05-24
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2712 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2710 - DEPENTANIZER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-02-15; A: 2019-02-15; C: 2019-06-10; A: 2019-06-11
[6 empty] | Issue Actual |  |  | B: 2019-02-15; A: 2019-02-15; C: 2019-06-10; A: 2019-06-11
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00874; A: TPSK-LSPA1-T-ME-00874; C: TPSK-LSPA1-T-ME-01850; A: TPSK-LSPA1-T-ME-01850
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; A: 2019-07-08
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2713 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2710 - DEPENTANIZER REFLUX PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-02-19; A: 2019-02-19; C: 2019-03-20; A: 2019-03-21
[6 empty] | Issue Actual |  |  | B: 2019-02-19; A: 2019-02-19; C: 2019-03-20; A: 2019-03-21
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00891; A: TPSK-LSPA1-T-ME-00891; C: TPSK-LSPA1-T-ME-01102; A: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; C: 2019-04-10; A: 2019-04-10
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2714 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2714 - C5 CUT PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-02-19; A: 2019-02-19; C: 2019-04-08; A: 2019-04-09
[6 empty] | Issue Actual |  |  | B: 2019-02-19; A: 2019-02-19; C: 2019-04-08; A: 2019-04-09
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00891; A: TPSK-LSPA1-T-ME-00891; C: TPSK-LSPA1-T-ME-01279; A: TPSK-LSPA1-T-ME-01279
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; C: 2019-05-16; A: 2019-05-16
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2715 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2715 - DEPENTANIZER REBOILER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | 2019-02-21 | 2019-02-22 | 2019-04-15 | 2019-04-16 | 2019-05-16 | 2019-05-17
[6 empty] | Issue Actual |  |  | 2019-02-21 | 2019-02-22 | 2019-04-15 | 2019-04-16 | 2019-05-16 | 2019-05-17
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00908 | TPSK-LSPA1-T-ME-00908 | TPSK-LSPA1-T-ME-01362 | TPSK-LSPA1-T-ME-01362 | TPSK-LSPA1-T-ME-01685 | TPSK-LSPA1-T-ME-01685
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; C: 2019-06-21
Owner Cmmt* | bar: B to A; C
| ME | OL1-2M03-2716 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2714 - C5 CUT COOLER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-01-29 | 2019-01-29
[6 empty] | Revised Plan |  |  | B: 2019-02-15; A: 2019-02-15; C: 2019-05-24; A: 2019-05-27
[6 empty] | Issue Actual |  |  | B: 2019-02-15; A: 2019-02-15; C: 2019-05-24; A: 2019-05-27
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00872; A: TPSK-LSPA1-T-ME-00872; C: TPSK-LSPA1-T-ME-01743; A: TPSK-LSPA1-T-ME-01743
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; A: 2019-06-21
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2718 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2720 - RERUN TOWER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-02-15; A: 2019-02-15; C: 2019-06-04; A: 2019-06-10
[6 empty] | Issue Actual |  |  | B: 2019-02-15; A: 2019-02-15; C: 2019-06-04; A: 2019-06-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00869; A: TPSK-LSPA1-T-ME-00869; C: TPSK-LSPA1-T-ME-01803; A: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; A: 2019-07-08
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2719 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2720 - RERUN TOWER REFLUX / PRODUCT PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-02-19; A: 2019-02-19; C: 2019-04-26; A: 2019-04-29
[6 empty] | Issue Actual |  |  | B: 2019-02-19; A: 2019-02-19; C: 2019-04-26; A: 2019-04-29
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00891; A: TPSK-LSPA1-T-ME-00891; C: TPSK-LSPA1-T-ME-01493; A: TPSK-LSPA1-T-ME-01493
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; C: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2720 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2720 - RERUN TOWER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | A: 2019-01-28; C: 2019-04-17; A: 2019-04-18
[6 empty] | Issue Actual |  |  | A: 2019-01-28; C: 2019-04-17; A: 2019-04-18
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00741; A: TPSK-LSPA1-T-ME-00741; C: TPSK-LSPA1-T-ME-01399; A: TPSK-LSPA1-T-ME-01399
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2721 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2720 - RERUN TOWER CONDENSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-02-28; A: 2019-03-01
[6 empty] | Issue Actual |  |  | B: 2019-02-28; A: 2019-03-01
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME -00956; A: TPSK-LSPA1-T-ME -00956
[6 empty] | Return Date |  |  | B: 2019-03-25; A: 2019-03-25
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2723 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2724 - WASH OIL CONDENSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-01-29 | 2019-01-29
[6 empty] | Revised Plan |  |  | B: 2019-02-25; A: 2019-02-26; C: 2019-05-24; A: 2019-05-27
[6 empty] | Issue Actual |  |  | B: 2019-02-25; A: 2019-02-26; C: 2019-05-24; A: 2019-05-27
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00929; A: TPSK-LSPA1-T-ME-00929; C: TPSK-LSPA1-T-ME-01743; A: TPSK-LSPA1-T-ME-01743
[6 empty] | Return Date |  |  | B: 2019-03-15; A: 2019-03-15; A: 2019-06-21
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2724 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2724 - WASH OIL DEGASSING DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-02-15; A: 2019-02-15; C: 2019-06-04; A: 2019-06-10
[6 empty] | Issue Actual |  |  | B: 2019-02-15; A: 2019-02-15; C: 2019-06-04; A: 2019-06-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00869; A: TPSK-LSPA1-T-ME-00869; C: TPSK-LSPA1-T-ME-01803; A: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; A: 2019-07-08
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2725 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2725 - RERUN TOWER REBOILER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-16; A: 2019-05-17
[6 empty] | Issue Actual |  |  | B: 2019-05-16; A: 2019-05-17
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01685; A: TPSK-LSPA1-T-ME-01685
[6 empty] | Return Date |  |  | A: 2019-06-21
Owner Cmmt* | bar: A
| ME | OL1-2M03-2726 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2726 - PYGAS FUEL OIL PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-02-20; A: 2019-02-20; C: 2019-04-30; A: 2019-05-02
[6 empty] | Issue Actual |  |  | B: 2019-02-20; A: 2019-02-20; C: 2019-04-30; A: 2019-05-02
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00898; A: TPSK-LSPA1-T-ME-00898; C: TPSK-LSPA1-T-ME-01524; A: TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date |  |  | B: 2019-03-19; A: 2019-03-19; C: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2727 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2726 - PYGAS FUEL OIL COOLER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-01-29 | 2019-01-29
[6 empty] | Revised Plan |  |  | B: 2019-02-20; A: 2019-02-20; C: 2019-05-24; A: 2019-05-27
[6 empty] | Issue Actual |  |  | B: 2019-02-20; A: 2019-02-20; C: 2019-05-24; A: 2019-05-27
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00897; A: TPSK-LSPA1-T-ME-00897; C: TPSK-LSPA1-T-ME-01743; A: TPSK-LSPA1-T-ME-01743
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; A: 2019-06-21
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2728 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2724 - RECYCLE WASH OIL PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-02-19; A: 2019-02-19; C: 2019-04-30; A: 2019-05-02
[6 empty] | Issue Actual |  |  | B: 2019-02-19; A: 2019-02-19; C: 2019-04-30; A: 2019-05-02
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00891; A: TPSK-LSPA1-T-ME-00891; C: TPSK-LSPA1-T-ME-01524; A: TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; C: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2729 | Mechanical Equipment Datasheet - Wash Oil Pumps |  | Class 2 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27 | 2019-01-17
[6 empty] | Revised Plan |  |  | 2019-02-20 | 2019-02-20 | 2019-04-09 | 2019-04-10 | 2019-04-30 | 2019-05-02
[6 empty] | Issue Actual |  |  | 2019-02-20 | 2019-02-20 | 2019-04-09 | 2019-04-10 | 2019-04-30 | 2019-05-02
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00898 | TPSK-LSPA1-T-ME-00898 | TPSK-LSPA1-T-ME-01287 | TPSK-LSPA1-T-ME-01287 | TPSK-LSPA1-T-ME-01524 | TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; B: 2019-06-18; C: 2019-06-18
Owner Cmmt* | bar: B to A; B to C
| ME | OL1-2M03-2730 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2730 - HYDROG REGEN HEATER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-04-18; A: 2019-04-19
[6 empty] | Issue Actual |  |  | B: 2019-04-18; A: 2019-04-19
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01410; A: TPSK-LSPA1-T-ME-01410
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2735 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2735 - REGEN HYDROG DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-04-04; A: 2019-04-05
[6 empty] | Issue Actual |  |  | B: 2019-04-04; A: 2019-04-05
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01253; A: TPSK-LSPA1-T-ME-01253
[6 empty] | Return Date |  |  | B: 2019-06-05; A: 2019-06-05
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2750 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2750 - C4 / C5 HYDROG SURGE DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-02-15; A: 2019-02-15; C: 2019-06-06; A: 2019-06-10
[6 empty] | Issue Actual |  |  | B: 2019-02-15; A: 2019-02-15; C: 2019-06-06; A: 2019-06-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00869; A: TPSK-LSPA1-T-ME-00869; C: TPSK-LSPA1-T-ME-01817; A: TPSK-LSPA1-T-ME-01817
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; A: 2019-07-08
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2751 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2750 - C4 / C5 HYDROG FEED PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | 2019-02-07 | 2019-02-07 | 2019-03-20 | 2019-03-21 | 2019-05-09 | 2019-05-10
[6 empty] | Issue Actual |  |  | 2019-02-07 | 2019-02-07 | 2019-03-20 | 2019-03-21 | 2019-05-09 | 2019-05-10
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00817 | TPSK-LSPA1-T-ME-00817 | TPSK-LSPA1-T-ME-01102 | TPSK-LSPA1-T-ME-01102 | TPSK-LSPA1-T-ME-01626 | TPSK-LSPA1-T-ME-01626
[6 empty] | Return Date |  |  | 2019-03-15 | 2019-03-15 | 2019-04-10 | 2019-04-10 | 2019-06-18 | 2019-06-18
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-2755 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2755 - C4 / C5 HYDROG S/U HEATER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-03-19; A: 2019-03-20; C: 2019-04-29; A: 2019-04-30
[6 empty] | Issue Actual |  |  | B: 2019-03-19; A: 2019-03-20; C: 2019-04-29; A: 2019-04-30
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01095; A: TPSK-LSPA1-T-ME-01095; C: TPSK-LSPA1-T-ME-01514; A: TPSK-LSPA1-T-ME-01514
[6 empty] | Return Date |  |  | B: 2019-04-11; A: 2019-04-11; C: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2760 | MECHANICAL EQUIPMENT DATA SHEET - 10-R-2760 - C4 / C5 HYDROG REACTOR |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-16 | 2019-02-16
[6 empty] | Revised Plan |  |  | A: 2019-02-01; C: 2019-02-04; A: 2019-04-12
[6 empty] | Issue Actual |  |  | A: 2019-02-01; C: 2019-02-04; A: 2019-04-12
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME -01346; A: TPSK-LSPA1-T-ME-00795; C: TPSK-LSPA1-T-ME-00795; A: TPSK-LSPA1-T-ME -01346
[6 empty] | Return Date |  |  | B: 2019-05-20; A: 2019-02-21; C: 2019-02-21; A: 2019-05-20
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2762 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2760 - C4 / C5 HYDROG RECYCLE DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-02-15; A: 2019-02-15; C: 2019-06-06; A: 2019-06-10
[6 empty] | Issue Actual |  |  | B: 2019-02-15; A: 2019-02-15; C: 2019-06-06; A: 2019-06-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00869; A: TPSK-LSPA1-T-ME-00869; C: TPSK-LSPA1-T-ME-01817; A: TPSK-LSPA1-T-ME-01817
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; A: 2019-07-08
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2763 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2760 - C4 / C5 HYDROG VENT CONDENSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-03-15; A: 2019-03-18; C: 2019-03-29; A: 2019-04-01
[6 empty] | Issue Actual |  |  | B: 2019-03-15; A: 2019-03-18; C: 2019-03-29; A: 2019-04-01
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01075; A: TPSK-LSPA1-T-ME-01075; C: TPSK-LSPA1-T-ME-01205; A: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date |  |  | B: 2019-05-02; A: 2019-05-02; C: 2019-05-02; A: 2019-05-02
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2764 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2760 - C4 / C5 HYDROG RECYCLE PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C | D
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | 2019-02-07 | 2019-02-07 | 2019-03-20 | 2019-03-21 | 2019-06-12 | 2019-06-14 | 2019-07-31
[6 empty] | Issue Actual |  |  | 2019-02-07 | 2019-02-07 | 2019-03-20 | 2019-03-21 | 2019-06-12 | 2019-06-14 | 2019-07-31
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00817 | TPSK-LSPA1-T-ME-00817 | TPSK-LSPA1-T-ME-01102 | TPSK-LSPA1-T-ME-01102 | TPSK-LSPA1-T-ME-01880 | TPSK-LSPA1-T-ME-01880 | TPSK-LSPA1-T-ME-02295
[6 empty] | Return Date |  |  | 2019-03-15 | 2019-03-15 | 2019-04-10 | 2019-04-10 |  | 2019-07-09
Owner Cmmt* | bar: B to A; C
| ME | OL1-2M03-2765 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2765 - C4 / C5 HYDROG RECYCLE COOLER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  |  | 2019-03-05 | 2019-04-03 | 2019-04-04 | 2019-05-21 | 2019-05-23
[6 empty] | Issue Actual |  |  |  | 2019-03-05 | 2019-04-03 | 2019-04-04 | 2019-05-21 | 2019-05-23
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00991 | TPSK-LSPA1-T-ME-00991 | TPSK-LSPA1-T-ME -01242 | TPSK-LSPA1-T-ME -01242 | TPSK-LSPA1-T-ME-01712 | TPSK-LSPA1-T-ME-01712
[6 empty] | Return Date |  |  | B: 2019-03-29; A: 2019-03-29; C: 2019-06-21
Owner Cmmt* | bar: B to A; C
| ME | OL1-2M03-2790 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2790 - LIGHT OIL DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-08; C: 2019-05-30; A: 2019-05-31
[6 empty] | Issue Actual |  |  | A: 2019-01-08; C: 2019-05-30; A: 2019-05-31
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00607; A: TPSK-LSPA1-T-ME-00607; C: TPSK-LSPA1-T-ME-01780; A: TPSK-LSPA1-T-ME-01780
[6 empty] | Return Date |  |  | B: 2019-01-28; A: 2019-01-28; A: 2019-06-21
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2791 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2790 - LIGHT OIL DRAIN DRUM PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2018-12-17; C: 2019-04-26; A: 2019-04-29
[6 empty] | Issue Actual |  |  | A: 2018-12-17; C: 2019-04-26; A: 2019-04-29
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00515; A: TPSK-LSPA1-T-ME-00515; C: TPSK-LSPA1-T-ME-01493; A: TPSK-LSPA1-T-ME-01493
[6 empty] | Return Date |  |  | B: 2019-01-14; A: 2019-01-14; C: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2800 | MECHANICAL EQUIPMENT DATA SHEET - 10-C-2800 - PROPYLENE REFRIG COMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | B: IFA; A: IFD; C: IFQ; A: IFQ
[6 empty] | Rev. |  | A | bar: B; C to A
[6 empty] | Issue Plan | 2018-09-13 |  | A: 2018-10-04
[6 empty] | Revised Plan |  | 2018-09-10 | B: 2018-09-11; C: 2018-10-03; A: 2018-10-04
[6 empty] | Issue Actual |  | 2018-09-10 | B: 2018-09-11; C: 2018-10-03; A: 2018-10-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00038 | B: TPSK-LSPA1-T-ME-00038; C: TPSK-LSPA1-T-ME-00127; A: TPSK-LSPA1-T-ME-00127
[6 empty] | Return Date |  | 2018-09-28 | B: 2018-09-28
[6 empty] | Owner Cmmt* |  | A3 | bar: B
| ME | OL1-2M03-2801 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2805 - PROPYLENE PRODUCT PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2018-12-20; C: 2019-03-12; A: 2019-03-13
[6 empty] | Issue Actual |  |  | A: 2018-12-20; C: 2019-03-12; A: 2019-03-13
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00543; A: TPSK-LSPA1-T-ME-00543; C: TPSK-LSPA1-T-ME-01035; A: TPSK-LSPA1-T-ME-01035
[6 empty] | Return Date |  |  | B: 2019-01-16; A: 2019-01-16; C: 2019-03-29; A: 2019-03-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2805 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2805 - C3R SURGE DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2018-12-13; C: 2019-03-28; A: 2019-03-29
[6 empty] | Issue Actual |  |  | A: 2018-12-13; C: 2019-03-28; A: 2019-03-29
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00483; A: TPSK-LSPA1-T-ME-00483; C: TPSK-LSPA1-T-ME-01186; A: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date |  |  | B: 2019-01-22; A: 2019-01-22; C: 2019-05-02; A: 2019-05-02
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2806 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2805 - C3R CONDENSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-17; C: 2019-03-21; A: 2019-03-22
[6 empty] | Issue Actual |  |  | A: 2019-01-17; C: 2019-03-21; A: 2019-03-22
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00671; A: TPSK-LSPA1-T-ME-00671; C: TPSK-LSPA1-T-ME-01123; A: TPSK-LSPA1-T-ME-01123
[6 empty] | Return Date |  |  | B: 2019-02-11; A: 2019-02-11; C: 2019-04-11; A: 2019-04-11
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2807 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2807 - C3 CHILLER NO. 1 |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2018-12-14; C: 2019-04-11; A: 2019-04-12
[6 empty] | Issue Actual |  |  | A: 2018-12-14; C: 2019-04-11; A: 2019-04-12
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00505; A: TPSK-LSPA1-T-ME-00505; C: TPSK-LSPA1-T-ME-01324; A: TPSK-LSPA1-T-ME-01324
[6 empty] | Return Date |  |  | B: 2019-01-22; A: 2019-01-22; C: 2019-05-20; A: 2019-05-20
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2809 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2809 - C3 CHILLER NO. 2 |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2018-12-14; C: 2019-04-11; A: 2019-04-12
[6 empty] | Issue Actual |  |  | A: 2018-12-14; C: 2019-04-11; A: 2019-04-12
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00505; A: TPSK-LSPA1-T-ME-00505; C: TPSK-LSPA1-T-ME-01324; A: TPSK-LSPA1-T-ME-01324
[6 empty] | Return Date |  |  | B: 2019-01-22; A: 2019-01-22; C: 2019-05-20; A: 2019-05-20
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2810 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2810 - C3R 1ST STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2018-12-13; C: 2019-06-04; A: 2019-06-10
[6 empty] | Issue Actual |  |  | A: 2018-12-13; C: 2019-06-04; A: 2019-06-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00483; A: TPSK-LSPA1-T-ME-00483; C: TPSK-LSPA1-T-ME-01803; A: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date |  |  | B: 2019-01-22; A: 2019-01-22; A: 2019-07-08
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2815 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2815 - C3R DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-08; C: 2019-05-30; A: 2019-05-31
[6 empty] | Issue Actual |  |  | A: 2019-01-08; C: 2019-05-30; A: 2019-05-31
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00607; A: TPSK-LSPA1-T-ME-00607; C: TPSK-LSPA1-T-ME-01783; A: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date |  |  | B: 2019-01-28; A: 2019-01-28; A: 2019-06-21
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2816 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2815 - PROPYLENE REFRIG RECOVERY PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2018-12-20; C: 2019-02-07; A: 2019-02-07
[6 empty] | Issue Actual |  |  | A: 2018-12-20; C: 2019-02-07; A: 2019-02-07
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00543; A: TPSK-LSPA1-T-ME-00543; C: TPSK-LSPA1-T-ME-00822; A: TPSK-LSPA1-T-ME-00822
[6 empty] | Return Date |  |  | B: 2019-01-16; A: 2019-01-16; C: 2019-02-21; A: 2019-02-21
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2820 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2820 - C3R 2ND STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2018-12-13; C: 2019-06-04; A: 2019-06-10
[6 empty] | Issue Actual |  |  | A: 2018-12-13; C: 2019-06-04; A: 2019-06-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00483; A: TPSK-LSPA1-T-ME-00483; C: TPSK-LSPA1-T-ME-01803; A: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date |  |  | B: 2019-01-22; A: 2019-01-22; A: 2019-07-08
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2830 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2830 - C3R 3RD STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2018-12-13
[6 empty] | Issue Actual |  |  | A: 2018-12-13
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00483; A: TPSK-LSPA1-T-ME-00483
[6 empty] | Return Date |  |  | B: 2019-01-22; A: 2019-01-22
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2840 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2840 - C3R 4TH STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2018-12-10
[6 empty] | Issue Actual |  |  | A: 2018-12-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00460; A: TPSK-LSPA1-T-ME-00460
[6 empty] | Return Date |  |  | B: 2018-12-27; A: 2018-12-27
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2850 | MECHANICAL EQUIPMENT DATA SHEET - 10-C-2850 - ETHYLENE REFRIG COMPRESSOR |  | Class 1 | Purpose** | IFR | IFA | B: IFA; A: IFD; C: IFQ; A: IFQ
[6 empty] | Rev. |  | A | bar: B; C to A
[6 empty] | Issue Plan | 2018-09-13 |  | A: 2018-10-04
[6 empty] | Revised Plan |  | 2018-09-10 | B: 2018-09-11; C: 2018-10-03; A: 2018-10-04
[6 empty] | Issue Actual |  | 2018-09-10 | B: 2018-09-11; C: 2018-10-03; A: 2018-10-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00038 | B: TPSK-LSPA1-T-ME-00038; C: TPSK-LSPA1-T-ME-00127; A: TPSK-LSPA1-T-ME-00127
[6 empty] | Return Date |  | 2018-09-28 | B: 2018-09-28; C: 2018-10-26; A: 2018-10-26
[6 empty] | Owner Cmmt* |  | A3 | bar: B; C to A
| ME | OL1-2M03-2852 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2852 - C2R DESUPERHEATER NO. 1 |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2018-12-14; C: 2019-04-10; A: 2019-04-11
[6 empty] | Issue Actual |  |  | A: 2018-12-14; C: 2019-04-10; A: 2019-04-11
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00505; A: TPSK-LSPA1-T-ME-00505; C: TPSK-LSPA1-T-ME-01311; A: TPSK-LSPA1-T-ME-01311
[6 empty] | Return Date |  |  | B: 2019-01-22; A: 2019-01-22
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2853 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2852 - C2R DESUPERHEATER NO. 2 |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2018-12-20; C: 2019-04-10; A: 2019-04-11
[6 empty] | Issue Actual |  |  | A: 2018-12-20; C: 2019-04-10; A: 2019-04-11
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00541; A: TPSK-LSPA1-T-ME-00541; C: TPSK-LSPA1-T-ME -01313; A: TPSK-LSPA1-T-ME -01313
[6 empty] | Return Date |  |  | B: 2019-01-22; A: 2019-01-22; C: 2019-06-05; A: 2019-06-05
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2854 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2855 - C2R SURGE DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-11
[6 empty] | Issue Actual |  |  | A: 2019-01-11
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00638; A: TPSK-LSPA1-T-ME-00638
[6 empty] | Return Date |  |  | B: 2019-01-31; A: 2019-01-31
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2855 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2855 - ETHYLENE PRODUCT PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2018-12-13; C: 2019-03-12; A: 2019-03-13
[6 empty] | Issue Actual |  |  | A: 2018-12-13; C: 2019-03-12; A: 2019-03-13
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00494; A: TPSK-LSPA1-T-ME-00494; C: TPSK-LSPA1-T-ME-01035; A: TPSK-LSPA1-T-ME-01035
[6 empty] | Return Date |  |  | B: 2019-01-14; A: 2019-01-14; C: 2019-03-29; A: 2019-03-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2856 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2855 - C2R CONDENSER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  |  | 2018-11-14 | 2019-01-30 | 2019-01-31 | 2019-03-29 | 2019-04-01
[6 empty] | Issue Actual |  |  |  | 2018-11-14 | 2019-01-30 | 2019-01-31 | 2019-03-29 | 2019-04-01
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00316 | TPSK-LSPA1-T-ME-00316 | TPSK-LSPA1-T-ME-00773 | TPSK-LSPA1-T-ME-00773 | TPSK-LSPA1-T-ME-01205 | TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date |  |  | 2019-02-04 | 2019-02-04 | 2019-02-26 | 2019-02-26 | 2019-05-02 | 2019-05-02
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-2857 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2857 - HP ETHYLENE PRODUCT VAPORIZER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  |  | 2018-11-13 | 2019-01-30 | 2019-01-31 | 2019-04-03 | 2019-04-04
[6 empty] | Issue Actual |  |  |  | 2018-11-13 | 2019-01-30 | 2019-01-31 | 2019-04-03 | 2019-04-04
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00312 | TPSK-LSPA1-T-ME-00312 | TPSK-LSPA1-T-ME-00773 | TPSK-LSPA1-T-ME-00773 | TPSK-LSPA1-T-ME-01246 | TPSK-LSPA1-T-ME-01246
[6 empty] | Return Date |  |  | 2019-02-11 | 2019-02-11 | 2019-02-26 | 2019-02-26 | 2019-05-20 | 2019-05-20
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-2858 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2858 - HP ETHYLENE PRODUCT SUPERHEATER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-22; C: 2019-04-04; A: 2019-04-05
[6 empty] | Issue Actual |  |  | A: 2019-01-22; C: 2019-04-04; A: 2019-04-05
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00684; A: TPSK-LSPA1-T-ME-00684; C: TPSK-LSPA1-T-ME-01256; A: TPSK-LSPA1-T-ME-01256
[6 empty] | Return Date |  |  | B: 2019-02-11; A: 2019-02-11; C: 2019-06-05; A: 2019-06-05
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2859 | Mechanical Equipment Data Sheet - 10-E-2856 - Ethylene Product Subcooler |  | Class 2 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-16 | 2019-02-16
[6 empty] | Revised Plan |  |  | A: 2018-12-20; C: 2019-04-03; A: 2019-04-03
[6 empty] | Issue Actual |  |  | A: 2018-12-20; C: 2019-04-03; A: 2019-04-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00541; A: TPSK-LSPA1-T-ME-00541; C: TPSK-LSPA1-T-ME -01234; A: TPSK-LSPA1-T-ME -01234
[6 empty] | Return Date |  |  | B: 2019-02-11; A: 2019-02-11; C: 2019-05-09; A: 2019-05-09
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2860 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2860 - C2R 1ST STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2018-12-20; C: 2019-05-30; A: 2019-05-31
[6 empty] | Issue Actual |  |  | A: 2018-12-20; C: 2019-05-30; A: 2019-05-31
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00553; A: TPSK-LSPA1-T-ME-00553; C: TPSK-LSPA1-T-ME-01783; A: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date |  |  | B: 2019-01-24; A: 2019-01-24; A: 2019-06-21
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2865 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2865 - C2R DRAIN DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-08; C: 2019-05-30; A: 2019-05-31
[6 empty] | Issue Actual |  |  | A: 2019-01-08; C: 2019-05-30; A: 2019-05-31
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00607; A: TPSK-LSPA1-T-ME-00607; C: TPSK-LSPA1-T-ME-01783; A: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date |  |  | B: 2019-01-28; A: 2019-01-28; A: 2019-06-21
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2870 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2870 - C2R 2ND STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-17; C: 2019-03-28; A: 2019-03-29
[6 empty] | Issue Actual |  |  | A: 2019-01-17; C: 2019-03-28; A: 2019-03-29
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00670; A: TPSK-LSPA1-T-ME-00670; C: TPSK-LSPA1-T-ME-01186; A: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date |  |  | B: 2019-02-11; A: 2019-02-11; C: 2019-05-02; A: 2019-05-02
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2880 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2880 - C2R 3RD STAGE SUCTION DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | B | A | A | B | C | C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | C: 2018-12-10; A: 2019-01-23; B: 2019-05-22; C: 2019-05-23
[6 empty] | Issue Actual |  |  | C: 2018-12-10; A: 2019-01-23; B: 2019-05-22; C: 2019-05-23
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00708 | TPSK-LSPA1-T-ME-00460 | TPSK-LSPA1-T-ME-00460 | TPSK-LSPA1-T-ME-00708 | TPSK-LSPA1-T-ME-01723 | TPSK-LSPA1-T-ME-01723
[6 empty] | Return Date |  |  | 2019-02-21 | 2018-12-27 | 2018-12-27 | 2019-02-21 |  | 2019-06-21
Owner Cmmt* | bar: B to A; C
| ME | OL1-2M03-2900 | MECHANICAL EQUIPMENT DATASHEET FOR pH CTRL / CORROSION INHIBITOR INJECTION PACKAGE TAG: 10-PK-2900 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01490 | TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-2902 | MECHANICAL EQUIPMENT DATASHEET FOR EMULSION BREAKER INJECTION PACKAGE TAG: 10-PK-2902 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01490 | TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-2904 | MECHANICAL EQUIPMENT DATASHEET FOR PROCESS WATER STRIPPER CHEMICAL INJECTION PACKAGE TAG: 10-PK-2904 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01490 | TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-2906 | MECHANICAL EQUIPMENT DATASHEET FOR DSG ANTI-FOULANT INJECTION PACKAGE TAG: 10-PK-2906 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01490 | TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-2910 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-2910 - WASH OIL DAY TANK |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-18 | 2019-02-26
[6 empty] | Revised Plan |  |  | C: 2019-01-28; A: 2019-04-23
[6 empty] | Issue Actual |  |  | C: 2019-01-28; A: 2019-04-23
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00745; A: TPSK-LSPA1-T-ME-01449; C: TPSK-LSPA1-T-ME-00745; A: TPSK-LSPA1-T-ME-01449
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-06-18; C: 2019-02-21; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2911 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2910 - WASH OIL INJECTION PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2018-12-27 | 2019-01-17
[6 empty] | Revised Plan |  |  | B: 2019-02-25; A: 2019-02-26; C: 2019-04-08; A: 2019-04-09
[6 empty] | Issue Actual |  |  | B: 2019-02-25; A: 2019-02-26; C: 2019-04-08; A: 2019-04-09
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00925; A: TPSK-LSPA1-T-ME-00925; C: TPSK-LSPA1-T-ME-01279; A: TPSK-LSPA1-T-ME-01279
[6 empty] | Return Date |  |  | B: 2019-03-12; A: 2019-03-12; C: 2019-05-16; A: 2019-05-16
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2912 | MECHANICAL EQUIPMENT DATASHEET FOR CAUSTIC TOWER ANTI-FOULANT INJECTION PACKAGE TAG: 10-PK-2912 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01490 | TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-2913 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-29012 - Start-up |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-02144 | TPSK-LSPA1-T-ME-02144
Return Date
Owner Cmmt*
| ME | OL1-2M03-2915 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-29015 - Start-up |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-02143 | TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date |  | 2019-08-01
[6 empty] | Owner Cmmt* |  | R1
| ME | OL1-2M03-2920 | MECHANICAL EQUIPMENT DATASHEET FOR POLYMERIZATION INHIBITOR INJECTION PACKAGE TAG: 10-PK-2920 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01490 | TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2M03-2921 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-29021 - Start-up |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-02143 | TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date |  | 2019-08-01
[6 empty] | Owner Cmmt* |  | R1
| ME | OL1-2M03-2926 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-29026 - Start-up |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-02143 | TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date |  | 2019-08-01
[6 empty] | Owner Cmmt* |  | R1
| ME | OL1-2M03-2931 | MECHANICAL EQUIPMENT DATASHEET FOR PROPANOL INJECTION PACKAGE TAG: 10-PK-2931 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01490 | TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2M03-2932 | Mechanical Equipment Data Sheet - Methanol Drum |  | Class 2 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-23; C: 2019-06-04; A: 2019-06-10
[6 empty] | Issue Actual |  |  | A: 2019-01-23; C: 2019-06-04; A: 2019-06-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00709; A: TPSK-LSPA1-T-ME-00709; C: TPSK-LSPA1-T-ME-01803; A: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; A: 2019-07-08
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-2934 | Mechanical Equipment Datasheet - Methanol Injection Pump |  | Class 2 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2018-12-27 | 2019-01-17
[6 empty] | Revised Plan |  |  | A: 2019-01-24; C: 2019-03-20; A: 2019-03-21
[6 empty] | Issue Actual |  |  | A: 2019-01-24; C: 2019-03-20; A: 2019-03-21
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00716; A: TPSK-LSPA1-T-ME-00716; C: TPSK-LSPA1-T-ME-01102; A: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; C: 2019-04-10; A: 2019-04-10
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-2940 | MECHANICAL EQUIPMENT DATASHEET FOR C4 POLYMER INHIBITOR INJECTION PACKAGE TAG: 10-PK-2940 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01490 | TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2M03-2945 | MECHANICAL EQUIPMENT DATASHEET FOR ANTI-OXIDANT INJECTION PACKAGE TAG: 10-PK-2945 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16 | 2019-05-17
[6 empty] | Issue Actual | 2019-05-16 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01673 | TPSK-LSPA1-T-ME-01673
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2M03-3000 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3000 - PREDISTILLATION TOWER |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | 2019-04-08 | 2019-04-09 | 2019-06-11 | 2019-06-11 | 2019-06-18 | 2019-06-18
[6 empty] | Issue Actual |  |  | 2019-04-08 | 2019-04-09 | 2019-06-11 | 2019-06-11 | 2019-06-18 | 2019-06-18
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-01275 | TPSK-LSPA1-T-ME-01275 | TPSK-LSPA1-T-ME-01870 | TPSK-LSPA1-T-ME-01870 | TPSK-LSPA1-T-ME-01909 | TPSK-LSPA1-T-ME-01909
[6 empty] | Return Date |  |  | B: 2019-05-20; A: 2019-05-20; A: 2019-07-08
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-3001 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3000 - PREDISTILLATION CONDENSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3002 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3002 - PREDISTILLATION FEED PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-10; A: 2019-05-13; C: 2019-08-15
[6 empty] | Issue Actual |  |  | B: 2019-05-10; A: 2019-05-13; C: 2019-08-15
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME -01645; A: TPSK-LSPA1-T-ME -01645; C: TPSK-LSPA1-T-ME-02437
[6 empty] | Return Date |  |  | B: 2019-06-03; A: 2019-06-03
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3003 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3000 - PREDISTILLATION REFLUX PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-10; A: 2019-05-13
[6 empty] | Issue Actual |  |  | B: 2019-05-10; A: 2019-05-13
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME -01645; A: TPSK-LSPA1-T-ME -01645
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3004 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3004 - PREDISTILLATION TRIM REBOILER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3005 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3005 - PREDISTILLATION REBOILER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3006 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3000 - PREDISTILLATION REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-04-16; A: 2019-04-17; C: 2019-06-18; A: 2019-06-18
[6 empty] | Issue Actual |  |  | B: 2019-04-16; A: 2019-04-17; C: 2019-06-18; A: 2019-06-18
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01370; A: TPSK-LSPA1-T-ME-01370; C: TPSK-LSPA1-T-ME-01910; A: TPSK-LSPA1-T-ME-01910
[6 empty] | Return Date |  |  | B: 2019-06-17; A: 2019-06-17; C: 2019-07-15; A: 2019-07-15
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3007 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3002 - PREDISTILLATION FEED DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-04-15; A: 2019-04-16; C: 2019-06-18; A: 2019-06-18
[6 empty] | Issue Actual |  |  | B: 2019-04-15; A: 2019-04-16; C: 2019-06-18; A: 2019-06-18
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01363; A: TPSK-LSPA1-T-ME-01363; C: TPSK-LSPA1-T-ME-01910; A: TPSK-LSPA1-T-ME-01910
[6 empty] | Return Date |  |  | C: 2019-07-15; A: 2019-07-15
Owner Cmmt* | bar: C to A
| ME | OL1-2M03-3010 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3010 - C4 FEED DRUM |  | Class 1 | Purpose** | IFQ | IFQ | B: IFQ; A: IFQ; C: IFQ; A: IFQ
[6 empty] | Rev. | A | A | bar: B to A
Issue Plan
[6 empty] | Revised Plan |  | 2019-04-08 | B: 2019-06-06; A: 2019-06-10; C: 2019-06-18; A: 2019-06-18
[6 empty] | Issue Actual |  | 2019-04-08 | B: 2019-06-06; A: 2019-06-10; C: 2019-06-18; A: 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01275 | TPSK-LSPA1-T-ME-01275 | B: TPSK-LSPA1-T-ME-01818; A: TPSK-LSPA1-T-ME-01818; C: TPSK-LSPA1-T-ME-01909; A: TPSK-LSPA1-T-ME-01909
[6 empty] | Return Date | 2019-05-20 | 2019-05-20 | A: 2019-07-08
[6 empty] | Owner Cmmt* | R1 | R1 | bar: A
| ME | OL1-2M03-3014 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3014 - C4 TRIM VAPORIZER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3015 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3015 - C4 VAPORIZER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3016 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3016 - HEAVY END DISCHARGE PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-04-23; A: 2019-04-24; C: 2019-06-18; A: 2019-06-18
[6 empty] | Issue Actual |  |  | B: 2019-04-23; A: 2019-04-24; C: 2019-06-18; A: 2019-06-18
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01451; A: TPSK-LSPA1-T-ME-01451; C: TPSK-LSPA1-T-ME-01910; A: TPSK-LSPA1-T-ME-01910
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18; C: 2019-07-15; A: 2019-07-15
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3018 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3018 - SOLVENT COOLER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3020 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3020 - MAIN WASHER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | B: 2019-04-08; A: 2019-04-09; C: 2019-06-11; A: 2019-06-11
[6 empty] | Issue Actual |  |  | B: 2019-04-08; A: 2019-04-09; C: 2019-06-11; A: 2019-06-11
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01275; A: TPSK-LSPA1-T-ME-01275; C: TPSK-LSPA1-T-ME-01870; A: TPSK-LSPA1-T-ME-01870
[6 empty] | Return Date |  |  | B: 2019-05-20; A: 2019-05-20; A: 2019-07-08
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-3021 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3020 - MAIN WASHER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3022 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3020 - MAIN WASHER CONDENSER |  | Class 1 | Purpose** | IFR | IFI | B: IFI; A: IFD; C: IFQ
[6 empty] | Rev. |  | A | bar: B; C
[6 empty] | Issue Plan | 2019-04-15 |  | A: 2019-05-20
[6 empty] | Revised Plan |  | 2019-05-10 | B: 2019-05-13; C: 2019-08-15
[6 empty] | Issue Actual |  | 2019-05-10 | B: 2019-05-13; C: 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME -01645 | B: TPSK-LSPA1-T-ME -01645; C: TPSK-LSPA1-T-ME-02437
[6 empty] | Return Date |  | 2019-06-18 | B: 2019-06-18
[6 empty] | Owner Cmmt* |  | R2 | bar: B
| ME | OL1-2M03-3023 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3020 - MAIN WASHER REFLUX PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-04-15; A: 2019-04-16
[6 empty] | Issue Actual |  |  | B: 2019-04-15; A: 2019-04-16
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01363; A: TPSK-LSPA1-T-ME-01363
[6 empty] | Return Date |  |  | B: 2019-06-17; A: 2019-06-17
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3026 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3026 - MAIN WASHER BOTTOM PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME -01562; A: TPSK-LSPA1-T-ME -01562
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3030 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3030 - AFTER WASHER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | B: 2019-04-11; A: 2019-04-12; C: 2019-06-13; A: 2019-06-14
[6 empty] | Issue Actual |  |  | B: 2019-04-11; A: 2019-04-12; C: 2019-06-13; A: 2019-06-14
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01325; A: TPSK-LSPA1-T-ME-01325; C: TPSK-LSPA1-T-ME-01893; A: TPSK-LSPA1-T-ME-01893
[6 empty] | Return Date |  |  | B: 2019-05-20; A: 2019-05-20
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3031 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3030 - AFTER WASHER CONDENSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3032 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3030 - AFTER WASHER REFLUX PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-10; A: 2019-05-13; C: 2019-08-15
[6 empty] | Issue Actual |  |  | B: 2019-05-10; A: 2019-05-13; C: 2019-08-15
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME -01645; A: TPSK-LSPA1-T-ME -01645; C: TPSK-LSPA1-T-ME-02437
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3033 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3030 - AFTER WASHER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-04-16; A: 2019-04-17; C: 2019-06-18; A: 2019-06-18
[6 empty] | Issue Actual |  |  | B: 2019-04-16; A: 2019-04-17; C: 2019-06-18; A: 2019-06-18
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01370; A: TPSK-LSPA1-T-ME-01370; C: TPSK-LSPA1-T-ME-01910; A: TPSK-LSPA1-T-ME-01910
[6 empty] | Return Date |  |  | B: 2019-06-17; A: 2019-06-17; C: 2019-07-15; A: 2019-07-15
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3036 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3036 - AFTER WASHER BOTTOM PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-04-16; A: 2019-04-17; C: 2019-06-18; A: 2019-06-18
[6 empty] | Issue Actual |  |  | B: 2019-04-16; A: 2019-04-17; C: 2019-06-18; A: 2019-06-18
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01370; A: TPSK-LSPA1-T-ME-01370; C: TPSK-LSPA1-T-ME-01910; A: TPSK-LSPA1-T-ME-01910
[6 empty] | Return Date |  |  | B: 2019-06-17; A: 2019-06-17; C: 2019-07-15; A: 2019-07-15
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3040 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3040 - RECTIFIER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | B: 2019-04-08; A: 2019-04-09; C: 2019-06-13; A: 2019-06-14
[6 empty] | Issue Actual |  |  | B: 2019-04-08; A: 2019-04-09; C: 2019-06-13; A: 2019-06-14
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01275; A: TPSK-LSPA1-T-ME-01275; C: TPSK-LSPA1-T-ME-01893; A: TPSK-LSPA1-T-ME-01893
[6 empty] | Return Date |  |  | B: 2019-05-20; A: 2019-05-20
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3044 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3044 - SOLVENT HEATER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3045 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3045 - SOLVENT HEAT EXCHANGER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3046 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3046 - DEGASSER FEED PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-04-17; A: 2019-04-18
[6 empty] | Issue Actual |  |  | B: 2019-04-17; A: 2019-04-18
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01398; A: TPSK-LSPA1-T-ME-01398
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3047 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3045 - RECTIFIER PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-04-17; A: 2019-04-18; C: 2019-06-18; A: 2019-06-18
[6 empty] | Issue Actual |  |  | B: 2019-04-17; A: 2019-04-18; C: 2019-06-18; A: 2019-06-18
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01398; A: TPSK-LSPA1-T-ME-01398; C: TPSK-LSPA1-T-ME-01910; A: TPSK-LSPA1-T-ME-01910
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18; C: 2019-07-15; A: 2019-07-15
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3050 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3050 - DEGASSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | B: 2019-04-11; A: 2019-04-12; C: 2019-06-13; A: 2019-06-14
[6 empty] | Issue Actual |  |  | B: 2019-04-11; A: 2019-04-12; C: 2019-06-13; A: 2019-06-14
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01325; A: TPSK-LSPA1-T-ME-01325; C: TPSK-LSPA1-T-ME-01893; A: TPSK-LSPA1-T-ME-01893
[6 empty] | Return Date |  |  | B: 2019-05-20; A: 2019-05-20
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3055 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3055 - DEGASSER REBOILER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3056 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3056 - DEGASSER BOTTOM PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-05-06; A: 2019-05-07
[6 empty] | Issue Actual |  |  | B: 2019-05-06; A: 2019-05-07
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01582; A: TPSK-LSPA1-T-ME-01582
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3060 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3060 - ACETYLENE WASHER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | B: 2019-04-08; A: 2019-04-09; C: 2019-06-11; A: 2019-06-11
[6 empty] | Issue Actual |  |  | B: 2019-04-08; A: 2019-04-09; C: 2019-06-11; A: 2019-06-11
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01275; A: TPSK-LSPA1-T-ME-01275; C: TPSK-LSPA1-T-ME-01870; A: TPSK-LSPA1-T-ME-01870
[6 empty] | Return Date |  |  | B: 2019-05-20; A: 2019-05-20; A: 2019-07-08
Owner Cmmt* | bar: B to A; A
| ME | OL1-2M03-3061 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3060 - ACETYLENE WASHER CONDENSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2018-12-27 | 2019-01-17
[6 empty] | Revised Plan |  |  | B: 2019-05-06; A: 2019-05-07
[6 empty] | Issue Actual |  |  | B: 2019-05-06; A: 2019-05-07
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01570; A: TPSK-LSPA1-T-ME-01570
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3062 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3062 - ACETYLENE CONDENSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3063 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3060 - WASTE WATER PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3064 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3062 - C4 ACETYLENE PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Issue Actual |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01654; A: TPSK-LSPA1-T-ME-01654
[6 empty] | Return Date |  |  | B: 2019-06-03; A: 2019-06-03
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3065 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3061 - WASTE HC PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-10; A: 2019-05-13
[6 empty] | Issue Actual |  |  | B: 2019-05-10; A: 2019-05-13
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME -01645; A: TPSK-LSPA1-T-ME -01645
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3066 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3062 - ACETYLENE ACCUMULATOR |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01563; A: TPSK-LSPA1-T-ME-01563
[6 empty] | Return Date |  |  | B: 2019-05-24; A: 2019-05-24
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3067 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3060 - C4 FEED DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-05-06; A: 2019-05-07
[6 empty] | Issue Actual |  |  | B: 2019-05-06; A: 2019-05-07
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01570; A: TPSK-LSPA1-T-ME-01570
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3070 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3070 - DIRECT COOLER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | B: 2019-04-08; A: 2019-04-09; C: 2019-06-13; A: 2019-06-14
[6 empty] | Issue Actual |  |  | B: 2019-04-08; A: 2019-04-09; C: 2019-06-13; A: 2019-06-14
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01275; A: TPSK-LSPA1-T-ME-01275; C: TPSK-LSPA1-T-ME-01893; A: TPSK-LSPA1-T-ME-01893
[6 empty] | Return Date |  |  | B: 2019-05-20; A: 2019-05-20
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3071 | MECHANICAL EQUIPMENT DATA SHEET - 10-C-3070 - RECYCLE GAS COMPRESSOR |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3073 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3070 - WATER / NMP COOLER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-31
[6 empty] | Revised Plan |  |  | A: 2019-01-22; C: 2019-03-14; A: 2019-03-15
[6 empty] | Issue Actual |  |  | A: 2019-01-22; C: 2019-03-14; A: 2019-03-15
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00692; A: TPSK-LSPA1-T-ME-00692; C: TPSK-LSPA1-T-ME-01066; A: TPSK-LSPA1-T-ME-01066
[6 empty] | Return Date |  |  | B: 2019-02-26; A: 2019-02-26; C: 2019-04-02; A: 2019-04-02
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3076 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3076 - DIRECT COOLER PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01563; A: TPSK-LSPA1-T-ME-01563
[6 empty] | Return Date |  |  | B: 2019-05-24; A: 2019-05-24
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3080 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3080 - BUTADIENE TOWER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | B: 2019-04-08; A: 2019-04-09; C: 2019-06-13; A: 2019-06-14
[6 empty] | Issue Actual |  |  | B: 2019-04-08; A: 2019-04-09; C: 2019-06-13; A: 2019-06-14
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01275; A: TPSK-LSPA1-T-ME-01275; C: TPSK-LSPA1-T-ME-01893; A: TPSK-LSPA1-T-ME-01893
[6 empty] | Return Date |  |  | B: 2019-05-20; A: 2019-05-20
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3081 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3080 - BUTADIENE TOWER REFLUX DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3082 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3080 - BUTADIENE TOWER CONDENSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-13; A: 2019-05-14; C: 2019-08-15
[6 empty] | Issue Actual |  |  | B: 2019-05-13; A: 2019-05-14; C: 2019-08-15
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01654; A: TPSK-LSPA1-T-ME-01654; C: TPSK-LSPA1-T-ME-02437
[6 empty] | Return Date |  |  | B: 2019-06-03; A: 2019-06-03
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3083 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3080 - BUTADIENE TOWER REFLUX PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01563; A: TPSK-LSPA1-T-ME-01563
[6 empty] | Return Date |  |  | B: 2019-05-24; A: 2019-05-24
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3084 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3084 - BUTADIENE TOWER TRIM REBOILER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LPSA1-T-ME-01565; A: TPSK-LPSA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3085 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3085 - BUTADIENE TOWER REBOILER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3086 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3086 - C4 / C5 HC PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-05-06; A: 2019-05-07
[6 empty] | Issue Actual |  |  | B: 2019-05-06; A: 2019-05-07
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01570; A: TPSK-LSPA1-T-ME-01570
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3090 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3090 - BUTADIENE DRYING TOWER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | B: 2019-04-10; A: 2019-04-11; C: 2019-06-13; A: 2019-06-14
[6 empty] | Issue Actual |  |  | B: 2019-04-10; A: 2019-04-11; C: 2019-06-13; A: 2019-06-14
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01312; A: TPSK-LSPA1-T-ME-01312; C: TPSK-LSPA1-T-ME-01893; A: TPSK-LSPA1-T-ME-01893
Return Date
Owner Cmmt*
| ME | OL1-2M03-3095 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3095 - BUTADIENE DRYING TOWER REBOILER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3097 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3096 - BUTADIENE PRODUCT PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-05-06; A: 2019-05-07
[6 empty] | Issue Actual |  |  | B: 2019-05-06; A: 2019-05-07
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01570; A: TPSK-LSPA1-T-ME-01570
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3098 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3098 - BUTADIENE PRODUCT SUBCOOLER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3100 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3100 - SOLVENT REGEN DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-07; A: 2019-05-13; C: 2019-08-15
[6 empty] | Issue Actual |  |  | B: 2019-05-07; A: 2019-05-13; C: 2019-08-15
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01654; A: TPSK-LSPA1-T-ME-01654; C: TPSK-LSPA1-T-ME-02437
[6 empty] | Return Date |  |  | B: 2019-06-03; A: 2019-06-03
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3110 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3110 - WATER WASHER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-03-14 | 2019-04-11
[6 empty] | Revised Plan |  |  | B: 2019-04-08; A: 2019-04-09; C: 2019-06-19; A: 2019-06-19
[6 empty] | Issue Actual |  |  | B: 2019-04-08; A: 2019-04-09; C: 2019-06-19; A: 2019-06-19
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01275; A: TPSK-LSPA1-T-ME-01275; C: TPSK-LSPA1-T-ME-01916; A: TPSK-LSPA1-T-ME-01916
[6 empty] | Return Date |  |  | B: 2019-05-20; A: 2019-05-20; C: 2019-07-15; A: 2019-07-15
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3111 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3110 - WATER WASHER ACCUMULATOR |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3112 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3110 - WATER WASHER CONDENSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Issue Actual |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01654; A: TPSK-LSPA1-T-ME-01654
[6 empty] | Return Date |  |  | B: 2019-06-03; A: 2019-06-03
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3113 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3110 - SOLVENT RETURN PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01563; A: TPSK-LSPA1-T-ME-01563
[6 empty] | Return Date |  |  | B: 2019-05-24; A: 2019-05-24
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3126 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3126 - EJECTOR SEAL DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Issue Actual |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01654; A: TPSK-LSPA1-T-ME-01654
[6 empty] | Return Date |  |  | B: 2019-06-03; A: 2019-06-03
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3127 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3126 - WASTE WATER RETURN PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01563; A: TPSK-LSPA1-T-ME-01563
[6 empty] | Return Date |  |  | B: 2019-05-24; A: 2019-05-24
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3150 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3150 - CONDENSATE HEATER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3151 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3150 - CONDENSATE FLASH DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Issue Actual |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01654; A: TPSK-LSPA1-T-ME-01654
[6 empty] | Return Date |  |  | B: 2019-06-03; A: 2019-06-03
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3160 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3160 - CONDENSATE COOLER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01565; A: TPSK-LSPA1-T-ME-01565
[6 empty] | Return Date |  |  | B: 2019-05-29; A: 2019-05-29
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3161 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3160 - CONDENSATE DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-13; A: 2019-05-14; C: 2019-08-15
[6 empty] | Issue Actual |  |  | B: 2019-05-13; A: 2019-05-14; C: 2019-08-15
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01654; A: TPSK-LSPA1-T-ME-01654; C: TPSK-LSPA1-T-ME-02437
[6 empty] | Return Date |  |  | B: 2019-06-03; A: 2019-06-03
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3162 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3160 - CONDENSATE RECYCLE PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Issue Actual |  |  | B: 2019-05-02; A: 2019-05-03
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01563; A: TPSK-LSPA1-T-ME-01563
[6 empty] | Return Date |  |  | B: 2019-05-24; A: 2019-05-24
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3180 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3180 - BLOWDOWN DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Issue Actual |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01654; A: TPSK-LSPA1-T-ME-01654
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3190 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3190 - NMP SLOP DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-13; A: 2019-05-14; C: 2019-08-15
[6 empty] | Issue Actual |  |  | B: 2019-05-13; A: 2019-05-14; C: 2019-08-15
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01654; A: TPSK-LSPA1-T-ME-01654; C: TPSK-LSPA1-T-ME-02437
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3191 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3190 - SOLVENT SLOP PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-05-06; A: 2019-05-07
[6 empty] | Issue Actual |  |  | B: 2019-05-06; A: 2019-05-07
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01570; A: TPSK-LSPA1-T-ME-01570
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3900 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-3900 - NMP STORAGE TANK |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-18 | 2019-02-26
[6 empty] | Revised Plan |  |  | B: 2019-04-23; A: 2019-04-24
[6 empty] | Issue Actual |  |  | B: 2019-04-23; A: 2019-04-24
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01449; A: TPSK-LSPA1-T-ME-01449
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3901 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3900 - NMP STORAGE PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-04-30; A: 2019-05-02
[6 empty] | Issue Actual |  |  | B: 2019-04-30; A: 2019-05-02
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01524; A: TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3902 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3902 - SOLVENT INHIBITOR DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Issue Actual |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01654; A: TPSK-LSPA1-T-ME-01654
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3903 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3902 - SOLVENT INHIBITOR DOSING PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2018-12-27 | 2019-01-17
[6 empty] | Revised Plan |  |  | B: 2019-04-23; A: 2019-04-24
[6 empty] | Issue Actual |  |  | B: 2019-04-23; A: 2019-04-24
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01451; A: TPSK-LSPA1-T-ME-01451
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3904 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3904 - PRODUCT INHIBITOR DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Issue Actual |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01654; A: TPSK-LSPA1-T-ME-01654
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3905 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3904 - PRODUCT INHIBITOR DOSING PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2018-12-27 | 2019-01-17
[6 empty] | Revised Plan |  |  | B: 2019-04-23; A: 2019-04-24
[6 empty] | Issue Actual |  |  | B: 2019-04-23; A: 2019-04-24
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01451; A: TPSK-LSPA1-T-ME-01451
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3906 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3906 - ANTI FOAM AGENT DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Issue Actual |  |  | B: 2019-05-13; A: 2019-05-14
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01654; A: TPSK-LSPA1-T-ME-01654
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3907 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3906 - ANTIFOAM DOSING PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2018-12-27 | 2019-01-17
[6 empty] | Revised Plan |  |  | B: 2019-04-23; A: 2019-04-24
[6 empty] | Issue Actual |  |  | B: 2019-04-23; A: 2019-04-24
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01451; A: TPSK-LSPA1-T-ME-01451
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-3908 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3908 - PREDISTILLATION INHIBITOR DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2019-04-17; A: 2019-04-18
[6 empty] | Issue Actual |  |  | B: 2019-04-17; A: 2019-04-18
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01389; A: TPSK-LSPA1-T-ME-01389
Return Date
Owner Cmmt*
| ME | OL1-2M03-3909 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3908 - PREDISTILLATION INHIBITOR DOSING PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2018-12-27 | 2019-01-17
[6 empty] | Revised Plan |  |  | B: 2019-04-23; A: 2019-04-24
[6 empty] | Issue Actual |  |  | B: 2019-04-23; A: 2019-04-24
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01451; A: TPSK-LSPA1-T-ME-01451
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-5100 | Mechanical Equipment Datasheet for Deaerator D-5100 |  | Class 2 | Purpose** | IFP | IFP
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2019-04-01 | 2019-04-02
[6 empty] | Issue Actual | 2019-04-01 | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01209 | TPSK-LSPA1-T-ME-01209
Return Date
Owner Cmmt*
| ME | OL1-2M03-5101 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5100 - SHP BFW PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | B | C | A | A | B | C | D | D
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan | [5 empty] | 2018-10-27 | 2018-11-15 | 2018-12-11 | 2019-04-22 | 2019-04-23
[6 empty] | Issue Actual | [5 empty] | 2018-10-27 | 2018-11-15 | 2018-12-11 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00322 | TPSK-LSPA1-T-ME-00476 | TPSK-LSPA1-T-ME-00236 | TPSK-LSPA1-T-ME-00236 | TPSK-LSPA1-T-ME-00322 | TPSK-LSPA1-T-ME-00476 | TPSK-LSPA1-T-ME-01433 | TPSK-LSPA1-T-ME-01433
[6 empty] | Return Date |  |  | 2018-12-10 | 2019-01-16 | 2018-11-19 | 2018-11-19 | 2018-12-10 | 2019-01-16 | 2019-06-18 | 2019-06-18
Owner Cmmt* | bar: B to D
| ME | OL1-2M03-5102 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5102 - BFW PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | B | A | A | B | C | C | D | D
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  |  |  | 2018-10-27 | 2018-12-11 | 2019-04-02 | 2019-04-03 | 2019-04-22 | 2019-04-23
[6 empty] | Issue Actual |  |  |  |  | 2018-10-27 | 2018-12-11 | 2019-04-02 | 2019-04-03 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00476 | TPSK-LSPA1-T-ME-00236 | TPSK-LSPA1-T-ME-00236 | TPSK-LSPA1-T-ME-00476 | TPSK-LSPA1-T-ME-01227 | TPSK-LSPA1-T-ME-01227 | TPSK-LSPA1-T-ME-01433 | TPSK-LSPA1-T-ME-01433
[6 empty] | Return Date |  |  | 2019-01-16 | 2018-11-19 | 2018-11-19 | 2019-01-16 |  |  | 2019-06-18 | 2019-06-18
Owner Cmmt* | bar: B to B; D to D
| ME | OL1-2M03-5103 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5100 - DEARATOR VENT CONDENSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-29
[6 empty] | Issue Actual |  |  | A: 2019-01-29
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00755; A: TPSK-LSPA1-T-ME-00755
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-5107 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5112 - SUSPECT CONDENSATE FLASH DRUM VENT CONDENSER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; A: IFQ; B: IFQ
Rev. | bar: B to B
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-29; A: 2019-04-18; B: 2019-04-18
[6 empty] | Issue Actual |  |  | A: 2019-01-29; A: 2019-04-18; B: 2019-04-18
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00755; A: TPSK-LSPA1-T-ME-00755; A: TPSK-LSPA1-T-ME-01396; B: TPSK-LSPA1-T-ME-01396
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; A: 2019-06-18; B: 2019-06-18
Owner Cmmt* | bar: B to B
| ME | OL1-2M03-5108 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5110 - SUSPECT CONDENSATE COOLER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2018-10-20 | 2018-10-20
[6 empty] | Revised Plan |  |  | A: 2019-01-25
[6 empty] | Issue Actual |  |  | A: 2019-01-25
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00723; A: TPSK-LSPA1-T-ME-00723
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-5109 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5110 - CONDENSATE PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | C | B | A | B | C | D | D | E | E
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan | [5 empty] | 2018-10-26 | 2018-11-14 | 2018-12-11 | 2019-03-25 | 2019-03-26 | 2019-03-29 | 2019-04-01
[6 empty] | Issue Actual | [5 empty] | 2018-10-26 | 2018-11-14 | 2018-12-11 | 2019-03-25 | 2019-03-26 | 2019-03-29 | 2019-04-01
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00235 | TPSK-LSPA1-T-ME-00476 | TPSK-LSPA1-T-ME-00317 | TPSK-LSPA1-T-ME-00235 | TPSK-LSPA1-T-ME-00317 | TPSK-LSPA1-T-ME-00476 | TPSK-LSPA1-T-ME-01151 | TPSK-LSPA1-T-ME-01151 | TPSK-LSPA1-T-ME-01197 | TPSK-LSPA1-T-ME-01197
[6 empty] | Return Date |  |  | 2018-11-19 | 2019-01-16 | 2019-02-21 | 2018-11-19 | 2019-02-21 | 2019-01-16 | 2019-04-10 | 2019-04-10
Owner Cmmt* | bar: A to D
| ME | OL1-2M03-5110 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5110 - CONDENSATE TANK |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; C: IFQ; B: IFQ; A: IFQ
Rev. | bar: A to A
[6 empty] | Issue Plan | 2019-02-18 | 2019-02-26
[6 empty] | Revised Plan |  |  | C: 2019-01-28; B: 2019-04-22; A: 2019-04-23
[6 empty] | Issue Actual |  |  | C: 2019-01-28; B: 2019-04-22; A: 2019-04-23
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00746; C: TPSK-LSPA1-T-ME-00746; B: TPSK-LSPA1-T-ME-01430; A: TPSK-LSPA1-T-ME-01430
[6 empty] | Return Date |  |  | A: 2019-02-21; C: 2019-02-21; B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: A to A
| ME | OL1-2M03-5111 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5112 - SUSPECT CONDENSATE PUMPS |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; C: IFQ; B: IFQ; A: IFQ
Rev. | bar: A to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2018-11-20; A: 2018-12-20
[6 empty] | Issue Actual |  |  | B: 2018-11-20; A: 2018-12-20
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00544; C: TPSK-LSPA1-T-ME-00341; B: TPSK-LSPA1-T-ME-00341; A: TPSK-LSPA1-T-ME-00544
[6 empty] | Return Date |  |  | A: 2019-01-16; C: 2018-12-13; B: 2018-12-13; A: 2019-01-16
Owner Cmmt* | bar: A to A
| ME | OL1-2M03-5112 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5112 - SUSPECT CONDENSATE FLASH DRUM |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; C: IFQ
Rev. | bar: A to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | C: 2019-01-16
[6 empty] | Issue Actual |  |  | C: 2019-01-16
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00657; C: TPSK-LSPA1-T-ME-00657
[6 empty] | Return Date |  |  | A: 2019-02-11; C: 2019-02-11
Owner Cmmt* | bar: A to C
| ME | OL1-2M03-5113 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5113 - FOUL CONDENSATE COOLER |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; C: IFQ; B: IFQ; A: IFQ
Rev. | bar: A to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | C: 2019-01-29; B: 2019-05-01; A: 2019-05-02
[6 empty] | Issue Actual |  |  | C: 2019-01-29; B: 2019-05-01; A: 2019-05-02
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00755; C: TPSK-LSPA1-T-ME-00755; B: TPSK-LSPA1-T-ME-01545; A: TPSK-LSPA1-T-ME-01545
[6 empty] | Return Date |  |  | A: 2019-02-21; C: 2019-02-21; B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: A to A
| ME | OL1-2M03-5114 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5114 - LP CONDENSATE FLASH DRUM |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; C: IFQ
Rev. | bar: A to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | C: 2019-01-16
[6 empty] | Issue Actual |  |  | C: 2019-01-16
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00657; C: TPSK-LSPA1-T-ME-00657
[6 empty] | Return Date |  |  | A: 2019-02-11; C: 2019-02-11
Owner Cmmt* | bar: A to C
| ME | OL1-2M03-5115 | Mechanical Equipment Datasheet For Condensate Carbon Filter Package |  | Class 2 | Purpose** | IFQ | IFQ | A: IFP
[6 empty] | Rev. | A | A | A: 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-13 | 2019-03-13 | A: 2019-08-14
[6 empty] | Issue Actual | 2019-03-13 | 2019-03-13 | A: 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01040 | TPSK-LSPA1-T-ME-01040 | A: TPSK-LSPA1-T-ME-02405
[6 empty] | Return Date | 2019-04-01 | 2019-04-01
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-5120 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5120 - RAW CONDENSATE TANK |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; C: IFQ
Rev. | bar: A to C
[6 empty] | Issue Plan | 2019-02-18 | 2019-02-26
[6 empty] | Revised Plan |  |  | C: 2019-01-28
[6 empty] | Issue Actual |  |  | C: 2019-01-28
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00746; C: TPSK-LSPA1-T-ME-00746
[6 empty] | Return Date |  |  | A: 2019-02-21; C: 2019-02-21
Owner Cmmt* | bar: A to C
| ME | OL1-2M03-5121 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5120 - RAW CONDENSATE PUMPS |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; C: IFQ; B: IFQ; A: IFQ
Rev. | bar: A to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2018-11-20; A: 2018-12-20
[6 empty] | Issue Actual |  |  | B: 2018-11-20; A: 2018-12-20
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00544; C: TPSK-LSPA1-T-ME-00341; B: TPSK-LSPA1-T-ME-00341; A: TPSK-LSPA1-T-ME-00544
[6 empty] | Return Date |  |  | A: 2019-01-16; C: 2018-12-13; B: 2018-12-13; A: 2019-01-16
Owner Cmmt* | bar: A to A
| ME | OL1-2M03-5122 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51022 - PV-5147 Outlet |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-02143 | TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date |  | 2019-08-01
[6 empty] | Owner Cmmt* |  | R1
| ME | OL1-2M03-5123 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51023 - PV-5155 Outlet |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-02143 | TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date |  | 2019-08-01
[6 empty] | Owner Cmmt* |  | R1
| ME | OL1-2M03-5124 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51024 - PV-5158 Outlet |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-02143 | TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date |  | 2019-08-01
[6 empty] | Owner Cmmt* |  | R1
| ME | OL1-2M03-5125 | Mechanical Equipment Datasheet for Condensate Polisher Package |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-02-27 | 2019-02-28
[6 empty] | Issue Actual | 2019-02-27 | 2019-02-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00941 | TPSK-LSPA1-T-ME-00941
[6 empty] | Return Date | 2019-04-01 | 2019-04-01
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-5126 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51026A-H - PSV-5143A-H Outlet |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-02143 | TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date |  | 2019-08-01
[6 empty] | Owner Cmmt* |  | R1
| ME | OL1-2M03-5127 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51021 - PV-5143 Outlet |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-02144 | TPSK-LSPA1-T-ME-02144
Return Date
Owner Cmmt*
| ME | OL1-2M03-5128 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51025 - PV-5161 Outlet |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-02144 | TPSK-LSPA1-T-ME-02144
Return Date
Owner Cmmt*
| ME | OL1-2M03-5130 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51030A/B/C/D - PSV-5150A/B/C/D Outlet |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-02143 | TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date |  | 2019-08-01
[6 empty] | Owner Cmmt* |  | R1
| ME | OL1-2M03-5140 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5140 - INTERMITTENT BLOWDOWN DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | B | A | A | B | C | C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | B: 2018-12-20; A: 2019-01-11; B: 2019-05-28; C: 2019-05-29
[6 empty] | Issue Actual |  |  | B: 2018-12-20; A: 2019-01-11; B: 2019-05-28; C: 2019-05-29
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00638 | TPSK-LSPA-T-ME-00548 | TPSK-LSPA-T-ME-00548 | TPSK-LSPA1-T-ME-00638 | TPSK-LSPA1-T-ME-01760 | TPSK-LSPA1-T-ME-01760
[6 empty] | Return Date |  |  | A: 2019-01-31; C: 2019-01-24; B: 2019-01-24; A: 2019-01-31; C: 2019-06-21
Owner Cmmt* | bar: A to A; C
| ME | OL1-2M03-5141 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5140 - INTERMITTENT BLOWDOWN PUMPS |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; C: IFQ
Rev. | bar: A to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | C: 2018-11-19
[6 empty] | Issue Actual |  |  | C: 2018-11-19
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00335; C: TPSK-LSPA1-T-ME-00335
[6 empty] | Return Date |  |  | A: 2018-12-13; C: 2018-12-13
Owner Cmmt* | bar: A to C
| ME | OL1-2M03-5150 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5150 - CONTINUOUS BLOWDOWN FLASH DRUM |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; C: IFQ; B: IFQ; A: IFQ
Rev. | bar: A to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | C: 2019-01-11; B: 2019-05-30; A: 2019-05-31
[6 empty] | Issue Actual |  |  | C: 2019-01-11; B: 2019-05-30; A: 2019-05-31
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00629; C: TPSK-LSPA1-T-ME-00629; B: TPSK-LSPA1-T-ME-01780; A: TPSK-LSPA1-T-ME-01780
[6 empty] | Return Date |  |  | A: 2019-01-31; C: 2019-01-31; A: 2019-06-21
Owner Cmmt* | bar: A to C; A
| ME | OL1-2M03-5170 | Mechanical Data Sheet For General Purpose Turbines PT-5100 A-B SHP BFW Pumps Turbines |  | Class 2 | Purpose** | IMP | IMP
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-15 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-02130 | TPSK-LSPA1-T-ME-02130
Return Date
Owner Cmmt*
| ME | OL1-2M03-5171 | Mechanical Data Sheet For General Purpose Steam Turbines PT-5102 A VLP BFW Pump Turbine |  | Class 2 | Purpose** | IMP | IMP
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-15 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-02130 | TPSK-LSPA1-T-ME-02130
[6 empty] | Return Date |  | 2019-08-01
[6 empty] | Owner Cmmt* |  | R2
| ME | OL1-2M03-5172 | Mechanical Data Sheet For General Purpose Steam Turbines PT-5110 A Condensate Pump Turbine |  | Class 2 | Purpose** | IMP | IMP
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-15 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-02130 | TPSK-LSPA1-T-ME-02130
[6 empty] | Return Date |  | 2019-08-01
[6 empty] | Owner Cmmt* |  | R2
| ME | OL1-2M03-5200 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5200 - FUEL GAS DRUM |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; C: IFQ
Rev. | bar: A to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | C: 2019-01-11
[6 empty] | Issue Actual |  |  | C: 2019-01-11
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00629; C: TPSK-LSPA1-T-ME-00629
[6 empty] | Return Date |  |  | A: 2019-01-31; C: 2019-01-31
Owner Cmmt* | bar: A to C
| ME | OL1-2M03-5201 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5200 - MP ETHYLENE SUPERHEATER |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; C: IFQ; B: IFQ; A: IFQ
Rev. | bar: A to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | C: 2019-01-29; B: 2019-04-12; A: 2019-04-15
[6 empty] | Issue Actual |  |  | C: 2019-01-29; B: 2019-04-12; A: 2019-04-15
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00755; C: TPSK-LSPA1-T-ME-00755; B: TPSK-LSPA1-T-ME-01344; A: TPSK-LSPA1-T-ME-01344
[6 empty] | Return Date |  |  | A: 2019-02-21; C: 2019-02-21; B: 2019-05-20; A: 2019-05-20
Owner Cmmt* | bar: A to A
| ME | OL1-2M03-5202 | Mechanical Equipment Data Sheet - MP Ethylene Superhtr Cond Pot |  | Class 2 | Purpose** | IFR | IFD | A: IFQ; C: IFQ; B: IFQ; A: IFQ
Rev. | bar: A to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | C: 2019-01-22; B: 2019-05-30; A: 2019-05-31
[6 empty] | Issue Actual |  |  | C: 2019-01-22; B: 2019-05-30; A: 2019-05-31
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00685; C: TPSK-LSPA1-T-ME-00685; B: TPSK-LSPA1-T-ME-01780; A: TPSK-LSPA1-T-ME-01780
[6 empty] | Return Date |  |  | A: 2019-02-15; C: 2019-02-15; A: 2019-06-21
Owner Cmmt* | bar: A to C; A
| ME | OL1-2M03-5210 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5210 - PILOT GAS VAPORIZER |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; C: IFQ; B: IFQ; A: IFQ
Rev. | bar: A to A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | C: 2019-01-17; B: 2019-04-22; A: 2019-04-23
[6 empty] | Issue Actual |  |  | C: 2019-01-17; B: 2019-04-22; A: 2019-04-23
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00673; C: TPSK-LSPA1-T-ME-00673; B: TPSK-LSPA1-T-ME-01436; A: TPSK-LSPA1-T-ME-01436
[6 empty] | Return Date |  |  | A: 2019-02-11; C: 2019-02-11; B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: A to A
| ME | OL1-2M03-5211 | Mechanical Equipment Data Sheet - Pilot Gas Vaporizer Cond Pot |  | Class 2 | Purpose** | IFR | IFD | A: IFQ; C: IFQ; B: IFQ; A: IFQ
Rev. | bar: A to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | C: 2019-01-23; B: 2019-03-28; A: 2019-03-29
[6 empty] | Issue Actual |  |  | C: 2019-01-23; B: 2019-03-28; A: 2019-03-29
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00709; C: TPSK-LSPA1-T-ME-00709; B: TPSK-LSPA1-T-ME-01186; A: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date |  |  | A: 2019-02-21; C: 2019-02-21; B: 2019-05-02; A: 2019-05-02
Owner Cmmt* | bar: A to A
| ME | OL1-2M03-5350 | Mechanical Equipment Datasheet for Cooling Tower |  | Class 2 | Purpose** | IFQ | IFQ | A: IFP; C: IFP
[6 empty] | Rev. | B | B | A: 0; C: 0
Issue Plan
[6 empty] | Revised Plan |  | 2018-11-06 | A: 2019-04-25; C: 2019-04-25
[6 empty] | Issue Actual |  | 2018-11-06 | A: 2019-04-25; C: 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00276 | TPSK-LSPA1-T-ME-00276 | A: TPSK-LSPA1-T-ME-01476; C: TPSK-LSPA1-T-ME-01476
[6 empty] | Return Date | 2019-02-15 | 2019-02-15 | A: 2019-06-18; C: 2019-06-18
[6 empty] | Owner Cmmt* | R1 | R1 | bar: A to C
| ME | OL1-2M03-5352 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5350 - OLEFINS COOLING WATER PUMPS |  | Class 1 | Purpose** | IFR | IFD | A: IFQ; C: IFQ; B: IFQ; A: IFQ
Rev. | bar: A to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2018-10-23; A: 2018-11-28
[6 empty] | Issue Actual |  |  | B: 2018-10-23; A: 2018-11-28
[6 empty] | Transmittal no. |  |  | A: TPSK-LSPA1-T-ME-00210; C: TPSK-LSPA1-T-ME-00388; B: TPSK-LSPA1-T-ME-00210; A: TPSK-LSPA1-T-ME-00388
[6 empty] | Return Date |  |  | A: 2018-11-14; C: 2018-12-18; B: 2018-11-14; A: 2018-12-18
Owner Cmmt* | bar: A to A
| ME | OL1-2M03-5355 | Mechanical Equipment Datasheet for Side Stream Filter Package |  | Class 2 | Purpose** | IFQ | IFQ | A: IFP; C: IFP
[6 empty] | Rev. | B | B | A: 0; C: 0
Issue Plan
[6 empty] | Revised Plan |  | 2018-10-31 | A: 2019-03-27; C: 2019-03-27
[6 empty] | Issue Actual |  | 2018-10-31 | A: 2019-03-27; C: 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00248 | TPSK-LSPA1-T-ME-00248 | A: TPSK-LSPA1-T-ME-01164; C: TPSK-LSPA1-T-ME-01164
[6 empty] | Return Date | 2018-11-27 | 2018-11-27 | A: 2019-04-25; C: 2019-04-25
Owner Cmmt* | bar: A to C
| ME | OL1-2M03-5361 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5360 - CTU COOLING WATER PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | B | A | D | C | A | B | C | D
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2018-10-23; B: 2018-11-14; C: 2018-11-28; D: 2019-01-11
[6 empty] | Issue Actual |  |  | A: 2018-10-23; B: 2018-11-14; C: 2018-11-28; D: 2019-01-11
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00317 | TPSK-LSPA1-T-ME-00210 | TPSK-LSPA1-T-ME-00627 | TPSK-LSPA1-T-ME-00388 | TPSK-LSPA1-T-ME-00210 | TPSK-LSPA1-T-ME-00317 | TPSK-LSPA1-T-ME-00388 | TPSK-LSPA1-T-ME-00627
[6 empty] | Return Date |  |  | 2019-02-21 | 2018-11-14 | 2019-01-31 | 2018-12-18 | 2018-11-14 | 2019-02-21 | 2018-12-18 | 2019-01-31
Owner Cmmt* | bar: B to D
| ME | OL1-2M03-5371 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5370 - CW FILTER BACKWASH PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  |  | 2019-01-24 | 2019-03-12 | 2019-03-13 | 2019-04-22 | 2019-04-23
[6 empty] | Issue Actual |  |  |  | 2019-01-24 | 2019-03-12 | 2019-03-13 | 2019-04-22 | 2019-04-23
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00716 | TPSK-LSPA1-T-ME-00716 | TPSK-LSPA1-T-ME-01038 | TPSK-LSPA1-T-ME-01038 | TPSK-LSPA1-T-ME-01426 | TPSK-LSPA1-T-ME-01426
[6 empty] | Return Date |  |  | 2019-02-21 | 2019-02-21 | 2019-03-29 | 2019-03-29 | 2019-06-18 | 2019-06-18
Owner Cmmt* | bar: B to B
| ME | OL1-2M03-5390 | MECHANICAL EQUIPMENT DATASHEET FOR COPPER CORROSION INHIBITOR INJECTION PACKAGE TAG: 10-PK-5390 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01490 | TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-5392 | MECHANICAL EQUIPMENT DATASHEET FOR MILD STEEL CORROSION INHIBITOR INJECTION PACKAGE TAG: 10-PK-5392 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01490 | TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-5394 | MECHANICAL EQUIPMENT DATASHEET FOR DISPERSANT INJECTION PACKAGE TAG: 10-PK-5394 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01490 | TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2M03-5397 | MECHANICAL EQUIPMENT DATASHEET FOR NON-OXIDIZING BIOCIDE INJECTION PACKAGE TAG: 10-PK-5397 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01490 | TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-5400 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5400 - INSTRUMENT AIR RECEIVER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-22; D: 2019-05-22; C: 2019-05-23
[6 empty] | Issue Actual |  |  | A: 2019-01-22; D: 2019-05-22; C: 2019-05-23
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00685; A: TPSK-LSPA1-T-ME-00685; D: TPSK-LSPA1-T-ME-01723; C: TPSK-LSPA1-T-ME-01723
[6 empty] | Return Date |  |  | B: 2019-02-15; A: 2019-02-15; C: 2019-06-21
Owner Cmmt* | bar: B to A; C
| ME | OL1-2M03-5500 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5500 - WARM FLARE DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2018-12-13; D: 2019-04-30; C: 2019-05-02
[6 empty] | Issue Actual |  |  | A: 2018-12-13; D: 2019-04-30; C: 2019-05-02
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00483; A: TPSK-LSPA1-T-ME-00483; D: TPSK-LSPA1-T-ME-01535; C: TPSK-LSPA1-T-ME-01535
[6 empty] | Return Date |  |  | B: 2019-01-22; A: 2019-01-22; D: 2019-06-18; C: 2019-06-18
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5501 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5500 - HOT BLOWDOWN PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  |  | 2019-01-10 | 2019-02-07 | 2019-02-07 | 2019-03-20 | 2019-03-21
[6 empty] | Issue Actual |  |  |  | 2019-01-10 | 2019-02-07 | 2019-02-07 | 2019-03-20 | 2019-03-21
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00616 | TPSK-LSPA1-T-ME-00616 | TPSK-LSPA1-T-ME-00822 | TPSK-LSPA1-T-ME-00822 | TPSK-LSPA1-T-ME-01102 | TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date |  |  | 2019-01-30 | 2019-01-30 | 2019-02-21 | 2019-02-21 | 2019-04-10 | 2019-04-10
Owner Cmmt* | bar: B to B
| ME | OL1-2M03-5510 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5510 - COLD FLARE DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-11
[6 empty] | Issue Actual |  |  | A: 2019-01-11
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00629; A: TPSK-LSPA1-T-ME-00629
[6 empty] | Return Date |  |  | B: 2019-01-31; A: 2019-01-31
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-5511 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5510 - COLD FLARE BLOWDOWN VAPORIZER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-29; D: 2019-04-26; C: 2019-04-29
[6 empty] | Issue Actual |  |  | A: 2019-01-29; D: 2019-04-26; C: 2019-04-29
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00755; A: TPSK-LSPA1-T-ME-00755; D: TPSK-LSPA1-T-ME-01495; C: TPSK-LSPA1-T-ME-01495
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-06-18; C: 2019-06-18
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5512 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5512 - COLD FLARE SUPERHEATER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-29; D: 2019-04-03; C: 2019-04-04
[6 empty] | Issue Actual |  |  | A: 2019-01-29; D: 2019-04-03; C: 2019-04-04
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00755; A: TPSK-LSPA1-T-ME-00755; D: TPSK-LSPA1-T-ME-01247; C: TPSK-LSPA1-T-ME-01247
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-05-20; C: 2019-05-20
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5513 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5513 - METHANOL VAPORIZER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-25; D: 2019-03-29; C: 2019-04-01
[6 empty] | Issue Actual |  |  | A: 2019-01-25; D: 2019-03-29; C: 2019-04-01
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00723; A: TPSK-LSPA1-T-ME-00723; D: TPSK-LSPA1-T-ME-01205; C: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-05-02; C: 2019-05-02
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5514 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5513 - METHANOL VAPROIZER COND POT |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-23; D: 2019-03-28; C: 2019-03-29
[6 empty] | Issue Actual |  |  | A: 2019-01-23; D: 2019-03-28; C: 2019-03-29
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00709; A: TPSK-LSPA1-T-ME-00709; D: TPSK-LSPA1-T-ME-01186; C: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-05-02; C: 2019-05-02
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5515 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5515 - METHANOL MAKE-UP DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-08; D: 2019-06-04; C: 2019-06-10
[6 empty] | Issue Actual |  |  | A: 2019-01-08; D: 2019-06-04; C: 2019-06-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00607; A: TPSK-LSPA1-T-ME-00607; D: TPSK-LSPA1-T-ME-01803; C: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date |  |  | B: 2019-01-28; A: 2019-01-28; C: 2019-07-08
Owner Cmmt* | bar: B to A; C
| ME | OL1-2M03-5520 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5520 - VENT COLLECTION DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-11; D: 2019-05-30; C: 2019-05-31
[6 empty] | Issue Actual |  |  | A: 2019-01-11; D: 2019-05-30; C: 2019-05-31
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00638; A: TPSK-LSPA1-T-ME-00638; D: TPSK-LSPA1-T-ME-01783; C: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date |  |  | B: 2019-01-31; A: 2019-01-31; C: 2019-06-21
Owner Cmmt* | bar: B to A; C
| ME | OL1-2M03-5522 | Mechanical Equipment Datasheet - LP Vent Blower |  | Class 2 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-18 | 2019-02-18
[6 empty] | Revised Plan |  |  | A: 2019-01-11
[6 empty] | Issue Actual |  |  | A: 2019-01-11
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00640; A: TPSK-LSPA1-T-ME-00640
[6 empty] | Return Date |  |  | B: 2019-02-11; A: 2019-02-11
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-5550 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5550 - HP FLARE KNOCK OUT DRUM |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  |  | 2019-01-11 | 2019-03-20 | 2019-03-21 | 2019-05-29 | 2019-05-30
[6 empty] | Issue Actual |  |  |  | 2019-01-11 | 2019-03-20 | 2019-03-21 | 2019-05-29 | 2019-05-30
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00629 | TPSK-LSPA1-T-ME-00629 | TPSK-LSPA1-T-ME-01114 | TPSK-LSPA1-T-ME-01114 | TPSK-LSPA1-T-ME-01764 | TPSK-LSPA1-T-ME-01764
[6 empty] | Return Date |  |  | B: 2019-01-31; A: 2019-01-31; B: 2019-06-21
Owner Cmmt* | bar: B to A; B
| ME | OL1-2M03-5551 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5550 - HP FLARE KNOCK OUT DRUM PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2019-01-10; D: 2019-04-30; C: 2019-05-02
[6 empty] | Issue Actual |  |  | A: 2019-01-10; D: 2019-04-30; C: 2019-05-02
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00616; A: TPSK-LSPA1-T-ME-00616; D: TPSK-LSPA1-T-ME-01524; C: TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date |  |  | B: 2019-01-30; A: 2019-01-30; D: 2019-06-18; C: 2019-06-18
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5552 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5552 - LPG STORAGE DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-11; D: 2019-05-30; C: 2019-05-31
[6 empty] | Issue Actual |  |  | A: 2019-01-11; D: 2019-05-30; C: 2019-05-31
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00638; A: TPSK-LSPA1-T-ME-00638; D: TPSK-LSPA1-T-ME-01783; C: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date |  |  | B: 2019-01-31; A: 2019-01-31; C: 2019-06-21
Owner Cmmt* | bar: B to A; C
| ME | OL1-2M03-5553 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5552 - LPG VAPORIZER / SUPERHEATER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-20
[6 empty] | Revised Plan |  |  | A: 2019-01-22; D: 2019-04-22; C: 2019-04-23
[6 empty] | Issue Actual |  |  | A: 2019-01-22; D: 2019-04-22; C: 2019-04-23
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00684; A: TPSK-LSPA1-T-ME-00684; D: TPSK-LSPA1-T-ME-01436; C: TPSK-LSPA1-T-ME-01436
[6 empty] | Return Date |  |  | B: 2019-02-11; A: 2019-02-11; D: 2019-06-18; C: 2019-06-18
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5555 | Mechanical Equipment Data Sheet - LPG Vaporizer-Superhtr Cond Pot |  | Class 2 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  |  | 2019-01-23 | 2019-03-28 | 2019-03-29 | 2019-05-30 | 2019-05-31
[6 empty] | Issue Actual |  |  |  | 2019-01-23 | 2019-03-28 | 2019-03-29 | 2019-05-30 | 2019-05-31
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00709 | TPSK-LSPA1-T-ME-00709 | TPSK-LSPA1-T-ME-01186 | TPSK-LSPA1-T-ME-01186 | TPSK-LSPA1-T-ME-01783 | TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date |  |  | 2019-02-21 | 2019-02-21 | 2019-05-02 | 2019-05-02 |  | 2019-06-21
Owner Cmmt* | bar: B to C; B
| ME | OL1-2M03-5560 | Mechanical Data Sheet for HP / Polyolefins Flare Package |  | Class 2 | Purpose** | IFQ | IFQ | B: IFP; A: IFP
[6 empty] | Rev. | A | A | B: 0; A: 0
Issue Plan
[6 empty] | Revised Plan |  | 2019-01-17 | B: 2019-06-25; A: 2019-06-25
[6 empty] | Issue Actual |  | 2019-01-17 | B: 2019-06-25; A: 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00667 | TPSK-LSPA1-T-ME-00667 | B: TPSK-LSPA1-T-ME-01969; A: TPSK-LSPA1-T-ME-01969
[6 empty] | Return Date | 2019-02-08 | 2019-02-08 | B: 2019-07-15; A: 2019-07-15
[6 empty] | Owner Cmmt* | R2 | R2 | bar: B to A
| ME | OL1-2M03-5565 | MECHANICAL EQUIPMENT DATA SHEET- 10-D-5565 - LLDPE LP FLARE KNOCK OUT DRUM |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-13
[6 empty] | Revised Plan |  |  | A: 2019-01-23; D: 2019-06-04; C: 2019-06-10
[6 empty] | Issue Actual |  |  | A: 2019-01-23; D: 2019-06-04; C: 2019-06-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00709; A: TPSK-LSPA1-T-ME-00709; D: TPSK-LSPA1-T-ME-01803; C: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; C: 2019-07-08
Owner Cmmt* | bar: B to A; C
| ME | OL1-2M03-5566 | Mechanical Equipment Datasheet - Polyolefins Flare Knock-Out Pumps |  | Class 2 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2019-01-24; D: 2019-04-22; C: 2019-04-23
[6 empty] | Issue Actual |  |  | A: 2019-01-24; D: 2019-04-22; C: 2019-04-23
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00716; A: TPSK-LSPA1-T-ME-00716; D: TPSK-LSPA1-T-ME-01426; C: TPSK-LSPA1-T-ME-01426
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-06-18; C: 2019-06-18
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5606 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5600 - PYGAS AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-02-07; A: 2019-02-07; D: 2019-04-08; C: 2019-04-09
[6 empty] | Issue Actual |  |  | B: 2019-02-07; A: 2019-02-07; D: 2019-04-08; C: 2019-04-09
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00817; A: TPSK-LSPA1-T-ME-00817; D: TPSK-LSPA1-T-ME-01279; C: TPSK-LSPA1-T-ME-01279
[6 empty] | Return Date |  |  | B: 2019-03-15; A: 2019-03-15; D: 2019-05-16; C: 2019-05-16
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5607 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5601 - BUTADIENE AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Issue Actual |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00716; A: TPSK-LSPA1-T-ME-00716; D: TPSK-LSPA1-T-ME-00962; C: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-03-15; C: 2019-03-15
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5608 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5602 - QW AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Issue Actual |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00716; A: TPSK-LSPA1-T-ME-00716; D: TPSK-LSPA1-T-ME-00962; C: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-03-15; C: 2019-03-15
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5609 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5603 - CGC AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Issue Actual |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00716; A: TPSK-LSPA1-T-ME-00716; D: TPSK-LSPA1-T-ME-00962; C: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-03-15; C: 2019-03-15
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5611 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5610 - HYDROBLAST PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2019-01-24; D: 2019-04-08; C: 2019-04-09
[6 empty] | Issue Actual |  |  | A: 2019-01-24; D: 2019-04-08; C: 2019-04-09
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00716; A: TPSK-LSPA1-T-ME-00716; D: TPSK-LSPA1-T-ME-01279; C: TPSK-LSPA1-T-ME-01279
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-05-16; C: 2019-05-16
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5612 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-5610 - HYDROBLAST FILTER |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-25 | 2019-03-18
[6 empty] | Revised Plan |  |  | A: 2019-01-11; D: 2019-03-25; C: 2019-03-26
[6 empty] | Issue Actual |  |  | A: 2019-01-11; D: 2019-03-25; C: 2019-03-26
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00639; A: TPSK-LSPA1-T-ME-00639; D: TPSK-LSPA1-T-ME-01141; C: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date |  |  | B: 2019-01-30; A: 2019-01-30; D: 2019-04-11; C: 2019-04-11
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5613 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5604 - REFRIG AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Issue Actual |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00716; A: TPSK-LSPA1-T-ME-00716; D: TPSK-LSPA1-T-ME-00962; C: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-03-15; C: 2019-03-15
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5614 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5605 - FURNACE AREA OILY WATER PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Issue Actual |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00716; A: TPSK-LSPA1-T-ME-00716; D: TPSK-LSPA1-T-ME-00962; C: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-03-15; C: 2019-03-15
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5616 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5615 - OLEFINS STORMWATER SUMP PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Issue Actual |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00716; A: TPSK-LSPA1-T-ME-00716; D: TPSK-LSPA1-T-ME-00962; C: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-03-15; C: 2019-03-15
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5621 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5621 - OLEFINS HOLDING BASIN SKIM OIL PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2019-01-28; D: 2019-03-20; C: 2019-03-21
[6 empty] | Issue Actual |  |  | A: 2019-01-28; D: 2019-03-20; C: 2019-03-21
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME -00742; A: TPSK-LSPA1-T-ME -00742; D: TPSK-LSPA1-T-ME-01102; C: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-04-10; C: 2019-04-10
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5622 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5620 - OLEFINS HOLDING BASIN PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2019-01-24; D: 2019-04-17; C: 2019-04-18
[6 empty] | Issue Actual |  |  | A: 2019-01-24; D: 2019-04-17; C: 2019-04-18
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00716; A: TPSK-LSPA1-T-ME-00716; D: TPSK-LSPA1-T-ME-01390; C: TPSK-LSPA1-T-ME-01390
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-06-18; C: 2019-06-18
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5623 | Mechanical Equipment Datasheet - Gate House Septic Tank Pumps |  | Class 2 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-02-13; A: 2019-02-13; D: 2019-04-15; C: 2019-04-16
[6 empty] | Issue Actual |  |  | B: 2019-02-13; A: 2019-02-13; D: 2019-04-15; C: 2019-04-16
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME -00847; A: TPSK-LSPA1-T-ME -00847; D: TPSK-LSPA1-T-ME-01363; C: TPSK-LSPA1-T-ME-01363
[6 empty] | Return Date |  |  | B: 2019-03-11; A: 2019-03-11; D: 2019-06-17; C: 2019-06-17
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5624 | Mechanical Equipment Datasheet - West Gate House Septic Tank Pumps |  | Class 2 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-02-13; A: 2019-02-13; D: 2019-04-15; C: 2019-04-16
[6 empty] | Issue Actual |  |  | B: 2019-02-13; A: 2019-02-13; D: 2019-04-15; C: 2019-04-16
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME -00847; A: TPSK-LSPA1-T-ME -00847; D: TPSK-LSPA1-T-ME-01363; C: TPSK-LSPA1-T-ME-01363
[6 empty] | Return Date |  |  | B: 2019-03-11; A: 2019-03-11; D: 2019-06-17; C: 2019-06-17
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5625 | Mechanical Equipment Datasheet - East Gate House Septic Tank Pumps |  | Class 2 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-02-13; A: 2019-02-13; D: 2019-04-15; C: 2019-04-16
[6 empty] | Issue Actual |  |  | B: 2019-02-13; A: 2019-02-13; D: 2019-04-15; C: 2019-04-16
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME -00847; A: TPSK-LSPA1-T-ME -00847; D: TPSK-LSPA1-T-ME-01363; C: TPSK-LSPA1-T-ME-01363
[6 empty] | Return Date |  |  | B: 2019-03-11; A: 2019-03-11; D: 2019-06-17; C: 2019-06-17
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5635 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5630 - CT AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-02-07; A: 2019-02-07
[6 empty] | Issue Actual |  |  | B: 2019-02-07; A: 2019-02-07
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00817; A: TPSK-LSPA1-T-ME-00817
[6 empty] | Return Date |  |  | B: 2019-03-15; A: 2019-03-15
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-5636 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5631 - CWWT AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-02-07; A: 2019-02-07
[6 empty] | Issue Actual |  |  | B: 2019-02-07; A: 2019-02-07
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00817; A: TPSK-LSPA1-T-ME-00817
[6 empty] | Return Date |  |  | B: 2019-03-15; A: 2019-03-15
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-5637 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5632 - HP FLARE AREA OILY WASTEWATER PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-02-07; A: 2019-02-07; D: 2019-03-20; C: 2019-03-21
[6 empty] | Issue Actual |  |  | B: 2019-02-07; A: 2019-02-07; D: 2019-03-20; C: 2019-03-21
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00817; A: TPSK-LSPA1-T-ME-00817; D: TPSK-LSPA1-T-ME-01102; C: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date |  |  | B: 2019-03-15; A: 2019-03-15; D: 2019-04-10; C: 2019-04-10
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5638 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5633 - HP FLARE AREA STORMWATER SUMP PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-02-07; A: 2019-02-07; D: 2019-03-20; C: 2019-03-21
[6 empty] | Issue Actual |  |  | B: 2019-02-07; A: 2019-02-07; D: 2019-03-20; C: 2019-03-21
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00817; A: TPSK-LSPA1-T-ME-00817; D: TPSK-LSPA1-T-ME-01102; C: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date |  |  | B: 2019-03-15; A: 2019-03-15; D: 2019-04-10; C: 2019-04-10
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5640 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5640 - OILY WASTEWATER EQUALIZATION TANKS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-18 | 2019-02-26
[6 empty] | Revised Plan |  |  | B: 2019-02-26; A: 2019-02-26
[6 empty] | Issue Actual |  |  | B: 2019-02-26; A: 2019-02-26
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00926; A: TPSK-LSPA1-T-ME-00926
[6 empty] | Return Date |  |  | B: 2019-03-15; A: 2019-03-15
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-5641 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5641 - WASTEWATER EQ TANK SKIMMED OIL PUMP |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-04-09; A: 2019-04-10
[6 empty] | Issue Actual |  |  | B: 2019-04-09; A: 2019-04-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01292; A: TPSK-LSPA1-T-ME-01292
[6 empty] | Return Date |  |  | B: 2019-05-16; A: 2019-05-16
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-5643 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5642 - COOLING WATER BD BASIN PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ
Rev. | bar: B to D
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-05-06; A: 2019-05-07; D: 2019-07-31
[6 empty] | Issue Actual |  |  | B: 2019-05-06; A: 2019-05-07; D: 2019-07-31
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01582; A: TPSK-LSPA1-T-ME-01582; D: TPSK-LSPA1-T-ME-02295
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-5644 | Mechanical Equipment Datasheet For Complex Waste Water Treatment Package |  | Class 2 | Purpose** | IFQ | IFQ | B: IFP
[6 empty] | Rev. | A | A | B: 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-15 | 2019-02-15 | B: 2019-08-09
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | B: 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00863 | TPSK-LSPA1-T-ME-00863 | B: TPSK-LSPA1-T-ME-02405
[6 empty] | Return Date | 2019-05-17 | 2019-05-17
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-5645 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5640 - OILY WASTEWATER EQ TANK PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | B: 2019-04-09; A: 2019-04-10
[6 empty] | Issue Actual |  |  | B: 2019-04-09; A: 2019-04-10
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-01292; A: TPSK-LSPA1-T-ME-01292
[6 empty] | Return Date |  |  | B: 2019-05-16; A: 2019-05-16
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-5648 | Mechanical Equipment Datasheet - C3 Hydrog Area Oily Wastewater Pump |  | Class 2 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Issue Actual |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00716; A: TPSK-LSPA1-T-ME-00716; D: TPSK-LSPA1-T-ME-00962; C: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-03-15; C: 2019-03-15
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5649 | Mechanical Equipment Datasheet - Flare KO Drum Oily Wastewater Pump |  | Class 2 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-28 | 2019-05-07
[6 empty] | Revised Plan |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Issue Actual |  |  | A: 2019-01-24; D: 2019-03-01; C: 2019-03-04
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00716; A: TPSK-LSPA1-T-ME-00716; D: TPSK-LSPA1-T-ME-00962; C: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; D: 2019-03-15; C: 2019-03-15
Owner Cmmt* | bar: B to C
| ME | OL1-2M03-5900 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5900 - SULFURIC ACID TANK |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2019-02-18 | 2019-02-26
[6 empty] | Revised Plan |  |  | A: 2019-01-29
[6 empty] | Issue Actual |  |  | A: 2019-01-29
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00754; A: TPSK-LSPA1-T-ME-00754
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-5901 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5900 - SULFURIC ACID PUMPS |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ
Rev. | bar: B to A
[6 empty] | Issue Plan | 2018-12-27 | 2019-01-17
[6 empty] | Revised Plan |  |  | B: 2019-02-01; A: 2019-02-04
[6 empty] | Issue Actual |  |  | B: 2019-02-01; A: 2019-02-04
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00787; A: TPSK-LSPA1-T-ME-00787
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-5902 | Mechanical Equipment Datasheet - Sulfuric Acid Metering Pumps |  | Class 2 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27 | 2019-01-17
[6 empty] | Revised Plan |  |  | 2019-02-01 | 2019-02-04 | 2019-04-08 | 2019-04-09 | 2019-04-17 | 2019-04-18
[6 empty] | Issue Actual |  |  | 2019-02-01 | 2019-02-04 | 2019-04-08 | 2019-04-09 | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00787 | TPSK-LSPA1-T-ME-00787 | TPSK-LSPA1-T-ME-01279 | TPSK-LSPA1-T-ME-01279 | TPSK-LSPA1-T-ME-01390 | TPSK-LSPA1-T-ME-01390
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; A: 2019-06-18; B: 2019-06-18
Owner Cmmt* | bar: B to A; A to B
| ME | OL1-2M03-5903 | Mechanical Equipment Datasheet - Sulfuric Acid Distribution Pumps |  | Class 2 | Purpose** | IFQ | IFQ | B: IFQ; A: IFQ
[6 empty] | Rev. | A | A | bar: B to A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15 | 2019-04-16 | B: 2019-05-21; A: 2019-05-23
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16 | B: 2019-05-21; A: 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01363 | TPSK-LSPA1-T-ME-01363 | B: TPSK-LSPA1-T-ME-01710; A: TPSK-LSPA1-T-ME-01710
[6 empty] | Return Date | 2019-06-17 | 2019-06-17 | A: 2019-06-21
[6 empty] | Owner Cmmt* | R2 | R2 | bar: A
| ME | OL1-2M03-5905 | Mechanical Equipment Datasheet - CTU Sulfuric Acid Metering Pumps |  | Class 2 | Purpose** | IFQ | IFQ | B: IFQ; A: IFQ
[6 empty] | Rev. | A | A | bar: B to A
Issue Plan
[6 empty] | Revised Plan | 2019-04-09 | 2019-04-10 | B: 2019-04-17; A: 2019-04-18
[6 empty] | Issue Actual | 2019-04-09 | 2019-04-10 | B: 2019-04-17; A: 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01292 | TPSK-LSPA1-T-ME-01292 | B: TPSK-LSPA1-T-ME-01390; A: TPSK-LSPA1-T-ME-01390
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-5910 | MECHANICAL EQUIPMENT DATASHEET FOR OXYGEN SCAVENGER INJECTION PACKAGE TAG: 10-PK-5910 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01490 | TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-5912 | MECHANICAL EQUIPMENT DATASHEET FOR NEUTRALIZATION AMINE INHIBITOR INJECTION PACKAGE TAG: 10-PK-5912 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01490 | TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-5914 | MECHANICAL EQUIPMENT DATASHEET FOR PHOSPHATE INJECTION PACKAGE TAG: 10-PK-5914 |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-26 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01490 | TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | 2019-06-18 | 2019-06-18
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-5950 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5950 - SODIUM HYPOCHLORITE TANK |  | Class 1 | Purpose** | IFR | IFD | B: IFQ; A: IFQ; D: IFQ; C: IFQ
Rev. | bar: B to C
[6 empty] | Issue Plan | 2019-02-18 | 2019-02-26
[6 empty] | Revised Plan |  |  | B: 2019-02-11; A: 2019-02-11; D: 2019-07-08; C: 2019-07-08
[6 empty] | Issue Actual |  |  | B: 2019-02-11; A: 2019-02-11; D: 2019-07-08; C: 2019-07-08
[6 empty] | Transmittal no. |  |  | B: TPSK-LSPA1-T-ME-00839; A: TPSK-LSPA1-T-ME-00839; D: TPSK-LSPA1-T-ME-02086; C: TPSK-LSPA1-T-ME-02086
[6 empty] | Return Date |  |  | B: 2019-02-28; A: 2019-02-28; C: 2019-08-06
Owner Cmmt* | bar: B to A; C
| ME | OL1-2M03-5951 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5950 - SODIUM HYPOCHLORITE METERING PUMPS |  | Class 1 | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | A | B | B | C | C
[6 empty] | Issue Plan | 2018-12-27 | 2019-01-17
[6 empty] | Revised Plan |  |  |  | 2019-01-28 | 2019-04-08 | 2019-04-09 | 2019-04-17 | 2019-04-18
[6 empty] | Issue Actual |  |  |  | 2019-01-28 | 2019-04-08 | 2019-04-09 | 2019-04-17 | 2019-04-18
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME -00742 | TPSK-LSPA1-T-ME -00742 | TPSK-LSPA1-T-ME-01279 | TPSK-LSPA1-T-ME-01279 | TPSK-LSPA1-T-ME-01390 | TPSK-LSPA1-T-ME-01390
[6 empty] | Return Date |  |  | B: 2019-02-21; A: 2019-02-21; A: 2019-06-18; B: 2019-06-18
Owner Cmmt* | bar: B to A; A to B
| ME | OL1-2M03-5955 | Mechanical Equipment Datasheet - CTU NaCOl Metering Pumps |  | Class 2 | Purpose** | IFQ | IFQ | B: IFQ; A: IFQ
[6 empty] | Rev. | A | A | bar: B to A
Issue Plan
[6 empty] | Revised Plan | 2019-04-09 | 2019-04-10 | B: 2019-04-17; A: 2019-04-18
[6 empty] | Issue Actual | 2019-04-09 | 2019-04-10 | B: 2019-04-17; A: 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01292 | TPSK-LSPA1-T-ME-01292 | B: TPSK-LSPA1-T-ME-01390; A: TPSK-LSPA1-T-ME-01390
[6 empty] | Return Date |  |  | B: 2019-06-18; A: 2019-06-18
Owner Cmmt* | bar: B to A
| ME | OL1-2M03-6004 | Mechanical Equipment Datasheet For Cracked Gas Compressor Bridge Crane (10-EL-2300) |  | Class 2 | Purpose** | IFQ | IFQ | B: IFP
[6 empty] | Rev. | A | A | B: 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-22 | 2019-02-25 | B: 2019-08-07
[6 empty] | Issue Actual | 2019-02-22 | 2019-02-25 | B: 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00913 | TPSK-LSPA1-T-ME-00913 | B: TPSK-LSPA1-T-ME-02360
[6 empty] | Return Date | 2019-04-05 | 2019-04-05
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-6005 | Mechanical Equipment Datasheet For Ethylene And Propylene Compressor Bridge Crane (10-EL-2800) |  | Class 2 | Purpose** | IFQ | IFQ | B: IFP
[6 empty] | Rev. | A | A | B: 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-22 | 2019-02-25 | B: 2019-08-07
[6 empty] | Issue Actual | 2019-02-22 | 2019-02-25 | B: 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00913 | TPSK-LSPA1-T-ME-00913 | B: TPSK-LSPA1-T-ME-02360
[6 empty] | Return Date | 2019-04-05 | 2019-04-05
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-7000 | Mechanical Equipment Data Sheet 10-d-D-2415 CG Liquid Dryer Feed Coalescer |  | Class 2 | Purpose** | IFP | IFP
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-16 | 2019-05-17
[6 empty] | Issue Actual | 2019-05-16 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01682 | TPSK-LSPA1-T-ME-01682
[6 empty] | Return Date | 2019-06-19 | 2019-06-19
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-7001 | Mechanical Equipment Data Sheet 10-D-765 C4-C5 Hydrog Coalescer Drum |  | Class 2 | Purpose** | IFP | IFP
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-16 | 2019-05-17
[6 empty] | Issue Actual | 2019-05-16 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01682 | TPSK-LSPA1-T-ME-01682
[6 empty] | Return Date | 2019-06-19 | 2019-06-19
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2M03-7002 | Mechanical Equipment Data Sheet 10-D-2136 Process Water Feed Coalescer |  | Class 2 | Purpose** | IFP | IFP
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-16 | 2019-05-17
[6 empty] | Issue Actual | 2019-05-16 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01682 | TPSK-LSPA1-T-ME-01682
[6 empty] | Return Date | 2019-06-19 | 2019-06-19
[6 empty] | Owner Cmmt* | R1 | R1
Category Code: M04 Mechanical design basic / philosophy / logic diagram
Category Code: M05 Mechanical calculation sheet / report
Category Code: M06 Mechanical equipment drawing
| ME | OL1-2M06-1001 | USC 36M FURNACE GENERAL ARRANGEMENT CROSS SECTION ELEVATION |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A |  |  | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | IFR: 2019-01-08; IFD: 2019-03-13; IFF: 2019-10-14
[6 empty] | Revised Plan |  |  |  | 2019-10-14 | 2019-04-15 | 2019-04-16 | 2019-06-26 | 2019-06-26
[6 empty] | Issue Actual |  | 2018-11-16 |  |  | 2019-04-15 | 2019-04-16 | 2019-06-26 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00327 | TPSK-LSPA1-T-ME-00327 |  |  | TPSK-LSPA1-T-ME-01361 | TPSK-LSPA1-T-ME-01361 | TPSK-LSPA1-T-ME-01993 | TPSK-LSPA1-T-ME-01993
[6 empty] | Return Date | IFR: 2019-05-24; IFR: 2019-05-24; IMP: 2019-08-05
Owner Cmmt* | bar: IFR to IFR; IMP
| ME | OL1-2M06-1002 | USC 36M FURNACE GENERAL ARRANGEMENT LONGITUDINAL ELEVATION |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A |  |  | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | R1 IFR: 2019-01-08; R1 IFD: 2019-03-13; R1 IFF: 2019-10-14
[6 empty] | Revised Plan |  |  |  | 2019-10-14 | 2019-04-15 | 2019-04-16 | 2019-06-26 | 2019-06-26
[6 empty] | Issue Actual |  | 2018-11-16 |  |  | 2019-04-15 | 2019-04-16 | 2019-06-26 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00327 | TPSK-LSPA1-T-ME-00327 |  |  | TPSK-LSPA1-T-ME-01361 | TPSK-LSPA1-T-ME-01361 | TPSK-LSPA1-T-ME-01993 | TPSK-LSPA1-T-ME-01993
[6 empty] | Return Date | R1 IFR: 2019-05-24; R1 IFR: 2019-05-24; R1 IMP: 2019-08-05
Owner Cmmt* | bar: R1 IFR to R1 IFR; R1 IMP
| ME | OL1-2M06-1004 | USC 36M FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A |  |  | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | R1 IFR: 2019-01-08; R1 IFD: 2019-03-13; R1 IFF: 2019-10-14
[6 empty] | Revised Plan |  |  |  | 2019-10-14 | 2019-04-26 | 2019-04-29 | 2019-06-26 | 2019-06-26
[6 empty] | Issue Actual | 2019-01-30 | 2019-01-31 |  |  | 2019-04-26 | 2019-04-29 | 2019-06-26 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00764 | TPSK-LSPA1-T-ME-00764 |  |  | TPSK-LSPA1-T-ME-01500 | TPSK-LSPA1-T-ME-01500 | TPSK-LSPA1-T-ME-01993 | TPSK-LSPA1-T-ME-01993
[6 empty] | Return Date | R1 IFR: 2019-02-21; R1 IFR: 2019-02-21; R1 IMP: 2019-08-05
Owner Cmmt* | bar: R1 IFR to R1 IFR; R1 IMP
| ME | OL1-2M06-1005 | USC 36M Recycle Furnace General Arrangement Instrumentation Sections |  | Class 2 | Purpose** | IMP | IFR | IFR | IMP | IMP | IMP
[6 empty] | Rev. | 0 | A | A | 0 | 1 | 1
Issue Plan
[6 empty] | Revised Plan |  | 2019-01-30 | 2019-01-31 | 2019-04-26 | 2019-06-26 | 2019-06-26
[6 empty] | Issue Actual |  | 2019-01-30 | 2019-01-31 | 2019-04-26 | 2019-06-26 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01500 | TPSK-LSPA1-T-ME-00764 | TPSK-LSPA1-T-ME-00764 | TPSK-LSPA1-T-ME-01500 | TPSK-LSPA1-T-ME-01993 | TPSK-LSPA1-T-ME-01993
[6 empty] | Return Date | R1 IFR: 2019-02-21; R1 IFD: 2019-02-21; R1 IMP: 2019-08-05
Owner Cmmt* | bar: R1 IFR to R1 IFD; R1 IMP
| ME | OL1-2M06-1101 | USC 36M FURNACE REFRACTORY & INSULATION RADIANT SECTION DETAILS |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A |  |  | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | IFR: 2019-01-23; R2 IFD: 2019-02-20; R2 IFF: 2019-02-20
[6 empty] | Revised Plan | R2 IMP: 2019-05-13; R2 IMP: 2019-05-14; R2 IMP: 2019-06-12; R2 IMP: 2019-06-14
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 |  |  | 2019-05-13 | 2019-05-14 | 2019-06-12 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01065 | TPSK-LSPA1-T-ME-01065 |  |  | TPSK-LSPA1-T-ME-01653 | TPSK-LSPA1-T-ME-01653 | TPSK-LSPA1-T-ME-01876 | TPSK-LSPA1-T-ME-01876
[6 empty] | Return Date | 2019-04-02 | 2019-04-02 |  |  | 2019-06-13 | 2019-06-13 |  | 2019-07-08
Owner Cmmt* | bar: IFR to R2 IFR; R2 IMP to R2 IMP; R2 IMP
| ME | OL1-2M06-1102 | USC 36M FURNACE REFRACTORY & INSULATION CONVECTION SECTION DETAILS |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; R2 IFR: A; R2 IMP: 0; R2 IMP: 0
[6 empty] | Issue Plan | IFR: 2019-01-23; R2 IFD: 2019-02-20; R2 IFF: 2019-02-20
[6 empty] | Revised Plan | R2 IMP: 2019-05-13; R2 IMP: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-03-14; R2 IFR: 2019-03-15; R2 IMP: 2019-05-13; R2 IMP: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; R2 IFR: TPSK-LSPA1-T-ME-01065; R2 IMP: TPSK-LSPA1-T-ME-01653; R2 IMP: TPSK-LSPA1-T-ME-01653
[6 empty] | Return Date | IFR: 2019-04-02; R2 IFR: 2019-04-02; R2 IMP: 2019-06-13; R2 IMP: 2019-06-13
Owner Cmmt* | bar: IFR to R2 IFR; R2 IMP to R2 IMP
| ME | OL1-2M06-1103 | USC 36M FURNACE INSULATION INSTALLATION DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; R2 IFD: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-03-14; R2 IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; R2 IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02; R2 IFR: 2019-04-02
Owner Cmmt* | bar: IFR to R2 IFR
| ME | OL1-2M06-1104 | USC 36M FURNACE REFRACTORY AND INSULATION ANCHOR DETAILS |  | Class 3 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; R2 IFR: A; R2 IMP: 0; R2 IMP: 0
[6 empty] | Issue Plan | IFR: 2019-01-23; R2 IFD: 2019-02-20; R2 IFF: 2019-02-20
[6 empty] | Revised Plan | R2 IMP: 2019-05-13; R2 IMP: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-03-14; R2 IFR: 2019-03-15; R2 IMP: 2019-05-13; R2 IMP: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; R2 IFR: TPSK-LSPA1-T-ME-01065; R2 IMP: TPSK-LSPA1-T-ME-01653; R2 IMP: TPSK-LSPA1-T-ME-01653
[6 empty] | Return Date | IFR: 2019-04-02; R2 IFR: 2019-04-02; R2 IMP: 2019-06-13; R2 IMP: 2019-06-13
Owner Cmmt* | bar: IFR to R2 IFR; R2 IMP to R2 IMP
| ME | OL1-2M06-1105 | USC 36M FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; R2 IFD: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-03-14; R2 IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; R2 IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02; R2 IFR: 2019-04-02
Owner Cmmt* | bar: IFR to R2 IFR
| ME | OL1-2M06-1106 | USC 36M FURNACE PEEP DOOR INSERT DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; R2 IFD: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-03-14; R2 IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; R2 IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02; R2 IFR: 2019-04-02
Owner Cmmt* | bar: IFR to R2 IFR
| ME | OL1-2M06-1107 | USC 36M FURNACE USX ASSEMBLY INSULATION DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFD
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-01-28; R2 IFD: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-05-08; R2 IFR: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01619; R2 IFR: TPSK-LSPA1-T-ME-01619
[6 empty] | Return Date | IFR: 2019-05-31; R2 IFR: 2019-05-31
Owner Cmmt* | bar: IFR to R2 IFR
| ME | OL1-2M06-1108 | USC 36M FURNACE DECOKE NOZZLE DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; R2 IFD: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-03-14; R2 IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; R2 IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02; R2 IFR: 2019-04-02
Owner Cmmt* | bar: IFR to R2 IFR
| ME | OL1-2M06-1109 | USC 36M FURNACE SEAL BOOT DETAILS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFI; R2 IFD: IFI; R2 IFF: IFC
[6 empty] | Rev. | R2 IFR: 0; R2 IFD: 0
[6 empty] | Issue Plan | IFR: 2019-09-01; R2 IFF: 2019-09-17
[6 empty] | Revised Plan | R2 IFR: 2019-04-16; R2 IFD: 2019-04-17
[6 empty] | Issue Actual | R2 IFR: 2019-04-16; R2 IFD: 2019-04-17
[6 empty] | Transmittal no. | R2 IFR: TPSK-LSPA1-T-ME-01368; R2 IFD: TPSK-LSPA1-T-ME-01368
Return Date
Owner Cmmt*
| ME | OL1-2M06-1110 | USC 36M FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | IFR: IFR; R2 IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-01; R2 IFR: 2019-09-17
[6 empty] | Revised Plan | IFR: 2019-09-01; R2 IFR: 2019-09-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1201 | USC 36M FURNACE RADIANT COIL ASSEMBLY AND DETAILS |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; R2 IFR: A; R2 IMP: 0; R2 IMP: 0
[6 empty] | Issue Plan | IFR: 2018-09-18; R2 IFD: 2018-12-07; R2 IFF: 2019-01-31
[6 empty] | Revised Plan | R2 IMP: 2018-12-13
[6 empty] | Issue Actual | IFR: 2018-10-08; R2 IFR: 2018-10-08; R2 IMP: 2018-12-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00062; R2 IFR: TPSK-LSPA1-T-ME-00062; R2 IMP: TPSK-LSPA1-T-ME-00486; R2 IMP: TPSK-LSPA1-T-ME-00486
[6 empty] | Return Date | IFR: 2019-02-21; R2 IFR: 2019-02-21; R2 IMP: 2019-01-16; R2 IMP: 2019-01-16
Owner Cmmt* | bar: IFR to R2 IFR; R2 IMP to R2 IMP
| ME | OL1-2M06-1202 | USC 36M FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  | Class 2 | Purpose** | IFR: IFR; R2 IFR: IFR; R2 IFD: IFC
Rev. | bar: IFR to R2 IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; R2 IFD: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | IFR: 2018-10-08; R2 IFR: 2018-10-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00062; R2 IFR: TPSK-LSPA1-T-ME-00062
[6 empty] | Return Date | IFR: 2019-02-21; R2 IFR: 2019-02-21
Owner Cmmt* | bar: IFR to R2 IFR
| ME | OL1-2M06-1203 | USC 36M FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; R2 IFR: A; R2 IMP: 0; R2 IMP: 0
[6 empty] | Issue Plan | IFR: 2018-09-18; R2 IFD: 2018-12-07; R2 IFF: 2019-01-31
[6 empty] | Revised Plan | R2 IMP: 2018-12-13
[6 empty] | Issue Actual | IFR: 2018-10-08; R2 IFR: 2018-10-08; R2 IMP: 2018-12-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00062; R2 IFR: TPSK-LSPA1-T-ME-00062; R2 IMP: TPSK-LSPA1-T-ME-00486; R2 IMP: TPSK-LSPA1-T-ME-00486
[6 empty] | Return Date | IFR: 2019-02-21; R2 IFR: 2019-02-21; R2 IMP: 2019-01-16; R2 IMP: 2019-01-16
Owner Cmmt* | bar: IFR to R2 IFR; R2 IMP to R2 IMP
| ME | OL1-2M06-1204 | USC 36M FURNACE FABRICATION ASSEMBLY OF CONVECTION COILS, FINNED TUBES, AND BILL OF MATERIAL |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A |  |  | 0 | 0 | 1 | 1 | 2 | 2
[6 empty] | Issue Plan | R1 IFR: 2018-10-16; R1 IFD: 2018-12-17; R1 IFF: 2019-03-20
[6 empty] | Revised Plan |  |  |  |  | 2019-02-13 | 2019-02-13 | 2019-04-15 | 2019-04-16 | 2019-05-28 | 2019-05-29
[6 empty] | Issue Actual | 2018-10-16 | 2018-10-17 |  |  | 2019-02-13 | 2019-02-13 | 2019-04-15 | 2019-04-16 | 2019-05-28 | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00182 | TPSK-LSPA1-T-ME-00182 |  |  | TPSK-LSPA1-T-ME-00848 | TPSK-LSPA1-T-ME-00848 | TPSK-LSPA1-T-ME-01356 | TPSK-LSPA1-T-ME-01356 | TPSK-LSPA1-T-ME-01754 | TPSK-LSPA1-T-ME-01754
[6 empty] | Return Date |  |  |  |  | 2019-03-07 | 2019-03-07 | 2019-05-24 | 2019-05-24 | 2019-06-21 | 2019-06-21
Owner Cmmt* | bar: R1 IMP to R1 IMP
| ME | OL1-2M06-1206 | USC 36M CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  | Class 2 | Purpose** | R1 IFR: IFR; R1 IFR: IFD; R1 IFD: IFF
Rev.
[6 empty] | Issue Plan | R1 IFR: 2018-09-18; R1 IFR: 2018-12-07; R1 IFD: 2019-01-31
[6 empty] | Revised Plan | R1 IFD: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1301 | USC 36M FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORTS AND DETAILS |  | Class 3 | Purpose** | R1 IFR: IFR; R1 IFR: IFI; R1 IFD: IFI; R1 IFF: IFC
[6 empty] | Rev. | R1 IFR: 0; R1 IFD: 0
[6 empty] | Issue Plan | R1 IFR: 2018-12-17; R1 IFF: 2019-01-28
[6 empty] | Revised Plan | R1 IFD: 2018-11-07
[6 empty] | Issue Actual | R1 IFD: 2018-11-07
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00286; R1 IFD: TPSK-LSPA1-T-ME-00286
Return Date
Owner Cmmt*
| ME | OL1-2M06-1302 | USC 36M FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  | Class 3 | Purpose** | R1 IFR: IFR; R1 IFR: IFI; R1 IFD: IFI; R1 IFF: IFC
[6 empty] | Rev. | R1 IFR: 0; R1 IFD: 0
[6 empty] | Issue Plan | R1 IFR: 2018-12-17; R1 IFF: 2019-01-28
[6 empty] | Revised Plan | R1 IFD: 2018-11-07
[6 empty] | Issue Actual | R1 IFD: 2018-11-07
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00286; R1 IFD: TPSK-LSPA1-T-ME-00286
Return Date
Owner Cmmt*
| ME | OL1-2M06-1303 | USC 36M FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  | Class 3 | Purpose** | R1 IFR: IFR; R1 IFR: IFI; R1 IFD: IFI; R1 IFF: IFC
Rev. | bar: R1 IFR to R1 IFD
[6 empty] | Issue Plan | R1 IFR: 2018-12-17; R1 IFF: 2019-01-28
[6 empty] | Revised Plan | R1 IFR: 2019-04-09; R1 IFD: 2019-04-10
[6 empty] | Issue Actual | R1 IFR: 2019-04-09; R1 IFD: 2019-04-10
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-01290; R1 IFD: TPSK-LSPA1-T-ME-01290
[6 empty] | Return Date | R1 IFR: 2019-05-15; R1 IFD: 2019-05-15
Owner Cmmt* | bar: R1 IFR to R1 IFD
| ME | OL1-2M06-2001 | USC 132SU FURNACE GENERAL ARRANGEMENT CROSS SECTION ELEVATION |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A |  |  | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | IFR: 2019-01-08; R1 IFD: 2019-03-13; R1 IFF: 2019-10-14
[6 empty] | Revised Plan |  |  |  | 2019-10-14 | 2019-04-16 | 2019-04-17 | 2019-06-26 | 2019-06-26
[6 empty] | Issue Actual |  | 2018-11-16 |  |  | 2019-04-16 | 2019-04-17 | 2019-06-26 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00328 | TPSK-LSPA1-T-ME-00328 |  |  | TPSK-LSPA1-T-ME-01369 | TPSK-LSPA1-T-ME-01369 | TPSK-LSPA1-T-ME-01993 | TPSK-LSPA1-T-ME-01993
[6 empty] | Return Date | R1 IMP: 2019-08-05
Owner Cmmt* | bar: R1 IMP
| ME | OL1-2M06-2002 | USC 132SU FURNACE GENERAL ARRANGEMENT LONGITUDINAL ELEVATION |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A |  |  | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | IFR: 2019-01-08; IFD: 2019-03-13; IFF: 2019-10-14
[6 empty] | Revised Plan |  |  |  | 2019-10-14 | 2019-04-16 | 2019-04-17 | 2019-06-26 | 2019-06-26
[6 empty] | Issue Actual |  | 2018-11-16 |  |  | 2019-04-16 | 2019-04-17 | 2019-06-26 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00328 | TPSK-LSPA1-T-ME-00328 |  |  | TPSK-LSPA1-T-ME-01369 | TPSK-LSPA1-T-ME-01369 | TPSK-LSPA1-T-ME-01993 | TPSK-LSPA1-T-ME-01993
[6 empty] | Return Date | R1 IMP: 2019-08-05
Owner Cmmt* | bar: R1 IMP
| ME | OL1-2M06-2004 | USC 132SU FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A |  |  | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | IFR: 2019-01-08; IFD: 2019-03-13; IFF: 2019-10-14
[6 empty] | Revised Plan | IFF: 2019-10-14; IMP: 2019-04-26; R1 IMP: 2019-06-26; R1 IMP: 2019-06-26
[6 empty] | Issue Actual | 2019-01-30 | 2019-01-31 |  |  |  | 2019-04-26 | 2019-06-26 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00766 | TPSK-LSPA1-T-ME-00766 |  |  | TPSK-LSPA1-T-ME-01500 | TPSK-LSPA1-T-ME-01500 | TPSK-LSPA1-T-ME-01993 | TPSK-LSPA1-T-ME-01993
[6 empty] | Return Date | IFR: 2019-02-21; IFR: 2019-02-21; R1 IMP: 2019-08-05
Owner Cmmt* | bar: IFR to IFR; R1 IMP
| ME | OL1-2M06-2005 | USC 132U Cracking Furnace General Arrangement Instrumentation Sections |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2018-12-21; IFD: 2019-01-23
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-01-30; IFR: 2019-01-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00768; IFR: TPSK-LSPA1-T-ME-00768
[6 empty] | Return Date | IFR: 2019-02-21; IFR: 2019-02-21
Owner Cmmt* | bar: IFR to IFR
| ME | OL1-2M06-2019 | USC 132U Cracking Furnace Seal Boot Details |  | Class 2 | Purpose** | IFR: IFI; IFR: IFI
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-16; IFR: 2019-04-17
[6 empty] | Issue Actual | IFR: 2019-04-16; IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01368; IFR: TPSK-LSPA1-T-ME-01368
Return Date
Owner Cmmt*
| ME | OL1-2M06-2101 | USC 132U FURNACE REFRACTORY & INSULATION RADIANT SECTION DETAILS |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A |  |  | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | IFR: 2019-01-23; IFD: 2019-02-20; IFF: 2019-02-20
[6 empty] | Revised Plan | IMP: 2019-05-13; IMP: 2019-05-14; IMP: 2019-06-12; IMP: 2019-06-14
[6 empty] | Issue Actual | 2019-03-14 | 2019-03-15 |  |  | 2019-05-13 | 2019-05-14 | 2019-06-12 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01065 | TPSK-LSPA1-T-ME-01065 |  |  | TPSK-LSPA1-T-ME-01653 | TPSK-LSPA1-T-ME-01653 | TPSK-LSPA1-T-ME-01876 | TPSK-LSPA1-T-ME-01876
[6 empty] | Return Date | 2019-04-02 | 2019-04-02 |  |  | 2019-06-13 | 2019-06-13 |  | 2019-07-08
Owner Cmmt* | bar: IFR to IFR; IMP to IMP; IMP
| ME | OL1-2M06-2102 | USC 132U FURNACE REFRACTORY & INSULATION CONVECTION SECTION DETAILS |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; IFR: A; IMP: 0; IMP: 0
[6 empty] | Issue Plan | IFR: 2019-01-23; IFD: 2019-02-20; IFF: 2019-02-20
[6 empty] | Revised Plan | IMP: 2019-05-13; IMP: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-03-14; IFR: 2019-03-15; IMP: 2019-05-13; IMP: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; IFR: TPSK-LSPA1-T-ME-01065; IMP: TPSK-LSPA1-T-ME-01653; IMP: TPSK-LSPA1-T-ME-01653
[6 empty] | Return Date | IFR: 2019-04-02; IFR: 2019-04-02; IMP: 2019-06-13; IMP: 2019-06-13
Owner Cmmt* | bar: IFR to IFR; IMP to IMP
| ME | OL1-2M06-2103 | USC 132U FURNACE INSULATION INSTALLATION DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; IFD: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-03-14; IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02; IFR: 2019-04-02
Owner Cmmt* | bar: IFR to IFR
| ME | OL1-2M06-2104 | USC 132U FURNACE REFRACTORY AND INSULATION ANCHOR DETAILS |  | Class 3 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; IFR: A; IMP: 0; IMP: 0
[6 empty] | Issue Plan | IFR: 2019-01-23; IFD: 2019-02-20; IFF: 2019-02-20
[6 empty] | Revised Plan | IMP: 2019-05-13; IMP: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-03-14; IFR: 2019-03-15; IMP: 2019-05-13; IMP: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; IFR: TPSK-LSPA1-T-ME-01065; IMP: TPSK-LSPA1-T-ME-01653; IMP: TPSK-LSPA1-T-ME-01653
[6 empty] | Return Date | IFR: 2019-04-02; IFR: 2019-04-02; IMP: 2019-06-13; IMP: 2019-06-13
Owner Cmmt* | bar: IFR to IFR; IMP to IMP
| ME | OL1-2M06-2105 | USC 132U FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; IFD: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-03-14; IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02; IFR: 2019-04-02
Owner Cmmt* | bar: IFR to IFR
| ME | OL1-2M06-2106 | USC 132U FURNACE PEEP DOOR INSERT DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; IFD: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-03-14; IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02; IFR: 2019-04-02
Owner Cmmt* | bar: IFR to IFR
| ME | OL1-2M06-2107 | USC 132U FURNACE USX ASSEMBLY INSULATION DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFD
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-01-28; IFD: 2019-02-25
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-05-08; IFR: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01619; IFR: TPSK-LSPA1-T-ME-01619
[6 empty] | Return Date | IFR: 2019-05-31; IFR: 2019-05-31
Owner Cmmt* | bar: IFR to IFR
| ME | OL1-2M06-2108 | USC 132U FURNACE DECOKE NOZZLE DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; IFD: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-03-14; IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02; IFR: 2019-04-02
Owner Cmmt* | bar: IFR to IFR
| ME | OL1-2M06-2109 | USC 132U FURNACE SEAL BOOT DETAILS |  | Class 3 | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-01; IFR: 2019-09-17
[6 empty] | Revised Plan | IFR: 2019-09-01; IFR: 2019-09-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2110 | USC 132U FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 3 | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-01; IFR: 2019-09-17
[6 empty] | Revised Plan | IFR: 2019-09-01; IFR: 2019-09-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2201 | USC 132U FURNACE RADIANT COIL ASSEMBLY AND DETAILS |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; IFR: A; IMP: 0; IMP: 0
[6 empty] | Issue Plan | IFR: 2018-09-18; IFD: 2018-12-07; IFF: 2019-01-31
[6 empty] | Revised Plan | IMP: 2018-12-13
[6 empty] | Issue Actual | IFR: 2018-10-08; IFR: 2018-10-08; IMP: 2018-12-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00062; IFR: TPSK-LSPA1-T-ME-00062; IMP: TPSK-LSPA1-T-ME-00486; IMP: TPSK-LSPA1-T-ME-00486
[6 empty] | Return Date | IFR: 2019-02-21; IFR: 2019-02-21; IMP: 2019-01-16; IMP: 2019-01-16
Owner Cmmt* | bar: IFR to IFR; IMP to IMP
| ME | OL1-2M06-2202 | USC 132U FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IFD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; IFD: 2019-09-17
Revised Plan
[6 empty] | Issue Actual | IFR: 2018-10-08; IFR: 2018-10-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00062; IFR: TPSK-LSPA1-T-ME-00062
[6 empty] | Return Date | IFR: 2019-02-21; IFR: 2019-02-21
Owner Cmmt* | bar: IFR to IFR
| ME | OL1-2M06-2203 | USC 132U FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; IFR: A; IMP: 0; IMP: 0
[6 empty] | Issue Plan | IFR: 2018-09-18; IFD: 2018-12-07; IFF: 2019-01-31
[6 empty] | Revised Plan | IMP: 2018-12-13
[6 empty] | Issue Actual | IFR: 2018-10-08; IFR: 2018-10-08; IMP: 2018-12-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00062; IFR: TPSK-LSPA1-T-ME-00062; IMP: TPSK-LSPA1-T-ME-00486; IMP: TPSK-LSPA1-T-ME-00486
[6 empty] | Return Date | IFR: 2019-02-21; IFR: 2019-02-21; IMP: 2019-01-16; IMP: 2019-01-16
Owner Cmmt* | bar: IFR to IFR; IMP to IMP
| ME | OL1-2M06-2204 | USC 132U FURNACE FABRICATION ASSEMBLY OF CONVECTION COILS, FINNED TUBES, AND BILL OF MATERIAL |  | Class 2 | Purpose** | IFR | IFR | IFD | IFF | IMP | IMP | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A |  |  | 0 | 0 | 1 | 1 | 2 | 2
[6 empty] | Issue Plan | R1 IFR: 2018-10-16; R1 IFD: 2018-12-17; R1 IFF: 2019-03-20
[6 empty] | Revised Plan |  |  |  |  | 2019-02-13 | 2019-02-13 | 2019-04-15 | 2019-04-16 | 2019-05-28 | 2019-05-29
[6 empty] | Issue Actual | 2018-10-16 | 2018-10-17 |  |  | 2019-02-13 | 2019-02-13 | 2019-04-15 | 2019-04-16 | 2019-05-28 | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00182 | TPSK-LSPA1-T-ME-00182 |  |  | TPSK-LSPA1-T-ME-00848 | TPSK-LSPA1-T-ME-00848 | TPSK-LSPA1-T-ME-01356 | TPSK-LSPA1-T-ME-01356 | TPSK-LSPA1-T-ME-01754 | TPSK-LSPA1-T-ME-01754
[6 empty] | Return Date |  |  |  |  | 2019-03-07 | 2019-03-07 | 2019-05-24 | 2019-05-24 | 2019-06-21 | 2019-06-21
Owner Cmmt* | bar: R1 IMP to R1 IMP
| ME | OL1-2M06-2206 | USC 132U CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  | Class 2 | Purpose** | R1 IFR: IFR; R1 IFR: IFD; R1 IFD: IFF
Rev.
[6 empty] | Issue Plan | R1 IFR: 2018-09-18; R1 IFR: 2018-12-07; R1 IFD: 2019-01-31
[6 empty] | Revised Plan | R1 IFD: 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2207 | DILUTION STEAM MIXING TEE DRAWING |  | Class 3 | Purpose** | R1 IFR: IFI; R1 IFR: IFI
[6 empty] | Rev. | R1 IFR: 0; R1 IFR: 0
Issue Plan
[6 empty] | Revised Plan | R1 IFR: 2019-01-23
[6 empty] | Issue Actual | R1 IFR: 2019-01-23
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00669; R1 IFR: TPSK-LSPA1-T-ME-00669
Return Date
Owner Cmmt*
| ME | OL1-2M06-2207- | USC 132U Cracking Furnace Dilution Mixing Tee Details |  | Class 2 | Purpose** | R1 IFR: IMP; R1 IFR: IMP
Rev. | bar: R1 IFR to R1 IFR
Issue Plan
[6 empty] | Revised Plan | R1 IFR: 2019-04-26; R1 IFR: 2019-04-29
[6 empty] | Issue Actual | R1 IFR: 2019-04-26; R1 IFR: 2019-04-29
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-01509; R1 IFR: TPSK-LSPA1-T-ME-01509
[6 empty] | Return Date | R1 IFR: 2019-05-31; R1 IFR: 2019-05-31
Owner Cmmt* | bar: R1 IFR to R1 IFR
| ME | OL1-2M06-2301 | USC 132SU FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT & DETAILS |  | Class 3 | Purpose** | R1 IFR: IFR; R1 IFR: IFI; R1 IFD: IFI; R1 IFF: IFC
[6 empty] | Rev. | R1 IFR: 0; R1 IFD: 0
[6 empty] | Issue Plan | R1 IFR: 2018-12-17; R1 IFF: 2019-01-28
[6 empty] | Revised Plan | R1 IFD: 2018-11-08
[6 empty] | Issue Actual | R1 IFD: 2018-11-08
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00289; R1 IFD: TPSK-LSPA1-T-ME-00289
Return Date
Owner Cmmt*
| ME | OL1-2M06-2302 | USC 132SU FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  | Class 3 | Purpose** | R1 IFR: IFR; R1 IFR: IFI; R1 IFD: IFI; R1 IFF: IFC
[6 empty] | Rev. | R1 IFR: 0; R1 IFD: 0
[6 empty] | Issue Plan | R1 IFR: 2018-12-17; R1 IFF: 2019-01-28
[6 empty] | Revised Plan | R1 IFD: 2018-11-08
[6 empty] | Issue Actual | R1 IFD: 2018-11-08
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00289; R1 IFD: TPSK-LSPA1-T-ME-00289
Return Date
Owner Cmmt*
| ME | OL1-2M06-2303 | USC 132SU FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  | Class 3 | Purpose** | R1 IFR: IFR; R1 IFR: IFI; R1 IFD: IFI; R1 IFF: IFC
Rev. | bar: R1 IFR to R1 IFD
[6 empty] | Issue Plan | R1 IFR: 2018-12-17; R1 IFF: 2019-01-28
[6 empty] | Revised Plan | R1 IFR: 2019-04-09; R1 IFD: 2019-04-10
[6 empty] | Issue Actual | R1 IFR: 2019-04-09; R1 IFD: 2019-04-10
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-01291; R1 IFD: TPSK-LSPA1-T-ME-01291
[6 empty] | Return Date | R1 IFR: 2019-05-15; R1 IFD: 2019-05-15
Owner Cmmt* | bar: R1 IFR to R1 IFD
| ME | OL1-2M06-2554 | FURNACE PEEP DOOR DETAILS (RIGHT HAND) |  | Class 3 | Purpose** | R1 IFR: IFR; R1 IFR: IFI; R1 IFD: IFI; R1 IFF: IFC
[6 empty] | Rev. | R1 IFR: 0; R1 IFD: 0
[6 empty] | Issue Plan | R1 IFR: 2019-01-29; R1 IFF: 2019-03-27
[6 empty] | Revised Plan | R1 IFD: 2018-12-04
[6 empty] | Issue Actual | R1 IFD: 2018-12-04
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00422; R1 IFD: TPSK-LSPA1-T-ME-00422
Return Date
Owner Cmmt*
Category Code: M07 Mechanical certification, inspection and test record |  |  |  |  | Class 3 | Purpose**
Category Code: M20 Static Equipment Datasheet | [5 empty] | Rev.
Category Code: M21 Rotating Machinery Datasheet | [5 empty] | Issue Plan
Category Code: M22 Package Unit-Datasheet | [5 empty] | Revised Plan
Category Code: M55 Request for Quotation (RFQ) for Mechanical work | [5 empty] | Issue Actual
| ME | OL1-2M55-0003 | MR COOLING WATER PUMPS |  | Class 2 | Purpose** | R1 IFR: IFQ; R1 IFR: IFQ
Rev. | bar: R1 IFR to R1 IFR
Issue Plan
[6 empty] | Revised Plan | R1 IFR: 2018-11-15
[6 empty] | Issue Actual | R1 IFR: 2018-11-15
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00319; R1 IFR: TPSK-LSPA1-T-ME-00319
[6 empty] | Return Date | R1 IFR: 2018-12-10; R1 IFR: 2018-12-10
Owner Cmmt* | bar: R1 IFR to R1 IFR
| ME | OL1-2M55-0014 | MR INTEGRALLY GEARED COMPRESSORS |  | Class 2 | Purpose** | R1 IFR: IFQ
Rev. | bar: R1 IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00198
[6 empty] | Return Date | R1 IFR: 2018-11-07
Owner Cmmt* | bar: R1 IFR
| ME | OL1-2M55-0015 | MR API CENTRIFUGAL PUMPS - LLI |  | Class 2 | Purpose** | R1 IFR: IFQ; R1 IFR: IFQ
Rev. | bar: R1 IFR to R1 IFR
Issue Plan
[6 empty] | Revised Plan | R1 IFR: 2018-10-31
[6 empty] | Issue Actual | R1 IFR: 2018-10-31
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00257; R1 IFR: TPSK-LSPA1-T-ME-00257
[6 empty] | Return Date | R1 IFR: 2018-11-27; R1 IFR: 2018-11-27
Owner Cmmt* | bar: R1 IFR to R1 IFR
| ME | OL1-2M55-0055 | MR FOR COLUMNS TRAYS & INTERN. (OPEN SOURCE ITEMS) |  | Class 2 | Purpose** | R1 IFR: IFQ
Rev. | bar: R1 IFR
Issue Plan
[6 empty] | Revised Plan | R1 IFR: 2018-11-09
[6 empty] | Issue Actual | R1 IFR: 2018-11-09
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00300
[6 empty] | Return Date | R1 IFR: 2018-12-06
Owner Cmmt* | bar: R1 IFR
| ME | OL1-2M55-0066 | MR FOR COLD BOX AND CORE EXCHANGERS |  | Class 2 | Purpose** | R1 IFR: IFQ
Rev. | bar: R1 IFR
Issue Plan
[6 empty] | Revised Plan | R1 IFR: 2018-10-04
[6 empty] | Issue Actual | R1 IFR: 2018-10-04
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00125
[6 empty] | Return Date | R1 IFR: 2018-10-24
Owner Cmmt* | bar: R1 IFR
| ME | OL1-2M55-0075 | MR FOR COLUMNS TRAYS & INTERN. (UOP MD TRAYS FOR COLUMNS) |  | Class 2 | Purpose** | R1 IFR: IMP; R1 IFR: IFQ; R1 IFD: IMP
Rev. | bar: R1 IFR to R1 IFD
Issue Plan
[6 empty] | Revised Plan | R1 IFR: 2018-11-07; R1 IFD: 2018-11-14
[6 empty] | Issue Actual | R1 IFR: 2018-11-07; R1 IFD: 2018-11-14
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00314; R1 IFR: TPSK-LSPA1-T-ME-00278; R1 IFD: TPSK-LSPA1-T-ME-00314
[6 empty] | Return Date | R1 IFR: 2019-02-08; R1 IFR: 2018-11-29; R1 IFD: 2019-02-08
Owner Cmmt* | bar: R1 IFR to R1 IFD
| ME | OL1-2M55-2002 | MATERIAL REQUISITION FOR CONVECTION FITTING |  | Class 3 | Purpose** | R1 IFR: IFQ
Rev. | bar: R1 IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00207
Return Date
Owner Cmmt*
| ME | OL1-2M55-2003 | MATERIAL REQUISITION FOR QUENCH SYSTEM |  | Class 3 | Purpose** | R1 IFR: IFQ; R1 IFR: IFQ; R1 IFD: IFP
[6 empty] | Rev. | R1 IFR: A; R1 IFR: A; R1 IFD: 0
Issue Plan
[6 empty] | Revised Plan | R1 IFR: 2018-10-26; R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFR: 2018-10-26; R1 IFD: 2018-12-10
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00233; R1 IFR: TPSK-LSPA1-T-ME-00233; R1 IFD: TPSK-LSPA1-T-ME-00466
Return Date
Owner Cmmt*
| ME | OL1-2M55-2004 | MATERIAL REQUISITION FOR RADIANT COILS |  | Class 3 | Purpose** | R1 IFR: IFQ
Rev. | bar: R1 IFR
Issue Plan
[6 empty] | Revised Plan | R1 IFR: 2018-10-18
[6 empty] | Issue Actual | R1 IFR: 2018-10-18
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00063
Return Date
Owner Cmmt*
| ME | OL1-2M55-2005 | MATERIAL REQUISITION FOR ID FAN |  | Class 3 | Purpose** | R1 IFR: IFQ
Rev. | bar: R1 IFR
Issue Plan
[6 empty] | Revised Plan | R1 IFR: 2018-11-05
[6 empty] | Issue Actual | R1 IFR: 2018-11-05
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00269
Return Date
Owner Cmmt*
| ME | OL1-2M55-2007 | MATERIAL REQUISITION FOR ITS |  | Class 3 | Purpose** | R1 IFR: IFQ
Rev. | bar: R1 IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00329
[6 empty] | Return Date | R1 IFR: 2018-12-10
Owner Cmmt* | bar: R1 IFR
| ME | OL1-2M55-2018 | DILUTION STEAM MIXING TEE MR |  | Class 2 | Purpose** | R1 IFR: IFQ
Rev. | bar: R1 IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00263
Return Date
Owner Cmmt*
| ME | OL1-4M55-2001 | Material Requisition for Convection Tubes |  |  | Purpose** | R1 IFR: IFQ
Rev. | bar: R1 IFR
Issue Plan
[6 empty] | Revised Plan | R1 IFR: 2018-09-13
[6 empty] | Issue Actual | R1 IFR: 2018-09-13
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-00044
Return Date
Owner Cmmt*
Category Code: M71 Appraisal Report for Consultancy Service
Category Code: M72 Appraisal Report for EPC Contractor Work
Category Code: M73 Appraisal Report for Vendor/Supplier
Category Code: M90 Vendor Document/drawings
Category Code: M91 Index/List
| ME | OL1-2M91-0001 | Item Index |  | Class 2 | Purpose** | R1 IFR: IFR; R1 IFR: IFR; R1 IFD: IBD; R1 IFF: IBD
Rev. | bar: R1 IFR to R1 IFF
Issue Plan
[6 empty] | Revised Plan | R1 IFR: 2019-03-15; R1 IFR: 2019-03-18; R1 IFD: 2019-06-13; R1 IFF: 2019-06-14
[6 empty] | Issue Actual | R1 IFR: 2019-03-15; R1 IFR: 2019-03-18; R1 IFD: 2019-06-13; R1 IFF: 2019-06-14
[6 empty] | Transmittal no. | R1 IFR: TPSK-LSPA1-T-ME-01080; R1 IFR: TPSK-LSPA1-T-ME-01080; R1 IFD: TPSK-LSPA1-T-ME-01887; R1 IFF: TPSK-LSPA1-T-ME-01887
[6 empty] | Return Date | R1 IFR: 2019-04-05; R1 IFR: 2019-04-05
Owner Cmmt* | bar: R1 IFR to R1 IFR
| ME | OL1-2M91-0002 | Item Index Furnace Island |  | Class 2 | Purpose** | IFR | IFR | IBD | IBD | IBD | IBD | IBD | IDD1
[6 empty] | Rev. | A | A | B | B | C | C | D | E
Issue Plan
[6 empty] | Revised Plan | 2019-03-15 | 2019-03-18 | 2019-05-30 | 2019-05-31 | 2019-07-11 | 2019-07-11 | 2019-07-23 | 2019-08-14
[6 empty] | Issue Actual | 2019-03-15 | 2019-03-18 | 2019-05-30 | 2019-05-31 | 2019-07-11 | 2019-07-11 | 2019-07-23 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01080 | TPSK-LSPA1-T-ME-01080 | TPSK-LSPA1-T-ME-01766 | TPSK-LSPA1-T-ME-01766 | TPSK-LSPA1-T-ME-02122 | TPSK-LSPA1-T-ME-02122 | TPSK-LSPA1-T-ME-02226 | TPSK-LSPA1-T-ME-02411
[6 empty] | Return Date | 2019-03-15: 2019-04-05; 2019-03-18: 2019-04-05; 2019-07-11: 2019-07-19; 2019-07-23: 2019-08-06
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18; 2019-07-11; 2019-07-23
| ME | OL1-2M91-1001 | Approved Vendor List for 36M and 132U Furnace |  | Class 2 | Purpose** | 2019-03-15: IMP; 2019-03-18: IMP
[6 empty] | Rev. | 2019-03-15: 0; 2019-03-18: 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2018-10-23
[6 empty] | Issue Actual | 2019-03-18: 2018-10-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-ME-00211; 2019-03-18: TPSK-LSPA1-T-ME-00211
Return Date
Owner Cmmt*
Category Code: M92 Procedures & Standards
| ME | OL1-2M92-0002 | Special Technical Specification For Furnace Island Erection |  | Class 2 | Purpose** | 2019-03-15: IFQ
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-24
[6 empty] | Issue Actual | 2019-03-15: 2019-07-24
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-ME-02247
Return Date
Owner Cmmt*
| ME | OL1-2M92-2001 | SPECIFICATION FOR CENTRIFUGALLY CAST TUBE FOR RADIANT AND TRANSFER LINES |  | Class 2 | Purpose** | 2019-03-15: IMP; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IMP
[6 empty] | Rev. | 2019-03-15: 0; 2019-03-18: A; 2019-05-30: A; 2019-05-31: 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2018-09-10; 2019-05-30: 2018-09-11; 2019-05-31: 2018-12-11
[6 empty] | Issue Actual | 2019-03-18: 2018-09-10; 2019-05-30: 2018-09-11; 2019-05-31: 2018-12-11
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-ME-00470; 2019-03-18: TPSK-LSPA1-T-ME-00037; 2019-05-30: TPSK-LSPA1-T-ME-00037; 2019-05-31: TPSK-LSPA1-T-ME-00470
[6 empty] | Return Date | 2019-03-18: 2018-09-25; 2019-05-30: 2018-09-25
Owner Cmmt* | bar: 2019-03-18 to 2019-05-30
| ME | OL1-2M92-2002 | SPECIFICATION FOR STATICALLY CAST FITTINGS FOR RADIANT COILS AND TRANSFER LINES IN CRACKING FURNACES |  | Class 2 | Purpose** | 2019-03-15: IMP; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IMP
[6 empty] | Rev. | 2019-03-15: 0; 2019-03-18: A; 2019-05-30: A; 2019-05-31: 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2018-09-10; 2019-05-30: 2018-09-11; 2019-05-31: 2018-12-11
[6 empty] | Issue Actual | 2019-03-18: 2018-09-10; 2019-05-30: 2018-09-11; 2019-05-31: 2018-12-11
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-ME-00471; 2019-03-18: TPSK-LSPA1-T-ME-00037; 2019-05-30: TPSK-LSPA1-T-ME-00037; 2019-05-31: TPSK-LSPA1-T-ME-00471
[6 empty] | Return Date | 2019-03-18: 2018-09-25; 2019-05-30: 2018-09-25
Owner Cmmt* | bar: 2019-03-18 to 2019-05-30
| ME | OL1-2M92-2003 | SPECIFICATION FOR CAST INTERMEDIATE TUBE SUPPORTS |  | Class 3 | Purpose** | IFR | IFI | IFI | IFQ | IFP | IMP | IMP
[6 empty] | Rev. | 2019-03-18: 0; 2019-05-30: 0; 2019-07-11: 1; 2019-07-23: 1
[6 empty] | Issue Plan | 2019-03-15: 2018-10-26; 2019-05-31: 2018-10-26; 2019-07-11: 2019-01-07
[6 empty] | Revised Plan | 2019-05-30: 2018-10-26; 2019-07-23: 2018-12-17
[6 empty] | Issue Actual | 2019-05-30: 2018-10-26; 2019-07-23: 2018-12-17
[6 empty] | Transmittal no. | 2019-03-18: TPSK-LSPA1-T-ME-00232; 2019-05-30: TPSK-LSPA1-T-ME-00232; 2019-07-11: TPSK-LSPA1-T-ME-00517; 2019-07-23: TPSK-LSPA1-T-ME-00517
Return Date
Owner Cmmt*
| ME | OL1-2M92-2004 | SPECIFICATION FOR FABRICATION OF CONVECTION COILS FOR CRACKING FURNACES |  | Class 2 | Purpose** | IFR | IFR | IFQ | IFP | IMP | IMP
[6 empty] | Rev. | 2019-03-15: A; 2019-03-18: A; 2019-07-11: 0; 2019-07-11: 0
[6 empty] | Issue Plan | 2019-03-15: 2018-09-07; 2019-05-30: 2018-09-19; 2019-05-31: 2018-12-13
[6 empty] | Revised Plan | 2019-07-11: 2019-05-10; 2019-07-11: 2019-05-13
[6 empty] | Issue Actual | 2019-03-15: 2019-02-12; 2019-03-18: 2019-02-12; 2019-07-11: 2019-05-10; 2019-07-11: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-ME-00842; 2019-03-18: TPSK-LSPA1-T-ME-00842; 2019-07-11: TPSK-LSPA1-T-ME -01640; 2019-07-11: TPSK-LSPA1-T-ME -01640
[6 empty] | Return Date | 2019-03-15: 2019-03-07; 2019-03-18: 2019-03-07
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| ME | OL1-2M92-2005 | SPECIFICATION FOR SUPPLY & INSTALLATION OF CERAMIC FIBER BLANKET & CF MODULE |  | Class 2 | Purpose** | IFR | IFR | IFQ | IFP | IMP | IMP
[6 empty] | Rev. | 2019-03-15: A; 2019-03-18: A; 2019-07-11: 0; 2019-07-11: 0
[6 empty] | Issue Plan | 2019-03-15: 2019-01-31; 2019-05-30: 2019-02-07; 2019-05-31: 2019-04-09
[6 empty] | Revised Plan | 2019-07-11: 2019-05-10; 2019-07-11: 2019-05-13
[6 empty] | Issue Actual | 2019-03-15: 2019-02-12; 2019-03-18: 2019-02-12; 2019-07-11: 2019-05-10; 2019-07-11: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-ME-00842; 2019-03-18: TPSK-LSPA1-T-ME-00842; 2019-07-11: TPSK-LSPA1-T-ME -01640; 2019-07-11: TPSK-LSPA1-T-ME -01640
[6 empty] | Return Date | 2019-03-15: 2019-03-07; 2019-03-18: 2019-03-07
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| ME | OL1-2M92-2006 | SPECIFICATION FOR SUPPLY & INSTALLATION OF REFRACTORY INSULATION |  | Class 2 | Purpose** | IFR | IFR | IFQ | IFP | IMP | IMP
[6 empty] | Rev. | 2019-03-15: A; 2019-03-18: A; 2019-07-11: 0; 2019-07-11: 0
[6 empty] | Issue Plan | 2019-03-15: 2019-01-31; 2019-05-30: 2019-02-07; 2019-05-31: 2019-04-09
[6 empty] | Revised Plan | 2019-07-11: 2019-05-10; 2019-07-11: 2019-05-13
[6 empty] | Issue Actual | 2019-03-15: 2019-02-12; 2019-03-18: 2019-02-12; 2019-07-11: 2019-05-10; 2019-07-11: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-ME-00842; 2019-03-18: TPSK-LSPA1-T-ME-00842; 2019-07-11: TPSK-LSPA1-T-ME -01640; 2019-07-11: TPSK-LSPA1-T-ME -01640
[6 empty] | Return Date | 2019-03-15: 2019-03-07; 2019-03-18: 2019-03-07
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| ME | OL1-2M92-2007 | SPECIFICATION FOR SLE / USX QUENCH EXCHANGERS |  | Class 2 | Purpose** | 2019-03-15: IMP; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IMP
[6 empty] | Rev. | 2019-03-15: 0; 2019-03-18: A; 2019-05-30: A; 2019-05-31: 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2018-09-20; 2019-05-30: 2018-09-24; 2019-05-31: 2018-12-05
[6 empty] | Issue Actual | 2019-03-18: 2018-09-20; 2019-05-30: 2018-09-24; 2019-05-31: 2018-12-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-ME-00427; 2019-03-18: TPSK-LSPA1-T-ME-00067; 2019-05-30: TPSK-LSPA1-T-ME-00067; 2019-05-31: TPSK-LSPA1-T-ME-00427
[6 empty] | Return Date | 2019-03-18: 2018-10-12; 2019-05-30: 2018-10-12
Owner Cmmt* | bar: 2019-03-18 to 2019-05-30
| ME | OL1-2M92-2008 | SPECIFICATION FOR TLX EXCHANGERS |  | Class 2 | Purpose** | 2019-03-15: IMP; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IMP
[6 empty] | Rev. | 2019-03-15: 0; 2019-03-18: A; 2019-05-30: A; 2019-05-31: 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2018-09-20; 2019-05-30: 2018-09-24; 2019-05-31: 2018-12-05
[6 empty] | Issue Actual | 2019-03-18: 2018-09-20; 2019-05-30: 2018-09-24; 2019-05-31: 2018-12-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-ME-00428; 2019-03-18: TPSK-LSPA1-T-ME-00067; 2019-05-30: TPSK-LSPA1-T-ME-00067; 2019-05-31: TPSK-LSPA1-T-ME-00428
[6 empty] | Return Date | 2019-03-18: 2018-10-12; 2019-05-30: 2018-10-12
Owner Cmmt* | bar: 2019-03-18 to 2019-05-30
| ME | OL1-2M92-2009 | SPECIFICATION FOR BURNERS |  | Class 2 | Purpose** | IFR | IFR | IFQ | IFP | IMP | IMP
[6 empty] | Rev. | 2019-03-15: A; 2019-03-18: A; 2019-07-11: 0; 2019-07-11: 0
[6 empty] | Issue Plan | 2019-03-15: 2018-10-25; 2019-05-30: 2018-10-25; 2019-05-31: 2019-01-23
[6 empty] | Revised Plan | 2019-07-11: 2019-01-22
[6 empty] | Issue Actual | 2019-03-18: 2018-10-25; 2019-07-11: 2019-01-22
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-00231; 2019-03-18: TPSK-LSPA1-T-PE-00231; 2019-07-11: TPSK-LSPA1-T-ME-00698; 2019-07-11: TPSK-LSPA1-T-ME-00698
[6 empty] | Return Date | 2019-03-15: 2018-11-14; 2019-03-18: 2018-11-14; 2019-07-11: 2019-02-14; 2019-07-11: 2019-02-14
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18; 2019-07-11 to 2019-07-11
| ME | OL1-4M92-2001 | Project Specification for Centrifugally Cast Tubes for Radiant Coils and Transfer Lines in Cracking Furnaces |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFQ; 2019-05-30: IFP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2018-10-26; 2019-03-18: 2018-10-26; 2019-05-30: 2019-01-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-4M92-2002 | Project Specification for Statically Cast Fittings for Radiant Coils and Transfer Lines in Cracking Furnaces |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFQ; 2019-05-30: IFP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2018-10-26; 2019-03-18: 2018-10-26; 2019-05-30: 2019-01-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-4M92-2007 | Project Specification For SLE and USX Exchangers |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFQ; 2019-05-30: IFP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2018-09-20; 2019-03-18: 2018-10-26; 2019-05-30: 2018-12-10
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-4M92-2008 | Project Specification For Transfer Line Exchangers |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFQ; 2019-05-30: IFP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2018-09-20; 2019-03-18: 2018-10-26; 2019-05-30: 2018-12-10
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: M93 Policy , Guidelines & Memo
Category Code: M94 Forms & Templates
Category Code: M95 Progress/Status Reports
Category Code: M96 Spare part list for construction/precommissioning/commissioning
Category Code: M97 Spare Part List for Maintenance During First Two Years Operation
Category Code: M98 Special tools books
Category Code: M99 Other
Category Code: O01 Precommissioning Plan and Schedule
Category Code: O02 Commissioning Plan and Schedule |  |  |  |  | Class 2 | Purpose**
Category Code: O03 Startup Plan and Schedule | [5 empty] | Rev.
Category Code: O04 Performance Test Plan and Schedule | [5 empty] | Issue Plan
| PE | OL1-2O04-1004 | PERFORMANCE TEST PROCEDURE |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-09-30
[6 empty] | Revised Plan | 2019-03-15: 2019-09-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O05 Production Plan
Category Code: O06 Operating Manuals
| PE | OL1-2O06-0001 | CUO 107 - OPERATING MANUALS |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-12-15; 2019-03-18: 2021-06-30
[6 empty] | Revised Plan | 2019-03-15: 2020-12-15; 2019-03-18: 2021-06-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O07 Startup Lists
| PE | OL1-2O07-0002 | CUO 110 - PLANT MAINTENANCE MANUAL - OFFSITES - S04 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-11-15; 2019-03-18: 2019-12-15
[6 empty] | Revised Plan | 2019-03-15: 2019-11-15; 2019-03-18: 2019-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O07-0003 | CUO 110 - PLANT MAINTENANCE MANUAL - WASTE WATER TREATMENT - S05 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-09-15; 2019-03-18: 2020-10-01
[6 empty] | Revised Plan | 2019-03-15: 2020-09-15; 2019-03-18: 2020-10-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O07-0004 | CUO 110 - PLANT MAINTENANCE MANUAL - FURNACES - S06 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-12-01; 2019-03-18: 2021-01-30
[6 empty] | Revised Plan | 2019-03-15: 2020-12-01; 2019-03-18: 2021-01-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O08 Startup Philosophy |  |  |  |  | Class 2 | Purpose**
| PE | OL1-2O08-0001 | START-UP DELIVERABLE LIST |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-11-01; 2019-03-18: 2019-12-01
[6 empty] | Revised Plan | 2019-03-15: 2019-11-01; 2019-03-18: 2019-12-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O08-0002 | START-UP PACKAGE LIST |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-10-30; 2019-03-18: 2021-12-31
[6 empty] | Revised Plan | 2019-03-15: 2021-10-30; 2019-03-18: 2021-12-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O09 Scope of Work |  |  |  |  | Class 2 | Purpose**
| PE | OL1-2O09-0001 | RESPONSABILITY MATRIX - DEFINITION OF MECHANICAL COMPLET./PRE-COMMISSIONING TPIT-SUBCONTRACTOR |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-01-15; 2019-03-18: 2020-01-30
[6 empty] | Revised Plan | 2019-03-15: 2020-01-15; 2019-03-18: 2020-01-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O09-0002 | DEFINITION OF SCOPE OF WORK - TPIT - SPECIALIZED COMPANY |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-01-15; 2019-03-18: 2020-01-30
[6 empty] | Revised Plan | 2019-03-15: 2020-01-15; 2019-03-18: 2020-01-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O10 Maintenance Manuals
| PE | OL1-2O10-0002 | CUO 110 - MAINTENANCE PHILOSOPHY DURING INTERIM MAINTENANCE MANAGEMENT |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-09-16; 2019-03-18: 2021-11-15
[6 empty] | Revised Plan | 2019-03-15: 2021-09-16; 2019-03-18: 2021-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O11 Operating Condition Calculation
Category Code: O12 Product Quality Calculation
Category Code: O13 Training Schedule
Category Code: O20 Precommissioning Form and Checksheet
| PE | OL1-2O20-0001 | PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - PIPING - (from 51 to 99 ) |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-08-01; 2019-03-18: 2019-10-01
[6 empty] | Revised Plan | 2019-03-15: 2019-08-23; 2019-03-18: 2019-10-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O20-0002 | PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - INSTRUMENTATION - (from 51 to 99 ) |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-08-01; 2019-03-18: 2019-10-01
[6 empty] | Revised Plan | 2019-03-15: 2019-08-23; 2019-03-18: 2019-10-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O20-0003 | PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - ELECTRICAL - (from 51 to 99 ) |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-08-01; 2019-03-18: 2019-10-01
[6 empty] | Revised Plan | 2019-03-15: 2019-08-23; 2019-03-18: 2019-10-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O20-0004 | PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - MECHANICAL - (from 51 to 99 ) |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-08-01; 2019-03-18: 2019-10-01
[6 empty] | Revised Plan | 2019-03-15: 2019-08-23; 2019-03-18: 2019-10-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O21 Commissioning Form and Checksheet
Category Code: O22 Operation Form and Checksheet
Category Code: O23 Equipment Patrol Checksheet
Category Code: O51 Appraisal Report for Consultancy Service
Category Code: O52 Appraisal Report for EPC Contractor Work
Category Code: O53 Appraisal Report for Vendor/Supplier
Category Code: O60 Precommissioning Record and Report
Category Code: O61 Commissioning Record and Report
Category Code: O62 Startup, Shutdown and Emergency Shutdown Record and Report
Category Code: O63 Plant performance Test and record
Category Code: O64 Operation Record and Report Production Record,Report
Category Code: O65 Troubleshooting Record, Report
Category Code: O66 Modification Record,Report
Category Code: O67 List of set point and controller parameter
| PE | OL1-2O67-1001 | ALARM & SETPOINT SUMMARY |  | Class 3 | Purpose** | 2019-03-15: IFR; 2019-03-18: IBD; 2019-05-30: IFD; 2019-05-31: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-04-04; 2019-03-18: 2019-06-13; 2019-05-30: 2019-06-24; 2019-05-31: 2019-10-28
[6 empty] | Revised Plan | 2019-05-30: 2019-08-20; 2019-05-31: 2019-10-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2O67-1101 | Alarm & Setpoint Summary 36M Furnace 10-H-1100 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-10; 2019-03-18: 2019-06-11
[6 empty] | Issue Actual | 2019-03-15: 2019-06-10; 2019-03-18: 2019-06-11
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-IE-01848; 2019-03-18: TPSK-LSPA1-T-IE-01848
[6 empty] | Return Date | 2019-03-18: 2019-07-23
Owner Cmmt* | bar: 2019-03-18
| IE | OL1-2O67-1201 | Alarm & Setpoint Summary 132U Furnaces 10-H-1200 - 10-H-1600 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-10; 2019-03-18: 2019-06-11
[6 empty] | Issue Actual | 2019-03-15: 2019-06-10; 2019-03-18: 2019-06-11
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-IE-01848; 2019-03-18: TPSK-LSPA1-T-IE-01848
[6 empty] | Return Date | 2019-03-18: 2019-07-23
Owner Cmmt* | bar: 2019-03-18
| PE | OL1-2O67-2001 | ALARM & SETPOINT SUMMARY |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IBD; 2019-05-30: IFD; 2019-05-31: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-04-04; 2019-03-18: 2019-06-13; 2019-05-30: 2019-06-24; 2019-05-31: 2019-10-28
[6 empty] | Revised Plan | 2019-05-30: 2019-08-20; 2019-05-31: 2019-10-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O70 Precommissioning Procedure |  |  |  |  | Class 2 | Purpose**
Category Code: O71 Commissioning Procedure | [5 empty] | Rev.
| PE | OL1-2O71-0001 | JOB START UP SPECIFICATION FOR WATER FLUSHING OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev. | bar: 2019-03-15
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-18: 2020-06-15
[6 empty] | Issue Actual | 2019-03-15: 2019-08-15
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02426
Return Date
Owner Cmmt*
| PE | OL1-2O71-0002 | JOB START UP SPECIFICATION FOR AIR BLOWING OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev. | bar: 2019-03-15
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-18: 2020-06-15
[6 empty] | Issue Actual | 2019-03-15: 2019-08-15
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02426
Return Date
Owner Cmmt*
| PE | OL1-2O71-0003 | JOB START UP SPECIFICATION FOR DRYING OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev. | bar: 2019-03-15
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-18: 2020-06-15
[6 empty] | Issue Actual | 2019-03-15: 2019-08-15
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02426
Return Date
Owner Cmmt*
| PE | OL1-2O71-0004 | JOB START UP SPECIFICATION FOR GROSS LEAK TEST |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev. | bar: 2019-03-15
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-18: 2020-06-15
[6 empty] | Issue Actual | 2019-03-15: 2019-08-15
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02426
Return Date
Owner Cmmt*
| PE | OL1-2O71-0005 | JOB START UP SPECIFICATION FOR TIGHTNESS TEST |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0006 | JOB START UP SPECIFICATION FOR STEAM BLOWING OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0007 | JOB START UP SPECIFICATION FOR CHEMICAL CLEANING OF CS OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0008 | JOB START UP SPECIFICATION FOR CHEMICAL CLEANING OF SS OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0009 | JOB START UP SPECIFICATION FOR NITROGEN PURGING OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0010 | JOB START UP SPECIFICATION FOR HYDRO-JETTING OF PIPING & EQUIPMENT |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0011 | JOB START UP SPECIFICATION FOR OIL FLUSHING |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0012 | JOB START UP SPECIFICATION FOR MANUAL CLEANING FOR LARGE BORE PIPING PROCEDURE |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0013 | JOB START UP SPECIFICATION FOR PIPING INSPECTION |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0014 | JOB START UP SPECIFICATION FOR RELIEF VALVE MANAGEMENT |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev. | bar: 2019-03-15
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-18: 2020-06-15
[6 empty] | Issue Actual | 2019-03-15: 2019-08-15
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02426
Return Date
Owner Cmmt*
| PE | OL1-2O71-0015 | JOB START UP SPECIFICATION FOR SPRING HANGER SETTING |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0016 | JOB START UP SPECIFICATION FOR TIGHTNESS TEST WITH NITROGEN & HELIUM |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0017 | JOB START UP SPECIFICATION FOR LOOP CHECK MANAGEMENT |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev. | bar: 2019-03-15
[6 empty] | Issue Plan | 2019-03-15: 2019-09-15; 2019-03-18: 2019-10-01
[6 empty] | Revised Plan | 2019-03-18: 2020-06-01
[6 empty] | Issue Actual | 2019-03-15: 2019-08-15
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02426
Return Date
Owner Cmmt*
| PE | OL1-2O71-0018 | JOB START UP SPECIFICATION FOR LOOP FOLDER MANAGEMENT |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev. | bar: 2019-03-15
[6 empty] | Issue Plan | 2019-03-15: 2019-09-15; 2019-03-18: 2019-10-01
[6 empty] | Revised Plan | 2019-03-18: 2020-06-01
[6 empty] | Issue Actual | 2019-03-15: 2019-08-15
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02426
Return Date
Owner Cmmt*
| PE | OL1-2O71-0019 | JOB START UP SPECIFICATION FOR ELECTRICAL MOTOR SOLO RUN |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
[6 empty] | Revised Plan | 2019-03-15: 2020-05-01; 2019-03-18: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0020 | JOB START UP SPECIFICATION FOR ELECTRICAL SUBSTATION ENERGIZATION |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2020-01-15; 2019-03-18: 2020-02-01
[6 empty] | Revised Plan | 2019-03-15: 2020-01-15; 2019-03-18: 2020-02-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0021 | JOB START UP SPECIFICATION FOR PUMP ALIGNMENT |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-09-15; 2019-03-18: 2019-10-01
[6 empty] | Revised Plan | 2019-03-15: 2019-09-13; 2019-03-18: 2019-10-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0022 | JOB START UP SPECIFICATION FOR VESSELS/EQUIPMENT INSPECTION |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-09-15; 2019-03-18: 2019-10-01
[6 empty] | Revised Plan | 2019-03-15: 2019-09-13; 2019-03-18: 2019-10-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0023 | CUO 110 - JOB START UP SPECIF.FOR MTL PRESERVATION DURING CONSTRUCTION, PRECOMM., COMMISS. AND STARTUP |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IMP; 2019-05-31: IMP
[6 empty] | Rev. | 2019-03-15: A; 2019-03-18: A; 2019-05-30: 0; 2019-05-31: 0
[6 empty] | Issue Plan | 2019-03-15: 2019-03-31; 2019-05-30: 2019-05-31
Revised Plan
[6 empty] | Issue Actual | 2019-03-15: 2019-03-18; 2019-03-18: 2019-03-19; 2019-05-30: 2019-07-04; 2019-05-31: 2019-07-04
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-01090; 2019-03-18: TPSK-LSPA1-T-PE-01090; 2019-05-30: TPSK-LSPA1-T-PE-02067; 2019-05-31: TPSK-LSPA1-T-PE-02067
[6 empty] | Return Date | 2019-05-30: 2019-08-02
Owner Cmmt* | bar: 2019-05-30
| PE | OL1-2O71-1001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 1 | Purpose** | 2019-03-15: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-12-18
[6 empty] | Revised Plan | 2019-03-15: 2019-12-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-2001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 1 | Purpose** | 2019-03-15: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-12-18
[6 empty] | Revised Plan | 2019-03-15: 2019-12-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-3001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 1 | Purpose** | 2019-03-15: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-12-18
[6 empty] | Revised Plan | 2019-03-15: 2019-12-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-4001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 1 | Purpose** | 2019-03-15: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-12-18
[6 empty] | Revised Plan | 2019-03-15: 2019-12-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-5001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 1 | Purpose** | 2019-03-15: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-12-18
[6 empty] | Revised Plan | 2019-03-15: 2019-12-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-6001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 1 | Purpose** | 2019-03-15: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-12-18
[6 empty] | Revised Plan | 2019-03-15: 2019-12-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O72 Startup, Shutdown and Emergency Shutdown Procedure
Category Code: O73 Plant performance Test procedure
Category Code: O74 Tag-in Tag-out/Lock-out Tag-out Procedure
Category Code: O75 Operation Work instruction
| PE | OL1-2O75-0001 | OPERATIONAL TEST PROCEDURE (OTP) |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IMP
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-03-01; 2019-03-18: 2021-07-01
[6 empty] | Revised Plan | 2019-03-15: 2021-03-01; 2019-03-18: 2021-07-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-1001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 3 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-11-11; 2019-03-18: 2019-12-04
[6 empty] | Revised Plan | 2019-03-15: 2019-11-11; 2019-03-18: 2019-12-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-2001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 3 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-11-11; 2019-03-18: 2019-12-04
[6 empty] | Revised Plan | 2019-03-15: 2019-11-11; 2019-03-18: 2019-12-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-3001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 3 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-11-11; 2019-03-18: 2019-12-04
[6 empty] | Revised Plan | 2019-03-15: 2019-11-11; 2019-03-18: 2019-12-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-4001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 3 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-11-11; 2019-03-18: 2019-12-04
[6 empty] | Revised Plan | 2019-03-15: 2019-11-11; 2019-03-18: 2019-12-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-5001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 3 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-11-11; 2019-03-18: 2019-12-04
[6 empty] | Revised Plan | 2019-03-15: 2019-11-11; 2019-03-18: 2019-12-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-6001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 3 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-11-11; 2019-03-18: 2019-12-04
[6 empty] | Revised Plan | 2019-03-15: 2019-11-11; 2019-03-18: 2019-12-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O80 Lab, Product QA and QC
| PE | OL1-2O80-1003 | SAMPLING AND ANALYTICAL MANUAL |  | Class 1 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFD; 2019-05-30: IFF
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-07-19; 2019-03-18: 2019-08-16; 2019-05-30: 2020-05-30
[6 empty] | Revised Plan | 2019-03-18: 2019-08-16; 2019-05-30: 2020-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O80-1005 | Sampling and Analytical Manual |  | Class 2 | Purpose** | 2019-03-15: IFI
[6 empty] | Rev. | 2019-03-15: 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02325
Return Date
Owner Cmmt*
Category Code: O91 Index/List
Category Code: O92 Procedures & Standards
Category Code: O93 Policy , Guidelines & Memo
Category Code: O94 Forms & Templates
Category Code: O95 Progress/Status Reports
Category Code: P03 Piping datasheet
| MP | OL1-2P03-1101 | PIPING SPECIALTY ITEM - DATA SHEETS |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFF
Rev. | bar: 2019-03-15 to 2019-03-18
[6 empty] | Issue Plan | 2019-03-15: 2019-05-22; 2019-05-30: 2019-05-22
Revised Plan
[6 empty] | Issue Actual | 2019-03-15: 2019-05-16; 2019-03-18: 2019-05-17
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01683; 2019-03-18: TPSK-LSPA1-T-MP-01683
[6 empty] | Return Date | 2019-03-18: 2019-07-17
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-1102 | Piping Specialty Item Datasheet - T- Type Filter - Crossover Line - 10-SP-11002 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-17
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-17
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643; 2019-05-30: TPSK-LSPA1-T-MP-02162
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1103 | Piping Specialty Item Datasheet - Exhaust Head - 10-SP-11003 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-16; 2019-03-18: 2019-05-17; 2019-05-30: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-05-16; 2019-03-18: 2019-05-17; 2019-05-30: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01683; 2019-03-18: TPSK-LSPA1-T-MP-01683; 2019-05-30: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | 2019-03-15: 2019-06-13; 2019-03-18: 2019-06-13
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1104 | Piping Specialty Item Datasheet - Vent Silencer - PSV-1142 A-B Outlet - 10- SP-11004 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-17
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-17
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643; 2019-05-30: TPSK-LSPA1-T-MP-02162
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03; 2019-05-30: 2019-08-16
Owner Cmmt* | bar: 2019-03-15 to 2019-05-30
| MP | OL1-2P03-1105 | Piping Specialty Item Datasheet - T-Type Filter - Fuel Gas Line - 10 SP-11005 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643; 2019-05-30: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1107 | Piping Specialty Item Datasheet - Special Tee Fitting 30 inches - 10-SP-11007 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1108 | Piping Specialty Item Datasheet - Special Tee Fitting 20 inches - 10-SP-11008 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1109 | Piping Specialty Item Datasheet - Special Tee Fitting 16 inches - 10-SP-11009 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1110 | Piping Specialty Item Datasheet - Special Tee Fitting 12 inches - 10-SP-11010 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1111 | Piping Specialty Item Datasheet - Stop Check Valve - 10-SP-11011 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643; 2019-05-30: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| PE | OL1-2P03-1112 | Piping Specialty Item Datasheet - 10-SP-11012 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-04-23; 2019-03-18: 2019-04-24; 2019-05-30: 2019-07-17
[6 empty] | Issue Actual | 2019-03-15: 2019-04-23; 2019-03-18: 2019-04-24; 2019-05-30: 2019-07-17
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-01457; 2019-03-18: TPSK-LSPA1-T-PE-01457; 2019-05-30: TPSK-LSPA1-T-MP-02160
[6 empty] | Return Date | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1113 | Piping Specialty Item Datasheet - Vent Silencer - PSV-1144 Outlet - 10-SP-11013 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643; 2019-05-30: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1114 | Piping Specialty Item Datasheet - Vent Silencer - Start up - 10-SP-11014 |  | Class 2 | Purpose** | 2019-03-15: IFD; 2019-03-18: IFR; 2019-05-30: IFR
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-05-10; 2019-05-30: 2019-05-13
[6 empty] | Issue Actual | 2019-03-18: 2019-05-10; 2019-05-30: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02292; 2019-03-18: TPSK-LSPA1-T-MP-01643; 2019-05-30: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | 2019-03-18: 2019-06-03; 2019-05-30: 2019-06-03
Owner Cmmt* | bar: 2019-03-18 to 2019-05-30
| MP | OL1-2P03-1115 | Piping Specialty Item – Data Sheet Y-Type Filter – Purge SRY-11002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-1116 | Piping Specialty Item – Data Sheet Y-Type Filter – Purge Steam SRY-11003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| PE | OL1-2P03-1151 | Piping Specialty Item Datasheet - 10-BDV-11001 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-04-23; 2019-03-18: 2019-04-24; 2019-05-30: 2019-07-17
[6 empty] | Issue Actual | 2019-03-15: 2019-04-23; 2019-03-18: 2019-04-24; 2019-05-30: 2019-07-17
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-01457; 2019-03-18: TPSK-LSPA1-T-PE-01457; 2019-05-30: TPSK-LSPA1-T-MP-02160
[6 empty] | Return Date | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19; 2019-05-30: 2019-08-16
Owner Cmmt* | bar: 2019-03-15 to 2019-05-30
| MP | OL1-2P03-1152 | Piping Specialty Item Datasheet - Flexible Hose - 10-FLX-11001 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-16; 2019-03-18: 2019-05-17; 2019-05-30: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-05-16; 2019-03-18: 2019-05-17; 2019-05-30: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01683; 2019-03-18: TPSK-LSPA1-T-MP-01683; 2019-05-30: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | 2019-03-15: 2019-06-13; 2019-03-18: 2019-06-13
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1153 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-11001 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10; 2019-05-30: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10; 2019-05-30: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01829; 2019-03-18: TPSK-LSPA1-T-MP-01829; 2019-05-30: TPSK-LSPA1-T-MP-02324
[6 empty] | Return Date | 2019-03-18: 2019-07-08
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-1154 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-11002 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10; 2019-05-30: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10; 2019-05-30: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01829; 2019-03-18: TPSK-LSPA1-T-MP-01829; 2019-05-30: TPSK-LSPA1-T-MP-02324
[6 empty] | Return Date | 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-1201 | PIPING SPECIALTY ITEM - DATA SHEETS |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFF
Rev. | bar: 2019-03-15 to 2019-03-18
[6 empty] | Issue Plan | 2019-03-15: 2019-05-22; 2019-05-30: 2019-05-22
Revised Plan
[6 empty] | Issue Actual | 2019-03-15: 2019-05-16; 2019-03-18: 2019-05-17
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01683; 2019-03-18: TPSK-LSPA1-T-MP-01683
[6 empty] | Return Date | 2019-03-18: 2019-07-17
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-1202 | SP/RO DATASHEETS - MIXING T |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-17
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-17
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643; 2019-05-30: TPSK-LSPA1-T-MP-02162
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1203 | SP/RO DATASHEETS - ANGLE VALVES |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFF
Rev. | bar: 2019-03-15 to 2019-03-18
[6 empty] | Issue Plan | 2019-03-15: 2019-05-22; 2019-05-30: 2019-05-22
Revised Plan
[6 empty] | Issue Actual | 2019-03-15: 2019-05-16; 2019-03-18: 2019-05-17
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01683; 2019-03-18: TPSK-LSPA1-T-MP-01683
[6 empty] | Return Date | 2019-03-15: 2019-06-13; 2019-03-18: 2019-06-13
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1204 | SP/RO DATASHEETS - SAMPLE COOLER |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFF
Rev. | bar: 2019-03-15 to 2019-03-18
[6 empty] | Issue Plan | 2019-03-15: 2019-05-22; 2019-05-30: 2019-05-22
Revised Plan
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1205 | SP/RO DATASHEETS - ISOKINETIC NOZZLE |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFF
Rev. | bar: 2019-03-15 to 2019-03-18
[6 empty] | Issue Plan | 2019-03-15: 2019-05-22; 2019-05-30: 2019-05-22
Revised Plan
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1206 | SP/RO DATASHEETS - SILENCER |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFF
Rev. | bar: 2019-03-15 to 2019-03-18
[6 empty] | Issue Plan | 2019-03-15: 2019-05-22; 2019-05-30: 2019-05-22
Revised Plan
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1207 | Piping Specialty Item Datasheet - Special Tee Fitting 30 inches - 10-SP-12007-16007 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1208 | Piping Specialty Item Datasheet - Special Tee Fitting 20 inches - 10-SP-12008-16008 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1209 | Piping Specialty Item Datasheet - Special Tee Fitting 16 inches - 10-SP-12009-16009 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1211 | Piping Specialty Item Datasheet - Stop Check Valve - 10-SP-12011-16011 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643; 2019-05-30: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| PE | OL1-2P03-1212 | Piping Specialty Item Datasheet - 10-SP-12012-16012 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-04-23; 2019-03-18: 2019-04-24; 2019-05-30: 2019-07-17
[6 empty] | Issue Actual | 2019-03-15: 2019-04-23; 2019-03-18: 2019-04-24; 2019-05-30: 2019-07-17
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-01457; 2019-03-18: TPSK-LSPA1-T-PE-01457; 2019-05-30: TPSK-LSPA1-T-MP-02160
[6 empty] | Return Date | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19; 2019-05-30: 2019-08-16
Owner Cmmt* | bar: 2019-03-15 to 2019-05-30
| MP | OL1-2P03-1213 | Piping Specialty Item Datasheet - Vent Silencer - PSV-1244 Outlet - 10-SP-12013-16013 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643; 2019-05-30: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1214 | Piping Specialty Item Datasheet - Vent Silencer - Start up - 10-SP-12014-16014 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-05-10; 2019-03-18: 2019-05-13; 2019-05-30: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01643; 2019-03-18: TPSK-LSPA1-T-MP-01643; 2019-05-30: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | 2019-03-15: 2019-06-03; 2019-03-18: 2019-06-03
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1215 | Piping Specialty Item – Data Sheet Y-Type Filter – Purge Steam SRY-12002-16002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-1216 | Piping Specialty Item – Data Sheet Y-Type Filter – Purge Steam SRY-12003-16003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| PE | OL1-2P03-1251 | Piping Specialty Item Datasheet - 10-BDV-12001-16001 |  | Class 2 | Purpose** | 2019-03-15: IFD; 2019-03-18: IFR; 2019-05-30: IFR
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-04-23; 2019-05-30: 2019-04-24
[6 empty] | Issue Actual | 2019-03-18: 2019-04-23; 2019-05-30: 2019-04-24
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02160; 2019-03-18: TPSK-LSPA1-T-PE-01457; 2019-05-30: TPSK-LSPA1-T-PE-01457
[6 empty] | Return Date | 2019-03-15: 2019-08-16; 2019-03-18: 2019-06-19; 2019-05-30: 2019-06-19
Owner Cmmt* | bar: 2019-03-15 to 2019-05-30
| MP | OL1-2P03-1252 | Piping Specialty Item Datasheet - Flexible Hose - 10-FLX-12001-16001 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-05-16; 2019-03-18: 2019-05-17; 2019-05-30: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-05-16; 2019-03-18: 2019-05-17; 2019-05-30: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01683; 2019-03-18: TPSK-LSPA1-T-MP-01683; 2019-05-30: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | 2019-03-15: 2019-06-13; 2019-03-18: 2019-06-13
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-1253 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-12001 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFD
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10; 2019-05-30: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10; 2019-05-30: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01829; 2019-03-18: TPSK-LSPA1-T-MP-01829; 2019-05-30: TPSK-LSPA1-T-MP-02324
[6 empty] | Return Date | 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-1254 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-12002 |  | Class 2 | Purpose** | 2019-03-15: IFD; 2019-03-18: IFR; 2019-05-30: IFR
Rev. | bar: 2019-03-15 to 2019-05-30
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-06-07; 2019-05-30: 2019-06-10
[6 empty] | Issue Actual | 2019-03-18: 2019-06-07; 2019-05-30: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02324; 2019-03-18: TPSK-LSPA1-T-MP-01829; 2019-05-30: TPSK-LSPA1-T-MP-01829
[6 empty] | Return Date | 2019-05-30: 2019-07-15
Owner Cmmt* | bar: 2019-05-30
| MP | OL1-2P03-1903 | Piping Specialty Item – Data Sheet T-Type Filter – P-1910/P-1912 SRT-19001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-2001 | Piping Specialty Item - Datasheet - Basket-Type Filter - Quench Oil Pump Suction - 10-SP-20001 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-18; 2019-03-18: 2019-06-18
[6 empty] | Issue Actual | 2019-03-15: 2019-06-18; 2019-03-18: 2019-06-18
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01913; 2019-03-18: TPSK-LSPA1-T-MP-01913
Return Date
Owner Cmmt*
| MP | OL1-2P03-2003 | Piping Specialty Item - Datasheet - T-Type Filter - P-2026 A-B Suction - SRT-20001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-25
[6 empty] | Issue Actual | 2019-03-15: 2019-07-25
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02259
Return Date
Owner Cmmt*
| MP | OL1-2P03-2004 | Piping Specialty Item - Basket-Type Filter - Heavy Fuel Oil Pump Suction - 10-SP-20004 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-18; 2019-03-18: 2019-06-18
[6 empty] | Issue Actual | 2019-03-15: 2019-06-18; 2019-03-18: 2019-06-18
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01913; 2019-03-18: TPSK-LSPA1-T-MP-01913
Return Date
Owner Cmmt*
| MP | OL1-2P03-2005 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2030 A-B - ILK-20001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02347
Return Date
Owner Cmmt*
| MP | OL1-2P03-2007 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-2006 A-B-C Discharge - SCV-20001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-2008 | Piping Specialty Item - Datasheet - Steam Trap - E-2008 A-B Shell Side Outlet - STT-20001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-07
[6 empty] | Issue Actual | 2019-03-15: 2019-08-07
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02365
Return Date
Owner Cmmt*
| MP | OL1-2P03-2101 | Piping Specialty Item - Datasheet - T-Type Filter - P-2126 A-B Suction - SRT-21001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-25
[6 empty] | Issue Actual | 2019-03-15: 2019-07-25
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02259
Return Date
Owner Cmmt*
| MP | OL1-2P03-2102 | Piping Specialty Item - Datasheet - T-Type Filter - P-2105 A-B Suction - SRT-21005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-25
[6 empty] | Issue Actual | 2019-03-15: 2019-07-25
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02259
Return Date
Owner Cmmt*
| MP | OL1-2P03-2103 | Piping Specialty Item - Datasheet - T-Type Filter - P-2106 A-B-C - SRT-21003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-25
[6 empty] | Issue Actual | 2019-03-15: 2019-07-25
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02259
Return Date
Owner Cmmt*
| MP | OL1-2P03-2104 | Piping Specialty Item - Datasheet - T-Type Filter - P-2146 A-B Suction - SRT-21002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-25
[6 empty] | Issue Actual | 2019-03-15: 2019-07-25
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02259
Return Date
Owner Cmmt*
| MP | OL1-2P03-2105 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2120 A-B - ILK-21001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02347
Return Date
Owner Cmmt*
| MP | OL1-2P03-2106 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2105 A-O - ILK-21002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02347
Return Date
Owner Cmmt*
| MP | OL1-2P03-2107 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - Quench Water Tower T-2100 Vacuum Protection - ILK-21003 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06; 2019-03-18: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06; 2019-03-18: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02347; 2019-03-18: TPSK-LSPA1-T-MP-02419
Return Date
Owner Cmmt*
| MP | OL1-2P03-2108 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Device - Process Water Stripper T-2140 Over-Pressure Protection - ILK-21004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-07
[6 empty] | Issue Actual | 2019-03-15: 2019-08-07
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02365
Return Date
Owner Cmmt*
| MP | OL1-2P03-2118 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Device - Furnace Continous Blowdown Overpressure Protection - ILK-10003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-07
[6 empty] | Issue Actual | 2019-03-15: 2019-08-07
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02365
Return Date
Owner Cmmt*
| MP | OL1-2P03-2122 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-2146 A-B Discharge - SCV-21001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02418
Return Date
Owner Cmmt*
| MP | OL1-2P03-2123 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-2106 A-B-C Discharge - SCV-21002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-2201 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2201 A-B-C - ILK-22001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-25
[6 empty] | Issue Actual | 2019-03-15: 2019-07-25
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02259
Return Date
Owner Cmmt*
| MP | OL1-2P03-2202 | Piping Specialty Item - Datasheet - T-Type Filter - P-2210 A-B Suction - 10-SP-22002 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-06; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-06; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01819; 2019-03-18: TPSK-LSPA1-T-MP-01819
[6 empty] | Return Date | 2019-03-18: 2019-07-08
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2203 | Piping Specialty Item - Datasheet - T-Type Filter - 1st Stage CG Compressor Suction - 10-SP-22003 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-06; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-06; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01819; 2019-03-18: TPSK-LSPA1-T-MP-01819
[6 empty] | Return Date | 2019-03-18: 2019-07-08
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2204 | Piping Specialty Item - Datasheet - T-Type Filter - 2nd Stage CG Compressor Suction - 10-SP-22004 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-06; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-06; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01819; 2019-03-18: TPSK-LSPA1-T-MP-01819
[6 empty] | Return Date | 2019-03-18: 2019-07-08
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2205 | Piping Specialty Item - Datasheet - T-Type Filter - P-2220 A-B Suction - 10-SP-22005 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-06; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-06; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01821; 2019-03-18: TPSK-LSPA1-T-MP-01821
[6 empty] | Return Date | 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2206 | Piping Specialty Item - Datasheet - T-Type Filter - 3rd Stage CG Compressor Suction - 10-SP-22006 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-06; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-06; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01819; 2019-03-18: TPSK-LSPA1-T-MP-01819
[6 empty] | Return Date | 2019-03-18: 2019-07-08
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2207 | Piping Specialty Item - Datasheet - T-Type Filter - 4th Stage CG Compressor Suction - 10-SP-22007 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-06; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-06; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01819; 2019-03-18: TPSK-LSPA1-T-MP-01819
[6 empty] | Return Date | 2019-03-18: 2019-07-08
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2208 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2200 4th Stage Discharge - 10-SP-22008 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-26; 2019-03-18: 2019-06-26
[6 empty] | Issue Actual | 2019-03-15: 2019-06-26; 2019-03-18: 2019-06-26
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01984; 2019-03-18: TPSK-LSPA1-T-MP-01984
[6 empty] | Return Date | 2019-03-15: 2019-07-31
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2209 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Looking Device - PSV-2235 A-B-C-D - IKL-22003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-24
[6 empty] | Issue Actual | 2019-03-15: 2019-07-24
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02250
Return Date
Owner Cmmt*
| MP | OL1-2P03-2211 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2200 4th Stage Suction - 10-SP-22011 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-26; 2019-03-18: 2019-06-26
[6 empty] | Issue Actual | 2019-03-15: 2019-06-26; 2019-03-18: 2019-06-26
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01984; 2019-03-18: TPSK-LSPA1-T-MP-01984
[6 empty] | Return Date | 2019-03-15: 2019-07-31
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2213 | Piping Specialty Item - Datasheet - Y-Type Filter - C-2200 Heavy Wash Oil - SRY-22002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-24
[6 empty] | Issue Actual | 2019-03-15: 2019-07-24
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02250
Return Date
Owner Cmmt*
| MP | OL1-2P03-2214 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2200 4th Stage Suction - 10-SP-22014 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-26; 2019-03-18: 2019-06-26
[6 empty] | Issue Actual | 2019-03-15: 2019-06-26; 2019-03-18: 2019-06-26
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01985; 2019-03-18: TPSK-LSPA1-T-MP-01985
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2215 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2266 A-B - ILK-22004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-24
[6 empty] | Issue Actual | 2019-03-15: 2019-07-24
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02252
Return Date
Owner Cmmt*
| MP | OL1-2P03-2301 | Piping Specialty Item - Datasheet - T-Type Filter - P-2306 A-B Suction - 10-SP-23001 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-12; 2019-03-18: 2019-06-14
[6 empty] | Issue Actual | 2019-03-15: 2019-06-12; 2019-03-18: 2019-06-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01884; 2019-03-18: TPSK-LSPA1-T-MP-01884
[6 empty] | Return Date | 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2302 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2322 A-B - ILK-23002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-25
[6 empty] | Issue Actual | 2019-03-15: 2019-07-25
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02259
Return Date
Owner Cmmt*
| MP | OL1-2P03-2303 | Piping Specialty Item - T-Type Filter - P-2304 Suction - 10-SP-23003 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-12; 2019-03-18: 2019-06-14
[6 empty] | Issue Actual | 2019-03-15: 2019-06-12; 2019-03-18: 2019-06-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01884; 2019-03-18: TPSK-LSPA1-T-MP-01884
[6 empty] | Return Date | 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2304 | Piping Specialty Item - Datasheet - T-Type Filter - P-2302 A-B Suction - 10-SP-23004 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-12; 2019-03-18: 2019-06-14
[6 empty] | Issue Actual | 2019-03-15: 2019-06-12; 2019-03-18: 2019-06-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01884; 2019-03-18: TPSK-LSPA1-T-MP-01884
[6 empty] | Return Date | 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2305 | SP Item Datasheet - Double-Keyed Interlocked Locking Device - PSV-2335 A-B - ILK-23003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02296
Return Date
Owner Cmmt*
| MP | OL1-2P03-2306 | Piping Specialty Item - Datasheet - T-Type Filter - P-2310 A-B Suction - 10-SP-23006 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-12; 2019-03-18: 2019-06-14
[6 empty] | Issue Actual | 2019-03-15: 2019-06-12; 2019-03-18: 2019-06-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01884; 2019-03-18: TPSK-LSPA1-T-MP-01884
[6 empty] | Return Date | 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2307 | SP Item Datasheet - Double-Keyed Interlocked Locking Device - PSV-2327 A-B - ILK-23004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02296
Return Date
Owner Cmmt*
| MP | OL1-2P03-2308 | SP Item Datasheet - Double-Keyed Interlocked Locking Device - PSV-2316 A-B - ILK-23001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02296
Return Date
Owner Cmmt*
| MP | OL1-2P03-2309 | Piping Specialty Item - Datasheet - T-Type Filter - P-2320 A-B Suction - 10-SP-23009 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-12; 2019-03-18: 2019-06-14
[6 empty] | Issue Actual | 2019-03-15: 2019-06-12; 2019-03-18: 2019-06-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01884; 2019-03-18: TPSK-LSPA1-T-MP-01884
[6 empty] | Return Date | 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2310 | Piping Specialty Item – Datasheet - Y-Type Filter - SRY-23001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-24
[6 empty] | Issue Actual | 2019-03-15: 2019-07-24
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02252
Return Date
Owner Cmmt*
| MP | OL1-2P03-2311 | SP Item Data Sheet - Desuperheater - SP-23011 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-24
[6 empty] | Issue Actual | 2019-03-15: 2019-07-24
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02253
Return Date
Owner Cmmt*
| MP | OL1-2P03-2312 | Piping Specialty Item - Datasheet - T-Type Filter - P-2300 A-B Suction - 10-SP-23012 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-12; 2019-03-18: 2019-06-14
[6 empty] | Issue Actual | 2019-03-15: 2019-06-12; 2019-03-18: 2019-06-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01884; 2019-03-18: TPSK-LSPA1-T-MP-01884
[6 empty] | Return Date | 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2323 | Piping Specialty Item - Datasheet - T-Type Filter - P-2300 A-B Suction - 10-SP-23023 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-12; 2019-03-18: 2019-06-14
[6 empty] | Issue Actual | 2019-03-15: 2019-06-12; 2019-03-18: 2019-06-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01884; 2019-03-18: TPSK-LSPA1-T-MP-01884
[6 empty] | Return Date | 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2325 | Piping Specialty Item - Datasheet - Sight Glass - SGT-23001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-24
[6 empty] | Issue Actual | 2019-03-15: 2019-07-24
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02254
Return Date
Owner Cmmt*
| MP | OL1-2P03-2326 | SP Item Datasheet - Double-Keyed Interlocked Locking Device - PSV-2332 A-B - ILK-23005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02296
Return Date
Owner Cmmt*
| MP | OL1-2P03-2403 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - D-2405 Overhead Cracked Gas - SVC-24012 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02059; 2019-03-18: TPSK-LSPA1-T-PE-02059
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2404 | Piping Specialty Item - Datasheet - T-Type Filter - P-2415 A-B Suction - 10-SP-24004 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01835; 2019-03-18: TPSK-LSPA1-T-MP-01835
[6 empty] | Return Date | 2019-03-18: 2019-07-08
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2405 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2414 A-B - ILK-24010 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-25
[6 empty] | Issue Actual | 2019-03-15: 2019-07-25
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02259
Return Date
Owner Cmmt*
| MP | OL1-2P03-2406 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2415 A-B - ILK-24007 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-25
[6 empty] | Issue Actual | 2019-03-15: 2019-07-25
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02259
Return Date
Owner Cmmt*
| MP | OL1-2P03-2407 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2418 A-B-C-D - ILK-24009 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-25
[6 empty] | Issue Actual | 2019-03-15: 2019-07-25
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02259
Return Date
Owner Cmmt*
| MP | OL1-2P03-2408 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2423 A-B-C - ILK-24004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-25
[6 empty] | Issue Actual | 2019-03-15: 2019-07-25
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02259
Return Date
Owner Cmmt*
| MP | OL1-2P03-2409 | Piping Specialty Item - Datasheet - Desuperheater - SP-24009 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-25
[6 empty] | Issue Actual | 2019-03-15: 2019-07-25
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02259
Return Date
Owner Cmmt*
| MP | OL1-2P03-2410 | Piping Specialty Item - Datasheet - T-Type Filter - P-2445 A-B Suction - 10-SP-24010 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01835; 2019-03-18: TPSK-LSPA1-T-MP-01835
[6 empty] | Return Date | 2019-03-18: 2019-07-08
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2411 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2428 A-B - ILK-24005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-25
[6 empty] | Issue Actual | 2019-03-15: 2019-07-25
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02259
Return Date
Owner Cmmt*
| MP | OL1-2P03-2412 | Piping Specialty Item - Datasheet - Desuperheater - SP-24012 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-25
[6 empty] | Issue Actual | 2019-03-15: 2019-07-25
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02259
Return Date
Owner Cmmt*
| MP | OL1-2P03-2413 | Piping Specialty Item - Datasheet - T-Type Filter - P-2455 A-B Suction - 10-SP-24013 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01835; 2019-03-18: TPSK-LSPA1-T-MP-01835
[6 empty] | Return Date | 2019-03-18: 2019-07-08
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2414 | Piping Specialty Item - Datasheet - T-Type Filter - P-2450 A-B Suction - 10-SP-24014 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01835; 2019-03-18: TPSK-LSPA1-T-MP-01835
[6 empty] | Return Date | 2019-03-18: 2019-07-08
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2415 | Piping Specialty Item - Datasheet - T-Type Filter - 5th Stage CG Compressor Suction - 10-SP-24015 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-07; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01835; 2019-03-18: TPSK-LSPA1-T-MP-01835
[6 empty] | Return Date | 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2416 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2435 A-B-C-D - ILK-24008 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-25
[6 empty] | Issue Actual | 2019-03-15: 2019-07-25
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02259
Return Date
Owner Cmmt*
| MP | OL1-2P03-2417 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2200 5th Stage Discharge - SCV-24006 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02059; 2019-03-18: TPSK-LSPA1-T-PE-02059
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2418 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - E-2460 -Shell Side- Outlet - SCV-24007 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02062; 2019-03-18: TPSK-LSPA1-T-PE-02062
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2421 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - D-2480 - ILK-24011 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02297
Return Date
Owner Cmmt*
| MP | OL1-2P03-2428 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - D-2440 Vapor Outlet - SCV-24010 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02062; 2019-03-18: TPSK-LSPA1-T-PE-02062
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2446 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - E-2460 -Shell Side- Outlet - SCV-24008 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02062; 2019-03-18: TPSK-LSPA1-T-PE-02062
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2451 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - D-2405 Overhead Cracked Gas - SCV-24013 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02062; 2019-03-18: TPSK-LSPA1-T-PE-02062
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2460 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - D-2440 Vapor Outlet - SCV-24009 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02062; 2019-03-18: TPSK-LSPA1-T-PE-02062
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2501 | Piping Specialty Item - Datasheet - Cone Filter - E-2506 Cracked Gas Inlet - 10-SP-25001 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2502 | Piping Specialty Item - Datasheet - Basket-Type Filter - D-2506 BTMS TO E-2506 - 10-SP-25002 |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IFR
Rev. | bar: 2019-03-15 to 2019-07-11
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-17; 2019-05-31: 2019-06-18; 2019-07-11: 2019-06-18
[6 empty] | Issue Actual | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-17; 2019-05-31: 2019-06-18; 2019-07-11: 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-01913 | TPSK-LSPA1-T-MP-01871 | TPSK-LSPA1-T-MP-01913 | TPSK-LSPA1-T-MP-01871 | TPSK-LSPA1-T-MP-01871
[6 empty] | Return Date | 2019-05-31: 2019-07-09; 2019-07-11: 2019-07-09
Owner Cmmt* | bar: 2019-05-31 to 2019-07-11
| MP | OL1-2P03-25024 | Piping Specialty Item - Datasheet - Cone Filter - E-2525 Hydrogen Inlet - 10-SP-25024 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2503 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2507 - 10-SP-25003 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-11; 2019-05-31: 2019-06-17
[6 empty] | Issue Actual | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-11; 2019-05-31: 2019-06-17
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01913; 2019-03-18: TPSK-LSPA1-T-MP-01871; 2019-05-30: TPSK-LSPA1-T-MP-01871; 2019-05-31: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2504 | Piping Specialty Item - Datasheet - Cone Filter - E-2508 Cracked Gas Inlet - 10-SP-25004 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2505 | Piping Specialty Item - Datasheet - Cone Filter - E-2508 Residue Gas Inlet - 10-SP-25005 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2506 | Piping Specialty Item - Datasheet - Cone Filter - E-2508 Hydrogen Inlet - 10-SP-25006 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-07-01
[6 empty] | Issue Actual | 2019-03-18: 2019-07-01
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2507 | Piping Specialty Item - Datasheet - Cone Filter - E-2508 Methane Recycle Inlet - 10-SP-25007 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2508 | Piping Specialty Item - Datasheet - Basket-Type Filter - D-2508 BTMS To E-2508 - 10-SP-25008 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-05-30: 2019-06-11; 2019-05-31: 2019-06-17
[6 empty] | Issue Actual | 2019-05-30: 2019-06-11; 2019-05-31: 2019-06-17
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01872; 2019-03-18: TPSK-LSPA1-T-MP-01913; 2019-05-30: TPSK-LSPA1-T-MP-01872; 2019-05-31: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2509 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2509 - 10-SP-25009 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-05-30: 2019-06-11; 2019-05-31: 2019-06-17
[6 empty] | Issue Actual | 2019-05-30: 2019-06-11; 2019-05-31: 2019-06-17
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01872; 2019-03-18: TPSK-LSPA1-T-MP-01913; 2019-05-30: TPSK-LSPA1-T-MP-01872; 2019-05-31: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2510 | Piping Specialty Item - Datasheet - Basket-Type Filter - Demeth BTMS To E-2510 - 10-SP-25010 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-05-30: 2019-06-11; 2019-05-31: 2019-06-17
[6 empty] | Issue Actual | 2019-05-30: 2019-06-11; 2019-05-31: 2019-06-17
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01872; 2019-03-18: TPSK-LSPA1-T-MP-01913; 2019-05-30: TPSK-LSPA1-T-MP-01872; 2019-05-31: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2511 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2521 - 10-SP-25011 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-05-30: 2019-06-11; 2019-05-31: 2019-06-17
[6 empty] | Issue Actual | 2019-05-30: 2019-06-11; 2019-05-31: 2019-06-17
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01872; 2019-03-18: TPSK-LSPA1-T-MP-01913; 2019-05-30: TPSK-LSPA1-T-MP-01872; 2019-05-31: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2512 | Piping Specialty Item - Datasheet - Basket-Type Filter - Methane Recycle To E-2520 - 10-SP-25012 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-05-30: 2019-06-11; 2019-05-31: 2019-06-17
[6 empty] | Issue Actual | 2019-05-30: 2019-06-11; 2019-05-31: 2019-06-17
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01872; 2019-03-18: TPSK-LSPA1-T-MP-01913; 2019-05-30: TPSK-LSPA1-T-MP-01872; 2019-05-31: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2513 | Piping Specialty Item - Datasheet - Cone Filter - E-2520 Residue Gas Inlet - 10-SP-25013 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2514 | Piping Specialty Item - Datasheet - Cone Filter - E-2520 Hydrogen Inlet - 10-SP-25014 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2515 | Piping Specialty Item - Datasheet - Cone Filter - E-2520 Cracked Gas inlet - 10-SP-25015 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2516 | Piping Specialty Item - Datasheet - Cone Filter - E-2520 Rectifier Ovhd Inlet - 10-SP-25016 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2517 | Piping Specialty Item - Datasheet - Cone Filter - E-2530 Demeth Prefrac Ovhd Inlet - 10-SP-25017 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2518 | Piping Specialty Item - Datasheet - Basket-Type Filter - T-2520 BTMS To E-2530 - 10-SP-25018 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-18; 2019-05-31: 2019-06-18
[6 empty] | Issue Actual | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-18; 2019-05-31: 2019-06-18
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01872; 2019-03-18: TPSK-LSPA1-T-MP-01872; 2019-05-30: TPSK-LSPA1-T-MP-01913; 2019-05-31: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2519 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2530 - 10-SP-25019 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Issue Actual | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01872; 2019-03-18: TPSK-LSPA1-T-MP-01872; 2019-05-30: TPSK-LSPA1-T-MP-01917; 2019-05-31: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2520 | Piping Specialty Item - Datasheet - Cone Filter - E-2540 Demeth Ovhd Inlet - 10-SP-25020 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2521 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To E-2540 - 10-SP-25021 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Issue Actual | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01872; 2019-03-18: TPSK-LSPA1-T-MP-01872; 2019-05-30: TPSK-LSPA1-T-MP-01917; 2019-05-31: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2522 | Piping Specialty Item - Datasheet - T-Type Filter - TX-2550 Residue Gas Expander Suction - 10-SP-25022 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Issue Actual | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01917; 2019-03-18: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2523 | Piping Specialty Item - Datasheet - T-Type Filter - C-2550 Residue Gas Recompressor Suction - 10-SP-25023 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Issue Actual | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01917; 2019-03-18: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2525 | Piping Specialty Item - Datasheet - Cone Filter - E-2525 Rectifier Relux Drum Ovhd Inlet - 10-SP-25025 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2526 | Piping Specialty Item - Datasheet - Basket-Type Filter - Residue Gas To E-2525 - 10-SP-25026 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Issue Actual | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01872; 2019-03-18: TPSK-LSPA1-T-MP-01872; 2019-05-30: TPSK-LSPA1-T-MP-01917; 2019-05-31: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2527 | Pipng Specialty Item - Datasheet - Cone Filter - E-2500 Residue Gas Inlet - 10-SO-25027 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2528 | Piping Specialty Item - Datasheet Cone Filter - E-2500 Ethane Recycle Inlet - 10-SP-25028 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2529 | Piping Specialty Item - Datasheet - Cone Filter - E-2500 Methane Recycle Inlet - 10-SP-25029 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2530 | Piping Specialty Item - Datasheet - Cone Filter - E-2500 Hydro gem Inlet - 10-SP-25030 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2531 | Piping Specialty Item - Datasheet - Basket-Type Filter - C3R To E-2500 - 10-SP-25031 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Issue Actual | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01872; 2019-03-18: TPSK-LSPA1-T-MP-01872; 2019-05-30: TPSK-LSPA1-T-MP-01917; 2019-05-31: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2532 | Piping Specialty Item - Datasheet - Basket-Type Filter - C3R To E-2500 - 10-SP-25032 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Issue Actual | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01872; 2019-03-18: TPSK-LSPA1-T-MP-01872; 2019-05-30: TPSK-LSPA1-T-MP-01917; 2019-05-31: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2533 | Piping Specialty Item - Datasheet - Cone Filter - E-2585 C2R Inlet - 10-SP-25033 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2534 | Piping Specialty Item - Datasheet - Basket-Type Filter - T-2580 Side Reboiler Inlet - 10-SP-25034 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Issue Actual | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01872; 2019-03-18: TPSK-LSPA1-T-MP-01872; 2019-05-30: TPSK-LSPA1-T-MP-01917; 2019-05-31: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2535 | Piping Specialty Item - Datasheet - Cone Filter - E-2587 C2R Inlet - 10-SP-25035 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02046; 2019-03-18: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2536 | Piping Specialty Item - Datasheet - T-Type Filter - P-2570 A-B Suction - 10-SP-25036 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Issue Actual | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01917; 2019-03-18: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2538 | Piping Specialty Item - Datasheet - T-Type Filter - P-2586 A-B Suction - 10-SP-25038 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Issue Actual | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01917; 2019-03-18: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2539 | Piping Specialty Item - Datasheet - Basket-Type Filter - T-2580 Bottoms Reboiler Inlet - 10-SP-25039 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Issue Actual | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01872; 2019-03-18: TPSK-LSPA1-T-MP-01872; 2019-05-30: TPSK-LSPA1-T-MP-01917; 2019-05-31: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2540 | Piping Specialty Item - Datasheet - Cone Filter - E-2510 Demeth Prefrac Ovhd Inlet - 10-SP-25040 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-15: 2019-07-02; 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02045; 2019-03-18: TPSK-LSPA1-T-MP-02045
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2544 | Piping Specialty Item - Datasheet - T-Type Filter - P-2575 A-b Suction - 10-SP-25044 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Issue Actual | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01917; 2019-03-18: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2546 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2530 A-B - ILK-25010 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02347
Return Date
Owner Cmmt*
| MP | OL1-2P03-2547 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2550 Discharge - 10-SP-25047 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02418
Return Date
Owner Cmmt*
| MP | OL1-2P03-2548 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - TX-2550 Discharge - 10-SP-25048 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02418
Return Date
Owner Cmmt*
| MP | OL1-2P03-2549 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2510 A-B - ILK-25011 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02347
Return Date
Owner Cmmt*
| MP | OL1-2P03-2550 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2520 A-B - ILK-25001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02347
Return Date
Owner Cmmt*
| MP | OL1-2P03-2551 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2524 A-B - ILK-25002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2552 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2525 A-B - ILK-25013 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2553 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2539 A-B - ILK-25003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2554 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2540 A-B - ILK-25004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2555 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2544 A-B - ILK-25005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2556 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2550 A-B-C - ILK-25007 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2557 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2565 A-B-C - ILK-25008 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2558 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2548 A-B - ILK-25009 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2559 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2545 A-B - ILK-25012 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2560 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2514 A-B - ILK-25014 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02349
Return Date
Owner Cmmt*
| MP | OL1-2P03-2601 | Piping Specialty Item - Datasheet - T-Type Filter - 2-2620 A-B Suction - 10-SP-26001 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Issue Actual | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01917; 2019-03-18: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2602 | Piping Specialty Item - Datasheet - T-Type Filter - P-2630 A-B Suction - 10-SP-26002 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Issue Actual | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01917; 2019-03-18: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2603 | Piping Specialty Item - Datasheet - T-Type Filter - P-2666 A-B Suction - 10-SP-26003 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Issue Actual | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01917; 2019-03-18: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2605 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2639 A-B - ILK-26003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2606 | Piping Specialty Item - Datasheet - T-Type Filter - P-2660 A-B Suction - 10-SP-26006 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Issue Actual | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01917; 2019-03-18: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2607 | Piping Specialty Item - Datasheet - T-Type Filter - P-2646 A-B Suction - 10-SP-26007 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Issue Actual | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01917; 2019-03-18: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2608 | Piping Specialty Item - Datasheet - T-Type Filter - P-2647 Suction - 10-SP-26008 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Issue Actual | 2019-03-15: 2019-06-19; 2019-03-18: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01917; 2019-03-18: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2609 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2633 A-B - ILK-26004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2610 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2620 A-B - ILK-26005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2612 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2626 A-B - ILK-26006 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2617 | Piping Specialty Item - Datasheet - Y-Type Filter - R-2620 Hydrogen Inlet - SRY-26001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-07
[6 empty] | Issue Actual | 2019-03-15: 2019-08-07
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02365
Return Date
Owner Cmmt*
| MP | OL1-2P03-2621 | Piping Specialty Item - Datasheet - Flexible Hose - MP Nitrogen to C3 Hydrogenation Reactor R-2620 - FLX-26001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-07
[6 empty] | Issue Actual | 2019-03-15: 2019-08-07
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02365
Return Date
Owner Cmmt*
| MP | OL1-2P03-2702 | Piping Specialty Item - Datasheet - T-Type Filter - P-2705 A-B Suction - SRT-27001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02297
Return Date
Owner Cmmt*
| MP | OL1-2P03-2703 | Piping Specialty Item - Datasheet - T-Type Filter -P-2710 A-B Suction - SRT-27002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02297
Return Date
Owner Cmmt*
| MP | OL1-2P03-2705 | Piping Specialty Item - Datasheet - T-Type Filter - P-2720 A-B Suction - SRT-27003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02297
Return Date
Owner Cmmt*
| MP | OL1-2P03-2706 | Piping Specialty Item - Datasheet - T-Type Filter - P-2724 A-B Suction - SRT-27004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02297
Return Date
Owner Cmmt*
| MP | OL1-2P03-2707 | Piping Specialty Item - Datasheet - T-Type Filter - P-2726 A-B Suction - SRT-27005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02297
Return Date
Owner Cmmt*
| MP | OL1-2P03-2708 | Piping Specialty Item - Datasheet - T-Type Filter - P-2750 A-B Suction - SRT-27006 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02297
Return Date
Owner Cmmt*
| MP | OL1-2P03-2710 | SP Item Datasheet - Desuperheater - HP Steam to E-2715 A-B & E-2725 A-C - SP-27010 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02419
Return Date
Owner Cmmt*
| MP | OL1-2P03-2712 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2750 A-B - ILK-27001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2713 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2716 A-B - ILK-27002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2715 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2733 A-E - ILK-27003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2716 | Piping Specialty Item - Datasheet - T-Type Filter - P-2721 A-B Suction - SRT-27001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02297
Return Date
Owner Cmmt*
| MP | OL1-2P03-2717 | Piping Specialty Item - Datasheet - Liquid Drain Trap - D-2735 Drain to OWD - STT-27001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02419
Return Date
Owner Cmmt*
| MP | OL1-2P03-2718 | Piping Specialty Item - Datasheet - Flexible Hose - MP Nitrogen to GHU-1 Reactor R-2700A - FLX-27001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-07
[6 empty] | Issue Actual | 2019-03-15: 2019-08-07
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02365
Return Date
Owner Cmmt*
| MP | OL1-2P03-2719 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2723 A-D - ILK-27004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2724 | Piping Specialty Item - Datasheet - Flexible Hose - MP Nitrogen to C4 C5 Hydrogenation Reactor R-2760 - FLX-27002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-07
[6 empty] | Issue Actual | 2019-03-15: 2019-08-07
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02365
Return Date
Owner Cmmt*
| MP | OL1-2P03-2725 | Piping Specialty Item - Datasheet - T-Type Filter - P-2714 A-B Suction - SRT-27008 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02297
Return Date
Owner Cmmt*
| MP | OL1-2P03-2726 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2761 A-B - ILK-27007 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2727 | Piping Specialty Item - Datasheet - T-Type Filter - P-2760 A-B Suction - 10-SRT-27009 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-31
[6 empty] | Issue Actual | 2019-03-15: 2019-07-31
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02297
Return Date
Owner Cmmt*
| MP | OL1-2P03-2728 | Piping Specialty Item - Datasheet - Y-Type Filter - R-2760 Hydrogen Inlet - SRY-27001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-07
[6 empty] | Issue Actual | 2019-03-15: 2019-08-07
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02365
Return Date
Owner Cmmt*
| MP | OL1-2P03-2729 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2771 A-B - ILK-27008 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2736 | Piping Specialty Item - Datasheet - Flexible Hose - MP Nitrogen to GHU-1 Reactor R-2700B - FLX-27003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-07
[6 empty] | Issue Actual | 2019-03-15: 2019-08-07
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02365
Return Date
Owner Cmmt*
| MP | OL1-2P03-2801 | Piping Specialty Item - Datasheet - T-Type Filter - C-2800 3rd Stage Propylene Refrig. Compressor Suction - 10-SP-28000 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01928
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2802 | Piping Specialty Item - Database - T-Type Filter - C-2800 2nd Stage Propylene Refrig. Compressor Suction - 10-SP-28001 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01928; 2019-03-18: TPSK-LSPA1-T-MP-01928
[6 empty] | Return Date | 2019-03-15: 2019-07-09; 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2803 | Piping Specialty Item - Datasheet - T-Type Filter - C-2800 - 1st Stage Propylene Refrig. Compressor Suction - 10-SP-28002 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01928; 2019-03-18: TPSK-LSPA1-T-MP-01928
[6 empty] | Return Date | 2019-03-15: 2019-07-09; 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2804 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 3rd Stage Suction - 10-SP-28101 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01928; 2019-03-18: TPSK-LSPA1-T-MP-01928
[6 empty] | Return Date | 2019-03-15: 2019-07-09; 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2805 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 2nd Stage Suction - 10-SP-28102 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01928; 2019-03-18: TPSK-LSPA1-T-MP-01928
[6 empty] | Return Date | 2019-03-15: 2019-07-09; 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2806 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 1st Stage Suction - 10-SP-28103 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01931; 2019-03-18: TPSK-LSPA1-T-MP-01931
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2807 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 5th Stage Discharge - 10-SP-28104 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01933; 2019-03-18: TPSK-LSPA1-T-MP-01933
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2808 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 4th Stage Suction - 10-SP-28105 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01933; 2019-03-18: TPSK-LSPA1-T-MP-01933
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2809 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 4th Stage Discharge - 10-SP-28108 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01934; 2019-03-18: TPSK-LSPA1-T-MP-01934
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2810 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 4th Stage Discharge - 10-SP-28109 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01935; 2019-03-18: TPSK-LSPA1-T-MP-01935
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2811 | Piping Specialty Item - Datasheet - T-Type Filter - C-2800 th Stage Propylene Refrig. Compressor Suction - 10-SP-28003 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01936; 2019-03-18: TPSK-LSPA1-T-MP-01936
[6 empty] | Return Date | 2019-03-15: 2019-07-09; 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2812 | Piping Specialty Item - Datasheet - Non-Slam Check valve - C-2800 5th Stage Discharge - 10-SP-28106 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01937; 2019-03-18: TPSK-LSPA1-T-MP-01937
[6 empty] | Return Date | 2019-03-15: 2019-07-09; 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2813 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 5th Stage Discharge - 10-SP-28011 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01937; 2019-03-18: TPSK-LSPA1-T-MP-01937
[6 empty] | Return Date | 2019-03-15: 2019-07-09; 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2820 | Piping Specialty Item - Datasheet - T-Type Filter - P-2815 Suction - 10-SP-28009 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01936; 2019-03-18: TPSK-LSPA1-T-MP-01936
[6 empty] | Return Date | 2019-03-15: 2019-07-09; 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2821 | Piping Specialty Item - Datasheet - T-Type Filter - P-2805 A-B Suction - 10-SP-28010 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01936; 2019-03-18: TPSK-LSPA1-T-MP-01936
[6 empty] | Return Date | 2019-03-15: 2019-07-09; 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2822 | Piping Specialty Item - Datasheet - T-Type Filter - C-2850 3rd Stage Ethylene Refrig. Compressor Suction - 10-SP-28504 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01936; 2019-03-18: TPSK-LSPA1-T-MP-01936
[6 empty] | Return Date | 2019-03-15: 2019-07-09; 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2823 | Piping Specialty Item - Datasheet - T-Type Filter - C-2850 2nd Stage Ethylene Refrig. Compressor Suction - 10-SP-28505 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-06-19
[6 empty] | Issue Actual | 2019-03-18: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01936; 2019-03-18: TPSK-LSPA1-T-MP-01936
[6 empty] | Return Date | 2019-03-15: 2019-07-09; 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2824 | Piping Specialty Item - Datasheets - T-Type Filter - C-2850 1st Stage Ethylene Refrig. Compressor Suction - 10-SP-28506 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01936; 2019-03-18: TPSK-LSPA1-T-MP-01936
[6 empty] | Return Date | 2019-03-15: 2019-07-09; 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2825 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 3rd Stage Suction - 10-SP-28604 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01937; 2019-03-18: TPSK-LSPA1-T-MP-01937
[6 empty] | Return Date | 2019-03-15: 2019-07-09; 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2826 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 2nd Stage Suction - 10-SP-28605 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01937; 2019-03-18: TPSK-LSPA1-T-MP-01937
[6 empty] | Return Date | 2019-03-15: 2019-07-09; 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2827 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 1st Stage Suction - 10-SP-28606 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01937; 2019-03-18: TPSK-LSPA1-T-MP-01937
[6 empty] | Return Date | 2019-03-15: 2019-07-09; 2019-03-18: 2019-07-09
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2828 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 3rd Stage Discharge - 10-SP-28602 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20; 2019-05-30: 2019-06-20; 2019-05-31: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20; 2019-05-30: 2019-06-20; 2019-05-31: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01938; 2019-03-18: TPSK-LSPA1-T-MP-01938; 2019-05-30: TPSK-LSPA1-T-MP-01938; 2019-05-31: TPSK-LSPA1-T-MP-01938
[6 empty] | Return Date | 2019-03-15: 2019-07-16; 2019-03-18: 2019-07-16
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2829 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 4th Stage Discharge - 10-SP-28603 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01938; 2019-03-18: TPSK-LSPA1-T-MP-01938
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2830 | Piping Specialty Item - Datasheet -Non-Slam Check - C-2850 3 rd Stage Discharge - 10-SP-28607 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01938; 2019-03-18: TPSK-LSPA1-T-MP-01938
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2833 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C2R Desuperheater 2 Outlet - 10-SP-28609 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01939; 2019-03-18: TPSK-LSPA1-T-MP-01939
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2834 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C2R Desuperheater 2 Outlet - 10-SP-28608 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01939; 2019-03-18: TPSK-LSPA1-T-MP-01939
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2835 | Piping Specialty Item - Datasheet - T-Type Filter - P-2855 A-B Suction - 10-SP-28510 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01940; 2019-03-18: TPSK-LSPA1-T-MP-01940
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-2843 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2884 - 10-SP-28508 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Issue Actual | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01872; 2019-03-18: TPSK-LSPA1-T-MP-01872; 2019-05-30: TPSK-LSPA1-T-MP-01917; 2019-05-31: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2844 | Piping Specialty Item - Datasheet - Basket-Type Filter - LP Ethylene To D-2882 & E-2882 - 10-SP-28512 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR; 2019-05-30: IFR; 2019-05-31: IFR
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Issue Actual | 2019-03-18: 2019-06-11; 2019-05-30: 2019-06-19; 2019-05-31: 2019-06-19
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01872; 2019-03-18: TPSK-LSPA1-T-MP-01872; 2019-05-30: TPSK-LSPA1-T-MP-01917; 2019-05-31: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | 2019-03-15: 2019-07-09
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2855 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2805 A-E - ILK-28001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2856 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2806 A-D - ILK-28002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2857 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2820 A-B - ILK-28003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2858 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2823 A-B - ILK-28004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2859 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2826 A-B - ILK-28005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2860 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2829 A-B - ILK-28006 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2861 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2845 A-B - ILK-28013 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02348
Return Date
Owner Cmmt*
| MP | OL1-2P03-2862 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2867 A-B - ILK-28014 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02352
Return Date
Owner Cmmt*
| MP | OL1-2P03-2863 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2842 A-B - ILK-28007 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02352
Return Date
Owner Cmmt*
| MP | OL1-2P03-2864 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2841 A-D - ILK-28008 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02352
Return Date
Owner Cmmt*
| MP | OL1-2P03-2865 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2864 A-B - ILK-28009 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02352
Return Date
Owner Cmmt*
| MP | OL1-2P03-2866 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2858 A-B - ILK-28011 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02352
Return Date
Owner Cmmt*
| MP | OL1-2P03-2867 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2861 A-B - ILK-28010 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02352
Return Date
Owner Cmmt*
| MP | OL1-2P03-2868 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2854 A-B - ILK-28015 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02352
Return Date
Owner Cmmt*
| MP | OL1-2P03-2901 | Piping Specialty Item - Datasheet - T-Type Filter - P-2930 Suction - 10-SP-29001 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2902 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2925 - A-B - ILK-29001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02352
Return Date
Owner Cmmt*
| MP | OL1-2P03-2904 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2006A Suction - 10-SP-29004 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2905 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2106A Suction - 10-SP-29005 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2906 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2146A Suction - 10-SP-29006 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-18: 2019-07-02
[6 empty] | Issue Actual | 2019-03-18: 2019-07-02
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-15: 2019-08-05
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2907 | Piping Specialty Item - Datasheet - T-Type Filter - P-2202 A-B Suction - 10-SP-29007 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2910 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2951 A-G - ILK-29003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02352
Return Date
Owner Cmmt*
| MP | OL1-2P03-2911 | Piping Specialty Item - Datasheet - T-Type Filter - CT-2200 Suction - 10-SP-29011 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2912 | Piping Specialty Item - Datasheet - Vent Silencer - Start-Up - 10-SP-29012 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01809; 2019-03-18: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | 2019-03-18: 2019-07-08
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2915 | Piping Speacialty Item - Datasheet - Vent Silencer - Start-Up - 10-SP-29015 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01809; 2019-03-18: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | 2019-03-18: 2019-07-08
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2916 | Piping Specialty Item - Datasheet - T-Type Filter - CT-2850 Suction - 10-SP-29016 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2918 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2976 A-B-C - ILK-29002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-06
[6 empty] | Issue Actual | 2019-03-15: 2019-08-06
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02352
Return Date
Owner Cmmt*
| MP | OL1-2P03-2919 | Piping Specialty Item - Datasheet - T-Type Filter - P2862 A-B Suction - 10-SP-29019 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2920 | Piping Specialty Item - Datasheet - T-Type Filter - CT-2800 Suction - 10-SP-29020 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2921 | Piping Specialty Item - Datasheet - Vent Silencer - Start-Up - 10-SP-29021 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01809; 2019-03-18: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | 2019-03-18: 2019-07-08
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2922 | Piping Specialty Item - Datasheet - T-Type Filter - P-2802 A-B Suction - 10-SP-29022 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2924 | Piping Specialty Item - Datasheet - T-Type Filter - CT-2800 Suction - 10-SP-29024 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2926 | Piping Specialty Item - Datasheet - Vent Silencer - Start-Up - 10-SP-29026 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01809; 2019-03-18: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | 2019-03-18: 2019-07-08
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2927 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2201A Suction - 10-SP-29027 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2928 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2801A Suction - 10-SP-29028 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02063; 2019-03-18: TPSK-LSPA1-T-MP-02063
[6 empty] | Return Date | 2019-03-15: 2019-07-24
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-2929 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2861A Suction - 10-SP-29029 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2931 | Piping Specialty Item - Datasheet - T-Type Filter - P-2910 1st STG Suction - 10-SP-29031 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2932 | Piping Specialty Item - Datasheet - T-Type Filter - P-2910 2nd STG Suction - 10-SP-29032 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2933 | Piping Specialty Item - Datasheet - T-Type Filter - P-2910 3rD STG Suction - 10-SP-29033 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2934 | Piping Specialty Item - Datasheet - T-Type Filter - P-2910 4th STG Suction - 10-SP-29034 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-2935 | Piping Specialty Item - Datasheet - T-Type Filter - P-2910 5th STG Suction - 10-SP-29035 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Issue Actual | 2019-03-15: 2019-07-03; 2019-03-18: 2019-07-03
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-PE-02058; 2019-03-18: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | 2019-03-18: 2019-08-05
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-3001 | Piping Specialty Item - Datasheet - T-Type Filter - P-3002 A-B Suction - 10-SP-30001 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02012; 2019-03-18: TPSK-LSPA1-T-MP-02012
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3002 | Piping Specialty Item - Datasheet - T-Type Filter - P-3000 A-B Suction - 10-SP-30002 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02009; 2019-03-18: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3003 | Piping Specialty Item - Datasheet - T-Type Filter - P-3016 A-B Suction - 10-SP-30003 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02009; 2019-03-18: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3004 | Piping Specialty Item - Datasheet - T-Type Filter - P-3026 A-B Suction - 10-SP-30004 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02009; 2019-03-18: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3005 | Piping Specialty Item - Datasheet - T-Type Filter - P-3020 A-B Suction - 10-SP-30005 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02012; 2019-03-18: TPSK-LSPA1-T-MP-02012
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3006 | Piping Specialty Item – Data Sheet Double-Keyed Interlocked Locking Device - PSV-3001 A/B ILK-30001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3007 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3005 A/B ILK-30002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3008 | Piping Specialty Item - Datasheet - T-Type Filter - P-3030 A-B Suction - 10-SP-30008 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02009; 2019-03-18: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3009 | Piping Specialty Item - Datasheet - T-Type Filter - P-3045 A-B Suction - 10-SP-30009 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02009; 2019-03-18: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3010 | Piping Specialty Item - Datasheet - T-Type Filter - P-3046 A-B Suction - 10-SP-30010 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02009; 2019-03-18: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3011 | Piping Specialty Item - Datasheet - T-Type Filter - P-3036 A-B Suction - 10-SP-30011 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02009; 2019-03-18: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3012 | Piping Specialty Item - Datasheet - T-Type Filter - P-3062 A-B Suction - 10-SP-30012 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02009; 2019-03-18: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3013 | Piping Specialty Item - Datasheet - T-Type Filter - P-3086 A-B Suction - 10-SP-30013 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02009; 2019-03-18: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3014 | Piping Specialty Item - Datasheet - T-Type Filter - P-3076 A-B Suction - 10-SP-30014 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02010; 2019-03-18: TPSK-LSPA1-T-MP-02010
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3015 | Piping Specialty Item - Datasheet - T-Type Filter - P-3056 A-B Suction - 10-SP-30015 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02010; 2019-03-18: TPSK-LSPA1-T-MP-02010
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3016 | Piping Specialty Item - Datasheet - T-Type Filter - P-3060 A-B Suction - 10-SP-30016 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02010; 2019-03-18: TPSK-LSPA1-T-MP-02010
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3017 | Piping Specialty Item - Datasheet - T-Type Filter - P-3061 A-B Suction - 10-SP-30017 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02010; 2019-03-18: TPSK-LSPA1-T-MP-02010
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3018 | Piping Specialty Item - Datasheet - T-Type Filter - P-3096 A-B Suction - 10-SP-30018 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02010; 2019-03-18: TPSK-LSPA1-T-MP-02010
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3019 | Piping Specialty Item - Datasheet - T-Type Filter - P-3080 A-B Suction - 10-SP-30019 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Issue Actual | 2019-03-15: 2019-06-27; 2019-03-18: 2019-06-27
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02010; 2019-03-18: TPSK-LSPA1-T-MP-02010
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-3020 | Piping Specialty Item - Datasheet - Y-Type Filter - P-3016 A-B Discharge - SRY-30001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02415
Return Date
Owner Cmmt*
| MP | OL1-2P03-3024 | Piping Specialty Item - Datasheet - Y-Type Filter - E-3030 Product Inhibitor Inlet - SRY-30002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02415
Return Date
Owner Cmmt*
| MP | OL1-2P03-3025 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3026 A/B ILK-30005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3026 | Piping Specialty Item - Datasheet - Y-Type Filter - E-3080 Product Inhiditor Inlet - SRY-39005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02415
Return Date
Owner Cmmt*
| MP | OL1-2P03-3030 | Piping Specialty Item - Datasheet - Y-Type Filter - E-3055 A-B MP Condensate Outlet - SRY-30003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02415
Return Date
Owner Cmmt*
| MP | OL1-2P03-3031 | Piping Specialty Item - Datasheet - Steam Trap - E-3055 A-B MP Condensate Outlet - STT-30001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02419
Return Date
Owner Cmmt*
| MP | OL1-2P03-3036 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3028 A/B ILK-30006 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3037 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3033 A/B ILK-30007 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3038 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3039A/B ILK-30008 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3039 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3031A/B ILK-30009 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3040 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3042A/B ILK-30010 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3101 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3163A/B ILK-31001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3102 | Piping Specialty Item – T-Type Filter - P-3160A/B Suction SRT-31001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3103 | Piping Specialty Item – T-Type Filter - P-3110A/B Suction SRT-31002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3104 | Piping Specialty Item – T-Type Filter - P-3126A/B Suction SRT-31003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3106 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3162A/B ILK-31002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3107 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3164A/B ILK-31003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3108 | Piping Specialty Item - Datasheet - Steam Trap - D-3190 Heating Coil Outlet - 10-STT-31001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02419
Return Date
Owner Cmmt*
| MP | OL1-2P03-3109 | Piping Specialty Item - Datasheet - Y-Type Filter - D-3190 LP Condensate Outlet - SRY-31002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02415
Return Date
Owner Cmmt*
| MP | OL1-2P03-3110 | Piping Specialty Item - Datasheet - Y-Type Filter - D-3190 LP Condensate Outlet - SRY-31001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02415
Return Date
Owner Cmmt*
| MP | OL1-2P03-3111 | Piping Specialty Item - Datasheet - Steam Trap - D-3180 Heating Coil Outlet - 10-STT-31004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02419
Return Date
Owner Cmmt*
| MP | OL1-2P03-3112 | Piping Specialty Item - Datasheet - Y-Type Filter - D-3100 Jacket LP Condensate Outlet - SRY-31003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02415
Return Date
Owner Cmmt*
| MP | OL1-2P03-3113 | Piping Specialty Item - Datasheet - Y-Type Filter - LP Condensate from D-3100 Jacket LP Steam Inlet Line - SRY-31004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02415
Return Date
Owner Cmmt*
| MP | OL1-2P03-3114 | Piping Specialty Item - Datasheet - Steam Trap - LP Condensate D-3100 Jacket - STT-31003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02419
Return Date
Owner Cmmt*
| MP | OL1-2P03-3115 | Piping Specialty Item - Datasheet - Steam Trap - LP Condensate from D-3100 Jacket LP Steam Inlet Line - STT-31002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02419
Return Date
Owner Cmmt*
| MP | OL1-2P03-3118 | SP Item Datasheet - BDU MP Steam Desuperheater - SP-31018 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02420
Return Date
Owner Cmmt*
| MP | OL1-2P03-3119 | SP Item Datasheet - BDU LP Steam Desuperheater - SP-31019 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02420
Return Date
Owner Cmmt*
| MP | OL1-2P03-3120 | Piping Specialty Item - Datasheet - Y-Type Filter - HP BFW to Desuperheaters - 10-SRY-31005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02415
Return Date
Owner Cmmt*
| MP | OL1-2P03-3121 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3165A/B ILK-31004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3122 | Piping Specialty Item - Datasheet - Y-Type Filter - E-3150 LP Condensate Outlet - SRY-31006 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02415
Return Date
Owner Cmmt*
| MP | OL1-2P03-3123 | Piping Specialty Item - Datasheet - Steam Trap - LP Condensate from E-3150 - 10-STT-31005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02419
Return Date
Owner Cmmt*
| MP | OL1-2P03-3125 | Piping Specialty Item - Datasheet - Y-Type Filter - PK-3120 MP Steam Inlet - SRY-31007 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02415
Return Date
Owner Cmmt*
| MP | OL1-2P03-3901 | Piping Specialty Item – T-Type Filter - P-3900 Suction SRT-39001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-3902 | Piping Specialty Item - Datasheet - Y-Type Filter - P-3902 A-B Suction - SRY-39001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02419
Return Date
Owner Cmmt*
| MP | OL1-2P03-3903 | Piping Specialty Item - Datasheet - Y-Type Filter - P-3906 A-B - Suction - SRY-39002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02419
Return Date
Owner Cmmt*
| MP | OL1-2P03-3904 | Piping Specialty Item - Datasheet - Y-Type Filter - P-3908 A-B Suction - SRY-39003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02419
Return Date
Owner Cmmt*
| MP | OL1-2P03-3905 | Piping Specialty Item - Datasheet - Y-Type Filter - P-3904 A-B Suction - SRY-39004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02419
Return Date
Owner Cmmt*
| MP | OL1-2P03-5001 | Piping Specialty Item - Datasheet - Safety Shower and Eye Station - Area 50 - SS-50001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5101 | Piping Specialty Item - Datasheet - T-Type Filter - HP BFW to SHP-HP Steam Letdown - SRT-51001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-5102 | Piping Specialty Item - Datasheet - T-Type Filter - HP BFW to HP-MP Steam Letdown - SRT-51002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-5103 | Piping Specialty Item - Datasheet - T-Type Filter - HP BFW to MP-LP LS1 Steam Letdown - SRT-51003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-5104 | Piping Specialty Item - Datasheet - T-Type Filter - VLP BFW to LP LS1 - VLP LS2 Steam Letdown - SRT-51021 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-5105 | SP Item Data Sheet - LP LS1 VLP LS2 Letdown Desuperheater - SP-51005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02317
Return Date
Owner Cmmt*
| MP | OL1-2P03-5106 | SP Item Data Sheet - MP - LP LS1 Letdown Desuperheater - SP-51006 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02317
Return Date
Owner Cmmt*
| MP | OL1-2P03-5107 | SP Item Data Sheet - HP - MP Letdown Desuperheater - SP-51007 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02317
Return Date
Owner Cmmt*
| MP | OL1-2P03-5108 | SP Item Data Sheet - SHP - HP Letdown Desuperheater - SP-51008 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02317
Return Date
Owner Cmmt*
| MP | OL1-2P03-5109 | SP Item Data Sheet - SHP - HP Letdown Desuperheater - SP-51009 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02317
Return Date
Owner Cmmt*
| MP | OL1-2P03-5112 | Piping Specialty Item - Datasheet - T-Type Filter - HP BFW to SHP-HP Steam Letdown - SRT-51004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-5113 | Piping Specialty Item - Datasheet - T-Type Filter - P-5100 A-B-C Suction - SRT-51018 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-5115 | Piping Specialty Item - Datasheet - T-Type Filter - P-5102 A-B Suction - SRT-51016 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-5116 | Piping Specialty Item - Datasheet - T-Type Filter - P-5112 A-B Suction - SRT-51023 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-5117 | Piping Specialty Item - Datasheet - T-Type Filter - P-5120 A-B Suction - SRT-51022 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-5118 | Piping Specialty Item - Datasheet - T-Type Filter - P-5110 A-B Suction - SRT-51027 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-5119 | Piping Specialty Item - Datasheet - Exhaust Head - 10-SP-51019 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01809; 2019-03-18: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | 2019-03-18: 2019-06-27
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-5120 | Piping Specialty Item - Datasheet - T-Type Filter - P-5140 A-B Suction - SRT-51015 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-5121 | Piping Specialty Item - Datasheet - Vent Silencer -PV-5143 Outlet - 10-SP-51021 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01809; 2019-03-18: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | 2019-03-18: 2019-06-27
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-5122 | Piping Specialty Item - Datasheet - Vent Silencer - PV-5147 Outlet - 10-SP-51022 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01809; 2019-03-18: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | 2019-03-18: 2019-07-01
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-5123 | Piping Specialty Item - Datasheet - Vent Silencer - PV-5155 Outlet - 10-SP-51023 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01809; 2019-03-18: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | 2019-03-18: 2019-07-01
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-5124 | Piping Specialty Item - Datasheet - Vent Silencer - PV-5158 Outlet - 10-SP-51024 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01809; 2019-03-18: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | 2019-03-18: 2019-07-01
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-5125 | Piping Specialty Item - Datasheet - Vent Silencer - PV-5161 Outlet - 10-SP-51025 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01809; 2019-03-18: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | 2019-03-18: 2019-07-01
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-5126 | Piping Specialty Item - Datasheet - Vent Silencer - PSV-5134 A-H- Outlet - 10-SP-51026 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01941; 2019-03-18: TPSK-LSPA1-T-MP-01941
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-5128 | Piping Specialty Item - Datasheet – Double-Keyed Interlocked Locking Device - PSV-5143 A-H - ILK-51001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5129 | Piping Specialty Item - Datasheet – Double-Keyed Interlocked Locking Device - PSV-5150 A-D - ILK-51004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5130 | Piping Specialty Item - Datasheet - Vent Silencer - PSV-5150 A-B-C-D Outlet - 10-SP-51030 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Issue Actual | 2019-03-15: 2019-06-20; 2019-03-18: 2019-06-20
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01941; 2019-03-18: TPSK-LSPA1-T-MP-01941
[6 empty] | Return Date | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18
| MP | OL1-2P03-5134 | Piping Specialty Item - Datasheet – Double-Keyed Interlocked Locking Device - PSV-5153 A-D - ILK-51002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5141 | Piping Specialty Item - Datasheet - Exhaust Head - 10-SP-51041 |  | Class 2 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFR
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-05; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01809; 2019-03-18: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | 2019-03-18: 2019-07-01
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P03-5143 | Piping Specialty Item - Datasheet – Double-Keyed Interlocked Locking Device - PSV-5140 A-B - ILK-51005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5144 | Piping Specialty Item - Datasheet - Injection Quill - Amine Injection to BFW Pump Suction - IJQ-51001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5145 | Piping Specialty Item - Datasheet - Injection Quill - Phosphate Injection to SHP BFW - IJQ-51002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5146 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-5102 A-B Discharge - SCV-51004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-5147 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-5100 A-B-C Discharge - SCV-51001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-5148 | Piping Specialty Item - Datasheet - Multistage Restriction Orifice - SHP BFW Pump Warmup - ORI-51003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5201 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5204 A-B-C-D - ILK-52001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5202 | Piping Specialty Item - Datasheet - Steam Trap - E-5210 Shell Side Outlet - STT-52002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5203 | Piping Specialty Item - Datasheet - Steam Trap - E-5200 Shell Side Outlet - STT-52001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5206 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5209 A-B - ILK-52002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5303 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-5350 A-H Discharge - SCV-53004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-5304 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-5360 A-B-C Discharge - SCV-53001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02319
Return Date
Owner Cmmt*
| MP | OL1-2P03-5401 | Piping Specialty Item - Datasheet - Liquid Drain Trap - D-5400 Drain to OWD - STT-54001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02421
Return Date
Owner Cmmt*
| MP | OL1-2P03-5446 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5404 A-B - ILK-54001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5501 | Piping Specialty Item - Datasheet - T-Type Filter - p-5500 A-B Suction - SRT-55003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5508 | Piping Specialty Item - Datasheet - Steam Trap - E-5513 Tube Side Outlet - STT-55001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5510 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5510 A-B - ILK-55003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5512 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5531 A-B - ILK-55002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5514 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5532 A-B - ILK-55001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5521 | Piping Specialty Item - Datasheet - T-Type Filter - P-5550 A-B Suction - SRT-55001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5522 | Piping Specialty Item - Datasheet - T-Type Filter - p-5565 A-B Suction - SRT-55002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5523 | Piping Specialty Item - Datasheet - Steam Trap - D-5565 Coil Outlet - STT-55004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5524 | Piping Specialty Item - Datasheet - Liquid Drain Trap - Vent Gas Header in WWT Unit - STT-55005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-14
[6 empty] | Issue Actual | 2019-03-15: 2019-08-14
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02421
Return Date
Owner Cmmt*
| MP | OL1-2P03-5566 | Piping Specialty Item - Datasheet - Steam Trap - E-5552 Shell Side Outlet - STT-55002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5601 | Piping Specialty Item - Datasheet - T-Type Filter - P-5620 A-C Suction - SRT-56005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5602 | Piping Specialty Item - Datasheet - T-Type Filter - P-5621 Suction - SRT-56002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5603 | Piping Specialty Item - Datasheet - T-Type Filter - P-5655 A-C Suction - SRT-56006 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5604 | Piping Specialty Item - Datasheet - T-Type Filter - P-5640 A-B Suction - SRT-56007 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5605 | Piping Specialty Item - Datasheet - T-Type Filter - P-5641 Suction - SRT-56003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5606 | Piping Specialty Item - Datasheet - T-Type Filter - P-5675 Suction - SRT-56004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5607 | Piping Specialty Item - Datasheet - T-Type Filter - P-5676 Suction - SRT-56001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5608 | Piping Specialty Item - Datasheet - Carbon Canister - PIT-5632 Vent SP-56008 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-15
[6 empty] | Issue Actual | 2019-03-15: 2019-08-15
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02438
Return Date
Owner Cmmt*
| MP | OL1-2P03-5609 | Piping Specialty Item - Datasheet - Steam Trap - TK-5675A Coil Outlet - STT-56001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5610 | Piping Specialty Item - Datasheet - Steam Trap - TK-5675B Coil Outlet - STT-56002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5611 | Piping Specialty Item - Datasheet - Steam Trap - TK-5676 Coil Outlet - STT-56003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5613 | Piping Specialty Item - Datasheet - T-Type Filter - P-5656 A-B Suction - SRT-56008 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5614 | Piping Specialty Item - Datasheet - T-Type Filter - P-5653 A-B Suction - SRT-56009 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5615 | Piping Specialty Item - Datasheet - Sight Glass -P-5621 Discharge STG-56001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-15
[6 empty] | Issue Actual | 2019-03-15: 2019-08-15
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02438
Return Date
Owner Cmmt*
| MP | OL1-2P03-5901 | Piping Specialty Item - Datasheet - Carbon Canister - TK-5900 Sulfuric Acid Tank Vent SP-59001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-15
[6 empty] | Issue Actual | 2019-03-15: 2019-08-15
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02438
Return Date
Owner Cmmt*
| MP | OL1-2P03-5902 | Piping Specialty Item - Datasheet - T-Type Filter - P-5900 A-B Suction - SRT-59004 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5903 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5950 A-B Suction - SRT-59001 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5904 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5901 A-B Suction - SRT-59003 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5905 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5110 A Inlet - SRT-51012 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5906 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5350 A-B-C Inlet - SRT- 51010 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5909 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5360 A Inlet - SRT-51011 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5910 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5100 A-B Inlet - SRT-59002 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5912 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5101 A Inlet - SRT-51029 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5913 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5103 A- Inlet - SRT-51030 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-09
[6 empty] | Issue Actual | 2019-03-15: 2019-08-09
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02398
Return Date
Owner Cmmt*
| MP | OL1-2P03-5914 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5102 A Inlet - SRT-51026 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5915 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5105 A Inlet - SRT-51031 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5917 | Piping Specialty Item - Datasheet - T-Type Filter - P-5905 A-B Suction - SRT-59005 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-5918 | Piping Specialty Item - Datasheet - T-Type Filter - P-5955 A-B Suction - SRT-59006 |  | Class 2 | Purpose** | 2019-03-15: IFR
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-23
[6 empty] | Issue Actual | 2019-03-15: 2019-07-23
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | 2019-03-15: 2019-08-15
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P03-XXXA | AREA 30 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFD
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-04-18; 2019-03-18: 2019-05-16
[6 empty] | Revised Plan | 2019-03-18: 2019-09-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-XXXB | AREA 53 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFD
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-04-18; 2019-03-18: 2019-05-16
[6 empty] | Revised Plan | 2019-03-15: 2019-08-23; 2019-03-18: 2019-09-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-XXXC | AREA 55 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFD
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-04-18; 2019-03-18: 2019-05-16
[6 empty] | Revised Plan | 2019-03-15: 2019-08-23; 2019-03-18: 2019-09-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-XXXD | AREA 56 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFD
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-04-18; 2019-03-18: 2019-05-16
[6 empty] | Revised Plan | 2019-03-15: 2019-08-23; 2019-03-18: 2019-09-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-XXXX | SP ITEM DATA SHEETS, OLEFINS UNIT |  | Class 1 | Purpose** | 2019-03-15: IFR; 2019-03-18: IFD
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-04-18; 2019-03-18: 2019-05-16
[6 empty] | Revised Plan | 2019-03-15: 2019-08-23; 2019-03-18: 2019-09-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P04 Piping design basic / philosophy / logic diagram
Category Code: P05 Piping calculation sheet / report
| MP | OL1-2P05-0002 | CRITICAL LINE LIST - COOLING WATER UNIT |  | Class 3 | Purpose** | 2019-03-15: IDD; 2019-03-18: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-09-30; 2019-03-18: 2020-04-10
[6 empty] | Revised Plan | 2019-03-15: 2019-09-30; 2019-03-18: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0003 | CRITICAL LINE LIST - MAIN PIPE RACK |  | Class 3 | Purpose** | 2019-03-15: IDD; 2019-03-18: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-09-30; 2019-03-18: 2020-04-10
[6 empty] | Revised Plan | 2019-03-15: 2019-09-30; 2019-03-18: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0004 | CRITICAL LINE LIST - OFF-SITES |  | Class 3 | Purpose** | 2019-03-15: IDD; 2019-03-18: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-09-30; 2019-03-18: 2020-04-10
[6 empty] | Revised Plan | 2019-03-15: 2019-09-30; 2019-03-18: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0005 | CRITICAL LINE LIST - WASTE WATER TREATMENT |  | Class 3 | Purpose** | 2019-03-15: IDD; 2019-03-18: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-09-30; 2019-03-18: 2020-04-10
[6 empty] | Revised Plan | 2019-03-15: 2019-09-30; 2019-03-18: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0006 | CRITICAL LINE LIST - FURNACES UTILITIES |  | Class 3 | Purpose** | 2019-03-15: IDD; 2019-03-18: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-09-30; 2019-03-18: 2020-04-10
[6 empty] | Revised Plan | 2019-03-15: 2019-09-30; 2019-03-18: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0007 | CRITICAL LINE LIST - FRACTIONATION 1 & 2 |  | Class 3 | Purpose** | 2019-03-15: IDD; 2019-03-18: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-09-30; 2019-03-18: 2020-04-10
[6 empty] | Revised Plan | 2019-03-15: 2019-09-30; 2019-03-18: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0008 | CRITICAL LINE LIST - FRACTIONATION 3 & BUTADIENE EXTRACTION |  | Class 3 | Purpose** | 2019-03-15: IDD; 2019-03-18: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-09-30; 2019-03-18: 2020-04-10
[6 empty] | Revised Plan | 2019-03-15: 2019-09-30; 2019-03-18: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0041 | Loads On Rack 10-PRK-0P01 |  | Class 2 | Purpose** | 2019-03-15: IBD; 2019-03-18: IBD; 2019-05-30: IDD; 2019-05-31: IDD
Rev. | bar: 2019-03-15 to 2019-05-31
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-04-02; 2019-03-18: 2019-04-03; 2019-05-30: 2019-07-10; 2019-05-31: 2019-07-10
[6 empty] | Issue Actual | 2019-03-15: 2019-04-02; 2019-03-18: 2019-04-03; 2019-05-30: 2019-07-10; 2019-05-31: 2019-07-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01228; 2019-03-18: TPSK-LSPA1-T-MP-01228; 2019-05-30: TPSK-LSPA1-T-MP-02108; 2019-05-31: TPSK-LSPA1-T-MP-02108
[6 empty] | Return Date | 2019-03-15: 2019-04-26; 2019-03-18: 2019-04-26; 2019-05-31: 2019-07-19
Owner Cmmt* | bar: 2019-03-15 to 2019-03-18; 2019-05-31
| MP | OL1-2P05-0042 | Loads On Rack 10-PRK-0P02 |  | Class 2 | Purpose** | 2019-03-15: IBD; 2019-03-18: IBD
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-04-23; 2019-03-18: 2019-04-24
[6 empty] | Issue Actual | 2019-03-15: 2019-04-23; 2019-03-18: 2019-04-24
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01439; 2019-03-18: TPSK-LSPA1-T-MP-01439
[6 empty] | Return Date | 2019-03-18: 2019-06-14
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P05-0043 | Loads On Rack 10-PRK-0P03 |  | Class 2 | Purpose** | 2019-03-15: IBD; 2019-03-18: IBD
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-04-23; 2019-03-18: 2019-04-24
[6 empty] | Issue Actual | 2019-03-15: 2019-04-23; 2019-03-18: 2019-04-24
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01439; 2019-03-18: TPSK-LSPA1-T-MP-01439
[6 empty] | Return Date | 2019-03-18: 2019-06-14
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P05-0073 | Loads On Structure 10-STR-2A02 |  | Class 2 | Purpose** | 2019-03-15: IBD
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02322
[6 empty] | Return Date | 2019-03-15: 2019-08-13
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P05-0112 | Loads On structures 10-STR-2C01-2C |  | Class 2 | Purpose** | 2019-03-15: IDB
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02322
[6 empty] | Return Date | 2019-03-15: 2019-08-13
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P05-0113 | Loads On Structures 10-STR-2C03-2C |  | Class 2 | Purpose** | 2019-03-15: IBD
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02322
[6 empty] | Return Date | 2019-03-15: 2019-08-13
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P05-0131 | Loads On Rack 10-PRK-2D01 |  | Class 2 | Purpose** | 2019-03-15: IBD
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02322
[6 empty] | Return Date | 2019-03-15: 2019-08-13
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P05-0153 | Loads On Structures 10-STR-2E01-2E |  | Class 2 | Purpose** | 2019-03-15: IBD
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-05
[6 empty] | Issue Actual | 2019-03-15: 2019-08-05
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02322
[6 empty] | Return Date | 2019-03-15: 2019-08-13
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P05-0191 | Loads On Rack 10-PRK-5F01 |  | Class 2 | Purpose** | 2019-03-15: IBD; 2019-03-18: IBD
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
[6 empty] | Issue Actual | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02142; 2019-03-18: TPSK-LSPA1-T-MP-02142
[6 empty] | Return Date | 2019-03-18: 2019-07-30
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P05-0192 | Loads On Sleeper Way 10-SLW-5F01 |  | Class 2 | Purpose** | 2019-03-15: IBD; 2019-03-18: IBD
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-10; 2019-03-18: 2019-07-10
[6 empty] | Issue Actual | 2019-03-15: 2019-07-10; 2019-03-18: 2019-07-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02103; 2019-03-18: TPSK-LSPA1-T-MP-02103
Return Date
Owner Cmmt*
| MP | OL1-2P05-0211 | Loads on Rack 10-PRK-5T01 |  | Class 2 | Purpose** | 2019-03-15: IBD
Rev. | bar: 2019-03-15
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-08-07
[6 empty] | Issue Actual | 2019-03-15: 2019-08-07
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02357
Return Date
Owner Cmmt*
| MP | OL1-2P05-0212 | Loads on Sleeper Way 10-SLW-5T02 |  | Class 2 | Purpose** | 2019-03-15: IBD; 2019-03-18: IBD
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
[6 empty] | Issue Actual | 2019-03-15: 2019-07-15; 2019-03-18: 2019-07-15
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-02151; 2019-03-18: TPSK-LSPA1-T-MP-02151
Return Date
Owner Cmmt*
| MP | OL1-2P05-0231 | Loads On Rack 10-PRK-5U01 |  | Class 2 | Purpose** | 2019-03-15: IFD; 2019-03-18: IFD
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-10; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-10; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01839; 2019-03-18: TPSK-LSPA1-T-MP-01839
[6 empty] | Return Date | 2019-03-18: 2019-06-27
Owner Cmmt* | bar: 2019-03-18
| MP | OL1-2P05-0251 | Loads On Sleeper Way 10-SLW-5W01 |  | Class 2 | Purpose** | 2019-03-15: IFD; 2019-03-18: IFD
Rev. | bar: 2019-03-15 to 2019-03-18
Issue Plan
[6 empty] | Revised Plan | 2019-03-15: 2019-06-10; 2019-03-18: 2019-06-10
[6 empty] | Issue Actual | 2019-03-15: 2019-06-10; 2019-03-18: 2019-06-10
[6 empty] | Transmittal no. | 2019-03-15: TPSK-LSPA1-T-MP-01839; 2019-03-18: TPSK-LSPA1-T-MP-01839
[6 empty] | Return Date | 2019-03-15: 2019-06-27
Owner Cmmt* | bar: 2019-03-15
| MP | OL1-2P05-1101 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1102 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1103 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1104 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1105 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1106 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1107 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1108 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1109 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1110 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1111 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1112 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1113 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1114 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1115 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1116 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1117 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1118 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1119 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1120 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1121 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1122 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1123 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1124 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1201 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1202 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1203 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1204 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1205 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1206 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1207 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1208 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1209 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1210 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1211 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1212 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1213 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1214 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1215 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1216 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1217 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1218 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1219 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1220 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1221 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1222 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1223 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1224 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1301 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1302 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1303 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1304 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1305 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1306 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1307 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1308 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1309 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1310 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1311 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1312 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1313 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1314 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1315 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1316 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1317 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1318 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1319 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1320 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1321 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1322 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1323 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1324 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1401 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1402 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1403 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1404 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1405 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1406 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1407 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1408 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1409 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1410 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1411 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1412 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1413 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1414 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1415 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1416 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1417 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1418 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1419 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1420 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1421 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1422 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1423 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1424 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1501 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1502 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1503 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1504 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1505 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1506 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1507 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1508 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1509 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1510 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1511 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1512 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1513 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1514 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1515 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1516 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1517 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1518 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1519 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1520 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1521 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1522 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1523 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1524 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1601 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1602 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1603 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1604 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1605 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1606 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1607 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1608 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1609 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1610 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1611 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1612 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1613 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1614 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1615 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1616 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1617 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1618 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1619 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1620 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1621 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1622 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1623 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1624 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 3 | Purpose** | 2019-03-15: IFI
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2019-10-08
[6 empty] | Revised Plan | 2019-03-15: 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-2001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 0C |  | Class 3 | Purpose** | 2019-03-15: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-03-18
[6 empty] | Revised Plan | 2019-03-15: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-2501 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5T |  | Class 3 | Purpose** | 2019-03-15: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-03-18
[6 empty] | Revised Plan | 2019-03-15: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-3001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 0P |  | Class 3 | Purpose** | 2019-03-15: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-03-18
[6 empty] | Revised Plan | 2019-03-15: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-4001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5R |  | Class 3 | Purpose** | 2019-03-15: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-03-18
[6 empty] | Revised Plan | 2019-03-15: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-4501 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5F |  | Class 3 | Purpose** | 2019-03-15: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-03-18
[6 empty] | Revised Plan | 2019-03-15: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-5001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5W |  | Class 3 | Purpose** | 2019-03-15: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-03-18
[6 empty] | Revised Plan | 2019-03-15: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-6001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 1B |  | Class 3 | Purpose** | 2019-03-15: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-03-18
[6 empty] | Revised Plan | 2019-03-15: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2A |  | Class 3 | Purpose** | 2019-03-15: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-03-18
[6 empty] | Revised Plan | 2019-03-15: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7201 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2B |  | Class 3 | Purpose** | 2019-03-15: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-03-18
[6 empty] | Revised Plan | 2019-03-15: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7401 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2D |  | Class 3 | Purpose** | 2019-03-15: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-03-18
[6 empty] | Revised Plan | 2019-03-15: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7601 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2E |  | Class 3 | Purpose** | 2019-03-15: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-03-18
[6 empty] | Revised Plan | 2019-03-15: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7801 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5U |  | Class 3 | Purpose** | 2019-03-15: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-03-18
[6 empty] | Revised Plan | 2019-03-15: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-8001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2C |  | Class 3 | Purpose** | 2019-03-15: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-03-18
[6 empty] | Revised Plan | 2019-03-15: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-8501 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 3A |  | Class 3 | Purpose** | 2019-03-15: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-15: 2021-03-18
[6 empty] | Revised Plan | 2019-03-15: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P06 Piping drawing
| MP | OL1-2P06-0001 | GENERAL PLOT PLAN |  | Class 1 | Purpose** | IFR | IFR | IBD | IBD | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B | C | D
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IDD: 2019-09-17; IFC: 2020-04-10
[6 empty] | Revised Plan | IDD: 2019-09-17; IFC: 2020-04-10
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-05-28 | 2019-05-29 | 2019-07-23 | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-02219 | TPSK-LSPA1-T-MP-02386
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15; IBD: 2019-06-19
Owner Cmmt* | bar: IFR to IFR; IBD
| MP | OL1-2P06-0002 | DETAIL PLOT PLAN METERING STATION |  | Class 1 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IBD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-08-30; IBD: 2019-09-17; IBD: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; IFR: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; IFR: TPSK-LSPA1-T-MP-00871
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15
Owner Cmmt* | bar: IFR to IFR
| MP | OL1-2P06-0003 | DETAIL PLOT-PLAN MAIN PIPE RACK |  | Class 1 | Purpose** | IFR | IFR | IBD | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-05-28 | 2019-05-29 | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15; IBD: 2019-06-19
Owner Cmmt* | bar: IFR to IFR; IBD
| MP | OL1-2P06-0004 | DETAIL PLOT-PLAN ELECTRICAL SUB-STATION & FAR E |  | Class 1 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IBD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-09-17; IBD: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; IFR: 2019-02-15; IBD: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; IFR: TPSK-LSPA1-T-MP-00871; IBD: TPSK-LSPA1-T-MP-02386
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15
Owner Cmmt* | bar: IFR to IFR
| MP | OL1-2P06-0005 | DETAIL PLOT PLAN FURNACES |  | Class 1 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IBD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-09-17; IBD: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; IFR: 2019-02-15; IBD: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; IFR: TPSK-LSPA1-T-MP-00871; IBD: TPSK-LSPA1-T-MP-02386
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15
Owner Cmmt* | bar: IFR to IFR
| MP | OL1-2P06-0006 | DETAIL PLOT PLAN FURNACES AND AUXILIARIES |  | Class 1 | Purpose** | IFR | IFR | IBD | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IBD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-09-17; IBD: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-03-07; IFR: 2019-03-08; IBD: 2019-05-28; IBD: 2019-05-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01003; IFR: TPSK-LSPA1-T-MP-01003; IBD: TPSK-LSPA1-T-MP-01752; IBD: TPSK-LSPA1-T-MP-01752
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01; IBD: 2019-06-19
Owner Cmmt* | bar: IFR to IFR; IBD
| MP | OL1-2P06-0007 | DETAIL PLOT PLAN QUENCH |  | Class 1 | Purpose** | IFR | IFR | IBD | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-05-28 | 2019-05-29 | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15; IBD: 2019-06-19
Owner Cmmt* | bar: IFR to IFR; IBD
| MP | OL1-2P06-0008 | DETAIL PLOT PLAN C3 HYDROGENATION |  | Class 1 | Purpose** | IFR | IFR | IBD | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-05-28 | 2019-05-29 | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15; IBD: 2019-06-19
Owner Cmmt* | bar: IFR to IFR; IBD
| MP | OL1-2P06-0009 | DETAIL PLOT PLAN HOT FRACTIONATION / GHU UNIT |  | Class 1 | Purpose** | IFR | IFR | IBD | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-05-28 | 2019-05-29 | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15; IBD: 2019-06-19
Owner Cmmt* | bar: IFR to IFR; IBD
| MP | OL1-2P06-0010 | DETAIL PLOT PLAN PROCESS COLD COMPRESSORS |  | Class 1 | Purpose** | IFR | IFR | IBD | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-05-28 | 2019-05-29 | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15; IBD: 2019-06-19
Owner Cmmt* | bar: IFR to IFR; IBD
| MP | OL1-2P06-0011 | DETAIL PLOT PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  | Class 1 | Purpose** | IFR | IFR | IBD | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-05-28 | 2019-05-29 | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15; IBD: 2019-06-19
Owner Cmmt* | bar: IFR to IFR; IBD
| MP | OL1-2P06-0012 | DETAIL PLOT PLAN BUTADIENE EXTRACTION UNIT |  | Class 1 | Purpose** | IFR | IFR | IBD | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-05-28 | 2019-05-29 | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15; IBD: 2019-06-19
Owner Cmmt* | bar: IFR to IFR; IBD
| MP | OL1-2P06-0013 | DETAIL PLOT-PLAN ELECTRICAL SUB-STATION & FAR C |  | Class 1 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IBD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-09-17; IBD: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; IFR: 2019-02-15; IBD: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; IFR: TPSK-LSPA1-T-MP-00871; IBD: TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15
Owner Cmmt* | bar: IFR to IFR
| MP | OL1-2P06-0014 | DETAIL PLOT PLAN FLARE UNIT |  | Class 1 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IBD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-09-17; IBD: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-03-12; IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01031; IFR: TPSK-LSPA1-T-MP-01031
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
| MP | OL1-2P06-0015 | DETAIL PLOT PLAN COOLING WATER UNIT |  | Class 1 | Purpose** | IFR | IFR | IBD | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-05-28 | 2019-05-29 | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15; IBD: 2019-06-19
Owner Cmmt* | bar: IFR to IFR; IBD
| MP | OL1-2P06-0016 | DETAIL PLOT PLAN UTILITIES |  | Class 1 | Purpose** | IFR | IFR | IBD | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-05-28 | 2019-05-29 | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15; IBD: 2019-06-19
Owner Cmmt* | bar: IFR to IFR; IBD
| MP | OL1-2P06-0017 | DETAIL PLOT PLAN WASTE WATER TREATMENT UNIT |  | Class 1 | Purpose** | IFR | IFR | IBD | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | A | B | B | C
[6 empty] | Issue Plan | IFR: 2019-03-19; IBD: 2019-05-02; IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Revised Plan | IBD: 2019-09-17; IDD: 2020-04-01
[6 empty] | Issue Actual | 2019-02-15 | 2019-02-15 | 2019-05-28 | 2019-05-29 | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15; IBD: 2019-06-19
Owner Cmmt* | bar: IFR to IFR; IBD
| MP | OL1-2P06-0020 | GENERAL KEY-PLAN |  | Class 3 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-29; IBD: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-30; IFR: 2019-05-31; IBD: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; IFR: TPSK-LSPA1-T-MP-01767; IBD: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0021 | DETAIL KEY-PLAN METERING STATION |  | Class 3 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-03-29; IBD: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IBD: 2019-08-30; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-04-24; IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01468; IFR: TPSK-LSPA1-T-MP-01468
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0022 | DETAIL KEY-PLAN MAIN PIPE RACK |  | Class 3 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-29; IBD: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-30; IFR: 2019-05-31; IBD: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; IFR: TPSK-LSPA1-T-MP-01767; IBD: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0023 | DETAIL KEY-PLAN ELECTRICAL SUB-STATION & FAR E |  | Class 3 | Purpose** | IFR: IFR; IFR: IBD; IBD: IDD; IBD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-03-29; IFR: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-08-30; IFR: 2019-08-30; IBD: 2019-09-30; IBD: 2020-04-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0024 | DETAIL KEY-PLAN FURNACES |  | Class 3 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-29; IBD: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-30; IFR: 2019-05-31; IBD: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; IFR: TPSK-LSPA1-T-MP-01767; IBD: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0025 | DETAIL KEY-PLAN FURNACES AUXILIARIES |  | Class 3 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-29; IBD: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-30; IFR: 2019-05-31; IBD: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; IFR: TPSK-LSPA1-T-MP-01767; IBD: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0026 | DETAIL KEY-PLAN QUENCH |  | Class 3 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-29; IBD: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-30; IFR: 2019-05-31; IBD: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; IFR: TPSK-LSPA1-T-MP-01767; IBD: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0027 | DETAIL KEY-PLAN C3 HYDROGENATION |  | Class 3 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-29; IBD: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-30; IFR: 2019-05-31; IBD: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; IFR: TPSK-LSPA1-T-MP-01767; IBD: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0028 | DETAIL KEY-PLAN HOT FRACTIONATION / GHU DETAIL |  | Class 3 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-29; IBD: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-30; IFR: 2019-05-31; IBD: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; IFR: TPSK-LSPA1-T-MP-01767; IBD: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0029 | DETAIL KEY-PLAN COLD COMPRESSORS |  | Class 3 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-29; IBD: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-30; IFR: 2019-05-31; IBD: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; IFR: TPSK-LSPA1-T-MP-01767; IBD: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0030 | DETAIL KEY-PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  | Class 3 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-29; IBD: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-30; IFR: 2019-05-31; IBD: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; IFR: TPSK-LSPA1-T-MP-01767; IBD: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0031 | DETAIL KEY-PLAN BUTADIENE EXTRACTION DETAIL |  | Class 3 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-29; IBD: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-06-18; IFR: 2019-06-18; IBD: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01904; IFR: TPSK-LSPA1-T-MP-01904; IBD: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-07-04; IFR: 2019-07-04
Owner Cmmt* | bar: IFR to IFR
| MP | OL1-2P06-0032 | DETAIL KEY-PLAN ELECTRICAL SUB-STATION & FAR C |  | Class 3 | Purpose** | IFR: IFR; IFR: IBD; IBD: IDD; IBD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-03-29; IFR: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-08-30; IFR: 2019-08-30; IBD: 2019-09-30; IBD: 2020-04-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0033 | DETAIL KEY-PLAN FLARE DETAIL |  | Class 3 | Purpose** | IFR: IFR; IFR: IBD; IBD: IDD; IBD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-03-29; IFR: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-08-30; IFR: 2019-08-30; IBD: 2019-09-30; IBD: 2020-04-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0034 | DETAIL KEY-PLAN COOLING WATER DETAIL |  | Class 3 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-29; IBD: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-30; IFR: 2019-05-31; IBD: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; IFR: TPSK-LSPA1-T-MP-01767; IBD: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0035 | DETAIL KEY-PLAN UTILITIES |  | Class 3 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-29; IBD: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-30; IFR: 2019-05-31; IBD: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; IFR: TPSK-LSPA1-T-MP-01767; IBD: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0036 | DETAIL KEY-PLAN WASTE WATER TREATMENT DETAIL |  | Class 3 | Purpose** | IFR | IFR | IBD | IDD | IFC
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-03-29; IBD: 2019-05-09; IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Revised Plan | IBD: 2019-09-30; IBD: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-30; IFR: 2019-05-31; IBD: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; IFR: TPSK-LSPA1-T-MP-01767; IBD: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0040 | UTILITY STATION PLOT PLAN MAIN PIPE RACK |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0041 | UTILITY STATION PLOT PLAN FURNACES AUXILIARIES |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0042 | UTILITY STATION PLOT PLAN QUENCH |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0043 | UTILITY STATION PLOT PLAN C3 HYDROGENATION |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0044 | UTILITY STATION PLOT PLAN HOT FRACTIONATION / GHU UNIT |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0045 | UTILITY STATION PLOT PLAN COLD COMPRESSORS |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0046 | UTILITY STATION PLOT PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0047 | UTILITY STATION PLOT PLAN BUTADIENE EXTRACTION UNIT |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0048 | UTILITY STATION PLOT PLAN FLARE UNIT |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0049 | UTILITY STATION PLOT PLAN COOLING WATER UNIT |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0050 | UTILITY STATION PLOT PLAN UTILITIES |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0051 | UTILITY STATION PLOT PLAN WASTE WATER TREATMENT UNIT |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0060 | STEAM TRACING MANIFOLDS LOCATION PLAN MAIN PIPE RACK |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-09-01
[6 empty] | Revised Plan | IFR: 2020-09-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0061 | STEAM TRACING MANIFOLDS LOCATION PLAN QUENCH |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-09-01
[6 empty] | Revised Plan | IFR: 2020-09-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0062 | STEAM TRACING MANIFOLDS LOCATION PLAN C3 HYDROGENATION |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-09-01
[6 empty] | Revised Plan | IFR: 2020-09-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0063 | STEAM TRACING MANIFOLDS LOCATION PLAN HOT FRACTIONATION / GHU UNIT |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-09-01
[6 empty] | Revised Plan | IFR: 2020-09-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0064 | STEAM TRACING MANIFOLDS LOCATION PLAN COLD COMPRESSORS |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-09-01
[6 empty] | Revised Plan | IFR: 2020-09-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0065 | STEAM TRACING MANIFOLDS LOCATION PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-09-01
[6 empty] | Revised Plan | IFR: 2020-09-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0066 | STEAM TRACING MANIFOLDS LOCATION PLAN BUTADIENE EXTRACTION UNIT |  | Class 3 | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-09-01
[6 empty] | Revised Plan | IFR: 2020-09-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0070 | GAD KEY-PLAN MAIN PIPE RACK |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IBD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-17; IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394; IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0071 | GAD KEY-PLAN METERING STATION |  | Class 3 | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-11-20; IFR: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IFR: 2021-01-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0072 | GAD KEY-PLAN ELECTRICAL SUB-STATION & FAR E |  | Class 3 | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-11-20; IFR: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IFR: 2021-01-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0073 | GAD KEY-PLAN FURNACES AUXILIARIES |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IBD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-17; IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394; IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0074 | GAD KEY-PLAN QUENCH |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IBD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-17; IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394; IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0075 | GAD KEY-PLAN C3 HYDROGENATION |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IBD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-17; IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394; IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0076 | GAD KEY-PLAN HOT FRACTIONATION / GHU UNIT |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IBD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-17; IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394; IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0077 | GAD KEY-PLAN COLD COMPRESSORS |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IBD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-17; IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394; IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0078 | GAD KEY-PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IBD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-17; IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394; IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0079 | GAD KEY-PLAN BUTADIENE EXTRACTION UNIT |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IBD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-17; IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394; IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0080 | GAD KEY-PLAN ELECTRICAL SUB-STATION & FAR C |  | Class 3 | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-11-20; IFR: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IFR: 2021-01-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0081 | GAD KEY-PLAN FLARE UNIT |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IBD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-17; IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394; IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0082 | GAD KEY-PLAN FLARE LINES ROUTING |  | Class 3 | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-11-20; IFR: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IFR: 2021-01-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0083 | GAD KEY-PLAN COOLING WATER UNIT |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IBD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-17; IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394; IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0084 | GAD KEY-PLAN UTILITIES |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR; IBD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-17; IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394; IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0085 | STD.AUX.PIPE SUPPORTS COLLECTION |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; IBD: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-17; IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394; IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0086 | GAD KEY-PLAN WASTE WATER TREATMENT UNIT |  | Class 3 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-17; IFR: 2019-04-18
[6 empty] | Issue Actual | IFR: 2019-04-17; IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394; IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-2000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 0C |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-2500 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5T |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-2901 | MISC ENGINEERED SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-19; IFR: 2019-12-17
[6 empty] | Revised Plan | IFR: 2019-11-19; IFR: 2019-12-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-2902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  | Class 3 | Purpose** | IFR: IFD; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-09; IFR: 2019-08-06
[6 empty] | Revised Plan | IFR: 2019-09-04; IFR: 2019-10-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-3000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 0P |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-3901 | MISC ENGINEERED SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-19; IFR: 2019-12-17
[6 empty] | Revised Plan | IFR: 2019-11-19; IFR: 2019-12-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-3902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  | Class 3 | Purpose** | IFR: IFD; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-09; IFR: 2019-08-06
[6 empty] | Revised Plan | IFR: 2019-09-04; IFR: 2019-10-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-4500 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5F |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-4901 | MISC ENGINEERED SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-19; IFR: 2019-12-17
[6 empty] | Revised Plan | IFR: 2019-11-19; IFR: 2019-12-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-4902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  | Class 3 | Purpose** | IFR: IFD; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-09; IFR: 2019-08-06
[6 empty] | Revised Plan | IFR: 2019-09-04; IFR: 2019-10-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2C |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5500 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 3A |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5901 | MISC ENGINEERED SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-19; IFR: 2019-12-17
[6 empty] | Revised Plan | IFR: 2019-11-19; IFR: 2019-12-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  | Class 3 | Purpose** | IFR: IFD; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-09; IFR: 2019-08-06
[6 empty] | Revised Plan | IFR: 2019-09-04; IFR: 2019-10-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-6000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 1B |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-6901 | MISC ENGINEERED SUPPORTS |  | Class 3 | Purpose** | IFR: IFR; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-19; IFR: 2019-12-17
[6 empty] | Revised Plan | IFR: 2019-11-19; IFR: 2019-12-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-6902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  | Class 3 | Purpose** | IFR: IFD; IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-09; IFR: 2019-08-06
[6 empty] | Revised Plan | IFR: 2019-09-04; IFR: 2019-10-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2A |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7200 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2B |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7400 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2D |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7600 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2E |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7800 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5U |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-8000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5W |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P07 Piping certification, inspection and test record |  |  |  |  | Class 1 | Purpose**
Category Code: P08 Piping Material Take-off (MTO) | [5 empty] | Rev.
Category Code: P09 Painting Material Take-off (MTO) | [5 empty] | Issue Plan
Category Code: P10 Insulation Material Take-off (MTO) | [5 empty] | Revised Plan
| MP | OL1-2P10-10XX | FURNACE 10-H-1100 LARGE BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1100 LARGE BORE ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-10YY | FURNACE 10-H-1100 SMALL BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1100 SMALL BORE ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-20XX | FURNACE 10-H-1200 LARGE BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1200 LARGE BORE ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-20YY | FURNACE 10-H-1200 SMALL BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1200 SMALL BORE ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-30XX | FURNACE 10-H-1300 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1300 ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-40XX | FURNACE 10-H-1400 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1400 ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-50XX | FURNACE 10-H-1500 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1500 ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-60XX | FURNACE 10-H-1600 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1600 ISOMETRIC DRAWINGS) |  | Class 3 | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAA | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAB | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAC | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAD | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAE | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAF | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAG | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAH | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAI | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAJ | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAK | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAL | ISO.SKETCHES PIPE RACK / SLEEPER |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAM | ISO.SKETCHES PIPE-RACK |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXA | ISO.SKETCHES |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXB | ISO.SKETCHES |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXC | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXD | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXE | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXF | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXG | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXH | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXI | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXJ | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXK | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXL | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXM | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXN | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXO | ISO.SKETCHES AROUND EQUIPMENT |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXP | ISO.SKETCHES CWR HEADER |  | Class 3 | Purpose** | IFR: IFC1; IFR: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; IFR: 2020-10-08; IBD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P20 Aboveground Piping General Arrangement Drawings
| MP | OL1-2P20-0100 | GAD (N...) |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0101 | GAD BATTERY LIMIT OL1-A |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0200 | GAD (N...) |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0300 | GAD (N...) |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0400 | GAD (N...) |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-1000 | GAD (N...) |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2200 | GAD (N...) |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2300 | GAD (N...) |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2301 | GAD BATTERY LIMIT OU1-A |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2400 | GAD (N...) |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2500 | GAD (N...) |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-3000 | GAD (N...) |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5100 | GAD (N...) |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5200 | GAD (N...) |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5300 | GAD (N...) |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5400 | GAD (N...) |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5500 | GAD (N...) |  | Class 3 | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P21 Underground Piping General Arrangement Drawings
Category Code: P22 Aboveground Piping Isometric Drawings
Category Code: P23 Underground Piping Isometric Drawings
Category Code: P25 Pipe support drawing
| MP | OL1-2P25-0085 | Standard Auxiliary Piping Support Collection |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: IFC
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-01-31; IBD: 2019-02-28
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-02-20; IFR: 2019-02-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00896; IFR: TPSK-LSPA1-T-MP-00896
[6 empty] | Return Date | IFR: 2019-04-05; IFR: 2019-04-05
Owner Cmmt* | bar: IFR to IFR
Category Code: P30 3D Model Review File
| MP | OL1-2P30-0014 | Model Review Report Furnace Island Action List 30 Percent |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IFR | IFR
[6 empty] | Rev. | A | A | B | B | C | C
Issue Plan
[6 empty] | Revised Plan | 2019-04-11 | 2019-04-12 | 2019-05-30 | 2019-05-31 | 2019-07-10 | 2019-07-10
[6 empty] | Issue Actual | 2019-04-11 | 2019-04-12 | 2019-05-30 | 2019-05-31 | 2019-07-10 | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-01331 | TPSK-LSPA1-T-MP-01331 | TPSK-LSPA1-T-MP-01782 | TPSK-LSPA1-T-MP-01782 | TPSK-LSPA1-T-MP-02107 | TPSK-LSPA1-T-MP-02107
[6 empty] | Return Date | IFR: 2019-05-27; IFR: 2019-05-27
Owner Cmmt* | bar: IFR to IFR
| MP | OL1-2P30-0020 | Model Review Report Metering Station And General Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; IFR: IFI
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02145; IFR: TPSK-LSPA1-T-MP-02145
Return Date
Owner Cmmt*
| MP | OL1-2P30-0022 | Model Review Report Furnace Utilities And Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; IFR: IFI
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02145; IFR: TPSK-LSPA1-T-MP-02145
Return Date
Owner Cmmt*
| MP | OL1-2P30-0024 | Model Review Report C3 Hydrogenation Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; IFR: IFI
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02145; IFR: TPSK-LSPA1-T-MP-02145
Return Date
Owner Cmmt*
| MP | OL1-2P30-0025 | Model Review Report Hot Fractioning Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; IFR: IFI
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02145; IFR: TPSK-LSPA1-T-MP-02145
Return Date
Owner Cmmt*
| MP | OL1-2P30-0026 | Model Review Report Cold Compression Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; IFR: IFI
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02145; IFR: TPSK-LSPA1-T-MP-02145
Return Date
Owner Cmmt*
| MP | OL1-2P30-0027 | Model Review Report Cracked Gas Compressor Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; IFR: IFI
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02145; IFR: TPSK-LSPA1-T-MP-02145
Return Date
Owner Cmmt*
| MP | OL1-2P30-0028 | Model Review Report Butadeine Extraction Unit Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; IFR: IFI
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02145; IFR: TPSK-LSPA1-T-MP-02145
Return Date
Owner Cmmt*
| MP | OL1-2P30-0029 | Model Review Report Flare Unit Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; IFR: IFI
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02145; IFR: TPSK-LSPA1-T-MP-02145
Return Date
Owner Cmmt*
| MP | OL1-2P30-0030 | Model Review Report Cooling Water Unit Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; IFR: IFI
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02145; IFR: TPSK-LSPA1-T-MP-02145
Return Date
Owner Cmmt*
| MP | OL1-2P30-0031 | Model Review Report Utilities And Flare KO Drum Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; IFR: IFI
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02145; IFR: TPSK-LSPA1-T-MP-02145
Return Date
Owner Cmmt*
| MP | OL1-2P30-0032 | Model Review Report Waste Water Treatment Unit Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; IFR: IFI
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02145; IFR: TPSK-LSPA1-T-MP-02145
Return Date
Owner Cmmt*
| MP | OL1-P30-0002 | AUX.PIPE SUPP.LIST & BILL OF MTL - COOLING WATER UNIT |  | Class 3 | Purpose** | IFR: IFC; IFR: IFC1; IBD: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2020-11-16; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2020-11-16; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-P30-0003 | AUX.PIPE SUPP.LIST & BILL OF MTL - MAIN PIPE RACK |  | Class 3 | Purpose** | IFR: IFC; IFR: IFC1; IBD: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2020-11-16; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2020-11-16; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-P30-0004 | AUX.PIPE SUPP.LIST & BILL OF MTL - OFF-SITES |  | Class 3 | Purpose** | IFR: IFC; IFR: IFC1; IBD: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2020-11-16; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2020-11-16; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-P30-0005 | AUX.PIPE SUPP.LIST & BILL OF MTL - WASTE WATER TREATMENT |  | Class 3 | Purpose** | IFR: IFC; IFR: IFC1; IBD: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2020-11-16; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2020-11-16; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-P30-0006 | AUX.PIPE SUPP.LIST & BILL OF MTL - FURNACES UTILITIES |  | Class 3 | Purpose** | IFR: IFC; IFR: IFC1; IBD: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2020-11-16; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2020-11-16; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-P30-0007 | AUX.PIPE SUPP.LIST & BILL OF MTL - FRACTIONATION 1 & 2 |  | Class 3 | Purpose** | IFR: IFC; IFR: IFC1; IBD: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2020-11-16; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2020-11-16; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-P30-0008 | AUX.PIPE SUPP.LIST & BILL OF MTL - FRACTIONATION 3 & BUTADIENE EXTRACTION |  | Class 3 | Purpose** | IFR: IFC; IFR: IFC1; IBD: IFC2; IBD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2020-11-16; IBD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; IFR: 2020-07-29; IBD: 2020-11-16; IBD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P40 Piping Generic Lists
| MP | OL1-2P40-0007 | TIE-INS / INTERFACE POINTS LIST |  | Class 2 | Purpose** | IBD | IDD1 | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-03-20 | 2019-08-06 | 2019-11-12 | 2020-02-07 | 2020-04-30
[6 empty] | Revised Plan | IBD: 2019-11-12; IBD: 2020-02-07; IBD: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P40-0008 | STEAM TRACING MANIFOLD LIST |  | Class 3 | Purpose** | IFR: IFR; IFR: IDD; IBD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-12; IFR: 2020-03-20; IBD: 2020-04-30
[6 empty] | Revised Plan | IFR: 2019-11-12; IFR: 2020-03-20; IBD: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P71 Appraisal Report for Consultancy Service
Category Code: P72 Appraisal Report for EPC Contractor Work
Category Code: P73 Appraisal Report for Vendor/Supplier
Category Code: P90 Vendor Document/drawings
Category Code: P91 Index/List
| MP | OL1-2P91-1001 | LINE LIST - OLEFINS PROCESS AREA 10 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-05-01; IBD: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01541; IBD: TPSK-LSPA1-T-MP-01541
[6 empty] | Return Date | IFR: 2019-05-24; IBD: 2019-05-24
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-1101 | LINE DESIGNATION TABLE - FURNACE AREA |  | Class 2 | Purpose** | IFR | IBD | IBD | IFD | IFF
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-01-10; IFR: 2019-02-15; IBD: 2019-06-10; IBD: 2019-09-03
[6 empty] | Revised Plan | IBD: 2019-09-03
[6 empty] | Issue Actual | IFR: 2019-02-26; IBD: 2019-02-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-00933; IBD: TPSK-LSPA1-T-PE-00933
[6 empty] | Return Date | IFR: 2019-05-15; IBD: 2019-05-15
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-1201 | LINE DESIGNATION TABLE - FURNACE AREA |  | Class 2 | Purpose** | IFR | IBD | IBD | IFD | IFF
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | IFR: 2019-01-10; IFR: 2019-02-15; IBD: 2019-06-10; IBD: 2019-09-03
[6 empty] | Revised Plan | IBD: 2019-09-03
[6 empty] | Issue Actual | IFR: 2019-02-26; IBD: 2019-02-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-00934; IBD: TPSK-LSPA1-T-PE-00934
[6 empty] | Return Date | IFR: 2019-05-15; IBD: 2019-05-15
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-1901 | Line Designation Table - Furnace Auxiliaries |  | Class 2 | Purpose** | IFR: IBD; IFR: IBD
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-16; IFR: 2019-04-17
[6 empty] | Issue Actual | IFR: 2019-04-16; IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP -01375; IFR: TPSK-LSPA1-T-MP -01375
[6 empty] | Return Date | IFR: 2019-05-24; IFR: 2019-05-24
Owner Cmmt* | bar: IFR to IFR
| MP | OL1-2P91-2001 | LINE LIST - OLEFINS PROCESS AREA 20 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-04-23; IBD: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01450; IBD: TPSK-LSPA1-T-MP-01450
[6 empty] | Return Date | IFR: 2019-05-24; IBD: 2019-05-24
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-2101 | LINE LIST - OLEFINS PROCESS AREA 21 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-04-26; IBD: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01497; IBD: TPSK-LSPA1-T-MP-01497
[6 empty] | Return Date | IFR: 2019-05-24; IBD: 2019-05-24
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-2201 | LINE LIST - OLEFINS PROCESS AREA 22 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-04-16; IBD: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP -01375; IBD: TPSK-LSPA1-T-MP -01375
[6 empty] | Return Date | IFR: 2019-05-24; IBD: 2019-05-24
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-2301 | LINE LIST - OLEFINS PROCESS AREA 23 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-04-16; IBD: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP -01375; IBD: TPSK-LSPA1-T-MP -01375
[6 empty] | Return Date | IFR: 2019-05-24; IBD: 2019-05-24
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-2401 | LINE LIST - OLEFINS PROCESS AREA 24 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-04-30; IBD: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01531; IBD: TPSK-LSPA1-T-MP-01531
[6 empty] | Return Date | IFR: 2019-05-24; IBD: 2019-05-24
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-2501 | LINE LIST - OLEFINS PROCESS AREA 25 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-04-24; IBD: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01466; IBD: TPSK-LSPA1-T-MP-01466
[6 empty] | Return Date | IFR: 2019-05-24; IBD: 2019-05-24
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-2601 | LINE LIST - OLEFINS PROCESS AREA 26 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-05-13; IBD: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01651; IBD: TPSK-LSPA1-T-MP-01651
[6 empty] | Return Date | IFR: 2019-05-24; IBD: 2019-05-24
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-2701 | LINE LIST - OLEFINS PROCESS AREA 27 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-05-13; IBD: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP -01656; IBD: TPSK-LSPA1-T-MP -01656
[6 empty] | Return Date | IFR: 2019-05-24; IBD: 2019-05-24
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-2801 | LINE LIST - OLEFINS PROCESS AREA 28 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-04-26; IBD: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01497; IBD: TPSK-LSPA1-T-MP-01497
[6 empty] | Return Date | IFR: 2019-05-24; IBD: 2019-05-24
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-2901 | LINE LIST - OLEFINS PROCESS AREA 29 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-05-08; IBD: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01620; IBD: TPSK-LSPA1-T-MP-01620
[6 empty] | Return Date | IFR: 2019-05-24; IBD: 2019-05-24
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-3001 | LINE LIST - OLEFINS PROCESS AREA 30 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-06-03; IBD: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01795; IBD: TPSK-LSPA1-T-MP-01795
[6 empty] | Return Date | IFR: 2019-06-21; IBD: 2019-06-21
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-3101 | Line Designation Table - Butadiene Extraction Unit Utilities |  | Class 2 | Purpose** | IFR: IBD; IFR: IBD
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01795; IFR: TPSK-LSPA1-T-MP-01795
[6 empty] | Return Date | IFR: 2019-06-21; IFR: 2019-06-21
Owner Cmmt* | bar: IFR to IFR
| MP | OL1-2P91-3901 | Line Designation Table - C4 Unit Auxiliaries |  | Class 2 | Purpose** | IFR: IBD; IFR: IBD
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-03; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01795; IFR: TPSK-LSPA1-T-MP-01795
[6 empty] | Return Date | IFR: 2019-06-21; IFR: 2019-06-21
Owner Cmmt* | bar: IFR to IFR
| MP | OL1-2P91-5001 | LINE LIST - OLEFINS UTILITY AREA 50 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-05-08; IBD: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01620; IBD: TPSK-LSPA1-T-MP-01620
[6 empty] | Return Date | IFR: 2019-05-24; IBD: 2019-05-24
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-5101 | Line Designation Table - BFW - Steam - Steam Condensate System |  | Class 2 | Purpose** | IFR: IBD; IFR: IBD
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-05-13; IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP -01656; IFR: TPSK-LSPA1-T-MP -01656
[6 empty] | Return Date | IFR: 2019-05-24; IFR: 2019-05-24
Owner Cmmt* | bar: IFR to IFR
| MP | OL1-2P91-5201 | Line Designation Table - Fuel System |  | Class 2 | Purpose** | IFR: IBD; IFR: IBD
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Issue Actual | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01627; IFR: TPSK-LSPA1-T-MP-01627
[6 empty] | Return Date | IFR: 2019-05-24; IFR: 2019-05-24
Owner Cmmt* | bar: IFR to IFR
| MP | OL1-2P91-5301 | LINE LIST - OLEFINS UTILITY AREA 53 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-05-13; IBD: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP -01656; IBD: TPSK-LSPA1-T-MP -01656
[6 empty] | Return Date | IFR: 2019-05-24; IBD: 2019-05-24
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-5401 | Line Designation Table - Plant Air - Instrument Air - Nitrogen |  | Class 2 | Purpose** | IFR: IBD; IFR: IBD
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Issue Actual | IFR: 2019-05-09; IFR: 2019-05-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01627; IFR: TPSK-LSPA1-T-MP-01627
[6 empty] | Return Date | IFR: 2019-05-24; IFR: 2019-05-24
Owner Cmmt* | bar: IFR to IFR
| MP | OL1-2P91-5501 | LINE LIST - OLEFINS UTILITY AREA 55 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-05-13; IBD: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP -01648; IBD: TPSK-LSPA1-T-MP -01648
[6 empty] | Return Date | IFR: 2019-05-24; IBD: 2019-05-24
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-5601 | LINE LIST - OLEFINS UTILITY AREA 56 |  | Class 3 | Purpose** | IFR | IBD | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IBD
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  |  |  | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | IFR: 2019-05-13; IBD: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP -01656; IBD: TPSK-LSPA1-T-MP -01656
[6 empty] | Return Date | IFR: 2019-05-24; IBD: 2019-05-24
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P91-5701 | Line Designation Table - Fire Water |  | Class 2 | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | 2019-06-10 |  | 2019-10-30 | 2020-05-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | IBD: 2019-10-30; IBD: 2020-05-06; IBD: 2020-05-29; IBD: 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-06-10; IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01841; IFR: TPSK-LSPA1-T-MP-01841
[6 empty] | Return Date | IFR: 2019-06-27
Owner Cmmt* | bar: IFR
| MP | OL1-2P91-5901 | Line Designation Table - Supporting Utilities Auxiliaries |  | Class 2 | Purpose** | IFR: IBD; IFR: IBD
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-08; IFR: 2019-05-09
[6 empty] | Issue Actual | IFR: 2019-05-08; IFR: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01620; IFR: TPSK-LSPA1-T-MP-01620
[6 empty] | Return Date | IFR: 2019-05-24; IFR: 2019-05-24
Owner Cmmt* | bar: IFR to IFR
Category Code: P92 Procedures & Standards
| MP | OL1-2P92-0001 | PIPING STANDARD ASSEMBLY COLLECTION |  |  | Purpose** | IFR: IFR; IFR: IFR; IBD: IMP
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-02-28; IBD: 2019-03-17
[6 empty] | Revised Plan | IBD: 2019-09-13
[6 empty] | Issue Actual | IFR: 2019-06-20; IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01927; IFR: TPSK-LSPA1-T-MP-01927
[6 empty] | Return Date | IFR: 2019-07-10; IFR: 2019-07-10
Owner Cmmt* | bar: IFR to IFR
| MP | OL1-2P92-0002 | Piping Design Standard Drawings |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: CAN
[6 empty] | Rev. | IFR: A; IFR: A; IBD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-08-08; IFR: 2018-08-08; IBD: 2018-11-16
[6 empty] | Issue Actual | IFR: 2018-08-08; IFR: 2018-08-08; IBD: 2018-11-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00012; IFR: TPSK-LSPA1-T-MP-00012; IBD: TPSK-LSPA1-T-MP-00325
[6 empty] | Return Date | IFR: 2018-09-26; IFR: 2018-09-26; IBD: 2018-12-07
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P92-0003 | Piping Construction Drawing |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: CAN
[6 empty] | Rev. | IFR: A; IFR: A; IBD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-08-08; IFR: 2018-08-08; IBD: 2018-11-16
[6 empty] | Issue Actual | IFR: 2018-08-08; IFR: 2018-08-08; IBD: 2018-11-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00012; IFR: TPSK-LSPA1-T-MP-00012; IBD: TPSK-LSPA1-T-MP-00325
[6 empty] | Return Date | IFR: 2018-09-26; IFR: 2018-09-26; IBD: 2018-12-07
Owner Cmmt* | bar: IFR to IBD
| MP | OL1-2P92-0004 | JOB CONSTRUCTION SPECIFICATION FOR BOLTED FLANGED JOINT ASSEMBLY |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: IMP
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-04-06; IBD: 2019-05-06
[6 empty] | Revised Plan | IBD: 2019-08-30
[6 empty] | Issue Actual | IFR: 2019-05-10; IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01635; IFR: TPSK-LSPA1-T-MP-01635
[6 empty] | Return Date | IFR: 2019-05-31; IFR: 2019-05-31
Owner Cmmt* | bar: IFR to IFR
| MP | OL1-2P92-0007 | CONSTRUCTION SPECIFICATION FOR PIPING PREFABRICATION, ERECTION AND NON DESTRUCTIVE TESTING |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: IFC; IBD: IFC
[6 empty] | Rev. | IFR: A; IFR: A; IBD: 0; IBD: 0
[6 empty] | Issue Plan | IFR: 2019-04-16; IBD: 2019-06-15
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-02-25; IFR: 2019-02-26; IBD: 2019-05-23; IBD: 2019-05-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00917; IFR: TPSK-LSPA1-T-MP-00917; IBD: TPSK-LSPA1-T-MP-01726; IBD: TPSK-LSPA1-T-MP-01726
[6 empty] | Return Date | IFR: 2019-05-07; IFR: 2019-05-07; IBD: 2019-06-14
Owner Cmmt* | bar: IFR to IFR; IBD
| MP | OL1-2P92-0008 | HYDROSTATIC LEAK TESTING FOR PIPING SYSTEMS |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: IFC; IBD: IFC
[6 empty] | Rev. | IFR: A; IFR: A; IBD: 0; IBD: 0
[6 empty] | Issue Plan | IFR: 2019-04-16; IBD: 2019-06-15
Revised Plan
[6 empty] | Issue Actual | IFR: 2019-03-25; IFR: 2019-03-26; IBD: 2019-05-23; IBD: 2019-05-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01136; IFR: TPSK-LSPA1-T-MP-01136; IBD: TPSK-LSPA1-T-MP-01726; IBD: TPSK-LSPA1-T-MP-01726
[6 empty] | Return Date | IFR: 2019-04-11; IFR: 2019-04-11; IBD: 2019-06-14
Owner Cmmt* | bar: IFR to IFR; IBD
| MP | OL1-2P92-0012 | SPECIAL TECH.SPEC.PIP.PREFAB. & ERE. |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-01-30; IFR: 2019-03-15
[6 empty] | Revised Plan | IFR: 2019-08-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P93 Policy , Guidelines & Memo
Category Code: P94 Forms & Templates
Category Code: P95 Progress/Status Reports
Category Code: Q07 Quality Audit Reports
Category Code: Q10 QC Record and Report for Civil work (Engineerig and Procurement)
Category Code: Q11 QC Record and Report for Building work (Engineerig and Procurement)
Category Code: Q12 QC Record and Report for Steel Structure work (Engineerig and Procurement)
Category Code: Q13 QC Record and Report for Mechanical work (Engineerig and Procurement)
Category Code: Q14 QC Record and Report for Piping work (Engineerig and Procurement)
Category Code: Q15 QC Record and Report for Fire Fighting work (Engineerig and Procurement)
Category Code: Q16 QC Record and Report for Electrical work (Engineerig and Procurement)
Category Code: Q17 QC Record and Report for Instrumentation work (Engineerig and Procurement)
Category Code: Q20 QC Record and Report for Civil work (construction)
| QM | OL1-2Q20-0001 | Quality Control Plan Civil Works-Fencing |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-13
[6 empty] | Issue Actual | IFR: 2018-12-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00488; IFR: TPSK-LSPA1-T-QM-00488
[6 empty] | Return Date | IFR: 2019-02-25; IFR: 2019-02-25
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0002 | Quality Control Plan Civil Works-Bored Cast In Situ Piles |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-11
[6 empty] | Issue Actual | IFR: 2019-01-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00625; IFR: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0003 | Quality Control Plan Civil Works-Continuous Flight Auger Piles |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-11
[6 empty] | Issue Actual | IFR: 2019-01-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00625; IFR: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0004 | Quality Control Plan Civil Works-Concrete Precast Driven Piles |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-11
[6 empty] | Issue Actual | IFR: 2019-01-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00625; IFR: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0005 | Quality Control Plan Civil Works-Earth Moving |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-11
[6 empty] | Issue Actual | IFR: 2019-01-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00625; IFR: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0006 | Quality Control Plan Civil Works-Asphalt Roads And Yards |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-11
[6 empty] | Issue Actual | IFR: 2019-01-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00625; IFR: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0007 | Quality Control Plan U-G Civil Works-Sewers |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-11
[6 empty] | Issue Actual | IFR: 2019-01-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00625; IFR: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0008 | Quality Control Plan Non Metallic Pressure Piping Installation - Above and Underground |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-11
[6 empty] | Issue Actual | IFR: 2019-01-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00625; IFR: TPSK-LSPA1-T-QM-00625
Return Date
Owner Cmmt*
| QM | OL1-2Q20-0009 | Quality Control Plan Civil Works-Reinforced Concrete For Foundation-Elevation Structures And Basins |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729; IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0010 | Quality Control Plan Civil Works-Prefabrication of Concrete Elements |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729; IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0011 | Quality Control Plan Precast Pipe-Rack Erection |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729; IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0012 | Quality Control Plan Civil Works-Tank Rings Foundations |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729; IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0013 | Quality Control Plan Above Ground Civil Works- Concrete Elements Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729; IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0014 | Quality Control Plan Civil Works-Rigid Paving |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729; IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0015 | Quality Control Plan U-G Civil Works-Installation of Concrete Pits Cable Duct Banks Trenches-Ditches Cable Trenches Direct Buried Box Culverts and Lighting Poles Foundations |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729; IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0016 | Quality Control Plan Civil Works-Concrete Structure for Cooling Tower |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729; IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0017 | Quality Control Plan Civil Works-Fire Proofing |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729; IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0018 | Quality Control Plan Civil Works-Grouting |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729; IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q20-0019 | Quality Control Plan Concrete Protective Coating |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729; IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
Category Code: Q21 QC Record and Report for Building work (construction)
| QM | OL1-2Q21-0001 | Quality Control Plan Building -Concrete And Masonry- |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01596; IFR: TPSK-LSPA1-T-QM-01596
[6 empty] | Return Date | IFR: 2019-06-12
Owner Cmmt* | bar: IFR
Category Code: Q22 QC Record and Report for Steel Structure work (construction)
| QM | OL1-2Q22-0001 | Quality Control Plan Steel Structures Erection |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729; IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27; IFR: 2019-02-27
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q22-0002 | Quality Control Plan Secondary Steel Structures Erection - Ladders Platforms Walkways Handrails Gratings |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00735; IFR: TPSK-LSPA1-T-QM-00735
[6 empty] | Return Date | IFR: 2019-03-18; IFR: 2019-03-18
Owner Cmmt* | bar: IFR to IFR
Category Code: Q23 QC Record and Report for Mechanical work (construction)
| QM | OL1-2Q23-0001 | Quality Control Plan Fixed Roof Tanks Erection |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-27; IFR: 2019-02-28
[6 empty] | Issue Actual | IFR: 2019-02-27; IFR: 2019-02-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00942; IFR: TPSK-LSPA1-T-QM-00942
Return Date
Owner Cmmt*
| QM | OL1-2Q23-0002 | Quality Control Plan Floating Roof Tanks Erection |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-27; IFR: 2019-02-28
[6 empty] | Issue Actual | IFR: 2019-02-27; IFR: 2019-02-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00942; IFR: TPSK-LSPA1-T-QM-00942
Return Date
Owner Cmmt*
| QM | OL1-2Q23-0003 | Quality Control Plan Cryogenic Tanks Erection |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-27; IFR: 2019-02-28
[6 empty] | Issue Actual | IFR: 2019-02-27; IFR: 2019-02-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00942; IFR: TPSK-LSPA1-T-QM-00942
Return Date
Owner Cmmt*
| QM | OL1-2Q23-0006 | Quality Control Plan Static Equipment Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q23-0007 | Quality Control Plan Package Furnace - Site Assembled - Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q23-0008 | Quality Control Plan Flare System Erection |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q23-0009 | Quality Control Plan Refractory Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q23-0010 | Quality Control Plan Machinery Installation - Centrifugal and Rotary Pumps |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q23-0011 | Quality Control Plan Machinery Installation - Blower and Fans |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q23-0012 | Quality Control Plan Machinery Installation - Centrifugal Compressors |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q23-0013 | Quality Control Plan Machinery Installation - Reciprocating Compressors |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q23-0014 | Quality Control Plan Machinery Installation - Mixers and Agitators |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q23-0015 | Quality Control Plan Elevator Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q23-0016 | Quality Control Plan Equipment Internals Installation - Trays |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
Return Date
Owner Cmmt*
| QM | OL1-2Q23-0017 | Quality Control Plan Equipment Internals Installation - Distributors-Grids-Demisters-etc |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q23-0018 | Quality Control Plan Air Coolers Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-19; IFR: 2019-03-20
[6 empty] | Issue Actual | IFR: 2019-03-19; IFR: 2019-03-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01091; IFR: TPSK-LSPA1-T-QM-01091
Return Date
Owner Cmmt*
| QM | OL1-2Q23-0019 | Quality Control Plan Cooling Tower Mechanical Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q23-0020 | Quality Control Plan Packages Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q23-0021 | Quality Control Plan Skid Mounted Packages |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q23-0022 | Quality Control Plan Bridge Crane Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-08; IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011; IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01; IFR: 2019-04-01
Owner Cmmt* | bar: IFR to IFR
Category Code: Q24 QC Dossier for Piping work (construction)
| QM | OL1-2Q24-0001 | Quality Control Plan Piping Prefabrication |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730; IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05; IFR: 2019-04-05
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q24-0002 | Quality Control Plan Piping Support Prefabrication |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730; IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05; IFR: 2019-04-05
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q24-0003 | Quality Control Plan Piping Erection - Above & Underground |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730; IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05; IFR: 2019-04-05
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q24-0004 | Quality Control Plan Piping Support Erection |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730; IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05; IFR: 2019-04-05
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q24-0005 | Quality Control Plan Steam Tracing System |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730; IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05; IFR: 2019-04-05
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q24-0006 | Quality Control Plan Piping Tie-ins |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730; IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05; IFR: 2019-04-05
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q24-0007 | Quality Control Plan Piping NDE PWHT Management |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730; IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05; IFR: 2019-04-05
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q24-0008 | Quality Control Plan Welders Management |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730; IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05; IFR: 2019-04-05
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q24-0009 | Quality Control Plan Insulation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730; IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05; IFR: 2019-04-05
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q24-0010 | Quality Control Plan Painting |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730; IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05; IFR: 2019-04-05
Owner Cmmt* | bar: IFR to IFR
Category Code: Q25 QC Record and Report for Fire Fighting work (construction)
| QM | OL1-2Q25-0001 | Quality Control Plan Fire Fighting System Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01596; IFR: TPSK-LSPA1-T-QM-01596
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
Category Code: Q26 QC Record and Report for Electrical work (construction)
| QM | OL1-2Q26-0001 | Quality Control Plan - Electrical Installation - Grounding And Lightning System |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-16; IFR: 2019-05-17
[6 empty] | Issue Actual | IFR: 2019-05-16; IFR: 2019-05-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01676; IFR: TPSK-LSPA1-T-QM-01676
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| QM | OL1-2Q26-0002 | Quality Control Plan -Electrical Installation- Substation Equipment |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-23; IFR: 2019-05-24
[6 empty] | Issue Actual | IFR: 2019-05-23; IFR: 2019-05-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01724; IFR: TPSK-LSPA1-T-QM-01724
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| QM | OL1-2Q26-0003 | Quality Control PlanElectrical InstallationPower System |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-31; IFR: 2019-06-03
[6 empty] | Issue Actual | IFR: 2019-05-31; IFR: 2019-06-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01789; IFR: TPSK-LSPA1-T-QM-01789
[6 empty] | Return Date | IFR: 2019-06-10; IFR: 2019-06-10
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q26-0004 | Quality Control Plan - Electrical Iinstallation - High Voltage Equipment |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-16; IFR: 2019-05-17
[6 empty] | Issue Actual | IFR: 2019-05-16; IFR: 2019-05-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01676; IFR: TPSK-LSPA1-T-QM-01676
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| QM | OL1-2Q26-0005 | Quality Control Plan - Electrical Installation-Electrical Heat Tracing System |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-27; IFR: 2019-05-28
[6 empty] | Issue Actual | IFR: 2019-05-27; IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01750; IFR: TPSK-LSPA1-T-QM-01750
[6 empty] | Return Date | IFR: 2019-06-10; IFR: 2019-06-10
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q26-0006 | Quality Control Plan - Electrical Installation-Cathodic Protection System |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-27; IFR: 2019-05-28
[6 empty] | Issue Actual | IFR: 2019-05-27; IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01750; IFR: TPSK-LSPA1-T-QM-01750
[6 empty] | Return Date | IFR: 2019-06-10; IFR: 2019-06-10
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q26-0007 | Quality Control PlanElectrical InstallationLighting System |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-27; IFR: 2019-05-28
[6 empty] | Issue Actual | IFR: 2019-05-27; IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01750; IFR: TPSK-LSPA1-T-QM-01750
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| QM | OL1-2Q26-0008 | Quality Control Plan -Electrical Installation- Rotating Equipment |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-23; IFR: 2019-05-24
[6 empty] | Issue Actual | IFR: 2019-05-23; IFR: 2019-05-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01724; IFR: TPSK-LSPA1-T-QM-01724
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| QM | OL1-2Q26-0009 | Quality Control Plan Building HVAC -Heating Ventilation And Air Conditioning- System Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01596; IFR: TPSK-LSPA1-T-QM-01596
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
Category Code: Q27 QC Record and Report for Instrumentation work (construction)
| QM | OL1-2Q27-0001 | Quality Control Plan - Instrumentation And Communication System - Installation Works In Control Room |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-10; IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-10; IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01636; IFR: TPSK-LSPA1-T-QM-01636
[6 empty] | Return Date | IFR: 2019-06-17
Owner Cmmt* | bar: IFR
| QM | OL1-2Q27-0002 | Quality Control Plan - Instrumentation And Communication System Installation - Instrument Cables Junction Boxes And Local Panels Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-10; IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-10; IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01636; IFR: TPSK-LSPA1-T-QM-01636
[6 empty] | Return Date | IFR: 2019-06-17
Owner Cmmt* | bar: IFR
| QM | OL1-2Q27-0003 | Quality Control Plan - Instrumentation And Communication System Installation - Field Instrumentation Works |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-10; IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-10; IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01636; IFR: TPSK-LSPA1-T-QM-01636
[6 empty] | Return Date | IFR: 2019-06-17
Owner Cmmt* | bar: IFR
| QM | OL1-2Q27-0004 | Quality Control Plan - Instrumentation And Communication System Installation - Analyzer Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-10; IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-10; IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01636; IFR: TPSK-LSPA1-T-QM-01636
[6 empty] | Return Date | IFR: 2019-06-17
Owner Cmmt* | bar: IFR
| QM | OL1-2Q27-0005 | Quality Control Plan - Instrumentation And Communication System Installation - Telecommunication Systems Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-10; IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-10; IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01636; IFR: TPSK-LSPA1-T-QM-01636
[6 empty] | Return Date | IFR: 2019-06-10; IFR: 2019-06-10
Owner Cmmt* | bar: IFR to IFR
| QM | OL1-2Q27-0006 | Quality Control Plan - Instrumentation And Communication System Installation - Package Instrumentation Test |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-10; IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-10; IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01636; IFR: TPSK-LSPA1-T-QM-01636
[6 empty] | Return Date | IFR: 2019-06-17
Owner Cmmt* | bar: IFR
Category Code: Q30 Shop Inspection Notice (Civil)
Category Code: Q31 Shop Inspection Notice (Mechanical)
Category Code: Q32 Shop Inspection Notice (Piping)
Category Code: Q33 Shop Inspection Notice (Electrical)
Category Code: Q34 Shop Inspection Notice (Instrumentation)
Category Code: Q35 Mechanical certification (Civil)
Category Code: Q36 Mechanical certification (Static)
Category Code: Q37 Mechanical certification (Rotating)
Category Code: Q38 Mechanical certification (Piping))
Category Code: Q40 Site Inspection Notice (Civil)
Category Code: Q41 Site Inspection Notice (Mechanical)
Category Code: Q42 Site Inspection Notice (Piping)
Category Code: Q43 Site Inspection Notice (Electrical)
Category Code: Q44 Site Inspection Notice (Instrumentation)
Category Code: Q60 Inspection and Test Plan (ITP) for Mechanical Work
Category Code: Q61 Inspection and Test Plan (ITP) for Piping Work
Category Code: Q62 Inspection and Test Plan (ITP) for Electrical work
Category Code: Q63 Inspection and Test Plan (ITP)for Instrumentation work
Category Code: Q64 Inspection and Test Plan (ITP) for Civil,Structure and Architecture.
Category Code: Q65 Inspection and Test Plan (ITP) for Mechanical Work (Construction)
Category Code: Q66 Inspection and Test Plan (ITP) for Piping Work (Construction)
Category Code: Q67 Inspection and Test Plan (ITP) for Electrical work (Construction)
Category Code: Q68 Inspection and Test Plan (ITP)for Instrumentation work (Construction)
Category Code: Q69 Inspection and Test Plan (ITP) for Civil,Structure and Architecture (Construction)
Category Code: Q71 Appraisal Report for Consultancy Service
Category Code: Q72 Appraisal Report for EPC Contractor Work
Category Code: Q73 Appraisal Report for Vendor/Supplier
Category Code: Q90 Vendor Document/drawings
Category Code: Q91 Index/List
Category Code: Q92 Procedures & Standards
| QM | OL1-2Q92-0004 | Overall Project Audit Plan |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-21
[6 empty] | Issue Actual | IFR: 2019-03-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01116
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0008 | Quality Control Plan Material Management and Warehouse |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-07; IFR: 2019-02-07
[6 empty] | Issue Actual | IFR: 2019-02-07; IFR: 2019-02-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00818; IFR: TPSK-LSPA1-T-QM-00818
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0011 | Job Construction Specification For Welders Management |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-03; IFR: 2019-04-04
[6 empty] | Issue Actual | IFR: 2019-04-03; IFR: 2019-04-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01236; IFR: TPSK-LSPA1-T-QM-01236
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0012 | Job Construction Specification For Welding Activities Management |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-03; IFR: 2019-04-04
[6 empty] | Issue Actual | IFR: 2019-04-03; IFR: 2019-04-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01236; IFR: TPSK-LSPA1-T-QM-01236
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0013 | Job Construction Specification For Piping Material Traceability |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-03; IFR: 2019-04-04
[6 empty] | Issue Actual | IFR: 2019-04-03; IFR: 2019-04-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01236; IFR: TPSK-LSPA1-T-QM-01236
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0014 | Job Construction Specification For Bolted Flange Joint Assembly Management During Construction Precommissioning And Commissioning |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-10; IFR: 2019-04-11
[6 empty] | Issue Actual | IFR: 2019-04-10; IFR: 2019-04-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01306; IFR: TPSK-LSPA1-T-QM-01306
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0015 | Job Construction Specification For Instrument Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-25; IFR: 2019-06-25
[6 empty] | Issue Actual | IFR: 2019-06-25; IFR: 2019-06-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01973; IFR: TPSK-LSPA1-T-QM-01973
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| QM | OL1-2Q92-0017 | Job Construction Specification For Material Receiving And Warehousting |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-07; IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01597; IFR: TPSK-LSPA1-T-QM-01597
[6 empty] | Return Date | IFR: 2019-06-20
Owner Cmmt* | bar: IFR
| QM | OL1-2Q92-0018 | Job Construction Specification For Static Equipment and Trays-Internals Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-03
[6 empty] | Issue Actual | IFR: 2019-04-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01237; IFR: TPSK-LSPA1-T-QM-01237
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0019 | Job Construction Specification For Machinery And Air Coolers Installation |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-10; IFR: 2019-04-11
[6 empty] | Issue Actual | IFR: 2019-04-10; IFR: 2019-04-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01305; IFR: TPSK-LSPA1-T-QM-01305
Return Date
Owner Cmmt*
Category Code: Q93 Policy , Guidelines,& Memo
Category Code: Q94 Forms & Templates
Category Code: Q95 Progress/Status Reports
Category Code: Q96 Quality Audit Reports
Category Code: Q97 Non-Conformance Record
Category Code: Q98 Addition Vendors/Subcontractors Assessment and Prequalification Report
Category Code: R01 Process Specification (PE)
Category Code: R02 Civil Specification (CV)
| CV | OL1-2R02-0001 | JOB DES.SPEC.FOR UNDERG.SYSTEM |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: IMP; IBD: IMP
[6 empty] | Rev. | IFR: A; IFR: A; IBD: 0; IBD: 0
[6 empty] | Issue Plan | IFR: 2018-09-24; IBD: 2019-03-16
Revised Plan
[6 empty] | Issue Actual | IFR: 2018-09-25; IFR: 2018-09-27; IBD: 2019-03-06; IBD: 2019-03-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00087; IFR: TPSK-LSPA1-T-CV-00087; IBD: TPSK-LSPA1-T-CV-00994; IBD: TPSK-LSPA1-T-CV-00994
[6 empty] | Return Date | IFR: 2018-11-02; IFR: 2018-11-02; IBD: 2019-03-15; IBD: 2019-03-15
Owner Cmmt* | bar: IFR to IBD
| CV | OL1-2R02-0002 | JOB DESIGN SPECIFICATION FOR GEOTECHNICAL RECOMMENDATIONS |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: IMP
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-02-15; IBD: 2019-10-08
[6 empty] | Revised Plan | IBD: 2019-10-08
[6 empty] | Issue Actual | IFR: 2019-05-02; IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01598; IFR: TPSK-LSPA1-T-CV-01598
[6 empty] | Return Date | IFR: 2019-05-31; IFR: 2019-05-31
Owner Cmmt* | bar: IFR to IFR
| CV | OL1-2R02-0004 | JSD FOR FOUNDATION & STRUCT. |  | Class 2 | Purpose** | IFR | IFR | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | IFR: 2018-09-25; IBD: 2019-01-31
Revised Plan
[6 empty] | Issue Actual | 2018-09-25 | 2018-09-27 | 2019-02-19 | 2019-02-19 | 2019-07-04 | 2019-07-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00087 | TPSK-LSPA1-T-CV-00087 | TPSK-LSPA1-T-CV-00887 | TPSK-LSPA1-T-CV-00887 | TPSK-LSPA1-T-CV-02066 | TPSK-LSPA1-T-CV-02066
[6 empty] | Return Date | IFR: 2018-11-02; IFR: 2018-11-02; IBD: 2019-03-18; IBD: 2019-03-18
Owner Cmmt* | bar: IFR to IBD
| CV | OL1-2R02-0005 | AMENDMENT - CV-012 - BUILDING DESIGN AND CONSTRUCTION |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: IMP
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2018-10-10; IBD: 2019-01-15
[6 empty] | Revised Plan | IBD: 2019-08-20
[6 empty] | Issue Actual | IFR: 2018-10-11; IFR: 2018-10-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00158; IFR: TPSK-LSPA1-T-CV-00158
[6 empty] | Return Date | IFR: 2019-03-18; IFR: 2019-03-18
Owner Cmmt* | bar: IFR to IFR
| CV | OL1-2R02-0006 | JOB SUPPLY SPEC.FOR STEEL STRUCT. |  | Class 2 | Purpose** | IFR: IFQ; IFR: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-16; IFR: 2019-10-16
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2R02-0011 | Geotechnical Factual Report |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: IMP
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-02-15; IBD: 2019-10-08
[6 empty] | Revised Plan | IBD: 2019-10-08
[6 empty] | Issue Actual | IFR: 2019-05-02; IFR: 2019-05-03
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-CV-01549; IFR: TPSK-LPSA1-T-CV-01549
[6 empty] | Return Date | IFR: 2019-05-27; IFR: 2019-05-27
Owner Cmmt* | bar: IFR to IFR
| CV | OL1-2R02-0012 | Additional Ground Investigation Technical Specification |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: IMP
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2018-10-08; IBD: 2019-12-17
[6 empty] | Revised Plan | IBD: 2019-12-17
[6 empty] | Issue Actual | IFR: 2019-05-31; IFR: 2019-06-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01788; IFR: TPSK-LSPA1-T-CV-01788
[6 empty] | Return Date | IFR: 2019-06-20
Owner Cmmt* | bar: IFR
| CV | OL1-2R02-0101 | Technical Specification For Piles |  | Class 2 | Purpose** | IFR: IFR; IFR: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-03-15; IFR: 2019-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2R02-0102 | Technical Specification for Civil Works |  | Class 2 | Purpose** | IFR: IFQ; IFR: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-06-14; IFR: 2019-07-31
[6 empty] | Revised Plan | IFR: 2019-09-13
[6 empty] | Issue Actual | IFR: 2019-05-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01666
[6 empty] | Return Date | IFR: 2019-06-08
Owner Cmmt* | bar: IFR
| CV | OL1-2R02-0103 | Technical Specification for Precast Concrete Pipe-Racks |  | Class 2 | Purpose** | IFR: IFQ; IFR: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-04-30; IFR: 2019-08-31
[6 empty] | Revised Plan | IFR: 2019-08-31
[6 empty] | Issue Actual | IFR: 2019-05-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01666
[6 empty] | Return Date | IFR: 2019-06-08
Owner Cmmt* | bar: IFR
| CV | OL1-2R02-0104 | Technical Specification For Steel Structures Erection |  | Class 2 | Purpose** | IFR: IFQ; IFR: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-05-16; IFR: 2019-10-16
[6 empty] | Revised Plan | IFR: 2019-10-16
[6 empty] | Issue Actual | IFR: 2019-05-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01666
[6 empty] | Return Date | IFR: 2019-06-08
Owner Cmmt* | bar: IFR
| CV | OL1-2R02-5001 | Technical Specification For Buildings |  | Class 2 | Purpose** | IFR: IFQ; IFR: IFQ; IBD: IFP
Rev. | bar: IFR to IFR
[6 empty] | Issue Plan | IFR: 2019-03-05; IBD: 2019-07-05
[6 empty] | Revised Plan | IBD: 2019-10-07
[6 empty] | Issue Actual | IFR: 2019-06-26; IFR: 2019-06-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01997; IFR: TPSK-LSPA1-T-CV-01997
Return Date
Owner Cmmt*
Category Code: R03 Mechanical Specification (ME)
| ME | OL1-2R03-0001 | WELDING AND NDE FOR PRESSURE VESSELS |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: IMP; IBD: IMP
[6 empty] | Rev. | IFR: A; IFR: A; IBD: 0; IBD: 0
[6 empty] | Issue Plan | IFR: 2019-04-06; IBD: 2019-05-06
Revised Plan
[6 empty] | Issue Actual | IFR: 2018-08-27; IFR: 2018-08-29; IBD: 2019-02-25; IBD: 2019-02-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00029; IFR: TPSK-LSPA1-T-ME-00029; IBD: TPSK-LSPA1-T-ME-00921; IBD: TPSK-LSPA1-T-ME-00921
[6 empty] | Return Date | IFR: 2018-09-19; IFR: 2018-09-19; IBD: 2019-03-15; IBD: 2019-03-15
Owner Cmmt* | bar: IFR to IBD
| ME | OL1-2R03-0002 | JOB SUPPLY SPECIFICATION FOR MATERIAL IN SOUR SERVICE |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: IMP; IBD: IMP
[6 empty] | Rev. | IFR: A; IFR: A; IBD: 0; IBD: 0
[6 empty] | Issue Plan | IFR: 2019-04-06; IBD: 2019-05-06
Revised Plan
[6 empty] | Issue Actual | IFR: 2018-08-27; IFR: 2018-08-29; IBD: 2019-02-25; IBD: 2019-02-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00029; IFR: TPSK-LSPA1-T-ME-00029; IBD: TPSK-LSPA1-T-ME-00921; IBD: TPSK-LSPA1-T-ME-00921
[6 empty] | Return Date | IFR: 2018-09-19; IFR: 2018-09-19; IBD: 2019-03-15; IBD: 2019-03-15
Owner Cmmt* | bar: IFR to IBD
| ME | OL1-2R03-0003 | JOB SUPPLY SPECIFICATION FOR POSITIVE MATERIAL IDENTIFICATION ON EQUIPMENT & PIPING |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: IMP; IBD: IMP
[6 empty] | Rev. | IFR: A; IFR: A; IBD: 0; IBD: 0
[6 empty] | Issue Plan | IFR: 2019-04-06; IBD: 2019-05-06
Revised Plan
[6 empty] | Issue Actual | IFR: 2018-08-27; IFR: 2018-08-29; IBD: 2019-02-25; IBD: 2019-02-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00029; IFR: TPSK-LSPA1-T-ME-00029; IBD: TPSK-LSPA1-T-ME-00921; IBD: TPSK-LSPA1-T-ME-00921
[6 empty] | Return Date | IFR: 2018-09-19; IFR: 2018-09-19; IBD: 2019-03-15; IBD: 2019-03-15
Owner Cmmt* | bar: IFR to IBD
| ME | OL1-2R03-0004 | WELDING AND NDE FOR TANKS STORAGE |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: IMP; IBD: IMP
[6 empty] | Rev. | IFR: A; IFR: A; IBD: 0; IBD: 0
[6 empty] | Issue Plan | IFR: 2019-04-06; IBD: 2019-05-06
Revised Plan
[6 empty] | Issue Actual | IFR: 2018-08-27; IFR: 2018-08-29; IBD: 2019-02-25; IBD: 2019-02-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00029; IFR: TPSK-LSPA1-T-ME-00029; IBD: TPSK-LSPA1-T-ME-00921; IBD: TPSK-LSPA1-T-ME-00921
[6 empty] | Return Date | IFR: 2018-09-19; IFR: 2018-09-19; IBD: 2019-03-15; IBD: 2019-03-15
Owner Cmmt* | bar: IFR to IBD
| ME | OL1-2R03-0005 | ME-005 Double Jacket Pipe Heat Exchangers for 36M and 132U Furnace |  | Class 2 | Purpose** | IFR: IMP; IFR: IMP
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-23
[6 empty] | Issue Actual | IFR: 2018-10-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00212; IFR: TPSK-LSPA1-T-ME-00212
Return Date
Owner Cmmt*
| ME | OL1-2R03-0006 | PLATE HEAT EXCHANGER |  | Class 2 | Purpose** | IFR: IFR; IFR: IMP; IBD: IMP
[6 empty] | Rev. | IFR: 0; IBD: 0
[6 empty] | Issue Plan | IFR: 2018-09-10; IFR: 2018-09-24
Revised Plan
[6 empty] | Issue Actual | IFR: 2018-09-12; IBD: 2018-09-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00042; IBD: TPSK-LSPA1-T-ME-00042
Return Date
Owner Cmmt*
| ME | OL1-2R03-0007 | Job Specification for AXENS Standard Material Specifications - Carbon Steels For Pressure Service |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-21; IFR: 2019-02-22
[6 empty] | Issue Actual | IFR: 2019-02-21; IFR: 2019-02-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00909; IFR: TPSK-LSPA1-T-ME-00909
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15
Owner Cmmt* | bar: IFR to IFR
| ME | OL1-2R03-0008 | Job Specification For Axens Standard Material Specifications - Low Alloyed Steels For Pressure Vessels |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-21; IFR: 2019-02-22
[6 empty] | Issue Actual | IFR: 2019-02-21; IFR: 2019-02-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00909; IFR: TPSK-LSPA1-T-ME-00909
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15
Owner Cmmt* | bar: IFR to IFR
| ME | OL1-2R03-0009 | Job Specification For Axens Standard Material Specifications For Wet H2S Service |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-21; IFR: 2019-02-22
[6 empty] | Issue Actual | IFR: 2019-02-21; IFR: 2019-02-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00909; IFR: TPSK-LSPA1-T-ME-00909
[6 empty] | Return Date | IFR: 2019-03-15; IFR: 2019-03-15
Owner Cmmt* | bar: IFR to IFR
| ME | OL1-2R03-0010 | ME-010 Centrifugal Pump |  | Class 2 | Purpose** | IFR: IMP; IFR: IFR; IBD: IFR; IBD: IMP
[6 empty] | Rev. | IFR: 0; IFR: A; IBD: A; IBD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-24; IBD: 2018-09-25; IBD: 2019-01-22
[6 empty] | Issue Actual | IFR: 2018-09-24; IBD: 2018-09-25; IBD: 2019-01-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00693; IFR: TPSK-LSPA1-T-ME-00078; IBD: TPSK-LSPA1-T-ME-00078; IBD: TPSK-LSPA1-T-ME-00693
[6 empty] | Return Date | IFR: 2019-02-14; IFR: 2018-10-12; IBD: 2018-10-12; IBD: 2019-02-14
Owner Cmmt* | bar: IFR to IBD
| ME | OL1-2R03-0011 | ME-011 RECIPROCATING PUMP |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-24; IFR: 2019-04-25
[6 empty] | Issue Actual | IFR: 2019-04-24; IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01459; IFR: TPSK-LSPA1-T-ME-01459
[6 empty] | Return Date | IFR: 2019-05-24; IFR: 2019-05-24
Owner Cmmt* | bar: IFR to IFR
| ME | OL1-2R03-0013 | ME-013 Diesel Engine |  | Class 2 | Purpose** | IFR: IFR; IFR: IMP; IBD: IFR; IBD: IMP
[6 empty] | Rev. | IFR: A; IFR: 0; IBD: A; IBD: 0
Issue Plan
[6 empty] | Revised Plan | IBD: 2018-10-18; IBD: 2019-01-23
[6 empty] | Issue Actual | IBD: 2018-10-18; IBD: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00196; IFR: TPSK-LSPA1-T-ME-00668; IBD: TPSK-LSPA1-T-ME-00196; IBD: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | IFR: 2018-11-02; IFR: 2019-04-25; IBD: 2018-11-02; IBD: 2019-04-25
Owner Cmmt* | bar: IFR to IBD
| ME | OL1-2R03-0014 | ME-014 Centrifugal Compressor |  | Class 2 | Purpose** | IFR: IMP; IFR: IFR; IBD: IFR; IBD: IMP
[6 empty] | Rev. | IFR: 0; IFR: A; IBD: A; IBD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-18; IBD: 2018-10-19; IBD: 2019-01-23
[6 empty] | Issue Actual | IFR: 2018-09-18; IBD: 2018-10-19; IBD: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00668; IFR: TPSK-LSPA1-T-ME-00065; IBD: TPSK-LSPA1-T-ME-00065; IBD: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | IFR: 2019-04-25; IFR: 2018-10-10; IBD: 2018-10-10; IBD: 2019-04-25
Owner Cmmt* | bar: IFR to IBD
| ME | OL1-2R03-0016 | ME-016 Centrifugal Compressor For PA-IA Servise |  | Class 2 | Purpose** | IFR: IMP; IFR: IFR; IBD: IFR; IBD: IMP
[6 empty] | Rev. | IFR: 0; IFR: A; IBD: A; IBD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-12; IBD: 2018-10-15; IBD: 2019-01-23
[6 empty] | Issue Actual | IFR: 2018-10-12; IBD: 2018-10-15; IBD: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00668; IFR: TPSK-LSPA1-T-ME-00164; IBD: TPSK-LSPA1-T-ME-00164; IBD: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | IFR: 2019-04-25; IFR: 2018-11-07; IBD: 2018-11-07; IBD: 2019-04-25
Owner Cmmt* | bar: IFR to IBD
| ME | OL1-2R03-0017 | ME-017 Root Blower |  | Class 2 | Purpose** | IFR: IMP; IFR: IMP
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-19
[6 empty] | Issue Actual | IFR: 2018-11-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00334; IFR: TPSK-LSPA1-T-ME-00334
Return Date
Owner Cmmt*
| ME | OL1-2R03-0018 | ME-018 General Purpose Steam Turbines |  | Class 2 | Purpose** | IFR: IMP; IFR: IFR; IBD: IFR; IBD: IMP
[6 empty] | Rev. | IFR: 0; IFR: A; IBD: A; IBD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-24; IBD: 2018-09-25; IBD: 2019-01-23
[6 empty] | Issue Actual | IFR: 2018-09-24; IBD: 2018-09-25; IBD: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00668; IFR: TPSK-LSPA1-T-ME-00078; IBD: TPSK-LSPA1-T-ME-00078; IBD: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | IFR: 2019-04-25; IFR: 2018-10-12; IBD: 2018-10-12; IBD: 2019-04-25
Owner Cmmt* | bar: IFR to IBD
| ME | OL1-2R03-0019 | ME-019 Lube Oil Unit And Seal Oil System |  | Class 2 | Purpose** | IFR: IMP; IFR: IFR; IBD: IFR; IBD: IMP
[6 empty] | Rev. | IFR: 0; IFR: A; IBD: A; IBD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-18; IBD: 2018-10-19; IBD: 2019-01-23
[6 empty] | Issue Actual | IFR: 2018-09-18; IBD: 2018-10-19; IBD: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00668; IFR: TPSK-LSPA1-T-ME-00065; IBD: TPSK-LSPA1-T-ME-00065; IBD: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | IFR: 2019-04-25; IFR: 2018-10-10; IBD: 2018-10-10; IBD: 2019-04-25
Owner Cmmt* | bar: IFR to IBD
| ME | OL1-2R03-0020 | ME-020 Special Purpose Steam Tturbines |  | Class 2 | Purpose** | IFR: IMP; IFR: IFR; IBD: IFR; IBD: IMP
[6 empty] | Rev. | IFR: 0; IFR: A; IBD: A; IBD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-24; IBD: 2018-09-25; IBD: 2019-01-23
[6 empty] | Issue Actual | IFR: 2018-09-24; IBD: 2018-09-25; IBD: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00668; IFR: TPSK-LSPA1-T-ME-00078; IBD: TPSK-LSPA1-T-ME-00078; IBD: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | IFR: 2019-04-25; IFR: 2018-10-12; IBD: 2018-10-12; IBD: 2019-04-25
Owner Cmmt* | bar: IFR to IBD
| ME | OL1-2R03-0021 | ME-021 Flare System |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR; IBD: IMP; IBD: IMP
[6 empty] | Rev. | IFR: A; IFR: A; IBD: 0; IBD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-06; IBD: 2019-06-25; IBD: 2019-06-25
[6 empty] | Issue Actual | IFR: 2018-12-06; IBD: 2019-06-25; IBD: 2019-06-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00429; IFR: TPSK-LSPA1-T-ME-00429; IBD: TPSK-LSPA1-T-ME-01969; IBD: TPSK-LSPA1-T-ME-01969
[6 empty] | Return Date | IFR: 2018-12-26; IFR: 2018-12-26; IBD: 2019-07-08; IBD: 2019-07-08
Owner Cmmt* | bar: IFR to IBD
| ME | OL1-2R03-0022 | ME-022 Special Purpose Gear |  | Class 2 | Purpose** | IFR: IMP; IFR: IFR; IBD: IFR; IBD: IMP
[6 empty] | Rev. | IFR: 0; IFR: A; IBD: A; IBD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-12; IBD: 2018-10-15; IBD: 2019-01-23
[6 empty] | Issue Actual | IFR: 2018-10-12; IBD: 2018-10-15; IBD: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00668; IFR: TPSK-LSPA1-T-ME-00166; IBD: TPSK-LSPA1-T-ME-00166; IBD: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | IFR: 2019-04-25; IFR: 2018-11-07; IBD: 2018-11-07; IBD: 2019-04-25
Owner Cmmt* | bar: IFR to IBD
| ME | OL1-2R03-0024 | ME-024 Elevator For 36M and 132U Furnace |  | Class 2 | Purpose** | IFR: IMP; IFR: IMP
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-20
[6 empty] | Issue Actual | IFR: 2018-12-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00537; IFR: TPSK-LSPA1-T-ME-00537
Return Date
Owner Cmmt*
| ME | OL1-2R03-0028 | ME-028 Mechanical Seal |  | Class 2 | Purpose** | IFR: IMP; IFR: IMP
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-17; IFR: 2018-09-18
[6 empty] | Issue Actual | IFR: 2018-09-17; IFR: 2018-09-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00057; IFR: TPSK-LSPA1-T-ME-00057
Return Date
Owner Cmmt*
| ME | OL1-2R03-0029 | ME-029 Centrifugal Blower for 36M and 132U Furnace |  | Class 2 | Purpose** | IFR: IMP; IFR: IMP
[6 empty] | Rev. | IFR: 0; IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-17; IFR: 2018-10-17
[6 empty] | Issue Actual | IFR: 2018-10-17; IFR: 2018-10-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00185; IFR: TPSK-LSPA1-T-ME-00185
[6 empty] | Return Date | IFR: 2018-11-05; IFR: 2018-11-05
Owner Cmmt*
| MP | OL1-2R03-0030 | Job Sprcification For Supply And Fabrication Of Grade 91 Alloy Steel Piping |  | Class 2 | Purpose** | IFR: IFR; IFR: IFR
Rev. | bar: IFR to IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-24; IFR: 2019-04-25
[6 empty] | Issue Actual | IFR: 2019-04-24; IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01465; IFR: TPSK-LSPA1-T-MP-01465
[6 empty] | Return Date | IFR: 2019-05-17; IFR: 2019-05-17
Owner Cmmt* | bar: IFR to IFR
| ME | OL1-2R03-0047 | ME-047 Dry Screw Compressor for Hydrocarbon Services |  | Class 2 | Purpose** | IFR: IMP; IFR: IFR; IBD: IFR; IBD: IMP
[6 empty] | Rev. | IFR: 0; IFR: A; IBD: A; IBD: 0
Issue Plan
[6 empty] | Revised Plan | IBD: 2018-12-06; IBD: 2019-01-17
[6 empty] | Issue Actual | IBD: 2018-12-06; IBD: 2019-01-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00666; IFR: TPSK-LSPA1-T-ME-00429; IBD: TPSK-LSPA1-T-ME-00429; IBD: TPSK-LSPA1-T-ME-00666
[6 empty] | Return Date | IFR: 2019-02-04; IFR: 2018-12-26; IBD: 2018-12-26; IBD: 2019-02-04
Owner Cmmt* | bar: IFR to IBD
| ME | OL1-2R03-0050 | JOB SPEC. FOR DESIGN OF PRESSURE & ATMOSPHERIC EQUIPMENT |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A | B | B | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | IFR: 2018-08-10; IBD: 2018-09-20
Revised Plan
[6 empty] | Issue Actual | 2018-08-10 | 2018-08-13 | 2018-09-25 | 2018-09-27 |  | 2018-10-31 | 2019-02-19 | 2019-02-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00017 | TPSK-LSPA1-T-ME-00017 | TPSK-LSPA1-T-ME-00084 | TPSK-LSPA1-T-ME-00084 | TPSK-LSPA1-T-ME-00245 | TPSK-LSPA1-T-ME-00245 | TPSK-LSPA1-T-ME-00888 | TPSK-LSPA1-T-ME-00888
[6 empty] | Return Date | 2018-08-27 | 2018-08-27 | 2018-10-24 | 2018-10-24 | 2018-11-26 | 2018-11-26 | 2019-03-15 | 2019-03-15
Owner Cmmt* | bar: 2018-08-27 to 2018-10-24; 2019-03-15 to 2019-03-15
| ME | OL1-2R03-0051 | JOB SPEC. FOR SUPPLY OF PRESSURE VESSELS |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A | B | B | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2018-08-27: 2018-09-10; 2018-11-26: 2018-09-22
Revised Plan
[6 empty] | Issue Actual | 2018-08-13 | 2018-08-13 | 2018-09-25 | 2018-09-27 |  | 2018-10-31 | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00021 | TPSK-LSPA1-T-ME-00021 | TPSK-LSPA1-T-ME-00084 | TPSK-LSPA1-T-ME-00084 | TPSK-LSPA1-T-ME-00249 | TPSK-LSPA1-T-ME-00249 | TPSK-LSPA1-T-ME-01350 | TPSK-LSPA1-T-ME-01350
[6 empty] | Return Date | 2018-08-27 | 2018-08-27 | 2018-10-24 | 2018-10-24 | 2018-11-27 | 2018-11-27 | 2019-05-13 | 2019-05-13
Owner Cmmt* | bar: 2018-08-27 to 2018-10-24; 2019-05-13 to 2019-05-13
| ME | OL1-2R03-0052 | JOB SPEC. FOR SUPPLY OF COLUMN INTERNALS |  | Class 2 | Purpose** | 2018-08-27: IFR; 2018-08-27: IFR; 2018-10-24: IMP; 2018-10-24: IMP
[6 empty] | Rev. | 2018-08-27: A; 2018-08-27: A; 2018-10-24: 0; 2018-10-24: 0
[6 empty] | Issue Plan | 2018-08-27: 2018-08-10; 2018-10-24: 2018-09-23
Revised Plan
[6 empty] | Issue Actual | 2018-08-27: 2018-08-10; 2018-08-27: 2018-08-13; 2018-10-24: 2018-09-24; 2018-10-24: 2018-09-25
[6 empty] | Transmittal no. | 2018-08-27: TPSK-LSPA1-T-ME-00017; 2018-08-27: TPSK-LSPA1-T-ME-00017; 2018-10-24: TPSK-LSPA1-T-ME-00081; 2018-10-24: TPSK-LSPA1-T-ME-00081
[6 empty] | Return Date | 2018-08-27: 2018-08-27; 2018-08-27: 2018-08-27; 2018-10-24: 2018-10-24; 2018-10-24: 2018-10-24
Owner Cmmt* | bar: 2018-08-27 to 2018-08-27
| ME | OL1-2R03-0053 | JOB SPEC. FOR SUPPLY OF EQUIPMENT LADDERS AND PLATFORMS |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IMP
[6 empty] | Rev. | 2018-08-27: A; 2018-08-27: A; 2018-10-24: 0; 2018-10-24: 0
[6 empty] | Issue Plan | 2018-08-27: 2018-08-10; 2018-11-27: 2018-09-25
Revised Plan
[6 empty] | Issue Actual | 2018-08-27: 2018-08-10; 2018-08-27: 2018-08-13; 2018-10-24: 2018-09-24; 2018-10-24: 2018-09-25
[6 empty] | Transmittal no. | 2018-08-27: TPSK-LSPA1-T-ME-00017; 2018-08-27: TPSK-LSPA1-T-ME-00017; 2018-10-24: TPSK-LSPA1-T-ME-00081; 2018-10-24: TPSK-LSPA1-T-ME-00081
[6 empty] | Return Date | 2018-08-27: 2018-08-27; 2018-08-27: 2018-08-27; 2018-10-24: 2018-10-24; 2018-10-24: 2018-10-24
Owner Cmmt* | bar: 2018-08-27 to 2018-08-27
| ME | OL1-2R03-0054 | CONST.STANDARDS FOR PRESS. EQUIP. |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IFC
Rev. | bar: 2018-08-27 to 2018-10-24
[6 empty] | Issue Plan | 2018-08-27: 2018-08-10; 2018-11-27: 2018-10-19
Revised Plan
[6 empty] | Issue Actual | 2018-08-27: 2018-08-10; 2018-08-27: 2018-08-13; 2018-10-24: 2018-09-25; 2018-10-24: 2018-09-27
[6 empty] | Transmittal no. | 2018-08-27: TPSK-LSPA1-T-ME-00018; 2018-08-27: TPSK-LSPA1-T-ME-00018; 2018-10-24: TPSK-LSPA1-T-ME-00084; 2018-10-24: TPSK-LSPA1-T-ME-00084
[6 empty] | Return Date | 2018-08-27: 2018-08-27; 2018-08-27: 2018-08-27; 2018-10-24: 2018-10-24; 2018-10-24: 2018-10-24
Owner Cmmt* | bar: 2018-08-27 to 2018-10-24
| ME | OL1-2R03-0055 | CONST.STANDARDS FOR LADDERS AND PLATFORMS ATTACHED TO PRESSURE EQUIPMENT |  | Class 2 | Purpose** | 2018-08-27: IFR; 2018-08-27: IFC
Rev. | bar: 2018-08-27
[6 empty] | Issue Plan | 2018-08-27: 2018-10-23; 2018-08-27: 2018-12-20
Revised Plan
[6 empty] | Issue Actual | 2018-08-27: 2018-08-29
[6 empty] | Transmittal no. | 2018-08-27: TPSK-LSPA1-T-ME-00027
[6 empty] | Return Date | 2018-08-27: 2018-09-18
Owner Cmmt* | bar: 2018-08-27
| ME | OL1-2R03-0102 | MARKING FOR VESSEL & HEAT EXCHANGER |  | Class 2 | Purpose** | 2018-08-27: IFR; 2018-08-27: IMP; 2018-10-24: IMP
[6 empty] | Rev. | 2018-08-27: 0; 2018-10-24: 0
[6 empty] | Issue Plan | 2018-08-27: 2018-09-10; 2018-08-27: 2018-09-22
Revised Plan
[6 empty] | Issue Actual | 2018-08-27: 2018-09-12; 2018-10-24: 2018-09-13
[6 empty] | Transmittal no. | 2018-08-27: TPSK-LSPA1-T-ME-00042; 2018-10-24: TPSK-LSPA1-T-ME-00042
Return Date
Owner Cmmt*
| ME | OL1-2R03-0104 | ME-008 Cooling Water |  | Class 2 | Purpose** | 2018-08-27: IFQ; 2018-08-27: IFQ
Rev. | bar: 2018-08-27 to 2018-08-27
Issue Plan
[6 empty] | Revised Plan | 2018-08-27: 2018-11-06
[6 empty] | Issue Actual | 2018-08-27: 2018-11-06
[6 empty] | Transmittal no. | 2018-08-27: TPSK-LSPA1-T-ME-00276; 2018-08-27: TPSK-LSPA1-T-ME-00276
[6 empty] | Return Date | 2018-08-27: 2019-02-15; 2018-08-27: 2019-02-15
Owner Cmmt*
| ME | OL1-2R03-0500 | ME-050 Centrifugal Pump - Non API |  | Class 2 | Purpose** | 2018-08-27: IMP; 2018-08-27: IFR; 2018-10-24: IFR; 2018-10-24: IMP
[6 empty] | Rev. | 2018-08-27: 0; 2018-08-27: A; 2018-10-24: A; 2018-10-24: 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-24: 2018-11-12; 2018-10-24: 2019-01-23
[6 empty] | Issue Actual | 2018-10-24: 2018-11-12; 2018-10-24: 2019-01-23
[6 empty] | Transmittal no. | 2018-08-27: TPSK-LSPA1-T-ME-00668; 2018-08-27: TPSK-LSPA1-T-ME-00308; 2018-10-24: TPSK-LSPA1-T-ME-00308; 2018-10-24: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | 2018-08-27: 2019-04-25; 2018-08-27: 2018-12-06; 2018-10-24: 2018-12-06; 2018-10-24: 2019-04-25
Owner Cmmt* | bar: 2018-08-27 to 2018-10-24
| ME | OL1-2R03-055 | Construction Standards For Ladders And Platforms Attached To Pressure Equipment |  | Class 2 | Purpose** | 2018-08-27: IFR
Rev. | bar: 2018-08-27
Issue Plan
[6 empty] | Revised Plan | 2018-08-27: 2018-08-27
[6 empty] | Issue Actual | 2018-08-27: 2018-08-27
[6 empty] | Transmittal no. | 2018-08-27: TPSK-LSPA1-T-ME-00027
[6 empty] | Return Date | 2018-08-27: 2018-09-18
Owner Cmmt* | bar: 2018-08-27
| ME | OL1-2R03-1001 | ME-001 Pressure Vessel for 36M and 132U Furnace |  | Class 2 | Purpose** | 2018-08-27: IFE; 2018-08-27: IFE
[6 empty] | Rev. | 2018-08-27: 0; 2018-08-27: 0
Issue Plan
[6 empty] | Revised Plan | 2018-08-27: 2018-11-07
[6 empty] | Issue Actual | 2018-08-27: 2018-11-07
[6 empty] | Transmittal no. | 2018-08-27: TPSK-LSPA1-T-ME-00262; 2018-08-27: TPSK-LSPA1-T-ME-00262
Return Date
Owner Cmmt*
| ME | OL1-2R03-1004 | ME-004 Shell and Tube Heat Exchangers for 36M and 132U Furnace |  | Class 2 | Purpose** | 2018-08-27: IFI; 2018-08-27: IFI
[6 empty] | Rev. | 2018-08-27: 0; 2018-08-27: 0
Issue Plan
[6 empty] | Revised Plan | 2018-08-27: 2018-10-24
[6 empty] | Issue Actual | 2018-08-27: 2018-10-24
[6 empty] | Transmittal no. | 2018-08-27: TPSK-LSPA1-T-ME-00221; 2018-08-27: TPSK-LSPA1-T-ME-00221
Return Date
Owner Cmmt*
| ME | OL1-2R03-1005 | Job Specification for Axens General Statement about Selection of Materials for Equipment and Piping |  | Class 2 | Purpose** | 2018-08-27: IFR; 2018-08-27: IFR
Rev. | bar: 2018-08-27 to 2018-08-27
Issue Plan
[6 empty] | Revised Plan | 2018-08-27: 2019-04-26; 2018-08-27: 2019-04-29
[6 empty] | Issue Actual | 2018-08-27: 2019-04-26; 2018-08-27: 2019-04-29
[6 empty] | Transmittal no. | 2018-08-27: TPSK-LSPA1-T-ME-01505; 2018-08-27: TPSK-LSPA1-T-ME-01505
[6 empty] | Return Date | 2018-08-27: 2019-05-24; 2018-08-27: 2019-05-24
Owner Cmmt* | bar: 2018-08-27 to 2018-08-27
| ME | OL1-2R03-1006 | Job Specification for Air Liquide-Design Rules- Codes and Standards for Columns and Column Internals |  | Class 2 | Purpose** | 2018-08-27: IFR; 2018-08-27: IFR
Rev. | bar: 2018-08-27 to 2018-08-27
Issue Plan
[6 empty] | Revised Plan | 2018-08-27: 2019-04-26; 2018-08-27: 2019-04-29
[6 empty] | Issue Actual | 2018-08-27: 2019-04-26; 2018-08-27: 2019-04-29
[6 empty] | Transmittal no. | 2018-08-27: TPSK-LSPA1-T-ME-01504; 2018-08-27: TPSK-LSPA1-T-ME-01504
[6 empty] | Return Date | 2018-08-27: 2019-05-24; 2018-08-27: 2019-05-24
Owner Cmmt* | bar: 2018-08-27 to 2018-08-27
Category Code: R04 Piping Specification (PIP)
| MP | OL1-2R04-0001 | PIPING CLASSES SUMMARY & PIPING CLASSES |  | Class 2 | Purpose** | IFR | IFR | IMP | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0 | 1
[6 empty] | Issue Plan | 2018-08-27: 2018-12-19; 2018-10-24: 2020-10-15
[6 empty] | Revised Plan | 2018-10-24: 2020-10-15
[6 empty] | Issue Actual | 2018-08-27: 2018-12-27; 2018-10-24: 2019-04-05; 2018-10-24: 2019-04-08; 2018-11-27: 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00562 | TPSK-LSPA1-T-MP-00562 | 1262-TPSK-LSPA1-T-MP-01262 | 1262-TPSK-LSPA1-T-MP-01262 | TPSK-LSPA1-T-MP-02390
[6 empty] | Return Date | 2018-08-27: 2019-01-17; 2018-08-27: 2019-01-17
Owner Cmmt* | bar: 2018-08-27 to 2018-08-27
| MP | OL1-2R04-0002 | JOB DES.SPEC.FOR PIPING AND STD |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IFC
Rev. | bar: 2018-08-27 to 2018-10-24
[6 empty] | Issue Plan | 2018-08-27: 2018-11-13; 2018-11-27: 2019-02-01
Revised Plan
[6 empty] | Issue Actual | 2018-08-27: 2018-08-08; 2018-10-24: 2018-08-08; 2018-10-24: 2018-11-16
[6 empty] | Transmittal no. | 2018-08-27: TPSK-LSPA1-T-MP-00012; 2018-08-27: TPSK-LSPA1-T-MP-00012; 2018-10-24: TPSK-LSPA1-T-MP-00012; 2018-10-24: TPSK-LSPA1-T-MP-00012
[6 empty] | Return Date | 2018-08-27: 2018-12-07; 2018-08-27: 2018-09-26; 2018-10-24: 2018-09-26; 2018-10-24: 2018-12-07
Owner Cmmt* | bar: 2018-08-27 to 2018-10-24
| MP | OL1-2R04-0003 | JOB DESIGN SPECIFICATION FOR THERMAL INSULATION (HOT SERVICE) |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IFR | IMP
[6 empty] | Rev. | B | A | A | B | C
[6 empty] | Issue Plan | 2018-08-27: 2019-04-29; 2018-11-27: 2019-08-27
[6 empty] | Revised Plan | 2018-11-27: 2019-08-27
[6 empty] | Issue Actual | 2018-08-27: 2018-08-22; 2018-10-24: 2018-08-23; 2018-10-24: 2018-12-27; 2018-11-27: 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00562 | TPSK-LSPA1-T-MP-00024 | TPSK-LSPA1-T-MP-00024 | TPSK-LSPA1-T-MP-00562 | TPSK-LSPA1-T-MP-02391
[6 empty] | Return Date | 2018-08-27: 2019-01-17; 2018-08-27: 2018-09-12; 2018-10-24: 2018-09-12; 2018-10-24: 2019-01-17
Owner Cmmt* | bar: 2018-08-27 to 2018-10-24
| MP | OL1-2R04-0004 | JOB DESIGN SPECIFICATION FOR THERMAL INSULATION (COLD SERVICE) |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IFR | IFR | IFR | IMP
[6 empty] | Rev. | B | A | A | B | C | C | D
[6 empty] | Rev.: Issue Plan; B: 2019-04-29 | 2019-08-27
[6 empty] | Rev.: Revised Plan | 2019-08-27
[6 empty] | Issue Actual |  | 2018-08-22 | 2018-08-23 | 2018-12-27 | 2019-05-15 | 2019-05-16 | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00562 | TPSK-LSPA1-T-MP-00024 | TPSK-LSPA1-T-MP-00024 | TPSK-LSPA1-T-MP-00562 | TPSK-LSPA1-T-MP-01665 | TPSK-LSPA1-T-MP-01665 | TPSK-LSPA1-T-MP-02391
[6 empty] | Return Date | 2019-01-17 | 2018-09-12 | 2018-09-12 | 2019-01-17 | 2019-05-27 | 2019-05-27
[6 empty] | Owner Cmmt* | R2 | A4 | A4 | R2 | R1 | R1
| MP | OL1-2R04-0005 | JOB DESIGN SPECIFICATION FOR PAINTING |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IMP | IMP | IMP
[6 empty] | Rev. | B | A | A | B | 0 | 0 | 1
[6 empty] | Issue Plan | 2019-04-29 |  |  |  | 2019-08-27
[6 empty] | Revised Plan |  |  |  |  | 2019-08-27
[6 empty] | Issue Actual |  | 2018-08-22 | 2018-08-23 | 2018-12-27 | 2019-05-17 | 2019-05-21 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00562 | TPSK-LSPA1-T-MP-00024 | TPSK-LSPA1-T-MP-00024 | TPSK-LSPA1-T-MP-00562 | TPSK-LSPA1-T-MP-01690 | TPSK-LSPA1-T-MP-01690 | TPSK-LSPA1-T-MP-02314
[6 empty] | Return Date | 2019-01-17 | 2018-09-12 | 2018-09-12 | 2019-01-17 |  | 2019-06-14 | 2019-08-13
[6 empty] | Owner Cmmt* | R2 | A4 | A4 | R2 |  | R2 | R1
| MP | OL1-2R04-0006 | JOB SUPPLY SPECIFICATION FOR PIPING MATERIAL |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IMP | IMP
[6 empty] | Rev. | B | A | A | B | 0 | 0
[6 empty] | Issue Plan | 2019-04-06 |  |  |  | 2019-05-06
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-27 | 2018-08-29 | 2018-11-20 | 2019-02-28 | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00342 | TPSK-LSPA1-T-MP-00028 | TPSK-LSPA1-T-MP-00028 | TPSK-LSPA1-T-MP-00342 | TPSK-LSPA1-T-MP-00951 | TPSK-LSPA1-T-MP-00951
[6 empty] | Return Date | 2019-01-30 | 2018-09-18 | 2018-09-18 | 2019-01-30 | 2019-04-01 | 2019-04-01
[6 empty] | Owner Cmmt* | R1 | R2 | R2 | R1 | R2 | R2
| ME | OL1-2R04-0007 | PIP-007 Marking of Piping Material for 36M and 132U Furnace |  | Class 2 | Rev.: Purpose**; B: IMP; A: IMP
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  | 2018-10-23
[6 empty] | Issue Actual |  | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00213 | TPSK-LSPA1-T-ME-00213
Return Date
Owner Cmmt*
| MP | OL1-2R04-0008 | JOB SUPPLY SPECIFICATION FOR BUTTERFLY VALVES |  | Class 2 | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-04-13 |  | 2019-05-13
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-26 | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00352 | TPSK-LSPA1-T-MP-00352 | TPSK-LSPA1-T-MP-01463 | TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-01-30 | 2019-01-30 | 2019-05-17 | 2019-05-17
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| MP | OL1-2R04-0009 | JOB SUPPLY SPECIFICATION FOR PLUG VALVES |  | Class 2 | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-04-13 |  | 2019-05-13
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-26 | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00352 | TPSK-LSPA1-T-MP-00352 | TPSK-LSPA1-T-MP-01463 | TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-01-30 | 2019-01-30 | 2019-05-17 | 2019-05-17
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| MP | OL1-2R04-0010 | JOB SUPPLY SPECIFICATION FOR BALL VALVES |  | Class 2 | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-04-13 |  | 2019-05-13
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-26 | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00352 | TPSK-LSPA1-T-MP-00352 | TPSK-LSPA1-T-MP-01463 | TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-01-30 | 2019-01-30 | 2019-05-17 | 2019-05-17
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| MP | OL1-2R04-0011 | JOB SUPPLY SPECIFICATION FOR PIPES |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IMP | IMP
[6 empty] | Rev. | B | A | A | B | 0 | 0
[6 empty] | Issue Plan | 2019-04-06 |  |  |  | 2019-05-06
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-27 | 2018-08-29 | 2018-11-20 | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00342 | TPSK-LSPA1-T-MP-00028 | TPSK-LSPA1-T-MP-00028 | TPSK-LSPA1-T-MP-00342 | TPSK-LSPA1-T-MP-01463 | TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-01-30 | 2018-09-18 | 2018-09-18 | 2019-01-30 | 2019-05-17 | 2019-05-17
[6 empty] | Owner Cmmt* | R1 | R2 | R2 | R1 | R1 | R1
| MP | OL1-2R04-0012 | Pipe Support |  | Class 2 | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  | 2018-11-16 | 2019-02-08 | 2019-02-08
[6 empty] | Issue Actual |  | 2018-11-16 | 2019-02-08 | 2019-02-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00324 | TPSK-LSPA1-T-MP-00324 | TPSK-LSPA1-T-MP-00828 | TPSK-LSPA1-T-MP-00828
[6 empty] | Return Date | 2018-12-18 | 2018-12-18 | 2019-02-25 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| MP | OL1-2R04-0013 | JOB SUPPLY SPECIFICATION FOR BUTTWELDING FITTINGS |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IMP | IMP
[6 empty] | Rev. | B | A | A | B | 0 | 0
[6 empty] | Issue Plan | 2019-04-06 |  |  |  | 2019-05-06
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-27 | 2018-08-29 | 2018-11-20 | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00342 | TPSK-LSPA1-T-MP-00028 | TPSK-LSPA1-T-MP-00028 | TPSK-LSPA1-T-MP-00342 | TPSK-LSPA1-T-MP-01463 | TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-01-30 | 2018-09-18 | 2018-09-18 | 2019-01-30 | 2019-05-17 | 2019-05-17
[6 empty] | Owner Cmmt* | R1 | A4 | A4 | R1 | R1 | R1
| MP | OL1-2R04-0014 | JOB SUPPLY SPECIFICATION FOR FORGED FITTINGS |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IMP | IMP
[6 empty] | Rev. | B | A | A | B | 0 | 0
[6 empty] | Issue Plan | 2019-04-06 |  |  |  | 2019-05-06
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-27 | 2018-08-29 | 2018-11-20 | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00342 | TPSK-LSPA1-T-MP-00028 | TPSK-LSPA1-T-MP-00028 | TPSK-LSPA1-T-MP-00342 | TPSK-LSPA1-T-MP-01463 | TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-01-30 | 2018-09-18 | 2018-09-18 | 2019-01-30 | 2019-05-17 | 2019-05-17
[6 empty] | Owner Cmmt* | R1 | A4 | A4 | R1 | R1 | R1
| MP | OL1-2R04-0015 | JOB SUPPLY SPECIFICATION FOR FLANGES |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IMP | IMP
[6 empty] | Rev. | B | A | A | B | 0 | 0
[6 empty] | Issue Plan | 2019-04-06 |  |  |  | 2019-05-06
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-27 | 2018-08-29 | 2018-11-20 | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00342 | TPSK-LSPA1-T-MP-00028 | TPSK-LSPA1-T-MP-00028 | TPSK-LSPA1-T-MP-00342 | TPSK-LSPA1-T-MP-01463 | TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-01-30 | 2018-09-18 | 2018-09-18 | 2019-01-30 | 2019-05-17 | 2019-05-17
[6 empty] | Owner Cmmt* | R1 | A4 | A4 | R1 | R1 | R1
| MP | OL1-2R04-0016 | JOB SUPPLY SPECIFICATION FOR GASKETS |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP
Rev.
[6 empty] | Issue Plan | 2019-04-20 | 2019-05-20
[6 empty] | Revised Plan | 2019-08-30 | 2019-10-25
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2R04-0017 | JOB SUPPLY SPECIFICATION FOR BOLTING |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP
Rev.
[6 empty] | Issue Plan | 2019-04-20 | 2019-05-20
[6 empty] | Revised Plan | 2019-08-30 | 2019-09-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2R04-0030 | Piping Flexibility |  | Class 2 | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  | 2018-11-20 | 2019-02-08 | 2019-02-08
[6 empty] | Issue Actual |  | 2018-11-20 | 2019-02-08 | 2019-02-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00336 | TPSK-LSPA1-T-MP-00336 | TPSK-LSPA1-T-MP-00828 | TPSK-LSPA1-T-MP-00828
[6 empty] | Return Date | 2018-12-07 | 2018-12-07 | 2019-02-25 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| MP | OL1-2R04-0031 | JOB DES.SPEC.FOR STEAM TRACING |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IFC
[6 empty] | Rev. | B | A | A | B
[6 empty] | Issue Plan | 2018-11-13 |  |  |  | 2019-02-01
Revised Plan
[6 empty] | Issue Actual |  | 2018-08-08 | 2018-08-08 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00292 | TPSK-LSPA1-T-MP-00012 | TPSK-LSPA1-T-MP-00012 | TPSK-LSPA1-T-MP-00292
[6 empty] | Return Date | 2019-01-23 | 2018-09-26 | 2018-09-26 | 2019-01-23
[6 empty] | Owner Cmmt* | R1 | A4 | A4 | R1
| MP | OL1-2R04-0032 | JSD FOR PIPING STRESS ANALYSIS |  | Class 2 | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-15
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-16 | 2019-02-19 | 2019-02-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00324 | TPSK-LSPA1-T-MP-00324 | TPSK-LSPA1-T-MP-00881 | TPSK-LSPA1-T-MP-00881
[6 empty] | Return Date | 2018-12-18 | 2018-12-18 | 2019-03-21 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| MP | OL1-2R04-0033 | JSD FOR PIPING LOADS ON PIPERACKS (PRK), SLEEPER WAYS (SLW), STRUCTURES (STR), ISOLATED SUPPORTS (IS) |  | Class 2 | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-15
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-16 | 2019-02-08 | 2019-02-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00324 | TPSK-LSPA1-T-MP-00324 | TPSK-LSPA1-T-MP-00828 | TPSK-LSPA1-T-MP-00828
[6 empty] | Return Date | 2018-12-18 | 2018-12-18 | 2019-02-25 | 2019-02-25
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| MP | OL1-2R04-0034 | JSD AUXILIARY STD PIPE SUPPORTS |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | B | B | 0 | 0
[6 empty] | Issue Plan | 2018-11-12 |  |  |  | 2019-02-15
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-16 | 2019-02-08 | 2019-02-08 | 2019-03-07 | 2019-03-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00324 | TPSK-LSPA1-T-MP-00324 | TPSK-LSPA1-T-MP-00830 | TPSK-LSPA1-T-MP-00830 | TPSK-LSPA1-T-MP-01002 | TPSK-LSPA1-T-MP-01002
[6 empty] | Return Date | 2018-12-18 | 2018-12-18 | 2019-02-25 | 2019-02-25 | 2019-04-01 | 2019-04-01
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1 | R1 | R1
| MP | OL1-2R04-0036 | JSS CRYOGENIC SUPPORTS |  | Class 3 | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-01-31 |  | 2019-02-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-08 | 2019-02-08 | 2019-04-02 | 2019-04-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00831 | TPSK-LSPA1-T-MP-00831 | TPSK-LSPA1-T-MP-01223 | TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | 2019-03-21 | 2019-03-21 | 2019-04-26 | 2019-04-26
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| MP | OL1-2R04-0037 | JSS FOR ROD & SPRING HANGERS |  | Class 3 | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-01-31 |  | 2019-02-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-08 | 2019-02-08 | 2019-04-02 | 2019-04-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00831 | TPSK-LSPA1-T-MP-00831 | TPSK-LSPA1-T-MP-01223 | TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | 2019-03-21 | 2019-03-21 | 2019-04-26 | 2019-04-26
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| MP | OL1-2R04-0038 | JSS SLIDING PLATES |  | Class 3 | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-01-31 |  | 2019-02-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-08 | 2019-02-08 | 2019-04-02 | 2019-04-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00831 | TPSK-LSPA1-T-MP-00831 | TPSK-LSPA1-T-MP-01223 | TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | 2019-03-21 | 2019-03-21 | 2019-04-26 | 2019-04-26
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R2
| MP | OL1-2R04-0039 | JSS DYNAMIC PIPING SUPPORTS |  | Class 3 | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-01-31 |  | 2019-02-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-08 | 2019-02-08 | 2019-04-02 | 2019-04-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00831 | TPSK-LSPA1-T-MP-00831 | TPSK-LSPA1-T-MP-01223 | TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | 2019-03-21 | 2019-03-21 | 2019-04-26 | 2019-04-26
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R2
| MP | OL1-2R04-0040 | JSS METALLIC EXPANSION JOINTS |  | Class 3 | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-01-31 |  | 2019-02-28
Revised Plan
[6 empty] | Issue Actual | 2019-02-08 | 2019-02-08 | 2019-04-02 | 2019-04-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00831 | TPSK-LSPA1-T-MP-00831 | TPSK-LSPA1-T-MP-01223 | TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | 2019-03-21 | 2019-03-21 | 2019-04-26 | 2019-04-26
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| MP | OL1-2R04-0041 | JOB SUPPLY SPECIFICATION FOR VALVE (GATE,GLOBE,CHECK) |  | Class 2 | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-04-13 |  | 2019-05-13
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-26 | 2019-04-24 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00356 | TPSK-LSPA1-T-MP-00356 | TPSK-LSPA1-T-MP-01463 | TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | 2019-01-30 | 2019-01-30 | 2019-05-17 | 2019-05-17
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| MP | OL1-2R04-0042 | Job Supply Specification For Non Metallic Expansion Joints |  | Class 2 | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-01-31 |  | 2019-02-28
Revised Plan
[6 empty] | Issue Actual | 2019-03-07 | 2019-03-08 | 2019-04-02 | 2019-04-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-01000 | TPSK-LSPA1-T-MP-01000 | TPSK-LSPA1-T-MP-01223 | TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | 2019-04-01 | 2019-04-01 | 2019-04-26 | 2019-04-26
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| ME | OL1-2R04-1004 | PIP-004 Piping Welding Specification for 36M and 132U Furnace |  | Class 2 | Rev.: Purpose**; B: IMP; A: IMP
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-16 | 2018-10-17
[6 empty] | Issue Actual | 2018-10-16 | 2018-10-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00184 | TPSK-LSPA1-T-ME-00184
Return Date
Owner Cmmt*
Category Code: R05 Electrical Specification (EE)
| EE | OL1-2R05-0001 | GENERAL ELECTRICAL DESIGN SPECIFICATION |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2019-01-30
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-12-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00424 | TPSK-LSPA1-T-EE-00424
Return Date
Owner Cmmt*
| EE | OL1-2R05-0002 | ELECTRICAL SYSTEM DESIGN |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2019-01-30
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-12-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00424 | TPSK-LSPA1-T-EE-00424
Return Date
Owner Cmmt*
| EE | OL1-2R05-0003 | OIL FILLED DISTRIBUTION TRANSFORMER |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00268 | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0004 | PROTECTIVE RELAY AND CONTROL UNIT |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2019-01-30
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-12-20
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00522 | TPSK-LSPA1-T-EE-00522
Return Date
Owner Cmmt*
| EE | OL1-2R05-0005 | SUBSTATION MONITORING AND CONTROL SYSTEM |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-12-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00425 | TPSK-LSPA1-T-EE-00425
Return Date
Owner Cmmt*
| EE | OL1-2R05-0006 | MEDIUM VOLTAGE SWITCHGEAR |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00268 | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0007 | LOW VOLTAGE DISTRIBUTION PANEL |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-11-12
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00309 | TPSK-LSPA1-T-EE-00309
Return Date
Owner Cmmt*
| EE | OL1-2R05-0008 | LOW VOLTAGE SWITCHGEAR AND MOTOR CONTROL CENTER |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP
Rev.
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| TS | OL1-2R05-0009 | SMCS I/O LIST |  | Class 2 | Rev.: Purpose**; B: IFR; A: IFR; A: IMP
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-06-15 |  | 2019-08-17
[6 empty] | Revised Plan |  |  | 2019-08-17
[6 empty] | Issue Actual | 2019-07-01 | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02023 | TPSK-LSPA1-T-EE-02023
[6 empty] | Return Date | 2019-07-16 | 2019-07-16
[6 empty] | Owner Cmmt* | A3 | A3
| EE | OL1-2R05-0010 | ELECTRICAL MOTORS UP TO 300 KW |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-09-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00079 | TPSK-LSPA1-T-EE-00079
Return Date
Owner Cmmt*
| EE | OL1-2R05-0011 | ELECTRICAL MOTORS GREATER THAN TO 300 KW |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-11-08
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00748 | TPSK-LSPA1-T-EE-00748
[6 empty] | Return Date |  | 2019-02-25 | 2019-02-25
[6 empty] | Owner Cmmt* |  | R1 | R1
| EE | OL1-2R05-0012 | UNINTERRUPTIBLE POWER SUPPLIES |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00268 | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0013 | INTERCOM/PAGING/AUDIBLE ALARM SYSTEM |  |  | Purpose** | IFR | IFR | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-15
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-04 | 2019-03-06 | 2019-03-07 | 2019-07-01 | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00403 | TPSK-LSPA1-T-EE-00403 | TPSK-LSPA1-T-EE-00987 | TPSK-LSPA1-T-EE-00987 | TPSK-LSPA1-T-EE-02031 | TPSK-LSPA1-T-EE-02031
[6 empty] | Return Date | 2018-12-17 | 2018-12-17 | 2019-03-21 | 2019-03-21 | 2019-07-08 | 2019-07-08
[6 empty] | Owner Cmmt* | R1 | R1 | R2 | R2 | R2 | R2
| EE | OL1-2R05-0014 | LIGHTING SYSTEM |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2019-01-30
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00258 | TPSK-LSPA1-T-EE-00258
Return Date
Owner Cmmt*
| EE | OL1-2R05-0015 | EARTHING AND LIGHTING PROTECTION |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2019-01-30
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00258 | TPSK-LSPA1-T-EE-00258
Return Date
Owner Cmmt*
| EE | OL1-2R05-0016 | CATHODIC PROTECTION |  | Class 2 | Purpose** | IFR | IMP | IMP | IMP | IMP
[6 empty] | Rev. |  | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-11-05 | 2019-05-02 | 2019-05-03
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00268 | TPSK-LSPA1-T-EE-00268 | TPSK-LSPA1-T-EE-01556 | TPSK-LSPA1-T-EE-01556
[6 empty] | Return Date |  |  |  | 2019-05-17 | 2019-05-17
[6 empty] | Owner Cmmt* |  |  |  | R1 | R1
| EE | OL1-2R05-0017 | DIESEL ENGINE GENERATOR |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00268 | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0018 | POWER, CONTROL, AND FIBER OPTIC CABLES |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-12-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00425 | TPSK-LSPA1-T-EE-00425
Return Date
Owner Cmmt*
| EE | OL1-2R05-0019 | SAFETY SUPERVISORY SYSTEM |  |  | Purpose** | IFR | IFR | IMP | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0 | 1
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-15
Revised Plan
[6 empty] | Issue Actual |  | 2018-12-04 | 2019-03-06 | 2019-03-07 | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00403 | TPSK-LSPA1-T-EE-00403 | TPSK-LSPA1-T-EE-00987 | TPSK-LSPA1-T-EE-00987 | TPSK-LSPA1-T-EE-02179
[6 empty] | Return Date | 2018-12-17 | 2018-12-17 | 2019-03-21 | 2019-03-21 | 2019-07-30
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R1
| EE | OL1-2R05-0021 | POWER CAPACITORS |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00268 | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0022 | MISCELLANEOUS EQUIPMENT |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00268 | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0023 | LOW VOLTAGE VARIABLE VOLTAGE VARIABLE FREQUENCY SYSTEM |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00268 | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0024 | SUBSTATION DESIGN |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP
Rev.
[6 empty] | Issue Plan | 2018-10-14 | 2019-01-30
[6 empty] | Revised Plan | 2019-08-30 | 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2R05-0027 | NEUTRAL GROUNDING RESISTOR |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-12-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00425 | TPSK-LSPA1-T-EE-00425
Return Date
Owner Cmmt*
| EE | OL1-2R05-0028 | TELECOM NUMBERING |  |  | Purpose** | IFR | IFR | IFR | IMP
[6 empty] | Rev. | A | A | B
[6 empty] | Issue Plan | 2019-01-21 |  |  | 2019-02-15
[6 empty] | Revised Plan |  |  |  | 2019-09-03
[6 empty] | Issue Actual | 2019-02-21 | 2019-02-22 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00905 | TPSK-LSPA1-T-EE-00905 | TPSK-LSPA1-T-EE-02310
[6 empty] | Return Date | 2019-03-04 | 2019-03-04 | 2019-08-08
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| EE | OL1-2R05-0029 | FUNCTIONAL AND SCHEMATIC DIAGRAM |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2019-01-30
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00258 | TPSK-LSPA1-T-EE-00258
Return Date
Owner Cmmt*
| EE | OL1-2R05-0036 | DOCUMENT TEMPLATE |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2019-01-30
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-12-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00424 | TPSK-LSPA1-T-EE-00424
Return Date
Owner Cmmt*
| EE | OL1-2R05-0037 | ELECTRICAL HEAT TRACING SYSTEM |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-09-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00079 | TPSK-LSPA1-T-EE-00079
Return Date
Owner Cmmt*
| EE | OL1-2R05-0038 | LOW VOLTAGE BUS DUCT |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00268 | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0040 | MEDIUM VOLTAGE VARIABLE VOLTAGE VARIABLE FREQUENCY (VVVF) SYSTEM |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00268 | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0041 | NUMBERING SYSTEM FOR ELECTRICAL EQUIPMENT |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP
Rev.
[6 empty] | Issue Plan | 2018-10-14 | 2019-01-30
[6 empty] | Revised Plan | 2019-08-30 | 2019-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2R05-0042 | General Design Rule For Package Equipment Electrical System - Client code for next revision will be OL1-2E04-6000 |  | Class 2 | Rev.: Purpose**; B: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-08-07
[6 empty] | Issue Actual | 2018-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | 2018-08-24
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2R05-0044 | Coordination Procedure For Smartplant Electrical |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP
Rev.
[6 empty] | Issue Plan | 2018-10-14 | 2018-12-03
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: R06 Instrument Specification (INS) |  |  |  |  | Class 2 | Rev.: Purpose**
| IE | OL1-2R06-0001 | NSTRUMENT GENERAL DESIGN |  |  | Purpose** | IFR | IFR | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2018-09-28 |  | 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2018-10-03 | 2018-10-04 |  | 2018-12-17 | 2019-05-24 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-00507 | TPSK-LSPA1-T-IE-00507 | TPSK-LSPA1-T-IE-01741 | TPSK-LSPA1-T-IE-01741
[6 empty] | Return Date | 2018-10-09 | 2018-10-09 | 2018-12-26 | 2018-12-26 | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | A2 | A2
| IE | OL1-2R06-0003 | FLOW MEASUREMENT |  |  | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-09-28 | 2018-09-28
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-10-03
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-00122 | TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0005 | LEVEL MEASUREMENT |  |  | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2018-09-28 |  | 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2018-10-03 | 2018-10-04 |  | 2018-12-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-00507 | TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | 2018-10-09 | 2018-10-09 | 2018-12-26 | 2018-12-26
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| IE | OL1-2R06-0006 | PRESSURE MEASUREMENT |  |  | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2018-09-28 |  | 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2018-10-03 | 2018-10-04 |  | 2018-12-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-00507 | TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | 2018-10-09 | 2018-10-09 | 2018-12-26 | 2018-12-26
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| IE | OL1-2R06-0007 | TEMPERATURE MEASUREMENT |  |  | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2018-09-28 |  | 2018-12-21
Revised Plan
[6 empty] | Issue Actual | 2018-10-03 | 2018-10-04 |  | 2018-12-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-00507 | TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | 2018-10-09 | 2018-10-09 | 2018-12-26 | 2018-12-26
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| IE | OL1-2R06-0008 | FINAL CONTROL ELEMENT |  |  | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2018-09-28 |  | 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2018-10-03 | 2018-10-04 | 2019-05-23 | 2019-05-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-01727 | TPSK-LSPA1-T-IE-01727
[6 empty] | Return Date | 2018-10-09 | 2018-10-09 |  | 2019-06-12
[6 empty] | Owner Cmmt* | R1 | R1 |  | R2
| IE | OL1-2R06-0010 | INSTRUMENT CONSTRUCTION MATERIAL |  |  | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2019-02-15 | 2019-09-28
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-03 | 2018-10-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-00122 | TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0011 | INSTRUMENT AIR SUPPLY |  |  | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-02-15 |  | 2019-09-28
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-26 | 2019-03-08 | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00357 | TPSK-LSPA1-T-IE-00357 | TPSK-LSPA1-T-IE-01014 | TPSK-LSPA1-T-IE-01014
[6 empty] | Return Date | 2019-02-01 | 2019-02-01 | 2019-04-05 | 2019-04-05
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| IE | OL1-2R06-0012 | GROUNDING SYSTEM FOR INSTRUMENT |  |  | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2019-02-15 | 2019-09-28
Revised Plan
[6 empty] | Issue Actual |  |  | 2018-12-17
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-00508 | TPSK-LSPA1-T-IE-00508
Return Date
Owner Cmmt*
| IE | OL1-2R06-0013 | MACHINE MONITORING SYSTEM |  |  | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-07-30 |  | 2020-03-05
Revised Plan
[6 empty] | Issue Actual | 2018-10-03 | 2018-10-04 | 2019-02-19 | 2019-02-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-00889 | TPSK-LSPA1-T-IE-00889
[6 empty] | Return Date | 2018-10-09 | 2018-10-09 | 2019-03-08 | 2019-03-08
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| IE | OL1-2R06-0015 | INTEGRATED CONTROL AND SAFETY SYSTEM (ICSS) |  |  | Purpose** | IFR | IFR | IMP | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0 | 0
[6 empty] | Issue Plan | 2018-11-20 |  | 2019-02-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-26 | 2019-06-14 | 2019-06-17 | 2019-06-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00357 | TPSK-LSPA1-T-IE-00357 | TPSK-LSPA1-T-IE-01897 | TPSK-LSPA1-T-IE-01897 | TPSK-LSPA1-T-IE-01897
[6 empty] | Return Date | 2019-02-01 | 2019-02-01 |  | 2019-06-27 | 2019-06-27
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2 | R2
| IE | OL1-2R06-0016 | INSTRUMENT CABINETS |  |  | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2018-11-20 |  | 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2018-10-03 | 2018-10-04 | 2019-03-05 | 2019-03-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-00986 | TPSK-LSPA1-T-IE-00986
[6 empty] | Return Date | 2018-10-09 | 2018-10-09 | 2019-05-15 | 2019-05-15
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| IE | OL1-2R06-0017 | INTEGRATED TURBINE AND COMPRESSOR CONTROL SYSTEM (ITCC) |  |  | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2018-11-07 |  | 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-10-10 |  | 2018-12-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00148 | TPSK-LSPA1-T-IE-00148 | TPSK-LSPA1-T-IE-00507 | TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | 2018-10-24 | 2018-10-24 | 2018-12-26 | 2018-12-26
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| IE | OL1-2R06-0021 | PRESSURE SAFETY VALVE |  |  | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-09-28 | 2018-09-28
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-03 | 2018-10-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-00122 | TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0022 | INSTRUMENT NUMBERING |  |  | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2018-10-03 |  | 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2018-10-05 | 2018-10-05 | 2019-04-11 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-IE-01320 | TPSK-LSPA1-T-IE-01320
[6 empty] | Return Date | 2018-10-24 | 2018-10-24 | 2019-05-09 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| IE | OL1-2R06-0023 | INSTRUMENT INSPECTION AND TEST PLAN |  |  | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-03 | 2019-02-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-03 | 2018-10-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-00122 | TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0024 | JSD FOR SMART PLANT INSTRUMENTATION SET UP |  |  | Purpose** | IFR | IFR | IFR | IFR | IMP | IMP
[6 empty] | Rev. | B | A | A | B | 0 | 0
[6 empty] | Issue Plan | 2018-10-03 |  |  |  | 2019-02-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-09-28 | 2018-11-08 | 2019-03-19 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00291 | TPSK-LSPA1-T-IE-00109 | TPSK-LSPA1-T-IE-00109 | TPSK-LSPA1-T-IE-00291 | TPSK-LSPA1-T-IE-01094 | TPSK-LSPA1-T-IE-01094
[6 empty] | Return Date | 2019-02-01 | 2018-10-09 | 2018-10-09 | 2019-02-01 | 2019-04-05 | 2019-04-05
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R1 | R1
| IE | OL1-2R06-0026 | JSD For Automation System Availability |  | Class 2 | Rev.: Purpose**; B: IFR; A: IFR; A: IMP
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-21
[6 empty] | Revised Plan |  |  | 2019-08-30
[6 empty] | Issue Actual | 2019-04-15 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01355 | TPSK-LSPA1-T-IE-01355
[6 empty] | Return Date | 2019-05-07 | 2019-05-07
[6 empty] | Owner Cmmt* | R2 | R2
| IE | OL1-2R06-0035 | JSD FOR INSTRUMENTATION AND CONTROL OF PACKAGED EQUIPMENT |  |  | Purpose** | IFR | IFR | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0 | 1 | 1
[6 empty] | Issue Plan | 2018-11-07 |  | 2019-02-02
Revised Plan
[6 empty] | Issue Actual | 2018-09-17 | 2018-09-18 |  | 2018-11-29 | 2019-04-11 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00056 | TPSK-LSPA1-T-IE-00056 | TPSK-LSPA1-T-IE-00393 | TPSK-LSPA1-T-IE-00393 | TPSK-LSPA1-T-IE-01320 | TPSK-LSPA1-T-IE-01320
[6 empty] | Return Date | 2018-10-02 | 2018-10-02 | 2018-12-13 | 2018-12-13 | 2019-05-09 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R1 | R1
| IE | OL1-2R06-1025 | JSD FOR CTRL & SAFETY PHILOSOPHY |  |  | Rev.: Purpose**; B: IFR; A: IFR; A: IMP
[6 empty] | Rev. | A | A
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-21
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00750 | TPSK-LSPA1-T-IE-00750
[6 empty] | Return Date | 2019-02-27 | 2019-02-27
[6 empty] | Owner Cmmt* | R2 | R2
| IE | OL1-2R06-1301 | PROGRAMMABLE LOGIC CONTROLLER (PLC) |  |  | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2018-11-07 |  | 2019-02-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-08 | 2019-03-19 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00291 | TPSK-LSPA1-T-IE-00291 | TPSK-LSPA1-T-IE-01094 | TPSK-LSPA1-T-IE-01094
[6 empty] | Return Date | 2019-02-01 | 2019-02-01 | 2019-04-05 | 2019-04-05
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| IE | OL1-2R06-2003 | PROCESS ONLINE ANALYZER AND ANALYZER HOUSING |  |  | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2019-01-10 |  | 2019-02-10
Revised Plan
[6 empty] | Issue Actual | 2019-02-08 | 2019-02-08 | 2019-03-13 | 2019-03-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00825 | TPSK-LSPA1-T-IE-00825 | TPSK-LSPA1-T-IE-01044 | TPSK-LSPA1-T-IE-01044
[6 empty] | Return Date | 2019-03-08 | 2019-03-08 | 2019-05-09 | 2019-05-09
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| IE | OL1-2R06-3101 | CUSTODY TRANSFER SYSTEM |  |  | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2018-11-20 |  | 2019-01-21
Revised Plan
[6 empty] | Issue Actual |  | 2018-11-26 | 2019-03-19 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00357 | TPSK-LSPA1-T-IE-00357 | TPSK-LSPA1-T-IE-01094 | TPSK-LSPA1-T-IE-01094
[6 empty] | Return Date | 2019-02-01 | 2019-02-01 | 2019-04-05 | 2019-04-05
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
Category Code: R07 Project Specification (SP)
| ME | OL1-2R07-0009 | SP-009 Painting for 36M and 132U Furnace |  | Class 2 | Rev.: Purpose**; B: IMP; A: IMP
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  | 2018-10-23
[6 empty] | Issue Actual |  | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00214 | TPSK-LSPA1-T-ME-00214
Return Date
Owner Cmmt*
| ME | OL1-2R07-0018 | Units Of Measurement |  | Class 2 | Rev.: Purpose**; B: IMP; A: IMP
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2018-09-24 | 2018-09-25
[6 empty] | Issue Actual | 2018-09-24 | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00080 | TPSK-LSPA1-T-ME-00080
[6 empty] | Return Date | 2018-10-24 | 2018-10-24
Owner Cmmt*
| ME | OL1-2R07-0020 | ELETRICAL AND INTRUMENT INTERFACE PHILOSOPHY |  |  | Purpose** | IFR | IFR | IMP | IMP
[6 empty] | Rev. | A | A | 0 | 0
[6 empty] | Issue Plan | 2018-09-28 |  | 2019-01-21
Revised Plan
[6 empty] | Issue Actual | 2018-10-03 | 2018-10-04 |  | 2018-12-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-00121 | TPSK-LSPA1-T-IE-00507 | TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | 2018-10-09 | 2018-10-09 | 2018-12-26 | 2018-12-26
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| ME | OL1-2R07-0026 | Project Design Basis |  | Class 2 | Purpose** | IMP | IMP | IMP | IMP
[6 empty] | Rev. | 0 | 0 | 1 | 1
Issue Plan
[6 empty] | Revised Plan | 2018-09-28 | 2018-09-28 | 2019-05-02 | 2019-05-03
[6 empty] | Issue Actual | 2018-09-28 | 2018-09-28 | 2019-05-02 | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00110 | TPSK-LSPA1-T-ME-00110 | TPSK-LSPA1-T-ME-01547 | TPSK-LSPA1-T-ME-01547
[6 empty] | Return Date | 2018-10-24 | 2018-10-24 | 2019-05-31 | 2019-05-31
[6 empty] | Owner Cmmt* |  |  | R1 | R1
Category Code: R08 Construction Specification (CON)
| CON | OL1-2R08-0001 | SPECIAL TEC.SP.FOR ERECT |  |  | Rev.: Purpose**; B: IFQ; A: IFP
Rev.
[6 empty] | Issue Plan | 2019-01-27 | 2019-03-27
[6 empty] | Revised Plan | 2019-08-30 | 2019-09-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CON | OL1-2R08-0003 | INSTRUMENT INSTALLATION |  |  | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2019-02-15 | 2019-09-28
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-03 | 2018-10-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-00122 | TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
Category Code: R91 Index/List
Category Code: R92 Procedures & Standards
Category Code: R93 Policy , Guidelines & Memo
| CON | OL1-2R93-2001 | GUIDELINE FOR CRACKING FURNACE CONSTRUCTION / ERECTION |  | Class 2 | Rev.: Purpose**; B: IFR; A: IFD; A: IFF
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2019-09-03 | 2019-10-08
[6 empty] | Revised Plan | 2019-08-30 | 2019-09-03 | 2019-10-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: R94 Forms & Templates
Category Code: R95 Progress/Status Reports
Category Code: Request for Quotation (RFQ) for Mechanical work Request for Quotation (RFQ) for Mechanical work
Category Code: S01 Environmental Management Plan and program;
Category Code: S02 Waste Material Management
Category Code: S03 Health/Social Management and Program; Community Affairs Management
Category Code: S04 Environmental Management Report
Category Code: S05 Health/Social Management Report
Category Code: S06 ESIA Report
Category Code: S07 ESIA Database
Category Code: S08 Environmental Specification (nuovo codice richiesto dal cliente S82)
| ES | OL1-2S08-0001 | ENVIRONMENTAL JOB SPECIFICATION FOR DESIGN |  | Class 2 | Rev.: Purpose**; B: IFR; A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan |  | 2018-12-11
[6 empty] | Issue Actual |  | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ES-00473 | TPSK-LSPA1-T-ES-00473
Return Date
Owner Cmmt*
Category Code: S63 EH&S Monitoring report
Category Code: S64 OSHE Review/Audit Report
Category Code: S71 Appraisal Report for Consultancy Service
Category Code: S72 Appraisal Report for EPC Contractor Work
Category Code: S73 Appraisal Report for Vendor/Supplier
Category Code: S81 CSR Procedure & Standard
Category Code: S82 CSR Policy, Guideline & Memo
Category Code: S83 CSR Template & Form
Category Code: S84 CSR Report
Category Code: S85 CSR Audit Report
Category Code: S90 Vendor Document/drawings
Category Code: S91 Index/List
Category Code: S92 Procedures & Standards
Category Code: S93 Policy , Guidelines & Memo
Category Code: S94 Forms & Templates
Category Code: S95 Progress/Status Reports
| ES | OL1-2S95-0210 | Furnace Section HAZOP Report |  | Class 2 | Rev.: Purpose**; B: IFR; A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-03-20 | 2019-03-21
[6 empty] | Issue Actual | 2019-03-20 | 2019-03-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ES-01113 | TPSK-LSPA1-T-ES-01113
[6 empty] | Return Date | 2019-04-22 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| ES | OL1-2S95-0211 | Recovery Process and Utilities Sections HAZOP Report |  | Class 2 | Rev.: Purpose**; B: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-09
[6 empty] | Issue Actual | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ES-02101
Return Date
Owner Cmmt*
| ES | OL1-2S95-0230 | Furnace Section SIL Classification Report |  | Class 2 | Rev.: Purpose**; B: IFR; A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-03-25 | 2019-03-26
[6 empty] | Issue Actual | 2019-03-25 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ES-01146 | TPSK-LSPA1-T-ES-01146
[6 empty] | Return Date | 2019-04-22 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R2
| ES | OL1-2S95-0231 | Recovery Process and Utilities Sections SIL Classification Report |  | Class 2 | Rev.: Purpose**; B: IFR; A: IFR
[6 empty] | Rev. | A | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-11 | 2019-07-11
[6 empty] | Issue Actual | 2019-07-11 | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ES-02124 | TPSK-LSPA1-T-ES-02124
[6 empty] | Return Date |  | 2019-08-07
[6 empty] | Owner Cmmt* |  | R2
Category Code: T01 Design basis
| EE | OL1-2T01-0001 | Job Supply Specification For Intercom Paging And Audible Alarm System -Ex Document Client Reference OL1-2T92-0001 |  | Class 2 | Purpose** | IFR | IFR | IFF | IFF
[6 empty] | Rev. | A | A | 1 | 1
[6 empty] | Issue Plan | 2019-04-15 |  | 2019-05-15
Revised Plan
[6 empty] | Issue Actual |  | 2019-01-03 | 2019-07-01 | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00577 | TPSK-LSPA1-T-EE-00577 | TPSK-LSPA1-T-EE-02025 | TPSK-LSPA1-T-EE-02025
[6 empty] | Return Date | 2019-01-23 | 2019-01-23 | 2019-07-08 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| EE | OL1-2T01-0002 | Job Supply Specification For Safety Supervisory System - Ex Document Client Reference OL1-2T92-0002 |  | Class 2 | Purpose** | IFR | IFR | IFR | IFR | IFF | IMP
[6 empty] | Rev. | A | A | B | B |  | 0
[6 empty] | Issue Plan | 2019-04-15 |  |  |  | 2019-05-15
[6 empty] | Revised Plan | [5 empty] | 2019-07-19
[6 empty] | Issue Actual |  | 2019-01-03 | 2019-03-06 | 2019-03-07 |  | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00577 | TPSK-LSPA1-T-EE-00577 | TPSK-LSPA1-T-EE-00985 | TPSK-LSPA1-T-EE-00985 |  | TPSK-LSPA1-T-EE-02181
[6 empty] | Return Date | 2019-01-23 | 2019-01-23 | 2019-03-21 | 2019-03-21 |  | 2019-08-01
[6 empty] | Owner Cmmt* | R2 | R2 | A2 | A2 |  | A1
Category Code: T02 Abbreviation and standard symbols
Category Code: T03 Project Communication, IT, and Safety Supervisory System specification
Category Code: T04 System philosophy
Category Code: T05 Equipment datasheets
Category Code: T10 Intercom/Paging/Audible Alarm system equipment data sheets
Category Code: T11 Intercom/Paging/Audible Alarm system schematic diagram
| EE | OL1-2T11-0001 | TELECOMM.SYST ARCHITECTURE OF INTERCOM, PAGING AND AUDIBLE ALARM SYSTEMS |  |  | Purpose** | IFR | IFR | IFR | IFR | IFR | IFR | IBD | IDD
[6 empty] | Rev. | A | A | B | B | C | C
[6 empty] | Rev.: Issue Plan; B: 2019-01-09; D: 2019-01-09 | 2019-02-28
[6 empty] | Rev.: Revised Plan | 2019-08-30
[6 empty] | Issue Actual | 2019-03-04 | 2019-03-05 | 2019-05-09 | 2019-05-10 | 2019-07-01 | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00976 | TPSK-LSPA1-T-EE-00976 | TPSK-LSPA1-T-EE-01624 | TPSK-LSPA1-T-EE-01624 | TPSK-LSPA1-T-EE-02024 | TPSK-LSPA1-T-EE-02024
[6 empty] | Return Date | 2019-03-21 | 2019-03-21 | 2019-05-26 | 2019-05-26 | 2019-07-22
[6 empty] | Owner Cmmt* | A3 | A3 | A3 | A3 | A2
Category Code: T12 Intercom/Paging/Audible Alarm aystem layout
| EE | OL1-2T12-0002 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT COMMON AREA |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
Rev.
[6 empty] | Issue Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
[6 empty] | Revised Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0003 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT METERING |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
[6 empty] | Revised Plan |  | 2020-01-31 | 2020-07-15
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02171
[6 empty] | Return Date | 2019-08-12
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2T12-0004 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT MAIN PIPE RACK |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
Rev.
[6 empty] | Issue Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
[6 empty] | Revised Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0005 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT AREA SUBSTATION E & FAR E |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
[6 empty] | Revised Plan |  | 2020-01-31 | 2020-07-15
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | 2019-08-12
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2T12-0006 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT AREA SUBSTATION C & FAR C |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
[6 empty] | Revised Plan |  | 2020-01-31 | 2020-07-15
[6 empty] | Issue Actual | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02183
[6 empty] | Return Date | 2019-08-12
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2T12-0007 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT FURNACES UTILITY |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
[6 empty] | Revised Plan |  | 2020-01-31 | 2020-07-15
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | 2019-08-12
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2T12-0008 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT QUENCH |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
[6 empty] | Revised Plan |  | 2020-01-31 | 2020-07-15
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | 2019-08-12
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2T12-0009 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS 20B |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
[6 empty] | Revised Plan |  | 2020-01-31 | 2020-07-15
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | 2019-08-12
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2T12-0010 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS 20C |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
[6 empty] | Revised Plan |  | 2020-01-31 | 2020-07-15
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | 2019-08-12
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2T12-0011 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS COLD COMPRESSORS |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
[6 empty] | Revised Plan |  | 2020-01-31 | 2020-07-15
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | 2019-08-12
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2T12-0012 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS CGC |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
[6 empty] | Revised Plan |  | 2020-01-31 | 2020-07-15
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | 2019-08-12
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2T12-0014 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT COOLING WATER UNIT |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
[6 empty] | Revised Plan |  | 2020-01-31 | 2020-07-15
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | 2019-08-12
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2T12-0015 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT UTILITIES |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
[6 empty] | Revised Plan |  | 2020-01-31 | 2020-07-15
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | 2019-08-12
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2T12-0016 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT WASTE WATER TREATMENT |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
[6 empty] | Revised Plan |  | 2020-01-31 | 2020-07-15
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | 2019-08-12
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2T12-0017 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT FLARE AREA |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-01-31 | 2020-07-15
[6 empty] | Revised Plan |  | 2020-01-31 | 2020-07-15
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02171
[6 empty] | Return Date | 2019-08-12
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2T12-0018 | Telecom And Security System Devices Layout - Process 3A |  | Class As Built | Rev.: Purpose**; B: IFR
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30
Revised Plan
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02171
[6 empty] | Return Date | 2019-08-12
[6 empty] | Owner Cmmt* | A3
Category Code: T13 Intercom/Paging/Audible Alarm aystem wiring layout
| EE | OL1-2T13-1001 | TELECOM WIRING DRAWINGS FOR FAR-E SYSTEMS |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-02-28 | 2020-08-31
[6 empty] | Revised Plan | 2020-02-28 | 2020-02-28 | 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T13-1002 | TELECOM WIRING DRAWINGS FOR FAR-C SYSTEMS |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-02-28 | 2020-08-31
[6 empty] | Revised Plan | 2020-02-28 | 2020-02-28 | 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T13-1003 | TELECOM WIRING DRAWINGS FOR FAR-FL SYSTEMS |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-02-28 | 2020-08-31
[6 empty] | Revised Plan | 2020-02-28 | 2020-02-28 | 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T13-1004 | TELECOM WIRING DRAWINGS FOR CCB SYSTEMS |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-02-28 | 2020-08-31
[6 empty] | Revised Plan | 2020-02-28 | 2020-02-28 | 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T14 Cable drum schedule for Intercom/Paging/Audible Alarm aystem
Category Code: T15 Cable schedule for Intercom/Paging/Audible Alarm aystem
Category Code: T16 Connection List for Intercom/Paging/Audible Alarm aystem
| EE | OL1-2T16-1001 | TELECOM CABLE LIST FOR FAR C SYSTEMS |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
[6 empty] | Revised Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T16-1002 | TELECOM CABLE LIST FOR FAR E SYSTEMS |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
[6 empty] | Revised Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T16-1003 | TELECOM CABLE LIST FOR FAR FL SYSTEMS |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
[6 empty] | Revised Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T16-1004 | TELECOM CABLE LIST FOR CCB AND OTHER BULDINGS SYSTEMS |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
[6 empty] | Revised Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T17 Bill of quantities for Intercom/Paging/Audible Alarm aystem
| EE | OL1-2T17-0001 | TELECOMM. & SUPERVISORY SYSTEMS EQUIPMENT LIST |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-04 | 2020-02-28 | 2020-08-30
[6 empty] | Revised Plan | 2019-12-31 | 2020-02-28 | 2020-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T17-0002 | TELECOMM. & SUPERVISORY SYSTEMS EQUIPMENT LIST FOR OTHER CONTRACTORS |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
Rev.
[6 empty] | Issue Plan | 2019-03-04 | 2020-02-28 | 2020-08-30
[6 empty] | Revised Plan | 2019-12-31 | 2020-02-28 | 2020-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T18 Typical drawing for Intercom/Paging/Audible Alarm aystem
Category Code: T20 Computer Network (LAN) and Telephone system equipment data sheets
Category Code: T21 Computer Network (LAN) and Telephone system schematic diagram
Category Code: T22 Computer Network (LAN) and Telephone system layout
Category Code: T23 Computer Network (LAN) and Telephone system wiring layout
Category Code: T24 Cable drum schedule for Computer Network (LAN) and Telephone system
Category Code: T25 Cable schedule for Computer Network (LAN) and Telephone system
Category Code: T26 Connection List for Computer Network (LAN) and Telephone system
| EE | OL1-2T26-0001 | FIBRE OPTIC TERMINATION DRAWINGS |  |  | Rev.: Purpose**; B: IFR; A: IDD; A: IFC
Rev.
[6 empty] | Issue Plan | 2019-11-30 | 2020-02-28 | 2020-08-31
[6 empty] | Revised Plan | 2019-11-30 | 2020-02-28 | 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T27 Bill of quantities for Computer Network (LAN) and Telephone system
Category Code: T28 Typical drawing for Computer Network (LAN) and Telephone system
Category Code: T30 CCTV, Access Control, and Intrusion Alarm system equipment data sheets
Category Code: T31 CCTV, Access Control, and Intrusion Alarm system schematic diagram
| EE | OL1-2T31-0001 | Telecomm Syst Architecture Of Safety Supervisory System |  | Class As Built | Purpose** | IFR | IFR | IBD | IBD | IDD
[6 empty] | Rev. | A | A | B | B
[6 empty] | Issue Plan | 2019-01-09 |  | 2019-01-09 |  | 2019-02-28
[6 empty] | Revised Plan |  |  |  |  | 2019-08-30
[6 empty] | Issue Actual | 2019-03-04 | 2019-03-05 | 2019-05-09 | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00976 | TPSK-LSPA1-T-EE-00976 | TPSK-LSPA1-T-EE-01624 | TPSK-LSPA1-T-EE-01624
[6 empty] | Return Date | 2019-03-21 | 2019-03-21 | 2019-05-26 | 2019-05-26
[6 empty] | Owner Cmmt* | A3 | A3 | A3 | A3
Category Code: T32 CCTV, Access Control, and Intrusion Alarm system layout
Category Code: T33 CCTV, Access Control, and Intrusion Alarm system wiring layout
Category Code: T34 Cable drum schedule for CCTV, Access Control, and Intrusion Alarm system
Category Code: T35 Cable schedule for CCTV, Access Control, and Intrusion Alarm system
Category Code: T36 Connection List for CCTV, Access Control, and Intrusion Alarm system
Category Code: T37 Bill of quantities for CCTV, Access Control, and Intrusion Alarm system
Category Code: T38 Typical drawing for CCTV, Access Control, and Intrusion Alarm system
Category Code: T40 Fire Alarm system equipment data sheets
Category Code: T41 Fire Alarm system schematic diagram
Category Code: T42 Fire alarm system layout
Category Code: T43 Fire alarm system wiring layout
Category Code: T44 Cable drum schedule for Fire alarm system
Category Code: T45 Cable schedule for Fire alarm system
Category Code: T46 Connection List for Fire alarm system
Category Code: T47 Bill of quantities forFire alarm system
Category Code: T48 Typical drawing for Fire alarm system
Category Code: T60 Application software system
Category Code: T61 Application software Procedure
Category Code: T71 Appraisal Report for Consultancy Service
Category Code: T72 Appraisal Report for EPC Contractor Work
Category Code: T73 Appraisal Report for Vendor/Supplier
Category Code: T90 Vendor documents
Category Code: T91 Index/List
Category Code: T92 Procedures & Standards
Category Code: T93 Policy , Guidelines & Memo | [5 empty] | Rev.: Purpose**
Category Code: T94 Forms & Templates | [5 empty] | Rev.: Rev.
Category Code: T95 Progress/Status Reports | [5 empty] | Rev.: Issue Plan
Category Code: U02 Finance Reports | [5 empty] | Rev.: Revised Plan
Category Code: U03 Certification(Finance) | [5 empty] | Rev.: Issue Actual
Category Code: U07 Bond and other financial security for Consultancy Service | [5 empty] | Rev.: Transmittal no.
Category Code: U08 Bond and other financial security for EPC Contractor | [5 empty] | Rev.: Return Date
Category Code: U09 Bond and other financial security for Vendor/Supplier | [5 empty] | Rev.: Owner Cmmt*
Category Code: U11 Certificates of Insurance
Category Code: U12 Insurance Policies and Guarantees
Category Code: U71 Appraisal Report for Consultancy Service
Category Code: U72 Appraisal Report for EPC Contractor Work
Category Code: U73 Appraisal Report for Vendor/Supplier
Category Code: U91 Index/List
Category Code: U92 Procedures & Standards
Category Code: U93 Policy , Guidelines & Memo
Category Code: U94 Forms & Templates
Category Code: U95 Progress/Status Reports
Category Code: V04 Interface Matrix (Responsibility Matrix)
Category Code: V71 Appraisal Report for Consultancy Service
Category Code: V72 Appraisal Report for EPC Contractor Work
Category Code: V73 Appraisal Report for Vendor/Supplier
Category Code: V91 Index/List
Category Code: V92 Procedures & Standards
Category Code: V93 Policy , Guidelines & Memo
Category Code: V94 Forms & Templates
Category Code: V95 Progress/Status Reports
Category Code: W71 Appraisal Report for Consultancy Service
Category Code: W72 Appraisal Report for EPC Contractor Work
Category Code: W73 Appraisal Report for Vendor/Supplier
Category Code: W90 Technical Report
| PM | OL1-2W90-0001 | Firefighting basic design report for package A1 |  |  | Purpose** | IFI | IFI | IFI | IFI
[6 empty] | Rev. | 0 | 0 | 1 | 1
Issue Plan
[6 empty] | Revised Plan | 2018-08-10 | 2018-08-13 | 2018-10-17 | 2018-10-17
[6 empty] | Issue Actual | 2018-08-10 | 2018-08-13 | 2018-10-17 | 2018-10-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00020 | TPSK-LSPA1-T-PC-00020 | TPSK-LSPA1-T-PM-00187 | TPSK-LSPA1-T-PM-00187
[6 empty] | Return Date | 2018-08-20 | 2018-08-20
[6 empty] | Owner Cmmt* | R2 | R2
Category Code: W91 Index/List
Category Code: W92 Procedures & Standards
| PC | OL1-2W92-0001 | Coordination Procedure |  | Class 2 | Rev.: Purpose**; B: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-07-27
[6 empty] | Issue Actual | 2018-07-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PM-00001
[6 empty] | Return Date | 2018-08-22
Owner Cmmt*
| PC | OL1-2W92-0003 | Project Document Coding |  | Class 2 | Rev.: Purpose**; B: IMP; A: IFR; A: IMP
[6 empty] | Rev. | 0 | A | 1
Issue Plan
[6 empty] | Revised Plan |  | 2018-07-27 | 2019-03-14
[6 empty] | Issue Actual |  | 2018-07-27 | 2019-03-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00240 | TPSK-LSPA1-T-PM-00001 | TPSK-LSPA1-T-PC-01041
[6 empty] | Return Date |  | 2018-08-22
Owner Cmmt*
| PC | OL1-2W92-0004 | Document Management Procedure |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2018-08-09 | 2019-03-15
[6 empty] | Issue Actual | 2018-08-09 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00013 | TPSL-LSPA1-T-PC-01062
[6 empty] | Return Date | 2018-08-29
[6 empty] | Owner Cmmt* | R2
| PC | OL1-2W92-0005 | Requirements For Vendor Documentation And Exchange Of Correspondence |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP; A: IMP
[6 empty] | Rev. | A | 0 | 1
Issue Plan
[6 empty] | Revised Plan |  |  | 2019-06-10
[6 empty] | Issue Actual |  |  | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00385 | TPSK-LSPA1-T-PC-00717 | TPSK-LSPA1-T-PC-01790
[6 empty] | Return Date |  |  | 2019-06-27
[6 empty] | Owner Cmmt* |  |  | R2
| PC | OL1-2W92-0006 | TPSK Project Directorate Organization Chart |  | Class 2 | Rev.: Purpose**; B: IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2018-08-07
[6 empty] | Issue Actual | 2018-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00010
Return Date
Owner Cmmt*
| PC | OL1-2W92-0007 | TPSK Roc Organization Chart |  | Class 2 | Rev.: Purpose**; B: IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-09-03
[6 empty] | Issue Actual | 2018-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00030
Return Date
Owner Cmmt*
| PC | OL1-2W92-0009 | Criticality Rating Procedure |  | Class 2 | Rev.: Purpose**; B: IMP; A: IFR
[6 empty] | Rev. | 0 | A
Issue Plan
[6 empty] | Revised Plan |  | 2018-09-06
[6 empty] | Issue Actual |  | 2018-09-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00642 | TPSK-LSPA1-T-PC-00033
[6 empty] | Return Date |  | 2018-10-01
[6 empty] | Owner Cmmt* |  | R2
| PC | OL1-2W92-0010 | Prescriptions For Preparation Of Vendor Data Book |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan |  | 2019-02-07
[6 empty] | Issue Actual |  | 2019-02-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00435 | TPSK-LSPA1-T-PC-00824
[6 empty] | Return Date |  | 2019-05-30
[6 empty] | Owner Cmmt* |  | R2
| PC | OL1-2W92-0011 | TPSK HOC Organization Chart |  | Class 2 | Rev.: Purpose**; B: IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-08
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PM-00146
Return Date
Owner Cmmt*
| PC | OL1-2W92-0012 | ITC Plan |  | Class 2 | Rev.: Purpose**; B: IFR; A: IMP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan |  | 2019-04-24
[6 empty] | Issue Actual |  | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PM-00197 | TPSK-LSPA1-T-PC-01444
Return Date
Owner Cmmt*
| PC | OL1-2W92-0013 | Project Execution Plan |  | Class 2 | Rev.: Purpose**; B: IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-02
[6 empty] | Issue Actual | 2018-10-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00118
Return Date
Owner Cmmt*
| PC | OL1-2W92-0015 | Prescriptions For Preparation Of Manufacturing Data Record Book |  | Class 2 | Rev.: Purpose**; B: IMP; A: IFR; A: IMP
[6 empty] | Rev. | 0 | A | 1
Issue Plan
[6 empty] | Revised Plan |  | 2018-09-13 | 2019-03-22
[6 empty] | Issue Actual |  | 2018-09-13 | 2019-03-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00296 | TPSK-LSPA1-T-PC-00047 | TPSK-LSPA1-T-PC-01135
[6 empty] | Return Date |  |  | 2019-06-16
[6 empty] | Owner Cmmt* |  |  | R2
| PC | OL1-2W92-0016 | Reporting Procedure |  | Class 2 | Rev.: Purpose**; B: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-09-25
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00083
[6 empty] | Return Date | 2019-03-11
[6 empty] | Owner Cmmt* | R2
| PC | OL1-2W92-0018 | Engineering Execution Plan |  | Class 2 | Rev.: Purpose**; B: IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-15
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PM-00170
Return Date
Owner Cmmt*
| PC | OL1-2W92-0019 | Project Control Procedure |  | Class 2 | Rev.: Purpose**; B: IMP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-11
[6 empty] | Issue Actual | 2018-10-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00156
Return Date
Owner Cmmt*
| PC | OL1-2W92-0020 | TPSK SOC Organization Chart |  | Class 2 | Rev.: Purpose**; B: IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-11
[6 empty] | Issue Actual | 2018-10-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00157
Return Date
Owner Cmmt*
| PC | OL1-2W92-0021 | TPSK KLOC Organization Chart |  | Class 2 | Rev.: Purpose**; B: IFI; A: IFI; A: IFI
[6 empty] | Rev. | 0 | 1 | 2
Issue Plan
[6 empty] | Revised Plan | 2018-10-15 | 2019-01-31 | 2019-07-19
[6 empty] | Issue Actual | 2018-10-15 | 2019-01-31 | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00171 | TPSK-LSPA1-T-PC-00761 | TPSK-LSPA1-T-PC-02182
Return Date
Owner Cmmt*
| PC | OL1-2W92-0022 | Computerized Maintenance Management System CMMS |  | Class 2 | Rev.: Purpose**; B: IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00578
Return Date
Owner Cmmt*
| PC | OL1-2W92-0023 | Lsp Document Coding |  | Class 2 | Rev.: Purpose**; B: IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-17
[6 empty] | Issue Actual | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-01674
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | R2
| PC | OL1-2W92-2122 | Project Engineering Plan - Package A1 - Furnaces - Houston Scope (Internal Only) |  | Class 2 | Rev.: Purpose**; B: IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PM-00220
Return Date
Owner Cmmt*
Category Code: W93 Policy , Guidelines & Memo
Category Code: W94 Forms & Templates
Category Code: W95 Progress/Status Reports
Category Code: X71 Appraisal Report for Consultancy Service
Category Code: X72 Appraisal Report for EPC Contractor Work
Category Code: X73 Appraisal Report for Vendor/Supplier
Category Code: X91 Index/List
Category Code: X92 Procedures & Standards
Category Code: X93 Policy , Guidelines & Memo
Category Code: X94 Forms & Templates
Category Code: X95 Progress/Status Reports
Category Code: Y01 Bidding Guideline
Category Code: Y02 Bidding Committee Assignment
Category Code: Y03 Bidding Policy
Category Code: Y04 Pre-Qualification Document
Category Code: Y05 List of qualified Bidders
Category Code: Y06 Bidding Evaluation Criteria for Consultancy Service
Category Code: Y07 Bidding Evaluation Criteria for EPC Contractor
Category Code: Y08 Bidding Evaluation Criteria for Vendor/Supplier
Category Code: Y09 Contractor Selection Plan
Category Code: Y13 ITB Structure
Category Code: Y21 Tender or ITB Document for Consultancy service
Category Code: Y22 Tender or ITB Document for EPC Contractor
Category Code: Y23 Tender or ITB Document for Vendor/Supplier
| ME | OL1-2Y23-2001 | Technical Bid Tabulation for Convection Tubes |  | Class 2 | Rev.: Purpose**; B: IFI; A: IFI
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  | 2018-12-04
[6 empty] | Issue Actual |  | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00404 | TPSK-LSPA1-T-ME-00404
Return Date
Owner Cmmt*
| PC | OL1-2Y23-2002 | Technical Bid Tabulation for Convection Fittings |  | Class 2 | Purpose** | IFI | IFI | IFI | IFI
[6 empty] | Rev. | 1 | 0 | 0 | 1
Issue Plan
[6 empty] | Revised Plan |  |  | 2018-12-20 | 2019-01-07
[6 empty] | Issue Actual |  |  | 2018-12-20 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00591 | TPSK-LSPA1-T-ME-00545 | TPSK-LSPA1-T-ME-00545 | TPSK-LSPA1-T-PC-00591
Return Date
Owner Cmmt*
| ME | OL1-2Y23-2003 | Technical Bid Tabulation for Quench Exchangers |  | Class 2 | Rev.: Purpose**; B: IFI; A: IFI
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  | 2018-11-28
[6 empty] | Issue Actual |  | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00380 | TPSK-LSPA1-T-ME-00380
Return Date
Owner Cmmt*
| PC | OL1-2Y23-2004 | Technical Bid Tabulation for Radiant Coils |  | Class 2 | Rev.: Purpose**; B: IFI; A: IFI
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  | 2018-12-13
[6 empty] | Issue Actual |  | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00490 | TPSK-LSPA1-T-PC-00490
Return Date
Owner Cmmt*
| ME | OL1-2Y23-2006 | Technical Bid Tabulation For Burners |  | Class 2 | Rev.: Purpose**; B: IFI; A: IFI
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-04 | 2019-02-04
[6 empty] | Issue Actual | 2019-02-04 | 2019-02-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00789 | TPSK-LSPA1-T-ME-00789
[6 empty] | Return Date | 2019-02-21 | 2019-02-21
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2Y23-2007 | Technical Bid Tabulation for Cast Intermediate Tube Supports |  | Class 2 | Rev.: Purpose**; B: IFI; A: IFI
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  | 2018-12-17
[6 empty] | Issue Actual |  | 2018-12-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00519 | TPSK-LSPA1-T-ME-00519
Return Date
Owner Cmmt*
| ME | OL1-2Y23-2008 | Technical Bid Tabulation for Peep Doors |  | Class 2 | Rev.: Purpose**; B: IFI; A: IFI
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-06 | 2019-02-06
[6 empty] | Issue Actual | 2019-02-06 | 2019-02-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00813 | TPSK-LSPA1-T-ME-00813
[6 empty] | Return Date | 2019-02-21 | 2019-02-21
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2Y23-2018 | Technical Bid Tabulation for Furnace Steam Drums |  | Class 2 | Rev.: Purpose**; B: IFI; A: IFI
[6 empty] | Rev. | 0 | 0
Issue Plan
[6 empty] | Revised Plan |  | 2018-12-14
[6 empty] | Issue Actual |  | 2018-12-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00500 | TPSK-LSPA1-T-ME-00500
Return Date
Owner Cmmt*
| PC | OL1-2Y23-2201 | Technical Bid Tabulation For Control Valves |  | Class 2 | Rev.: Purpose**; B: IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-11
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-02100
Return Date
Owner Cmmt*
Category Code: Y31 Tender or ITB clarification records for Consultancy service
Category Code: Y32 Tender or ITB clarification records for EPC Contractor
Category Code: Y33 Tender or ITB clarification records for Vendor/Supplier
Category Code: Y41 Proposal Document of Consultancy service bidding
Category Code: Y42 Proposal Document of EPC Contractor bidding
Category Code: Y43 Proposal Document of Vendor/Supplier bidding
Category Code: Y51 Proposal clarification records for Consultancy service
Category Code: Y52 Proposal clarification records for EPC Contractor
Category Code: Y53 Proposal clarification records for Vendor/Supplier
Category Code: Y61 Un-Priced Commerical proposals evaluation report
Category Code: Y62 Priced Commercial proposals evaluation report
Category Code: Y63 Bid Evaluation Report (Technical & Un-priced Commercial proposal )
Category Code: Y64 Bid Evaluation report (Executive Summary)
Category Code: Y65 Nomination of successful bidder for approval
Category Code: Y66 EPC Contract Negotiation, Compliance Report
Category Code: Y71 Appraisal Report for Consultancy Service
Category Code: Y72 Appraisal Report for EPC Contractor Work
Category Code: Y73 Appraisal Report for Vendor/Supplier
Category Code: Y81 Consultancy Service Bidding Records
Category Code: Y82 EPC Contractor Bidding Records
Category Code: Y83 Vendor/Supplier Bidding Records