## CPY_Format
[6 empty] | ABBREVIATION | [7 empty] | DOCUMENT NO. | REV.
[6 empty] | **Revision Purpose of Issued Document |  |  |  | *Owner Feedback (Comment) |  | ***Classification
[6 empty] | IFR = Issue For Review |  | IFF = Issue For Final |  | A1 = App. w/o comments | R1 = No comments | Class 1 = For Approval |  | LSP-2W91-0001 | A
[6 empty] | IFA = Issue For Approval |  | ASB = Issue For As-Built |  | A2 = App. with comments, re-submit not required | R2 = Comments as noted | Class 2 = For Review
[6 empty] | IFC = Issue For Construction |  | AFC = Approved for Construction |  | A3 = App. with comments, re-submit for review |  | Class 3 = For Information
Owner: |  |  |  | Plant Name: |  | IFI = Issue For Information |  | IMP = Issue for Implementation |  | A4 = Not App., re-submit for approval |  |  |  | Issue Date
[6 empty] | IFP = Issue For Planning |  | / Execution
Document Code : | [5 empty] | IFD = Issue For Design |  | CAN = Issue for Cancellation |  | Period for Company's comment |  | __________ | Working Days
Item | Org. | Document No. | Document Name |  | Classification
Category Code: A92
| CO | OL1-2A92-0001 | VARIATION ORDER PROCEDURE |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CO-00035
Return Date
[6 empty] | Owner Cmmt* | Tr
| CO | OL1-2A92-0002 | CAR & THIRD PARTY INSURANCE CLAIM PROCEDURE |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CO-00192
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R2
Category Code: B01
| PC | OL1-2B01-0001 | ENGINEERING AND PROCUREMENT LEVEL 3 SCHEDULE |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00135
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | A3
Category Code: B91
| PC | OL1-2B91-0001 | SIX (6) WEEK LOOK-HEAD SCHEDULE |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00096
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: B92
| PC | OL1-2B92-0001 | PLANNING SCHEDULING AND PROGRESS MEASUREMENT PROCEDURE |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00045
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PC | OL1-2B92-0002 | 90 DAYS LOOK-HEAD SCHEDULE |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00133
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R2
Category Code: C01
| PL | OL1-2C01-0001 | SUBVENDOR LIST FOR COMPRESSOR AND TURBOEXPANDER - ABSTRACT FROM APPROVED VENDOR LIST |  | Class 3 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00134
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: C92
| PL | OL1-2C92-0001 | PROJECT PROCUREMENT EXECUTION PLAN |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00051
Return Date
[6 empty] | Owner Cmmt* | Tr
| PL | OL1-2C92-0002 | PROJECT QCS COORDINATION PROCEDURE |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00046 | TPSK-LSPA1-T-PL-00244
[6 empty] | Return Date | 2018-10-01
[6 empty] | Owner Cmmt* | R2 | Tr
| PL | OL1-2C92-0005 | PROJECT QCS REQUIREMENTS FOR SUPPLIERS |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00046 | TPSK-LSPA1-T-PL-00244
[6 empty] | Return Date | 2018-10-01
[6 empty] | Owner Cmmt* | R2 | Tr
| PL | OL1-2C92-0007 | PRESCRIPTIONS FOR PREPARATION OF DOCUMENTATION PACKAGE FOR TRANSPORTATION |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00048 | TPSK-LSPA1-T-PL-00140
[6 empty] | Return Date | 2018-10-01 | 2018-10-30
[6 empty] | Owner Cmmt* | R2 | R2
| PL | OL1-2C92-0008 | PROJECT QCS EXPEDITING PROCEDURE |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00046
Return Date
[6 empty] | Owner Cmmt* | Tr
| PL | OL1-2C92-0009 | PROJECT QCS INSPECTION PROCEDURE |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00046 | TPSK-LSPA1-T-PL-00244
[6 empty] | Return Date | 2018-10-01
[6 empty] | Owner Cmmt* | R2 | Tr
| PL | OL1-2C92-0013 | SPARE PARTS & SPECIAL TOOLS INSTRUCTIONS |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19 | 2018-10-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00064 | TPSK-LSPA1-T-PL-00119
[6 empty] | Return Date | 2018-09-25
[6 empty] | Owner Cmmt* | R2 | Tr
| PL | OL1-2C92-0014 | PROJECT EXPEDITING AND INSPECTION LEVEL DEFINITION |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00046 | TPSK-LSPA1-T-PL-00244
[6 empty] | Return Date | 2018-10-01
[6 empty] | Owner Cmmt* | R2 | Tr
| PL | OL1-2C92-0015 | TRANSPORTATION PLAN |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00048 | TPSK-LSPA1-T-PL-00177
[6 empty] | Return Date | 2018-10-01 | 2018-10-30
[6 empty] | Owner Cmmt* | R2 | R2
| PL | OL1-2C92-0016 | PARKING MARKING AND SHIPPING INSTRUCTIONS |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00048 | TPSK-LSPA1-T-PL-00140
[6 empty] | Return Date | 2018-10-01 | 2018-10-30
[6 empty] | Owner Cmmt* | R2 | R2
| PL | OL1-2C92-0017 | PROJECT SITE SERVICES CONDITIONS FOR SUPPLIER SPECIALISTS |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-14 | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00051 | TPSK-LSPA1-T-PL-00284
[6 empty] | Return Date | 2018-10-04
[6 empty] | Owner Cmmt* | R2 | Tr
Category Code: C93
| PL | OL1-2C93-0001 | GENERAL SUPPLY RULES FOR SUPPLIER DOCUMENTATION |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00043
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: D92
| CM | OL1-2D92-0001 | CONSTRUCTION SUBCONTRACTING PLAN |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CM-00193
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: E01
Category Code: E02
Category Code: E03
Category Code: E04
| EE | OL1-2E04-6000 | GENERAL DESIGN RULE FOR PACKAGE EQUIPMENT ELECTRICAL SYSTEM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00126
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
Category Code: E08
Category Code: E10
Category Code: E11
Category Code: E12
Category Code: E13
Category Code: E14
Category Code: E15
Category Code: E17
Category Code: E18
Category Code: E19
Category Code: E20
Category Code: E22
Category Code: E23
Category Code: E31
Category Code: E32
Category Code: E34
Category Code: E35
Category Code: E36
Category Code: E42
Category Code: E43
Category Code: E44
Category Code: E50
Category Code: E52
Category Code: E55
Category Code: E60
Category Code: E61
Category Code: E63
Category Code: E92
Category Code: F01
Category Code: F02
Category Code: F03
Category Code: F10
Category Code: F14
Category Code: F20
Category Code: F25
Category Code: F26
Category Code: F30
Category Code: F35
Category Code: F40
Category Code: F41
Category Code: F45
Category Code: F51
Category Code: F52
Category Code: F53
Category Code: F54
Category Code: F55
Category Code: F56
Category Code: F65
Category Code: F75
Category Code: F80
Category Code: G01
| PE | OL1-2G01-0001 | JSD FOR P&ID PREPARATION |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00006
[6 empty] | Return Date | 2018-08-21
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G01-0002 | COLD BOX DESIGN SPECIFICATION |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00123
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G01-0003 | PLATE-FIN EXCHANGER DESIGN SPECIFICATION |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00123
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
Category Code: G02
| PE | OL1-2G02-0001 | PROCESS DESIGN BASIS |  | Class 1 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00002
[6 empty] | Return Date | 2018-08-17
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G02-0002 | EQUIPMENT BASIS OF DESIGN |  | Class 1 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00002
[6 empty] | Return Date | 2018-08-17
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G02-0003 | FLARE AND BLOWDOWN SYSTEM DESIGN BASIS |  | Class 1 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00034
[6 empty] | Return Date | 2018-09-28
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G02-0006 | FURNACE PROCESS BASIS OF DESIGN |  | Class 1 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00004
[6 empty] | Return Date | 2018-08-17
[6 empty] | Owner Cmmt* | A3
Category Code: G05
| PE | OL1-2G05-1001 | AREA BASIS OF DESIGN - 10 FEED PREPARATION |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00011
[6 empty] | Return Date | 2018-08-27
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-2001 | AREA BASIS OF DESIGN - 20-21 QUENCH AND DILUTION STEAM |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00011
[6 empty] | Return Date | 2018-08-27
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-2201 | AREA BASIS OF DESIGN - 22-24 COMPRESSSION TRAIN |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00022
[6 empty] | Return Date | 2018-09-05
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-2301 | AREA BASIS OF DESIGN - 23 CAUSTIC AND SPENT CAUSTIC PRETREATMENT |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00014
[6 empty] | Return Date | 2018-08-31
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-2501 | AREA BASIS OF DESIGN - 25 COLD FRACTIONATION |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00011
[6 empty] | Return Date | 2018-08-27
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-2601 | AREA BASIS OF DESIGN - 26 HOT FRACTIONATION |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00014
[6 empty] | Return Date | 2018-08-31
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-2602 | AREA BASIS OF DESIGN - 262 C3 HYDROGENATION |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00307
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G05-2801 | AREA BASIS OF DESIGN - 28 REFRIGERATION |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00022
[6 empty] | Return Date | 2018-09-05
[6 empty] | Owner Cmmt* | A1
| PE | OL1-2G05-3001 | AREA BASIS OF DESIGN - 30 BDU |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00150
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G05-5001 | AREA BASIS OF DESIGN - 50 ISBL SUPPORTING UTILITIES |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00003
[6 empty] | Return Date | 2018-08-17
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-5301 | AREA BASIS OF DESIGN - 53 COOLING TOWER SYSTEM |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-07-31 | 2018-09-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00003 | TPSK-LSPA1-T-PE-00003
[6 empty] | Return Date | 2018-08-17
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G05-5501 | AREA BASIS OF DESIGN - 55 FLARE SYSTEM |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00016
[6 empty] | Return Date | 2018-08-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-5601 | AREA BASIS OF DESIGN - 56 WASTE WATER TREATMENT SYSTEM |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-07 | 2018-09-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-00011
[6 empty] | Return Date | 2018-08-27 | 2018-10-12
[6 empty] | Owner Cmmt* | A3 | A3
Category Code: G21
Category Code: G22
| PE | OL1-2G22-0001 | FLARE LOAD SUMMARY |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00229
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
Category Code: G30
| PE | OL1-2G30-1000 | PROCESS EQUIPMENT DATASHEET - 10-D-1000 - LPG DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00227
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1001 | PROCESS EQUIPMENT DATASHEET - USC 36M CRACKING FURNACE YIELDS |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-10-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00176 | TPSK-LSPA1-T-PE-00117
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2 | Tr
| PE | OL1-2G30-1003 | PROCESS EQUIPMENT DATASHEET - 10-E-1001 - LPG STEAM VAPORIZER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00179
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1005 | PROCESS EQUIPMENT DATASHEET - 10-E-1005 - LPG FEED HEATER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00176
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1011 | PROCESS EQUIPMENT DATASHEET - 10-C-1100 - USC 36M INDUCED DRAFT FAN |  | Class 2 | Purpose** | IFD | IFR
[6 empty] | Rev. | B | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-09-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00222 | TPSK-LSPA1-T-PE-00090
[6 empty] | Return Date |  | 2018-10-12
[6 empty] | Owner Cmmt* | Tr | R1
| PE | OL1-2G30-1015 | PROCESS EQUIPMENT DATASHEET - 10-E-1015 - LPG SUPERHEATER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00176
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1020 | PROCESS EQUIPMENT DATASHEET - 10-E-1020 - LIQUID FEED HEATER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1051 | PROCESS EQUIPMENT DATASHEET - 10-E-1050 - C2 FEED SUPERHEATER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1101 | PROCESS EQUIPMENT DATASHEET - 10-H-1100 - 36M CRACKING FURNACE YIELDS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00204
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1102 | ANTICIPATED OPERATING CONDITIONS - 10-H-1100 - USC 36M GAS CRACKING FURNACE |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00224
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1106 | PROCESS EQUIPMENT DATASHEET - 10-H-1100 - USC 36M BURNER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00241
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1107 | PROCESS EQUIPMENT DATASHEET - 10-D-1100 - 36M CRACKING FURNACE STEAM DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00159
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1108 | PROCESS EQUIPMENT DATASHEET - 10-E-1100A1 - F6 - USC 36M USX EXCHANGER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1109 | PROCESS EQUIPMENT DATASHEET - 10-E-1110 - USC 36M TLX-1 QUENCH EXCHANGER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1110 | PROCESS EQUIPMENT DATASHEET - 10-E-1120 - USC 36M TLX-2 QUENCH EXCHANGER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1201 | PROCESS EQUIPMENT DATASHEET - 10-H-1200 - 132U CRACKING FURNACE YIELDS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00204
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1202 | ANTICIPATED OPERATING CONDITIONS - 10-H-1200/1600 - USC 132U LIQUID CRACKING FURNACE |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00224
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1206 | PROCESS EQUIPMENT DATASHEET - 10-H-1200 - 1600 - USC 132U BURNER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00241
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1207 | PROCESS EQUIPMENT DATASHEET - 10-D-1200-1600 - 132U CRACKING FURNACE STEAM DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00159
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1208 | PROCESS EQUIPMENT DATASHEET - 10-E-1200A-F - 10-E-1600A-F - USC 132U SLE EXCHANGER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1209 | PROCESS EQUIPMENT DATASHEET - 10-E-1210 - 10-E-1610 - USC 132U TLX QUENCH EXCHANGER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1211 | PROCESS EQUIPMENT DATASHEET - 10-C-1200 1600 - USC 132U INDUCED DRAFT FAN |  | Class 2 | Purpose** | IFD
[6 empty] | Rev. | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00222
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1950 | PROCESS EQUIPMENT DATASHEET - 10-PK-1950 - DECOKE AIR COMPRESSOR PKG |  | Class 2 | Purpose** | IFA | IFD | IFD
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-29 | 2018-09-28 | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00031 | TPSK-LSPA1-T-PE-00114 | TPSK-LSPA1-T-PE-00242
[6 empty] | Return Date | 2018-09-28 | 2018-10-24
[6 empty] | Owner Cmmt* | A3 | R2 | Tr
| PE | OL1-2G30-2000 | PROCESS EQUIPMENT DATASHEET - 10-T-2000 - QUENCH OIL TOWER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00162
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2006 | PROCESS EQUIPMENT DATASHEET - 10-P-2006 A-C - QUENCH OIL PUMPS |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-20 | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00071 | TPSK-LSPA1-T-PE-00202
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2015 | PROCESS EQUIPMENT DATASHEET - 10-E-2008 A-C - LS2 STEAM GENERATORS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00305
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2020 | PROCESS EQUIPMENT DATASHEET - 10-T-2020 - LIGHT FUEL OIL STRIPPER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00238
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2024 | PROCESS EQUIPMENT DATASHEET - 10-P-2026 A-B - LIGHT FUEL OIL PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2026 | PROCESS EQUIPMENT DATASHEET - 10-E-2026 - FO PRODUCT COOLER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00298
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2040 | PROCESS EQUIPMENT DATASHEET - 10-T-2040 - HEAVY FUEL OIL STRIPPER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00162
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2046 | PROCESS EQUIPMENT DATASHEET - 10-P-2046 A-B - HEAVY FUEL OIL PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2048 | PROCESS EQUIPMENT DATASHEET - 10-E-2048 - HEAVY FUEL OIL PRODUCT COOLER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00298
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2100 | PROCESS EQUIPMENT DATASHEET - 10-T-2100 - QUENCH WATER TOWER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00238
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2101 | PROCESS EQUIPMENT DATASHEET - 10-E-2100 A-F - QUENCH WATER COOLER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00143
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2105 | PROCESS EQUIPMENT DATASHEET - 10-P-2105 A-B - QUENCH OIL REFLUX PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2106 | PROCESS EQUIPMENT DATASHEET - 10-P-2106 A-C - QUENCH WATER PUMPS |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-20 | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00070 | TPSK-LSPA1-T-PE-00202
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2120 | PROCESS EQUIPMENT DATASHEET - 10-T-2120 - DISTILLATE STRIPPER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00253
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2125 | PROCESS EQUIPMENT DATASHEET - 10-E-2125 - DISTILLATE STRIPPER REBOILER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00265
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2137 | PROCESS EQUIPMENT DATASHEET - 10-E-2136 - PROCESS WATER STRIPPER FEED HEATER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2140 | PROCESS EQUIPMENT DATASHEET - 10-T-2140 - PROCESS WATER STRIPPER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00189
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2145 | PROCESS EQUIPMENT DATASHEET - 10-E-2145 - PROCESS WATER STRIPPER REBOILER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2146 | PROCESS EQUIPMENT DATASHEET - 10-P-2146 A-B - DSG FEED PUMPS |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-20 | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00069 | TPSK-LSPA1-T-PE-00202
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2147 | PROCESS EQUIPMENT DATASHEET - 10-E-2146 - DSG FEED HEATER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2160 | PROCESS EQUIPMENT DATASHEET - 10-D-2160 - DILUTION STEAM GENERATOR |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00115
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2161 | PROCESS EQUIPMENT DATASHEET - 10-E-2160 - DILUTION STEAM SUPERHEATER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2165 | PROCESS EQUIPMENT DATASHEET - 10-E-2165 A-D DSG REBOILERS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2166 | PROCESS EQUIPMENT DATASHEET - 10-E-2166 - DSG BLOWDOWN COOLER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00209
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2200 | PROCESS EQUIPMENT DATA SHEET - 10-C-2200 - CRACKED GAS COMPRESSOR |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-22 | 2018-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00055
[6 empty] | Return Date | 2018-09-11
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2210 | PROCESS EQUIPMENT DATASHEET - 10-D-2210 - CG 1ST STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2211 | PROCESS EQUIPMENT DATASHEET - 10-E-2210 A-B - CG 1ST STAGE AFTERCOOLERS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00266
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2212 | PROCESS EQUIPMENT DATASHEET - 10-P-2210 A-B - CG 1ST STAGE CONDENSATE PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2220 | PROCESS EQUIPMENT DATASHEET - 10-D-2220 - CG 2ND STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2221 | PROCESS EQUIPMENT DATASHEET - 10-E-2220 A-B - CG 2ND STAGE AFTERCOOLERS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2222 | PROCESS EQUIPMENT DATASHEET - 10-P-2220 A-B - CG 2ND STAGE CONDENSED HC PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2230 | PROCESS EQUIPMENT DATASHEET - 10-D-2230 - CG 3RD STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2231 | PROCESS EQUIPMENT DATASHEET - 10-E-2230 A-B - CG 3RD STAGE AFTERCOOLER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2240 | PROCESS EQUIPMENT DATASHEET - 10-D-2240 - CG 4TH STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00175
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2241 | PROCESS EQUIPMENT DATASHEET - 10-E-2240 A-B - CG 4TH STAGE AFTERCOOLER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2245 | PROCESS EQUIPMENT DATASHEET - 10-D-2245 - CG 4TH STAGE DISCHARGE DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00264
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2300 | PROCESS EQUIPMENT DATASHEET - 10-T-2300 - CAUSTIC TOWER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-18 | 2018-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00060 | TPSK-LSPA1-T-PE-00290
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2301 | PROCESS EQUIPMENT DATASHEET - 10-X-2300 - CAUSTIC DILUTION MIXER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2302 | PROCESS EQUIPMENT DATASHEET - 10-P-2302 A-B - STRONG CAUSTIC CIRCULATING PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2304 | PROCESS EQUIPMENT DATASHEET - 10-P-2304 - INTERMEDIATE CAUSTIC CIRCULATING PUMP |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2305 | PROCESS EQUIPMENT DATASHEET - 10-E-2305 - CAUSTIC TOWER FEED HEATER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00259
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2306 | PROCESS EQUIPMENT DATASHEET - 10-P-2306 A-B - WEAK CAUSTIC CIRCULATING PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2307 | PROCESS EQUIPMENT DATASHEET - 10-F-2306 A-B - WEAK CAUSTIC CIRCULATING FILTERS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00205
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2308 | PROCESS EQUIPMENT DATASHEET - 10-X-2306 - WEAK CAUSTIC - WASH OIL MIXER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2309 | PROCESS EQUIPMENT DATASHEET - 10-D-2305 - YELLOW OIL DRUM |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00102
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2310 | PROCESS EQUIPMENT DATASHEET - 10-D-2310 - SPENT CAUSTIC DEOILING DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00254
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2311 | PROCESS EQUIPMENT DATASHEET - 10-P-2310 A-B - WASH OIL CIRCULATING PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2313 | PROCESS EQUIPMENT DATASHEET - 10-X-2312 - SPENT WASH OIL MIXER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2314 | PROCESS EQUIPMENT DATASHEET - 10-F-2310 A-B - WASH OIL CIRCULATING FILTER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00205
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2315 | PROCESS EQUIPMENT DATASHEET - 10-X-2310 - SPENT CAUSTIC MIXER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2316 | PROCESS EQUIPMENT DATASHEET - 10-D-2316 - SPENT CAUSTIC DEGASSING DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00175
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2319 | PROCESS EQUIPMENT DATASHEET - 10-F-2320 A-B - SPENT CAUSTIC PUMP DISCHARGE FILTERS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00255
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2320 | PROCESS EQUIPMENT DATASHEET - 10-TK-2320 - SPENT CAUSTIC STORAGE TANK |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-20 | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00068 | TPSK-LSPA1-T-PE-00203
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2321 | PROCESS EQUIPMENT DATASHEET - 10-P-2320 A-B - SPENT CAUSTIC PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00252
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2322 | PROCESS EQUIPMENT DATASHEET - 10-D-2322 - SKIM OIL DRUM |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00111
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2330 | PROCESS EQUIPMENT DATASHEET - 10-T-2330 - SPENT CAUSTIC STRIPPER |  | Class 2 | Purpose** | IFA | IFA
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24 | 2018-10-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00073 | TPSK-LSPA1-T-PE-00160
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2331 | PROCESS EQUIPMENT DATASHEET - 10-D-2330 - SPENT CAUSTIC STRIPPER OVHD DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00175
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2350 | PROCESS EQUIPMENT DATASHEET - 10-PK-2350 - WET AIR OXIDATION PKG |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00180
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2390 | PROCESS EQUIPMENT DATASHEET - 10-D-2390 - CAUSTIC DRAIN DRUM |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00102
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2392 | PROCESS EQUIPMENT DATASHEET - 10-D-2392 SPENT CAUSTIC DRAIN DRUM |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00102
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2393 | PROCESS EQUIPMENT DATASHEET - 10-P-2392 - SPENT CAUSTIC DRAIN DRUM PUMP |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00252
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2406 | PROCESS EQUIPMENT DATASHEET - 10-E-2405 - GAS DRYER FEED CHILLER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00239
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2412 | PROCESS EQUIPMENT DATASHEET - 10-E-2412 - HP DEPROPANIZER FEED CHILLER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00239
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2413 | PROCESS EQUIPMENT DATASHEET - 10-E-2413 - HP DEPROP FEED - OVERHEAD EXCHANGER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2416 | PROCESS EQUIPMENT DATASHEET - 10-P-2415 A-B - CG LIQUID DRYER FEED PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2420 | PROCESS EQUIPMENT DATASHEET - 10-D-2420 A-B - CG LIQUID DRYER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00301
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2438 | PROCESS EQUIPMENT DATASHEET - 10-D-2440 - HP DEPROPANIZER REFLUX DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00264
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2439 | PROCESS EQUIPMENT DATASHEET - 10-E-2440 - HP DEPROPANIZER CONDENSER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2440 | PROCESS EQUIPMENT DATASHEET - 10-T-2440 - HP DEPROPANIZER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-14 | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00167
[6 empty] | Return Date | 2018-10-03
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2441 | PROCESS EQUIPMENT DATASHEET - 10-E-2441 - HP DEPROP REFLUX CHILLER NO 2 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2442 | PROCESS EQUIPMENT DATASHEET - 10-E-2442 - HP DEPROP REFLUX CHILLER NO 1 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2445 | PROCESS EQUIPMENT DATASHEET - 10-E-2445 A-B - HP DEPROPANIZER REBOILERS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00267
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2446 | PROCESS EQUIPMENT DATASHEET - 10-E-2446 - LP DEPROPANIZER FEED COOLER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2450 | PROCESS EQUIPMENT DATASHEET - 10-T-2450 - LP DEPROPANIZER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-14 | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00167
[6 empty] | Return Date | 2018-10-03
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2451 | PROCESS EQUIPMENT DATASHEET - 10-E-2450 - LP DEPROPANIZER CONDENSER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00259
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2452 | PROCESS EQUIPMENT DATASHEET - 10-D-2450 - LP DEPROPANIZER REFLUX DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00264
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2453 | PROCESS EQUIPMENT DATASHEET - 10-P-2450 A-B - LP DEPROPANIZER REFLUX-PRODUCT PUMP |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2455 | PROCESS EQUIPMENT DATASHEET - 10-E-2455 A-B - LP DEPROPANIZER REBOILERS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00228
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2461 | PROCESS EQUIPMENT DATASHEET - 10-E-2460 - C2 HYDROG FEED COOLER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2470 | PROCESS EQUIPMENT DATASHEET - 10-R-2470 A-C - C2 HYDROG REACTOR |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00299
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2500 | PROCESS EQUIPMENT DATASHEET - 10-E-2500 - PROPYLENE REFRIG SUBCOOLER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-11 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00039 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-09-28
[6 empty] | Owner Cmmt* | A2 | Tr
| PE | OL1-2G30-2502 | PROCESS EQUIPMENT DATASHEET - 10-E-2502 - DEMETH PREFRAC FEED COOLER NO 1 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2503 | PROCESS EQUIPMENT DATASHEET - 10-E-2504 - DEMETH PREFRAC FEED COOLER NO 2 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2504 | PROCESS EQUIPMENT DATASHEET - 10-D-2504 - DEMETH PREFRAC FEED SEPARATOR NO 1 |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00217 | TPSK-LSPA1-T-PE-00303
[6 empty] | Return Date | 2018-11-07
[6 empty] | Owner Cmmt* | R1 | Tr
| PE | OL1-2G30-2505 | PROCESS EQUIPMENT DATASHEET - 10-E2506 AND 10-E2508 - DEMETH PREFRAC FEED COOLER NO 3 AND NO 4 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2506 | PROCESS EQUIPMENT DATASHEET - 10-D-2506 - DEMETH PREFRAC FEED SEPARATOR NO 2 |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00217 | TPSK-LSPA1-T-PE-00303
[6 empty] | Return Date | 2018-11-07
[6 empty] | Owner Cmmt* | R1 | Tr
| PE | OL1-2G30-2508 | PROCESS EQUIPMENT DATASHEET - 10-D-2508 - DEMETH PREFRAC FEED SEPARATOR NO 3 |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00217 | TPSK-LSPA1-T-PE-00303
[6 empty] | Return Date | 2018-11-07
[6 empty] | Owner Cmmt* | R1 | Tr
| PE | OL1-2G30-2510 | PROCESS EQUIPMENT DATASHEET - 10-T-2510 - 10-D-2510 - DEMETHANIZER PREFRACTIONATOR & REFLUX DRUM |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-26 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00092 | TPSK-LSPA1-T-PE-00306
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2511 | PROCESS EQUIPMENT DATASHEET - 10-E-2510 - DEMETH PREFRAC CONDENSER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2515 | PROCESS EQUIPMENT DATASHEET - 10-E-2515 - DEMETH PREFRAC REBOILER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2520 | PROCESS EQUIPMENT DATASHEET - 10-T-2520 AND 10-D-2520 - RESIDUE GAS RECTIFIER & REFLUX DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00172
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2521 | PROCESS EQUIPMENT DATASHEET - 10-E-2520 - RECTIFIER CONDENSER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2525 | PROCESS EQUIPMENT DATASHEET - 10-D-2525 - HYDROGEN DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218
[6 empty] | Return Date | 2018-11-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2526 | PROCESS EQUIPMENT DATASHEET - 10-E-2525 - HYDROGEN CORE EXCHANGER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2531 | PROCESS EQUIPMENT DATASHEET - 10-E-2530 - DEMETH FEED COOLER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2540 | PROCESS EQUIPMENT DATASHEET - 10-T-2540 - 10-D-2540 - DEMETHANIZER & REFLUX DRUM |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00073 | TPSK-LSPA1-T-PE-00306
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2541 | PROCESS EQUIPMENT DATASHEET - 10-E-2540 - DEMETHANIZER CONDENSER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2545 | PROCESS EQUIPMENT DATASHEET - 10-E-2545 - DEMETHANIZER REBOILER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2546 | PROCESS EQUIPMENT DATASHEET - 10-E-2546 - DEMETHANIZER BOTTOMS COOLER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2548 | PROCESS EQUIPMENT DATASHEET - 10-E-2548 - DEMETHANIZER BOTTOMS VAPORIZER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2550 | PROCESS EQUIPMENT DATASHEET - 10-TX-2550 - 10-C-2550 - RESIDUE GAS EXPANDER - RECOMPRESSOR |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-29 | 2018-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00031 | TPSK-LSPA1-T-PE-00114
[6 empty] | Return Date | 2018-09-28 | 2018-10-24
[6 empty] | Owner Cmmt* | A3 | R1
| PE | OL1-2G30-2551 | PROCESS EQUIPMENT DATASHEET - 10-D-2550 - EXPANDER SUCTION DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218
[6 empty] | Return Date | 2018-11-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2555 | PROCESS EQUIPMENT DATASHEET - 10-D-2555 - EXPANDER DISCHARGE DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218
[6 empty] | Return Date | 2018-11-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2560 | PROCESS EQUIPMENT DATASHEET - 10-PK-2560 - PSA UNIT |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00190
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2570 | PROCESS EQUIPMENT DATASHEET - 10-T-2570 - DEETHANIZER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00191
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2571 | PROCESS EQUIPMENT DATASHEET - 10-E-2570 - DEETHANIZER CONDENSER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2572 | PROCESS EQUIPMENT DATASHEET - 10-D-2570 - DEETHANIZER REFLUX DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00227
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2575 | PROCESS EQUIPMENT DATASHEET - 10-E-2575 - DEETHANIZER REBOILER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-26 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00094 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | A2 | Tr
| PE | OL1-2G30-2576 | PROCESS EQUIPMENT DATASHEET - 10-E-2576 - DEETHANIZER BOTTOMS COOLER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-26 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00094 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | A2 | Tr
| PE | OL1-2G30-2580 | PROCESS EQUIPMENT DATASHEET - 10-T-2580 - C2 TOWER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00162
[6 empty] | Return Date | 2018-10-31
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2582 | PROCESS EQUIPMENT DATASHEET - 10-E-2582 - C2 TOWER REFLUX COOLER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00265
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2585 | PROCESS EQUIPMENT DATASHEET - 10-E-2585 - C2 TOWER BOTTOMS REBOILER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2587 | PROCESS EQUIPMENT DATASHEET - 10-E-2587 - C2 TOWER SIDE REBOILER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2591 | PROCESS EQUIPMENT DATASHEET - 10-E-2856 - ETHYLENE PRODUCT SUBCOOLER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2630 | PROCESS EQUIPMENT DATASHEET - 10-T-2630 - SECONDARY DEETHANIZER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-14 | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00169
[6 empty] | Return Date | 2018-10-03
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2631 | PROCESS EQUIPMENT DATASHEET - 10-E-2630 - SECONDARY DEETH CONDENSER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00074 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | A2 | Tr
| PE | OL1-2G30-2632 | PROCESS EQUIPMENT DATASHEET - 10-D-2630 - SECONDARY DEETH REFLUX DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00287
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2633 | PROCESS EQUIPMENT DATASHEET - 10-P-2630 A-B - SECONDARY DEETH REFLUX PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00277
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2635 | PROCESS EQUIPMENT DATASHEET - 10-E-2635 - SECONDARY DEETH REBOILER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00074 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | A2 | Tr
| PE | OL1-2G30-2636 | PROCESS EQUIPMENT DATASHEET - 10-E-2636 - SECONDARY DEETH BOTTOMS COOLER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00074 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | A2 | Tr
| PE | OL1-2G30-2640 | PROCESS EQUIPMENT DATASHEET - 10-T-2640 - C3 TOWER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00201
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2645 | PROCESS EQUIPMENT DATASHEET - 10-E-2645 A-B - C3 TOWER REBOILERS |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00041 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-01
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2646 | PROCESS EQUIPMENT DATASHEET - 10-P-2646 A-B - PROPANE RECYCLE PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00277
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2647 | PROCESS EQUIPMENT DATASHEET - 10-P-2647 - HP PROPYLENE - OFF SPEC PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00302
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2660 | PROCESS EQUIPMENT DATASHEET - 10-T-2660 - DEBUTANIZER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-14 | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00169
[6 empty] | Return Date | 2018-10-03
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2661 | PROCESS EQUIPMENT DATASHEET - 10-E-2660 - DEBUTANIZER CONDENSER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-26 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00094 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | A2 | Tr
| PE | OL1-2G30-2662 | PROCESS EQUIPMENT DATASHEET - 10-D-2660 - DEBUTANIZER REFLUX DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00287
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2665 | PROCESS EQUIPMENT DATASHEET - 10-E-2665 A-B - DEBUTANIZER REBOILERS |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-27 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00101 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2666 | PROCESS EQUIPMENT DATASHEET - 10-E-2666 - DEBUTANIZER BOTTOMS COOLER |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00112
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2800 | PROCESS EQUIPMENT DATA SHEET - 10-C-2800 - PROPYLENE REFRIG COMPRESSOR |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-22 | 2018-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00055
[6 empty] | Return Date | 2018-09-11
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2801 | PROCESS EQUIPMENT DATASHEET - 10-P-2805 A-B - PROPYLENE PRODUCT PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00277
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2805 | PROCESS EQUIPMENT DATASHEET - 10-D-2805 - C3R SURGE DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218
[6 empty] | Return Date | 2018-11-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2806 | PROCESS EQUIPMENT DATASHEET - 10-E-2805 A-B - C3 REFRIG CONDENSERS |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2807 | PROCESS EQUIPMENT DATASHEET - 10-E-2807 - C3 CHILLER NO 1 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2809 | PROCESS EQUIPMENT DATASHEET - 10-E-2809 - C3 CHILLER NO 2 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00273
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2810 | PROCESS EQUIPMENT DATASHEET - 10-D-2810 - C3R 1ST STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2820 | PROCESS EQUIPMENT DATASHEET - 10-D-2820 - C3R 2ND STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2830 | PROCESS EQUIPMENT DATASHEET - 10-D-2830 - C3R 3RD STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2840 | PROCESS EQUIPMENT DATASHEET - 10-D-2840 - C3R 4TH STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2850 | PROCESS EQUIPMENT DATA SHEET - 10-C-2850 - ETHYLENE REFRIG COMPRESSOR |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-22 | 2018-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00055
[6 empty] | Return Date | 2018-09-11
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2852 | PROCESS EQUIPMENT DATASHEET - 10-E-2852 - C2R DESUPERHEATER NO 1 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2853 | PROCESS EQUIPMENT DATASHEET - 10-E-2853 - C2R DESUPERHEATER NO 2 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2854 | PROCESS EQUIPMENT DATASHEET - 10-D-2855 - C2R SURGE DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218
[6 empty] | Return Date | 2018-11-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2856 | PROCESS EQUIPMENT DATASHEET - 10-E-2855 - C2R CONDENSER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-11 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00039 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-09-28
[6 empty] | Owner Cmmt* | A2 | Tr
| PE | OL1-2G30-2857 | PROCESS EQUIPMENT DATASHEET - 10-E-2857 - HP ETHYLENE PRODUCT VAPORIZER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00041 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-01
[6 empty] | Owner Cmmt* | A1 | Tr
| PE | OL1-2G30-2858 | PROCESS EQUIPMENT DATASHEET - 10-E-2858 - HP ETHYLENE PRODUCT SUPERHEATER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00223
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2860 | PROCESS EQUIPMENT DATASHEET - 10-D-2860 - C2R 1ST STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00208
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2870 | PROCESS EQUIPMENT DATASHEET - 10-D-2870 - C2R 2ND STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218
[6 empty] | Return Date | 2018-11-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2880 | PROCESS EQUIPMENT DATASHEET - 10-D-2880 - C2R 3RD STAGE SUCTION DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00208
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2882 | PROCESS EQUIPMENT DATASHEET - 10-E-2882 - LP ETHYLENE PRODUCT COOLER NO 1 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2884 | PROCESS EQUIPMENT DATASHEET - 10-E-2884 - LP ETHYLENE PRODUCT COOLER NO 2 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G30-2914 | PROCESS EQUIPMENT DATASHEET - 10-PK-2914 - NEUTRALIZATION INJECTION PKG |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00181
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-5100 | PROCESS EQUIPMENT DATASHEET - 10-D-5100 - DEAERATOR |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-11-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00151 | TPSK-LSPA1-T-PE-00151
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2 | Tr
| PE | OL1-2G30-5101 | PROCESS EQUIPMENT DATASHEET - 10-P-5100 A-C - SHP BFW PUMPS |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00251
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R1 | Tr
| PE | OL1-2G30-5102 | PROCESS EQUIPMENT DATASHEET - 10-P-5102 A-B - VLP BFW PUMPS |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00251
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R1 | Tr
| PE | OL1-2G30-5103 | PROCESS EQUIPMENT DATASHEET - 10-E-5100 - DEAERATOR VENT CONDENSER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00230
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5107 | PROCESS EQUIPMENT DATASHEET - 10-E-5112 - SUSPECT COND FLASH DRUM VENT CONDENSER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00243
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5108 | PROCESS EQUIPMENT DATASHEET - 10-E-5110 - SUSPECT CONDENSATE COOLER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00243
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5109 | PROCESS EQUIPMENT DATASHEET - 10-P-5110 A-B - CONDENSATE PUMPS |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00251
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R1 | Tr
| PE | OL1-2G30-5111 | PROCESS EQUIPMENT DATASHEET - 10-P-5112 A-B - SUSPECT CONDENSATE PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00219
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5112 | PROCESS EQUIPMENT DATASHEET - 10-D-5112 - SUSPECT CONDENSATE FLASH DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00274
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-5113 | PROCESS EQUIPMENT DATASHEET - 10-E-5113 - FOUL CONDENSATE COOLER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00230
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5114 | PROCESS EQUIPMENT DATASHEET - 10-D-5114 - LP CONDENSATE FLASH DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00274
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-5121 | PROCESS EQUIPMENT DATASHEET - 10-P-5120 A-B - RAW CONDENSATE PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00219
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5141 | PROCESS EQUIPMENT DATASHEET - 10-P-5140 A-B - INTERMITTENT BLOWDOWN PUMPS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00219
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5201 | PROCESS EQUIPMENT DATASHEET - 10-E-5200 - MP ETHYLENE SUPERHEATER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00275
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-5350 | PROCESS EQUIPMENT DATASHEET - 10-PK-5350 - COOLING TOWER |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25 | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00082 | TPSK-LSPA1-T-PE-00226
[6 empty] | Return Date | 2018-10-13 | 2018-11-14
[6 empty] | Owner Cmmt* | A3 | A1
| PE | OL1-2G30-5352 | PROCESS EQUIPMENT DATASHEET - 10-P-5350 A-H - OLEFINS COOLING WATER PUMPS |  | Class 2 | Purpose** | IFA | IFD | IFD
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24 | 2018-10-24 | 2018-10-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00225 | TPSK-LSPA1-T-PE-00075
[6 empty] | Return Date |  | 2018-11-14 | 2018-11-14
[6 empty] | Owner Cmmt* | Tr | A1 | A1
| PE | OL1-2G30-5355 | PROCESS EQUIPMENT DATASHEET - 10-PK-5355 - SIDE STREAM FILTER PKG |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25 | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00082 | TPSK-LSPA1-T-PE-00226
[6 empty] | Return Date | 2018-10-13 | 2018-11-14
[6 empty] | Owner Cmmt* | A3 | A1
| PE | OL1-2G30-5361 | PROCESS EQUIPMENT DATASHEET - 10-P-5360 A-C - CTU COOLING WATER PUMPS |  | Class 2 | Purpose** | IFA | IFD | IFD
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24 | 2018-10-24 | 2018-10-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00225 | TPSK-LSPA1-T-PE-00075
[6 empty] | Return Date | 2018-10-24 | 2018-11-14 | 2018-11-14
[6 empty] | Owner Cmmt* | A3 | A1 | A1
| PE | OL1-2G30-5500 | PROCESS EQUIPMENT DATASHEET - 10-D-5500 - HOT FLARE DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00168
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5550 | PROCESS EQUIPMENT DATASHEET - 10-D-5550 - HP FLARE KNOCK-OUT DRUM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00142
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5644 | PROCESS EQUIPMENT DATASHEET - 10-PK-5644 - WASTEWATER CPI - IGF PACKAGE |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00281
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-5650 | PROCESS EQUIPMENT DATASHEET - 10-PK-5650 - BIO TREATMENT PKG |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00281
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-5653 | PROCESS EQUIPMENT DATASHEET - 10-PK-5653 - WASTEWATER DUAL MEDIA FILTERS PKG |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00282
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-5670 | PROCESS EQUIPMENT DATASHEET - 10-PK-5670 - DEWATERING PKG |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00281
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1008 | SEE DOCUMENT NUMBER 036909C-1011-PDS-0630-1108 OR OL1-2G30-1108 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1009 | SEE DOCUMENT NUMBER 036909C-1011-PDS-0610-1109 OR OL1-2G30-1109 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-1010 | SEE DOCUMENT NUMBER 036909C-1011-PDS-0610-1110 OR OL1-2G30-1110 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2001 | PROCESS EQUIPMENT DATASHEET - USC 132U CRACKING FURNACE YIELDS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00117
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2008 | SEE DOCUMENT NUMBER 036909C-1012-PDS-0630-1208 OR OL1-2G30-1208 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2009 | SEE DOCUMENT NUMBER 036909C-1012-PDS-0610-1209 OR OL1-2G30-1209 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G30-2011 | PROCESS EQUIPMENT DATA SHEET - 10-C-1200-1600 - USC 132U INDUCED DRAFT FAN |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00090
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
Category Code: G31
Category Code: G32
Category Code: G40
| PE | OL1-2G40-0010 | BLOCK FLOW DIAGRAM - OLEFINS UNIT 10 - 00-GENERAL - OVERALL PLANT SCHEME |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
Category Code: G41
| PE | OL1-2G41-0001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 00-GENERAL - LEGEND & SYMBOLS |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-0002 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 00-GENERAL - DRAWING INDEX |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-1001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 10 - FEED PREPARATION - FEED PREHEAT |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-1003 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 10 - FEED PREPARATION - FEEDSTOCK DISTRIBUTION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-1101 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 11 - FURNACES - RECYCLE GAS CRACKING FURNACE |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-1201 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 12 - FURNACES - LIQUID CRACKING FURNACES |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-1901 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 19 - CRACKING FURNACE UNIT AUX - DECOKE AIR COMPRESSOR |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-1902 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 19 - CRACKING FURNACE UNIT AUX - CHEMICAL STORAGE |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 20 - QUENCH OIL - QUENCH OIL TOWER |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2002 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 20 - QUENCH OIL - HEAVY FUEL OIL STRIPPER |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2101 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 21 - QUENCH WATER - DILUTION STEAM - QUENCH WATER TOWER |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2102 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 21 - QUENCH WATER - DILUTION STEAM - QUENCH WATER CIRCUIT |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2103 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 21 - QUENCH WATER - DILUTION STEAM - DILUTION STEAM GENERATION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2201 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 22 - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2301 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 - CAUSTIC & SPENT CAUSTIC TREATMENT - CAUSTIC TOWER |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2302 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC HANDLING |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2303 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STORAGE |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2304 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC TREATMENT |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2305 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 23 - CAUSTIC & SPENT CAUSTIC TREATMENT - WET AIR OXIDATION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2401 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 - DEHYDRATION - REGEN - DEPROP - C2 HYDROG - CG DEHYDRATION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2402 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 - DEHYDRATION - REGEN - DEPROP - C2 HYDROG - REGENERATION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2403 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 - DEHYDRATION - REGEN - DEPROP - C2 HYDROG - HP DEPROPANIZER |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2404 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 - DEHYDRATION - REGEN - DEPROP - C2 HYDROG - C2 HYDROGENATION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2405 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 24 - DEHYDRATION - REGEN - DEPROP - C2 HYDROG - LP DEPROPANIZER |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2501 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2502 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - RESIDUE GAS SYSTEM |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2503 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - DEMETHANIZER |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2504 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - DEETHANIZER |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2505 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - ETHYLENE FRACTIONATION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2506 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 25 - COLD FRACTIONATION - HYDROGEN PURIFICATION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2601 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 - HOT FRACTIONATION - C3 HYDROGENATION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2602 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 - HOT FRACTIONATION - SECONDARY DEETHANIZER |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2603 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 - HOT FRACTIONATION - PROPYLENE FRACTIONATION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2604 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 26 - HOT FRACTIONATION - DEBUTANIZER |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2701 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 - GHU & C4-C5 HYDROG - GHU-1 REACTOR & DEPENTANIZER |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2702 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 - GHU & C4-C5 HYDROG - GHU-1 RERUN TOWER |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2703 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 - GHU & C4-C5 HYDROG - HYDROG REACTIVATION GAS SYSTEM |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2704 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 27 - GHU & C4-C5 HYDROG - C4-C5 HYDROGENATION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2801 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 - REFRIGERATION SYSTEM - PROPYLENE REFRIGERATION 1 |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2802 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 - REFRIGERATION SYSTEM - PROPYLENE REFRIGERATION 2 |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2803 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 - REFRIGERATION SYSTEM - ETHYLENE REFRIGERATION 1 |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2804 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 28 - REFRIGERATION SYSTEM - ETHYLENE REFRIGERATION 2 |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-2901 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 29 - OLEFINS RECOVERY UNIT AUX - CHEMICAL STORAGE |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-3001 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 - C4 UNIT BDU - PREDISTILLATION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-3002 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 - C4 UNIT BDU - EVAPORATION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-3003 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 - C4 UNIT BDU - RECTIFIER |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-3004 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 - C4 UNIT BDU - DEGASSING |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-3005 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 30 - C4 UNIT BDU - FRACTIONATION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-3101 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 31 - C4 UNIT BDU UTILITIES - SOLVENT REGENERATION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-3102 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 31 - C4 UNIT BDU UTILITIES - STEAM AND CONDENSATE SYSTEM |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G41-3901 | PROCESS FLOW DIAGRAM - OLEFINS UNIT 10 - 39 - C4 UNIT AUX - BDU CHEMICAL STORAGE |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
Category Code: G42
| PE | OL1-2G42-5001 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 50 - WATER SYSTEM - TREATED POTABLE AND DEMIN WATER SYSTEMS |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5101 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 - BFW STEAM AND CONDENSATE SYSTEM - STEAM BALANCE DIAGRAM |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5102 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 - BFW STEAM AND CONDENSATE SYSTEM - CONDENSATE AND BOILER FEEDWATER SYSTEMS |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5103 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 - BFW STEAM AND CONDENSATE SYSTEM - CONDENSATE TREATMENT SYSTEM |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5104 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 51 - BFW STEAM AND CONDENSATE SYSTEM - FURNACE BLOWDOWN SYSTEM |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5201 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 52 - FUEL SYSTEM - FUEL GAS SYSTEM |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5301 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 53 - COOLING WATER SYSTEM - COOLING WATER DIAGRAM |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5311 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 53 - COOLING WATER SYSTEM - COOLING TOWER |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5401 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 54 - AIR AND NITROGEN SYSTEM - PLANT AIR INSTRUMENT AIR AND NITROGEN SYSTEMS |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5501 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 - VENT GAS AND FLARE SYSTEM - FLARE AND BLOWDOWN SYSTEM |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5502 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 - VENT GAS AND FLARE SYSTEM - PROCESS VENT GAS COLLECTION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5511 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 - VENT GAS AND FLARE SYSTEM - HP - LLDPE LP FLARE |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5512 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 55 - VENT GAS AND FLARE SYSTEM - ENCLOSED GROUND FLARE |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5601 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - OILY WASTEWATER COLLECTION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5602 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - SURFACE RUNOFF COLLECTION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5603 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - CRACKER HOLDING BASIN |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5604 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - DOMESTIC WASTEWATER COLLECTION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5610 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - HP FLARE AREA SW & OILY WW COLLECTION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5611 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - OSBL OILY WASTEWATER COLLECTION |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5612 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - OILY WASTEWATER EQUALIZATION TANK |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5613 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - CPI & IGF PACKAGES |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5614 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - BIOTREATMENT PACKAGE |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5615 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - CHECK BASIN |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5616 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - SLUDGE DEWATERING PACKAGE |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5617 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 56 - WASTEWATER - SLOP & OIL SLUDGE |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5901 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 59 - UTILITIES AUXILLIARIES - CHEMICAL STORAGE |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
| PE | OL1-2G42-5911 | UTILITY FLOW DIAGRAM - OLEFINS UNIT 10 - 59 - UTILITIES AUXILLIARIES - COMPLEX U & O CHEMICAL STORAGE |  | Class 1 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3 | Tr
Category Code: G43
Category Code: G44
| PE | OL1-2G44-1001 | OVERALL MATERIAL BALANCE |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00009
[6 empty] | Return Date | 2018-08-23
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G44-1002 | HEAT & MATERIAL BALANCE - DESIGN CASE 6 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00032
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G44-1003 | HEAT & MATERIAL BALANCE - DESIGN CASE 8 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00032
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G44-1004 | HEAT & MATERIAL BALANCE - DESIGN CASE 9 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00032
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G44-1010 | HEAT AND MATERIAL BALANCE - ISBL SUPPORTING UTILITIES |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00128
Return Date
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G44-1011 | HEAT & MATERIAL BALANCE - COOLING WATER SYSTEM |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00116
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: G50
Category Code: G60
Category Code: G61
Category Code: G62
| PE | OL1-2G62-1001 | STEAM BALANCE |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00059
[6 empty] | Return Date | 2018-10-04
[6 empty] | Owner Cmmt* | Tr
| PE | OL1-2G62-1006 | COOLING WATER BALANCE |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00054
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G62-1008 | FUEL BALANCE |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00049
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: G63
Category Code: G64
Category Code: G74
Category Code: G76
Category Code: G91
Category Code: H03
| EE | OL1-2H03-0001 | AIR CONDITIONING VENTILATING AND DUCTING DESIGN |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00165
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R2
Category Code: H10
Category Code: H20
Category Code: H21
Category Code: H40
Category Code: I20
Category Code: I21
Category Code: I30
Category Code: I31
Category Code: I34
Category Code: I35
Category Code: I42
Category Code: I43
Category Code: I44
Category Code: I46
Category Code: I47
Category Code: I48
Category Code: I49
Category Code: I50
Category Code: I51
Category Code: I52
Category Code: I53
Category Code: I54
Category Code: I55
Category Code: I57
Category Code: I61
Category Code: I71
Category Code: I81
Category Code: I84
Category Code: I91
Category Code: I92
Category Code: J92
| HR | OL1-2J92-0002 | EMPLOYEE GRIEVANCE MANAGEMENT PLAN |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-00040
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: J93
| HR | OL1-2J93-0004 | HUMAN RESOURCE POLICY AND PROCEDURES |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-00040
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: J94
| HR | OL1-2J94-0002 | WORKER CODE OF CONDUCT DECLARATION FORM |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-00040
Return Date
[6 empty] | Owner Cmmt* | Tr
| HR | OL1-2J94-0004 | CHILD LABOR RISK ASSESSMENT CHECKLIST |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-00040
Return Date
[6 empty] | Owner Cmmt* | Tr
| HR | OL1-2J94-0005 | FORCED LABOR RISK ASSESSMENT CHECKLIST |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-00040
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: K10
Category Code: K11
Category Code: K12
Category Code: K13
Category Code: K14
Category Code: K15
Category Code: K16
Category Code: K18
Category Code: K20
| CV | OL1-2K20-0001 | CONSTRUCTION STANDARDS FOR REINFORCED CONCRETE WORKS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00088
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
Category Code: K21
| CV | OL1-2K21-0001 | CONSTRUCTION STANDARDS FOR STEEL STRUCTURES |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00088
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
Category Code: K23
| CV | OL1-2K23-0001 | STANDARD CONSTRUCTION DRAWINGS FOR UNDERGROUND SYSTEMS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00088
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
Category Code: K25
Category Code: K27
Category Code: K29
Category Code: K30
Category Code: K31
Category Code: K32
Category Code: K34
Category Code: K35
Category Code: K36
Category Code: K37
Category Code: K38
Category Code: K39
Category Code: K43
| CV | OL1-2K43-0002 | TECHNICAL SPECIFICATION FOR GEOTECHNICAL INVESTIGATION |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-10 | 2018-10-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00147 | TPSK-LSPA1-T-CV-00188
[6 empty] | Return Date |  | 2018-11-01
[6 empty] | Owner Cmmt* | Tr | R1
| CV | OL1-2K43-0003 | PRICE LIST FOR GEOTECHNICAL INVESTIGATION |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-10 | 2018-10-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00147 | TPSK-LSPA1-T-CV-00188
[6 empty] | Return Date |  | 2018-11-01
[6 empty] | Owner Cmmt* | Tr | R1
| CV | OL1-2K43-0004 | SOIL INVESTIGATION PLAN |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-10 | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00145 | TPSK-LSPA1-T-CV-00163
Return Date
[6 empty] | Owner Cmmt* | Tr | Tr
Category Code: K44
Category Code: K54
Category Code: K60
Category Code: K61
Category Code: K92
| CV | OL1-2K92-0001 | GENERAL NOTES FOR UNDERGROUND WORKS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00086
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K92-0002 | GENERAL NOTES FOR PRECAST CONCRETE WORKS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00137
Return Date
[6 empty] | Owner Cmmt* | Tr
| CV | OL1-2K92-0003 | GENERAL NOTES FOR CONCRETE WORKS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00086
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K92-0004 | GENERAL NOTES FOR STEEL STRUCTURES |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00086
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
Category Code: K97
Category Code: M03
| ME | OL1-2M03-1001 | MECHANICAL EQUIPMENT DATASHEET FOR FURNACE ID FAN USC 36M |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00247
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M03-1950 | MECHANICAL EQUIPMENT DATASHEET - DECOKE AIR COMPRESSOR PACKAGE |  | Class 2 | Purpose** | IFA | IFQ | IFQ
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-11 | 2018-11-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00050 | TPSK-LSPA1-T-ME-00161 | TPSK-LSPA1-T-ME-00261
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A3 | Tr | Tr
| ME | OL1-2M03-2001 | MECHANICAL EQUIPMENT DATASHEET FOR FURNACE ID FAN USC 132U |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00247
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M03-2006 | MECHANICAL EQUIPMENT DATA SHEET QUENCH OIL PUMP 10-P-2006 A-B-C |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00235
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M03-2101 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2100 - QUENCH WATER COOLER |  | Class 2 | Purpose** | IFA | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-17 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00058 | TPSK-LSPA1-T-ME-00154
[6 empty] | Return Date | 2018-09-28 | 2018-11-07
[6 empty] | Owner Cmmt* | A3 | R1
| ME | OL1-2M03-2106 | MECHANICAL EQUIPMENT DATA SHEET - QUENCH WATER PUMPS - 10-P-2106 A-B-C |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00236
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M03-2146 | MECHANICAL EQUIPMENT DATA SHEET - DSG FEED PUMPS 10-P-2146 A-B |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00235
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M03-2200 | MECHANICAL EQUIPMENT DATA SHEET FOR CRACKED GAS COMPRESSOR |  | Class 2 | Purpose** | IFA | IFQ | IFQ
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-03 | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00038 | TPSK-LSPA1-T-ME-00127 | TPSK-LSPA1-T-ME-00280
[6 empty] | Return Date | 2018-09-28
[6 empty] | Owner Cmmt* | A3 | Tr | Tr
| ME | OL1-2M03-2300 | MECHANICAL EQUIPMENT DATA SHEET CAUSTIC TOWER 10-T-2300 |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00246
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M03-2440 | MECHANICAL EQUIPMENT DATASHEET FOR HP DEPROPANIZER |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00215
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M03-2450 | MECHANICAL EQUIPMENT DATASHEET - LP DEPROPANIZER |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-16 | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00183 | TPSK-LSPA1-T-ME-00283
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | A3 | Tr
| ME | OL1-2M03-2453 | MECHANICAL EQUIPMENT DATASHEET - LP DEPROPANIZER REFLUX-PRODUCT PUMP |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00294
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M03-2510 | MECHANICAL EQUIPMENT DATA SHEET - DEMETHANIZER PREFRACTIONATOR AND REFLUX DRUM |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00260
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M03-2540 | MECHANICAL EQUIPMENT DATA SHEET - DEMETHANIZER AND DEMETHANIZER REFLUX DRUM |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00304
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M03-2550 | MECHANICAL EQUIPMENT DATASHEET FOR RESIDUE GAS EXPANDER-RECOMPRESSOR |  | Class 2 | Purpose** | IFA | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00050 | TPSK-LSPA1-T-ME-00130
[6 empty] | Return Date | 2018-10-02 | 2018-10-26
[6 empty] | Owner Cmmt* | A3 | A3
| ME | OL1-2M03-2571 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2570 - DEETHANIZER CONDENSER |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00310
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M03-2660 | MECHANICAL EQUIPMENT DATASHEET - DEBUTANIZER |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23 | 2018-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00215 | TPSK-LSPA1-T-ME-00288
Return Date
[6 empty] | Owner Cmmt* | Tr | Tr
| ME | OL1-2M03-2800 | MECHANICAL EQUIPMENT DATA SHEET FOR PROPYLENE REFRIGERATION COMPRESSOR |  | Class 2 | Purpose** | IFA | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00038 | TPSK-LSPA1-T-ME-00127
[6 empty] | Return Date | 2018-09-28
[6 empty] | Owner Cmmt* | A3 | Tr
| ME | OL1-2M03-2850 | MECHANICAL EQUIPMENT DATA SHEET FOR ETHYLENE REFRIGERATION COMPRESSOR |  | Class 2 | Purpose** | IFA | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00038 | TPSK-LSPA1-T-ME-00127
[6 empty] | Return Date | 2018-09-28 | 2018-10-26
[6 empty] | Owner Cmmt* | A3 | A3
| ME | OL1-2M03-5101 | MECHANICAL EQUIPMENT DATA SHEET FOR SHP BFW PUMPS |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-27 | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00236 | TPSK-LSPA1-T-ME-00236
Return Date
[6 empty] | Owner Cmmt* | Tr | Tr
| ME | OL1-2M03-5102 | MECHANICAL EQUIPMENT DATA SHEET VLP BFW PUMPS - 10-P-5102 A-B |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00236
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M03-5109 | MECHANICAL EQUIPMENT DATA SHEET - CONDENSATE PUMPS 10-P-5110 A-B |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00235
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M03-5350 | MECHANICAL EQUIPMENT DATASHEET FOR COOLING TOWER |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00276
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M03-5352 | MECHANICAL EQUIPMENT DATA SHEET FOR OLEFINS COOLING WATER PUMPS 10-P-5350 A-H |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00210
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M03-5355 | MECHANICAL EQUIPMENT DATASHEET FOR SIDE STREAM FILTER PACKAGE |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00248
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M03-5361 | MECHANICAL EQUIPMENT DATA SHEET FOR CTU COOLING WATER PUMPS 10-P-5360 A-B-C |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00210
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
Category Code: M04
Category Code: M06
| ME | OL1-2M06-1201 | USC 36M RECYCLE FURNACE RADIANT COIL ASSEMBLY AND DETAILS |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00062
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M06-1202 | USC 36M RECYCLE FURNACE TRANSFER LINE AND CLEAN-OUT DETAILS |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00062
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M06-1203 | USC 36M RECYCLE FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00062
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M06-1204 | USC 36M RECYCLE FURNACE FABRICATION ASSEMBLY OF CONVECTION COILS FINNED TUBES AND BILL OF MATERIAL |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00182
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M06-1301 | USC 36M RECYCLE FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00286
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M06-1302 | USC 36M RECYCLE FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00286
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M06-2201 | USC 132U FURNACE RADIANT COIL ASSEMBLY AND DETAILS |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00062
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M06-2202 | USC 132U CRACKING FURNACE TRANSFER LINES AND CLEAN-OUT DETAILS |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00062
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M06-2203 | USC 132U CRACKING FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00062
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M06-2204 | USC 132U CRACKING FURNACE FABRICATIN ASSEMBLY OF CONVECTION COILS FINNED TUBES AND BILL OF MATERIAL |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00182
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M06-2301 | USC 132U CRACKING FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00289
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M06-2302 | USC 132U CRACKING FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00289
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: M07
| ME | OL1-2M07-0008 | INSPECTION AND TEST PLAN FOR CENTRIFUGAL COMPRESSORS STEAM TURBINE DRIVEN |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00136
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M07-0012 | INSPECTION AND TEST PLAN FOR RESIDUE GAS EXPANDER/RECOMPRESSOR |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00139
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M07-0014 | INSPECTION AND TEST PLAN FOR INTEGRALLY GEARED DECOKING AIR COMPRESSORS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00198
[6 empty] | Return Date | 2018-11-07
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M07-0015 | INSPECTION AND TEST PLAN FOR API CENTRIFUGAL PUMPS - LLI |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00257
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M07-0055 | INSPECTION AND TEST PLAN FOR TRAYS FOR COLUMNS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00300
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M07-0064 | INSPECTION AND TEST PLAN FOR PLATE AND FRAME HEAT EXCHANGERS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00124
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M07-0066 | INSPECTION AND TEST PLAN FOR COLD BOX AND CORE EXCHANGERS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00125
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M07-0075 | INSPECTION AND TEST PLAN FOR MD TRAYS FOR COLUMNS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00278
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M07-0104 | INSPECTION AND TEST PLAN FOR COOLING TOWER |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00276
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M07-0108 | INSPECTION AND TEST PLAN FOR DEAREATOR |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00270
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M07-2002 | INSPECTION AND TEST PLAN FOR FURNACE CONVECTION FITTINGS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00207
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M07-2003 | INSPECTION AND TEST PLAN FOR QUENCH EXCHANGERS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00233
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M07-2004 | INSPECTION AND TEST PLAN FOR RADIANT COIL ASSEMBLIES |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00063
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M07-2005 | INSPECTION AND TEST PLAN FOR FURNACE ID FANS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00269
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M07-2018 | INSPECTION AND TEST PLAN FOR FURNACE STEAM DRUMS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00263
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M07-2001 | INSPECTION AND TEST PLAN FOR CONVECTION TUBES |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00044
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | Tr
Category Code: M55
| ME | OL1-2M55-0008 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSORS STEAM TURBINE DRIVEN |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00136
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M55-0012 | MATERIAL REQUISITION FOR RESIDUE GAS EXPANDER/RECOMPRESSOR |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00139
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M55-0014 | MATERIAL REQUISITION FOR INTEGRALLY GEARED DECOKING AIR COMPRESSORS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00198
[6 empty] | Return Date | 2018-11-07
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M55-0015 | MATERIAL REQUISITION FOR API CENTRIFUGAL PUMPS - LLI |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00257
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M55-0055 | MATERIAL REQUISITION FOR TRAYS FOR COLUMNS REQUISITION FOR INQUIRY |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00300
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M55-0064 | MATERIAL REQUISITION FOR PLATE AND FRAME HEAT EXCHANGERS REQUISITION FOR INQUIRY |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00124
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M55-0066 | MATERIAL REQUISITION FOR COLD BOX AND CORE EXCHANGERS REQUISITION FOR INQUIRY |  | Class 3 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00125 | TPSK-LSPA1-T-ME-00153
[6 empty] | Return Date | 2018-10-24 | 2018-11-02
[6 empty] | Owner Cmmt* | Tr | R1
| ME | OL1-2M55-0075 | MATERIAL REQUISITION FOR MD TRAYS FOR COLUMNS REQUISITION FOR INQUIRY |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00278
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M55-0108 | MATERIAL REQUISITION FOR DEAREATOR |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00270
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M55-0109 | MATERIAL REQUISITION FOR SIDE STREAM FILTER PACKAGE |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00248
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M55-2002 | MATERIAL REQUISITION FOR FURNACE CONVECTION FITTINGS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00207
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M55-2003 | MATERIAL REQUISITION FOR QUENCH EXCHANGERS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00233
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M55-2004 | MATERIAL REQUISITION FOR RADIANT COIL ASSEMBLIES |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00063
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M55-2005 | MATERIAL REQUISITION FOR FURNACE ID FANS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00269
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M55-2018 | MATERIAL REQUISITION FOR FURNACE STEAM DRUMS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00263
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M55-2001 | MATERIAL REQUISITION FOR CONVECTION TUBES |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00044
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: M56
| ME | OL1-2M56-0008 | SCOPE OF SUPPLY FOR CENTRIFUGAL COMPRESSORS STEAM TURBINE DRIVEN |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00136
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M56-0012 | SCOPE OF SUPPLY FOR RESIDUE GAS EXPANDER/RECOMPRESSOR |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00139
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M56-0014 | SCOPE OF SUPPLY FOR INTEGRALLY GEARED DECOKING AIR COMPRESSORS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00198
[6 empty] | Return Date | 2018-11-07
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M56-0015 | SCOPE OF SUPPLY FOR API CENTRIFUGAL PUMPS - LLI |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00257
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M56-0055 | SCOPE OF SUPPLY FOR TRAYS FOR COLUMNS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00300
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M56-0064 | SCOPE OF SUPPLY FOR PLATE AND FRAME HEAT EXCHANGERS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00124
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M56-0066 | SCOPE OF SUPPLY FOR COLD BOX AND CORE EXCHANGERS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00125
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M56-0075 | SCOPE OF SUPPLY FOR MD TRAYS FOR COLUMNS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00278
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M56-0104 | SCOPE OF SUPPLY FOR COOLING TOWER |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00276
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M56-0108 | SCOPE OF SUPPLY FOR DEAREATOR |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00270
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M56-0109 | SCOPE OF SUPPLY FOR SIDE STREAM FILTER PACKAGE |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00248
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M56-2002 | SCOPE OF SUPPLY FOR FURNACE CONVECTION FITTINGS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00207
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M56-2003 | SCOPE OF SUPPLY FOR QUENCH EXCHANGERS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00233
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M56-2004 | SCOPE OF SUPPLY FOR RADIANT COIL ASSEMBLIES |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00063
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M56-2005 | SCOPE OF SUPPLY FOR FURNACE ID FANS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00269
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M56-2001 | MATERIAL REQUISITION SCOPE OF SUPPLY FOR CONVECTION TUBES |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00044
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: M57
| ME | OL1-2M57-0008 | PARTICULAR TECHNICAL SPECIFICATION FOR CENTRIFUGAL COMPRESSORS STEAM TURBINE DRIVEN |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00136
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M57-0012 | PARTICULAR TECHNICAL SPECIFICATION FOR RESIDUE GAS EXPANDER/RECOMPRESSOR |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00139
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M57-0014 | PARTICULAR TECHNICAL SPECIFICATION FOR INTEGRALLY GEARED DECOKING AIR COMPRESSORS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00198
[6 empty] | Return Date | 2018-11-07
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M57-0015 | PARTICULAR TECHNICAL SPECIFICATION FOR API CENTRIFUGAL PUMPS - LLI |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00257
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M57-0055 | PARTICULAR TECHNICAL SPECIFICATION FOR TRAYS FOR COLUMNS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00300
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M57-0064 | PARTICULAR TECHNICAL SPECIFICATION FOR PLATE AND FRAME HEAT EXCHANGERS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00124
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M57-0066 | PARTICULAR TECHNICAL SPECIFICATION FOR COLD BOX AND CORE EXCHANGERS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00125
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M57-0075 | PARTICULAR TECHNICAL SPECIFICATION FOR MD TRAYS FOR COLUMNS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00278
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M57-0104 | PARTICULAR TECHNICAL SPECIFICATION FOR COOLING TOWER |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00276
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M57-0108 | PARTICULAR TECHNICAL SPECIFICATION FOR DEAERATOR |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00270
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M57-0109 | PARTICULAR TECHNICAL SPECIFICATION FOR SIDE STEAM FILTER PACKAGE |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00248
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M57-2002 | PARTICULAR TECHNICAL SPECIFICATION FOR FURNACE CONVECTION FITTINGS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00207
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M57-2003 | PARTICULAR TECHANICAL SPECIFICATION FOR QUENCH EXCHANGERS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00233
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M57-2004 | PARTICULAR TECHNICAL SPECIFICATION FOR RADIANT COIL ASSEMBLIES |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00063
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M57-2005 | PARTICULAR TECHNICAL SPECIFICATION FOR FURNACE ID FANS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00269
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M57-2001 | TECHNICAL NOTES FOR CONVECTION TUBES MATERIAL REQUISITION |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00044
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: M58
| ME | OL1-2M58-0008 | DEVIATION LIST FOR CENTRIFUGAL COMPRESSORS STEAM TURBINE DRIVEN |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00136
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M58-0012 | DEVIATION LIST FOR RESIDUE GAS EXPANDER/RECOMPRESSOR |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00139
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M58-0014 | DEVIATION LIST FOR INTEGRALLY GEARED DECOKING AIR COMPRESSORS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00198
[6 empty] | Return Date | 2018-11-07
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M58-0015 | DEVIATION LIST FOR API CENTRIFUGAL PUMPS - LLI |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00257
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M58-0055 | DEVIATION LIST FOR TRAYS FOR COLUMN |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00300
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M58-0064 | DEVIATION LIST FOR PLATE AND FRAME HEAT EXCHANGERS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00124
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M58-0066 | DEVIATION LIST FOR COLD BOX AND CORE EXCHANGERS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00125
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M58-0075 | DEVIATION LIST FOR MD TRAYS FOR COLUMNS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00278
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M58-0104 | DEVIATION LIST |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00276
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M58-0108 | DEVIATION LIST FOR DEAERATOR |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00270
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M58-0109 | DEVIATION LIST FOR SIDE STREAM FILTER PACKAGE |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00248
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M58-2005 | DEVIATION LIST FOR FURNACE ID FANS |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00269
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: M91
| ME | OL1-2M91-1001 | APPROVED VENDOR LIST FOR 36M AND 132U FURNACE |  | Class 3 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00211
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: M92
| ME | OL1-2M92-2003 | PROJECT SPECIFICATION FOR CAST INTERMEDIATE TUBE SUPPORTS |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00232
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2M92-2009 | PROJECT SPECIFICATION FOR FURNACE BURNERS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00231
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M92-2001 | PROJECT SPECIFICATION FOR CENTRIFUGALLY CAST TUBES FOR RADIANT COILS AND TRANSFER LINES IN CRACKING FURNACES |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00037
[6 empty] | Return Date | 2018-09-25
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M92-2002 | PROJECT SPECIFICATION FOR STATICALLY CAST FITTINGS FOR RADIANT COILS AND TRANSFER LINES IN CRACKING FURNACES |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00037
[6 empty] | Return Date | 2018-09-25
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M92-2007 | PROJECT SPECIFICATION FOR SLE AND USX EXCHANGERS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00067
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M92-2008 | PROJECT SPECIFICATION FOR TRANSFER LINE EXCHANGERS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00067
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R2
Category Code: O01
Category Code: O04
Category Code: O06
Category Code: O07
Category Code: O08
Category Code: O09
Category Code: O10
Category Code: O20
Category Code: O67
Category Code: O71
Category Code: O75
Category Code: O80
Category Code: O92
| PE | OL1-2O92-0001 | INSTRUCTIONS TO SUPPLIER FOR FILLING-UP OF SPARE PARTS AND INTERCHANGEABILITY RECORD (SPIR FORM) |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00095
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: P03
Category Code: P05
Category Code: P06
Category Code: P20
Category Code: P30
Category Code: P40
Category Code: P55
Category Code: P91
Category Code: P92
| MP | OL1-2P92-0002 | PIPING DESIGN STANDARD DRAWINGS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00012
[6 empty] | Return Date | 2018-09-26
[6 empty] | Owner Cmmt* | A4
| MP | OL1-2P92-0003 | PIPING CONSTRUCTION DRAWING |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00012
[6 empty] | Return Date | 2018-09-26
[6 empty] | Owner Cmmt* | A4
Category Code: Q92
| QM | OL1-2Q92-0001 | OVERALL PROJECT QUALITY PLAN |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-QM-00072
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R2
| QM | OL1-2Q92-0002 | CONFIDENTIALITY PLAN |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-QM-00199
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: R02
| CV | OL1-2R02-0001 | JOB DESIGN SPECIFICATION FOR UNDERGROUND SYSTEMS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00087
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2R02-0004 | JOB DESIGN SPECIFICATION FOR FOUNDATIONS AND STRUCTURES |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00087
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2R02-0005 | BUILDINGS DESIGN AND CONSTRUCTION |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00158
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: R03
| ME | OL1-2R03-0001 | JO B SPECIFICATION FOR WELDINGS AND NDE OF PRESSURE VESSELS AND HEAT EXCHANGERS |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00029
[6 empty] | Return Date | 2018-09-19
[6 empty] | Owner Cmmt* | A4
| ME | OL1-2R03-0002 | JOB SPECIFICATION FOR MATERIALS IN SOUR SERVICES |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00029
[6 empty] | Return Date | 2018-09-19
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0003 | JOB SPECIFICATION FOR SUPPLY POSITIVE ALLOY MATERIAL IDENTIFICATION OF EQUIPMENT AND PIPING |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00029
[6 empty] | Return Date | 2018-09-19
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0004 | JOB SPECIFICATION FOR WELDING AND NDE STORAGE TANKS |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00029
[6 empty] | Return Date | 2018-09-19
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0005 | ME-005 DOUBLE JACKET PIPE HEAT EXCHANGERS FOR 36M AND 132U FURNACE |  | Class 3 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00212
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2R03-0006 | PLATE HEAT EXCHANGER |  | Class 3 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00042
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2R03-0010 | ME-010 CENTRIFUGAL PUMP |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00078
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0013 | ME-013 DIESEL ENGINE |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00196
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0014 | ME-014 CENTRIFUGAL COMPRESSOR |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00065
[6 empty] | Return Date | 2018-10-10
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0016 | ME-016 CENTRIFUGAL COMPRESSOR FOR PA/IA SERVISE |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00164
[6 empty] | Return Date | 2018-11-07
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0018 | ME-018 GENERAL PURPOSE STEAM TURBINES |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00078
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0019 | ME-019 LUBE OIL UNIT AND SEAL OIL SYSTEM |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00065
[6 empty] | Return Date | 2018-10-10
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0020 | ME-020 SPECIAL PURPOSE STEAM TTURBINES |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00078
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0022 | ME-022 SPECIAL PURPOSE GEAR |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00166
[6 empty] | Return Date | 2018-11-07
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0028 | ME-028 MECHANICAL SEAL |  | Class 3 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00057
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2R03-0029 | ME-029 CENTRIFUGAL BLOWER FOR 36M AND 132U FURNACE |  | Class 3 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00185
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0050 | JOB SPECIFICATION FOR DESIGN OF PRESSURE & ATMOSPHERIC STATIC EQUIPMENT |  | Class 3 | Purpose** | IFR | IFR | IMP
[6 empty] | Rev. | A | B | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-10 | 2018-09-25 | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00017 | TPSK-LSPA1-T-ME-00084 | TPSK-LSPA1-T-ME-00245
[6 empty] | Return Date | 2018-08-27 | 2018-10-24
[6 empty] | Owner Cmmt* | A3 | R1 | Tr
| ME | OL1-2R03-0051 | JOB SPECIFICATION FOR SUPPLY OF PRESSURE VESSELS |  | Class 3 | Purpose** | IFR | IFR | IMP
[6 empty] | Rev. | A | B | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-13 | 2018-09-25 | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00021 | TPSK-LSPA1-T-ME-00084 | TPSK-LSPA1-T-ME-00249
[6 empty] | Return Date | 2018-08-27 | 2018-10-24
[6 empty] | Owner Cmmt* | A4 | R1 | Tr
| ME | OL1-2R03-0052 | JOB SPECIFICATION FOR SUPPLY OF COLUMN INTERNALS |  | Class 3 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-10 | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00017 | TPSK-LSPA1-T-ME-00081
[6 empty] | Return Date | 2018-08-27 | 2018-10-24
[6 empty] | Owner Cmmt* | A3 | Tr
| ME | OL1-2R03-0053 | JOB SPECIFICATION FOR SUPPLY OF EQUIPMENT LADDERS AND PLATFORMS |  | Class 3 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-10 | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00017 | TPSK-LSPA1-T-ME-00081
[6 empty] | Return Date | 2018-08-27 | 2018-10-24
[6 empty] | Owner Cmmt* | A4 | Tr
| ME | OL1-2R03-0054 | CONSTRUCTION STANDARDS FOR PRESSURE EQUIPMENT |  | Class 3 | Purpose** | IFR | IFR | IMP
[6 empty] | Rev. | A | B | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-10 | 2018-09-25 | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00018 | TPSK-LSPA1-T-ME-00084 | TPSK-LSPA1-T-ME-00256
[6 empty] | Return Date | 2018-08-27 | 2018-10-24
[6 empty] | Owner Cmmt* | A3 | R1 | Tr
| ME | OL1-2R03-0055 | CONSTRUCTION STANDARDS FOR LADDERS & PLATFORMS ATTACHED TO PRESSURE EQUIPMENT |  | Class 3 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00120
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2R03-0102 | MARKING FOR VESSEL & HEAT EXCHANGER |  | Class 3 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00042
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2R03-0104 | ME-008 COOLING WATER |  | Class 3 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00276
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2R03-0500 | ME-050 CENTRIFUGAL PUMP (NON API) |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00308
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2R03-055 | CONSTRUCTION STANDARDS FOR LADDERS AND PLATFORMS ATTACHED TO PRESSURE EQUIPMENT |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00027
[6 empty] | Return Date | 2018-09-18
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2R03-1001 | ME-001 PRESSURE VESSEL FOR 36M AND 132U FURNACE |  | Class 3 | Purpose** | IFE
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00262
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2R03-1004 | ME-004 SHELL AND TUBE HEAT EXCHANGERS FOR 36M AND 132U FURNACE |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00221
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: R04
| MP | OL1-2R04-0002 | JOB SPECIFICATION FOR DETAIL DESIGN PIPING |  | Class 3 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-08 | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00012 | TPSK-LSPA1-T-MP-00012
[6 empty] | Return Date | 2018-09-26
[6 empty] | Owner Cmmt* | A4 | Tr
| MP | OL1-2R04-0003 | JOB DESIGN SPECIFICATION FOR THERMAL INSULATION (HOT SERVICE) |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00024
[6 empty] | Return Date | 2018-09-12
[6 empty] | Owner Cmmt* | A4
| MP | OL1-2R04-0004 | JOB DESIGN SPECIFICATION FOR THERMAL INSULATION (COLD SERVICE) |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00024
[6 empty] | Return Date | 2018-09-12
[6 empty] | Owner Cmmt* | A4
| MP | OL1-2R04-0005 | JOB DESIGN SPECIFICATION FOR PAINTING |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00024
[6 empty] | Return Date | 2018-09-12
[6 empty] | Owner Cmmt* | A4
| MP | OL1-2R04-0006 | GENERAL SUPPLY SPECIFICATION FOR PIPING MATERIAL |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00028
[6 empty] | Return Date | 2018-09-18
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2R04-0007 | PIP-007 MARKING OF PIPING MATERIAL FOR 36M AND 132U FURNACE |  | Class 3 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00213
Return Date
[6 empty] | Owner Cmmt* | Tr
| MP | OL1-2R04-0011 | JOB SUPPLY SPECIFICATION FOR PIPES |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00028
[6 empty] | Return Date | 2018-09-18
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2R04-0013 | JOB SUPPLY SPECIFICATION FOR BUTT WELDING FITTINGS |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00028
[6 empty] | Return Date | 2018-09-18
[6 empty] | Owner Cmmt* | A4
| MP | OL1-2R04-0014 | JOB SUPPLY SPECIFICATION FOR FORGED FITTINGS |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00028
[6 empty] | Return Date | 2018-09-18
[6 empty] | Owner Cmmt* | A4
| MP | OL1-2R04-0015 | JOB SUPPLY SPECIFICATION FOR FLANGES |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00028
[6 empty] | Return Date | 2018-09-18
[6 empty] | Owner Cmmt* | A4
| MP | OL1-2R04-0031 | JOB DESIGN SPECIFICATION FOR STEAM TRACING |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00012
[6 empty] | Return Date | 2018-09-26
[6 empty] | Owner Cmmt* | A4
| MP | OL1-2R04-1004 | PIP-004 PIPING WELDING SPECIFICATION FOR 36M AND 132U FURNACE |  | Class 3 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00184
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: R05
| EE | OL1-2R05-0003 | OIL FILLED DISTRIBUTION TRANSFORMER |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0006 | MEDIUM VOLTAGE SWITCHGEAR |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0007 | LOW VOLTAGE DISTRIBUTION PANEL |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00309
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0008 | LOW VOLTAGE SWITCHGEAR AND MOTOR CONTROL CENTER |  | Class 2 | Purpose** | IFE
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00309
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0010 | ELECTRICAL MOTOS UP TO 300 KW |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00079
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0011 | ELECTRICAL MOTORS GREATER THAN 300 KW |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00293
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0012 | UNINTERRUPTIBLE POWER SUPPLIES |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0014 | LIGHTING SYSTEM |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00258
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0015 | EARTHING AND LIGHTNING PROTECTION |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00258
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0016 | CATHODIC PROTECTION |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0017 | DIESEL ENGINE GENERATOR |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0021 | POWER CAPACITORS |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0022 | MISCELLANEOUS EQUIPMENT |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0023 | LOW VOLTAGE VARIABLE VOLTAGE VARIABLE FREQUENCY SYSTEM |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0029 | FUNCTIONAL AND SCHEMATIC DIAGRAM |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00258
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0037 | ELECTRICAL HEAT TRACING |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00079
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0038 | LOW VOLTAGE BUS DUCT |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0040 | MEDIUM VOLTAGE VARIABLE VOLTAGE VARIABLE FREQUENCY SYSTEM |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
[6 empty] | Owner Cmmt* | Tr
| EE | OL1-2R05-0042 | GENERAL DESIGN RULE FOR PACKAGE EQUIPMENT ELECTRICAL SYSTEM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | 2018-08-24
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2R05-0043 | GENERAL DESIGN RULE FOR SMARTPLANT ELECTRICAL |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | 2018-08-24
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2R05-0044 | COORDINATION PROCEDURE FOR SMARTPLANT ELECTRICAL |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | 2018-08-24
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2R05-0045 | COORDINATION PROCEDURE FOR ETAP |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | 2018-08-24
[6 empty] | Owner Cmmt* | A3
Category Code: R06
| IE | OL1-2R06-0001 | INSTRUMENT GENERAL DESIGN |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0003 | FLOW MEASUREMENT |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00122
Return Date
[6 empty] | Owner Cmmt* | Tr
| IE | OL1-2R06-0005 | LEVEL MEASUREMENT |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0006 | PRESSURE MEASUREMENT |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0007 | TEMPERATURE MEASUREMENT |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0008 | FINAL CONTROL ELEMENT |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0010 | INSTRUMENT CONSTRUCTION MATERIAL |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00122
Return Date
[6 empty] | Owner Cmmt* | Tr
| IE | OL1-2R06-0013 | MACHINERY MONITORING SYSTEM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0016 | INSTRUMENT CABINET |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0017 | INTEGRATED TURBINE AND COMPRESSOR CONTROL SYSTEM |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00148
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0021 | PRESSURE SAFETY VALVE |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00122
Return Date
[6 empty] | Owner Cmmt* | Tr
| IE | OL1-2R06-0022 | INSTRUMENT NUMBERING |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2R06-0023 | INSTRUMENT INSPECTION AND TEST PLAN |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00122
Return Date
[6 empty] | Owner Cmmt* | Tr
| IE | OL1-2R06-0024 | GENERAL DESIGN RULES FOR SMARTPLANT INSTRUMENTATION SETUP |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28 | 2018-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00109 | TPSK-LSPA1-T-IE-00291
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R2 | Tr
| IE | OL1-2R06-0035 | GENERAL DESIGN RULES FOR INSTRUMENTATION AND CONTROL OF PACKAGED EQUIPMENT |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00056
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2R06-1301 | PROGAMMABLE LOGIC CONTROLLER |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00291
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: R07
| ME | OL1-2R07-0001 | TAGGING PROCEDURE |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-07-30 | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PM-00001 | TPSK-LSPA1-T-ME-00279
[6 empty] | Return Date | 2018-08-22
[6 empty] | Owner Cmmt* | A4 | Tr
| ME | OL1-2R07-0010 | EQUIPMENT PRESERVATION |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00149
Return Date
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2R07-0018 | UNITS OF MEASUREMENT |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00080
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2R07-0020 | ELECTRICAL AND INSTRUMENT INTERFACE PHILOSOPHY |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R07-0023 | DRAFTING PROCEDURE FOR 2D DRAWINGS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00089
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2R07-0025 | REQUIREMENTS FOR EQIPMENT SUPPLIER 3D MODEL |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00108
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | Tr
| ME | OL1-2R07-0026 | PROJECT DESIGN BASIS |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00110
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | Tr
Category Code: R08
| CON | OL1-2R08-0003 | INSTRUMENT INSTALLATION |  | Class 3 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00122
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: R93
Category Code: S08
Category Code: S09
Category Code: S10
Category Code: S12
Category Code: S13
Category Code: S22
Category Code: S23
Category Code: S30
Category Code: S92
| ES | OL1-2S92-0001 | PROJECT HSSE PLAN |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ES-00129
Return Date
[6 empty] | Owner Cmmt* | Tr
| ES | OL1-2S92-0002 | INCIDENT INVESTIGATION AND REPORTING PROCEDURE |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ES-00152
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: T11
Category Code: T12
Category Code: T16
Category Code: T17
Category Code: T31
Category Code: T92
Category Code: V92
| IF | OL1-2V92-0014 | INTERFACE MANAGEMENT PLAN |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IF-00138
[6 empty] | Return Date | 2018-10-25
[6 empty] | Owner Cmmt* | R2
Category Code: W01
| PC | OL1-2W01-0001 | PLANT AND SECTION CODES |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-10 | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00019 | TPSK-LSPA1-T-PC-00076
[6 empty] | Return Date | 2018-08-22
[6 empty] | Owner Cmmt* | A2 | Tr
| PC | OL1-2W01-0002 | PLANT AND ZONE CODES |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-09 | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00015 | TPSK-LSPA1-T-PC-00077
[6 empty] | Return Date | 2018-08-17 | 2018-10-17
[6 empty] | Owner Cmmt* | A4 | R2
Category Code: W90
| PC | OL1-2W90-0001 | FIRE FIGHTING BASIC DESIGN REPORT FOR PACKAGE A1 |  | Class 3 | Purpose** | IFI | IFI
[6 empty] | Rev. | 0 | 1
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-10 | 2018-10-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00020 | TPSK-LSPA1-T-PM-00187
[6 empty] | Return Date | 2018-08-20
[6 empty] | Owner Cmmt* | R2 | Tr
Category Code: W91
| PC | OL1-2W91-0001 | MASTER DOCUMENT INDEX (MDI) |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PM-00186
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: W92
| PC | OL1-2W92-0001 | COORDINATION PROCEDURE |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PM-00001
[6 empty] | Return Date | 2018-08-22
[6 empty] | Owner Cmmt* | R2
| PC | OL1-2W92-0003 | PROJECT DOCUMENT CODING |  | Class 1 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-07-30 | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PM-00001 | TPSK-LSPA1-T-PC-00240
[6 empty] | Return Date | 2018-08-22
[6 empty] | Owner Cmmt* | A4 | Tr
| PC | OL1-2W92-0004 | DOCUMENT MANAGEMENT PROCEDURE |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00013
[6 empty] | Return Date | 2018-08-29
[6 empty] | Owner Cmmt* | R2
| PC | OL1-2W92-0006 | TPSK PROJECT DIRECTORATE ORGANIZATION CHART |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00010
Return Date
[6 empty] | Owner Cmmt* | Tr
| PC | OL1-2W92-0007 | TPSK ROC ORGANIZATION CHART |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00030
Return Date
[6 empty] | Owner Cmmt* | Tr
| PC | OL1-2W92-0009 | CRITICALITY RATING PROCEDURE |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00033
[6 empty] | Return Date | 2018-10-01
[6 empty] | Owner Cmmt* | R2
| PC | OL1-2W92-0011 | TPSK HOC ORGANIZATION CHART |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PM-00146
Return Date
[6 empty] | Owner Cmmt* | Tr
| PC | OL1-2W92-0012 | ITC PLAN |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PM-00197
Return Date
[6 empty] | Owner Cmmt* | Tr
| PC | OL1-2W92-0013 | PROJECT EXECUTION PLAN |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00118
Return Date
[6 empty] | Owner Cmmt* | Tr
| PC | OL1-2W92-0015 | PRESCRIPTIONS FOR PREPARATION OF MANUFACTURING DATA RECORD BOOK |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00047
Return Date
[6 empty] | Owner Cmmt* | Tr
| PC | OL1-2W92-0016 | REPORTING PROCEDURE |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00083
Return Date
[6 empty] | Owner Cmmt* | Tr
| PC | OL1-2W92-0018 | ENGINEERING EXECUTION PLAN |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PM-00170
Return Date
[6 empty] | Owner Cmmt* | Tr
| PC | OL1-2W92-0019 | PROJECT CONTROL PROCEDURE |  | Class 1 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00156
Return Date
[6 empty] | Owner Cmmt* | Tr
| PC | OL1-2W92-0020 | TPSK SOC ORGANIZATION CHART |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00157
Return Date
[6 empty] | Owner Cmmt* | Tr
| PC | OL1-2W92-0021 | TPSK KLOC ORGANIZATION CHART |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00171
Return Date
[6 empty] | Owner Cmmt* | Tr
| PC | OL1-2W92-2122 | PROJECT ENGINEERING PLAN - PACKAGE A1 - FURNACES - HOUSTON SCOPE (INTERNAL ONLY) |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PM-00220
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: W95
| PC | OL1-2W95-5000 | MONTHLY PROGRESS REPORT AS OF OCTOBER 15TH 2018 |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00195
Return Date
[6 empty] | Owner Cmmt* | Tr
Category Code: X01
| PC | OL1-2X01-0001 | PAYMENT AND INVOICING PROCEDURE |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00023
Return Date
[6 empty] | Owner Cmmt* | Tr